## Scoring template
|  |  |  | Template Details: | v1 - Tx
Dropdown input | Manual input | Template will load information from the Approved Accomplishment File based on the AR# entered in cell C11 and is reflective of the Alternative listed in the approved Accomplishment File only (info from other alternatives will not be brought in). If an AR is not in the ACC File, "#N/A" will be displayed in the fields that contain lookups. Please update any/all information as required. |  | Save Completed Template As: | Tx - Power Systems_11111_Watson TS Power System Upgrade_Watson Power SystemSystem Improvement
Allocation Grouping | Tx - Power Systems
Investment title
Investment status
Scorer | James Warburton
Date scored | 2018-06-27
Investment information
AR | 11111 | Parent/Child AR# | None | NOTE: Pre-populated data is based on ACC Alternative: | #VALUE! | SDOC Breakdown
Tranche Identifier | Watson Power System | Is this alternative aligned to the Tx Filing alternative? | YES | Driver Title | System Capability Reinforcement | Driver Owner | #VALUE!
Alternative Identifier | System Improvement | Is this the Recommended Alternative? | YES | ISD | #VALUE! | ISD description | Transmission Station Demand and Spares
A/R Name | Watson TS Power System Upgrade | Driver | #VALUE! | Investment Code - Primary | #VALUE! | Prog/Proj | Project
Investment strategy | Currently station has two 115 kV breakers each connecting a line to a transformer. One of the lines is a T- tap connection; effectively one of the breakers is connecting 2 segments of lines to one transformer. Station is proposed to be converted to a 5-breaker ring bus by adding 3 more breakers; two feeders for transformers T1 and T2, and 3 feeders for 115 kV Magpie, 115 kV No. 1 High Falls and 115 kV No.2 High Falls lines. Additionally, this project entails the replacement of 12KV Switchgear equipment at Watson TS. There have been known alignement issues with the existing breakers with the racking mechanism often breaking, an issue that has already occurred in the current year. The problem is often compounded by the forced outages that often need to be taken on the Number 1 and 2 Wawa local distribution feeders. | Investment Stage | Short Term Planning | AIP Code Description | #VALUE! | Investment Owner | #VALUE!
Potential driver reorganization
Scoring background
Disaggregated Program? | YES | Data Quality | Medium
Flagging
For flags that do not apply, please either select FALSE or leave blank
Mandatory flags |  |  | Discretionary flags
Flag | TRUE/FALSE | Rationale | Flag | TRUE/FALSE | Rationale
3rd Party Request | False | #VALUE! | Capital Sustainment | False | #VALUE!
Compliance | False | #VALUE! | Corrective Maintenance | False | #VALUE!
Contracts | False | #VALUE! | Customer | False | #VALUE!
In-flight | False | #VALUE! | Emerging Risk | True | Known issues with the racking mechanism and alignment have been more frequent and cause outages to the local distribution feeders
Load Growth | False | #VALUE! | Political | False | #VALUE!
|  |  | Prev Maintainence | False | #VALUE!
|  |  | Productivity Embedded | False | #VALUE!
|  |  | Productivity Enablement | False | #VALUE!
|  |  | Strategic | False | #VALUE!
Multi-asset considerations
Multi-Asset Risk? | NO
Asset scored
Risk scoring
Reportable-Unit
Safety scoring
Risk Multiplier (Unitized Risk) | 3
Safety - WRDI | N/A | Safety Consequence Type | Impact on employee or contractor | Safety Probability Type | Probability of event occurring in next year
Safety - Baseline Impact Score | 1 | Safety - Baseline Impact Description | N/A | Safety - Residual Impact Score | 1 | Safety - Residual Impact Description | N/A
Safety - Baseline Probability Score | 1 | Safety - Baseline Probability Description | Very Low | Safety - Residual Probability Score | 1 | Safety - Residual Probability Description | Very Low
Environment scoring
Risk Multiplier (Unitized Risk) | 3
Environment - WRDI | N/A | Environment Consequence Type | Plant, animal or habitat impact | Environment Probability Type | Expected time to event
Environment - Baseline Impact Score | 1 | Environment - Baseline Impact Description | N/A | Environment - Residual Impact Score | 1 | Environment - Residual Impact Description | N/A
Environment - Baseline Probability Score | 1 | Environment - Baseline Probability Description | Very Low | Environment - Residual Probability Score | 1 | Environment - Residual Probability Description | 1
Reliability scoring
Risk Multiplier (Unitized Risk) | 3 | Dx or Tx Reliability Risk?
Reliability - WRDI | During a fault condition, isolating a segment of the line while maintaining the other segment is not possible due to current configuration. This results in outages to generation an transmission feeders on the bus. | Reliability Consequence Type | Impact on customers | Reliability Probability Type | Probability of event occurring in next year
Reliability - Baseline Impact Score | 5 | Reliability - Baseline Impact Description | Inability for station to capabily transfer 150MVA via bussing system | Reliability - Residual Impact Score | 5 | Reliability - Residual Impact Description | Inability for station to capabily transfer 150MVA via bussing system
Reliability - Baseline Probability Score | 4 | Reliability - Baseline Probability Description | 1 every 3-10 years | Reliability - Residual Probability Score | 1 | Reliability - Residual Probability Description | Less than 1 every 100 years
Financial scoring (enter using uninflated literal dollars)
OMA/Annual Savings - Description |  | OM&A annual savings | If specific annual savings are known, please enter them in the section below (column H71), otherwise enter the avg annual savings here | OMA Savings Confidence Level |  | OMA Savings Confidence Type
Capital Deferral - Description |  | Capital Deferral Amount |  | Capital Deferral Confidence Level |  | Capital Deferral Confidence Type
Year Capex would be spent in abscene of this investment
Year Capex will be spent as a result of this investment
Investment costs (enter in literal dollars)
Insert dollars based on start date
Uninflated Dollars? |  | Removal %
[6 empty] | OMA Annual Savings (specific) | Savings entered here are related to the financial scoring section above, they will not be deducted from your investment costs
2019-Gross |  | 2019-Removal | #VALUE! | 2019-CC | #VALUE! | 2019-OMA Annual Savings | 0
2020-Gross |  | 2020-Removal | #VALUE! | 2020-CC | #VALUE! | 2020-OMA Annual Savings | 0
2021-Gross |  | 2021-Removal | #VALUE! | 2021-CC | #VALUE! | 2021-OMA Annual Savings | 0
2022-Gross |  | 2022-Removal | #VALUE! | 2022-CC | #VALUE! | 2022-OMA Annual Savings | 0
2023-Gross |  | 2023-Removal | #VALUE! | 2023-CC | #VALUE! | 2023-OMA Annual Savings | 0
2024-Gross | 1000000 | 2024-Removal | #REF! | 2024-CC | #VALUE! | 2024-OMA Annual Savings | 0
2025-Gross | 3700000 | 2025-Removal | #REF! | 2025-CC | #VALUE! | 2025-OMA Annual Savings | 0
2026-Gross |  | 2026-Removal | #VALUE! | 2026-CC | #VALUE! | 2026-OMA Annual Savings | 0
2027-Gross |  | 2027-Removal | #VALUE! | 2027-CC | #VALUE! | 2027-OMA Annual Savings | 0
2028-Gross |  | 2028-Removal | #VALUE! | 2028-CC | 0 | 2028-OMA Annual Savings | 0
[6 empty] | 2029-OMA Annual Savings | 0
Timing
Start date is date of first cash flow. Earliest possible date of first cash flow cannot be earlier than Jan. 1, 2019. Leave latest possible date of first cash flow blank if not mandatory
Start Date | 2024-01-01 | Earliest Start Date | 2024-01-01
EMPP date | 2024-01-01 | Latest Start Date | 2024-01-01
All-IS Date | 2025-12-31 | Project Is Shiftable?
Units
Insert units based on start date
Reportable-Unit | #VALUE!
2019-ACCOMP | #VALUE!
2020-ACCOMP | #VALUE!
2021-ACCOMP | #VALUE!
2022-ACCOMP | #VALUE!
2023-ACCOMP | #VALUE!
2024-ACCOMP | #VALUE!
Other investment information
OEB Investment Category | #VALUE! | Estimate Quality |  | Asset Analytics Used In Investment Development
LOB(s) | #VALUE! | Customer Realtionship Code | #VALUE! | Comments
LOB name | #VALUE! | Area | #VALUE! | # of Breaker Reductions | #VALUE!
OEB Section 92 Status | #VALUE! | EA Status | #VALUE! | # of Transformer Reductions | #VALUE!
Plan Over Plan |  | Planning Estimate Category |  | Costs updated based on:
Asset Replacements (DO NOT MODIFY ANYTHING OTHER THAN QUANTITY)
Asset Type | Voltage / Sub - Category | Quantity
AC Transfer Scheme | BULK | [6 empty] | AC-BULK
| DESN | [6 empty] | AC-DESN
| UNSPECIFIED | [6 empty] | AC
AC Transfer Scheme |  | 0
Battery | 48V | [6 empty] | DCBATTERY-48V
| 125V | [6 empty] | DCBATTERY-125V
| 250V | [6 empty] | DCBATTERY-250V
| UNSPECIFIED | [6 empty] | DCBATTERY
Battery |  | 0
Breakers (HV) | 115kV | 3 | [5 empty] | BRHV-115kV
| 230kV | [6 empty] | BRHV-230kV
| 345kV | [6 empty] | BRHV-345kV
| 500kV | [6 empty] | BRHV-500kV
| UNSPECIFIED | [6 empty] | BRHV
Breakers (HV) |  | 3
Breakers (LV) | 13.8kV | 12 | [5 empty] | BRLV-13.8kV
| 27.6kV | [6 empty] | BRLV-27.6kV
| 44kV | [6 empty] | BRLV-44kV
| UNSPECIFIED | [6 empty] | BRLV
Breakers (LV) |  | 12
Capacitor Banks | 13.8kV | [6 empty] | SC-13.8kV
| 27.6kV | [6 empty] | SC-27.6kV
| 44kV | [6 empty] | SC-44kV
| 115kV | [6 empty] | SC-115kV
| 230kV | [6 empty] | SC-230kV
| 345kV | [6 empty] | SC-345kV
| 500kV | [6 empty] | SC-500kV
| UNSPECIFIED | [6 empty] | SC
Capacitor Banks |  | 0
Charger | 48V | [6 empty] | CHARGER-48V
| 125V | [6 empty] | CHARGER-125V
| 250V | [6 empty] | CHARGER-250V
| UNSPECIFIED | [6 empty] | CHARGER
Charger |  | 0
DC Transfer Scheme | DC Transfer Scheme | [6 empty] | DC
DC Transfer Scheme |  | 0
HVITs | 115kV | [6 empty] | HVIT-115kV
| 230kV | [6 empty] | HVIT-230kV
| 345kV | [6 empty] | HVIT-345kV
| 500kV | [6 empty] | HVIT-500kV
| UNSPECIFIED | [6 empty] | HVIT
HVITs |  | 0
Insulators | 13.8kV | [6 empty] | IN-13.8kV
| 27.6kV | [6 empty] | IN-27.6kV
| 44kV | [6 empty] | IN-44kV
| 115kV | [6 empty] | IN-115kV
| 230kV | [6 empty] | IN-230kV
| 345kV | [6 empty] | IN-345kV
| 500kV | [6 empty] | IN-500kV
| UNSPECIFIED | [6 empty] | IN
Insulators |  | 0
Line Refurb (Km) | Line Refurb (Km) | [6 empty] | LINERFRB
Line Refurb (Km) |  | 0
MVGIS (Buses) | 13.8kV | [6 empty] | MVGIS-13.8kV
| 27.6kV | [6 empty] | MVGIS-27.6kV
| 44kV | [6 empty] | MVGIS-44kV
| UNSPECIFIED | [6 empty] | MVGIS
MVGIS (Buses) |  | 0
OPGW (Km) | OPGW (Km) | [6 empty] | OPGW
OPGW (Km) |  | 0
Overhead Conductor (Km) | Overhead Conductor (Km) | [6 empty] | OHCD
Overhead Conductor (Km) |  | 0
PCT Box | PCT Box | [6 empty] | PCT
PCT Box |  | 0
Protections | Protections | [6 empty] | PR
Protections |  | 0
Reactors | 13.8kV | [6 empty] | RE-13.8kV
| 27.6kV | [6 empty] | RE-27.6kV
| 44kV | [6 empty] | RE-44kV
| 115kV | [6 empty] | RE-115kV
| 230kV | [6 empty] | RE-230kV
| 345kV | [6 empty] | RE-345kV
| 500kV | [6 empty] | RE-500kV
| UNSPECIFIED | [6 empty] | RE
Reactors |  | 0
Regulators | 13.8kV | [6 empty] | REG-13.8kV
| 27.6kV | [6 empty] | REG-27.6kV
| 44kV | [6 empty] | REG-44kV
| 115kV | [6 empty] | REG-115kV
| 230kV | [6 empty] | REG-230kV
| 345kV | [6 empty] | REG-345kV
| 500kV | [6 empty] | REG-500kV
| UNSPECIFIED | [6 empty] | REG
Regulators |  | 0
RTU | BULK | [6 empty] | RTU-BULK
| DESN | [6 empty] | RTU-DESN
| UNSPECIFIED | [6 empty] | RTU
RTU |  | 0
Security - DNU | Security - DNU | [6 empty] | SECURITY
Security - DNU |  | 0
Shieldwire (Km) | Shieldwire (Km) | [6 empty] | NCSH
Shieldwire (Km) |  | 0
Spill Containment | Spill Containment | [6 empty] | SPILL
Spill Containment |  | 0
SS Transformers | BULK | [6 empty] | SS-BULK
| DESN | [6 empty] | SS-DESN
| UNSPECIFIED | [6 empty] | SS
SS Transformers |  | 0
Steel Structures | 13.8kV | [6 empty] | PLST-13.8kV
| 27.6kV | [6 empty] | PLST-27.6kV
| 44kV | [6 empty] | PLST-44kV
| 115kV | [6 empty] | PLST-115kV
| 230kV | [6 empty] | PLST-230kV
| 345kV | [6 empty] | PLST-345kV
| 500kV | [6 empty] | PLST-500kV
| UNSPECIFIED | [6 empty] | PLST
Steel Structures |  | 0
Surge Arrestor | 13.8kV | [6 empty] | SA-13.8kV
| 27.6kV | [6 empty] | SA-27.6kV
| 44kV | [6 empty] | SA-44kV
| 115kV | [6 empty] | SA-115kV
| 230kV | [6 empty] | SA-230kV
| 345kV | [6 empty] | SA-345kV
| 500kV | [6 empty] | SA-500kV
| UNSPECIFIED | [6 empty] | SA
Surge Arrestor |  | 0
Switches - Circuit Switchers (HV) | 115kV | [6 empty] | SWCS-115kV
| 230kV | [6 empty] | SWCS-230kV
| 345kV | [6 empty] | SWCS-345kV
| 500kV | [6 empty] | SWCS-500kV
| UNSPECIFIED | [6 empty] | SWCS
Switches - Circuit Switchers (HV) |  | 0
Switches (HV) | 115kV | [6 empty] | SWAB-115kV
| 230kV | [6 empty] | SWAB-230kV
| 345kV | [6 empty] | SWAB-345kV
| 500kV | [6 empty] | SWAB-500kV
| UNSPECIFIED | [6 empty] | SWAB
Switches (HV) |  | 0
Telecom - DNU - DNU | Telecom - DNU - DNU | [6 empty] | TC
Telecom - DNU - DNU |  | 0
Tower Coating (Structures) | Tower Coating (Structures) | [6 empty] | PLCOATING
Tower Coating (Structures) |  | 0
Transformers | 115kV (Non-Standard) | [6 empty] | TF-115kV
| 230kV (Non-Standard) | [6 empty] | TF-230kV
| AUTO S230-A(239-121kV) - 125MVA | [6 empty] | TF-AUTO S230-A(239-121kV) - 125MVA
| AUTO S230-B(239-121kV) - 250MVA | [6 empty] | TF-AUTO S230-B(239-121kV) - 250MVA
| AUTO S500-A(500-240kV) - 750MVA | [6 empty] | TF-AUTO S500-A(500-240kV) - 750MVA
| S115-A(115-14kV) - 42MVA | [6 empty] | TF-S115-A(115-14kV) - 42MVA
| S115-B(110-28kV) - 42MVA | [6 empty] | TF-S115-B(110-28kV) - 42MVA
| S115-C(115-44kV) - 42MVA | [6 empty] | TF-S115-C(115-44kV) - 42MVA
| S115-D(110-14-14kV) - 75MVA | [6 empty] | TF-S115-D(110-14-14kV) - 75MVA
| S115-E(110-28kV) - 83MVA | [6 empty] | TF-S115-E(110-28kV) - 83MVA
| S115-F(110-14-14kV) - 100MVA | [6 empty] | TF-S115-F(110-14-14kV) - 100MVA
| S230-A(215-28kV) - 83MVA | [6 empty] | TF-S230-A(215-28kV) - 83MVA
| S230-B(215-44kV) - 83MVA | [6 empty] | TF-S230-B(215-44kV) - 83MVA
| S230-C(215-14-14kV) - 100MVA | [6 empty] | TF-S230-C(215-14-14kV) - 100MVA
| S230-D(215-28-28kV) - 125MVA | [6 empty] | TF-S230-D(215-28-28kV) - 125MVA
| S230-E(215-44kV) - 125MVA | [6 empty] | TF-S230-E(215-44kV) - 125MVA
| UNSPECIFIED | [6 empty] | TF
Transformers |  | 0
Undefined | Undefined | [6 empty] | Undefined
Undefined |  | 0
Underground Conductor (Km) | Underground Conductor (Km) | [6 empty] | UGCD
Underground Conductor (Km) |  | 0
Unspecified - DNU | Unspecified - DNU | [6 empty] | UNSP
Unspecified - DNU |  | 0
Wood Poles (Structures) | Wood Poles (Structures) | [6 empty] | PLWD
Wood Poles (Structures) |  | 0
Write-off
Would cancelling this investment create a write-off
If TRUE, enter cost in $
Note on B11: Cells in green will be populated if the AR entered is inclued in Approved Accomplishment File
Note on B12: e.g., portion of disaggregated program (assign unique names to each tranche e.g. critical poles, poor poles, fair poles, etc.)
Note on B13: e.g., alternative for a station (assign unique names like 'refurb' 'repair' etc.)
Note on B43: Only use in Non Multi-Asset Risk Investments
Note on B50: Only use in Non Multi-Asset Risk Investments
Note on B57: Only use in Non Multi-Asset Risk Investments
Note on B70: Indicated "Yes" if an uninflated unit price is being used and therefore, inflation is not factored in as part of your costs. Note that any pre-populated costs are based on inflated values
Note on D65: Enter the year Capex would need to be spent if this investment does not proceed
Note on D66: Enter the year Capex will now be spent as result of this investment Note Must be outside the current Planning Window If Capex will be deferred indefintely, leave this field blank
Note on F2: Nomenclature: [Common Allocation]_[AR]_[AR Name]_[Tranche]_[Alternative]
Note on G102: If no, indicate why
Note on H63: Indicate what was used to determine the confidence level. Options are aligned with headings in the revised Taxonomies
Note on H64: Indicate what was used to determine the confidence level. Options are aligned with headings in the revised Taxonomies

## Sheet3 (hidden)
Driver Owner | (empty)
(empty)
cindy.copp@hydroone.com
Daila.Dzintars@HydroOne.com
emre.aydin@HydroOne.com
Godfrey.Holder@HydroOne.com
hassan.hamzeh@hydroone.com
Imran.Merali@HydroOne.com
James.Mardegan@HydroOne.com
jj.blais@HydroOne.com
john.boldt@HydroOne.com
joseph.parete@hydroone.com
Kevin.Mancherjee@HydroOne.com
lincoln.frost-hunt@hydroone.com
lyla.garzouzi@hydroone.com
Mike.Tanaskovic@HydroOne.com
Miroslav.Kostic@HydroOne.com
Peter.Mitskos@HydroOne.com
Rick.Haier@HydroOne.com
robert.berardi@HydroOne.com
Robert.Reinmuller@HydroOne.com
ryan.boudreau@HydroOne.com
ted.lyberogiannis@HydroOne.com
welchw@hydroone.com
Driver Owner
Total Result

## Lookups 2 (hidden)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99
Appropriation request | Description of appropriation request | Position ID | Resp.Cctr | LOB (as per SAP AR) | LOB Name | Investment Code (as per Ref AR in SAP) | Investment Code - Accomplishment File via AR (based on Approved ACC) | AIP Code Reference | AIP Code Mismatch? | AIP Code to use | Investment Code Name | ISD | ISD Description | Driver Title | Driver Owner | Investment Owner | OEB Category | Area | OEB Section 92 Status | Customer Relationship Code | EA Status | SAP Project/Program | SAP Variant User Status | Status | Status to display | Reportable Unit | 2018-Net | 2019-Net | 2020-Net | 2021-Net | 2022-Net | 2023-Net | 2024-Net | 2025-Net | 2026-Net | 2027-Net | 2018-Gross | 2019-Gross | 2020-Gross | 2021-Gross | 2022-Gross | 2023-Gross | 2024-Gross | 2025-Gross | 2026-Gross | 2027-Gross | 2018-Removal | 2019-Removal | 2020-Removal | 2021-Removal | 2022-Removal | 2023-Removal | 2024-Removal | 2025-Removal | 2026-Removal | 2027-Removal | All-RemovalPerc | Removal % | 2018-CC | 2019-CC | 2020-CC | 2021-CC | 2022-CC | 2023-CC | 2024-CC | 2025-CC | 2026-CC | 2027-CC | 2018-ACCOMP | 2019-ACCOMP | 2020-ACCOMP | 2021-ACCOMP | 2022-ACCOMP | 2023-ACCOMP | 2024-ACCOMP | 2025-ACCOMP | 2026-ACCOMP | 2027-ACCOMP | BCS Approval Date | All-IS | Third Party Request | Third Party Request Description | Immediate / Short-Term Compliance Requirement | Immediate / Short-Term Compliance Requirement Description | Forecast is based on signed 3rd Party Contracts | Contractual / Political Commitments Description | Corrective Maintenance/Demand Replacements | Customer Engagement | Customer Engagement Considerations | Political Commitments | Preventative Maintenance/System Renewal | Productivity Embedded | Productivity Enablement | Strategic | Strategic | # of Breaker Reductions | # of Transformer Reductions | Alternative Name
17005 | Kingston Gardiner TS: Increase 230-44 kV Capactiy | N.T.C.2.11 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Load Customer Connection | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17009 | Thunder Bay TGS- Bus Reconfiguration | N.T.C.2.02 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Local Area Supply | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17015 | Dymond TS M1 Feeder Relief | N.D.C.2.02 | 7374 | 205 | LINES | UNPLND |  |  | Yes |  |  |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | [6 empty] | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17018 | Greely DS F4 | N.D.C.2.02 | 7374 | 205 | LINES | UNPLND |  |  | Yes |  |  |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | [6 empty] | Project | EMPP AWRD | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17020 | Muskoka TS 2M6 Feeder Rehabilitation - Part 1 | N.D.C.1.07 | 7374 | 205 | LINES | 6 |  |  | Yes |  |  |  |  | Lines | emre.aydin@HydroOne.com | [6 empty] | Program | ACTN EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17037 | Long Lac T1: Replace End-of-Life 115-44 kV Transfo | N.T.C.2.11 | 7700 | 203 | PROJECT DELIVERY | 157 |  |  | Yes |  |  |  |  | Load Customer Connection | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17057 | Kingston Gardiner TS - Install New Feeder Protecti | N.T.C.2.20 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Performance Enhancement | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | INSC DETL | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17071 | Toronto AreaTelecom Cable Removals | N.T.C.1.25 | 7700 | 203 | PROJECT DELIVERY | AIP000650 |  | AIP000650 | Yes | AIP000650 |  |  |  | Auxiliary Telecommunication Equipment | Miroslav.Kostic@HydroOne.com | [6 empty] | Program | EMPP ACCP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17087 | Keith TS: Upgrade T11/T12 Provide 250MVA Autos | N.T.C.2.02 | 7700 | 203 | PROJECT DELIVERY | DO NOT USE |  |  | Yes |  |  |  |  | Local Area Supply | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | DETL INSC | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17112 | 2007+2008 Manby TS - Major Drainage Improvements | N.T.C.1.21 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Infrastructure | James.Mardegan@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17113 | 2008 Major Drainage Refurbishment | N.T.C.1.21 | 7700 | 203 | PROJECT DELIVERY | AIP000625 |  | AIP000625 | Yes | AIP000625 |  |  |  | Infrastructure | James.Mardegan@HydroOne.com | [6 empty] | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17123 | Station Cap and Pin Insulator Replacement | N.T.C.1.18 | 7700 | 203 | PROJECT DELIVERY | AIP000572 |  | AIP000572 | Yes | AIP000572 |  |  |  | Other Power Equipment | James.Mardegan@HydroOne.com | [6 empty] | Program | EMPP ACTN | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17125 | Station String Insulator Replacement | N.T.C.1.18 | 7700 | 203 | PROJECT DELIVERY | AIP000572 |  | AIP000572 | Yes | AIP000572 |  |  |  | Other Power Equipment | James.Mardegan@HydroOne.com | [6 empty] | Program | ACTN EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17128 | Nanticoke TS: Add 500 kV, 350 MVAr SVC | N.T.C.2.03 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Network Transfer Capability | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17130 | Grainger Jct: Install 2x230kV Switches on V71/75P | N.T.C.2.02 | 7700 | 203 | PROJECT DELIVERY | AIP000697 | AIP000697 | AIP000697 | No | AIP000697 | Grainger Jct: Install 2x230kV breakers on Circuits | 0 |  | Local Area Supply | Robert.Reinmuller@HydroOne.com | E.Warren.King@HydroOne.com | System Service | 0 | Not Required | 02 - Expectation (no agreement) | Required | Project | ACCP EMPP | Executing | Executing |  | 2574294.5423 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2574294.5423 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43250 | [13 empty] | FALSE |  | 0 | 0 | Alternative 1
17134 | Enbridge Ontario Wind Power A and B | N.T.C.2.12 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Generator Customer Connection | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17135 | 2008 Burlington TS Wood Pole Structures 115 kV K | N.T.C.1.21 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Infrastructure | James.Mardegan@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17136 | BSPS Modifications for Bruce for 2009 | N.T.C.2.03 | 7700 | 203 | PROJECT DELIVERY | 81 |  |  | Yes |  |  |  |  | Network Transfer Capability | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | EMPP AWRD | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17138 | Cable & Pothead Replacement Program | N.T.C.1.18 | 7700 | 203 | PROJECT DELIVERY | AIP000566 |  | AIP000566 | Yes | AIP000566 |  |  |  | Other Power Equipment | James.Mardegan@HydroOne.com | [6 empty] | Program | EMPP ACTN | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17142 | 2007 & 2008 Load Center and Generator Purchase | N.T.C.1.18 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Other Power Equipment | James.Mardegan@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17144 | Fire Detection Upgrade Program | N.T.C.1.21 | 7700 | 203 | PROJECT DELIVERY | AIP000628 | AIP000628 | AIP000628 | No | AIP000628 | Fire Detection Upgrade Program | 0 |  | Infrastructure | James.Mardegan@HydroOne.com | mark.truchanowicz@hydroone.com | System Renewal | N/A | 0 | 03 - None (default) | 0 | Program | ACTN EMPP | Executing | Short Term Planning | # of Systems | 591652.6364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 591652.6364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43190 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Asset Optimal - Modified
17147 | Protection Replacement Program | N.T.C.1.19 | 7700 | 203 | PROJECT DELIVERY | AIP000609A |  | AIP000609 | Yes | AIP000609 |  |  |  | Protection Control & Metering Equip | Miroslav.Kostic@HydroOne.com | [6 empty] | Program | ACCP EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17148 | Elgin TS; Station Refurbishment | N.T.C.1.08 | 7700 | 203 | PROJECT DELIVERY | AIP005149 | AIP005149 | AIP005149 | No | AIP005149 | Elgin TS T1/T2/T3/T4; T1,T2,T3,T4 MVGI and Component Replacement | SR-02 | Station Reinvestment Projects | System Re-investment | James.Mardegan@HydroOne.com | mark.truchanowicz@hydroone.com | System Renewal | Hamilton Niagara | 0 | 02 - Expectation (no agreement) | 0 | Project | EMPP ACTN | Executing | Executing |  | 14049810.1506 | 11319736.0492 | 1823480.169 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15672473.7526 | 12567829.1927 | 2031218.3646 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1057512.592 | -852023.1435 | -137251.1955 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | -565151.01 | -396070 | -70487 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43815 |  |  |  |  | False | [8 empty] | FALSE |  | 0 | 2 | Alternative1-Station upgrade
17149 | Tone Equipment Replacement | N.T.C.1.25 | 7700 | 203 | PROJECT DELIVERY | AIP000662 |  | AIP000662 | Yes | AIP000662 |  |  |  | Auxiliary Telecommunication Equipment | Miroslav.Kostic@HydroOne.com | [6 empty] | Program | ACCP EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17150 | PC&T Systems | N.T.C.1.19 | 7700 | 203 | PROJECT DELIVERY | AIP000607 |  | AIP000607 | Yes | AIP000607 |  |  |  | Protection Control & Metering Equip | Miroslav.Kostic@HydroOne.com | [6 empty] | Program | ACCP EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17168 | DFR Sustainment Program | N.T.C.1.19 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Protection Control & Metering Equip | Miroslav.Kostic@HydroOne.com | [6 empty] | Program | EMPP ACCP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17185 | Orangeville TS - Transmission Station Re-Inve | N.T.C.1.08 | 7700 | 203 | PROJECT DELIVERY | AIP000432 |  | AIP000432 | Yes | AIP000432 |  |  |  | System Re-investment | James.Mardegan@HydroOne.com | [6 empty] | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17192 | Kingsville TS: T1, T2, T3, T4 & Component Repl. | N.T.C.1.08 | 7700 | 203 | PROJECT DELIVERY | AIP000423 | AIP000423 | AIP000423 | No | AIP000423 | Kingsville TS: T1, T2, T3, T4 & Component Replacement Phase 1 | SR-05 | Load Station Transformer Replacement Projects | System Re-investment | James.Mardegan@HydroOne.com | mark.truchanowicz@hydroone.com | System Renewal | Western | Not Required | 03 - None (default) | Not Required | Project | EMPP ACCP | Executing | Executing |  | 7537651.7659 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8076055.4635 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -538403.6976 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -6.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43066 | 44058 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 2 | Component Replacement (Accelerated)
17196 | 2007 Tx OH Component Analysis - Kinectrics | N.T.M.1.20 | 4337 | 223 | SMART METERS | UNPLND |  |  | Yes |  |  |  |  | Overhead Lines | hassan.hamzeh@hydroone.com | [6 empty] | Program | EMPP AWRD | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17197 | 2008 Tx OH Component Analysis Kinectrics | N.T.M.1.20 | 4337 | 223 | SMART METERS | UNPLND |  |  | Yes |  |  |  |  | Overhead Lines | hassan.hamzeh@hydroone.com | [6 empty] | Program | init BEST | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17200 | closed-2008 Overhead Transmission Lines RoW Vege | N.T.M.1.07 | 7362 | 204 | FORESTRY | UNPLND |  |  | Yes |  |  |  |  | Rights of Way | hassan.hamzeh@hydroone.com | [6 empty] | Program | AWRD EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17203 | PMR Maintenance & Leased Facilities | N.T.M.1.24 | 4048 | 213 | PLANNING | AIP001134 | AIP001134 | AIP001134 | No | AIP001134 | PMR Maintenance & Leased Facilities | 0 |  | Leased Facilities | Miroslav.Kostic@HydroOne.com | Sheraz.Majid@HydroOne.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | EMPP AWRD | Executing | Short Term Planning | Assumption - Retainer | 2632358.6211 | 2444493.3393 | 2497605.3032 | 2553999.5034 | 2605719.6337 | 2658315.7947 | 0 | 0 | 0 | 0 | 2632358.6211 | 2444493.3393 | 2497605.3032 | 2553999.5034 | 2605719.6337 | 2658315.7947 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1300 | 1300 | 1300 | 1300 | 1300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | True | PMR maintenance and lease contracts | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Asset Optimal
17206 | 2007 Station 48V DC/DC Converter Installation | N.T.C.1.20 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Ancillary Systems | James.Mardegan@HydroOne.com | [6 empty] | Program | EMPP ACCP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17209 | 2008 Demand Investments | N.D.C.2.02 | 7374 | 205 | LINES | UNPLND |  |  | Yes |  |  |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | [6 empty] | Program | EMPP ACCP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17216 | Supervisory Control for LV Reclosers | N.D.C.2.06 | 7716 | 224 | ENGINEERING | UNPLND |  |  | Yes |  |  |  |  | Smart Grid | ryan.boudreau@HydroOne.com | [6 empty] | Project | DETL ACTN | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17228 | 2007/2009 Tx PCB & Regulated Waste Storage Units | N.T.C.1.22 | 7700 | 203 | PROJECT DELIVERY | 1 |  |  | Yes | [12 empty] | Program | AWRD EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17240 | Cherrywood TS x Claireville TS: Unbundle 500kV cir | N.T.C.2.03 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Network Transfer Capability | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17241 | 2007 Power Equipment - Reliability Improvement Pro | N.T.M.1.16 | 7370 | 206 | TX LINES AND STATIONS | UNPLND |  |  | Yes |  |  |  |  | Power Equipment | Mike.Tanaskovic@HydroOne.com | [6 empty] | Program | EXTR EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17244 | Operations Support Tools - NOMS/UWPC /EL Repl (Tx) | N.T.C.3.06 | 4514 | 212 | INFO SOLUTIONS DIVISION | UNPLND |  |  | Yes |  |  |  |  | Grid Operating and Control Facilities | Godfrey.Holder@HydroOne.com | [6 empty] | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17247 | Kruger Port Alma Wind Farm 112 MW Generation Conne | N.T.C.2.12 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Generator Customer Connection | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17248 | Interface Protections to Fiber network – Ottawa | N.T.C.1.25 | 7700 | 203 | PROJECT DELIVERY | AIP000647 |  | AIP000647 | Yes | AIP000647 |  |  |  | Auxiliary Telecommunication Equipment | Miroslav.Kostic@HydroOne.com | [6 empty] | Project | EMPP ACTN | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17259 | Leaside TS x Bridgman TS: Build new 115kV circuit | N.T.C.2.02 | 7700 | 203 | PROJECT DELIVERY | AIP000703 |  | AIP000703 | Yes | AIP000703 |  |  |  | Local Area Supply | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17260 | Northeast Transmission Reinforcement: Install SVC | N.T.C.2.03 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Network Transfer Capability | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17269 | GCD 16- Northern Cross Gas Generation (GCD #16) | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Distribution Generation Connection | ryan.boudreau@HydroOne.com | [6 empty] | Project | DETL ACTN | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17279 | Stayner TS x Blue Mountain - Build 2 New 44 kV Fee | N.D.C.2.02 | 7374 | 205 | LINES | UNPLND |  |  | Yes |  |  |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | [6 empty] | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17285 | GCD 36- Belwood North Tie in on Hwy 9 (GCD# 36) | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Distribution Generation Connection | ryan.boudreau@HydroOne.com | [6 empty] | Project | DETL ACTN | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17288 | GCD 69A- Connection of Aeolian Proof Line EG (GCD# | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Distribution Generation Connection | ryan.boudreau@HydroOne.com | [6 empty] | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17314 | 2007 Tx R&D Technology Program -Kinectrics | N.T.M.2.21 | 4337 | 223 | SMART METERS | UNPLND |  |  | Yes |  |  |  |  | Technology Program | Daila.Dzintars@HydroOne.com | [6 empty] | Program | AWRD EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17318 | Caledonia TS: Add 2x27.6kV Feeder Breaker Positi | N.T.C.2.11 | 7700 | 203 | PROJECT DELIVERY | AIP005515 |  | AIP005515 | Yes | AIP005515 |  |  |  | Load Customer Connection | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | DETL HOLD | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17320 | Terry Fox MTS: Build New 230kV Line Tap | N.T.C.2.11 | 7700 | 203 | PROJECT DELIVERY | AIP000817 | AIP000817 | AIP000817 | No | AIP000817 | Terry Fox MTS: Build New 230kV Line Tap | 0 |  | Load Customer Connection | Robert.Reinmuller@HydroOne.com | Jean.Morneau@HydroOne.com | System Access | Western | 0 | 01 - Agreement (current/future) | 0 | Project | EMPP ACTN | Executing | Executing |  | 32803.5192 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32803.5192 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43190 | [13 empty] | FALSE |  | 0 | 0 | Alternative 1
17321 | Designated Substance and Hazardous Materials Manag | N.C.M.3.03 | 4337 | 223 | SMART METERS | UNPLND |  |  | Yes |  |  |  |  | Environment Health and Safety | welchw@hydroone.com | [6 empty] | Program | AWRD EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17323 | Designated Substances and Hazardous Material Manag | N.C.M.3.03 | 4337 | 223 | SMART METERS | UNPLND |  |  | Yes |  |  |  |  | Environment Health and Safety | welchw@hydroone.com | [6 empty] | Program | EMPP AWRD | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17324 | Health Fairs | N.C.M.3.03 | 4337 | 223 | SMART METERS | UNPLND |  |  | Yes |  |  |  |  | Environment Health and Safety | welchw@hydroone.com | [6 empty] | Program | AWRD EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17325 | AED Devices | N.C.M.3.03 | 4337 | 223 | SMART METERS | UNPLND |  |  | Yes |  |  |  |  | Environment Health and Safety | welchw@hydroone.com | [6 empty] | Program | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17326 | E-Learning | N.C.M.3.03 | 4337 | 223 | SMART METERS | UNPLND |  |  | Yes |  |  |  |  | Environment Health and Safety | welchw@hydroone.com | [6 empty] | Program | AWRD EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17327 | Learning Management System | N.C.M.3.03 | 4337 | 223 | SMART METERS | UNPLND |  |  | Yes |  |  |  |  | Environment Health and Safety | welchw@hydroone.com | [6 empty] | Program | EMPP AWRD | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17328 | Learning Management System | N.C.M.3.03 | 4337 | 223 | SMART METERS | UNPLND |  |  | Yes |  |  |  |  | Environment Health and Safety | welchw@hydroone.com | [6 empty] | Program | AWRD EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17335 | 2009 Distribution System Modifications | N.D.C.2.02 | 7374 | 205 | LINES | UNPLND |  |  | Yes |  |  |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17336 | 2009 Demand Investments | N.D.C.2.02 | 7374 | 205 | LINES | UNPLND |  |  | Yes |  |  |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | [6 empty] | Program | ACCP EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17338 | 2008 Small Distribution Lines Projects | N.D.C.1.07 | 7374 | 205 | LINES | 2 |  |  | Yes |  |  |  |  | Lines | emre.aydin@HydroOne.com | [6 empty] | Program | AWRD EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17343 | 2007 & 2008 Tx R&D Technology Program - EPRI | N.T.M.2.21 | 4337 | 223 | SMART METERS | UNPLND |  |  | Yes |  |  |  |  | Technology Program | Daila.Dzintars@HydroOne.com | [6 empty] | Program | EMPP AWRD | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17353 | End of Life Replacement of Wood Poles | N.D.C.1.02 | 7374 | 205 | LINES | AIP000128 | AIP000128 | AIP000128 | No | AIP000128 | Pole Replacement | ISD-SR-09 | Pole Replacement Program | Wood Pole Replacement | emre.aydin@HydroOne.com | Matthew.Bell@HydroOne.com | System Renewal | 0 | 0 | 03 - None (default) | 0 | Program | AWRD EMPP | Executing | Short Term Planning | # of Poles | 73834625.1435 | 112199122.5959 | 128059014.4158 | 130603801.4375 | 133157944.2548 | 0 | 0 | 0 | 0 | 0 | 83902983.1176 | 127499002.9499 | 145521607.2907 | 148413410.7244 | 151315845.7441 | 0 | 0 | 0 | 0 | 0 | -10068357.9741 | -15299880.354 | -17462592.8749 | -17809609.2869 | -18157901.4893 | 0 | 0 | 0 | 0 | 0 | -12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9600 | 14300 | 16000 | 16000 | 16000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Plan B Modified - Scenario 1
17354 | Connection of Windrush Skyway 8 Wind Farm A | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000199 |  | AIP000199 | Yes | AIP000199 | Large Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17356 | Joint Use and Line Relocations | N.D.C.1.03 | 7374 | 205 | LINES | UNPLND |  |  | Yes |  |  |  |  | Joint Use and Relocations | john.boldt@HydroOne.com | [6 empty] | Program | ACTN EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17361 | Defect Correction | N.D.M.1.02 | 7374 | 205 | LINES | AIP000231 | AIP000231 | AIP000231 | No | AIP000231 | Defect Corrections |  |  | Line Maintenance and Repair | emre.aydin@HydroOne.com | Matthew.Bell@HydroOne.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | EMPP ACCP | Executing | Short Term Planning | # of defects | 4694296.7246 | 4997838.9547 | 5267302.0979 | 5545646.0514 | 5809558.548 | 0 | 0 | 0 | 0 | 0 | 4694296.7246 | 4997838.9547 | 5267302.0979 | 5545646.0514 | 5809558.548 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9210 | 9210 | 9210 | 9210 | 9210 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Vulnerable Modified
17362 | Distribution Line Patrols | N.D.M.1.02 | 7374 | 205 | LINES | AIP000232 | AIP000232 | AIP000232 | No | AIP000232 | Distribution Patrols |  |  | Line Maintenance and Repair | emre.aydin@HydroOne.com | Matthew.Bell@HydroOne.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | DETL init | Short Term Planning | Short Term Planning | # of poles/inspectio | 9504506.4683 | 9783566.4472 | 9987915.0214 | 10201301.7002 | 10381388.3905 | 0 | 0 | 0 | 0 | 0 | 9504506.4683 | 9783566.4472 | 9987915.0214 | 10201301.7002 | 10381388.3905 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350000 | 350000 | 350000 | 350000 | 350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
17365 | Recoverable - Pickering - Sewer Line - Engineering | N.T.C.1.12 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Overhead Lines Component Refurb & Repl | hassan.hamzeh@hydroone.com | [6 empty] | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17367 | Dx O&M Trouble Call | N.D.M.1.01 | 7374 | 205 | LINES | AIP000230 | AIP000230 | AIP000230 | No | AIP000230 | Trouble Call |  |  | Trouble Calls Customer Locates & Disconn | emre.aydin@HydroOne.com | Wojciech.Maroszek@HydroOne.com | System O&M | N/A | 0 | 03 - None (default) | 0 | Program | EMPP ACCP | Executing | Short Term Planning | # of Calls | 62135452.8402 | 64014632.6335 | 65341669.9912 | 66753771.5265 | 67972838.0865 | 0 | 0 | 0 | 0 | 0 | 62135452.8402 | 64014632.6335 | 65341669.9912 | 66753771.5265 | 67972838.0865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42645 | 42645 | 42645 | 42645 | 42645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Demand
17368 | Dx Disconnects / Reconnects | N.D.M.1.01 | 7374 | 205 | LINES | AIP000228 | AIP000228 | AIP000228 | No | AIP000228 | Disconnect/Reconnect |  |  | Trouble Calls Customer Locates & Disconn | emre.aydin@HydroOne.com | Wojciech.Maroszek@HydroOne.com | System O&M | N/A | 0 | 03 - None (default) | 0 | Program | ACCP EMPP | Executing | Short Term Planning | # of disconnect/reconnections | 12100504.5087 | 12467719.5442 | 12740339.1344 | 13023632.7648 | 13266277.1868 | 0 | 0 | 0 | 0 | 0 | 12100504.5087 | 12467719.5442 | 12740339.1344 | 13023632.7648 | 13266277.1868 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14250 | 14250 | 14250 | 14250 | 14250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Demand
17369 | Dx Cable Locates | N.D.M.1.01 | 7374 | 205 | LINES | AIP000227 | AIP000227 | AIP000227 | No | AIP000227 | Cable Locates |  |  | Trouble Calls Customer Locates & Disconn | emre.aydin@HydroOne.com | Wojciech.Maroszek@HydroOne.com | System O&M | N/A | 0 | 03 - None (default) | 0 | Program | ACCP EMPP | Executing | Short Term Planning | # of locates | 14172194.4125 | 14610123.6854 | 14931553.7656 | 15259633.2754 | 15534105.0022 | 0 | 0 | 0 | 0 | 0 | 14172194.4125 | 14610123.6854 | 14931553.7656 | 15259633.2754 | 15534105.0022 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 200000 | 200000 | 200000 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Demand
17370 | Dx Overtime and Forestry Storm Costs | N.D.M.1.01 | 7374 | 205 | LINES | AIP000229 | AIP000229 | AIP000229 | No | AIP000229 | O&M Costs - Storm Response |  |  | Trouble Calls Customer Locates & Disconn | emre.aydin@HydroOne.com | Wojciech.Maroszek@HydroOne.com | System O&M | N/A | 0 | 03 - None (default) | 0 | Program | EMPP ACCP | Executing | Short Term Planning | # of Storms | 13507680.8729 | 13917599.7437 | 14221922.4389 | 14538160.4957 | 14809022.2929 | 0 | 0 | 0 | 0 | 0 | 13507680.8729 | 13917599.7437 | 14221922.4389 | 14538160.4957 | 14809022.2929 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Demand
17371 | Dx Capital Trouble Call Poles & Equipment | N.D.C.1.06 | 7374 | 205 | LINES | AIP000135 | AIP000135 | AIP000135 | No | AIP000135 | Equipment Replaced (Trouble Call) | ISD-SR-07 | Distribution Lines Trouble Call and Storm Damage Response Program | Trouble Calls & Storm Damage | emre.aydin@HydroOne.com | Wojciech.Maroszek@HydroOne.com | System Renewal | 0 | 0 | 03 - None (default) | 0 | Program | ACCP EMPP | Executing | Short Term Planning | # of poles/equipment | 24031272.5685 | 24513750.5702 | 25022395.4769 | 25537132.565 | 26047017.4125 | 0 | 0 | 0 | 0 | 0 | 27308264.2824 | 27856534.7389 | 28434540.3147 | 29019468.8239 | 29598883.4233 | 0 | 0 | 0 | 0 | 0 | -3276991.7139 | -3342784.1687 | -3412144.8378 | -3482336.2589 | -3551866.0108 | 0 | 0 | 0 | 0 | 0 | -12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3376 | 3376 | 3376 | 3376 | 3376 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Demand
17372 | Small External Demand (Yearly) | N.D.M.1.07 | 7374 | 205 | LINES | AIP000275 | AIP000275 | AIP000275 | No | AIP000275 | Small External Demand Requests |  |  | Other Services | emre.aydin@HydroOne.com | patrick.howe@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | AWRD EMPP | Executing | Short Term Planning | # of occurences | 7739043.0901 | 7973900.558 | 8148258.1653 | 8329442.5451 | 8484629.0522 | 0 | 0 | 0 | 0 | 0 | 7739043.0901 | 7973900.558 | 8148258.1653 | 8329442.5451 | 8484629.0522 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Demand
17373 | 2015/16 - Replacement of Waste Storage Sites | N.D.C.1.04 | 4220 | 209 | HEALTH, SAFETY & ENV | UNPLND |  |  | Yes |  |  |  |  | PCB Transformer Replacement | emre.aydin@HydroOne.com | [6 empty] | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17383 | Pristine East Windsor Co-Generation | N.T.C.2.12 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Generator Customer Connection | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17384 | Thorold Co-Generation | N.T.C.2.12 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Generator Customer Connection | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | EMPP AWRD | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17385 | Equipment Protective Recoating (Paint) | N.T.M.1.16 | 7370 | 206 | TX LINES AND STATIONS | AIP001048A |  | AIP001048 | Yes | AIP001048 |  |  |  | Power Equipment | Mike.Tanaskovic@HydroOne.com | [6 empty] | Program | ACTN EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17389 | Guelph Area Transmission Refurbishment | N.T.C.2.02 | 7700 | 203 | PROJECT DELIVERY | AIP000698 | AIP000698 | AIP000698 | No | AIP000698 | Guelph Area Transmission Refurbishment | 0 |  | Local Area Supply | Robert.Reinmuller@HydroOne.com | Emeka.Okongwu@HydroOne.com | System Service | 0 | 0 | 01 - Agreement (current/future) | In Progress | Project | ACCP EMPP | Executing | Executing |  | 1703003.0049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1703003.0049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43339 | [13 empty] | FALSE |  | 0 | 0 | Alternative 1
17393 | Beck 2 TS, ABCB Replacement & Yard Upgrade | N.T.C.1.08 | 7700 | 203 | PROJECT DELIVERY | AIP000387 | AIP000387 | AIP000387 | No | AIP000387 | Beck 2 TS 230 kV ABCB Replacement | SR-01 | Air Blast Circuit Breaker Replacement Projects | System Re-investment | James.Mardegan@HydroOne.com | Fred.Kouhdani@HydroOne.com | System Renewal | Hamilton Niagara | 0 | 02 - Expectation (no agreement) | 0 | Project | EMPP ACCP | Executing | Executing |  | 11301181.5892 | 13853127.1629 | 8823248.9384 | 6740409.0957 | 4820851.1254 | 1155425.4845 | 0 | 0 | 0 | 0 | 12151808.1604 | 14895835.659 | 9487364.4499 | 7247751.7158 | 5183710.8875 | 1242392.994 | 0 | 0 | 0 | 0 | -850626.5712 | -1042708.4961 | -664115.5115 | -507342.6201 | -362859.7621 | -86967.5096 | 0 | 0 | 0 | 0 | -4.6564 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44545 | [13 empty] | FALSE |  | 0 | 0 | Alternative 1 Bay by BAYoption
17395 | Meaford TS M1 ID109 Silver Springs Wind Farm A | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000199 |  | AIP000199 | Yes | AIP000199 | Large Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17397 | Connection of Landfill to Energy Project Ottawa ge | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000199 |  | AIP000199 | Yes | AIP000199 | Large Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17411 | 2010 Small Distribution Lines Projects | N.D.C.1.07 | 7374 | 205 | LINES | UNPLND |  |  | Yes |  |  |  |  | Lines | emre.aydin@HydroOne.com | [6 empty] | Program | EMPP ACCP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17412 | 2010 Demand Investments | N.D.C.2.02 | 7374 | 205 | LINES | UNPLND |  |  | Yes |  |  |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | [6 empty] | Program | EMPP ACCP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17413 | 2010 Distribution System Modifications | N.D.C.2.02 | 7374 | 205 | LINES | UNPLND |  |  | Yes |  |  |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | [6 empty] | Program | ACCP EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17418 | Lower Mattagami Generation Connection | N.T.C.2.12 | 7700 | 203 | PROJECT DELIVERY | AIP000883 |  | AIP000883 | Yes | AIP000883 |  |  |  | Generator Customer Connection | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17422 | Cyber Security - OGCCOT | N.T.M.1.29 | 4339 | 212 | INFO SOLUTIONS DIVISION | UNPLND |  |  | Yes |  |  |  |  | NERC Cyber Security Compliance Readiness | lincoln.frost-hunt@hydroone.com | [6 empty] | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17424 | Upgrade Wholesale Meters at Seal Expiry | N.D.C.2.05 | 7700 | 203 | PROJECT DELIVERY | AIP000204 | AIP000204 | AIP000204 | No | AIP000204 | Wholesale Metering |  |  | Wholesale Metering | Peter.Mitskos@HydroOne.com | Dominic.Consorti@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Program | EMPP ACCP | Executing | Short Term Planning | # of Meter Points | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Demand
17431 | 2007 Dx R&D Technology Program - Kinectrics | N.D.M.2.21 | 4230 | 213 | PLANNING | AIP000320 |  | AIP000320 | Yes | AIP000320 |  |  |  | Distribution RD&D | Daila.Dzintars@HydroOne.com | [6 empty] | Program | EMPP AWRD | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17437 | DouglasPointTS ID40a-Barrington Huron-Kinloss Wind | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Distribution Generation Connection | ryan.boudreau@HydroOne.com | [6 empty] | Project | ACTN DETL | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17438 | DouglasPointTS ID40b Barrington Huron-Kinloss Wind | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Distribution Generation Connection | ryan.boudreau@HydroOne.com | [6 empty] | Project | DETL ACTN | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17443 | 2009 E&CS Wood Pole Program | N.T.C.1.12 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Overhead Lines Component Refurb & Repl | hassan.hamzeh@hydroone.com | [6 empty] | Program | ACCP EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17445 | Albion TS, EOL Metalclad Replacement Project | N.T.C.1.08 | 7700 | 203 | PROJECT DELIVERY | AIP000384 |  | AIP000384 | Yes | AIP000384 |  |  |  | System Re-investment | James.Mardegan@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17447 | Hub Site Upgrade Program | N.T.C.3.08 | 7700 | 203 | PROJECT DELIVERY | 3853 |  |  | Yes |  |  |  |  | Integrating Operating Infrastructure | Miroslav.Kostic@HydroOne.com | [6 empty] | Program | AWRD EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17449 | Pandemic Planning - Tamiflu Prophylaxis | N.C.M.3.03 | 4337 | 223 | SMART METERS | UNPLND |  |  | Yes |  |  |  |  | Environment Health and Safety | welchw@hydroone.com | [6 empty] | Program | AWRD EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17457 | HV UG Cable - PM (Preventative Maintenance) | N.T.M.1.21 | 7370 | 206 | TX LINES AND STATIONS | AIP001119 | AIP001119 | AIP001119 | No | AIP001119 | HV UG Cable - PM (Preventative Maintenance) | 0 |  | Underground Cables | hassan.hamzeh@hydroone.com | Tyler.Wales@HydroOne.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | ACTN EMPP | Executing | Short Term Planning | Number of Orders | 977330.0252 | 993149.7987 | 1015054.3807 | 1038041.4784 | 1059300.7664 | 1080992.8172 | 0 | 0 | 0 | 0 | 977330.0252 | 993149.7987 | 1015054.3807 | 1038041.4784 | 1059300.7664 | 1080992.8172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | False |  | False | True | False | False | FALSE |  | 0 | 0 | Intermediate
17458 | HV UG Cable - Planned CM (Corrective Maintenance) | N.T.M.1.21 | 7370 | 206 | TX LINES AND STATIONS | AIP001118A | AIP001118 | AIP001118 | No | AIP001118 | HV UG Cable - CM (Corrective Maintenance) | 0 |  | Underground Cables | hassan.hamzeh@hydroone.com | Tyler.Wales@HydroOne.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | EMPP ACTN | Executing | Short Term Planning | Number of Repairs | 1683290.7504 | 1710537.6299 | 1748264.7262 | 1787856.3639 | 1824471.8833 | 1861832.9412 | 0 | 0 | 0 | 0 | 1683290.7504 | 1710537.6299 | 1748264.7262 | 1787856.3639 | 1824471.8833 | 1861832.9412 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | True | False |  | False | True | False | False | FALSE |  | 0 | 0 | Asset Optimal
17461 | HV UG Cable - Locates | N.T.M.1.21 | 7370 | 206 | TX LINES AND STATIONS | AIP001121 | AIP001121 | AIP001121 | No | AIP001121 | HV UG Cable - Locates | 0 |  | Underground Cables | hassan.hamzeh@hydroone.com | Tyler.Wales@HydroOne.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | EMPP ACTN | Executing | Short Term Planning | Number of Locates | 1384884.6566 | 1407301.4085 | 1438340.3977 | 1470913.3413 | 1501037.776 | 1531775.6117 | 0 | 0 | 0 | 0 | 1384884.6566 | 1407301.4085 | 1438340.3977 | 1470913.3413 | 1501037.776 | 1531775.6117 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | True | HONI is required by provincial legislation (Ontario Underground Infrastructure Notification System Act) to provide locate services of its underground infrastructure. | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Asset Optimal
17466 | Pole Rentals (Yearly) | N.D.M.1.07 | 4388 | 213 | PLANNING | AIP000274 | AIP000274 | AIP000274 | No | AIP000274 | Pole Rentals |  |  | Other Services | emre.aydin@HydroOne.com | Jenny.Seo@HydroOne.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | AWRD EMPP | Executing | Short Term Planning | # of Poles Rented | 647331.4137 | 666976.0029 | 681560.094 | 696715.285 | 709695.8145 | 0 | 0 | 0 | 0 | 0 | 647331.4137 | 666976.0029 | 681560.094 | 696715.285 | 709695.8145 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Demand
17469 | Dx Capital Storm Damage | N.D.C.1.06 | 7374 | 205 | LINES | AIP000137 | AIP000137 | AIP000137 | No | AIP000137 | Storm Damage | ISD-SR-07 | Distribution Lines Trouble Call and Storm Damage Response Program | Trouble Calls & Storm Damage | emre.aydin@HydroOne.com | Wojciech.Maroszek@HydroOne.com | System Renewal | N/A | 0 | 03 - None (default) | 0 | Program | ACCP EMPP | Executing | Short Term Planning | # of Storms | 43949348.3795 | 44814987.1822 | 45556427.862 | 46387915.7115 | 47250303.356 | 0 | 0 | 0 | 0 | 0 | 49942441.3403 | 50926121.798 | 51768668.025 | 52713540.5812 | 53693526.5409 | 0 | 0 | 0 | 0 | 0 | -5993092.9608 | -6111134.6158 | -6212240.163 | -6325624.8697 | -6443223.1849 | 0 | 0 | 0 | 0 | 0 | -12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Demand
17471 | Dx Capital Trouble Sub and UG Cable | N.D.C.1.06 | 7374 | 205 | LINES | AIP000138 | AIP000138 | AIP000138 | No | AIP000138 | UG Sub Replace Trouble | ISD-SR-07 | Distribution Lines Trouble Call and Storm Damage Response Program | Trouble Calls & Storm Damage | emre.aydin@HydroOne.com | Wojciech.Maroszek@HydroOne.com | System Renewal | N/A | 0 | 03 - None (default) | 0 | Program | EMPP ACCP | Executing | Short Term Planning | # of cables | 5023445.005 | 5124301.1391 | 5230627.1396 | 5338226.5745 | 5444811.748 | 0 | 0 | 0 | 0 | 0 | 5708460.2329 | 5823069.4762 | 5943894.4768 | 6066166.562 | 6187286.0772 | 0 | 0 | 0 | 0 | 0 | -685015.228 | -698768.3371 | -713267.3372 | -727939.9874 | -742474.3293 | 0 | 0 | 0 | 0 | 0 | -12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Demand
17472 | Dx Capital Post Trouble Call & Power Quality | N.D.C.1.06 | 7374 | 205 | LINES | AIP000136A | AIP000136 | AIP000136 | No | AIP000136 | Post Trouble and Power Quality |  |  | Trouble Calls & Storm Damage | emre.aydin@HydroOne.com | Wojciech.Maroszek@HydroOne.com | System Service | 0 | 0 | 03 - None (default) | 0 | Program | ACCP EMPP | Executing | Short Term Planning | # of occurrences | 6687225.9981 | 6821486.0457 | 6963027.5404 | 7106264.3441 | 7248151.0361 | 0 | 0 | 0 | 0 | 0 | 7599120.4523 | 7751688.6883 | 7912531.2959 | 8075300.391 | 8236535.2683 | 0 | 0 | 0 | 0 | 0 | -911894.4543 | -930202.6426 | -949503.7555 | -969036.0469 | -988384.2322 | 0 | 0 | 0 | 0 | 0 | -12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Demand
17477 | Dx Capital Trouble Call Damage Claims | N.D.C.1.06 | 7374 | 205 | LINES | AIP000134 | AIP000134 | AIP000134 | No | AIP000134 | Damage Claims | ISD-SR-07 | Distribution Lines Trouble Call and Storm Damage Response Program | Trouble Calls & Storm Damage | emre.aydin@HydroOne.com | Wojciech.Maroszek@HydroOne.com | System Renewal | N/A | 0 | 03 - None (default) | 0 | Program | ACCP EMPP | Executing | Short Term Planning | # of claims | 2654970.7796 | 2708274.8051 | 2764469.7689 | 2821337.9674 | 2877669.8658 | 0 | 0 | 0 | 0 | 0 | 5793224.3696 | 5909321.3658 | 6029813.9992 | 6152204.3521 | 6275140.6329 | 0 | 0 | 0 | 0 | 0 | -362041.47 | -369310.2007 | -376973.1503 | -384727.9047 | -392409.5271 | 0 | 0 | 0 | 0 | 0 | -12 | 12 | -2776212.12 | -2831736.36 | -2888371.08 | -2946138.48 | -3005061.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Demand
17491 | Meter Management & Verification Ser (SLA 054) | N.D.M.1.05 | 8706 | 214 | METER SHOP | AIP000262 |  | AIP000262 | Yes | AIP000262 | Meter Management and Verification |  |  | Customer Meters | Peter.Mitskos@HydroOne.com | Dominic.Consorti@HydroOne.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | ACTN EMPP | Executing | Short Term Planning | Retainer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17492 | Wholesale Meter Services Provider (MSP) | N.D.M.1.05 | 8706 | 214 | METER SHOP | AIP000263 |  | AIP000263 | Yes | AIP000263 | Wholesale Meter Service |  |  | Customer Meters | Peter.Mitskos@HydroOne.com | Dominic.Consorti@HydroOne.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | EMPP AWRD | Executing | Short Term Planning | Assumption - # of Meter Points | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17494 | Recloser & Regulator Maintenance | N.D.M.1.02 | 7374 | 205 | LINES | AIP000236 | AIP000236 | AIP000236 | No | AIP000236 | Recloser & Regulator Maintenance |  |  | Line Maintenance and Repair | emre.aydin@HydroOne.com | Matthew.Bell@HydroOne.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | ACTN EMPP | Executing | Short Term Planning | # of regulators/recl | 101090.2627 | 130197.5779 | 159653.3596 | 190403.993 | 221658.741 | 0 | 0 | 0 | 0 | 0 | 101090.2627 | 130197.5779 | 159653.3596 | 190403.993 | 221658.741 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 125 | 150 | 175 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
17495 | Switch Maintenance | N.D.M.1.02 | 7374 | 205 | LINES | AIP000237 | AIP000237 | AIP000237 | No | AIP000237 | Switch Maintenance |  |  | Line Maintenance and Repair | emre.aydin@HydroOne.com | Matthew.Bell@HydroOne.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | ACTN EMPP | Executing | Short Term Planning | # of switches | 1282835.3935 | 1320724.1175 | 1348538.8382 | 1377436.8795 | 1401991.7598 | 0 | 0 | 0 | 0 | 0 | 1282835.3935 | 1320724.1175 | 1348538.8382 | 1377436.8795 | 1401991.7598 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 215 | 215 | 215 | 215 | 215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Vulnerable
17498 | Sentinel Lights Maintenance | N.D.M.1.02 | 7374 | 205 | LINES | AIP000238 | AIP000238 | AIP000238 | No | AIP000238 | Sentinel Light Maintenance |  |  | Line Maintenance and Repair | emre.aydin@HydroOne.com | Matthew.Bell@HydroOne.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | AWRD EMPP | Executing | Short Term Planning | # of lights | 1035164.2206 | 1065536.9118 | 1087771.7077 | 1110871.2894 | 1130459.7323 | 0 | 0 | 0 | 0 | 0 | 1035164.2206 | 1065536.9118 | 1087771.7077 | 1110871.2894 | 1130459.7323 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 2000 | 2000 | 2000 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Demand
17501 | Insulator Washing | N.D.M.1.02 | 7374 | 205 | LINES | AIP000235 | AIP000235 | AIP000235 | No | AIP000235 | Insulator Washing |  |  | Line Maintenance and Repair | emre.aydin@HydroOne.com | Matthew.Bell@HydroOne.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | HOLD | Short Term Planning | Short Term Planning | Insulator | 291139.9334 | 299975.1772 | 305470.0806 | 312262.58 | 316972.0377 | 0 | 0 | 0 | 0 | 0 | 291139.9334 | 299975.1772 | 305470.0806 | 312262.58 | 316972.0377 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | 6000 | 6000 | 6000 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Vulnerable
17503 | Leamington TS: New 230/27.6 kV DESN and Line cone | N.T.C.2.11 | 7700 | 203 | PROJECT DELIVERY | AIP000794 | AIP000794 | AIP000794 | No | AIP000794 | Supply to Essex County Transmission Reinforcement | 0 |  | Load Customer Connection | Robert.Reinmuller@HydroOne.com | Emeka.Okongwu@HydroOne.com | System Access | Western | In Progress | 01 - Agreement (current/future) | Required | Project | ACCP EMPP | Executing | Executing |  | 9570571.6996 | 107277.816 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11824223.6996 | 132227.816 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2.7756e-11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2253652 | -24950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43449 | [13 empty] | FALSE |  | 0 | 0 | Alternative 1
17517 | Lambton TS: Station Service Upgrade | N.T.C.2.21 | 7700 | 203 | PROJECT DELIVERY | AIP000965 | AIP000965 | AIP000965 | No | AIP000965 | Risk Mitigation Projects | 0 |  | Major Risk Mitigation | Robert.Reinmuller@HydroOne.com | farooq.qureshy@hydroone.com | System Service | 0 | Not Required | 0 | Not Required | Project | ACCP EMPP | Executing | Executing |  | 1460.7357 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1460.7357 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43101 | [13 empty] | FALSE |  | 0 | 0 | Alternative 1
17522 | CMS System Reserve / Strategic Inventory Managem | N.T.M.1.16 | 7370 | 206 | TX LINES AND STATIONS | AIP001063 | AIP001063 | AIP001063 | No | AIP001063 | Other Mtce - System Reserve Equipment - Inventory Management | 0 |  | Power Equipment | Mike.Tanaskovic@HydroOne.com | andrea.Lemhenyi@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | ACTN EMPP | Executing | Short Term Planning | # of Inspections | 908013.8634 | 921240.6658 | 941833.5382 | 963444.0468 | 983430.0648 | 1004050.6845 | 0 | 0 | 0 | 0 | 908013.8634 | 921240.6658 | 941833.5382 | 963444.0468 | 983430.0648 | 1004050.6845 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | False |  | False | True | False | False | FALSE |  | 0 | 0 | Intermediate
17528 | Circuit Switcher Replacement Program | N.T.C.1.18 | 7700 | 203 | PROJECT DELIVERY | AIP000571 |  | AIP000571 | Yes | AIP000571 |  |  |  | Other Power Equipment | James.Mardegan@HydroOne.com | [6 empty] | Program | ACCP EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17529 | 2009 New Connections Upgrades & Service Cancellati | N.D.C.2.01 | 7374 | 205 | LINES | UNPLND |  |  | Yes |  |  |  |  | New Load Connection Upg/Cancel/Meters | emre.aydin@HydroOne.com | [6 empty] | Program | AWRD EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17531 | Ancillary Preventive Maintenance - Planned (PMO) | N.T.M.1.18 | 7370 | 206 | TX LINES AND STATIONS | AIP001089 | AIP001089 | AIP001089 | No | AIP001089 | Ancillary Preventive Maintenance | 0 |  | Ancillary Systems Maintenance | Mike.Tanaskovic@HydroOne.com | Harshal.Bhatt@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | ACTN EMPP | Executing | Short Term Planning | # of Orders | 3777845.0436 | 4403849.7844 | 4197434.313 | 4169193.684 | 3925662.6096 | 3691717.9735 | 0 | 0 | 0 | 0 | 3777845.0436 | 4403849.7844 | 4197434.313 | 4169193.684 | 3925662.6096 | 3691717.9735 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3830 | 3447 | 3275 | 3256 | 3064 | 2873 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | True | DC Batteries and Chargers : NPCC Directory 8, NERC PRC-005-02, High Pressure air system: TSSA | False |  | False | False |  | False | True | False | False | FALSE |  | 0 | 0 | Vulnerable Modified (Tx Decision)
17532 | Ancillary Corrective Maintenance - Demand | N.T.M.1.18 | 7370 | 206 | TX LINES AND STATIONS | AIP001088A | AIP001088 | AIP001088 | No | AIP001088 | Ancillary Corrective Maintenance | 0 |  | Ancillary Systems Maintenance | Mike.Tanaskovic@HydroOne.com | Harshal.Bhatt@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | ACTN EMPP | Executing | Short Term Planning | # of Orders | 2034277.9635 | 2120423.8639 | 2124756.1657 | 2130344.2377 | 2131360.7156 | 2132372.5664 | 0 | 0 | 0 | 0 | 2034277.9635 | 2120423.8639 | 2124756.1657 | 2130344.2377 | 2131360.7156 | 2132372.5664 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 735 | 770 | 770 | 770 | 770 | 770 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | True | False |  | False | False | False | False | FALSE |  | 0 | 0 | Intermediate (Modified-Tx Decision)
17533 | Payments for Ancillary Services to Third Parties | N.T.M.1.18 | 4363 | 213 | PLANNING | AIP001096 | AIP001096 | AIP001096 | No | AIP001096 | Payments for Ancillary Services to Third Parties | 0 |  | Ancillary Systems Maintenance | Mike.Tanaskovic@HydroOne.com | Farinaz.Yousefi@HydroOne.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | EMPP AWRD | Executing | Short Term Planning | Retainer | 790797.4684 | 793022.9018 | 794466.8956 | 796258.6137 | 796551.6649 | 796797.5406 | 0 | 0 | 0 | 0 | 790797.4684 | 793022.9018 | 794466.8956 | 796258.6137 | 796551.6649 | 796797.5406 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | True |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Intermediate 1 - Tx Constraint Reduction
17534 | Infrastructure Corrective Maintenance - Demand | N.T.M.1.19 | 7370 | 206 | TX LINES AND STATIONS | AIP001107A | AIP001107 | AIP001107 | No | AIP001107 | Tx Infrastructure Corrective Maintenance | 0 |  | Infrastructure Maintenance | Mike.Tanaskovic@HydroOne.com | Sebastian.Niculae@HydroOne.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | ACTN EMPP | Executing | Short Term Planning | # of Orders | 1402536.9172 | 1687364.3189 | 1964949.8861 | 1793416.4835 | 1843374.8145 | 2119357.5105 | 0 | 0 | 0 | 0 | 1402536.9172 | 1687364.3189 | 1964949.8861 | 1793416.4835 | 1843374.8145 | 2119357.5105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Intermediate - (Modified-Tx Decision)
17537 | Kirkland Lake TS Civil Infrastructure Improvements | N.T.C.1.21 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Infrastructure | James.Mardegan@HydroOne.com | [6 empty] | Program | ACCP EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17538 | Transmission Land Assessment and Remediation | N.T.M.1.03 | 7053 | 209 | HEALTH, SAFETY & ENV | AIP001006 | AIP001006 | AIP001006 | No | AIP001006 | Land Assessment and Remediation (Tx) | 0 |  | Land Assessment and Remediation | Mike.Tanaskovic@HydroOne.com | Sebastian.Niculae@HydroOne.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | AWRD EMPP | Executing | Short Term Planning | # of Sites | 1759524.3671 | 1268836.7698 | 1618726.2999 | 1104808.8265 | 677068.9151 | 0 | 0 | 0 | 0 | 0 | 1759524.3671 | 1268836.7698 | 1618726.2999 | 1104808.8265 | 677068.9151 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Asset Optimal (Modified - Tx Decision)
17540 | Grounding Upgrade Program | N.T.C.1.20 | 7700 | 203 | PROJECT DELIVERY | AIP000620 | AIP000620 | AIP000620 | No | AIP000620 | Station Grounding System Upgrades Program - Carryover | 0 |  | Ancillary Systems | James.Mardegan@HydroOne.com | mark.truchanowicz@hydroone.com | System Renewal | 0 | 0 | 03 - None (default) | 0 | Program | EMPP ACCP | Executing | Short Term Planning | # of Stations | 542928.3017 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 542928.3017 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Carryover Work
17541 | Distribution Land Assessment and Remediation | N.D.M.1.08 | 7053 | 209 | HEALTH, SAFETY & ENV | AIP000279 | AIP000279 | AIP000279 | No | AIP000279 | Land Assessment and Remediation (Dx) |  |  | Land Assessment and Remediation | emre.aydin@HydroOne.com | Trevor.Beausoleil@HydroOne.com | System O&M | N/A | 0 | 03 - None (default) | 0 | Program | ACTN EMPP | Executing | Short Term Planning | # of Sites | 4015640.3445 | 2680413.1799 | 4943392.0593 | 4462617.6266 | 2886168.138 | 0 | 0 | 0 | 0 | 0 | 4015640.3445 | 2680413.1799 | 4943392.0593 | 4462617.6266 | 2886168.138 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 4 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Vulnerable
17543 | 2009 MIST Meter Upgrades | N.D.C.1.09 | 7374 | 205 | LINES | UNPLND |  |  | Yes |  |  |  |  | Metering | Peter.Mitskos@HydroOne.com | [6 empty] | Program | EMPP ACCP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17547 | Infrastructure Preventive Maintenance-Planned(PMO) | N.T.M.1.19 | 7370 | 206 | TX LINES AND STATIONS | AIP001101 | AIP001101 | AIP001101 | No | AIP001101 | Infrastructure Preventive Maintenance | 0 |  | Infrastructure Maintenance | Mike.Tanaskovic@HydroOne.com | Sebastian.Niculae@HydroOne.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | EMPP ACTN | Executing | Short Term Planning | # of Orders | 2163279.5842 | 2393588.399 | 2437634.8983 | 2493116.2443 | 2543407.2407 | 2583913.6469 | 0 | 0 | 0 | 0 | 2163279.5842 | 2393588.399 | 2437634.8983 | 2493116.2443 | 2543407.2407 | 2583913.6469 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1899 | 1899 | 1899 | 1899 | 1899 | 1899 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | True | Fire Code / Building Code (portion of program, only reduced forecast for non-regulatory funding) | False |  | False | False |  | False | True | False | False | FALSE |  | 0 | 0 | Vulnerable Modified (Tx Decision)
17552 | ACA - Grounding System Studies | N.T.M.1.18 | 7370 | 206 | TX LINES AND STATIONS | AIP001090A | AIP001090 | AIP001090 | No | AIP001090 | Grounding System Studies & Repairs | 0 |  | Ancillary Systems Maintenance | Mike.Tanaskovic@HydroOne.com | Harshal.Bhatt@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | ACTN EMPP | Executing | Short Term Planning | # of Stations as demanded | 153515.6437 | 159729.7449 | 242665.3764 | 167044.7358 | 170508.9623 | 253356.1196 | 0 | 0 | 0 | 0 | 153515.6437 | 159729.7449 | 242665.3764 | 167044.7358 | 170508.9623 | 253356.1196 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Vulnerable (Modified-Tx Decision)
17553 | Field Metering Services - PL&F (SLA D027) | N.D.M.1.05 | 7374 | 205 | LINES | AIP000261 | AIP000261 | AIP000261 | No | AIP000261 | Field Meter Service |  |  | Customer Meters | Peter.Mitskos@HydroOne.com | Dominic.Consorti@HydroOne.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | ACCP EMPP | Executing | Short Term Planning | # of meters | 3578162.6027 | 3683596.5548 | 3760920.4296 | 3841254.6958 | 3909466.6133 | 0 | 0 | 0 | 0 | 0 | 3578162.6027 | 3683596.5548 | 3760920.4296 | 3841254.6958 | 3909466.6133 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8000 | 8000 | 8000 | 8000 | 8000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Demand - Modified - M2M Savings
17557 | Support & Update of SAP/FAO/BOA and Other Database | N.T.M.1.16 | 7716 | 224 | ENGINEERING | AIP001058 | AIP001058 | AIP001058 | No | AIP001058 | Other Mtce - Power Equipment - GO Support & Update of SAP | 0 |  | Power Equipment | Mike.Tanaskovic@HydroOne.com | andrea.Lemhenyi@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | EMPP ACTN | Executing | Short Term Planning | Retainer | 247124.2089 | 399504.7558 | 408236.8143 | 417340.5986 | 408343.7277 | 416639.1393 | 0 | 0 | 0 | 0 | 247124.2089 | 399504.7558 | 408236.8143 | 417340.5986 | 408343.7277 | 416639.1393 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | True | This investment funds the inputting of all the test data into SAP, including regulatory related testing/measurements, such as the PCB measuring points. | False |  | False | False |  | False | True | False | False | FALSE |  | 0 | 0 | Asset Optimal (Modified-Tx Decision)
17564 | Corrective Maintenance - Planned | N.T.M.1.16 | 7370 | 206 | TX LINES AND STATIONS | AIP001068A | AIP001068 | AIP001068 | No | AIP001068 | Power Equipment Corrective Maintenance | 0 |  | Power Equipment | Mike.Tanaskovic@HydroOne.com | kristoffer.hammel@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | ACTN EMPP | Executing | Short Term Planning | # of Orders | 9831192.0495 | 9577073.1343 | 9303635.595 | 9132714.0676 | 8744413.5705 | 8060965.2975 | 0 | 0 | 0 | 0 | 9831192.0495 | 9577073.1343 | 9303635.595 | 9132714.0676 | 8744413.5705 | 8060965.2975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2337 | 2324 | 2273 | 2223 | 2169 | 2108 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | True | False |  | False | False | False | False | FALSE |  | 0 | 0 | Demand (Modified - Tx Decision)
17565 | Corrective Maintenance - Demand | N.T.M.1.16 | 7370 | 206 | TX LINES AND STATIONS | AIP001068B | AIP001068 | AIP001068 | No | AIP001068 | Power Equipment Corrective Maintenance | 0 |  | Power Equipment | Mike.Tanaskovic@HydroOne.com | kristoffer.hammel@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | ACTN EMPP | Executing | Short Term Planning | # of Orders | 12261344.596 | 11702294.4069 | 11335282.3238 | 10777051.1171 | 10291328.871 | 10099882.2628 | 0 | 0 | 0 | 0 | 12261344.596 | 11702294.4069 | 11335282.3238 | 10777051.1171 | 10291328.871 | 10099882.2628 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4245 | 4240 | 4230 | 4220 | 4210 | 4200 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | True | False |  | False | False | False | False | FALSE |  | 0 | 0 | Demand (Modified - Tx Decision)
17566 | Preventive Maintenance - Planned (PMO) | N.T.M.1.16 | 7370 | 206 | TX LINES AND STATIONS | AIP001069 | AIP001069 | AIP001069 | No | AIP001069 | Power Equipment Preventive Maintenance (Vulnerable) | 0 |  | Power Equipment | Mike.Tanaskovic@HydroOne.com | kristoffer.hammel@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | EMPP ACTN | Executing | Short Term Planning | # of Orders | 18710442.0549 | 18254975.7121 | 17919257.695 | 17569840.7947 | 17158886.8314 | 16722939.345 | 0 | 0 | 0 | 0 | 18710442.0549 | 18254975.7121 | 17919257.695 | 17569840.7947 | 17158886.8314 | 16722939.345 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7400 | 7216 | 7028 | 6833 | 6634 | 6429 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | False |  | False | True | False | False | FALSE |  | 0 | 0 | Reaggregated - Condition Based Maintenance (Vulnerable/Intermediate)
17568 | BSPS Replacement of End-of-life Equipment | N.T.C.1.19 | 7700 | 203 | PROJECT DELIVERY | AIP000591 | AIP000591 | AIP000591 | No | AIP000591 | BSPS Replacement of End-of-life Equipment | 0 |  | Protection Control & Metering Equip | Miroslav.Kostic@HydroOne.com | janusz.ploski@hydroone.com | System Renewal | 0 | 0 | 03 - None (default) | 0 | Project | ACCP EMPP | Executing | Executing |  | 2850541.6329 | 0.99102 | 7.3711 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2850541.6329 | 0.99102 | 7.3711 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43435 | [13 empty] | FALSE |  | 0 | 0 | Alternative 1
17573 | Telecom Preventative Maintenance | N.T.M.1.22 | 7370 | 206 | TX LINES AND STATIONS | AIP001125 | AIP001125 | AIP001125 | No | AIP001125 | Telecom Preventive Maintenance | 0 |  | Telecommunication Assets Maintenance | Miroslav.Kostic@HydroOne.com | Sheraz.Majid@HydroOne.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | AWRD EMPP | Executing | Short Term Planning | # of orders | 1452913.8754 | 2150251.6147 | 2189871.8024 | 2233887.4963 | 2286998.0304 | 2336222.5275 | 0 | 0 | 0 | 0 | 1452913.8754 | 2150251.6147 | 2189871.8024 | 2233887.4963 | 2286998.0304 | 2336222.5275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200 | 1695 | 1675 | 1726 | 1720 | 1735 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | True | NERC PRC 005 | False |  | False | False |  | False | True | False | False | FALSE |  | 0 | 0 | Intermediate (Modified - Tx Decision)
17576 | HONI-HOT Alarm Based Monitoring and Response | N.T.M.1.23 | 4048 | 213 | PLANNING | AIP001127 | AIP001127 | AIP001127 | No | AIP001127 | HONI-HOT Alarm Based Monitoring and Response | 0 |  | Operation of Telecom Services | Miroslav.Kostic@HydroOne.com | Sheraz.Majid@HydroOne.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | AWRD EMPP | Executing | Short Term Planning | Retainer | 2767791.1392 | 2835057.0782 | 2899804.1691 | 2956110.1033 | 3016939.4306 | 3077630.5004 | 0 | 0 | 0 | 0 | 2767791.1392 | 2835057.0782 | 2899804.1691 | 2956110.1033 | 3016939.4306 | 3077630.5004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | True | SLA with HOT | False |  | True | TSA with HOT | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Asset Optimal (Modified-Tx Decision)
17578 | Multi-Station Spill Containment | N.T.C.1.22 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes | [12 empty] | Program | init EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17580 | Stations Environmental Compliance | N.T.M.1.05 | 7053 | 209 | HEALTH, SAFETY & ENV | AIP001015 | AIP001015 | AIP001015 | No | AIP001015 | Stations Environmental Compliance | 0 |  | Environmental Management | Mike.Tanaskovic@HydroOne.com | Sebastian.Niculae@HydroOne.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | EMPP AWRD | Executing | Short Term Planning | Assumption - # of stations sampled | 553357.9979 | 565720.9056 | 578086.0508 | 590977.4896 | 603018.8836 | 615269.2126 | 0 | 0 | 0 | 0 | 553357.9979 | 565720.9056 | 578086.0508 | 590977.4896 | 603018.8836 | 615269.2126 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250 | 250 | 250 | 250 | 250 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | True | Requirements within indivudual site specific ECA's. | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Asset Optimal
17581 | Transmission PCB and Regulated Waste Manage | N.T.M.1.05 | 7053 | 209 | HEALTH, SAFETY & ENV | AIP001016 | AIP001016 | AIP001016 | No | AIP001016 | Transmission PCB and Regulated Waste Manage | 0 |  | Environmental Management | Mike.Tanaskovic@HydroOne.com | Harshal.Bhatt@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | AWRD EMPP | Executing | Short Term Planning | 209-TM1XX | 2589861.7088 | 3830867.7724 | 3914599.7347 | 4001896.6681 | 4083436.9286 | 4166540.0352 | 0 | 0 | 0 | 0 | 2589861.7088 | 3830867.7724 | 3914599.7347 | 4001896.6681 | 4083436.9286 | 4166540.0352 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | True | Environment Canada PCB regulation (SOR/2008-273) | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Asset Optimal (Modified - Tx Decision)
17582 | Spill Containment System Commissioning | N.T.M.1.05 | 7370 | 206 | TX LINES AND STATIONS | AIP001013 | AIP001013 | AIP001013 | No | AIP001013 | Environmental Spill Containment Commissioning | 0 |  | Environmental Management | Mike.Tanaskovic@HydroOne.com | Sebastian.Niculae@HydroOne.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | ACTN EMPP | Executing | Short Term Planning | # of Sumps | 494803.1986 | 502010.8621 | 513232.4909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 494803.1986 | 502010.8621 | 513232.4909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Asset Optimal
17584 | Environmental Mgt- Demand Corrective Mtc | N.T.M.1.05 | 7370 | 206 | TX LINES AND STATIONS | AIP001011A | AIP001011 | AIP001011 | No | AIP001011 | Environmental Corrective Maintenance | 0 |  | Environmental Management | Mike.Tanaskovic@HydroOne.com | Sebastian.Niculae@HydroOne.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | EMPP ACTN | Executing | Short Term Planning | # of Orders | 310160.673 | 582013.2817 | 583194.8293 | 584718.8489 | 584996.188 | 585272.0509 | 0 | 0 | 0 | 0 | 310160.673 | 582013.2817 | 583194.8293 | 584718.8489 | 584996.188 | 585272.0509 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 110 | 110 | 110 | 110 | 110 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Intermedia (Tx Constraint Reduction)
17587 | 2008 R&D Program - Kinectrics | N.T.M.2.21 | 4337 | 223 | SMART METERS | UNPLND |  |  | Yes |  |  |  |  | Technology Program | Daila.Dzintars@HydroOne.com | [6 empty] | Program | EMPP AWRD | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17590 | 2008 R&D Program - Kinectrics | N.D.M.2.21 | 4337 | 223 | SMART METERS | UNPLND |  |  | Yes |  |  |  |  | Distribution RD&D | Daila.Dzintars@HydroOne.com | [6 empty] | Program | EMPP AWRD | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17594 | Connection of OPG Wawaitin GS (Proj ID #251) | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000199 |  | AIP000199 | Yes | AIP000199 | Large Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17595 | Connection of OPG Sandy Falls GS (Proj ID #250) | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000199 |  | AIP000199 | Yes | AIP000199 | Large Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17600 | DS Station Refurbishment Program | N.D.C.1.08 | 7700 | 203 | PROJECT DELIVERY | AIP000160A | AIP000160 | AIP000160 | No | AIP000160 | DS Station Refurbishment Program |  |  | Distributing & Regulating Stations | emre.aydin@HydroOne.com | Nathan.Cox@hydroone.com | System Renewal | N/A | 0 | 03 - None (default) | 0 | Program | EMPP ACTN | Executing | Short Term Planning | # of Stations | 9311125.5551 | 15982591.862 | 29909511.0912 | 30524977.7072 | 31133722.5255 | 0 | 0 | 0 | 0 | 0 | 10011962.9625 | 17185582.6473 | 32160764.6142 | 32822556.6744 | 33477120.9952 | 0 | 0 | 0 | 0 | 0 | -700837.4074 | -1202990.7853 | -2251253.523 | -2297578.9672 | -2343398.4697 | 0 | 0 | 0 | 0 | 0 | -7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 9 | 13 | 15 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Plan B - Modified - Scenario 1
17605 | DS Corrective Maintenance - Planned - Station Mtce | N.D.M.1.04 | 7370 | 206 | TX LINES AND STATIONS | AIP000252 | AIP000252 | AIP000252 | No | AIP000252 | DS Corrective Maintenance - Planned - Station |  |  | Distributing and Regulating Stations | emre.aydin@HydroOne.com | Trevor.Beausoleil@HydroOne.com | System O&M | N/A | 0 | 03 - None (default) | 0 | Program | ACTN EMPP | Executing | Short Term Planning | # of Orders | 5634021.1558 | 5804230.4548 | 5800628.2096 | 5854425.2115 | 5916451.0847 | 0 | 0 | 0 | 0 | 0 | 5634021.1558 | 5804230.4548 | 5800628.2096 | 5854425.2115 | 5916451.0847 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Vulnerable
17606 | DS Preventive Maintenance - Planned - Station Mtce | N.D.M.1.04 | 7370 | 206 | TX LINES AND STATIONS | AIP000257 | AIP000257 | AIP000257 | No | AIP000257 | DS Preventive Maintenance - Station |  |  | Distributing and Regulating Stations | emre.aydin@HydroOne.com | Trevor.Beausoleil@HydroOne.com | System O&M | N/A | 0 | 03 - None (default) | 0 | Program | EMPP ACTN | Executing | Short Term Planning | # of Orders | 4297880.8387 | 4428308.9958 | 4525138.5306 | 4625759.3299 | 4711942.2791 | 0 | 0 | 0 | 0 | 0 | 4297880.8387 | 4428308.9958 | 4525138.5306 | 4625759.3299 | 4711942.2791 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6234 | 6234 | 6234 | 6234 | 6234 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Vulnerable
17635 | TODS Database Maintenance | N.T.M.1.14 | 7716 | 224 | ENGINEERING | AIP001037 | AIP001037 | AIP001037 | No | AIP001037 | Other Mtce - P&C - TODS Database | 0 |  | Engineering and Environmental Support | Mike.Tanaskovic@HydroOne.com | Farinaz.Yousefi@HydroOne.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | EMPP ACTN | Executing | Short Term Planning | Retainer | 148274.5253 | 287470.8307 | 287994.2497 | 288643.7475 | 288749.9785 | 288839.1085 | 0 | 0 | 0 | 0 | 148274.5253 | 287470.8307 | 287994.2497 | 288643.7475 | 288749.9785 | 288839.1085 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Intermediate (Modified-Tx Decision)
17636 | P&C Emergency Correctives | N.T.M.1.17 | 7370 | 206 | TX LINES AND STATIONS | AIP001083A | AIP001083 | AIP001083 | No | AIP001083 | P&C Corrective Maintenance | 0 |  | Protection Control & Metering Equipment | Miroslav.Kostic@HydroOne.com | warren.tingle@hydroone.com | System O&M | 0 | 0 | 02 - Expectation (no agreement) | 0 | Program | EMPP ACTN | Executing | Short Term Planning | # of DR's and TC's | 3463622.3901 | 3514076.2693 | 3790527.6416 | 3675061.0944 | 3751298.0038 | 4811618.5411 | 0 | 0 | 0 | 0 | 3463622.3901 | 3514076.2693 | 3790527.6416 | 3675061.0944 | 3751298.0038 | 4811618.5411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | True | False |  | False | False | False | False | FALSE |  | 0 | 0 | Intermediate (Modified-Tx Decision)
17637 | P&C Technical Services | N.T.M.1.17 | 7716 | 224 | ENGINEERING | AIP001084 | AIP001084 | AIP001084 | No | AIP001084 | P&C Support (NOEA/Spares/data and info mgmnt) | 0 |  | Protection Control & Metering Equipment | Miroslav.Kostic@HydroOne.com | warren.tingle@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | ACCP EMPP | Executing | Short Term Planning | Retainer | 6394641.3843 | 6540890.3446 | 6683855.8721 | 6832908.1632 | 6972131.372 | 7113769.1202 | 0 | 0 | 0 | 0 | 6394641.3843 | 6540890.3446 | 6683855.8721 | 6832908.1632 | 6972131.372 | 7113769.1202 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Vulnerable
17638 | P&C Preventive Maintenance | N.T.M.1.17 | 7370 | 206 | TX LINES AND STATIONS | AIP001081 | AIP001081 | AIP001081 | No | AIP001081 | P&C Preventive Maintenance (1) | 0 |  | Protection Control & Metering Equipment | Miroslav.Kostic@HydroOne.com | warren.tingle@hydroone.com | System O&M | 0 | 0 | 02 - Expectation (no agreement) | 0 | Program | EMPP ACTN | Executing | Short Term Planning | # of Orders | 3661837.8995 | 3714632.4464 | 3866143.0896 | 4689075.7758 | 4672647.1281 | 4170820.5695 | 0 | 0 | 0 | 0 | 3661837.8995 | 3714632.4464 | 3866143.0896 | 4689075.7758 | 4672647.1281 | 4170820.5695 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1476 | 1515 | 1606 | 1938 | 1931 | 1725 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | True | NERC PRC-005 | False |  | False | False |  | False | True | False | False | FALSE |  | 0 | 0 | Reggregated ((1)/(2) Optimal)
17639 | P&C Planned Correctives | N.T.M.1.17 | 7370 | 206 | TX LINES AND STATIONS | AIP001083B | AIP001083 | AIP001083 | No | AIP001083 | P&C Corrective Maintenance | 0 |  | Protection Control & Metering Equipment | Miroslav.Kostic@HydroOne.com | warren.tingle@hydroone.com | System O&M | 0 | 0 | 02 - Expectation (no agreement) | 0 | Program | ACTN EMPP | Executing | Short Term Planning | # of DR's and TC's | 3443048.8063 | 3490364.3422 | 3766815.7146 | 3651349.1674 | 3727586.0767 | 4787906.6141 | 0 | 0 | 0 | 0 | 3443048.8063 | 3490364.3422 | 3766815.7146 | 3651349.1674 | 3727586.0767 | 4787906.6141 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | True | False |  | False | False | False | False | FALSE |  | 0 | 0 | Intermediate (Modified-Tx Decision)
17643 | Power Qualiy Monitoring: Install Power Quality Mon | N.T.C.2.20 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Performance Enhancement | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17644 | Connection of AIM PowerGen Corp - Frogmore Wind F | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000199 |  | AIP000199 | Yes | AIP000199 | Large Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17648 | Town of Thessalon Rebuild - Phase 4 of 4 | N.D.C.1.07 | 7374 | 205 | LINES | UNPLND |  |  | Yes |  |  |  |  | Lines | emre.aydin@HydroOne.com | [6 empty] | Program | EMPP AWRD | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17652 | Malvern TS: Provide Connection to 26M22 Feeder Pos | N.T.C.2.11 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Load Customer Connection | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17664 | Ear Falls Generation Expansion | N.T.C.2.12 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Generator Customer Connection | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17674 | Cyber Security Compliance Project - Systems Manage | N.T.C.1.29 | 4032 | 212 | INFO SOLUTIONS DIVISION | UNPLND |  |  | Yes |  |  |  |  | NERC Cyber Security Compliance Readiness | lincoln.frost-hunt@hydroone.com | [6 empty] | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17675 | Rexdale TS: Provide Connection to M31 Feeder Posit | N.T.C.1.21 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Infrastructure | James.Mardegan@HydroOne.com | [6 empty] | Project | init EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17680 | Connection of Gengrowth - Comber Wind Farm (Proj I | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000199 |  | AIP000199 | Yes | AIP000199 | Large Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17693 | Sir Adam Beck TS #1: Installation of Isolating E B | N.T.C.2.12 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Generator Customer Connection | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17708 | 2008 ABB HPL Replacement Program | N.T.C.1.01 | 7700 | 203 | PROJECT DELIVERY | 17 |  |  | Yes |  |  |  |  | Circuit Breakers | James.Mardegan@HydroOne.com | [6 empty] | Program | EMPP AWRD | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17716 | ABCB Auxillary Component Remediation | N.T.M.1.16 | 7370 | 206 | TX LINES AND STATIONS | AIP001044A | AIP001044 | AIP001044 | No | AIP001044 | Circuit Breaker Maintenance and Refurbishment | 0 |  | Power Equipment | Mike.Tanaskovic@HydroOne.com | kristoffer.hammel@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | ACTN EMPP | Executing | Short Term Planning | # of Breakers | 96634.8664 | 135132.2672 | 106035.8845 | 86683.1026 | 47441.9121 | 47464.8319 | 0 | 0 | 0 | 0 | 96634.8664 | 135132.2672 | 106035.8845 | 86683.1026 | 47441.9121 | 47464.8319 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 7 | 5 | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | True | OPG Darlington has provided their overhaul schedule for their generating units, with the expectation that we will complete the refurbishment of the breakers within the timing of the unit overhaul, in order to minimize requirements for outages for performing this type of maintenance in the future. | False | False | False | True | FALSE |  | 0 | 0 | Intermediate (Modified - Tx Decision)
17734 | Install Animal Deterrent Fences at various Station | N.T.C.2.20 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Performance Enhancement | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17740 | Generation Connection for Kingsville Energy Leamin | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Distribution Generation Connection | ryan.boudreau@HydroOne.com | [6 empty] | Project | EMPP EXTR | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17752 | Ottawa - Alta Vista Hospital Link - Recoverable | N.T.C.1.14 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Third Party Transmission System Modifications | john.boldt@HydroOne.com | [6 empty] | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17759 | Moses GS-St. Lawrence Line Differential Protection | N.T.C.1.19 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Protection Control & Metering Equip | Miroslav.Kostic@HydroOne.com | [6 empty] | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17765 | New Liskeard DS #1 - Exchange Transformer & Add 3r | N.D.C.2.02 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17778 | Porcupine TS - Install 2x100 MVAr Shunt Cap Bank | N.T.C.2.03 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Network Transfer Capability | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17781 | Generation Connection for Donnandale Farm GCD ID 8 | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Distribution Generation Connection | ryan.boudreau@HydroOne.com | [6 empty] | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17783 | South Porcupine Voltage Conversion | N.D.C.1.07 | 7374 | 205 | LINES | AIP000152 |  | AIP000152 | Yes | AIP000152 | Large Sustainment Initiatives | ISD-SR-12 | Distribution Lines Sustainment Initiatives | Lines | emre.aydin@HydroOne.com | Alexander.Hamlyn@HydroOne.com | System Renewal | N/A | 0 | 03 - None (default) | 0 | Program | EMPP ACCP | Executing | Short Term Planning | # of projects | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17786 | Jarvis TS: Install Current Limiting Reactors & Loa | N.T.C.2.21 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Major Risk Mitigation | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17795 | Station Charger Replacement Program | N.T.C.1.20 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Ancillary Systems | James.Mardegan@HydroOne.com | [6 empty] | Program | ACTN EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17797 | BULK Station Service Upgrades Program | N.T.C.1.20 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Ancillary Systems | James.Mardegan@HydroOne.com | [6 empty] | Program | EMPP ACCP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17800 | HV Capacitor Bank Replacement | N.T.C.1.18 | 7700 | 203 | PROJECT DELIVERY | AIP000570 |  | AIP000570 | Yes | AIP000570 |  |  |  | Other Power Equipment | James.Mardegan@HydroOne.com | [6 empty] | Program | ACCP EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17810 | Oil Circuit Breaker Replacement Program | N.T.C.1.01 | 7700 | 203 | PROJECT DELIVERY | AIP000379 |  | AIP000379 | Yes | AIP000379 |  |  |  | Circuit Breakers | James.Mardegan@HydroOne.com | [6 empty] | Program | ACCP EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17812 | Roads Bridges & Rlwys Inspection Program | N.T.M.1.19 | 7716 | 224 | ENGINEERING | AIP001106 |  | AIP001106 | Yes | AIP001106 |  |  |  | Infrastructure Maintenance | Mike.Tanaskovic@HydroOne.com | [6 empty] | Program | EMPP ACCP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17817 | Infrastructure Corrective Maintenance - Planned | N.T.M.1.19 | 7370 | 206 | TX LINES AND STATIONS | AIP001107B | AIP001107 | AIP001107 | No | AIP001107 | Tx Infrastructure Corrective Maintenance | 0 |  | Infrastructure Maintenance | Mike.Tanaskovic@HydroOne.com | Sebastian.Niculae@HydroOne.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | ACTN EMPP | Executing | Short Term Planning | # of Orders | 1689736.164 | 1970434.7126 | 2288114.4275 | 2077998.1136 | 2127831.5559 | 2442766.0636 | 0 | 0 | 0 | 0 | 1689736.164 | 1970434.7126 | 2288114.4275 | 2077998.1136 | 2127831.5559 | 2442766.0636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Intermediate - (Modified-Tx Decision)
17826 | Data Collection | N.D.M.1.07 | 7374 | 205 | LINES | AIP000268 | AIP000268 | AIP000268 | No | AIP000268 | Data Collection |  |  | Other Services | emre.aydin@HydroOne.com | patrick.howe@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | AWRD EMPP | Executing | Short Term Planning |  | 571723.7175 | 589073.9115 | 601954.6272 | 615339.609 | 626804.0502 | 0 | 0 | 0 | 0 | 0 | 571723.7175 | 589073.9115 | 601954.6272 | 615339.609 | 626804.0502 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Demand
17827 | Joint Use and Relocations (Yearly) | N.D.C.1.03 | 7374 | 205 | LINES | AIP000129 | AIP000129 | AIP000129 | No | AIP000129 | Joint Use & Line Relocations | ISD-SA-01 | Joint Use and Line Relocations Program | Joint Use and Relocations | john.boldt@HydroOne.com | Jenny.Seo@HydroOne.com | System Access | 0 | 0 | 03 - None (default) | 0 | Program | ACCP EMPP | Executing | Short Term Planning | # of projects | 21741685.3318 | 21978157.4305 | 22231842.5557 | 22484527.3315 | 22726611.8311 | 0 | 0 | 0 | 0 | 0 | 43181179.3435 | 43661957.3661 | 44163449.4758 | 44665977.0967 | 45159347.0539 | 0 | 0 | 0 | 0 | 0 | -2765872.8217 | -2796881.2356 | -2830016.1901 | -2863232.2352 | -2894931.6128 | 0 | 0 | 0 | 0 | 0 | -11.2924 | 0 | -18673621.19 | -18886918.7 | -19101590.73 | -19318217.53 | -19537803.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Critical Spend Plan
17843 | PN Upgrades | N.T.C.1.19 | 7700 | 203 | PROJECT DELIVERY | AIP000608 | AIP000608 | AIP000608 | No | AIP000608 | PN Upgrades | 0 |  | Protection Control & Metering Equip | Miroslav.Kostic@HydroOne.com | warren.tingle@hydroone.com | System Renewal | 0 | 0 | 03 - None (default) | 0 | Program | ACCP EMPP | Executing | Short Term Planning | # of Upgrades | 1888376.1883 | 1919644.7588 | 1941829.811 | 1956870.5862 | 1971739.8279 | 1993908.1254 | 0 | 0 | 0 | 0 | 2030512.0305 | 2064134.1492 | 2087989.0441 | 2104161.9207 | 2120150.3526 | 2143987.2316 | 0 | 0 | 0 | 0 | -142135.8421 | -144489.3904 | -146159.2331 | -147291.3344 | -148410.5247 | -150079.1062 | 0 | 0 | 0 | 0 | -7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | True | False |  | False | False | False | False | FALSE |  | 0 | 0 | Demand
17846 | Power Transformer Rad Refurbishment / Paint | N.T.M.1.16 | 7370 | 206 | TX LINES AND STATIONS | AIP001071A | AIP001071 | AIP001071 | No | AIP001071 | Transformer Refurbishments | 0 |  | Power Equipment | Mike.Tanaskovic@HydroOne.com | perry.ng@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | ACTN EMPP | Executing | Short Term Planning | # of Transformers | 989606.3972 | 1512807.5399 | 1546472.4265 | 1581801.0196 | 1614473.9303 | 1647812.1855 | 0 | 0 | 0 | 0 | 989606.3972 | 1512807.5399 | 1546472.4265 | 1581801.0196 | 1614473.9303 | 1647812.1855 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | False |  | False | True | False | False | FALSE |  | 0 | 0 | Asset Optimal Modified (Tx Decision)
17847 | Power Transformer Oil Dehydration Program | N.T.M.1.16 | 7370 | 206 | TX LINES AND STATIONS | AIP001071B | AIP001071 | AIP001071 | No | AIP001071 | Transformer Refurbishments | 0 |  | Power Equipment | Mike.Tanaskovic@HydroOne.com | perry.ng@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | ACTN EMPP | Executing | Short Term Planning | # of Transformers | 296881.9192 | 301206.5407 | 307939.518 | 315005.1895 | 321539.8188 | 328207.4463 | 0 | 0 | 0 | 0 | 296881.9192 | 301206.5407 | 307939.518 | 315005.1895 | 321539.8188 | 328207.4463 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 30 | 30 | 30 | 30 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | False |  | False | True | False | False | FALSE |  | 0 | 0 | Asset Optimal Modified (Tx Decision)
17852 | Replace EoL Stn Service Transformers | N.T.C.1.17 | 7700 | 203 | PROJECT DELIVERY | AIP000555 |  | AIP000555 | Yes | AIP000555 |  |  |  | Power Transformers | James.Mardegan@HydroOne.com | [6 empty] | Program | ACTN EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17853 | Retail Revenue Meters | N.D.C.2.01 | 7374 | 205 | LINES | AIP000179 | AIP000179 | AIP000179 | No | AIP000179 | Retail Revenue Meters | ISD-SA-04 | New Load Connections, Upgrades, Cancellations and Metering | New Load Connection Upg/Cancel/Meters | emre.aydin@HydroOne.com | michael.sullivan@hydroone.com | System Access | N/A | 0 | 03 - None (default) | 0 | Program | ACTN EMPP | Executing | Short Term Planning | Retainer | 11245277.8796 | 11534105.1858 | 11842724.1264 | 12157650.0319 | 12473716.558 | 0 | 0 | 0 | 0 | 0 | 11245277.8796 | 11534105.1858 | 11842724.1264 | 12157650.0319 | 12473716.558 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Demand
17857 | Residential, Subdivision, Expansion | N.D.C.2.01 | 7374 | 205 | LINES | AIP000177A | AIP000177 | AIP000177 | No | AIP000177 | New Connections |  |  | New Load Connection Upg/Cancel/Meters | emre.aydin@HydroOne.com | michael.sullivan@hydroone.com | System Access | N/A | 0 | 03 - None (default) | 0 | Program | AWRD EMPP | Executing | Short Term Planning | # of Connects | 65498874.2127 | 67354169.3916 | 69097667.7375 | 70998596.5235 | 72966502.623 | 0 | 0 | 0 | 0 | 0 | 84899317.0828 | 87326204.3769 | 89662650.2173 | 92173656.6242 | 94767757.163 | 0 | 0 | 0 | 0 | 0 | -661604.79 | -680345.1454 | -697956.2398 | -717157.5406 | -737035.38 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | -18738838.08 | -19291689.84 | -19867026.24 | -20457902.56 | -21064219.16 | 0 | 0 | 0 | 0 | 0 | 14724 | 14862 | 15005 | 15148 | 15291 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Demand
17858 | Generation Connection for Skyway 124 Wind Farm GCD | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000199 |  | AIP000199 | Yes | AIP000199 | Large Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17871 | Connection of Matthias GS 2.812MW (GCD ID#42) | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Distribution Generation Connection | ryan.boudreau@HydroOne.com | [6 empty] | Project | EMPP AWRD | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17873 | DS Corrective Maintenance - Demand - Station Mtce | N.D.M.1.04 | 7370 | 206 | TX LINES AND STATIONS | AIP000250 | AIP000250 | AIP000250 | No | AIP000250 | DS Corrective Maintenance - Demand - Station |  |  | Distributing and Regulating Stations | emre.aydin@HydroOne.com | Trevor.Beausoleil@HydroOne.com | System O&M | N/A | 0 | 03 - None (default) | 0 | Program | ACTN EMPP | Executing | Short Term Planning | # of Orders | 3159944.1353 | 3255839.2356 | 3327031.4816 | 3401011.2852 | 3464375.8444 | 0 | 0 | 0 | 0 | 0 | 3159944.1353 | 3255839.2356 | 3327031.4816 | 3401011.2852 | 3464375.8444 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
17875 | Install 7 Capacitor Banks in SWO: OPA Near Term Me | N.T.C.2.03 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Network Transfer Capability | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17878 | Tx Lines - RoW G&S Preventive Maintenance | N.T.M.1.07 | 7370 | 206 | TX LINES AND STATIONS | AIP001020 | AIP001020 | AIP001020 | No | AIP001020 | Ground & Sites Preventive Maintenance | 0 |  | Rights of Way | hassan.hamzeh@hydroone.com | Shannon.O'Keefe@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | ACTN EMPP | Executing | Short Term Planning | # of Work Orders | 912112.9673 | 918473.9937 | 930115.8555 | 942344.901 | 952609.1681 | 962880.6497 | 0 | 0 | 0 | 0 | 912112.9673 | 918473.9937 | 930115.8555 | 942344.901 | 952609.1681 | 962880.6497 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | True | Grass cutting and snow removal maintenance is required to meet municipal bi-laws. | False |  | False | False |  | False | True | True | False | FALSE |  | 0 | 0 | Optimal (Modified)
17883 | Health Fairs | N.C.M.3.03 | 4337 | 223 | SMART METERS | UNPLND |  |  | Yes |  |  |  |  | Environment Health and Safety | welchw@hydroone.com | [6 empty] | Program | EMPP AWRD | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17891 | Trout Lake TS M8 - Replace Conductor | N.D.C.1.07 | 7374 | 205 | LINES | AIP000152 |  | AIP000152 | Yes | AIP000152 | Large Sustainment Initiatives | ISD-SR-12 | Distribution Lines Sustainment Initiatives | Lines | emre.aydin@HydroOne.com | Alexander.Hamlyn@HydroOne.com | System Renewal | N/A | 0 | 03 - None (default) | 0 | Program | ACCP EMPP | Executing | Short Term Planning | # of projects | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17911 | Tx Lines - RoW Line Clearing | N.T.M.1.07 | 7362 | 204 | FORESTRY | AIP001022 | AIP001022 | AIP001022 | No | AIP001022 | ROW Line Clearing- L0, Vulnerable | 0 |  | Rights of Way | hassan.hamzeh@hydroone.com | Shannon.O'Keefe@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | ACCP EMPP | Executing | Short Term Planning | route km | 6514194.1455 | 6592003.5306 | 6673521.9234 | 6748291.751 | 6820473.6303 | 6892298.7259 | 0 | 0 | 0 | 0 | 6514194.1455 | 6592003.5306 | 6673521.9234 | 6748291.751 | 6820473.6303 | 6892298.7259 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | True | The transmission ROWs selected for brush control maintenance in the vulnerable investment level are critical circuits regulated by NERC standard FAC-003-04. | False |  | False | False |  | False | True | False | False | FALSE |  | 0 | 0 | Reaggregated (Vulnerable/Intermediate (Modified))
17917 | Brockville Water DS T2 | N.D.C.2.02 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17918 | Brockville 44 kV Downtown Cable Rehabilitation | N.D.C.1.07 | 7374 | 205 | LINES | AIP000152 |  | AIP000152 | Yes | AIP000152 | Large Sustainment Initiatives | ISD-SR-12 | Distribution Lines Sustainment Initiatives | Lines | emre.aydin@HydroOne.com | Alexander.Hamlyn@HydroOne.com | System Renewal | N/A | 0 | 03 - None (default) | 0 | Program | ACCP EMPP | Executing | Short Term Planning | # of projects | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17930 | H24C H26C C28C M29C Relocation Recoverable | N.T.C.1.12 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Overhead Lines Component Refurb & Repl | hassan.hamzeh@hydroone.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17931 | DC Signaling (remote trip) Replacement | N.T.C.1.25 | 7700 | 203 | PROJECT DELIVERY | AIP000641 |  | AIP000641 | Yes | AIP000641 |  |  |  | Auxiliary Telecommunication Equipment | Miroslav.Kostic@HydroOne.com | [6 empty] | Program | ACCP EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17938 | Circuit Breakers - Delle Ram & Cap Refurbishment | N.T.M.1.16 | 7370 | 206 | TX LINES AND STATIONS | UNPLND |  |  | Yes |  |  |  |  | Power Equipment | Mike.Tanaskovic@HydroOne.com | [6 empty] | Program | ACTN EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17942 | 2010 Generation Connections - Line Transfers Trini | N.D.C.2.03 | 7374 | 205 | LINES | UNPLND |  |  | Yes |  |  |  |  | Distribution Generation Connection | ryan.boudreau@HydroOne.com | [6 empty] | Program | ACCP EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17943 | Connection of Micro-Generation Facilities Und | N.D.C.2.03 | 7374 | 205 | LINES | UNPLND |  |  | Yes |  |  |  |  | Distribution Generation Connection | ryan.boudreau@HydroOne.com | [6 empty] | Program | ACCP EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17953 | HONI-HOT Carrier Vendor Management | N.T.M.1.23 | 4048 | 213 | PLANNING | AIP001128 | AIP001128 | AIP001128 | No | AIP001128 | HONI-HOT Carrier Vendor Management | 0 |  | Operation of Telecom Services | Miroslav.Kostic@HydroOne.com | Sheraz.Majid@HydroOne.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | AWRD EMPP | Executing | Short Term Planning | Retainer | 1344355.6962 | 1377877.4297 | 1410178.7398 | 1443218.7373 | 1473620.6596 | 1503955.3578 | 0 | 0 | 0 | 0 | 1344355.6962 | 1377877.4297 | 1410178.7398 | 1443218.7373 | 1473620.6596 | 1503955.3578 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | True | SLA with HOT | False |  | True | TSA with HOT | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Asset Optimal (Modified-Tx Decision)
17954 | PSTS Leased Circuits | N.T.M.1.24 | 4048 | 213 | PLANNING | AIP001135 | AIP001135 | AIP001135 | No | AIP001135 | PSTS Leased Circuits | 0 |  | Leased Facilities | Miroslav.Kostic@HydroOne.com | Sheraz.Majid@HydroOne.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | AWRD EMPP | Executing | Short Term Planning | Assumption - # of circuits | 7361627.3523 | 8391174.4191 | 8470010.1911 | 8647368.5446 | 8811852.673 | 8990864.1288 | 0 | 0 | 0 | 0 | 7361627.3523 | 8391174.4191 | 8470010.1911 | 8647368.5446 | 8811852.673 | 8990864.1288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | True | leased facilities agreements | False |  | False |  | False | False |  | False | False | False | False | TRUE | program is for on-going costs of leased facilities | 0 | 0 | Asset Optimal
17957 | Meter Corrective Maintenance – Planned | N.T.M.1.17 | 7370 | 206 | TX LINES AND STATIONS | AIP001077 |  | AIP001077 | Yes | AIP001077 |  |  |  | Protection Control & Metering Equipment | Miroslav.Kostic@HydroOne.com | [6 empty] | Program | ACTN EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17958 | Meter Preventive Maintenance – Planned | N.T.M.1.17 | 7370 | 206 | TX LINES AND STATIONS | AIP001079 |  | AIP001079 | Yes | AIP001079 |  |  |  | Protection Control & Metering Equipment | Miroslav.Kostic@HydroOne.com | [6 empty] | Program | ACTN EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17959 | Neutralizing Transformer | N.T.C.1.25 | 7700 | 203 | PROJECT DELIVERY | AIP000652 |  | AIP000652 | Yes | AIP000652 |  |  |  | Auxiliary Telecommunication Equipment | Miroslav.Kostic@HydroOne.com | [6 empty] | Program | EMPP ACCP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17960 | 2010 PM Wawa Breaker Replacement Program | N.T.C.1.01 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Circuit Breakers | James.Mardegan@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17966 | GCD 1084- Generation Connection for Clear Creek II | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000199 |  | AIP000199 | Yes | AIP000199 | Large Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | EMPP ACTN | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17974 | Telecom PLND Corrective Maintenance | N.T.M.1.22 | 7370 | 206 | TX LINES AND STATIONS | AIP001123A | AIP001123 | AIP001123 | No | AIP001123 | Telecom Corrective Maintenance | 0 |  | Telecommunication Assets Maintenance | Miroslav.Kostic@HydroOne.com | Sheraz.Majid@HydroOne.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | ACTN EMPP | Executing | Short Term Planning | # of Orders | 1448824.6698 | 1908927.1584 | 2138012.1902 | 1996384.2717 | 2036618.917 | 2528850.4872 | 0 | 0 | 0 | 0 | 1448824.6698 | 1908927.1584 | 2138012.1902 | 1996384.2717 | 2036618.917 | 2528850.4872 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 680 | 879 | 965 | 879 | 879 | 1068 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | True | NERC, NPCC, Transport Canada, CSA, etc. | False |  | True | False |  | False | False | False | False | FALSE |  | 0 | 0 | Asset Optimal (Modified-Tx Decision)
17984 | HONI-HOT Coordination of Network Management | N.T.M.1.23 | 4048 | 213 | PLANNING | AIP001129 | AIP001129 | AIP001129 | No | AIP001129 | HONI-HOT Coordination of Network Management | 0 |  | Operation of Telecom Services | Miroslav.Kostic@HydroOne.com | Sheraz.Majid@HydroOne.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | EMPP AWRD | Executing | Short Term Planning | Retainer | 3874907.674 | 3955202.1184 | 4041850.3316 | 4140544.7912 | 4221723.8237 | 4302706.7191 | 0 | 0 | 0 | 0 | 3874907.674 | 3955202.1184 | 4041850.3316 | 4140544.7912 | 4221723.8237 | 4302706.7191 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | True | SLA with HOT | False |  | True | TSA with HOT | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Asset Optimal (Modified-Tx Decision)
17985 | HONI-HOT System Analysis | N.T.M.1.23 | 4048 | 213 | PLANNING | AIP001133 | AIP001133 | AIP001133 | No | AIP001133 | HONI-HOT System Analysis | 0 |  | Operation of Telecom Services | Miroslav.Kostic@HydroOne.com | Sheraz.Majid@HydroOne.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | AWRD EMPP | Executing | Short Term Planning | Retainer | 415168.6709 | 426249.8524 | 436956.7926 | 447895.4702 | 448060.3115 | 458158.5858 | 0 | 0 | 0 | 0 | 415168.6709 | 426249.8524 | 436956.7926 | 447895.4702 | 448060.3115 | 458158.5858 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | True | SLA contract with HOT | False |  | True | TSA with HOT | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Asset Optimal (Modified-Tx Decision)
17990 | Connection of Skypower - Lennox 1 GS (ID #1072) | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000199 |  | AIP000199 | Yes | AIP000199 | Large Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17992 | Install 115kV Switch at L7S Tap to St Marys Cement | N.T.C.2.20 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Performance Enhancement | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17993 | Procurement of materials having long lead times | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000199 |  | AIP000199 | Yes | AIP000199 | Large Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17995 | GCD1073-Napanee TS-Lennox #2 | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | 2 |  |  | Yes |  |  |  |  | Distribution Generation Connection | ryan.boudreau@HydroOne.com | [6 empty] | Project | EMPP AWRD | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17997 | 2009 Oil Circuit Breaker Replacement and Dymond TS | N.T.C.1.08 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | System Re-investment | James.Mardegan@HydroOne.com | [6 empty] | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17998 | Tx Aviation Light Replacement Program | N.T.C.1.12 | 7370 | 206 | TX LINES AND STATIONS | AIP000454 | AIP000454 | AIP000454 | No | AIP000454 | Tx Aviation Light Replacement Program | 0 |  | Overhead Lines Component Refurb & Repl | hassan.hamzeh@hydroone.com | jacky.chiu@hydroone.com | System Renewal | 0 | 0 | 03 - None (default) | 0 | Program | EMPP ACTN | Executing | Short Term Planning | # of lighting systems | 1742179.3588 | 1771027.1366 | 1791494.6437 | 1805370.9668 | 1819089.032 | 1839541.1645 | 0 | 0 | 0 | 0 | 1979749.2714 | 2012530.837 | 2035789.3678 | 2051557.9168 | 2067146.6272 | 2090387.6869 | 0 | 0 | 0 | 0 | -237569.9126 | -241503.7004 | -244294.7241 | -246186.95 | -248057.5953 | -250846.5224 | 0 | 0 | 0 | 0 | -12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 13 | 13 | 13 | 13 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | True | Transport Canada Standard 621 - Obstruction Marking and Lighting | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Intermediate
18014 | Generation Connection of Mohawk Wind Farm Design a | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000199 |  | AIP000199 | Yes | AIP000199 | Large Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18029 | Lambton TS M5 - St. Clair Solar 1 -ID#1007 | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000199 |  | AIP000199 | Yes | AIP000199 | Large Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | EMPP ACTN | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18030 | Lambton TS M5 - St. Clair Solar 2 -ID#1008 | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000199 |  | AIP000199 | Yes | AIP000199 | Large Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18032 | Lambton TS M3 - St. Clair Solar 3 -ID#1100 | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000199 |  | AIP000199 | Yes | AIP000199 | Large Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18048 | Midhurst TS M3 - Relocate Snow Valley Tap | N.D.C.1.07 | 7374 | 205 | LINES | 6 |  |  | Yes |  |  |  |  | Lines | emre.aydin@HydroOne.com | [6 empty] | Program | init EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18056 | Gesner Wind Farm (formerly Vickery WF) - ID1014 | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000199 |  | AIP000199 | Yes | AIP000199 | Large Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18058 | Armitage TS - M11 & M44 Retermination for PowerStr | N.T.C.2.11 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Load Customer Connection | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18059 | Modeland TS Generation | N.T.C.2.12 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Generator Customer Connection | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | ACTN DETL | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18065 | Connection of Douglas New GS - ID 645 | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000199 |  | AIP000199 | Yes | AIP000199 | Large Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18068 | GCD 585- Connection of Wilno 9.0 MW Wind Farm Proj | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Distribution Generation Connection | ryan.boudreau@HydroOne.com | [6 empty] | Project | DETL ACTN | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18074 | J.Clarke Keith TS M3 ID689 Amherstburg-1 | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000199 |  | AIP000199 | Yes | AIP000199 | Large Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18075 | J.Clarke Keith TS M4 ID1053 Amherstburg Solar | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | 2 |  |  | Yes |  |  |  |  | Distribution Generation Connection | ryan.boudreau@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18076 | Civil Infrastructure-Stn Road & Site Improvements | N.T.C.1.21 | 7700 | 203 | PROJECT DELIVERY | AIP000624 |  | AIP000624 | Yes | AIP000624 |  |  |  | Infrastructure | James.Mardegan@HydroOne.com | [6 empty] | Program | EMPP ACTN | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18079 | Rosseau DS F3-Feeder Development to Horseshoe Lk | N.D.C.2.02 | 7374 | 205 | LINES | UNPLND |  |  | Yes |  |  |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | [6 empty] | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18081 | 2011 Kirkland Lake TS-M62 Split Feeder | N.D.C.2.02 | 7374 | 205 | LINES | AIP000183A |  | AIP000183 | Yes | AIP000183 | (1) System upgrade driven by load growth |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Michael.Medeiros@HydroOne.com | System Service | 0 | 0 | 03 - None (default) | Not Required | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18094 | Trafalgar TS: Install Two 27.6kV Fdr Brkrs Pos | N.T.C.2.11 | 7700 | 203 | PROJECT DELIVERY | DO NOT USE |  |  | Yes |  |  |  |  | Load Customer Connection | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | DETL ACTN | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18102 | TC08 Essex Walker Interim GenCon | N.T.C.2.12 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Generator Customer Connection | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | INSC EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18104 | Essa TS & Middlport TS - Cybectec Gateways for Dx | N.D.C.2.02 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | [6 empty] | Project | EMPP ACTN | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18124 | TC121-08 MULTIPLE STNS 2008 Noise Abatement | N.T.C.1.21 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Infrastructure | James.Mardegan@HydroOne.com | [6 empty] | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18143 | Smith Falls TS GenCon ID 1200 | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | 2 |  |  | Yes |  |  |  |  | Distribution Generation Connection | ryan.boudreau@HydroOne.com | [6 empty] | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18144 | Gordie Howe International Bridge Work | N.T.C.1.14 | 7700 | 203 | PROJECT DELIVERY | AIP000494 | AIP000494 | AIP000494 | No | AIP000494 | Detroit River International Crossing Work | 0 |  | Third Party Transmission System Modifications | john.boldt@HydroOne.com | Gian.Minichini@HydroOne.com | System Renewal | Western | 0 | 01 - Agreement (current/future) | 0 | Project | EMPP ACCP | Executing | Executing |  | -107566.4268 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10327529.1711 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2002.4021 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1.8275 | 0 | -10437098 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43419 | [13 empty] | FALSE |  | 0 | 0 | Detroit River International Crossing Work_Recoverable
18157 | ParrySoundTS ParryIsland CentralGenCon 730 | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Distribution Generation Connection | ryan.boudreau@HydroOne.com | [6 empty] | Project | DETL ACTN | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18165 | 2009 PERIMETER SECURITY UPGRADE AT STATIONS | N.T.C.1.21 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Infrastructure | James.Mardegan@HydroOne.com | [6 empty] | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18168 | IBM PowerStream DC RT Replacement | N.T.C.1.25 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Auxiliary Telecommunication Equipment | Miroslav.Kostic@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18175 | 2008 Missigissauga Tx RoW Landscape Project | N.T.C.1.12 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Overhead Lines Component Refurb & Repl | hassan.hamzeh@hydroone.com | [6 empty] | Program | EMPP init | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18177 | Ancillary Corrective Maintenance - Planned | N.T.M.1.18 | 7370 | 206 | TX LINES AND STATIONS | AIP001088B | AIP001088 | AIP001088 | No | AIP001088 | Ancillary Corrective Maintenance | 0 |  | Ancillary Systems Maintenance | Mike.Tanaskovic@HydroOne.com | Harshal.Bhatt@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | ACTN EMPP | Executing | Short Term Planning | # of Orders | 1163102.6399 | 1156594.812 | 1158957.7895 | 1162006.064 | 1162560.3888 | 1163112.2323 | 0 | 0 | 0 | 0 | 1163102.6399 | 1156594.812 | 1158957.7895 | 1162006.064 | 1162560.3888 | 1163112.2323 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 686 | 686 | 686 | 686 | 686 | 686 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | True | False |  | False | False | False | False | FALSE |  | 0 | 0 | Intermediate (Modified-Tx Decision)
18179 | Human Factors Risk Management | N.C.M.3.03 | 4337 | 223 | SMART METERS | UNPLND |  |  | Yes |  |  |  |  | Environment Health and Safety | welchw@hydroone.com | [6 empty] | Program | EMPP AWRD | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18180 | Human Factors Risk Management | N.C.M.3.03 | 4337 | 223 | SMART METERS | UNPLND |  |  | Yes |  |  |  |  | Environment Health and Safety | welchw@hydroone.com | [6 empty] | Program | AWRD EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18181 | ICM Upgrades and License Fee | N.C.M.3.03 | 4337 | 223 | SMART METERS | UNPLND |  |  | Yes |  |  |  |  | Environment Health and Safety | welchw@hydroone.com | [6 empty] | Program | AWRD EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18182 | ICM Upgrades and License Fee | N.C.M.3.03 | 4337 | 223 | SMART METERS | UNPLND |  |  | Yes |  |  |  |  | Environment Health and Safety | welchw@hydroone.com | [6 empty] | Program | EMPP AWRD | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18183 | MSD Prevention Program | N.C.M.3.03 | 4337 | 223 | SMART METERS | UNPLND |  |  | Yes |  |  |  |  | Environment Health and Safety | welchw@hydroone.com | [6 empty] | Program | AWRD EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18184 | MSD Prevention Program | N.C.M.3.03 | 4337 | 223 | SMART METERS | UNPLND |  |  | Yes |  |  |  |  | Environment Health and Safety | welchw@hydroone.com | [6 empty] | Program | AWRD EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18185 | Species at Risk | N.C.M.3.03 | 4337 | 223 | SMART METERS | UNPLND |  |  | Yes |  |  |  |  | Environment Health and Safety | welchw@hydroone.com | [6 empty] | Program | EMPP AWRD | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18186 | Public Safety Educational Materials | N.C.M.3.03 | 4337 | 223 | SMART METERS | UNPLND |  |  | Yes |  |  |  |  | Environment Health and Safety | welchw@hydroone.com | [6 empty] | Program | AWRD EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18188 | SONET Sync Clock Replacement | N.T.C.1.25 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Auxiliary Telecommunication Equipment | Miroslav.Kostic@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18202 | Arc Flash | N.C.M.3.03 | 4337 | 223 | SMART METERS | UNPLND |  |  | Yes |  |  |  |  | Environment Health and Safety | welchw@hydroone.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18205 | Longueuil TS-M23-ID927-Stardale Solar Park #3 | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | 2 |  |  | Yes |  |  |  |  | Distribution Generation Connection | ryan.boudreau@HydroOne.com | [6 empty] | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18206 | Havelock TS-M4-ID835-Healey Falls G1 Unit | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | 2 |  |  | Yes |  |  |  |  | Distribution Generation Connection | ryan.boudreau@HydroOne.com | [6 empty] | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18208 | Longueuil TS-M23-ID964-Stardale Solar Park #1 | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | 2 |  |  | Yes |  |  |  |  | Distribution Generation Connection | ryan.boudreau@HydroOne.com | [6 empty] | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18210 | Longueuil TS-M23-ID 965-Stardale Solar Park #2 | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | 2 |  |  | Yes |  |  |  |  | Distribution Generation Connection | ryan.boudreau@HydroOne.com | [6 empty] | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18226 | Environmental Mgt- Preventative Mtc Program | N.T.M.1.05 | 7370 | 206 | TX LINES AND STATIONS | AIP001012 | AIP001012 | AIP001012 | No | AIP001012 | Environmental Preventive Maintenance | 0 |  | Environmental Management | Mike.Tanaskovic@HydroOne.com | Sebastian.Niculae@HydroOne.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | EMPP ACTN | Executing | Short Term Planning | # of Orders | 941592.5945 | 955308.6498 | 976663.0372 | 999072.6418 | 1019797.8223 | 1040944.9563 | 0 | 0 | 0 | 0 | 941592.5945 | 955308.6498 | 976663.0372 | 999072.6418 | 1019797.8223 | 1040944.9563 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2985 | 2985 | 2985 | 2985 | 2985 | 2985 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | True | Requirements within individual site specific ECA's for monthly inspections. Only applicable if a station has an MOECC issued ECA. | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Intermediate
18236 | Richview BUCC Generator Upgrade | N.T.C.1.28 | 7236 | 215 | FACILITIES & REAL ESTATE | 5 |  |  | Yes |  |  |  |  | Transmission Site Facilities | cindy.copp@hydroone.com | [6 empty] | Project | EMPP AWRD | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18238 | Essa TS - Install 245 Mvar Cap Bank | N.T.C.2.03 | 7700 | 203 | PROJECT DELIVERY | 77 |  |  | Yes |  |  |  |  | Network Transfer Capability | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18239 | Kapuskasing TS - Install 21.6 MVAr Cap Bank | N.T.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000726 |  | AIP000726 | Yes | AIP000726 |  |  |  | Network Transfer Capability | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18254 | 2009 R&D Program - E&CS | N.T.M.2.21 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Technology Program | Daila.Dzintars@HydroOne.com | [6 empty] | Program | ACCP EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18260 | Hearn TS: Rebuild Hearn SS | N.T.C.2.02 | 7700 | 203 | PROJECT DELIVERY | AIP000700 | AIP000700 | AIP000700 | No | AIP000700 | Hearn TS: Rebuild Hearn SS | 0 |  | Local Area Supply | Robert.Reinmuller@HydroOne.com | farooq.qureshy@hydroone.com | System Service | Greater Toronto Area | Not Required | 0 | Complete | Project | EMPP ACCP | Executing | Executing |  | 1893288.4365 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1893288.4365 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41639 | [13 empty] | FALSE |  | 0 | 0 | Alternative 1
18271 | SQI Reporting (Yearly) | N.D.M.1.07 | 7374 | 205 | LINES | AIP000276 | AIP000276 | AIP000276 | No | AIP000276 | SQI Reporting |  |  | Other Services | emre.aydin@HydroOne.com | patrick.howe@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | AWRD EMPP | Executing | Short Term Planning | # of occurences | 1003978.598 | 1034446.451 | 1057065.6354 | 1080570.5016 | 1100702.7186 | 0 | 0 | 0 | 0 | 0 | 1003978.598 | 1034446.451 | 1057065.6354 | 1080570.5016 | 1100702.7186 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Demand
18273 | Malden TS-EG1096-Harrow I WF | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | 2 |  |  | Yes |  |  |  |  | Distribution Generation Connection | ryan.boudreau@HydroOne.com | [6 empty] | Project | EMPP AWRD | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18274 | Malden TS-EG1097-Harrow II WF | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | 2 |  |  | Yes |  |  |  |  | Distribution Generation Connection | ryan.boudreau@HydroOne.com | [6 empty] | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18275 | Malden TS-EG1098-Harrow III WF | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | 2 |  |  | Yes |  |  |  |  | Distribution Generation Connection | ryan.boudreau@HydroOne.com | [6 empty] | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18282 | Wolverton DS - 2010 Add Third Feeder | N.D.C.2.02 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | [6 empty] | Project | DETL ACTN | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18297 | 2011 Fort Frances M1 phases 7 to 10 of 10 | N.D.C.1.07 | 7374 | 205 | LINES | 6 |  |  | Yes |  |  |  |  | Lines | emre.aydin@HydroOne.com | [6 empty] | Program | AWRD EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18302 | St. Thomas TS - Transfer Trip | N.T.C.2.12 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Generator Customer Connection | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18315 | Brant TS M14-Conductor Upgrade | N.D.C.2.02 | 7374 | 205 | LINES | UNPLND |  |  | Yes |  |  |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | [6 empty] | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18319 | Owen Sound/Line Refurbishment | N.D.C.1.07 | 7374 | 205 | LINES | 6 |  |  | Yes |  |  |  |  | Lines | emre.aydin@HydroOne.com | [6 empty] | Program | AWRD EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18320 | Port Severn DS/Line Work | N.D.C.2.02 | 7374 | 205 | LINES | AIP000183A |  | AIP000183 | Yes | AIP000183 | (1) System upgrade driven by load growth |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Michael.Medeiros@HydroOne.com | System Service | 0 | 0 | 03 - None (default) | Not Required | Project | EMPP ACTN | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18321 | Dobbin TS M5 Blue Moon Solar Farm | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000199 |  | AIP000199 | Yes | AIP000199 | Large Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18330 | Transformer Midlife Refurbishment Program | N.T.M.1.16 | 7370 | 206 | TX LINES AND STATIONS | AIP001071C | AIP001071 | AIP001071 | No | AIP001071 | Transformer Refurbishments | 0 |  | Power Equipment | Mike.Tanaskovic@HydroOne.com | perry.ng@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | ACTN EMPP | Executing | Short Term Planning | # of Transformers | 3027940.576 | 4659718.2163 | 4014595.4596 | 4106449.7781 | 4191399.4871 | 4278078.88 | 0 | 0 | 0 | 0 | 3027940.576 | 4659718.2163 | 4014595.4596 | 4106449.7781 | 4191399.4871 | 4278078.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | False |  | False | True | False | False | FALSE |  | 0 | 0 | Asset Optimal Modified (Tx Decision)
18332 | North Bay TS M1 Convert to 44 kV | N.D.C.2.02 | 7374 | 205 | LINES | UNPLND |  |  | Yes |  |  |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | [6 empty] | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18335 | Transformer Oil Leak Reduction Program | N.T.M.1.05 | 7370 | 206 | TX LINES AND STATIONS | AIP001010 | AIP001010 | AIP001010 | No | AIP001010 | Environmental - Transformer Oil Leak Reduction | 0 |  | Environmental Management | Mike.Tanaskovic@HydroOne.com | perry.ng@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | ACTN EMPP | Executing | Short Term Planning | # of Transformers | 2281691.5163 | 3802063.8903 | 3878337.7949 | 3967026.7458 | 4057298.268 | 4137818.8362 | 0 | 0 | 0 | 0 | 2281691.5163 | 3802063.8903 | 3878337.7949 | 3967026.7458 | 4057298.268 | 4137818.8362 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 7 | 7 | 7 | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | True | False |  | False | False | False | False | FALSE |  | 0 | 0 | Intermediate (Modified-Tx Decision)
18344 | 2009 FMP - E&CS | N.T.M.1.17 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Protection Control & Metering Equipment | Miroslav.Kostic@HydroOne.com | [6 empty] | Program | AWRD EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18348 | GCD1946 - Beardmore HVDS | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Distribution Generation Connection | ryan.boudreau@HydroOne.com | [6 empty] | Project | EMPP AWRD | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18357 | 2012 New Keewatin DS | N.D.C.2.02 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18358 | 2009 GCD-Line Transfers | N.D.C.2.03 | 7374 | 205 | LINES | UNPLND |  |  | Yes |  |  |  |  | Distribution Generation Connection | ryan.boudreau@HydroOne.com | [6 empty] | Program | ACCP EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18359 | 2012 Keewatin DS Feeders | N.D.C.2.02 | 7374 | 205 | LINES | UNPLND |  |  | Yes |  |  |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | [6 empty] | Project | EMPP ACTN | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18360 | WSD PMO Documentation & Support | N.T.M.1.16 | 7370 | 206 | TX LINES AND STATIONS | AIP001062 | AIP001062 | AIP001062 | No | AIP001062 | Other Mtce - Power Equipment - Work Standard Document Revisi | 0 |  | Power Equipment | Mike.Tanaskovic@HydroOne.com | Harshal.Bhatt@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | ACTN EMPP | Executing | Short Term Planning | # of Documents as required | 109443.9929 | 114943.2827 | 118713.6133 | 121436.0118 | 123953.729 | 126522.7261 | 0 | 0 | 0 | 0 | 109443.9929 | 114943.2827 | 118713.6133 | 121436.0118 | 123953.729 | 126522.7261 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Vulnerable
18361 | Multi-year Stations-Switch Replacement Program | N.T.C.1.18 | 7700 | 203 | PROJECT DELIVERY | AIP000583 | AIP000583 | AIP000583 | No | AIP000583 | Multi-year Stations-Switch Replacement Program | 0 |  | Other Power Equipment | James.Mardegan@HydroOne.com | mark.truchanowicz@hydroone.com | System Renewal | 0 | 0 | 03 - None (default) | 0 | Program | ACTN EMPP | Executing | Short Term Planning | # of switches | 225722.9386 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 225722.9386 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Carryover Work
18371 | H2JK & K6J - Replace HV UG Cables | N.T.C.1.15 | 7700 | 203 | PROJECT DELIVERY | AIP000544 |  | AIP000544 | Yes | AIP000544 |  |  |  | U/G Lines Cable Sys & Comp Refurb & Repl | hassan.hamzeh@hydroone.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18372 | 2010 Mazinaw DS/SSI | N.D.C.2.02 | 7374 | 205 | LINES | UNPLND |  |  | Yes |  |  |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | [6 empty] | Project | EMPP ACTN | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18374 | 2010 Best DS/Supply Reconfiguration | N.D.C.2.02 | 7374 | 205 | LINES | UNPLND |  |  | Yes |  |  |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | [6 empty] | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18377 | Whitney DS x Dwight DS Tie Line | N.D.C.2.02 | 7374 | 205 | LINES | AIP000183A |  | AIP000183 | Yes | AIP000183 | (1) System upgrade driven by load growth |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Michael.Medeiros@HydroOne.com | System Service | 0 | 0 | 03 - None (default) | Not Required | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18378 | 2010 Craft Creek Rd/Convert to 16 kV | N.D.C.2.02 | 7374 | 205 | LINES | UNPLND |  |  | Yes |  |  |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | [6 empty] | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18388 | GCD1201-Smith Falls | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | 2 |  |  | Yes |  |  |  |  | Distribution Generation Connection | ryan.boudreau@HydroOne.com | [6 empty] | Project | EMPP AWRD | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18390 | Kirkland Lake TS - Install SVC | N.T.C.2.03 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Network Transfer Capability | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18393 | Twelve Mile Bay DS - New Station | N.D.C.2.02 | 7700 | 203 | PROJECT DELIVERY | AIP005401 | AIP005401 | AIP005401 | No | AIP005401 | Twelve Mile Bay DS - New Station & Feeder Development | ISD-SS-02 | System Upgrades Driven by Load Growth | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Gaurav.Behal@HydroOne.com | System Service | 0 | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 2482006.0248 | 1546366.5827 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2596240.6117 | 1617538.2665 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -114234.5869 | -71171.6837 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4.9587 | 4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43281 | 43753 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
18397 | 2011 Kent Area/Enabler TS Feeders | N.D.C.2.03 | 7374 | 205 | LINES | 3 |  |  | Yes |  |  |  |  | Distribution Generation Connection | ryan.boudreau@HydroOne.com | [6 empty] | Project | DETL ACCP | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18399 | ADS Phase 0 | N.D.C.2.06 | 4343 | 222 | SMART GRID | AIP000207 |  | AIP000207 | Yes | AIP000207 | Distribution Modernization Project | ISD-SS-07 | Advanced Distribution System (“ADS”) | Smart Grid | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Service | 0 | Not Required | 02 - Expectation (no agreement) | Not Required | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18400 | Haileybury DS F1 F2 F3 /Convert (New Liskeard) | N.D.C.2.02 | 7374 | 205 | LINES | UNPLND |  |  | Yes |  |  |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | [6 empty] | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18401 | Smart Zone | N.D.M.2.06 | 4337 | 223 | SMART METERS | UNPLND |  |  | Yes |  |  |  |  | Smart Grid | Godfrey.Holder@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18402 | System Reserve Equip-Operating Spare Mtce&Inspect | N.T.M.1.16 | 7370 | 206 | TX LINES AND STATIONS | AIP001064 | AIP001064 | AIP001064 | No | AIP001064 | System Reserve Equipment - Operating Spare Inspection | 0 |  | Power Equipment | Mike.Tanaskovic@HydroOne.com | peter.zhao@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | ACTN EMPP | Executing | Short Term Planning | # of Orders | 183077.1835 | 185744.053 | 189896.0028 | 194253.2375 | 198282.9354 | 202394.6272 | 0 | 0 | 0 | 0 | 183077.1835 | 185744.053 | 189896.0028 | 194253.2375 | 198282.9354 | 202394.6272 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 210 | 210 | 210 | 210 | 210 | 210 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Asset Optimal
18407 | 2010 Pefferlaw DS F3/Add Feeder | N.D.C.2.02 | 7374 | 205 | LINES | UNPLND |  |  | Yes |  |  |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | [6 empty] | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18409 | Marchwood MS - 2nd Tap Connection | N.T.C.2.11 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Load Customer Connection | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18411 | A6P - Line Refurbishment Program (2010-2012) | N.T.C.1.14 | 7700 | 203 | PROJECT DELIVERY | 4 |  |  | Yes |  |  |  |  | Third Party Transmission System Modifications | john.boldt@HydroOne.com | [6 empty] | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18429 | Timmins 27.6 kV Vaults/Refurb | N.D.C.1.07 | 7374 | 205 | LINES | AIP000152 |  | AIP000152 | Yes | AIP000152 | Large Sustainment Initiatives | ISD-SR-12 | Distribution Lines Sustainment Initiatives | Lines | emre.aydin@HydroOne.com | Alexander.Hamlyn@HydroOne.com | System Renewal | N/A | 0 | 03 - None (default) | 0 | Program | ACCP EMPP | Executing | Short Term Planning | # of projects | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18435 | HV UG Cable - Demand CM (Corrective Maintenance) | N.T.M.1.21 | 7370 | 206 | TX LINES AND STATIONS | AIP001118B | AIP001118 | AIP001118 | No | AIP001118 | HV UG Cable - CM (Corrective Maintenance) | 0 |  | Underground Cables | hassan.hamzeh@hydroone.com | Tyler.Wales@HydroOne.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | EMPP AWRD | Executing | Short Term Planning | Number of Repairs | 991349.1035 | 1007395.7602 | 1029614.5502 | 1052931.431 | 1074495.6486 | 1096498.89 | 0 | 0 | 0 | 0 | 991349.1035 | 1007395.7602 | 1029614.5502 | 1052931.431 | 1074495.6486 | 1096498.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | True | False |  | False | True | False | False | FALSE |  | 0 | 0 | Asset Optimal
18438 | Tx Lines Insulator Replacement Program - PL&F | N.T.C.1.12 | 7370 | 206 | TX LINES AND STATIONS | AIP000459A | AIP000459 | AIP000459 | No | AIP000459 | Tx Lines Insulator Replacement Program | SR-25 | Transmission Line Insulator Replacement | Overhead Lines Component Refurb & Repl | hassan.hamzeh@hydroone.com | Tyler.Wales@HydroOne.com | System Renewal | 0 | 0 | 03 - None (default) | 0 | Program | EMPP ACTN | Executing | Short Term Planning | Number of Circuit Structures | 31593627.7666 | 29593013.0414 | 29811810.2788 | 29966993.969 | 14621747.2564 | 14744339.3777 | 0 | 0 | 0 | 0 | 35901849.7348 | 33628423.9107 | 33877057.135 | 34053402.2375 | 16615621.8823 | 16754931.111 | 0 | 0 | 0 | 0 | -4308221.9682 | -4035410.8693 | -4065246.8562 | -4086408.2685 | -1993874.6259 | -2010591.7333 | 0 | 0 | 0 | 0 | -12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1850 | 1850 | 1850 | 1850 | 925 | 925 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Asset Optimal (Modified - Tx Decision)
18441 | Nuisance Wildlife Control - Civil & Assessment | N.T.M.1.19 | 7370 | 206 | TX LINES AND STATIONS | AIP001102 | AIP001102 | AIP001102 | No | AIP001102 | Nuisance Wildlife Control (Civil) | 0 |  | Infrastructure Maintenance | Mike.Tanaskovic@HydroOne.com | Sebastian.Niculae@HydroOne.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | EMPP ACTN | Executing | Short Term Planning | # of Stations | 1500293.7416 | 1524578.5778 | 1558204.1634 | 1593491.6421 | 1626126.5554 | 1659146.7217 | 0 | 0 | 0 | 0 | 1500293.7416 | 1524578.5778 | 1558204.1634 | 1593491.6421 | 1626126.5554 | 1659146.7217 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | True | Numerous customers request animal mitigation performance numbers and udates on investments (i.e. Domtar, Alectra, Toronto Hydro) | False | False | False | False | FALSE |  | 0 | 0 | Asset Optimal
18442 | Nuisance Wildlife Control - Capital Solutions | N.T.C.1.21 | 7370 | 206 | TX LINES AND STATIONS | AIP000634 |  | AIP000634 | Yes | AIP000634 |  |  |  | Infrastructure | James.Mardegan@HydroOne.com | [6 empty] | Program | ACTN EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18443 | Nuisance Wildlife Control - Bus & Overhead | N.T.M.1.16 | 7370 | 206 | TX LINES AND STATIONS | AIP001050 | AIP001050 | AIP001050 | No | AIP001050 | Nuisance Wildlife Control (Bus & O/H) | 0 |  | Power Equipment | Mike.Tanaskovic@HydroOne.com | Sebastian.Niculae@HydroOne.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | ACTN EMPP | Executing | Short Term Planning | # of Stations | 675439.1892 | 686372.3324 | 701510.7074 | 717397.2785 | 732089.7307 | 747612.842 | 0 | 0 | 0 | 0 | 675439.1892 | 686372.3324 | 701510.7074 | 717397.2785 | 732089.7307 | 747612.842 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | True | Numerous customers request animal mitigation performance numbers and udates on investments (i.e. Domtar, Alectra, Toronto Hydro) | False | False | False | False | FALSE |  | 0 | 0 | Intermediate
18446 | 2011+ Small Sustainment Initiatives | N.D.C.1.07 | 7374 | 205 | LINES | AIP000153 | AIP000153 | AIP000153 | No | AIP000153 | Small Sustainment Initiatives | ISD-SR-12 | Distribution Lines Sustainment Initiatives | Lines | emre.aydin@HydroOne.com | joseph.parete@hydroone.com | System Renewal | N/A | 0 | 03 - None (default) | 0 | Program | ACCP EMPP | Executing | Short Term Planning | # of projects | 5793819.0422 | 5794256.9244 | 5798513.82 | 5801760.1605 | 5801569.1214 | 0 | 0 | 0 | 0 | 0 | 6583885.2753 | 6584382.8686 | 6589220.25 | 6592909.2733 | 6592692.1834 | 0 | 0 | 0 | 0 | 0 | -790066.233 | -790125.9442 | -790706.43 | -791149.1128 | -791123.062 | 0 | 0 | 0 | 0 | 0 | -12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Plan B
18447 | 2011+ Demand Investments | N.D.C.2.02 | 7374 | 205 | LINES | AIP000188 | AIP000188 | AIP000188 | No | AIP000188 | Demand Investments - Dx | ISD-SS-04 | Demand Investments | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Wojciech.Maroszek@HydroOne.com | System Service | 0 | 0 | 03 - None (default) | 0 | Program | ACCP EMPP | Executing | Short Term Planning | Demand | 3601421.2066 | 3746836.071 | 3853056.3781 | 3932317.8685 | 4010832.12 | 0 | 0 | 0 | 0 | 0 | 4092524.0984 | 4257768.2625 | 4378473.1569 | 4468543.0324 | 4557763.7728 | 0 | 0 | 0 | 0 | 0 | -491102.8918 | -510932.1915 | -525416.7788 | -536225.1639 | -546931.6527 | 0 | 0 | 0 | 0 | 0 | -12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43830 | [13 empty] | FALSE |  | 0 | 0 | Critical Spend Plan
18448 | 2011+ Distribution System Modifications | N.D.C.2.02 | 7374 | 205 | LINES | AIP000189 | AIP000189 | AIP000189 | No | AIP000189 | Dx System Modifications | ISD-SS-05 | Distribution System Modifications | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Wojciech.Maroszek@HydroOne.com | System Service | 0 | 0 | 03 - None (default) | 0 | Program | EMPP ACCP | Executing | Short Term Planning | Demand | 7330150.9475 | 7222399.5481 | 8027127.0685 | 8031621.2348 | 8031356.651 | 0 | 0 | 0 | 0 | 0 | 8329716.9858 | 8207272.2138 | 9121735.3051 | 9126842.3122 | 9126541.6489 | 0 | 0 | 0 | 0 | 0 | -999566.0383 | -984872.6657 | -1094608.2366 | -1095221.0775 | -1095184.9979 | 0 | 0 | 0 | 0 | 0 | -12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43830 | [13 empty] | FALSE |  | 0 | 0 | Hybrid Scenario
18450 | Ellwood MTS 230 kV Connection | N.T.C.2.11 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Load Customer Connection | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18454 | Station Battery Replacement Program | N.T.C.1.20 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Ancillary Systems | James.Mardegan@HydroOne.com | [6 empty] | Program | ACTN EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18455 | Bloomsburg MTS Modification | N.T.C.2.11 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Load Customer Connection | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18470 | 2010 DX Engineering Stds Development | N.D.M.2.20 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Standards Program | Kevin.Mancherjee@HydroOne.com | [6 empty] | Program | EMPP ACCP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18471 | 2010 SACE Breaker Replacement Program | N.T.C.1.01 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Circuit Breakers | James.Mardegan@HydroOne.com | [6 empty] | Program | ACTN EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18473 | Multi-SACE Breaker Replacement | N.T.C.1.01 | 7700 | 203 | PROJECT DELIVERY | AIP000378 | AIP000378 | AIP000378 | No | AIP000378 | Metalclad Breaker Replacement Program - Carryover | 0 |  | Circuit Breakers | James.Mardegan@HydroOne.com | Donald.Mastrangelo@HydroOne.com | System Renewal | 0 | 0 | 03 - None (default) | 0 | Program | ACCP EMPP | Executing | Short Term Planning | # of Breakers | 2984852.7476 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3045768.1098 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -60915.3622 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Carryover Work
18482 | Int. Plowing Match/Community Events | N.D.M.1.07 | 7374 | 205 | LINES | AIP000271 | AIP000271 | AIP000271 | No | AIP000271 | Int Plowing Match & Community Events |  |  | Other Services | emre.aydin@HydroOne.com | patrick.howe@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | EMPP AWRD | Executing | Short Term Planning | # of Events | 216465.7092 | 223564.3087 | 228885.0018 | 234309.2065 | 238910.6035 | 0 | 0 | 0 | 0 | 0 | 216465.7092 | 223564.3087 | 228885.0018 | 234309.2065 | 238910.6035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Vulnerable
18484 | Kam Reg DS F1/Convert to 16 kV-Stage 1 | N.D.C.2.02 | 7374 | 205 | LINES | UNPLND |  |  | Yes |  |  |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | [6 empty] | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18488 | TECHS-LINES-Standards-Dx | N.D.M.2.20 | 7374 | 205 | LINES | AIP000309 |  | AIP000309 | Yes | AIP000309 | Dx - TECHS-LINES-Standards |  |  | Standards Program | Kevin.Mancherjee@HydroOne.com | rossella.fazio@hydroone.com | System O&M | N/A | 0 | 03 - None (default) | 0 | Program | AWRD EMPP | Executing | Short Term Planning | Assumption - # of Standards | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18497 | Steel Structure Coating Program – PL | N.T.C.1.12 | 7370 | 206 | TX LINES AND STATIONS | AIP000468 | AIP000468 | AIP000468 | No | AIP000468 | Steel Structure Coating Program | SR-22 | Steel Structure Coating Program | Overhead Lines Component Refurb & Repl | hassan.hamzeh@hydroone.com | TeodorConstantin.Culinescu@HydroOne.com | System Renewal | 0 | 0 | 03 - None (default) | 0 | Program | EMPP ACTN | Executing | Short Term Planning | # of Structures | 30785824.5774 | 27253024.8484 | 27567984.3731 | 27780545.819 | 27989523.8258 | 28300789.5604 | 0 | 0 | 0 | 0 | 30785824.5774 | 27253024.8484 | 27567984.3731 | 27780545.819 | 27989523.8258 | 28300789.5604 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1050 | 820 | 820 | 820 | 820 | 820 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Tx Decision
18505 | Hanmer TS - Install Additional 149 MVAr Shunt Cap | N.T.C.2.03 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Network Transfer Capability | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18506 | Interconnection: Upgrade Pool Niagara A | N.T.C.2.03 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Network Transfer Capability | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18507 | Telecommunication Performance Improvement | N.T.C.3.08 | 7700 | 203 | PROJECT DELIVERY | AIP001000 |  | AIP001000 | Yes | AIP001000 |  |  |  | Integrating Operating Infrastructure | Miroslav.Kostic@HydroOne.com | [6 empty] | Program | ACTN EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18533 | Enfield TS (Formerly Oshawa Area TS)- Build 230/44 | N.T.C.2.11 | 7700 | 203 | PROJECT DELIVERY | AIP000780 | AIP000780 | AIP000780 | No | AIP000780 | Enfield TS - Build New DESN Station | 0 |  | Load Customer Connection | Robert.Reinmuller@HydroOne.com | Quyen.Diep@HydroOne.com | System Access | Central | Not Required | 01 - Agreement (current/future) | Complete | Project | EMPP ACCP | Executing | Executing |  | 24402802.4927 | 1046942.2924 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24402802.4927 | 1296942.2924 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43555 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Alternative 1
18538 | 2005-06 Nanticoke TS TSI & ABCB Repl. Prog. | N.T.C.1.08 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | System Re-investment | James.Mardegan@HydroOne.com | [6 empty] | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18553 | Birch Island DS F2 - Replace 1.7 km Aerial Water | N.D.C.1.07 | 7374 | 205 | LINES | AIP000152 |  | AIP000152 | Yes | AIP000152 | Large Sustainment Initiatives | ISD-SR-12 | Distribution Lines Sustainment Initiatives | Lines | emre.aydin@HydroOne.com | Alexander.Hamlyn@HydroOne.com | System Renewal | N/A | 0 | 03 - None (default) | 0 | Program | ACCP EMPP | Executing | Short Term Planning | # of projects | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18588 | Pilot Project - GE F60 Hi-Z Module | N.T.C.1.19 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Protection Control & Metering Equip | Miroslav.Kostic@HydroOne.com | [6 empty] | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18589 | Pinard TS: Reconfig 115 kV, Build Swyrd, Demerge | N.T.C.1.08 | 7700 | 203 | PROJECT DELIVERY | AIP000436 |  | AIP000436 | Yes | AIP000436 |  |  |  | System Re-investment | James.Mardegan@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18623 | Nobel SS: Install series capacitor banks | N.T.C.2.03 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Network Transfer Capability | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18627 | HSE Compliance Audits | N.C.M.3.03 | 4337 | 223 | SMART METERS | UNPLND |  |  | Yes |  |  |  |  | Environment Health and Safety | welchw@hydroone.com | [6 empty] | Program | EMPP AWRD | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18628 | Public Safety Educational Materials | N.C.M.3.03 | 4337 | 223 | SMART METERS | UNPLND |  |  | Yes |  |  |  |  | Environment Health and Safety | welchw@hydroone.com | [6 empty] | Program | AWRD EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18629 | Health & Rehab Services | N.C.M.3.03 | 4337 | 223 | SMART METERS | UNPLND |  |  | Yes |  |  |  |  | Environment Health and Safety | welchw@hydroone.com | [6 empty] | Program | AWRD EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18630 | Specialist HSE Resources | N.C.M.3.03 | 4337 | 223 | SMART METERS | UNPLND |  |  | Yes |  |  |  |  | Environment Health and Safety | welchw@hydroone.com | [6 empty] | Program | EMPP AWRD | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18631 | Health & Safety Conference | N.C.M.3.03 | 4337 | 223 | SMART METERS | UNPLND |  |  | Yes |  |  |  |  | Environment Health and Safety | welchw@hydroone.com | [6 empty] | Program | AWRD EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18633 | HSE Compliance Audits | N.C.M.3.03 | 4337 | 223 | SMART METERS | UNPLND |  |  | Yes |  |  |  |  | Environment Health and Safety | welchw@hydroone.com | [6 empty] | Program | EMPP AWRD | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18634 | Public Electrical Safety Presentations in Schools | N.C.M.3.03 | 4337 | 223 | SMART METERS | UNPLND |  |  | Yes |  |  |  |  | Environment Health and Safety | welchw@hydroone.com | [6 empty] | Program | AWRD EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18635 | Health & Rehab Services | N.C.M.3.03 | 4337 | 223 | SMART METERS | UNPLND |  |  | Yes |  |  |  |  | Environment Health and Safety | welchw@hydroone.com | [6 empty] | Program | AWRD EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18636 | Specialist HSE Resources | N.C.M.3.03 | 4337 | 223 | SMART METERS | UNPLND |  |  | Yes |  |  |  |  | Environment Health and Safety | welchw@hydroone.com | [6 empty] | Program | EMPP AWRD | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18637 | Health & Safety Conference | N.C.M.3.03 | 4337 | 223 | SMART METERS | UNPLND |  |  | Yes |  |  |  |  | Environment Health and Safety | welchw@hydroone.com | [6 empty] | Program | AWRD EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18639 | EMF Measurements | N.C.M.3.03 | 7374 | 205 | LINES | UNPLND |  |  | Yes |  |  |  |  | Environment Health and Safety | welchw@hydroone.com | [6 empty] | Program | AWRD EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18669 | 2008 - Rainy River DS - F1 & F2 - 4.16kV Feeders P | N.D.C.1.07 | 7374 | 205 | LINES | UNPLND |  |  | Yes |  |  |  |  | Lines | emre.aydin@HydroOne.com | [6 empty] | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18675 | HODS - A CORPORATE DOCUMENT SYSTEM | N.C.M.3.03 | 4337 | 223 | SMART METERS | UNPLND |  |  | Yes |  |  |  |  | Environment Health and Safety | welchw@hydroone.com | [6 empty] | Program | EMPP AWRD | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18676 | HODS - A CORPORATE DOCUMENT SYSTEM | N.C.M.3.03 | 4337 | 223 | SMART METERS | UNPLND |  |  | Yes |  |  |  |  | Environment Health and Safety | welchw@hydroone.com | [6 empty] | Program | AWRD EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18679 | DC signalling replacement in Hamilton area | N.T.C.1.25 | 7700 | 203 | PROJECT DELIVERY | 6 |  |  | Yes |  |  |  |  | Auxiliary Telecommunication Equipment | Miroslav.Kostic@HydroOne.com | [6 empty] | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18681 | closed-2005 HV UG Cable Maintenance Prog-Kinectric | N.T.M.1.21 | 4337 | 223 | SMART METERS | UNPLND |  |  | Yes |  |  |  |  | Underground Cables | hassan.hamzeh@hydroone.com | [6 empty] | Program | AWRD EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18682 | 2006-07 Station Service Upgrades - DESN | N.T.C.1.20 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Ancillary Systems | James.Mardegan@HydroOne.com | [6 empty] | Program | EMPP ACCP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18684 | 2007 Station Service Upgrades - BULK | N.T.C.1.20 | 7700 | 203 | PROJECT DELIVERY | 3 |  |  | Yes |  |  |  |  | Ancillary Systems | James.Mardegan@HydroOne.com | [6 empty] | Program | ACCP EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18685 | Brockville Area Reliability Improvements | N.D.C.2.02 | 7374 | 205 | LINES | UNPLND |  |  | Yes |  |  |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | [6 empty] | Project | EMPP ACTN | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18713 | Rosseau DS - New 7.5 MVA 44-12.48 kV Distribution | N.D.C.2.02 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18714 | Stayner TS x Wasaga Beach - Extend 44 kV Feeder | N.D.C.2.02 | 7374 | 205 | LINES | UNPLND |  |  | Yes |  |  |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | [6 empty] | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18725 | 2006 Purchase Operating Spare Station Service Tran | N.T.C.1.17 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Power Transformers | James.Mardegan@HydroOne.com | [6 empty] | Program | EMPP AWRD | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18740 | 2006 Civil/Geotech - Footings & Foundation Works | N.T.C.1.21 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Infrastructure | James.Mardegan@HydroOne.com | [6 empty] | Program | ACCP EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18764 | E-Learning | N.C.M.3.03 | 7803 | 209 | HEALTH, SAFETY & ENV | UNPLND |  |  | Yes |  |  |  |  | Environment Health and Safety | welchw@hydroone.com | [6 empty] | Program | AWRD EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18773 | Holland TS - 44kV feeder development | N.D.C.2.02 | 7374 | 205 | LINES | UNPLND |  |  | Yes |  |  |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | [6 empty] | Project | EMPP ACTN | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18784 | Kleinburg TS Feeders to Bolton Area | N.D.C.2.02 | 7374 | 205 | LINES | UNPLND |  |  | Yes |  |  |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | [6 empty] | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18795 | Timmins M9 Feeder Extension | N.D.C.2.02 | 7374 | 205 | LINES | UNPLND |  |  | Yes |  |  |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | [6 empty] | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18805 | Commerce Way TS:Build new TS | N.T.C.2.11 | 7700 | 203 | PROJECT DELIVERY | 162 |  |  | Yes |  |  |  |  | Load Customer Connection | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18808 | Build New Duart TS | N.T.C.2.11 | 7700 | 203 | PROJECT DELIVERY | 145 |  |  | Yes |  |  |  |  | Load Customer Connection | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18811 | DESN Station Service Upgrades Program | N.T.C.1.20 | 7700 | 203 | PROJECT DELIVERY | AIP000623 |  | AIP000623 | Yes | AIP000623 |  |  |  | Ancillary Systems | James.Mardegan@HydroOne.com | [6 empty] | Program | ACCP EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18812 | 2006 Tx Site Facility Capital | N.T.C.1.21 | 7236 | 215 | FACILITIES & REAL ESTATE | UNPLND |  |  | Yes |  |  |  |  | Infrastructure | James.Mardegan@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18830 | Tx Operating Facilities Sustainment / NMS Upgrade | N.T.C.3.06 | 4339 | 212 | INFO SOLUTIONS DIVISION | 8 |  |  | Yes |  |  |  |  | Grid Operating and Control Facilities | Godfrey.Holder@HydroOne.com | [6 empty] | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18835 | CNR/Nova Steel Modifications to Q2AH/Q5G | N.T.C.1.12 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Overhead Lines Component Refurb & Repl | hassan.hamzeh@hydroone.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18839 | New 500 kV Bruce to Milton Double Circuit Line | N.T.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000731 |  | AIP000731 | Yes | AIP000731 |  |  |  | Network Transfer Capability | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18843 | St. Lawrence TS: Revise Beauharnois - Saunders GR | N.T.C.2.03 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Network Transfer Capability | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18850 | 2010 Station Service Upgrades - BULK (Formerly 200 | N.T.C.1.20 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Ancillary Systems | James.Mardegan@HydroOne.com | [6 empty] | Program | DETL ACTN | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18860 | Ringwood DS T3 27.6kV Addition | N.D.C.2.02 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18864 | North Bay TS: Upgrade to a 115-44 kV TS | N.T.C.2.11 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Load Customer Connection | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18873 | Pleasant TS new M21 feeder | N.D.C.2.02 | 7374 | 205 | LINES | UNPLND |  |  | Yes |  |  |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | [6 empty] | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18883 | Oil Farm Operation Program | N.T.M.1.18 | 7370 | 206 | TX LINES AND STATIONS | AIP001093 | AIP001093 | AIP001093 | No | AIP001093 | Other Mtce - Ancillary - Oil Farm Operation Program | 0 |  | Ancillary Systems Maintenance | Mike.Tanaskovic@HydroOne.com | peter.zhao@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | ACTN EMPP | Executing | Short Term Planning | Retainer | 423091.6085 | 429254.6733 | 438849.9226 | 448558.6707 | 457863.8394 | 467358.4141 | 0 | 0 | 0 | 0 | 423091.6085 | 429254.6733 | 438849.9226 | 448558.6707 | 457863.8394 | 467358.4141 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Asset Optimal
18884 | P3S/P4S - Line Refurbishment Program (2009-2010) | N.T.C.1.14 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Third Party Transmission System Modifications | john.boldt@HydroOne.com | [6 empty] | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18890 | Station Surge Arrester Replacement Program | N.T.C.1.18 | 7700 | 203 | PROJECT DELIVERY | AIP000582 |  | AIP000582 | Yes | AIP000582 |  |  |  | Other Power Equipment | James.Mardegan@HydroOne.com | [6 empty] | Program | EMPP ACTN | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18893 | TELCO CHARGES - VOICE | N.C.M.1.25 | 4199 | 212 | INFO SOLUTIONS DIVISION | AIP000084 | AIP000084 | AIP000084 | No | AIP000084 | Telecom Voice | 0 |  | Business Telecom | lincoln.frost-hunt@hydroone.com | robert.hosford@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | EMPP init | Executing | Short Term Planning | Retainer | 2249999.88 | 2199999.88 | 2200000.12 | 2200000 | 2199999.88 | 2200000.12 | 0 | 0 | 0 | 0 | 2249999.88 | 2199999.88 | 2200000.12 | 2200000 | 2199999.88 | 2200000.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | True | Agreement/Contract with Telecommunication provider such as Bell. | False | False |  | False | False | True | False | FALSE |  | 0 | 0 | Intermediate
18894 | OPS AND CARRIER MGMT | N.C.M.1.25 | 4339 | 212 | INFO SOLUTIONS DIVISION | AIP000081A | AIP000081 | AIP000081 | No | AIP000081 | Telecom OPS & Carrier Mgmt | 0 |  | Business Telecom | lincoln.frost-hunt@hydroone.com | robert.hosford@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | init EMPP | Executing | Short Term Planning | Retainer | 8000000 | 7899505.32 | 7899505.24 | 8059819.24 | 7999701.68 | 7999702 | 0 | 0 | 0 | 0 | 8000000 | 7899505.32 | 7899505.24 | 8059819.24 | 7999701.68 | 7999702 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | True | Agreement/Contract with H1 Telecom. | False | False |  | False | False | True | False | FALSE |  | 0 | 0 | Intermediate
18899 | TELCO CHARGES - DATA | N.C.M.1.25 | 4339 | 212 | INFO SOLUTIONS DIVISION | AIP000082 | AIP000082 | AIP000082 | No | AIP000082 | Telecom Data | 0 |  | Business Telecom | lincoln.frost-hunt@hydroone.com | robert.hosford@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | init EMPP | Executing | Short Term Planning | Retainer | 5300000 | 5099607.52 | 5099607.36 | 5099607.32 | 5099607.36 | 5100000.12 | 0 | 0 | 0 | 0 | 5300000 | 5099607.52 | 5099607.36 | 5099607.32 | 5099607.36 | 5100000.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | True | Agreement/Contract with Telecommunication Service provider such as Bell. | False | False |  | False | False | True | False | FALSE |  | 0 | 0 | Vulnerable - Tx Contraint Reduction
19095 | Transmission Site Maintenance | N.T.M.1.28 | 1142 | 215 | FACILITIES & REAL ESTATE | AIP001138 | AIP001138 | AIP001138 | No | AIP001138 | Transmission Site Maintenance | 0 |  | Transmission Site Facilities | cindy.copp@hydroone.com | Peter.Erdman@HydroOne.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | AWRD EMPP | Executing | Short Term Planning | Placeholder | 14915814.4908 | 15247867.7818 | 15574587.0419 | 15907812.3305 | 16311176.4764 | 16613586.5816 | 0 | 0 | 0 | 0 | 14915814.4908 | 15247867.7818 | 15574587.0419 | 15907812.3305 | 16311176.4764 | 16613586.5816 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | True | OBC or OFC regulated requirements | True | BGIS contractual commitments | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Vulnerable (Modified - Tx Decision)
19096 | Water Supply Upgrade | N.T.C.1.28 | 7236 | 215 | FACILITIES & REAL ESTATE | AIP000670 |  | AIP000670 | Yes | AIP000670 |  |  |  | Transmission Site Facilities | cindy.copp@hydroone.com | [6 empty] | Program | AWRD EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19098 | Critical Station Infrastructure Security | N.T.C.1.28 | 1142 | 215 | FACILITIES & REAL ESTATE | UNPLND |  |  | Yes |  |  |  |  | Transmission Site Facilities | cindy.copp@hydroone.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19100 | HQ & Admin & SC & OGCC Facilities - Operations & M | N.C.M.1.50 | 7236 | 215 | FACILITIES & REAL ESTATE | AIP000086 | AIP000086 | AIP000086 | No | AIP000086 | HQ & Admin & SC & OGCC Facilities - Operations & M | 0 |  | Real Estate Facility | cindy.copp@hydroone.com | Peter.Erdman@HydroOne.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | AWRD EMPP | Executing | Short Term Planning | Retainer | 50900000 | 54200000 | 54200000.12 | 55200000.12 | 55600000 | 56000000 | 0 | 0 | 0 | 0 | 50900000 | 54200000 | 54200000.12 | 55200000.12 | 55600000 | 56000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | True | Leases, utility payments, BGIS/Facility Mtce costs | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Vulnerable (Modified - Tx Decision)
19102 | Facilities Accommodation Project (Picton SC) | N.C.C.1.50 | 7236 | 215 | FACILITIES & REAL ESTATE | AIP000027 |  | AIP000027 | Yes | AIP000027 | Facility Accommodation & Improvements Service Centres & Admin |  |  | Real Estate Facilities | cindy.copp@hydroone.com | Peter.Erdman@HydroOne.com | General Plant | 0 | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19107 | Orillia TS Fence 2009 | N.T.C.1.28 | 1142 | 215 | FACILITIES & REAL ESTATE | UNPLND |  |  | Yes |  |  |  |  | Transmission Site Facilities | cindy.copp@hydroone.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19108 | Essa TS Fence 2009 | N.T.C.1.28 | 1142 | 215 | FACILITIES & REAL ESTATE | UNPLND |  |  | Yes |  |  |  |  | Transmission Site Facilities | cindy.copp@hydroone.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19110 | Muskoka TS Fence 2009 | N.T.C.1.28 | 1142 | 215 | FACILITIES & REAL ESTATE | UNPLND |  |  | Yes |  |  |  |  | Transmission Site Facilities | cindy.copp@hydroone.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19114 | Lake TS Fence 2009 | N.T.C.1.28 | 1142 | 215 | FACILITIES & REAL ESTATE | UNPLND |  |  | Yes |  |  |  |  | Transmission Site Facilities | cindy.copp@hydroone.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19115 | Lorne Park TS Fence 2009 | N.T.C.1.28 | 1142 | 215 | FACILITIES & REAL ESTATE | UNPLND |  |  | Yes |  |  |  |  | Transmission Site Facilities | cindy.copp@hydroone.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19117 | Middleport TS Fence 2009 | N.T.C.1.28 | 1142 | 215 | FACILITIES & REAL ESTATE | UNPLND |  |  | Yes |  |  |  |  | Transmission Site Facilities | cindy.copp@hydroone.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19118 | Palermo TS Fence 2009 | N.T.C.1.28 | 1142 | 215 | FACILITIES & REAL ESTATE | UNPLND |  |  | Yes |  |  |  |  | Transmission Site Facilities | cindy.copp@hydroone.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19119 | Bronte TS Fence 2009 | N.T.C.1.28 | 1142 | 215 | FACILITIES & REAL ESTATE | UNPLND |  |  | Yes |  |  |  |  | Transmission Site Facilities | cindy.copp@hydroone.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19120 | Claireville TS Fence 2009 | N.T.C.1.28 | 1142 | 215 | FACILITIES & REAL ESTATE | UNPLND |  |  | Yes |  |  |  |  | Transmission Site Facilities | cindy.copp@hydroone.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19121 | St Lawrence TS Fence 2009 | N.T.C.1.28 | 1142 | 215 | FACILITIES & REAL ESTATE | UNPLND |  |  | Yes |  |  |  |  | Transmission Site Facilities | cindy.copp@hydroone.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19125 | Cedar TS Fence 2009 | N.T.C.1.28 | 1142 | 215 | FACILITIES & REAL ESTATE | UNPLND |  |  | Yes |  |  |  |  | Transmission Site Facilities | cindy.copp@hydroone.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19129 | Lauzon TS Fence 2009 | N.T.C.1.28 | 1142 | 215 | FACILITIES & REAL ESTATE | UNPLND |  |  | Yes |  |  |  |  | Transmission Site Facilities | cindy.copp@hydroone.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19130 | Parry Sound TS Fence 2009 | N.T.C.1.28 | 1142 | 215 | FACILITIES & REAL ESTATE | UNPLND |  |  | Yes |  |  |  |  | Transmission Site Facilities | cindy.copp@hydroone.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19132 | Riverdale TS Fence 2009 | N.T.C.1.28 | 1142 | 215 | FACILITIES & REAL ESTATE | UNPLND |  |  | Yes |  |  |  |  | Transmission Site Facilities | cindy.copp@hydroone.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19174 | HQ 483 Bay Street Tenant Improvements 2012 -2015 | N.C.C.1.50 | 7236 | 215 | FACILITIES & REAL ESTATE | AIP000028 |  | AIP000028 | Yes | AIP000028 |  |  |  | Real Estate Facilities | cindy.copp@hydroone.com | [6 empty] | Program | AWRD EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19179 | Bldg Repair Roof TS Facilities | N.T.C.1.28 | 1142 | 215 | FACILITIES & REAL ESTATE | AIP000668 |  | AIP000668 | Yes | AIP000668 |  |  |  | Transmission Site Facilities | cindy.copp@hydroone.com | [6 empty] | Program | EMPP AWRD | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19183 | Facilities Improvements Admin & SC | N.C.C.1.50 | 7236 | 215 | FACILITIES & REAL ESTATE | UNPLND |  |  | Yes |  |  |  |  | Real Estate Facilities | cindy.copp@hydroone.com | [6 empty] | Program | EMPP AWRD | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19206 | Bruce x Milton OPGW | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | 271 |  |  | Yes |  |  |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | [6 empty] | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19210 | Horner TS: Install 2 x 27.6 kV Feeder Positions | N.T.C.2.11 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Load Customer Connection | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19213 | Malden TS-M11-ID1099-Harrow IV Wind Farm | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Distribution Generation Connection | ryan.boudreau@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19214 | Station Grounding System Repairs | N.T.M.1.18 | 7370 | 206 | TX LINES AND STATIONS | AIP001090B | AIP001090 | AIP001090 | No | AIP001090 | Grounding System Studies & Repairs | 0 |  | Ancillary Systems Maintenance | Mike.Tanaskovic@HydroOne.com | Harshal.Bhatt@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | EMPP ACTN | Executing | Short Term Planning | # of Stations as demanded | 122636.3645 | 425946.0345 | 650371.2337 | 445452.7457 | 454690.4966 | 682166.7361 | 0 | 0 | 0 | 0 | 122636.3645 | 425946.0345 | 650371.2337 | 445452.7457 | 454690.4966 | 682166.7361 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Vulnerable (Modified-Tx Decision)
19216 | LV Cap Bank Replacement Program | N.T.C.1.18 | 7700 | 203 | PROJECT DELIVERY | AIP000576 |  | AIP000576 | Yes | AIP000576 |  |  |  | Other Power Equipment | James.Mardegan@HydroOne.com | [6 empty] | Program | ACCP EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19243 | NMS Enhancements | N.T.C.3.06 | 4514 | 212 | INFO SOLUTIONS DIVISION | 35 |  |  | Yes |  |  |  |  | Grid Operating and Control Facilities | Godfrey.Holder@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19248 | Dx UVM - Public Safety and Reliability | N.D.M.1.03 | 7362 | 204 | FORESTRY | AIP000244 | AIP000244 | AIP000244 | No | AIP000244 | Dx UVM – Public Safety and Reliability |  |  | Vegetation Management | emre.aydin@HydroOne.com | patrick.howe@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | AWRD EMPP | Executing | Short Term Planning | # of defects | 19035392.6321 | 21588870.867 | 26877821.3578 | 53802623.437 | 54705983.9749 | 0 | 0 | 0 | 0 | 0 | 19035392.6321 | 19234587.1599 | 19486914.3999 | 19422678.437 | 19463830.3558 | 0 | 0 | 0 | 0 | 0 | 0 | 2354283.7071 | 7390906.9579 | 34379945 | 35242153.6191 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Demand
19250 | Multi Year HVIT Replacement Program | N.T.C.1.18 | 7700 | 203 | PROJECT DELIVERY | AIP000569 |  | AIP000569 | Yes | AIP000569 |  |  |  | Other Power Equipment | James.Mardegan@HydroOne.com | [6 empty] | Program | EMPP ACTN | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19254 | Field Switching - Stations | N.T.M.3.01 | 7370 | 206 | TX LINES AND STATIONS | AIP001186 | AIP001186 | AIP001186 | No | AIP001186 | Operating Field Switching -Stations | 0 |  | Operations Contract | Godfrey.Holder@HydroOne.com | Daniel.Lam@HydroOne.com | System O&M | N/A | 0 | 03 - None (default) | 0 | Program | EMPP ACTN | Executing | Short Term Planning | # of orders | 3925471.0172 | 3982652.5952 | 4071658.669 | 4165103.5522 | 4251506.0591 | 4339667.6482 | 0 | 0 | 0 | 0 | 3925471.0172 | 3982652.5952 | 4071658.669 | 4165103.5522 | 4251506.0591 | 4339667.6482 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3900 | 3900 | 3900 | 3900 | 3900 | 3900 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | True | False |  | False | False | False | False | FALSE |  | 0 | 0 | Asset Optimal
19259 | To Be Closed - Distribution Document Management | N.D.M.1.07 | 7716 | 224 | ENGINEERING | AIP000269 | AIP000269 | AIP000269 | No | AIP000269 | Distribution Document Management |  |  | Other Services | emre.aydin@HydroOne.com | patrick.howe@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | init EMPP | Executing | Short Term Planning |  | 178045.4725 | 183448.6352 | 187459.8814 | 191628.229 | 195198.4576 | 0 | 0 | 0 | 0 | 0 | 178045.4725 | 183448.6352 | 187459.8814 | 191628.229 | 195198.4576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Preferred Alternative
19261 | Trout Creek DS-F1-ID10020-South River Small Hydro | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | 2 |  |  | Yes |  |  |  |  | Distribution Generation Connection | ryan.boudreau@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19267 | Greener Choices | N.C.M.2.50 | 7053 | 209 | HEALTH, SAFETY & ENV | AIP000101 | AIP000101 | AIP000101 | No | AIP000101 | Greener Choices | 0 |  | Conservation and Demand Management | welchw@hydroone.com | welchw@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | init | Short Term Planning | Short Term Planning | Placeholder | 429142.96 | 437725.73 | 446480.33 | 455409.88 | 464518.12 | 400000 | 0 | 0 | 0 | 0 | 429142.96 | 437725.73 | 446480.33 | 455409.88 | 464518.12 | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | False | [8 empty] | FALSE |  | 0 | 0 | Optimal (Modified-Tx Decision)
19268 | Dx UVM - QA/QC | N.D.M.1.03 | 7362 | 204 | FORESTRY | AIP000248 | AIP000248 | AIP000248 | No | AIP000248 | Dx UVM – QA/QC |  |  | Vegetation Management | emre.aydin@HydroOne.com | patrick.howe@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | AWRD EMPP | Executing | Short Term Planning | # of defects | 4853491.2371 | 4902726.0689 | 4911695.3176 | 4922462.3215 | 4915856.0383 | 0 | 0 | 0 | 0 | 0 | 4853491.2371 | 4916221.0442 | 5003519.9077 | 5090786.3908 | 5117341.092 | 0 | 0 | 0 | 0 | 0 | 0 | -13494.9752 | -91824.59 | -168324.0694 | -201485.0538 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Vulnerable
19270 | DC203 2010 Capacity Allocation Exempt Gen Conn | N.D.C.2.03 | 7374 | 205 | LINES | UNPLND |  |  | Yes |  |  |  |  | Distribution Generation Connection | ryan.boudreau@HydroOne.com | [6 empty] | Program | ACCP EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19275 | Level II Inspections - Stations | N.T.M.3.01 | 7370 | 206 | TX LINES AND STATIONS | AIP001188 | AIP001188 | AIP001188 | No | AIP001188 | Operating Level 2 Inspections - Stations | 0 |  | Operations Contract | Godfrey.Holder@HydroOne.com | emily.booth@hydroone.com | System O&M | N/A | 0 | 03 - None (default) | 0 | Program | ACTN EMPP | Executing | Short Term Planning | # of Orders | 380998.4629 | 386548.3744 | 395189.0932 | 404256.7757 | 412642.8146 | 421199.5423 | 0 | 0 | 0 | 0 | 380998.4629 | 386548.3744 | 395189.0932 | 404256.7757 | 412642.8146 | 421199.5423 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 602 | 602 | 602 | 602 | 602 | 602 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | False |  | False | True | False | False | FALSE |  | 0 | 0 | Asset Optimal
19276 | Field Verification - Stations | N.T.M.3.01 | 7370 | 206 | TX LINES AND STATIONS | AIP001187 | AIP001187 | AIP001187 | No | AIP001187 | Tx Field Verification of Operating Diagrams | 0 |  | Operations Contract | Godfrey.Holder@HydroOne.com | Mitchell.Wotton@HydroOne.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | EMPP ACTN | Executing | Short Term Planning | # of Stations Verified | 214385.5578 | 224614.3801 | 229633.1747 | 234899.9744 | 239770.9409 | 245161.3297 | 0 | 0 | 0 | 0 | 214385.5578 | 224614.3801 | 229633.1747 | 234899.9744 | 239770.9409 | 245161.3297 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59 | 60 | 59 | 61 | 62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | True | Transmission System Code, Section 6.10 | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Asset Optimal
19277 | Customer Event Investigation - Stations | N.T.M.3.01 | 7370 | 206 | TX LINES AND STATIONS | AIP001190 | AIP001190 | AIP001190 | No | AIP001190 | Customer Event Investigations -Stations | 0 |  | Operations Contract | Godfrey.Holder@HydroOne.com | Mitchell.Wotton@HydroOne.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | ACTN EMPP | Executing | Short Term Planning | # of Customer Requests | 139628.6358 | 145280.6217 | 148527.0521 | 153441.6858 | 158178.0473 | 158252.9001 | 0 | 0 | 0 | 0 | 139628.6358 | 145280.6217 | 148527.0521 | 153441.6858 | 158178.0473 | 158252.9001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 10 | 10 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | True | Transmission System Code, Section 6.10 | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Asset Optimal
19278 | Emergency Preparedness - Stations | N.T.M.3.01 | 7370 | 206 | TX LINES AND STATIONS | AIP001185 | AIP001185 | AIP001185 | No | AIP001185 | Operating Emergency Preparedness -Stations | 0 |  | Operations Contract | Godfrey.Holder@HydroOne.com | Mitchell.Wotton@HydroOne.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | ACTN EMPP | Executing | Short Term Planning | # of FCP Operations | 108697.1356 | 113096.9795 | 115624.1157 | 118246.1816 | 120602.6488 | 120660.1267 | 0 | 0 | 0 | 0 | 108697.1356 | 113096.9795 | 115624.1157 | 118246.1816 | 120602.6488 | 120660.1267 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 120 | 120 | 120 | 120 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | True | Electricity Market Rules: Chapter 5, Section 11. NERC standard COM-001 (R2 & R5) | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Asset Optimal
19279 | Operating Diagrams - E&CS | N.T.M.3.01 | 7716 | 224 | ENGINEERING | AIP001184 | AIP001184 | AIP001184 | No | AIP001184 | Tx Operating Diagrams | 0 |  | Operations Contract | Godfrey.Holder@HydroOne.com | Daniel.Lam@HydroOne.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | EMPP ACCP | Executing | Short Term Planning | # of Drawings Revised | 395398.7342 | 409398.114 | 412129.7021 | 421759.0775 | 432617.5644 | 441836.1882 | 0 | 0 | 0 | 0 | 395398.7342 | 409398.114 | 412129.7021 | 421759.0775 | 432617.5644 | 441836.1882 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300 | 300 | 300 | 300 | 300 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | True | False |  | False | False | False | False | FALSE |  | 0 | 0 | Asset Optimal
19281 | Operating Facilities Support & Mtce - OGCC IT | N.T.M.3.01 | 4339 | 212 | INFO SOLUTIONS DIVISION | UNPLND |  |  | Yes |  |  |  |  | Operations Contract | Godfrey.Holder@HydroOne.com | [6 empty] | Program | AWRD EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19282 | Control System Technical Support - OGCC IT | N.T.M.3.01 | 4339 | 212 | INFO SOLUTIONS DIVISION | UNPLND |  |  | Yes |  |  |  |  | Operations Contract | Godfrey.Holder@HydroOne.com | [6 empty] | Program | AWRD EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19285 | Network Operations Buildings Sustainment | N.T.C.3.06 | 4514 | 212 | INFO SOLUTIONS DIVISION | UNPLND |  |  | Yes |  |  |  |  | Grid Operating and Control Facilities | Godfrey.Holder@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19289 | DS Recloser Upgrade Program | N.D.C.1.08 | 7700 | 203 | PROJECT DELIVERY | AIP000157 | AIP000157 | AIP000157 | No | AIP000157 | DS Recloser Upgrade Program | ISD-SR-05 | Distribution Station Feeder Protection Upgrade | Distributing & Regulating Stations | emre.aydin@HydroOne.com | Cecilia.Pang@HydroOne.com | System Renewal | 0 | 0 | 03 - None (default) | 0 | Program | ACCP EMPP | Executing | Short Term Planning | # of Feeder Reclosers | 2297113.2294 | 2343080.3889 | 2392116.5501 | 2293772.8576 | 2340011.7408 | 0 | 0 | 0 | 0 | 0 | 2418013.9257 | 2466400.4094 | 2518017.4211 | 2414497.7448 | 2463170.2535 | 0 | 0 | 0 | 0 | 0 | -120900.6963 | -123320.0205 | -125900.8711 | -120724.8872 | -123158.5127 | 0 | 0 | 0 | 0 | 0 | -5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38 | 38 | 38 | 37 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Critical Spend Plan
19295 | Kenora TS - Power Angle Relay Decommissioning | N.T.C.2.03 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Network Transfer Capability | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19297 | Kirkland Lake TS - Add 44kV Feeder Position | N.T.C.2.11 | 7700 | 203 | PROJECT DELIVERY | AIP000792 | AIP000792 | AIP000792 | No | AIP000792 | Kirkland Lake TS - Add 44kV Feeder Position | 0 |  | Load Customer Connection | Robert.Reinmuller@HydroOne.com | Kirpal.Bahra@HydroOne.com | System Access | Northern | Not Required | 03 - None (default) | Not Required | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -5600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42871 | [13 empty] | FALSE |  | 0 | 0 | Alternative 1
19299 | DS Transformer Purchase Program | N.D.C.1.08 | 7700 | 203 | PROJECT DELIVERY | AIP000165 | AIP000165 | AIP000165 | No | AIP000165 | Station Spare Transformer Purchases | ISD-SR-03 | Station Spare Transformer Purchases Program | Distributing & Regulating Stations | emre.aydin@HydroOne.com | Trevor.Beausoleil@HydroOne.com | System Renewal | N/A | 0 | 03 - None (default) | 0 | Program | ACCP EMPP | Executing | Short Term Planning | # of Transformers | 2641517.1861 | 3368189.0363 | 4125692.2115 | 4210562.0099 | 4294631.7846 | 0 | 0 | 0 | 0 | 0 | 2641517.1861 | 3368189.0363 | 4125692.2115 | 4210562.0099 | 4294631.7846 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 5 | 6 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Vulnerable
19301 | DS Technical Support Program | N.D.M.1.04 | 7716 | 224 | ENGINEERING | AIP000255 | AIP000255 | AIP000255 | No | AIP000255 | DS Misc Mtce & Support - Technical Support |  |  | Distributing and Regulating Stations | emre.aydin@HydroOne.com | Trevor.Beausoleil@HydroOne.com | System O&M | N/A | 0 | 03 - None (default) | 0 | Program | EMPP ACCP | Executing | Short Term Planning | Retainer | 1141944.8718 | 1072441.5974 | 1095891.5652 | 1120259.8427 | 1141131.5052 | 0 | 0 | 0 | 0 | 0 | 1141944.8718 | 1072441.5974 | 1095891.5652 | 1120259.8427 | 1141131.5052 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal (Retainer)
19309 | Environmental Mgt- Planned Corrective Mtc Program | N.T.M.1.05 | 7370 | 206 | TX LINES AND STATIONS | AIP001011B | AIP001011 | AIP001011 | No | AIP001011 | Environmental Corrective Maintenance | 0 |  | Environmental Management | Mike.Tanaskovic@HydroOne.com | Sebastian.Niculae@HydroOne.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | ACTN EMPP | Executing | Short Term Planning | # of Orders | 77540.1682 | 194358.3201 | 194752.1693 | 195260.1758 | 195352.5829 | 195444.5765 | 0 | 0 | 0 | 0 | 77540.1682 | 194358.3201 | 194752.1693 | 195260.1758 | 195352.5829 | 195444.5765 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 10 | 10 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Intermedia (Tx Constraint Reduction)
19310 | DS Transformer / ULTC Refurbishments | N.D.M.1.04 | 7370 | 206 | TX LINES AND STATIONS | AIP000258 | AIP000258 | AIP000258 | No | AIP000258 | DS Transformer Overhaul Program |  |  | Distributing and Regulating Stations | emre.aydin@HydroOne.com | Trevor.Beausoleil@HydroOne.com | System O&M | N/A | 0 | 03 - None (default) | 0 | Program | ACTN EMPP | Executing | Short Term Planning | # of Transformers | 1309832.6084 | 1349582.1907 | 1379092.1764 | 1409757.6096 | 1436022.9727 | 0 | 0 | 0 | 0 | 0 | 1309832.6084 | 1349582.1907 | 1379092.1764 | 1409757.6096 | 1436022.9727 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 6 | 6 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Vulnerable
19337 | DS Demand/Emergency Capital Program | N.D.C.1.08 | 7370 | 206 | TX LINES AND STATIONS | AIP000155 | AIP000155 | AIP000155 | No | AIP000155 | DS Demand Capital | ISD-SR-01 | Distribution Stations Demand Capital Program | Distributing & Regulating Stations | emre.aydin@HydroOne.com | Trevor.Beausoleil@HydroOne.com | System Renewal | N/A | 0 | 03 - None (default) | 0 | Program | ACTN EMPP | Executing | Short Term Planning | # of Demand replacement | 2283265.7575 | 2329107.1202 | 2377434.6862 | 2426340.9076 | 2474786.3236 | 0 | 0 | 0 | 0 | 0 | 2455124.4705 | 2504416.2583 | 2556381.383 | 2608968.7179 | 2661060.5631 | 0 | 0 | 0 | 0 | 0 | -171858.7129 | -175309.1381 | -178946.6968 | -182627.8102 | -186274.2394 | 0 | 0 | 0 | 0 | 0 | -7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
19338 | DS Station Refurbishment Program | N.D.C.1.08 | 7700 | 203 | PROJECT DELIVERY | AIP000160 |  | AIP000160 | Yes | AIP000160 | DS Station Refurbishment Program | ISD-SR-06 | Distribution Station Refurbishment | Distributing & Regulating Stations | emre.aydin@HydroOne.com | Nathan.Cox@hydroone.com | System Renewal | N/A | 0 | 03 - None (default) | 0 | Program | EMPP ACTN | Executing | Short Term Planning | # of Stations | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19339 | DS Component Replacement Program | N.D.C.1.08 | 7700 | 203 | PROJECT DELIVERY | AIP000154 | AIP000154 | AIP000154 | No | AIP000154 | DS Component Replacement | ISD-SR-04 | Distribution Station Planned Component Replacement Program | Distributing & Regulating Stations | emre.aydin@HydroOne.com | Nathan.Cox@hydroone.com | System Renewal | N/A | 0 | 03 - None (default) | 0 | Program | AWRD EMPP | Executing | Short Term Planning | # of Stations | 1938604.2727 | 1977525.7344 | 2018558.1021 | 2060082.0582 | 2101214.5168 | 0 | 0 | 0 | 0 | 0 | 2084520.7234 | 2126371.7574 | 2170492.5829 | 2215141.9981 | 2259370.4481 | 0 | 0 | 0 | 0 | 0 | -145916.4506 | -148846.023 | -151934.4808 | -155059.9399 | -158155.9314 | 0 | 0 | 0 | 0 | 0 | -7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 50 | 50 | 50 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Vulnerable
19341 | DS MUS Refurbishment Program | N.D.C.1.08 | 7700 | 203 | PROJECT DELIVERY | AIP000156A | AIP000156 | AIP000156 | No | AIP000156 | DS MUS Refurbishment_Purchase Program |  |  | Distributing & Regulating Stations | emre.aydin@HydroOne.com | Trevor.Beausoleil@HydroOne.com | System Renewal | N/A | 0 | 03 - None (default) | 0 | Program | EMPP ACCP | Executing | Short Term Planning | # of MUSs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Vulnerable
19349 | Tx Lines - RoW Unplanned Work | N.T.M.1.07 | 7362 | 204 | FORESTRY | AIP001026 | AIP001026 | AIP001026 | No | AIP001026 | Unplanned ROW Maintenance | 0 |  | Rights of Way | hassan.hamzeh@hydroone.com | Shannon.O'Keefe@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | EMPP ACCP | Executing | Short Term Planning | # of Work Orders (asset pop in route kms) | 1364125.6329 | 1377877.509 | 1400247.9036 | 1413359.0393 | 1433792.8773 | 1444195.5423 | 0 | 0 | 0 | 0 | 1364125.6329 | 1377877.509 | 1400247.9036 | 1413359.0393 | 1433792.8773 | 1444195.5423 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | True | False |  | False | False | False | False | FALSE |  | 0 | 0 | Optimal (Modified)
19353 | TX Stations Cleanup Program | N.T.M.1.19 | 7370 | 206 | TX LINES AND STATIONS | AIP001104 |  | AIP001104 | Yes | AIP001104 |  |  |  | Infrastructure Maintenance | Mike.Tanaskovic@HydroOne.com | [6 empty] | Program | ACTN EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19357 | Tx Lines - RoW Condition Patrols | N.T.M.1.07 | 7362 | 204 | FORESTRY | AIP001019 | AIP001019 | AIP001019 | No | AIP001019 | ROW Condition Patrols- L0, Vulnerable | 0 |  | Rights of Way | hassan.hamzeh@hydroone.com | Shannon.O'Keefe@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | ACCP EMPP | Executing | Short Term Planning | route km's | 1354240.6645 | 1387790.217 | 1400247.9036 | 1413359.0393 | 1423836.1009 | 1444195.5423 | 0 | 0 | 0 | 0 | 1354240.6645 | 1387790.217 | 1400247.9036 | 1413359.0393 | 1423836.1009 | 1444195.5423 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | True | The transmission ROWs selected for brush control maintenance in the vulnerable investment level are critical circuits regulated by NERC standard FAC-003-04. | False |  | False | False |  | False | True | False | False | FALSE |  | 0 | 0 | Reaggregated (Vulnerable/Intermediate (Modified))
19358 | Tx Lines - RoW Program Management | N.T.M.1.07 | 7362 | 204 | FORESTRY | AIP001024 | AIP001024 | AIP001024 | No | AIP001024 | ROW Program Auditing and Management | 0 |  | Rights of Way | hassan.hamzeh@hydroone.com | Shannon.O'Keefe@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | EMPP ACCP | Executing | Short Term Planning | N/A | 98849.6835 | 99127.8726 | 99308.362 | 109485.5594 | 109525.8141 | 109559.6618 | 0 | 0 | 0 | 0 | 98849.6835 | 99127.8726 | 99308.362 | 109485.5594 | 109525.8141 | 109559.6618 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | False |  | False | False | False | False | TRUE | An annual review of Hydro One's Transmisison Vegetation Management Program helps Hydro One to maintain industry best practices. | 0 | 0 | Optimal (Modified)
19359 | Tx Lines - RoW Notifications | N.T.M.1.07 | 7362 | 204 | FORESTRY | AIP001025 | AIP001025 | AIP001025 | No | AIP001025 | ROW Notification Program | 0 |  | Rights of Way | hassan.hamzeh@hydroone.com | Shannon.O'Keefe@hydroone.com | System O&M | 0 | 0 | 02 - Expectation (no agreement) | 0 | Program | ACCP EMPP | Executing | Short Term Planning | route km's | 1512400.1582 | 1536482.0259 | 1559141.2827 | 1572610.762 | 1593103.2501 | 1613515.0196 | 2418794.64 | 0 | 0 | 0 | 1512400.1582 | 1536482.0259 | 1559141.2827 | 1572610.762 | 1593103.2501 | 1613515.0196 | 2418794.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3400 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | True | The notification program is required to inform all adjacent property owners of upcoming ROW maintenance. Customers are accustomed to receiving notifications prior to maintenance and without the program, would be shocked at the vegetation changes. Negative media attention would likely result. | False | False | False | False | FALSE |  | 0 | 0 | Intermediate (Modified)
19365 | Tx Lines - RoW Brush Control | N.T.M.1.07 | 7362 | 204 | FORESTRY | AIP001018 | AIP001018 | AIP001018 | No | AIP001018 | ROW Brush Control- L0, Vulnerable | 0 |  | Rights of Way | hassan.hamzeh@hydroone.com | Shannon.O'Keefe@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | ACCP EMPP | Executing | Short Term Planning | # of ha | 19295458.2277 | 19557929.2721 | 19821949.0462 | 20095576.7629 | 20331981.2454 | 20577296.4851 | 0 | 0 | 0 | 0 | 19295458.2277 | 19557929.2721 | 19821949.0462 | 20095576.7629 | 20331981.2454 | 20577296.4851 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12500 | 12500 | 12500 | 12500 | 12500 | 12500 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | True | The transmission ROWs selected for brush control maintenance in the vulnerable investment level are critical circuits regulated by NERC standard FAC-003-04. | False |  | False | False |  | False | True | False | False | FALSE |  | 0 | 0 | Reaggregated (Vulnerable/Intermediate (Modified-Tx Decision))
19372 | Field verification of DS Operating Diagrams | N.D.M.3.01 | 7370 | 206 | TX LINES AND STATIONS | AIP000351 | AIP000351 | AIP000351 | No | AIP000351 | Dx Field Verification of Operating Diagrams |  |  | Operations Contract | Godfrey.Holder@HydroOne.com | william.ilie@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | ACTN EMPP | Executing | Short Term Planning | # of Field Checks | 93337.4803 | 96170.0213 | 98272.8364 | 100457.995 | 102880.6476 | 0 | 0 | 0 | 0 | 0 | 93337.4803 | 96170.0213 | 98272.8364 | 100457.995 | 102880.6476 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 101 | 155 | 112 | 101 | 101 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
19373 | Emergency Preparedness Funding | N.D.M.3.01 | 7374 | 205 | LINES | AIP000350 | AIP000350 | AIP000350 | No | AIP000350 | Dx Emergency Preparedness - Operating |  |  | Operations Contract | Godfrey.Holder@HydroOne.com | william.ilie@hydroone.com | System O&M | N/A | 0 | 03 - None (default) | 0 | Program | EMPP ACCP | Executing | Short Term Planning | Retainer | 51000.0588 | 52547.6926 | 53696.7358 | 54890.8007 | 55913.4185 | 0 | 0 | 0 | 0 | 0 | 51000.0588 | 52547.6926 | 53696.7358 | 54890.8007 | 55913.4185 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
19374 | D058 OGCC Data Collection & Information Updates | N.D.M.3.01 | 7374 | 205 | LINES | AIP000347 | AIP000347 | AIP000347 | No | AIP000347 | Dx Data Collection & Information Updates - OGCC/Provincial Lines |  |  | Operations Contract | Godfrey.Holder@HydroOne.com | william.ilie@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | ACCP EMPP | Executing | Short Term Planning | # of field checks | 204000.1188 | 262738.6981 | 268483.7967 | 274453.6982 | 279567.0925 | 0 | 0 | 0 | 0 | 0 | 204000.1188 | 262738.6981 | 268483.7967 | 274453.6982 | 279567.0925 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 250 | 300 | 300 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
19381 | Dual Station LAN | N.T.C.3.08 | 7700 | 203 | PROJECT DELIVERY | AIP000997 | AIP000997 | AIP000997 | No | AIP000997 | Station Controls | 0 |  | Integrating Operating Infrastructure | Miroslav.Kostic@HydroOne.com | Andrew.Webb@HydroOne.com | General Plant | 0 | 0 | 03 - None (default) | 0 | Program | EMPP ACCP | Executing | Short Term Planning | # of Stations | 622555.0017 | 632863.5194 | 640177.4234 | 645136.0526 | 650038.0631 | 657346.5471 | 0 | 0 | 0 | 0 | 622555.0017 | 632863.5194 | 640177.4234 | 645136.0526 | 650038.0631 | 657346.5471 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | True | False |  | False | False | False | False | FALSE |  | 0 | 0 | Demand
19383 | Tx Lines - RoW G&S Demand Corrective Maintenance | N.T.M.1.07 | 7370 | 206 | TX LINES AND STATIONS | AIP005649A | AIP005649 | AIP005649 | No | AIP005649 | Grounds & Sites Corrective Maintenance | 0 |  | Rights of Way | hassan.hamzeh@hydroone.com | Shannon.O'Keefe@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | ACTN EMPP | Executing | Short Term Planning | # of Work Orders | 353075.9873 | 459236.9968 | 460162.5424 | 471172.4505 | 471394.2275 | 481440.4034 | 0 | 0 | 0 | 0 | 353075.9873 | 459236.9968 | 460162.5424 | 471172.4505 | 471394.2275 | 481440.4034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | True | False |  | False | False | True | False | FALSE |  | 0 | 0 | Asset Optimal (Modified -Tx Decision)
19384 | Ottawa - Hwy 417 Interchange_Recoverable | N.T.C.1.14 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Third Party Transmission System Modifications | john.boldt@HydroOne.com | [6 empty] | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19386 | 600 Volt Self Contained to 120/208 Xfr Rated | N.D.C.1.09 | 7374 | 205 | LINES | AIP000172A | AIP000172 | AIP000172 | No | AIP000172 | Revenue Meter Upgrades |  |  | Metering | Peter.Mitskos@HydroOne.com | Dominic.Consorti@HydroOne.com | System Access | 0 | 0 | 03 - None (default) | 0 | Program | ACCP EMPP | Executing | Short Term Planning | # of meters | 562258.5927 | 573547.1053 | 585447.8808 | 597491.0993 | 609420.9131 | 0 | 0 | 0 | 0 | 0 | 562258.5927 | 573547.1053 | 585447.8808 | 597491.0993 | 609420.9131 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 130 | 130 | 130 | 130 | 130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Demand - Modified - M2M Savings
19397 | Strategic Sourcing for Transmission Transformers | N.T.C.1.75 | 7732 | 207 | SUPPLY CHAIN SERVICES | UNPLND |  |  | Yes | [12 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19405 | 750MVA Autotransformer Remediation Prog | N.T.M.1.16 | 7370 | 206 | TX LINES AND STATIONS | AIP001071D |  | AIP001071 | Yes | AIP001071 | Transformer Refurbishments |  |  | Power Equipment | Mike.Tanaskovic@HydroOne.com | perry.ng@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | EMPP ACTN | Executing | Short Term Planning | # of Transformers | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19411 | TELCO CHARGES - BELL MSA - 2009 to 2013 | N.C.M.1.25 | 4339 | 212 | INFO SOLUTIONS DIVISION | AIP000083A | AIP000083 | AIP000083 | No | AIP000083 | Telecom Field Services | 0 |  | Business Telecom | lincoln.frost-hunt@hydroone.com | robert.hosford@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | init EMPP | Executing | Short Term Planning | Retainer | 1700000 | 1700000.12 | 1700000.12 | 1700000 | 1700000 | 1700000 | 0 | 0 | 0 | 0 | 1700000 | 1700000.12 | 1700000.12 | 1700000 | 1700000 | 1700000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | True | Agreement/Contract with Telecommunicatons Provider Bell. | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Intermediate
19425 | IESO SIA's | N.T.M.1.14 | 4048 | 213 | PLANNING | AIP001033 | AIP001033 | AIP001033 | No | AIP001033 | IESO SIA's | 0 |  | Engineering and Environmental Support | Mike.Tanaskovic@HydroOne.com | Farinaz.Yousefi@HydroOne.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | AWRD EMPP | Executing | Short Term Planning | # of documents | 104737.2004 | 101110.4697 | 101294.4895 | 101522.9334 | 101560.3373 | 101591.7263 | 0 | 0 | 0 | 0 | 104737.2004 | 101110.4697 | 101294.4895 | 101522.9334 | 101560.3373 | 101591.7263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | True | transmission system code requierement | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Intermediate
19427 | Technical Support E&CS <50 hours | N.T.M.1.14 | 7716 | 224 | ENGINEERING | AIP001040A | AIP001040 | AIP001040 | No | AIP001040 | Technical Support | 0 |  | Engineering and Environmental Support | Mike.Tanaskovic@HydroOne.com | Farinaz.Yousefi@HydroOne.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | EMPP ACCP | Executing | Short Term Planning | Retainer | 494248.4177 | 1090406.5991 | 1142046.1625 | 1094855.5938 | 1095258.5392 | 1145396.4646 | 0 | 0 | 0 | 0 | 494248.4177 | 1090406.5991 | 1142046.1625 | 1094855.5938 | 1095258.5392 | 1145396.4646 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Intermediate - (Modified-Tx Decision)
19428 | Technical Support E&CS >50 hours | N.T.M.1.14 | 7716 | 224 | ENGINEERING | AIP001040B | AIP001040 | AIP001040 | No | AIP001040 | Technical Support | 0 |  | Engineering and Environmental Support | Mike.Tanaskovic@HydroOne.com | Farinaz.Yousefi@HydroOne.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | ACTN EMPP | Executing | Short Term Planning | Retainer | 395398.7342 | 594767.2358 | 635573.5165 | 597193.9603 | 597413.8681 | 637438.0723 | 0 | 0 | 0 | 0 | 395398.7342 | 594767.2358 | 635573.5165 | 597193.9603 | 597413.8681 | 637438.0723 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Intermediate - (Modified-Tx Decision)
19429 | Technical Support External | N.T.M.1.14 | 4048 | 213 | PLANNING | AIP001040C | AIP001040 | AIP001040 | No | AIP001040 | Technical Support | 0 |  | Engineering and Environmental Support | Mike.Tanaskovic@HydroOne.com | Farinaz.Yousefi@HydroOne.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | AWRD EMPP | Executing | Short Term Planning | Retainer | 49424.8418 | 49563.9363 | 49654.181 | 49766.1634 | 49784.5587 | 49799.8463 | 0 | 0 | 0 | 0 | 49424.8418 | 49563.9363 | 49654.181 | 49766.1634 | 49784.5587 | 49799.8463 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Intermediate - (Modified-Tx Decision)
19430 | Technical Support Stations | N.T.M.1.14 | 7370 | 206 | TX LINES AND STATIONS | AIP001040D | AIP001040 | AIP001040 | No | AIP001040 | Technical Support | 0 |  | Engineering and Environmental Support | Mike.Tanaskovic@HydroOne.com | Farinaz.Yousefi@HydroOne.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | EMPP ACTN | Executing | Short Term Planning | Retainer | 49038.3316 | 48854.9997 | 48953.462 | 49080.4636 | 49103.6439 | 49126.5638 | 0 | 0 | 0 | 0 | 49038.3316 | 48854.9997 | 48953.462 | 49080.4636 | 49103.6439 | 49126.5638 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Intermediate - (Modified-Tx Decision)
19432 | Telecom Mgmt of Drawings/Records | N.T.M.1.14 | 7716 | 224 | ENGINEERING | AIP001041 | AIP001041 | AIP001041 | No | AIP001041 | Telecom Mgmt of drawings/records | 0 |  | Engineering and Environmental Support | Mike.Tanaskovic@HydroOne.com | Farinaz.Yousefi@HydroOne.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | ACCP EMPP | Executing | Short Term Planning | Retainer | 49424.8418 | 99127.8726 | 99308.4414 | 99532.3267 | 99569.0378 | 99599.6527 | 0 | 0 | 0 | 0 | 49424.8418 | 99127.8726 | 99308.4414 | 99532.3267 | 99569.0378 | 99599.6527 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Intermediate (Modified-Tx Decision)
19436 | Overhead Tx Lines - Demand Work - PL | N.T.M.1.20 | 7370 | 206 | TX LINES AND STATIONS | AIP001111 | AIP001111 | AIP001111 | No | AIP001111 | Demand Maintenance | 0 |  | Overhead Lines | hassan.hamzeh@hydroone.com | jacky.chiu@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | ACTN EMPP | Executing | Short Term Planning | # of incidents | 3564851.3215 | 3500445.8349 | 3556850.3391 | 3690577.9747 | 3733600.8666 | 3821132.3561 | 0 | 0 | 0 | 0 | 3564851.3215 | 3500445.8349 | 3556850.3391 | 3690577.9747 | 3733600.8666 | 3821132.3561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | True | False |  | False | False | False | False | FALSE |  | 0 | 0 | Demand
19457 | TC219 Advance Release for 17 Generator Connections | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | [6 empty] | Program | EMPP ACCP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19459 | Shieldwire Replacement Program - E&CS | N.T.C.1.12 | 7370 | 206 | TX LINES AND STATIONS | AIP000466A | AIP000466 | AIP000466 | No | AIP000466 | Tx Lines Shieldwire Replacement Program | SR-24 | Transmission Line Shieldwire Replacement | Overhead Lines Component Refurb & Repl | hassan.hamzeh@hydroone.com | Deniz.Turkben@HydroOne.com | System Renewal | N/A | 0 | 03 - None (default) | 0 | Program | ACTN EMPP | Executing | Short Term Planning | # of KM of shieldwire replaced | 5052320.1406 | 5135978.7674 | 5195334.4903 | 5235575.8619 | 5275357.9049 | 5334669.3884 | 0 | 0 | 0 | 0 | 5741272.887 | 5836339.5085 | 5903789.1935 | 5949518.0249 | 5994724.892 | 6062124.305 | 0 | 0 | 0 | 0 | -688952.7464 | -700360.741 | -708454.7032 | -713942.163 | -719366.987 | -727454.9166 | 0 | 0 | 0 | 0 | -12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109.85 | 109.85 | 109.85 | 109.85 | 109.85 | 109.85 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Intermediate
19461 | ISD Project Governance | N.C.M.2.70 | 4342 | 212 | INFO SOLUTIONS DIVISION | AIP000111 | AIP000111 | AIP000111 | No | AIP000111 | ISD Project Governance | 0 |  | IT - Project & Architecture Services | lincoln.frost-hunt@hydroone.com | Raj.Agnihotri@HydroOne.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | EMPP AWRD | Executing | Short Term Planning | Retainer | 849509.24 | 850000.12 | 850000 | 849999.88 | 849999.88 | 850000 | 0 | 0 | 0 | 0 | 849509.24 | 850000.12 | 850000 | 849999.88 | 849999.88 | 850000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | False |  | False | False | True | False | FALSE |  | 0 | 0 | Intermediate
19462 | Tx Lines Emergency Replacements | N.T.C.1.12 | 7370 | 206 | TX LINES AND STATIONS | AIP000457 | AIP000457 | AIP000457 | No | AIP000457 | Tx Lines Emergency Replacement | SR-26 | Transmission Line Emergency Restoration | Overhead Lines Component Refurb & Repl | hassan.hamzeh@hydroone.com | jacky.chiu@hydroone.com | System Renewal | 0 | 0 | 03 - None (default) | 0 | Program | ACTN EMPP | Executing | Short Term Planning | # of Work Orders | 8934253.1222 | 9082190.4837 | 9187152.1308 | 9258312.7488 | 9328661.3157 | 9433544.442 | 0 | 0 | 0 | 0 | 10152560.3661 | 10320671.0042 | 10439945.6031 | 10520809.9418 | 10600751.4951 | 10719936.8659 | 0 | 0 | 0 | 0 | -1218307.2439 | -1238480.5205 | -1252793.4724 | -1262497.193 | -1272090.1794 | -1286392.4239 | 0 | 0 | 0 | 0 | -12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | True | False |  | False | False | False | False | FALSE |  | 0 | 0 | Demand
19463 | Tx Lines - TC112 ROW projects | N.T.C.1.12 | 7370 | 206 | TX LINES AND STATIONS | AIP000464 | AIP000464 | AIP000464 | No | AIP000464 | Transmission Access ROW Projects (TARP) | 0 |  | Overhead Lines Component Refurb & Repl | hassan.hamzeh@hydroone.com | Shannon.O'Keefe@hydroone.com | System Renewal | 0 | 0 | 03 - None (default) | 0 | Program | ACTN EMPP | Executing | Short Term Planning | # of Access Structures | 2054878.2181 | 2088903.7625 | 2113044.9795 | 2129411.9155 | 2145592.1797 | 2169715.2167 | 0 | 0 | 0 | 0 | 2335088.8842 | 2373754.2756 | 2401187.4767 | 2419786.2676 | 2438172.9315 | 2465585.4735 | 0 | 0 | 0 | 0 | -280210.6661 | -284850.5131 | -288142.4972 | -290374.3521 | -292580.7518 | -295870.2568 | 0 | 0 | 0 | 0 | -12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 10 | 10 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | True | The Public Lands Act with the Ministry of Natural Resources and Forestry requires Hydro One to maintain any bridges owned and operated by Hydro One. | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Optimal
19466 | Caledonia TS M4 ID10650 Walpole1 10MW Solar Projct | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000199 |  | AIP000199 | Yes | AIP000199 | Large Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19467 | Caledonia TS M4 ID10720 Walpole2 10MW Solar Projct | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000195 |  | AIP000195 | Yes | AIP000195 | Small Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19469 | Microwave Replacement - Phase 3 drawings | N.T.C.1.25 | 7700 | 203 | PROJECT DELIVERY | 267 |  |  | Yes |  |  |  |  | Auxiliary Telecommunication Equipment | Miroslav.Kostic@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19482 | Inergi Base Services | N.C.M.1.70 | 4339 | 212 | INFO SOLUTIONS DIVISION | AIP000091C |  | AIP000091 | Yes | AIP000091 | Inergi Sustainment |  |  | IT - Sustainment and Operations | lincoln.frost-hunt@hydroone.com | robert.hosford@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | AWRD EMPP | Executing | Short Term Planning | Retainer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19484 | IT 3RD PARTY CONTRACTS | N.C.M.1.70 | 4339 | 212 | INFO SOLUTIONS DIVISION | AIP000090 | AIP000090 | AIP000090 | No | AIP000090 | 3rd Party Contracts | 0 |  | IT - Sustainment and Operations | lincoln.frost-hunt@hydroone.com | robert.hosford@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | init EMPP | Executing | Short Term Planning | Retainer | 23469000 | 23468999.88 | 23469000 | 23468999.88 | 23469000 | 23468999.88 | 0 | 0 | 0 | 0 | 23469000 | 23468999.88 | 23469000 | 23468999.88 | 23469000 | 23468999.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | True | Multiple Vendors for hardware/software licenses and maintenance | False | False |  | False | False | True | False | FALSE |  | 0 | 0 | Intermediate
19488 | PeakSaver Aggregator Agreement | N.D.M.2.50 | 1144 | 220 | STRATEGY & CONSERV | AIP005521 |  | AIP005521 | Yes | AIP005521 |  |  |  | Conservation and Demand Management | Imran.Merali@HydroOne.com | [6 empty] | Program | AWRD EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19500 | TELCO PROJECTS -MAC Changes (non Bell) 2010 | N.C.M.1.25 | 4339 | 212 | INFO SOLUTIONS DIVISION | AIP000083B | AIP000083 | AIP000083 | No | AIP000083 | Telecom Field Services | 0 |  | Business Telecom | lincoln.frost-hunt@hydroone.com | robert.hosford@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | AWRD EMPP | Executing | Short Term Planning | Retainer | 100000.13 | 100000.23 | 100000.13 | 100196.32 | 100196.16 | 100000 | 0 | 0 | 0 | 0 | 100000.13 | 100000.23 | 100000.13 | 100196.32 | 100196.16 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | True | Agreement/Contract with Telecommunicatons Provider Bell. | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Intermediate
19502 | Dx Operating Facilities Sustainment | N.D.C.3.08 | 4514 | 212 | INFO SOLUTIONS DIVISION | UNPLND |  |  | Yes |  |  |  |  | Operating Infrastructure | Godfrey.Holder@HydroOne.com | [6 empty] | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19507 | Infra / Tech Refresh Capital | N.C.C.1.70 | 4339 | 212 | INFO SOLUTIONS DIVISION | AIP000031 | AIP000031 | AIP000031 | No | AIP000031 | Infrastructure Refresh | GP-07 | Hardware/Software Refresh and Maintenance | IT - Sustainment and Operations | lincoln.frost-hunt@hydroone.com | Raj.Agnihotri@HydroOne.com | General Plant | 0 | 0 | 03 - None (default) | 0 | Program | init EMPP | Executing | Short Term Planning | Retainer | 13950000.24 | 13513615.2737 | 13394038.7991 | 13229865.9091 | 13064351.3487 | 12948802.0162 | 0 | 0 | 0 | 0 | 13950000.24 | 13513615.2737 | 13394038.7991 | 13229865.9091 | 13064351.3487 | 12948802.0162 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | False |  | False | False | True | False | FALSE |  | 0 | 0 | Vulnerable Modified (Tx Decision)
19509 | Infra / Tech Refresh OM&A - 2010 | N.C.M.2.70 | 4330 | 212 | INFO SOLUTIONS DIVISION | 306 |  |  | Yes |  |  |  |  | IT - Project & Architecture Services | lincoln.frost-hunt@hydroone.com | [6 empty] | Program | AWRD EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19510 | MFA Client Tech & Periph Refresh | N.C.C.1.70 | 4339 | 212 | INFO SOLUTIONS DIVISION | 6 |  |  | Yes |  |  |  |  | IT - Sustainment and Operations | lincoln.frost-hunt@hydroone.com | [6 empty] | Program | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19512 | MFA Telecom Tech Refresh | N.C.C.1.70 | 4339 | 212 | INFO SOLUTIONS DIVISION | 12 |  |  | Yes |  |  |  |  | IT - Sustainment and Operations | lincoln.frost-hunt@hydroone.com | [6 empty] | Program | EMPP init | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19514 | Security OM&A | N.C.M.2.70 | 838 | 212 | INFO SOLUTIONS DIVISION | AIP000110 | AIP000110 | AIP000110 | No | AIP000110 | IT Security | 0 |  | IT - Project & Architecture Services | lincoln.frost-hunt@hydroone.com | Sherry.Wilging@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | AWRD EMPP | Executing | Short Term Planning | Retainer | 679509.24 | 680000.12 | 679999.88 | 680000.04 | 680000 | 680000 | 0 | 0 | 0 | 0 | 679509.24 | 680000.12 | 679999.88 | 680000.04 | 680000 | 680000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | False |  | False | False | True | False | FALSE |  | 0 | 0 | Intermediate
19520 | Microwave Tower Remote Alarm Monitoring | N.T.M.1.23 | 4048 | 213 | PLANNING | AIP001130 | AIP001130 | AIP001130 | No | AIP001130 | Microwave Tower Remote Alarm Monitoring | 0 |  | Operation of Telecom Services | Miroslav.Kostic@HydroOne.com | Sheraz.Majid@HydroOne.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | AWRD EMPP | Executing | Short Term Planning | Retainer | 9660.8564 | 9932.2956 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9660.8564 | 9932.2956 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | True | contract with stanley | False |  | True |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Asset Optimal
19523 | Transmission Management of Records | N.T.M.1.14 | 7716 | 224 | ENGINEERING | AIP001042 | AIP001042 | AIP001042 | No | AIP001042 | Tx Mgmt of Records | 0 |  | Engineering and Environmental Support | Mike.Tanaskovic@HydroOne.com | Farinaz.Yousefi@HydroOne.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | ACCP EMPP | Executing | Short Term Planning | Retainer | 247124.2089 | 247819.6816 | 248270.9049 | 248830.8168 | 248922.3953 | 248999.3111 | 0 | 0 | 0 | 0 | 247124.2089 | 247819.6816 | 248270.9049 | 248830.8168 | 248922.3953 | 248999.3111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | True |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Intermediate (Tx Constraint Reduction)
19529 | Joint Use Audits (Yearly) | N.D.M.1.07 | 7374 | 205 | LINES | AIP000272 | AIP000272 | AIP000272 | No | AIP000272 | Joint Use Audits |  |  | Other Services | emre.aydin@HydroOne.com | Jenny.Seo@HydroOne.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | EMPP AWRD | Executing | Short Term Planning | # of audits | 95024.8353 | 97908.6163 | 100049.4261 | 102274.1178 | 104179.574 | 0 | 0 | 0 | 0 | 0 | 95024.8353 | 97908.6163 | 100049.4261 | 102274.1178 | 104179.574 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 10 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Vulnerable
19532 | DX-External Standards Dev | N.D.M.2.20 | 4419 | 213 | PLANNING | AIP000313 |  | AIP000313 | Yes | AIP000313 |  |  |  | Standards Program | Kevin.Mancherjee@HydroOne.com | [6 empty] | Program | EMPP AWRD | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19533 | 2010 TX Engineering Standards Dev't and Maint | N.T.M.2.20 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Standards Program | Kevin.Mancherjee@HydroOne.com | [6 empty] | Program | ACCP EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19534 | YEC 393 MW Generation Connections | N.T.C.2.12 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Generator Customer Connection | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19686 | Thunder Bay - Hwy 11/17-Pearl Lake_Recoverable | N.T.C.1.14 | 7700 | 203 | PROJECT DELIVERY | AIP000525 | AIP000525 | AIP000525 | No | AIP000525 | Thunder Bay - Hwy 11/17-Pearl Lake_Recoverable | 0 |  | Third Party Transmission System Modifications | john.boldt@HydroOne.com | Gian.Minichini@HydroOne.com | System Renewal | Northern | 0 | 01 - Agreement (current/future) | 0 | Project | DETL EXTR | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | 9968000 | 3323000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -300000 | -9968000 | -3323000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43266 | 44180 | True | Ministry of Transportation of Ontario (MTO) asked HONI to relocate several transmission structures on circuits A7L/R1LB and A6P to accommodate their highway development. | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Thunder Bay - Hwy 11/17-Pearl Lake_Recoverable
19755 | Tx TECHS-Stations Standards | N.T.M.2.20 | 7716 | 224 | ENGINEERING | AIP001162 | AIP001162 | AIP001162 | No | AIP001162 | Tx TECH-STATIONS Standards Development | 0 |  | Standards Program | Kevin.Mancherjee@HydroOne.com | rossella.fazio@hydroone.com | System O&M | N/A | 0 | 03 - None (default) | 0 | Program | ACCP EMPP | Executing | Short Term Planning | Assumption - # of Standards | 449498.1775 | 563453.7322 | 603571.3969 | 623843.7407 | 642795.2884 | 662284.1718 | 0 | 0 | 0 | 0 | 449498.1775 | 563453.7322 | 603571.3969 | 623843.7407 | 642795.2884 | 662284.1718 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 23 | 24 | 24 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Vulnerable
19756 | TX-External Standards Dev | N.T.M.2.20 | 4230 | 213 | PLANNING | AIP001160 |  | AIP001160 | Yes | AIP001160 |  |  |  | Standards Program | Kevin.Mancherjee@HydroOne.com | [6 empty] | Program | AWRD EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19757 | Disaster Rec Readiness Capital | N.C.C.1.70 | 4339 | 212 | INFO SOLUTIONS DIVISION | AIP000030 | AIP000030 | AIP000030 | No | AIP000030 | Disaster Recovery | GP-07 | Hardware/Software Refresh and Maintenance | IT - Sustainment and Operations | lincoln.frost-hunt@hydroone.com | Raj.Agnihotri@HydroOne.com | General Plant | 0 | 0 | 03 - None (default) | 0 | Program | EMPP AWRD | Executing | Short Term Planning | Retainer | 500000 | 497861.3682 | 493481.2834 | 487467.5767 | 481404.8512 | 477172.1247 | 0 | 0 | 0 | 0 | 500000 | 497861.3682 | 493481.2834 | 487467.5767 | 481404.8512 | 477172.1247 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | False |  | False | False | False | False | TRUE | Improve our disaster recovery and crisis management capabilities. | 0 | 0 | Intermediate
19759 | Disaster Rec Readiness OM&A | N.C.M.2.70 | 4339 | 212 | INFO SOLUTIONS DIVISION | AIP000107 | AIP000107 | AIP000107 | No | AIP000107 | Disaster Rec Readiness OM&A | 0 |  | IT - Project & Architecture Services | lincoln.frost-hunt@hydroone.com | Raj.Agnihotri@HydroOne.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | init EMPP | Executing | Short Term Planning | Retainer | 100000.12 | 100000.23 | 100000.13 | 100196.32 | 100196.28 | 100000 | 0 | 0 | 0 | 0 | 100000.12 | 100000.23 | 100000.13 | 100196.32 | 100196.28 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | False |  | False | False | False | False | TRUE | Improve our disaster recovery and crisis management capabilities. | 0 | 0 | Intermediate
19761 | Cornerstone Phase 3 - Capital | N.C.C.2.10 | 7193 | 227 | CORNERSTONE | UNPLND |  |  | Yes | [12 empty] | Project | AWRD | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19763 | Oshawa-Hwy 407 Ext.-Sideline 4_Recoverable | N.T.C.1.14 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Third Party Transmission System Modifications | john.boldt@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19765 | DX AM Standards Dev | N.D.M.2.20 | 4230 | 213 | PLANNING | AIP000308 | AIP000308 | AIP000308 | No | AIP000308 | Dx - AM Standards Development |  |  | Standards Program | Kevin.Mancherjee@HydroOne.com | rossella.fazio@hydroone.com | System O&M | N/A | 0 | 03 - None (default) | 0 | Program | init EMPP | Executing | Short Term Planning | Assumption - Standards Support | 92683.2394 | 96431.719 | 99507.0178 | 102717.0213 | 105656.5332 | 0 | 0 | 0 | 0 | 0 | 92683.2394 | 96431.719 | 99507.0178 | 102717.0213 | 105656.5332 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Vulnerable
19766 | TX AM Standards Dev | N.T.M.2.20 | 4230 | 213 | PLANNING | AIP001158 | AIP001158 | AIP001158 | No | AIP001158 | Tx - AM Standards Development | 0 |  | Standards Program | Kevin.Mancherjee@HydroOne.com | rossella.fazio@hydroone.com | System O&M | N/A | 0 | 03 - None (default) | 0 | Program | AWRD EMPP | Executing | Short Term Planning | Assumption - Standards Support | 236983.2198 | 223037.7134 | 251487.5027 | 324521.1699 | 344410.9776 | 354852.7887 | 0 | 0 | 0 | 0 | 236983.2198 | 223037.7134 | 251487.5027 | 324521.1699 | 344410.9776 | 354852.7887 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 7 | 8 | 9 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Asset Optimal
19767 | Security Capital | N.C.C.1.70 | 838 | 212 | INFO SOLUTIONS DIVISION | AIP000032 | AIP000032 | AIP000032 | No | AIP000032 | IT Security | 0 |  | IT - Sustainment and Operations | lincoln.frost-hunt@hydroone.com | Sherry.Wilging@hydroone.com | General Plant | 0 | 0 | 03 - None (default) | 0 | Program | AWRD EMPP | Executing | Short Term Planning | Retainer | 1301962.6 | 997677.0614 | 988899.698 | 976848.7563 | 964699.3126 | 956253.1674 | 0 | 0 | 0 | 0 | 1301962.6 | 997677.0614 | 988899.698 | 976848.7563 | 964699.3126 | 956253.1674 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | False |  | False | False | False | False | TRUE | Refresh and enhance IT and Security hardware and applications | 0 | 0 | Intermediate - Modified (Tx Decision)
19768 | Enterprise Content Management - Capital - 2010 | N.C.C.2.60 | 4330 | 212 | INFO SOLUTIONS DIVISION | 15876 |  |  | Yes |  |  |  |  | IT Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19769 | Enterprise Content Management - OM&A - 2010 | N.C.M.2.60 | 4330 | 212 | INFO SOLUTIONS DIVISION | 15875 |  |  | Yes |  |  |  |  | IT-Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19776 | Dx PCB Reduction Program - Testing | N.D.M.1.04 | 7370 | 206 | TX LINES AND STATIONS | AIP000254 | AIP000254 | AIP000254 | No | AIP000254 | DS Misc Mtce & Support - PCB Oil Sampling |  |  | Distributing and Regulating Stations | emre.aydin@HydroOne.com | Trevor.Beausoleil@HydroOne.com | System O&M | N/A | 0 | 03 - None (default) | 0 | Program | EMPP ACTN | Executing | Short Term Planning | # of Samples | 637414.5566 | 656758.1629 | 671118.9202 | 686041.8804 | 698823.5435 | 0 | 0 | 0 | 0 | 0 | 637414.5566 | 656758.1629 | 671118.9202 | 686041.8804 | 698823.5435 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 558 | 558 | 558 | 558 | 558 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Vulnerable
19780 | Load Transfer Studies | N.T.M.3.01 | 7370 | 206 | TX LINES AND STATIONS | AIP001183 | AIP001183 | AIP001183 | No | AIP001183 | Load Transfer Studies | 0 |  | Operations Contract | Godfrey.Holder@HydroOne.com | emily.booth@hydroone.com | System O&M | N/A | 0 | 03 - None (default) | 0 | Program | ACCP EMPP | Executing | Short Term Planning | # of Studies | 492034.0048 | 396189.825 | 298001.9282 | 197065.6492 | 108534.9069 | 110757.4493 | 0 | 0 | 0 | 0 | 492034.0048 | 396189.825 | 298001.9282 | 197065.6492 | 108534.9069 | 110757.4493 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | False |  | False | True | False | False | FALSE |  | 0 | 0 | Asset Optimal
19786 | Wilhaven DS F5 (North Service Road) Tie Line | N.D.C.2.02 | 7374 | 205 | LINES | AIP000189 |  | AIP000189 | Yes | AIP000189 | Dx System Modifications | ISD-SS-05 | Distribution System Modifications | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Wojciech.Maroszek@HydroOne.com | System Service | 0 | 0 | 03 - None (default) | 0 | Project | EMPP ACTN | Executing | Executing | Demand | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19788 | Cyber Vulnerability Assessment | N.T.M.1.29 | 838 | 212 | INFO SOLUTIONS DIVISION | AIP001140 | AIP001140 | AIP001140 | No | AIP001140 | Cyber Vulnerability Assessment | 0 |  | NERC Cyber Security Compliance Readiness | lincoln.frost-hunt@hydroone.com | Sherry.Wilging@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | AWRD EMPP | Executing | Short Term Planning | Retainer | 345973.8924 | 346947.5542 | 347579.2271 | 199455.3377 | 199528.7443 | 199199.3851 | 0 | 0 | 0 | 0 | 345973.8924 | 346947.5542 | 347579.2271 | 199455.3377 | 199528.7443 | 199199.3851 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | True | CIP-010 | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Asset Optimal
19790 | CSC-ESP Annual Reviews-PSIT | N.T.M.1.29 | 4032 | 212 | INFO SOLUTIONS DIVISION | UNPLND |  |  | Yes |  |  |  |  | NERC Cyber Security Compliance Readiness | lincoln.frost-hunt@hydroone.com | [6 empty] | Program | init EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19794 | CSC-System Management-PSIT | N.T.M.1.29 | 4339 | 212 | INFO SOLUTIONS DIVISION | UNPLND |  |  | Yes |  |  |  |  | NERC Cyber Security Compliance Readiness | lincoln.frost-hunt@hydroone.com | [6 empty] | Program | AWRD EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19823 | CSO Regulatory Compliance - MR & Billing | N.D.M.4.01 | 4175 | 202 | CUSTOMER CARE SERVICES | AIP000365 | AIP000365 | AIP000365 | No | AIP000365 | Billing - Regulatory Compliance |  |  | Customer Care Services Dx | Imran.Merali@HydroOne.com | Imran.Merali@HydroOne.com | System O&M | 0 | 0 | 01 - Agreement (current/future) | 0 | Program | AWRD EMPP | Executing | Short Term Planning | 202-D502003 | 242674.5619 | 245136.3034 | 245584.7659 | 246123.1161 | 245792.8019 | 0 | 0 | 0 | 0 | 0 | 242674.5619 | 245136.3034 | 245584.7659 | 246123.1161 | 245792.8019 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal: Anticipated OEB Requirements
19824 | CSO Regulatory Compliance - Collections | N.D.M.4.01 | 4175 | 202 | CUSTOMER CARE SERVICES | AIP000366 | AIP000366 | AIP000366 | No | AIP000366 | Collections - Regulatory Compliance |  |  | Customer Care Services Dx | Imran.Merali@HydroOne.com | Imran.Merali@HydroOne.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | AWRD EMPP | Executing | Short Term Planning | 202-D502006 | 3919679.5231 | 4019254.8313 | 4085518.7736 | 4155285.6999 | 4212260.457 | 0 | 0 | 0 | 0 | 0 | 3919679.5231 | 4019254.8313 | 4085518.7736 | 4155285.6999 | 4212260.457 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal: Base Case
19827 | Final Destination-Enterprise GIS DB Development | N.D.C.2.60 | 4512 | 212 | INFO SOLUTIONS DIVISION | AIP000215 |  | AIP000215 | Yes | AIP000215 |  |  |  | IT Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19829 | Enterprise GIS | N.C.C.2.60 | 4512 | 212 | INFO SOLUTIONS DIVISION | AIP000061 |  | AIP000061 | Yes | AIP000061 |  |  |  | IT Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | EMPP AWRD | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19831 | Tx Lines Foundation Life Extension-CN | N.T.C.1.12 | 7370 | 206 | TX LINES AND STATIONS | AIP000472A | AIP000472 | AIP000472 | No | AIP000472 | Tower Foundations | 0 |  | Overhead Lines Component Refurb & Repl | hassan.hamzeh@hydroone.com | TeodorConstantin.Culinescu@HydroOne.com | System Renewal | 0 | 0 | 03 - None (default) | 0 | Program | ACTN EMPP | Executing | Short Term Planning | Number of structures | 772812.8951 | 785609.4893 | 794688.6146 | 800844.0218 | 806929.2623 | 816001.496 | 0 | 0 | 0 | 0 | 878196.4717 | 892738.056 | 903055.2438 | 910050.0248 | 916965.0708 | 927274.4273 | 0 | 0 | 0 | 0 | -105383.5766 | -107128.5667 | -108366.6293 | -109206.003 | -110035.8085 | -111272.9313 | 0 | 0 | 0 | 0 | -12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Vulnerable (Tx Decision)
19836 | Cornerstone Phase 3 - OM&A | N.C.M.2.10 | 7193 | 227 | CORNERSTONE | UNPLND |  |  | Yes | [12 empty] | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19839 | Field Collections | N.D.M.4.01 | 7374 | 205 | LINES | AIP000361 | AIP000361 | AIP000361 | No | AIP000361 | Provincial Lines - Collections |  |  | Customer Care Services Dx | Imran.Merali@HydroOne.com | Imran.Merali@HydroOne.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | EMPP AWRD | Executing | Short Term Planning | # of Occurances | 5665618.1603 | 5957994.7113 | 6200540.8688 | 6503825.9856 | 6777077.8274 | 0 | 0 | 0 | 0 | 0 | 5665618.1603 | 5957994.7113 | 6200540.8688 | 6503825.9856 | 6777077.8274 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Vulnerable: Base Case - Modified - M2M Savings
19840 | OM&A portion of Enterprise GIS Capital Projects | N.C.M.2.60 | 4512 | 212 | INFO SOLUTIONS DIVISION | UNPLND |  |  | Yes |  |  |  |  | IT-Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19843 | CSO Service Enhancements - Contact Handling | N.D.M.4.01 | 4175 | 202 | CUSTOMER CARE SERVICES | UNPLND |  |  | Yes |  |  |  |  | Customer Care Services Dx | Imran.Merali@HydroOne.com | [6 empty] | Program | AWRD EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19847 | Grid Ops Zone Services Specialist Support to SIP | N.T.M.1.16 | 7370 | 206 | TX LINES AND STATIONS | AIP001053A | AIP001053 | AIP001053 | No | AIP001053 | Other Mtce - Power Equipment - Asset Condition Assessments | 0 |  | Power Equipment | Mike.Tanaskovic@HydroOne.com | Harshal.Bhatt@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | ACTN EMPP | Executing | Short Term Planning | Retainer | 247401.5993 | 251005.4897 | 256616.2455 | 262504.3443 | 267949.849 | 273506.2052 | 0 | 0 | 0 | 0 | 247401.5993 | 251005.4897 | 256616.2455 | 262504.3443 | 267949.849 | 273506.2052 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Intermediate
19850 | Overhead Tx Lines - Preventative Maintenance - PL | N.T.M.1.20 | 7370 | 206 | TX LINES AND STATIONS | AIP001113 | AIP001113 | AIP001113 | No | AIP001113 | Preventative Maintenance | 0 |  | Overhead Lines | hassan.hamzeh@hydroone.com | jacky.chiu@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | ACTN EMPP | Executing | Short Term Planning | skf ( # of km, circuit structure, assessments) | 4040758.5218 | 5286110.9636 | 5394671.4293 | 5502901.5779 | 5619412.0202 | 5731104.8888 | 0 | 0 | 0 | 0 | 4040758.5218 | 5286110.9636 | 5394671.4293 | 5502901.5779 | 5619412.0202 | 5731104.8888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | False |  | False | True | False | False | FALSE |  | 0 | 0 | Intermediate (modified-Tx Decision)
19865 | Overhead Tx Lines - Condition Assessment - PL | N.T.M.1.20 | 7370 | 206 | TX LINES AND STATIONS | AIP001109 | AIP001109 | AIP001109 | No | AIP001109 | Condition Assessment | 0 |  | Overhead Lines | hassan.hamzeh@hydroone.com | jacky.chiu@hydroone.com | System O&M | N/A | 0 | 03 - None (default) | 0 | Program | EMPP ACTN | Executing | Short Term Planning | skf ( # of km, circuit structure, assessments) | 4182969.7226 | 6903211.4525 | 7048319.4526 | 7174582.1679 | 7323305.6991 | 7488853.3793 | 0 | 0 | 0 | 0 | 4182969.7226 | 6903211.4525 | 7048319.4526 | 7174582.1679 | 7323305.6991 | 7488853.3793 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | False |  | False | True | False | False | FALSE |  | 0 | 0 | Intermediate (Modified) - Tx Decision
19866 | Overhead Tx Lines - Corrective Maintenance - PL | N.T.M.1.20 | 7370 | 206 | TX LINES AND STATIONS | AIP001110A | AIP001110 | AIP001110 | No | AIP001110 | Tx Corrective Maintenance | 0 |  | Overhead Lines | hassan.hamzeh@hydroone.com | jacky.chiu@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | ACTN EMPP | Executing | Short Term Planning | # circuit structures | 1456311.8897 | 1701131.0883 | 1738826.9687 | 1775731.1728 | 1810939.4906 | 1847158.8759 | 0 | 0 | 0 | 0 | 1456311.8897 | 1701131.0883 | 1738826.9687 | 1775731.1728 | 1810939.4906 | 1847158.8759 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | True | False |  | False | False | False | False | FALSE |  | 0 | 0 | Intermediate (Modified - Tx Decision)
19867 | Overhead Tx Lines - Technical Support - PL | N.T.M.1.20 | 7370 | 206 | TX LINES AND STATIONS | AIP001115A | AIP001115 | AIP001115 | No | AIP001115 | Tx Technical Support 3rd party/E&CS/PL | 0 |  | Overhead Lines | hassan.hamzeh@hydroone.com | jacky.chiu@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | ACTN EMPP | Executing | Short Term Planning | N/A | 209884.0591 | 223755.8985 | 224206.8166 | 223806.914 | 223912.2581 | 224017.1307 | 0 | 0 | 0 | 0 | 209884.0591 | 223755.8985 | 224206.8166 | 223806.914 | 223912.2581 | 224017.1307 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | False |  | False | True | False | False | FALSE |  | 0 | 0 | Intermediate (Modified - Tx Decision)
19868 | Overhead Tx Lines - Technical Support - Kinectrics | N.T.M.1.20 | 4048 | 213 | PLANNING | AIP001115B | AIP001115 | AIP001115 | No | AIP001115 | Tx Technical Support 3rd party/E&CS/PL | 0 |  | Overhead Lines | hassan.hamzeh@hydroone.com | jacky.chiu@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | EMPP AWRD | Executing | Short Term Planning | N/A | 426042.1361 | 628470.7125 | 629614.9353 | 631034.9513 | 631267.2342 | 631462.1306 | 0 | 0 | 0 | 0 | 426042.1361 | 628470.7125 | 629614.9353 | 631034.9513 | 631267.2342 | 631462.1306 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | False |  | False | True | False | False | FALSE |  | 0 | 0 | Intermediate (Modified - Tx Decision)
19869 | Overhead Tx Lines - Corrective Maintenance - E&CS | N.T.M.1.20 | 7370 | 206 | TX LINES AND STATIONS | AIP001110B | AIP001110 | AIP001110 | No | AIP001110 | Tx Corrective Maintenance | 0 |  | Overhead Lines | hassan.hamzeh@hydroone.com | jacky.chiu@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | ACTN EMPP | Executing | Short Term Planning | # circuit structures | 1456311.8897 | 1701131.0883 | 1738826.9687 | 1775731.1728 | 1810939.4906 | 1847158.8759 | 0 | 0 | 0 | 0 | 1456311.8897 | 1701131.0883 | 1738826.9687 | 1775731.1728 | 1810939.4906 | 1847158.8759 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | True | False |  | False | False | False | False | FALSE |  | 0 | 0 | Intermediate (Modified - Tx Decision)
19872 | CSO Regulatory Compliance - Contact Handling | N.D.M.4.01 | 4175 | 202 | CUSTOMER CARE SERVICES | AIP000367 | AIP000367 | AIP000367 | No | AIP000367 | Contact Handling - Regulatory Compliance |  |  | Customer Care Services Dx | Imran.Merali@HydroOne.com | Imran.Merali@HydroOne.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | AWRD EMPP | Executing | Short Term Planning | 202-D502004 | 52956.6273 | 74174.3232 | 55756.5829 | 56996.2067 | 77721.6896 | 0 | 0 | 0 | 0 | 0 | 52956.6273 | 74174.3232 | 55756.5829 | 56996.2067 | 77721.6896 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal: Base Case
19873 | CSO Sustainment | N.D.M.4.01 | 4175 | 202 | CUSTOMER CARE SERVICES | AIP000357 | AIP000357 | AIP000357 | No | AIP000357 | Inergi CSO Contract |  |  | Customer Care Services Dx | Imran.Merali@HydroOne.com | Imran.Merali@HydroOne.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | AWRD EMPP | Executing | Short Term Planning | 202-D500001 | 39114760.2604 | 40073999.3967 | 40781346.7726 | 41492206.8484 | 42057150.0554 | 0 | 0 | 0 | 0 | 0 | 39114760.2604 | 40073999.3967 | 40781346.7726 | 41492206.8484 | 42057150.0554 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal: Base Contract with Voice Recording
19874 | CSO Volume | N.D.M.4.01 | 4175 | 202 | CUSTOMER CARE SERVICES | AIP000358 |  | AIP000358 | Yes | AIP000358 |  |  |  | Customer Care Services Dx | Imran.Merali@HydroOne.com | [6 empty] | Program | EMPP AWRD | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19875 | CSO Service Enhancements - MR & Billing | N.D.M.4.01 | 4175 | 202 | CUSTOMER CARE SERVICES | AIP000354 | AIP000354 | AIP000354 | No | AIP000354 | Billing - Service Enhancements |  |  | Customer Care Services Dx | Imran.Merali@HydroOne.com | Imran.Merali@HydroOne.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | AWRD EMPP | Executing | Short Term Planning | 202-D503003 | 1164838.0911 | 1176654.2565 | 1178806.9941 | 1181390.9572 | 1179805.2919 | 0 | 0 | 0 | 0 | 0 | 1164838.0911 | 1176654.2565 | 1178806.9941 | 1181390.9572 | 1179805.2919 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal: Initiatives
19876 | CSO Service Enhancements - Collections | N.D.M.4.01 | 4175 | 202 | CUSTOMER CARE SERVICES | AIP000368 | AIP000368 | AIP000368 | No | AIP000368 | Collections - Service Enhancements |  |  | Customer Care Services Dx | Imran.Merali@HydroOne.com | Imran.Merali@HydroOne.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | AWRD EMPP | Executing | Short Term Planning | 202- | 48534.9124 | 49027.2607 | 49116.9532 | 49224.6232 | 49158.5604 | 0 | 0 | 0 | 0 | 0 | 48534.9124 | 49027.2607 | 49116.9532 | 49224.6232 | 49158.5604 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal: Base Case
19880 | Settlements Sustainment | N.D.M.4.01 | 4175 | 202 | CUSTOMER CARE SERVICES | AIP000356 | AIP000356 | AIP000356 | No | AIP000356 | Inergi Settlements Contract Dx |  |  | Customer Care Services Dx | Imran.Merali@HydroOne.com | Imran.Merali@HydroOne.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | AWRD EMPP | Executing | Short Term Planning | 202-D501002 | 3965219.8314 | 4114123.5613 | 4519714.5258 | 4603805.7386 | 4671711.0313 | 0 | 0 | 0 | 0 | 0 | 3965219.8314 | 4114123.5613 | 4519714.5258 | 4603805.7386 | 4671711.0313 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal: Base Contract - Modified
19881 | Settlements Sustainment | N.T.M.4.50 | 4175 | 202 | CUSTOMER CARE SERVICES | AIP001191 | AIP001191 | AIP001191 | No | AIP001191 | Inergi Settlements Contract Tx | 0 |  | Customer Care Services Tx | Imran.Merali@HydroOne.com | Imran.Merali@HydroOne.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | EMPP AWRD | Executing | Short Term Planning | 202-T501002 | 447342.2659 | 460989.2153 | 506797.2651 | 517030.6243 | 526633.2829 | 536593.3836 | 0 | 0 | 0 | 0 | 447342.2659 | 460989.2153 | 506797.2651 | 517030.6243 | 526633.2829 | 536593.3836 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | True | Inergi Contract to handle Tx Settlements | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Asset Optimal: Base Contract - Modified
19902 | Barwick TS: Build a new 115-44 kV TS | N.T.C.2.11 | 7700 | 203 | PROJECT DELIVERY | AIP000763 |  | AIP000763 | Yes | AIP000763 |  |  |  | Load Customer Connection | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19903 | FMP and Drawing Demerger | N.T.M.1.14 | 7716 | 224 | ENGINEERING | AIP001032 | AIP001032 | AIP001032 | No | AIP001032 | FMP and Drawing Demerger | 0 |  | Engineering and Environmental Support | Mike.Tanaskovic@HydroOne.com | Farinaz.Yousefi@HydroOne.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | ACCP EMPP | Executing | Short Term Planning | # of drawings | 247124.2089 | 495639.3632 | 496541.8098 | 497661.6336 | 497844.8304 | 497998.4629 | 500000 | 331224.36 | 331224.36 | 331224.24 | 247124.2089 | 495639.3632 | 496541.8098 | 497661.6336 | 497844.8304 | 497998.4629 | 500000 | 331224.36 | 331224.36 | 331224.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Intermediate (Modified - Tx Decision)
19906 | R&D Program- External | N.T.M.2.21 | 4230 | 213 | PLANNING | AIP001168 |  | AIP001168 | Yes | AIP001168 |  |  |  | Technology Program | Daila.Dzintars@HydroOne.com | [6 empty] | Program | init EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19908 | Field Switching - Lines | N.T.M.3.01 | 7370 | 206 | TX LINES AND STATIONS | AIP005026 | AIP005026 | AIP005026 | No | AIP005026 | Operating Field Switching - Lines | 0 |  | Operations Contract | Godfrey.Holder@HydroOne.com | emily.booth@hydroone.com | System O&M | N/A | 0 | 03 - None (default) | 0 | Program | ACTN EMPP | Executing | Short Term Planning | # of Incidents | 1025881.8965 | 1050382.4928 | 1076976.0847 | 1087623.0732 | 1099919.8641 | 1124015.7788 | 0 | 0 | 0 | 0 | 1025881.8965 | 1050382.4928 | 1076976.0847 | 1087623.0732 | 1099919.8641 | 1124015.7788 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1175 | 1175 | 1200 | 1208 | 1220 | 1220 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | True | False |  | False | False | False | False | FALSE |  | 0 | 0 | Asset Optimal Modified
19914 | Transformer Station ACA | N.T.M.1.16 | 7370 | 206 | TX LINES AND STATIONS | AIP001053B | AIP001053 | AIP001053 | No | AIP001053 | Other Mtce - Power Equipment - Asset Condition Assessments | 0 |  | Power Equipment | Mike.Tanaskovic@HydroOne.com | Harshal.Bhatt@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | ACTN EMPP | Executing | Short Term Planning | Retainer | 239169.8963 | 242653.9325 | 248077.9763 | 253770.2009 | 259034.4544 | 264406.0322 | 0 | 0 | 0 | 0 | 239169.8963 | 242653.9325 | 248077.9763 | 253770.2009 | 259034.4544 | 264406.0322 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Intermediate
19917 | Physical Security | N.T.C.1.29 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | NERC Cyber Security Compliance Readiness | lincoln.frost-hunt@hydroone.com | [6 empty] | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19919 | 2010 System Management | N.T.C.1.29 | 4032 | 212 | INFO SOLUTIONS DIVISION | UNPLND |  |  | Yes |  |  |  |  | NERC Cyber Security Compliance Readiness | lincoln.frost-hunt@hydroone.com | [6 empty] | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19920 | Tilbury TS-M1-ID 1477-Tilbury Solar 2 | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000199 |  | AIP000199 | Yes | AIP000199 | Large Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19927 | East-West Tie Connection | N.T.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000743 | AIP000743 | AIP000743 | No | AIP000743 | East-West Tie Connection | SS-03 | East-West Tie Connection | Network Transfer Capability | Robert.Reinmuller@HydroOne.com | Hamid.Hamadanizadeh@HydroOne.com | System Service | Northern | Not Required | 02 - Expectation (no agreement) | Not Required | Project | LLTM ACTN | Short Term Planning | Short Term Planning |  | 10558341.6803 | 39153474.3376 | 34006118.9184 | 48213715.9443 | 11543972.6966 | 0 | 0 | 0 | 0 | 0 | 10558341.6803 | 39153474.3376 | 34006118.9184 | 48213715.9443 | 11543972.6966 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43281 | 44530 | True | NextBridge line needs to be connected to the grid | False |  | False | Government has issued OiC for the project | False | False |  | True | False | False | False | FALSE |  | 0 | 0 | Alternative 1
19928 | DS Spill Containment Program | N.D.C.1.08 | 7700 | 203 | PROJECT DELIVERY | AIP000164 | AIP000164 | AIP000164 | No | AIP000164 | Spill Containment Program |  |  | Distributing & Regulating Stations | emre.aydin@HydroOne.com | Trevor.Beausoleil@HydroOne.com | System Renewal | N/A | 0 | 03 - None (default) | 0 | Program | EMPP ACTN | Executing | Short Term Planning | # of Transformers | 601179.97 | 613249.9522 | 625974.5014 | 638851.4137 | 651606.918 | 0 | 0 | 0 | 0 | 0 | 601179.97 | 613249.9522 | 625974.5014 | 638851.4137 | 651606.918 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Vulnerable
19930 | Field Special Investigations | N.D.M.4.01 | 7374 | 205 | LINES | AIP000362 | AIP000362 | AIP000362 | No | AIP000362 | Provincial Lines - Special Investigations |  |  | Customer Care Services Dx | Imran.Merali@HydroOne.com | Imran.Merali@HydroOne.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | ACCP EMPP | Executing | Short Term Planning | # of Occurances | 2091669.3587 | 1939851.779 | 1799519.425 | 1586172.9098 | 1357658.1711 | 0 | 0 | 0 | 0 | 0 | 2091669.3587 | 1939851.779 | 1799519.425 | 1586172.9098 | 1357658.1711 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Vulnerable: Base Case - M2M Savings
19931 | Substandard Clearance Correction Program - L&FS | N.T.C.1.12 | 7370 | 206 | TX LINES AND STATIONS | AIP000455 | AIP000455 | AIP000455 | No | AIP000455 | Tx Lines Substandard Electrical Clearance Corrections | 0 |  | Overhead Lines Component Refurb & Repl | hassan.hamzeh@hydroone.com | Deniz.Turkben@HydroOne.com | System Renewal | 0 | 0 | 03 - None (default) | 0 | Program | EMPP ACTN | Executing | Short Term Planning | # of line segments mitigated | 976576.2732 | 992746.7884 | 1004219.8022 | 1011998.232 | 1019687.7813 | 1031152.3146 | 0 | 0 | 0 | 0 | 1109745.765 | 1128121.3505 | 1141158.8661 | 1149997.9909 | 1158736.1151 | 1171763.9938 | 0 | 0 | 0 | 0 | -133169.4918 | -135374.5621 | -136939.0639 | -137999.7589 | -139048.3338 | -140611.6793 | 0 | 0 | 0 | 0 | -12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Vulnerable
19936 | Meter Reading - Prov. Lines | N.D.M.4.01 | 7374 | 205 | LINES | AIP000359 | AIP000359 | AIP000359 | No | AIP000359 | Provincial Lines - Meter Reading |  |  | Customer Care Services Dx | Imran.Merali@HydroOne.com | Imran.Merali@HydroOne.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | AWRD EMPP | Executing | Short Term Planning | # of Reads | 7624707.8827 | 7371752.5861 | 7053131.8324 | 6929116.836 | 6562187.178 | 0 | 0 | 0 | 0 | 0 | 7624707.8827 | 7371752.5861 | 7053131.8324 | 6929116.836 | 6562187.178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Vulnerable: Status Quo - Modified - M2M Savings
19940 | CSO Service Support - 3rd Party - Contact Handling | N.D.M.4.01 | 4175 | 202 | CUSTOMER CARE SERVICES | AIP000375 | AIP000375 | AIP000375 | No | AIP000375 | Contact Handling - Third Party Support |  |  | Customer Care Services Dx | Imran.Merali@HydroOne.com | Imran.Merali@HydroOne.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | EMPP AWRD | Executing | Short Term Planning | 202-D504004 | 977711.6588 | 1423191.7591 | 1300698.3364 | 1314911.7631 | 1407441.0452 | 0 | 0 | 0 | 0 | 0 | 977711.6588 | 1423191.7591 | 1300698.3364 | 1314911.7631 | 1407441.0452 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Intermediate: Base Case
19941 | CSO Service Support - 3rd Party - MR & Billing | N.D.M.4.01 | 4175 | 202 | CUSTOMER CARE SERVICES | AIP000373 | AIP000373 | AIP000373 | No | AIP000373 | Billing - Third Party Support |  |  | Customer Care Services Dx | Imran.Merali@HydroOne.com | Imran.Merali@HydroOne.com | System O&M | N/A | 0 | 02 - Expectation (no agreement) | 0 | Program | AWRD EMPP | Executing | Short Term Planning | 202-D504003 | 11578800.571 | 11410983.5551 | 11325185.7134 | 11009728.5462 | 10878937.1931 | 0 | 0 | 0 | 0 | 0 | 11578800.571 | 11410983.5551 | 11325185.7134 | 11009728.5462 | 10878937.1931 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal: eBilling & OEB Monthly billing
19942 | CSO Service Support - 3rd Party - Collections | N.D.M.4.01 | 4175 | 202 | CUSTOMER CARE SERVICES | AIP000374 | AIP000374 | AIP000374 | No | AIP000374 | Collections - Third Party Support |  |  | Customer Care Services Dx | Imran.Merali@HydroOne.com | Imran.Merali@HydroOne.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | AWRD EMPP | Executing | Short Term Planning | 202-D504006 | 448781.0182 | 450760.557 | 445203.0578 | 442144.4261 | 438746.0504 | 0 | 0 | 0 | 0 | 0 | 448781.0182 | 450760.557 | 445203.0578 | 442144.4261 | 438746.0504 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Vulnerable: Base Case
19944 | IESO Meter Data Validation - Stations | N.T.M.4.50 | 4175 | 202 | CUSTOMER CARE SERVICES | AIP001192 |  | AIP001192 | Yes | AIP001192 | IESO Meter Data Validation Tx |  |  | Customer Care Services Tx | Imran.Merali@HydroOne.com | Imran.Merali@HydroOne.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | init EMPP | Executing | Short Term Planning | # Validations | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19946 | St Isidore TS: Add 44 kV Feeder breaker | N.T.C.2.11 | 7700 | 203 | PROJECT DELIVERY | AIP000814 |  | AIP000814 | Yes | AIP000814 |  |  |  | Load Customer Connection | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19947 | Chesterville TS -Add 44kV Feeder | N.T.C.2.11 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Load Customer Connection | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19948 | Ottawa Area- Build Orleans TS | N.T.C.2.11 | 7700 | 203 | PROJECT DELIVERY | AIP000811 |  | AIP000811 | Yes | AIP000811 |  |  |  | Load Customer Connection | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19952 | Cedar Mills DS F2 conversion- Demand PQ Work | N.D.C.2.02 | 7374 | 205 | LINES | UNPLND |  |  | Yes |  |  |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | [6 empty] | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19967 | Dx Smart Grid Miscellaneous studies | N.D.M.2.22 | 4230 | 213 | PLANNING | UNPLND |  |  | Yes | [12 empty] | Program | EMPP AWRD | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19968 | MSP Support | N.T.M.1.17 | 7370 | 206 | TX LINES AND STATIONS | AIP001078 |  | AIP001078 | Yes | AIP001078 |  |  |  | Protection Control & Metering Equipment | Miroslav.Kostic@HydroOne.com | [6 empty] | Program | ACTN EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19975 | Meter Reading Ancilliary Services | N.D.M.4.01 | 7374 | 205 | LINES | AIP000360 | AIP000360 | AIP000360 | No | AIP000360 | Provincial Lines - Meter Reading Ancillary |  |  | Customer Care Services Dx | Imran.Merali@HydroOne.com | Imran.Merali@HydroOne.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | EMPP AWRD | Executing | Short Term Planning | Retainer | 844000.7708 | 867519.7281 | 884091.4044 | 912609.747 | 938725.97 | 0 | 0 | 0 | 0 | 0 | 844000.7708 | 867519.7281 | 884091.4044 | 912609.747 | 938725.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Vulnerable: Status Quo
19979 | Other, EI, Data Collection | N.D.C.2.01 | 7374 | 205 | LINES | AIP000178 | AIP000178 | AIP000178 | No | AIP000178 | New Connections - Other | ISD-SA-04 | New Load Connections, Upgrades, Cancellations and Metering | New Load Connection Upg/Cancel/Meters | emre.aydin@HydroOne.com | michael.sullivan@hydroone.com | System Access | N/A | 0 | 03 - None (default) | 0 | Program | INSC EMPP | Executing | Short Term Planning | # of Connects | 10826080.4929 | 11041355.9446 | 11269643.9069 | 11501908.9485 | 11731243.3329 | 0 | 0 | 0 | 0 | 0 | 13300172.3213 | 13564917.0325 | 13843751.5338 | 14127568.087 | 14409408.6203 | 0 | 0 | 0 | 0 | 0 | -109354.3484 | -111528.8479 | -113834.7869 | -116180.8985 | -118497.4074 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | -2364737.48 | -2412032.24 | -2460272.84 | -2509478.24 | -2559667.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Demand
19988 | Component Replacement - Regulators/Reclosers | N.D.C.1.07 | 7374 | 205 | LINES | AIP000142 | AIP000142 | AIP000142 | No | AIP000142 | Component Replacement - Regulators/Reclosers | ISD-SR-10 | Distribution Lines Planned Component Replacement Program | Lines | emre.aydin@HydroOne.com | joseph.parete@hydroone.com | System Renewal | 0 | 0 | 03 - None (default) | 0 | Program | ACCP EMPP | Executing | Short Term Planning | # of regulators/recl | 4520872.8124 | 1291912.9124 | 1317737.4376 | 1344844.7191 | 1370674.3242 | 0 | 0 | 0 | 0 | 0 | 5137355.4687 | 1468082.855 | 1497428.9063 | 1528232.6353 | 1557584.4594 | 0 | 0 | 0 | 0 | 0 | -616482.6562 | -176169.9426 | -179691.4688 | -183387.9162 | -186910.1351 | 0 | 0 | 0 | 0 | 0 | -12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250 | 250 | 250 | 250 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Vulnerable
19994 | 2010 Budget N.T.C.1.28 | N.T.C.1.28 | 1142 | 215 | FACILITIES & REAL ESTATE | UNPLND |  |  | Yes |  |  |  |  | Transmission Site Facilities | cindy.copp@hydroone.com | [6 empty] | Project | AWRD | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19998 | Belleville TS: Replace Neutral Reactors | N.T.C.2.21 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Major Risk Mitigation | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20013 | To be Closed - Misc Eng & Environmental Support | N.D.M.1.07 | 7716 | 224 | ENGINEERING | AIP000273 | AIP000273 | AIP000273 | No | AIP000273 | Misc Engineering & Environmental Support |  |  | Other Services | emre.aydin@HydroOne.com | patrick.howe@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | init EMPP | Executing | Short Term Planning | Retainer | 49457.1145 | 50958.0327 | 52072.222 | 53230.1293 | 54221.8134 | 0 | 0 | 0 | 0 | 0 | 49457.1145 | 50958.0327 | 52072.222 | 53230.1293 | 54221.8134 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Demand
20015 | IED Data Extraction - Distance to Fault | N.T.C.3.08 | 4514 | 212 | INFO SOLUTIONS DIVISION | AIP000981 |  | AIP000981 | Yes | AIP000981 |  |  |  | Integrating Operating Infrastructure | Miroslav.Kostic@HydroOne.com | [6 empty] | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20025 | Large Project | N.D.C.2.01 | 7374 | 205 | LINES | AIP000177B | AIP000177 | AIP000177 | No | AIP000177 | New Connections |  |  | New Load Connection Upg/Cancel/Meters | emre.aydin@HydroOne.com | michael.sullivan@hydroone.com | System Access | N/A | 0 | 03 - None (default) | 0 | Program | AWRD EMPP | Executing | Short Term Planning | # of Connects | 1091649.0605 | 1112654.575 | 1135860.5818 | 1159365.1809 | 1182672.4349 | 0 | 0 | 0 | 0 | 0 | 4678384.5787 | 4771116.3901 | 4867501.201 | 4965646.5803 | 5065080.7411 | 0 | 0 | 0 | 0 | 0 | -11026.7582 | -11238.9351 | -11473.3392 | -11710.7594 | -11946.1862 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | -3575708.76 | -3647222.88 | -3720167.28 | -3794570.64 | -3870462.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Demand
20026 | Customer Upgrade | N.D.C.2.01 | 7374 | 205 | LINES | AIP000181A | AIP000181 | AIP000181 | No | AIP000181 | Service Upgrades |  |  | New Load Connection Upg/Cancel/Meters | emre.aydin@HydroOne.com | michael.sullivan@hydroone.com | System Access | N/A | 0 | 03 - None (default) | 0 | Program | INSC EMPP | Executing | Short Term Planning | # of Upgrades | 17491811.5982 | 18013111.2289 | 18570189.4898 | 19140479.8793 | 19714788.4034 | 0 | 0 | 0 | 0 | 0 | 27090961.1143 | 27896140.0583 | 28750582.1766 | 29625923.3574 | 30512144.6802 | 0 | 0 | 0 | 0 | 0 | -2385247.0361 | -2456333.3494 | -2532298.5668 | -2610065.4381 | -2688380.2368 | 0 | 0 | 0 | 0 | 0 | -12 | 12 | -7213902.48 | -7426695.48 | -7648094.12 | -7875378.04 | -8108976.04 | 0 | 0 | 0 | 0 | 0 | 4469 | 4511 | 4554 | 4597 | 4641 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Demand
20027 | Upgrade - Other | N.D.C.2.01 | 7374 | 205 | LINES | AIP000182 | AIP000182 | AIP000182 | No | AIP000182 | Service Upgrades - Other | ISD-SA-04 | New Load Connections, Upgrades, Cancellations and Metering | New Load Connection Upg/Cancel/Meters | emre.aydin@HydroOne.com | michael.sullivan@hydroone.com | System Access | N/A | 0 | 03 - None (default) | 0 | Program | EMPP INSC | Executing | Short Term Planning | # of Upgrades | 3483312.0276 | 3553370.1679 | 3626395.216 | 3701240.9165 | 3774559.3459 | 0 | 0 | 0 | 0 | 0 | 4824748.0823 | 4921688.3253 | 5022346.7346 | 5125427.547 | 5227133.384 | 0 | 0 | 0 | 0 | 0 | -474997.0947 | -484550.4774 | -494508.4386 | -504714.6704 | -514712.6381 | 0 | 0 | 0 | 0 | 0 | -12 | 12 | -866438.96 | -883767.68 | -901443.08 | -919471.96 | -937861.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Demand
20028 | Upgrade - Large Project | N.D.C.2.01 | 7374 | 205 | LINES | AIP000181B | AIP000181 | AIP000181 | No | AIP000181 | Service Upgrades |  |  | New Load Connection Upg/Cancel/Meters | emre.aydin@HydroOne.com | michael.sullivan@hydroone.com | System Access | N/A | 0 | 03 - None (default) | 0 | Program | AWRD EMPP | Executing | Short Term Planning | # of Upgrades | 351293.7652 | 358346.7646 | 365782.2721 | 373306.7848 | 380760.4522 | 0 | 0 | 0 | 0 | 0 | 538487.1404 | 549287.7125 | 560578.6329 | 572027.5754 | 583453.972 | 0 | 0 | 0 | 0 | 0 | -47903.6953 | -48865.4679 | -49879.4007 | -50905.4706 | -51921.8798 | 0 | 0 | 0 | 0 | 0 | -12 | 12 | -139289.68 | -142075.48 | -144916.96 | -147815.32 | -150771.64 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Demand
20029 | Service Cancellations | N.D.C.2.01 | 7374 | 205 | LINES | AIP000180 | AIP000180 | AIP000180 | No | AIP000180 | Service Cancellations | ISD-SA-04 | New Load Connections, Upgrades, Cancellations and Metering | New Load Connection Upg/Cancel/Meters | emre.aydin@HydroOne.com | michael.sullivan@hydroone.com | System Access | N/A | 0 | 03 - None (default) | 0 | Program | INSC EMPP | Executing | Short Term Planning | # of Cancellations | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5476225.08 | 5639164.2 | 5808712.48 | 5985005.44 | 6163970.52 | 0 | 0 | 0 | 0 | 0 | -5476225.08 | -5639164.2 | -5808712.48 | -5985005.44 | -6163970.52 | 0 | 0 | 0 | 0 | 0 | -100 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5562 | 5614 | 5668 | 5722 | 5776 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Demand
20035 | Single Line Diagram & SSLA Support – E&PD | N.D.M.4.01 | 7716 | 224 | ENGINEERING | AIP000371 | AIP000371 | AIP000371 | No | AIP000371 | Single Line Diagrams |  |  | Customer Care Services Dx | Imran.Merali@HydroOne.com | Imran.Merali@HydroOne.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | EMPP ACCP | Executing | Short Term Planning | # of drawings | 40396.4618 | 41622.1832 | 42532.3344 | 43478.1407 | 44288.0089 | 0 | 0 | 0 | 0 | 0 | 40396.4618 | 41622.1832 | 42532.3344 | 43478.1407 | 44288.0089 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Vulnerable: Base Case
20036 | IESO Meter Data Validation - Stations | N.D.M.4.01 | 4337 | 223 | SMART METERS | AIP000364B |  | AIP000364 | Yes | AIP000364 | IESO Meter Data Validation Dx |  |  | Customer Care Services Dx | Imran.Merali@HydroOne.com | Imran.Merali@HydroOne.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | AWRD EMPP | Executing | Short Term Planning | # Validations | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20040 | Funds Transferred from DC203 | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20045 | Tx Wood Pole Replacement Program - L&FS | N.T.C.1.12 | 7370 | 206 | TX LINES AND STATIONS | AIP000474A | AIP000474 | AIP000474 | No | AIP000474 | Wood Pole Structure Replacements | SR-21 | Wood Pole Structure Replacements | Overhead Lines Component Refurb & Repl | hassan.hamzeh@hydroone.com | TeodorConstantin.Culinescu@HydroOne.com | System Renewal | 0 | 0 | 03 - None (default) | 0 | Program | AWRD EMPP | Executing | Short Term Planning | # of Structures | 17007763.863 | 17249536.3559 | 17441535.5015 | 17525395.2512 | 17638972.8272 | 17832329.4448 | 0 | 0 | 0 | 0 | 19327004.3897 | 19601745.859 | 19819926.7063 | 19915221.8764 | 20044287.3036 | 20264010.7328 | 0 | 0 | 0 | 0 | -2319240.5268 | -2352209.5031 | -2378391.2048 | -2389826.6252 | -2405314.4764 | -2431681.2879 | 0 | 0 | 0 | 0 | -12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 425 | 425 | 425 | 425 | 425 | 425 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Vulnerable
20047 | Ongoing Maintenance support | N.D.M.2.50 | 1144 | 220 | STRATEGY & CONSERV | AIP000343 |  | AIP000343 | Yes | AIP000343 |  |  |  | Conservation and Demand Management | Imran.Merali@HydroOne.com | [6 empty] | Program | AWRD EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20049 | DX Leased Circuits | N.D.M.1.09 | 4048 | 213 | PLANNING | AIP000280 | AIP000280 | AIP000280 | No | AIP000280 | DX Leased Circuits |  |  | Telecom Monitoring and Control | Peter.Mitskos@HydroOne.com | Dominic.Consorti@HydroOne.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | AWRD EMPP | Executing | Short Term Planning | Retainer | 4156483.7291 | 4361869.174 | 4539321.4241 | 4726395.4491 | 4903335.5496 | 0 | 0 | 0 | 0 | 0 | 4156483.7291 | 4361869.174 | 4539321.4241 | 4726395.4491 | 4903335.5496 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
20062 | CGE Ellesmere TS T3 & T4 Replace EOL Transformer | N.T.C.1.17 | 7700 | 203 | PROJECT DELIVERY | 14.4 |  |  | Yes |  |  |  |  | Power Transformers | James.Mardegan@HydroOne.com | [6 empty] | Program | ACCP EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20064 | Meter Conversions and Efficiency Improvements | N.D.C.1.09 | 7374 | 205 | LINES | AIP000172B | AIP000172 | AIP000172 | No | AIP000172 | Revenue Meter Upgrades |  |  | Metering | Peter.Mitskos@HydroOne.com | Dominic.Consorti@HydroOne.com | System Access | 0 | 0 | 03 - None (default) | 0 | Program | ACCP EMPP | Executing | Short Term Planning | # of meters | 301024.6163 | 307068.2879 | 313439.7024 | 319887.5117 | 326274.5686 | 0 | 0 | 0 | 0 | 0 | 313567.2736 | 319862.7949 | 326499.7034 | 333216.1931 | 339869.3022 | 0 | 0 | 0 | 0 | 0 | -12542.6573 | -12794.507 | -13060.001 | -13328.6814 | -13594.7336 | 0 | 0 | 0 | 0 | 0 | -4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 137 | 137 | 137 | 137 | 137 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Demand - Modified - M2M Savings
20073 | Wholesale to Retail Standard (New meter w TCP/IP) | N.D.C.1.09 | 7370 | 206 | TX LINES AND STATIONS | AIP000168 |  | AIP000168 | Yes | AIP000168 | DS Meters - Wholesale to Retail Standard |  |  | Metering | Peter.Mitskos@HydroOne.com | Dominic.Consorti@HydroOne.com | System Access | 0 | 0 | 03 - None (default) | 0 | Program | ACTN EMPP | Executing | Short Term Planning | Assumption - # of Meter installation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20074 | Transformer/OCB/Component Refurbishment Program | N.T.M.1.16 | 7370 | 206 | TX LINES AND STATIONS | AIP001065 | AIP001065 | AIP001065 | No | AIP001065 | Other Mtce - System Reserve Equipment - Refurbishment | 0 |  | Power Equipment | Mike.Tanaskovic@HydroOne.com | peter.zhao@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | EMPP ACTN | Executing | Short Term Planning | # of Refurbishments | 630024.9974 | 636272.6855 | 657153.7726 | 668697.0875 | 678836.6051 | 698809.2081 | 0 | 0 | 0 | 0 | 630024.9974 | 636272.6855 | 657153.7726 | 668697.0875 | 678836.6051 | 698809.2081 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Intermediate (Modified - Tx Decision)
20075 | Milton TS and 230kV Lines | N.T.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000718 | AIP000718 | AIP000718 | No | AIP000718 | Milton Transformer Station and 230kV Lines | SS-06 | Milton SS: Station Expansion and Connect 230kV Circuits | Network Transfer Capability | Robert.Reinmuller@HydroOne.com | Gene.Ng@HydroOne.com | System Service | Greater Toronto Area | Required | 03 - None (default) | Required | Project | init | Short Term Planning | Short Term Planning |  | 0 | 983755.5973 | 4881728.2398 | 961581.8896 | 68634684.9013 | 113652946.4448 | 40000000 | 0 | 0 | 0 | 0 | 983755.5973 | 4881728.2398 | 961581.8896 | 68634684.9013 | 113652946.4448 | 40000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44530 | 45443 | False |  | True | IESO Ontario Resource and Transmission Assessment Criteria | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Alternative 1
20076 | 2010 L7S Wood Structure Replacement | N.T.C.2.20 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Performance Enhancement | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | ACTN BEST | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20099 | Component Replacement - Crossarms | N.D.C.1.07 | 7374 | 205 | LINES | AIP000139 | AIP000139 | AIP000139 | No | AIP000139 | Component Replacement - Crossarms | ISD-SR-10 | Distribution Lines Planned Component Replacement Program | Lines | emre.aydin@HydroOne.com | joseph.parete@hydroone.com | System Renewal | 0 | 0 | 03 - None (default) | 0 | Program | EMPP ACCP | Executing | Short Term Planning | # of crossarms | 1433258.1583 | 1460179.4959 | 1489531.0665 | 1519206.4665 | 1548554.4826 | 0 | 0 | 0 | 0 | 0 | 1643644.6769 | 1674517.7706 | 1708177.8285 | 1742209.2506 | 1775865.2324 | 0 | 0 | 0 | 0 | 0 | -210386.5186 | -214338.2746 | -218646.7621 | -223002.7841 | -227310.7497 | 0 | 0 | 0 | 0 | 0 | -12.8 | 12.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 1000 | 1000 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Vulnerable
20112 | Clarington TS: New 500/230kV station | N.T.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000723 | AIP000723 | AIP000723 | No | AIP000723 | Clarington TS: New 500/230kV station | 0 |  | Network Transfer Capability | Robert.Reinmuller@HydroOne.com | Jean.Morneau@HydroOne.com | System Service | 0 | 0 | 03 - None (default) | In Progress | Project | EMPP ACCP | Executing | Executing |  | 21759488.2626 | 0.99102 | 0.23588 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22000702.338 | 0.99102 | 0.23588 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -241214.0755 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1.0964 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43215 | [13 empty] | FALSE |  | 0 | 0 | Alternative 1
20118 | Tx Lines Foundation Assess/Clean/Coat-PL | N.T.C.1.12 | 7370 | 206 | TX LINES AND STATIONS | AIP000472B | AIP000472 | AIP000472 | No | AIP000472 | Tower Foundations | SR-23 | Tower Foundation Assess/Clean/Coat Program | Overhead Lines Component Refurb & Repl | hassan.hamzeh@hydroone.com | TeodorConstantin.Culinescu@HydroOne.com | System Renewal | 0 | 0 | 03 - None (default) | 0 | Program | ACTN EMPP | Executing | Short Term Planning | Number of structures | 7674182.1627 | 7273356.3654 | 7357413.6067 | 7414401.7268 | 7470739.5148 | 7554733.7828 | 0 | 0 | 0 | 0 | 8720661.5486 | 8265177.6879 | 8360697.2803 | 8425456.5077 | 8489476.7214 | 8584924.7532 | 0 | 0 | 0 | 0 | -1046479.3858 | -991821.3226 | -1003283.6736 | -1011054.7809 | -1018737.2066 | -1030190.9704 | 0 | 0 | 0 | 0 | -12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800 | 750 | 750 | 750 | 750 | 750 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Vulnerable (Tx Decision)
20120 | Component Replacement - Nest Platforms | N.D.C.1.07 | 7374 | 205 | LINES | AIP000140 | AIP000140 | AIP000140 | No | AIP000140 | Component Replacement - Nest Platforms | ISD-SR-10 | Distribution Lines Planned Component Replacement Program | Lines | emre.aydin@HydroOne.com | joseph.parete@hydroone.com | System Renewal | 0 | 0 | 03 - None (default) | 0 | Program | EMPP ACTN | Executing | Short Term Planning | # of incidents | 129301.3048 | 131897.3227 | 134634.0535 | 137143.9265 | 139882.1283 | 0 | 0 | 0 | 0 | 0 | 148281.3129 | 151258.3975 | 154396.8504 | 157275.1451 | 160415.2848 | 0 | 0 | 0 | 0 | 0 | -18980.008 | -19361.0749 | -19762.7968 | -20131.2186 | -20533.1565 | 0 | 0 | 0 | 0 | 0 | -12.8 | 12.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 15 | 15 | 15 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
20121 | Component Replacement - Transformers | N.D.C.1.07 | 7374 | 205 | LINES | AIP000145 | AIP000145 | AIP000145 | No | AIP000145 | Component Replacement - Transformers | ISD-SR-10 | Distribution Lines Planned Component Replacement Program | Lines | emre.aydin@HydroOne.com | joseph.parete@hydroone.com | System Renewal | 0 | 0 | 03 - None (default) | 0 | Program | ACTN EMPP | Executing | Short Term Planning | # of Transformers | 759432.5941 | 774679.8139 | 790753.9068 | 806045.8862 | 822139.6508 | 0 | 0 | 0 | 0 | 0 | 862991.5842 | 880317.9703 | 898583.985 | 915961.2343 | 934249.6031 | 0 | 0 | 0 | 0 | 0 | -103558.9901 | -105638.1564 | -107830.0782 | -109915.3481 | -112109.9524 | 0 | 0 | 0 | 0 | 0 | -12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 30 | 30 | 30 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Vulnerable
20122 | Abandoned Line Removal | N.D.C.1.07 | 7374 | 205 | LINES | AIP000150 | AIP000150 | AIP000150 | No | AIP000150 | Idle Line Removal |  |  | Lines | emre.aydin@HydroOne.com | joseph.parete@hydroone.com | System Renewal | 0 | 0 | 03 - None (default) | 0 | Program | ACTN EMPP | Executing | Short Term Planning | # of projects | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1620588.96 | 1653000.72 | 1686061.27 | 1719782.48 | 1754178.08 | 0 | 0 | 0 | 0 | 0 | -1620588.96 | -1653000.72 | -1686061.27 | -1719782.48 | -1754178.08 | 0 | 0 | 0 | 0 | 0 | -100 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
20123 | Component Replacement - Sentinel Lights | N.D.C.1.07 | 7374 | 205 | LINES | AIP000143 | AIP000143 | AIP000143 | No | AIP000143 | Component Replacement - Sentinel Lights | ISD-SR-10 | Distribution Lines Planned Component Replacement Program | Lines | emre.aydin@HydroOne.com | joseph.parete@hydroone.com | System Renewal | 0 | 0 | 03 - None (default) | 0 | Program | ACTN EMPP | Executing | Short Term Planning | # of lights | 474505.148 | 482968.6177 | 492989.9155 | 501729.6554 | 511747.4382 | 0 | 0 | 0 | 0 | 0 | 1512319.8581 | 1541619.5876 | 1573607.2365 | 1604870.3795 | 1636913.9576 | 0 | 0 | 0 | 0 | 0 | -1037814.7101 | -1058650.97 | -1080617.3211 | -1103140.7241 | -1125166.5194 | 0 | 0 | 0 | 0 | 0 | -68.6893 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400 | 1400 | 1400 | 1400 | 1400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Demand
20124 | Conductor Replacement - Submarine | N.D.C.1.07 | 7374 | 205 | LINES | AIP000147 | AIP000147 | AIP000147 | No | AIP000147 | Conductor Replacement - Submarine | ISD-SR-11 | Submarine Cable Replacement Program | Lines | emre.aydin@HydroOne.com | joseph.parete@hydroone.com | System Renewal | 0 | 0 | 03 - None (default) | 0 | Program | EMPP ACTN | Executing | Short Term Planning | # of incidents | 7517360.3452 | 7667969.9256 | 7827022.6146 | 7988209.176 | 8147193.5302 | 0 | 0 | 0 | 0 | 0 | 8542454.9378 | 8713602.1881 | 8894343.8802 | 9077510.4273 | 9258174.4661 | 0 | 0 | 0 | 0 | 0 | -1025094.5925 | -1045632.2626 | -1067321.2656 | -1089301.2513 | -1110980.9359 | 0 | 0 | 0 | 0 | 0 | -12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Critical Spend Plan
20125 | Component Replacement - Switches | N.D.C.1.07 | 7374 | 205 | LINES | AIP000144 | AIP000144 | AIP000144 | No | AIP000144 | Component Replacement - Switches | ISD-SR-10 | Distribution Lines Planned Component Replacement Program | Lines | emre.aydin@HydroOne.com | joseph.parete@hydroone.com | System Renewal | 0 | 0 | 03 - None (default) | 0 | Program | EMPP AWRD | Executing | Short Term Planning | # of switches | 1260576.3121 | 1284957.966 | 1311619.9843 | 1337635.7534 | 1112161.5296 | 0 | 0 | 0 | 0 | 0 | 1445615.0368 | 1473575.6491 | 1504151.3581 | 1533985.9557 | 1275414.5982 | 0 | 0 | 0 | 0 | 0 | -185038.7247 | -188617.6831 | -192531.3738 | -196350.2023 | -163253.0686 | 0 | 0 | 0 | 0 | 0 | -12.8 | 12.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 30 | 30 | 30 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Vulnerable
20131 | Connect the Samsung Chatham Tx Project | N.T.C.2.12 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Generator Customer Connection | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20132 | Connect the Samsung Nanticoke Tx Project | N.T.C.2.12 | 7700 | 203 | PROJECT DELIVERY | AIP000863 |  | AIP000863 | Yes | AIP000863 |  |  |  | Generator Customer Connection | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20133 | Uxbridge DS #1: Build new feeders | N.D.C.2.02 | 7374 | 205 | LINES | UNPLND |  |  | Yes |  |  |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20139 | Carlaw A6-A7 Metalclad Swgr | N.T.C.1.08 | 7700 | 203 | PROJECT DELIVERY | AIP000393 |  | AIP000393 | Yes | AIP000393 |  |  |  | System Re-investment | James.Mardegan@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20141 | Wiltshire TS T1/T6; A5-A6 M/C & Component Replacem | N.T.C.1.43 | 7700 | 203 | PROJECT DELIVERY | AIP005303 |  | AIP005303 | Yes | AIP005303 |  |  |  | Greater Toronto Area Zone Station/Yard Investments | James.Mardegan@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20145 | DS Preventive Maintenance - Planned - Ground &Site | N.D.M.1.04 | 7370 | 206 | TX LINES AND STATIONS | AIP000256A | AIP000256 | AIP000256 | No | AIP000256 | DS Preventive Maintenance - Ground and Sites |  |  | Distributing and Regulating Stations | emre.aydin@HydroOne.com | patrick.howe@hydroone.com | System O&M | N/A | 0 | 03 - None (default) | 0 | Program | ACTN EMPP | Executing | Short Term Planning | # of Orders | 1740540.856 | 1793361.1088 | 1832574.8201 | 1873323.9617 | 1908225.9461 | 0 | 0 | 0 | 0 | 0 | 1740540.856 | 1793361.1088 | 1832574.8201 | 1873323.9617 | 1908225.9461 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3521 | 3521 | 3521 | 3521 | 3521 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
20146 | DS Corrective Maintenance - Planned - Ground &Site | N.D.M.1.04 | 7370 | 206 | TX LINES AND STATIONS | AIP000251 | AIP000251 | AIP000251 | No | AIP000251 | DS Corrective Maintenance - Planned - Ground & Site |  |  | Distributing and Regulating Stations | emre.aydin@HydroOne.com | Trevor.Beausoleil@HydroOne.com | System O&M | N/A | 0 | 03 - None (default) | 0 | Program | EMPP ACTN | Executing | Short Term Planning | # of Orders | 464687.6562 | 478789.5988 | 489258.8037 | 500138.0025 | 509456.0776 | 0 | 0 | 0 | 0 | 0 | 464687.6562 | 478789.5988 | 489258.8037 | 500138.0025 | 509456.0776 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
20147 | Strachan TS T12/T14; A7-A8 M/C & Comp Replacement | N.T.C.1.08 | 7700 | 203 | PROJECT DELIVERY | AIP000444 | AIP000444 | AIP000444 | No | AIP000444 | Strachan TS T12/T14; A7-A8 M/C & Component Replacement | 0 |  | System Re-investment | James.Mardegan@HydroOne.com | michael.xavier@hydroone.com | System Renewal | Greater Toronto Area | 0 | 01 - Agreement (current/future) | 0 | Project | ACCP EMPP | Executing | Executing |  | 36750.6676 | 990919.3889 | 0.019656 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76314.6676 | 2018037.1323 | 0.019656 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.9389e-12 | -9824.7434 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -0.9462 | 0 | -39564 | -1017293 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43800 | [13 empty] | FALSE |  | 0 | 0 | A7-A8 M/C
20148 | DS Corrective Maintenance - Demand - Ground & Site | N.D.M.1.04 | 7370 | 206 | TX LINES AND STATIONS | AIP000249 | AIP000249 | AIP000249 | No | AIP000249 | DS Corrective Maintenance - Demand - Ground & Site |  |  | Distributing and Regulating Stations | emre.aydin@HydroOne.com | Trevor.Beausoleil@HydroOne.com | System O&M | N/A | 0 | 03 - None (default) | 0 | Program | ACTN EMPP | Executing | Short Term Planning | # of Orders | 143717.9715 | 148079.3888 | 151317.3482 | 154682.0383 | 157563.8829 | 0 | 0 | 0 | 0 | 0 | 143717.9715 | 148079.3888 | 151317.3482 | 154682.0383 | 157563.8829 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
20151 | Toronto-TTC Maintenance Facility_Recoverable | N.T.C.1.14 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Third Party Transmission System Modifications | john.boldt@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20152 | Wiltshire A3-A4 Metalclad Swgr | N.T.C.1.08 | 7700 | 203 | PROJECT DELIVERY | AIP000450 | AIP000450 | AIP000450 | No | AIP000450 | Wiltshire A3-A4 Metalclad Swgr | 0 |  | System Re-investment | James.Mardegan@HydroOne.com | michael.xavier@hydroone.com | System Renewal | Greater Toronto Area | 0 | 01 - Agreement (current/future) | 0 | Project | EMPP ACTN | Executing | Executing |  | 1181601.9099 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2399742.6975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -9860.7876 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -0.82762 | 0 | -1208280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43435 | [13 empty] | FALSE |  | 0 | 0 | Alternative 1
20153 | Strachan TS T12/T14; A5-A6 M/C & Comp Replacement | N.T.C.1.43 | 7700 | 203 | PROJECT DELIVERY | AIP000443 | AIP000443 | AIP000443 | No | AIP000443 | Strachan TS: A5-A6 M/C & Component Replacements | 0 |  | Greater Toronto Area Zone Station/Yard Investments | James.Mardegan@HydroOne.com | michael.xavier@hydroone.com | System Renewal | Greater Toronto Area | Not Required | 01 - Agreement (current/future) | Not Required | Project | BEST EXTR | Short Term Planning | Short Term Planning |  | 0 | 791065.5371 | 988174.3038 | 962913.6051 | -571746.7899 | 0 | 0 | 0 | 0 | 0 | 0 | 850608.1044 | 1062553.0148 | 2471019.6933 | 849559.7455 | 0 | 0 | 0 | 0 | 0 | 0 | -59542.5673 | -74378.711 | -72477.3681 | 43034.7046 | 0 | 0 | 0 | 0 | 0 | -7 | 7.00 | 0 | 0 | 0 | -1435628.72 | -1464341.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43742 | 44834 | True | THESL Metalclad Replacement Schedule | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Component Replacements
20154 | Carlaw TS: A4-A5 M/C Replacement | N.T.C.1.43 | 7700 | 203 | PROJECT DELIVERY | AIP000392 | AIP000392 | AIP000392 | No | AIP000392 | Carlaw TS: A4-A5 M/C Replacements | 0 |  | Greater Toronto Area Zone Station/Yard Investments | James.Mardegan@HydroOne.com | michael.xavier@hydroone.com | System Renewal | Greater Toronto Area | Not Required | 01 - Agreement (current/future) | Not Required | Project | init | Short Term Planning | Short Term Planning |  | 639038.0248 | 521864.452 | 1364516.1569 | -304092.0295 | 0 | 0 | 0 | 0 | 0 | 0 | 687137.6611 | 561144.572 | 2874700.794 | 1108648.0431 | 0 | 0 | 0 | 0 | 0 | 0 | -48099.6363 | -39280.12 | -102705.5172 | 22888.6474 | 0 | 0 | 0 | 0 | 0 | 0 | -7 | 7.00 | 0 | 0 | -1407479.12 | -1435628.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43591 | 44561 | True | THESL Metalclad Replacement Schedule | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Component Replacements
20171 | Manby TS: Uprate 115kV Switchyard | N.T.C.2.02 | 7700 | 203 | PROJECT DELIVERY | AIP000708 |  | AIP000708 | Yes | AIP000708 |  |  |  | Local Area Supply | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20190 | OPA Programs | N.D.M.2.50 | 1144 | 220 | STRATEGY & CONSERV | UNPLND |  |  | Yes |  |  |  |  | Conservation and Demand Management | Imran.Merali@HydroOne.com | [6 empty] | Program | init EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20198 | Fort William TS ID 767 Skypower Thunde Bay Hy(TX) | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20208 | Telecom DCN Security Enhancement | N.T.C.1.29 | 7700 | 203 | PROJECT DELIVERY | AIP000684 |  | AIP000684 | Yes | AIP000684 |  |  |  | NERC Cyber Security Compliance Readiness | lincoln.frost-hunt@hydroone.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20216 | Tx PCB Reduction Program - Testing | N.T.M.1.05 | 7370 | 206 | TX LINES AND STATIONS | AIP001009 | AIP001009 | AIP001009 | No | AIP001009 | Environmental - PCB Retirement - Testing | 0 |  | Environmental Management | Mike.Tanaskovic@HydroOne.com | Harshal.Bhatt@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | ACTN EMPP | Executing | Short Term Planning | # of Orders | 1080704.8903 | 1112630.5002 | 1165063.566 | 549025.3569 | 0 | 0 | 0 | 0 | 0 | 0 | 1080704.8903 | 1112630.5002 | 1165063.566 | 549025.3569 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | 3000 | 3000 | 1200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | True | Environment Canada PCB regulation (SOR/2008-273) | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Asset Optimal
20232 | Local Control Computer (LCC) Replacement | N.T.C.1.19 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Protection Control & Metering Equip | Miroslav.Kostic@HydroOne.com | [6 empty] | Program | ACCP EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20241 | Install TF UCL Fall Protection Device -Base Plates | N.T.M.1.16 | 7370 | 206 | TX LINES AND STATIONS | AIP001060 | AIP001060 | AIP001060 | No | AIP001060 | Other Mtce - Power Equipment - UCL Installation | 0 |  | Power Equipment | Mike.Tanaskovic@HydroOne.com | perry.ng@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | ACTN EMPP | Executing | Short Term Planning | # of Transformers | 164807.9321 | 261601.3563 | 262132.9351 | 174473.9092 | 272764.3241 | 272893.1151 | 0 | 0 | 0 | 0 | 164807.9321 | 261601.3563 | 262132.9351 | 174473.9092 | 272764.3241 | 272893.1151 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 32 | 32 | 20 | 31 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | True | Ontario Regulation 213/91, Section 26.7 | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Vulnerable (Modified-Tx Decision)
20246 | Uxbridge DS #1: Land Purchase | N.D.C.2.02 | 7882 | 215 | FACILITIES & REAL ESTATE | UNPLND |  |  | Yes |  |  |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | [6 empty] | Project | init EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20247 | Vibration Damper Replacement Program - E&CS | N.T.M.1.20 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Overhead Lines | hassan.hamzeh@hydroone.com | [6 empty] | Program | ACTN EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20251 | Smart Grid Discovery Phase | N.D.M.2.06 | 4343 | 222 | SMART GRID | UNPLND |  |  | Yes |  |  |  |  | Smart Grid | Godfrey.Holder@HydroOne.com | [6 empty] | Program | EMPP AWRD | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20256 | Merivale GIS 'ITE' Bus Replacement | N.T.C.1.08 | 7700 | 203 | PROJECT DELIVERY | AIP000428 |  | AIP000428 | Yes | AIP000428 |  |  |  | System Re-investment | James.Mardegan@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20258 | Energy Storage Study - Large Scale Urban Utility | N.D.M.2.22 | 4230 | 213 | PLANNING | UNPLND |  |  | Yes | [12 empty] | Project | init EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20259 | Energy Hub Management System - OCE | N.D.M.2.22 | 4230 | 213 | PLANNING | UNPLND |  |  | Yes | [12 empty] | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20261 | Power Transformer ULTC Mod's/Upgrades Program | N.T.M.1.16 | 7370 | 206 | TX LINES AND STATIONS | AIP001072 | AIP001072 | AIP001072 | No | AIP001072 | Transformer ULTC Modifications | 0 |  | Power Equipment | Mike.Tanaskovic@HydroOne.com | perry.ng@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | AWRD EMPP | Executing | Short Term Planning | # of Tap Changers | 569568.9925 | 888054.8502 | 907872.4617 | 928669.4256 | 947903.0119 | 967528.3358 | 0 | 0 | 0 | 0 | 569568.9925 | 888054.8502 | 907872.4617 | 928669.4256 | 947903.0119 | 967528.3358 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 32 | 32 | 32 | 32 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | False |  | False | True | False | False | FALSE |  | 0 | 0 | Intermediate Modified (Tx Decision)
20265 | Bruce A & B Station Service Upgrades | N.T.C.1.20 | 7700 | 203 | PROJECT DELIVERY | AIP000622B |  | AIP000622 | Yes | AIP000622 |  |  |  | Ancillary Systems | James.Mardegan@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20275 | Doane DS Second Transformer Addition and Feeders | N.D.C.2.02 | 7700 | 203 | PROJECT DELIVERY | 3872.5 |  |  | Yes |  |  |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20278 | Shieldwire Replacement Program - L&FS | N.T.C.1.12 | 7370 | 206 | TX LINES AND STATIONS | AIP000466B | AIP000466 | AIP000466 | No | AIP000466 | Tx Lines Shieldwire Replacement Program | SR-24 | Transmission Line Shieldwire Replacement | Overhead Lines Component Refurb & Repl | hassan.hamzeh@hydroone.com | Deniz.Turkben@HydroOne.com | System Renewal | N/A | 0 | 03 - None (default) | 0 | Program | ACTN EMPP | Executing | Short Term Planning | # of KM of shieldwire replaced | 5052320.1406 | 5135978.7674 | 5195334.4903 | 5235575.8619 | 5275357.9049 | 5334669.3884 | 0 | 0 | 0 | 0 | 5741272.887 | 5836339.5085 | 5903789.1935 | 5949518.0249 | 5994724.892 | 6062124.305 | 0 | 0 | 0 | 0 | -688952.7464 | -700360.741 | -708454.7032 | -713942.163 | -719366.987 | -727454.9166 | 0 | 0 | 0 | 0 | -12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109.85 | 109.85 | 109.85 | 109.85 | 109.85 | 109.85 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Intermediate
20286 | SF6 Breaker Replacement Program (All Types) | N.T.C.1.01 | 7700 | 203 | PROJECT DELIVERY | AIP000381 |  | AIP000381 | Yes | AIP000381 |  |  |  | Circuit Breakers | James.Mardegan@HydroOne.com | [6 empty] | Program | ACCP EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20291 | Detour Lake - 230kV Mine Connection | N.T.C.2.11 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Load Customer Connection | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20296 | Transmission Health Safety and Environment | N.T.M.3.03 | 7793 | 209 | HEALTH, SAFETY & ENV | UNPLND |  |  | Yes | [12 empty] | Program | EMPP init | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20300 | Distribution Health Safety and Environment | N.D.M.3.03 | 7793 | 209 | HEALTH, SAFETY & ENV | UNPLND |  |  | Yes | [12 empty] | Program | EMPP init | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20304 | Tx Lines 500KV Foundation Repair/Replace | N.T.C.1.12 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Overhead Lines Component Refurb & Repl | hassan.hamzeh@hydroone.com | [6 empty] | Program | ACCP EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20307 | In-Line Circuit Breakers (Summerhaven) | N.T.C.2.04 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes | [12 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20311 | CGE Brantford TS T3 & T4 - Replace EOL Trfrmr | N.T.C.1.17 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Power Transformers | James.Mardegan@HydroOne.com | [6 empty] | Program | ACCP EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20312 | Specs, Scope, and Tendering of PQ Meters for DG | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000195 |  | AIP000195 | Yes | AIP000195 | Small Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | EMPP ACTN | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20317 | CGE Finch TS T3 & T4 - Replace EOL Trfrmr | N.T.C.1.17 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Power Transformers | James.Mardegan@HydroOne.com | [6 empty] | Program | ACCP EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20318 | Placeholder - Unforeseen Risk Mitigation | N.T.C.2.21 | 7700 | 203 | PROJECT DELIVERY | AIP000946 | AIP000946 | AIP000946 | No | AIP000946 | Unforeseen Risk Mitigation (e.g. rod gap replacement, limit short circuit) | 0 |  | Major Risk Mitigation | Robert.Reinmuller@HydroOne.com | farooq.qureshy@hydroone.com | System Service | 0 | Not Required | 03 - None (default) | Not Required | Project | init | Short Term Planning | Short Term Planning |  | 0 | 1967511.2732 | 1952691.2959 | 1923163.7792 | 1906519.025 | 1894215.7728 | 0 | 0 | 0 | 0 | 0 | 1967511.2732 | 1952691.2959 | 1923163.7792 | 1906519.025 | 1894215.7728 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43466 | 45047 | False |  | False |  | False |  | True | False |  | False | True | False | False | FALSE |  | 0 | 0 | Alternative 1
20322 | Underfrequency Load Shedding Upgrades | N.T.C.1.19 | 7700 | 203 | PROJECT DELIVERY | AIP000613 |  | AIP000613 | Yes | AIP000613 |  |  |  | Protection Control & Metering Equip | Miroslav.Kostic@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20325 | Tx Lines Insulator Replacement Program - CS | N.T.C.1.12 | 7370 | 206 | TX LINES AND STATIONS | AIP000459B | AIP000459 | AIP000459 | No | AIP000459 | Tx Lines Insulator Replacement Program | SR-25 | Transmission Line Insulator Replacement | Overhead Lines Component Refurb & Repl | hassan.hamzeh@hydroone.com | Tyler.Wales@HydroOne.com | System Renewal | 0 | 0 | 03 - None (default) | 0 | Program | AWRD EMPP | Executing | Short Term Planning | Number of Circuit Structures | 31593627.7666 | 29593013.0414 | 29811810.2788 | 29966993.969 | 14621747.2564 | 14744339.3777 | 0 | 0 | 0 | 0 | 35901849.7348 | 33628423.9107 | 33877057.135 | 34053402.2375 | 16615621.8823 | 16754931.111 | 0 | 0 | 0 | 0 | -4308221.9682 | -4035410.8693 | -4065246.8562 | -4086408.2685 | -1993874.6259 | -2010591.7333 | 0 | 0 | 0 | 0 | -12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1850 | 1850 | 1850 | 1850 | 925 | 925 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Asset Optimal (Modified - Tx Decision)
20331 | Kent TS-M2-ID273-Kent Breeze-Dx | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000199 |  | AIP000199 | Yes | AIP000199 | Large Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20333 | CGE Ingersoll TS T5 & T6 - Replace EOL Trfrmr | N.T.C.1.17 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Power Transformers | James.Mardegan@HydroOne.com | [6 empty] | Program | ACCP EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20341 | HP Air Refurbishment Program | N.T.C.1.20 | 7700 | 203 | PROJECT DELIVERY | AIP000618 |  | AIP000618 | Yes | AIP000618 |  |  |  | Ancillary Systems | James.Mardegan@HydroOne.com | [6 empty] | Program | ACTN EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20342 | Placeholder - Unforeseen Projects (Gen Connection) | N.T.C.2.12 | 7700 | 203 | PROJECT DELIVERY | AIP000896 | AIP000896 | AIP000896 | No | AIP000896 | Provision for Unforeseen Generation Connection Projects | SA-11 | Future Transmission Generation Connection Plans | Generator Customer Connection | Robert.Reinmuller@HydroOne.com | farooq.qureshy@hydroone.com | System Access | 0 | Not Required | 03 - None (default) | Not Required | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0.0095326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4007850.77 | 4007850.87 | 4007850.8895 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3.2502e-11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4007850.77 | -4007850.87 | -4007850.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44255 | 45778 | True | Future customer connection requests. | True | Transmission license requirement to connect customers. | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Alternative 1
20346 | PCB Padmount Transformer Replacement | N.D.C.1.04 | 7374 | 205 | LINES | UNPLND |  |  | Yes |  |  |  |  | PCB Transformer Replacement | emre.aydin@HydroOne.com | [6 empty] | Program | ACTN EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20347 | PCB Overhead Equipment Replacement | N.D.C.1.04 | 7374 | 205 | LINES | AIP000131 | AIP000131 | AIP000131 | No | AIP000131 | PCB Overhead Equipment Replacement | ISD-SR-08 | Distribution Lines PCB Equipment Replacement Program | PCB Transformer Replacement | emre.aydin@HydroOne.com | Wojciech.Maroszek@HydroOne.com | System Renewal | N/A | 0 | 03 - None (default) | 0 | Program | EMPP ACTN | Executing | Short Term Planning | Transformers | 11596030.6676 | 11828845.1186 | 12073339.8639 | 18485449.3019 | 18854537.3596 | 0 | 0 | 0 | 0 | 0 | 13298200.3069 | 13565189.3562 | 13845573.2384 | 21198909.7499 | 21622175.8711 | 0 | 0 | 0 | 0 | 0 | -1702169.6393 | -1736344.2376 | -1772233.3745 | -2713460.448 | -2767638.5115 | 0 | 0 | 0 | 0 | 0 | -12.8 | 12.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2152 | 2152 | 2152 | 3228 | 3228 | 2152 | 2152 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Hybrid Scenario
20353 | Wallace TS M4 ID549 Greenview Power DX | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000195 |  | AIP000195 | Yes | AIP000195 | Small Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20354 | Wallace TS M4 ID549 Greenview Power TX | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20357 | Kingston Gardiner #2 TS - Invista Protections | N.T.C.2.11 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Load Customer Connection | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | DETL HOLD | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20361 | Martindale TS Spill Containment | N.T.C.1.22 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes | [12 empty] | Program | ACCP EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20364 | Spill Containment Upgrades | N.T.C.1.22 | 7700 | 203 | PROJECT DELIVERY | AIP000639 |  | AIP000639 | Yes | AIP000639 | [11 empty] | Program | ACCP EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20367 | Overhead PCB Inspection and Testing | N.D.M.1.06 | 7374 | 205 | LINES | AIP000265 | AIP000265 | AIP000265 | No | AIP000265 | Overhead PCB Equipment Inspection & Testing |  |  | PCB Test and Destruction | emre.aydin@HydroOne.com | Wojciech.Maroszek@HydroOne.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | ACCP EMPP | Executing | Short Term Planning | Transformers | 9376529.6113 | 9655659.619 | 9860855.4361 | 10075232.4389 | 10256874.2894 | 0 | 0 | 0 | 0 | 0 | 9376529.6113 | 9655659.619 | 9860855.4361 | 10075232.4389 | 10256874.2894 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27595 | 27595 | 27595 | 27595 | 27595 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Demand - EC Mandated Program
20369 | On Call Environmental Assistance | N.D.M.1.06 | 7053 | 209 | HEALTH, SAFETY & ENV | AIP000264 | AIP000264 | AIP000264 | No | AIP000264 | On Call Environmental Assistance |  |  | PCB Test and Destruction | emre.aydin@HydroOne.com | Wojciech.Maroszek@HydroOne.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | EMPP ACCP | Executing | Short Term Planning |  | 220320.1189 | 227006.2578 | 231969.9787 | 237189.0045 | 241608.0713 | 0 | 0 | 0 | 0 | 0 | 220320.1189 | 227006.2578 | 231969.9787 | 237189.0045 | 241608.0713 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Demand
20371 | PCB and Other Waste Management | N.D.M.1.06 | 7053 | 209 | HEALTH, SAFETY & ENV | AIP000266 | AIP000266 | AIP000266 | No | AIP000266 | PCB & Waste Management |  |  | PCB Test and Destruction | emre.aydin@HydroOne.com | Wojciech.Maroszek@HydroOne.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | ACCP EMPP | Executing | Short Term Planning |  | 5362838.4677 | 5614119.3482 | 5827348.0974 | 6052670.7756 | 6264076.749 | 0 | 0 | 0 | 0 | 0 | 5362838.4677 | 5614119.3482 | 5827348.0974 | 6052670.7756 | 6264076.749 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Demand
20374 | GIC Maintenance/Re-Calibration | N.T.M.1.17 | 7370 | 206 | TX LINES AND STATIONS | UNPLND |  |  | Yes |  |  |  |  | Protection Control & Metering Equipment | Miroslav.Kostic@HydroOne.com | [6 empty] | Project | init EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20379 | St. Isidore TS- M2- ID 1212- St. Isidore B | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | 6009 |  |  | Yes |  |  |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | [6 empty] | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20383 | Whitedog DS Transformer Fan Monitoring | N.D.C.2.02 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | [6 empty] | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20390 | Tx Lines Switch Replacement Program | N.T.C.1.12 | 7370 | 206 | TX LINES AND STATIONS | AIP000469 | AIP000469 | AIP000469 | No | AIP000469 | Tx Lines Switch Replacement Program | 0 |  | Overhead Lines Component Refurb & Repl | hassan.hamzeh@hydroone.com | Tyler.Wales@HydroOne.com | System Renewal | 0 | 0 | 03 - None (default) | 0 | Program | AWRD EMPP | Executing | Short Term Planning | Number of Switches | 828448.9657 | 619240.2972 | 626396.7728 | 631248.6539 | 636045.1045 | 643196.1903 | 0 | 0 | 0 | 0 | 862967.6726 | 645041.9762 | 652496.6384 | 657550.6811 | 662546.9839 | 669996.0316 | 0 | 0 | 0 | 0 | -34518.7069 | -25801.679 | -26099.8655 | -26302.0272 | -26501.8794 | -26799.8413 | 0 | 0 | 0 | 0 | -4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Asset Optimal
20391 | Midhurst Perimeter Security Upgrade | N.T.C.1.80 | 7700 | 203 | PROJECT DELIVERY | AIP000691 |  | AIP000691 | Yes | AIP000691 | Tx Stations Security Upgrades - Carryover Work |  |  | Security Infrastructure | James.Mardegan@HydroOne.com | mark.truchanowicz@hydroone.com | General Plant | 0 | 0 | 03 - None (default) | 0 | Project | ACCP EMPP | Executing | Executing | # of Stations | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20392 | SECURITY SERVICES TX | N.T.M.1.80 | 838 | 212 | INFO SOLUTIONS DIVISION | AIP001154 | AIP001154 | AIP001154 | No | AIP001154 | Tx Security Incident Response | 0 |  | Security Infrastructure | Rick.Haier@HydroOne.com | dave.belluz@HydroOne.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | EMPP AWRD | Executing | Short Term Planning | Retainer | 717448.7 | 759726.2459 | 783942.6125 | 809282.0703 | 833867.6311 | 850581.3746 | 0 | 0 | 0 | 0 | 717448.7 | 759726.2459 | 783942.6125 | 809282.0703 | 833867.6311 | 850581.3746 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | False |  | False | False | False | False | TRUE | Investments are required in Security Infrastructure to maintain system reliability, meet regulatory requirements and promote greater safety within the station environment. | 0 | 0 | Intermediate 1
20397 | Transformer Deluge Upgrade Program | N.T.C.1.21 | 7700 | 203 | PROJECT DELIVERY | AIP000627 |  | AIP000627 | Yes | AIP000627 |  |  |  | Infrastructure | James.Mardegan@HydroOne.com | [6 empty] | Program | ACCP EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20402 | Holland DS spare recloser and switchgear | N.D.C.2.02 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20413 | Cancelled-2012 Burleigh DS Transformer Replacement | N.D.C.2.02 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | [6 empty] | Project | DETL ACTN | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20425 | Goodfish DS F10 Duncan Ave Rebuild | N.D.C.1.07 | 7374 | 205 | LINES | AIP000152 |  | AIP000152 | Yes | AIP000152 | Large Sustainment Initiatives | ISD-SR-12 | Distribution Lines Sustainment Initiatives | Lines | emre.aydin@HydroOne.com | Alexander.Hamlyn@HydroOne.com | System Renewal | N/A | 0 | 03 - None (default) | 0 | Program | ACCP EMPP | Executing | Short Term Planning | # of projects | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20426 | Matachewan Voltage Conversion | N.D.C.2.02 | 7374 | 205 | LINES | UNPLND |  |  | Yes |  |  |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | [6 empty] | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20429 | Kent TS-M2-ID273-Kent Breeze-Tx | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20430 | SECURITY SERVICES DX | N.D.M.1.80 | 838 | 212 | INFO SOLUTIONS DIVISION | AIP000287 | AIP000287 | AIP000287 | No | AIP000287 | Dx Security Incident Response |  |  | Security Infrastructure | Rick.Haier@HydroOne.com | dave.belluz@HydroOne.com | System O&M | N/A | 0 | 03 - None (default) | 0 | Program | AWRD EMPP | Executing | Short Term Planning | Retainer | 154472.0656 | 160720.1854 | 165844.3747 | 171194.3791 | 176093.8287 | 0 | 0 | 0 | 0 | 0 | 154472.0656 | 160720.1854 | 165844.3747 | 171194.3791 | 176093.8287 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Intermediate 1
20431 | Dx Station Security Upgrades | N.D.C.1.80 | 7700 | 203 | PROJECT DELIVERY | AIP000176 | AIP000176 | AIP000176 | No | AIP000176 | Stations Security Upgrades | ISD-GP-24 | Station Security Upgrades | Security Infrastructure | emre.aydin@HydroOne.com | patrick.howe@hydroone.com | General Plant | N/A | 0 | 03 - None (default) | 0 | Program | EMPP ACCP | Executing | Short Term Planning | # of Stations | 1089011.0083 | 1110875.1625 | 1133925.0917 | 1157251.141 | 1180357.2334 | 0 | 0 | 0 | 0 | 0 | 1170979.5789 | 1194489.422 | 1219274.2922 | 1244356.0656 | 1269201.3263 | 0 | 0 | 0 | 0 | 0 | -81968.5705 | -83614.2595 | -85349.2005 | -87104.9246 | -88844.0928 | 0 | 0 | 0 | 0 | 0 | -7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal (Pilot Program)
20435 | Dundas OC 2010 Paving | N.D.C.1.50 | 7236 | 215 | FACILITIES & REAL ESTATE | UNPLND |  |  | Yes |  |  |  |  | Real Estate Facilities | cindy.copp@hydroone.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20446 | Cherrywood TS Drainage and Roads | N.T.C.1.21 | 7700 | 203 | PROJECT DELIVERY | 1 |  |  | Yes |  |  |  |  | Infrastructure | James.Mardegan@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20453 | S2B Steel Structure Replacement | N.T.C.1.12 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Overhead Lines Component Refurb & Repl | hassan.hamzeh@hydroone.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20456 | 2012 Drayton DS Transformer Replacement | N.D.C.2.02 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20458 | CGE Leslie TS T3 - Replace EOL Trfrmr | N.T.C.1.17 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Power Transformers | James.Mardegan@HydroOne.com | [6 empty] | Program | EMPP ACCP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20462 | 2010 Durham Elgin Install MUS Facility | N.D.C.1.07 | 7374 | 205 | LINES | UNPLND |  |  | Yes |  |  |  |  | Lines | emre.aydin@HydroOne.com | [6 empty] | Program | ACCP DETL | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20470 | Connect the Comber East & West Wind FIT Projects | N.T.C.2.12 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Generator Customer Connection | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20474 | White River Tx FIT Projects | N.T.C.2.12 | 7700 | 203 | PROJECT DELIVERY | AIP000909 |  | AIP000909 | Yes | AIP000909 |  |  |  | Generator Customer Connection | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20479 | Connect the Summerhaven WEC Tx FIT Project | N.T.C.2.12 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Generator Customer Connection | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20482 | Connect the Wahpeestan Project Tx FIT Project | N.T.C.2.12 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Generator Customer Connection | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | HOLD | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20484 | Connect the Trout Lake River Tx FIT Project | N.T.C.2.12 | 7700 | 203 | PROJECT DELIVERY | AIP000865 |  | AIP000865 | Yes | AIP000865 |  |  |  | Generator Customer Connection | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20485 | Connect the High Falls Hydropower Tx FIT Project | N.T.C.2.12 | 7700 | 203 | PROJECT DELIVERY | DO NOT USE |  |  | Yes |  |  |  |  | Generator Customer Connection | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | HOLD | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20486 | Namewaminikan Tx FIT Project Connection | N.T.C.2.12 | 7700 | 203 | PROJECT DELIVERY | AIP000890 |  | AIP000890 | Yes | AIP000890 |  |  |  | Generator Customer Connection | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20493 | Dufferin Wind Farm Project | N.T.C.2.12 | 7700 | 203 | PROJECT DELIVERY | AIP000870 |  | AIP000870 | Yes | AIP000870 |  |  |  | Generator Customer Connection | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20495 | X22: Connect White Pines Wind Farm Tx FIT Project | N.T.C.2.12 | 7700 | 203 | PROJECT DELIVERY | AIP000925 | AIP000925 | AIP000925 | No | AIP000925 | -X22: Connect White Pines Wind Farm Tx FIT Project | 0 |  | Generator Customer Connection | Robert.Reinmuller@HydroOne.com | Quyen.Diep@HydroOne.com | System Access | Eastern | Not Required | 01 - Agreement (current/future) | Required | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1226400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1226400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43132 | [13 empty] | FALSE |  | 0 | 0 | Alternative 1
20497 | Connect the Wolfe Island Shoals Wind Farm Tx FIT | N.T.C.2.12 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Generator Customer Connection | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | DETL init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20499 | Connect the Liskeard 1,3,4 Tx FIT Project | N.T.C.2.12 | 7700 | 203 | PROJECT DELIVERY | AIP000859 |  | AIP000859 | Yes | AIP000859 |  |  |  | Generator Customer Connection | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20508 | Duart TS Feeder Construction | N.D.C.2.02 | 7374 | 205 | LINES | UNPLND |  |  | Yes |  |  |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | [6 empty] | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20513 | DS Power Quality Monitoring | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | 11 |  |  | Yes |  |  |  |  | Distribution Generation Connection | ryan.boudreau@HydroOne.com | [6 empty] | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20515 | Mitigation Measures for Windsor Malden - Dx | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Distribution Generation Connection | ryan.boudreau@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20516 | Napanee TS M2 ID1505 Lennox #3 (Tx) | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | [6 empty] | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20521 | Short Circuit Studies | N.D.M.2.02 | 7374 | 205 | LINES | AIP000293 | AIP000293 | AIP000293 | No | AIP000293 | Short Circuit Studies |  |  | Engineering and Technical Services | ted.lyberogiannis@HydroOne.com | Charlie.Lee@HydroOne.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | ACCP EMPP | Executing | Short Term Planning | # of Studies | 182973.3581 | 188526.0552 | 192648.4391 | 196932.1231 | 200601.18 | 0 | 0 | 0 | 0 | 0 | 182973.3581 | 188526.0552 | 192648.4391 | 196932.1231 | 200601.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 200 | 200 | 200 | 200 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Demand
20523 | Technical Studies | N.D.M.2.02 | 7374 | 205 | LINES | AIP000294 | AIP000294 | AIP000294 | No | AIP000294 | Technical Studies |  |  | Engineering and Technical Services | ted.lyberogiannis@HydroOne.com | Helen.Guo@HydroOne.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | ACCP EMPP | Executing | Short Term Planning | # of Studies | 753830.0479 | 776706.6116 | 793690.159 | 811338.6301 | 826454.7397 | 0 | 0 | 0 | 0 | 0 | 753830.0479 | 776706.6116 | 793690.159 | 811338.6301 | 826454.7397 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250 | 250 | 250 | 250 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Demand
20524 | ERA Surveys | N.D.M.2.02 | 7374 | 205 | LINES | AIP000291 | AIP000291 | AIP000291 | No | AIP000291 | ERA Surveys |  |  | Engineering and Technical Services | ted.lyberogiannis@HydroOne.com | Helen.Guo@HydroOne.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | ACCP EMPP | Executing | Short Term Planning | # of Points | 381514.697 | 131030.8452 | 133895.9971 | 136873.2785 | 139423.3516 | 0 | 0 | 0 | 0 | 0 | 381514.697 | 131030.8452 | 133895.9971 | 136873.2785 | 139423.3516 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2220 | 740 | 740 | 740 | 740 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Demand
20525 | Mitigation Measures for Windsor Malden - Tx | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20527 | Hub Site EOL and Capacity Expansion | N.T.C.3.08 | 7700 | 203 | PROJECT DELIVERY | AIP000986 | AIP000986 | AIP000986 | No | AIP000986 | Control Network Reconfiguration | 0 |  | Integrating Operating Infrastructure | Miroslav.Kostic@HydroOne.com | Andrew.Webb@HydroOne.com | General Plant | 0 | 0 | 02 - Expectation (no agreement) | 0 | Program | ACCP EMPP | Executing | Short Term Planning | # of sites | 2617324.9314 | 2660663.7803 | 2691412.7608 | 2712259.5759 | 2732868.4454 | 2763594.3903 | 0 | 0 | 0 | 0 | 2617324.9314 | 2660663.7803 | 2691412.7608 | 2712259.5759 | 2732868.4454 | 2763594.3903 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | False |  | False | False | False | True | FALSE |  | 0 | 0 | Asset Optimal
20537 | Hanmer TS - Transmission Station Re-Inve | N.T.C.1.08 | 7700 | 203 | PROJECT DELIVERY | AIP000418 |  | AIP000418 | Yes | AIP000418 |  |  |  | System Re-investment | James.Mardegan@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20539 | Conductor Replacement - Overhead | N.D.C.1.07 | 7374 | 205 | LINES | AIP000146 | AIP000146 | AIP000146 | No | AIP000146 | Component Replacement - Overhead Conductor | ISD-SR-10 | Distribution Lines Planned Component Replacement Program | Lines | emre.aydin@HydroOne.com | joseph.parete@hydroone.com | System Renewal | 0 | 0 | 03 - None (default) | 0 | Program | EMPP ACTN | Executing | Short Term Planning | # of kilometers | 519862.9274 | 530300.1664 | 540357.0788 | 550507.0685 | 561498.7756 | 0 | 0 | 0 | 0 | 0 | 596173.0818 | 608142.3926 | 619675.5491 | 631315.4455 | 643920.6143 | 0 | 0 | 0 | 0 | 0 | -76310.1545 | -77842.2263 | -79318.4703 | -80808.377 | -82421.8386 | 0 | 0 | 0 | 0 | 0 | -12.8 | 12.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Vulnerable
20543 | Delete: Enterprise Resource Planning Program | N.C.M.1.60 | 4330 | 212 | INFO SOLUTIONS DIVISION | 19342; 19389 |  |  | Yes |  |  |  |  | IT Business Improvements & Enhancements | lincoln.frost-hunt@hydroone.com | [6 empty] | Program | #N/A | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20544 | Delete: Enterprise Asset Management Program | N.C.M.1.60 | 4330 | 212 | INFO SOLUTIONS DIVISION | 19393; 19350 |  |  | Yes |  |  |  |  | IT Business Improvements & Enhancements | lincoln.frost-hunt@hydroone.com | [6 empty] | Program | #N/A | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20548 | INERGI INCREMENTAL APPLICATION SUPPORT | N.C.M.1.70 | 4339 | 212 | INFO SOLUTIONS DIVISION | AIP000091E |  | AIP000091 | Yes | AIP000091 | Inergi Sustainment |  |  | IT - Sustainment and Operations | lincoln.frost-hunt@hydroone.com | robert.hosford@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | init EMPP | Executing | Short Term Planning | Retainer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20550 | Parry Sound TS: Upgrade Txfmrs to 50/83 MVA | N.T.C.2.11 | 7700 | 203 | PROJECT DELIVERY | DO NOT USE |  |  | Yes |  |  |  |  | Load Customer Connection | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | DETL INSC | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20560 | Enterprise GIS | N.C.M.1.60 | 4330 | 212 | INFO SOLUTIONS DIVISION |  |  |  | No |  |  |  |  | IT Business Improvements & Enhancements | lincoln.frost-hunt@hydroone.com | [6 empty] | Program | #N/A | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20574 | NRC TS EOL Asset Replacement Project | N.T.C.1.08 | 7700 | 203 | PROJECT DELIVERY | AIP000431 | AIP000431 | AIP000431 | No | AIP000431 | NRC T1/T3 Station Refurbishment | 0 |  | System Re-investment | James.Mardegan@HydroOne.com | Fred.Kouhdani@HydroOne.com | System Renewal | Eastern | 0 | 03 - None (default) | 0 | Project | ACCP EMPP | Executing | Executing |  | 3015700.2234 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4048174.7404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -848794.517 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -21.9639 | 0 | -183680 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43276 | [13 empty] | FALSE |  | 0 | 1 | Alternative 1
20584 | London Nelson TS EOL Replacement Project | N.T.C.1.40 | 7700 | 203 | PROJECT DELIVERY | AIP000427 | AIP000427 | AIP000427 | No | AIP000427 | Nelson TS Recofiguration-Replace T1/T2 DESN with new DESN | 0 |  | Western Zone Station/Yard Investments | James.Mardegan@HydroOne.com | mark.truchanowicz@hydroone.com | System Renewal | Hamilton Niagara | 0 | 01 - Agreement (current/future) | Required | Project | ACTN EMPP | Executing | Executing |  | 9752750.2003 | 302422.3572 | -1.9165 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12183516.2003 | 383539.3572 | 596291.8738 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.2097 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -14.3996 | 0 | -2430766 | -81117 | -596301 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43464 | [13 empty] | FALSE |  | 14 | 2 | Alternative 1
20585 | CSO Service Enhancements - Settlements | N.D.M.4.01 | 4175 | 202 | CUSTOMER CARE SERVICES | UNPLND |  |  | Yes |  |  |  |  | Customer Care Services Dx | Imran.Merali@HydroOne.com | [6 empty] | Program | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20586 | London Transmission Lines Facility | N.C.C.1.50 | 7236 | 215 | FACILITIES & REAL ESTATE | UNPLND |  |  | Yes |  |  |  |  | Real Estate Facilities | cindy.copp@hydroone.com | [6 empty] | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20587 | London Fleet Maintenance Facility | N.C.C.1.50 | 7236 | 215 | FACILITIES & REAL ESTATE | UNPLND |  |  | Yes |  |  |  |  | Real Estate Facilities | cindy.copp@hydroone.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20588 | Wilhaven DS —B Switches | N.D.C.2.02 | 7700 | 203 | PROJECT DELIVERY | 3875.1 |  |  | Yes |  |  |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20592 | Larchwood TS EOL Asset Replacement Program | N.T.C.1.08 | 7700 | 203 | PROJECT DELIVERY | AIP000424 |  | AIP000424 | Yes | AIP000424 |  |  |  | System Re-investment | James.Mardegan@HydroOne.com | [6 empty] | Program | ACCP EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20593 | Timmins TS EOL 115kV Asset Replacement Project | N.T.C.1.08 | 7700 | 203 | PROJECT DELIVERY | AIP000446 |  | AIP000446 | Yes | AIP000446 |  |  |  | System Re-investment | James.Mardegan@HydroOne.com | [6 empty] | Project | EMPP ACTN | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20594 | Aylmer TS EOL Asset Replacement | N.T.C.1.08 | 7700 | 203 | PROJECT DELIVERY | AIP000385 |  | AIP000385 | Yes | AIP000385 |  |  |  | System Re-investment | James.Mardegan@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20598 | Carlton TS: T1, T4 & Swyd Refurb. and Reconfig. | N.T.C.1.41 | 7700 | 203 | PROJECT DELIVERY | AIP000394 | AIP000394 | AIP000394 | No | AIP000394 | Carlton TS: T1, T4 & Switchyard Refurbishment and Reconfiguration | SR-02 | Station Reinvestment Projects | Hamilton/Niagara Zone Station/Yard Investments | James.Mardegan@HydroOne.com | mark.truchanowicz@hydroone.com | System Renewal | Hamilton Niagara | 0 | 02 - Expectation (no agreement) | 0 | Project | ACTN BEST | Short Term Planning | Short Term Planning |  | 662895.59 | 1830200.4912 | 12171185.1135 | 4750316.8595 | 0 | 0 | 0 | 0 | 0 | 0 | 712790.957 | 1967957.5175 | 13087295.821 | 5107867.5909 | 0 | 0 | 0 | 0 | 0 | 0 | -49895.367 | -137757.0262 | -916110.7075 | -357550.7314 | 0 | 0 | 0 | 0 | 0 | 0 | -7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43554 | 44560 | False |  | False |  | False |  | False | True | Customer (Alectra) was consulted on final station configuration to meet customer needs | False | False | False | False | FALSE |  | 8 | 2 | Switchyard Refurbishment and Reconfiguration
20600 | Burlington TS: ABCB Replacement Project | N.T.C.1.08 | 7700 | 203 | PROJECT DELIVERY | AIP000391 |  | AIP000391 | Yes | AIP000391 |  |  |  | System Re-investment | James.Mardegan@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20603 | Kemptville West DS F2 Relief | N.D.C.2.02 | 7374 | 205 | LINES | UNPLND |  |  | Yes |  |  |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | [6 empty] | Project | EMPP ACTN | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20604 | Cumberland DS F4 | N.D.C.2.02 | 7374 | 205 | LINES | AIP005650 | AIP005650 | AIP005650 | No | AIP005650 | Cumberland DS F4 | ISD-SS-02 | System Upgrades Driven by Load Growth | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Muhammad.Sabir@HydroOne.com | System Service | Eastern | Not Required | 03 - None (default) | Not Required | Project | DETL ACCP | Short Term Planning | Short Term Planning |  | 1232996.5414 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1401132.4334 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -168135.892 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42886 | 43373 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
20605 | Pickering 'A' SS - Station Re-Investment | N.T.C.1.08 | 7700 | 203 | PROJECT DELIVERY | AIP000434 |  | AIP000434 | Yes | AIP000434 |  |  |  | System Re-investment | James.Mardegan@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20607 | Gage TS: T3,T4,T5,T6, PCT & Switchyard Reconfig. | N.T.C.1.08 | 7700 | 203 | PROJECT DELIVERY | AIP000414 | AIP000414 | AIP000414 | No | AIP000414 | Gage TS: T3,T4,T5,T6, PCT & Switchyard Reconfiguration | SR-02 | Station Reinvestment Projects | System Re-investment | James.Mardegan@HydroOne.com | mark.truchanowicz@hydroone.com | System Renewal | Hamilton Niagara | Not Required | 02 - Expectation (no agreement) | 0 | Project | DETL AWRD | Short Term Planning | Short Term Planning |  | 2497360.7846 | 17502670.2885 | 6889013.079 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2685334.177 | 18820075.579 | 7407540.9452 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -187973.3924 | -1317405.2905 | -518527.8662 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43205 | 44150 | False |  | False |  | False |  | False | True | Reconfiguration of switchyard based on customer needs and decreased industrial loading | False | False | False | False | FALSE |  | 1 | 2 | Switchyard Reconfiguration (Accelerated)
20609 | Kirkland Lake TS T12 & T13 EOL Replment Program | N.T.C.1.17 | 7700 | 203 | PROJECT DELIVERY | AIP000560A | AIP000560 | AIP000560 | No | AIP000560 | Replace EOL Large Transformers Program | 0 |  | Power Transformers | James.Mardegan@HydroOne.com | peter.zhao@hydroone.com | System Renewal | 0 | 0 | 03 - None (default) | 0 | Program | ACCP EMPP | Executing | Short Term Planning | # of Transformers | 387607.0549 | 0 | 0.029484 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 416781.7795 | 0 | 0.031704 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -29174.7246 | 0 | -0.0022193 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -33.9098 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43084 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Vulnerable
20610 | Morrisburg TS 18M24 | N.D.C.2.02 | 7374 | 205 | LINES | UNPLND |  |  | Yes |  |  |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | [6 empty] | Project | EMPP ACTN | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20611 | St Lawrence TS 49M27 Extension | N.D.C.2.02 | 7374 | 205 | LINES | AIP000183A |  | AIP000183 | Yes | AIP000183 | (1) System upgrade driven by load growth |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Michael.Medeiros@HydroOne.com | System Service | 0 | 0 | 03 - None (default) | Not Required | Project | ACTN BEST | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20618 | Hawthorne TS: Uprate Short Circuit Capability | N.T.C.2.21 | 7700 | 203 | PROJECT DELIVERY | AIP000954 | AIP000954 | AIP000954 | No | AIP000954 | Hawthorne TS: Uprate Short Circuit Capability | 0 |  | Major Risk Mitigation | Robert.Reinmuller@HydroOne.com | Jean.Morneau@HydroOne.com | System Service | Eastern | Not Required | 03 - None (default) | Not Required | Project | ACTN EMPP | Executing | Executing |  | 1086852.2105 | 550048.0582 | 0.0098282 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1086852.2105 | 550048.0582 | 0.0098282 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43733 | [13 empty] | FALSE |  | 0 | 0 | Alternative 1
20619 | Bruce A 230kV- Replace Breakers & Upgrade Station | N.T.C.1.08 | 7700 | 203 | PROJECT DELIVERY | AIP000390 | AIP000390 | AIP000390 | No | AIP000390 | Bruce A TS 230 kV ABCB Station Refurbishment | SR-01 | Air Blast Circuit Breaker Replacement Projects | System Re-investment | James.Mardegan@HydroOne.com | Fred.Kouhdani@HydroOne.com | System Renewal | Western | 0 | 02 - Expectation (no agreement) | 0 | Project | ACTN EMPP | Executing | Executing |  | 11882513.8447 | 8299390.4641 | 51657.8523 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13680039.8447 | 9763710.9203 | 293147.2211 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -349850.4562 | -177900.3588 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3.3123 | 0 | -1797526 | -1114470 | -63589.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43805 | [13 empty] | FALSE |  | 2 | 0 | Alternative 1
20621 | John Transformer Station Reinvestment | N.T.C.1.43 | 7700 | 203 | PROJECT DELIVERY | AIP000421 | AIP000421 | AIP000421 | No | AIP000421 | John TS: HV/LV Station Rebuild | SR-08 | John Transformer Station Reinvestment Project | Greater Toronto Area Zone Station/Yard Investments | James.Mardegan@HydroOne.com | michael.xavier@hydroone.com | System Renewal | Greater Toronto Area | TBD | 01 - Agreement (current/future) | Required | Project | BEST init | Short Term Planning | Short Term Planning |  | 0 | 24474857.3508 | 3045592.0845 | 24712219.9474 | 65100279.0525 | 56151306.54 | 14500000.16 | 0 | 0 | 0 | 0 | 26317050.9148 | 3274830.1984 | 26572279.5134 | 70000300.0564 | 60377748.9678 | 15591398 | 0 | 0 | 0 | 0 | -1842193.564 | -229238.1139 | -1860059.5659 | -4900021.004 | -4226442.4277 | -1091397.84 | 0 | 0 | 0 | -7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43959 | 45590 | False |  | False |  | False |  | False | False |  | False | False | False | False | TRUE | This investment is required to maintain reliability in downtown Toronto. This station supplies citical loads in Toronto (stock exchange etc). Ongoing co-ordination of this project with THESL and IESO. | 0 | 0 | Component Replacements
20625 | Leaside TS: 27.6kV Switchyard & Component Replace. | N.T.C.1.43 | 7700 | 203 | PROJECT DELIVERY | AIP000425 | AIP000425 | AIP000425 | No | AIP000425 | Leaside TS: 27.6kV Yard & Component Replacements | SR-06 | Load Station Switchgear and Ancillary Equipment Replacement Projects | Greater Toronto Area Zone Station/Yard Investments | James.Mardegan@HydroOne.com | michael.xavier@hydroone.com | System Renewal | Greater Toronto Area | Not Required | 01 - Agreement (current/future) | Not Required | Project | ACCP EMPP | Executing | Executing |  | 8883661.0098 | 7683966.9618 | 8280203.8937 | 662779.8484 | 0 | 0 | 0 | 0 | 0 | 0 | 9332330.7578 | 8158285.9101 | 8756077.6806 | 662779.8484 | 0 | 0 | 0 | 0 | 0 | 0 | -448669.748 | -474318.9483 | -475873.787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -5.1903 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43021 | 44180 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Component Replacements
20626 | Markham Clegg Rd HVAC Replacement 2010 | N.D.C.1.50 | 7236 | 215 | FACILITIES & REAL ESTATE | UNPLND |  |  | Yes |  |  |  |  | Real Estate Facilities | cindy.copp@hydroone.com | [6 empty] | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20629 | CTS Service Equipment | N.C.C.1.40 | 7241 | 201 | CENTRAL TOOLS SRVCS | AIP000018 | AIP000018 | AIP000018 | No | AIP000018 | CTS Service Equipment | 0 |  | Work Equipment | Mike.Tanaskovic@HydroOne.com | Farinaz.Yousefi@HydroOne.com | General Plant | 0 | 0 | 03 - None (default) | 0 | Program | ACTN EMPP | Executing | Short Term Planning | Retainer | 300000.12 | 298716.8209 | 296088.77 | 292480.5694 | 288842.7721 | 286303.3435 | 0 | 0 | 0 | 0 | 300000.12 | 298716.8209 | 296088.77 | 292480.5694 | 288842.7721 | 286303.3435 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | False |  | False | False | False | False | TRUE | All the purchases from Megger and Menta and TVC canada– P&C mandated NERC NPCC&TSC Regulation. Ministry regulations such as CSA 225, CVOR regulations. | 0 | 0 | Asset Optimal
20630 | Tillsonburg TS: M2 feeder, STATCOM unit | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000194 |  | AIP000194 | Yes | AIP000194 | Distance Limitation Mitigation Work (E&T) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | Not Required | 03 - None (default) | Not Required | Project | DETL ACTN | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20631 | Abandoned Equipment Removals Program | N.T.C.1.18 | 7700 | 203 | PROJECT DELIVERY | AIP000565 |  | AIP000565 | Yes | AIP000565 |  |  |  | Other Power Equipment | James.Mardegan@HydroOne.com | [6 empty] | Program | EMPP ACCP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20633 | Stations Service Equipment | N.C.C.1.40 | 7370 | 206 | TX LINES AND STATIONS | AIP000025 | AIP000025 | AIP000025 | No | AIP000025 | Stations Service Equipment | 0 |  | Work Equipment | Mike.Tanaskovic@HydroOne.com | Farinaz.Yousefi@HydroOne.com | General Plant | 0 | 0 | 03 - None (default) | 0 | Program | ACTN EMPP | Executing | Short Term Planning | 206-CC1XX | 2120000 | 2110932.2013 | 2092360.6416 | 2066862.6516 | 2041156.4059 | 2023210.4087 | 0 | 0 | 0 | 0 | 2120000 | 2110932.2013 | 2092360.6416 | 2066862.6516 | 2041156.4059 | 2023210.4087 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | False |  | False | False | False | False | TRUE | All the purchases from Megger and Menta and TVC canada– P&C mandated NERC NPCC&TSC Regulation. Ministry regulations such as CSA 225, CVOR regulations. | 0 | 0 | Asset Optimal
20634 | CMS Service Equipment | N.C.C.1.40 | 7370 | 206 | TX LINES AND STATIONS | AIP000016 | AIP000016 | AIP000016 | No | AIP000016 | CMS Service Equipment | 0 |  | Work Equipment | Mike.Tanaskovic@HydroOne.com | Farinaz.Yousefi@HydroOne.com | General Plant | 0 | 0 | 03 - None (default) | 0 | Program | EMPP ACTN | Executing | Short Term Planning | 206-CC1XX | 300000.12 | 896150.4628 | 888266.3101 | 877441.7083 | 866528.5474 | 858910.1451 | 0 | 0 | 0 | 0 | 300000.12 | 896150.4628 | 888266.3101 | 877441.7083 | 866528.5474 | 858910.1451 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | False |  | False | False | False | False | TRUE | All the purchases from Megger and Menta and TVC canada– P&C mandated NERC NPCC&TSC Regulation. Ministry regulations such as CSA 225, CVOR regulations. | 0 | 0 | Asset Optimal
20636 | Port Arthur TS #1: PCT & Component Replacement | N.T.C.1.45 | 7700 | 203 | PROJECT DELIVERY | AIP000437 | AIP000437 | AIP000437 | No | AIP000437 | Port Arthur TS #1: PCT & Component Replacement | SR-06 | Load Station Switchgear and Ancillary Equipment Replacement Projects | Northern Zone Station/Yard Investments | James.Mardegan@HydroOne.com | Donald.Mastrangelo@HydroOne.com | System Renewal | Northern | Not Required | 03 - None (default) | Not Required | Project | init | Short Term Planning | Short Term Planning |  | 0 | 794009.9194 | 1724368.8309 | 11332449.2437 | 11305513.8621 | 2841838.8674 | 0 | 0 | 0 | 0 | 0 | 853774.1069 | 1854160.0332 | 12185429.2943 | 12156466.5183 | 3055740.7177 | 0 | 0 | 0 | 0 | 0 | -59764.1875 | -129791.2023 | -852980.0506 | -850952.6563 | -213901.8502 | 0 | 0 | 0 | 0 | -7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43868 | 45076 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Component Replacement
20638 | RichviewTS ABCB 230kV Tx Station Re-Invest Project | N.T.C.1.08 | 7700 | 203 | PROJECT DELIVERY | AIP000438 | AIP000438 | AIP000438 | No | AIP000438 | Richview TS 230kV ABCB Station Refurbishment | SR-01 | Air Blast Circuit Breaker Replacement Projects | System Re-investment | James.Mardegan@HydroOne.com | michael.xavier@hydroone.com | System Renewal | Greater Toronto Area | 0 | 03 - None (default) | 0 | Project | EMPP ACCP | Executing | Executing |  | 10283770.5204 | 7147532.0311 | 0.049141 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10964394.9964 | 7147532.0311 | 0.049141 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -680624.476 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3.7048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43814 | [13 empty] | FALSE |  | 0 | 0 | Alternative 1
20640 | Fleet Service Equipment | N.C.C.1.40 | 7818 | 219 | FLEET | AIP000021 | AIP000021 | AIP000021 | No | AIP000021 | Fleet Service Equipment | 0 |  | Work Equipment | Mike.Tanaskovic@HydroOne.com | Farinaz.Yousefi@HydroOne.com | General Plant | 0 | 0 | 03 - None (default) | 0 | Program | ACCP EMPP | Executing | Short Term Planning | Retainer | 100000 | 99572.2736 | 98696.2567 | 97493.4841 | 96280.9625 | 95434.4478 | 0 | 0 | 0 | 0 | 100000 | 99572.2736 | 98696.2567 | 97493.4841 | 96280.9625 | 95434.4478 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | False |  | False | False | False | False | TRUE | All the purchases from Megger and Menta and TVC canada– P&C mandated NERC NPCC&TSC Regulation. Ministry regulations such as CSA 225, CVOR regulations. | 0 | 0 | Asset Optimal
20641 | Toronto -Spadina Subway Tunneling_Recoverable | N.T.C.1.14 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Third Party Transmission System Modifications | john.boldt@HydroOne.com | [6 empty] | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20642 | AED Implementation | N.C.M.3.03 | 7054 | 209 | HEALTH, SAFETY & ENV | UNPLND |  |  | Yes |  |  |  |  | Environment Health and Safety | welchw@hydroone.com | [6 empty] | Program | AWRD EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20646 | HS&E Service Equipment | N.C.C.1.40 | 4051 | 209 | HEALTH, SAFETY & ENV | AIP000023 | AIP000023 | AIP000023 | No | AIP000023 | HS&E Service Equipment | 0 |  | Work Equipment | Mike.Tanaskovic@HydroOne.com | Farinaz.Yousefi@HydroOne.com | General Plant | 0 | 0 | 03 - None (default) | 0 | Program | EMPP AWRD | Executing | Short Term Planning | 209-CC1XX | 300000.12 | 298716.8209 | 296088.77 | 292480.5694 | 288842.7721 | 286303.3435 | 0 | 0 | 0 | 0 | 300000.12 | 298716.8209 | 296088.77 | 292480.5694 | 288842.7721 | 286303.3435 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | False |  | False | False | False | False | TRUE | All the purchases from Megger and Menta and TVC canada– P&C mandated NERC NPCC&TSC Regulation. Ministry regulations such as CSA 225, CVOR regulations. | 0 | 0 | Asset Optimal
20647 | Provincial Lines Service Equipment | N.C.C.1.40 | 7374 | 205 | LINES | AIP000024 | AIP000024 | AIP000024 | No | AIP000024 | Provincial Lines Service Equipment | 0 |  | Work Equipment | Mike.Tanaskovic@HydroOne.com | Farinaz.Yousefi@HydroOne.com | General Plant | 0 | 0 | 03 - None (default) | 0 | Program | ACTN EMPP | Executing | Short Term Planning | 205-1533 | 600000 | 597433.7614 | 592177.7769 | 584961.2558 | 577685.7753 | 572606.687 | 0 | 0 | 0 | 0 | 600000 | 597433.7614 | 592177.7769 | 584961.2558 | 577685.7753 | 572606.687 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | False |  | False | False | False | False | TRUE | All the purchases from Megger and Menta and TVC canada– P&C mandated NERC NPCC&TSC Regulation. Ministry regulations such as CSA 225, CVOR regulations. | 0 | 0 | Asset Optimal
20648 | Forestry Service Equipment | N.C.C.1.40 | 7362 | 204 | FORESTRY | AIP000022 | AIP000022 | AIP000022 | No | AIP000022 | Forestry Service Equipment | 0 |  | Work Equipment | Mike.Tanaskovic@HydroOne.com | Farinaz.Yousefi@HydroOne.com | General Plant | 0 | 0 | 03 - None (default) | 0 | Program | ACCP EMPP | Executing | Short Term Planning | 204-CC1XX | 160313.92 | 159628.2151 | 158223.838 | 156295.8057 | 154351.8238 | 152695.1165 | 0 | 0 | 0 | 0 | 160313.92 | 159628.2151 | 158223.838 | 156295.8057 | 154351.8238 | 152695.1165 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | False |  | False | False | False | False | TRUE | All the purchases from Megger and Menta and TVC canada– P&C mandated NERC NPCC&TSC Regulation. Ministry regulations such as CSA 225, CVOR regulations. | 0 | 0 | Asset Optimal
20651 | Circuit Breakers - HV SF6 ABB AHMA Drive Rebuild | N.T.M.1.16 | 7370 | 206 | TX LINES AND STATIONS | AIP001044B | AIP001044 | AIP001044 | No | AIP001044 | Circuit Breaker Maintenance and Refurbishment | 0 |  | Power Equipment | Mike.Tanaskovic@HydroOne.com | kristoffer.hammel@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | EMPP ACTN | Executing | Short Term Planning | # of Breakers | 937250.0694 | 677497.5665 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 937250.0694 | 677497.5665 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | True | OPG Darlington has provided their overhaul schedule for their generating units, with the expectation that we will complete the refurbishment of the breakers within the timing of the unit overhaul, in order to minimize requirements for outages for performing this type of maintenance in the future. | False | False | False | True | FALSE |  | 0 | 0 | Intermediate (Modified - Tx Decision)
20652 | Circuit Breakers -HV SF6 Areva FX32/42 Ram Rebuild | N.T.M.1.16 | 7370 | 206 | TX LINES AND STATIONS | AIP001045 | AIP001045 | AIP001045 | No | AIP001045 | Circuit Breakers - HV SF6 Areva FX32/42 Ram Rebuild | 0 |  | Power Equipment | Mike.Tanaskovic@HydroOne.com | kristoffer.hammel@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | ACTN EMPP | Executing | Short Term Planning | Breakers | 316674.0471 | 0 | 0 | 309779.0718 | 309926.9231 | 350087.9348 | 0 | 0 | 0 | 0 | 316674.0471 | 0 | 0 | 309779.0718 | 309926.9231 | 350087.9348 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Vulnerable Modified (Tx Decision)
20658 | Essa TS BULK; ABCB & Component Replacement | N.T.C.1.42 | 7700 | 203 | PROJECT DELIVERY | AIP000412 | AIP000412 | AIP000412 | No | AIP000412 | Essa TS BULK; ABCB & Component Replacement | SR-01 | Air Blast Circuit Breaker Replacement Projects | Central Zone Station/Yard Investments | James.Mardegan@HydroOne.com | Fred.Kouhdani@HydroOne.com | System Renewal | Central | Not Required | 03 - None (default) | Not Required | Project | init | Short Term Planning | Short Term Planning |  | 152718.2088 | 382007.0325 | 442562.5077 | 5890001.387 | 17454900.0737 | 11470550.175 | 12440610 | 12812610.12 | 0 | 0 | 164213.1278 | 410760.25 | 475873.6642 | 6333334.8247 | 18768709.7566 | 12333924.9193 | 13377000 | 13777000.12 | 0 | 0 | -11494.9189 | -28753.2175 | -33311.1565 | -443333.4377 | -1313809.683 | -863374.7444 | -936390 | -964390 | 0 | 0 | -7 | 7.00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44048 | 46006 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | ALT 1-Component Replacement- 1-3PH AUTO
20659 | Cherrywood ABCB Replacement Project | N.T.C.1.08 | 7700 | 203 | PROJECT DELIVERY | AIP000397 |  | AIP000397 | Yes | AIP000397 |  |  |  | System Re-investment | James.Mardegan@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20666 | Runnymede TS, EOL T3 T4 Asset Replacement Project | N.T.C.1.08 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | System Re-investment | James.Mardegan@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20667 | Sheppard TS: T3, T4, PCT, LV Yard & Component Repl | N.T.C.1.42 | 7700 | 203 | PROJECT DELIVERY | AIP000441 | AIP000441 | AIP000441 | No | AIP000441 | Sheppard TS: T3, T4, PCT, LV Yard & Component Replacements | SR-02 | Station Reinvestment Projects | Central Zone Station/Yard Investments | James.Mardegan@HydroOne.com | michael.xavier@hydroone.com | System Renewal | Central | Not Required | 03 - None (default) | Required | Project | ACCP EMPP | Executing | Executing |  | 5025513.9893 | 23147153.6167 | 8280346.6939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5403778.4831 | 24889412.491 | 8903598.5955 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -378264.4938 | -1742258.8744 | -623251.9017 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43046 | 44150 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Component Replacements
20668 | ArcFM Business Process Support | N.D.M.2.02 | 7374 | 205 | LINES | AIP000288 | AIP000288 | AIP000288 | No | AIP000288 | ArcFM Business Process Support |  |  | Engineering and Technical Services | ted.lyberogiannis@HydroOne.com | Helen.Guo@HydroOne.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | ACCP EMPP | Executing | Short Term Planning | Retainer | 353940.266 | 364742.9341 | 373668.42 | 384832.3155 | 396713.1217 | 0 | 0 | 0 | 0 | 0 | 353940.266 | 364742.9341 | 373668.42 | 384832.3155 | 396713.1217 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Demand
20669 | Care Management | N.C.M.3.03 | 7054 | 209 | HEALTH, SAFETY & ENV | AIP000118A | AIP000118 | AIP000118 | No | AIP000118 | Health & Rehab Services | 0 |  | Environment Health and Safety | welchw@hydroone.com | welchw@hydroone.com | System O&M | N/A | 0 | 03 - None (default) | 0 | Program | EMPP AWRD | Executing | Short Term Planning | Retainer | 536428.64 | 547157.24 | 558100.4 | 569262.32 | 580647.68 | 539999.88 | 0 | 0 | 0 | 0 | 536428.64 | 547157.24 | 558100.4 | 569262.32 | 580647.68 | 539999.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | True | Care Management - Contracted service for 3rd party to manage all Hydro One's major medical absences to ensure that employees receive timely treatment, the absences are warranted and employees return to work in a timely manner. | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Optimal - (Modified-Tx Decision)
20670 | Middleport ABCB Replacement Project | N.T.C.1.41 | 7700 | 203 | PROJECT DELIVERY | AIP000429 | AIP000429 | AIP000429 | No | AIP000429 | Middleport TS; ABCB Station Refurbishment | SR-01 | Air Blast Circuit Breaker Replacement Projects | Hamilton/Niagara Zone Station/Yard Investments | James.Mardegan@HydroOne.com | Fred.Kouhdani@HydroOne.com | System Renewal | Hamilton Niagara | Not Required | 03 - None (default) | TBD | Project | AWRD LLTM | Short Term Planning | Short Term Planning |  | 1879351.9467 | 13690495.5526 | 29187890.0397 | 20496571.0759 | 20248066.8556 | 16633455.3557 | 0 | 0 | 0 | 0 | 2020808.5449 | 14720962.9598 | 31384827.9997 | 22039323.7375 | 21772114.8985 | 17885435.8664 | 0 | 0 | 0 | 0 | -141456.5981 | -1030467.4072 | -2196937.96 | -1542752.6616 | -1524048.0429 | -1251980.5106 | 0 | 0 | 0 | 0 | -7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43371 | 45230 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Alternative 1- Station Refurbishment
20673 | Kent TS-M2-ID274-MacLeod Windmill-Tx | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | [6 empty] | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20675 | Designated Substances | N.C.M.3.03 | 7054 | 209 | HEALTH, SAFETY & ENV | AIP000125C |  | AIP000125 | Yes | AIP000125 | Strategy & Technical Services |  |  | Environment Health and Safety | welchw@hydroone.com | welchw@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | AWRD EMPP | Executing | Short Term Planning | Retainer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20676 | E-Learning | N.C.M.3.03 | 7054 | 209 | HEALTH, SAFETY & ENV | AIP000121A | AIP000121 | AIP000121 | No | AIP000121 | Learning Management | 0 |  | Environment Health and Safety | welchw@hydroone.com | welchw@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | AWRD EMPP | Executing | Short Term Planning | Retainer | 448454.44 | 486970 | 531311.56 | 578370.64 | 627099.48 | 580000.08 | 0 | 0 | 0 | 0 | 448454.44 | 486970 | 531311.56 | 578370.64 | 627099.48 | 580000.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | True | E-Learning - contracted service for external company to create e-learning packages for use by Hydro One employees across the province. Modules will continue to be developed/refreshed to enable employees to be trained remotely and allow for timely and immediate delivery of required training. | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Optimal - (Modified-Tx Decision)
20677 | Health and Wellness | N.C.M.3.03 | 7054 | 209 | HEALTH, SAFETY & ENV | AIP000118B | AIP000118 | AIP000118 | No | AIP000118 | Health & Rehab Services | 0 |  | Environment Health and Safety | welchw@hydroone.com | welchw@hydroone.com | System O&M | N/A | 0 | 03 - None (default) | 0 | Program | EMPP AWRD | Executing | Short Term Planning | Retainer | 221451.7 | 227889 | 234454.79 | 241152.11 | 247983.11 | 240000 | 0 | 0 | 0 | 0 | 221451.7 | 227889 | 234454.79 | 241152.11 | 247983.11 | 240000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | True | Care Management - Contracted service for 3rd party to manage all Hydro One's major medical absences to ensure that employees receive timely treatment, the absences are warranted and employees return to work in a timely manner. | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Optimal - (Modified-Tx Decision)
20678 | ICM Upgrades and Licence Fee | N.C.M.3.03 | 7054 | 209 | HEALTH, SAFETY & ENV | AIP005020 |  | AIP005020 | Yes | AIP005020 | Safety System Evaluation |  |  | Environment Health and Safety | welchw@hydroone.com | welchw@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | AWRD EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20679 | Instructor Certification | N.C.M.3.03 | 7054 | 209 | HEALTH, SAFETY & ENV | UNPLND |  |  | Yes |  |  |  |  | Environment Health and Safety | welchw@hydroone.com | [6 empty] | Program | AWRD EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20680 | ISO 14001 / OHSAS 18001 Registration | N.C.M.3.03 | 7054 | 209 | HEALTH, SAFETY & ENV | AIP000125A | AIP000125 | AIP000125 | No | AIP000125 | Strategy & Technical Services | 0 |  | Environment Health and Safety | welchw@hydroone.com | welchw@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | EMPP AWRD | Executing | Short Term Planning | Retainer | 150200 | 246220.68 | 223240.16 | 227705 | 232259 | 229999.88 | 0 | 0 | 0 | 0 | 150200 | 246220.68 | 223240.16 | 227705 | 232259 | 229999.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | True | 18001 Registration - Contracted service for auditing of Hydro One's HSE Management System for the maintainance of Hydro One's 18001 registration. Additional contracted support to maintain HSEMS legal registry | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Optimal - (Modified - Tx Decision)
20681 | Journey to Zero | N.C.M.3.03 | 7054 | 209 | HEALTH, SAFETY & ENV | AIP000120 | AIP000120 | AIP000120 | No | AIP000120 | Journey to Zero | 0 |  | Environment Health and Safety | welchw@hydroone.com | welchw@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | AWRD EMPP | Executing | Short Term Planning | Retainer | 19000 | 25000.12 | 25000.12 | 55999.92 | 119000 | 24999.88 | 0 | 0 | 0 | 0 | 19000 | 25000.12 | 25000.12 | 55999.92 | 119000 | 24999.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Optimum 1 (Modified-Tx Decision)
20682 | Learning Management System | N.C.M.3.03 | 7054 | 209 | HEALTH, SAFETY & ENV | AIP000121B | AIP000121 | AIP000121 | No | AIP000121 | Learning Management | 0 |  | Environment Health and Safety | welchw@hydroone.com | welchw@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | AWRD EMPP | Executing | Short Term Planning | Retainer | 10728.52 | 10943.2 | 11161.96 | 11385.16 | 11612.92 | 11845.24 | 0 | 0 | 0 | 0 | 10728.52 | 10943.2 | 11161.96 | 11385.16 | 11612.92 | 11845.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | True | E-Learning - contracted service for external company to create e-learning packages for use by Hydro One employees across the province. Modules will continue to be developed/refreshed to enable employees to be trained remotely and allow for timely and immediate delivery of required training. | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Optimal - (Modified-Tx Decision)
20683 | Pandemic Planning | N.C.M.3.03 | 7054 | 209 | HEALTH, SAFETY & ENV | AIP000118D |  | AIP000118 | Yes | AIP000118 | Health & Rehab Services |  |  | Environment Health and Safety | welchw@hydroone.com | welchw@hydroone.com | System O&M | N/A | 0 | 03 - None (default) | 0 | Program | EMPP AWRD | Executing | Short Term Planning | Retainer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20684 | Public Safety Educational Materials | N.C.M.3.03 | 7054 | 209 | HEALTH, SAFETY & ENV | AIP000122A | AIP000122 | AIP000122 | No | AIP000122 | Public Electrical Safety Presentations | 0 |  | Environment Health and Safety | welchw@hydroone.com | welchw@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | AWRD EMPP | Executing | Short Term Planning | Assumption - program covers employees attending schools, fairs, plowing match, etc. to deliver safety messages. Includes production of materials used for presentations. | 30000 | 30000.12 | 29999.88 | 30000 | 30000 | 30000 | 0 | 0 | 0 | 0 | 30000 | 30000.12 | 29999.88 | 30000 | 30000 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Optimal - (Modified-Tx Decision)
20686 | Specialist HSE Resources | N.C.M.3.03 | 7054 | 209 | HEALTH, SAFETY & ENV | AIP000124 | AIP000124 | AIP000124 | No | AIP000124 | Specialist HSE Resources | 0 |  | Environment Health and Safety | welchw@hydroone.com | welchw@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | EMPP AWRD | Executing | Short Term Planning | Retainer | 120000 | 159999.88 | 150000 | 150000 | 150000 | 109999.96 | 0 | 0 | 0 | 0 | 120000 | 159999.88 | 150000 | 150000 | 150000 | 109999.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Optimal (Challenge Session)
20687 | Species at Risk | N.C.M.3.03 | 7054 | 209 | HEALTH, SAFETY & ENV | AIP000125B | AIP000125 | AIP000125 | No | AIP000125 | Strategy & Technical Services | 0 |  | Environment Health and Safety | welchw@hydroone.com | welchw@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | AWRD EMPP | Executing | Short Term Planning | Retainer | 134107.16 | 138977.92 | 143989.92 | 149146.76 | 154452.28 | 150000.12 | 0 | 0 | 0 | 0 | 134107.16 | 138977.92 | 143989.92 | 149146.76 | 154452.28 | 150000.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | True | 18001 Registration - Contracted service for auditing of Hydro One's HSE Management System for the maintainance of Hydro One's 18001 registration. Additional contracted support to maintain HSEMS legal registry | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Optimal - (Modified - Tx Decision)
20695 | Brant TS M14 bypass to St George | N.D.C.2.02 | 7374 | 205 | LINES | UNPLND |  |  | Yes |  |  |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | [6 empty] | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20700 | Red Lake TS-M6-Two Feathers Forest Prdt ID-1777-TX | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20703 | HV UG Cable - Diagnostics | N.T.M.1.21 | 7370 | 206 | TX LINES AND STATIONS | AIP001120 |  | AIP001120 | Yes | AIP001120 |  |  |  | Underground Cables | hassan.hamzeh@hydroone.com | [6 empty] | Program | EMPP ACTN | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20708 | Cornerstone Phase 4 - CIS - Capital | N.D.C.2.10 | 7193 | 227 | CORNERSTONE | UNPLND |  |  | Yes | [12 empty] | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20709 | Cornerstone Phase 4 - CIS - OM&A | N.D.M.2.10 | 7193 | 227 | CORNERSTONE | UNPLND |  |  | Yes | [12 empty] | Project | init EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20712 | SONET and Microwave System Device Replacement | N.T.C.1.25 | 7700 | 203 | PROJECT DELIVERY | AIP000658A | AIP000658 | AIP000658 | No | AIP000658 | SONET and Microwave Device Replacement | 0 |  | Auxiliary Telecommunication Equipment | Miroslav.Kostic@HydroOne.com | Sheraz.Majid@HydroOne.com | System Renewal | 0 | 0 | 03 - None (default) | 0 | Program | ACCP EMPP | Executing | Short Term Planning | # of Devices | 1488762.1447 | 1534694.0584 | 1552430.2725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1534806.3348 | 1582158.8231 | 1600443.5799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -46044.19 | -47464.7647 | -48013.3074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | True | reliability requirements to need TSC, NPCC, NERC | False |  | True | False |  | False | False | False | False | FALSE |  | 0 | 0 | Asset Optimal
20713 | PLC Device Replacement | N.T.C.1.25 | 7700 | 203 | PROJECT DELIVERY | AIP000656 |  | AIP000656 | Yes | AIP000656 |  |  |  | Auxiliary Telecommunication Equipment | Miroslav.Kostic@HydroOne.com | [6 empty] | Program | EMPP ACCP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20717 | BPS Compliance - Budget Placeholder | N.T.C.1.19 | 7700 | 203 | PROJECT DELIVERY | AIP000589 |  | AIP000589 | Yes | AIP000589 |  |  |  | Protection Control & Metering Equip | Miroslav.Kostic@HydroOne.com | [6 empty] | Program | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20720 | University of Waterloo- MOU | N.T.M.2.22 | 4230 | 213 | PLANNING | AIP001179B |  | AIP001179 | Yes | AIP001179 | [11 empty] | Program | AWRD EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20725 | PALC Replacements | N.T.C.1.19 | 7700 | 203 | PROJECT DELIVERY | AIP000609B |  | AIP000609 | Yes | AIP000609 |  |  |  | Protection Control & Metering Equip | Miroslav.Kostic@HydroOne.com | [6 empty] | Program | EMPP HOLD | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20726 | PSR Replacement - Budget Placeholder | N.T.C.1.19 | 7700 | 203 | PROJECT DELIVERY | AIP000609C |  | AIP000609 | Yes | AIP000609 |  |  |  | Protection Control & Metering Equip | Miroslav.Kostic@HydroOne.com | [6 empty] | Program | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20730 | Fiber Cable Condition Monitoring System | N.T.C.1.25 | 7700 | 203 | PROJECT DELIVERY | AIP000645 |  | AIP000645 | Yes | AIP000645 |  |  |  | Auxiliary Telecommunication Equipment | Miroslav.Kostic@HydroOne.com | [6 empty] | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20731 | Hinchey TS: Add switching to idle trfr windings | N.T.C.2.11 | 7700 | 203 | PROJECT DELIVERY | AIP000786 |  | AIP000786 | Yes | AIP000786 |  |  |  | Load Customer Connection | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20732 | Ottawa-Relocation & Raising of H9A_Recoverable | N.T.C.1.14 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Third Party Transmission System Modifications | john.boldt@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20735 | ITMC Backup Centre re-fresh | N.T.C.1.25 | 4048 | 213 | PLANNING | UNPLND |  |  | Yes |  |  |  |  | Auxiliary Telecommunication Equipment | Miroslav.Kostic@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20736 | Demand Capital Program | N.T.C.1.25 | 7370 | 206 | TX LINES AND STATIONS | AIP000644 | AIP000644 | AIP000644 | No | AIP000644 | Demand Capital - Telecom | 0 |  | Auxiliary Telecommunication Equipment | Miroslav.Kostic@HydroOne.com | Sheraz.Majid@HydroOne.com | System Renewal | 0 | 0 | 03 - None (default) | 0 | Program | ACTN EMPP | Executing | Short Term Planning | # of Stations | 568750.0711 | 586297.5939 | 581444.2308 | 574458.8483 | 567474.4545 | 562829.8981 | 0 | 0 | 0 | 0 | 598684.2854 | 617155.362 | 612046.5587 | 604693.5245 | 597341.531 | 592452.5243 | 0 | 0 | 0 | 0 | -29934.2143 | -30857.7681 | -30602.3279 | -30234.6762 | -29867.0766 | -29622.6262 | 0 | 0 | 0 | 0 | -5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | True | NERC, transport canada, TSC | False |  | True | False |  | False | False | False | False | FALSE |  | 0 | 0 | Asset Optimal
20737 | Safety by Design | N.C.M.3.03 | 7054 | 209 | HEALTH, SAFETY & ENV | UNPLND |  |  | Yes |  |  |  |  | Environment Health and Safety | welchw@hydroone.com | [6 empty] | Program | EMPP AWRD | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20738 | Training Development | N.C.M.3.03 | 7054 | 209 | HEALTH, SAFETY & ENV | AIP000121C | AIP000121 | AIP000121 | No | AIP000121 | Learning Management | 0 |  | Environment Health and Safety | welchw@hydroone.com | welchw@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | AWRD EMPP | Executing | Short Term Planning | Retainer | 145908.64 | 151015.44 | 157384.32 | 162809 | 168387.76 | 160000 | 0 | 0 | 0 | 0 | 145908.64 | 151015.44 | 157384.32 | 162809 | 168387.76 | 160000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | True | E-Learning - contracted service for external company to create e-learning packages for use by Hydro One employees across the province. Modules will continue to be developed/refreshed to enable employees to be trained remotely and allow for timely and immediate delivery of required training. | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Optimal - (Modified-Tx Decision)
20742 | RTU Preventative Maintenance - Budget Placeholder | N.T.M.1.17 | 7370 | 206 | TX LINES AND STATIONS | AIP001085 | AIP001085 | AIP001085 | No | AIP001085 | RTU Preventive Maintenance | 0 |  | Protection Control & Metering Equipment | Miroslav.Kostic@HydroOne.com | Andrew.Webb@HydroOne.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | INSC | Short Term Planning | Short Term Planning | RTUs | 50568.8675 | 51305.5515 | 52452.3519 | 53655.9014 | 54768.9892 | 55904.6754 | 0 | 0 | 0 | 0 | 50568.8675 | 51305.5515 | 52452.3519 | 53655.9014 | 54768.9892 | 55904.6754 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Demand
20743 | Commerce Way TS feeder construction | N.D.C.2.02 | 7374 | 205 | LINES | UNPLND |  |  | Yes |  |  |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | [6 empty] | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20748 | Cobden TS M2 ID1237-Dx SQPV01 | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | 2 |  |  | Yes |  |  |  |  | Distribution Generation Connection | ryan.boudreau@HydroOne.com | [6 empty] | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20749 | Cobden TS M2 ID1237-Tx SQPV01 | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000928 |  | AIP000928 | Yes | AIP000928 |  |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | [6 empty] | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20751 | Meter Inventory Sustainment | N.D.C.1.09 | 7374 | 205 | LINES | AIP000173 |  | AIP000173 | Yes | AIP000173 | Sustainment of Meter Inventory | ISD-SA-02 | Metering Infrastructure Sustainment Program | Metering | Peter.Mitskos@HydroOne.com | Dominic.Consorti@HydroOne.com | System Access | 0 | 0 | 03 - None (default) | 0 | Program | EMPP ACTN | Executing | Short Term Planning | # of meters | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20752 | Crystal Falls TS M2 Crystal Falls Conn. ID-10 TX | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | 6009 |  |  | Yes |  |  |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20754 | Butternut DS F3 | N.D.C.2.02 | 7374 | 205 | LINES | UNPLND |  |  | Yes |  |  |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | [6 empty] | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20755 | Owen Sound Line Refurbishment - Stage 2 | N.D.C.1.07 | 7374 | 205 | LINES | AIP000152 |  | AIP000152 | Yes | AIP000152 | Large Sustainment Initiatives | ISD-SR-12 | Distribution Lines Sustainment Initiatives | Lines | emre.aydin@HydroOne.com | Alexander.Hamlyn@HydroOne.com | System Renewal | N/A | 0 | 03 - None (default) | 0 | Program | EMPP ACCP | Executing | Short Term Planning | # of projects | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20756 | Owen Sound Line Refurbishment - Stage 3 | N.D.C.1.07 | 7374 | 205 | LINES | AIP000152 |  | AIP000152 | Yes | AIP000152 | Large Sustainment Initiatives | ISD-SR-12 | Distribution Lines Sustainment Initiatives | Lines | emre.aydin@HydroOne.com | Alexander.Hamlyn@HydroOne.com | System Renewal | N/A | 0 | 03 - None (default) | 0 | Program | ACCP EMPP | Executing | Short Term Planning | # of projects | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20760 | Tx Lines - Annual ROW Inspections-NERC | N.T.M.1.07 | 7362 | 204 | FORESTRY | AIP001023 | AIP001023 | AIP001023 | No | AIP001023 | Annual Vegetation Patrol (AVP) | 0 |  | Rights of Way | hassan.hamzeh@hydroone.com | Shannon.O'Keefe@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | ACCP EMPP | Executing | Short Term Planning | # of KM | 494248.4177 | 505552.1505 | 506472.646 | 517568.0989 | 517758.5822 | 527878.3706 | 493244.36 | 0 | 0 | 0 | 494248.4177 | 505552.1505 | 506472.646 | 517568.0989 | 517758.5822 | 527878.3706 | 493244.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12300 | 12300 | 12300 | 12300 | 12300 | 12300 | 10400 | 0 | 0 | 0 | 0 | 0 | False |  | True | NERC standard FAC-003 requires that annual vegetatation patrols be conducted on all overhead transmission lines operating at a voltage greater than or equal to 200 kV. | False |  | False | False |  | False | True | False | False | FALSE |  | 0 | 0 | Intermediate (modified)
20764 | Placeholder for CAR DG Projects (E&PD) | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000199 | AIP000199 | AIP000199 | No | AIP000199 | Large Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 1249470.6562 | 1062165.4959 | 1083984.1059 | 1106002.531 | 1128766.7146 | 0 | 0 | 0 | 0 | 0 | 2673499.9462 | 2319293.5459 | 2422201.1259 | 2493042.681 | 2556004.9646 | 0 | 0 | 0 | 0 | 0 | -2.2204e-10 | 0 | 2.2204e-10 | -2.2204e-10 | 2.2204e-10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1424029.29 | -1257128.05 | -1338217.02 | -1387040.15 | -1427238.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43100 | 44926 | [13 empty] | FALSE |  | 0 | 0 | Critical Spend Plan
20768 | Placeholder for CAE DG Projects (E&PD) | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000195 | AIP000195 | AIP000195 | No | AIP000195 | Small Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 416368.5204 | 425182.0495 | 216878.9019 | 221539.6 | 226083.1377 | 0 | 0 | 0 | 0 | 0 | 2081008.5204 | 2123114.8295 | 1082824.5819 | 1104804.24 | 1127013.1377 | 0 | 0 | 0 | 0 | 0 | 0 | -2.2204e-10 | -8.3267e-11 | 1.1102e-10 | -1.3878e-10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1664640 | -1697932.78 | -865945.68 | -883264.64 | -900930 | 0 | 0 | 0 | 0 | 0 | 20 | 20 | 10 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 43100 | 44926 | [13 empty] | FALSE |  | 0 | 0 | Critical Spend Plan
20778 | Power Quality Monitoring (Lines) | N.D.C.2.03 | 7374 | 205 | LINES | UNPLND |  |  | Yes |  |  |  |  | Distribution Generation Connection | ryan.boudreau@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20790 | CEATI-Tx Annual Program | N.T.M.2.22 | 4230 | 213 | PLANNING | UNPLND |  |  | Yes | [12 empty] | Program | EMPP init | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20791 | University of Western Ontario- MOU | N.T.M.2.22 | 4230 | 213 | PLANNING | AIP001179C |  | AIP001179 | Yes | AIP001179 | [11 empty] | Program | AWRD EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20792 | Studies-Capacity Enhancement | N.T.M.2.22 | 4230 | 213 | PLANNING | AIP001177 |  | AIP001177 | Yes | AIP001177 | [11 empty] | Program | AWRD | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20794 | Clean Energy Initiatives | N.D.M.2.22 | 4230 | 213 | PLANNING | AIP000323 |  | AIP000323 | Yes | AIP000323 | [11 empty] | Program | EMPP AWRD | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20804 | Malden TS M12 - Extension | N.D.C.2.02 | 7374 | 205 | LINES | UNPLND |  |  | Yes |  |  |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20806 | Small Embedded Generation CIAs and Estimates | N.D.M.2.03 | 7374 | 205 | LINES | AIP000295 | AIP000295 | AIP000295 | No | AIP000295 | Small Embedded Generation - CIAs/Estimates |  |  | Distributed Generation Connections | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | EMPP ACCP | Executing | Short Term Planning | # of Estimates | 366957.7178 | 315598.9493 | 322499.7534 | 219780.6968 | 223875.3201 | 0 | 0 | 0 | 0 | 0 | 1069914.8378 | 912581.3493 | 931421.9134 | 634216.0568 | 646599.4401 | 0 | 0 | 0 | 0 | 0 | 5.5511e-11 | -5.5511e-11 | 0 | 5.5511e-11 | 2.7756e-11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -702957.12 | -596982.4 | -608922.16 | -414435.36 | -422724.12 | 0 | 0 | 0 | 0 | 0 | 180 | 150 | 150 | 100 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
20807 | Telserv Replacement | N.T.C.1.25 | 4048 | 213 | PLANNING | UNPLND |  |  | Yes |  |  |  |  | Auxiliary Telecommunication Equipment | Miroslav.Kostic@HydroOne.com | [6 empty] | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20813 | Recoverable - Toronto - 570 Bay St. | N.T.C.1.14 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Third Party Transmission System Modifications | john.boldt@HydroOne.com | [6 empty] | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20814 | Recoverable - Toronto - 580 Jarvis St. | N.T.C.1.14 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Third Party Transmission System Modifications | john.boldt@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20816 | PHEV Grid Impact/ Integration and PQ Studies | N.D.M.2.22 | 4230 | 213 | PLANNING | AIP000327 |  | AIP000327 | Yes | AIP000327 | [11 empty] | Project | EMPP AWRD | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20818 | Crosby TS M2 ID11950-DX Rideau Lakes | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000199 |  | AIP000199 | Yes | AIP000199 | Large Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20819 | Crosby TS M2 ID11950-TX Rideau Lakes | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20820 | SVC Studies- CEATI | N.D.M.2.22 | 4230 | 213 | PLANNING | UNPLND |  |  | Yes | [12 empty] | Program | AWRD | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20821 | Green Energy Impact Studies on Dx | N.D.M.2.22 | 4230 | 213 | PLANNING | UNPLND |  |  | Yes | [12 empty] | Program | AWRD EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20822 | Studies - Advanced Grid | N.D.M.2.22 | 4230 | 213 | PLANNING | AIP000322 |  | AIP000322 | Yes | AIP000322 | [11 empty] | Program | AWRD EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20823 | DVAR Study | N.D.M.2.22 | 4230 | 213 | PLANNING | UNPLND |  |  | Yes | [12 empty] | Project | AWRD | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20825 | Petawawa Craig DS F4 | N.D.C.2.02 | 7374 | 205 | LINES | UNPLND |  |  | Yes |  |  |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | [6 empty] | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20828 | Napanee Area Study | N.D.C.2.02 | 7374 | 205 | LINES | UNPLND |  |  | Yes |  |  |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20830 | Hawthorne TS: Replace 2 existing Transformers | N.T.C.2.02 | 7700 | 203 | PROJECT DELIVERY | AIP000699 | AIP000699 | AIP000699 | No | AIP000699 | Hawthorne TS: Replace 2 existing Transformers | 0 |  | Local Area Supply | Robert.Reinmuller@HydroOne.com | Jean.Morneau@HydroOne.com | System Service | Eastern | Not Required | 03 - None (default) | Not Required | Project | EMPP ACTN | Executing | Executing |  | 1036791.1982 | 763013.3523 | 2629904.1551 | 2233318.9641 | 0 | 0 | 0 | 0 | 0 | 0 | 1229529.7509 | 763013.3523 | 2629904.1551 | 2233318.9641 | 0 | 0 | 0 | 0 | 0 | 0 | -192738.5527 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2.776 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44377 | [13 empty] | FALSE |  | 0 | 0 | Alternative 1
20836 | T27P/T28P Protection Upgrade | N.T.C.1.19 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Protection Control & Metering Equip | Miroslav.Kostic@HydroOne.com | [6 empty] | Program | ACCP EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20842 | Security Operations Efficiency | N.T.C.1.29 | 838 | 212 | INFO SOLUTIONS DIVISION | UNPLND |  |  | Yes |  |  |  |  | NERC Cyber Security Compliance Readiness | lincoln.frost-hunt@hydroone.com | [6 empty] | Program | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20843 | Beachburg DS F2 ID 11250 -DX Fepro Solar | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | 2 |  |  | Yes |  |  |  |  | Distribution Generation Connection | ryan.boudreau@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20845 | Address New Vulnerabilities | N.T.C.1.29 | 7700 | 203 | PROJECT DELIVERY | AIP000673 |  | AIP000673 | Yes | AIP000673 |  |  |  | NERC Cyber Security Compliance Readiness | lincoln.frost-hunt@hydroone.com | [6 empty] | Program | ACCP EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20846 | Physical Security - Critical Stations (non CIP014) | N.T.C.1.29 | 7700 | 203 | PROJECT DELIVERY | AIP000678 | AIP000678 | AIP000678 | No | AIP000678 | Physical Security for Critical Stations (non CIP-014) High Criticality | SR-17 | Critical Station Physical Security Implementation (Non CIP-014) | NERC Cyber Security Compliance Readiness | lincoln.frost-hunt@hydroone.com | Sherry.Wilging@hydroone.com | System Renewal | 0 | 0 | 03 - None (default) | 0 | Project | DETL ACTN | Short Term Planning | Short Term Planning |  | 0 | 3925547.0802 | 3892720.5499 | 3844032.981 | 3796809.3371 | 3763869.6402 | 0 | 0 | 0 | 0 | 0 | 3925547.0802 | 3892720.5499 | 3844032.981 | 3796809.3371 | 3763869.6402 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43555 | 45275 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Non-CIP14 Critical Stations (High)
20847 | PSIT Cyber Sustainment | N.T.M.1.29 | 4514 | 212 | INFO SOLUTIONS DIVISION | AIP001145 | AIP001145 | AIP001145 | No | AIP001145 | PSIT Cyber Sustainment | 0 |  | NERC Cyber Security Compliance Readiness | lincoln.frost-hunt@hydroone.com | Sherry.Wilging@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | EMPP AWRD | Executing | Short Term Planning | Retainer | 6029830.6962 | 6046800.2311 | 6057810.0395 | 6071471.9294 | 6073706.4047 | 6075581.2468 | 0 | 0 | 0 | 0 | 6029830.6962 | 6046800.2311 | 6057810.0395 | 6071471.9294 | 6073706.4047 | 6075581.2468 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | True | CIP-002, 004, 005, 007, 009, 010, 011 | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Asset Optimal
20849 | User Access Management | N.T.M.1.29 | 838 | 212 | INFO SOLUTIONS DIVISION | AIP001139 | AIP001139 | AIP001139 | No | AIP001139 | User Access Management | 0 |  | NERC Cyber Security Compliance Readiness | lincoln.frost-hunt@hydroone.com | Sherry.Wilging@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | AWRD EMPP | Executing | Short Term Planning | Retainer | 192840.2231 | 198256.1021 | 223691.4001 | 199455.3377 | 199528.7443 | 199199.3851 | 0 | 0 | 0 | 0 | 192840.2231 | 198256.1021 | 223691.4001 | 199455.3377 | 199528.7443 | 199199.3851 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 200 | 200 | 200 | 200 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | True | compliance with NERC CIP and Bill 198 | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Asset Optimal
20851 | Placeholder Security Awareness Training | N.T.M.1.29 | 7700 | 203 | PROJECT DELIVERY | AIP001153 |  | AIP001153 | Yes | AIP001153 |  |  |  | NERC Cyber Security Compliance Readiness | lincoln.frost-hunt@hydroone.com | [6 empty] | Program | INSC | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20853 | Independent Audit | N.T.M.1.29 | 838 | 212 | INFO SOLUTIONS DIVISION | AIP001146 |  | AIP001146 | Yes | AIP001146 |  |  |  | NERC Cyber Security Compliance Readiness | lincoln.frost-hunt@hydroone.com | [6 empty] | Program | AWRD EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20855 | Field Site Surveys - BCA Identification | N.T.M.1.29 | 7370 | 206 | TX LINES AND STATIONS | AIP001148 |  | AIP001148 | Yes | AIP001148 | Field Site Audits - BCA Identification |  |  | NERC Cyber Security Compliance Readiness | lincoln.frost-hunt@hydroone.com | Sherry.Wilging@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | INSC EMPP | Executing | Short Term Planning | # of Surveys | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20857 | TDCN Management | N.T.M.1.29 | 4339 | 212 | INFO SOLUTIONS DIVISION | AIP001152 | AIP001152 | AIP001152 | No | AIP001152 | NERC Sustainment Resources | 0 |  | NERC Cyber Security Compliance Readiness | lincoln.frost-hunt@hydroone.com | Sherry.Wilging@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | EMPP init | Executing | Short Term Planning | Retainer | 3922355.443 | 3965114.985 | 4729064.1566 | 4839261.7247 | 5737163.3661 | 5838533.9785 | 0 | 0 | 0 | 0 | 3922355.443 | 3965114.985 | 4729064.1566 | 4839261.7247 | 5737163.3661 | 5838533.9785 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70 | 70 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | True | Maintain NERC V5 Compliance | False |  | False | False |  | False | False | False | False | TRUE | NERC V5 implemented | 0 | 0 | Asset Optimal
20858 | 2010 Kenora DS F3 Recloser Upgrade | N.D.C.2.02 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | [6 empty] | Project | DETL init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20859 | Cable Monitoring Infrastructure | N.T.C.3.08 | 7700 | 203 | PROJECT DELIVERY | AIP000979 |  | AIP000979 | Yes | AIP000979 |  |  |  | Integrating Operating Infrastructure | Miroslav.Kostic@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20862 | Goulbourne OC Building Renovations 2010 | N.C.C.1.50 | 7236 | 215 | FACILITIES & REAL ESTATE | UNPLND |  |  | Yes |  |  |  |  | Real Estate Facilities | cindy.copp@hydroone.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20865 | HV UG Cable - Emergency Repairs | N.T.C.1.15 | 7370 | 206 | TX LINES AND STATIONS | AIP000551 | AIP000551 | AIP000551 | No | AIP000551 | HV UG Cable - Emergency Repairs | 0 |  | U/G Lines Cable Sys & Comp Refurb & Repl | hassan.hamzeh@hydroone.com | Tyler.Wales@HydroOne.com | System Renewal | 0 | 0 | 03 - None (default) | 0 | Program | AWRD EMPP | Executing | Short Term Planning | Number of Repairs | 505089.9777 | 513453.3703 | 519387.2729 | 523410.3813 | 527387.3942 | 533316.9294 | 0 | 0 | 0 | 0 | 507628.1182 | 516033.538 | 521997.2592 | 526040.5843 | 530037.5821 | 535996.914 | 0 | 0 | 0 | 0 | -2538.1406 | -2580.1677 | -2609.9863 | -2630.2029 | -2650.1879 | -2679.9846 | 0 | 0 | 0 | 0 | -0.49999 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | True | False |  | False | True | False | False | FALSE |  | 0 | 0 | Asset Optimal
20873 | Burford DS Removal | N.D.C.2.02 | 7374 | 205 | LINES | AIP005429 | AIP005429 | AIP005429 | No | AIP005429 | Burford DS Removal | ISD-SR-13 | Life Cycle Optimization & Operational Efficiency Projects | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Alexander.Hamlyn@HydroOne.com | System Renewal | Western | 0 | 03 - None (default) | 0 | Project | DETL ACTN | Short Term Planning | Short Term Planning |  | 996965.7949 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1132915.676 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -135949.8811 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42947 | 43296 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
20881 | Oshawa-Highway 407 Extension-Harmony Rd_Recoverabl | N.T.C.1.14 | 7700 | 203 | PROJECT DELIVERY | 9 |  |  | Yes |  |  |  |  | Third Party Transmission System Modifications | john.boldt@HydroOne.com | [6 empty] | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20883 | Hwy 407 East Ext.-Reloc at Leskard Rd-Recoverable | N.T.C.1.14 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Third Party Transmission System Modifications | john.boldt@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20895 | Infrastructure Technology OM&A | N.C.M.2.70 | 4339 | 212 | INFO SOLUTIONS DIVISION | AIP000108 | AIP000108 | AIP000108 | No | AIP000108 | Infrastructure Refresh | 0 |  | IT - Project & Architecture Services | lincoln.frost-hunt@hydroone.com | Raj.Agnihotri@HydroOne.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | init EMPP | Executing | Short Term Planning | Retainer | 1530000 | 1570000 | 1570000.12 | 1570000 | 1570000 | 1570000 | 0 | 0 | 0 | 0 | 1530000 | 1570000 | 1570000.12 | 1570000 | 1570000 | 1570000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | False |  | False | False | True | False | FALSE |  | 0 | 0 | Vulnerable
20896 | MFA Infrastructure Technology | N.C.C.1.70 | 4339 | 212 | INFO SOLUTIONS DIVISION | 3582 |  |  | Yes |  |  |  |  | IT - Sustainment and Operations | lincoln.frost-hunt@hydroone.com | [6 empty] | Program | EMPP init | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20897 | ISD Business Impr and Enhancements | N.C.M.1.60 | 4042 | 212 | INFO SOLUTIONS DIVISION | AIP000087 | AIP000087 | AIP000087 | No | AIP000087 | ISD Business Improvements and Enhancements | 0 |  | IT Business Improvements & Enhancements | lincoln.frost-hunt@hydroone.com | Mark.Jungjohann@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | AWRD EMPP | Executing | Short Term Planning | Retainer | 3100000.12 | 4160000 | 3479999.84 | 3579999.88 | 4249999.92 | 4750000 | 0 | 0 | 0 | 0 | 3100000.12 | 4160000 | 3479999.84 | 3579999.88 | 4249999.92 | 4750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | False |  | False | False | True | False | TRUE | The enhancements are prioritized at the request of H1 LOBs to meet legal and regulatory requirements and improve day to day user experience, system performance, data availability, and activation of additional functionality to leverage applications & drive ongoing business improvements. | 0 | 0 | Vulnerable - Tx Contraint Reduction
20905 | Budget 2013 NDC150 | N.D.C.1.50 | 7236 | 215 | FACILITIES & REAL ESTATE | UNPLND |  |  | Yes |  |  |  |  | Real Estate Facilities | cindy.copp@hydroone.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20910 | Fault Indicator Installation Program | N.T.C.2.20 | 7370 | 206 | TX LINES AND STATIONS | AIP000937 |  | AIP000937 | Yes | AIP000937 |  |  |  | Performance Enhancement | Robert.Reinmuller@HydroOne.com | [6 empty] | Program | EMPP ACCP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20918 | Niagara TS Telecom Relocation | N.T.C.1.25 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Auxiliary Telecommunication Equipment | Miroslav.Kostic@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20920 | Re-establish Property Rights | N.T.C.1.14 | 7236 | 215 | FACILITIES & REAL ESTATE | AIP000463 | AIP000463 | AIP000463 | No | AIP000463 | Re-establish Property Rights | 0 |  | Third Party Transmission System Modifications | john.boldt@HydroOne.com | Gian.Minichini@HydroOne.com | System Renewal | 0 | 0 | 03 - None (default) | 0 | Program | AWRD EMPP | Executing | Short Term Planning | Retainer | 5078268.9314 | 1604459.8993 | 268146.6291 | 264632.6543 | 261415.1312 | 260121.9143 | 0 | 0 | 0 | 0 | 5078268.9314 | 1604459.8993 | 268146.6291 | 264632.6543 | 261415.1312 | 260121.9143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Asset Optimal
20921 | Studies- Universities | N.T.M.2.22 | 4230 | 213 | PLANNING | AIP001179D |  | AIP001179 | Yes | AIP001179 | [11 empty] | Program | EMPP AWRD | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20923 | FACTS / Micro Grid Studies | N.D.M.2.22 | 4230 | 213 | PLANNING | UNPLND |  |  | Yes | [12 empty] | Project | AWRD | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20924 | R&D Project-Grid Ops | N.D.M.2.21 | 4230 | 213 | PLANNING | AIP000319 |  | AIP000319 | Yes | AIP000319 |  |  |  | Distribution RD&D | Daila.Dzintars@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20926 | Misc. Studies- FACTS Technology / Devices | N.T.M.2.22 | 4230 | 213 | PLANNING | UNPLND |  |  | Yes | [12 empty] | Program | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20935 | Maclean's Mountain Wind Farm | N.T.C.2.12 | 7700 | 203 | PROJECT DELIVERY | AIP000884 |  | AIP000884 | Yes | AIP000884 |  |  |  | Generator Customer Connection | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20940 | Placeholder - Non-Recoverable - Line Removals | N.T.C.1.14 | 7700 | 203 | PROJECT DELIVERY | AIP000500 |  | AIP000500 | Yes | AIP000500 |  |  |  | Third Party Transmission System Modifications | john.boldt@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20944 | Trafalgar T14 750 MVA Autotransformer Re-Invest | N.T.C.1.08 | 7700 | 203 | PROJECT DELIVERY | AIP000447 |  | AIP000447 | Yes | AIP000447 |  |  |  | System Re-investment | James.Mardegan@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20946 | Modify Lennox X21X22 LEO Protection | N.T.C.2.21 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Major Risk Mitigation | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20947 | Fencing - Station Perimeter Program | N.T.C.1.21 | 7700 | 203 | PROJECT DELIVERY | AIP000626 |  | AIP000626 | Yes | AIP000626 |  |  |  | Infrastructure | James.Mardegan@HydroOne.com | [6 empty] | Program | ACCP EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20963 | Install Power Quality Monitors- Various Locations | N.T.C.2.20 | 7700 | 203 | PROJECT DELIVERY | 11 |  |  | Yes |  |  |  |  | Performance Enhancement | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | ACTN BEST | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20968 | Nebo TS:Increase Capacity of 230/27.6 kV T1T2 DESN | N.T.C.2.11 | 7700 | 203 | PROJECT DELIVERY | AIP000806 |  | AIP000806 | Yes | AIP000806 |  |  |  | Load Customer Connection | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20970 | Telecom EMERG Corrective Maintenance | N.T.M.1.22 | 7370 | 206 | TX LINES AND STATIONS | AIP001123B | AIP001123 | AIP001123 | No | AIP001123 | Telecom Corrective Maintenance | 0 |  | Telecommunication Assets Maintenance | Miroslav.Kostic@HydroOne.com | Sheraz.Majid@HydroOne.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | ACTN EMPP | Executing | Short Term Planning | # of Orders | 978959.0402 | 993025.9165 | 1112542.5485 | 1036934.8443 | 1057070.6484 | 1313030.1449 | 0 | 0 | 0 | 0 | 978959.0402 | 993025.9165 | 1112542.5485 | 1036934.8443 | 1057070.6484 | 1313030.1449 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 457 | 457 | 502 | 457 | 457 | 555 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | True | NERC, NPCC, Transport Canada, CSA, etc. | False |  | True | False |  | False | False | False | False | FALSE |  | 0 | 0 | Asset Optimal (Modified-Tx Decision)
20971 | Telecom Mtce Support / Spares / Spares Mgmt | N.T.M.1.22 | 7370 | 206 | TX LINES AND STATIONS | AIP001124 | AIP001124 | AIP001124 | No | AIP001124 | Telecom Mtce Support/Spares/Spares Mgmt | 0 |  | Telecommunication Assets Maintenance | Miroslav.Kostic@HydroOne.com | Sheraz.Majid@HydroOne.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | ACTN EMPP | Executing | Short Term Planning | Retainer | 605759.8701 | 1035345.2148 | 1058488.6529 | 1082775.8747 | 1105237.392 | 1128156.2296 | 0 | 0 | 0 | 0 | 605759.8701 | 1035345.2148 | 1058488.6529 | 1082775.8747 | 1105237.392 | 1128156.2296 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | True | NERC, NPCC, reliability compliance | False |  | True | False |  | False | True | False | False | FALSE |  | 0 | 0 | Asset Optimal (Modified-Tx Decision)
20977 | Underground Oil Pipeline Decommissioning Program | N.T.M.1.05 | 7700 | 203 | PROJECT DELIVERY | AIP001017 |  | AIP001017 | Yes | AIP001017 |  |  |  | Environmental Management | Mike.Tanaskovic@HydroOne.com | [6 empty] | Program | EMPP ACCP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20982 | Waubaushene TS M1 ID12000-Dx Waubaushene 5 | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | 2 |  |  | Yes |  |  |  |  | Distribution Generation Connection | ryan.boudreau@HydroOne.com | [6 empty] | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20983 | Waubaushene TS M1 ID12000-Tx Waubaushene 5 | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | 3823 |  |  | Yes |  |  |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20992 | Dx TECHS-Stations Standards | N.D.M.2.20 | 7716 | 224 | ENGINEERING | AIP000310 | AIP000310 | AIP000310 | No | AIP000310 | DX TECHS-Stations Standards Development |  |  | Standards Program | Kevin.Mancherjee@HydroOne.com | rossella.fazio@hydroone.com | System O&M | N/A | 0 | 03 - None (default) | 0 | Program | ACCP EMPP | Executing | Short Term Planning | Assumption - # of Standards | 154472.0656 | 160720.1854 | 165844.3747 | 171194.3791 | 176093.868 | 0 | 0 | 0 | 0 | 0 | 154472.0656 | 160720.1854 | 165844.3747 | 171194.3791 | 176093.868 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Vulnerable
20999 | Wholesale to Retail Standard - PL&F | N.D.C.1.09 | 7374 | 205 | LINES | AIP000172C | AIP000172 | AIP000172 | No | AIP000172 | Revenue Meter Upgrades |  |  | Metering | Peter.Mitskos@HydroOne.com | Dominic.Consorti@HydroOne.com | System Access | 0 | 0 | 03 - None (default) | 0 | Program | EMPP ACCP | Executing | Short Term Planning | # of meters | 654602.8979 | 666092.0007 | 679913.0322 | 693899.5009 | 707754.1519 | 0 | 0 | 0 | 0 | 0 | 655529.8971 | 667037.6865 | 680878.2832 | 694884.6544 | 708758.9953 | 0 | 0 | 0 | 0 | 0 | -926.9992 | -945.6857 | -965.251 | -985.1536 | -1004.8434 | 0 | 0 | 0 | 0 | 0 | -0.1417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54 | 54 | 54 | 54 | 54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Demand - Modified - M2M Savings
21007 | Budget 2011 NCC150 | N.C.C.1.50 | 7236 | 215 | FACILITIES & REAL ESTATE | UNPLND |  |  | Yes |  |  |  |  | Real Estate Facilities | cindy.copp@hydroone.com | [6 empty] | Program | AWRD EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21009 | Budget Bldg Renovations | N.T.C.1.28 | 7236 | 215 | FACILITIES & REAL ESTATE | AIP000664 |  | AIP000664 | Yes | AIP000664 |  |  |  | Transmission Site Facilities | cindy.copp@hydroone.com | [6 empty] | Program | EMPP AWRD | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21015 | TC219 - DG Connection Advancement for $107.7M | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 | AIP000931 | AIP000931 | No | AIP000931 | TS Upgrades for DG | SA-10 | Protection and Control Modifications for Distributed Generation | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43525 | True | multiple DG customers | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Asset Optimal
21016 | DC203 - DG Connection Advancement for $107.7M | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000199 |  | AIP000199 | Yes | AIP000199 | Large Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | EMPP ACTN | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21029 | Ponsonby DS F1 ID11520-Dx Martin Farm Biogas | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | 11 |  |  | Yes |  |  |  |  | Distribution Generation Connection | ryan.boudreau@HydroOne.com | [6 empty] | Project | ACCP | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21030 | Tx Standards Subscription | N.T.M.2.20 | 4230 | 213 | PLANNING | AIP001163 | AIP001163 | AIP001163 | No | AIP001163 | Tx External Standards Subscription | 0 |  | Standards Program | Kevin.Mancherjee@HydroOne.com | rossella.fazio@hydroone.com | System O&M | N/A | 0 | 03 - None (default) | 0 | Program | EMPP AWRD | Executing | Short Term Planning | Assumption - # of Tasks | 171257.0767 | 180326.487 | 189686.8366 | 199621.0391 | 209678.2861 | 216035.7969 | 0 | 0 | 0 | 0 | 171257.0767 | 180326.487 | 189686.8366 | 199621.0391 | 209678.2861 | 216035.7969 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | True |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Asset Optimal
21033 | Small Embedded Generation - Connections | N.D.C.2.03 | 7374 | 205 | LINES | AIP000191A |  | AIP000191 | Yes | AIP000191 | Small Embedded Generation |  |  | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 03 - None (default) | 0 | Program | EMPP AWRD | Executing | Short Term Planning | # of Gen Connections | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21037 | Belleville Operations Centre | N.C.C.1.50 | 7236 | 215 | FACILITIES & REAL ESTATE | AIP000027 |  | AIP000027 | Yes | AIP000027 | Facility Accommodation & Improvements Service Centres & Admin |  |  | Real Estate Facilities | cindy.copp@hydroone.com | Peter.Erdman@HydroOne.com | General Plant | 0 | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21040 | ADS Project - Phase 1 - Dx Capital | N.D.C.2.06 | 4343 | 222 | SMART GRID | AIP000207 |  | AIP000207 | Yes | AIP000207 | Distribution Modernization Project | ISD-SS-07 | Advanced Distribution System (“ADS”) | Smart Grid | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Service | 0 | Not Required | 02 - Expectation (no agreement) | Not Required | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21045 | Crosby TS M2 ID11970-DX Northland Solar Crosby | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000199 |  | AIP000199 | Yes | AIP000199 | Large Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21046 | Crosby TS M2 ID11970-TX Northland Solar Crosby | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21047 | Kirkland Lake TS M62- ID11730-Dx Charlton Dam | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000199 |  | AIP000199 | Yes | AIP000199 | Large Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21048 | Kirkland Lake TS M62 ID11730-Tx Charlton Dam | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21055 | CGE FGK253 OCB Remediation Program | N.T.M.1.16 | 7370 | 206 | TX LINES AND STATIONS | UNPLND |  |  | Yes |  |  |  |  | Power Equipment | Mike.Tanaskovic@HydroOne.com | [6 empty] | Program | EMPP EXTR | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21060 | Tx PCB Reduction Program - Retrofill | N.T.M.1.05 | 7370 | 206 | TX LINES AND STATIONS | AIP001008 | AIP001008 | AIP001008 | No | AIP001008 | Environmental - PCB Retirement - Retrofill | 0 |  | Environmental Management | Mike.Tanaskovic@HydroOne.com | Harshal.Bhatt@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | ACTN EMPP | Executing | Short Term Planning | # of Retrofills | 4288653.6966 | 6469026.8646 | 7735449.1305 | 13164411.1974 | 14899093.9409 | 15456330.6043 | 0 | 0 | 0 | 0 | 4288653.6966 | 6469026.8646 | 7735449.1305 | 13164411.1974 | 14899093.9409 | 15456330.6043 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 341 | 389 | 420 | 1083 | 1091 | 1181 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | True | Environment Canada PCB regulation (SOR/2008-273) | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Asset Optimal (Modified-Tx Decision)
21063 | Dx PCB Oil Reduction Program - Retrofill | N.D.M.1.04 | 7370 | 206 | TX LINES AND STATIONS | AIP000253 | AIP000253 | AIP000253 | No | AIP000253 | DS Misc Mtce & Support - PCB Oil Retrofill |  |  | Distributing and Regulating Stations | emre.aydin@HydroOne.com | Trevor.Beausoleil@HydroOne.com | System O&M | N/A | 0 | 03 - None (default) | 0 | Program | ACTN EMPP | Executing | Short Term Planning | # of Orders | 654466.4632 | 674327.572 | 689072.4633 | 704394.6314 | 717518.308 | 0 | 0 | 0 | 0 | 0 | 654466.4632 | 674327.572 | 689072.4633 | 704394.6314 | 717518.308 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43 | 43 | 43 | 43 | 43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Vulnerable
21064 | Herbicide Application | N.T.M.1.19 | 7362 | 204 | FORESTRY | AIP001100 | AIP001100 | AIP001100 | No | AIP001100 | Herbicide Application | 0 |  | Infrastructure Maintenance | Mike.Tanaskovic@HydroOne.com | Sebastian.Niculae@HydroOne.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | ACTN EMPP | Executing | Short Term Planning | # of Orders | 454708.5443 | 783110.1939 | 794466.8956 | 806211.8464 | 816465.4565 | 826677.4483 | 0 | 0 | 0 | 0 | 454708.5443 | 783110.1939 | 794466.8956 | 806211.8464 | 816465.4565 | 826677.4483 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 452 | 550 | 550 | 550 | 550 | 550 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Intermediate (Modified-Tx Decision)
21065 | Station Site Surface Treatment | N.T.C.1.21 | 7700 | 203 | PROJECT DELIVERY | AIP000636 |  | AIP000636 | Yes | AIP000636 |  |  |  | Infrastructure | James.Mardegan@HydroOne.com | [6 empty] | Program | EMPP ACTN | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21074 | Smiths Falls TS M21 ID14330-Tx RE Smiths Falls 4 | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000928 |  | AIP000928 | Yes | AIP000928 |  |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21078 | Bruce HWB Upgrade for Supply to DGR Site | N.T.C.2.11 | 7700 | 203 | PROJECT DELIVERY | AIP000768 |  | AIP000768 | Yes | AIP000768 |  |  |  | Load Customer Connection | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | DETL ACTN | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21087 | Transport and Work Equipment (TWE) | N.C.C.1.30 | 7818 | 219 | FLEET | AIP000014A | AIP000014 | AIP000014 | No | AIP000014 | Transport and Work Equipment (TWE) Capital Requirements | GP-13 | Transport & Work Equipment | Fleet | robert.berardi@HydroOne.com | angela.mallozzi@hydroone.com | General Plant | 0 | 0 | 03 - None (default) | 0 | Program | EMPP AWRD | Executing | Short Term Planning | # of Vehicles | 39924709.77 | 44790065.8515 | 45279343.5949 | 45603130.893 | 45944623.523 | 46455810.4304 | 0 | 0 | 0 | 0 | 39924709.77 | 44790065.8515 | 45279343.5949 | 45603130.893 | 45944623.523 | 46455810.4304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 503 | 473 | 473 | 473 | 473 | 473 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | False |  | False | False | False | False | TRUE | Vehicles must be maintained at an optimum level to ensure public and employee safety, meet Ministry regulations such as CSA 225, Highway Trafffic Act, CVOR regulations. | 0 | 0 | Vulnerable (Modified - Tx Decision)
21088 | SpencervilleDS_F2_ID12,110_Clearydale Farms_Dx | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000199 |  | AIP000199 | Yes | AIP000199 | Large Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21089 | SpencervilleDS_F2_ID12,110_Clearydale Farms_Tx | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000928 |  | AIP000928 | Yes | AIP000928 |  |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21098 | Power Transformer ULTC Oil Filters/Breathers | N.T.M.1.16 | 7370 | 206 | TX LINES AND STATIONS | AIP001073 | AIP001073 | AIP001073 | No | AIP001073 | Transformer ULTC Protection Devices | 0 |  | Power Equipment | Mike.Tanaskovic@HydroOne.com | perry.ng@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | ACTN EMPP | Executing | Short Term Planning | # of Transformers | 425530.7508 | 431729.4141 | 441380.0033 | 451507.5601 | 460873.7638 | 470430.6808 | 0 | 0 | 0 | 0 | 425530.7508 | 431729.4141 | 441380.0033 | 451507.5601 | 460873.7638 | 470430.6808 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | False |  | False | True | False | False | FALSE |  | 0 | 0 | Intermediate
21100 | ADS Project - Phase 1 - Tx Capital | N.T.C.2.06 | 4343 | 222 | SMART GRID | AIP000761 |  | AIP000761 | Yes | AIP000761 | [11 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21104 | P&C W-TC219- DG Connection Advancement for $107.7M | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21111 | Hearst TS-M2-ID 12080- Dx- Mattawishkwia Solar Par | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000199 |  | AIP000199 | Yes | AIP000199 | Large Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21112 | Hearst TS-M2-ID 12080- Tx- Mattawishkwia Solar Par | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000928 |  | AIP000928 | Yes | AIP000928 |  |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21113 | Belleville TS M6 ID12360 Dx 2225051Ontario Inc. | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000199 |  | AIP000199 | Yes | AIP000199 | Large Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21114 | Wilson TS M12 ID12810 - Tx Ballyduff Wind Farm | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000928 |  | AIP000928 | Yes | AIP000928 |  |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | [6 empty] | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21122 | Small Embedded Generation - Expansions | N.D.C.2.03 | 7374 | 205 | LINES | AIP000191A | AIP000191 | AIP000191 | No | AIP000191 | Small Embedded Generation |  |  | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 03 - None (default) | 0 | Program | EMPP ACTN | Executing | Short Term Planning | # of Gen Connections | 551355.7007 | 442285.3043 | 451462.5564 | 273570.0913 | 279032.2079 | 0 | 0 | 0 | 0 | 0 | 1426146.8207 | 1156114.9043 | 1179568.6764 | 737737.7713 | 752483.2079 | 0 | 0 | 0 | 0 | 0 | 0 | -1.1102e-10 | -5.5511e-11 | -5.5511e-11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -874791.12 | -713829.6 | -728106.12 | -464167.68 | -473451 | 0 | 0 | 0 | 0 | 0 | 10 | 8 | 8 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
21123 | Small Embedded Generation - REI | N.D.C.2.03 | 7374 | 205 | LINES | AIP000191B | AIP000191 | AIP000191 | No | AIP000191 | Small Embedded Generation |  |  | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 03 - None (default) | 0 | Program | ACTN EMPP | Executing | Short Term Planning | # of Gen Connections | 1228825.0098 | 1053617.2415 | 1076564.4467 | 750933.2085 | 767056.2868 | 0 | 0 | 0 | 0 | 0 | 1228825.0098 | 1053617.2415 | 1076564.4467 | 750933.2085 | 767056.2868 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180 | 150 | 150 | 100 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
21124 | Relay Alternative to TT | N.D.M.2.22 | 4230 | 213 | PLANNING | UNPLND |  |  | Yes | [12 empty] | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21126 | Sidney TS R8S Dx- ID10000 Ranney Falls G3 | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000199 |  | AIP000199 | Yes | AIP000199 | Large Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21127 | Kam Reg DS Voltage Conversion Part 2 | N.D.C.2.02 | 7374 | 205 | LINES | UNPLND |  |  | Yes |  |  |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | [6 empty] | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21128 | Huntsville DS F3 Feeder Development | N.D.C.2.02 | 7374 | 205 | LINES | UNPLND |  |  | Yes |  |  |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | [6 empty] | Project | EMPP ACTN | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21131 | Interim Bolton Operation Centre - Improvements | N.C.C.1.50 | 7236 | 215 | FACILITIES & REAL ESTATE | UNPLND |  |  | Yes |  |  |  |  | Real Estate Facilities | cindy.copp@hydroone.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21132 | Wilson TS M12 ID12810 - Dx Ballyduff Wind Farm | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000195 |  | AIP000195 | Yes | AIP000195 | Small Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21133 | Belleville TS M6 ID12360-Tx 2225051 Ontario Inc | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000928 |  | AIP000928 | Yes | AIP000928 |  |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21134 | CAPE Support Maintenance & Training | N.T.M.1.17 | 7716 | 224 | ENGINEERING | AIP001075 | AIP001075 | AIP001075 | No | AIP001075 | Cape Support | 0 |  | Protection Control & Metering Equipment | Miroslav.Kostic@HydroOne.com | warren.tingle@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | ACTN EMPP | Executing | Short Term Planning | Retainer | 335233.815 | 351601.5286 | 359206.7665 | 366997.8644 | 374116.3806 | 381736.3393 | 0 | 0 | 0 | 0 | 335233.815 | 351601.5286 | 359206.7665 | 366997.8644 | 374116.3806 | 381736.3393 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 42735 | False |  | True | PRC-027-1 | False |  | False | False |  | False | True | False | False | FALSE |  | 0 | 0 | Asset Optimal
21136 | Comber DS - Station removal | N.D.C.2.02 | 7374 | 205 | LINES | UNPLND |  |  | Yes |  |  |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | [6 empty] | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21137 | Jungbunzlauer CTS:Provide 115 kV Connection | N.T.C.2.11 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Load Customer Connection | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21142 | Overhead Tx Lines - M3K Unregulated Asset | N.T.M.1.20 | 7370 | 206 | TX LINES AND STATIONS | AIP001113B |  | AIP001113 | Yes | AIP001113 | Preventative Maintenance |  |  | Overhead Lines | hassan.hamzeh@hydroone.com | jacky.chiu@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | ACCP EMPP | Executing | Short Term Planning | skf ( # of km, circuit structure, assessments) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21143 | Gold Corp – Line Tap from 115 kV line E2R | N.T.C.2.11 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Load Customer Connection | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | INSC EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21147 | DM203 Class C estimates 2013 | N.D.M.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP005024 | AIP005024 | AIP005024 | No | AIP005024 | Class C Estimates (PD) |  |  | Distributed Generation Connections | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | ACTN EMPP | Executing | Short Term Planning | # of estimates | 606541.5765 | 520790.3117 | 532177.8654 | 408008.4889 | 415610.1836 | 0 | 0 | 0 | 0 | 0 | 606541.5765 | 520790.3117 | 532177.8654 | 408008.4889 | 415610.1836 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 100 | 100 | 75 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
21151 | Assumption for Unplanned Lines DG Work - (Lines) | N.D.C.2.03 | 7374 | 205 | LINES | UNPLND |  |  | Yes |  |  |  |  | Distribution Generation Connection | ryan.boudreau@HydroOne.com | [6 empty] | Program | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21162 | CMS HVAC Replacement 2011 | N.C.C.1.50 | 7236 | 215 | FACILITIES & REAL ESTATE | UNPLND |  |  | Yes |  |  |  |  | Real Estate Facilities | cindy.copp@hydroone.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21166 | Replace Yard Lighting Program | N.T.C.1.21 | 7700 | 203 | PROJECT DELIVERY | AIP000638 |  | AIP000638 | Yes | AIP000638 |  |  |  | Infrastructure | James.Mardegan@HydroOne.com | [6 empty] | Program | ACCP EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21167 | Muskoka TS - Add 44kV Fdr Position &Chnge CT Ratio | N.T.C.2.11 | 7700 | 203 | PROJECT DELIVERY | AIP000805 |  | AIP000805 | Yes | AIP000805 |  |  |  | Load Customer Connection | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21168 | 2011-2014 OPA Residential Programs | N.D.M.2.50 | 1144 | 220 | STRATEGY & CONSERV | AIP000342 |  | AIP000342 | Yes | AIP000342 |  |  |  | Conservation and Demand Management | Imran.Merali@HydroOne.com | [6 empty] | Program | EMPP AWRD | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21178 | Muskoka TS M10 ID12250-Tx Burks Falls East Solar | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000928 |  | AIP000928 | Yes | AIP000928 |  |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | [6 empty] | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21180 | DG Power Quality Monitoring (Stations) | N.D.M.2.03 | 8706 | 214 | METER SHOP | AIP000297A | AIP000297 | AIP000297 | No | AIP000297 | DG Power Quality Monitoring |  |  | Distributed Generation Connections | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | ACTN EMPP | Executing | Short Term Planning | # of monitoring sites | 668206.6193 | 731189.5458 | 791880.7297 | 854097.8945 | 915450.7288 | 0 | 0 | 0 | 0 | 0 | 668206.6193 | 731189.5458 | 791880.7297 | 854097.8945 | 915450.7288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
21190 | Greener Choices Retrofits - Capital Work | N.C.C.2.50 | 7053 | 209 | HEALTH, SAFETY & ENV | UNPLND |  |  | Yes | [12 empty] | Program | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21191 | Overhead Tx Lines - H2N Beaver Power Agreement | N.T.M.1.20 | 7370 | 206 | TX LINES AND STATIONS | AIP001113C |  | AIP001113 | Yes | AIP001113 | Preventative Maintenance |  |  | Overhead Lines | hassan.hamzeh@hydroone.com | jacky.chiu@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | ACCP EMPP | Executing | Short Term Planning | skf ( # of km, circuit structure, assessments) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21196 | Stayner TS M6 ID12860-Dx Fairview Wind Farm | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000199 |  | AIP000199 | Yes | AIP000199 | Large Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | EMPP init | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21197 | Stayner TS M6 ID12860-Tx Fairview Wind Farm | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | [6 empty] | Project | init EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21198 | CM125 recoveries HOT Remotes | N.C.M.1.25 | 4339 | 212 | INFO SOLUTIONS DIVISION | AIP000080 | AIP000080 | AIP000080 | No | AIP000080 | Recovery from HOT/REM | 0 |  | Business Telecom | lincoln.frost-hunt@hydroone.com | robert.hosford@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | init EMPP | Executing | Short Term Planning | Retainer | -400315 | -393219 | -393723 | -397971 | -396730 | -396819 | 0 | 0 | 0 | 0 | -400315 | -393219 | -393723 | -397971 | -396730 | -396819 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | True | Agreement/Contract with H1 Telecom and Providers such as Bell. | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Intermediate
21199 | CM170 Cost Recovery HOT Remotes | N.C.M.1.70 | 4339 | 212 | INFO SOLUTIONS DIVISION | AIP000092 | AIP000092 | AIP000092 | No | AIP000092 | Allocation HOT/Remotes | 0 |  | IT - Sustainment and Operations | lincoln.frost-hunt@hydroone.com | robert.hosford@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | EMPP init | Executing | Short Term Planning | Retainer | -1159333.88 | -1128885 | -1016897 | -1016471 | -1014515 | -1014751.12 | 0 | 0 | 0 | 0 | -1159333.88 | -1128885 | -1016897 | -1016471 | -1014515 | -1014751.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | True | Agreement/Contract with Inergi | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Intermediate
21201 | DG Power Quality Monitoring (Lines) | N.D.M.2.03 | 7374 | 205 | LINES | AIP000297B | AIP000297 | AIP000297 | No | AIP000297 | DG Power Quality Monitoring |  |  | Distributed Generation Connections | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | ACTN EMPP | Executing | Short Term Planning | # of monitoring sites | 54060.0783 | 55700.6455 | 56918.5328 | 58184.1741 | 59268.1953 | 0 | 0 | 0 | 0 | 0 | 54060.0783 | 55700.6455 | 56918.5328 | 58184.1741 | 59268.1953 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
21202 | Manitouwadge TS M2 ID931 Dx-Becker Cogen | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000199 |  | AIP000199 | Yes | AIP000199 | Large Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21203 | Manitouwadge TS M2 ID931 Tx-Becker Cogen | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000928 |  | AIP000928 | Yes | AIP000928 |  |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | [6 empty] | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21207 | Gardiner TS M14 ID12520 Dx 2225055 ON Hwy2 North | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000199 |  | AIP000199 | Yes | AIP000199 | Large Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21208 | Gardiner TS_M14_ID12520_Tx 2225055 ON Hwy2 North | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000928 |  | AIP000928 | Yes | AIP000928 |  |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21210 | Ramore TS M5 ID12050-Dx Ramore Solar Park | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000195 |  | AIP000195 | Yes | AIP000195 | Small Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21212 | Muskoka TS M1 ID12190-Dx North Bala Small Hydro | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000199 |  | AIP000199 | Yes | AIP000199 | Large Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21213 | Muskoka TS M1 ID12190-Tx North Bala Small Hydro | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000928 |  | AIP000928 | Yes | AIP000928 |  |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | [6 empty] | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21214 | 2012+ Large Sustainment Initiatives | N.D.C.1.07 | 7374 | 205 | LINES | AIP000152 | AIP000152 | AIP000152 | No | AIP000152 | Large Sustainment Initiatives | ISD-SR-12 | Distribution Lines Sustainment Initiatives | Lines | emre.aydin@HydroOne.com | Alexander.Hamlyn@HydroOne.com | System Renewal | N/A | 0 | 03 - None (default) | 0 | Program | AWRD EMPP | Executing | Short Term Planning | # of projects | 16491387.9986 | 25279899.0847 | 25136823.052 | 25583004.0752 | 25517468.2651 | 0 | 0 | 0 | 0 | 0 | 18740213.6348 | 28727158.0508 | 28564571.65 | 29071595.54 | 28997123.0285 | 0 | 0 | 0 | 0 | 0 | -2248825.6362 | -3447258.9661 | -3427748.598 | -3488591.4648 | -3479654.7634 | 0 | 0 | 0 | 0 | 0 | -12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Plan B Modified
21215 | 2011-2014 OPA Commercial Programs | N.D.M.2.50 | 1144 | 220 | STRATEGY & CONSERV | AIP000339 |  | AIP000339 | Yes | AIP000339 |  |  |  | Conservation and Demand Management | Imran.Merali@HydroOne.com | [6 empty] | Program | AWRD EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21216 | 2011-2014 OPA Industrial Programs | N.D.M.2.50 | 1144 | 220 | STRATEGY & CONSERV | AIP000340 |  | AIP000340 | Yes | AIP000340 |  |  |  | Conservation and Demand Management | Imran.Merali@HydroOne.com | [6 empty] | Program | EMPP AWRD | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21224 | Kirkland Lake TS ID 12730- Tx Marter Twp GS | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21228 | Dobbin TS M4 ID11650-TX London Street GS-Expansion | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000928 |  | AIP000928 | Yes | AIP000928 |  |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21229 | Lauzon/Belle River reconfiguration | N.D.C.2.02 | 7374 | 205 | LINES | UNPLND |  |  | Yes |  |  |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | [6 empty] | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21230 | Perth OC Fence Replacement 2011 | N.C.C.1.50 | 7236 | 215 | FACILITIES & REAL ESTATE | UNPLND |  |  | Yes |  |  |  |  | Real Estate Facilities | cindy.copp@hydroone.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21231 | Kapuskasing OC Fence Replacement 2011 | N.D.C.1.50 | 7236 | 215 | FACILITIES & REAL ESTATE | UNPLND |  |  | Yes |  |  |  |  | Real Estate Facilities | cindy.copp@hydroone.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21233 | New Liskeard OC Fence Replacement 2011 | N.D.C.1.50 | 7236 | 215 | FACILITIES & REAL ESTATE | UNPLND |  |  | Yes |  |  |  |  | Real Estate Facilities | cindy.copp@hydroone.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21234 | Dundas OC HVAC Replacement 2011 | N.D.C.1.50 | 7236 | 215 | FACILITIES & REAL ESTATE | AIP000027 |  | AIP000027 | Yes | AIP000027 | Facility Accommodation & Improvements Service Centres & Admin |  |  | Real Estate Facilities | cindy.copp@hydroone.com | Peter.Erdman@HydroOne.com | General Plant | 0 | 0 | 03 - None (default) | 0 | Program | EMPP AWRD | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21235 | Manitoulin OC Fence Replacement 2011 | N.D.C.1.50 | 7236 | 215 | FACILITIES & REAL ESTATE | UNPLND |  |  | Yes |  |  |  |  | Real Estate Facilities | cindy.copp@hydroone.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21237 | Orangeville TS M4 ID12830-Dx Whittington Wind Farm | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000195 |  | AIP000195 | Yes | AIP000195 | Small Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21238 | Orangeville TS M4 ID12830-Tx Whittington Wind Farm | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000928 |  | AIP000928 | Yes | AIP000928 |  |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | [6 empty] | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21240 | Dobbin TS M4 ID11650-DX London Street GS-Expansion | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000195 |  | AIP000195 | Yes | AIP000195 | Small Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21241 | Orillia TS M2 ID11790-Dx Wasdell Falls Waterpower | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000199 |  | AIP000199 | Yes | AIP000199 | Large Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21242 | Orillia TS M2 ID11790-Tx Wasdell Falls Waterpower | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000928 |  | AIP000928 | Yes | AIP000928 |  |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21244 | Pilot Project for Security Monitoring Tx | N.T.C.1.80 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Security Infrastructure | James.Mardegan@HydroOne.com | [6 empty] | Project | BEST ACTN | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21249 | Port Hope TS M16 ID12750-Dx Clean Breeze Wind Park | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000199 |  | AIP000199 | Yes | AIP000199 | Large Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21252 | Havelock TS M3 ID12950-Dx Kawartha Biogas | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000195 |  | AIP000195 | Yes | AIP000195 | Small Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21253 | Havelock TS M3 ID12950-Tx Kawartha Biogas | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21256 | DS Operating Spare Corrective Maintenance | N.D.M.1.04 | 7370 | 206 | TX LINES AND STATIONS | AIP000259 | AIP000259 | AIP000259 | No | AIP000259 | Dx Corrective Maintenance - Operating Spare |  |  | Distributing and Regulating Stations | emre.aydin@HydroOne.com | Trevor.Beausoleil@HydroOne.com | System O&M | N/A | 0 | 03 - None (default) | 0 | Program | ACTN EMPP | Executing | Short Term Planning | # of Orders | 124871.7874 | 128661.2597 | 131474.5706 | 134397.9888 | 136902.0288 | 0 | 0 | 0 | 0 | 0 | 124871.7874 | 128661.2597 | 131474.5706 | 134397.9888 | 136902.0288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Vulnerable
21257 | Pickering 'A' T3L7 & T2L8 Brk Remov, Decommiss Air | N.T.C.1.08 | 7700 | 203 | PROJECT DELIVERY | AIP000435 | AIP000435 | AIP000435 | No | AIP000435 | Pickering A 'SS' T3L7 & T2L8 Bypass (ABCB) | 0 |  | System Re-investment | James.Mardegan@HydroOne.com | michael.xavier@hydroone.com | System Renewal | Central | 0 | 03 - None (default) | 0 | Project | ACTN EMPP | Executing | Executing |  | 282800.0165 | 0 | 0.029484 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 879424.5238 | 0 | 0.029484 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -596624.5073 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -67.8426 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43100 | [13 empty] | FALSE |  | 2 | 0 | Alternative 1
21262 | Toronto Power TS Bldg Demolition | N.T.C.1.28 | 7236 | 215 | FACILITIES & REAL ESTATE | UNPLND |  |  | Yes |  |  |  |  | Transmission Site Facilities | cindy.copp@hydroone.com | [6 empty] | Project | EMPP AWRD | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21266 | Overhead Tx Lines -Condition Assess LCSP TLDF-E&CS | N.T.M.1.20 | 7716 | 224 | ENGINEERING | AIP001115C | AIP001115 | AIP001115 | No | AIP001115 | Tx Technical Support 3rd party/E&CS/PL | 0 |  | Overhead Lines | hassan.hamzeh@hydroone.com | jacky.chiu@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | EMPP ACCP | Executing | Short Term Planning | N/A | 252313.8172 | 258084.4125 | 263725.3516 | 269606.5178 | 275099.8709 | 280688.4672 | 0 | 0 | 0 | 0 | 252313.8172 | 258084.4125 | 263725.3516 | 269606.5178 | 275099.8709 | 280688.4672 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | False |  | False | True | False | False | FALSE |  | 0 | 0 | Intermediate (Modified - Tx Decision)
21273 | Midhurst TS M9 ID12210-Dx RE Midhurst 6 | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000199 |  | AIP000199 | Yes | AIP000199 | Large Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21274 | Henvey Inlet Wind Farm | N.T.C.2.12 | 7700 | 203 | PROJECT DELIVERY | AIP000874 | AIP000874 | AIP000874 | No | AIP000874 | Henvey Inlet Wind Farm | 0 |  | Generator Customer Connection | Robert.Reinmuller@HydroOne.com | Alexander.Constantinescu@HydroOne.com | System Access | Northern | Not Required | 01 - Agreement (current/future) | Not Required | Project | ACTN LLTM BEST | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3500000 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3500000 | -500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43131 | 43524 | True | Customer requested work. | True | Transmission license requirement to connect customers. | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Henvey Inlet Wind Farm
21277 | HONI-HOT Smart Meter Sustainment | N.D.M.1.09 | 4048 | 213 | PLANNING | AIP000281 | AIP000281 | AIP000281 | No | AIP000281 | HOT Support - AMI |  |  | Telecom Monitoring and Control | Peter.Mitskos@HydroOne.com | Dominic.Consorti@HydroOne.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | AWRD EMPP | Executing | Short Term Planning | Retainer | 1570504.3041 | 1635299.3776 | 1689660.5967 | 1746249.3367 | 1799295.1382 | 0 | 0 | 0 | 0 | 0 | 1570504.3041 | 1635299.3776 | 1689660.5967 | 1746249.3367 | 1799295.1382 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
21280 | Whitby TS_ID13530_C17 Real Canadian Superstore | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | [6 empty] | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21285 | Niagara Region Wind Farm Tx FIT Project | N.T.C.2.12 | 7700 | 203 | PROJECT DELIVERY | AIP000891 |  | AIP000891 | Yes | AIP000891 |  |  |  | Generator Customer Connection | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21286 | Q6S:Connect the Amherst Island Wind Tx FIT Project | N.T.C.2.12 | 7700 | 203 | PROJECT DELIVERY | AIP000897 | AIP000897 | AIP000897 | No | AIP000897 | Q6S:Connect the Amherst Island Wind Tx FIT Project | 0 |  | Generator Customer Connection | Robert.Reinmuller@HydroOne.com | Quyen.Diep@HydroOne.com | System Access | Eastern | Not Required | 01 - Agreement (current/future) | Required | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 411230 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -411230 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43117 | [13 empty] | FALSE |  | 0 | 0 | Alternative 1
21287 | Elliot Lake TS M3 ID12310 Pecors Power DX | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000199 |  | AIP000199 | Yes | AIP000199 | Large Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21288 | Elliot Lake TS M3 - ID 12310 Pecors Power TX | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000928 |  | AIP000928 | Yes | AIP000928 |  |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21292 | Lakehead TS – C8 Synchronous Condenser Refurb | N.T.C.1.18 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Other Power Equipment | James.Mardegan@HydroOne.com | [6 empty] | Project | EMPP ACTN | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21294 | Claireville 750 MVA Autotransf Replacement - T14 | N.T.C.1.17 | 7700 | 203 | PROJECT DELIVERY | AIP000553 |  | AIP000553 | Yes | AIP000553 |  |  |  | Power Transformers | James.Mardegan@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21295 | Extreme Space Weather Prepardness | N.T.C.3.08 | 7700 | 203 | PROJECT DELIVERY | AIP000982 | AIP000982 | AIP000982 | No | AIP000982 | Extreme Space Weather Prepardness | 0 |  | Integrating Operating Infrastructure | Miroslav.Kostic@HydroOne.com | David.Hesch@HydroOne.com | General Plant | 0 | 0 | 0 | 0 | Project | EMPP ACCP | Executing | Executing |  | 441965.5138 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 441965.5138 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43190 | [13 empty] | FALSE |  | 0 | 0 | Alternative 1
21300 | Copeland MTS Line Connection (formerly Bremner MTS | N.T.C.2.11 | 7700 | 203 | PROJECT DELIVERY | AIP000767 | AIP000767 | AIP000767 | No | AIP000767 | Copeland MTS Line Connection (formerly Bremner MTS) | 0 |  | Load Customer Connection | Robert.Reinmuller@HydroOne.com | Harneet.Panesar@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Complete | Project | ACTN EMPP | Executing | Executing |  | 1183932.7229 | 0 | 0.029484 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9681149.7229 | 0 | 0.029484 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1.3323e-09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -8497217 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43242 | [13 empty] | FALSE |  | 0 | 0 | Alternative 1
21305 | St.Lawrence TS M26 12,180-DX SunE Rutley | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000195 |  | AIP000195 | Yes | AIP000195 | Small Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | EMPP ACTN | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21307 | Dryden TS-M3 ID 12070-DX- Wainwright Solar Park | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000199 |  | AIP000199 | Yes | AIP000199 | Large Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21313 | Trout Lake TS- M7- ID#12780- Dx- Trout Lake Wind | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000199 |  | AIP000199 | Yes | AIP000199 | Large Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21314 | Trout Lake TS- M7- ID#12780- Tx- Trout Lake Wind | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000928 |  | AIP000928 | Yes | AIP000928 |  |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21333 | Town of Madsen Conversion from 4.16 to 25 kV | N.D.C.2.02 | 7374 | 205 | LINES | AIP005261 | AIP005261 | AIP005261 | No | AIP005261 | Town of Madsen Voltage Conversion |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Cecilia.Pang@HydroOne.com | System Renewal | Northern | Not Required | 03 - None (default) | Not Required | Project | EMPP ACTN | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42673 | 43040 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
21360 | Cobalt DS F2 ID12500-Dx Latchford Dam | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000199 |  | AIP000199 | Yes | AIP000199 | Large Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21361 | Cobalt DS F2 ID12500-Tx Latchford Dam | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21371 | Higbury TS Building Demolition 2011 | N.T.C.1.28 | 7236 | 215 | FACILITIES & REAL ESTATE | UNPLND |  |  | Yes |  |  |  |  | Transmission Site Facilities | cindy.copp@hydroone.com | [6 empty] | Program | AWRD EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21372 | London Project Office Building Demolition 2011 | N.C.C.1.50 | 7236 | 215 | FACILITIES & REAL ESTATE | UNPLND |  |  | Yes |  |  |  |  | Real Estate Facilities | cindy.copp@hydroone.com | [6 empty] | Program | AWRD EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21380 | Kirkland Lake TS M62 ID12890 - Dx Wendigo Waterpo | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000199 |  | AIP000199 | Yes | AIP000199 | Large Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21381 | Kirkland Lake TS M62 ID12890 - Tx Wendigo Waterpo | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000928 |  | AIP000928 | Yes | AIP000928 |  |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21387 | Sudbury-Maley Dr Extension/Widening_Recoverable | N.T.C.1.14 | 7700 | 203 | PROJECT DELIVERY | AIP000523 |  | AIP000523 | Yes | AIP000523 |  |  |  | Third Party Transmission System Modifications | john.boldt@HydroOne.com | [6 empty] | Project | init BEST | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21391 | Malvern TS: Install M23 & M24 Feeder Breakers | N.T.C.2.11 | 7700 | 203 | PROJECT DELIVERY | AIP000799 |  | AIP000799 | Yes | AIP000799 |  |  |  | Load Customer Connection | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21394 | Owen Sound OC Pavement Installation 2011 | N.D.C.1.50 | 7236 | 215 | FACILITIES & REAL ESTATE | AIP000027 |  | AIP000027 | Yes | AIP000027 | Facility Accommodation & Improvements Service Centres & Admin |  |  | Real Estate Facilities | cindy.copp@hydroone.com | Peter.Erdman@HydroOne.com | General Plant | 0 | 0 | 03 - None (default) | 0 | Program | AWRD EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21398 | Trout Lake TS- M7- ID#11850- Dx- Okikendawt Hydro | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000199 |  | AIP000199 | Yes | AIP000199 | Large Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21399 | Trout Lake TS- M7- ID#11850- Tx- Okikendawt Hydro | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000928 |  | AIP000928 | Yes | AIP000928 |  |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | [6 empty] | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21401 | Tx - Scrap & Surplus of System Reserve Equipment | N.T.C.1.17 | 7700 | 203 | PROJECT DELIVERY | AIP000557 |  | AIP000557 | Yes | AIP000557 | Power Equipment - Scrap & Surplus of Operating Spare Sys Eqpt |  |  | Power Transformers | James.Mardegan@HydroOne.com | peter.zhao@hydroone.com | System Renewal | 0 | 0 | 03 - None (default) | 0 | Program | ACTN EMPP | Executing | Short Term Planning | # of Equipments | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21415 | Port Hope TS M18 ID 12910-DX Clarington Wind Park | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000199 |  | AIP000199 | Yes | AIP000199 | Large Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21416 | Port Hope TS M18 ID 12910-TX Clarington Wind Park | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000928 |  | AIP000928 | Yes | AIP000928 |  |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21421 | Sidney TS R8S ID10000 Tx- Ranney Falls G3 | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21423 | Sidney TS R8S ID10000 Dx- Ranney Falls G3 | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000199 |  | AIP000199 | Yes | AIP000199 | Large Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21426 | 2011-2014 OPA Low Income Program | N.D.M.2.50 | 1144 | 220 | STRATEGY & CONSERV | AIP000341 |  | AIP000341 | Yes | AIP000341 |  |  |  | Conservation and Demand Management | Imran.Merali@HydroOne.com | [6 empty] | Program | AWRD EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21427 | Stayner TS M2 ID12280-Dx Skyway Windfarm | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000195 |  | AIP000195 | Yes | AIP000195 | Small Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21428 | Stayner TS M2 ID12280-Tx Skyway Windfarm | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000928 |  | AIP000928 | Yes | AIP000928 |  |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21434 | Crowland TS M1 ID12590-Tx Axio Welland Ridge Rd | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000928 |  | AIP000928 | Yes | AIP000928 |  |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | [6 empty] | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21440 | DS Station & Equipment Retirement | N.D.C.1.08 | 7700 | 203 | PROJECT DELIVERY | AIP000159 | AIP000159 | AIP000159 | No | AIP000159 | DS Station & Equipment Retirement |  |  | Distributing & Regulating Stations | emre.aydin@HydroOne.com | Trevor.Beausoleil@HydroOne.com | System Renewal | N/A | 0 | 03 - None (default) | 0 | Program | ACCP EMPP | Executing | Short Term Planning | # of stations | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 406152.96 | 414276.12 | 422561.64 | 431012.88 | 439633.08 | 0 | 0 | 0 | 0 | 0 | -406152.96 | -414276.12 | -422561.64 | -431012.88 | -439633.08 | 0 | 0 | 0 | 0 | 0 | -100 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 12 | 12 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
21445 | Trout Lake TS M5 ID12970-Dx Merrick Landfill Ga | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000195 |  | AIP000195 | Yes | AIP000195 | Small Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21446 | Trout Lake TS M5 ID12970-Tx Merrick Landfill Ga | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000928 |  | AIP000928 | Yes | AIP000928 |  |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21447 | Northland Power FIT Connection-Long Lake Solar | N.T.C.2.12 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Generator Customer Connection | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21448 | Northland Power FIT Connection -Abitibi/Martin/Emp | N.T.C.2.12 | 7700 | 203 | PROJECT DELIVERY | 2452 |  |  | Yes |  |  |  |  | Generator Customer Connection | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | DETL ACTN | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21460 | Thunder Bay - Hwy 11/17-Red Rock-Nipigon_Recovrabl | N.T.C.1.14 | 7700 | 203 | PROJECT DELIVERY | AIP000526 |  | AIP000526 | Yes | AIP000526 |  |  |  | Third Party Transmission System Modifications | john.boldt@HydroOne.com | [6 empty] | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21462 | Cobalt DS F2 ID12630-Dx Latchford Dam 2 | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000199 |  | AIP000199 | Yes | AIP000199 | Large Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21463 | Cobalt DS F2 ID12630-Tx Latchford Dam 2 | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000928 |  | AIP000928 | Yes | AIP000928 |  |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21465 | Bell Creek Complex - 115kV P7G Mine Connection | N.T.C.2.11 | 7700 | 203 | PROJECT DELIVERY | 3735 |  |  | Yes |  |  |  |  | Load Customer Connection | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21471 | B5G/B6G - Provide Transfer Trip Protection | N.T.C.2.21 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Major Risk Mitigation | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21473 | Physical Security - ADT Monitoring | N.T.M.1.29 | 4361 | 226 | NETWORK OPERATING | UNPLND |  |  | Yes |  |  |  |  | NERC Cyber Security Compliance Readiness | lincoln.frost-hunt@hydroone.com | [6 empty] | Program | EMPP AWRD | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21475 | Smiths Falls TS M23 ID14460-Dx Burritts Rapids | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000199 |  | AIP000199 | Yes | AIP000199 | Large Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21490 | Social Benchmarking | N.D.M.2.50 | 1144 | 220 | STRATEGY & CONSERV | AIP000338 | AIP000338 | AIP000338 | No | AIP000338 | Social Benchmarking |  |  | Conservation and Demand Management | Imran.Merali@HydroOne.com | Imran.Merali@HydroOne.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | EMPP init | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4227600 | 4269200 | 4394000 | 4393999.96 | 4394000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4227600 | -4269200 | -4394000 | -4393999.96 | -4394000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Base Case
21491 | 2011-2014 OEB Commercial Programs | N.D.M.2.50 | 1144 | 220 | STRATEGY & CONSERV | UNPLND |  |  | Yes |  |  |  |  | Conservation and Demand Management | Imran.Merali@HydroOne.com | [6 empty] | Program | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21492 | 2011-2014 OEB Industrial Programs | N.D.M.2.50 | 1144 | 220 | STRATEGY & CONSERV | UNPLND |  |  | Yes |  |  |  |  | Conservation and Demand Management | Imran.Merali@HydroOne.com | [6 empty] | Program | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21495 | PMR Engineering Support | N.T.M.1.23 | 7716 | 224 | ENGINEERING | AIP001122 | AIP001122 | AIP001122 | No | AIP001122 | PMR Engineering Support | 0 |  | Operation of Telecom Services | Miroslav.Kostic@HydroOne.com | Sheraz.Majid@HydroOne.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | ACTN EMPP | Executing | Short Term Planning | Retainer | 98849.6835 | 99127.8726 | 99308.4414 | 99532.3267 | 99569.0378 | 99599.6527 | 0 | 0 | 0 | 0 | 98849.6835 | 99127.8726 | 99308.4414 | 99532.3267 | 99569.0378 | 99599.6527 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | True | Eng support activities for transport canada compliance for PMR | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Vulnerable
21498 | Seaton MTS - 230 kV Tx Supply to New 28 kV DESN | N.T.C.2.11 | 7700 | 203 | PROJECT DELIVERY | AIP000813 | AIP000813 | AIP000813 | No | AIP000813 | Seaton TS: Build/Connect 230-28kV Transformer Station | 0 |  | Load Customer Connection | Robert.Reinmuller@HydroOne.com | Quyen.Diep@HydroOne.com | System Access | Central | Required | 01 - Agreement (current/future) | Required | Project | ACTN DETL | Short Term Planning | Short Term Planning |  | 5104441.8685 | 983755.5973 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5104441.8685 | 983755.5973 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43130 | 43677 | True | Customer requested work- Veridian | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Alternative 1
21499 | MetroLinx Traction Power Station Connections | N.T.C.2.11 | 7700 | 203 | PROJECT DELIVERY | AIP000803 |  | AIP000803 | Yes | AIP000803 |  |  |  | Load Customer Connection | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | ACTN BEST | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21514 | ADS Phase 1 Release 2 - Dx OM&A | N.D.M.2.06 | 4343 | 222 | SMART GRID | AIP000302 | AIP000302 | AIP000302 | No | AIP000302 | Distribution Modernization Project OM&A |  |  | Smart Grid | Godfrey.Holder@HydroOne.com | Daniel.Lam@HydroOne.com | System O&M | 0 | Not Required | 02 - Expectation (no agreement) | Not Required | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41130 | 41638 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
21516 | Abitibi Bowater CTS - G6 Generator Connection | N.T.C.2.12 | 7700 | 203 | PROJECT DELIVERY | AIP000842 |  | AIP000842 | Yes | AIP000842 |  |  |  | Generator Customer Connection | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21517 | Dryden TS - Install Redundant NSD570 for Domtar | N.T.C.2.12 | 7700 | 203 | PROJECT DELIVERY | AIP000869 |  | AIP000869 | Yes | AIP000869 |  |  |  | Generator Customer Connection | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21518 | Reactors at Marathon TS | N.T.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000735 |  | AIP000735 | Yes | AIP000735 |  |  |  | Network Transfer Capability | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21519 | Northcote DS-F3-ID645-Dx-PV mitigation | N.D.C.2.03 | 7374 | 205 | LINES | UNPLND |  |  | Yes |  |  |  |  | Distribution Generation Connection | ryan.boudreau@HydroOne.com | [6 empty] | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21520 | Malden TS-M8-ID689-Dx-PV mitigation | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000194 |  | AIP000194 | Yes | AIP000194 | Distance Limitation Mitigation Work (E&T) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | Not Required | 03 - None (default) | Not Required | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21521 | Kent TS-M23-ID49-Dx-PV mitigation | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000194 |  | AIP000194 | Yes | AIP000194 | Distance Limitation Mitigation Work (E&T) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | Not Required | 03 - None (default) | Not Required | Project | ACTN BEST | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21523 | Duart TS-M5-ID487-Dx-Distance Limitation | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000194 |  | AIP000194 | Yes | AIP000194 | Distance Limitation Mitigation Work (E&T) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | Not Required | 03 - None (default) | Not Required | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21524 | Kent TS-M15-ID274-Dx-PV mitigation | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000194 |  | AIP000194 | Yes | AIP000194 | Distance Limitation Mitigation Work (E&T) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | Not Required | 03 - None (default) | Not Required | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21525 | Kingsville TS-M7-ID1097-Dx-PV mitigation | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000194 |  | AIP000194 | Yes | AIP000194 | Distance Limitation Mitigation Work (E&T) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | Not Required | 03 - None (default) | Not Required | Project | ACTN DETL | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21526 | Kingsville TS-M1 M7-DG 1096 and 1099 DX PV mitigat | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000194 |  | AIP000194 | Yes | AIP000194 | Distance Limitation Mitigation Work (E&T) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | Not Required | 03 - None (default) | Not Required | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21529 | 95 Mural Street (Tenant Improvements) 2011 | N.C.C.1.50 | 7236 | 215 | FACILITIES & REAL ESTATE | UNPLND |  |  | Yes |  |  |  |  | Real Estate Facilities | cindy.copp@hydroone.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21532 | NMS Capital Sustainment | N.T.C.3.06 | 4514 | 212 | INFO SOLUTIONS DIVISION | AIP000971 |  | AIP000971 | Yes | AIP000971 |  |  |  | Grid Operating and Control Facilities | Godfrey.Holder@HydroOne.com | [6 empty] | Project | EMPP AWRD | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21533 | Voice Communications System Upgrades (Dx) | N.D.C.3.08 | 4514 | 212 | INFO SOLUTIONS DIVISION | UNPLND |  |  | Yes |  |  |  |  | Operating Infrastructure | Godfrey.Holder@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21536 | Kapuskasing TS M3 - ID11740 - Old Woman Falls DX | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000199 |  | AIP000199 | Yes | AIP000199 | Large Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21537 | Kapuskasing TS M3 - ID 11740 - Old Woman Falls TX | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000928 |  | AIP000928 | Yes | AIP000928 |  |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21538 | Kapuskasing TS M3 -ID 11750- White Otter Falls DX | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000195 |  | AIP000195 | Yes | AIP000195 | Small Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21539 | Kapuskasing TS M3 -ID 11750 - White Otter Falls TX | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000928 |  | AIP000928 | Yes | AIP000928 |  |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | [6 empty] | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21542 | ADS Phase 1 Release 2 - Common | N.D.C.2.06 | 4343 | 222 | SMART GRID | AIP000207 | AIP000207 | AIP000207 | No | AIP000207 | Distribution Modernization Project | ISD-SS-07 | Advanced Distribution System (“ADS”) | Smart Grid | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Service | 0 | Not Required | 02 - Expectation (no agreement) | Not Required | Project | AWRD EMPP | Executing | Executing |  | 5004044.4049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5004044.4049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41130 | 43100 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
21555 | OGCC Sustainment - Dx OM&A | N.D.M.2.06 | 4343 | 222 | SMART GRID | AIP000304 | AIP000304 | AIP000304 | No | AIP000304 | Distribution Modernization Sustainment |  |  | Smart Grid | Godfrey.Holder@HydroOne.com | Daniel.Lam@HydroOne.com | System O&M | 0 | 0 | 03 - None (default) | Not Required | Program | EMPP AWRD | Executing | Short Term Planning |  | 11131990.2159 | 11579855.0718 | 12584003.6839 | 13522541.6482 | 14556186.1705 | 0 | 0 | 0 | 0 | 0 | 11131990.2159 | 11579855.0718 | 12584003.6839 | 13522541.6482 | 14556186.1705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Recommended - Outsourced DMS & Cellular SCADA
21568 | Kent TS-M15-ID274-Tx-PV mitigation | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000928 |  | AIP000928 | Yes | AIP000928 |  |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | [6 empty] | Project | EMPP ACTN | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21578 | Muskoka TS M7 ID14110-Dx Bracebridge Falls | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000195 |  | AIP000195 | Yes | AIP000195 | Small Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21579 | Muskoka TS M7 ID14110 -Tx Bracebridge Falls | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000928 |  | AIP000928 | Yes | AIP000928 |  |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | [6 empty] | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21585 | Trout Lake OC Overhead Door Replacement | N.T.C.1.28 | 7236 | 215 | FACILITIES & REAL ESTATE | UNPLND |  |  | Yes |  |  |  |  | Transmission Site Facilities | cindy.copp@hydroone.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21587 | Timmins TS-M11-ID251-Dx PV mitigation-EXP ONLY | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000194 |  | AIP000194 | Yes | AIP000194 | Distance Limitation Mitigation Work (E&T) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | Not Required | 03 - None (default) | Not Required | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21589 | Security Event Management Services | N.T.M.1.29 | 838 | 212 | INFO SOLUTIONS DIVISION | AIP001151 |  | AIP001151 | Yes | AIP001151 |  |  |  | NERC Cyber Security Compliance Readiness | lincoln.frost-hunt@hydroone.com | [6 empty] | Program | AWRD EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21599 | Leaside TS HVAC Replacement 2011/12 | N.T.C.1.28 | 7236 | 215 | FACILITIES & REAL ESTATE | UNPLND |  |  | Yes |  |  |  |  | Transmission Site Facilities | cindy.copp@hydroone.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21605 | Muskoka TS M7 ID 14120-Dx Wilson’s Falls Gen | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000195 |  | AIP000195 | Yes | AIP000195 | Small Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21606 | Muskoka TS M7 ID14120 -Tx Wilson’s Falls Gen | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000928 |  | AIP000928 | Yes | AIP000928 |  |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | [6 empty] | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21609 | Nebo TS M8 ID14490-Tx Redeemer University College | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000928 |  | AIP000928 | Yes | AIP000928 |  |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | [6 empty] | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21613 | Nipigon voltage conversion | N.D.C.2.02 | 7374 | 205 | LINES | AIP005262 | AIP005262 | AIP005262 | No | AIP005262 | Nipigon Voltage Conversion |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Cecilia.Pang@HydroOne.com | System Renewal | 0 | 0 | 03 - None (default) | 0 | Project | EMPP AWRD | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42671 | 43039 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
21618 | Tx Idle Line Rental Payments | N.D.M.1.07 | 7374 | 205 | LINES | AIP000277 | AIP000277 | AIP000277 | No | AIP000277 | Tx Idle Lines Rental |  |  | Other Services | emre.aydin@HydroOne.com | Wojciech.Maroszek@HydroOne.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | ACCP EMPP | Executing | Short Term Planning |  | 3969797.6443 | 4090268.8573 | 4179707.3291 | 4272647.0466 | 4352251.2558 | 0 | 0 | 0 | 0 | 0 | 3969797.6443 | 4090268.8573 | 4179707.3291 | 4272647.0466 | 4352251.2558 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Demand
21619 | Toronto-TTC-Eglinton Crosstown LRT_Recoverable | N.T.C.1.14 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Third Party Transmission System Modifications | john.boldt@HydroOne.com | [6 empty] | Project | DETL ACTN | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21621 | Non Production Computer Room Facility (Tx) | N.T.C.3.06 | 4514 | 212 | INFO SOLUTIONS DIVISION | 8 |  |  | Yes |  |  |  |  | Grid Operating and Control Facilities | Godfrey.Holder@HydroOne.com | [6 empty] | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21623 | Lennox 4kV Station Service COVER work | N.T.C.1.19 | 6426 | 210 | NS UNNODED | UNPLND |  |  | Yes |  |  |  |  | Protection Control & Metering Equip | Miroslav.Kostic@HydroOne.com | [6 empty] | Project | EMPP AWRD | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21627 | Control Room Wallboard Refresh (Dx) | N.D.C.3.08 | 4514 | 212 | INFO SOLUTIONS DIVISION | UNPLND |  |  | Yes |  |  |  |  | Operating Infrastructure | Godfrey.Holder@HydroOne.com | [6 empty] | Project | EMPP AWRD | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21628 | Control Room Wallboard Refresh (Tx) | N.T.C.3.06 | 4514 | 212 | INFO SOLUTIONS DIVISION | UNPLND |  |  | Yes |  |  |  |  | Grid Operating and Control Facilities | Godfrey.Holder@HydroOne.com | [6 empty] | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21644 | Connect Bluewater Wind Energy Centre | N.T.C.2.12 | 7700 | 203 | PROJECT DELIVERY | AIP000853 |  | AIP000853 | Yes | AIP000853 |  |  |  | Generator Customer Connection | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21645 | DG Connection Advancement for $29.76M - TC219 | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21646 | DG Connection Advancement | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000199 |  | AIP000199 | Yes | AIP000199 | Large Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21647 | Manitoulin TS T3 & T4 Replace EOL Transformers | N.T.C.1.17 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Power Transformers | James.Mardegan@HydroOne.com | [6 empty] | Program | ACCP EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21649 | Petawawa DSs Monitoring and Feeders | N.D.C.2.02 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21655 | B562L (Evergreen SS) - Connect JAB windfarms | N.T.C.2.12 | 7700 | 203 | PROJECT DELIVERY | AIP000847 |  | AIP000847 | Yes | AIP000847 |  |  |  | Generator Customer Connection | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21661 | L29C - Connect East Lake St. Clair Wind | N.T.C.2.12 | 7700 | 203 | PROJECT DELIVERY | AIP000878 |  | AIP000878 | Yes | AIP000878 |  |  |  | Generator Customer Connection | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21662 | W45LC - Connect Erieau Wind | N.T.C.2.12 | 7700 | 203 | PROJECT DELIVERY | AIP000908 |  | AIP000908 | Yes | AIP000908 |  |  |  | Generator Customer Connection | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21664 | B23D - Connect Grand Bend Wind Farm | N.T.C.2.12 | 7700 | 203 | PROJECT DELIVERY | AIP000845 |  | AIP000845 | Yes | AIP000845 |  |  |  | Generator Customer Connection | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21665 | B4V - Connect Grand Valley Wind Farms (Phase 3) | N.T.C.2.12 | 7700 | 203 | PROJECT DELIVERY | AIP000846 |  | AIP000846 | Yes | AIP000846 |  |  |  | Generator Customer Connection | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21667 | WT1A - Connect Silvercreek Solar Park | N.T.C.2.12 | 7700 | 203 | PROJECT DELIVERY | AIP000910 |  | AIP000910 | Yes | AIP000910 |  |  |  | Generator Customer Connection | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21668 | Telecom Battery Replacement Program | N.T.C.1.25 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Auxiliary Telecommunication Equipment | Miroslav.Kostic@HydroOne.com | [6 empty] | Program | EMPP ACCP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21669 | Telecom Charger Replacement Program | N.T.C.1.25 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Auxiliary Telecommunication Equipment | Miroslav.Kostic@HydroOne.com | [6 empty] | Program | ACCP EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21670 | Goderich TS - Station Reconfiguration | N.T.C.1.08 | 7700 | 203 | PROJECT DELIVERY | AIP000417 | AIP000417 | AIP000417 | No | AIP000417 | Goderich TS; T1/T2/T3, Component replacement | 0 |  | System Re-investment | James.Mardegan@HydroOne.com | mark.truchanowicz@hydroone.com | System Renewal | Western | 0 | 03 - None (default) | 0 | Project | ACCP EMPP | Executing | Executing |  | 8352.7431 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8981.4442 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -628.7011 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42893 | [13 empty] | FALSE |  | 2 | 2 | Alternative 1- AR 21670
21674 | Brown Hill TS- M12- ID15940- Tx- GoldLight LP | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21675 | Petawawa Craig DS T2 and F5 | N.D.C.2.02 | 7700 | 203 | PROJECT DELIVERY | AIP000183B |  | AIP000183 | Yes | AIP000183 | (1) System upgrade driven by load growth |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Michael.Medeiros@HydroOne.com | System Service | 0 | 0 | 03 - None (default) | Not Required | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21678 | Norfolk TS M1 ID15080-Tx Bright Power | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000928 |  | AIP000928 | Yes | AIP000928 |  |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21680 | Waterloo - LRT _ Recoverable | N.T.C.1.14 | 7700 | 203 | PROJECT DELIVERY | AIP000537 |  | AIP000537 | Yes | AIP000537 |  |  |  | Third Party Transmission System Modifications | john.boldt@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21683 | Morrisburg TS M25 ID12800 Dx-Southbranch Wind Farm | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000199 |  | AIP000199 | Yes | AIP000199 | Large Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21687 | Corporate support Optimization(SC, HR, Eh&S) | N.C.C.2.60 | 4339 | 212 | INFO SOLUTIONS DIVISION | AIP000060 |  | AIP000060 | Yes | AIP000060 |  |  |  | IT Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | init EMPP BEST | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21688 | OMA of Select CC260 Projects | N.C.M.2.60 | 4339 | 212 | INFO SOLUTIONS DIVISION | AIP000105 |  | AIP000105 | Yes | AIP000105 |  |  |  | IT-Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21689 | CTI Replacment | N.D.C.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION | AIP000213 | AIP000213 | AIP000213 | No | AIP000213 | CTI Replacement, IVR, Call Recording, Speech Analytics |  |  | IT Business Solution Development | jj.blais@HydroOne.com | Myla.MendinuetoMartinez@HydroOne.com | General Plant | 0 | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 7456026.1633 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7456026.1633 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43008 | 43465 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
21695 | Wilson TS M14 ID16030-Dx Illumination | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000199 |  | AIP000199 | Yes | AIP000199 | Large Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21696 | Wilson TS M14 ID16030-Tx Illumination | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000928 |  | AIP000928 | Yes | AIP000928 |  |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21698 | St. Lawrence TS M25 ID16470-Tx Glengarry St. Lawre | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000928 |  | AIP000928 | Yes | AIP000928 |  |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | [6 empty] | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21699 | Beaverton TS-M24-ID15900-Dx-Sparkle Light | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000195 |  | AIP000195 | Yes | AIP000195 | Small Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21705 | Move to Mobile - Lines Phase1 | N.C.C.2.60 | 4339 | 212 | INFO SOLUTIONS DIVISION | AIP000065 |  | AIP000065 | Yes | AIP000065 |  |  |  | IT Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21706 | AA 2015 Remediation | N.C.C.2.60 | 4339 | 212 | INFO SOLUTIONS DIVISION | AIP000062 |  | AIP000062 | Yes | AIP000062 |  |  |  | IT Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21708 | Chalk River MTS Connection Development | N.T.C.2.11 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Load Customer Connection | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | DETL ACTN | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21710 | E-Customer replacement | N.D.C.2.60 | 4339 | 212 | INFO SOLUTIONS DIVISION | AIP000214 |  | AIP000214 | Yes | AIP000214 | E-Customer Replacement |  |  | IT Business Solution Development | jj.blais@HydroOne.com | jj.blais@HydroOne.com | General Plant | 0 | 0 | 03 - None (default) | 0 | Project | EMPP AWRD | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21712 | Beaverton TS M24 ID15910 Dx-DiscoveryLight LP | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000195 |  | AIP000195 | Yes | AIP000195 | Small Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21715 | DS Single Phase Transformer Changeouts | N.D.C.1.08 | 7700 | 203 | PROJECT DELIVERY | AIP000158 |  | AIP000158 | Yes | AIP000158 |  |  |  | Distributing & Regulating Stations | emre.aydin@HydroOne.com | [6 empty] | Program | ACTN EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21716 | ROW Environment- Vegetation Re-Engineering | N.T.M.2.21 | 4230 | 213 | PLANNING | AIP001170 |  | AIP001170 | Yes | AIP001170 |  |  |  | Technology Program | Daila.Dzintars@HydroOne.com | [6 empty] | Project | AWRD BEST | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21717 | Ontario Solar Connection Study-CanSIA | N.D.M.2.22 | 4230 | 213 | PLANNING | AIP000327 |  | AIP000327 | Yes | AIP000327 | [11 empty] | Project | AWRD | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21722 | Beaverton TS M23 15880 Dx-GoodLight LP | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000199 |  | AIP000199 | Yes | AIP000199 | Large Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21723 | Brown Hill TS M11 ID15920 -Dx- Earthlight LP | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000199 |  | AIP000199 | Yes | AIP000199 | Large Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21724 | Cobden DS-SSI | N.D.C.2.02 | 7374 | 205 | LINES | UNPLND |  |  | Yes |  |  |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | [6 empty] | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21725 | Chesterville TS M2 ID15990 Dx - MightySolar | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000199 |  | AIP000199 | Yes | AIP000199 | Large Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21726 | Chesterville TS M2 ID15990 Tx - MightySolar | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21731 | Belleville TS M2 Dx-ID16020 Lunar Light LP | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Distribution Generation Connection | ryan.boudreau@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21732 | Belleville TS M2 ID16020-Tx - Lunar Light LP | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21733 | OPS AND CARRIER MGMT - Smart Meter | N.C.M.1.25 | 4339 | 212 | INFO SOLUTIONS DIVISION | AIP000081B | AIP000081 | AIP000081 | No | AIP000081 | Telecom OPS & Carrier Mgmt | 0 |  | Business Telecom | lincoln.frost-hunt@hydroone.com | robert.hosford@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | init EMPP | Executing | Short Term Planning | Retainer | 170000.47 | 170000.35 | 170000.36 | 170333.72 | 170333.64 | 170000 | 0 | 0 | 0 | 0 | 170000.47 | 170000.35 | 170000.36 | 170333.72 | 170333.64 | 170000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | True | Agreement/Contract with H1 Telecom. | False | False |  | False | False | True | False | FALSE |  | 0 | 0 | Intermediate
21737 | Training Enhancements (External) | N.C.M.3.03 | 7054 | 209 | HEALTH, SAFETY & ENV | AIP000121D | AIP000121 | AIP000121 | No | AIP000121 | Learning Management | 0 |  | Environment Health and Safety | welchw@hydroone.com | welchw@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | AWRD EMPP | Executing | Short Term Planning | Retainer | 316492.96 | 337048.84 | 360532.88 | 385959.84 | 411098.52 | 390000.12 | 0 | 0 | 0 | 0 | 316492.96 | 337048.84 | 360532.88 | 385959.84 | 411098.52 | 390000.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | True | E-Learning - contracted service for external company to create e-learning packages for use by Hydro One employees across the province. Modules will continue to be developed/refreshed to enable employees to be trained remotely and allow for timely and immediate delivery of required training. | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Optimal - (Modified-Tx Decision)
21738 | Lab Repairs and Upgrades | N.C.M.3.03 | 7054 | 209 | HEALTH, SAFETY & ENV | AIP000121E | AIP000121 | AIP000121 | No | AIP000121 | Learning Management | 0 |  | Environment Health and Safety | welchw@hydroone.com | welchw@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | AWRD EMPP | Executing | Short Term Planning | Retainer | 107285.68 | 109431.4 | 111620.12 | 113852.56 | 116129.56 | 109999.96 | 0 | 0 | 0 | 0 | 107285.68 | 109431.4 | 111620.12 | 113852.56 | 116129.56 | 109999.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | True | E-Learning - contracted service for external company to create e-learning packages for use by Hydro One employees across the province. Modules will continue to be developed/refreshed to enable employees to be trained remotely and allow for timely and immediate delivery of required training. | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Optimal - (Modified-Tx Decision)
21740 | Brown Hill TS M4 ID 15950 - Tx BeamLight LP | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | [6 empty] | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21743 | DG Coordination | N.D.M.2.03 | 7374 | 205 | LINES | AIP000296 | AIP000296 | AIP000296 | No | AIP000296 | DG Coordination |  |  | Distributed Generation Connections | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | EMPP ACCP | Executing | Short Term Planning | # of People | 1166581.6204 | 1201984.0143 | 1228266.6265 | 1255578.2532 | 1278971.1254 | 0 | 0 | 0 | 0 | 0 | 1166581.6204 | 1201984.0143 | 1228266.6265 | 1255578.2532 | 1278971.1254 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 7 | 7 | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
21744 | Compliance Audit Readiness | N.T.M.2.21 | 4230 | 213 | PLANNING | UNPLND |  |  | Yes |  |  |  |  | Technology Program | Daila.Dzintars@HydroOne.com | [6 empty] | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21745 | Inergi Base Services - Smart Metering | N.C.M.1.70 | 4339 | 212 | INFO SOLUTIONS DIVISION | AIP000091D |  | AIP000091 | Yes | AIP000091 | Inergi Sustainment |  |  | IT - Sustainment and Operations | lincoln.frost-hunt@hydroone.com | robert.hosford@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | init EMPP | Executing | Short Term Planning | Retainer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21746 | IT Application Upgrade | N.C.M.2.70 | 4330 | 212 | INFO SOLUTIONS DIVISION | AIP000109A | AIP000109 | AIP000109 | No | AIP000109 | IT Application Upgrade | 0 |  | IT - Project & Architecture Services | lincoln.frost-hunt@hydroone.com | Raj.Agnihotri@HydroOne.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | EMPP AWRD | Executing | Short Term Planning | Retainer | 4390000 | 3849999.96 | 3850000 | 3849999.88 | 3850000 | 3850000.12 | 0 | 0 | 0 | 0 | 4390000 | 3849999.96 | 3850000 | 3849999.88 | 3850000 | 3850000.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | False |  | False | False | True | False | FALSE |  | 0 | 0 | Vulnerable - Tx Contraint Reduction
21747 | IT Application Upgrade - Smart Metering | N.C.M.2.70 | 4330 | 212 | INFO SOLUTIONS DIVISION | AIP000109B | AIP000109 | AIP000109 | No | AIP000109 | IT Application Upgrade | 0 |  | IT - Project & Architecture Services | lincoln.frost-hunt@hydroone.com | Raj.Agnihotri@HydroOne.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | init EMPP | Executing | Short Term Planning | Retainer | 729999.88 | 1729999.92 | 1230000.12 | 1230000.12 | 1230000.08 | 1230000.12 | 0 | 0 | 0 | 0 | 729999.88 | 1729999.92 | 1230000.12 | 1230000.12 | 1230000.08 | 1230000.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | False |  | False | False | True | False | FALSE |  | 0 | 0 | Vulnerable - Tx Contraint Reduction
21750 | Placeholder - Projects to be identified | N.T.C.1.14 | 7700 | 203 | PROJECT DELIVERY | AIP000512 | AIP000512 | AIP000512 | No | AIP000512 | Recoverable projects to be identified - Placeholder | 0 |  | Third Party Transmission System Modifications | john.boldt@HydroOne.com | Gian.Minichini@HydroOne.com | System Renewal | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 999999.96 | 1000000 | 1000000 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1000000 | -999999.96 | -1000000 | -1000000 | -1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43101 | 44696 | True | This is a placeholder for demand-driven projects that spring up | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Recoverable projects to be identified - Placeholder
21752 | Picton TS M6 ID15960 Dx FotoLight LP | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000199 |  | AIP000199 | Yes | AIP000199 | Large Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21753 | Brown Hill TS M4 15950- Dx- BeamLight LP | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000199 |  | AIP000199 | Yes | AIP000199 | Large Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21754 | Waubaushene TS M2 ID15860 DX - Aria LP | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000199 |  | AIP000199 | Yes | AIP000199 | Large Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21755 | Waubaushene TS M2 ID15870 DX - RayLight | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000195 |  | AIP000195 | Yes | AIP000195 | Small Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21756 | Brown Hill TS M12ID15940 -Dx- GoldLight LP | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000199 |  | AIP000199 | Yes | AIP000199 | Large Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21757 | Micro Embedded Generation Connections | N.D.C.2.03 | 7374 | 205 | LINES | AIP000198 | AIP000198 | AIP000198 | No | AIP000198 | Micro Embedded Generation Connections | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Program | ACCP EMPP | Executing | Short Term Planning | # of Gen Connections | 763976.8669 | 565614.9353 | 575180.5562 | 475148.0174 | 482375.6142 | 0 | 0 | 0 | 0 | 0 | 4096514.4669 | 3115006.1753 | 3175559.6762 | 2685470.2174 | 2736904.2542 | 0 | 0 | 0 | 0 | 0 | 6.6613e-10 | 1.1102e-10 | 0 | -2.2204e-10 | 5.5511e-11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3332537.6 | -2549391.24 | -2600379.12 | -2210322.2 | -2254528.64 | 0 | 0 | 0 | 0 | 0 | 450 | 350 | 250 | 100 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
21761 | Guelph Forestry OC Windows Replacement 2011/12 | N.D.C.1.50 | 7236 | 215 | FACILITIES & REAL ESTATE | UNPLND |  |  | Yes |  |  |  |  | Real Estate Facilities | cindy.copp@hydroone.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21762 | B563L (Ashfield SS) - Connect K2 Wind Generator | N.T.C.2.12 | 7700 | 203 | PROJECT DELIVERY | AIP000849 |  | AIP000849 | Yes | AIP000849 |  |  |  | Generator Customer Connection | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21773 | Security Upgrade Cobden OC 2011 | N.D.C.1.50 | 7236 | 215 | FACILITIES & REAL ESTATE | UNPLND |  |  | Yes |  |  |  |  | Real Estate Facilities | cindy.copp@hydroone.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21777 | Whitby TS M23 ID 15750- Tx Index Energy Mills Road | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21779 | Norfolk TS M1 ID15090 - Tx 510 Main St | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000928 |  | AIP000928 | Yes | AIP000928 |  |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | [6 empty] | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21782 | Energy Research Initiatives-ERI | N.D.M.2.22 | 4230 | 213 | PLANNING | UNPLND |  |  | Yes | [12 empty] | Program | AWRD EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21783 | Energy Research Initiatives-ERI | N.T.M.2.22 | 4230 | 213 | PLANNING | UNPLND |  |  | Yes | [12 empty] | Program | EMPP AWRD | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21784 | Green Energy Impact Studies- Tx | N.T.M.2.22 | 4230 | 213 | PLANNING | UNPLND |  |  | Yes | [12 empty] | Program | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21785 | Advanced Grid Studies- Tx | N.T.M.2.22 | 4230 | 213 | PLANNING | UNPLND |  |  | Yes | [12 empty] | Program | AWRD EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21787 | X3H - Connect Kingston Solar Project | N.T.C.2.12 | 7700 | 203 | PROJECT DELIVERY | AIP000926 |  | AIP000926 | Yes | AIP000926 |  |  |  | Generator Customer Connection | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21796 | Coboconk DS F2 ID16140 Dx Norland Hydropower | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000199 |  | AIP000199 | Yes | AIP000199 | Large Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21797 | Coboconk DS F2 ID16140 Tx Norland Hydropower | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000928 |  | AIP000928 | Yes | AIP000928 |  |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | [6 empty] | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21798 | Revenue Meter for DGfacility under 250 kW for 2012 | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Distribution Generation Connection | ryan.boudreau@HydroOne.com | [6 empty] | Project | EMPP ACTN | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21799 | Provincial Mobile Radio System Expansion | N.T.C.3.08 | 7700 | 203 | PROJECT DELIVERY | AIP000992 |  | AIP000992 | Yes | AIP000992 |  |  |  | Integrating Operating Infrastructure | Miroslav.Kostic@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21806 | Mountjoy DS F2 - Remove Underbuild | N.D.C.2.02 | 7374 | 205 | LINES | 3873 |  |  | Yes |  |  |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | [6 empty] | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21807 | Duplex T1/T2A1-A2 M/C Component Replace | N.T.C.1.43 | 7700 | 203 | PROJECT DELIVERY | AIP000404 | AIP000404 | AIP000404 | No | AIP000404 | Duplex TS: A1-A2 M/C & Component Replacements | 0 |  | Greater Toronto Area Zone Station/Yard Investments | James.Mardegan@HydroOne.com | michael.xavier@hydroone.com | System Renewal | Greater Toronto Area | Not Required | 01 - Agreement (current/future) | Not Required | Project | init | Short Term Planning | Short Term Planning |  | 0 | 872836.4542 | 348822.6811 | 1696337.1882 | 322311.7046 | -951852.8283 | 0 | 0 | 0 | 0 | 0 | 938533.8217 | 375078.1517 | 1824018.4819 | 1810912.9654 | 470130.4152 | 0 | 0 | 0 | 0 | 0 | -65697.3675 | -26255.4706 | -127681.2937 | -24260.0208 | 71644.8365 | 0 | 0 | 0 | 0 | -7 | 7.00 | 0 | 0 | 0 | 0 | -1464341.24 | -1493628.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43956 | 45076 | True | THESL Metalclad Replacement Schedule | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | A1-A2 M/C & Component Replacements
21809 | John TS A5-A6 (Windsor) Metalclad Swgr | N.T.C.1.43 | 7700 | 203 | PROJECT DELIVERY | AIP000420 | AIP000420 | AIP000420 | No | AIP000420 | John TS: A5-A6 M/C & Component Replacements | SR-08 | John Transformer Station Reinvestment Project | Greater Toronto Area Zone Station/Yard Investments | James.Mardegan@HydroOne.com | michael.xavier@hydroone.com | System Renewal | Greater Toronto Area | Not Required | 01 - Agreement (current/future) | Not Required | Project | HOLD | Short Term Planning | Short Term Planning |  | 0 | 275632.6603 | 846200.6335 | 815032.6504 | 1089471.6848 | 1645173.4607 | 0 | 0 | 0 | 0 | 0 | 296379.2047 | 909893.1543 | 3722716.274 | 4074738.7699 | 1769003.7211 | 0 | 0 | 0 | 0 | 0 | -20746.5443 | -63692.5208 | -61346.5436 | -82003.2451 | -123830.2605 | 0 | 0 | 0 | 0 | -7 | 7 | 0 | 0 | 0 | -2846337.08 | -2903263.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43525 | 45260 | True | THESL Metalclad replacement Schedule | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Component Replacements
21814 | Studies- Universities | N.D.M.2.22 | 4230 | 213 | PLANNING | AIP000334 |  | AIP000334 | Yes | AIP000334 | [11 empty] | Program | init EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21817 | Cooksville TS Transformer Replacement Project | N.T.C.1.08 | 7700 | 203 | PROJECT DELIVERY | AIP000399 |  | AIP000399 | Yes | AIP000399 |  |  |  | System Re-investment | James.Mardegan@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21825 | Bridgman TS: T11,T12,T13, M/C & Component Replacem | N.T.C.1.43 | 7700 | 203 | PROJECT DELIVERY | AIP000388 | AIP000388 | AIP000388 | No | AIP000388 | Bridgman TS: T11, T12, T13, M/C & Component Replacements | SR-05 | Load Station Transformer Replacement Projects | Greater Toronto Area Zone Station/Yard Investments | James.Mardegan@HydroOne.com | michael.xavier@hydroone.com | System Renewal | Greater Toronto Area | Not Required | 01 - Agreement (current/future) | Required | Project | BEST ACTN | Short Term Planning | Short Term Planning |  | 625894.2984 | 1288123.0701 | 9171874.1152 | 21553406.3044 | 7404342.5431 | 0 | 0 | 0 | 0 | 0 | 673004.622 | 1385078.57 | 9862230.2314 | 23175705.7037 | 7961658.6485 | 0 | 0 | 0 | 0 | 0 | -47110.3235 | -96955.4999 | -690356.1162 | -1622299.3993 | -557316.1054 | 0 | 0 | 0 | 0 | 0 | -7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43704 | 44822 | True | THESL request to increase transformer capacity | True | Site ECA timeline in effect (have until ~2025) | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Component Replacements
21830 | B22D- Connect Armow Wind Farm | N.T.C.2.12 | 7700 | 203 | PROJECT DELIVERY | AIP000844 |  | AIP000844 | Yes | AIP000844 |  |  |  | Generator Customer Connection | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21836 | Steel Structure Refurbishment/Replacement Program | N.T.C.1.12 | 7370 | 206 | TX LINES AND STATIONS | AIP000467 |  | AIP000467 | Yes | AIP000467 |  |  |  | Overhead Lines Component Refurb & Repl | hassan.hamzeh@hydroone.com | [6 empty] | Program | ACCP EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21848 | Woodstock TS T1 & T2 Transformer Replacement Prog | N.T.C.1.17 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Power Transformers | James.Mardegan@HydroOne.com | [6 empty] | Program | ACCP EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21850 | Lakehead TS T7&T8 Transformer Replacement Prog. | N.T.C.1.17 | 7700 | 203 | PROJECT DELIVERY | AIP000560C |  | AIP000560 | Yes | AIP000560 | Replace EOL Large Transformers Program |  |  | Power Transformers | James.Mardegan@HydroOne.com | peter.zhao@hydroone.com | System Renewal | 0 | 0 | 03 - None (default) | 0 | Project | ACTN EMPP | Executing | Executing | # of Transformers | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21851 | Dymond TS T3&T4 Transformer Replacement Prog. | N.T.C.1.17 | 7700 | 203 | PROJECT DELIVERY | AIP000560B | AIP000560 | AIP000560 | No | AIP000560 | Replace EOL Large Transformers Program | 0 |  | Power Transformers | James.Mardegan@HydroOne.com | peter.zhao@hydroone.com | System Renewal | 0 | 0 | 03 - None (default) | 0 | Project | ACCP EMPP | Executing | Executing | # of Transformers | 243422.799 | 0 | 0.0098282 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 261744.9451 | 0 | 0.010568 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -18322.1462 | 0 | -0.00073975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43084 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Vulnerable
21854 | Almonte TS T4 Transformer Replacement Project | N.T.C.1.17 | 7700 | 203 | PROJECT DELIVERY | AIP000560 |  | AIP000560 | Yes | AIP000560 | Replace EOL Large Transformers Program |  |  | Power Transformers | James.Mardegan@HydroOne.com | peter.zhao@hydroone.com | System Renewal | 0 | 0 | 03 - None (default) | 0 | Program | init | Short Term Planning | Short Term Planning | # of Transformers | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21861 | Hawthorne TS ISCR | N.T.C.1.10 | 7700 | 203 | PROJECT DELIVERY | AIP005078 | AIP005078 | AIP005078 | No | AIP005078 | Hawthorne TS - ISCR | 0 |  | Integrated Station Component Replacement | James.Mardegan@HydroOne.com | Fred.Kouhdani@HydroOne.com | System Renewal | Eastern | 0 | 03 - None (default) | 0 | Project | ACTN EMPP | Executing | Executing | Components | 9331988.2063 | 2140356.0067 | 0.078625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9752608.4839 | 2140356.0067 | 0.078625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -420620.2777 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3.5346 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43759 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
21863 | Keith TS T1 Transformer Replacement Program | N.T.C.1.17 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Power Transformers | James.Mardegan@HydroOne.com | [6 empty] | Program | init EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21864 | Martindale TS T 22 Transformer Replacement program | N.T.C.1.17 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Power Transformers | James.Mardegan@HydroOne.com | [6 empty] | Program | EMPP ACCP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21865 | Hanmer TS: Northern Station Replacement Project | N.T.C.1.45 | 7700 | 203 | PROJECT DELIVERY | AIP005265 | AIP005265 | AIP005265 | No | AIP005265 | Hanmer TS: Northern Station Replacement Project | SR-02 | Station Reinvestment Projects | Northern Zone Station/Yard Investments | James.Mardegan@HydroOne.com | Donald.Mastrangelo@HydroOne.com | System Renewal | Northern | Not Required | 03 - None (default) | Required | Project | ACTN EMPP | Executing | Executing |  | 19897461.8436 | 8060127.9633 | 0.078625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20133020.1372 | 8067065.0969 | 0.078625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -235558.2936 | -6937.1336 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -0.85916 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43710 | [13 empty] | FALSE |  | 0 | 0 | Component replacement
21868 | Centralia TS T1/T2/T3; T1,T2,T3, PCT, MVGIS | N.T.C.1.40 | 7700 | 203 | PROJECT DELIVERY | AIP000395 | AIP000395 | AIP000395 | No | AIP000395 | Centralia TS T1/T2/T3; T1,T2,T3, PCT, MVGIS | 0 |  | Western Zone Station/Yard Investments | James.Mardegan@HydroOne.com | mark.truchanowicz@hydroone.com | System Renewal | Western | 0 | 03 - None (default) | 0 | Project | EMPP ACCP | Executing | Executing |  | 5956555.8911 | 0 | 0.039313 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5956555.8911 | 0 | 0.039313 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43434 | [13 empty] | FALSE |  | 1 | 1 | Station Replacement
21871 | Stanley TS T2 Replacement Project | N.T.C.1.17 | 7700 | 203 | PROJECT DELIVERY | AIP000560A |  | AIP000560 | Yes | AIP000560 | Replace EOL Large Transformers Program |  |  | Power Transformers | James.Mardegan@HydroOne.com | peter.zhao@hydroone.com | System Renewal | 0 | 0 | 03 - None (default) | 0 | Program | EMPP ACTN | Executing | Short Term Planning | # of Transformers | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21872 | Cobden TS T1&T2 Replacement Project | N.T.C.1.17 | 7700 | 203 | PROJECT DELIVERY | AIP000560E |  | AIP000560 | Yes | AIP000560 | Replace EOL Large Transformers Program |  |  | Power Transformers | James.Mardegan@HydroOne.com | peter.zhao@hydroone.com | System Renewal | 0 | 0 | 03 - None (default) | 0 | Program | ACCP EMPP | Executing | Short Term Planning | # of Transformers | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21873 | Chesterville TS T1& T2 Replacement Project | N.T.C.1.17 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Power Transformers | James.Mardegan@HydroOne.com | [6 empty] | Program | ACCP EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21880 | Rogers TCA Equipment Change Out - Recoverable | N.T.C.1.14 | 7700 | 203 | PROJECT DELIVERY | AIP000524 |  | AIP000524 | Yes | AIP000524 |  |  |  | Third Party Transmission System Modifications | john.boldt@HydroOne.com | [6 empty] | Project | DETL HOLD | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21890 | Micro Embedded Net Metered Generation Connections | N.D.C.2.03 | 7374 | 205 | LINES | AIP000200 | AIP000200 | AIP000200 | No | AIP000200 | Net Metered Embedded Generation | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 03 - None (default) | 0 | Program | ACTN EMPP | Executing | Short Term Planning | # of connections | -9380.3014 | -10631.8358 | -10852.5109 | -11075.6591 | -11296.8091 | 0 | 0 | 0 | 0 | 0 | 1129930.9786 | 1981080.0442 | 2528851.0491 | 3442552.8609 | 3511404.1909 | 0 | 0 | 0 | 0 | 0 | 6.245e-11 | -8.1532e-11 | 8.3267e-11 | 2.9664e-10 | 1.8215e-10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1139311.28 | -1991711.88 | -2539703.56 | -3453628.52 | -3522701 | 0 | 0 | 0 | 0 | 0 | 70 | 120 | 150 | 200 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
21961 | Waubaushene TS M2 ID15870 Tx-RayLight | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | [6 empty] | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21964 | Goderich TS - New Feeder Position | N.T.C.2.11 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Load Customer Connection | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21971 | Picton TS M6 ID15960 Tx-FotoLight LP | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000928 |  | AIP000928 | Yes | AIP000928 |  |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | [6 empty] | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21973 | Wilson TS M15 ID10250 Tx - Clarington #1 | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000928 |  | AIP000928 | Yes | AIP000928 |  |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21976 | MicroFIT Mitigation (2012 - onwards) - Program | N.D.C.2.03 | 7374 | 205 | LINES | UNPLND |  |  | Yes |  |  |  |  | Distribution Generation Connection | ryan.boudreau@HydroOne.com | [6 empty] | Program | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21979 | Guelph OC Fence Replacement 2012 | N.D.C.1.50 | 7236 | 215 | FACILITIES & REAL ESTATE | UNPLND |  |  | Yes |  |  |  |  | Real Estate Facilities | cindy.copp@hydroone.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21986 | H24C - Line Refurbishment | N.T.C.1.12 | 7700 | 203 | PROJECT DELIVERY | AIP000489 |  | AIP000489 | Yes | AIP000489 |  |  |  | Overhead Lines Component Refurb & Repl | hassan.hamzeh@hydroone.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21987 | H27H - Line Refurbishment | N.T.C.1.14 | 7700 | 203 | PROJECT DELIVERY | AIP005033B |  | AIP005033 | Yes | AIP005033 |  |  |  | Third Party Transmission System Modifications | john.boldt@HydroOne.com | [6 empty] | Program | EMPP ACCP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22016 | R&D Program, E&PD | N.T.M.2.21 | 4230 | 213 | PLANNING | AIP001164 |  | AIP001164 | Yes | AIP001164 |  |  |  | Technology Program | Daila.Dzintars@HydroOne.com | [6 empty] | Program | AWRD EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22020 | Orangeville TS New 27.6 kV Feeder | N.D.C.2.02 | 7374 | 205 | LINES | UNPLND |  |  | Yes |  |  |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | [6 empty] | Project | EMPP ACTN | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22025 | Snow Road DS-SSI | N.D.C.2.02 | 7374 | 205 | LINES | AIP000183A |  | AIP000183 | Yes | AIP000183 | (1) System upgrade driven by load growth |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Michael.Medeiros@HydroOne.com | System Service | 0 | 0 | 03 - None (default) | Not Required | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22028 | Grounding Transformer Installations | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000192 | AIP000192 | AIP000192 | No | AIP000192 | Delta-Wye TOV Mitigation Work (Lines) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | Cecilia.Pang@HydroOne.com | System Access | 0 | 0 | 0 | Not Required | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43033 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
22030 | Picton TS M7 ID16620 Dx Sunny Shores Solar Farm | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000199 |  | AIP000199 | Yes | AIP000199 | Large Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22031 | Picton TS M7 ID16620 Tx Sunny Shores Solar Farm | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22032 | Crawford TS -Recoverable Review and Monitoring | N.T.C.2.11 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Load Customer Connection | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22035 | Tx Lines Damage Claims and Costs | N.T.C.1.12 | 7370 | 206 | TX LINES AND STATIONS | AIP000473 | AIP000473 | AIP000473 | No | AIP000473 | Tx Lines Damage Claims | 0 |  | Overhead Lines Component Refurb & Repl | hassan.hamzeh@hydroone.com | TeodorConstantin.Culinescu@HydroOne.com | System Renewal | 0 | 0 | 01 - Agreement (current/future) | 0 | Program | EMPP ACTN | Executing | Short Term Planning | Retainer | 85687.6095 | 87106.5739 | 88113.2143 | 88795.558 | 89470.3642 | 90476.2168 | 0 | 0 | 0 | 0 | 240312.2835 | 244783.5031 | 248843.4126 | 252593.1231 | 256393.6684 | 260631.2027 | 0 | 0 | 0 | 0 | -11684.674 | -11878.1692 | -12015.4383 | -12108.4852 | -12200.5042 | -12337.6659 | 0 | 0 | 0 | 0 | -12 | 12 | -142940 | -145798.76 | -148714.76 | -151689.08 | -154722.8 | -157817.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Demand
22040 | Waste Bin Replacement | N.D.C.1.04 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | PCB Transformer Replacement | emre.aydin@HydroOne.com | [6 empty] | Program | ACCP EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22041 | Tillsonburg IPCC Cap Bank Replacement | N.T.C.1.18 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Other Power Equipment | James.Mardegan@HydroOne.com | [6 empty] | Project | BEST ACTN | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22042 | Construction Service Equipment | N.C.C.1.40 | 7411 | 228 | CONSTRUCTION | AIP000017 | AIP000017 | AIP000017 | No | AIP000017 | Construction Service Equipment | 0 |  | Work Equipment | Mike.Tanaskovic@HydroOne.com | Farinaz.Yousefi@HydroOne.com | General Plant | 0 | 0 | 03 - None (default) | 0 | Program | ACTN EMPP | Executing | Short Term Planning | 228-CC1XX | 800000 | 796578.1095 | 789570.0534 | 779948.1851 | 770247.7003 | 763475.5827 | 0 | 0 | 0 | 0 | 800000 | 796578.1095 | 789570.0534 | 779948.1851 | 770247.7003 | 763475.5827 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | False |  | False | False | False | False | TRUE | All the purchases from Megger and Menta and TVC canada– P&C mandated NERC NPCC&TSC Regulation. Ministry regulations such as CSA 225, CVOR regulations. | 0 | 0 | Asset Optimal
22045 | Recloser Retrofit Project | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Distribution Generation Connection | ryan.boudreau@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22046 | Fault-Prone Indoor GE Meter Replacement | N.D.C.1.09 | 7374 | 205 | LINES | UNPLND |  |  | Yes |  |  |  |  | Metering | Peter.Mitskos@HydroOne.com | [6 empty] | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22050 | Garage Bay Improvements Richview TS 2012 | N.T.C.1.28 | 7236 | 215 | FACILITIES & REAL ESTATE | UNPLND |  |  | Yes |  |  |  |  | Transmission Site Facilities | cindy.copp@hydroone.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22051 | Failure Investigations | N.D.M.1.02 | 4048 | 213 | PLANNING | AIP000233 | AIP000233 | AIP000233 | No | AIP000233 | Failure Investigations |  |  | Line Maintenance and Repair | emre.aydin@HydroOne.com | Matthew.Bell@HydroOne.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | AWRD EMPP | Executing | Short Term Planning | Investigations | 101090.2627 | 104158.0623 | 106435.5731 | 108802.2479 | 110829.4295 | 0 | 0 | 0 | 0 | 0 | 101090.2627 | 104158.0623 | 106435.5731 | 108802.2479 | 110829.4295 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Vulnerable
22057 | Brown Hill TS New 44 kV Feeder | N.D.C.2.02 | 7374 | 205 | LINES | AIP000183A |  | AIP000183 | Yes | AIP000183 | (1) System upgrade driven by load growth |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Michael.Medeiros@HydroOne.com | System Service | 0 | 0 | 03 - None (default) | Not Required | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22060 | Nebo TS M6 Tie Line on Wilson Rd | N.D.C.2.02 | 7374 | 205 | LINES | UNPLND |  |  | Yes |  |  |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | [6 empty] | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22061 | Festival Hydro: Provide Line Connection to New MTS | N.T.C.2.11 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Load Customer Connection | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22068 | Bolton Operation Centre | N.D.C.1.50 | 7236 | 215 | FACILITIES & REAL ESTATE | AIP000027 |  | AIP000027 | Yes | AIP000027 | Facility Accommodation & Improvements Service Centres & Admin |  |  | Real Estate Facilities | cindy.copp@hydroone.com | Peter.Erdman@HydroOne.com | General Plant | 0 | 0 | 03 - None (default) | 0 | Program | EMPP AWRD | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22069 | Manotick DS F5 ID 19080 Schouten Farms DX | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000199 |  | AIP000199 | Yes | AIP000199 | Large Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22071 | OGCC HVAC Replacement 2012 | N.C.C.1.50 | 7236 | 215 | FACILITIES & REAL ESTATE | UNPLND |  |  | Yes |  |  |  |  | Real Estate Facilities | cindy.copp@hydroone.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22074 | Mountjoy DS Voltage Conversion | N.D.C.2.02 | 7374 | 205 | LINES | AIP000184A |  | AIP000184 | Yes | AIP000184 | (2) Asset Life Cycle Optimization & Operational Efficiency |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Michael.Medeiros@HydroOne.com | System Renewal | 0 | 0 | 03 - None (default) | 0 | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22076 | Iroquois Falls: Conductor Upgrade | N.T.C.2.11 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Load Customer Connection | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22077 | Toronto-GTS Expansion Project-Recoverable | N.T.C.1.14 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Third Party Transmission System Modifications | john.boldt@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22078 | Load Displacement Capacity and Assessment | N.D.M.2.03 | 4363 | 213 | PLANNING | UNPLND |  |  | Yes |  |  |  |  | Distributed Generation Connections | ryan.boudreau@HydroOne.com | [6 empty] | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22082 | Clarabelle TS - M8 Feeder Relief | N.D.C.2.02 | 7374 | 205 | LINES | AIP000183A |  | AIP000183 | Yes | AIP000183 | (1) System upgrade driven by load growth |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Michael.Medeiros@HydroOne.com | System Service | 0 | 0 | 03 - None (default) | Not Required | Project | EMPP AWRD | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22083 | Chesterville TS New Feeder 73M1 | N.D.C.2.02 | 4048 | 213 | PLANNING | UNPLND |  |  | Yes |  |  |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | [6 empty] | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22084 | Cataraqui Woods Drive Reinforcement | N.D.C.2.02 | 7374 | 205 | LINES | AIP005272 | AIP005272 | AIP005272 | No | AIP005272 | Cataraqui Woods Drive Reinforcement | ISD-SS-02 | System Upgrades Driven by Load Growth | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Daniel.Weisser@HydroOne.com | System Service | Eastern | 0 | 03 - None (default) | 0 | Project | DETL EXTR | Short Term Planning | Short Term Planning |  | 74714.0059 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84902.2794 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -10188.2735 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42702 | 43142 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
22086 | Lindsay OC Office Renovations 2012 | N.D.C.1.50 | 7236 | 215 | FACILITIES & REAL ESTATE | UNPLND |  |  | Yes |  |  |  |  | Real Estate Facilities | cindy.copp@hydroone.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22087 | 2012 Budget NCC150 | N.C.C.1.50 | 7236 | 215 | FACILITIES & REAL ESTATE | UNPLND |  |  | Yes |  |  |  |  | Real Estate Facilities | cindy.copp@hydroone.com | [6 empty] | Program | AWRD EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22089 | NTC128 Budget 2012 | N.T.C.1.28 | 7236 | 215 | FACILITIES & REAL ESTATE | UNPLND |  |  | Yes |  |  |  |  | Transmission Site Facilities | cindy.copp@hydroone.com | [6 empty] | Program | EMPP AWRD | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22091 | Orillia TS M1 ID16880-TX H06-3225 Monarch | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22093 | Public Safety Hazard Hamlet Presentations | N.C.M.3.03 | 7053 | 209 | HEALTH, SAFETY & ENV | AIP000122B | AIP000122 | AIP000122 | No | AIP000122 | Public Electrical Safety Presentations | 0 |  | Environment Health and Safety | welchw@hydroone.com | welchw@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | init | Short Term Planning | Short Term Planning | Assumption - program covers employees attending schools, fairs, plowing match, etc. to deliver safety messages. Includes production of materials used for presentations. | 370000 | 370000.04 | 370000 | 369999.96 | 370000 | 349999.96 | 0 | 0 | 0 | 0 | 370000 | 370000.04 | 370000 | 369999.96 | 370000 | 349999.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 271 | 271 | 271 | 271 | 271 | 271 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Optimal - (Modified-Tx Decision)
22094 | Large Diesel Generator Upgrade Project | N.T.C.1.18 | 7700 | 203 | PROJECT DELIVERY | AIP000574 |  | AIP000574 | Yes | AIP000574 |  |  |  | Other Power Equipment | James.Mardegan@HydroOne.com | [6 empty] | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22095 | Point Au Baril DS F2 Feeder Extension | N.D.C.2.02 | 7374 | 205 | LINES | AIP000183A |  | AIP000183 | Yes | AIP000183 | (1) System upgrade driven by load growth |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Michael.Medeiros@HydroOne.com | System Service | 0 | 0 | 03 - None (default) | Not Required | Project | DETL ACTN | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22099 | IT 3rd Party Contracts - Smart Metering | N.C.M.1.70 | 4339 | 212 | INFO SOLUTIONS DIVISION | AIP000090B |  | AIP000090 | Yes | AIP000090 | 3rd Party Contracts |  |  | IT - Sustainment and Operations | lincoln.frost-hunt@hydroone.com | robert.hosford@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | EMPP init | Executing | Short Term Planning | Retainer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22104 | Birmingham TS Roof Repair 2012 | N.T.C.1.28 | 7236 | 215 | FACILITIES & REAL ESTATE | UNPLND |  |  | Yes |  |  |  |  | Transmission Site Facilities | cindy.copp@hydroone.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22105 | Bayridge Drive Reinforcement | N.D.C.2.02 | 7374 | 205 | LINES | AIP005274 |  | AIP005274 | Yes | AIP005274 |  |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | [6 empty] | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22111 | Manby 230kV Reconfiguration | N.T.C.2.02 | 7700 | 203 | PROJECT DELIVERY | AIP000707 |  | AIP000707 | Yes | AIP000707 |  |  |  | Local Area Supply | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22118 | On Call Environmental Assistance | N.D.M.1.06 | 7054 | 209 | HEALTH, SAFETY & ENV | UNPLND |  |  | Yes |  |  |  |  | PCB Test and Destruction | emre.aydin@HydroOne.com | [6 empty] | Program | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22119 | PCB and Other Waste Management | N.D.M.1.06 | 7054 | 209 | HEALTH, SAFETY & ENV | UNPLND |  |  | Yes |  |  |  |  | PCB Test and Destruction | emre.aydin@HydroOne.com | [6 empty] | Program | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22120 | Baywood OC Roof Replacement 2012 | N.T.C.1.28 | 7236 | 215 | FACILITIES & REAL ESTATE | UNPLND |  |  | Yes |  |  |  |  | Transmission Site Facilities | cindy.copp@hydroone.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22123 | Micro Inverter RTDS study and dynamic model dvlp | N.D.M.2.03 | 4171 | 213 | PLANNING | UNPLND |  |  | Yes |  |  |  |  | Distributed Generation Connections | ryan.boudreau@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22125 | Stations Environmental Compliance | N.T.M.1.05 | 7054 | 209 | HEALTH, SAFETY & ENV | AIP001015 |  | AIP001015 | Yes | AIP001015 | Stations Environmental Compliance |  |  | Environmental Management | Mike.Tanaskovic@HydroOne.com | Sebastian.Niculae@HydroOne.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | init | Short Term Planning | Short Term Planning | Assumption - # of stations sampled | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22126 | Transmission PCB and Regulated Waste Manage | N.T.M.1.05 | 7054 | 209 | HEALTH, SAFETY & ENV | AIP001016 |  | AIP001016 | Yes | AIP001016 | Transmission PCB and Regulated Waste Manage |  |  | Environmental Management | Mike.Tanaskovic@HydroOne.com | Harshal.Bhatt@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | init | Short Term Planning | Short Term Planning | 209-TM1XX | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22127 | Awenda DS - Upgrade F2 Feeder Recloser to VIPER | N.D.C.2.02 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22129 | Kapuskasing TS M4 ID17860-DX Hydro Kapuskasing Hyd | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000199 |  | AIP000199 | Yes | AIP000199 | Large Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22131 | Ft. Frances TS: Remove T3 and Reconnect SC1&2 | N.T.C.2.11 | 7700 | 203 | PROJECT DELIVERY | AIP000782 |  | AIP000782 | Yes | AIP000782 |  |  |  | Load Customer Connection | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | EMPP ACTN | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22135 | Kapuskasing TS M4 ID17860-TX Hydro Kapuskasing Hyd | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22141 | D10S/D9HS - Line Refurbishment | N.T.C.1.12 | 7700 | 203 | PROJECT DELIVERY | AIP000486 |  | AIP000486 | Yes | AIP000486 |  |  |  | Overhead Lines Component Refurb & Repl | hassan.hamzeh@hydroone.com | [6 empty] | Program | ACTN EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22150 | IPS Replacement Project | N.T.C.1.29 | 4514 | 212 | INFO SOLUTIONS DIVISION | AIP000679 |  | AIP000679 | Yes | AIP000679 |  |  |  | NERC Cyber Security Compliance Readiness | lincoln.frost-hunt@hydroone.com | [6 empty] | Project | EMPP init | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22152 | Crystal Falls TS M1 ID18380 Tx-WNPG Turbines Upgrd | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000928 |  | AIP000928 | Yes | AIP000928 |  |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22154 | L5H Idle Line Removal Non-Recoverable | N.T.C.1.14 | 7700 | 203 | PROJECT DELIVERY | AIP000485 |  | AIP000485 | Yes | AIP000485 |  |  |  | Third Party Transmission System Modifications | john.boldt@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22155 | Cherrywood TS - Install 2x250MVAr Cap Banks | N.T.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000722 | AIP000722 | AIP000722 | No | AIP000722 | Cherrywood TS - Install 2x250MVAr Cap Banks | SS-07 | Cherrywood TS: Install Two Capacitor Banks | Network Transfer Capability | Robert.Reinmuller@HydroOne.com | Jean.Morneau@HydroOne.com | System Service | Central | Not Required | 03 - None (default) | Not Required | Project | ACTN BEST | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 480790.9448 | 3336408.2938 | 7576863.0913 | 3000000 | 0 | 0 | 0 | 0 | 0 | 0 | 480790.9448 | 3336408.2938 | 7576863.0913 | 3000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44712 | 45443 | True | IESO Request | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Alternative 1
22156 | Almonte TS - Install new 230 kV Breaker | N.T.C.2.02 | 7700 | 203 | PROJECT DELIVERY | AIP000694 |  | AIP000694 | Yes | AIP000694 |  |  |  | Local Area Supply | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22157 | DS Operating Spare Mtce & Inspection | N.D.M.1.04 | 7370 | 206 | TX LINES AND STATIONS | AIP000260 | AIP000260 | AIP000260 | No | AIP000260 | Dx Preventive Maintenance - Operating Spare |  |  | Distributing and Regulating Stations | emre.aydin@HydroOne.com | Trevor.Beausoleil@HydroOne.com | System O&M | N/A | 0 | 03 - None (default) | 0 | Program | ACTN EMPP | Executing | Short Term Planning | # of Orders | 73165.1379 | 75385.4535 | 77033.772 | 78746.7169 | 80213.832 | 0 | 0 | 0 | 0 | 0 | 73165.1379 | 75385.4535 | 77033.772 | 78746.7169 | 80213.832 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 166 | 166 | 166 | 166 | 166 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Vulnerable
22160 | Infra / Tech Refresh - Smart Meter | N.C.C.1.70 | 4339 | 212 | INFO SOLUTIONS DIVISION | AIP000036 | AIP000036 | AIP000036 | No | AIP000036 | Infrastructure Tech refresh - Smart Meter | GP-07 | Hardware/Software Refresh and Maintenance | IT - Sustainment and Operations | lincoln.frost-hunt@hydroone.com | Raj.Agnihotri@HydroOne.com | General Plant | 0 | 0 | 03 - None (default) | 0 | Program | EMPP init | Executing | Short Term Planning | Retainer | 120000.24 | 119486.9674 | 118435.7449 | 117221.8835 | 115763.9545 | 114521.3374 | 0 | 0 | 0 | 0 | 120000.24 | 119486.9674 | 118435.7449 | 117221.8835 | 115763.9545 | 114521.3374 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | False |  | False | False | False | False | TRUE | Hydro One adheres to to an IT industry standard practice of managing its assets through a lifecycle program ensuring vendor support is available and decreasing the likelihood of failure. Funding decisions are made based on software lifecycles, vendor schedules, reliability requirements, and experience with similar initiatives/projects. Refreshes for applications in sustainment are funded from this investment. The only exception is if the refresh is going to drive new funcitonality that can be tied to a Business Case. | 0 | 0 | Intermediate
22161 | Seaforth TS-ID17740-Dx-St Columban 2 wind project | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000199 |  | AIP000199 | Yes | AIP000199 | Large Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22162 | Seaforth TS-ID17740-Tx-St Columban 2 Wind Project | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22163 | Microwave Tower Alarm Monitoring System | N.T.C.1.25 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Auxiliary Telecommunication Equipment | Miroslav.Kostic@HydroOne.com | [6 empty] | Project | EMPP ACTN | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22165 | V73R/V74R self damping conductor replacement | N.T.C.1.14 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Third Party Transmission System Modifications | john.boldt@HydroOne.com | [6 empty] | Project | DETL ACTN | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22166 | Owen Sound TS M28 Extension to Brookholm DS | N.D.C.2.02 | 7374 | 205 | LINES | AIP005227 |  | AIP005227 | Yes | AIP005227 |  |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | [6 empty] | Project | EMPP AWRD | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22168 | Wingham TS-ID17730-Tx-St Columban Wind Proje | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22170 | Hanover TS-H1E-ID17750-Dx-East Durham Wind Energy | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000199 |  | AIP000199 | Yes | AIP000199 | Large Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22180 | Malden TS -Two 28kV feeders | N.T.C.2.11 | 7700 | 203 | PROJECT DELIVERY | AIP000798 |  | AIP000798 | Yes | AIP000798 |  |  |  | Load Customer Connection | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | DETL ACCP | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22186 | Hinchey TS T3&T4 Transformer Replacement Program | N.T.C.1.17 | 7700 | 203 | PROJECT DELIVERY | AIP000560F |  | AIP000560 | Yes | AIP000560 | Replace EOL Large Transformers Program |  |  | Power Transformers | James.Mardegan@HydroOne.com | peter.zhao@hydroone.com | System Renewal | 0 | 0 | 03 - None (default) | 0 | Program | ACCP EMPP | Executing | Short Term Planning | # of Transformers | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22188 | Pembroke TS T1&T2 Transformer Replacement Program | N.T.C.1.17 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Power Transformers | James.Mardegan@HydroOne.com | [6 empty] | Program | ACCP EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22198 | NWGTA Electricity Corridor - Concep. Planning & EA | N.T.M.2.02 | 7700 | 203 | PROJECT DELIVERY | AIP001156 | AIP001156 | AIP001156 | No | AIP001156 | NWGTA Electricity Corridor - Concept. Planning & EA | 0 |  | Infrastructure Development | Robert.Reinmuller@HydroOne.com | Alessia.Dawes@HydroOne.com | System O&M | 0 | Required | 03 - None (default) | Required | Project | HOLD BEST | Short Term Planning | Short Term Planning |  | 0 | 977099.9542 | 1468603.8587 | 1472413.9078 | 1473106.9609 | 0 | 0 | 0 | 0 | 0 | 0 | 977099.9542 | 1468603.8587 | 1472413.9078 | 1473106.9609 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43469 | 45992 | True | We will be directed by either the IESO or the Ministry to Develop a new transmission corridor | False |  | False | We will be directed by either the IESO or the Ministry to Develop a new transmission corridor | False | False |  | True | False | False | False | FALSE |  | 0 | 0 | Alternative 1 (Modified)
22210 | Park Road DS Transformer Fan Monitoring | N.D.C.2.02 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22215 | Manitouwadge T1- Replace EOL Transformers | N.T.C.1.17 | 7700 | 203 | PROJECT DELIVERY | AIP000560G |  | AIP000560 | Yes | AIP000560 | Replace EOL Large Transformers Program |  |  | Power Transformers | James.Mardegan@HydroOne.com | peter.zhao@hydroone.com | System Renewal | 0 | 0 | 03 - None (default) | 0 | Project | EMPP init | Executing | Executing | # of Transformers | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22217 | Mooselake TS, T2- Replace EOL Transformers | N.T.C.1.17 | 7700 | 203 | PROJECT DELIVERY | AIP000560H |  | AIP000560 | Yes | AIP000560 | Replace EOL Large Transformers Program |  |  | Power Transformers | James.Mardegan@HydroOne.com | peter.zhao@hydroone.com | System Renewal | 0 | 0 | 03 - None (default) | 0 | Program | ACCP EMPP | Executing | Short Term Planning | # of Transformers | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22218 | Thornton TS T3 T4- Replace EOL Transformers | N.T.C.1.17 | 7700 | 203 | PROJECT DELIVERY | AIP000560D |  | AIP000560 | Yes | AIP000560 | Replace EOL Large Transformers Program |  |  | Power Transformers | James.Mardegan@HydroOne.com | peter.zhao@hydroone.com | System Renewal | 0 | 0 | 03 - None (default) | 0 | Program | ACTN EMPP | Executing | Short Term Planning | # of Transformers | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22225 | 3rdParty HONI station/Lines Monitoring-Recoverable | N.T.M.1.20 | 4048 | 213 | PLANNING | AIP001114 | AIP001114 | AIP001114 | No | AIP001114 | Recoverable - Third Party Monitoring/Maintenance | 0 |  | Overhead Lines | hassan.hamzeh@hydroone.com | Gian.Minichini@HydroOne.com | System O&M | 0 | 0 | 01 - Agreement (current/future) | 0 | Program | AWRD EMPP | Executing | Short Term Planning | Retainer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 999999.96 | 1000000 | 1000000 | 1000000 | 1000000.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1000000 | -999999.96 | -1000000 | -1000000 | -1000000 | -1000000.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | True | Various | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Recoverable - Third Party Monitoring/Maintenance
22230 | Independent Compliance Audit | N.T.M.1.29 | 4230 | 213 | PLANNING | UNPLND |  |  | Yes |  |  |  |  | NERC Cyber Security Compliance Readiness | lincoln.frost-hunt@hydroone.com | [6 empty] | Program | EMPP init | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22231 | Kimberly DS F3 Feeder Extension | N.D.C.2.02 | 7374 | 205 | LINES | AIP000183A |  | AIP000183 | Yes | AIP000183 | (1) System upgrade driven by load growth |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Michael.Medeiros@HydroOne.com | System Service | 0 | 0 | 03 - None (default) | Not Required | Project | ACTN BEST | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22232 | City of Owen Sound Tie-Line Reinforcement | N.D.C.2.02 | 7374 | 205 | LINES | AIP005400 | AIP005400 | AIP005400 | No | AIP005400 | City of Owen Sound Tie Line Reinforcement | ISD-SS-02 | System Upgrades Driven by Load Growth | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Jerry.Vo@HydroOne.com | System Service | 0 | 0 | 03 - None (default) | 0 | Project | init BEST | Short Term Planning | Short Term Planning |  | 970974.7882 | 326688.6972 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1106083.9872 | 372629.2966 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -135109.1989 | -45940.5994 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -12.2437 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43174 | 43494 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
22233 | Town of Meaford Tie-Line Reinforcement | N.D.C.2.02 | 7374 | 205 | LINES | AIP005424 | AIP005424 | AIP005424 | No | AIP005424 | Town of Meaford Tie Line Reinforcement |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Jerry.Vo@HydroOne.com | System Service | 0 | 0 | 03 - None (default) | 0 | Project | EMPP AWRD | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42704 | 43039 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
22235 | Removals - Revenue Meter Installations | N.D.C.2.05 | 7374 | 205 | LINES | AIP000203B |  | AIP000203 | Yes | AIP000203 | Revenue Meter - Removals |  |  | Wholesale Metering | Peter.Mitskos@HydroOne.com | Dominic.Consorti@HydroOne.com | System Access | 0 | 0 | 03 - None (default) | 0 | Program | EMPP EXTR | Executing | Short Term Planning | # of Meter Installations | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22240 | Mattawa HVDS | N.D.C.2.02 | 7700 | 203 | PROJECT DELIVERY | AIP005235 | AIP005235 | AIP005235 | No | AIP005235 | Mattawa HVDS - New Station |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Jerry.Vo@HydroOne.com | System Renewal | 0 | Not Required | 03 - None (default) | Complete | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42215 | 42825 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
22242 | Malden TS M12 ID19180-Dx River Canard Energy N | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000195 |  | AIP000195 | Yes | AIP000195 | Small Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22247 | Ear Falls TS, EOL T5, Asset Replacement Project | N.T.C.1.08 | 7700 | 203 | PROJECT DELIVERY | AIP000408 | AIP000408 | AIP000408 | No | AIP000408 | Ear Falls TS; T5 - Yard Repalcement | 0 |  | System Re-investment | James.Mardegan@HydroOne.com | Donald.Mastrangelo@HydroOne.com | System Renewal | Northern | 0 | 03 - None (default) | 0 | Project | EMPP ACTN | Executing | Executing |  | 4742715.4854 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5150796.5953 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -408081.1099 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -7.9227 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43373 | [13 empty] | FALSE |  | 0 | 1 | Alternative 1- Build new HVDS
22251 | Upstream LDC Payments - DX | N.D.M.2.03 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Distributed Generation Connections | ryan.boudreau@HydroOne.com | [6 empty] | Program | ACTN EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22263 | Wallaceburg TS-Feeder M1- ID 17530-SA3 | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22265 | Extreme Space Weather Prepardness Phase II | N.T.C.3.08 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Integrating Operating Infrastructure | Miroslav.Kostic@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22275 | Thunder Bay - Pipeline Easement-Recoverable | N.T.M.1.20 | 4048 | 213 | PLANNING | UNPLND |  |  | Yes |  |  |  |  | Overhead Lines | hassan.hamzeh@hydroone.com | [6 empty] | Project | EMPP AWRD | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22279 | Holland TS - Add Breakers and Re-terminate Lines | N.T.C.2.02 | 7700 | 203 | PROJECT DELIVERY | AIP000701 | AIP000701 | AIP000701 | No | AIP000701 | York Region - Increase Transmission Capability for B82V/B83V | 0 |  | Local Area Supply | Robert.Reinmuller@HydroOne.com | E.Warren.King@HydroOne.com | System Service | Central | Not Required | 02 - Expectation (no agreement) | Required | Project | ACCP EMPP | Executing | Executing |  | 73106.3896 | 0 | 0.058969 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73106.3896 | 0 | 0.058969 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43044 | [13 empty] | FALSE |  | 0 | 0 | Alternative 1
22285 | Ottawa Telecom Cable Removals | N.T.C.1.25 | 7700 | 203 | PROJECT DELIVERY | AIP000655 |  | AIP000655 | Yes | AIP000655 |  |  |  | Auxiliary Telecommunication Equipment | Miroslav.Kostic@HydroOne.com | [6 empty] | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22287 | Upper Beaver Mine(Osisko)-115kV Mine Connection | N.T.C.2.11 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Load Customer Connection | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22290 | Highbury TS M11 ID19570-DX RE Sunningdale 1 | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000199 |  | AIP000199 | Yes | AIP000199 | Large Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22293 | KGHM Ltd - Victoria Mine Connection | N.T.C.2.11 | 7700 | 203 | PROJECT DELIVERY | AIP000790 | AIP000790 | AIP000790 | No | AIP000790 | KGHM Ltd - Victoria Mine Connection | 0 |  | Load Customer Connection | Robert.Reinmuller@HydroOne.com | Raj.Ghai@HydroOne.com | System Access | Northern | Not Required | 01 - Agreement (current/future) | Not Required | Project | ACTN EMPP | Executing | Executing |  | 469839.8108 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1219279.8108 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1.1102e-10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -749440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43028 | [13 empty] | FALSE |  | 0 | 0 | Alternative 1
22295 | PMR Base Station Alarm System | N.T.C.1.25 | 7700 | 203 | PROJECT DELIVERY | AIP000657 |  | AIP000657 | Yes | AIP000657 |  |  |  | Auxiliary Telecommunication Equipment | Miroslav.Kostic@HydroOne.com | [6 empty] | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22296 | Sunnidale Properties deck and pool removal | N.T.C.1.28 | 7236 | 215 | FACILITIES & REAL ESTATE | AIP000664 |  | AIP000664 | Yes | AIP000664 |  |  |  | Transmission Site Facilities | cindy.copp@hydroone.com | [6 empty] | Program | AWRD EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22297 | Tx Stations Security Upgrades | N.T.C.1.80 | 7700 | 203 | PROJECT DELIVERY | AIP000691 | AIP000691 | AIP000691 | No | AIP000691 | Tx Stations Security Upgrades - Carryover Work | 0 |  | Security Infrastructure | James.Mardegan@HydroOne.com | mark.truchanowicz@hydroone.com | General Plant | 0 | 0 | 03 - None (default) | 0 | Program | ACCP EMPP | Executing | Short Term Planning | # of Stations | 1988748.3577 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1988748.3577 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Carryover Work
22298 | Wiltshire TS - Tx Station Re-investment Project | N.T.C.1.08 | 7700 | 203 | PROJECT DELIVERY | AIP000452 |  | AIP000452 | Yes | AIP000452 |  |  |  | System Re-investment | James.Mardegan@HydroOne.com | [6 empty] | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22301 | Campbellford Area Study Implementation | N.D.C.2.02 | 7374 | 205 | LINES | AIP000183A |  | AIP000183 | Yes | AIP000183 | (1) System upgrade driven by load growth |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Michael.Medeiros@HydroOne.com | System Service | 0 | 0 | 03 - None (default) | Not Required | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22302 | Carleton Place Supply Improvements | N.D.C.2.02 | 7374 | 205 | LINES | AIP005280 | AIP005280 | AIP005280 | No | AIP005280 | Carleton Place Supply Improvements |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Muhammad.Sabir@HydroOne.com | System Service | 0 | 0 | 03 - None (default) | 0 | Project | EMPP ACTN | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42582 | 42978 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
22304 | Bobcaygeon Area Study Implementation | N.D.C.2.02 | 7374 | 205 | LINES | AIP000183A |  | AIP000183 | Yes | AIP000183 | (1) System upgrade driven by load growth |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Michael.Medeiros@HydroOne.com | System Service | 0 | 0 | 03 - None (default) | Not Required | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22310 | Rockland DS T2 | N.D.C.2.02 | 7700 | 203 | PROJECT DELIVERY | AIP005652 | AIP005652 | AIP005652 | No | AIP005652 | Rockland DS T2 | ISD-SS-02 | System Upgrades Driven by Load Growth | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Muhammad.Sabir@HydroOne.com | System Service | Eastern | 0 | 03 - None (default) | 0 | Project | DETL init | Short Term Planning | Short Term Planning |  | 0 | 2335824.2164 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2654345.7004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -318521.484 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43101 | 43768 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
22312 | Morrisburg TS 18M24 Reconductor | N.D.C.2.02 | 7374 | 205 | LINES | AIP000183A |  | AIP000183 | Yes | AIP000183 | (1) System upgrade driven by load growth |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Michael.Medeiros@HydroOne.com | System Service | 0 | 0 | 03 - None (default) | Not Required | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22314 | Strathroy TS-M1-ID 17760-Dx-Napier Wind Farm | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000199 |  | AIP000199 | Yes | AIP000199 | Large Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22316 | Orleans TS Feeder Egress & Revenue Meter | N.D.C.2.02 | 7374 | 205 | LINES | AIP005406 |  | AIP005406 | Yes | AIP005406 |  |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | [6 empty] | Project | EMPP ACTN | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22317 | Shannonville DS SSI | N.D.C.2.02 | 7374 | 205 | LINES | AIP000183A |  | AIP000183 | Yes | AIP000183 | (1) System upgrade driven by load growth |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Michael.Medeiros@HydroOne.com | System Service | 0 | 0 | 03 - None (default) | Not Required | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22318 | Hanover TS - T3 Transformer Replacement Program | N.T.C.1.17 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Power Transformers | James.Mardegan@HydroOne.com | [6 empty] | Program | INFD EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22319 | OverBrook TS, EOL Transformer Asset Replacement | N.T.C.1.08 | 7700 | 203 | PROJECT DELIVERY | AIP000433 | AIP000433 | AIP000433 | No | AIP000433 | Overbrook T2/T3 Station Refurbishment | 0 |  | System Re-investment | James.Mardegan@HydroOne.com | Fred.Kouhdani@HydroOne.com | System Renewal | Eastern | Not Required | 01 - Agreement (current/future) | Required | Project | ACCP EMPP | Executing | Executing |  | 33410.9724 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35925.7768 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2514.8044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43055 | [13 empty] | FALSE |  | 0 | 0 | T2/T3 component Replacement
22320 | Wilson TS M11 ID19990 Tx 405 Lake Road | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22321 | Tilbury West HVDS F1 ID21000-Dx 37 Mill St West | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000195 |  | AIP000195 | Yes | AIP000195 | Small Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22322 | Tilbury West HVDS F1 ID21090-Dx 351 Queen Street | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000195 |  | AIP000195 | Yes | AIP000195 | Small Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22326 | CMS - Security Upgrade 2012 | N.C.C.1.50 | 7236 | 215 | FACILITIES & REAL ESTATE | UNPLND |  |  | Yes |  |  |  |  | Real Estate Facilities | cindy.copp@hydroone.com | [6 empty] | Program | AWRD EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22328 | Chenaux TS EOL Transformer Replacement project | N.T.C.1.44 | 7700 | 203 | PROJECT DELIVERY | AIP005110 | AIP005110 | AIP005110 | No | AIP005110 | Chenaux TS BULK: T3/T4 115kv Yard Replacement | SR-02 | Station Reinvestment Projects | Eastern Zone Station/Yard Investments | James.Mardegan@HydroOne.com | Fred.Kouhdani@HydroOne.com | System Renewal | Eastern | 0 | 02 - Expectation (no agreement) | 0 | Project | EMPP ACCP | Executing | Executing |  | 5822131.7857 | 5991402.9449 | 0.039313 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6260356.7588 | 6442368.758 | 0.042272 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -438224.9731 | -450965.8131 | -0.002959 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -7.0671 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43819 | [13 empty] | FALSE |  | 0 | 2 | Station Refurb/Rebuild
22329 | Espanola TS EOL Stat Reinvstmt proj | N.T.C.1.45 | 7700 | 203 | PROJECT DELIVERY | AIP000411 |  | AIP000411 | Yes | AIP000411 |  |  |  | Northern Zone Station/Yard Investments | James.Mardegan@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22331 | St. Thomas 115/27.6 (T3 & T4):Decommissioning Cost | N.T.C.2.11 | 7700 | 203 | PROJECT DELIVERY | AIP000816 |  | AIP000816 | Yes | AIP000816 |  |  |  | Load Customer Connection | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22335 | Glendale TS: T1,T3,T4 & Swyd Refurb. and Reconfig. | N.T.C.1.41 | 7700 | 203 | PROJECT DELIVERY | AIP000416 | AIP000416 | AIP000416 | No | AIP000416 | Glendale TS: T1, T3, T4 & Switchyard Refurbishment and Reconfiguration | SR-02 | Station Reinvestment Projects | Hamilton/Niagara Zone Station/Yard Investments | James.Mardegan@HydroOne.com | mark.truchanowicz@hydroone.com | System Renewal | Hamilton Niagara | Not Required | 02 - Expectation (no agreement) | 0 | Project | ACTN BEST | Short Term Planning | Short Term Planning |  | 0 | 0 | 823166.4767 | 6674571.8045 | 10577672.9162 | 5796585.0487 | 0 | 0 | 0 | 0 | 0 | 0 | 885125.2438 | 7176958.9296 | 11373841.8454 | 6232887.1491 | 0 | 0 | 0 | 0 | 0 | 0 | -61958.7671 | -502387.1251 | -796168.9292 | -436302.1004 | 0 | 0 | 0 | 0 | -7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44104 | 45260 | False |  | False |  | False |  | False | True | Customer (Alectra) was consulted on final station configuration to meet customer needs | False | False | False | False | FALSE |  | 0 | 2 | Switchyard Refurbishment and Reconfiguration (Modified)
22336 | Stanley TS Station Upgrade | N.T.C.1.41 | 7700 | 203 | PROJECT DELIVERY | AIP005140 |  | AIP005140 | Yes | AIP005140 |  |  |  | Hamilton/Niagara Zone Station/Yard Investments | James.Mardegan@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22337 | Business Unit for Enterprise Content Management | N.C.C.2.60 | 4339 | 212 | INFO SOLUTIONS DIVISION | AIP000063 |  | AIP000063 | Yes | AIP000063 |  |  |  | IT Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22345 | Dobbin TS: Component Replacement | N.T.C.1.44 | 7700 | 203 | PROJECT DELIVERY | AIP000401 |  | AIP000401 | Yes | AIP000401 |  |  |  | Eastern Zone Station/Yard Investments | James.Mardegan@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22351 | Mississagi TS - Add Goulais Wind to GR Scheme | N.T.C.2.12 | 7700 | 203 | PROJECT DELIVERY | AIP000886 |  | AIP000886 | Yes | AIP000886 |  |  |  | Generator Customer Connection | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22354 | Orangeville TS M3 - Mayfield West | N.D.C.2.02 | 7374 | 205 | LINES | AIP005436 | AIP005436 | AIP005436 | No | AIP005436 | Orangeville TS M3 - Mayfield West | ISD-SS-02 | System Upgrades Driven by Load Growth | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Mark.VanTol@hydroone.com | System Service | Central | 0 | 03 - None (default) | 0 | Project | ACTN DETL | Short Term Planning | Short Term Planning |  | 1849494.812 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2101698.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -252203.838 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43132 | 43405 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
22355 | Dryden TS - Install Shunt Reactors | N.T.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000724 |  | AIP000724 | Yes | AIP000724 |  |  |  | Network Transfer Capability | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22357 | Ballantrae DS load balancing | N.D.C.2.02 | 7374 | 205 | LINES | UNPLND |  |  | Yes |  |  |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | [6 empty] | Project | EMPP ACTN | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22360 | Lindsay TS D4M7 Upgrade | N.D.C.2.02 | 7374 | 205 | LINES | AIP000183A |  | AIP000183 | Yes | AIP000183 | (1) System upgrade driven by load growth |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Michael.Medeiros@HydroOne.com | System Service | 0 | 0 | 03 - None (default) | Not Required | Project | DETL ACTN | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22361 | Neustadt DS F2 ID18530-Dx Normanby Solar 5 | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000195 |  | AIP000195 | Yes | AIP000195 | Small Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22362 | Nebo TS feeder - demand enhancement | N.D.C.2.02 | 7374 | 205 | LINES | UNPLND |  |  | Yes |  |  |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | [6 empty] | Project | EMPP ACTN | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22364 | Neustadt DS F2 ID18540-Dx Normanby Solar 2 | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000195 |  | AIP000195 | Yes | AIP000195 | Small Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22367 | Nebo TS feeder extension to Binbrook - phase 1 | N.D.C.2.02 | 7374 | 205 | LINES | AIP000185 |  | AIP000185 | Yes | AIP000185 | (3) Reliability Improvements | ISD-SS-03 | Reliability Improvements | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Michael.Medeiros@HydroOne.com | System Service | 0 | 0 | 03 - None (default) | 0 | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22368 | Nebo TS M12 feeder extension to Hamilton Airport | N.D.C.2.02 | 7374 | 205 | LINES | UNPLND |  |  | Yes |  |  |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | [6 empty] | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22370 | TEM Logical Data Validation | N.T.M.1.24 | 4048 | 213 | PLANNING | UNPLND |  |  | Yes |  |  |  |  | Leased Facilities | Miroslav.Kostic@HydroOne.com | [6 empty] | Project | EMPP AWRD | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22380 | Nobleton DS T1-new 27.6 kV transformer and feeder | N.D.C.2.02 | 7700 | 203 | PROJECT DELIVERY | AIP005267 | AIP005267 | AIP005267 | No | AIP005267 | Nobleton DS T1 - New Transformer & Line Work |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Dhaval.Patel@hydroone.com | System Service | Central | 0 | 03 - None (default) | 0 | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41988 | 42916 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
22381 | Tenth Line DS T3 | N.D.C.2.02 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22384 | Bradford North DS | N.D.C.2.02 | 7700 | 203 | PROJECT DELIVERY | AIP005836 | AIP005836 | AIP005836 | No | AIP005836 | Bradford North DS | ISD-SS-02 | System Upgrades Driven by Load Growth | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Mark.VanTol@hydroone.com | System Service | Central | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 250202.2202 | 4754201.468 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250202.2202 | 4754201.468 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43435 | 43784 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
22386 | Enfield TS feeder development | N.D.C.2.02 | 7374 | 205 | LINES | UNPLND |  |  | Yes |  |  |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22391 | Telecom Perf Upgrade - Bruce A-B | N.T.C.3.08 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Integrating Operating Infrastructure | Miroslav.Kostic@HydroOne.com | [6 empty] | Project | init DETL | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22397 | Orillia TS M1 ID20150-TX 555 Memorial Ave | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22400 | Strathroy Septic Rehab 2012 | N.D.C.1.50 | 7236 | 215 | FACILITIES & REAL ESTATE | UNPLND |  |  | Yes |  |  |  |  | Real Estate Facilities | cindy.copp@hydroone.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22401 | Clinton Concrete Column Rahab 2012 | N.D.C.1.50 | 7236 | 215 | FACILITIES & REAL ESTATE | UNPLND |  |  | Yes |  |  |  |  | Real Estate Facilities | cindy.copp@hydroone.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22402 | Vankleek Hill OC Security Upgrade 2012 | N.D.C.1.50 | 7236 | 215 | FACILITIES & REAL ESTATE | UNPLND |  |  | Yes |  |  |  |  | Real Estate Facilities | cindy.copp@hydroone.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22403 | Thunder Bay OC (205) Security Upgrade 2012 | N.C.C.1.50 | 7236 | 215 | FACILITIES & REAL ESTATE | AIP000027 |  | AIP000027 | Yes | AIP000027 | Facility Accommodation & Improvements Service Centres & Admin |  |  | Real Estate Facilities | cindy.copp@hydroone.com | Peter.Erdman@HydroOne.com | General Plant | 0 | 0 | 03 - None (default) | 0 | Program | EMPP AWRD | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22405 | Kingston OC Security Upgrade 2012 | N.C.C.1.50 | 7236 | 215 | FACILITIES & REAL ESTATE | UNPLND |  |  | Yes |  |  |  |  | Real Estate Facilities | cindy.copp@hydroone.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22406 | Essex OC Security Upgrade 2012 | N.D.C.1.50 | 7236 | 215 | FACILITIES & REAL ESTATE | UNPLND |  |  | Yes |  |  |  |  | Real Estate Facilities | cindy.copp@hydroone.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22407 | Brockville OC Security Upgrade 2012 | N.D.C.1.50 | 7236 | 215 | FACILITIES & REAL ESTATE | UNPLND |  |  | Yes |  |  |  |  | Real Estate Facilities | cindy.copp@hydroone.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22408 | Thunder Bay OC (255) Security Upgrade 2012 | N.C.C.1.50 | 7236 | 215 | FACILITIES & REAL ESTATE | AIP000027 |  | AIP000027 | Yes | AIP000027 | Facility Accommodation & Improvements Service Centres & Admin |  |  | Real Estate Facilities | cindy.copp@hydroone.com | Peter.Erdman@HydroOne.com | General Plant | 0 | 0 | 03 - None (default) | 0 | Program | AWRD EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22416 | Burlington Beach Line Relocation - Recoverable | N.T.C.1.14 | 7700 | 203 | PROJECT DELIVERY | AIP000481 | AIP000481 | AIP000481 | No | AIP000481 | Burlington Beach Line Relocation - Recoverable | 0 |  | Third Party Transmission System Modifications | john.boldt@HydroOne.com | Gian.Minichini@HydroOne.com | System Renewal | Hamilton Niagara | 0 | 01 - Agreement (current/future) | 0 | Project | EXTR | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 150000 | 10000000 | 11700000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -150000 | -150000 | -10000000 | -11700000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43763 | 44545 | True | City of Burlington asked HONI to relocate sections of B18H/B20H and B10/B11 to accommodate their beach revitilization project | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Burlington Beach Line Relocation - Recoverable
22418 | Nanticoke TS - Station Service Upgrade / Demerger | N.T.M.1.14 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Engineering and Environmental Support | Mike.Tanaskovic@HydroOne.com | [6 empty] | Program | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22420 | Strathroy TS – EOL Station Refurbishment | N.T.C.1.08 | 7700 | 203 | PROJECT DELIVERY | AIP000445 | AIP000445 | AIP000445 | No | AIP000445 | Strathroy TS T1/T2; T1, PCT & Component Replacement | 0 |  | System Re-investment | James.Mardegan@HydroOne.com | mark.truchanowicz@hydroone.com | System Renewal | Western | Not Required | 03 - None (default) | Not Required | Project | ACTN EMPP | Executing | Executing |  | 394209.6995 | 0 | 0.019656 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 423881.3973 | 0 | 0.021136 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -29671.6978 | 0 | -0.0014795 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -22.4855 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43077 | [13 empty] | FALSE |  | 0 | 0 | Alternative 1
22421 | P1P Superior Fine Papers Removals-Non-Recoverable | N.T.C.1.14 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Third Party Transmission System Modifications | john.boldt@HydroOne.com | [6 empty] | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22422 | Ottawa - 800 Hunt Club Road_Recoverable | N.T.C.1.14 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Third Party Transmission System Modifications | john.boldt@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22426 | Storage Acquisition Project | N.C.M.2.70 | 4330 | 212 | INFO SOLUTIONS DIVISION | UNPLND |  |  | Yes |  |  |  |  | IT - Project & Architecture Services | lincoln.frost-hunt@hydroone.com | [6 empty] | Project | EMPP init | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22436 | Claireville 750 MVA Autotranf Replacement - T15 | N.T.C.1.17 | 7700 | 203 | PROJECT DELIVERY | AIP000552 |  | AIP000552 | Yes | AIP000552 |  |  |  | Power Transformers | James.Mardegan@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22446 | Dx - Engineering Standards | N.D.M.2.20 | 7716 | 224 | ENGINEERING | AIP000311 | AIP000311 | AIP000311 | No | AIP000311 | Dx - Engineering Standards |  |  | Standards Program | Kevin.Mancherjee@HydroOne.com | rossella.fazio@hydroone.com | System O&M | N/A | 0 | 03 - None (default) | 0 | Program | ACCP EMPP | Executing | Short Term Planning | Assumption - # of Standards | 216260.8918 | 187506.7196 | 193485.392 | 159781.1186 | 164353.7813 | 0 | 0 | 0 | 0 | 0 | 216260.8918 | 187506.7196 | 193485.392 | 159781.1186 | 164353.7813 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 5 | 5 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Vulnerable
22448 | Tx - Engineering Standards | N.T.M.2.20 | 7716 | 224 | ENGINEERING | AIP001159 | AIP001159 | AIP001159 | No | AIP001159 | Tx - Engineering Standards | 0 |  | Standards Program | Kevin.Mancherjee@HydroOne.com | rossella.fazio@hydroone.com | System O&M | N/A | 0 | 03 - None (default) | 0 | Program | ACCP EMPP | Executing | Short Term Planning | Assumption - # of Standards | 1750184.0605 | 2193887.1732 | 1868198.8359 | 2340515.6018 | 2411617.9153 | 2484732.4545 | 0 | 0 | 0 | 0 | 1750184.0605 | 2193887.1732 | 1868198.8359 | 2340515.6018 | 2411617.9153 | 2484732.4545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49 | 60 | 49 | 60 | 60 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Vulnerable
22450 | Tillsonburg TS-M2-HVTT and line back up protection | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22451 | Brant TS M12 ID20070-TX Ferrero Canada Quattro-Gen | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22453 | To be Closed- CMS Station Service & Yard Supply | N.T.C.1.20 | 7700 | 203 | PROJECT DELIVERY | AIP000616 |  | AIP000616 | Yes | AIP000616 |  |  |  | Ancillary Systems | James.Mardegan@HydroOne.com | [6 empty] | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22457 | Strathroy TS-M3-ID 21170-Dx -RE Adelaide 1 ULC | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000199 |  | AIP000199 | Yes | AIP000199 | Large Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22458 | Strathroy TS-M3-ID 21170-Tx-RE Adelaide 1 ULC | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22461 | Douglas Point TS-M6-ID20530-Quixote One WE-Dx | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000199 |  | AIP000199 | Yes | AIP000199 | Large Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22462 | Douglas Point TS-M6-ID20530-Quixote One WE -Tx | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22467 | Cornerstone Phase 3 - EDT CAP | N.C.C.2.10 | 7193 | 227 | CORNERSTONE | UNPLND |  |  | Yes | [12 empty] | Project | EMPP init | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22480 | RichviewTS T1/T2; T1,T2,PCT &Component Replacement | N.T.C.1.43 | 7700 | 203 | PROJECT DELIVERY | AIP005210 | AIP005210 | AIP005210 | No | AIP005210 | Richview TS T1/T2; T1, T2, PCT & Component Replacement | 0 |  | Greater Toronto Area Zone Station/Yard Investments | James.Mardegan@HydroOne.com | michael.xavier@hydroone.com | System Renewal | Greater Toronto Area | 0 | 03 - None (default) | 0 | Project | ACTN EMPP | Executing | Executing |  | 1652069.1707 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1776418.4632 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -124349.2924 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1.4824 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43280 | [13 empty] | FALSE |  | 0 | 0 | Component Replacement
22481 | CrowlandTS, T5&T6 - Replace EOL Transformers | N.T.C.1.17 | 7700 | 203 | PROJECT DELIVERY | AIP000560 |  | AIP000560 | Yes | AIP000560 | Replace EOL Large Transformers Program |  |  | Power Transformers | James.Mardegan@HydroOne.com | peter.zhao@hydroone.com | System Renewal | 0 | 0 | 03 - None (default) | 0 | Program | init BEST | Short Term Planning | Short Term Planning | # of Transformers | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22487 | Markham OC Security Improvments 2012 | N.D.C.1.50 | 7236 | 215 | FACILITIES & REAL ESTATE | AIP000027 |  | AIP000027 | Yes | AIP000027 | Facility Accommodation & Improvements Service Centres & Admin |  |  | Real Estate Facilities | cindy.copp@hydroone.com | Peter.Erdman@HydroOne.com | General Plant | 0 | 0 | 03 - None (default) | 0 | Program | AWRD EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22488 | Oro SC Drainage 2013 | N.C.C.1.50 | 7236 | 215 | FACILITIES & REAL ESTATE | UNPLND |  |  | Yes |  |  |  |  | Real Estate Facilities | cindy.copp@hydroone.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22492 | Orangeville OC Elevator Lift | N.C.C.1.50 | 7236 | 215 | FACILITIES & REAL ESTATE | UNPLND |  |  | Yes |  |  |  |  | Real Estate Facilities | cindy.copp@hydroone.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22493 | Lindsay TS M7 ID20780 Dx Balsam Lake Green Energy | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000199 |  | AIP000199 | Yes | AIP000199 | Large Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22494 | Lindsay TS M7 ID20780 Tx Balsam Lake Green Energy | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22496 | Mississaugi TS - Add Bow Lake Wind to GR Scheme | N.T.C.2.12 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Generator Customer Connection | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22502 | Lambton TS - New Feeder to Terra Nitrogen | N.D.C.2.02 | 7374 | 205 | LINES | UNPLND |  |  | Yes |  |  |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22505 | Smith Falls Roadway Site Drainage | N.T.C.1.28 | 7236 | 215 | FACILITIES & REAL ESTATE | UNPLND |  |  | Yes |  |  |  |  | Transmission Site Facilities | cindy.copp@hydroone.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22507 | Vale - Victor Deep Mine Connection | N.T.C.2.11 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Load Customer Connection | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | #N/A | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22511 | Hearing Conservation Program | N.C.M.3.03 | 7054 | 209 | HEALTH, SAFETY & ENV | AIP000118C | AIP000118 | AIP000118 | No | AIP000118 | Health & Rehab Services | 0 |  | Environment Health and Safety | welchw@hydroone.com | welchw@hydroone.com | System O&M | N/A | 0 | 03 - None (default) | 0 | Program | AWRD | Short Term Planning | Short Term Planning | Retainer | 135827.34 | 166403.76 | 142328.73 | 174140.5 | 149093.01 | 180000 | 0 | 0 | 0 | 0 | 135827.34 | 166403.76 | 142328.73 | 174140.5 | 149093.01 | 180000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | True | Care Management - Contracted service for 3rd party to manage all Hydro One's major medical absences to ensure that employees receive timely treatment, the absences are warranted and employees return to work in a timely manner. | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Optimal - (Modified-Tx Decision)
22517 | Whitby - O1S - Idle Line Removal - Recoverable | N.T.C.1.14 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Third Party Transmission System Modifications | john.boldt@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22518 | Ottawa - McRae Structure Replacement - Recoverable | N.T.C.1.14 | 7700 | 203 | PROJECT DELIVERY | AIP000507 |  | AIP000507 | Yes | AIP000507 |  |  |  | Third Party Transmission System Modifications | john.boldt@HydroOne.com | [6 empty] | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22530 | Cameron DS Improvements | N.D.C.2.02 | 7374 | 205 | LINES | AIP005276 | AIP005276 | AIP005276 | No | AIP005276 | Cameron DS Improvements | ISD-SS-02 | System Upgrades Driven by Load Growth | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Dhaval.Patel@hydroone.com | System Service | Eastern | 0 | 03 - None (default) | 0 | Project | ACTN DETL | Short Term Planning | Short Term Planning |  | 1147714.2739 | 203635.9708 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1304220.7658 | 231404.5123 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -156506.4919 | -27768.5415 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42975 | 43493 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
22531 | Colborne DS Relief | N.D.C.2.02 | 7374 | 205 | LINES | AIP005277 |  | AIP005277 | Yes | AIP005277 |  |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | [6 empty] | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22543 | Duart TS - M5 - Tx - DG 487 Distance Limitation | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000928 |  | AIP000928 | Yes | AIP000928 |  |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | [6 empty] | Project | EMPP ACTN | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22544 | Colpoys Bay DS F2 Feeder Upgrade | N.D.C.2.02 | 7374 | 205 | LINES | AIP000183A |  | AIP000183 | Yes | AIP000183 | (1) System upgrade driven by load growth |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Michael.Medeiros@HydroOne.com | System Service | 0 | 0 | 03 - None (default) | Not Required | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22545 | Kingsville TS-M7-ID20300-200 Clark St -Tx | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22547 | Kingsville TS M5 ID21520 - TX - Wigle Ave Solar | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22548 | Creemore DS - New Feeder to Collus | N.D.C.2.02 | 7374 | 205 | LINES | AIP005230 |  | AIP005230 | Yes | AIP005230 |  |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | [6 empty] | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22550 | Kingsville TS M5 ID21110 Tx - Kingvsille Plastic 2 | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22552 | MicroGrids Impact/Integration | N.D.M.2.22 | 4230 | 213 | PLANNING | AIP000329 |  | AIP000329 | Yes | AIP000329 | [11 empty] | Program | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22553 | Nebo TS feeder extension to Binbrook - phase 2 | N.D.C.2.02 | 7374 | 205 | LINES | AIP005645 | AIP005645 | AIP005645 | No | AIP005645 | Nebo TS Feeder Extension to Binbrook - Phase 2 | ISD-SS-03 | Reliability Improvements | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Mark.VanTol@hydroone.com | System Service | Hamilton Niagara | 0 | 03 - None (default) | 0 | Project | DETL ACTN | Short Term Planning | Short Term Planning |  | 27515.5588 | 1001095.8263 | 1814531.9459 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31267.6805 | 1137608.8935 | 2061968.1204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3752.1217 | -136513.0672 | -247436.1744 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43677 | 44134 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
22560 | R&D Program- Kinectrics | N.T.M.2.21 | 4230 | 213 | PLANNING | AIP001169 |  | AIP001169 | Yes | AIP001169 |  |  |  | Technology Program | Daila.Dzintars@HydroOne.com | [6 empty] | Program | AWRD EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22566 | Mattawa Voltage Conversion | N.D.C.2.02 | 7374 | 205 | LINES | AIP005246 |  | AIP005246 | Yes | AIP005246 |  |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | [6 empty] | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22567 | Tillsonburg TS-M2-Dx work_DG 281 and 282 | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Distribution Generation Connection | ryan.boudreau@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22575 | Middleport TS septic system rehab 2013 | N.T.C.1.28 | 7236 | 215 | FACILITIES & REAL ESTATE | UNPLND |  |  | Yes |  |  |  |  | Transmission Site Facilities | cindy.copp@hydroone.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22576 | Orangeville OC Garage apron & drain rehab 2013 | N.C.C.1.50 | 7236 | 215 | FACILITIES & REAL ESTATE | UNPLND |  |  | Yes |  |  |  |  | Real Estate Facilities | cindy.copp@hydroone.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22577 | Air to Gas Bushing Replacement Program | N.T.M.1.16 | 7370 | 206 | TX LINES AND STATIONS | AIP001043 | AIP001043 | AIP001043 | No | AIP001043 | Air to Gas Bushing Replacement Program | 0 |  | Power Equipment | Mike.Tanaskovic@HydroOne.com | andrea.Lemhenyi@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | ACTN EMPP | Executing | Short Term Planning | # of bushings | 501708.1879 | 664643.8883 | 920560.6702 | 638307.0124 | 658253.4212 | 963150.8554 | 0 | 0 | 0 | 0 | 501708.1879 | 664643.8883 | 920560.6702 | 638307.0124 | 658253.4212 | 963150.8554 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 6 | 9 | 6 | 6 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Intermediate (Modified - Tx Decision)
22579 | Operating Power Systems IT Support | N.C.M.3.01 | 4032 | 212 | INFO SOLUTIONS DIVISION | AIP000116 | AIP000116 | AIP000116 | No | AIP000116 | Operating Power Systems IT Support | 0 |  | Common Operating Infrastructure | Godfrey.Holder@HydroOne.com | mallen@hydroone.com | System O&M | N/A | 0 | 03 - None (default) | 0 | Program | init BEST | Short Term Planning | Short Term Planning | Retainer | 18600000.28 | 19140000.44 | 20829999.44 | 21799999.56 | 20456853.12 | 20740000.12 | 0 | 0 | 0 | 0 | 18600000.28 | 19140000.44 | 20829999.44 | 21799999.56 | 20456853.12 | 20740000.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | True | NERC CIP: Security Patches | True |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Asset Optimal - Modified - Tx Constraint Reduction
22582 | Station Battery Monitoring Systems | N.T.C.3.08 | 7700 | 203 | PROJECT DELIVERY | AIP000996 | AIP000996 | AIP000996 | No | AIP000996 | Station Battery Monitoring Systems | 0 |  | Integrating Operating Infrastructure | Miroslav.Kostic@HydroOne.com | alan.wong@hydroone.com | General Plant | N/A | 0 | 03 - None (default) | 0 | Program | init | Short Term Planning | Short Term Planning | # sites | 1393757.637 | 1436758.4604 | 1453362.9073 | 1464620.1314 | 1475748.9674 | 1463538.8145 | 0 | 0 | 0 | 0 | 1393757.637 | 1436758.4604 | 1453362.9073 | 1464620.1314 | 1475748.9674 | 1463538.8145 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 15 | 15 | 15 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | True | PRC standard for Battery Testing | False |  | False | False |  | False | True | False | True | FALSE |  | 0 | 0 | Asset Optimal
22583 | Internal Compliance Plan | N.T.M.1.29 | 4230 | 213 | PLANNING | AIP001147 |  | AIP001147 | Yes | AIP001147 |  |  |  | NERC Cyber Security Compliance Readiness | lincoln.frost-hunt@hydroone.com | [6 empty] | Program | init EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22587 | Thunder Bay OC Fence Replacement 2013 | N.C.C.1.50 | 7236 | 215 | FACILITIES & REAL ESTATE | UNPLND |  |  | Yes |  |  |  |  | Real Estate Facilities | cindy.copp@hydroone.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22588 | Lambton OC Fence Replacement 2013 | N.D.C.1.50 | 7236 | 215 | FACILITIES & REAL ESTATE | UNPLND |  |  | Yes |  |  |  |  | Real Estate Facilities | cindy.copp@hydroone.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22589 | Integrated Voice Comm & Telephony Sys Replacement | N.C.C.3.01 | 4514 | 212 | INFO SOLUTIONS DIVISION | AIP000079 |  | AIP000079 | Yes | AIP000079 |  |  |  | Common Oper Infrast & Control Facilities | Godfrey.Holder@HydroOne.com | [6 empty] | Project | BEST EMPP AWRD | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22592 | CGE type SBM CSS Replacement Program | N.T.M.1.16 | 7370 | 206 | TX LINES AND STATIONS | AIP001046 | AIP001046 | AIP001046 | No | AIP001046 | CSS Replacement Program | 0 |  | Power Equipment | Mike.Tanaskovic@HydroOne.com | kristoffer.hammel@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | EMPP ACTN | Executing | Short Term Planning | # of breakers | 103908.6717 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 103908.6717 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Asset Optimal
22593 | Phone Enhancements Project (Dx) | N.D.C.3.08 | 4514 | 212 | INFO SOLUTIONS DIVISION | 3783 |  |  | Yes |  |  |  |  | Operating Infrastructure | Godfrey.Holder@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22594 | CMS - Railway siding acquisition 2012 | N.C.C.1.50 | 7236 | 215 | FACILITIES & REAL ESTATE | AIP000027 |  | AIP000027 | Yes | AIP000027 | Facility Accommodation & Improvements Service Centres & Admin |  |  | Real Estate Facilities | cindy.copp@hydroone.com | Peter.Erdman@HydroOne.com | General Plant | 0 | 0 | 03 - None (default) | 0 | Program | AWRD EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22596 | Douglas Point TS-M1-ID20940-Dx-Meyer Wind Farm | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000199 |  | AIP000199 | Yes | AIP000199 | Large Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22597 | Douglas Point TS-M1-ID20940-Tx-Meyer Wind Farm | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22598 | CEATI-Tx Annual Program | N.T.M.2.21 | 4230 | 213 | PLANNING | AIP001166 |  | AIP001166 | Yes | AIP001166 |  |  |  | Technology Program | Daila.Dzintars@HydroOne.com | [6 empty] | Program | init EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22600 | Lennox TS 500kV Bus -Connect Napanee GS | N.T.C.2.12 | 7700 | 203 | PROJECT DELIVERY | AIP000882 | AIP000882 | AIP000882 | No | AIP000882 | Napanee Gas Generation Connection | 0 |  | Generator Customer Connection | Robert.Reinmuller@HydroOne.com | Quyen.Diep@HydroOne.com | System Access | Eastern | Not Required | 01 - Agreement (current/future) | Not Required | Project | EMPP ACTN | Executing | Executing |  | 49718.7089 | 0 | 0.0098282 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51958.7089 | 0 | 0.0098282 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43076 | [13 empty] | FALSE |  | 0 | 0 | Alternative 1
22609 | Minden Trailer - Bldg 2012 | N.D.C.1.50 | 7236 | 215 | FACILITIES & REAL ESTATE | UNPLND |  |  | Yes |  |  |  |  | Real Estate Facilities | cindy.copp@hydroone.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22610 | Voice Communications System Support & Mtce | N.C.M.3.01 | 4032 | 212 | INFO SOLUTIONS DIVISION | AIP000115 | AIP000115 | AIP000115 | No | AIP000115 | Integrated Voice System Support | 0 |  | Common Operating Infrastructure | Godfrey.Holder@HydroOne.com | emily.booth@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | AWRD EMPP | Executing | Short Term Planning | Retainer | 1043461.96 | 851465 | 868494.32 | 885864.2 | 903581.48 | 922103.96 | 0 | 0 | 0 | 0 | 1043461.96 | 851465 | 868494.32 | 885864.2 | 903581.48 | 922103.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | True | NERC CIP regarding security patch updates. | True | Support agreement with Longview, the system integrator. | False | False |  | False | True | False | False | FALSE |  | 0 | 0 | Asset Optimal
22615 | Red Rock HVDS F3 ID20990 Dx-Black Bay Solar | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000199 |  | AIP000199 | Yes | AIP000199 | Large Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22616 | Red Rock HVDS F3 ID20990 Tx-Black Bay Solar | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22621 | Furniture Systems - Facilities (Field) | N.C.C.1.55 | 7236 | 215 | FACILITIES & REAL ESTATE | AIP000029 | AIP000029 | AIP000029 | No | AIP000029 | Facilities & Real Estate MFA | GP-11 | Facility Accommodation & Improvements Service Centres & Admin | MFA - Real Estate Facilities | cindy.copp@hydroone.com | Peter.Erdman@HydroOne.com | General Plant | 0 | 0 | 03 - None (default) | 0 | Program | AWRD EMPP | Executing | Short Term Planning | Retainer | 1600000 | 1593156.3784 | 1579140.2253 | 1559896.2533 | 1540495.4007 | 1526951.1654 | 0 | 0 | 0 | 0 | 1600000 | 1593156.3784 | 1579140.2253 | 1559896.2533 | 1540495.4007 | 1526951.1654 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal (Challenge Session)
22622 | Head Office Improvements Furniture | N.C.C.1.55 | 7236 | 215 | FACILITIES & REAL ESTATE | AIP000029B |  | AIP000029 | Yes | AIP000029 | Facilities & Real Estate MFA |  |  | MFA - Real Estate Facilities | cindy.copp@hydroone.com | Peter.Erdman@HydroOne.com | General Plant | 0 | 0 | 03 - None (default) | 0 | Program | EMPP AWRD | Executing | Short Term Planning | Retainer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22623 | Cornerstone Phase 3 - AIP PH2 | N.C.C.2.10 | 7193 | 227 | CORNERSTONE | UNPLND |  |  | Yes | [12 empty] | Project | init EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22624 | Cornerstone Phase 3 - HR/Pay Enhancements | N.C.C.2.10 | 7193 | 227 | CORNERSTONE | AIP000054 |  | AIP000054 | Yes | AIP000054 | [11 empty] | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22626 | S&E Contractor Pre-Qualification Process | N.C.M.3.03 | 7054 | 209 | HEALTH, SAFETY & ENV | AIP000123 | AIP000123 | AIP000123 | No | AIP000123 | S&E Contractor Pre-Qualification Process | 0 |  | Environment Health and Safety | welchw@hydroone.com | welchw@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | init EMPP | Executing | Short Term Planning | Retainer | 19311.48 | 19697.64 | 20091.6 | 20493.48 | 20903.28 | 21321.36 | 0 | 0 | 0 | 0 | 19311.48 | 19697.64 | 20091.6 | 20493.48 | 20903.28 | 21321.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | True | Contracted service with ISNetworld to carry out contractor HSE prequalifications for contractors that work for Hydro One. This investment covers Hydro One's annual fee requirement. | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Optimum
22627 | P&C Distribution Support | N.D.M.1.17 | 7716 | 224 | ENGINEERING | AIP000283 | AIP000283 | AIP000283 | No | AIP000283 | P&C Distribution Support |  |  | Protection, Control and Telecom Maintenance | joseph.parete@hydroone.com | warren.tingle@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | ACTN EMPP | Executing | Short Term Planning | Retainer | 262183.8494 | 270140.3339 | 276047.2574 | 282185.4393 | 287395.023 | 0 | 0 | 0 | 0 | 0 | 262183.8494 | 270140.3339 | 276047.2574 | 282185.4393 | 287395.023 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
22629 | Operating Facilities Refresh | N.C.C.3.01 | 4514 | 212 | INFO SOLUTIONS DIVISION | AIP000077 | AIP000077 | AIP000077 | No | AIP000077 | Operating Facilities Sustainment | 0 |  | Common Oper Infrast & Control Facilities | Godfrey.Holder@HydroOne.com | mallen@hydroone.com | General Plant | 0 | Not Required | 03 - None (default) | Not Required | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 1780019.3418 | 1072428.7545 | 481404.8512 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1780019.3418 | 1072428.7545 | 481404.8512 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43885 | 44834 | False |  | True | NERC CIP Security Patches | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Asset Optimal
22630 | MFA for Development Project | N.C.C.1.75 | 4342 | 212 | INFO SOLUTIONS DIVISION | AIP000047 |  | AIP000047 | Yes | AIP000047 |  |  |  | IT - MFA | lincoln.frost-hunt@hydroone.com | [6 empty] | Project | init EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22634 | Engineering Cyber Lab Sustainment | N.T.M.1.29 | 4512 | 212 | INFO SOLUTIONS DIVISION | AIP001143 | AIP001143 | AIP001143 | No | AIP001143 | Engineering Cyber Lab Sustainment | 0 |  | NERC Cyber Security Compliance Readiness | lincoln.frost-hunt@hydroone.com | Sherry.Wilging@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | init | Short Term Planning | Short Term Planning | Retainer | 193218.3231 | 198644.8024 | 199006.5688 | 199455.3477 | 199528.8538 | 199199.3851 | 0 | 0 | 0 | 0 | 193218.3231 | 198644.8024 | 199006.5688 | 199455.3477 | 199528.8538 | 199199.3851 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | True | CIP-005, 007, 010 | False |  | False | False |  | False | False | False | False | TRUE | This program provides sustainment funding for the Engineering Cyber Lab. Activiites such has purchasing new equipment and software to perform cyber testing. | 0 | 0 | Asset Optimal
22635 | E4D – Upgrade to operate at Higher Temperature | N.T.C.2.11 | 7700 | 203 | PROJECT DELIVERY | AIP000778 | AIP000778 | AIP000778 | No | AIP000778 | E4D - Upgrade to operate at Higher Temperature (Red Lake) | 0 |  | Load Customer Connection | Robert.Reinmuller@HydroOne.com | Erfan.Hajian@hydroone.com | System Access | Northern | TBD | 01 - Agreement (current/future) | Required | Project | EMPP HOLD | Executing | Executing |  | 362.9466 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1823.9466 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.421e-14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1461 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43179 | [13 empty] | FALSE |  | 0 | 0 | Alternative 1
22636 | Kingston - ABNA Tower Relocation - Recoverable | N.T.C.1.14 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Third Party Transmission System Modifications | john.boldt@HydroOne.com | [6 empty] | Project | HOLD | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22637 | ORMS Sustainment Upgrade | N.D.C.3.08 | 4514 | 212 | INFO SOLUTIONS DIVISION | AIP000223 | AIP000223 | AIP000223 | No | AIP000223 | ORMS Sustainment |  |  | Operating Infrastructure | Godfrey.Holder@HydroOne.com | Natalie.Briggs@HydroOne.com | General Plant | 0 | Not Required | 03 - None (default) | Not Required | Project | EMPP AWRD | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41988 | 42978 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
22638 | Kingsville TS M1 ID21640 Tx - Brian Curtis | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22645 | ADS Project Phase 1 Release 2- MFA | N.C.C.1.75 | 4343 | 222 | SMART GRID | AIP000043 | AIP000043 | AIP000043 | No | AIP000043 | ADS MFA | 0 |  | IT - MFA | lincoln.frost-hunt@hydroone.com | Raj.Agnihotri@HydroOne.com | General Plant | 0 | Not Required | 03 - None (default) | Not Required | Project | AWRD EMPP | Executing | Executing |  | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43462 | 42916 | False |  | False |  | False |  | False | False |  | False | False | False | False | TRUE | MFA $ required for ADS/Dx modernisation project under Smart Grid investment driver. | 0 | 0 | Alternative
22647 | Cornerstone Phase 3 - AIP PH2 OM&A | N.C.M.2.10 | 7193 | 227 | CORNERSTONE | UNPLND |  |  | Yes | [12 empty] | Project | init EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22648 | CSO Regulatory Compliance/CIS Projects | N.D.M.1.60 | 4042 | 212 | INFO SOLUTIONS DIVISION | AIP000285A | AIP000285 | AIP000285 | No | AIP000285 | ISD Customer Care |  |  | IT Business Improvements & Enhancements | lincoln.frost-hunt@hydroone.com | Wayne.Logan@HydroOne.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | EMPP AWRD | Executing | Short Term Planning | Retainer | 1164837.8969 | 2059144.949 | 1178806.8762 | 1181390.9178 | 1179805.4492 | 0 | 0 | 0 | 0 | 0 | 1164837.8969 | 2059144.949 | 1178806.8762 | 1181390.9178 | 1179805.4492 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Vulnerable
22649 | CSO Service Enhancements - Projects | N.D.M.1.60 | 4042 | 212 | INFO SOLUTIONS DIVISION | AIP000285B | AIP000285 | AIP000285 | No | AIP000285 | ISD Customer Care |  |  | IT Business Improvements & Enhancements | lincoln.frost-hunt@hydroone.com | Wayne.Logan@HydroOne.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | AWRD EMPP | Executing | Short Term Planning | Retainer | 1242493.7567 | 1255097.8736 | 1257393.962 | 1260150.3543 | 1258459.1851 | 0 | 0 | 0 | 0 | 0 | 1242493.7567 | 1255097.8736 | 1257393.962 | 1260150.3543 | 1258459.1851 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Vulnerable
22650 | Cornerstone Phase 3 - Workflow of the Future | N.C.C.2.10 | 7193 | 227 | CORNERSTONE | AIP000056 |  | AIP000056 | Yes | AIP000056 | [11 empty] | Project | init EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22651 | Cornerstone Phase 3 - Meter Management | N.C.C.2.10 | 7193 | 227 | CORNERSTONE | UNPLND |  |  | Yes | [12 empty] | Project | EMPP init | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22653 | DX P&C Corrective | N.D.M.1.17 | 7370 | 206 | TX LINES AND STATIONS | AIP000282 | AIP000282 | AIP000282 | No | AIP000282 | DX P&C Corrective |  |  | Protection, Control and Telecom Maintenance | joseph.parete@hydroone.com | warren.tingle@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | ACTN EMPP | Executing | Short Term Planning | # of Orders | 262183.8494 | 270140.3339 | 276047.2574 | 282185.4393 | 287395.023 | 0 | 0 | 0 | 0 | 0 | 262183.8494 | 270140.3339 | 276047.2574 | 282185.4393 | 287395.023 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
22656 | Oshawa Wilson TS: Install Neutral Reactors | N.T.C.2.21 | 7700 | 203 | PROJECT DELIVERY | AIP000960 |  | AIP000960 | Yes | AIP000960 |  |  |  | Major Risk Mitigation | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22657 | MFA Client Tech & Periph Refresh | N.C.C.1.75 | 4339 | 212 | INFO SOLUTIONS DIVISION | AIP000044 | AIP000044 | AIP000044 | No | AIP000044 | MFA - Client Technology | 0 |  | IT - MFA | lincoln.frost-hunt@hydroone.com | Raj.Agnihotri@HydroOne.com | General Plant | 0 | 0 | 03 - None (default) | 0 | Program | EMPP init | Executing | Short Term Planning | Retainer | 1930000 | 1991445.4729 | 1973925.252 | 1949870.4628 | 1925619.2509 | 1908689.0713 | 0 | 0 | 0 | 0 | 1930000 | 1991445.4729 | 1973925.252 | 1949870.4628 | 1925619.2509 | 1908689.0713 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | False |  | False | False | True | False | TRUE | Replacement of MFA that have reached endo of their useful life is necessary to address warranty considerations and to maintain harware reliability, as well as to upgrade existing equipment to meet business performance needs. | 0 | 0 | Intermediate Modified - (Tx Decision)
22658 | MFA Telecom Tech Refresh | N.C.C.1.75 | 4339 | 212 | INFO SOLUTIONS DIVISION | AIP000046 | AIP000046 | AIP000046 | No | AIP000046 | MFA - Telecom | 0 |  | IT - MFA | lincoln.frost-hunt@hydroone.com | Raj.Agnihotri@HydroOne.com | General Plant | 0 | 0 | 03 - None (default) | 0 | Program | init EMPP | Executing | Short Term Planning | Retainer | 1249999.88 | 995722.617 | 986962.6852 | 974935.1144 | 962809.5484 | 954344.4784 | 0 | 0 | 0 | 0 | 1249999.88 | 995722.617 | 986962.6852 | 974935.1144 | 962809.5484 | 954344.4784 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | False |  | False | False | True | False | TRUE | Telecom infrsastrucutre is the underlying hardware to support the business telecom network which is used to transmit data required to run business applications. This investment is required to replace end-of-life assets and to maintain service reliability and security, by refreshing network switches and routers, upgrading voice infrastructure, replacing un-interruptible power source systems, and upgrading the security solutions for external netwrok interfaces. | 0 | 0 | Intermediate - Modified (Tx Decision)
22659 | MFA Infrastructure Technology | N.C.C.1.75 | 4339 | 212 | INFO SOLUTIONS DIVISION | AIP000045 | AIP000045 | AIP000045 | No | AIP000045 | MFA - Infrastructure Refresh | 0 |  | IT - MFA | lincoln.frost-hunt@hydroone.com | Raj.Agnihotri@HydroOne.com | General Plant | 0 | 0 | 03 - None (default) | 0 | Program | init EMPP | Executing | Short Term Planning | Retainer | 3400000 | 3385457.4235 | 3355672.6087 | 3314779.6698 | 3273552.6109 | 3244771.4174 | 0 | 0 | 0 | 0 | 3400000 | 3385457.4235 | 3355672.6087 | 3314779.6698 | 3273552.6109 | 3244771.4174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | False |  | False | False | True | False | TRUE | IT system availablity directly impacts the producivity of employees who use the technology. IT availabiliy also has direct impacts on the availability and security of the power network itself given the modern suites of tools that are relied upon to monitor and operate the grid. | 0 | 0 | Intermediate
22663 | Barrie TS M1, M6 ID 16490 - TX -IBM Data Center | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22665 | North of Dryden DX Contribution to TX upgrades | N.D.C.2.02 | 7700 | 203 | PROJECT DELIVERY | AIP005264 | AIP005264 | AIP005264 | No | AIP005264 | Red Lake Tx Upgrades Capital Contribution |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Cecilia.Pang@HydroOne.com | General Plant | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | EMPP ACTN | Executing | Executing |  | 614111.3415 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2187486.3415 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1.1102e-10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1573375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41973 | 43179 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
22667 | Regulated Waste Storage Units - Transmission | N.T.C.1.22 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes | [12 empty] | Program | ACCP EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22670 | Cambridge-MTO-3 Improved Hwy 401 Crossings-Recover | N.T.C.1.14 | 7700 | 203 | PROJECT DELIVERY | AIP000484 |  | AIP000484 | Yes | AIP000484 |  |  |  | Third Party Transmission System Modifications | john.boldt@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22678 | Massey DS F3 Feeder Upgrades | N.D.C.2.02 | 7374 | 205 | LINES | AIP000183A |  | AIP000183 | Yes | AIP000183 | (1) System upgrade driven by load growth |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Michael.Medeiros@HydroOne.com | System Service | 0 | 0 | 03 - None (default) | Not Required | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22680 | Manvers - Lafarge Aggregate Pit - Recoverable | N.T.C.1.14 | 7700 | 203 | PROJECT DELIVERY | AIP000497 | AIP000497 | AIP000497 | No | AIP000497 | Manvers - Lafarge Aggregate Pit - Recov | 0 |  | Third Party Transmission System Modifications | john.boldt@HydroOne.com | Gian.Minichini@HydroOne.com | System Renewal | Eastern | 0 | 01 - Agreement (current/future) | 0 | Project | ACTN DETL | Short Term Planning | Short Term Planning |  | 0 | 0 | 248.6131 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3869000 | 9341000 | 223248.6531 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1.9516e-12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3869000 | -9341000 | -223000.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43631 | 44180 | True | Lafarge asked HONI to relocate four 230 kV transmission circuits (C28C, H24C, H26C, M29C) that cross through Lafarge's aggregate pit. | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Manvers – Lafarge Aggregate Pit - Recov
22681 | Brockville TS: Install Neutral Reactor | N.T.C.2.21 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Major Risk Mitigation | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22685 | Marathon OC Concrete Pad | N.D.C.1.50 | 7236 | 215 | FACILITIES & REAL ESTATE | UNPLND |  |  | Yes |  |  |  |  | Real Estate Facilities | cindy.copp@hydroone.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22691 | Penetang OC Paving 2013 | N.D.C.1.50 | 7236 | 215 | FACILITIES & REAL ESTATE | UNPLND |  |  | Yes |  |  |  |  | Real Estate Facilities | cindy.copp@hydroone.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22692 | Kent TS-M18-ID 76-PV mitigation | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000194 |  | AIP000194 | Yes | AIP000194 | Distance Limitation Mitigation Work (E&T) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | Not Required | 03 - None (default) | Not Required | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22694 | Pond Mills Construction Site Improvemets | N.C.C.1.50 | 7236 | 215 | FACILITIES & REAL ESTATE | UNPLND |  |  | Yes |  |  |  |  | Real Estate Facilities | cindy.copp@hydroone.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22695 | Thunder Bay 205 Burwood Paving 2013 | N.C.C.1.50 | 7236 | 215 | FACILITIES & REAL ESTATE | UNPLND |  |  | Yes |  |  |  |  | Real Estate Facilities | cindy.copp@hydroone.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22696 | Kenora OC Paving 2013 | N.C.C.1.50 | 7236 | 215 | FACILITIES & REAL ESTATE | UNPLND |  |  | Yes |  |  |  |  | Real Estate Facilities | cindy.copp@hydroone.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22697 | Safety System Evaluation | N.C.M.3.03 | 7054 | 209 | HEALTH, SAFETY & ENV | AIP005020 | AIP005020 | AIP005020 | No | AIP005020 | Safety System Evaluation | 0 |  | Environment Health and Safety | welchw@hydroone.com | welchw@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | init | Short Term Planning | Short Term Planning |  | 0 | 286710.4 | 0 | 313094.36 | 0 | 310000 | 0 | 0 | 0 | 0 | 0 | 286710.4 | 0 | 313094.36 | 0 | 310000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Optimal - (Modified-Tx Decision)
22700 | Stratford TS M6 expansion | N.D.C.2.02 | 7374 | 205 | LINES | AIP000183A |  | AIP000183 | Yes | AIP000183 | (1) System upgrade driven by load growth |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Michael.Medeiros@HydroOne.com | System Service | 0 | 0 | 03 - None (default) | Not Required | Project | DETL EXTR | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22701 | Jones Creek DS-SSI | N.D.C.2.02 | 7374 | 205 | LINES | AIP000183A |  | AIP000183 | Yes | AIP000183 | (1) System upgrade driven by load growth |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Michael.Medeiros@HydroOne.com | System Service | 0 | 0 | 03 - None (default) | Not Required | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22702 | St. Isidore TS New Feeder 62M5 | N.D.C.2.02 | 7700 | 203 | PROJECT DELIVERY | AIP005281 |  | AIP005281 | Yes | AIP005281 |  |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | [6 empty] | Project | EMPP ACTN | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22703 | Lily Lake DS-Chemung DS Tie Line | N.D.C.2.02 | 7374 | 205 | LINES | AIP000185 |  | AIP000185 | Yes | AIP000185 | (3) Reliability Improvements | ISD-SS-03 | Reliability Improvements | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Michael.Medeiros@HydroOne.com | System Service | 0 | 0 | 03 - None (default) | 0 | Project | DETL ACTN | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22704 | Rice Lake DS F2 | N.D.C.2.02 | 7374 | 205 | LINES | AIP005625 | AIP005625 | AIP005625 | No | AIP005625 | Rice Lake DS F2 |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Dhaval.Patel@hydroone.com | System Service | Eastern | 0 | 03 - None (default) | 0 | Project | DETL HOLD | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42794 | 43069 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
22705 | Kent OC Paving 2013 | N.D.C.1.50 | 7236 | 215 | FACILITIES & REAL ESTATE | UNPLND |  |  | Yes |  |  |  |  | Real Estate Facilities | cindy.copp@hydroone.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22706 | Mobile IT | N.C.C.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION | UNPLND |  |  | Yes |  |  |  |  | IT Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22707 | NOMS Upgrade | N.C.C.3.01 | 4514 | 212 | INFO SOLUTIONS DIVISION | AIP000074 | AIP000074 | AIP000074 | No | AIP000074 | NOMS Refresh | 0 |  | Common Oper Infrast & Control Facilities | Godfrey.Holder@HydroOne.com | emily.booth@hydroone.com | General Plant | 0 | Not Required | 03 - None (default) | Not Required | Project | AWRD EMPP | Executing | Executing |  | 612600 | 3953182.8212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 612600 | 3953182.8212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43467 | 43765 | False |  | True | Market Rules; DSC 4.4.7; Hydro One Conditions of Service, Section H | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Asset Optimal
22708 | Placeholder for DC202 Load Growth Projects - EPD | N.D.C.2.02 | 7700 | 203 | PROJECT DELIVERY | AIP000183A | AIP000183 | AIP000183 | No | AIP000183 | (1) System upgrade driven by load growth |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Michael.Medeiros@HydroOne.com | System Service | 0 | 0 | 03 - None (default) | Not Required | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 5426231.9165 | 5537855.1792 | 5648426.3354 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5426231.9165 | 5537855.1792 | 5648426.3354 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43098 | 44910 | [13 empty] | FALSE |  | 0 | 0 | Alternative 1
22709 | Placeholder for TC108 E&PD Projects | N.T.C.1.08 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | System Re-investment | James.Mardegan@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22710 | NMS Enhancements | N.T.C.3.06 | 4514 | 212 | INFO SOLUTIONS DIVISION | AIP005058 | AIP005058 | AIP005058 | No | AIP005058 | NMS Enhancements | 0 |  | Grid Operating and Control Facilities | Godfrey.Holder@HydroOne.com | Daniel.Lam@HydroOne.com | General Plant | N/A | Not Required | 03 - None (default) | Not Required | Project | init | Short Term Planning | Short Term Planning |  | 2456276.4573 | 1387426.7196 | 2457039.6054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2456276.4573 | 1387426.7196 | 2457039.6054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43038 | 43976 | False |  | True | NERC CIP System vulnerability and patch management. | False |  | False | False |  | False | True | False | False | FALSE |  | 0 | 0 | Asset Optimal - NMS Enhancements
22711 | Incremental ADS Provincial Rollout Placeholder - P | N.T.C.1.19 | 4342 | 212 | INFO SOLUTIONS DIVISION | UNPLND |  |  | Yes |  |  |  |  | Protection Control & Metering Equip | Miroslav.Kostic@HydroOne.com | [6 empty] | Program | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22712 | Incremental ADS Provincial Rollout Placeholder - P | N.D.C.1.08 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Distributing & Regulating Stations | emre.aydin@HydroOne.com | [6 empty] | Program | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22713 | Incremental ADS Provincial Rollout Placeholder - P | N.D.C.1.07 | 7374 | 205 | LINES | UNPLND |  |  | Yes |  |  |  |  | Lines | emre.aydin@HydroOne.com | [6 empty] | Program | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22714 | Incremental ADS Provincial Rollout Placeholder - P | N.T.C.2.11 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Load Customer Connection | Robert.Reinmuller@HydroOne.com | [6 empty] | Program | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22715 | Incremental ADS Provincial Rollout Placeholder - P | N.D.C.2.02 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22716 | Placeholder for TC202 Projects to be Identified | N.T.C.2.02 | 7700 | 203 | PROJECT DELIVERY | AIP000704 | AIP000704 | AIP000704 | No | AIP000704 | Local Area Supply - Regional Plans | SS-16 | Future Transmission Regional Plans | Local Area Supply | Robert.Reinmuller@HydroOne.com | farooq.qureshy@hydroone.com | System Service | 0 | Not Required | 03 - None (default) | Not Required | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 4807909.448 | 19065190.2504 | 18942157.7661 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4807909.448 | 19065190.2504 | 18942157.7661 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44255 | 45778 | True | Future plans requested by the Regional Planning Working Groups. | True | Future plans required to meet IESO load supply critieria in the Ontario Resource and Transmission Assessment Critieria. | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Alternative 1
22717 | Placeholder for TC211 Projects | N.T.C.2.11 | 7700 | 203 | PROJECT DELIVERY | AIP000820 | AIP000820 | AIP000820 | No | AIP000820 | Tx Load Connection Plans | SA-09 | Future Transmission Load Connection Plans | Load Customer Connection | Robert.Reinmuller@HydroOne.com | farooq.qureshy@hydroone.com | System Access | 0 | TBD | 03 - None (default) | TBD | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 1414486.9596 | 9859563.2142 | 8229420.3871 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3343486.9596 | 28016563.1342 | 24430420.4271 | 0 | 0 | 0 | 0 | 5.5511e-11 | 0 | 0 | 2.2204e-10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1929018.381 | -18156985.8514 | -16201001.8204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44255 | 45961 | True | Placeholder for future load connection requests. | True | Transmission license requirement to connect customers. | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Alternative 1
22720 | Unforseen Eng and Environ Tech Support | N.T.M.1.14 | 4048 | 213 | PLANNING | UNPLND |  |  | Yes |  |  |  |  | Engineering and Environmental Support | Mike.Tanaskovic@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22721 | Unforseen Power Equip Tech Support | N.T.M.1.16 | 4048 | 213 | PLANNING | UNPLND |  |  | Yes |  |  |  |  | Power Equipment | Mike.Tanaskovic@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22722 | Unforseen Infrastructure Main Tech Support | N.T.M.1.19 | 4048 | 213 | PLANNING | UNPLND |  |  | Yes |  |  |  |  | Infrastructure Maintenance | Mike.Tanaskovic@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22724 | Placeholder for TC203 Projects | N.T.C.2.03 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Network Transfer Capability | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22725 | Beckwith DS T2 and F3 | N.D.C.2.02 | 7700 | 203 | PROJECT DELIVERY | AIP005395 |  | AIP005395 | Yes | AIP005395 |  |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22730 | MFA 2013 - Cornerstone Phase 4 - CIS | N.C.C.1.75 | 7193 | 227 | CORNERSTONE | UNPLND |  |  | Yes |  |  |  |  | IT - MFA | lincoln.frost-hunt@hydroone.com | [6 empty] | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22732 | Belle River DS Voltage Conversion | N.D.C.2.02 | 7374 | 205 | LINES | AIP005243 |  | AIP005243 | Yes | AIP005243 |  |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | [6 empty] | Project | EMPP ACTN | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22733 | Bob-Lo DS Voltage Conversion | N.D.C.2.02 | 7374 | 205 | LINES | AIP000184A |  | AIP000184 | Yes | AIP000184 | (2) Asset Life Cycle Optimization & Operational Efficiency |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Michael.Medeiros@HydroOne.com | System Renewal | 0 | 0 | 03 - None (default) | 0 | Project | EMPP ACTN | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22734 | Northwest Special Protection Scheme | N.T.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP005103 | AIP005103 | AIP005103 | No | AIP005103 | Northwest Special Protection Scheme | 0 |  | Network Transfer Capability | Robert.Reinmuller@HydroOne.com | Hamid.Hamadanizadeh@HydroOne.com | System Service | 0 | Not Required | 03 - None (default) | Not Required | Project | ACCP EMPP | Executing | Executing |  | 31183.5742 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31183.5742 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42719 | [13 empty] | FALSE |  | 0 | 0 | Alternative 1
22735 | Listowel OC Paving 2013 | N.D.C.1.50 | 7236 | 215 | FACILITIES & REAL ESTATE | UNPLND |  |  | Yes |  |  |  |  | Real Estate Facilities | cindy.copp@hydroone.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22737 | Operating Power System IT Support | N.T.M.1.17 | 4514 | 212 | INFO SOLUTIONS DIVISION | AIP005042 | AIP005042 | AIP005042 | No | AIP005042 | Operating Power System IT Support | 0 |  | Protection Control & Metering Equipment | Miroslav.Kostic@HydroOne.com | alan.wong@hydroone.com | System O&M | 0 | 0 | 02 - Expectation (no agreement) | 0 | Program | EMPP AWRD | Executing | Short Term Planning | Daily and monthly reportng | 1532170.0554 | 1643766.2192 | 1713115.6803 | 1785485.486 | 1858977.4994 | 1859526.2603 | 0 | 0 | 0 | 0 | 1532170.0554 | 1643766.2192 | 1713115.6803 | 1785485.486 | 1858977.4994 | 1859526.2603 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Vulnerable (Modified-Tx Decision)
22738 | Bell TCA Equipment Change Out - Recoverable | N.T.C.1.14 | 7700 | 203 | PROJECT DELIVERY | AIP005099 |  | AIP005099 | Yes | AIP005099 |  |  |  | Third Party Transmission System Modifications | john.boldt@HydroOne.com | [6 empty] | Project | ACTN LLTM | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22739 | Head Office Improvements Furniture-Lines | N.C.C.1.55 | 7374 | 205 | LINES |  |  |  | No |  |  |  |  | MFA - Real Estate Facilities | cindy.copp@hydroone.com | [6 empty] | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22743 | TWE - Constrution Services | N.C.C.1.30 | 7411 | 228 | CONSTRUCTION | AIP000014B | AIP000014 | AIP000014 | No | AIP000014 | Transport and Work Equipment (TWE) Capital Requirements | GP-13 | Transport & Work Equipment | Fleet | robert.berardi@HydroOne.com | angela.mallozzi@hydroone.com | General Plant | 0 | 0 | 03 - None (default) | 0 | Program | AWRD EMPP | Executing | Short Term Planning | # of Vehicles | 313038.6 | 317933.752 | 321439.2984 | 323872.6259 | 326241.3404 | 329840.4623 | 0 | 0 | 0 | 0 | 313038.6 | 317933.752 | 321439.2984 | 323872.6259 | 326241.3404 | 329840.4623 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | False |  | False | False | False | False | TRUE | Vehicles must be maintained at an optimum level to ensure public and employee safety, meet Ministry regulations such as CSA 225, Highway Trafffic Act, CVOR regulations. | 0 | 0 | Vulnerable (Modified - Tx Decision)
22744 | TWE - Forestry operation | N.C.C.1.30 | 7362 | 204 | FORESTRY | AIP000014C | AIP000014 | AIP000014 | No | AIP000014 | Transport and Work Equipment (TWE) Capital Requirements | GP-13 | Transport & Work Equipment | Fleet | robert.berardi@HydroOne.com | angela.mallozzi@hydroone.com | General Plant | 0 | 0 | 03 - None (default) | 0 | Program | EMPP ACTN | Executing | Short Term Planning | # of Vehicles | 1252154.4 | 1271734.53 | 1285756.9565 | 1295490.2697 | 1304965.3617 | 1319361.8491 | 0 | 0 | 0 | 0 | 1252154.4 | 1271734.53 | 1285756.9565 | 1295490.2697 | 1304965.3617 | 1319361.8491 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | False |  | False | False | False | False | TRUE | Vehicles must be maintained at an optimum level to ensure public and employee safety, meet Ministry regulations such as CSA 225, Highway Trafffic Act, CVOR regulations. | 0 | 0 | Vulnerable (Modified - Tx Decision)
22745 | Head Office Improvements Furniture-Construction | N.C.C.1.55 | 7411 | 228 | CONSTRUCTION |  |  |  | No |  |  |  |  | MFA - Real Estate Facilities | cindy.copp@hydroone.com | [6 empty] | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22750 | TWE - Provincial lines | N.C.C.1.30 | 7374 | 205 | LINES | AIP000014D | AIP000014 | AIP000014 | No | AIP000014 | Transport and Work Equipment (TWE) Capital Requirements | GP-13 | Transport & Work Equipment | Fleet | robert.berardi@HydroOne.com | angela.mallozzi@hydroone.com | General Plant | 0 | 0 | 03 - None (default) | 0 | Program | ACTN EMPP | Executing | Short Term Planning | # of Vehicles | 313038.6 | 317933.752 | 321439.2984 | 323872.6259 | 326241.3404 | 329840.4623 | 0 | 0 | 0 | 0 | 313038.6 | 317933.752 | 321439.2984 | 323872.6259 | 326241.3404 | 329840.4623 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | False |  | False | False | False | False | TRUE | Vehicles must be maintained at an optimum level to ensure public and employee safety, meet Ministry regulations such as CSA 225, Highway Trafffic Act, CVOR regulations. | 0 | 0 | Vulnerable (Modified - Tx Decision)
22752 | GPS Telemetrics Expansion | N.C.C.1.75 | 4330 | 212 | INFO SOLUTIONS DIVISION | AIP005023 |  | AIP005023 | Yes | AIP005023 |  |  |  | IT - MFA | lincoln.frost-hunt@hydroone.com | [6 empty] | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22755 | OPGW upgrade D1A/D3A | N.T.C.3.08 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Integrating Operating Infrastructure | Miroslav.Kostic@HydroOne.com | [6 empty] | Project | EMPP init | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22760 | AMI Wireless Telecom Upgrade | N.D.C.1.09 | 7374 | 205 | LINES | AIP005003 | AIP005003 | AIP005003 | No | AIP005003 | Metering CDMA Replacement |  |  | Metering | Peter.Mitskos@HydroOne.com | Dominic.Consorti@HydroOne.com | System Access | 0 | 0 | 03 - None (default) | 0 | Program | AWRD EMPP | Executing | Short Term Planning | # of Meters | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41517 | 42827 | [13 empty] | FALSE |  | 0 | 0 | Vulnerable
22766 | Brant TS: Install 115kV Switching Facilities | N.T.C.2.02 | 7700 | 203 | PROJECT DELIVERY | AIP005449 | AIP005449 | AIP005449 | No | AIP005449 | Brant TS: Install 115kV Switching Facilities | SS-09 | Brant TS: Install 115kV Switching Facilities | Local Area Supply | Robert.Reinmuller@HydroOne.com | Khurram.Makhdoom@HydroOne.com | System Service | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACCP EMPP | Executing | Executing |  | 5032333.2594 | 4284206.7827 | 0.0098282 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5032333.2594 | 4284206.7827 | 0.0098282 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43707 | [13 empty] | FALSE |  | 0 | 0 | Alternative 1
22772 | Engineering Design Transformation | N.C.C.2.60 | 4514 | 212 | INFO SOLUTIONS DIVISION | AIP005030 |  | AIP005030 | Yes | AIP005030 |  |  |  | IT Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22773 | Customer Care Program – Analytics & Alerts | N.D.C.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION | AIP005031 |  | AIP005031 | Yes | AIP005031 | Customer Alerts & Analytics |  |  | IT Business Solution Development | jj.blais@HydroOne.com | jj.blais@HydroOne.com | General Plant | 0 | 0 | 03 - None (default) | 0 | Project | AWRD | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22775 | Tillsonburg TS-M2-ID 21130-Dx-Grid Scale Flywheel | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Distribution Generation Connection | ryan.boudreau@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22776 | Tillsonburg TS-M2-ID 21130-Tx-Grid Scale Flywheel | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | [6 empty] | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22780 | L28C - Connect Green Electron Power Plant | N.T.C.2.12 | 7700 | 203 | PROJECT DELIVERY | AIP005056 |  | AIP005056 | Yes | AIP005056 |  |  |  | Generator Customer Connection | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22790 | DM203 Customer Care Reporting Program | N.D.M.2.03 | 4175 | 202 | CUSTOMER CARE SERVICES |  |  |  | No |  |  |  |  | Distributed Generation Connections | ryan.boudreau@HydroOne.com | [6 empty] | Program | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22791 | Brant TS M14 21700 GEDS - 29: St. George - German | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22795 | Palmerston TS 28M2 Supply to Mount Forest | N.D.C.2.02 | 7374 | 205 | LINES | AIP005238 |  | AIP005238 | Yes | AIP005238 |  |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22800 | Morrisburg TS New Feeder 18M24 | N.D.C.2.02 | 4048 | 213 | PLANNING | UNPLND |  |  | Yes |  |  |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | [6 empty] | Project | EMPP AWRD | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22801 | Dobbin DS F1 Reinforcement | N.D.C.2.02 | 7374 | 205 | LINES | AIP000183A |  | AIP000183 | Yes | AIP000183 | (1) System upgrade driven by load growth |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Michael.Medeiros@HydroOne.com | System Service | 0 | 0 | 03 - None (default) | Not Required | Project | init BEST | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22805 | Mississauga-QEW Credit Valley Future Circuit Reloc | N.T.C.1.14 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Third Party Transmission System Modifications | john.boldt@HydroOne.com | [6 empty] | Project | BEST EXTR | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22810 | Scarboro TS ISCR | N.T.C.1.10 | 7700 | 203 | PROJECT DELIVERY | AIP005079 | AIP005079 | AIP005079 | No | AIP005079 | Scarboro TS - ISCR | 0 |  | Integrated Station Component Replacement | James.Mardegan@HydroOne.com | michael.xavier@hydroone.com | System Renewal | Central | 0 | 03 - None (default) | 0 | Project | EMPP ACTN | Executing | Executing | Components | 287334.3627 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 287334.3627 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43069 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
22815 | Information Rights Management | N.C.C.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION | AIP005045 | AIP005045 | AIP005045 | No | AIP005045 | Information Rights Management | 0 |  | IT Business Solution Development | jj.blais@HydroOne.com | Sherry.Wilging@hydroone.com | General Plant | 0 | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 1633929.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1633929.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43024 | 43322 | False |  | True | Bill 198 | False |  | False | False |  | False | False | True | False | FALSE |  | 0 | 0 | Asset Optimal - Modified (Tx Decision)
22817 | Final Destination - Enterprise GIS Updates | N.D.C.2.60 | 4514 | 212 | INFO SOLUTIONS DIVISION | AIP005047 |  | AIP005047 | Yes | AIP005047 |  |  |  | IT Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22820 | Placeholder - CornerStone Phase 3 OMA - HR Pay | N.C.M.2.10 | 7193 | 227 | CORNERSTONE | AIP005048 |  | AIP005048 | Yes | AIP005048 | [11 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22821 | Placeholder - CornerStone Phase 3 OMA - Workflow | N.C.M.2.10 | 7193 | 227 | CORNERSTONE | AIP005049 |  | AIP005049 | Yes | AIP005049 | [11 empty] | Project | init EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22823 | Kent TS M24 expansion | N.D.C.2.02 | 7374 | 205 | LINES | AIP005241 |  | AIP005241 | Yes | AIP005241 |  |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | [6 empty] | Project | EMPP ACTN | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22826 | Pickering CMS HVAC Upgrade 2013 | N.C.C.1.50 | 7236 | 215 | FACILITIES & REAL ESTATE | UNPLND |  |  | Yes |  |  |  |  | Real Estate Facilities | cindy.copp@hydroone.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22830 | Tilbury DS New Feeder | N.D.C.2.02 | 7700 | 203 | PROJECT DELIVERY | AIP005331 | AIP005331 | AIP005331 | No | AIP005331 | Tilbury West DS Upgrade | ISD-SS-03 | Reliability Improvements | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Alexander.Hamlyn@HydroOne.com | System Service | Western | 0 | 02 - Expectation (no agreement) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 176142.3631 | 1761556.7545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200161.7762 | 2001769.0391 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -24019.4131 | -240212.2847 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43448 | 43798 | [13 empty] | FALSE |  | 1 | 1 | Asset Optimal
22855 | Extend 44 kV Supply to Coniston | N.D.C.2.02 | 7374 | 205 | LINES | AIP005247 |  | AIP005247 | Yes | AIP005247 |  |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | [6 empty] | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22860 | Operating Hardware Refresh | N.C.C.3.01 | 4514 | 212 | INFO SOLUTIONS DIVISION | AIP000073 | AIP000073 | AIP000073 | No | AIP000073 | Operating Hardware Refresh | GP-06 | Operating Common IT Infrastructure | Common Oper Infrast & Control Facilities | Godfrey.Holder@HydroOne.com | mallen@hydroone.com | General Plant | 0 | Not Required | 03 - None (default) | Not Required | Project | AWRD | Short Term Planning | Short Term Planning |  | 4200000 | 3385457.304 | 1585061.8823 | 4003084.1381 | 7326981.2496 | 6680411.3488 | 0 | 0 | 0 | 0 | 4200000 | 3385457.304 | 1585061.8823 | 4003084.1381 | 7326981.2496 | 6680411.3488 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43798 | 45198 | False |  | True | NERC CIP-007-5 R2 | True |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Asset Optimal
22861 | Placeholder for DC202 Reliability Projects - Lines | N.D.C.2.02 | 7374 | 205 | LINES | AIP000185 | AIP000185 | AIP000185 | No | AIP000185 | (3) Reliability Improvements | ISD-SS-03 | Reliability Improvements | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Michael.Medeiros@HydroOne.com | System Service | 0 | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 4127351.1175 | 4210216.2076 | 4297575.5855 | 4385981.3385 | 4473553.6153 | 0 | 0 | 0 | 0 | 0 | 4690171.7244 | 4784336.5995 | 4883608.6199 | 4984069.7028 | 5083583.6538 | 0 | 0 | 0 | 0 | 0 | -562820.6069 | -574120.3919 | -586033.0344 | -598088.3643 | -610030.0385 | 0 | 0 | 0 | 0 | 0 | -12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43098 | 44910 | [13 empty] | FALSE |  | 0 | 0 | Alternative 1
22862 | Placeholder for DC202 Capital Contrib Projects | N.D.C.2.02 | 4048 | 213 | PLANNING | AIP000186 |  | AIP000186 | Yes | AIP000186 |  |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22864 | Placeholder for DC308 - ISD | N.D.C.3.08 | 4514 | 212 | INFO SOLUTIONS DIVISION |  |  |  | No |  |  |  |  | Operating Infrastructure | Godfrey.Holder@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22867 | PSIT Cyber System End-of-Life Lifecycle | N.T.C.1.29 | 4514 | 212 | INFO SOLUTIONS DIVISION | AIP005052 |  | AIP005052 | Yes | AIP005052 |  |  |  | NERC Cyber Security Compliance Readiness | lincoln.frost-hunt@hydroone.com | [6 empty] | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22869 | Q11S/Q12S - Tx Lines Refurbishment Program | N.T.C.1.12 | 7700 | 203 | PROJECT DELIVERY | AIP005373 |  | AIP005373 | Yes | AIP005373 |  |  |  | Overhead Lines Component Refurb & Repl | hassan.hamzeh@hydroone.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22871 | Placeholder for DM250 - CDM Projects | N.D.M.2.50 | 1144 | 220 | STRATEGY & CONSERV |  |  |  | No |  |  |  |  | Conservation and Demand Management | Imran.Merali@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22873 | Budget Placeholder TC203 - E&CS Projects | N.T.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000729 |  | AIP000729 | Yes | AIP000729 |  |  |  | Network Transfer Capability | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22874 | Budget Placeholder TC308 - E&CS Projects | N.T.C.3.08 | 7700 | 203 | PROJECT DELIVERY | AIP005053 |  | AIP005053 | Yes | AIP005053 |  |  |  | Integrating Operating Infrastructure | Miroslav.Kostic@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22875 | Placeholder for TC108 E&PD Programs | N.T.C.1.08 | 7700 | 203 | PROJECT DELIVERY |  |  |  | No |  |  |  |  | System Re-investment | James.Mardegan@HydroOne.com | [6 empty] | Program | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22881 | PCB Removals Lighting Replacements 2013-2014 | N.T.C.1.28 | 7236 | 215 | FACILITIES & REAL ESTATE | AIP000664 |  | AIP000664 | Yes | AIP000664 |  |  |  | Transmission Site Facilities | cindy.copp@hydroone.com | [6 empty] | Program | AWRD EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22882 | Poonamalie DS Recloser Upgrade | N.D.C.2.02 | 4048 | 213 | PLANNING | UNPLND |  |  | Yes |  |  |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | [6 empty] | Project | init EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22885 | Tilbury TS / Tilbury West HVDS - DESN Rebuild | N.T.C.2.11 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Load Customer Connection | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | EXTR BEST | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22893 | Kingsville TS M6 ID 21860 DX Leamington Pollution | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Distribution Generation Connection | ryan.boudreau@HydroOne.com | [6 empty] | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22895 | Wiarton RS Reconfiguration | N.D.C.2.02 | 7700 | 203 | PROJECT DELIVERY | AIP005229 | AIP005229 | AIP005229 | No | AIP005229 | Wiarton RS Reconfiguration |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Jerry.Vo@HydroOne.com | System Service | 0 | Not Required | 03 - None (default) | Not Required | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41912 | 42720 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
22896 | Huntsville OC paving 2013 | N.C.C.1.50 | 7236 | 215 | FACILITIES & REAL ESTATE | AIP000027 |  | AIP000027 | Yes | AIP000027 | Facility Accommodation & Improvements Service Centres & Admin |  |  | Real Estate Facilities | cindy.copp@hydroone.com | Peter.Erdman@HydroOne.com | General Plant | 0 | 0 | 03 - None (default) | 0 | Program | AWRD EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22897 | Hanmer TS - T7/T8 Station Refurb | N.T.C.1.08 | 7700 | 203 | PROJECT DELIVERY | AIP005018 |  | AIP005018 | Yes | AIP005018 |  |  |  | System Re-investment | James.Mardegan@HydroOne.com | [6 empty] | Program | EMPP ACCP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22899 | Smiths Falls TS M23 Tx-ID14460 Station Anti-island | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000933 |  | AIP000933 | Yes | AIP000933 |  |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22900 | Install Power Quality Monitors-Various Locations | N.T.C.2.20 | 7700 | 203 | PROJECT DELIVERY | AIP005051 |  | AIP005051 | Yes | AIP005051 |  |  |  | Performance Enhancement | Robert.Reinmuller@HydroOne.com | [6 empty] | Program | EMPP ACCP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22901 | Nepean TS Roof Replacement 2013 | N.T.C.1.28 | 7236 | 215 | FACILITIES & REAL ESTATE | UNPLND |  |  | Yes |  |  |  |  | Transmission Site Facilities | cindy.copp@hydroone.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22902 | Hanmer OC Concrete Pad Repair 2013 | N.C.C.1.50 | 7236 | 215 | FACILITIES & REAL ESTATE | UNPLND |  |  | Yes |  |  |  |  | Real Estate Facilities | cindy.copp@hydroone.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22903 | Minden OC Drainage Rehabiliation 2013 | N.D.C.1.50 | 7236 | 215 | FACILITIES & REAL ESTATE | UNPLND |  |  | Yes |  |  |  |  | Real Estate Facilities | cindy.copp@hydroone.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22904 | Lindsay OC Drainage Rehabilitiation 2013 | N.D.C.1.50 | 7236 | 215 | FACILITIES & REAL ESTATE | UNPLND |  |  | Yes |  |  |  |  | Real Estate Facilities | cindy.copp@hydroone.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22907 | Finch TS Roof Replacement 2013 | N.T.C.1.28 | 7236 | 215 | FACILITIES & REAL ESTATE | UNPLND |  |  | Yes |  |  |  |  | Transmission Site Facilities | cindy.copp@hydroone.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22908 | Cherrywood TS Septic System 2013 | N.T.C.1.28 | 7236 | 215 | FACILITIES & REAL ESTATE | UNPLND |  |  | Yes |  |  |  |  | Transmission Site Facilities | cindy.copp@hydroone.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22909 | London Project Office Demolition | N.C.C.1.50 | 7236 | 215 | FACILITIES & REAL ESTATE | UNPLND |  |  | Yes |  |  |  |  | Real Estate Facilities | cindy.copp@hydroone.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22910 | Allanburg TS M7 - conversion on Haist St | N.D.C.2.02 | 7374 | 205 | LINES | UNPLND |  |  | Yes |  |  |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | [6 empty] | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22912 | Fort Francis TS Roof Replacement 2013 | N.T.C.1.28 | 7236 | 215 | FACILITIES & REAL ESTATE | UNPLND |  |  | Yes |  |  |  |  | Transmission Site Facilities | cindy.copp@hydroone.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22915 | Kingsville TS M6 ID 21860 TX Leamington Pollution | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22917 | Hub Site IPS Replacement Project | N.T.C.1.29 | 7700 | 203 | PROJECT DELIVERY | AIP000679 |  | AIP000679 | Yes | AIP000679 |  |  |  | NERC Cyber Security Compliance Readiness | lincoln.frost-hunt@hydroone.com | [6 empty] | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22918 | Dunnville TS: Add 1x27.6kV Feeder Breaker Position | N.T.C.2.11 | 7700 | 203 | PROJECT DELIVERY | AIP005104 |  | AIP005104 | Yes | AIP005104 |  |  |  | Load Customer Connection | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22919 | Wallbridge DS SSI | N.D.C.2.02 | 7374 | 205 | LINES | UNPLND |  |  | Yes |  |  |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | [6 empty] | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22923 | Norfolk TS M5 ID18230-TX UDI Port Ryerse Wind Farm | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | [6 empty] | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22924 | L&FS Tx Wood Pole Repl Program - Construction | N.T.C.1.12 | 7370 | 206 | TX LINES AND STATIONS | AIP000474C |  | AIP000474 | Yes | AIP000474 | Wood Pole Structure Replacements |  |  | Overhead Lines Component Refurb & Repl | hassan.hamzeh@hydroone.com | TeodorConstantin.Culinescu@HydroOne.com | System Renewal | 0 | 0 | 03 - None (default) | 0 | Program | EMPP ACTN | Executing | Short Term Planning | # of Structures | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22925 | Orillia Forestry Work Centre - Improvements | N.D.C.1.50 | 7236 | 215 | FACILITIES & REAL ESTATE | UNPLND |  |  | Yes |  |  |  |  | Real Estate Facilities | cindy.copp@hydroone.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22926 | Placeholder - Technical Support for Recov Proj | N.T.M.1.20 | 4048 | 213 | PLANNING | AIP001114 |  | AIP001114 | Yes | AIP001114 | Recoverable - Third Party Monitoring/Maintenance |  |  | Overhead Lines | hassan.hamzeh@hydroone.com | Gian.Minichini@HydroOne.com | System O&M | 0 | 0 | 01 - Agreement (current/future) | 0 | Program | init | Short Term Planning | Short Term Planning | Retainer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22930 | Longwood TS HVAC Replacement | N.T.C.1.28 | 7236 | 215 | FACILITIES & REAL ESTATE | UNPLND |  |  | Yes |  |  |  |  | Transmission Site Facilities | cindy.copp@hydroone.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22935 | Goodfish DS F8 Voltage Conversion | N.D.C.2.02 | 7374 | 205 | LINES | AIP000184A |  | AIP000184 | Yes | AIP000184 | (2) Asset Life Cycle Optimization & Operational Efficiency |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Michael.Medeiros@HydroOne.com | System Renewal | 0 | 0 | 03 - None (default) | 0 | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22943 | Carleton Place DS Reconstruction | N.D.C.2.02 | 7374 | 205 | LINES | AIP005279 | AIP005279 | AIP005279 | No | AIP005279 | Carleton Place DS Reconstruction - Line Work | ISD-SR-13 | Life Cycle Optimization & Operational Efficiency Projects | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Muhammad.Sabir@HydroOne.com | System Renewal | Eastern | Not Required | 03 - None (default) | Not Required | Project | HOLD BEST | Short Term Planning | Short Term Planning |  | 2722200.1663 | 3162795.0418 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3093409.2798 | 3594085.2748 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -371209.1136 | -431290.233 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42885 | 43738 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
22944 | Manotick DS Feeder Relief | N.D.C.2.02 | 7374 | 205 | LINES | AIP005278 | AIP005278 | AIP005278 | No | AIP005278 | Manotick DS Feeder Relief | ISD-SS-02 | System Upgrades Driven by Load Growth | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Muhammad.Sabir@HydroOne.com | System Service | Eastern | Not Required | 03 - None (default) | Not Required | Project | init | Short Term Planning | Short Term Planning |  | 1742047.9706 | 888511.6114 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1979599.9666 | 1009672.2857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -237551.996 | -121160.6743 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43128 | 43494 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
22946 | Nipissing OC 2013 Improvements | N.C.C.1.50 | 7236 | 215 | FACILITIES & REAL ESTATE | UNPLND |  |  | Yes |  |  |  |  | Real Estate Facilities | cindy.copp@hydroone.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22948 | Port Hope TS: Component Replacement | N.T.C.1.44 | 7700 | 203 | PROJECT DELIVERY | AIP005019 | AIP005019 | AIP005019 | No | AIP005019 | Port Hope TS: T3/T4 & Component Replacement | SR-05 | Load Station Transformer Replacement Projects | Eastern Zone Station/Yard Investments | James.Mardegan@HydroOne.com | Fred.Kouhdani@HydroOne.com | System Renewal | Eastern | Not Required | 03 - None (default) | Required | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 608794.3202 | 1259730.8115 | 5941283.0688 | 13654359.2019 | 12273044.12 | 2888885.76 | 0 | 0 | 0 | 0 | 654617.5486 | 1354549.2597 | 6388476.4181 | 14682106.6687 | 13196821.52 | 3106328.76 | 0 | 0 | 0 | 0 | -45823.2284 | -94818.4482 | -447193.3493 | -1027747.4668 | -923777.4 | -217443 | 0 | 0 | -7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44509 | 45925 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Component Replacement
22949 | Wanstead TS EOL Station Refurb | N.T.C.1.40 | 7700 | 203 | PROJECT DELIVERY | AIP005009 | AIP005009 | AIP005009 | No | AIP005009 | Wanstead TS T1/T2/T3; T1,T2,PCT,MVGIS | 0 |  | Western Zone Station/Yard Investments | James.Mardegan@HydroOne.com | mark.truchanowicz@hydroone.com | System Renewal | Western | 0 | 03 - None (default) | 0 | Project | ACCP EMPP IESO | Executing | Executing |  | 23887949.3417 | 35608.4257 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27193592.3083 | 39637.4257 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -543384.9666 | -6.9389e-12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2.2209 | 0 | -2762258 | -4029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43434 | [13 empty] | FALSE |  | 0 | 1 | Alternative 1
22950 | Cornerstone Ph3 - OM&A for HR/Pay Transf Project | N.C.M.2.10 | 7193 | 227 | CORNERSTONE | UNPLND |  |  | Yes | [12 empty] | Project | EMPP init | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22951 | Cornerstone Ph3 - MFA for HR/Pay Transf Project | N.C.C.1.75 | 7193 | 227 | CORNERSTONE | UNPLND |  |  | Yes |  |  |  |  | IT - MFA | lincoln.frost-hunt@hydroone.com | [6 empty] | Project | init EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22952 | Sidney TS - ISCR | N.T.C.1.10 | 7700 | 203 | PROJECT DELIVERY | AIP005080 |  | AIP005080 | Yes | AIP005080 |  |  |  | Integrated Station Component Replacement | James.Mardegan@HydroOne.com | [6 empty] | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22953 | Allanburg TS - ISCR | N.T.C.1.10 | 7700 | 203 | PROJECT DELIVERY | AIP005081 | AIP005081 | AIP005081 | No | AIP005081 | Allanburg TS - ISCR | 0 |  | Integrated Station Component Replacement | James.Mardegan@HydroOne.com | mark.truchanowicz@hydroone.com | System Renewal | Hamilton Niagara | 0 | 03 - None (default) | 0 | Project | ACCP EMPP | Executing | Executing | Components | 6019784.1677 | 0 | 0.029484 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6377758.8721 | 0 | 0.029484 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -357974.7044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -5.6129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43447 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
22955 | Buchanan TS: 115 kV Switchyard & Component Repl. | N.T.C.1.40 | 7700 | 203 | PROJECT DELIVERY | AIP005013 | AIP005013 | AIP005013 | No | AIP005013 | Buchanan TS: 115 kV Switchyard & Component Replacement | SR-04 | Bulk Station Switchgear and Ancillary Equipment Replacement Projects | Western Zone Station/Yard Investments | James.Mardegan@HydroOne.com | mark.truchanowicz@hydroone.com | System Renewal | Western | Not Required | 03 - None (default) | Not Required | Project | init | Short Term Planning | Short Term Planning |  | 0 | 307789.7395 | 1072794.2567 | 5594669.3377 | 18040754.6178 | 17005602.6117 | 4599166.88 | 0 | 0 | 0 | 0 | 330956.7092 | 1153542.2115 | 6015773.4814 | 19398660.8793 | 18285594.2061 | 4945340.72 | 0 | 0 | 0 | 0 | -23166.9696 | -80747.9548 | -421104.1437 | -1357906.2616 | -1279991.5944 | -346173.84 | 0 | 0 | 0 | -7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44321 | 45597 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Component Replacement
22957 | Keith TS: T11,T12 & Component Replacement | N.T.C.1.40 | 7700 | 203 | PROJECT DELIVERY | AIP005012 | AIP005012 | AIP005012 | No | AIP005012 | Keith TS: T11,T12 & Component Replacement | SR-03 | Bulk Station Transformer Replacement Projects | Western Zone Station/Yard Investments | James.Mardegan@HydroOne.com | mark.truchanowicz@hydroone.com | System Renewal | Western | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 658440.8019 | 1505872.8057 | 8732790.0164 | 20254916.3167 | 16582381.69 | 3848081.7875 | 0 | 0 | 0 | 0 | 708000.8623 | 1619218.0707 | 9390096.7919 | 21779479.9104 | 17830517.9463 | 4137722.3522 | 0 | 0 | 0 | 0 | -49560.0604 | -113345.2649 | -657306.7754 | -1524563.5937 | -1248136.2562 | -289640.5647 | 0 | 0 | 0 | 0 | -7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43850 | 45184 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 1 | 0 | Component Replacement
22958 | Beach TS: T6, T7, T8 & Component Replacement | N.T.C.1.41 | 7700 | 203 | PROJECT DELIVERY | AIP005011 | AIP005011 | AIP005011 | No | AIP005011 | Beach TS: T6, T7, T8 & Component Replacement | 0 |  | Hamilton/Niagara Zone Station/Yard Investments | James.Mardegan@HydroOne.com | mark.truchanowicz@hydroone.com | System Renewal | Hamilton Niagara | 0 | 03 - None (default) | TBD | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 322053.2864 | 724958.9523 | 5445002.92 | 22213430.36 | 22657699 | 5778280.72 | 0 | 0 | 0 | 0 | 346293.8564 | 779525.7552 | 5854841.8 | 23885409.08 | 24363117.28 | 6213205 | 0 | 0 | 0 | 0 | -24240.5699 | -54566.8029 | -409838.88 | -1671978.72 | -1705418.28 | -434924.28 | -7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45447 | 46722 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Component Replacement
22959 | Warden TS Component Replacement | N.T.C.1.42 | 7700 | 203 | PROJECT DELIVERY | AIP005014 | AIP005014 | AIP005014 | No | AIP005014 | Warden TS: Component Replacements | 0 |  | Central Zone Station/Yard Investments | James.Mardegan@HydroOne.com | michael.xavier@hydroone.com | System Renewal | Greater Toronto Area | Not Required | 01 - Agreement (current/future) | Not Required | Project | AWRD EMPP | Executing | Executing |  | 549352.9532 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 590702.1002 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -41349.147 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -17.8449 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43266 |  |  |  |  | False | [8 empty] | FALSE |  | 0 | 0 | Component Replacements
22961 | Halton TS, PCT and component replacement | N.T.C.1.43 | 7700 | 203 | PROJECT DELIVERY | AIP005015 | AIP005015 | AIP005015 | No | AIP005015 | Halton TS: Breakers, PCT & Component Replacements | SR-06 | Load Station Switchgear and Ancillary Equipment Replacement Projects | Greater Toronto Area Zone Station/Yard Investments | James.Mardegan@HydroOne.com | michael.xavier@hydroone.com | System Renewal | Greater Toronto Area | Not Required | 03 - None (default) | TBD | Project | init | Short Term Planning | Short Term Planning |  | 751073.1581 | 634873.7494 | 3413009.0198 | 3428929.2672 | 863295.2829 | 0 | 0 | 0 | 0 | 0 | 807605.5463 | 682659.9455 | 3669902.1719 | 3687020.7175 | 928274.4978 | 0 | 0 | 0 | 0 | 0 | -56532.3882 | -47786.1962 | -256893.152 | -258091.4502 | -64979.2148 | 0 | 0 | 0 | 0 | 0 | -7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43574 | 44696 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Breakers, PCT & Component Replacements
22963 | Birmingham TS: MV Switchgear Replacement | N.T.C.1.41 | 7700 | 203 | PROJECT DELIVERY | AIP005016 | AIP005016 | AIP005016 | No | AIP005016 | Birmingham TS: MV Switchgear Replacement | SR-06 | Load Station Switchgear and Ancillary Equipment Replacement Projects | Hamilton/Niagara Zone Station/Yard Investments | James.Mardegan@HydroOne.com | mark.truchanowicz@hydroone.com | System Renewal | Hamilton Niagara | 0 | 0 | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 359951.2014 | 854662.6592 | 2660902.5164 | 11338199.9637 | 4236659.7824 | 0 | 0 | 0 | 0 | 0 | 387044.3026 | 918992.1067 | 2861185.5015 | 12191612.8642 | 4555548.1531 | 0 | 0 | 0 | 0 | 0 | -27093.1012 | -64329.4475 | -200282.9851 | -853412.9005 | -318888.3707 | 0 | 0 | 0 | 0 | -7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44209 | 45260 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Component Replacement
22965 | Mohawk TS; T1/T2 Component Replacement | N.T.C.1.41 | 7700 | 203 | PROJECT DELIVERY | AIP005007 | AIP005007 | AIP005007 | No | AIP005007 | Mohawk TS ; T1,T2 Component Replacement | 0 |  | Hamilton/Niagara Zone Station/Yard Investments | James.Mardegan@HydroOne.com | mark.truchanowicz@hydroone.com | System Renewal | Hamilton Niagara | 0 | 03 - None (default) | Required | Project | ACCP EMPP | Executing | Executing |  | 9836270.8993 | 2450460.3701 | 0.0098282 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10576635.3755 | 2634903.6238 | 0.010568 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -740364.4763 | -184443.2537 | -0.00073975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -6.3118 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43615 | [13 empty] | FALSE |  | 0 | 0 | Alternative 1- Component Replacement
22966 | PlaceholderCornerstone Ph3 - OM&A Waste & PCB Mgmt | N.C.M.2.10 | 7193 | 227 | CORNERSTONE | AIP005088 |  | AIP005088 | Yes | AIP005088 | [11 empty] | Project | EMPP AWRD | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22967 | Cornerstone Phase 3 - Waste & PCB | N.C.C.2.10 | 7193 | 227 | CORNERSTONE | AIP005087 |  | AIP005087 | Yes | AIP005087 | [11 empty] | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22970 | Dryden TS - ISCR | N.T.C.1.10 | 7700 | 203 | PROJECT DELIVERY | AIP005083 | AIP005083 | AIP005083 | No | AIP005083 | Dryden TS - ISCR | 0 |  | Integrated Station Component Replacement | James.Mardegan@HydroOne.com | Donald.Mastrangelo@HydroOne.com | System Renewal | Northern | 0 | 03 - None (default) | 0 | Project | ACCP EMPP | Executing | Executing | Components | 3639642.1782 | 66001.8711 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4023470.6112 | 66001.8711 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -383828.433 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -9.3853 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43281 | [13 empty] | FALSE |  | 0 | 1 | Asset Optimal
22971 | Manby TS - ISCR | N.T.C.1.10 | 7700 | 203 | PROJECT DELIVERY | AIP005084 | AIP005084 | AIP005084 | No | AIP005084 | Manby TS - ISCR | SR-06 | Load Station Switchgear and Ancillary Equipment Replacement Projects | Integrated Station Component Replacement | James.Mardegan@HydroOne.com | michael.xavier@hydroone.com | System Renewal | Greater Toronto Area | 0 | 03 - None (default) | 0 | Project | ACCP EMPP | Executing | Executing | Components | 9850412.2021 | 2070159.9946 | 8181.9222 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11574552.6331 | 3138999.3404 | 8181.9222 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1724140.4309 | -1068839.3459 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -19.374 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43730 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
22973 | Stewartville TS - ISCR | N.T.C.1.10 | 7700 | 203 | PROJECT DELIVERY | AIP005086 | AIP005086 | AIP005086 | No | AIP005086 | Stewartville TS - ISCR | 0 |  | Integrated Station Component Replacement | James.Mardegan@HydroOne.com | Donald.Mastrangelo@HydroOne.com | System Renewal | Eastern | 0 | 03 - None (default) | 0 | Project | ACCP EMPP | Executing | Executing | Components | 6409696.3609 | 1305153.9998 | 0.029484 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6626787.2566 | 2132730.9107 | 0.029484 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -217090.8957 | -177576.9109 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -5.4607 | 0 | 0 | -650000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43738 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
22974 | Markham CC Site Improvements 2013 | N.D.C.1.50 | 7236 | 215 | FACILITIES & REAL ESTATE | AIP000027 |  | AIP000027 | Yes | AIP000027 | Facility Accommodation & Improvements Service Centres & Admin |  |  | Real Estate Facilities | cindy.copp@hydroone.com | Peter.Erdman@HydroOne.com | General Plant | 0 | 0 | 03 - None (default) | 0 | Program | AWRD EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22976 | Barwick TS- M2- ID12030- Dx- Morley Solar Park | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000199 |  | AIP000199 | Yes | AIP000199 | Large Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22977 | Barwick TS- M2- ID12030- Tx- Morley Solar Park | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22981 | Arnprior Forestry Work Centre - Improvements | N.C.C.1.50 | 7236 | 215 | FACILITIES & REAL ESTATE | UNPLND |  |  | Yes |  |  |  |  | Real Estate Facilities | cindy.copp@hydroone.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22983 | Wood Pole Replacement Program - Lines | N.T.C.1.21 | 7370 | 206 | TX LINES AND STATIONS | UNPLND |  |  | Yes |  |  |  |  | Infrastructure | James.Mardegan@HydroOne.com | [6 empty] | Program | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22985 | Limoges DS Relief | N.D.C.2.02 | 7374 | 205 | LINES | AIP005405 | AIP005405 | AIP005405 | No | AIP005405 | Limoges DS Relief | ISD-SS-02 | System Upgrades Driven by Load Growth | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Muhammad.Sabir@HydroOne.com | System Service | Eastern | Not Required | 03 - None (default) | Not Required | Project | DETL ACTN | Short Term Planning | Short Term Planning |  | 910004.2502 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1034095.7389 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -124091.4887 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42977 | 43357 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
22986 | Greely DS F1 | N.D.C.2.02 | 7374 | 205 | LINES | AIP005829 | AIP005829 | AIP005829 | No | AIP005829 | Greely DS F1 | ISD-SS-02 | System Upgrades Driven by Load Growth | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Donald.Lau@HydroOne.com | System Service | Eastern | Not Required | 03 - None (default) | Not Required | Project | ACTN DETL | Short Term Planning | Short Term Planning |  | 0 | 1501326.7794 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1501326.7794 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43313 | 43721 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
22987 | Manotick DS F3 | N.D.C.2.02 | 7700 | 203 | PROJECT DELIVERY | AIP005827 | AIP005827 | AIP005827 | No | AIP005827 | Manotick DS - Add F3 Feeder Position | ISD-SS-02 | System Upgrades Driven by Load Growth | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Donald.Lau@HydroOne.com | System Service | Eastern | Not Required | 03 - None (default) | Not Required | Project | DETL init | Short Term Planning | Short Term Planning |  | 0 | 1945719.5061 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1945719.5061 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43434 | 43723 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
22988 | Barwick TS- M2- ID12040-Dx- Dave Rampel Solar Park | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000199 |  | AIP000199 | Yes | AIP000199 | Large Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22989 | Barwick TS-M2- ID12040- Tx- Dave Rampel Solar Park | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22993 | Norfolk TS: M3 feeder, STATCOM unit | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000194 |  | AIP000194 | Yes | AIP000194 | Distance Limitation Mitigation Work (E&T) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | Not Required | 03 - None (default) | Not Required | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22996 | Gate Security (Perth, Brockville, Vankleek Hill) | N.D.C.1.50 | 7236 | 215 | FACILITIES & REAL ESTATE | AIP000027 |  | AIP000027 | Yes | AIP000027 | Facility Accommodation & Improvements Service Centres & Admin |  |  | Real Estate Facilities | cindy.copp@hydroone.com | Peter.Erdman@HydroOne.com | General Plant | 0 | 0 | 03 - None (default) | 0 | Program | AWRD EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22998 | Lythmore DS F3 sw4291 load relief | N.D.C.2.02 | 7374 | 205 | LINES | UNPLND |  |  | Yes |  |  |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | [6 empty] | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23000 | Barwick TS- M2- ID12060-Dx- Vanzwolf Solar Park | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000199 |  | AIP000199 | Yes | AIP000199 | Large Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23001 | Barwick TS-M2- ID12060- Tx- Vanzwolf Solar Park | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23002 | Smart Grid Fund Initiatives | N.D.M.2.22 | 4230 | 213 | PLANNING | AIP005089 |  | AIP005089 | Yes | AIP005089 | [11 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23004 | Strathroy TS M4 ID22370 TX Entegrus Powerlines | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | [6 empty] | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23005 | Toyota Woodstock TS - Upgrade to DESN | N.T.C.2.11 | 7700 | 203 | PROJECT DELIVERY | AIP005090 | AIP005090 | AIP005090 | No | AIP005090 | Toyota Woodstock TS - Upgrade | SA-05 | Toyota Woodstock TS: Upgrade Station and Install Second 115kV Supply | Load Customer Connection | Robert.Reinmuller@HydroOne.com | hemant.barot@hydroone.com | System Access | Western | 0 | 01 - Agreement (current/future) | 0 | Project | DETL LLTM EXTR | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 1500000 | 5000000 | 3000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -500000 | -1500000 | -5000000 | -3000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43707 | 44407 | True | Toyota request | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Alternative 1
23011 | Bruce SC Bldg B37 well improvements | N.T.C.1.28 | 7236 | 215 | FACILITIES & REAL ESTATE | AIP000664 |  | AIP000664 | Yes | AIP000664 |  |  |  | Transmission Site Facilities | cindy.copp@hydroone.com | [6 empty] | Program | AWRD EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23020 | Beach TS ISCR | N.T.C.1.10 | 7700 | 203 | PROJECT DELIVERY | AIP005107 | AIP005107 | AIP005107 | No | AIP005107 | Beach TS - ISCR | SR-02 | Station Reinvestment Projects | Integrated Station Component Replacement | James.Mardegan@HydroOne.com | mark.truchanowicz@hydroone.com | System Renewal | Hamilton Niagara | 0 | 03 - None (default) | 0 | Project | EMPP ACTN | Executing | Executing | Components | 9884696.031 | 3002575.1772 | 0.088453 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10106719.9385 | 3667624.9579 | 0.088453 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -222023.9075 | -665049.7807 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -6.5591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43830 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
23025 | IESO Meter Data Validation - Stations | N.T.M.4.50 | 4337 | 223 | SMART METERS | AIP001192 |  | AIP001192 | Yes | AIP001192 | IESO Meter Data Validation Tx |  |  | Customer Care Services Tx | Imran.Merali@HydroOne.com | Imran.Merali@HydroOne.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | AWRD EMPP | Executing | Short Term Planning | # Validations | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23030 | Meadowvale TS M3 ID22460-TX CCS-Mississauga Gen | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23031 | Markham Skylights / Snow Guard Replacement 2013 | N.D.C.1.50 | 7236 | 215 | FACILITIES & REAL ESTATE | UNPLND |  |  | Yes |  |  |  |  | Real Estate Facilities | cindy.copp@hydroone.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23054 | Government Road Line Extension Kirkland Lake | N.D.C.2.02 | 7374 | 205 | LINES | AIP005232 |  | AIP005232 | Yes | AIP005232 |  |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | [6 empty] | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23061 | Kirkland Lake TS - Archer Drive Voltage Conversion | N.D.C.2.02 | 7374 | 205 | LINES | AIP005377 | AIP005377 | AIP005377 | No | AIP005377 | Archer Drive Voltage Conversion |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Gert.Alikaj@HydroOne.com | System Service | 0 | 0 | 03 - None (default) | 0 | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42501 | 43039 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
23062 | Dunchurch DS F2 - Extend to Magnetewan | N.D.C.2.02 | 7374 | 205 | LINES | UNPLND |  |  | Yes |  |  |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23063 | West Bay DS #2 & Line Work | N.D.C.2.02 | 7700 | 203 | PROJECT DELIVERY | AIP005381 | AIP005381 | AIP005381 | No | AIP005381 | Manitou Lake DS & Line Work | ISD-SR-13 | Life Cycle Optimization & Operational Efficiency Projects | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Gert.Alikaj@HydroOne.com | System Renewal | Northern | Not Required | 02 - Expectation (no agreement) | In Progress | Project | EMPP ACCP | Executing | Executing |  | 833808.3066 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 911977.8353 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -78169.5287 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -8.5714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42690 | 43129 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
23064 | Pelham DS F2 Feeder Conversion | N.D.C.2.02 | 7374 | 205 | LINES | AIP005266 |  | AIP005266 | Yes | AIP005266 |  |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | [6 empty] | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23065 | LCC/LMC OS Upgrade | N.T.C.1.19 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Protection Control & Metering Equip | Miroslav.Kostic@HydroOne.com | [6 empty] | Program | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23066 | RTU D20M++ End of Life | N.T.C.1.19 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Protection Control & Metering Equip | Miroslav.Kostic@HydroOne.com | [6 empty] | Program | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23067 | Margach DS F1 offload stepdown transformer SD3936 | N.D.C.2.02 | 7374 | 205 | LINES | AIP005384 | AIP005384 | AIP005384 | No | AIP005384 | Margach DS F1 - offload stepdown transformer SD3936 | ISD-SS-02 | System Upgrades Driven by Load Growth | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Cecilia.Pang@HydroOne.com | System Service | 0 | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 917189.1372 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1042260.3832 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -125071.246 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42978 | 43404 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
23071 | Elk Lake Voltage Conversion | N.D.C.2.02 | 7374 | 205 | LINES | UNPLND |  |  | Yes |  |  |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23072 | Hanmer TS Feeder Development | N.D.C.2.02 | 7374 | 205 | LINES | AIP005426 | AIP005426 | AIP005426 | No | AIP005426 | Hanmer TS Feeder Development | ISD-SR-13 | Life Cycle Optimization & Operational Efficiency Projects | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Gert.Alikaj@HydroOne.com | System Renewal | 0 | Not Required | 03 - None (default) | Not Required | Project | HOLD | Short Term Planning | Short Term Planning |  | 1000808.881 | 200176.9039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000808.881 | 400353.8078 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -200176.9039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -14.2857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43008 | 43497 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
23073 | Hanmer TS DESN Capital Contribution | N.D.C.2.02 | 7700 | 203 | PROJECT DELIVERY | AIP005423 | AIP005423 | AIP005423 | No | AIP005423 | Hanmer TS Capital Contribution | ISD-GP-26 | Hanmer TS Capital Contribution | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Gert.Alikaj@HydroOne.com | General Plant | 0 | Not Required | 03 - None (default) | Not Required | Project | init | Short Term Planning | Short Term Planning |  | 3402750.1953 | 300265.3559 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3402750.1953 | 300265.3559 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42885 | 43497 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
23074 | Mar DS | N.D.C.2.02 | 7700 | 203 | PROJECT DELIVERY | AIP000183 |  | AIP000183 | Yes | AIP000183 | (1) System upgrade driven by load growth | ISD-SS-02 | System Upgrades Driven by Load Growth | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Michael.Medeiros@HydroOne.com | System Service | 0 | 0 | 03 - None (default) | Not Required | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23075 | Snow Valley DS & Line Work | N.D.C.2.02 | 7700 | 203 | PROJECT DELIVERY | AIP005434 | AIP005434 | AIP005434 | No | AIP005434 | Midhurst Wilson DS | ISD-SS-02 | System Upgrades Driven by Load Growth | System Capability Reinforcement | lyla.garzouzi@hydroone.com | michael.sullivan@hydroone.com | System Service | 0 | Not Required | 03 - None (default) | Not Required | Project | ACCP EMPP | Executing | Executing |  | 669684.6073 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 679882.8498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -10198.2425 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42778 | 43128 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
23077 | Mar DS Red Bay Line Upgrade | N.D.C.2.02 | 7374 | 205 | LINES | UNPLND |  |  | Yes |  |  |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23078 | Point Au Baril DS F2 Submarine Cable Upgrade | N.D.C.2.02 | 7374 | 205 | LINES | UNPLND |  |  | Yes |  |  |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23080 | Kirkland Lake Voltage Conversion - Stage 1 | N.D.C.2.02 | 7700 | 203 | PROJECT DELIVERY | AIP005639 | AIP005639 | AIP005639 | No | AIP005639 | Town of Kirkland Lake Voltage Conversion-Part 1 | ISD-SS-02 | System Upgrades Driven by Load Growth | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Gert.Alikaj@HydroOne.com | System Service | 0 | 0 | 03 - None (default) | 0 | Project | DETL ACTN | Short Term Planning | Short Term Planning |  | 4050406.8791 | 784733.4887 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4565823.5529 | 889886.4364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -515416.6738 | -105152.9476 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -11.3747 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43099 | 43465 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
23085 | Lorne Park TS M4 ID22470-TX C2-5 Biogas Handling | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23090 | Mattawa DS Connection | N.T.C.2.11 | 7700 | 203 | PROJECT DELIVERY | AIP005526 | AIP005526 | AIP005526 | No | AIP005526 | Mattawa DS Connection | 0 |  | Load Customer Connection | Robert.Reinmuller@HydroOne.com | Kirpal.Bahra@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACCP EMPP | Executing | Executing |  | 85453.5338 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 259933.5338 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2.7756e-11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -174480 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43218 | [13 empty] | FALSE |  | 0 | 0 | Alternative 1
23091 | Riverdale TS HVAC Improvements 2013 | N.T.C.1.28 | 7236 | 215 | FACILITIES & REAL ESTATE | UNPLND |  |  | Yes |  |  |  |  | Transmission Site Facilities | cindy.copp@hydroone.com | [6 empty] | Project | EMPP AWRD | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23092 | Satellite Phones for security | N.C.C.1.55 | 838 | 212 | INFO SOLUTIONS DIVISION | UNPLND |  |  | Yes |  |  |  |  | MFA - Real Estate Facilities | cindy.copp@hydroone.com | [6 empty] | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23093 | Hazard Hamlet for H&S | N.C.C.1.55 | 7803 | 209 | HEALTH, SAFETY & ENV | UNPLND |  |  | Yes |  |  |  |  | MFA - Real Estate Facilities | cindy.copp@hydroone.com | [6 empty] | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23094 | Claireville TS HVAC Upgrade 2013 | N.T.C.1.28 | 7236 | 215 | FACILITIES & REAL ESTATE | UNPLND |  |  | Yes |  |  |  |  | Transmission Site Facilities | cindy.copp@hydroone.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23095 | Grid Control Network Sustainment | N.T.C.3.08 | 7700 | 203 | PROJECT DELIVERY | AIP000985 |  | AIP000985 | Yes | AIP000985 | Local PSMC Network Sustainment |  |  | Integrating Operating Infrastructure | Miroslav.Kostic@HydroOne.com | Andrew.Webb@HydroOne.com | General Plant | 0 | 0 | 02 - Expectation (no agreement) | 0 | Program | init | Short Term Planning | Short Term Planning | # of sites/upgrades | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23101 | Smithfield DS F1 Development | N.D.C.2.02 | 7374 | 205 | LINES | AIP005404 |  | AIP005404 | Yes | AIP005404 |  |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | [6 empty] | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23110 | Recloser Retrofit Project - Tx | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | [6 empty] | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23111 | Martindale TS T21 & T23 Replacement | N.T.C.1.17 | 7700 | 203 | PROJECT DELIVERY | AIP000560 |  | AIP000560 | Yes | AIP000560 | Replace EOL Large Transformers Program |  |  | Power Transformers | James.Mardegan@HydroOne.com | peter.zhao@hydroone.com | System Renewal | 0 | 0 | 03 - None (default) | 0 | Program | init | Short Term Planning | Short Term Planning | # of Transformers | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23115 | Itron Sentinel 16S meter replacements | N.D.C.1.09 | 7374 | 205 | LINES | UNPLND |  |  | Yes |  |  |  |  | Metering | Peter.Mitskos@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23130 | Fleet Telematics -TWE | N.C.C.1.30 | 7818 | 219 | FLEET | AIP005359 |  | AIP005359 | Yes | AIP005359 |  |  |  | Fleet | robert.berardi@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23131 | Brant M14 St George Loop Feed | N.D.C.2.02 | 7374 | 205 | LINES | AIP005269 |  | AIP005269 | Yes | AIP005269 |  |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | [6 empty] | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23136 | Customer Experience Initiatives - Dx | N.D.M.4.10 | 1144 | 220 | STRATEGY & CONSERV | UNPLND |  |  | Yes | [12 empty] | Program | EMPP init | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23137 | HV UG Cable - Replace H7L/H11L | N.T.C.1.15 | 7700 | 203 | PROJECT DELIVERY | AIP005225 | AIP005225 | AIP005225 | No | AIP005225 | HV UG Cable - Replace H7L/H11L | 0 |  | U/G Lines Cable Sys & Comp Refurb & Repl | hassan.hamzeh@hydroone.com | Tyler.Wales@HydroOne.com | System Renewal | Greater Toronto Area | Not Required | 03 - None (default) | Required | Project | ACCP EMPP | Executing | Executing |  | 27305187.8023 | 243106.8918 | 0.039313 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27442399.8013 | 244328.5345 | 0.03951 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -137211.999 | -1221.6427 | -0.00019755 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1.5028 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43434 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Alternative 1
23138 | Glengarry DS SSI | N.D.C.2.02 | 7374 | 205 | LINES | AIP000183A |  | AIP000183 | Yes | AIP000183 | (1) System upgrade driven by load growth |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Michael.Medeiros@HydroOne.com | System Service | 0 | 0 | 03 - None (default) | Not Required | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23139 | Kingsville TS M4 ID22910-Tx Mucci Farms | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23140 | Customer Experience Initiatives - Tx | N.T.M.4.10 | 1144 | 220 | STRATEGY & CONSERV | UNPLND |  |  | Yes | [12 empty] | Program | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23141 | South Huron-Raise L7S for Goshen Wind-Recoverable | N.T.C.1.14 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Third Party Transmission System Modifications | john.boldt@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23142 | Kingsville TS M4 ID22920-Tx Agriville Farms | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23143 | Kingsville TS M4 ID22920-Dx Agriville Farms | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000199 |  | AIP000199 | Yes | AIP000199 | Large Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23144 | NERC CIP Version 5 - OPEX | N.T.M.1.29 | 4514 | 212 | INFO SOLUTIONS DIVISION | AIP005306 |  | AIP005306 | Yes | AIP005306 |  |  |  | NERC Cyber Security Compliance Readiness | lincoln.frost-hunt@hydroone.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23146 | OMA for Teldig Project | N.C.M.2.60 | 4339 | 212 | INFO SOLUTIONS DIVISION | AIP000105 |  | AIP000105 | Yes | AIP000105 |  |  |  | IT-Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23147 | NERC CIP Version 5 - CAPEX | N.T.C.1.29 | 4514 | 212 | INFO SOLUTIONS DIVISION | AIP000680 |  | AIP000680 | Yes | AIP000680 |  |  |  | NERC Cyber Security Compliance Readiness | lincoln.frost-hunt@hydroone.com | [6 empty] | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23148 | St. Andrews TS: Modify M9/M10 P&C (Imperial Oil) | N.T.C.2.11 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Load Customer Connection | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | DETL HOLD | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23150 | Timmins Helipad Concrete Apron 2014 | N.T.C.1.28 | 7236 | 215 | FACILITIES & REAL ESTATE | UNPLND |  |  | Yes |  |  |  |  | Transmission Site Facilities | cindy.copp@hydroone.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23159 | Mattawa DS 115 kV Line Connection - Payment to Tx | N.D.C.2.02 | 7700 | 203 | PROJECT DELIVERY | AIP005414 | AIP005414 | AIP005414 | No | AIP005414 | Mattawa DS 115 kV Line Connection - Payment to Tx |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Richard.Shannon@HydroOne.com | General Plant | 0 | Not Required | 03 - None (default) | Complete | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42215 | 42825 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
23160 | Kingsville TS M4 ID22910-Dx Mucci Farms | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000199 |  | AIP000199 | Yes | AIP000199 | Large Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23166 | Commerce Way New Feeder Extension | N.D.C.2.02 | 7374 | 205 | LINES | AIP000183A |  | AIP000183 | Yes | AIP000183 | (1) System upgrade driven by load growth |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Michael.Medeiros@HydroOne.com | System Service | 0 | 0 | 03 - None (default) | Not Required | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23167 | Windsor - DRIC Dx Relocation_Recoverable | N.D.C.1.03 | 7374 | 205 | LINES | AIP000494 |  | AIP000494 | Yes | AIP000494 | Detroit River International Crossing Work |  |  | Joint Use and Relocations | john.boldt@HydroOne.com | Gian.Minichini@HydroOne.com | System Renewal | Western | 0 | 01 - Agreement (current/future) | 0 | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23168 | CUSTOMER EXPERIENCE - SURVEYS | N.D.M.4.01 | 4028 | 220 | STRATEGY & CONSERV | AIP000375 |  | AIP000375 | Yes | AIP000375 | Contact Handling - Third Party Support |  |  | Customer Care Services Dx | Imran.Merali@HydroOne.com | Imran.Merali@HydroOne.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | init | Short Term Planning | Short Term Planning | 202-D504004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23170 | Frontenac TS EOL Stat Reinvstmt proj | N.T.C.1.44 | 7700 | 203 | PROJECT DELIVERY | AIP005168 | AIP005168 | AIP005168 | No | AIP005168 | Frontenac TS BULK: Component Replacement | 0 |  | Eastern Zone Station/Yard Investments | James.Mardegan@HydroOne.com | Fred.Kouhdani@HydroOne.com | System Renewal | Eastern | Not Required | 03 - None (default) | Not Required | Project | ACTN EMPP | Executing | Executing |  | 581930.6401 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 625731.871 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -43801.231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -14.5938 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43220 | [13 empty] | FALSE |  | 1 | 0 | Component replacement
23177 | Sarnia Sott TS Roor Replacement 2014 | N.T.C.1.28 | 7236 | 215 | FACILITIES & REAL ESTATE | UNPLND |  |  | Yes |  |  |  |  | Transmission Site Facilities | cindy.copp@hydroone.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23178 | Wallaceburg TS Roof Replacement 2014 | N.T.C.1.28 | 7236 | 215 | FACILITIES & REAL ESTATE | UNPLND |  |  | Yes |  |  |  |  | Transmission Site Facilities | cindy.copp@hydroone.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23179 | Buchanan TS Roof Replacement 2014 | N.T.C.1.28 | 7236 | 215 | FACILITIES & REAL ESTATE | UNPLND |  |  | Yes |  |  |  |  | Transmission Site Facilities | cindy.copp@hydroone.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23182 | Grand Bend East DS Monitoring & New Fdr Position | N.D.C.2.02 | 7700 | 203 | PROJECT DELIVERY | AIP005388 |  | AIP005388 | Yes | AIP005388 |  |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23183 | CMS Room 080 Refurbishment Project- Capital Funds | N.T.C.1.21 | 7370 | 206 | TX LINES AND STATIONS | UNPLND |  |  | Yes |  |  |  |  | Infrastructure | James.Mardegan@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23184 | OGCC Storage Area Network Upgrade | N.C.C.3.01 | 4514 | 212 | INFO SOLUTIONS DIVISION | AIP000075 |  | AIP000075 | Yes | AIP000075 |  |  |  | Common Oper Infrast & Control Facilities | Godfrey.Holder@HydroOne.com | [6 empty] | Project | EMPP AWRD | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23185 | Edgeware TS Roof Replacement 2014 | N.T.C.1.28 | 7236 | 215 | FACILITIES & REAL ESTATE | UNPLND |  |  | Yes |  |  |  |  | Transmission Site Facilities | cindy.copp@hydroone.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23186 | TransCanada-Pump Stn (Cancel) | N.T.C.2.11 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Load Customer Connection | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23195 | Aylmer TS M1 ID21470 TX IGPC Cogeneration Project | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23200 | Edgeware TS- M7- ID24300-Dx- Formet 800 kW CHP Sys | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000199 |  | AIP000199 | Yes | AIP000199 | Large Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23201 | EdgewareTS-M7- ID24300- Tx- Formet 800 kW CHP Sys | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23203 | Timmins TS M8 - 1 km Conductor Upgrade | N.D.C.2.02 | 7374 | 205 | LINES | AIP000183A |  | AIP000183 | Yes | AIP000183 | (1) System upgrade driven by load growth |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Michael.Medeiros@HydroOne.com | System Service | 0 | 0 | 03 - None (default) | Not Required | Project | EMPP ACTN | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23204 | Clarke TS M2 Extension_Ilderton | N.D.C.2.02 | 7374 | 205 | LINES | AIP005242 |  | AIP005242 | Yes | AIP005242 |  |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | [6 empty] | Project | EMPP HOLD | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23205 | Integration Playbook | N.D.M.9.01 | 4465 | 216 | BUSINESS INTEGRATION | UNPLND |  |  | Yes | [12 empty] | Program | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23206 | Norfolk Integration Costs | N.D.M.9.01 | 4465 | 216 | BUSINESS INTEGRATION | UNPLND |  |  | Yes | [12 empty] | Program | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23209 | Arnprior Area Study Upgrades | N.D.C.2.02 | 7700 | 203 | PROJECT DELIVERY | AIP005397 | AIP005397 | AIP005397 | No | AIP005397 | Arnprior Area Study Upgrades |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Muhammad.Sabir@HydroOne.com | System Service | Eastern | Not Required | 03 - None (default) | Not Required | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42466 | 43039 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
23210 | Commerce WayTS M1 ID22500 DX Gunn's Hill Wind Farm | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000199 |  | AIP000199 | Yes | AIP000199 | Large Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23211 | Commerce WayTS M1 ID22500 TX Gunn's Hill Wind Farm | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | EMPP ACTN | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23219 | Trinity UPS upgrade 05 South HVAC 2014 | N.C.C.1.50 | 7236 | 215 | FACILITIES & REAL ESTATE | UNPLND |  |  | Yes |  |  |  |  | Real Estate Facilities | cindy.copp@hydroone.com | [6 empty] | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23222 | Malden TS-M8-ID689-OM&A-PV mitigation | N.D.M.2.03 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Distributed Generation Connections | ryan.boudreau@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23224 | Almonte TS T3/T4 | N.T.C.1.44 | 7700 | 203 | PROJECT DELIVERY | AIP005129 |  | AIP005129 | Yes | AIP005129 |  |  |  | Eastern Zone Station/Yard Investments | James.Mardegan@HydroOne.com | [6 empty] | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23225 | CMS Room 080 Refurbishment Project- OM&A Funds | N.T.M.1.16 | 7370 | 206 | TX LINES AND STATIONS | UNPLND |  |  | Yes |  |  |  |  | Power Equipment | Mike.Tanaskovic@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23228 | Richview Manby Transmission Reinforcement - Line | N.T.C.2.02 | 7700 | 203 | PROJECT DELIVERY | AIP005296 | AIP005296 | AIP005296 | No | AIP005296 | Southwest GTA Transmission Reinforcement | SS-15 | Southwest GTA Transmission Reinforcement | Local Area Supply | Robert.Reinmuller@HydroOne.com | Eva.Ping@HydroOne.com | System Service | 0 | Required | 03 - None (default) | Required | Project | BEST ACTN | Short Term Planning | Short Term Planning |  | 1177948.1235 | 4918778.1831 | 9763456.4796 | 4088646.1946 | 0 | 0 | 0 | 0 | 0 | 0 | 1177948.1235 | 4918778.1831 | 9763456.4796 | 4088646.1946 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44042 | 44347 | True |  | True | Ontario Resource and Transmission Assessment Criteria | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Southwest GTA Transmission Reinforcement
23231 | Rainy River Gold Project | N.T.C.2.11 | 7700 | 203 | PROJECT DELIVERY | AIP005334 |  | AIP005334 | Yes | AIP005334 |  |  |  | Load Customer Connection | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | EMPP ACTN | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23233 | Allanburg TS M5 feeder construction | N.D.C.2.02 | 7374 | 205 | LINES | AIP005383 | AIP005383 | AIP005383 | No | AIP005383 | Allanburg TS M5 feeder | ISD-SS-02 | System Upgrades Driven by Load Growth | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Mark.VanTol@hydroone.com | System Service | Hamilton Niagara | 0 | 03 - None (default) | 0 | Project | ACTN EMPP | Executing | Executing |  | 548339.1026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 623112.6166 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -74773.514 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42807 | 43144 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
23237 | Hinchinbrooke SS BULK | N.T.C.1.44 | 7700 | 203 | PROJECT DELIVERY | AIP005115 | AIP005115 | AIP005115 | No | AIP005115 | Hinchinbrooke SS BULK: Component Replacement | 0 |  | Eastern Zone Station/Yard Investments | James.Mardegan@HydroOne.com | Fred.Kouhdani@HydroOne.com | System Renewal | Eastern | 0 | 03 - None (default) | 0 | Project | ACCP EMPP | Executing | Executing |  | 1161335.5697 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1941919.3001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -780583.7304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -40.1965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43434 | [13 empty] | FALSE |  | 0 | 0 | Component Replacement
23239 | St.Isidore TS T3/T4 | N.T.C.1.44 | 7700 | 203 | PROJECT DELIVERY | AIP005109 | AIP005109 | AIP005109 | No | AIP005109 | St.Isidore TS T3/T4: Transformer, PCT, and Component replacement | 0 |  | Eastern Zone Station/Yard Investments | James.Mardegan@HydroOne.com | Fred.Kouhdani@HydroOne.com | System Renewal | Eastern | 0 | 03 - None (default) | 0 | Project | EMPP ACTN | Executing | Executing |  | 664639.7011 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1609295.1711 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -944655.4699 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -58.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43074 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Component Replacement
23240 | Lauzon TS T5/T6; PCT & Component Replacement | N.T.C.1.40 | 7700 | 203 | PROJECT DELIVERY | AIP005124 | AIP005124 | AIP005124 | No | AIP005124 | Lauzon TS T5/T6; PCT & Component Replacement | 0 |  | Western Zone Station/Yard Investments | James.Mardegan@HydroOne.com | mark.truchanowicz@hydroone.com | System Renewal | Western | 0 | 03 - None (default) | 0 | Project | ACTN EMPP | Executing | Executing |  | 738389.4509 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 738389.4509 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43084 | [13 empty] | FALSE |  | 0 | 0 | Alternative 1
23241 | Buchanan TS BULK | N.T.C.1.40 | 7700 | 203 | PROJECT DELIVERY | AIP005128 | AIP005128 | AIP005128 | No | AIP005128 | Buchanan TS BULK; Component Replacement | 0 |  | Western Zone Station/Yard Investments | James.Mardegan@HydroOne.com | mark.truchanowicz@hydroone.com | System Renewal | Western | Not Required | 03 - None (default) | Not Required | Project | ACTN EMPP | Executing | Executing |  | 412450.4994 | 0 | 0.12777 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 412450.4994 | 0 | 0.12777 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43080 | [13 empty] | FALSE |  | 0 | 0 | Alternative 1
23242 | Ellesmere TS T3/T4; PCT & Component Replacement | N.T.C.1.42 | 7700 | 203 | PROJECT DELIVERY | AIP005141 |  | AIP005141 | Yes | AIP005141 |  |  |  | Central Zone Station/Yard Investments | James.Mardegan@HydroOne.com | [6 empty] | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23243 | Brant TS T1/T2 | N.T.C.1.41 | 7700 | 203 | PROJECT DELIVERY | AIP005117 |  | AIP005117 | Yes | AIP005117 |  |  |  | Hamilton/Niagara Zone Station/Yard Investments | James.Mardegan@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23245 | Buttonville TS T3/T4; PCT & Component Replacement | N.T.C.1.42 | 7700 | 203 | PROJECT DELIVERY | AIP005240 |  | AIP005240 | Yes | AIP005240 |  |  |  | Central Zone Station/Yard Investments | James.Mardegan@HydroOne.com | [6 empty] | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23246 | Longueuil TS T3/T4 | N.T.C.1.44 | 7700 | 203 | PROJECT DELIVERY | AIP005142 |  | AIP005142 | Yes | AIP005142 |  |  |  | Eastern Zone Station/Yard Investments | James.Mardegan@HydroOne.com | [6 empty] | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23247 | Cumberland TS T3/T4 | N.T.C.1.41 | 7700 | 203 | PROJECT DELIVERY | AIP005139 |  | AIP005139 | Yes | AIP005139 |  |  |  | Hamilton/Niagara Zone Station/Yard Investments | James.Mardegan@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23248 | Leaside TS BULK; Component Replacement | N.T.C.1.43 | 7700 | 203 | PROJECT DELIVERY | AIP005147 | AIP005147 | AIP005147 | No | AIP005147 | Leaside TS BULK; Component Replacement | SR-07 | Protection and Automation Replacement Projects | Greater Toronto Area Zone Station/Yard Investments | James.Mardegan@HydroOne.com | michael.xavier@hydroone.com | System Renewal | Greater Toronto Area | Not Required | 03 - None (default) | 0 | Project | EMPP ACCP | Executing | Executing |  | 5578665.6022 | 1794264.9782 | 1091.1221 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6080824.5625 | 3806033.7216 | 1091.1221 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -502158.9603 | -2011768.7434 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -25.4598 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43800 | [13 empty] | FALSE |  | 0 | 0 | Component Replacement
23249 | Nepean TS T3/T4 | N.T.C.1.44 | 7700 | 203 | PROJECT DELIVERY | AIP005135 |  | AIP005135 | Yes | AIP005135 |  |  |  | Eastern Zone Station/Yard Investments | James.Mardegan@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23250 | Birch TS: Component Replacement | N.T.C.1.45 | 7700 | 203 | PROJECT DELIVERY | AIP005228 | AIP005228 | AIP005228 | No | AIP005228 | Birch TS: Component Replacement | SR-04 | Bulk Station Switchgear and Ancillary Equipment Replacement Projects | Northern Zone Station/Yard Investments | James.Mardegan@HydroOne.com | Donald.Mastrangelo@HydroOne.com | System Renewal | Northern | Not Required | 03 - None (default) | Required | Project | ACCP EMPP | Executing | Executing |  | 4514544.1987 | 3923692.403 | 0.088453 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4854348.6007 | 4219024.0893 | 0.095111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -339804.4021 | -295331.6863 | -0.0066578 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -10.1502 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43664 | [13 empty] | FALSE |  | 0 | 0 | Component Replacement
23254 | Timminco Idle Line Removal - Recoverable | N.T.C.1.14 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Third Party Transmission System Modifications | john.boldt@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23260 | Moosonee SC Purchase 2014 (1 Keewatin Drive) | N.D.C.1.50 | 7236 | 215 | FACILITIES & REAL ESTATE | UNPLND |  |  | Yes |  |  |  |  | Real Estate Facilities | cindy.copp@hydroone.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23261 | Carlisle DS Transformer Upgrade | N.D.C.2.02 | 7700 | 203 | PROJECT DELIVERY | AIP005268 | AIP005268 | AIP005268 | No | AIP005268 | Carlisle DS Transformer Upgrade | ISD-SS-02 | System Upgrades Driven by Load Growth | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Mark.VanTol@hydroone.com | System Service | Western | 0 | 03 - None (default) | 0 | Project | DETL LLTM EXTR | Short Term Planning | Short Term Planning |  | 823665.709 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 823665.709 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43084 | 43420 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
23267 | Keith TS Roof Replacement 2014 | N.T.C.1.28 | 7236 | 215 | FACILITIES & REAL ESTATE | UNPLND |  |  | Yes |  |  |  |  | Transmission Site Facilities | cindy.copp@hydroone.com | [6 empty] | Project | EMPP AWRD | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23268 | Physical Security | N.T.C.1.29 | 7700 | 203 | PROJECT DELIVERY | AIP005290 |  | AIP005290 | Yes | AIP005290 |  |  |  | NERC Cyber Security Compliance Readiness | lincoln.frost-hunt@hydroone.com | [6 empty] | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23271 | Riverdale JCT x Overbrook TS: Build new A6R Tap | N.T.C.2.02 | 7700 | 203 | PROJECT DELIVERY | AIP005300 | AIP005300 | AIP005300 | No | AIP005300 | Riverdale JCT x Overbrook TS: Build new A6R Tap | 0 |  | Local Area Supply | Robert.Reinmuller@HydroOne.com | Jean.Morneau@HydroOne.com | System Service | 0 | TBD | 01 - Agreement (current/future) | Required | Project | ACCP EMPP | Executing | Executing |  | 0 | -603697.1241 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3870362.59 | 1419615.2959 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1.1102e-10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3870362.59 | -2023312.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43616 | True |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Alternative 1
23273 | Stouffville 10th Line DS New T3 & feeders | N.D.C.2.02 | 7700 | 203 | PROJECT DELIVERY | AIP005402 | AIP005402 | AIP005402 | No | AIP005402 | Stouffville 10th Line DS T3 | ISD-SS-02 | System Upgrades Driven by Load Growth | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Dhaval.Patel@hydroone.com | System Service | Central | 0 | 03 - None (default) | 0 | Project | DETL ACTN | Short Term Planning | Short Term Planning |  | 2432280.8055 | 3887971.6178 | 335204.1004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2615355.7049 | 4180614.6428 | 360434.5165 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -183074.8993 | -292643.025 | -25230.4162 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43312 | 43830 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
23274 | Longueuil TS-M24-ID964 & 965-Dx PV mitigation | N.D.M.2.03 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Distributed Generation Connections | ryan.boudreau@HydroOne.com | [6 empty] | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23276 | Storm Management Customer Satisfaction Surveys | N.D.M.3.01 | 4175 | 202 | CUSTOMER CARE SERVICES | AIP005237 | AIP005237 | AIP005237 | No | AIP005237 | Dx Storm Management Customer Satisfaction Surveys |  |  | Operations Contract | Godfrey.Holder@HydroOne.com | william.ilie@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | init EMPP | Executing | Short Term Planning | # of Reports | 100831.2805 | 121293.4429 | 125159.8201 | 128141.5392 | 131656.4564 | 0 | 0 | 0 | 0 | 0 | 100831.2805 | 121293.4429 | 125159.8201 | 128141.5392 | 131656.4564 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200 | 1200 | 1200 | 1200 | 1200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Intermediate
23277 | Magnetometer Installation Project | N.T.C.3.08 | 7700 | 203 | PROJECT DELIVERY | AIP005336 | AIP005336 | AIP005336 | No | AIP005336 | Magnetometer Installation Project | 0 |  | Integrating Operating Infrastructure | Miroslav.Kostic@HydroOne.com | Afshin.Rezaei-Zare@HydroOne.com | General Plant | N/A | Not Required | 03 - None (default) | Not Required | Project | ACCP EMPP | Executing | Executing |  | 378042.1697 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 378042.1697 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43189 | [13 empty] | FALSE |  | 0 | 0 | Magnetometer Installation Project
23278 | MTO Highway 427 Extension at Langstaff-Recoverable | N.T.C.1.14 | 7700 | 203 | PROJECT DELIVERY | AIP005283 |  | AIP005283 | Yes | AIP005283 |  |  |  | Third Party Transmission System Modifications | john.boldt@HydroOne.com | [6 empty] | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23279 | Grand Bend DS F3 Voltage Conversion | N.D.C.2.02 | 7374 | 205 | LINES | AIP005679 | AIP005679 | AIP005679 | No | AIP005679 | Grand Bend DS F3 Voltage Conversion | ISD-SS-02 | System Upgrades Driven by Load Growth | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Jerry.Vo@HydroOne.com | System Service | 0 | 0 | 03 - None (default) | 0 | Project | HOLD DETL | Short Term Planning | Short Term Planning |  | 1398339.1758 | 1010693.1879 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1589021.7907 | 1148514.9862 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -190682.6149 | -137821.7983 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43205 | 43463 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
23280 | Lennox TS 500kV Shunt Reactors | N.T.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP005308 | AIP005308 | AIP005308 | No | AIP005308 | Lennox 500kV Shunt Reactors | SS-02 | Lennox TS: Install 500kV Shunt Reactors | Network Transfer Capability | Robert.Reinmuller@HydroOne.com | Gene.Ng@HydroOne.com | System Service | 0 | Not Required | 03 - None (default) | TBD | Project | DETL AWRD | Short Term Planning | Short Term Planning |  | 1963246.8725 | 23610135.2789 | 19526912.9591 | 3846327.5584 | 0 | 0 | 0 | 0 | 0 | 0 | 1963246.8725 | 23610135.2789 | 19526912.9591 | 3846327.5584 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43371 | 44166 | True | IESO request. | True | IESO market rule requirement for 500kV voltage to be kept below 550kV. | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Alternative 1
23281 | Placeholder for Distance Limitation Mitigation | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000194 | AIP000194 | AIP000194 | No | AIP000194 | Distance Limitation Mitigation Work (E&T) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | Not Required | 03 - None (default) | Not Required | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43100 | 43100 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
23285 | Clearwater Bay voltage conversion Phase 1 of 3 | N.D.C.2.02 | 7374 | 205 | LINES | AIP005263 | AIP005263 | AIP005263 | No | AIP005263 | Clearwater Bay DS F2 (Phase 1 of 3) | ISD-SR-13 | Life Cycle Optimization & Operational Efficiency Projects | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Cecilia.Pang@HydroOne.com | System Renewal | 0 | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 513625.9265 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 583665.8255 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -70039.8991 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43008 | 43404 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
23286 | Lauzon TS DESN2-M26- ID22580- Tx- Manning Pumping | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23287 | 2015-2020 OPA Residential Programs | N.D.M.2.50 | 1144 | 220 | STRATEGY & CONSERV | AIP005313 | AIP005313 | AIP005313 | No | AIP005313 | 2015-2020 OPA Residential Programs |  |  | Conservation and Demand Management | Imran.Merali@HydroOne.com | Imran.Merali@HydroOne.com | System O&M | N/A | 0 | 03 - None (default) | 0 | Program | AWRD EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21883566 | 21665330 | 21406474 | 21406474.04 | 21406474 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -21883566 | -21665330 | -21406474 | -21406474.04 | -21406474 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | 2015-2019 OPA Residential Programs
23288 | 2015-2020 OPA Commercial Programs | N.D.M.2.50 | 1144 | 220 | STRATEGY & CONSERV | AIP005314 | AIP005314 | AIP005314 | No | AIP005314 | 2015-2020 OPA Commercial Programs |  |  | Conservation and Demand Management | Imran.Merali@HydroOne.com | Imran.Merali@HydroOne.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | EMPP AWRD | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19833777 | 18540416.08 | 18804484 | 18804484.04 | 18804484 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -19833777 | -18540416.08 | -18804484 | -18804484.04 | -18804484 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | 2015-2019 OPA Commercial Programs
23289 | 2015-2020 OPA Industrial Programs | N.D.M.2.50 | 1144 | 220 | STRATEGY & CONSERV | AIP005315 | AIP005315 | AIP005315 | No | AIP005315 | 2015-2020 OPA Industrial programs |  |  | Conservation and Demand Management | Imran.Merali@HydroOne.com | Imran.Merali@HydroOne.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | AWRD EMPP | Executing | Short Term Planning |  | 0 | 0 | 1.1002 | 0.98449 | 0.98317 | 0 | 0 | 0 | 0 | 0 | 10547492 | 10547492 | 8747491.9802 | 8747491.9845 | 8747491.9832 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.18e-09 | 1.6341e-09 | 9.8195e-10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -10547492 | -10547492 | -8747490.88 | -8747491 | -8747491 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | 2015-2020 Industrial OPA programs
23290 | Palmerston TS: Station Rebuild | N.T.C.1.40 | 7700 | 203 | PROJECT DELIVERY | AIP005108 | AIP005108 | AIP005108 | No | AIP005108 | Palmerston TS T1/T2/T3; T1,T2,T3, PCT, MVGIS | SR-02 | Station Reinvestment Projects | Western Zone Station/Yard Investments | James.Mardegan@HydroOne.com | mark.truchanowicz@hydroone.com | System Renewal | Western | Not Required | 03 - None (default) | Not Required | Project | ACTN EMPP | Executing | Executing |  | 11178562.9625 | 5100402.2526 | 0.0098282 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12091226.1747 | 5515670.4974 | 0.010568 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -841397.2122 | -383901.2448 | -0.00073975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -7.6186 | 7 | -71266 | -31367 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43571 | [13 empty] | FALSE |  | 1 | 1 | Alternative 1
23293 | Lauzon TS DESN2-M26- ID22580- Dx- Manning Pumping | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000199 |  | AIP000199 | Yes | AIP000199 | Large Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23294 | Sturgeon Falls DS - F2 ID24720 - Dx AGRIS 12 | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000199 |  | AIP000199 | Yes | AIP000199 | Large Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23295 | 2015-2020 OPA Low Icome Program | N.D.M.2.50 | 1144 | 220 | STRATEGY & CONSERV | AIP005316 | AIP005316 | AIP005316 | No | AIP005316 | 2015-2020 OPA Low Income Programs |  |  | Conservation and Demand Management | Imran.Merali@HydroOne.com | Imran.Merali@HydroOne.com | System O&M | 0 | 0 | 01 - Agreement (current/future) | 0 | Program | EMPP AWRD | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1864851 | 1667794 | 1507639 | 1507639 | 1507638.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1864851 | -1667794 | -1507639 | -1507639 | -1507638.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | 2015-2020 OPA Low income programs
23296 | Foots Bay DS F1 Line Upgrade - Muskoka Rd 38 | N.D.C.2.02 | 7374 | 205 | LINES | AIP005234 |  | AIP005234 | Yes | AIP005234 |  |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | [6 empty] | Project | EMPP HOLD | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23297 | Ancaster West DS Transformer Upgrade | N.D.C.2.02 | 7700 | 203 | PROJECT DELIVERY | AIP005392 | AIP005392 | AIP005392 | No | AIP005392 | Ancaster West DS Upgrade | ISD-SS-02 | System Upgrades Driven by Load Growth | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Mark.VanTol@hydroone.com | System Service | Western | 0 | 03 - None (default) | 0 | Project | DETL init | Short Term Planning | Short Term Planning |  | 0 | 0 | 100927.9832 | 515020.4544 | 1420421.0518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 108524.7132 | 553785.4349 | 1527334.4643 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -7596.7299 | -38764.9804 | -106913.4125 | 0 | 0 | 0 | 0 | 0 | -7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44498 | 44865 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
23299 | Chesters Corners DS-F3-ID24060-Dx-AGRIS Solar 4 | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000199 |  | AIP000199 | Yes | AIP000199 | Large Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23300 | HV UG Cable - Damage Claims | N.T.C.1.15 | 7370 | 206 | TX LINES AND STATIONS | AIP005324 | AIP005324 | AIP005324 | No | AIP005324 | HV UG Cable - Damage Claims | 0 |  | U/G Lines Cable Sys & Comp Refurb & Repl | hassan.hamzeh@hydroone.com | Tyler.Wales@HydroOne.com | System Renewal | 0 | 0 | 03 - None (default) | 0 | Program | AWRD EMPP | Executing | Short Term Planning | Number of Repairs | -1522.8244 | -1548.1304 | -1565.9795 | -1578.1603 | -1590.1656 | -1608.0098 | 0 | 0 | 0 | 0 | 304769.5232 | 310870.0901 | 317100.6713 | 323461.8693 | 329950.8036 | 336563.8298 | 0 | 0 | 0 | 0 | 7.6524 | 7.7795 | 7.8692 | 7.9305 | 7.9908 | 8.0805 | 0 | 0 | 0 | 0 | -0.5 | 0.5 | -306300 | -312426 | -318674.52 | -325047.96 | -331548.96 | -338179.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Asset Optimal
23301 | Picton TS M5 ID24790 Dx AGRIS Solar Garden 15 | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000195 |  | AIP000195 | Yes | AIP000195 | Small Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23302 | Picton TS M5 ID24790 Tx-AGRIS Solar Garden 15 | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23303 | Leamington TS - capital contribution | N.D.C.2.02 | 7700 | 203 | PROJECT DELIVERY | AIP005319 | AIP005319 | AIP005319 | No | AIP005319 | Leamington TS Capital Contribution to Tx | ISD-GP-25 | Leamington TS Capital Contribution | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Alexander.Hamlyn@HydroOne.com | General Plant | Western | Required | 03 - None (default) | Required | Project | ACTN EMPP | Executing | Executing |  | 2169207.1422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6668791.0922 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.4409e-10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4499583.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42521 | 43220 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
23304 | Leamington TS Feeder Development | N.D.C.2.02 | 7374 | 205 | LINES | AIP005428 | AIP005428 | AIP005428 | No | AIP005428 | Leamington TS Feeder Development | ISD-SS-02 | System Upgrades Driven by Load Growth | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Alexander.Hamlyn@HydroOne.com | System Service | Western | In Progress | 01 - Agreement (current/future) | TBD | Project | ACTN EMPP | Executing | Executing |  | 2833296.6174 | 900796.1077 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5987100.6827 | 1000884.5641 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -314810.7353 | -100088.4564 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -10 | 10 | -2838993.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42781 | 43646 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
23305 | Chesters Corners DS-F3-ID24060-Tx-AGRIS Solar 4 | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23307 | Trafalgar TS - Replace T15 and T15 'B' protection | N.T.C.1.17 | 7700 | 203 | PROJECT DELIVERY | AIP000554 |  | AIP000554 | Yes | AIP000554 | Demand Capital - Power Transformers |  |  | Power Transformers | James.Mardegan@HydroOne.com | peter.zhao@hydroone.com | System Renewal | N/A | 0 | 03 - None (default) | 0 | Program | AWRD EMPP | Executing | Short Term Planning | # of Transformers | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23308 | Allanburg TS M6 Line Upgrade | N.D.C.2.02 | 7374 | 205 | LINES | AIP005270 |  | AIP005270 | Yes | AIP005270 |  |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | [6 empty] | Project | DETL ACTN | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23309 | Striker HVDS F2 ID25200 Dx Solvation-F | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000195 |  | AIP000195 | Yes | AIP000195 | Small Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23310 | Picton TS M5 ID24780 DX Agris Solar Garden 11 | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000195 |  | AIP000195 | Yes | AIP000195 | Small Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23311 | Picton TS M5 ID24780 Tx-AGRIS Solar Garden 11 | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23312 | To Be Deleted - John TS HV/LV Station Rebuild | N.T.C.1.43 | 7700 | 203 | PROJECT DELIVERY | AIP000421 |  | AIP000421 | Yes | AIP000421 | John TS: HV/LV Station Rebuild |  |  | Greater Toronto Area Zone Station/Yard Investments | James.Mardegan@HydroOne.com | michael.xavier@hydroone.com | System Renewal | Greater Toronto Area | TBD | 01 - Agreement (current/future) | Required | Program | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23313 | Sturgeon Falls DS F2 ID24660-DX FRITZ Solar 32 | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000199 |  | AIP000199 | Yes | AIP000199 | Large Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23314 | Sturgeon Falls DS F2 ID24670-DX FRITZ Solar 31 | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000199 |  | AIP000199 | Yes | AIP000199 | Large Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23315 | Sturgeon Falls DS - F2 ID24720- Tx AGRIS 12 | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | EMPP ACTN | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23316 | Sturgeon Falls DS - F2 ID24830 - Dx AGRIS 13 | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000199 |  | AIP000199 | Yes | AIP000199 | Large Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23317 | Sturgeon Falls DS - F2 ID24830- Tx AGRIS 13 | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23318 | Chesters Corners DS-F3-ID23540-Dx-AGRIS Solar 1 | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000199 |  | AIP000199 | Yes | AIP000199 | Large Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23319 | Chesters Corners DS-F3-ID23540-Tx-AGRIS Solar 1 | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23320 | Sturgeon Falls DS F2 ID24660-TX FRITZ Solar 32 | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23321 | Sturgeon Falls DS F2 ID24670-TX FRITZ Solar 31 | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23322 | Tafalgar TS Well Tank 2014 | N.T.C.1.28 | 7236 | 215 | FACILITIES & REAL ESTATE | UNPLND |  |  | Yes |  |  |  |  | Transmission Site Facilities | cindy.copp@hydroone.com | [6 empty] | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23325 | Coutsville DS-F3-ID24,040-Dx-AGRIS Solar 3 | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000199 |  | AIP000199 | Yes | AIP000199 | Large Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23326 | Coutsville DS-F3-ID24,040-Tx-AGRIS Solar 3 | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23329 | Striker HVDS F2 ID25200 Tx Solvation-F | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23331 | Picton TS M5 ID24800 AGRIS Solar Garden 10 | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000195 |  | AIP000195 | Yes | AIP000195 | Small Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23332 | Picton TS M5 ID24800 Tx AGRIS Solar Garden 10 | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23333 | Picton TS M5 ID25050 Dx FRITZ Solar 34 | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000195 |  | AIP000195 | Yes | AIP000195 | Small Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23334 | Picton TS M5 ID25050 Tx-FRITZ solar 34 | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23335 | Woodstock Integration Costs | N.D.M.9.01 | 4465 | 216 | BUSINESS INTEGRATION | UNPLND |  |  | Yes | [12 empty] | Program | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23336 | Haldimand Integration Costs | N.D.M.9.01 | 4465 | 216 | BUSINESS INTEGRATION | UNPLND |  |  | Yes | [12 empty] | Program | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23341 | Lennox TS BULK: ABCB component replacement | N.T.C.1.44 | 7700 | 203 | PROJECT DELIVERY | AIP000426 | AIP000426 | AIP000426 | No | AIP000426 | Lennox TS BULK: ABCB component replacement | SR-01 | Air Blast Circuit Breaker Replacement Projects | Eastern Zone Station/Yard Investments | James.Mardegan@HydroOne.com | Fred.Kouhdani@HydroOne.com | System Renewal | Eastern | Not Required | 02 - Expectation (no agreement) | Not Required | Project | ACTN EMPP | Executing | Executing |  | 8827884.6041 | 11979091.5578 | 6258108.5196 | 7201198.2371 | 5607835.9832 | 2017285.3085 | 0 | 0 | 0 | 0 | 9492349.0367 | 12880743.6106 | 6729148.9458 | 7743223.9108 | 6029931.1647 | 2169123.9876 | 0 | 0 | 0 | 0 | -664464.4326 | -901652.0527 | -471040.4262 | -542025.6738 | -422095.1815 | -151838.6791 | 0 | 0 | 0 | 0 | -18.0578 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45111 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Component Replacement
23342 | Stanley TS - Station Upgrade | N.T.C.1.41 | 7700 | 203 | PROJECT DELIVERY | AIP005140 |  | AIP005140 | Yes | AIP005140 |  |  |  | Hamilton/Niagara Zone Station/Yard Investments | James.Mardegan@HydroOne.com | [6 empty] | Program | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23343 | DeCew Falls SS; P&C, Component Replacement | N.T.C.1.41 | 7700 | 203 | PROJECT DELIVERY | AIP005305 |  | AIP005305 | Yes | AIP005305 |  |  |  | Hamilton/Niagara Zone Station/Yard Investments | James.Mardegan@HydroOne.com | [6 empty] | Project | EMPP ACTN | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23344 | Crowland TS: T5, T6 & Component Replacement | N.T.C.1.41 | 7700 | 203 | PROJECT DELIVERY | AIP005175 |  | AIP005175 | Yes | AIP005175 |  |  |  | Hamilton/Niagara Zone Station/Yard Investments | James.Mardegan@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23345 | Striker HVDS F2 ID25150 Dx Solvation-V | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000195 |  | AIP000195 | Yes | AIP000195 | Small Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23346 | Underground Locates | N.C.C.2.10 | 7193 | 227 | CORNERSTONE | UNPLND |  |  | Yes | [12 empty] | Project | EMPP AWRD | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23347 | Dymond TS - M1 - ID25110-DX Gengrowth Garden 04 | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000195 |  | AIP000195 | Yes | AIP000195 | Small Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23348 | Dymond TS - M1 - ID25110-TX Gengrowth Garden 04 | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23349 | Dymond TS - M1 - ID25190-DX Gengrowth Garden 01 | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000195 |  | AIP000195 | Yes | AIP000195 | Small Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23350 | Striker HVDS F2 ID25150 Tx Solvation-V | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23352 | Kingston OC Erosion Control Humps 2014 | N.C.C.1.50 | 7236 | 215 | FACILITIES & REAL ESTATE | UNPLND |  |  | Yes |  |  |  |  | Real Estate Facilities | cindy.copp@hydroone.com | [6 empty] | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23353 | COUTSVILLE DS-F1-ID25140-DX Gengrowth Garden 06 | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000195 |  | AIP000195 | Yes | AIP000195 | Small Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23354 | COUTSVILLE DS-F1-ID25140-TX Gengrowth Garden 06 | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23355 | Bruce A TS New System Service Transformer Connectn | N.T.C.2.11 | 7700 | 203 | PROJECT DELIVERY | unpld |  |  | Yes |  |  |  |  | Load Customer Connection | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23356 | Lennox TS Roof Replacement 2014 | N.T.C.1.28 | 7236 | 215 | FACILITIES & REAL ESTATE | UNPLND |  |  | Yes |  |  |  |  | Transmission Site Facilities | cindy.copp@hydroone.com | [6 empty] | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23357 | Chats Fall SS Roof Replacement 2014 | N.T.C.1.28 | 7236 | 215 | FACILITIES & REAL ESTATE | UNPLND |  |  | Yes |  |  |  |  | Transmission Site Facilities | cindy.copp@hydroone.com | [6 empty] | Project | EMPP AWRD | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23359 | Crystal Falls TS - M2 ID25630 - Dx 08 Guenette | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000195 |  | AIP000195 | Yes | AIP000195 | Small Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23360 | Horning TS; Station Refurbishment | N.T.C.1.41 | 7700 | 203 | PROJECT DELIVERY | AIP005122 | AIP005122 | AIP005122 | No | AIP005122 | Horning TS; Station Refurbishment | 0 |  | Hamilton/Niagara Zone Station/Yard Investments | James.Mardegan@HydroOne.com | mark.truchanowicz@hydroone.com | System Renewal | Hamilton Niagara | Not Required | 03 - None (default) | TBD | Project | EMPP ACCP | Executing | Executing |  | 9775910.4509 | 62781.0591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9973134.7387 | 533515.1246 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -197224.2877 | -470734.0656 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -6.3369 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43447 | [13 empty] | FALSE |  | 0 | 0 | Alternative 1 - PCT-2MVGIS-2Transformers
23361 | Brantford TS: PCT, MV Swyrd and Component Repl. | N.T.C.1.41 | 7700 | 203 | PROJECT DELIVERY | AIP005130 |  | AIP005130 | Yes | AIP005130 |  |  |  | Hamilton/Niagara Zone Station/Yard Investments | James.Mardegan@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23362 | Beck 1 SS 115kV ABCB Replacement | N.T.C.1.41 | 7700 | 203 | PROJECT DELIVERY | AIP005297 | AIP005297 | AIP005297 | No | AIP005297 | Beck 1 SS 115kV ABCB Replacement | SR-01 | Air Blast Circuit Breaker Replacement Projects | Hamilton/Niagara Zone Station/Yard Investments | James.Mardegan@HydroOne.com | Fred.Kouhdani@HydroOne.com | System Renewal | Hamilton Niagara | Not Required | 01 - Agreement (current/future) | TBD | Project | DETL ACTN LLTM | Short Term Planning | Short Term Planning |  | 1954459.3343 | 8262996.5611 | 8290083.0335 | 2062248.9286 | 0 | 0 | 0 | 0 | 0 | 0 | 2101569.1767 | 8884942.5388 | 8914067.7779 | 2217471.9663 | 0 | 0 | 0 | 0 | 0 | 0 | -147109.8424 | -621945.9777 | -623984.7445 | -155223.0376 | 0 | 0 | 0 | 0 | 0 | 0 | -7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43343 | 44545 | False |  | False |  | False |  | False | True | need to be aligned with OPG canal refurbishment project | False | False | False | False | FALSE |  | 0 | 0 | Alternative 1 component replacement
23363 | Nebo TS: Component Replacement | N.T.C.1.41 | 7700 | 203 | PROJECT DELIVERY | AIP005209 |  | AIP005209 | Yes | AIP005209 |  |  |  | Hamilton/Niagara Zone Station/Yard Investments | James.Mardegan@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23364 | Newton TS: T1, T2, PCT & Switchyard Refurbishment | N.T.C.1.41 | 7700 | 203 | PROJECT DELIVERY | AIP005111 | AIP005111 | AIP005111 | No | AIP005111 | Newton TS: T1, T2, PCT & Switchyard Refurbishment | SR-02 | Station Reinvestment Projects | Hamilton/Niagara Zone Station/Yard Investments | James.Mardegan@HydroOne.com | mark.truchanowicz@hydroone.com | System Renewal | Hamilton Niagara | Not Required | 03 - None (default) | TBD | Project | init | Short Term Planning | Short Term Planning |  | 0 | 352893.3355 | 705167.0613 | 3251472.2352 | 13103244.516 | 13174919.726 | 3644259.6 | 0 | 0 | 0 | 0 | 379455.1994 | 758244.1519 | 3496206.7045 | 14089510.2322 | 14166580.3505 | 3918558.72 | 0 | 0 | 0 | 0 | -26561.864 | -53077.0906 | -244734.4693 | -986265.7163 | -991660.6245 | -274299.12 | 0 | 0 | 0 | -7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44214 | 45627 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Switchyard Refurbishment
23365 | Crystal Falls TS - M2 ID25360 - Dx 07 Rivet | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000195 |  | AIP000195 | Yes | AIP000195 | Small Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23366 | Crystal Falls TS - M2 ID25360- Tx 07 Rivet | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23367 | Underground Locates - OMA | N.C.M.2.10 | 7193 | 227 | CORNERSTONE | unpld |  |  | Yes | [12 empty] | Project | EMPP AWRD | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23369 | COUTSVILLE DS-F3-ID25120-DX Gengrowth Garden 05 | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000195 |  | AIP000195 | Yes | AIP000195 | Small Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23370 | Crystal Falls TS - M2 ID25630 - Tx 08 Guenette | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23371 | Battersea HVDS - F2 ID25590 - Dx 10 Foster | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000199 |  | AIP000199 | Yes | AIP000199 | Large Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23372 | Battersea HVDS - F2 ID25590 - Tx 10 Foster | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23373 | Princeton DS Voltage Conversion | N.D.C.2.02 | 7374 | 205 | LINES | AIP005628 | AIP005628 | AIP005628 | No | AIP005628 | Princeton DS Voltage Conversion | ISD-SR-13 | Life Cycle Optimization & Operational Efficiency Projects | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Alexander.Hamlyn@HydroOne.com | System Renewal | Western | Not Required | 03 - None (default) | Not Required | Project | DETL ACTN | Short Term Planning | Short Term Planning |  | 479987.9393 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 545440.8401 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -65452.9008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43084 | 43434 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
23374 | Beaver Valley RS | N.D.C.2.02 | 7700 | 203 | PROJECT DELIVERY | AIP005419 | AIP005419 | AIP005419 | No | AIP005419 | Beaver Valley RS | ISD-SR-13 | Life Cycle Optimization & Operational Efficiency Projects | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Jerry.Vo@HydroOne.com | System Renewal | 0 | Not Required | 03 - None (default) | Not Required | Project | ACTN DETL | Short Term Planning | Short Term Planning |  | 1418604.8951 | -789864.7034 | -85137.6868 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1418604.8951 | 127612.7762 | -137.6868 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -917477.4796 | -85000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -64.8345 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42705 | 43466 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
23375 | Dymond TS - M1 - ID25190-TX Gengrowth Garden 01 | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23376 | Kenilworth TS: T1, T3, T4 & Switchyard Refurb. | N.T.C.1.41 | 7700 | 203 | PROJECT DELIVERY | AIP000422 | AIP000422 | AIP000422 | No | AIP000422 | Kenilworth TS: T1, T3, T4 & Switchyard Refurbishment and Reconfiguration | SR-02 | Station Reinvestment Projects | Hamilton/Niagara Zone Station/Yard Investments | James.Mardegan@HydroOne.com | mark.truchanowicz@hydroone.com | System Renewal | Hamilton Niagara | Not Required | 02 - Expectation (no agreement) | TBD | Project | ACCP EMPP | Executing | Executing |  | 2029566.6501 | 1738322.8619 | 11560040.2052 | 3796246.5176 | 0 | 0 | 0 | 0 | 0 | 0 | 2182329.7313 | 1869164.3676 | 12430150.7583 | 4081985.5028 | 0 | 0 | 0 | 0 | 0 | 0 | -152763.0812 | -130841.5057 | -870110.5531 | -285738.9852 | 0 | 0 | 0 | 0 | 0 | 0 | -7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43190 | 44530 | False |  | False |  | False |  | False | True | Customer (Alectra) was consulted on final station configuration to meet customer needs | False | False | False | False | FALSE |  | 11 | 2 | Switchyard Refurbishment and Reconfiguration
23377 | Main TS T3/T4; T3, T4 & Component Replacement | N.T.C.1.43 | 7700 | 203 | PROJECT DELIVERY | AIP005116 | AIP005116 | AIP005116 | No | AIP005116 | Main TS: T3, T4 & Component Replacements | SR-05 | Load Station Transformer Replacement Projects | Greater Toronto Area Zone Station/Yard Investments | James.Mardegan@HydroOne.com | michael.xavier@hydroone.com | System Renewal | Greater Toronto Area | Not Required | 01 - Agreement (current/future) | TBD | Project | BEST ACTN | Short Term Planning | Short Term Planning |  | 838417.9592 | 3768816.5578 | 16105027.1433 | 5943807.9002 | 0 | 0 | 0 | 0 | 0 | 0 | 901524.6873 | 4052490.9223 | 17529683.1274 | 6607890.0106 | 0 | 0 | 0 | 0 | 0 | 0 | -63106.7281 | -283674.3646 | -1212206.3441 | -447383.3903 | 0 | 0 | 0 | 0 | 0 | 0 | -7 | 7 | 0 | 0 | -212449.64 | -216698.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43441 | 44525 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Component Replacements
23378 | Midhurst TS T1/T2; Component Replacement | N.T.C.1.42 | 7700 | 203 | PROJECT DELIVERY | AIP005178 |  | AIP005178 | Yes | AIP005178 |  |  |  | Central Zone Station/Yard Investments | James.Mardegan@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23379 | Minden TS: T1, T2, PCT and Component Replacement | N.T.C.1.42 | 7700 | 203 | PROJECT DELIVERY | AIP005200 | AIP005200 | AIP005200 | No | AIP005200 | Minden TS: T1, T2, PCT & Component Replacements | SR-05 | Load Station Transformer Replacement Projects | Central Zone Station/Yard Investments | James.Mardegan@HydroOne.com | michael.xavier@hydroone.com | System Renewal | Central | Not Required | 03 - None (default) | Required | Project | DETL ACTN | Short Term Planning | Short Term Planning |  | 3338102.9608 | 8028322.5562 | 7081002.0266 | 88055.0749 | 0 | 0 | 0 | 0 | 0 | 0 | 3589358.0224 | 8632604.8991 | 7613980.6737 | 94682.8762 | 0 | 0 | 0 | 0 | 0 | 0 | -251255.0616 | -604282.3429 | -532978.6472 | -6627.8013 | 0 | 0 | 0 | 0 | 0 | 0 | -7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43119 | 44150 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Component Replacements
23380 | COUTSVILLE DS-F3-ID25120-TX Gengrowth Garden 05 | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23381 | Aylmer TS: Add 2 Breakers - ETPC & H1Dx | N.T.C.2.11 | 7700 | 203 | PROJECT DELIVERY | AIP005501 |  | AIP005501 | Yes | AIP005501 |  |  |  | Load Customer Connection | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23382 | Warren HVDS F2 ID25080 Tx Gengrowth Garden 03 Giro | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23383 | Warren HVDS F2 ID25080 Dx Gengrowth Garden 03 Giro | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000195 |  | AIP000195 | Yes | AIP000195 | Small Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | EMPP ACTN | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23384 | Placeholder for DC202 Life Cycle Projects - EPD | N.D.C.2.02 | 7700 | 203 | PROJECT DELIVERY | AIP000184B |  | AIP000184 | Yes | AIP000184 | (2) Asset Life Cycle Optimization & Operational Efficiency |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Michael.Medeiros@HydroOne.com | System Renewal | 0 | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23386 | "CND MTS#2"- Provide 115 KV Connection | N.T.C.2.11 | 7700 | 203 | PROJECT DELIVERY | AIP005339 |  | AIP005339 | Yes | AIP005339 |  |  |  | Load Customer Connection | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | BEST HOLD | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23387 | "Vaughan MTS#4"- Provide 230 kV Connection | N.T.C.2.11 | 7700 | 203 | PROJECT DELIVERY | AIP000822 | AIP000822 | AIP000822 | No | AIP000822 | Vaughan MTS4 - Provide 230kV Line Connection | 0 |  | Load Customer Connection | Robert.Reinmuller@HydroOne.com | Harneet.Panesar@HydroOne.com | System Access | Greater Toronto Area | Not Required | 01 - Agreement (current/future) | Required | Project | EMPP ACCP | Executing | Executing |  | 460136.7075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 460136.7075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43373 | [13 empty] | FALSE |  | 0 | 0 | Alternative 1
23389 | Beach TS HVAC 2014 | N.T.C.1.28 | 7236 | 215 | FACILITIES & REAL ESTATE | UNPLND |  |  | Yes |  |  |  |  | Transmission Site Facilities | cindy.copp@hydroone.com | [6 empty] | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23390 | Richview TS T5/T6; Component Replacement | N.T.C.1.43 | 7700 | 203 | PROJECT DELIVERY | AIP005202 |  | AIP005202 | Yes | AIP005202 |  |  |  | Greater Toronto Area Zone Station/Yard Investments | James.Mardegan@HydroOne.com | [6 empty] | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23391 | Richview TS T7/T8; Component Replacement | N.T.C.1.43 | 7700 | 203 | PROJECT DELIVERY | AIP005131 |  | AIP005131 | Yes | AIP005131 |  |  |  | Greater Toronto Area Zone Station/Yard Investments | James.Mardegan@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23392 | Line Refurbishment - C22J/C24Z/C21J/C23Z | N.T.C.1.12 | 7700 | 203 | PROJECT DELIVERY | AIP005340 |  | AIP005340 | Yes | AIP005340 |  |  |  | Overhead Lines Component Refurb & Repl | hassan.hamzeh@hydroone.com | [6 empty] | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23393 | Gardiner TS: T1/T2 PCT Component Replacement | N.T.C.1.44 | 7700 | 203 | PROJECT DELIVERY | AIP005119 |  | AIP005119 | Yes | AIP005119 |  |  |  | Eastern Zone Station/Yard Investments | James.Mardegan@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23394 | Barrett Chute SS: Component Replacement | N.T.C.1.44 | 7700 | 203 | PROJECT DELIVERY | AIP005144 | AIP005144 | AIP005144 | No | AIP005144 | Barrett Chute SS: Component Replacement | 0 |  | Eastern Zone Station/Yard Investments | James.Mardegan@HydroOne.com | Donald.Mastrangelo@HydroOne.com | System Renewal | Eastern | Not Required | 02 - Expectation (no agreement) | Not Required | Project | EMPP ACCP | Executing | Executing |  | 9063075.2914 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9745242.2489 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -682166.9574 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -5.5248 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43451 | [13 empty] | FALSE |  | 0 | 0 | Component Replacement
23395 | Sturgeon Falls DS - F2 ID24810 - Dx AGRIS 14 | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000199 |  | AIP000199 | Yes | AIP000199 | Large Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23396 | Sturgeon Falls DS - F2 ID24810- Tx AGRIS 14 | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23397 | Energy Storage Validation Projects | N.T.M.2.21 | 4230 | 213 | PLANNING | AIP005312 |  | AIP005312 | Yes | AIP005312 |  |  |  | Technology Program | Daila.Dzintars@HydroOne.com | [6 empty] | Program | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23398 | Minor Demand Capital Investments | N.T.C.1.46 | 7370 | 206 | TX LINES AND STATIONS | AIP005325 | AIP005325 | AIP005325 | No | AIP005325 | Minor Component Demand Capital | SR-09 | Transmission Station Demand and Spares | Tx Station Demand and Spares | James.Mardegan@HydroOne.com | Donald.Mastrangelo@HydroOne.com | System Renewal | N/A | 0 | 03 - None (default) | 0 | Program | ACTN EMPP | Executing | Short Term Planning |  | 3846016.7707 | 3776661.6536 | 3842534.7132 | 3865165.8799 | 3883089.8035 | 3904768.8905 | 4599166.88 | 4691150.12 | 0 | 0 | 4135501.904 | 4060926.5092 | 4131757.7561 | 4156092.344 | 4175365.3801 | 4198676.2263 | 4945340.72 | 5044247.48 | 0 | 0 | -289485.1333 | -284264.8556 | -289223.0429 | -290926.4641 | -292275.5766 | -293907.3358 | -346173.84 | -353097.36 | 0 | 0 | -7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Demand
23399 | IT Service Management Report | N.T.C.1.29 | 4514 | 212 | INFO SOLUTIONS DIVISION | AIP005328 | AIP005328 | AIP005328 | No | AIP005328 | Configuration Management Project (ITSM) | 0 |  | NERC Cyber Security Compliance Readiness | lincoln.frost-hunt@hydroone.com | Shivakumar.Kodali@HydroOne.com | System Renewal | 0 | 0 | 03 - None (default) | 0 | Project | AWRD EMPP | Executing | Executing |  | 1054036.6296 | 495509.5427 | 491407.9604 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1054036.6296 | 495509.5427 | 491407.9604 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41944 | 42734 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Asset Optimal
23400 | Placeholder for DC202 Load Growth Projects - Lines | N.D.C.2.02 | 7374 | 205 | LINES | AIP000183B | AIP000183 | AIP000183 | No | AIP000183 | (1) System upgrade driven by load growth |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Michael.Medeiros@HydroOne.com | System Service | 0 | 0 | 03 - None (default) | Not Required | Project | init | Short Term Planning | Short Term Planning |  | 0 | 16798224.6977 | 10200272.7134 | 10332991.2226 | 10495682.7383 | 0 | 0 | 0 | 0 | 0 | 124970.16 | 19247805.0847 | 11776050.5002 | 11941184.3119 | 12135985.6784 | 0 | 0 | 0 | 0 | 0 | -124970.16 | -2449580.387 | -1575777.7868 | -1608193.0893 | -1640302.9402 | 0 | 0 | 0 | 0 | 0 | -13.3975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43098 | 44910 | [13 empty] | FALSE |  | 0 | 0 | Alternative 1
23401 | Placeholder for DC202 Life Cycle Projects - Lines | N.D.C.2.02 | 7374 | 205 | LINES | AIP000184 | AIP000184 | AIP000184 | No | AIP000184 | (2) Asset Life Cycle Optimization & Operational Efficiency | ISD-SR-13 | Life Cycle Optimization & Operational Efficiency Projects | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Michael.Medeiros@HydroOne.com | System Renewal | 0 | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 8794674.0667 | 8404147.9159 | 7797300.1039 | 6958861.2462 | 0 | 0 | 0 | 0 | 0 | 0 | 9993947.8031 | 9550168.0862 | 8860568.2998 | 7907796.8707 | 0 | 0 | 0 | 0 | 0 | 0 | -1199273.7364 | -1146020.1703 | -1063268.196 | -948935.6245 | 0 | 0 | 0 | 0 | 0 | -12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43098 | 44910 | [13 empty] | FALSE |  | 0 | 0 | Alternative 1
23405 | Pine Portage SS: Component Replacement | N.T.C.1.45 | 7700 | 203 | PROJECT DELIVERY | AIP005138 | AIP005138 | AIP005138 | No | AIP005138 | Pine Portage SS: Component Replacement | SR-02 | Station Reinvestment Projects | Northern Zone Station/Yard Investments | James.Mardegan@HydroOne.com | Donald.Mastrangelo@HydroOne.com | System Renewal | Northern | Not Required | 01 - Agreement (current/future) | Not Required | Project | EMPP ACCP | Executing | Executing |  | 2659384.2445 | 5050315.4047 | 6475636.1078 | 2986114.4684 | 0 | 0 | 0 | 0 | 0 | 0 | 2659384.2445 | 5050315.4047 | 6770480.7425 | 3228866.5297 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -294844.6347 | -242752.0613 | 0 | 0 | 0 | 0 | 0 | 0 | -3.0582 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44377 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Component Replacement
23406 | Kenora TS: Component Replacement | N.T.C.1.45 | 7700 | 203 | PROJECT DELIVERY | AIP005190 | AIP005190 | AIP005190 | No | AIP005190 | Kenora TS: Component Replacement | SR-04 | Bulk Station Switchgear and Ancillary Equipment Replacement Projects | Northern Zone Station/Yard Investments | James.Mardegan@HydroOne.com | Donald.Mastrangelo@HydroOne.com | System Renewal | Northern | Not Required | 03 - None (default) | Not Required | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 785086.1426 | 1312801.0332 | 8116705.2617 | 9793711.545 | 3009080.52 | 0 | 0 | 0 | 0 | 0 | 844178.648 | 1411614.0142 | 8727640.0663 | 10530872.629 | 3235570.44 | 0 | 0 | 0 | 0 | 0 | -59092.5054 | -98812.981 | -610934.8046 | -737161.084 | -226489.92 | 0 | 0 | 0 | -7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44410 | 45458 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Component Replacement
23407 | Ridgetown Palmer DS Voltage Conversion | N.D.C.2.02 | 7374 | 205 | LINES | AIP005417 | AIP005417 | AIP005417 | No | AIP005417 | Ridgetown palmer DS Voltage Conversion | ISD-SR-13 | Life Cycle Optimization & Operational Efficiency Projects | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Alexander.Hamlyn@HydroOne.com | System Renewal | Western | Not Required | 03 - None (default) | Not Required | Project | DETL ACTN | Short Term Planning | Short Term Planning |  | 851966.8228 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 968144.1168 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -116177.294 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43084 | 43434 | [13 empty] | FALSE |  | 0 | 1 | Asset Optimal
23408 | Peterborough Switch 237 Voltage Conversion | N.D.C.2.02 | 7374 | 205 | LINES | AIP000183A |  | AIP000183 | Yes | AIP000183 | (1) System upgrade driven by load growth |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Michael.Medeiros@HydroOne.com | System Service | 0 | 0 | 03 - None (default) | Not Required | Project | EMPP ACTN | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23409 | Physical Security Expansion Pilot Project | N.T.C.1.29 | 7700 | 203 | PROJECT DELIVERY | AIP005327 |  | AIP005327 | Yes | AIP005327 |  |  |  | NERC Cyber Security Compliance Readiness | lincoln.frost-hunt@hydroone.com | [6 empty] | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23410 | Otto Holden TS: T3/T4 & Component Replacement | N.T.C.1.45 | 7700 | 203 | PROJECT DELIVERY | AIP005182 | AIP005182 | AIP005182 | No | AIP005182 | Otto Holden TS: T3/T4 & Component Replacement | SR-03 | Bulk Station Transformer Replacement Projects | Northern Zone Station/Yard Investments | James.Mardegan@HydroOne.com | Donald.Mastrangelo@HydroOne.com | System Renewal | Northern | Not Required | 03 - None (default) | Required | Project | BEST HOLD | Short Term Planning | Short Term Planning |  | 0 | 0 | 995695.9744 | 4421162.5865 | 14256868.2603 | 13438804.8656 | 3634635.72 | 0 | 0 | 0 | 0 | 0 | 1070640.8327 | 4753938.265 | 15329965.8713 | 14450327.8125 | 3908210.4 | 0 | 0 | 0 | 0 | 0 | -74944.8583 | -332775.6786 | -1073097.611 | -1011522.9469 | -273574.68 | 0 | 0 | 0 | -7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44178 | 45625 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Component Replacement
23411 | Hearst TS: Component Replacement | N.T.C.1.45 | 7700 | 203 | PROJECT DELIVERY | AIP005173 | AIP005173 | AIP005173 | No | AIP005173 | Hearst TS: Component Replacement | 0 |  | Northern Zone Station/Yard Investments | James.Mardegan@HydroOne.com | Donald.Mastrangelo@HydroOne.com | System Renewal | Northern | Not Required | 03 - None (default) | Not Required | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 96661.201 | 855460 | 1636067.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 103936.7753 | 919849.48 | 1759212.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -7275.5743 | -64389.48 | -123144.84 | 0 | 0 | -7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45491 | 45991 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Component Replacement
23412 | Malden TS: Component Replacement | N.T.C.1.40 | 7700 | 203 | PROJECT DELIVERY | AIP005192 | AIP005192 | AIP005192 | No | AIP005192 | Malden TS T1/T2; PCT & Component Replacement | 0 |  | Western Zone Station/Yard Investments | James.Mardegan@HydroOne.com | mark.truchanowicz@hydroone.com | System Renewal | Western | 0 | 03 - None (default) | 0 | Project | EMPP ACCP | Executing | Executing |  | 1519571.7945 | 55001.5592 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1633948.1662 | 59141.4615 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -114376.3716 | -4139.9023 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -5.2642 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43429 | [13 empty] | FALSE |  | 0 | 0 | Alternative 1
23413 | Talbot TS T3/T4; Component Replacement | N.T.C.1.40 | 7700 | 203 | PROJECT DELIVERY | AIP005189 | AIP005189 | AIP005189 | No | AIP005189 | Talbot TS T3/T4; Component Replacement | 0 |  | Western Zone Station/Yard Investments | James.Mardegan@HydroOne.com | mark.truchanowicz@hydroone.com | System Renewal | Western | Not Required | 03 - None (default) | Not Required | Project | ACCP EMPP | Executing | Executing |  | 2295667.9143 | 46201.3098 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2468460.1229 | 49678.8277 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -172792.2086 | -3477.5179 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4.8479 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43404 | [13 empty] | FALSE |  | 0 | 0 | Alternative 1
23414 | Detweiler TS: AC Station Service Component Repl | N.T.C.1.40 | 7700 | 203 | PROJECT DELIVERY | AIP005157 | AIP005157 | AIP005157 | No | AIP005157 | Detweiler TS BULK | 0 |  | Western Zone Station/Yard Investments | James.Mardegan@HydroOne.com | mark.truchanowicz@hydroone.com | System Renewal | Western | Not Required | 03 - None (default) | Not Required | Project | ACCP EMPP | Executing | Executing |  | 1122716.0654 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1182378.5161 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -59662.4507 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -5.046 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43251 | [13 empty] | FALSE |  | 0 | 0 | Alternative 1
23415 | Alexander SS: Component Replacement | N.T.C.1.45 | 7700 | 203 | PROJECT DELIVERY | AIP005201 | AIP005201 | AIP005201 | No | AIP005201 | Alexander SS: Component Replacement | SR-04 | Bulk Station Switchgear and Ancillary Equipment Replacement Projects | Northern Zone Station/Yard Investments | James.Mardegan@HydroOne.com | Donald.Mastrangelo@HydroOne.com | System Renewal | Northern | Not Required | 01 - Agreement (current/future) | Not Required | Project | EMPP ACCP | Executing | Executing |  | 7839080.5553 | 7206865.8723 | 0.0098282 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8429118.8767 | 7749318.1423 | 0.010568 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -590038.3214 | -542452.27 | -0.00073975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3.2555 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43646 | [13 empty] | FALSE |  | 0 | 0 | Component Replacement
23416 | Leaside TS HVAC upgrade 2014 | N.T.C.1.28 | 7236 | 215 | FACILITIES & REAL ESTATE | UNPLND |  |  | Yes |  |  |  |  | Transmission Site Facilities | cindy.copp@hydroone.com | [6 empty] | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23417 | Martindale TS: T21/T23 & Component Replacement | N.T.C.1.45 | 7700 | 203 | PROJECT DELIVERY | AIP005146 | AIP005146 | AIP005146 | No | AIP005146 | Martindale TS: T21/T23 & Component Replacement | SR-02 | Station Reinvestment Projects | Northern Zone Station/Yard Investments | James.Mardegan@HydroOne.com | Donald.Mastrangelo@HydroOne.com | System Renewal | Northern | Not Required | 02 - Expectation (no agreement) | Required | Project | INSC EMPP | Executing | Executing |  | 9447417.9906 | 14274822.5278 | 13172664.935 | 4772909.554 | 865200.4966 | 0 | 0 | 0 | 0 | 0 | 10158513.9684 | 15349271.5353 | 14164155.8441 | 5132160.8107 | 930323.1146 | 0 | 0 | 0 | 0 | 0 | -711095.9778 | -1074449.0075 | -991490.9091 | -359251.2568 | -65122.618 | 0 | 0 | 0 | 0 | 0 | -8.0091 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44542 | [13 empty] | FALSE |  | 0 | 0 | Componet Replacement
23418 | Mississagi TS HVAC upgrade 2014 | N.T.C.1.28 | 7236 | 215 | FACILITIES & REAL ESTATE | UNPLND |  |  | Yes |  |  |  |  | Transmission Site Facilities | cindy.copp@hydroone.com | [6 empty] | Project | EMPP AWRD | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23419 | Lincoln Heights TS: Component Replacement | N.T.C.1.44 | 7700 | 203 | PROJECT DELIVERY | AIP005170 | AIP005170 | AIP005170 | No | AIP005170 | Lincoln Heights TS: Component Replacement-PCT | SR-07 | Protection and Automation Replacement Projects | Eastern Zone Station/Yard Investments | James.Mardegan@HydroOne.com | Fred.Kouhdani@HydroOne.com | System Renewal | Eastern | Not Required | 02 - Expectation (no agreement) | Not Required | Project | init | Short Term Planning | Short Term Planning |  | 0 | 264669.9731 | 796612.7194 | 880550.4079 | 4523346.8799 | 1371972.7363 | 0 | 0 | 0 | 0 | 0 | 284591.369 | 856572.8166 | 946828.3956 | 4863813.8494 | 1475239.5014 | 0 | 0 | 0 | 0 | 0 | -19921.3958 | -59960.0972 | -66277.9877 | -340466.9695 | -103266.7651 | 0 | 0 | 0 | 0 | -7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44169 | 45291 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Component replacement
23420 | Wonderland TS: T5, PCT & Component Replacement | N.T.C.1.40 | 7700 | 203 | PROJECT DELIVERY | AIP005174 | AIP005174 | AIP005174 | No | AIP005174 | Wonderland TS: T5, PCT & Component Replacement | SR-05 | Load Station Transformer Replacement Projects | Western Zone Station/Yard Investments | James.Mardegan@HydroOne.com | mark.truchanowicz@hydroone.com | System Renewal | Western | Not Required | 03 - None (default) | Not Required | Project | init | Short Term Planning | Short Term Planning |  | 253911.1299 | 843435.8131 | 2320469.9983 | 9957633.7559 | 3729089.2079 | 0 | 0 | 0 | 0 | 0 | 273022.7204 | 906920.2292 | 2495129.0304 | 10707133.0708 | 4009773.3419 | 0 | 0 | 0 | 0 | 0 | -19111.5904 | -63484.416 | -174659.0321 | -749499.315 | -280684.1339 | 0 | 0 | 0 | 0 | 0 | -7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43944 | 44816 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Component Replacement
23421 | Seaforth TS: T1, T2, T5, T6, PCT & Component Repl. | N.T.C.1.40 | 7700 | 203 | PROJECT DELIVERY | AIP005197 | AIP005197 | AIP005197 | No | AIP005197 | Seaforth TS: T1, T2, T5, T6, PCT & Component Replacement | SR-03 | Bulk Station Transformer Replacement Projects | Western Zone Station/Yard Investments | James.Mardegan@HydroOne.com | mark.truchanowicz@hydroone.com | System Renewal | Western | Not Required | 03 - None (default) | TBD | Project | ACTN BEST | Short Term Planning | Short Term Planning |  | 333810.3284 | 1323349.8656 | 6364368.6531 | 17220972.1772 | 15183612.8191 | 3634460.6789 | 0 | 0 | 0 | 0 | 358935.837 | 1422956.8448 | 6843407.1539 | 18517174.384 | 16326465.3969 | 3908022.2354 | 0 | 0 | 0 | 0 | -25125.5086 | -99606.9791 | -479038.5008 | -1296202.2069 | -1142852.5778 | -273561.5565 | 0 | 0 | 0 | 0 | -7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43784 | 45230 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Component Replacement
23422 | Kent TS: T1, T2 & Component Replacement | N.T.C.1.40 | 7700 | 203 | PROJECT DELIVERY | AIP005169 | AIP005169 | AIP005169 | No | AIP005169 | Kent TS: T1, T2 & Component Replacement | SR-02 | Station Reinvestment Projects | Western Zone Station/Yard Investments | James.Mardegan@HydroOne.com | mark.truchanowicz@hydroone.com | System Renewal | Western | Not Required | 03 - None (default) | Not Required | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 180565.4736 | 718529.0735 | 1927513.2227 | 12722545.438 | 11561541.96 | 2563172.08 | 0 | 0 | 0 | 0 | 194156.4232 | 772611.907 | 2072594.8632 | 13680156.3849 | 12431765.52 | 2756098.96 | 0 | 0 | 0 | 0 | -13590.9496 | -54082.8335 | -145081.6404 | -957610.9469 | -870223.56 | -192926.88 | 0 | 0 | -7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44721 | 45768 | False |  | False |  | False |  | False | True | Entegrus Powerlines have expressed issues wit DPP due to physically split transitional bus | False | False | False | False | FALSE |  | 2 | 0 | Component Replacement
23423 | Edgeware TS: PCT & Component Replacement | N.T.C.1.40 | 7700 | 203 | PROJECT DELIVERY | AIP005127 | AIP005127 | AIP005127 | No | AIP005127 | Edgeware TS: PCT & Component Replacement | SR-07 | Protection and Automation Replacement Projects | Western Zone Station/Yard Investments | James.Mardegan@HydroOne.com | mark.truchanowicz@hydroone.com | System Renewal | Western | Not Required | 03 - None (default) | Not Required | Project | ACTN BEST | Short Term Planning | Short Term Planning |  | 790703.1519 | 1554567.8309 | 3684733.4852 | 1274638.2074 | 0 | 0 | 0 | 0 | 0 | 0 | 850218.4429 | 1671578.3128 | 3962079.0163 | 1370578.7176 | 0 | 0 | 0 | 0 | 0 | 0 | -59515.291 | -117010.4819 | -277345.5311 | -95940.5102 | 0 | 0 | 0 | 0 | 0 | 0 | -7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43524 | 44452 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Component Replacement
23424 | Galt TS: PCT & Component Replacement | N.T.C.1.40 | 7700 | 203 | PROJECT DELIVERY | AIP005160 |  | AIP005160 | Yes | AIP005160 |  |  |  | Western Zone Station/Yard Investments | James.Mardegan@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23425 | Clarke TS: T3, T4, PCT & Component Replacement | N.T.C.1.40 | 7700 | 203 | PROJECT DELIVERY | AIP005145 | AIP005145 | AIP005145 | No | AIP005145 | Clarke TS: T3, T4, PCT & Component Replacement | SR-05 | Load Station Transformer Replacement Projects | Western Zone Station/Yard Investments | James.Mardegan@HydroOne.com | mark.truchanowicz@hydroone.com | System Renewal | Western | Not Required | 03 - None (default) | Not Required | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 276265.2911 | 1398826.3448 | 8318349.1286 | 10548393.6244 | 5092749.44 | 742138.32 | 0 | 0 | 0 | 0 | 297059.4528 | 1504114.3492 | 8944461.4286 | 11342358.7359 | 5476074.61 | 797998.17 | 0 | 0 | 0 | 0 | -20794.1617 | -105288.0044 | -626112.3 | -793965.1115 | -383325.17 | -55859.85 | 0 | 0 | -7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44697 | 45745 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Component Replacement
23427 | Bowmanville SS Overhead Door Ugrades | N.T.C.1.28 | 7236 | 215 | FACILITIES & REAL ESTATE | UNPLND |  |  | Yes |  |  |  |  | Transmission Site Facilities | cindy.copp@hydroone.com | [6 empty] | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23428 | Richview TS elevator upgrades 2014 | N.T.C.1.28 | 7236 | 215 | FACILITIES & REAL ESTATE | UNPLND |  |  | Yes |  |  |  |  | Transmission Site Facilities | cindy.copp@hydroone.com | [6 empty] | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23429 | Essex OC Windows Replacement 2014 | N.D.C.1.50 | 7236 | 215 | FACILITIES & REAL ESTATE | UNPLND |  |  | Yes |  |  |  |  | Real Estate Facilities | cindy.copp@hydroone.com | [6 empty] | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23430 | Stayner TS T3/T4; Component Replacement | N.T.C.1.42 | 7700 | 203 | PROJECT DELIVERY | AIP005153 |  | AIP005153 | Yes | AIP005153 |  |  |  | Central Zone Station/Yard Investments | James.Mardegan@HydroOne.com | [6 empty] | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23431 | John TS T1/T2/T3/T4; A3-A4 M/C & Component Replace | N.T.C.1.43 | 7700 | 203 | PROJECT DELIVERY | AIP005304 |  | AIP005304 | Yes | AIP005304 |  |  |  | Greater Toronto Area Zone Station/Yard Investments | James.Mardegan@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23432 | Finch TS T1/T2; Component Replacement | N.T.C.1.43 | 7700 | 203 | PROJECT DELIVERY | AIP005172 | AIP005172 | AIP005172 | No | AIP005172 | Finch TS: Component Replacements | SR-06 | Load Station Switchgear and Ancillary Equipment Replacement Projects | Greater Toronto Area Zone Station/Yard Investments | James.Mardegan@HydroOne.com | michael.xavier@hydroone.com | System Renewal | Greater Toronto Area | Not Required | 03 - None (default) | Not Required | Project | init | Short Term Planning | Short Term Planning |  | 233667.2406 | 723431.184 | 957146.9522 | 6312130.3793 | 2446643.947 | 0 | 0 | 0 | 0 | 0 | 251255.0975 | 777882.9935 | 1029190.2712 | 6787236.967 | 2630799.943 | 0 | 0 | 0 | 0 | 0 | -17587.8568 | -54451.8095 | -72043.319 | -475106.5877 | -184155.996 | 0 | 0 | 0 | 0 | 0 | -7 | 7.00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43962 | 44926 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Component Replacements
23433 | Horner TS: Component Replacement | N.T.C.1.43 | 7700 | 203 | PROJECT DELIVERY | AIP005166 | AIP005166 | AIP005166 | No | AIP005166 | Horner TS: Component Replacements | 0 |  | Greater Toronto Area Zone Station/Yard Investments | James.Mardegan@HydroOne.com | michael.xavier@hydroone.com | System Renewal | Greater Toronto Area | Not Required | 03 - None (default) | Not Required | Project | DETL ACTN | Short Term Planning | Short Term Planning |  | 358846.1003 | 2161471.4093 | 1168365.3218 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 385856.0218 | 2324162.8057 | 1256306.7977 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -27009.9215 | -162691.3964 | -87941.4758 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -7 | 7.00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43357 | 44012 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Component Replacements
23434 | Waubaushene TS T5/T6; PCT & Component Replacement | N.T.C.1.42 | 7700 | 203 | PROJECT DELIVERY | AIP005292 |  | AIP005292 | Yes | AIP005292 |  |  |  | Central Zone Station/Yard Investments | James.Mardegan@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23436 | Orangeville TS: T1, T2, T3, T4 & Component Replace | N.T.C.1.42 | 7700 | 203 | PROJECT DELIVERY | AIP005208 | AIP005208 | AIP005208 | No | AIP005208 | Orangeville TS: T1, T2, T3, T4 & Component Replacements | SR-05 | Load Station Transformer Replacement Projects | Central Zone Station/Yard Investments | James.Mardegan@HydroOne.com | michael.xavier@hydroone.com | System Renewal | Central | Not Required | 03 - None (default) | Required | Project | ACTN BEST | Short Term Planning | Short Term Planning |  | 266691.9543 | 1290879.3944 | 8645349.3502 | 20315022.7986 | 6978462.9547 | 0 | 0 | 0 | 0 | 0 | 286765.5423 | 1388042.3596 | 9296074.5701 | 21844110.5361 | 7503723.6072 | 0 | 0 | 0 | 0 | 0 | -20073.588 | -97162.9652 | -650725.2199 | -1529087.7375 | -525260.6525 | 0 | 0 | 0 | 0 | 0 | -7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43721 | 44819 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Component Replacements
23437 | Cherrywood TS 230kV BULK; ABCB & Component Repl. | N.T.C.1.42 | 7700 | 203 | PROJECT DELIVERY | AIP005214 | AIP005214 | AIP005214 | No | AIP005214 | Cherrywood TS 230kV - Phase 1 ABCB (12) & AC/DC SS | SR-01 | Air Blast Circuit Breaker Replacement Projects | Central Zone Station/Yard Investments | James.Mardegan@HydroOne.com | Fred.Kouhdani@HydroOne.com | System Renewal | Central | Not Required | 03 - None (default) | In Progress | Project | EMPP ACCP | Executing | Executing |  | 8111949.0433 | 41986713.3 | 13115081.5695 | 5605223.8606 | 7557618.6427 | 5596690.1961 | 0 | 0 | 0 | 0 | 8722139.9005 | 45117218.3586 | 14104899.0464 | 6031296.6203 | 8128181.4306 | 6020821.5756 | 0 | 0 | 0 | 0 | -610190.8572 | -3130505.0585 | -989817.4769 | -426072.7597 | -570562.7879 | -424131.3794 | 0 | 0 | 0 | 0 | -6.9805 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43159 | 45275 | False |  | False |  | False |  | False | True | need to be aligned with OPG -Pickering shutdown plan | False | False | False | False | TRUE | The 2003 strategy recommended to replace the air blast circuit breakers at age fifty. The breakers performance / reliability have deteriorated significantly over the last five years and have shown no sign of improvement. This investment is to replace these assets to effectively manage the numerous risks associated with this aging breakers. | 0 | 0 | Component Replacement (Accelerated)
23438 | Tomken TS T3/T4 PCT & Component Replacement | N.T.C.1.43 | 7700 | 203 | PROJECT DELIVERY | AIP005284 | AIP005284 | AIP005284 | No | AIP005284 | Tomken TS T3/T4; PCT & Component Replacement | 0 |  | Greater Toronto Area Zone Station/Yard Investments | James.Mardegan@HydroOne.com | michael.xavier@hydroone.com | System Renewal | Greater Toronto Area | 0 | 03 - None (default) | 0 | Project | ACTN EMPP | Executing | Executing |  | 1952054.9584 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2098983.8262 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -146928.8678 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -12.9174 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43371 | [13 empty] | FALSE |  | 0 | 0 | Component Replacement
23439 | Pleasant TS Station Centric | N.T.C.1.43 | 7700 | 203 | PROJECT DELIVERY | AIP005181 | AIP005181 | AIP005181 | No | AIP005181 | Pleasant TS: Breakers, PCT & Component Replacements | SR-06 | Load Station Switchgear and Ancillary Equipment Replacement Projects | Greater Toronto Area Zone Station/Yard Investments | James.Mardegan@HydroOne.com | michael.xavier@hydroone.com | System Renewal | Greater Toronto Area | Not Required | 03 - None (default) | TBD | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 748467.8145 | 1399730.3347 | 8744937.5784 | 11608592.24 | 3289585.96 | 0 | 0 | 0 | 0 | 0 | 804804.1016 | 1505086.3814 | 9403158.6865 | 12482357.24 | 3537189.16 | 0 | 0 | 0 | 0 | 0 | -56336.2871 | -105356.0467 | -658221.1081 | -873765 | -247603.2 | 0 | 0 | -7 | 7.00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44757 | 45823 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Breakers, PCT & Component Replacements
23442 | Dufferin TS T2/T4; Component Replacement | N.T.C.1.43 | 7700 | 203 | PROJECT DELIVERY | AIP005193 |  | AIP005193 | Yes | AIP005193 |  |  |  | Greater Toronto Area Zone Station/Yard Investments | James.Mardegan@HydroOne.com | [6 empty] | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23443 | Bermondsey TS T3/T4; T3, T4 & Component Replace | N.T.C.1.42 | 7700 | 203 | PROJECT DELIVERY | AIP005123 | AIP005123 | AIP005123 | No | AIP005123 | Bermondsey TS: T3, T4 & Component Replacements | SR-05 | Load Station Transformer Replacement Projects | Central Zone Station/Yard Investments | James.Mardegan@HydroOne.com | michael.xavier@hydroone.com | System Renewal | Central | Not Required | 03 - None (default) | TBD | Project | init | Short Term Planning | Short Term Planning |  | 0 | 794009.9194 | 1463927.0285 | 9353706.978 | 11310320.5823 | 3158887.6584 | 0 | 0 | 0 | 0 | 0 | 853774.1069 | 1574115.0844 | 10057749.4387 | 12161635.0347 | 3396653.3962 | 0 | 0 | 0 | 0 | 0 | -59764.1875 | -110188.0559 | -704042.4607 | -851314.4524 | -237765.7377 | 0 | 0 | 0 | 0 | -7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44040 | 45105 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Component Replacements
23444 | Dufferin TS: T1, T3, T4 & Component Replacement | N.T.C.1.43 | 7700 | 203 | PROJECT DELIVERY | AIP005112 | AIP005112 | AIP005112 | No | AIP005112 | Dufferin TS: T1, T3, T4 & Component Replacements | 0 |  | Greater Toronto Area Zone Station/Yard Investments | James.Mardegan@HydroOne.com | michael.xavier@hydroone.com | System Renewal | Greater Toronto Area | Not Required | 01 - Agreement (current/future) | TBD | Project | EMPP ACCP | Executing | Executing |  | 8797091.8029 | 2188162.5394 | 0.068797 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9459238.4978 | 2352862.9456 | 0.073975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -662146.6948 | -164700.4062 | -0.0051783 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -5.1618 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43636 | [13 empty] | FALSE |  | 0 | 0 | Component Replacements
23445 | Cecil TS: T1 & Component Replacement | N.T.C.1.43 | 7700 | 203 | PROJECT DELIVERY | AIP005120 | AIP005120 | AIP005120 | No | AIP005120 | Cecil TS: T1 & Component Replacements | SR-05 | Load Station Transformer Replacement Projects | Greater Toronto Area Zone Station/Yard Investments | James.Mardegan@HydroOne.com | michael.xavier@hydroone.com | System Renewal | Greater Toronto Area | Not Required | 01 - Agreement (current/future) | Required | Project | ACCP EMPP | Executing | Executing |  | 7026287.6532 | 3858759.8316 | 0.0098282 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7555148.0142 | 4149204.12 | 0.010568 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -528860.361 | -290444.2884 | -0.00073975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -12 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43539 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Component Replacements
23446 | Erindale TS: PCT & Component Replacements | N.T.C.1.43 | 7700 | 203 | PROJECT DELIVERY | AIP005212 | AIP005212 | AIP005212 | No | AIP005212 | Erindale TS: PCT & Component Replacements | 0 |  | Greater Toronto Area Zone Station/Yard Investments | James.Mardegan@HydroOne.com | michael.xavier@hydroone.com | System Renewal | Greater Toronto Area | Not Required | 03 - None (default) | Not Required | Project | init | Short Term Planning | Short Term Planning |  | 751073.1581 | 447443.5813 | 2114561.1999 | 2575036.2436 | 721014.8823 | 0 | 0 | 0 | 0 | 0 | 807605.5463 | 481122.1304 | 2273721.7204 | 2768856.1759 | 775284.8197 | 0 | 0 | 0 | 0 | 0 | -56532.3882 | -33678.5491 | -159160.5204 | -193819.9323 | -54269.9374 | 0 | 0 | 0 | 0 | 0 | -7 | 7.00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43558 | 44727 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Component Replacements
23447 | Fairbank TS: T1, T2, T3, T4, PCT & LV Yard Replace | N.T.C.1.43 | 7700 | 203 | PROJECT DELIVERY | AIP000413 | AIP000413 | AIP000413 | No | AIP000413 | Fairbank TS: T1, T2, T3, T4, PCT & LV Yard Replacements | SR-02 | Station Reinvestment Projects | Greater Toronto Area Zone Station/Yard Investments | James.Mardegan@HydroOne.com | michael.xavier@hydroone.com | System Renewal | Greater Toronto Area | Not Required | 01 - Agreement (current/future) | TBD | Project | DETL ACTN | Short Term Planning | Short Term Planning |  | 426025.3499 | 5689056.9391 | 23285559.7333 | 23628509.7157 | 5952699.1135 | 0 | 0 | 0 | 0 | 0 | 458091.7741 | 6117265.5259 | 25038236.2723 | 25406999.6943 | 6400751.735 | 0 | 0 | 0 | 0 | 0 | -32066.4242 | -428208.5868 | -1752676.5391 | -1778489.9786 | -448052.6214 | 0 | 0 | 0 | 0 | 0 | -7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43475 | 44910 | True | THESL requested additional feeder positions | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Component Replacements
23449 | Ingersoll TS - Replace SP Breakers & Component Rep | N.T.C.1.40 | 7700 | 203 | PROJECT DELIVERY | AIP005330 |  | AIP005330 | Yes | AIP005330 |  |  |  | Western Zone Station/Yard Investments | James.Mardegan@HydroOne.com | [6 empty] | Program | ACCP EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23450 | Campbell TS: PCT & Component Replacement | N.T.C.1.40 | 7700 | 203 | PROJECT DELIVERY | AIP005194 | AIP005194 | AIP005194 | No | AIP005194 | Campbell TS: PCT & Component Replacement | SR-07 | Protection and Automation Replacement Projects | Western Zone Station/Yard Investments | James.Mardegan@HydroOne.com | mark.truchanowicz@hydroone.com | System Renewal | Western | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 650114.6938 | 972983.1703 | 5547314.9084 | 8266066.7268 | 2512977.4271 | 0 | 0 | 0 | 0 | 0 | 699048.0579 | 1046218.4627 | 5964854.7403 | 8888243.7923 | 2702126.2656 | 0 | 0 | 0 | 0 | 0 | -48933.3641 | -73235.2924 | -417539.8318 | -622177.0655 | -189148.8386 | 0 | 0 | 0 | 0 | 0 | -7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43837 | 44773 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Component Replacement
23451 | Bruce B SS BULK | N.T.C.1.40 | 7700 | 203 | PROJECT DELIVERY | AIP005165 | AIP005165 | AIP005165 | No | AIP005165 | Bruce B SS ABCB Replacement project | SR-01 | Air Blast Circuit Breaker Replacement Projects | Western Zone Station/Yard Investments | James.Mardegan@HydroOne.com | Fred.Kouhdani@HydroOne.com | System Renewal | Western | Not Required | 02 - Expectation (no agreement) | Not Required | Project | DETL ACTN | Short Term Planning | Short Term Planning |  | 0 | 5659332.2054 | 22709729.1522 | 22592351.249 | 5580052.9584 | 0 | 0 | 0 | 0 | 0 | 0 | 6085303.4467 | 24419063.6046 | 24292850.8054 | 6000056.9445 | 0 | 0 | 0 | 0 | 0 | 0 | -425971.2413 | -1709334.4523 | -1700499.5564 | -420003.9861 | 0 | 0 | 0 | 0 | 0 | -7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43434 | 44803 | False |  | False |  | False |  | False | True | need to be aligned with BP refurbishment project | False | False | False | False | FALSE |  | 0 | 0 | Alternative 1_ ABCB Replacement- Breaker by Breaker replacement- New PCT Building
23452 | Owen Sound TS BULK; Component replacement | N.T.C.1.40 | 7700 | 203 | PROJECT DELIVERY | AIP005187 |  | AIP005187 | Yes | AIP005187 |  |  |  | Western Zone Station/Yard Investments | James.Mardegan@HydroOne.com | [6 empty] | Program | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23453 | Walker TS #1 T3/T4; Component Replacement | N.T.C.1.40 | 7700 | 203 | PROJECT DELIVERY | AIP005125 |  | AIP005125 | Yes | AIP005125 |  |  |  | Western Zone Station/Yard Investments | James.Mardegan@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23454 | Crawford TS T3/T4; Component Replacement | N.T.C.1.40 | 7700 | 203 | PROJECT DELIVERY | AIP005154 |  | AIP005154 | Yes | AIP005154 |  |  |  | Western Zone Station/Yard Investments | James.Mardegan@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23456 | DS MUS Purchase Program | N.D.C.1.08 | 7700 | 203 | PROJECT DELIVERY | AIP000156B | AIP000156 | AIP000156 | No | AIP000156 | DS MUS Refurbishment_Purchase Program |  |  | Distributing & Regulating Stations | emre.aydin@HydroOne.com | Trevor.Beausoleil@HydroOne.com | System Renewal | N/A | 0 | 03 - None (default) | 0 | Program | EMPP ACCP | Executing | Short Term Planning | # of MUSs | 3486189.0329 | 5689890.4918 | 5807952.1238 | 5927427.7561 | 6045777.221 | 0 | 0 | 0 | 0 | 0 | 3486189.0329 | 5689890.4918 | 5807952.1238 | 5927427.7561 | 6045777.221 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Vulnerable
23458 | Striker HVDS F2 ID25090 Dx Solvation-VF | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000195 |  | AIP000195 | Yes | AIP000195 | Small Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23459 | Lennox TS BULK:OPG Sync Breaker Replacement Coord | N.T.C.1.44 | 7700 | 203 | PROJECT DELIVERY | AIP000426 |  | AIP000426 | Yes | AIP000426 | Lennox TS BULK: ABCB component replacement |  |  | Eastern Zone Station/Yard Investments | James.Mardegan@HydroOne.com | Fred.Kouhdani@HydroOne.com | System Renewal | Eastern | Not Required | 02 - Expectation (no agreement) | Not Required | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23461 | Aylmer TS capital contribution to Tx | N.D.C.2.02 | 7700 | 203 | PROJECT DELIVERY | AIP000186 |  | AIP000186 | Yes | AIP000186 |  |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | [6 empty] | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23462 | New Post Creek GS Connection | N.T.C.2.12 | 7700 | 203 | PROJECT DELIVERY | AIP005411 |  | AIP005411 | Yes | AIP005411 |  |  |  | Generator Customer Connection | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | EMPP ACTN | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23464 | Campbell TS M14&24 ID25800-TX-Guelph-Ind EnergyCtr | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23465 | Striker HVDS F2 ID25090 Tx Solvation-VF | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23466 | Line Refurbishment - S7M | N.T.C.1.12 | 7700 | 203 | PROJECT DELIVERY | AIP005341 | AIP005341 | AIP005341 | No | AIP005341 | S7M, Manotick JCT-Richmond DS & Str. 673 N-Manordale JCT, Tx Line Refurb. (EoL) | SR-19 | Transmission Line Refurbishment - End of Life ACSR, Copper Conductors & Structures | Overhead Lines Component Refurb & Repl | hassan.hamzeh@hydroone.com | Deniz.Turkben@HydroOne.com | System Renewal | Eastern | 0 | 03 - None (default) | 0 | Project | HOLD | Short Term Planning | Short Term Planning |  | 342378.801 | 446784.9604 | 904858.7027 | 912441.428 | 0 | 0 | 0 | 0 | 0 | 0 | 389066.8193 | 507710.1822 | 1028248.5258 | 1036865.2591 | 0 | 0 | 0 | 0 | 0 | 0 | -46688.0183 | -60925.2219 | -123389.8231 | -124423.8311 | 0 | 0 | 0 | 0 | 0 | 0 | -12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43882 | 44502 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Proceed with complete line refurbishment
23467 | PLACEHOLDER: NextBridge East-West Tie Line | N.T.C.1.14 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Third Party Transmission System Modifications | john.boldt@HydroOne.com | [6 empty] | Project | HOLD | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23468 | Metrolinx-Eglinton LRT at Jonesville Cres-Recovera | N.T.C.1.14 | 7700 | 203 | PROJECT DELIVERY | AIP005444 |  | AIP005444 | Yes | AIP005444 |  |  |  | Third Party Transmission System Modifications | john.boldt@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23470 | Hanmer TS: 230-44 kV 83MVA DESN | N.T.C.2.11 | 7700 | 203 | PROJECT DELIVERY | AIP005507 | AIP005507 | AIP005507 | No | AIP005507 | Hanmer TS: Build a New 230-44 kV TS | SA-04 | Hanmer TS: Build 230/44kV Transformer Station | Load Customer Connection | Robert.Reinmuller@HydroOne.com | Kirpal.Bahra@HydroOne.com | System Access | 0 | 0 | 03 - None (default) | 0 | Project | HOLD BEST | Short Term Planning | Short Term Planning |  | 87522.3603 | -1197017.4594 | 4147613.9471 | 1543050.4582 | 0 | 0 | 0 | 0 | 0 | 0 | 498361.5303 | 7019765.8706 | 9899513.9471 | 8938350.4582 | 0 | 0 | 0 | 0 | 0 | 0 | -1.3878e-11 | 0 | 8.8818e-10 | 4.4409e-10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -410839.17 | -8216783.33 | -5751900 | -7395300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43635 | 44347 | True | HON Distribution Request | True | Tranmission license requirement to connect customers. | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Alternative 1
23471 | M20/21D Install 230 kV In-Line Switches | N.T.C.2.02 | 7700 | 203 | PROJECT DELIVERY | AIP005450 |  | AIP005450 | Yes | AIP005450 |  |  |  | Local Area Supply | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23472 | Dx Coniston Voltage Conversion | N.D.C.2.02 | 7700 | 203 | PROJECT DELIVERY | AIP005421 | AIP005421 | AIP005421 | No | AIP005421 | Coniston Voltage Conversion | ISD-SR-13 | Life Cycle Optimization & Operational Efficiency Projects | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Gert.Alikaj@HydroOne.com | System Renewal | 0 | Not Required | 03 - None (default) | Not Required | Project | DETL ACTN | Short Term Planning | Short Term Planning |  | 2685700.2961 | 1191052.5583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2845132.8538 | 1191052.5583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -159432.5577 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3.9502 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42975 | 43493 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
23474 | Bronte TS; T5/T6 DESN Refurbishment | N.T.C.1.41 | 7700 | 203 | PROJECT DELIVERY | AIP005500 | AIP005500 | AIP005500 | No | AIP005500 | Bronte TS; T5/T6 DESN Refurbishment | SR-02 | Station Reinvestment Projects | Hamilton/Niagara Zone Station/Yard Investments | James.Mardegan@HydroOne.com | mark.truchanowicz@hydroone.com | System Renewal | Hamilton Niagara | 0 | 03 - None (default) | TBD | Project | ACCP EMPP | Executing | Executing |  | 17706892.399 | 10746537.8248 | 0.0098282 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19039669.2462 | 11555417.0159 | 0.010568 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1332776.8472 | -808879.1911 | -0.00073975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -5.6788 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43723 | [13 empty] | FALSE |  | 0 | 0 | T5/T6 DESN Rebuild
23475 | Operating Support System (OSS) Upgrades | N.T.M.1.23 | 4048 | 213 | PLANNING | AIP000654 | AIP000654 | AIP000654 | No | AIP000654 | Operating Support System (OSS) Upgrades | 0 |  | Operation of Telecom Services | Miroslav.Kostic@HydroOne.com | Sheraz.Majid@HydroOne.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | init EMPP | Executing | Short Term Planning | Retainer | 494248.4177 | 1695086.6222 | 1698172.9894 | 796258.6137 | 816465.4565 | 826677.4483 | 0 | 0 | 0 | 0 | 494248.4177 | 1695086.6222 | 1698172.9894 | 796258.6137 | 816465.4565 | 826677.4483 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Vulnerable (Modified-Tx Decision)
23476 | CMS Station Service and Yard Supply Replacement | N.T.C.1.42 | 7700 | 203 | PROJECT DELIVERY | AIP000616 |  | AIP000616 | Yes | AIP000616 |  |  |  | Central Zone Station/Yard Investments | James.Mardegan@HydroOne.com | [6 empty] | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23477 | Wilson TS M6 ID22420-TX Oshawa PUC Networks Inc La | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23479 | Kingsville TS-M1 M7-DG 1096 and 1099 TX PV mitigat | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000928 |  | AIP000928 | Yes | AIP000928 |  |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | [6 empty] | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23485 | Striker HVDS F2 ID25180 Dx Solvation-S | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000195 |  | AIP000195 | Yes | AIP000195 | Small Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23486 | Striker HVDS F2 ID25180 Tx Solvation-S | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23490 | GTA OC Building Improvements 2014 | N.C.C.1.50 | 7236 | 215 | FACILITIES & REAL ESTATE |  |  |  | No |  |  |  |  | Real Estate Facilities | cindy.copp@hydroone.com | [6 empty] | Project | EMPP AWRD | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23491 | Kenora OC HVAC 2014 | N.C.C.1.50 | 7236 | 215 | FACILITIES & REAL ESTATE |  |  |  | No |  |  |  |  | Real Estate Facilities | cindy.copp@hydroone.com | [6 empty] | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23492 | Kirkland OC HVAC 2014 Upgrade | N.D.C.1.50 | 7236 | 215 | FACILITIES & REAL ESTATE |  |  |  | No |  |  |  |  | Real Estate Facilities | cindy.copp@hydroone.com | [6 empty] | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23495 | St Thomas Fleet - Gate Installation 2014 | N.C.C.1.50 | 7236 | 215 | FACILITIES & REAL ESTATE |  |  |  | No |  |  |  |  | Real Estate Facilities | cindy.copp@hydroone.com | [6 empty] | Project | EMPP AWRD | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23496 | Trafalgar TS Compressor & Motor Replacement 2014 | N.T.C.1.28 | 7236 | 215 | FACILITIES & REAL ESTATE |  |  |  | No |  |  |  |  | Transmission Site Facilities | cindy.copp@hydroone.com | [6 empty] | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23498 | Cancelled - Steel Structure Replacement - K6F/K24F | N.T.C.1.12 | 7700 | 203 | PROJECT DELIVERY | AIP005342 |  | AIP005342 | Yes | AIP005342 |  |  |  | Overhead Lines Component Refurb & Repl | hassan.hamzeh@hydroone.com | [6 empty] | Program | BEST ACTN | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23499 | D2L,Upper Notch x Martin River-Line Refurbishment | N.T.C.1.12 | 7700 | 203 | PROJECT DELIVERY | AIP005531 | AIP005531 | AIP005531 | No | AIP005531 | Line Refurbishment - D2L, Upper Notch JCT x Martin River JCT | SR-19 | Transmission Line Refurbishment - End of Life ACSR, Copper Conductors & Structures | Overhead Lines Component Refurb & Repl | hassan.hamzeh@hydroone.com | Deniz.Turkben@HydroOne.com | System Renewal | Northern | Not Required | 03 - None (default) | Not Required | Project | ACCP EMPP | Executing | Executing |  | 10133712.1826 | 14808170.6996 | 0.0098282 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11515582.0256 | 16827466.7041 | 0.011168 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1381869.8431 | -2019296.0045 | -0.0013402 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43658 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Proceed with complete line refurbishment
23500 | Lighting Upgrades OC 2014 | N.D.C.1.50 | 7236 | 215 | FACILITIES & REAL ESTATE |  |  |  | No |  |  |  |  | Real Estate Facilities | cindy.copp@hydroone.com | [6 empty] | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23502 | Tweed OC Trailer Acquisition 2014 | N.D.C.1.50 | 7236 | 215 | FACILITIES & REAL ESTATE |  |  |  | No |  |  |  |  | Real Estate Facilities | cindy.copp@hydroone.com | [6 empty] | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23505 | J5D, Keith TS-Mid R. JCT Waterman, Tx Line Refurb. | N.T.C.1.12 | 7700 | 203 | PROJECT DELIVERY | AIP005361 |  | AIP005361 | Yes | AIP005361 |  |  |  | Overhead Lines Component Refurb & Repl | hassan.hamzeh@hydroone.com | [6 empty] | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23510 | Preston TS M24-M30 ID25670 TX Toyota Motor Manufac | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23516 | DOM Mtce & DS Operating Diagrams | N.D.M.3.01 | 7370 | 206 | TX LINES AND STATIONS | AIP000349 | AIP000349 | AIP000349 | No | AIP000349 | Dx Operating Diagrams |  |  | Operations Contract | Godfrey.Holder@HydroOne.com | william.ilie@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | BEST ACTN | Short Term Planning | Short Term Planning | # of Drawings | 1183583.3614 | 1223423.753 | 1254104.5407 | 1285928.7775 | 1313819.7468 | 0 | 0 | 0 | 0 | 0 | 1183583.3614 | 1223423.753 | 1254104.5407 | 1285928.7775 | 1313819.7468 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2030 | 2030 | 2030 | 2030 | 2030 | 2030 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
23517 | Horner TS - M4 - ID26490-TX Campbell Company of Ca | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23518 | Fergus TS - M4 - ID25260-TX Cripton | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23519 | Lauzon TS - M29 - ID25580 - TX Woodslee Solar Gard | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23520 | Barry's Bay Trailer acquisition 2014 | N.D.C.1.50 | 7236 | 215 | FACILITIES & REAL ESTATE |  |  |  | No |  |  |  |  | Real Estate Facilities | cindy.copp@hydroone.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23521 | Winchester OC Trailer Acquisition 2014 | N.D.C.1.50 | 7236 | 215 | FACILITIES & REAL ESTATE |  |  |  | No |  |  |  |  | Real Estate Facilities | cindy.copp@hydroone.com | [6 empty] | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23522 | Brockville OC Trailer Acquisition 2014 | N.D.C.1.50 | 7236 | 215 | FACILITIES & REAL ESTATE |  |  |  | No |  |  |  |  | Real Estate Facilities | cindy.copp@hydroone.com | [6 empty] | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23524 | Fergus TS - M4 - ID25250- TX Haja | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23530 | Brockville TS ID26230-Dx 2MW Cogeneration System | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000199 |  | AIP000199 | Yes | AIP000199 | Large Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23531 | Brockville TS ID26230 TX 2MW Cogeneration System | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23532 | Grand Bend Municipal DS F3 Voltage Conversion | N.D.C.2.02 | 7374 | 205 | LINES | AIP000183 |  | AIP000183 | Yes | AIP000183 | (1) System upgrade driven by load growth | ISD-SS-02 | System Upgrades Driven by Load Growth | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Michael.Medeiros@HydroOne.com | System Service | 0 | 0 | 03 - None (default) | Not Required | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23533 | Kenilworth DS Upgrades | N.D.C.2.02 | 7700 | 203 | PROJECT DELIVERY | AIP000183 |  | AIP000183 | Yes | AIP000183 | (1) System upgrade driven by load growth | ISD-SS-02 | System Upgrades Driven by Load Growth | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Michael.Medeiros@HydroOne.com | System Service | 0 | 0 | 03 - None (default) | Not Required | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23534 | HVAC Replacements NTC128 Budget | N.T.C.1.28 | 7236 | 215 | FACILITIES & REAL ESTATE | AIP000667 |  | AIP000667 | Yes | AIP000667 |  |  |  | Transmission Site Facilities | cindy.copp@hydroone.com | [6 empty] | Program | EMPP AWRD | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23535 | Longlac TS: Relocate | N.T.C.2.11 | 7700 | 203 | PROJECT DELIVERY | AIP005356 | AIP005356 | AIP005356 | No | AIP005356 | Relocate Longlac TS | 0 |  | Load Customer Connection | Robert.Reinmuller@HydroOne.com | Hamid.Hamadanizadeh@HydroOne.com | System Access | Northern | 0 | 01 - Agreement (current/future) | 0 | Project | DETL ACTN | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800000 | 1400000 | 2300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -800000 | -1400000 | -2300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43130 | 44439 | True | GGM has asked HONI to relocate Longlac TS, A4L and feeders | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Alternative 1
23540 | Roof Replacements N.T.C.1.28 Budget | N.T.C.1.28 | 7236 | 215 | FACILITIES & REAL ESTATE | AIP000668 |  | AIP000668 | Yes | AIP000668 |  |  |  | Transmission Site Facilities | cindy.copp@hydroone.com | [6 empty] | Program | AWRD EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23545 | Port Colbourne TS M11 Conversion | N.D.C.2.02 | 7374 | 205 | LINES | AIP005403 |  | AIP005403 | Yes | AIP005403 |  |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | [6 empty] | Project | EMPP AWRD | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23550 | Grid Control Network | N.T.C.3.08 | 7700 | 203 | PROJECT DELIVERY | AIP000985 | AIP000985 | AIP000985 | No | AIP000985 | Local PSMC Network Sustainment | GP-02 | Grid Control Network Sustainment | Integrating Operating Infrastructure | Miroslav.Kostic@HydroOne.com | Andrew.Webb@HydroOne.com | General Plant | 0 | 0 | 02 - Expectation (no agreement) | 0 | Program | AWRD EMPP | Executing | Short Term Planning | # of sites/upgrades | 7315994.6623 | 6881630.2261 | 6961140.7652 | 3225680.3798 | 3250190.4308 | 3286732.6213 | 0 | 0 | 0 | 0 | 7315994.6623 | 6881630.2261 | 6961140.7652 | 3225680.3798 | 3250190.4308 | 3286732.6213 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Asset Optimal (Modified - Tx Decision)
23555 | Integrated System Operations Centre - New Facility | N.C.C.3.01 | 4342 | 212 | INFO SOLUTIONS DIVISION | AIP000071 | AIP000071 | AIP000071 | No | AIP000071 | Integrated System Operations Centre - New Facility Development | GP-01 | Integrated System Operations Centre - New Facility Development | Common Oper Infrast & Control Facilities | Godfrey.Holder@HydroOne.com | Daniel.Lam@HydroOne.com | General Plant | Central | TBD | 03 - None (default) | TBD | Project | AWRD EMPP | Executing | Executing |  | 43899999.88 | 72389042.8619 | 6119167.9141 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43899999.88 | 72389042.8619 | 6119167.9141 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43049 | 43861 | False |  | True | Maintain compliance with NERC EOP-008. | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Asset Optimal
23557 | Buchanan TS Furnace Replacement 2014 | N.T.C.1.28 | 7236 | 215 | FACILITIES & REAL ESTATE |  |  |  | No |  |  |  |  | Transmission Site Facilities | cindy.copp@hydroone.com | [6 empty] | Project | EMPP AWRD | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23558 | Thunder Bay Maintenance Center - Humidifier Instal | N.C.C.1.50 | 7236 | 215 | FACILITIES & REAL ESTATE |  |  |  | No |  |  |  |  | Real Estate Facilities | cindy.copp@hydroone.com | [6 empty] | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23559 | Sudbury OC Building/ Yard Improvements 2014 | N.C.C.1.50 | 7236 | 215 | FACILITIES & REAL ESTATE |  |  |  | No |  |  |  |  | Real Estate Facilities | cindy.copp@hydroone.com | [6 empty] | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23561 | Z1E: Connect Windsor Solar Project | N.T.C.2.12 | 7700 | 203 | PROJECT DELIVERY | AIP005482 |  | AIP005482 | Yes | AIP005482 |  |  |  | Generator Customer Connection | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23562 | CSO Efficiency Enhancement | N.D.C.2.60 | 4339 | 212 | INFO SOLUTIONS DIVISION | UNPLND |  |  | Yes |  |  |  |  | IT Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | init EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23563 | CSO Efficiency Enhancement OM&A | N.D.M.2.60 | 4339 | 212 | INFO SOLUTIONS DIVISION | AIP005418A |  | AIP005418 | Yes | AIP005418 |  |  |  | IT Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | EMPP init | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23565 | Insulator/Pothead/Recoating Program | N.T.M.1.16 | 7370 | 206 | TX LINES AND STATIONS | AIP001048B |  | AIP001048 | Yes | AIP001048 |  |  |  | Power Equipment | Mike.Tanaskovic@HydroOne.com | [6 empty] | Program | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23566 | Field Metering Services Installation Labor Capital | N.D.C.1.09 | 7374 | 205 | LINES | AIP005358 | AIP005358 | AIP005358 | No | AIP005358 | Field Metering Services Installation Labor Capital | ISD-SA-02 | Metering Infrastructure Sustainment Program | Metering | Peter.Mitskos@HydroOne.com | Dominic.Consorti@HydroOne.com | System Access | 0 | 0 | 03 - None (default) | 0 | Program | AWRD EMPP | Executing | Short Term Planning | # Of Devices | 7864306.1062 | 8016212.5908 | 8176433.6508 | 8339434.9154 | 8499583.1435 | 0 | 0 | 0 | 0 | 0 | 8456243.125 | 8619583.431 | 8791864.1406 | 8967134.3177 | 9139336.7134 | 0 | 0 | 0 | 0 | 0 | -591937.0187 | -603370.8402 | -615430.4898 | -627699.4022 | -639753.5699 | 0 | 0 | 0 | 0 | 0 | -7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20265 | 20265 | 20265 | 20265 | 20265 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
23568 | Kirkland Lake TS - Indian Chute GS Re-connection | N.D.C.2.02 | 7374 | 205 | LINES | AIP000183 |  | AIP000183 | Yes | AIP000183 | (1) System upgrade driven by load growth | ISD-SS-02 | System Upgrades Driven by Load Growth | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Michael.Medeiros@HydroOne.com | System Service | 0 | 0 | 03 - None (default) | Not Required | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23569 | Trans. Prot. Replacement due to 2dn Harm. Misops | N.T.C.1.19 | 7700 | 203 | PROJECT DELIVERY | AIP005455 | AIP005455 | AIP005455 | No | AIP005455 | Transformer Protection Replacement due to 2nd Harmonic Misoperations | SR-10 | Transformer Protection Replacement | Protection Control & Metering Equip | Miroslav.Kostic@HydroOne.com | Sasa.Maljukan@HydroOne.com | System Renewal | N/A | 0 | 03 - None (default) | 0 | Project | ACTN EMPP | Executing | Executing |  | 3771244.6673 | 3811645.6645 | 2995448.9841 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3771244.6673 | 3811645.6645 | 2995448.9841 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44180 | [13 empty] | FALSE |  | 0 | 0 | Vulnerable
23570 | iMDS Station Refurbishments | N.D.C.1.08 | 7700 | 203 | PROJECT DELIVERY | AIP000160B | AIP000160 | AIP000160 | No | AIP000160 | DS Station Refurbishment Program |  |  | Distributing & Regulating Stations | emre.aydin@HydroOne.com | Nathan.Cox@hydroone.com | System Renewal | N/A | 0 | 03 - None (default) | 0 | Program | EMPP ACTN | Executing | Short Term Planning | # of Stations | 5724126.2746 | 13618083.3763 | 3971614.3129 | 4053314.5809 | 4134244.7942 | 0 | 0 | 0 | 0 | 0 | 6154974.4889 | 14643100.4046 | 4270553.0246 | 4358402.7752 | 4445424.5099 | 0 | 0 | 0 | 0 | 0 | -430848.2142 | -1025017.0283 | -298938.7117 | -305088.1943 | -311179.7157 | 0 | 0 | 0 | 0 | 0 | -7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 6 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Plan B - Modified - Scenario 1
23571 | Caledonia TS M3 Conversion | N.D.C.2.02 | 7374 | 205 | LINES | AIP000183 |  | AIP000183 | Yes | AIP000183 | (1) System upgrade driven by load growth | ISD-SS-02 | System Upgrades Driven by Load Growth | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Michael.Medeiros@HydroOne.com | System Service | 0 | 0 | 03 - None (default) | Not Required | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23572 | MeadowvaleTS M3 ID22460 TX 3.3MW CCS- Mississauga | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23573 | Buchanan Grounding upgrade | N.T.C.1.40 | 7700 | 203 | PROJECT DELIVERY | AIP005013 |  | AIP005013 | Yes | AIP005013 | Buchanan TS: 115 kV Switchyard & Component Replacement |  |  | Western Zone Station/Yard Investments | James.Mardegan@HydroOne.com | mark.truchanowicz@hydroone.com | System Renewal | Western | Not Required | 03 - None (default) | Not Required | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23575 | Picton OC Carbon Dioxide Detection Installation | N.D.C.1.50 | 7236 | 215 | FACILITIES & REAL ESTATE |  |  |  | No |  |  |  |  | Real Estate Facilities | cindy.copp@hydroone.com | [6 empty] | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23576 | Perth OC Roof Improvements 2014 | N.D.C.1.50 | 7236 | 215 | FACILITIES & REAL ESTATE |  |  |  | No |  |  |  |  | Real Estate Facilities | cindy.copp@hydroone.com | [6 empty] | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23577 | DS Herbicide Applications | N.D.M.1.04 | 7362 | 204 | FORESTRY | AIP000256B | AIP000256 | AIP000256 | No | AIP000256 | DS Preventive Maintenance - Ground and Sites |  |  | Distributing and Regulating Stations | emre.aydin@HydroOne.com | patrick.howe@hydroone.com | System O&M | N/A | 0 | 03 - None (default) | 0 | Program | AWRD EMPP | Executing | Short Term Planning | # of Orders | 672806.2923 | 693223.9726 | 708382.0665 | 724133.5872 | 737624.9851 | 0 | 0 | 0 | 0 | 0 | 672806.2923 | 693223.9726 | 708382.0665 | 724133.5872 | 737624.9851 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2295 | 2295 | 2295 | 2295 | 2295 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
23578 | CSO Efficiency Initiatives & Ramp Down | N.D.M.4.01 | 4175 | 202 | CUSTOMER CARE SERVICES | UNPLND |  |  | Yes |  |  |  |  | Customer Care Services Dx | Imran.Merali@HydroOne.com | [6 empty] | Project | EMPP AWRD | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23579 | Merivale MTS: Station Upgrade | N.T.C.2.11 | 7700 | 203 | PROJECT DELIVERY | AIP005250 | AIP005250 | AIP005250 | No | AIP005250 | Merivale MTS: Station Upgrade | 0 |  | Load Customer Connection | Robert.Reinmuller@HydroOne.com | J.Brent.Currie@HydroOne.com | System Access | 0 | Not Required | 01 - Agreement (current/future) | Required | Project | EMPP ACCP | Executing | Executing |  | 55685.0634 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1267836.9534 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -9.0206e-11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1212151.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43388 | [13 empty] | FALSE |  | 0 | 0 | Alternative 1
23580 | New Liskeard Bldg Improvements | N.D.C.1.50 | 7236 | 215 | FACILITIES & REAL ESTATE |  |  |  | No |  |  |  |  | Real Estate Facilities | cindy.copp@hydroone.com | [6 empty] | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23581 | Brockville OC Site Improvements 2014 | N.D.C.1.50 | 7236 | 215 | FACILITIES & REAL ESTATE |  |  |  | No |  |  |  |  | Real Estate Facilities | cindy.copp@hydroone.com | [6 empty] | Project | EMPP AWRD | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23582 | Line Refurbishment - N21W/N22W | N.T.C.1.12 | 7700 | 203 | PROJECT DELIVERY | AIP005372 | AIP005372 | AIP005372 | No | AIP005372 | N21W/N22W, Sarnia Scott TS-Buchanan TS, Str. Refurb. | SR-19 | Transmission Line Refurbishment - End of Life ACSR, Copper Conductors & Structures | Overhead Lines Component Refurb & Repl | hassan.hamzeh@hydroone.com | Deniz.Turkben@HydroOne.com | System Renewal | Western | Not Required | 03 - None (default) | Not Required | Project | ACCP EMPP | Executing | Executing |  | 13220650.6057 | 9901670.5895 | 911461.6889 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15023466.5974 | 11251898.3971 | 1035751.9192 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1802815.9917 | -1350227.8077 | -124290.2303 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43041 | 43814 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Proceed with complete line refurbishment
23583 | Trout Lake TS M5 ID19960-TX-North Bay Hydro | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23584 | Tillsonburg TS-M2-Tx work_DG 281 and 282 | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP005549 | AIP005549 | AIP005549 | No | AIP005549 | Tillsonburg TS-M2-Tx work_DG 281 and 282 | 0 |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Chen.Wang@HydroOne.com | System Access | 0 | 0 | 03 - None (default) | 0 | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0.0098282 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0098282 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42519 | [13 empty] | FALSE |  | 0 | 0 | Tillsonburg TS-M2-Tx work_DG 281 and 282
23587 | Tx Lines - RoW G&S Planned Corrective Maintenance | N.T.M.1.07 | 7370 | 206 | TX LINES AND STATIONS | AIP005649B | AIP005649 | AIP005649 | No | AIP005649 | Grounds & Sites Corrective Maintenance | 0 |  | Rights of Way | hassan.hamzeh@hydroone.com | Shannon.O'Keefe@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | ACTN EMPP | Executing | Short Term Planning | # of Work Orders | 353075.9873 | 459236.9968 | 460162.5424 | 471172.4505 | 471394.2275 | 481440.4034 | 0 | 0 | 0 | 0 | 353075.9873 | 459236.9968 | 460162.5424 | 471172.4505 | 471394.2275 | 481440.4034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | True | False |  | False | False | True | False | FALSE |  | 0 | 0 | Asset Optimal (Modified -Tx Decision)
23588 | Mobility | N.C.M.1.25 | 4339 | 212 | INFO SOLUTIONS DIVISION | AIP005481 | AIP005481 | AIP005481 | No | AIP005481 | Mobility | 0 |  | Business Telecom | lincoln.frost-hunt@hydroone.com | robert.hosford@hydroone.com | System O&M | N/A | 0 | 03 - None (default) | 0 | Program | AWRD | Short Term Planning | Short Term Planning |  | 475001.82 | 475001.56 | 475001.69 | 474958.92 | 474958.72 | 474959.08 | 0 | 0 | 0 | 0 | 475001.82 | 475001.56 | 475001.69 | 474958.92 | 474958.72 | 474959.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False | Agreements/Contracts with Telecommuncation Service Providers such as Bell, Rogers etc. | False |  | True |  | False | False |  | False | False | True | False | FALSE |  | 0 | 0 | Vulnerable - Tx Contraint Reduction
23591 | Kingston OC Improvements | N.C.C.1.50 | 7236 | 215 | FACILITIES & REAL ESTATE |  |  |  | No |  |  |  |  | Real Estate Facilities | cindy.copp@hydroone.com | [6 empty] | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23596 | Purchase of Spare Transformers Program | N.T.C.1.46 | 7700 | 203 | PROJECT DELIVERY | AIP000559 | AIP000559 | AIP000559 | No | AIP000559 | Purchase of Transformer Operating Spares | SR-09 | Transmission Station Demand and Spares | Tx Station Demand and Spares | James.Mardegan@HydroOne.com | peter.zhao@hydroone.com | System Renewal | 0 | 0 | 03 - None (default) | 0 | Program | EMPP INSC | Executing | Short Term Planning | # of Transformers | 23129429.5015 | 8353798.8687 | 8450342.5633 | 8515796.1436 | 8580502.7635 | 8676974.2236 | 0 | 0 | 0 | 0 | 23363060.1026 | 8438180.6755 | 8535699.5589 | 8601814.2864 | 8667174.5086 | 8764620.4279 | 0 | 0 | 0 | 0 | -233630.601 | -84381.8068 | -85356.9956 | -86018.1429 | -86671.7451 | -87646.2043 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Asset Optimal (Modified - Tx Decision)
23597 | Demand Capital - Equipment Failure (Breakers) | N.T.C.1.46 | 7370 | 206 | TX LINES AND STATIONS | AIP000377 | AIP000377 | AIP000377 | No | AIP000377 | Demand Capital - Breaker | SR-09 | Transmission Station Demand and Spares | Tx Station Demand and Spares | James.Mardegan@HydroOne.com | Donald.Mastrangelo@HydroOne.com | System Renewal | 0 | 0 | 03 - None (default) | 0 | Program | ACTN EMPP | Executing | Short Term Planning | # of Circuit Breaker | 1140349.2181 | 1158448.7987 | 1171926.0635 | 1181063.3432 | 1190096.4617 | 1203563.7143 | 0 | 0 | 0 | 0 | 1226181.955 | 1245643.8696 | 1260135.5522 | 1269960.5841 | 1279673.6147 | 1294154.5316 | 0 | 0 | 0 | 0 | -85832.7368 | -87195.0709 | -88209.4887 | -88897.2409 | -89577.153 | -90590.8172 | 0 | 0 | 0 | 0 | -7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Demand
23598 | Demand Capital - Equipment Failure (Transformers) | N.T.C.1.46 | 7370 | 206 | TX LINES AND STATIONS | AIP000554 | AIP000554 | AIP000554 | No | AIP000554 | Demand Capital - Power Transformers | SR-09 | Transmission Station Demand and Spares | Tx Station Demand and Spares | James.Mardegan@HydroOne.com | peter.zhao@hydroone.com | System Renewal | N/A | 0 | 03 - None (default) | 0 | Program | ACTN EMPP IESO | Executing | Short Term Planning | # of Transformers | 8086221.1079 | 8214564.3134 | 8310132.8294 | 8374925.2817 | 8438978.3087 | 8534475.284 | 0 | 0 | 0 | 0 | 8251246.0285 | 8382208.483 | 8479727.377 | 8545842.1241 | 8611202.3558 | 8708648.2489 | 0 | 0 | 0 | 0 | -165024.9206 | -167644.1697 | -169594.5475 | -170916.8425 | -172224.0471 | -174172.965 | 0 | 0 | 0 | 0 | -2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Asset Optimal
23599 | Power Transformer Capital Refurbishment Program | N.T.C.1.46 | 7370 | 206 | TX LINES AND STATIONS | AIP000563 | AIP000563 | AIP000563 | No | AIP000563 | Transformers Capital Refurbishment Program | 0 |  | Tx Station Demand and Spares | James.Mardegan@HydroOne.com | peter.zhao@hydroone.com | System Renewal | 0 | 0 | 03 - None (default) | 0 | Program | EMPP ACTN | Executing | Short Term Planning | # of Transformers | 661507.4665 | 672578.0024 | 680402.7726 | 685707.6742 | 690952.0655 | 699201.1263 | 0 | 0 | 0 | 0 | 668189.3601 | 679371.7196 | 687275.5279 | 692634.0143 | 697931.3793 | 706263.764 | 0 | 0 | 0 | 0 | -6681.8936 | -6793.7172 | -6872.7553 | -6926.3401 | -6979.3138 | -7062.6376 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Intermediate
23600 | Rabbit Lake TS Septic Tank 2015 | N.T.C.1.28 | 7236 | 215 | FACILITIES & REAL ESTATE |  |  |  | No |  |  |  |  | Transmission Site Facilities | cindy.copp@hydroone.com | [6 empty] | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23602 | Sale of 115kV Transmission Line M3K | N.T.C.2.03 | 7700 | 203 | PROJECT DELIVERY |  |  |  | No |  |  |  |  | Network Transfer Capability | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23603 | NERC CIP Version 5 - Development | N.T.M.1.29 | 4514 | 212 | INFO SOLUTIONS DIVISION | AIP005306 |  | AIP005306 | Yes | AIP005306 |  |  |  | NERC Cyber Security Compliance Readiness | lincoln.frost-hunt@hydroone.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23605 | Purchase of Breaker Operating Spares | N.T.C.1.46 | 7700 | 203 | PROJECT DELIVERY | AIP000380 | AIP000380 | AIP000380 | No | AIP000380 | Purchase of Strategic Breaker Spares | SR-09 | Transmission Station Demand and Spares | Tx Station Demand and Spares | James.Mardegan@HydroOne.com | kristoffer.hammel@hydroone.com | System Renewal | 0 | 0 | 03 - None (default) | 0 | Program | ACTN EMPP | Executing | Short Term Planning | # breakers | 415036.628 | 421909.013 | 426784.9883 | 430090.6629 | 433358.7088 | 0 | 0 | 0 | 0 | 0 | 415036.628 | 421909.013 | 426784.9883 | 430090.6629 | 433358.7088 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Vulnerable
23606 | C25H – Line Refurbishment | N.T.C.1.12 | 7700 | 203 | PROJECT DELIVERY | AIP000482 |  | AIP000482 | Yes | AIP000482 |  |  |  | Overhead Lines Component Refurb & Repl | hassan.hamzeh@hydroone.com | [6 empty] | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23609 | Stratford TS: T1 & Component Replacement | N.T.C.1.40 | 7700 | 203 | PROJECT DELIVERY | AIP005506 |  | AIP005506 | Yes | AIP005506 |  |  |  | Western Zone Station/Yard Investments | James.Mardegan@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23610 | Yellow Falls Hydroelectric | N.T.C.2.12 | 7700 | 203 | PROJECT DELIVERY | AIP005485 | AIP005485 | AIP005485 | No | AIP005485 | Yellow Falls GS | 0 |  | Generator Customer Connection | Robert.Reinmuller@HydroOne.com | Qasim.raza@hydroone.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1497000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1497000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43281 | True | Customer requested work. | True | Transmission license requirement to connect customer. | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Alternative 1
23615 | Horner TS - Build 230-28-28kV Station | N.T.C.2.11 | 7700 | 203 | PROJECT DELIVERY | AIP005474 | AIP005474 | AIP005474 | No | AIP005474 | Horner TS - Build 230-28-28kV Station | SA-02 | Horner TS: Build a Second 230/27.6kV Station | Load Customer Connection | Robert.Reinmuller@HydroOne.com | Eva.Ping@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | DETL AWRD | Short Term Planning | Short Term Planning |  | 323935.734 | 2006861.4987 | 1923400.9265 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2443935.734 | 14966861.4987 | 22763551.6403 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2.2204e-10 | 0 | -110150.7139 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3.1363 | 0 | -2120000 | -12960000 | -20730000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43235 | 44165 | True | Customer requested work. | False | Transmission license requirement to connect customers. | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Alternative 1
23616 | Runnymede TS - 115-28kV Station plus KxW upgrades | N.T.C.2.11 | 7700 | 203 | PROJECT DELIVERY | AIP005475 | AIP005475 | AIP005475 | No | AIP005475 | Runnymede TS - 115-28kV Station plus KxW upgrades | 0 |  | Load Customer Connection | Robert.Reinmuller@HydroOne.com | nafiz.somjee@hydroone.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20851040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -20851040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43434 | [13 empty] | FALSE |  | 0 | 0 | Alternative 1
23617 | H29/H30: Reconductor 230kV Circuits | N.T.C.2.11 | 7700 | 203 | PROJECT DELIVERY | AIP006020 | AIP006020 | AIP006020 | No | AIP006020 | H29/H30: Reconductor 230kV Circuits | 0 |  | Load Customer Connection | Robert.Reinmuller@HydroOne.com | Quyen.Diep@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 480790.9448 | 762607.61 | 2367769.6781 | 2499999.92 | 0 | 0 | 0 | 0 | 0 | 0 | 480790.9448 | 762607.61 | 2367769.6781 | 2499999.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44576 | 45436 | True | Requested by regional planning working group to meet future load growth. | True | To meet IESO Ontario Resource and Transmission Assessment Criteria, and is identified in the Regional Infrastructure Planning Report for GTA West | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Alternative 1
23618 | Connect New DESN near Halton TS | N.T.C.2.11 | 7700 | 203 | PROJECT DELIVERY | AIP005473 | AIP005473 | AIP005473 | No | AIP005473 | Connect New DESN near Halton TS | SA-07 | Halton TS: Build a Second 230/27.6kV Station | Load Customer Connection | Robert.Reinmuller@HydroOne.com | Gene.Ng@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 69138.9878 | 970048.3397 | 343831.8361 | 7585381.0412 | 0 | 0 | 0 | 0 | 0 | 0 | 248705.6778 | 3483981.9797 | 1241669.8361 | 27696941.0412 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1.1102e-10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -179566.69 | -2513933.64 | -897838 | -20111560 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43848 | 44347 | True | Refer to Regional Infrastructure Planning report for GTA West. | True | Transmission license requirement to connect customers. | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Alternative 1
23619 | V41H/V42H - Connect Peel Energy Recovery Centre | N.T.C.2.12 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Generator Customer Connection | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23620 | Caledonia TS M3 Extension | N.D.C.2.02 | 7374 | 205 | LINES | AIP005888 | AIP005888 | AIP005888 | No | AIP005888 | Caledonia TS M3 Extension | ISD-SS-02 | System Upgrades Driven by Load Growth | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Helen.Guo@HydroOne.com | System Service | Western | 0 | 03 - None (default) | 0 | Project | DETL ACTN | Short Term Planning | Short Term Planning |  | 490696.194 | 594108.306 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 557609.3114 | 675123.075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -66913.1174 | -81014.769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43343 | 43769 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
23621 | M30A/M31A Conductor Upgrade | N.T.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP005452 | AIP005452 | AIP005452 | No | AIP005452 | M30A/M31A Conductor Upgrade | SS-05 | Merivale TS to Hawthorne TS: 230kV Conductor Upgrade | Network Transfer Capability | Robert.Reinmuller@HydroOne.com | Jean.Morneau@HydroOne.com | System Service | 0 | 0 | 02 - Expectation (no agreement) | 0 | Project | IESO ACTN DETL | Short Term Planning | Short Term Planning |  | 245405.8591 | 245938.9092 | 7322592.3597 | 9615818.896 | 1906519.025 | 0 | 0 | 0 | 0 | 0 | 245405.8591 | 245938.9092 | 7322592.3597 | 9615818.896 | 1906519.025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43738 | 44712 | True | IESO Request | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Alternative 1
23623 | CSO DBOT | N.D.M.4.01 | 4175 | 202 | CUSTOMER CARE SERVICES | UNPLND |  |  | Yes |  |  |  |  | Customer Care Services Dx | Imran.Merali@HydroOne.com | [6 empty] | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23624 | 2015-2020 OPA First Nations | N.D.M.2.50 | 1144 | 220 | STRATEGY & CONSERV | AIP005432 | AIP005432 | AIP005432 | No | AIP005432 | 2015-2020 First Nations CDM programs |  |  | Conservation and Demand Management | Imran.Merali@HydroOne.com | Imran.Merali@HydroOne.com | System O&M | 0 | 0 | 01 - Agreement (current/future) | 0 | Program | EMPP init | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000000.04 | 4000000 | 3000000 | 3000000 | 2999999.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4000000.04 | -4000000 | -3000000 | -3000000 | -2999999.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | 2015-2020 First Nations - Base Case
23625 | Placeholder Corporate Performance Data - CAP | N.C.C.2.60 | 4339 | 212 | INFO SOLUTIONS DIVISION | AIP005502 | AIP005502 | AIP005502 | No | AIP005502 | Corporate Performance Reporting | 0 |  | IT Business Solution Development | jj.blais@HydroOne.com | hany.eskandar@hydroone.com | General Plant | 0 | 0 | 03 - None (default) | 0 | Project | AWRD EMPP | Executing | Executing |  | 0 | 3883318.5528 | 1677836.3635 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3883318.5528 | 1677836.3635 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42551 | 44196 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Asset Optimal
23626 | Placeholder Corporate Performance Data – OMA | N.C.M.2.60 | 4339 | 212 | INFO SOLUTIONS DIVISION | AIP005504 |  | AIP005504 | Yes | AIP005504 | Enterprise Analytics – Reliability Analytics/CPR |  |  | IT-Business Solution Development | jj.blais@HydroOne.com | hany.eskandar@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23627 | Physical Security Monitoring Services | N.T.M.1.29 | 838 | 212 | INFO SOLUTIONS DIVISION | AIP001149 | AIP001149 | AIP001149 | No | AIP001149 | Physical Security Monitoring Services (External) | 0 |  | NERC Cyber Security Compliance Readiness | lincoln.frost-hunt@hydroone.com | Sherry.Wilging@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | AWRD EMPP | Executing | Short Term Planning | # of PSP | 2273542.7215 | 2379069.0623 | 2433054.8679 | 2488308.1678 | 2539008.4317 | 2589592.0068 | 0 | 0 | 0 | 0 | 2273542.7215 | 2379069.0623 | 2433054.8679 | 2488308.1678 | 2539008.4317 | 2589592.0068 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | True | CIP-006, 014 | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Asset Optimal
23628 | Placeholder OGCC Major Tools Assessment/RFI | N.C.M.3.01 | 4514 | 212 | INFO SOLUTIONS DIVISION | AIP005360 | AIP005360 | AIP005360 | No | AIP005360 | OGCC Major Tools Assessment/RFI | 0 |  | Common Operating Infrastructure | Godfrey.Holder@HydroOne.com | Mitchell.Wotton@HydroOne.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | init | Short Term Planning | Short Term Planning | Retainer | 0 | 100000 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | False |  | False | False | True | True | TRUE | The OGCC utilizes various core network systems to manage to Operations of both the Transmission and Distribution System. This investment is a strategic initiative to analyze possible integration in the next version lifecycle upgrades for ORMS, DMS, and the NMS. These systems are multi-million dollar network applications that are currently sourced individually by three different vendors with minimal integration. The Major tools assessment investment will undergo a thorough investigation of these tools and possible integration techniques to reduce costs in the following version upgrades. | 0 | 0 | Asset optimal
23629 | TOU Billing & Meter Reading Optimiza - Capital | N.D.C.2.06 | 4339 | 212 | INFO SOLUTIONS DIVISION |  |  |  | No |  |  |  |  | Smart Grid | ryan.boudreau@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23630 | Bridgman PT Installation &Revenue Metering Upgrade | N.T.C.1.43 | 7700 | 203 | PROJECT DELIVERY | AIP005513 | AIP005513 | AIP005513 | No | AIP005513 | Bridgman TS: PT Installation & Revenue Metering Upgrade | 0 |  | Greater Toronto Area Zone Station/Yard Investments | James.Mardegan@HydroOne.com | michael.xavier@hydroone.com | System Renewal | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | AWRD EMPP | Executing | Executing |  | 307647.4384 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1193914.6973 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -23156.2588 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4.636 | 7 | -863111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43399 | [13 empty] | FALSE |  | 0 | 0 | Component Replacements
23631 | B4V - Connect Southgate Solar Project | N.T.C.2.12 | 7700 | 203 | PROJECT DELIVERY | AIP005483 |  | AIP005483 | Yes | AIP005483 |  |  |  | Generator Customer Connection | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23632 | Bruce A TS & Longwood TS: Reactor Switching Scheme | N.T.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP005453 | AIP005453 | AIP005453 | No | AIP005453 | Bruce A TS & Longwood TS: Reactor Switching Scheme | 0 |  | Network Transfer Capability | Robert.Reinmuller@HydroOne.com | Alessia.Dawes@HydroOne.com | System Service | 0 | 0 | 03 - None (default) | 0 | Project | EMPP ACTN | Executing | Executing |  | 508326.069 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 508326.069 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43403 | [13 empty] | FALSE |  | 0 | 0 | Alternative 1
23633 | Uprate Q3N and Q4N | N.T.C.2.02 | 7700 | 203 | PROJECT DELIVERY |  |  |  | No |  |  |  |  | Local Area Supply | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23634 | Gemini Power - Smooth Rock Fls Upgrade | N.T.C.2.12 | 7700 | 203 | PROJECT DELIVERY | AIP005484 | AIP005484 | AIP005484 | No | AIP005484 | Gemini Power Smooth Rock Falls Upgrade | 0 |  | Generator Customer Connection | Robert.Reinmuller@HydroOne.com | Kirpal.Bahra@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -13440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42995 | [13 empty] | FALSE |  | 0 | 0 | Alternative 1
23635 | Opus One; Dist Energy Mgmt & Storage Ntwrk (DEMSN) | N.D.M.2.22 | 4230 | 213 | PLANNING | AIP005089 |  | AIP005089 | Yes | AIP005089 | [11 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23637 | HV UG Cable - Replace Pumping Plant HMI | N.T.C.1.15 | 7700 | 203 | PROJECT DELIVERY | AIP005370 | AIP005370 | AIP005370 | No | AIP005370 | HV UG Cable - Replace Pumping Plant HMI | 0 |  | U/G Lines Cable Sys & Comp Refurb & Repl | hassan.hamzeh@hydroone.com | Tyler.Wales@HydroOne.com | System Renewal | 0 | Not Required | 03 - None (default) | Not Required | Project | ACCP EMPP | Executing | Executing |  | 714572.2204 | 811210.5448 | 0.0098282 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 714572.2204 | 811210.5448 | 0.0098282 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43768 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Alternative 1
23638 | Kleinburg TS M6 Mayfield Rd Line Extension | N.D.C.2.02 | 7374 | 205 | LINES | AIP005644 | AIP005644 | AIP005644 | No | AIP005644 | Kleinburg TS M6 Mayfield Rd Line Extension | ISD-SS-02 | System Upgrades Driven by Load Growth | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Mark.VanTol@hydroone.com | System Service | Greater Toronto Area | 0 | 03 - None (default) | 0 | Project | DETL ACTN | Short Term Planning | Short Term Planning |  | 1000808.881 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000808.881 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43100 | 43405 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
23639 | AMI Network & Meter Reading Enhancements | N.D.C.1.09 | 7374 | 205 | LINES | AIP005003 |  | AIP005003 | Yes | AIP005003 | Metering CDMA Replacement |  |  | Metering | Peter.Mitskos@HydroOne.com | Dominic.Consorti@HydroOne.com | System Access | 0 | 0 | 03 - None (default) | 0 | Program | init | Short Term Planning | Short Term Planning | # of Meters | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23642 | Placeholder ORMS Enhancements | N.D.C.3.08 | 4514 | 212 | INFO SOLUTIONS DIVISION | AIP005374 | AIP005374 | AIP005374 | No | AIP005374 | ORMS Enhancements |  |  | Operating Infrastructure | Godfrey.Holder@HydroOne.com | william.ilie@hydroone.com | General Plant | 0 | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 120097.0657 | 430380.3434 | 440712.7315 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120097.0657 | 430380.3434 | 440712.7315 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43115 | 44134 | [13 empty] | FALSE |  | 0 | 0 | Critical Spend Plan
23643 | Power Express Feeder Barrie TS to OGCC | N.D.C.3.08 | 2051 | 205 | LINES | AIP005435 | AIP005435 | AIP005435 | No | AIP005435 | Power Express Feeder - Barrie TS to OGCC |  |  | Operating Infrastructure | Godfrey.Holder@HydroOne.com | Natalie.Briggs@HydroOne.com | System Service | N/A | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 714156.6677 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 714156.6677 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44257 | 44532 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
23644 | Inergi Base ITO | N.C.M.1.70 | 4339 | 212 | INFO SOLUTIONS DIVISION | AIP000091A | AIP000091 | AIP000091 | No | AIP000091 | Inergi Sustainment | 0 |  | IT - Sustainment and Operations | lincoln.frost-hunt@hydroone.com | robert.hosford@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | EMPP AWRD | Executing | Short Term Planning | Retainer | 27046000 | 25836000 | 23336000 | 23336000 | 23336000.12 | 23335999.88 | 0 | 0 | 0 | 0 | 27046000 | 25836000 | 23336000 | 23336000 | 23336000.12 | 23335999.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False | Signed Contract with Inergi. | False |  | True |  | False | False |  | False | False | True | False | FALSE |  | 0 | 0 | Intermediate
23645 | TOU Billing & Meter Reading Optimization - OM&A | N.D.M.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION | AIP000354 |  | AIP000354 | Yes | AIP000354 | Billing - Service Enhancements |  |  | IT Business Solution Development | jj.blais@HydroOne.com | Imran.Merali@HydroOne.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning | 202-D503003 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23646 | HV UG Cable - Replace C5E/C7E | N.T.C.1.15 | 7700 | 203 | PROJECT DELIVERY | AIP005366 | AIP005366 | AIP005366 | No | AIP005366 | HV UG Cable - Replace C5E/C7E | SR-27 | C5E/C7E Underground Cable Replacement | U/G Lines Cable Sys & Comp Refurb & Repl | hassan.hamzeh@hydroone.com | Tyler.Wales@HydroOne.com | System Renewal | Greater Toronto Area | Required | 03 - None (default) | Required | Project | DETL ACTN | Short Term Planning | Short Term Planning |  | 4040718.9859 | 3944255.9599 | 1378841.4858 | 10502085.4054 | 10145339.2582 | 9660830.137 | 11890249.96 | 0 | 0 | 0 | 4061024.1065 | 3964076.3416 | 1385770.3375 | 10554859.704 | 10196320.8625 | 9709377.0221 | 11950000 | 0 | 0 | 0 | -20305.1205 | -19820.3817 | -6928.8517 | -52774.2985 | -50981.6043 | -48546.8851 | -59750.04 | 0 | 0 | 0 | -0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43929 | 45627 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Alternative 1
23647 | Strachan TS T12/T14; T12 & Component Replacement | N.T.C.1.43 | 7700 | 203 | PROJECT DELIVERY | AIP005391 | AIP005391 | AIP005391 | No | AIP005391 | Strachan TS: T12 & Component Replacements | SR-05 | Load Station Transformer Replacement Projects | Greater Toronto Area Zone Station/Yard Investments | James.Mardegan@HydroOne.com | michael.xavier@hydroone.com | System Renewal | Greater Toronto Area | Not Required | 01 - Agreement (current/future) | Not Required | Project | EMPP ACCP | Executing | Executing |  | 3140688.2358 | 4743189.4826 | 1998669.9054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3140688.2358 | 5786691.1688 | 2198669.9054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1043501.6862 | 2.2204e-10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -9.2437 | 0 | 0 | 0 | -200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43062 | 44196 | False |  | False |  | False |  | False | True | Request for larger unit by THESL | False | False | False | False | FALSE |  | 0 | 0 | Component Replacements
23648 | Kingsville Pulford DS Conversion | N.D.C.2.02 | 7374 | 205 | LINES | AIP000183 |  | AIP000183 | Yes | AIP000183 | (1) System upgrade driven by load growth | ISD-SS-02 | System Upgrades Driven by Load Growth | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Michael.Medeiros@HydroOne.com | System Service | 0 | 0 | 03 - None (default) | Not Required | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23650 | 2015-2020 CDM Pilots | N.D.M.2.50 | 1144 | 220 | STRATEGY & CONSERV | AIP005433 | AIP005433 | AIP005433 | No | AIP005433 | 2015-2020 CDM Pilot projects |  |  | Conservation and Demand Management | Imran.Merali@HydroOne.com | Imran.Merali@HydroOne.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | AWRD EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9000000 | 13000000 | 9000000 | 7000000 | 7000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -9000000 | -13000000 | -9000000 | -7000000 | -7000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | 2015-2020 CDM Pilot Projects
23651 | Display Technology Capital Replacement | N.C.C.3.01 | 4514 | 212 | INFO SOLUTIONS DIVISION | AIP005369 | AIP005369 | AIP005369 | No | AIP005369 | Display Technology Capital Replacement | 0 |  | Common Oper Infrast & Control Facilities | Godfrey.Holder@HydroOne.com | Daniel.Lam@HydroOne.com | General Plant | N/A | Not Required | 03 - None (default) | Not Required | Project | init | Short Term Planning | Short Term Planning |  | 0 | 892930.6938 | 4934.6944 | 879163.9508 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 892930.6938 | 4934.6944 | 879163.9508 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43528 | 44530 | False |  | False |  | False |  | False | False |  | False | True | False | False | TRUE | Strategic to insure that the monitors at the BUCC is consistent with monitors at the OGCC. | 0 | 0 | Asset Optimal
23653 | Stirton TS HVAC 2015 | N.T.C.1.28 | 7236 | 215 | FACILITIES & REAL ESTATE |  |  |  | No |  |  |  |  | Transmission Site Facilities | cindy.copp@hydroone.com | [6 empty] | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23654 | Fixed Asset Capitalization Enhancement | N.C.C.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION | AIP005412 | AIP005412 | AIP005412 | No | AIP005412 | Fixed Asset & Capitalization Enhancement - CAP | 0 |  | IT Business Solution Development | jj.blais@HydroOne.com | Jun.Macabanti@hydroone.com | General Plant | 0 | 0 | 03 - None (default) | 0 | Project | EMPP AWRD | Executing | Executing |  | 460464 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 460464 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42916 | 43190 | False |  | False |  | False |  | False | False |  | False | False | False | False | TRUE | This is part of the Let's Get Great Initiative | 0 | 0 | Asset Optimal
23655 | Burleigh DS F2 1ph to 3ph Conversion | N.D.C.2.02 | 7374 | 205 | LINES | AIP005382 | AIP005382 | AIP005382 | No | AIP005382 | Burleigh DS F2 1ph to 3ph Conversion (Phase 1 of 2) | ISD-SS-02 | System Upgrades Driven by Load Growth | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Cecilia.Pang@HydroOne.com | System Service | Northern | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 733751.3578 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 833808.3612 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -100057.0033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43039 | 43405 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
23656 | Clearwater Bay voltage conversion Phase 2 | N.D.C.2.02 | 7374 | 205 | LINES | AIP005385 | AIP005385 | AIP005385 | No | AIP005385 | Clearwater Bay DS F2 Voltage Conversion (Phase 2 of 3) | ISD-SR-13 | Life Cycle Optimization & Operational Efficiency Projects | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Cecilia.Pang@HydroOne.com | System Renewal | 0 | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 2751.5839 | 907535.5035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3126.7999 | 1031290.3449 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -375.216 | -123754.8414 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43371 | 43769 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
23657 | Margach F3 voltage conversion - SD 3676 | N.D.C.2.02 | 7374 | 205 | LINES | AIP005386 | AIP005386 | AIP005386 | No | AIP005386 | Margach DS F3 Voltage Conversion | ISD-SR-13 | Life Cycle Optimization & Operational Efficiency Projects | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Cecilia.Pang@HydroOne.com | System Renewal | 0 | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 1375783.7058 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1563390.5748 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -187606.869 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43069 | 43404 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
23658 | Devlin DS F1 3 Phase | N.D.C.2.02 | 7374 | 205 | LINES | AIP005387 | AIP005387 | AIP005387 | No | AIP005387 | Devlin DS F1 3ph | ISD-SS-02 | System Upgrades Driven by Load Growth | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Cecilia.Pang@HydroOne.com | System Service | 0 | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 1008908.0269 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1146486.3942 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -137578.3673 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43008 | 43404 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
23659 | Cataraqui TS: Component Replacement | N.T.C.1.44 | 7700 | 203 | PROJECT DELIVERY | AIP005363 |  | AIP005363 | Yes | AIP005363 |  |  |  | Eastern Zone Station/Yard Investments | James.Mardegan@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23660 | Algoma TS: T5/T6 & Component Replacement | N.T.C.1.45 | 7700 | 203 | PROJECT DELIVERY | AIP005365 | AIP005365 | AIP005365 | No | AIP005365 | Algoma TS: T5/T6 & Component Replacement | SR-03 | Bulk Station Transformer Replacement Projects | Northern Zone Station/Yard Investments | James.Mardegan@HydroOne.com | Donald.Mastrangelo@HydroOne.com | System Renewal | Northern | Not Required | 03 - None (default) | Required | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 531075.1463 | 1249832.2513 | 7004419.5583 | 18781268.5369 | 18179594.4 | 4415200.24 | 0 | 0 | 0 | 0 | 571048.5444 | 1343905.6466 | 7531633.9336 | 20194912.4053 | 19547950.92 | 4747527.04 | 0 | 0 | 0 | 0 | -39973.3981 | -94073.3953 | -527214.3754 | -1413643.8684 | -1368356.52 | -332326.8 | 0 | 0 | -7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44811 | 45945 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Component Replacement
23661 | Mississagi TS: Component Replacement | N.T.C.1.45 | 7700 | 203 | PROJECT DELIVERY | AIP005362 | AIP005362 | AIP005362 | No | AIP005362 | Mississagi TS: Component Replacement | SR-04 | Bulk Station Switchgear and Ancillary Equipment Replacement Projects | Northern Zone Station/Yard Investments | James.Mardegan@HydroOne.com | Donald.Mastrangelo@HydroOne.com | System Renewal | Northern | Not Required | 03 - None (default) | Not Required | Project | init | Short Term Planning | Short Term Planning |  | 0 | 705786.595 | 886630.2232 | 4582400.4866 | 10694093.2787 | 3665392.2116 | 0 | 0 | 0 | 0 | 0 | 758910.3172 | 953365.8314 | 4927312.3512 | 11499025.0308 | 3941281.948 | 0 | 0 | 0 | 0 | 0 | -53123.7222 | -66735.6082 | -344911.8646 | -804931.7522 | -275889.7364 | 0 | 0 | 0 | 0 | -7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44134 | 45183 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Component Replacement
23662 | Widdifield SS: Component Replacement | N.T.C.1.45 | 7700 | 203 | PROJECT DELIVERY | AIP005364 |  | AIP005364 | Yes | AIP005364 |  |  |  | Northern Zone Station/Yard Investments | James.Mardegan@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23664 | Orillia TS: Spill Cont. & Component Replacements | N.T.C.1.42 | 7700 | 203 | PROJECT DELIVERY | AIP005447 | AIP005447 | AIP005447 | No | AIP005447 | Orillia TS: Spill Cont. & Component Replacements | 0 |  | Central Zone Station/Yard Investments | James.Mardegan@HydroOne.com | michael.xavier@hydroone.com | System Renewal | Central | Not Required | 01 - Agreement (current/future) | TBD | Project | ACTN EMPP | Executing | Executing |  | 168844.7356 | 0 | 0.0098282 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 181553.4791 | 0 | 0.010568 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -12708.7435 | 0 | -0.00073975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43054 | [13 empty] | FALSE |  | 0 | 0 | Component Replacements
23665 | Foundation Repair/Replace - PL | N.T.C.1.12 | 7370 | 206 | TX LINES AND STATIONS | AIP000472C |  | AIP000472 | Yes | AIP000472 | Tower Foundations |  |  | Overhead Lines Component Refurb & Repl | hassan.hamzeh@hydroone.com | TeodorConstantin.Culinescu@HydroOne.com | System Renewal | 0 | 0 | 03 - None (default) | 0 | Program | ACTN EMPP | Executing | Short Term Planning | Number of structures | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23667 | Armitage TS M22 Extension | N.D.C.2.02 | 7374 | 205 | LINES | AIP005393 | AIP005393 | AIP005393 | No | AIP005393 | Armitage TS M22 Extension | ISD-SS-02 | System Upgrades Driven by Load Growth | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Dhaval.Patel@hydroone.com | System Service | Central | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 1477854.222 | 494116.6596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1679379.7977 | 561496.2041 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -201525.5757 | -67379.5445 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43222 | 43495 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
23668 | Uxbridge RS #2 (New) | N.D.C.2.02 | 7700 | 203 | PROJECT DELIVERY | AIP005396 |  | AIP005396 | Yes | AIP005396 |  |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23669 | Beaverton M29 extension | N.D.C.2.02 | 7374 | 205 | LINES | AIP005394 |  | AIP005394 | Yes | AIP005394 |  |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23670 | Orangeville TS M3-M6 Tie Line | N.D.C.2.02 | 7374 | 205 | LINES | AIP005399 | AIP005399 | AIP005399 | No | AIP005399 | Orangeville TS M3-M6 Tie Line | ISD-SS-03 | Reliability Improvements | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Mark.VanTol@hydroone.com | System Service | Central | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 2643024.0181 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3003436.3843 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -360412.3661 | 0 | 0 | 0 | 0 | 0 | -12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44593 | 44910 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
23671 | St Thomas DS Voltage Conversion | N.D.C.2.02 | 7374 | 205 | LINES | AIP005398 | AIP005398 | AIP005398 | No | AIP005398 | St Thomas DS Voltage Conversion | ISD-SR-13 | Life Cycle Optimization & Operational Efficiency Projects | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Alexander.Hamlyn@HydroOne.com | System Renewal | Western | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 149428.0518 | 762140.4324 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 169804.6043 | 866068.6732 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -20376.5525 | -103928.2408 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43448 | 43797 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
23672 | Beckwith DS F3 Feeder Development | N.D.C.2.02 | 7374 | 205 | LINES | AIP005828 | AIP005828 | AIP005828 | No | AIP005828 | Beckwith DS F3 Development | ISD-SS-02 | System Upgrades Driven by Load Growth | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Muhammad.Sabir@HydroOne.com | System Service | Eastern | Not Required | 03 - None (default) | Not Required | Project | init | Short Term Planning | Short Term Planning |  | 200161.7762 | 1778299.5507 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200161.7762 | 1778299.5507 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43357 | 43721 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
23673 | Arnprior Area Study - Line Work | N.D.C.2.02 | 7374 | 205 | LINES | AIP000183A |  | AIP000183 | Yes | AIP000183 | (1) System upgrade driven by load growth |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Michael.Medeiros@HydroOne.com | System Service | 0 | 0 | 03 - None (default) | Not Required | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23674 | Arnprior Area Study - Station Work | N.D.C.2.02 | 7374 | 205 | LINES | AIP000183A |  | AIP000183 | Yes | AIP000183 | (1) System upgrade driven by load growth |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Michael.Medeiros@HydroOne.com | System Service | 0 | 0 | 03 - None (default) | Not Required | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23675 | Placeholder OMA for NDC260 Projects | N.D.M.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION | AIP005418B |  | AIP005418 | Yes | AIP005418 |  |  |  | IT Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23676 | Runnymede TS: T3, T4 & Switchyard Replacement | N.T.C.1.43 | 7700 | 203 | PROJECT DELIVERY | AIP005465 | AIP005465 | AIP005465 | No | AIP005465 | Runnymede TS: T3, T4 & Switchyard Replacement | SR-02 | Station Reinvestment Projects | Greater Toronto Area Zone Station/Yard Investments | James.Mardegan@HydroOne.com | michael.xavier@hydroone.com | System Renewal | Greater Toronto Area | Not Required | 03 - None (default) | TBD | Project | ACTN DETL | Short Term Planning | Short Term Planning |  | 3589357.9838 | 14893614.9754 | 6852582.5327 | 4450093.2677 | 0 | 0 | 0 | 0 | 0 | 0 | 3589357.9838 | 15178206.3443 | 7613980.5919 | 4639458.9387 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -284591.369 | -761398.0592 | -189365.671 | 0 | 0 | 0 | 0 | 0 | 0 | -3.9514 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43363 | 44459 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Component Replacements
23677 | Fairchild TS: T1, PCT & Component Replacements | N.T.C.1.43 | 7700 | 203 | PROJECT DELIVERY | AIP005466 | AIP005466 | AIP005466 | No | AIP005466 | Fairchild TS: T1, PCT & Component Replacements | SR-05 | Load Station Transformer Replacement Projects | Greater Toronto Area Zone Station/Yard Investments | James.Mardegan@HydroOne.com | michael.xavier@hydroone.com | System Renewal | Greater Toronto Area | Not Required | 03 - None (default) | TBD | Project | init | Short Term Planning | Short Term Planning |  | 0 | 617563.3086 | 886630.2232 | 4582400.4866 | 10694093.2787 | 3666358.8255 | 0 | 0 | 0 | 0 | 0 | 664046.5684 | 953365.8314 | 4927312.3512 | 11499025.0308 | 3942321.3177 | 0 | 0 | 0 | 0 | 0 | -46483.2598 | -66735.6082 | -344911.8646 | -804931.7522 | -275962.4922 | 0 | 0 | 0 | 0 | -7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44124 | 45188 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Component Replacements
23678 | Grenfel DS Load Transfer to Utopia DS | N.D.C.2.02 | 7374 | 205 | LINES | UNPLND |  |  | Yes |  |  |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | [6 empty] | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23679 | Minden TS 230kV BULK; Component Replacement | N.T.C.1.42 | 7700 | 203 | PROJECT DELIVERY | AIP005469 |  | AIP005469 | Yes | AIP005469 |  |  |  | Central Zone Station/Yard Investments | James.Mardegan@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23680 | Inergi Base ADM | N.C.M.1.70 | 4339 | 212 | INFO SOLUTIONS DIVISION | AIP000091B | AIP000091 | AIP000091 | No | AIP000091 | Inergi Sustainment | 0 |  | IT - Sustainment and Operations | lincoln.frost-hunt@hydroone.com | robert.hosford@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | EMPP AWRD | Executing | Short Term Planning | Retainer | 28326000.12 | 28167000 | 25666999.88 | 25666999.88 | 25667000 | 25667000 | 0 | 0 | 0 | 0 | 28326000.12 | 28167000 | 25666999.88 | 25666999.88 | 25667000 | 25667000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False | Signed Contract with Inergi. | False |  | True |  | False | False |  | False | False | True | False | FALSE |  | 0 | 0 | Intermediate
23681 | Replace Aviation Obstruct. Lights on Radio Towers | N.T.C.1.25 | 7700 | 203 | PROJECT DELIVERY | AIP005470 |  | AIP005470 | Yes | AIP005470 |  |  |  | Auxiliary Telecommunication Equipment | Miroslav.Kostic@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23682 | Tx Lines Insulator Replacement SGB | N.T.C.1.12 | 7700 | 203 | PROJECT DELIVERY | AIP005456 | AIP005456 | AIP005456 | No | AIP005456 | Tx Lines Insulator Replacement SGB | 0 |  | Overhead Lines Component Refurb & Repl | hassan.hamzeh@hydroone.com | Tyler.Wales@HydroOne.com | System Renewal | Central | TBD | 03 - None (default) | TBD | Project | ACCP EMPP | Executing | Executing |  | 138315.4595 | 0 | 0.0098282 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 157176.6586 | 0 | 0.011168 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -18861.199 | 0 | -0.0013402 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -7.268 | 12.00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43069 | [13 empty] | FALSE |  | 0 | 0 | Alternative 1
23683 | Birch TS M8 ID 27060 TX Thunder Bay RHSC CHP | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23684 | CxA,Cameron Falls GS-Alexander GS,Tx Line Refurb | N.T.C.1.12 | 7700 | 203 | PROJECT DELIVERY | AIP005371 | AIP005371 | AIP005371 | No | AIP005371 | Line Refurbishment - C1A/C2A/C3A | 0 |  | Overhead Lines Component Refurb & Repl | hassan.hamzeh@hydroone.com | Mohammed.Nihar@HydroOne.com | System Renewal | Northern | TBD | 03 - None (default) | TBD | Project | AWRD EMPP | Executing | Executing |  | 2352700.2453 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2673523.006 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -320822.7607 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3.0725 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43434 | [13 empty] | FALSE |  | 0 | 0 | Alternative 1
23685 | B5/6C, BurlingtonTS X WestoverCTS, Tx Line Refurb. | N.T.C.1.12 | 7700 | 203 | PROJECT DELIVERY | AIP005422 | AIP005422 | AIP005422 | No | AIP005422 | B5/6C, BurlingtonTS X WestoverCTS, Tx Line Refurb. | SR-19 | Transmission Line Refurbishment - End of Life ACSR, Copper Conductors & Structures | Overhead Lines Component Refurb & Repl | hassan.hamzeh@hydroone.com | Deniz.Turkben@HydroOne.com | System Renewal | Hamilton Niagara | TBD | 03 - None (default) | TBD | Project | ACCP EMPP | Executing | Executing |  | 7361144.2216 | 4467849.9546 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8364936.6154 | 5077102.2212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1003792.3938 | -609252.2665 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43091 | 43619 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Proceed with complete line refurbishment
23686 | Replace Legacy SONET Systems | N.T.C.1.25 | 7700 | 203 | PROJECT DELIVERY | AIP005464 | AIP005464 | AIP005464 | No | AIP005464 | Replace Legacy SONET Systems | SR-11 | Legacy SONET System Replacement | Auxiliary Telecommunication Equipment | Miroslav.Kostic@HydroOne.com | Sheraz.Majid@HydroOne.com | System Renewal | N/A | 0 | 03 - None (default) | 0 | Project | LLTM ACTN | Short Term Planning | Short Term Planning |  | 2390397.577 | 4246769.3421 | 24024127.7855 | 24180551.461 | 23587459.3705 | 15268988.96 | 8330959.92 | 0 | 0 | 0 | 2489997.476 | 4423718.0647 | 25025133.1098 | 25188074.4386 | 24570270.1776 | 15905196.8333 | 8678083.29 | 0 | 0 | 0 | -99599.899 | -176948.7226 | -1001005.3244 | -1007522.9775 | -982810.8071 | -636207.8733 | -347123.37 | 0 | 0 | 0 | -4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43753 | 45626 | False |  | False |  | False |  | False | False |  | False | True | False | False | FALSE |  | 0 | 0 | Asset Optimal
23687 | Line Refurbishment - B23C | N.T.C.1.12 | 7700 | 203 | PROJECT DELIVERY | AIP005416 | AIP005416 | AIP005416 | No | AIP005416 | B23C, Pancake JCT-Oshawa Area JCT, Tx Line Refurb. | SR-20 | Transmission Line Refurbishment - Near End of Life ACSR Conductor | Overhead Lines Component Refurb & Repl | hassan.hamzeh@hydroone.com | Deniz.Turkben@HydroOne.com | System Renewal | Eastern | Not Required | 03 - None (default) | Not Required | Project | HOLD | Short Term Planning | Short Term Planning |  | 0 | 357428.0385 | 1085830.3503 | 22811034.8957 | 25245885.4196 | 25649090.1664 | 0 | 0 | 0 | 0 | 0 | 406168.2256 | 1233898.1253 | 25921630.5633 | 28688506.1587 | 29146693.3709 | 0 | 0 | 0 | 0 | 0 | -48740.1871 | -148067.775 | -3110595.6676 | -3442620.739 | -3497603.2045 | 0 | 0 | 0 | 0 | -12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44256 | 45261 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Proceed with complete line refurbishment
23688 | Line Refurbishment - C28C | N.T.C.1.12 | 7700 | 203 | PROJECT DELIVERY | AIP005420 | AIP005420 | AIP005420 | No | AIP005420 | Tx Line Refurb. C28C, Complete Line, Chats Falls SS X Cherrywood TS (Near EoL) | SR-20 | Transmission Line Refurbishment - Near End of Life ACSR Conductor | Overhead Lines Component Refurb & Repl | hassan.hamzeh@hydroone.com | Deniz.Turkben@HydroOne.com | System Renewal | Eastern | Not Required | 03 - None (default) | Not Required | Project | HOLD | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 1824882.7411 | 1836064.4951 | 73745678.5096 | 76899415.24 | 38684800 | 0 | 0 | 0 | 0 | 0 | 2073730.3876 | 2086436.9262 | 83801907.3973 | 87385699.12 | 43960000 | 0 | 0 | 0 | 0 | 0 | -248847.6465 | -250372.4311 | -10056228.8877 | -10486283.88 | -5275200 | 0 | 0 | -12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44575 | 45995 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Proceed with complete line refurbishment (Tx Decision)
23689 | Birch TS M3 ID 27030 TX CMC CHP | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23690 | Cherrywood TS 500kV BULK; ABCB & Component Repl. | N.T.C.1.42 | 7700 | 203 | PROJECT DELIVERY | AIP005440 | AIP005440 | AIP005440 | No | AIP005440 | Cherrywood TS 230 & 500 kV: Phase 2 ABCB (26) | SR-01 | Air Blast Circuit Breaker Replacement Projects | Central Zone Station/Yard Investments | James.Mardegan@HydroOne.com | Fred.Kouhdani@HydroOne.com | System Renewal | Central | Not Required | 03 - None (default) | Not Required | Project | init | Short Term Planning | Short Term Planning |  | 152718.2088 | 382006.9946 | 442562.7361 | 12229964.0509 | 12081685.7038 | 23818305.4653 | 25832610 | 25832610 | 12916769.96 | 12916769.92 | 164213.1278 | 410760.2092 | 475873.9098 | 13150498.9795 | 12991059.8966 | 25611081.1455 | 27777000 | 27777000 | 13889000 | 13888999.96 | -11494.9189 | -28753.2146 | -33311.1737 | -920534.9286 | -909374.1928 | -1792775.6802 | -1944390 | -1944390 | -972230.04 | -972230.04 | -7 | 7.00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44099 | 46736 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 4 | 0 | ABCB & Component Replacement
23691 | Thornton TS T3/T4; Component Replacement | N.T.C.1.42 | 7700 | 203 | PROJECT DELIVERY | AIP005457 |  | AIP005457 | Yes | AIP005457 |  |  |  | Central Zone Station/Yard Investments | James.Mardegan@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23692 | Leslie TS: Station Centric | N.T.C.1.42 | 7700 | 203 | PROJECT DELIVERY | AIP005476 | AIP005476 | AIP005476 | No | AIP005476 | Leslie TS: T1, PCT & Component Replacements | SR-05 | Load Station Transformer Replacement Projects | Central Zone Station/Yard Investments | James.Mardegan@HydroOne.com | michael.xavier@hydroone.com | System Renewal | Central | Not Required | 01 - Agreement (current/future) | TBD | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 785086.1426 | 1253648.5377 | 7668714.6255 | 9253375.3962 | 2843335.16 | 0 | 0 | 0 | 0 | 0 | 844178.648 | 1348009.1803 | 8245929.7048 | 9949866.0174 | 3057349.64 | 0 | 0 | 0 | 0 | 0 | -59092.5054 | -94360.6426 | -577215.0793 | -696490.6212 | -214014.48 | 0 | 0 | 0 | -7 | 7.00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44412 | 45459 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Component Replacements
23693 | Manby TS: T7, T9, T12, T13 & Component Replacement | N.T.C.1.43 | 7700 | 203 | PROJECT DELIVERY | AIP005472 | AIP005472 | AIP005472 | No | AIP005472 | Manby TS: T7, T9, T12, T13 & Component Replacements | SR-03 | Bulk Station Transformer Replacement Projects | Greater Toronto Area Zone Station/Yard Investments | James.Mardegan@HydroOne.com | michael.xavier@hydroone.com | System Renewal | Greater Toronto Area | Not Required | 03 - None (default) | TBD | Project | init | Short Term Planning | Short Term Planning |  | 166149.8735 | 702863.0448 | 3216502.4596 | 15722127.5528 | 25347039.0429 | 15928796.954 | 3524495.2 | 0 | 0 | 0 | 178655.778 | 755766.7148 | 3458604.7953 | 16905513.4977 | 27254880.6913 | 17127738.6602 | 3789779.8 | 0 | 0 | 0 | -12505.9045 | -52903.67 | -242102.3357 | -1183385.9448 | -1907841.6484 | -1198941.7062 | -265284.6 | 0 | 0 | 0 | -7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44124 | 45458 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Component Replacements
23694 | Wanstead TS Capital Contribution | N.D.C.2.02 | 7700 | 203 | PROJECT DELIVERY | AIP005541 | AIP005541 | AIP005541 | No | AIP005541 | Wanstead TS Capital Contribution |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Alexander.Hamlyn@HydroOne.com | General Plant | Western | Not Required | 01 - Agreement (current/future) | Not Required | Project | EMPP ACTN | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | 200000.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -300000 | -200000.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42510 | 43434 | [13 empty] | FALSE |  | 0 | 0 | Alternative 1
23695 | System Operations DC Colocation | N.C.C.3.01 | 4032 | 212 | INFO SOLUTIONS DIVISION | AIP005460 | AIP005460 | AIP005460 | No | AIP005460 | OGCC Data Centre Remediation - Incl. Co-Location | 0 |  | Common Oper Infrast & Control Facilities | Godfrey.Holder@HydroOne.com | mallen@hydroone.com | General Plant | 0 | 0 | 03 - None (default) | 0 | Project | AWRD EMPP | Executing | Executing |  | 710000.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 710000.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43616 | 44792 | False |  | False |  | False |  | True | False |  | False | False | False | False | TRUE | This comment applies to "Corrective Maintenance/Demad Replacements": This investment will allow for the systimatic replacement of EOL assets located at the OGCC data center and correct the know issues including the single point of failure in the cooling heat rejection system. | 0 | 0 | Asset Optimal
23696 | D3A, Allanburg TS X ASW Steel CTS, Tx Line Refurb. | N.T.C.1.12 | 7700 | 203 | PROJECT DELIVERY | AIP005413 | AIP005413 | AIP005413 | No | AIP005413 | D3A, Allanburg TS X AWS Steel CTS, Tx Line Refurb. | SR-19 | Transmission Line Refurbishment - End of Life ACSR, Copper Conductors & Structures | Overhead Lines Component Refurb & Repl | hassan.hamzeh@hydroone.com | Deniz.Turkben@HydroOne.com | System Renewal | Hamilton Niagara | Not Required | 03 - None (default) | Not Required | Project | DETL ACTN LLTM | Short Term Planning | Short Term Planning |  | 3423788.01 | 3574280.0339 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3890668.1932 | 4061681.8567 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -466880.1832 | -487401.8228 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43259 | 43812 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Proceed with complete line refurbishment
23698 | Essex TS - Connect Enwin Feeder to M10 Breaker | N.T.C.2.11 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Load Customer Connection | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23699 | 2015-2020 Development of CDM new programs | N.D.M.2.50 | 1144 | 220 | STRATEGY & CONSERV |  |  |  | No |  |  |  |  | Conservation and Demand Management | Imran.Merali@HydroOne.com | [6 empty] | Program | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23700 | Bramalea TS; Component Replacement | N.T.C.1.43 | 7700 | 203 | PROJECT DELIVERY | AIP005675 | AIP005675 | AIP005675 | No | AIP005675 | Bramalea TS: PCT & Component Replacements | 0 |  | Greater Toronto Area Zone Station/Yard Investments | James.Mardegan@HydroOne.com | michael.xavier@hydroone.com | System Renewal | Greater Toronto Area | Not Required | 03 - None (default) | TBD | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 220137.4789 | 695899.5034 | 1353256.6299 | 9543725.64 | 7996006.04 | 1774478.48 | 0 | 0 | 0 | 0 | 236706.9665 | 748279.036 | 1455114.6558 | 10262070.6 | 8597855.96 | 1908041.48 | 0 | 0 | 0 | 0 | -16569.4877 | -52379.5325 | -101858.0259 | -718344.96 | -601849.92 | -133563 | 0 | -7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45064 | 46126 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | PCT & Component Replacements
23701 | Placeholder OGCC Data Centre Remediation | N.C.C.3.01 | 4514 | 212 | INFO SOLUTIONS DIVISION | AIP005378 |  | AIP005378 | Yes | AIP005378 |  |  |  | Common Oper Infrast & Control Facilities | Godfrey.Holder@HydroOne.com | [6 empty] | Project | BEST init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23702 | OGCC Office Remediation | N.C.C.3.01 | 7236 | 215 | FACILITIES & REAL ESTATE | AIP005431 | AIP005431 | AIP005431 | No | AIP005431 | OGCC Office Remediation | 0 |  | Common Oper Infrast & Control Facilities | Godfrey.Holder@HydroOne.com | Mitchell.Wotton@HydroOne.com | General Plant | 0 | Not Required | 03 - None (default) | Not Required | Project | init BEST | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 945687.1355 | 2108553.0797 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 945687.1355 | 2108553.0797 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44228 | 44836 | False |  | False |  | False |  | False | False |  | False | True | False | False | FALSE |  | 0 | 0 | Asset Optimal
23704 | Beachville OC Trailer Acquisition 2015 | N.D.C.1.50 | 7236 | 215 | FACILITIES & REAL ESTATE |  |  |  | No |  |  |  |  | Real Estate Facilities | cindy.copp@hydroone.com | [6 empty] | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23705 | Guelph-MTO-Silvercreek Pkwy Relocation-Recoverable | N.T.C.1.14 | 7700 | 203 | PROJECT DELIVERY | AIP005439 | AIP005439 | AIP005439 | No | AIP005439 | Guelph – MTO – Silvercreek Parkway Wood Pole Relocations - Recoverable | 0 |  | Third Party Transmission System Modifications | john.boldt@HydroOne.com | Gian.Minichini@HydroOne.com | System Renewal | Western | 0 | 01 - Agreement (current/future) | 0 | Project | HOLD DETL | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43266 | 43449 | True | Ministry of Transportation of Ontario (MTO) asked HONI to remove/relocate structures #40 and 41 on B5G/B6G (idle) so as to maintain sufficient clearances from MTO's proposed new ramp. | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Guelph – MTO – Silvercreek Parkway Wood Pole Relocations - Recoverable
23706 | Hawthorne TS T7/T8 DESN: Add 44 kV Breaker for HOL | N.T.C.2.11 | 7700 | 203 | PROJECT DELIVERY | AIP005547 | AIP005547 | AIP005547 | No | AIP005547 | Hawthorne TS -Add One 44kV feeder | 0 |  | Load Customer Connection | Robert.Reinmuller@HydroOne.com | Dieter.Wagner@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1058113 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1058113 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43205 | [13 empty] | FALSE |  | 0 | 0 | Alternative 1
23707 | Enhanced Low Income Program | N.D.M.4.01 | 4175 | 202 | CUSTOMER CARE SERVICES |  |  |  | No |  |  |  |  | Customer Care Services Dx | Imran.Merali@HydroOne.com | [6 empty] | Project | init EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23708 | BSPS Removals | N.T.C.1.19 | 7700 | 203 | PROJECT DELIVERY | AIP005499 | AIP005499 | AIP005499 | No | AIP005499 | BSPS Removals | 0 |  | Protection Control & Metering Equip | Miroslav.Kostic@HydroOne.com | Murched.Ajami@HydroOne.com | System Renewal | 0 | 0 | 03 - None (default) | 0 | Project | HOLD DETL | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 794561.8 | 821541.56 | 837713.72 | 853340.72 | 0 | 0 | 0 | 0 | 0 | 0 | -794561.8 | -821541.56 | -837713.72 | -853340.72 | 0 | 0 | 0 | 0 | -100 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44074 | 44926 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Asset Optimal
23709 | Merivale TS Add 230/115kV Autotransformers | N.T.C.2.02 | 7700 | 203 | PROJECT DELIVERY | AIP005524 |  | AIP005524 | Yes | AIP005524 |  |  |  | Local Area Supply | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23710 | Dundas OC Trailer Acquisition 2015 | N.D.C.1.50 | 7236 | 215 | FACILITIES & REAL ESTATE |  |  |  | No |  |  |  |  | Real Estate Facilities | cindy.copp@hydroone.com | [6 empty] | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23714 | Tx Scrap & Surplus of System Reserve Equipment | N.T.C.1.46 | 7700 | 203 | PROJECT DELIVERY | AIP000557 | AIP000557 | AIP000557 | No | AIP000557 | Power Equipment - Scrap & Surplus of Operating Spare Sys Eqpt | 0 |  | Tx Station Demand and Spares | James.Mardegan@HydroOne.com | peter.zhao@hydroone.com | System Renewal | 0 | 0 | 03 - None (default) | 0 | Program | ACTN EMPP | Executing | Short Term Planning | # of Equipments | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000 | 35000 | 35000.08 | 14000 | 14000 | 14000 | 0 | 0 | 0 | 0 | -35000 | -35000 | -35000.08 | -14000 | -14000 | -14000 | 0 | 0 | 0 | 0 | -100 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 4 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Asset Optimal
23715 | Hanmer TS Fleet Garage Bolier | N.T.C.1.28 | 7236 | 215 | FACILITIES & REAL ESTATE |  |  |  | No |  |  |  |  | Transmission Site Facilities | cindy.copp@hydroone.com | [6 empty] | Project | EMPP AWRD | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23716 | Bracebridge forestry Washroom Improvements | N.D.C.1.50 | 7236 | 215 | FACILITIES & REAL ESTATE |  |  |  | No |  |  |  |  | Real Estate Facilities | cindy.copp@hydroone.com | [6 empty] | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23717 | Timmins WestMine CTS Lakeshore Gold New Xfrm | N.T.C.2.11 | 7700 | 203 | PROJECT DELIVERY | AIP005516 |  | AIP005516 | Yes | AIP005516 |  |  |  | Load Customer Connection | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23718 | Northwest Bulk Transmission Line - Development | N.T.M.2.02 | 7700 | 203 | PROJECT DELIVERY | AIP005530 | AIP005530 | AIP005530 | No | AIP005530 | Northwest Bulk Transmission Line Project -Developm | 0 |  | Infrastructure Development | Robert.Reinmuller@HydroOne.com | Hamid.Hamadanizadeh@HydroOne.com | System O&M | Northern | 0 | 03 - None (default) | 0 | Project | init BEST | Short Term Planning | Short Term Planning |  | 1961533.263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1961533.263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43404 | True | Requested by the provincial government and the IESO. | False |  | False | Recommended in LTEP | False | False |  | True | False | False | False | FALSE |  | 0 | 0 | Northwest Bulk Transmission Line Project -Development (Modified)
23719 | TransAlta Sarnia CGS Telecom Upgrade | N.T.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP005528 | AIP005528 | AIP005528 | No | AIP005528 | Lambton/Scott SPS Modifications | 0 |  | Network Transfer Capability | Robert.Reinmuller@HydroOne.com | Emeka.Okongwu@HydroOne.com | System Service | 0 | 0 | 03 - None (default) | 0 | Project | ACTN DETL | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 350000.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -400000 | -350000.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43327 | 43692 | True | Request from TransAlta Sarnia | True | NPCC Requirement | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Alternative 1
23720 | Waterloo-Columbia St Pole Relocation-Recoverable | N.T.C.1.14 | 7700 | 203 | PROJECT DELIVERY | AIP005441 |  | AIP005441 | Yes | AIP005441 |  |  |  | Third Party Transmission System Modifications | john.boldt@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23721 | Lauzon TS - New Breaker for H1Dx | N.T.C.2.11 | 7700 | 203 | PROJECT DELIVERY | AIP005508 |  | AIP005508 | Yes | AIP005508 |  |  |  | Load Customer Connection | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | HOLD | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23722 | Nanticoke TS: Connect HVDC Lake Erie Circuits | N.T.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP005525 | AIP005525 | AIP005525 | No | AIP005525 | Nanticoke TS: Connect HVDC Lake Erie Circuits | SS-01 | Nanticoke TS: Connect HVDC Lake Erie Circuits | Network Transfer Capability | Robert.Reinmuller@HydroOne.com | Gene.Ng@HydroOne.com | System Service | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | LLTM ACTN | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2474000 | 9877000 | 4057000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2474000 | -9877000 | -4057000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43190 | 43966 | True | Request from ITC Lake Erie Connector | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Alternative 1
23723 | Wilson TS; Component Replacement | N.T.C.1.42 | 7700 | 203 | PROJECT DELIVERY | AIP005520 |  | AIP005520 | Yes | AIP005520 |  |  |  | Central Zone Station/Yard Investments | James.Mardegan@HydroOne.com | [6 empty] | Program | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23724 | D2L,DymondxUpper+MartinxCrystal-Line Refurbishment | N.T.C.1.12 | 7700 | 203 | PROJECT DELIVERY | AIP005343 | AIP005343 | AIP005343 | No | AIP005343 | Line Refurbishment - D2L, Dymond x Upper Notch Jct and Martin River x Crystal Falls SS | 0 |  | Overhead Lines Component Refurb & Repl | hassan.hamzeh@hydroone.com | Deniz.Turkben@HydroOne.com | System Renewal | Northern | Not Required | 03 - None (default) | In Progress | Project | ACTN EMPP | Executing | Executing |  | 540754.5997 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 608372.0439 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -67617.4442 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -11.1145 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43388 | [13 empty] | FALSE |  | 0 | 0 | Alternative 1
23725 | Carling TS ID26860 TX Chaudiere Hydro GS2 | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23726 | Line Rating Sensor Project | N.T.M.2.21 | 4230 | 213 | PLANNING | AIP001164 |  | AIP001164 | Yes | AIP001164 |  |  |  | Technology Program | Daila.Dzintars@HydroOne.com | [6 empty] | Program | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23727 | Retailer, Budget Billing, and Unbilled Revenue Opt | N.D.C.2.60 | 4339 | 212 | INFO SOLUTIONS DIVISION | UNPLND |  |  | Yes |  |  |  |  | IT Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | init AWRD | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23728 | Dundas TS: MV Switchyard Refurbishment | N.T.C.1.41 | 7700 | 203 | PROJECT DELIVERY | AIP005532 | AIP005532 | AIP005532 | No | AIP005532 | Dundas TS: MV Switchyard Refurbishment | 0 |  | Hamilton/Niagara Zone Station/Yard Investments | James.Mardegan@HydroOne.com | mark.truchanowicz@hydroone.com | System Renewal | Hamilton Niagara | Not Required | 03 - None (default) | TBD | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 258553.1457 | 772927.9772 | 1056506.8405 | 7593276.84 | 2978733.16 | 0 | 0 | 0 | 0 | 0 | 278014.1352 | 831105.3518 | 1136028.8607 | 8164813.8 | 3202938.88 | 0 | 0 | 0 | 0 | 0 | -19460.9895 | -58177.3746 | -79522.0203 | -571536.96 | -224205.72 | 0 | 0 | -7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45055 | 45992 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | MV Switchyard Refurbishment
23729 | South March TS Roof Replacement 2015 | N.T.C.1.28 | 7236 | 215 | FACILITIES & REAL ESTATE |  |  |  | No |  |  |  |  | Transmission Site Facilities | cindy.copp@hydroone.com | [6 empty] | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23735 | BL104 & BSH106 Idle Lines Removal Non-Recoverable | N.T.C.1.14 | 7700 | 203 | PROJECT DELIVERY | AIP000500 |  | AIP000500 | Yes | AIP000500 |  |  |  | Third Party Transmission System Modifications | john.boldt@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23736 | Caledonia TS M3 ID26810 DX Oneida Business park | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000195 |  | AIP000195 | Yes | AIP000195 | Small Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23737 | Brockville TS M5 & B1R ID27020 TX Invista Maitland | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23742 | Merivale TS Steel Canopy Improvements 2015 | N.T.C.1.28 | 7236 | 215 | FACILITIES & REAL ESTATE | UNPLND |  |  | Yes |  |  |  |  | Transmission Site Facilities | cindy.copp@hydroone.com | [6 empty] | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23743 | Musselwhite Mine Dart Upgrade | N.T.C.2.11 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Load Customer Connection | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | ACTN DETL | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23744 | ICM Replacement Project (SAP EHSM Implementation) | N.C.C.2.60 | 4339 | 212 | INFO SOLUTIONS DIVISION | AIP000060 |  | AIP000060 | Yes | AIP000060 |  |  |  | IT Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23746 | Bruce A 500kV- Replace ABCB & Yard Reconfiguration | N.T.C.1.40 | 7700 | 203 | PROJECT DELIVERY | AIP005519 | AIP005519 | AIP005519 | No | AIP005519 | Bruce A TS: 500kV ABCB replacement and Yard Reconfiguration | SR-01 | Air Blast Circuit Breaker Replacement Projects | Western Zone Station/Yard Investments | James.Mardegan@HydroOne.com | Fred.Kouhdani@HydroOne.com | System Renewal | Western | Not Required | 03 - None (default) | TBD | Project | init | Short Term Planning | Short Term Planning |  | 361349.6775 | 441116.6978 | 12443975.7265 | 37138092.4048 | 24458258.909 | 24109849.6875 | 26148810.04 | 0 | 0 | 0 | 388548.0403 | 474319.0299 | 13380619.0608 | 39933432.6933 | 26299203.1279 | 25924569.5564 | 28117000.04 | 0 | 0 | 0 | -27198.3628 | -33202.3321 | -936643.3343 | -2795340.2885 | -1840944.219 | -1814719.8689 | -1968190 | 0 | 0 | 0 | -7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44015 | 45641 | False |  | False |  | False |  | False | True | need to be aligned with BP refurbishment project | False | False | False | False | FALSE |  | 0 | 0 | ALT 1- Station Rebild- AIS green field
23747 | Caledonia TS M3 ID26810 TX Oneida Business Park | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23748 | Transfer of Ownership of T8M Line to Hydro One | N.T.C.2.02 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Local Area Supply | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | init EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23749 | Enfield TS - capital contribution | N.D.C.2.02 | 7700 | 203 | PROJECT DELIVERY | AIP000183 AR18533 |  | AIP000183 | Yes | AIP000183 | (1) System upgrade driven by load growth |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Michael.Medeiros@HydroOne.com | System Service | 0 | 0 | 03 - None (default) | Not Required | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23755 | OMA - ICM Replacement Project (SAP EHSM Impl) | N.C.M.2.60 | 4339 | 212 | INFO SOLUTIONS DIVISION | UNPLND |  |  | Yes |  |  |  |  | IT-Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23757 | Timmins OC Generator Fuel Tank Replacement 2015 | N.C.C.1.50 | 7236 | 215 | FACILITIES & REAL ESTATE |  |  |  | No |  |  |  |  | Real Estate Facilities | cindy.copp@hydroone.com | [6 empty] | Project | EMPP AWRD | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23763 | Nepean TS M26 ID27820 TX Algonquin College - Cogen | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23767 | AA 2015 Remediation | N.C.M.2.60 | 4339 | 212 | INFO SOLUTIONS DIVISION | UNPLND |  |  | Yes |  |  |  |  | IT-Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23768 | Thornton TS M2 ID25430-TX Oshawa PUC Metrolinx LD | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23769 | Wilson TS HVAC Replacement 2015 | N.T.C.1.28 | 7236 | 215 | FACILITIES & REAL ESTATE | AIP000667 |  | AIP000667 | Yes | AIP000667 |  |  |  | Transmission Site Facilities | cindy.copp@hydroone.com | [6 empty] | Program | AWRD EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23770 | Wiltshire TS Metal Roof Coating 2015 | N.T.C.1.28 | 7236 | 215 | FACILITIES & REAL ESTATE | UNPLND |  |  | Yes |  |  |  |  | Transmission Site Facilities | cindy.copp@hydroone.com | [6 empty] | Project | EMPP AWRD | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23771 | Horning TS Metal Roof Coating 2015 | N.T.C.1.28 | 7236 | 215 | FACILITIES & REAL ESTATE | UNPLND |  |  | Yes |  |  |  |  | Transmission Site Facilities | cindy.copp@hydroone.com | [6 empty] | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23773 | Lindsay SC Heat Pump Replacement 2015 | N.D.C.1.50 | 7236 | 215 | FACILITIES & REAL ESTATE | AIP000027 |  | AIP000027 | Yes | AIP000027 | Facility Accommodation & Improvements Service Centres & Admin |  |  | Real Estate Facilities | cindy.copp@hydroone.com | Peter.Erdman@HydroOne.com | General Plant | 0 | 0 | 03 - None (default) | 0 | Program | AWRD EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23774 | Brockville OC Office Trailer Acquisition 2015 | N.D.C.1.50 | 7236 | 215 | FACILITIES & REAL ESTATE | AIP000027 |  | AIP000027 | Yes | AIP000027 | Facility Accommodation & Improvements Service Centres & Admin |  |  | Real Estate Facilities | cindy.copp@hydroone.com | Peter.Erdman@HydroOne.com | General Plant | 0 | 0 | 03 - None (default) | 0 | Program | EMPP AWRD | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23775 | OGCC Emergency Generator Fuel System upgrades | N.C.C.3.01 | 7370 | 206 | TX LINES AND STATIONS | UNPLND |  |  | Yes |  |  |  |  | Common Oper Infrast & Control Facilities | Godfrey.Holder@HydroOne.com | [6 empty] | Project | EMPP ACTN DETL | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23781 | A5A M2D W6CS 115kV Line Protection NERC Upgrades | N.T.C.1.45 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Northern Zone Station/Yard Investments | James.Mardegan@HydroOne.com | [6 empty] | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23782 | GIC Replacement Pilot Project | N.T.C.3.08 | 7370 | 206 | TX LINES AND STATIONS | UNPLND |  |  | Yes |  |  |  |  | Integrating Operating Infrastructure | Miroslav.Kostic@HydroOne.com | [6 empty] | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23785 | Barrie Area Transmission Upgrade | N.T.C.2.02 | 7700 | 203 | PROJECT DELIVERY | AIP005523 | AIP005523 | AIP005523 | No | AIP005523 | Upgrade Barrie TS and Line E3/4B to 230 kV | SS-12 | Barrie TS: Upgrade Station and Reconductor E3B/E4B Circuits | Local Area Supply | Robert.Reinmuller@HydroOne.com | Alexander.Constantinescu@HydroOne.com | System Service | 0 | 0 | 03 - None (default) | 0 | Project | DETL ACTN | Short Term Planning | Short Term Planning |  | 6380552.3356 | 34431447.2818 | 34172097.6785 | 2884745.6688 | 0 | 0 | 0 | 0 | 0 | 0 | 6380552.3356 | 34431447.2818 | 34172097.6785 | 2884745.6688 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43556 | 44165 | False |  | True | IESO Ontario Resource and Transmission Assessment Criteria | False |  | False | False |  | False | True | False | False | FALSE |  | 0 | 0 | Alternative 1
23786 | Meaford TS: Component Replacement | N.T.C.1.40 | 7700 | 203 | PROJECT DELIVERY | AIP005195 | AIP005195 | AIP005195 | No | AIP005195 | Meaford TS: Component Replacement | SR-06 | Load Station Switchgear and Ancillary Equipment Replacement Projects | Western Zone Station/Yard Investments | James.Mardegan@HydroOne.com | mark.truchanowicz@hydroone.com | System Renewal | Western | 0 | 03 - None (default) | 0 | Project | BEST ACTN | Short Term Planning | Short Term Planning |  | 745544.3623 | 700106.8343 | 3029398.1376 | 1142022.3603 | 0 | 0 | 0 | 0 | 0 | 0 | 801660.6046 | 752803.0476 | 3257417.3522 | 1227981.0326 | 0 | 0 | 0 | 0 | 0 | 0 | -56116.2423 | -52696.2133 | -228019.2147 | -85958.6723 | 0 | 0 | 0 | 0 | 0 | 0 | -7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43460 | 44515 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Component Replacement
23790 | Q11/12S - Beck GS #1 "Super" Str. Refurb + Conduct | N.T.C.1.12 | 7700 | 203 | PROJECT DELIVERY | AIP005555 |  | AIP005555 | Yes | AIP005555 |  |  |  | Overhead Lines Component Refurb & Repl | hassan.hamzeh@hydroone.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23792 | Aylmer OC Security Upgrade 2015 | N.D.C.1.50 | 7236 | 215 | FACILITIES & REAL ESTATE | AIP000027 |  | AIP000027 | Yes | AIP000027 | Facility Accommodation & Improvements Service Centres & Admin |  |  | Real Estate Facilities | cindy.copp@hydroone.com | Peter.Erdman@HydroOne.com | General Plant | 0 | 0 | 03 - None (default) | 0 | Program | EMPP AWRD | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23794 | Kent OC Security Upgrade 2015 | N.D.C.1.50 | 7236 | 215 | FACILITIES & REAL ESTATE | AIP000027 |  | AIP000027 | Yes | AIP000027 | Facility Accommodation & Improvements Service Centres & Admin |  |  | Real Estate Facilities | cindy.copp@hydroone.com | Peter.Erdman@HydroOne.com | General Plant | 0 | 0 | 03 - None (default) | 0 | Program | AWRD EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23796 | Orangeville OC Security upgrade 2015 | N.C.C.1.50 | 7236 | 215 | FACILITIES & REAL ESTATE | AIP000027 |  | AIP000027 | Yes | AIP000027 | Facility Accommodation & Improvements Service Centres & Admin |  |  | Real Estate Facilities | cindy.copp@hydroone.com | Peter.Erdman@HydroOne.com | General Plant | 0 | 0 | 03 - None (default) | 0 | Program | AWRD EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23798 | Lambton OC Security Upgrade 2015 | N.D.C.1.50 | 7236 | 215 | FACILITIES & REAL ESTATE | AIP000027 |  | AIP000027 | Yes | AIP000027 | Facility Accommodation & Improvements Service Centres & Admin |  |  | Real Estate Facilities | cindy.copp@hydroone.com | Peter.Erdman@HydroOne.com | General Plant | 0 | 0 | 03 - None (default) | 0 | Program | AWRD EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23799 | Simcoe OC Security upgrade 2015 | N.D.C.1.50 | 7236 | 215 | FACILITIES & REAL ESTATE | AIP000027 |  | AIP000027 | Yes | AIP000027 | Facility Accommodation & Improvements Service Centres & Admin |  |  | Real Estate Facilities | cindy.copp@hydroone.com | Peter.Erdman@HydroOne.com | General Plant | 0 | 0 | 03 - None (default) | 0 | Program | EMPP AWRD | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23804 | Hanmer TS HVAC Replacement 2015 | N.T.C.1.28 | 7236 | 215 | FACILITIES & REAL ESTATE | AIP000667 |  | AIP000667 | Yes | AIP000667 |  |  |  | Transmission Site Facilities | cindy.copp@hydroone.com | [6 empty] | Program | AWRD EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23806 | Chatham SS: Component Replacement | N.T.C.1.40 | 7700 | 203 | PROJECT DELIVERY | AIP005477 | AIP005477 | AIP005477 | No | AIP005477 | Chatham SS: Component Replacement | SR-04 | Bulk Station Switchgear and Ancillary Equipment Replacement Projects | Western Zone Station/Yard Investments | James.Mardegan@HydroOne.com | mark.truchanowicz@hydroone.com | System Renewal | Western | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 500715.4387 | 1288319.8745 | 4217369.6878 | 8056171.1471 | 6957793.9155 | 2720529.1699 | 429868.62 | 0 | 0 | 0 | 538403.6976 | 1385290.1877 | 4534806.1159 | 8662549.6205 | 7481498.8339 | 2925300.1827 | 462224.34 | 0 | 0 | 0 | -37688.2588 | -96970.3131 | -317436.4281 | -606378.4734 | -523704.9184 | -204771.0128 | -32355.72 | 0 | 0 | 0 | -7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43802 | 45214 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Component Replacement
23807 | Sarnia Scott TS: T5 & Component Replacement | N.T.C.1.40 | 7700 | 203 | PROJECT DELIVERY | AIP005480 | AIP005480 | AIP005480 | No | AIP005480 | Sarnia Scott TS: T5 & Component Replacement | SR-02 | Station Reinvestment Projects | Western Zone Station/Yard Investments | James.Mardegan@HydroOne.com | mark.truchanowicz@hydroone.com | System Renewal | Western | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 333810.3284 | 1223196.3193 | 5111678.344 | 11378244.6422 | 10646346.0778 | 4117122.115 | 607376.64 | 0 | 0 | 0 | 358935.837 | 1315264.8595 | 5496428.3269 | 12234671.6583 | 11447683.9547 | 4427013.0269 | 653093.12 | 0 | 0 | 0 | -25125.5086 | -92068.5402 | -384749.9829 | -856427.0161 | -801337.8768 | -309890.9119 | -45716.48 | 0 | 0 | 0 | -7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43831 | 45245 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Component Replacement
23808 | St. Andrews TS: T3, T4 & Switchyard Refurbishment | N.T.C.1.40 | 7700 | 203 | PROJECT DELIVERY | AIP005467 | AIP005467 | AIP005467 | No | AIP005467 | St. Andrews TS: T3, T4 & Switchyard Refurbishment | SR-05 | Load Station Transformer Replacement Projects | Western Zone Station/Yard Investments | James.Mardegan@HydroOne.com | mark.truchanowicz@hydroone.com | System Renewal | Western | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 930719.3789 | 1083136.7834 | 7102100.7483 | 4887519.7848 | 877683.4987 | 0 | 0 | 0 | 0 | 0 | 1000773.5257 | 1164663.208 | 7636667.4713 | 5255397.6181 | 943745.6976 | 0 | 0 | 0 | 0 | 0 | -70054.1468 | -81526.4246 | -534566.723 | -367877.8333 | -66062.1988 | 0 | 0 | 0 | 0 | -7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44064 | 45000 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Switchyard Refurbishment
23809 | St. Thomas TS: Station Decom & W3T, W4T, T11T Rcfg | N.T.C.1.40 | 7700 | 203 | PROJECT DELIVERY | AIP005471 | AIP005471 | AIP005471 | No | AIP005471 | St. Thomas TS: Station Decommissioning & W3T, W4T, T11T Reconfiguration | 0 |  | Western Zone Station/Yard Investments | James.Mardegan@HydroOne.com | mark.truchanowicz@hydroone.com | System Renewal | Western | 0 | 03 - None (default) | 0 | Project | DETL ACTN | Short Term Planning | Short Term Planning |  | 540548.3749 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2702741.8743 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2162193.4994 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -80 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43308 | 43774 | False |  | False |  | False |  | False | True | Coordination with Sys. Planning Tillsonburg Project to address voltage drop and CX reliability. | False | False | False | False | TRUE | No customer load is being supplied from this station, and no future plans have been identified in regional planning. Prudent asset management is to decomission the station to avoid future liabilities on maintenance and environmental risks for station that does not supply customer load. In coordination with System Planning, reinforcement of the circuits supplying Tillsonrburg TS and station refurbishment will be completed to address customer reliability concerns in the area. | 8 | 2 | Station Decomissioning
23810 | Remote Disconnect/Reconnect - Installation | N.D.C.1.09 | 7374 | 205 | LINES | UNPLND |  |  | Yes |  |  |  |  | Metering | Peter.Mitskos@HydroOne.com | [6 empty] | Project | EMPP AWRD | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23811 | Remote Disconnect/Reconnect - Inventory | N.D.C.1.09 | 7374 | 205 | LINES | UNPLND |  |  | Yes |  |  |  |  | Metering | Peter.Mitskos@HydroOne.com | [6 empty] | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23812 | Remote Disconnect/Reconnect - PL Support | N.D.M.1.05 | 7374 | 205 | LINES | UNPLND |  |  | Yes |  |  |  |  | Customer Meters | Peter.Mitskos@HydroOne.com | [6 empty] | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23815 | Detweiler TS: T2, T4 & Component Replacement | N.T.C.1.40 | 7700 | 203 | PROJECT DELIVERY | AIP005458 | AIP005458 | AIP005458 | No | AIP005458 | Detweiler TS: T2, T4 & Component Replacement | SR-03 | Bulk Station Transformer Replacement Projects | Western Zone Station/Yard Investments | James.Mardegan@HydroOne.com | mark.truchanowicz@hydroone.com | System Renewal | Western | 0 | 03 - None (default) | 0 | Project | ACCP EMPP | Executing | Executing |  | 4075358.8494 | 8789004.8152 | 6746099.0725 | 1520788.3561 | 0 | 0 | 0 | 0 | 0 | 0 | 4382106.2897 | 9450542.812 | 7253869.9705 | 1635256.2969 | 0 | 0 | 0 | 0 | 0 | 0 | -306747.4403 | -661537.9968 | -507770.8979 | -114467.9408 | 0 | 0 | 0 | 0 | 0 | 0 | -7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43131 | 44545 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Component Replacement
23816 | Hanlon TS: T1, T2 & Component Replacement | N.T.C.1.40 | 7700 | 203 | PROJECT DELIVERY | AIP005463 | AIP005463 | AIP005463 | No | AIP005463 | Hanlon TS: T1, T2 & Component Replacement | SR-05 | Load Station Transformer Replacement Projects | Western Zone Station/Yard Investments | James.Mardegan@HydroOne.com | mark.truchanowicz@hydroone.com | System Renewal | Western | 0 | 03 - None (default) | 0 | Project | ACTN BEST | Short Term Planning | Short Term Planning |  | 0 | 269963.3726 | 722262.1989 | 1833147.2955 | 12000352.4087 | 4640800.891 | 0 | 0 | 0 | 0 | 0 | 290283.1963 | 776626.0204 | 1971126.1242 | 12903604.7405 | 4990108.485 | 0 | 0 | 0 | 0 | 0 | -20319.8237 | -54363.8214 | -137978.8287 | -903252.3318 | -349307.5939 | 0 | 0 | 0 | 0 | -7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44207 | 45291 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Component Replacement
23817 | Wingham TS: T1, T2, PCT & Component Replacement | N.T.C.1.40 | 7700 | 203 | PROJECT DELIVERY | AIP005468 | AIP005468 | AIP005468 | No | AIP005468 | Wingham TS: T1, T2, PCT & Component Replacement | SR-05 | Load Station Transformer Replacement Projects | Western Zone Station/Yard Investments | James.Mardegan@HydroOne.com | mark.truchanowicz@hydroone.com | System Renewal | Western | 0 | 03 - None (default) | 0 | Project | BEST AWRD | Short Term Planning | Short Term Planning |  | 667620.6029 | 1144794.2051 | 6959529.7984 | 12878043.4044 | 4185732.0079 | 0 | 0 | 0 | 0 | 0 | 717871.616 | 1230961.5109 | 7483365.3747 | 13847358.4994 | 4500787.1053 | 0 | 0 | 0 | 0 | 0 | -50251.0131 | -86167.3058 | -523835.5762 | -969315.095 | -315055.0974 | 0 | 0 | 0 | 0 | 0 | -7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43747 | 44795 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Component Replacement
23823 | OGCC Dip pole 2015 | N.C.C.1.50 | 7236 | 215 | FACILITIES & REAL ESTATE | AIP000027 |  | AIP000027 | Yes | AIP000027 | Facility Accommodation & Improvements Service Centres & Admin |  |  | Real Estate Facilities | cindy.copp@hydroone.com | Peter.Erdman@HydroOne.com | General Plant | 0 | 0 | 03 - None (default) | 0 | Program | AWRD EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23825 | Alfred DS F2 System Study Implementation | N.D.C.2.02 | 7374 | 205 | LINES | AIP005643 | AIP005643 | AIP005643 | No | AIP005643 | Alfred DS feeder Upgrade | ISD-SS-02 | System Upgrades Driven by Load Growth | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Muhammad.Sabir@HydroOne.com | System Service | Eastern | Not Required | 03 - None (default) | Not Required | Project | init | Short Term Planning | Short Term Planning |  | 1582932.7093 | 807356.6717 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1798787.1697 | 917450.7633 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -215854.4604 | -110094.0916 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43012 | 43477 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
23826 | SAP Hold Co - CAP Portion | N.C.C.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION | AIP005575 |  | AIP005575 | Yes | AIP005575 |  |  |  | IT Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23827 | Nipissing OC Security Upgrades 2015 | N.C.C.1.50 | 7236 | 215 | FACILITIES & REAL ESTATE | AIP000027 |  | AIP000027 | Yes | AIP000027 | Facility Accommodation & Improvements Service Centres & Admin |  |  | Real Estate Facilities | cindy.copp@hydroone.com | Peter.Erdman@HydroOne.com | General Plant | 0 | 0 | 03 - None (default) | 0 | Program | EMPP AWRD | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23828 | Buchanan TS Re-bricking 2015 Wall | N.T.C.1.28 | 7236 | 215 | FACILITIES & REAL ESTATE | AIP000664 |  | AIP000664 | Yes | AIP000664 |  |  |  | Transmission Site Facilities | cindy.copp@hydroone.com | [6 empty] | Program | AWRD EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23829 | Frankford pole Yard Parking Improvements 2015 | N.D.C.1.50 | 7236 | 215 | FACILITIES & REAL ESTATE | AIP000027 |  | AIP000027 | Yes | AIP000027 | Facility Accommodation & Improvements Service Centres & Admin |  |  | Real Estate Facilities | cindy.copp@hydroone.com | Peter.Erdman@HydroOne.com | General Plant | 0 | 0 | 03 - None (default) | 0 | Program | AWRD EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23830 | IESO Meter Data Validation Dx | N.D.M.4.01 | 8706 | 214 | METER SHOP | AIP000364 | AIP000364 | AIP000364 | No | AIP000364 | IESO Meter Data Validation Dx |  |  | Customer Care Services Dx | Imran.Merali@HydroOne.com | Imran.Merali@HydroOne.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | EMPP init | Executing | Short Term Planning | # Validations | 0 | 0 | 69818.7666 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69818.7666 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal: Base Case
23831 | Smiths Falls TS M25 ID27370 DX 3M Perth Cogen | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000199 |  | AIP000199 | Yes | AIP000199 | Large Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23832 | Smiths Falls TS M25 ID27370 TX 3M Perth Cogen | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23833 | Leaside TS - BY (27.6kV) Yard - Revenue Metering | N.T.C.1.42 | 7700 | 203 | PROJECT DELIVERY | AIP000425 |  | AIP000425 | Yes | AIP000425 | Leaside TS: 27.6kV Yard & Component Replacements |  |  | Central Zone Station/Yard Investments | James.Mardegan@HydroOne.com | michael.xavier@hydroone.com | System Renewal | Greater Toronto Area | Not Required | 01 - Agreement (current/future) | Not Required | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23834 | Protective Relaying Database for CAPE | N.T.C.1.19 | 7716 | 224 | ENGINEERING | AIP005556 | AIP005556 | AIP005556 | No | AIP005556 | Protective Relaying Database for CAPE | 0 |  | Protection Control & Metering Equip | Miroslav.Kostic@HydroOne.com | Murched.Ajami@HydroOne.com | System Renewal | N/A | Not Required | 03 - None (default) | Not Required | Project | ACTN EMPP | Executing | Executing |  | 1814033.4933 | 1215686.4221 | 0.019656 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1814033.4933 | 1215686.4221 | 0.019656 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42917 | 43707 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Alternative 1
23835 | HMI Replacement | N.T.C.3.08 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Integrating Operating Infrastructure | Miroslav.Kostic@HydroOne.com | [6 empty] | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23837 | Don Mouth Naturalization&Port Lands Flood Protect | N.T.C.1.14 | 7700 | 203 | PROJECT DELIVERY | AIP005445 |  | AIP005445 | Yes | AIP005445 |  |  |  | Third Party Transmission System Modifications | john.boldt@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23839 | R&D Program - EPRI | N.C.M.2.21 | 4230 | 213 | PLANNING | AIP005490 | AIP005490 | AIP005490 | No | AIP005490 | R&D Program - EPRI - CONTRACT 2018 | 0 |  | Research Development and Demonstration | Daila.Dzintars@HydroOne.com | janet.eby@Hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | AWRD | Short Term Planning | Short Term Planning | # of Final Reports | 3245000.12 | 3310000 | 3376000.04 | 3443999.88 | 3513000.12 | 3583000 | 0 | 0 | 0 | 0 | 3245000.12 | 3310000 | 3376000.04 | 3443999.88 | 3513000.12 | 3583000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | True | 3rd Party Contract with EPRI until end of 2018 | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Reaggregated (Vulnerable)
23840 | Chatham SS-MTO-Bell Conduit & Access Rd Relocation | N.T.C.1.14 | 7700 | 203 | PROJECT DELIVERY | AIP005599 | AIP005599 | AIP005599 | No | AIP005599 | Chatham SS-MTO-Bell Conduit & Access Rd Relocation | 0 |  | Third Party Transmission System Modifications | john.boldt@HydroOne.com | Gian.Minichini@HydroOne.com | System Renewal | Western | 0 | 01 - Agreement (current/future) | 0 | Project | DETL EXTR | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 532000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -532000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43266 | 43359 | True | MTO has required Bell to relocate a telecom line that was servicing Chatham SS. HONI needs to reconfigure/install telecom equipment/services at Chatham SS as a result. MTO will pay for this work. | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Chatham SS-MTO-Bell Conduit & Access Rd Relocation
23841 | Thorold Defoe DS Voltage Conversion | N.D.C.2.02 | 7374 | 205 | LINES | AIP005592 | AIP005592 | AIP005592 | No | AIP005592 | Thorold Defoe DS Voltage Conversion | ISD-SR-13 | Life Cycle Optimization & Operational Efficiency Projects | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Mark.VanTol@hydroone.com | System Renewal | Western | 0 | 03 - None (default) | 0 | Project | EMPP AWRD | Executing | Executing |  | 436186.0574 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 469017.2661 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -32831.2086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43191 | 43449 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
23843 | Nanticoke TS; CGVB Switch Replacement | N.T.C.1.41 | 7700 | 203 | PROJECT DELIVERY | AIP005552 |  | AIP005552 | Yes | AIP005552 |  |  |  | Hamilton/Niagara Zone Station/Yard Investments | James.Mardegan@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23844 | Nanticoke TS; ABCB Project | N.T.C.1.41 | 7700 | 203 | PROJECT DELIVERY | AIP005554 | AIP005554 | AIP005554 | No | AIP005554 | Nanticoke ABCB Station Refurbishment Project | SR-01 | Air Blast Circuit Breaker Replacement Projects | Hamilton/Niagara Zone Station/Yard Investments | James.Mardegan@HydroOne.com | Fred.Kouhdani@HydroOne.com | System Renewal | Hamilton Niagara | 0 | 03 - None (default) | 0 | Project | BEST ACTN | Short Term Planning | Short Term Planning |  | 1669051.4624 | 20026694.5955 | 7523564.6104 | 3698311.554 | 2957572.934 | 0 | 0 | 0 | 0 | 0 | 1794678.9919 | 21534080.2102 | 8089854.4198 | 3976679.0903 | 3180185.9506 | 0 | 0 | 0 | 0 | 0 | -125627.5294 | -1507385.6147 | -566289.8094 | -278367.5363 | -222613.0165 | 0 | 0 | 0 | 0 | 0 | -7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43555 | 44869 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 2 | 0 | Alternative 1
23845 | Replacement of Waste Storage Sites - 2015/2016 | N.D.C.1.04 | 4220 | 209 | HEALTH, SAFETY & ENV | AIP005478 |  | AIP005478 | Yes | AIP005478 |  |  |  | PCB Transformer Replacement | emre.aydin@HydroOne.com | [6 empty] | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23846 | Placeholder Upgrade/Enhancements to GIS | N.D.C.2.60 | 4330 | 212 | INFO SOLUTIONS DIVISION | AIP005551 |  | AIP005551 | Yes | AIP005551 |  |  |  | IT Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23847 | NERC CIP Version 6 - OPEX | N.T.M.1.29 | 838 | 212 | INFO SOLUTIONS DIVISION | AIP005367 | AIP005367 | AIP005367 | No | AIP005367 | NERC CIP V6 OMA Low Impact | 0 |  | NERC Cyber Security Compliance Readiness | lincoln.frost-hunt@hydroone.com | Sherry.Wilging@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Project | EMPP AWRD | Executing | Executing |  | 966091.7144 | 993224.3191 | 995032.7646 | 997276.6886 | 997643.8409 | 997988.9196 | 0 | 0 | 0 | 0 | 966091.7144 | 993224.3191 | 995032.7646 | 997276.6886 | 997643.8409 | 997988.9196 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43131 | 42826 | False |  | False |  | False |  | False | False |  | False | False | False | False | TRUE | Funding the work leading up to the NERC CIP V6 compliance date of Dec 1 2018 to be compliant and off set Transient Sustainment for Medium and High sites. | 0 | 0 | Asset Optimal
23848 | CIP V6 Transient Cyber Assets & Removeable Media | N.T.C.1.29 | 4512 | 212 | INFO SOLUTIONS DIVISION | AIP005375 | AIP005375 | AIP005375 | No | AIP005375 | CIP V6 Transient Cyber Assets & Removeable Media | 0 |  | NERC Cyber Security Compliance Readiness | lincoln.frost-hunt@hydroone.com | Sherry.Wilging@hydroone.com | System Renewal | 0 | 0 | 03 - None (default) | 0 | Project | AWRD EMPP | Executing | Executing |  | 5465993.8097 | 1962038.1708 | 1945631.6844 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5465993.8097 | 1962038.1708 | 1945631.6844 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43132 | 44162 | False |  | True | CIP-010 | False |  | False | False |  | False | False | False | False | TRUE | This investment is to extend the Transient solution used to connect with BES Cyber Systems. Hydro One field staff currently use notebooks for the troubleshooting, commissioning and maintenance of protection and control cyber assets. A POC to be conducted in 2017 and roll out to the stations 2018-2020. | 0 | 0 | Asset Optimal
23850 | Retailer, Budget Billing, and Unbilled Revenue Opt | N.D.M.2.60 | 4339 | 212 | INFO SOLUTIONS DIVISION | UNPLND |  |  | Yes |  |  |  |  | IT Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23851 | Retailer, Budget Billing, and Unbilled Revenue Opt | N.D.C.2.60 | 4339 | 212 | INFO SOLUTIONS DIVISION | UNPLND |  |  | Yes |  |  |  |  | IT Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | EMPP AWRD | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23852 | Don Mouth Naturalization&Port Lands Development | N.T.M.1.14 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Engineering and Environmental Support | Mike.Tanaskovic@HydroOne.com | [6 empty] | Project | ACTN BEST | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23854 | Hawtorne TS Accommodation Trailer 2015 | N.T.C.1.28 | 7236 | 215 | FACILITIES & REAL ESTATE | AIP000664 |  | AIP000664 | Yes | AIP000664 |  |  |  | Transmission Site Facilities | cindy.copp@hydroone.com | [6 empty] | Program | EMPP AWRD | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23859 | Listowel SC Metal Roof Coating 2015 | N.D.C.1.50 | 7236 | 215 | FACILITIES & REAL ESTATE | AIP000027 |  | AIP000027 | Yes | AIP000027 | Facility Accommodation & Improvements Service Centres & Admin |  |  | Real Estate Facilities | cindy.copp@hydroone.com | Peter.Erdman@HydroOne.com | General Plant | 0 | 0 | 03 - None (default) | 0 | Program | EMPP AWRD | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23860 | R&D Program - CEATI | N.C.M.2.21 | 4230 | 213 | PLANNING | AIP005493 | AIP005493 | AIP005493 | No | AIP005493 | R&D Program - CEATI - Non Contract | 0 |  | Research Development and Demonstration | Daila.Dzintars@HydroOne.com | janet.eby@Hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | AWRD | Short Term Planning | Short Term Planning |  | 522000 | 527000 | 538000 | 549999.92 | 560999.88 | 512000 | 584000 | 595000 | 607000 | 0 | 522000 | 527000 | 538000 | 549999.92 | 560999.88 | 512000 | 584000 | 595000 | 607000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Vulnerable
23861 | PlaceholderRD&D Project - Grid Mod& Energy Storage | N.D.M.2.21 | 4230 | 213 | PLANNING | AIP005498 | AIP005498 | AIP005498 | No | AIP005498 | RD&D Project - Grid Modernization and Energy Storage |  |  | Distribution RD&D | Daila.Dzintars@HydroOne.com | janet.eby@Hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 3106234.3918 | 3137744.6841 | 3241718.9096 | 3317739.6047 | 3342782.106 | 0 | 0 | 0 | 0 | 0 | 3106234.3918 | 3137744.6841 | 3241718.9096 | 3317739.6047 | 3342782.106 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43100 | 44927 | [13 empty] | FALSE |  | 0 | 0 | Vulnerable
23862 | Stirton TS: Swyd Refurbishment & Component Repl | N.T.C.1.41 | 7700 | 203 | PROJECT DELIVERY | AIP005557 |  | AIP005557 | Yes | AIP005557 |  |  |  | Hamilton/Niagara Zone Station/Yard Investments | James.Mardegan@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23863 | Awenda DS F1 Upgrade Supply to Christian Island | N.D.C.2.02 | 7374 | 205 | LINES | AIP005380 | AIP005380 | AIP005380 | No | AIP005380 | Awenda DS F1 Upgrade - Supply to Christian Island | ISD-SS-02 | System Upgrades Driven by Load Growth | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Matthew.Bell@HydroOne.com | System Service | 0 | 0 | 03 - None (default) | 0 | Project | ACTN DETL | Short Term Planning | Short Term Planning |  | 917189.1372 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1042260.3832 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -125071.246 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42885 | 43189 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
23864 | Station Local Control Equipment Sustainment | N.T.C.3.08 | 7700 | 203 | PROJECT DELIVERY | AIP005443 |  | AIP005443 | Yes | AIP005443 |  |  |  | Integrating Operating Infrastructure | Miroslav.Kostic@HydroOne.com | [6 empty] | Program | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23865 | Niagara Area Fiber Infrastructure Development | N.T.C.1.25 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Auxiliary Telecommunication Equipment | Miroslav.Kostic@HydroOne.com | [6 empty] | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23866 | Simcoe OC Metal Roof Coating 2015 | N.D.C.1.50 | 7236 | 215 | FACILITIES & REAL ESTATE | AIP000027 |  | AIP000027 | Yes | AIP000027 | Facility Accommodation & Improvements Service Centres & Admin |  |  | Real Estate Facilities | cindy.copp@hydroone.com | Peter.Erdman@HydroOne.com | General Plant | 0 | 0 | 03 - None (default) | 0 | Program | EMPP AWRD | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23867 | Minden CC Metal Roof Coating 2015 | N.D.C.1.50 | 7236 | 215 | FACILITIES & REAL ESTATE | AIP000027 |  | AIP000027 | Yes | AIP000027 | Facility Accommodation & Improvements Service Centres & Admin |  |  | Real Estate Facilities | cindy.copp@hydroone.com | Peter.Erdman@HydroOne.com | General Plant | 0 | 0 | 03 - None (default) | 0 | Program | AWRD EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23868 | Lambton CC Metal Roof Coating 2015 | N.D.C.1.50 | 7236 | 215 | FACILITIES & REAL ESTATE | AIP000027 |  | AIP000027 | Yes | AIP000027 | Facility Accommodation & Improvements Service Centres & Admin |  |  | Real Estate Facilities | cindy.copp@hydroone.com | Peter.Erdman@HydroOne.com | General Plant | 0 | 0 | 03 - None (default) | 0 | Program | AWRD EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23869 | Fenlon Falls SC Metal Roof Coating 2015 | N.D.C.1.50 | 7236 | 215 | FACILITIES & REAL ESTATE | AIP000027 |  | AIP000027 | Yes | AIP000027 | Facility Accommodation & Improvements Service Centres & Admin |  |  | Real Estate Facilities | cindy.copp@hydroone.com | Peter.Erdman@HydroOne.com | General Plant | 0 | 0 | 03 - None (default) | 0 | Program | EMPP AWRD | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23871 | ITC - J5D Protection and Telecom Replacement | N.T.C.1.19 | 7700 | 203 | PROJECT DELIVERY | AIP005489 | AIP005489 | AIP005489 | No | AIP005489 | ITC - J5D Protection and Telecom Replacement | 0 |  | Protection Control & Metering Equip | Miroslav.Kostic@HydroOne.com | Abu.Zahid@hydroone.com | System Renewal | Western | Not Required | 01 - Agreement (current/future) | TBD | Project | init | Short Term Planning | Short Term Planning |  | 0 | 495509.5427 | 2063913.1506 | 946733.0391 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 495509.5427 | 2257727.3899 | 1066815.5648 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -93814.2392 | -45082.5257 | 0 | 0 | 0 | 0 | 0 | 0 | -3.8462 | 0 | 0 | 0 | -100000 | -75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43836 | 44355 | False |  | False |  | False |  | False | False |  | False | False | False | False | TRUE | International Facilities Agreement (IFA) between HONI and ITC obligates both parties to carry extraordinary maintenance, repair and end-of-life replacement on IPL and its associated equipment. | 0 | 0 | Alternative Protection Solution
23872 | ITC - L4D L51D Line Protection and Telecom Replace | N.T.C.1.19 | 7700 | 203 | PROJECT DELIVERY | AIP005488 |  | AIP005488 | Yes | AIP005488 |  |  |  | Protection Control & Metering Equip | Miroslav.Kostic@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23873 | Longueuil TS M26 ID12510 DX Alfred Solar Farm | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000195 |  | AIP000195 | Yes | AIP000195 | Small Embedded Generation (E/PD) |  |  | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23875 | Lincoln SC Metal Roof Coating 2015 | N.D.C.1.50 | 7236 | 215 | FACILITIES & REAL ESTATE | AIP000027 |  | AIP000027 | Yes | AIP000027 | Facility Accommodation & Improvements Service Centres & Admin |  |  | Real Estate Facilities | cindy.copp@hydroone.com | Peter.Erdman@HydroOne.com | General Plant | 0 | 0 | 03 - None (default) | 0 | Program | AWRD EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23876 | Remote Disconnection Program | N.D.C.1.09 | 7374 | 205 | LINES | AIP005540 | AIP005540 | AIP005540 | No | AIP005540 | Remote Disconnection Program | ISD-SS-01 | Remote Disconnection / Reconnection Program | Metering | Peter.Mitskos@HydroOne.com | Dominic.Consorti@HydroOne.com | System Service | 0 | 0 | 03 - None (default) | 0 | Program | AWRD EMPP | Executing | Short Term Planning |  | 5822934.6142 | 5776891.0175 | 5722913.357 | 5655552.8333 | 5570755.0854 | 0 | 0 | 0 | 0 | 0 | 5941770.0145 | 5894786.7525 | 5839707.5072 | 5770972.2789 | 5684443.9647 | 0 | 0 | 0 | 0 | 0 | -118835.4003 | -117895.7351 | -116794.1501 | -115419.4456 | -113688.8793 | 0 | 0 | 0 | 0 | 0 | -2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11875 | 11500 | 11125 | 10750 | 10375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
23878 | Beach TS HVAC Replacement 2015 | N.T.C.1.28 | 7236 | 215 | FACILITIES & REAL ESTATE | AIP000667 |  | AIP000667 | Yes | AIP000667 |  |  |  | Transmission Site Facilities | cindy.copp@hydroone.com | [6 empty] | Program | AWRD EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23879 | Winchester OC Trailer Acquisition 2015 | N.D.C.1.50 | 7236 | 215 | FACILITIES & REAL ESTATE | AIP000027 |  | AIP000027 | Yes | AIP000027 | Facility Accommodation & Improvements Service Centres & Admin |  |  | Real Estate Facilities | cindy.copp@hydroone.com | Peter.Erdman@HydroOne.com | General Plant | 0 | 0 | 03 - None (default) | 0 | Program | AWRD EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23880 | Essex OC Metal Roof Coating 2015 | N.D.C.1.50 | 7236 | 215 | FACILITIES & REAL ESTATE | AIP000027 |  | AIP000027 | Yes | AIP000027 | Facility Accommodation & Improvements Service Centres & Admin |  |  | Real Estate Facilities | cindy.copp@hydroone.com | Peter.Erdman@HydroOne.com | General Plant | 0 | 0 | 03 - None (default) | 0 | Program | EMPP AWRD | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23881 | East Elgin OC Metal Roof Coating 2015 | N.D.C.1.50 | 7236 | 215 | FACILITIES & REAL ESTATE | AIP000027 |  | AIP000027 | Yes | AIP000027 | Facility Accommodation & Improvements Service Centres & Admin |  |  | Real Estate Facilities | cindy.copp@hydroone.com | Peter.Erdman@HydroOne.com | General Plant | 0 | 0 | 03 - None (default) | 0 | Program | AWRD EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23883 | Clinton OC Metal Roof Coating 2015 | N.D.C.1.50 | 7236 | 215 | FACILITIES & REAL ESTATE | AIP000027 |  | AIP000027 | Yes | AIP000027 | Facility Accommodation & Improvements Service Centres & Admin |  |  | Real Estate Facilities | cindy.copp@hydroone.com | Peter.Erdman@HydroOne.com | General Plant | 0 | 0 | 03 - None (default) | 0 | Program | EMPP AWRD | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23884 | Removals - Revenue Meter Installations | N.D.C.2.05 | 7700 | 203 | PROJECT DELIVERY | AIP000203 | AIP000203 | AIP000203 | No | AIP000203 | Revenue Meter - Removals |  |  | Wholesale Metering | Peter.Mitskos@HydroOne.com | Dominic.Consorti@HydroOne.com | System Access | 0 | 0 | 03 - None (default) | 0 | Program | DETL ACTN | Short Term Planning | Short Term Planning | # of Meter Installations | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 221480.45 | 225910.12 | 230428.28 | 235036.84 | 239737.6 | 0 | 0 | 0 | 0 | 0 | -221480.45 | -225910.12 | -230428.28 | -235036.84 | -239737.6 | 0 | 0 | 0 | 0 | 0 | -100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Vulnerable
23886 | Tilbury TS M1 Transfer | N.D.C.2.02 | 7374 | 205 | LINES | AIP000185 |  | AIP000185 | Yes | AIP000185 | (3) Reliability Improvements |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Michael.Medeiros@HydroOne.com | System Service | 0 | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23887 | Remote Disconnect/Reconnect - M&RS Support | N.D.M.1.05 | 8706 | 214 | METER SHOP | UNPLND |  |  | Yes |  |  |  |  | Customer Meters | Peter.Mitskos@HydroOne.com | [6 empty] | Project | EMPP init | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23888 | Panasonic/UOIT - Microgrid Research | N.D.M.2.22 | 4230 | 213 | PLANNING |  |  |  | No | [12 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23889 | Tomken TS: Revenue Metering Upgrade | N.T.C.2.11 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Load Customer Connection | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23890 | Barry's Bay Trailer Acquisition 2015 | N.D.C.1.50 | 7236 | 215 | FACILITIES & REAL ESTATE | AIP000027 |  | AIP000027 | Yes | AIP000027 | Facility Accommodation & Improvements Service Centres & Admin |  |  | Real Estate Facilities | cindy.copp@hydroone.com | Peter.Erdman@HydroOne.com | General Plant | 0 | 0 | 03 - None (default) | 0 | Program | EMPP AWRD | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23891 | OEB Package 1 - CAP Portion | N.D.C.2.60 | 4339 | 212 | INFO SOLUTIONS DIVISION | UNPLND |  |  | Yes |  |  |  |  | IT Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | AWRD | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23892 | OEB Package 1 - OMA Portion | N.D.M.2.60 | 4339 | 212 | INFO SOLUTIONS DIVISION | UNPLND |  |  | Yes |  |  |  |  | IT Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23893 | PSP Lockbox | N.T.C.1.29 | 7700 | 203 | PROJECT DELIVERY | AIP005945 | AIP005945 | AIP005945 | No | AIP005945 | PSP Lockbox | 0 |  | NERC Cyber Security Compliance Readiness | lincoln.frost-hunt@hydroone.com | Tameeza.Dhanani@HydroOne.com | System Renewal | 0 | 0 | 0 | 0 | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0.53072 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.53072 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43069 | [13 empty] | FALSE |  | 0 | 0 | PSP Lockbox
23895 | SAP Hold Co - OMA Portion | N.C.M.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION | AIP005578 |  | AIP005578 | Yes | AIP005578 |  |  |  | IT-Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | EMPP AWRD | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23896 | Online DGA Monitor Program | N.T.C.1.46 | 7700 | 203 | PROJECT DELIVERY | AIP000562 | AIP000562 | AIP000562 | No | AIP000562 | Transformer Monitoring | 0 |  | Tx Station Demand and Spares | James.Mardegan@HydroOne.com | peter.zhao@hydroone.com | System Renewal | 0 | 0 | 03 - None (default) | 0 | Program | EMPP ACCP | Executing | Short Term Planning | # of Monitor Systems | 1556387.5041 | 1582158.7986 | 1600443.6176 | 1612840.1899 | 1625095.1579 | 1643366.3677 | 0 | 0 | 0 | 0 | 1556387.5041 | 1582158.7986 | 1600443.6176 | 1612840.1899 | 1625095.1579 | 1643366.3677 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 10 | 10 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Intermediate
23898 | Kirkland Lake TS - M62 - ID26950 - Tx GT CH4 | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | EMPP ACTN | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23899 | Kirkland Lake TS - M62 - ID26950 - Dx GT CH4 | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000195 |  | AIP000195 | Yes | AIP000195 | Small Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23901 | Orangeville SC Storage Yard Grading 2015 | N.C.C.1.50 | 7236 | 215 | FACILITIES & REAL ESTATE |  |  |  | No |  |  |  |  | Real Estate Facilities | cindy.copp@hydroone.com | [6 empty] | Program | EMPP AWRD | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23904 | C23Z :Connect Belle River Wind Project | N.T.C.2.12 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Generator Customer Connection | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23905 | Esplanade TS Windows Replacement 2015 | N.T.C.1.28 | 7236 | 215 | FACILITIES & REAL ESTATE | AIP000664 |  | AIP000664 | Yes | AIP000664 |  |  |  | Transmission Site Facilities | cindy.copp@hydroone.com | [6 empty] | Program | AWRD EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23907 | Cobden SC HVAC 2015 | N.D.C.1.50 | 7236 | 215 | FACILITIES & REAL ESTATE | AIP000027 |  | AIP000027 | Yes | AIP000027 | Facility Accommodation & Improvements Service Centres & Admin |  |  | Real Estate Facilities | cindy.copp@hydroone.com | Peter.Erdman@HydroOne.com | General Plant | 0 | 0 | 03 - None (default) | 0 | Program | EMPP AWRD | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23909 | Bruce SC - Stairs 2015 | N.T.C.1.28 | 7236 | 215 | FACILITIES & REAL ESTATE | AIP000664 |  | AIP000664 | Yes | AIP000664 |  |  |  | Transmission Site Facilities | cindy.copp@hydroone.com | [6 empty] | Program | AWRD EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23918 | Kirkland Lake TS - M62 - ID26970 - Tx GT CH2 | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | EMPP ACTN | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23919 | Kirkland Lake TS - M62 - ID26970 - Dx GT CH2 | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000195 |  | AIP000195 | Yes | AIP000195 | Small Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23924 | Kirkland Lake TS - M62 - ID27160 - Tx GT CH16 | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23925 | Kirkland Lake TS - M62 - ID26980 - Tx GT CH9 | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | EMPP ACTN | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23926 | Kirkland Lake TS - M62 - ID26980 - Dx GT CH9 | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000195 |  | AIP000195 | Yes | AIP000195 | Small Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23927 | Kirkland Lake TS - M62 - ID26990 - Tx GT CH13 | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23928 | Kirkland Lake TS - M62 - ID26990 - Dx GT CH13 | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000195 |  | AIP000195 | Yes | AIP000195 | Small Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | EMPP ACTN | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23929 | Kirkland Lake TS - M62 - ID27000 - Tx GT CH7 | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23930 | Science Hill DS - F1 - ID27790 - Dx | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000191 |  | AIP000191 | Yes | AIP000191 | Small Embedded Generation |  |  | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning | # of Gen Connections | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23931 | Kirkland Lake TS - M62 - ID27150 - Tx GT CH8 | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23932 | Kirkland Lake TS - M62 - ID27150 - Dx GT CH8 | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000195 |  | AIP000195 | Yes | AIP000195 | Small Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | EMPP ACTN | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23933 | Parry Sound TS M4 ID 27760-TX-Lakeland Power | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23935 | Kirkland Lake TS - M62 - ID27000 - Dx GT CH7 | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000195 |  | AIP000195 | Yes | AIP000195 | Small Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | EMPP ACTN | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23936 | Kirkland Lake TS - M62 - ID27010 - Tx GT CH14 | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23937 | Kirkland Lake TS - M62 - ID27010 - Dx GT CH14 | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000195 |  | AIP000195 | Yes | AIP000195 | Small Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23938 | Kirkland Lake TS - G3K - ID27420 - Tx Matachewan | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23939 | Kirkland Lake TS - G3K - ID27420 - Dx Matachewan | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000191 |  | AIP000191 | Yes | AIP000191 | Small Embedded Generation | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning | # of Gen Connections | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23940 | Kirkland Lake TS - M62 - ID27140 - Tx GT CH3 | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23941 | Kirkland Lake TS - M62 - ID27140 - Dx GT CH3 | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000195 |  | AIP000195 | Yes | AIP000195 | Small Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23942 | Kirkland Lake TS - G3K - ID27430 - Tx KL 3 | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23943 | Kirkland Lake TS - G3K - ID27430 - Dx KL 3 | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000195 |  | AIP000195 | Yes | AIP000195 | Small Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23944 | Cobden SC - Site Grading 2015 | N.D.C.1.50 | 7236 | 215 | FACILITIES & REAL ESTATE | AIP000027 |  | AIP000027 | Yes | AIP000027 | Facility Accommodation & Improvements Service Centres & Admin |  |  | Real Estate Facilities | cindy.copp@hydroone.com | Peter.Erdman@HydroOne.com | General Plant | 0 | 0 | 03 - None (default) | 0 | Program | AWRD EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23945 | Carlton TS M17 ID27930-Shickluna | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23946 | Kirkland Lake TS - G3K - ID27440 - Tx KL 2 | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | EMPP ACTN | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23947 | Kirkland Lake TS - G3K - ID27440 - Dx KL 2 | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000195 |  | AIP000195 | Yes | AIP000195 | Small Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23948 | Woodstock OC - Land Acquisition 2015 | N.D.C.1.50 | 7236 | 215 | FACILITIES & REAL ESTATE | AIP000027 |  | AIP000027 | Yes | AIP000027 | Facility Accommodation & Improvements Service Centres & Admin |  |  | Real Estate Facilities | cindy.copp@hydroone.com | Peter.Erdman@HydroOne.com | General Plant | 0 | 0 | 03 - None (default) | 0 | Program | AWRD EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23949 | Duart TS - Feeder M5 - DG 487 Distance Limitation | N.D.M.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP005618 | AIP005618 | AIP005618 | No | AIP005618 | Duart TS - Feeder M5 - DG 487 Distance Limitation |  |  | Distributed Generation Connections | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System O&M | 0 | 0 | 0 | 0 | Project | EMPP ACTN | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42643 | [13 empty] | FALSE |  | 0 | 0 | Alternative 1
23950 | Kirkland Lake TS - M62 - ID27160 - Dx GT CH16 | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000195 |  | AIP000195 | Yes | AIP000195 | Small Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23951 | Bathurst TS - Support Customer Duct Work | N.T.C.2.11 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Load Customer Connection | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | EXTR | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23952 | Finch/Warden/Runnymede Customer Fiber Support Work | N.T.C.2.11 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Load Customer Connection | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23953 | Kirkland Lake TS - G3K - ID27450 - Tx KL 1 | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | EMPP ACTN | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23954 | Kirkland Lake TS - G3K - ID27450 - Dx KL 1 | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000195 |  | AIP000195 | Yes | AIP000195 | Small Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23955 | Minden SC Paiving and Drainage 2015 | N.D.C.1.50 | 7236 | 215 | FACILITIES & REAL ESTATE | AIP000027 |  | AIP000027 | Yes | AIP000027 | Facility Accommodation & Improvements Service Centres & Admin |  |  | Real Estate Facilities | cindy.copp@hydroone.com | Peter.Erdman@HydroOne.com | General Plant | 0 | 0 | 03 - None (default) | 0 | Program | AWRD EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23956 | Vale Copper#4 CTS - 230kV Supply Relocation | N.T.C.2.11 | 7700 | 203 | PROJECT DELIVERY | AIP006104 | AIP006104 | AIP006104 | No | AIP006104 | Vale Copper#4CTS - 230kV Supply Relocation | 0 |  | Load Customer Connection | Robert.Reinmuller@HydroOne.com | Kirpal.Bahra@HydroOne.com | System Access | 0 | 0 | 0 | 0 | Project | BEST ACTN | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 750000 | 750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -50000 | -750000 | -750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43677 | 44012 | True | Customer requested work- Vale Copper | True | Tranmission license requirement to connect customers. | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | 230kV Supply Relocation
23958 | ISD Customer Care | N.D.M.1.60 | 4042 | 212 | INFO SOLUTIONS DIVISION | AIP000285C | AIP000285 | AIP000285 | No | AIP000285 | ISD Customer Care |  |  | IT Business Improvements & Enhancements | lincoln.frost-hunt@hydroone.com | Wayne.Logan@HydroOne.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | init EMPP | Executing | Short Term Planning | Retainer | 417.9438 | 422.1737 | 422.9559 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 417.9438 | 422.1737 | 422.9559 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Vulnerable
23959 | Mid-Feeder Recloser Pilot - Integration with DMS | N.D.C.2.02 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23960 | Two Abandoned Towers near E2R Removal Non-Recovera | N.T.C.1.14 | 7700 | 203 | PROJECT DELIVERY | AIP000500 |  | AIP000500 | Yes | AIP000500 |  |  |  | Third Party Transmission System Modifications | john.boldt@HydroOne.com | [6 empty] | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23961 | George Bolton Parkway 44kV Expansion | N.D.C.2.02 | 7374 | 205 | LINES | UNPLND |  |  | Yes |  |  |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | [6 empty] | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23963 | AMI System Evaluation | N.D.C.1.09 | 4042 | 212 | INFO SOLUTIONS DIVISION | AIP005059A | AIP005059 | AIP005059 | No | AIP005059 | AMI Hardware Refresh |  |  | Metering | Peter.Mitskos@HydroOne.com | Dominic.Consorti@HydroOne.com | System Renewal | 0 | 0 | 03 - None (default) | 0 | Program | init | Short Term Planning | Short Term Planning | # of meters | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Vulnerable
23967 | Claireville TS, Trafalgar TS - Drainage Upgrade | N.T.C.1.43 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Greater Toronto Area Zone Station/Yard Investments | James.Mardegan@HydroOne.com | [6 empty] | Project | EMPP AWRD | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23968 | Kingston OC Concrete Pad 2015 | N.C.C.1.50 | 7236 | 215 | FACILITIES & REAL ESTATE | AIP000027 |  | AIP000027 | Yes | AIP000027 | Facility Accommodation & Improvements Service Centres & Admin |  |  | Real Estate Facilities | cindy.copp@hydroone.com | Peter.Erdman@HydroOne.com | General Plant | 0 | 0 | 03 - None (default) | 0 | Program | AWRD EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23969 | OGCC Washrooms & Kitchen & Cafeteria Upgrades 2015 | N.C.C.1.50 | 7236 | 215 | FACILITIES & REAL ESTATE | AIP000027 |  | AIP000027 | Yes | AIP000027 | Facility Accommodation & Improvements Service Centres & Admin |  |  | Real Estate Facilities | cindy.copp@hydroone.com | Peter.Erdman@HydroOne.com | General Plant | 0 | 0 | 03 - None (default) | 0 | Program | AWRD EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23970 | Belle River TS M4 ID28210 TX GE004 | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | EMPP ACTN | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23972 | Manby TS Watermain 2015 | N.T.C.1.28 | 7236 | 215 | FACILITIES & REAL ESTATE | AIP000670 |  | AIP000670 | Yes | AIP000670 |  |  |  | Transmission Site Facilities | cindy.copp@hydroone.com | [6 empty] | Program | AWRD EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23974 | South Nepean Trans Reinforcement | N.T.C.2.02 | 7700 | 203 | PROJECT DELIVERY | AIP005522 | AIP005522 | AIP005522 | No | AIP005522 | South Nepean Transmission Reinforcement | SS-13 | South Nepean Transmission Reinforcement | Local Area Supply | Robert.Reinmuller@HydroOne.com | Jean.Morneau@HydroOne.com | System Service | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACTN DETL | Short Term Planning | Short Term Planning |  | 736217.5772 | 0.0787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 736217.5772 | 1000000.0387 | 10000000 | 27500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0684e-10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -999999.96 | -10000000 | -27500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43692 | 44347 | True |  | True | Electricity Transmission License. ET-2003-0035. Section 8. | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Alternative 1
23975 | Five Nations Energy (FNEI) - Moosonee PLC channel | N.T.C.2.11 | 7700 | 203 | PROJECT DELIVERY | AIP005622 | AIP005622 | AIP005622 | No | AIP005622 | Five Nations Energy (FNEI) - Moosonee PLC channel | 0 |  | Load Customer Connection | Robert.Reinmuller@HydroOne.com | Kirpal.Bahra@HydroOne.com | System Access | 0 | 0 | 0 | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -200000 | -500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43405 | 43800 | True | Customer requested work- Five Nations Energy | True | IESO Reliabilty Compliance | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Enter Descriptive Name for Project Alternative
23976 | Bruce B SS HVAC Replacement 2015 | N.T.C.1.28 | 7236 | 215 | FACILITIES & REAL ESTATE | AIP000667 |  | AIP000667 | Yes | AIP000667 |  |  |  | Transmission Site Facilities | cindy.copp@hydroone.com | [6 empty] | Program | AWRD EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23979 | Phase 2: Fiber Cable Condition Monitoring System | N.T.C.1.25 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Auxiliary Telecommunication Equipment | Miroslav.Kostic@HydroOne.com | [6 empty] | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23980 | Manby TS 115kV Load Rejection Scheme | N.T.C.2.21 | 7700 | 203 | PROJECT DELIVERY | AIP005299 | AIP005299 | AIP005299 | No | AIP005299 | Manby TS - 115kV Load Rejection Scheme | 0 |  | Major Risk Mitigation | Robert.Reinmuller@HydroOne.com | Eva.Ping@HydroOne.com | System Service | 0 | Not Required | 03 - None (default) | Not Required | Project | ACCP EMPP | Executing | Executing |  | 1880911.4611 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1880911.4611 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43220 | True |  | True | Electricity Transmission License. ET-2003-0035. Section 8. | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Manby TS - 115kV Load Rejection Scheme
23985 | Penetanguishene concrete Pad 2015 | N.D.C.1.50 | 7236 | 215 | FACILITIES & REAL ESTATE | AIP000027 |  | AIP000027 | Yes | AIP000027 | Facility Accommodation & Improvements Service Centres & Admin |  |  | Real Estate Facilities | cindy.copp@hydroone.com | Peter.Erdman@HydroOne.com | General Plant | 0 | 0 | 03 - None (default) | 0 | Program | AWRD EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23991 | Brockville Office Tralier Renovations 2015 | N.D.C.1.50 | 7236 | 215 | FACILITIES & REAL ESTATE | AIP000027 |  | AIP000027 | Yes | AIP000027 | Facility Accommodation & Improvements Service Centres & Admin |  |  | Real Estate Facilities | cindy.copp@hydroone.com | Peter.Erdman@HydroOne.com | General Plant | 0 | 0 | 03 - None (default) | 0 | Program | AWRD EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23993 | TS Facilities & Site Improvements | N.T.C.1.28 | 7236 | 215 | FACILITIES & REAL ESTATE | AIP005577 | AIP005577 | AIP005577 | No | AIP005577 | TS Facilities & Site Improvements | GP-12 | Transmission Facilities & Site Improvements | Transmission Site Facilities | cindy.copp@hydroone.com | Peter.Erdman@HydroOne.com | General Plant | 0 | 0 | 03 - None (default) | 0 | Program | init EMPP | Executing | Short Term Planning | Retainer | 8452180.5203 | 9910191.7657 | 9828159.2866 | 9710082.2583 | 9592023.3974 | 9509673.718 | 0 | 0 | 0 | 0 | 8452180.5203 | 9910191.7657 | 9828159.2866 | 9710082.2583 | 9592023.3974 | 9509673.718 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | True | False |  | False | True | False | False | FALSE |  | 0 | 0 | Vulnerable (Modified - Tx Decision)
23994 | Tweed OC Drainage Improvement Design 2015 | N.D.C.1.50 | 7236 | 215 | FACILITIES & REAL ESTATE | AIP000027 |  | AIP000027 | Yes | AIP000027 | Facility Accommodation & Improvements Service Centres & Admin |  |  | Real Estate Facilities | cindy.copp@hydroone.com | Peter.Erdman@HydroOne.com | General Plant | 0 | 0 | 03 - None (default) | 0 | Program | AWRD EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23995 | Arnprior Fleet Garage - Exhaust System 2015 | N.C.C.1.50 | 7236 | 215 | FACILITIES & REAL ESTATE | AIP000027 |  | AIP000027 | Yes | AIP000027 | Facility Accommodation & Improvements Service Centres & Admin |  |  | Real Estate Facilities | cindy.copp@hydroone.com | Peter.Erdman@HydroOne.com | General Plant | 0 | 0 | 03 - None (default) | 0 | Program | EMPP AWRD | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23996 | Enterprise Content Management Phase B | N.C.C.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION | AIP005934 | AIP005934 | AIP005934 | No | AIP005934 | Enterprise Content Management Phase B | 0 |  | IT Business Solution Development | jj.blais@HydroOne.com | Myla.MendinuetoMartinez@HydroOne.com | General Plant | 0 | 0 | 0 | 0 | Project | AWRD EMPP | Executing | Executing |  | 2000000 | 1991445.4729 | 1973925.1336 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000 | 1991445.4729 | 1973925.1336 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44194 | [13 empty] | FALSE |  | 0 | 0 | Enterprise Content Management Phase B
23997 | Facilities Accommodation Improvements SC & Admin | N.C.C.1.50 | 7236 | 215 | FACILITIES & REAL ESTATE | AIP000027 | AIP000027 | AIP000027 | No | AIP000027 | Facility Accommodation & Improvements Service Centres & Admin | GP-11 | Facility Accommodation & Improvements Service Centres & Admin | Real Estate Facilities | cindy.copp@hydroone.com | Peter.Erdman@HydroOne.com | General Plant | 0 | 0 | 03 - None (default) | 0 | Program | init EMPP | Executing | Short Term Planning |  | 31068694.72 | 39907082.0976 | 39555987.4447 | 36149623.4452 | 35700018.1016 | 35386138.9144 | 0 | 0 | 0 | 0 | 31068694.72 | 39907082.0976 | 39555987.4447 | 36149623.4452 | 35700018.1016 | 35386138.9144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | True | Regulatory requirements for Orleans and Guelph, for customer response times. | False |  | False | LDC aquisition activities for Orillia, Woodstock & Haldimand | False | False |  | True | False | False | False | TRUE | The Field Facilities Capital work program focuses on undertaking facility work encompassing improvements, additions or new facilities on a priority and timely basis at a level of expenditure required to support the business operations to fully deliver the prescribed various work programs addressing network requirements, customer needs, corporate and government policy and regulatory/licensing directives in a safe, efficient and cost effective manner. This work is conducted on a project basis. | 0 | 0 | Vulnerable Post Enterprise Engagement
23998 | Wanstead TS M4 PET-6 Recloser Teleprotection Upgra | N.D.C.2.02 | 7700 | 203 | PROJECT DELIVERY | AIP000185 |  | AIP000185 | Yes | AIP000185 | (3) Reliability Improvements | ISD-SS-03 | Reliability Improvements | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Michael.Medeiros@HydroOne.com | System Service | 0 | 0 | 03 - None (default) | 0 | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23999 | Markham-Enbridge-IBM CTS Grounding Mods | N.T.C.1.14 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Third Party Transmission System Modifications | john.boldt@HydroOne.com | [6 empty] | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24000 | Almonte TS M25 ID26880 TX Enerdu Generation Expans | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24001 | SMNO Smart Meter Network Operations | N.D.M.4.01 | 8706 | 214 | METER SHOP | AIP000372 | AIP000372 | AIP000372 | No | AIP000372 | SMNO Smart Meter Network Operations |  |  | Customer Care Services Dx | Imran.Merali@HydroOne.com | Imran.Merali@HydroOne.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | EMPP ACTN | Executing | Short Term Planning | Retainer | 8222110.8011 | 7913526.1535 | 7516257.244 | 6751039.9587 | 6876819.2093 | 0 | 0 | 0 | 0 | 0 | 8222110.8011 | 7913526.1535 | 7516257.244 | 6751039.9587 | 6876819.2093 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Vulnerable: Base Case - Modified
24002 | New Facilities and Service Centers Improvements DX | N.D.C.1.50 | 7236 | 215 | FACILITIES & REAL ESTATE | AIP001215 | AIP001215 | AIP001215 | No | AIP001215 | Dx Facility Accommodation & Improvements |  |  | Real Estate Facilities | cindy.copp@hydroone.com | Peter.Erdman@HydroOne.com | General Plant | 0 | 0 | 01 - Agreement (current/future) | 0 | Program | init | Short Term Planning | Short Term Planning | Retainer | 17013750.9766 | 22019459.3906 | 16025917.5102 | 16034889.7779 | 13027918.9173 | 0 | 0 | 0 | 0 | 0 | 17013750.9766 | 22019459.3906 | 16025917.5102 | 16034889.7779 | 13027918.9173 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Plan B - Modified
24003 | PSIT Cyber Equipment EOL | N.T.C.1.29 | 4514 | 212 | INFO SOLUTIONS DIVISION | AIP005585 | AIP005585 | AIP005585 | No | AIP005585 | PSIT Cyber Equipment EOL | SR-18 | PSIT Cyber Equipment Replacement | NERC Cyber Security Compliance Readiness | lincoln.frost-hunt@hydroone.com | Sherry.Wilging@hydroone.com | System Renewal | 0 | 0 | 03 - None (default) | 0 | Program | AWRD EMPP | Executing | Short Term Planning |  | 5895063.7621 | 3931778.2047 | 3899045.8954 | 3851721.047 | 3804402.9162 | 3771397.1895 | 0 | 0 | 0 | 0 | 5895063.7621 | 3931778.2047 | 3899045.8954 | 3851721.047 | 3804402.9162 | 3771397.1895 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | False |  | False | False | False | False | TRUE | Cyber security equipment is used to secure the OGCC and BUCC. EOL equipment may not be able to protect the control centres with new threats/attacks or meet the latest NERC CIP requirements. | 0 | 0 | Asset Optimal
24005 | Striker DS F1 - ID29560 - Tx North Shore Power | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24006 | Striker DS F1 - ID29560 - Dx North Shore Power | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | Distribution Generation Connection | ryan.boudreau@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | EMPP ACTN | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24007 | Striker DS F1 - ID29570 - Tx North Shore Power | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24008 | Striker DS F1 - ID29570 - Dx North Shore Power | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | Distribution Generation Connection | ryan.boudreau@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24009 | Manotick DS F5 ID28120 DX 7251572 Canada Ltd. | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000199 |  | AIP000199 | Yes | AIP000199 | Large Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | EMPP ACTN | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24010 | Manotick DS F5 ID28120 TX 7251572 Canada Ltd. | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24011 | IESO Meter Data Validation - Stations | N.T.M.4.50 | 8706 | 214 | METER SHOP | AIP001192 | AIP001192 | AIP001192 | No | AIP001192 | IESO Meter Data Validation Tx | 0 |  | Customer Care Services Tx | Imran.Merali@HydroOne.com | Imran.Merali@HydroOne.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | init | Short Term Planning | Short Term Planning | # Validations | 0 | 0 | 70582.4252 | 0 | 0 | 75695.7664 | 0 | 0 | 0 | 0 | 0 | 0 | 70582.4252 | 0 | 0 | 75695.7664 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | True |  | False | False | False | False | FALSE |  | 0 | 0 | Asset Optimal: Base Case
24012 | Interval Meters - Stations | N.D.M.4.01 | 8706 | 214 | METER SHOP | AIP000363 | AIP000363 | AIP000363 | No | AIP000363 | Interval Meter Reading |  |  | Customer Care Services Dx | Imran.Merali@HydroOne.com | Imran.Merali@HydroOne.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | ACTN EMPP | Executing | Short Term Planning | # of meters | 1958531.2991 | 2247872.3689 | 2251984.7976 | 2256921.4086 | 2253892.5434 | 0 | 0 | 0 | 0 | 0 | 1958531.2991 | 2247872.3689 | 2251984.7976 | 2256921.4086 | 2253892.5434 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Vulnerable: Base Case
24013 | Placeholder Customer First Capital | N.D.C.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION | AIP005576 |  | AIP005576 | Yes | AIP005576 |  |  |  | IT Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24014 | Placeholder Customer First OMA | N.D.M.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION | AIP005579 |  | AIP005579 | Yes | AIP005579 |  |  |  | IT Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24017 | Palmerston TS T1/T2/T3; T1,T2,T3, PCT, MVGIS (Dx) | N.D.C.2.02 | 7700 | 203 | PROJECT DELIVERY | AIP000184 |  | AIP000184 | Yes | AIP000184 | (2) Asset Life Cycle Optimization & Operational Efficiency | ISD-SR-13 | Life Cycle Optimization & Operational Efficiency Projects | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Michael.Medeiros@HydroOne.com | System Renewal | 0 | 0 | 03 - None (default) | 0 | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24020 | Tilbury TS-M1-ID 1477-Tilbury Solar 2 Tx work | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000199 |  | AIP000199 | Yes | AIP000199 | Large Embedded Generation (E/PD) |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24021 | Allanburg TS M6-M7 (Fonthill) feeder tie | N.D.C.2.02 | 7374 | 205 | LINES | UNPLND |  |  | Yes |  |  |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | [6 empty] | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24022 | Grenfel DS Station Relief | N.D.C.2.02 | 7374 | 205 | LINES | AIP005648 | AIP005648 | AIP005648 | No | AIP005648 | Grenfel DS Station Relief |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | michael.sullivan@hydroone.com | System Service | 0 | Not Required | 03 - None (default) | Not Required | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42643 | 42885 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
24023 | NOMS-CROW Interface | N.C.C.3.01 | 4514 | 212 | INFO SOLUTIONS DIVISION | AIP000074 |  | AIP000074 | Yes | AIP000074 | NOMS Refresh |  |  | Common Oper Infrast & Control Facilities | Godfrey.Holder@HydroOne.com | emily.booth@hydroone.com | General Plant | 0 | Not Required | 03 - None (default) | Not Required | Project | EMPP AWRD | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24025 | Meter Management & Verification Ser (SLA 054) | N.D.M.1.05 | 8706 | 214 | METER SHOP | AIP000262 | AIP000262 | AIP000262 | No | AIP000262 | Meter Management and Verification |  |  | Customer Meters | Peter.Mitskos@HydroOne.com | Dominic.Consorti@HydroOne.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | EMPP ACTN | Executing | Short Term Planning | Retainer | 4593460.0859 | 4797691.9581 | 4941511.8623 | 5179794.9081 | 5407374.0786 | 0 | 0 | 0 | 0 | 0 | 4593460.0859 | 4797691.9581 | 4941511.8623 | 5179794.9081 | 5407374.0786 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Demand
24026 | Wholesale Meter Services Provider (MSP) | N.D.M.1.05 | 8706 | 214 | METER SHOP | AIP000263 | AIP000263 | AIP000263 | No | AIP000263 | Wholesale Meter Service |  |  | Customer Meters | Peter.Mitskos@HydroOne.com | Dominic.Consorti@HydroOne.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | ACTN EMPP | Executing | Short Term Planning | Assumption - # of Meter Points | 2983651.5885 | 2627924.9868 | 2814577.3736 | 3166119.968 | 3289495.485 | 0 | 0 | 0 | 0 | 0 | 2983651.5885 | 2627924.9868 | 2814577.3736 | 3166119.968 | 3289495.485 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 401 | 401 | 401 | 401 | 401 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Demand
24030 | Wholesale to Retail Standard (New meter w TCP/IP) | N.D.C.1.09 | 7374 | 205 | LINES | AIP000168 | AIP000168 | AIP000168 | No | AIP000168 | DS Meters - Wholesale to Retail Standard |  |  | Metering | Peter.Mitskos@HydroOne.com | Dominic.Consorti@HydroOne.com | System Access | 0 | 0 | 03 - None (default) | 0 | Program | EMPP ACTN | Executing | Short Term Planning | Assumption - # of Meter installation | 105164.1165 | 107275.4834 | 109501.3283 | 111753.9213 | 113985.2311 | 0 | 0 | 0 | 0 | 0 | 105164.1165 | 107275.4834 | 109501.3283 | 111753.9213 | 113985.2311 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 20 | 20 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Demand
24031 | Meter Inventory Sustainment | N.D.C.1.09 | 7374 | 205 | LINES | AIP000173 | AIP000173 | AIP000173 | No | AIP000173 | Sustainment of Meter Inventory | ISD-SA-02 | Metering Infrastructure Sustainment Program | Metering | Peter.Mitskos@HydroOne.com | Dominic.Consorti@HydroOne.com | System Access | 0 | 0 | 03 - None (default) | 0 | Program | ACTN EMPP | Executing | Short Term Planning | # of meters | 6425737.2958 | 6794517.4926 | 6933951.0371 | 7148459.034 | 7400684.9974 | 0 | 0 | 0 | 0 | 0 | 6425737.2958 | 6794517.4926 | 6933951.0371 | 7148459.034 | 7400684.9974 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25835 | 25835 | 25835 | 25566 | 25566 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
24032 | Nanticoke TS New 600V Station Service Supply | N.T.C.2.21 | 7700 | 203 | PROJECT DELIVERY | AIP005586 | AIP005586 | AIP005586 | No | AIP005586 | Nanticoke TS: New 600V Station Service Supply | 0 |  | Major Risk Mitigation | Robert.Reinmuller@HydroOne.com | Gene.Ng@HydroOne.com | System Service | 0 | 0 | 03 - None (default) | 0 | Project | ACCP EMPP | Executing | Executing |  | 156883.4086 | 0 | 0.0098282 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 470111.2749 | 0 | 0.0098282 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -313227.8663 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -66.6285 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43070 | [13 empty] | FALSE |  | 0 | 0 | Alternative 1
24033 | Small Embedded Generation - Connections | N.D.C.2.03 | 7374 | 205 | LINES | AIP000191C | AIP000191 | AIP000191 | No | AIP000191 | Small Embedded Generation |  |  | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 03 - None (default) | 0 | Program | init | Short Term Planning | Short Term Planning | # of Gen Connections | -105268.2807 | -110571.3561 | -115036.1593 | -119617.6718 | -124265.3815 | 0 | 0 | 0 | 0 | 0 | 3433470.1193 | 2897710.3239 | 2953411.1207 | 1966926.5282 | 2004009.6585 | 0 | 0 | 0 | 0 | 0 | 1.3878e-10 | 8.3267e-11 | -2.6368e-10 | 1.5266e-10 | -5.5511e-11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3538738.4 | -3008281.68 | -3068447.28 | -2086544.2 | -2128275.04 | 0 | 0 | 0 | 0 | 0 | 180 | 150 | 150 | 100 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
24035 | Kingston Gardiner TS M26 Development | N.D.C.2.02 | 7374 | 205 | LINES | AIP005651 | AIP005651 | AIP005651 | No | AIP005651 | Kingston Gardiner TS M26 Development | ISD-SS-02 | System Upgrades Driven by Load Growth | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Daniel.Weisser@HydroOne.com | System Service | Eastern | 0 | 03 - None (default) | 0 | Project | DETL ACTN | Short Term Planning | Short Term Planning |  | 917189.1372 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1042260.3832 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -125071.246 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42766 | 43404 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
24036 | Wilson TS M1 ID29460-TX Oshawa PUC Microgrid Resea | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24040 | Dynamic Energy Pricing Energate Pilot | N.D.M.2.50 | 1144 | 220 | STRATEGY & CONSERV | UNPLND |  |  | Yes |  |  |  |  | Conservation and Demand Management | Imran.Merali@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24041 | Murillo HVDS Feeder Protection Upgrade | N.D.C.2.02 | 7700 | 203 | PROJECT DELIVERY |  |  |  | No |  |  |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24042 | Nanticoke TS - Emergecy Feeder Connection | N.T.C.2.21 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Major Risk Mitigation | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24043 | TSSA Station Equipment Inspections | N.T.M.1.14 | 7370 | 206 | TX LINES AND STATIONS | AIP005756 | AIP005756 | AIP005756 | No | AIP005756 | TSSA Station Equipment Inspections | 0 |  | Engineering and Environmental Support | Mike.Tanaskovic@HydroOne.com | Farinaz.Yousefi@HydroOne.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | ACTN EMPP | Executing | Short Term Planning | Retainer | 196153.3263 | 195419.9987 | 195813.8478 | 196321.8544 | 196414.2615 | 196506.255 | 0 | 0 | 0 | 0 | 196153.3263 | 195419.9987 | 195813.8478 | 196321.8544 | 196414.2615 | 196506.255 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | True | Regulatory requirement | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Intermediate (Tx Constraint Reduction)
24044 | Fergus TS M7 ID28770 - Tx Elora GS | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | [6 empty] | Project | EMPP ACTN | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24045 | Simpson Road 44kV Expansion | N.D.C.2.02 | 7374 | 205 | LINES | UNPLND |  |  | Yes |  |  |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | [6 empty] | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24046 | Tx Coniston Voltage Conversion | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | DETL ACTN | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24047 | Hamilton - Anti-Climb - Recoverable | N.T.C.1.14 | 7700 | 203 | PROJECT DELIVERY | AIP000512 |  | AIP000512 | Yes | AIP000512 | Recoverable projects to be identified - Placeholder |  |  | Third Party Transmission System Modifications | john.boldt@HydroOne.com | Gian.Minichini@HydroOne.com | System Renewal | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24048 | Bala River DS F3 - ID28600 - Dx - Little Burgess | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000195 |  | AIP000195 | Yes | AIP000195 | Small Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | EMPP init | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24049 | Bala River DS F3 - ID28600 - Tx - Little Burgess | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | init EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24050 | Web Redesign: HydroOne.com | N.C.C.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION | AIP005775 |  | AIP005775 | Yes | AIP005775 |  |  |  | IT Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24051 | Newport DS removal via voltage conversion | N.D.C.2.02 | 7374 | 205 | LINES | AIP005659 | AIP005659 | AIP005659 | No | AIP005659 | Newport DS Voltage Conversion | ISD-SR-13 | Life Cycle Optimization & Operational Efficiency Projects | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Mark.VanTol@hydroone.com | System Renewal | Western | 0 | 03 - None (default) | 0 | Project | LLTM ACTN DETL | Short Term Planning | Short Term Planning |  | 844230.8503 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 938034.2782 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -93803.4278 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43103 | 43314 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
24052 | Town of Shelburne voltage conversion | N.D.C.2.02 | 7700 | 203 | PROJECT DELIVERY | AIP005661 | AIP005661 | AIP005661 | No | AIP005661 | Town of Shelburne Voltage Conversion | ISD-SS-02 | System Upgrades Driven by Load Growth | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Mark.VanTol@hydroone.com | System Service | Central | 0 | 03 - None (default) | 0 | Project | DETL ACTN | Short Term Planning | Short Term Planning |  | 2792256.7779 | 2792467.8096 | 2794519.3658 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3002426.6429 | 3002653.5587 | 3004859.5332 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -210169.865 | -210185.7491 | -210340.1673 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42979 | 44136 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
24053 | New Old School DS and feeders | N.D.C.2.02 | 7700 | 203 | PROJECT DELIVERY | AIP005642 | AIP005642 | AIP005642 | No | AIP005642 | Old School DS - New Station & Feeders | ISD-SS-02 | System Upgrades Driven by Load Growth | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Mark.VanTol@hydroone.com | System Service | Greater Toronto Area | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 331952.8133 | 1898878.1906 | 4750682.8418 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 356938.5089 | 2041804.506 | 5108261.1202 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -24985.6956 | -142926.3154 | -357578.2784 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43586 | 44135 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
24054 | Carling TS KY Bus ID29920 TX The Royal Ottawa Coge | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | EMPP ACTN | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24055 | Thorold Transmission Towers Removal | N.T.C.1.14 | 7700 | 203 | PROJECT DELIVERY | AIP005944 | AIP005944 | AIP005944 | No | AIP005944 | Thorold Transmission Towers Removal | 0 |  | Third Party Transmission System Modifications | john.boldt@HydroOne.com | Tyler.Wales@HydroOne.com | System Renewal | 0 | 0 | 0 | 0 | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -59360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43434 | [13 empty] | FALSE |  | 0 | 0 | Thorold Transmission Towers Removal
24057 | Hamilton - Anti-Climb - Recoverable | N.T.C.1.14 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Third Party Transmission System Modifications | john.boldt@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24058 | L29C - Connect North Kent Wind I Project | N.T.C.2.12 | 7700 | 203 | PROJECT DELIVERY | AIP005954 | AIP005954 | AIP005954 | No | AIP005954 | L29C - Connect North Kent Wind I Project | 0 |  | Generator Customer Connection | Robert.Reinmuller@HydroOne.com | Jennifer.Li@HydroOne.com | System Access | 0 | 0 | 0 | 0 | Project | EMPP ACCP | Executing | Executing |  | 149156.1268 | 0 | 0.0098282 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 174559.1268 | 0 | 0.0098282 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -25403 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43069 | [13 empty] | FALSE |  | 0 | 0 | L29C - Connect North Kent Wind I Project
24059 | Schomberg DS F4 ID29370 TX Foothill Greenhouses | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP005760 |  | AIP005760 | Yes | AIP005760 | Placeholder for Upstream Tx Work for DG (Project) |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24060 | Tillsongurg Norfolk Tie Line | N.D.C.2.02 | 7374 | 205 | LINES |  |  |  | No |  |  |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24061 | Collection Redesign CAP | N.D.C.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION | UNPLND |  |  | Yes |  |  |  |  | IT Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24062 | Collection Redesign OMA | N.D.M.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION | UNPLND |  |  | Yes |  |  |  |  | IT Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | EMPP AWRD | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24066 | Napanee TS - M2 - ID29150 - Tx - SFF 14 Solar PV | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | EMPP ACTN | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24067 | Napanee TS - M2 - ID29150 - Dx - SFF 14 Solar PV | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000195 |  | AIP000195 | Yes | AIP000195 | Small Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24068 | Napanee TS - M2 - ID29160 - Tx - SFF 09 Solar PV | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24069 | Napanee TS - M2 - ID29160 - Dx - SFF 09 Solar PV | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000195 |  | AIP000195 | Yes | AIP000195 | Small Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | EMPP ACTN | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24070 | Otonabee TS - M28 - ID29230 - Dx SFF 08 | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000195 |  | AIP000195 | Yes | AIP000195 | Small Embedded Generation (E/PD) |  |  | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24071 | Otonabee TS - M28 - ID29230 - Tx SFF 08 | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24072 | Dundas TS M8 ID29310 DX Neven Produce CoGen | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000199 |  | AIP000199 | Yes | AIP000199 | Large Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24073 | Dundas TS M8 ID29310 TX Neven Produce CoGen | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP005760 |  | AIP005760 | Yes | AIP005760 | Placeholder for Upstream Tx Work for DG (Project) |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | EMPP ACTN | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24074 | L3P/L4P Telecom and Protection Upgrade | N.T.C.1.25 | 7700 | 203 | PROJECT DELIVERY | AIP005641 | AIP005641 | AIP005641 | No | AIP005641 | L3P/L4P Protection and Telecom Upgrade | 0 |  | Auxiliary Telecommunication Equipment | Miroslav.Kostic@HydroOne.com | Sheraz.Majid@HydroOne.com | System Renewal | 0 | 0 | 03 - None (default) | 0 | Project | ACTN EMPP | Executing | Executing |  | 2198473.8045 | 11000.3118 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2198473.8045 | 11000.3118 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43392 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Asset Optimal
24075 | Napanee TS - M2 - ID29190 - Tx - SFF 23 Solar PV | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24076 | Napanee TS - M2 - ID29220 - Tx - SFF 01 Solar PV | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | EMPP ACTN | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24077 | Napanee TS - M2 - ID29220 - Dx - SFF 01 Solar PV | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000195 |  | AIP000195 | Yes | AIP000195 | Small Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24078 | Napanee TS - M2 - ID29190 - Dx - SFF 23 Solar PV | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000195 |  | AIP000195 | Yes | AIP000195 | Small Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24079 | Schomberg DS F4 ID29370 Dx Foothill Greenhouses | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000199 |  | AIP000199 | Yes | AIP000199 | Large Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | EMPP ACTN | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24081 | Tx Wood Pole Replacement Program - ECS | N.T.C.1.12 | 7370 | 206 | TX LINES AND STATIONS | AIP000474B | AIP000474 | AIP000474 | No | AIP000474 | Wood Pole Structure Replacements | SR-21 | Wood Pole Structure Replacements | Overhead Lines Component Refurb & Repl | hassan.hamzeh@hydroone.com | TeodorConstantin.Culinescu@HydroOne.com | System Renewal | 0 | 0 | 03 - None (default) | 0 | Program | ACTN EMPP | Executing | Short Term Planning | # of Structures | 17048108.7947 | 17315113.3249 | 17509795.8629 | 17608013.7322 | 17722816.0566 | 17917319.4255 | 0 | 0 | 0 | 0 | 19372850.9031 | 19676265.1419 | 19897495.2988 | 20009106.5139 | 20139563.7007 | 20360590.2563 | 0 | 0 | 0 | 0 | -2324742.1084 | -2361151.817 | -2387699.4359 | -2401092.7817 | -2416747.6441 | -2443270.8308 | 0 | 0 | 0 | 0 | -12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 425 | 425 | 425 | 425 | 425 | 425 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Vulnerable
24082 | Erindale TS - M42 - ID29470 - PepsiCo | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24085 | Otonabee TS-M28-ID29060-Dx GreenLife Solar 18 | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000195 |  | AIP000195 | Yes | AIP000195 | Small Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | EMPP ACTN | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24086 | Otonabee TS-M28-ID29060-Tx GreenLife Solar 18 | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24087 | Otonabee TS-M28-ID29080-Dx GreenLife Solar 7 | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000195 |  | AIP000195 | Yes | AIP000195 | Small Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24088 | Otonabee TS-M28-ID29080-Tx GreenLife Solar 7 | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | EMPP ACTN | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24089 | Barry's Bay Voltage Conversion | N.D.C.2.02 | 7374 | 205 | LINES | AIP005631 | AIP005631 | AIP005631 | No | AIP005631 | Barry's Bay Voltage Conversion | ISD-SR-13 | Life Cycle Optimization & Operational Efficiency Projects | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Daniel.Weisser@HydroOne.com | System Renewal | Eastern | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 1834378.2744 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2084520.7664 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -250142.492 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43014 | 43420 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
24090 | Aguasabon SS: Component Replacement | N.T.C.1.45 | 7700 | 203 | PROJECT DELIVERY | AIP005609 |  | AIP005609 | Yes | AIP005609 |  |  |  | Northern Zone Station/Yard Investments | James.Mardegan@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24091 | Ansonville TS: Component Replacement | N.T.C.1.45 | 7700 | 203 | PROJECT DELIVERY | AIP005610 | AIP005610 | AIP005610 | No | AIP005610 | Ansonville TS: Component Replacement | SR-07 | Protection and Automation Replacement Projects | Northern Zone Station/Yard Investments | James.Mardegan@HydroOne.com | Donald.Mastrangelo@HydroOne.com | System Renewal | Northern | Not Required | 03 - None (default) | Not Required | Project | init | Short Term Planning | Short Term Planning |  | 0 | 264669.9731 | 890391.0728 | 2159061.5977 | 6619878.3476 | 2376898.5993 | 0 | 0 | 0 | 0 | 0 | 284591.369 | 957409.7557 | 2321571.6104 | 7118148.7608 | 2555804.9455 | 0 | 0 | 0 | 0 | 0 | -19921.3958 | -67018.6829 | -162510.0127 | -498270.4133 | -178906.3462 | 0 | 0 | 0 | 0 | -7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44292 | 45229 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Component Replacement
24092 | Elliot Lake TS: Component Replacement | N.T.C.1.45 | 7700 | 203 | PROJECT DELIVERY | AIP005611 | AIP005611 | AIP005611 | No | AIP005611 | Elliot Lake TS: Component Replacement | SR-05 | Load Station Transformer Replacement Projects | Northern Zone Station/Yard Investments | James.Mardegan@HydroOne.com | Donald.Mastrangelo@HydroOne.com | System Renewal | Northern | Not Required | 03 - None (default) | Required | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 305572.4541 | 1057110.0738 | 3270523.7423 | 7615934.957 | 2872207 | 0 | 0 | 0 | 0 | 0 | 328572.5313 | 1136677.4988 | 3516692.1961 | 8189177.3732 | 3088394.56 | 0 | 0 | 0 | 0 | 0 | -23000.0772 | -79567.4249 | -246168.4537 | -573242.4161 | -216187.56 | 0 | 0 | 0 | -7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44621 | 45560 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 1 | Component Replacement
24093 | Kapuskasing TS: Component Replacement | N.T.C.1.45 | 7700 | 203 | PROJECT DELIVERY | AIP005612 |  | AIP005612 | Yes | AIP005612 |  |  |  | Northern Zone Station/Yard Investments | James.Mardegan@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24094 | Mackenzie TS: Component Replacement | N.T.C.1.45 | 7700 | 203 | PROJECT DELIVERY | AIP005613 | AIP005613 | AIP005613 | No | AIP005613 | Mackenzie TS: Component Replacement | SR-04 | Bulk Station Switchgear and Ancillary Equipment Replacement Projects | Northern Zone Station/Yard Investments | James.Mardegan@HydroOne.com | Donald.Mastrangelo@HydroOne.com | System Renewal | Northern | Not Required | 03 - None (default) | Not Required | Project | init | Short Term Planning | Short Term Planning |  | 0 | 595366.434 | 1001337.3915 | 4193139.8453 | 9657754.4584 | 7889486.0139 | 2014608.36 | 0 | 0 | 0 | 0 | 640178.9613 | 1076706.8726 | 4508752.5218 | 10384682.2133 | 8483318.2946 | 2166245.52 | 0 | 0 | 0 | 0 | -44812.5273 | -75369.4811 | -315612.6765 | -726927.7549 | -593832.2806 | -151637.16 | 0 | 0 | 0 | -7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44134 | 45550 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Component Replacement
24095 | Parry Sound TS: Component Replacement | N.T.C.1.45 | 7700 | 203 | PROJECT DELIVERY | AIP005614 | AIP005614 | AIP005614 | No | AIP005614 | Parry Sound TS: Component Replacement | SR-05 | Load Station Transformer Replacement Projects | Northern Zone Station/Yard Investments | James.Mardegan@HydroOne.com | Donald.Mastrangelo@HydroOne.com | System Renewal | Northern | Not Required | 02 - Expectation (no agreement) | Required | Project | init | Short Term Planning | Short Term Planning |  | 765141.6826 | 1233915.2825 | 7840518.5189 | 7876805.9719 | 1984233.0378 | 0 | 0 | 0 | 0 | 0 | 822732.9921 | 1326790.6263 | 8430665.0741 | 8469683.8407 | 2133583.9117 | 0 | 0 | 0 | 0 | 0 | -57591.3094 | -92875.3438 | -590146.5552 | -592877.8689 | -149350.8738 | 0 | 0 | 0 | 0 | 0 | -7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43860 | 44711 | True | Commitment to HONI Dx to replace the transformers by 2022 to avoid having to offload Parry Sound TS. | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Component Replacement
24096 | Rabbit Lake SS: Component Replacement | N.T.C.1.45 | 7700 | 203 | PROJECT DELIVERY | AIP005615 | AIP005615 | AIP005615 | No | AIP005615 | Rabbit Lake SS: Component Replacement | SR-04 | Bulk Station Switchgear and Ancillary Equipment Replacement Projects | Northern Zone Station/Yard Investments | James.Mardegan@HydroOne.com | Donald.Mastrangelo@HydroOne.com | System Renewal | Northern | Not Required | 01 - Agreement (current/future) | Not Required | Project | init | Short Term Planning | Short Term Planning |  | 333810.3284 | 993196.1395 | 2953240.02 | 6939908.7482 | 1350442.8763 | 0 | 0 | 0 | 0 | 0 | 358935.837 | 1067952.8382 | 3175526.9033 | 7462267.4712 | 2557252.3143 | 0 | 0 | 0 | 0 | 0 | -25125.5086 | -74756.6987 | -222286.8832 | -522358.723 | -101646.238 | 0 | 0 | 0 | 0 | 0 | -7 | 7 | 0 | 0 | 0 | 0 | -1105163.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43845 | 44819 | True | enora Hydro has expressed interest in a system facility upgrade. There is a possibility Kenora Hydro may request the 15M1 transferrability to K6F circuit be upgraded to a make-before-break configuration. | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Component Replacement
24097 | South March TS: Component Replacement | N.T.C.1.44 | 7700 | 203 | PROJECT DELIVERY | AIP005616 |  | AIP005616 | Yes | AIP005616 |  |  |  | Eastern Zone Station/Yard Investments | James.Mardegan@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24098 | Whitedog Falls SS: Component Replacement | N.T.C.1.45 | 7700 | 203 | PROJECT DELIVERY | AIP005617 | AIP005617 | AIP005617 | No | AIP005617 | Whitedog Falls SS: Component Replacement | SR-04 | Bulk Station Switchgear and Ancillary Equipment Replacement Projects | Northern Zone Station/Yard Investments | James.Mardegan@HydroOne.com | Donald.Mastrangelo@HydroOne.com | System Renewal | Northern | Not Required | 02 - Expectation (no agreement) | Not Required | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 305572.4541 | 836719.7918 | 1404537.055 | 4299489.5723 | 1699157.36 | 0 | 0 | 0 | 0 | 0 | 328572.5313 | 899698.7008 | 1510254.8978 | 4623107.067 | 1827050.96 | 0 | 0 | 0 | 0 | 0 | -23000.0772 | -62978.9091 | -105717.8428 | -323617.4947 | -127893.6 | 0 | 0 | 0 | -7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44488 | 45580 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Component Replacement
24099 | Port Arthur TS #1: Component Replacement | N.T.C.1.45 | 7700 | 203 | PROJECT DELIVERY | TBD |  |  | Yes |  |  |  |  | Northern Zone Station/Yard Investments | James.Mardegan@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24100 | Forest Jura HVDS-ID69-SCADA Upgrade | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24101 | CIP-014 Physical Security Implementation | N.T.C.1.29 | 7700 | 203 | PROJECT DELIVERY | AIP005635 | AIP005635 | AIP005635 | No | AIP005635 | CIP-014 Physical Security Implementation - Initial Sites | SR-16 | NERC CIP-014 Physical Security Implementation | NERC Cyber Security Compliance Readiness | lincoln.frost-hunt@hydroone.com | Sherry.Wilging@hydroone.com | System Renewal | 0 | 0 | 03 - None (default) | 0 | Project | EMPP ACCP | Executing | Executing |  | 9347117.2813 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9347117.2813 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42933 | 43448 | False |  | True | CIP-014 | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | CIP 14 Initial Stations
24102 | GIS Breaker Refurbishment | N.T.M.1.16 | 7370 | 206 | TX LINES AND STATIONS | AIP001044C | AIP001044 | AIP001044 | No | AIP001044 | Circuit Breaker Maintenance and Refurbishment | 0 |  | Power Equipment | Mike.Tanaskovic@HydroOne.com | kristoffer.hammel@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | ACTN EMPP | Executing | Short Term Planning | # of Breakers | 767751.8387 | 1770192.1842 | 1594948.2752 | 1611619.7687 | 1625150.9449 | 974401.6092 | 0 | 0 | 0 | 0 | 767751.8387 | 1770192.1842 | 1594948.2752 | 1611619.7687 | 1625150.9449 | 974401.6092 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | True | OPG Darlington has provided their overhaul schedule for their generating units, with the expectation that we will complete the refurbishment of the breakers within the timing of the unit overhaul, in order to minimize requirements for outages for performing this type of maintenance in the future. | False | False | False | True | FALSE |  | 0 | 0 | Intermediate (Modified - Tx Decision)
24103 | 48 VDC Telecom Equipment Replacement Program | N.T.C.1.25 | 7700 | 203 | PROJECT DELIVERY | AIP005627 | AIP005627 | AIP005627 | No | AIP005627 | 48 VDC Equipment Refurbishment | 0 |  | Auxiliary Telecommunication Equipment | Miroslav.Kostic@HydroOne.com | Sheraz.Majid@HydroOne.com | System Renewal | 0 | 0 | 03 - None (default) | 0 | Program | ACCP EMPP | Executing | Short Term Planning |  | 470617.3318 | 523258.1167 | 518926.686 | 512692.3923 | 506458.904 | 502110.7443 | 0 | 0 | 0 | 0 | 490226.3873 | 545060.5383 | 540548.6313 | 534054.5753 | 527561.3583 | 523032.0253 | 0 | 0 | 0 | 0 | -19609.0555 | -21802.4215 | -21621.9453 | -21362.183 | -21102.4543 | -20921.281 | 0 | 0 | 0 | 0 | -4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | True | False |  | False | False | False | False | FALSE |  | 0 | 0 | Asset Optimal
24104 | Migration of Protections in Ottawa to Fiber NTWK | N.T.C.1.25 | 7700 | 203 | PROJECT DELIVERY | AIP005624 | AIP005624 | AIP005624 | No | AIP005624 | Migration of Ottawa Protection to Existing fiber ring | 0 |  | Auxiliary Telecommunication Equipment | Miroslav.Kostic@HydroOne.com | Sheraz.Majid@HydroOne.com | System Renewal | 0 | 0 | 03 - None (default) | 0 | Project | EMPP ACCP | Executing | Executing | # of Devices | 1551339.5238 | 1426914.4102 | 0.068797 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1571772.5672 | 1445708.6223 | 0.069703 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -20433.0434 | -18794.2121 | -0.00090614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1.4527 | 1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43819 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Asset Optimal
24105 | Warkworth DS Removal | N.D.C.2.02 | 7374 | 205 | LINES | AIP005640 | AIP005640 | AIP005640 | No | AIP005640 | Warkworth DS Removal | ISD-SR-13 | Life Cycle Optimization & Operational Efficiency Projects | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Daniel.Weisser@HydroOne.com | System Renewal | Eastern | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 137578.2745 | 2806810.8851 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 156338.9483 | 3189557.824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -18760.6738 | -382746.9389 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43405 | 43771 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
24106 | Snow Valley DS F1 Extend to County Rd 90 | N.D.C.2.02 | 7374 | 205 | LINES | AIP005664 | AIP005664 | AIP005664 | No | AIP005664 | Midhurst Wilson DS F1 Feeder Extension | ISD-SS-02 | System Upgrades Driven by Load Growth | System Capability Reinforcement | lyla.garzouzi@hydroone.com | michael.sullivan@hydroone.com | System Service | 0 | Not Required | 03 - None (default) | Not Required | Project | DETL ACTN | Short Term Planning | Short Term Planning |  | 704708.9049 | 142245.6979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800805.5738 | 161642.8385 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -96096.6689 | -19397.1406 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43067 | 43462 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
24107 | NMS Capital Sustainment | N.T.C.3.06 | 4514 | 212 | INFO SOLUTIONS DIVISION | AIP005630 | AIP005630 | AIP005630 | No | AIP005630 | NMS Capital Sustainment | GP-03 | Network Management System Capital Sustainment | Grid Operating and Control Facilities | Godfrey.Holder@HydroOne.com | Daniel.Lam@HydroOne.com | General Plant | 0 | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 7768065.8843 | 22445334.3908 | 8178319.5611 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7768065.8843 | 22445334.3908 | 8178319.5611 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44025 | 45015 | False |  | True | NERC CIP vulnerability and patch management. | False |  | False | False |  | False | True | False | False | FALSE |  | 0 | 0 | Asset Optimal
24108 | Mobile Radio System Replacement | N.T.C.1.25 | 7700 | 203 | PROJECT DELIVERY | AIP000987 | AIP000987 | AIP000987 | No | AIP000987 | Mobile Radio System Replacement | SR-14 | Mobile Radio System Replacement | Auxiliary Telecommunication Equipment | Miroslav.Kostic@HydroOne.com | Sheraz.Majid@HydroOne.com | System Renewal | 0 | Not Required | 03 - None (default) | Not Required | Project | init | Short Term Planning | Short Term Planning |  | 0 | 652973.2787 | 2860644.371 | 6209215.3453 | 6121705.9705 | 4016886.3349 | 0 | 0 | 0 | 0 | 0 | 680180.4987 | 2979837.8865 | 6467932.6514 | 6376777.0526 | 4184256.5989 | 0 | 0 | 0 | 0 | 0 | -27207.2199 | -119193.5155 | -258717.3061 | -255071.0821 | -167370.264 | 0 | 0 | 0 | 0 | -4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43762 | 45231 | False |  | False |  | False |  | False | False |  | False | True | False | False | FALSE |  | 0 | 0 | Alternative 1
24109 | Lakehead TS: Component Replacement | N.T.C.1.45 | 7700 | 203 | PROJECT DELIVERY | AIP005203 | AIP005203 | AIP005203 | No | AIP005203 | Lakehead TS: Component Replacement | SR-04 | Bulk Station Switchgear and Ancillary Equipment Replacement Projects | Northern Zone Station/Yard Investments | James.Mardegan@HydroOne.com | Donald.Mastrangelo@HydroOne.com | System Renewal | Northern | Not Required | 02 - Expectation (no agreement) | Not Required | Project | ACTN BEST | Short Term Planning | Short Term Planning |  | 479704.5216 | 1880733.1418 | 8241993.7792 | 12164398.6491 | 6894825.2594 | 1283660.543 | 0 | 0 | 0 | 0 | 515811.3135 | 2022293.7009 | 8862358.9024 | 13079998.5474 | 7413790.6015 | 1380280.1538 | 0 | 0 | 0 | 0 | -36106.7919 | -141560.5591 | -620365.1232 | -915599.8983 | -518965.3421 | -96619.6108 | 0 | 0 | 0 | 0 | -7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43616 | 45061 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Component Replacement
24110 | Aylmer TS Dx new Feeder | N.D.C.2.02 | 7374 | 205 | LINES | AIP005638 | AIP005638 | AIP005638 | No | AIP005638 | Aylmer TS New Feeder | ISD-SS-03 | Reliability Improvements | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Alexander.Hamlyn@HydroOne.com | System Service | Western | Not Required | 03 - None (default) | Not Required | Project | AWRD EMPP | Executing | Executing |  | 246797.4684 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 280451.6687 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -33654.2002 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42973 | 43128 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
24111 | Woodroffe TS - Replace 15kV UG Cables/Terminations | N.T.C.2.11 | 7700 | 203 | PROJECT DELIVERY | AIP005951 | AIP005951 | AIP005951 | No | AIP005951 | Woodroffe TS - Support HOL 14kV Swtchgr Rplcmnt | 0 |  | Load Customer Connection | Robert.Reinmuller@HydroOne.com | melissa.miron@hydroone.com | System Access | 0 | 0 | 0 | 0 | Project | EMPP ACCP | Executing | Executing |  | -29890.8878 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 259918.3643 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3070.7479 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -9.3161 | 0 | -292880 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43306 | [13 empty] | FALSE |  | 0 | 0 | Woodroffe TS - Support HOL 14kV Swtchgr Rplcmnt
24112 | Rose Corner F3 (Part 1 & 2) | N.D.C.2.02 | 7374 | 205 | LINES | AIP005658 | AIP005658 | AIP005658 | No | AIP005658 | Rose Corner F3 ( Part 1 & 2) | ISD-SS-02 | System Upgrades Driven by Load Growth | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Muhammad.Sabir@HydroOne.com | System Service | Eastern | Not Required | 03 - None (default) | Not Required | Project | init | Short Term Planning | Short Term Planning |  | 934838.8822 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1062316.9116 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -127478.0294 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42763 | 43144 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
24113 | Billing - OEB Regulatory Compliance | N.D.C.2.60 | 4339 | 212 | INFO SOLUTIONS DIVISION | AIP005700 |  | AIP005700 | Yes | AIP005700 |  |  |  | IT Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24114 | Hydro One Customer App Enhancement - CAP | N.D.C.2.60 | 4339 | 212 | INFO SOLUTIONS DIVISION | AIP005703 | AIP005703 | AIP005703 | No | AIP005703 | Hydro One Customer App Enhancement - CAP |  |  | IT Business Solution Development | jj.blais@HydroOne.com | jj.blais@HydroOne.com | General Plant | 0 | 0 | 0 | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 2332060.8205 | 1402267.7821 | 0 | 1803865.6962 | 0 | 0 | 0 | 0 | 0 | 0 | 2332060.8205 | 1402267.7821 | 0 | 1803865.6962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43646 | 44926 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
24115 | Alexandria Area Study | N.D.C.2.02 | 7374 | 205 | LINES | AIP005654 | AIP005654 | AIP005654 | No | AIP005654 | Alexandria Area Study | ISD-SR-13 | Life Cycle Optimization & Operational Efficiency Projects | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Muhammad.Sabir@HydroOne.com | System Renewal | Eastern | Not Required | 03 - None (default) | Not Required | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 3851226.184 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4376393.391 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -525167.2069 | 0 | 0 | 0 | 0 | 0 | 0 | -12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44012 | 44453 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
24116 | ESA Fees | N.D.M.1.07 | 4048 | 213 | PLANNING | AIP005678 | AIP005678 | AIP005678 | No | AIP005678 | ESA Fees |  |  | Other Services | emre.aydin@HydroOne.com | Wojciech.Maroszek@HydroOne.com | System O&M | N/A | 0 | 03 - None (default) | 0 | Program | init | Short Term Planning | Short Term Planning |  | 895589.4998 | 929618.637 | 957246.1945 | 986301.9614 | 1012910.1703 | 0 | 0 | 0 | 0 | 0 | 895589.4998 | 929618.637 | 957246.1945 | 986301.9614 | 1012910.1703 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
24117 | HR Operations Process Optimization | N.C.C.2.60 | 4339 | 212 | INFO SOLUTIONS DIVISION | AIP005725 |  | AIP005725 | Yes | AIP005725 |  |  |  | IT Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24118 | HR Pay Transformation Project - Discovery | N.C.C.2.60 | 4339 | 212 | INFO SOLUTIONS DIVISION | AIP005734 | AIP005734 | AIP005734 | No | AIP005734 | Corporate Services Transformation - HR/Pay - CAP | GP-10 | Corporate Services Transformation - HR / Payroll | IT Business Solution Development | jj.blais@HydroOne.com | Jun.Macabanti@hydroone.com | General Plant | 0 | 0 | 0 | 0 | Project | init | Short Term Planning | Short Term Planning |  | 4039999.8 | 11182938.4836 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4039999.8 | 11182938.4836 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43190 | 43830 | False |  | False |  | False |  | False | False |  | False | False | True | True | TRUE | HR is considering a change in the HR Operating Model to support the company’s growth strategies. The Outsourcing Agreement with Inergi is expiring after 2019. Hydro One needs strategic leverage in any (re)negotiations in this regard. SAP is re-architecting its solution, with on-premise applications no longer supported after 2025. Meanwhile, ISD will have to be ready for a potential change in the IT Outsourcing Model. To enable and support the above objectives, ISD will have to move towards standardized SAP processes, leverage industry best practices and aim for cost effective solutions. | 0 | 0 | Asset Optimal
24119 | SuccessFactors Onboarding - Discovery | N.C.C.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION | AIP005731 | AIP005731 | AIP005731 | No | AIP005731 | Corporate Services Transformation - HR - CAP | GP-10 | Corporate Services Transformation - HR / Payroll | IT Business Solution Development | jj.blais@HydroOne.com | Jun.Macabanti@hydroone.com | General Plant | 0 | 0 | 0 | 0 | Project | init | Short Term Planning | Short Term Planning |  | 1000000 | 1105239.5843 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 1105239.5843 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43190 | 43738 | False |  | False |  | False |  | False | False |  | False | False | True | True | TRUE | HR is considering a change in the HR Operating Model to support the company’s growth strategies. The Outsourcing Agreement with Inergi is expiring after 2019. Hydro One needs strategic leverage in any (re)negotiations in this regard. SAP is re-architecting its solution, with on-premise applications no longer supported after 2025. Meanwhile, ISD will have to be ready for a potential change in the IT Outsourcing Model. To enable and support the above objectives, ISD will have to move towards standardized SAP processes, leverage industry best practices and aim for cost effective solutions. | 0 | 0 | Asset Optimal
24120 | PMR Infrastructure Refurbishment Program | N.T.C.1.25 | 7700 | 203 | PROJECT DELIVERY | AIP005632 | AIP005632 | AIP005632 | No | AIP005632 | PMR Infrastructure Refresh (Towers, Shelters) | 0 |  | Auxiliary Telecommunication Equipment | Miroslav.Kostic@HydroOne.com | Sheraz.Majid@HydroOne.com | System Renewal | 0 | 0 | 03 - None (default) | 0 | Program | EMPP ACCP | Executing | Short Term Planning |  | 572759.4077 | 570826.9932 | 566101.9251 | 559300.7493 | 552500.4237 | 456464.4237 | 0 | 0 | 0 | 0 | 596624.383 | 594611.4512 | 589689.5053 | 582604.9472 | 575521.2747 | 475483.7747 | 0 | 0 | 0 | 0 | -23864.9753 | -23784.458 | -23587.5802 | -23304.1979 | -23020.851 | -19019.351 | 0 | 0 | 0 | 0 | -4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | True | False |  | False | False | False | False | FALSE |  | 0 | 0 | Asset Optimal
24121 | ITMC Backup Move to ISOC | N.T.C.1.25 | 7700 | 203 | PROJECT DELIVERY | AIP005637 | AIP005637 | AIP005637 | No | AIP005637 | ITMC Backup Move to ISOC | 0 |  | Auxiliary Telecommunication Equipment | Miroslav.Kostic@HydroOne.com | Sheraz.Majid@HydroOne.com | System Renewal | 0 | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 297889.2773 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 297889.2773 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43556 | 43800 | True | comittment with HOT to cover HONI portion of work | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Asset Optimal
24122 | PLC System Refurbishment | N.T.C.1.25 | 7700 | 203 | PROJECT DELIVERY | AIP005633 |  | AIP005633 | Yes | AIP005633 |  |  |  | Auxiliary Telecommunication Equipment | Miroslav.Kostic@HydroOne.com | [6 empty] | Program | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24123 | Telecom Performance -Ring 8 OPGW (H27H, X3H) | N.T.C.1.25 | 7700 | 203 | PROJECT DELIVERY | AIP005634A | AIP005634 | AIP005634 | No | AIP005634 | Telecom Performance Improvements | SR-12 | Telecom Performance Improvements | Auxiliary Telecommunication Equipment | Miroslav.Kostic@HydroOne.com | Sheraz.Majid@HydroOne.com | System Renewal | 0 | 0 | 03 - None (default) | 0 | Project | ACCP EMPP | Executing | Executing |  | 2358025.298 | 3812982.4798 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2456276.3521 | 3971856.7498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -98251.0541 | -158874.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43084 | 43814 | False |  | False |  | False |  | True | False |  | False | False | False | False | FALSE |  | 0 | 0 | Asset Optimal
24124 | Telecom Performance - Ring 6 OPGW (B22D,Hannover) | N.T.C.1.25 | 7700 | 203 | PROJECT DELIVERY | AIP005634B | AIP005634 | AIP005634 | No | AIP005634 | Telecom Performance Improvements | SR-12 | Telecom Performance Improvements | Auxiliary Telecommunication Equipment | Miroslav.Kostic@HydroOne.com | Sheraz.Majid@HydroOne.com | System Renewal | 0 | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 476622.6712 | 3781419.973 | 5603984.9351 | 922641.5221 | 0 | 0 | 0 | 0 | 0 | 0 | 496481.9492 | 3938979.1385 | 5837484.3074 | 961084.9188 | 0 | 0 | 0 | 0 | 0 | 0 | -19859.278 | -157559.1655 | -233499.3723 | -38443.3968 | 0 | 0 | 0 | 0 | 0 | -4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43739 | 43814 | False |  | False |  | False |  | True | False |  | False | False | False | False | FALSE |  | 0 | 0 | Asset Optimal
24125 | Telecom Performance - Ring 6/2 (ADSS D6V/E9V) | N.T.C.1.25 | 7700 | 203 | PROJECT DELIVERY | AIP005634C | AIP005634 | AIP005634 | No | AIP005634 | Telecom Performance Improvements | SR-13 | ADSS Fibre Optic Cable Replacements | Auxiliary Telecommunication Equipment | Miroslav.Kostic@HydroOne.com | Sheraz.Majid@HydroOne.com | System Renewal | 0 | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 933997.3338 | 5535849.4777 | 3658881.9938 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 972913.8894 | 5766509.8726 | 3811335.4102 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -38916.5556 | -230660.3949 | -152453.4164 | 0 | 0 | 0 | 0 | -4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44484 | 43814 | False |  | False |  | False |  | True | False |  | False | False | False | False | FALSE |  | 0 | 0 | Asset Optimal
24126 | Telecom Performance - OPGW Repl Strategy | N.T.C.1.25 | 7700 | 203 | PROJECT DELIVERY | AIP005634 | AIP005634 | AIP005634 | No | AIP005634 | Telecom Performance Improvements | SR-12 | Telecom Performance Improvements | Auxiliary Telecommunication Equipment | Miroslav.Kostic@HydroOne.com | Sheraz.Majid@HydroOne.com | System Renewal | 0 | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 235802.4224 | 476622.6712 | 945354.9908 | 466998.8417 | 508836.0376 | 514556.9294 | 0 | 0 | 0 | 0 | 245627.5233 | 496481.9492 | 984744.7821 | 486457.1268 | 530037.5391 | 535996.8015 | 0 | 0 | 0 | 0 | -9825.1009 | -19859.278 | -39389.7913 | -19458.2851 | -21201.5016 | -21439.8721 | 0 | 0 | 0 | 0 | -4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43739 | 43814 | False |  | False |  | False |  | True | False |  | False | False | False | False | FALSE |  | 0 | 0 | Asset Optimal
24127 | Merivale TS: Component Replacement | N.T.C.1.44 | 7700 | 203 | PROJECT DELIVERY | AIP005646 | AIP005646 | AIP005646 | No | AIP005646 | Merivale TS: Component Replacement | SR-04 | Bulk Station Switchgear and Ancillary Equipment Replacement Projects | Eastern Zone Station/Yard Investments | James.Mardegan@HydroOne.com | Fred.Kouhdani@HydroOne.com | System Renewal | Eastern | Not Required | 02 - Expectation (no agreement) | Required | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 277168.0427 | 698769.4759 | 2665364.6834 | 10509586.1932 | 11398377.52 | 2849594.48 | 0 | 0 | 0 | 0 | 298030.1534 | 751365.0278 | 2865983.5305 | 11300630.3153 | 12256319.92 | 3064080.04 | 0 | 0 | 0 | 0 | -20862.1107 | -52595.5519 | -200618.8471 | -791044.1221 | -857942.4 | -214485.56 | 0 | 0 | -7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44610 | 46022 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Component Replacement
24128 | Albion TS: Component Replacement | N.T.C.1.44 | 7700 | 203 | PROJECT DELIVERY | AIP005669 | AIP005669 | AIP005669 | No | AIP005669 | Albion TS: Component Replacement | 0 |  | Eastern Zone Station/Yard Investments | James.Mardegan@HydroOne.com | Fred.Kouhdani@HydroOne.com | System Renewal | Eastern | Not Required | 02 - Expectation (no agreement) | Required | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 588685.48 | 5164965.77 | 15242783.89 | 18997893.08 | 0 | 0 | 0 | 0 | 0 | 0 | 632995.18 | 5553726.66 | 16390090.18 | 20427842.07 | 0 | 0 | 0 | 0 | 0 | 0 | -44309.7 | -388760.89 | -1147306.29 | -1429948.99 | -7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46104 | 46874 | [13 empty] | FALSE |  | 0 | 0 | Component Replacement
24129 | Billing - Peak Pricing & Rate Options | N.D.C.2.60 | 4339 | 212 | INFO SOLUTIONS DIVISION | AIP005706 |  | AIP005706 | Yes | AIP005706 |  |  |  | IT Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24130 | Threat Risk Assessments (TRAs) | N.T.M.1.29 | 838 | 212 | INFO SOLUTIONS DIVISION | AIP005680 | AIP005680 | AIP005680 | No | AIP005680 | Threat Risk Assessments (TRAs) | 0 |  | NERC Cyber Security Compliance Readiness | lincoln.frost-hunt@hydroone.com | Sherry.Wilging@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | AWRD EMPP | Executing | Short Term Planning |  | 494248.4177 | 495639.3632 | 496541.8495 | 497661.5937 | 497844.7905 | 497998.4629 | 0 | 0 | 0 | 0 | 494248.4177 | 495639.3632 | 496541.8495 | 497661.5937 | 497844.7905 | 497998.4629 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | True | CIP-014 | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Asset Optimal - Modified
24131 | King City DS - New Station & Feeders | N.D.C.2.02 | 7700 | 203 | PROJECT DELIVERY | AIP005688 | AIP005688 | AIP005688 | No | AIP005688 | King City DS - New Station & Feeders | ISD-SS-02 | System Upgrades Driven by Load Growth | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Dhaval.Patel@hydroone.com | System Service | Central | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 244233.4604 | 1956880.7061 | 2935224.2853 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 265471.1526 | 2127044.2458 | 3190461.1796 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -21237.6922 | -170163.5397 | -255236.8944 | 0 | 0 | 0 | 0 | 0 | -8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44228 | 44866 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
24132 | NERC CIP V6 CAPEX - Low Impact Facilities | N.T.C.1.29 | 7700 | 203 | PROJECT DELIVERY | AIP005684 | AIP005684 | AIP005684 | No | AIP005684 | NERC CIP V6 CAPEX - Low Impact Facilities | 0 |  | NERC Cyber Security Compliance Readiness | lincoln.frost-hunt@hydroone.com | Sherry.Wilging@hydroone.com | System Renewal | 0 | 0 | 03 - None (default) | 0 | Project | AWRD EMPP | Executing | Executing |  | 1988249.1819 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1988249.1819 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43464 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Asset Optimal
24133 | Removal of Abandoned Metering Installations | N.T.C.1.19 | 7700 | 203 | PROJECT DELIVERY | AIP005685 |  | AIP005685 | Yes | AIP005685 |  |  |  | Protection Control & Metering Equip | Miroslav.Kostic@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24134 | St. Lawrence TS: Component Replacement | N.T.C.1.44 | 7700 | 203 | PROJECT DELIVERY | AIP005676 | AIP005676 | AIP005676 | No | AIP005676 | St. Lawrence TS: Phase shifter and Regulator Replacement | SR-03 | Bulk Station Transformer Replacement Projects | Eastern Zone Station/Yard Investments | James.Mardegan@HydroOne.com | Fred.Kouhdani@HydroOne.com | System Renewal | Eastern | Not Required | 03 - None (default) | Not Required | Project | init | Short Term Planning | Short Term Planning |  | 0 | 270845.5299 | 688627.3635 | 4025876.178 | 15906523.5787 | 15679934.179 | 4251959.88 | 0 | 0 | 0 | 0 | 291231.7526 | 740459.5307 | 4328899.1161 | 17103788.7943 | 16860144.2785 | 4571999.88 | 0 | 0 | 0 | 0 | -20386.2227 | -51832.1671 | -303022.9381 | -1197265.2156 | -1180210.0995 | -320040 | 0 | 0 | 0 | -7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44245 | 45657 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Component Replacement
24135 | Billing - Non-Energy Integration | N.D.C.2.60 | 4339 | 212 | INFO SOLUTIONS DIVISION | AIP005704 | AIP005704 | AIP005704 | No | AIP005704 | Billing - Non-Energy Integration |  |  | IT Business Solution Development | jj.blais@HydroOne.com | jj.blais@HydroOne.com | General Plant | 0 | 0 | 0 | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 4469725.5144 | 1703650.9353 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4469725.5144 | 1703650.9353 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44377 | 44926 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
24136 | Collections - Pre-Paid Metering | N.D.C.2.60 | 4339 | 212 | INFO SOLUTIONS DIVISION | AIP005709 | AIP005709 | AIP005709 | No | AIP005709 | Collections - Pre-Paid Metering |  |  | IT Business Solution Development | jj.blais@HydroOne.com | jj.blais@HydroOne.com | General Plant | 0 | 0 | 0 | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 3507516.6316 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3507516.6316 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44742 | 44926 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
24137 | Collections - Dunning Redesign | N.D.C.2.60 | 4339 | 212 | INFO SOLUTIONS DIVISION | AIP005711 | AIP005711 | AIP005711 | No | AIP005711 | Collections - Dunning Redesign |  |  | IT Business Solution Development | jj.blais@HydroOne.com | jj.blais@HydroOne.com | General Plant | 0 | 0 | 0 | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 2605583.8937 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2605583.8937 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44742 | 45291 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
24138 | Contact Center - Enhance Outage App | N.D.C.2.60 | 4339 | 212 | INFO SOLUTIONS DIVISION | AIP005712 |  | AIP005712 | Yes | AIP005712 |  |  |  | IT Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24139 | Contact Center - Customer Insight & Data Analytics | N.D.C.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION | AIP005715 | AIP005715 | AIP005715 | No | AIP005715 | Contact Center - Customer Insight & Data Analytics |  |  | IT Business Solution Development | jj.blais@HydroOne.com | jj.blais@HydroOne.com | General Plant | 0 | 0 | 0 | 0 | Project | init | Short Term Planning | Short Term Planning |  | 1801455.9958 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1801455.9958 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42916 | 43465 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
24140 | C&I Customers - Alerts & Analytics | N.D.C.2.60 | 4339 | 212 | INFO SOLUTIONS DIVISION | UNPLND |  |  | Yes |  |  |  |  | IT Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24141 | C&I Customers - New Rate Design | N.D.C.2.60 | 4339 | 212 | INFO SOLUTIONS DIVISION | AIP005717 | AIP005717 | AIP005717 | No | AIP005717 | C&I Customers - New Rate Design |  |  | IT Business Solution Development | jj.blais@HydroOne.com | jj.blais@HydroOne.com | General Plant | 0 | 0 | 0 | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 2103358.7078 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2103358.7078 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43646 | 43830 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
24142 | C&I Customers - Demand to Interval | N.D.C.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION | AIP005720 | AIP005720 | AIP005720 | No | AIP005720 | C&I Customers - Demand to Interval |  |  | IT Business Solution Development | jj.blais@HydroOne.com | jj.blais@HydroOne.com | General Plant | 0 | 0 | 0 | 0 | Project | init | Short Term Planning | Short Term Planning |  | 3442782.5506 | 3481576.8013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3442782.5506 | 3481576.8013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42916 | 43830 | [13 empty] | FALSE |  | 0 | 0 | Plan B Modified
24143 | C&I Customers - Microfit Replacement | N.D.C.2.60 | 4339 | 212 | INFO SOLUTIONS DIVISION | AIP005721 |  | AIP005721 | Yes | AIP005721 |  |  |  | IT Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24144 | C&I Customers - Large Customer Calendar Month Bill | N.D.C.2.60 | 4339 | 212 | INFO SOLUTIONS DIVISION | UNPLND |  |  | Yes |  |  |  |  | IT Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24145 | SAP BPC - Planning Module | N.C.C.2.60 | 4339 | 212 | INFO SOLUTIONS DIVISION | AIP005729 |  | AIP005729 | Yes | AIP005729 |  |  |  | IT Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24146 | SAP Mobile - Pay Advice & Time Reporting | N.C.C.2.60 | 4339 | 212 | INFO SOLUTIONS DIVISION | UNPLND |  |  | Yes |  |  |  |  | IT Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24147 | S4 HANA - Finance & Logistics | N.C.C.2.60 | 4339 | 212 | INFO SOLUTIONS DIVISION | UNPLND |  |  | Yes |  |  |  |  | IT Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24148 | BPC Move to Embedded Model | N.C.C.2.60 | 4339 | 212 | INFO SOLUTIONS DIVISION | UNPLND |  |  | Yes |  |  |  |  | IT Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | #N/A | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24150 | RF Device Replacement | N.C.C.2.60 | 4339 | 212 | INFO SOLUTIONS DIVISION | AIP005746 |  | AIP005746 | Yes | AIP005746 |  |  |  | IT Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24151 | TC219 - Upstream Transmission Work for DG | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP005760 | AIP005760 | AIP005760 | No | AIP005760 | Placeholder for Upstream Tx Work for DG (Project) | SA-10 | Protection and Control Modifications for Distributed Generation | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | init | Short Term Planning | Short Term Planning |  | 0 | -0.11805 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500000 | 2999999.8819 | 3750000 | 3750000.12 | 3249999.92 | 3000000 | 0 | 0 | 0 | 0 | 0 | -4.9232e-11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2500000 | -3000000 | -3750000 | -3750000.12 | -3249999.92 | -3000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43070 | 45275 | True | Requests from mutiple DG customers (note: the Distribution Planning will manage the DG connection process but the funding for station and other transmssion related work is provided through TC219) | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Asset Optimal
24152 | Domtar Espanola: Supply additional Load | N.T.C.2.11 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Load Customer Connection | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24153 | Placeholder - IVCT Refresh | N.C.C.3.01 | 4514 | 212 | INFO SOLUTIONS DIVISION | AIP005657 | AIP005657 | AIP005657 | No | AIP005657 | IVCT Refresh | GP-04 | Integrated Voice Communications and Telephony System Refresh | Common Oper Infrast & Control Facilities | Godfrey.Holder@HydroOne.com | emily.booth@hydroone.com | General Plant | 0 | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 3899740.9256 | 6354543.5279 | 2290426.6336 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3899740.9256 | 6354543.5279 | 2290426.6336 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44286 | 45019 | False |  | True | NERC (incl. CIP), Market Rules to fulfill IESO notification obligations. | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Asset Optimal
24154 | Alliston TS: T3, T4 & Component Replacements | N.T.C.1.42 | 7700 | 203 | PROJECT DELIVERY | AIP005682 |  | AIP005682 | Yes | AIP005682 |  |  |  | Central Zone Station/Yard Investments | James.Mardegan@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24155 | Billing - Dynamic Pricing | N.D.C.2.60 | 4339 | 212 | INFO SOLUTIONS DIVISION | AIP005707 | AIP005707 | AIP005707 | No | AIP005707 | Billing - Dynamic Pricing |  |  | IT Business Solution Development | jj.blais@HydroOne.com | jj.blais@HydroOne.com | General Plant | 0 | 0 | 0 | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 3906317.3931 | 1042267.9432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3906317.3931 | 1042267.9432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44012 | 44561 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
24156 | Contact Center - Mobile Platform Strategy | N.D.C.2.60 | 4339 | 212 | INFO SOLUTIONS DIVISION | AIP005716 |  | AIP005716 | Yes | AIP005716 |  |  |  | IT Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24157 | Bill Redesign | N.D.C.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION | AIP005701 | AIP005701 | AIP005701 | No | AIP005701 | Billing - Bill Redesign |  |  | IT Business Solution Development | jj.blais@HydroOne.com | jj.blais@HydroOne.com | General Plant | 0 | 0 | 0 | 0 | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 4209019.8577 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4209019.8577 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42916 | 44926 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
24158 | Billing – Seasonal Rate Class Elimination | N.D.C.2.60 | 4339 | 212 | INFO SOLUTIONS DIVISION | UNPLND |  |  | Yes |  |  |  |  | IT Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24159 | Storage Area Network Refresh | N.C.C.3.01 | 4514 | 212 | INFO SOLUTIONS DIVISION | AIP005705 | AIP005705 | AIP005705 | No | AIP005705 | OGCC Storage Area Network | 0 |  | Common Oper Infrast & Control Facilities | Godfrey.Holder@HydroOne.com | Tarek.Othman@HydroOne.com | General Plant | 0 | Not Required | 03 - None (default) | Not Required | Project | AWRD EMPP | Executing | Executing |  | 0 | 597433.6419 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 597433.6419 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42767 | 43738 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Asset Optimal
24160 | Frontenac TS: PCT & Component Replacement | N.T.C.1.44 | 7700 | 203 | PROJECT DELIVERY | AIP005687 | AIP005687 | AIP005687 | No | AIP005687 | Frontenac TS: PCT & Component Replacement | SR-07 | Protection and Automation Replacement Projects | Eastern Zone Station/Yard Investments | James.Mardegan@HydroOne.com | Fred.Kouhdani@HydroOne.com | System Renewal | Eastern | Not Required | 02 - Expectation (no agreement) | Not Required | Project | ACTN DETL | Short Term Planning | Short Term Planning |  | 756621.0852 | 746964.3479 | 4243225.9284 | 4263740.9727 | 1073831.5299 | 0 | 0 | 0 | 0 | 0 | 813571.0593 | 803187.4708 | 4562608.5251 | 4584667.7125 | 1154657.5591 | 0 | 0 | 0 | 0 | 0 | -56949.9742 | -56223.123 | -319382.5968 | -320926.7399 | -80826.0291 | 0 | 0 | 0 | 0 | 0 | -7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43384 | 44711 | True | Upgrade P&C equipment in line with customer upgrading in thier end | False |  | False |  | False | True | yes | False | False | False | False | FALSE |  | 0 | 0 | PCT & Component Replacement
24161 | Smith Falls TS: Component Replacement | N.T.C.1.44 | 7700 | 203 | PROJECT DELIVERY | AIP005699 |  | AIP005699 | Yes | AIP005699 |  |  |  | Eastern Zone Station/Yard Investments | James.Mardegan@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24162 | Terrace Bay SS: Component Replacement | N.T.C.1.45 | 7700 | 203 | PROJECT DELIVERY | AIP005696 |  | AIP005696 | Yes | AIP005696 |  |  |  | Northern Zone Station/Yard Investments | James.Mardegan@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24163 | Marathon TS: Component Replacement | N.T.C.1.45 | 7700 | 203 | PROJECT DELIVERY | AIP005718 | AIP005718 | AIP005718 | No | AIP005718 | Marathon TS: Component Replacement | SR-04 | Bulk Station Switchgear and Ancillary Equipment Replacement Projects | Northern Zone Station/Yard Investments | James.Mardegan@HydroOne.com | Donald.Mastrangelo@HydroOne.com | System Renewal | Northern | Not Required | 03 - None (default) | Not Required | Project | ACTN BEST | Short Term Planning | Short Term Planning |  | 745544.3623 | 1719947.4043 | 5631935.0517 | 5358059.9238 | 1319937.9706 | 0 | 0 | 0 | 0 | 0 | 801660.6046 | 1849405.8111 | 6055844.1416 | 5761354.7568 | 1419288.1405 | 0 | 0 | 0 | 0 | 0 | -56116.2423 | -129458.4068 | -423909.0899 | -403294.833 | -99350.1698 | 0 | 0 | 0 | 0 | 0 | -7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43490 | 44880 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Component Replacement
24164 | Wawa TS: Component Replacement | N.T.C.1.45 | 7700 | 203 | PROJECT DELIVERY | AIP005702 | AIP005702 | AIP005702 | No | AIP005702 | Wawa TS: Component Replacement | SR-02 | Station Reinvestment Projects | Northern Zone Station/Yard Investments | James.Mardegan@HydroOne.com | Donald.Mastrangelo@HydroOne.com | System Renewal | Northern | Not Required | 03 - None (default) | Not Required | Project | BEST ACTN | Short Term Planning | Short Term Planning |  | 933847.52 | 4762931.3961 | 15598297.4335 | 14838658.2246 | 3655065.0653 | 0 | 0 | 0 | 0 | 0 | 1004137.1183 | 5121431.6088 | 16772362.8317 | 15955546.4781 | 3930177.4896 | 0 | 0 | 0 | 0 | 0 | -70289.5983 | -358500.2126 | -1174065.3982 | -1116888.2535 | -275112.4243 | 0 | 0 | 0 | 0 | 0 | -7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43419 | 44895 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Component Replacement
24165 | Fort Frances TS: Component Replacement | N.T.C.1.45 | 7700 | 203 | PROJECT DELIVERY | AIP005677 | AIP005677 | AIP005677 | No | AIP005677 | Fort Frances TS: Component Replacement | SR-07 | Protection and Automation Replacement Projects | Northern Zone Station/Yard Investments | James.Mardegan@HydroOne.com | Donald.Mastrangelo@HydroOne.com | System Renewal | Northern | Not Required | 03 - None (default) | Not Required | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 319613.614 | 910401.4331 | 3329011.3648 | 15572580.04 | 5902930.68 | 0 | 0 | 0 | 0 | 0 | 343670.5527 | 978926.2721 | 3579582.1127 | 16744709.68 | 6347237.28 | 0 | 0 | 0 | 0 | 0 | -24056.9387 | -68524.839 | -250570.7479 | -1172129.64 | -444306.6 | 0 | 0 | -7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44943 | 45991 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Component Replacement
24166 | Crawford TS: T4 & Component Replacement | N.T.C.1.40 | 7700 | 203 | PROJECT DELIVERY | AIP005727 |  | AIP005727 | Yes | AIP005727 |  |  |  | Western Zone Station/Yard Investments | James.Mardegan@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24167 | Compliance Enhancement | N.C.M.2.70 | 838 | 212 | INFO SOLUTIONS DIVISION | AIP005741 |  | AIP005741 | Yes | AIP005741 |  |  |  | IT - Project & Architecture Services | lincoln.frost-hunt@hydroone.com | [6 empty] | Program | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24168 | Segregation of networks (Dev/QA) - Placeholder | N.C.M.2.70 | 838 | 212 | INFO SOLUTIONS DIVISION | AIP005708 |  | AIP005708 | Yes | AIP005708 | IT Security Operations - SEM Monitoring and Maintenance |  |  | IT - Project & Architecture Services | lincoln.frost-hunt@hydroone.com | Sherry.Wilging@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | init | Short Term Planning | Short Term Planning | Retainer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24169 | Security Perimeter Enhancement | N.C.M.2.70 | 4339 | 212 | INFO SOLUTIONS DIVISION | AIP005708A | AIP005708 | AIP005708 | No | AIP005708 | IT Security Operations - SEM Monitoring and Maintenance | 0 |  | IT - Project & Architecture Services | lincoln.frost-hunt@hydroone.com | Sherry.Wilging@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | AWRD | Short Term Planning | Short Term Planning | Retainer | 2700000 | 1500000 | 1599999.92 | 1700000 | 1750000 | 1800000 | 0 | 0 | 0 | 0 | 2700000 | 1500000 | 1599999.92 | 1700000 | 1750000 | 1800000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | False |  | False | False | True | False | TRUE | To achieve the desired level Security Event monitoring, security incident management and situational awareness through the detection, containment, and remediation of IT threats in a 7/24/365 environment AIP001151 is no longer required after 2017 as the consolidate SEM monitoring will be funded from this driver. By consolidating estimate savings of 5M over 2019-2022 | 0 | 0 | Vulnerable
24170 | Enfield TS - capital contribution | N.D.C.2.02 | 7700 | 203 | PROJECT DELIVERY | AIP005761 | AIP005761 | AIP005761 | No | AIP005761 | Enfield TS - capital contribution | ISD-GP-27 | Enfield TS Capital Contribution | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Dhaval.Patel@hydroone.com | General Plant | Central | 0 | 03 - None (default) | Required | Project | ACCP EMPP | Executing | Executing |  | 2001617.762 | 1000884.5196 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2001617.762 | 1000884.5196 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42886 | 43616 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
24171 | Enfield TS Feeder Development | N.D.C.2.02 | 7374 | 205 | LINES | AIP005763 | AIP005763 | AIP005763 | No | AIP005763 | Enfield TS Feeder Development | ISD-SS-02 | System Upgrades Driven by Load Growth | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Dhaval.Patel@hydroone.com | System Service | Central | 0 | 0 | TBD | Project | DETL ACTN | Short Term Planning | Short Term Planning |  | 3002426.6429 | 4604068.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3002426.6429 | 4604068.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43190 | 43616 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
24172 | Cedar TS: T7, T8 & Component Replacement | N.T.C.1.40 | 7700 | 203 | PROJECT DELIVERY | AIP005724 |  | AIP005724 | Yes | AIP005724 |  |  |  | Western Zone Station/Yard Investments | James.Mardegan@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24173 | Asset Analytics Risk Factor - OMA | N.C.M.2.60 | 4339 | 212 | INFO SOLUTIONS DIVISION | AIP005681 | AIP005681 | AIP005681 | No | AIP005681 | Enterprise Analytics – AA Analytics Risk Factor Upgrades | 0 |  | IT-Business Solution Development | jj.blais@HydroOne.com | hany.eskandar@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 115300.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 115300.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43190 | 43465 | False |  | False |  | False |  | False | False |  | False | False | True | False | TRUE | This investment will remediate missing data and algorithm weights to comply with the Auditor General’s findings and recommendations: “Asset Analytics System not accurately considering all factors related to asset replacement decisions and reflecting impacts of asset condition and risk of failure” | 0 | 0 | Vulnerable - Tx Contraint Reduction
24174 | Asset Analytics Risk Factor - CAP | N.C.C.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION | AIP005623 | AIP005623 | AIP005623 | No | AIP005623 | Enterprise Analytics – AA Analytics Risk Factor Upgrades | 0 |  | IT Business Solution Development | jj.blais@HydroOne.com | hany.eskandar@hydroone.com | General Plant | 0 | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 2531628.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2531628.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43190 | 43465 | False |  | False |  | False |  | False | False |  | False | False | True | False | TRUE | This investment will remediate missing data and algorithm weights to comply with the Auditor General’s findings and recommendations: “Asset Analytics System not accurately considering all factors related to asset replacement decisions and reflecting impacts of asset condition and risk of failure” | 0 | 0 | Asset Optimal
24175 | Scarboro TS: T23 & Component Replacements | N.T.C.1.42 | 7700 | 203 | PROJECT DELIVERY | AIP005660 |  | AIP005660 | Yes | AIP005660 |  |  |  | Central Zone Station/Yard Investments | James.Mardegan@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24176 | Wilson TS: T1 & Component Replacement | N.T.C.1.42 | 7700 | 203 | PROJECT DELIVERY | AIP005667 | AIP005667 | AIP005667 | No | AIP005667 | Wilson TS: T1, PCT & Component Replacements | SR-05 | Load Station Transformer Replacement Projects | Central Zone Station/Yard Investments | James.Mardegan@HydroOne.com | michael.xavier@hydroone.com | System Renewal | Central | Not Required | 0 | TBD | Project | init | Short Term Planning | Short Term Planning |  | 584168.0119 | 726751.2649 | 3824826.7307 | 11811392.5578 | 4250142.5978 | 0 | 0 | 0 | 0 | 0 | 628137.6472 | 781452.973 | 4112716.9148 | 12700422.1052 | 4570045.8041 | 0 | 0 | 0 | 0 | 0 | -43969.6353 | -54701.7081 | -287890.184 | -889029.5474 | -319903.2063 | 0 | 0 | 0 | 0 | 0 | -7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43719 | 44859 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Component Replacements
24177 | Bathurst TS: T3, PCT & Component Replacements | N.T.C.1.43 | 7700 | 203 | PROJECT DELIVERY | AIP005714 |  | AIP005714 | Yes | AIP005714 |  |  |  | Greater Toronto Area Zone Station/Yard Investments | James.Mardegan@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24178 | Charles TS: T3, T4 & Component Replacements | N.T.C.1.43 | 7700 | 203 | PROJECT DELIVERY | AIP005653 | AIP005653 | AIP005653 | No | AIP005653 | Charles TS: T3, T4 & Component Replacements | SR-05 | Load Station Transformer Replacement Projects | Greater Toronto Area Zone Station/Yard Investments | James.Mardegan@HydroOne.com | michael.xavier@hydroone.com | System Renewal | Greater Toronto Area | Not Required | 01 - Agreement (current/future) | Not Required | Project | init | Short Term Planning | Short Term Planning |  | 0 | 838121.5436 | 1017321.1164 | 6403721.1385 | 7743700.1571 | 2162310.7663 | 0 | 0 | 0 | 0 | 0 | 901205.9609 | 1093893.6736 | 6885721.6543 | 8326559.3087 | 2325065.3401 | 0 | 0 | 0 | 0 | 0 | -63084.4173 | -76572.5571 | -482000.5158 | -582859.1516 | -162754.5738 | 0 | 0 | 0 | 0 | -7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44089 | 45102 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Component Replacements
24179 | Claireville TS: Component Replacements | N.T.C.1.43 | 7700 | 203 | PROJECT DELIVERY | AIP005754 | AIP005754 | AIP005754 | No | AIP005754 | Claireville TS: Component Replacements | SR-04 | Bulk Station Switchgear and Ancillary Equipment Replacement Projects | Greater Toronto Area Zone Station/Yard Investments | James.Mardegan@HydroOne.com | michael.xavier@hydroone.com | System Renewal | Greater Toronto Area | Not Required | 03 - None (default) | TBD | Project | ACTN BEST | Short Term Planning | Short Term Planning |  | 751073.1581 | 948176.1375 | 5953491.2308 | 7249027.4894 | 2029416.6346 | 0 | 0 | 0 | 0 | 0 | 807605.5463 | 1019544.2339 | 6401603.4739 | 7794653.2144 | 2182168.4243 | 0 | 0 | 0 | 0 | 0 | -56532.3882 | -71368.0964 | -448112.2432 | -545625.725 | -152751.7897 | 0 | 0 | 0 | 0 | 0 | -7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43774 | 44724 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Component Replacements
24180 | Duplex TS: T1, T2 & Component Replacements | N.T.C.1.43 | 7700 | 203 | PROJECT DELIVERY | AIP005656 | AIP005656 | AIP005656 | No | AIP005656 | Duplex TS: T1, T2 & Component Replacements | SR-05 | Load Station Transformer Replacement Projects | Greater Toronto Area Zone Station/Yard Investments | James.Mardegan@HydroOne.com | michael.xavier@hydroone.com | System Renewal | Greater Toronto Area | Not Required | 01 - Agreement (current/future) | Required | Project | init | Short Term Planning | Short Term Planning |  | 0 | 757989.6072 | 936462.0511 | 5339932.4783 | 6249705.5541 | 1595824.1519 | 0 | 0 | 0 | 0 | 0 | 815042.5884 | 1006948.442 | 5741862.8799 | 6941146.139 | 1941393.2683 | 0 | 0 | 0 | 0 | 0 | -57052.9812 | -70486.3909 | -401930.4016 | -470407.9449 | -120115.7964 | 0 | 0 | 0 | 0 | -7 | 7 | 0 | 0 | 0 | 0 | -221032.64 | -225453.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44172 | 45107 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | T1, T2 & Component Replacements
24181 | Kleinburg TS: Component Replacements | N.T.C.1.43 | 7700 | 203 | PROJECT DELIVERY | AIP005683 | AIP005683 | AIP005683 | No | AIP005683 | Kleinburg TS: Component Replacements | 0 |  | Greater Toronto Area Zone Station/Yard Investments | James.Mardegan@HydroOne.com | michael.xavier@hydroone.com | System Renewal | Greater Toronto Area | Not Required | 03 - None (default) | TBD | Project | DETL ACTN | Short Term Planning | Short Term Planning |  | 701237.8209 | 771771.2668 | 2405090.0274 | 872020.3555 | 0 | 0 | 0 | 0 | 0 | 0 | 754019.1623 | 829861.5772 | 2586118.309 | 937656.2962 | 0 | 0 | 0 | 0 | 0 | 0 | -52781.3414 | -58090.3104 | -181028.2816 | -65635.9407 | 0 | 0 | 0 | 0 | 0 | 0 | -7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43357 | 44479 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Component Replacements
24182 | Rexdale TS M/C Switchgear & Component Replacement | N.T.C.1.43 | 7700 | 203 | PROJECT DELIVERY | AIP005690 | AIP005690 | AIP005690 | No | AIP005690 | Rexdale TS: Metalclad Switchgear & Component Replacement | SR-06 | Load Station Switchgear and Ancillary Equipment Replacement Projects | Greater Toronto Area Zone Station/Yard Investments | James.Mardegan@HydroOne.com | michael.xavier@hydroone.com | System Renewal | Greater Toronto Area | Not Required | 03 - None (default) | TBD | Project | ACTN BEST | Short Term Planning | Short Term Planning |  | 586210.9308 | 1289960.5817 | 8830573.2475 | 7360653.7804 | 1612189.3222 | 0 | 0 | 0 | 0 | 0 | 630334.3342 | 1387054.3889 | 9495240.051 | 7914681.4843 | 1733536.9056 | 0 | 0 | 0 | 0 | 0 | -44123.4034 | -97093.8072 | -664666.8036 | -554027.7039 | -121347.5834 | 0 | 0 | 0 | 0 | 0 | -7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43543 | 44652 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Metalclad Switchgear & Component Replacement
24183 | Tomken TS: T1 & Component Replacements | N.T.C.1.43 | 7700 | 203 | PROJECT DELIVERY | AIP005674 |  | AIP005674 | Yes | AIP005674 |  |  |  | Greater Toronto Area Zone Station/Yard Investments | James.Mardegan@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24184 | Trafalgar TS: Component Replacements | N.T.C.1.43 | 7700 | 203 | PROJECT DELIVERY | AIP005752 | AIP005752 | AIP005752 | No | AIP005752 | Trafalgar TS: Component Replacements | SR-04 | Bulk Station Switchgear and Ancillary Equipment Replacement Projects | Greater Toronto Area Zone Station/Yard Investments | James.Mardegan@HydroOne.com | michael.xavier@hydroone.com | System Renewal | Greater Toronto Area | Not Required | 01 - Agreement (current/future) | TBD | Project | BEST ACTN | Short Term Planning | Short Term Planning |  | 639038.1056 | 1130093.6569 | 7745556.0393 | 4457417.3638 | 591232.3135 | 0 | 0 | 0 | 0 | 0 | 687137.748 | 1215154.4698 | 8328554.8809 | 4792921.8965 | 635733.6704 | 0 | 0 | 0 | 0 | 0 | -48099.6424 | -85060.8129 | -582998.8417 | -335504.5328 | -44501.3569 | 0 | 0 | 0 | 0 | 0 | -7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43565 | 44604 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Component Replacements
24185 | Woodbridge TS: T5 & Component Replacements | N.T.C.1.43 | 7700 | 203 | PROJECT DELIVERY | AIP005671 | AIP005671 | AIP005671 | No | AIP005671 | Woodbridge TS: T5 & Component Replacements | SR-05 | Load Station Transformer Replacement Projects | Greater Toronto Area Zone Station/Yard Investments | James.Mardegan@HydroOne.com | michael.xavier@hydroone.com | System Renewal | Greater Toronto Area | Not Required | 03 - None (default) | TBD | Project | init | Short Term Planning | Short Term Planning |  | 253911.2197 | 852623.5988 | 1635047.5114 | 5050849.1553 | 1817918.9238 | 0 | 0 | 0 | 0 | 0 | 273022.8168 | 916799.5686 | 1758115.6037 | 5431020.5971 | 1954751.531 | 0 | 0 | 0 | 0 | 0 | -19111.5972 | -64175.9698 | -123068.0923 | -380171.4418 | -136832.6072 | 0 | 0 | 0 | 0 | 0 | -7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43865 | 44862 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Component Replacements
24186 | SAP Treasury | N.C.C.2.60 | 4339 | 212 | INFO SOLUTIONS DIVISION | AIP005776 |  | AIP005776 | Yes | AIP005776 |  |  |  | IT Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24187 | Placeholder-Customer PQ Dx- Capital (Cancelled) | N.D.C.2.23 | 7700 | 203 | PROJECT DELIVERY | AIP005533 | AIP005533 | AIP005533 | No | AIP005533 | Customer Power Quality (Dx) - Capital |  |  | Customer Power Quality (Dx) | Robert.Reinmuller@HydroOne.com | andrew.yan@HydroOne.com | System Service | N/A | 0 | 03 - None (default) | Not Required | Project | init | Short Term Planning | Short Term Planning |  | 199770.0296 | 199785.1177 | 199932.015 | 200436.1618 | 200429.5218 | 0 | 0 | 0 | 0 | 0 | 199770.0296 | 199785.1177 | 199932.015 | 200436.1618 | 200429.5218 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43100 | 44927 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
24188 | DX UVM - Defect Correction | N.D.M.1.03 | 7362 | 204 | FORESTRY | AIP005662 | AIP005662 | AIP005662 | No | AIP005662 | Dx UVM – Defect Correction |  |  | Vegetation Management | emre.aydin@HydroOne.com | patrick.howe@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | EMPP AWRD | Executing | Short Term Planning | # of kms | 121337280.9286 | 120607061.2959 | 117880687.6234 | 93526784.1083 | 93401264.7269 | 0 | 0 | 0 | 0 | 0 | 121337280.9286 | 122944435.6771 | 125176302.3743 | 127734885.8421 | 128438391.0713 | 0 | 0 | 0 | 0 | 0 | 0 | -2337374.3811 | -7295614.7509 | -34208101.7339 | -35037126.3443 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34666 | 34666 | 34666 | 34666 | 34666 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Vulnerable
24189 | Closed - Tactical Maintenance | N.D.M.1.03 | 7362 | 204 | FORESTRY | AIP005663 |  | AIP005663 | Yes | AIP005663 |  |  |  | Vegetation Management | emre.aydin@HydroOne.com | [6 empty] | Program | AWRD EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24190 | Risk and Security Profiling | N.C.M.2.70 | 838 | 212 | INFO SOLUTIONS DIVISION | AIP005722A | AIP005722 | AIP005722 | No | AIP005722 | Data Security | 0 |  | IT - Project & Architecture Services | lincoln.frost-hunt@hydroone.com | Sherry.Wilging@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | init | Short Term Planning | Short Term Planning | Retainer | 99999.92 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 99999.92 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | False |  | False | False | False | False | TRUE | AIP focus on Data Loss Prevention of, External Threat and Vulnerability feeds that provide in-depth information about specific threats to help HONI protect itself from the types of attacks that could do them the most damage. | 0 | 0 | Vulnerable - Tx Contraint Reduction
24191 | Security Awareness Program | N.C.M.2.70 | 838 | 212 | INFO SOLUTIONS DIVISION | AIP005722B |  | AIP005722 | Yes | AIP005722 | Data Security |  |  | IT - Project & Architecture Services | lincoln.frost-hunt@hydroone.com | Sherry.Wilging@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | init | Short Term Planning | Short Term Planning | Retainer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24192 | Cyber Threat Intelligence Program | N.C.M.2.70 | 838 | 212 | INFO SOLUTIONS DIVISION | AIP005722C |  | AIP005722 | Yes | AIP005722 | Data Security |  |  | IT - Project & Architecture Services | lincoln.frost-hunt@hydroone.com | Sherry.Wilging@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | init | Short Term Planning | Short Term Planning | Retainer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24193 | Data Loss Prevention | N.C.M.2.70 | 4339 | 212 | INFO SOLUTIONS DIVISION | AIP005722B | AIP005722 | AIP005722 | No | AIP005722 | Data Security | 0 |  | IT - Project & Architecture Services | lincoln.frost-hunt@hydroone.com | Sherry.Wilging@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | AWRD | Short Term Planning | Short Term Planning | Retainer | 175000 | 175000 | 175000.12 | 175000 | 175000 | 175000 | 0 | 0 | 0 | 0 | 175000 | 175000 | 175000.12 | 175000 | 175000 | 175000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | False |  | False | False | False | False | TRUE | AIP focus on Data Loss Prevention of, External Threat and Vulnerability feeds that provide in-depth information about specific threats to help HONI protect itself from the types of attacks that could do them the most damage. | 0 | 0 | Vulnerable - Tx Contraint Reduction
24194 | Application Security Review | N.C.M.2.70 | 838 | 212 | INFO SOLUTIONS DIVISION | AIP005722C | AIP005722 | AIP005722 | No | AIP005722 | Data Security | 0 |  | IT - Project & Architecture Services | lincoln.frost-hunt@hydroone.com | Sherry.Wilging@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | init | Short Term Planning | Short Term Planning | Retainer | 250000.12 | 149999.88 | 0 | 0 | 250000.08 | 250000.08 | 0 | 0 | 0 | 0 | 250000.12 | 149999.88 | 0 | 0 | 250000.08 | 250000.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | False |  | False | False | False | False | TRUE | AIP focus on Data Loss Prevention of, External Threat and Vulnerability feeds that provide in-depth information about specific threats to help HONI protect itself from the types of attacks that could do them the most damage. | 0 | 0 | Vulnerable - Tx Contraint Reduction
24195 | Security Risk Management strategy | N.C.M.2.70 | 838 | 212 | INFO SOLUTIONS DIVISION | AIP005728A |  | AIP005728 | Yes | AIP005728 |  |  |  | IT - Project & Architecture Services | lincoln.frost-hunt@hydroone.com | [6 empty] | Program | AWRD EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24196 | Cyber Security Program | N.C.M.2.70 | 838 | 212 | INFO SOLUTIONS DIVISION | AIP005728B |  | AIP005728 | Yes | AIP005728 |  |  |  | IT - Project & Architecture Services | lincoln.frost-hunt@hydroone.com | [6 empty] | Program | EMPP AWRD | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24197 | Governance Framework | N.C.M.2.70 | 838 | 212 | INFO SOLUTIONS DIVISION | AIP005728C |  | AIP005728 | Yes | AIP005728 |  |  |  | IT - Project & Architecture Services | lincoln.frost-hunt@hydroone.com | [6 empty] | Program | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24198 | Enterprise identifty & Access Management | N.C.M.2.70 | 838 | 212 | INFO SOLUTIONS DIVISION | AIP005728D |  | AIP005728 | Yes | AIP005728 |  |  |  | IT - Project & Architecture Services | lincoln.frost-hunt@hydroone.com | [6 empty] | Program | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24199 | Security Event Monitoring Project - Placeholder | N.C.C.1.70 | 838 | 212 | INFO SOLUTIONS DIVISION | AIP005749 | AIP005749 | AIP005749 | No | AIP005749 | IT Security Operations Capital | 0 |  | IT - Sustainment and Operations | lincoln.frost-hunt@hydroone.com | Sherry.Wilging@hydroone.com | General Plant | 0 | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning | Retainer | 2500000 | 0 | 341936.7799 | 1447402.8471 | 476404.9283 | 0 | 0 | 0 | 0 | 0 | 2500000 | 0 | 341936.7799 | 1447402.8471 | 476404.9283 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42989 | 45254 | False |  | True | NERC v5 Compliance | False |  | False | False |  | False | False | False | False | TRUE | Security Program strategy refresh and enhance security applications | 0 | 0 | Vulnerable
24200 | Endpoint Security - Placeholder | N.C.C.1.70 | 838 | 212 | INFO SOLUTIONS DIVISION | AIP005749B |  | AIP005749 | Yes | AIP005749 | IT Security Operations Capital |  |  | IT - Sustainment and Operations | lincoln.frost-hunt@hydroone.com | Sherry.Wilging@hydroone.com | General Plant | 0 | 0 | 03 - None (default) | 0 | Program | init | Short Term Planning | Short Term Planning | Retainer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24201 | Vulnerability Assessments&Security Patching - PHol | N.C.C.1.70 | 838 | 212 | INFO SOLUTIONS DIVISION | AIP005749 |  | AIP005749 | Yes | AIP005749 | IT Security Operations Capital |  |  | IT - Sustainment and Operations | lincoln.frost-hunt@hydroone.com | Sherry.Wilging@hydroone.com | General Plant | 0 | 0 | 03 - None (default) | 0 | Program | init | Short Term Planning | Short Term Planning | Retainer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24202 | Data Loss Prevention | N.C.C.1.70 | 838 | 212 | INFO SOLUTIONS DIVISION | AIP005750B |  | AIP005750 | Yes | AIP005750 |  |  |  | IT - Sustainment and Operations | lincoln.frost-hunt@hydroone.com | [6 empty] | Program | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24203 | Customer PQTx-Cap (PQ meters stand-alone) | N.T.C.2.23 | 7700 | 203 | PROJECT DELIVERY | AIP005538 | AIP005538 | AIP005538 | No | AIP005538 | Customer PQ Tx - PQ-Meter Installations | SS-17 | Customer Power Quality Program | Customer Power Quality (Tx) | Robert.Reinmuller@HydroOne.com | andrew.yan@HydroOne.com | System Service | 0 | 0 | 03 - None (default) | 0 | Program | ACCP EMPP | Executing | Short Term Planning |  | 819006.8173 | 809476.9207 | 822715.8094 | 827786.5292 | 832010.6972 | 837414.5173 | 0 | 0 | 0 | 0 | 819006.8173 | 809476.9207 | 822715.8094 | 827786.5292 | 832010.6972 | 837414.5173 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45291 | False |  | False |  | False |  | False | False |  | False | False | False | True | TRUE | This investment aligns with company’s strategy of being customer oriented. Installation of PQ meters improves our ability to respond to our customer needs in a meaningful and efficient manner. Moreover, it provides us with customer load loss information and allows accurate tracking of PQ performance | 0 | 0 | Asset Optimal
24204 | Customer PQ Dx - OMA | N.D.M.2.23 | 4050 | 213 | PLANNING | AIP005534 | AIP005534 | AIP005534 | No | AIP005534 | Customer Power Quality (Dx) - OMA |  |  | Customer Power Quality (Dx) | Robert.Reinmuller@HydroOne.com | andrew.yan@HydroOne.com | System O&M | N/A | 0 | 03 - None (default) | 0 | Project | EMPP AWRD | Executing | Executing |  | 193759.6891 | 195725.2181 | 196083.4038 | 196898.5322 | 196634.2415 | 0 | 0 | 0 | 0 | 0 | 193759.6891 | 195725.2181 | 196083.4038 | 196898.5322 | 196634.2415 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43100 | 44927 | [13 empty] | FALSE |  | 0 | 0 | ASSET OPTIMAL
24205 | PCMIS Modernization and Optimization | N.C.C.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION | AIP005670 | AIP005670 | AIP005670 | No | AIP005670 | PCMIS Modernization and Optimization | 0 |  | IT Business Solution Development | jj.blais@HydroOne.com | Tim.Nelson@hydroone.com | General Plant | 0 | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 2500723.7843 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500723.7843 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43834 | 44194 | False |  | False |  | False |  | False | False |  | False | False | True | False | FALSE |  | 0 | 0 | PCMIS Modernization and Optimization
24206 | PCMIS Modernization and Optimization OMA | N.C.M.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION | AIP005773 | AIP005773 | AIP005773 | No | AIP005773 | PCMIS Modernization and Optimization - OMA portion | 0 |  | IT-Business Solution Development | jj.blais@HydroOne.com | Tim.Nelson@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 127960 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 127960 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43834 | 44194 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Vulnerable - Tx Contraint Reduction
24207 | Lotus Notes Modernization and Optimization | N.C.C.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION | AIP005666 |  | AIP005666 | Yes | AIP005666 |  |  |  | IT Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24208 | Lotus Notes Modernization and Optimization OMA | N.C.M.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION | AIP005766 |  | AIP005766 | Yes | AIP005766 |  |  |  | IT-Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24209 | Project Portfolio Management Tool for ISD | N.C.C.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION | AIP005672 | AIP005672 | AIP005672 | No | AIP005672 | Project Portfolio Management Tool for ISD | 0 |  | IT Business Solution Development | jj.blais@HydroOne.com | Tim.Nelson@hydroone.com | General Plant | 0 | 0 | 03 - None (default) | 0 | Project | AWRD EMPP | Executing | Executing |  | 1280000 | 1215438.0253 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1280000 | 1215438.0253 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43023 | 43826 | False |  | False |  | False |  | False | False |  | False | False | True | False | FALSE |  | 0 | 0 | Asset Optimal
24210 | Engineering Design Transformation | N.C.C.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION | AIP005762 | AIP005762 | AIP005762 | No | AIP005762 | Engineering Document Management | 0 |  | IT Business Solution Development | jj.blais@HydroOne.com | Tim.Nelson@hydroone.com | General Plant | 0 | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 2700000 | 746238.4021 | 704357.306 | 665762.2784 | 641102.0991 | 745535.1554 | 0 | 0 | 0 | 0 | 2700000 | 746238.4021 | 704357.306 | 665762.2784 | 641102.0991 | 745535.1554 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42978 | 45282 | False |  | False |  | False |  | False | False |  | False | False | True | False | FALSE |  | 0 | 0 | Asset Optimal
24211 | Engineering Design Transformation OMA | N.C.M.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION | AIP005767 | AIP005767 | AIP005767 | No | AIP005767 | Engineering Document Management - OM&A Portion | 0 |  | IT-Business Solution Development | jj.blais@HydroOne.com | Tim.Nelson@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 751000 | 47800 | 36000 | 34500 | 33700 | 39500 | 0 | 0 | 0 | 0 | 751000 | 47800 | 36000 | 34500 | 33700 | 39500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43023 | 45282 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Vulnerable - Modified
24212 | Source-to-Order Transformation Project - CAP | N.C.C.2.60 | 4339 | 212 | INFO SOLUTIONS DIVISION | AIP005744 | AIP005744 | AIP005744 | No | AIP005744 | Supply Chain - Strategic Sourcing Solution | 0 |  | IT Business Solution Development | jj.blais@HydroOne.com | Jun.Macabanti@hydroone.com | General Plant | 0 | 0 | 0 | 0 | Project | EMPP AWRD | Executing | Executing |  | 2732081 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2732081 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42916 | 43220 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Asset Optimal
24213 | Napanee TS Cap-Switcher Installation | N.T.C.2.23 | 7700 | 203 | PROJECT DELIVERY | AIP005536 |  | AIP005536 | Yes | AIP005536 |  |  |  | Customer Power Quality (Tx) | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24214 | Hanover TS: T2 & Component Replacement | N.T.C.1.40 | 7700 | 203 | PROJECT DELIVERY | AIP005740 | AIP005740 | AIP005740 | No | AIP005740 | Hanover TS: T2 & Component Replacement | SR-02 | Station Reinvestment Projects | Western Zone Station/Yard Investments | James.Mardegan@HydroOne.com | mark.truchanowicz@hydroone.com | System Renewal | Western | 0 | 03 - None (default) | Not Required | Project | init | Short Term Planning | Short Term Planning |  | 285436.9457 | 910506.3528 | 3397965.3931 | 11034779.2479 | 10423953.0871 | 2562488.0168 | 0 | 0 | 0 | 0 | 306921.447 | 979039.089 | 3653726.2292 | 11865354.03 | 11208551.7066 | 2755363.4589 | 0 | 0 | 0 | 0 | -21484.5013 | -68532.7362 | -255760.836 | -830574.7821 | -784598.6195 | -192875.4421 | 0 | 0 | 0 | 0 | -7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43830 | 45245 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Component Replacement
24215 | Lauzon TS: T6, T8 & Component Replacement | N.T.C.1.40 | 7700 | 203 | PROJECT DELIVERY | AIP005755 | AIP005755 | AIP005755 | No | AIP005755 | Lauzon TS: T6, T8 & Component Replacement | SR-05 | Load Station Transformer Replacement Projects | Western Zone Station/Yard Investments | James.Mardegan@HydroOne.com | mark.truchanowicz@hydroone.com | System Renewal | Western | 0 | 03 - None (default) | Not Required | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 314974.6923 | 985554.8465 | 4075176.32 | 13113056.6606 | 13599675.4 | 3391022.08 | 0 | 0 | 0 | 0 | 338682.4648 | 1059736.3941 | 4381910.0215 | 14100060.9254 | 14623306.84 | 3646260.28 | 0 | 0 | 0 | 0 | -23707.7725 | -74181.5476 | -306733.7015 | -987004.2648 | -1023631.44 | -255238.2 | 0 | 0 | -7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44576 | 45991 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Component Replacement
24216 | Longwood TS: Component Replacement | N.T.C.1.40 | 7700 | 203 | PROJECT DELIVERY | AIP005757 | AIP005757 | AIP005757 | No | AIP005757 | Longwood TS: Component Replacement | SR-07 | Protection and Automation Replacement Projects | Western Zone Station/Yard Investments | James.Mardegan@HydroOne.com | mark.truchanowicz@hydroone.com | System Renewal | Western | 0 | 03 - None (default) | Not Required | Project | init | Short Term Planning | Short Term Planning |  | 765141.6826 | 1560999.2923 | 6700968.3066 | 9889894.7013 | 5605650.6125 | 1043940.8604 | 0 | 0 | 0 | 0 | 822732.9921 | 1678493.8627 | 7205342.2652 | 10634295.3777 | 6027581.3038 | 1122517.0542 | 0 | 0 | 0 | 0 | -57591.3094 | -117494.5704 | -504373.9586 | -744400.6764 | -421930.6913 | -78576.1938 | 0 | 0 | 0 | 0 | -7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43769 | 45061 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Component Replacement
24217 | Talbot TS: Component Replacement | N.T.C.1.40 | 7700 | 203 | PROJECT DELIVERY | AIP005758 |  | AIP005758 | Yes | AIP005758 |  |  |  | Western Zone Station/Yard Investments | James.Mardegan@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24218 | Caledonia TS: Component Replacement | N.T.C.1.41 | 7700 | 203 | PROJECT DELIVERY | AIP005713 |  | AIP005713 | Yes | AIP005713 |  |  |  | Hamilton/Niagara Zone Station/Yard Investments | James.Mardegan@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24219 | Jarvis TS: Component Replacement | N.T.C.1.41 | 7700 | 203 | PROJECT DELIVERY | AIP005751 |  | AIP005751 | Yes | AIP005751 |  |  |  | Hamilton/Niagara Zone Station/Yard Investments | James.Mardegan@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24220 | Lake TS: T1,T2, P&C & Switchyard Refurbishment | N.T.C.1.41 | 7700 | 203 | PROJECT DELIVERY | AIP005753 | AIP005753 | AIP005753 | No | AIP005753 | Lake TS: T1,T2, P&C & Switchyard Refurbishment | SR-02 | Station Reinvestment Projects | Hamilton/Niagara Zone Station/Yard Investments | James.Mardegan@HydroOne.com | mark.truchanowicz@hydroone.com | System Renewal | Hamilton Niagara | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 314974.6923 | 985554.8465 | 4075176.32 | 13113056.6606 | 13599675.4 | 3391022.08 | 0 | 0 | 0 | 0 | 338682.4648 | 1059736.3941 | 4381910.0215 | 14100060.9254 | 14623306.84 | 3646260.28 | 0 | 0 | 0 | 0 | -23707.7725 | -74181.5476 | -306733.7015 | -987004.2648 | -1023631.44 | -255238.2 | 0 | 0 | -7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44577 | 45991 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Component Replacement
24221 | Stanley TS: T2, PCT & Component Replacement | N.T.C.1.41 | 7700 | 203 | PROJECT DELIVERY | AIP005730 | AIP005730 | AIP005730 | No | AIP005730 | Stanley TS: T2, PCT & Component Replacement | SR-05 | Load Station Transformer Replacement Projects | Hamilton/Niagara Zone Station/Yard Investments | James.Mardegan@HydroOne.com | mark.truchanowicz@hydroone.com | System Renewal | Hamilton Niagara | Not Required | 03 - None (default) | TBD | Project | DETL AWRD | Short Term Planning | Short Term Planning |  | 2356772.3804 | 8131161.7723 | 7801029.1415 | 1934854.9157 | 0 | 0 | 0 | 0 | 0 | 0 | 2534163.8498 | 8743184.7014 | 8388203.378 | 2080489.1566 | 0 | 0 | 0 | 0 | 0 | 0 | -177391.4695 | -612022.9291 | -587174.2365 | -145634.241 | 0 | 0 | 0 | 0 | 0 | 0 | -7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43395 | 44530 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Stanley TS: T2, PCT & Component Replacement
24222 | Thorold TS: T1, MV Switchyard & Component Repl. | N.T.C.1.41 | 7700 | 203 | PROJECT DELIVERY | AIP005759 | AIP005759 | AIP005759 | No | AIP005759 | Thorold TS: T1, MV Switchyard & Component Replacement | SR-05 | Load Station Transformer Replacement Projects | Hamilton/Niagara Zone Station/Yard Investments | James.Mardegan@HydroOne.com | mark.truchanowicz@hydroone.com | System Renewal | Hamilton Niagara | 0 | 03 - None (default) | TBD | Project | ACTN BEST | Short Term Planning | Short Term Planning |  | 803483.8866 | 3675101.4168 | 5641337.2899 | 3816281.9358 | 0 | 0 | 0 | 0 | 0 | 0 | 863961.1684 | 3951721.9536 | 6065954.0751 | 4103528.9632 | 0 | 0 | 0 | 0 | 0 | 0 | -60477.2818 | -276620.5368 | -424616.7853 | -287247.0274 | 0 | 0 | 0 | 0 | 0 | 0 | -7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43565 | 44407 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Component Replacement
24223 | Construction Services, Capital Project Estimating | N.C.C.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION | AIP005974 | AIP005974 | AIP005974 | No | AIP005974 | Engineering & Construction - Work Estimation | 0 |  | IT Business Solution Development | jj.blais@HydroOne.com | hany.eskandar@hydroone.com | General Plant | 0 | 0 | 0 | 0 | Project | AWRD EMPP | Executing | Executing |  | 1031624.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1031624.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42916 | 43251 | False |  | True | In Flight | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Asset Optimal
24224 | Construction Services, Capital Project Estimating | N.C.M.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION | AIP005975 | AIP005975 | AIP005975 | No | AIP005975 | Engineering & Construction - Work Estimation OMA | 0 |  | IT-Business Solution Development | jj.blais@HydroOne.com | hany.eskandar@hydroone.com | System O&M | 0 | 0 | 0 | 0 | Project | EMPP AWRD | Executing | Executing |  | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42825 | 43251 | False |  | True | In Flight | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Asset Optimal
24225 | MFA for M2M Project | N.C.C.1.75 | 4342 | 212 | INFO SOLUTIONS DIVISION | AIP000065 |  | AIP000065 | Yes | AIP000065 |  |  |  | IT - MFA | lincoln.frost-hunt@hydroone.com | [6 empty] | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24226 | Minden TS - M3 - ID30220 - Dx Minden GS | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000195 |  | AIP000195 | Yes | AIP000195 | Small Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24227 | Minden TS - M3 - ID30220 - Tx Minden GS | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | EMPP ACTN | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24228 | Beck #1 SS - G10 OPG Upgrade Work | N.T.C.2.12 | 7700 | 203 | PROJECT DELIVERY |  |  |  | No |  |  |  |  | Generator Customer Connection | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24229 | Smiths Falls TS M24 ID29880 DX Hershey Drive | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000199 |  | AIP000199 | Yes | AIP000199 | Large Embedded Generation (E/PD) |  |  | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24230 | Customer PQ Tx - OMA - Revenue meters | N.T.M.2.23 | 8706 | 214 | METER SHOP | AIP005535A | AIP005535 | AIP005535 | No | AIP005535 | Customer Power Quality (Tx) - OMA | 0 |  | Customer Power Quality (Tx) | Robert.Reinmuller@HydroOne.com | andrew.yan@HydroOne.com | System O&M | N/A | 0 | 03 - None (default) | 0 | Program | AWRD EMPP | Executing | Short Term Planning |  | 100925.5269 | 103233.7888 | 105490.1883 | 107842.639 | 110039.9484 | 112275.3869 | 0 | 0 | 0 | 0 | 100925.5269 | 103233.7888 | 105490.1883 | 107842.639 | 110039.9484 | 112275.3869 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42370 | 45291 | True | The customer revenue meter program will be communicated via our key account management (KAM). We expect 22-25 customers to enroll in this initiative each year. The aggregated annual demand for PQ audit is variable. The customers are selected based on the results of our PQ investigation | False |  | False |  | False | True | The customer revenue meter program will be communicated via our key account management (KAM). We expect 22-25 customers to enroll in this initiative each year. The aggregated annual demand for PQ audit is variable. The customers are selected based on the results of our PQ investigation | False | False | False | True | TRUE | This investment aligns with company’s strategy of being customer oriented. Integrating customer’s revenue meters as PQ meters into H1 data base improves our ability to respond to our customer needs in a meaningful and efficient manner. Performing customer PQ audit provide us with information on system PQ performance, customer’s equipment immunity to power quality related disturbances, and practical solutions to extend the customer’s equipment ride-through capability. | 0 | 0 | Asset Optimal
24231 | HV UG Cable - Polarization Cell Rplmt | N.T.C.1.15 | 7700 | 203 | PROJECT DELIVERY | AIP005695 | AIP005695 | AIP005695 | No | AIP005695 | HV UG Cable - Polarization Cell Replacement | 0 |  | U/G Lines Cable Sys & Comp Refurb & Repl | hassan.hamzeh@hydroone.com | Tyler.Wales@HydroOne.com | System Renewal | 0 | Not Required | 0 | Not Required | Project | EMPP ACCP | Executing | Executing |  | 707125.7301 | 718834.7422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 710679.1257 | 722446.9771 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3553.3956 | -3612.2349 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -0.50001 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43074 | 43799 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Alternative 1
24232 | Stations Work Management & Mobility - Capital | N.C.C.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION | AIP005689 |  | AIP005689 | Yes | AIP005689 |  |  |  | IT Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24233 | Stations Work Management & Mobility - OMA | N.C.M.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION | AIP005736 |  | AIP005736 | Yes | AIP005736 |  |  |  | IT-Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24234 | Forestry Move to Mobile - Capital | N.C.C.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION | AIP005691 | AIP005691 | AIP005691 | No | AIP005691 | Forestry Transformation Initiative - Capital | GP-08 | Forestry Work Management & Mobility | IT Business Solution Development | jj.blais@HydroOne.com | Jun.Macabanti@hydroone.com | General Plant | 0 | 0 | 0 | 0 | Project | init | Short Term Planning | Short Term Planning |  | 1070000 | 7810360.9465 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1070000 | 7810360.9465 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43100 | 43830 | False |  | False |  | False |  | False | False |  | False | False | True | False | TRUE | This will enable and support Forestry's strategic intent of aligning with industry standards and achieving versatility with any workforce. | 0 | 0 | Asset Optimal
24236 | Third-Party TCA Upgrades - Recoverable | N.T.C.1.14 | 7700 | 203 | PROJECT DELIVERY | AIP005745 | AIP005745 | AIP005745 | No | AIP005745 | Third-Party TCA Upgrades - Recoverable | 0 |  | Third Party Transmission System Modifications | john.boldt@HydroOne.com | Gian.Minichini@HydroOne.com | System Renewal | Greater Toronto Area | 0 | 01 - Agreement (current/future) | 0 | Program | init | Short Term Planning | Short Term Planning | Retainer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 985000 | 1726000 | 2000000 | 2000000 | 2000000 | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -985000 | -1726000 | -2000000 | -2000000 | -2000000 | -2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | True | Rogers and Bell require HONI to upgrade their equipment which is mounted on several transmission towers across the province. | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Third-Party TCA Upgrades - Recoverable
24238 | D4Z, Nine Mile JCT-IPB Casey JCT, Tx Line Refurb. | N.T.C.1.12 | 7700 | 203 | PROJECT DELIVERY | AIP005799 | AIP005799 | AIP005799 | No | AIP005799 | Tx Line Refurb. D4Z ¦ Nine Mile JCT-IPB Casey JCT (Close EoL) | SR-20 | Transmission Line Refurbishment - Near End of Life ACSR Conductor | Overhead Lines Component Refurb & Repl | hassan.hamzeh@hydroone.com | Deniz.Turkben@HydroOne.com | System Renewal | Northern | 0 | 03 - None (default) | 0 | Project | ACTN DETL | Short Term Planning | Short Term Planning |  | 2156986.4463 | 2608330.8824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2451120.9617 | 2964012.3664 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -294134.5154 | -355681.484 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43342 | 43808 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Proceed with complete line refurbishment
24239 | D1/2M, Minden TS X Otter Creek JCT, Tx Line Refurb | N.T.C.1.12 | 7700 | 203 | PROJECT DELIVERY | AIP005800 | AIP005800 | AIP005800 | No | AIP005800 | Tx Line Refurb. D1M/D2M/D3M/D4M ¦ Otter Creek JCT-Minden TS (Close EoL) | SR-20 | Transmission Line Refurbishment - Near End of Life ACSR Conductor | Overhead Lines Component Refurb & Repl | hassan.hamzeh@hydroone.com | Deniz.Turkben@HydroOne.com | System Renewal | Central | 0 | 03 - None (default) | 0 | Project | ACTN BEST | Short Term Planning | Short Term Planning |  | 0 | 4467849.9546 | 13572879.2626 | 18248827.8707 | 18360643.9312 | 18653883.7061 | 0 | 0 | 0 | 0 | 0 | 5077102.2212 | 15423726.4348 | 20737304.3985 | 20864368.1037 | 21197595.1205 | 0 | 0 | 0 | 0 | 0 | -609252.2665 | -1850847.1722 | -2488476.5278 | -2503724.1724 | -2543711.4145 | 0 | 0 | 0 | 0 | -12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44039 | 45283 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Proceed with complete line refurbishment
24240 | Smiths Falls TS M24 ID29880 TX Hershey Drive | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24241 | C&I Customers - First Fuel | N.D.C.2.60 | 4339 | 212 | INFO SOLUTIONS DIVISION | AIP005777 | AIP005777 | AIP005777 | No | AIP005777 | C&I Customers - First Fuel |  |  | IT Business Solution Development | jj.blais@HydroOne.com | jj.blais@HydroOne.com | General Plant | 0 | 0 | 0 | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 1768159.5013 | 1102398.6695 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1768159.5013 | 1102398.6695 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44012 | 44561 | [13 empty] | FALSE |  | 0 | 0 | Plan B Modified
24242 | Emergency Response Plans Program | N.T.M.1.05 | 1142 | 215 | FACILITIES & REAL ESTATE | AIP001007 | AIP001007 | AIP001007 | No | AIP001007 | Emergency Response Plans Program | 0 |  | Environmental Management | Mike.Tanaskovic@HydroOne.com | Sebastian.Niculae@HydroOne.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | init | Short Term Planning | Short Term Planning | # of ERP's | 336088.924 | 497621.9207 | 508867.5267 | 520215.4597 | 530815.0696 | 541167.3998 | 0 | 0 | 0 | 0 | 336088.924 | 497621.9207 | 508867.5267 | 520215.4597 | 530815.0696 | 541167.3998 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 57 | 57 | 57 | 57 | 57 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | False |  | False | False | False | False | TRUE | This program supports the Journey to Zero Initiative. Emergency Response Plans are documents containing emergency procedures including up to date contact information. SP0294 R13 - Health, Safety and Environment Emergency Preparedness and Response Procedure | 0 | 0 | Asset Optimal (Modified - Tx Decision)
24243 | Napanee TS - M5 M6 - Development | N.D.C.2.02 | 7374 | 205 | LINES | AIP000185 |  | AIP000185 | Yes | AIP000185 | (3) Reliability Improvements | ISD-SS-03 | Reliability Improvements | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Michael.Medeiros@HydroOne.com | System Service | 0 | 0 | 03 - None (default) | 0 | Project | DETL ACTN | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24244 | Northwest Bulk Transmission Line - Construction | N.T.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP005248 | AIP005248 | AIP005248 | No | AIP005248 | Northwest Bulk Transmission Line Project - Construction | SS-08 | Northwest Bulk Transmission Line | Network Transfer Capability | Robert.Reinmuller@HydroOne.com | Hamid.Hamadanizadeh@HydroOne.com | System Service | Northern | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 2944870.3088 | 6394411.638 | 5858073.8877 | 961581.8896 | 57195570.7511 | 142066182.9613 | 150000000 | 139999999.96 | 0 | 0 | 2944870.3088 | 6394411.638 | 5858073.8877 | 961581.8896 | 57195570.7511 | 142066182.9613 | 150000000 | 139999999.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44545 | 45961 | True | Requested by provincial government and IESO. | False |  | False | The project is recommended in LTEP | False | False |  | True | False | False | False | FALSE |  | 0 | 0 | Alternative 1
24245 | Forestry Move to Mobile - OMA | N.C.M.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION | AIP005737 | AIP005737 | AIP005737 | No | AIP005737 | Forestry Transformation Initiative - OMA | 0 |  | IT-Business Solution Development | jj.blais@HydroOne.com | Jun.Macabanti@hydroone.com | System O&M | 0 | 0 | 0 | 0 | Project | init | Short Term Planning | Short Term Planning |  | 197550.12 | 160100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 197550.12 | 160100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43100 | 43830 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Vulnerable - Tx Contraint Reduction
24246 | Consolidate Security Event Monitoring - Placeholde | N.C.M.2.70 | 838 | 212 | INFO SOLUTIONS DIVISION | AIP000TBD |  | AIP000TBD | Yes | AIP000TBD |  |  |  | IT - Project & Architecture Services | lincoln.frost-hunt@hydroone.com | [6 empty] | Program | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24247 | GIS Roadmap Initiatives - Capital | N.C.C.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION | AIP005692 |  | AIP005692 | Yes | AIP005692 |  |  |  | IT Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24248 | GIS Roadmap Initiatives - OM&A | N.C.M.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION | AIP005732 |  | AIP005732 | Yes | AIP005732 |  |  |  | IT-Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24249 | Environment Health & Safety System Enh - Capital | N.C.C.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION | AIP005694 |  | AIP005694 | Yes | AIP005694 |  |  |  | IT Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24250 | Environment Health & Safety System Enh - OMA | N.C.M.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION | AIP005735 |  | AIP005735 | Yes | AIP005735 |  |  |  | IT-Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24251 | Move to Mobile - Provincial Lines - OMA | N.C.M.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION | AIP005742 |  | AIP005742 | Yes | AIP005742 |  |  |  | IT-Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24252 | Enterprise Content Management - Phase C | N.C.C.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION | AIP005686 |  | AIP005686 | Yes | AIP005686 |  |  |  | IT Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24253 | Enterprise Content Management - Phase C - OMA | N.C.M.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION | AIP005771 |  | AIP005771 | Yes | AIP005771 |  |  |  | IT-Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24254 | ECM E-Signature | N.C.C.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION | AIP005747 | AIP005747 | AIP005747 | No | AIP005747 | Enterprise Content Management | 0 |  | IT Business Solution Development | jj.blais@HydroOne.com | Tim.Nelson@hydroone.com | General Plant | 0 | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 2000000 | 1973645.5928 | 1956975.2125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000 | 1973645.5928 | 1956975.2125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43189 | 44196 | False |  | True | Compliance related as this is required to meet the record retention period as mandated by the OEB, PIPEDA, NERC Reliability Standards, Ontario Business Corporations Act, Ontario Employment Standards Act and Income Tax Act. | False |  | False | False |  | False | False | True | False | FALSE |  | 0 | 0 | Enterprise Content Management
24255 | ECM E-Signature- OMA portion | N.C.M.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION | AIP005765 | AIP005765 | AIP005765 | No | AIP005765 | Enterprise Content Management - OMA portion | 0 |  | IT-Business Solution Development | jj.blais@HydroOne.com | Tim.Nelson@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 84400 | 199000 | 84750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84400 | 199000 | 84750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43189 | 44196 | False |  | True | Compliance related as this is required to meet the record retention period as mandated by the OEB, PIPEDA, NERC Reliability Standards, Ontario Business Corporations Act, Ontario Employment Standards Act and Income Tax Act. | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Vulnerable - Tx Contraint Reduction
24256 | Enterprise Content Management - Program | N.C.C.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION | AIP005748 |  | AIP005748 | Yes | AIP005748 |  |  |  | IT Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24257 | Enterprise Content Management - Program- OMA | N.C.M.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION | AIP005770 |  | AIP005770 | Yes | AIP005770 |  |  |  | IT-Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24259 | Thunder Bay-MTO-Hwy11/17 at Ouimet-Recoverable | N.T.C.1.14 | 7700 | 203 | PROJECT DELIVERY | AIP005733 | AIP005733 | AIP005733 | No | AIP005733 | Thunder Bay - MTO - Highway 11/17 Four Laning at Ouimet - Recoverable | 0 |  | Third Party Transmission System Modifications | john.boldt@HydroOne.com | Gian.Minichini@HydroOne.com | System Renewal | Northern | 0 | 01 - Agreement (current/future) | 0 | Project | ACTN DETL | Short Term Planning | Short Term Planning |  | -248.5935 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1093751.4065 | 3281000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5894e-10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1094000 | -3281000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43419 | 43814 | True | Ministry of Transportation of Ontario (MTO) asked HONI to relocate several transmission structures on circuits A7L/R1LB and A6P to accommodate their highway development. | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Thunder Bay - MTO - Highway 11/17 Four Laning at Ouimet - Recoverable
24261 | Information Rights Management - Placeholder | N.C.M.2.60 | 838 | 212 | INFO SOLUTIONS DIVISION | AIP005772 | AIP005772 | AIP005772 | No | AIP005772 | Information Rights Management | 0 |  | IT-Business Solution Development | jj.blais@HydroOne.com | Sherry.Wilging@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42993 | 43280 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Vulnerable - Tx Contraint Reduction
24262 | RD&D Project - TX Grid Mordern & Energy | N.T.M.2.21 | 4230 | 213 | PLANNING | AIP005726 |  | AIP005726 | Yes | AIP005726 | RD&D Project - Tx Grid Modernization & Energy Storage |  |  | Technology Program | Daila.Dzintars@HydroOne.com | janet.eby@Hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24263 | PLACEHOLDER: Tx Line Refurb. Future Candidate | N.T.C.1.12 | 7700 | 203 | PROJECT DELIVERY | AIP005723 | AIP005723 | AIP005723 | No | AIP005723 | Tx Line Refurb: Placeholder, Expected EoL Line Discoveries | SR-19 | Transmission Line Refurbishment - End of Life ACSR, Copper Conductors & Structures | Overhead Lines Component Refurb & Repl | hassan.hamzeh@hydroone.com | Deniz.Turkben@HydroOne.com | System Renewal | 0 | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 960994.026 | 4855450.1186 | 18737374.4983 | 30552250.6975 | 37654727.1286 | 33677600 | 0 | 0 | 0 | 0 | 1092038.6659 | 5517556.953 | 21292471.0209 | 34718466.7016 | 42789462.6462 | 38270000 | 0 | 0 | 0 | 0 | -131044.6399 | -662106.8344 | -2555096.5225 | -4166216.0042 | -5134735.5175 | -4592400 | 0 | 0 | 0 | -12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44037 | 45654 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Funding Placeholder (Modified)
24264 | Douglas Point TS: Component Replacement | N.T.C.1.40 | 7700 | 203 | PROJECT DELIVERY | AIP005813 |  | AIP005813 | Yes | AIP005813 |  |  |  | Western Zone Station/Yard Investments | James.Mardegan@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24265 | B3/B4, Horning Mt. - Glanford, Tx Line Refurb (Cu) | N.T.C.1.12 | 7700 | 203 | PROJECT DELIVERY | AIP005780 | AIP005780 | AIP005780 | No | AIP005780 | Tx Line Refurb. B3/B4 ¦ Horning Mountain JCT-Glanford JCT (Copper) | SR-19 | Transmission Line Refurbishment - End of Life ACSR, Copper Conductors & Structures | Overhead Lines Component Refurb & Repl | hassan.hamzeh@hydroone.com | Deniz.Turkben@HydroOne.com | System Renewal | Hamilton Niagara | 0 | 03 - None (default) | 0 | Project | DETL ACTN | Short Term Planning | Short Term Planning |  | 3423788.01 | 4244457.5329 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3890668.1932 | 4823247.1965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -466880.1832 | -578789.6636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43357 | 43803 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Proceed with complete line refurbishment
24266 | X2Y, Magel. Aero. CTS X IPB Bryson JCT, Tx Ln Refb | N.T.C.1.12 | 7700 | 203 | PROJECT DELIVERY | AIP005781 | AIP005781 | AIP005781 | No | AIP005781 | Tx Line Refurb. X2Y ¦ Chenaux JCT-IPB Bryson JCT-Magellan Aero S JCT (Copper) | SR-19 | Transmission Line Refurbishment - End of Life ACSR, Copper Conductors & Structures | Overhead Lines Component Refurb & Repl | hassan.hamzeh@hydroone.com | Deniz.Turkben@HydroOne.com | System Renewal | 0 | 0 | 03 - None (default) | 0 | Project | DETL ACTN | Short Term Planning | Short Term Planning |  | 1538992.7105 | 2346514.8463 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1748855.3528 | 2666494.1435 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -209862.6423 | -319979.2972 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43336 | 43588 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Proceed with full line refurbishment
24267 | Tx Line Refurb. P1P/P1T ¦ TBPI Thndr Bay-Prt Arthr | N.T.C.1.12 | 7700 | 203 | PROJECT DELIVERY | AIP005782 | AIP005782 | AIP005782 | No | AIP005782 | Tx Line Refurb. P1P/P1T ¦ TBPI Thunder Bay JCT-Port Arthur JCT (EoL) | SR-19 | Transmission Line Refurbishment - End of Life ACSR, Copper Conductors & Structures | Overhead Lines Component Refurb & Repl | hassan.hamzeh@hydroone.com | Deniz.Turkben@HydroOne.com | System Renewal | Northern | 0 | 03 - None (default) | 0 | Project | HOLD | Short Term Planning | Short Term Planning |  | 251502.5473 | 1029636.4564 | 170366.6708 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 285798.3492 | 1170041.4278 | 193598.4896 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -34295.8019 | -140404.9713 | -23231.8187 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43724 | 44181 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Proceed with complete line refurbishment
24268 | DETL- A8/9K, Str.141 X Kirkland Lake TS, Tx Ln Ref | N.T.C.1.12 | 7700 | 203 | PROJECT DELIVERY | AIP005783 | AIP005783 | AIP005783 | No | AIP005783 | Tx Line Refurb. A8K/A9K ¦ A8K Str. 141 JCT-A8K Str. 277 JCT-Ramore JCT (Copper) | SR-19 | Transmission Line Refurbishment - End of Life ACSR, Copper Conductors & Structures | Overhead Lines Component Refurb & Repl | hassan.hamzeh@hydroone.com | Deniz.Turkben@HydroOne.com | System Renewal | Northern | 0 | 03 - None (default) | 0 | Project | DETL ACTN | Short Term Planning | Short Term Planning |  | 955709.6796 | 12964838.9694 | 14523758.7269 | 9566587.609 | 0 | 0 | 0 | 0 | 0 | 0 | 1086033.7268 | 14732771.5561 | 16504271.2806 | 10871122.283 | 0 | 0 | 0 | 0 | 0 | 0 | -130324.0472 | -1767932.5867 | -1980512.5537 | -1304534.674 | 0 | 0 | 0 | 0 | 0 | 0 | -12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43406 | 44440 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Proceed with complete line refurbishment
24269 | A7L/R1LB/A6P & 57M1, Alxdr B-Lkhd, Tx Ln Refurb | N.T.C.1.12 | 7700 | 203 | PROJECT DELIVERY | AIP005784 | AIP005784 | AIP005784 | No | AIP005784 | Tx Line Refurb. A7L/R1LB & 57M1 ¦ Alexander B JCT-Lakehead TS & Nipigon JCT (Copper) | SR-19 | Transmission Line Refurbishment - End of Life ACSR, Copper Conductors & Structures | Overhead Lines Component Refurb & Repl | hassan.hamzeh@hydroone.com | Deniz.Turkben@HydroOne.com | System Renewal | Northern | 0 | 03 - None (default) | 0 | Project | DETL ACTN | Short Term Planning | Short Term Planning |  | 838341.8242 | 15701955.9607 | 20358817.1254 | 20379526.4207 | 13456945.6579 | 0 | 0 | 0 | 0 | 0 | 952661.1639 | 17843131.7736 | 23135019.4606 | 23158552.7508 | 15291983.7022 | 0 | 0 | 0 | 0 | 0 | -114319.3397 | -2141175.8128 | -2776202.3353 | -2779026.3301 | -1835038.0443 | 0 | 0 | 0 | 0 | 0 | -12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43420 | 44783 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Proceed with complete line refurbishment
24270 | K1/K2, Krklnd Lk- A. Barrick, Tx Line Refurb (Cu) | N.T.C.1.12 | 7700 | 203 | PROJECT DELIVERY | AIP005785 | AIP005785 | AIP005785 | No | AIP005785 | Tx Line Refurb. K1/K2 ¦ Kirkland Lake TS-Holloway Holt JCT (Copper) | SR-19 | Transmission Line Refurbishment - End of Life ACSR, Copper Conductors & Structures | Overhead Lines Component Refurb & Repl | hassan.hamzeh@hydroone.com | Deniz.Turkben@HydroOne.com | System Renewal | Northern | 0 | 03 - None (default) | 0 | Project | ACTN BEST | Short Term Planning | Short Term Planning |  | 2850362.2023 | 9180925.0699 | 4259166.7707 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3239047.9571 | 10432869.3977 | 4259166.7707 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -388685.7549 | -1251944.3277 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -9.1459 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43560 | 44185 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Proceed with complete line refurbishment
24272 | E1C, E.Fall X S.Fall + Etrcn X C.River, Tx Ln Rfb. | N.T.C.1.12 | 7700 | 203 | PROJECT DELIVERY | AIP005787 | AIP005787 | AIP005787 | No | AIP005787 | Tx Line Refurb. E1C ¦ Ear Falls TS-Slate Falls DS (EoL) + Etruscan JCT-Crow River DS (Near EoL) | SR-19 | Transmission Line Refurbishment - End of Life ACSR, Copper Conductors & Structures | Overhead Lines Component Refurb & Repl | hassan.hamzeh@hydroone.com | Deniz.Turkben@HydroOne.com | System Renewal | 0 | 0 | 03 - None (default) | 0 | Project | ACTN LLTM | Short Term Planning | Short Term Planning |  | 1617999.7207 | 0 | 0 | 11600329.5669 | 15075101.8395 | 14141865.1565 | 0 | 0 | 0 | 0 | 1838636.0463 | 0 | 0 | 13182192.6896 | 17130797.5449 | 16070301.3142 | 0 | 0 | 0 | 0 | -220636.3256 | 0 | 0 | -1581863.1228 | -2055695.7054 | -1928436.1577 | 0 | 0 | 0 | 0 | -12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44404 | 45265 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Proceed with complete line refurbishment (Deferred)
24273 | D1A/D3A, Gibson JCT-Thorold TS, Tx Line Refurb. | N.T.C.1.12 | 7700 | 203 | PROJECT DELIVERY | AIP005788 | AIP005788 | AIP005788 | No | AIP005788 | Tx Line Refurb. D1A/D3A ¦ Gibson JCT-Thorold TS (EoL) | SR-19 | Transmission Line Refurbishment - End of Life ACSR, Copper Conductors & Structures | Overhead Lines Component Refurb & Repl | hassan.hamzeh@hydroone.com | Deniz.Turkben@HydroOne.com | System Renewal | Hamilton Niagara | 0 | 03 - None (default) | 0 | Project | DETL ACTN LLTM | Short Term Planning | Short Term Planning |  | 941541.7028 | 1340354.9981 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1069933.7531 | 1523130.6796 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -128392.0504 | -182775.6816 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43396 | 43808 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Proceed with complete line refurbishment
24274 | H1L/H3L/H6LC/H8LC, Bloor St-Leasd, Tx Line Refurb. | N.T.C.1.12 | 7700 | 203 | PROJECT DELIVERY | AIP005789 | AIP005789 | AIP005789 | No | AIP005789 | Tx Line Refurb. H1L/H3L/H6LC/H8LC ¦ Bloor Street JCT-Leaside 34 JCT (EoL) | SR-19 | Transmission Line Refurbishment - End of Life ACSR, Copper Conductors & Structures | Overhead Lines Component Refurb & Repl | hassan.hamzeh@hydroone.com | Deniz.Turkben@HydroOne.com | System Renewal | Greater Toronto Area | 0 | 03 - None (default) | 0 | Project | HOLD BEST | Short Term Planning | Short Term Planning |  | 556365.5516 | 7327274.0285 | 8143727.5111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 632233.5814 | 8326447.7597 | 9254235.8081 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -75868.0298 | -999173.7312 | -1110508.297 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43682 | 44172 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Proceed with complete line refurbishment
24275 | D6V/D7V, Guelph North JCT-Fergus TS,Tx Line Refurb | N.T.C.1.12 | 7700 | 203 | PROJECT DELIVERY | AIP005790 | AIP005790 | AIP005790 | No | AIP005790 | Tx Line Refurb. D6V/D7V ¦ Guelph North JCT-Fergus JCT (EoL) | SR-19 | Transmission Line Refurbishment - End of Life ACSR, Copper Conductors & Structures | Overhead Lines Component Refurb & Repl | hassan.hamzeh@hydroone.com | Deniz.Turkben@HydroOne.com | System Renewal | Western | 0 | 03 - None (default) | 0 | Project | DETL ACTN | Short Term Planning | Short Term Planning |  | 1832699.0619 | 5290340.7946 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2082612.5703 | 6011750.903 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -249913.5084 | -721410.1084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43402 | 43738 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Proceed with complete line refurbishment
24276 | Q3M6, Frontenac TS-Novelis CTS, Tx Line Refurb. | N.T.C.1.12 | 7700 | 203 | PROJECT DELIVERY | AIP005791 | AIP005791 | AIP005791 | No | AIP005791 | Tx Line Refurb. Q3M6 ¦ Frontenac TS-Novelis CTS (EoL) | SR-19 | Transmission Line Refurbishment - End of Life ACSR, Copper Conductors & Structures | Overhead Lines Component Refurb & Repl | hassan.hamzeh@hydroone.com | Deniz.Turkben@HydroOne.com | System Renewal | Eastern | 0 | 03 - None (default) | 0 | Project | DETL ACTN | Short Term Planning | Short Term Planning |  | 670673.4594 | 943833.4184 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 762128.9311 | 1072537.9755 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -91455.4717 | -128704.5571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43420 | 43798 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Proceed with complete line refurbishment
24277 | D2/3H, Hunta SS and Abitibi Canyon SS, Tx Ln Refub | N.T.C.1.12 | 7700 | 203 | PROJECT DELIVERY | AIP005792 | AIP005792 | AIP005792 | No | AIP005792 | Tx Line Refurb. D2/3H & D4 & D6T, Hunta SS X Abitibi Canyon SS (EoL) | SR-19 | Transmission Line Refurbishment - End of Life ACSR, Copper Conductors & Structures | Overhead Lines Component Refurb & Repl | hassan.hamzeh@hydroone.com | Deniz.Turkben@HydroOne.com | System Renewal | Northern | 0 | 03 - None (default) | 0 | Project | ACTN DETL | Short Term Planning | Short Term Planning |  | 2095854.5605 | 19820501.7865 | 34499250.8429 | 25684940.3236 | 0 | 0 | 0 | 0 | 0 | 0 | 2381652.9097 | 22523297.4847 | 39203694.1397 | 29187432.1859 | 0 | 0 | 0 | 0 | 0 | 0 | -285798.3492 | -2702795.6982 | -4704443.2968 | -3502491.8623 | 0 | 0 | 0 | 0 | 0 | 0 | -12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43392 | 44415 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Proceed with complete line refurbishment
24278 | Tx Line Refurb. C27P ¦ Galetta-Bannockburn | N.T.C.1.12 | 7700 | 203 | PROJECT DELIVERY | AIP005793 | AIP005793 | AIP005793 | No | AIP005793 | Tx Line Refurb. C27P ¦ Galetta JCT-Bannockburn JCT (Near EoL) | SR-20 | Transmission Line Refurbishment - Near End of Life ACSR Conductor | Overhead Lines Component Refurb & Repl | hassan.hamzeh@hydroone.com | Deniz.Turkben@HydroOne.com | System Renewal | 0 | 0 | 03 - None (default) | 0 | Project | HOLD | Short Term Planning | Short Term Planning |  | 796166.4284 | 10489803.3893 | 12828440.2275 | 22597576.2852 | 21246979.887 | 0 | 0 | 0 | 0 | 0 | 904734.5778 | 11920231.1242 | 14577772.9858 | 25679063.9604 | 24144295.3261 | 0 | 0 | 0 | 0 | 0 | -108568.1493 | -1430427.7349 | -1749332.7583 | -3081487.6753 | -2897315.4391 | 0 | 0 | 0 | 0 | 0 | -12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43635 | 44900 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Proceed with complete line refurbishment
24279 | Tx Line Refurb. L22H ¦ Easton JCT-Hinchinbrk N | N.T.C.1.12 | 7700 | 203 | PROJECT DELIVERY | AIP005794 | AIP005794 | AIP005794 | No | AIP005794 | Tx Line Refurb. L22H ¦ Easton JCT-Hinchinbrk N JCT (Near EoL) | SR-20 | Transmission Line Refurbishment - Near End of Life ACSR Conductor | Overhead Lines Component Refurb & Repl | hassan.hamzeh@hydroone.com | Deniz.Turkben@HydroOne.com | System Renewal | 0 | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 831161.7635 | 3776455.8278 | 7015164.8943 | 11063958.2267 | 12217123.0305 | 0 | 0 | 0 | 0 | 0 | 944502.004 | 4291427.077 | 7971778.289 | 12572679.8031 | 13883094.3528 | 0 | 0 | 0 | 0 | 0 | -113340.2405 | -514971.2492 | -956613.3947 | -1508721.5764 | -1665971.3223 | 0 | 0 | 0 | 0 | -12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44337 | 45160 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Proceed with complete line refurbishment
24280 | Tx Line Refurb. E8V/E9V ¦ Orangeville TS-Essa JCT | N.T.C.1.12 | 7700 | 203 | PROJECT DELIVERY | AIP005795 | AIP005795 | AIP005795 | No | AIP005795 | Tx Line Refurb. E8V/E9V ¦ Orangeville TS-Essa JCT (Near EoL) | SR-20 | Transmission Line Refurbishment - Near End of Life ACSR Conductor | Overhead Lines Component Refurb & Repl | hassan.hamzeh@hydroone.com | Deniz.Turkben@HydroOne.com | System Renewal | Central | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 1809717.1731 | 16423945.0147 | 16524579.5494 | 16788495.3693 | 0 | 0 | 0 | 0 | 0 | 0 | 2056496.7876 | 18663573.8803 | 18777931.3062 | 19077835.6469 | 0 | 0 | 0 | 0 | 0 | 0 | -246779.6145 | -2239628.8656 | -2253351.7567 | -2289340.2776 | 0 | 0 | 0 | 0 | -12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44139 | 45160 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Proceed with complete line refurbishment
24281 | Q4C, IPB Ottawa River-Chats Falls, Tx Line Refurb. | N.T.C.1.12 | 7700 | 203 | PROJECT DELIVERY | AIP005796 | AIP005796 | AIP005796 | No | AIP005796 | Tx Line Refurb. Q4C ¦ IPB Ottawa River-Chats Falls SS (Close EoL) | SR-20 | Transmission Line Refurbishment - Near End of Life ACSR Conductor | Overhead Lines Component Refurb & Repl | hassan.hamzeh@hydroone.com | Deniz.Turkben@HydroOne.com | System Renewal | Eastern | 0 | 03 - None (default) | 0 | Project | ACTN DETL | Short Term Planning | Short Term Planning |  | 335336.7297 | 1029636.4564 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 381064.4655 | 1170041.4278 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -45727.7359 | -140404.9713 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43420 | 43813 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Proceed with complete line refurbishment
24282 | M6/7E, Coopers Falls JCT X Orillia TS, Tx Ln Refur | N.T.C.1.12 | 7700 | 203 | PROJECT DELIVERY | AIP005798 | AIP005798 | AIP005798 | No | AIP005798 | Tx Line Refurb. M6E/M7E ¦ Cooper's Falls JCT-Orillia TS (Near EoL) | SR-20 | Transmission Line Refurbishment - Near End of Life ACSR Conductor | Overhead Lines Component Refurb & Repl | hassan.hamzeh@hydroone.com | Deniz.Turkben@HydroOne.com | System Renewal | Central | 0 | 03 - None (default) | 0 | Project | ACTN BEST | Short Term Planning | Short Term Planning |  | 796166.4284 | 4841598.6572 | 7841771.6468 | 7796195.0669 | 0 | 0 | 0 | 0 | 0 | 0 | 904734.5778 | 5501816.6559 | 8911104.1441 | 8859312.576 | 0 | 0 | 0 | 0 | 0 | 0 | -108568.1493 | -660217.9987 | -1069332.4973 | -1063117.5091 | 0 | 0 | 0 | 0 | 0 | 0 | -12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43635 | 44399 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Proceed with complete line refurbishment
24284 | eBilling Customer Usage Analytics - OMA | N.D.M.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION | AIP005418 |  | AIP005418 | Yes | AIP005418 |  |  |  | IT Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | EMPP AWRD | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24285 | C7BM, Chats Falls SS X Fitzroy JCT, Tx Ln Refurb. | N.T.C.1.12 | 7700 | 203 | PROJECT DELIVERY | AIP005801 | AIP005801 | AIP005801 | No | AIP005801 | Tx Line Refurb. C7BM/W6CS, Chats Falls SS X Fitzroy JCT (Close EoL) | SR-20 | Transmission Line Refurbishment - Near End of Life ACSR Conductor | Overhead Lines Component Refurb & Repl | hassan.hamzeh@hydroone.com | Deniz.Turkben@HydroOne.com | System Renewal | Eastern | 0 | 03 - None (default) | 0 | Project | DETL ACTN | Short Term Planning | Short Term Planning |  | 556365.5516 | 759534.5379 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 632233.5814 | 863107.4295 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -75868.0298 | -103572.8915 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43444 | 43741 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Proceed with complete line refurbishment
24286 | A4H/A5H, Tunis JCT-Fournier JCT, Tx Line Refurb. | N.T.C.1.12 | 7700 | 203 | PROJECT DELIVERY | AIP005802 | AIP005802 | AIP005802 | No | AIP005802 | Tx Line Refurb. A4H/A5H ¦ C.P. Tunis JCT-Fournier JCT (Close EoL) | SR-20 | Transmission Line Refurbishment - Near End of Life ACSR Conductor | Overhead Lines Component Refurb & Repl | hassan.hamzeh@hydroone.com | Deniz.Turkben@HydroOne.com | System Renewal | Northern | 0 | 03 - None (default) | 0 | Project | ACTN BEST | Short Term Planning | Short Term Planning |  | 0 | 1724731.7428 | 11146172.4539 | 2755762.272 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1959922.4349 | 12666105.0613 | 3131548.0363 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -235190.6922 | -1519932.6074 | -375785.7644 | 0 | 0 | 0 | 0 | 0 | 0 | -12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43720 | 44280 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Proceed with complete line refurbishment
24287 | Tx Line Refurb. B5QK ¦Barrett Chute#2-Sharbot | N.T.C.1.12 | 7700 | 203 | PROJECT DELIVERY | AIP005803 | AIP005803 | AIP005803 | No | AIP005803 | Tx Line Refurb. B5QK ¦ Barrett Chute #2 JCT-Sharbot JCT (Near EoL) | SR-20 | Transmission Line Refurbishment - Near End of Life ACSR Conductor | Overhead Lines Component Refurb & Repl | hassan.hamzeh@hydroone.com | Deniz.Turkben@HydroOne.com | System Renewal | Eastern | 0 | 03 - None (default) | 0 | Project | HOLD | Short Term Planning | Short Term Planning |  | 796166.4284 | 7172825.0597 | 11864216.6582 | 4719755.0901 | 0 | 0 | 0 | 0 | 0 | 0 | 904734.5778 | 8150937.5678 | 13482064.3843 | 5363358.0569 | 0 | 0 | 0 | 0 | 0 | 0 | -108568.1493 | -978112.5081 | -1617847.7261 | -643602.9668 | 0 | 0 | 0 | 0 | 0 | 0 | -12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43635 | 44276 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Proceed with complete line refurbishment
24288 | A4L, Beardmore X LongLac TS, Tx Line Refurb | N.T.C.1.12 | 7700 | 203 | PROJECT DELIVERY | AIP005804 | AIP005804 | AIP005804 | No | AIP005804 | Tx Line Refurb. A4L ¦ Roxmark Mines CTS-Beardmore JCT/DS #2 (Near EoL) | SR-20 | Transmission Line Refurbishment - Near End of Life ACSR Conductor | Overhead Lines Component Refurb & Repl | hassan.hamzeh@hydroone.com | Deniz.Turkben@HydroOne.com | System Renewal | Northern | 0 | 03 - None (default) | 0 | Project | BEST ACTN | Short Term Planning | Short Term Planning |  | 1052950.5292 | 5541552.6673 | 5503454.1452 | 5471467.8268 | 0 | 0 | 0 | 0 | 0 | 0 | 1196534.6923 | 6297218.9401 | 6253925.165 | 6217577.0759 | 0 | 0 | 0 | 0 | 0 | 0 | -143584.1631 | -755666.2728 | -750471.0198 | -746109.2491 | 0 | 0 | 0 | 0 | 0 | 0 | -12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43635 | 44544 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Proceed with complete line refurbishment
24289 | S2N, Sydenham JCT-Adelaide JCT, Tx Line Refurb. | N.T.C.1.12 | 7700 | 203 | PROJECT DELIVERY | AIP005805 | AIP005805 | AIP005805 | No | AIP005805 | Tx Line Refurb. S2N ¦ Sydenham JCT-Adelaide JCT (Close EoL) | SR-20 | Transmission Line Refurbishment - Near End of Life ACSR Conductor | Overhead Lines Component Refurb & Repl | hassan.hamzeh@hydroone.com | Deniz.Turkben@HydroOne.com | System Renewal | Western | 0 | 03 - None (default) | 0 | Project | DETL ACTN | Short Term Planning | Short Term Planning |  | 1087884.6808 | 942581.6496 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1236232.5918 | 1071115.5109 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -148347.911 | -128533.8613 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43409 | 43769 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Proceed with complete line refurbishment
24291 | Tx Line Refurb. L9C/L12C ¦ Leaside TS-Balfour JCT | N.T.C.1.12 | 7700 | 203 | PROJECT DELIVERY | AIP005807 | AIP005807 | AIP005807 | No | AIP005807 | Tx Line Refurb. L9C/L12C ¦ Leaside TS-Balfour JCT (Near EoL) | SR-20 | Transmission Line Refurbishment - Near End of Life ACSR Conductor | Overhead Lines Component Refurb & Repl | hassan.hamzeh@hydroone.com | Deniz.Turkben@HydroOne.com | System Renewal | Greater Toronto Area | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 759534.5379 | 995344.4684 | 821197.2278 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 863107.4295 | 1131073.2596 | 933178.6679 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -103572.8915 | -135728.7911 | -111981.4402 | 0 | 0 | 0 | 0 | 0 | 0 | -12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44000 | 44368 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Proceed with complete line refurbishment
24292 | D7F/D9F, Twr157 JCT-Kitch MTS7, Tx Line Refurb. | N.T.C.1.12 | 7700 | 203 | PROJECT DELIVERY | AIP005808 | AIP005808 | AIP005808 | No | AIP005808 | Tx Line Refurb. D7F/D9F ¦ Tower 157 JCT-Kitchener MTS#7-Freeport SS (Close EoL) | SR-20 | Transmission Line Refurbishment - Near End of Life ACSR Conductor | Overhead Lines Component Refurb & Repl | hassan.hamzeh@hydroone.com | Deniz.Turkben@HydroOne.com | System Renewal | Western | 0 | 03 - None (default) | 0 | Project | ACTN DETL | Short Term Planning | Short Term Planning |  | 770352.3023 | 357428.0385 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 875400.3435 | 406168.2256 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -105048.0412 | -48740.1871 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43420 | 43549 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Proceed with complete line refurbishment
24294 | D6, Des Joachims TS X Petawawa DS, Tx Line Refur | N.T.C.1.12 | 7700 | 203 | PROJECT DELIVERY | AIP005810 | AIP005810 | AIP005810 | No | AIP005810 | Tx Line Refurb. D6 ¦ Des Joachims JCT X Tee Lake JCT + Chalk River JCT X Petawawa JCT (Close EoL) | SR-19 | Transmission Line Refurbishment - End of Life ACSR, Copper Conductors & Structures | Overhead Lines Component Refurb & Repl | hassan.hamzeh@hydroone.com | Deniz.Turkben@HydroOne.com | System Renewal | Eastern | 0 | 03 - None (default) | 0 | Project | DETL ACTN | Short Term Planning | Short Term Planning |  | 556365.5516 | 1072283.9985 | 6424496.1038 | 2737324.1691 | 0 | 0 | 0 | 0 | 0 | 0 | 632233.5814 | 1218504.5437 | 7300563.7543 | 3110595.6467 | 0 | 0 | 0 | 0 | 0 | 0 | -75868.0298 | -146220.5452 | -876067.6505 | -373271.4776 | 0 | 0 | 0 | 0 | 0 | 0 | -12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43668 | 44263 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Proceed with complete line refurbishment
24295 | Tx Line Refurb. T2R/T61S¦Wawaitin JCT-Shiningtree | N.T.C.1.12 | 7700 | 203 | PROJECT DELIVERY | AIP005811 | AIP005811 | AIP005811 | No | AIP005811 | Tx Line Refurb. T2R/T61S ¦ Timmins JCT-Wawaitin JCT-Shiningtree JCT (Close EoL) | SR-20 | Transmission Line Refurbishment - Near End of Life ACSR Conductor | Overhead Lines Component Refurb & Repl | hassan.hamzeh@hydroone.com | Deniz.Turkben@HydroOne.com | System Renewal | Northern | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 1003685.5134 | 11108189.6571 | 20519272.1556 | 22260357.04 | 0 | 0 | 0 | 0 | 0 | 0 | 1140551.7197 | 12622942.7922 | 23317354.7223 | 25295860.24 | 0 | 0 | 0 | 0 | 0 | 0 | -136866.2064 | -1514753.1351 | -2798082.5667 | -3035503.2 | 0 | 0 | 0 | -12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44628 | 45641 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Proceed with complete line refurbishment
24296 | Tx Line Refurb. B7/B8 ¦Burlington TS-Bronte TS | N.T.C.1.12 | 7700 | 203 | PROJECT DELIVERY | AIP005812 | AIP005812 | AIP005812 | No | AIP005812 | Tx Line Refurb. B7/B8 ¦Burlington TS-Bronte TS (Near EoL) | SR-20 | Transmission Line Refurbishment - Near End of Life ACSR Conductor | Overhead Lines Component Refurb & Repl | hassan.hamzeh@hydroone.com | Deniz.Turkben@HydroOne.com | System Renewal | Hamilton Niagara | 0 | 03 - None (default) | 0 | Project | ACTN DETL | Short Term Planning | Short Term Planning |  | 770352.3023 | 2680709.9962 | 3619434.4623 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 875400.3435 | 3046261.3593 | 4112993.7071 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -105048.0412 | -365551.3631 | -493559.2449 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43696 | 44175 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Proceed with complete line refurbishment
24297 | Kapuskasing area reinforcement - Kapuskasing TS | N.T.C.2.02 | 7700 | 203 | PROJECT DELIVERY | AIP005998 | AIP005998 | AIP005998 | No | AIP005998 | Kapuskasing area reinforcement - Kapuskasing TS | SS-10 | Kapuskasing Area Transmission Reinforcement | Local Area Supply | Robert.Reinmuller@HydroOne.com | Kirpal.Bahra@HydroOne.com | System Service | 0 | 0 | 0 | 0 | Project | DETL ACTN | Short Term Planning | Short Term Planning |  | 490811.7181 | 4918778.1831 | 6834419.5357 | 3846327.5584 | 0 | 0 | 0 | 0 | 0 | 0 | 490811.7181 | 4918778.1831 | 6834419.5357 | 3846327.5584 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43481 | 44165 | True | IESO letter | True | IESO ORTAC Compliance | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Alternative 1
24298 | Project Portfolio Management Tool for ISD - OMA | N.C.M.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION | AIP005774 | AIP005774 | AIP005774 | No | AIP005774 | Project Portfolio Management Tool for ISD - OMA portion | 0 |  | IT-Business Solution Development | jj.blais@HydroOne.com | Tim.Nelson@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Project | AWRD EMPP | Executing | Executing |  | 161000.04 | 135600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 161000.04 | 135600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42949 | 44038 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Vulnerable - Modified
24299 | Thorold Allanport DS removal via voltage conversio | N.D.C.2.02 | 7374 | 205 | LINES | UNPLND |  |  | Yes |  |  |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24300 | Preston TS: T3, T4 & Component Replacement | N.T.C.1.40 | 7700 | 203 | PROJECT DELIVERY | AIP005814 | AIP005814 | AIP005814 | No | AIP005814 | Preston TS: T3, T4 & Component Replacement | SR-07 | Protection and Automation Replacement Projects | Western Zone Station/Yard Investments | James.Mardegan@HydroOne.com | mark.truchanowicz@hydroone.com | System Renewal | Western | Not Required | 0 | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 1025625.7965 | 742164.7656 | 4920054.4497 | 2552478.68 | 191965.16 | 0 | 0 | 0 | 0 | 0 | 1102823.4371 | 798026.6297 | 5290381.1287 | 2744600.84 | 206414.24 | 0 | 0 | 0 | 0 | 0 | -77197.6406 | -55861.8641 | -370326.679 | -192122.16 | -14449.08 | 0 | 0 | -7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44734 | 45671 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Component Replacement
24301 | Modernization of Worst Performing Feeders | N.D.C.2.02 | 4343 | 222 | SMART GRID | AIP005826 | AIP005826 | AIP005826 | No | AIP005826 | Modernization of Worst Performing Feeders | ISD-SS-06 | Worst Performing Feeders | System Capability Reinforcement | lyla.garzouzi@hydroone.com | sinisa.grkovic@HydroOne.com | System Service | 0 | 0 | 03 - None (default) | 0 | Program | init | Short Term Planning | Short Term Planning | # of Normal Open Points | 7064853.0065 | 10129386.2024 | 10519856.1316 | 10916653.1917 | 11315006.1338 | 0 | 0 | 0 | 0 | 0 | 7064853.0065 | 10129386.2024 | 10519856.1316 | 10916653.1917 | 11315006.1338 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 33 | 35 | 36 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Critical Spend Plan
24302 | Norfolk TS: Component Replacement | N.T.C.1.41 | 7700 | 203 | PROJECT DELIVERY | AIP005815 | AIP005815 | AIP005815 | No | AIP005815 | Norfolk TS: Component Replacement | SR-06 | Load Station Switchgear and Ancillary Equipment Replacement Projects | Hamilton/Niagara Zone Station/Yard Investments | James.Mardegan@HydroOne.com | mark.truchanowicz@hydroone.com | System Renewal | Hamilton Niagara | Not Required | 0 | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 265537.4589 | 715006.9762 | 885532.1164 | 5782865.3943 | 2460779.88 | 0 | 0 | 0 | 0 | 0 | 285524.1494 | 768824.7056 | 952185.0714 | 6218134.8326 | 2646000 | 0 | 0 | 0 | 0 | 0 | -19986.6905 | -53817.7294 | -66652.955 | -435269.4383 | -185220.12 | 0 | 0 | 0 | -7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44689 | 45626 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Component Replacement
24303 | Burlington TS: MV Switchyard and Component Repl. | N.T.C.1.41 | 7700 | 203 | PROJECT DELIVERY | AIP005816 | AIP005816 | AIP005816 | No | AIP005816 | Burlington TS: MV Switchyaard and Component Replacement | 0 |  | Hamilton/Niagara Zone Station/Yard Investments | James.Mardegan@HydroOne.com | mark.truchanowicz@hydroone.com | System Renewal | Hamilton Niagara | Not Required | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 264165.111 | 811382.1881 | 1596842.7311 | 7468165.92 | 2830396.32 | 0 | 0 | 0 | 0 | 0 | 284048.5064 | 872453.9656 | 1717035.1947 | 8030285.88 | 3043436.88 | 0 | 0 | 0 | 0 | 0 | -19883.3955 | -61071.7776 | -120192.4636 | -562119.96 | -213040.56 | 0 | 0 | -7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45043 | 45976 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | MV Switchyard and Component Replacement
24304 | FCI Deployment Program | N.D.C.2.02 | 7374 | 205 | LINES | AIP005825 | AIP005825 | AIP005825 | No | AIP005825 | Fault Current Indicators Deployment Program |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | sinisa.grkovic@HydroOne.com | System Service | 0 | 0 | 03 - None (default) | 0 | Program | EMPP AWRD | Executing | Short Term Planning | # of Fault Indicators | 666004.4029 | 679375.8302 | 693472.4208 | 707737.9014 | 721868.9299 | 0 | 0 | 0 | 0 | 0 | 666004.4029 | 679375.8302 | 693472.4208 | 707737.9014 | 721868.9299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 205 | 205 | 205 | 205 | 205 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Demand
24305 | Meadowvale TS: Component Replacement | N.T.C.1.43 | 7700 | 203 | PROJECT DELIVERY | AIP005779 | AIP005779 | AIP005779 | No | AIP005779 | Meadowvale TS: Component Replacement | 0 |  | Greater Toronto Area Zone Station/Yard Investments | James.Mardegan@HydroOne.com | michael.xavier@hydroone.com | System Renewal | Central | 0 | 0 | 0 | Project | ACTN BEST | Short Term Planning | Short Term Planning |  | 0 | 659305.3492 | 219668.4034 | 1074714.2262 | 614656.2169 | 81663.1041 | 0 | 0 | 0 | 0 | 0 | 679696.2363 | 226462.2715 | 1107952.8105 | 633666.203 | 84188.7671 | 0 | 0 | 0 | 0 | 0 | -20390.8871 | -6793.8681 | -33238.5843 | -19009.9861 | -2525.663 | 0 | 0 | 0 | 0 | -3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43889 | 44982 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Alternative 1
24306 | Morrisburg TS; Component Replacement | N.T.C.1.44 | 7700 | 203 | PROJECT DELIVERY | AIP005821 |  | AIP005821 | Yes | AIP005821 |  |  |  | Eastern Zone Station/Yard Investments | James.Mardegan@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24307 | Carling TS; Component Replacement | N.T.C.1.44 | 7700 | 203 | PROJECT DELIVERY | AIP005822 |  | AIP005822 | Yes | AIP005822 |  |  |  | Eastern Zone Station/Yard Investments | James.Mardegan@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24308 | Otonabee TS; Component Replacement | N.T.C.1.44 | 7700 | 203 | PROJECT DELIVERY | AIP005823 |  | AIP005823 | Yes | AIP005823 |  |  |  | Eastern Zone Station/Yard Investments | James.Mardegan@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24309 | Moose Lake TS: Component Replacement | N.T.C.1.45 | 7700 | 203 | PROJECT DELIVERY | AIP005824 | AIP005824 | AIP005824 | No | AIP005824 | Moose Lake TS: Component Replacement | SR-05 | Load Station Transformer Replacement Projects | Northern Zone Station/Yard Investments | James.Mardegan@HydroOne.com | Donald.Mastrangelo@HydroOne.com | System Renewal | Northern | Not Required | 03 - None (default) | Required | Project | ACTN BEST | Short Term Planning | Short Term Planning |  | 0 | 0 | 1074674.7577 | 3373593.1717 | 9161696.2083 | 7975514.5732 | 2101223.64 | 0 | 0 | 0 | 0 | 0 | 1155564.2555 | 3627519.5395 | 9851286.2455 | 8575822.1217 | 2259380.28 | 0 | 0 | 0 | 0 | 0 | -80889.4979 | -253926.3678 | -689590.0372 | -600307.5485 | -158156.64 | 0 | 0 | 0 | -7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44149 | 45594 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Alternative 1
24310 | Bilberry Creek TS; Component Replacement | N.T.C.1.44 | 7700 | 203 | PROJECT DELIVERY | AIP005820 |  | AIP005820 | Yes | AIP005820 |  |  |  | Eastern Zone Station/Yard Investments | James.Mardegan@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24311 | Havelock TS; Component Replacement | N.T.C.1.44 | 7700 | 203 | PROJECT DELIVERY | AIP005819 | AIP005819 | AIP005819 | No | AIP005819 | Havelock TS T1 T2 Component Replacement | 0 |  | Eastern Zone Station/Yard Investments | James.Mardegan@HydroOne.com | Fred.Kouhdani@HydroOne.com | System Renewal | Eastern | Not Required | 0 | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 282368.72 | 818033.52 | 1936907.32 | 12839993.12 | 0 | 0 | 0 | 0 | 0 | 0 | 303622.16 | 879606 | 2082696.04 | 13806444.32 | 0 | 0 | 0 | 0 | 0 | 0 | -21253.44 | -61572.48 | -145788.72 | -966451.2 | -7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46033 | 47117 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Alternative 1
24312 | Hunta SS; Component Replacement | N.T.C.1.45 | 7700 | 203 | PROJECT DELIVERY | AIP005818 | AIP005818 | AIP005818 | No | AIP005818 | Hunta SS: Component Replacement | SR-07 | Protection and Automation Replacement Projects | Northern Zone Station/Yard Investments | James.Mardegan@HydroOne.com | Donald.Mastrangelo@HydroOne.com | System Renewal | Northern | Not Required | 03 - None (default) | Not Required | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 95407.1592 | 1922706.5025 | 2996496.8628 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 102588.3432 | 2067426.3468 | 3222039.6375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -7181.184 | -144719.8443 | -225542.7746 | 0 | 0 | 0 | 0 | -7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44714 | 45229 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Component Replacement
24313 | Spruce Falls TS; Component Replacement | N.T.C.1.45 | 7700 | 203 | PROJECT DELIVERY | AIP005817 |  | AIP005817 | Yes | AIP005817 |  |  |  | Northern Zone Station/Yard Investments | James.Mardegan@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24314 | Kapuskasing area reinforcement - H9K Upgrade | N.T.C.2.02 | 7700 | 203 | PROJECT DELIVERY | AIP005948 | AIP005948 | AIP005948 | No | AIP005948 | Kapuskasing area reinforcement - H9K Upgrade | SS-10 | Kapuskasing Area Transmission Reinforcement | Local Area Supply | Robert.Reinmuller@HydroOne.com | Kirpal.Bahra@HydroOne.com | System Service | 0 | 0 | 0 | 0 | Project | ACTN LLTM | Short Term Planning | Short Term Planning |  | 981623.4363 | 10329434.1845 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 981623.4363 | 10329434.1845 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43372 | 43738 | True | IESO Directive to upgrade Line | True | IESO ORTAC compliance | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Kapuskasing area reinforcement - H9K Upgrade
24315 | Thorold Turner DS removal via votlage conversion | N.D.C.2.02 | 7374 | 205 | LINES | UNPLND |  |  | Yes |  |  |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24316 | Kent TS-M15-ID274-Dx-PV mitigation | N.D.M.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP005958 | AIP005958 | AIP005958 | No | AIP005958 | Kent TS-M15-ID274-Dx-PV mitigation |  |  | Distributed Generation Connections | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System O&M | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42794 | [13 empty] | FALSE |  | 0 | 0 | Enter Descriptive Name for Project Alternative
24317 | Ramore TS - Install second transformer | N.T.C.2.11 | 7700 | 203 | PROJECT DELIVERY | AIP006022 | AIP006022 | AIP006022 | No | AIP006022 | Ramore TS - Install second transformer | SA-01 | Ramore TS: Install Second Transformer | Load Customer Connection | Robert.Reinmuller@HydroOne.com | Qasim.raza@hydroone.com | System Access | 0 | 0 | 03 - None (default) | 0 | Project | IESO init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 6000000 | 3500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1000000 | -6000000 | -3500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43447 | 44050 | True | Requested by Hydro One Distribution to supply load. | True | Transmission license requirement to supply customer load. | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Alternative 1
24320 | PCAD v6.5 Upgrade | N.C.C.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION | UNPLND |  |  | Yes |  |  |  |  | IT Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | EMPP AWRD | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24321 | Wendover HVDS F3 ID30400 DX Ferme Rene Franche & F | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000199 |  | AIP000199 | Yes | AIP000199 | Large Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24322 | IAMGOLD - 115 kV Mine Connection | N.T.C.2.11 | 7700 | 203 | PROJECT DELIVERY | AIP006008 | AIP006008 | AIP006008 | No | AIP006008 | IAMGOLD - 115 kV Connection | SA-06 | Connect New IAMGOLD Mine | Load Customer Connection | Robert.Reinmuller@HydroOne.com | Kirpal.Bahra@HydroOne.com | System Access | 0 | 0 | 0 | 0 | Project | ACTN BEST | Short Term Planning | Short Term Planning |  | 128165.2517 | 513774.5759 | 2549531.3905 | 2510978.7883 | 0 | 0 | 0 | 0 | 0 | 0 | 497600.6717 | 1991516.2459 | 9938231.3905 | 9899678.7883 | 0 | 0 | 0 | 0 | 0 | 0 | 5.5511e-11 | 0 | -4.4409e-10 | -8.8818e-10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -369435.42 | -1477741.67 | -7388700 | -7388700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43769 | 44377 | True | Customer requested work. | True | Transmission license requirement to connect customers | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Alternative 1
24323 | Ramore TS Upgrade Capital Contribution | N.D.C.2.02 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | [6 empty] | Project | ACTN IESO | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24324 | Beck #1 SS - G1 G2 OPG Connection | N.T.C.2.12 | 7700 | 203 | PROJECT DELIVERY | AIP005982 | AIP005982 | AIP005982 | No | AIP005982 | Beck #1 SS - G1 G2 OPG Connection | 0 |  | Generator Customer Connection | Robert.Reinmuller@HydroOne.com | Gene.Ng@HydroOne.com | System Access | 0 | 0 | 0 | 0 | Project | ACTN DETL | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 1000000 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -500000 | -1000000 | -1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43350 | 44362 | True | Work requested by OPG. | True | Transmission license requirement to connect customers. | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Beck #1 SS - G1 G2 OPG Connection
24325 | Fairchild TS M8 - Support THESL Protection Upgrade | N.T.C.2.11 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Load Customer Connection | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24326 | eBilling Customer Usage Analytics - CAP | N.D.C.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION | AIP005031 | AIP005031 | AIP005031 | No | AIP005031 | Customer Alerts & Analytics |  |  | IT Business Solution Development | jj.blais@HydroOne.com | jj.blais@HydroOne.com | General Plant | 0 | 0 | 03 - None (default) | 0 | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42916 | 43099 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
24327 | Wanstead TS Egress Relocation | N.D.C.2.02 | 7700 | 203 | PROJECT DELIVERY | AIP005987 |  | AIP005987 | Yes | AIP005987 |  |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | [6 empty] | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24329 | H23B - Connect Stone Mills CGS | N.T.C.2.12 | 7700 | 203 | PROJECT DELIVERY | AIP005999 | AIP005999 | AIP005999 | No | AIP005999 | H23B - Connect Loyalist Solar | 0 |  | Generator Customer Connection | Robert.Reinmuller@HydroOne.com | Quyen.Diep@HydroOne.com | System Access | 0 | 0 | 0 | 0 | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2331500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2331500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43130 | 43343 | True | Customer requested work. | True | Transmission license requirement to connect customers. | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Alternative 1
24331 | Oxy Vinyls Load Displacement Generator Connection | N.T.C.2.12 | 7700 | 203 | PROJECT DELIVERY | AIP005985 | AIP005985 | AIP005985 | No | AIP005985 | Oxy Vinyls Load Displacement Generator Connection | 0 |  | Generator Customer Connection | Robert.Reinmuller@HydroOne.com | Gene.Ng@HydroOne.com | System Access | 0 | 0 | 0 | 0 | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -59360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43084 | [13 empty] | FALSE |  | 0 | 0 | Oxy Vinyls Load Displacement Generator Connection
24335 | Enhancemnts-Cust Billing/Metering/Testing Platform | N.C.C.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION | UNPLANNED |  |  | Yes |  |  |  |  | IT Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24336 | OMA Enhancements-Cust Billing/Metering/Testing | N.C.M.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION | UNPLANNED |  |  | Yes |  |  |  |  | IT-Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24337 | MSO and Jumper Installations | N.T.C.2.21 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Major Risk Mitigation | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | EMPP ACTN | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24338 | Cooksville TS-EZ Bus-ID28280-Lakeview Water Treatm | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24339 | Almonte M25 ID 63 – Mississippi River Power SCADA | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | [6 empty] | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24341 | Wanstead TS M4 PET-6 Recloser Teleprotection TX | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24342 | Kirkland Lake TS - G3K - ID30060 - Tx Matachewan L | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24343 | Kirkland Lake TS - G3K - ID30060 - Dx Matachewan L | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000195 |  | AIP000195 | Yes | AIP000195 | Small Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24344 | Source-to-Order Transformation Project - OMA | N.C.M.2.60 | 4339 | 212 | INFO SOLUTIONS DIVISION | AIP005908 | AIP005908 | AIP005908 | No | AIP005908 | OMA - Strategic Sourcing - Ariba | 0 |  | IT-Business Solution Development | jj.blais@HydroOne.com | Jun.Macabanti@hydroone.com | System O&M | 0 | 0 | 0 | 0 | Project | EMPP AWRD | Executing | Executing |  | 160000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42916 | 43220 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Asset Optimal
24345 | Nanticoke TS - Removal of OPG Equipment | N.T.C.1.41 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Hamilton/Niagara Zone Station/Yard Investments | James.Mardegan@HydroOne.com | [6 empty] | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24346 | AMI Network Expansion Economic Limits | N.D.C.1.09 | 7374 | 205 | LINES | AIP005831 | AIP005831 | AIP005831 | No | AIP005831 | AMI Network Expansion Economic Limits Project | ISD-SA-03 | Meter Infrastructure Expansion Program | Metering | Peter.Mitskos@HydroOne.com | Dominic.Consorti@HydroOne.com | System Access | 0 | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning | # Of Devices | 2988762.9195 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3049758.0812 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -60995.1616 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43433 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
24347 | Nebo TS M12 ID32360 DX Maple Leaf Foods Inc | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000199 |  | AIP000199 | Yes | AIP000199 | Large Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | HOLD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24348 | Nebo TS M12 ID32360 TX Maple Leaf Foods Inc | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000199 |  | AIP000199 | Yes | AIP000199 | Large Embedded Generation (E/PD) |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | EMPP HOLD | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24349 | Onaping Depth Connection to S5M | N.T.C.2.11 | 7700 | 203 | PROJECT DELIVERY | AIP006103 | AIP006103 | AIP006103 | No | AIP006103 | Onaping Depth Connection to S5M | 0 |  | Load Customer Connection | Robert.Reinmuller@HydroOne.com | Kirpal.Bahra@HydroOne.com | System Access | 0 | 0 | 0 | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | 2650000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -300000 | -2650000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43799 | 44165 | True | Customer requested work- Onaping Mine | True | Transmission license requirement to connect customer. | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Onaping Connection to S5M
24350 | Demand Capital - Equipment Failure (E&CS) | N.T.C.1.46 | 7700 | 203 | PROJECT DELIVERY | AIP000554 |  | AIP000554 | Yes | AIP000554 | Demand Capital - Power Transformers |  |  | Tx Station Demand and Spares | James.Mardegan@HydroOne.com | peter.zhao@hydroone.com | System Renewal | N/A | 0 | 03 - None (default) | 0 | Program | ACTN EMPP | Executing | Short Term Planning | # of Transformers | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24351 | Havelock TS-M1-ID29980-Dx-O'Brien | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000195 |  | AIP000195 | Yes | AIP000195 | Small Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24352 | Havelock TS-M1-ID 30,120- Dx-Emma Cardiff 2 | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000195 |  | AIP000195 | Yes | AIP000195 | Small Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24353 | Havelock TS-M1-ID29980-Tx-O'Brien | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24354 | Havelock TS-M1- ID30,120 -Tx- Emma Cardiff 2 | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24356 | Town of Dundalk voltage conversion | N.D.C.2.02 | 7374 | 205 | LINES | AIP005835 | AIP005835 | AIP005835 | No | AIP005835 | Town of Dundalk voltage conversion | ISD-SS-02 | System Upgrades Driven by Load Growth | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Mark.VanTol@hydroone.com | System Service | Central | 0 | 03 - None (default) | 0 | Project | DETL AWRD | Short Term Planning | Short Term Planning |  | 0 | 510451.0649 | 4597435.0857 | 4600008.9935 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 510451.0649 | 4597435.0857 | 4600008.9935 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43833 | 44501 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
24358 | Havelock TS-M1-ID29970-Dx-Antonio West | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000195 |  | AIP000195 | Yes | AIP000195 | Small Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24359 | Havelock TS-M1-ID29970-Tx-Antonio West | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24360 | TWE - Construction Service Equipment | N.C.C.1.30 | 7411 | 228 | CONSTRUCTION | AIP000014 |  | AIP000014 | Yes | AIP000014 | Transport and Work Equipment (TWE) Capital Requirements |  |  | Fleet | robert.berardi@HydroOne.com | angela.mallozzi@hydroone.com | General Plant | 0 | 0 | 03 - None (default) | 0 | Program | init | Short Term Planning | Short Term Planning | # of Vehicles | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24361 | Havelock TS-M1-ID30130-Dx-Kelly North | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000195 |  | AIP000195 | Yes | AIP000195 | Small Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24362 | Havelock TS-M1-ID30130-Tx-Kelly North | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24363 | Bermondsey TS - Support THESL M1 Breaker Upgrade | N.T.C.2.11 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Load Customer Connection | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24364 | Dundas Sydenham DS Voltage Conversion | N.D.C.2.02 | 7374 | 205 | LINES | AIP005834 | AIP005834 | AIP005834 | No | AIP005834 | Dundas Sydenham DS Voltage Conversion | ISD-SR-13 | Life Cycle Optimization & Operational Efficiency Projects | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Helen.Guo@HydroOne.com | System Renewal | Western | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 234508.5762 | 2631385.1347 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 260565.0847 | 2923761.2608 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -26056.5085 | -292376.1261 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43468 | 43679 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
24365 | Havelock TS-M1-ID30110-Dx-Donovan | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000195 |  | AIP000195 | Yes | AIP000195 | Small Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24366 | Havelock TS-M1-ID30110-Tx-Donovan | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24370 | Havelock TS-M1-ID30090-Dx-Card | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000195 |  | AIP000195 | Yes | AIP000195 | Small Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24371 | Havelock TS-M1-ID30090-Tx-Card | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24372 | Havelock TS-M1-ID30100-Dx-Conlon | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000195 |  | AIP000195 | Yes | AIP000195 | Small Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24373 | Havelock TS-M1-ID30100-Tx-Conlon | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24374 | Havelock TS-M1-ID30140-Dx-Forcier | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000195 |  | AIP000195 | Yes | AIP000195 | Small Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24375 | Havelock TS-M1-ID30140-Tx-Forcier | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24376 | Havelock TS-M1-ID30150-Dx-Painter | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000195 |  | AIP000195 | Yes | AIP000195 | Small Embedded Generation (E/PD) |  |  | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24377 | Havelock TS-M1-ID30150-Tx-Painter | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24378 | Havelock TS-M1-ID 30,170- Dx-Switzer G | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000195 |  | AIP000195 | Yes | AIP000195 | Small Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24379 | Havelock TS-M1- ID30,170 -Tx- Switzer G | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24380 | Havelock TS-M1-ID30960-Dx-McGinn | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000195 |  | AIP000195 | Yes | AIP000195 | Small Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24381 | Havelock TS-M1-ID30960-Tx-McGinn | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24382 | HavelockTS-M1-ID31000-Dx-Lambe | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000195 |  | AIP000195 | Yes | AIP000195 | Small Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24383 | HavelockTS-M1-ID31000-Tx-Lambe | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24384 | HavelockTS-M1-ID31010-Dx-Watson | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000195 |  | AIP000195 | Yes | AIP000195 | Small Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24385 | HavelockTS-M1-ID31010-Tx-Watson | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24386 | HavelockTS-M1-ID31020-Dx-Kelly South | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000195 |  | AIP000195 | Yes | AIP000195 | Small Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24387 | HavelockTS-M1-ID31020-Tx-Kelly South | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24388 | Stewartville TS-M3-ID31060-Tx-Time Fibre Fit | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | EMPP ACTN | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24389 | CTI Replacement - OMA | N.D.M.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION | AIP005839 | AIP005839 | AIP005839 | No | AIP005839 | CTI Replacement - OMA |  |  | IT Business Solution Development | jj.blais@HydroOne.com | jj.blais@HydroOne.com | System O&M | 0 | 0 | 0 | 0 | Project | init | Short Term Planning | Short Term Planning |  | 728023.6856 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 728023.6856 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43008 | 43465 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
24390 | Havelock TS-M1-ID30180-Dx-Scheurer | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000195 |  | AIP000195 | Yes | AIP000195 | Small Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24391 | Havelock TS-M1-ID30180-Tx-Scheurer | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24392 | Havelock TS-M1-ID30930-Dx-Blakely | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000195 |  | AIP000195 | Yes | AIP000195 | Small Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24393 | Havelock TS-M1-ID30930-Tx-Blakely | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24394 | Havelock TS-M1-ID30940-Dx-Kyte | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000195 |  | AIP000195 | Yes | AIP000195 | Small Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24395 | Havelock TS-M1-ID30940-Tx- Kyte | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24396 | Havelock TS-M1-ID30950-Dx-Cox | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000195 |  | AIP000195 | Yes | AIP000195 | Small Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24397 | Havelock TS-M1-ID30950-Tx-Cox | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24398 | Kapuskasing L21L38 PSR | N.T.C.2.21 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Major Risk Mitigation | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24399 | Perth Area Study | N.D.C.2.02 | 7374 | 205 | LINES | AIP005830 | AIP005830 | AIP005830 | No | AIP005830 | Perth Area Study | ISD-SS-02 | System Upgrades Driven by Load Growth | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Donald.Lau@HydroOne.com | System Service | Eastern | Not Required | 03 - None (default) | Not Required | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 2126974.0797 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2126974.0797 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44348 | 44817 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
24400 | Web Redesign: eCustomer | N.D.M.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION | UNPLND |  |  | Yes |  |  |  |  | IT Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | EMPP AWRD | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24401 | Web Redesign: HydroOne.com | N.C.M.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION | UNPLND |  |  | Yes |  |  |  |  | IT-Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24402 | Forest Jefferson and Mcnab DS Conversion | N.D.C.2.02 | 7374 | 205 | LINES | AIP005862 | AIP005862 | AIP005862 | No | AIP005862 | Forest Jefferson and Forest McNab DS Removals | ISD-SR-13 | Life Cycle Optimization & Operational Efficiency Projects | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Alexander.Hamlyn@HydroOne.com | System Renewal | Western | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 1585281.2675 | 1585401.079 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1801455.9858 | 1801592.1352 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -216174.7183 | -216191.0562 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43160 | 43784 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
24403 | Wallaceburg DS Conversion | N.D.C.2.02 | 7374 | 205 | LINES | AIP005864 | AIP005864 | AIP005864 | No | AIP005864 | Wallaceburg DS Removal | ISD-SR-13 | Life Cycle Optimization & Operational Efficiency Projects | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Alexander.Hamlyn@HydroOne.com | System Renewal | Western | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 161710.87 | 1456467.4352 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 183762.3523 | 1655076.6309 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -22051.4823 | -198609.1957 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43818 | 44163 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
24404 | Lucan Market DS 4kV Conversion | N.D.C.2.02 | 7374 | 205 | LINES | AIP005863 | AIP005863 | AIP005863 | No | AIP005863 | Lucan Market DS Voltage Conversion | ISD-SR-13 | Life Cycle Optimization & Operational Efficiency Projects | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Alexander.Hamlyn@HydroOne.com | System Renewal | Western | 0 | 03 - None (default) | 0 | Project | DETL ACTN | Short Term Planning | Short Term Planning |  | 2016830.0569 | 1030510.7014 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2291852.3374 | 1171034.8879 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -275022.2805 | -140524.1865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43160 | 43784 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
24405 | Drumbo DS Conversion | N.D.C.2.02 | 7374 | 205 | LINES | AIP005884 | AIP005884 | AIP005884 | No | AIP005884 | Drumbo DS Conversion | ISD-SR-13 | Life Cycle Optimization & Operational Efficiency Projects | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Alexander.Hamlyn@HydroOne.com | System Renewal | Western | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 202579.0368 | 1824550.7085 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 230203.4509 | 2073353.0779 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -27624.4141 | -248802.3693 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43818 | 44163 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
24406 | Anderdon DS Conversion | N.D.C.2.02 | 7374 | 205 | LINES | AIP005885 | AIP005885 | AIP005885 | No | AIP005885 | Anderdon DS Conversion | ISD-SR-13 | Life Cycle Optimization & Operational Efficiency Projects | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Alexander.Hamlyn@HydroOne.com | System Renewal | Western | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 146796.4196 | 1322138.1946 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 166814.1131 | 1502429.7666 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -20017.6936 | -180291.572 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43818 | 44163 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
24407 | Wardsville DS Conversion | N.D.C.2.02 | 7374 | 205 | LINES | AIP005886 | AIP005886 | AIP005886 | No | AIP005886 | Wardsville DS Conversion | ISD-SR-13 | Life Cycle Optimization & Operational Efficiency Projects | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Alexander.Hamlyn@HydroOne.com | System Renewal | Western | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 103620.9438 | 933274.0339 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 117751.0724 | 1060538.6748 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -14130.1287 | -127264.641 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43818 | 44163 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
24408 | Zorra DS Conversion | N.D.C.2.02 | 7374 | 205 | LINES |  |  |  | No |  |  |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24409 | Stray Voltage Investigation and Resolution | N.D.C.1.06 | 7374 | 205 | LINES | AIP000136B | AIP000136 | AIP000136 | No | AIP000136 | Post Trouble and Power Quality |  |  | Trouble Calls & Storm Damage | emre.aydin@HydroOne.com | Wojciech.Maroszek@HydroOne.com | System Service | 0 | 0 | 03 - None (default) | 0 | Program | init EMPP | Executing | Short Term Planning | # of occurrences | 458594.5686 | 467801.8542 | 477508.3183 | 487331.1663 | 497061.5262 | 0 | 0 | 0 | 0 | 0 | 521130.1916 | 531593.0162 | 542623.0889 | 553785.4162 | 564842.6434 | 0 | 0 | 0 | 0 | 0 | -62535.623 | -63791.1619 | -65114.7707 | -66454.2499 | -67781.1172 | 0 | 0 | 0 | 0 | 0 | -12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Demand
24410 | Norfolk TS M5 ID18230 Dx-UDI Port Ryerse Wind Farm | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000199 |  | AIP000199 | Yes | AIP000199 | Large Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | EMPP ACTN | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24411 | AMI Network Expansion Economic Limits Program | N.D.C.1.09 | 7374 | 205 | LINES | AIP005832 | AIP005832 | AIP005832 | No | AIP005832 | AMI Network Expansion Economic Limits Program | ISD-SA-03 | Meter Infrastructure Expansion Program | Metering | Peter.Mitskos@HydroOne.com | Dominic.Consorti@HydroOne.com | System Access | 0 | 0 | 03 - None (default) | 0 | Program | init | Short Term Planning | Short Term Planning | # Of Devices | 0 | 2943638.605 | 2897405.9966 | 2737970.852 | 2792638.3727 | 0 | 0 | 0 | 0 | 0 | 0 | 3003712.8622 | 2956536.7313 | 2793847.8081 | 2849630.9926 | 0 | 0 | 0 | 0 | 0 | 0 | -60074.2572 | -59130.7346 | -55876.9562 | -56992.6199 | 0 | 0 | 0 | 0 | 0 | -2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 694 | 659 | 626 | 595 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
24412 | Web Redesign: eCustomer | N.D.C.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION | AIP000214 | AIP000214 | AIP000214 | No | AIP000214 | E-Customer Replacement |  |  | IT Business Solution Development | jj.blais@HydroOne.com | jj.blais@HydroOne.com | General Plant | 0 | 0 | 03 - None (default) | 0 | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42916 | 43100 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
24413 | Operation-time DG Connection Impact Assessment | N.D.M.2.21 | 4230 | 213 | PLANNING | AIP005498 |  | AIP005498 | Yes | AIP005498 | RD&D Project - Grid Modernization and Energy Storage |  |  | Distribution RD&D | Daila.Dzintars@HydroOne.com | janet.eby@Hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24414 | SAP Fixed Asset & Settlement - OMA | N.C.M.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION | AIP005896 | AIP005896 | AIP005896 | No | AIP005896 | Fixed Asset & Capitalization Enhancement - OMA | 0 |  | IT-Business Solution Development | jj.blais@HydroOne.com | Jun.Macabanti@hydroone.com | System O&M | 0 | 0 | 0 | 0 | Project | EMPP AWRD | Executing | Executing |  | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42916 | 43100 | False |  | False |  | False |  | False | False |  | False | False | False | True | TRUE | Same as the Capital portion of the Fixed Asset & Capitalization Enhancement Project | 0 | 0 | Asset Optimal
24415 | Thorold Turner DS Voltage Conversion | N.D.C.2.02 | 7374 | 205 | LINES | AIP005838 | AIP005838 | AIP005838 | No | AIP005838 | Thorold Turner DS Voltage Conversion | ISD-SR-13 | Life Cycle Optimization & Operational Efficiency Projects | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Helen.Guo@HydroOne.com | System Renewal | Western | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 95686.8021 | 879049.6609 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 106318.6689 | 976721.8454 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -10631.8669 | -97672.1845 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43833 | 44044 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
24416 | Thorold Front DS Voltage Conversion | N.D.C.2.02 | 7374 | 205 | LINES | AIP005833 | AIP005833 | AIP005833 | No | AIP005833 | Thorold Front DS Voltage Conversion | ISD-SR-13 | Life Cycle Optimization & Operational Efficiency Projects | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Helen.Guo@HydroOne.com | System Renewal | Western | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 37521.3658 | 727219.1912 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41690.4064 | 808021.3235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4169.0406 | -80802.1324 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43434 | 43768 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
24417 | Thorold Allanport DS Voltage Conversion | N.D.C.2.02 | 7374 | 205 | LINES | AIP005861 | AIP005861 | AIP005861 | No | AIP005861 | Thorold Allanport DS Voltage Conversion | ISD-SR-13 | Life Cycle Optimization & Operational Efficiency Projects | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Helen.Guo@HydroOne.com | System Renewal | Western | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 45859.4649 | 327461.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52113.0283 | 372115.125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -6253.5634 | -44653.815 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43434 | 43768 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
24418 | Thorold Cleveland DS Voltage Conversion | N.D.C.2.02 | 7374 | 205 | LINES | AIP005856 | AIP005856 | AIP005856 | No | AIP005856 | Thorold Cleveland DS Voltage Conversion | ISD-SR-13 | Life Cycle Optimization & Operational Efficiency Projects | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Helen.Guo@HydroOne.com | System Renewal | Western | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 46901.6672 | 334903.567 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52112.9636 | 372115.0744 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -5211.2964 | -37211.5074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43434 | 43768 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
24419 | Thorold Ormond Voltage Conversion | N.D.C.2.02 | 7374 | 205 | LINES | AIP005855 | AIP005855 | AIP005855 | No | AIP005855 | Thorold Ormond DS Voltage Conversion | ISD-SR-13 | Life Cycle Optimization & Operational Efficiency Projects | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Helen.Guo@HydroOne.com | System Renewal | Western | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 47843.2809 | 341852.4923 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53159.201 | 379836.1026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -5315.9201 | -37983.6103 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43798 | 44134 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
24420 | Dundas TS #2 New Feeders | N.D.C.2.02 | 7374 | 205 | LINES | AIP005857 | AIP005857 | AIP005857 | No | AIP005857 | Dundas TS #2 New Feeders | ISD-SS-02 | System Upgrades Driven by Load Growth | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Helen.Guo@HydroOne.com | System Service | Western | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 467801.8542 | 6207609.3394 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 531593.0162 | 7054101.522 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -63791.1619 | -846492.1826 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43769 | 44134 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
24421 | Caledonia TS New Feeders | N.D.C.2.02 | 7374 | 205 | LINES | AIP005859 | AIP005859 | AIP005859 | No | AIP005859 | Caledonia TS New Feeders | ISD-SS-02 | System Upgrades Driven by Load Growth | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Helen.Guo@HydroOne.com | System Service | Western | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 233900.8671 | 4058821.4264 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 265796.4398 | 4612297.0755 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -31895.5728 | -553475.6491 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43798 | 44134 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
24422 | Puslinch DS 4th Feeder | N.D.C.2.02 | 7374 | 205 | LINES | AIP005858 | AIP005858 | AIP005858 | No | AIP005858 | Puslinch DS 4th Feeder | ISD-SS-03 | Reliability Improvements | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Helen.Guo@HydroOne.com | System Service | Western | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 191003.3754 | 2729055.0123 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 217049.2902 | 3101198.8776 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -26045.9148 | -372143.8653 | 0 | 0 | 0 | 0 | 0 | 0 | -12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44133 | 44500 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
24423 | Tilsonburg-Norfolk Tie Line | N.D.C.2.02 | 7374 | 205 | LINES | AIP005860 | AIP005860 | AIP005860 | No | AIP005860 | Tilsonburg-Norfolk Tie Line | ISD-SS-03 | Reliability Improvements | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Helen.Guo@HydroOne.com | System Service | Western | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 97466.2333 | 994123.0523 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 110757.0832 | 1129685.2868 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -13290.85 | -135562.2344 | 0 | 0 | 0 | 0 | 0 | -12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44530 | 44865 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
24424 | Macville DS - new 27.6kV station and feeders | N.D.C.2.02 | 7700 | 203 | PROJECT DELIVERY | AIP005837 | AIP005837 | AIP005837 | No | AIP005837 | Macville DS - New 27.6kV station | ISD-SS-02 | System Upgrades Driven by Load Growth | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Mark.VanTol@hydroone.com | System Service | Central | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 200176.9039 | 3505669.4554 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200176.9039 | 3505669.4554 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43800 | 44150 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
24425 | OEB Regulatory Compliance - OMA | N.D.M.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION | UNPLND |  |  | Yes |  |  |  |  | IT Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24426 | Bill Redesign - OMA | N.D.M.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION | AIP005842 | AIP005842 | AIP005842 | No | AIP005842 | OMA – Bill Redesign |  |  | IT Business Solution Development | jj.blais@HydroOne.com | jj.blais@HydroOne.com | System O&M | 0 | 0 | 0 | 0 | Project | EMPP AWRD | Executing | Executing |  | 0 | 0 | 0 | 0 | 353941.6348 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 353941.6348 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42916 | 44926 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
24427 | Hydro One Customer App Enhancement - OMA | N.D.M.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION | AIP005843 | AIP005843 | AIP005843 | No | AIP005843 | OMA – Hydro One Customer App Enhancement |  |  | IT Business Solution Development | jj.blais@HydroOne.com | jj.blais@HydroOne.com | System O&M | 0 | 0 | 0 | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 264747.2077 | 196467.8127 | 0 | 98317.2289 | 0 | 0 | 0 | 0 | 0 | 0 | 264747.2077 | 196467.8127 | 0 | 98317.2289 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43646 | 44926 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
24428 | Non-Energy Integration - OMA | N.D.M.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION | AIP005844 | AIP005844 | AIP005844 | No | AIP005844 | OMA – Non-Energy Integration |  |  | IT Business Solution Development | jj.blais@HydroOne.com | jj.blais@HydroOne.com | System O&M | 0 | 0 | 0 | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 315037.4803 | 137643.9691 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 315037.4803 | 137643.9691 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44377 | 44926 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
24429 | Peak Pricing & Rate Options - OMA | N.D.M.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION | UNPLND |  |  | Yes |  |  |  |  | IT Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24430 | Dynamic Pricing - OMA | N.D.M.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION | AIP005853 | AIP005853 | AIP005853 | No | AIP005853 | OMA - Billing - Dynamic Pricing |  |  | IT Business Solution Development | jj.blais@HydroOne.com | jj.blais@HydroOne.com | System O&M | 0 | 0 | 0 | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 294701.7191 | 78759.3971 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 294701.7191 | 78759.3971 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44012 | 44561 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
24431 | Pre-Paid Metering - OMA | N.D.M.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION | AIP005845 | AIP005845 | AIP005845 | No | AIP005845 | OMA – Pre-Paid Metering |  |  | IT Business Solution Development | jj.blais@HydroOne.com | jj.blais@HydroOne.com | System O&M | 0 | 0 | 0 | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 196634.2415 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 196634.2415 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44742 | 44926 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
24432 | Dunning Redesign - OMA | N.D.M.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION | AIP005846 | AIP005846 | AIP005846 | No | AIP005846 | OMA – Dunning Redesign |  |  | IT Business Solution Development | jj.blais@HydroOne.com | jj.blais@HydroOne.com | System O&M | 0 | 0 | 0 | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 137643.9691 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 137643.9691 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44742 | 45291 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
24433 | Enhance Outage App - OMA | N.D.M.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION | UNPLND |  |  | Yes |  |  |  |  | IT Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24434 | Customer Insight & Data - OMA | N.D.M.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION | AIP005847 | AIP005847 | AIP005847 | No | AIP005847 | OMA – Customer Insight & Data |  |  | IT Business Solution Development | jj.blais@HydroOne.com | jj.blais@HydroOne.com | System O&M | 0 | 0 | 0 | 0 | Project | init | Short Term Planning | Short Term Planning |  | 194139.6495 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 194139.6495 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42916 | 43465 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
24435 | Mobile Platform Strategy - OMA | N.D.M.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION | UNPLND |  |  | Yes |  |  |  |  | IT Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24436 | New Rate Design - OMA | N.D.M.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION | AIP005854 | AIP005854 | AIP005854 | No | AIP005854 | OMA - C&I - New Rate Design |  |  | IT Business Solution Development | jj.blais@HydroOne.com | jj.blais@HydroOne.com | System O&M | 0 | 0 | 0 | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 197579.8606 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 197579.8606 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43646 | 43830 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
24437 | First Fuel - OMA | N.D.M.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION | UNPLND |  |  | Yes |  |  |  |  | IT Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24438 | Demand to Interval Conversion - OMA | N.D.M.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION | AIP005840 | AIP005840 | AIP005840 | No | AIP005840 | OMA – Demand to Interval Conversion |  |  | IT Business Solution Development | jj.blais@HydroOne.com | jj.blais@HydroOne.com | System O&M | 0 | 0 | 0 | 0 | Project | init | Short Term Planning | Short Term Planning |  | 436814.2113 | 214249.1292 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 436814.2113 | 214249.1292 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42916 | 43830 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
24439 | Seasonal Rate Class Removal - OMA | N.D.M.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION | UNPLND |  |  | Yes |  |  |  |  | IT Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24440 | Net Metering Program (Microfit Replacement) - OMA | N.D.M.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION | UNPLND |  |  | Yes |  |  |  |  | IT Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24441 | eCustomer Replacement - OMA | N.D.M.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION | AIP005850 | AIP005850 | AIP005850 | No | AIP005850 | OMA – eCustomer Replacement |  |  | IT Business Solution Development | jj.blais@HydroOne.com | jj.blais@HydroOne.com | System O&M | 0 | 0 | 0 | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42916 | 43100 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
24442 | eBilling Customer Usage Alerts - OMA | N.D.M.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION | AIP005851 | AIP005851 | AIP005851 | No | AIP005851 | OMA – eBilling Customer Usage Alerts |  |  | IT Business Solution Development | jj.blais@HydroOne.com | jj.blais@HydroOne.com | System O&M | 0 | 0 | 0 | 0 | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42916 | 43100 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
24443 | Malden TS M12 ID30730 DX - McKinley | N.D.C.2.03 | 7374 | 205 | LINES | AIP000191 |  | AIP000191 | Yes | AIP000191 | Small Embedded Generation | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 03 - None (default) | 0 | Project | AWRD EMPP | Executing | Executing | # of Gen Connections | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24444 | Dresden DS Conversion | N.D.C.2.02 | 7374 | 205 | LINES | AIP005883 | AIP005883 | AIP005883 | No | AIP005883 | Dresden DS Removal | ISD-SR-13 | Life Cycle Optimization & Operational Efficiency Projects | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Alexander.Hamlyn@HydroOne.com | System Renewal | Western | 0 | 03 - None (default) | 0 | Project | EMPP AWRD | Executing | Executing |  | 255406.3864 | 2298831.5646 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 290234.53 | 2612308.5961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -34828.1436 | -313477.0315 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43453 | 43798 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
24445 | HR Operations Process Optimization - OMA | N.C.M.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION | AIP005904 |  | AIP005904 | Yes | AIP005904 |  |  |  | IT-Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24446 | SAP BPC - Planning Module - OMA | N.C.M.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION | AIP005905 |  | AIP005905 | Yes | AIP005905 |  |  |  | IT-Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24447 | SuccessFactors Onboarding - OMA | N.C.M.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION | AIP005906 | AIP005906 | AIP005906 | No | AIP005906 | Corporate Services Transformation - HR - OMA | 0 |  | IT-Business Solution Development | jj.blais@HydroOne.com | Jun.Macabanti@hydroone.com | System O&M | 0 | 0 | 0 | 0 | Project | init | Short Term Planning | Short Term Planning |  | 42200 | 99850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42200 | 99850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43190 | 43738 | False |  | False |  | False |  | False | False |  | False | False | True | True | TRUE | HR is considering a change in the HR Operating Model to support the company’s growth strategies. The Outsourcing Agreement with Inergi is expiring after 2019. Hydro One needs strategic leverage in any (re)negotiations in this regard. SAP is re-architecting its solution, with on-premise applications no longer supported after 2025. Meanwhile, ISD will have to be ready for a potential change in the IT Outsourcing Model. To enable and support the above objectives, ISD will have to move towards standardized SAP processes, leverage industry best practices and aim for cost effective solutions. | 0 | 0 | Vulnerable - Tx Contraint Reduction
24448 | HR Pay Transformation Project - OMA | N.C.M.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION | AIP005907 | AIP005907 | AIP005907 | No | AIP005907 | Corporate Services Transformation - HR/Pay - OMA | 0 |  | IT-Business Solution Development | jj.blais@HydroOne.com | Jun.Macabanti@hydroone.com | System O&M | 0 | 0 | 0 | 0 | Project | init | Short Term Planning | Short Term Planning |  | 170499.88 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 170499.88 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43190 | 43830 | False |  | False |  | False |  | False | False |  | False | False | True | True | TRUE | HR is considering a change in the HR Operating Model to support the company’s growth strategies. The Outsourcing Agreement with Inergi is expiring after 2019. Hydro One needs strategic leverage in any (re)negotiations in this regard. SAP is re-architecting its solution, with on-premise applications no longer supported after 2025. Meanwhile, ISD will have to be ready for a potential change in the IT Outsourcing Model. To enable and support the above objectives, ISD will have to move towards standardized SAP processes, leverage industry best practices and aim for cost effective solutions. | 0 | 0 | Vulnerable - Modified
24449 | Strategic Sourcing – Ariba - OMA | N.C.M.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION |  |  |  | No |  |  |  |  | IT-Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24450 | RF Device Replacement - OMA | N.C.M.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION | AIP005909 |  | AIP005909 | Yes | AIP005909 |  |  |  | IT-Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24451 | HydroOne.com Redesign - OMA | N.C.M.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION |  |  |  | No |  |  |  |  | IT-Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24452 | SAP Treasury - OMA | N.C.M.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION | AIP005910 |  | AIP005910 | Yes | AIP005910 |  |  |  | IT-Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24453 | Brockville 44kV M3/M7 expansion for Load Growth | N.D.C.2.02 | 7374 | 205 | LINES | AIP005866 | AIP005866 | AIP005866 | No | AIP005866 | Brockville 44kV Area Study | ISD-SS-02 | System Upgrades Driven by Load Growth | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Muhammad.Sabir@HydroOne.com | System Service | Eastern | Not Required | 03 - None (default) | Not Required | Project | DETL ACTN | Short Term Planning | Short Term Planning |  | 0 | 0 | 490990.1614 | 9825300.0758 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 490990.1614 | 9825300.0758 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44091 | 44455 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
24454 | Embrun Area Study | N.D.C.2.02 | 7374 | 205 | LINES | AIP005871 | AIP005871 | AIP005871 | No | AIP005871 | Embrun Area Study | ISD-SR-13 | Life Cycle Optimization & Operational Efficiency Projects | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Muhammad.Sabir@HydroOne.com | System Renewal | Eastern | Not Required | 03 - None (default) | Not Required | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 200436.1217 | 4008590.4361 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200436.1217 | 4008590.4361 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44456 | 44820 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
24455 | SAP CRM & iCare Enhancements - CAP | N.D.C.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION | AIP005867 | AIP005867 | AIP005867 | No | AIP005867 | SAP CRM & iCare Enhancements |  |  | IT Business Solution Development | jj.blais@HydroOne.com | jj.blais@HydroOne.com | General Plant | 0 | 0 | 0 | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 7191630.5929 | 2856214.7345 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7191630.5929 | 2856214.7345 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44012 | 44561 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
24456 | Complaint Management Tool - CAP | N.D.C.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION | AIP005869 | AIP005869 | AIP005869 | No | AIP005869 | Complaint Management Tool |  |  | IT Business Solution Development | jj.blais@HydroOne.com | jj.blais@HydroOne.com | General Plant | 0 | 0 | 0 | 0 | Project | init | Short Term Planning | Short Term Planning |  | 3012192.8663 | 272240.5993 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3012192.8663 | 272240.5993 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42947 | 43496 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
24457 | SAP CRM & iCare Enhancements - OMA | N.D.M.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION | AIP005868 | AIP005868 | AIP005868 | No | AIP005868 | OMA - SAP CRM & iCare Enhancements |  |  | IT Business Solution Development | jj.blais@HydroOne.com | jj.blais@HydroOne.com | System O&M | 0 | 0 | 0 | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 343818.7803 | 137828.945 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 343818.7803 | 137828.945 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44012 | 44561 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
24458 | Complaint Management Tool - OMA | N.D.M.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION | AIP005870 | AIP005870 | AIP005870 | No | AIP005870 | OMA - Complaint Management Tool |  |  | IT Business Solution Development | jj.blais@HydroOne.com | jj.blais@HydroOne.com | System O&M | 0 | 0 | 0 | 0 | Project | init | Short Term Planning | Short Term Planning |  | 364165.5334 | 33338.5373 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 364165.5334 | 33338.5373 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43131 | 43496 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
24459 | Shedden DS Refurbishment | N.D.C.1.08 | 7700 | 203 | PROJECT DELIVERY | AIP005912 |  | AIP005912 | Yes | AIP005912 |  |  |  | Distributing & Regulating Stations | emre.aydin@HydroOne.com | [6 empty] | Project | DETL init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24460 | Weston Lake DS - Feeder Tie & F2 Egress 3-phasing | N.D.C.2.02 | 7374 | 205 | LINES |  |  |  | No |  |  |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24461 | Brookside DS removal | N.D.C.2.02 | 7374 | 205 | LINES | AIP005889 | AIP005889 | AIP005889 | No | AIP005889 | Brookside DS removal | ISD-SR-13 | Life Cycle Optimization & Operational Efficiency Projects | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Dhaval.Patel@hydroone.com | System Renewal | Eastern | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 92391.69 | 1849190.5166 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 102090.2652 | 2043304.4383 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -9698.5752 | -194113.9216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -9.5 | 9.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43861 | 44164 | [13 empty] | FALSE |  | 0 | 0 | Brookside DS removal
24462 | SAP Spares Management | N.C.C.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION | AIP005919 |  | AIP005919 | Yes | AIP005919 |  |  |  | IT Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24463 | Mobile Enterprise Content Management | N.C.C.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION | UNPLND |  |  | Yes |  |  |  |  | IT Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24464 | Customer Request System | N.C.C.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION | AIP005923 |  | AIP005923 | Yes | AIP005923 |  |  |  | IT Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24465 | Brockville Town Area Study | N.D.C.2.02 | 7374 | 205 | LINES | AIP005872 | AIP005872 | AIP005872 | No | AIP005872 | Brockville Town Area Study | ISD-SR-13 | Life Cycle Optimization & Operational Efficiency Projects | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Muhammad.Sabir@HydroOne.com | System Renewal | Eastern | Not Required | 03 - None (default) | Not Required | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 200436.1217 | 4008590.4361 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200436.1217 | 4008590.4361 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44455 | 44818 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
24466 | Smiths Falls Area Study | N.D.C.2.02 | 7374 | 205 | LINES | AIP005873 | AIP005873 | AIP005873 | No | AIP005873 | Smith Fals Area Study | ISD-SR-13 | Life Cycle Optimization & Operational Efficiency Projects | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Muhammad.Sabir@HydroOne.com | System Renewal | Eastern | Not Required | 03 - None (default) | Not Required | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 200436.1217 | 4008590.4361 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200436.1217 | 4008590.4361 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44455 | 44818 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
24467 | Chesterville Area Study | N.D.C.2.02 | 7374 | 205 | LINES | AIP005874 | AIP005874 | AIP005874 | No | AIP005874 | Chesterville Area Study | ISD-SR-13 | Life Cycle Optimization & Operational Efficiency Projects | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Muhammad.Sabir@HydroOne.com | System Renewal | Eastern | Not Required | 03 - None (default) | Not Required | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 200436.1217 | 4008590.4361 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200436.1217 | 4008590.4361 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44455 | 44818 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
24468 | Ivy Lea Area Study | N.D.C.2.02 | 7374 | 205 | LINES | AIP005875 | AIP005875 | AIP005875 | No | AIP005875 | Ivy Lea Area Study | ISD-SR-13 | Life Cycle Optimization & Operational Efficiency Projects | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Muhammad.Sabir@HydroOne.com | System Renewal | Eastern | Not Required | 03 - None (default) | Not Required | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 200436.1217 | 4008590.4361 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200436.1217 | 4008590.4361 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44455 | 44818 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
24469 | Actons Corners Area Study | N.D.C.2.02 | 7374 | 205 | LINES | AIP005876 | AIP005876 | AIP005876 | No | AIP005876 | Actons Corner Area Study | ISD-SR-13 | Life Cycle Optimization & Operational Efficiency Projects | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Muhammad.Sabir@HydroOne.com | System Renewal | Eastern | Not Required | 03 - None (default) | Not Required | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 200436.1217 | 4008590.4361 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200436.1217 | 4008590.4361 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44455 | 44818 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
24470 | Russell Area Study | N.D.C.2.02 | 7374 | 205 | LINES | AIP005877 | AIP005877 | AIP005877 | No | AIP005877 | Russell Area Study | ISD-SR-13 | Life Cycle Optimization & Operational Efficiency Projects | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Muhammad.Sabir@HydroOne.com | System Renewal | Eastern | Not Required | 03 - None (default) | Not Required | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 200436.1217 | 4008590.4361 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200436.1217 | 4008590.4361 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44455 | 44818 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
24471 | Maxville Area Study | N.D.C.2.02 | 7374 | 205 | LINES | AIP005878 | AIP005878 | AIP005878 | No | AIP005878 | Maxville Area Study | ISD-SR-13 | Life Cycle Optimization & Operational Efficiency Projects | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Muhammad.Sabir@HydroOne.com | System Renewal | Eastern | Not Required | 03 - None (default) | Not Required | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 200323.9689 | 4008722.3944 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200323.9689 | 4008722.3944 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44452 | 44452 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
24472 | Kemptville Area Study | N.D.C.2.02 | 7374 | 205 | LINES | AIP005879 | AIP005879 | AIP005879 | No | AIP005879 | Kemptville Area Study | ISD-SR-13 | Life Cycle Optimization & Operational Efficiency Projects | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Muhammad.Sabir@HydroOne.com | System Renewal | Eastern | Not Required | 03 - None (default) | Not Required | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 200323.9689 | 4008722.3944 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200323.9689 | 4008722.3944 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44088 | 44452 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
24473 | Prescott Area Study | N.D.C.2.02 | 7374 | 205 | LINES | AIP005880 | AIP005880 | AIP005880 | No | AIP005880 | Prescott Area Study | ISD-SR-13 | Life Cycle Optimization & Operational Efficiency Projects | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Muhammad.Sabir@HydroOne.com | System Renewal | Eastern | Not Required | 03 - None (default) | Not Required | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 200323.9689 | 4008722.3944 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200323.9689 | 4008722.3944 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44088 | 44452 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
24474 | Berwick - Finch Area Study | N.D.C.2.02 | 7374 | 205 | LINES | AIP005881 | AIP005881 | AIP005881 | No | AIP005881 | Berwick - Finch Area Study | ISD-SR-13 | Life Cycle Optimization & Operational Efficiency Projects | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Muhammad.Sabir@HydroOne.com | System Renewal | Eastern | Not Required | 03 - None (default) | Not Required | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 200323.9689 | 4008722.3944 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200323.9689 | 4008722.3944 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44088 | 44452 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
24475 | Rondeau DS Conversion | N.D.C.2.02 | 7374 | 205 | LINES | AIP005887 | AIP005887 | AIP005887 | No | AIP005887 | Rondeau DS Conversion | ISD-SR-13 | Life Cycle Optimization & Operational Efficiency Projects | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Alexander.Hamlyn@HydroOne.com | System Renewal | Western | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 167347.9717 | 1507237.5418 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 190168.1497 | 1712769.9339 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -22820.178 | -205532.3921 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43818 | 44163 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
24476 | Tx Portal Enhancement - CAP | N.T.C.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION | AIP006155 | AIP006155 | AIP006155 | No | AIP006155 | Tx Portal Enhancement | 0 |  | IT Business Solutions Development | jj.blais@HydroOne.com | Myla.MendinuetoMartinez@HydroOne.com | General Plant | 0 | 0 | 0 | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 1746214.0517 | 495163.2637 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1746214.0517 | 495163.2637 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43644 | 44104 | False |  | False |  | False |  | False | True |  | False | False | False | False | FALSE |  | 0 | 0 | Asset Optimal
24477 | Website Upgrade & Enhancement - CAP | N.C.C.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION | AIP005899 |  | AIP005899 | Yes | AIP005899 |  |  |  | IT Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24478 | C&I Portal Enhancement - CAP | N.D.C.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION | UNPLND |  |  | Yes |  |  |  |  | IT Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24479 | Tx Portal Enhancement – OMA | N.T.M.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION | AIP006159 | AIP006159 | AIP006159 | No | AIP006159 | Tx Portal Enhancement | 0 |  | IT Business Solutions Development | jj.blais@HydroOne.com | Myla.MendinuetoMartinez@HydroOne.com | System O&M | 0 | 0 | 0 | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 178430.1708 | 49654.181 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 178430.1708 | 49654.181 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43644 | 44104 | False |  | False |  | False |  | False | True |  | False | False | False | False | FALSE |  | 0 | 0 | Asset Optimal
24480 | Website Upgrade & Enhancement - OMA | N.C.M.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION | AIP005902 |  | AIP005902 | Yes | AIP005902 |  |  |  | IT-Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24481 | C&I Portal Enhancement – OMA | N.D.M.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION | UNPLND |  |  | Yes |  |  |  |  | IT Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24482 | Mattawa HVDS Automation Pilot | N.D.C.2.02 | 7700 | 203 | PROJECT DELIVERY | AIP005894 | AIP005894 | AIP005894 | No | AIP005894 | Mattawa HVDS Automation Pilot |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Daniel.boutros@hydroone.com | System Renewal | 0 | Not Required | 03 - None (default) | Complete | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42215 | 42825 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
24483 | Dundalk Victoria DS F2 1-3ph conversion | N.D.C.2.02 | 7374 | 205 | LINES | AIP005916 | AIP005916 | AIP005916 | No | AIP005916 | Corbetton DS F1 - Reinforcement |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Mark.VanTol@hydroone.com | System Service | Central | 0 | 03 - None (default) | 0 | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42750 | 43040 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
24484 | Bradford DS F3 - reinforcement | N.D.C.2.02 | 7374 | 205 | LINES | AIP005917 | AIP005917 | AIP005917 | No | AIP005917 | Bradford DS F3 - Reinforcement |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Mark.VanTol@hydroone.com | System Service | Central | 0 | 03 - None (default) | 0 | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42750 | 43040 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
24485 | Lily Lake DS Removal | N.D.C.2.02 | 7374 | 205 | LINES | AIP005895 | AIP005895 | AIP005895 | No | AIP005895 | Lily Lake DS removal | ISD-SR-13 | Life Cycle Optimization & Operational Efficiency Projects | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Dhaval.Patel@hydroone.com | System Renewal | Eastern | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 161685.3675 | 3236083.4342 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 178657.8646 | 3575782.8002 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -16972.4971 | -339699.366 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -9.5 | 9.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43861 | 44163 | [13 empty] | FALSE |  | 0 | 0 | Lily Lake DS removal
24486 | Goderich TS - M4 - ID30870 - Compass LDG | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24487 | Eganville Bruce DS removal Area Study | N.D.C.2.02 | 7374 | 205 | LINES | AIP005911 |  | AIP005911 | Yes | AIP005911 |  |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24488 | Wainfleet DS End-of-life station replacement | N.D.C.2.02 | 7374 | 205 | LINES | AIP000160A |  | AIP000160 | Yes | AIP000160 | DS Station Refurbishment Program |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Nathan.Cox@hydroone.com | System Renewal | N/A | 0 | 03 - None (default) | 0 | Project | DETL ACTN | Short Term Planning | Short Term Planning | # of Stations | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24489 | PMR Engineering Support New | N.T.M.1.23 | 4048 | 213 | PLANNING | AIP001122 |  | AIP001122 | Yes | AIP001122 | PMR Engineering Support |  |  | Operation of Telecom Services | Miroslav.Kostic@HydroOne.com | Sheraz.Majid@HydroOne.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | init | Short Term Planning | Short Term Planning | Retainer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24490 | Oil Springs DS Refurbishment | N.D.C.1.08 | 7700 | 203 | PROJECT DELIVERY | AIP005913 |  | AIP005913 | Yes | AIP005913 |  |  |  | Distributing & Regulating Stations | emre.aydin@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24491 | Stratford DS Refurbishment | N.D.C.1.08 | 7700 | 203 | PROJECT DELIVERY | AIP005914 |  | AIP005914 | Yes | AIP005914 |  |  |  | Distributing & Regulating Stations | emre.aydin@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24492 | Stratford East Hope DS Refurbishment | N.D.C.1.08 | 7700 | 203 | PROJECT DELIVERY | AIP005915 |  | AIP005915 | Yes | AIP005915 |  |  |  | Distributing & Regulating Stations | emre.aydin@HydroOne.com | [6 empty] | Project | DETL init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24493 | Enhancements for AMINO and P&L | N.D.C.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION | AIP005927 | AIP005927 | AIP005927 | No | AIP005927 | Enhancements for AMINO and P&L |  |  | IT Business Solution Development | jj.blais@HydroOne.com | jj.blais@HydroOne.com | General Plant | 0 | 0 | 0 | 0 | Project | init | Short Term Planning | Short Term Planning |  | 2502022.2024 | 2854522.6498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2502022.2024 | 2854522.6498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43373 | 43830 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
24494 | Enhancements for AMINO and P&L - OMA | N.D.M.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION | AIP005928 | AIP005928 | AIP005928 | No | AIP005928 | Enhancements to AMINO and P&L |  |  | IT Business Solution Development | jj.blais@HydroOne.com | jj.blais@HydroOne.com | System O&M | 0 | 0 | 0 | 0 | Project | init | Short Term Planning | Short Term Planning |  | 194139.6495 | 243175.213 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 194139.6495 | 243175.213 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43373 | 43830 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
24495 | C&I Billing & Telephony Enhancements | N.D.C.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION | UNPLND |  |  | Yes |  |  |  |  | IT Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24496 | SAP Spares Management - OMA | N.C.M.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION | AIP005920 |  | AIP005920 | Yes | AIP005920 |  |  |  | IT-Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24497 | Mobile Enterprise Content Management - OMA | N.C.M.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION | UNPLND |  |  | Yes |  |  |  |  | IT-Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24498 | Customer Request System - OMA | N.C.M.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION | AIP005924 |  | AIP005924 | Yes | AIP005924 |  |  |  | IT-Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24499 | C&I Billing & Telephony Enhancements - OMA | N.D.M.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION | UNPLND |  |  | Yes |  |  |  |  | IT Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24500 | OEB Regulatory Compliance | N.D.C.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION | UNPLND |  |  | Yes |  |  |  |  | IT Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Program | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24501 | OEB Regulatory Compliance - OMA | N.D.M.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION | UNPLND |  |  | Yes |  |  |  |  | IT Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Program | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24502 | C-Suite Replacement | N.D.C.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION | AIP005925 | AIP005925 | AIP005925 | No | AIP005925 | C-Suite Replacement |  |  | IT Business Solution Development | jj.blais@HydroOne.com | jj.blais@HydroOne.com | General Plant | 0 | 0 | 0 | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 4003538.0783 | 4006479.3776 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4003538.0783 | 4006479.3776 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43646 | 44196 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
24503 | C-Suite Replacement - OMA | N.D.M.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION | AIP005926 | AIP005926 | AIP005926 | No | AIP005926 | C-Suite Replacement - OMA |  |  | IT Business Solution Development | jj.blais@HydroOne.com | jj.blais@HydroOne.com | System O&M | 0 | 0 | 0 | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 392218.0855 | 392935.6254 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 392218.0855 | 392935.6254 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43646 | 44196 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
24504 | Striker HVDS F2 ID30270 Dx NSPG Fixed 300 | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000195 |  | AIP000195 | Yes | AIP000195 | Small Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24505 | Great Lakes Power Integration Costs | N.D.M.9.01 | 4465 | 216 | BUSINESS INTEGRATION | UNPLND |  |  | Yes | [12 empty] | Program | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24506 | S2B - Surge Arrestors on 115kV circuit | N.T.C.2.21 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Major Risk Mitigation | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | EMPP ACTN | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24507 | Medonte DS F1-Deand Enhancement Diamond Valley | N.D.C.2.02 | 7374 | 205 | LINES | AIP005918 | AIP005918 | AIP005918 | No | AIP005918 | Medonte DS F1 - Demand Enhancement - Diamond Valley | ISD-SS-02 | System Upgrades Driven by Load Growth | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Matthew.Bell@HydroOne.com | System Service | 0 | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 47715.7983 | 286505.0631 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54222.498 | 325573.9353 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -6506.6998 | -39068.8722 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43769 | 44134 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
24508 | Kingsville TS-M1 M7-DG 1096-1099 Cust PV Mitigatio | N.D.M.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000194 |  | AIP000194 | Yes | AIP000194 | Distance Limitation Mitigation Work (E&T) | ISD-SA-05 | Distributed Generation Connections | Distributed Generation Connections | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | Not Required | 03 - None (default) | Not Required | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24509 | Drive X Software and Process Development | N.D.M.1.05 | 4342 | 212 | INFO SOLUTIONS DIVISION | AIP005970 | AIP005970 | AIP005970 | No | AIP005970 | DriveX Tool Development |  |  | Customer Meters | Peter.Mitskos@HydroOne.com | Dominic.Consorti@HydroOne.com | System O&M | 0 | 0 | 0 | 0 | Project | init | Short Term Planning | Short Term Planning |  | 618334.706 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 618334.706 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43465 | [13 empty] | FALSE |  | 0 | 0 | DriveX Tool
24510 | Striker HVDS F2 ID30260 Dx NSPG Fixed 200 | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000195 |  | AIP000195 | Yes | AIP000195 | Small Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24511 | Striker HVDS F2 ID30260 Tx NSPG Fixed 200 | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | EMPP ACTN | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24512 | Kent TS M22 ID30440 TX - Entegrus -Dajcor Aluminum | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24513 | E2E Performance Monitoring - OMA | N.C.M.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION | UNPLND |  |  | Yes |  |  |  |  | IT-Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24515 | Striker HVDS F2 ID30270 Tx NSPG Fixed 300 | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24516 | Striker HVDS F2 ID30430 Tx NSPG Fixed 400 | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24517 | Striker HVDS F2 ID30430 Dx NSPG Fixed 400 | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000195 |  | AIP000195 | Yes | AIP000195 | Small Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24518 | Walker TS - Connect Enwin Feeder to M3 breaker | N.T.C.2.11 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Load Customer Connection | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24519 | Clarke TS M8 ID31660 TX - London Hydro 3M Cogen | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24520 | Itron EE Upgrade CAP | N.D.C.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION | AIP005961 | AIP005961 | AIP005961 | No | AIP005961 | IEE SAP Upgrade |  |  | IT Business Solution Development | jj.blais@HydroOne.com | Myla.MendinuetoMartinez@HydroOne.com | General Plant | 0 | 0 | 0 | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 1383009.1296 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1383009.1296 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44469 | 44561 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
24521 | NDM260 - Itron EE Upgrade – OMA | N.D.M.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION | AIP005968 | AIP005968 | AIP005968 | No | AIP005968 | IEE SAP Upgrade OMA |  |  | IT Business Solution Development | jj.blais@HydroOne.com | jj.blais@HydroOne.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 118139.0957 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 118139.0957 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44469 | 44561 | [13 empty] | FALSE |  | 0 | 0 | IEE SAP Upgrade OMA
24522 | Corporate Services Transformation - Finance - CAP | N.C.C.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION | AIP005962 | AIP005962 | AIP005962 | No | AIP005962 | Corporate Services Transformation - Finance - CAP | GP-09 | Corporate Services Transformation - Finance | IT Business Solution Development | jj.blais@HydroOne.com | Jun.Macabanti@hydroone.com | General Plant | 0 | 0 | 0 | 0 | Project | init | Short Term Planning | Short Term Planning |  | 1000000 | 2052593.2931 | 7662226.7783 | 7402935.2849 | 12654106.9402 | 14374878.6278 | 0 | 0 | 0 | 0 | 1000000 | 2052593.2931 | 7662226.7783 | 7402935.2849 | 12654106.9402 | 14374878.6278 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43189 | 45169 | False |  | False |  | False |  | False | False |  | False | False | True | False | TRUE | HR is considering a change in the HR Operating Model to support the company’s growth strategies. The Outsourcing Agreement with Inergi is expiring after 2019. Hydro One needs strategic leverage in any (re)negotiations in this regard. SAP is re-architecting its solution, with on-premise applications no longer supported after 2025. Meanwhile, ISD will have to be ready for a potential change in the IT Outsourcing Model. To enable and support the above objectives, ISD will have to move towards standardized SAP processes, leverage industry best practices and aim for cost effective solutions. | 0 | 0 | Asset Optimal
24523 | Corporate Services Transformation - Finance - OMA | N.C.M.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION | AIP005964 | AIP005964 | AIP005964 | No | AIP005964 | Corporate Services Transformation - Finance - OMA | 0 |  | IT-Business Solution Development | jj.blais@HydroOne.com | Jun.Macabanti@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 132599.88 | 210000 | 210000 | 170000 | 170000.08 | 0 | 0 | 0 | 0 | 0 | 132599.88 | 210000 | 210000 | 170000 | 170000.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43189 | 45169 | False |  | False |  | False |  | False | False |  | False | False | False | False | TRUE | HR is considering a change in the HR Operating Model to support the company’s growth strategies. The Outsourcing Agreement with Inergi is expiring after 2019. Hydro One needs strategic leverage in any (re)negotiations in this regard. SAP is re-architecting its solution, with on-premise applications no longer supported after 2025. Meanwhile, ISD will have to be ready for a potential change in the IT Outsourcing Model. To enable and support the above objectives, ISD will have to move towards standardized SAP processes, leverage industry best practices and aim for cost effective solutions. | 0 | 0 | Vulnerable - Modified
24524 | Move-to-Mobile – Corporate - CAP | N.C.C.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION | AIP005963 |  | AIP005963 | Yes | AIP005963 |  |  |  | IT Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24525 | Move-to-Mobile - Corporate - OMA | N.C.M.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION | AIP005965 |  | AIP005965 | Yes | AIP005965 |  |  |  | IT-Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24526 | Web Redesign Project CAP | N.D.C.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION | AIP005959 | AIP005959 | AIP005959 | No | AIP005959 | Web Redesign Project |  |  | IT Business Solution Development | jj.blais@HydroOne.com | Myla.MendinuetoMartinez@HydroOne.com | General Plant | 0 | 0 | 0 | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 2272945.5101 | 5140015.0967 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2272945.5101 | 5140015.0967 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44377 | 44926 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
24527 | Web Redesign Project – OMA | N.D.M.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION | AIP005966 | AIP005966 | AIP005966 | No | AIP005966 | Web Redesign OMA |  |  | IT Business Solution Development | jj.blais@HydroOne.com | jj.blais@HydroOne.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 129953.0053 | 298667.7495 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 129953.0053 | 298667.7495 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44377 | 44926 | [13 empty] | FALSE |  | 0 | 0 | Web Redesign OMA
24528 | Customer Alerts & Analytics CAP | N.D.C.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION | AIP005960 | AIP005960 | AIP005960 | No | AIP005960 | eBilling, High Bill Alerts and Analytics |  |  | IT Business Solution Development | jj.blais@HydroOne.com | Myla.MendinuetoMartinez@HydroOne.com | General Plant | 0 | 0 | 0 | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 851376.9779 | 4409594.5677 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 851376.9779 | 4409594.5677 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44104 | 44561 | [13 empty] | FALSE |  | 0 | 0 | Asset Optimal
24529 | Customer Alerts & Analytics – OMA | N.D.M.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION | AIP005967 | AIP005967 | AIP005967 | No | AIP005967 | eBilling, High Bill Alerts and Analytics OMA |  |  | IT Business Solution Development | jj.blais@HydroOne.com | jj.blais@HydroOne.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 49116.9532 | 295347.7393 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49116.9532 | 295347.7393 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44104 | 44561 | [13 empty] | FALSE |  | 0 | 0 | eBilling, High Bill Aleers and Analytics OMA
24530 | Dymond TS - M3 - ID30700 - Tx Wahgoshig Solar 2 | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24531 | Dymond TS - M3 - ID30700 - Dx Wahgoshig Solar 2 | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000195 |  | AIP000195 | Yes | AIP000195 | Small Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24532 | SIA_PO_DG projects ID 32020 and 32050 | N.D.M.2.03 | 4048 | 213 | PLANNING | UNPLND |  |  | Yes |  |  |  |  | Distributed Generation Connections | ryan.boudreau@HydroOne.com | [6 empty] | Program | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24536 | Muskoka TS Cap-Switcher Installation | N.T.C.2.23 | 7700 | 203 | PROJECT DELIVERY | AIP005536 |  | AIP005536 | Yes | AIP005536 |  |  |  | Customer Power Quality (Tx) | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24540 | King Edward TS T3 and PCT Replacement | N.T.C.1.44 | 7700 | 203 | PROJECT DELIVERY | AIP005997 | AIP005997 | AIP005997 | No | AIP005997 | King Edward TS T3 and PCT Replacement | SR-07 | Protection and Automation Replacement Projects | Eastern Zone Station/Yard Investments | James.Mardegan@HydroOne.com | Fred.Kouhdani@HydroOne.com | System Renewal | Eastern | 0 | 01 - Agreement (current/future) | 0 | Project | DETL AWRD | Short Term Planning | Short Term Planning |  | 2130126.92 | 3169774.9488 | 893211.7766 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2290459.0537 | 3408360.16 | 960442.7705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -160332.1338 | -238585.2112 | -67230.9939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43375 | 43995 | True | HOL requested for upgrade existing TX from 75 to 100 MVA | False |  | False |  | False | True | HOL requested for upgrade existing TX and request for estimate for advancement and upgrade incremental cost | False | False | False | False | FALSE |  | 0 | 0 | Alternative 1
24541 | AMI Hardware Refresh (EOL) | N.D.C.1.09 | 7374 | 205 | LINES | AIP005059B | AIP005059 | AIP005059 | No | AIP005059 | AMI Hardware Refresh |  |  | Metering | Peter.Mitskos@HydroOne.com | Dominic.Consorti@HydroOne.com | System Renewal | 0 | 0 | 03 - None (default) | 0 | Program | init | Short Term Planning | Short Term Planning | # of meters | 0 | 0 | 0 | 1355575.0669 | 78705670.1874 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1355575.0669 | 78705670.1874 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3621 | 206119 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Vulnerable
24545 | Field Site Surveys - BCA Identification | N.T.M.1.29 | 4512 | 212 | INFO SOLUTIONS DIVISION | AIP001148 | AIP001148 | AIP001148 | No | AIP001148 | Field Site Audits - BCA Identification | 0 |  | NERC Cyber Security Compliance Readiness | lincoln.frost-hunt@hydroone.com | Sherry.Wilging@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | EMPP AWRD | Executing | Short Term Planning | # of Surveys | 98849.6835 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 98849.6835 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | True |  | False |  | False | False |  | False | False | False | False | TRUE | Asset inventory required for NERC projects; PCMIS updated for future projects | 0 | 0 | Asset Optimal
24546 | Hardware Firmware Security - Standards | N.T.M.1.29 | 4512 | 212 | INFO SOLUTIONS DIVISION | AIP005054 |  | AIP005054 | Yes | AIP005054 |  |  |  | NERC Cyber Security Compliance Readiness | lincoln.frost-hunt@hydroone.com | [6 empty] | Program | AWRD EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24547 | TFE Support - Standards | N.T.M.1.29 | 4512 | 212 | INFO SOLUTIONS DIVISION | AIP005055 |  | AIP005055 | Yes | AIP005055 |  |  |  | NERC Cyber Security Compliance Readiness | lincoln.frost-hunt@hydroone.com | [6 empty] | Program | AWRD EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24548 | TC219 - Transmission Work for DGs (Program) | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP005760 |  | AIP005760 | Yes | AIP005760 | Placeholder for Upstream Tx Work for DG (Project) |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Program | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24549 | Business Call Center Project | N.D.M.1.60 | 4042 | 212 | INFO SOLUTIONS DIVISION | UNPLND |  |  | Yes |  |  |  |  | IT Business Improvements & Enhancements | lincoln.frost-hunt@hydroone.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24550 | Ontario Rebate for Electricity Consumers | N.D.M.1.60 | 4042 | 212 | INFO SOLUTIONS DIVISION | UNPLND |  |  | Yes |  |  |  |  | IT Business Improvements & Enhancements | lincoln.frost-hunt@hydroone.com | [6 empty] | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24551 | WINDEEE2- Progressive Failure Analysis of Tx Lines | N.T.M.2.21 | 4230 | 213 | PLANNING | UNPLND |  |  | Yes |  |  |  |  | Technology Program | Daila.Dzintars@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24552 | Watay Line_to_Pickle Lake Connection | N.T.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP006017 | AIP006017 | AIP006017 | No | AIP006017 | Watay Line_to_Pickle Lake Connection | SS-04 | Watay Line to Pickle Lake Connection | Network Transfer Capability | Robert.Reinmuller@HydroOne.com | Hamid.Hamadanizadeh@HydroOne.com | System Service | 0 | 0 | 02 - Expectation (no agreement) | 0 | Project | BEST init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800000 | 8200000 | 20000000 | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -800000 | -8200000 | -20000000 | -1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43646 | 44095 | True | Watay will apply to OEB for connection to the grid. | False |  | False | Government has issued Order in Council for Watay to build the line to Pickle Lake. HONI is required to connect the line to the grid. | False | False |  | True | False | False | False | FALSE |  | 0 | 0 | Connect Watay 230 kV Line and 230/115 kV TS
24554 | D10H - 115 kV In-Line Switches | N.T.C.2.21 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Major Risk Mitigation | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | ACTN BEST | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24560 | L7S - Reliability Performance Mitigation | N.T.C.2.21 | 7700 | 203 | PROJECT DELIVERY | AIP005991 | AIP005991 | AIP005991 | No | AIP005991 | L7S - 115 kV In-Line Switches | 0 |  | Major Risk Mitigation | Robert.Reinmuller@HydroOne.com | Alessia.Dawes@HydroOne.com | System Service | 0 | 0 | 0 | 0 | Project | BEST ACTN | Short Term Planning | Short Term Planning |  | 196324.6873 | 196751.1273 | 0 | 144237.2834 | 1096248.4013 | 1420661.8296 | 0 | 0 | 0 | 0 | 196324.6873 | 196751.1273 | 0 | 144237.2834 | 1096248.4013 | 1420661.8296 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43343 | 45230 | False |  | False |  | False |  | False | True | improve customer delivery point performance | False | False | False | False | FALSE |  | 0 | 0 | L7S - 115 kV In-Line Switches
24566 | BATHURST TS:Support Breaker Installation for THESL | N.T.C.2.11 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Load Customer Connection | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24567 | Espanola TS - M2 - ID30900 - Helios Queensway | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | EMPP ACTN | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24570 | Ottawa LRT - Recoverable | N.T.C.1.14 | 7700 | 203 | PROJECT DELIVERY | AIP006170 | AIP006170 | AIP006170 | No | AIP006170 | Ottawa LRT - Recoverable | 0 |  | Third Party Transmission System Modifications | john.boldt@HydroOne.com | Gian.Minichini@HydroOne.com | System Renewal | Eastern | 0 | 01 - Agreement (current/future) | 0 | Project | DETL ACTN | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 650000 | 8093000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -650000 | -8093000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43409 | 43814 | True | City of Ottawa asked HONI to modify several transmission lines (H9A, F10MV, C7BM, V12M) to accommodate their LRT project. | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Ottawa LRT - Recoverable
24575 | Cobden TS M6 Extension | N.D.C.2.02 | 7374 | 205 | LINES | UNPLND |  |  | Yes |  |  |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | [6 empty] | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24576 | Parry Sound TS M1 ID 32180 -TX- Parry Energy Store | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24578 | 2017 Dynamic Energy Pricing Pilot – OEB Extension | N.D.M.2.50 | 1144 | 220 | STRATEGY & CONSERV | AIP005433 |  | AIP005433 | Yes | AIP005433 | 2015-2020 CDM Pilot projects |  |  | Conservation and Demand Management | Imran.Merali@HydroOne.com | Imran.Merali@HydroOne.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24579 | Cecil TS: Revenue Metering Upgrade | N.T.C.2.11 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Load Customer Connection | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24580 | Bermondsey TS - Support THESL M9 and M11 upgrade | N.T.C.2.11 | 7700 | 203 | PROJECT DELIVERY | AIP006026 | AIP006026 | AIP006026 | No | AIP006026 | Bermondsey TS - Support THESL M9 and M11 upgrade | 0 |  | Load Customer Connection | Robert.Reinmuller@HydroOne.com | Eva.Ping@HydroOne.com | System Access | 0 | 0 | 03 - None (default) | 0 | Project | ACCP EMPP | Executing | Executing |  | -43752.4639 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12247.5361 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -56000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43281 | True |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Bermondsey TS - Support THESL M9 and M11 upgrade
24582 | Red Lake TS / E4D upgrade - Capital Contribution | N.D.C.2.02 | 7700 | 203 | PROJECT DELIVERY |  |  |  | No |  |  |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24583 | Brocks Beach DS F2 ID 30820 - DX - Storage Zone | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | Distribution Generation Connection | ryan.boudreau@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24587 | DirectCurrent Fast Charger(DCFC) for EVs | N.D.M.2.21 | 4230 | 213 | PLANNING | AIP005498 |  | AIP005498 | Yes | AIP005498 | RD&D Project - Grid Modernization and Energy Storage |  |  | Distribution RD&D | Daila.Dzintars@HydroOne.com | janet.eby@Hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24589 | Parry Sound TS M1 ID 32180 -DX- Parry Energy Store | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | Distribution Generation Connection | ryan.boudreau@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24590 | Connect Marmora Pumping Station TX | N.T.C.2.12 | 7700 | 203 | PROJECT DELIVERY | AIP006037 | AIP006037 | AIP006037 | No | AIP006037 | Connect Marmora Pumping Station TX | 0 |  | Generator Customer Connection | Robert.Reinmuller@HydroOne.com | Quyen.Diep@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | BEST ACTN | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 1000000 | 2499999.96 | 21000000 | 14999999.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -500000 | -1000000 | -2499999.96 | -21000000 | -14999999.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44684 | 45838 | True | Customer requested work. | True | Transmission license requirement to connect customers. | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Alternative 1
24591 | 2017 Low Income ASHP CDM Pilot | N.D.M.2.50 | 1144 | 220 | STRATEGY & CONSERV | AIP005433 |  | AIP005433 | Yes | AIP005433 | 2015-2020 CDM Pilot projects |  |  | Conservation and Demand Management | Imran.Merali@HydroOne.com | Imran.Merali@HydroOne.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24592 | Brocks Beach DS F2 ID 30820 - TX - Storage Zone | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24595 | Erin DS F3 - Demand Enhancement | N.D.C.2.02 | 7374 | 205 | LINES | UNPLANNED |  |  | Yes |  |  |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | [6 empty] | Project | init DETL | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24596 | SIA Application: ID32450 Sky One Muskoka M2 | N.D.M.2.03 | 4048 | 213 | PLANNING | UNPLND |  |  | Yes |  |  |  |  | Distributed Generation Connections | ryan.boudreau@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24600 | Porcupine TS; Installation of Physical Security Pe | N.T.C.1.29 | 7700 | 203 | PROJECT DELIVERY | AIP005635 |  | AIP005635 | Yes | AIP005635 | CIP-014 Physical Security Implementation - Initial Sites |  |  | NERC Cyber Security Compliance Readiness | lincoln.frost-hunt@hydroone.com | Sherry.Wilging@hydroone.com | System Renewal | 0 | 0 | 03 - None (default) | 0 | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24601 | Tel Eng Technical Support New | N.T.M.1.23 | 7716 | 224 | ENGINEERING | AIP005346 | AIP005346 | AIP005346 | No | AIP005346 | Tel Eng Technical Support | 0 |  | Operation of Telecom Services | Miroslav.Kostic@HydroOne.com | Sheraz.Majid@HydroOne.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | ACTN EMPP | Executing | Short Term Planning | Retainer | 491282.9272 | 505552.1505 | 506472.646 | 508610.1895 | 508797.3759 | 508954.429 | 511000 | 510999.92 | 0 | 0 | 491282.9272 | 505552.1505 | 506472.646 | 508610.1895 | 508797.3759 | 508954.429 | 511000 | 510999.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | True | NERC, TSC | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Asset Optimal
24602 | Longueuil TS M24 44kV Line Expansion | N.D.C.2.02 | 7374 | 205 | LINES | UNPLND |  |  | Yes |  |  |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | [6 empty] | Project | ACTN DETL | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24604 | SIA App: ID33250-Gardiner TS-Invista swordfish | N.D.M.2.03 | 4048 | 213 | PLANNING | UNPLND |  |  | Yes |  |  |  |  | Distributed Generation Connections | ryan.boudreau@HydroOne.com | [6 empty] | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24605 | ITC - L4D L51D Protection Replacement | N.T.C.1.19 | 7700 | 203 | PROJECT DELIVERY | AIP006105 | AIP006105 | AIP006105 | No | AIP006105 | ITC L4D L51D Protection Replacement | 0 |  | Protection Control & Metering Equip | Miroslav.Kostic@HydroOne.com | Abu.Zahid@hydroone.com | System Renewal | Western | 0 | 01 - Agreement (current/future) | TBD | Project | AWRD DETL | Short Term Planning | Short Term Planning |  | 1352348.8832 | 1015794.5229 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1733815.6834 | 1575444.0687 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -81466.8002 | -84649.5458 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -6.647 | 0 | -300000 | -475000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43245 | 43601 | False |  | True | NPCC D4 | False |  | False | False |  | False | False | False | False | TRUE | International Facilities Agreement (IFA) between HONI and ITC obligates both parties to carry extraordinary maintenance, repair and end-of-life replacement on IPL and its associated equipment. | 0 | 0 | 2019 ISD
24607 | Clarabelle TS: Component Replacement | N.T.C.1.45 | 7700 | 203 | PROJECT DELIVERY | AIP006053 | AIP006053 | AIP006053 | No | AIP006053 | Clarabelle TS: Component Replacement | SR-06 | Load Station Switchgear and Ancillary Equipment Replacement Projects | Northern Zone Station/Yard Investments | James.Mardegan@HydroOne.com | Donald.Mastrangelo@HydroOne.com | System Renewal | Northern | Not Required | 03 - None (default) | Not Required | Project | DETL ACTN | Short Term Planning | Short Term Planning |  | 426025.3499 | 3215713.6117 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 458091.7741 | 3457756.5717 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -32066.4242 | -242042.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43289 | 43709 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Component Replacement
24609 | Wendover DS F3 ID31800 DX Celeste Solar | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Distribution Generation Connection | ryan.boudreau@HydroOne.com | [6 empty] | Project | EMPP ACTN | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24610 | Holland TS M6 ID32390 TX NTP BESS | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | UNPLANNED |  |  | Yes |  |  |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | [6 empty] | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24612 | Brant TS M22 Line Enhancement | N.D.C.2.02 | 7374 | 205 | LINES | UNPLND |  |  | Yes |  |  |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | [6 empty] | Project | EMPP ACTN | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24613 | Riverdale TS ID31620 CHP Carleton University | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | [6 empty] | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24614 | Aylmer TS: New Feeder Position for Erie Thames | N.T.C.2.11 | 7700 | 203 | PROJECT DELIVERY | AIP006027 | AIP006027 | AIP006027 | No | AIP006027 | Aylmer TS: New Feeder Position for Erie Thames | 0 |  | Load Customer Connection | Robert.Reinmuller@HydroOne.com | Jennifer.Li@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 700000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -700000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43131 | 43403 | True | Customer request from Erie Thames | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Alternative 1
24615 | Cap-Switcher Installations - Multiple | N.T.C.2.23 | 7700 | 203 | PROJECT DELIVERY | AIP006191 | AIP006191 | AIP006191 | No | AIP006191 | Customer Power Quality (Tx) - Capital - Cap Switcher | SS-17 | Customer Power Quality Program | Customer Power Quality (Tx) | Robert.Reinmuller@HydroOne.com | andrew.yan@HydroOne.com | System Service | N/A | 0 | 03 - None (default) | 0 | Program | ACCP EMPP | Executing | Short Term Planning |  | 3248819.3172 | 3302614.6673 | 3340782.5394 | 3366659.2026 | 3392240.468 | 3430379.7452 | 0 | 0 | 0 | 0 | 3248819.3172 | 3302614.6673 | 3340782.5394 | 3366659.2026 | 3392240.468 | 3430379.7452 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43131 | 45291 | True | Installation site are selected based on the transient over voltage complaints received from customers and the severity of transients observed in the station | False |  | False |  | False | True | The stations to install Cap-switchers are selected based on the severity of transient over voltages and the complaints received from industrial customers. Ex: the installation of Cap-Switcher at Napanee was based on the complaint received from Goodyear a large costumer supplied from Napanee | False | False | False | True | TRUE | This investment aligns with company’s strategy of being customer oriented. Installation of Cap switchers improves the quality of power customers receive. Installation site are selected based on the transient over voltage complaints received from customers and the severity of transients observed in the station | 0 | 0 | Asset Optimal
24616 | Transient USB solution (Was 23848) | N.T.M.1.29 | 4512 | 212 | INFO SOLUTIONS DIVISION | UNPLND |  |  | Yes |  |  |  |  | NERC Cyber Security Compliance Readiness | lincoln.frost-hunt@hydroone.com | [6 empty] | Project | EMPP AWRD | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24617 | NAE CTS SCADA Connection to Merivale TS | N.T.C.2.11 | 7700 | 203 | PROJECT DELIVERY | AIP006028 | AIP006028 | AIP006028 | No | AIP006028 | NAE CTS SCADA Connection to Merivale TS | 0 |  | Load Customer Connection | Robert.Reinmuller@HydroOne.com | Jean.Morneau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | DETL ACTN | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 225000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -225000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43131 | 43343 | True | Customer request- NAE | False |  | False |  | False | True |  | False | False | False | False | FALSE |  | 0 | 0 | Alternative 1
24622 | Station Service Estimates | N.T.M.1.17 | 8706 | 214 | METER SHOP | AIP005698 | AIP005698 | AIP005698 | No | AIP005698 | Station Service Estimates | 0 |  | Protection Control & Metering Equipment | Miroslav.Kostic@HydroOne.com | Mohnish.Bilimoria@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | AWRD EMPP | Executing | Short Term Planning |  | 77359.446 | 79128.6657 | 80858.1792 | 82661.3186 | 84345.6211 | 86059.0347 | 0 | 0 | 0 | 0 | 77359.446 | 79128.6657 | 80858.1792 | 82661.3186 | 84345.6211 | 86059.0347 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | True | IESOs Market Rules - Section 2.3.1 and 2.3.2 of Market Manual 3.7 | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Intermediate
24625 | Wendover DS F3 ID31800 TX Celeste Solar | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | [6 empty] | Project | EMPP ACTN | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24626 | Chapleau DS - 7 MW Borden mine - SIA application | N.D.M.2.02 | 4048 | 213 | PLANNING | UNPLND |  |  | Yes |  |  |  |  | Engineering and Technical Services | ted.lyberogiannis@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24630 | Operationalize DTF in Sector 4 | N.T.C.3.08 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Integrating Operating Infrastructure | Miroslav.Kostic@HydroOne.com | [6 empty] | Project | EMPP AWRD | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24635 | Frontenac M1/M8 Switching - town of Gananoque | N.D.C.2.02 | 7374 | 205 | LINES | UNPLND |  |  | Yes |  |  |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | [6 empty] | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24636 | Bruce Info Centre Wind Turbine - Decommissioning | N.D.C.2.02 | 7700 | 203 | PROJECT DELIVERY | AIP000184 |  | AIP000184 | Yes | AIP000184 | (2) Asset Life Cycle Optimization & Operational Efficiency | ISD-SR-13 | Life Cycle Optimization & Operational Efficiency Projects | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Michael.Medeiros@HydroOne.com | System Renewal | 0 | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24637 | Hinchey TS QZ BUS ID32620 Hull2 HOL | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP005760 |  | AIP005760 | Yes | AIP005760 | Placeholder for Upstream Tx Work for DG (Project) |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | EMPP ACTN | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24638 | Dundas TS M1 ID29300 DX eNature Greenhouses Inc | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000199 |  | AIP000199 | Yes | AIP000199 | Large Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24639 | Dundas TS M1 ID29300 TX eNature Greenhouses Inc | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000199 |  | AIP000199 | Yes | AIP000199 | Large Embedded Generation (E/PD) |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24640 | Overbrook TS: Relocate HONI P&C Equipment | N.T.C.2.11 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Load Customer Connection | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24641 | Lisgar TS QZ Bus ID32610 Tx 1GS HOL | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP005760 |  | AIP005760 | Yes | AIP005760 | Placeholder for Upstream Tx Work for DG (Project) |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | EMPP ACTN | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24645 | St Lawrence TS M24 ID31940 Dx Barlow Energy Centre | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Distribution Generation Connection | ryan.boudreau@HydroOne.com | [6 empty] | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24646 | St Lawrence TS M24 ID31940 TX Barlow Energy Centre | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | [6 empty] | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24650 | Meadowvale TS M7 ID32340 TX 3050 Argentia | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000199 |  | AIP000199 | Yes | AIP000199 | Large Embedded Generation (E/PD) |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | EMPP ACTN | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24666 | Orillia Integration Costs | N.D.M.9.01 | 4465 | 216 | BUSINESS INTEGRATION | UNPLND |  |  | Yes | [12 empty] | Program | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24667 | C21J: Connect Romney Wind Energy Centre | N.T.C.2.12 | 7700 | 203 | PROJECT DELIVERY | AIP006046 | AIP006046 | AIP006046 | No | AIP006046 | C21J: Connect Romney Wind Energy Centre | 0 |  | Generator Customer Connection | Robert.Reinmuller@HydroOne.com | Emeka.Okongwu@HydroOne.com | System Access | Western | Not Required | 01 - Agreement (current/future) | Not Required | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 999999.88 | 100000.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1000000 | -999999.88 | -100000.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43205 | 43862 | True | Romney Energy Centre LP. CCEA/CCRA expected. | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Alternative 1
24668 | Metrolinx Electrification Conflicts - Recoverable | N.T.C.1.14 | 7700 | 203 | PROJECT DELIVERY | AIP006167 | AIP006167 | AIP006167 | No | AIP006167 | Metrolinx Electrification - Recoverable | 0 |  | Third Party Transmission System Modifications | john.boldt@HydroOne.com | Gian.Minichini@HydroOne.com | System Renewal | Northern | 0 | 01 - Agreement (current/future) | 0 | Project | ACTN BEST | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -500000 | -1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43560 | 43814 | True | Metrolinx asked HONI to investigate and mitigate transmission line conflicts with their overhead electrification infrastructure at numerous locations across the province. | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Metrolinx Electrification - Recoverable
24670 | Arnprior TS: Station Rebuild | N.T.C.1.44 | 7700 | 203 | PROJECT DELIVERY | AIP006140 | AIP006140 | AIP006140 | No | AIP006140 | Arnprior TS: T1/T2 and PCT and Component Replacment | SR-02 | Station Reinvestment Projects | Eastern Zone Station/Yard Investments | James.Mardegan@HydroOne.com | Fred.Kouhdani@HydroOne.com | System Renewal | 0 | 0 | 03 - None (default) | 0 | Project | BEST ACTN | Short Term Planning | Short Term Planning |  | 0 | 689081.537 | 1730950.2035 | 7023866.9346 | 7077482.312 | 1779532.3438 | 0 | 0 | 0 | 0 | 0 | 740947.8892 | 1861236.7779 | 7552545.091 | 7610196.0344 | 1913475.6385 | 0 | 0 | 0 | 0 | 0 | -51866.3522 | -130286.5745 | -528678.1564 | -532713.7224 | -133943.2947 | 0 | 0 | 0 | 0 | -7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43857 | 45291 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Alternative 1- Green feild
24671 | Manby x Whiltshire OPGW (KxW) | N.T.C.1.25 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Auxiliary Telecommunication Equipment | Miroslav.Kostic@HydroOne.com | [6 empty] | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24675 | Keith TS M1 ID31600 TX - K+S Windsor Salt | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24680 | Leslie TS - M21, M25, M27, M28 KSO replace support | N.T.C.2.11 | 7700 | 203 | PROJECT DELIVERY | AIP006029 | AIP006029 | AIP006029 | No | AIP006029 | Leslie TS - M21, M25, M27, M28 KSO replace support | 0 |  | Load Customer Connection | Robert.Reinmuller@HydroOne.com | Eva.Ping@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42997 | 43281 | True | Toronto Hydro Request | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Leslie TS - M21, M25, M27, M28 KSO replace support
24681 | Physical Security Expansion Pilot Project | N.T.C.1.29 | 7700 | 203 | PROJECT DELIVERY | AIP005327 |  | AIP005327 | Yes | AIP005327 |  |  |  | NERC Cyber Security Compliance Readiness | lincoln.frost-hunt@hydroone.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24682 | Porcupine TS; Installation of Physical Security Pe | N.T.C.1.29 | 7700 | 203 | PROJECT DELIVERY | AIP005635 |  | AIP005635 | Yes | AIP005635 | CIP-014 Physical Security Implementation - Initial Sites |  |  | NERC Cyber Security Compliance Readiness | lincoln.frost-hunt@hydroone.com | Sherry.Wilging@hydroone.com | System Renewal | 0 | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24685 | Business Continuity and Emergency Preparedness | N.C.M.2.70 | 838 | 212 | INFO SOLUTIONS DIVISION | UNPLD |  |  | Yes |  |  |  |  | IT - Project & Architecture Services | lincoln.frost-hunt@hydroone.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24690 | Nebo TS M11 Book Road Expansion | N.D.C.2.02 | 7374 | 205 | LINES | UNPLND |  |  | Yes |  |  |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | [6 empty] | Project | DETL ACTN | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24695 | NERC Sustainment Program | N.T.M.1.29 | 4512 | 212 | INFO SOLUTIONS DIVISION | UNPLND |  |  | Yes |  |  |  |  | NERC Cyber Security Compliance Readiness | lincoln.frost-hunt@hydroone.com | [6 empty] | Program | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24696 | Fair Hydro Plan | N.D.M.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION | UNPLND |  |  | Yes |  |  |  |  | IT Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24697 | Fair Hydro Plan | N.D.C.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION | UNPLND |  |  | Yes |  |  |  |  | IT Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | EMPP AWRD | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24699 | Gerrard TS x Carlaw TS LV Cable Replacements | N.T.C.2.11 | 7700 | 203 | PROJECT DELIVERY | AIP006030 | AIP006030 | AIP006030 | No | AIP006030 | Gerrard TS x Carlaw TS LV Cable Replacements | 0 |  | Load Customer Connection | Robert.Reinmuller@HydroOne.com | Eva.Ping@HydroOne.com | System Access | 0 | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1070000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1070000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43251 | 43434 | True | Toronto Hydro Request | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Alternative 1
24700 | Kingsville TS M4 ID31570 TX - SPN030 | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24701 | Joint Use and Relocations >$75k | N.D.C.1.03 | 7374 | 205 | LINES | AIP000129 |  | AIP000129 | Yes | AIP000129 | Joint Use & Line Relocations | ISD-SA-01 | Joint Use and Line Relocations Program | Joint Use and Relocations | john.boldt@HydroOne.com | Jenny.Seo@HydroOne.com | System Access | 0 | 0 | 03 - None (default) | 0 | Program | EMPP AWRD | Executing | Short Term Planning | # of projects | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24702 | L7S - Increase Capacity - 3 spans out of Seaforth | N.T.C.2.02 | 7700 | 203 | PROJECT DELIVERY |  |  |  | No |  |  |  |  | Local Area Supply | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24703 | C21J and C22J: Upgrade Thermal Rating | N.T.C.2.02 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Local Area Supply | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24704 | B27S/B28S - Connect New TS | N.T.C.2.11 | 7700 | 203 | PROJECT DELIVERY |  |  |  | No |  |  |  |  | Load Customer Connection | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24705 | Vulnerability and Compliance Program. | N.C.M.2.70 | 4514 | 212 | INFO SOLUTIONS DIVISION | UNPLD |  |  | Yes |  |  |  |  | IT - Project & Architecture Services | lincoln.frost-hunt@hydroone.com | [6 empty] | Program | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24706 | GoWest Gold - Connect Bradshaw Gold CTS to H6T | N.T.C.2.11 | 7700 | 203 | PROJECT DELIVERY |  |  |  | No |  |  |  |  | Load Customer Connection | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24707 | Stewartville TS M1 ID32050 DX Calabogie Upgrade | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Distribution Generation Connection | ryan.boudreau@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24708 | Stewartville TS M1 ID32050 TX Calabogie Upgrade | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24709 | N5K: Connect Otter Creek Generation | N.T.C.2.12 | 7700 | 203 | PROJECT DELIVERY | AIP006038 | AIP006038 | AIP006038 | No | AIP006038 | N5K: Connect Otter Creek Generation | 0 |  | Generator Customer Connection | Robert.Reinmuller@HydroOne.com | Qasim.raza@hydroone.com | System Access | 0 | 0 | 02 - Expectation (no agreement) | 0 | Project | ACTN DETL | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 999999.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1000000 | -999999.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43343 | 43710 | True | Customer requested work. | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Alternative 1
24710 | Workplace Screening | N.C.M.2.70 | 838 | 212 | INFO SOLUTIONS DIVISION | UNPLD |  |  | Yes |  |  |  |  | IT - Project & Architecture Services | lincoln.frost-hunt@hydroone.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24711 | OPG Drawing Demerger | N.T.M.1.14 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Engineering and Environmental Support | Mike.Tanaskovic@HydroOne.com | [6 empty] | Project | INFD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24712 | Security and Architecture for Projects | N.C.M.2.70 | 838 | 212 | INFO SOLUTIONS DIVISION | UNPLD |  |  | Yes |  |  |  |  | IT - Project & Architecture Services | lincoln.frost-hunt@hydroone.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24714 | Campbell TS: T1, T2 Transformer Replacement | N.T.C.1.46 | 7370 | 206 | TX LINES AND STATIONS | AIP006120 | AIP006120 | AIP006120 | No | AIP006120 | Campbell TS: T1, T2 Transformer Replacement | 0 |  | Tx Station Demand and Spares | James.Mardegan@HydroOne.com | mark.truchanowicz@hydroone.com | System Renewal | Western | 0 | 03 - None (default) | 0 | Project | ACTN EMPP | Executing | Executing |  | 9446554.6991 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9635485.7931 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -188931.094 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1.9608 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42885 | 43462 | False |  | False |  | False |  | True | False |  | False | False | False | False | FALSE |  | 0 | 0 | Transformer Replacement
24716 | NERC v5 Mock Audit | N.T.M.1.29 | 838 | 212 | INFO SOLUTIONS DIVISION | UNPLND |  |  | Yes |  |  |  |  | NERC Cyber Security Compliance Readiness | lincoln.frost-hunt@hydroone.com | [6 empty] | Project | EMPP AWRD | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24717 | Leamington DESN2: Build Second 230/27.6 kV DESN | N.T.C.2.11 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Load Customer Connection | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24718 | Elgin TS ID31690 TX Alectra Utilities 2MW Cogen | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000199 |  | AIP000199 | Yes | AIP000199 | Large Embedded Generation (E/PD) |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24719 | Niagara Region Wind Farm SPS Implementation | N.T.C.2.12 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Generator Customer Connection | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24720 | Nepean TS M24 ID31850 TX Algonquin College cogen | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP005760 |  | AIP005760 | Yes | AIP005760 | Placeholder for Upstream Tx Work for DG (Project) |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24721 | W44LC – Connect Dutton CGS | N.T.C.2.12 | 7700 | 203 | PROJECT DELIVERY | AIP006039 | AIP006039 | AIP006039 | No | AIP006039 | W44LC - Connect Strong Breeze Wind Project | 0 |  | Generator Customer Connection | Robert.Reinmuller@HydroOne.com | Jennifer.Li@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | DETL ACTN | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1425000 | 1425000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1425000 | -1425000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43251 | 43708 | True | Generator customer connection request; CCEA expected to be signed by Q3 2017 and CCRA executed by Q1 2018 | False |  | False | Green energy large renewable | False | True |  | True | False | False | False | FALSE |  | 0 | 0 | Alternative 1
24722 | Doane DS - Installation and Expansion of F4 feeder | N.D.C.2.02 | 7374 | 205 | LINES |  |  |  | No |  |  |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24723 | Telecom Capital Lease Renewals (IRU Agreements) | N.T.C.1.25 | 4048 | 213 | PLANNING | AIP006113 | AIP006113 | AIP006113 | No | AIP006113 | Telecom Capital Lease Renewals (Fiber IRU Agreements) | SR-15 | Telecom Fibre IRU Agreement Renewals | Auxiliary Telecommunication Equipment | Miroslav.Kostic@HydroOne.com | Sheraz.Majid@HydroOne.com | System Renewal | N/A | 0 | 03 - None (default) | 0 | Program | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 2627854.2569 | 7858960.3492 | 2365351.9942 | 1294968.64 | 1209397.24 | 1435311.28 | 0 | 0 | 0 | 0 | 2627854.2569 | 7858960.3492 | 2365351.9942 | 1294968.64 | 1209397.24 | 1435311.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42797 | 45657 | False |  | False |  | True | IRU fibre renewals are required to operate the SONET network . After the end of "initial terms" as per HONI-HOT Master Fibre Optic Cable Agreement, Hydro One will need to exercise renewal options under this master contract. This investment is to provide sufficient funding for these renewals. | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Asset Optimal
24724 | Idle Metallic Communication Cable Removals | N.T.C.1.25 | 7700 | 203 | PROJECT DELIVERY |  |  |  | No |  |  |  |  | Auxiliary Telecommunication Equipment | Miroslav.Kostic@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24725 | Nanticoke TS - Connect Nanticoke Solar Generation | N.T.C.2.12 | 7700 | 203 | PROJECT DELIVERY | AIP006040 | AIP006040 | AIP006040 | No | AIP006040 | Nanticoke TS - Connect Nanticoke Solar Generation | 0 |  | Generator Customer Connection | Robert.Reinmuller@HydroOne.com | Jennifer.Li@HydroOne.com | System Access | 0 | 0 | 02 - Expectation (no agreement) | 0 | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1800000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43147 | 43434 | True | Generator customer connection request; CCEA will be signed by Q3 2018 and CCRA to be executed by Q1 2018 | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Alternative 1
24726 | Connect Markham MTS#5 | N.T.C.2.11 | 7700 | 203 | PROJECT DELIVERY | AIP006033 | AIP006033 | AIP006033 | No | AIP006033 | Connect Markham MTS#5 | 0 |  | Load Customer Connection | Robert.Reinmuller@HydroOne.com | E.Warren.King@HydroOne.com | System Access | Greater Toronto Area | Required | 01 - Agreement (current/future) | Required | Project | init | Short Term Planning | Short Term Planning |  | 196324.6873 | 196751.1273 | 107397.9041 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 596324.6873 | 596751.1273 | 297397.9041 | 600000 | 1500000 | 610000 | 0 | 0 | 0 | 0 | 5.5511e-11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -400000 | -400000 | -190000 | -600000 | -1500000 | -610000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44347 | 45077 | True | Customer request and attached letter from IESO confirming need for investment. | True | Ontario Resource and Transmission Assessment Criteria, Hydro One's Electricity Transmission License ET-2003-0035, Section 8 | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Connect Markham MTS #5
24727 | SIA Application: 7Acres 15 MW - Douglas Point TS | N.D.M.2.02 | 4048 | 213 | PLANNING | UNPLND |  |  | Yes |  |  |  |  | Engineering and Technical Services | ted.lyberogiannis@HydroOne.com | [6 empty] | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24728 | Hawthorne M30A/M31A Line Disconnect Switch Upgrade | N.T.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP006018 | AIP006018 | AIP006018 | No | AIP006018 | Hawthorne M30A/M31A Line Disconnect Switch Upgrade | 0 |  | Network Transfer Capability | Robert.Reinmuller@HydroOne.com | Jean.Morneau@HydroOne.com | System Service | 0 | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 466271.1322 | 467283.9274 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 466271.1322 | 467283.9274 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43343 | 43585 | True | IESO Request | True | ORTAC-Rating Exceeded | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Alternative 1
24729 | Bill Redesign | N.D.C.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION |  |  |  | No |  |  |  |  | IT Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24730 | D6V/D7V - Connect New MTS | N.T.C.2.11 | 7700 | 203 | PROJECT DELIVERY | AIP006034 | AIP006034 | AIP006034 | No | AIP006034 | D6V/D7V - Connect New MTS | 0 |  | Load Customer Connection | Robert.Reinmuller@HydroOne.com | Alessia.Dawes@HydroOne.com | System Access | 0 | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 1060760.8328 | 880000 | 0 | 0 | 0 | 0 | 0 | 0 | 39999.96 | 200000 | 1440760.8328 | 1260000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.2204e-10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -39999.96 | -200000 | -380000 | -380000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 45427 | True | customer requires connection to transmission system for their load growth | False |  | True |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Alternative 1
24731 | Campbell TS - Build 2nd Half of DESN#2 | N.T.C.2.11 | 7700 | 203 | PROJECT DELIVERY | AIP006035 | AIP006035 | AIP006035 | No | AIP006035 | Campbell TS - Build 2nd Half of DESN#2 | SA-03 | Campbell TS: Install Metalclad Substation and Connect to Idle Transformer Windings | Load Customer Connection | Robert.Reinmuller@HydroOne.com | Emeka.Okongwu@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000 | 999999.96 | 6499999.92 | 2499999.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -250000 | -999999.96 | -6499999.92 | -2499999.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43553 | 44286 | True | Guelph Hydro: CCEA/CCRA expected. | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Alternative 1
24732 | Nanticoke GS Disconnection | N.T.C.2.12 | 7700 | 203 | PROJECT DELIVERY | AIP006041 | AIP006041 | AIP006041 | No | AIP006041 | Nanticoke GS Disconnection | 0 |  | Generator Customer Connection | Robert.Reinmuller@HydroOne.com | Gene.Ng@HydroOne.com | System Access | 0 | 0 | 03 - None (default) | 0 | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 900000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -900000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42999 | 43115 | True | Request from OPGI | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Alternative 1
24733 | Lambton GS Disconnection | N.T.C.2.12 | 7700 | 203 | PROJECT DELIVERY | AIP006042 | AIP006042 | AIP006042 | No | AIP006042 | Lambton GS Disconnection | 0 |  | Generator Customer Connection | Robert.Reinmuller@HydroOne.com | Emeka.Okongwu@HydroOne.com | System Access | 0 | 0 | 03 - None (default) | 0 | Project | DETL LLTM HOLD | Short Term Planning | Short Term Planning |  | 736217.5772 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1986217.5772 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1.1102e-10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43251 | 43363 | True | Customer request from OPGI | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Alternative 1
24734 | Aylmer Tillsonburg Area Tranmission Reinforcement | N.T.C.2.02 | 7700 | 203 | PROJECT DELIVERY | AIP006015 | AIP006015 | AIP006015 | No | AIP006015 | Aylmer Tillsonburg Area Tranmission Reinforcement | SS-14 | Alymer-Tillsonburg Area Transmission Reinforcement | Local Area Supply | Robert.Reinmuller@HydroOne.com | Jennifer.Li@HydroOne.com | System Service | 0 | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 981623.4363 | 983755.5973 | 10251629.3036 | 13462146.4543 | 6196186.8314 | 0 | 0 | 0 | 0 | 0 | 981623.4363 | 983755.5973 | 10251629.3036 | 13462146.4543 | 6196186.8314 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43916 | 44742 | True | Request from HONI Dx and Tillsonburg Hydro Inc | True | Required to meet thermal and voltage criteria | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Alternative 1
24735 | D6V/D7V - Upgrade 5 km of circuit out of Detweiler | N.T.C.2.02 | 7700 | 203 | PROJECT DELIVERY | AIP006016 | AIP006016 | AIP006016 | No | AIP006016 | D6V/D7V - Upgrade 5 km of circuit out of Detweiler | 0 |  | Local Area Supply | Robert.Reinmuller@HydroOne.com | Alessia.Dawes@HydroOne.com | System Service | 0 | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 95325.9513 | 189421.5773 | 400000 | 1920000 | 1440000 | 0 | 0 | 0 | 0 | 0 | 95325.9513 | 189421.5773 | 500000 | 2400000 | 1800000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -100000 | -480000 | -360000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45352 | 46174 | True |  | True | ORTAC -Rating Exceeded | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Alternative 1
24737 | Tx Lines Aviation Light Remote Monitoring Repl | N.T.C.1.12 | 7700 | 203 | PROJECT DELIVERY | AIP006139 | AIP006139 | AIP006139 | No | AIP006139 | Aviation Light Remote Monitoring Replacement | 0 |  | Overhead Lines Component Refurb & Repl | hassan.hamzeh@hydroone.com | jacky.chiu@hydroone.com | System Renewal | 0 | Not Required | 0 | Not Required | Project | ACCP EMPP | Executing | Executing |  | 1883083.4055 | 1787139.9584 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2139867.5063 | 2030840.8619 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -256784.1008 | -243700.9034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43091 | 43819 | False |  | True | Transport Canada Standard 621 - Obstruction Marking and Lighting | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Aviation Light Remote Monitoring Replacement
24738 | Software for PQ Reports - Tx | N.T.M.2.23 | 8706 | 214 | METER SHOP | AIP005535B | AIP005535 | AIP005535 | No | AIP005535 | Customer Power Quality (Tx) - OMA | 0 |  | Customer Power Quality (Tx) | Robert.Reinmuller@HydroOne.com | andrew.yan@HydroOne.com | System O&M | N/A | 0 | 03 - None (default) | 0 | Program | AWRD EMPP | Executing | Short Term Planning |  | 201851.0538 | 206467.4586 | 210980.2575 | 215685.278 | 220079.8967 | 224550.8136 | 0 | 0 | 0 | 0 | 201851.0538 | 206467.4586 | 210980.2575 | 215685.278 | 220079.8967 | 224550.8136 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42370 | 45291 | True | The customer revenue meter program will be communicated via our key account management (KAM). We expect 22-25 customers to enroll in this initiative each year. The aggregated annual demand for PQ audit is variable. The customers are selected based on the results of our PQ investigation | False |  | False |  | False | True | The customer revenue meter program will be communicated via our key account management (KAM). We expect 22-25 customers to enroll in this initiative each year. The aggregated annual demand for PQ audit is variable. The customers are selected based on the results of our PQ investigation | False | False | False | True | TRUE | This investment aligns with company’s strategy of being customer oriented. Integrating customer’s revenue meters as PQ meters into H1 data base improves our ability to respond to our customer needs in a meaningful and efficient manner. Performing customer PQ audit provide us with information on system PQ performance, customer’s equipment immunity to power quality related disturbances, and practical solutions to extend the customer’s equipment ride-through capability. | 0 | 0 | Asset Optimal
24739 | Q25BM/Q29HM ADSS Replacement with OPGW | N.T.C.1.25 | 7700 | 203 | PROJECT DELIVERY | AIP006012 | AIP006012 | AIP006012 | No | AIP006012 | Q25BM/Q29HM ADSS Replacement | SR-13 | ADSS Fibre Optic Cable Replacements | Auxiliary Telecommunication Equipment | Miroslav.Kostic@HydroOne.com | Sheraz.Majid@HydroOne.com | System Renewal | 0 | 0 | 03 - None (default) | 0 | Project | AWRD DETL | Short Term Planning | Short Term Planning |  | 365492.1732 | 1393290.5795 | 3288582.7526 | 568123.7186 | 0 | 0 | 0 | 0 | 0 | 0 | 406102.4146 | 1548100.6439 | 3653980.8363 | 631248.5762 | 0 | 0 | 0 | 0 | 0 | 0 | -40610.2415 | -154810.0644 | -365398.0836 | -63124.8576 | 0 | 0 | 0 | 0 | 0 | 0 | -10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43327 | 44346 | False |  | False |  | False |  | True | False |  | False | True | False | False | FALSE |  | 0 | 0 | Replacement of Q25BM/Q29HM ADSS with OPGW
24740 | Muskoka TS M2 ID 32450 - TX - Sky One | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP005760 |  | AIP005760 | Yes | AIP005760 | Placeholder for Upstream Tx Work for DG (Project) |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24741 | Eastern Field Wind Power Project Connection | N.T.C.2.12 | 7700 | 203 | PROJECT DELIVERY | AIP006043 | AIP006043 | AIP006043 | No | AIP006043 | Eastern Field Wind Power Project Connection | 0 |  | Generator Customer Connection | Robert.Reinmuller@HydroOne.com | Jean.Morneau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | DETL ACTN | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2200000 | 600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2200000 | -600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43190 | 43539 | True | Work requested by customer. | True | Transmission license requirement to connect customers. | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Alternative 1
24742 | Muskoka TS M2 ID 32450 - DX - Sky One | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000199 |  | AIP000199 | Yes | AIP000199 | Large Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24743 | MTU Mtce&Inspect | N.T.M.1.16 | 7370 | 206 | TX LINES AND STATIONS | AIP006004 | AIP006004 | AIP006004 | No | AIP006004 | MTU Mtce&Inspect | 0 |  | Power Equipment | Mike.Tanaskovic@HydroOne.com | peter.zhao@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | init | Short Term Planning | Short Term Planning | # of Orders | 77019.5338 | 123133.2057 | 125885.6909 | 128774.1156 | 131445.5026 | 134171.1733 | 0 | 0 | 0 | 0 | 77019.5338 | 123133.2057 | 125885.6909 | 128774.1156 | 131445.5026 | 134171.1733 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Vulnerable (Modified - Tx Decision)
24744 | Customer PQ Tx - OMA - PQ Audit - Lightning | N.T.M.2.23 | 7792 | 213 | PLANNING | AIP005535C | AIP005535 | AIP005535 | No | AIP005535 | Customer Power Quality (Tx) - OMA | 0 |  | Customer Power Quality (Tx) | Robert.Reinmuller@HydroOne.com | andrew.yan@HydroOne.com | System O&M | N/A | 0 | 03 - None (default) | 0 | Program | AWRD EMPP | Executing | Short Term Planning |  | 152397.5456 | 155882.9414 | 159290.0962 | 162842.3315 | 166160.279 | 169535.8876 | 0 | 0 | 0 | 0 | 152397.5456 | 155882.9414 | 159290.0962 | 162842.3315 | 166160.279 | 169535.8876 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42370 | 45291 | True | The customer revenue meter program will be communicated via our key account management (KAM). We expect 22-25 customers to enroll in this initiative each year. The aggregated annual demand for PQ audit is variable. The customers are selected based on the results of our PQ investigation | False |  | False |  | False | True | The customer revenue meter program will be communicated via our key account management (KAM). We expect 22-25 customers to enroll in this initiative each year. The aggregated annual demand for PQ audit is variable. The customers are selected based on the results of our PQ investigation | False | False | False | True | TRUE | This investment aligns with company’s strategy of being customer oriented. Integrating customer’s revenue meters as PQ meters into H1 data base improves our ability to respond to our customer needs in a meaningful and efficient manner. Performing customer PQ audit provide us with information on system PQ performance, customer’s equipment immunity to power quality related disturbances, and practical solutions to extend the customer’s equipment ride-through capability. | 0 | 0 | Asset Optimal
24745 | Fergus TS M4 M8 ties | N.D.C.2.02 | 7374 | 205 | LINES | UNPLND |  |  | Yes |  |  |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | [6 empty] | Project | ACTN DETL | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24746 | H6T: Connection of Bradshaw Gold 5MW Load | N.T.C.2.11 | 7700 | 203 | PROJECT DELIVERY | AIP006036 | AIP006036 | AIP006036 | No | AIP006036 | H6T: Connection of Bradshaw Gold 5MW Load | 0 |  | Load Customer Connection | Robert.Reinmuller@HydroOne.com | Kirpal.Bahra@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 1290000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -200000 | -1290000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43404 | 43769 | True | Customer requested work | True | Transmission license requirement to connect customer. | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Alternative 1
24747 | Nation Rise Wind Farm Connection | N.T.C.2.12 | 7700 | 203 | PROJECT DELIVERY | AIP006044 | AIP006044 | AIP006044 | No | AIP006044 | Nation Rise Wind Farm Connection | 0 |  | Generator Customer Connection | Robert.Reinmuller@HydroOne.com | Jean.Morneau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | DETL ACTN | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 2400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -500000 | -2400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43190 | 43798 | True | Work requested by customer. | True | Transmission license requirement to connect customers. | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Alternative 1
24748 | 3rd Party SLU Technical Reviews | N.T.M.1.14 | 7716 | 224 | ENGINEERING | AIP006138 | AIP006138 | AIP006138 | No | AIP006138 | 3rd Party SLU Technical Reviews | 0 |  | Engineering and Environmental Support | Mike.Tanaskovic@HydroOne.com | Gian.Minichini@HydroOne.com | System O&M | N/A | 0 | 01 - Agreement (current/future) | 0 | Program | ACCP EMPP | Executing | Short Term Planning |  | 741372.6266 | 743459.0448 | 744812.7147 | 746492.4503 | 746767.1858 | 746997.5748 | 0 | 0 | 0 | 0 | 741372.6266 | 743459.0448 | 744812.7147 | 746492.4503 | 746767.1858 | 746997.5748 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | True | Ministry of Infrastructure, Infrastructure of ontario | False |  | False | Ministry of Infrastructure, Ongoing Indefinitely | False | False |  | True | False | False | False | FALSE |  | 0 | 0 | Intermediate
24749 | Stations Work Management & Mobility - Capital | N.C.C.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION | AIP006141 | AIP006141 | AIP006141 | No | AIP006141 | Stations Work Management & Mobility Ph2 - CAP | 0 |  | IT Business Solution Development | jj.blais@HydroOne.com | Jun.Macabanti@hydroone.com | General Plant | 0 | 0 | 0 | 0 | Project | init | Short Term Planning | Short Term Planning |  | 1773272 | 2807362.033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1773272 | 2807362.033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43281 | 43830 | False |  | False |  | False |  | False | False |  | False | False | True | False | TRUE | This is aligned with the overall IT strategy of moving away from custom/end-of-life platform into the new SAP mobility platform and achieve integration. | 0 | 0 | Asset Optimal
24750 | Bill Redesign OMA | N.D.M.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION |  |  |  | No |  |  |  |  | IT Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24751 | Telecom Infrastructure-Leaside x Downtown GTA | N.T.C.1.25 | 7700 | 203 | PROJECT DELIVERY | AIP006013 | AIP006013 | AIP006013 | No | AIP006013 | Telecom Infrastructure - Leaside x Downtown GTA Sites | 0 |  | Auxiliary Telecommunication Equipment | Miroslav.Kostic@HydroOne.com | Sheraz.Majid@HydroOne.com | System Renewal | 0 | 0 | 03 - None (default) | 0 | Project | DETL ACTN | Short Term Planning | Short Term Planning |  | 482246.6174 | 980463.7808 | 1487692.2716 | 499738.5597 | 0 | 0 | 0 | 0 | 0 | 0 | 507628.0183 | 1032067.1376 | 1565991.8648 | 526040.5892 | 0 | 0 | 0 | 0 | 0 | 0 | -25381.4009 | -51603.3569 | -78299.5932 | -26302.0295 | 0 | 0 | 0 | 0 | 0 | 0 | -5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43449 | 44553 | False |  | False |  | False |  | False | False |  | False | False | True | True | FALSE |  | 0 | 0 | Asset Optimal
24752 | Ctrl Room Windows 10 Computer Consoles -Dev Projet | N.C.C.3.01 | 4514 | 212 | INFO SOLUTIONS DIVISION | AIP000073 |  | AIP000073 | Yes | AIP000073 | Operating Hardware Refresh |  |  | Common Oper Infrast & Control Facilities | Godfrey.Holder@HydroOne.com | mallen@hydroone.com | General Plant | 0 | Not Required | 03 - None (default) | Not Required | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24753 | Basin TS A-12-BN ID32190 IESO BESS#1 | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP005760 |  | AIP005760 | Yes | AIP005760 | Placeholder for Upstream Tx Work for DG (Project) |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24754 | Basin TS A-12-BN ID32200 IESO BESS#2 | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP005760 |  | AIP005760 | Yes | AIP005760 | Placeholder for Upstream Tx Work for DG (Project) |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24755 | Third Party Studies & Estimates-SLU-Recoverable | N.T.M.1.14 | 7700 | 203 | PROJECT DELIVERY | AIP006137 | AIP006137 | AIP006137 | No | AIP006137 | 3rd Party Studies for SLU – Recoverable | 0 |  | Engineering and Environmental Support | Mike.Tanaskovic@HydroOne.com | Gian.Minichini@HydroOne.com | System O&M | 0 | 0 | 01 - Agreement (current/future) | 0 | Program | ACCP EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | 750000 | 750000 | 750000 | 750000 | 749999.88 | 750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -750000 | -750000 | -750000 | -750000 | -750000 | -749999.88 | -750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | True | Various Customer | False |  | True |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Intermediate
24756 | Physical Security Strategy | N.C.M.2.70 | 838 | 212 | INFO SOLUTIONS DIVISION | UNPLD |  |  | Yes |  |  |  |  | IT - Project & Architecture Services | lincoln.frost-hunt@hydroone.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24757 | New DESN in Northern York Region | N.T.C.2.11 | 7700 | 203 | PROJECT DELIVERY | AIP006068 | AIP006068 | AIP006068 | No | AIP006068 | New DESN in Northern York Region | 0 |  | Load Customer Connection | Robert.Reinmuller@HydroOne.com | E.Warren.King@HydroOne.com | System Access | Greater Toronto Area | 0 | 01 - Agreement (current/future) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 2000000 | 14300000.08 | 5500000 | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | 3000000 | 21450000 | 8250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -100000 | -1000000 | -7149999.92 | -2750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45778 | 46538 | True | Will be required to meet expected customer demand. | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | New DESN in Northern York Region
24758 | Pickering End of Commercial Operation | N.T.C.2.12 | 7700 | 203 | PROJECT DELIVERY | AIP006067 |  | AIP006067 | Yes | AIP006067 |  |  |  | Generator Customer Connection | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24759 | Proxy Server Hardware Refresh | N.C.C.3.01 | 4514 | 212 | INFO SOLUTIONS DIVISION | AIP000073 |  | AIP000073 | Yes | AIP000073 | Operating Hardware Refresh |  |  | Common Oper Infrast & Control Facilities | Godfrey.Holder@HydroOne.com | mallen@hydroone.com | General Plant | 0 | Not Required | 03 - None (default) | Not Required | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24760 | Ingersoll TS M46 ID33650 DX - Greenholm Farms -CA | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000191 |  | AIP000191 | Yes | AIP000191 | Small Embedded Generation | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 03 - None (default) | 0 | Project | EMPP ACTN | Executing | Executing | # of Gen Connections | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24761 | Ingersoll TS M46 ID33650 TX - Greenholm Farms | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000191 |  | AIP000191 | Yes | AIP000191 | Small Embedded Generation |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 03 - None (default) | 0 | Project | ACTN EMPP | Executing | Executing | # of Gen Connections | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24762 | Sidney TS-M1-Existing-Dx-Glen Miller CGS | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000195 |  | AIP000195 | Yes | AIP000195 | Small Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24763 | Sidney TS-M1-Existing-Tx-Glen Miller CGS | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24764 | Install DDRs for NERC Compliance | N.T.C.1.19 | 7700 | 203 | PROJECT DELIVERY | AIP006045 | AIP006045 | AIP006045 | No | AIP006045 | Install DDRs for NERC Compliance | 0 |  | Protection Control & Metering Equip | Miroslav.Kostic@HydroOne.com | Kunal.Gupta@HydroOne.com | System Renewal | 0 | 0 | 0 | 0 | Project | DETL ACTN | Short Term Planning | Short Term Planning |  | 994374.1789 | 1982038.1708 | 1965631.6844 | 1942016.4905 | 0 | 0 | 0 | 0 | 0 | 0 | 994374.1789 | 1982038.1708 | 1965631.6844 | 1942016.4905 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43315 | 44561 | False |  | True | NERC standard PRC-002-2 R5 | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Vulnerable
24765 | Stations Work Management & Mobility - OMA | N.C.M.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION | AIP006144 | AIP006144 | AIP006144 | No | AIP006144 | Stations Work Management & Mobility Ph2 - OMA | 0 |  | IT-Business Solution Development | jj.blais@HydroOne.com | Jun.Macabanti@hydroone.com | System O&M | 0 | 0 | 0 | 0 | Project | init | Short Term Planning | Short Term Planning |  | 88650 | 242399.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88650 | 242399.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43281 | 43830 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Vulnerable - Tx Contraint Reduction
24766 | J3E and J4E: Upgrade Thermal Rating | N.T.C.2.02 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Local Area Supply | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24767 | Little Long SS - Install 2nd Battery & Stn Service | N.T.C.2.02 | 7700 | 203 | PROJECT DELIVERY | AIP006052 | AIP006052 | AIP006052 | No | AIP006052 | Little Long Add 2nd Battery | 0 |  | Local Area Supply | Robert.Reinmuller@HydroOne.com | Kirpal.Bahra@HydroOne.com | System Service | 0 | 0 | 0 | 0 | Project | init | Short Term Planning | Short Term Planning |  | 196324.6873 | 1967511.2732 | 976345.648 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 196324.6873 | 1967511.2732 | 976345.648 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43496 | 43921 | False |  | True | Reliability Compliance requirement for Station Service | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Alternative 1
24768 | Dryden TS: Component Replacement | N.T.C.1.45 | 7700 | 203 | PROJECT DELIVERY |  |  |  | No |  |  |  |  | Northern Zone Station/Yard Investments | James.Mardegan@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24770 | Testing New900MHzTelecom Systems_DG Teleprotection | N.D.M.2.21 | 7792 | 213 | PLANNING | AIP005498 |  | AIP005498 | Yes | AIP005498 | RD&D Project - Grid Modernization and Energy Storage |  |  | Distribution RD&D | Daila.Dzintars@HydroOne.com | janet.eby@Hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24772 | M6E/M7E Sectionalizing Disconnect Switches | N.T.C.2.02 | 7700 | 203 | PROJECT DELIVERY | AIP006102 | AIP006102 | AIP006102 | No | AIP006102 | M6E/M7E Sectionalizing Disconnect Switches | SS-11 | Orillia TS: Install Sectionalizing Disconnect Switches on 230kV Circuits | Local Area Supply | Robert.Reinmuller@HydroOne.com | Alexander.Constantinescu@HydroOne.com | System Service | 0 | Not Required | 0 | Not Required | Project | DETL ACTN | Short Term Planning | Short Term Planning |  | 294487.0309 | 1967511.2732 | 4393555.4158 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 294487.0309 | 1967511.2732 | 4393555.4158 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43434 | 44162 | False |  | True | IESO Ontario Resource and Transmission Assessment Criteria | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Motorized Disconnect Switches on M6E/M7E
24773 | Kleinburg Coverall Enclosure | N.C.C.1.50 | 7226 | 209 | HEALTH, SAFETY & ENV |  |  |  | No |  |  |  |  | Real Estate Facilities | cindy.copp@hydroone.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24774 | Cooksville Microwave Replacement | N.T.C.1.25 | 7700 | 203 | PROJECT DELIVERY | AIP006051 | AIP006051 | AIP006051 | No | AIP006051 | Cooskville Microwave Replacement | 0 |  | Auxiliary Telecommunication Equipment | Miroslav.Kostic@HydroOne.com | Sheraz.Majid@HydroOne.com | System Renewal | 0 | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 490231.8904 | 991794.8084 | 999476.8864 | 503535.7157 | 0 | 0 | 0 | 0 | 0 | 0 | 516033.5688 | 1043994.5352 | 1052080.9331 | 530037.5955 | 0 | 0 | 0 | 0 | 0 | 0 | -25801.6784 | -52199.7268 | -52604.0467 | -26501.8798 | 0 | 0 | 0 | 0 | 0 | -5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43770 | 44917 | False |  | False |  | False |  | True | False |  | False | False | False | False | FALSE |  | 0 | 0 | Asset Optimal
24775 | Longueuil TS: T3/T4 Replacement | N.T.C.1.44 | 7700 | 203 | PROJECT DELIVERY | AIP006152 | AIP006152 | AIP006152 | No | AIP006152 | Longueil TS T3/T4 replacement | SR-05 | Load Station Transformer Replacement Projects | Eastern Zone Station/Yard Investments | James.Mardegan@HydroOne.com | Fred.Kouhdani@HydroOne.com | System Renewal | 0 | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 57345.1608 | 1035596.5353 | 1851930.2492 | 5970003.4411 | 5627533.6939 | 1522273.24 | 0 | 0 | 0 | 0 | 61661.4633 | 1113544.6616 | 1991322.8486 | 6419358.5388 | 6051111.4988 | 1636852.98 | 0 | 0 | 0 | 0 | -4316.3024 | -77948.1263 | -139392.5994 | -449355.0977 | -423577.8049 | -114579.74 | 0 | 0 | 0 | -7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44355 | 45626 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Alternative 1
24776 | Arnprior TS: Station Refurbishment | N.T.C.1.44 | 7700 | 203 | PROJECT DELIVERY | UNPLANNED |  |  | Yes |  |  |  |  | Eastern Zone Station/Yard Investments | James.Mardegan@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24778 | Overbrook TS: Metalclad & Component Replacement | N.T.C.1.44 | 7700 | 203 | PROJECT DELIVERY | AIP006148 | AIP006148 | AIP006148 | No | AIP006148 | Overbrook TS Metalclad replacement | 0 |  | Eastern Zone Station/Yard Investments | James.Mardegan@HydroOne.com | Fred.Kouhdani@HydroOne.com | System Renewal | 0 | 0 | 03 - None (default) | 0 | Project | AWRD DETL | Short Term Planning | Short Term Planning |  | 1043157.1281 | 926344.906 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1121674.3313 | 996069.7913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -78517.2032 | -69724.8854 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43418 | 43830 | False |  | True | NFPA 70 compliance | False |  | False | True | Hydro Ottawa is planning to replace thier cells within the same line up | False | False | True | False | FALSE |  | 0 | 0 | Alternative 1
24779 | Crosby TS T3 & Component Replacement | N.T.C.1.44 | 7700 | 203 | PROJECT DELIVERY | AIP006146 | AIP006146 | AIP006146 | No | AIP006146 | Crosby TS T3 and Component Replacement | 0 |  | Eastern Zone Station/Yard Investments | James.Mardegan@HydroOne.com | Fred.Kouhdani@HydroOne.com | System Renewal | 0 | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 264165.1015 | 869874.4144 | 1629217.7488 | 7068000.04 | 2790000 | 0 | 0 | 0 | 0 | 0 | 284048.4963 | 935348.8327 | 1751847.0417 | 7600000 | 3000000 | 0 | 0 | 0 | 0 | 0 | -19883.3947 | -65474.4183 | -122629.2929 | -531999.96 | -210000 | 0 | 0 | -7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45055 | 45991 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Alternative 1
24780 | Wallace TS T3/T4 & Component Replacement | N.T.C.1.44 | 7700 | 203 | PROJECT DELIVERY | AIP006157 | AIP006157 | AIP006157 | No | AIP006157 | Wallace TS T3 T4 and Component Replacement | SR-05 | Load Station Transformer Replacement Projects | Eastern Zone Station/Yard Investments | James.Mardegan@HydroOne.com | Fred.Kouhdani@HydroOne.com | System Renewal | 0 | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 920884.2275 | 1145155.7183 | 7891751.1736 | 7859624.1406 | 2177037.12 | 0 | 0 | 0 | 0 | 0 | 990198.0941 | 1231350.2347 | 8485753.9501 | 8451208.7533 | 2340900.12 | 0 | 0 | 0 | 0 | 0 | -69313.8666 | -86194.5164 | -594002.7765 | -591584.6127 | -163863 | 0 | 0 | 0 | -7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44680 | 45414 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Alternative 1 (modified)
24781 | Slater TS T1/T2/T3 & Component Replacement | N.T.C.1.44 | 7700 | 203 | PROJECT DELIVERY | AIP006143 | AIP006143 | AIP006143 | No | AIP006143 | Slater TS T1/T2/T3 and component replacement | SR-02 | Station Reinvestment Projects | Eastern Zone Station/Yard Investments | James.Mardegan@HydroOne.com | Fred.Kouhdani@HydroOne.com | System Renewal | 0 | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 250357.7194 | 689081.537 | 2241491.2436 | 14783322.1291 | 5729665.0722 | 0 | 0 | 0 | 0 | 0 | 269201.8488 | 740947.8892 | 2410205.6382 | 15896045.3001 | 6160930.1851 | 0 | 0 | 0 | 0 | 0 | -18844.1294 | -51866.3522 | -168714.3947 | -1112723.171 | -431265.113 | 0 | 0 | 0 | 0 | 0 | -7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43880 | 44925 | True | station cant operate fully loaded due to derate transformers, HOL requested to have full loading of station | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Alternative 1
24783 | MetroLinx City View Traction Substation Connection | N.T.C.2.11 | 7700 | 203 | PROJECT DELIVERY | AIP006060 | AIP006060 | AIP006060 | No | AIP006060 | MetroLinx Cityview Traction Station Connection | SA-08 | Connect Metrolinx Traction Substations | Load Customer Connection | Robert.Reinmuller@HydroOne.com | chester.li@HydroOne.com | System Access | Greater Toronto Area | Not Required | 01 - Agreement (current/future) | In Progress | Project | ACTN DETL | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 300000 | 2000000 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -200000 | -300000 | -2000000 | -500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43555 | 44286 | True | Metrolinx request | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Alternative 1
24784 | MetroLinx Mimico Traction Substation Connection | N.T.C.2.11 | 7700 | 203 | PROJECT DELIVERY | AIP006061 | AIP006061 | AIP006061 | No | AIP006061 | MetroLinx Mimico Traction Station Connection | SA-08 | Connect Metrolinx Traction Substations | Load Customer Connection | Robert.Reinmuller@HydroOne.com | chester.li@HydroOne.com | System Access | Greater Toronto Area | Not Required | 0 | In Progress | Project | DETL ACTN | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 1500000 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -400000 | -1500000 | -1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43475 | 43921 | True | Metrolinx Request | True | Transmission license requirement to connect customers. | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Alternative 1
24785 | Kirkland Lake TS: Component Replacement | N.T.C.1.45 | 7700 | 203 | PROJECT DELIVERY | AIP006055 | AIP006055 | AIP006055 | No | AIP006055 | Kirkland Lake TS: Component Replacement | SR-06 | Load Station Switchgear and Ancillary Equipment Replacement Projects | Northern Zone Station/Yard Investments | James.Mardegan@HydroOne.com | Donald.Mastrangelo@HydroOne.com | System Renewal | Northern | Not Required | 03 - None (default) | Not Required | Project | AWRD BEST | Short Term Planning | Short Term Planning |  | 915954.5884 | 897643.4869 | 6154698.8529 | 3542463.6446 | 470101.684 | 0 | 0 | 0 | 0 | 0 | 984897.4069 | 965208.0505 | 6617955.7558 | 3809100.6932 | 505485.6817 | 0 | 0 | 0 | 0 | 0 | -68942.8185 | -67564.5635 | -463256.9029 | -266637.0485 | -35383.9977 | 0 | 0 | 0 | 0 | 0 | -7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43683 | 44620 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Kirkland Lake TS: Component Replacement
24786 | Muskoka TS: Component Replacement | N.T.C.1.45 | 7700 | 203 | PROJECT DELIVERY | AIP006056 | AIP006056 | AIP006056 | No | AIP006056 | Muskoka TS: Component Replacement | SR-06 | Load Station Switchgear and Ancillary Equipment Replacement Projects | Northern Zone Station/Yard Investments | James.Mardegan@HydroOne.com | Donald.Mastrangelo@HydroOne.com | System Renewal | Northern | Not Required | 03 - None (default) | Not Required | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 254800.5281 | 856755.3236 | 1036338.7828 | 3171453.4172 | 1253248.88 | 0 | 0 | 0 | 0 | 0 | 273979.0624 | 921242.2835 | 1114342.7773 | 3410164.9648 | 1347579.44 | 0 | 0 | 0 | 0 | 0 | -19178.5344 | -64486.9598 | -78003.9944 | -238711.5475 | -94330.56 | 0 | 0 | 0 | -7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44534 | 45594 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Muskoka TS: Component Replacement
24787 | Pinard TS: Component Replacement | N.T.C.1.45 | 7700 | 203 | PROJECT DELIVERY |  |  |  | No |  |  |  |  | Northern Zone Station/Yard Investments | James.Mardegan@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24788 | Porcupine TS: Component Replacement | N.T.C.1.45 | 7700 | 203 | PROJECT DELIVERY | AIP006058 | AIP006058 | AIP006058 | No | AIP006058 | Porcupine TS: Component Replacement | SR-03 | Bulk Station Transformer Replacement Projects | Northern Zone Station/Yard Investments | James.Mardegan@HydroOne.com | Donald.Mastrangelo@HydroOne.com | System Renewal | 0 | Not Required | 03 - None (default) | Required | Project | init | Short Term Planning | Short Term Planning |  | 233462.0011 | 486032.1219 | 1313491.3324 | 8279423.6723 | 17728314.7718 | 12582386.7611 | 13919403.48 | 11832038.4 | 0 | 0 | 251034.4098 | 522615.1848 | 1412356.2714 | 8902606.0993 | 19062704.0557 | 13529448.1302 | 14967100.56 | 12722621.88 | 0 | 0 | -17572.4087 | -36583.0629 | -98864.939 | -623182.4269 | -1334389.2839 | -947061.3691 | -1047697.08 | -890583.48 | 0 | 0 | -7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43956 | 45960 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Reconfig
24789 | Spruce Falls TS: Component Replacement | N.T.C.1.45 | 7700 | 203 | PROJECT DELIVERY | AIP006059 | AIP006059 | AIP006059 | No | AIP006059 | Spruce Falls TS: Component Replacement | 0 |  | Northern Zone Station/Yard Investments | James.Mardegan@HydroOne.com | Donald.Mastrangelo@HydroOne.com | System Renewal | 0 | Not Required | 03 - None (default) | Not Required | Project | init | Short Term Planning | Short Term Planning |  | 276916.5008 | 780959.1663 | 1410334.351 | 1550364.4335 | 0 | 0 | 0 | 0 | 0 | 0 | 297759.6782 | 839741.0391 | 1516488.5495 | 1667058.5306 | 0 | 0 | 0 | 0 | 0 | 0 | -20843.1775 | -58781.8727 | -106154.1985 | -116694.0971 | 0 | 0 | 0 | 0 | 0 | 0 | -7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43715 | 44423 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Spruce Falls TS: Component Replacement
24790 | Dufferin TS: Revenue Metering Upgrade | N.T.C.2.11 | 7700 | 203 | PROJECT DELIVERY | AIP006073 | AIP006073 | AIP006073 | No | AIP006073 | Dufferin TS: Revenue Metering Upgrade | 0 |  | Load Customer Connection | Robert.Reinmuller@HydroOne.com | Lukito.Adiputra@HydroOne.com | System Access | 0 | 0 | 03 - None (default) | 0 | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 900000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -900000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43012 | 0 | True | Toronto Hydro | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Dufferin TS: Revenue Metering Upgrade
24791 | Nanticoke TS T12 & Component Replacement | N.T.C.1.46 | 7700 | 203 | PROJECT DELIVERY | AIP006261 | AIP006261 | AIP006261 | No | AIP006261 | Nanticoke 750MVA Autotransformer Replacement - T12 | 0 |  | Tx Station Demand and Spares | James.Mardegan@HydroOne.com | Fred.Kouhdani@HydroOne.com | System Renewal | Hamilton Niagara | 0 | 0 | 0 | Project | EMPP ACCP | Executing | Executing |  | 18495359.6969 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19887483.5451 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1392123.8482 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42934 | 43449 | False |  | False |  | False |  | True | False |  | False | False | False | False | FALSE |  | 0 | 0 | Alternative 1
24792 | Connect X21/X22 to Belleville | N.T.C.2.03 | 7700 | 203 | PROJECT DELIVERY |  |  |  | No |  |  |  |  | Network Transfer Capability | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24793 | Connect C27P to Chenaux | N.T.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP006083 | AIP006083 | AIP006083 | No | AIP006083 | Connect X21/X22 to Belleville | 0 |  | Network Transfer Capability | Robert.Reinmuller@HydroOne.com | Quyen.Diep@HydroOne.com | System Service | Eastern | TBD | 03 - None (default) | TBD | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 480790.9448 | 1429889.2688 | 189421.5773 | 9800000 | 30000000 | 13000000 | 0 | 0 | 0 | 0 | 480790.9448 | 1429889.2688 | 189421.5773 | 9800000 | 30000000 | 13000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45261 | 46357 | False |  | True | IESO Ontario Resource and Transmission Assessment Criteria | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Connect from Napanee TS to Belleville TS
24794 | Duplex TS: Revenue Metering Upgrade | N.T.C.2.11 | 7700 | 203 | PROJECT DELIVERY | AIP006092 | AIP006092 | AIP006092 | No | AIP006092 | Duplex TS: Revenue Metering Upgrade | 0 |  | Load Customer Connection | Robert.Reinmuller@HydroOne.com | Lukito.Adiputra@HydroOne.com | System Access | 0 | 0 | 03 - None (default) | 0 | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 900000 | 900000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -900000 | -900000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | True | Toronto Hydro | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Duplex TS: Revenue Metering Upgrade
24795 | MetroLinx Burlington Traction Substation Connectio | N.T.C.2.11 | 7700 | 203 | PROJECT DELIVERY | AIP006063 | AIP006063 | AIP006063 | No | AIP006063 | MetroLinx Burlington Traction Station Connection | SA-08 | Connect Metrolinx Traction Substations | Load Customer Connection | Robert.Reinmuller@HydroOne.com | chester.li@HydroOne.com | System Access | Hamilton Niagara | Not Required | 01 - Agreement (current/future) | In Progress | Project | ACTN DETL | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 200000 | 2600000 | 500000.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -200000 | -200000 | -2600000 | -500000.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43921 | 44651 | True | Metrolinx Request | True | Transmission license requirement to connect customers | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Alternative 1
24796 | MetroLinx Scarborough Traction Station Connection | N.T.C.2.11 | 7700 | 203 | PROJECT DELIVERY | AIP006064 | AIP006064 | AIP006064 | No | AIP006064 | MetroLinx Scarborough Traction Station Connection | SA-08 | Connect Metrolinx Traction Substations | Load Customer Connection | Robert.Reinmuller@HydroOne.com | chester.li@HydroOne.com | System Access | Greater Toronto Area | Not Required | 01 - Agreement (current/future) | In Progress | Project | DETL ACTN | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 200000 | 1500000 | 1400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -200000 | -200000 | -1500000 | -1400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43921 | 45016 | True | Metrolinx Request | True | Transmission license requirement to connect customers | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Alternative 1
24797 | MetroLinx ERMF Traction Substation Connection | N.T.C.2.11 | 7700 | 203 | PROJECT DELIVERY | AIP006065 | AIP006065 | AIP006065 | No | AIP006065 | MetroLinx ERMF Traction Station Connection | SA-08 | Connect Metrolinx Traction Substations | Load Customer Connection | Robert.Reinmuller@HydroOne.com | chester.li@HydroOne.com | System Access | Greater Toronto Area | Not Required | 01 - Agreement (current/future) | In Progress | Project | DETL ACTN | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 200000 | 2400000 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -200000 | -200000 | -2400000 | -500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43921 | 45016 | True | Metrolinx request | True | Transmission license requirement | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Alternative 1
24798 | MetroLinx Allandale Traction Substation Connection | N.T.C.2.11 | 7700 | 203 | PROJECT DELIVERY | AIP006066 | AIP006066 | AIP006066 | No | AIP006066 | MetroLinx Allandale Traction Station Connection | SA-08 | Connect Metrolinx Traction Substations | Load Customer Connection | Robert.Reinmuller@HydroOne.com | chester.li@HydroOne.com | System Access | Central | Not Required | 01 - Agreement (current/future) | In Progress | Project | ACTN DETL | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 1700000 | 2800000 | 700000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -200000 | -1700000 | -2800000 | -700000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43921 | 44651 | True | Metrolinx request | True | Transmission license requirement to connect customers. | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Alternative 1
24799 | Wendover DS F3 ID32020 DX Pendleton Solar Energy C | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000199 |  | AIP000199 | Yes | AIP000199 | Large Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24800 | VMware Server Refresh | N.C.C.3.01 | 4514 | 212 | INFO SOLUTIONS DIVISION | AIP000073 |  | AIP000073 | Yes | AIP000073 | Operating Hardware Refresh |  |  | Common Oper Infrast & Control Facilities | Godfrey.Holder@HydroOne.com | mallen@hydroone.com | General Plant | 0 | Not Required | 03 - None (default) | Not Required | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24801 | Malden TS: Add Two New 27.6 kV Feeders | N.T.C.2.11 | 7700 | 203 | PROJECT DELIVERY | AIP006069 | AIP006069 | AIP006069 | No | AIP006069 | Malden TS: Add Two New 27.6 kV Feeders | 0 |  | Load Customer Connection | Robert.Reinmuller@HydroOne.com | Emeka.Okongwu@HydroOne.com | System Access | Western | Not Required | 01 - Agreement (current/future) | Not Required | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 600000 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -100000 | -600000 | -500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43952 | 44347 | True | Essex Power | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Alternative 1
24802 | Strachan TS: Revenue Metering Upgrade | N.T.C.2.11 | 7700 | 203 | PROJECT DELIVERY | AIP006088 | AIP006088 | AIP006088 | No | AIP006088 | Strachan TS: Revenue Metering Upgrade | 0 |  | Load Customer Connection | Robert.Reinmuller@HydroOne.com | Lukito.Adiputra@HydroOne.com | System Access | 0 | 0 | 03 - None (default) | 0 | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600000 | 600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -600000 | -600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | True | Toronto Hydro | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Strachan TS: Revenue Metering Upgrade
24803 | John TS: Revenue Metering Upgrade | N.T.C.2.11 | 7700 | 203 | PROJECT DELIVERY | AIP006089 | AIP006089 | AIP006089 | No | AIP006089 | John TS: Revenue Metering Upgrade | 0 |  | Load Customer Connection | Robert.Reinmuller@HydroOne.com | Lukito.Adiputra@HydroOne.com | System Access | 0 | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2400000 | 2400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2400000 | -2400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | True | Toronto Hydro | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | John TS: Revenue Metering Upgrade
24804 | Charles TS: Revenue Metering Upgrade | N.T.C.2.11 | 7700 | 203 | PROJECT DELIVERY | AIP006090 | AIP006090 | AIP006090 | No | AIP006090 | Charles TS: Revenue Metering Upgrade | 0 |  | Load Customer Connection | Robert.Reinmuller@HydroOne.com | Lukito.Adiputra@HydroOne.com | System Access | 0 | 0 | 03 - None (default) | 0 | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200000 | 1200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1200000 | -1200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | True | Toronto Hydro | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Charles TS: Revenue Metering Upgrade
24805 | Wendover DS F3 ID32020 TX Pendleton Solar Energy C | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP005760 |  | AIP005760 | Yes | AIP005760 | Placeholder for Upstream Tx Work for DG (Project) |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24806 | S4 HANA (EAM) | N.C.C.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION |  |  |  | No |  |  |  |  | IT Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24807 | S4 HANA (EAM) | N.D.M.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION |  |  |  | No |  |  |  |  | IT Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24808 | Norfolk-Ireland DS F1 line rebuild Oakwood Ave | N.D.C.1.07 | 7374 | 205 | LINES | UNPLND |  |  | Yes |  |  |  |  | Lines | emre.aydin@HydroOne.com | [6 empty] | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24809 | King Edward TS: Upgrade metalclad | N.T.C.2.11 | 7700 | 203 | PROJECT DELIVERY | AIP006072 | AIP006072 | AIP006072 | No | AIP006072 | King Edward TS: Upgrade metalclad | 0 |  | Load Customer Connection | Robert.Reinmuller@HydroOne.com | Jean.Morneau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 98162.3436 | 491877.8183 | 2733767.7752 | 2692429.2909 | 1715867.1225 | 0 | 0 | 0 | 0 | 0 | 98162.3436 | 491877.8183 | 2733767.7752 | 2692429.2909 | 1715867.1225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44012 | 44712 | True | Work requested by Hydro Ottawa. | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Alternative 1
24810 | Orleans TS: Provide second 230kV supply | N.T.C.2.02 | 7700 | 203 | PROJECT DELIVERY | AIP006071 | AIP006071 | AIP006071 | No | AIP006071 | Orleans TS: Provide second 230kV supply | 0 |  | Local Area Supply | Robert.Reinmuller@HydroOne.com | Jean.Morneau@HydroOne.com | System Service | 0 | 0 | 02 - Expectation (no agreement) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 238314.8781 | 710330.8012 | 750000 | 250000 | 8000000.04 | 6000000 | 0 | 0 | 0 | 0 | 238314.8781 | 710330.8012 | 750000 | 250000 | 8000000.04 | 6000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46204 | 46904 | False |  | True | Investment needed to meet load supply security requirements in IESO's Ontario Resource and Transmission Assessment Critieria. | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Alternative 1
24811 | Tremaine TS - Add Four 27.6kV Feeders | N.T.C.2.11 | 7700 | 203 | PROJECT DELIVERY | AIP006062 |  | AIP006062 | Yes | AIP006062 |  |  |  | Load Customer Connection | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24812 | Pleasant TS - 42M1 Feeder Position | N.T.C.2.11 | 7700 | 203 | PROJECT DELIVERY | AIP006070 |  | AIP006070 | Yes | AIP006070 |  |  |  | Load Customer Connection | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24813 | EPRI TX Rate Filing Support 2018 | N.T.M.2.21 | 4048 | 213 | PLANNING | UNPLND |  |  | Yes |  |  |  |  | Technology Program | Daila.Dzintars@HydroOne.com | [6 empty] | Project | EMPP init | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24814 | Terauley A5-A6 M/C Replacement | N.T.C.1.43 | 7700 | 203 | PROJECT DELIVERY |  |  |  | No |  |  |  |  | Greater Toronto Area Zone Station/Yard Investments | James.Mardegan@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24815 | Terauley TS: Revenue Metering Upgrade | N.T.C.2.11 | 7700 | 203 | PROJECT DELIVERY | AIP006091 | AIP006091 | AIP006091 | No | AIP006091 | Terauley TS: Revenue Metering Upgrade | 0 |  | Load Customer Connection | Robert.Reinmuller@HydroOne.com | Lukito.Adiputra@HydroOne.com | System Access | 0 | 0 | 03 - None (default) | 0 | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200000 | 1200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1200000 | -1200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | True | Toronto Hydro | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Terauley TS: Revenue Metering Upgrade
24816 | Back Office Associates Data Migration Accelerator | N.D.M.9.01 | 4465 | 216 | BUSINESS INTEGRATION | UNPLND |  |  | Yes | [12 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24817 | Infobase / NAMCIS Replacement | N.C.C.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION |  |  |  | No |  |  |  |  | IT Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24818 | Infobase / NAMCIS Replacement | N.D.M.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION |  |  |  | No |  |  |  |  | IT Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24819 | HL3/HL4 Cable Replacement | N.T.C.2.02 | 7700 | 203 | PROJECT DELIVERY | AIP006079 | AIP006079 | AIP006079 | No | AIP006079 | HL3/HL4 Cable Replacement | 0 |  | Local Area Supply | Robert.Reinmuller@HydroOne.com | Khurram.Makhdoom@HydroOne.com | System Service | Hamilton Niagara | Not Required | 03 - None (default) | Required | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 190651.9025 | 1704794.1955 | 12400000 | 3600000 | 0 | 0 | 0 | 0 | 0 | 0 | 190651.9025 | 1704794.1955 | 12400000 | 3600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45033 | 45808 | False |  | True | ORTAC-restoration | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | HL3/HL4 Cable Replacement
24820 | Connect C28C to Dobbin | N.T.C.2.03 | 7700 | 203 | PROJECT DELIVERY |  |  |  | No |  |  |  |  | Network Transfer Capability | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24822 | K2M Protection Modification for Kenora CGS Upgrade | N.T.C.2.12 | 7700 | 203 | PROJECT DELIVERY | AIP006076 | AIP006076 | AIP006076 | No | AIP006076 | K2M Protection Modification for Kenora CGS Upgrade | 0 |  | Generator Customer Connection | Robert.Reinmuller@HydroOne.com | Hamid.Hamadanizadeh@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 360000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -360000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43220 | 43435 | True | H2O is upgrading Kenora CGS. It requires K2M Protection upgrade. | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | K2M Protection Modification
24825 | Cecil A1-A2 M/C Replacement | N.T.C.1.43 | 7700 | 203 | PROJECT DELIVERY |  |  |  | No |  |  |  |  | Greater Toronto Area Zone Station/Yard Investments | James.Mardegan@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24826 | Duplex A3-A4 M/C Replacement | N.T.C.1.43 | 7700 | 203 | PROJECT DELIVERY |  |  |  | No |  |  |  |  | Greater Toronto Area Zone Station/Yard Investments | James.Mardegan@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24827 | Beaverton TS: Component Replacements | N.T.C.1.42 | 7700 | 203 | PROJECT DELIVERY | AIP005184 | AIP005184 | AIP005184 | No | AIP005184 | Beaverton TS: Component Replacements | 0 |  | Central Zone Station/Yard Investments | James.Mardegan@HydroOne.com | michael.xavier@hydroone.com | System Renewal | Central | Not Required | 03 - None (default) | TBD | Project | init | Short Term Planning | Short Term Planning |  | 0 | 970456.5302 | 179582.5087 | 838627.9918 | 576811.9283 | 103427.3597 | 0 | 0 | 0 | 0 | 0 | 1043501.6454 | 193099.4717 | 901750.5288 | 620227.8799 | 111212.2147 | 0 | 0 | 0 | 0 | 0 | -73045.1152 | -13516.963 | -63122.537 | -43415.9516 | -7784.855 | 0 | 0 | 0 | 0 | -7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43922 | 45010 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Component Replacement
24828 | Milton SS: Component Replacements | N.T.C.1.43 | 7700 | 203 | PROJECT DELIVERY | AIP005198 | AIP005198 | AIP005198 | No | AIP005198 | Milton SS: Component Replacements | SR-04 | Bulk Station Switchgear and Ancillary Equipment Replacement Projects | Greater Toronto Area Zone Station/Yard Investments | James.Mardegan@HydroOne.com | michael.xavier@hydroone.com | System Renewal | Greater Toronto Area | Not Required | 03 - None (default) | TBD | Project | init | Short Term Planning | Short Term Planning |  | 0 | 749898.1813 | 809531.8933 | 4370596.8773 | 5284558.715 | 1476016.2574 | 0 | 0 | 0 | 0 | 0 | 806342.1304 | 870464.4014 | 4699566.5347 | 5682321.199 | 1587114.2553 | 0 | 0 | 0 | 0 | 0 | -56443.9491 | -60932.5081 | -328969.6574 | -397762.4839 | -111097.9979 | 0 | 0 | 0 | 0 | -7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44146 | 45098 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Component Replacement
24829 | Bowmanville SS: Component Replacement | N.T.C.1.42 | 7700 | 203 | PROJECT DELIVERY |  |  |  | No |  |  |  |  | Central Zone Station/Yard Investments | James.Mardegan@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24830 | Kenilworth TS: Install 13.8kV Capacitor Breaker | N.T.C.2.11 | 7700 | 203 | PROJECT DELIVERY | AIP006080 | AIP006080 | AIP006080 | No | AIP006080 | Kenilworth TS: Add New 13.8 kV Breaker | 0 |  | Load Customer Connection | Robert.Reinmuller@HydroOne.com | Khurram.Makhdoom@HydroOne.com | System Access | Hamilton Niagara | Not Required | 01 - Agreement (current/future) | Not Required | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 900000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -100000 | -900000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43434 | 43798 | True | Alectra Request | True | Transmission license requirement to connect customer. | False |  | True | False |  | False | False | False | False | FALSE |  | 0 | 0 | Kenilworth TS: Add New 13.8 kV Breaker
24831 | Norfolk TS: Install Capacitor Bank | N.T.C.2.11 | 7700 | 203 | PROJECT DELIVERY | AIP006081 | AIP006081 | AIP006081 | No | AIP006081 | Norfolk TS: Add LV Capacitor Bank | 0 |  | Load Customer Connection | Robert.Reinmuller@HydroOne.com | Khurram.Makhdoom@HydroOne.com | System Access | Hamilton Niagara | Not Required | 03 - None (default) | Not Required | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 48817.2824 | 336553.6614 | 953259.5125 | 568264.7318 | 0 | 0 | 0 | 0 | 0 | 0 | 48817.2824 | 336553.6614 | 953259.5125 | 568264.7318 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44347 | 45077 | False |  | True | ORTAC | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Norfolk TS: Install Capacitor Bank
24832 | BasinTS: New Ashbridge Bay Generation | N.T.C.2.12 | 7700 | 203 | PROJECT DELIVERY | AIP006085 | AIP006085 | AIP006085 | No | AIP006085 | Basin TS: Connect New Ashbridge's Bay Generation | 0 |  | Generator Customer Connection | Robert.Reinmuller@HydroOne.com | Khurram.Makhdoom@HydroOne.com | System Access | Hamilton Niagara | Not Required | 01 - Agreement (current/future) | Not Required | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43527 | 43801 | True | Customer Request | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Basin TS: Connect New Ashbridge's Bay Generation
24835 | Basin TS: Open A7/A8 Bus Tie | N.T.C.2.11 | 7700 | 203 | PROJECT DELIVERY |  | AIP006087 |  | Yes | AIP006087 | Brantford TS: New Breaker Positions | 0 |  | Load Customer Connection | Robert.Reinmuller@HydroOne.com | Khurram.Makhdoom@HydroOne.com | System Access | Hamilton Niagara | Not Required | 01 - Agreement (current/future) | Not Required | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 1900000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -100000 | -1900000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43434 | 43798 | True | Energy One Request | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Brantford TS: New Breaker Positions
24836 | Extend H82V/H83V to Kleinburg TS | N.T.C.2.02 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Local Area Supply | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24837 | Telecom Infrastructure-Wiltshire x Bridgeman | N.T.C.1.25 | 7700 | 203 | PROJECT DELIVERY | AIP006075 | AIP006075 | AIP006075 | No | AIP006075 | Telecom Infrastrucutre - Wiltshire x Bridgeman | 0 |  | Auxiliary Telecommunication Equipment | Miroslav.Kostic@HydroOne.com | Sheraz.Majid@HydroOne.com | System Renewal | 0 | 0 | 03 - None (default) | 0 | Project | ACTN DETL | Short Term Planning | Short Term Planning |  | 243661.4488 | 990784.4517 | 501117.2767 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 253814.0092 | 1032067.1372 | 521997.1633 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -10152.5604 | -41282.6855 | -20879.8865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43419 | 44034 | False |  | False |  | False |  | False | False |  | False | False | True | True | FALSE |  | 0 | 0 | Asset Optimal
24838 | Telecom Infrastructure-GTA Downtown Fiber Install | N.T.C.1.25 | 7700 | 203 | PROJECT DELIVERY | AIP006077 | AIP006077 | AIP006077 | No | AIP006077 | Telecom Infrastructure - GTA Downtown Fiber Installations | 0 |  | Auxiliary Telecommunication Equipment | Miroslav.Kostic@HydroOne.com | Sheraz.Majid@HydroOne.com | System Renewal | 0 | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 241123.3087 | 735347.7761 | 743846.0178 | 249869.2022 | 0 | 0 | 0 | 0 | 0 | 0 | 253814.0092 | 774050.2906 | 782995.8083 | 263020.2128 | 0 | 0 | 0 | 0 | 0 | 0 | -12690.7005 | -38702.5145 | -39149.7904 | -13151.0106 | 0 | 0 | 0 | 0 | 0 | 0 | -5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43449 | 44553 | False |  | False |  | False |  | False | False |  | False | False | True | True | FALSE |  | 0 | 0 | Asset Optimal
24840 | Mock Audit Remediation | N.T.M.1.29 | 838 | 212 | INFO SOLUTIONS DIVISION | UNPLND |  |  | Yes |  |  |  |  | NERC Cyber Security Compliance Readiness | lincoln.frost-hunt@hydroone.com | [6 empty] | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24841 | Copeland MTS Phase 2 Connection | N.T.C.2.11 | 7700 | 203 | PROJECT DELIVERY | AIP006084 | AIP006084 | AIP006084 | No | AIP006084 | Copeland MTS Phase 2 Connection | 0 |  | Load Customer Connection | Robert.Reinmuller@HydroOne.com | Eva.Ping@HydroOne.com | System Access | Greater Toronto Area | 0 | 01 - Agreement (current/future) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 1000000 | 600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -400000 | -1000000 | -600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43921 | 44347 | True |  | True | Electricity Transmission License. ET-2003-0035. Section 8. | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Copeland MTS Phase 2 Connection
24845 | Basin TS Expansion | N.T.C.2.11 | 7700 | 203 | PROJECT DELIVERY | AIP006093 | AIP006093 | AIP006093 | No | AIP006093 | Basin TS Expansion | 0 |  | Load Customer Connection | Robert.Reinmuller@HydroOne.com | Eva.Ping@HydroOne.com | System Access | Greater Toronto Area | 0 | 01 - Agreement (current/future) | Required | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 500000 | 10000000 | 14999999.88 | 9400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -100000 | -500000 | -10000000 | -14999999.88 | -9400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45442 | 46173 | True |  | True | Transmission License ET-2003-0035, Section 8 | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Basin TS Expansion
24846 | Esplanade TS to Don Fleet Jct 115kV TX Upgrade | N.T.C.2.02 | 7700 | 203 | PROJECT DELIVERY |  |  |  | No |  |  |  |  | Local Area Supply | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24847 | Bridgman Jct - Replace Two Air Break Switches | N.T.C.2.21 | 7700 | 203 | PROJECT DELIVERY | AIP006107 | AIP006107 | AIP006107 | No | AIP006107 | Bridgman Jct - Replace Two Air Break Switches | 0 |  | Major Risk Mitigation | Robert.Reinmuller@HydroOne.com | Eva.Ping@HydroOne.com | System Service | 0 | 0 | 03 - None (default) | 0 | Project | DETL ACTN | Short Term Planning | Short Term Planning |  | 981623.4363 | 442690.0365 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 981623.4363 | 442690.0365 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43311 | 43616 | False |  | False |  | False |  | True | False |  | False | True | False | False | FALSE |  | 0 | 0 | Bridgman Jct - Replace Two Air Break Switches
24850 | Georgia Pacific CTS Disconnection | N.T.C.2.11 | 7370 | 206 | TX LINES AND STATIONS | UNPLND |  |  | Yes |  |  |  |  | Load Customer Connection | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | EMPP ACTN | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24851 | Watay Red Lake Connection | N.T.C.2.11 | 7700 | 203 | PROJECT DELIVERY | AIP006094 | AIP006094 | AIP006094 | No | AIP006094 | Watay Red Lake Connection | 0 |  | Load Customer Connection | Robert.Reinmuller@HydroOne.com | Hamid.Hamadanizadeh@HydroOne.com | System Access | Northern | 0 | 0 | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 1000000.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -100000 | -1000000.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43715 | 45199 | True | Watay asks HONI to connect the Remotes to the grid | False |  | False | Government issued OiC for connection of Remotes. | False | False |  | True | False | False | False | FALSE |  | 0 | 0 | Connect Watay 115 kV line to E2R
24852 | Richview Manby Transmission Reinforcement -Station | N.T.C.2.02 | 7700 | 203 | PROJECT DELIVERY | AIP006111 | AIP006111 | AIP006111 | No | AIP006111 | Richview Manby Transmission Reinforcement -Station | SS-15 | Southwest GTA Transmission Reinforcement | Local Area Supply | Robert.Reinmuller@HydroOne.com | Eva.Ping@HydroOne.com | System Service | 0 | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 9816.2344 | 186913.571 | 488172.824 | 2884745.6688 | 3813038.0882 | 3788431.6214 | 1300000 | 0 | 0 | 0 | 9816.2344 | 186913.571 | 488172.824 | 2884745.6688 | 3813038.0882 | 3788431.6214 | 1300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43980 | 45458 | True | IESO | True | ORTAC -Rating Exceeded | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Richview Manby Transmission Reinforcement -Station
24854 | Telecom 48Vdc Power Supply Remote Monitoring | N.T.C.1.25 | 7700 | 203 | PROJECT DELIVERY | AIP006116 | AIP006116 | AIP006116 | No | AIP006116 | Telecom 48Vdc Power Supply Remote Monitoring | 0 |  | Auxiliary Telecommunication Equipment | Miroslav.Kostic@HydroOne.com | Sheraz.Majid@HydroOne.com | System Renewal | 0 | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 198990.1832 | 1820566.3572 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 203051.2073 | 1857720.7726 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4061.0241 | -37154.4155 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43388 | 43825 | False |  | False |  | False |  | False | False |  | False | False | True | True | FALSE |  | 0 | 0 | Asset Optimal
24855 | Lambton TS Demerger | N.T.C.2.12 | 7700 | 203 | PROJECT DELIVERY | AIP006098 | AIP006098 | AIP006098 | No | AIP006098 | Lambton TS Demerger | 0 |  | Generator Customer Connection | Robert.Reinmuller@HydroOne.com | Emeka.Okongwu@HydroOne.com | System Access | 0 | 0 | 0 | 0 | Project | init | Short Term Planning | Short Term Planning |  | 147243.5154 | 1475633.4549 | 585807.3888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 147243.5154 | 1475633.4549 | 1985807.3888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1.1102e-10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43556 | 44044 | True | Customer request from OPGI | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Alternative 1
24856 | Nanticoke TS Demerger | N.T.C.2.12 | 7700 | 203 | PROJECT DELIVERY | AIP006097 | AIP006097 | AIP006097 | No | AIP006097 | Nanticoke TS Demerger | 0 |  | Generator Customer Connection | Robert.Reinmuller@HydroOne.com | Gene.Ng@HydroOne.com | System Access | 0 | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 564433.4758 | 590253.382 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 564433.4758 | 1990253.382 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1.1102e-10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43424 | 43621 | True | Request from OPGI | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Alternative 1
24858 | Goderich TS M3 ID34010 Tx - NRStor Goderich CAES | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP005760 |  | AIP005760 | Yes | AIP005760 | Placeholder for Upstream Tx Work for DG (Project) |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24859 | GE UR CPU VI/VO Replacement | N.T.C.1.19 | 7700 | 203 | PROJECT DELIVERY | AIP006131 | AIP006131 | AIP006131 | No | AIP006131 | GE UR CPU VI/VO Replacement | 0 |  | Protection Control & Metering Equip | Miroslav.Kostic@HydroOne.com | Sasa.Maljukan@HydroOne.com | System Renewal | 0 | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 1754514.0234 | 1774790.7056 | 1788537.7232 | 1802127.7642 | 1822389.2503 | 0 | 0 | 0 | 0 | 0 | 1754514.0234 | 1774790.7056 | 1788537.7232 | 1802127.7642 | 1822389.2503 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43465 | 45291 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Replace
24860 | IT Service Management Project Phase 2 | N.T.C.1.29 | 4514 | 212 | INFO SOLUTIONS DIVISION | AIP006268 | AIP006268 | AIP006268 | No | AIP006268 | IT Service Management Project Phase 2 | 0 |  | NERC Cyber Security Compliance Readiness | lincoln.frost-hunt@hydroone.com | Sherry.Wilging@hydroone.com | System Renewal | 0 | 0 | 0 | 0 | Project | AWRD EMPP | Executing | Executing |  | 69606.1925 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69606.1925 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43086 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Enter Descriptive Name for Project Alternative
24861 | Elmira TS M1 ID33390 Tx-Elmira Solid Battery SS | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP005760 |  | AIP005760 | Yes | AIP005760 | Placeholder for Upstream Tx Work for DG (Project) |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | EMPP ACTN | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24862 | Norfolk Thomson Rd. Pole-Trans Replacements | N.D.C.1.07 | 7374 | 205 | LINES | UNPLND |  |  | Yes |  |  |  |  | Lines | emre.aydin@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24863 | Aylmer TS M4 ID32590 TX - IGPC Ethanol | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24864 | Phaser Development | N.T.C.3.06 | 4514 | 212 | INFO SOLUTIONS DIVISION | AIP006112 | AIP006112 | AIP006112 | No | AIP006112 | Phasor Meaurement Unit (PMU) Deployment | 0 |  | Grid Operating and Control Facilities | Godfrey.Holder@HydroOne.com | emily.booth@hydroone.com | General Plant | 0 | Not Required | 03 - None (default) | Not Required | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 884534.258 | 1165209.8943 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 884534.258 | 1165209.8943 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43951 | 44499 | False |  | True | NERC and IESO compliance requirements by a 2020 enforcement date (established August 2016). | False |  | False | False |  | False | False | False | True | FALSE |  | 0 | 0 | PMU Deployment Without NMS Integration
24865 | Legacy Metering Maintenance | N.T.M.1.17 | 8706 | 214 | METER SHOP | AIP006108 | AIP006108 | AIP006108 | No | AIP006108 | Legacy Metering Maintenance | 0 |  | Protection Control & Metering Equipment | Miroslav.Kostic@HydroOne.com | Mohnish.Bilimoria@hydroone.com | System O&M | Greater Toronto Area | 0 | 02 - Expectation (no agreement) | 0 | Program | EMPP AWRD | Executing | Short Term Planning |  | 355035.3703 | 245772.5872 | 159929.8976 | 81670.9171 | 26641.1159 | 0 | 0 | 0 | 0 | 0 | 355035.3703 | 245772.5872 | 159929.8976 | 81670.9171 | 26641.1159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | True | Toronto Hydro | True | IESO Market Rules, Chapter 6, Section 3.2; Appendix 6.3 (all sections) | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Asset Optimal
24866 | HONI TXs Metering Asset Maintenance | N.T.M.1.17 | 8706 | 214 | METER SHOP | AIP006109 | AIP006109 | AIP006109 | No | AIP006109 | HONI TXs Metering Asset Maintenance | 0 |  | Protection Control & Metering Equipment | Miroslav.Kostic@HydroOne.com | Mohnish.Bilimoria@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | AWRD EMPP | Executing | Short Term Planning |  | 121894.3699 | 107978.5073 | 117126.1673 | 116324.0374 | 134573.6421 | 126562.699 | 0 | 0 | 0 | 0 | 121894.3699 | 107978.5073 | 117126.1673 | 116324.0374 | 134573.6421 | 126562.699 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | True | Measurement Canada, E-26, Section 5.1; GEN-24, Section 3 [new line] IESO, Appendix 6.3 (all sections) [new line] IESO, Market Manual 3.2, Appendix D, Guiding Principals | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Vulnerable
24867 | Prevent Presistent Estimation | N.D.C.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION | UNPLND |  |  | Yes |  |  |  |  | IT Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24868 | CSO Technology Projects 2023+ | N.D.C.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION | UNPLND |  |  | Yes |  |  |  |  | IT Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24869 | Select Bill Due Date | N.D.M.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION | UNPLND |  |  | Yes |  |  |  |  | IT Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24871 | 2018 Compensation Upgrades | N.C.C.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION | UNPLND |  |  | Yes |  |  |  |  | IT Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24872 | Select Bill Due Date | N.D.C.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION | UNPLND |  |  | Yes |  |  |  |  | IT Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24873 | Bill Redesign | N.D.C.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION | UNPLND |  |  | Yes |  |  |  |  | IT Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24874 | Waterloo-Erb Street Widening-Recoverable | N.T.C.1.14 | 7700 | 203 | PROJECT DELIVERY | AIP006171 | AIP006171 | AIP006171 | No | AIP006171 | Waterloo - Region - Erb Street Improvements - 230kV Tower Relocation - Recoverable | 0 |  | Third Party Transmission System Modifications | john.boldt@HydroOne.com | Gian.Minichini@HydroOne.com | System Renewal | Western | 0 | 01 - Agreement (current/future) | 0 | Project | DETL ACTN | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 1720000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -500000 | -1720000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43327 | 43814 | True | Region of Waterloo asked HONI to relocate lines D4W/D5W and D8S/D10H to accommodate their road project. | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Waterloo - Region - Erb Street Improvements - 230kV Tower Relocation - Recoverable
24877 | Digital Correspondance | N.D.C.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION | UNPLND |  |  | Yes |  |  |  |  | IT Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24878 | Predictive Analytics & Artificial Intelligence | N.D.C.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION | UNPLND |  |  | Yes |  |  |  |  | IT Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24879 | Digital Correspondence | N.D.M.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION | UNPLND |  |  | Yes |  |  |  |  | IT Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24880 | Prevent Presistent Estimation | N.D.M.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION | UNPLND |  |  | Yes |  |  |  |  | IT Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24881 | CSO Technology Projects 2023+ | N.D.M.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION | UNPLND |  |  | Yes |  |  |  |  | IT Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24882 | Bill Redesign | N.D.M.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION | UNPLND |  |  | Yes |  |  |  |  | IT Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24883 | Autotransformer Tertiary-GF Prot Tripping | N.T.M.1.17 | 7700 | 203 | PROJECT DELIVERY | AIP006135 | AIP006135 | AIP006135 | No | AIP006135 | Autotransformer Tertiary-GF Protection Tripping | 0 |  | Protection Control & Metering Equipment | Miroslav.Kostic@HydroOne.com | Sasa.Maljukan@HydroOne.com | System O&M | N/A | 0 | 03 - None (default) | 0 | Program | init | Short Term Planning | Short Term Planning | 180 | 107884.3295 | 214962.0376 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 107884.3295 | 214962.0376 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | True | False |  | False | False | False | False | FALSE |  | 0 | 0 | Corrections (Modified-Tx Decision)
24884 | Autotransformer Tertiary-GF Prot Tripping Upgrade | N.T.C.1.19 | 7700 | 203 | PROJECT DELIVERY | AIP006134 | AIP006134 | AIP006134 | No | AIP006134 | Autotransformer Tertiary-GF Protection Tripping (Upgrade) | 0 |  | Protection Control & Metering Equip | Miroslav.Kostic@HydroOne.com | Sasa.Maljukan@HydroOne.com | System Renewal | N/A | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 1032067.1356 | 1043994.5952 | 1052080.9862 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1032067.1356 | 1043994.5952 | 1052080.9862 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43465 | 44561 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Replacement
24885 | Predictive Analytics & Artificial Intelligence | N.D.M.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION | UNPLND |  |  | Yes |  |  |  |  | IT Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24886 | Telecom Transport Network & Unforeseen Asset Repl | N.T.C.1.25 | 7700 | 203 | PROJECT DELIVERY | AIP000658B | AIP000658 | AIP000658 | No | AIP000658 | SONET and Microwave Device Replacement | 0 |  | Auxiliary Telecommunication Equipment | Miroslav.Kostic@HydroOne.com | Sheraz.Majid@HydroOne.com | System Renewal | 0 | 0 | 03 - None (default) | 0 | Program | init | Short Term Planning | Short Term Planning | # of Devices | 0 | 0 | 0 | 1564454.9655 | 1576342.2801 | 1594065.3653 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1612840.1707 | 1625095.1341 | 1643366.3559 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -48385.2051 | -48752.854 | -49300.9907 | 0 | 0 | 0 | 0 | -3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | True | reliability requirements to need TSC, NPCC, NERC | False |  | True | False |  | False | False | False | False | FALSE |  | 0 | 0 | Asset Optimal
24887 | DNU (DELETE) Milton SS: Component Replacements | N.T.C.1.43 | 7700 | 203 | PROJECT DELIVERY | AIP005198 |  | AIP005198 | Yes | AIP005198 | Milton SS: Component Replacements |  |  | Greater Toronto Area Zone Station/Yard Investments | James.Mardegan@HydroOne.com | michael.xavier@hydroone.com | System Renewal | Greater Toronto Area | Not Required | 03 - None (default) | TBD | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24888 | DNU (DELETE) Beaverton TS: Component Replacements | N.T.C.1.42 | 7700 | 203 | PROJECT DELIVERY | AIP005184 |  | AIP005184 | Yes | AIP005184 | Beaverton TS: Component Replacements |  |  | Central Zone Station/Yard Investments | James.Mardegan@HydroOne.com | michael.xavier@hydroone.com | System Renewal | Central | Not Required | 03 - None (default) | TBD | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24889 | NOMS Upgrade (2023) | N.C.C.3.01 | 4514 | 212 | INFO SOLUTIONS DIVISION | AIP006123 | AIP006123 | AIP006123 | No | AIP006123 | NOMS Refresh (2023) | 0 |  | Common Oper Infrast & Control Facilities | Godfrey.Holder@HydroOne.com | emily.booth@hydroone.com | General Plant | 0 | Not Required | 03 - None (default) | Not Required | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 1239322.1993 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1239322.1993 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44958 | 45748 | False |  | True | Market Rules; DSC 4.4.7; Hydro One Conditions of Service, Section H | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Asset Optimal
24890 | GE UR CPU VI/VO Corrections | N.T.M.1.17 | 7370 | 206 | TX LINES AND STATIONS | AIP006132 | AIP006132 | AIP006132 | No | AIP006132 | GE UR CPU VI/VO Corrections | 0 |  | Protection Control & Metering Equipment | Miroslav.Kostic@HydroOne.com | Sasa.Maljukan@HydroOne.com | System O&M | N/A | 0 | 03 - None (default) | 0 | Program | EMPP ACTN | Executing | Short Term Planning | Number of SAP Orders Completed | 500681.3654 | 508785.6984 | 561607.9792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500681.3654 | 508785.6984 | 561607.9792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Asset Optimal
24891 | Leaside TS: Restring O/H M3 fdr to new THESL pole | N.T.C.2.11 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Load Customer Connection | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24892 | TremaineTS: New Breaker Positions-Burlington Hydro | N.T.C.2.11 | 7700 | 203 | PROJECT DELIVERY | AIP006149 | AIP006149 | AIP006149 | No | AIP006149 | Tremaine TS: New Breaker Positions-Burlington Hydro | 0 |  | Load Customer Connection | Robert.Reinmuller@HydroOne.com | Khurram.Makhdoom@HydroOne.com | System Access | Hamilton Niagara | Not Required | 01 - Agreement (current/future) | Not Required | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 1900000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -100000 | -1900000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43434 | 43800 | True | Burlington Hydro Request | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Tremaine TS: New Breaker Positions-Burlington Hydro
24893 | TremaineTS: New Breaker Positions-Milton Hydro | N.T.C.2.11 | 7700 | 203 | PROJECT DELIVERY | AIP006153 | AIP006153 | AIP006153 | No | AIP006153 | Tremaine TS: New Breaker Positions-Milton Hydro | 0 |  | Load Customer Connection | Robert.Reinmuller@HydroOne.com | Khurram.Makhdoom@HydroOne.com | System Access | Hamilton Niagara | Not Required | 01 - Agreement (current/future) | Not Required | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 1900000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -100000 | -1900000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43434 | 43800 | True | Milton Hydro Request | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Tremaine TS: New Breaker Positions-Burlington Hydro
24894 | Anti-Climb Devices - Recoverable | N.T.C.1.14 | 7370 | 206 | TX LINES AND STATIONS | AIP006166 | AIP006166 | AIP006166 | No | AIP006166 | Anti-Climbing Devices Installations - Recoverable | 0 |  | Third Party Transmission System Modifications | john.boldt@HydroOne.com | Gian.Minichini@HydroOne.com | System Renewal | 0 | 0 | 01 - Agreement (current/future) | 0 | Program | EMPP AWRD | Executing | Short Term Planning | Retainer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -100000 | -100000 | -100000 | -100000 | -100000 | -100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42962 | 0 | True | Various Secondary Land Use proposals have asked HONI to install anti-climbing devices on various towers across the province. | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Anti-Climbing Devices Installations - Recoverable
24895 | Emergency Communication System | N.C.M.2.70 | 838 | 212 | INFO SOLUTIONS DIVISION |  |  |  | No |  |  |  |  | IT - Project & Architecture Services | lincoln.frost-hunt@hydroone.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24896 | Business Continuity Database | N.C.C.1.70 | 838 | 212 | INFO SOLUTIONS DIVISION | AIP006160 | AIP006160 | AIP006160 | No | AIP006160 | Business Continuity Program | 0 |  | IT - Sustainment and Operations | lincoln.frost-hunt@hydroone.com | Sherry.Wilging@hydroone.com | General Plant | 0 | 0 | 0 | 0 | Project | init | Short Term Planning | Short Term Planning |  | 350000 | 0 | 0 | 0 | 336983.3689 | 0 | 0 | 0 | 0 | 0 | 350000 | 0 | 0 | 0 | 336983.3689 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43171 | 44890 | False |  | False |  | False |  | False | False |  | False | False | False | False | TRUE | Improve resilience of our organization by improving our business continuity and crisis management capabilities | 0 | 0 | Business Continuity Program
24897 | Advanced Persistent Threat End Point Protection | N.C.C.1.70 | 838 | 212 | INFO SOLUTIONS DIVISION | AIP006125 | AIP006125 | AIP006125 | No | AIP006125 | Security Operations - Advance Persistent Threat Protection Project | 0 |  | IT - Sustainment and Operations | lincoln.frost-hunt@hydroone.com | Sherry.Wilging@hydroone.com | General Plant | 0 | 0 | 0 | 0 | Project | init | Short Term Planning | Short Term Planning |  | 400000.12 | 492861.367 | 0 | 96493.5231 | 0 | 944344.5929 | 0 | 0 | 0 | 0 | 400000.12 | 492861.367 | 0 | 96493.5231 | 0 | 944344.5929 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43234 | 45254 | False |  | False |  | False |  | False | False |  | False | False | False | False | TRUE | Security Program Strategy to shift from reactive to proactive approach: There is a high level risk that a malicious attack from an insider or external third party could result in degradation of the systems that control the Grid, which could, in turn, have a downstream impact on the delivery of electricity. | 0 | 0 | Security Operations - Advance Persistent Threat Protection Project
24898 | Threat Hunting HW-SW | N.C.C.1.70 | 838 | 212 | INFO SOLUTIONS DIVISION | AIP006122A | AIP006122 | AIP006122 | No | AIP006122 | Security Operations - Threat Hunting Capital Project | 0 |  | IT - Sustainment and Operations | lincoln.frost-hunt@hydroone.com | Sherry.Wilging@hydroone.com | General Plant | 0 | 0 | 0 | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 1478584.1047 | 488481.2826 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1478584.1047 | 488481.2826 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43605 | 45289 | False |  | False |  | False |  | False | False |  | False | False | False | False | TRUE | IT Operational Security Maturity and Capability Upgrade: Shift from a Reactive to Proactive Continuous Approach by improving areas such as penetration testing, Advance Persistent Threat (detect) and threat hunting (protect) etc. Jan 2017, RSA deployed a threat hunting technology to determine if Hydro One had been compromised by the malware Grizzly Steppe. This technology is starting to be deployed by more organization and is becoming main stream tool against cyber-attacks. | 0 | 0 | Security Operations - Threat Hunting Capital Project
24899 | Perimeter Security - EIT Infrasturcture Refresh | N.C.C.1.70 | 838 | 212 | INFO SOLUTIONS DIVISION | AIP005749 |  | AIP005749 | Yes | AIP005749 | IT Security Operations Capital |  |  | IT - Sustainment and Operations | lincoln.frost-hunt@hydroone.com | Sherry.Wilging@hydroone.com | General Plant | 0 | 0 | 03 - None (default) | 0 | Program | init | Short Term Planning | Short Term Planning | Retainer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24900 | new AR | N.T.C.3.08 | 7700 | 203 | PROJECT DELIVERY | AIP000985 |  | AIP000985 | Yes | AIP000985 | Local PSMC Network Sustainment |  |  | Integrating Operating Infrastructure | Miroslav.Kostic@HydroOne.com | Andrew.Webb@HydroOne.com | General Plant | 0 | 0 | 02 - Expectation (no agreement) | 0 | Program | init | Short Term Planning | Short Term Planning | # of sites/upgrades | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24901 | Bunting TS: MV Switchyard & Component Replacement | N.T.C.1.41 | 7700 | 203 | PROJECT DELIVERY | AIP006186 | AIP006186 | AIP006186 | No | AIP006186 | Bunting TS: MV Switchgear & Component Replacement | SR-06 | Load Station Switchgear and Ancillary Equipment Replacement Projects | Hamilton/Niagara Zone Station/Yard Investments | James.Mardegan@HydroOne.com | mark.truchanowicz@hydroone.com | System Renewal | Hamilton Niagara | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 619587.5945 | 878698.9418 | 4460678.9197 | 8177536.3893 | 2918187.92 | 0 | 0 | 0 | 0 | 0 | 666223.2199 | 944837.5719 | 4796428.9459 | 8793049.881 | 3137836.52 | 0 | 0 | 0 | 0 | 0 | -46635.6254 | -66138.63 | -335750.0262 | -615513.4917 | -219648.6 | 0 | 0 | 0 | -7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44599 | 45534 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | MV Switchyard and Component Replacement
24902 | Murray TS: T11, T12 & Component Replacement | N.T.C.1.41 | 7700 | 203 | PROJECT DELIVERY | AIP006185 | AIP006185 | AIP006185 | No | AIP006185 | Murray TS: T11, T12 & Component Replacement | SR-05 | Load Station Transformer Replacement Projects | Hamilton/Niagara Zone Station/Yard Investments | James.Mardegan@HydroOne.com | mark.truchanowicz@hydroone.com | System Renewal | Hamilton Niagara | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 796612.7194 | 1331882.465 | 8264753.547 | 9971568.0516 | 3064685.56 | 0 | 0 | 0 | 0 | 0 | 856572.8166 | 1432131.6828 | 8886831.771 | 10722116.1845 | 3295360.72 | 0 | 0 | 0 | 0 | 0 | -59960.0972 | -100249.2178 | -622078.224 | -750548.1329 | -230675.16 | 0 | 0 | 0 | -7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44423 | 45472 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | MV Switchyard and Component Replacement
24903 | Information Rights Management Phase 2 | N.C.C.2.60 | 838 | 212 | INFO SOLUTIONS DIVISION | AIP006150 | AIP006150 | AIP006150 | No | AIP006150 | Information Rights Management Phase 2 | 0 |  | IT Business Solution Development | jj.blais@HydroOne.com | Sherry.Wilging@hydroone.com | General Plant | 0 | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 2327487.4145 | 1391925.829 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2327487.4145 | 1391925.829 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43905 | 44530 | False |  | True | Bill 198 | False |  | False | False |  | False | False | True | False | FALSE |  | 0 | 0 | Asset Optimal
24904 | Information Rights Management Phase 2 | N.C.M.2.60 | 838 | 212 | INFO SOLUTIONS DIVISION | AIP006151 | AIP006151 | AIP006151 | No | AIP006151 | Information Rights Management Phase 2 | 0 |  | IT-Business Solution Development | jj.blais@HydroOne.com | Sherry.Wilging@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 210000 | 50000.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 210000 | 50000.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43479 | 44554 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Vulnerable - Tx Contraint Reduction
24905 | OGCC Long View Phone System QA Environment | N.T.C.1.29 | 838 | 212 | INFO SOLUTIONS DIVISION | UNPLND |  |  | Yes |  |  |  |  | NERC Cyber Security Compliance Readiness | lincoln.frost-hunt@hydroone.com | [6 empty] | Project | AWRD EMPP BEST | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24906 | PSR Replacement | N.T.C.3.08 | 7700 | 203 | PROJECT DELIVERY | AIP006050 | AIP006050 | AIP006050 | No | AIP006050 | PSR Replacement | 0 |  | Integrating Operating Infrastructure | Miroslav.Kostic@HydroOne.com | Andrew.Webb@HydroOne.com | General Plant | 0 | 0 | 0 | 0 | Project | init | Short Term Planning | Short Term Planning |  | 101525.6037 | 309620.1288 | 417597.8617 | 210416.2439 | 106007.511 | 53599.7174 | 0 | 0 | 0 | 0 | 101525.6037 | 309620.1288 | 417597.8617 | 210416.2439 | 106007.511 | 53599.7174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43814 | 44927 | False |  | False |  | False |  | False | False |  | False | True | False | False | FALSE |  | 0 | 0 | Asset Optimal
24907 | SAP Control Entry Project | N.T.C.3.08 | 7700 | 203 | PROJECT DELIVERY | AIP006121 | AIP006121 | AIP006121 | No | AIP006121 | SAP Control Entry Project | 0 |  | Integrating Operating Infrastructure | Miroslav.Kostic@HydroOne.com | Andrew.Webb@HydroOne.com | General Plant | 0 | 0 | 03 - None (default) | 0 | Program | init | Short Term Planning | Short Term Planning |  | 50762.8018 | 51603.3152 | 52199.7474 | 52604.061 | 53003.7555 | 53599.7174 | 0 | 0 | 0 | 0 | 50762.8018 | 51603.3152 | 52199.7474 | 52604.061 | 53003.7555 | 53599.7174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43100 | 45261 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Asset Optimal
24908 | TX Non-Operational Data Mgmt System | N.T.C.3.08 | 7700 | 203 | PROJECT DELIVERY | AIP006100 | AIP006100 | AIP006100 | No | AIP006100 | Non-Operational Data Mgmt System | GP-05 | Transmission Non-Operational Data Management System | Integrating Operating Infrastructure | Miroslav.Kostic@HydroOne.com | alan.wong@hydroone.com | General Plant | N/A | Not Required | 03 - None (default) | Not Required | Project | ACCP EMPP | Executing | Executing |  | 994374.1789 | 4955095.427 | 4914079.2109 | 4855041.2263 | 4796011.5452 | 950967.4289 | 0 | 0 | 0 | 0 | 994374.1789 | 4955095.427 | 4914079.2109 | 4855041.2263 | 4796011.5452 | 950967.4289 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43100 | 45275 | False |  | True | Equipment maintenace for compliance can be eliminated | False |  | True | False |  | False | True | False | True | FALSE |  | 0 | 0 | Asset Optimal
24909 | Place Holder - Campbellville Pit Remediation | N.T.M.1.14 | 7700 | 203 | PROJECT DELIVERY |  |  |  | No |  |  |  |  | Engineering and Environmental Support | Mike.Tanaskovic@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24910 | Security Ed. & Communication - Staff,ELT & Board | N.C.M.2.70 | 838 | 212 | INFO SOLUTIONS DIVISION | AIP006165 | AIP006165 | AIP006165 | No | AIP006165 | Security Culture - Security Education and Communication | 0 |  | IT - Project & Architecture Services | lincoln.frost-hunt@hydroone.com | Sherry.Wilging@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | init | Short Term Planning | Short Term Planning |  | 200000 | 200000 | 199999.88 | 200000 | 200000 | 199999.96 | 0 | 0 | 0 | 0 | 200000 | 200000 | 199999.88 | 200000 | 200000 | 199999.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | True | CIP-004, 003, 011 | False |  | False | False |  | False | False | False | False | TRUE | Create a vigilant and accountable people culture Enhance Security Awareness and Education of our staff. Establish accountability for ownership and protection of our sensitive data and systems The end user continues to be targeted and exploited via spear phishing, drive by exploites and social engineering attacks. An internal phishing exercise demonstrated the need for continual security education. Strategy is to be proactive, align, assess, educated, monitor and practice a vigilant culture. | 0 | 0 | Vulnerable - Tx Contraint Reduction
24911 | Code of Practice Governance and Risk Mgt | N.C.M.2.70 | 838 | 212 | INFO SOLUTIONS DIVISION | AIP006179 | AIP006179 | AIP006179 | No | AIP006179 | Security Culture - Code of Practice Governance and Risk Management | 0 |  | IT - Project & Architecture Services | lincoln.frost-hunt@hydroone.com | Sherry.Wilging@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | init | Short Term Planning | Short Term Planning |  | 225000 | 225000 | 225000 | 225000 | 225000 | 225000 | 0 | 0 | 0 | 0 | 225000 | 225000 | 225000 | 225000 | 225000 | 225000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | False |  | False | False | False | False | TRUE | To maintain the correct set of documentation, procedural and technical security controls that outlines the level of protection required for Hydro One. It contains guidance on how to select appropriate controls for an implementation, including those essential for legislative compliance and those required for best practice. This funding is to maintain and develop the code of practice, the associated artifacts and monitor for compliance | 0 | 0 | Security Culture - Code of Practice Governance and Risk Management
24912 | Workforce Screening | N.C.M.2.70 | 838 | 212 | INFO SOLUTIONS DIVISION | AIP006178 | AIP006178 | AIP006178 | No | AIP006178 | Security Culture - Workforce Screening | 0 |  | IT - Project & Architecture Services | lincoln.frost-hunt@hydroone.com | Sherry.Wilging@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | init | Short Term Planning | Short Term Planning |  | 200000 | 400000 | 400000 | 400000 | 400000 | 400000 | 0 | 0 | 0 | 0 | 200000 | 400000 | 400000 | 400000 | 400000 | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | False |  | False | False | False | False | TRUE | Hydro One is revising the Pre-Employment screening process used to verify information supplied by candidates on their resumes and applications. This investment is to fund a third party organization specialized in background screening against a number of indicators to determine any tendencies that might jeopardize the employer, tarnish its reputation, endanger staff, or limit the effectiveness of the candidate. . | 0 | 0 | Vulnerable - Tx Contraint Reduction
24913 | Business Continuity Sustainment | N.C.M.2.70 | 838 | 212 | INFO SOLUTIONS DIVISION | AIP006160-1 A | AIP006160-1 | AIP006160 | Yes | AIP006160-1 | Business Continuity Notification and Annual Subscription | 0 |  | IT - Project & Architecture Services | lincoln.frost-hunt@hydroone.com | Sherry.Wilging@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | init | Short Term Planning | Short Term Planning |  | 54000 | 54000 | 54000.12 | 54000 | 54000 | 54000.12 | 0 | 0 | 0 | 0 | 54000 | 54000 | 54000.12 | 54000 | 54000 | 54000.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | False |  | False | False | False | False | TRUE | Improve resilience of our organization by improving our business continuity and crisis management capabilities. | 0 | 0 | Vulnerable - Tx Contraint Reduction
24914 | Application Security External Expertise | N.C.M.2.70 | 4339 | 212 | INFO SOLUTIONS DIVISION | AIP005722D | AIP005722 | AIP005722 | No | AIP005722 | Data Security | 0 |  | IT - Project & Architecture Services | lincoln.frost-hunt@hydroone.com | Sherry.Wilging@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | init | Short Term Planning | Short Term Planning | Retainer | 0 | 250000 | 250000 | 250000 | 250000.08 | 250000.08 | 0 | 0 | 0 | 0 | 0 | 250000 | 250000 | 250000 | 250000.08 | 250000.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | False |  | False | False | False | False | TRUE | AIP focus on Data Loss Prevention of, External Threat and Vulnerability feeds that provide in-depth information about specific threats to help HONI protect itself from the types of attacks that could do them the most damage. | 0 | 0 | Vulnerable - Tx Contraint Reduction
24915 | Emergency Notification Annual Subscription | N.C.M.2.70 | 838 | 212 | INFO SOLUTIONS DIVISION | AIP006160-1 B | AIP006160-1 | AIP006160 | Yes | AIP006160-1 | Business Continuity Notification and Annual Subscription | 0 |  | IT - Project & Architecture Services | lincoln.frost-hunt@hydroone.com | Sherry.Wilging@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | init | Short Term Planning | Short Term Planning |  | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 0 | 0 | 0 | 0 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | False |  | False | False | False | False | TRUE | Improve resilience of our organization by improving our business continuity and crisis management capabilities. | 0 | 0 | Vulnerable - Tx Contraint Reduction
24916 | Advanced Persistent Threat End Point Protection | N.C.M.2.70 | 838 | 212 | INFO SOLUTIONS DIVISION | AIP006163 | AIP006163 | AIP006163 | No | AIP006163 | Advance Persistent Threat Protection Maintenance | 0 |  | IT - Project & Architecture Services | lincoln.frost-hunt@hydroone.com | Sherry.Wilging@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | init | Short Term Planning | Short Term Planning |  | 72000 | 162000 | 162000 | 162000 | 162000 | 180000.12 | 0 | 0 | 0 | 0 | 72000 | 162000 | 162000 | 162000 | 162000 | 180000.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | False |  | False | False | False | False | TRUE | Security Program Strategy to shift from reactive to proactive approach: There is a medium level risk that a malicious attack from an insider or external third party could result in degradation of the systems that control the Grid, which could, in turn, have a downstream impact on the delivery of electricity. | 0 | 0 | Security Operations - Advance Persistent Threat Protection Project
24917 | Adv'd Persistent Threat Prot. SW - OM&A Install | N.C.M.2.70 | 838 | 212 | INFO SOLUTIONS DIVISION | AIP006162 | AIP006162 | AIP006162 | No | AIP006162 | Security Operations - Advance Persistent Threat Protection OMA | 0 |  | IT - Project & Architecture Services | lincoln.frost-hunt@hydroone.com | Sherry.Wilging@hydroone.com | System O&M | 0 | 0 | 0 | 0 | Project | init | Short Term Planning | Short Term Planning |  | 100000 | 200000 | 100000 | 0 | 0 | 300000 | 0 | 0 | 0 | 0 | 100000 | 200000 | 100000 | 0 | 0 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43234 | 45254 | False |  | False |  | False |  | False | False |  | False | False | False | False | TRUE | Security Program Strategy to shift from reactive to proactive approach: There is a medium level risk that a malicious attack from an insider or external third party could result in degradation of the systems that control the Grid, which could, in turn, have a downstream impact on the delivery of electricity. | 0 | 0 | Security Operations - Advance Persistent Threat Protection Project
24918 | Forensic Service Retainer | N.C.M.2.70 | 838 | 212 | INFO SOLUTIONS DIVISION | AIP006181 | AIP006181 | AIP006181 | No | AIP006181 | Security Operations - Forensic | 0 |  | IT - Project & Architecture Services | lincoln.frost-hunt@hydroone.com | Sherry.Wilging@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | init | Short Term Planning | Short Term Planning |  | 150000.12 | 149999.88 | 150000 | 150000.12 | 150000.12 | 150000 | 0 | 0 | 0 | 0 | 150000.12 | 149999.88 | 150000 | 150000.12 | 150000.12 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | False |  | False | False | False | False | TRUE | Third party Forensic Incident Response on retainer. | 0 | 0 | Vulnerable - Tx Contraint Reduction
24919 | Penetration Testing Program | N.C.M.2.70 | 838 | 212 | INFO SOLUTIONS DIVISION | AIP006182 | AIP006182 | AIP006182 | No | AIP006182 | Security Operations - Penetration & Vulnerability Testing | 0 |  | IT - Project & Architecture Services | lincoln.frost-hunt@hydroone.com | Sherry.Wilging@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | init | Short Term Planning | Short Term Planning |  | 250000 | 249999.88 | 250000 | 250000.08 | 250000.12 | 250000 | 0 | 0 | 0 | 0 | 250000 | 249999.88 | 250000 | 250000.08 | 250000.12 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | False |  | False | False | False | False | TRUE | Conduct Penetration testing or Vulnerability test on critical application to ensure any security risks are identified and remediated. | 0 | 0 | Penetration & Vulnerabiltiy Testing
24920 | Threat and Vulnerability Feeds | N.C.M.2.70 | 838 | 212 | INFO SOLUTIONS DIVISION | AIP005722E | AIP005722 | AIP005722 | No | AIP005722 | Data Security | 0 |  | IT - Project & Architecture Services | lincoln.frost-hunt@hydroone.com | Sherry.Wilging@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | init | Short Term Planning | Short Term Planning | Retainer | 300000.12 | 300000 | 300000 | 299999.88 | 300000 | 300000 | 0 | 0 | 0 | 0 | 300000.12 | 300000 | 300000 | 299999.88 | 300000 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | False |  | False | False | False | False | TRUE | AIP focus on Data Loss Prevention of, External Threat and Vulnerability feeds that provide in-depth information about specific threats to help HONI protect itself from the types of attacks that could do them the most damage. | 0 | 0 | Vulnerable - Tx Contraint Reduction
24921 | Threat Hunting HW-SW Maintenance | N.C.M.2.70 | 838 | 212 | INFO SOLUTIONS DIVISION | AIP006164A | AIP006164 | AIP006164 | No | AIP006164 | Security Operations - Threat Hunting Maintenance | 0 |  | IT - Project & Architecture Services | lincoln.frost-hunt@hydroone.com | Sherry.Wilging@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | init | Short Term Planning | Short Term Planning |  | 0 | 270000 | 360000 | 360000 | 360000 | 360000 | 0 | 0 | 0 | 0 | 0 | 270000 | 360000 | 360000 | 360000 | 360000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | False |  | False | False | False | False | TRUE | IT Operational Security Maturity and Capability Upgrade: Shift from a Reactive to Proactive Continuous Approach by improving areas such as penetration testing, advance persistent threat (protect) tool, threat hunting (detect) tool, etc. Jan 2017, RSA deployed a threat hunting technology to determine if Hydro One had been compromised by the malware Grizzly Steppe. This technology is starting to be deployed by more organization and is becoming main stream tool against cyber-attacks. | 0 | 0 | Security Operations - Threat Hunting Capital Project
24922 | Threat Hunting HW-SW OM&A Installation Expertise | N.C.M.2.70 | 838 | 212 | INFO SOLUTIONS DIVISION | AIP006161 | AIP006161 | AIP006161 | No | AIP006161 | Security Operations - Threat Hunting OMA | 0 |  | IT - Project & Architecture Services | lincoln.frost-hunt@hydroone.com | Sherry.Wilging@hydroone.com | System O&M | 0 | 0 | 0 | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 400000 | 100000 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 400000 | 100000 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43605 | 45289 | False |  | False |  | False |  | False | False |  | False | False | False | False | TRUE | IT Operational Security Maturity and Capability Upgrade: Shift from a Reactive to Proactive Continuous Approach by improving areas such as penetration testing, Advance Persistent Threat (protect), threat hunting (detect) etc. Jan 2017, RSA deployed a threat hunting technology to determine if Hydro One had been compromised by the malware Grizzly Steppe. This technology is starting to be deployed by more organization and is becoming main stream tool against cyber-attacks. | 0 | 0 | Security Operations - Threat Hunting Capital Project
24923 | Threat Hunting quarterly service | N.C.M.2.70 | 838 | 212 | INFO SOLUTIONS DIVISION | AIP006164B | AIP006164 | AIP006164 | No | AIP006164 | Security Operations - Threat Hunting Maintenance | 0 |  | IT - Project & Architecture Services | lincoln.frost-hunt@hydroone.com | Sherry.Wilging@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | init | Short Term Planning | Short Term Planning |  | 0 | 149999.88 | 500000.12 | 500000 | 499999.92 | 500000 | 0 | 0 | 0 | 0 | 0 | 149999.88 | 500000.12 | 500000 | 499999.92 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | False |  | False | False | False | False | TRUE | IT Operational Security Maturity and Capability Upgrade: Shift from a Reactive to Proactive Continuous Approach by improving areas such as penetration testing, advance persistent threat (protect) tool, threat hunting (detect) tool, etc. Jan 2017, RSA deployed a threat hunting technology to determine if Hydro One had been compromised by the malware Grizzly Steppe. This technology is starting to be deployed by more organization and is becoming main stream tool against cyber-attacks. | 0 | 0 | Security Operations - Threat Hunting Capital Project
24924 | SIEM Hardware-Software | N.T.C.1.29 | 838 | 212 | INFO SOLUTIONS DIVISION | AIP005749 |  | AIP005749 | Yes | AIP005749 | IT Security Operations Capital |  |  | NERC Cyber Security Compliance Readiness | lincoln.frost-hunt@hydroone.com | Sherry.Wilging@hydroone.com | General Plant | 0 | 0 | 03 - None (default) | 0 | Program | init | Short Term Planning | Short Term Planning | Retainer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24925 | SIEM Hardware-Software Fixed Price Installation | N.T.C.1.29 | 838 | 212 | INFO SOLUTIONS DIVISION | AIP005749 |  | AIP005749 | Yes | AIP005749 | IT Security Operations Capital |  |  | NERC Cyber Security Compliance Readiness | lincoln.frost-hunt@hydroone.com | Sherry.Wilging@hydroone.com | General Plant | 0 | 0 | 03 - None (default) | 0 | Program | init | Short Term Planning | Short Term Planning | Retainer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24926 | SIEM Hardware-Software Maintenance 18% | N.C.M.2.70 | 838 | 212 | INFO SOLUTIONS DIVISION | AIP005708B | AIP005708 | AIP005708 | No | AIP005708 | IT Security Operations - SEM Monitoring and Maintenance | 0 |  | IT - Project & Architecture Services | lincoln.frost-hunt@hydroone.com | Sherry.Wilging@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | init | Short Term Planning | Short Term Planning | Retainer | 756000 | 756000.12 | 819000 | 818999.88 | 630000 | 630000 | 0 | 0 | 0 | 0 | 756000 | 756000.12 | 819000 | 818999.88 | 630000 | 630000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | False |  | False | False | True | False | TRUE | To achieve the desired level Security Event monitoring, security incident management and situational awareness through the detection, containment, and remediation of IT threats in a 7/24/365 environment AIP001151 is no longer required after 2017 as the consolidate SEM monitoring will be funded from this driver. By consolidating estimate savings of 5M over 2019-2022 | 0 | 0 | Vulnerable
24927 | SIEM Hardware-Software Monitoring Managed Service | N.T.M.1.29 | 838 | 212 | INFO SOLUTIONS DIVISION | AIP005749 |  | AIP005749 | Yes | AIP005749 | IT Security Operations Capital |  |  | NERC Cyber Security Compliance Readiness | lincoln.frost-hunt@hydroone.com | Sherry.Wilging@hydroone.com | General Plant | 0 | 0 | 03 - None (default) | 0 | Program | init | Short Term Planning | Short Term Planning | Retainer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24928 | Owen Sound TS: Component Replacement | N.T.C.1.40 | 7700 | 203 | PROJECT DELIVERY | AIP006189 | AIP006189 | AIP006189 | No | AIP006189 | Owen Sound TS: Component Replacement | SR-06 | Load Station Switchgear and Ancillary Equipment Replacement Projects | Western Zone Station/Yard Investments | James.Mardegan@HydroOne.com | mark.truchanowicz@hydroone.com | System Renewal | Western | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 658156.099 | 800465.1281 | 3792538.4089 | 6954772.4084 | 2481903.28 | 0 | 0 | 0 | 0 | 0 | 707694.7301 | 860715.1915 | 4077998.2892 | 7478249.9015 | 2668713.28 | 0 | 0 | 0 | 0 | 0 | -49538.6311 | -60250.0634 | -285459.8802 | -523477.4931 | -186810 | 0 | 0 | 0 | -7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44508 | 45534 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Component Replacement
24929 | Tilbury TS: Station Decommissioning | N.T.C.1.40 | 7700 | 203 | PROJECT DELIVERY | AIP005517 | AIP005517 | AIP005517 | No | AIP005517 | Tilbury TS: Station Decommissioning | 0 |  | Western Zone Station/Yard Investments | James.Mardegan@HydroOne.com | mark.truchanowicz@hydroone.com | System Renewal | 0 | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 137427.5438 | 296379.1435 | 303297.7013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 458091.8127 | 987930.4782 | 1010992.3377 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -320664.2689 | -691551.3347 | -707694.6364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -70 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43516 | 44129 | False |  | False |  | False |  | False | True | Due to decreased CX loading, all loading can be transferred to Tilbury HVDS. | False | False | False | False | TRUE | Coordination with TX Asset Management and Hydro One DX has resulted in agreement that the minimal customer load supplied from Tilbury TS can be adequately supplied from Tilbury HVDS. It is fiscally prudent to proceed with the decomissioning of Tilbury TS to avoid future liabities on maintenance costs and environmental risks with a station supplying minimal customer load. | 1 | 1 | Station Decommissioning
24930 | Lambton TS: T5 & Component Replacement | N.T.C.1.40 | 7700 | 203 | PROJECT DELIVERY | AIP006147 | AIP006147 | AIP006147 | No | AIP006147 | Lambton TS: T5 & Component Replacement | SR-02 | Station Reinvestment Projects | Western Zone Station/Yard Investments | James.Mardegan@HydroOne.com | mark.truchanowicz@hydroone.com | System Renewal | Western | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 307789.7965 | 986293.7648 | 4282822.5181 | 13810800.402 | 13018328.6504 | 3520217.92 | 0 | 0 | 0 | 0 | 330956.7704 | 1060530.9299 | 4605185.5033 | 14850323.013 | 13998202.8499 | 3785180.56 | 0 | 0 | 0 | 0 | -23166.9739 | -74237.1651 | -322362.9852 | -1039522.6109 | -979874.1995 | -264962.64 | 0 | 0 | 0 | -7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44209 | 45623 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Component Replacement
24931 | Port Colborne TS: T61, T62 & Switchyard Refurb. | N.T.C.1.41 | 7700 | 203 | PROJECT DELIVERY | AIP006154 | AIP006154 | AIP006154 | No | AIP006154 | Port Colborne TS: T61, T62 & Switchyard Refurbishment | SR-02 | Station Reinvestment Projects | Hamilton/Niagara Zone Station/Yard Investments | James.Mardegan@HydroOne.com | mark.truchanowicz@hydroone.com | System Renewal | Hamilton Niagara | Not Required | 03 - None (default) | TBD | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 314974.6923 | 715552.9553 | 2299556.9384 | 15025981.4582 | 6393494.16 | 0 | 0 | 0 | 0 | 0 | 338682.4648 | 769411.7799 | 2472641.8692 | 16156969.3099 | 6874724.88 | 0 | 0 | 0 | 0 | 0 | -23707.7725 | -53858.8246 | -173084.9308 | -1130987.8517 | -481230.72 | 0 | 0 | 0 | -7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44579 | 45627 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Switchyard Refurbishment
24932 | Palermo TS: T3, T4 & Switchyard Refurbishment | N.T.C.1.41 | 7700 | 203 | PROJECT DELIVERY | AIP006142 | AIP006142 | AIP006142 | No | AIP006142 | Palermo TS: T3, T4 & Switchyard Refurbishment | SR-05 | Load Station Transformer Replacement Projects | Hamilton/Niagara Zone Station/Yard Investments | James.Mardegan@HydroOne.com | mark.truchanowicz@hydroone.com | System Renewal | Hamilton Niagara | Not Required | 03 - None (default) | TBD | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 314974.6923 | 905412.8328 | 3353200.0488 | 14255591.8022 | 5860970.28 | 0 | 0 | 0 | 0 | 0 | 338682.4648 | 973562.1858 | 3605591.4503 | 15328593.3357 | 6302118.6 | 0 | 0 | 0 | 0 | 0 | -23707.7725 | -68149.353 | -252391.4015 | -1073001.5335 | -441148.32 | 0 | 0 | 0 | -7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44576 | 45625 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Component Replacement
24933 | Minor Enhancements to Aveksa-Access control | N.C.M.2.70 | 838 | 212 | INFO SOLUTIONS DIVISION | AIP006195 | AIP006195 | AIP006195 | No | AIP006195 | Security Operations - Aveska Enhancement | 0 |  | IT - Project & Architecture Services | lincoln.frost-hunt@hydroone.com | Sherry.Wilging@hydroone.com | System O&M | 0 | 0 | 0 | 0 | Project | init | Short Term Planning | Short Term Planning |  | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43251 | 43462 | False |  | False |  | False |  | False | False |  | False | False | False | False | TRUE | Provide additional enhancements to the Aveksa tool | 0 | 0 | Aveksa Enhancement
24934 | Access Central Application | N.T.C.1.29 | 838 | 212 | INFO SOLUTIONS DIVISION | AIP006183 | AIP006183 | AIP006183 | No | AIP006183 | Security Operations - Access Central Application | 0 |  | NERC Cyber Security Compliance Readiness | lincoln.frost-hunt@hydroone.com | Sherry.Wilging@hydroone.com | System Renewal | 0 | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning | Retainer | 497187.0894 | 98101.9085 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 497187.0894 | 98101.9085 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43177 | 43672 | False |  | True | CIP-004, 003, 014 | False |  | False | False |  | False | False | False | False | TRUE | Replace the "home-grown" SharePoint process with an Access Management tool to ensure that only those users with the proper authority and need, have access to Critical Cyber Assets. | 0 | 0 | Asset Optimal
24935 | NERC v7 Suppy Chain (2019) | N.T.C.1.29 | 838 | 212 | INFO SOLUTIONS DIVISION |  |  |  | No |  |  |  |  | NERC Cyber Security Compliance Readiness | lincoln.frost-hunt@hydroone.com | [6 empty] | Program | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24936 | NERC v7Virtulization | N.T.C.1.29 | 838 | 212 | INFO SOLUTIONS DIVISION |  |  |  | No |  |  |  |  | NERC Cyber Security Compliance Readiness | lincoln.frost-hunt@hydroone.com | [6 empty] | Program | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24937 | NERC v7 Encryption | N.T.C.1.29 | 838 | 212 | INFO SOLUTIONS DIVISION | AIP006174 | AIP006174 | AIP006174 | No | AIP006174 | NERC v7 Encryption | 0 |  | NERC Cyber Security Compliance Readiness | lincoln.frost-hunt@hydroone.com | Sherry.Wilging@hydroone.com | System Renewal | 0 | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 497187.0894 | 1962038.1708 | 1945631.6844 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 497187.0894 | 1962038.1708 | 1945631.6844 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43255 | 44285 | False |  | True | NERC Compliance CIP-012-1 | False |  | False | False |  | False | False | False | False | TRUE | This investiment is identified in the NERC CIP Standard Delevlopment projects with an enforcement date of 2020 or beyond. This CIP Standard has yet to be passed by FERC/NERC. | 0 | 0 | NERC v7 Encryption (Modified - Challenge Session)
24938 | NERC v7Transient LOW (2019) | N.T.C.1.29 | 838 | 212 | INFO SOLUTIONS DIVISION | AIP006175 | AIP006175 | AIP006175 | No | AIP006175 | NERC v7 Transient for Low | 0 |  | NERC Cyber Security Compliance Readiness | lincoln.frost-hunt@hydroone.com | Sherry.Wilging@hydroone.com | System Renewal | 0 | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 1740154.813 | 1962038.1708 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1740154.813 | 1962038.1708 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43150 | 43812 | False |  | True | NERC Compliance CIP-003-7 | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | NERC v7 Transient for Low Impact Sites
24939 | ISL Replacement | N.T.C.1.29 | 838 | 212 | INFO SOLUTIONS DIVISION | AIP006176 | AIP006176 | AIP006176 | No | AIP006176 | Physical Security ISL Application Replacement | 0 |  | NERC Cyber Security Compliance Readiness | lincoln.frost-hunt@hydroone.com | Sherry.Wilging@hydroone.com | System Renewal | 0 | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 4971870.8943 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4971870.8943 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43122 | 43448 | False |  | True | CIP-006, 004, 014 | False |  | False | False |  | False | False | False | False | TRUE | The current ISL application is end-of-life and is proprietary to our current thrid party vendor Tyco for monitoring physical security. The contract with Tyco will expire in 2020. Plan is to implement new vendor augnostic application and migrate all the access control readers, doors and gates prior to new vendor RFP. | 0 | 0 | Physical Security ISL Application Replacement
24940 | ISOC Security Equipment | N.T.C.1.29 | 838 | 212 | INFO SOLUTIONS DIVISION | AIP006173 | AIP006173 | AIP006173 | No | AIP006173 | ISOC Physical Security Equipment | 0 |  | NERC Cyber Security Compliance Readiness | lincoln.frost-hunt@hydroone.com | Sherry.Wilging@hydroone.com | System Renewal | 0 | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 981019.0462 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 981019.0462 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43514 | 43847 | False |  | False |  | False |  | False | False |  | False | False | False | False | TRUE | This investment is to purchase physical security equipment for the new ISOC in Orillia | 0 | 0 | ISCO Physical Security Equipment
24941 | IT Service Management | N.T.C.1.29 | 838 | 212 | INFO SOLUTIONS DIVISION |  |  |  | No |  |  |  |  | NERC Cyber Security Compliance Readiness | lincoln.frost-hunt@hydroone.com | [6 empty] | Program | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24942 | NERC Sustainment Resources | N.T.M.1.29 | 838 | 212 | INFO SOLUTIONS DIVISION |  |  |  | No |  |  |  |  | NERC Cyber Security Compliance Readiness | lincoln.frost-hunt@hydroone.com | [6 empty] | Program | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24943 | NERC V7 Virtualization - Encryption - Third party | N.T.M.1.29 | 838 | 212 | INFO SOLUTIONS DIVISION | AIP006184 | AIP006184 | AIP006184 | No | AIP006184 | NERV v7 OMA for projects | 0 |  | NERC Cyber Security Compliance Readiness | lincoln.frost-hunt@hydroone.com | Sherry.Wilging@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 494248.4177 | 495639.3632 | 496541.8098 | 497661.6336 | 497844.8304 | 497998.4629 | 0 | 0 | 0 | 0 | 494248.4177 | 495639.3632 | 496541.8098 | 497661.6336 | 497844.8304 | 497998.4629 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43255 | 45289 | False |  | True | NERC Compliance CIP-012-1 | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | NERC v7 Encryption
24944 | ISL Replacement OMA | N.T.M.1.29 | 838 | 212 | INFO SOLUTIONS DIVISION | AIP006177 | AIP006177 | AIP006177 | No | AIP006177 | Physical Security ISL Application Replacement OMA | 0 |  | NERC Cyber Security Compliance Readiness | lincoln.frost-hunt@hydroone.com | Sherry.Wilging@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 197699.3671 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 197699.3671 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43115 | 43455 | False |  | True | CIP-006, 014, 004 | False |  | False | False |  | False | False | False | False | TRUE | The current ISL application is end-of-life and is proprietary to our current thrid party vendor Tyco for monitoring physical security. The contract with Tyco will expire in 2020. Plan is to implement new vendor augnostic application and migrate all the access control readers, doors and gates prior to new vendor RFP. | 0 | 0 | Physical Security ISL Application Replacement OMA
24945 | Tx Lines Idle Line Removal | N.T.C.1.12 | 7370 | 206 | TX LINES AND STATIONS | AIP006158 | AIP006158 | AIP006158 | No | AIP006158 | Tx Lines Idle Line Removal | 0 |  | Overhead Lines Component Refurb & Repl | hassan.hamzeh@hydroone.com | Tyler.Wales@HydroOne.com | System Renewal | 0 | 0 | 03 - None (default) | 0 | Program | ACTN EMPP | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2042000 | 2082839.96 | 2124496.76 | 2166986.72 | 2210326.52 | 2254532.96 | 0 | 0 | 0 | 0 | -2042000 | -2082839.96 | -2124496.76 | -2166986.72 | -2210326.52 | -2254532.96 | 0 | 0 | 0 | 0 | -100 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Asset Optimal
24946 | TWE - CMS Service Equipment | N.C.C.1.30 | 7370 | 206 | TX LINES AND STATIONS | AIP000014E | AIP000014 | AIP000014 | No | AIP000014 | Transport and Work Equipment (TWE) Capital Requirements | GP-13 | Transport & Work Equipment | Fleet | robert.berardi@HydroOne.com | angela.mallozzi@hydroone.com | General Plant | 0 | 0 | 03 - None (default) | 0 | Program | EMPP AWRD | Executing | Short Term Planning | # of Vehicles | 1794754.72 | 953801.017 | 964317.7766 | 971617.6438 | 978724.0213 | 989521.3868 | 0 | 0 | 0 | 0 | 1794754.72 | 953801.017 | 964317.7766 | 971617.6438 | 978724.0213 | 989521.3868 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | False |  | False | False | False | False | TRUE | Vehicles must be maintained at an optimum level to ensure public and employee safety, meet Ministry regulations such as CSA 225, Highway Trafffic Act, CVOR regulations. | 0 | 0 | Vulnerable (Modified - Tx Decision)
24947 | Outlier - D7V - Animal Abatement | N.T.C.2.20 | 7700 | 203 | PROJECT DELIVERY |  |  |  | No |  |  |  |  | Performance Enhancement | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24948 | Campbellville Pit Remediation - Recoverable | N.T.M.1.14 | 7700 | 203 | PROJECT DELIVERY | AIP006156 | AIP006156 | AIP006156 | No | AIP006156 | Campbellville Pit Remediation | 0 |  | Engineering and Environmental Support | Mike.Tanaskovic@HydroOne.com | Gian.Minichini@HydroOne.com | System O&M | 0 | 0 | 0 | 0 | Project | #N/A | Short Term Planning | Short Term Planning |  | 2942299.8945 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2942299.8945 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43101 | 43449 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Vulnerable
24949 | GIS: Migration to Cloud | N.C.C.2.60 | 4339 | 212 | INFO SOLUTIONS DIVISION | AIP006236 | AIP006236 | AIP006236 | No | AIP006236 | ENTERPRISE GIS Modernization: Migration to Cloud (Phase 1) | 0 |  | IT Business Solution Development | jj.blais@HydroOne.com | Tim.Nelson@hydroone.com | General Plant | 0 | 0 | 0 | 0 | Project | init | Short Term Planning | Short Term Planning |  | 440000.12 | 2639622.4802 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 440000.12 | 2639622.4802 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43069 | 43826 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | ENTERPRISE GIS Modernization: Migration to Cloud (Phase 1)
24950 | Metrolinx - Wilson (Don) Yard Relocations - Recov | N.T.C.1.14 | 7700 | 203 | PROJECT DELIVERY | AIP006168 | AIP006168 | AIP006168 | No | AIP006168 | Metrolinx - Wilson (Don) Yard Modifications - Recoverable | 0 |  | Third Party Transmission System Modifications | john.boldt@HydroOne.com | Gian.Minichini@HydroOne.com | System Renewal | Greater Toronto Area | 0 | 01 - Agreement (current/future) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000 | 3000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2000000 | -3000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43454 | 43814 | True | Metrolinx asked HONI to relocate overhead lines H9EJ/H10EJ and underground circuit H2JK to accommodate their track expansion project. | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Metrolinx - Wilson (Don) Yard Modifications - Recoverable
24951 | Metrolinx - Caldeonia GO Station - Recoverable | N.T.C.1.14 | 7700 | 203 | PROJECT DELIVERY | AIP006169 | AIP006169 | AIP006169 | No | AIP006169 | Metrolinx - Caledonia GO Station Modifications - Recoverable | 0 |  | Third Party Transmission System Modifications | john.boldt@HydroOne.com | Gian.Minichini@HydroOne.com | System Renewal | Greater Toronto Area | 0 | 01 - Agreement (current/future) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 14000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1000000 | -14000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43560 | 43814 | True | Metrolinx asked HONI to relocate K1W/K3W to accommodate their Caledonia GO station expansion project. | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Metrolinx - Caledonia GO Station Modifications - Recoverable
24952 | NextBridge - East-West Tie Line - Tx Mods - Recove | N.T.C.1.14 | 7700 | 203 | PROJECT DELIVERY | AIP006172 | AIP006172 | AIP006172 | No | AIP006172 | NextBridge - East-West Tie Line - Tx Mods - Recoverable | 0 |  | Third Party Transmission System Modifications | john.boldt@HydroOne.com | Gian.Minichini@HydroOne.com | System Renewal | Western | 0 | 01 - Agreement (current/future) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -500000 | -1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43560 | 43814 | True | NextBridge asked Hydro One to relocate line T1M to accommodate their proposed East-West Tie transmission line. | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | NextBridge - East-West Tie Line - Tx Mods - Recoverable
24953 | Enterprise Analytics – AA New Risk Factors | N.C.C.2.60 | 4339 | 212 | INFO SOLUTIONS DIVISION | AIP006127 | AIP006127 | AIP006127 | No | AIP006127 | Enterprise Analytics – AA New Risk Factors | 0 |  | IT Business Solution Development | jj.blais@HydroOne.com | hany.eskandar@hydroone.com | General Plant | 0 | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 4133062.2878 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4133062.2878 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43920 | 44196 | False |  | False |  | False |  | False | False |  | False | False | True | False | TRUE | The new Health Safety & Environment Risk Factor will improve investment decisions related to employee, public and environmental safety, investor, regulatory and media confidence. Obsolescence Risk Factor will improve investment decision data by providing a view of the asset’s ongoing sustainability. | 0 | 0 | Asset Optimal
24954 | Enterprise Analytics – Reliability Analytics/CP | N.C.C.2.60 | 4339 | 212 | INFO SOLUTIONS DIVISION | AIP006130 | AIP006130 | AIP006130 | No | AIP006130 | Enterprise Analytics – Reliability Analytics/CPR | 0 |  | IT Business Solution Development | jj.blais@HydroOne.com | hany.eskandar@hydroone.com | General Plant | 0 | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 3420831.5895 | 1407501.1654 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3420831.5895 | 1407501.1654 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43555 | 44194 | False |  | False |  | False |  | False | False |  | False | False | True | False | TRUE | This project is requested by Senior Mgmt since current tool presents unacceptable business reliability and continuity risks. It’s not supported by Corp. IT processes or Service Agreements. Integration with enterprise SAP self-service tools enables avoidance of the current third-party vendor costs. | 0 | 0 | Asset Optimal
24955 | Enterprise Analytics – AA New Risk Factors | N.C.M.2.60 | 4339 | 212 | INFO SOLUTIONS DIVISION | AIP006128 | AIP006128 | AIP006128 | No | AIP006128 | Enterprise Analytics – AA New Risk Factors | 0 |  | IT-Business Solution Development | jj.blais@HydroOne.com | hany.eskandar@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 110250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 110250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43920 | 44196 | False |  | False |  | False |  | False | False |  | False | False | True | False | TRUE | The new Health Safety & Environment Risk Factor will improve investment decisions related to employee, public and environmental safety, investor, regulatory and media confidence. Obsolescence Risk Factor will improve investment decision data by providing a view of the asset’s ongoing sustainability. | 0 | 0 | Vulnerable - Tx Contraint Reduction
24956 | Enterprise Analytics – Reliability Analytics/CPR | N.C.M.2.60 | 4339 | 212 | INFO SOLUTIONS DIVISION | AIP005504 | AIP005504 | AIP005504 | No | AIP005504 | Enterprise Analytics – Reliability Analytics/CPR | 0 |  | IT-Business Solution Development | jj.blais@HydroOne.com | hany.eskandar@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 223499.88 | 42050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 223499.88 | 42050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43646 | 44194 | False |  | False |  | False |  | False | False |  | False | False | True | False | TRUE | This project is requested by Senior Mgmt since current tool presents unacceptable business reliability and continuity risks. It’s not supported by Corp. IT processes or Service Agreements. Integration with enterprise SAP self-service tools enables avoidance of the current third-party vendor costs. | 0 | 0 | Vulnerable - Tx Contraint Reduction
24957 | System Reserve Equip-Operating Spares Corrective | N.T.M.1.16 | 7370 | 206 | TX LINES AND STATIONS | AIP006145 | AIP006145 | AIP006145 | No | AIP006145 | System Reserve Equipment - Operating Spares Corrective | 0 |  | Power Equipment | Mike.Tanaskovic@HydroOne.com | peter.zhao@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | ACTN EMPP | Executing | Short Term Planning | # of Orders | 290775.6309 | 289148.7034 | 289739.3597 | 290501.487 | 290640.0976 | 290778.088 | 0 | 0 | 0 | 0 | 290775.6309 | 289148.7034 | 289739.3597 | 290501.487 | 290640.0976 | 290778.088 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Intermediate - Tx Constraint Reduction
24958 | Edgeware TS M7M8 Asset Purchase | N.D.C.2.02 | 7374 | 205 | LINES | UNPLND |  |  | Yes |  |  |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24959 | Heritage Resources Management | N.C.M.3.03 | 4220 | 209 | HEALTH, SAFETY & ENV | AIP006249 | AIP006249 | AIP006249 | No | AIP006249 | Heritage Resource Management | 0 |  | Environment Health and Safety | welchw@hydroone.com | welchw@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | AWRD | Short Term Planning | Short Term Planning | Retainer | 107285.8 | 109431.52 | 111620.2 | 113852.56 | 116129.56 | 110000 | 0 | 0 | 0 | 0 | 107285.8 | 109431.52 | 111620.2 | 113852.56 | 116129.56 | 110000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | True | Ontario Heritage Act - Part III.1 and Ontario Regulation 157/10 | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Optimal - Modified
24960 | Transient Cyber Asset Sustainment | N.T.M.1.29 | 838 | 212 | INFO SOLUTIONS DIVISION |  |  |  | No |  |  |  |  | NERC Cyber Security Compliance Readiness | lincoln.frost-hunt@hydroone.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24962 | Completion of Q26M/Q35M Line Work | N.T.M.2.02 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Infrastructure Development | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | EXTR DETL | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24963 | Gardiner TS-M24-33250-Dx-Invista Swordfish | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000195 |  | AIP000195 | Yes | AIP000195 | Small Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24964 | Gardiner TS-M24-33250-Tx-Invista Swordfish | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24965 | Circuit Switchers for Outlier Improvement | N.T.C.2.20 | 7700 | 203 | PROJECT DELIVERY | AIP006247 | AIP006247 | AIP006247 | No | AIP006247 | Circuit Switchers for Outlier Improvement | 0 |  | Performance Enhancement | Robert.Reinmuller@HydroOne.com | Lukito.Adiputra@HydroOne.com | System Service | 0 | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 245405.8591 | 737816.7275 | 1464518.4719 | 1442372.8344 | 1429889.2688 | 1420661.8296 | 0 | 0 | 0 | 0 | 245405.8591 | 737816.7275 | 1464518.4719 | 1442372.8344 | 1429889.2688 | 1420661.8296 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43678 | 45261 | False |  | True | To comply with Customer Delivery Point Performance Standard (CDPPS) | False |  | False | True | Based on recent customer survey, most consider reliability to be extremely important. This investment is proposed to improve the reliability of some of the worst performing delivery points (outliers)” | False | False | False | False | TRUE | The project is required to improve reliability of customer delivery point performance, as mandated by the Transmission System Code (TSC) | 0 | 0 | Circuit Switchers
24967 | Outlier - M9K - Lightning | N.T.C.2.20 | 7700 | 203 | PROJECT DELIVERY |  |  |  | No |  |  |  |  | Performance Enhancement | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24968 | Outlier - S2B-e - Line Assessment | N.T.C.2.20 | 7700 | 203 | PROJECT DELIVERY |  |  |  | No |  |  |  |  | Performance Enhancement | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24969 | Outlier - S5M- Line Assessment | N.T.C.2.20 | 7700 | 203 | PROJECT DELIVERY |  |  |  | No |  |  |  |  | Performance Enhancement | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24970 | Outlier - P15T/P7G- Line Assessment | N.T.C.2.20 | 7700 | 203 | PROJECT DELIVERY |  |  |  | No |  |  |  |  | Performance Enhancement | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24971 | Outlier - A4L - Fault Locator | N.T.C.2.20 | 7700 | 203 | PROJECT DELIVERY |  |  |  | No |  |  |  |  | Performance Enhancement | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24972 | Haldimand-Jarvis TS M6 Lakeshore Rebuild | N.D.C.1.07 | 7374 | 205 | LINES | UNPLND |  |  | Yes |  |  |  |  | Lines | emre.aydin@HydroOne.com | [6 empty] | Project | DETL ACTN | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24973 | Outlier - Animal Abatement Projects | N.T.C.2.20 | 7700 | 203 | PROJECT DELIVERY |  |  |  | No |  |  |  |  | Performance Enhancement | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24974 | Outlier - Lightning Protection Projects | N.T.C.2.20 | 7700 | 203 | PROJECT DELIVERY |  |  |  | No |  |  |  |  | Performance Enhancement | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24975 | Outlier - Line Sectionalizer Projects | N.T.C.2.20 | 7700 | 203 | PROJECT DELIVERY |  |  |  | No |  |  |  |  | Performance Enhancement | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24976 | P&C Sparing Plan | N.T.M.1.17 | 7700 | 203 | PROJECT DELIVERY | AIP006251 | AIP006251 | AIP006251 | No | AIP006251 | P&C Sparing Plan | 0 |  | Protection Control & Metering Equipment | Miroslav.Kostic@HydroOne.com | Sasa.Maljukan@HydroOne.com | System O&M | N/A | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 203514.2559 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 203514.2559 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43449 | 0 | False |  | False |  | False |  | True | False |  | False | False | False | False | FALSE |  | 0 | 0 | Asset Optimal
24979 | Otonabee TS - M28 - ID32570 - SFF08 | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000195 |  | AIP000195 | Yes | AIP000195 | Small Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24980 | GIS: Field Network Design Replacement | N.C.C.2.60 | 4339 | 212 | INFO SOLUTIONS DIVISION | AIP006238 | AIP006238 | AIP006238 | No | AIP006238 | ENTERPRISE GIS Modernization: Field Network Design Replacement (Phase 2) | 0 |  | IT Business Solution Development | jj.blais@HydroOne.com | Tim.Nelson@hydroone.com | General Plant | 0 | 0 | 0 | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 1281504.9664 | 1563600.8987 | 820156.0273 | 192533.8977 | 191034.1118 | 0 | 0 | 0 | 0 | 0 | 1281504.9664 | 1563600.8987 | 820156.0273 | 192533.8977 | 191034.1118 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43404 | 44463 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | ENTERPRISE GIS Modernization: Field Network Design Replacement (Phase 2)
24981 | GIS: SAP Data Improvement and OMS Consolidation | N.C.C.2.60 | 4339 | 212 | INFO SOLUTIONS DIVISION | AIP006240 | AIP006240 | AIP006240 | No | AIP006240 | ENTERPRISE GIS Platform: SAP Data Quality Improvement and OMS Database Consolidation | 0 |  | IT Business Solution Development | jj.blais@HydroOne.com | Tim.Nelson@hydroone.com | General Plant | 0 | 0 | 0 | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 878908.5855 | 1592067.4768 | 476334.9894 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 878908.5855 | 1592067.4768 | 476334.9894 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43769 | 44736 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | ENTERPRISE GIS Modernization: Field Network Design Replacement (Phase 2)
24982 | GIS: Customer GIS + Legacy System Consolidation | N.C.C.2.60 | 4339 | 212 | INFO SOLUTIONS DIVISION | AIP006242 | AIP006242 | AIP006242 | No | AIP006242 | ENTERPRISE GIS Platform: Customer Facing GIS and Legacy Systems Consolidation | 0 |  | IT Business Solution Development | jj.blais@HydroOne.com | Tim.Nelson@hydroone.com | General Plant | 0 | 0 | 0 | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 1714806.0806 | 2077466.0362 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1714806.0806 | 2077466.0362 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44500 | 45282 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | ENTERPRISE GIS Platform: Customer Facing GIS and Legacy Systems Consolidation
24983 | GIS: Migration to Cloud-OMA | N.C.M.2.60 | 4339 | 212 | INFO SOLUTIONS DIVISION | AIP006237 | AIP006237 | AIP006237 | No | AIP006237 | ENTERPRISE GIS Modernization: Migration to Cloud (Phase 1) - OMA | 0 |  | IT-Business Solution Development | jj.blais@HydroOne.com | Tim.Nelson@hydroone.com | System O&M | 0 | 0 | 0 | 0 | Project | init | Short Term Planning | Short Term Planning |  | 110000 | 90000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 110000 | 90000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43069 | 43826 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Vulnerable - Tx Contraint Reduction
24984 | GIS: Field Network Design Replacement - OMA | N.C.M.2.60 | 4339 | 212 | INFO SOLUTIONS DIVISION | AIP006239 | AIP006239 | AIP006239 | No | AIP006239 | ENTERPRISE GIS Modernization: Field Network Design Replacement (Phase 2) - OMA | 0 |  | IT-Business Solution Development | jj.blais@HydroOne.com | Tim.Nelson@hydroone.com | System O&M | 0 | 0 | 0 | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 88000 | 80000 | 42500 | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 88000 | 80000 | 42500 | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43769 | 44828 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Vulnerable - Tx Contraint Reduction
24985 | GIS:SAP Data Improvement and OMS Consolidation-OMA | N.C.M.2.60 | 4339 | 212 | INFO SOLUTIONS DIVISION | AIP006241 | AIP006241 | AIP006241 | No | AIP006241 | ENTERPRISE GIS Platform: SAP Data Quality Improvement and OMS Database Consolidation - OMA | 0 |  | IT-Business Solution Development | jj.blais@HydroOne.com | Tim.Nelson@hydroone.com | System O&M | 0 | 0 | 0 | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 45000.12 | 82500 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000.12 | 82500 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43769 | 44736 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Vulnerable - Tx Contraint Reduction
24986 | GIS:Customer GIS + Legacy System Consolidation-OMA | N.C.M.2.60 | 4339 | 212 | INFO SOLUTIONS DIVISION | AIP006243 | AIP006243 | AIP006243 | No | AIP006243 | ENTERPRISE GIS Platform: Customer Facing GIS and Legacy Systems Consolidation - OMA | 0 |  | IT-Business Solution Development | jj.blais@HydroOne.com | Tim.Nelson@hydroone.com | System O&M | 0 | 0 | 0 | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 90000.12 | 110000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90000.12 | 110000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44500 | 45282 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Vulnerable - Tx Contraint Reduction
24987 | Dx Zone 2 InterPhase Spacer Pilot Project | N.D.C.2.02 | 7374 | 205 | LINES | UNPLND |  |  | Yes |  |  |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24988 | Bill Redesign - C&I Customers - Capital | N.D.C.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION | UNPLND |  |  | Yes |  |  |  |  | IT Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24989 | CDM Online Shopping Tool | N.D.C.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION |  |  |  | No |  |  |  |  | IT Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24990 | RAS Procedures | N.T.M.1.17 | 7716 | 224 | ENGINEERING | AIP006253 | AIP006253 | AIP006253 | No | AIP006253 | Preparation of RAS Maintenance Procedures | 0 |  | Protection Control & Metering Equipment | Miroslav.Kostic@HydroOne.com | Murched.Ajami@HydroOne.com | System O&M | N/A | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 297383.6179 | 198616.7239 | 99532.3267 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 297383.6179 | 198616.7239 | 99532.3267 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43466 | 44287 | False |  | True | NERC PRC-005-6 and NERC PRC-012-2 | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Asset Optimal
24991 | Synchrophasors (PMU) | N.T.C.3.08 | 7700 | 203 | PROJECT DELIVERY | AIP006252 | AIP006252 | AIP006252 | No | AIP006252 | Synchrophasors (PMU) | 0 |  | Integrating Operating Infrastructure | Miroslav.Kostic@HydroOne.com | alan.wong@hydroone.com | General Plant | N/A | Not Required | 03 - None (default) | Not Required | Project | init | Short Term Planning | Short Term Planning |  | 0 | 594611.4512 | 982815.8422 | 971008.2453 | 959202.3244 | 0 | 0 | 0 | 0 | 0 | 0 | 594611.4512 | 982815.8422 | 971008.2453 | 959202.3244 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43465 | 44910 | True | IESO has requested the implementation of Synchrophasors | True | Synchrophasors will be mandated by the IESO through market rules | True |  | False | False |  | False | False | False | True | FALSE |  | 0 | 0 | Asset Optimal
24992 | Safety by Design | N.T.M.1.14 | 7716 | 224 | ENGINEERING | AIP006248 | AIP006248 | AIP006248 | No | AIP006248 | Safety by Design | 0 |  | Engineering and Environmental Support | Mike.Tanaskovic@HydroOne.com | Farinaz.Yousefi@HydroOne.com | System O&M | N/A | 0 | 03 - None (default) | 0 | Program | EMPP ACCP | Executing | Short Term Planning | Retainer | 98849.6835 | 99127.8726 | 99308.362 | 99532.3267 | 99568.9581 | 99599.6926 | 0 | 0 | 0 | 0 | 98849.6835 | 99127.8726 | 99308.362 | 99532.3267 | 99568.9581 | 99599.6926 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Intermediate
24993 | Bala River DS F2 ID 28600 - DX - Little Burgess GS | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | Distribution Generation Connection | ryan.boudreau@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24994 | Bala River DS F2 ID 28600 - TX - Little Burgess GS | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP005760 |  | AIP005760 | Yes | AIP005760 | Placeholder for Upstream Tx Work for DG (Project) |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24995 | IVR Redesign - Capital | N.D.C.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION |  |  |  | No |  |  |  |  | IT Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24996 | Smart Meter Replacement - Capital | N.D.C.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION |  |  |  | No |  |  |  |  | IT Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24997 | Web Redesign 2.0 - Capital | N.D.C.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION |  |  |  | No |  |  |  |  | IT Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24998 | Bill Redesign - C&I Customers - OMA | N.D.M.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION |  |  |  | No |  |  |  |  | IT Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24999 | CDM Online Shopping Tool | N.D.M.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION |  |  |  | No |  |  |  |  | IT Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25000 | IVR Redesign - OMA | N.D.M.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION |  |  |  | No |  |  |  |  | IT Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25001 | Smart Meter Replacement - OMA | N.D.M.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION |  |  |  | No |  |  |  |  | IT Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25002 | Web Redesign 2.0 - OMA | N.D.M.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION |  |  |  | No |  |  |  |  | IT Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25003 | Corporate Mobility - CAP | N.C.C.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION |  |  |  | No |  |  |  |  | IT Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25004 | Corporate Mobility - OMA | N.C.M.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION |  |  |  | No |  |  |  |  | IT-Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25005 | Otonabee TS - M28 - ID32570 - Tx - SFF08 | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP005760 |  | AIP005760 | Yes | AIP005760 | Placeholder for Upstream Tx Work for DG (Project) |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25006 | L7S - Reliability Performance Mitigation | N.T.M.2.02 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Infrastructure Development | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | ACTN BEST | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25007 | Lake TS M4M6 Rebuild | N.D.C.2.02 | 7370 | 206 | TX LINES AND STATIONS | UNPLND |  |  | Yes |  |  |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | [6 empty] | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25008 | Otonabee TS - M28 - ID33630 - Tx - 741-JP-BLK W PL | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP005760 |  | AIP005760 | Yes | AIP005760 | Placeholder for Upstream Tx Work for DG (Project) |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25010 | Lauzon TS M7 - ID33510 TX WFCU Centre CHP Project | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25011 | Kleinburg TS M25 ID34330 DX - Husky Energy Strg-CA | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000199 |  | AIP000199 | Yes | AIP000199 | Large Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25012 | Kleinburg TS M25 ID34330 TX - Husky Energy Strg | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP005760 |  | AIP005760 | Yes | AIP005760 | Placeholder for Upstream Tx Work for DG (Project) |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25013 | Lake TS M4M6 Rebuild | N.D.C.2.02 | 7374 | 205 | LINES | UNPLND |  |  | Yes |  |  |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | [6 empty] | Project | BEST init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25014 | Crawford TS M11 ID34550 TX - Aquatic Centre CHP | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP005760 |  | AIP005760 | Yes | AIP005760 | Placeholder for Upstream Tx Work for DG (Project) |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25016 | Physical Access Monitoring Upgrade | N.T.C.1.29 | 4339 | 212 | INFO SOLUTIONS DIVISION | AIP006275 | AIP006275 | AIP006275 | No | AIP006275 | Physical Access Monitoring Upgrade | 0 |  | NERC Cyber Security Compliance Readiness | lincoln.frost-hunt@hydroone.com | Sherry.Wilging@hydroone.com | System Renewal | 0 | 0 | 0 | 0 | Project | init | Short Term Planning | Short Term Planning |  | 149156.1268 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 149156.1268 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43190 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Physical Access Monitoring Upgrade
25017 | Physical Security Spare Inventory | N.T.C.1.29 | 4342 | 212 | INFO SOLUTIONS DIVISION |  |  |  | No |  |  |  |  | NERC Cyber Security Compliance Readiness | lincoln.frost-hunt@hydroone.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25018 | Customer Digital Enhancements - Capital | N.D.C.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION | UNPLND |  |  | Yes |  |  |  |  | IT Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25019 | Customer Digital Enhancements - OMA | N.D.M.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION |  |  |  | No |  |  |  |  | IT Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25020 | Norfolk-Bloomsburg DS M3 Recloser and Regulator | N.D.C.2.02 | 7374 | 205 | LINES | UNPLND |  |  | Yes |  |  |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | [6 empty] | Project | ACTN EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25021 | Otonabee TS - M28 - ID31900 - Dx - GGELP_0026 | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000195 |  | AIP000195 | Yes | AIP000195 | Small Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25022 | Chapleau DS - Borden Mine 7 MW Load Connection | N.D.C.2.02 | 7700 | 203 | PROJECT DELIVERY | AIP005381 |  | AIP005381 | Yes | AIP005381 | Manitou Lake DS & Line Work | ISD-SR-13 | Life Cycle Optimization & Operational Efficiency Projects | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Gert.Alikaj@HydroOne.com | System Renewal | Northern | Not Required | 02 - Expectation (no agreement) | In Progress | Project | DETL ACTN | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25023 | Muskoka TS M8 ID35020 DX - 1.21GW Lancelot | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000191 |  | AIP000191 | Yes | AIP000191 | Small Embedded Generation | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 03 - None (default) | 0 | Project | ACCP EMPP | Executing | Executing | # of Gen Connections | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25024 | Muskoka TS M8 ID35020 TX - 1.21GW Lancelot | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP005760 |  | AIP005760 | Yes | AIP005760 | Placeholder for Upstream Tx Work for DG (Project) |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25025 | Sidney TS - M4 - ID31530 - Dx - Trenton Lock 1 | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000195 |  | AIP000195 | Yes | AIP000195 | Small Embedded Generation (E/PD) |  |  | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | init EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25026 | Sidney TS - M4 - ID31530 - Tx - Trenton Lock 1 | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000195 |  | AIP000195 | Yes | AIP000195 | Small Embedded Generation (E/PD) |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | init EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25027 | Otonabee TS - M28 - ID33630 - Dx - 741-JP-BLK W PL | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000195 |  | AIP000195 | Yes | AIP000195 | Small Embedded Generation (E/PD) |  |  | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25030 | SIA App: ID35640-Picton TS-White Pines Wind Farm | N.D.M.2.03 | 4048 | 213 | PLANNING | UNPLND |  |  | Yes |  |  |  |  | Distributed Generation Connections | ryan.boudreau@HydroOne.com | [6 empty] | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25031 | Otonabee TS - M28 - ID31900 - Tx - GGELP_0026 | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP005760 |  | AIP005760 | Yes | AIP005760 | Placeholder for Upstream Tx Work for DG (Project) |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25032 | Lake Superior Link - Development | N.T.M.2.02 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Infrastructure Development | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25035 | McCrimmon DS F3 ID33240 Dx Sen Biogas 2 | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000195 |  | AIP000195 | Yes | AIP000195 | Small Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25036 | McCrimmon DS F3 ID33240 Tx Senn Biogas 2 | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP005760 |  | AIP005760 | Yes | AIP005760 | Placeholder for Upstream Tx Work for DG (Project) |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25037 | NOVA Corunna CTS T2 Transformer Relocation | N.T.C.2.11 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Load Customer Connection | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25038 | OGCC DC Cooling Enhancements | N.C.C.3.01 | 4514 | 212 | INFO SOLUTIONS DIVISION | AIP006273 | AIP006273 | AIP006273 | No | AIP006273 | OGCC Data Centre Cooling Enhancements | 0 |  | Common Oper Infrast & Control Facilities | Godfrey.Holder@HydroOne.com | mallen@hydroone.com | General Plant | 0 | 0 | 03 - None (default) | 0 | Project | EMPP AWRD | Executing | Executing |  | 840000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 840000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43158 | 43158 | False |  | False |  | False |  | True | False |  | False | False | False | False | TRUE | This comment applies to "Corrective Maintenance/Demad Replacements": This investment will allow for the systimatic replacement of EOL assets located at the OGCC data center and correct the know issues including the single point of failure in the cooling heat rejection system. | 0 | 0 | Asset Optimal
25039 | OGCC Data Centre Remediation | N.C.C.3.01 | 4514 | 212 | INFO SOLUTIONS DIVISION | AIP006274 | AIP006274 | AIP006274 | No | AIP006274 | OGCC Data Centre Remediation - Discovery | 0 |  | Common Oper Infrast & Control Facilities | Godfrey.Holder@HydroOne.com | mallen@hydroone.com | General Plant | 0 | 0 | 03 - None (default) | 0 | Project | AWRD EMPP | Executing | Executing |  | 3199999.88 | 3186312.7567 | 1184355.0801 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3199999.88 | 3186312.7567 | 1184355.0801 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43158 | 44165 | False |  | False |  | False |  | True | False |  | False | False | False | False | TRUE | This comment applies to "Corrective Maintenance/Demad Replacements": This investment will allow for the systimatic replacement of EOL assets located at the OGCC data center and correct the know issues including the single point of failure in the cooling heat rejection system. | 0 | 0 | Asset Optimal
25040 | SIA Application: Peace Naturals 12MW - Stayner TS | N.D.M.2.02 | 4048 | 213 | PLANNING | UNPLND |  |  | Yes |  |  |  |  | Engineering and Technical Services | ted.lyberogiannis@HydroOne.com | [6 empty] | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25042 | Wanstead TS M4 ID33690 TX - Union Gas - Dawn Exp. | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP005760 |  | AIP005760 | Yes | AIP005760 | Placeholder for Upstream Tx Work for DG (Project) |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25043 | Wanstead TS M4 ID33690 DX - Union Gas - Dawn Exp | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000191 |  | AIP000191 | Yes | AIP000191 | Small Embedded Generation | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 03 - None (default) | 0 | Project | ACTN EMPP | Executing | Executing | # of Gen Connections | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25044 | Lindsay TS - M7 - ID 34000 - SCI CE9_Tx | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP005760 |  | AIP005760 | Yes | AIP005760 | Placeholder for Upstream Tx Work for DG (Project) |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25045 | To be allocated | N.T.C.1.29 | 4342 | 212 | INFO SOLUTIONS DIVISION |  |  |  | No |  |  |  |  | NERC Cyber Security Compliance Readiness | lincoln.frost-hunt@hydroone.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25046 | Thornton TS - M1 and M8 - ID34110 - TX - Class A | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP005760 |  | AIP005760 | Yes | AIP005760 | Placeholder for Upstream Tx Work for DG (Project) |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | ACTN DETL | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25047 | Birch TS M6 ID 35060 TX Lakehead University Cogen | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP005760 |  | AIP005760 | Yes | AIP005760 | Placeholder for Upstream Tx Work for DG (Project) |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25050 | Lindsay TS - M7 - ID 34000 - SCI CE9_Dx | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000195 |  | AIP000195 | Yes | AIP000195 | Small Embedded Generation (E/PD) |  |  | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25055 | Call Center Repatriation Project - Capital | N.D.C.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION | UNPLND |  |  | Yes |  |  |  |  | IT Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25056 | 2018 RPP Road Map Pricing Pilot - OEB | N.D.M.2.50 | 1144 | 220 | STRATEGY & CONSERV | UNPLND |  |  | Yes |  |  |  |  | Conservation and Demand Management | Imran.Merali@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25060 | Call Center Repatriation Project - OMA | N.D.M.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION |  |  |  | No |  |  |  |  | IT Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25061 | Belleville TS - Station Refurbishment | N.T.C.1.44 | 7700 | 203 | PROJECT DELIVERY | AIP006254 | AIP006254 | AIP006254 | No | AIP006254 | Belleville TS- Station Refurbishment | SR-02 | Station Reinvestment Projects | Eastern Zone Station/Yard Investments | James.Mardegan@HydroOne.com | Fred.Kouhdani@HydroOne.com | System Renewal | 0 | 0 | 0 | 0 | Project | init BEST | Short Term Planning | Short Term Planning |  | 736346.3094 | 6487009.2458 | 10847123.0254 | 3539467.1601 | 0 | 0 | 0 | 0 | 0 | 0 | 791770.2252 | 6975278.7589 | 11663573.1456 | 3805878.6668 | 0 | 0 | 0 | 0 | 0 | 0 | -55423.9158 | -488269.5131 | -816450.1202 | -266411.5067 | 0 | 0 | 0 | 0 | 0 | 0 | -7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43853 | 44545 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Alternative 1
25065 | Havelock TS-M2-ID33970-Tx-SCI HA2 | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25066 | Havelock TS-M2-ID33970-Dx-SCI HA2 | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000195 |  | AIP000195 | Yes | AIP000195 | Small Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25067 | Stewartville TS-M1-ID35350-Dx-SCI RE9 | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000195 |  | AIP000195 | Yes | AIP000195 | Small Embedded Generation (E/PD) |  |  | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | init EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25068 | Stewartville TS-M1-ID35350-Tx-SCI RE9 | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP005760 |  | AIP005760 | Yes | AIP005760 | Placeholder for Upstream Tx Work for DG (Project) |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | init EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25069 | Stewartville TS-M1-ID35370-Dx-SCI RE11 | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000195 |  | AIP000195 | Yes | AIP000195 | Small Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | EMPP init | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25070 | Stewartville TS-M1-ID35370-Tx-SCI RE11 | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP005760 |  | AIP005760 | Yes | AIP005760 | Placeholder for Upstream Tx Work for DG (Project) |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | init EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25071 | Orillia TS - M2 - ID33430 - Dx - 734-DT-PT LT 15 | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000195 |  | AIP000195 | Yes | AIP000195 | Small Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25072 | Orillia TS - M2 - ID33430 - Tx - 734-DT-PT LT 15 | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP005760 |  | AIP005760 | Yes | AIP005760 | Placeholder for Upstream Tx Work for DG (Project) |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25073 | Orillia TS - M2 - ID33490 - Dx - 749-DT-7663 | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000195 |  | AIP000195 | Yes | AIP000195 | Small Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25074 | Orillia TS - M2 - ID33490 - Tx - 749-DT-7663 | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP005760 |  | AIP005760 | Yes | AIP005760 | Placeholder for Upstream Tx Work for DG (Project) |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25075 | Brant–Powerline Rd Line Relocation–Recoverable | N.T.C.1.14 | 7700 | 203 | PROJECT DELIVERY | AIP000512 |  | AIP000512 | Yes | AIP000512 | Recoverable projects to be identified - Placeholder |  |  | Third Party Transmission System Modifications | john.boldt@HydroOne.com | Gian.Minichini@HydroOne.com | System Renewal | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACTN DETL | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25076 | 2018 Saugeen FN Geothermal Heat Pump Pilot | N.D.M.2.50 | 1144 | 220 | STRATEGY & CONSERV | UNPLND |  |  | Yes |  |  |  |  | Conservation and Demand Management | Imran.Merali@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25080 | Kingsville TS: T1,T3 & Component Repl Phase 2 | N.T.C.1.40 | 7700 | 203 | PROJECT DELIVERY | AIP006280 | AIP006280 | AIP006280 | No | AIP006280 | Kingsville TS: T1, T2, T3, T4 & Component Replacement Phase 2 | SR-05 | Load Station Transformer Replacement Projects | Western Zone Station/Yard Investments | James.Mardegan@HydroOne.com | mark.truchanowicz@hydroone.com | System Renewal | Western | Not Required | 03 - None (default) | Not Required | Project | init | Short Term Planning | Short Term Planning |  | 964639.9581 | 1416316.3795 | 9232903.2152 | 3532616.5919 | 0 | 0 | 0 | 0 | 0 | 0 | 964639.9581 | 1416316.3795 | 9232903.2152 | 3532616.5919 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43647 | 44545 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Component Replacement (Accelerated)
25081 | Distribution Line Spacers | N.D.C.2.02 | 7374 | 205 | LINES | UNPLND |  |  | Yes |  |  |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25082 | Hurondale DS Padmount Transformers | N.D.C.2.02 | 7374 | 205 | LINES | UNPLND |  |  | Yes |  |  |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | [6 empty] | Project | ACTN DETL | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25083 | GORMS to FDGIS Migration Project | N.D.C.3.08 | 4514 | 212 | INFO SOLUTIONS DIVISION | UNPLND |  |  | Yes |  |  |  |  | Operating Infrastructure | Godfrey.Holder@HydroOne.com | [6 empty] | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25085 | Orillia TS - M2 - ID33420 - Dx - 868-DT-6989 CON | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000195 |  | AIP000195 | Yes | AIP000195 | Small Embedded Generation (E/PD) |  |  | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25086 | Orillia TS - M2 - ID33420 - Tx - 868-DT-6989 CON | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP005760 |  | AIP005760 | Yes | AIP005760 | Placeholder for Upstream Tx Work for DG (Project) |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25087 | Orillia TS - M2 - ID33460 - Dx - 865-DT-7181 | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000195 |  | AIP000195 | Yes | AIP000195 | Small Embedded Generation (E/PD) |  |  | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25088 | Orillia TS - M2 - ID33460 - Tx - 865-DT-7181 | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP005760 |  | AIP005760 | Yes | AIP005760 | Placeholder for Upstream Tx Work for DG (Project) |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25089 | Orillia TS - M2 - ID33470 - Dx - 869-DT-7868 Cronk | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000195 |  | AIP000195 | Yes | AIP000195 | Small Embedded Generation (E/PD) |  |  | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25090 | Orillia TS - M2 - ID33470 - Tx - 869-DT-7868 Cronk | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP005760 |  | AIP005760 | Yes | AIP005760 | Placeholder for Upstream Tx Work for DG (Project) |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25091 | Security Operation - Threat Hunting Cap Proj | N.C.C.1.70 | 838 | 212 | INFO SOLUTIONS DIVISION | AIP006122B | AIP006122 | AIP006122 | No | AIP006122 | Security Operations - Threat Hunting Capital Project | 0 |  | IT - Sustainment and Operations | lincoln.frost-hunt@hydroone.com | Sherry.Wilging@hydroone.com | General Plant | 0 | 0 | 0 | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 1416516.7176 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1416516.7176 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43605 | 45289 | False |  | False |  | False |  | False | False |  | False | False | False | False | TRUE | IT Operational Security Maturity and Capability Upgrade: Shift from a Reactive to Proactive Continuous Approach by improving areas such as penetration testing, Advance Persistent Threat (detect) and threat hunting (protect) etc. Jan 2017, RSA deployed a threat hunting technology to determine if Hydro One had been compromised by the malware Grizzly Steppe. This technology is starting to be deployed by more organization and is becoming main stream tool against cyber-attacks. | 0 | 0 | Security Operations - Threat Hunting Capital Project
25092 | Physical Security for Critical Stations | N.T.C.1.29 | 7700 | 203 | PROJECT DELIVERY | AIP006281 | AIP006281 | AIP006281 | No | AIP006281 | Physical Security for Critical Stations (non CIP-014) Med Criticality | SR-17 | Critical Station Physical Security Implementation (Non CIP-014) | NERC Cyber Security Compliance Readiness | lincoln.frost-hunt@hydroone.com | Sherry.Wilging@hydroone.com | System Renewal | 0 | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 5549706.9179 | 5503768.7162 | 5437646.1734 | 5371533.0166 | 5325417.3125 | 0 | 0 | 0 | 0 | 0 | 5549706.9179 | 5503768.7162 | 5437646.1734 | 5371533.0166 | 5325417.3125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43555 | 45275 | False |  | False |  | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Non-CIP14 Critical Stations (Med)
25093 | CIP-014 Physical Security Implementation | N.T.C.1.29 | 7700 | 203 | PROJECT DELIVERY | AIP006282 | AIP006282 | AIP006282 | No | AIP006282 | CIP-014 Physical Security Implementation | SR-16 | NERC CIP-014 Physical Security Implementation | NERC Cyber Security Compliance Readiness | lincoln.frost-hunt@hydroone.com | Sherry.Wilging@hydroone.com | System Renewal | 0 | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 11892229.0247 | 11793790.1061 | 11652098.943 | 11510427.8927 | 0 | 0 | 0 | 0 | 0 | 0 | 11892229.0247 | 11793790.1061 | 11652098.943 | 11510427.8927 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43555 | 44910 | False |  | True | CIP-014 | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | CIP 14 Stations
25094 | Lindsay TS - M6 - ID 34030 - Lakeview2 GM Sola_Dx | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000195 |  | AIP000195 | Yes | AIP000195 | Small Embedded Generation (E/PD) |  |  | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25095 | RD&D Project - Tx Grid Modernization&EnergyStorage | N.T.M.2.21 | 4230 | 213 | PLANNING | AIP005726 | AIP005726 | AIP005726 | No | AIP005726 | RD&D Project - Tx Grid Modernization & Energy Storage | 0 |  | Technology Program | Daila.Dzintars@HydroOne.com | janet.eby@Hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 1982557.4528 | 2025890.5839 | 2071267.7189 | 2112853.291 | 0 | 0 | 0 | 0 | 0 | 0 | 1982557.4528 | 2025890.5839 | 2071267.7189 | 2112853.291 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | False |  | False |  | False | False |  | False | False | False | False | TRUE | Hydro One needs to keep pace with the changes in technologies and consider ameliorating technologies (e.g. energy storage) in order to maintain system reliability in these challenging circumstances. Further, RD&D results in solutions to assist the company in doing current work better, faster and more economically - all of which can affect reliability. In order to improve system reliability, Hydro One needs to conduct rigorous demonstration/field testing of various types of new technologies, and ensure knowledge transfer to internal LOBs. | 0 | 0 | Vulnerable - Modified
25096 | Distance to Fault | N.T.C.3.08 | 7700 | 203 | PROJECT DELIVERY | AIP005769 | AIP005769 | AIP005769 | No | AIP005769 | Distance to Fault | 0 |  | Integrating Operating Infrastructure | Miroslav.Kostic@HydroOne.com | Jacek.Kliber@HydroOne.com | General Plant | 0 | 0 | 03 - None (default) | 0 | Program | init | Short Term Planning | Short Term Planning |  | 0 | 263693.0935 | 1600443.6176 | 1612840.1316 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 263693.0935 | 1600443.6176 | 1612840.1316 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43657 | 44561 | False |  | False |  | False |  | False | False |  | False | False | True | True | TRUE | This investment will lead to reduced OM&A with savings of over $1M/year. Outage times can also be greatly reduced and employee safety is also a direct benefit of this initiative as it will reduce number of kilometers driven and flown in the effort to locate faults. | 0 | 0 | Asset Optimal
25097 | Carbon Cap & Trade Program | N.T.M.1.05 | 4208 | 209 | HEALTH, SAFETY & ENV | AIP006188 | AIP006188 | AIP006188 | No | AIP006188 | Carbon Cap & Trade Program | 0 |  | Environmental Management | Mike.Tanaskovic@HydroOne.com | Sebastian.Niculae@HydroOne.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | init | Short Term Planning | Short Term Planning |  | 3027765.8069 | 2064674.9429 | 2426273.3779 | 2588222.7384 | 2750998.8285 | 2919160.3379 | 0 | 0 | 0 | 0 | 3027765.8069 | 2064674.9429 | 2426273.3779 | 2588222.7384 | 2750998.8285 | 2919160.3379 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False |  | True | Climate Change Mitigation and Low-carbon Economy Act, 2016; Ontario Regulation 144/16: The Cap and Trade Program | False |  | False | False |  | False | False | False | False | FALSE |  | 0 | 0 | Asset Optimal
25098 | Beaverton TS - M26 - ID 33990 - SCI CE2_Dx | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000195 |  | AIP000195 | Yes | AIP000195 | Small Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25099 | Beaverton TS - M26 - ID 33960 - SCI CE5_Dx | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000195 |  | AIP000195 | Yes | AIP000195 | Small Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25100 | Orillia TS - M2 - ID33410 - Dx - 831-DT-5714 Allan | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000195 |  | AIP000195 | Yes | AIP000195 | Small Embedded Generation (E/PD) |  |  | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25101 | Orillia TS - M2 - ID33410 - Tx - 831-DT-5714 Allan | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP005760 |  | AIP005760 | Yes | AIP005760 | Placeholder for Upstream Tx Work for DG (Project) |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25102 | Midhurst TS - M4 - ID34210 - Dx -LSRA Solar | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000195 |  | AIP000195 | Yes | AIP000195 | Small Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25103 | Affordability Fund Trust | N.D.M.2.50 | 1144 | 220 | STRATEGY & CONSERV | UNPLND |  |  | Yes |  |  |  |  | Conservation and Demand Management | Imran.Merali@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25104 | Contact Centre Transition - Discovery | N.D.M.4.01 | 4175 | 202 | CUSTOMER CARE SERVICES | UNPLND |  |  | Yes |  |  |  |  | Customer Care Services Dx | Imran.Merali@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25105 | Lindsay TS - M6 - ID 34030 - Lakeview2 GM Sola_Tx | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP005760 |  | AIP005760 | Yes | AIP005760 | Placeholder for Upstream Tx Work for DG (Project) |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25106 | Battersea HVDS-F1-ID34830-Dx-William Benjamin Grn | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000195 |  | AIP000195 | Yes | AIP000195 | Small Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25107 | Otonabee TS - M28 - ID 33940 - SCI NO1_Dx | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000195 |  | AIP000195 | Yes | AIP000195 | Small Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25108 | Otonabee TS - M28 - ID 33940 - SCI NO1_Tx | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP005760 |  | AIP005760 | Yes | AIP005760 | Placeholder for Upstream Tx Work for DG (Project) |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25109 | Otonabee TS - M28 - ID 33980 - SCI OT1_Dx | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000195 |  | AIP000195 | Yes | AIP000195 | Small Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25110 | Beaverton TS - M26 - ID 33990 - SCI CE2_Tx | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP005760 |  | AIP005760 | Yes | AIP005760 | Placeholder for Upstream Tx Work for DG (Project) |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25111 | Beaverton TS - M26 - ID 33960 - SCI CE5_Tx | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP005760 |  | AIP005760 | Yes | AIP005760 | Placeholder for Upstream Tx Work for DG (Project) |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25113 | Coniston TS - Station Decomission & Removal | N.T.C.2.11 | 7700 | 203 | PROJECT DELIVERY | AIP005507 |  | AIP005507 | Yes | AIP005507 | Hanmer TS: Build a New 230-44 kV TS |  |  | Load Customer Connection | Robert.Reinmuller@HydroOne.com | Kirpal.Bahra@HydroOne.com | System Access | 0 | 0 | 03 - None (default) | 0 | Project | ACTN BEST | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25114 | Midhurst TS - M4 - ID34210 - Tx -LSRA Solar | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP005760 |  | AIP005760 | Yes | AIP005760 | Placeholder for Upstream Tx Work for DG (Project) |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25115 | Otonabee TS - M28 - ID 33980 - SCI OT1_Tx | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP005760 |  | AIP005760 | Yes | AIP005760 | Placeholder for Upstream Tx Work for DG (Project) |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25116 | Picton TS-M5-35640-Dx-White Pines Wind Farm | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000199 |  | AIP000199 | Yes | AIP000199 | Large Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25117 | Picton TS-M5-35640-Tx-White Pines Wind Farm | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP005760 |  | AIP005760 | Yes | AIP005760 | Placeholder for Upstream Tx Work for DG (Project) |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25118 | Dundas TS M1 Rebuild | N.D.C.1.07 | 7374 | 205 | LINES | UNPLND |  |  | Yes |  |  |  |  | Lines | emre.aydin@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25120 | Beaverton TS - M26 - ID 35330 - SCI CE3_Dx | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000195 |  | AIP000195 | Yes | AIP000195 | Small Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25121 | Beaverton TS - M26 - ID 35330 - SCI CE3_Tx | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP005760 |  | AIP005760 | Yes | AIP005760 | Placeholder for Upstream Tx Work for DG (Project) |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | EMPP AWRD | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25122 | Niagara Murray TS: Revenue Metering Upgrade | N.T.C.2.11 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Load Customer Connection | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25125 | Battersea HVDS-F1-ID34830-Tx-William Benjamin Grn | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP005760 |  | AIP005760 | Yes | AIP005760 | Placeholder for Upstream Tx Work for DG (Project) |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25126 | Crowland TS M19 ID35130 TX - GE BTM | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP005760 |  | AIP005760 | Yes | AIP005760 | Placeholder for Upstream Tx Work for DG (Project) |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25130 | Tx Tower Grounding Upgrades-Recoverable | N.T.C.1.14 | 7370 | 206 | TX LINES AND STATIONS | AIP000512 |  | AIP000512 | Yes | AIP000512 | Recoverable projects to be identified - Placeholder |  |  | Third Party Transmission System Modifications | john.boldt@HydroOne.com | Gian.Minichini@HydroOne.com | System Renewal | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25131 | Dx Sensors Deployment Project | N.D.C.3.08 | 4514 | 212 | INFO SOLUTIONS DIVISION | UNPLND |  |  | Yes |  |  |  |  | Operating Infrastructure | Godfrey.Holder@HydroOne.com | [6 empty] | Project | AWRD EMPP BEST | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25132 | RTES Replacement | N.T.C.3.08 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Integrating Operating Infrastructure | Miroslav.Kostic@HydroOne.com | [6 empty] | Project | ACTN DETL | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25137 | Dack DS - F1 - ID11730-DX Charlton Dam | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000931 |  | AIP000931 | Yes | AIP000931 | TS Upgrades for DG |  |  | Distribution Generation Connection | ryan.boudreau@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25138 | TECHS-LINES-Standards-Dx | N.D.M.2.20 | 7716 | 224 | ENGINEERING | AIP000309 | AIP000309 | AIP000309 | No | AIP000309 | Dx - TECHS-LINES-Standards |  |  | Standards Program | Kevin.Mancherjee@HydroOne.com | rossella.fazio@hydroone.com | System O&M | N/A | 0 | 03 - None (default) | 0 | Program | EMPP init | Executing | Short Term Planning | Assumption - # of Standards | 834149.1543 | 867889.3936 | 895561.1953 | 924450.2379 | 950905.495 | 0 | 0 | 0 | 0 | 0 | 834149.1543 | 867889.3936 | 895561.1953 | 924450.2379 | 950905.495 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 16 | 17 | 17 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | FALSE |  | 0 | 0 | Vulnerable
25140 | OEB Price Pilot Project - Capital | N.D.C.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION |  |  |  | No |  |  |  |  | IT Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25141 | OEB Price Pilot Project - OMA | N.D.M.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION |  |  |  | No |  |  |  |  | IT Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25142 | Success Factors Onboarding | N.C.C.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION | AIP005731 |  | AIP005731 | Yes | AIP005731 | Corporate Services Transformation - HR - CAP |  |  | IT Business Solution Development | jj.blais@HydroOne.com | Jun.Macabanti@hydroone.com | General Plant | 0 | 0 | 0 | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25145 | Dack DS - F1 - ID11730-TX Charlton Dam | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP005760 |  | AIP005760 | Yes | AIP005760 | Placeholder for Upstream Tx Work for DG (Project) |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25146 | GORMS to FDGIS Migration Project - OM&A | N.D.M.3.01 | 4514 | 212 | INFO SOLUTIONS DIVISION | UNPLND |  |  | Yes |  |  |  |  | Operations Contract | Godfrey.Holder@HydroOne.com | [6 empty] | Program | EMPP AWRD | Executing | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25147 | Stewartville M3 - ID34500 - SCI RE5_Dx | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000195 |  | AIP000195 | Yes | AIP000195 | Small Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25148 | Stewartville - M3 ID34500 - SCI RE5_Tx | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP005760 |  | AIP005760 | Yes | AIP005760 | Placeholder for Upstream Tx Work for DG (Project) |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25149 | Stewartville M3 - ID34490 - SCI RE1 DX | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000195 |  | AIP000195 | Yes | AIP000195 | Small Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25150 | Stratford TS M6 ID35610 TX - Koskamp 100kW Biogas | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP005760 |  | AIP005760 | Yes | AIP005760 | Placeholder for Upstream Tx Work for DG (Project) |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25151 | Stratford TS M6 ID35610 DX - Koskamp 100kW Biogas | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000191 |  | AIP000191 | Yes | AIP000191 | Small Embedded Generation | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning | # of Gen Connections | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25152 | Stewartville - M3 - ID 34500 - SCI RE5_Dx | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000195 |  | AIP000195 | Yes | AIP000195 | Small Embedded Generation (E/PD) |  |  | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25154 | Joint Use Projects and Relocations <75K | N.D.C.1.03 | 7374 | 205 | LINES | AIP000129 |  | AIP000129 | Yes | AIP000129 | Joint Use & Line Relocations |  |  | Joint Use and Relocations | john.boldt@HydroOne.com | Jenny.Seo@HydroOne.com | System Access | 0 | 0 | 03 - None (default) | 0 | Program | init | Short Term Planning | Short Term Planning | # of projects | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25155 | Strewartville M3 - ID34500 - SCI RE5_Dx | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000195 |  | AIP000195 | Yes | AIP000195 | Small Embedded Generation (E/PD) |  |  | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25156 | Construction for EnWin DX Duct Bank in Keith TS | N.T.M.1.14 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Engineering and Environmental Support | Mike.Tanaskovic@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25157 | Ft. Frances TS: Remove T4 and GT1 | N.T.C.2.11 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Load Customer Connection | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25158 | Cochrane West DS - Station Refurbishment | N.D.C.1.08 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Distributing & Regulating Stations | emre.aydin@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25159 | WPF Coe Hill DS F2 Communicating FCIs | N.D.C.2.02 | 7374 | 205 | LINES | AIP005826 |  | AIP005826 | Yes | AIP005826 | Modernization of Worst Performing Feeders | ISD-SS-06 | Worst Performing Feeders | System Capability Reinforcement | lyla.garzouzi@hydroone.com | sinisa.grkovic@HydroOne.com | System Service | 0 | 0 | 03 - None (default) | 0 | Project | ACTN EMPP | Executing | Executing | # of Normal Open Points | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25160 | Stewartville - M3 ID34490 - SCI RE1_Tx | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP005760 |  | AIP005760 | Yes | AIP005760 | Placeholder for Upstream Tx Work for DG (Project) |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25161 | Stewartville M3 - ID34510 - SCI RE7 DX | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000195 |  | AIP000195 | Yes | AIP000195 | Small Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25162 | Stewartville - M3 ID34510 - SCI RE7_Tx | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP005760 |  | AIP005760 | Yes | AIP005760 | Placeholder for Upstream Tx Work for DG (Project) |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25163 | Stewartville - M3 ID35280 - SCI RE6_Tx | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP005760 |  | AIP005760 | Yes | AIP005760 | Placeholder for Upstream Tx Work for DG (Project) |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25164 | Stewartville M3 - ID35280 - SCI RE6 DX | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000195 |  | AIP000195 | Yes | AIP000195 | Small Embedded Generation (E/PD) | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25165 | Customer Select Due Date - Capital | N.D.C.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION |  |  |  | No |  |  |  |  | IT Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25166 | Customer Select Due Date - OMA | N.D.M.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION |  |  |  | No |  |  |  |  | IT Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25167 | Toronto-TTC Scarborough Subway TPSS–Recoverable | N.T.C.1.14 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Third Party Transmission System Modifications | john.boldt@HydroOne.com | [6 empty] | Project | ACTN BEST | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25168 | Muskoka TS M2 ID34980 DX - 1.21GW Lancelot | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000191 |  | AIP000191 | Yes | AIP000191 | Small Embedded Generation | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 03 - None (default) | 0 | Project | EMPP ACCP | Executing | Executing | # of Gen Connections | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25169 | Muskoka TS M2 ID34980 TX - 1.21GW Lancelot | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP005760 |  | AIP005760 | Yes | AIP005760 | Placeholder for Upstream Tx Work for DG (Project) |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25175 | CIP-014 Implement Defined Security Measures-OGCC | N.T.C.1.29 | 838 | 212 | INFO SOLUTIONS DIVISION | AIP005635 |  | AIP005635 | Yes | AIP005635 | CIP-014 Physical Security Implementation - Initial Sites |  |  | NERC Cyber Security Compliance Readiness | lincoln.frost-hunt@hydroone.com | Sherry.Wilging@hydroone.com | System Renewal | 0 | 0 | 03 - None (default) | 0 | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25176 | CIP-014 Implement Remaining 24 sites | N.T.C.1.29 | 7700 | 203 | PROJECT DELIVERY | AIP005635 |  | AIP005635 | Yes | AIP005635 | CIP-014 Physical Security Implementation - Initial Sites |  |  | NERC Cyber Security Compliance Readiness | lincoln.frost-hunt@hydroone.com | Sherry.Wilging@hydroone.com | System Renewal | 0 | 0 | 03 - None (default) | 0 | Project | ACTN DETL | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25177 | WPF Smiths Falls TS M25 Remote Operable Switches | N.D.C.2.02 | 7374 | 205 | LINES | AIP005826 |  | AIP005826 | Yes | AIP005826 | Modernization of Worst Performing Feeders | ISD-SS-06 | Worst Performing Feeders | System Capability Reinforcement | lyla.garzouzi@hydroone.com | sinisa.grkovic@HydroOne.com | System Service | 0 | 0 | 03 - None (default) | 0 | Project | ACTN EMPP | Executing | Executing | # of Normal Open Points | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25178 | WPF Smiths Falls TS M26 Remote Operable Switches | N.D.C.2.02 | 7374 | 205 | LINES | AIP005826 |  | AIP005826 | Yes | AIP005826 | Modernization of Worst Performing Feeders | ISD-SS-06 | Worst Performing Feeders | System Capability Reinforcement | lyla.garzouzi@hydroone.com | sinisa.grkovic@HydroOne.com | System Service | 0 | 0 | 03 - None (default) | 0 | Project | ACTN EMPP | Executing | Executing | # of Normal Open Points | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25179 | WPF Snow Road DS F2 Communicating FCIs | N.D.C.2.02 | 7374 | 205 | LINES | AIP005826 |  | AIP005826 | Yes | AIP005826 | Modernization of Worst Performing Feeders | ISD-SS-06 | Worst Performing Feeders | System Capability Reinforcement | lyla.garzouzi@hydroone.com | sinisa.grkovic@HydroOne.com | System Service | 0 | 0 | 03 - None (default) | 0 | Project | EMPP AWRD | Executing | Executing | # of Normal Open Points | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25180 | Crystal Falls TS - M1 - ID34710 - Tx Shoreline 2 | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP05760 |  | AIP05760 | Yes | AIP05760 |  |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25181 | Crystal Falls TS - M1 - ID34710 - Dx Shoreline 2 | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000191 |  | AIP000191 | Yes | AIP000191 | Small Embedded Generation | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning | # of Gen Connections | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25182 | Scarboro TS M24 ID32640 TX - 50 Salome Dr | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP005760 |  | AIP005760 | Yes | AIP005760 | Placeholder for Upstream Tx Work for DG (Project) |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25183 | WPF Orillia TS M2 Remote Operable Switches | N.D.C.2.02 | 7374 | 205 | LINES | AIP005826 |  | AIP005826 | Yes | AIP005826 | Modernization of Worst Performing Feeders | ISD-SS-06 | Worst Performing Feeders | System Capability Reinforcement | lyla.garzouzi@hydroone.com | sinisa.grkovic@HydroOne.com | System Service | 0 | 0 | 03 - None (default) | 0 | Project | EMPP ACTN | Executing | Executing | # of Normal Open Points | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25184 | Dx Work for CAE and CAR DG Projects (E&PD) | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000199 |  | AIP000199 | Yes | AIP000199 | Large Embedded Generation (E/PD) |  |  | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25185 | WPF Almonte TS M28 Remote Operable Switches | N.D.C.2.02 | 7374 | 205 | LINES | AIP005826 |  | AIP005826 | Yes | AIP005826 | Modernization of Worst Performing Feeders | ISD-SS-06 | Worst Performing Feeders | System Capability Reinforcement | lyla.garzouzi@hydroone.com | sinisa.grkovic@HydroOne.com | System Service | 0 | 0 | 03 - None (default) | 0 | Project | ACTN EMPP | Executing | Executing | # of Normal Open Points | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25186 | WPF Arnprior TS M2 Remote Operable Switches | N.D.C.2.02 | 7374 | 205 | LINES | AIP005826 |  | AIP005826 | Yes | AIP005826 | Modernization of Worst Performing Feeders | ISD-SS-06 | Worst Performing Feeders | System Capability Reinforcement | lyla.garzouzi@hydroone.com | sinisa.grkovic@HydroOne.com | System Service | 0 | 0 | 03 - None (default) | 0 | Project | EMPP ACTN | Executing | Executing | # of Normal Open Points | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25187 | WPF Brockville TS M6 Remote Operable Switches | N.D.C.2.02 | 7374 | 205 | LINES | AIP005826 |  | AIP005826 | Yes | AIP005826 | Modernization of Worst Performing Feeders | ISD-SS-06 | Worst Performing Feeders | System Capability Reinforcement | lyla.garzouzi@hydroone.com | sinisa.grkovic@HydroOne.com | System Service | 0 | 0 | 03 - None (default) | 0 | Project | ACTN EMPP | Executing | Executing | # of Normal Open Points | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25188 | WPF Chesterville TS M1 Remote Operable Switches | N.D.C.2.02 | 7374 | 205 | LINES | AIP005826 |  | AIP005826 | Yes | AIP005826 | Modernization of Worst Performing Feeders | ISD-SS-06 | Worst Performing Feeders | System Capability Reinforcement | lyla.garzouzi@hydroone.com | sinisa.grkovic@HydroOne.com | System Service | 0 | 0 | 03 - None (default) | 0 | Project | ACTN EMPP | Executing | Executing | # of Normal Open Points | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25189 | WPF - Palmerston TS M3 - Remote Operable Switches | N.D.C.2.02 | 7374 | 205 | LINES | AIP005826 |  | AIP005826 | Yes | AIP005826 | Modernization of Worst Performing Feeders | ISD-SS-06 | Worst Performing Feeders | System Capability Reinforcement | lyla.garzouzi@hydroone.com | sinisa.grkovic@HydroOne.com | System Service | 0 | 0 | 03 - None (default) | 0 | Project | ACTN EMPP | Executing | Executing | # of Normal Open Points | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25191 | Stewartville M1 - ID35350 - SCI RE9_Dx | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000191 |  | AIP000191 | Yes | AIP000191 | Small Embedded Generation |  |  | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 03 - None (default) | 0 | Project | ACCP EMPP | Executing | Executing | # of Gen Connections | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25192 | Stewartville - M1 ID35350 - SCI RE9 TX | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP005760 |  | AIP005760 | Yes | AIP005760 | Placeholder for Upstream Tx Work for DG (Project) |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25193 | Stewartville M1 - ID35360 - SCI RE4_Dx | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000191 |  | AIP000191 | Yes | AIP000191 | Small Embedded Generation |  |  | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 03 - None (default) | 0 | Project | ACCP EMPP | Executing | Executing | # of Gen Connections | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25194 | Stewartville - M1 ID35360 - SCI RE4 Tx | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP005760 |  | AIP005760 | Yes | AIP005760 | Placeholder for Upstream Tx Work for DG (Project) |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25195 | Stewartville M1 - ID35370 - SCI RE11 Dx | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000191 |  | AIP000191 | Yes | AIP000191 | Small Embedded Generation |  |  | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 03 - None (default) | 0 | Project | ACCP EMPP | Executing | Executing | # of Gen Connections | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25196 | Stewartville - M1 ID35370 - SCI RE11 Tx | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP005760 |  | AIP005760 | Yes | AIP005760 | Placeholder for Upstream Tx Work for DG (Project) |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25197 | Stewartville M1 - ID35380- SCI RE12 Dx | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000191 |  | AIP000191 | Yes | AIP000191 | Small Embedded Generation |  |  | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 03 - None (default) | 0 | Project | EMPP ACCP | Executing | Executing | # of Gen Connections | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25198 | Stewartville - M1 ID35380 - SCI RE12 Tx | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP005760 |  | AIP005760 | Yes | AIP005760 | Placeholder for Upstream Tx Work for DG (Project) |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25199 | Coniston TS Removal Capital Contribution | N.D.C.2.02 | 7700 | 203 | PROJECT DELIVERY | AIP005507 |  | AIP005507 | Yes | AIP005507 | Hanmer TS: Build a New 230-44 kV TS |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Kirpal.Bahra@HydroOne.com | System Access | 0 | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25200 | Viaduct Platform Pilot | N.D.M.2.21 | 4230 | 213 | PLANNING | AIP005498 |  | AIP005498 | Yes | AIP005498 | RD&D Project - Grid Modernization and Energy Storage |  |  | Distribution RD&D | Daila.Dzintars@HydroOne.com | janet.eby@Hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25201 | Stewartville TS - M1 - ID35600 - Dx - Mill Ridge | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY |  |  |  | No |  |  |  |  | Distribution Generation Connection | ryan.boudreau@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25202 | Stewartville TS - M1 - ID35600 - Tx - Mill Ridge | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY |  |  |  | No |  |  |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25203 | Chapleau DS - F4 - ID35580 - Tx Goldcorp Borden Mi | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP05760 |  | AIP05760 | Yes | AIP05760 |  |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25204 | Chapleau DS - F4 - ID35580 - Dx Goldcorp Borden Mi | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000191 |  | AIP000191 | Yes | AIP000191 | Small Embedded Generation | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning | # of Gen Connections | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25205 | AMI-Standards-Dx | N.D.M.2.20 | 8706 | 214 | METER SHOP | AIP000309 |  | AIP000309 | Yes | AIP000309 | Dx - TECHS-LINES-Standards |  |  | Standards Program | Kevin.Mancherjee@HydroOne.com | rossella.fazio@hydroone.com | System O&M | N/A | 0 | 03 - None (default) | 0 | Program | EMPP ACCP | Executing | Short Term Planning | Assumption - # of Standards | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25206 | WPF Emsdale DS F3 Line Relocation | N.D.C.2.02 | 7374 | 205 | LINES | AIP005826 |  | AIP005826 | Yes | AIP005826 | Modernization of Worst Performing Feeders | ISD-SS-06 | Worst Performing Feeders | System Capability Reinforcement | lyla.garzouzi@hydroone.com | sinisa.grkovic@HydroOne.com | System Service | 0 | 0 | 03 - None (default) | 0 | Project | ACTN EMPP | Executing | Executing | # of Normal Open Points | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25207 | WPF - Manitoulin TS M25 - Remote Operable Switches | N.D.C.2.02 | 7374 | 205 | LINES | AIP005826 |  | AIP005826 | Yes | AIP005826 | Modernization of Worst Performing Feeders | ISD-SS-06 | Worst Performing Feeders | System Capability Reinforcement | lyla.garzouzi@hydroone.com | sinisa.grkovic@HydroOne.com | System Service | 0 | 0 | 03 - None (default) | 0 | Project | ACTN EMPP | Executing | Executing | # of Normal Open Points | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25208 | WPF - Manitoulin TS M26 - Remote Operable Switches | N.D.C.2.02 | 7374 | 205 | LINES | AIP005826 |  | AIP005826 | Yes | AIP005826 | Modernization of Worst Performing Feeders | ISD-SS-06 | Worst Performing Feeders | System Capability Reinforcement | lyla.garzouzi@hydroone.com | sinisa.grkovic@HydroOne.com | System Service | 0 | 0 | 03 - None (default) | 0 | Project | ACTN EMPP | Executing | Executing | # of Normal Open Points | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25209 | WPF - Trout Lake TS M7 - Remote Operable Switches | N.D.C.2.02 | 7374 | 205 | LINES | AIP005826 |  | AIP005826 | Yes | AIP005826 | Modernization of Worst Performing Feeders | ISD-SS-06 | Worst Performing Feeders | System Capability Reinforcement | lyla.garzouzi@hydroone.com | sinisa.grkovic@HydroOne.com | System Service | 0 | 0 | 03 - None (default) | 0 | Project | EMPP ACTN | Executing | Executing | # of Normal Open Points | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25210 | WPF - Owen Sound TS M25 - Remote Operable Switches | N.D.C.2.02 | 7374 | 205 | LINES | AIP005826 |  | AIP005826 | Yes | AIP005826 | Modernization of Worst Performing Feeders | ISD-SS-06 | Worst Performing Feeders | System Capability Reinforcement | lyla.garzouzi@hydroone.com | sinisa.grkovic@HydroOne.com | System Service | 0 | 0 | 03 - None (default) | 0 | Project | EMPP ACTN | Executing | Executing | # of Normal Open Points | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25211 | WPF Murillo DS F1 Remote Operable SW + CFCIs + OCR | N.D.C.2.02 | 7374 | 205 | LINES | AIP005826 |  | AIP005826 | Yes | AIP005826 | Modernization of Worst Performing Feeders | ISD-SS-06 | Worst Performing Feeders | System Capability Reinforcement | lyla.garzouzi@hydroone.com | sinisa.grkovic@HydroOne.com | System Service | 0 | 0 | 03 - None (default) | 0 | Project | ACTN EMPP | Executing | Executing | # of Normal Open Points | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25212 | WPF Murillo DS F3 Remote Operable SW + CFCIs + OCR | N.D.C.2.02 | 7374 | 205 | LINES | AIP005826 |  | AIP005826 | Yes | AIP005826 | Modernization of Worst Performing Feeders | ISD-SS-06 | Worst Performing Feeders | System Capability Reinforcement | lyla.garzouzi@hydroone.com | sinisa.grkovic@HydroOne.com | System Service | 0 | 0 | 03 - None (default) | 0 | Project | EMPP ACTN | Executing | Executing | # of Normal Open Points | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25213 | Bathurst TS - M3, M5, M30, M31 KSO replace support | N.T.C.2.11 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Load Customer Connection | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25214 | Bermondsey -M23 & M26 relay & fibre duct supp work | N.T.C.2.11 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Load Customer Connection | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25216 | WPF Waubaushene TS M7 Remote Operable Switches | N.D.C.2.02 | 7374 | 205 | LINES | AIP005826 |  | AIP005826 | Yes | AIP005826 | Modernization of Worst Performing Feeders | ISD-SS-06 | Worst Performing Feeders | System Capability Reinforcement | lyla.garzouzi@hydroone.com | sinisa.grkovic@HydroOne.com | System Service | 0 | 0 | 03 - None (default) | 0 | Project | EMPP ACTN | Executing | Executing | # of Normal Open Points | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25217 | Tx Lines Idle Line Removal – Lakeview GS | N.T.C.1.12 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Overhead Lines Component Refurb & Repl | hassan.hamzeh@hydroone.com | [6 empty] | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25218 | WPF Waubaushene TS M1 Remote Operable Switches | N.D.C.2.02 | 7374 | 205 | LINES | AIP005826 |  | AIP005826 | Yes | AIP005826 | Modernization of Worst Performing Feeders | ISD-SS-06 | Worst Performing Feeders | System Capability Reinforcement | lyla.garzouzi@hydroone.com | sinisa.grkovic@HydroOne.com | System Service | 0 | 0 | 03 - None (default) | 0 | Project | ACTN EMPP | Executing | Executing | # of Normal Open Points | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25219 | WPF Cobden TS M6 Remote Operable Switches | N.D.C.2.02 | 7374 | 205 | LINES | AIP005826 |  | AIP005826 | Yes | AIP005826 | Modernization of Worst Performing Feeders | ISD-SS-06 | Worst Performing Feeders | System Capability Reinforcement | lyla.garzouzi@hydroone.com | sinisa.grkovic@HydroOne.com | System Service | 0 | 0 | 03 - None (default) | 0 | Project | EMPP ACTN | Executing | Executing | # of Normal Open Points | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25220 | WPF Trout Creek DS F1 Fault Indicators and others | N.D.C.2.02 | 7374 | 205 | LINES | AIP005826 |  | AIP005826 | Yes | AIP005826 | Modernization of Worst Performing Feeders | ISD-SS-06 | Worst Performing Feeders | System Capability Reinforcement | lyla.garzouzi@hydroone.com | sinisa.grkovic@HydroOne.com | System Service | 0 | 0 | 03 - None (default) | 0 | Project | ACTN EMPP | Executing | Executing | # of Normal Open Points | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25221 | WPF Port Arthur TS M6 Fault Indicators and others | N.D.C.2.02 | 7374 | 205 | LINES | AIP005826 |  | AIP005826 | Yes | AIP005826 | Modernization of Worst Performing Feeders | ISD-SS-06 | Worst Performing Feeders | System Capability Reinforcement | lyla.garzouzi@hydroone.com | sinisa.grkovic@HydroOne.com | System Service | 0 | 0 | 03 - None (default) | 0 | Project | ACTN EMPP | Executing | Executing | # of Normal Open Points | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25222 | Hydro Hawkesbury MTS: SCADA Connection | N.T.C.2.11 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Load Customer Connection | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25223 | WPF MindenTS M2 Remote Switch and Recloser Upgrade | N.D.C.2.02 | 7374 | 205 | LINES | AIP005826 |  | AIP005826 | Yes | AIP005826 | Modernization of Worst Performing Feeders | ISD-SS-06 | Worst Performing Feeders | System Capability Reinforcement | lyla.garzouzi@hydroone.com | sinisa.grkovic@HydroOne.com | System Service | 0 | 0 | 03 - None (default) | 0 | Project | INSC | Short Term Planning | Short Term Planning | # of Normal Open Points | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25224 | WPF OtonabeeTS M27 Remote Switch, Recloser Upgrade | N.D.C.2.02 | 7374 | 205 | LINES | AIP005826 |  | AIP005826 | Yes | AIP005826 | Modernization of Worst Performing Feeders | ISD-SS-06 | Worst Performing Feeders | System Capability Reinforcement | lyla.garzouzi@hydroone.com | sinisa.grkovic@HydroOne.com | System Service | 0 | 0 | 03 - None (default) | 0 | Project | INSC | Short Term Planning | Short Term Planning | # of Normal Open Points | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25225 | WPF Picton TS M5 Remote Operable Switches | N.D.C.2.02 | 7374 | 205 | LINES | AIP005826 |  | AIP005826 | Yes | AIP005826 | Modernization of Worst Performing Feeders | ISD-SS-06 | Worst Performing Feeders | System Capability Reinforcement | lyla.garzouzi@hydroone.com | sinisa.grkovic@HydroOne.com | System Service | 0 | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning | # of Normal Open Points | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25226 | WPF Muskoka TS M4 Remote Operable Switches | N.D.C.2.02 | 7374 | 205 | LINES | AIP005826 |  | AIP005826 | Yes | AIP005826 | Modernization of Worst Performing Feeders | ISD-SS-06 | Worst Performing Feeders | System Capability Reinforcement | lyla.garzouzi@hydroone.com | sinisa.grkovic@HydroOne.com | System Service | 0 | 0 | 03 - None (default) | 0 | Project | EMPP INSC | Executing | Executing | # of Normal Open Points | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25227 | WPF Muskoka TS M2 Switches and Recloser Relocate | N.D.C.2.02 | 7374 | 205 | LINES | AIP005826 |  | AIP005826 | Yes | AIP005826 | Modernization of Worst Performing Feeders | ISD-SS-06 | Worst Performing Feeders | System Capability Reinforcement | lyla.garzouzi@hydroone.com | sinisa.grkovic@HydroOne.com | System Service | 0 | 0 | 03 - None (default) | 0 | Project | ACTN EMPP | Executing | Executing | # of Normal Open Points | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25228 | WPF Muskoka TS M10 Remote Operable Switches | N.D.C.2.02 | 7374 | 205 | LINES | AIP005826 |  | AIP005826 | Yes | AIP005826 | Modernization of Worst Performing Feeders | ISD-SS-06 | Worst Performing Feeders | System Capability Reinforcement | lyla.garzouzi@hydroone.com | sinisa.grkovic@HydroOne.com | System Service | 0 | 0 | 03 - None (default) | 0 | Project | INSC EMPP | Executing | Executing | # of Normal Open Points | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25229 | WPF Muskoka TS M1 Remote Operable Switches | N.D.C.2.02 | 7374 | 205 | LINES | AIP005826 |  | AIP005826 | Yes | AIP005826 | Modernization of Worst Performing Feeders | ISD-SS-06 | Worst Performing Feeders | System Capability Reinforcement | lyla.garzouzi@hydroone.com | sinisa.grkovic@HydroOne.com | System Service | 0 | 0 | 03 - None (default) | 0 | Project | EMPP INSC | Executing | Executing | # of Normal Open Points | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25230 | WPF Combermere DS F3 Communicating FCIs | N.D.C.2.02 | 7374 | 205 | LINES | AIP005826 |  | AIP005826 | Yes | AIP005826 | Modernization of Worst Performing Feeders | ISD-SS-06 | Worst Performing Feeders | System Capability Reinforcement | lyla.garzouzi@hydroone.com | sinisa.grkovic@HydroOne.com | System Service | 0 | 0 | 03 - None (default) | 0 | Project | ACTN EMPP | Executing | Executing | # of Normal Open Points | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25231 | Port Hope TS M17 ID35930 Dx Sabic Demand Response | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000191 |  | AIP000191 | Yes | AIP000191 | Small Embedded Generation | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 03 - None (default) | 0 | Project | ACCP EMPP | Executing | Executing | # of Gen Connections | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25232 | Port Hope TS M17 ID35930 Tx Sabic Demand Response | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP005760 |  | AIP005760 | Yes | AIP005760 | Placeholder for Upstream Tx Work for DG (Project) |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25233 | WPF - Clarabelle TS M8 - Remote Operable Switches | N.D.C.2.02 | 7374 | 205 | LINES | AIP005826 |  | AIP005826 | Yes | AIP005826 | Modernization of Worst Performing Feeders | ISD-SS-06 | Worst Performing Feeders | System Capability Reinforcement | lyla.garzouzi@hydroone.com | sinisa.grkovic@HydroOne.com | System Service | 0 | 0 | 03 - None (default) | 0 | Project | EMPP ACTN | Executing | Executing | # of Normal Open Points | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25234 | Power Quality/P&C Spares Management | N.T.M.1.17 | 8178 | 214 | METER SHOP | AIP001084 |  | AIP001084 | Yes | AIP001084 | P&C Support (NOEA/Spares/data and info mgmnt) |  |  | Protection Control & Metering Equipment | Miroslav.Kostic@HydroOne.com | warren.tingle@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | AWRD EMPP | Executing | Short Term Planning | Retainer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25235 | WPF Wallace TS M4 REMOTE OPERABLE SWITCHES | N.D.C.2.02 | 7374 | 205 | LINES | AIP005826 |  | AIP005826 | Yes | AIP005826 | Modernization of Worst Performing Feeders | ISD-SS-06 | Worst Performing Feeders | System Capability Reinforcement | lyla.garzouzi@hydroone.com | sinisa.grkovic@HydroOne.com | System Service | 0 | 0 | 03 - None (default) | 0 | Project | AWRD EMPP | Executing | Executing | # of Normal Open Points | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25236 | WPF Wolverton DS F1 Sensors | N.D.C.2.02 | 7374 | 205 | LINES | AIP005826 |  | AIP005826 | Yes | AIP005826 | Modernization of Worst Performing Feeders | ISD-SS-06 | Worst Performing Feeders | System Capability Reinforcement | lyla.garzouzi@hydroone.com | sinisa.grkovic@HydroOne.com | System Service | 0 | 0 | 03 - None (default) | 0 | Project | EMPP ACTN | Executing | Executing | # of Normal Open Points | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25237 | Bruce B SS - Transfer control of JL501 & L501L563 | N.T.C.1.40 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Western Zone Station/Yard Investments | James.Mardegan@HydroOne.com | [6 empty] | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25238 | WPF Havelock TS M1 REMOTE OPERABLE SWITCHES | N.D.C.2.02 | 7374 | 205 | LINES | AIP005826 |  | AIP005826 | Yes | AIP005826 | Modernization of Worst Performing Feeders | ISD-SS-06 | Worst Performing Feeders | System Capability Reinforcement | lyla.garzouzi@hydroone.com | sinisa.grkovic@HydroOne.com | System Service | 0 | 0 | 03 - None (default) | 0 | Project | ACTN EMPP | Executing | Executing | # of Normal Open Points | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25239 | WPF - Martindale TS M5 - Remote Operable Switches | N.D.C.2.02 | 7374 | 205 | LINES | AIP005826 |  | AIP005826 | Yes | AIP005826 | Modernization of Worst Performing Feeders | ISD-SS-06 | Worst Performing Feeders | System Capability Reinforcement | lyla.garzouzi@hydroone.com | sinisa.grkovic@HydroOne.com | System Service | 0 | 0 | 03 - None (default) | 0 | Project | ACTN EMPP | Executing | Executing | # of Normal Open Points | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25240 | SCADA Enablement Existing M Reclosers | N.D.C.2.02 | 7370 | 206 | TX LINES AND STATIONS | UNPLND |  |  | Yes |  |  |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | [6 empty] | Project | EMPP ACTN | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25241 | WPF Wallace TS M6 REMOTE OPERABLE SWITCHES | N.D.C.2.02 | 7374 | 205 | LINES | AIP005826 |  | AIP005826 | Yes | AIP005826 | Modernization of Worst Performing Feeders | ISD-SS-06 | Worst Performing Feeders | System Capability Reinforcement | lyla.garzouzi@hydroone.com | sinisa.grkovic@HydroOne.com | System Service | 0 | 0 | 03 - None (default) | 0 | Project | ACTN EMPP | Executing | Executing | # of Normal Open Points | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25242 | WPF Big Chute F2 Tie-Line Construction | N.D.C.2.02 | 7374 | 205 | LINES | AIP005826 |  | AIP005826 | Yes | AIP005826 | Modernization of Worst Performing Feeders | ISD-SS-06 | Worst Performing Feeders | System Capability Reinforcement | lyla.garzouzi@hydroone.com | sinisa.grkovic@HydroOne.com | System Service | 0 | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning | # of Normal Open Points | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25243 | WPF -Shiningtree DS F1 -Remote Operable G&W Vipers | N.D.C.2.02 | 7374 | 205 | LINES | AIP005826 |  | AIP005826 | Yes | AIP005826 | Modernization of Worst Performing Feeders | ISD-SS-06 | Worst Performing Feeders | System Capability Reinforcement | lyla.garzouzi@hydroone.com | sinisa.grkovic@HydroOne.com | System Service | 0 | 0 | 03 - None (default) | 0 | Project | EMPP ACTN | Executing | Executing | # of Normal Open Points | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25245 | Orillia TS M4 ID35540 DX - OSMH Restart | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000191 |  | AIP000191 | Yes | AIP000191 | Small Embedded Generation | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 03 - None (default) | 0 | Project | ACCP EMPP | Executing | Executing | # of Gen Connections | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25246 | Orillia TS M4 ID35540 TX - OSMH Restart | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP005760 |  | AIP005760 | Yes | AIP005760 | Placeholder for Upstream Tx Work for DG (Project) |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25247 | WPF - Grand Bend East DS F2 - Protection Upgrade | N.D.C.2.02 | 7374 | 205 | LINES | AIP005826 |  | AIP005826 | Yes | AIP005826 | Modernization of Worst Performing Feeders | ISD-SS-06 | Worst Performing Feeders | System Capability Reinforcement | lyla.garzouzi@hydroone.com | sinisa.grkovic@HydroOne.com | System Service | 0 | 0 | 03 - None (default) | 0 | Project | EMPP ACTN | Executing | Executing | # of Normal Open Points | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25248 | WPF Schomberg DS F3 CFCIs | N.D.C.2.02 | 7374 | 205 | LINES | AIP005826 |  | AIP005826 | Yes | AIP005826 | Modernization of Worst Performing Feeders | ISD-SS-06 | Worst Performing Feeders | System Capability Reinforcement | lyla.garzouzi@hydroone.com | sinisa.grkovic@HydroOne.com | System Service | 0 | 0 | 03 - None (default) | 0 | Project | ACTN | Short Term Planning | Short Term Planning | # of Normal Open Points | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25249 | PQ Audit Dx - OMA | N.D.M.2.23 | 4050 | 213 | PLANNING | AIP005534 |  | AIP005534 | Yes | AIP005534 | Customer Power Quality (Dx) - OMA |  |  | Customer Power Quality (Dx) | Robert.Reinmuller@HydroOne.com | andrew.yan@HydroOne.com | System O&M | N/A | 0 | 03 - None (default) | 0 | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25250 | Revenue Meter Integration Dx - OMA | N.D.M.2.23 | 4050 | 213 | PLANNING | AIP005534 |  | AIP005534 | Yes | AIP005534 | Customer Power Quality (Dx) - OMA |  |  | Customer Power Quality (Dx) | Robert.Reinmuller@HydroOne.com | andrew.yan@HydroOne.com | System O&M | N/A | 0 | 03 - None (default) | 0 | Project | EMPP AWRD | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25251 | Beach TS M82 ID30230 TX Columbian Chem Cogen | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP005760 |  | AIP005760 | Yes | AIP005760 | Placeholder for Upstream Tx Work for DG (Project) |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | ACCP EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25256 | WPF Tillsonburg TS M10 Sensors | N.D.C.2.02 | 7374 | 205 | LINES | AIP005826 |  | AIP005826 | Yes | AIP005826 | Modernization of Worst Performing Feeders | ISD-SS-06 | Worst Performing Feeders | System Capability Reinforcement | lyla.garzouzi@hydroone.com | sinisa.grkovic@HydroOne.com | System Service | 0 | 0 | 03 - None (default) | 0 | Project | ACTN EMPP | Executing | Executing | # of Normal Open Points | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25260 | Nebo TS M12 ID35860 DX Maple Leaf Foods Inc | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000191 |  | AIP000191 | Yes | AIP000191 | Small Embedded Generation | ISD-SA-05 | Distributed Generation Connections | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning | # of Gen Connections | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25261 | Nebo TS M12 ID35860TX Maple Leaf Foods Inc | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP005760 |  | AIP005760 | Yes | AIP005760 | Placeholder for Upstream Tx Work for DG (Project) |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25262 | WPF Orangeville M45 Remote Switch,Recloser Upgrade | N.D.C.2.02 | 7374 | 205 | LINES | AIP005826 |  | AIP005826 | Yes | AIP005826 | Modernization of Worst Performing Feeders | ISD-SS-06 | Worst Performing Feeders | System Capability Reinforcement | lyla.garzouzi@hydroone.com | sinisa.grkovic@HydroOne.com | System Service | 0 | 0 | 03 - None (default) | 0 | Project | ACTN EMPP | Executing | Executing | # of Normal Open Points | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25265 | Fairchild TS - M2, M4, M5, M6 replace support | N.T.C.2.11 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Load Customer Connection | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25271 | CSO Transition CAP | N.D.C.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION | UNPLND |  |  | Yes |  |  |  |  | IT Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25272 | Lake Superior Link - Construction | N.T.C.2.03 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Network Transfer Capability | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | ACTN BEST | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25273 | Transmission Tower Grounding Upgrades | N.T.C.1.14 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Third Party Transmission System Modifications | john.boldt@HydroOne.com | [6 empty] | Project | AWRD EMPP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25274 | Alliston TS M11, M12 - ID36290 Tx Honda Alliston | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP005760 |  | AIP005760 | Yes | AIP005760 | Placeholder for Upstream Tx Work for DG (Project) |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | EMPP ACCP | Executing | Executing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25276 | Slater TS T1 Emergency Replacement | N.T.C.1.46 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Tx Station Demand and Spares | James.Mardegan@HydroOne.com | [6 empty] | Project | ACTN LLTM | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25277 | NTM117 DG OM&A cost for 2018 | N.T.M.1.17 | 7700 | 203 | PROJECT DELIVERY | AIP005024 |  | AIP005024 | Yes | AIP005024 | Class C Estimates (PD) |  |  | Protection Control & Metering Equipment | Miroslav.Kostic@HydroOne.com | ryan.boudreau@HydroOne.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | init | Short Term Planning | Short Term Planning | # of estimates | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25278 | Cat Lake MTS Upgrade | N.D.C.3.08 | 9000 | 900 | #N/A |  |  |  | No |  |  |  |  | Operating Infrastructure | Godfrey.Holder@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25279 | Leamington TS #2- capital contribution | N.D.C.2.02 | 7700 | 203 | PROJECT DELIVERY |  |  |  | No |  |  |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25280 | Otonabee TS M27 ID35750 DX Dam 24 Hydro (Peterboro | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000191 |  | AIP000191 | Yes | AIP000191 | Small Embedded Generation |  |  | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning | # of Gen Connections | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25281 | Otonabee TS M27 ID35750 TX Dam 24 Hydro (Peterboro | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP005760 |  | AIP005760 | Yes | AIP005760 | Placeholder for Upstream Tx Work for DG (Project) |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25282 | Pelham Load Relief | N.D.C.2.02 | 7374 | 205 | LINES | AIP005383 |  | AIP005383 | Yes | AIP005383 | Allanburg TS M5 feeder |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Mark.VanTol@hydroone.com | System Service | Hamilton Niagara | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25283 | Dresden Area Load Relief | N.D.C.2.02 | 7374 | 205 | LINES | AIP005883 |  | AIP005883 | Yes | AIP005883 | Dresden DS Removal |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Alexander.Hamlyn@HydroOne.com | System Renewal | Western | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25284 | Fiddlers Green DS Supply Improvements | N.D.C.2.02 | 7374 | 205 | LINES | AIP005383 |  | AIP005383 | Yes | AIP005383 | Allanburg TS M5 feeder |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Mark.VanTol@hydroone.com | System Service | Hamilton Niagara | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25285 | Leamington TS #2 Feeder Development | N.D.C.2.02 | 7374 | 205 | LINES | AIP005428 |  | AIP005428 | Yes | AIP005428 | Leamington TS Feeder Development |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Alexander.Hamlyn@HydroOne.com | System Service | Western | In Progress | 01 - Agreement (current/future) | TBD | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25286 | Bismark DS Offloading | N.D.C.2.02 | 7374 | 205 | LINES | AIP005883 |  | AIP005883 | Yes | AIP005883 | Dresden DS Removal |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Alexander.Hamlyn@HydroOne.com | System Renewal | Western | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25287 | Decewesville DS Conversion | N.D.C.2.02 | 7374 | 205 | LINES | AIP005883 |  | AIP005883 | Yes | AIP005883 | Dresden DS Removal |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Alexander.Hamlyn@HydroOne.com | System Renewal | Western | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25288 | Ancaster Area Load Relief | N.D.C.2.02 | 7374 | 205 | LINES | AIP005383 |  | AIP005383 | Yes | AIP005383 | Allanburg TS M5 feeder |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Mark.VanTol@hydroone.com | System Service | Hamilton Niagara | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25289 | Decewesville RS Replacement | N.D.C.2.02 | 7374 | 205 | LINES | AIP005883 |  | AIP005883 | Yes | AIP005883 | Dresden DS Removal |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Alexander.Hamlyn@HydroOne.com | System Renewal | Western | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25290 | Elora Area Load Relief | N.D.C.2.02 | 7374 | 205 | LINES | AIP005383 |  | AIP005383 | Yes | AIP005383 | Allanburg TS M5 feeder |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Mark.VanTol@hydroone.com | System Service | Hamilton Niagara | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25291 | Alma Area Load Relief | N.D.C.2.02 | 7374 | 205 | LINES | AIP005383 |  | AIP005383 | Yes | AIP005383 | Allanburg TS M5 feeder |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Mark.VanTol@hydroone.com | System Service | Hamilton Niagara | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25292 | Inergi - Base IT Sustainment | N.C.M.1.70 | 4339 | 212 | INFO SOLUTIONS DIVISION | AIP000091B |  | AIP000091 | Yes | AIP000091 | Inergi Sustainment |  |  | IT - Sustainment and Operations | lincoln.frost-hunt@hydroone.com | robert.hosford@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | init | Short Term Planning | Short Term Planning | Retainer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25293 | Inergi - ITO Modernization Master AR | N.C.M.1.70 | 4339 | 212 | INFO SOLUTIONS DIVISION | AIP000091B |  | AIP000091 | Yes | AIP000091 | Inergi Sustainment |  |  | IT - Sustainment and Operations | lincoln.frost-hunt@hydroone.com | robert.hosford@hydroone.com | System O&M | 0 | 0 | 03 - None (default) | 0 | Program | init | Short Term Planning | Short Term Planning | Retainer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25294 | Northwest Transmission Enhancement - Phase 2 | N.T.M.2.02 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Infrastructure Development | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25295 | Wanstead TS New Feeder Position | N.D.C.2.02 | 7374 | 205 | LINES | AIP005883 |  | AIP005883 | Yes | AIP005883 | Dresden DS Removal |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Alexander.Hamlyn@HydroOne.com | System Renewal | Western | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25296 | Havelock TS M3 ID34630 Tx - Drain Bros | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP005760 |  | AIP005760 | Yes | AIP005760 | Placeholder for Upstream Tx Work for DG (Project) |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25297 | Havelock TS M3 ID34630 Dx - Drain Bros | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000191 |  | AIP000191 | Yes | AIP000191 | Small Embedded Generation |  |  | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning | # of Gen Connections | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25299 | UI Path Automation - CAP | N.D.C.2.60 | 4339 | 212 | INFO SOLUTIONS DIVISION | UNPLND |  |  | Yes |  |  |  |  | IT Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25300 | WPF Commerce Way Wolverton Tie | N.D.C.2.02 | 7374 | 205 | LINES | AIP005826 |  | AIP005826 | Yes | AIP005826 | Modernization of Worst Performing Feeders |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | sinisa.grkovic@HydroOne.com | System Service | 0 | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning | # of Normal Open Points | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25301 | Dover Center Load Relief | N.D.C.2.02 | 7374 | 205 | LINES | AIP005883 |  | AIP005883 | Yes | AIP005883 | Dresden DS Removal |  |  | System Capability Reinforcement | lyla.garzouzi@hydroone.com | Alexander.Hamlyn@HydroOne.com | System Renewal | Western | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25303 | Kirkton DS - F1 - ID36150 - DX - Gardiner Biogas | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY |  |  |  | No |  |  |  |  | Distribution Generation Connection | ryan.boudreau@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25304 | Dx Lines SAP Work MGR Upgrade - CAP | N.C.C.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION | UNPLND |  |  | Yes |  |  |  |  | IT Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25305 | Pickering Communication Tower Removal | N.T.C.1.25 | 7700 | 203 | PROJECT DELIVERY | UNPLANNED |  |  | Yes |  |  |  |  | Auxiliary Telecommunication Equipment | Miroslav.Kostic@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25306 | D60 Relay Upgrades for Fault Detection - Dx OM&A | N.D.M.2.06 | 4343 | 222 | SMART GRID | Unplanned |  |  | Yes |  |  |  |  | Smart Grid | Godfrey.Holder@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25307 | Woodstock TS M6 ID35770 TX-Woodstock Hospital CHP | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP005760 |  | AIP005760 | Yes | AIP005760 | Placeholder for Upstream Tx Work for DG (Project) |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25308 | Woodstock TS M6 ID35770 DX-Woodstock Hospital CHP | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000191 |  | AIP000191 | Yes | AIP000191 | Small Embedded Generation |  |  | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning | # of Gen Connections | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25310 | Comm Tower Lighting and Monitoring Upgrades | N.T.C.1.25 | 7700 | 203 | PROJECT DELIVERY | UNPLANNED |  |  | Yes |  |  |  |  | Auxiliary Telecommunication Equipment | Miroslav.Kostic@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25312 | Avista Financial Integration | N.C.C.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION | UNPLND |  |  | Yes |  |  |  |  | IT Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25313 | Ellesmere TS M29 ID31760 Tx - Copperfield | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP005760 |  | AIP005760 | Yes | AIP005760 | Placeholder for Upstream Tx Work for DG (Project) |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25314 | Galt TS M14 ID36680 Tx - Franklin Gen Set | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP005760 |  | AIP005760 | Yes | AIP005760 | Placeholder for Upstream Tx Work for DG (Project) |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25315 | Alliston TS M11, M12 - ID36290 Dx Honda Alliston | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000191 |  | AIP000191 | Yes | AIP000191 | Small Embedded Generation |  |  | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 03 - None (default) | 0 | Project | ACCP EMPP | Executing | Executing | # of Gen Connections | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25316 | Bronte TS M1 - ID36010 NRStor C&I Monarch Plastics | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP005760 |  | AIP005760 | Yes | AIP005760 | Placeholder for Upstream Tx Work for DG (Project) |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25317 | Otonabee TS M27 ID35740 DX Buckhorn Hydro Peterbor | N.D.C.2.03 | 7700 | 203 | PROJECT DELIVERY | AIP000191 |  | AIP000191 | Yes | AIP000191 | Small Embedded Generation |  |  | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ryan.boudreau@HydroOne.com | System Access | 0 | 0 | 03 - None (default) | 0 | Project | init | Short Term Planning | Short Term Planning | # of Gen Connections | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25318 | Otonabee TS M27 ID35740 TX Buckhorn Hydro Peterbor | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP005760 |  | AIP005760 | Yes | AIP005760 | Placeholder for Upstream Tx Work for DG (Project) |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25319 | Enterprise Content Management (ECM) Implementation | N.C.C.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION |  |  |  | No |  |  |  |  | IT Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25320 | Enterprise Content Management (ECM) Implementation | N.C.M.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION |  |  |  | No |  |  |  |  | IT-Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25321 | Coniston TS: EOL Component Replacement | N.T.C.1.45 | 7700 | 203 | PROJECT DELIVERY |  |  |  | No |  |  |  |  | Northern Zone Station/Yard Investments | James.Mardegan@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25322 | Orillia TS M4 - ID35870 289 Coldwater Rd - Loblaws | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP005760 |  | AIP005760 | Yes | AIP005760 | Placeholder for Upstream Tx Work for DG (Project) |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25323 | Next Generation Data Centre-Ph2 | N.T.C.1.29 | 4512 | 212 | INFO SOLUTIONS DIVISION |  |  |  | No |  |  |  |  | NERC Cyber Security Compliance Readiness | lincoln.frost-hunt@hydroone.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25324 | Electronic File Transfer | N.T.C.1.29 | 4339 | 212 | INFO SOLUTIONS DIVISION |  |  |  | No |  |  |  |  | NERC Cyber Security Compliance Readiness | lincoln.frost-hunt@hydroone.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25325 | Woodbridge TS M3 ID36860 Tx - Gracious Living | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP005760 |  | AIP005760 | Yes | AIP005760 | Placeholder for Upstream Tx Work for DG (Project) |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25326 | Planbox | N.C.M.1.60 | 4339 | 212 | INFO SOLUTIONS DIVISION | UNPLND |  |  | Yes |  |  |  |  | IT Business Improvements & Enhancements | lincoln.frost-hunt@hydroone.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25327 | Wholesale Meter Upgrades - Bilberry and Woodstock | N.D.C.2.05 | 7516 | 210 | NS UNNODED | AIP000204 |  | AIP000204 | Yes | AIP000204 | Wholesale Metering |  |  | Wholesale Metering | Peter.Mitskos@HydroOne.com | Dominic.Consorti@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | 0 | Project | init | Short Term Planning | Short Term Planning | # of Meter Points | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25328 | Gerrard TS - ID35460 Regent Park Energy Inc. | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP005760 |  | AIP005760 | Yes | AIP005760 | Placeholder for Upstream Tx Work for DG (Project) |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25330 | UI Path Automation - OMA | N.D.M.1.60 | 4042 | 212 | INFO SOLUTIONS DIVISION | UNPLND |  |  | Yes |  |  |  |  | IT Business Improvements & Enhancements | lincoln.frost-hunt@hydroone.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25331 | EnWin Chrysler MTS Telecom Upgrade | N.T.C.2.11 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Load Customer Connection | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25332 | Metrolinx-HamiltonLRT-Line Relocation | N.T.C.1.14 | 7700 | 203 | PROJECT DELIVERY | AIP006168 |  | AIP006168 | Yes | AIP006168 | Metrolinx - Wilson (Don) Yard Modifications - Recoverable |  |  | Third Party Transmission System Modifications | john.boldt@HydroOne.com | Gian.Minichini@HydroOne.com | System Renewal | Greater Toronto Area | 0 | 01 - Agreement (current/future) | 0 | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25333 | iHub Upgrade | N.C.C.1.70 | 4339 | 212 | INFO SOLUTIONS DIVISION |  |  |  | No |  |  |  |  | IT - Sustainment and Operations | lincoln.frost-hunt@hydroone.com | [6 empty] | Program | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25334 | Tivoli Upgrade | N.C.C.1.70 | 4339 | 212 | INFO SOLUTIONS DIVISION |  |  |  | No |  |  |  |  | IT - Sustainment and Operations | lincoln.frost-hunt@hydroone.com | [6 empty] | Program | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25335 | Low Impact Electronic Protection | N.T.C.1.29 | 4512 | 212 | INFO SOLUTIONS DIVISION |  |  |  | No |  |  |  |  | NERC Cyber Security Compliance Readiness | lincoln.frost-hunt@hydroone.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25336 | Leslie TS - M23, M24 breaker & relay upgrade supp. | N.T.C.2.11 | 7700 | 203 | PROJECT DELIVERY | UNPLND |  |  | Yes |  |  |  |  | Load Customer Connection | Robert.Reinmuller@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25337 | Private Cloud Data Center | N.C.C.1.70 | 4339 | 212 | INFO SOLUTIONS DIVISION |  |  |  | No |  |  |  |  | IT - Sustainment and Operations | lincoln.frost-hunt@hydroone.com | [6 empty] | Program | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25338 | Private Cloud Data Center | N.C.C.1.75 | 4339 | 212 | INFO SOLUTIONS DIVISION |  |  |  | No |  |  |  |  | IT - MFA | lincoln.frost-hunt@hydroone.com | [6 empty] | Program | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25339 | K6F-13 Disconnect Switch Controls | N.T.C.3.08 | 7700 | 203 | PROJECT DELIVERY | AIP000985 |  | AIP000985 | Yes | AIP000985 | Local PSMC Network Sustainment |  |  | Integrating Operating Infrastructure | Miroslav.Kostic@HydroOne.com | Andrew.Webb@HydroOne.com | General Plant | 0 | 0 | 02 - Expectation (no agreement) | 0 | Program | init | Short Term Planning | Short Term Planning | # of sites/upgrades | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25340 | UI Path Automation – COMMON CAP | N.C.C.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION |  |  |  | No |  |  |  |  | IT Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25341 | UI Path Automation - COMMON OMA | N.C.M.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION |  |  |  | No |  |  |  |  | IT-Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25342 | UI Path Automation - DX OMA | N.D.M.2.60 | 4342 | 212 | INFO SOLUTIONS DIVISION |  |  |  | No |  |  |  |  | IT Business Solution Development | jj.blais@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25343 | Glendale TS M31 ID35160 TX - Landfill Gas | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP005760 |  | AIP005760 | Yes | AIP005760 | Placeholder for Upstream Tx Work for DG (Project) |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25344 | John TS: T1, T4 Demand Replacement | N.T.C.1.43 | 7370 | 206 | TX LINES AND STATIONS |  |  |  | No |  |  |  |  | Greater Toronto Area Zone Station/Yard Investments | James.Mardegan@HydroOne.com | [6 empty] | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25345 | SAP Upgrade | N.C.C.1.70 | 4339 | 212 | INFO SOLUTIONS DIVISION |  |  |  | No |  |  |  |  | IT - Sustainment and Operations | lincoln.frost-hunt@hydroone.com | [6 empty] | Program | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25346 | iHUB Upgrade | N.C.C.1.75 | 4339 | 212 | INFO SOLUTIONS DIVISION |  |  |  | No |  |  |  |  | IT - MFA | lincoln.frost-hunt@hydroone.com | [6 empty] | Program | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25350 | Wilson TS - ID35810 1385 Harmony Rd N - Gen Set | N.T.C.2.19 | 7700 | 203 | PROJECT DELIVERY | AIP005760 |  | AIP005760 | Yes | AIP005760 | Placeholder for Upstream Tx Work for DG (Project) |  |  | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | Meifeng.Lian@HydroOne.com | System Access | 0 | 0 | 01 - Agreement (current/future) | Not Required | Project | init | Short Term Planning | Short Term Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
99999 | Description | Position ID | RESP COST | LOB | LOB NAME | AIP CODE |  | AIP CODE | yES | AIP Code | Investment Title | ISD | ISD Description | Driver Title | Driver Owner | Investment Owner | OEB Category | Area | OEB Section 92 Status | Customer Relationship Code | EA Status | SAP Project/Program | SAP Variant User Status | Status | Status to display | Reportable Unit | 2018-Net | 2019-Net | 2020-Net | 2021-Net | 2022-Net | 2023-Net | 2024-Net | 2025-Net | 2026-Net | 2027-Net | 2018-Gross | 2019-Gross | 2020-Gross | 2021-Gross | 2022-Gross | 2023-Gross | 2024-Gross | 2025-Gross | 2026-Gross | 2027-Gross | 2018-Removal | 2019-Removal | 2020-Removal | 2021-Removal | 2022-Removal | 2023-Removal | 2024-Removal | 2025-Removal | 2026-Removal | 2027-Removal | All-RemovalPerc | Removal % | 2018-CC | 2019-CC | 2020-CC | 2021-CC | 2022-CC | 2023-CC | 2024-CC | 2025-CC | 2026-CC | 2027-CC | 2018-ACCOMP | 2019-ACCOMP | 2020-ACCOMP | 2021-ACCOMP | 2022-ACCOMP | 2023-ACCOMP | 2024-ACCOMP | 2025-ACCOMP | 2026-ACCOMP | 2027-ACCOMP | BCS Approval Date | All-IS | Third Party Request | Third Party Request Description | Immediate / Short-Term Compliance Requirement | Immediate / Short-Term Compliance Requirement Description | Forecast is based on signed 3rd Party Contracts | Contractual / Political Commitments Description | Corrective Maintenance/Demand Replacements | Customer Engagement | Customer Engagement Considerations | Political Commitments | Preventative Maintenance/System Renewal | Productivity Embedded | Productivity Enablement | Strategic | Strategic | # of Breaker Reductions | # of Transformer Reductions | Alternative Name

## MultiRisk Template
Multi-asset considerations | [7 empty] | Multi-asset considerations | [7 empty] | Multi-asset considerations |  |  |  | Multi-asset considerations |  |  |  | Multi-asset considerations |  |  |  | Multi-asset considerations |  |  |  | Multi-asset considerations |  |  |  | Multi-asset considerations |  |  |  | Multi-asset considerations |  |  |  | Multi-asset considerations |  |  |  | Multi-asset considerations |  |  |  | Multi-asset considerations |  |  |  | Multi-asset considerations |  |  |  | Multi-asset considerations
Total Number of Asset Types scored | 2 | i.e., number of columns in this sheet you use
Asset scored | 12 kV Switchgear | [6 empty] | Asset scored | 115 kV Circuit Breakers | [6 empty] | Asset scored |  |  |  | Asset scored |  |  |  | Asset scored |  |  |  | Asset scored |  |  |  | Asset scored |  |  |  | Asset scored |  |  |  | Asset scored |  |  |  | Asset scored |  |  |  | Asset scored |  |  |  | Asset scored |  |  |  | Asset scored |  |  |  | Asset scored
Risk scoring | [7 empty] | Risk scoring | [7 empty] | Risk scoring |  |  |  | Risk scoring |  |  |  | Risk scoring |  |  |  | Risk scoring |  |  |  | Risk scoring |  |  |  | Risk scoring |  |  |  | Risk scoring |  |  |  | Risk scoring |  |  |  | Risk scoring |  |  |  | Risk scoring |  |  |  | Risk scoring |  |  |  | Risk scoring
Safety scoring | [7 empty] | Safety scoring | [7 empty] | Safety scoring |  |  |  | Safety scoring |  |  |  | Safety scoring |  |  |  | Safety scoring |  |  |  | Safety scoring |  |  |  | Safety scoring |  |  |  | Safety scoring |  |  |  | Safety scoring |  |  |  | Safety scoring |  |  |  | Safety scoring |  |  |  | Safety scoring |  |  |  | Safety scoring
Risk Multiplier (Unitized Risk) |  | e.g., number of transformers | [5 empty] | Risk Multiplier (Unitized Risk) | [7 empty] | Risk Multiplier (Unitized Risk) |  |  |  | Risk Multiplier (Unitized Risk) |  |  |  | Risk Multiplier (Unitized Risk) |  |  |  | Risk Multiplier (Unitized Risk) |  |  |  | Risk Multiplier (Unitized Risk) |  |  |  | Risk Multiplier (Unitized Risk) |  |  |  | Risk Multiplier (Unitized Risk) |  |  |  | Risk Multiplier (Unitized Risk) |  |  |  | Risk Multiplier (Unitized Risk) |  |  |  | Risk Multiplier (Unitized Risk) |  |  |  | Risk Multiplier (Unitized Risk) |  |  |  | Risk Multiplier (Unitized Risk)
Safety - WRDI | Shock risk/potential contact with live equipment due to the inability to isolate part of the circuit | Safety Consequence Type | Impact on employee or contractor | Safety Probability Type | Probability of event occurring in next year |  |  | Safety - WRDI | N/A | Safety Consequence Type | Impact on employee or contractor | Safety Probability Type | Probability of event occurring in next year |  |  | Safety - WRDI | Safety Consequence Type | Safety Probability Type |  | Safety - WRDI | Safety Consequence Type | Safety Probability Type |  | Safety - WRDI | Safety Consequence Type | Safety Probability Type |  | Safety - WRDI | Safety Consequence Type | Safety Probability Type |  | Safety - WRDI | Safety Consequence Type | Safety Probability Type |  | Safety - WRDI | Safety Consequence Type | Safety Probability Type |  | Safety - WRDI | Safety Consequence Type | Safety Probability Type |  | Safety - WRDI | Safety Consequence Type | Safety Probability Type |  | Safety - WRDI | Safety Consequence Type | Safety Probability Type |  | Safety - WRDI | Safety Consequence Type | Safety Probability Type |  | Safety - WRDI | Safety Consequence Type | Safety Probability Type |  | Safety - WRDI | Safety Consequence Type | Safety Probability Type
Safety - Baseline Impact Score | 2 | Safety - Baseline Impact Description | Minor injury to HOSSM workers due to arc flash hazards in the event of switchgear malfunction | Safety - Residual Impact Score | 2 | Safety - Residual Impact Description | Minor injury to HOSSM workers due to arc flash hazards in the event of a switchgear malfunction | Safety - Baseline Impact Score | 1 | Safety - Baseline Impact Description | N/A | Safety - Residual Impact Score | 1 | Safety - Residual Impact Description | N/A | Safety - Baseline Impact Score | Safety - Baseline Impact Description | Safety - Residual Impact Score | Safety - Residual Impact Description | Safety - Baseline Impact Score | Safety - Baseline Impact Description | Safety - Residual Impact Score | Safety - Residual Impact Description | Safety - Baseline Impact Score | Safety - Baseline Impact Description | Safety - Residual Impact Score | Safety - Residual Impact Description | Safety - Baseline Impact Score | Safety - Baseline Impact Description | Safety - Residual Impact Score | Safety - Residual Impact Description | Safety - Baseline Impact Score | Safety - Baseline Impact Description | Safety - Residual Impact Score | Safety - Residual Impact Description | Safety - Baseline Impact Score | Safety - Baseline Impact Description | Safety - Residual Impact Score | Safety - Residual Impact Description | Safety - Baseline Impact Score | Safety - Baseline Impact Description | Safety - Residual Impact Score | Safety - Residual Impact Description | Safety - Baseline Impact Score | Safety - Baseline Impact Description | Safety - Residual Impact Score | Safety - Residual Impact Description | Safety - Baseline Impact Score | Safety - Baseline Impact Description | Safety - Residual Impact Score | Safety - Residual Impact Description | Safety - Baseline Impact Score | Safety - Baseline Impact Description | Safety - Residual Impact Score | Safety - Residual Impact Description | Safety - Baseline Impact Score | Safety - Baseline Impact Description | Safety - Residual Impact Score | Safety - Residual Impact Description | Safety - Baseline Impact Score | Safety - Baseline Impact Description | Safety - Residual Impact Score | Safety - Residual Impact Description
Safety - Baseline Probability Score | 6 | Safety - Baseline Probability Description | Switchgear has malfunctioned in the current year, signifying a greatly increased probability of worst case event occuring | Safety - Residual Probability Score | 1 | Safety - Residual Probability Description | Rectified issue leads to almost 0% chance of event occurring within the next 5 years. | Safety - Baseline Probability Score | 1 | Safety - Baseline Probability Description | Very Low | Safety - Residual Probability Score | 1 | Safety - Residual Probability Description | Very Low | Safety - Baseline Probability Score | Safety - Baseline Probability Description | Safety - Residual Probability Score | Safety - Residual Probability Description | Safety - Baseline Probability Score | Safety - Baseline Probability Description | Safety - Residual Probability Score | Safety - Residual Probability Description | Safety - Baseline Probability Score | Safety - Baseline Probability Description | Safety - Residual Probability Score | Safety - Residual Probability Description | Safety - Baseline Probability Score | Safety - Baseline Probability Description | Safety - Residual Probability Score | Safety - Residual Probability Description | Safety - Baseline Probability Score | Safety - Baseline Probability Description | Safety - Residual Probability Score | Safety - Residual Probability Description | Safety - Baseline Probability Score | Safety - Baseline Probability Description | Safety - Residual Probability Score | Safety - Residual Probability Description | Safety - Baseline Probability Score | Safety - Baseline Probability Description | Safety - Residual Probability Score | Safety - Residual Probability Description | Safety - Baseline Probability Score | Safety - Baseline Probability Description | Safety - Residual Probability Score | Safety - Residual Probability Description | Safety - Baseline Probability Score | Safety - Baseline Probability Description | Safety - Residual Probability Score | Safety - Residual Probability Description | Safety - Baseline Probability Score | Safety - Baseline Probability Description | Safety - Residual Probability Score | Safety - Residual Probability Description | Safety - Baseline Probability Score | Safety - Baseline Probability Description | Safety - Residual Probability Score | Safety - Residual Probability Description | Safety - Baseline Probability Score | Safety - Baseline Probability Description | Safety - Residual Probability Score | Safety - Residual Probability Description
Environment scoring | [7 empty] | Environment scoring | [7 empty] | Environment scoring |  |  |  | Environment scoring |  |  |  | Environment scoring |  |  |  | Environment scoring |  |  |  | Environment scoring |  |  |  | Environment scoring |  |  |  | Environment scoring |  |  |  | Environment scoring |  |  |  | Environment scoring |  |  |  | Environment scoring |  |  |  | Environment scoring |  |  |  | Environment scoring
Risk Multiplier (Unitized Risk) |  | e.g., number of transformers | [5 empty] | Risk Multiplier (Unitized Risk) | [7 empty] | Risk Multiplier (Unitized Risk) |  |  |  | Risk Multiplier (Unitized Risk) |  |  |  | Risk Multiplier (Unitized Risk) |  |  |  | Risk Multiplier (Unitized Risk) |  |  |  | Risk Multiplier (Unitized Risk) |  |  |  | Risk Multiplier (Unitized Risk) |  |  |  | Risk Multiplier (Unitized Risk) |  |  |  | Risk Multiplier (Unitized Risk) |  |  |  | Risk Multiplier (Unitized Risk) |  |  |  | Risk Multiplier (Unitized Risk) |  |  |  | Risk Multiplier (Unitized Risk) |  |  |  | Risk Multiplier (Unitized Risk)
Environment - WRDI | N/A | Environment Consequence Type | Plant, animal or habitat impact | Environment Probability Type | Expected time to event |  |  | Environment - WRDI | N/A | Environment Consequence Type | Plant, animal or habitat impact | Environment Probability Type | Expected time to event |  |  | Environment - WRDI | Environment Consequence Type | Environment Probability Type |  | Environment - WRDI | Environment Consequence Type | Environment Probability Type |  | Environment - WRDI | Environment Consequence Type | Environment Probability Type |  | Environment - WRDI | Environment Consequence Type | Environment Probability Type |  | Environment - WRDI | Environment Consequence Type | Environment Probability Type |  | Environment - WRDI | Environment Consequence Type | Environment Probability Type |  | Environment - WRDI | Environment Consequence Type | Environment Probability Type |  | Environment - WRDI | Environment Consequence Type | Environment Probability Type |  | Environment - WRDI | Environment Consequence Type | Environment Probability Type |  | Environment - WRDI | Environment Consequence Type | Environment Probability Type |  | Environment - WRDI | Environment Consequence Type | Environment Probability Type |  | Environment - WRDI | Environment Consequence Type | Environment Probability Type
Environment - Baseline Impact Score | 1 | Environment - Baseline Impact Description | N/A | Environment - Residual Impact Score | 1 | Environment - Residual Impact Description | N/A | Environment - Baseline Impact Score | 1 | Environment - Baseline Impact Description | N/A | Environment - Residual Impact Score | 1 | Environment - Residual Impact Description | N/A | Environment - Baseline Impact Score | Environment - Baseline Impact Description | Environment - Residual Impact Score | Environment - Residual Impact Description | Environment - Baseline Impact Score | Environment - Baseline Impact Description | Environment - Residual Impact Score | Environment - Residual Impact Description | Environment - Baseline Impact Score | Environment - Baseline Impact Description | Environment - Residual Impact Score | Environment - Residual Impact Description | Environment - Baseline Impact Score | Environment - Baseline Impact Description | Environment - Residual Impact Score | Environment - Residual Impact Description | Environment - Baseline Impact Score | Environment - Baseline Impact Description | Environment - Residual Impact Score | Environment - Residual Impact Description | Environment - Baseline Impact Score | Environment - Baseline Impact Description | Environment - Residual Impact Score | Environment - Residual Impact Description | Environment - Baseline Impact Score | Environment - Baseline Impact Description | Environment - Residual Impact Score | Environment - Residual Impact Description | Environment - Baseline Impact Score | Environment - Baseline Impact Description | Environment - Residual Impact Score | Environment - Residual Impact Description | Environment - Baseline Impact Score | Environment - Baseline Impact Description | Environment - Residual Impact Score | Environment - Residual Impact Description | Environment - Baseline Impact Score | Environment - Baseline Impact Description | Environment - Residual Impact Score | Environment - Residual Impact Description | Environment - Baseline Impact Score | Environment - Baseline Impact Description | Environment - Residual Impact Score | Environment - Residual Impact Description | Environment - Baseline Impact Score | Environment - Baseline Impact Description | Environment - Residual Impact Score | Environment - Residual Impact Description
Environment - Baseline Probability Score | 1 | Environment - Baseline Probability Description | Very Low | Environment - Residual Probability Score | 1 | Environment - Residual Probability Description | Very Low | Environment - Baseline Probability Score | 1 | Environment - Baseline Probability Description | Very Low | Environment - Residual Probability Score | 1 | Environment - Residual Probability Description | 1 | Environment - Baseline Probability Score | Environment - Baseline Probability Description | Environment - Residual Probability Score | Environment - Residual Probability Description | Environment - Baseline Probability Score | Environment - Baseline Probability Description | Environment - Residual Probability Score | Environment - Residual Probability Description | Environment - Baseline Probability Score | Environment - Baseline Probability Description | Environment - Residual Probability Score | Environment - Residual Probability Description | Environment - Baseline Probability Score | Environment - Baseline Probability Description | Environment - Residual Probability Score | Environment - Residual Probability Description | Environment - Baseline Probability Score | Environment - Baseline Probability Description | Environment - Residual Probability Score | Environment - Residual Probability Description | Environment - Baseline Probability Score | Environment - Baseline Probability Description | Environment - Residual Probability Score | Environment - Residual Probability Description | Environment - Baseline Probability Score | Environment - Baseline Probability Description | Environment - Residual Probability Score | Environment - Residual Probability Description | Environment - Baseline Probability Score | Environment - Baseline Probability Description | Environment - Residual Probability Score | Environment - Residual Probability Description | Environment - Baseline Probability Score | Environment - Baseline Probability Description | Environment - Residual Probability Score | Environment - Residual Probability Description | Environment - Baseline Probability Score | Environment - Baseline Probability Description | Environment - Residual Probability Score | Environment - Residual Probability Description | Environment - Baseline Probability Score | Environment - Baseline Probability Description | Environment - Residual Probability Score | Environment - Residual Probability Description | Environment - Baseline Probability Score | Environment - Baseline Probability Description | Environment - Residual Probability Score | Environment - Residual Probability Description
Reliability scoring | [7 empty] | Reliability scoring | [7 empty] | Reliability scoring |  |  |  | Reliability scoring |  |  |  | Reliability scoring |  |  |  | Reliability scoring |  |  |  | Reliability scoring |  |  |  | Reliability scoring |  |  |  | Reliability scoring |  |  |  | Reliability scoring |  |  |  | Reliability scoring |  |  |  | Reliability scoring |  |  |  | Reliability scoring |  |  |  | Reliability scoring
Risk Multiplier (Unitized Risk) |  | e.g., number of transformers | [5 empty] | Risk Multiplier (Unitized Risk) | [7 empty] | Risk Multiplier (Unitized Risk) |  |  |  | Risk Multiplier (Unitized Risk) |  |  |  | Risk Multiplier (Unitized Risk) |  |  |  | Risk Multiplier (Unitized Risk) |  |  |  | Risk Multiplier (Unitized Risk) |  |  |  | Risk Multiplier (Unitized Risk) |  |  |  | Risk Multiplier (Unitized Risk) |  |  |  | Risk Multiplier (Unitized Risk) |  |  |  | Risk Multiplier (Unitized Risk) |  |  |  | Risk Multiplier (Unitized Risk) |  |  |  | Risk Multiplier (Unitized Risk) |  |  |  | Risk Multiplier (Unitized Risk)
Reliability - WRDI | Forced outages on the Wawa feeders | Reliability Consequence Type | Impact on customers | Reliability Probability Type | Probability of event occurring in next year |  |  | Reliability - WRDI | During a fault condition, isolating a segment of the line while maintaining the other segment is not possible due to current configuration. This results in outages to generation an transmission feeders on the bus. | Reliability Consequence Type | Impact on customers | Reliability Probability Type | Probability of event occurring in next year |  |  | Reliability - WRDI | Reliability Consequence Type | Reliability Probability Type |  | Reliability - WRDI | Reliability Consequence Type | Reliability Probability Type |  | Reliability - WRDI | Reliability Consequence Type | Reliability Probability Type |  | Reliability - WRDI | Reliability Consequence Type | Reliability Probability Type |  | Reliability - WRDI | Reliability Consequence Type | Reliability Probability Type |  | Reliability - WRDI | Reliability Consequence Type | Reliability Probability Type |  | Reliability - WRDI | Reliability Consequence Type | Reliability Probability Type |  | Reliability - WRDI | Reliability Consequence Type | Reliability Probability Type |  | Reliability - WRDI | Reliability Consequence Type | Reliability Probability Type |  | Reliability - WRDI | Reliability Consequence Type | Reliability Probability Type |  | Reliability - WRDI | Reliability Consequence Type | Reliability Probability Type |  | Reliability - WRDI | Reliability Consequence Type | Reliability Probability Type
Reliability - Baseline Impact Score | 5 | Reliability - Baseline Impact Description | Impacts at least 3 customers | Reliability - Residual Impact Score | 5 | Reliability - Residual Impact Description | Impacts at least 3 customers | Reliability - Baseline Impact Score | 5 | Reliability - Baseline Impact Description | Inability for station to capabily transfer 150MVA via bussing system | Reliability - Residual Impact Score | 5 | Reliability - Residual Impact Description | Inability for station to capabily transfer 150MVA via bussing system | Reliability - Baseline Impact Score | Reliability - Baseline Impact Description | Reliability - Residual Impact Score | Reliability - Residual Impact Description | Reliability - Baseline Impact Score | Reliability - Baseline Impact Description | Reliability - Residual Impact Score | Reliability - Residual Impact Description | Reliability - Baseline Impact Score | Reliability - Baseline Impact Description | Reliability - Residual Impact Score | Reliability - Residual Impact Description | Reliability - Baseline Impact Score | Reliability - Baseline Impact Description | Reliability - Residual Impact Score | Reliability - Residual Impact Description | Reliability - Baseline Impact Score | Reliability - Baseline Impact Description | Reliability - Residual Impact Score | Reliability - Residual Impact Description | Reliability - Baseline Impact Score | Reliability - Baseline Impact Description | Reliability - Residual Impact Score | Reliability - Residual Impact Description | Reliability - Baseline Impact Score | Reliability - Baseline Impact Description | Reliability - Residual Impact Score | Reliability - Residual Impact Description | Reliability - Baseline Impact Score | Reliability - Baseline Impact Description | Reliability - Residual Impact Score | Reliability - Residual Impact Description | Reliability - Baseline Impact Score | Reliability - Baseline Impact Description | Reliability - Residual Impact Score | Reliability - Residual Impact Description | Reliability - Baseline Impact Score | Reliability - Baseline Impact Description | Reliability - Residual Impact Score | Reliability - Residual Impact Description | Reliability - Baseline Impact Score | Reliability - Baseline Impact Description | Reliability - Residual Impact Score | Reliability - Residual Impact Description | Reliability - Baseline Impact Score | Reliability - Baseline Impact Description | Reliability - Residual Impact Score | Reliability - Residual Impact Description
Reliability - Baseline Probability Score | 5 | Reliability - Baseline Probability Description | 1 - 4 times per year | Reliability - Residual Probability Score | 1 | Reliability - Residual Probability Description | Less than 1 every 100 years | Reliability - Baseline Probability Score | 4 | Reliability - Baseline Probability Description | 1 every 3-10 years | Reliability - Residual Probability Score | 1 | Reliability - Residual Probability Description | Less than 1 every 100 years | Reliability - Baseline Probability Score | Reliability - Baseline Probability Description | Reliability - Residual Probability Score | Reliability - Residual Probability Description | Reliability - Baseline Probability Score | Reliability - Baseline Probability Description | Reliability - Residual Probability Score | Reliability - Residual Probability Description | Reliability - Baseline Probability Score | Reliability - Baseline Probability Description | Reliability - Residual Probability Score | Reliability - Residual Probability Description | Reliability - Baseline Probability Score | Reliability - Baseline Probability Description | Reliability - Residual Probability Score | Reliability - Residual Probability Description | Reliability - Baseline Probability Score | Reliability - Baseline Probability Description | Reliability - Residual Probability Score | Reliability - Residual Probability Description | Reliability - Baseline Probability Score | Reliability - Baseline Probability Description | Reliability - Residual Probability Score | Reliability - Residual Probability Description | Reliability - Baseline Probability Score | Reliability - Baseline Probability Description | Reliability - Residual Probability Score | Reliability - Residual Probability Description | Reliability - Baseline Probability Score | Reliability - Baseline Probability Description | Reliability - Residual Probability Score | Reliability - Residual Probability Description | Reliability - Baseline Probability Score | Reliability - Baseline Probability Description | Reliability - Residual Probability Score | Reliability - Residual Probability Description | Reliability - Baseline Probability Score | Reliability - Baseline Probability Description | Reliability - Residual Probability Score | Reliability - Residual Probability Description | Reliability - Baseline Probability Score | Reliability - Baseline Probability Description | Reliability - Residual Probability Score | Reliability - Residual Probability Description | Reliability - Baseline Probability Score | Reliability - Baseline Probability Description | Reliability - Residual Probability Score | Reliability - Residual Probability Description
Note on A2: Only use in Non Multi-Asset Risk Investments
Note on A9: Only use in Non Multi-Asset Risk Investments
Note on A16: Only use in Non Multi-Asset Risk Investments
Note on A23: Only use in Non Multi-Asset Risk Investments
Note on J9: Only use in Non Multi-Asset Risk Investments
Note on J16: Only use in Non Multi-Asset Risk Investments
Note on J23: Only use in Non Multi-Asset Risk Investments
Note on S9: Only use in Non Multi-Asset Risk Investments
Note on S16: Only use in Non Multi-Asset Risk Investments
Note on S23: Only use in Non Multi-Asset Risk Investments
Note on AB9: Only use in Non Multi-Asset Risk Investments
Note on AB16: Only use in Non Multi-Asset Risk Investments
Note on AB23: Only use in Non Multi-Asset Risk Investments
Note on AK9: Only use in Non Multi-Asset Risk Investments
Note on AK16: Only use in Non Multi-Asset Risk Investments
Note on AK23: Only use in Non Multi-Asset Risk Investments
Note on AT9: Only use in Non Multi-Asset Risk Investments
Note on AT16: Only use in Non Multi-Asset Risk Investments
Note on AT23: Only use in Non Multi-Asset Risk Investments
Note on BC9: Only use in Non Multi-Asset Risk Investments
Note on BC16: Only use in Non Multi-Asset Risk Investments
Note on BC23: Only use in Non Multi-Asset Risk Investments
Note on BL9: Only use in Non Multi-Asset Risk Investments
Note on BL16: Only use in Non Multi-Asset Risk Investments
Note on BL23: Only use in Non Multi-Asset Risk Investments
Note on BU9: Only use in Non Multi-Asset Risk Investments
Note on BU16: Only use in Non Multi-Asset Risk Investments
Note on BU23: Only use in Non Multi-Asset Risk Investments
Note on CD9: Only use in Non Multi-Asset Risk Investments
Note on CD16: Only use in Non Multi-Asset Risk Investments
Note on CD23: Only use in Non Multi-Asset Risk Investments
Note on CM9: Only use in Non Multi-Asset Risk Investments
Note on CM16: Only use in Non Multi-Asset Risk Investments
Note on CM23: Only use in Non Multi-Asset Risk Investments
Note on CV9: Only use in Non Multi-Asset Risk Investments
Note on CV16: Only use in Non Multi-Asset Risk Investments
Note on CV23: Only use in Non Multi-Asset Risk Investments
Note on DE9: Only use in Non Multi-Asset Risk Investments
Note on DE16: Only use in Non Multi-Asset Risk Investments
Note on DE23: Only use in Non Multi-Asset Risk Investments
Note on DN9: Only use in Non Multi-Asset Risk Investments
Note on DN16: Only use in Non Multi-Asset Risk Investments
Note on DN23: Only use in Non Multi-Asset Risk Investments

## Change Log
Date | Version | Comments
2018-04-27 | v0 | Initial Template
2018-05-16 | v1 | Majority of information pre-populated based on Approved Accomplishment File data if AR exists in the Approved Accomplishment File

## Template dropdowns (hidden)
Investment status
Investment Development
Scoring
Calibration
Challenge
Enterprise Engagement
Review and Approval
Investment information
Driver | Investment stage | ISD | ISD Description | Investment Code | Investment Owner
N.C.C.1.30 | Short Term Planning | GP-01 | Integrated System Operations Centre - New Facility Development | AIP000014 | Abu.Zahid@hydroone.com
N.C.C.1.40 | Executing | GP-02 | Grid Control Network Sustainment | AIP000016 | Afshin.Rezaei-Zare@HydroOne.com
N.C.C.1.50 | Prog/Proj | GP-03 | Network Management System Capital Sustainment | AIP000017 | alan.wong@hydroone.com
N.C.C.1.55 | Program | GP-04 | Integrated Voice Communications and Telephony System Refresh | AIP000018 | Alessia.Dawes@HydroOne.com
N.C.C.1.70 | Project | GP-05 | Transmission Non-Operational Data Management System | AIP000021 | Alexander.Constantinescu@HydroOne.com
N.C.C.1.75 |  | GP-06 | Operating Common IT Infrastructure | AIP000022 | Alexander.Hamlyn@HydroOne.com
N.C.C.2.10 | SDOC | GP-07 | Hardware/Software Refresh and Maintenance | AIP000023 | andrea.Lemhenyi@hydroone.com
N.C.C.2.50 | 1. Sustaining Capital | GP-08 | Forestry Work Management & Mobility | AIP000024 | Andrew.Webb@HydroOne.com
N.C.C.2.60 | 2. Development Capital | GP-09 | Corporate Services Transformation - Finance | AIP000025 | andrew.yan@HydroOne.com
N.C.C.3.01 | 3. Operations Capital | GP-10 | Corporate Services Transformation - HR / Payroll | AIP000027 | angela.mallozzi@hydroone.com
N.C.M.1.25 | 4. Capital Common Corporate Costs and Other Costs | GP-11 | Facility Accommodation & Improvements Service Centres & Admin | AIP000028 | Cecilia.Pang@HydroOne.com
N.C.M.1.50 | System OM&A | GP-12 | Transmission Facilities & Site Improvements | AIP000029 | Charlie.Lee@HydroOne.com
N.C.M.1.60 | SDOC Breakdown | GP-13 | Transport & Work Equipment | AIP000030 | Chen.Wang@HydroOne.com
N.C.M.1.70 | Connections, Upgrades | ISD-GP-24 | Station Security Upgrades | AIP000031 | chester.li@HydroOne.com
N.C.M.2.10 | Facilities & Real Estate | ISD-GP-25 | Leamington TS Capital Contribution | AIP000032 | Daniel.boutros@hydroone.com
N.C.M.2.21 | Generation Connections | ISD-GP-26 | Hanmer TS Capital Contribution | AIP000036 | Daniel.Lam@HydroOne.com
N.C.M.2.50 | Lines | ISD-GP-27 | Enfield TS Capital Contribution | AIP000043 | Daniel.Weisser@HydroOne.com
N.C.M.2.60 | Meters | ISD-SA-01 | Joint Use and Line Relocations Program | AIP000044 | dave.belluz@HydroOne.com
N.C.M.2.70 | Smart Grid Pilot | ISD-SA-02 | Metering Infrastructure Sustainment Program | AIP000045 | David.Hesch@HydroOne.com
N.C.M.3.01 | Stations | ISD-SA-03 | Meter Infrastructure Expansion Program | AIP000046 | Deniz.Turkben@HydroOne.com
N.C.M.3.03 | System Capability Reinforcement | ISD-SA-04 | New Load Connections, Upgrades, Cancellations and Metering | AIP000047 | Dhaval.Patel@hydroone.com
N.D.C.1.02 | System OM&A | ISD-SA-05 | Distributed Generation Connections | AIP000054 | Dieter.Wagner@HydroOne.com
N.D.C.1.03 | Wholesale Revenue Meters | ISD-SR-01 | Distribution Stations Demand Capital Program | AIP000056 | Dominic.Consorti@HydroOne.com
N.D.C.1.04 |  | ISD-SR-03 | Station Spare Transformer Purchases Program | AIP000060 | Donald.Lau@HydroOne.com
N.D.C.1.06 |  | ISD-SR-04 | Distribution Station Planned Component Replacement Program | AIP000061 | Donald.Mastrangelo@HydroOne.com
N.D.C.1.07 |  | ISD-SR-05 | Distribution Station Feeder Protection Upgrade | AIP000062 | E.Warren.King@HydroOne.com
N.D.C.1.08 |  | ISD-SR-06 | Distribution Station Refurbishment | AIP000063 | Emeka.Okongwu@HydroOne.com
N.D.C.1.09 |  | ISD-SR-07 | Distribution Lines Trouble Call and Storm Damage Response Program | AIP000065 | emily.booth@hydroone.com
N.D.C.1.50 |  | ISD-SR-08 | Distribution Lines PCB Equipment Replacement Program | AIP000071 | Erfan.Hajian@hydroone.com
N.D.C.1.80 |  | ISD-SR-09 | Pole Replacement Program | AIP000073 | Eva.Ping@HydroOne.com
N.D.C.2.01 |  | ISD-SR-10 | Distribution Lines Planned Component Replacement Program | AIP000074 | Farinaz.Yousefi@HydroOne.com
N.D.C.2.02 |  | ISD-SR-11 | Submarine Cable Replacement Program | AIP000075 | farooq.qureshy@hydroone.com
N.D.C.2.03 |  | ISD-SR-12 | Distribution Lines Sustainment Initiatives | AIP000077 | Fred.Kouhdani@HydroOne.com
N.D.C.2.05 |  | ISD-SR-13 | Life Cycle Optimization & Operational Efficiency Projects | AIP000079 | Gaurav.Behal@HydroOne.com
N.D.C.2.06 |  | ISD-SS-01 | Remote Disconnection / Reconnection Program | AIP000080 | Gene.Ng@HydroOne.com
N.D.C.2.10 |  | ISD-SS-02 | System Upgrades Driven by Load Growth | AIP000081 | Gert.Alikaj@HydroOne.com
N.D.C.2.23 |  | ISD-SS-03 | Reliability Improvements | AIP000082 | Gian.Minichini@HydroOne.com
N.D.C.2.60 |  | ISD-SS-04 | Demand Investments | AIP000083 | Hamid.Hamadanizadeh@HydroOne.com
N.D.C.3.08 |  | ISD-SS-05 | Distribution System Modifications | AIP000084 | hany.eskandar@hydroone.com
N.D.M.1.01 |  | ISD-SS-06 | Worst Performing Feeders | AIP000086 | Harneet.Panesar@HydroOne.com
N.D.M.1.02 |  | ISD-SS-07 | Advanced Distribution System (“ADS”) | AIP000087 | Harshal.Bhatt@hydroone.com
N.D.M.1.03 |  | SA-01 | Ramore TS: Install Second Transformer | AIP000090 | Helen.Guo@HydroOne.com
N.D.M.1.04 |  | SA-02 | Horner TS: Build a Second 230/27.6kV Station | AIP000091 | hemant.barot@hydroone.com
N.D.M.1.05 |  | SA-03 | Campbell TS: Install Metalclad Substation and Connect to Idle Transformer Windings | AIP000092 | Imran.Merali@HydroOne.com
N.D.M.1.06 |  | SA-04 | Hanmer TS: Build 230/44kV Transformer Station | AIP000101 | J.Brent.Currie@HydroOne.com
N.D.M.1.07 |  | SA-05 | Toyota Woodstock TS: Upgrade Station and Install Second 115kV Supply | AIP000105 | Jacek.Kliber@HydroOne.com
N.D.M.1.08 |  | SA-06 | Connect New IAMGOLD Mine | AIP000107 | jacky.chiu@hydroone.com
N.D.M.1.09 |  | SA-07 | Halton TS: Build a Second 230/27.6kV Station | AIP000108 | janet.eby@Hydroone.com
N.D.M.1.17 |  | SA-08 | Connect Metrolinx Traction Substations | AIP000109 | janusz.ploski@hydroone.com
N.D.M.1.60 |  | SA-09 | Future Transmission Load Connection Plans | AIP000110 | Jean.Morneau@HydroOne.com
N.D.M.1.80 |  | SA-10 | Protection and Control Modifications for Distributed Generation | AIP000111 | Jennifer.Li@HydroOne.com
N.D.M.2.02 |  | SA-11 | Future Transmission Generation Connection Plans | AIP000115 | Jenny.Seo@HydroOne.com
N.D.M.2.03 |  | SR-01 | Air Blast Circuit Breaker Replacement Projects | AIP000116 | Jerry.Vo@HydroOne.com
N.D.M.2.06 |  | SR-02 | Station Reinvestment Projects | AIP000118 | jj.blais@HydroOne.com
N.D.M.2.10 |  | SR-03 | Bulk Station Transformer Replacement Projects | AIP000120 | joseph.parete@hydroone.com
N.D.M.2.20 |  | SR-04 | Bulk Station Switchgear and Ancillary Equipment Replacement Projects | AIP000121 | Jun.Macabanti@hydroone.com
N.D.M.2.21 |  | SR-05 | Load Station Transformer Replacement Projects | AIP000122 | Khurram.Makhdoom@HydroOne.com
N.D.M.2.22 |  | SR-06 | Load Station Switchgear and Ancillary Equipment Replacement Projects | AIP000123 | Kirpal.Bahra@HydroOne.com
N.D.M.2.23 |  | SR-07 | Protection and Automation Replacement Projects | AIP000124 | kristoffer.hammel@hydroone.com
N.D.M.2.50 |  | SR-08 | John Transformer Station Reinvestment Project | AIP000125 | Kunal.Gupta@HydroOne.com
N.D.M.2.60 |  | SR-09 | Transmission Station Demand and Spares | AIP000128 | Lukito.Adiputra@HydroOne.com
N.D.M.3.01 |  | SR-10 | Transformer Protection Replacement | AIP000129 | mallen@hydroone.com
N.D.M.3.03 |  | SR-11 | Legacy SONET System Replacement | AIP000131 | Mark.Jungjohann@hydroone.com
N.D.M.4.01 |  | SR-12 | Telecom Performance Improvements | AIP000134 | mark.truchanowicz@hydroone.com
N.D.M.4.10 |  | SR-13 | ADSS Fibre Optic Cable Replacements | AIP000135 | Mark.VanTol@hydroone.com
N.D.M.9.01 |  | SR-14 | Mobile Radio System Replacement | AIP000136 | Matthew.Bell@HydroOne.com
N.T.C.1.01 |  | SR-15 | Telecom Fibre IRU Agreement Renewals | AIP000137 | Meifeng.Lian@HydroOne.com
N.T.C.1.08 |  | SR-16 | NERC CIP-014 Physical Security Implementation | AIP000138 | melissa.miron@hydroone.com
N.T.C.1.10 |  | SR-17 | Critical Station Physical Security Implementation (Non CIP-014) | AIP000139 | Michael.Medeiros@HydroOne.com
N.T.C.1.12 |  | SR-18 | PSIT Cyber Equipment Replacement | AIP000140 | michael.sullivan@hydroone.com
N.T.C.1.14 |  | SR-19 | Transmission Line Refurbishment - End of Life ACSR, Copper Conductors & Structures | AIP000142 | michael.xavier@hydroone.com
N.T.C.1.15 |  | SR-20 | Transmission Line Refurbishment - Near End of Life ACSR Conductor | AIP000143 | Mitchell.Wotton@HydroOne.com
N.T.C.1.17 |  | SR-21 | Wood Pole Structure Replacements | AIP000144 | Mohammed.Nihar@HydroOne.com
N.T.C.1.18 |  | SR-22 | Steel Structure Coating Program | AIP000145 | Mohnish.Bilimoria@hydroone.com
N.T.C.1.19 |  | SR-23 | Tower Foundation Assess/Clean/Coat Program | AIP000146 | Muhammad.Sabir@HydroOne.com
N.T.C.1.20 |  | SR-24 | Transmission Line Shieldwire Replacement | AIP000147 | Murched.Ajami@HydroOne.com
N.T.C.1.21 |  | SR-25 | Transmission Line Insulator Replacement | AIP000150 | Myla.MendinuetoMartinez@HydroOne.com
N.T.C.1.22 |  | SR-26 | Transmission Line Emergency Restoration | AIP000152 | nafiz.somjee@hydroone.com
N.T.C.1.25 |  | SR-27 | C5E/C7E Underground Cable Replacement | AIP000153 | Natalie.Briggs@HydroOne.com
N.T.C.1.28 |  | SS-01 | Nanticoke TS: Connect HVDC Lake Erie Circuits | AIP000154 | Nathan.Cox@hydroone.com
N.T.C.1.29 |  | SS-02 | Lennox TS: Install 500kV Shunt Reactors | AIP000155 | patrick.howe@hydroone.com
N.T.C.1.40 |  | SS-03 | East-West Tie Connection | AIP000156 | perry.ng@hydroone.com
N.T.C.1.41 |  | SS-04 | Watay Line to Pickle Lake Connection | AIP000157 | Peter.Erdman@HydroOne.com
N.T.C.1.42 |  | SS-05 | Merivale TS to Hawthorne TS: 230kV Conductor Upgrade | AIP000158 | peter.zhao@hydroone.com
N.T.C.1.43 |  | SS-06 | Milton SS: Station Expansion and Connect 230kV Circuits | AIP000159 | Qasim.raza@hydroone.com
N.T.C.1.44 |  | SS-07 | Cherrywood TS: Install Two Capacitor Banks | AIP000160 | Quyen.Diep@HydroOne.com
N.T.C.1.45 |  | SS-08 | Northwest Bulk Transmission Line | AIP000164 | Raj.Agnihotri@HydroOne.com
N.T.C.1.46 |  | SS-09 | Brant TS: Install 115kV Switching Facilities | AIP000165 | Raj.Ghai@HydroOne.com
N.T.C.1.75 |  | SS-10 | Kapuskasing Area Transmission Reinforcement | AIP000168 | Richard.Shannon@HydroOne.com
N.T.C.1.80 |  | SS-11 | Orillia TS: Install Sectionalizing Disconnect Switches on 230kV Circuits | AIP000172 | robert.hosford@hydroone.com
N.T.C.2.02 |  | SS-12 | Barrie TS: Upgrade Station and Reconductor E3B/E4B Circuits | AIP000173 | rossella.fazio@hydroone.com
N.T.C.2.03 |  | SS-13 | South Nepean Transmission Reinforcement | AIP000176 | ryan.boudreau@HydroOne.com
N.T.C.2.04 |  | SS-14 | Alymer-Tillsonburg Area Transmission Reinforcement | AIP000177 | Sasa.Maljukan@HydroOne.com
N.T.C.2.06 |  | SS-15 | Southwest GTA Transmission Reinforcement | AIP000178 | Sebastian.Niculae@HydroOne.com
N.T.C.2.11 |  | SS-16 | Future Transmission Regional Plans | AIP000179 | Shannon.O'Keefe@hydroone.com
N.T.C.2.12 |  | SS-17 | Customer Power Quality Program | AIP000180 | Sheraz.Majid@HydroOne.com
N.T.C.2.19 |  |  |  | AIP000181 | Sherry.Wilging@hydroone.com
N.T.C.2.20 |  |  |  | AIP000182 | Shivakumar.Kodali@HydroOne.com
N.T.C.2.21 |  | LOB | LOB NAME | AIP000183 | sinisa.grkovic@HydroOne.com
N.T.C.2.23 |  | 201 | CENTRAL TOOLS SRVCS | AIP000184 | Tameeza.Dhanani@HydroOne.com
N.T.C.2.60 |  | 202 | CUSTOMER CARE SERVICES | AIP000185 | Tarek.Othman@HydroOne.com
N.T.C.3.06 |  | 203 | PROJECT DELIVERY | AIP000186 | TeodorConstantin.Culinescu@HydroOne.com
N.T.C.3.08 |  | 204 | FORESTRY | AIP000188 | Tim.Nelson@hydroone.com
N.T.M.1.03 |  | 205 | LINES | AIP000189 | Trevor.Beausoleil@HydroOne.com
N.T.M.1.05 |  | 206 | TX LINES AND STATIONS | AIP000191 | Tyler.Wales@HydroOne.com
N.T.M.1.07 |  | 207 | SUPPLY CHAIN SERVICES | AIP000192 | warren.tingle@hydroone.com
N.T.M.1.14 |  | 208 | CUSTOMER BUS RELNS | AIP000194 | Wayne.Logan@HydroOne.com
N.T.M.1.16 |  | 209 | HEALTH, SAFETY & ENV | AIP000195 | welchw@hydroone.com
N.T.M.1.17 |  | 210 | NS UNNODED | AIP000198 | william.ilie@hydroone.com
N.T.M.1.18 |  | 211 | OGCCIT | AIP000199 | Wojciech.Maroszek@HydroOne.com
N.T.M.1.19 |  | 212 | INFO SOLUTIONS DIVISION | AIP000200
N.T.M.1.20 |  | 213 | PLANNING | AIP000203
N.T.M.1.21 |  | 214 | METER SHOP | AIP000204
N.T.M.1.22 |  | 215 | FACILITIES & REAL ESTATE | AIP000207
N.T.M.1.23 |  | 216 | BUSINESS INTEGRATION | AIP000213
N.T.M.1.24 |  | 219 | FLEET | AIP000214
N.T.M.1.28 |  | 220 | STRATEGY & CONSERV | AIP000215
N.T.M.1.29 |  | 221 | CORP FUNCTIONS & SRVCS | AIP000223
N.T.M.1.80 |  | 222 | SMART GRID | AIP000227
N.T.M.2.02 |  | 223 | SMART METERS | AIP000228
N.T.M.2.20 |  | 224 | ENGINEERING | AIP000229
N.T.M.2.21 |  | 226 | NETWORK OPERATING | AIP000230
N.T.M.2.22 |  | 227 | CORNERSTONE | AIP000231
N.T.M.2.23 |  | 228 | CONSTRUCTION | AIP000232
N.T.M.2.60 |  |  |  | AIP000233
N.T.M.3.01 |  |  |  | AIP000235
N.T.M.3.03 |  |  |  | AIP000236
N.T.M.4.10 |  |  |  | AIP000237 | Driver Owner
N.T.M.4.50 |  |  |  | AIP000238 | cindy.copp@hydroone.com
|  |  |  | AIP000244 | Daila.Dzintars@HydroOne.com
|  |  |  | AIP000248 | emre.aydin@HydroOne.com
Driver title |  |  |  | AIP000249 | Godfrey.Holder@HydroOne.com
Ancillary Systems |  |  |  | AIP000250 | hassan.hamzeh@hydroone.com
Ancillary Systems Maintenance |  |  |  | AIP000251 | Imran.Merali@HydroOne.com
Auxiliary Telecommunication Equipment |  |  |  | AIP000252 | James.Mardegan@HydroOne.com
Business Telecom |  |  |  | AIP000253 | jj.blais@HydroOne.com
Central Zone Station/Yard Investments |  |  |  | AIP000254 | john.boldt@HydroOne.com
Circuit Breakers |  |  |  | AIP000255 | joseph.parete@hydroone.com
Common Oper Infrast & Control Facilities |  |  |  | AIP000256 | Kevin.Mancherjee@HydroOne.com
Common Operating Infrastructure |  |  |  | AIP000257 | lincoln.frost-hunt@hydroone.com
Conservation and Demand Management |  |  |  | AIP000258 | lyla.garzouzi@hydroone.com
Customer Care Services Dx |  |  |  | AIP000259 | Mike.Tanaskovic@HydroOne.com
Customer Care Services Tx |  |  |  | AIP000260 | Miroslav.Kostic@HydroOne.com
Customer Meters |  |  |  | AIP000261 | Peter.Mitskos@HydroOne.com
Customer Power Quality (Dx) |  |  |  | AIP000262 | Rick.Haier@HydroOne.com
Customer Power Quality (Tx) |  |  |  | AIP000263 | robert.berardi@HydroOne.com
Distributed Generation Connections |  |  |  | AIP000264 | Robert.Reinmuller@HydroOne.com
Distributing & Regulating Stations |  |  |  | AIP000265 | ryan.boudreau@HydroOne.com
Distributing and Regulating Stations |  |  |  | AIP000266 | ted.lyberogiannis@HydroOne.com
Distribution Generation Connection |  |  |  | AIP000268 | welchw@hydroone.com
Distribution RD&D |  |  |  | AIP000269
Eastern Zone Station/Yard Investments |  |  |  | AIP000271
Engineering and Environmental Support |  |  |  | AIP000272
Engineering and Technical Services |  |  |  | AIP000273
Environment Health and Safety |  |  |  | AIP000274
Environmental Management |  |  |  | AIP000275
Fleet |  |  |  | AIP000276
Generator Customer Connection |  |  |  | AIP000277
Greater Toronto Area Zone Station/Yard Investments |  |  |  | AIP000279
Grid Operating and Control Facilities |  |  |  | AIP000280
Hamilton/Niagara Zone Station/Yard Investments |  |  |  | AIP000281
Infrastructure |  |  |  | AIP000282
Infrastructure Development |  |  |  | AIP000283
Infrastructure Maintenance |  |  |  | AIP000285
Integrated Station Component Replacement |  |  |  | AIP000287
Integrating Operating Infrastructure |  |  |  | AIP000288
IT - MFA |  |  |  | AIP000291
IT - Project & Architecture Services |  |  |  | AIP000293
IT - Sustainment and Operations |  |  |  | AIP000294
IT Business Improvements & Enhancements |  |  |  | AIP000295
IT Business Solution Development |  |  |  | AIP000296
IT Business Solutions Development |  |  |  | AIP000297
IT-Business Solution Development |  |  |  | AIP000302
Joint Use and Relocations |  |  |  | AIP000304
Land Assessment and Remediation |  |  |  | AIP000308
Leased Facilities |  |  |  | AIP000309
Line Maintenance and Repair |  |  |  | AIP000310
Lines |  |  |  | AIP000311
Load Customer Connection |  |  |  | AIP000313
Local Area Supply |  |  |  | AIP000319
Major Risk Mitigation |  |  |  | AIP000320
Metering |  |  |  | AIP000322
MFA - Real Estate Facilities |  |  |  | AIP000323
NERC Cyber Security Compliance Readiness |  |  |  | AIP000327
Network Transfer Capability |  |  |  | AIP000329
New Load Connection Upg/Cancel/Meters |  |  |  | AIP000334
Northern Zone Station/Yard Investments |  |  |  | AIP000338
Operating Infrastructure |  |  |  | AIP000339
Operation of Telecom Services |  |  |  | AIP000340
Operations Contract |  |  |  | AIP000341
Other Power Equipment |  |  |  | AIP000342
Other Services |  |  |  | AIP000343
Overhead Lines |  |  |  | AIP000347
Overhead Lines Component Refurb & Repl |  |  |  | AIP000349
P&C Enablement for Generation Connection |  |  |  | AIP000350
PCB Test and Destruction |  |  |  | AIP000351
PCB Transformer Replacement |  |  |  | AIP000354
Performance Enhancement |  |  |  | AIP000356
Power Equipment |  |  |  | AIP000357
Power Transformers |  |  |  | AIP000358
Protection Control & Metering Equip |  |  |  | AIP000359
Protection Control & Metering Equipment |  |  |  | AIP000360
Protection, Control and Telecom Maintenance |  |  |  | AIP000361
Real Estate Facilities |  |  |  | AIP000362
Real Estate Facility |  |  |  | AIP000363
Research Development and Demonstration |  |  |  | AIP000364
Rights of Way |  |  |  | AIP000365
Security Infrastructure |  |  |  | AIP000366
Smart Grid |  |  |  | AIP000367
Standards Program |  |  |  | AIP000368
System Capability Reinforcement |  |  |  | AIP000371
System Re-investment |  |  |  | AIP000372
Technology Program |  |  |  | AIP000373
Telecom Monitoring and Control |  |  |  | AIP000374
Telecommunication Assets Maintenance |  |  |  | AIP000375
Third Party Transmission System Modifications |  |  |  | AIP000377
Transmission Site Facilities |  |  |  | AIP000378
Trouble Calls & Storm Damage |  |  |  | AIP000379
Trouble Calls Customer Locates & Disconn |  |  |  | AIP000380
Tx Station Demand and Spares |  |  |  | AIP000381
U/G Lines Cable Sys & Comp Refurb & Repl |  |  |  | AIP000384
Underground Cables |  |  |  | AIP000385
Vegetation Management |  |  |  | AIP000387
Western Zone Station/Yard Investments |  |  |  | AIP000388
Wholesale Metering |  |  |  | AIP000390
Wood Pole Replacement |  |  |  | AIP000391
Work Equipment |  |  |  | AIP000392
AIP000393
AIP000394
Risk scoring |  |  |  | AIP000395
Safety Consequence Type |  |  |  | AIP000397
Impact on employee or contractor |  |  |  | AIP000399
Impact on member of public |  |  |  | AIP000401
Environment Consequence Type |  |  |  | AIP000404
PCB spill |  |  |  | AIP000408
Non PCB spill |  |  |  | AIP000411
Plant, animal or habitat impact |  |  |  | AIP000412
GHG |  |  |  | AIP000413
Geography |  |  |  | AIP000414
Surface |  |  |  | AIP000416
Duration |  |  |  | AIP000417
Recovery |  |  |  | AIP000418
AIP000420
Reliability Consequence Type |  |  |  | AIP000421
Impact on customers |  |  |  | AIP000422
Average load impacted |  |  |  | AIP000423
Unsupplied energy |  |  |  | AIP000424
Outage Duration or Customer Minutes Interrupted |  |  |  | AIP000425
Probability Type |  |  |  | AIP000426
Frequency |  |  |  | AIP000427
Expected time to event |  |  |  | AIP000428
Probability of event occurring in next year |  |  |  | AIP000429
Probability of event occurring in next 5 years |  |  |  | AIP000431
AIP000432
Confidence Type |  |  |  | AIP000433
Description |  |  |  | AIP000434
Estimate Quality |  |  |  | AIP000435
Past Experience |  |  |  | AIP000436
AIP000437
Deferral Year |  |  |  | AIP000438
2018 |  |  |  | AIP000441
2019 |  |  |  | AIP000443
2020 |  |  |  | AIP000444
2021 |  |  |  | AIP000445
2022 |  |  |  | AIP000446
2023 |  |  |  | AIP000447
2024 |  |  |  | AIP000450
2025 |  |  |  | AIP000452
2026 |  |  |  | AIP000454
2027 |  |  |  | AIP000455
2028 |  |  |  | AIP000457
2029 |  |  |  | AIP000459
2030 |  |  |  | AIP000463
AIP000464
Other investment information |  |  |  | AIP000466
Estimate Quality |  |  |  | AIP000467
Unit price |  |  |  | AIP000468
Planner estimate |  |  |  | AIP000469
Best |  |  |  | AIP000472
Detailed |  |  |  | AIP000473
OEB Investment Category |  |  |  | AIP000474
General Plant |  |  |  | AIP000481
System Access |  |  |  | AIP000482
System O&M |  |  |  | AIP000484
System Renewal |  |  |  | AIP000485
System Service |  |  |  | AIP000486
AIP000489
YES/NO |  |  |  | AIP000494
YES |  |  |  | AIP000497
NO |  |  |  | AIP000500
AIP000507
TRUE/FALSE |  |  |  | AIP000512
True |  |  |  | AIP000523
False |  |  |  | AIP000524
AIP000525
Data Quality |  |  |  | AIP000526
High |  |  |  | AIP000537
Medium |  |  |  | AIP000544
Low |  |  |  | AIP000551
AIP000552
EA Status |  |  |  | AIP000553
Complete |  |  |  | AIP000554
In Progress |  |  |  | AIP000555
Not Required |  |  |  | AIP000557
Required |  |  |  | AIP000559
TBD |  |  |  | AIP000560
AIP000562
OEB Section 92 Status |  |  |  | AIP000563
Complete |  |  |  | AIP000565
In Progress |  |  |  | AIP000566
Not Required |  |  |  | AIP000569
Required |  |  |  | AIP000570
TBD |  |  |  | AIP000571
AIP000572
Area |  |  |  | AIP000574
Central |  |  |  | AIP000576
Eastern |  |  |  | AIP000582
Greater Toronto Area |  |  |  | AIP000583
Hamilton Niagara |  |  |  | AIP000589
N/A |  |  |  | AIP000591
Northern |  |  |  | AIP000607
Western |  |  |  | AIP000608
AIP000609
Customer Relationship Code |  |  |  | AIP000613
01 - Agreement (current/future) |  |  |  | AIP000616
02 - Expectation (no agreement) |  |  |  | AIP000618
03 - None (default) |  |  |  | AIP000620
AIP000622
Investment Category |  |  |  | AIP000623
Lines Greenfield |  |  |  | AIP000624
Stations Greenfield |  |  |  | AIP000625
Lines Refurb |  |  |  | AIP000626
Stations Refurb Small (<$10M) |  |  |  | AIP000627
Medium ($10M - $50M) |  |  |  | AIP000628
Large (>$500M) |  |  |  | AIP000634
ABCB |  |  |  | AIP000636
Customer |  |  |  | AIP000638
AIP000639
Allocation Grouping |  |  |  | AIP000641
Tx - Power Systems |  |  |  | AIP000644
Dx - Power Systems |  |  |  | AIP000645
SOD |  |  |  | AIP000647
Facilities |  |  |  | AIP000650
Fleet |  |  |  | AIP000652
ISD |  |  |  | AIP000654
Security |  |  |  | AIP000655
HSE |  |  |  | AIP000656
Customer Care |  |  |  | AIP000657
AIP000658
Tx or Dx Reliability |  |  |  | AIP000662
Tx |  |  |  | AIP000664
Dx |  |  |  | AIP000667
AIP000668
Costs updated based on |  |  |  | AIP000670
Estimate Received by SP |  |  |  | AIP000673
Change in Customer Request |  |  |  | AIP000678
Regional Planning Needs |  |  |  | AIP000679
Updated Planner Estimate |  |  |  | AIP000680
AIP000684
AIP000691
AIP000694
AIP000697
AIP000698
AIP000699
AIP000700
AIP000701
AIP000703
AIP000704
AIP000707
AIP000708
AIP000718
AIP000722
AIP000723
AIP000724
AIP000726
AIP000729
AIP000731
AIP000735
AIP000743
AIP000761
AIP000763
AIP000767
AIP000768
AIP000778
AIP000780
AIP000782
AIP000786
AIP000790
AIP000792
AIP000794
AIP000798
AIP000799
AIP000803
AIP000805
AIP000806
AIP000811
AIP000813
AIP000814
AIP000816
AIP000817
AIP000820
AIP000822
AIP000842
AIP000844
AIP000845
AIP000846
AIP000847
AIP000849
AIP000853
AIP000859
AIP000863
AIP000865
AIP000869
AIP000870
AIP000874
AIP000878
AIP000882
AIP000883
AIP000884
AIP000886
AIP000890
AIP000891
AIP000896
AIP000897
AIP000908
AIP000909
AIP000910
AIP000925
AIP000926
AIP000928
AIP000931
AIP000933
AIP000937
AIP000946
AIP000954
AIP000960
AIP000965
AIP000971
AIP000979
AIP000981
AIP000982
AIP000985
AIP000986
AIP000987
AIP000992
AIP000996
AIP000997
AIP000TBD
AIP001000
AIP001006
AIP001007
AIP001008
AIP001009
AIP001010
AIP001011
AIP001012
AIP001013
AIP001015
AIP001016
AIP001017
AIP001018
AIP001019
AIP001020
AIP001022
AIP001023
AIP001024
AIP001025
AIP001026
AIP001032
AIP001033
AIP001037
AIP001040
AIP001041
AIP001042
AIP001043
AIP001044
AIP001045
AIP001046
AIP001048
AIP001050
AIP001053
AIP001058
AIP001060
AIP001062
AIP001063
AIP001064
AIP001065
AIP001068
AIP001069
AIP001071
AIP001072
AIP001073
AIP001075
AIP001077
AIP001078
AIP001079
AIP001081
AIP001083
AIP001084
AIP001085
AIP001088
AIP001089
AIP001090
AIP001093
AIP001096
AIP001100
AIP001101
AIP001102
AIP001104
AIP001106
AIP001107
AIP001109
AIP001110
AIP001111
AIP001113
AIP001114
AIP001115
AIP001118
AIP001119
AIP001120
AIP001121
AIP001122
AIP001123
AIP001124
AIP001125
AIP001127
AIP001128
AIP001129
AIP001130
AIP001133
AIP001134
AIP001135
AIP001138
AIP001139
AIP001140
AIP001143
AIP001145
AIP001146
AIP001147
AIP001148
AIP001149
AIP001151
AIP001152
AIP001153
AIP001154
AIP001156
AIP001158
AIP001159
AIP001160
AIP001162
AIP001163
AIP001164
AIP001166
AIP001168
AIP001169
AIP001170
AIP001177
AIP001179
AIP001183
AIP001184
AIP001185
AIP001186
AIP001187
AIP001188
AIP001190
AIP001191
AIP001192
AIP001215
AIP005003
AIP005007
AIP005009
AIP005011
AIP005012
AIP005013
AIP005014
AIP005015
AIP005016
AIP005018
AIP005019
AIP005020
AIP005023
AIP005024
AIP005026
AIP005030
AIP005031
AIP005033
AIP005042
AIP005045
AIP005047
AIP005048
AIP005049
AIP005051
AIP005052
AIP005053
AIP005054
AIP005055
AIP005056
AIP005058
AIP005059
AIP005078
AIP005079
AIP005080
AIP005081
AIP005083
AIP005084
AIP005086
AIP005087
AIP005088
AIP005089
AIP005090
AIP005099
AIP005103
AIP005104
AIP005107
AIP005108
AIP005109
AIP005110
AIP005111
AIP005112
AIP005115
AIP005116
AIP005117
AIP005119
AIP005120
AIP005122
AIP005123
AIP005124
AIP005125
AIP005127
AIP005128
AIP005129
AIP005130
AIP005131
AIP005135
AIP005138
AIP005139
AIP005140
AIP005141
AIP005142
AIP005144
AIP005145
AIP005146
AIP005147
AIP005149
AIP005153
AIP005154
AIP005157
AIP005160
AIP005165
AIP005166
AIP005168
AIP005169
AIP005170
AIP005172
AIP005173
AIP005174
AIP005175
AIP005178
AIP005181
AIP005182
AIP005184
AIP005187
AIP005189
AIP005190
AIP005192
AIP005193
AIP005194
AIP005195
AIP005197
AIP005198
AIP005200
AIP005201
AIP005202
AIP005203
AIP005208
AIP005209
AIP005210
AIP005212
AIP005214
AIP005225
AIP005227
AIP005228
AIP005229
AIP005230
AIP005232
AIP005234
AIP005235
AIP005237
AIP005238
AIP005240
AIP005241
AIP005242
AIP005243
AIP005246
AIP005247
AIP005248
AIP005250
AIP005261
AIP005262
AIP005263
AIP005264
AIP005265
AIP005266
AIP005267
AIP005268
AIP005269
AIP005270
AIP005272
AIP005274
AIP005276
AIP005277
AIP005278
AIP005279
AIP005280
AIP005281
AIP005283
AIP005284
AIP005290
AIP005292
AIP005296
AIP005297
AIP005299
AIP005300
AIP005303
AIP005304
AIP005305
AIP005306
AIP005308
AIP005312
AIP005313
AIP005314
AIP005315
AIP005316
AIP005319
AIP005324
AIP005325
AIP005327
AIP005328
AIP005330
AIP005331
AIP005334
AIP005336
AIP005339
AIP005340
AIP005341
AIP005342
AIP005343
AIP005346
AIP005356
AIP005358
AIP005359
AIP005360
AIP005361
AIP005362
AIP005363
AIP005364
AIP005365
AIP005366
AIP005367
AIP005369
AIP005370
AIP005371
AIP005372
AIP005373
AIP005374
AIP005375
AIP005377
AIP005378
AIP005380
AIP005381
AIP005382
AIP005383
AIP005384
AIP005385
AIP005386
AIP005387
AIP005388
AIP005391
AIP005392
AIP005393
AIP005394
AIP005395
AIP005396
AIP005397
AIP005398
AIP005399
AIP005400
AIP005401
AIP005402
AIP005403
AIP005404
AIP005405
AIP005406
AIP005411
AIP005412
AIP005413
AIP005414
AIP005416
AIP005417
AIP005418
AIP005419
AIP005420
AIP005421
AIP005422
AIP005423
AIP005424
AIP005426
AIP005428
AIP005429
AIP005431
AIP005432
AIP005433
AIP005434
AIP005435
AIP005436
AIP005439
AIP005440
AIP005441
AIP005443
AIP005444
AIP005445
AIP005447
AIP005449
AIP005450
AIP005452
AIP005453
AIP005455
AIP005456
AIP005457
AIP005458
AIP005460
AIP005463
AIP005464
AIP005465
AIP005466
AIP005467
AIP005468
AIP005469
AIP005470
AIP005471
AIP005472
AIP005473
AIP005474
AIP005475
AIP005476
AIP005477
AIP005478
AIP005480
AIP005481
AIP005482
AIP005483
AIP005484
AIP005485
AIP005488
AIP005489
AIP005490
AIP005493
AIP005498
AIP005499
AIP005500
AIP005501
AIP005502
AIP005504
AIP005506
AIP005507
AIP005508
AIP005513
AIP005515
AIP005516
AIP005517
AIP005519
AIP005520
AIP005521
AIP005522
AIP005523
AIP005524
AIP005525
AIP005526
AIP005528
AIP005530
AIP005531
AIP005532
AIP005533
AIP005534
AIP005535
AIP005536
AIP005538
AIP005540
AIP005541
AIP005547
AIP005549
AIP005551
AIP005552
AIP005554
AIP005555
AIP005556
AIP005557
AIP005575
AIP005576
AIP005577
AIP005578
AIP005579
AIP005585
AIP005586
AIP005592
AIP005599
AIP005609
AIP005610
AIP005611
AIP005612
AIP005613
AIP005614
AIP005615
AIP005616
AIP005617
AIP005618
AIP005622
AIP005623
AIP005624
AIP005625
AIP005627
AIP005628
AIP005630
AIP005631
AIP005632
AIP005633
AIP005634
AIP005635
AIP005637
AIP005638
AIP005639
AIP005640
AIP005641
AIP005642
AIP005643
AIP005644
AIP005645
AIP005646
AIP005648
AIP005649
AIP005650
AIP005651
AIP005652
AIP005653
AIP005654
AIP005656
AIP005657
AIP005658
AIP005659
AIP005660
AIP005661
AIP005662
AIP005663
AIP005664
AIP005666
AIP005667
AIP005669
AIP005670
AIP005671
AIP005672
AIP005674
AIP005675
AIP005676
AIP005677
AIP005678
AIP005679
AIP005680
AIP005681
AIP005682
AIP005683
AIP005684
AIP005685
AIP005686
AIP005687
AIP005688
AIP005689
AIP005690
AIP005691
AIP005692
AIP005694
AIP005695
AIP005696
AIP005698
AIP005699
AIP005700
AIP005701
AIP005702
AIP005703
AIP005704
AIP005705
AIP005706
AIP005707
AIP005708
AIP005709
AIP005711
AIP005712
AIP005713
AIP005714
AIP005715
AIP005716
AIP005717
AIP005718
AIP005720
AIP005721
AIP005722
AIP005723
AIP005724
AIP005725
AIP005726
AIP005727
AIP005728
AIP005729
AIP005730
AIP005731
AIP005732
AIP005733
AIP005734
AIP005735
AIP005736
AIP005737
AIP005740
AIP005741
AIP005742
AIP005744
AIP005745
AIP005746
AIP005747
AIP005748
AIP005749
AIP005750
AIP005751
AIP005752
AIP005753
AIP005754
AIP005755
AIP005756
AIP005757
AIP005758
AIP005759
AIP005760
AIP005761
AIP005762
AIP005763
AIP005765
AIP005766
AIP005767
AIP005769
AIP005770
AIP005771
AIP005772
AIP005773
AIP005774
AIP005775
AIP005776
AIP005777
AIP005779
AIP005780
AIP005781
AIP005782
AIP005783
AIP005784
AIP005785
AIP005787
AIP005788
AIP005789
AIP005790
AIP005791
AIP005792
AIP005793
AIP005794
AIP005795
AIP005796
AIP005798
AIP005799
AIP005800
AIP005801
AIP005802
AIP005803
AIP005804
AIP005805
AIP005807
AIP005808
AIP005810
AIP005811
AIP005812
AIP005813
AIP005814
AIP005815
AIP005816
AIP005817
AIP005818
AIP005819
AIP005820
AIP005821
AIP005822
AIP005823
AIP005824
AIP005825
AIP005826
AIP005827
AIP005828
AIP005829
AIP005830
AIP005831
AIP005832
AIP005833
AIP005834
AIP005835
AIP005836
AIP005837
AIP005838
AIP005839
AIP005840
AIP005842
AIP005843
AIP005844
AIP005845
AIP005846
AIP005847
AIP005850
AIP005851
AIP005853
AIP005854
AIP005855
AIP005856
AIP005857
AIP005858
AIP005859
AIP005860
AIP005861
AIP005862
AIP005863
AIP005864
AIP005866
AIP005867
AIP005868
AIP005869
AIP005870
AIP005871
AIP005872
AIP005873
AIP005874
AIP005875
AIP005876
AIP005877
AIP005878
AIP005879
AIP005880
AIP005881
AIP005883
AIP005884
AIP005885
AIP005886
AIP005887
AIP005888
AIP005889
AIP005894
AIP005895
AIP005896
AIP005899
AIP005902
AIP005904
AIP005905
AIP005906
AIP005907
AIP005908
AIP005909
AIP005910
AIP005911
AIP005912
AIP005913
AIP005914
AIP005915
AIP005916
AIP005917
AIP005918
AIP005919
AIP005920
AIP005923
AIP005924
AIP005925
AIP005926
AIP005927
AIP005928
AIP005934
AIP005944
AIP005945
AIP005948
AIP005951
AIP005954
AIP005958
AIP005959
AIP005960
AIP005961
AIP005962
AIP005963
AIP005964
AIP005965
AIP005966
AIP005967
AIP005968
AIP005970
AIP005974
AIP005975
AIP005982
AIP005985
AIP005987
AIP005991
AIP005997
AIP005998
AIP005999
AIP006004
AIP006008
AIP006012
AIP006013
AIP006015
AIP006016
AIP006017
AIP006018
AIP006020
AIP006022
AIP006026
AIP006027
AIP006028
AIP006029
AIP006030
AIP006033
AIP006034
AIP006035
AIP006036
AIP006037
AIP006038
AIP006039
AIP006040
AIP006041
AIP006042
AIP006043
AIP006044
AIP006045
AIP006046
AIP006050
AIP006051
AIP006052
AIP006053
AIP006055
AIP006056
AIP006058
AIP006059
AIP006060
AIP006061
AIP006062
AIP006063
AIP006064
AIP006065
AIP006066
AIP006067
AIP006068
AIP006069
AIP006070
AIP006071
AIP006072
AIP006073
AIP006075
AIP006076
AIP006077
AIP006079
AIP006080
AIP006081
AIP006083
AIP006084
AIP006085
AIP006087
AIP006088
AIP006089
AIP006090
AIP006091
AIP006092
AIP006093
AIP006094
AIP006097
AIP006098
AIP006100
AIP006102
AIP006103
AIP006104
AIP006105
AIP006107
AIP006108
AIP006109
AIP006111
AIP006112
AIP006113
AIP006116
AIP006120
AIP006121
AIP006122
AIP006123
AIP006125
AIP006127
AIP006128
AIP006130
AIP006131
AIP006132
AIP006134
AIP006135
AIP006137
AIP006138
AIP006139
AIP006140
AIP006141
AIP006142
AIP006143
AIP006144
AIP006145
AIP006146
AIP006147
AIP006148
AIP006149
AIP006150
AIP006151
AIP006152
AIP006153
AIP006154
AIP006155
AIP006156
AIP006157
AIP006158
AIP006159
AIP006160
AIP006160-1
AIP006161
AIP006162
AIP006163
AIP006164
AIP006165
AIP006166
AIP006167
AIP006168
AIP006169
AIP006170
AIP006171
AIP006172
AIP006173
AIP006174
AIP006175
AIP006176
AIP006177
AIP006178
AIP006179
AIP006181
AIP006182
AIP006183
AIP006184
AIP006185
AIP006186
AIP006188
AIP006189
AIP006191
AIP006195
AIP006236
AIP006237
AIP006238
AIP006239
AIP006240
AIP006241
AIP006242
AIP006243
AIP006247
AIP006248
AIP006249
AIP006251
AIP006252
AIP006253
AIP006254
AIP006261
AIP006268
AIP006273
AIP006274
AIP006275
AIP006280
AIP006281
AIP006282
AIP05760

## Sheet1 (hidden)
Driver Title | (empty)
Customer Meters
Distributed Generation Connections
Distributing & Regulating Stations
Distributing and Regulating Stations
Distribution Generation Connection
Engineering and Technical Services
IT Business Improvements & Enhancements
Joint Use and Relocations
Land Assessment and Remediation
Line Maintenance and Repair
Lines
Metering
New Load Connection Upg/Cancel/Meters
Other Services
PCB Test and Destruction
PCB Transformer Replacement
Protection, Control and Telecom Maintenance
Security Infrastructure
Smart Grid
System Capability Reinforcement
Telecom Monitoring and Control
Trouble Calls & Storm Damage
Trouble Calls Customer Locates & Disconn
Vegetation Management
Wholesale Metering
Wood Pole Replacement
Acquired Utilities - Tx Rationalization
Ancillary Systems
Ancillary Systems Maintenance
Auxiliary Telecommunication Equipment
Business Telecom
Central Zone Station/Yard Investments
Circuit Breakers
Common Oper Infrast & Control Facilities
Common Operating Infrastructure
Conservation and Demand Management
Customer Care Services Dx
Customer Care Services Tx
Customer Power Quality (Dx)
Customer Power Quality (Tx)
Distribution RD&D
Eastern Zone Station/Yard Investments
Engineering and Environmental Support
Environment Health and Safety
Environmental Management
Fleet
Generator Customer Connection
Greater Toronto Area Zone Station/Yard Investments
Grid Operating and Control Facilities
Hamilton/Niagara Zone Station/Yard Investments
Infrastructure
Infrastructure Development
Infrastructure Maintenance
Integrated Station Component Replacement
Integrating Operating Infrastructure
IT - MFA
IT - Project & Architecture Services
IT - Sustainment and Operations
IT Business Solution Development
IT Business Solutions Development
IT-Business Solution Development
Leased Facilities
Load Customer Connection
Local Area Supply
Major Risk Mitigation
MFA - Real Estate Facilities
NERC Cyber Security Compliance Readiness
Network Transfer Capability
Northern Zone Station/Yard Investments
Operating Infrastructure
Operation of Telecom Services
Operations Contract
Other Power Equipment
Overhead Lines
Overhead Lines Component Refurb & Repl
P&C Enablement for Generation Connection
Performance Enhancement
Power Equipment
Power Transformers
Protection Control & Metering Equip
Protection Control & Metering Equipment
Real Estate Facilities
Real Estate Facility
Research Development and Demonstration
Rights of Way
Standards Program
System Re-investment
Technology Program
Telecommunication Assets Maintenance
Third Party Transmission System Modifications
Transmission Site Facilities
Tx Station Demand and Spares
U/G Lines Cable Sys & Comp Refurb & Repl
Underground Cables
Western Zone Station/Yard Investments
Work Equipment
(empty)
Total Result

## Sheet2 (hidden)
ISD Description | (empty)
Advanced Distribution System (“ADS”)
Advanced Meter Infrastructure Hardware Refresh
Demand Investments
Distributed Generation Connections
Distribution Lines PCB Equipment Replacement Program
Distribution Lines Planned Component Replacement Program
Distribution Lines Sustainment Initiatives
Distribution Lines Trouble Call and Storm Damage Response Program
Distribution Station Feeder Protection Upgrade
Distribution Station Planned Component Replacement Program
Distribution Station Refurbishment
Distribution Stations Demand Capital Program
Distribution System Modifications
Enfield TS Capital Contribution
Hanmer TS Capital Contribution
Joint Use and Line Relocations Program
Leamington TS Capital Contribution
Less than $1M
Life Cycle Optimization & Operational Efficiency Projects
Meter Infrastructure Expansion Program
Metering Infrastructure Sustainment Program
Mobile Unit Substation Program
New Load Connections, Upgrades, Cancellations and Metering
No Cash Flows in 2018-2023
Pole Replacement Program
Reliability Improvements
Remote Disconnection / Reconnection Program
Station Security Upgrades
Station Spare Transformer Purchases Program
Submarine Cable Replacement Program
System OM&A
System Upgrades Driven by Load Growth
Worst Performing Feeders
Total Result

## Lookups (hidden)
Appropriation request | Description of appropriation request | LOB | LOB NAME | Driver | Driver Title | Driver Owner | ISD | ISD Description | Investment Code | Description
17005 | Kingston Gardiner TS: Increase 230-44 kV Capactiy | 201 | CENTRAL TOOLS SRVCS | N.C.C.1.30 | Fleet | robert.berardi@HydroOne.com | ISD-SA-04 | New Load Connections, Upgrades, Cancellations and Metering | AIP000177 | New Connections
17009 | Thunder Bay TGS- Bus Reconfiguration | 202 | CUSTOMER CARE SERVICES | N.C.C.1.40 | Work Equipment | Mike.Tanaskovic@HydroOne.com | ISD-SA-04 | New Load Connections, Upgrades, Cancellations and Metering | AIP000178 | New Connections - Other
17015 | Dymond TS M1 Feeder Relief | 203 | PROJECT DELIVERY | N.C.C.1.50 | Real Estate Facilities | cindy.copp@hydroone.com | ISD-SA-04 | New Load Connections, Upgrades, Cancellations and Metering | AIP000179 | Retail Revenue Meters
17018 | Greely DS F4 | 204 | FORESTRY | N.C.C.1.55 | MFA - Real Estate Facilities | cindy.copp@hydroone.com | ISD-SA-04 | New Load Connections, Upgrades, Cancellations and Metering | AIP000180 | Service Cancellations
17020 | Muskoka TS 2M6 Feeder Rehabilitation - Part 1 | 205 | LINES | N.C.C.1.70 | IT - Sustainment and Operations | lincoln.frost-hunt@hydroone.com | ISD-SA-04 | New Load Connections, Upgrades, Cancellations and Metering | AIP000181 | Service Upgrades
17037 | Long Lac T1: Replace End-of-Life 115-44 kV Transfo | 206 | TX LINES AND STATIONS | N.C.C.1.75 | IT - MFA | lincoln.frost-hunt@hydroone.com | ISD-SA-04 | New Load Connections, Upgrades, Cancellations and Metering | AIP000182 | Service Upgrades - Other
17057 | Kingston Gardiner TS - Install New Feeder Protecti | 207 | SUPPLY CHAIN SERVICES | N.C.C.2.60 | IT Business Solution Development | jj.blais@HydroOne.com | ISD-GP-24 | Station Security Upgrades | AIP000176 | Stations Security Upgrades
17071 | Toronto AreaTelecom Cable Removals | 208 | CUSTOMER BUS RELNS | N.C.C.3.01 | Common Oper Infrast & Control Facilities | Godfrey.Holder@HydroOne.com | ISD-SA-05 | Distributed Generation Connections | AIP000192 | Delta-Wye TOV Mitigation Work (Lines)
17087 | Keith TS: Upgrade T11/T12 Provide 250MVA Autos | 209 | HEALTH, SAFETY & ENV | N.C.M.1.25 | Business Telecom | lincoln.frost-hunt@hydroone.com | ISD-SA-05 | Distributed Generation Connections | AIP000191 | Small Embedded Generation
17112 | 2007+2008 Manby TS - Major Drainage Improvements | 210 | NS UNNODED | N.C.M.1.50 | Real Estate Facility | cindy.copp@hydroone.com | ISD-SA-05 | Distributed Generation Connections | AIP000194 | Distance Limitation Mitigation Work (E&T)
17113 | 2008 Major Drainage Refurbishment | 211 | OGCCIT | N.C.M.1.60 | IT Business Improvements & Enhancements | lincoln.frost-hunt@hydroone.com | ISD-SA-05 | Distributed Generation Connections | AIP000195 | Small Embedded Generation (E/PD)
17123 | Station Cap and Pin Insulator Replacement | 212 | INFO SOLUTIONS DIVISION | N.C.M.1.70 | IT - Sustainment and Operations | lincoln.frost-hunt@hydroone.com | ISD-SA-05 | Distributed Generation Connections | AIP000198 | Micro Embedded Generation Connections
17125 | Station String Insulator Replacement | 213 | PLANNING | N.C.M.2.21 | Research Development and Demonstration | Daila.Dzintars@HydroOne.com | ISD-SA-05 | Distributed Generation Connections | AIP000199 | Large Embedded Generation (E/PD)
17128 | Nanticoke TS: Add 500 kV, 350 MVAr SVC | 214 | METER SHOP | N.C.M.2.50 | Conservation and Demand Management | welchw@hydroone.com | ISD-SA-05 | Distributed Generation Connections | AIP000200 | Net Metered Embedded Generation
17130 | Grainger Jct: Install 2x230kV Switches on V71/75P | 215 | FACILITIES & REAL ESTATE | N.C.M.2.60 | IT-Business Solution Development | jj.blais@HydroOne.com | ISD-SA-01 | Joint Use and Line Relocations Program | AIP000129 | Joint Use & Line Relocations
17134 | Enbridge Ontario Wind Power A and B | 216 | BUSINESS INTEGRATION | N.C.M.2.70 | IT - Project & Architecture Services | lincoln.frost-hunt@hydroone.com | ISD-SR-07 | Distribution Lines Trouble Call and Storm Damage Response Program | AIP000134 | Damage Claims
17135 | 2008 Burlington TS Wood Pole Structures 115 kV K | 219 | FLEET | N.C.M.3.01 | Common Operating Infrastructure | Godfrey.Holder@HydroOne.com | ISD-SR-07 | Distribution Lines Trouble Call and Storm Damage Response Program | AIP000135 | Equipment Replaced (Trouble Call)
17136 | BSPS Modifications for Bruce for 2009 | 220 | STRATEGY & CONSERV | N.C.M.3.03 | Environment Health and Safety | welchw@hydroone.com | ISD-SR-07 | Distribution Lines Trouble Call and Storm Damage Response Program | AIP000136 | Post Trouble and Power Quality
17138 | Cable & Pothead Replacement Program | 221 | CORP FUNCTIONS & SRVCS | N.D.C.1.02 | Wood Pole Replacement | emre.aydin@HydroOne.com | ISD-SR-07 | Distribution Lines Trouble Call and Storm Damage Response Program | AIP000137 | Storm Damage
17142 | 2007 & 2008 Load Center and Generator Purchase | 222 | SMART GRID | N.D.C.1.03 | Joint Use and Relocations | john.boldt@HydroOne.com | ISD-SR-07 | Distribution Lines Trouble Call and Storm Damage Response Program | AIP000138 | UG Sub Replace Trouble
17144 | Fire Detection Upgrade Program | 223 | SMART METERS | N.D.C.1.04 | PCB Transformer Replacement | emre.aydin@HydroOne.com | ISD-SR-08 | Distribution Lines PCB Equipment Replacement Program | AIP000131 | PCB Overhead Equipment Replacement
17147 | Protection Replacement Program | 224 | ENGINEERING | N.D.C.1.06 | Trouble Calls & Storm Damage | emre.aydin@HydroOne.com | ISD-SR-09 | Pole Replacement Program | AIP000128 | Pole Replacement
17148 | Elgin TS; Station Refurbishment | 226 | NETWORK OPERATING | N.D.C.1.07 | Lines | emre.aydin@HydroOne.com | ISD-SR-10 | Distribution Lines Planned Component Replacement Program | AIP000139 | Component Replacement - Crossarms
17149 | Tone Equipment Replacement | 227 | CORNERSTONE | N.D.C.1.08 | Distributing & Regulating Stations | emre.aydin@HydroOne.com | ISD-SR-10 | Distribution Lines Planned Component Replacement Program | AIP000140 | Component Replacement - Nest Platforms
17150 | PC&T Systems | 228 | CONSTRUCTION | N.D.C.1.09 | Metering | Peter.Mitskos@HydroOne.com | ISD-SR-10 | Distribution Lines Planned Component Replacement Program | AIP000142 | Component Replacement - Regulators/Reclosers
17168 | DFR Sustainment Program |  |  | N.D.C.1.50 | Real Estate Facilities | cindy.copp@hydroone.com | ISD-SR-10 | Distribution Lines Planned Component Replacement Program | AIP000143 | Component Replacement - Sentinel Lights
17185 | Orangeville TS - Transmission Station Re-Inve |  |  | N.D.C.1.80 | Security Infrastructure | emre.aydin@HydroOne.com | ISD-SR-10 | Distribution Lines Planned Component Replacement Program | AIP000144 | Component Replacement - Switches
17192 | Kingsville TS: T1, T2, T3, T4 & Component Repl. |  |  | N.D.C.2.01 | New Load Connection Upg/Cancel/Meters | emre.aydin@HydroOne.com | ISD-SR-10 | Distribution Lines Planned Component Replacement Program | AIP000145 | Component Replacement - Transformers
17196 | 2007 Tx OH Component Analysis - Kinectrics |  |  | N.D.C.2.02 | System Capability Reinforcement | lyla.garzouzi@hydroone.com | ISD-SR-10 | Distribution Lines Planned Component Replacement Program | AIP000146 | Component Replacement - Overhead Conductor
17197 | 2008 Tx OH Component Analysis Kinectrics |  |  | N.D.C.2.03 | Distribution Generation Connection | ryan.boudreau@HydroOne.com | ISD-SR-11 | Submarine Cable Replacement Program | AIP000147 | Conductor Replacement - Submarine
17200 | closed-2008 Overhead Transmission Lines RoW Vege |  |  | N.D.C.2.05 | Wholesale Metering | Peter.Mitskos@HydroOne.com | ISD-SR-12 | Distribution Lines Sustainment Initiatives | AIP000152 | Large Sustainment Initiatives
17203 | PMR Maintenance & Leased Facilities |  |  | N.D.C.2.06 | Smart Grid | ryan.boudreau@HydroOne.com | ISD-SR-12 | Distribution Lines Sustainment Initiatives | AIP000153 | Small Sustainment Initiatives
17206 | 2007 Station 48V DC/DC Converter Installation |  |  | N.D.C.2.23 | Customer Power Quality (Dx) | Robert.Reinmuller@HydroOne.com | No Cash Flows in 2018-2023 | No Cash Flows in 2018-2023 | AIP000150 | Idle Line Removal
17209 | 2008 Demand Investments |  |  | N.D.C.2.60 | IT Business Solution Development | jj.blais@HydroOne.com | ISD-SA-02 | Metering Infrastructure Sustainment Program | AIP000173 | Sustainment of Meter Inventory
17216 | Supervisory Control for LV Reclosers |  |  | N.D.C.3.08 | Operating Infrastructure | Godfrey.Holder@HydroOne.com | ISD-SA-02 | Metering Infrastructure Sustainment Program | AIP005358 | Field Metering Services Installation Labor Capital
17228 | 2007/2009 Tx PCB & Regulated Waste Storage Units |  |  | N.D.M.1.01 | Trouble Calls Customer Locates & Disconn | emre.aydin@HydroOne.com | ISD-SA-03 | Meter Infrastructure Expansion Program | AIP005831 | AMI Network Expansion Economic Limits Project
17240 | Cherrywood TS x Claireville TS: Unbundle 500kV cir |  |  | N.D.M.1.02 | Line Maintenance and Repair | emre.aydin@HydroOne.com | ISD-SA-03 | Meter Infrastructure Expansion Program | AIP005832 | AMI Network Expansion Economic Limits Program
17241 | 2007 Power Equipment - Reliability Improvement Pro |  |  | N.D.M.1.03 | Vegetation Management | emre.aydin@HydroOne.com | ISD-SR-14 | Advanced Meter Infrastructure Hardware Refresh | AIP005059 | AMI Hardware Refresh
17244 | Operations Support Tools - NOMS/UWPC /EL Repl (Tx) |  |  | N.D.M.1.04 | Distributing and Regulating Stations | emre.aydin@HydroOne.com | ISD-SS-01 | Remote Disconnection / Reconnection Program | AIP005540 | Remote Disconnection Program
17247 | Kruger Port Alma Wind Farm 112 MW Generation Conne |  |  | N.D.M.1.05 | Customer Meters | Peter.Mitskos@HydroOne.com | Less than $1M | Less than $1M | AIP000168 | DS Meters - Wholesale to Retail Standard
17248 | Interface Protections to Fiber network – Ottawa |  |  | N.D.M.1.06 | PCB Test and Destruction | emre.aydin@HydroOne.com | Less than $1M | Less than $1M | AIP000172 | Revenue Meter Upgrades
17259 | Leaside TS x Bridgman TS: Build new 115kV circuit |  |  | N.D.M.1.07 | Other Services | emre.aydin@HydroOne.com | No Cash Flows in 2018-2023 | No Cash Flows in 2018-2023 | AIP005003 | Metering CDMA Replacement
17260 | Northeast Transmission Reinforcement: Install SVC |  |  | N.D.M.1.08 | Land Assessment and Remediation | emre.aydin@HydroOne.com | ISD-SS-07 | Advanced Distribution System (“ADS”) | AIP000207 | Distribution Modernization Project
17269 | GCD 16- Northern Cross Gas Generation (GCD #16) |  |  | N.D.M.1.09 | Telecom Monitoring and Control | Peter.Mitskos@HydroOne.com | ISD-SR-01 | Distribution Stations Demand Capital Program | AIP000155 | DS Demand Capital
17279 | Stayner TS x Blue Mountain - Build 2 New 44 kV Fee |  |  | N.D.M.1.17 | Protection, Control and Telecom Maintenance | joseph.parete@hydroone.com | ISD-SR-02 | Mobile Unit Substation Program | AIP000156 | DS MUS Refurbishment_Purchase Program
17285 | GCD 36- Belwood North Tie in on Hwy 9 (GCD# 36) |  |  | N.D.M.1.60 | IT Business Improvements & Enhancements | lincoln.frost-hunt@hydroone.com | ISD-SR-03 | Station Spare Transformer Purchases Program | AIP000165 | Station Spare Transformer Purchases
17288 | GCD 69A- Connection of Aeolian Proof Line EG (GCD# |  |  | N.D.M.1.80 | Security Infrastructure | Rick.Haier@HydroOne.com | ISD-SR-04 | Distribution Station Planned Component Replacement Program | AIP000154 | DS Component Replacement
17314 | 2007 Tx R&D Technology Program -Kinectrics |  |  | N.D.M.2.02 | Engineering and Technical Services | ted.lyberogiannis@HydroOne.com | ISD-SR-05 | Distribution Station Feeder Protection Upgrade | AIP000157 | DS Recloser Upgrade Program
17318 | Caledonia TS: Add 2x27.6kV Feeder Breaker Positi |  |  | N.D.M.2.03 | Distributed Generation Connections | ryan.boudreau@HydroOne.com | ISD-SR-06 | Distribution Station Refurbishment | AIP000160 | DS Station Refurbishment Program
17320 | Terry Fox MTS: Build New 230kV Line Tap |  |  | N.D.M.2.06 | Smart Grid | ryan.boudreau@HydroOne.com | Less than $1M | Less than $1M | AIP000164 | Spill Containment Program
17321 | Designated Substance and Hazardous Materials Manag |  |  | N.D.M.2.20 | Standards Program | Kevin.Mancherjee@HydroOne.com | No Cash Flows in 2018-2023 | No Cash Flows in 2018-2023 | AIP000159 | DS Station & Equipment Retirement
17323 | Designated Substances and Hazardous Material Manag |  |  | N.D.M.2.21 | Distribution RD&D | Daila.Dzintars@HydroOne.com | ISD-GP-25 | Leamington TS Capital Contribution | AIP005319 | Leamington TS Capital Contribution to Tx
17324 | Health Fairs |  |  | N.D.M.2.23 | Customer Power Quality (Dx) | Robert.Reinmuller@HydroOne.com | ISD-GP-26 | Hanmer TS Capital Contribution | AIP005423 | Hanmer TS Capital Contribution
17325 | AED Devices |  |  | N.D.M.2.50 | Conservation and Demand Management | Imran.Merali@HydroOne.com | ISD-GP-27 | Enfield TS Capital Contribution | AIP005761 | Enfield TS - capital contribution
17326 | E-Learning |  |  | N.D.M.2.60 | IT Business Solution Development | jj.blais@HydroOne.com | ISD-SR-13 | Life Cycle Optimization & Operational Efficiency Projects | AIP005263 | Clearwater Bay DS F2 (Phase 1 of 3)
17327 | Learning Management System |  |  | N.D.M.3.01 | Operations Contract | Godfrey.Holder@HydroOne.com | ISD-SR-13 | Life Cycle Optimization & Operational Efficiency Projects | AIP005381 | Manitou Lake DS & Line Work
17328 | Learning Management System |  |  | N.D.M.4.01 | Customer Care Services Dx | Imran.Merali@HydroOne.com | ISD-SR-13 | Life Cycle Optimization & Operational Efficiency Projects | AIP005386 | Margach DS F3 Voltage Conversion
17335 | 2009 Distribution System Modifications |  |  | N.T.C.1.01 | Circuit Breakers | James.Mardegan@HydroOne.com | ISD-SR-13 | Life Cycle Optimization & Operational Efficiency Projects | AIP005417 | Ridgetown palmer DS Voltage Conversion
17336 | 2009 Demand Investments |  |  | N.T.C.1.08 | System Re-investment | James.Mardegan@HydroOne.com | ISD-SR-13 | Life Cycle Optimization & Operational Efficiency Projects | AIP005429 | Burford DS Removal
17338 | 2008 Small Distribution Lines Projects |  |  | N.T.C.1.10 | Integrated Station Component Replacement | James.Mardegan@HydroOne.com | ISD-SR-13 | Life Cycle Optimization & Operational Efficiency Projects | AIP005592 | Thorold Defoe DS Voltage Conversion
17343 | 2007 & 2008 Tx R&D Technology Program - EPRI |  |  | N.T.C.1.12 | Overhead Lines Component Refurb & Repl | hassan.hamzeh@hydroone.com | ISD-SR-13 | Life Cycle Optimization & Operational Efficiency Projects | AIP005628 | Princeton DS Voltage Conversion
17353 | End of Life Replacement of Wood Poles |  |  | N.T.C.1.14 | Third Party Transmission System Modifications | john.boldt@HydroOne.com | ISD-SR-13 | Life Cycle Optimization & Operational Efficiency Projects | AIP005631 | Barry's Bay Voltage Conversion
17354 | Connection of Windrush Skyway 8 Wind Farm A |  |  | N.T.C.1.15 | U/G Lines Cable Sys & Comp Refurb & Repl | hassan.hamzeh@hydroone.com | ISD-SR-13 | Life Cycle Optimization & Operational Efficiency Projects | AIP005659 | Newport DS Voltage Conversion
17356 | Joint Use and Line Relocations |  |  | N.T.C.1.17 | Power Transformers | James.Mardegan@HydroOne.com | ISD-SR-13 | Life Cycle Optimization & Operational Efficiency Projects | AIP000184 | (2) Asset Life Cycle Optimization & Operational Efficiency
17361 | Defect Correction |  |  | N.T.C.1.18 | Other Power Equipment | James.Mardegan@HydroOne.com | ISD-SR-13 | Life Cycle Optimization & Operational Efficiency Projects | AIP005279 | Carleton Place DS Reconstruction - Line Work
17362 | Distribution Line Patrols |  |  | N.T.C.1.19 | Protection Control & Metering Equip | Miroslav.Kostic@HydroOne.com | ISD-SR-13 | Life Cycle Optimization & Operational Efficiency Projects | AIP005385 | Clearwater Bay DS F2 Voltage Conversion (Phase 2 of 3)
17365 | Recoverable - Pickering - Sewer Line - Engineering |  |  | N.T.C.1.20 | Ancillary Systems | James.Mardegan@HydroOne.com | ISD-SR-13 | Life Cycle Optimization & Operational Efficiency Projects | AIP005398 | St Thomas DS Voltage Conversion
17367 | Dx O&M Trouble Call |  |  | N.T.C.1.21 | Infrastructure | James.Mardegan@HydroOne.com | ISD-SR-13 | Life Cycle Optimization & Operational Efficiency Projects | AIP005419 | Beaver Valley RS
17368 | Dx Disconnects / Reconnects |  |  | N.T.C.1.25 | Auxiliary Telecommunication Equipment | Miroslav.Kostic@HydroOne.com | ISD-SR-13 | Life Cycle Optimization & Operational Efficiency Projects | AIP005421 | Coniston Voltage Conversion
17369 | Dx Cable Locates |  |  | N.T.C.1.28 | Transmission Site Facilities | cindy.copp@hydroone.com | ISD-SR-13 | Life Cycle Optimization & Operational Efficiency Projects | AIP005426 | Hanmer TS Feeder Development
17370 | Dx Overtime and Forestry Storm Costs |  |  | N.T.C.1.29 | NERC Cyber Security Compliance Readiness | lincoln.frost-hunt@hydroone.com | ISD-SR-13 | Life Cycle Optimization & Operational Efficiency Projects | AIP005640 | Warkworth DS Removal
17371 | Dx Capital Trouble Call Poles & Equipment |  |  | N.T.C.1.40 | Western Zone Station/Yard Investments | James.Mardegan@HydroOne.com | ISD-SR-13 | Life Cycle Optimization & Operational Efficiency Projects | AIP005654 | Alexandria Area Study
17372 | Small External Demand (Yearly) |  |  | N.T.C.1.41 | Hamilton/Niagara Zone Station/Yard Investments | James.Mardegan@HydroOne.com | ISD-SR-13 | Life Cycle Optimization & Operational Efficiency Projects | AIP005833 | Thorold Front DS Voltage Conversion
17373 | 2015/16 - Replacement of Waste Storage Sites |  |  | N.T.C.1.42 | Central Zone Station/Yard Investments | James.Mardegan@HydroOne.com | ISD-SR-13 | Life Cycle Optimization & Operational Efficiency Projects | AIP005834 | Dundas Sydenham DS Voltage Conversion
17383 | Pristine East Windsor Co-Generation |  |  | N.T.C.1.43 | Greater Toronto Area Zone Station/Yard Investments | James.Mardegan@HydroOne.com | ISD-SR-13 | Life Cycle Optimization & Operational Efficiency Projects | AIP005838 | Thorold Turner DS Voltage Conversion
17384 | Thorold Co-Generation |  |  | N.T.C.1.44 | Eastern Zone Station/Yard Investments | James.Mardegan@HydroOne.com | ISD-SR-13 | Life Cycle Optimization & Operational Efficiency Projects | AIP005855 | Thorold Ormond DS Voltage Conversion
17385 | Equipment Protective Recoating (Paint) |  |  | N.T.C.1.45 | Northern Zone Station/Yard Investments | James.Mardegan@HydroOne.com | ISD-SR-13 | Life Cycle Optimization & Operational Efficiency Projects | AIP005856 | Thorold Cleveland DS Voltage Conversion
17389 | Guelph Area Transmission Refurbishment |  |  | N.T.C.1.46 | Tx Station Demand and Spares | James.Mardegan@HydroOne.com | ISD-SR-13 | Life Cycle Optimization & Operational Efficiency Projects | AIP005861 | Thorold Allanport DS Voltage Conversion
17393 | Beck 2 TS, ABCB Replacement & Yard Upgrade |  |  | N.T.C.1.80 | Security Infrastructure | James.Mardegan@HydroOne.com | ISD-SR-13 | Life Cycle Optimization & Operational Efficiency Projects | AIP005862 | Forest Jefferson and Forest McNab DS Removals
17395 | Meaford TS M1 ID109 Silver Springs Wind Farm A |  |  | N.T.C.2.02 | Local Area Supply | Robert.Reinmuller@HydroOne.com | ISD-SR-13 | Life Cycle Optimization & Operational Efficiency Projects | AIP005863 | Lucan Market DS Voltage Conversion
17397 | Connection of Landfill to Energy Project Ottawa ge |  |  | N.T.C.2.03 | Network Transfer Capability | Robert.Reinmuller@HydroOne.com | ISD-SR-13 | Life Cycle Optimization & Operational Efficiency Projects | AIP005864 | Wallaceburg DS Removal
17411 | 2010 Small Distribution Lines Projects |  |  | N.T.C.2.11 | Load Customer Connection | Robert.Reinmuller@HydroOne.com | ISD-SR-13 | Life Cycle Optimization & Operational Efficiency Projects | AIP005871 | Embrun Area Study
17412 | 2010 Demand Investments |  |  | N.T.C.2.12 | Generator Customer Connection | Robert.Reinmuller@HydroOne.com | ISD-SR-13 | Life Cycle Optimization & Operational Efficiency Projects | AIP005872 | Brockville Town Area Study
17413 | 2010 Distribution System Modifications |  |  | N.T.C.2.19 | P&C Enablement for Generation Connection | Miroslav.Kostic@HydroOne.com | ISD-SR-13 | Life Cycle Optimization & Operational Efficiency Projects | AIP005873 | Smith Fals Area Study
17418 | Lower Mattagami Generation Connection |  |  | N.T.C.2.20 | Performance Enhancement | Robert.Reinmuller@HydroOne.com | ISD-SR-13 | Life Cycle Optimization & Operational Efficiency Projects | AIP005874 | Chesterville Area Study
17422 | Cyber Security - OGCCOT |  |  | N.T.C.2.21 | Major Risk Mitigation | Robert.Reinmuller@HydroOne.com | ISD-SR-13 | Life Cycle Optimization & Operational Efficiency Projects | AIP005875 | Ivy Lea Area Study
17424 | Upgrade Wholesale Meters at Seal Expiry |  |  | N.T.C.2.23 | Customer Power Quality (Tx) | Robert.Reinmuller@HydroOne.com | ISD-SR-13 | Life Cycle Optimization & Operational Efficiency Projects | AIP005876 | Actons Corner Area Study
17431 | 2007 Dx R&D Technology Program - Kinectrics |  |  | N.T.C.2.60 | IT Business Solutions Development | jj.blais@HydroOne.com | ISD-SR-13 | Life Cycle Optimization & Operational Efficiency Projects | AIP005877 | Russell Area Study
17437 | DouglasPointTS ID40a-Barrington Huron-Kinloss Wind |  |  | N.T.C.3.06 | Grid Operating and Control Facilities | Godfrey.Holder@HydroOne.com | ISD-SR-13 | Life Cycle Optimization & Operational Efficiency Projects | AIP005878 | Maxville Area Study
17438 | DouglasPointTS ID40b Barrington Huron-Kinloss Wind |  |  | N.T.C.3.08 | Integrating Operating Infrastructure | Miroslav.Kostic@HydroOne.com | ISD-SR-13 | Life Cycle Optimization & Operational Efficiency Projects | AIP005879 | Kemptville Area Study
17443 | 2009 E&CS Wood Pole Program |  |  | N.T.M.1.03 | Land Assessment and Remediation | Mike.Tanaskovic@HydroOne.com | ISD-SR-13 | Life Cycle Optimization & Operational Efficiency Projects | AIP005880 | Prescott Area Study
17445 | Albion TS, EOL Metalclad Replacement Project |  |  | N.T.M.1.05 | Environmental Management | Mike.Tanaskovic@HydroOne.com | ISD-SR-13 | Life Cycle Optimization & Operational Efficiency Projects | AIP005881 | Berwick - Finch Area Study
17447 | Hub Site Upgrade Program |  |  | N.T.M.1.07 | Rights of Way | hassan.hamzeh@hydroone.com | ISD-SR-13 | Life Cycle Optimization & Operational Efficiency Projects | AIP005883 | Dresden DS Removal
17449 | Pandemic Planning - Tamiflu Prophylaxis |  |  | N.T.M.1.14 | Engineering and Environmental Support | Mike.Tanaskovic@HydroOne.com | ISD-SR-13 | Life Cycle Optimization & Operational Efficiency Projects | AIP005884 | Drumbo DS Conversion
17457 | HV UG Cable - PM (Preventative Maintenance) |  |  | N.T.M.1.16 | Power Equipment | Mike.Tanaskovic@HydroOne.com | ISD-SR-13 | Life Cycle Optimization & Operational Efficiency Projects | AIP005885 | Anderdon DS Conversion
17458 | HV UG Cable - Planned CM (Corrective Maintenance) |  |  | N.T.M.1.17 | Protection Control & Metering Equipment | Miroslav.Kostic@HydroOne.com | ISD-SR-13 | Life Cycle Optimization & Operational Efficiency Projects | AIP005886 | Wardsville DS Conversion
17461 | HV UG Cable - Locates |  |  | N.T.M.1.18 | Ancillary Systems Maintenance | Mike.Tanaskovic@HydroOne.com | ISD-SR-13 | Life Cycle Optimization & Operational Efficiency Projects | AIP005887 | Rondeau DS Conversion
17466 | Pole Rentals (Yearly) |  |  | N.T.M.1.19 | Infrastructure Maintenance | Mike.Tanaskovic@HydroOne.com | ISD-SR-13 | Life Cycle Optimization & Operational Efficiency Projects | AIP005889 | Brookside DS removal
17469 | Dx Capital Storm Damage |  |  | N.T.M.1.20 | Overhead Lines | hassan.hamzeh@hydroone.com | ISD-SR-13 | Life Cycle Optimization & Operational Efficiency Projects | AIP005895 | Lily Lake DS removal
17471 | Dx Capital Trouble Sub and UG Cable |  |  | N.T.M.1.21 | Underground Cables | hassan.hamzeh@hydroone.com | ISD-SS-02 | System Upgrades Driven by Load Growth | AIP005268 | Carlisle DS Transformer Upgrade
17472 | Dx Capital Post Trouble Call & Power Quality |  |  | N.T.M.1.22 | Telecommunication Assets Maintenance | Miroslav.Kostic@HydroOne.com | ISD-SS-02 | System Upgrades Driven by Load Growth | AIP005272 | Cataraqui Woods Drive Reinforcement
17477 | Dx Capital Trouble Call Damage Claims |  |  | N.T.M.1.23 | Operation of Telecom Services | Miroslav.Kostic@HydroOne.com | ISD-SS-02 | System Upgrades Driven by Load Growth | AIP005380 | Awenda DS F1 Upgrade - Supply to Christian Island
17491 | Meter Management & Verification Ser (SLA 054) |  |  | N.T.M.1.24 | Leased Facilities | Miroslav.Kostic@HydroOne.com | ISD-SS-02 | System Upgrades Driven by Load Growth | AIP005382 | Burleigh DS F2 1ph to 3ph Conversion (Phase 1 of 2)
17492 | Wholesale Meter Services Provider (MSP) |  |  | N.T.M.1.28 | Transmission Site Facilities | cindy.copp@hydroone.com | ISD-SS-02 | System Upgrades Driven by Load Growth | AIP005383 | Allanburg TS M5 feeder
17494 | Recloser & Regulator Maintenance |  |  | N.T.M.1.29 | NERC Cyber Security Compliance Readiness | lincoln.frost-hunt@hydroone.com | ISD-SS-02 | System Upgrades Driven by Load Growth | AIP005384 | Margach DS F1 - offload stepdown transformer SD3936
17495 | Switch Maintenance |  |  | N.T.M.1.80 | Security Infrastructure | Rick.Haier@HydroOne.com | ISD-SS-02 | System Upgrades Driven by Load Growth | AIP005387 | Devlin DS F1 3ph
17498 | Sentinel Lights Maintenance |  |  | N.T.M.2.02 | Infrastructure Development | Robert.Reinmuller@HydroOne.com | ISD-SS-02 | System Upgrades Driven by Load Growth | AIP005405 | Limoges DS Relief
17501 | Insulator Washing |  |  | N.T.M.2.20 | Standards Program | Kevin.Mancherjee@HydroOne.com | ISD-SS-02 | System Upgrades Driven by Load Growth | AIP005434 | Midhurst Wilson DS
17503 | Leamington TS: New 230/27.6 kV DESN and Line cone |  |  | N.T.M.2.21 | Technology Program | Daila.Dzintars@HydroOne.com | ISD-SS-02 | System Upgrades Driven by Load Growth | AIP005436 | Orangeville TS M3 - Mayfield West
17517 | Lambton TS: Station Service Upgrade |  |  | N.T.M.2.23 | Customer Power Quality (Tx) | Robert.Reinmuller@HydroOne.com | ISD-SS-02 | System Upgrades Driven by Load Growth | AIP005644 | Kleinburg TS M6 Mayfield Rd Line Extension
17522 | CMS System Reserve / Strategic Inventory Managem |  |  | N.T.M.2.60 | IT Business Solutions Development | jj.blais@HydroOne.com | ISD-SS-02 | System Upgrades Driven by Load Growth | AIP005650 | Cumberland DS F4
17528 | Circuit Switcher Replacement Program |  |  | N.T.M.2.80 | Acquired Utilities - Tx Rationalization | bjesus@HydroOne.com | ISD-SS-02 | System Upgrades Driven by Load Growth | AIP005651 | Kingston Gardiner TS M26 Development
17529 | 2009 New Connections Upgrades & Service Cancellati |  |  | N.T.M.3.01 | Operations Contract | Godfrey.Holder@HydroOne.com | ISD-SS-02 | System Upgrades Driven by Load Growth | AIP005658 | Rose Corner F3 ( Part 1 & 2)
17531 | Ancillary Preventive Maintenance - Planned (PMO) |  |  | N.T.M.4.50 | Customer Care Services Tx | Imran.Merali@HydroOne.com | ISD-SS-02 | System Upgrades Driven by Load Growth | AIP000183 | (1) System upgrade driven by load growth
17532 | Ancillary Corrective Maintenance - Demand | [5 empty] | ISD-SS-02 | System Upgrades Driven by Load Growth | AIP005276 | Cameron DS Improvements
17533 | Payments for Ancillary Services to Third Parties | [5 empty] | ISD-SS-02 | System Upgrades Driven by Load Growth | AIP005278 | Manotick DS Feeder Relief
17534 | Infrastructure Corrective Maintenance - Demand | [5 empty] | ISD-SS-02 | System Upgrades Driven by Load Growth | AIP005392 | Ancaster West DS Upgrade
17537 | Kirkland Lake TS Civil Infrastructure Improvements | [5 empty] | ISD-SS-02 | System Upgrades Driven by Load Growth | AIP005393 | Armitage TS M22 Extension
17538 | Transmission Land Assessment and Remediation | [5 empty] | ISD-SS-02 | System Upgrades Driven by Load Growth | AIP005400 | City of Owen Sound Tie Line Reinforcement
17540 | Grounding Upgrade Program | [5 empty] | ISD-SS-02 | System Upgrades Driven by Load Growth | AIP005401 | Twelve Mile Bay DS - New Station & Feeder Development
17541 | Distribution Land Assessment and Remediation | [5 empty] | ISD-SS-02 | System Upgrades Driven by Load Growth | AIP005402 | Stouffville 10th Line DS T3
17543 | 2009 MIST Meter Upgrades | [5 empty] | ISD-SS-02 | System Upgrades Driven by Load Growth | AIP005428 | Leamington TS Feeder Development
17547 | Infrastructure Preventive Maintenance-Planned(PMO) | [5 empty] | ISD-SS-02 | System Upgrades Driven by Load Growth | AIP005639 | Town of Kirkland Lake Voltage Conversion-Part 1
17552 | ACA - Grounding System Studies | [5 empty] | ISD-SS-02 | System Upgrades Driven by Load Growth | AIP005642 | Old School DS - New Station & Feeders
17553 | Field Metering Services - PL&F (SLA D027) | [5 empty] | ISD-SS-02 | System Upgrades Driven by Load Growth | AIP005643 | Alfred DS feeder Upgrade
17557 | Support & Update of SAP/FAO/BOA and Other Database | [5 empty] | ISD-SS-02 | System Upgrades Driven by Load Growth | AIP005652 | Rockland DS T2
17564 | Corrective Maintenance - Planned | [5 empty] | ISD-SS-02 | System Upgrades Driven by Load Growth | AIP005661 | Town of Shelburne Voltage Conversion
17565 | Corrective Maintenance - Demand | [5 empty] | ISD-SS-02 | System Upgrades Driven by Load Growth | AIP005664 | Midhurst Wilson DS F1 Feeder Extension
17566 | Preventive Maintenance - Planned (PMO) | [5 empty] | ISD-SS-02 | System Upgrades Driven by Load Growth | AIP005679 | Grand Bend DS F3 Voltage Conversion
17568 | BSPS Replacement of End-of-life Equipment | [5 empty] | ISD-SS-02 | System Upgrades Driven by Load Growth | AIP005688 | King City DS - New Station & Feeders
17573 | Telecom Preventative Maintenance | [5 empty] | ISD-SS-02 | System Upgrades Driven by Load Growth | AIP005763 | Enfield TS Feeder Development
17576 | HONI-HOT Alarm Based Monitoring and Response | [5 empty] | ISD-SS-02 | System Upgrades Driven by Load Growth | AIP005827 | Manotick DS - Add F3 Feeder Position
17578 | Multi-Station Spill Containment | [5 empty] | ISD-SS-02 | System Upgrades Driven by Load Growth | AIP005828 | Beckwith DS F3 Development
17580 | Stations Environmental Compliance | [5 empty] | ISD-SS-02 | System Upgrades Driven by Load Growth | AIP005829 | Greely DS F1
17581 | Transmission PCB and Regulated Waste Manage | [5 empty] | ISD-SS-02 | System Upgrades Driven by Load Growth | AIP005830 | Perth Area Study
17582 | Spill Containment System Commissioning | [5 empty] | ISD-SS-02 | System Upgrades Driven by Load Growth | AIP005835 | Town of Dundalk voltage conversion
17584 | Environmental Mgt- Demand Corrective Mtc | [5 empty] | ISD-SS-02 | System Upgrades Driven by Load Growth | AIP005836 | Bradford North DS
17587 | 2008 R&D Program - Kinectrics | [5 empty] | ISD-SS-02 | System Upgrades Driven by Load Growth | AIP005837 | Macville DS - New 27.6kV station
17590 | 2008 R&D Program - Kinectrics | [5 empty] | ISD-SS-02 | System Upgrades Driven by Load Growth | AIP005857 | Dundas TS #2 New Feeders
17594 | Connection of OPG Wawaitin GS (Proj ID #251) | [5 empty] | ISD-SS-02 | System Upgrades Driven by Load Growth | AIP005859 | Caledonia TS New Feeders
17595 | Connection of OPG Sandy Falls GS (Proj ID #250) | [5 empty] | ISD-SS-02 | System Upgrades Driven by Load Growth | AIP005866 | Brockville 44kV Area Study
17600 | DS Station Refurbishment Program | [5 empty] | ISD-SS-02 | System Upgrades Driven by Load Growth | AIP005888 | Caledonia TS M3 Extension
17605 | DS Corrective Maintenance - Planned - Station Mtce | [5 empty] | ISD-SS-02 | System Upgrades Driven by Load Growth | AIP005918 | Medonte DS F1 - Demand Enhancement - Diamond Valley
17606 | DS Preventive Maintenance - Planned - Station Mtce | [5 empty] | ISD-SS-03 | Reliability Improvements | AIP005638 | Aylmer TS New Feeder
17635 | TODS Database Maintenance | [5 empty] | ISD-SS-03 | Reliability Improvements | AIP000185 | (3) Reliability Improvements
17636 | P&C Emergency Correctives | [5 empty] | ISD-SS-03 | Reliability Improvements | AIP005331 | Tilbury West DS Upgrade
17637 | P&C Technical Services | [5 empty] | ISD-SS-03 | Reliability Improvements | AIP005399 | Orangeville TS M3-M6 Tie Line
17638 | P&C Preventive Maintenance | [5 empty] | ISD-SS-03 | Reliability Improvements | AIP005645 | Nebo TS Feeder Extension to Binbrook - Phase 2
17639 | P&C Planned Correctives | [5 empty] | ISD-SS-03 | Reliability Improvements | AIP005858 | Puslinch DS 4th Feeder
17643 | Power Qualiy Monitoring: Install Power Quality Mon | [5 empty] | ISD-SS-03 | Reliability Improvements | AIP005860 | Tilsonburg-Norfolk Tie Line
17644 | Connection of AIM PowerGen Corp - Frogmore Wind F | [5 empty] | ISD-SS-04 | Demand Investments | AIP000188 | Demand Investments - Dx
17648 | Town of Thessalon Rebuild - Phase 4 of 4 | [5 empty] | ISD-SS-05 | Distribution System Modifications | AIP000189 | Dx System Modifications
17652 | Malvern TS: Provide Connection to 26M22 Feeder Pos | [5 empty] | ISD-SS-06 | Worst Performing Feeders | AIP005826 | Modernization of Worst Performing Feeders
17664 | Ear Falls Generation Expansion | [5 empty] | Less than $1M | Less than $1M | AIP005264 | Red Lake Tx Upgrades Capital Contribution
17674 | Cyber Security Compliance Project - Systems Manage | [5 empty] | Less than $1M | Less than $1M | AIP005825 | Fault Current Indicators Deployment Program
17675 | Rexdale TS: Provide Connection to M31 Feeder Posit | [5 empty] | No Cash Flows in 2018-2023 | No Cash Flows in 2018-2023 | AIP005229 | Wiarton RS Reconfiguration
17680 | Connection of Gengrowth - Comber Wind Farm (Proj I | [5 empty] | No Cash Flows in 2018-2023 | No Cash Flows in 2018-2023 | AIP005235 | Mattawa HVDS - New Station
17693 | Sir Adam Beck TS #1: Installation of Isolating E B | [5 empty] | No Cash Flows in 2018-2023 | No Cash Flows in 2018-2023 | AIP005260 | Courtice DS Voltage Conversion
17708 | 2008 ABB HPL Replacement Program | [5 empty] | No Cash Flows in 2018-2023 | No Cash Flows in 2018-2023 | AIP005261 | Town of Madsen Voltage Conversion
17716 | ABCB Auxillary Component Remediation | [5 empty] | No Cash Flows in 2018-2023 | No Cash Flows in 2018-2023 | AIP005267 | Nobleton DS T1 - New Transformer & Line Work
17734 | Install Animal Deterrent Fences at various Station | [5 empty] | No Cash Flows in 2018-2023 | No Cash Flows in 2018-2023 | AIP005280 | Carleton Place Supply Improvements
17740 | Generation Connection for Kingsville Energy Leamin | [5 empty] | No Cash Flows in 2018-2023 | No Cash Flows in 2018-2023 | AIP005377 | Archer Drive Voltage Conversion
17752 | Ottawa - Alta Vista Hospital Link - Recoverable | [5 empty] | No Cash Flows in 2018-2023 | No Cash Flows in 2018-2023 | AIP005397 | Arnprior Area Study Upgrades
17759 | Moses GS-St. Lawrence Line Differential Protection | [5 empty] | No Cash Flows in 2018-2023 | No Cash Flows in 2018-2023 | AIP005414 | Mattawa DS 115 kV Line Connection - Payment to Tx
17765 | New Liskeard DS #1 - Exchange Transformer & Add 3r | [5 empty] | No Cash Flows in 2018-2023 | No Cash Flows in 2018-2023 | AIP005541 | Wanstead TS Capital Contribution
17778 | Porcupine TS - Install 2x100 MVAr Shunt Cap Bank | [5 empty] | No Cash Flows in 2018-2023 | No Cash Flows in 2018-2023 | AIP005262 | Nipigon Voltage Conversion
17781 | Generation Connection for Donnandale Farm GCD ID 8 | [5 empty] | No Cash Flows in 2018-2023 | No Cash Flows in 2018-2023 | AIP005424 | Town of Meaford Tie Line Reinforcement
17783 | South Porcupine Voltage Conversion | [5 empty] | No Cash Flows in 2018-2023 | No Cash Flows in 2018-2023 | AIP005625 | Rice Lake DS F2
17786 | Jarvis TS: Install Current Limiting Reactors & Loa | [5 empty] | No Cash Flows in 2018-2023 | No Cash Flows in 2018-2023 | AIP005648 | Grenfel DS Station Relief
17795 | Station Charger Replacement Program | [5 empty] | No Cash Flows in 2018-2023 | No Cash Flows in 2018-2023 | AIP005894 | Mattawa HVDS Automation Pilot
17797 | BULK Station Service Upgrades Program | [5 empty] | No Cash Flows in 2018-2023 | No Cash Flows in 2018-2023 | AIP005916 | Corbetton DS F1 - Reinforcement
17800 | HV Capacitor Bank Replacement | [5 empty] | No Cash Flows in 2018-2023 | No Cash Flows in 2018-2023 | AIP005917 | Bradford DS F3 - Reinforcement
17810 | Oil Circuit Breaker Replacement Program | [5 empty] | System OM&A | System OM&A | AIP005970 | DriveX Tool Development
17812 | Roads Bridges & Rlwys Inspection Program | [5 empty] | System OM&A | System OM&A | AIP005618 | Duart TS - Feeder M5 - DG 487 Distance Limitation
17817 | Infrastructure Corrective Maintenance - Planned | [5 empty] | System OM&A | System OM&A | AIP005958 | Kent TS-M15-ID274-Dx-PV mitigation
17826 | Data Collection | [5 empty] | System OM&A | System OM&A | AIP000227 | Cable Locates
17827 | Joint Use and Relocations (Yearly) | [5 empty] | System OM&A | System OM&A | AIP000228 | Disconnect/Reconnect
17843 | PN Upgrades | [5 empty] | System OM&A | System OM&A | AIP000229 | O&M Costs - Storm Response
17846 | Power Transformer Rad Refurbishment / Paint | [5 empty] | System OM&A | System OM&A | AIP000230 | Trouble Call
17847 | Power Transformer Oil Dehydration Program | [5 empty] | System OM&A | System OM&A | AIP000231 | Defect Corrections
17852 | Replace EoL Stn Service Transformers | [5 empty] | System OM&A | System OM&A | AIP000232 | Distribution Patrols
17853 | Retail Revenue Meters | [5 empty] | System OM&A | System OM&A | AIP000233 | Failure Investigations
17857 | Residential, Subdivision, Expansion | [5 empty] | System OM&A | System OM&A | AIP000235 | Insulator Washing
17858 | Generation Connection for Skyway 124 Wind Farm GCD | [5 empty] | System OM&A | System OM&A | AIP000236 | Recloser & Regulator Maintenance
17871 | Connection of Matthias GS 2.812MW (GCD ID#42) | [5 empty] | System OM&A | System OM&A | AIP000237 | Switch Maintenance
17873 | DS Corrective Maintenance - Demand - Station Mtce | [5 empty] | System OM&A | System OM&A | AIP000238 | Sentinel Light Maintenance
17875 | Install 7 Capacitor Banks in SWO: OPA Near Term Me | [5 empty] | System OM&A | System OM&A | AIP000244 | Dx UVM – Public Safety and Reliability
17878 | Tx Lines - RoW G&S Preventive Maintenance | [5 empty] | System OM&A | System OM&A | AIP000248 | Dx UVM – QA/QC
17883 | Health Fairs | [5 empty] | System OM&A | System OM&A | AIP005662 | Dx UVM – Defect Correction
17891 | Trout Lake TS M8 - Replace Conductor | [5 empty] | System OM&A | System OM&A | AIP000249 | DS Corrective Maintenance - Demand - Ground & Site
17911 | Tx Lines - RoW Line Clearing | [5 empty] | System OM&A | System OM&A | AIP000250 | DS Corrective Maintenance - Demand - Station
17917 | Brockville Water DS T2 | [5 empty] | System OM&A | System OM&A | AIP000251 | DS Corrective Maintenance - Planned - Ground & Site
17918 | Brockville 44 kV Downtown Cable Rehabilitation | [5 empty] | System OM&A | System OM&A | AIP000252 | DS Corrective Maintenance - Planned - Station
17930 | H24C H26C C28C M29C Relocation Recoverable | [5 empty] | System OM&A | System OM&A | AIP000253 | DS Misc Mtce & Support - PCB Oil Retrofill
17931 | DC Signaling (remote trip) Replacement | [5 empty] | System OM&A | System OM&A | AIP000254 | DS Misc Mtce & Support - PCB Oil Sampling
17938 | Circuit Breakers - Delle Ram & Cap Refurbishment | [5 empty] | System OM&A | System OM&A | AIP000255 | DS Misc Mtce & Support - Technical Support
17942 | 2010 Generation Connections - Line Transfers Trini | [5 empty] | System OM&A | System OM&A | AIP000256 | DS Preventive Maintenance - Ground and Sites
17943 | Connection of Micro-Generation Facilities Und | [5 empty] | System OM&A | System OM&A | AIP000257 | DS Preventive Maintenance - Station
17953 | HONI-HOT Carrier Vendor Management | [5 empty] | System OM&A | System OM&A | AIP000258 | DS Transformer Overhaul Program
17954 | PSTS Leased Circuits | [5 empty] | System OM&A | System OM&A | AIP000259 | Dx Corrective Maintenance - Operating Spare
17957 | Meter Corrective Maintenance – Planned | [5 empty] | System OM&A | System OM&A | AIP000260 | Dx Preventive Maintenance - Operating Spare
17958 | Meter Preventive Maintenance – Planned | [5 empty] | System OM&A | System OM&A | AIP000261 | Field Meter Service
17959 | Neutralizing Transformer | [5 empty] | System OM&A | System OM&A | AIP000262 | Meter Management and Verification
17960 | 2010 PM Wawa Breaker Replacement Program | [5 empty] | System OM&A | System OM&A | AIP000263 | Wholesale Meter Service
17966 | GCD 1084- Generation Connection for Clear Creek II | [5 empty] | System OM&A | System OM&A | AIP000264 | On Call Environmental Assistance
17974 | Telecom PLND Corrective Maintenance | [5 empty] | System OM&A | System OM&A | AIP000265 | Overhead PCB Equipment Inspection & Testing
17984 | HONI-HOT Coordination of Network Management | [5 empty] | System OM&A | System OM&A | AIP000266 | PCB & Waste Management
17985 | HONI-HOT System Analysis | [5 empty] | System OM&A | System OM&A | AIP000268 | Data Collection
17990 | Connection of Skypower - Lennox 1 GS (ID #1072) | [5 empty] | System OM&A | System OM&A | AIP000269 | Distribution Document Management
17992 | Install 115kV Switch at L7S Tap to St Marys Cement | [5 empty] | System OM&A | System OM&A | AIP000271 | Int Plowing Match & Community Events
17993 | Procurement of materials having long lead times | [5 empty] | System OM&A | System OM&A | AIP000272 | Joint Use Audits
17995 | GCD1073-Napanee TS-Lennox #2 | [5 empty] | System OM&A | System OM&A | AIP000273 | Misc Engineering & Environmental Support
17997 | 2009 Oil Circuit Breaker Replacement and Dymond TS | [5 empty] | System OM&A | System OM&A | AIP000274 | Pole Rentals
17998 | Tx Aviation Light Replacement Program | [5 empty] | System OM&A | System OM&A | AIP000275 | Small External Demand Requests
18014 | Generation Connection of Mohawk Wind Farm Design a | [5 empty] | System OM&A | System OM&A | AIP000276 | SQI Reporting
18029 | Lambton TS M5 - St. Clair Solar 1 -ID#1007 | [5 empty] | System OM&A | System OM&A | AIP000277 | Tx Idle Lines Rental
18030 | Lambton TS M5 - St. Clair Solar 2 -ID#1008 | [5 empty] | System OM&A | System OM&A | AIP005678 | ESA Fees
18032 | Lambton TS M3 - St. Clair Solar 3 -ID#1100 | [5 empty] | System OM&A | System OM&A | AIP000279 | Land Assessment and Remediation (Dx)
18048 | Midhurst TS M3 - Relocate Snow Valley Tap | [5 empty] | System OM&A | System OM&A | AIP000280 | DX Leased Circuits
18056 | Gesner Wind Farm (formerly Vickery WF) - ID1014 | [5 empty] | System OM&A | System OM&A | AIP000281 | HOT Support - AMI
18058 | Armitage TS - M11 & M44 Retermination for PowerStr | [5 empty] | System OM&A | System OM&A | AIP000282 | DX P&C Corrective
18059 | Modeland TS Generation | [5 empty] | System OM&A | System OM&A | AIP000283 | P&C Distribution Support
18065 | Connection of Douglas New GS - ID 645 | [5 empty] | System OM&A | System OM&A | AIP000285 | ISD Customer Care
18068 | GCD 585- Connection of Wilno 9.0 MW Wind Farm Proj | [5 empty] | System OM&A | System OM&A | AIP000288 | ArcFM Business Process Support
18074 | J.Clarke Keith TS M3 ID689 Amherstburg-1 | [5 empty] | System OM&A | System OM&A | AIP000291 | ERA Surveys
18075 | J.Clarke Keith TS M4 ID1053 Amherstburg Solar | [5 empty] | System OM&A | System OM&A | AIP000293 | Short Circuit Studies
18076 | Civil Infrastructure-Stn Road & Site Improvements | [5 empty] | System OM&A | System OM&A | AIP000294 | Technical Studies
18079 | Rosseau DS F3-Feeder Development to Horseshoe Lk | [5 empty] | System OM&A | System OM&A | AIP000295 | Small Embedded Generation - CIAs/Estimates
18081 | 2011 Kirkland Lake TS-M62 Split Feeder | [5 empty] | System OM&A | System OM&A | AIP000296 | DG Coordination
18094 | Trafalgar TS: Install Two 27.6kV Fdr Brkrs Pos | [5 empty] | System OM&A | System OM&A | AIP000297 | DG Power Quality Monitoring
18102 | TC08 Essex Walker Interim GenCon | [5 empty] | System OM&A | System OM&A | AIP005024 | Class C Estimates (PD)
18104 | Essa TS & Middlport TS - Cybectec Gateways for Dx | [5 empty] | No Cash Flows in 2018-2023 | No Cash Flows in 2018-2023 | AIP000203 | Revenue Meter - Removals
18124 | TC121-08 MULTIPLE STNS 2008 Noise Abatement | [5 empty] | No Cash Flows in 2018-2023 | No Cash Flows in 2018-2023 | AIP000204 | Wholesale Metering
18143 | Smith Falls TS GenCon ID 1200
18144 | Gordie Howe International Bridge Work
18157 | ParrySoundTS ParryIsland CentralGenCon 730
18165 | 2009 PERIMETER SECURITY UPGRADE AT STATIONS
18168 | IBM PowerStream DC RT Replacement
18175 | 2008 Missigissauga Tx RoW Landscape Project
18177 | Ancillary Corrective Maintenance - Planned
18179 | Human Factors Risk Management
18180 | Human Factors Risk Management
18181 | ICM Upgrades and License Fee
18182 | ICM Upgrades and License Fee
18183 | MSD Prevention Program
18184 | MSD Prevention Program
18185 | Species at Risk
18186 | Public Safety Educational Materials
18188 | SONET Sync Clock Replacement
18202 | Arc Flash
18205 | Longueuil TS-M23-ID927-Stardale Solar Park #3
18206 | Havelock TS-M4-ID835-Healey Falls G1 Unit
18208 | Longueuil TS-M23-ID964-Stardale Solar Park #1
18210 | Longueuil TS-M23-ID 965-Stardale Solar Park #2
18226 | Environmental Mgt- Preventative Mtc Program
18236 | Richview BUCC Generator Upgrade
18238 | Essa TS - Install 245 Mvar Cap Bank
18239 | Kapuskasing TS - Install 21.6 MVAr Cap Bank
18254 | 2009 R&D Program - E&CS
18260 | Hearn TS: Rebuild Hearn SS
18271 | SQI Reporting (Yearly)
18273 | Malden TS-EG1096-Harrow I WF
18274 | Malden TS-EG1097-Harrow II WF
18275 | Malden TS-EG1098-Harrow III WF
18282 | Wolverton DS - 2010 Add Third Feeder
18297 | 2011 Fort Frances M1 phases 7 to 10 of 10
18302 | St. Thomas TS - Transfer Trip
18315 | Brant TS M14-Conductor Upgrade
18319 | Owen Sound/Line Refurbishment
18320 | Port Severn DS/Line Work
18321 | Dobbin TS M5 Blue Moon Solar Farm
18330 | Transformer Midlife Refurbishment Program
18332 | North Bay TS M1 Convert to 44 kV
18335 | Transformer Oil Leak Reduction Program
18344 | 2009 FMP - E&CS
18348 | GCD1946 - Beardmore HVDS
18357 | 2012 New Keewatin DS
18358 | 2009 GCD-Line Transfers
18359 | 2012 Keewatin DS Feeders
18360 | WSD PMO Documentation & Support
18361 | Multi-year Stations-Switch Replacement Program
18371 | H2JK & K6J - Replace HV UG Cables
18372 | 2010 Mazinaw DS/SSI
18374 | 2010 Best DS/Supply Reconfiguration
18377 | Whitney DS x Dwight DS Tie Line
18378 | 2010 Craft Creek Rd/Convert to 16 kV
18388 | GCD1201-Smith Falls
18390 | Kirkland Lake TS - Install SVC
18393 | Twelve Mile Bay DS - New Station
18397 | 2011 Kent Area/Enabler TS Feeders
18399 | ADS Phase 0
18400 | Haileybury DS F1 F2 F3 /Convert (New Liskeard)
18401 | Smart Zone
18402 | System Reserve Equip-Operating Spare Mtce&Inspect
18407 | 2010 Pefferlaw DS F3/Add Feeder
18409 | Marchwood MS - 2nd Tap Connection
18411 | A6P - Line Refurbishment Program (2010-2012)
18429 | Timmins 27.6 kV Vaults/Refurb
18435 | HV UG Cable - Demand CM (Corrective Maintenance)
18438 | Tx Lines Insulator Replacement Program - PL&F
18441 | Nuisance Wildlife Control - Civil & Assessment
18442 | Nuisance Wildlife Control - Capital Solutions
18443 | Nuisance Wildlife Control - Bus & Overhead
18446 | 2011+ Small Sustainment Initiatives
18447 | 2011+ Demand Investments
18448 | 2011+ Distribution System Modifications
18450 | Ellwood MTS 230 kV Connection
18454 | Station Battery Replacement Program
18455 | Bloomsburg MTS Modification
18470 | 2010 DX Engineering Stds Development
18471 | 2010 SACE Breaker Replacement Program
18473 | Multi-SACE Breaker Replacement
18482 | Int. Plowing Match/Community Events
18484 | Kam Reg DS F1/Convert to 16 kV-Stage 1
18488 | TECHS-LINES-Standards-Dx
18497 | Steel Structure Coating Program – PL
18505 | Hanmer TS - Install Additional 149 MVAr Shunt Cap
18506 | Interconnection: Upgrade Pool Niagara A
18507 | Telecommunication Performance Improvement
18533 | Enfield TS (Formerly Oshawa Area TS)- Build 230/44
18538 | 2005-06 Nanticoke TS TSI & ABCB Repl. Prog.
18553 | Birch Island DS F2 - Replace 1.7 km Aerial Water
18588 | Pilot Project - GE F60 Hi-Z Module
18589 | Pinard TS: Reconfig 115 kV, Build Swyrd, Demerge
18623 | Nobel SS: Install series capacitor banks
18627 | HSE Compliance Audits
18628 | Public Safety Educational Materials
18629 | Health & Rehab Services
18630 | Specialist HSE Resources
18631 | Health & Safety Conference
18633 | HSE Compliance Audits
18634 | Public Electrical Safety Presentations in Schools
18635 | Health & Rehab Services
18636 | Specialist HSE Resources
18637 | Health & Safety Conference
18639 | EMF Measurements
18669 | 2008 - Rainy River DS - F1 & F2 - 4.16kV Feeders P
18675 | HODS - A CORPORATE DOCUMENT SYSTEM
18676 | HODS - A CORPORATE DOCUMENT SYSTEM
18679 | DC signalling replacement in Hamilton area
18681 | closed-2005 HV UG Cable Maintenance Prog-Kinectric
18682 | 2006-07 Station Service Upgrades - DESN
18684 | 2007 Station Service Upgrades - BULK
18685 | Brockville Area Reliability Improvements
18713 | Rosseau DS - New 7.5 MVA 44-12.48 kV Distribution
18714 | Stayner TS x Wasaga Beach - Extend 44 kV Feeder
18725 | 2006 Purchase Operating Spare Station Service Tran
18740 | 2006 Civil/Geotech - Footings & Foundation Works
18764 | E-Learning
18773 | Holland TS - 44kV feeder development
18784 | Kleinburg TS Feeders to Bolton Area
18795 | Timmins M9 Feeder Extension
18805 | Commerce Way TS:Build new TS
18808 | Build New Duart TS
18811 | DESN Station Service Upgrades Program
18812 | 2006 Tx Site Facility Capital
18830 | Tx Operating Facilities Sustainment / NMS Upgrade
18835 | CNR/Nova Steel Modifications to Q2AH/Q5G
18839 | New 500 kV Bruce to Milton Double Circuit Line
18843 | St. Lawrence TS: Revise Beauharnois - Saunders GR
18850 | 2010 Station Service Upgrades - BULK (Formerly 200
18860 | Ringwood DS T3 27.6kV Addition
18864 | North Bay TS: Upgrade to a 115-44 kV TS
18873 | Pleasant TS new M21 feeder
18883 | Oil Farm Operation Program
18884 | P3S/P4S - Line Refurbishment Program (2009-2010)
18890 | Station Surge Arrester Replacement Program
18893 | TELCO CHARGES - VOICE
18894 | OPS AND CARRIER MGMT
18899 | TELCO CHARGES - DATA
19095 | Transmission Site Maintenance
19096 | Water Supply Upgrade
19098 | Critical Station Infrastructure Security
19100 | HQ & Admin & SC & OGCC Facilities - Operations & M
19102 | Facilities Accommodation Project (Picton SC)
19107 | Orillia TS Fence 2009
19108 | Essa TS Fence 2009
19110 | Muskoka TS Fence 2009
19114 | Lake TS Fence 2009
19115 | Lorne Park TS Fence 2009
19117 | Middleport TS Fence 2009
19118 | Palermo TS Fence 2009
19119 | Bronte TS Fence 2009
19120 | Claireville TS Fence 2009
19121 | St Lawrence TS Fence 2009
19125 | Cedar TS Fence 2009
19129 | Lauzon TS Fence 2009
19130 | Parry Sound TS Fence 2009
19132 | Riverdale TS Fence 2009
19174 | HQ 483 Bay Street Tenant Improvements 2012 -2015
19179 | Bldg Repair Roof TS Facilities
19183 | Facilities Improvements Admin & SC
19206 | Bruce x Milton OPGW
19210 | Horner TS: Install 2 x 27.6 kV Feeder Positions
19213 | Malden TS-M11-ID1099-Harrow IV Wind Farm
19214 | Station Grounding System Repairs
19216 | LV Cap Bank Replacement Program
19243 | NMS Enhancements
19248 | Dx UVM - Public Safety and Reliability
19250 | Multi Year HVIT Replacement Program
19254 | Field Switching - Stations
19259 | To Be Closed - Distribution Document Management
19261 | Trout Creek DS-F1-ID10020-South River Small Hydro
19267 | Greener Choices
19268 | Dx UVM - QA/QC
19270 | DC203 2010 Capacity Allocation Exempt Gen Conn
19275 | Level II Inspections - Stations
19276 | Field Verification - Stations
19277 | Customer Event Investigation - Stations
19278 | Emergency Preparedness - Stations
19279 | Operating Diagrams - E&CS
19281 | Operating Facilities Support & Mtce - OGCC IT
19282 | Control System Technical Support - OGCC IT
19285 | Network Operations Buildings Sustainment
19289 | DS Recloser Upgrade Program
19295 | Kenora TS - Power Angle Relay Decommissioning
19297 | Kirkland Lake TS - Add 44kV Feeder Position
19299 | DS Transformer Purchase Program
19301 | DS Technical Support Program
19309 | Environmental Mgt- Planned Corrective Mtc Program
19310 | DS Transformer / ULTC Refurbishments
19337 | DS Demand/Emergency Capital Program
19338 | DS Station Refurbishment Program
19339 | DS Component Replacement Program
19341 | DS MUS Refurbishment Program
19349 | Tx Lines - RoW Unplanned Work
19353 | TX Stations Cleanup Program
19357 | Tx Lines - RoW Condition Patrols
19358 | Tx Lines - RoW Program Management
19359 | Tx Lines - RoW Notifications
19365 | Tx Lines - RoW Brush Control
19372 | Field verification of DS Operating Diagrams
19373 | Emergency Preparedness Funding
19374 | D058 OGCC Data Collection & Information Updates
19381 | Dual Station LAN
19383 | Tx Lines - RoW G&S Demand Corrective Maintenance
19384 | Ottawa - Hwy 417 Interchange_Recoverable
19386 | 600 Volt Self Contained to 120/208 Xfr Rated
19397 | Strategic Sourcing for Transmission Transformers
19405 | 750MVA Autotransformer Remediation Prog
19411 | TELCO CHARGES - BELL MSA - 2009 to 2013
19425 | IESO SIA's
19427 | Technical Support E&CS <50 hours
19428 | Technical Support E&CS >50 hours
19429 | Technical Support External
19430 | Technical Support Stations
19432 | Telecom Mgmt of Drawings/Records
19436 | Overhead Tx Lines - Demand Work - PL
19457 | TC219 Advance Release for 17 Generator Connections
19459 | Shieldwire Replacement Program - E&CS
19461 | ISD Project Governance
19462 | Tx Lines Emergency Replacements
19463 | Tx Lines - TC112 ROW projects
19466 | Caledonia TS M4 ID10650 Walpole1 10MW Solar Projct
19467 | Caledonia TS M4 ID10720 Walpole2 10MW Solar Projct
19469 | Microwave Replacement - Phase 3 drawings
19482 | Inergi Base Services
19484 | IT 3RD PARTY CONTRACTS
19488 | PeakSaver Aggregator Agreement
19500 | TELCO PROJECTS -MAC Changes (non Bell) 2010
19502 | Dx Operating Facilities Sustainment
19507 | Infra / Tech Refresh Capital
19509 | Infra / Tech Refresh OM&A - 2010
19510 | MFA Client Tech & Periph Refresh
19512 | MFA Telecom Tech Refresh
19514 | Security OM&A
19520 | Microwave Tower Remote Alarm Monitoring
19523 | Transmission Management of Records
19529 | Joint Use Audits (Yearly)
19532 | DX-External Standards Dev
19533 | 2010 TX Engineering Standards Dev't and Maint
19534 | YEC 393 MW Generation Connections
19686 | Thunder Bay - Hwy 11/17-Pearl Lake_Recoverable
19755 | Tx TECHS-Stations Standards
19756 | TX-External Standards Dev
19757 | Disaster Rec Readiness Capital
19759 | Disaster Rec Readiness OM&A
19761 | Cornerstone Phase 3 - Capital
19763 | Oshawa-Hwy 407 Ext.-Sideline 4_Recoverable
19765 | DX AM Standards Dev
19766 | TX AM Standards Dev
19767 | Security Capital
19768 | Enterprise Content Management - Capital - 2010
19769 | Enterprise Content Management - OM&A - 2010
19776 | Dx PCB Reduction Program - Testing
19780 | Load Transfer Studies
19786 | Wilhaven DS F5 (North Service Road) Tie Line
19788 | Cyber Vulnerability Assessment
19790 | CSC-ESP Annual Reviews-PSIT
19794 | CSC-System Management-PSIT
19823 | CSO Regulatory Compliance - MR & Billing
19824 | CSO Regulatory Compliance - Collections
19827 | Final Destination-Enterprise GIS DB Development
19829 | Enterprise GIS
19831 | Tx Lines Foundation Life Extension-CN
19836 | Cornerstone Phase 3 - OM&A
19839 | Field Collections
19840 | OM&A portion of Enterprise GIS Capital Projects
19843 | CSO Service Enhancements - Contact Handling
19847 | Grid Ops Zone Services Specialist Support to SIP
19850 | Overhead Tx Lines - Preventative Maintenance - PL
19865 | Overhead Tx Lines - Condition Assessment - PL
19866 | Overhead Tx Lines - Corrective Maintenance - PL
19867 | Overhead Tx Lines - Technical Support - PL
19868 | Overhead Tx Lines - Technical Support - Kinectrics
19869 | Overhead Tx Lines - Corrective Maintenance - E&CS
19872 | CSO Regulatory Compliance - Contact Handling
19873 | CSO Sustainment
19874 | CSO Volume
19875 | CSO Service Enhancements - MR & Billing
19876 | CSO Service Enhancements - Collections
19880 | Settlements Sustainment
19881 | Settlements Sustainment
19902 | Barwick TS: Build a new 115-44 kV TS
19903 | FMP and Drawing Demerger
19906 | R&D Program- External
19908 | Field Switching - Lines
19914 | Transformer Station ACA
19917 | Physical Security
19919 | 2010 System Management
19920 | Tilbury TS-M1-ID 1477-Tilbury Solar 2
19927 | East-West Tie Connection
19928 | DS Spill Containment Program
19930 | Field Special Investigations
19931 | Substandard Clearance Correction Program - L&FS
19936 | Meter Reading - Prov. Lines
19940 | CSO Service Support - 3rd Party - Contact Handling
19941 | CSO Service Support - 3rd Party - MR & Billing
19942 | CSO Service Support - 3rd Party - Collections
19944 | IESO Meter Data Validation - Stations
19946 | St Isidore TS: Add 44 kV Feeder breaker
19947 | Chesterville TS -Add 44kV Feeder
19948 | Ottawa Area- Build Orleans TS
19952 | Cedar Mills DS F2 conversion- Demand PQ Work
19967 | Dx Smart Grid Miscellaneous studies
19968 | MSP Support
19975 | Meter Reading Ancilliary Services
19979 | Other, EI, Data Collection
19988 | Component Replacement - Regulators/Reclosers
19994 | 2010 Budget N.T.C.1.28
19998 | Belleville TS: Replace Neutral Reactors
20013 | To be Closed - Misc Eng & Environmental Support
20015 | IED Data Extraction - Distance to Fault
20025 | Large Project
20026 | Customer Upgrade
20027 | Upgrade - Other
20028 | Upgrade - Large Project
20029 | Service Cancellations
20035 | Single Line Diagram & SSLA Support – E&PD
20036 | IESO Meter Data Validation - Stations
20040 | Funds Transferred from DC203
20045 | Tx Wood Pole Replacement Program - L&FS
20047 | Ongoing Maintenance support
20049 | DX Leased Circuits
20062 | CGE Ellesmere TS T3 & T4 Replace EOL Transformer
20064 | Meter Conversions and Efficiency Improvements
20073 | Wholesale to Retail Standard (New meter w TCP/IP)
20074 | Transformer/OCB/Component Refurbishment Program
20075 | Milton TS and 230kV Lines
20076 | 2010 L7S Wood Structure Replacement
20099 | Component Replacement - Crossarms
20112 | Clarington TS: New 500/230kV station
20118 | Tx Lines Foundation Assess/Clean/Coat-PL
20120 | Component Replacement - Nest Platforms
20121 | Component Replacement - Transformers
20122 | Abandoned Line Removal
20123 | Component Replacement - Sentinel Lights
20124 | Conductor Replacement - Submarine
20125 | Component Replacement - Switches
20131 | Connect the Samsung Chatham Tx Project
20132 | Connect the Samsung Nanticoke Tx Project
20133 | Uxbridge DS #1: Build new feeders
20139 | Carlaw A6-A7 Metalclad Swgr
20141 | Wiltshire TS T1/T6; A5-A6 M/C & Component Replacem
20145 | DS Preventive Maintenance - Planned - Ground &Site
20146 | DS Corrective Maintenance - Planned - Ground &Site
20147 | Strachan TS T12/T14; A7-A8 M/C & Comp Replacement
20148 | DS Corrective Maintenance - Demand - Ground & Site
20151 | Toronto-TTC Maintenance Facility_Recoverable
20152 | Wiltshire A3-A4 Metalclad Swgr
20153 | Strachan TS T12/T14; A5-A6 M/C & Comp Replacement
20154 | Carlaw TS: A4-A5 M/C Replacement
20171 | Manby TS: Uprate 115kV Switchyard
20190 | OPA Programs
20198 | Fort William TS ID 767 Skypower Thunde Bay Hy(TX)
20208 | Telecom DCN Security Enhancement
20216 | Tx PCB Reduction Program - Testing
20232 | Local Control Computer (LCC) Replacement
20241 | Install TF UCL Fall Protection Device -Base Plates
20246 | Uxbridge DS #1: Land Purchase
20247 | Vibration Damper Replacement Program - E&CS
20251 | Smart Grid Discovery Phase
20256 | Merivale GIS 'ITE' Bus Replacement
20258 | Energy Storage Study - Large Scale Urban Utility
20259 | Energy Hub Management System - OCE
20261 | Power Transformer ULTC Mod's/Upgrades Program
20265 | Bruce A & B Station Service Upgrades
20275 | Doane DS Second Transformer Addition and Feeders
20278 | Shieldwire Replacement Program - L&FS
20286 | SF6 Breaker Replacement Program (All Types)
20291 | Detour Lake - 230kV Mine Connection
20296 | Transmission Health Safety and Environment
20300 | Distribution Health Safety and Environment
20304 | Tx Lines 500KV Foundation Repair/Replace
20307 | In-Line Circuit Breakers (Summerhaven)
20311 | CGE Brantford TS T3 & T4 - Replace EOL Trfrmr
20312 | Specs, Scope, and Tendering of PQ Meters for DG
20317 | CGE Finch TS T3 & T4 - Replace EOL Trfrmr
20318 | Placeholder - Unforeseen Risk Mitigation
20322 | Underfrequency Load Shedding Upgrades
20325 | Tx Lines Insulator Replacement Program - CS
20331 | Kent TS-M2-ID273-Kent Breeze-Dx
20333 | CGE Ingersoll TS T5 & T6 - Replace EOL Trfrmr
20341 | HP Air Refurbishment Program
20342 | Placeholder - Unforeseen Projects (Gen Connection)
20346 | PCB Padmount Transformer Replacement
20347 | PCB Overhead Equipment Replacement
20353 | Wallace TS M4 ID549 Greenview Power DX
20354 | Wallace TS M4 ID549 Greenview Power TX
20357 | Kingston Gardiner #2 TS - Invista Protections
20361 | Martindale TS Spill Containment
20364 | Spill Containment Upgrades
20367 | Overhead PCB Inspection and Testing
20369 | On Call Environmental Assistance
20371 | PCB and Other Waste Management
20374 | GIC Maintenance/Re-Calibration
20379 | St. Isidore TS- M2- ID 1212- St. Isidore B
20383 | Whitedog DS Transformer Fan Monitoring
20390 | Tx Lines Switch Replacement Program
20391 | Midhurst Perimeter Security Upgrade
20392 | SECURITY SERVICES TX
20397 | Transformer Deluge Upgrade Program
20402 | Holland DS spare recloser and switchgear
20413 | Cancelled-2012 Burleigh DS Transformer Replacement
20425 | Goodfish DS F10 Duncan Ave Rebuild
20426 | Matachewan Voltage Conversion
20429 | Kent TS-M2-ID273-Kent Breeze-Tx
20430 | SECURITY SERVICES DX
20431 | Dx Station Security Upgrades
20435 | Dundas OC 2010 Paving
20446 | Cherrywood TS Drainage and Roads
20453 | S2B Steel Structure Replacement
20456 | 2012 Drayton DS Transformer Replacement
20458 | CGE Leslie TS T3 - Replace EOL Trfrmr
20462 | 2010 Durham Elgin Install MUS Facility
20470 | Connect the Comber East & West Wind FIT Projects
20474 | White River Tx FIT Projects
20479 | Connect the Summerhaven WEC Tx FIT Project
20482 | Connect the Wahpeestan Project Tx FIT Project
20484 | Connect the Trout Lake River Tx FIT Project
20485 | Connect the High Falls Hydropower Tx FIT Project
20486 | Namewaminikan Tx FIT Project Connection
20493 | Dufferin Wind Farm Project
20495 | X22: Connect White Pines Wind Farm Tx FIT Project
20497 | Connect the Wolfe Island Shoals Wind Farm Tx FIT
20499 | Connect the Liskeard 1,3,4 Tx FIT Project
20508 | Duart TS Feeder Construction
20513 | DS Power Quality Monitoring
20515 | Mitigation Measures for Windsor Malden - Dx
20516 | Napanee TS M2 ID1505 Lennox #3 (Tx)
20521 | Short Circuit Studies
20523 | Technical Studies
20524 | ERA Surveys
20525 | Mitigation Measures for Windsor Malden - Tx
20527 | Hub Site EOL and Capacity Expansion
20537 | Hanmer TS - Transmission Station Re-Inve
20539 | Conductor Replacement - Overhead
20543 | Delete: Enterprise Resource Planning Program
20544 | Delete: Enterprise Asset Management Program
20548 | INERGI INCREMENTAL APPLICATION SUPPORT
20550 | Parry Sound TS: Upgrade Txfmrs to 50/83 MVA
20560 | Enterprise GIS
20574 | NRC TS EOL Asset Replacement Project
20584 | London Nelson TS EOL Replacement Project
20585 | CSO Service Enhancements - Settlements
20586 | London Transmission Lines Facility
20587 | London Fleet Maintenance Facility
20588 | Wilhaven DS —B Switches
20592 | Larchwood TS EOL Asset Replacement Program
20593 | Timmins TS EOL 115kV Asset Replacement Project
20594 | Aylmer TS EOL Asset Replacement
20598 | Carlton TS: T1, T4 & Swyd Refurb. and Reconfig.
20600 | Burlington TS: ABCB Replacement Project
20603 | Kemptville West DS F2 Relief
20604 | Cumberland DS F4
20605 | Pickering 'A' SS - Station Re-Investment
20607 | Gage TS: T3,T4,T5,T6, PCT & Switchyard Reconfig.
20609 | Kirkland Lake TS T12 & T13 EOL Replment Program
20610 | Morrisburg TS 18M24
20611 | St Lawrence TS 49M27 Extension
20618 | Hawthorne TS: Uprate Short Circuit Capability
20619 | Bruce A 230kV- Replace Breakers & Upgrade Station
20621 | John Transformer Station Reinvestment
20625 | Leaside TS: 27.6kV Switchyard & Component Replace.
20626 | Markham Clegg Rd HVAC Replacement 2010
20629 | CTS Service Equipment
20630 | Tillsonburg TS: M2 feeder, STATCOM unit
20631 | Abandoned Equipment Removals Program
20633 | Stations Service Equipment
20634 | CMS Service Equipment
20636 | Port Arthur TS #1: PCT & Component Replacement
20638 | RichviewTS ABCB 230kV Tx Station Re-Invest Project
20640 | Fleet Service Equipment
20641 | Toronto -Spadina Subway Tunneling_Recoverable
20642 | AED Implementation
20646 | HS&E Service Equipment
20647 | Provincial Lines Service Equipment
20648 | Forestry Service Equipment
20651 | Circuit Breakers - HV SF6 ABB AHMA Drive Rebuild
20652 | Circuit Breakers -HV SF6 Areva FX32/42 Ram Rebuild
20658 | Essa TS BULK; ABCB & Component Replacement
20659 | Cherrywood ABCB Replacement Project
20666 | Runnymede TS, EOL T3 T4 Asset Replacement Project
20667 | Sheppard TS: T3, T4, PCT, LV Yard & Component Repl
20668 | ArcFM Business Process Support
20669 | Care Management
20670 | Middleport ABCB Replacement Project
20673 | Kent TS-M2-ID274-MacLeod Windmill-Tx
20675 | Designated Substances
20676 | E-Learning
20677 | Health and Wellness
20678 | ICM Upgrades and Licence Fee
20679 | Instructor Certification
20680 | ISO 14001 / OHSAS 18001 Registration
20681 | Journey to Zero
20682 | Learning Management System
20683 | Pandemic Planning
20684 | Public Safety Educational Materials
20686 | Specialist HSE Resources
20687 | Species at Risk
20695 | Brant TS M14 bypass to St George
20700 | Red Lake TS-M6-Two Feathers Forest Prdt ID-1777-TX
20703 | HV UG Cable - Diagnostics
20708 | Cornerstone Phase 4 - CIS - Capital
20709 | Cornerstone Phase 4 - CIS - OM&A
20712 | SONET and Microwave System Device Replacement
20713 | PLC Device Replacement
20717 | BPS Compliance - Budget Placeholder
20720 | University of Waterloo- MOU
20725 | PALC Replacements
20726 | PSR Replacement - Budget Placeholder
20730 | Fiber Cable Condition Monitoring System
20731 | Hinchey TS: Add switching to idle trfr windings
20732 | Ottawa-Relocation & Raising of H9A_Recoverable
20735 | ITMC Backup Centre re-fresh
20736 | Demand Capital Program
20737 | Safety by Design
20738 | Training Development
20742 | RTU Preventative Maintenance - Budget Placeholder
20743 | Commerce Way TS feeder construction
20748 | Cobden TS M2 ID1237-Dx SQPV01
20749 | Cobden TS M2 ID1237-Tx SQPV01
20751 | Meter Inventory Sustainment
20752 | Crystal Falls TS M2 Crystal Falls Conn. ID-10 TX
20754 | Butternut DS F3
20755 | Owen Sound Line Refurbishment - Stage 2
20756 | Owen Sound Line Refurbishment - Stage 3
20760 | Tx Lines - Annual ROW Inspections-NERC
20764 | Placeholder for CAR DG Projects (E&PD)
20768 | Placeholder for CAE DG Projects (E&PD)
20778 | Power Quality Monitoring (Lines)
20790 | CEATI-Tx Annual Program
20791 | University of Western Ontario- MOU
20792 | Studies-Capacity Enhancement
20794 | Clean Energy Initiatives
20804 | Malden TS M12 - Extension
20806 | Small Embedded Generation CIAs and Estimates
20807 | Telserv Replacement
20813 | Recoverable - Toronto - 570 Bay St.
20814 | Recoverable - Toronto - 580 Jarvis St.
20816 | PHEV Grid Impact/ Integration and PQ Studies
20818 | Crosby TS M2 ID11950-DX Rideau Lakes
20819 | Crosby TS M2 ID11950-TX Rideau Lakes
20820 | SVC Studies- CEATI
20821 | Green Energy Impact Studies on Dx
20822 | Studies - Advanced Grid
20823 | DVAR Study
20825 | Petawawa Craig DS F4
20828 | Napanee Area Study
20830 | Hawthorne TS: Replace 2 existing Transformers
20836 | T27P/T28P Protection Upgrade
20842 | Security Operations Efficiency
20843 | Beachburg DS F2 ID 11250 -DX Fepro Solar
20845 | Address New Vulnerabilities
20846 | Physical Security - Critical Stations (non CIP014)
20847 | PSIT Cyber Sustainment
20849 | User Access Management
20851 | Placeholder Security Awareness Training
20853 | Independent Audit
20855 | Field Site Surveys - BCA Identification
20857 | TDCN Management
20858 | 2010 Kenora DS F3 Recloser Upgrade
20859 | Cable Monitoring Infrastructure
20862 | Goulbourne OC Building Renovations 2010
20865 | HV UG Cable - Emergency Repairs
20873 | Burford DS Removal
20881 | Oshawa-Highway 407 Extension-Harmony Rd_Recoverabl
20883 | Hwy 407 East Ext.-Reloc at Leskard Rd-Recoverable
20895 | Infrastructure Technology OM&A
20896 | MFA Infrastructure Technology
20897 | ISD Business Impr and Enhancements
20905 | Budget 2013 NDC150
20910 | Fault Indicator Installation Program
20918 | Niagara TS Telecom Relocation
20920 | Re-establish Property Rights
20921 | Studies- Universities
20923 | FACTS / Micro Grid Studies
20924 | R&D Project-Grid Ops
20926 | Misc. Studies- FACTS Technology / Devices
20935 | Maclean's Mountain Wind Farm
20940 | Placeholder - Non-Recoverable - Line Removals
20944 | Trafalgar T14 750 MVA Autotransformer Re-Invest
20946 | Modify Lennox X21X22 LEO Protection
20947 | Fencing - Station Perimeter Program
20963 | Install Power Quality Monitors- Various Locations
20968 | Nebo TS:Increase Capacity of 230/27.6 kV T1T2 DESN
20970 | Telecom EMERG Corrective Maintenance
20971 | Telecom Mtce Support / Spares / Spares Mgmt
20977 | Underground Oil Pipeline Decommissioning Program
20982 | Waubaushene TS M1 ID12000-Dx Waubaushene 5
20983 | Waubaushene TS M1 ID12000-Tx Waubaushene 5
20992 | Dx TECHS-Stations Standards
20999 | Wholesale to Retail Standard - PL&F
21007 | Budget 2011 NCC150
21009 | Budget Bldg Renovations
21015 | TC219 - DG Connection Advancement for $107.7M
21016 | DC203 - DG Connection Advancement for $107.7M
21029 | Ponsonby DS F1 ID11520-Dx Martin Farm Biogas
21030 | Tx Standards Subscription
21033 | Small Embedded Generation - Connections
21037 | Belleville Operations Centre
21040 | ADS Project - Phase 1 - Dx Capital
21045 | Crosby TS M2 ID11970-DX Northland Solar Crosby
21046 | Crosby TS M2 ID11970-TX Northland Solar Crosby
21047 | Kirkland Lake TS M62- ID11730-Dx Charlton Dam
21048 | Kirkland Lake TS M62 ID11730-Tx Charlton Dam
21055 | CGE FGK253 OCB Remediation Program
21060 | Tx PCB Reduction Program - Retrofill
21063 | Dx PCB Oil Reduction Program - Retrofill
21064 | Herbicide Application
21065 | Station Site Surface Treatment
21074 | Smiths Falls TS M21 ID14330-Tx RE Smiths Falls 4
21078 | Bruce HWB Upgrade for Supply to DGR Site
21087 | Transport and Work Equipment (TWE)
21088 | SpencervilleDS_F2_ID12,110_Clearydale Farms_Dx
21089 | SpencervilleDS_F2_ID12,110_Clearydale Farms_Tx
21098 | Power Transformer ULTC Oil Filters/Breathers
21100 | ADS Project - Phase 1 - Tx Capital
21104 | P&C W-TC219- DG Connection Advancement for $107.7M
21111 | Hearst TS-M2-ID 12080- Dx- Mattawishkwia Solar Par
21112 | Hearst TS-M2-ID 12080- Tx- Mattawishkwia Solar Par
21113 | Belleville TS M6 ID12360 Dx 2225051Ontario Inc.
21114 | Wilson TS M12 ID12810 - Tx Ballyduff Wind Farm
21122 | Small Embedded Generation - Expansions
21123 | Small Embedded Generation - REI
21124 | Relay Alternative to TT
21126 | Sidney TS R8S Dx- ID10000 Ranney Falls G3
21127 | Kam Reg DS Voltage Conversion Part 2
21128 | Huntsville DS F3 Feeder Development
21131 | Interim Bolton Operation Centre - Improvements
21132 | Wilson TS M12 ID12810 - Dx Ballyduff Wind Farm
21133 | Belleville TS M6 ID12360-Tx 2225051 Ontario Inc
21134 | CAPE Support Maintenance & Training
21136 | Comber DS - Station removal
21137 | Jungbunzlauer CTS:Provide 115 kV Connection
21142 | Overhead Tx Lines - M3K Unregulated Asset
21143 | Gold Corp – Line Tap from 115 kV line E2R
21147 | DM203 Class C estimates 2013
21151 | Assumption for Unplanned Lines DG Work - (Lines)
21162 | CMS HVAC Replacement 2011
21166 | Replace Yard Lighting Program
21167 | Muskoka TS - Add 44kV Fdr Position &Chnge CT Ratio
21168 | 2011-2014 OPA Residential Programs
21178 | Muskoka TS M10 ID12250-Tx Burks Falls East Solar
21180 | DG Power Quality Monitoring (Stations)
21190 | Greener Choices Retrofits - Capital Work
21191 | Overhead Tx Lines - H2N Beaver Power Agreement
21196 | Stayner TS M6 ID12860-Dx Fairview Wind Farm
21197 | Stayner TS M6 ID12860-Tx Fairview Wind Farm
21198 | CM125 recoveries HOT Remotes
21199 | CM170 Cost Recovery HOT Remotes
21201 | DG Power Quality Monitoring (Lines)
21202 | Manitouwadge TS M2 ID931 Dx-Becker Cogen
21203 | Manitouwadge TS M2 ID931 Tx-Becker Cogen
21207 | Gardiner TS M14 ID12520 Dx 2225055 ON Hwy2 North
21208 | Gardiner TS_M14_ID12520_Tx 2225055 ON Hwy2 North
21210 | Ramore TS M5 ID12050-Dx Ramore Solar Park
21212 | Muskoka TS M1 ID12190-Dx North Bala Small Hydro
21213 | Muskoka TS M1 ID12190-Tx North Bala Small Hydro
21214 | 2012+ Large Sustainment Initiatives
21215 | 2011-2014 OPA Commercial Programs
21216 | 2011-2014 OPA Industrial Programs
21224 | Kirkland Lake TS ID 12730- Tx Marter Twp GS
21228 | Dobbin TS M4 ID11650-TX London Street GS-Expansion
21229 | Lauzon/Belle River reconfiguration
21230 | Perth OC Fence Replacement 2011
21231 | Kapuskasing OC Fence Replacement 2011
21233 | New Liskeard OC Fence Replacement 2011
21234 | Dundas OC HVAC Replacement 2011
21235 | Manitoulin OC Fence Replacement 2011
21237 | Orangeville TS M4 ID12830-Dx Whittington Wind Farm
21238 | Orangeville TS M4 ID12830-Tx Whittington Wind Farm
21240 | Dobbin TS M4 ID11650-DX London Street GS-Expansion
21241 | Orillia TS M2 ID11790-Dx Wasdell Falls Waterpower
21242 | Orillia TS M2 ID11790-Tx Wasdell Falls Waterpower
21244 | Pilot Project for Security Monitoring Tx
21249 | Port Hope TS M16 ID12750-Dx Clean Breeze Wind Park
21252 | Havelock TS M3 ID12950-Dx Kawartha Biogas
21253 | Havelock TS M3 ID12950-Tx Kawartha Biogas
21256 | DS Operating Spare Corrective Maintenance
21257 | Pickering 'A' T3L7 & T2L8 Brk Remov, Decommiss Air
21262 | Toronto Power TS Bldg Demolition
21266 | Overhead Tx Lines -Condition Assess LCSP TLDF-E&CS
21273 | Midhurst TS M9 ID12210-Dx RE Midhurst 6
21274 | Henvey Inlet Wind Farm
21277 | HONI-HOT Smart Meter Sustainment
21280 | Whitby TS_ID13530_C17 Real Canadian Superstore
21285 | Niagara Region Wind Farm Tx FIT Project
21286 | Q6S:Connect the Amherst Island Wind Tx FIT Project
21287 | Elliot Lake TS M3 ID12310 Pecors Power DX
21288 | Elliot Lake TS M3 - ID 12310 Pecors Power TX
21292 | Lakehead TS – C8 Synchronous Condenser Refurb
21294 | Claireville 750 MVA Autotransf Replacement - T14
21295 | Extreme Space Weather Prepardness
21300 | Copeland MTS Line Connection (formerly Bremner MTS
21305 | St.Lawrence TS M26 12,180-DX SunE Rutley
21307 | Dryden TS-M3 ID 12070-DX- Wainwright Solar Park
21313 | Trout Lake TS- M7- ID#12780- Dx- Trout Lake Wind
21314 | Trout Lake TS- M7- ID#12780- Tx- Trout Lake Wind
21333 | Town of Madsen Conversion from 4.16 to 25 kV
21360 | Cobalt DS F2 ID12500-Dx Latchford Dam
21361 | Cobalt DS F2 ID12500-Tx Latchford Dam
21371 | Higbury TS Building Demolition 2011
21372 | London Project Office Building Demolition 2011
21380 | Kirkland Lake TS M62 ID12890 - Dx Wendigo Waterpo
21381 | Kirkland Lake TS M62 ID12890 - Tx Wendigo Waterpo
21387 | Sudbury-Maley Dr Extension/Widening_Recoverable
21391 | Malvern TS: Install M23 & M24 Feeder Breakers
21394 | Owen Sound OC Pavement Installation 2011
21398 | Trout Lake TS- M7- ID#11850- Dx- Okikendawt Hydro
21399 | Trout Lake TS- M7- ID#11850- Tx- Okikendawt Hydro
21401 | Tx - Scrap & Surplus of System Reserve Equipment
21415 | Port Hope TS M18 ID 12910-DX Clarington Wind Park
21416 | Port Hope TS M18 ID 12910-TX Clarington Wind Park
21421 | Sidney TS R8S ID10000 Tx- Ranney Falls G3
21423 | Sidney TS R8S ID10000 Dx- Ranney Falls G3
21426 | 2011-2014 OPA Low Income Program
21427 | Stayner TS M2 ID12280-Dx Skyway Windfarm
21428 | Stayner TS M2 ID12280-Tx Skyway Windfarm
21434 | Crowland TS M1 ID12590-Tx Axio Welland Ridge Rd
21440 | DS Station & Equipment Retirement
21445 | Trout Lake TS M5 ID12970-Dx Merrick Landfill Ga
21446 | Trout Lake TS M5 ID12970-Tx Merrick Landfill Ga
21447 | Northland Power FIT Connection-Long Lake Solar
21448 | Northland Power FIT Connection -Abitibi/Martin/Emp
21460 | Thunder Bay - Hwy 11/17-Red Rock-Nipigon_Recovrabl
21462 | Cobalt DS F2 ID12630-Dx Latchford Dam 2
21463 | Cobalt DS F2 ID12630-Tx Latchford Dam 2
21465 | Bell Creek Complex - 115kV P7G Mine Connection
21471 | B5G/B6G - Provide Transfer Trip Protection
21473 | Physical Security - ADT Monitoring
21475 | Smiths Falls TS M23 ID14460-Dx Burritts Rapids
21490 | Social Benchmarking
21491 | 2011-2014 OEB Commercial Programs
21492 | 2011-2014 OEB Industrial Programs
21495 | PMR Engineering Support
21498 | Seaton MTS - 230 kV Tx Supply to New 28 kV DESN
21499 | MetroLinx Traction Power Station Connections
21514 | ADS Phase 1 Release 2 - Dx OM&A
21516 | Abitibi Bowater CTS - G6 Generator Connection
21517 | Dryden TS - Install Redundant NSD570 for Domtar
21518 | Reactors at Marathon TS
21519 | Northcote DS-F3-ID645-Dx-PV mitigation
21520 | Malden TS-M8-ID689-Dx-PV mitigation
21521 | Kent TS-M23-ID49-Dx-PV mitigation
21523 | Duart TS-M5-ID487-Dx-Distance Limitation
21524 | Kent TS-M15-ID274-Dx-PV mitigation
21525 | Kingsville TS-M7-ID1097-Dx-PV mitigation
21526 | Kingsville TS-M1 M7-DG 1096 and 1099 DX PV mitigat
21529 | 95 Mural Street (Tenant Improvements) 2011
21532 | NMS Capital Sustainment
21533 | Voice Communications System Upgrades (Dx)
21536 | Kapuskasing TS M3 - ID11740 - Old Woman Falls DX
21537 | Kapuskasing TS M3 - ID 11740 - Old Woman Falls TX
21538 | Kapuskasing TS M3 -ID 11750- White Otter Falls DX
21539 | Kapuskasing TS M3 -ID 11750 - White Otter Falls TX
21542 | ADS Phase 1 Release 2 - Common
21555 | OGCC Sustainment - Dx OM&A
21568 | Kent TS-M15-ID274-Tx-PV mitigation
21578 | Muskoka TS M7 ID14110-Dx Bracebridge Falls
21579 | Muskoka TS M7 ID14110 -Tx Bracebridge Falls
21585 | Trout Lake OC Overhead Door Replacement
21587 | Timmins TS-M11-ID251-Dx PV mitigation-EXP ONLY
21589 | Security Event Management Services
21599 | Leaside TS HVAC Replacement 2011/12
21605 | Muskoka TS M7 ID 14120-Dx Wilson’s Falls Gen
21606 | Muskoka TS M7 ID14120 -Tx Wilson’s Falls Gen
21609 | Nebo TS M8 ID14490-Tx Redeemer University College
21613 | Nipigon voltage conversion
21618 | Tx Idle Line Rental Payments
21619 | Toronto-TTC-Eglinton Crosstown LRT_Recoverable
21621 | Non Production Computer Room Facility (Tx)
21623 | Lennox 4kV Station Service COVER work
21627 | Control Room Wallboard Refresh (Dx)
21628 | Control Room Wallboard Refresh (Tx)
21644 | Connect Bluewater Wind Energy Centre
21645 | DG Connection Advancement for $29.76M - TC219
21646 | DG Connection Advancement
21647 | Manitoulin TS T3 & T4 Replace EOL Transformers
21649 | Petawawa DSs Monitoring and Feeders
21655 | B562L (Evergreen SS) - Connect JAB windfarms
21661 | L29C - Connect East Lake St. Clair Wind
21662 | W45LC - Connect Erieau Wind
21664 | B23D - Connect Grand Bend Wind Farm
21665 | B4V - Connect Grand Valley Wind Farms (Phase 3)
21667 | WT1A - Connect Silvercreek Solar Park
21668 | Telecom Battery Replacement Program
21669 | Telecom Charger Replacement Program
21670 | Goderich TS - Station Reconfiguration
21674 | Brown Hill TS- M12- ID15940- Tx- GoldLight LP
21675 | Petawawa Craig DS T2 and F5
21678 | Norfolk TS M1 ID15080-Tx Bright Power
21680 | Waterloo - LRT _ Recoverable
21683 | Morrisburg TS M25 ID12800 Dx-Southbranch Wind Farm
21687 | Corporate support Optimization(SC, HR, Eh&S)
21688 | OMA of Select CC260 Projects
21689 | CTI Replacment
21695 | Wilson TS M14 ID16030-Dx Illumination
21696 | Wilson TS M14 ID16030-Tx Illumination
21698 | St. Lawrence TS M25 ID16470-Tx Glengarry St. Lawre
21699 | Beaverton TS-M24-ID15900-Dx-Sparkle Light
21705 | Move to Mobile - Lines Phase1
21706 | AA 2015 Remediation
21708 | Chalk River MTS Connection Development
21710 | E-Customer replacement
21712 | Beaverton TS M24 ID15910 Dx-DiscoveryLight LP
21715 | DS Single Phase Transformer Changeouts
21716 | ROW Environment- Vegetation Re-Engineering
21717 | Ontario Solar Connection Study-CanSIA
21722 | Beaverton TS M23 15880 Dx-GoodLight LP
21723 | Brown Hill TS M11 ID15920 -Dx- Earthlight LP
21724 | Cobden DS-SSI
21725 | Chesterville TS M2 ID15990 Dx - MightySolar
21726 | Chesterville TS M2 ID15990 Tx - MightySolar
21731 | Belleville TS M2 Dx-ID16020 Lunar Light LP
21732 | Belleville TS M2 ID16020-Tx - Lunar Light LP
21733 | OPS AND CARRIER MGMT - Smart Meter
21737 | Training Enhancements (External)
21738 | Lab Repairs and Upgrades
21740 | Brown Hill TS M4 ID 15950 - Tx BeamLight LP
21743 | DG Coordination
21744 | Compliance Audit Readiness
21745 | Inergi Base Services - Smart Metering
21746 | IT Application Upgrade
21747 | IT Application Upgrade - Smart Metering
21750 | Placeholder - Projects to be identified
21752 | Picton TS M6 ID15960 Dx FotoLight LP
21753 | Brown Hill TS M4 15950- Dx- BeamLight LP
21754 | Waubaushene TS M2 ID15860 DX - Aria LP
21755 | Waubaushene TS M2 ID15870 DX - RayLight
21756 | Brown Hill TS M12ID15940 -Dx- GoldLight LP
21757 | Micro Embedded Generation Connections
21761 | Guelph Forestry OC Windows Replacement 2011/12
21762 | B563L (Ashfield SS) - Connect K2 Wind Generator
21773 | Security Upgrade Cobden OC 2011
21777 | Whitby TS M23 ID 15750- Tx Index Energy Mills Road
21779 | Norfolk TS M1 ID15090 - Tx 510 Main St
21782 | Energy Research Initiatives-ERI
21783 | Energy Research Initiatives-ERI
21784 | Green Energy Impact Studies- Tx
21785 | Advanced Grid Studies- Tx
21787 | X3H - Connect Kingston Solar Project
21796 | Coboconk DS F2 ID16140 Dx Norland Hydropower
21797 | Coboconk DS F2 ID16140 Tx Norland Hydropower
21798 | Revenue Meter for DGfacility under 250 kW for 2012
21799 | Provincial Mobile Radio System Expansion
21806 | Mountjoy DS F2 - Remove Underbuild
21807 | Duplex T1/T2A1-A2 M/C Component Replace
21809 | John TS A5-A6 (Windsor) Metalclad Swgr
21814 | Studies- Universities
21817 | Cooksville TS Transformer Replacement Project
21825 | Bridgman TS: T11,T12,T13, M/C & Component Replacem
21830 | B22D- Connect Armow Wind Farm
21836 | Steel Structure Refurbishment/Replacement Program
21848 | Woodstock TS T1 & T2 Transformer Replacement Prog
21850 | Lakehead TS T7&T8 Transformer Replacement Prog.
21851 | Dymond TS T3&T4 Transformer Replacement Prog.
21854 | Almonte TS T4 Transformer Replacement Project
21861 | Hawthorne TS ISCR
21863 | Keith TS T1 Transformer Replacement Program
21864 | Martindale TS T 22 Transformer Replacement program
21865 | Hanmer TS: Northern Station Replacement Project
21868 | Centralia TS T1/T2/T3; T1,T2,T3, PCT, MVGIS
21871 | Stanley TS T2 Replacement Project
21872 | Cobden TS T1&T2 Replacement Project
21873 | Chesterville TS T1& T2 Replacement Project
21880 | Rogers TCA Equipment Change Out - Recoverable
21890 | Micro Embedded Net Metered Generation Connections
21961 | Waubaushene TS M2 ID15870 Tx-RayLight
21964 | Goderich TS - New Feeder Position
21971 | Picton TS M6 ID15960 Tx-FotoLight LP
21973 | Wilson TS M15 ID10250 Tx - Clarington #1
21976 | MicroFIT Mitigation (2012 - onwards) - Program
21979 | Guelph OC Fence Replacement 2012
21986 | H24C - Line Refurbishment
21987 | H27H - Line Refurbishment
22016 | R&D Program, E&PD
22020 | Orangeville TS New 27.6 kV Feeder
22025 | Snow Road DS-SSI
22028 | Grounding Transformer Installations
22030 | Picton TS M7 ID16620 Dx Sunny Shores Solar Farm
22031 | Picton TS M7 ID16620 Tx Sunny Shores Solar Farm
22032 | Crawford TS -Recoverable Review and Monitoring
22035 | Tx Lines Damage Claims and Costs
22040 | Waste Bin Replacement
22041 | Tillsonburg IPCC Cap Bank Replacement
22042 | Construction Service Equipment
22045 | Recloser Retrofit Project
22046 | Fault-Prone Indoor GE Meter Replacement
22050 | Garage Bay Improvements Richview TS 2012
22051 | Failure Investigations
22057 | Brown Hill TS New 44 kV Feeder
22060 | Nebo TS M6 Tie Line on Wilson Rd
22061 | Festival Hydro: Provide Line Connection to New MTS
22068 | Bolton Operation Centre
22069 | Manotick DS F5 ID 19080 Schouten Farms DX
22071 | OGCC HVAC Replacement 2012
22074 | Mountjoy DS Voltage Conversion
22076 | Iroquois Falls: Conductor Upgrade
22077 | Toronto-GTS Expansion Project-Recoverable
22078 | Load Displacement Capacity and Assessment
22082 | Clarabelle TS - M8 Feeder Relief
22083 | Chesterville TS New Feeder 73M1
22084 | Cataraqui Woods Drive Reinforcement
22086 | Lindsay OC Office Renovations 2012
22087 | 2012 Budget NCC150
22089 | NTC128 Budget 2012
22091 | Orillia TS M1 ID16880-TX H06-3225 Monarch
22093 | Public Safety Hazard Hamlet Presentations
22094 | Large Diesel Generator Upgrade Project
22095 | Point Au Baril DS F2 Feeder Extension
22099 | IT 3rd Party Contracts - Smart Metering
22104 | Birmingham TS Roof Repair 2012
22105 | Bayridge Drive Reinforcement
22111 | Manby 230kV Reconfiguration
22118 | On Call Environmental Assistance
22119 | PCB and Other Waste Management
22120 | Baywood OC Roof Replacement 2012
22123 | Micro Inverter RTDS study and dynamic model dvlp
22125 | Stations Environmental Compliance
22126 | Transmission PCB and Regulated Waste Manage
22127 | Awenda DS - Upgrade F2 Feeder Recloser to VIPER
22129 | Kapuskasing TS M4 ID17860-DX Hydro Kapuskasing Hyd
22131 | Ft. Frances TS: Remove T3 and Reconnect SC1&2
22135 | Kapuskasing TS M4 ID17860-TX Hydro Kapuskasing Hyd
22141 | D10S/D9HS - Line Refurbishment
22150 | IPS Replacement Project
22152 | Crystal Falls TS M1 ID18380 Tx-WNPG Turbines Upgrd
22154 | L5H Idle Line Removal Non-Recoverable
22155 | Cherrywood TS - Install 2x250MVAr Cap Banks
22156 | Almonte TS - Install new 230 kV Breaker
22157 | DS Operating Spare Mtce & Inspection
22160 | Infra / Tech Refresh - Smart Meter
22161 | Seaforth TS-ID17740-Dx-St Columban 2 wind project
22162 | Seaforth TS-ID17740-Tx-St Columban 2 Wind Project
22163 | Microwave Tower Alarm Monitoring System
22165 | V73R/V74R self damping conductor replacement
22166 | Owen Sound TS M28 Extension to Brookholm DS
22168 | Wingham TS-ID17730-Tx-St Columban Wind Proje
22170 | Hanover TS-H1E-ID17750-Dx-East Durham Wind Energy
22180 | Malden TS -Two 28kV feeders
22186 | Hinchey TS T3&T4 Transformer Replacement Program
22188 | Pembroke TS T1&T2 Transformer Replacement Program
22198 | NWGTA Electricity Corridor - Concep. Planning & EA
22210 | Park Road DS Transformer Fan Monitoring
22215 | Manitouwadge T1- Replace EOL Transformers
22217 | Mooselake TS, T2- Replace EOL Transformers
22218 | Thornton TS T3 T4- Replace EOL Transformers
22225 | 3rdParty HONI station/Lines Monitoring-Recoverable
22230 | Independent Compliance Audit
22231 | Kimberly DS F3 Feeder Extension
22232 | City of Owen Sound Tie-Line Reinforcement
22233 | Town of Meaford Tie-Line Reinforcement
22235 | Removals - Revenue Meter Installations
22240 | Mattawa HVDS
22242 | Malden TS M12 ID19180-Dx River Canard Energy N
22247 | Ear Falls TS, EOL T5, Asset Replacement Project
22251 | Upstream LDC Payments - DX
22263 | Wallaceburg TS-Feeder M1- ID 17530-SA3
22265 | Extreme Space Weather Prepardness Phase II
22275 | Thunder Bay - Pipeline Easement-Recoverable
22279 | Holland TS - Add Breakers and Re-terminate Lines
22285 | Ottawa Telecom Cable Removals
22287 | Upper Beaver Mine(Osisko)-115kV Mine Connection
22290 | Highbury TS M11 ID19570-DX RE Sunningdale 1
22293 | KGHM Ltd - Victoria Mine Connection
22295 | PMR Base Station Alarm System
22296 | Sunnidale Properties deck and pool removal
22297 | Tx Stations Security Upgrades
22298 | Wiltshire TS - Tx Station Re-investment Project
22301 | Campbellford Area Study Implementation
22302 | Carleton Place Supply Improvements
22304 | Bobcaygeon Area Study Implementation
22310 | Rockland DS T2
22312 | Morrisburg TS 18M24 Reconductor
22314 | Strathroy TS-M1-ID 17760-Dx-Napier Wind Farm
22316 | Orleans TS Feeder Egress & Revenue Meter
22317 | Shannonville DS SSI
22318 | Hanover TS - T3 Transformer Replacement Program
22319 | OverBrook TS, EOL Transformer Asset Replacement
22320 | Wilson TS M11 ID19990 Tx 405 Lake Road
22321 | Tilbury West HVDS F1 ID21000-Dx 37 Mill St West
22322 | Tilbury West HVDS F1 ID21090-Dx 351 Queen Street
22326 | CMS - Security Upgrade 2012
22328 | Chenaux TS EOL Transformer Replacement project
22329 | Espanola TS EOL Stat Reinvstmt proj
22331 | St. Thomas 115/27.6 (T3 & T4):Decommissioning Cost
22335 | Glendale TS: T1,T3,T4 & Swyd Refurb. and Reconfig.
22336 | Stanley TS Station Upgrade
22337 | Business Unit for Enterprise Content Management
22345 | Dobbin TS: Component Replacement
22351 | Mississagi TS - Add Goulais Wind to GR Scheme
22354 | Orangeville TS M3 - Mayfield West
22355 | Dryden TS - Install Shunt Reactors
22357 | Ballantrae DS load balancing
22360 | Lindsay TS D4M7 Upgrade
22361 | Neustadt DS F2 ID18530-Dx Normanby Solar 5
22362 | Nebo TS feeder - demand enhancement
22364 | Neustadt DS F2 ID18540-Dx Normanby Solar 2
22367 | Nebo TS feeder extension to Binbrook - phase 1
22368 | Nebo TS M12 feeder extension to Hamilton Airport
22370 | TEM Logical Data Validation
22380 | Nobleton DS T1-new 27.6 kV transformer and feeder
22381 | Tenth Line DS T3
22384 | Bradford North DS
22386 | Enfield TS feeder development
22391 | Telecom Perf Upgrade - Bruce A-B
22397 | Orillia TS M1 ID20150-TX 555 Memorial Ave
22400 | Strathroy Septic Rehab 2012
22401 | Clinton Concrete Column Rahab 2012
22402 | Vankleek Hill OC Security Upgrade 2012
22403 | Thunder Bay OC (205) Security Upgrade 2012
22405 | Kingston OC Security Upgrade 2012
22406 | Essex OC Security Upgrade 2012
22407 | Brockville OC Security Upgrade 2012
22408 | Thunder Bay OC (255) Security Upgrade 2012
22416 | Burlington Beach Line Relocation - Recoverable
22418 | Nanticoke TS - Station Service Upgrade / Demerger
22420 | Strathroy TS – EOL Station Refurbishment
22421 | P1P Superior Fine Papers Removals-Non-Recoverable
22422 | Ottawa - 800 Hunt Club Road_Recoverable
22426 | Storage Acquisition Project
22436 | Claireville 750 MVA Autotranf Replacement - T15
22446 | Dx - Engineering Standards
22448 | Tx - Engineering Standards
22450 | Tillsonburg TS-M2-HVTT and line back up protection
22451 | Brant TS M12 ID20070-TX Ferrero Canada Quattro-Gen
22453 | To be Closed- CMS Station Service & Yard Supply
22457 | Strathroy TS-M3-ID 21170-Dx -RE Adelaide 1 ULC
22458 | Strathroy TS-M3-ID 21170-Tx-RE Adelaide 1 ULC
22461 | Douglas Point TS-M6-ID20530-Quixote One WE-Dx
22462 | Douglas Point TS-M6-ID20530-Quixote One WE -Tx
22467 | Cornerstone Phase 3 - EDT CAP
22480 | RichviewTS T1/T2; T1,T2,PCT &Component Replacement
22481 | CrowlandTS, T5&T6 - Replace EOL Transformers
22487 | Markham OC Security Improvments 2012
22488 | Oro SC Drainage 2013
22492 | Orangeville OC Elevator Lift
22493 | Lindsay TS M7 ID20780 Dx Balsam Lake Green Energy
22494 | Lindsay TS M7 ID20780 Tx Balsam Lake Green Energy
22496 | Mississaugi TS - Add Bow Lake Wind to GR Scheme
22502 | Lambton TS - New Feeder to Terra Nitrogen
22505 | Smith Falls Roadway Site Drainage
22507 | Vale - Victor Deep Mine Connection
22511 | Hearing Conservation Program
22517 | Whitby - O1S - Idle Line Removal - Recoverable
22518 | Ottawa - McRae Structure Replacement - Recoverable
22530 | Cameron DS Improvements
22531 | Colborne DS Relief
22543 | Duart TS - M5 - Tx - DG 487 Distance Limitation
22544 | Colpoys Bay DS F2 Feeder Upgrade
22545 | Kingsville TS-M7-ID20300-200 Clark St -Tx
22547 | Kingsville TS M5 ID21520 - TX - Wigle Ave Solar
22548 | Creemore DS - New Feeder to Collus
22550 | Kingsville TS M5 ID21110 Tx - Kingvsille Plastic 2
22552 | MicroGrids Impact/Integration
22553 | Nebo TS feeder extension to Binbrook - phase 2
22560 | R&D Program- Kinectrics
22566 | Mattawa Voltage Conversion
22567 | Tillsonburg TS-M2-Dx work_DG 281 and 282
22575 | Middleport TS septic system rehab 2013
22576 | Orangeville OC Garage apron & drain rehab 2013
22577 | Air to Gas Bushing Replacement Program
22579 | Operating Power Systems IT Support
22582 | Station Battery Monitoring Systems
22583 | Internal Compliance Plan
22587 | Thunder Bay OC Fence Replacement 2013
22588 | Lambton OC Fence Replacement 2013
22589 | Integrated Voice Comm & Telephony Sys Replacement
22592 | CGE type SBM CSS Replacement Program
22593 | Phone Enhancements Project (Dx)
22594 | CMS - Railway siding acquisition 2012
22596 | Douglas Point TS-M1-ID20940-Dx-Meyer Wind Farm
22597 | Douglas Point TS-M1-ID20940-Tx-Meyer Wind Farm
22598 | CEATI-Tx Annual Program
22600 | Lennox TS 500kV Bus -Connect Napanee GS
22609 | Minden Trailer - Bldg 2012
22610 | Voice Communications System Support & Mtce
22615 | Red Rock HVDS F3 ID20990 Dx-Black Bay Solar
22616 | Red Rock HVDS F3 ID20990 Tx-Black Bay Solar
22621 | Furniture Systems - Facilities (Field)
22622 | Head Office Improvements Furniture
22623 | Cornerstone Phase 3 - AIP PH2
22624 | Cornerstone Phase 3 - HR/Pay Enhancements
22626 | S&E Contractor Pre-Qualification Process
22627 | P&C Distribution Support
22629 | Operating Facilities Refresh
22630 | MFA for Development Project
22634 | Engineering Cyber Lab Sustainment
22635 | E4D – Upgrade to operate at Higher Temperature
22636 | Kingston - ABNA Tower Relocation - Recoverable
22637 | ORMS Sustainment Upgrade
22638 | Kingsville TS M1 ID21640 Tx - Brian Curtis
22645 | ADS Project Phase 1 Release 2- MFA
22647 | Cornerstone Phase 3 - AIP PH2 OM&A
22648 | CSO Regulatory Compliance/CIS Projects
22649 | CSO Service Enhancements - Projects
22650 | Cornerstone Phase 3 - Workflow of the Future
22651 | Cornerstone Phase 3 - Meter Management
22653 | DX P&C Corrective
22656 | Oshawa Wilson TS: Install Neutral Reactors
22657 | MFA Client Tech & Periph Refresh
22658 | MFA Telecom Tech Refresh
22659 | MFA Infrastructure Technology
22663 | Barrie TS M1, M6 ID 16490 - TX -IBM Data Center
22665 | North of Dryden DX Contribution to TX upgrades
22667 | Regulated Waste Storage Units - Transmission
22670 | Cambridge-MTO-3 Improved Hwy 401 Crossings-Recover
22678 | Massey DS F3 Feeder Upgrades
22680 | Manvers - Lafarge Aggregate Pit - Recoverable
22681 | Brockville TS: Install Neutral Reactor
22685 | Marathon OC Concrete Pad
22691 | Penetang OC Paving 2013
22692 | Kent TS-M18-ID 76-PV mitigation
22694 | Pond Mills Construction Site Improvemets
22695 | Thunder Bay 205 Burwood Paving 2013
22696 | Kenora OC Paving 2013
22697 | Safety System Evaluation
22700 | Stratford TS M6 expansion
22701 | Jones Creek DS-SSI
22702 | St. Isidore TS New Feeder 62M5
22703 | Lily Lake DS-Chemung DS Tie Line
22704 | Rice Lake DS F2
22705 | Kent OC Paving 2013
22706 | Mobile IT
22707 | NOMS Upgrade
22708 | Placeholder for DC202 Load Growth Projects - EPD
22709 | Placeholder for TC108 E&PD Projects
22710 | NMS Enhancements
22711 | Incremental ADS Provincial Rollout Placeholder - P
22712 | Incremental ADS Provincial Rollout Placeholder - P
22713 | Incremental ADS Provincial Rollout Placeholder - P
22714 | Incremental ADS Provincial Rollout Placeholder - P
22715 | Incremental ADS Provincial Rollout Placeholder - P
22716 | Placeholder for TC202 Projects to be Identified
22717 | Placeholder for TC211 Projects
22720 | Unforseen Eng and Environ Tech Support
22721 | Unforseen Power Equip Tech Support
22722 | Unforseen Infrastructure Main Tech Support
22724 | Placeholder for TC203 Projects
22725 | Beckwith DS T2 and F3
22730 | MFA 2013 - Cornerstone Phase 4 - CIS
22732 | Belle River DS Voltage Conversion
22733 | Bob-Lo DS Voltage Conversion
22734 | Northwest Special Protection Scheme
22735 | Listowel OC Paving 2013
22737 | Operating Power System IT Support
22738 | Bell TCA Equipment Change Out - Recoverable
22739 | Head Office Improvements Furniture-Lines
22743 | TWE - Constrution Services
22744 | TWE - Forestry operation
22745 | Head Office Improvements Furniture-Construction
22750 | TWE - Provincial lines
22752 | GPS Telemetrics Expansion
22755 | OPGW upgrade D1A/D3A
22760 | AMI Wireless Telecom Upgrade
22766 | Brant TS: Install 115kV Switching Facilities
22772 | Engineering Design Transformation
22773 | Customer Care Program – Analytics & Alerts
22775 | Tillsonburg TS-M2-ID 21130-Dx-Grid Scale Flywheel
22776 | Tillsonburg TS-M2-ID 21130-Tx-Grid Scale Flywheel
22780 | L28C - Connect Green Electron Power Plant
22790 | DM203 Customer Care Reporting Program
22791 | Brant TS M14 21700 GEDS - 29: St. George - German
22795 | Palmerston TS 28M2 Supply to Mount Forest
22800 | Morrisburg TS New Feeder 18M24
22801 | Dobbin DS F1 Reinforcement
22805 | Mississauga-QEW Credit Valley Future Circuit Reloc
22810 | Scarboro TS ISCR
22815 | Information Rights Management
22817 | Final Destination - Enterprise GIS Updates
22820 | Placeholder - CornerStone Phase 3 OMA - HR Pay
22821 | Placeholder - CornerStone Phase 3 OMA - Workflow
22823 | Kent TS M24 expansion
22826 | Pickering CMS HVAC Upgrade 2013
22830 | Tilbury DS New Feeder
22855 | Extend 44 kV Supply to Coniston
22860 | Operating Hardware Refresh
22861 | Placeholder for DC202 Reliability Projects - Lines
22862 | Placeholder for DC202 Capital Contrib Projects
22864 | Placeholder for DC308 - ISD
22867 | PSIT Cyber System End-of-Life Lifecycle
22869 | Q11S/Q12S - Tx Lines Refurbishment Program
22871 | Placeholder for DM250 - CDM Projects
22873 | Budget Placeholder TC203 - E&CS Projects
22874 | Budget Placeholder TC308 - E&CS Projects
22875 | Placeholder for TC108 E&PD Programs
22881 | PCB Removals Lighting Replacements 2013-2014
22882 | Poonamalie DS Recloser Upgrade
22885 | Tilbury TS / Tilbury West HVDS - DESN Rebuild
22893 | Kingsville TS M6 ID 21860 DX Leamington Pollution
22895 | Wiarton RS Reconfiguration
22896 | Huntsville OC paving 2013
22897 | Hanmer TS - T7/T8 Station Refurb
22899 | Smiths Falls TS M23 Tx-ID14460 Station Anti-island
22900 | Install Power Quality Monitors-Various Locations
22901 | Nepean TS Roof Replacement 2013
22902 | Hanmer OC Concrete Pad Repair 2013
22903 | Minden OC Drainage Rehabiliation 2013
22904 | Lindsay OC Drainage Rehabilitiation 2013
22907 | Finch TS Roof Replacement 2013
22908 | Cherrywood TS Septic System 2013
22909 | London Project Office Demolition
22910 | Allanburg TS M7 - conversion on Haist St
22912 | Fort Francis TS Roof Replacement 2013
22915 | Kingsville TS M6 ID 21860 TX Leamington Pollution
22917 | Hub Site IPS Replacement Project
22918 | Dunnville TS: Add 1x27.6kV Feeder Breaker Position
22919 | Wallbridge DS SSI
22923 | Norfolk TS M5 ID18230-TX UDI Port Ryerse Wind Farm
22924 | L&FS Tx Wood Pole Repl Program - Construction
22925 | Orillia Forestry Work Centre - Improvements
22926 | Placeholder - Technical Support for Recov Proj
22930 | Longwood TS HVAC Replacement
22935 | Goodfish DS F8 Voltage Conversion
22943 | Carleton Place DS Reconstruction
22944 | Manotick DS Feeder Relief
22946 | Nipissing OC 2013 Improvements
22948 | Port Hope TS: Component Replacement
22949 | Wanstead TS EOL Station Refurb
22950 | Cornerstone Ph3 - OM&A for HR/Pay Transf Project
22951 | Cornerstone Ph3 - MFA for HR/Pay Transf Project
22952 | Sidney TS - ISCR
22953 | Allanburg TS - ISCR
22955 | Buchanan TS: 115 kV Switchyard & Component Repl.
22957 | Keith TS: T11,T12 & Component Replacement
22958 | Beach TS: T6, T7, T8 & Component Replacement
22959 | Warden TS Component Replacement
22961 | Halton TS, PCT and component replacement
22963 | Birmingham TS: MV Switchgear Replacement
22965 | Mohawk TS; T1/T2 Component Replacement
22966 | PlaceholderCornerstone Ph3 - OM&A Waste & PCB Mgmt
22967 | Cornerstone Phase 3 - Waste & PCB
22970 | Dryden TS - ISCR
22971 | Manby TS - ISCR
22973 | Stewartville TS - ISCR
22974 | Markham CC Site Improvements 2013
22976 | Barwick TS- M2- ID12030- Dx- Morley Solar Park
22977 | Barwick TS- M2- ID12030- Tx- Morley Solar Park
22981 | Arnprior Forestry Work Centre - Improvements
22983 | Wood Pole Replacement Program - Lines
22985 | Limoges DS Relief
22986 | Greely DS F1
22987 | Manotick DS F3
22988 | Barwick TS- M2- ID12040-Dx- Dave Rampel Solar Park
22989 | Barwick TS-M2- ID12040- Tx- Dave Rampel Solar Park
22993 | Norfolk TS: M3 feeder, STATCOM unit
22996 | Gate Security (Perth, Brockville, Vankleek Hill)
22998 | Lythmore DS F3 sw4291 load relief
23000 | Barwick TS- M2- ID12060-Dx- Vanzwolf Solar Park
23001 | Barwick TS-M2- ID12060- Tx- Vanzwolf Solar Park
23002 | Smart Grid Fund Initiatives
23004 | Strathroy TS M4 ID22370 TX Entegrus Powerlines
23005 | Toyota Woodstock TS - Upgrade to DESN
23011 | Bruce SC Bldg B37 well improvements
23020 | Beach TS ISCR
23025 | IESO Meter Data Validation - Stations
23030 | Meadowvale TS M3 ID22460-TX CCS-Mississauga Gen
23031 | Markham Skylights / Snow Guard Replacement 2013
23054 | Government Road Line Extension Kirkland Lake
23061 | Kirkland Lake TS - Archer Drive Voltage Conversion
23062 | Dunchurch DS F2 - Extend to Magnetewan
23063 | West Bay DS #2 & Line Work
23064 | Pelham DS F2 Feeder Conversion
23065 | LCC/LMC OS Upgrade
23066 | RTU D20M++ End of Life
23067 | Margach DS F1 offload stepdown transformer SD3936
23071 | Elk Lake Voltage Conversion
23072 | Hanmer TS Feeder Development
23073 | Hanmer TS DESN Capital Contribution
23074 | Mar DS
23075 | Snow Valley DS & Line Work
23077 | Mar DS Red Bay Line Upgrade
23078 | Point Au Baril DS F2 Submarine Cable Upgrade
23080 | Kirkland Lake Voltage Conversion - Stage 1
23085 | Lorne Park TS M4 ID22470-TX C2-5 Biogas Handling
23090 | Mattawa DS Connection
23091 | Riverdale TS HVAC Improvements 2013
23092 | Satellite Phones for security
23093 | Hazard Hamlet for H&S
23094 | Claireville TS HVAC Upgrade 2013
23095 | Grid Control Network Sustainment
23101 | Smithfield DS F1 Development
23110 | Recloser Retrofit Project - Tx
23111 | Martindale TS T21 & T23 Replacement
23115 | Itron Sentinel 16S meter replacements
23130 | Fleet Telematics -TWE
23131 | Brant M14 St George Loop Feed
23136 | Customer Experience Initiatives - Dx
23137 | HV UG Cable - Replace H7L/H11L
23138 | Glengarry DS SSI
23139 | Kingsville TS M4 ID22910-Tx Mucci Farms
23140 | Customer Experience Initiatives - Tx
23141 | South Huron-Raise L7S for Goshen Wind-Recoverable
23142 | Kingsville TS M4 ID22920-Tx Agriville Farms
23143 | Kingsville TS M4 ID22920-Dx Agriville Farms
23144 | NERC CIP Version 5 - OPEX
23146 | OMA for Teldig Project
23147 | NERC CIP Version 5 - CAPEX
23148 | St. Andrews TS: Modify M9/M10 P&C (Imperial Oil)
23150 | Timmins Helipad Concrete Apron 2014
23159 | Mattawa DS 115 kV Line Connection - Payment to Tx
23160 | Kingsville TS M4 ID22910-Dx Mucci Farms
23166 | Commerce Way New Feeder Extension
23167 | Windsor - DRIC Dx Relocation_Recoverable
23168 | CUSTOMER EXPERIENCE - SURVEYS
23170 | Frontenac TS EOL Stat Reinvstmt proj
23177 | Sarnia Sott TS Roor Replacement 2014
23178 | Wallaceburg TS Roof Replacement 2014
23179 | Buchanan TS Roof Replacement 2014
23182 | Grand Bend East DS Monitoring & New Fdr Position
23183 | CMS Room 080 Refurbishment Project- Capital Funds
23184 | OGCC Storage Area Network Upgrade
23185 | Edgeware TS Roof Replacement 2014
23186 | TransCanada-Pump Stn (Cancel)
23195 | Aylmer TS M1 ID21470 TX IGPC Cogeneration Project
23200 | Edgeware TS- M7- ID24300-Dx- Formet 800 kW CHP Sys
23201 | EdgewareTS-M7- ID24300- Tx- Formet 800 kW CHP Sys
23203 | Timmins TS M8 - 1 km Conductor Upgrade
23204 | Clarke TS M2 Extension_Ilderton
23205 | Integration Playbook
23206 | Norfolk Integration Costs
23209 | Arnprior Area Study Upgrades
23210 | Commerce WayTS M1 ID22500 DX Gunn's Hill Wind Farm
23211 | Commerce WayTS M1 ID22500 TX Gunn's Hill Wind Farm
23219 | Trinity UPS upgrade 05 South HVAC 2014
23222 | Malden TS-M8-ID689-OM&A-PV mitigation
23224 | Almonte TS T3/T4
23225 | CMS Room 080 Refurbishment Project- OM&A Funds
23228 | Richview Manby Transmission Reinforcement - Line
23231 | Rainy River Gold Project
23233 | Allanburg TS M5 feeder construction
23237 | Hinchinbrooke SS BULK
23239 | St.Isidore TS T3/T4
23240 | Lauzon TS T5/T6; PCT & Component Replacement
23241 | Buchanan TS BULK
23242 | Ellesmere TS T3/T4; PCT & Component Replacement
23243 | Brant TS T1/T2
23245 | Buttonville TS T3/T4; PCT & Component Replacement
23246 | Longueuil TS T3/T4
23247 | Cumberland TS T3/T4
23248 | Leaside TS BULK; Component Replacement
23249 | Nepean TS T3/T4
23250 | Birch TS: Component Replacement
23254 | Timminco Idle Line Removal - Recoverable
23260 | Moosonee SC Purchase 2014 (1 Keewatin Drive)
23261 | Carlisle DS Transformer Upgrade
23267 | Keith TS Roof Replacement 2014
23268 | Physical Security
23271 | Riverdale JCT x Overbrook TS: Build new A6R Tap
23273 | Stouffville 10th Line DS New T3 & feeders
23274 | Longueuil TS-M24-ID964 & 965-Dx PV mitigation
23276 | Storm Management Customer Satisfaction Surveys
23277 | Magnetometer Installation Project
23278 | MTO Highway 427 Extension at Langstaff-Recoverable
23279 | Grand Bend DS F3 Voltage Conversion
23280 | Lennox TS 500kV Shunt Reactors
23281 | Placeholder for Distance Limitation Mitigation
23285 | Clearwater Bay voltage conversion Phase 1 of 3
23286 | Lauzon TS DESN2-M26- ID22580- Tx- Manning Pumping
23287 | 2015-2020 OPA Residential Programs
23288 | 2015-2020 OPA Commercial Programs
23289 | 2015-2020 OPA Industrial Programs
23290 | Palmerston TS: Station Rebuild
23293 | Lauzon TS DESN2-M26- ID22580- Dx- Manning Pumping
23294 | Sturgeon Falls DS - F2 ID24720 - Dx AGRIS 12
23295 | 2015-2020 OPA Low Icome Program
23296 | Foots Bay DS F1 Line Upgrade - Muskoka Rd 38
23297 | Ancaster West DS Transformer Upgrade
23299 | Chesters Corners DS-F3-ID24060-Dx-AGRIS Solar 4
23300 | HV UG Cable - Damage Claims
23301 | Picton TS M5 ID24790 Dx AGRIS Solar Garden 15
23302 | Picton TS M5 ID24790 Tx-AGRIS Solar Garden 15
23303 | Leamington TS - capital contribution
23304 | Leamington TS Feeder Development
23305 | Chesters Corners DS-F3-ID24060-Tx-AGRIS Solar 4
23307 | Trafalgar TS - Replace T15 and T15 'B' protection
23308 | Allanburg TS M6 Line Upgrade
23309 | Striker HVDS F2 ID25200 Dx Solvation-F
23310 | Picton TS M5 ID24780 DX Agris Solar Garden 11
23311 | Picton TS M5 ID24780 Tx-AGRIS Solar Garden 11
23312 | To Be Deleted - John TS HV/LV Station Rebuild
23313 | Sturgeon Falls DS F2 ID24660-DX FRITZ Solar 32
23314 | Sturgeon Falls DS F2 ID24670-DX FRITZ Solar 31
23315 | Sturgeon Falls DS - F2 ID24720- Tx AGRIS 12
23316 | Sturgeon Falls DS - F2 ID24830 - Dx AGRIS 13
23317 | Sturgeon Falls DS - F2 ID24830- Tx AGRIS 13
23318 | Chesters Corners DS-F3-ID23540-Dx-AGRIS Solar 1
23319 | Chesters Corners DS-F3-ID23540-Tx-AGRIS Solar 1
23320 | Sturgeon Falls DS F2 ID24660-TX FRITZ Solar 32
23321 | Sturgeon Falls DS F2 ID24670-TX FRITZ Solar 31
23322 | Tafalgar TS Well Tank 2014
23325 | Coutsville DS-F3-ID24,040-Dx-AGRIS Solar 3
23326 | Coutsville DS-F3-ID24,040-Tx-AGRIS Solar 3
23329 | Striker HVDS F2 ID25200 Tx Solvation-F
23331 | Picton TS M5 ID24800 AGRIS Solar Garden 10
23332 | Picton TS M5 ID24800 Tx AGRIS Solar Garden 10
23333 | Picton TS M5 ID25050 Dx FRITZ Solar 34
23334 | Picton TS M5 ID25050 Tx-FRITZ solar 34
23335 | Woodstock Integration Costs
23336 | Haldimand Integration Costs
23341 | Lennox TS BULK: ABCB component replacement
23342 | Stanley TS - Station Upgrade
23343 | DeCew Falls SS; P&C, Component Replacement
23344 | Crowland TS: T5, T6 & Component Replacement
23345 | Striker HVDS F2 ID25150 Dx Solvation-V
23346 | Underground Locates
23347 | Dymond TS - M1 - ID25110-DX Gengrowth Garden 04
23348 | Dymond TS - M1 - ID25110-TX Gengrowth Garden 04
23349 | Dymond TS - M1 - ID25190-DX Gengrowth Garden 01
23350 | Striker HVDS F2 ID25150 Tx Solvation-V
23352 | Kingston OC Erosion Control Humps 2014
23353 | COUTSVILLE DS-F1-ID25140-DX Gengrowth Garden 06
23354 | COUTSVILLE DS-F1-ID25140-TX Gengrowth Garden 06
23355 | Bruce A TS New System Service Transformer Connectn
23356 | Lennox TS Roof Replacement 2014
23357 | Chats Fall SS Roof Replacement 2014
23359 | Crystal Falls TS - M2 ID25630 - Dx 08 Guenette
23360 | Horning TS; Station Refurbishment
23361 | Brantford TS: PCT, MV Swyrd and Component Repl.
23362 | Beck 1 SS 115kV ABCB Replacement
23363 | Nebo TS: Component Replacement
23364 | Newton TS: T1, T2, PCT & Switchyard Refurbishment
23365 | Crystal Falls TS - M2 ID25360 - Dx 07 Rivet
23366 | Crystal Falls TS - M2 ID25360- Tx 07 Rivet
23367 | Underground Locates - OMA
23369 | COUTSVILLE DS-F3-ID25120-DX Gengrowth Garden 05
23370 | Crystal Falls TS - M2 ID25630 - Tx 08 Guenette
23371 | Battersea HVDS - F2 ID25590 - Dx 10 Foster
23372 | Battersea HVDS - F2 ID25590 - Tx 10 Foster
23373 | Princeton DS Voltage Conversion
23374 | Beaver Valley RS
23375 | Dymond TS - M1 - ID25190-TX Gengrowth Garden 01
23376 | Kenilworth TS: T1, T3, T4 & Switchyard Refurb.
23377 | Main TS T3/T4; T3, T4 & Component Replacement
23378 | Midhurst TS T1/T2; Component Replacement
23379 | Minden TS: T1, T2, PCT and Component Replacement
23380 | COUTSVILLE DS-F3-ID25120-TX Gengrowth Garden 05
23381 | Aylmer TS: Add 2 Breakers - ETPC & H1Dx
23382 | Warren HVDS F2 ID25080 Tx Gengrowth Garden 03 Giro
23383 | Warren HVDS F2 ID25080 Dx Gengrowth Garden 03 Giro
23384 | Placeholder for DC202 Life Cycle Projects - EPD
23386 | "CND MTS#2"- Provide 115 KV Connection
23387 | "Vaughan MTS#4"- Provide 230 kV Connection
23389 | Beach TS HVAC 2014
23390 | Richview TS T5/T6; Component Replacement
23391 | Richview TS T7/T8; Component Replacement
23392 | Line Refurbishment - C22J/C24Z/C21J/C23Z
23393 | Gardiner TS: T1/T2 PCT Component Replacement
23394 | Barrett Chute SS: Component Replacement
23395 | Sturgeon Falls DS - F2 ID24810 - Dx AGRIS 14
23396 | Sturgeon Falls DS - F2 ID24810- Tx AGRIS 14
23397 | Energy Storage Validation Projects
23398 | Minor Demand Capital Investments
23399 | IT Service Management Report
23400 | Placeholder for DC202 Load Growth Projects - Lines
23401 | Placeholder for DC202 Life Cycle Projects - Lines
23405 | Pine Portage SS: Component Replacement
23406 | Kenora TS: Component Replacement
23407 | Ridgetown Palmer DS Voltage Conversion
23408 | Peterborough Switch 237 Voltage Conversion
23409 | Physical Security Expansion Pilot Project
23410 | Otto Holden TS: T3/T4 & Component Replacement
23411 | Hearst TS: Component Replacement
23412 | Malden TS: Component Replacement
23413 | Talbot TS T3/T4; Component Replacement
23414 | Detweiler TS: AC Station Service Component Repl
23415 | Alexander SS: Component Replacement
23416 | Leaside TS HVAC upgrade 2014
23417 | Martindale TS: T21/T23 & Component Replacement
23418 | Mississagi TS HVAC upgrade 2014
23419 | Lincoln Heights TS: Component Replacement
23420 | Wonderland TS: T5, PCT & Component Replacement
23421 | Seaforth TS: T1, T2, T5, T6, PCT & Component Repl.
23422 | Kent TS: T1, T2 & Component Replacement
23423 | Edgeware TS: PCT & Component Replacement
23424 | Galt TS: PCT & Component Replacement
23425 | Clarke TS: T3, T4, PCT & Component Replacement
23427 | Bowmanville SS Overhead Door Ugrades
23428 | Richview TS elevator upgrades 2014
23429 | Essex OC Windows Replacement 2014
23430 | Stayner TS T3/T4; Component Replacement
23431 | John TS T1/T2/T3/T4; A3-A4 M/C & Component Replace
23432 | Finch TS T1/T2; Component Replacement
23433 | Horner TS: Component Replacement
23434 | Waubaushene TS T5/T6; PCT & Component Replacement
23436 | Orangeville TS: T1, T2, T3, T4 & Component Replace
23437 | Cherrywood TS 230kV BULK; ABCB & Component Repl.
23438 | Tomken TS T3/T4 PCT & Component Replacement
23439 | Pleasant TS Station Centric
23442 | Dufferin TS T2/T4; Component Replacement
23443 | Bermondsey TS T3/T4; T3, T4 & Component Replace
23444 | Dufferin TS: T1, T3, T4 & Component Replacement
23445 | Cecil TS: T1 & Component Replacement
23446 | Erindale TS: PCT & Component Replacements
23447 | Fairbank TS: T1, T2, T3, T4, PCT & LV Yard Replace
23449 | Ingersoll TS - Replace SP Breakers & Component Rep
23450 | Campbell TS: PCT & Component Replacement
23451 | Bruce B SS BULK
23452 | Owen Sound TS BULK; Component replacement
23453 | Walker TS #1 T3/T4; Component Replacement
23454 | Crawford TS T3/T4; Component Replacement
23456 | DS MUS Purchase Program
23458 | Striker HVDS F2 ID25090 Dx Solvation-VF
23459 | Lennox TS BULK:OPG Sync Breaker Replacement Coord
23461 | Aylmer TS capital contribution to Tx
23462 | New Post Creek GS Connection
23464 | Campbell TS M14&24 ID25800-TX-Guelph-Ind EnergyCtr
23465 | Striker HVDS F2 ID25090 Tx Solvation-VF
23466 | Line Refurbishment - S7M
23467 | PLACEHOLDER: NextBridge East-West Tie Line
23468 | Metrolinx-Eglinton LRT at Jonesville Cres-Recovera
23470 | Hanmer TS: 230-44 kV 83MVA DESN
23471 | M20/21D Install 230 kV In-Line Switches
23472 | Dx Coniston Voltage Conversion
23474 | Bronte TS; T5/T6 DESN Refurbishment
23475 | Operating Support System (OSS) Upgrades
23476 | CMS Station Service and Yard Supply Replacement
23477 | Wilson TS M6 ID22420-TX Oshawa PUC Networks Inc La
23479 | Kingsville TS-M1 M7-DG 1096 and 1099 TX PV mitigat
23485 | Striker HVDS F2 ID25180 Dx Solvation-S
23486 | Striker HVDS F2 ID25180 Tx Solvation-S
23490 | GTA OC Building Improvements 2014
23491 | Kenora OC HVAC 2014
23492 | Kirkland OC HVAC 2014 Upgrade
23495 | St Thomas Fleet - Gate Installation 2014
23496 | Trafalgar TS Compressor & Motor Replacement 2014
23498 | Cancelled - Steel Structure Replacement - K6F/K24F
23499 | D2L,Upper Notch x Martin River-Line Refurbishment
23500 | Lighting Upgrades OC 2014
23502 | Tweed OC Trailer Acquisition 2014
23505 | J5D, Keith TS-Mid R. JCT Waterman, Tx Line Refurb.
23510 | Preston TS M24-M30 ID25670 TX Toyota Motor Manufac
23516 | DOM Mtce & DS Operating Diagrams
23517 | Horner TS - M4 - ID26490-TX Campbell Company of Ca
23518 | Fergus TS - M4 - ID25260-TX Cripton
23519 | Lauzon TS - M29 - ID25580 - TX Woodslee Solar Gard
23520 | Barry's Bay Trailer acquisition 2014
23521 | Winchester OC Trailer Acquisition 2014
23522 | Brockville OC Trailer Acquisition 2014
23524 | Fergus TS - M4 - ID25250- TX Haja
23530 | Brockville TS ID26230-Dx 2MW Cogeneration System
23531 | Brockville TS ID26230 TX 2MW Cogeneration System
23532 | Grand Bend Municipal DS F3 Voltage Conversion
23533 | Kenilworth DS Upgrades
23534 | HVAC Replacements NTC128 Budget
23535 | Longlac TS: Relocate
23540 | Roof Replacements N.T.C.1.28 Budget
23545 | Port Colbourne TS M11 Conversion
23550 | Grid Control Network
23555 | Integrated System Operations Centre - New Facility
23557 | Buchanan TS Furnace Replacement 2014
23558 | Thunder Bay Maintenance Center - Humidifier Instal
23559 | Sudbury OC Building/ Yard Improvements 2014
23561 | Z1E: Connect Windsor Solar Project
23562 | CSO Efficiency Enhancement
23563 | CSO Efficiency Enhancement OM&A
23565 | Insulator/Pothead/Recoating Program
23566 | Field Metering Services Installation Labor Capital
23568 | Kirkland Lake TS - Indian Chute GS Re-connection
23569 | Trans. Prot. Replacement due to 2dn Harm. Misops
23570 | iMDS Station Refurbishments
23571 | Caledonia TS M3 Conversion
23572 | MeadowvaleTS M3 ID22460 TX 3.3MW CCS- Mississauga
23573 | Buchanan Grounding upgrade
23575 | Picton OC Carbon Dioxide Detection Installation
23576 | Perth OC Roof Improvements 2014
23577 | DS Herbicide Applications
23578 | CSO Efficiency Initiatives & Ramp Down
23579 | Merivale MTS: Station Upgrade
23580 | New Liskeard Bldg Improvements
23581 | Brockville OC Site Improvements 2014
23582 | Line Refurbishment - N21W/N22W
23583 | Trout Lake TS M5 ID19960-TX-North Bay Hydro
23584 | Tillsonburg TS-M2-Tx work_DG 281 and 282
23587 | Tx Lines - RoW G&S Planned Corrective Maintenance
23588 | Mobility
23591 | Kingston OC Improvements
23596 | Purchase of Spare Transformers Program
23597 | Demand Capital - Equipment Failure (Breakers)
23598 | Demand Capital - Equipment Failure (Transformers)
23599 | Power Transformer Capital Refurbishment Program
23600 | Rabbit Lake TS Septic Tank 2015
23602 | Sale of 115kV Transmission Line M3K
23603 | NERC CIP Version 5 - Development
23605 | Purchase of Breaker Operating Spares
23606 | C25H – Line Refurbishment
23609 | Stratford TS: T1 & Component Replacement
23610 | Yellow Falls Hydroelectric
23615 | Horner TS - Build 230-28-28kV Station
23616 | Runnymede TS - 115-28kV Station plus KxW upgrades
23617 | H29/H30: Reconductor 230kV Circuits
23618 | Connect New DESN near Halton TS
23619 | V41H/V42H - Connect Peel Energy Recovery Centre
23620 | Caledonia TS M3 Extension
23621 | M30A/M31A Conductor Upgrade
23623 | CSO DBOT
23624 | 2015-2020 OPA First Nations
23625 | Placeholder Corporate Performance Data - CAP
23626 | Placeholder Corporate Performance Data – OMA
23627 | Physical Security Monitoring Services
23628 | Placeholder OGCC Major Tools Assessment/RFI
23629 | TOU Billing & Meter Reading Optimiza - Capital
23630 | Bridgman PT Installation &Revenue Metering Upgrade
23631 | B4V - Connect Southgate Solar Project
23632 | Bruce A TS & Longwood TS: Reactor Switching Scheme
23633 | Uprate Q3N and Q4N
23634 | Gemini Power - Smooth Rock Fls Upgrade
23635 | Opus One; Dist Energy Mgmt & Storage Ntwrk (DEMSN)
23637 | HV UG Cable - Replace Pumping Plant HMI
23638 | Kleinburg TS M6 Mayfield Rd Line Extension
23639 | AMI Network & Meter Reading Enhancements
23642 | Placeholder ORMS Enhancements
23643 | Power Express Feeder Barrie TS to OGCC
23644 | Inergi Base ITO
23645 | TOU Billing & Meter Reading Optimization - OM&A
23646 | HV UG Cable - Replace C5E/C7E
23647 | Strachan TS T12/T14; T12 & Component Replacement
23648 | Kingsville Pulford DS Conversion
23650 | 2015-2020 CDM Pilots
23651 | Display Technology Capital Replacement
23653 | Stirton TS HVAC 2015
23654 | Fixed Asset Capitalization Enhancement
23655 | Burleigh DS F2 1ph to 3ph Conversion
23656 | Clearwater Bay voltage conversion Phase 2
23657 | Margach F3 voltage conversion - SD 3676
23658 | Devlin DS F1 3 Phase
23659 | Cataraqui TS: Component Replacement
23660 | Algoma TS: T5/T6 & Component Replacement
23661 | Mississagi TS: Component Replacement
23662 | Widdifield SS: Component Replacement
23664 | Orillia TS: Spill Cont. & Component Replacements
23665 | Foundation Repair/Replace - PL
23667 | Armitage TS M22 Extension
23668 | Uxbridge RS #2 (New)
23669 | Beaverton M29 extension
23670 | Orangeville TS M3-M6 Tie Line
23671 | St Thomas DS Voltage Conversion
23672 | Beckwith DS F3 Feeder Development
23673 | Arnprior Area Study - Line Work
23674 | Arnprior Area Study - Station Work
23675 | Placeholder OMA for NDC260 Projects
23676 | Runnymede TS: T3, T4 & Switchyard Replacement
23677 | Fairchild TS: T1, PCT & Component Replacements
23678 | Grenfel DS Load Transfer to Utopia DS
23679 | Minden TS 230kV BULK; Component Replacement
23680 | Inergi Base ADM
23681 | Replace Aviation Obstruct. Lights on Radio Towers
23682 | Tx Lines Insulator Replacement SGB
23683 | Birch TS M8 ID 27060 TX Thunder Bay RHSC CHP
23684 | CxA,Cameron Falls GS-Alexander GS,Tx Line Refurb
23685 | B5/6C, BurlingtonTS X WestoverCTS, Tx Line Refurb.
23686 | Replace Legacy SONET Systems
23687 | Line Refurbishment - B23C
23688 | Line Refurbishment - C28C
23689 | Birch TS M3 ID 27030 TX CMC CHP
23690 | Cherrywood TS 500kV BULK; ABCB & Component Repl.
23691 | Thornton TS T3/T4; Component Replacement
23692 | Leslie TS: Station Centric
23693 | Manby TS: T7, T9, T12, T13 & Component Replacement
23694 | Wanstead TS Capital Contribution
23695 | System Operations DC Colocation
23696 | D3A, Allanburg TS X ASW Steel CTS, Tx Line Refurb.
23698 | Essex TS - Connect Enwin Feeder to M10 Breaker
23699 | 2015-2020 Development of CDM new programs
23700 | Bramalea TS; Component Replacement
23701 | Placeholder OGCC Data Centre Remediation
23702 | OGCC Office Remediation
23704 | Beachville OC Trailer Acquisition 2015
23705 | Guelph-MTO-Silvercreek Pkwy Relocation-Recoverable
23706 | Hawthorne TS T7/T8 DESN: Add 44 kV Breaker for HOL
23707 | Enhanced Low Income Program
23708 | BSPS Removals
23709 | Merivale TS Add 230/115kV Autotransformers
23710 | Dundas OC Trailer Acquisition 2015
23714 | Tx Scrap & Surplus of System Reserve Equipment
23715 | Hanmer TS Fleet Garage Bolier
23716 | Bracebridge forestry Washroom Improvements
23717 | Timmins WestMine CTS Lakeshore Gold New Xfrm
23718 | Northwest Bulk Transmission Line - Development
23719 | TransAlta Sarnia CGS Telecom Upgrade
23720 | Waterloo-Columbia St Pole Relocation-Recoverable
23721 | Lauzon TS - New Breaker for H1Dx
23722 | Nanticoke TS: Connect HVDC Lake Erie Circuits
23723 | Wilson TS; Component Replacement
23724 | D2L,DymondxUpper+MartinxCrystal-Line Refurbishment
23725 | Carling TS ID26860 TX Chaudiere Hydro GS2
23726 | Line Rating Sensor Project
23727 | Retailer, Budget Billing, and Unbilled Revenue Opt
23728 | Dundas TS: MV Switchyard Refurbishment
23729 | South March TS Roof Replacement 2015
23735 | BL104 & BSH106 Idle Lines Removal Non-Recoverable
23736 | Caledonia TS M3 ID26810 DX Oneida Business park
23737 | Brockville TS M5 & B1R ID27020 TX Invista Maitland
23742 | Merivale TS Steel Canopy Improvements 2015
23743 | Musselwhite Mine Dart Upgrade
23744 | ICM Replacement Project (SAP EHSM Implementation)
23746 | Bruce A 500kV- Replace ABCB & Yard Reconfiguration
23747 | Caledonia TS M3 ID26810 TX Oneida Business Park
23748 | Transfer of Ownership of T8M Line to Hydro One
23749 | Enfield TS - capital contribution
23755 | OMA - ICM Replacement Project (SAP EHSM Impl)
23757 | Timmins OC Generator Fuel Tank Replacement 2015
23763 | Nepean TS M26 ID27820 TX Algonquin College - Cogen
23767 | AA 2015 Remediation
23768 | Thornton TS M2 ID25430-TX Oshawa PUC Metrolinx LD
23769 | Wilson TS HVAC Replacement 2015
23770 | Wiltshire TS Metal Roof Coating 2015
23771 | Horning TS Metal Roof Coating 2015
23773 | Lindsay SC Heat Pump Replacement 2015
23774 | Brockville OC Office Trailer Acquisition 2015
23775 | OGCC Emergency Generator Fuel System upgrades
23781 | A5A M2D W6CS 115kV Line Protection NERC Upgrades
23782 | GIC Replacement Pilot Project
23785 | Barrie Area Transmission Upgrade
23786 | Meaford TS: Component Replacement
23790 | Q11/12S - Beck GS #1 "Super" Str. Refurb + Conduct
23792 | Aylmer OC Security Upgrade 2015
23794 | Kent OC Security Upgrade 2015
23796 | Orangeville OC Security upgrade 2015
23798 | Lambton OC Security Upgrade 2015
23799 | Simcoe OC Security upgrade 2015
23804 | Hanmer TS HVAC Replacement 2015
23806 | Chatham SS: Component Replacement
23807 | Sarnia Scott TS: T5 & Component Replacement
23808 | St. Andrews TS: T3, T4 & Switchyard Refurbishment
23809 | St. Thomas TS: Station Decom & W3T, W4T, T11T Rcfg
23810 | Remote Disconnect/Reconnect - Installation
23811 | Remote Disconnect/Reconnect - Inventory
23812 | Remote Disconnect/Reconnect - PL Support
23815 | Detweiler TS: T2, T4 & Component Replacement
23816 | Hanlon TS: T1, T2 & Component Replacement
23817 | Wingham TS: T1, T2, PCT & Component Replacement
23823 | OGCC Dip pole 2015
23825 | Alfred DS F2 System Study Implementation
23826 | SAP Hold Co - CAP Portion
23827 | Nipissing OC Security Upgrades 2015
23828 | Buchanan TS Re-bricking 2015 Wall
23829 | Frankford pole Yard Parking Improvements 2015
23830 | IESO Meter Data Validation Dx
23831 | Smiths Falls TS M25 ID27370 DX 3M Perth Cogen
23832 | Smiths Falls TS M25 ID27370 TX 3M Perth Cogen
23833 | Leaside TS - BY (27.6kV) Yard - Revenue Metering
23834 | Protective Relaying Database for CAPE
23835 | HMI Replacement
23837 | Don Mouth Naturalization&Port Lands Flood Protect
23839 | R&D Program - EPRI
23840 | Chatham SS-MTO-Bell Conduit & Access Rd Relocation
23841 | Thorold Defoe DS Voltage Conversion
23843 | Nanticoke TS; CGVB Switch Replacement
23844 | Nanticoke TS; ABCB Project
23845 | Replacement of Waste Storage Sites - 2015/2016
23846 | Placeholder Upgrade/Enhancements to GIS
23847 | NERC CIP Version 6 - OPEX
23848 | CIP V6 Transient Cyber Assets & Removeable Media
23850 | Retailer, Budget Billing, and Unbilled Revenue Opt
23851 | Retailer, Budget Billing, and Unbilled Revenue Opt
23852 | Don Mouth Naturalization&Port Lands Development
23854 | Hawtorne TS Accommodation Trailer 2015
23859 | Listowel SC Metal Roof Coating 2015
23860 | R&D Program - CEATI
23861 | PlaceholderRD&D Project - Grid Mod& Energy Storage
23862 | Stirton TS: Swyd Refurbishment & Component Repl
23863 | Awenda DS F1 Upgrade Supply to Christian Island
23864 | Station Local Control Equipment Sustainment
23865 | Niagara Area Fiber Infrastructure Development
23866 | Simcoe OC Metal Roof Coating 2015
23867 | Minden CC Metal Roof Coating 2015
23868 | Lambton CC Metal Roof Coating 2015
23869 | Fenlon Falls SC Metal Roof Coating 2015
23871 | ITC - J5D Protection and Telecom Replacement
23872 | ITC - L4D L51D Line Protection and Telecom Replace
23873 | Longueuil TS M26 ID12510 DX Alfred Solar Farm
23875 | Lincoln SC Metal Roof Coating 2015
23876 | Remote Disconnection Program
23878 | Beach TS HVAC Replacement 2015
23879 | Winchester OC Trailer Acquisition 2015
23880 | Essex OC Metal Roof Coating 2015
23881 | East Elgin OC Metal Roof Coating 2015
23883 | Clinton OC Metal Roof Coating 2015
23884 | Removals - Revenue Meter Installations
23886 | Tilbury TS M1 Transfer
23887 | Remote Disconnect/Reconnect - M&RS Support
23888 | Panasonic/UOIT - Microgrid Research
23889 | Tomken TS: Revenue Metering Upgrade
23890 | Barry's Bay Trailer Acquisition 2015
23891 | OEB Package 1 - CAP Portion
23892 | OEB Package 1 - OMA Portion
23893 | PSP Lockbox
23895 | SAP Hold Co - OMA Portion
23896 | Online DGA Monitor Program
23898 | Kirkland Lake TS - M62 - ID26950 - Tx GT CH4
23899 | Kirkland Lake TS - M62 - ID26950 - Dx GT CH4
23901 | Orangeville SC Storage Yard Grading 2015
23904 | C23Z :Connect Belle River Wind Project
23905 | Esplanade TS Windows Replacement 2015
23907 | Cobden SC HVAC 2015
23909 | Bruce SC - Stairs 2015
23918 | Kirkland Lake TS - M62 - ID26970 - Tx GT CH2
23919 | Kirkland Lake TS - M62 - ID26970 - Dx GT CH2
23924 | Kirkland Lake TS - M62 - ID27160 - Tx GT CH16
23925 | Kirkland Lake TS - M62 - ID26980 - Tx GT CH9
23926 | Kirkland Lake TS - M62 - ID26980 - Dx GT CH9
23927 | Kirkland Lake TS - M62 - ID26990 - Tx GT CH13
23928 | Kirkland Lake TS - M62 - ID26990 - Dx GT CH13
23929 | Kirkland Lake TS - M62 - ID27000 - Tx GT CH7
23930 | Science Hill DS - F1 - ID27790 - Dx
23931 | Kirkland Lake TS - M62 - ID27150 - Tx GT CH8
23932 | Kirkland Lake TS - M62 - ID27150 - Dx GT CH8
23933 | Parry Sound TS M4 ID 27760-TX-Lakeland Power
23935 | Kirkland Lake TS - M62 - ID27000 - Dx GT CH7
23936 | Kirkland Lake TS - M62 - ID27010 - Tx GT CH14
23937 | Kirkland Lake TS - M62 - ID27010 - Dx GT CH14
23938 | Kirkland Lake TS - G3K - ID27420 - Tx Matachewan
23939 | Kirkland Lake TS - G3K - ID27420 - Dx Matachewan
23940 | Kirkland Lake TS - M62 - ID27140 - Tx GT CH3
23941 | Kirkland Lake TS - M62 - ID27140 - Dx GT CH3
23942 | Kirkland Lake TS - G3K - ID27430 - Tx KL 3
23943 | Kirkland Lake TS - G3K - ID27430 - Dx KL 3
23944 | Cobden SC - Site Grading 2015
23945 | Carlton TS M17 ID27930-Shickluna
23946 | Kirkland Lake TS - G3K - ID27440 - Tx KL 2
23947 | Kirkland Lake TS - G3K - ID27440 - Dx KL 2
23948 | Woodstock OC - Land Acquisition 2015
23949 | Duart TS - Feeder M5 - DG 487 Distance Limitation
23950 | Kirkland Lake TS - M62 - ID27160 - Dx GT CH16
23951 | Bathurst TS - Support Customer Duct Work
23952 | Finch/Warden/Runnymede Customer Fiber Support Work
23953 | Kirkland Lake TS - G3K - ID27450 - Tx KL 1
23954 | Kirkland Lake TS - G3K - ID27450 - Dx KL 1
23955 | Minden SC Paiving and Drainage 2015
23956 | Vale Copper#4 CTS - 230kV Supply Relocation
23958 | ISD Customer Care
23959 | Mid-Feeder Recloser Pilot - Integration with DMS
23960 | Two Abandoned Towers near E2R Removal Non-Recovera
23961 | George Bolton Parkway 44kV Expansion
23963 | AMI System Evaluation
23967 | Claireville TS, Trafalgar TS - Drainage Upgrade
23968 | Kingston OC Concrete Pad 2015
23969 | OGCC Washrooms & Kitchen & Cafeteria Upgrades 2015
23970 | Belle River TS M4 ID28210 TX GE004
23972 | Manby TS Watermain 2015
23974 | South Nepean Trans Reinforcement
23975 | Five Nations Energy (FNEI) - Moosonee PLC channel
23976 | Bruce B SS HVAC Replacement 2015
23979 | Phase 2: Fiber Cable Condition Monitoring System
23980 | Manby TS 115kV Load Rejection Scheme
23985 | Penetanguishene concrete Pad 2015
23991 | Brockville Office Tralier Renovations 2015
23993 | TS Facilities & Site Improvements
23994 | Tweed OC Drainage Improvement Design 2015
23995 | Arnprior Fleet Garage - Exhaust System 2015
23996 | Enterprise Content Management Phase B
23997 | Facilities Accommodation Improvements SC & Admin
23998 | Wanstead TS M4 PET-6 Recloser Teleprotection Upgra
23999 | Markham-Enbridge-IBM CTS Grounding Mods
24000 | Almonte TS M25 ID26880 TX Enerdu Generation Expans
24001 | SMNO Smart Meter Network Operations
24002 | New Facilities and Service Centers Improvements DX
24003 | PSIT Cyber Equipment EOL
24005 | Striker DS F1 - ID29560 - Tx North Shore Power
24006 | Striker DS F1 - ID29560 - Dx North Shore Power
24007 | Striker DS F1 - ID29570 - Tx North Shore Power
24008 | Striker DS F1 - ID29570 - Dx North Shore Power
24009 | Manotick DS F5 ID28120 DX 7251572 Canada Ltd.
24010 | Manotick DS F5 ID28120 TX 7251572 Canada Ltd.
24011 | IESO Meter Data Validation - Stations
24012 | Interval Meters - Stations
24013 | Placeholder Customer First Capital
24014 | Placeholder Customer First OMA
24017 | Palmerston TS T1/T2/T3; T1,T2,T3, PCT, MVGIS (Dx)
24020 | Tilbury TS-M1-ID 1477-Tilbury Solar 2 Tx work
24021 | Allanburg TS M6-M7 (Fonthill) feeder tie
24022 | Grenfel DS Station Relief
24023 | NOMS-CROW Interface
24025 | Meter Management & Verification Ser (SLA 054)
24026 | Wholesale Meter Services Provider (MSP)
24030 | Wholesale to Retail Standard (New meter w TCP/IP)
24031 | Meter Inventory Sustainment
24032 | Nanticoke TS New 600V Station Service Supply
24033 | Small Embedded Generation - Connections
24035 | Kingston Gardiner TS M26 Development
24036 | Wilson TS M1 ID29460-TX Oshawa PUC Microgrid Resea
24040 | Dynamic Energy Pricing Energate Pilot
24041 | Murillo HVDS Feeder Protection Upgrade
24042 | Nanticoke TS - Emergecy Feeder Connection
24043 | TSSA Station Equipment Inspections
24044 | Fergus TS M7 ID28770 - Tx Elora GS
24045 | Simpson Road 44kV Expansion
24046 | Tx Coniston Voltage Conversion
24047 | Hamilton - Anti-Climb - Recoverable
24048 | Bala River DS F3 - ID28600 - Dx - Little Burgess
24049 | Bala River DS F3 - ID28600 - Tx - Little Burgess
24050 | Web Redesign: HydroOne.com
24051 | Newport DS removal via voltage conversion
24052 | Town of Shelburne voltage conversion
24053 | New Old School DS and feeders
24054 | Carling TS KY Bus ID29920 TX The Royal Ottawa Coge
24055 | Thorold Transmission Towers Removal
24057 | Hamilton - Anti-Climb - Recoverable
24058 | L29C - Connect North Kent Wind I Project
24059 | Schomberg DS F4 ID29370 TX Foothill Greenhouses
24060 | Tillsongurg Norfolk Tie Line
24061 | Collection Redesign CAP
24062 | Collection Redesign OMA
24066 | Napanee TS - M2 - ID29150 - Tx - SFF 14 Solar PV
24067 | Napanee TS - M2 - ID29150 - Dx - SFF 14 Solar PV
24068 | Napanee TS - M2 - ID29160 - Tx - SFF 09 Solar PV
24069 | Napanee TS - M2 - ID29160 - Dx - SFF 09 Solar PV
24070 | Otonabee TS - M28 - ID29230 - Dx SFF 08
24071 | Otonabee TS - M28 - ID29230 - Tx SFF 08
24072 | Dundas TS M8 ID29310 DX Neven Produce CoGen
24073 | Dundas TS M8 ID29310 TX Neven Produce CoGen
24074 | L3P/L4P Telecom and Protection Upgrade
24075 | Napanee TS - M2 - ID29190 - Tx - SFF 23 Solar PV
24076 | Napanee TS - M2 - ID29220 - Tx - SFF 01 Solar PV
24077 | Napanee TS - M2 - ID29220 - Dx - SFF 01 Solar PV
24078 | Napanee TS - M2 - ID29190 - Dx - SFF 23 Solar PV
24079 | Schomberg DS F4 ID29370 Dx Foothill Greenhouses
24081 | Tx Wood Pole Replacement Program - ECS
24082 | Erindale TS - M42 - ID29470 - PepsiCo
24085 | Otonabee TS-M28-ID29060-Dx GreenLife Solar 18
24086 | Otonabee TS-M28-ID29060-Tx GreenLife Solar 18
24087 | Otonabee TS-M28-ID29080-Dx GreenLife Solar 7
24088 | Otonabee TS-M28-ID29080-Tx GreenLife Solar 7
24089 | Barry's Bay Voltage Conversion
24090 | Aguasabon SS: Component Replacement
24091 | Ansonville TS: Component Replacement
24092 | Elliot Lake TS: Component Replacement
24093 | Kapuskasing TS: Component Replacement
24094 | Mackenzie TS: Component Replacement
24095 | Parry Sound TS: Component Replacement
24096 | Rabbit Lake SS: Component Replacement
24097 | South March TS: Component Replacement
24098 | Whitedog Falls SS: Component Replacement
24099 | Port Arthur TS #1: Component Replacement
24100 | Forest Jura HVDS-ID69-SCADA Upgrade
24101 | CIP-014 Physical Security Implementation
24102 | GIS Breaker Refurbishment
24103 | 48 VDC Telecom Equipment Replacement Program
24104 | Migration of Protections in Ottawa to Fiber NTWK
24105 | Warkworth DS Removal
24106 | Snow Valley DS F1 Extend to County Rd 90
24107 | NMS Capital Sustainment
24108 | Mobile Radio System Replacement
24109 | Lakehead TS: Component Replacement
24110 | Aylmer TS Dx new Feeder
24111 | Woodroffe TS - Replace 15kV UG Cables/Terminations
24112 | Rose Corner F3 (Part 1 & 2)
24113 | Billing - OEB Regulatory Compliance
24114 | Hydro One Customer App Enhancement - CAP
24115 | Alexandria Area Study
24116 | ESA Fees
24117 | HR Operations Process Optimization
24118 | HR Pay Transformation Project - Discovery
24119 | SuccessFactors Onboarding - Discovery
24120 | PMR Infrastructure Refurbishment Program
24121 | ITMC Backup Move to ISOC
24122 | PLC System Refurbishment
24123 | Telecom Performance -Ring 8 OPGW (H27H, X3H)
24124 | Telecom Performance - Ring 6 OPGW (B22D,Hannover)
24125 | Telecom Performance - Ring 6/2 (ADSS D6V/E9V)
24126 | Telecom Performance - OPGW Repl Strategy
24127 | Merivale TS: Component Replacement
24128 | Albion TS: Component Replacement
24129 | Billing - Peak Pricing & Rate Options
24130 | Threat Risk Assessments (TRAs)
24131 | King City DS - New Station & Feeders
24132 | NERC CIP V6 CAPEX - Low Impact Facilities
24133 | Removal of Abandoned Metering Installations
24134 | St. Lawrence TS: Component Replacement
24135 | Billing - Non-Energy Integration
24136 | Collections - Pre-Paid Metering
24137 | Collections - Dunning Redesign
24138 | Contact Center - Enhance Outage App
24139 | Contact Center - Customer Insight & Data Analytics
24140 | C&I Customers - Alerts & Analytics
24141 | C&I Customers - New Rate Design
24142 | C&I Customers - Demand to Interval
24143 | C&I Customers - Microfit Replacement
24144 | C&I Customers - Large Customer Calendar Month Bill
24145 | SAP BPC - Planning Module
24146 | SAP Mobile - Pay Advice & Time Reporting
24147 | S4 HANA - Finance & Logistics
24148 | BPC Move to Embedded Model
24150 | RF Device Replacement
24151 | TC219 - Upstream Transmission Work for DG
24152 | Domtar Espanola: Supply additional Load
24153 | Placeholder - IVCT Refresh
24154 | Alliston TS: T3, T4 & Component Replacements
24155 | Billing - Dynamic Pricing
24156 | Contact Center - Mobile Platform Strategy
24157 | Bill Redesign
24158 | Billing – Seasonal Rate Class Elimination
24159 | Storage Area Network Refresh
24160 | Frontenac TS: PCT & Component Replacement
24161 | Smith Falls TS: Component Replacement
24162 | Terrace Bay SS: Component Replacement
24163 | Marathon TS: Component Replacement
24164 | Wawa TS: Component Replacement
24165 | Fort Frances TS: Component Replacement
24166 | Crawford TS: T4 & Component Replacement
24167 | Compliance Enhancement
24168 | Segregation of networks (Dev/QA) - Placeholder
24169 | Security Perimeter Enhancement
24170 | Enfield TS - capital contribution
24171 | Enfield TS Feeder Development
24172 | Cedar TS: T7, T8 & Component Replacement
24173 | Asset Analytics Risk Factor - OMA
24174 | Asset Analytics Risk Factor - CAP
24175 | Scarboro TS: T23 & Component Replacements
24176 | Wilson TS: T1 & Component Replacement
24177 | Bathurst TS: T3, PCT & Component Replacements
24178 | Charles TS: T3, T4 & Component Replacements
24179 | Claireville TS: Component Replacements
24180 | Duplex TS: T1, T2 & Component Replacements
24181 | Kleinburg TS: Component Replacements
24182 | Rexdale TS M/C Switchgear & Component Replacement
24183 | Tomken TS: T1 & Component Replacements
24184 | Trafalgar TS: Component Replacements
24185 | Woodbridge TS: T5 & Component Replacements
24186 | SAP Treasury
24187 | Placeholder-Customer PQ Dx- Capital (Cancelled)
24188 | DX UVM - Defect Correction
24189 | Closed - Tactical Maintenance
24190 | Risk and Security Profiling
24191 | Security Awareness Program
24192 | Cyber Threat Intelligence Program
24193 | Data Loss Prevention
24194 | Application Security Review
24195 | Security Risk Management strategy
24196 | Cyber Security Program
24197 | Governance Framework
24198 | Enterprise identifty & Access Management
24199 | Security Event Monitoring Project - Placeholder
24200 | Endpoint Security - Placeholder
24201 | Vulnerability Assessments&Security Patching - PHol
24202 | Data Loss Prevention
24203 | Customer PQTx-Cap (PQ meters stand-alone)
24204 | Customer PQ Dx - OMA
24205 | PCMIS Modernization and Optimization
24206 | PCMIS Modernization and Optimization OMA
24207 | Lotus Notes Modernization and Optimization
24208 | Lotus Notes Modernization and Optimization OMA
24209 | Project Portfolio Management Tool for ISD
24210 | Engineering Design Transformation
24211 | Engineering Design Transformation OMA
24212 | Source-to-Order Transformation Project - CAP
24213 | Napanee TS Cap-Switcher Installation
24214 | Hanover TS: T2 & Component Replacement
24215 | Lauzon TS: T6, T8 & Component Replacement
24216 | Longwood TS: Component Replacement
24217 | Talbot TS: Component Replacement
24218 | Caledonia TS: Component Replacement
24219 | Jarvis TS: Component Replacement
24220 | Lake TS: T1,T2, P&C & Switchyard Refurbishment
24221 | Stanley TS: T2, PCT & Component Replacement
24222 | Thorold TS: T1, MV Switchyard & Component Repl.
24223 | Construction Services, Capital Project Estimating
24224 | Construction Services, Capital Project Estimating
24225 | MFA for M2M Project
24226 | Minden TS - M3 - ID30220 - Dx Minden GS
24227 | Minden TS - M3 - ID30220 - Tx Minden GS
24228 | Beck #1 SS - G10 OPG Upgrade Work
24229 | Smiths Falls TS M24 ID29880 DX Hershey Drive
24230 | Customer PQ Tx - OMA - Revenue meters
24231 | HV UG Cable - Polarization Cell Rplmt
24232 | Stations Work Management & Mobility - Capital
24233 | Stations Work Management & Mobility - OMA
24234 | Forestry Move to Mobile - Capital
24236 | Third-Party TCA Upgrades - Recoverable
24238 | D4Z, Nine Mile JCT-IPB Casey JCT, Tx Line Refurb.
24239 | D1/2M, Minden TS X Otter Creek JCT, Tx Line Refurb
24240 | Smiths Falls TS M24 ID29880 TX Hershey Drive
24241 | C&I Customers - First Fuel
24242 | Emergency Response Plans Program
24243 | Napanee TS - M5 M6 - Development
24244 | Northwest Bulk Transmission Line - Construction
24245 | Forestry Move to Mobile - OMA
24246 | Consolidate Security Event Monitoring - Placeholde
24247 | GIS Roadmap Initiatives - Capital
24248 | GIS Roadmap Initiatives - OM&A
24249 | Environment Health & Safety System Enh - Capital
24250 | Environment Health & Safety System Enh - OMA
24251 | Move to Mobile - Provincial Lines - OMA
24252 | Enterprise Content Management - Phase C
24253 | Enterprise Content Management - Phase C - OMA
24254 | ECM E-Signature
24255 | ECM E-Signature- OMA portion
24256 | Enterprise Content Management - Program
24257 | Enterprise Content Management - Program- OMA
24259 | Thunder Bay-MTO-Hwy11/17 at Ouimet-Recoverable
24261 | Information Rights Management - Placeholder
24262 | RD&D Project - TX Grid Mordern & Energy
24263 | PLACEHOLDER: Tx Line Refurb. Future Candidate
24264 | Douglas Point TS: Component Replacement
24265 | B3/B4, Horning Mt. - Glanford, Tx Line Refurb (Cu)
24266 | X2Y, Magel. Aero. CTS X IPB Bryson JCT, Tx Ln Refb
24267 | Tx Line Refurb. P1P/P1T ¦ TBPI Thndr Bay-Prt Arthr
24268 | DETL- A8/9K, Str.141 X Kirkland Lake TS, Tx Ln Ref
24269 | A7L/R1LB/A6P & 57M1, Alxdr B-Lkhd, Tx Ln Refurb
24270 | K1/K2, Krklnd Lk- A. Barrick, Tx Line Refurb (Cu)
24272 | E1C, E.Fall X S.Fall + Etrcn X C.River, Tx Ln Rfb.
24273 | D1A/D3A, Gibson JCT-Thorold TS, Tx Line Refurb.
24274 | H1L/H3L/H6LC/H8LC, Bloor St-Leasd, Tx Line Refurb.
24275 | D6V/D7V, Guelph North JCT-Fergus TS,Tx Line Refurb
24276 | Q3M6, Frontenac TS-Novelis CTS, Tx Line Refurb.
24277 | D2/3H, Hunta SS and Abitibi Canyon SS, Tx Ln Refub
24278 | Tx Line Refurb. C27P ¦ Galetta-Bannockburn
24279 | Tx Line Refurb. L22H ¦ Easton JCT-Hinchinbrk N
24280 | Tx Line Refurb. E8V/E9V ¦ Orangeville TS-Essa JCT
24281 | Q4C, IPB Ottawa River-Chats Falls, Tx Line Refurb.
24282 | M6/7E, Coopers Falls JCT X Orillia TS, Tx Ln Refur
24284 | eBilling Customer Usage Analytics - OMA
24285 | C7BM, Chats Falls SS X Fitzroy JCT, Tx Ln Refurb.
24286 | A4H/A5H, Tunis JCT-Fournier JCT, Tx Line Refurb.
24287 | Tx Line Refurb. B5QK ¦Barrett Chute#2-Sharbot
24288 | A4L, Beardmore X LongLac TS, Tx Line Refurb
24289 | S2N, Sydenham JCT-Adelaide JCT, Tx Line Refurb.
24291 | Tx Line Refurb. L9C/L12C ¦ Leaside TS-Balfour JCT
24292 | D7F/D9F, Twr157 JCT-Kitch MTS7, Tx Line Refurb.
24294 | D6, Des Joachims TS X Petawawa DS, Tx Line Refur
24295 | Tx Line Refurb. T2R/T61S¦Wawaitin JCT-Shiningtree
24296 | Tx Line Refurb. B7/B8 ¦Burlington TS-Bronte TS
24297 | Kapuskasing area reinforcement - Kapuskasing TS
24298 | Project Portfolio Management Tool for ISD - OMA
24299 | Thorold Allanport DS removal via voltage conversio
24300 | Preston TS: T3, T4 & Component Replacement
24301 | Modernization of Worst Performing Feeders
24302 | Norfolk TS: Component Replacement
24303 | Burlington TS: MV Switchyard and Component Repl.
24304 | FCI Deployment Program
24305 | Meadowvale TS: Component Replacement
24306 | Morrisburg TS; Component Replacement
24307 | Carling TS; Component Replacement
24308 | Otonabee TS; Component Replacement
24309 | Moose Lake TS: Component Replacement
24310 | Bilberry Creek TS; Component Replacement
24311 | Havelock TS; Component Replacement
24312 | Hunta SS; Component Replacement
24313 | Spruce Falls TS; Component Replacement
24314 | Kapuskasing area reinforcement - H9K Upgrade
24315 | Thorold Turner DS removal via votlage conversion
24316 | Kent TS-M15-ID274-Dx-PV mitigation
24317 | Ramore TS - Install second transformer
24320 | PCAD v6.5 Upgrade
24321 | Wendover HVDS F3 ID30400 DX Ferme Rene Franche & F
24322 | IAMGOLD - 115 kV Mine Connection
24323 | Ramore TS Upgrade Capital Contribution
24324 | Beck #1 SS - G1 G2 OPG Connection
24325 | Fairchild TS M8 - Support THESL Protection Upgrade
24326 | eBilling Customer Usage Analytics - CAP
24327 | Wanstead TS Egress Relocation
24329 | H23B - Connect Stone Mills CGS
24331 | Oxy Vinyls Load Displacement Generator Connection
24335 | Enhancemnts-Cust Billing/Metering/Testing Platform
24336 | OMA Enhancements-Cust Billing/Metering/Testing
24337 | MSO and Jumper Installations
24338 | Cooksville TS-EZ Bus-ID28280-Lakeview Water Treatm
24339 | Almonte M25 ID 63 – Mississippi River Power SCADA
24341 | Wanstead TS M4 PET-6 Recloser Teleprotection TX
24342 | Kirkland Lake TS - G3K - ID30060 - Tx Matachewan L
24343 | Kirkland Lake TS - G3K - ID30060 - Dx Matachewan L
24344 | Source-to-Order Transformation Project - OMA
24345 | Nanticoke TS - Removal of OPG Equipment
24346 | AMI Network Expansion Economic Limits
24347 | Nebo TS M12 ID32360 DX Maple Leaf Foods Inc
24348 | Nebo TS M12 ID32360 TX Maple Leaf Foods Inc
24349 | Onaping Depth Connection to S5M
24350 | Demand Capital - Equipment Failure (E&CS)
24351 | Havelock TS-M1-ID29980-Dx-O'Brien
24352 | Havelock TS-M1-ID 30,120- Dx-Emma Cardiff 2
24353 | Havelock TS-M1-ID29980-Tx-O'Brien
24354 | Havelock TS-M1- ID30,120 -Tx- Emma Cardiff 2
24356 | Town of Dundalk voltage conversion
24358 | Havelock TS-M1-ID29970-Dx-Antonio West
24359 | Havelock TS-M1-ID29970-Tx-Antonio West
24360 | TWE - Construction Service Equipment
24361 | Havelock TS-M1-ID30130-Dx-Kelly North
24362 | Havelock TS-M1-ID30130-Tx-Kelly North
24363 | Bermondsey TS - Support THESL M1 Breaker Upgrade
24364 | Dundas Sydenham DS Voltage Conversion
24365 | Havelock TS-M1-ID30110-Dx-Donovan
24366 | Havelock TS-M1-ID30110-Tx-Donovan
24370 | Havelock TS-M1-ID30090-Dx-Card
24371 | Havelock TS-M1-ID30090-Tx-Card
24372 | Havelock TS-M1-ID30100-Dx-Conlon
24373 | Havelock TS-M1-ID30100-Tx-Conlon
24374 | Havelock TS-M1-ID30140-Dx-Forcier
24375 | Havelock TS-M1-ID30140-Tx-Forcier
24376 | Havelock TS-M1-ID30150-Dx-Painter
24377 | Havelock TS-M1-ID30150-Tx-Painter
24378 | Havelock TS-M1-ID 30,170- Dx-Switzer G
24379 | Havelock TS-M1- ID30,170 -Tx- Switzer G
24380 | Havelock TS-M1-ID30960-Dx-McGinn
24381 | Havelock TS-M1-ID30960-Tx-McGinn
24382 | HavelockTS-M1-ID31000-Dx-Lambe
24383 | HavelockTS-M1-ID31000-Tx-Lambe
24384 | HavelockTS-M1-ID31010-Dx-Watson
24385 | HavelockTS-M1-ID31010-Tx-Watson
24386 | HavelockTS-M1-ID31020-Dx-Kelly South
24387 | HavelockTS-M1-ID31020-Tx-Kelly South
24388 | Stewartville TS-M3-ID31060-Tx-Time Fibre Fit
24389 | CTI Replacement - OMA
24390 | Havelock TS-M1-ID30180-Dx-Scheurer
24391 | Havelock TS-M1-ID30180-Tx-Scheurer
24392 | Havelock TS-M1-ID30930-Dx-Blakely
24393 | Havelock TS-M1-ID30930-Tx-Blakely
24394 | Havelock TS-M1-ID30940-Dx-Kyte
24395 | Havelock TS-M1-ID30940-Tx- Kyte
24396 | Havelock TS-M1-ID30950-Dx-Cox
24397 | Havelock TS-M1-ID30950-Tx-Cox
24398 | Kapuskasing L21L38 PSR
24399 | Perth Area Study
24400 | Web Redesign: eCustomer
24401 | Web Redesign: HydroOne.com
24402 | Forest Jefferson and Mcnab DS Conversion
24403 | Wallaceburg DS Conversion
24404 | Lucan Market DS 4kV Conversion
24405 | Drumbo DS Conversion
24406 | Anderdon DS Conversion
24407 | Wardsville DS Conversion
24408 | Zorra DS Conversion
24409 | Stray Voltage Investigation and Resolution
24410 | Norfolk TS M5 ID18230 Dx-UDI Port Ryerse Wind Farm
24411 | AMI Network Expansion Economic Limits Program
24412 | Web Redesign: eCustomer
24413 | Operation-time DG Connection Impact Assessment
24414 | SAP Fixed Asset & Settlement - OMA
24415 | Thorold Turner DS Voltage Conversion
24416 | Thorold Front DS Voltage Conversion
24417 | Thorold Allanport DS Voltage Conversion
24418 | Thorold Cleveland DS Voltage Conversion
24419 | Thorold Ormond Voltage Conversion
24420 | Dundas TS #2 New Feeders
24421 | Caledonia TS New Feeders
24422 | Puslinch DS 4th Feeder
24423 | Tilsonburg-Norfolk Tie Line
24424 | Macville DS - new 27.6kV station and feeders
24425 | OEB Regulatory Compliance - OMA
24426 | Bill Redesign - OMA
24427 | Hydro One Customer App Enhancement - OMA
24428 | Non-Energy Integration - OMA
24429 | Peak Pricing & Rate Options - OMA
24430 | Dynamic Pricing - OMA
24431 | Pre-Paid Metering - OMA
24432 | Dunning Redesign - OMA
24433 | Enhance Outage App - OMA
24434 | Customer Insight & Data - OMA
24435 | Mobile Platform Strategy - OMA
24436 | New Rate Design - OMA
24437 | First Fuel - OMA
24438 | Demand to Interval Conversion - OMA
24439 | Seasonal Rate Class Removal - OMA
24440 | Net Metering Program (Microfit Replacement) - OMA
24441 | eCustomer Replacement - OMA
24442 | eBilling Customer Usage Alerts - OMA
24443 | Malden TS M12 ID30730 DX - McKinley
24444 | Dresden DS Conversion
24445 | HR Operations Process Optimization - OMA
24446 | SAP BPC - Planning Module - OMA
24447 | SuccessFactors Onboarding - OMA
24448 | HR Pay Transformation Project - OMA
24449 | Strategic Sourcing – Ariba - OMA
24450 | RF Device Replacement - OMA
24451 | HydroOne.com Redesign - OMA
24452 | SAP Treasury - OMA
24453 | Brockville 44kV M3/M7 expansion for Load Growth
24454 | Embrun Area Study
24455 | SAP CRM & iCare Enhancements - CAP
24456 | Complaint Management Tool - CAP
24457 | SAP CRM & iCare Enhancements - OMA
24458 | Complaint Management Tool - OMA
24459 | Shedden DS Refurbishment
24460 | Weston Lake DS - Feeder Tie & F2 Egress 3-phasing
24461 | Brookside DS removal
24462 | SAP Spares Management
24463 | Mobile Enterprise Content Management
24464 | Customer Request System
24465 | Brockville Town Area Study
24466 | Smiths Falls Area Study
24467 | Chesterville Area Study
24468 | Ivy Lea Area Study
24469 | Actons Corners Area Study
24470 | Russell Area Study
24471 | Maxville Area Study
24472 | Kemptville Area Study
24473 | Prescott Area Study
24474 | Berwick - Finch Area Study
24475 | Rondeau DS Conversion
24476 | Tx Portal Enhancement - CAP
24477 | Website Upgrade & Enhancement - CAP
24478 | C&I Portal Enhancement - CAP
24479 | Tx Portal Enhancement – OMA
24480 | Website Upgrade & Enhancement - OMA
24481 | C&I Portal Enhancement – OMA
24482 | Mattawa HVDS Automation Pilot
24483 | Dundalk Victoria DS F2 1-3ph conversion
24484 | Bradford DS F3 - reinforcement
24485 | Lily Lake DS Removal
24486 | Goderich TS - M4 - ID30870 - Compass LDG
24487 | Eganville Bruce DS removal Area Study
24488 | Wainfleet DS End-of-life station replacement
24489 | PMR Engineering Support New
24490 | Oil Springs DS Refurbishment
24491 | Stratford DS Refurbishment
24492 | Stratford East Hope DS Refurbishment
24493 | Enhancements for AMINO and P&L
24494 | Enhancements for AMINO and P&L - OMA
24495 | C&I Billing & Telephony Enhancements
24496 | SAP Spares Management - OMA
24497 | Mobile Enterprise Content Management - OMA
24498 | Customer Request System - OMA
24499 | C&I Billing & Telephony Enhancements - OMA
24500 | OEB Regulatory Compliance
24501 | OEB Regulatory Compliance - OMA
24502 | C-Suite Replacement
24503 | C-Suite Replacement - OMA
24504 | Striker HVDS F2 ID30270 Dx NSPG Fixed 300
24505 | Great Lakes Power Integration Costs
24506 | S2B - Surge Arrestors on 115kV circuit
24507 | Medonte DS F1-Deand Enhancement Diamond Valley
24508 | Kingsville TS-M1 M7-DG 1096-1099 Cust PV Mitigatio
24509 | Drive X Software and Process Development
24510 | Striker HVDS F2 ID30260 Dx NSPG Fixed 200
24511 | Striker HVDS F2 ID30260 Tx NSPG Fixed 200
24512 | Kent TS M22 ID30440 TX - Entegrus -Dajcor Aluminum
24513 | E2E Performance Monitoring - OMA
24515 | Striker HVDS F2 ID30270 Tx NSPG Fixed 300
24516 | Striker HVDS F2 ID30430 Tx NSPG Fixed 400
24517 | Striker HVDS F2 ID30430 Dx NSPG Fixed 400
24518 | Walker TS - Connect Enwin Feeder to M3 breaker
24519 | Clarke TS M8 ID31660 TX - London Hydro 3M Cogen
24520 | Itron EE Upgrade CAP
24521 | NDM260 - Itron EE Upgrade – OMA
24522 | Corporate Services Transformation - Finance - CAP
24523 | Corporate Services Transformation - Finance - OMA
24524 | Move-to-Mobile – Corporate - CAP
24525 | Move-to-Mobile - Corporate - OMA
24526 | Web Redesign Project CAP
24527 | Web Redesign Project – OMA
24528 | Customer Alerts & Analytics CAP
24529 | Customer Alerts & Analytics – OMA
24530 | Dymond TS - M3 - ID30700 - Tx Wahgoshig Solar 2
24531 | Dymond TS - M3 - ID30700 - Dx Wahgoshig Solar 2
24532 | SIA_PO_DG projects ID 32020 and 32050
24536 | Muskoka TS Cap-Switcher Installation
24540 | King Edward TS T3 and PCT Replacement
24541 | AMI Hardware Refresh (EOL)
24545 | Field Site Surveys - BCA Identification
24546 | Hardware Firmware Security - Standards
24547 | TFE Support - Standards
24548 | TC219 - Transmission Work for DGs (Program)
24549 | Business Call Center Project
24550 | Ontario Rebate for Electricity Consumers
24551 | WINDEEE2- Progressive Failure Analysis of Tx Lines
24552 | Watay Line_to_Pickle Lake Connection
24554 | D10H - 115 kV In-Line Switches
24560 | L7S - Reliability Performance Mitigation
24566 | BATHURST TS:Support Breaker Installation for THESL
24567 | Espanola TS - M2 - ID30900 - Helios Queensway
24570 | Ottawa LRT - Recoverable
24575 | Cobden TS M6 Extension
24576 | Parry Sound TS M1 ID 32180 -TX- Parry Energy Store
24578 | 2017 Dynamic Energy Pricing Pilot – OEB Extension
24579 | Cecil TS: Revenue Metering Upgrade
24580 | Bermondsey TS - Support THESL M9 and M11 upgrade
24582 | Red Lake TS / E4D upgrade - Capital Contribution
24583 | Brocks Beach DS F2 ID 30820 - DX - Storage Zone
24587 | DirectCurrent Fast Charger(DCFC) for EVs
24589 | Parry Sound TS M1 ID 32180 -DX- Parry Energy Store
24590 | Connect Marmora Pumping Station TX
24591 | 2017 Low Income ASHP CDM Pilot
24592 | Brocks Beach DS F2 ID 30820 - TX - Storage Zone
24595 | Erin DS F3 - Demand Enhancement
24596 | SIA Application: ID32450 Sky One Muskoka M2
24600 | Porcupine TS; Installation of Physical Security Pe
24601 | Tel Eng Technical Support New
24602 | Longueuil TS M24 44kV Line Expansion
24604 | SIA App: ID33250-Gardiner TS-Invista swordfish
24605 | ITC - L4D L51D Protection Replacement
24607 | Clarabelle TS: Component Replacement
24609 | Wendover DS F3 ID31800 DX Celeste Solar
24610 | Holland TS M6 ID32390 TX NTP BESS
24612 | Brant TS M22 Line Enhancement
24613 | Riverdale TS ID31620 CHP Carleton University
24614 | Aylmer TS: New Feeder Position for Erie Thames
24615 | Cap-Switcher Installations - Multiple
24616 | Transient USB solution (Was 23848)
24617 | NAE CTS SCADA Connection to Merivale TS
24622 | Station Service Estimates
24625 | Wendover DS F3 ID31800 TX Celeste Solar
24626 | Chapleau DS - 7 MW Borden mine - SIA application
24630 | Operationalize DTF in Sector 4
24635 | Frontenac M1/M8 Switching - town of Gananoque
24636 | Bruce Info Centre Wind Turbine - Decommissioning
24637 | Hinchey TS QZ BUS ID32620 Hull2 HOL
24638 | Dundas TS M1 ID29300 DX eNature Greenhouses Inc
24639 | Dundas TS M1 ID29300 TX eNature Greenhouses Inc
24640 | Overbrook TS: Relocate HONI P&C Equipment
24641 | Lisgar TS QZ Bus ID32610 Tx 1GS HOL
24645 | St Lawrence TS M24 ID31940 Dx Barlow Energy Centre
24646 | St Lawrence TS M24 ID31940 TX Barlow Energy Centre
24650 | Meadowvale TS M7 ID32340 TX 3050 Argentia
24666 | Orillia Integration Costs
24667 | C21J: Connect Romney Wind Energy Centre
24668 | Metrolinx Electrification Conflicts - Recoverable
24670 | Arnprior TS: Station Rebuild
24671 | Manby x Whiltshire OPGW (KxW)
24675 | Keith TS M1 ID31600 TX - K+S Windsor Salt
24680 | Leslie TS - M21, M25, M27, M28 KSO replace support
24681 | Physical Security Expansion Pilot Project
24682 | Porcupine TS; Installation of Physical Security Pe
24685 | Business Continuity and Emergency Preparedness
24690 | Nebo TS M11 Book Road Expansion
24695 | NERC Sustainment Program
24696 | Fair Hydro Plan
24697 | Fair Hydro Plan
24699 | Gerrard TS x Carlaw TS LV Cable Replacements
24700 | Kingsville TS M4 ID31570 TX - SPN030
24701 | Joint Use and Relocations >$75k
24702 | L7S - Increase Capacity - 3 spans out of Seaforth
24703 | C21J and C22J: Upgrade Thermal Rating
24704 | B27S/B28S - Connect New TS
24705 | Vulnerability and Compliance Program.
24706 | GoWest Gold - Connect Bradshaw Gold CTS to H6T
24707 | Stewartville TS M1 ID32050 DX Calabogie Upgrade
24708 | Stewartville TS M1 ID32050 TX Calabogie Upgrade
24709 | N5K: Connect Otter Creek Generation
24710 | Workplace Screening
24711 | OPG Drawing Demerger
24712 | Security and Architecture for Projects
24714 | Campbell TS: T1, T2 Transformer Replacement
24716 | NERC v5 Mock Audit
24717 | Leamington DESN2: Build Second 230/27.6 kV DESN
24718 | Elgin TS ID31690 TX Alectra Utilities 2MW Cogen
24719 | Niagara Region Wind Farm SPS Implementation
24720 | Nepean TS M24 ID31850 TX Algonquin College cogen
24721 | W44LC – Connect Dutton CGS
24722 | Doane DS - Installation and Expansion of F4 feeder
24723 | Telecom Capital Lease Renewals (IRU Agreements)
24724 | Idle Metallic Communication Cable Removals
24725 | Nanticoke TS - Connect Nanticoke Solar Generation
24726 | Connect Markham MTS#5
24727 | SIA Application: 7Acres 15 MW - Douglas Point TS
24728 | Hawthorne M30A/M31A Line Disconnect Switch Upgrade
24729 | Bill Redesign
24730 | D6V/D7V - Connect New MTS
24731 | Campbell TS - Build 2nd Half of DESN#2
24732 | Nanticoke GS Disconnection
24733 | Lambton GS Disconnection
24734 | Aylmer Tillsonburg Area Tranmission Reinforcement
24735 | D6V/D7V - Upgrade 5 km of circuit out of Detweiler
24737 | Tx Lines Aviation Light Remote Monitoring Repl
24738 | Software for PQ Reports - Tx
24739 | Q25BM/Q29HM ADSS Replacement with OPGW
24740 | Muskoka TS M2 ID 32450 - TX - Sky One
24741 | Eastern Field Wind Power Project Connection
24742 | Muskoka TS M2 ID 32450 - DX - Sky One
24743 | MTU Mtce&Inspect
24744 | Customer PQ Tx - OMA - PQ Audit - Lightning
24745 | Fergus TS M4 M8 ties
24746 | H6T: Connection of Bradshaw Gold 5MW Load
24747 | Nation Rise Wind Farm Connection
24748 | 3rd Party SLU Technical Reviews
24749 | Stations Work Management & Mobility - Capital
24750 | Bill Redesign OMA
24751 | Telecom Infrastructure-Leaside x Downtown GTA
24752 | Ctrl Room Windows 10 Computer Consoles -Dev Projet
24753 | Basin TS A-12-BN ID32190 IESO BESS#1
24754 | Basin TS A-12-BN ID32200 IESO BESS#2
24755 | Third Party Studies & Estimates-SLU-Recoverable
24756 | Physical Security Strategy
24757 | New DESN in Northern York Region
24758 | Pickering End of Commercial Operation
24759 | Proxy Server Hardware Refresh
24760 | Ingersoll TS M46 ID33650 DX - Greenholm Farms -CA
24761 | Ingersoll TS M46 ID33650 TX - Greenholm Farms
24762 | Sidney TS-M1-Existing-Dx-Glen Miller CGS
24763 | Sidney TS-M1-Existing-Tx-Glen Miller CGS
24764 | Install DDRs for NERC Compliance
24765 | Stations Work Management & Mobility - OMA
24766 | J3E and J4E: Upgrade Thermal Rating
24767 | Little Long SS - Install 2nd Battery & Stn Service
24768 | Dryden TS: Component Replacement
24770 | Testing New900MHzTelecom Systems_DG Teleprotection
24772 | M6E/M7E Sectionalizing Disconnect Switches
24773 | Kleinburg Coverall Enclosure
24774 | Cooksville Microwave Replacement
24775 | Longueuil TS: T3/T4 Replacement
24776 | Arnprior TS: Station Refurbishment
24778 | Overbrook TS: Metalclad & Component Replacement
24779 | Crosby TS T3 & Component Replacement
24780 | Wallace TS T3/T4 & Component Replacement
24781 | Slater TS T1/T2/T3 & Component Replacement
24783 | MetroLinx City View Traction Substation Connection
24784 | MetroLinx Mimico Traction Substation Connection
24785 | Kirkland Lake TS: Component Replacement
24786 | Muskoka TS: Component Replacement
24787 | Pinard TS: Component Replacement
24788 | Porcupine TS: Component Replacement
24789 | Spruce Falls TS: Component Replacement
24790 | Dufferin TS: Revenue Metering Upgrade
24791 | Nanticoke TS T12 & Component Replacement
24792 | Connect X21/X22 to Belleville
24793 | Connect C27P to Chenaux
24794 | Duplex TS: Revenue Metering Upgrade
24795 | MetroLinx Burlington Traction Substation Connectio
24796 | MetroLinx Scarborough Traction Station Connection
24797 | MetroLinx ERMF Traction Substation Connection
24798 | MetroLinx Allandale Traction Substation Connection
24799 | Wendover DS F3 ID32020 DX Pendleton Solar Energy C
24800 | VMware Server Refresh
24801 | Malden TS: Add Two New 27.6 kV Feeders
24802 | Strachan TS: Revenue Metering Upgrade
24803 | John TS: Revenue Metering Upgrade
24804 | Charles TS: Revenue Metering Upgrade
24805 | Wendover DS F3 ID32020 TX Pendleton Solar Energy C
24806 | S4 HANA (EAM)
24807 | S4 HANA (EAM)
24808 | Norfolk-Ireland DS F1 line rebuild Oakwood Ave
24809 | King Edward TS: Upgrade metalclad
24810 | Orleans TS: Provide second 230kV supply
24811 | Tremaine TS - Add Four 27.6kV Feeders
24812 | Pleasant TS - 42M1 Feeder Position
24813 | EPRI TX Rate Filing Support 2018
24814 | Terauley A5-A6 M/C Replacement
24815 | Terauley TS: Revenue Metering Upgrade
24816 | Back Office Associates Data Migration Accelerator
24817 | Infobase / NAMCIS Replacement
24818 | Infobase / NAMCIS Replacement
24819 | HL3/HL4 Cable Replacement
24820 | Connect C28C to Dobbin
24822 | K2M Protection Modification for Kenora CGS Upgrade
24825 | Cecil A1-A2 M/C Replacement
24826 | Duplex A3-A4 M/C Replacement
24827 | Beaverton TS: Component Replacements
24828 | Milton SS: Component Replacements
24829 | Bowmanville SS: Component Replacement
24830 | Kenilworth TS: Install 13.8kV Capacitor Breaker
24831 | Norfolk TS: Install Capacitor Bank
24832 | BasinTS: New Ashbridge Bay Generation
24835 | Basin TS: Open A7/A8 Bus Tie
24836 | Extend H82V/H83V to Kleinburg TS
24837 | Telecom Infrastructure-Wiltshire x Bridgeman
24838 | Telecom Infrastructure-GTA Downtown Fiber Install
24840 | Mock Audit Remediation
24841 | Copeland MTS Phase 2 Connection
24845 | Basin TS Expansion
24846 | Esplanade TS to Don Fleet Jct 115kV TX Upgrade
24847 | Bridgman Jct - Replace Two Air Break Switches
24850 | Georgia Pacific CTS Disconnection
24851 | Watay Red Lake Connection
24852 | Richview Manby Transmission Reinforcement -Station
24854 | Telecom 48Vdc Power Supply Remote Monitoring
24855 | Lambton TS Demerger
24856 | Nanticoke TS Demerger
24858 | Goderich TS M3 ID34010 Tx - NRStor Goderich CAES
24859 | GE UR CPU VI/VO Replacement
24860 | IT Service Management Project Phase 2
24861 | Elmira TS M1 ID33390 Tx-Elmira Solid Battery SS
24862 | Norfolk Thomson Rd. Pole-Trans Replacements
24863 | Aylmer TS M4 ID32590 TX - IGPC Ethanol
24864 | Phaser Development
24865 | Legacy Metering Maintenance
24866 | HONI TXs Metering Asset Maintenance
24867 | Prevent Presistent Estimation
24868 | CSO Technology Projects 2023+
24869 | Select Bill Due Date
24871 | 2018 Compensation Upgrades
24872 | Select Bill Due Date
24873 | Bill Redesign
24874 | Waterloo-Erb Street Widening-Recoverable
24877 | Digital Correspondance
24878 | Predictive Analytics & Artificial Intelligence
24879 | Digital Correspondence
24880 | Prevent Presistent Estimation
24881 | CSO Technology Projects 2023+
24882 | Bill Redesign
24883 | Autotransformer Tertiary-GF Prot Tripping
24884 | Autotransformer Tertiary-GF Prot Tripping Upgrade
24885 | Predictive Analytics & Artificial Intelligence
24886 | Telecom Transport Network & Unforeseen Asset Repl
24887 | DNU (DELETE) Milton SS: Component Replacements
24888 | DNU (DELETE) Beaverton TS: Component Replacements
24889 | NOMS Upgrade (2023)
24890 | GE UR CPU VI/VO Corrections
24891 | Leaside TS: Restring O/H M3 fdr to new THESL pole
24892 | TremaineTS: New Breaker Positions-Burlington Hydro
24893 | TremaineTS: New Breaker Positions-Milton Hydro
24894 | Anti-Climb Devices - Recoverable
24895 | Emergency Communication System
24896 | Business Continuity Database
24897 | Advanced Persistent Threat End Point Protection
24898 | Threat Hunting HW-SW
24899 | Perimeter Security - EIT Infrasturcture Refresh
24900 | new AR
24901 | Bunting TS: MV Switchyard & Component Replacement
24902 | Murray TS: T11, T12 & Component Replacement
24903 | Information Rights Management Phase 2
24904 | Information Rights Management Phase 2
24905 | OGCC Long View Phone System QA Environment
24906 | PSR Replacement
24907 | SAP Control Entry Project
24908 | TX Non-Operational Data Mgmt System
24909 | Place Holder - Campbellville Pit Remediation
24910 | Security Ed. & Communication - Staff,ELT & Board
24911 | Code of Practice Governance and Risk Mgt
24912 | Workforce Screening
24913 | Business Continuity Sustainment
24914 | Application Security External Expertise
24915 | Emergency Notification Annual Subscription
24916 | Advanced Persistent Threat End Point Protection
24917 | Adv'd Persistent Threat Prot. SW - OM&A Install
24918 | Forensic Service Retainer
24919 | Penetration Testing Program
24920 | Threat and Vulnerability Feeds
24921 | Threat Hunting HW-SW Maintenance
24922 | Threat Hunting HW-SW OM&A Installation Expertise
24923 | Threat Hunting quarterly service
24924 | SIEM Hardware-Software
24925 | SIEM Hardware-Software Fixed Price Installation
24926 | SIEM Hardware-Software Maintenance 18%
24927 | SIEM Hardware-Software Monitoring Managed Service
24928 | Owen Sound TS: Component Replacement
24929 | Tilbury TS: Station Decommissioning
24930 | Lambton TS: T5 & Component Replacement
24931 | Port Colborne TS: T61, T62 & Switchyard Refurb.
24932 | Palermo TS: T3, T4 & Switchyard Refurbishment
24933 | Minor Enhancements to Aveksa-Access control
24934 | Access Central Application
24935 | NERC v7 Suppy Chain (2019)
24936 | NERC v7Virtulization
24937 | NERC v7 Encryption
24938 | NERC v7Transient LOW (2019)
24939 | ISL Replacement
24940 | ISOC Security Equipment
24941 | IT Service Management
24942 | NERC Sustainment Resources
24943 | NERC V7 Virtualization - Encryption - Third party
24944 | ISL Replacement OMA
24945 | Tx Lines Idle Line Removal
24946 | TWE - CMS Service Equipment
24947 | Outlier - D7V - Animal Abatement
24948 | Campbellville Pit Remediation - Recoverable
24949 | GIS: Migration to Cloud
24950 | Metrolinx - Wilson (Don) Yard Relocations - Recov
24951 | Metrolinx - Caldeonia GO Station - Recoverable
24952 | NextBridge - East-West Tie Line - Tx Mods - Recove
24953 | Enterprise Analytics – AA New Risk Factors
24954 | Enterprise Analytics – Reliability Analytics/CP
24955 | Enterprise Analytics – AA New Risk Factors
24956 | Enterprise Analytics – Reliability Analytics/CPR
24957 | System Reserve Equip-Operating Spares Corrective
24958 | Edgeware TS M7M8 Asset Purchase
24959 | Heritage Resources Management
24960 | Transient Cyber Asset Sustainment
24962 | Completion of Q26M/Q35M Line Work
24963 | Gardiner TS-M24-33250-Dx-Invista Swordfish
24964 | Gardiner TS-M24-33250-Tx-Invista Swordfish
24965 | Circuit Switchers for Outlier Improvement
24967 | Outlier - M9K - Lightning
24968 | Outlier - S2B-e - Line Assessment
24969 | Outlier - S5M- Line Assessment
24970 | Outlier - P15T/P7G- Line Assessment
24971 | Outlier - A4L - Fault Locator
24972 | Haldimand-Jarvis TS M6 Lakeshore Rebuild
24973 | Outlier - Animal Abatement Projects
24974 | Outlier - Lightning Protection Projects
24975 | Outlier - Line Sectionalizer Projects
24976 | P&C Sparing Plan
24979 | Otonabee TS - M28 - ID32570 - SFF08
24980 | GIS: Field Network Design Replacement
24981 | GIS: SAP Data Improvement and OMS Consolidation
24982 | GIS: Customer GIS + Legacy System Consolidation
24983 | GIS: Migration to Cloud-OMA
24984 | GIS: Field Network Design Replacement - OMA
24985 | GIS:SAP Data Improvement and OMS Consolidation-OMA
24986 | GIS:Customer GIS + Legacy System Consolidation-OMA
24987 | Dx Zone 2 InterPhase Spacer Pilot Project
24988 | Bill Redesign - C&I Customers - Capital
24989 | CDM Online Shopping Tool
24990 | RAS Procedures
24991 | Synchrophasors (PMU)
24992 | Safety by Design
24993 | Bala River DS F2 ID 28600 - DX - Little Burgess GS
24994 | Bala River DS F2 ID 28600 - TX - Little Burgess GS
24995 | IVR Redesign - Capital
24996 | Smart Meter Replacement - Capital
24997 | Web Redesign 2.0 - Capital
24998 | Bill Redesign - C&I Customers - OMA
24999 | CDM Online Shopping Tool
25000 | IVR Redesign - OMA
25001 | Smart Meter Replacement - OMA
25002 | Web Redesign 2.0 - OMA
25003 | Corporate Mobility - CAP
25004 | Corporate Mobility - OMA
25005 | Otonabee TS - M28 - ID32570 - Tx - SFF08
25006 | L7S - Reliability Performance Mitigation
25007 | Lake TS M4M6 Rebuild
25008 | Otonabee TS - M28 - ID33630 - Tx - 741-JP-BLK W PL
25010 | Lauzon TS M7 - ID33510 TX WFCU Centre CHP Project
25011 | Kleinburg TS M25 ID34330 DX - Husky Energy Strg-CA
25012 | Kleinburg TS M25 ID34330 TX - Husky Energy Strg
25013 | Lake TS M4M6 Rebuild
25014 | Crawford TS M11 ID34550 TX - Aquatic Centre CHP
25016 | Physical Access Monitoring Upgrade
25017 | Physical Security Spare Inventory
25018 | Customer Digital Enhancements - Capital
25019 | Customer Digital Enhancements - OMA
25020 | Norfolk-Bloomsburg DS M3 Recloser and Regulator
25021 | Otonabee TS - M28 - ID31900 - Dx - GGELP_0026
25022 | Chapleau DS - Borden Mine 7 MW Load Connection
25023 | Muskoka TS M8 ID35020 DX - 1.21GW Lancelot
25024 | Muskoka TS M8 ID35020 TX - 1.21GW Lancelot
25025 | Sidney TS - M4 - ID31530 - Dx - Trenton Lock 1
25026 | Sidney TS - M4 - ID31530 - Tx - Trenton Lock 1
25027 | Otonabee TS - M28 - ID33630 - Dx - 741-JP-BLK W PL
25030 | SIA App: ID35640-Picton TS-White Pines Wind Farm
25031 | Otonabee TS - M28 - ID31900 - Tx - GGELP_0026
25032 | Lake Superior Link - Development
25035 | McCrimmon DS F3 ID33240 Dx Sen Biogas 2
25036 | McCrimmon DS F3 ID33240 Tx Senn Biogas 2
25037 | NOVA Corunna CTS T2 Transformer Relocation
25038 | OGCC DC Cooling Enhancements
25039 | OGCC Data Centre Remediation
25040 | SIA Application: Peace Naturals 12MW - Stayner TS
25042 | Wanstead TS M4 ID33690 TX - Union Gas - Dawn Exp.
25043 | Wanstead TS M4 ID33690 DX - Union Gas - Dawn Exp
25044 | Lindsay TS - M7 - ID 34000 - SCI CE9_Tx
25045 | To be allocated
25046 | Thornton TS - M1 and M8 - ID34110 - TX - Class A
25047 | Birch TS M6 ID 35060 TX Lakehead University Cogen
25050 | Lindsay TS - M7 - ID 34000 - SCI CE9_Dx
25055 | Call Center Repatriation Project - Capital
25056 | 2018 RPP Road Map Pricing Pilot - OEB
25060 | Call Center Repatriation Project - OMA
25061 | Belleville TS - Station Refurbishment
25065 | Havelock TS-M2-ID33970-Tx-SCI HA2
25066 | Havelock TS-M2-ID33970-Dx-SCI HA2
25067 | Stewartville TS-M1-ID35350-Dx-SCI RE9
25068 | Stewartville TS-M1-ID35350-Tx-SCI RE9
25069 | Stewartville TS-M1-ID35370-Dx-SCI RE11
25070 | Stewartville TS-M1-ID35370-Tx-SCI RE11
25071 | Orillia TS - M2 - ID33430 - Dx - 734-DT-PT LT 15
25072 | Orillia TS - M2 - ID33430 - Tx - 734-DT-PT LT 15
25073 | Orillia TS - M2 - ID33490 - Dx - 749-DT-7663
25074 | Orillia TS - M2 - ID33490 - Tx - 749-DT-7663
25075 | Brant–Powerline Rd Line Relocation–Recoverable
25076 | 2018 Saugeen FN Geothermal Heat Pump Pilot
25080 | Kingsville TS: T1,T3 & Component Repl Phase 2
25081 | Distribution Line Spacers
25082 | Hurondale DS Padmount Transformers
25083 | GORMS to FDGIS Migration Project
25085 | Orillia TS - M2 - ID33420 - Dx - 868-DT-6989 CON
25086 | Orillia TS - M2 - ID33420 - Tx - 868-DT-6989 CON
25087 | Orillia TS - M2 - ID33460 - Dx - 865-DT-7181
25088 | Orillia TS - M2 - ID33460 - Tx - 865-DT-7181
25089 | Orillia TS - M2 - ID33470 - Dx - 869-DT-7868 Cronk
25090 | Orillia TS - M2 - ID33470 - Tx - 869-DT-7868 Cronk
25091 | Security Operation - Threat Hunting Cap Proj
25092 | Physical Security for Critical Stations
25093 | CIP-014 Physical Security Implementation
25094 | Lindsay TS - M6 - ID 34030 - Lakeview2 GM Sola_Dx
25095 | RD&D Project - Tx Grid Modernization&EnergyStorage
25096 | Distance to Fault
25097 | Carbon Cap & Trade Program
25098 | Beaverton TS - M26 - ID 33990 - SCI CE2_Dx
25099 | Beaverton TS - M26 - ID 33960 - SCI CE5_Dx
25100 | Orillia TS - M2 - ID33410 - Dx - 831-DT-5714 Allan
25101 | Orillia TS - M2 - ID33410 - Tx - 831-DT-5714 Allan
25102 | Midhurst TS - M4 - ID34210 - Dx -LSRA Solar
25103 | Affordability Fund Trust
25104 | Contact Centre Transition - Discovery
25105 | Lindsay TS - M6 - ID 34030 - Lakeview2 GM Sola_Tx
25106 | Battersea HVDS-F1-ID34830-Dx-William Benjamin Grn
25107 | Otonabee TS - M28 - ID 33940 - SCI NO1_Dx
25108 | Otonabee TS - M28 - ID 33940 - SCI NO1_Tx
25109 | Otonabee TS - M28 - ID 33980 - SCI OT1_Dx
25110 | Beaverton TS - M26 - ID 33990 - SCI CE2_Tx
25111 | Beaverton TS - M26 - ID 33960 - SCI CE5_Tx
25113 | Coniston TS - Station Decomission & Removal
25114 | Midhurst TS - M4 - ID34210 - Tx -LSRA Solar
25115 | Otonabee TS - M28 - ID 33980 - SCI OT1_Tx
25116 | Picton TS-M5-35640-Dx-White Pines Wind Farm
25117 | Picton TS-M5-35640-Tx-White Pines Wind Farm
25118 | Dundas TS M1 Rebuild
25120 | Beaverton TS - M26 - ID 35330 - SCI CE3_Dx
25121 | Beaverton TS - M26 - ID 35330 - SCI CE3_Tx
25122 | Niagara Murray TS: Revenue Metering Upgrade
25125 | Battersea HVDS-F1-ID34830-Tx-William Benjamin Grn
25126 | Crowland TS M19 ID35130 TX - GE BTM
25130 | Tx Tower Grounding Upgrades-Recoverable
25131 | Dx Sensors Deployment Project
25132 | RTES Replacement
25137 | Dack DS - F1 - ID11730-DX Charlton Dam
25138 | TECHS-LINES-Standards-Dx
25140 | OEB Price Pilot Project - Capital
25141 | OEB Price Pilot Project - OMA
25142 | Success Factors Onboarding
25145 | Dack DS - F1 - ID11730-TX Charlton Dam
25146 | GORMS to FDGIS Migration Project - OM&A
25147 | Stewartville M3 - ID34500 - SCI RE5_Dx
25148 | Stewartville - M3 ID34500 - SCI RE5_Tx
25149 | Stewartville M3 - ID34490 - SCI RE1 DX
25150 | Stratford TS M6 ID35610 TX - Koskamp 100kW Biogas
25151 | Stratford TS M6 ID35610 DX - Koskamp 100kW Biogas
25152 | Stewartville - M3 - ID 34500 - SCI RE5_Dx
25154 | Joint Use Projects and Relocations <75K
25155 | Strewartville M3 - ID34500 - SCI RE5_Dx
25156 | Construction for EnWin DX Duct Bank in Keith TS
25157 | Ft. Frances TS: Remove T4 and GT1
25158 | Cochrane West DS - Station Refurbishment
25159 | WPF Coe Hill DS F2 Communicating FCIs
25160 | Stewartville - M3 ID34490 - SCI RE1_Tx
25161 | Stewartville M3 - ID34510 - SCI RE7 DX
25162 | Stewartville - M3 ID34510 - SCI RE7_Tx
25163 | Stewartville - M3 ID35280 - SCI RE6_Tx
25164 | Stewartville M3 - ID35280 - SCI RE6 DX
25165 | Customer Select Due Date - Capital
25166 | Customer Select Due Date - OMA
25167 | Toronto-TTC Scarborough Subway TPSS–Recoverable
25168 | Muskoka TS M2 ID34980 DX - 1.21GW Lancelot
25169 | Muskoka TS M2 ID34980 TX - 1.21GW Lancelot
25175 | CIP-014 Implement Defined Security Measures-OGCC
25176 | CIP-014 Implement Remaining 24 sites
25177 | WPF Smiths Falls TS M25 Remote Operable Switches
25178 | WPF Smiths Falls TS M26 Remote Operable Switches
25179 | WPF Snow Road DS F2 Communicating FCIs
25180 | Crystal Falls TS - M1 - ID34710 - Tx Shoreline 2
25181 | Crystal Falls TS - M1 - ID34710 - Dx Shoreline 2
25182 | Scarboro TS M24 ID32640 TX - 50 Salome Dr
25183 | WPF Orillia TS M2 Remote Operable Switches
25184 | Dx Work for CAE and CAR DG Projects (E&PD)
25185 | WPF Almonte TS M28 Remote Operable Switches
25186 | WPF Arnprior TS M2 Remote Operable Switches
25187 | WPF Brockville TS M6 Remote Operable Switches
25188 | WPF Chesterville TS M1 Remote Operable Switches
25189 | WPF - Palmerston TS M3 - Remote Operable Switches
25191 | Stewartville M1 - ID35350 - SCI RE9_Dx
25192 | Stewartville - M1 ID35350 - SCI RE9 TX
25193 | Stewartville M1 - ID35360 - SCI RE4_Dx
25194 | Stewartville - M1 ID35360 - SCI RE4 Tx
25195 | Stewartville M1 - ID35370 - SCI RE11 Dx
25196 | Stewartville - M1 ID35370 - SCI RE11 Tx
25197 | Stewartville M1 - ID35380- SCI RE12 Dx
25198 | Stewartville - M1 ID35380 - SCI RE12 Tx
25199 | Coniston TS Removal Capital Contribution
25200 | Viaduct Platform Pilot
25201 | Stewartville TS - M1 - ID35600 - Dx - Mill Ridge
25202 | Stewartville TS - M1 - ID35600 - Tx - Mill Ridge
25203 | Chapleau DS - F4 - ID35580 - Tx Goldcorp Borden Mi
25204 | Chapleau DS - F4 - ID35580 - Dx Goldcorp Borden Mi
25205 | AMI-Standards-Dx
25206 | WPF Emsdale DS F3 Line Relocation
25207 | WPF - Manitoulin TS M25 - Remote Operable Switches
25208 | WPF - Manitoulin TS M26 - Remote Operable Switches
25209 | WPF - Trout Lake TS M7 - Remote Operable Switches
25210 | WPF - Owen Sound TS M25 - Remote Operable Switches
25211 | WPF Murillo DS F1 Remote Operable SW + CFCIs + OCR
25212 | WPF Murillo DS F3 Remote Operable SW + CFCIs + OCR
25213 | Bathurst TS - M3, M5, M30, M31 KSO replace support
25214 | Bermondsey -M23 & M26 relay & fibre duct supp work
25216 | WPF Waubaushene TS M7 Remote Operable Switches
25217 | Tx Lines Idle Line Removal – Lakeview GS
25218 | WPF Waubaushene TS M1 Remote Operable Switches
25219 | WPF Cobden TS M6 Remote Operable Switches
25220 | WPF Trout Creek DS F1 Fault Indicators and others
25221 | WPF Port Arthur TS M6 Fault Indicators and others
25222 | Hydro Hawkesbury MTS: SCADA Connection
25223 | WPF MindenTS M2 Remote Switch and Recloser Upgrade
25224 | WPF OtonabeeTS M27 Remote Switch, Recloser Upgrade
25225 | WPF Picton TS M5 Remote Operable Switches
25226 | WPF Muskoka TS M4 Remote Operable Switches
25227 | WPF Muskoka TS M2 Switches and Recloser Relocate
25228 | WPF Muskoka TS M10 Remote Operable Switches
25229 | WPF Muskoka TS M1 Remote Operable Switches
25230 | WPF Combermere DS F3 Communicating FCIs
25231 | Port Hope TS M17 ID35930 Dx Sabic Demand Response
25232 | Port Hope TS M17 ID35930 Tx Sabic Demand Response
25233 | WPF - Clarabelle TS M8 - Remote Operable Switches
25234 | Power Quality/P&C Spares Management
25235 | WPF Wallace TS M4 REMOTE OPERABLE SWITCHES
25236 | WPF Wolverton DS F1 Sensors
25237 | Bruce B SS - Transfer control of JL501 & L501L563
25238 | WPF Havelock TS M1 REMOTE OPERABLE SWITCHES
25239 | WPF - Martindale TS M5 - Remote Operable Switches
25240 | SCADA Enablement Existing M Reclosers
25241 | WPF Wallace TS M6 REMOTE OPERABLE SWITCHES
25242 | WPF Big Chute F2 Tie-Line Construction
25243 | WPF -Shiningtree DS F1 -Remote Operable G&W Vipers
25245 | Orillia TS M4 ID35540 DX - OSMH Restart
25246 | Orillia TS M4 ID35540 TX - OSMH Restart
25247 | WPF - Grand Bend East DS F2 - Protection Upgrade
25248 | WPF Schomberg DS F3 CFCIs
25249 | PQ Audit Dx - OMA
25250 | Revenue Meter Integration Dx - OMA
25251 | Beach TS M82 ID30230 TX Columbian Chem Cogen
25256 | WPF Tillsonburg TS M10 Sensors
25260 | Nebo TS M12 ID35860 DX Maple Leaf Foods Inc
25261 | Nebo TS M12 ID35860TX Maple Leaf Foods Inc
25262 | WPF Orangeville M45 Remote Switch,Recloser Upgrade
25265 | Fairchild TS - M2, M4, M5, M6 replace support
25271 | CSO Transition CAP
25272 | Lake Superior Link - Construction
25273 | Transmission Tower Grounding Upgrades
25274 | Alliston TS M11, M12 - ID36290 Tx Honda Alliston
25276 | Slater TS T1 Emergency Replacement
25277 | NTM117 DG OM&A cost for 2018
25278 | Cat Lake MTS Upgrade
25279 | Leamington TS #2- capital contribution
25280 | Otonabee TS M27 ID35750 DX Dam 24 Hydro (Peterboro
25281 | Otonabee TS M27 ID35750 TX Dam 24 Hydro (Peterboro
25282 | Pelham Load Relief
25283 | Dresden Area Load Relief
25284 | Fiddlers Green DS Supply Improvements
25285 | Leamington TS #2 Feeder Development
25286 | Bismark DS Offloading
25287 | Decewesville DS Conversion
25288 | Ancaster Area Load Relief
25289 | Decewesville RS Replacement
25290 | Elora Area Load Relief
25291 | Alma Area Load Relief
25292 | Inergi - Base IT Sustainment
25293 | Inergi - ITO Modernization Master AR
25294 | Northwest Transmission Enhancement - Phase 2
25295 | Wanstead TS New Feeder Position
25296 | Havelock TS M3 ID34630 Tx - Drain Bros
25297 | Havelock TS M3 ID34630 Dx - Drain Bros
25299 | UI Path Automation - CAP
25300 | WPF Commerce Way Wolverton Tie
25301 | Dover Center Load Relief
25303 | Kirkton DS - F1 - ID36150 - DX - Gardiner Biogas
25304 | Dx Lines SAP Work MGR Upgrade - CAP
25305 | Pickering Communication Tower Removal
25306 | D60 Relay Upgrades for Fault Detection - Dx OM&A
25307 | Woodstock TS M6 ID35770 TX-Woodstock Hospital CHP
25308 | Woodstock TS M6 ID35770 DX-Woodstock Hospital CHP
25310 | Comm Tower Lighting and Monitoring Upgrades
25312 | Avista Financial Integration
25313 | Ellesmere TS M29 ID31760 Tx - Copperfield
25314 | Galt TS M14 ID36680 Tx - Franklin Gen Set
25315 | Alliston TS M11, M12 - ID36290 Dx Honda Alliston
25316 | Bronte TS M1 - ID36010 NRStor C&I Monarch Plastics
25317 | Otonabee TS M27 ID35740 DX Buckhorn Hydro Peterbor
25318 | Otonabee TS M27 ID35740 TX Buckhorn Hydro Peterbor
25319 | Enterprise Content Management (ECM) Implementation
25320 | Enterprise Content Management (ECM) Implementation
25321 | Coniston TS: EOL Component Replacement
25322 | Orillia TS M4 - ID35870 289 Coldwater Rd - Loblaws
25323 | Next Generation Data Centre-Ph2
25324 | Electronic File Transfer
25325 | Woodbridge TS M3 ID36860 Tx - Gracious Living
25326 | Planbox
25327 | Wholesale Meter Upgrades - Bilberry and Woodstock
25328 | Gerrard TS - ID35460 Regent Park Energy Inc.
25330 | UI Path Automation - OMA
25331 | EnWin Chrysler MTS Telecom Upgrade
25332 | Metrolinx-HamiltonLRT-Line Relocation
25333 | iHub Upgrade
25334 | Tivoli Upgrade
25335 | Low Impact Electronic Protection
25336 | Leslie TS - M23, M24 breaker & relay upgrade supp.
25337 | Private Cloud Data Center
25338 | Private Cloud Data Center
25339 | K6F-13 Disconnect Switch Controls
25340 | UI Path Automation – COMMON CAP
25341 | UI Path Automation - COMMON OMA
25342 | UI Path Automation - DX OMA
25343 | Glendale TS M31 ID35160 TX - Landfill Gas
25344 | John TS: T1, T4 Demand Replacement
25345 | SAP Upgrade
25346 | iHUB Upgrade
25350 | Wilson TS - ID35810 1385 Harmony Rd N - Gen Set

## Lookup-ForecastAccomplishment (hidden)
AIPCode_Activity | AR_Activity | CODE_1 | CODE | CODE_2 | NAME_3 | Total
AIP000387AC | 17393AC | AIP000387 | 17393 | AC | AC Transfer Scheme | 2
AIP000387BRHV | 17393BRHV | AIP000387 | 17393 | BRHV | Breakers (HV) | 20
AIP000387DC | 17393DC | AIP000387 | 17393 | DC | DC Transfer Scheme | 2
AIP000387HVIT | 17393HVIT | AIP000387 | 17393 | HVIT | HVITs | 45
AIP000387PR | 17393PR | AIP000387 | 17393 | PR | Protections | 38
AIP000387SWAB | 17393SWAB | AIP000387 | 17393 | SWAB | Switches (HV) | 56
AIP000388AC-DESN | 21825AC-DESN | AIP000388 | 21825 | AC-DESN | DESN | 1
AIP000388BRLV-13.8kV | 21825BRLV-13.8kV | AIP000388 | 21825 | BRLV-13.8kV | 13.8kV | 6
AIP000388SA-115kV | 21825SA-115kV | AIP000388 | 21825 | SA-115kV | 115kV | 9
AIP000388SA-13.8kV | 21825SA-13.8kV | AIP000388 | 21825 | SA-13.8kV | 13.8kV | 18
AIP000388SPILL | 21825SPILL | AIP000388 | 21825 | SPILL | Spill Containment | 4
AIP000388SS-DESN | 21825SS-DESN | AIP000388 | 21825 | SS-DESN | DESN | 1
AIP000388SWAB-115kV | 21825SWAB-115kV | AIP000388 | 21825 | SWAB-115kV | 115kV | 3
AIP000388TF-S115-F(110-14-14kV) - 100MVA | 21825TF-S115-F(110-14-14kV) - 100MVA | AIP000388 | 21825 | TF-S115-F(110-14-14kV) - 100MVA | S115-F(110-14-14kV) - 100MVA | 3
AIP000390AC | 20619AC | AIP000390 | 20619 | AC | AC Transfer Scheme | 1
AIP000390BRHV | 20619BRHV | AIP000390 | 20619 | BRHV | Breakers (HV) | 17
AIP000390CHARGER | 20619CHARGER | AIP000390 | 20619 | CHARGER | Charger | 2
AIP000390DC | 20619DC | AIP000390 | 20619 | DC | DC Transfer Scheme | 1
AIP000390DCBATTERY | 20619DCBATTERY | AIP000390 | 20619 | DCBATTERY | Battery | 2
AIP000390HVIT | 20619HVIT | AIP000390 | 20619 | HVIT | HVITs | 48
AIP000390PR | 20619PR | AIP000390 | 20619 | PR | Protections | 64
AIP000390RTU | 20619RTU | AIP000390 | 20619 | RTU | RTU | 1
AIP000390SWAB | 20619SWAB | AIP000390 | 20619 | SWAB | Switches (HV) | 42
AIP000392BRLV-13.8kV | 20154BRLV-13.8kV | AIP000392 | 20154 | BRLV-13.8kV | 13.8kV | 4
AIP000392PR | 20154PR | AIP000392 | 20154 | PR | Protections | 4
AIP000394BRLV-13.8kV | 20598BRLV-13.8kV | AIP000394 | 20598 | BRLV-13.8kV | 13.8kV | 23
AIP000394PR | 20598PR | AIP000394 | 20598 | PR | Protections | 35
AIP000394SS-DESN | 20598SS-DESN | AIP000394 | 20598 | SS-DESN | DESN | 1
AIP000395BRLV | 21868BRLV | AIP000395 | 21868 | BRLV | Breakers (LV) | 9
AIP000395CHARGER | 21868CHARGER | AIP000395 | 21868 | CHARGER | Charger | 1
AIP000395DCBATTERY | 21868DCBATTERY | AIP000395 | 21868 | DCBATTERY | Battery | 1
AIP000395MVGIS | 21868MVGIS | AIP000395 | 21868 | MVGIS | MVGIS (Buses) | 2
AIP000395PCT | 21868PCT | AIP000395 | 21868 | PCT | PCT Box | 1
AIP000395PR | 21868PR | AIP000395 | 21868 | PR | Protections | 17
AIP000395RTU | 21868RTU | AIP000395 | 21868 | RTU | RTU | 1
AIP000395SA | 21868SA | AIP000395 | 21868 | SA | Surge Arrestor | 12
AIP000395SPILL | 21868SPILL | AIP000395 | 21868 | SPILL | Spill Containment | 2
AIP000395SWAB | 21868SWAB | AIP000395 | 21868 | SWAB | Switches (HV) | 3
AIP000395TF | 21868TF | AIP000395 | 21868 | TF | Transformers | 2
AIP000404BRLV-13.8kV | 21807BRLV-13.8kV | AIP000404 | 21807 | BRLV-13.8kV | 13.8kV | 4
AIP000404PR | 21807PR | AIP000404 | 21807 | PR | Protections | 4
AIP000408BRHV | 22247BRHV | AIP000408 | 22247 | BRHV | Breakers (HV) | 4
AIP000408HVIT | 22247HVIT | AIP000408 | 22247 | HVIT | HVITs | 3
AIP000408PCT | 22247PCT | AIP000408 | 22247 | PCT | PCT Box | 1
AIP000408PR | 22247PR | AIP000408 | 22247 | PR | Protections | 19
AIP000408RTU | 22247RTU | AIP000408 | 22247 | RTU | RTU | 1
AIP000408SA | 22247SA | AIP000408 | 22247 | SA | Surge Arrestor | 12
AIP000408SPILL | 22247SPILL | AIP000408 | 22247 | SPILL | Spill Containment | 2
AIP000408SWAB | 22247SWAB | AIP000408 | 22247 | SWAB | Switches (HV) | 2
AIP000408TF | 22247TF | AIP000408 | 22247 | TF | Transformers | 2
AIP000412AC | 20658AC | AIP000412 | 20658 | AC | AC Transfer Scheme | 2
AIP000412BRHV-230kV | 20658BRHV-230kV | AIP000412 | 20658 | BRHV-230kV | 230kV | 17
AIP000412BRHV-500kV | 20658BRHV-500kV | AIP000412 | 20658 | BRHV-500kV | 500kV | 6
AIP000412BRLV-27.6kV | 20658BRLV-27.6kV | AIP000412 | 20658 | BRLV-27.6kV | 27.6kV | 2
AIP000412DC | 20658DC | AIP000412 | 20658 | DC | DC Transfer Scheme | 2
AIP000412HVIT-230kV | 20658HVIT-230kV | AIP000412 | 20658 | HVIT-230kV | 230kV | 3
AIP000412HVIT-500kV | 20658HVIT-500kV | AIP000412 | 20658 | HVIT-500kV | 500kV | 24
AIP000412PR | 20658PR | AIP000412 | 20658 | PR | Protections | 37
AIP000412RE-27.6kV | 20658RE-27.6kV | AIP000412 | 20658 | RE-27.6kV | 27.6kV | 1
AIP000412SWAB-500kV | 20658SWAB-500kV | AIP000412 | 20658 | SWAB-500kV | 500kV | 18
AIP000412TF-AUTO S500-A(500-240kV) - 750MVA | 20658TF-AUTO S500-A(500-240kV) - 750MVA | AIP000412 | 20658 | TF-AUTO S500-A(500-240kV) - 750MVA | AUTO S500-A(500-240kV) - 750MVA | 1
AIP000413HVIT-115kV | 23447HVIT-115kV | AIP000413 | 23447 | HVIT-115kV | 115kV | 6
AIP000413MVGIS-27.6kV | 23447MVGIS-27.6kV | AIP000413 | 23447 | MVGIS-27.6kV | 27.6kV | 4
AIP000413PR | 23447PR | AIP000413 | 23447 | PR | Protections | 40
AIP000413SA-115kV | 23447SA-115kV | AIP000413 | 23447 | SA-115kV | 115kV | 12
AIP000413SA-27.6kV | 23447SA-27.6kV | AIP000413 | 23447 | SA-27.6kV | 27.6kV | 12
AIP000413SPILL | 23447SPILL | AIP000413 | 23447 | SPILL | Spill Containment | 4
AIP000413SWAB-115kV | 23447SWAB-115kV | AIP000413 | 23447 | SWAB-115kV | 115kV | 5
AIP000413TF-S115-E(110-28kV) - 83MVA | 23447TF-S115-E(110-28kV) - 83MVA | AIP000413 | 23447 | TF-S115-E(110-28kV) - 83MVA | S115-E(110-28kV) - 83MVA | 4
AIP000414AC-DESN | 20607AC-DESN | AIP000414 | 20607 | AC-DESN | DESN | 2
AIP000414BRLV-13.8kV | 20607BRLV-13.8kV | AIP000414 | 20607 | BRLV-13.8kV | 13.8kV | 14
AIP000414CHARGER-125V | 20607CHARGER-125V | AIP000414 | 20607 | CHARGER-125V | 125V | 1
AIP000414DCBATTERY-125V | 20607DCBATTERY-125V | AIP000414 | 20607 | DCBATTERY-125V | 125V | 1
AIP000414PR | 20607PR | AIP000414 | 20607 | PR | Protections | 59
AIP000414SPILL | 20607SPILL | AIP000414 | 20607 | SPILL | Spill Containment | 2
AIP000414SWAB-115kV | 20607SWAB-115kV | AIP000414 | 20607 | SWAB-115kV | 115kV | 8
AIP000414TF-S115-F(110-14-14kV) - 100MVA | 20607TF-S115-F(110-14-14kV) - 100MVA | AIP000414 | 20607 | TF-S115-F(110-14-14kV) - 100MVA | S115-F(110-14-14kV) - 100MVA | 2
AIP000416BRLV-13.8kV | 22335BRLV-13.8kV | AIP000416 | 22335 | BRLV-13.8kV | 13.8kV | 22
AIP000416PR | 22335PR | AIP000416 | 22335 | PR | Protections | 30
AIP000416SS-DESN | 22335SS-DESN | AIP000416 | 22335 | SS-DESN | DESN | 2
AIP000416TF-S115-D(110-14-14kV) - 75MVA | 22335TF-S115-D(110-14-14kV) - 75MVA | AIP000416 | 22335 | TF-S115-D(110-14-14kV) - 75MVA | S115-D(110-14-14kV) - 75MVA | 1
AIP000417BRLV | 21670BRLV | AIP000417 | 21670 | BRLV | Breakers (LV) | 6
AIP000417HVIT | 21670HVIT | AIP000417 | 21670 | HVIT | HVITs | 3
AIP000417PR | 21670PR | AIP000417 | 21670 | PR | Protections | 9
AIP000417SA | 21670SA | AIP000417 | 21670 | SA | Surge Arrestor | 6
AIP000417SPILL | 21670SPILL | AIP000417 | 21670 | SPILL | Spill Containment | 1
AIP000417SWAB | 21670SWAB | AIP000417 | 21670 | SWAB | Switches (HV) | 1
AIP000417TF | 21670TF | AIP000417 | 21670 | TF | Transformers | 1
AIP000420BRLV-13.8kV | 21809BRLV-13.8kV | AIP000420 | 21809 | BRLV-13.8kV | 13.8kV | 8
AIP000420PR | 21809PR | AIP000420 | 21809 | PR | Protections | 8
AIP000421BRHV-115kV | 20621BRHV-115kV | AIP000421 | 20621 | BRHV-115kV | 115kV | 20
AIP000421BRLV-13.8kV | 20621BRLV-13.8kV | AIP000421 | 20621 | BRLV-13.8kV | 13.8kV | 14
AIP000421PR | 20621PR | AIP000421 | 20621 | PR | Protections | 100
AIP000421TF-S115-F(110-14-14kV) - 100MVA | 20621TF-S115-F(110-14-14kV) - 100MVA | AIP000421 | 20621 | TF-S115-F(110-14-14kV) - 100MVA | S115-F(110-14-14kV) - 100MVA | 6
AIP000422BRLV-13.8kV | 23376BRLV-13.8kV | AIP000422 | 23376 | BRLV-13.8kV | 13.8kV | 15
AIP000422PCT | 23376PCT | AIP000422 | 23376 | PCT | PCT Box | 1
AIP000422SA | 23376SA | AIP000422 | 23376 | SA | Surge Arrestor | 9
AIP000422SWAB-115kV | 23376SWAB-115kV | AIP000422 | 23376 | SWAB-115kV | 115kV | 1
AIP000422TF-S115-F(110-14-14kV) - 100MVA | 23376TF-S115-F(110-14-14kV) - 100MVA | AIP000422 | 23376 | TF-S115-F(110-14-14kV) - 100MVA | S115-F(110-14-14kV) - 100MVA | 1
AIP000423PR | 17192PR | AIP000423 | 17192 | PR | Protections | 4
AIP000423SA-115kV | 17192SA-115kV | AIP000423 | 17192 | SA-115kV | 115kV | 6
AIP000423SA-27.6kV | 17192SA-27.6kV | AIP000423 | 17192 | SA-27.6kV | 27.6kV | 6
AIP000423TF-S115-E(110-28kV) - 83MVA | 17192TF-S115-E(110-28kV) - 83MVA | AIP000423 | 17192 | TF-S115-E(110-28kV) - 83MVA | S115-E(110-28kV) - 83MVA | 2
AIP000425AC-BULK | 20625AC-BULK | AIP000425 | 20625 | AC-BULK | BULK | 1
AIP000425CHARGER-125V | 20625CHARGER-125V | AIP000425 | 20625 | CHARGER-125V | 125V | 1
AIP000425DC | 20625DC | AIP000425 | 20625 | DC | DC Transfer Scheme | 1
AIP000425DCBATTERY-125V | 20625DCBATTERY-125V | AIP000425 | 20625 | DCBATTERY-125V | 125V | 1
AIP000425MVGIS-27.6kV | 20625MVGIS-27.6kV | AIP000425 | 20625 | MVGIS-27.6kV | 27.6kV | 2
AIP000425PR | 20625PR | AIP000425 | 20625 | PR | Protections | 25
AIP000425SS-BULK | 20625SS-BULK | AIP000425 | 20625 | SS-BULK | BULK | 3
AIP000426AC | 23341AC | AIP000426 | 23341 | AC | AC Transfer Scheme | 1
AIP000426BRHV | 23341BRHV | AIP000426 | 23341 | BRHV | Breakers (HV) | 16
AIP000426PR | 23341PR | AIP000426 | 23341 | PR | Protections | 72
AIP000426SWAB | 23341SWAB | AIP000426 | 23341 | SWAB | Switches (HV) | 44
AIP000426TFSSGT | 23341TFSSGT | AIP000426 | 23341 | TFSSGT | SS Transformers | 2
AIP000427AC | 20584AC | AIP000427 | 20584 | AC | AC Transfer Scheme | 1
AIP000427BRLV | 20584BRLV | AIP000427 | 20584 | BRLV | Breakers (LV) | 13
AIP000427CHARGER | 20584CHARGER | AIP000427 | 20584 | CHARGER | Charger | 1
AIP000427DC | 20584DC | AIP000427 | 20584 | DC | DC Transfer Scheme | 1
AIP000427DCBATTERY | 20584DCBATTERY | AIP000427 | 20584 | DCBATTERY | Battery | 1
AIP000427HVIT | 20584HVIT | AIP000427 | 20584 | HVIT | HVITs | 6
AIP000427MVGIS | 20584MVGIS | AIP000427 | 20584 | MVGIS | MVGIS (Buses) | 2
AIP000427PCT | 20584PCT | AIP000427 | 20584 | PCT | PCT Box | 1
AIP000427PR | 20584PR | AIP000427 | 20584 | PR | Protections | 19
AIP000427RTU | 20584RTU | AIP000427 | 20584 | RTU | RTU | 1
AIP000427SPILL | 20584SPILL | AIP000427 | 20584 | SPILL | Spill Containment | 2
AIP000427SWAB | 20584SWAB | AIP000427 | 20584 | SWAB | Switches (HV) | 4
AIP000427TF | 20584TF | AIP000427 | 20584 | TF | Transformers | 2
AIP000427TFSSGT | 20584TFSSGT | AIP000427 | 20584 | TFSSGT | SS Transformers | 2
AIP000429AC | 20670AC | AIP000429 | 20670 | AC | AC Transfer Scheme | 1
AIP000429BRHV-230kV | 20670BRHV-230kV | AIP000429 | 20670 | BRHV-230kV | 230kV | 29
AIP000429BRHV-500kV | 20670BRHV-500kV | AIP000429 | 20670 | BRHV-500kV | 500kV | 2
AIP000429CHARGER-250V | 20670CHARGER-250V | AIP000429 | 20670 | CHARGER-250V | 250V | 4
AIP000429CHARGER-48V | 20670CHARGER-48V | AIP000429 | 20670 | CHARGER-48V | 48V | 6
AIP000429DCBATTERY-250V | 20670DCBATTERY-250V | AIP000429 | 20670 | DCBATTERY-250V | 250V | 4
AIP000429HVIT-230kV | 20670HVIT-230kV | AIP000429 | 20670 | HVIT-230kV | 230kV | 33
AIP000429PR | 20670PR | AIP000429 | 20670 | PR | Protections | 86
AIP000429RTU | 20670RTU | AIP000429 | 20670 | RTU | RTU | 1
AIP000429SA-230kV | 20670SA-230kV | AIP000429 | 20670 | SA-230kV | 230kV | 18
AIP000429SA-27.6kV | 20670SA-27.6kV | AIP000429 | 20670 | SA-27.6kV | 27.6kV | 6
AIP000429SA-500kV | 20670SA-500kV | AIP000429 | 20670 | SA-500kV | 500kV | 6
AIP000429SWAB-230kV | 20670SWAB-230kV | AIP000429 | 20670 | SWAB-230kV | 230kV | 84
AIP000429SWAB-500kV | 20670SWAB-500kV | AIP000429 | 20670 | SWAB-500kV | 500kV | 14
AIP000431AC | 20574AC | AIP000431 | 20574 | AC | AC Transfer Scheme | 1
AIP000431BRLV | 20574BRLV | AIP000431 | 20574 | BRLV | Breakers (LV) | 15
AIP000431CHARGER | 20574CHARGER | AIP000431 | 20574 | CHARGER | Charger | 1
AIP000431DC | 20574DC | AIP000431 | 20574 | DC | DC Transfer Scheme | 1
AIP000431DCBATTERY | 20574DCBATTERY | AIP000431 | 20574 | DCBATTERY | Battery | 1
AIP000431HVIT | 20574HVIT | AIP000431 | 20574 | HVIT | HVITs | 3
AIP000431PR | 20574PR | AIP000431 | 20574 | PR | Protections | 26
AIP000431SA | 20574SA | AIP000431 | 20574 | SA | Surge Arrestor | 18
AIP000431SPILL | 20574SPILL | AIP000431 | 20574 | SPILL | Spill Containment | 2
AIP000431SWAB | 20574SWAB | AIP000431 | 20574 | SWAB | Switches (HV) | 4
AIP000431TF | 20574TF | AIP000431 | 20574 | TF | Transformers | 2
AIP000433AC | 22319AC | AIP000433 | 22319 | AC | AC Transfer Scheme | 1
AIP000433CHARGER | 22319CHARGER | AIP000433 | 22319 | CHARGER | Charger | 1
AIP000433DCBATTERY | 22319DCBATTERY | AIP000433 | 22319 | DCBATTERY | Battery | 1
AIP000433HVIT | 22319HVIT | AIP000433 | 22319 | HVIT | HVITs | 6
AIP000433PR | 22319PR | AIP000433 | 22319 | PR | Protections | 26
AIP000433SA | 22319SA | AIP000433 | 22319 | SA | Surge Arrestor | 18
AIP000433SPILL | 22319SPILL | AIP000433 | 22319 | SPILL | Spill Containment | 2
AIP000433SWAB | 22319SWAB | AIP000433 | 22319 | SWAB | Switches (HV) | 6
AIP000433SWCS | 22319SWCS | AIP000433 | 22319 | SWCS | Switches - Circuit Switchers (HV) | 2
AIP000433TF | 22319TF | AIP000433 | 22319 | TF | Transformers | 2
AIP000433TFSSGT | 22319TFSSGT | AIP000433 | 22319 | TFSSGT | SS Transformers | 2
AIP000437AC | 20636AC | AIP000437 | 20636 | AC | AC Transfer Scheme | 1
AIP000437BRHV-115kV | 20636BRHV-115kV | AIP000437 | 20636 | BRHV-115kV | 115kV | 2
AIP000437BRLV-27.6kV | 20636BRLV-27.6kV | AIP000437 | 20636 | BRLV-27.6kV | 27.6kV | 9
AIP000437DC | 20636DC | AIP000437 | 20636 | DC | DC Transfer Scheme | 1
AIP000437DCBATTERY-125V | 20636DCBATTERY-125V | AIP000437 | 20636 | DCBATTERY-125V | 125V | 2
AIP000437HVIT-115kV | 20636HVIT-115kV | AIP000437 | 20636 | HVIT-115kV | 115kV | 9
AIP000437PCT | 20636PCT | AIP000437 | 20636 | PCT | PCT Box | 1
AIP000437PR | 20636PR | AIP000437 | 20636 | PR | Protections | 10
AIP000437SA-115kV | 20636SA-115kV | AIP000437 | 20636 | SA-115kV | 115kV | 6
AIP000437SA-27.6kV | 20636SA-27.6kV | AIP000437 | 20636 | SA-27.6kV | 27.6kV | 6
AIP000437SS-BULK | 20636SS-BULK | AIP000437 | 20636 | SS-BULK | BULK | 2
AIP000438BRHV | 20638BRHV | AIP000438 | 20638 | BRHV | Breakers (HV) | 27
AIP000438HVIT | 20638HVIT | AIP000438 | 20638 | HVIT | HVITs | 21
AIP000438PR | 20638PR | AIP000438 | 20638 | PR | Protections | 107
AIP000438SWAB | 20638SWAB | AIP000438 | 20638 | SWAB | Switches (HV) | 73
AIP000441HVIT-230kV | 20667HVIT-230kV | AIP000441 | 20667 | HVIT-230kV | 230kV | 1
AIP000441MVGIS-27.6kV | 20667MVGIS-27.6kV | AIP000441 | 20667 | MVGIS-27.6kV | 27.6kV | 2
AIP000441PCT | 20667PCT | AIP000441 | 20667 | PCT | PCT Box | 1
AIP000441PR | 20667PR | AIP000441 | 20667 | PR | Protections | 30
AIP000441SA-230kV | 20667SA-230kV | AIP000441 | 20667 | SA-230kV | 230kV | 6
AIP000441SA-27.6kV | 20667SA-27.6kV | AIP000441 | 20667 | SA-27.6kV | 27.6kV | 12
AIP000441SPILL | 20667SPILL | AIP000441 | 20667 | SPILL | Spill Containment | 2
AIP000441SS-DESN | 20667SS-DESN | AIP000441 | 20667 | SS-DESN | DESN | 1
AIP000441SWAB-230kV | 20667SWAB-230kV | AIP000441 | 20667 | SWAB-230kV | 230kV | 2
AIP000441TF-S230-A(215-28kV) - 83MVA | 20667TF-S230-A(215-28kV) - 83MVA | AIP000441 | 20667 | TF-S230-A(215-28kV) - 83MVA | S230-A(215-28kV) - 83MVA | 2
AIP000443BRLV-13.8kV | 20153BRLV-13.8kV | AIP000443 | 20153 | BRLV-13.8kV | 13.8kV | 4
AIP000443PR | 20153PR | AIP000443 | 20153 | PR | Protections | 4
AIP000444BRLV | 20147BRLV | AIP000444 | 20147 | BRLV | Breakers (LV) | 4
AIP000444PR | 20147PR | AIP000444 | 20147 | PR | Protections | 4
AIP000445AC | 22420AC | AIP000445 | 22420 | AC | AC Transfer Scheme | 1
AIP000445BRLV | 22420BRLV | AIP000445 | 22420 | BRLV | Breakers (LV) | 7
AIP000445CHARGER | 22420CHARGER | AIP000445 | 22420 | CHARGER | Charger | 1
AIP000445DC | 22420DC | AIP000445 | 22420 | DC | DC Transfer Scheme | 1
AIP000445DCBATTERY | 22420DCBATTERY | AIP000445 | 22420 | DCBATTERY | Battery | 1
AIP000445PCT | 22420PCT | AIP000445 | 22420 | PCT | PCT Box | 1
AIP000445PR | 22420PR | AIP000445 | 22420 | PR | Protections | 17
AIP000445SA | 22420SA | AIP000445 | 22420 | SA | Surge Arrestor | 3
AIP000445SPILL | 22420SPILL | AIP000445 | 22420 | SPILL | Spill Containment | 2
AIP000445TF | 22420TF | AIP000445 | 22420 | TF | Transformers | 1
AIP000450BRLV | 20152BRLV | AIP000450 | 20152 | BRLV | Breakers (LV) | 6
AIP000450PR | 20152PR | AIP000450 | 20152 | PR | Protections | 5
AIP005007AC | 22965AC | AIP005007 | 22965 | AC | AC Transfer Scheme | 1
AIP005007PR | 22965PR | AIP005007 | 22965 | PR | Protections | 8
AIP005007SA | 22965SA | AIP005007 | 22965 | SA | Surge Arrestor | 18
AIP005007SPILL | 22965SPILL | AIP005007 | 22965 | SPILL | Spill Containment | 2
AIP005007SWAB | 22965SWAB | AIP005007 | 22965 | SWAB | Switches (HV) | 2
AIP005007TF | 22965TF | AIP005007 | 22965 | TF | Transformers | 2
AIP005007TFSSGT | 22965TFSSGT | AIP005007 | 22965 | TFSSGT | SS Transformers | 1
AIP005009AC | 22949AC | AIP005009 | 22949 | AC | AC Transfer Scheme | 1
AIP005009BRLV | 22949BRLV | AIP005009 | 22949 | BRLV | Breakers (LV) | 8
AIP005009CHARGER | 22949CHARGER | AIP005009 | 22949 | CHARGER | Charger | 1
AIP005009DC | 22949DC | AIP005009 | 22949 | DC | DC Transfer Scheme | 1
AIP005009DCBATTERY | 22949DCBATTERY | AIP005009 | 22949 | DCBATTERY | Battery | 1
AIP005009HVIT | 22949HVIT | AIP005009 | 22949 | HVIT | HVITs | 6
AIP005009MVGIS | 22949MVGIS | AIP005009 | 22949 | MVGIS | MVGIS (Buses) | 2
AIP005009PR | 22949PR | AIP005009 | 22949 | PR | Protections | 15
AIP005009RTU | 22949RTU | AIP005009 | 22949 | RTU | RTU | 1
AIP005009SA | 22949SA | AIP005009 | 22949 | SA | Surge Arrestor | 12
AIP005009SC | 22949SC | AIP005009 | 22949 | SC | Capacitor Banks | 1
AIP005009SPILL | 22949SPILL | AIP005009 | 22949 | SPILL | Spill Containment | 2
AIP005009SWAB | 22949SWAB | AIP005009 | 22949 | SWAB | Switches (HV) | 2
AIP005009TF | 22949TF | AIP005009 | 22949 | TF | Transformers | 2
AIP005009TFSSGT | 22949TFSSGT | AIP005009 | 22949 | TFSSGT | SS Transformers | 2
AIP005011BRHV-230kV | 22958BRHV-230kV | AIP005011 | 22958 | BRHV-230kV | 230kV | 4
AIP005011BRLV-13.8kV | 22958BRLV-13.8kV | AIP005011 | 22958 | BRLV-13.8kV | 13.8kV | 22
AIP005011PR | 22958PR | AIP005011 | 22958 | PR | Protections | 8
AIP005011SWAB-230kV | 22958SWAB-230kV | AIP005011 | 22958 | SWAB-230kV | 230kV | 12
AIP005011TF-AUTO S230-B(239-121kV) - 250MVA | 22958TF-AUTO S230-B(239-121kV) - 250MVA | AIP005011 | 22958 | TF-AUTO S230-B(239-121kV) - 250MVA | AUTO S230-B(239-121kV) - 250MVA | 2
AIP005011TF-S230-C(215-14-14kV) - 100MVA | 22958TF-S230-C(215-14-14kV) - 100MVA | AIP005011 | 22958 | TF-S230-C(215-14-14kV) - 100MVA | S230-C(215-14-14kV) - 100MVA | 1
AIP005012BRHV-115kV | 22957BRHV-115kV | AIP005012 | 22957 | BRHV-115kV | 115kV | 1
AIP005012BRHV-230kV | 22957BRHV-230kV | AIP005012 | 22957 | BRHV-230kV | 230kV | 1
AIP005012BRLV-27.6kV | 22957BRLV-27.6kV | AIP005012 | 22957 | BRLV-27.6kV | 27.6kV | 2
AIP005012PR | 22957PR | AIP005012 | 22957 | PR | Protections | 24
AIP005012SA-115kV | 22957SA-115kV | AIP005012 | 22957 | SA-115kV | 115kV | 6
AIP005012SA-230kV | 22957SA-230kV | AIP005012 | 22957 | SA-230kV | 230kV | 6
AIP005012SWAB-230kV | 22957SWAB-230kV | AIP005012 | 22957 | SWAB-230kV | 230kV | 12
AIP005012TF-AUTO S230-B(239-121kV) - 250MVA | 22957TF-AUTO S230-B(239-121kV) - 250MVA | AIP005012 | 22957 | TF-AUTO S230-B(239-121kV) - 250MVA | AUTO S230-B(239-121kV) - 250MVA | 2
AIP005013AC-BULK | 22955AC-BULK | AIP005013 | 22955 | AC-BULK | BULK | 1
AIP005013BRHV-115kV | 22955BRHV-115kV | AIP005013 | 22955 | BRHV-115kV | 115kV | 6
AIP005013BRHV-230kV | 22955BRHV-230kV | AIP005013 | 22955 | BRHV-230kV | 230kV | 2
AIP005013BRLV-27.6kV | 22955BRLV-27.6kV | AIP005013 | 22955 | BRLV-27.6kV | 27.6kV | 13
AIP005013CHARGER | 22955CHARGER | AIP005013 | 22955 | CHARGER | Charger | 1
AIP005013HVIT-115kV | 22955HVIT-115kV | AIP005013 | 22955 | HVIT-115kV | 115kV | 41
AIP005013PR | 22955PR | AIP005013 | 22955 | PR | Protections | 67
AIP005013SPILL | 22955SPILL | AIP005013 | 22955 | SPILL | Spill Containment | 2
AIP005013SS-BULK | 22955SS-BULK | AIP005013 | 22955 | SS-BULK | BULK | 3
AIP005013SWAB-115kV | 22955SWAB-115kV | AIP005013 | 22955 | SWAB-115kV | 115kV | 18
AIP005013SWAB-230kV | 22955SWAB-230kV | AIP005013 | 22955 | SWAB-230kV | 230kV | 20
AIP005014CHARGER | 22959CHARGER | AIP005014 | 22959 | CHARGER | Charger | 1
AIP005014DC | 22959DC | AIP005014 | 22959 | DC | DC Transfer Scheme | 1
AIP005014DCBATTERY | 22959DCBATTERY | AIP005014 | 22959 | DCBATTERY | Battery | 1
AIP005014RTU | 22959RTU | AIP005014 | 22959 | RTU | RTU | 1
AIP005014SA | 22959SA | AIP005014 | 22959 | SA | Surge Arrestor | 18
AIP005015BRLV-27.6kV | 22961BRLV-27.6kV | AIP005015 | 22961 | BRLV-27.6kV | 27.6kV | 5
AIP005015PR | 22961PR | AIP005015 | 22961 | PR | Protections | 23
AIP005015RTU-DESN | 22961RTU-DESN | AIP005015 | 22961 | RTU-DESN | DESN | 7
AIP005016BRLV-13.8kV | 22963BRLV-13.8kV | AIP005016 | 22963 | BRLV-13.8kV | 13.8kV | 22
AIP005016CHARGER-125V | 22963CHARGER-125V | AIP005016 | 22963 | CHARGER-125V | 125V | 1
AIP005016PR | 22963PR | AIP005016 | 22963 | PR | Protections | 27
AIP005016SWAB-115kV | 22963SWAB-115kV | AIP005016 | 22963 | SWAB-115kV | 115kV | 8
AIP005019BRLV-44kV | 22948BRLV-44kV | AIP005019 | 22948 | BRLV-44kV | 44kV | 8
AIP005019SA-44kV | 22948SA-44kV | AIP005019 | 22948 | SA-44kV | 44kV | 6
AIP005019SC-44kV | 22948SC-44kV | AIP005019 | 22948 | SC-44kV | 44kV | 2
AIP005019SWAB-115kV | 22948SWAB-115kV | AIP005019 | 22948 | SWAB-115kV | 115kV | 6
AIP005019TF-115kV | 22948TF-115kV | AIP005019 | 22948 | TF-115kV | 115kV (Non-Standard) | 2
AIP005078BRHV | 21861BRHV | AIP005078 | 21861 | BRHV | Breakers (HV) | 3
AIP005078PR | 21861PR | AIP005078 | 21861 | PR | Protections | 34
AIP005078SWAB | 21861SWAB | AIP005078 | 21861 | SWAB | Switches (HV) | 1
AIP005078TF | 21861TF | AIP005078 | 21861 | TF | Transformers | 2
AIP005079BRLV | 22810BRLV | AIP005079 | 22810 | BRLV | Breakers (LV) | 2
AIP005079CHARGER | 22810CHARGER | AIP005079 | 22810 | CHARGER | Charger | 2
AIP005079DCBATTERY | 22810DCBATTERY | AIP005079 | 22810 | DCBATTERY | Battery | 2
AIP005079HVIT | 22810HVIT | AIP005079 | 22810 | HVIT | HVITs | 6
AIP005079PCT | 22810PCT | AIP005079 | 22810 | PCT | PCT Box | 2
AIP005079PR | 22810PR | AIP005079 | 22810 | PR | Protections | 57
AIP005079SA | 22810SA | AIP005079 | 22810 | SA | Surge Arrestor | 12
AIP005079SWAB | 22810SWAB | AIP005079 | 22810 | SWAB | Switches (HV) | 2
AIP005081CHARGER | 22953CHARGER | AIP005081 | 22953 | CHARGER | Charger | 2
AIP005081DCBATTERY | 22953DCBATTERY | AIP005081 | 22953 | DCBATTERY | Battery | 2
AIP005081PR | 22953PR | AIP005081 | 22953 | PR | Protections | 90
AIP005081SA | 22953SA | AIP005081 | 22953 | SA | Surge Arrestor | 9
AIP005081SPILL | 22953SPILL | AIP005081 | 22953 | SPILL | Spill Containment | 4
AIP005081SWAB | 22953SWAB | AIP005081 | 22953 | SWAB | Switches (HV) | 6
AIP005081TF | 22953TF | AIP005081 | 22953 | TF | Transformers | 1
AIP005083BRHV | 22970BRHV | AIP005083 | 22970 | BRHV | Breakers (HV) | 5
AIP005083BRLV | 22970BRLV | AIP005083 | 22970 | BRLV | Breakers (LV) | 5
AIP005083HVIT | 22970HVIT | AIP005083 | 22970 | HVIT | HVITs | 8
AIP005083PR | 22970PR | AIP005083 | 22970 | PR | Protections | 34
AIP005083SA | 22970SA | AIP005083 | 22970 | SA | Surge Arrestor | 12
AIP005083SPILL | 22970SPILL | AIP005083 | 22970 | SPILL | Spill Containment | 4
AIP005083SWAB | 22970SWAB | AIP005083 | 22970 | SWAB | Switches (HV) | 12
AIP005083TF | 22970TF | AIP005083 | 22970 | TF | Transformers | 2
AIP005084AC | 22971AC | AIP005084 | 22971 | AC | AC Transfer Scheme | 2
AIP005084BRLV | 22971BRLV | AIP005084 | 22971 | BRLV | Breakers (LV) | 2
AIP005084CHARGER | 22971CHARGER | AIP005084 | 22971 | CHARGER | Charger | 1
AIP005084DC | 22971DC | AIP005084 | 22971 | DC | DC Transfer Scheme | 1
AIP005084DCBATTERY | 22971DCBATTERY | AIP005084 | 22971 | DCBATTERY | Battery | 1
AIP005084PR | 22971PR | AIP005084 | 22971 | PR | Protections | 23
AIP005084SWAB | 22971SWAB | AIP005084 | 22971 | SWAB | Switches (HV) | 3
AIP005084TFSSGT | 22971TFSSGT | AIP005084 | 22971 | TFSSGT | SS Transformers | 1
AIP005086AC | 22973AC | AIP005086 | 22973 | AC | AC Transfer Scheme | 1
AIP005086BRHV | 22973BRHV | AIP005086 | 22973 | BRHV | Breakers (HV) | 4
AIP005086BRLV | 22973BRLV | AIP005086 | 22973 | BRLV | Breakers (LV) | 6
AIP005086CHARGER | 22973CHARGER | AIP005086 | 22973 | CHARGER | Charger | 2
AIP005086DC | 22973DC | AIP005086 | 22973 | DC | DC Transfer Scheme | 1
AIP005086DCBATTERY | 22973DCBATTERY | AIP005086 | 22973 | DCBATTERY | Battery | 2
AIP005086HVIT | 22973HVIT | AIP005086 | 22973 | HVIT | HVITs | 12
AIP005086PR | 22973PR | AIP005086 | 22973 | PR | Protections | 30
AIP005086RTU | 22973RTU | AIP005086 | 22973 | RTU | RTU | 1
AIP005086SA | 22973SA | AIP005086 | 22973 | SA | Surge Arrestor | 12
AIP005086SWAB | 22973SWAB | AIP005086 | 22973 | SWAB | Switches (HV) | 2
AIP005086TF | 22973TF | AIP005086 | 22973 | TF | Transformers | 2
AIP005086TFSSGT | 22973TFSSGT | AIP005086 | 22973 | TFSSGT | SS Transformers | 2
AIP005107BRHV | 23020BRHV | AIP005107 | 23020 | BRHV | Breakers (HV) | 8
AIP005107CHARGER | 23020CHARGER | AIP005107 | 23020 | CHARGER | Charger | 2
AIP005107DCBATTERY | 23020DCBATTERY | AIP005107 | 23020 | DCBATTERY | Battery | 2
AIP005107HVIT | 23020HVIT | AIP005107 | 23020 | HVIT | HVITs | 21
AIP005107PR | 23020PR | AIP005107 | 23020 | PR | Protections | 51
AIP005107SA | 23020SA | AIP005107 | 23020 | SA | Surge Arrestor | 18
AIP005107SPILL | 23020SPILL | AIP005107 | 23020 | SPILL | Spill Containment | 2
AIP005107SWAB | 23020SWAB | AIP005107 | 23020 | SWAB | Switches (HV) | 34
AIP005107TF | 23020TF | AIP005107 | 23020 | TF | Transformers | 2
AIP005108AC | 23290AC | AIP005108 | 23290 | AC | AC Transfer Scheme | 1
AIP005108BRLV | 23290BRLV | AIP005108 | 23290 | BRLV | Breakers (LV) | 9
AIP005108CHARGER | 23290CHARGER | AIP005108 | 23290 | CHARGER | Charger | 1
AIP005108DC | 23290DC | AIP005108 | 23290 | DC | DC Transfer Scheme | 1
AIP005108DCBATTERY | 23290DCBATTERY | AIP005108 | 23290 | DCBATTERY | Battery | 1
AIP005108HVIT | 23290HVIT | AIP005108 | 23290 | HVIT | HVITs | 3
AIP005108PCT | 23290PCT | AIP005108 | 23290 | PCT | PCT Box | 1
AIP005108PR | 23290PR | AIP005108 | 23290 | PR | Protections | 19
AIP005108RTU | 23290RTU | AIP005108 | 23290 | RTU | RTU | 1
AIP005108SA | 23290SA | AIP005108 | 23290 | SA | Surge Arrestor | 12
AIP005108SPILL | 23290SPILL | AIP005108 | 23290 | SPILL | Spill Containment | 2
AIP005108SWAB | 23290SWAB | AIP005108 | 23290 | SWAB | Switches (HV) | 2
AIP005108TF | 23290TF | AIP005108 | 23290 | TF | Transformers | 2
AIP005108TFSSGT | 23290TFSSGT | AIP005108 | 23290 | TFSSGT | SS Transformers | 2
AIP005109AC | 23239AC | AIP005109 | 23239 | AC | AC Transfer Scheme | 1
AIP005109BRLV | 23239BRLV | AIP005109 | 23239 | BRLV | Breakers (LV) | 8
AIP005109CHARGER | 23239CHARGER | AIP005109 | 23239 | CHARGER | Charger | 2
AIP005109DC | 23239DC | AIP005109 | 23239 | DC | DC Transfer Scheme | 1
AIP005109DCBATTERY | 23239DCBATTERY | AIP005109 | 23239 | DCBATTERY | Battery | 2
AIP005109PCT | 23239PCT | AIP005109 | 23239 | PCT | PCT Box | 1
AIP005109PR | 23239PR | AIP005109 | 23239 | PR | Protections | 24
AIP005109RTU | 23239RTU | AIP005109 | 23239 | RTU | RTU | 1
AIP005109SA | 23239SA | AIP005109 | 23239 | SA | Surge Arrestor | 18
AIP005109SC | 23239SC | AIP005109 | 23239 | SC | Capacitor Banks | 2
AIP005109SPILL | 23239SPILL | AIP005109 | 23239 | SPILL | Spill Containment | 2
AIP005109SWAB | 23239SWAB | AIP005109 | 23239 | SWAB | Switches (HV) | 2
AIP005109TF | 23239TF | AIP005109 | 23239 | TF | Transformers | 2
AIP005109TFSSGT | 23239TFSSGT | AIP005109 | 23239 | TFSSGT | SS Transformers | 2
AIP005110BRHV | 22328BRHV | AIP005110 | 22328 | BRHV | Breakers (HV) | 2
AIP005110PR | 22328PR | AIP005110 | 22328 | PR | Protections | 14
AIP005110SA | 22328SA | AIP005110 | 22328 | SA | Surge Arrestor | 18
AIP005110SPILL | 22328SPILL | AIP005110 | 22328 | SPILL | Spill Containment | 2
AIP005110SWAB | 22328SWAB | AIP005110 | 22328 | SWAB | Switches (HV) | 9
AIP005110TF | 22328TF | AIP005110 | 22328 | TF | Transformers | 2
AIP005111AC-DESN | 23364AC-DESN | AIP005111 | 23364 | AC-DESN | DESN | 1
AIP005111BRHV-115kV | 23364BRHV-115kV | AIP005111 | 23364 | BRHV-115kV | 115kV | 5
AIP005111BRLV-13.8kV | 23364BRLV-13.8kV | AIP005111 | 23364 | BRLV-13.8kV | 13.8kV | 12
AIP005111CHARGER-125V | 23364CHARGER-125V | AIP005111 | 23364 | CHARGER-125V | 125V | 1
AIP005111DC | 23364DC | AIP005111 | 23364 | DC | DC Transfer Scheme | 1
AIP005111DCBATTERY-125V | 23364DCBATTERY-125V | AIP005111 | 23364 | DCBATTERY-125V | 125V | 1
AIP005111PR | 23364PR | AIP005111 | 23364 | PR | Protections | 27
AIP005111SWAB-115kV | 23364SWAB-115kV | AIP005111 | 23364 | SWAB-115kV | 115kV | 16
AIP005111TF-S115-D(110-14-14kV) - 75MVA | 23364TF-S115-D(110-14-14kV) - 75MVA | AIP005111 | 23364 | TF-S115-D(110-14-14kV) - 75MVA | S115-D(110-14-14kV) - 75MVA | 2
AIP005112PR | 23444PR | AIP005112 | 23444 | PR | Protections | 10
AIP005112SWAB-115kV | 23444SWAB-115kV | AIP005112 | 23444 | SWAB-115kV | 115kV | 2
AIP005112TF-S115-F(110-14-14kV) - 100MVA | 23444TF-S115-F(110-14-14kV) - 100MVA | AIP005112 | 23444 | TF-S115-F(110-14-14kV) - 100MVA | S115-F(110-14-14kV) - 100MVA | 3
AIP005116HVIT-115kV | 23377HVIT-115kV | AIP005116 | 23377 | HVIT-115kV | 115kV | 6
AIP005116SA-115kV | 23377SA-115kV | AIP005116 | 23377 | SA-115kV | 115kV | 12
AIP005116SA-13.8kV | 23377SA-13.8kV | AIP005116 | 23377 | SA-13.8kV | 13.8kV | 12
AIP005116SPILL | 23377SPILL | AIP005116 | 23377 | SPILL | Spill Containment | 2
AIP005116SWAB-115kV | 23377SWAB-115kV | AIP005116 | 23377 | SWAB-115kV | 115kV | 2
AIP005116TF-S115-F(110-14-14kV) - 100MVA | 23377TF-S115-F(110-14-14kV) - 100MVA | AIP005116 | 23377 | TF-S115-F(110-14-14kV) - 100MVA | S115-F(110-14-14kV) - 100MVA | 2
AIP005120DCBATTERY-250V | 23445DCBATTERY-250V | AIP005120 | 23445 | DCBATTERY-250V | 250V | 2
AIP005120PR | 23445PR | AIP005120 | 23445 | PR | Protections | 8
AIP005120TF-S115-F(110-14-14kV) - 100MVA | 23445TF-S115-F(110-14-14kV) - 100MVA | AIP005120 | 23445 | TF-S115-F(110-14-14kV) - 100MVA | S115-F(110-14-14kV) - 100MVA | 1
AIP005122AC | 23360AC | AIP005122 | 23360 | AC | AC Transfer Scheme | 1
AIP005122BRLV | 23360BRLV | AIP005122 | 23360 | BRLV | Breakers (LV) | 22
AIP005122CHARGER | 23360CHARGER | AIP005122 | 23360 | CHARGER | Charger | 1
AIP005122DC | 23360DC | AIP005122 | 23360 | DC | DC Transfer Scheme | 1
AIP005122DCBATTERY | 23360DCBATTERY | AIP005122 | 23360 | DCBATTERY | Battery | 1
AIP005122HVIT | 23360HVIT | AIP005122 | 23360 | HVIT | HVITs | 6
AIP005122MVGIS | 23360MVGIS | AIP005122 | 23360 | MVGIS | MVGIS (Buses) | 4
AIP005122PCT | 23360PCT | AIP005122 | 23360 | PCT | PCT Box | 1
AIP005122PR | 23360PR | AIP005122 | 23360 | PR | Protections | 34
AIP005122RTU | 23360RTU | AIP005122 | 23360 | RTU | RTU | 1
AIP005122SA | 23360SA | AIP005122 | 23360 | SA | Surge Arrestor | 18
AIP005122SPILL | 23360SPILL | AIP005122 | 23360 | SPILL | Spill Containment | 2
AIP005122SWAB | 23360SWAB | AIP005122 | 23360 | SWAB | Switches (HV) | 2
AIP005122TF | 23360TF | AIP005122 | 23360 | TF | Transformers | 2
AIP005122TFSSGT | 23360TFSSGT | AIP005122 | 23360 | TFSSGT | SS Transformers | 2
AIP005123BRLV-27.6kV | 23443BRLV-27.6kV | AIP005123 | 23443 | BRLV-27.6kV | 27.6kV | 7
AIP005123CHARGER-125V | 23443CHARGER-125V | AIP005123 | 23443 | CHARGER-125V | 125V | 1
AIP005123DCBATTERY-125V | 23443DCBATTERY-125V | AIP005123 | 23443 | DCBATTERY-125V | 125V | 1
AIP005123PR | 23443PR | AIP005123 | 23443 | PR | Protections | 11
AIP005123RTU | 23443RTU | AIP005123 | 23443 | RTU | RTU | 1
AIP005123SA-230kV | 23443SA-230kV | AIP005123 | 23443 | SA-230kV | 230kV | 6
AIP005123SA-27.6kV | 23443SA-27.6kV | AIP005123 | 23443 | SA-27.6kV | 27.6kV | 12
AIP005123SPILL | 23443SPILL | AIP005123 | 23443 | SPILL | Spill Containment | 2
AIP005123SS-DESN | 23443SS-DESN | AIP005123 | 23443 | SS-DESN | DESN | 1
AIP005123SWAB-230kV | 23443SWAB-230kV | AIP005123 | 23443 | SWAB-230kV | 230kV | 2
AIP005123TF-S230-D(215-28-28kV) - 125MVA | 23443TF-S230-D(215-28-28kV) - 125MVA | AIP005123 | 23443 | TF-S230-D(215-28-28kV) - 125MVA | S230-D(215-28-28kV) - 125MVA | 2
AIP005127AC-DESN | 23423AC-DESN | AIP005127 | 23423 | AC-DESN | DESN | 1
AIP005127DCBATTERY-125V | 23423DCBATTERY-125V | AIP005127 | 23423 | DCBATTERY-125V | 125V | 1
AIP005127PR | 23423PR | AIP005127 | 23423 | PR | Protections | 22
AIP005127SWAB-230kV | 23423SWAB-230kV | AIP005127 | 23423 | SWAB-230kV | 230kV | 2
AIP005128BRHV | 23241BRHV | AIP005128 | 23241 | BRHV | Breakers (HV) | 2
AIP005128PR | 23241PR | AIP005128 | 23241 | PR | Protections | 39
AIP005128SC | 23241SC | AIP005128 | 23241 | SC | Capacitor Banks | 2
AIP005128SWAB | 23241SWAB | AIP005128 | 23241 | SWAB | Switches (HV) | 5
AIP005138AC-BULK | 23405AC-BULK | AIP005138 | 23405 | AC-BULK | BULK | 1
AIP005138BRHV-115kV | 23405BRHV-115kV | AIP005138 | 23405 | BRHV-115kV | 115kV | 5
AIP005138DC | 23405DC | AIP005138 | 23405 | DC | DC Transfer Scheme | 1
AIP005138PR | 23405PR | AIP005138 | 23405 | PR | Protections | 18
AIP005138RTU-BULK | 23405RTU-BULK | AIP005138 | 23405 | RTU-BULK | BULK | 1
AIP005138SS-BULK | 23405SS-BULK | AIP005138 | 23405 | SS-BULK | BULK | 2
AIP005138SWAB-115kV | 23405SWAB-115kV | AIP005138 | 23405 | SWAB-115kV | 115kV | 3
AIP005144AC | 23394AC | AIP005144 | 23394 | AC | AC Transfer Scheme | 1
AIP005144BRHV | 23394BRHV | AIP005144 | 23394 | BRHV | Breakers (HV) | 6
AIP005144CHARGER | 23394CHARGER | AIP005144 | 23394 | CHARGER | Charger | 2
AIP005144DC | 23394DC | AIP005144 | 23394 | DC | DC Transfer Scheme | 1
AIP005144DCBATTERY | 23394DCBATTERY | AIP005144 | 23394 | DCBATTERY | Battery | 2
AIP005144HVIT | 23394HVIT | AIP005144 | 23394 | HVIT | HVITs | 10
AIP005144PCT | 23394PCT | AIP005144 | 23394 | PCT | PCT Box | 1
AIP005144PR | 23394PR | AIP005144 | 23394 | PR | Protections | 36
AIP005144SA | 23394SA | AIP005144 | 23394 | SA | Surge Arrestor | 6
AIP005144SWAB | 23394SWAB | AIP005144 | 23394 | SWAB | Switches (HV) | 7
AIP005144TFSSGT | 23394TFSSGT | AIP005144 | 23394 | TFSSGT | SS Transformers | 6
AIP005145BRLV-27.6kV | 23425BRLV-27.6kV | AIP005145 | 23425 | BRLV-27.6kV | 27.6kV | 3
AIP005145CHARGER-125V | 23425CHARGER-125V | AIP005145 | 23425 | CHARGER-125V | 125V | 1
AIP005145DCBATTERY-125V | 23425DCBATTERY-125V | AIP005145 | 23425 | DCBATTERY-125V | 125V | 1
AIP005145PR | 23425PR | AIP005145 | 23425 | PR | Protections | 21
AIP005145SWAB-230kV | 23425SWAB-230kV | AIP005145 | 23425 | SWAB-230kV | 230kV | 2
AIP005145TF-S230-A(215-28kV) - 83MVA | 23425TF-S230-A(215-28kV) - 83MVA | AIP005145 | 23425 | TF-S230-A(215-28kV) - 83MVA | S230-A(215-28kV) - 83MVA | 2
AIP005146AC | 23417AC | AIP005146 | 23417 | AC | AC Transfer Scheme | 1
AIP005146BRHV | 23417BRHV | AIP005146 | 23417 | BRHV | Breakers (HV) | 5
AIP005146BRLV | 23417BRLV | AIP005146 | 23417 | BRLV | Breakers (LV) | 11
AIP005146CHARGER | 23417CHARGER | AIP005146 | 23417 | CHARGER | Charger | 1
AIP005146DC | 23417DC | AIP005146 | 23417 | DC | DC Transfer Scheme | 1
AIP005146DCBATTERY | 23417DCBATTERY | AIP005146 | 23417 | DCBATTERY | Battery | 1
AIP005146PCT | 23417PCT | AIP005146 | 23417 | PCT | PCT Box | 1
AIP005146PR | 23417PR | AIP005146 | 23417 | PR | Protections | 65
AIP005146RTU | 23417RTU | AIP005146 | 23417 | RTU | RTU | 1
AIP005146SA | 23417SA | AIP005146 | 23417 | SA | Surge Arrestor | 22
AIP005146SPILL | 23417SPILL | AIP005146 | 23417 | SPILL | Spill Containment | 2
AIP005146SWAB | 23417SWAB | AIP005146 | 23417 | SWAB | Switches (HV) | 11
AIP005146TF | 23417TF | AIP005146 | 23417 | TF | Transformers | 2
AIP005146TFSSGT | 23417TFSSGT | AIP005146 | 23417 | TFSSGT | SS Transformers | 2
AIP005147DCBATTERY | 23248DCBATTERY | AIP005147 | 23248 | DCBATTERY | Battery | 2
AIP005147PR | 23248PR | AIP005147 | 23248 | PR | Protections | 98
AIP005147SA | 23248SA | AIP005147 | 23248 | SA | Surge Arrestor | 12
AIP005147SPILL | 23248SPILL | AIP005147 | 23248 | SPILL | Spill Containment | 9
AIP005147SWAB | 23248SWAB | AIP005147 | 23248 | SWAB | Switches (HV) | 1
AIP005149AC | 17148AC | AIP005149 | 17148 | AC | AC Transfer Scheme | 1
AIP005149BRLV | 17148BRLV | AIP005149 | 17148 | BRLV | Breakers (LV) | 39
AIP005149CHARGER | 17148CHARGER | AIP005149 | 17148 | CHARGER | Charger | 1
AIP005149DC | 17148DC | AIP005149 | 17148 | DC | DC Transfer Scheme | 1
AIP005149DCBATTERY | 17148DCBATTERY | AIP005149 | 17148 | DCBATTERY | Battery | 1
AIP005149MVGIS | 17148MVGIS | AIP005149 | 17148 | MVGIS | MVGIS (Buses) | 8
AIP005149PR | 17148PR | AIP005149 | 17148 | PR | Protections | 59
AIP005149RTU | 17148RTU | AIP005149 | 17148 | RTU | RTU | 1
AIP005149SA | 17148SA | AIP005149 | 17148 | SA | Surge Arrestor | 18
AIP005149SC | 17148SC | AIP005149 | 17148 | SC | Capacitor Banks | 1
AIP005149SPILL | 17148SPILL | AIP005149 | 17148 | SPILL | Spill Containment | 2
AIP005149SWAB | 17148SWAB | AIP005149 | 17148 | SWAB | Switches (HV) | 2
AIP005149TF | 17148TF | AIP005149 | 17148 | TF | Transformers | 2
AIP005149TFSSGT | 17148TFSSGT | AIP005149 | 17148 | TFSSGT | SS Transformers | 2
AIP005157AC | 23414AC | AIP005157 | 23414 | AC | AC Transfer Scheme | 1
AIP005157SA | 23414SA | AIP005157 | 23414 | SA | Surge Arrestor | 3
AIP005165BRHV-500kV | 23451BRHV-500kV | AIP005165 | 23451 | BRHV-500kV | 500kV | 10
AIP005165HVIT-500kV | 23451HVIT-500kV | AIP005165 | 23451 | HVIT-500kV | 500kV | 8
AIP005165PCT | 23451PCT | AIP005165 | 23451 | PCT | PCT Box | 1
AIP005165SWAB-500kV | 23451SWAB-500kV | AIP005165 | 23451 | SWAB-500kV | 500kV | 28
AIP005166AC-DESN | 23433AC-DESN | AIP005166 | 23433 | AC-DESN | DESN | 1
AIP005166BRLV-27.6kV | 23433BRLV-27.6kV | AIP005166 | 23433 | BRLV-27.6kV | 27.6kV | 2
AIP005166SA-27.6kV | 23433SA-27.6kV | AIP005166 | 23433 | SA-27.6kV | 27.6kV | 6
AIP005168BRHV | 23170BRHV | AIP005168 | 23170 | BRHV | Breakers (HV) | 3
AIP005168HVIT | 23170HVIT | AIP005168 | 23170 | HVIT | HVITs | 3
AIP005168PR | 23170PR | AIP005168 | 23170 | PR | Protections | 14
AIP005168SA | 23170SA | AIP005168 | 23170 | SA | Surge Arrestor | 12
AIP005168SWAB | 23170SWAB | AIP005168 | 23170 | SWAB | Switches (HV) | 8
AIP005169BRLV-27.6kV | 23422BRLV-27.6kV | AIP005169 | 23422 | BRLV-27.6kV | 27.6kV | 5
AIP005169DCBATTERY-48V | 23422DCBATTERY-48V | AIP005169 | 23422 | DCBATTERY-48V | 48V | 2
AIP005169PR | 23422PR | AIP005169 | 23422 | PR | Protections | 17
AIP005169SS-DESN | 23422SS-DESN | AIP005169 | 23422 | SS-DESN | DESN | 2
AIP005169SWAB-115kV | 23422SWAB-115kV | AIP005169 | 23422 | SWAB-115kV | 115kV | 5
AIP005169TF-S230-D(215-28-28kV) - 125MVA | 23422TF-S230-D(215-28-28kV) - 125MVA | AIP005169 | 23422 | TF-S230-D(215-28-28kV) - 125MVA | S230-D(215-28-28kV) - 125MVA | 2
AIP005170DCBATTERY-125V | 23419DCBATTERY-125V | AIP005170 | 23419 | DCBATTERY-125V | 125V | 1
AIP005170PR | 23419PR | AIP005170 | 23419 | PR | Protections | 25
AIP005170RTU | 23419RTU | AIP005170 | 23419 | RTU | RTU | 1
AIP005170SPILL | 23419SPILL | AIP005170 | 23419 | SPILL | Spill Containment | 2
AIP005172BRLV-27.6kV | 23432BRLV-27.6kV | AIP005172 | 23432 | BRLV-27.6kV | 27.6kV | 7
AIP005172PR | 23432PR | AIP005172 | 23432 | PR | Protections | 27
AIP005172RTU | 23432RTU | AIP005172 | 23432 | RTU | RTU | 1
AIP005172SS-DESN | 23432SS-DESN | AIP005172 | 23432 | SS-DESN | DESN | 2
AIP005173CHARGER-125V | 23411CHARGER-125V | AIP005173 | 23411 | CHARGER-125V | 125V | 1
AIP005173PR | 23411PR | AIP005173 | 23411 | PR | Protections | 10
AIP005173RTU-DESN | 23411RTU-DESN | AIP005173 | 23411 | RTU-DESN | DESN | 1
AIP005174BRLV-27.6kV | 23420BRLV-27.6kV | AIP005174 | 23420 | BRLV-27.6kV | 27.6kV | 4
AIP005174DCBATTERY-125V | 23420DCBATTERY-125V | AIP005174 | 23420 | DCBATTERY-125V | 125V | 4
AIP005174PR | 23420PR | AIP005174 | 23420 | PR | Protections | 22
AIP005174SWAB-230kV | 23420SWAB-230kV | AIP005174 | 23420 | SWAB-230kV | 230kV | 4
AIP005174TF-S230-A(215-28kV) - 83MVA | 23420TF-S230-A(215-28kV) - 83MVA | AIP005174 | 23420 | TF-S230-A(215-28kV) - 83MVA | S230-A(215-28kV) - 83MVA | 1
AIP005181BRLV-27.6kV | 23439BRLV-27.6kV | AIP005181 | 23439 | BRLV-27.6kV | 27.6kV | 14
AIP005181CHARGER-125V | 23439CHARGER-125V | AIP005181 | 23439 | CHARGER-125V | 125V | 1
AIP005181PR | 23439PR | AIP005181 | 23439 | PR | Protections | 69
AIP005181SA-230kV | 23439SA-230kV | AIP005181 | 23439 | SA-230kV | 230kV | 6
AIP005181SA-27.6kV | 23439SA-27.6kV | AIP005181 | 23439 | SA-27.6kV | 27.6kV | 12
AIP005182BRHV-115kV | 23410BRHV-115kV | AIP005182 | 23410 | BRHV-115kV | 115kV | 2
AIP005182HVIT-115kV | 23410HVIT-115kV | AIP005182 | 23410 | HVIT-115kV | 115kV | 6
AIP005182PR | 23410PR | AIP005182 | 23410 | PR | Protections | 26
AIP005182SA-115kV | 23410SA-115kV | AIP005182 | 23410 | SA-115kV | 115kV | 6
AIP005182SA-13.8kV | 23410SA-13.8kV | AIP005182 | 23410 | SA-13.8kV | 13.8kV | 6
AIP005182SA-230kV | 23410SA-230kV | AIP005182 | 23410 | SA-230kV | 230kV | 6
AIP005182SWAB-115kV | 23410SWAB-115kV | AIP005182 | 23410 | SWAB-115kV | 115kV | 2
AIP005182SWAB-230kV | 23410SWAB-230kV | AIP005182 | 23410 | SWAB-230kV | 230kV | 2
AIP005182TF-AUTO S230-A(239-121kV) - 125MVA | 23410TF-AUTO S230-A(239-121kV) - 125MVA | AIP005182 | 23410 | TF-AUTO S230-A(239-121kV) - 125MVA | AUTO S230-A(239-121kV) - 125MVA | 2
AIP005184BRLV-44kV | 24827BRLV-44kV | AIP005184 | 24827 | BRLV-44kV | 44kV | 4
AIP005184CHARGER-48V | 24827CHARGER-48V | AIP005184 | 24827 | CHARGER-48V | 48V | 2
AIP005184DCBATTERY-48V | 24827DCBATTERY-48V | AIP005184 | 24827 | DCBATTERY-48V | 48V | 2
AIP005189PR | 23413PR | AIP005189 | 23413 | PR | Protections | 34
AIP005190AC-BULK | 23406AC-BULK | AIP005190 | 23406 | AC-BULK | BULK | 1
AIP005190BRHV-230kV | 23406BRHV-230kV | AIP005190 | 23406 | BRHV-230kV | 230kV | 5
AIP005190DC | 23406DC | AIP005190 | 23406 | DC | DC Transfer Scheme | 1
AIP005190HVIT-230kV | 23406HVIT-230kV | AIP005190 | 23406 | HVIT-230kV | 230kV | 9
AIP005190PR | 23406PR | AIP005190 | 23406 | PR | Protections | 33
AIP005190SS-BULK | 23406SS-BULK | AIP005190 | 23406 | SS-BULK | BULK | 2
AIP005190SWAB-115kV | 23406SWAB-115kV | AIP005190 | 23406 | SWAB-115kV | 115kV | 1
AIP005190SWAB-230kV | 23406SWAB-230kV | AIP005190 | 23406 | SWAB-230kV | 230kV | 2
AIP005192AC | 23412AC | AIP005192 | 23412 | AC | AC Transfer Scheme | 1
AIP005192BRLV | 23412BRLV | AIP005192 | 23412 | BRLV | Breakers (LV) | 2
AIP005192CHARGER | 23412CHARGER | AIP005192 | 23412 | CHARGER | Charger | 1
AIP005192DC | 23412DC | AIP005192 | 23412 | DC | DC Transfer Scheme | 1
AIP005192DCBATTERY | 23412DCBATTERY | AIP005192 | 23412 | DCBATTERY | Battery | 1
AIP005192PR | 23412PR | AIP005192 | 23412 | PR | Protections | 2
AIP005194AC-DESN | 23450AC-DESN | AIP005194 | 23450 | AC-DESN | DESN | 1
AIP005194BRLV-13.8kV | 23450BRLV-13.8kV | AIP005194 | 23450 | BRLV-13.8kV | 13.8kV | 3
AIP005194DCBATTERY-125V | 23450DCBATTERY-125V | AIP005194 | 23450 | DCBATTERY-125V | 125V | 1
AIP005194PR | 23450PR | AIP005194 | 23450 | PR | Protections | 65
AIP005195BRLV-44kV | 23786BRLV-44kV | AIP005195 | 23786 | BRLV-44kV | 44kV | 2
AIP005195DCBATTERY-125V | 23786DCBATTERY-125V | AIP005195 | 23786 | DCBATTERY-125V | 125V | 1
AIP005195PR | 23786PR | AIP005195 | 23786 | PR | Protections | 5
AIP005195SS-DESN | 23786SS-DESN | AIP005195 | 23786 | SS-DESN | DESN | 2
AIP005195SWAB-115kV | 23786SWAB-115kV | AIP005195 | 23786 | SWAB-115kV | 115kV | 4
AIP005197BRLV-27.6kV | 23421BRLV-27.6kV | AIP005197 | 23421 | BRLV-27.6kV | 27.6kV | 2
AIP005197DC | 23421DC | AIP005197 | 23421 | DC | DC Transfer Scheme | 1
AIP005197SA-115kV | 23421SA-115kV | AIP005197 | 23421 | SA-115kV | 115kV | 6
AIP005197SA-230kV | 23421SA-230kV | AIP005197 | 23421 | SA-230kV | 230kV | 18
AIP005197SPILL | 23421SPILL | AIP005197 | 23421 | SPILL | Spill Containment | 4
AIP005197SS-DESN | 23421SS-DESN | AIP005197 | 23421 | SS-DESN | DESN | 1
AIP005197SWAB-115kV | 23421SWAB-115kV | AIP005197 | 23421 | SWAB-115kV | 115kV | 5
AIP005197SWAB-230kV | 23421SWAB-230kV | AIP005197 | 23421 | SWAB-230kV | 230kV | 4
AIP005197TF-AUTO S230-B(239-121kV) - 250MVA | 23421TF-AUTO S230-B(239-121kV) - 250MVA | AIP005197 | 23421 | TF-AUTO S230-B(239-121kV) - 250MVA | AUTO S230-B(239-121kV) - 250MVA | 2
AIP005197TF-S115-B(110-28kV) - 42MVA | 23421TF-S115-B(110-28kV) - 42MVA | AIP005197 | 23421 | TF-S115-B(110-28kV) - 42MVA | S115-B(110-28kV) - 42MVA | 2
AIP005198AC-BULK | 24828AC-BULK | AIP005198 | 24828 | AC-BULK | BULK | 1
AIP005198CHARGER-250V | 24828CHARGER-250V | AIP005198 | 24828 | CHARGER-250V | 250V | 1
AIP005198CHARGER-48V | 24828CHARGER-48V | AIP005198 | 24828 | CHARGER-48V | 48V | 2
AIP005198DC | 24828DC | AIP005198 | 24828 | DC | DC Transfer Scheme | 1
AIP005198DCBATTERY-48V | 24828DCBATTERY-48V | AIP005198 | 24828 | DCBATTERY-48V | 48V | 4
AIP005198HVIT-500kV | 24828HVIT-500kV | AIP005198 | 24828 | HVIT-500kV | 500kV | 15
AIP005198PR | 24828PR | AIP005198 | 24828 | PR | Protections | 12
AIP005198SA-500kV | 24828SA-500kV | AIP005198 | 24828 | SA-500kV | 500kV | 18
AIP005198SS-BULK | 24828SS-BULK | AIP005198 | 24828 | SS-BULK | BULK | 1
AIP005200AC-BULK | 23379AC-BULK | AIP005200 | 23379 | AC-BULK | BULK | 1
AIP005200PR | 23379PR | AIP005200 | 23379 | PR | Protections | 9
AIP005200RTU-DESN | 23379RTU-DESN | AIP005200 | 23379 | RTU-DESN | DESN | 1
AIP005200SA-230kV | 23379SA-230kV | AIP005200 | 23379 | SA-230kV | 230kV | 6
AIP005200SA-44kV | 23379SA-44kV | AIP005200 | 23379 | SA-44kV | 44kV | 6
AIP005200SPILL | 23379SPILL | AIP005200 | 23379 | SPILL | Spill Containment | 2
AIP005200SS-BULK | 23379SS-BULK | AIP005200 | 23379 | SS-BULK | BULK | 1
AIP005200TF-S230-B(215-44kV) - 83MVA | 23379TF-S230-B(215-44kV) - 83MVA | AIP005200 | 23379 | TF-S230-B(215-44kV) - 83MVA | S230-B(215-44kV) - 83MVA | 2
AIP005201AC | 23415AC | AIP005201 | 23415 | AC | AC Transfer Scheme | 1
AIP005201BRHV | 23415BRHV | AIP005201 | 23415 | BRHV | Breakers (HV) | 10
AIP005201DCBATTERY | 23415DCBATTERY | AIP005201 | 23415 | DCBATTERY | Battery | 2
AIP005201HVIT | 23415HVIT | AIP005201 | 23415 | HVIT | HVITs | 14
AIP005201PR | 23415PR | AIP005201 | 23415 | PR | Protections | 37
AIP005201RTU | 23415RTU | AIP005201 | 23415 | RTU | RTU | 1
AIP005201SWAB | 23415SWAB | AIP005201 | 23415 | SWAB | Switches (HV) | 9
AIP005201TFSSGT | 23415TFSSGT | AIP005201 | 23415 | TFSSGT | SS Transformers | 1
AIP005203AC | 24109AC | AIP005203 | 24109 | AC | AC Transfer Scheme | 1
AIP005203BRHV-115kV | 24109BRHV-115kV | AIP005203 | 24109 | BRHV-115kV | 115kV | 8
AIP005203BRHV-230kV | 24109BRHV-230kV | AIP005203 | 24109 | BRHV-230kV | 230kV | 6
AIP005203DCBATTERY-48V | 24109DCBATTERY-48V | AIP005203 | 24109 | DCBATTERY-48V | 48V | 2
AIP005203HVIT-115kV | 24109HVIT-115kV | AIP005203 | 24109 | HVIT-115kV | 115kV | 6
AIP005203PR | 24109PR | AIP005203 | 24109 | PR | Protections | 50
AIP005203SS-BULK | 24109SS-BULK | AIP005203 | 24109 | SS-BULK | BULK | 2
AIP005203SWAB-115kV | 24109SWAB-115kV | AIP005203 | 24109 | SWAB-115kV | 115kV | 6
AIP005203SWAB-230kV | 24109SWAB-230kV | AIP005203 | 24109 | SWAB-230kV | 230kV | 2
AIP005208BRLV-44kV | 23436BRLV-44kV | AIP005208 | 23436 | BRLV-44kV | 44kV | 2
AIP005208PR | 23436PR | AIP005208 | 23436 | PR | Protections | 9
AIP005208SA-230kV | 23436SA-230kV | AIP005208 | 23436 | SA-230kV | 230kV | 12
AIP005208SA-27.6kV | 23436SA-27.6kV | AIP005208 | 23436 | SA-27.6kV | 27.6kV | 6
AIP005208SA-44kV | 23436SA-44kV | AIP005208 | 23436 | SA-44kV | 44kV | 6
AIP005208SPILL | 23436SPILL | AIP005208 | 23436 | SPILL | Spill Containment | 4
AIP005208SWAB-230kV | 23436SWAB-230kV | AIP005208 | 23436 | SWAB-230kV | 230kV | 4
AIP005208TF-S230-A(215-28kV) - 83MVA | 23436TF-S230-A(215-28kV) - 83MVA | AIP005208 | 23436 | TF-S230-A(215-28kV) - 83MVA | S230-A(215-28kV) - 83MVA | 2
AIP005208TF-S230-E(215-44kV) - 125MVA | 23436TF-S230-E(215-44kV) - 125MVA | AIP005208 | 23436 | TF-S230-E(215-44kV) - 125MVA | S230-E(215-44kV) - 125MVA | 2
AIP005210AC | 22480AC | AIP005210 | 22480 | AC | AC Transfer Scheme | 2
AIP005210PCT | 22480PCT | AIP005210 | 22480 | PCT | PCT Box | 1
AIP005210PR | 22480PR | AIP005210 | 22480 | PR | Protections | 23
AIP005210SA | 22480SA | AIP005210 | 22480 | SA | Surge Arrestor | 18
AIP005210SPILL | 22480SPILL | AIP005210 | 22480 | SPILL | Spill Containment | 2
AIP005210SWAB | 22480SWAB | AIP005210 | 22480 | SWAB | Switches (HV) | 2
AIP005210TF | 22480TF | AIP005210 | 22480 | TF | Transformers | 2
AIP005210TFSSGT | 22480TFSSGT | AIP005210 | 22480 | TFSSGT | SS Transformers | 1
AIP005212BRLV-27.6kV | 23446BRLV-27.6kV | AIP005212 | 23446 | BRLV-27.6kV | 27.6kV | 6
AIP005212PR | 23446PR | AIP005212 | 23446 | PR | Protections | 15
AIP005214AC | 23437AC | AIP005214 | 23437 | AC | AC Transfer Scheme | 1
AIP005214BRHV-230kV | 23437BRHV-230kV | AIP005214 | 23437 | BRHV-230kV | 230kV | 12
AIP005214CHARGER-250V | 23437CHARGER-250V | AIP005214 | 23437 | CHARGER-250V | 250V | 3
AIP005214DC | 23437DC | AIP005214 | 23437 | DC | DC Transfer Scheme | 1
AIP005214DCBATTERY-48V | 23437DCBATTERY-48V | AIP005214 | 23437 | DCBATTERY-48V | 48V | 4
AIP005214HVIT-230kV | 23437HVIT-230kV | AIP005214 | 23437 | HVIT-230kV | 230kV | 12
AIP005214PR | 23437PR | AIP005214 | 23437 | PR | Protections | 101
AIP005214SWAB-230kV | 23437SWAB-230kV | AIP005214 | 23437 | SWAB-230kV | 230kV | 24
AIP005225NCSH | 23137NCSH | AIP005225 | 23137 | NCSH | Shieldwire (Km) | 4.2
AIP005225OPGW | 23137OPGW | AIP005225 | 23137 | OPGW | OPGW (Km) | 4.2
AIP005225UGCD | 23137UGCD | AIP005225 | 23137 | UGCD | Underground Conductor (Km) | 4.7
AIP005228BRHV | 23250BRHV | AIP005228 | 23250 | BRHV | Breakers (HV) | 12
AIP005228BRLV | 23250BRLV | AIP005228 | 23250 | BRLV | Breakers (LV) | 2
AIP005228CHARGER | 23250CHARGER | AIP005228 | 23250 | CHARGER | Charger | 1
AIP005228DC | 23250DC | AIP005228 | 23250 | DC | DC Transfer Scheme | 1
AIP005228DCBATTERY | 23250DCBATTERY | AIP005228 | 23250 | DCBATTERY | Battery | 1
AIP005228HVIT | 23250HVIT | AIP005228 | 23250 | HVIT | HVITs | 12
AIP005228PR | 23250PR | AIP005228 | 23250 | PR | Protections | 67
AIP005228RTU | 23250RTU | AIP005228 | 23250 | RTU | RTU | 1
AIP005228SA | 23250SA | AIP005228 | 23250 | SA | Surge Arrestor | 24
AIP005228SC | 23250SC | AIP005228 | 23250 | SC | Capacitor Banks | 2
AIP005228SPILL | 23250SPILL | AIP005228 | 23250 | SPILL | Spill Containment | 3
AIP005228SWAB | 23250SWAB | AIP005228 | 23250 | SWAB | Switches (HV) | 11
AIP005265AC | 21865AC | AIP005265 | 21865 | AC | AC Transfer Scheme | 1
AIP005265BRHV | 21865BRHV | AIP005265 | 21865 | BRHV | Breakers (HV) | 9
AIP005265CHARGER | 21865CHARGER | AIP005265 | 21865 | CHARGER | Charger | 4
AIP005265DC | 21865DC | AIP005265 | 21865 | DC | DC Transfer Scheme | 1
AIP005265HVIT | 21865HVIT | AIP005265 | 21865 | HVIT | HVITs | 12
AIP005265PR | 21865PR | AIP005265 | 21865 | PR | Protections | 66
AIP005265RE | 21865RE | AIP005265 | 21865 | RE | Reactors | 7
AIP005265SA | 21865SA | AIP005265 | 21865 | SA | Surge Arrestor | 6
AIP005265SPILL | 21865SPILL | AIP005265 | 21865 | SPILL | Spill Containment | 3
AIP005265SWAB | 21865SWAB | AIP005265 | 21865 | SWAB | Switches (HV) | 9
AIP005265TFSSGT | 21865TFSSGT | AIP005265 | 21865 | TFSSGT | SS Transformers | 1
AIP005284AC | 23438AC | AIP005284 | 23438 | AC | AC Transfer Scheme | 1
AIP005284PR | 23438PR | AIP005284 | 23438 | PR | Protections | 22
AIP005284RTU | 23438RTU | AIP005284 | 23438 | RTU | RTU | 1
AIP005284TFSSGT | 23438TFSSGT | AIP005284 | 23438 | TFSSGT | SS Transformers | 2
AIP005297BRHV-115kV | 23362BRHV-115kV | AIP005297 | 23362 | BRHV-115kV | 115kV | 2
AIP005297PR | 23362PR | AIP005297 | 23362 | PR | Protections | 17
AIP005297SWAB-115kV | 23362SWAB-115kV | AIP005297 | 23362 | SWAB-115kV | 115kV | 5
AIP005341NCSH | 23466NCSH | AIP005341 | 23466 | NCSH | Shieldwire (Km) | 6.59
AIP005341OHCD | 23466OHCD | AIP005341 | 23466 | OHCD | Overhead Conductor (Km) | 6.59
AIP005341PLCOATING | 23466PLCOATING | AIP005341 | 23466 | PLCOATING | Tower Coating (Structures) | 1
AIP005341PLWD | 23466PLWD | AIP005341 | 23466 | PLWD | Wood Poles (Structures) | 63
AIP005341SWCS-115kV | 23466SWCS-115kV | AIP005341 | 23466 | SWCS-115kV | 115kV | 1
AIP005343IN-115kV | 23724IN-115kV | AIP005343 | 23724 | IN-115kV | 115kV | 700
AIP005343OHCD | 23724OHCD | AIP005343 | 23724 | OHCD | Overhead Conductor (Km) | 77
AIP005343OPGW | 23724OPGW | AIP005343 | 23724 | OPGW | OPGW (Km) | 77
AIP005343PLCOATING | 23724PLCOATING | AIP005343 | 23724 | PLCOATING | Tower Coating (Structures) | 153
AIP005343PLWD | 23724PLWD | AIP005343 | 23724 | PLWD | Wood Poles (Structures) | 60
AIP005343UNSP | 23724UNSP | AIP005343 | 23724 | UNSP | Unspecified - DNU | 58
AIP005362AC | 23661AC | AIP005362 | 23661 | AC | AC Transfer Scheme | 1
AIP005362BRHV-230kV | 23661BRHV-230kV | AIP005362 | 23661 | BRHV-230kV | 230kV | 7
AIP005362DC | 23661DC | AIP005362 | 23661 | DC | DC Transfer Scheme | 1
AIP005362DCBATTERY-250V | 23661DCBATTERY-250V | AIP005362 | 23661 | DCBATTERY-250V | 250V | 2
AIP005362SS-BULK | 23661SS-BULK | AIP005362 | 23661 | SS-BULK | BULK | 2
AIP005362SWAB-230kV | 23661SWAB-230kV | AIP005362 | 23661 | SWAB-230kV | 230kV | 18
AIP005365AC | 23660AC | AIP005365 | 23660 | AC | AC Transfer Scheme | 1
AIP005365BRHV-115kV | 23660BRHV-115kV | AIP005365 | 23660 | BRHV-115kV | 115kV | 5
AIP005365CHARGER-125V | 23660CHARGER-125V | AIP005365 | 23660 | CHARGER-125V | 125V | 1
AIP005365DC | 23660DC | AIP005365 | 23660 | DC | DC Transfer Scheme | 1
AIP005365DCBATTERY-125V | 23660DCBATTERY-125V | AIP005365 | 23660 | DCBATTERY-125V | 125V | 1
AIP005365HVIT-115kV | 23660HVIT-115kV | AIP005365 | 23660 | HVIT-115kV | 115kV | 6
AIP005365HVIT-230kV | 23660HVIT-230kV | AIP005365 | 23660 | HVIT-230kV | 230kV | 3
AIP005365PR | 23660PR | AIP005365 | 23660 | PR | Protections | 44
AIP005365RTU-BULK | 23660RTU-BULK | AIP005365 | 23660 | RTU-BULK | BULK | 1
AIP005365SA-115kV | 23660SA-115kV | AIP005365 | 23660 | SA-115kV | 115kV | 6
AIP005365SA-13.8kV | 23660SA-13.8kV | AIP005365 | 23660 | SA-13.8kV | 13.8kV | 6
AIP005365SA-230kV | 23660SA-230kV | AIP005365 | 23660 | SA-230kV | 230kV | 6
AIP005365SS-BULK | 23660SS-BULK | AIP005365 | 23660 | SS-BULK | BULK | 2
AIP005365SWAB-115kV | 23660SWAB-115kV | AIP005365 | 23660 | SWAB-115kV | 115kV | 5
AIP005365SWAB-230kV | 23660SWAB-230kV | AIP005365 | 23660 | SWAB-230kV | 230kV | 6
AIP005365TF-AUTO S230-B(239-121kV) - 250MVA | 23660TF-AUTO S230-B(239-121kV) - 250MVA | AIP005365 | 23660 | TF-AUTO S230-B(239-121kV) - 250MVA | AUTO S230-B(239-121kV) - 250MVA | 2
AIP005366UGCD | 23646UGCD | AIP005366 | 23646 | UGCD | Underground Conductor (Km) | 7.1
AIP005371IN | 23684IN | AIP005371 | 23684 | IN | Insulators | 120
AIP005371NCSH | 23684NCSH | AIP005371 | 23684 | NCSH | Shieldwire (Km) | 5
AIP005371OHCD | 23684OHCD | AIP005371 | 23684 | OHCD | Overhead Conductor (Km) | 8
AIP005371OPGW | 23684OPGW | AIP005371 | 23684 | OPGW | OPGW (Km) | 3
AIP005371PLCOATING | 23684PLCOATING | AIP005371 | 23684 | PLCOATING | Tower Coating (Structures) | 15
AIP005371PLWD | 23684PLWD | AIP005371 | 23684 | PLWD | Wood Poles (Structures) | 16
AIP005372NCSH | 23582NCSH | AIP005372 | 23582 | NCSH | Shieldwire (Km) | 60
AIP005372OPGW | 23582OPGW | AIP005372 | 23582 | OPGW | OPGW (Km) | 98
AIP005372PLCOATING | 23582PLCOATING | AIP005372 | 23582 | PLCOATING | Tower Coating (Structures) | 282
AIP005372PLST | 23582PLST | AIP005372 | 23582 | PLST | Steel Structures | 183
AIP005372PLWD | 23582PLWD | AIP005372 | 23582 | PLWD | Wood Poles (Structures) | 11
AIP005372SWAB-230kV | 23582SWAB-230kV | AIP005372 | 23582 | SWAB-230kV | 230kV | 2
AIP005372UNSP | 23582UNSP | AIP005372 | 23582 | UNSP | Unspecified - DNU | 282
AIP005391PR | 23647PR | AIP005391 | 23647 | PR | Protections | 12
AIP005391SA-13.8kV | 23647SA-13.8kV | AIP005391 | 23647 | SA-13.8kV | 13.8kV | 6
AIP005391SA-230kV | 23647SA-230kV | AIP005391 | 23647 | SA-230kV | 230kV | 3
AIP005391SPILL | 23647SPILL | AIP005391 | 23647 | SPILL | Spill Containment | 4
AIP005391SWAB-115kV | 23647SWAB-115kV | AIP005391 | 23647 | SWAB-115kV | 115kV | 1
AIP005391TF-S115-F(110-14-14kV) - 100MVA | 23647TF-S115-F(110-14-14kV) - 100MVA | AIP005391 | 23647 | TF-S115-F(110-14-14kV) - 100MVA | S115-F(110-14-14kV) - 100MVA | 1
AIP005413IN | 23696IN | AIP005413 | 23696 | IN | Insulators | 161
AIP005413NCSH | 23696NCSH | AIP005413 | 23696 | NCSH | Shieldwire (Km) | 12
AIP005413OHCD | 23696OHCD | AIP005413 | 23696 | OHCD | Overhead Conductor (Km) | 12
AIP005413PLCOATING | 23696PLCOATING | AIP005413 | 23696 | PLCOATING | Tower Coating (Structures) | 52
AIP005416IN-230kV | 23687IN-230kV | AIP005416 | 23687 | IN-230kV | 230kV | 1045
AIP005416NCSH | 23687NCSH | AIP005416 | 23687 | NCSH | Shieldwire (Km) | 240
AIP005416OHCD | 23687OHCD | AIP005416 | 23687 | OHCD | Overhead Conductor (Km) | 119
AIP005420IN-230kV | 23688IN-230kV | AIP005420 | 23688 | IN-230kV | 230kV | 3080
AIP005420NCSH | 23688NCSH | AIP005420 | 23688 | NCSH | Shieldwire (Km) | 590.3
AIP005420OHCD | 23688OHCD | AIP005420 | 23688 | OHCD | Overhead Conductor (Km) | 295.65
AIP005420PLCOATING | 23688PLCOATING | AIP005420 | 23688 | PLCOATING | Tower Coating (Structures) | 900.88
AIP005422IN | 23685IN | AIP005422 | 23685 | IN | Insulators | 620
AIP005422NCSH | 23685NCSH | AIP005422 | 23685 | NCSH | Shieldwire (Km) | 25
AIP005422OHCD | 23685OHCD | AIP005422 | 23685 | OHCD | Overhead Conductor (Km) | 38
AIP005422PLCOATING | 23685PLCOATING | AIP005422 | 23685 | PLCOATING | Tower Coating (Structures) | 147
AIP005440AC | 23690AC | AIP005440 | 23690 | AC | AC Transfer Scheme | 1
AIP005440BRHV-500kV | 23690BRHV-500kV | AIP005440 | 23690 | BRHV-500kV | 500kV | 8
AIP005440CHARGER-48V | 23690CHARGER-48V | AIP005440 | 23690 | CHARGER-48V | 48V | 2
AIP005440DCBATTERY-48V | 23690DCBATTERY-48V | AIP005440 | 23690 | DCBATTERY-48V | 48V | 2
AIP005440PR | 23690PR | AIP005440 | 23690 | PR | Protections | 18
AIP005440SWAB-500kV | 23690SWAB-500kV | AIP005440 | 23690 | SWAB-500kV | 500kV | 16
AIP005440TFSSGT | 23690TFSSGT | AIP005440 | 23690 | TFSSGT | SS Transformers | 1
AIP005447SA | 23664SA | AIP005447 | 23664 | SA | Surge Arrestor | 12
AIP005447SPILL | 23664SPILL | AIP005447 | 23664 | SPILL | Spill Containment | 2
AIP005456IN | 23682IN | AIP005456 | 23682 | IN | Insulators | 64
AIP005458HVIT-230kV | 23815HVIT-230kV | AIP005458 | 23815 | HVIT-230kV | 230kV | 15
AIP005458PR | 23815PR | AIP005458 | 23815 | PR | Protections | 16
AIP005458SA-230kV | 23815SA-230kV | AIP005458 | 23815 | SA-230kV | 230kV | 6
AIP005458SWAB-230kV | 23815SWAB-230kV | AIP005458 | 23815 | SWAB-230kV | 230kV | 3
AIP005458TF-AUTO S230-B(239-121kV) - 250MVA | 23815TF-AUTO S230-B(239-121kV) - 250MVA | AIP005458 | 23815 | TF-AUTO S230-B(239-121kV) - 250MVA | AUTO S230-B(239-121kV) - 250MVA | 2
AIP005463DCBATTERY-125V | 23816DCBATTERY-125V | AIP005463 | 23816 | DCBATTERY-125V | 125V | 1
AIP005463SS-DESN | 23816SS-DESN | AIP005463 | 23816 | SS-DESN | DESN | 2
AIP005463TF-S115-A(115-14kV) - 42MVA | 23816TF-S115-A(115-14kV) - 42MVA | AIP005463 | 23816 | TF-S115-A(115-14kV) - 42MVA | S115-A(115-14kV) - 42MVA | 2
AIP005465AC-DESN | 23676AC-DESN | AIP005465 | 23676 | AC-DESN | DESN | 1
AIP005465MVGIS-27.6kV | 23676MVGIS-27.6kV | AIP005465 | 23676 | MVGIS-27.6kV | 27.6kV | 2
AIP005465SA-115kV | 23676SA-115kV | AIP005465 | 23676 | SA-115kV | 115kV | 6
AIP005465SA-27.6kV | 23676SA-27.6kV | AIP005465 | 23676 | SA-27.6kV | 27.6kV | 6
AIP005465SWAB-115kV | 23676SWAB-115kV | AIP005465 | 23676 | SWAB-115kV | 115kV | 2
AIP005465TF-S115-E(110-28kV) - 83MVA | 23676TF-S115-E(110-28kV) - 83MVA | AIP005465 | 23676 | TF-S115-E(110-28kV) - 83MVA | S115-E(110-28kV) - 83MVA | 2
AIP005465TFSSGT | 23676TFSSGT | AIP005465 | 23676 | TFSSGT | SS Transformers | 1
AIP005466BRLV-27.6kV | 23677BRLV-27.6kV | AIP005466 | 23677 | BRLV-27.6kV | 27.6kV | 6
AIP005466PCT | 23677PCT | AIP005466 | 23677 | PCT | PCT Box | 1
AIP005466PR | 23677PR | AIP005466 | 23677 | PR | Protections | 35
AIP005466SA-230kV | 23677SA-230kV | AIP005466 | 23677 | SA-230kV | 230kV | 3
AIP005466SA-27.6kV | 23677SA-27.6kV | AIP005466 | 23677 | SA-27.6kV | 27.6kV | 6
AIP005466SPILL | 23677SPILL | AIP005466 | 23677 | SPILL | Spill Containment | 2
AIP005466TF-S230-D(215-28-28kV) - 125MVA | 23677TF-S230-D(215-28-28kV) - 125MVA | AIP005466 | 23677 | TF-S230-D(215-28-28kV) - 125MVA | S230-D(215-28-28kV) - 125MVA | 1
AIP005467BRLV-27.6kV | 23808BRLV-27.6kV | AIP005467 | 23808 | BRLV-27.6kV | 27.6kV | 1
AIP005467HVIT-115kV | 23808HVIT-115kV | AIP005467 | 23808 | HVIT-115kV | 115kV | 6
AIP005467PR | 23808PR | AIP005467 | 23808 | PR | Protections | 5
AIP005467SWAB-115kV | 23808SWAB-115kV | AIP005467 | 23808 | SWAB-115kV | 115kV | 2
AIP005467TF-S115-E(110-28kV) - 83MVA | 23808TF-S115-E(110-28kV) - 83MVA | AIP005467 | 23808 | TF-S115-E(110-28kV) - 83MVA | S115-E(110-28kV) - 83MVA | 2
AIP005468BRLV-44kV | 23817BRLV-44kV | AIP005468 | 23817 | BRLV-44kV | 44kV | 7
AIP005468CHARGER-125V | 23817CHARGER-125V | AIP005468 | 23817 | CHARGER-125V | 125V | 1
AIP005468DCBATTERY-125V | 23817DCBATTERY-125V | AIP005468 | 23817 | DCBATTERY-125V | 125V | 1
AIP005468HVIT-230kV | 23817HVIT-230kV | AIP005468 | 23817 | HVIT-230kV | 230kV | 1
AIP005468PR | 23817PR | AIP005468 | 23817 | PR | Protections | 21
AIP005468TF-S230-B(215-44kV) - 83MVA | 23817TF-S230-B(215-44kV) - 83MVA | AIP005468 | 23817 | TF-S230-B(215-44kV) - 83MVA | S230-B(215-44kV) - 83MVA | 2
AIP005472BRHV-230kV | 23693BRHV-230kV | AIP005472 | 23693 | BRHV-230kV | 230kV | 12
AIP005472BRLV-27.6kV | 23693BRLV-27.6kV | AIP005472 | 23693 | BRLV-27.6kV | 27.6kV | 6
AIP005472PR | 23693PR | AIP005472 | 23693 | PR | Protections | 35
AIP005472SA-115kV | 23693SA-115kV | AIP005472 | 23693 | SA-115kV | 115kV | 6
AIP005472SA-230kV | 23693SA-230kV | AIP005472 | 23693 | SA-230kV | 230kV | 9
AIP005472TF-AUTO S230-B(239-121kV) - 250MVA | 23693TF-AUTO S230-B(239-121kV) - 250MVA | AIP005472 | 23693 | TF-AUTO S230-B(239-121kV) - 250MVA | AUTO S230-B(239-121kV) - 250MVA | 3
AIP005472TF-S230-A(215-28kV) - 83MVA | 23693TF-S230-A(215-28kV) - 83MVA | AIP005472 | 23693 | TF-S230-A(215-28kV) - 83MVA | S230-A(215-28kV) - 83MVA | 1
AIP005476BRLV-27.6kV | 23692BRLV-27.6kV | AIP005476 | 23692 | BRLV-27.6kV | 27.6kV | 6
AIP005476PR | 23692PR | AIP005476 | 23692 | PR | Protections | 34
AIP005476SA-230kV | 23692SA-230kV | AIP005476 | 23692 | SA-230kV | 230kV | 9
AIP005476SPILL | 23692SPILL | AIP005476 | 23692 | SPILL | Spill Containment | 2
AIP005476SS-DESN | 23692SS-DESN | AIP005476 | 23692 | SS-DESN | DESN | 2
AIP005476SWAB-230kV | 23692SWAB-230kV | AIP005476 | 23692 | SWAB-230kV | 230kV | 4
AIP005476TF-S230-A(215-28kV) - 83MVA | 23692TF-S230-A(215-28kV) - 83MVA | AIP005476 | 23692 | TF-S230-A(215-28kV) - 83MVA | S230-A(215-28kV) - 83MVA | 1
AIP005477AC-BULK | 23806AC-BULK | AIP005477 | 23806 | AC-BULK | BULK | 1
AIP005477BRHV-230kV | 23806BRHV-230kV | AIP005477 | 23806 | BRHV-230kV | 230kV | 5
AIP005477DC | 23806DC | AIP005477 | 23806 | DC | DC Transfer Scheme | 1
AIP005477PR | 23806PR | AIP005477 | 23806 | PR | Protections | 18
AIP005477SC-230kV | 23806SC-230kV | AIP005477 | 23806 | SC-230kV | 230kV | 1
AIP005480BRHV-115kV | 23807BRHV-115kV | AIP005480 | 23807 | BRHV-115kV | 115kV | 1
AIP005480CHARGER-250V | 23807CHARGER-250V | AIP005480 | 23807 | CHARGER-250V | 250V | 2
AIP005480CHARGER-48V | 23807CHARGER-48V | AIP005480 | 23807 | CHARGER-48V | 48V | 1
AIP005480DC | 23807DC | AIP005480 | 23807 | DC | DC Transfer Scheme | 1
AIP005480PR | 23807PR | AIP005480 | 23807 | PR | Protections | 23
AIP005480SWAB-115kV | 23807SWAB-115kV | AIP005480 | 23807 | SWAB-115kV | 115kV | 6
AIP005480SWAB-230kV | 23807SWAB-230kV | AIP005480 | 23807 | SWAB-230kV | 230kV | 4
AIP005480TF-AUTO S230-B(239-121kV) - 250MVA | 23807TF-AUTO S230-B(239-121kV) - 250MVA | AIP005480 | 23807 | TF-AUTO S230-B(239-121kV) - 250MVA | AUTO S230-B(239-121kV) - 250MVA | 1
AIP005500AC | 23474AC | AIP005500 | 23474 | AC | AC Transfer Scheme | 1
AIP005500BRLV | 23474BRLV | AIP005500 | 23474 | BRLV | Breakers (LV) | 14
AIP005500CHARGER | 23474CHARGER | AIP005500 | 23474 | CHARGER | Charger | 1
AIP005500DC | 23474DC | AIP005500 | 23474 | DC | DC Transfer Scheme | 1
AIP005500DCBATTERY | 23474DCBATTERY | AIP005500 | 23474 | DCBATTERY | Battery | 1
AIP005500HVIT | 23474HVIT | AIP005500 | 23474 | HVIT | HVITs | 6
AIP005500PCT | 23474PCT | AIP005500 | 23474 | PCT | PCT Box | 1
AIP005500PR | 23474PR | AIP005500 | 23474 | PR | Protections | 24
AIP005500RTU | 23474RTU | AIP005500 | 23474 | RTU | RTU | 1
AIP005500SA | 23474SA | AIP005500 | 23474 | SA | Surge Arrestor | 12
AIP005500SPILL | 23474SPILL | AIP005500 | 23474 | SPILL | Spill Containment | 2
AIP005500SWAB | 23474SWAB | AIP005500 | 23474 | SWAB | Switches (HV) | 2
AIP005500SWCS | 23474SWCS | AIP005500 | 23474 | SWCS | Switches - Circuit Switchers (HV) | 1
AIP005500TF | 23474TF | AIP005500 | 23474 | TF | Transformers | 2
AIP005500TFSSGT | 23474TFSSGT | AIP005500 | 23474 | TFSSGT | SS Transformers | 2
AIP005519BRHV-500kV | 23746BRHV-500kV | AIP005519 | 23746 | BRHV-500kV | 500kV | 9
AIP005519BRLV-27.6kV | 23746BRLV-27.6kV | AIP005519 | 23746 | BRLV-27.6kV | 27.6kV | 3
AIP005519HVIT-500kV | 23746HVIT-500kV | AIP005519 | 23746 | HVIT-500kV | 500kV | 21
AIP005519RE-27.6kV | 23746RE-27.6kV | AIP005519 | 23746 | RE-27.6kV | 27.6kV | 3
AIP005519SA-500kV | 23746SA-500kV | AIP005519 | 23746 | SA-500kV | 500kV | 13
AIP005519SWAB-500kV | 23746SWAB-500kV | AIP005519 | 23746 | SWAB-500kV | 500kV | 25
AIP005519TF-AUTO S500-A(500-240kV) - 750MVA | 23746TF-AUTO S500-A(500-240kV) - 750MVA | AIP005519 | 23746 | TF-AUTO S500-A(500-240kV) - 750MVA | AUTO S500-A(500-240kV) - 750MVA | 2
AIP005531IN-115kV | 23499IN-115kV | AIP005531 | 23499 | IN-115kV | 115kV | 1040
AIP005531OHCD | 23499OHCD | AIP005531 | 23499 | OHCD | Overhead Conductor (Km) | 58
AIP005531OPGW | 23499OPGW | AIP005531 | 23499 | OPGW | OPGW (Km) | 58
AIP005531PLCOATING | 23499PLCOATING | AIP005531 | 23499 | PLCOATING | Tower Coating (Structures) | 260
AIP005532BRLV-13.8kV | 23728BRLV-13.8kV | AIP005532 | 23728 | BRLV-13.8kV | 13.8kV | 13
AIP005532PR | 23728PR | AIP005532 | 23728 | PR | Protections | 15
AIP005532SS-DESN | 23728SS-DESN | AIP005532 | 23728 | SS-DESN | DESN | 1
AIP005554BRHV-500kV | 23844BRHV-500kV | AIP005554 | 23844 | BRHV-500kV | 500kV | 6
AIP005610CHARGER-250V | 24091CHARGER-250V | AIP005610 | 24091 | CHARGER-250V | 250V | 2
AIP005610CHARGER-48V | 24091CHARGER-48V | AIP005610 | 24091 | CHARGER-48V | 48V | 2
AIP005610DC | 24091DC | AIP005610 | 24091 | DC | DC Transfer Scheme | 1
AIP005610PR | 24091PR | AIP005610 | 24091 | PR | Protections | 40
AIP005610RTU-BULK | 24091RTU-BULK | AIP005610 | 24091 | RTU-BULK | BULK | 1
AIP005610SA-115kV | 24091SA-115kV | AIP005610 | 24091 | SA-115kV | 115kV | 3
AIP005610SA-230kV | 24091SA-230kV | AIP005610 | 24091 | SA-230kV | 230kV | 3
AIP005611AC | 24092AC | AIP005611 | 24092 | AC | AC Transfer Scheme | 1
AIP005611BRLV-44kV | 24092BRLV-44kV | AIP005611 | 24092 | BRLV-44kV | 44kV | 1
AIP005611PR | 24092PR | AIP005611 | 24092 | PR | Protections | 10
AIP005611SA-115kV | 24092SA-115kV | AIP005611 | 24092 | SA-115kV | 115kV | 9
AIP005611SA-44kV | 24092SA-44kV | AIP005611 | 24092 | SA-44kV | 44kV | 9
AIP005611SS-DESN | 24092SS-DESN | AIP005611 | 24092 | SS-DESN | DESN | 2
AIP005611SWAB-115kV | 24092SWAB-115kV | AIP005611 | 24092 | SWAB-115kV | 115kV | 11
AIP005611TF-S115-C(115-44kV) - 42MVA | 24092TF-S115-C(115-44kV) - 42MVA | AIP005611 | 24092 | TF-S115-C(115-44kV) - 42MVA | S115-C(115-44kV) - 42MVA | 1
AIP005613AC | 24094AC | AIP005613 | 24094 | AC | AC Transfer Scheme | 1
AIP005613BRHV-230kV | 24094BRHV-230kV | AIP005613 | 24094 | BRHV-230kV | 230kV | 6
AIP005613DC | 24094DC | AIP005613 | 24094 | DC | DC Transfer Scheme | 1
AIP005613HVIT-115kV | 24094HVIT-115kV | AIP005613 | 24094 | HVIT-115kV | 115kV | 3
AIP005613HVIT-230kV | 24094HVIT-230kV | AIP005613 | 24094 | HVIT-230kV | 230kV | 6
AIP005613PR | 24094PR | AIP005613 | 24094 | PR | Protections | 41
AIP005613RTU-BULK | 24094RTU-BULK | AIP005613 | 24094 | RTU-BULK | BULK | 1
AIP005613SPILL | 24094SPILL | AIP005613 | 24094 | SPILL | Spill Containment | 1
AIP005613SS-BULK | 24094SS-BULK | AIP005613 | 24094 | SS-BULK | BULK | 1
AIP005613SWAB-115kV | 24094SWAB-115kV | AIP005613 | 24094 | SWAB-115kV | 115kV | 1
AIP005614PR | 24095PR | AIP005614 | 24095 | PR | Protections | 22
AIP005614SA-44kV | 24095SA-44kV | AIP005614 | 24095 | SA-44kV | 44kV | 6
AIP005614TF-S230-B(215-44kV) - 83MVA | 24095TF-S230-B(215-44kV) - 83MVA | AIP005614 | 24095 | TF-S230-B(215-44kV) - 83MVA | S230-B(215-44kV) - 83MVA | 2
AIP005615AC-BULK | 24096AC-BULK | AIP005615 | 24096 | AC-BULK | BULK | 1
AIP005615BRHV-115kV | 24096BRHV-115kV | AIP005615 | 24096 | BRHV-115kV | 115kV | 5
AIP005615DC | 24096DC | AIP005615 | 24096 | DC | DC Transfer Scheme | 1
AIP005615HVIT-115kV | 24096HVIT-115kV | AIP005615 | 24096 | HVIT-115kV | 115kV | 6
AIP005615PR | 24096PR | AIP005615 | 24096 | PR | Protections | 27
AIP005615RTU-BULK | 24096RTU-BULK | AIP005615 | 24096 | RTU-BULK | BULK | 1
AIP005615SS-BULK | 24096SS-BULK | AIP005615 | 24096 | SS-BULK | BULK | 1
AIP005615SWAB-115kV | 24096SWAB-115kV | AIP005615 | 24096 | SWAB-115kV | 115kV | 9
AIP005617BRHV-115kV | 24098BRHV-115kV | AIP005617 | 24098 | BRHV-115kV | 115kV | 4
AIP005617CHARGER-48V | 24098CHARGER-48V | AIP005617 | 24098 | CHARGER-48V | 48V | 2
AIP005617DC | 24098DC | AIP005617 | 24098 | DC | DC Transfer Scheme | 1
AIP005617PR | 24098PR | AIP005617 | 24098 | PR | Protections | 4
AIP005617RTU-BULK | 24098RTU-BULK | AIP005617 | 24098 | RTU-BULK | BULK | 1
AIP005617SWAB-115kV | 24098SWAB-115kV | AIP005617 | 24098 | SWAB-115kV | 115kV | 4
AIP005646AC | 24127AC | AIP005646 | 24127 | AC | AC Transfer Scheme | 1
AIP005646BRHV-115kV | 24127BRHV-115kV | AIP005646 | 24127 | BRHV-115kV | 115kV | 4
AIP005646DC | 24127DC | AIP005646 | 24127 | DC | DC Transfer Scheme | 1
AIP005646DCBATTERY-250V | 24127DCBATTERY-250V | AIP005646 | 24127 | DCBATTERY-250V | 250V | 2
AIP005646DCBATTERY-48V | 24127DCBATTERY-48V | AIP005646 | 24127 | DCBATTERY-48V | 48V | 2
AIP005646PR | 24127PR | AIP005646 | 24127 | PR | Protections | 55
AIP005646SWAB-115kV | 24127SWAB-115kV | AIP005646 | 24127 | SWAB-115kV | 115kV | 8
AIP005653HVIT-115kV | 24178HVIT-115kV | AIP005653 | 24178 | HVIT-115kV | 115kV | 6
AIP005653PR | 24178PR | AIP005653 | 24178 | PR | Protections | 28
AIP005653TF-S115-F(110-14-14kV) - 100MVA | 24178TF-S115-F(110-14-14kV) - 100MVA | AIP005653 | 24178 | TF-S115-F(110-14-14kV) - 100MVA | S115-F(110-14-14kV) - 100MVA | 2
AIP005656PR | 24180PR | AIP005656 | 24180 | PR | Protections | 6
AIP005667BRLV-44kV | 24176BRLV-44kV | AIP005667 | 24176 | BRLV-44kV | 44kV | 9
AIP005667PR | 24176PR | AIP005667 | 24176 | PR | Protections | 40
AIP005667SPILL | 24176SPILL | AIP005667 | 24176 | SPILL | Spill Containment | 1
AIP005667TF-S230-E(215-44kV) - 125MVA | 24176TF-S230-E(215-44kV) - 125MVA | AIP005667 | 24176 | TF-S230-E(215-44kV) - 125MVA | S230-E(215-44kV) - 125MVA | 1
AIP005669AC | 24128AC | AIP005669 | 24128 | AC | AC Transfer Scheme | 1
AIP005669PR | 24128PR | AIP005669 | 24128 | PR | Protections | 24
AIP005669SA-13.8kV | 24128SA-13.8kV | AIP005669 | 24128 | SA-13.8kV | 13.8kV | 12
AIP005669SA-230kV | 24128SA-230kV | AIP005669 | 24128 | SA-230kV | 230kV | 6
AIP005669SPILL | 24128SPILL | AIP005669 | 24128 | SPILL | Spill Containment | 2
AIP005669SWAB-230kV | 24128SWAB-230kV | AIP005669 | 24128 | SWAB-230kV | 230kV | 2
AIP005671SA-27.6kV | 24185SA-27.6kV | AIP005671 | 24185 | SA-27.6kV | 27.6kV | 12
AIP005671SA-44kV | 24185SA-44kV | AIP005671 | 24185 | SA-44kV | 44kV | 12
AIP005671TF-230kV | 24185TF-230kV | AIP005671 | 24185 | TF-230kV | 230kV (Non-Standard) | 1
AIP005675BRLV-27.6kV | 23700BRLV-27.6kV | AIP005675 | 23700 | BRLV-27.6kV | 27.6kV | 3
AIP005675BRLV-44kV | 23700BRLV-44kV | AIP005675 | 23700 | BRLV-44kV | 44kV | 2
AIP005675CHARGER-250V | 23700CHARGER-250V | AIP005675 | 23700 | CHARGER-250V | 250V | 1
AIP005675HVIT-230kV | 23700HVIT-230kV | AIP005675 | 23700 | HVIT-230kV | 230kV | 2
AIP005675PR | 23700PR | AIP005675 | 23700 | PR | Protections | 69
AIP005675RTU-DESN | 23700RTU-DESN | AIP005675 | 23700 | RTU-DESN | DESN | 2
AIP005675SA-230kV | 23700SA-230kV | AIP005675 | 23700 | SA-230kV | 230kV | 4
AIP005676TF-230kV | 24134TF-230kV | AIP005676 | 24134 | TF-230kV | 230kV (Non-Standard) | 3
AIP005677AC | 24165AC | AIP005677 | 24165 | AC | AC Transfer Scheme | 1
AIP005677BRHV-230kV | 24165BRHV-230kV | AIP005677 | 24165 | BRHV-230kV | 230kV | 2
AIP005677DC | 24165DC | AIP005677 | 24165 | DC | DC Transfer Scheme | 1
AIP005677HVIT-115kV | 24165HVIT-115kV | AIP005677 | 24165 | HVIT-115kV | 115kV | 14
AIP005677PR | 24165PR | AIP005677 | 24165 | PR | Protections | 58
AIP005677RTU-BULK | 24165RTU-BULK | AIP005677 | 24165 | RTU-BULK | BULK | 1
AIP005677SS-BULK | 24165SS-BULK | AIP005677 | 24165 | SS-BULK | BULK | 2
AIP005677SWAB-230kV | 24165SWAB-230kV | AIP005677 | 24165 | SWAB-230kV | 230kV | 1
AIP005683PR | 24181PR | AIP005683 | 24181 | PR | Protections | 12
AIP005683RE-27.6kV | 24181RE-27.6kV | AIP005683 | 24181 | RE-27.6kV | 27.6kV | 3
AIP005683RE-44kV | 24181RE-44kV | AIP005683 | 24181 | RE-44kV | 44kV | 3
AIP005683SA-230kV | 24181SA-230kV | AIP005683 | 24181 | SA-230kV | 230kV | 6
AIP005683SA-27.6kV | 24181SA-27.6kV | AIP005683 | 24181 | SA-27.6kV | 27.6kV | 6
AIP005683SA-44kV | 24181SA-44kV | AIP005683 | 24181 | SA-44kV | 44kV | 6
AIP005687BRLV-44kV | 24160BRLV-44kV | AIP005687 | 24160 | BRLV-44kV | 44kV | 4
AIP005687CHARGER-125V | 24160CHARGER-125V | AIP005687 | 24160 | CHARGER-125V | 125V | 1
AIP005687DCBATTERY-125V | 24160DCBATTERY-125V | AIP005687 | 24160 | DCBATTERY-125V | 125V | 1
AIP005687PCT | 24160PCT | AIP005687 | 24160 | PCT | PCT Box | 1
AIP005687SC-44kV | 24160SC-44kV | AIP005687 | 24160 | SC-44kV | 44kV | 1
AIP005690CHARGER-125V | 24182CHARGER-125V | AIP005690 | 24182 | CHARGER-125V | 125V | 1
AIP005690MVGIS-27.6kV | 24182MVGIS-27.6kV | AIP005690 | 24182 | MVGIS-27.6kV | 27.6kV | 2
AIP005690PR | 24182PR | AIP005690 | 24182 | PR | Protections | 36
AIP005690RTU-DESN | 24182RTU-DESN | AIP005690 | 24182 | RTU-DESN | DESN | 1
AIP005690SA-230kV | 24182SA-230kV | AIP005690 | 24182 | SA-230kV | 230kV | 6
AIP005702AC | 24164AC | AIP005702 | 24164 | AC | AC Transfer Scheme | 1
AIP005702BRHV-115kV | 24164BRHV-115kV | AIP005702 | 24164 | BRHV-115kV | 115kV | 3
AIP005702BRHV-230kV | 24164BRHV-230kV | AIP005702 | 24164 | BRHV-230kV | 230kV | 4
AIP005702HVIT | 24164HVIT | AIP005702 | 24164 | HVIT | HVITs | 12
AIP005702PR | 24164PR | AIP005702 | 24164 | PR | Protections | 26
AIP005702SPILL | 24164SPILL | AIP005702 | 24164 | SPILL | Spill Containment | 2
AIP005702SS-BULK | 24164SS-BULK | AIP005702 | 24164 | SS-BULK | BULK | 2
AIP005702SWAB-115kV | 24164SWAB-115kV | AIP005702 | 24164 | SWAB-115kV | 115kV | 3
AIP005702SWAB-230kV | 24164SWAB-230kV | AIP005702 | 24164 | SWAB-230kV | 230kV | 5
AIP005702TF-AUTO S230-A(239-121kV) - 125MVA | 24164TF-AUTO S230-A(239-121kV) - 125MVA | AIP005702 | 24164 | TF-AUTO S230-A(239-121kV) - 125MVA | AUTO S230-A(239-121kV) - 125MVA | 2
AIP005718AC-BULK | 24163AC-BULK | AIP005718 | 24163 | AC-BULK | BULK | 1
AIP005718BRHV-115kV | 24163BRHV-115kV | AIP005718 | 24163 | BRHV-115kV | 115kV | 4
AIP005718BRHV-230kV | 24163BRHV-230kV | AIP005718 | 24163 | BRHV-230kV | 230kV | 3
AIP005718HVIT-115kV | 24163HVIT-115kV | AIP005718 | 24163 | HVIT-115kV | 115kV | 6
AIP005718HVIT-230kV | 24163HVIT-230kV | AIP005718 | 24163 | HVIT-230kV | 230kV | 9
AIP005718PR | 24163PR | AIP005718 | 24163 | PR | Protections | 21
AIP005730BRLV-13.8kV | 24221BRLV-13.8kV | AIP005730 | 24221 | BRLV-13.8kV | 13.8kV | 18
AIP005730DCBATTERY-125V | 24221DCBATTERY-125V | AIP005730 | 24221 | DCBATTERY-125V | 125V | 1
AIP005730HVIT-115kV | 24221HVIT-115kV | AIP005730 | 24221 | HVIT-115kV | 115kV | 3
AIP005730PCT | 24221PCT | AIP005730 | 24221 | PCT | PCT Box | 1
AIP005730SWAB-115kV | 24221SWAB-115kV | AIP005730 | 24221 | SWAB-115kV | 115kV | 2
AIP005730TF-S115-D(110-14-14kV) - 75MVA | 24221TF-S115-D(110-14-14kV) - 75MVA | AIP005730 | 24221 | TF-S115-D(110-14-14kV) - 75MVA | S115-D(110-14-14kV) - 75MVA | 1
AIP005740BRLV-44kV | 24214BRLV-44kV | AIP005740 | 24214 | BRLV-44kV | 44kV | 3
AIP005740CHARGER-125V | 24214CHARGER-125V | AIP005740 | 24214 | CHARGER-125V | 125V | 1
AIP005740CHARGER-48V | 24214CHARGER-48V | AIP005740 | 24214 | CHARGER-48V | 48V | 2
AIP005740DCBATTERY-125V | 24214DCBATTERY-125V | AIP005740 | 24214 | DCBATTERY-125V | 125V | 1
AIP005740HVIT-115kV | 24214HVIT-115kV | AIP005740 | 24214 | HVIT-115kV | 115kV | 2
AIP005740PR | 24214PR | AIP005740 | 24214 | PR | Protections | 27
AIP005740SA-115kV | 24214SA-115kV | AIP005740 | 24214 | SA-115kV | 115kV | 3
AIP005740SA-44kV | 24214SA-44kV | AIP005740 | 24214 | SA-44kV | 44kV | 3
AIP005740SWAB-115kV | 24214SWAB-115kV | AIP005740 | 24214 | SWAB-115kV | 115kV | 6
AIP005740SWAB-230kV | 24214SWAB-230kV | AIP005740 | 24214 | SWAB-230kV | 230kV | 5
AIP005740TF-S115-C(115-44kV) - 42MVA | 24214TF-S115-C(115-44kV) - 42MVA | AIP005740 | 24214 | TF-S115-C(115-44kV) - 42MVA | S115-C(115-44kV) - 42MVA | 1
AIP005752CHARGER-250V | 24184CHARGER-250V | AIP005752 | 24184 | CHARGER-250V | 250V | 2
AIP005752DC | 24184DC | AIP005752 | 24184 | DC | DC Transfer Scheme | 1
AIP005752DCBATTERY-125V | 24184DCBATTERY-125V | AIP005752 | 24184 | DCBATTERY-125V | 125V | 1
AIP005752DCBATTERY-250V | 24184DCBATTERY-250V | AIP005752 | 24184 | DCBATTERY-250V | 250V | 2
AIP005752DCBATTERY-48V | 24184DCBATTERY-48V | AIP005752 | 24184 | DCBATTERY-48V | 48V | 3
AIP005752HVIT-500kV | 24184HVIT-500kV | AIP005752 | 24184 | HVIT-500kV | 500kV | 6
AIP005752PR | 24184PR | AIP005752 | 24184 | PR | Protections | 42
AIP005752SA-230kV | 24184SA-230kV | AIP005752 | 24184 | SA-230kV | 230kV | 60
AIP005753BRLV-13.8kV | 24220BRLV-13.8kV | AIP005753 | 24220 | BRLV-13.8kV | 13.8kV | 20
AIP005753BRLV-27.6kV | 24220BRLV-27.6kV | AIP005753 | 24220 | BRLV-27.6kV | 27.6kV | 9
AIP005753CHARGER-125V | 24220CHARGER-125V | AIP005753 | 24220 | CHARGER-125V | 125V | 1
AIP005753DCBATTERY-125V | 24220DCBATTERY-125V | AIP005753 | 24220 | DCBATTERY-125V | 125V | 1
AIP005753PR | 24220PR | AIP005753 | 24220 | PR | Protections | 18
AIP005753SS-DESN | 24220SS-DESN | AIP005753 | 24220 | SS-DESN | DESN | 2
AIP005753TF-S230-A(215-28kV) - 83MVA | 24220TF-S230-A(215-28kV) - 83MVA | AIP005753 | 24220 | TF-S230-A(215-28kV) - 83MVA | S230-A(215-28kV) - 83MVA | 2
AIP005754AC-BULK | 24179AC-BULK | AIP005754 | 24179 | AC-BULK | BULK | 1
AIP005754CHARGER-250V | 24179CHARGER-250V | AIP005754 | 24179 | CHARGER-250V | 250V | 2
AIP005754DC | 24179DC | AIP005754 | 24179 | DC | DC Transfer Scheme | 1
AIP005754DCBATTERY-250V | 24179DCBATTERY-250V | AIP005754 | 24179 | DCBATTERY-250V | 250V | 2
AIP005754HVIT-500kV | 24179HVIT-500kV | AIP005754 | 24179 | HVIT-500kV | 500kV | 9
AIP005754PR | 24179PR | AIP005754 | 24179 | PR | Protections | 24
AIP005755BRHV-115kV | 24215BRHV-115kV | AIP005755 | 24215 | BRHV-115kV | 115kV | 2
AIP005755BRLV-27.6kV | 24215BRLV-27.6kV | AIP005755 | 24215 | BRLV-27.6kV | 27.6kV | 3
AIP005755CHARGER-250V | 24215CHARGER-250V | AIP005755 | 24215 | CHARGER-250V | 250V | 2
AIP005755DCBATTERY-250V | 24215DCBATTERY-250V | AIP005755 | 24215 | DCBATTERY-250V | 250V | 2
AIP005755PR | 24215PR | AIP005755 | 24215 | PR | Protections | 38
AIP005755SWAB-115kV | 24215SWAB-115kV | AIP005755 | 24215 | SWAB-115kV | 115kV | 2
AIP005755TF-S230-A(215-28kV) - 83MVA | 24215TF-S230-A(215-28kV) - 83MVA | AIP005755 | 24215 | TF-S230-A(215-28kV) - 83MVA | S230-A(215-28kV) - 83MVA | 2
AIP005757AC-BULK | 24216AC-BULK | AIP005757 | 24216 | AC-BULK | BULK | 1
AIP005757CHARGER-125V | 24216CHARGER-125V | AIP005757 | 24216 | CHARGER-125V | 125V | 1
AIP005757CHARGER-250V | 24216CHARGER-250V | AIP005757 | 24216 | CHARGER-250V | 250V | 2
AIP005757DCBATTERY-125V | 24216DCBATTERY-125V | AIP005757 | 24216 | DCBATTERY-125V | 125V | 1
AIP005757DCBATTERY-250V | 24216DCBATTERY-250V | AIP005757 | 24216 | DCBATTERY-250V | 250V | 1
AIP005757HVIT-230kV | 24216HVIT-230kV | AIP005757 | 24216 | HVIT-230kV | 230kV | 6
AIP005757PR | 24216PR | AIP005757 | 24216 | PR | Protections | 92
AIP005759BRLV-13.8kV | 24222BRLV-13.8kV | AIP005759 | 24222 | BRLV-13.8kV | 13.8kV | 11
AIP005759CHARGER-125V | 24222CHARGER-125V | AIP005759 | 24222 | CHARGER-125V | 125V | 1
AIP005759DCBATTERY-125V | 24222DCBATTERY-125V | AIP005759 | 24222 | DCBATTERY-125V | 125V | 1
AIP005759PR | 24222PR | AIP005759 | 24222 | PR | Protections | 31
AIP005759TF-S115-D(110-14-14kV) - 75MVA | 24222TF-S115-D(110-14-14kV) - 75MVA | AIP005759 | 24222 | TF-S115-D(110-14-14kV) - 75MVA | S115-D(110-14-14kV) - 75MVA | 1
AIP005779CHARGER-250V | 24305CHARGER-250V | AIP005779 | 24305 | CHARGER-250V | 250V | 1
AIP005779DCBATTERY-250V | 24305DCBATTERY-250V | AIP005779 | 24305 | DCBATTERY-250V | 250V | 1
AIP005779PR | 24305PR | AIP005779 | 24305 | PR | Protections | 4
AIP005780IN | 24265IN | AIP005780 | 24265 | IN | Insulators | 384
AIP005780NCSH | 24265NCSH | AIP005780 | 24265 | NCSH | Shieldwire (Km) | 10.58
AIP005780OHCD | 24265OHCD | AIP005780 | 24265 | OHCD | Overhead Conductor (Km) | 21.95
AIP005780PLST | 24265PLST | AIP005780 | 24265 | PLST | Steel Structures | 62
AIP005781IN | 24266IN | AIP005781 | 24266 | IN | Insulators | 121
AIP005781NCSH | 24266NCSH | AIP005781 | 24266 | NCSH | Shieldwire (Km) | 4.15
AIP005781OHCD | 24266OHCD | AIP005781 | 24266 | OHCD | Overhead Conductor (Km) | 3.87
AIP005781PLWD | 24266PLWD | AIP005781 | 24266 | PLWD | Wood Poles (Structures) | 39
AIP005782IN | 24267IN | AIP005782 | 24267 | IN | Insulators | 105
AIP005782NCSH | 24267NCSH | AIP005782 | 24267 | NCSH | Shieldwire (Km) | 2.48
AIP005782OHCD | 24267OHCD | AIP005782 | 24267 | OHCD | Overhead Conductor (Km) | 2.47
AIP005782PLWD | 24267PLWD | AIP005782 | 24267 | PLWD | Wood Poles (Structures) | 34
AIP005783IN | 24268IN | AIP005783 | 24268 | IN | Insulators | 4315
AIP005783NCSH | 24268NCSH | AIP005783 | 24268 | NCSH | Shieldwire (Km) | 106
AIP005783OHCD | 24268OHCD | AIP005783 | 24268 | OHCD | Overhead Conductor (Km) | 106
AIP005783PLST | 24268PLST | AIP005783 | 24268 | PLST | Steel Structures | 11
AIP005783PLWD | 24268PLWD | AIP005783 | 24268 | PLWD | Wood Poles (Structures) | 682
AIP005784IN | 24269IN | AIP005784 | 24269 | IN | Insulators | 2641
AIP005784NCSH | 24269NCSH | AIP005784 | 24269 | NCSH | Shieldwire (Km) | 127.87
AIP005784OHCD | 24269OHCD | AIP005784 | 24269 | OHCD | Overhead Conductor (Km) | 210.3877
AIP005784PLST | 24269PLST | AIP005784 | 24269 | PLST | Steel Structures | 410
AIP005784PLWD | 24269PLWD | AIP005784 | 24269 | PLWD | Wood Poles (Structures) | 32
AIP005785IN | 24270IN | AIP005785 | 24270 | IN | Insulators | 1411
AIP005785NCSH | 24270NCSH | AIP005785 | 24270 | NCSH | Shieldwire (Km) | 59.93
AIP005785OHCD | 24270OHCD | AIP005785 | 24270 | OHCD | Overhead Conductor (Km) | 58.5707
AIP005785PLST | 24270PLST | AIP005785 | 24270 | PLST | Steel Structures | 11
AIP005785PLWD | 24270PLWD | AIP005785 | 24270 | PLWD | Wood Poles (Structures) | 444
AIP005787IN | 24272IN | AIP005787 | 24272 | IN | Insulators | 4666
AIP005787NCSH | 24272NCSH | AIP005787 | 24272 | NCSH | Shieldwire (Km) | 162.3
AIP005787OHCD | 24272OHCD | AIP005787 | 24272 | OHCD | Overhead Conductor (Km) | 162.3
AIP005787PLWD | 24272PLWD | AIP005787 | 24272 | PLWD | Wood Poles (Structures) | 1505
AIP005788IN | 24273IN | AIP005788 | 24273 | IN | Insulators | 87
AIP005788NCSH | 24273NCSH | AIP005788 | 24273 | NCSH | Shieldwire (Km) | 2.51
AIP005788OHCD | 24273OHCD | AIP005788 | 24273 | OHCD | Overhead Conductor (Km) | 5.09
AIP005788PLST | 24273PLST | AIP005788 | 24273 | PLST | Steel Structures | 8
AIP005789IN | 24274IN | AIP005789 | 24274 | IN | Insulators | 149
AIP005789NCSH | 24274NCSH | AIP005789 | 24274 | NCSH | Shieldwire (Km) | 4.04
AIP005789OHCD | 24274OHCD | AIP005789 | 24274 | OHCD | Overhead Conductor (Km) | 8.19
AIP005789PLST | 24274PLST | AIP005789 | 24274 | PLST | Steel Structures | 12
AIP005790IN | 24275IN | AIP005790 | 24275 | IN | Insulators | 205
AIP005790NCSH | 24275NCSH | AIP005790 | 24275 | NCSH | Shieldwire (Km) | 28.48
AIP005790OHCD | 24275OHCD | AIP005790 | 24275 | OHCD | Overhead Conductor (Km) | 19.12
AIP005790PLST | 24275PLST | AIP005790 | 24275 | PLST | Steel Structures | 33
AIP005791IN | 24276IN | AIP005791 | 24276 | IN | Insulators | 62
AIP005791NCSH | 24276NCSH | AIP005791 | 24276 | NCSH | Shieldwire (Km) | 1.83
AIP005791OHCD | 24276OHCD | AIP005791 | 24276 | OHCD | Overhead Conductor (Km) | 1.91
AIP005791PLWD | 24276PLWD | AIP005791 | 24276 | PLWD | Wood Poles (Structures) | 20
AIP005792IN | 24277IN | AIP005792 | 24277 | IN | Insulators | 3075.2
AIP005792NCSH | 24277NCSH | AIP005792 | 24277 | NCSH | Shieldwire (Km) | 183.9
AIP005792OHCD | 24277OHCD | AIP005792 | 24277 | OHCD | Overhead Conductor (Km) | 182.74
AIP005792PLST | 24277PLST | AIP005792 | 24277 | PLST | Steel Structures | 575
AIP005793IN | 24278IN | AIP005793 | 24278 | IN | Insulators | 1283
AIP005793NCSH | 24278NCSH | AIP005793 | 24278 | NCSH | Shieldwire (Km) | 256.98
AIP005793OHCD | 24278OHCD | AIP005793 | 24278 | OHCD | Overhead Conductor (Km) | 128.4874
AIP005793PLST | 24278PLST | AIP005793 | 24278 | PLST | Steel Structures | 414
AIP005794IN | 24279IN | AIP005794 | 24279 | IN | Insulators | 595
AIP005794NCSH | 24279NCSH | AIP005794 | 24279 | NCSH | Shieldwire (Km) | 129.67
AIP005794OHCD | 24279OHCD | AIP005794 | 24279 | OHCD | Overhead Conductor (Km) | 65.33
AIP005794PLST | 24279PLST | AIP005794 | 24279 | PLST | Steel Structures | 192
AIP005795IN | 24280IN | AIP005795 | 24280 | IN | Insulators | 1141
AIP005795NCSH | 24280NCSH | AIP005795 | 24280 | NCSH | Shieldwire (Km) | 167
AIP005795OHCD | 24280OHCD | AIP005795 | 24280 | OHCD | Overhead Conductor (Km) | 112
AIP005795PLST | 24280PLST | AIP005795 | 24280 | PLST | Steel Structures | 184
AIP005796IN | 24281IN | AIP005796 | 24281 | IN | Insulators | 62
AIP005796NCSH | 24281NCSH | AIP005796 | 24281 | NCSH | Shieldwire (Km) | 11.87
AIP005796OHCD | 24281OHCD | AIP005796 | 24281 | OHCD | Overhead Conductor (Km) | 6.3203
AIP005796PLST | 24281PLST | AIP005796 | 24281 | PLST | Steel Structures | 20
AIP005798IN | 24282IN | AIP005798 | 24282 | IN | Insulators | 508
AIP005798NCSH | 24282NCSH | AIP005798 | 24282 | NCSH | Shieldwire (Km) | 49.72
AIP005798OHCD | 24282OHCD | AIP005798 | 24282 | OHCD | Overhead Conductor (Km) | 49.7691
AIP005798PLST | 24282PLST | AIP005798 | 24282 | PLST | Steel Structures | 82
AIP005799IN | 24238IN | AIP005799 | 24238 | IN | Insulators | 270
AIP005799OHCD | 24238OHCD | AIP005799 | 24238 | OHCD | Overhead Conductor (Km) | 15.5092
AIP005799PLWD | 24238PLWD | AIP005799 | 24238 | PLWD | Wood Poles (Structures) | 87
AIP005800IN | 24239IN | AIP005800 | 24239 | IN | Insulators | 4145
AIP005800NCSH | 24239NCSH | AIP005800 | 24239 | NCSH | Shieldwire (Km) | 315
AIP005800OHCD | 24239OHCD | AIP005800 | 24239 | OHCD | Overhead Conductor (Km) | 248
AIP005800PLST | 24239PLST | AIP005800 | 24239 | PLST | Steel Structures | 562
AIP005801IN | 24285IN | AIP005801 | 24285 | IN | Insulators | 34
AIP005801NCSH | 24285NCSH | AIP005801 | 24285 | NCSH | Shieldwire (Km) | 1.2
AIP005801OHCD | 24285OHCD | AIP005801 | 24285 | OHCD | Overhead Conductor (Km) | 1.96
AIP005801PLWD | 24285PLWD | AIP005801 | 24285 | PLWD | Wood Poles (Structures) | 10
AIP005802IN | 24286IN | AIP005802 | 24286 | IN | Insulators | 471
AIP005802NCSH | 24286NCSH | AIP005802 | 24286 | NCSH | Shieldwire (Km) | 23.54
AIP005802OHCD | 24286OHCD | AIP005802 | 24286 | OHCD | Overhead Conductor (Km) | 47.06
AIP005802PLST | 24286PLST | AIP005802 | 24286 | PLST | Steel Structures | 80
AIP005803IN | 24287IN | AIP005803 | 24287 | IN | Insulators | 648
AIP005803NCSH | 24287NCSH | AIP005803 | 24287 | NCSH | Shieldwire (Km) | 59.84
AIP005803OHCD | 24287OHCD | AIP005803 | 24287 | OHCD | Overhead Conductor (Km) | 59.8381
AIP005803PLST | 24287PLST | AIP005803 | 24287 | PLST | Steel Structures | 209
AIP005804IN | 24288IN | AIP005804 | 24288 | IN | Insulators | 1854
AIP005804NCSH | 24288NCSH | AIP005804 | 24288 | NCSH | Shieldwire (Km) | 27.98
AIP005804OHCD | 24288OHCD | AIP005804 | 24288 | OHCD | Overhead Conductor (Km) | 70.3899
AIP005804PLWD | 24288PLWD | AIP005804 | 24288 | PLWD | Wood Poles (Structures) | 598
AIP005805IN | 24289IN | AIP005805 | 24289 | IN | Insulators | 136
AIP005805NCSH | 24289NCSH | AIP005805 | 24289 | NCSH | Shieldwire (Km) | 13.3
AIP005805OHCD | 24289OHCD | AIP005805 | 24289 | OHCD | Overhead Conductor (Km) | 6.6546
AIP005805PLWD | 24289PLWD | AIP005805 | 24289 | PLWD | Wood Poles (Structures) | 45
AIP005807IN | 24291IN | AIP005807 | 24291 | IN | Insulators | 149
AIP005807NCSH | 24291NCSH | AIP005807 | 24291 | NCSH | Shieldwire (Km) | 3.56
AIP005807OHCD | 24291OHCD | AIP005807 | 24291 | OHCD | Overhead Conductor (Km) | 7.19
AIP005807PLST | 24291PLST | AIP005807 | 24291 | PLST | Steel Structures | 24
AIP005808IN | 24292IN | AIP005808 | 24292 | IN | Insulators | 62
AIP005808NCSH | 24292NCSH | AIP005808 | 24292 | NCSH | Shieldwire (Km) | 0.35
AIP005808OHCD | 24292OHCD | AIP005808 | 24292 | OHCD | Overhead Conductor (Km) | 0.9
AIP005808PLST | 24292PLST | AIP005808 | 24292 | PLST | Steel Structures | 10
AIP005810IN | 24294IN | AIP005810 | 24294 | IN | Insulators | 853
AIP005810NCSH | 24294NCSH | AIP005810 | 24294 | NCSH | Shieldwire (Km) | 39.83
AIP005810OHCD | 24294OHCD | AIP005810 | 24294 | OHCD | Overhead Conductor (Km) | 39.83
AIP005810PLWD | 24294PLWD | AIP005810 | 24294 | PLWD | Wood Poles (Structures) | 275
AIP005811IN | 24295IN | AIP005811 | 24295 | IN | Insulators | 1085
AIP005811NCSH | 24295NCSH | AIP005811 | 24295 | NCSH | Shieldwire (Km) | 114
AIP005811OHCD | 24295OHCD | AIP005811 | 24295 | OHCD | Overhead Conductor (Km) | 114
AIP005811PLST | 24295PLST | AIP005811 | 24295 | PLST | Steel Structures | 350
AIP005812IN | 24296IN | AIP005812 | 24296 | IN | Insulators | 310
AIP005812NCSH | 24296NCSH | AIP005812 | 24296 | NCSH | Shieldwire (Km) | 10
AIP005812OHCD | 24296OHCD | AIP005812 | 24296 | OHCD | Overhead Conductor (Km) | 20
AIP005812PLST | 24296PLST | AIP005812 | 24296 | PLST | Steel Structures | 50
AIP005814BRHV | 24300BRHV | AIP005814 | 24300 | BRHV | Breakers (HV) | 2
AIP005814CHARGER | 24300CHARGER | AIP005814 | 24300 | CHARGER | Charger | 1
AIP005814HVIT-230kV | 24300HVIT-230kV | AIP005814 | 24300 | HVIT-230kV | 230kV | 2
AIP005814PR | 24300PR | AIP005814 | 24300 | PR | Protections | 25
AIP005814SWAB-115kV | 24300SWAB-115kV | AIP005814 | 24300 | SWAB-115kV | 115kV | 4
AIP005815AC | 24302AC | AIP005815 | 24302 | AC | AC Transfer Scheme | 1
AIP005815BRLV-13.8kV | 24302BRLV-13.8kV | AIP005815 | 24302 | BRLV-13.8kV | 13.8kV | 13
AIP005815CHARGER | 24302CHARGER | AIP005815 | 24302 | CHARGER | Charger | 1
AIP005815DCBATTERY | 24302DCBATTERY | AIP005815 | 24302 | DCBATTERY | Battery | 1
AIP005815PR | 24302PR | AIP005815 | 24302 | PR | Protections | 15
AIP005815SS-DESN | 24302SS-DESN | AIP005815 | 24302 | SS-DESN | DESN | 2
AIP005816BRLV-27.6kV | 24303BRLV-27.6kV | AIP005816 | 24303 | BRLV-27.6kV | 27.6kV | 9
AIP005816PR | 24303PR | AIP005816 | 24303 | PR | Protections | 29
AIP005816SA-230kV | 24303SA-230kV | AIP005816 | 24303 | SA-230kV | 230kV | 6
AIP005816SS-DESN | 24303SS-DESN | AIP005816 | 24303 | SS-DESN | DESN | 1
AIP005818PR | 24312PR | AIP005818 | 24312 | PR | Protections | 27
AIP005819BRHV | 24311BRHV | AIP005819 | 24311 | BRHV | Breakers (HV) | 1
AIP005819PCT | 24311PCT | AIP005819 | 24311 | PCT | PCT Box | 7
AIP005819TF | 24311TF | AIP005819 | 24311 | TF | Transformers | 2
AIP005824AC-BULK | 24309AC-BULK | AIP005824 | 24309 | AC-BULK | BULK | 1
AIP005824BRLV-44kV | 24309BRLV-44kV | AIP005824 | 24309 | BRLV-44kV | 44kV | 2
AIP005824DCBATTERY | 24309DCBATTERY | AIP005824 | 24309 | DCBATTERY | Battery | 2
AIP005824PR | 24309PR | AIP005824 | 24309 | PR | Protections | 31
AIP005824SPILL | 24309SPILL | AIP005824 | 24309 | SPILL | Spill Containment | 2
AIP005824SS-BULK | 24309SS-BULK | AIP005824 | 24309 | SS-BULK | BULK | 2
AIP005824SWAB-115kV | 24309SWAB-115kV | AIP005824 | 24309 | SWAB-115kV | 115kV | 2
AIP005824TF-S115-C(115-44kV) - 42MVA | 24309TF-S115-C(115-44kV) - 42MVA | AIP005824 | 24309 | TF-S115-C(115-44kV) - 42MVA | S115-C(115-44kV) - 42MVA | 2
AIP006053SA-230kV | 24607SA-230kV | AIP006053 | 24607 | SA-230kV | 230kV | 6
AIP006053SWAB-230kV | 24607SWAB-230kV | AIP006053 | 24607 | SWAB-230kV | 230kV | 2
AIP006055BRLV-44kV | 24785BRLV-44kV | AIP006055 | 24785 | BRLV-44kV | 44kV | 8
AIP006055HVIT-115kV | 24785HVIT-115kV | AIP006055 | 24785 | HVIT-115kV | 115kV | 12
AIP006055PR | 24785PR | AIP006055 | 24785 | PR | Protections | 24
AIP006055RTU-BULK | 24785RTU-BULK | AIP006055 | 24785 | RTU-BULK | BULK | 1
AIP006055SA-115kV | 24785SA-115kV | AIP006055 | 24785 | SA-115kV | 115kV | 6
AIP006055SA-44kV | 24785SA-44kV | AIP006055 | 24785 | SA-44kV | 44kV | 6
AIP006055SC-44kV | 24785SC-44kV | AIP006055 | 24785 | SC-44kV | 44kV | 1
AIP006056BRLV-44kV | 24786BRLV-44kV | AIP006056 | 24786 | BRLV-44kV | 44kV | 9
AIP006056RTU-DESN | 24786RTU-DESN | AIP006056 | 24786 | RTU-DESN | DESN | 1
AIP006056SC-44kV | 24786SC-44kV | AIP006056 | 24786 | SC-44kV | 44kV | 1
AIP006058BRHV-230kV | 24788BRHV-230kV | AIP006058 | 24788 | BRHV-230kV | 230kV | 2
AIP006058CHARGER-48V | 24788CHARGER-48V | AIP006058 | 24788 | CHARGER-48V | 48V | 4
AIP006058PR | 24788PR | AIP006058 | 24788 | PR | Protections | 34
AIP006058RTU-BULK | 24788RTU-BULK | AIP006058 | 24788 | RTU-BULK | BULK | 1
AIP006058SWAB-230kV | 24788SWAB-230kV | AIP006058 | 24788 | SWAB-230kV | 230kV | 9
AIP006058SWAB-500kV | 24788SWAB-500kV | AIP006058 | 24788 | SWAB-500kV | 500kV | 4
AIP006058TF-AUTO S230-B(239-121kV) - 250MVA | 24788TF-AUTO S230-B(239-121kV) - 250MVA | AIP006058 | 24788 | TF-AUTO S230-B(239-121kV) - 250MVA | AUTO S230-B(239-121kV) - 250MVA | 2
AIP006058TF-AUTO S500-A(500-240kV) - 750MVA | 24788TF-AUTO S500-A(500-240kV) - 750MVA | AIP006058 | 24788 | TF-AUTO S500-A(500-240kV) - 750MVA | AUTO S500-A(500-240kV) - 750MVA | 1
AIP006059CHARGER-250V | 24789CHARGER-250V | AIP006059 | 24789 | CHARGER-250V | 250V | 2
AIP006059DC | 24789DC | AIP006059 | 24789 | DC | DC Transfer Scheme | 2
AIP006059DCBATTERY-250V | 24789DCBATTERY-250V | AIP006059 | 24789 | DCBATTERY-250V | 250V | 2
AIP006059PR | 24789PR | AIP006059 | 24789 | PR | Protections | 21
AIP006120PR | 24714PR | AIP006120 | 24714 | PR | Protections | 4
AIP006120SPILL | 24714SPILL | AIP006120 | 24714 | SPILL | Spill Containment | 2
AIP006120TF-S230-C(215-14-14kV) - 100MVA | 24714TF-S230-C(215-14-14kV) - 100MVA | AIP006120 | 24714 | TF-S230-C(215-14-14kV) - 100MVA | S230-C(215-14-14kV) - 100MVA | 2
AIP006140AC-DESN | 24670AC-DESN | AIP006140 | 24670 | AC-DESN | DESN | 1
AIP006140BRLV-44kV | 24670BRLV-44kV | AIP006140 | 24670 | BRLV-44kV | 44kV | 5
AIP006140CHARGER-250V | 24670CHARGER-250V | AIP006140 | 24670 | CHARGER-250V | 250V | 1
AIP006140DCBATTERY-250V | 24670DCBATTERY-250V | AIP006140 | 24670 | DCBATTERY-250V | 250V | 1
AIP006140HVIT | 24670HVIT | AIP006140 | 24670 | HVIT | HVITs | 4
AIP006140PR | 24670PR | AIP006140 | 24670 | PR | Protections | 15
AIP006140TF-S115-A(115-14kV) - 42MVA | 24670TF-S115-A(115-14kV) - 42MVA | AIP006140 | 24670 | TF-S115-A(115-14kV) - 42MVA | S115-A(115-14kV) - 42MVA | 2
AIP006142AC-DESN | 24932AC-DESN | AIP006142 | 24932 | AC-DESN | DESN | 1
AIP006142BRLV-13.8kV | 24932BRLV-13.8kV | AIP006142 | 24932 | BRLV-13.8kV | 13.8kV | 11
AIP006142SS-DESN | 24932SS-DESN | AIP006142 | 24932 | SS-DESN | DESN | 1
AIP006142TF-S230-A(215-28kV) - 83MVA | 24932TF-S230-A(215-28kV) - 83MVA | AIP006142 | 24932 | TF-S230-A(215-28kV) - 83MVA | S230-A(215-28kV) - 83MVA | 2
AIP006143DCBATTERY-250V | 24781DCBATTERY-250V | AIP006143 | 24781 | DCBATTERY-250V | 250V | 2
AIP006143HVIT | 24781HVIT | AIP006143 | 24781 | HVIT | HVITs | 3
AIP006143PR | 24781PR | AIP006143 | 24781 | PR | Protections | 1
AIP006143TF-S115-F(110-14-14kV) - 100MVA | 24781TF-S115-F(110-14-14kV) - 100MVA | AIP006143 | 24781 | TF-S115-F(110-14-14kV) - 100MVA | S115-F(110-14-14kV) - 100MVA | 3
AIP006146CHARGER-250V | 24779CHARGER-250V | AIP006146 | 24779 | CHARGER-250V | 250V | 1
AIP006146DCBATTERY-250V | 24779DCBATTERY-250V | AIP006146 | 24779 | DCBATTERY-250V | 250V | 1
AIP006146PR | 24779PR | AIP006146 | 24779 | PR | Protections | 15
AIP006146TF-S115-A(115-14kV) - 42MVA | 24779TF-S115-A(115-14kV) - 42MVA | AIP006146 | 24779 | TF-S115-A(115-14kV) - 42MVA | S115-A(115-14kV) - 42MVA | 1
AIP006147BRLV-27.6kV | 24930BRLV-27.6kV | AIP006147 | 24930 | BRLV-27.6kV | 27.6kV | 9
AIP006147CHARGER-250V | 24930CHARGER-250V | AIP006147 | 24930 | CHARGER-250V | 250V | 9
AIP006147DC | 24930DC | AIP006147 | 24930 | DC | DC Transfer Scheme | 9
AIP006147HVIT-230kV | 24930HVIT-230kV | AIP006147 | 24930 | HVIT-230kV | 230kV | 2
AIP006147PR | 24930PR | AIP006147 | 24930 | PR | Protections | 17
AIP006147SA-115kV | 24930SA-115kV | AIP006147 | 24930 | SA-115kV | 115kV | 6
AIP006147SWAB-230kV | 24930SWAB-230kV | AIP006147 | 24930 | SWAB-230kV | 230kV | 2
AIP006147TF-S230-A(215-28kV) - 83MVA | 24930TF-S230-A(215-28kV) - 83MVA | AIP006147 | 24930 | TF-S230-A(215-28kV) - 83MVA | S230-A(215-28kV) - 83MVA | 2
AIP006148BRLV | 24778BRLV | AIP006148 | 24778 | BRLV | Breakers (LV) | 8
AIP006152TF-S230-E(215-44kV) - 125MVA | 24775TF-S230-E(215-44kV) - 125MVA | AIP006152 | 24775 | TF-S230-E(215-44kV) - 125MVA | S230-E(215-44kV) - 125MVA | 2
AIP006154AC-DESN | 24931AC-DESN | AIP006154 | 24931 | AC-DESN | DESN | 1
AIP006154BRLV-27.6kV | 24931BRLV-27.6kV | AIP006154 | 24931 | BRLV-27.6kV | 27.6kV | 8
AIP006154CHARGER-125V | 24931CHARGER-125V | AIP006154 | 24931 | CHARGER-125V | 125V | 1
AIP006154DCBATTERY-125V | 24931DCBATTERY-125V | AIP006154 | 24931 | DCBATTERY-125V | 125V | 1
AIP006154PR | 24931PR | AIP006154 | 24931 | PR | Protections | 16
AIP006154SWAB-115kV | 24931SWAB-115kV | AIP006154 | 24931 | SWAB-115kV | 115kV | 2
AIP006154TF-S115-B(110-28kV) - 42MVA | 24931TF-S115-B(110-28kV) - 42MVA | AIP006154 | 24931 | TF-S115-B(110-28kV) - 42MVA | S115-B(110-28kV) - 42MVA | 2
AIP006157BRLV-44kV | 24780BRLV-44kV | AIP006157 | 24780 | BRLV-44kV | 44kV | 2
AIP006157PR | 24780PR | AIP006157 | 24780 | PR | Protections | 6
AIP006157SA | 24780SA | AIP006157 | 24780 | SA | Surge Arrestor | 18
AIP006157SPILL | 24780SPILL | AIP006157 | 24780 | SPILL | Spill Containment | 2
AIP006157TF-S115-A(115-14kV) - 42MVA | 24780TF-S115-A(115-14kV) - 42MVA | AIP006157 | 24780 | TF-S115-A(115-14kV) - 42MVA | S115-A(115-14kV) - 42MVA | 2
AIP006185BRLV-13.8kV | 24902BRLV-13.8kV | AIP006185 | 24902 | BRLV-13.8kV | 13.8kV | 9
AIP006185PR | 24902PR | AIP006185 | 24902 | PR | Protections | 23
AIP006185SPILL | 24902SPILL | AIP006185 | 24902 | SPILL | Spill Containment | 2
AIP006185SWAB-115kV | 24902SWAB-115kV | AIP006185 | 24902 | SWAB-115kV | 115kV | 2
AIP006185TF-S115-D(110-14-14kV) - 75MVA | 24902TF-S115-D(110-14-14kV) - 75MVA | AIP006185 | 24902 | TF-S115-D(110-14-14kV) - 75MVA | S115-D(110-14-14kV) - 75MVA | 2
AIP006186AC-DESN | 24901AC-DESN | AIP006186 | 24901 | AC-DESN | DESN | 1
AIP006186BRLV-13.8kV | 24901BRLV-13.8kV | AIP006186 | 24901 | BRLV-13.8kV | 13.8kV | 17
AIP006186DCBATTERY-125V | 24901DCBATTERY-125V | AIP006186 | 24901 | DCBATTERY-125V | 125V | 2
AIP006186PR | 24901PR | AIP006186 | 24901 | PR | Protections | 29
AIP006189BRLV-44kV | 24928BRLV-44kV | AIP006189 | 24928 | BRLV-44kV | 44kV | 3
AIP006189CHARGER-125V | 24928CHARGER-125V | AIP006189 | 24928 | CHARGER-125V | 125V | 1
AIP006189CHARGER-48V | 24928CHARGER-48V | AIP006189 | 24928 | CHARGER-48V | 48V | 4
AIP006189DC | 24928DC | AIP006189 | 24928 | DC | DC Transfer Scheme | 1
AIP006189DCBATTERY-125V | 24928DCBATTERY-125V | AIP006189 | 24928 | DCBATTERY-125V | 125V | 1
AIP006189PR | 24928PR | AIP006189 | 24928 | PR | Protections | 40
AIP006254TF-S230-E(215-44kV) - 125MVA | 25061TF-S230-E(215-44kV) - 125MVA | AIP006254 | 25061 | TF-S230-E(215-44kV) - 125MVA | S230-E(215-44kV) - 125MVA | 2
AIP006261TF-AUTO S500-A(500-240kV) - 750MVA | 24791TF-AUTO S500-A(500-240kV) - 750MVA | AIP006261 | 24791 | TF-AUTO S500-A(500-240kV) - 750MVA | AUTO S500-A(500-240kV) - 750MVA | 1
AIP006280AC-DESN | 25080AC-DESN | AIP006280 | 25080 | AC-DESN | DESN | 1
AIP006280BRLV-27.6kV | 25080BRLV-27.6kV | AIP006280 | 25080 | BRLV-27.6kV | 27.6kV | 5
AIP006280CHARGER-125V | 25080CHARGER-125V | AIP006280 | 25080 | CHARGER-125V | 125V | 1
AIP006280DCBATTERY-125V | 25080DCBATTERY-125V | AIP006280 | 25080 | DCBATTERY-125V | 125V | 1
AIP006280PR | 25080PR | AIP006280 | 25080 | PR | Protections | 27
AIP006280SWAB-115kV | 25080SWAB-115kV | AIP006280 | 25080 | SWAB-115kV | 115kV | 6