## Summary Chart
Confidential Draft for Illustrative Purposes | [9 empty] | Inc / (Dec) | Inc / (Dec) |  | Inc / (Dec)
CAD $MM | [7 empty] | Rate Case | As of May 2023 | Total Delta from Rate Case | Delta explained in Qtrly Reports | Delta explained in document: | Delta after last Qtrly Report | Delta after last Qtrly Report explained:
NextBridge Project Cost - East West Tie |  | $MM CAD | Comment
Engineering & Construction |  | 614.2385 | As of May 2023 |  |  |  | Engineering & Construction | 614.28 | 614.2385 | -0.041485 | 0 |  | -0.041485
1 | Engineering, Design and Procurement | 9.9753 | As of May 2023 |  |  |  | Engineering, Design and Procurement | 8.5 | 9.9753 | 1.4753 | 1.5 | Quarterly OEB report filed 10/22/21; page 28 & Quarterly OEB report filed 10/21/22; page 12 | -0.024698 | Project completion. No additional engineering expenses were needed
2 | Materials and Equipment | 68.7007 | As of May 2023 |  |  |  | Materials and Equipment | 66.94 | 68.7007 | 1.7607 | 1.7 | Quarterly OEB report filed 10/22/21; page 28 & Quarterly OEB report filed 10/21/22; page 12 | 0.060749 | True up to material costs additional spare material procurement
8 | Site Clearing, Access | 137.1984 | As of May 2023 |  |  |  | Site Clearing, Access | 140.64 | 137.1984 | -3.4416 | -3.4 | Quarterly OEB report filed 10/22/21; page 28 & Quarterly OEB report filed 10/21/22; page 12 | -0.041622 | Project completion. No additional engineering expenses were needed
9 | Construction | 398.3641 | As of May 2023 |  |  |  | Construction | 398.2 | 398.3641 | 0.16409 | 0.2 | Quarterly OEB report filed 10/22/21; page 28 & Quarterly OEB report filed 10/21/22; page 12 | -0.035915 | Project completion. No additional engineering expenses were needed
Environmental & Remediation Activities |  | 31.3 | As of May 2023 |  |  |  | Environmental & Remediation Activities | 31.6 | 31.3 | -0.3 | -0.3 |  | 1.0547e-15
3 | Environmental and Regulatory Approvals | 19.1 | As of May 2023 |  |  |  | Environmental and Regulatory Approvals | 19.1 | 19.1 | 0 | 0 |  | 0
10 | Site Remediation | 12.2 | As of May 2023 |  |  |  | Site Remediation | 12.5 | 12.2 | -0.3 | -0.3 | Quarterly OEB report filed 1/20/23; page 12 | 1.0547e-15
Indigenous Activities |  | 24.0831 | As of May 2023 |  |  |  | Indigenous Activities | 23.6 | 24.0831 | 0.48309 | 1.7764e-15 | Quarterly OEB report filed 1/20/23; page 12 | 0.48309
5 | Indigenous Economic Participation | 10.4 | As of May 2023 |  |  |  | Indigenous Economic Participation | 9.7 | 10.4 | 0.7 | 0.1 |  | 0.6 | Increase in legal feels to Support BLP Buy-In
6 | Indigenous Consultation | 13.6831 | As of May 2023 |  |  |  | Indigenous Consultation | 13.9 | 13.6831 | -0.21691 | -0.1 |  | -0.11691 | Project completion. No additional engineering expenses were needed
4 | Land Rights (excludes Aboriginal) | 23.3305 | As of May 2023 |  |  |  | Land Rights (excludes Aboriginal) | 23.8 | 23.3305 | -0.46949 | -0.5 | Quarterly OEB report filed 4/21/22; page 29 | 0.030512 | n/a
7 | Other Consultation | 1.7 | As of May 2023 |  |  |  | Other Consultation | 2.5 | 1.7 | -0.8 | -0.8 | Quarterly OEB report filed 10/22/21; page 28 & Quarterly OEB report filed 4/21/22; page 29 | 0 | n/a
11 | Contingency | 0 | As of May 2023 |  |  |  | Contingency | 0 | 0 | 0 | 0 |  | 0 | n/a
12 | Regulatory | 5.4774 | As of May 2023 |  |  |  | Regulatory | 5.4 | 5.4774 | 0.077391 | 0.2 | Quarterly OEB report filed 4/21/22; page 29 | -0.12261 | Project completion. No additional engineering expenses were needed
13 | EWT Management | 5.7651 | As of May 2023 |  |  |  | EWT Management | 4.9 | 5.7651 | 0.86514 | 0.9 | Quarterly OEB report filed 10/22/21; page 28 & Quarterly OEB report filed 4/21/22; page 29 | -0.034864 | Project completion. No additional engineering expenses were needed
Total Project Spend including Spares |  | 705.8946 | As of May 2023 |  |  |  | Total Project Spend including Spares | 706.08 | 705.8946 | -0.18535 | -0.5 | n/a | 0.31465
14 | Interest During Construction (IDC) | 31.3 | As of May 2023 | Category | Amount | Docket Approved in | Interest During Construction (IDC) | 31 | 31.3 | 0.3 | 0.3 | Quarterly OEB report filed 4/21/22; page 28 | 0 | n/a
Total Construction Costs |  | 737.1946 | Approved in D&O from EB-2020-0150 | Construction | 737.1 | EB-2020-0150 | Total Construction Costs | 737.08 | 737.1946 | 0.11465 | -0.2 |  | 0.31465
Development | Development Costs | 31.2 | Approved in D&O from EB-2017-0182 | Development | 31.2 | EB-2017-0182
Phase Shift | Phase Shift Costs | 5.3 | Approved in D&O from EB-2020-0150 | Phase Shift | 5.3 | EB-2020-0150
Total Construction, Development, Phase Shift | COVID | 773.6946 | Approved in D&O from EB-2020-0150
Construction Cost Variance: Wildfire |  | 0 | To be reviewed in 2023; for rate year 2024
Construction Cost Variance: Kama Cliffs |  | 0 | To be reviewed in 2023; for rate year 2024
Construction Cost Variance: White Lake Narrows |  | 0 | To be reviewed in 2023; for rate year 2024
Construction Cost Variance: Delay & Other |  | 0 | To be reviewed in 2023; for rate year 2024
Total Construction Cost Variance |  | 0 | To be reviewed in 2023; for rate year 2024
COVID-19 |  | 0 | To be reviewed in 2023; for rate year 2024
Total Construction Cost Variance & COVID-19 |  | 0 | To be reviewed in 2023; for rate year 2024
Total |  | 773.6946

## Construction Cost Bal
OEB Bucket | Sub Category | Budget
01. Engineering, Design and Procurement | NEER - Engineering | 9.9753
01. Engineering, Design and Procurement Total |  | 9.9753
02. Materials and Equipment | NEER - Conductor/OPGW/OHGW | 26.5475
| NEER - Structures/poles | 42.1532
02. Materials and Equipment Total |  | 68.7007
03. Environmental and Regulatory Approvals | Construction Compliance | 2.6
| Consultation Support | 0.1
| Environment Surveys & Studies | 4.2
| Environmental Permits and licensing | 3.9
| Environmental Project Management - inter | 1
| Environmental Protection and Compensatio | 6.7
| Project Management - consultants | 0.6
03. Environmental and Regulatory Approvals Total |  | 19.1
04. Land Rights (excludes Aboriginal) | Bell Crossing | 0.015809
| Damage Settlements (Crown) - CanACRE | 0.30325
| Damage Settlements (Crown) - Fees | 0.27867
| Damage Settlements (Crown) - Internal la | 0.058624
| Damage Settlements (Private) - CanACRE | 0.63781
| Damage Settlements (Private) - Fees | 1.9061
| Damage Settlements (Private) - Internal | 0.06063
| GIS - CanACRE | 0.42286
| Land Acquisition (Crown) - CanACRE | 0.33943
| Land Acquisition (Crown) - Fees | 2.448
| Land Acquisition (Crown) - Internal labo | 0.2731
| Land Acquisition (Private) - CanACRE | 1.8523
| Land Acquisition (Private) - Fees | 4.9784
| Land Acquisition (Private) - Internal la | 0.29658
| Land permitting - CanACRE | 1.1568
| Market & Timber Valuations | 0.53912
| Project coordination - CanACRE | 0.061635
| Regulatory (External Legal Fee's) | 0.25284
| Surveys - Internal labour | 0.058624
| Surveys costs | 3.1491
| Temporary Work Space (Private) | 1.0795
| Third Party Payments (Agreements) - Fees | 2.0995
| Third Party Payments (Agreements) - Inte | 0.2027
| Trapper Costs | 0.26821
| Open Damage Settlements, permitting, and project coordination - CanACRE | 0.59095
04. Land Rights (excludes Aboriginal) Total |  | 23.3305
05. Indigenous Economic Participation | 28.2 Land Permits - External legal fees | 0.2
| 28.2 Land Permits - MFN | 0.9
| 28.2 Land Permits -ppfn | 1
| AGLP fees | 2
| Bonus fees - MNO | 1.6
| Indigenous Benefits - BLP | 2.7
| Indigenous Benefits - Consultants | 0.1
| Indigenous Benefits - External legal fee | 0.4
| Indigenous Benefits - Internal labour | 0.2
| Indigenous Benefits - MNO | 1.3
05. Indigenous Economic Participation Total |  | 10.4
06. Indigenous Consultation | Capacity Funding Agreements - Consultati | 2.4099
| Capacity Funding Agreements - Fees | 0.17283
| Community Investments - Fees | 0.00027
| Community Investments - Internal labour | 0.0066104
| Construction Phase Management Support - | 0.11658
| Education & Training - Consultants | 1.6279
| Education & Training - Fees | 6e-05
| Education & Training - Internal labour | 0.0066875
| Indigenous Capacity Support - Capacity p | 7.2143
| Indigenous Capacity Support - Consultant | 0.10817
| Indigenous Capacity Support - External l | -0.0038583
| Indigenous Capacity Support - Fees | 0.010463
| Indigenous Capacity Support - Internal L | 0.18938
| Indigenous monitors and tours - Aborigin | 1.5716
| Indigenous monitors and tours - External | 0.022716
| Indigenous monitors and tours - Internal | 0.22951
06. Indigenous Consultation Total |  | 13.6831
07. Other Consultation | Administration - Internal labour | 0.4
| Community Investments - External costs | 0.1
| Engagement events - Internal labour | 0.1
| Government Relations | 0.8
| Notices and newsletters - External costs | 0.3
07. Other Consultation Total |  | 1.7
08. Site Clearing, Access | E&C Atwell | 1.8096
| Valard Construction - Civil Work | 135.3888
08. Site Clearing, Access Total |  | 137.1984
09. Construction | E&C NEER - NEER Internal Labor | 6.9029
| NEER - NEER Construction Services | 8.7897
| NEER - NEER Internal Expense | 0.39579
| Valard Construction - Conductor, OPGW/OH | 86.9734
| Valard Construction - Contractor G&A, Mo | 19.4534
| Valard Construction - Foundations | 122.3047
| Valard Construction - Material Managemen | 7.7489
| Valard Construction - Project Management | 45.8828
| Valard Construction - Reimbursables | 0.35358
| Valard Construction - Structures | 99.5588
09. Construction Total |  | 398.3641
10. Site Remediation | Neutral Footprint | 1
| Site Rem Yards | 10.3
| Site Remediation Env Inspection | 0.8
| Site Remediation Internal Time | 0.1
10. Site Remediation Total |  | 12.2
12. Regulatory | BZA Appeal/Judicial review - Legal | 0.12438
| BZA Appeal/Judicial review-Travel/accomo | 0.00017921
| Crossing application support - Aird & Be | 0.0020277
| Expropriation application (s. 99 OEB Act | 0.0023297
| General regulatory support - Aird & Berl | 0.34476
| General regulatory support - Experts | 0.16363
| General regulatory support - Travel/acco | 0.022694
| Land support (not including expropriatio | 0.027081
| Leave to construct (including intervenor | 1.0346
| Rate case application - Aird & Berlis | 0.5177
| Rate case application - Travel | 0.006841
| Reg BZA Matter - Internal Labour | 0.0068449
| Reg Crossing application support - Inter | 0.0055008
| Reg Expropriation application (s. 99 OEB | 0.035785
| Reg General regulatory support - Interna | 0.68023
| Reg Land support (not including expropri | 0.089016
| Reg Leave to construct (including interv | 0.88285
| Reg Rate case application - hearing intervenor | 0.20291
| Reg Rate case application - Internal la | 1.3281
12. Regulatory Total |  | 5.4774
13. EWT Management | Monthly Reporting/Accounting - external | 0.075982
| OEB Reporting - external consultant | 0.052358
| Office expenses | 0.2442
| Operations & Maintenance - field office | 0.11236
| Operations & Maintenance - field visit | 0.022261
| Operations & Maintenance - Ops lead | 0.3821
| Operations & Maintenance - Studies/prepa | 0.12627
| PMO Interconnection studies - internal l | 0.0053096
| PMO Monthly Reporting/Accounting - inter | 1.4603
| PMO OEB Reporting - internal labour | 0.032526
| PMO Project Management - internal labour | 2.2621
| Project Management - employees T&E | 0.060578
| Project Management - external consultant | 0.7503
| Project Management - government relation | 0.032882
| Regulatory Support - external consultant | -0.17489
| Regulatory Support - internal labour | 0.067334
| Year-end Audit - audit fees | 0.25313
13. EWT Management Total |  | 5.7651
14. Interest During Construction | IDC - construction | 31.3
14. Interest During Construction Total |  | 31.3
Grand Total |  | 737.1946

## CCVA & COVID
Period/Year |  | JAN 2019 - MAY 2023
Company Hierarchy (Auth) |  | CH2TRANS NEE Transmission
Source (CC=10; IO=15; PS=20) |  | Project System
Inputs (S)/Outputs (H) |  | S Inputs
Account(s)
#N/A
Amount-Obj Currency
WBS-Project |  | WBS | Time-Year | 2020 | 2021 | 2022 | 2023
P-4921 | Const Var: NextBridge Construction Final | P-4921-001-09 | Carrying Charge IDC | 134.8 | 133286.83 | 291655.91 |  | IDC on CCVA & last month const's IDC (outside of Rate Case Amount)
|  | P-4921-002-09 | Const Var: Valard Construction - Contrac |  |  | 10133021 |  | Delays
|  | P-4921-002-12 | Const var: Cama Cliffs |  | 9091759.47 | 2977976 |  | Kama Cliffs
|  | P-4921-002-13 | Const var: Forest Fire Construct shutdn |  | 20526459 | 282805 |  | Wildfire
|  | P-4921-003-03 | White Lake Narrow E&C |  |  | 3961420 |  | White Lake Narrows (E&C Valard)
|  | P-4921-003-04 | White Lake Narrow Environmental | 349481.83 | 66718.65 | 82713.41 | -7294.19 | White Lake Narrows (Enviro - Non Valard)
|  | P-4921-003-05 | White Lake Narrow First Nations | 79686.48 |  | 300000 |  | White Lake Narrows (First Nations - Pic Mobert)
|  | P-4921-005-03 | Const Var: Other - BZA Settlement |  | 420000 |  |  | BZA Settlement
P-4837 | COVID-19 | P-4837-001-01 | Eng and Const NEER COVID |  | 0 | 77930 |  | TDI
|  | P-4837-002-01 | Eng and Const Valard COVID |  |  | 110600206 |  | Valard
|  | P-4837-005-01 | FNM Consultation COVID | 126869.26 | -126869.26 | 384110.66 |  | First Nations Consultation (Supercom)
|  | P-4837-006-01 | FNM Participation COVID | 293915.01 | -293915.01 | 640906.56 |  | First Nations Participation (Atwell)
|  | P-4837-009-01 | PMO COVID | 28.24 | -28.24 | -7118.29 |  | Other
|  | P-4837-011-01 | Carry Charge IDC COVID | 295.79 | -295.79 | 7346.8 |  | IDC on COVID & last month const's IDC (outside of Rate Case Amount)

## Development and Phase Shift
|  |  | Permanent | Permanent | Permanent | Permanent | Permanent
|  |  | Designation Decision | All other Development Costs | $5.3M | Write off | $5.3M
|  |  | Reclassed from P-3217 | Reclassed from P-2156 | Reduce Dev | Reduce Dev | Phase Shift
P-4480-001-01 | Development cost | Engineering and Construction - NEER | 8.7125 | 1.5509
P-4480-001-02 | Write - Off | Engineering and Construction - NEER |  |  |  | -0.77147
P-4480-002-01 | Development cost | Engineering and Construction - Valard
P-4480-002-02 | Write - Off | Engineering and Construction - Valard
P-4480-003-01 | Development cost | Environmental | 4.1141 | 3.7884 | -0.46
P-4480-003-02 | Write - Off | Environmental |  |  |  | -1.1494 | 0.46
P-4480-004-01 | Development cost | Land | 2.1905 | 3.61 | -1.439
P-4480-004-02 | Write - Off | Land |  |  |  | -0.0069041
P-4480-004-03 | Land Acquisition (Private) - Internal la | Land |  |  |  |  | 0.20368
P-4480-004-04 | Land Acquisition (Private) - CanACRE | Land |  |  |  |  | 1.2353
P-4480-005-01 | Development cost | FNM - Consultation Support | 1.9911 | 1.2629
P-4480-005-02 | Write - Off | FNM - Consultation Support |  |  |  | -0.0077728
P-4480-006-01 | Development cost | FNM - Participation |  | 3.4322 | -3.4322
P-4480-006-02 | Write - Off | FNM - Participation
P-4480-006-05 | Indigenous Benefits - BLP | FNM - Participation |  |  |  |  | 3.4154
P-4480-006-06 | Indigenous Benefits - Consultants | FNM - Participation |  |  |  |  | 0.017
P-4480-007-01 | Development cost | Stakeholder Relations | 0.9195 | 0.66752
P-4480-007-02 | Write - Off | Stakeholder Relations |  |  |  | -0.17342
P-4480-008-01 | Development cost | Regulatory | 0.93021 | 0.94328
P-4480-008-02 | Write - Off | Regulatory |  |  |  | -0.11427
P-4480-009-01 | Development cost | PMO | 3.5401 | 1.5106
P-4480-009-02 | Write - Off | PMO |  |  |  | -1.1024
P-4480-010-01 | Development cost | Other costs |  | 0.23016
P-4480-010-02 | Write - Off | Other costs |  |  |  | -0.35152
P-4480-011-01 | Development cost | Carrying charges |  | 0.85547
P-4480-011-02 | Write - Off | Carrying charges
Total |  |  | 22.398 | 17.8515 | -5.3312 | -3.6773 | 5.3314 | 8.886
|  |  | Development Spend | 40.2495
|  |  | Construction Cost eligible | -5.3312 | -9.0085
|  |  | Write off | -3.6773
|  |  | Ending Balance After Write Off | 31.241
|  |  | Actual Development Costs | 40.2495
|  |  | Allow Dev costs - Beg bal CWIP | 31.241 | Include Carry Costs
|  |  | Write-off | -9.0085

## P-3217 and P-2156 Pivot
See P-3217_$22.4M_Detail |  |  |  | See P-2156 thru 7-17_Detail
Column X | Column J | Column K | Sum of Value in Obj. Crcy | Column V | Column W | Column I | Column J | Sum of Value in Obj. Crcy
(empty) | (empty) | (empty) |  | (empty) | (empty) | (empty) | (empty)
(empty) Result |  |  |  | (empty) Result
Total Result |  |  |  | Total Result

## Land
Incremental land optioning negotiations | Time | Staff Expenses | External parties | TOTALS
Engineering & construction |  |  |  | 0
Environment |  |  |  | 0
Land | 95584.2685 | 108098.5804 |  | 203682.8489
CanACRE |  |  | 1257702.8255 | 1235316.8255
First Nation Métis |  |  |  | 0
Stakeholder relations |  |  |  | 0
Regulatory |  |  |  | 0
Project Management office |  |  |  | 0
TOTAL | 95584.2685 | 108098.5804 | 1257702.8255 | 1438999.6744
Budget |  |  |  | 460000