[11 empty] | WF6_3001 | C248 | YES | 0.10687 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 70 | C247-C249 | 1 | 0 | 0 | 0
[11 empty] | WF6_3009 | C248 | YES | 0.084072 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 70 | C247-C249 | 1 | 0 | 0 | 0
[11 empty] | WF6_3011 | C248 | NO | 0.17658 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 70 | C247-C249 | 1 | 0 | 0 | 0
[11 empty] | WF6_7171 | C248 | NO | 0.017446 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 70 | C247-C249 | 1 | 0 | 0 | 0
[11 empty] | WF6_3010 | C248 | NO | 0.23504 |  | Harvest Disposal | Mulch |  | 6 | 70 | C247-C249 | 1 | 0 | 0 | 0
[11 empty] | WF6_3003 | C248 | NO | 1.2176 |  | Non Productive | Non-Treed |  | 6 | 70 | C247-C249 | 1 | 0 | 0 | 0
[11 empty] | WF6_3000 | C248 | YES | 0.0566 |  | Retention | Retention |  | 6 | 70 | C247-C249 | 1 | 0 | 0 | 8
[11 empty] | WF6_3006 | C248 | NO | 0.24969 |  | Retention | Retention |  | 6 | 70 | C247-C249 | 1 | 0 | 0 | 8
[11 empty] | WF6_3007 | C248 | YES | 0.034938 |  | Retention | Retention |  | 6 | 70 | C247-C249 | 1 | 0 | 0 | 8
[11 empty] | WF6_3012 | C248 | NO | 0.24434 |  | Retention | Retention |  | 6 | 70 | C247-C249 | 1 | 0 | 0 | 8
[11 empty] | WF6_7855 | C248 | NO | 0.17318 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 70 | C247-C249 | 1 | 0 | 0 | 0
[11 empty] | WF6_2958 | C248 | NO | 0.011688 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 70 | C247-C249 | 0 | 1 | 0 | 0
[11 empty] | WF6_3013 | C249 | NO | 0.12578 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 72 | C249-C251 | 1 | 0 | 0 | 0
[11 empty] | WF6_7172 | C249 | NO | 0.020875 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 72 | C249-C251 | 1 | 0 | 0 | 0
[11 empty] | WF6_7173 | C249 | NO | 0.42735 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 72 | C249-C251 | 1 | 0 | 0 | 0
[11 empty] | WF6_2942 | C249 | NO | 0.32899 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 71 | C247-C249 | 0 | 1 | 0 | 0
[11 empty] | WF6_2968 | C249 | NO | 0.02996 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 71 | C247-C249 | 0 | 1 | 0 | 0
[11 empty] | WF6_2968 | C249 | NO | 0.71442 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 72 | C249-C251 | 0 | 1 | 0 | 0
[11 empty] | WF6_2968 | C249 | NO | 0.767 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 72 | C249-C251 | 0 | 1 | 0 | 0
[11 empty] | WF6_3010 | C249 | NO | 0.64808 |  | Harvest Disposal | Mulch |  | 6 | 72 | C249-C251 | 1 | 0 | 0 | 0
[11 empty] | WF6_3014 | C249 | NO | 0.53263 |  | Harvest Disposal | Mulch |  | 6 | 72 | C249-C251 | 1 | 0 | 0 | 0
[11 empty] | WF6_3015 | C249 | NO | 0.093906 |  | Retention | Retention |  | 6 | 72 | C249-C251 | 1 | 0 | 0 | 8
[11 empty] | WF6_6516 | C249 | NO | 0.01259 |  | Retention | Retention |  | 6 | 72 | C249-C251 | 1 | 0 | 0 | 8
[11 empty] | WF6_7283 | C249 | NO | 0.021136 |  | Retention | Retention |  | 6 | 72 | C249-C251 | 1 | 0 | 0 | 8
[11 empty] | WF6_7284 | C249 | NO | 0.058701 |  | Retention | Retention |  | 6 | 72 | C249-C251 | 1 | 0 | 0 | 8
[11 empty] | WF6_7174 | C250 | NO | 1.1359 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 72 | C249-C251 | 1 | 0 | 0 | 0
[11 empty] | WF6_7175 | C250 | NO | 0.054772 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 72 | C249-C251 | 1 | 0 | 0 | 0
[11 empty] | WF6_3014 | C250 | NO | 0.39443 |  | Harvest Disposal | Mulch |  | 6 | 72 | C249-C251 | 1 | 0 | 0 | 0
[11 empty] | WF6_3017 | C250 | NO | 0.15519 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 72 | C249-C251 | 0 | 1 | 0 | 0
[11 empty] | WF6_3025 | C250 | NO | 0.26099 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 72 | C249-C251 | 0 | 1 | 0 | 0
[11 empty] | WF6_3020 | C250 | NO | 0.26188 |  | Retention | Retention |  | 6 | 72 | C249-C251 | 1 | 0 | 0 | 8
[11 empty] | WF6_7737 | C250 | NO | 0.54869 |  | Harvest Disposal | Mulch |  | 6 | 72 | C249-C251 | 1 | 0 | 0 | 0
[11 empty] | WF6_7873 | C250 | NO | 0.029525 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 72 | C249-C251 | 1 | 0 | 0 | 0
[11 empty] | WF6_3021 | C251 | NO | 0.030383 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 73 | C251-C253 | 1 | 0 | 0 | 0
[11 empty] | WF6_6302 | C251 | NO | 0.019707 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 73 | C251-C253 | 1 | 0 | 0 | 0
[11 empty] | WF6_6303 | C251 | NO | 0.028065 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 73 | C251-C253 | 1 | 0 | 0 | 0
[11 empty] | WF6_6358 | C251 | NO | 0.2456 |  | Harvest Disposal | Mulch |  | 6 | 73 | C251-C253 | 1 | 0 | 0 | 0
[11 empty] | WF6_6359 | C251 | NO | 0.032567 |  | Harvest Disposal | Mulch |  | 6 | 73 | C251-C253 | 1 | 0 | 0 | 0
[11 empty] | WF6_7071 | C251 | NO | 0.63388 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 73 | C251-C253 | 1 | 0 | 0 | 0
[11 empty] | WF6_7176 | C251 | NO | 0.037882 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 73 | C251-C253 | 1 | 0 | 0 | 0
[11 empty] | WF6_7177 | C251 | NO | 0.028593 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 73 | C251-C253 | 1 | 0 | 0 | 0
[11 empty] | WF6_7178 | C251 | NO | 0.23923 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 73 | C251-C253 | 1 | 0 | 0 | 0
[11 empty] | WF6_7244 | C251 | NO | 0.023615 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 73 | C251-C253 | 1 | 0 | 0 | 0
[11 empty] | WF6_3017 | C251 | NO | 0.45314 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 73 | C251-C253 | 0 | 1 | 0 | 0
[11 empty] | WF6_3022 | C251 | NO | 0.5587 |  | Harvest Disposal | Mulch |  | 6 | 73 | C251-C253 | 1 | 0 | 0 | 0
[11 empty] | WF6_3019 | C251 | NO | 0.056078 |  | Retention | Retention |  | 6 | 73 | C251-C253 | 1 | 0 | 0 | 8
[11 empty] | WF6_3023 | C251 | NO | 0.13838 |  | Retention | Retention |  | 6 | 73 | C251-C253 | 1 | 0 | 0 | 8
[11 empty] | WF6_3024 | C251 | NO | 0.030306 |  | Retention | Retention |  | 6 | 73 | C251-C253 | 1 | 0 | 0 | 8
[11 empty] | WF6_3027 | C251 | NO | 0.096388 |  | Retention | Retention |  | 6 | 73 | C251-C253 | 1 | 0 | 0 | 8
[11 empty] | WF6_7285 | C251 | NO | 0.016608 |  | Retention | Retention |  | 6 | 73 | C251-C253 | 1 | 0 | 0 | 8
[11 empty] | WF6_3035 | C252 | NO | 0.041736 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 73 | C251-C253 | 1 | 0 | 0 | 0
[11 empty] | WF6_7243 | C252 | NO | 0.049184 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 73 | C251-C253 | 1 | 0 | 0 | 0
[11 empty] | WF6_7245 | C252 | NO | 0.023093 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 73 | C251-C253 | 1 | 0 | 0 | 0
[11 empty] | WF6_7246 | C252 | NO | 0.052251 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 73 | C251-C253 | 1 | 0 | 0 | 0
[11 empty] | WF6_7247 | C252 | NO | 0.013689 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 73 | C251-C253 | 1 | 0 | 0 | 0
[11 empty] | WF6_3004 | C252 | NO | 0.3271 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 73 | C251-C253 | 0 | 1 | 0 | 0
[11 empty] | WF6_3004 | C252 | NO | 0.29116 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 73 | C251-C253 | 0 | 1 | 0 | 0
[11 empty] | WF6_3004 | C252 | NO | 0.734 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 73 | C251-C253 | 0 | 1 | 0 | 0
[11 empty] | WF6_3028 | C252 | NO | 1.3814 |  | Harvest Processing | Non-Mulch |  | 6 | 73 | C251-C253 | 1 | 0 | 0 | 0
[11 empty] | WF6_3033 | C252 | NO | 0.11157 |  | Harvest Processing | Non-Mulch |  | 6 | 73 | C251-C253 | 1 | 0 | 0 | 0
[11 empty] | WF6_3030 | C252 | NO | 0.37947 |  | Retention | Retention |  | 6 | 73 | C251-C253 | 1 | 0 | 0 | 8
[11 empty] | WF6_3031 | C252 | NO | 0.056496 |  | Retention | Retention |  | 6 | 73 | C251-C253 | 1 | 0 | 0 | 8
[11 empty] | WF6_6517 | C252 | NO | 0.05309 |  | Retention | Retention |  | 6 | 73 | C251-C253 | 1 | 0 | 0 | 8
[11 empty] | WF6_7286 | C252 | NO | 0.090153 |  | Retention | Retention |  | 6 | 73 | C251-C253 | 1 | 0 | 0 | 8
[11 empty] | WF6_7287 | C252 | NO | 0.068876 |  | Retention | Retention |  | 6 | 73 | C251-C253 | 1 | 0 | 0 | 8
[11 empty] | WF6_7738 | C252 | NO | 0.090328 |  | Harvest Disposal | Mulch |  | 6 | 73 | C251-C253 | 1 | 0 | 0 | 0
[11 empty] | WF6_7874 | C252 | NO | 0.16385 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 73 | C251-C253 | 1 | 0 | 0 | 0
[11 empty] | WF6_7882 | C252 | NO | 0.075291 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 73 | C251-C253 | 1 | 0 | 0 | 0
[11 empty] | WF6_3004 | C252 | NO | 0.015367 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 73 | C251-C253 | 0 | 1 | 0 | 0
[11 empty] | WF6_3039 | C253 | NO | 0.047705 |  | Harvest Disposal | Mulch |  | 6 | 74 | C253-C255 | 1 | 0 | 0 | 0
[11 empty] | WF6_3043 | C253 | NO | 0.013592 |  | Harvest Processing | Non-Mulch |  | 6 | 74 | C253-C255 | 1 | 0 | 0 | 0
[11 empty] | WF6_3038 | C253 | NO | 0.029533 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 74 | C253-C255 | 1 | 0 | 0 | 0
[11 empty] | WF6_3042 | C253 | YES | 0.11722 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 74 | C253-C255 | 1 | 0 | 0 | 0
[11 empty] | WF6_3037 | C253 | NO | 0.032564 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 74 | C253-C255 | 1 | 0 | 0 | 0
[11 empty] | WF6_7248 | C253 | NO | 0.011782 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 74 | C253-C255 | 1 | 0 | 0 | 0
[11 empty] | WF6_7249 | C253 | NO | 0.05737 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 74 | C253-C255 | 1 | 0 | 0 | 0
[11 empty] | WF6_3004 | C253 | NO | 0.18485 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 73 | C251-C253 | 0 | 1 | 0 | 0
[11 empty] | WF6_3004 | C253 | NO | 0.1091 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 74 | C253-C255 | 0 | 1 | 0 | 0
[11 empty] | WF6_3004 | C253 | NO | 0.49732 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 74 | C253-C255 | 0 | 1 | 0 | 0
[11 empty] | WF6_3004 | C253 | NO | 0.11953 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 74 | C253-C255 | 0 | 1 | 0 | 0
[11 empty] | WF6_3034 | C253 | NO | 0.12847 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 74 | C253-C255 | 0 | 1 | 0 | 0
[11 empty] | WF6_6198 | C253 | NO | 0.22835 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 74 | C253-C255 | 0 | 1 | 0 | 0
[11 empty] | WF6_3033 | C253 | NO | 1.0471 |  | Harvest Processing | Non-Mulch |  | 6 | 74 | C253-C255 | 1 | 0 | 0 | 0
[11 empty] | WF6_3036 | C253 | NO | 0.32301 |  | Retention | Retention |  | 6 | 74 | C253-C255 | 1 | 0 | 0 | 8
[11 empty] | WF6_3041 | C253 | NO | 0.29741 |  | Retention | Retention |  | 6 | 74 | C253-C255 | 1 | 0 | 0 | 8
[11 empty] | WF6_3004 | C253 | NO | 0.015367 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 73 | C251-C253 | 0 | 1 | 0 | 0
[11 empty] | WF6_3046 | C254 | NO | 0.22395 |  | Harvest Disposal | Mulch |  | 6 | 74 | C253-C255 | 1 | 0 | 0 | 0
[11 empty] | WF6_3040 | C254 | NO | 1.4545 |  | Harvest Processing | Non-Mulch |  | 6 | 74 | C253-C255 | 1 | 0 | 0 | 0
[11 empty] | WF6_3034 | C254 | NO | 0.10611 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 74 | C253-C255 | 0 | 1 | 0 | 0
[11 empty] | WF6_6198 | C254 | NO | 0.29671 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 74 | C253-C255 | 0 | 1 | 0 | 0
[11 empty] | WF6_6198 | C254 | NO | 0.52547 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 74 | C253-C255 | 0 | 1 | 0 | 0
[11 empty] | WF6_3044 | C254 | NO | 0.067405 |  | Retention | Retention |  | 6 | 74 | C253-C255 | 1 | 0 | 0 | 8
[11 empty] | WF6_3045 | C254 | NO | 0.083102 |  | Retention | Retention |  | 6 | 74 | C253-C255 | 1 | 0 | 0 | 8
[11 empty] | WF6_3048 | C254 | NO | 0.069259 |  | Retention | Retention |  | 6 | 74 | C253-C255 | 1 | 0 | 0 | 8
[11 empty] | WF6_8197 | C254 | NO | 0.057505 |  | Hand Fall / Lop and Scatter | Mulch |  | 6 | 74 | C253-C255 | 1 | 0 | 0 | 0
[11 empty] | WF6_7661 | C254 | NO | 0.036359 |  | Harvest Processing | Non-Mulch |  | 6 | 74 | C253-C255 | 1 | 0 | 0 | 0
[11 empty] | WF6_7536 | C254 | NO | 0.053333 |  | Harvest Disposal | Mulch |  | 6 | 74 | C253-C255 | 1 | 0 | 0 | 0
[11 empty] | WF6_8228 | C254 | NO | 0.037762 |  | Harvest Disposal | Mulch |  | 6 | 74 | C253-C255 | 1 | 0 | 0 | 0
[11 empty] | WF6_8229 | C254 | NO | 0.095963 |  | Hand Fall / Lop and Scatter | Mulch |  | 6 | 74 | C253-C255 | 1 | 0 | 0 | 0
[11 empty] | WF6_7538 | C255 | NO | 1.4538 |  | Harvest Disposal | Mulch |  | 6 | 75 | C255-C257 | 1 | 0 | 0 | 0
[11 empty] | WF6_8230 | C255 | NO | 0.16305 |  | Hand Fall / Lop and Scatter | Mulch |  | 6 | 75 | C255-C257 | 1 | 0 | 0 | 0
[11 empty] | WF6_3049 | C256 | NO | 0.22973 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 75 | C255-C257 | 1 | 0 | 0 | 0
[11 empty] | WF6_3052 | C256 | NO | 0.44079 |  | Harvest Disposal | Mulch |  | 6 | 75 | C255-C257 | 1 | 0 | 0 | 0
[11 empty] | WF6_3056 | C256 | NO | 0.16953 |  | Harvest Disposal | Mulch |  | 6 | 75 | C255-C257 | 1 | 0 | 0 | 0
[11 empty] | WF6_3055 | C256 | NO | 0.10409 |  | Non Productive | Non-Treed |  | 6 | 75 | C255-C257 | 1 | 0 | 0 | 0
[11 empty] | WF6_3050 | C256 | NO | 0.5416 |  | Retention | Retention |  | 6 | 75 | C255-C257 | 1 | 0 | 0 | 8
[11 empty] | WF6_3054 | C256 | NO | 0.39417 |  | Retention | Retention |  | 6 | 75 | C255-C257 | 1 | 0 | 0 | 8
[11 empty] | WF6_3057 | C256 | NO | 0.032888 |  | Retention | Retention |  | 6 | 75 | C255-C257 | 1 | 0 | 0 | 8
[11 empty] | WF6_8198 | C256 | NO | 0.17061 |  | Hand Fall / Lop and Scatter | Mulch |  | 6 | 75 | C255-C257 | 1 | 0 | 0 | 0
[11 empty] | WF6_7537 | C256 | NO | 0.058296 |  | Harvest Disposal | Mulch |  | 6 | 75 | C255-C257 | 1 | 0 | 0 | 0
[11 empty] | WF6_7179 | C257 | NO | 0.79644 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 76 | C257-C259 | 1 | 0 | 0 | 0
[11 empty] | WF6_3053 | C257 | NO | 0.34647 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 76 | C257-C259 | 0 | 1 | 0 | 0
[11 empty] | WF6_3056 | C257 | NO | 0.54854 |  | Harvest Disposal | Mulch |  | 6 | 76 | C257-C259 | 1 | 0 | 0 | 0
[11 empty] | WF6_7875 | C257 | NO | 0.029992 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 76 | C257-C259 | 1 | 0 | 0 | 0
[11 empty] | WF6_3062 | C258 | YES | 0.03107 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 76 | C257-C259 | 1 | 0 | 0 | 0
[11 empty] | WF6_6304 | C258 | YES | 0.03026 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 76 | C257-C259 | 1 | 0 | 0 | 0
[11 empty] | WF6_6360 | C258 | NO | 0.33292 |  | Harvest Disposal | Mulch |  | 6 | 76 | C257-C259 | 1 | 0 | 0 | 0
[11 empty] | WF6_7072 | C258 | YES | 0.40191 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 76 | C257-C259 | 1 | 0 | 0 | 0
[11 empty] | WF6_7180 | C258 | NO | 0.92001 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 76 | C257-C259 | 1 | 0 | 0 | 0
[11 empty] | WF6_7250 | C258 | NO | 0.079551 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 76 | C257-C259 | 1 | 0 | 0 | 0
[11 empty] | WF6_3053 | C258 | NO | 0.16918 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 76 | C257-C259 | 0 | 1 | 0 | 0
[11 empty] | WF6_3060 | C258 | NO | 0.14208 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 76 | C257-C259 | 0 | 1 | 0 | 0
[11 empty] | WF6_3063 | C258 | NO | 0.23088 |  | Harvest Processing | Non-Mulch |  | 6 | 76 | C257-C259 | 1 | 0 | 0 | 0
[11 empty] | WF6_3059 | C258 | NO | 0.13929 |  | Retention | Retention |  | 6 | 76 | C257-C259 | 1 | 0 | 0 | 8
[11 empty] | WF6_3070 | C259 | YES | 0.40056 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 77 | C259-C261 | 1 | 0 | 0 | 0
[11 empty] | WF6_3064 | C259 | YES | 0.20371 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 77 | C259-C261 | 1 | 0 | 0 | 0
[11 empty] | WF6_3066 | C259 | YES | 0.94426 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 77 | C259-C261 | 1 | 0 | 0 | 0
[11 empty] | WF6_3069 | C259 | YES | 0.02957 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 77 | C259-C261 | 1 | 0 | 0 | 0
[11 empty] | WF6_7251 | C259 | NO | 0.10634 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 77 | C259-C261 | 1 | 0 | 0 | 0
[11 empty] | WF6_3058 | C259 | NO | 0.70497 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 77 | C259-C261 | 0 | 1 | 0 | 0
[11 empty] | WF6_3063 | C259 | NO | 0.17497 |  | Harvest Processing | Non-Mulch |  | 6 | 77 | C259-C261 | 1 | 0 | 0 | 0
[11 empty] | WF6_3072 | C259 | NO | 0.039219 |  | Harvest Processing | Non-Mulch |  | 6 | 77 | C259-C261 | 1 | 0 | 0 | 0
[11 empty] | WF6_3065 | C259 | YES | 0.059874 |  | Non Productive | Non-Treed |  | 6 | 77 | C259-C261 | 1 | 0 | 0 | 0
[11 empty] | WF6_3068 | C259 | YES | 0.24989 |  | Non Productive | Non-Treed |  | 6 | 77 | C259-C261 | 1 | 0 | 0 | 0
[11 empty] | WF6_7271 | C259 | YES | 0.023112 |  | Non Productive | Non-Treed |  | 6 | 77 | C259-C261 | 1 | 0 | 0 | 0
[11 empty] | WF6_7272 | C259 | YES | 0.012546 |  | Non Productive | Non-Treed |  | 6 | 77 | C259-C261 | 1 | 0 | 0 | 0
[11 empty] | WF6_7273 | C259 | YES | 0.016072 |  | Non Productive | Non-Treed |  | 6 | 77 | C259-C261 | 1 | 0 | 0 | 0
[11 empty] | WF6_3077 | C260 | YES | 0.33676 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 77 | C259-C261 | 1 | 0 | 0 | 0
[11 empty] | WF6_3085 | C260 | YES | 0.02669 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 77 | C259-C261 | 1 | 0 | 0 | 0
[11 empty] | WF6_7252 | C260 | NO | 0.14151 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 77 | C259-C261 | 1 | 0 | 0 | 0
[11 empty] | WF6_3071 | C260 | NO | 0.47146 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 77 | C259-C261 | 0 | 1 | 0 | 0
[11 empty] | WF6_3072 | C260 | NO | 0.16536 |  | Harvest Processing | Non-Mulch |  | 6 | 77 | C259-C261 | 1 | 0 | 0 | 0
[11 empty] | WF6_3078 | C260 | NO | 0.14023 |  | Harvest Processing | Non-Mulch |  | 6 | 77 | C259-C261 | 1 | 0 | 0 | 0
[11 empty] | WF6_3074 | C260 | YES | 0.10437 |  | Non Productive | Non-Treed |  | 6 | 77 | C259-C261 | 1 | 0 | 0 | 0
[11 empty] | WF6_3075 | C260 | YES | 0.032662 |  | Non Productive | Non-Treed |  | 6 | 77 | C259-C261 | 1 | 0 | 0 | 0
[11 empty] | WF6_3073 | C260 | YES | 0.033663 |  | Retention | Retention |  | 6 | 77 | C259-C261 | 1 | 0 | 0 | 8
[11 empty] | WF6_3076 | C260 | YES | 0.086622 |  | Retention | Retention |  | 6 | 77 | C259-C261 | 1 | 0 | 0 | 8
[11 empty] | WF6_3084 | C260 | YES | 0.1256 |  | Retention | Retention |  | 6 | 77 | C259-C261 | 1 | 0 | 0 | 8
[11 empty] | WF6_7274 | C260 | YES | 0.035372 |  | Non Productive | Non-Treed |  | 6 | 77 | C259-C261 | 1 | 0 | 0 | 0
[11 empty] | WF6_7503 | C260 | YES | 0.35282 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 77 | C259-C261 | 1 | 0 | 0 | 0
[11 empty] | WF6_7253 | C261 | NO | 0.17724 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 78 | C261-C263 | 1 | 0 | 0 | 0
[11 empty] | WF6_6197 | C261 | NO | 0.16646 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 78 | C261-C263 | 0 | 1 | 0 | 0
[11 empty] | WF6_6197 | C261 | NO | 0.015932 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 78 | C261-C263 | 0 | 1 | 0 | 0
[11 empty] | WF6_3071 | C261 | NO | 0.016644 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 78 | C261-C263 | 0 | 1 | 0 | 0
[11 empty] | WF6_3088 | C261 | NO | 0.21985 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 78 | C261-C263 | 0 | 1 | 0 | 0
[11 empty] | WF6_3088 | C261 | NO | 0.026751 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 78 | C261-C263 | 0 | 1 | 0 | 0
[11 empty] | WF6_3078 | C261 | NO | 0.26599 |  | Harvest Processing | Non-Mulch |  | 6 | 78 | C261-C263 | 1 | 0 | 0 | 0
[11 empty] | WF6_3083 | C261 | NO | 0.53253 |  | Harvest Processing | Non-Mulch |  | 6 | 78 | C261-C263 | 0 | 1 | 0 | 0
[11 empty] | WF6_3067 | C261 | NO | 0.71685 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 78 | C261-C263 | 1 | 0 | 0 | 0
[11 empty] | WF6_3082 | C261 | NO | 0.047519 |  | Non Productive | Non-Treed |  | 6 | 78 | C261-C263 | 1 | 0 | 0 | 0
[11 empty] | WF6_3061 | C261 | NO | 0.31596 |  | Retention | Retention |  | 6 | 78 | C261-C263 | 1 | 0 | 0 | 8
[11 empty] | WF6_7254 | C262 | NO | 0.37557 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 78 | C261-C263 | 1 | 1 | 0 | 0
[11 empty] | WF6_3083 | C262 | NO | 1.8222 |  | Harvest Processing | Non-Mulch |  | 6 | 78 | C261-C263 | 0 | 1 | 0 | 0
[11 empty] | WF6_3086 | C262 | NO | 0.6513 |  | Harvest Processing | Non-Mulch |  | 6 | 78 | C261-C263 | 1 | 0 | 0 | 0
[11 empty] | WF6_3087 | C262 | NO | 0.38347 |  | Retention | Retention |  | 6 | 78 | C261-C263 | 1 | 0 | 0 | 8
[11 empty] | WF6_3083 | C263 | NO | 2.2285 |  | Harvest Processing | Non-Mulch |  | 6 | 79 | C263-C265 | 0 | 1 | 0 | 0
[11 empty] | WF6_6207 | C264 | NO | 0.017191 |  | Non-Merch Disposal | Mulch | AU2 | 6 | 79 | C263-C265 | 0 | 1 | 0 | 0
[11 empty] | WF6_6361 | C264 | NO | 0.18422 |  | Non-Merch Disposal | Mulch | AU2 | 6 | 80 | C263-C265 | 0 | 1 | 0 | 0
[11 empty] | WF6_6409 | C264 | NO | 0.017019 |  | Non-Merch Disposal | Mulch | AU2 | 6 | 79 | C263-C265 | 0 | 1 | 0 | 0
[11 empty] | WF6_3080 | C264 | NO | 0.17974 |  | Non-Merch Disposal | Mulch | AU2 | 6 | 80 | C263-C265 | 0 | 1 | 0 | 0
[11 empty] | WF6_3089 | C264 | NO | 0.15804 |  | Non-Merch Disposal | Mulch | AU2 | 6 | 79 | C263-C265 | 0 | 1 | 0 | 0
[11 empty] | WF6_3089 | C264 | NO | 0.03102 |  | Non-Merch Disposal | Mulch | AU2 | 6 | 79 | C263-C265 | 0 | 1 | 0 | 0
[11 empty] | WF6_3089 | C264 | NO | 0.033998 |  | Non-Merch Disposal | Mulch | AU2 | 6 | 79 | C263-C265 | 0 | 1 | 0 | 0
[11 empty] | WF6_3089 | C264 | NO | 0.34847 |  | Non-Merch Disposal | Mulch | AU2 | 6 | 80 | C263-C265 | 0 | 1 | 0 | 0
[11 empty] | WF6_3089 | C264 | NO | 0.34471 |  | Non-Merch Disposal | Mulch | AU2 | 6 | 80 | C263-C265 | 0 | 1 | 0 | 0
[11 empty] | WF6_3094 | C264 | NO | 0.058585 |  | Non-Merch Disposal | Mulch | AU2 | 6 | 79 | C263-C265 | 0 | 1 | 0 | 0
[11 empty] | WF6_3095 | C264 | NO | 0.60782 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 79 | C263-C265 | 0 | 1 | 0 | 0
[11 empty] | WF6_6124 | C264 | NO | 0.060172 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 79 | C263-C265 | 0 | 1 | 0 | 0
[11 empty] | WF6_3083 | C264 | NO | 2.2328 |  | Harvest Processing | Non-Mulch |  | 6 | 79 | C263-C265 | 0 | 1 | 0 | 0
[11 empty] | WF6_3093 | C264 | NO | 0.075216 |  | Harvest Processing | Non-Mulch |  | 6 | 79 | C263-C265 | 1 | 0 | 0 | 0
[11 empty] | WF6_3095 | C265 | NO | 0.080845 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 79 | C263-C265 | 0 | 1 | 0 | 0
[11 empty] | WF6_3095 | C265 | NO | 0.51692 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 81 | C265-C267 | 0 | 1 | 0 | 0
[11 empty] | WF6_3083 | C265 | NO | 0.023785 |  | Harvest Processing | Non-Mulch |  | 6 | 79 | C263-C265 | 0 | 1 | 0 | 0
[11 empty] | WF6_3083 | C265 | NO | 1.8436 |  | Harvest Processing | Non-Mulch |  | 6 | 81 | C265-C267 | 0 | 1 | 0 | 0
[11 empty] | WF6_3093 | C265 | NO | 0.020131 |  | Harvest Processing | Non-Mulch |  | 6 | 81 | C265-C267 | 1 | 0 | 0 | 0
[11 empty] | WF6_3096 | C265 | NO | 0.95963 |  | Harvest Processing | Non-Mulch |  | 6 | 81 | C265-C267 | 1 | 0 | 0 | 0
[11 empty] | WF6_3097 | C266 | YES | 0.02262 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 81 | C265-C267 | 1 | 0 | 0 | 0
[11 empty] | WF6_6469 | C266 | NO | 0.65416 |  | Harvest Processing | Non-Mulch |  | 6 | 81 | C265-C267 | 1 | 0 | 0 | 0
[11 empty] | WF6_7073 | C266 | YES | 0.42019 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 81 | C265-C267 | 1 | 0 | 0 | 0
[11 empty] | WF6_7255 | C266 | NO | 0.29261 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 81 | C265-C267 | 1 | 0 | 0 | 0
[11 empty] | WF6_7256 | C266 | NO | 0.083269 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 81 | C265-C267 | 1 | 0 | 0 | 0
[11 empty] | WF6_3101 | C266 | NO | 0.61653 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 81 | C265-C267 | 0 | 1 | 0 | 0
[11 empty] | WF6_3101 | C266 | NO | 0.20267 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 82 | C267-C269 | 0 | 1 | 0 | 0
[11 empty] | WF6_3083 | C266 | NO | 0.078606 |  | Harvest Processing | Non-Mulch |  | 6 | 81 | C265-C267 | 0 | 1 | 0 | 0
[11 empty] | WF6_3098 | C266 | NO | 0.014504 |  | Harvest Processing | Non-Mulch |  | 6 | 81 | C265-C267 | 1 | 0 | 0 | 0
[11 empty] | WF6_3099 | C266 | NO | 1.7293 |  | Harvest Processing | Non-Mulch |  | 6 | 81 | C265-C267 | 1 | 0 | 0 | 0
[11 empty] | WF6_3101 | C267 | NO | 0.069658 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 82 | C267-C269 | 0 | 1 | 0 | 0
[11 empty] | WF6_3102 | C267 | NO | 0.087093 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 82 | C267-C269 | 0 | 1 | 0 | 0
[11 empty] | WF6_3099 | C267 | NO | 2.5336 |  | Harvest Processing | Non-Mulch |  | 6 | 82 | C267-C269 | 1 | 0 | 0 | 0
[11 empty] | WF6_6195 | C268 | NO | 0.21282 |  | Harvest Disposal | Mulch |  | 6 | 82 | C267-C269 | 1 | 0 | 0 | 0
[11 empty] | WF6_6195 | C268 | NO | 0.011131 |  | Harvest Disposal | Mulch |  | 6 | 83 | C269-C271 | 1 | 0 | 0 | 0
[11 empty] | WF6_3103 | C268 | NO | 0.28329 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 82 | C267-C269 | 0 | 1 | 0 | 0
[11 empty] | WF6_3103 | C268 | NO | 0.26696 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 82 | C267-C269 | 0 | 1 | 0 | 0
[11 empty] | WF6_3103 | C268 | NO | 0.26019 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 82 | C267-C269 | 0 | 1 | 0 | 0
[11 empty] | WF6_3099 | C268 | NO | 1.466 |  | Harvest Processing | Non-Mulch |  | 6 | 82 | C267-C269 | 1 | 0 | 0 | 0
[11 empty] | WF6_3104 | C268 | NO | 0.13755 |  | Retention | Retention |  | 6 | 82 | C267-C269 | 1 | 0 | 0 | 8
[11 empty] | WF6_3105 | C268 | NO | 0.21727 |  | Retention | Retention |  | 6 | 82 | C267-C269 | 1 | 0 | 0 | 8
[11 empty] | WF6_3103 | C268 | NO | 0.024094 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 82 | C267-C269 | 0 | 1 | 0 | 0
[11 empty] | WF6_3103 | C268 | NO | 0.024094 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 82 | C267-C269 | 0 | 1 | 0 | 0
[11 empty] | WF6_7182 | C269 | NO | 0.48098 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 83 | C269-C271 | 1 | 0 | 0 | 0
[11 empty] | WF6_3103 | C269 | NO | 0.053912 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 82 | C267-C269 | 0 | 1 | 0 | 0
[11 empty] | WF6_3103 | C269 | NO | 0.59699 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 83 | C269-C271 | 0 | 1 | 0 | 0
[11 empty] | WF6_3110 | C269 | NO | 0.15953 |  | Non Productive | Non-Treed |  | 6 | 83 | C269-C271 | 1 | 0 | 0 | 0
[11 empty] | WF6_3107 | C269 | NO | 0.2147 |  | Retention | Retention |  | 6 | 83 | C269-C271 | 1 | 0 | 0 | 8
[11 empty] | WF6_3108 | C269 | NO | 0.41261 |  | Retention | Retention |  | 6 | 83 | C269-C271 | 1 | 0 | 0 | 8
[11 empty] | WF6_3109 | C269 | NO | 0.81964 |  | Retention | Retention |  | 6 | 83 | C269-C271 | 1 | 0 | 0 | 8
[11 empty] | WF6_3111 | C269 | NO | 0.022662 |  | Retention | Retention |  | 6 | 83 | C269-C271 | 1 | 0 | 0 | 8
[11 empty] | WF6_7615 | C269 | NO | 0.12929 |  | Harvest Disposal | Mulch |  | 6 | 83 | C269-C271 | 1 | 0 | 0 | 0
[11 empty] | WF6_7616 | C269 | NO | 0.018186 |  | Harvest Disposal | Mulch |  | 6 | 83 | C269-C271 | 1 | 0 | 0 | 0
[11 empty] | WF6_7765 | C269 | NO | 0.57172 |  | Harvest Disposal | Mulch |  | 6 | 83 | C269-C271 | 1 | 0 | 0 | 0
[11 empty] | WF6_6196 | C270 | NO | 0.31075 |  | Harvest Disposal | Mulch |  | 6 | 83 | C269-C271 | 1 | 0 | 0 | 0
[11 empty] | WF6_6421 | C270 | NO | 0.017417 |  | Harvest Disposal | Mulch |  | 6 | 83 | C269-C271 | 1 | 0 | 0 | 0
[11 empty] | WF6_6422 | C270 | NO | 0.12563 |  | Harvest Disposal | Mulch |  | 6 | 83 | C269-C271 | 1 | 0 | 0 | 0
[11 empty] | WF6_7183 | C270 | NO | 1.0783 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 83 | C269-C271 | 1 | 0 | 0 | 0
[11 empty] | WF6_3113 | C270 | NO | 0.35994 |  | Non Productive | Non-Treed |  | 6 | 83 | C269-C271 | 1 | 0 | 0 | 0
[11 empty] | WF6_3114 | C270 | NO | 0.24303 |  | Retention | Retention |  | 6 | 83 | C269-C271 | 1 | 0 | 0 | 8
[11 empty] | WF6_3116 | C270 | NO | 0.082095 |  | Retention | Retention |  | 6 | 83 | C269-C271 | 1 | 0 | 0 | 8
[11 empty] | WF6_7275 | C270 | NO | 0.23762 |  | Non Productive | Non-Treed |  | 6 | 83 | C269-C271 | 1 | 0 | 0 | 0
[11 empty] | WF6_7288 | C270 | NO | 0.32583 |  | Retention | Retention |  | 6 | 83 | C269-C271 | 1 | 0 | 0 | 8
[11 empty] | WF6_3106 | C271 | NO | 0.49092 |  | Harvest Disposal | Mulch |  | 6 | 84 | C271-C273 | 1 | 0 | 0 | 0
[11 empty] | WF6_6362 | C271 | NO | 0.12061 |  | Harvest Disposal | Mulch |  | 6 | 84 | C271-C273 | 1 | 0 | 0 | 0
[11 empty] | WF6_7181 | C271 | NO | 0.5471 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 84 | C271-C273 | 1 | 0 | 0 | 0
[11 empty] | WF6_3115 | C271 | NO | 0.53343 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 84 | C271-C273 | 0 | 1 | 0 | 0
[11 empty] | WF6_3117 | C271 | NO | 0.19151 |  | Retention | Retention |  | 6 | 84 | C271-C273 | 1 | 0 | 0 | 8
[11 empty] | WF6_3118 | C271 | NO | 0.45362 |  | Retention | Retention |  | 6 | 84 | C271-C273 | 1 | 0 | 0 | 8
[11 empty] | WF6_3120 | C272 | NO | 0.10097 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 84 | C271-C273 | 0 | 1 | 0 | 0
[11 empty] | WF6_3122 | C272 | NO | 0.18017 |  | Harvest Processing | Non-Mulch |  | 6 | 84 | C271-C273 | 1 | 0 | 0 | 0
[11 empty] | WF6_3121 | C272 | NO | 0.079516 |  | Non Productive | Non-Treed |  | 6 | 84 | C271-C273 | 1 | 0 | 0 | 0
[11 empty] | WF6_3119 | C272 | NO | 0.1461 |  | Retention | Retention |  | 6 | 84 | C271-C273 | 1 | 0 | 0 | 8
[11 empty] | WF6_3123 | C272 | NO | 0.064273 |  | Retention | Retention |  | 6 | 84 | C271-C273 | 1 | 0 | 0 | 8
[11 empty] | WF6_7739 | C272 | NO | 1.1881 |  | Harvest Disposal | Mulch |  | 6 | 84 | C271-C273 | 1 | 0 | 0 | 0
[11 empty] | WF6_7257 | C273 | NO | 0.013831 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 85 | C273-C275 | 1 | 0 | 0 | 0
[11 empty] | WF6_3122 | C273 | NO | 1.8311 |  | Harvest Processing | Non-Mulch |  | 6 | 85 | C273-C275 | 1 | 0 | 0 | 0
[11 empty] | WF6_3124 | C274 | NO | 0.012373 |  | Harvest Processing | Non-Mulch |  | 6 | 85 | C273-C275 | 1 | 0 | 0 | 0
[11 empty] | WF6_6470 | C274 | NO | 1.9185 |  | Harvest Processing | Non-Mulch |  | 6 | 85 | C273-C275 | 1 | 0 | 0 | 0
[11 empty] | WF6_7257 | C274 | NO | 0.14013 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 85 | C273-C275 | 1 | 0 | 0 | 0
[11 empty] | WF6_3132 | C274 | NO | 0.1021 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 85 | C273-C275 | 0 | 1 | 0 | 0
[11 empty] | WF6_3132 | C274 | NO | 0.013908 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 86 | C275-C277 | 0 | 1 | 0 | 0
[11 empty] | WF6_3122 | C274 | NO | 0.092615 |  | Harvest Processing | Non-Mulch |  | 6 | 85 | C273-C275 | 1 | 0 | 0 | 0
[11 empty] | WF6_3127 | C275 | YES | 0.019357 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 86 | C275-C277 | 1 | 0 | 0 | 0
[11 empty] | WF6_3130 | C275 | YES | 0.14847 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 86 | C275-C277 | 1 | 0 | 0 | 0
[11 empty] | WF6_6305 | C275 | YES | 0.014823 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 86 | C275-C277 | 1 | 0 | 0 | 0
[11 empty] | WF6_7074 | C275 | YES | 0.12057 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 86 | C275-C277 | 1 | 0 | 0 | 0
[11 empty] | WF6_7075 | C275 | YES | 0.31229 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 86 | C275-C277 | 1 | 0 | 0 | 0
[11 empty] | WF6_3132 | C275 | NO | 0.26398 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 86 | C275-C277 | 0 | 1 | 0 | 0
[11 empty] | WF6_3132 | C275 | NO | 0.082492 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 86 | C275-C277 | 0 | 1 | 0 | 0
[11 empty] | WF6_3132 | C275 | NO | 0.31487 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 86 | C275-C277 | 0 | 1 | 0 | 0
[11 empty] | WF6_3131 | C275 | NO | 0.27063 |  | Harvest Processing | Non-Mulch |  | 6 | 86 | C275-C277 | 1 | 0 | 0 | 0
[11 empty] | WF6_3128 | C275 | YES | 0.45816 |  | Non Productive | Non-Treed |  | 6 | 86 | C275-C277 | 1 | 0 | 0 | 0
[11 empty] | WF6_3126 | C275 | YES | 0.070916 |  | Retention | Retention |  | 6 | 86 | C275-C277 | 1 | 0 | 0 | 8
[11 empty] | WF6_3129 | C275 | NO | 0.18307 |  | Retention | Retention |  | 6 | 86 | C275-C277 | 1 | 0 | 0 | 8
[11 empty] | WF6_3133 | C275 | YES | 0.11685 |  | Retention | Retention |  | 6 | 86 | C275-C277 | 1 | 0 | 0 | 8
[11 empty] | WF6_7781 | C275 | NO | 0.27489 |  | Harvest Processing | Non-Mulch |  | 6 | 86 | C275-C277 | 1 | 0 | 0 | 0
[11 empty] | WF6_3134 | C276 | YES | 0.010882 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 86 | C275-C277 | 1 | 0 | 0 | 0
[11 empty] | WF6_3136 | C276 | YES | 0.012829 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 86 | C275-C277 | 1 | 0 | 0 | 0
[11 empty] | WF6_3139 | C276 | YES | 0.030908 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 86 | C275-C277 | 1 | 0 | 0 | 0
[11 empty] | WF6_6306 | C276 | YES | 0.012393 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 86 | C275-C277 | 1 | 0 | 0 | 0
[11 empty] | WF6_7076 | C276 | YES | 0.058264 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 86 | C275-C277 | 1 | 0 | 0 | 0
[11 empty] | WF6_7077 | C276 | YES | 0.011946 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 86 | C275-C277 | 1 | 0 | 0 | 0
[11 empty] | WF6_7078 | C276 | YES | 0.031975 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 86 | C275-C277 | 1 | 0 | 0 | 0
[11 empty] | WF6_7258 | C276 | NO | 0.18039 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 86 | C275-C277 | 1 | 0 | 0 | 0
[11 empty] | WF6_3131 | C276 | NO | 0.90316 |  | Harvest Processing | Non-Mulch |  | 6 | 86 | C275-C277 | 1 | 0 | 0 | 0
[11 empty] | WF6_3137 | C276 | NO | 0.038344 |  | Non Productive | Non-Treed |  | 6 | 86 | C275-C277 | 1 | 0 | 0 | 0
[11 empty] | WF6_3135 | C276 | YES | 0.054518 |  | Retention | Retention |  | 6 | 86 | C275-C277 | 1 | 0 | 0 | 8
[11 empty] | WF6_3138 | C276 | NO | 0.1826 |  | Retention | Retention |  | 6 | 86 | C275-C277 | 1 | 0 | 0 | 8
[11 empty] | WF6_3140 | C276 | YES | 0.063172 |  | Retention | Retention |  | 6 | 86 | C275-C277 | 1 | 0 | 0 | 8
[11 empty] | WF6_3142 | C276 | NO | 0.018262 |  | Retention | Retention |  | 6 | 86 | C275-C277 | 1 | 0 | 0 | 8
[11 empty] | WF6_6518 | C276 | NO | 0.22935 |  | Retention | Retention |  | 6 | 86 | C275-C277 | 1 | 0 | 0 | 8
[11 empty] | WF6_7289 | C276 | YES | 0.034153 |  | Retention | Retention |  | 6 | 86 | C275-C277 | 1 | 0 | 0 | 8
[11 empty] | WF6_7290 | C276 | NO | 0.066229 |  | Retention | Retention |  | 6 | 86 | C275-C277 | 1 | 0 | 0 | 8
[11 empty] | WF6_7504 | C276 | YES | 0.12355 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 86 | C275-C277 | 1 | 0 | 0 | 0
[11 empty] | WF6_7663 | C276 | NO | 0.39784 |  | Harvest Processing | Non-Mulch |  | 6 | 86 | C275-C277 | 1 | 0 | 0 | 0
[11 empty] | WF6_7856 | C276 | YES | 0.02 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 86 | C275-C277 | 1 | 0 | 0 | 0
[11 empty] | WF6_3143 | C277 | NO | 0.10915 |  | Retention | Retention |  | 6 | 87 | C277-C279 | 1 | 0 | 0 | 8
[11 empty] | WF6_3144 | C277 | NO | 0.10831 |  | Retention | Retention |  | 6 | 87 | C277-C279 | 1 | 0 | 0 | 8
[11 empty] | WF6_7662 | C277 | NO | 1.9486 |  | Harvest Processing | Non-Mulch |  | 6 | 87 | C277-C279 | 1 | 0 | 0 | 0
[11 empty] | WF6_3150 | C278 | NO |  |  | Harvest Disposal | Mulch |  | 6 | 87 | C277-C279 | 0 | 0 | 1 | 0
[11 empty] | WF6_3145 | C278 | NO |  |  | Harvest Processing | Non-Mulch |  | 6 | 87 | C277-C279 | 0 | 0 | 1 | 0
[11 empty] | WF6_3166 | C278 | NO | 0.074562 |  | Non-Merch Disposal | Mulch |  | 6 | 87 | C277-C279 | 1 | 0 | 0 | 0
[11 empty] | WF6_3141 | C278 | NO | 1.8761 |  | Harvest Processing | Non-Mulch |  | 6 | 87 | C277-C279 | 1 | 0 | 0 | 0
[11 empty] | WF6_3141 | C278 | NO | 0.019042 |  | Harvest Processing | Non-Mulch |  | 6 | 87 | C277-C279 | 1 | 0 | 0 | 0
[11 empty] | WF6_3163 | C278 | NO | 0.26685 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 87 | C277-C279 | 0 | 1 | 0 | 0
[11 empty] | WF5_2229 | C99 | NO | 0.35204 |  | Non-Merch Disposal | Mulch | AN | 5 | 50 | C098-C100 | 0 | 1 | 0 | 0
[11 empty] | WF6_3163 | D001 | NO | 0.01782 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 87 | C277-C279 | 0 | 1 | 0 | 0
[11 empty] | WF6_6363 | D001 | NO | 0.072539 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 87 | C277-C279 | 0 | 1 | 0 | 0
[11 empty] | WF7_3176 | D001 | NO | 1.3699 |  | Harvest Disposal | Mulch |  | 7 | 1 | D001-D003 | 1 | 0 | 0 | 0
[11 empty] | WF7_3171 | D001 | NO | 0.10132 |  | Non Productive | Non-Treed | AU1 | 7 | 1 | D001-D003 | 0 | 1 | 0 | 0
[11 empty] | WF7_3172 | D001 | NO | 0.17643 |  | Non Productive | Non-Treed |  | 7 | 1 | D001-D003 | 1 | 0 | 0 | 0
[11 empty] | WF7_3173 | D001 | NO | 0.029811 |  | Non Productive | Non-Treed |  | 7 | 1 | D001-D003 | 1 | 0 | 0 | 0
[11 empty] | WF7_3174 | D001 | NO | 0.08557 |  | Non Productive | Non-Treed |  | 7 | 1 | D001-D003 | 1 | 0 | 0 | 0
[11 empty] | WF7_3176 | D002 | NO | 0.11827 |  | Harvest Disposal | Mulch |  | 7 | 1 | D001-D003 | 1 | 0 | 0 | 0
[11 empty] | WF7_3195 | D002 | NO | 0.27858 |  | Harvest Disposal | Mulch |  | 7 | 1 | D001-D003 | 1 | 0 | 0 | 0
[11 empty] | WF7_3206 | D002 | NO | 0.72927 |  | Harvest Disposal | Mulch |  | 7 | 1 | D001-D003 | 1 | 0 | 0 | 0
[11 empty] | WF7_3191 | D002 | NO | 1.0039 |  | Harvest Processing | Non-Mulch |  | 7 | 1 | D001-D003 | 1 | 0 | 0 | 0
[11 empty] | WF7_3204 | D002 | NO | 0.026577 |  | Non Productive | Non-Treed |  | 7 | 1 | D001-D003 | 1 | 0 | 0 | 0
[11 empty] | WF7_3220 | D002 | NO | 0.052054 |  | Non Productive | Non-Treed |  | 7 | 1 | D001-D003 | 1 | 0 | 0 | 0
[11 empty] | WF7_3206 | D003 | NO | 2.1972 |  | Harvest Disposal | Mulch |  | 7 | 2 | D003-D005 | 1 | 0 | 0 | 0
[11 empty] | WF7_3220 | D003 | NO | 0.067981 |  | Non Productive | Non-Treed |  | 7 | 2 | D003-D005 | 1 | 0 | 0 | 0
[11 empty] | WF7_3206 | D004 | NO | 2.0651 |  | Harvest Disposal | Mulch |  | 7 | 2 | D003-D005 | 1 | 0 | 0 | 0
[11 empty] | WF7_3247 | D005 | YES | 0.13641 |  | Hand Fall / Lop and Scatter | Handfall |  | 7 | 3 | D005-D007 | 1 | 0 | 0 | 0
[11 empty] | WF7_3263 | D005 | NO | 1.0938 |  | Non-Merch Disposal | Mulch |  | 7 | 3 | D005-D007 | 1 | 0 | 0 | 0
[11 empty] | WF7_3206 | D005 | NO | 0.085957 |  | Harvest Disposal | Mulch |  | 7 | 3 | D005-D007 | 1 | 0 | 0 | 0
[11 empty] | WF7_3273 | D005 | NO | 0.16566 |  | Harvest Disposal | Mulch |  | 7 | 3 | D005-D007 | 1 | 0 | 0 | 0
[11 empty] | WF7_3253 | D005 | NO | 0.18753 |  | Non Productive | Non-Treed |  | 7 | 3 | D005-D007 | 1 | 0 | 0 | 0
[11 empty] | WF7_3259 | D005 | NO | 0.038073 |  | Non Productive | Non-Treed |  | 7 | 3 | D005-D007 | 1 | 0 | 0 | 0
[11 empty] | WF7_3252 | D005 | YES | 0.044357 |  | Retention | Retention |  | 7 | 3 | D005-D007 | 1 | 0 | 0 | 8
[11 empty] | WF7_3257 | D005 | YES | 0.40222 |  | Retention | Retention |  | 7 | 3 | D005-D007 | 1 | 0 | 0 | 8
[11 empty] | WF7_3261 | D005 | NO | 0.22573 |  | Retention | Retention |  | 7 | 3 | D005-D007 | 1 | 0 | 0 | 8
[11 empty] | WF7_3263 | D006 | NO | 0.31932 |  | Non-Merch Disposal | Mulch |  | 7 | 3 | D005-D007 | 1 | 0 | 0 | 0
[11 empty] | WF7_3273 | D006 | NO | 0.046389 |  | Harvest Disposal | Mulch |  | 7 | 3 | D005-D007 | 1 | 0 | 0 | 0
[11 empty] | WF7_3278 | D006 | NO | 1.8431 |  | Harvest Disposal | Mulch |  | 7 | 3 | D005-D007 | 1 | 0 | 0 | 0
[11 empty] | WF7_3277 | D006 | NO | 0.1295 |  | Retention | Retention |  | 7 | 3 | D005-D007 | 1 | 0 | 0 | 8
[11 empty] | WF7_3288 | D006 | NO | 0.066637 |  | Retention | Retention |  | 7 | 3 | D005-D007 | 1 | 0 | 0 | 8
[11 empty] | WF7_3278 | D007 | NO | 2.2746 |  | Harvest Disposal | Mulch |  | 7 | 4 | D007-D009 | 1 | 0 | 0 | 0
[11 empty] | WF7_3335 | D007 | NO | 0.45876 |  | Non Productive | Non-Treed |  | 7 | 4 | D007-D009 | 1 | 0 | 0 | 0
[11 empty] | WF7_3336 | D007 | NO | 0.59486 |  | Retention | Retention |  | 7 | 4 | D007-D009 | 1 | 0 | 0 | 8
[11 empty] | WF7_3343 | D008 | NO | 0.27328 |  | Harvest Disposal | Mulch |  | 7 | 4 | D007-D009 | 1 | 0 | 0 | 0
[11 empty] | WF7_3278 | D008 | NO | 1.2785 |  | Harvest Disposal | Mulch |  | 7 | 4 | D007-D009 | 1 | 0 | 0 | 0
[11 empty] | WF7_3303 | D008 | NO | 0.020756 |  | Harvest Disposal | Mulch | AU1 | 7 | 4 | D007-D009 | 0 | 1 | 0 | 0
[11 empty] | WF7_3331 | D008 | NO | 0.41397 |  | Harvest Disposal | Mulch |  | 7 | 4 | D007-D009 | 1 | 0 | 0 | 0
[11 empty] | WF7_3334 | D008 | NO | 0.11616 |  | Harvest Disposal | Mulch |  | 7 | 4 | D007-D009 | 1 | 0 | 0 | 0
[11 empty] | WF7_3332 | D008 | NO | 0.044431 |  | Non Productive | Non-Treed |  | 7 | 4 | D007-D009 | 1 | 0 | 0 | 0
[11 empty] | WF7_3333 | D008 | NO | 0.29159 |  | Non Productive | Non-Treed |  | 7 | 4 | D007-D009 | 1 | 0 | 0 | 0
[11 empty] | WF7_3344 | D008 | NO | 0.78034 |  | Retention | Retention |  | 7 | 4 | D007-D009 | 1 | 0 | 0 | 8
[11 empty] | WF7_3297 | D009 | YES | 0.1792 |  | Hand Fall / Lop and Scatter | Handfall | AN | 7 | 5 | D009-D011 | 0 | 1 | 0 | 0
[11 empty] | WF7_6290 | D009 | YES | 0.046524 |  | Hand Fall / Lop and Scatter | Handfall | AU1 | 7 | 5 | D009-D011 | 0 | 1 | 0 | 0
[11 empty] | WF7_3309 | D009 | YES | 0.011045 |  | Hand Fall / Lop and Scatter | Handfall | AN | 7 | 5 | D009-D011 | 0 | 1 | 0 | 0
[11 empty] | WF7_3300 | D009 | NO | 0.041697 |  | Harvest Disposal | Mulch | AN | 7 | 5 | D009-D011 | 0 | 1 | 0 | 0
[11 empty] | WF7_3304 | D009 | NO | 0.034203 |  | Harvest Processing | Non-Mulch | AN | 7 | 5 | D009-D011 | 0 | 1 | 0 | 0
[11 empty] | WF7_3299 | D009 | YES | 0.021816 |  | Hand Fall / Lop and Scatter | Handfall | AU1 | 7 | 5 | D009-D011 | 0 | 1 | 0 | 0
[11 empty] | WF7_3322 | D009 | YES | 0.15226 |  | Hand Fall / Lop and Scatter | Handfall |  | 7 | 5 | D009-D011 | 1 | 0 | 0 | 0
[11 empty] | WF7_3323 | D009 | YES | 0.029681 |  | Hand Fall / Lop and Scatter | Handfall |  | 7 | 5 | D009-D011 | 1 | 0 | 0 | 0
[11 empty] | WF7_3325 | D009 | YES | 0.55089 |  | Hand Fall / Lop and Scatter | Handfall |  | 7 | 5 | D009-D011 | 1 | 0 | 0 | 0
[11 empty] | WF7_3327 | D009 | YES | 0.1775 |  | Hand Fall / Lop and Scatter | Handfall |  | 7 | 5 | D009-D011 | 1 | 0 | 0 | 0
[11 empty] | WF7_3303 | D009 | NO | 0.032974 |  | Harvest Disposal | Mulch | AU1 | 7 | 5 | D009-D011 | 0 | 1 | 0 | 0
[11 empty] | WF7_3329 | D009 | NO | 0.013761 |  | Harvest Disposal | Mulch |  | 7 | 5 | D009-D011 | 1 | 0 | 0 | 0
[11 empty] | WF7_3331 | D009 | NO | 0.48319 |  | Harvest Disposal | Mulch |  | 7 | 5 | D009-D011 | 1 | 0 | 0 | 0
[11 empty] | WF7_7351 | D009 | NO | 0.02267 |  | Harvest Disposal | Mulch | AU1 | 7 | 5 | D009-D011 | 0 | 1 | 0 | 0
[11 empty] | WF7_3301 | D009 | NO | 0.011418 |  | Non Productive | Non-Treed | AU1 | 7 | 5 | D009-D011 | 0 | 1 | 0 | 0
[11 empty] | WF7_3324 | D009 | NO | 0.58798 |  | Non Productive | Non-Treed |  | 7 | 5 | D009-D011 | 1 | 0 | 0 | 0
[11 empty] | WF7_3326 | D009 | YES | 0.058755 |  | Non Productive | Non-Treed |  | 7 | 5 | D009-D011 | 1 | 0 | 0 | 0
[11 empty] | WF7_3328 | D009 | NO | 0.063501 |  | Non Productive | Non-Treed |  | 7 | 5 | D009-D011 | 1 | 0 | 0 | 0
[11 empty] | WF7_3330 | D009 | NO | 0.017735 |  | Non Productive | Non-Treed |  | 7 | 5 | D009-D011 | 1 | 0 | 0 | 0
[11 empty] | WF7_3338 | D009 | NO | 0.067409 |  | Non Productive | Non-Treed |  | 7 | 5 | D009-D011 | 1 | 0 | 0 | 0
[11 empty] | WF7_3340 | D010 | NO | 0.18787 |  | Hand Fall / Lop and Scatter | Handfall | AN | 7 | 5 | D009-D011 | 0 | 1 | 0 | 0
[11 empty] | WF7_3342 | D010 | NO | 0.038113 |  | Harvest Processing | Non-Mulch | AN | 7 | 5 | D009-D011 | 0 | 1 | 0 | 0
[11 empty] | WF7_3318 | D010 | YES | 0.22758 |  | Hand Fall / Lop and Scatter | Handfall |  | 7 | 5 | D009-D011 | 1 | 0 | 0 | 0
[11 empty] | WF7_3320 | D010 | YES | 0.21445 |  | Hand Fall / Lop and Scatter | Handfall |  | 7 | 5 | D009-D011 | 1 | 0 | 0 | 0
[11 empty] | WF7_3322 | D010 | YES | 0.018414 |  | Hand Fall / Lop and Scatter | Handfall |  | 7 | 5 | D009-D011 | 1 | 0 | 0 | 0
[11 empty] | WF7_3341 | D010 | YES | 0.037262 |  | Hand Fall / Lop and Scatter | Handfall | AN | 7 | 5 | D009-D011 | 0 | 1 | 0 | 0
[11 empty] | WF7_3317 | D010 | NO | 0.1902 |  | Harvest Disposal | Mulch |  | 7 | 5 | D009-D011 | 1 | 0 | 0 | 0
[11 empty] | WF7_3315 | D010 | NO | 1.2374 |  | Harvest Processing | Non-Mulch |  | 7 | 5 | D009-D011 | 1 | 0 | 0 | 0
[11 empty] | WF7_3321 | D010 | NO | 0.14346 |  | Harvest Processing | Non-Mulch |  | 7 | 5 | D009-D011 | 1 | 0 | 0 | 0
[11 empty] | WF7_3319 | D010 | NO | 0.14316 |  | Non Productive | Non-Treed |  | 7 | 5 | D009-D011 | 1 | 0 | 0 | 0
[11 empty] | WF7_3314 | D011 | NO | 0.12385 |  | Harvest Disposal | Mulch |  | 7 | 6 | D011-D013 | 1 | 0 | 0 | 0
[11 empty] | WF7_3315 | D011 | NO | 2.1363 |  | Harvest Processing | Non-Mulch |  | 7 | 6 | D011-D013 | 1 | 0 | 0 | 0
[11 empty] | WF7_3313 | D012 | NO | 0.049608 |  | Harvest Disposal | Mulch |  | 7 | 6 | D011-D013 | 1 | 0 | 0 | 0
[11 empty] | WF7_3314 | D012 | NO | 1.5133 |  | Harvest Disposal | Mulch |  | 7 | 6 | D011-D013 | 1 | 0 | 0 | 0
[11 empty] | WF7_3312 | D012 | NO | 0.67475 |  | Harvest Processing | Non-Mulch |  | 7 | 6 | D011-D013 | 1 | 0 | 0 | 0
[11 empty] | WF7_3315 | D012 | NO | 0.048987 |  | Harvest Processing | Non-Mulch |  | 7 | 6 | D011-D013 | 1 | 0 | 0 | 0
[11 empty] | WF7_3311 | D013 | NO | 0.72063 |  | Harvest Disposal | Mulch |  | 7 | 7 | D013-D015 | 1 | 0 | 0 | 0
[11 empty] | WF7_3313 | D013 | NO | 0.18812 |  | Harvest Disposal | Mulch |  | 7 | 7 | D013-D015 | 1 | 0 | 0 | 0
[11 empty] | WF7_3310 | D013 | NO | 0.47753 |  | Harvest Processing | Non-Mulch |  | 7 | 7 | D013-D015 | 1 | 0 | 0 | 0
[11 empty] | WF7_3312 | D013 | NO | 0.48046 |  | Harvest Processing | Non-Mulch |  | 7 | 7 | D013-D015 | 1 | 0 | 0 | 0
[11 empty] | WF7_3306 | D014 | YES | 0.1399 |  | Hand Fall / Lop and Scatter | Handfall |  | 7 | 7 | D013-D015 | 1 | 0 | 0 | 0
[11 empty] | WF7_3308 | D014 | YES | 0.60324 |  | Hand Fall / Lop and Scatter | Handfall |  | 7 | 7 | D013-D015 | 1 | 0 | 0 | 0
[11 empty] | WF7_3307 | D014 | NO | 1.2711 |  | Harvest Processing | Non-Mulch |  | 7 | 7 | D013-D015 | 1 | 0 | 0 | 0
[11 empty] | WF7_3307 | D014 | NO | 0.010131 |  | Harvest Processing | Non-Mulch |  | 7 | 8 | D015-D017 | 1 | 0 | 0 | 0
[11 empty] | WF7_3310 | D014 | NO | 0.26137 |  | Harvest Processing | Non-Mulch |  | 7 | 7 | D013-D015 | 1 | 0 | 0 | 0
[11 empty] | WF7_3306 | D015 | YES | 0.012141 |  | Hand Fall / Lop and Scatter | Handfall |  | 7 | 7 | D013-D015 | 1 | 0 | 0 | 0
[11 empty] | WF7_3306 | D015 | YES | 0.069951 |  | Hand Fall / Lop and Scatter | Handfall |  | 7 | 8 | D015-D017 | 1 | 0 | 0 | 0
[11 empty] | WF7_3339 | D015 | YES | 0.047754 |  | Hand Fall / Lop and Scatter | Handfall |  | 7 | 8 | D015-D017 | 1 | 0 | 0 | 0
[11 empty] | WF7_3346 | D015 | NO | 0.22201 |  | Harvest Disposal | Mulch |  | 7 | 8 | D015-D017 | 1 | 0 | 0 | 0
[11 empty] | WF7_3307 | D015 | NO | 1.3685 |  | Harvest Processing | Non-Mulch |  | 7 | 8 | D015-D017 | 1 | 0 | 0 | 0
[11 empty] | WF7_3346 | D016 | NO | 1.0702 |  | Harvest Disposal | Mulch |  | 7 | 8 | D015-D017 | 1 | 0 | 0 | 0
[11 empty] | WF7_3351 | D016 | NO | 0.74447 |  | Harvest Processing | Non-Mulch |  | 7 | 8 | D015-D017 | 1 | 0 | 0 | 0
[11 empty] | WF7_3352 | D017 | YES | 0.16355 |  | Hand Fall / Lop and Scatter | Handfall |  | 7 | 9 | D017-D019 | 1 | 0 | 0 | 0
[11 empty] | WF7_3356 | D017 | YES | 0.379 |  | Hand Fall / Lop and Scatter | Handfall |  | 7 | 9 | D017-D019 | 1 | 0 | 0 | 0
[11 empty] | WF7_3358 | D017 | YES | 0.20448 |  | Hand Fall / Lop and Scatter | Handfall |  | 7 | 9 | D017-D019 | 1 | 0 | 0 | 0
[11 empty] | WF7_3359 | D017 | NO | 0.66055 |  | Harvest Processing | Non-Mulch |  | 7 | 9 | D017-D019 | 1 | 0 | 0 | 0
[11 empty] | WF7_3361 | D017 | YES | 0.43021 |  | Hand Fall / Lop and Scatter | Handfall |  | 7 | 9 | D017-D019 | 1 | 0 | 0 | 0
[11 empty] | WF7_3351 | D017 | NO | 0.15427 |  | Harvest Processing | Non-Mulch |  | 7 | 9 | D017-D019 | 1 | 0 | 0 | 0
[11 empty] | WF7_3362 | D017 | NO | 0.47973 |  | Harvest Processing | Non-Mulch |  | 7 | 9 | D017-D019 | 1 | 0 | 0 | 0
[11 empty] | WF7_3357 | D017 | NO | 0.43698 |  | Non Productive | Non-Treed |  | 7 | 9 | D017-D019 | 1 | 0 | 0 | 0
[11 empty] | WF7_3376 | D018 | YES | 0.069121 |  | Hand Fall / Lop and Scatter | Handfall |  | 7 | 9 | D017-D019 | 1 | 0 | 0 | 0
[11 empty] | WF7_3362 | D018 | NO | 1.7834 |  | Harvest Processing | Non-Mulch |  | 7 | 9 | D017-D019 | 1 | 0 | 0 | 0
[11 empty] | WF7_3387 | D019 | YES | 0.06869 |  | Hand Fall / Lop and Scatter | Handfall |  | 7 | 10 | D019-D021 | 1 | 0 | 0 | 0
[11 empty] | WF7_3376 | D019 | YES | 0.39 |  | Hand Fall / Lop and Scatter | Handfall |  | 7 | 10 | D019-D021 | 1 | 0 | 0 | 0
[11 empty] | WF7_3384 | D019 | YES | 0.27113 |  | Hand Fall / Lop and Scatter | Handfall |  | 7 | 10 | D019-D021 | 1 | 0 | 0 | 0
[11 empty] | WF7_3379 | D019 | NO | 0.82082 |  | Harvest Disposal | Mulch |  | 7 | 10 | D019-D021 | 1 | 0 | 0 | 0
[11 empty] | WF7_3383 | D019 | NO | 0.26456 |  | Harvest Disposal | Mulch | AN | 7 | 10 | D019-D021 | 0 | 1 | 0 | 0
[11 empty] | WF7_3383 | D019 | NO | 0.21773 |  | Harvest Disposal | Mulch | AN | 7 | 11 | D019-D021 | 0 | 1 | 0 | 0
[11 empty] | WF7_3446 | D019 | NO | 0.35981 |  | Harvest Disposal | Mulch | AN | 7 | 11 | D019-D021 | 0 | 1 | 0 | 0
[11 empty] | WF7_3477 | D019 | NO | 0.079373 |  | Harvest Disposal | Mulch | AU2 | 7 | 11 | D019-D021 | 0 | 1 | 0 | 0
[11 empty] | WF7_3362 | D019 | NO | 0.26256 |  | Harvest Processing | Non-Mulch |  | 7 | 10 | D019-D021 | 1 | 0 | 0 | 0
[11 empty] | WF7_3386 | D019 | NO | 0.069076 |  | Harvest Processing | Non-Mulch |  | 7 | 10 | D019-D021 | 1 | 0 | 0 | 0
[11 empty] | WF7_3389 | D019 | NO | 0.35206 |  | Harvest Processing | Non-Mulch |  | 7 | 10 | D019-D021 | 1 | 0 | 0 | 0
[11 empty] | WF7_3399 | D019 | NO | 0.3394 |  | Harvest Processing | Non-Mulch | AN | 7 | 11 | D019-D021 | 0 | 1 | 0 | 0
[11 empty] | WF7_3504 | D019 | NO | 0.14296 |  | Harvest Processing | Non-Mulch | AU2 | 7 | 11 | D019-D021 | 0 | 1 | 0 | 0
[11 empty] | WF7_7354 | D019 | NO | 0.081421 |  | Harvest Disposal | Mulch | AU2 | 7 | 11 | D019-D021 | 0 | 1 | 0 | 0
[11 empty] | WF7_7405 | D019 | NO | 0.1427 |  | Harvest Processing | Non-Mulch | AU2 | 7 | 11 | D019-D021 | 0 | 1 | 0 | 0
[11 empty] | WF7_3392 | D020 | YES | 0.33644 |  | Hand Fall / Lop and Scatter | Handfall |  | 7 | 10 | D019-D021 | 1 | 0 | 0 | 0
[11 empty] | WF7_3397 | D020 | NO | 0.43296 |  | Harvest Disposal | Mulch |  | 7 | 10 | D019-D021 | 1 | 0 | 0 | 0
[11 empty] | WF7_3389 | D020 | NO | 1.1281 |  | Harvest Processing | Non-Mulch |  | 7 | 10 | D019-D021 | 1 | 0 | 0 | 0
[11 empty] | WF7_7335 | D021 |  | 0.010345 |  | Harvest Disposal | Mulch |  | 7 | 12 | D021-D023 | 0 | 1 | 0 | 0
[11 empty] | WF7_7336 | D021 |  | 0.11933 |  | Harvest Disposal | Mulch |  | 7 | 12 | D021-D023 | 0 | 1 | 0 | 0
[11 empty] | WF7_3397 | D021 | NO | 1.8592 |  | Harvest Disposal | Mulch |  | 7 | 12 | D021-D023 | 1 | 0 | 0 | 0
[11 empty] | WF7_3405 | D022 | NO |  |  | Harvest Disposal | Mulch | AN | 7 | 12 | D021-D023 | 0 | 0 | 1 | 0
[11 empty] | WF7_3438 | D022 | NO | 0.019552 |  | Harvest Disposal | Mulch | AN | 7 | 12 | D021-D023 | 0 | 0 | 1 | 0
[11 empty] | WF7_3461 | D022 | NO | 0.064955 |  | Harvest Disposal | Mulch | AN | 7 | 12 | D021-D023 | 0 | 0 | 1 | 0
[11 empty] | WF7_3418 | D022 | NO | 0.47244 |  | Harvest Processing | Non-Mulch | AN | 7 | 12 | D021-D023 | 0 | 0 | 1 | 0
[11 empty] | WF7_3443 | D022 | NO |  |  | Harvest Processing | Non-Mulch | AN | 7 | 12 | D021-D023 | 0 | 0 | 1 | 0
[11 empty] | WF7_3397 | D022 | NO | 0.41637 |  | Harvest Disposal | Mulch |  | 7 | 12 | D021-D023 | 1 | 0 | 0 | 0
[11 empty] | WF7_3453 | D022 | NO | 0.47634 |  | Harvest Disposal | Mulch |  | 7 | 12 | D021-D023 | 1 | 0 | 0 | 0
[11 empty] | WF7_3430 | D022 | NO | 1.1681 |  | Harvest Processing | Non-Mulch |  | 7 | 12 | D021-D023 | 1 | 0 | 1 | 0
[11 empty] | WF7_3462 | D022 | NO | 0.11683 |  | Harvest Processing | Non-Mulch |  | 7 | 12 | D021-D023 | 1 | 0 | 0 | 0
[11 empty] | WF7_8202 | D022 | NO | 0.084341 |  | Hand Fall / Lop and Scatter | Mulch |  | 7 | 12 | D021-D023 | 1 | 0 | 0 | 0
[11 empty] | WF7_3493 | D023 | NO | 0.10803 |  | Hand Fall / Lop and Scatter | Handfall |  | 7 | 13 | D023-D025 | 1 | 0 | 0 | 0
[11 empty] | WF7_3453 | D023 | NO | 0.039471 |  | Harvest Disposal | Mulch |  | 7 | 13 | D023-D025 | 1 | 0 | 0 | 0
[11 empty] | WF7_3462 | D023 | NO | 1.6491 |  | Harvest Processing | Non-Mulch |  | 7 | 13 | D023-D025 | 1 | 0 | 0 | 0
[11 empty] | WF7_3492 | D023 | NO | 0.15343 |  | Non Productive | Non-Treed | AN | 7 | 13 | D023-D025 | 0 | 1 | 0 | 0
[11 empty] | WF7_3493 | D024 | NO | 0.90819 |  | Hand Fall / Lop and Scatter | Handfall |  | 7 | 13 | D023-D025 | 1 | 0 | 0 | 0
[11 empty] | WF7_3462 | D024 | NO | 0.31829 |  | Harvest Processing | Non-Mulch |  | 7 | 13 | D023-D025 | 1 | 0 | 0 | 0
[11 empty] | WF7_3513 | D024 | NO | 0.3877 |  | Harvest Processing | Non-Mulch |  | 7 | 13 | D023-D025 | 1 | 0 | 0 | 0
[11 empty] | WF7_3492 | D024 | NO | 0.091003 |  | Non Productive | Non-Treed | AN | 7 | 13 | D023-D025 | 0 | 1 | 0 | 0
Filter full clearing into "OffROW" clearing only
Given 84.5ha requires seeding, calculate the number of Mix Seed Bags required and the purchase cost
Given seeding is required across 84 ha (or ~$57km), a crew with two labours will require at least one full shift to complete the planned scope
1
2
3

## All Season Access - Removal
All-season Access Removal Forecast
Item |  | All-season Road (km) | Road Reclamation | Wetland Road (km) | Wetland Removal | Mat Removal* | Total Forecast
Actual all-season Roads |  | 37.7724 | 469990.5141 | 4.4253 | 0 | #REF! | #REF!
*Est. mat removal cost will be similar to install cost with an approximate increase of 20% arriving from additional requirements associated with disposal (i.e., the requirement of Triaxle trucks to extract broken and additional support required to dispose of mats).
The following crew compositions are used to calculate the remaining forecasted scope
Road Reclamation
|  | Daily Hours |  | 11
Equipment | Rate | Qty per Crew | # of Crews | Daily Cost
Excavator - 36 ton | 146.96 | 1 | 1 | 1616.56
Excavator Operator - Mon - Fri or Sat | 73.08 | 1 | 1 | 803.88
Pickups | 243.75 | 2 | 1 | 487.5
Dozer D6D | 131.48 | 1 | 1 | 1446.28
Operator - Principle - After Jan 10 | 75 | 1 | 1 | 825
LOA | 210 | LS | LS | 420 | 2
|  | Total Cost |  | 5599.22
|  | Productivity (m/day) |  | 450
|  | Average $ per day |  | 5599.22
|  | Cost ($/km) |  | 12442.7111
Bridge Removal
|  | Daily Hours |  | 11
Equipment | Rate | Qty per Crew | # of Crews | Daily Cost
Excavator - 36 ton | 146.96 | 2 | 2 | 6466.24
Excavator Operator - Mon - Fri or Sat | 73.08 | 2 | 2 | 3215.52
Pickups | 243.75 | 2 | 2 | 975
Labourer - General | 60 | 1 | 2 | 1320
LOA | 210 | LS | LS | 1260 | 6
|  | Total Cost |  | 13236.76
Wetland Removal
|  | Daily Hours |  | 11
Equipment | Rate | Qty per Crew | # of Crews | Daily Cost
Excavator - 36 ton | 146.96 | 1 | 1 | 1616.56
Excavator Operator - Mon - Fri or Sat | 73.08 | 1 | 1 | 803.88
Dump - Triaxle- After Jan 10 | 55.2 | 5 | 1 | 3036
Driver - AZ - After Jan 10 | 70 | 5 | 1 | 3850
Pickups | 243.75 | 2 | 1 | 487.5
Labourer - General | 60 | 2 | 1 | 1320
LOA | 210 | LS | LS | 1680 | 8
|  | Total Cost |  | 12793.94
Road Maintenance
|  |  | Daily Hours |  | 11
Equipment | Rate | UofM | Qty per Crew | # of Crews | Daily Cost
Grader | 126.98 | HR | 1 | 2 | 2793.56
Operator - Principle - After Jan 10 | 75 | HR | 1 | 2 | 1650
Pick ups | 243.75 | HR | 1 | 2 | 487.5
LOA | 210 | DAY | LS | LS | 420 | 2
|  |  |  | Total Cost | 5351.06
|  |  |  | Per unit | 2675.53
|  |  |  | 20 days worth of Grader time | 53510.6
Bridge Install Crew
|  |  | Daily Hours |  | 11
Equipment | Rate | UofM | Qty per Crew | # of Crews | Daily Cost
Excavator - 36 ton | 146.96 | HR | 2 | 3 | 9699.36
Excavator Operator - Mon - Fri or Sat | 73.08 | HR | 2 | 3 | 4823.28
Labourer - General | 60 | HR | 1 | 3 | 1980
Pickups | 243.75 | DAY | 2 | 3 | 1462.5
LOA | 210 | LS | LS | LS | 1890 | 9
Foreman | 95 | H | 1 | 1 | 1045
Pickups | 243.75 | DAY | 1 | 1 | 243.75
0
21143.89
|  |  | Average per day |  | 7047.9633
|  |  | 19 bridges required to be re-installed |  | 66955.6517 | 2 bridges per day

## DPCache_All Labour (hidden)
Code | Employee | Role | Company | Date | Activity | Notes | Cost Code | Hours | Rate | Labour Cost | Lodging Cost | Total Cost | Facility | Structures | Activity Tags | Timesheet Tags
117403 | Mario Brito | Foreman | 00677 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Walked machines out due to forest fires | 57010138 | 6.5 | 146.89 | 954.785 | 124.0909 | 1078.8759 |  |  |  | mVolts
205419 | Carlos Brito | Labourer | 00677 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Walked machines out due to forest fires | 57010138 | 6.5 | 81.03 | 526.695 | 124.0909 | 650.7859 |  |  |  | mVolts
203987 | Antonio Teixeira | Labourer | 00677 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Shut Down For forest fires , walked drill 7740 to laydown , went back to cooks east west y and walked drill 7651 to lay down. Cristian did wet cure and concrete cure at C055,C056,C059,C060,C039 and walked Machine from C39 to the layd down | 57010138 | 5.5 | 81.03 | 445.665 | 105 | 550.665 |  |  |  | mVolts
197247 | Nathaniel McNutt | Equipment Operator | 00677 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Shut Down For forest fires , walked drill 7740 to laydown , went back to cooks east west y and walked drill 7651 to lay down. Cristian did wet cure and concrete cure at C055,C056,C059,C060,C039 and walked Machine from C39 to the layd down | 57010138 | 5.5 | 111.7 | 614.35 | 105 | 719.35 |  |  |  | mVolts
196261 | Cristian Sinisterra Mosquera | Labourer | 00677 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Shut Down For forest fires , walked drill 7740 to laydown , went back to cooks east west y and walked drill 7651 to lay down. Cristian did wet cure and concrete cure at C055,C056,C059,C060,C039 and walked Machine from C39 to the layd down | 57010138 | 4 | 81.03 | 324.12 | 76.3636 | 400.4836 |  |  |  | mVolts
117745 | Bradley Eagle | Equipment Operator | 00677 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Got shut down due to dry forest conditions and had to walk bucket hoe unit #7679 from C069 to lay down on Antler Road | 57010138 | 4.5 | 111.7 | 502.65 | 85.9091 | 588.5591 |  |  |  | mVolts
118960 | Barry Skinner | Labourer | 00677 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Got shut down due to dry forest conditions and had to walk bucket hoe unit #7679 from C069 to lay down on Antler Road | 57010138 | 4.5 | 81.03 | 364.635 | 85.9091 | 450.5441 |  |  |  | mVolts
117424 | Michael Brushett | Equipment Operator | 00677 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Demoved equipment | 57010138 | 3 | 111.7 | 335.1 | 57.2727 | 392.3727 |  |  |  | mVolts
190198 | Erick Aguilar Calderon | Labourer | 00677 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Demoved equipment | 57010138 | 3 | 81.03 | 243.09 | 57.2727 | 300.3627 |  |  |  | mVolts
117855 | Gregory Gagnon | Lineman / Electrician | 00677 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Walked equipment out of ROW, structures a002 and b197 | 57010138 | 9 | 132.15 | 1189.35 | 171.8182 | 1361.1682 |  |  |  | mVolts
117346 | Robert Bjerkelund | Foreman | 00677 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Walked equipment out of ROW, structures a002 and b197 | 57010138 | 9 | 146.89 | 1322.01 | 171.8182 | 1493.8282 |  |  |  | mVolts
176397 | Trevor Malcolm | Lineman / Electrician | 00677 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Walked equipment out of ROW, structures a002 and b197 | 57010138 | 9 | 132.15 | 1189.35 | 171.8182 | 1361.1682 |  |  |  | mVolts
204485 | Jeffrey Stuckless | Lineman / Electrician | 00677 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Walked equipment out of ROW, structures a002 and b197 | 57010138 | 9 | 132.15 | 1189.35 | 171.8182 | 1361.1682 |  |  |  | mVolts
118038 | Nicholas Hickey | Labourer | 00677 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Walked equipment out of ROW, structures a002 and b197 | 57010138 | 9 | 81.03 | 729.27 | 171.8182 | 901.0882 |  |  |  | mVolts
117563 | Jordan Clarke | Labourer | 00677 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Walked equipment out of ROW, structures a002 and b197 | 57010138 | 9 | 81.03 | 729.27 | 171.8182 | 901.0882 |  |  |  | mVolts
118248 | Marc Lalonde | Equipment Operator | 00677 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Walked equipment out of ROW, structures a002 and b197 | 57010138 | 9 | 111.7 | 1005.3 | 171.8182 | 1177.1182 |  |  |  | mVolts
117296 | Andrew Beauchemin | Equipment Operator | 00677 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Walked equipment out of ROW, structures a002 and b197 | 57010138 | 9 | 111.7 | 1005.3 | 171.8182 | 1177.1182 |  |  |  | mVolts
118557 | Chad Mouland | Equipment Operator | 00677 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Walked equipment out of ROW, structures a002 and b197 | 57010138 | 9 | 111.7 | 1005.3 | 171.8182 | 1177.1182 |  |  |  | mVolts
118106 | Derek Hynes | Foreman | 00677 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Walked equipment out of ROW, structures a002 and b197 | 57010138 | 9 | 146.89 | 1322.01 | 171.8182 | 1493.8282 |  |  |  | mVolts
186559 | Derek Lavallee | Labourer | 00677 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Walked equipment out of ROW, structures a002 and b197 | 57010138 | 9 | 81.03 | 729.27 | 171.8182 | 901.0882 |  |  |  | mVolts
195654 | Devin Budney | Labourer | 00677 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Walked equipment out of ROW, structures a002 and b197 | 57010138 | 9 | 81.03 | 729.27 | 171.8182 | 901.0882 |  |  |  | mVolts
118962 | Caleb Sladen | Foreman | 00677 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Walked equipment out of ROW, structures a002 and b197 | 57010138 | 9 | 146.89 | 1322.01 | 171.8182 | 1493.8282 |  |  |  | mVolts
205991 | Stephen Crawley | Apprentice - 1st Year | 00677 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Walked equipment out of ROW, structures a002 and b197 | 57010138 | 9 | 70.81 | 637.29 | 171.8182 | 809.1082 |  |  |  | mVolts
118087 | Thomas Howes | Supervisor | 00677 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Get all equipment moved off ROW to laydowns for hauling. | 57010138 | 9 | 150.59 | 1355.31 | 171.8182 | 1527.1282 |  |  |  | mVolts
117459 | Mark Byrd | Labourer | 00677 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Moving equipment off site | 57010138 | 1.5 | 81.03 | 121.545 | 28.6364 | 150.1814 |  |  |  | mVolts
118183 | Edward Kearley | Equipment Operator | 00677 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Moving equipment off site | 57010138 | 1.5 | 111.7 | 167.55 | 28.6364 | 196.1864 |  |  |  | mVolts
117569 | Samuel Clarke | Foreman | 00677 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Moving equipment off site | 57010138 | 1.5 | 146.89 | 220.335 | 28.6364 | 248.9714 |  |  |  | mVolts
116573 | Jeffory Dominaux | Labourer | 00677 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Moving equipment off site | 57010138 | 1.5 | 81.03 | 121.545 | 28.6364 | 150.1814 |  |  |  | mVolts
205779 | Craig Marshall | Labourer | 00677 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Travel equipment to laydown | 57010138 | 6 | 81.03 | 486.18 | 114.5455 | 600.7255 |  |  |  | mVolts
185469 | Deacon Hynes | Labourer | 00677 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Travel equipment to laydown | 57010138 | 3 | 81.03 | 243.09 | 57.2727 | 300.3627 |  |  |  | mVolts
119196 | Joseph Wells Jr | Foreman | 00677 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Travel equipment to laydown | 57010138 | 6 | 146.89 | 881.34 | 114.5455 | 995.8855 |  |  |  | mVolts
116660 | Richard Hickey | Equipment Operator | 00677 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Travel equipment to laydown | 57010138 | 6 | 111.7 | 670.2 | 114.5455 | 784.7455 |  |  |  | mVolts
204132 | Ian Day | Labourer | 00677 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Travel equipment to laydown | 57010138 | 3 | 81.03 | 243.09 | 57.2727 | 300.3627 |  |  |  | mVolts
204116 | Stephen Bustard | Labourer | 00677 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Travel equipment to laydown | 57010138 | 3 | 81.03 | 243.09 | 57.2727 | 300.3627 |  |  |  | mVolts
185748 | Steven Wray | Labourer | 00677 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Travel equipment to laydown | 57010138 | 3 | 81.03 | 243.09 | 57.2727 | 300.3627 |  |  |  | mVolts
177096 | Evan-Reece Cheesequay-MacLaurin | Labourer | 00677 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Travel equipment to laydown | 57010138 | 3 | 81.03 | 243.09 | 57.2727 | 300.3627 |  |  |  | mVolts
117873 | Kevin Genaille | Labourer | 00677 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Travel equipment to laydown | 57010138 | 3 | 81.03 | 243.09 | 57.2727 | 300.3627 |  |  |  | mVolts
205229 | Ashton Kenney | Labourer | 00677 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Travel equipment to laydown | 57010138 | 3 | 81.03 | 243.09 | 57.2727 | 300.3627 |  |  |  | mVolts
176091 | Scott Randa | Labourer | 00677 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Travel equipment to laydown | 57010138 | 3 | 81.03 | 243.09 | 57.2727 | 300.3627 |  |  |  | mVolts
117812 | Benjamin Foote | Labourer | 00677 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Mobilize equipment | 57010138 | 1 | 81.03 | 81.03 | 19.0909 | 100.1209 |  |  |  | mVolts
176481 | Dylan Berlingeri | Labourer | 00677 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Mobilize equipment | 57010138 | 1 | 81.03 | 81.03 | 19.0909 | 100.1209 |  |  |  | mVolts
185005 | Michael Mischke | Labourer | 00677 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Mobilize equipment | 57010138 | 1 | 81.03 | 81.03 | 19.0909 | 100.1209 |  |  |  | mVolts
174879 | Andre Sabourin | Labourer | 00677 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Mobilize equipment | 57010138 | 1 | 81.03 | 81.03 | 19.0909 | 100.1209 |  |  |  | mVolts
117570 | Terence Clarke | Foreman | 00677 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Mob Gear/crews out | 57010138 | 2 | 146.89 | 293.78 | 38.1818 | 331.9618 |  |  |  | mVolts
118615 | Gary O'Brien | Foreman | 00677 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Walk out drill from Str C099 to laydown due to fires | 57010138 | 3 | 146.89 | 440.67 | 57.2727 | 497.9427 |  |  |  | mVolts
205842 | Shane Moores | Labourer | 00677 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Walk out drill from Str C099 to laydown due to fires | 57010138 | 3 | 81.03 | 243.09 | 57.2727 | 300.3627 |  |  |  | mVolts
118036 | Keith Hickey | Equipment Operator | 00677 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Move equipment from sitr to road | 57010138 | 3 | 111.7 | 335.1 | 57.2727 | 392.3727 |  |  |  | mVolts
118239 | Trevor Labour | Labourer | 00677 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Move equipment from sitr to road | 57010138 | 3 | 81.03 | 243.09 | 57.2727 | 300.3627 |  |  |  | mVolts
117815 | Keith Foote | Labourer | 00677 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Move equipment from sitr to road | 57010138 | 3 | 81.03 | 243.09 | 57.2727 | 300.3627 |  |  |  | mVolts
116488 | Perry Abbott | Labourer | 00677 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Move equipment from sitr to road | 57010138 | 3 | 81.03 | 243.09 | 57.2727 | 300.3627 |  |  |  | mVolts
118238 | Lee Labour | Labourer | 00677 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Move equipment from sitr to road | 57010138 | 3 | 81.03 | 243.09 | 57.2727 | 300.3627 |  |  |  | mVolts
174876 | Matt Michano | Labourer | 00677 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Move equipment from sitr to road | 57010138 | 3 | 81.03 | 243.09 | 57.2727 | 300.3627 |  |  |  | mVolts
196449 | Denzil Bouchard | Labourer | 00677 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Move equipment from sitr to road | 57010138 | 3 | 81.03 | 243.09 | 57.2727 | 300.3627 |  |  |  | mVolts
205918 | Norman Edwards | Labourer | 00677 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Move equipment from sitr to road | 57010138 | 3 | 81.03 | 243.09 | 57.2727 | 300.3627 |  |  |  | mVolts
117550 | Barry Clarke | Foreman | 00677 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Move equipment from sitr to road | 57010138 | 3 | 146.89 | 440.67 | 57.2727 | 497.9427 |  |  |  | mVolts
175342 | Patrick Bananish | Apprentice - 2nd Year | 00677 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Move equipment from sitr to road | 57010138 | 3 | 81.03 | 243.09 | 57.2727 | 300.3627 |  |  |  | mVolts
118960 | Barry Skinner | Labourer | 00677 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Shut down due to extreme fire conditions. Cleaned truck. Got drills ready on Cooks rd and Antler rd for floats to move gear. | 57010138 | 11 | 81.03 | 891.33 | 210 | 1101.33 |  |  |  | mVolts
117745 | Bradley Eagle | Equipment Operator | 00677 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Shut down due to extreme fire conditions. Cleaned truck. Got drills ready on Cooks rd and Antler rd for floats to move gear. | 57010138 | 11 | 111.7 | 1228.7 | 210 | 1438.7 |  |  |  | mVolts
119254 | David Wood | Truck Driver / Picker Op. | 00677 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Equipment Hauling from Restricted Area | 57010138 | 11.5 | 127.04 | 1460.96 | 210 | 1670.96 |  |  |  | mVolts
118054 | Robert Hinsperger | Equipment Operator | 00677 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Equipment Hauling from Restricted Area | 57010138 | 11 | 111.7 | 1228.7 | 210 | 1438.7 |  |  |  | mVolts
205419 | Carlos Brito | Labourer | 00677 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Meeting in the morning at Marathon. Clean grout,truck demoved equipment , move it to Marathon. Organized crews | 57010138 | 11 | 81.03 | 891.33 | 210 | 1101.33 |  |  |  | mVolts
117403 | Mario Brito | Foreman | 00677 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Meeting in the morning at Marathon. Clean grout,truck demoved equipment , move it to Marathon. Organized crews | 57010138 | 11 | 146.89 | 1615.79 | 210 | 1825.79 |  |  |  | mVolts
190198 | Erick Aguilar Calderon | Labourer | 00677 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Move equipment | 57010138 | 11 | 81.03 | 891.33 | 210 | 1101.33 |  |  |  | mVolts
117424 | Michael Brushett | Equipment Operator | 00677 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Move equipment | 57010138 | 11 | 111.7 | 1228.7 | 210 | 1438.7 |  |  |  | mVolts
156144 | Kenneth Cyrette | Labourer | 00677 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Travel fire caches to marathon | 57010138 | 11 | 81.03 | 891.33 | 210 | 1101.33 |  |  |  | mVolts
117567 | Oliver Clarke | Labourer | 00677 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Travel fire caches to marathon | 57010138 | 11 | 81.03 | 891.33 | 210 | 1101.33 |  |  |  | mVolts
117372 | Ronald Bolt | Labourer | 00677 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Travel fire caches to marathon | 57010138 | 11 | 81.03 | 891.33 | 210 | 1101.33 |  |  |  | mVolts
117776 | Gregory Evans | Labourer | 00677 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Travel fire caches to marathon | 57010138 | 11 | 81.03 | 891.33 | 210 | 1101.33 |  |  |  | mVolts
176090 | David Maxwell | Labourer | 00677 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Travel fire caches to marathon | 57010138 | 11 | 81.03 | 891.33 | 210 | 1101.33 |  |  |  | mVolts
156263 | James Young | Labourer | 00677 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Travel fire caches to marathon | 57010138 | 11 | 81.03 | 891.33 | 210 | 1101.33 |  |  |  | mVolts
116573 | Jeffory Dominaux | Labourer | 00677 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Travel fire caches to marathon | 57010138 | 11 | 81.03 | 891.33 | 210 | 1101.33 |  |  |  | mVolts
118183 | Edward Kearley | Equipment Operator | 00677 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Travel fire caches to marathon | 57010138 | 11 | 111.7 | 1228.7 | 210 | 1438.7 |  |  |  | mVolts
117459 | Mark Byrd | Labourer | 00677 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Travel fire caches to marathon | 57010138 | 11 | 81.03 | 891.33 | 210 | 1101.33 |  |  |  | mVolts
117569 | Samuel Clarke | Foreman | 00677 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Travel fire caches to marathon | 57010138 | 11 | 146.89 | 1615.79 | 210 | 1825.79 |  |  |  | mVolts
176091 | Scott Randa | Labourer | 00677 - Valard | 2021-07-21 | FORFIRES - Forest Fires | N/a | 57010138 | 11 | 81.03 | 891.33 | 210 | 1101.33 |  |  |  | mVolts
205229 | Ashton Kenney | Labourer | 00677 - Valard | 2021-07-21 | FORFIRES - Forest Fires | N/a | 57010138 | 11 | 81.03 | 891.33 | 210 | 1101.33 |  |  |  | mVolts
117873 | Kevin Genaille | Labourer | 00677 - Valard | 2021-07-21 | FORFIRES - Forest Fires | N/a | 57010138 | 11 | 81.03 | 891.33 | 210 | 1101.33 |  |  |  | mVolts
177096 | Evan-Reece Cheesequay-MacLaurin | Labourer | 00677 - Valard | 2021-07-21 | FORFIRES - Forest Fires | N/a | 57010138 | 11 | 81.03 | 891.33 | 210 | 1101.33 |  |  |  | mVolts
185748 | Steven Wray | Labourer | 00677 - Valard | 2021-07-21 | FORFIRES - Forest Fires | N/a | 57010138 | 11 | 81.03 | 891.33 | 210 | 1101.33 |  |  |  | mVolts
204116 | Stephen Bustard | Labourer | 00677 - Valard | 2021-07-21 | FORFIRES - Forest Fires | N/a | 57010138 | 11 | 81.03 | 891.33 | 210 | 1101.33 |  |  |  | mVolts
204132 | Ian Day | Labourer | 00677 - Valard | 2021-07-21 | FORFIRES - Forest Fires | N/a | 57010138 | 11 | 81.03 | 891.33 | 210 | 1101.33 |  |  |  | mVolts
116660 | Richard Hickey | Equipment Operator | 00677 - Valard | 2021-07-21 | FORFIRES - Forest Fires | N/a | 57010138 | 12 | 111.7 | 1340.4 | 210 | 1550.4 |  |  |  | mVolts
185469 | Deacon Hynes | Labourer | 00677 - Valard | 2021-07-21 | FORFIRES - Forest Fires | N/a | 57010138 | 12 | 81.03 | 972.36 | 210 | 1182.36 |  |  |  | mVolts
205779 | Craig Marshall | Labourer | 00677 - Valard | 2021-07-21 | FORFIRES - Forest Fires | N/a | 57010138 | 12 | 81.03 | 972.36 | 210 | 1182.36 |  |  |  | mVolts
119196 | Joseph Wells Jr | Foreman | 00677 - Valard | 2021-07-21 | FORFIRES - Forest Fires | N/a | 57010138 | 12 | 146.89 | 1762.68 | 210 | 1972.68 |  |  |  | mVolts
117455 | Charles Byrd | Equipment Operator | 00677 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Mobilze from nipigon to wawa | 57010138 | 4 | 111.7 | 446.8 | 76.3636 | 523.1636 |  |  |  | mVolts
117813 | Craig Foote | Labourer | 00677 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Mobilze from nipigon to wawa | 57010138 | 4 | 81.03 | 324.12 | 76.3636 | 400.4836 |  |  |  | mVolts
116524 | Edward Bolt | Labourer | 00677 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Mobilze from nipigon to wawa | 57010138 | 4 | 81.03 | 324.12 | 76.3636 | 400.4836 |  |  |  | mVolts
117967 | Leeland Halleran | Foreman | 00677 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Mobilze from nipigon to wawa | 57010138 | 4 | 146.89 | 587.56 | 76.3636 | 663.9236 |  |  |  | mVolts
117812 | Benjamin Foote | Labourer | 00677 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Mobilze from nipigon to wawa | 57010138 | 4 | 81.03 | 324.12 | 76.3636 | 400.4836 |  |  |  | mVolts
176481 | Dylan Berlingeri | Labourer | 00677 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Mobilze from nipigon to wawa | 57010138 | 4 | 81.03 | 324.12 | 76.3636 | 400.4836 |  |  |  | mVolts
175345 | Gabriel Oskaboose-Eccleston | Labourer | 00677 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Mobilze from nipigon to wawa | 57010138 | 4 | 81.03 | 324.12 | 76.3636 | 400.4836 |  |  |  | mVolts
176490 | Ward Bolt | Labourer | 00677 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Mobilze from nipigon to wawa | 57010138 | 4 | 81.03 | 324.12 | 76.3636 | 400.4836 |  |  |  | mVolts
185005 | Michael Mischke | Labourer | 00677 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Mobilze from nipigon to wawa | 57010138 | 4 | 81.03 | 324.12 | 76.3636 | 400.4836 |  |  |  | mVolts
153100 | Axel Beaulieu | Labourer | 00677 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Mobilze from nipigon to wawa | 57010138 | 4 | 81.03 | 324.12 | 76.3636 | 400.4836 |  |  |  | mVolts
174879 | Andre Sabourin | Labourer | 00677 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Mobilze from nipigon to wawa | 57010138 | 4 | 81.03 | 324.12 | 76.3636 | 400.4836 |  |  |  | mVolts
118087 | Thomas Howes | Supervisor | 00677 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Moving equipment from Thunder Bay to white lake laydown. | 57010138 | 12 | 150.59 | 1807.08 | 210 | 2017.08 |  |  |  | mVolts
117513 | Dwayne Chambers | Truck Driver / Picker Op. | 00677 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Floated equipment between white lake east and macgregor rd | 57010138 | 13 | 127.04 | 1651.52 | 210 | 1861.52 |  |  |  | mVolts
117248 | Wayne Ashley | Equipment Operator | 00677 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Floated equipment between white lake east and macgregor rd | 57010138 | 13 | 111.7 | 1452.1 | 210 | 1662.1 |  |  |  | mVolts
205991 | Stephen Crawley | Apprentice - 1st Year | 00677 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Floated equipment between white lake east and macgregor rd | 57010138 | 12 | 70.81 | 849.72 | 210 | 1059.72 |  |  |  | mVolts
118962 | Caleb Sladen | Foreman | 00677 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Floated equipment between white lake east and macgregor rd | 57010138 | 12 | 146.89 | 1762.68 | 210 | 1972.68 |  |  |  | mVolts
195654 | Devin Budney | Labourer | 00677 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Floated equipment between white lake east and macgregor rd | 57010138 | 12 | 81.03 | 972.36 | 210 | 1182.36 |  |  |  | mVolts
186559 | Derek Lavallee | Labourer | 00677 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Floated equipment between white lake east and macgregor rd | 57010138 | 12 | 81.03 | 972.36 | 210 | 1182.36 |  |  |  | mVolts
118106 | Derek Hynes | Foreman | 00677 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Floated equipment between white lake east and macgregor rd | 57010138 | 12 | 146.89 | 1762.68 | 210 | 1972.68 |  |  |  | mVolts
118557 | Chad Mouland | Equipment Operator | 00677 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Floated equipment between white lake east and macgregor rd | 57010138 | 12 | 111.7 | 1340.4 | 210 | 1550.4 |  |  |  | mVolts
117296 | Andrew Beauchemin | Equipment Operator | 00677 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Floated equipment between white lake east and macgregor rd | 57010138 | 12 | 111.7 | 1340.4 | 210 | 1550.4 |  |  |  | mVolts
118248 | Marc Lalonde | Equipment Operator | 00677 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Floated equipment between white lake east and macgregor rd | 57010138 | 12 | 111.7 | 1340.4 | 210 | 1550.4 |  |  |  | mVolts
117563 | Jordan Clarke | Labourer | 00677 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Floated equipment between white lake east and macgregor rd | 57010138 | 12 | 81.03 | 972.36 | 210 | 1182.36 |  |  |  | mVolts
118038 | Nicholas Hickey | Labourer | 00677 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Floated equipment between white lake east and macgregor rd | 57010138 | 12 | 81.03 | 972.36 | 210 | 1182.36 |  |  |  | mVolts
204485 | Jeffrey Stuckless | Lineman / Electrician | 00677 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Floated equipment between white lake east and macgregor rd | 57010138 | 12 | 132.15 | 1585.8 | 210 | 1795.8 |  |  |  | mVolts
117346 | Robert Bjerkelund | Foreman | 00677 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Floated equipment between white lake east and macgregor rd | 57010138 | 12 | 146.89 | 1762.68 | 210 | 1972.68 |  |  |  | mVolts
117855 | Gregory Gagnon | Lineman / Electrician | 00677 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Floated equipment between white lake east and macgregor rd | 57010138 | 12 | 132.15 | 1585.8 | 210 | 1795.8 |  |  |  | mVolts
176397 | Trevor Malcolm | Lineman / Electrician | 00677 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Floated equipment between white lake east and macgregor rd | 57010138 | 12 | 132.15 | 1585.8 | 210 | 1795.8 |  |  |  | mVolts
205842 | Shane Moores | Labourer | 00677 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Getting equipment ready for float | 57010138 | 11 | 81.03 | 891.33 | 210 | 1101.33 |  |  |  | mVolts
118615 | Gary O'Brien | Foreman | 00677 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Getting equipment ready for float | 57010138 | 11 | 146.89 | 1615.79 | 210 | 1825.79 |  |  |  | mVolts
117438 | Bobby Burt | Truck Driver / Picker Op. | 00677 - Valard | 2021-07-22 | FORFIRES - Forest Fires | Equipment Hauling from Restricted Area | 57010138 | 6 | 127.04 | 762.24 | 114.5455 | 876.7855 |  |  |  | mVolts
205842 | Shane Moores | Labourer | 00677 - Valard | 2021-07-22 | FORFIRES - Forest Fires | Mobe to Wawa from Schrieber | 57010138 | 4 | 81.03 | 324.12 | 76.3636 | 400.4836 |  |  |  | mVolts
118615 | Gary O'Brien | Foreman | 00677 - Valard | 2021-07-22 | FORFIRES - Forest Fires | Mobe to Wawa from Schrieber | 57010138 | 4 | 146.89 | 587.56 | 76.3636 | 663.9236 |  |  |  | mVolts
117403 | Mario Brito | Foreman | 00677 - Valard | 2021-07-22 | FORFIRES - Forest Fires | Organized moving equipment to wawa due to forest fires. | 57010138 | 5 | 146.89 | 734.45 | 95.4545 | 829.9045 |  |  |  | mVolts
205419 | Carlos Brito | Labourer | 00677 - Valard | 2021-07-22 | FORFIRES - Forest Fires | Organized moving equipment to wawa due to forest fires. | 57010138 | 5 | 81.03 | 405.15 | 95.4545 | 500.6045 |  |  |  | mVolts
118087 | Thomas Howes | Supervisor | 00677 - Valard | 2021-07-22 | FORFIRES - Forest Fires | Moving cranes around and hauling equipment. | 57010138 | 12 | 150.59 | 1807.08 | 210 | 2017.08 |  |  |  | mVolts
117513 | Dwayne Chambers | Truck Driver / Picker Op. | 00677 - Valard | 2021-07-22 | FORFIRES - Forest Fires | Piloted cranes ad mob'd equipment between white lake east and macgregor rd | 57010138 | 13.5 | 127.04 | 1715.04 | 210 | 1925.04 |  |  |  | mVolts
117248 | Wayne Ashley | Equipment Operator | 00677 - Valard | 2021-07-22 | FORFIRES - Forest Fires | Piloted cranes ad mob'd equipment between white lake east and macgregor rd | 57010138 | 13.5 | 111.7 | 1507.95 | 210 | 1717.95 |  |  |  | mVolts
205991 | Stephen Crawley | Apprentice - 1st Year | 00677 - Valard | 2021-07-22 | FORFIRES - Forest Fires | Piloted cranes ad mob'd equipment between white lake east and macgregor rd | 57010138 | 12 | 70.81 | 849.72 | 210 | 1059.72 |  |  |  | mVolts
118962 | Caleb Sladen | Foreman | 00677 - Valard | 2021-07-22 | FORFIRES - Forest Fires | Piloted cranes ad mob'd equipment between white lake east and macgregor rd | 57010138 | 12 | 146.89 | 1762.68 | 210 | 1972.68 |  |  |  | mVolts
195654 | Devin Budney | Labourer | 00677 - Valard | 2021-07-22 | FORFIRES - Forest Fires | Piloted cranes ad mob'd equipment between white lake east and macgregor rd | 57010138 | 12 | 81.03 | 972.36 | 210 | 1182.36 |  |  |  | mVolts
186559 | Derek Lavallee | Labourer | 00677 - Valard | 2021-07-22 | FORFIRES - Forest Fires | Piloted cranes ad mob'd equipment between white lake east and macgregor rd | 57010138 | 12 | 81.03 | 972.36 | 210 | 1182.36 |  |  |  | mVolts
118106 | Derek Hynes | Foreman | 00677 - Valard | 2021-07-22 | FORFIRES - Forest Fires | Piloted cranes ad mob'd equipment between white lake east and macgregor rd | 57010138 | 12 | 146.89 | 1762.68 | 210 | 1972.68 |  |  |  | mVolts
118557 | Chad Mouland | Equipment Operator | 00677 - Valard | 2021-07-22 | FORFIRES - Forest Fires | Piloted cranes ad mob'd equipment between white lake east and macgregor rd | 57010138 | 12 | 111.7 | 1340.4 | 210 | 1550.4 |  |  |  | mVolts
117296 | Andrew Beauchemin | Equipment Operator | 00677 - Valard | 2021-07-22 | FORFIRES - Forest Fires | Piloted cranes ad mob'd equipment between white lake east and macgregor rd | 57010138 | 12 | 111.7 | 1340.4 | 210 | 1550.4 |  |  |  | mVolts
118248 | Marc Lalonde | Equipment Operator | 00677 - Valard | 2021-07-22 | FORFIRES - Forest Fires | Piloted cranes ad mob'd equipment between white lake east and macgregor rd | 57010138 | 12 | 111.7 | 1340.4 | 210 | 1550.4 |  |  |  | mVolts
117563 | Jordan Clarke | Labourer | 00677 - Valard | 2021-07-22 | FORFIRES - Forest Fires | Piloted cranes ad mob'd equipment between white lake east and macgregor rd | 57010138 | 12 | 81.03 | 972.36 | 210 | 1182.36 |  |  |  | mVolts
118038 | Nicholas Hickey | Labourer | 00677 - Valard | 2021-07-22 | FORFIRES - Forest Fires | Piloted cranes ad mob'd equipment between white lake east and macgregor rd | 57010138 | 12 | 81.03 | 972.36 | 210 | 1182.36 |  |  |  | mVolts
204485 | Jeffrey Stuckless | Lineman / Electrician | 00677 - Valard | 2021-07-22 | FORFIRES - Forest Fires | Piloted cranes ad mob'd equipment between white lake east and macgregor rd | 57010138 | 12 | 132.15 | 1585.8 | 210 | 1795.8 |  |  |  | mVolts
117346 | Robert Bjerkelund | Foreman | 00677 - Valard | 2021-07-22 | FORFIRES - Forest Fires | Piloted cranes ad mob'd equipment between white lake east and macgregor rd | 57010138 | 12 | 146.89 | 1762.68 | 210 | 1972.68 |  |  |  | mVolts
117855 | Gregory Gagnon | Lineman / Electrician | 00677 - Valard | 2021-07-22 | FORFIRES - Forest Fires | Piloted cranes ad mob'd equipment between white lake east and macgregor rd | 57010138 | 12 | 132.15 | 1585.8 | 210 | 1795.8 |  |  |  | mVolts
176397 | Trevor Malcolm | Lineman / Electrician | 00677 - Valard | 2021-07-22 | FORFIRES - Forest Fires | Piloted cranes ad mob'd equipment between white lake east and macgregor rd | 57010138 | 12 | 132.15 | 1585.8 | 210 | 1795.8 |  |  |  | mVolts
117513 | Dwayne Chambers | Truck Driver / Picker Op. | 00677 - Valard | 2021-07-23 | FORFIRES - Forest Fires | Moving equipment due to fire ban. | 57010138 | 11 | 127.04 | 1397.44 | 210 | 1607.44 |  |  |  | mVolts
117248 | Wayne Ashley | Equipment Operator | 00677 - Valard | 2021-07-23 | FORFIRES - Forest Fires | Moving equipment due to fire ban. | 57010138 | 11 | 111.7 | 1228.7 | 210 | 1438.7 |  |  |  | mVolts
118557 | Chad Mouland | Equipment Operator | 00677 - Valard | 2021-07-23 | FORFIRES - Forest Fires | Moving equipment due to fire ban. | 57010138 | 11 | 111.7 | 1228.7 | 210 | 1438.7 |  |  |  | mVolts
118106 | Derek Hynes | Foreman | 00677 - Valard | 2021-07-23 | FORFIRES - Forest Fires | Moving equipment due to fire ban. | 57010138 | 11 | 146.89 | 1615.79 | 210 | 1825.79 |  |  |  | mVolts
186559 | Derek Lavallee | Labourer | 00677 - Valard | 2021-07-23 | FORFIRES - Forest Fires | Moving equipment due to fire ban. | 57010138 | 11 | 81.03 | 891.33 | 210 | 1101.33 |  |  |  | mVolts
195654 | Devin Budney | Labourer | 00677 - Valard | 2021-07-23 | FORFIRES - Forest Fires | Moving equipment due to fire ban. | 57010138 | 11 | 81.03 | 891.33 | 210 | 1101.33 |  |  |  | mVolts
205991 | Stephen Crawley | Apprentice - 1st Year | 00677 - Valard | 2021-07-23 | FORFIRES - Forest Fires | Moving equipment due to fire ban. | 57010138 | 11 | 70.81 | 778.91 | 210 | 988.91 |  |  |  | mVolts
118038 | Nicholas Hickey | Labourer | 00677 - Valard | 2021-07-23 | FORFIRES - Forest Fires | Moving equipment due to fire ban. | 57010138 | 11 | 81.03 | 891.33 | 210 | 1101.33 |  |  |  | mVolts
117563 | Jordan Clarke | Labourer | 00677 - Valard | 2021-07-23 | FORFIRES - Forest Fires | Moving equipment due to fire ban. | 57010138 | 11 | 81.03 | 891.33 | 210 | 1101.33 |  |  |  | mVolts
117855 | Gregory Gagnon | Lineman / Electrician | 00677 - Valard | 2021-07-23 | FORFIRES - Forest Fires | Moving equipment due to fire ban. | 57010138 | 11 | 132.15 | 1453.65 | 210 | 1663.65 |  |  |  | mVolts
176397 | Trevor Malcolm | Lineman / Electrician | 00677 - Valard | 2021-07-23 | FORFIRES - Forest Fires | Moving equipment due to fire ban. | 57010138 | 11 | 132.15 | 1453.65 | 210 | 1663.65 |  |  |  | mVolts
204485 | Jeffrey Stuckless | Lineman / Electrician | 00677 - Valard | 2021-07-23 | FORFIRES - Forest Fires | Moving equipment due to fire ban. | 57010138 | 11 | 132.15 | 1453.65 | 210 | 1663.65 |  |  |  | mVolts
117346 | Robert Bjerkelund | Foreman | 00677 - Valard | 2021-07-23 | FORFIRES - Forest Fires | Moving equipment due to fire ban. | 57010138 | 11 | 146.89 | 1615.79 | 210 | 1825.79 |  |  |  | mVolts
117296 | Andrew Beauchemin | Equipment Operator | 00677 - Valard | 2021-07-23 | FORFIRES - Forest Fires | Moving equipment due to fire ban. | 57010138 | 11 | 111.7 | 1228.7 | 210 | 1438.7 |  |  |  | mVolts
118962 | Caleb Sladen | Foreman | 00677 - Valard | 2021-07-23 | FORFIRES - Forest Fires | Moving equipment due to fire ban. | 57010138 | 11 | 146.89 | 1615.79 | 210 | 1825.79 |  |  |  | mVolts
118248 | Marc Lalonde | Equipment Operator | 00677 - Valard | 2021-07-23 | FORFIRES - Forest Fires | Moving equipment due to fire ban. | 57010138 | 11 | 111.7 | 1228.7 | 210 | 1438.7 |  |  |  | mVolts
118087 | Thomas Howes | Supervisor | 00677 - Valard | 2021-07-23 | FORFIRES - Forest Fires | Moving equipment due to fire ban. | 57010138 | 11 | 150.59 | 1656.49 | 210 | 1866.49 |  |  |  | mVolts
205419 | Carlos Brito | Labourer | 00677 - Valard | 2021-07-23 | FORFIRES - Forest Fires | Poured STR C061 with mixer on legs A,B and C Stripped STR C059. Get material to formed STR C070 | 57010138 | 11 | 81.03 | 891.33 | 210 | 1101.33 |  |  |  | mVolts
117403 | Mario Brito | Foreman | 00677 - Valard | 2021-07-23 | FORFIRES - Forest Fires | Poured STR C061 with mixer on legs A,B and C Stripped STR C059. Get material to formed STR C070 | 57010138 | 11 | 146.89 | 1615.79 | 210 | 1825.79 |  |  |  | mVolts
119254 | David Wood | Truck Driver / Picker Op. | 00677 - Valard | 2021-07-23 | FORFIRES - Forest Fires | Equipment Hauling from Restricted Zone | 57010138 | 11 | 127.04 | 1397.44 | 210 | 1607.44 |  |  |  | mVolts
118054 | Robert Hinsperger | Equipment Operator | 00677 - Valard | 2021-07-23 | FORFIRES - Forest Fires | Equipment Hauling from Restricted Zone | 57010138 | 12 | 111.7 | 1340.4 | 210 | 1550.4 |  |  |  | mVolts
155244 | Craig Greenslade | Surveyor | 00677 - Valard | 2021-07-23 | FORFIRES - Forest Fires | Travel from Thunderbay to White River | 57010138 | 7.5 | 132.15 | 991.125 | 143.1818 | 1134.3068 |  |  |  | mVolts
138222 | Trent Linton | Surveyor | 00677 - Valard | 2021-07-23 | FORFIRES - Forest Fires | Travel from Thunderbay to White River | 57010138 | 7.5 | 132.15 | 991.125 | 143.1818 | 1134.3068 |  |  |  | mVolts
205419 | Carlos Brito | Labourer | 00677 - Valard | 2021-07-24 | FORFIRES - Forest Fires | Poured grout pad with mixer at STR C070 and C072. | 57010138 | 11 | 81.03 | 891.33 | 210 | 1101.33 |  |  |  | mVolts
117403 | Mario Brito | Foreman | 00677 - Valard | 2021-07-24 | FORFIRES - Forest Fires | Poured grout pad with mixer at STR C070 and C072. | 57010138 | 11 | 146.89 | 1615.79 | 210 | 1825.79 |  |  |  | mVolts
117438 | Bobby Burt | Truck Driver / Picker Op. | 00677 - Valard | 2021-07-24 | FORFIRES - Forest Fires | Equipment Hauling from Restricted Zone | 57010138 | 7 | 127.04 | 889.28 | 133.6364 | 1022.9164 |  |  |  | mVolts
119254 | David Wood | Truck Driver / Picker Op. | 00677 - Valard | 2021-07-24 | FORFIRES - Forest Fires | Equipment Hauling from Restricted Zone | 57010138 | 11 | 127.04 | 1397.44 | 210 | 1607.44 |  |  |  | mVolts
176227 | Craig McKay | Surveyor | 00677 - Valard | 2021-07-24 | FORFIRES - Forest Fires | Travel from Thunder Bay to Wawa. | 57010138 | 10 | 132.15 | 1321.5 | 190.9091 | 1512.4091 |  |  |  | mVolts
117128 | Kirk Somers | Project Assistant/Coord | 00677 - Valard | 2021-07-25 | FORFIRES - Forest Fires | Fire Watch Monitoring as per MNRF approval | 57010138 | 12 | 91.26 | 1095.12 | 210 | 1305.12 |  |  |  | mVolts
117438 | Bobby Burt | Truck Driver / Picker Op. | 00677 - Valard | 2021-07-25 | FORFIRES - Forest Fires | Equipment Hauling from Restricted Zone | 57010138 | 4 | 127.04 | 508.16 | 76.3636 | 584.5236 |  |  |  | mVolts
206244 | Bryan Lavigne | Labourer | 00677 - Valard | 2021-07-25 | FORFIRES - Forest Fires | Clean up | 57010138 | 11 | 81.03 | 891.33 | 210 | 1101.33 |  |  |  | mVolts
206248 | Joshua Hewitt | Labourer | 00677 - Valard | 2021-07-25 | FORFIRES - Forest Fires | Clean up | 57010138 | 11 | 81.03 | 891.33 | 210 | 1101.33 |  |  |  | mVolts
190198 | Erick Aguilar Calderon | Labourer | 00677 - Valard | 2021-07-25 | FORFIRES - Forest Fires | Clean up | 57010138 | 11 | 81.03 | 891.33 | 210 | 1101.33 |  |  |  | mVolts
117424 | Michael Brushett | Equipment Operator | 00677 - Valard | 2021-07-25 | FORFIRES - Forest Fires | Clean up | 57010138 | 11 | 111.7 | 1228.7 | 210 | 1438.7 |  |  |  | mVolts
203233 | Eric Marsh | Truck Driver / Picker Op. | 00677 - Valard | 2021-07-25 | FORFIRES - Forest Fires | Hauling water totes back to marathon from access | 57010138 | 11 | 127.04 | 1397.44 | 210 | 1607.44 |  |  |  | mVolts
118625 | Joseph O'Donnell | Labourer | 00677 - Valard | 2021-07-25 | FORFIRES - Forest Fires | Placed dowels and bent rebar for u-bar | 57010138 | 5 | 81.03 | 405.15 | 95.4545 | 500.6045 |  |  |  | mVolts
195524 | Jose Ayala-Guzman | Labourer | 00677 - Valard | 2021-07-25 | FORFIRES - Forest Fires | Placed dowels and bent rebar for u-bar | 57010138 | 5 | 81.03 | 405.15 | 95.4545 | 500.6045 |  |  |  | mVolts
119017 | Frank Stone | Labourer | 00677 - Valard | 2021-07-25 | FORFIRES - Forest Fires | Placed dowels and bent rebar for u-bar | 57010138 | 5 | 81.03 | 405.15 | 95.4545 | 500.6045 |  |  |  | mVolts
116651 | Sheldon Hardiman | Foreman | 00677 - Valard | 2021-07-25 | FORFIRES - Forest Fires | Placed dowels and bent rebar for u-bar | 57010138 | 5 | 146.89 | 734.45 | 95.4545 | 829.9045 |  |  |  | mVolts
116651 | Sheldon Hardiman | Foreman | 00677 - Valard | 2021-07-25 | FORFIRES - Forest Fires | Carried in anchor bar from the laydown at Antler to str C068 and installed couplers to join on extensions . Then we put out dowels and bent u-bars | 57010138 | 6 | 146.89 | 881.34 | 114.5455 | 995.8855 |  |  |  | mVolts
119017 | Frank Stone | Labourer | 00677 - Valard | 2021-07-25 | FORFIRES - Forest Fires | Carried in anchor bar from the laydown at Antler to str C068 and installed couplers to join on extensions . Then we put out dowels and bent u-bars | 57010138 | 6 | 81.03 | 486.18 | 114.5455 | 600.7255 |  |  |  | mVolts
195524 | Jose Ayala-Guzman | Labourer | 00677 - Valard | 2021-07-25 | FORFIRES - Forest Fires | Carried in anchor bar from the laydown at Antler to str C068 and installed couplers to join on extensions . Then we put out dowels and bent u-bars | 57010138 | 6 | 81.03 | 486.18 | 114.5455 | 600.7255 |  |  |  | mVolts
118625 | Joseph O'Donnell | Labourer | 00677 - Valard | 2021-07-25 | FORFIRES - Forest Fires | Carried in anchor bar from the laydown at Antler to str C068 and installed couplers to join on extensions . Then we put out dowels and bent u-bars | 57010138 | 6 | 81.03 | 486.18 | 114.5455 | 600.7255 |  |  |  | mVolts
176478 | Ryan Moses | Labourer | 00677 - Valard | 2021-07-26 | FORFIRES - Forest Fires | Fire Watch | 57010138 | 3.75 | 81.03 | 303.8625 | 71.5909 | 375.4534 |  |  |  | mVolts
117128 | Kirk Somers | Project Assistant/Coord | 00677 - Valard | 2021-07-26 | FORFIRES - Forest Fires | Fire Watch monitoring as required by MNRF | 57010138 | 12 | 91.26 | 1095.12 | 210 | 1305.12 |  |  |  | mVolts
206244 | Bryan Lavigne | Labourer | 00677 - Valard | 2021-07-26 | FORFIRES - Forest Fires | Clean up site | 57010138 | 11 | 81.03 | 891.33 | 210 | 1101.33 |  |  |  | mVolts
190198 | Erick Aguilar Calderon | Labourer | 00677 - Valard | 2021-07-26 | FORFIRES - Forest Fires | Clean up site | 57010138 | 11 | 81.03 | 891.33 | 210 | 1101.33 |  |  |  | mVolts
117424 | Michael Brushett | Equipment Operator | 00677 - Valard | 2021-07-26 | FORFIRES - Forest Fires | Clean up site | 57010138 | 11 | 111.7 | 1228.7 | 210 | 1438.7 |  |  |  | mVolts
185848 | Austin McCarthy | Labourer | 00677 - Valard | 2021-07-26 | FORFIRES - Forest Fires | Fire watch. | 57010138 | 14 | 81.03 | 1134.42 | 210 | 1344.42 |  |  |  | mVolts
118625 | Joseph O'Donnell | Labourer | 00677 - Valard | 2021-07-26 | FORFIRES - Forest Fires | Clean up spill on str c193,clean up sites in on Gurnney and carried extra steel to Antler laydown. | 57010138 | 11 | 81.03 | 891.33 | 210 | 1101.33 |  |  |  | mVolts
195524 | Jose Ayala-Guzman | Labourer | 00677 - Valard | 2021-07-26 | FORFIRES - Forest Fires | Clean up spill on str c193,clean up sites in on Gurnney and carried extra steel to Antler laydown. | 57010138 | 11 | 81.03 | 891.33 | 210 | 1101.33 |  |  |  | mVolts
119017 | Frank Stone | Labourer | 00677 - Valard | 2021-07-26 | FORFIRES - Forest Fires | Clean up spill on str c193,clean up sites in on Gurnney and carried extra steel to Antler laydown. | 57010138 | 11 | 81.03 | 891.33 | 210 | 1101.33 |  |  |  | mVolts
116651 | Sheldon Hardiman | Foreman | 00677 - Valard | 2021-07-26 | FORFIRES - Forest Fires | Clean up spill on str c193,clean up sites in on Gurnney and carried extra steel to Antler laydown. | 57010138 | 11 | 146.89 | 1615.79 | 210 | 1825.79 |  |  |  | mVolts
203233 | Eric Marsh | Truck Driver / Picker Op. | 00677 - Valard | 2021-07-26 | FORFIRES - Forest Fires | Loaded plywood,2x4 at nipigon yard and then loaded rebar at cooks road and went back to marathon for to deliver to Wawa | 57010138 | 11 | 127.04 | 1397.44 | 210 | 1607.44 |  |  |  | mVolts
176478 | Ryan Moses | Labourer | 00677 - Valard | 2021-07-27 | FORFIRES - Forest Fires | Fire Watch | 57010138 | 0.5 | 81.03 | 40.515 | 9.5455 | 50.0605 |  |  |  | mVolts
117128 | Kirk Somers | Project Assistant/Coord | 00677 - Valard | 2021-07-27 | FORFIRES - Forest Fires | Monitoring compliance to Fire Watch as required by MNRF | 57010138 | 12 | 91.26 | 1095.12 | 210 | 1305.12 |  |  |  | mVolts
176478 | Ryan Moses | Labourer | 00677 - Valard | 2021-07-27 | FORFIRES - Forest Fires | Fire Watch | 57010138 | 14 | 81.03 | 1134.42 | 210 | 1344.42 |  |  |  | mVolts
185848 | Austin McCarthy | Labourer | 00677 - Valard | 2021-07-27 | FORFIRES - Forest Fires | Fire watch. | 57010138 | 14 | 81.03 | 1134.42 | 210 | 1344.42 |  |  |  | mVolts
196172 | Dwayne Hollmer | Labourer | 00677 - Valard | 2021-07-27 | FORFIRES - Forest Fires | Fire watch. | 57010138 | 3 | 81.03 | 243.09 | 57.2727 | 300.3627 |  |  |  | mVolts
117128 | Kirk Somers | Project Assistant/Coord | 00677 - Valard | 2021-07-28 | FORFIRES - Forest Fires | Ongoing monitoring of Fire Watch requirements as per MNRF | 57010138 | 12 | 91.26 | 1095.12 | 210 | 1305.12 |  |  |  | mVolts
176478 | Ryan Moses | Labourer | 00677 - Valard | 2021-07-28 | FORFIRES - Forest Fires | Fire Watch | 57010138 | 12 | 81.03 | 972.36 | 210 | 1182.36 |  |  |  | mVolts
118087 | Thomas Howes | Supervisor | 00677 - Valard | 2021-07-28 | FORFIRES - Forest Fires | Moved crane from Thunder Bay to 600rd due to fire ban. | 57010138 | 11 | 150.59 | 1656.49 | 210 | 1866.49 |  |  |  | mVolts
185848 | Austin McCarthy | Labourer | 00677 - Valard | 2021-07-28 | FORFIRES - Forest Fires | Fire watch. | 57010138 | 12 | 81.03 | 972.36 | 210 | 1182.36 |  |  |  | mVolts
118248 | Marc Lalonde | Equipment Operator | 00677 - Valard | 2021-07-28 | FORFIRES - Forest Fires | Mono poles ,move 200 ton to 600 rd | 57010138 | 11 | 111.7 | 1228.7 | 210 | 1438.7 |  |  |  | mVolts
117296 | Andrew Beauchemin | Equipment Operator | 00677 - Valard | 2021-07-28 | FORFIRES - Forest Fires | Mono poles ,move 200 ton to 600 rd | 57010138 | 11 | 111.7 | 1228.7 | 210 | 1438.7 |  |  |  | mVolts
117346 | Robert Bjerkelund | Foreman | 00677 - Valard | 2021-07-28 | FORFIRES - Forest Fires | Mono poles ,move 200 ton to 600 rd | 57010138 | 11 | 146.89 | 1615.79 | 210 | 1825.79 |  |  |  | mVolts
204485 | Jeffrey Stuckless | Lineman / Electrician | 00677 - Valard | 2021-07-28 | FORFIRES - Forest Fires | Mono poles ,move 200 ton to 600 rd | 57010138 | 11 | 132.15 | 1453.65 | 210 | 1663.65 |  |  |  | mVolts
117128 | Kirk Somers | Project Assistant/Coord | 00677 - Valard | 2021-07-29 | FORFIRES - Forest Fires | Monitoring site for compliance to fire watch as required by MNRF | 57010138 | 12 | 91.26 | 1095.12 | 210 | 1305.12 |  |  |  | mVolts
176478 | Ryan Moses | Labourer | 00677 - Valard | 2021-07-29 | FORFIRES - Forest Fires | Fire Watch | 57010138 | 13.5 | 81.03 | 1093.905 | 210 | 1303.905 |  |  |  | mVolts
176478 | Ryan Moses | Labourer | 00677 - Valard | 2021-07-30 | FORFIRES - Forest Fires | Fire Watch | 57010138 | 11 | 81.03 | 891.33 | 210 | 1101.33 |  |  |  | mVolts
117128 | Kirk Somers | Project Assistant/Coord | 00677 - Valard | 2021-07-30 | FORFIRES - Forest Fires | Monitoring site for Fire watch compliance. Weekly Safety Meeting | 57010138 | 11 | 91.26 | 1003.86 | 210 | 1213.86 |  |  |  | mVolts
176478 | Ryan Moses | Labourer | 00677 - Valard | 2021-07-31 | FORFIRES - Forest Fires | Fire Watch | 57010138 | 1 | 81.03 | 81.03 | 19.0909 | 100.1209 |  |  |  | mVolts
117128 | Kirk Somers | Project Assistant/Coord | 00677 - Valard | 2021-08-02 | FORFIRES - Forest Fires | Preparation for upcoming work in restricted fire zone | 57010138 | 2 | 91.26 | 182.52 | 38.1818 | 220.7018 |  |  |  | mVolts
117128 | Kirk Somers | Project Assistant/Coord | 00677 - Valard | 2021-08-03 | FORFIRES - Forest Fires | Crossover discussion with Kim to ensure compliance for fire restricted zone | 57010138 | 1 | 91.26 | 91.26 | 19.0909 | 110.3509 |  |  |  | mVolts
154287 | Kimberly Frankland | Safety Supervisor | 00677 - Valard | 2021-08-04 | FORFIRES - Forest Fires | preparation fire watch | 57010138 | 1 | 111.7 | 111.7 | 19.0909 | 130.7909 |  |  |  | mVolts
154287 | Kimberly Frankland | Safety Supervisor | 00677 - Valard | 2021-08-05 | FORFIRES - Forest Fires | fire | 57010138 | 5 | 111.7 | 558.5 | 95.4545 | 653.9545 |  |  |  | mVolts
154287 | Kimberly Frankland | Safety Supervisor | 00677 - Valard | 2021-08-06 | FORFIRES - Forest Fires | Fire | 57010138 | 5 | 111.7 | 558.5 | 95.4545 | 653.9545 |  |  |  | mVolts
154287 | Kimberly Frankland | Safety Supervisor | 00677 - Valard | 2021-08-07 | FORFIRES - Forest Fires | fire C 006 | 57010138 | 5 | 111.7 | 558.5 | 95.4545 | 653.9545 |  |  |  | mVolts
154287 | Kimberly Frankland | Safety Supervisor | 00677 - Valard | 2021-08-08 | FORFIRES - Forest Fires | fire C006 | 57010138 | 6 | 111.7 | 670.2 | 114.5455 | 784.7455 |  |  |  | mVolts
205991 | Stephen Crawley | Apprentice - 1st Year | 00677 - Valard | 2021-08-12 | FORFIRES - Forest Fires | Move 200t off site. | 57010138 | 5 | 70.81 | 354.05 | 95.4545 | 449.5045 |  |  |  | mVolts
117346 | Robert Bjerkelund | Foreman | 00677 - Valard | 2021-08-12 | FORFIRES - Forest Fires | Move 200t off site. | 57010138 | 5 | 146.89 | 734.45 | 95.4545 | 829.9045 |  |  |  | mVolts
118087 | Thomas Howes | Supervisor | 00677 - Valard | 2021-08-12 | FORFIRES - Forest Fires | Move 200t off site. | 57010138 | 5 | 150.59 | 752.95 | 95.4545 | 848.4045 |  |  |  | mVolts
117296 | Andrew Beauchemin | Equipment Operator | 00677 - Valard | 2021-08-12 | FORFIRES - Forest Fires | Move 200t off site. | 57010138 | 5 | 111.7 | 558.5 | 95.4545 | 653.9545 |  |  |  | mVolts
117128 | Kirk Somers | Project Assistant/Coord | 00677 - Valard | 2021-08-15 | FORFIRES - Forest Fires | Monitoring of sites and fire cache (with tote) inspection | 57010138 | 1 | 91.26 | 91.26 | 19.0909 | 110.3509 |  |  |  | mVolts
117128 | Kirk Somers | Project Assistant/Coord | 00677 - Valard | 2021-08-16 | FORFIRES - Forest Fires | Inspection of Fire Cache and Fire Equipment | 57010138 | 1 | 91.26 | 91.26 | 19.0909 | 110.3509 |  |  |  | mVolts
117128 | Kirk Somers | Project Assistant/Coord | 00677 - Valard | 2021-08-19 | FORFIRES - Forest Fires | Working on improving fire response | 57010138 | 1 | 91.26 | 91.26 | 19.0909 | 110.3509 |  |  |  | mVolts
117128 | Kirk Somers | Project Assistant/Coord | 00677 - Valard | 2021-08-20 | FORFIRES - Forest Fires | Working on IOP protocol communication | 57010138 | 1 | 91.26 | 91.26 | 19.0909 | 110.3509 |  |  |  | mVolts
117128 | Kirk Somers | Project Assistant/Coord | 00677 - Valard | 2021-08-21 | FORFIRES - Forest Fires | Ongoing communication of IOP requirements with crews | 57010138 | 1 | 91.26 | 91.26 | 19.0909 | 110.3509 |  |  |  | mVolts
117128 | Kirk Somers | Project Assistant/Coord | 00677 - Valard | 2021-08-22 | FORFIRES - Forest Fires | Incident Investigation information | 57010138 | 3 | 91.26 | 273.78 | 57.2727 | 331.0527 |  |  |  | mVolts
119036 | Junior Stuckey | Equipment Operator | 00677 - Valard | 2021-08-22 | FORFIRES - Forest Fires | Fire Watch | 57010138 | 4 | 111.7 | 446.8 | 76.3636 | 523.1636 |  |  |  | mVolts
191544 | Neil Burnet | Labourer | 00677 - Valard | 2021-08-22 | FORFIRES - Forest Fires | Fire Watch | 57010138 | 4 | 81.03 | 324.12 | 76.3636 | 400.4836 |  |  |  | mVolts
117128 | Kirk Somers | Project Assistant/Coord | 00677 - Valard | 2021-08-23 | FORFIRES - Forest Fires | Ongoing monitoring, coaching for I.O.P compliance | 57010138 | 2 | 91.26 | 182.52 | 38.1818 | 220.7018 |  |  |  | mVolts

## DPCache_All Equipment (hidden)
Equipment | Description | Company | Date | Activity | Notes | Cost Code | Hours | Rate | Equipment Cost | Facility | Structures | Activity Tags | Timesheet Tags | Unit Number
10624 - Ford F350 Crew 4WD | Crew Cab Truck | 00675 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Get all equipment moved off ROW to laydowns for hauling. | 57010138 | 9 | 31.95 | 287.55 |  |  |  | mVolts | 10624
72861 - John Deere 210G Excavator | JD 200 Track-hoe | 00675 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Mobilize equipment | 57010138 | 1 | 138.54 | 138.54 |  |  |  | mVolts | 72861
2824 - 2015 F350 Crew 4x4 Flex | Crew Cab Truck | 00675 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Mobilize equipment | 57010138 | 1 | 31.95 | 31.95 |  |  |  | mVolts | 2824
72863 - Komatsu Excavator | JD 200 Track-hoe | 00675 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Travel equipment to laydown | 57010138 | 2 | 138.54 | 277.08 |  |  |  | mVolts | 72863
10547 - Ford Super Duty F350 SRW XLT 4 | Pickup | 00675 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Travel equipment to laydown | 57010138 | 3 | 27.07 | 81.21 |  |  |  | mVolts | 10547
10622 - Ford F350 Crew 4WD | Crew Cab Truck | 00675 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Travel equipment to laydown | 57010138 | 3 | 31.95 | 95.85 |  |  |  | mVolts | 10622
2214 - 2017 F350 | Pickup | 00675 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Travel equipment to laydown | 57010138 | 6 | 27.07 | 162.42 |  |  |  | mVolts | 2214
021471 - Ford F250 4X4 Crewcab Pickup | Crew Cab Truck | 00675 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Moving equipment off site | 57010138 | 1.5 | 31.95 | 47.925 |  |  |  | mVolts | 21471
10577 - Ford Super Duty F250 SRW XLT 4 | Pickup | 00675 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Move equipment from sitr to road | 57010138 | 3 | 27.07 | 81.21 |  |  |  | mVolts | 10577
10544 - Ford Super Duty F350 SRW XLT 4 | Pickup | 00675 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Move equipment from sitr to road | 57010138 | 3 | 27.07 | 81.21 |  |  |  | mVolts | 10544
2963 - Ford F250 4X4 Crewcab Pickup | Crew Cab Truck | 00675 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Move equipment from sitr to road | 57010138 | 3 | 31.95 | 95.85 |  |  |  | mVolts | 2963
7002 - John Deere 210G Excavator | JD 200 Track-hoe | 00675 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Move equipment from sitr to road | 57010138 | 3 | 138.54 | 415.62 |  |  |  | mVolts | 7002
76373 - Boom 135' Telescopic With JIB | 120' Gene Lift | 00675 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Walked equipment out of ROW, structures a002 and b197 | 57010138 | 2 | 90.19 | 180.38 |  |  |  | mVolts | 76373
72853 - Hydraulic Excavator | JD 350 LDC Excavator | 00675 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Walked equipment out of ROW, structures a002 and b197 | 57010138 | 1 | 173.26 | 173.26 |  |  |  | mVolts | 72853
569028 - JD 644K 4WD Wheelloader | JD 554 Loader | 00675 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Walked equipment out of ROW, structures a002 and b197 | 57010138 | 1 | 73.49 | 73.49 |  |  |  | mVolts | 569028
7955 - 2014 LTM 1130-5.1 Mobile Crane | 130T RT Crane | 00675 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Walked equipment out of ROW, structures a002 and b197 | 57010138 | 1 | 335 | 335 |  |  |  | mVolts | 7955
7975 - Liebherr LTM1200 Mobile Crane | 200T All-Tr. Crane | 00675 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Walked equipment out of ROW, structures a002 and b197 | 57010138 | 1 | 431.32 | 431.32 |  |  |  | mVolts | 7975
2619 - F350 pickup | Pickup | 00675 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Walked equipment out of ROW, structures a002 and b197 | 57010138 | 9 | 27.07 | 243.63 |  |  |  | mVolts | 2619
2169 - Ford Crew 4x4 Flex 2015 | Crew Cab Truck | 00675 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Walked equipment out of ROW, structures a002 and b197 | 57010138 | 9 | 31.95 | 287.55 |  |  |  | mVolts | 2169
2869 - 2017 Ford F350 W3B | Pickup | 00675 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Walked equipment out of ROW, structures a002 and b197 | 57010138 | 9 | 27.07 | 243.63 |  |  |  | mVolts | 2869
2825 - Ford Crew 4x4 Flex 2015 | Crew Cab Truck | 00675 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Walked equipment out of ROW, structures a002 and b197 | 57010138 | 9 | 31.95 | 287.55 |  |  |  | mVolts | 2825
2091 - Ford Crew 4x4 Flex Fuel 2014 | Crew Cab Truck | 00675 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Walked equipment out of ROW, structures a002 and b197 | 57010138 | 9 | 31.95 | 287.55 |  |  |  | mVolts | 2091
2050 - Ford Crew 4x4 Flex Fuel 2013 | Crew Cab Truck | 00675 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Walked equipment out of ROW, structures a002 and b197 | 57010138 | 9 | 31.95 | 287.55 |  |  |  | mVolts | 2050
7596 - 2012 JD 250G LC Excavator | JD 200 Track-hoe | 00675 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Walk out drill from Str C099 to laydown due to fires | 57010138 | 3 | 138.54 | 415.62 |  |  |  | mVolts | 7596
2767 - Ford Crew 4x4 Flex 2015 | Crew Cab Truck | 00675 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Walk out drill from Str C099 to laydown due to fires | 57010138 | 3 | 31.95 | 95.85 |  |  |  | mVolts | 2767
932042 - Gerry 55 Ton Tridem Lowboy | Tridem Trailer | 00675 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Equipment Hauling from Restricted Area | 57010138 | 11 | 11.5 | 126.5 |  |  |  | mVolts | 932042
3292 - 2015 Kenworth Tractor | Tractor Trailer | 00675 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Equipment Hauling from Restricted Area | 57010138 | 11 | 137.22 | 1509.42 |  |  |  | mVolts | 3292
4703 - 2008 Peerless LB65-DSBTHAN-3A | Tridem Trailer | 00675 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Equipment Hauling from Restricted Area | 57010138 | 5.5 | 11.5 | 63.25 |  |  |  | mVolts | 4703
TT10 - Tractor Peterbilt 367 Tridrive | Tractor Trailer | 00675 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Equipment Hauling from Restricted Area | 57010138 | 5.5 | 137.22 | 754.71 |  |  |  | mVolts | TT10
7649 - John Deere 225D LC Excavator | JD 200 Track-hoe | 00675 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Walked machines out due to forest fires | 57010138 | 6 | 138.54 | 831.24 |  |  |  | mVolts | 7649
2990 - Ford F250 4X4 Crewcab Pickup | Crew Cab Truck | 00675 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Walked machines out due to forest fires | 57010138 | 6.5 | 31.95 | 207.675 |  |  |  | mVolts | 2990
021458 - 2020 F250 4X4 Crewcab Pickup | Crew Cab Truck | 00675 - Valard | 2021-07-20 | FORFIRES - Forest Fires | Mob Gear/crews out | 57010138 | 2 | 31.95 | 63.9 |  |  |  | mVolts | 21458
10624 - Ford F350 Crew 4WD | Crew Cab Truck | 00675 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Moving equipment from Thunder Bay to white lake laydown. | 57010138 | 12 | 31.95 | 383.4 |  |  |  | mVolts | 10624
2826 - 2015 F350 Crew 4x4 Flex | Crew Cab Truck | 00675 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Move equipment | 57010138 | 11 | 31.95 | 351.45 |  |  |  | mVolts | 2826
10547 - Ford Super Duty F350 SRW XLT 4 | Pickup | 00675 - Valard | 2021-07-21 | FORFIRES - Forest Fires | N/a | 57010138 | 11 | 27.07 | 297.77 |  |  |  | mVolts | 10547
10622 - Ford F350 Crew 4WD | Crew Cab Truck | 00675 - Valard | 2021-07-21 | FORFIRES - Forest Fires | N/a | 57010138 | 11 | 31.95 | 351.45 |  |  |  | mVolts | 10622
2214 - 2017 F350 | Pickup | 00675 - Valard | 2021-07-21 | FORFIRES - Forest Fires | N/a | 57010138 | 11 | 27.07 | 297.77 |  |  |  | mVolts | 2214
10582 - Ford Super Duty F250 SRW XLT 4 | Crew Cab Truck | 00675 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Travel fire caches to marathon | 57010138 | 11 | 31.95 | 351.45 |  |  |  | mVolts | 10582
10580 - Ford Super Duty F250 SRW XLT 4 | Crew Cab Truck | 00675 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Travel fire caches to marathon | 57010138 | 11 | 31.95 | 351.45 |  |  |  | mVolts | 10580
021471 - Ford F250 4X4 Crewcab Pickup | Crew Cab Truck | 00675 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Travel fire caches to marathon | 57010138 | 11 | 31.95 | 351.45 |  |  |  | mVolts | 21471
2824 - 2015 F350 Crew 4x4 Flex | Crew Cab Truck | 00675 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Mobilze from nipigon to wawa | 57010138 | 4 | 31.95 | 127.8 |  |  |  | mVolts | 2824
2570 - F350 pickup | Pickup | 00675 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Mobilze from nipigon to wawa | 57010138 | 4 | 27.07 | 108.28 |  |  |  | mVolts | 2570
10583 - Ford Super Duty F350 SRW XLT 4 | Crew Cab Truck | 00675 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Mobilze from nipigon to wawa | 57010138 | 4 | 31.95 | 127.8 |  |  |  | mVolts | 10583
932042 - Gerry 55 Ton Tridem Lowboy | Tridem Trailer | 00675 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Equipment Hauling from Restricted Area | 57010138 | 11 | 11.5 | 126.5 |  |  |  | mVolts | 932042
3292 - 2015 Kenworth Tractor | Tractor Trailer | 00675 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Equipment Hauling from Restricted Area | 57010138 | 11 | 137.22 | 1509.42 |  |  |  | mVolts | 3292
4703 - 2008 Peerless LB65-DSBTHAN-3A | Tridem Trailer | 00675 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Equipment Hauling from Restricted Area | 57010138 | 11.5 | 11.5 | 132.25 |  |  |  | mVolts | 4703
TT10 - Tractor Peterbilt 367 Tridrive | Tractor Trailer | 00675 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Equipment Hauling from Restricted Area | 57010138 | 11.5 | 137.22 | 1578.03 |  |  |  | mVolts | TT10
2990 - Ford F250 4X4 Crewcab Pickup | Crew Cab Truck | 00675 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Meeting in the morning at Marathon. Clean grout,truck demoved equipment , move it to Marathon. Organized crews | 57010138 | 11 | 31.95 | 351.45 |  |  |  | mVolts | 2990
76369 - Boom 135' Telescopic With JIB | 120' Gene Lift | 00675 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Floated equipment between white lake east and macgregor rd | 57010138 | 2 | 90.19 | 180.38 |  |  |  | mVolts | 76369
76373 - Boom 135' Telescopic With JIB | 120' Gene Lift | 00675 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Floated equipment between white lake east and macgregor rd | 57010138 | 4 | 90.19 | 360.76 |  |  |  | mVolts | 76373
72869 - Hydraulic Excavator | JD 200 Track-hoe | 00675 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Floated equipment between white lake east and macgregor rd | 57010138 | 2 | 138.54 | 277.08 |  |  |  | mVolts | 72869
72853 - Hydraulic Excavator | JD 350 LDC Excavator | 00675 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Floated equipment between white lake east and macgregor rd | 57010138 | 4 | 173.26 | 693.04 |  |  |  | mVolts | 72853
7029 - 2013 JD 450J Dozer | Crawler Tractors 750 JD | 00675 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Floated equipment between white lake east and macgregor rd | 57010138 | 2 | 175.9 | 351.8 |  |  |  | mVolts | 7029
569028 - JD 644K 4WD Wheelloader | JD 554 Loader | 00675 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Floated equipment between white lake east and macgregor rd | 57010138 | 4 | 73.49 | 293.96 |  |  |  | mVolts | 569028
7955 - 2014 LTM 1130-5.1 Mobile Crane | 130T RT Crane | 00675 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Floated equipment between white lake east and macgregor rd | 57010138 | 12 | 335 | 4020 |  |  |  | mVolts | 7955
7975 - Liebherr LTM1200 Mobile Crane | 200T All-Tr. Crane | 00675 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Floated equipment between white lake east and macgregor rd | 57010138 | 12 | 431.32 | 5175.84 |  |  |  | mVolts | 7975
2619 - F350 pickup | Pickup | 00675 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Floated equipment between white lake east and macgregor rd | 57010138 | 12 | 27.07 | 324.84 |  |  |  | mVolts | 2619
2169 - Ford Crew 4x4 Flex 2015 | Crew Cab Truck | 00675 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Floated equipment between white lake east and macgregor rd | 57010138 | 12 | 31.95 | 383.4 |  |  |  | mVolts | 2169
2869 - 2017 Ford F350 W3B | Pickup | 00675 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Floated equipment between white lake east and macgregor rd | 57010138 | 12 | 27.07 | 324.84 |  |  |  | mVolts | 2869
2825 - Ford Crew 4x4 Flex 2015 | Crew Cab Truck | 00675 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Floated equipment between white lake east and macgregor rd | 57010138 | 12 | 31.95 | 383.4 |  |  |  | mVolts | 2825
2091 - Ford Crew 4x4 Flex Fuel 2014 | Crew Cab Truck | 00675 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Floated equipment between white lake east and macgregor rd | 57010138 | 12 | 31.95 | 383.4 |  |  |  | mVolts | 2091
2050 - Ford Crew 4x4 Flex Fuel 2013 | Crew Cab Truck | 00675 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Floated equipment between white lake east and macgregor rd | 57010138 | 12 | 31.95 | 383.4 |  |  |  | mVolts | 2050
2767 - Ford Crew 4x4 Flex 2015 | Crew Cab Truck | 00675 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Getting equipment ready for float | 57010138 | 11 | 31.95 | 351.45 |  |  |  | mVolts | 2767
2184 - Ford Crew 4x4 Flex 2015 | Crew Cab Truck | 00675 - Valard | 2021-07-21 | FORFIRES - Forest Fires | Shut down due to extreme fire conditions. Cleaned truck. Got drills ready on Cooks rd and Antler rd for floats to move gear. | 57010138 | 11 | 31.95 | 351.45 |  |  |  | mVolts | 2184
10624 - Ford F350 Crew 4WD | Crew Cab Truck | 00675 - Valard | 2021-07-22 | FORFIRES - Forest Fires | Moving cranes around and hauling equipment. | 57010138 | 12 | 31.95 | 383.4 |  |  |  | mVolts | 10624
7948 - 2013 Liebherr LTM 1200-5.1 | 200T All-Tr. Crane | 00675 - Valard | 2021-07-22 | FORFIRES - Forest Fires | Piloted cranes ad mob'd equipment between white lake east and macgregor rd | 57010138 | 12 | 431.32 | 5175.84 |  |  |  | mVolts | 7948
76369 - Boom 135' Telescopic With JIB | 120' Gene Lift | 00675 - Valard | 2021-07-22 | FORFIRES - Forest Fires | Piloted cranes ad mob'd equipment between white lake east and macgregor rd | 57010138 | 4 | 90.19 | 360.76 |  |  |  | mVolts | 76369
76373 - Boom 135' Telescopic With JIB | 120' Gene Lift | 00675 - Valard | 2021-07-22 | FORFIRES - Forest Fires | Piloted cranes ad mob'd equipment between white lake east and macgregor rd | 57010138 | 4 | 90.19 | 360.76 |  |  |  |  | 76373
72869 - Hydraulic Excavator | JD 200 Track-hoe | 00675 - Valard | 2021-07-22 | FORFIRES - Forest Fires | Piloted cranes ad mob'd equipment between white lake east and macgregor rd | 57010138 | 2 | 138.54 | 277.08 |  |  |  |  | 72869
72853 - Hydraulic Excavator | JD 350 LDC Excavator | 00675 - Valard | 2021-07-22 | FORFIRES - Forest Fires | Piloted cranes ad mob'd equipment between white lake east and macgregor rd | 57010138 | 2 | 173.26 | 346.52 |  |  |  |  | 72853
7029 - 2013 JD 450J Dozer | Crawler Tractors 750 JD | 00675 - Valard | 2021-07-22 | FORFIRES - Forest Fires | Piloted cranes ad mob'd equipment between white lake east and macgregor rd | 57010138 | 2 | 175.9 | 351.8 |  |  |  |  | 7029
569028 - JD 644K 4WD Wheelloader | JD 554 Loader | 00675 - Valard | 2021-07-22 | FORFIRES - Forest Fires | Piloted cranes ad mob'd equipment between white lake east and macgregor rd | 57010138 | 2 | 73.49 | 146.98 |  |  |  |  | 569028
7955 - 2014 LTM 1130-5.1 Mobile Crane | 130T RT Crane | 00675 - Valard | 2021-07-22 | FORFIRES - Forest Fires | Piloted cranes ad mob'd equipment between white lake east and macgregor rd | 57010138 | 10 | 335 | 3350 |  |  |  |  | 7955
7975 - Liebherr LTM1200 Mobile Crane | 200T All-Tr. Crane | 00675 - Valard | 2021-07-22 | FORFIRES - Forest Fires | Piloted cranes ad mob'd equipment between white lake east and macgregor rd | 57010138 | 10 | 431.32 | 4313.2 |  |  |  |  | 7975
2619 - F350 pickup | Pickup | 00675 - Valard | 2021-07-22 | FORFIRES - Forest Fires | Piloted cranes ad mob'd equipment between white lake east and macgregor rd | 57010138 | 12 | 27.07 | 324.84 |  |  |  |  | 2619
2169 - Ford Crew 4x4 Flex 2015 | Crew Cab Truck | 00675 - Valard | 2021-07-22 | FORFIRES - Forest Fires | Piloted cranes ad mob'd equipment between white lake east and macgregor rd | 57010138 | 12 | 31.95 | 383.4 |  |  |  |  | 2169
2869 - 2017 Ford F350 W3B | Pickup | 00675 - Valard | 2021-07-22 | FORFIRES - Forest Fires | Piloted cranes ad mob'd equipment between white lake east and macgregor rd | 57010138 | 12 | 27.07 | 324.84 |  |  |  |  | 2869
2825 - Ford Crew 4x4 Flex 2015 | Crew Cab Truck | 00675 - Valard | 2021-07-22 | FORFIRES - Forest Fires | Piloted cranes ad mob'd equipment between white lake east and macgregor rd | 57010138 | 12 | 31.95 | 383.4 |  |  |  |  | 2825
2091 - Ford Crew 4x4 Flex Fuel 2014 | Crew Cab Truck | 00675 - Valard | 2021-07-22 | FORFIRES - Forest Fires | Piloted cranes ad mob'd equipment between white lake east and macgregor rd | 57010138 | 12 | 31.95 | 383.4 |  |  |  |  | 2091
2050 - Ford Crew 4x4 Flex Fuel 2013 | Crew Cab Truck | 00675 - Valard | 2021-07-22 | FORFIRES - Forest Fires | Piloted cranes ad mob'd equipment between white lake east and macgregor rd | 57010138 | 12 | 31.95 | 383.4 |  |  |  |  | 2050
2767 - Ford Crew 4x4 Flex 2015 | Crew Cab Truck | 00675 - Valard | 2021-07-22 | FORFIRES - Forest Fires | Mobe to Wawa from Schrieber | 57010138 | 4 | 31.95 | 127.8 |  |  |  |  | 2767
932044 - Gerry 55 Ton Tridem Lowboy | Tridem Trailer | 00675 - Valard | 2021-07-22 | FORFIRES - Forest Fires | Equipment Hauling from Restricted Area | 57010138 | 6 | 11.5 | 69 |  |  |  |  | 932044
3293 - 2016 Kenworth Tractor | Tractor Trailer | 00675 - Valard | 2021-07-22 | FORFIRES - Forest Fires | Equipment Hauling from Restricted Area | 57010138 | 6 | 137.22 | 823.32 |  |  |  |  | 3293
7948 - 2013 Liebherr LTM 1200-5.1 | 200T All-Tr. Crane | 00675 - Valard | 2021-07-23 | FORFIRES - Forest Fires | Moving equipment due to fire ban. | 57010138 | 11 | 431.32 | 4744.52 |  |  |  |  | 7948
76369 - Boom 135' Telescopic With JIB | 120' Gene Lift | 00675 - Valard | 2021-07-23 | FORFIRES - Forest Fires | Moving equipment due to fire ban. | 57010138 | 11 | 90.19 | 992.09 |  |  |  |  | 76369
76373 - Boom 135' Telescopic With JIB | 120' Gene Lift | 00675 - Valard | 2021-07-23 | FORFIRES - Forest Fires | Moving equipment due to fire ban. | 57010138 | 11 | 90.19 | 992.09 |  |  |  |  | 76373
72869 - Hydraulic Excavator | JD 200 Track-hoe | 00675 - Valard | 2021-07-23 | FORFIRES - Forest Fires | Moving equipment due to fire ban. | 57010138 | 11 | 138.54 | 1523.94 |  |  |  |  | 72869
72853 - Hydraulic Excavator | JD 350 LDC Excavator | 00675 - Valard | 2021-07-23 | FORFIRES - Forest Fires | Moving equipment due to fire ban. | 57010138 | 11 | 173.26 | 1905.86 |  |  |  |  | 72853
7029 - 2013 JD 450J Dozer | Crawler Tractors 750 JD | 00675 - Valard | 2021-07-23 | FORFIRES - Forest Fires | Moving equipment due to fire ban. | 57010138 | 11 | 175.9 | 1934.9 |  |  |  |  | 7029
569028 - JD 644K 4WD Wheelloader | JD 554 Loader | 00675 - Valard | 2021-07-23 | FORFIRES - Forest Fires | Moving equipment due to fire ban. | 57010138 | 11 | 73.49 | 808.39 |  |  |  |  | 569028
7975 - Liebherr LTM1200 Mobile Crane | 200T All-Tr. Crane | 00675 - Valard | 2021-07-23 | FORFIRES - Forest Fires | Moving equipment due to fire ban. | 57010138 | 11 | 431.32 | 4744.52 |  |  |  |  | 7975
2169 - Ford Crew 4x4 Flex 2015 | Crew Cab Truck | 00675 - Valard | 2021-07-23 | FORFIRES - Forest Fires | Moving equipment due to fire ban. | 57010138 | 11 | 31.95 | 351.45 |  |  |  |  | 2169
2869 - 2017 Ford F350 W3B | Pickup | 00675 - Valard | 2021-07-23 | FORFIRES - Forest Fires | Moving equipment due to fire ban. | 57010138 | 11 | 27.07 | 297.77 |  |  |  |  | 2869
2825 - Ford Crew 4x4 Flex 2015 | Crew Cab Truck | 00675 - Valard | 2021-07-23 | FORFIRES - Forest Fires | Moving equipment due to fire ban. | 57010138 | 11 | 31.95 | 351.45 |  |  |  |  | 2825
2091 - Ford Crew 4x4 Flex Fuel 2014 | Crew Cab Truck | 00675 - Valard | 2021-07-23 | FORFIRES - Forest Fires | Moving equipment due to fire ban. | 57010138 | 11 | 31.95 | 351.45 |  |  |  |  | 2091
2050 - Ford Crew 4x4 Flex Fuel 2013 | Crew Cab Truck | 00675 - Valard | 2021-07-23 | FORFIRES - Forest Fires | Moving equipment due to fire ban. | 57010138 | 11 | 31.95 | 351.45 |  |  |  |  | 2050
10624 - Ford F350 Crew 4WD | Crew Cab Truck | 00675 - Valard | 2021-07-23 | FORFIRES - Forest Fires | Moving equipment due to fire ban. | 57010138 | 11 | 31.95 | 351.45 |  |  |  |  | 10624
4703 - 2008 Peerless LB65-DSBTHAN-3A | Tridem Trailer | 00675 - Valard | 2021-07-23 | FORFIRES - Forest Fires | Equipment Hauling from Restricted Zone | 57010138 | 11 | 11.5 | 126.5 |  |  |  |  | 4703
TT10 - Tractor Peterbilt 367 Tridrive | Tractor Trailer | 00675 - Valard | 2021-07-23 | FORFIRES - Forest Fires | Equipment Hauling from Restricted Zone | 57010138 | 11 | 137.22 | 1509.42 |  |  |  |  | TT10
932042 - Gerry 55 Ton Tridem Lowboy | Tridem Trailer | 00675 - Valard | 2021-07-23 | FORFIRES - Forest Fires | Equipment Hauling from Restricted Zone | 57010138 | 12 | 11.5 | 138 |  |  |  |  | 932042
3292 - 2015 Kenworth Tractor | Tractor Trailer | 00675 - Valard | 2021-07-23 | FORFIRES - Forest Fires | Equipment Hauling from Restricted Zone | 57010138 | 12 | 137.22 | 1646.64 |  |  |  |  | 3292
2990 - Ford F250 4X4 Crewcab Pickup | Crew Cab Truck | 00675 - Valard | 2021-07-23 | FORFIRES - Forest Fires | Poured STR C061 with mixer on legs A,B and C Stripped STR C059. Get material to formed STR C070 | 57010138 | 11 | 31.95 | 351.45 |  |  |  |  | 2990
2981 - Ford F250 4X4 Crewcab Pickup | Crew Cab Truck | 00675 - Valard | 2021-07-23 | FORFIRES - Forest Fires | Travel from Thunderbay to White River | 57010138 | 7.5 | 31.95 | 239.625 |  |  |  |  | 2981
4703 - 2008 Peerless LB65-DSBTHAN-3A | Tridem Trailer | 00675 - Valard | 2021-07-24 | FORFIRES - Forest Fires | Equipment Hauling from Restricted Zone | 57010138 | 11 | 11.5 | 126.5 |  |  |  |  | 4703
TT10 - Tractor Peterbilt 367 Tridrive | Tractor Trailer | 00675 - Valard | 2021-07-24 | FORFIRES - Forest Fires | Equipment Hauling from Restricted Zone | 57010138 | 11 | 137.22 | 1509.42 |  |  |  |  | TT10
932044 - Gerry 55 Ton Tridem Lowboy | Tridem Trailer | 00675 - Valard | 2021-07-24 | FORFIRES - Forest Fires | Equipment Hauling from Restricted Zone | 57010138 | 7 | 11.5 | 80.5 |  |  |  |  | 932044
3293 - 2016 Kenworth Tractor | Tractor Trailer | 00675 - Valard | 2021-07-24 | FORFIRES - Forest Fires | Equipment Hauling from Restricted Zone | 57010138 | 7 | 137.22 | 960.54 |  |  |  |  | 3293
2990 - Ford F250 4X4 Crewcab Pickup | Crew Cab Truck | 00675 - Valard | 2021-07-24 | FORFIRES - Forest Fires | Poured grout pad with mixer at STR C070 and C072. | 57010138 | 11 | 31.95 | 351.45 |  |  |  |  | 2990
2983 - Ford F250 4X4 Crewcab Pickup | Crew Cab Truck | 00675 - Valard | 2021-07-24 | FORFIRES - Forest Fires | Travel from Thunder Bay to Wawa. | 57010138 | 10 | 31.95 | 319.5 |  |  |  |  | 2983
9198 - Trimble TSC7 w/Access Data Col | Survey Equipment | 00675 - Valard | 2021-07-24 | FORFIRES - Forest Fires | Travel from Thunder Bay to Wawa. | 57010138 | 10 | 55 | 550 |  |  |  |  | 9198
2826 - 2015 F350 Crew 4x4 Flex | Crew Cab Truck | 00675 - Valard | 2021-07-25 | FORFIRES - Forest Fires | Clean up | 57010138 | 11 | 31.95 | 351.45 |  |  |  |  | 2826
041855 - F350 FLAT DECK (Lineman Truck) | Pickup | 00675 - Valard | 2021-07-25 | FORFIRES - Forest Fires | Placed dowels and bent rebar for u-bar | 57010138 | 5 | 27.07 | 135.35 |  |  |  |  | 41855
041855 - F350 FLAT DECK (Lineman Truck) | Pickup | 00675 - Valard | 2021-07-25 | FORFIRES - Forest Fires | Carried in anchor bar from the laydown at Antler to str C068 and installed couplers to join on extensions . Then we put out dowels and bent u-bars | 57010138 | 6 | 27.07 | 162.42 |  |  |  |  | 41855
3340 - Kenworth T800BT/A w/ 1996 Hiab | Tractor Trailer | 00675 - Valard | 2021-07-25 | FORFIRES - Forest Fires | Hauling water totes back to marathon from access | 57010138 | 11 | 137.22 | 1509.42 |  |  |  |  | 3340
932044 - Gerry 55 Ton Tridem Lowboy | Tridem Trailer | 00675 - Valard | 2021-07-25 | FORFIRES - Forest Fires | Equipment Hauling from Restricted Zone | 57010138 | 4 | 11.5 | 46 |  |  |  |  | 932044
3293 - 2016 Kenworth Tractor | Tractor Trailer | 00675 - Valard | 2021-07-25 | FORFIRES - Forest Fires | Equipment Hauling from Restricted Zone | 57010138 | 4 | 137.22 | 548.88 |  |  |  |  | 3293
1508 - 2014 F150 Pickup | Pickup | 00675 - Valard | 2021-07-25 | FORFIRES - Forest Fires | Fire Watch Monitoring as per MNRF approval | 57010138 | 12 | 27.07 | 324.84 |  |  |  |  | 1508
2826 - 2015 F350 Crew 4x4 Flex | Crew Cab Truck | 00675 - Valard | 2021-07-26 | FORFIRES - Forest Fires | Clean up site | 57010138 | 11 | 31.95 | 351.45 |  |  |  |  | 2826
041855 - F350 FLAT DECK (Lineman Truck) | Pickup | 00675 - Valard | 2021-07-26 | FORFIRES - Forest Fires | Clean up spill on str c193,clean up sites in on Gurnney and carried extra steel to Antler laydown. | 57010138 | 11 | 27.07 | 297.77 |  |  |  |  | 41855
3340 - Kenworth T800BT/A w/ 1996 Hiab | Tractor Trailer | 00675 - Valard | 2021-07-26 | FORFIRES - Forest Fires | Loaded plywood,2x4 at nipigon yard and then loaded rebar at cooks road and went back to marathon for to deliver to Wawa | 57010138 | 11 | 137.22 | 1509.42 |  |  |  |  | 3340
1508 - 2014 F150 Pickup | Pickup | 00675 - Valard | 2021-07-26 | FORFIRES - Forest Fires | Fire Watch monitoring as required by MNRF | 57010138 | 12 | 27.07 | 324.84 |  |  |  |  | 1508
2794 - 2015 Ford Crew 4x4 Flex | Crew Cab Truck | 00675 - Valard | 2021-07-27 | FORFIRES - Forest Fires | Fire watch. | 57010138 | 14 | 31.95 | 447.3 |  |  |  |  | 2794
1508 - 2014 F150 Pickup | Pickup | 00675 - Valard | 2021-07-27 | FORFIRES - Forest Fires | Monitoring compliance to Fire Watch as required by MNRF | 57010138 | 12 | 27.07 | 324.84 |  |  |  |  | 1508
2794 - 2015 Ford Crew 4x4 Flex | Crew Cab Truck | 00675 - Valard | 2021-07-28 | FORFIRES - Forest Fires | Fire watch. | 57010138 | 12 | 31.95 | 383.4 |  |  |  |  | 2794
2619 - F350 pickup | Pickup | 00675 - Valard | 2021-07-28 | FORFIRES - Forest Fires | Mono poles ,move 200 ton to 600 rd | 57010138 | 11 | 27.07 | 297.77 |  |  |  |  | 2619
2091 - Ford Crew 4x4 Flex Fuel 2014 | Crew Cab Truck | 00675 - Valard | 2021-07-28 | FORFIRES - Forest Fires | Mono poles ,move 200 ton to 600 rd | 57010138 | 11 | 31.95 | 351.45 |  |  |  |  | 2091
7955 - 2014 LTM 1130-5.1 Mobile Crane | 130T RT Crane | 00675 - Valard | 2021-07-28 | FORFIRES - Forest Fires | Mono poles ,move 200 ton to 600 rd | 57010138 | 11 | 335 | 3685 |  |  |  |  | 7955
10624 - Ford F350 Crew 4WD | Crew Cab Truck | 00675 - Valard | 2021-07-28 | FORFIRES - Forest Fires | Moved crane from Thunder Bay to 600rd due to fire ban. | 57010138 | 11 | 31.95 | 351.45 |  |  |  |  | 10624
1508 - 2014 F150 Pickup | Pickup | 00675 - Valard | 2021-07-28 | FORFIRES - Forest Fires | Ongoing monitoring of Fire Watch requirements as per MNRF | 57010138 | 12 | 27.07 | 324.84 |  |  |  |  | 1508
1508 - 2014 F150 Pickup | Pickup | 00675 - Valard | 2021-07-29 | FORFIRES - Forest Fires | Monitoring site for compliance to fire watch as required by MNRF | 57010138 | 12 | 27.07 | 324.84 |  |  |  |  | 1508
1508 - 2014 F150 Pickup | Pickup | 00675 - Valard | 2021-07-30 | FORFIRES - Forest Fires | Monitoring site for Fire watch compliance. Weekly Safety Meeting | 57010138 | 11 | 27.07 | 297.77 |  |  |  |  | 1508
10624 - Ford F350 Crew 4WD | Crew Cab Truck | 00675 - Valard | 2021-08-12 | FORFIRES - Forest Fires | Move 200t off site. | 57010138 | 5 | 31.95 | 159.75 |  |  |  |  | 10624
2769 - Ford Crew 4x4 Flex 2015 | Crew Cab Truck | 00675 - Valard | 2021-08-22 | FORFIRES - Forest Fires | Fire Watch | 57010138 | 4 | 31.95 | 127.8 |  |  |  |  | 2769

## DPCache_LEM Backup (hidden)
Company | ID | ROWSegment | TicketID | TimeTicket | CostCode | Category | NightShift | Activity | Rate | ActivityUnits | UnitofMeasure | StandByRate | StandByUnit | OvertimeRate | OvertimeUnit | SubTotal | GST | Total | TicketDate | Paid | InvoiceNumber | InvoiceDate | Invoice ID | Error | ExtraWork | AddedBy | Task | AssociatedTask | Contract_Number | PO_Number | WorkOrder | Notes | ChangeManagementID | Status | DESCRIPTION OF CHANGE | CHANGE ORDER NUMBER | Description | WF | Specific IDs | LocationsWorked | CM_Boolean | SubmittedToValard | ChangeManagementType | ApprovedBy | ApprovedDate | ThirdPartyTicket | ThirdPartyNote | Crossing # | Road Type | Crossing Type | ApproverFullName | Workfront | ID-1 | ID-2 | Item - 1 | Item - 2 | Net
Northern Mat & Bridge | 15 | 0 | 9954 | 21658 | 53530601 | Rig/Access Mats | 0 | Subsistence Per Day | 225 | 6 | DAY |  |  |  | 0 | 1350 | 175.5 | 1525.5 | 2021-09-22 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travel in. safety meeting. Truck mats in, unload trucks, shuttle mats, lay mats as per Valard instruction. Very busy site with 10 gravel trucks hauling. Shuttles waiting on gravel trucks. 230 mats trucked in. layed 215 mats 90m double layer, 80m single. total onsite 320. crew travel out. ***COVID 19 policies in effect*** | 6 | C262-C266 | Hare Lake Road | 0 | 2021-09-24 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge995421658Subsistence Per Day61350 | Northern Mat & Bridge995421658Subsistence Per Day61350ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9954 | 21658 | 53530601 | Rig/Access Mats | 0 | Operator | 84.69 | 8 | HR |  |  | 127.04 | 2 | 931.6 | 121.108 | 1052.708 | 2021-09-22 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travel in. safety meeting. Truck mats in, unload trucks, shuttle mats, lay mats as per Valard instruction. Very busy site with 10 gravel trucks hauling. Shuttles waiting on gravel trucks. 230 mats trucked in. layed 215 mats 90m double layer, 80m single. total onsite 320. crew travel out. ***COVID 19 policies in effect*** | 6 | C262-C266 | Hare Lake Road | 0 | 2021-09-24 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge995421658Operator8931.6 | Northern Mat & Bridge995421658Operator8931.6ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9954 | 21658 | 53530601 | Rig/Access Mats | 0 | Operator | 84.69 | 8 | HR |  |  | 127.04 | 3 | 1058.64 | 137.6232 | 1196.2632 | 2021-09-22 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travel in. safety meeting. Truck mats in, unload trucks, shuttle mats, lay mats as per Valard instruction. Very busy site with 10 gravel trucks hauling. Shuttles waiting on gravel trucks. 230 mats trucked in. layed 215 mats 90m double layer, 80m single. total onsite 320. crew travel out. ***COVID 19 policies in effect*** | 6 | C262-C266 | Hare Lake Road | 0 | 2021-09-24 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge995421658Operator81058.64 | Northern Mat & Bridge995421658Operator81058.64ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9954 | 21658 | 53530601 | Rig/Access Mats | 0 | Operator | 84.69 | 8 | HR |  |  | 127.04 | 3 | 1058.64 | 137.6232 | 1196.2632 | 2021-09-22 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travel in. safety meeting. Truck mats in, unload trucks, shuttle mats, lay mats as per Valard instruction. Very busy site with 10 gravel trucks hauling. Shuttles waiting on gravel trucks. 230 mats trucked in. layed 215 mats 90m double layer, 80m single. total onsite 320. crew travel out. ***COVID 19 policies in effect*** | 6 | C262-C266 | Hare Lake Road | 0 | 2021-09-24 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge995421658Operator81058.64 | Northern Mat & Bridge995421658Operator81058.64ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9954 | 21658 | 53530601 | Rig/Access Mats | 0 | Operator | 84.69 | 8 | HR |  |  | 127.04 | 4 | 1185.68 | 154.1384 | 1339.8184 | 2021-09-22 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travel in. safety meeting. Truck mats in, unload trucks, shuttle mats, lay mats as per Valard instruction. Very busy site with 10 gravel trucks hauling. Shuttles waiting on gravel trucks. 230 mats trucked in. layed 215 mats 90m double layer, 80m single. total onsite 320. crew travel out. ***COVID 19 policies in effect*** | 6 | C262-C266 | Hare Lake Road | 0 | 2021-09-24 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge995421658Operator81185.68 | Northern Mat & Bridge995421658Operator81185.68ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9954 | 21658 | 53530601 | Rig/Access Mats | 0 | Operator | 84.69 | 8 | HR |  |  | 127.04 | 3 | 1058.64 | 137.6232 | 1196.2632 | 2021-09-22 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travel in. safety meeting. Truck mats in, unload trucks, shuttle mats, lay mats as per Valard instruction. Very busy site with 10 gravel trucks hauling. Shuttles waiting on gravel trucks. 230 mats trucked in. layed 215 mats 90m double layer, 80m single. total onsite 320. crew travel out. ***COVID 19 policies in effect*** | 6 | C262-C266 | Hare Lake Road | 0 | 2021-09-24 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge995421658Operator81058.64 | Northern Mat & Bridge995421658Operator81058.64ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9954 | 21658 | 53530601 | Rig/Access Mats | 0 | Supervisor | 101.49 | 8 | HR |  |  | 129 | 5 | 1456.92 | 189.3996 | 1646.3196 | 2021-09-22 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travel in. safety meeting. Truck mats in, unload trucks, shuttle mats, lay mats as per Valard instruction. Very busy site with 10 gravel trucks hauling. Shuttles waiting on gravel trucks. 230 mats trucked in. layed 215 mats 90m double layer, 80m single. total onsite 320. crew travel out. ***COVID 19 policies in effect*** | 6 | C262-C266 | Hare Lake Road | 0 | 2021-09-24 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge995421658Supervisor81456.92 | Northern Mat & Bridge995421658Supervisor81456.92ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9954 | 21658 | 53530601 | Rig/Access Mats | 0 | Flatbed Truck | 187.5 | 20 | HR |  | 0 |  |  | 3750 | 487.5 | 4237.5 | 2021-09-22 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travel in. safety meeting. Truck mats in, unload trucks, shuttle mats, lay mats as per Valard instruction. Very busy site with 10 gravel trucks hauling. Shuttles waiting on gravel trucks. 230 mats trucked in. layed 215 mats 90m double layer, 80m single. total onsite 320. crew travel out. ***COVID 19 policies in effect*** | 6 | C262-C266 | Hare Lake Road | 0 | 2021-09-24 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge995421658Flatbed Truck203750 | Northern Mat & Bridge995421658Flatbed Truck203750ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9954 | 21658 | 53530601 | Rig/Access Mats | 0 | Float Truck | 199.14 | 11 | HR |  | 0 |  |  | 2190.54 | 284.7702 | 2475.3102 | 2021-09-22 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travel in. safety meeting. Truck mats in, unload trucks, shuttle mats, lay mats as per Valard instruction. Very busy site with 10 gravel trucks hauling. Shuttles waiting on gravel trucks. 230 mats trucked in. layed 215 mats 90m double layer, 80m single. total onsite 320. crew travel out. ***COVID 19 policies in effect*** | 6 | C262-C266 | Hare Lake Road | 0 | 2021-09-24 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge995421658Float Truck112190.54 | Northern Mat & Bridge995421658Float Truck112190.54ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9954 | 21658 | 53530601 | Rig/Access Mats | 0 | Track Carrier | 172.56 | 19 | HR |  | 0 |  |  | 3278.64 | 426.2232 | 3704.8632 | 2021-09-22 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travel in. safety meeting. Truck mats in, unload trucks, shuttle mats, lay mats as per Valard instruction. Very busy site with 10 gravel trucks hauling. Shuttles waiting on gravel trucks. 230 mats trucked in. layed 215 mats 90m double layer, 80m single. total onsite 320. crew travel out. ***COVID 19 policies in effect*** | 6 | C262-C266 | Hare Lake Road | 0 | 2021-09-24 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge995421658Track Carrier193278.64 | Northern Mat & Bridge995421658Track Carrier193278.64ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9954 | 21658 | 53530601 | Rig/Access Mats | 0 | Loader | 98.83 | 8 | HR |  | 0 |  |  | 790.64 | 102.7832 | 893.4232 | 2021-09-22 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travel in. safety meeting. Truck mats in, unload trucks, shuttle mats, lay mats as per Valard instruction. Very busy site with 10 gravel trucks hauling. Shuttles waiting on gravel trucks. 230 mats trucked in. layed 215 mats 90m double layer, 80m single. total onsite 320. crew travel out. ***COVID 19 policies in effect*** | 6 | C262-C266 | Hare Lake Road | 0 | 2021-09-24 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge995421658Loader8790.64 | Northern Mat & Bridge995421658Loader8790.64ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9954 | 21658 | 53530601 | Rig/Access Mats | 0 | Loader | 98.83 | 10 | HR |  | 0 |  |  | 988.3 | 128.479 | 1116.779 | 2021-09-22 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travel in. safety meeting. Truck mats in, unload trucks, shuttle mats, lay mats as per Valard instruction. Very busy site with 10 gravel trucks hauling. Shuttles waiting on gravel trucks. 230 mats trucked in. layed 215 mats 90m double layer, 80m single. total onsite 320. crew travel out. ***COVID 19 policies in effect*** | 6 | C262-C266 | Hare Lake Road | 0 | 2021-09-24 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge995421658Loader10988.3 | Northern Mat & Bridge995421658Loader10988.3ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9954 | 21658 | 53530601 | Rig/Access Mats | 0 | Excavator | 127.81 | 9 | HR |  | 0 |  |  | 1150.29 | 149.5377 | 1299.8277 | 2021-09-22 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travel in. safety meeting. Truck mats in, unload trucks, shuttle mats, lay mats as per Valard instruction. Very busy site with 10 gravel trucks hauling. Shuttles waiting on gravel trucks. 230 mats trucked in. layed 215 mats 90m double layer, 80m single. total onsite 320. crew travel out. ***COVID 19 policies in effect*** | 6 | C262-C266 | Hare Lake Road | 0 | 2021-09-24 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge995421658Excavator91150.29 | Northern Mat & Bridge995421658Excavator91150.29ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9954 | 21658 | 53530601 | Rig/Access Mats | 0 | Crew Truck | 225 | 2 | DAY |  | 0 |  |  | 450 | 58.5 | 508.5 | 2021-09-22 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travel in. safety meeting. Truck mats in, unload trucks, shuttle mats, lay mats as per Valard instruction. Very busy site with 10 gravel trucks hauling. Shuttles waiting on gravel trucks. 230 mats trucked in. layed 215 mats 90m double layer, 80m single. total onsite 320. crew travel out. ***COVID 19 policies in effect*** | 6 | C262-C266 | Hare Lake Road | 0 | 2021-09-24 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge995421658Crew Truck2450 | Northern Mat & Bridge995421658Crew Truck2450ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9949 | 21657 | 53530601 | Rig/Access Mats | 0 | Subsistence Per Day | 225 | 6 | DAY |  |  |  | 0 | 1350 | 175.5 | 1525.5 | 2021-09-22 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | Crew travelled to site, safety meeting. Move 4 pieces of equipment from Del Lake to Hare Lake. 2 guys on each site to help lowbed load and unload. Hare Lake extremely busy with gravel trucks hauling and no radio communication. Nick unloading and loading trucks Marathon yard. Keegan and Daniel sent to town after lowbed was finished. jamie and dylan unload mats at Hare lake and walked excavator up to ROW. crew travelled out. ***COVID 19 policies in effect*** | 6 | C262-C266 | Hare Lake Creek | 0 | 2021-09-21 |  | 37 | 2021-09-25 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge994921657Subsistence Per Day61350 | Northern Mat & Bridge994921657Subsistence Per Day61350ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9949 | 21657 | 53530601 | Rig/Access Mats | 0 | Operator | 84.69 | 8 | HR |  |  | 127.04 | 4 | 1185.68 | 154.1384 | 1339.8184 | 2021-09-22 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | Crew travelled to site, safety meeting. Move 4 pieces of equipment from Del Lake to Hare Lake. 2 guys on each site to help lowbed load and unload. Hare Lake extremely busy with gravel trucks hauling and no radio communication. Nick unloading and loading trucks Marathon yard. Keegan and Daniel sent to town after lowbed was finished. jamie and dylan unload mats at Hare lake and walked excavator up to ROW. crew travelled out. ***COVID 19 policies in effect*** | 6 | C262-C266 | Hare Lake Creek | 0 | 2021-09-21 |  | 37 | 2021-09-25 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge994921657Operator81185.68 | Northern Mat & Bridge994921657Operator81185.68ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9949 | 21657 | 53530601 | Rig/Access Mats | 0 | Operator | 84.69 | 8 | HR |  |  | 127.04 | 0 | 677.52 | 88.0776 | 765.5976 | 2021-09-22 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | Crew travelled to site, safety meeting. Move 4 pieces of equipment from Del Lake to Hare Lake. 2 guys on each site to help lowbed load and unload. Hare Lake extremely busy with gravel trucks hauling and no radio communication. Nick unloading and loading trucks Marathon yard. Keegan and Daniel sent to town after lowbed was finished. jamie and dylan unload mats at Hare lake and walked excavator up to ROW. crew travelled out. ***COVID 19 policies in effect*** | 6 | C262-C266 | Hare Lake Creek | 0 | 2021-09-21 |  | 37 | 2021-09-25 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge994921657Operator8677.52 | Northern Mat & Bridge994921657Operator8677.52ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9949 | 21657 | 53530601 | Rig/Access Mats | 0 | Operator | 84.69 | 8 | HR |  |  | 127.04 | 0 | 677.52 | 88.0776 | 765.5976 | 2021-09-22 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | Crew travelled to site, safety meeting. Move 4 pieces of equipment from Del Lake to Hare Lake. 2 guys on each site to help lowbed load and unload. Hare Lake extremely busy with gravel trucks hauling and no radio communication. Nick unloading and loading trucks Marathon yard. Keegan and Daniel sent to town after lowbed was finished. jamie and dylan unload mats at Hare lake and walked excavator up to ROW. crew travelled out. ***COVID 19 policies in effect*** | 6 | C262-C266 | Hare Lake Creek | 0 | 2021-09-21 |  | 37 | 2021-09-25 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge994921657Operator8677.52 | Northern Mat & Bridge994921657Operator8677.52ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9949 | 21657 | 53530601 | Rig/Access Mats | 0 | Operator | 84.69 | 8 | HR |  |  | 127.04 | 4 | 1185.68 | 154.1384 | 1339.8184 | 2021-09-22 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | Crew travelled to site, safety meeting. Move 4 pieces of equipment from Del Lake to Hare Lake. 2 guys on each site to help lowbed load and unload. Hare Lake extremely busy with gravel trucks hauling and no radio communication. Nick unloading and loading trucks Marathon yard. Keegan and Daniel sent to town after lowbed was finished. jamie and dylan unload mats at Hare lake and walked excavator up to ROW. crew travelled out. ***COVID 19 policies in effect*** | 6 | C262-C266 | Hare Lake Creek | 0 | 2021-09-21 |  | 37 | 2021-09-25 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge994921657Operator81185.68 | Northern Mat & Bridge994921657Operator81185.68ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9949 | 21657 | 53530601 | Rig/Access Mats | 0 | Operator | 84.69 | 8 | HR |  |  | 127.04 | 2 | 931.6 | 121.108 | 1052.708 | 2021-09-22 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | Crew travelled to site, safety meeting. Move 4 pieces of equipment from Del Lake to Hare Lake. 2 guys on each site to help lowbed load and unload. Hare Lake extremely busy with gravel trucks hauling and no radio communication. Nick unloading and loading trucks Marathon yard. Keegan and Daniel sent to town after lowbed was finished. jamie and dylan unload mats at Hare lake and walked excavator up to ROW. crew travelled out. ***COVID 19 policies in effect*** | 6 | C262-C266 | Hare Lake Creek | 0 | 2021-09-21 |  | 37 | 2021-09-25 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge994921657Operator8931.6 | Northern Mat & Bridge994921657Operator8931.6ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9949 | 21657 | 53530601 | Rig/Access Mats | 0 | Supervisor | 101.49 | 8 | HR |  |  | 129 | 5 | 1456.92 | 189.3996 | 1646.3196 | 2021-09-22 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | Crew travelled to site, safety meeting. Move 4 pieces of equipment from Del Lake to Hare Lake. 2 guys on each site to help lowbed load and unload. Hare Lake extremely busy with gravel trucks hauling and no radio communication. Nick unloading and loading trucks Marathon yard. Keegan and Daniel sent to town after lowbed was finished. jamie and dylan unload mats at Hare lake and walked excavator up to ROW. crew travelled out. ***COVID 19 policies in effect*** | 6 | C262-C266 | Hare Lake Creek | 0 | 2021-09-21 |  | 37 | 2021-09-25 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge994921657Supervisor81456.92 | Northern Mat & Bridge994921657Supervisor81456.92ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9949 | 21657 | 53530601 | Rig/Access Mats | 0 | Flatbed Truck | 187.5 | 8.5 | HR |  | 0 |  |  | 1593.75 | 207.1875 | 1800.9375 | 2021-09-22 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | Crew travelled to site, safety meeting. Move 4 pieces of equipment from Del Lake to Hare Lake. 2 guys on each site to help lowbed load and unload. Hare Lake extremely busy with gravel trucks hauling and no radio communication. Nick unloading and loading trucks Marathon yard. Keegan and Daniel sent to town after lowbed was finished. jamie and dylan unload mats at Hare lake and walked excavator up to ROW. crew travelled out. ***COVID 19 policies in effect*** | 6 | C262-C266 | Hare Lake Creek | 0 | 2021-09-21 |  | 37 | 2021-09-25 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge994921657Flatbed Truck8.51593.75 | Northern Mat & Bridge994921657Flatbed Truck8.51593.75ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9949 | 21657 | 53530601 | Rig/Access Mats | 0 | Float Truck | 199.14 | 13 | HR |  | 0 |  |  | 2588.82 | 336.5466 | 2925.3666 | 2021-09-22 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | Crew travelled to site, safety meeting. Move 4 pieces of equipment from Del Lake to Hare Lake. 2 guys on each site to help lowbed load and unload. Hare Lake extremely busy with gravel trucks hauling and no radio communication. Nick unloading and loading trucks Marathon yard. Keegan and Daniel sent to town after lowbed was finished. jamie and dylan unload mats at Hare lake and walked excavator up to ROW. crew travelled out. ***COVID 19 policies in effect*** | 6 | C262-C266 | Hare Lake Creek | 0 | 2021-09-21 |  | 37 | 2021-09-25 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge994921657Float Truck132588.82 | Northern Mat & Bridge994921657Float Truck132588.82ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9949 | 21657 | 53530601 | Rig/Access Mats | 0 | Loader | 98.83 | 8 | HR |  | 0 |  |  | 790.64 | 102.7832 | 893.4232 | 2021-09-22 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | Crew travelled to site, safety meeting. Move 4 pieces of equipment from Del Lake to Hare Lake. 2 guys on each site to help lowbed load and unload. Hare Lake extremely busy with gravel trucks hauling and no radio communication. Nick unloading and loading trucks Marathon yard. Keegan and Daniel sent to town after lowbed was finished. jamie and dylan unload mats at Hare lake and walked excavator up to ROW. crew travelled out. ***COVID 19 policies in effect*** | 6 | C262-C266 | Hare Lake Creek | 0 | 2021-09-21 |  | 37 | 2021-09-25 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge994921657Loader8790.64 | Northern Mat & Bridge994921657Loader8790.64ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9949 | 21657 | 53530601 | Rig/Access Mats | 0 | Loader | 98.83 | 2 | HR |  | 0 |  |  | 197.66 | 25.6958 | 223.3558 | 2021-09-22 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | Crew travelled to site, safety meeting. Move 4 pieces of equipment from Del Lake to Hare Lake. 2 guys on each site to help lowbed load and unload. Hare Lake extremely busy with gravel trucks hauling and no radio communication. Nick unloading and loading trucks Marathon yard. Keegan and Daniel sent to town after lowbed was finished. jamie and dylan unload mats at Hare lake and walked excavator up to ROW. crew travelled out. ***COVID 19 policies in effect*** | 6 | C262-C266 | Hare Lake Creek | 0 | 2021-09-21 |  | 37 | 2021-09-25 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge994921657Loader2197.66 | Northern Mat & Bridge994921657Loader2197.66ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9949 | 21657 | 53530601 | Rig/Access Mats | 0 | Excavator | 127.81 | 1 | HR |  | 0 |  |  | 127.81 | 16.6153 | 144.4253 | 2021-09-22 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | Crew travelled to site, safety meeting. Move 4 pieces of equipment from Del Lake to Hare Lake. 2 guys on each site to help lowbed load and unload. Hare Lake extremely busy with gravel trucks hauling and no radio communication. Nick unloading and loading trucks Marathon yard. Keegan and Daniel sent to town after lowbed was finished. jamie and dylan unload mats at Hare lake and walked excavator up to ROW. crew travelled out. ***COVID 19 policies in effect*** | 6 | C262-C266 | Hare Lake Creek | 0 | 2021-09-21 |  | 37 | 2021-09-25 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge994921657Excavator1127.81 | Northern Mat & Bridge994921657Excavator1127.81ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9949 | 21657 | 53530601 | Rig/Access Mats | 0 | Crew Truck | 225 | 2 | DAY |  | 0 |  |  | 450 | 58.5 | 508.5 | 2021-09-22 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | Crew travelled to site, safety meeting. Move 4 pieces of equipment from Del Lake to Hare Lake. 2 guys on each site to help lowbed load and unload. Hare Lake extremely busy with gravel trucks hauling and no radio communication. Nick unloading and loading trucks Marathon yard. Keegan and Daniel sent to town after lowbed was finished. jamie and dylan unload mats at Hare lake and walked excavator up to ROW. crew travelled out. ***COVID 19 policies in effect*** | 6 | C262-C266 | Hare Lake Creek | 0 | 2021-09-21 |  | 37 | 2021-09-25 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge994921657Crew Truck2450 | Northern Mat & Bridge994921657Crew Truck2450ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9889 | 21655 | 53530601 | Rig/Access Mats | 0 | Subsistence Per Day | 225 | 6 | DAY |  |  |  | 0 | 1350 | 175.5 | 1525.5 | 2021-09-20 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travel in, safety meeting. Unload trucks. Load shuttles. Lay mats as per valard instuction. 180 mats trucked and layed. Covering 200 meters. 1021 total mats on site. 709C, 312D. ***COVID19 policies in effect*** | 6 | C186-C195 | Del Lake | 0 | 2021-09-21 |  | 37 | 2021-09-25 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge988921655Subsistence Per Day61350 | Northern Mat & Bridge988921655Subsistence Per Day61350ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9889 | 21655 | 53530601 | Rig/Access Mats | 0 | Operator | 84.69 | 8 | HR |  |  | 127.04 | 2 | 931.6 | 121.108 | 1052.708 | 2021-09-20 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travel in, safety meeting. Unload trucks. Load shuttles. Lay mats as per valard instuction. 180 mats trucked and layed. Covering 200 meters. 1021 total mats on site. 709C, 312D. ***COVID19 policies in effect*** | 6 | C186-C195 | Del Lake | 0 | 2021-09-21 |  | 37 | 2021-09-25 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge988921655Operator8931.6 | Northern Mat & Bridge988921655Operator8931.6ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9889 | 21655 | 53530601 | Rig/Access Mats | 0 | Operator | 84.69 | 8 | HR |  |  | 127.04 | 2 | 931.6 | 121.108 | 1052.708 | 2021-09-20 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travel in, safety meeting. Unload trucks. Load shuttles. Lay mats as per valard instuction. 180 mats trucked and layed. Covering 200 meters. 1021 total mats on site. 709C, 312D. ***COVID19 policies in effect*** | 6 | C186-C195 | Del Lake | 0 | 2021-09-21 |  | 37 | 2021-09-25 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge988921655Operator8931.6 | Northern Mat & Bridge988921655Operator8931.6ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9889 | 21655 | 53530601 | Rig/Access Mats | 0 | Operator | 84.69 | 8 | HR |  |  | 127.04 | 2 | 931.6 | 121.108 | 1052.708 | 2021-09-20 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travel in, safety meeting. Unload trucks. Load shuttles. Lay mats as per valard instuction. 180 mats trucked and layed. Covering 200 meters. 1021 total mats on site. 709C, 312D. ***COVID19 policies in effect*** | 6 | C186-C195 | Del Lake | 0 | 2021-09-21 |  | 37 | 2021-09-25 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge988921655Operator8931.6 | Northern Mat & Bridge988921655Operator8931.6ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9889 | 21655 | 53530601 | Rig/Access Mats | 0 | Operator | 84.69 | 8 | HR |  |  | 127.04 | 2 | 931.6 | 121.108 | 1052.708 | 2021-09-20 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travel in, safety meeting. Unload trucks. Load shuttles. Lay mats as per valard instuction. 180 mats trucked and layed. Covering 200 meters. 1021 total mats on site. 709C, 312D. ***COVID19 policies in effect*** | 6 | C186-C195 | Del Lake | 0 | 2021-09-21 |  | 37 | 2021-09-25 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge988921655Operator8931.6 | Northern Mat & Bridge988921655Operator8931.6ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9889 | 21655 | 53530601 | Rig/Access Mats | 0 | Operator | 84.69 | 8 | HR |  |  | 127.04 | 2 | 931.6 | 121.108 | 1052.708 | 2021-09-20 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travel in, safety meeting. Unload trucks. Load shuttles. Lay mats as per valard instuction. 180 mats trucked and layed. Covering 200 meters. 1021 total mats on site. 709C, 312D. ***COVID19 policies in effect*** | 6 | C186-C195 | Del Lake | 0 | 2021-09-21 |  | 37 | 2021-09-25 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge988921655Operator8931.6 | Northern Mat & Bridge988921655Operator8931.6ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9889 | 21655 | 53530601 | Rig/Access Mats | 0 | Supervisor | 101.49 | 8 | HR |  |  | 129 | 3 | 1198.92 | 155.8596 | 1354.7796 | 2021-09-20 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travel in, safety meeting. Unload trucks. Load shuttles. Lay mats as per valard instuction. 180 mats trucked and layed. Covering 200 meters. 1021 total mats on site. 709C, 312D. ***COVID19 policies in effect*** | 6 | C186-C195 | Del Lake | 0 | 2021-09-21 |  | 37 | 2021-09-25 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge988921655Supervisor81198.92 | Northern Mat & Bridge988921655Supervisor81198.92ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9889 | 21655 | 53530601 | Rig/Access Mats | 0 | Track Carrier | 172.56 | 9 | HR |  | 0 |  |  | 1553.04 | 201.8952 | 1754.9352 | 2021-09-20 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travel in, safety meeting. Unload trucks. Load shuttles. Lay mats as per valard instuction. 180 mats trucked and layed. Covering 200 meters. 1021 total mats on site. 709C, 312D. ***COVID19 policies in effect*** | 6 | C186-C195 | Del Lake | 0 | 2021-09-21 |  | 37 | 2021-09-25 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge988921655Track Carrier91553.04 | Northern Mat & Bridge988921655Track Carrier91553.04ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9889 | 21655 | 53530601 | Rig/Access Mats | 0 | Track Carrier | 172.56 | 9 | HR |  | 0 |  |  | 1553.04 | 201.8952 | 1754.9352 | 2021-09-20 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travel in, safety meeting. Unload trucks. Load shuttles. Lay mats as per valard instuction. 180 mats trucked and layed. Covering 200 meters. 1021 total mats on site. 709C, 312D. ***COVID19 policies in effect*** | 6 | C186-C195 | Del Lake | 0 | 2021-09-21 |  | 37 | 2021-09-25 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge988921655Track Carrier91553.04 | Northern Mat & Bridge988921655Track Carrier91553.04ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9889 | 21655 | 53530601 | Rig/Access Mats | 0 | Loader | 98.83 | 4 | HR |  | 0 |  |  | 395.32 | 51.3916 | 446.7116 | 2021-09-20 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travel in, safety meeting. Unload trucks. Load shuttles. Lay mats as per valard instuction. 180 mats trucked and layed. Covering 200 meters. 1021 total mats on site. 709C, 312D. ***COVID19 policies in effect*** | 6 | C186-C195 | Del Lake | 0 | 2021-09-21 |  | 37 | 2021-09-25 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge988921655Loader4395.32 | Northern Mat & Bridge988921655Loader4395.32ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9889 | 21655 | 53530601 | Rig/Access Mats | 0 | Loader | 98.83 | 9 | HR |  | 0 |  |  | 889.47 | 115.6311 | 1005.1011 | 2021-09-20 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travel in, safety meeting. Unload trucks. Load shuttles. Lay mats as per valard instuction. 180 mats trucked and layed. Covering 200 meters. 1021 total mats on site. 709C, 312D. ***COVID19 policies in effect*** | 6 | C186-C195 | Del Lake | 0 | 2021-09-21 |  | 37 | 2021-09-25 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge988921655Loader9889.47 | Northern Mat & Bridge988921655Loader9889.47ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9889 | 21655 | 53530601 | Rig/Access Mats | 0 | Excavator | 127.81 | 9 | HR |  | 0 |  |  | 1150.29 | 149.5377 | 1299.8277 | 2021-09-20 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travel in, safety meeting. Unload trucks. Load shuttles. Lay mats as per valard instuction. 180 mats trucked and layed. Covering 200 meters. 1021 total mats on site. 709C, 312D. ***COVID19 policies in effect*** | 6 | C186-C195 | Del Lake | 0 | 2021-09-21 |  | 37 | 2021-09-25 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge988921655Excavator91150.29 | Northern Mat & Bridge988921655Excavator91150.29ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9889 | 21655 | 53530601 | Rig/Access Mats | 0 | Crew Truck | 225 | 3 | DAY |  | 0 |  |  | 675 | 87.75 | 762.75 | 2021-09-20 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travel in, safety meeting. Unload trucks. Load shuttles. Lay mats as per valard instuction. 180 mats trucked and layed. Covering 200 meters. 1021 total mats on site. 709C, 312D. ***COVID19 policies in effect*** | 6 | C186-C195 | Del Lake | 0 | 2021-09-21 |  | 37 | 2021-09-25 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge988921655Crew Truck3675 | Northern Mat & Bridge988921655Crew Truck3675ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9888 | 21654 | 53530601 | Rig/Access Mats | 0 | Subsistence Per Day | 225 | 7 | DAY |  |  |  | 0 | 1575 | 204.75 | 1779.75 | 2021-09-19 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travel in. safety meeting. Unload trucks, shuttle mats, lay mats as per Valard instruction. Nick travel to Marathon en route to wawa pv km 214.Dylan Therrien loading trucks in Orangeville. Crew travel out. *** COVID 19 policies in effect. 156 mats trucked and layed, 150 meters covered, double layer matting. 841 total mats on site. 529C, 312D | 6 | C186-C195 | Del Lake | 0 | 2021-09-20 |  | 37 | 2021-09-21 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge988821654Subsistence Per Day71575 | Northern Mat & Bridge988821654Subsistence Per Day71575ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9888 | 21654 | 53530601 | Rig/Access Mats | 0 | Travel per KM | 0.82 | 214 | km |  |  |  | 0 | 175.48 | 22.8124 | 198.2924 | 2021-09-19 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travel in. safety meeting. Unload trucks, shuttle mats, lay mats as per Valard instruction. Nick travel to Marathon en route to wawa pv km 214.Dylan Therrien loading trucks in Orangeville. Crew travel out. *** COVID 19 policies in effect. 156 mats trucked and layed, 150 meters covered, double layer matting. 841 total mats on site. 529C, 312D | 6 | C186-C195 | Del Lake | 0 | 2021-09-20 |  | 37 | 2021-09-21 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge988821654Travel per KM214175.48 | Northern Mat & Bridge988821654Travel per KM214175.48ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9888 | 21654 | 53530601 | Rig/Access Mats | 0 | Operator - Sunday/Stat Holidays |  | 0 |  |  |  | 169.42 | 4 | 677.68 | 88.0984 | 765.7784 | 2021-09-19 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travel in. safety meeting. Unload trucks, shuttle mats, lay mats as per Valard instruction. Nick travel to Marathon en route to wawa pv km 214.Dylan Therrien loading trucks in Orangeville. Crew travel out. *** COVID 19 policies in effect. 156 mats trucked and layed, 150 meters covered, double layer matting. 841 total mats on site. 529C, 312D | 6 | C186-C195 | Del Lake | 0 | 2021-09-20 |  | 37 | 2021-09-21 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge988821654Operator - Sunday/Stat Holidays0677.68 | Northern Mat & Bridge988821654Operator - Sunday/Stat Holidays0677.68ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9888 | 21654 | 53530601 | Rig/Access Mats | 0 | Operator - Sunday/Stat Holidays | [5 empty] | 169.42 | 2.5 | 423.55 | 55.0615 | 478.6115 | 2021-09-19 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travel in. safety meeting. Unload trucks, shuttle mats, lay mats as per Valard instruction. Nick travel to Marathon en route to wawa pv km 214.Dylan Therrien loading trucks in Orangeville. Crew travel out. *** COVID 19 policies in effect. 156 mats trucked and layed, 150 meters covered, double layer matting. 841 total mats on site. 529C, 312D | 6 | C186-C195 | Del Lake | 0 | 2021-09-20 |  | 37 | 2021-09-21 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge988821654Operator - Sunday/Stat Holidays423.55 | Northern Mat & Bridge988821654Operator - Sunday/Stat Holidays423.55ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9888 | 21654 | 53530601 | Rig/Access Mats | 0 | Operator - Sunday/Stat Holidays |  | 0 |  |  |  | 169.42 | 10 | 1694.2 | 220.246 | 1914.446 | 2021-09-19 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travel in. safety meeting. Unload trucks, shuttle mats, lay mats as per Valard instruction. Nick travel to Marathon en route to wawa pv km 214.Dylan Therrien loading trucks in Orangeville. Crew travel out. *** COVID 19 policies in effect. 156 mats trucked and layed, 150 meters covered, double layer matting. 841 total mats on site. 529C, 312D | 6 | C186-C195 | Del Lake | 0 | 2021-09-20 |  | 37 | 2021-09-21 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge988821654Operator - Sunday/Stat Holidays01694.2 | Northern Mat & Bridge988821654Operator - Sunday/Stat Holidays01694.2ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9888 | 21654 | 53530601 | Rig/Access Mats | 0 | Operator - Sunday/Stat Holidays |  | 0 |  |  |  | 169.42 | 10 | 1694.2 | 220.246 | 1914.446 | 2021-09-19 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travel in. safety meeting. Unload trucks, shuttle mats, lay mats as per Valard instruction. Nick travel to Marathon en route to wawa pv km 214.Dylan Therrien loading trucks in Orangeville. Crew travel out. *** COVID 19 policies in effect. 156 mats trucked and layed, 150 meters covered, double layer matting. 841 total mats on site. 529C, 312D | 6 | C186-C195 | Del Lake | 0 | 2021-09-20 |  | 37 | 2021-09-21 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge988821654Operator - Sunday/Stat Holidays01694.2 | Northern Mat & Bridge988821654Operator - Sunday/Stat Holidays01694.2ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9888 | 21654 | 53530601 | Rig/Access Mats | 0 | Operator - Sunday/Stat Holidays |  | 0 |  |  |  | 169.42 | 10 | 1694.2 | 220.246 | 1914.446 | 2021-09-19 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travel in. safety meeting. Unload trucks, shuttle mats, lay mats as per Valard instruction. Nick travel to Marathon en route to wawa pv km 214.Dylan Therrien loading trucks in Orangeville. Crew travel out. *** COVID 19 policies in effect. 156 mats trucked and layed, 150 meters covered, double layer matting. 841 total mats on site. 529C, 312D | 6 | C186-C195 | Del Lake | 0 | 2021-09-20 |  | 37 | 2021-09-21 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge988821654Operator - Sunday/Stat Holidays01694.2 | Northern Mat & Bridge988821654Operator - Sunday/Stat Holidays01694.2ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9888 | 21654 | 53530601 | Rig/Access Mats | 0 | Operator - Sunday/Stat Holidays |  | 0 |  |  |  | 169.42 | 10 | 1694.2 | 220.246 | 1914.446 | 2021-09-19 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travel in. safety meeting. Unload trucks, shuttle mats, lay mats as per Valard instruction. Nick travel to Marathon en route to wawa pv km 214.Dylan Therrien loading trucks in Orangeville. Crew travel out. *** COVID 19 policies in effect. 156 mats trucked and layed, 150 meters covered, double layer matting. 841 total mats on site. 529C, 312D | 6 | C186-C195 | Del Lake | 0 | 2021-09-20 |  | 37 | 2021-09-21 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge988821654Operator - Sunday/Stat Holidays01694.2 | Northern Mat & Bridge988821654Operator - Sunday/Stat Holidays01694.2ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9888 | 21654 | 53530601 | Rig/Access Mats | 0 | Supervisor - Sunday/Stat Holidays |  | 0 |  |  |  | 156.9 | 11 | 1725.9 | 224.367 | 1950.267 | 2021-09-19 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travel in. safety meeting. Unload trucks, shuttle mats, lay mats as per Valard instruction. Nick travel to Marathon en route to wawa pv km 214.Dylan Therrien loading trucks in Orangeville. Crew travel out. *** COVID 19 policies in effect. 156 mats trucked and layed, 150 meters covered, double layer matting. 841 total mats on site. 529C, 312D | 6 | C186-C195 | Del Lake | 0 | 2021-09-20 |  | 37 | 2021-09-21 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge988821654Supervisor - Sunday/Stat Holidays01725.9 | Northern Mat & Bridge988821654Supervisor - Sunday/Stat Holidays01725.9ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9888 | 21654 | 53530601 | Rig/Access Mats | 0 | Track Carrier | 172.56 | 8 | HR |  | 0 |  |  | 1380.48 | 179.4624 | 1559.9424 | 2021-09-19 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travel in. safety meeting. Unload trucks, shuttle mats, lay mats as per Valard instruction. Nick travel to Marathon en route to wawa pv km 214.Dylan Therrien loading trucks in Orangeville. Crew travel out. *** COVID 19 policies in effect. 156 mats trucked and layed, 150 meters covered, double layer matting. 841 total mats on site. 529C, 312D | 6 | C186-C195 | Del Lake | 0 | 2021-09-20 |  | 37 | 2021-09-21 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge988821654Track Carrier81380.48 | Northern Mat & Bridge988821654Track Carrier81380.48ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9888 | 21654 | 53530601 | Rig/Access Mats | 0 | Track Carrier | 172.56 | 7 | HR |  | 0 |  |  | 1207.92 | 157.0296 | 1364.9496 | 2021-09-19 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travel in. safety meeting. Unload trucks, shuttle mats, lay mats as per Valard instruction. Nick travel to Marathon en route to wawa pv km 214.Dylan Therrien loading trucks in Orangeville. Crew travel out. *** COVID 19 policies in effect. 156 mats trucked and layed, 150 meters covered, double layer matting. 841 total mats on site. 529C, 312D | 6 | C186-C195 | Del Lake | 0 | 2021-09-20 |  | 37 | 2021-09-21 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge988821654Track Carrier71207.92 | Northern Mat & Bridge988821654Track Carrier71207.92ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9888 | 21654 | 53530601 | Rig/Access Mats | 0 | Loader | 98.83 | 2 | HR |  | 0 |  |  | 197.66 | 25.6958 | 223.3558 | 2021-09-19 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travel in. safety meeting. Unload trucks, shuttle mats, lay mats as per Valard instruction. Nick travel to Marathon en route to wawa pv km 214.Dylan Therrien loading trucks in Orangeville. Crew travel out. *** COVID 19 policies in effect. 156 mats trucked and layed, 150 meters covered, double layer matting. 841 total mats on site. 529C, 312D | 6 | C186-C195 | Del Lake | 0 | 2021-09-20 |  | 37 | 2021-09-21 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge988821654Loader2197.66 | Northern Mat & Bridge988821654Loader2197.66ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9888 | 21654 | 53530601 | Rig/Access Mats | 0 | Loader | 98.83 | 9 | HR |  | 0 |  |  | 889.47 | 115.6311 | 1005.1011 | 2021-09-19 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travel in. safety meeting. Unload trucks, shuttle mats, lay mats as per Valard instruction. Nick travel to Marathon en route to wawa pv km 214.Dylan Therrien loading trucks in Orangeville. Crew travel out. *** COVID 19 policies in effect. 156 mats trucked and layed, 150 meters covered, double layer matting. 841 total mats on site. 529C, 312D | 6 | C186-C195 | Del Lake | 0 | 2021-09-20 |  | 37 | 2021-09-21 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge988821654Loader9889.47 | Northern Mat & Bridge988821654Loader9889.47ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9888 | 21654 | 53530601 | Rig/Access Mats | 0 | Excavator | 127.81 | 7 | HR |  | 0 |  |  | 894.67 | 116.3071 | 1010.9771 | 2021-09-19 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travel in. safety meeting. Unload trucks, shuttle mats, lay mats as per Valard instruction. Nick travel to Marathon en route to wawa pv km 214.Dylan Therrien loading trucks in Orangeville. Crew travel out. *** COVID 19 policies in effect. 156 mats trucked and layed, 150 meters covered, double layer matting. 841 total mats on site. 529C, 312D | 6 | C186-C195 | Del Lake | 0 | 2021-09-20 |  | 37 | 2021-09-21 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge988821654Excavator7894.67 | Northern Mat & Bridge988821654Excavator7894.67ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9888 | 21654 | 53530601 | Rig/Access Mats | 0 | Crew Truck | 225 | 3 | DAY |  | 0 |  |  | 675 | 87.75 | 762.75 | 2021-09-19 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travel in. safety meeting. Unload trucks, shuttle mats, lay mats as per Valard instruction. Nick travel to Marathon en route to wawa pv km 214.Dylan Therrien loading trucks in Orangeville. Crew travel out. *** COVID 19 policies in effect. 156 mats trucked and layed, 150 meters covered, double layer matting. 841 total mats on site. 529C, 312D | 6 | C186-C195 | Del Lake | 0 | 2021-09-20 |  | 37 | 2021-09-21 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge988821654Crew Truck3675 | Northern Mat & Bridge988821654Crew Truck3675ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9838 | 21653 | 53530601 | Rig/Access Mats | 0 | Subsistence Per Day | 225 | 8 | DAY |  |  |  | 0 | 1800 | 234 | 2034 | 2021-09-18 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travelled in safety meeting, unload 2nd track carrier, move loader to thunder bay. Unload trucks, load shuttles, lay mats as per Valard instruction. Daniel travel infrom morrisburg to run 2nd track carrier 1472km paid for Personal vehicle us, No travel hours 2 loa.162 mats trucked and layed covering 150 meter, triple layer and pad built. 685 mats on site, 479C, 206D. *** COVID 19 policies in effect*** | 6 | C186-C195 | Del Lake | 0 | 2021-09-18 |  | 37 | 2021-09-20 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge983821653Subsistence Per Day81800 | Northern Mat & Bridge983821653Subsistence Per Day81800ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9838 | 21653 | 53530601 | Rig/Access Mats | 0 | Travel per KM | 0.82 | 1472 | km |  |  |  | 0 | 1207.04 | 156.9152 | 1363.9552 | 2021-09-18 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travelled in safety meeting, unload 2nd track carrier, move loader to thunder bay. Unload trucks, load shuttles, lay mats as per Valard instruction. Daniel travel infrom morrisburg to run 2nd track carrier 1472km paid for Personal vehicle us, No travel hours 2 loa.162 mats trucked and layed covering 150 meter, triple layer and pad built. 685 mats on site, 479C, 206D. *** COVID 19 policies in effect*** | 6 | C186-C195 | Del Lake | 0 | 2021-09-18 |  | 37 | 2021-09-20 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge983821653Travel per KM14721207.04 | Northern Mat & Bridge983821653Travel per KM14721207.04ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9838 | 21653 | 53530601 | Rig/Access Mats | 0 | Operator | 84.69 | 2 | HR |  |  | 127.04 | 6 | 931.62 | 121.1106 | 1052.7306 | 2021-09-18 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travelled in safety meeting, unload 2nd track carrier, move loader to thunder bay. Unload trucks, load shuttles, lay mats as per Valard instruction. Daniel travel infrom morrisburg to run 2nd track carrier 1472km paid for Personal vehicle us, No travel hours 2 loa.162 mats trucked and layed covering 150 meter, triple layer and pad built. 685 mats on site, 479C, 206D. *** COVID 19 policies in effect*** | 6 | C186-C195 | Del Lake | 0 | 2021-09-18 |  | 37 | 2021-09-20 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge983821653Operator2931.62 | Northern Mat & Bridge983821653Operator2931.62ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9838 | 21653 | 53530601 | Rig/Access Mats | 0 | Operator | 84.69 | 0 | HR |  |  | 127.04 | 11 | 1397.44 | 181.6672 | 1579.1072 | 2021-09-18 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travelled in safety meeting, unload 2nd track carrier, move loader to thunder bay. Unload trucks, load shuttles, lay mats as per Valard instruction. Daniel travel infrom morrisburg to run 2nd track carrier 1472km paid for Personal vehicle us, No travel hours 2 loa.162 mats trucked and layed covering 150 meter, triple layer and pad built. 685 mats on site, 479C, 206D. *** COVID 19 policies in effect*** | 6 | C186-C195 | Del Lake | 0 | 2021-09-18 |  | 37 | 2021-09-20 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge983821653Operator01397.44 | Northern Mat & Bridge983821653Operator01397.44ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9838 | 21653 | 53530601 | Rig/Access Mats | 0 | Operator | 84.69 | 0 | HR |  |  | 127.04 | 10 | 1270.4 | 165.152 | 1435.552 | 2021-09-18 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travelled in safety meeting, unload 2nd track carrier, move loader to thunder bay. Unload trucks, load shuttles, lay mats as per Valard instruction. Daniel travel infrom morrisburg to run 2nd track carrier 1472km paid for Personal vehicle us, No travel hours 2 loa.162 mats trucked and layed covering 150 meter, triple layer and pad built. 685 mats on site, 479C, 206D. *** COVID 19 policies in effect*** | 6 | C186-C195 | Del Lake | 0 | 2021-09-18 |  | 37 | 2021-09-20 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge983821653Operator01270.4 | Northern Mat & Bridge983821653Operator01270.4ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9838 | 21653 | 53530601 | Rig/Access Mats | 0 | Operator | 84.69 | 0 | HR |  |  | 127.04 | 5.5 | 698.72 | 90.8336 | 789.5536 | 2021-09-18 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travelled in safety meeting, unload 2nd track carrier, move loader to thunder bay. Unload trucks, load shuttles, lay mats as per Valard instruction. Daniel travel infrom morrisburg to run 2nd track carrier 1472km paid for Personal vehicle us, No travel hours 2 loa.162 mats trucked and layed covering 150 meter, triple layer and pad built. 685 mats on site, 479C, 206D. *** COVID 19 policies in effect*** | 6 | C186-C195 | Del Lake | 0 | 2021-09-18 |  | 37 | 2021-09-20 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge983821653Operator0698.72 | Northern Mat & Bridge983821653Operator0698.72ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9838 | 21653 | 53530601 | Rig/Access Mats | 0 | Operator | 84.69 | 0 | HR |  |  | 127.04 | 10 | 1270.4 | 165.152 | 1435.552 | 2021-09-18 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travelled in safety meeting, unload 2nd track carrier, move loader to thunder bay. Unload trucks, load shuttles, lay mats as per Valard instruction. Daniel travel infrom morrisburg to run 2nd track carrier 1472km paid for Personal vehicle us, No travel hours 2 loa.162 mats trucked and layed covering 150 meter, triple layer and pad built. 685 mats on site, 479C, 206D. *** COVID 19 policies in effect*** | 6 | C186-C195 | Del Lake | 0 | 2021-09-18 |  | 37 | 2021-09-20 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge983821653Operator01270.4 | Northern Mat & Bridge983821653Operator01270.4ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9838 | 21653 | 53530601 | Rig/Access Mats | 0 | Operator | 84.69 | 0 | HR |  |  | 127.04 | 10 | 1270.4 | 165.152 | 1435.552 | 2021-09-18 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travelled in safety meeting, unload 2nd track carrier, move loader to thunder bay. Unload trucks, load shuttles, lay mats as per Valard instruction. Daniel travel infrom morrisburg to run 2nd track carrier 1472km paid for Personal vehicle us, No travel hours 2 loa.162 mats trucked and layed covering 150 meter, triple layer and pad built. 685 mats on site, 479C, 206D. *** COVID 19 policies in effect*** | 6 | C186-C195 | Del Lake | 0 | 2021-09-18 |  | 37 | 2021-09-20 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge983821653Operator01270.4 | Northern Mat & Bridge983821653Operator01270.4ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9838 | 21653 | 53530601 | Rig/Access Mats | 0 | Supervisor | 101.49 | 0 | HR |  |  | 129 | 12 | 1548 | 201.24 | 1749.24 | 2021-09-18 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travelled in safety meeting, unload 2nd track carrier, move loader to thunder bay. Unload trucks, load shuttles, lay mats as per Valard instruction. Daniel travel infrom morrisburg to run 2nd track carrier 1472km paid for Personal vehicle us, No travel hours 2 loa.162 mats trucked and layed covering 150 meter, triple layer and pad built. 685 mats on site, 479C, 206D. *** COVID 19 policies in effect*** | 6 | C186-C195 | Del Lake | 0 | 2021-09-18 |  | 37 | 2021-09-20 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge983821653Supervisor01548 | Northern Mat & Bridge983821653Supervisor01548ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9838 | 21653 | 53530601 | Rig/Access Mats | 0 | Float Truck | 199.14 | 3 | HR |  | 0 |  |  | 597.42 | 77.6646 | 675.0846 | 2021-09-18 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travelled in safety meeting, unload 2nd track carrier, move loader to thunder bay. Unload trucks, load shuttles, lay mats as per Valard instruction. Daniel travel infrom morrisburg to run 2nd track carrier 1472km paid for Personal vehicle us, No travel hours 2 loa.162 mats trucked and layed covering 150 meter, triple layer and pad built. 685 mats on site, 479C, 206D. *** COVID 19 policies in effect*** | 6 | C186-C195 | Del Lake | 0 | 2021-09-18 |  | 37 | 2021-09-20 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge983821653Float Truck3597.42 | Northern Mat & Bridge983821653Float Truck3597.42ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9838 | 21653 | 53530601 | Rig/Access Mats | 0 | Float Truck | 199.14 | 32 | HR |  | 0 |  |  | 6372.48 | 828.4224 | 7200.9024 | 2021-09-18 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travelled in safety meeting, unload 2nd track carrier, move loader to thunder bay. Unload trucks, load shuttles, lay mats as per Valard instruction. Daniel travel infrom morrisburg to run 2nd track carrier 1472km paid for Personal vehicle us, No travel hours 2 loa.162 mats trucked and layed covering 150 meter, triple layer and pad built. 685 mats on site, 479C, 206D. *** COVID 19 policies in effect*** | 6 | C186-C195 | Del Lake | 0 | 2021-09-18 |  | 37 | 2021-09-20 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge983821653Float Truck326372.48 | Northern Mat & Bridge983821653Float Truck326372.48ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9838 | 21653 | 53530601 | Rig/Access Mats | 0 | Track Carrier | 172.56 | 2 | HR |  | 0 |  |  | 345.12 | 44.8656 | 389.9856 | 2021-09-18 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travelled in safety meeting, unload 2nd track carrier, move loader to thunder bay. Unload trucks, load shuttles, lay mats as per Valard instruction. Daniel travel infrom morrisburg to run 2nd track carrier 1472km paid for Personal vehicle us, No travel hours 2 loa.162 mats trucked and layed covering 150 meter, triple layer and pad built. 685 mats on site, 479C, 206D. *** COVID 19 policies in effect*** | 6 | C186-C195 | Del Lake | 0 | 2021-09-18 |  | 37 | 2021-09-20 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge983821653Track Carrier2345.12 | Northern Mat & Bridge983821653Track Carrier2345.12ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9838 | 21653 | 53530601 | Rig/Access Mats | 0 | Track Carrier | 172.56 | 7 | HR |  | 0 |  |  | 1207.92 | 157.0296 | 1364.9496 | 2021-09-18 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travelled in safety meeting, unload 2nd track carrier, move loader to thunder bay. Unload trucks, load shuttles, lay mats as per Valard instruction. Daniel travel infrom morrisburg to run 2nd track carrier 1472km paid for Personal vehicle us, No travel hours 2 loa.162 mats trucked and layed covering 150 meter, triple layer and pad built. 685 mats on site, 479C, 206D. *** COVID 19 policies in effect*** | 6 | C186-C195 | Del Lake | 0 | 2021-09-18 |  | 37 | 2021-09-20 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge983821653Track Carrier71207.92 | Northern Mat & Bridge983821653Track Carrier71207.92ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9838 | 21653 | 53530601 | Rig/Access Mats | 0 | Loader | 98.83 | 4 | HR |  | 0 |  |  | 395.32 | 51.3916 | 446.7116 | 2021-09-18 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travelled in safety meeting, unload 2nd track carrier, move loader to thunder bay. Unload trucks, load shuttles, lay mats as per Valard instruction. Daniel travel infrom morrisburg to run 2nd track carrier 1472km paid for Personal vehicle us, No travel hours 2 loa.162 mats trucked and layed covering 150 meter, triple layer and pad built. 685 mats on site, 479C, 206D. *** COVID 19 policies in effect*** | 6 | C186-C195 | Del Lake | 0 | 2021-09-18 |  | 37 | 2021-09-20 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge983821653Loader4395.32 | Northern Mat & Bridge983821653Loader4395.32ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9838 | 21653 | 53530601 | Rig/Access Mats | 0 | Loader | 98.83 | 10 | HR |  | 0 |  |  | 988.3 | 128.479 | 1116.779 | 2021-09-18 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travelled in safety meeting, unload 2nd track carrier, move loader to thunder bay. Unload trucks, load shuttles, lay mats as per Valard instruction. Daniel travel infrom morrisburg to run 2nd track carrier 1472km paid for Personal vehicle us, No travel hours 2 loa.162 mats trucked and layed covering 150 meter, triple layer and pad built. 685 mats on site, 479C, 206D. *** COVID 19 policies in effect*** | 6 | C186-C195 | Del Lake | 0 | 2021-09-18 |  | 37 | 2021-09-20 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge983821653Loader10988.3 | Northern Mat & Bridge983821653Loader10988.3ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9838 | 21653 | 53530601 | Rig/Access Mats | 0 | Loader | 98.83 | 7 | HR |  | 0 |  |  | 691.81 | 89.9353 | 781.7453 | 2021-09-18 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travelled in safety meeting, unload 2nd track carrier, move loader to thunder bay. Unload trucks, load shuttles, lay mats as per Valard instruction. Daniel travel infrom morrisburg to run 2nd track carrier 1472km paid for Personal vehicle us, No travel hours 2 loa.162 mats trucked and layed covering 150 meter, triple layer and pad built. 685 mats on site, 479C, 206D. *** COVID 19 policies in effect*** | 6 | C186-C195 | Del Lake | 0 | 2021-09-18 |  | 37 | 2021-09-20 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge983821653Loader7691.81 | Northern Mat & Bridge983821653Loader7691.81ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9838 | 21653 | 53530601 | Rig/Access Mats | 0 | Excavator | 127.81 | 7 | HR |  | 0 |  |  | 894.67 | 116.3071 | 1010.9771 | 2021-09-18 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travelled in safety meeting, unload 2nd track carrier, move loader to thunder bay. Unload trucks, load shuttles, lay mats as per Valard instruction. Daniel travel infrom morrisburg to run 2nd track carrier 1472km paid for Personal vehicle us, No travel hours 2 loa.162 mats trucked and layed covering 150 meter, triple layer and pad built. 685 mats on site, 479C, 206D. *** COVID 19 policies in effect*** | 6 | C186-C195 | Del Lake | 0 | 2021-09-18 |  | 37 | 2021-09-20 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge983821653Excavator7894.67 | Northern Mat & Bridge983821653Excavator7894.67ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9838 | 21653 | 53530601 | Rig/Access Mats | 0 | Crew Truck | 225 | 3 | DAY |  | 0 |  |  | 675 | 87.75 | 762.75 | 2021-09-18 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travelled in safety meeting, unload 2nd track carrier, move loader to thunder bay. Unload trucks, load shuttles, lay mats as per Valard instruction. Daniel travel infrom morrisburg to run 2nd track carrier 1472km paid for Personal vehicle us, No travel hours 2 loa.162 mats trucked and layed covering 150 meter, triple layer and pad built. 685 mats on site, 479C, 206D. *** COVID 19 policies in effect*** | 6 | C186-C195 | Del Lake | 0 | 2021-09-18 |  | 37 | 2021-09-20 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge983821653Crew Truck3675 | Northern Mat & Bridge983821653Crew Truck3675ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9836 | 21651 | 53530601 | Rig/Access Mats | 0 | Subsistence Per Day | 225 | 5 | DAY |  |  |  | 0 | 1125 | 146.25 | 1271.25 | 2021-09-17 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | Move loader to Nipigon to load mats. Crew travelled to site, Safety meeting. Unload mats, shuttle mats, lay mats as per Valard instruction.298 mats trucked and layed,500 meter of access. Total mats on site 523. 382C, 141D. Toal coverage 800meters. | 6 | C186-C195 | Del Lake | 0 | 2021-09-17 |  | 37 | 2021-09-18 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge983621651Subsistence Per Day51125 | Northern Mat & Bridge983621651Subsistence Per Day51125ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9836 | 21651 | 53530601 | Rig/Access Mats | 0 | Operator | 84.69 | 3 | HR |  |  | 127.04 | 0 | 254.07 | 33.0291 | 287.0991 | 2021-09-17 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | Move loader to Nipigon to load mats. Crew travelled to site, Safety meeting. Unload mats, shuttle mats, lay mats as per Valard instruction.298 mats trucked and layed,500 meter of access. Total mats on site 523. 382C, 141D. Toal coverage 800meters. | 6 | C186-C195 | Del Lake | 0 | 2021-09-17 |  | 37 | 2021-09-18 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge983621651Operator3254.07 | Northern Mat & Bridge983621651Operator3254.07ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9836 | 21651 | 53530601 | Rig/Access Mats | 0 | Operator | 84.69 | 8 | HR |  |  | 127.04 | 0 | 677.52 | 88.0776 | 765.5976 | 2021-09-17 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | Move loader to Nipigon to load mats. Crew travelled to site, Safety meeting. Unload mats, shuttle mats, lay mats as per Valard instruction.298 mats trucked and layed,500 meter of access. Total mats on site 523. 382C, 141D. Toal coverage 800meters. | 6 | C186-C195 | Del Lake | 0 | 2021-09-17 |  | 37 | 2021-09-18 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge983621651Operator8677.52 | Northern Mat & Bridge983621651Operator8677.52ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9836 | 21651 | 53530601 | Rig/Access Mats | 0 | Operator | 84.69 | 8 | HR |  |  | 127.04 | 4 | 1185.68 | 154.1384 | 1339.8184 | 2021-09-17 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | Move loader to Nipigon to load mats. Crew travelled to site, Safety meeting. Unload mats, shuttle mats, lay mats as per Valard instruction.298 mats trucked and layed,500 meter of access. Total mats on site 523. 382C, 141D. Toal coverage 800meters. | 6 | C186-C195 | Del Lake | 0 | 2021-09-17 |  | 37 | 2021-09-18 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge983621651Operator81185.68 | Northern Mat & Bridge983621651Operator81185.68ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9836 | 21651 | 53530601 | Rig/Access Mats | 0 | Operator | 84.69 | 8 | HR |  |  | 127.04 | 4 | 1185.68 | 154.1384 | 1339.8184 | 2021-09-17 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | Move loader to Nipigon to load mats. Crew travelled to site, Safety meeting. Unload mats, shuttle mats, lay mats as per Valard instruction.298 mats trucked and layed,500 meter of access. Total mats on site 523. 382C, 141D. Toal coverage 800meters. | 6 | C186-C195 | Del Lake | 0 | 2021-09-17 |  | 37 | 2021-09-18 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge983621651Operator81185.68 | Northern Mat & Bridge983621651Operator81185.68ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9836 | 21651 | 53530601 | Rig/Access Mats | 0 | Operator | 84.69 | 8 | HR |  |  | 127.04 | 4 | 1185.68 | 154.1384 | 1339.8184 | 2021-09-17 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | Move loader to Nipigon to load mats. Crew travelled to site, Safety meeting. Unload mats, shuttle mats, lay mats as per Valard instruction.298 mats trucked and layed,500 meter of access. Total mats on site 523. 382C, 141D. Toal coverage 800meters. | 6 | C186-C195 | Del Lake | 0 | 2021-09-17 |  | 37 | 2021-09-18 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge983621651Operator81185.68 | Northern Mat & Bridge983621651Operator81185.68ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9836 | 21651 | 53530601 | Rig/Access Mats | 0 | Supervisor | 101.49 | 8 | HR |  |  | 129 | 5 | 1456.92 | 189.3996 | 1646.3196 | 2021-09-17 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | Move loader to Nipigon to load mats. Crew travelled to site, Safety meeting. Unload mats, shuttle mats, lay mats as per Valard instruction.298 mats trucked and layed,500 meter of access. Total mats on site 523. 382C, 141D. Toal coverage 800meters. | 6 | C186-C195 | Del Lake | 0 | 2021-09-17 |  | 37 | 2021-09-18 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge983621651Supervisor81456.92 | Northern Mat & Bridge983621651Supervisor81456.92ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9836 | 21651 | 53530601 | Rig/Access Mats | 0 | Float Truck | 199.14 | 3 | HR |  | 0 |  |  | 597.42 | 77.6646 | 675.0846 | 2021-09-17 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | Move loader to Nipigon to load mats. Crew travelled to site, Safety meeting. Unload mats, shuttle mats, lay mats as per Valard instruction.298 mats trucked and layed,500 meter of access. Total mats on site 523. 382C, 141D. Toal coverage 800meters. | 6 | C186-C195 | Del Lake | 0 | 2021-09-17 |  | 37 | 2021-09-18 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge983621651Float Truck3597.42 | Northern Mat & Bridge983621651Float Truck3597.42ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9836 | 21651 | 53530601 | Rig/Access Mats | 0 | Track Carrier | 172.56 | 10 | HR |  | 0 |  |  | 1725.6 | 224.328 | 1949.928 | 2021-09-17 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | Move loader to Nipigon to load mats. Crew travelled to site, Safety meeting. Unload mats, shuttle mats, lay mats as per Valard instruction.298 mats trucked and layed,500 meter of access. Total mats on site 523. 382C, 141D. Toal coverage 800meters. | 6 | C186-C195 | Del Lake | 0 | 2021-09-17 |  | 37 | 2021-09-18 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge983621651Track Carrier101725.6 | Northern Mat & Bridge983621651Track Carrier101725.6ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9836 | 21651 | 53530601 | Rig/Access Mats | 0 | Loader | 98.83 | 3 | HR |  | 0 |  |  | 296.49 | 38.5437 | 335.0337 | 2021-09-17 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | Move loader to Nipigon to load mats. Crew travelled to site, Safety meeting. Unload mats, shuttle mats, lay mats as per Valard instruction.298 mats trucked and layed,500 meter of access. Total mats on site 523. 382C, 141D. Toal coverage 800meters. | 6 | C186-C195 | Del Lake | 0 | 2021-09-17 |  | 37 | 2021-09-18 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge983621651Loader3296.49 | Northern Mat & Bridge983621651Loader3296.49ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9836 | 21651 | 53530601 | Rig/Access Mats | 0 | Loader | 98.83 | 7 | HR |  | 0 |  |  | 691.81 | 89.9353 | 781.7453 | 2021-09-17 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | Move loader to Nipigon to load mats. Crew travelled to site, Safety meeting. Unload mats, shuttle mats, lay mats as per Valard instruction.298 mats trucked and layed,500 meter of access. Total mats on site 523. 382C, 141D. Toal coverage 800meters. | 6 | C186-C195 | Del Lake | 0 | 2021-09-17 |  | 37 | 2021-09-18 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge983621651Loader7691.81 | Northern Mat & Bridge983621651Loader7691.81ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9836 | 21651 | 53530601 | Rig/Access Mats | 0 | Loader | 98.83 | 10 | HR |  | 0 |  |  | 988.3 | 128.479 | 1116.779 | 2021-09-17 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | Move loader to Nipigon to load mats. Crew travelled to site, Safety meeting. Unload mats, shuttle mats, lay mats as per Valard instruction.298 mats trucked and layed,500 meter of access. Total mats on site 523. 382C, 141D. Toal coverage 800meters. | 6 | C186-C195 | Del Lake | 0 | 2021-09-17 |  | 37 | 2021-09-18 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge983621651Loader10988.3 | Northern Mat & Bridge983621651Loader10988.3ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9836 | 21651 | 53530601 | Rig/Access Mats | 0 | Excavator | 127.81 | 10 | HR |  | 0 |  |  | 1278.1 | 166.153 | 1444.253 | 2021-09-17 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | Move loader to Nipigon to load mats. Crew travelled to site, Safety meeting. Unload mats, shuttle mats, lay mats as per Valard instruction.298 mats trucked and layed,500 meter of access. Total mats on site 523. 382C, 141D. Toal coverage 800meters. | 6 | C186-C195 | Del Lake | 0 | 2021-09-17 |  | 37 | 2021-09-18 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge983621651Excavator101278.1 | Northern Mat & Bridge983621651Excavator101278.1ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9836 | 21651 | 53530601 | Rig/Access Mats | 0 | Crew Truck | 225 | 2 | DAY |  | 0 |  |  | 450 | 58.5 | 508.5 | 2021-09-17 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | Move loader to Nipigon to load mats. Crew travelled to site, Safety meeting. Unload mats, shuttle mats, lay mats as per Valard instruction.298 mats trucked and layed,500 meter of access. Total mats on site 523. 382C, 141D. Toal coverage 800meters. | 6 | C186-C195 | Del Lake | 0 | 2021-09-17 |  | 37 | 2021-09-18 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge983621651Crew Truck2450 | Northern Mat & Bridge983621651Crew Truck2450ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9835 | 21650 | 53530601 | Rig/Access Mats | 0 | Subsistence Per Day | 225 | 5 | DAY |  |  |  | 0 | 1125 | 146.25 | 1271.25 | 2021-09-16 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | Crew travel to site, safety meeting. Unload equipment and mats. Lay mats as per Valard instruction. Dylan T day 2 of travel with PV 325km . Andrew travel in PV 150 km. 225 mats trucked and laid covering 300 meter of access. Crew travelled out. ** COVID 19 policies in effect ** | 6 | C186-C195 | Del Lake | 0 | 2021-09-18 |  | 37 | 2021-09-18 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge983521650Subsistence Per Day51125 | Northern Mat & Bridge983521650Subsistence Per Day51125ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9835 | 21650 | 53530601 | Rig/Access Mats | 0 | Travel per KM | 0.82 | 475 | km |  |  |  | 0 | 389.5 | 50.635 | 440.135 | 2021-09-16 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | Crew travel to site, safety meeting. Unload equipment and mats. Lay mats as per Valard instruction. Dylan T day 2 of travel with PV 325km . Andrew travel in PV 150 km. 225 mats trucked and laid covering 300 meter of access. Crew travelled out. ** COVID 19 policies in effect ** | 6 | C186-C195 | Del Lake | 0 | 2021-09-18 |  | 37 | 2021-09-18 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge983521650Travel per KM475389.5 | Northern Mat & Bridge983521650Travel per KM475389.5ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9835 | 21650 | 53530601 | Rig/Access Mats | 0 | Operator | 84.69 | 8 | HR |  |  | 127.04 | 4.5 | 1249.2 | 162.396 | 1411.596 | 2021-09-16 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | Crew travel to site, safety meeting. Unload equipment and mats. Lay mats as per Valard instruction. Dylan T day 2 of travel with PV 325km . Andrew travel in PV 150 km. 225 mats trucked and laid covering 300 meter of access. Crew travelled out. ** COVID 19 policies in effect ** | 6 | C186-C195 | Del Lake | 0 | 2021-09-18 |  | 37 | 2021-09-18 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge983521650Operator81249.2 | Northern Mat & Bridge983521650Operator81249.2ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9835 | 21650 | 53530601 | Rig/Access Mats | 0 | Operator | 84.69 | 8 | HR |  |  | 127.04 | 1 | 804.56 | 104.5928 | 909.1528 | 2021-09-16 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | Crew travel to site, safety meeting. Unload equipment and mats. Lay mats as per Valard instruction. Dylan T day 2 of travel with PV 325km . Andrew travel in PV 150 km. 225 mats trucked and laid covering 300 meter of access. Crew travelled out. ** COVID 19 policies in effect ** | 6 | C186-C195 | Del Lake | 0 | 2021-09-18 |  | 37 | 2021-09-18 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge983521650Operator8804.56 | Northern Mat & Bridge983521650Operator8804.56ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9835 | 21650 | 53530601 | Rig/Access Mats | 0 | Operator | 84.69 | 8 | HR |  |  | 127.04 | 3 | 1058.64 | 137.6232 | 1196.2632 | 2021-09-16 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | Crew travel to site, safety meeting. Unload equipment and mats. Lay mats as per Valard instruction. Dylan T day 2 of travel with PV 325km . Andrew travel in PV 150 km. 225 mats trucked and laid covering 300 meter of access. Crew travelled out. ** COVID 19 policies in effect ** | 6 | C186-C195 | Del Lake | 0 | 2021-09-18 |  | 37 | 2021-09-18 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge983521650Operator81058.64 | Northern Mat & Bridge983521650Operator81058.64ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9835 | 21650 | 53530601 | Rig/Access Mats | 0 | Operator | 84.69 | 8 | HR |  |  | 127.04 | 3 | 1058.64 | 137.6232 | 1196.2632 | 2021-09-16 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | Crew travel to site, safety meeting. Unload equipment and mats. Lay mats as per Valard instruction. Dylan T day 2 of travel with PV 325km . Andrew travel in PV 150 km. 225 mats trucked and laid covering 300 meter of access. Crew travelled out. ** COVID 19 policies in effect ** | 6 | C186-C195 | Del Lake | 0 | 2021-09-18 |  | 37 | 2021-09-18 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge983521650Operator81058.64 | Northern Mat & Bridge983521650Operator81058.64ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9835 | 21650 | 53530601 | Rig/Access Mats | 0 | Supervisor | 101.49 | 8 | HR |  |  | 129 | 5.5 | 1521.42 | 197.7846 | 1719.2046 | 2021-09-16 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | Crew travel to site, safety meeting. Unload equipment and mats. Lay mats as per Valard instruction. Dylan T day 2 of travel with PV 325km . Andrew travel in PV 150 km. 225 mats trucked and laid covering 300 meter of access. Crew travelled out. ** COVID 19 policies in effect ** | 6 | C186-C195 | Del Lake | 0 | 2021-09-18 |  | 37 | 2021-09-18 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge983521650Supervisor81521.42 | Northern Mat & Bridge983521650Supervisor81521.42ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9835 | 21650 | 53530601 | Rig/Access Mats | 0 | Float Truck | 199.14 | 28.7235 | HR |  | 0 |  |  | 5719.9978 | 743.5997 | 6463.5975 | 2021-09-16 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | Crew travel to site, safety meeting. Unload equipment and mats. Lay mats as per Valard instruction. Dylan T day 2 of travel with PV 325km . Andrew travel in PV 150 km. 225 mats trucked and laid covering 300 meter of access. Crew travelled out. ** COVID 19 policies in effect ** | 6 | C186-C195 | Del Lake | 0 | 2021-09-18 |  | 37 | 2021-09-18 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge983521650Float Truck28.72355719.9978 | Northern Mat & Bridge983521650Float Truck28.72355719.9978ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9835 | 21650 | 53530601 | Rig/Access Mats | 0 | Float Truck | 199.14 | 28.7235 | HR |  | 0 |  |  | 5719.9978 | 743.5997 | 6463.5975 | 2021-09-16 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | Crew travel to site, safety meeting. Unload equipment and mats. Lay mats as per Valard instruction. Dylan T day 2 of travel with PV 325km . Andrew travel in PV 150 km. 225 mats trucked and laid covering 300 meter of access. Crew travelled out. ** COVID 19 policies in effect ** | 6 | C186-C195 | Del Lake | 0 | 2021-09-18 |  | 37 | 2021-09-18 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge983521650Float Truck28.72355719.9978 | Northern Mat & Bridge983521650Float Truck28.72355719.9978ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9835 | 21650 | 53530601 | Rig/Access Mats | 0 | Loader | 98.83 | 11 | HR |  | 0 |  |  | 1087.13 | 141.3269 | 1228.4569 | 2021-09-16 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | Crew travel to site, safety meeting. Unload equipment and mats. Lay mats as per Valard instruction. Dylan T day 2 of travel with PV 325km . Andrew travel in PV 150 km. 225 mats trucked and laid covering 300 meter of access. Crew travelled out. ** COVID 19 policies in effect ** | 6 | C186-C195 | Del Lake | 0 | 2021-09-18 |  | 37 | 2021-09-18 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge983521650Loader111087.13 | Northern Mat & Bridge983521650Loader111087.13ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9835 | 21650 | 53530601 | Rig/Access Mats | 0 | Loader | 98.83 | 7 | HR |  | 0 |  |  | 691.81 | 89.9353 | 781.7453 | 2021-09-16 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | Crew travel to site, safety meeting. Unload equipment and mats. Lay mats as per Valard instruction. Dylan T day 2 of travel with PV 325km . Andrew travel in PV 150 km. 225 mats trucked and laid covering 300 meter of access. Crew travelled out. ** COVID 19 policies in effect ** | 6 | C186-C195 | Del Lake | 0 | 2021-09-18 |  | 37 | 2021-09-18 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge983521650Loader7691.81 | Northern Mat & Bridge983521650Loader7691.81ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9835 | 21650 | 53530601 | Rig/Access Mats | 0 | Excavator | 127.81 | 7 | HR |  | 0 |  |  | 894.67 | 116.3071 | 1010.9771 | 2021-09-16 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | Crew travel to site, safety meeting. Unload equipment and mats. Lay mats as per Valard instruction. Dylan T day 2 of travel with PV 325km . Andrew travel in PV 150 km. 225 mats trucked and laid covering 300 meter of access. Crew travelled out. ** COVID 19 policies in effect ** | 6 | C186-C195 | Del Lake | 0 | 2021-09-18 |  | 37 | 2021-09-18 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge983521650Excavator7894.67 | Northern Mat & Bridge983521650Excavator7894.67ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9835 | 21650 | 53530601 | Rig/Access Mats | 0 | Crew Truck | 225 | 2 | DAY |  | 0 |  |  | 450 | 58.5 | 508.5 | 2021-09-16 | 0 | ESI10895 | 2021-10-07 | 167 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | Crew travel to site, safety meeting. Unload equipment and mats. Lay mats as per Valard instruction. Dylan T day 2 of travel with PV 325km . Andrew travel in PV 150 km. 225 mats trucked and laid covering 300 meter of access. Crew travelled out. ** COVID 19 policies in effect ** | 6 | C186-C195 | Del Lake | 0 | 2021-09-18 |  | 37 | 2021-09-18 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge983521650Crew Truck2450 | Northern Mat & Bridge983521650Crew Truck2450ESI10895 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9834 | 21649 | 53530601 | Rig/Access Mats | 0 | Subsistence Per Day | 225 | 7 | DAY |  |  |  | 0 | 1575 | 204.75 | 1779.75 | 2021-09-15 | 0 | ESI10897 | 2021-10-07 | 166 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | Jason day 2 Sault Ste Mariel to Marathon, meet with Valard, scout job. Jamie day 1 travel PV to Orangeville 300km, load up truck with fire suppression gear and trvel to noelville, day 2 travel to Marathon. Dylan day 1 travel Bancroft to Wawa PV 856km. Nick day 1 of travel Newmarket to Nipigon, day 2 travel to Thunder bay PV 1362km, load trucks | 6 | C186-C195 | Del Lake | 0 | 2021-09-18 |  | 37 | 2021-09-19 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge983421649Subsistence Per Day71575 | Northern Mat & Bridge983421649Subsistence Per Day71575ESI10897 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9834 | 21649 | 53530601 | Rig/Access Mats | 0 | Travel per KM | 0.82 | 2518 | km |  |  |  | 0 | 2064.76 | 268.4188 | 2333.1788 | 2021-09-15 | 0 | ESI10897 | 2021-10-07 | 166 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | Jason day 2 Sault Ste Mariel to Marathon, meet with Valard, scout job. Jamie day 1 travel PV to Orangeville 300km, load up truck with fire suppression gear and trvel to noelville, day 2 travel to Marathon. Dylan day 1 travel Bancroft to Wawa PV 856km. Nick day 1 of travel Newmarket to Nipigon, day 2 travel to Thunder bay PV 1362km, load trucks | 6 | C186-C195 | Del Lake | 0 | 2021-09-18 |  | 37 | 2021-09-19 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge983421649Travel per KM25182064.76 | Northern Mat & Bridge983421649Travel per KM25182064.76ESI10897 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9834 | 21649 | 53530601 | Rig/Access Mats | 0 | Operator - Travel | 84.69 | 8 | HR |  |  |  | 0 | 677.52 | 88.0776 | 765.5976 | 2021-09-15 | 0 | ESI10897 | 2021-10-07 | 166 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | Jason day 2 Sault Ste Mariel to Marathon, meet with Valard, scout job. Jamie day 1 travel PV to Orangeville 300km, load up truck with fire suppression gear and trvel to noelville, day 2 travel to Marathon. Dylan day 1 travel Bancroft to Wawa PV 856km. Nick day 1 of travel Newmarket to Nipigon, day 2 travel to Thunder bay PV 1362km, load trucks | 6 | C186-C195 | Del Lake | 0 | 2021-09-18 |  | 37 | 2021-09-19 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge983421649Operator - Travel8677.52 | Northern Mat & Bridge983421649Operator - Travel8677.52ESI10897 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9834 | 21649 | 53530601 | Rig/Access Mats | 0 | Operator - Travel | 84.69 | 16 | HR |  |  |  | 0 | 1355.04 | 176.1552 | 1531.1952 | 2021-09-15 | 0 | ESI10897 | 2021-10-07 | 166 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | Jason day 2 Sault Ste Mariel to Marathon, meet with Valard, scout job. Jamie day 1 travel PV to Orangeville 300km, load up truck with fire suppression gear and trvel to noelville, day 2 travel to Marathon. Dylan day 1 travel Bancroft to Wawa PV 856km. Nick day 1 of travel Newmarket to Nipigon, day 2 travel to Thunder bay PV 1362km, load trucks | 6 | C186-C195 | Del Lake | 0 | 2021-09-18 |  | 37 | 2021-09-19 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge983421649Operator - Travel161355.04 | Northern Mat & Bridge983421649Operator - Travel161355.04ESI10897 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9834 | 21649 | 53530601 | Rig/Access Mats | 0 | Supervisor | 101.49 | 10.5 | HR |  |  | 129 | 0 | 1065.645 | 138.5339 | 1204.1789 | 2021-09-15 | 0 | ESI10897 | 2021-10-07 | 166 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | Jason day 2 Sault Ste Mariel to Marathon, meet with Valard, scout job. Jamie day 1 travel PV to Orangeville 300km, load up truck with fire suppression gear and trvel to noelville, day 2 travel to Marathon. Dylan day 1 travel Bancroft to Wawa PV 856km. Nick day 1 of travel Newmarket to Nipigon, day 2 travel to Thunder bay PV 1362km, load trucks | 6 | C186-C195 | Del Lake | 0 | 2021-09-18 |  | 37 | 2021-09-19 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge983421649Supervisor10.51065.645 | Northern Mat & Bridge983421649Supervisor10.51065.645ESI10897 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9834 | 21649 | 53530601 | Rig/Access Mats | 0 | Loader | 98.83 | 4 | HR |  | 0 |  |  | 395.32 | 51.3916 | 446.7116 | 2021-09-15 | 0 | ESI10897 | 2021-10-07 | 166 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | Jason day 2 Sault Ste Mariel to Marathon, meet with Valard, scout job. Jamie day 1 travel PV to Orangeville 300km, load up truck with fire suppression gear and trvel to noelville, day 2 travel to Marathon. Dylan day 1 travel Bancroft to Wawa PV 856km. Nick day 1 of travel Newmarket to Nipigon, day 2 travel to Thunder bay PV 1362km, load trucks | 6 | C186-C195 | Del Lake | 0 | 2021-09-18 |  | 37 | 2021-09-19 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge983421649Loader4395.32 | Northern Mat & Bridge983421649Loader4395.32ESI10897 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9834 | 21649 | 53530601 | Rig/Access Mats | 0 | Crew Truck | 225 | 3 | DAY |  | 0 |  |  | 675 | 87.75 | 762.75 | 2021-09-15 | 0 | ESI10897 | 2021-10-07 | 166 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | Jason day 2 Sault Ste Mariel to Marathon, meet with Valard, scout job. Jamie day 1 travel PV to Orangeville 300km, load up truck with fire suppression gear and trvel to noelville, day 2 travel to Marathon. Dylan day 1 travel Bancroft to Wawa PV 856km. Nick day 1 of travel Newmarket to Nipigon, day 2 travel to Thunder bay PV 1362km, load trucks | 6 | C186-C195 | Del Lake | 0 | 2021-09-18 |  | 37 | 2021-09-19 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge983421649Crew Truck3675 | Northern Mat & Bridge983421649Crew Truck3675ESI10897 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9957 | 21661 | 53530601 | Rig/Access Mats | 0 | Subsistence Per Day | 225 | 2 | DAY |  |  |  | 0 | 450 | 58.5 | 508.5 | 2021-09-25 | 0 | ESI11123 | 2021-10-22 | 169 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | Jason day 2 travel to cornwall. Dylan day 2 travel to Bancroft. Load out excavator EE037 Marathon to Orangeville. | 6 | C262-C264 | Hare Lake Road | 0 | 2021-09-27 |  | 37 | 2021-09-27 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge995721661Subsistence Per Day2450 | Northern Mat & Bridge995721661Subsistence Per Day2450ESI11123 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9957 | 21661 | 53530601 | Rig/Access Mats | 0 | Travel per KM | 0.82 | 504 | km |  |  |  | 0 | 413.28 | 53.7264 | 467.0064 | 2021-09-25 | 0 | ESI11123 | 2021-10-22 | 169 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | Jason day 2 travel to cornwall. Dylan day 2 travel to Bancroft. Load out excavator EE037 Marathon to Orangeville. | 6 | C262-C264 | Hare Lake Road | 0 | 2021-09-27 |  | 37 | 2021-09-27 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge995721661Travel per KM504413.28 | Northern Mat & Bridge995721661Travel per KM504413.28ESI11123 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9957 | 21661 | 53530601 | Rig/Access Mats | 0 | Supervisor | 101.49 | 6 | HR |  |  | 129 | 0 | 608.94 | 79.1622 | 688.1022 | 2021-09-25 | 0 | ESI11123 | 2021-10-22 | 169 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | Jason day 2 travel to cornwall. Dylan day 2 travel to Bancroft. Load out excavator EE037 Marathon to Orangeville. | 6 | C262-C264 | Hare Lake Road | 0 | 2021-09-27 |  | 37 | 2021-09-27 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge995721661Supervisor6608.94 | Northern Mat & Bridge995721661Supervisor6608.94ESI11123 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9957 | 21661 | 53530601 | Rig/Access Mats | 0 | Float Truck | 199.14 | 28.7235 | HR |  | 0 |  |  | 5720 | 743.6 | 6463.6 | 2021-09-25 | 0 | ESI11123 | 2021-10-22 | 169 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | Jason day 2 travel to cornwall. Dylan day 2 travel to Bancroft. Load out excavator EE037 Marathon to Orangeville. | 6 | C262-C264 | Hare Lake Road | 0 | 2021-09-27 |  | 37 | 2021-09-27 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge995721661Float Truck28.7235115720 | Northern Mat & Bridge995721661Float Truck28.7235115720ESI11123 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9957 | 21661 | 53530601 | Rig/Access Mats | 0 | Crew Truck | 225 | 1 | DAY |  | 0 |  |  | 225 | 29.25 | 254.25 | 2021-09-25 | 0 | ESI11123 | 2021-10-22 | 169 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | Jason day 2 travel to cornwall. Dylan day 2 travel to Bancroft. Load out excavator EE037 Marathon to Orangeville. | 6 | C262-C264 | Hare Lake Road | 0 | 2021-09-27 |  | 37 | 2021-09-27 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge995721661Crew Truck1225 | Northern Mat & Bridge995721661Crew Truck1225ESI11123 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9956 | 21660 | 53530601 | Rig/Access Mats | 0 | Subsistence Per Day | 225 | 6 | DAY |  |  |  | 0 | 1350 | 175.5 | 1525.5 | 2021-09-24 | 0 | ESI11123 | 2021-10-22 | 169 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | Jason day 1 of travel to Cornwall, Jamie travel to Orangeville PV to Northbrook, Dylan day 1 of travel to Bancroft. Keegan day 1 travel to Bampton. Daniel day of traevl to Brampton, Nick travel to Orangeville. Load out track carriers to Orangeville. | 6 | C262-C264 | Hare Lake Road | 0 | 2021-09-27 |  | 37 | 2021-09-27 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge995621660Subsistence Per Day61350 | Northern Mat & Bridge995621660Subsistence Per Day61350ESI11123 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9956 | 21660 | 53530601 | Rig/Access Mats | 0 | Travel per KM | 0.82 | 4464 | km |  |  |  | 0 | 3660.48 | 475.8624 | 4136.3424 | 2021-09-24 | 0 | ESI11123 | 2021-10-22 | 169 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | Jason day 1 of travel to Cornwall, Jamie travel to Orangeville PV to Northbrook, Dylan day 1 of travel to Bancroft. Keegan day 1 travel to Bampton. Daniel day of traevl to Brampton, Nick travel to Orangeville. Load out track carriers to Orangeville. | 6 | C262-C264 | Hare Lake Road | 0 | 2021-09-27 |  | 37 | 2021-09-27 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge995621660Travel per KM44643660.48 | Northern Mat & Bridge995621660Travel per KM44643660.48ESI11123 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9956 | 21660 | 53530601 | Rig/Access Mats | 0 | Operator - Travel | 84.69 | 11.5 | HR |  |  |  | 0 | 973.935 | 126.6115 | 1100.5466 | 2021-09-24 | 0 | ESI11123 | 2021-10-22 | 169 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | Jason day 1 of travel to Cornwall, Jamie travel to Orangeville PV to Northbrook, Dylan day 1 of travel to Bancroft. Keegan day 1 travel to Bampton. Daniel day of traevl to Brampton, Nick travel to Orangeville. Load out track carriers to Orangeville. | 6 | C262-C264 | Hare Lake Road | 0 | 2021-09-27 |  | 37 | 2021-09-27 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge995621660Operator - Travel11.5973.935 | Northern Mat & Bridge995621660Operator - Travel11.5973.935ESI11123 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9956 | 21660 | 53530601 | Rig/Access Mats | 0 | Supervisor | 101.49 | 12 | HR |  |  | 129 | 0 | 1217.88 | 158.3244 | 1376.2044 | 2021-09-24 | 0 | ESI11123 | 2021-10-22 | 169 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | Jason day 1 of travel to Cornwall, Jamie travel to Orangeville PV to Northbrook, Dylan day 1 of travel to Bancroft. Keegan day 1 travel to Bampton. Daniel day of traevl to Brampton, Nick travel to Orangeville. Load out track carriers to Orangeville. | 6 | C262-C264 | Hare Lake Road | 0 | 2021-09-27 |  | 37 | 2021-09-27 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge995621660Supervisor121217.88 | Northern Mat & Bridge995621660Supervisor121217.88ESI11123 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9956 | 21660 | 53530601 | Rig/Access Mats | 0 | Float Truck | 199.14 | 24.8569 | HR |  | 0 |  |  | 4949.9991 | 643.4999 | 5593.499 | 2021-09-24 | 0 | ESI11123 | 2021-10-22 | 169 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | Jason day 1 of travel to Cornwall, Jamie travel to Orangeville PV to Northbrook, Dylan day 1 of travel to Bancroft. Keegan day 1 travel to Bampton. Daniel day of traevl to Brampton, Nick travel to Orangeville. Load out track carriers to Orangeville. | 6 | C262-C264 | Hare Lake Road | 0 | 2021-09-27 |  | 37 | 2021-09-27 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge995621660Float Truck24.856884949.9991 | Northern Mat & Bridge995621660Float Truck24.856884949.9991ESI11123 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9956 | 21660 | 53530601 | Rig/Access Mats | 0 | Float Truck | 199.14 | 24.8569 | HR |  | 0 |  |  | 4949.9991 | 643.4999 | 5593.499 | 2021-09-24 | 0 | ESI11123 | 2021-10-22 | 169 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | Jason day 1 of travel to Cornwall, Jamie travel to Orangeville PV to Northbrook, Dylan day 1 of travel to Bancroft. Keegan day 1 travel to Bampton. Daniel day of traevl to Brampton, Nick travel to Orangeville. Load out track carriers to Orangeville. | 6 | C262-C264 | Hare Lake Road | 0 | 2021-09-27 |  | 37 | 2021-09-27 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge995621660Float Truck24.856884949.9991 | Northern Mat & Bridge995621660Float Truck24.856884949.9991ESI11123 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9956 | 21660 | 53530601 | Rig/Access Mats | 0 | Crew Truck | 225 | 2 | DAY |  | 0 |  |  | 450 | 58.5 | 508.5 | 2021-09-24 | 0 | ESI11123 | 2021-10-22 | 169 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | Jason day 1 of travel to Cornwall, Jamie travel to Orangeville PV to Northbrook, Dylan day 1 of travel to Bancroft. Keegan day 1 travel to Bampton. Daniel day of traevl to Brampton, Nick travel to Orangeville. Load out track carriers to Orangeville. | 6 | C262-C264 | Hare Lake Road | 0 | 2021-09-27 |  | 37 | 2021-09-27 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge995621660Crew Truck2450 | Northern Mat & Bridge995621660Crew Truck2450ESI11123 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9955 | 21659 | 53530601 | Rig/Access Mats | 0 | Subsistence Per Day | 225 | 6 | DAY |  |  |  | 0 | 1350 | 175.5 | 1525.5 | 2021-09-23 | 0 | ESI11123 | 2021-10-22 | 169 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travel in, safety meeting, haul mats, unload trucks, shuttle mats lay mats as per Valard instruction. Extremly busy location with 10 gravel trucks hauling, lots of wait time for shuttles and lowbeds. Trucked in 25 mats, total on ground 272C,45D, 60m double layer 40m single layer. 33C mats racked on site, 15C mats racked valard Marathon Yard. total mats in for Hare lake is 315C 45 D 360 total. *** COVID 19 policies in effect*** float gear off site to Marathon Yard. lowbeds take loaders to Thunder bay. | 6 | C262-C266 | Hare Lake Road | 0 | 2021-09-25 |  | 37 | 2021-09-25 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge995521659Subsistence Per Day61350 | Northern Mat & Bridge995521659Subsistence Per Day61350ESI11123 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9955 | 21659 | 53530601 | Rig/Access Mats | 0 | Operator | 84.69 | 8 | HR |  |  | 127.04 | 0 | 677.52 | 88.0776 | 765.5976 | 2021-09-23 | 0 | ESI11123 | 2021-10-22 | 169 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travel in, safety meeting, haul mats, unload trucks, shuttle mats lay mats as per Valard instruction. Extremly busy location with 10 gravel trucks hauling, lots of wait time for shuttles and lowbeds. Trucked in 25 mats, total on ground 272C,45D, 60m double layer 40m single layer. 33C mats racked on site, 15C mats racked valard Marathon Yard. total mats in for Hare lake is 315C 45 D 360 total. *** COVID 19 policies in effect*** float gear off site to Marathon Yard. lowbeds take loaders to Thunder bay. | 6 | C262-C266 | Hare Lake Road | 0 | 2021-09-25 |  | 37 | 2021-09-25 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge995521659Operator8677.52 | Northern Mat & Bridge995521659Operator8677.52ESI11123 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9955 | 21659 | 53530601 | Rig/Access Mats | 0 | Operator | 84.69 | 8 | HR |  |  | 127.04 | 0 | 677.52 | 88.0776 | 765.5976 | 2021-09-23 | 0 | ESI11123 | 2021-10-22 | 169 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travel in, safety meeting, haul mats, unload trucks, shuttle mats lay mats as per Valard instruction. Extremly busy location with 10 gravel trucks hauling, lots of wait time for shuttles and lowbeds. Trucked in 25 mats, total on ground 272C,45D, 60m double layer 40m single layer. 33C mats racked on site, 15C mats racked valard Marathon Yard. total mats in for Hare lake is 315C 45 D 360 total. *** COVID 19 policies in effect*** float gear off site to Marathon Yard. lowbeds take loaders to Thunder bay. | 6 | C262-C266 | Hare Lake Road | 0 | 2021-09-25 |  | 37 | 2021-09-25 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge995521659Operator8677.52 | Northern Mat & Bridge995521659Operator8677.52ESI11123 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9955 | 21659 | 53530601 | Rig/Access Mats | 0 | Operator | 84.69 | 8 | HR |  |  | 127.04 | 0 | 677.52 | 88.0776 | 765.5976 | 2021-09-23 | 0 | ESI11123 | 2021-10-22 | 169 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travel in, safety meeting, haul mats, unload trucks, shuttle mats lay mats as per Valard instruction. Extremly busy location with 10 gravel trucks hauling, lots of wait time for shuttles and lowbeds. Trucked in 25 mats, total on ground 272C,45D, 60m double layer 40m single layer. 33C mats racked on site, 15C mats racked valard Marathon Yard. total mats in for Hare lake is 315C 45 D 360 total. *** COVID 19 policies in effect*** float gear off site to Marathon Yard. lowbeds take loaders to Thunder bay. | 6 | C262-C266 | Hare Lake Road | 0 | 2021-09-25 |  | 37 | 2021-09-25 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge995521659Operator8677.52 | Northern Mat & Bridge995521659Operator8677.52ESI11123 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9955 | 21659 | 53530601 | Rig/Access Mats | 0 | Operator | 84.69 | 8 | HR |  |  | 127.04 | 2 | 931.6 | 121.108 | 1052.708 | 2021-09-23 | 0 | ESI11123 | 2021-10-22 | 169 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travel in, safety meeting, haul mats, unload trucks, shuttle mats lay mats as per Valard instruction. Extremly busy location with 10 gravel trucks hauling, lots of wait time for shuttles and lowbeds. Trucked in 25 mats, total on ground 272C,45D, 60m double layer 40m single layer. 33C mats racked on site, 15C mats racked valard Marathon Yard. total mats in for Hare lake is 315C 45 D 360 total. *** COVID 19 policies in effect*** float gear off site to Marathon Yard. lowbeds take loaders to Thunder bay. | 6 | C262-C266 | Hare Lake Road | 0 | 2021-09-25 |  | 37 | 2021-09-25 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge995521659Operator8931.6 | Northern Mat & Bridge995521659Operator8931.6ESI11123 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9955 | 21659 | 53530601 | Rig/Access Mats | 0 | Operator | 84.69 | 8 | HR |  |  | 127.04 | 2 | 931.6 | 121.108 | 1052.708 | 2021-09-23 | 0 | ESI11123 | 2021-10-22 | 169 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travel in, safety meeting, haul mats, unload trucks, shuttle mats lay mats as per Valard instruction. Extremly busy location with 10 gravel trucks hauling, lots of wait time for shuttles and lowbeds. Trucked in 25 mats, total on ground 272C,45D, 60m double layer 40m single layer. 33C mats racked on site, 15C mats racked valard Marathon Yard. total mats in for Hare lake is 315C 45 D 360 total. *** COVID 19 policies in effect*** float gear off site to Marathon Yard. lowbeds take loaders to Thunder bay. | 6 | C262-C266 | Hare Lake Road | 0 | 2021-09-25 |  | 37 | 2021-09-25 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge995521659Operator8931.6 | Northern Mat & Bridge995521659Operator8931.6ESI11123 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9955 | 21659 | 53530601 | Rig/Access Mats | 0 | Supervisor | 101.49 | 8 | HR |  |  | 129 | 3 | 1198.92 | 155.8596 | 1354.7796 | 2021-09-23 | 0 | ESI11123 | 2021-10-22 | 169 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travel in, safety meeting, haul mats, unload trucks, shuttle mats lay mats as per Valard instruction. Extremly busy location with 10 gravel trucks hauling, lots of wait time for shuttles and lowbeds. Trucked in 25 mats, total on ground 272C,45D, 60m double layer 40m single layer. 33C mats racked on site, 15C mats racked valard Marathon Yard. total mats in for Hare lake is 315C 45 D 360 total. *** COVID 19 policies in effect*** float gear off site to Marathon Yard. lowbeds take loaders to Thunder bay. | 6 | C262-C266 | Hare Lake Road | 0 | 2021-09-25 |  | 37 | 2021-09-25 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge995521659Supervisor81198.92 | Northern Mat & Bridge995521659Supervisor81198.92ESI11123 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9955 | 21659 | 53530601 | Rig/Access Mats | 0 | Flatbed Truck | 187.5 | 10 | HR |  | 0 |  |  | 1875 | 243.75 | 2118.75 | 2021-09-23 | 0 | ESI11123 | 2021-10-22 | 169 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travel in, safety meeting, haul mats, unload trucks, shuttle mats lay mats as per Valard instruction. Extremly busy location with 10 gravel trucks hauling, lots of wait time for shuttles and lowbeds. Trucked in 25 mats, total on ground 272C,45D, 60m double layer 40m single layer. 33C mats racked on site, 15C mats racked valard Marathon Yard. total mats in for Hare lake is 315C 45 D 360 total. *** COVID 19 policies in effect*** float gear off site to Marathon Yard. lowbeds take loaders to Thunder bay. | 6 | C262-C266 | Hare Lake Road | 0 | 2021-09-25 |  | 37 | 2021-09-25 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge995521659Flatbed Truck101875 | Northern Mat & Bridge995521659Flatbed Truck101875ESI11123 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9955 | 21659 | 53530601 | Rig/Access Mats | 0 | Float Truck | 199.14 | 21 | HR |  | 0 |  |  | 4181.94 | 543.6522 | 4725.5922 | 2021-09-23 | 0 | ESI11123 | 2021-10-22 | 169 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travel in, safety meeting, haul mats, unload trucks, shuttle mats lay mats as per Valard instruction. Extremly busy location with 10 gravel trucks hauling, lots of wait time for shuttles and lowbeds. Trucked in 25 mats, total on ground 272C,45D, 60m double layer 40m single layer. 33C mats racked on site, 15C mats racked valard Marathon Yard. total mats in for Hare lake is 315C 45 D 360 total. *** COVID 19 policies in effect*** float gear off site to Marathon Yard. lowbeds take loaders to Thunder bay. | 6 | C262-C266 | Hare Lake Road | 0 | 2021-09-25 |  | 37 | 2021-09-25 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge995521659Float Truck214181.94 | Northern Mat & Bridge995521659Float Truck214181.94ESI11123 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9955 | 21659 | 53530601 | Rig/Access Mats | 0 | Track Carrier | 172.56 | 13 | HR |  | 0 |  |  | 2243.28 | 291.6264 | 2534.9064 | 2021-09-23 | 0 | ESI11123 | 2021-10-22 | 169 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travel in, safety meeting, haul mats, unload trucks, shuttle mats lay mats as per Valard instruction. Extremly busy location with 10 gravel trucks hauling, lots of wait time for shuttles and lowbeds. Trucked in 25 mats, total on ground 272C,45D, 60m double layer 40m single layer. 33C mats racked on site, 15C mats racked valard Marathon Yard. total mats in for Hare lake is 315C 45 D 360 total. *** COVID 19 policies in effect*** float gear off site to Marathon Yard. lowbeds take loaders to Thunder bay. | 6 | C262-C266 | Hare Lake Road | 0 | 2021-09-25 |  | 37 | 2021-09-25 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge995521659Track Carrier132243.28 | Northern Mat & Bridge995521659Track Carrier132243.28ESI11123 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9955 | 21659 | 53530601 | Rig/Access Mats | 0 | Loader | 98.83 | 13 | HR |  | 0 |  |  | 1284.79 | 167.0227 | 1451.8127 | 2021-09-23 | 0 | ESI11123 | 2021-10-22 | 169 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travel in, safety meeting, haul mats, unload trucks, shuttle mats lay mats as per Valard instruction. Extremly busy location with 10 gravel trucks hauling, lots of wait time for shuttles and lowbeds. Trucked in 25 mats, total on ground 272C,45D, 60m double layer 40m single layer. 33C mats racked on site, 15C mats racked valard Marathon Yard. total mats in for Hare lake is 315C 45 D 360 total. *** COVID 19 policies in effect*** float gear off site to Marathon Yard. lowbeds take loaders to Thunder bay. | 6 | C262-C266 | Hare Lake Road | 0 | 2021-09-25 |  | 37 | 2021-09-25 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge995521659Loader131284.79 | Northern Mat & Bridge995521659Loader131284.79ESI11123 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9955 | 21659 | 53530601 | Rig/Access Mats | 0 | Excavator | 127.81 | 7 | HR |  | 0 |  |  | 894.67 | 116.3071 | 1010.9771 | 2021-09-23 | 0 | ESI11123 | 2021-10-22 | 169 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travel in, safety meeting, haul mats, unload trucks, shuttle mats lay mats as per Valard instruction. Extremly busy location with 10 gravel trucks hauling, lots of wait time for shuttles and lowbeds. Trucked in 25 mats, total on ground 272C,45D, 60m double layer 40m single layer. 33C mats racked on site, 15C mats racked valard Marathon Yard. total mats in for Hare lake is 315C 45 D 360 total. *** COVID 19 policies in effect*** float gear off site to Marathon Yard. lowbeds take loaders to Thunder bay. | 6 | C262-C266 | Hare Lake Road | 0 | 2021-09-25 |  | 37 | 2021-09-25 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge995521659Excavator7894.67 | Northern Mat & Bridge995521659Excavator7894.67ESI11123 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Northern Mat & Bridge | 15 | 0 | 9955 | 21659 | 53530601 | Rig/Access Mats | 0 | Crew Truck | 225 | 2 | DAY |  | 0 |  |  | 450 | 58.5 | 508.5 | 2021-09-23 | 0 | ESI11123 | 2021-10-22 | 169 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2020-037 | TBA |  |  |  | Approved |  |  | crew travel in, safety meeting, haul mats, unload trucks, shuttle mats lay mats as per Valard instruction. Extremly busy location with 10 gravel trucks hauling, lots of wait time for shuttles and lowbeds. Trucked in 25 mats, total on ground 272C,45D, 60m double layer 40m single layer. 33C mats racked on site, 15C mats racked valard Marathon Yard. total mats in for Hare lake is 315C 45 D 360 total. *** COVID 19 policies in effect*** float gear off site to Marathon Yard. lowbeds take loaders to Thunder bay. | 6 | C262-C266 | Hare Lake Road | 0 | 2021-09-25 |  | 37 | 2021-09-25 | [5 empty] | Harold Furlong | 06 | Northern Mat & Bridge995521659Crew Truck2450 | Northern Mat & Bridge995521659Crew Truck2450ESI11123 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Corbiere and Sons Contracting | 6 | 0 | 9756 | 20210828-3 | 53511012 | Access | 0 | Labourer - General - After Jan 10 | 60 | 11 | HR |  |  | 60 | 0 | 660 | 85.8 | 745.8 | 2021-08-28 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26, KM34-KM36 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-31 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975620210828-3Labourer - General - After Jan 1011660 | Corbiere and Sons Contracting975620210828-3Labourer - General - After Jan 1011660INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9756 | 20210828-3 | 53511012 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 132 | HR |  |  | 75 | 0 | 9900 | 1287 | 11187 | 2021-08-28 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26, KM34-KM36 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-31 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975620210828-3Operator - Principle - After Jan 101329900 | Corbiere and Sons Contracting975620210828-3Operator - Principle - After Jan 101329900INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9756 | 20210828-3 | 53511012 | Access | 0 | L.O.A. | 210 | 14 | DAY |  |  |  | 0 | 2940 | 382.2 | 3322.2 | 2021-08-28 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26, KM34-KM36 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-31 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975620210828-3L.O.A.142940 | Corbiere and Sons Contracting975620210828-3L.O.A.142940INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9756 | 20210828-3 | 53511012 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-08-28 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26, KM34-KM36 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-31 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975620210828-3Foreman121140 | Corbiere and Sons Contracting975620210828-3Foreman121140INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9756 | 20210828-3 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 9 | Dynamic | 103.54 | 0 |  |  | 1242.45 | 161.5185 | 1403.9685 | 2021-08-28 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26, KM34-KM36 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-31 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975620210828-3Rock Truck - 30 Ton- After Jan 1091242.45 | Corbiere and Sons Contracting975620210828-3Rock Truck - 30 Ton- After Jan 1091242.45INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9756 | 20210828-3 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 9 | Dynamic | 103.54 | 0 |  |  | 1242.45 | 161.5185 | 1403.9685 | 2021-08-28 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26, KM34-KM36 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-31 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975620210828-3Rock Truck - 30 Ton- After Jan 1091242.45 | Corbiere and Sons Contracting975620210828-3Rock Truck - 30 Ton- After Jan 1091242.45INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9756 | 20210828-3 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 7 | Dynamic | 103.54 | 0 |  |  | 966.35 | 125.6255 | 1091.9755 | 2021-08-28 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26, KM34-KM36 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-31 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975620210828-3Rock Truck - 30 Ton- After Jan 107966.35 | Corbiere and Sons Contracting975620210828-3Rock Truck - 30 Ton- After Jan 107966.35INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9756 | 20210828-3 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 9 | Dynamic | 103.54 | 0 |  |  | 1242.45 | 161.5185 | 1403.9685 | 2021-08-28 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26, KM34-KM36 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-31 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975620210828-3Rock Truck - 30 Ton- After Jan 1091242.45 | Corbiere and Sons Contracting975620210828-3Rock Truck - 30 Ton- After Jan 1091242.45INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9756 | 20210828-3 | 53511012 | Access | 0 | Marooka- After Jan 10 | 144.6 | 5 | Dynamic | 108.45 | 0 |  |  | 723 | 93.99 | 816.99 | 2021-08-28 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26, KM34-KM36 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-31 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975620210828-3Marooka- After Jan 105723 | Corbiere and Sons Contracting975620210828-3Marooka- After Jan 105723INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9756 | 20210828-3 | 53511012 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 7 | DAY | 182.81 | 0 |  |  | 1706.25 | 221.8125 | 1928.0625 | 2021-08-28 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26, KM34-KM36 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-31 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975620210828-3Light Truck - Pick up- After Jan 1071706.25 | Corbiere and Sons Contracting975620210828-3Light Truck - Pick up- After Jan 1071706.25INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9756 | 20210828-3 | 53511012 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-08-28 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26, KM34-KM36 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-31 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975620210828-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting975620210828-3Light Truck - Pick up- After Jan 101243.75INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9756 | 20210828-3 | 53511012 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 9 | HR | 47.54 | 0 |  |  | 570.42 | 74.1546 | 644.5746 | 2021-08-28 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26, KM34-KM36 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-31 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975620210828-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42 | Corbiere and Sons Contracting975620210828-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9756 | 20210828-3 | 53511012 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 9 | HR | 47.54 | 0 |  |  | 570.42 | 74.1546 | 644.5746 | 2021-08-28 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26, KM34-KM36 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-31 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975620210828-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42 | Corbiere and Sons Contracting975620210828-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9756 | 20210828-3 | 53511012 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 9 | HR | 47.54 | 0 |  |  | 570.42 | 74.1546 | 644.5746 | 2021-08-28 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26, KM34-KM36 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-31 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975620210828-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42 | Corbiere and Sons Contracting975620210828-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9756 | 20210828-3 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 6 | HR | 9.16 | 0 |  |  | 73.26 | 9.5238 | 82.7838 | 2021-08-28 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26, KM34-KM36 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-31 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975620210828-3Excavator Thumb - 30 - 50 ton- After Jan 10673.26 | Corbiere and Sons Contracting975620210828-3Excavator Thumb - 30 - 50 ton- After Jan 10673.26INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9756 | 20210828-3 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-08-28 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26, KM34-KM36 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-31 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975620210828-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting975620210828-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9756 | 20210828-3 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-08-28 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26, KM34-KM36 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-31 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975620210828-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting975620210828-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9756 | 20210828-3 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 6 | Dynamic | 110.22 | 0 |  |  | 881.76 | 114.6288 | 996.3888 | 2021-08-28 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26, KM34-KM36 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-31 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975620210828-3Excavator - 36 ton- After Jan 106881.76 | Corbiere and Sons Contracting975620210828-3Excavator - 36 ton- After Jan 106881.76INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9756 | 20210828-3 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-08-28 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26, KM34-KM36 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-31 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975620210828-3Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting975620210828-3Excavator - 36 ton- After Jan 1091322.64INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9756 | 20210828-3 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-08-28 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26, KM34-KM36 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-31 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975620210828-3Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting975620210828-3Excavator - 36 ton- After Jan 1091322.64INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9756 | 20210828-3 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-08-28 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26, KM34-KM36 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-31 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975620210828-3Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting975620210828-3Excavator - 36 ton- After Jan 1091322.64INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9756 | 20210828-3 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 103.84 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2021-08-28 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26, KM34-KM36 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-31 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975620210828-3Excavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting975620210828-3Excavator - 30 ton- After Jan 1091246.05INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9756 | 20210828-3 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 103.84 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2021-08-28 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26, KM34-KM36 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-31 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975620210828-3Excavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting975620210828-3Excavator - 30 ton- After Jan 1091246.05INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9756 | 20210828-3 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 103.84 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2021-08-28 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26, KM34-KM36 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-31 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975620210828-3Excavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting975620210828-3Excavator - 30 ton- After Jan 1091246.05INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9755 | 20210827-3-R1 | 53511012 | Access | 0 | Labourer - General - After Jan 10 | 60 | 11 | HR |  |  | 60 | 0 | 660 | 85.8 | 745.8 | 2021-08-27 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-09-05 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975520210827-3-R1Labourer - General - After Jan 1011660 | Corbiere and Sons Contracting975520210827-3-R1Labourer - General - After Jan 1011660INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9755 | 20210827-3-R1 | 53511012 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 12 | HR |  |  | 70 | 0 | 840 | 109.2 | 949.2 | 2021-08-27 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-09-05 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975520210827-3-R1Driver - AZ - After Jan 1012840 | Corbiere and Sons Contracting975520210827-3-R1Driver - AZ - After Jan 1012840INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9755 | 20210827-3-R1 | 53511012 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 143 | HR |  |  | 75 | 0 | 10725 | 1394.25 | 12119.25 | 2021-08-27 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-09-05 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975520210827-3-R1Operator - Principle - After Jan 1014310725 | Corbiere and Sons Contracting975520210827-3-R1Operator - Principle - After Jan 1014310725INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9755 | 20210827-3-R1 | 53511012 | Access | 0 | L.O.A. | 210 | 17 | DAY |  |  |  | 0 | 3570 | 464.1 | 4034.1 | 2021-08-27 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-09-05 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975520210827-3-R1L.O.A.173570 | Corbiere and Sons Contracting975520210827-3-R1L.O.A.173570INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9755 | 20210827-3-R1 | 53511012 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-08-27 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-09-05 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975520210827-3-R1Foreman121140 | Corbiere and Sons Contracting975520210827-3-R1Foreman121140INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9755 | 20210827-3-R1 | 53511012 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-08-27 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-09-05 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975520210827-3-R1Foreman121140 | Corbiere and Sons Contracting975520210827-3-R1Foreman121140INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9755 | 20210827-3-R1 | 53511012 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 12 | Dynamic | 91.79 | 0 |  |  | 1468.68 | 190.9284 | 1659.6084 | 2021-08-27 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-09-05 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975520210827-3-R1Tractor Trailer - 60 Ton- After Jan 10121468.68 | Corbiere and Sons Contracting975520210827-3-R1Tractor Trailer - 60 Ton- After Jan 10121468.68INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9755 | 20210827-3-R1 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 9 | Dynamic | 103.54 | 0 |  |  | 1242.45 | 161.5185 | 1403.9685 | 2021-08-27 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-09-05 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975520210827-3-R1Rock Truck - 30 Ton- After Jan 1091242.45 | Corbiere and Sons Contracting975520210827-3-R1Rock Truck - 30 Ton- After Jan 1091242.45INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9755 | 20210827-3-R1 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 9 | Dynamic | 103.54 | 0 |  |  | 1242.45 | 161.5185 | 1403.9685 | 2021-08-27 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-09-05 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975520210827-3-R1Rock Truck - 30 Ton- After Jan 1091242.45 | Corbiere and Sons Contracting975520210827-3-R1Rock Truck - 30 Ton- After Jan 1091242.45INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9755 | 20210827-3-R1 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 9 | Dynamic | 103.54 | 0 |  |  | 1242.45 | 161.5185 | 1403.9685 | 2021-08-27 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-09-05 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975520210827-3-R1Rock Truck - 30 Ton- After Jan 1091242.45 | Corbiere and Sons Contracting975520210827-3-R1Rock Truck - 30 Ton- After Jan 1091242.45INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9755 | 20210827-3-R1 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 9 | Dynamic | 103.54 | 0 |  |  | 1242.45 | 161.5185 | 1403.9685 | 2021-08-27 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-09-05 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975520210827-3-R1Rock Truck - 30 Ton- After Jan 1091242.45 | Corbiere and Sons Contracting975520210827-3-R1Rock Truck - 30 Ton- After Jan 1091242.45INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9755 | 20210827-3-R1 | 53511012 | Access | 0 | Marooka- After Jan 10 | 144.6 | 5 | Dynamic | 108.45 | 0 |  |  | 723 | 93.99 | 816.99 | 2021-08-27 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-09-05 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975520210827-3-R1Marooka- After Jan 105723 | Corbiere and Sons Contracting975520210827-3-R1Marooka- After Jan 105723INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9755 | 20210827-3-R1 | 53511012 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 7 | DAY | 182.81 | 0 |  |  | 1706.25 | 221.8125 | 1928.0625 | 2021-08-27 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-09-05 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975520210827-3-R1Light Truck - Pick up- After Jan 1071706.25 | Corbiere and Sons Contracting975520210827-3-R1Light Truck - Pick up- After Jan 1071706.25INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9755 | 20210827-3-R1 | 53511012 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-08-27 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-09-05 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975520210827-3-R1Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting975520210827-3-R1Light Truck - Pick up- After Jan 101243.75INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9755 | 20210827-3-R1 | 53511012 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 9 | HR | 47.54 | 0 |  |  | 570.42 | 74.1546 | 644.5746 | 2021-08-27 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-09-05 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975520210827-3-R1Excavator Hammer - 30 - 50 ton- After Jan 109570.42 | Corbiere and Sons Contracting975520210827-3-R1Excavator Hammer - 30 - 50 ton- After Jan 109570.42INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9755 | 20210827-3-R1 | 53511012 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 9 | HR | 47.54 | 0 |  |  | 570.42 | 74.1546 | 644.5746 | 2021-08-27 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-09-05 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975520210827-3-R1Excavator Hammer - 30 - 50 ton- After Jan 109570.42 | Corbiere and Sons Contracting975520210827-3-R1Excavator Hammer - 30 - 50 ton- After Jan 109570.42INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9755 | 20210827-3-R1 | 53511012 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 9 | HR | 47.54 | 0 |  |  | 570.42 | 74.1546 | 644.5746 | 2021-08-27 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-09-05 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975520210827-3-R1Excavator Hammer - 30 - 50 ton- After Jan 109570.42 | Corbiere and Sons Contracting975520210827-3-R1Excavator Hammer - 30 - 50 ton- After Jan 109570.42INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9755 | 20210827-3-R1 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-08-27 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-09-05 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975520210827-3-R1Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting975520210827-3-R1Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9755 | 20210827-3-R1 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-08-27 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-09-05 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975520210827-3-R1Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting975520210827-3-R1Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9755 | 20210827-3-R1 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-08-27 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-09-05 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975520210827-3-R1Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting975520210827-3-R1Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9755 | 20210827-3-R1 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-08-27 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-09-05 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975520210827-3-R1Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting975520210827-3-R1Excavator - 36 ton- After Jan 1091322.64INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9755 | 20210827-3-R1 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-08-27 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-09-05 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975520210827-3-R1Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting975520210827-3-R1Excavator - 36 ton- After Jan 1091322.64INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9755 | 20210827-3-R1 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-08-27 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-09-05 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975520210827-3-R1Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting975520210827-3-R1Excavator - 36 ton- After Jan 1091322.64INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9755 | 20210827-3-R1 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-08-27 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-09-05 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975520210827-3-R1Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting975520210827-3-R1Excavator - 36 ton- After Jan 1091322.64INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9755 | 20210827-3-R1 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 103.84 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2021-08-27 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-09-05 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975520210827-3-R1Excavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting975520210827-3-R1Excavator - 30 ton- After Jan 1091246.05INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9755 | 20210827-3-R1 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 103.84 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2021-08-27 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-09-05 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975520210827-3-R1Excavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting975520210827-3-R1Excavator - 30 ton- After Jan 1091246.05INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9755 | 20210827-3-R1 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 103.84 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2021-08-27 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-09-05 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975520210827-3-R1Excavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting975520210827-3-R1Excavator - 30 ton- After Jan 1091246.05INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9754 | 20210826-3 | 53511012 | Access | 0 | Labourer - General - After Jan 10 | 60 | 11 | HR |  |  | 60 | 0 | 660 | 85.8 | 745.8 | 2021-08-26 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975420210826-3Labourer - General - After Jan 1011660 | Corbiere and Sons Contracting975420210826-3Labourer - General - After Jan 1011660INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9754 | 20210826-3 | 53511012 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 143 | HR |  |  | 75 | 0 | 10725 | 1394.25 | 12119.25 | 2021-08-26 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975420210826-3Operator - Principle - After Jan 1014310725 | Corbiere and Sons Contracting975420210826-3Operator - Principle - After Jan 1014310725INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9754 | 20210826-3 | 53511012 | Access | 0 | L.O.A. | 210 | 15 | DAY |  |  |  | 0 | 3150 | 409.5 | 3559.5 | 2021-08-26 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975420210826-3L.O.A.153150 | Corbiere and Sons Contracting975420210826-3L.O.A.153150INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9754 | 20210826-3 | 53511012 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-08-26 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975420210826-3Foreman121140 | Corbiere and Sons Contracting975420210826-3Foreman121140INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9754 | 20210826-3 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 9 | Dynamic | 103.54 | 0 |  |  | 1242.45 | 161.5185 | 1403.9685 | 2021-08-26 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975420210826-3Rock Truck - 30 Ton- After Jan 1091242.45 | Corbiere and Sons Contracting975420210826-3Rock Truck - 30 Ton- After Jan 1091242.45INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9754 | 20210826-3 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 9 | Dynamic | 103.54 | 0 |  |  | 1242.45 | 161.5185 | 1403.9685 | 2021-08-26 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975420210826-3Rock Truck - 30 Ton- After Jan 1091242.45 | Corbiere and Sons Contracting975420210826-3Rock Truck - 30 Ton- After Jan 1091242.45INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9754 | 20210826-3 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 9 | Dynamic | 103.54 | 0 |  |  | 1242.45 | 161.5185 | 1403.9685 | 2021-08-26 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975420210826-3Rock Truck - 30 Ton- After Jan 1091242.45 | Corbiere and Sons Contracting975420210826-3Rock Truck - 30 Ton- After Jan 1091242.45INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9754 | 20210826-3 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 9 | Dynamic | 103.54 | 0 |  |  | 1242.45 | 161.5185 | 1403.9685 | 2021-08-26 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975420210826-3Rock Truck - 30 Ton- After Jan 1091242.45 | Corbiere and Sons Contracting975420210826-3Rock Truck - 30 Ton- After Jan 1091242.45INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9754 | 20210826-3 | 53511012 | Access | 0 | Marooka- After Jan 10 | 144.6 | 5 | Dynamic | 108.45 | 0 |  |  | 723 | 93.99 | 816.99 | 2021-08-26 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975420210826-3Marooka- After Jan 105723 | Corbiere and Sons Contracting975420210826-3Marooka- After Jan 105723INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9754 | 20210826-3 | 53511012 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 7 | DAY | 182.81 | 0 |  |  | 1706.25 | 221.8125 | 1928.0625 | 2021-08-26 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975420210826-3Light Truck - Pick up- After Jan 1071706.25 | Corbiere and Sons Contracting975420210826-3Light Truck - Pick up- After Jan 1071706.25INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9754 | 20210826-3 | 53511012 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-08-26 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975420210826-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting975420210826-3Light Truck - Pick up- After Jan 101243.75INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9754 | 20210826-3 | 53511012 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 9 | HR | 47.54 | 0 |  |  | 570.42 | 74.1546 | 644.5746 | 2021-08-26 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975420210826-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42 | Corbiere and Sons Contracting975420210826-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9754 | 20210826-3 | 53511012 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 9 | HR | 47.54 | 0 |  |  | 570.42 | 74.1546 | 644.5746 | 2021-08-26 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975420210826-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42 | Corbiere and Sons Contracting975420210826-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9754 | 20210826-3 | 53511012 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 8.5 | HR | 47.54 | 0 |  |  | 538.73 | 70.0349 | 608.7649 | 2021-08-26 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975420210826-3Excavator Hammer - 30 - 50 ton- After Jan 108.5538.73 | Corbiere and Sons Contracting975420210826-3Excavator Hammer - 30 - 50 ton- After Jan 108.5538.73INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9754 | 20210826-3 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-08-26 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975420210826-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting975420210826-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9754 | 20210826-3 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-08-26 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975420210826-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting975420210826-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9754 | 20210826-3 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-08-26 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975420210826-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting975420210826-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9754 | 20210826-3 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-08-26 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975420210826-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting975420210826-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9754 | 20210826-3 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-08-26 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975420210826-3Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting975420210826-3Excavator - 36 ton- After Jan 1091322.64INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9754 | 20210826-3 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-08-26 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975420210826-3Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting975420210826-3Excavator - 36 ton- After Jan 1091322.64INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9754 | 20210826-3 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-08-26 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975420210826-3Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting975420210826-3Excavator - 36 ton- After Jan 1091322.64INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9754 | 20210826-3 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 8.5 | Dynamic | 110.22 | 0 |  |  | 1249.16 | 162.3908 | 1411.5508 | 2021-08-26 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975420210826-3Excavator - 36 ton- After Jan 108.51249.16 | Corbiere and Sons Contracting975420210826-3Excavator - 36 ton- After Jan 108.51249.16INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9754 | 20210826-3 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 103.84 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2021-08-26 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975420210826-3Excavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting975420210826-3Excavator - 30 ton- After Jan 1091246.05INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9754 | 20210826-3 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 103.84 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2021-08-26 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975420210826-3Excavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting975420210826-3Excavator - 30 ton- After Jan 1091246.05INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9754 | 20210826-3 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 103.84 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2021-08-26 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975420210826-3Excavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting975420210826-3Excavator - 30 ton- After Jan 1091246.05INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9754 | 20210826-3 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 103.84 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2021-08-26 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975420210826-3Excavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting975420210826-3Excavator - 30 ton- After Jan 1091246.05INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9753 | 20210825-3 | 53511012 | Access | 0 | Labourer - General - After Jan 10 | 60 | 11 | HR |  |  | 60 | 0 | 660 | 85.8 | 745.8 | 2021-08-25 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Dorion | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975320210825-3Labourer - General - After Jan 1011660 | Corbiere and Sons Contracting975320210825-3Labourer - General - After Jan 1011660INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9753 | 20210825-3 | 53511012 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 11.5 | HR |  |  | 70 | 0 | 805 | 104.65 | 909.65 | 2021-08-25 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Dorion | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975320210825-3Driver - AZ - After Jan 1011.5805 | Corbiere and Sons Contracting975320210825-3Driver - AZ - After Jan 1011.5805INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9753 | 20210825-3 | 53511012 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 143 | HR |  |  | 75 | 0 | 10725 | 1394.25 | 12119.25 | 2021-08-25 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Dorion | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975320210825-3Operator - Principle - After Jan 1014310725 | Corbiere and Sons Contracting975320210825-3Operator - Principle - After Jan 1014310725INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9753 | 20210825-3 | 53511012 | Access | 0 | L.O.A. | 210 | 16 | DAY |  |  |  | 0 | 3360 | 436.8 | 3796.8 | 2021-08-25 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Dorion | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975320210825-3L.O.A.163360 | Corbiere and Sons Contracting975320210825-3L.O.A.163360INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9753 | 20210825-3 | 53511012 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-08-25 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Dorion | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975320210825-3Foreman121140 | Corbiere and Sons Contracting975320210825-3Foreman121140INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9753 | 20210825-3 | 53511012 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 11.5 | Dynamic | 91.79 | 0 |  |  | 1407.485 | 182.9731 | 1590.458 | 2021-08-25 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Dorion | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975320210825-3Tractor Trailer - 60 Ton- After Jan 1011.51407.485 | Corbiere and Sons Contracting975320210825-3Tractor Trailer - 60 Ton- After Jan 1011.51407.485INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9753 | 20210825-3 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 9 | Dynamic | 103.54 | 0 |  |  | 1242.45 | 161.5185 | 1403.9685 | 2021-08-25 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Dorion | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975320210825-3Rock Truck - 30 Ton- After Jan 1091242.45 | Corbiere and Sons Contracting975320210825-3Rock Truck - 30 Ton- After Jan 1091242.45INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9753 | 20210825-3 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 9 | Dynamic | 103.54 | 0 |  |  | 1242.45 | 161.5185 | 1403.9685 | 2021-08-25 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Dorion | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975320210825-3Rock Truck - 30 Ton- After Jan 1091242.45 | Corbiere and Sons Contracting975320210825-3Rock Truck - 30 Ton- After Jan 1091242.45INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9753 | 20210825-3 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 9 | Dynamic | 103.54 | 0 |  |  | 1242.45 | 161.5185 | 1403.9685 | 2021-08-25 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Dorion | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975320210825-3Rock Truck - 30 Ton- After Jan 1091242.45 | Corbiere and Sons Contracting975320210825-3Rock Truck - 30 Ton- After Jan 1091242.45INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9753 | 20210825-3 | 53511012 | Access | 0 | Marooka- After Jan 10 | 144.6 | 5 | Dynamic | 108.45 | 0 |  |  | 723 | 93.99 | 816.99 | 2021-08-25 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Dorion | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975320210825-3Marooka- After Jan 105723 | Corbiere and Sons Contracting975320210825-3Marooka- After Jan 105723INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9753 | 20210825-3 | 53511012 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 7 | DAY | 182.81 | 0 |  |  | 1706.25 | 221.8125 | 1928.0625 | 2021-08-25 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Dorion | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975320210825-3Light Truck - Pick up- After Jan 1071706.25 | Corbiere and Sons Contracting975320210825-3Light Truck - Pick up- After Jan 1071706.25INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9753 | 20210825-3 | 53511012 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-08-25 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Dorion | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975320210825-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting975320210825-3Light Truck - Pick up- After Jan 101243.75INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9753 | 20210825-3 | 53511012 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 9 | HR | 47.54 | 0 |  |  | 570.42 | 74.1546 | 644.5746 | 2021-08-25 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Dorion | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975320210825-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42 | Corbiere and Sons Contracting975320210825-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9753 | 20210825-3 | 53511012 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 9 | HR | 47.54 | 0 |  |  | 570.42 | 74.1546 | 644.5746 | 2021-08-25 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Dorion | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975320210825-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42 | Corbiere and Sons Contracting975320210825-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9753 | 20210825-3 | 53511012 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 9 | HR | 47.54 | 0 |  |  | 570.42 | 74.1546 | 644.5746 | 2021-08-25 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Dorion | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975320210825-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42 | Corbiere and Sons Contracting975320210825-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9753 | 20210825-3 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-08-25 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Dorion | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975320210825-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting975320210825-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9753 | 20210825-3 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 8 | HR | 9.16 | 0 |  |  | 97.68 | 12.6984 | 110.3784 | 2021-08-25 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Dorion | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975320210825-3Excavator Thumb - 30 - 50 ton- After Jan 10897.68 | Corbiere and Sons Contracting975320210825-3Excavator Thumb - 30 - 50 ton- After Jan 10897.68INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9753 | 20210825-3 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-08-25 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Dorion | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975320210825-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting975320210825-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9753 | 20210825-3 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-08-25 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Dorion | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975320210825-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting975320210825-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9753 | 20210825-3 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-08-25 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Dorion | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975320210825-3Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting975320210825-3Excavator - 36 ton- After Jan 1091322.64INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9753 | 20210825-3 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-08-25 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Dorion | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975320210825-3Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting975320210825-3Excavator - 36 ton- After Jan 1091322.64INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9753 | 20210825-3 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-08-25 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Dorion | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975320210825-3Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting975320210825-3Excavator - 36 ton- After Jan 1091322.64INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9753 | 20210825-3 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-08-25 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Dorion | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975320210825-3Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting975320210825-3Excavator - 36 ton- After Jan 1091322.64INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9753 | 20210825-3 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 8 | Dynamic | 103.84 | 0 |  |  | 1107.6 | 143.988 | 1251.588 | 2021-08-25 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Dorion | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975320210825-3Excavator - 30 ton- After Jan 1081107.6 | Corbiere and Sons Contracting975320210825-3Excavator - 30 ton- After Jan 1081107.6INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9753 | 20210825-3 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 103.84 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2021-08-25 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Dorion | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975320210825-3Excavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting975320210825-3Excavator - 30 ton- After Jan 1091246.05INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9753 | 20210825-3 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 103.84 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2021-08-25 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Dorion | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975320210825-3Excavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting975320210825-3Excavator - 30 ton- After Jan 1091246.05INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9753 | 20210825-3 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 103.84 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2021-08-25 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM33-KM34 and KM38-KM44 | 6 | F066-F118 | Dorion | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975320210825-3Excavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting975320210825-3Excavator - 30 ton- After Jan 1091246.05INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9752 | 20210824-4 | 53511012 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-08-24 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Stockpiling of material at KM24.5 | 6 | km 24.5 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975220210824-4Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting975220210824-4Operator - Principle - After Jan 1011825INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9752 | 20210824-4 | 53511012 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-08-24 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Stockpiling of material at KM24.5 | 6 | km 24.5 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975220210824-4L.O.A.1210 | Corbiere and Sons Contracting975220210824-4L.O.A.1210INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9752 | 20210824-4 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-08-24 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Stockpiling of material at KM24.5 | 6 | km 24.5 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975220210824-4Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting975220210824-4Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9752 | 20210824-4 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-08-24 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Stockpiling of material at KM24.5 | 6 | km 24.5 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975220210824-4Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting975220210824-4Excavator - 36 ton- After Jan 1091322.64INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9751 | 20210824-3 | 53511012 | Access | 0 | Labourer - General - After Jan 10 | 60 | 11 | HR |  |  | 60 | 0 | 660 | 85.8 | 745.8 | 2021-08-24 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM34-KM38 and KM40-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975120210824-3Labourer - General - After Jan 1011660 | Corbiere and Sons Contracting975120210824-3Labourer - General - After Jan 1011660INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9751 | 20210824-3 | 53511012 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-08-24 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM34-KM38 and KM40-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975120210824-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting975120210824-3Operator - Principle - After Jan 1011825INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9751 | 20210824-3 | 53511012 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 143 | HR |  |  | 75 | 0 | 10725 | 1394.25 | 12119.25 | 2021-08-24 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM34-KM38 and KM40-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975120210824-3Operator - Principle - After Jan 1014310725 | Corbiere and Sons Contracting975120210824-3Operator - Principle - After Jan 1014310725INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9751 | 20210824-3 | 53511012 | Access | 0 | L.O.A. | 210 | 16 | DAY |  |  |  | 0 | 3360 | 436.8 | 3796.8 | 2021-08-24 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM34-KM38 and KM40-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975120210824-3L.O.A.163360 | Corbiere and Sons Contracting975120210824-3L.O.A.163360INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9751 | 20210824-3 | 53511012 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-08-24 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM34-KM38 and KM40-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975120210824-3Foreman121140 | Corbiere and Sons Contracting975120210824-3Foreman121140INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9751 | 20210824-3 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 9 | Dynamic | 103.54 | 0 |  |  | 1242.45 | 161.5185 | 1403.9685 | 2021-08-24 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM34-KM38 and KM40-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975120210824-3Rock Truck - 30 Ton- After Jan 1091242.45 | Corbiere and Sons Contracting975120210824-3Rock Truck - 30 Ton- After Jan 1091242.45INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9751 | 20210824-3 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 9 | Dynamic | 103.54 | 0 |  |  | 1242.45 | 161.5185 | 1403.9685 | 2021-08-24 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM34-KM38 and KM40-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975120210824-3Rock Truck - 30 Ton- After Jan 1091242.45 | Corbiere and Sons Contracting975120210824-3Rock Truck - 30 Ton- After Jan 1091242.45INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9751 | 20210824-3 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 9 | Dynamic | 103.54 | 0 |  |  | 1242.45 | 161.5185 | 1403.9685 | 2021-08-24 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM34-KM38 and KM40-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975120210824-3Rock Truck - 30 Ton- After Jan 1091242.45 | Corbiere and Sons Contracting975120210824-3Rock Truck - 30 Ton- After Jan 1091242.45INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9751 | 20210824-3 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 9 | Dynamic | 103.54 | 0 |  |  | 1242.45 | 161.5185 | 1403.9685 | 2021-08-24 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM34-KM38 and KM40-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975120210824-3Rock Truck - 30 Ton- After Jan 1091242.45 | Corbiere and Sons Contracting975120210824-3Rock Truck - 30 Ton- After Jan 1091242.45INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9751 | 20210824-3 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 9 | Dynamic | 103.54 | 0 |  |  | 1242.45 | 161.5185 | 1403.9685 | 2021-08-24 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM34-KM38 and KM40-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975120210824-3Rock Truck - 30 Ton- After Jan 1091242.45 | Corbiere and Sons Contracting975120210824-3Rock Truck - 30 Ton- After Jan 1091242.45INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9751 | 20210824-3 | 53511012 | Access | 0 | Marooka- After Jan 10 | 144.6 | 5 | Dynamic | 108.45 | 0 |  |  | 723 | 93.99 | 816.99 | 2021-08-24 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM34-KM38 and KM40-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975120210824-3Marooka- After Jan 105723 | Corbiere and Sons Contracting975120210824-3Marooka- After Jan 105723INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9751 | 20210824-3 | 53511012 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 8 | DAY | 182.81 | 0 |  |  | 1950 | 253.5 | 2203.5 | 2021-08-24 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM34-KM38 and KM40-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975120210824-3Light Truck - Pick up- After Jan 1081950 | Corbiere and Sons Contracting975120210824-3Light Truck - Pick up- After Jan 1081950INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9751 | 20210824-3 | 53511012 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-08-24 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM34-KM38 and KM40-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975120210824-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting975120210824-3Light Truck - Pick up- After Jan 101243.75INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9751 | 20210824-3 | 53511012 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 5 | HR | 47.54 | 0 |  |  | 316.9 | 41.197 | 358.097 | 2021-08-24 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM34-KM38 and KM40-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975120210824-3Excavator Hammer - 30 - 50 ton- After Jan 105316.9 | Corbiere and Sons Contracting975120210824-3Excavator Hammer - 30 - 50 ton- After Jan 105316.9INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9751 | 20210824-3 | 53511012 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 7 | HR | 47.54 | 0 |  |  | 443.66 | 57.6758 | 501.3358 | 2021-08-24 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM34-KM38 and KM40-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975120210824-3Excavator Hammer - 30 - 50 ton- After Jan 107443.66 | Corbiere and Sons Contracting975120210824-3Excavator Hammer - 30 - 50 ton- After Jan 107443.66INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9751 | 20210824-3 | 53511012 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 9 | HR | 47.54 | 0 |  |  | 570.42 | 74.1546 | 644.5746 | 2021-08-24 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM34-KM38 and KM40-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975120210824-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42 | Corbiere and Sons Contracting975120210824-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9751 | 20210824-3 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-08-24 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM34-KM38 and KM40-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975120210824-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting975120210824-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9751 | 20210824-3 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 2 | HR | 9.16 | 0 |  |  | 24.42 | 3.1746 | 27.5946 | 2021-08-24 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM34-KM38 and KM40-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975120210824-3Excavator Thumb - 30 - 50 ton- After Jan 10224.42 | Corbiere and Sons Contracting975120210824-3Excavator Thumb - 30 - 50 ton- After Jan 10224.42INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9751 | 20210824-3 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-08-24 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM34-KM38 and KM40-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975120210824-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting975120210824-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9751 | 20210824-3 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 2 | Dynamic | 110.22 | 0 |  |  | 293.92 | 38.2096 | 332.1296 | 2021-08-24 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM34-KM38 and KM40-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975120210824-3Excavator - 36 ton- After Jan 102293.92 | Corbiere and Sons Contracting975120210824-3Excavator - 36 ton- After Jan 102293.92INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9751 | 20210824-3 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-08-24 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM34-KM38 and KM40-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975120210824-3Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting975120210824-3Excavator - 36 ton- After Jan 1091322.64INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9751 | 20210824-3 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-08-24 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM34-KM38 and KM40-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975120210824-3Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting975120210824-3Excavator - 36 ton- After Jan 1091322.64INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9751 | 20210824-3 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 103.84 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2021-08-24 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM34-KM38 and KM40-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975120210824-3Excavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting975120210824-3Excavator - 30 ton- After Jan 1091246.05INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9751 | 20210824-3 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 5 | Dynamic | 103.84 | 0 |  |  | 692.25 | 89.9925 | 782.2425 | 2021-08-24 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM34-KM38 and KM40-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975120210824-3Excavator - 30 ton- After Jan 105692.25 | Corbiere and Sons Contracting975120210824-3Excavator - 30 ton- After Jan 105692.25INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9751 | 20210824-3 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 7 | Dynamic | 103.84 | 0 |  |  | 969.15 | 125.9895 | 1095.1395 | 2021-08-24 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM34-KM38 and KM40-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975120210824-3Excavator - 30 ton- After Jan 107969.15 | Corbiere and Sons Contracting975120210824-3Excavator - 30 ton- After Jan 107969.15INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9751 | 20210824-3 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 103.84 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2021-08-24 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM34-KM38 and KM40-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975120210824-3Excavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting975120210824-3Excavator - 30 ton- After Jan 1091246.05INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9751 | 20210824-3 | 53511012 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 9 | Dynamic | 98.61 | 0 |  |  | 1183.32 | 153.8316 | 1337.1516 | 2021-08-24 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26, KM34-KM38 and KM40-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting975120210824-3Dozer D6 or equal- After Jan 1091183.32 | Corbiere and Sons Contracting975120210824-3Dozer D6 or equal- After Jan 1091183.32INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9740 | 20210823-4 | 53511012 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-08-23 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Stockpiling of material at KM24.5 | 6 | km 24.5 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting974020210823-4Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting974020210823-4Operator - Principle - After Jan 1011825INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9740 | 20210823-4 | 53511012 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-08-23 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Stockpiling of material at KM24.5 | 6 | km 24.5 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting974020210823-4L.O.A.1210 | Corbiere and Sons Contracting974020210823-4L.O.A.1210INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9740 | 20210823-4 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-08-23 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Stockpiling of material at KM24.5 | 6 | km 24.5 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting974020210823-4Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting974020210823-4Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9740 | 20210823-4 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-08-23 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Stockpiling of material at KM24.5 | 6 | km 24.5 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-08-31 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting974020210823-4Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting974020210823-4Excavator - 36 ton- After Jan 1091322.64INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9733 | 20210823-3 | 53511012 | Access | 0 | Labourer - General - After Jan 10 | 60 | 11 | HR |  |  | 0 | 0 | 660 | 85.8 | 745.8 | 2021-08-23 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26 and KM40-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-26 |  | 37 | 2021-09-01 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting973320210823-3Labourer - General - After Jan 1011660 | Corbiere and Sons Contracting973320210823-3Labourer - General - After Jan 1011660INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9733 | 20210823-3 | 53511012 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 143 | HR |  |  | 0 | 0 | 10725 | 1394.25 | 12119.25 | 2021-08-23 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26 and KM40-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-26 |  | 37 | 2021-09-01 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting973320210823-3Operator - Principle - After Jan 1014310725 | Corbiere and Sons Contracting973320210823-3Operator - Principle - After Jan 1014310725INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9733 | 20210823-3 | 53511012 | Access | 0 | L.O.A. | 210 | 15 | DAY |  |  | 0 | 0 | 3150 | 409.5 | 3559.5 | 2021-08-23 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26 and KM40-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-26 |  | 37 | 2021-09-01 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting973320210823-3L.O.A.153150 | Corbiere and Sons Contracting973320210823-3L.O.A.153150INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9733 | 20210823-3 | 53511012 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 0 | 0 | 1140 | 148.2 | 1288.2 | 2021-08-23 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26 and KM40-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-26 |  | 37 | 2021-09-01 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting973320210823-3Foreman121140 | Corbiere and Sons Contracting973320210823-3Foreman121140INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9733 | 20210823-3 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 9 | Dynamic | 103.54 | 0 |  |  | 1242.45 | 161.5185 | 1403.9685 | 2021-08-23 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26 and KM40-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-26 |  | 37 | 2021-09-01 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting973320210823-3Rock Truck - 30 Ton- After Jan 1091242.45 | Corbiere and Sons Contracting973320210823-3Rock Truck - 30 Ton- After Jan 1091242.45INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9733 | 20210823-3 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 9 | Dynamic | 103.54 | 0 |  |  | 1242.45 | 161.5185 | 1403.9685 | 2021-08-23 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26 and KM40-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-26 |  | 37 | 2021-09-01 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting973320210823-3Rock Truck - 30 Ton- After Jan 1091242.45 | Corbiere and Sons Contracting973320210823-3Rock Truck - 30 Ton- After Jan 1091242.45INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9733 | 20210823-3 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 9 | Dynamic | 103.54 | 0 |  |  | 1242.45 | 161.5185 | 1403.9685 | 2021-08-23 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26 and KM40-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-26 |  | 37 | 2021-09-01 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting973320210823-3Rock Truck - 30 Ton- After Jan 1091242.45 | Corbiere and Sons Contracting973320210823-3Rock Truck - 30 Ton- After Jan 1091242.45INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9733 | 20210823-3 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 9 | Dynamic | 103.54 | 0 |  |  | 1242.45 | 161.5185 | 1403.9685 | 2021-08-23 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26 and KM40-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-26 |  | 37 | 2021-09-01 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting973320210823-3Rock Truck - 30 Ton- After Jan 1091242.45 | Corbiere and Sons Contracting973320210823-3Rock Truck - 30 Ton- After Jan 1091242.45INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9733 | 20210823-3 | 53511012 | Access | 0 | Marooka- After Jan 10 | 144.6 | 5 | Dynamic | 108.45 | 0 |  |  | 723 | 93.99 | 816.99 | 2021-08-23 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26 and KM40-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-26 |  | 37 | 2021-09-01 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting973320210823-3Marooka- After Jan 105723 | Corbiere and Sons Contracting973320210823-3Marooka- After Jan 105723INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9733 | 20210823-3 | 53511012 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 8 | DAY | 182.81 | 0 |  |  | 1950 | 253.5 | 2203.5 | 2021-08-23 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26 and KM40-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-26 |  | 37 | 2021-09-01 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting973320210823-3Light Truck - Pick up- After Jan 1081950 | Corbiere and Sons Contracting973320210823-3Light Truck - Pick up- After Jan 1081950INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9733 | 20210823-3 | 53511012 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-08-23 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26 and KM40-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-26 |  | 37 | 2021-09-01 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting973320210823-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting973320210823-3Light Truck - Pick up- After Jan 101243.75INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9733 | 20210823-3 | 53511012 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 5 | HR | 47.54 | 0 |  |  | 316.9 | 41.197 | 358.097 | 2021-08-23 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26 and KM40-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-26 |  | 37 | 2021-09-01 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting973320210823-3Excavator Hammer - 30 - 50 ton- After Jan 105316.9 | Corbiere and Sons Contracting973320210823-3Excavator Hammer - 30 - 50 ton- After Jan 105316.9INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9733 | 20210823-3 | 53511012 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 9 | HR | 47.54 | 0 |  |  | 570.42 | 74.1546 | 644.5746 | 2021-08-23 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26 and KM40-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-26 |  | 37 | 2021-09-01 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting973320210823-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42 | Corbiere and Sons Contracting973320210823-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9733 | 20210823-3 | 53511012 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 9 | HR | 47.54 | 0 |  |  | 570.42 | 74.1546 | 644.5746 | 2021-08-23 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26 and KM40-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-26 |  | 37 | 2021-09-01 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting973320210823-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42 | Corbiere and Sons Contracting973320210823-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9733 | 20210823-3 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-08-23 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26 and KM40-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-26 |  | 37 | 2021-09-01 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting973320210823-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting973320210823-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9733 | 20210823-3 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-08-23 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26 and KM40-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-26 |  | 37 | 2021-09-01 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting973320210823-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting973320210823-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9733 | 20210823-3 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-08-23 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26 and KM40-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-26 |  | 37 | 2021-09-01 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting973320210823-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting973320210823-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9733 | 20210823-3 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-08-23 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26 and KM40-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-26 |  | 37 | 2021-09-01 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting973320210823-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting973320210823-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9733 | 20210823-3 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-08-23 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26 and KM40-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-26 |  | 37 | 2021-09-01 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting973320210823-3Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting973320210823-3Excavator - 36 ton- After Jan 1091322.64INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9733 | 20210823-3 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-08-23 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26 and KM40-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-26 |  | 37 | 2021-09-01 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting973320210823-3Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting973320210823-3Excavator - 36 ton- After Jan 1091322.64INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9733 | 20210823-3 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-08-23 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26 and KM40-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-26 |  | 37 | 2021-09-01 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting973320210823-3Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting973320210823-3Excavator - 36 ton- After Jan 1091322.64INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9733 | 20210823-3 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 103.84 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2021-08-23 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26 and KM40-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-26 |  | 37 | 2021-09-01 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting973320210823-3Excavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting973320210823-3Excavator - 30 ton- After Jan 1091246.05INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9733 | 20210823-3 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 5 | Dynamic | 103.84 | 0 |  |  | 692.25 | 89.9925 | 782.2425 | 2021-08-23 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26 and KM40-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-26 |  | 37 | 2021-09-01 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting973320210823-3Excavator - 30 ton- After Jan 105692.25 | Corbiere and Sons Contracting973320210823-3Excavator - 30 ton- After Jan 105692.25INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9733 | 20210823-3 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 103.84 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2021-08-23 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26 and KM40-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-26 |  | 37 | 2021-09-01 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting973320210823-3Excavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting973320210823-3Excavator - 30 ton- After Jan 1091246.05INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9733 | 20210823-3 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 103.84 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2021-08-23 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26 and KM40-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-26 |  | 37 | 2021-09-01 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting973320210823-3Excavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting973320210823-3Excavator - 30 ton- After Jan 1091246.05INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9733 | 20210823-3 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 103.84 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2021-08-23 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26 and KM40-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-26 |  | 37 | 2021-09-01 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting973320210823-3Excavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting973320210823-3Excavator - 30 ton- After Jan 1091246.05INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9733 | 20210823-3 | 53511012 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 9 | Dynamic | 98.61 | 0 |  |  | 1183.32 | 153.8316 | 1337.1516 | 2021-08-23 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23-KM26 and KM40-KM44 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-26 |  | 37 | 2021-09-01 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting973320210823-3Dozer D6 or equal- After Jan 1091183.32 | Corbiere and Sons Contracting973320210823-3Dozer D6 or equal- After Jan 1091183.32INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9732 | 20210822-3 | 53511012 | Access | 0 | Labourer - General - After Jan 10 | 60 | 11 | HR |  |  | 60 | 0 | 660 | 85.8 | 745.8 | 2021-08-22 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23, KM24, KM25 and KM41-KM45 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-25 |  | 57 | 2021-08-25 | [6 empty] | 10 | Corbiere and Sons Contracting973220210822-3Labourer - General - After Jan 1011660 | Corbiere and Sons Contracting973220210822-3Labourer - General - After Jan 1011660INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9732 | 20210822-3 | 53511012 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 121 | HR |  |  | 75 | 0 | 9075 | 1179.75 | 10254.75 | 2021-08-22 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23, KM24, KM25 and KM41-KM45 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-25 |  | 57 | 2021-08-25 | [6 empty] | 10 | Corbiere and Sons Contracting973220210822-3Operator - Principle - After Jan 101219075 | Corbiere and Sons Contracting973220210822-3Operator - Principle - After Jan 101219075INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9732 | 20210822-3 | 53511012 | Access | 0 | L.O.A. | 210 | 13 | DAY |  |  |  | 0 | 2730 | 354.9 | 3084.9 | 2021-08-22 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23, KM24, KM25 and KM41-KM45 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-25 |  | 57 | 2021-08-25 | [6 empty] | 10 | Corbiere and Sons Contracting973220210822-3L.O.A.132730 | Corbiere and Sons Contracting973220210822-3L.O.A.132730INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9732 | 20210822-3 | 53511012 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-08-22 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23, KM24, KM25 and KM41-KM45 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-25 |  | 57 | 2021-08-25 | [6 empty] | 10 | Corbiere and Sons Contracting973220210822-3Foreman121140 | Corbiere and Sons Contracting973220210822-3Foreman121140INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9732 | 20210822-3 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 9 | Dynamic | 103.54 | 0 |  |  | 1242.45 | 161.5185 | 1403.9685 | 2021-08-22 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23, KM24, KM25 and KM41-KM45 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-25 |  | 57 | 2021-08-25 | [6 empty] | 10 | Corbiere and Sons Contracting973220210822-3Rock Truck - 30 Ton- After Jan 1091242.45 | Corbiere and Sons Contracting973220210822-3Rock Truck - 30 Ton- After Jan 1091242.45INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9732 | 20210822-3 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 9 | Dynamic | 103.54 | 0 |  |  | 1242.45 | 161.5185 | 1403.9685 | 2021-08-22 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23, KM24, KM25 and KM41-KM45 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-25 |  | 57 | 2021-08-25 | [6 empty] | 10 | Corbiere and Sons Contracting973220210822-3Rock Truck - 30 Ton- After Jan 1091242.45 | Corbiere and Sons Contracting973220210822-3Rock Truck - 30 Ton- After Jan 1091242.45INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9732 | 20210822-3 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 9 | Dynamic | 103.54 | 0 |  |  | 1242.45 | 161.5185 | 1403.9685 | 2021-08-22 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23, KM24, KM25 and KM41-KM45 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-25 |  | 57 | 2021-08-25 | [6 empty] | 10 | Corbiere and Sons Contracting973220210822-3Rock Truck - 30 Ton- After Jan 1091242.45 | Corbiere and Sons Contracting973220210822-3Rock Truck - 30 Ton- After Jan 1091242.45INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9732 | 20210822-3 | 53511012 | Access | 0 | Marooka- After Jan 10 | 144.6 | 5 | Dynamic | 108.45 | 0 |  |  | 723 | 93.99 | 816.99 | 2021-08-22 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23, KM24, KM25 and KM41-KM45 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-25 |  | 57 | 2021-08-25 | [6 empty] | 10 | Corbiere and Sons Contracting973220210822-3Marooka- After Jan 105723 | Corbiere and Sons Contracting973220210822-3Marooka- After Jan 105723INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9732 | 20210822-3 | 53511012 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 8 | DAY | 182.81 | 0 |  |  | 1950 | 253.5 | 2203.5 | 2021-08-22 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23, KM24, KM25 and KM41-KM45 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-25 |  | 57 | 2021-08-25 | [6 empty] | 10 | Corbiere and Sons Contracting973220210822-3Light Truck - Pick up- After Jan 1081950 | Corbiere and Sons Contracting973220210822-3Light Truck - Pick up- After Jan 1081950INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9732 | 20210822-3 | 53511012 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 9 | HR | 47.54 | 0 |  |  | 570.42 | 74.1546 | 644.5746 | 2021-08-22 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23, KM24, KM25 and KM41-KM45 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-25 |  | 57 | 2021-08-25 | [6 empty] | 10 | Corbiere and Sons Contracting973220210822-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42 | Corbiere and Sons Contracting973220210822-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9732 | 20210822-3 | 53511012 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 9 | HR | 47.54 | 0 |  |  | 570.42 | 74.1546 | 644.5746 | 2021-08-22 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23, KM24, KM25 and KM41-KM45 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-25 |  | 57 | 2021-08-25 | [6 empty] | 10 | Corbiere and Sons Contracting973220210822-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42 | Corbiere and Sons Contracting973220210822-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9732 | 20210822-3 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-08-22 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23, KM24, KM25 and KM41-KM45 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-25 |  | 57 | 2021-08-25 | [6 empty] | 10 | Corbiere and Sons Contracting973220210822-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting973220210822-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9732 | 20210822-3 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-08-22 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23, KM24, KM25 and KM41-KM45 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-25 |  | 57 | 2021-08-25 | [6 empty] | 10 | Corbiere and Sons Contracting973220210822-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting973220210822-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9732 | 20210822-3 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-08-22 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23, KM24, KM25 and KM41-KM45 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-25 |  | 57 | 2021-08-25 | [6 empty] | 10 | Corbiere and Sons Contracting973220210822-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting973220210822-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9732 | 20210822-3 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-08-22 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23, KM24, KM25 and KM41-KM45 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-25 |  | 57 | 2021-08-25 | [6 empty] | 10 | Corbiere and Sons Contracting973220210822-3Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting973220210822-3Excavator - 36 ton- After Jan 1091322.64INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9732 | 20210822-3 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-08-22 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23, KM24, KM25 and KM41-KM45 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-25 |  | 57 | 2021-08-25 | [6 empty] | 10 | Corbiere and Sons Contracting973220210822-3Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting973220210822-3Excavator - 36 ton- After Jan 1091322.64INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9732 | 20210822-3 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-08-22 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23, KM24, KM25 and KM41-KM45 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-25 |  | 57 | 2021-08-25 | [6 empty] | 10 | Corbiere and Sons Contracting973220210822-3Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting973220210822-3Excavator - 36 ton- After Jan 1091322.64INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9732 | 20210822-3 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 103.84 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2021-08-22 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23, KM24, KM25 and KM41-KM45 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-25 |  | 57 | 2021-08-25 | [6 empty] | 10 | Corbiere and Sons Contracting973220210822-3Excavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting973220210822-3Excavator - 30 ton- After Jan 1091246.05INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9732 | 20210822-3 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 103.84 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2021-08-22 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23, KM24, KM25 and KM41-KM45 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-25 |  | 57 | 2021-08-25 | [6 empty] | 10 | Corbiere and Sons Contracting973220210822-3Excavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting973220210822-3Excavator - 30 ton- After Jan 1091246.05INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9732 | 20210822-3 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 103.84 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2021-08-22 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23, KM24, KM25 and KM41-KM45 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-25 |  | 57 | 2021-08-25 | [6 empty] | 10 | Corbiere and Sons Contracting973220210822-3Excavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting973220210822-3Excavator - 30 ton- After Jan 1091246.05INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9732 | 20210822-3 | 53511012 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 9 | Dynamic | 98.61 | 0 |  |  | 1183.32 | 153.8316 | 1337.1516 | 2021-08-22 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM23, KM24, KM25 and KM41-KM45 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-25 |  | 57 | 2021-08-25 | [6 empty] | 10 | Corbiere and Sons Contracting973220210822-3Dozer D6 or equal- After Jan 1091183.32 | Corbiere and Sons Contracting973220210822-3Dozer D6 or equal- After Jan 1091183.32INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9727 | 20210821-3 | 53511012 | Access | 0 | Labourer - General - After Jan 10 | 60 | 11 | HR |  |  | 0 | 0 | 660 | 85.8 | 745.8 | 2021-08-21 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 |  | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972720210821-3Labourer - General - After Jan 1011660 | Corbiere and Sons Contracting972720210821-3Labourer - General - After Jan 1011660INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9727 | 20210821-3 | 53511012 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 121 | HR |  |  | 0 | 0 | 9075 | 1179.75 | 10254.75 | 2021-08-21 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 |  | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972720210821-3Operator - Principle - After Jan 101219075 | Corbiere and Sons Contracting972720210821-3Operator - Principle - After Jan 101219075INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9727 | 20210821-3 | 53511012 | Access | 0 | L.O.A. | 210 | 13 | DAY |  |  | 0 | 0 | 2730 | 354.9 | 3084.9 | 2021-08-21 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 |  | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972720210821-3L.O.A.132730 | Corbiere and Sons Contracting972720210821-3L.O.A.132730INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9727 | 20210821-3 | 53511012 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 0 | 0 | 1140 | 148.2 | 1288.2 | 2021-08-21 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 |  | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972720210821-3Foreman121140 | Corbiere and Sons Contracting972720210821-3Foreman121140INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9727 | 20210821-3 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 9 | Dynamic | 103.54 | 0 |  |  | 1242.45 | 161.5185 | 1403.9685 | 2021-08-21 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 |  | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972720210821-3Rock Truck - 30 Ton- After Jan 1091242.45 | Corbiere and Sons Contracting972720210821-3Rock Truck - 30 Ton- After Jan 1091242.45INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9727 | 20210821-3 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 9 | Dynamic | 103.54 | 0 |  |  | 1242.45 | 161.5185 | 1403.9685 | 2021-08-21 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 |  | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972720210821-3Rock Truck - 30 Ton- After Jan 1091242.45 | Corbiere and Sons Contracting972720210821-3Rock Truck - 30 Ton- After Jan 1091242.45INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9727 | 20210821-3 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 18 | Dynamic | 103.54 | 0 |  |  | 2484.9 | 323.037 | 2807.937 | 2021-08-21 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 |  | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972720210821-3Rock Truck - 30 Ton- After Jan 10182484.9 | Corbiere and Sons Contracting972720210821-3Rock Truck - 30 Ton- After Jan 10182484.9INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9727 | 20210821-3 | 53511012 | Access | 0 | Marooka- After Jan 10 | 144.6 | 5 | Dynamic | 108.45 | 0 |  |  | 723 | 93.99 | 816.99 | 2021-08-21 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 |  | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972720210821-3Marooka- After Jan 105723 | Corbiere and Sons Contracting972720210821-3Marooka- After Jan 105723INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9727 | 20210821-3 | 53511012 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 8 | DAY | 182.81 | 0 |  |  | 1950 | 253.5 | 2203.5 | 2021-08-21 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 |  | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972720210821-3Light Truck - Pick up- After Jan 1081950 | Corbiere and Sons Contracting972720210821-3Light Truck - Pick up- After Jan 1081950INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9727 | 20210821-3 | 53511012 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-08-21 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 |  | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972720210821-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting972720210821-3Light Truck - Pick up- After Jan 101243.75INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9727 | 20210821-3 | 53511012 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 9 | HR | 47.54 | 0 |  |  | 570.42 | 74.1546 | 644.5746 | 2021-08-21 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 |  | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972720210821-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42 | Corbiere and Sons Contracting972720210821-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9727 | 20210821-3 | 53511012 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 9 | HR | 47.54 | 0 |  |  | 570.42 | 74.1546 | 644.5746 | 2021-08-21 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 |  | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972720210821-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42 | Corbiere and Sons Contracting972720210821-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9727 | 20210821-3 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-08-21 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 |  | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972720210821-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting972720210821-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9727 | 20210821-3 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-08-21 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 |  | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972720210821-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting972720210821-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9727 | 20210821-3 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-08-21 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 |  | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972720210821-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting972720210821-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9727 | 20210821-3 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-08-21 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 |  | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972720210821-3Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting972720210821-3Excavator - 36 ton- After Jan 1091322.64INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9727 | 20210821-3 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-08-21 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 |  | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972720210821-3Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting972720210821-3Excavator - 36 ton- After Jan 1091322.64INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9727 | 20210821-3 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-08-21 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 |  | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972720210821-3Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting972720210821-3Excavator - 36 ton- After Jan 1091322.64INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9727 | 20210821-3 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 103.84 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2021-08-21 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 |  | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972720210821-3Excavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting972720210821-3Excavator - 30 ton- After Jan 1091246.05INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9727 | 20210821-3 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 103.84 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2021-08-21 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 |  | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972720210821-3Excavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting972720210821-3Excavator - 30 ton- After Jan 1091246.05INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9727 | 20210821-3 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 103.84 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2021-08-21 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 |  | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972720210821-3Excavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting972720210821-3Excavator - 30 ton- After Jan 1091246.05INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9727 | 20210821-3 | 53511012 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 9 | Dynamic | 98.61 | 0 |  |  | 1183.32 | 153.8316 | 1337.1516 | 2021-08-21 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 |  | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972720210821-3Dozer D6 or equal- After Jan 1091183.32 | Corbiere and Sons Contracting972720210821-3Dozer D6 or equal- After Jan 1091183.32INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9726 | 20210820-3 | 53511012 | Access | 0 | Labourer - General - After Jan 10 | 60 | 11 | HR |  |  | 0 | 0 | 660 | 85.8 | 745.8 | 2021-08-20 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972620210820-3Labourer - General - After Jan 1011660 | Corbiere and Sons Contracting972620210820-3Labourer - General - After Jan 1011660INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9726 | 20210820-3 | 53511012 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 139 | HR |  |  | 0 | 0 | 10425 | 1355.25 | 11780.25 | 2021-08-20 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972620210820-3Operator - Principle - After Jan 1013910425 | Corbiere and Sons Contracting972620210820-3Operator - Principle - After Jan 1013910425INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9726 | 20210820-3 | 53511012 | Access | 0 | L.O.A. | 210 | 15 | DAY |  |  | 0 | 0 | 3150 | 409.5 | 3559.5 | 2021-08-20 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972620210820-3L.O.A.153150 | Corbiere and Sons Contracting972620210820-3L.O.A.153150INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9726 | 20210820-3 | 53511012 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 0 | 0 | 1140 | 148.2 | 1288.2 | 2021-08-20 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972620210820-3Foreman121140 | Corbiere and Sons Contracting972620210820-3Foreman121140INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9726 | 20210820-3 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 9 | Dynamic | 103.54 | 0 |  |  | 1242.45 | 161.5185 | 1403.9685 | 2021-08-20 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972620210820-3Rock Truck - 30 Ton- After Jan 1091242.45 | Corbiere and Sons Contracting972620210820-3Rock Truck - 30 Ton- After Jan 1091242.45INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9726 | 20210820-3 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 9 | Dynamic | 103.54 | 0 |  |  | 1242.45 | 161.5185 | 1403.9685 | 2021-08-20 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972620210820-3Rock Truck - 30 Ton- After Jan 1091242.45 | Corbiere and Sons Contracting972620210820-3Rock Truck - 30 Ton- After Jan 1091242.45INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9726 | 20210820-3 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 9 | Dynamic | 103.54 | 0 |  |  | 1242.45 | 161.5185 | 1403.9685 | 2021-08-20 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972620210820-3Rock Truck - 30 Ton- After Jan 1091242.45 | Corbiere and Sons Contracting972620210820-3Rock Truck - 30 Ton- After Jan 1091242.45INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9726 | 20210820-3 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 16 | Dynamic | 103.54 | 0 |  |  | 2208.8 | 287.144 | 2495.944 | 2021-08-20 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972620210820-3Rock Truck - 30 Ton- After Jan 10162208.8 | Corbiere and Sons Contracting972620210820-3Rock Truck - 30 Ton- After Jan 10162208.8INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9726 | 20210820-3 | 53511012 | Access | 0 | Marooka- After Jan 10 | 144.6 | 5 | Dynamic | 108.45 | 0 |  |  | 723 | 93.99 | 816.99 | 2021-08-20 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972620210820-3Marooka- After Jan 105723 | Corbiere and Sons Contracting972620210820-3Marooka- After Jan 105723INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9726 | 20210820-3 | 53511012 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 7 | DAY | 182.81 | 0 |  |  | 1706.25 | 221.8125 | 1928.0625 | 2021-08-20 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972620210820-3Light Truck - Pick up- After Jan 1071706.25 | Corbiere and Sons Contracting972620210820-3Light Truck - Pick up- After Jan 1071706.25INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9726 | 20210820-3 | 53511012 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-08-20 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972620210820-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting972620210820-3Light Truck - Pick up- After Jan 101243.75INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9726 | 20210820-3 | 53511012 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-08-20 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972620210820-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting972620210820-3Light Truck - Pick up- After Jan 101243.75INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9726 | 20210820-3 | 53511012 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 8 | HR | 47.54 | 0 |  |  | 507.04 | 65.9152 | 572.9552 | 2021-08-20 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972620210820-3Excavator Hammer - 30 - 50 ton- After Jan 108507.04 | Corbiere and Sons Contracting972620210820-3Excavator Hammer - 30 - 50 ton- After Jan 108507.04INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9726 | 20210820-3 | 53511012 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 9 | HR | 47.54 | 0 |  |  | 570.42 | 74.1546 | 644.5746 | 2021-08-20 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972620210820-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42 | Corbiere and Sons Contracting972620210820-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9726 | 20210820-3 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-08-20 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972620210820-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting972620210820-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9726 | 20210820-3 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-08-20 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972620210820-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting972620210820-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9726 | 20210820-3 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 8 | HR | 9.16 | 0 |  |  | 97.68 | 12.6984 | 110.3784 | 2021-08-20 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972620210820-3Excavator Thumb - 30 - 50 ton- After Jan 10897.68 | Corbiere and Sons Contracting972620210820-3Excavator Thumb - 30 - 50 ton- After Jan 10897.68INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9726 | 20210820-3 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-08-20 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972620210820-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting972620210820-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9726 | 20210820-3 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-08-20 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972620210820-3Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting972620210820-3Excavator - 36 ton- After Jan 1091322.64INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9726 | 20210820-3 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-08-20 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972620210820-3Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting972620210820-3Excavator - 36 ton- After Jan 1091322.64INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9726 | 20210820-3 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-08-20 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972620210820-3Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting972620210820-3Excavator - 36 ton- After Jan 1091322.64INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9726 | 20210820-3 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 103.84 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2021-08-20 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972620210820-3Excavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting972620210820-3Excavator - 30 ton- After Jan 1091246.05INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9726 | 20210820-3 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 8 | Dynamic | 103.84 | 0 |  |  | 1107.6 | 143.988 | 1251.588 | 2021-08-20 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972620210820-3Excavator - 30 ton- After Jan 1081107.6 | Corbiere and Sons Contracting972620210820-3Excavator - 30 ton- After Jan 1081107.6INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9726 | 20210820-3 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 8 | Dynamic | 103.84 | 0 |  |  | 1107.6 | 143.988 | 1251.588 | 2021-08-20 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972620210820-3Excavator - 30 ton- After Jan 1081107.6 | Corbiere and Sons Contracting972620210820-3Excavator - 30 ton- After Jan 1081107.6INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9726 | 20210820-3 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 103.84 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2021-08-20 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972620210820-3Excavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting972620210820-3Excavator - 30 ton- After Jan 1091246.05INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9726 | 20210820-3 | 53511012 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 9 | Dynamic | 98.61 | 0 |  |  | 1183.32 | 153.8316 | 1337.1516 | 2021-08-20 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972620210820-3Dozer D6 or equal- After Jan 1091183.32 | Corbiere and Sons Contracting972620210820-3Dozer D6 or equal- After Jan 1091183.32INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9725 | 20210819-3 | 53511012 | Access | 0 | Labourer - General - After Jan 10 | 60 | 11 | HR |  |  | 0 | 0 | 660 | 85.8 | 745.8 | 2021-08-19 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 |  | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972520210819-3Labourer - General - After Jan 1011660 | Corbiere and Sons Contracting972520210819-3Labourer - General - After Jan 1011660INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9725 | 20210819-3 | 53511012 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 149 | HR |  |  | 0 | 0 | 11175 | 1452.75 | 12627.75 | 2021-08-19 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 |  | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972520210819-3Operator - Principle - After Jan 1014911175 | Corbiere and Sons Contracting972520210819-3Operator - Principle - After Jan 1014911175INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9725 | 20210819-3 | 53511012 | Access | 0 | L.O.A. | 210 | 16 | DAY |  |  | 0 | 0 | 3360 | 436.8 | 3796.8 | 2021-08-19 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 |  | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972520210819-3L.O.A.163360 | Corbiere and Sons Contracting972520210819-3L.O.A.163360INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9725 | 20210819-3 | 53511012 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 0 | 0 | 1140 | 148.2 | 1288.2 | 2021-08-19 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 |  | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972520210819-3Foreman121140 | Corbiere and Sons Contracting972520210819-3Foreman121140INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9725 | 20210819-3 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 5 | Dynamic | 103.54 | 0 |  |  | 690.25 | 89.7325 | 779.9825 | 2021-08-19 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 |  | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972520210819-3Rock Truck - 30 Ton- After Jan 105690.25 | Corbiere and Sons Contracting972520210819-3Rock Truck - 30 Ton- After Jan 105690.25INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9725 | 20210819-3 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 9 | Dynamic | 0 | 0 |  |  | 1242.45 | 161.5185 | 1403.9685 | 2021-08-19 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 |  | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972520210819-3Rock Truck - 30 Ton- After Jan 1091242.45 | Corbiere and Sons Contracting972520210819-3Rock Truck - 30 Ton- After Jan 1091242.45INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9725 | 20210819-3 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 9 | Dynamic | 0 | 0 |  |  | 1242.45 | 161.5185 | 1403.9685 | 2021-08-19 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 |  | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972520210819-3Rock Truck - 30 Ton- After Jan 1091242.45 | Corbiere and Sons Contracting972520210819-3Rock Truck - 30 Ton- After Jan 1091242.45INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9725 | 20210819-3 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 18 | Dynamic | 0 | 0 |  |  | 2484.9 | 323.037 | 2807.937 | 2021-08-19 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 |  | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972520210819-3Rock Truck - 30 Ton- After Jan 10182484.9 | Corbiere and Sons Contracting972520210819-3Rock Truck - 30 Ton- After Jan 10182484.9INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9725 | 20210819-3 | 53511012 | Access | 0 | Marooka- After Jan 10 | 144.6 | 5 | Dynamic | 0 | 0 |  |  | 723 | 93.99 | 816.99 | 2021-08-19 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 |  | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972520210819-3Marooka- After Jan 105723 | Corbiere and Sons Contracting972520210819-3Marooka- After Jan 105723INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9725 | 20210819-3 | 53511012 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 7 | DAY | 0 | 0 |  |  | 1706.25 | 221.8125 | 1928.0625 | 2021-08-19 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 |  | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972520210819-3Light Truck - Pick up- After Jan 1071706.25 | Corbiere and Sons Contracting972520210819-3Light Truck - Pick up- After Jan 1071706.25INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9725 | 20210819-3 | 53511012 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-08-19 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 |  | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972520210819-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting972520210819-3Light Truck - Pick up- After Jan 101243.75INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9725 | 20210819-3 | 53511012 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-08-19 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 |  | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972520210819-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting972520210819-3Light Truck - Pick up- After Jan 101243.75INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9725 | 20210819-3 | 53511012 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 9 | HR | 47.54 | 0 |  |  | 570.42 | 74.1546 | 644.5746 | 2021-08-19 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 |  | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972520210819-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42 | Corbiere and Sons Contracting972520210819-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9725 | 20210819-3 | 53511012 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 9 | HR | 0 | 0 |  |  | 570.42 | 74.1546 | 644.5746 | 2021-08-19 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 |  | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972520210819-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42 | Corbiere and Sons Contracting972520210819-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9725 | 20210819-3 | 53511012 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 9 | HR | 0 | 0 |  |  | 570.42 | 74.1546 | 644.5746 | 2021-08-19 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 |  | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972520210819-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42 | Corbiere and Sons Contracting972520210819-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9725 | 20210819-3 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 0 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-08-19 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 |  | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972520210819-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting972520210819-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9725 | 20210819-3 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 0 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-08-19 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 |  | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972520210819-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting972520210819-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9725 | 20210819-3 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 0 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-08-19 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 |  | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972520210819-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting972520210819-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9725 | 20210819-3 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 0 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-08-19 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 |  | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972520210819-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting972520210819-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9725 | 20210819-3 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 0 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-08-19 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 |  | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972520210819-3Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting972520210819-3Excavator - 36 ton- After Jan 1091322.64INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9725 | 20210819-3 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 0 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-08-19 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 |  | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972520210819-3Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting972520210819-3Excavator - 36 ton- After Jan 1091322.64INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9725 | 20210819-3 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 0 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-08-19 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 |  | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972520210819-3Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting972520210819-3Excavator - 36 ton- After Jan 1091322.64INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9725 | 20210819-3 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 103.84 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2021-08-19 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 |  | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972520210819-3Excavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting972520210819-3Excavator - 30 ton- After Jan 1091246.05INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9725 | 20210819-3 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 0 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2021-08-19 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 |  | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972520210819-3Excavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting972520210819-3Excavator - 30 ton- After Jan 1091246.05INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9725 | 20210819-3 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 0 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2021-08-19 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 |  | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972520210819-3Excavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting972520210819-3Excavator - 30 ton- After Jan 1091246.05INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9725 | 20210819-3 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 0 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2021-08-19 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 |  | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972520210819-3Excavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting972520210819-3Excavator - 30 ton- After Jan 1091246.05INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9725 | 20210819-3 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 0 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2021-08-19 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 |  | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972520210819-3Excavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting972520210819-3Excavator - 30 ton- After Jan 1091246.05INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9725 | 20210819-3 | 53511012 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 9 | Dynamic | 0 | 0 |  |  | 1183.32 | 153.8316 | 1337.1516 | 2021-08-19 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 |  | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972520210819-3Dozer D6 or equal- After Jan 1091183.32 | Corbiere and Sons Contracting972520210819-3Dozer D6 or equal- After Jan 1091183.32INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9724 | 20210818-3 | 53511012 | Access | 0 | Labourer - General - After Jan 10 | 60 | 16 | HR |  |  | 0 | 0 | 960 | 124.8 | 1084.8 | 2021-08-19 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972420210818-3Labourer - General - After Jan 1016960 | Corbiere and Sons Contracting972420210818-3Labourer - General - After Jan 1016960INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9724 | 20210818-3 | 53511012 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 143 | HR |  |  | 0 | 0 | 10725 | 1394.25 | 12119.25 | 2021-08-19 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972420210818-3Operator - Principle - After Jan 1014310725 | Corbiere and Sons Contracting972420210818-3Operator - Principle - After Jan 1014310725INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9724 | 20210818-3 | 53511012 | Access | 0 | L.O.A. | 210 | 16 | DAY |  |  | 0 | 0 | 3360 | 436.8 | 3796.8 | 2021-08-19 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972420210818-3L.O.A.163360 | Corbiere and Sons Contracting972420210818-3L.O.A.163360INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9724 | 20210818-3 | 53511012 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 0 | 0 | 1140 | 148.2 | 1288.2 | 2021-08-19 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972420210818-3Foreman121140 | Corbiere and Sons Contracting972420210818-3Foreman121140INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9724 | 20210818-3 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 9 | Dynamic | 0 | 0 |  |  | 1242.45 | 161.5185 | 1403.9685 | 2021-08-19 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972420210818-3Rock Truck - 30 Ton- After Jan 1091242.45 | Corbiere and Sons Contracting972420210818-3Rock Truck - 30 Ton- After Jan 1091242.45INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9724 | 20210818-3 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 9 | Dynamic | 0 | 0 |  |  | 1242.45 | 161.5185 | 1403.9685 | 2021-08-19 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972420210818-3Rock Truck - 30 Ton- After Jan 1091242.45 | Corbiere and Sons Contracting972420210818-3Rock Truck - 30 Ton- After Jan 1091242.45INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9724 | 20210818-3 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 18 | Dynamic | 0 | 0 |  |  | 2484.9 | 323.037 | 2807.937 | 2021-08-19 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972420210818-3Rock Truck - 30 Ton- After Jan 10182484.9 | Corbiere and Sons Contracting972420210818-3Rock Truck - 30 Ton- After Jan 10182484.9INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9724 | 20210818-3 | 53511012 | Access | 0 | Marooka- After Jan 10 | 144.6 | 5 | Dynamic | 0 | 0 |  |  | 723 | 93.99 | 816.99 | 2021-08-19 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972420210818-3Marooka- After Jan 105723 | Corbiere and Sons Contracting972420210818-3Marooka- After Jan 105723INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9724 | 20210818-3 | 53511012 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 7 | DAY | 0 | 0 |  |  | 1706.25 | 221.8125 | 1928.0625 | 2021-08-19 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972420210818-3Light Truck - Pick up- After Jan 1071706.25 | Corbiere and Sons Contracting972420210818-3Light Truck - Pick up- After Jan 1071706.25INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9724 | 20210818-3 | 53511012 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-08-19 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972420210818-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting972420210818-3Light Truck - Pick up- After Jan 101243.75INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9724 | 20210818-3 | 53511012 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-08-19 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972420210818-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting972420210818-3Light Truck - Pick up- After Jan 101243.75INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9724 | 20210818-3 | 53511012 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 9 | HR | 0 | 0 |  |  | 570.42 | 74.1546 | 644.5746 | 2021-08-19 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972420210818-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42 | Corbiere and Sons Contracting972420210818-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9724 | 20210818-3 | 53511012 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 9 | HR | 47.54 | 0 |  |  | 570.42 | 74.1546 | 644.5746 | 2021-08-19 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972420210818-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42 | Corbiere and Sons Contracting972420210818-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9724 | 20210818-3 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-08-19 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972420210818-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting972420210818-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9724 | 20210818-3 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-08-19 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972420210818-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting972420210818-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9724 | 20210818-3 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 0 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-08-19 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972420210818-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting972420210818-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9724 | 20210818-3 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 0 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-08-19 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972420210818-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting972420210818-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9724 | 20210818-3 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 0 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-08-19 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972420210818-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting972420210818-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9724 | 20210818-3 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 0 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-08-19 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972420210818-3Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting972420210818-3Excavator - 36 ton- After Jan 1091322.64INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9724 | 20210818-3 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 0 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-08-19 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972420210818-3Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting972420210818-3Excavator - 36 ton- After Jan 1091322.64INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9724 | 20210818-3 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-08-19 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972420210818-3Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting972420210818-3Excavator - 36 ton- After Jan 1091322.64INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9724 | 20210818-3 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 0 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-08-19 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972420210818-3Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting972420210818-3Excavator - 36 ton- After Jan 1091322.64INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9724 | 20210818-3 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 0 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2021-08-19 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972420210818-3Excavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting972420210818-3Excavator - 30 ton- After Jan 1091246.05INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9724 | 20210818-3 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 0 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2021-08-19 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972420210818-3Excavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting972420210818-3Excavator - 30 ton- After Jan 1091246.05INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9724 | 20210818-3 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 0 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2021-08-19 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972420210818-3Excavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting972420210818-3Excavator - 30 ton- After Jan 1091246.05INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9724 | 20210818-3 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 0 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2021-08-19 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972420210818-3Excavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting972420210818-3Excavator - 30 ton- After Jan 1091246.05INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9724 | 20210818-3 | 53511012 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 9 | Dynamic | 0 | 0 |  |  | 1183.32 | 153.8316 | 1337.1516 | 2021-08-19 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972420210818-3Dozer D6 or equal- After Jan 1091183.32 | Corbiere and Sons Contracting972420210818-3Dozer D6 or equal- After Jan 1091183.32INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9723 | 20210817-3 | 53511012 | Access | 0 | Labourer - General - After Jan 10 | 60 | 11 | HR |  |  | 0 | 0 | 660 | 85.8 | 745.8 | 2021-08-17 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972320210817-3Labourer - General - After Jan 1011660 | Corbiere and Sons Contracting972320210817-3Labourer - General - After Jan 1011660INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9723 | 20210817-3 | 53511012 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 143 | HR |  |  | 0 | 0 | 10725 | 1394.25 | 12119.25 | 2021-08-17 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972320210817-3Operator - Principle - After Jan 1014310725 | Corbiere and Sons Contracting972320210817-3Operator - Principle - After Jan 1014310725INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9723 | 20210817-3 | 53511012 | Access | 0 | L.O.A. | 210 | 15 | DAY |  |  | 0 | 0 | 3150 | 409.5 | 3559.5 | 2021-08-17 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972320210817-3L.O.A.153150 | Corbiere and Sons Contracting972320210817-3L.O.A.153150INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9723 | 20210817-3 | 53511012 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 0 | 0 | 1140 | 148.2 | 1288.2 | 2021-08-17 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972320210817-3Foreman121140 | Corbiere and Sons Contracting972320210817-3Foreman121140INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9723 | 20210817-3 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 9 | Dynamic | 103.54 | 0 |  |  | 1242.45 | 161.5185 | 1403.9685 | 2021-08-17 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972320210817-3Rock Truck - 30 Ton- After Jan 1091242.45 | Corbiere and Sons Contracting972320210817-3Rock Truck - 30 Ton- After Jan 1091242.45INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9723 | 20210817-3 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 9 | Dynamic | 0 | 0 |  |  | 1242.45 | 161.5185 | 1403.9685 | 2021-08-17 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972320210817-3Rock Truck - 30 Ton- After Jan 1091242.45 | Corbiere and Sons Contracting972320210817-3Rock Truck - 30 Ton- After Jan 1091242.45INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9723 | 20210817-3 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 18 | Dynamic | 0 | 0 |  |  | 2484.9 | 323.037 | 2807.937 | 2021-08-17 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972320210817-3Rock Truck - 30 Ton- After Jan 10182484.9 | Corbiere and Sons Contracting972320210817-3Rock Truck - 30 Ton- After Jan 10182484.9INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9723 | 20210817-3 | 53511012 | Access | 0 | Marooka- After Jan 10 | 144.6 | 5 | Dynamic | 108.45 | 0 |  |  | 723 | 93.99 | 816.99 | 2021-08-17 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972320210817-3Marooka- After Jan 105723 | Corbiere and Sons Contracting972320210817-3Marooka- After Jan 105723INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9723 | 20210817-3 | 53511012 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 7 | DAY | 182.81 | 0 |  |  | 1706.25 | 221.8125 | 1928.0625 | 2021-08-17 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972320210817-3Light Truck - Pick up- After Jan 1071706.25 | Corbiere and Sons Contracting972320210817-3Light Truck - Pick up- After Jan 1071706.25INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9723 | 20210817-3 | 53511012 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-08-17 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972320210817-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting972320210817-3Light Truck - Pick up- After Jan 101243.75INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9723 | 20210817-3 | 53511012 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-08-17 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972320210817-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting972320210817-3Light Truck - Pick up- After Jan 101243.75INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9723 | 20210817-3 | 53511012 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 9 | HR | 47.54 | 0 |  |  | 570.42 | 74.1546 | 644.5746 | 2021-08-17 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972320210817-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42 | Corbiere and Sons Contracting972320210817-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9723 | 20210817-3 | 53511012 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 9 | HR | 0 | 0 |  |  | 570.42 | 74.1546 | 644.5746 | 2021-08-17 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972320210817-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42 | Corbiere and Sons Contracting972320210817-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9723 | 20210817-3 | 53511012 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 9 | HR | 47.54 | 0 |  |  | 570.42 | 74.1546 | 644.5746 | 2021-08-17 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972320210817-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42 | Corbiere and Sons Contracting972320210817-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9723 | 20210817-3 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-08-17 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972320210817-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting972320210817-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9723 | 20210817-3 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 0 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-08-17 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972320210817-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting972320210817-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9723 | 20210817-3 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 0 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-08-17 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972320210817-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting972320210817-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9723 | 20210817-3 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 0 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-08-17 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972320210817-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting972320210817-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9723 | 20210817-3 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-08-17 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972320210817-3Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting972320210817-3Excavator - 36 ton- After Jan 1091322.64INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9723 | 20210817-3 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-08-17 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972320210817-3Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting972320210817-3Excavator - 36 ton- After Jan 1091322.64INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9723 | 20210817-3 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 0 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-08-17 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972320210817-3Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting972320210817-3Excavator - 36 ton- After Jan 1091322.64INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9723 | 20210817-3 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 103.84 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2021-08-17 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972320210817-3Excavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting972320210817-3Excavator - 30 ton- After Jan 1091246.05INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9723 | 20210817-3 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 103.84 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2021-08-17 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972320210817-3Excavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting972320210817-3Excavator - 30 ton- After Jan 1091246.05INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9723 | 20210817-3 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 0 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2021-08-17 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972320210817-3Excavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting972320210817-3Excavator - 30 ton- After Jan 1091246.05INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9723 | 20210817-3 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 0 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2021-08-17 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972320210817-3Excavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting972320210817-3Excavator - 30 ton- After Jan 1091246.05INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9723 | 20210817-3 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 0 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2021-08-17 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972320210817-3Excavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting972320210817-3Excavator - 30 ton- After Jan 1091246.05INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9723 | 20210817-3 | 53511012 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 9 | Dynamic | 0 | 0 |  |  | 1183.32 | 153.8316 | 1337.1516 | 2021-08-17 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972320210817-3Dozer D6 or equal- After Jan 1091183.32 | Corbiere and Sons Contracting972320210817-3Dozer D6 or equal- After Jan 1091183.32INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9722 | 20210816-3 | 53511012 | Access | 0 | Labourer - General - After Jan 10 | 60 | 11 | HR |  |  | 60 | 0 | 660 | 85.8 | 745.8 | 2021-08-16 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972220210816-3Labourer - General - After Jan 1011660 | Corbiere and Sons Contracting972220210816-3Labourer - General - After Jan 1011660INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9722 | 20210816-3 | 53511012 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 143 | HR |  |  | 75 | 0 | 10725 | 1394.25 | 12119.25 | 2021-08-16 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972220210816-3Operator - Principle - After Jan 1014310725 | Corbiere and Sons Contracting972220210816-3Operator - Principle - After Jan 1014310725INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9722 | 20210816-3 | 53511012 | Access | 0 | L.O.A. | 210 | 16 | DAY |  |  |  | 0 | 3360 | 436.8 | 3796.8 | 2021-08-16 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972220210816-3L.O.A.163360 | Corbiere and Sons Contracting972220210816-3L.O.A.163360INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9722 | 20210816-3 | 53511012 | Access | 0 | Foreman | 95 | 24 | HR |  |  | 95 | 0 | 2280 | 296.4 | 2576.4 | 2021-08-16 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972220210816-3Foreman242280 | Corbiere and Sons Contracting972220210816-3Foreman242280INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9722 | 20210816-3 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 9 | Dynamic | 103.54 | 0 |  |  | 1242.45 | 161.5185 | 1403.9685 | 2021-08-16 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972220210816-3Rock Truck - 30 Ton- After Jan 1091242.45 | Corbiere and Sons Contracting972220210816-3Rock Truck - 30 Ton- After Jan 1091242.45INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9722 | 20210816-3 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 9 | Dynamic | 103.54 | 0 |  |  | 1242.45 | 161.5185 | 1403.9685 | 2021-08-16 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972220210816-3Rock Truck - 30 Ton- After Jan 1091242.45 | Corbiere and Sons Contracting972220210816-3Rock Truck - 30 Ton- After Jan 1091242.45INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9722 | 20210816-3 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 9 | Dynamic | 103.54 | 0 |  |  | 1242.45 | 161.5185 | 1403.9685 | 2021-08-16 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972220210816-3Rock Truck - 30 Ton- After Jan 1091242.45 | Corbiere and Sons Contracting972220210816-3Rock Truck - 30 Ton- After Jan 1091242.45INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9722 | 20210816-3 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 18 | Dynamic | 103.54 | 0 |  |  | 2484.9 | 323.037 | 2807.937 | 2021-08-16 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972220210816-3Rock Truck - 30 Ton- After Jan 10182484.9 | Corbiere and Sons Contracting972220210816-3Rock Truck - 30 Ton- After Jan 10182484.9INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9722 | 20210816-3 | 53511012 | Access | 0 | Marooka- After Jan 10 | 144.6 | 5 | Dynamic | 108.45 | 0 |  |  | 723 | 93.99 | 816.99 | 2021-08-16 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972220210816-3Marooka- After Jan 105723 | Corbiere and Sons Contracting972220210816-3Marooka- After Jan 105723INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9722 | 20210816-3 | 53511012 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 7 | DAY | 182.81 | 0 |  |  | 1706.25 | 221.8125 | 1928.0625 | 2021-08-16 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972220210816-3Light Truck - Pick up- After Jan 1071706.25 | Corbiere and Sons Contracting972220210816-3Light Truck - Pick up- After Jan 1071706.25INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9722 | 20210816-3 | 53511012 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-08-16 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972220210816-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting972220210816-3Light Truck - Pick up- After Jan 101243.75INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9722 | 20210816-3 | 53511012 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-08-16 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972220210816-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting972220210816-3Light Truck - Pick up- After Jan 101243.75INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9722 | 20210816-3 | 53511012 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 9 | HR | 47.54 | 0 |  |  | 570.42 | 74.1546 | 644.5746 | 2021-08-16 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972220210816-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42 | Corbiere and Sons Contracting972220210816-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9722 | 20210816-3 | 53511012 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 9 | HR | 47.54 | 0 |  |  | 570.42 | 74.1546 | 644.5746 | 2021-08-16 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972220210816-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42 | Corbiere and Sons Contracting972220210816-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9722 | 20210816-3 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-08-16 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972220210816-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting972220210816-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9722 | 20210816-3 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-08-16 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972220210816-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting972220210816-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9722 | 20210816-3 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-08-16 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972220210816-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting972220210816-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9722 | 20210816-3 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-08-16 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972220210816-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting972220210816-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9722 | 20210816-3 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-08-16 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972220210816-3Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting972220210816-3Excavator - 36 ton- After Jan 1091322.64INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9722 | 20210816-3 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-08-16 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972220210816-3Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting972220210816-3Excavator - 36 ton- After Jan 1091322.64INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9722 | 20210816-3 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-08-16 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972220210816-3Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting972220210816-3Excavator - 36 ton- After Jan 1091322.64INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9722 | 20210816-3 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 103.84 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2021-08-16 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972220210816-3Excavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting972220210816-3Excavator - 30 ton- After Jan 1091246.05INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9722 | 20210816-3 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 103.84 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2021-08-16 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972220210816-3Excavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting972220210816-3Excavator - 30 ton- After Jan 1091246.05INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9722 | 20210816-3 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 103.84 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2021-08-16 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972220210816-3Excavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting972220210816-3Excavator - 30 ton- After Jan 1091246.05INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9722 | 20210816-3 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 103.84 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2021-08-16 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972220210816-3Excavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting972220210816-3Excavator - 30 ton- After Jan 1091246.05INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9722 | 20210816-3 | 53511012 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 9 | Dynamic | 98.61 | 0 |  |  | 1183.32 | 153.8316 | 1337.1516 | 2021-08-16 | 0 | INV #144 | 2021-09-07 | 160 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM19, KM27, KM30, KM35 and KM46 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-24 |  | 57 | 2021-08-24 | [6 empty] | 10 | Corbiere and Sons Contracting972220210816-3Dozer D6 or equal- After Jan 1091183.32 | Corbiere and Sons Contracting972220210816-3Dozer D6 or equal- After Jan 1091183.32INV #144 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9830 | 20210909-5 | 53511012 | Access | 0 | Labourer - General - After Jan 10 | 60 | 11 | HR |  |  | 60 | 0 | 660 | 85.8 | 745.8 | 2021-09-09 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Continue cleanup of Paint Lake 2 and walk out 300 from KM25 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-15 |  | 57 | 2021-09-15 | [6 empty] | 10 | Corbiere and Sons Contracting983020210909-5Labourer - General - After Jan 1011660 | Corbiere and Sons Contracting983020210909-5Labourer - General - After Jan 1011660INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9830 | 20210909-5 | 53511012 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-09-09 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Continue cleanup of Paint Lake 2 and walk out 300 from KM25 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-15 |  | 57 | 2021-09-15 | [6 empty] | 10 | Corbiere and Sons Contracting983020210909-5L.O.A.1210 | Corbiere and Sons Contracting983020210909-5L.O.A.1210INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9830 | 20210909-5 | 53511012 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-09-09 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Continue cleanup of Paint Lake 2 and walk out 300 from KM25 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-15 |  | 57 | 2021-09-15 | [6 empty] | 10 | Corbiere and Sons Contracting983020210909-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting983020210909-5Light Truck - Pick up- After Jan 101243.75INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9830 | 20210909-5 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 5 | HR | 9.16 | 0 |  |  | 61.05 | 7.9365 | 68.9865 | 2021-09-09 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Continue cleanup of Paint Lake 2 and walk out 300 from KM25 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-15 |  | 57 | 2021-09-15 | [6 empty] | 10 | Corbiere and Sons Contracting983020210909-5Excavator Thumb - 30 - 50 ton- After Jan 10561.05 | Corbiere and Sons Contracting983020210909-5Excavator Thumb - 30 - 50 ton- After Jan 10561.05INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9830 | 20210909-5 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 5 | Dynamic | 103.84 | 0 |  |  | 692.25 | 89.9925 | 782.2425 | 2021-09-09 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Continue cleanup of Paint Lake 2 and walk out 300 from KM25 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-15 |  | 57 | 2021-09-15 | [6 empty] | 10 | Corbiere and Sons Contracting983020210909-5Excavator - 30 ton- After Jan 105692.25 | Corbiere and Sons Contracting983020210909-5Excavator - 30 ton- After Jan 105692.25INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9812 | 20210908-5 | 53511012 | Access | 0 | Labourer - General - After Jan 10 | 60 | 11 | HR |  |  | 60 | 0 | 660 | 85.8 | 745.8 | 2021-09-08 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Cleanup of laydown and area - Orientation and float of AG Chapman RT - Demob of Corbiere RT | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-11 |  | 57 | 2021-09-15 | [6 empty] | 10 | Corbiere and Sons Contracting981220210908-5Labourer - General - After Jan 1011660 | Corbiere and Sons Contracting981220210908-5Labourer - General - After Jan 1011660INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9812 | 20210908-5 | 53511012 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 19 | HR |  |  | 70 | 0 | 1330 | 172.9 | 1502.9 | 2021-09-08 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Cleanup of laydown and area - Orientation and float of AG Chapman RT - Demob of Corbiere RT | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-11 |  | 57 | 2021-09-15 | [6 empty] | 10 | Corbiere and Sons Contracting981220210908-5Driver - AZ - After Jan 10191330 | Corbiere and Sons Contracting981220210908-5Driver - AZ - After Jan 10191330INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9812 | 20210908-5 | 53511012 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5 | HR |  |  | 75 | 0 | 375 | 48.75 | 423.75 | 2021-09-08 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Cleanup of laydown and area - Orientation and float of AG Chapman RT - Demob of Corbiere RT | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-11 |  | 57 | 2021-09-15 | [6 empty] | 10 | Corbiere and Sons Contracting981220210908-5Operator - Principle - After Jan 105375 | Corbiere and Sons Contracting981220210908-5Operator - Principle - After Jan 105375INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9812 | 20210908-5 | 53511012 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-09-08 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Cleanup of laydown and area - Orientation and float of AG Chapman RT - Demob of Corbiere RT | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-11 |  | 57 | 2021-09-15 | [6 empty] | 10 | Corbiere and Sons Contracting981220210908-5L.O.A.3630 | Corbiere and Sons Contracting981220210908-5L.O.A.3630INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9812 | 20210908-5 | 53511012 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 8 | Dynamic | 91.79 | 0 |  |  | 979.12 | 127.2856 | 1106.4056 | 2021-09-08 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Cleanup of laydown and area - Orientation and float of AG Chapman RT - Demob of Corbiere RT | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-11 |  | 57 | 2021-09-15 | [6 empty] | 10 | Corbiere and Sons Contracting981220210908-5Tractor Trailer - 60 Ton- After Jan 108979.12 | Corbiere and Sons Contracting981220210908-5Tractor Trailer - 60 Ton- After Jan 108979.12INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9812 | 20210908-5 | 53511012 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 11 | Dynamic | 91.79 | 0 |  |  | 1346.29 | 175.0177 | 1521.3077 | 2021-09-08 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Cleanup of laydown and area - Orientation and float of AG Chapman RT - Demob of Corbiere RT | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-11 |  | 57 | 2021-09-15 | [6 empty] | 10 | Corbiere and Sons Contracting981220210908-5Tractor Trailer - 60 Ton- After Jan 10111346.29 | Corbiere and Sons Contracting981220210908-5Tractor Trailer - 60 Ton- After Jan 10111346.29INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9812 | 20210908-5 | 53511012 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-09-08 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Cleanup of laydown and area - Orientation and float of AG Chapman RT - Demob of Corbiere RT | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-11 |  | 57 | 2021-09-15 | [6 empty] | 10 | Corbiere and Sons Contracting981220210908-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting981220210908-5Light Truck - Pick up- After Jan 101243.75INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9821 | 20210907-5 | 53511012 | Access | 0 | Labourer - General - After Jan 10 | 60 | 11 | HR |  |  | 60 | 0 | 660 | 85.8 | 745.8 | 2021-09-07 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Cleaning up and demob of equipment - Ex (was actually RT) delivered to Neys | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-11 |  | 57 | 2021-09-15 | [6 empty] | 10 | Corbiere and Sons Contracting982120210907-5Labourer - General - After Jan 1011660 | Corbiere and Sons Contracting982120210907-5Labourer - General - After Jan 1011660INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9821 | 20210907-5 | 53511012 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 10 | HR |  |  | 70 | 0 | 700 | 91 | 791 | 2021-09-07 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Cleaning up and demob of equipment - Ex (was actually RT) delivered to Neys | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-11 |  | 57 | 2021-09-15 | [6 empty] | 10 | Corbiere and Sons Contracting982120210907-5Driver - AZ - After Jan 1010700 | Corbiere and Sons Contracting982120210907-5Driver - AZ - After Jan 1010700INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9821 | 20210907-5 | 53511012 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-09-07 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Cleaning up and demob of equipment - Ex (was actually RT) delivered to Neys | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-11 |  | 57 | 2021-09-15 | [6 empty] | 10 | Corbiere and Sons Contracting982120210907-5Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting982120210907-5Operator - Principle - After Jan 1011825INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9821 | 20210907-5 | 53511012 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2021-09-07 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Cleaning up and demob of equipment - Ex (was actually RT) delivered to Neys | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-11 |  | 57 | 2021-09-15 | [6 empty] | 10 | Corbiere and Sons Contracting982120210907-5L.O.A.4840 | Corbiere and Sons Contracting982120210907-5L.O.A.4840INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9821 | 20210907-5 | 53511012 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-09-07 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Cleaning up and demob of equipment - Ex (was actually RT) delivered to Neys | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-11 |  | 57 | 2021-09-15 | [6 empty] | 10 | Corbiere and Sons Contracting982120210907-5Foreman121140 | Corbiere and Sons Contracting982120210907-5Foreman121140INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9821 | 20210907-5 | 53511012 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 10 | Dynamic | 91.79 | 0 |  |  | 1223.9 | 159.107 | 1383.007 | 2021-09-07 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Cleaning up and demob of equipment - Ex (was actually RT) delivered to Neys | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-11 |  | 57 | 2021-09-15 | [6 empty] | 10 | Corbiere and Sons Contracting982120210907-5Tractor Trailer - 60 Ton- After Jan 10101223.9 | Corbiere and Sons Contracting982120210907-5Tractor Trailer - 60 Ton- After Jan 10101223.9INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9821 | 20210907-5 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 5 | Dynamic | 103.54 | 0 |  |  | 690.25 | 89.7325 | 779.9825 | 2021-09-07 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Cleaning up and demob of equipment - Ex (was actually RT) delivered to Neys | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-11 |  | 57 | 2021-09-15 | [6 empty] | 10 | Corbiere and Sons Contracting982120210907-5Rock Truck - 30 Ton- After Jan 105690.25 | Corbiere and Sons Contracting982120210907-5Rock Truck - 30 Ton- After Jan 105690.25INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9821 | 20210907-5 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 5 | Dynamic | 103.54 | 0 |  |  | 690.25 | 89.7325 | 779.9825 | 2021-09-07 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Cleaning up and demob of equipment - Ex (was actually RT) delivered to Neys | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-11 |  | 57 | 2021-09-15 | [6 empty] | 10 | Corbiere and Sons Contracting982120210907-5Rock Truck - 30 Ton- After Jan 105690.25 | Corbiere and Sons Contracting982120210907-5Rock Truck - 30 Ton- After Jan 105690.25INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9821 | 20210907-5 | 53511012 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-09-07 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Cleaning up and demob of equipment - Ex (was actually RT) delivered to Neys | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-11 |  | 57 | 2021-09-15 | [6 empty] | 10 | Corbiere and Sons Contracting982120210907-5Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting982120210907-5Light Truck - Pick up- After Jan 102487.5INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9821 | 20210907-5 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 5 | HR | 9.16 | 0 |  |  | 61.05 | 7.9365 | 68.9865 | 2021-09-07 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Cleaning up and demob of equipment - Ex (was actually RT) delivered to Neys | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-11 |  | 57 | 2021-09-15 | [6 empty] | 10 | Corbiere and Sons Contracting982120210907-5Excavator Thumb - 30 - 50 ton- After Jan 10561.05 | Corbiere and Sons Contracting982120210907-5Excavator Thumb - 30 - 50 ton- After Jan 10561.05INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9821 | 20210907-5 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 5 | Dynamic | 103.84 | 0 |  |  | 692.25 | 89.9925 | 782.2425 | 2021-09-07 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Cleaning up and demob of equipment - Ex (was actually RT) delivered to Neys | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-11 |  | 57 | 2021-09-15 | [6 empty] | 10 | Corbiere and Sons Contracting982120210907-5Excavator - 30 ton- After Jan 105692.25 | Corbiere and Sons Contracting982120210907-5Excavator - 30 ton- After Jan 105692.25INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9819 | 20210906-4 | 53511012 | Access | 0 | Labourer - General - After Jan 10 | 60 | 11 | HR |  |  | 0 | 0 | 660 | 85.8 | 745.8 | 2021-09-06 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Crews walking out of Paint Lake 2 and touching road up on way out - Fuel Buggy demobbed - RT Ops returning Tuesday | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-11 |  | 57 | 2021-09-15 | [6 empty] | 10 | Corbiere and Sons Contracting981920210906-4Labourer - General - After Jan 1011660 | Corbiere and Sons Contracting981920210906-4Labourer - General - After Jan 1011660INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9819 | 20210906-4 | 53511012 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 10 | HR |  |  | 70 | 0 | 700 | 91 | 791 | 2021-09-06 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Crews walking out of Paint Lake 2 and touching road up on way out - Fuel Buggy demobbed - RT Ops returning Tuesday | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-11 |  | 57 | 2021-09-15 | [6 empty] | 10 | Corbiere and Sons Contracting981920210906-4Driver - AZ - After Jan 1010700 | Corbiere and Sons Contracting981920210906-4Driver - AZ - After Jan 1010700INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9819 | 20210906-4 | 53511012 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 25 | HR |  |  | 0 | 0 | 1875 | 243.75 | 2118.75 | 2021-09-06 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Crews walking out of Paint Lake 2 and touching road up on way out - Fuel Buggy demobbed - RT Ops returning Tuesday | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-11 |  | 57 | 2021-09-15 | [6 empty] | 10 | Corbiere and Sons Contracting981920210906-4Operator - Principle - After Jan 10251875 | Corbiere and Sons Contracting981920210906-4Operator - Principle - After Jan 10251875INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9819 | 20210906-4 | 53511012 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 33 | HR |  |  | 0 | 0 | 2475 | 321.75 | 2796.75 | 2021-09-06 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Crews walking out of Paint Lake 2 and touching road up on way out - Fuel Buggy demobbed - RT Ops returning Tuesday | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-11 |  | 57 | 2021-09-15 | [6 empty] | 10 | Corbiere and Sons Contracting981920210906-4Operator - Principle - After Jan 10332475 | Corbiere and Sons Contracting981920210906-4Operator - Principle - After Jan 10332475INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9819 | 20210906-4 | 53511012 | Access | 0 | L.O.A. | 210 | 11 | DAY |  |  | 0 | 0 | 2310 | 300.3 | 2610.3 | 2021-09-06 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Crews walking out of Paint Lake 2 and touching road up on way out - Fuel Buggy demobbed - RT Ops returning Tuesday | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-11 |  | 57 | 2021-09-15 | [6 empty] | 10 | Corbiere and Sons Contracting981920210906-4L.O.A.112310 | Corbiere and Sons Contracting981920210906-4L.O.A.112310INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9819 | 20210906-4 | 53511012 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 0 | 0 | 1140 | 148.2 | 1288.2 | 2021-09-06 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Crews walking out of Paint Lake 2 and touching road up on way out - Fuel Buggy demobbed - RT Ops returning Tuesday | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-11 |  | 57 | 2021-09-15 | [6 empty] | 10 | Corbiere and Sons Contracting981920210906-4Foreman121140 | Corbiere and Sons Contracting981920210906-4Foreman121140INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9819 | 20210906-4 | 53511012 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 10 | Dynamic | 91.79 | 0 |  |  | 1223.9 | 159.107 | 1383.007 | 2021-09-06 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Crews walking out of Paint Lake 2 and touching road up on way out - Fuel Buggy demobbed - RT Ops returning Tuesday | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-11 |  | 57 | 2021-09-15 | [6 empty] | 10 | Corbiere and Sons Contracting981920210906-4Tractor Trailer - 60 Ton- After Jan 10101223.9 | Corbiere and Sons Contracting981920210906-4Tractor Trailer - 60 Ton- After Jan 10101223.9INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9819 | 20210906-4 | 53511012 | Access | 0 | Marooka- After Jan 10 | 144.6 | 5 | Dynamic | 0 | 0 |  |  | 723 | 93.99 | 816.99 | 2021-09-06 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Crews walking out of Paint Lake 2 and touching road up on way out - Fuel Buggy demobbed - RT Ops returning Tuesday | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-11 |  | 57 | 2021-09-15 | [6 empty] | 10 | Corbiere and Sons Contracting981920210906-4Marooka- After Jan 105723 | Corbiere and Sons Contracting981920210906-4Marooka- After Jan 105723INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9819 | 20210906-4 | 53511012 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 0 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2021-09-06 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Crews walking out of Paint Lake 2 and touching road up on way out - Fuel Buggy demobbed - RT Ops returning Tuesday | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-11 |  | 57 | 2021-09-15 | [6 empty] | 10 | Corbiere and Sons Contracting981920210906-4Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting981920210906-4Light Truck - Pick up- After Jan 103731.25INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9819 | 20210906-4 | 53511012 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 9 | HR | 0 | 0 |  |  | 570.42 | 74.1546 | 644.5746 | 2021-09-06 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Crews walking out of Paint Lake 2 and touching road up on way out - Fuel Buggy demobbed - RT Ops returning Tuesday | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-11 |  | 57 | 2021-09-15 | [6 empty] | 10 | Corbiere and Sons Contracting981920210906-4Excavator Hammer - 30 - 50 ton- After Jan 109570.42 | Corbiere and Sons Contracting981920210906-4Excavator Hammer - 30 - 50 ton- After Jan 109570.42INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9819 | 20210906-4 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-09-06 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Crews walking out of Paint Lake 2 and touching road up on way out - Fuel Buggy demobbed - RT Ops returning Tuesday | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-11 |  | 57 | 2021-09-15 | [6 empty] | 10 | Corbiere and Sons Contracting981920210906-4Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting981920210906-4Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9819 | 20210906-4 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 0 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-09-06 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Crews walking out of Paint Lake 2 and touching road up on way out - Fuel Buggy demobbed - RT Ops returning Tuesday | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-11 |  | 57 | 2021-09-15 | [6 empty] | 10 | Corbiere and Sons Contracting981920210906-4Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting981920210906-4Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9819 | 20210906-4 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 0 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-09-06 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Crews walking out of Paint Lake 2 and touching road up on way out - Fuel Buggy demobbed - RT Ops returning Tuesday | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-11 |  | 57 | 2021-09-15 | [6 empty] | 10 | Corbiere and Sons Contracting981920210906-4Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting981920210906-4Excavator - 36 ton- After Jan 1091322.64INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9819 | 20210906-4 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 0 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-09-06 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Crews walking out of Paint Lake 2 and touching road up on way out - Fuel Buggy demobbed - RT Ops returning Tuesday | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-11 |  | 57 | 2021-09-15 | [6 empty] | 10 | Corbiere and Sons Contracting981920210906-4Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting981920210906-4Excavator - 36 ton- After Jan 1091322.64INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9819 | 20210906-4 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 0 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2021-09-06 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Crews walking out of Paint Lake 2 and touching road up on way out - Fuel Buggy demobbed - RT Ops returning Tuesday | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-11 |  | 57 | 2021-09-15 | [6 empty] | 10 | Corbiere and Sons Contracting981920210906-4Excavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting981920210906-4Excavator - 30 ton- After Jan 1091246.05INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9818 | 20210905-4 | 53511012 | Access | 0 | Labourer - General - After Jan 10 | 60 | 11 | HR |  |  | 60 | 0 | 660 | 85.8 | 745.8 | 2021-09-05 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 - OP's for RT's waiting for restart | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-11 |  | 57 | 2021-09-15 | [6 empty] | 10 | Corbiere and Sons Contracting981820210905-4Labourer - General - After Jan 1011660 | Corbiere and Sons Contracting981820210905-4Labourer - General - After Jan 1011660INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9818 | 20210905-4 | 53511012 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 25 | HR |  |  | 75 | 0 | 1875 | 243.75 | 2118.75 | 2021-09-05 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 - OP's for RT's waiting for restart | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-11 |  | 57 | 2021-09-15 | [6 empty] | 10 | Corbiere and Sons Contracting981820210905-4Operator - Principle - After Jan 10251875 | Corbiere and Sons Contracting981820210905-4Operator - Principle - After Jan 10251875INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9818 | 20210905-4 | 53511012 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 33 | HR |  |  | 75 | 0 | 2475 | 321.75 | 2796.75 | 2021-09-05 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 - OP's for RT's waiting for restart | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-11 |  | 57 | 2021-09-15 | [6 empty] | 10 | Corbiere and Sons Contracting981820210905-4Operator - Principle - After Jan 10332475 | Corbiere and Sons Contracting981820210905-4Operator - Principle - After Jan 10332475INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9818 | 20210905-4 | 53511012 | Access | 0 | L.O.A. | 210 | 10 | DAY |  |  |  | 0 | 2100 | 273 | 2373 | 2021-09-05 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 - OP's for RT's waiting for restart | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-11 |  | 57 | 2021-09-15 | [6 empty] | 10 | Corbiere and Sons Contracting981820210905-4L.O.A.102100 | Corbiere and Sons Contracting981820210905-4L.O.A.102100INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9818 | 20210905-4 | 53511012 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-09-05 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 - OP's for RT's waiting for restart | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-11 |  | 57 | 2021-09-15 | [6 empty] | 10 | Corbiere and Sons Contracting981820210905-4Foreman121140 | Corbiere and Sons Contracting981820210905-4Foreman121140INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9818 | 20210905-4 | 53511012 | Access | 0 | Marooka- After Jan 10 | 144.6 | 5 | Dynamic | 108.45 | 0 |  |  | 723 | 93.99 | 816.99 | 2021-09-05 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 - OP's for RT's waiting for restart | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-11 |  | 57 | 2021-09-15 | [6 empty] | 10 | Corbiere and Sons Contracting981820210905-4Marooka- After Jan 105723 | Corbiere and Sons Contracting981820210905-4Marooka- After Jan 105723INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9818 | 20210905-4 | 53511012 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2021-09-05 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 - OP's for RT's waiting for restart | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-11 |  | 57 | 2021-09-15 | [6 empty] | 10 | Corbiere and Sons Contracting981820210905-4Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting981820210905-4Light Truck - Pick up- After Jan 103731.25INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9818 | 20210905-4 | 53511012 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 9 | HR | 47.54 | 0 |  |  | 570.42 | 74.1546 | 644.5746 | 2021-09-05 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 - OP's for RT's waiting for restart | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-11 |  | 57 | 2021-09-15 | [6 empty] | 10 | Corbiere and Sons Contracting981820210905-4Excavator Hammer - 30 - 50 ton- After Jan 109570.42 | Corbiere and Sons Contracting981820210905-4Excavator Hammer - 30 - 50 ton- After Jan 109570.42INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9818 | 20210905-4 | 53511012 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 9 | HR | 47.54 | 0 |  |  | 570.42 | 74.1546 | 644.5746 | 2021-09-05 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 - OP's for RT's waiting for restart | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-11 |  | 57 | 2021-09-15 | [6 empty] | 10 | Corbiere and Sons Contracting981820210905-4Excavator Hammer - 30 - 50 ton- After Jan 109570.42 | Corbiere and Sons Contracting981820210905-4Excavator Hammer - 30 - 50 ton- After Jan 109570.42INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9818 | 20210905-4 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-09-05 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 - OP's for RT's waiting for restart | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-11 |  | 57 | 2021-09-15 | [6 empty] | 10 | Corbiere and Sons Contracting981820210905-4Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting981820210905-4Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9818 | 20210905-4 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-09-05 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 - OP's for RT's waiting for restart | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-11 |  | 57 | 2021-09-15 | [6 empty] | 10 | Corbiere and Sons Contracting981820210905-4Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting981820210905-4Excavator - 36 ton- After Jan 1091322.64INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9818 | 20210905-4 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-09-05 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 - OP's for RT's waiting for restart | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-11 |  | 57 | 2021-09-15 | [6 empty] | 10 | Corbiere and Sons Contracting981820210905-4Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting981820210905-4Excavator - 36 ton- After Jan 1091322.64INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9818 | 20210905-4 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 103.84 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2021-09-05 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 - OP's for RT's waiting for restart | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-11 |  | 57 | 2021-09-15 | [6 empty] | 10 | Corbiere and Sons Contracting981820210905-4Excavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting981820210905-4Excavator - 30 ton- After Jan 1091246.05INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9794 | 20210904-3 | 53511012 | Access | 0 | Labourer - General - After Jan 10 | 60 | 11 | HR |  |  | 60 | 0 | 660 | 85.8 | 745.8 | 2021-09-04 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 - RT's shutdown early due to road conditions | 6 |  | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979420210904-3Labourer - General - After Jan 1011660 | Corbiere and Sons Contracting979420210904-3Labourer - General - After Jan 1011660INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9794 | 20210904-3 | 53511012 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 25 | HR |  |  | 75 | 0 | 1875 | 243.75 | 2118.75 | 2021-09-04 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 - RT's shutdown early due to road conditions | 6 |  | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979420210904-3Operator - Principle - After Jan 10251875 | Corbiere and Sons Contracting979420210904-3Operator - Principle - After Jan 10251875INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9794 | 20210904-3 | 53511012 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 33 | HR |  |  | 75 | 0 | 2475 | 321.75 | 2796.75 | 2021-09-04 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 - RT's shutdown early due to road conditions | 6 |  | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979420210904-3Operator - Principle - After Jan 10332475 | Corbiere and Sons Contracting979420210904-3Operator - Principle - After Jan 10332475INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9794 | 20210904-3 | 53511012 | Access | 0 | L.O.A. | 210 | 10 | DAY |  |  |  | 0 | 2100 | 273 | 2373 | 2021-09-04 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 - RT's shutdown early due to road conditions | 6 |  | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979420210904-3L.O.A.102100 | Corbiere and Sons Contracting979420210904-3L.O.A.102100INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9794 | 20210904-3 | 53511012 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-09-04 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 - RT's shutdown early due to road conditions | 6 |  | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979420210904-3Foreman121140 | Corbiere and Sons Contracting979420210904-3Foreman121140INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9794 | 20210904-3 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 20 | Dynamic | 103.54 | 0 |  |  | 2761 | 358.93 | 3119.93 | 2021-09-04 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 - RT's shutdown early due to road conditions | 6 |  | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979420210904-3Rock Truck - 30 Ton- After Jan 10202761 | Corbiere and Sons Contracting979420210904-3Rock Truck - 30 Ton- After Jan 10202761INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9794 | 20210904-3 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 5 | Dynamic | 103.54 | 0 |  |  | 690.25 | 89.7325 | 779.9825 | 2021-09-04 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 - RT's shutdown early due to road conditions | 6 |  | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979420210904-3Rock Truck - 30 Ton- After Jan 105690.25 | Corbiere and Sons Contracting979420210904-3Rock Truck - 30 Ton- After Jan 105690.25INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9794 | 20210904-3 | 53511012 | Access | 0 | Marooka- After Jan 10 | 144.6 | 5 | Dynamic | 108.45 | 0 |  |  | 723 | 93.99 | 816.99 | 2021-09-04 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 - RT's shutdown early due to road conditions | 6 |  | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979420210904-3Marooka- After Jan 105723 | Corbiere and Sons Contracting979420210904-3Marooka- After Jan 105723INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9794 | 20210904-3 | 53511012 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 6 | DAY | 182.81 | 0 |  |  | 1462.5 | 190.125 | 1652.625 | 2021-09-04 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 - RT's shutdown early due to road conditions | 6 |  | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979420210904-3Light Truck - Pick up- After Jan 1061462.5 | Corbiere and Sons Contracting979420210904-3Light Truck - Pick up- After Jan 1061462.5INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9794 | 20210904-3 | 53511012 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 9 | HR | 47.54 | 0 |  |  | 570.42 | 74.1546 | 644.5746 | 2021-09-04 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 - RT's shutdown early due to road conditions | 6 |  | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979420210904-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42 | Corbiere and Sons Contracting979420210904-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9794 | 20210904-3 | 53511012 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 9 | HR | 47.54 | 0 |  |  | 570.42 | 74.1546 | 644.5746 | 2021-09-04 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 - RT's shutdown early due to road conditions | 6 |  | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979420210904-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42 | Corbiere and Sons Contracting979420210904-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9794 | 20210904-3 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-09-04 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 - RT's shutdown early due to road conditions | 6 |  | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979420210904-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting979420210904-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9794 | 20210904-3 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-09-04 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 - RT's shutdown early due to road conditions | 6 |  | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979420210904-3Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting979420210904-3Excavator - 36 ton- After Jan 1091322.64INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9794 | 20210904-3 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-09-04 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 - RT's shutdown early due to road conditions | 6 |  | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979420210904-3Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting979420210904-3Excavator - 36 ton- After Jan 1091322.64INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9794 | 20210904-3 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 103.84 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2021-09-04 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 - RT's shutdown early due to road conditions | 6 |  | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979420210904-3Excavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting979420210904-3Excavator - 30 ton- After Jan 1091246.05INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9793 | 20210903-5 | 53511012 | Access | 0 | Labourer - General - After Jan 10 | 60 | 10 | HR |  |  | 60 | 0 | 600 | 78 | 678 | 2021-09-03 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F006-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979320210903-5Labourer - General - After Jan 1010600 | Corbiere and Sons Contracting979320210903-5Labourer - General - After Jan 1010600INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9793 | 20210903-5 | 53511012 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 80 | HR |  |  | 75 | 0 | 6000 | 780 | 6780 | 2021-09-03 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F006-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979320210903-5Operator - Principle - After Jan 10806000 | Corbiere and Sons Contracting979320210903-5Operator - Principle - After Jan 10806000INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9793 | 20210903-5 | 53511012 | Access | 0 | L.O.A. | 210 | 10 | DAY |  |  |  | 0 | 2100 | 273 | 2373 | 2021-09-03 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F006-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979320210903-5L.O.A.102100 | Corbiere and Sons Contracting979320210903-5L.O.A.102100INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9793 | 20210903-5 | 53511012 | Access | 0 | Foreman | 95 | 11 | HR |  |  | 95 | 0 | 1045 | 135.85 | 1180.85 | 2021-09-03 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F006-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979320210903-5Foreman111045 | Corbiere and Sons Contracting979320210903-5Foreman111045INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9793 | 20210903-5 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 16 | Dynamic | 103.54 | 0 |  |  | 2208.8 | 287.144 | 2495.944 | 2021-09-03 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F006-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979320210903-5Rock Truck - 30 Ton- After Jan 10162208.8 | Corbiere and Sons Contracting979320210903-5Rock Truck - 30 Ton- After Jan 10162208.8INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9793 | 20210903-5 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 8 | Dynamic | 103.54 | 0 |  |  | 1104.4 | 143.572 | 1247.972 | 2021-09-03 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F006-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979320210903-5Rock Truck - 30 Ton- After Jan 1081104.4 | Corbiere and Sons Contracting979320210903-5Rock Truck - 30 Ton- After Jan 1081104.4INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9793 | 20210903-5 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 8 | Dynamic | 103.54 | 0 |  |  | 1104.4 | 143.572 | 1247.972 | 2021-09-03 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F006-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979320210903-5Rock Truck - 30 Ton- After Jan 1081104.4 | Corbiere and Sons Contracting979320210903-5Rock Truck - 30 Ton- After Jan 1081104.4INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9793 | 20210903-5 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 8 | Dynamic | 103.54 | 0 |  |  | 1104.4 | 143.572 | 1247.972 | 2021-09-03 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F006-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979320210903-5Rock Truck - 30 Ton- After Jan 1081104.4 | Corbiere and Sons Contracting979320210903-5Rock Truck - 30 Ton- After Jan 1081104.4INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9793 | 20210903-5 | 53511012 | Access | 0 | Marooka- After Jan 10 | 144.6 | 5 | Dynamic | 108.45 | 0 |  |  | 723 | 93.99 | 816.99 | 2021-09-03 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F006-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979320210903-5Marooka- After Jan 105723 | Corbiere and Sons Contracting979320210903-5Marooka- After Jan 105723INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9793 | 20210903-5 | 53511012 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 7 | DAY | 182.81 | 0 |  |  | 1706.25 | 221.8125 | 1928.0625 | 2021-09-03 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F006-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979320210903-5Light Truck - Pick up- After Jan 1071706.25 | Corbiere and Sons Contracting979320210903-5Light Truck - Pick up- After Jan 1071706.25INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9793 | 20210903-5 | 53511012 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 8 | HR | 47.54 | 0 |  |  | 507.04 | 65.9152 | 572.9552 | 2021-09-03 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F006-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979320210903-5Excavator Hammer - 30 - 50 ton- After Jan 108507.04 | Corbiere and Sons Contracting979320210903-5Excavator Hammer - 30 - 50 ton- After Jan 108507.04INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9793 | 20210903-5 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 8 | HR | 9.16 | 0 |  |  | 97.68 | 12.6984 | 110.3784 | 2021-09-03 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F006-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979320210903-5Excavator Thumb - 30 - 50 ton- After Jan 10897.68 | Corbiere and Sons Contracting979320210903-5Excavator Thumb - 30 - 50 ton- After Jan 10897.68INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9793 | 20210903-5 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 8 | HR | 9.16 | 0 |  |  | 97.68 | 12.6984 | 110.3784 | 2021-09-03 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F006-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979320210903-5Excavator Thumb - 30 - 50 ton- After Jan 10897.68 | Corbiere and Sons Contracting979320210903-5Excavator Thumb - 30 - 50 ton- After Jan 10897.68INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9793 | 20210903-5 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 8 | Dynamic | 110.22 | 0 |  |  | 1175.68 | 152.8384 | 1328.5184 | 2021-09-03 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F006-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979320210903-5Excavator - 36 ton- After Jan 1081175.68 | Corbiere and Sons Contracting979320210903-5Excavator - 36 ton- After Jan 1081175.68INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9793 | 20210903-5 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 8 | Dynamic | 110.22 | 0 |  |  | 1175.68 | 152.8384 | 1328.5184 | 2021-09-03 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F006-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979320210903-5Excavator - 36 ton- After Jan 1081175.68 | Corbiere and Sons Contracting979320210903-5Excavator - 36 ton- After Jan 1081175.68INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9793 | 20210903-5 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 8 | Dynamic | 103.84 | 0 |  |  | 1107.6 | 143.988 | 1251.588 | 2021-09-03 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F006-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979320210903-5Excavator - 30 ton- After Jan 1081107.6 | Corbiere and Sons Contracting979320210903-5Excavator - 30 ton- After Jan 1081107.6INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9792 | 20210902-5 | 53511012 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 99 | HR |  |  | 75 | 0 | 7425 | 965.25 | 8390.25 | 2021-09-02 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979220210902-5Operator - Principle - After Jan 10997425 | Corbiere and Sons Contracting979220210902-5Operator - Principle - After Jan 10997425INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9792 | 20210902-5 | 53511012 | Access | 0 | L.O.A. | 210 | 10 | DAY |  |  |  | 0 | 2100 | 273 | 2373 | 2021-09-02 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979220210902-5L.O.A.102100 | Corbiere and Sons Contracting979220210902-5L.O.A.102100INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9792 | 20210902-5 | 53511012 | Access | 0 | Foreman | 95 | 11 | HR |  |  | 95 | 0 | 1045 | 135.85 | 1180.85 | 2021-09-02 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979220210902-5Foreman111045 | Corbiere and Sons Contracting979220210902-5Foreman111045INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9792 | 20210902-5 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 9 | Dynamic | 103.54 | 0 |  |  | 1242.45 | 161.5185 | 1403.9685 | 2021-09-02 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979220210902-5Rock Truck - 30 Ton- After Jan 1091242.45 | Corbiere and Sons Contracting979220210902-5Rock Truck - 30 Ton- After Jan 1091242.45INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9792 | 20210902-5 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 9 | Dynamic | 103.54 | 0 |  |  | 1242.45 | 161.5185 | 1403.9685 | 2021-09-02 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979220210902-5Rock Truck - 30 Ton- After Jan 1091242.45 | Corbiere and Sons Contracting979220210902-5Rock Truck - 30 Ton- After Jan 1091242.45INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9792 | 20210902-5 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 9 | Dynamic | 103.54 | 0 |  |  | 1242.45 | 161.5185 | 1403.9685 | 2021-09-02 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979220210902-5Rock Truck - 30 Ton- After Jan 1091242.45 | Corbiere and Sons Contracting979220210902-5Rock Truck - 30 Ton- After Jan 1091242.45INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9792 | 20210902-5 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 9 | Dynamic | 103.54 | 0 |  |  | 1242.45 | 161.5185 | 1403.9685 | 2021-09-02 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979220210902-5Rock Truck - 30 Ton- After Jan 1091242.45 | Corbiere and Sons Contracting979220210902-5Rock Truck - 30 Ton- After Jan 1091242.45INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9792 | 20210902-5 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 9 | Dynamic | 103.54 | 0 |  |  | 1242.45 | 161.5185 | 1403.9685 | 2021-09-02 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979220210902-5Rock Truck - 30 Ton- After Jan 1091242.45 | Corbiere and Sons Contracting979220210902-5Rock Truck - 30 Ton- After Jan 1091242.45INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9792 | 20210902-5 | 53511012 | Access | 0 | Marooka- After Jan 10 | 144.6 | 5 | Dynamic | 108.45 | 0 |  |  | 723 | 93.99 | 816.99 | 2021-09-02 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979220210902-5Marooka- After Jan 105723 | Corbiere and Sons Contracting979220210902-5Marooka- After Jan 105723INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9792 | 20210902-5 | 53511012 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 7 | DAY | 182.81 | 0 |  |  | 1706.25 | 221.8125 | 1928.0625 | 2021-09-02 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979220210902-5Light Truck - Pick up- After Jan 1071706.25 | Corbiere and Sons Contracting979220210902-5Light Truck - Pick up- After Jan 1071706.25INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9792 | 20210902-5 | 53511012 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 6 | HR | 47.54 | 0 |  |  | 380.28 | 49.4364 | 429.7164 | 2021-09-02 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979220210902-5Excavator Hammer - 30 - 50 ton- After Jan 106380.28 | Corbiere and Sons Contracting979220210902-5Excavator Hammer - 30 - 50 ton- After Jan 106380.28INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9792 | 20210902-5 | 53511012 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 9 | HR | 47.54 | 0 |  |  | 570.42 | 74.1546 | 644.5746 | 2021-09-02 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979220210902-5Excavator Hammer - 30 - 50 ton- After Jan 109570.42 | Corbiere and Sons Contracting979220210902-5Excavator Hammer - 30 - 50 ton- After Jan 109570.42INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9792 | 20210902-5 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-09-02 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979220210902-5Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting979220210902-5Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9792 | 20210902-5 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-09-02 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979220210902-5Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting979220210902-5Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9792 | 20210902-5 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 3 | Dynamic | 110.22 | 0 |  |  | 440.88 | 57.3144 | 498.1944 | 2021-09-02 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979220210902-5Excavator - 36 ton- After Jan 103440.88 | Corbiere and Sons Contracting979220210902-5Excavator - 36 ton- After Jan 103440.88INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9792 | 20210902-5 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-09-02 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979220210902-5Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting979220210902-5Excavator - 36 ton- After Jan 1091322.64INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9792 | 20210902-5 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-09-02 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979220210902-5Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting979220210902-5Excavator - 36 ton- After Jan 1091322.64INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9792 | 20210902-5 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 6 | Dynamic | 103.84 | 0 |  |  | 830.7 | 107.991 | 938.691 | 2021-09-02 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979220210902-5Excavator - 30 ton- After Jan 106830.7 | Corbiere and Sons Contracting979220210902-5Excavator - 30 ton- After Jan 106830.7INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9792 | 20210902-5 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 103.84 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2021-09-02 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979220210902-5Excavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting979220210902-5Excavator - 30 ton- After Jan 1091246.05INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9791 | 20210901-5 | 53511012 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 99 | HR |  |  | 75 | 0 | 7425 | 965.25 | 8390.25 | 2021-09-01 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979120210901-5Operator - Principle - After Jan 10997425 | Corbiere and Sons Contracting979120210901-5Operator - Principle - After Jan 10997425INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9791 | 20210901-5 | 53511012 | Access | 0 | L.O.A. | 210 | 10 | DAY |  |  |  | 0 | 2100 | 273 | 2373 | 2021-09-01 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979120210901-5L.O.A.102100 | Corbiere and Sons Contracting979120210901-5L.O.A.102100INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9791 | 20210901-5 | 53511012 | Access | 0 | Foreman | 95 | 11 | HR |  |  | 95 | 0 | 1045 | 135.85 | 1180.85 | 2021-09-01 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979120210901-5Foreman111045 | Corbiere and Sons Contracting979120210901-5Foreman111045INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9791 | 20210901-5 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 9 | Dynamic | 103.54 | 0 |  |  | 1242.45 | 161.5185 | 1403.9685 | 2021-09-01 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979120210901-5Rock Truck - 30 Ton- After Jan 1091242.45 | Corbiere and Sons Contracting979120210901-5Rock Truck - 30 Ton- After Jan 1091242.45INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9791 | 20210901-5 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 9 | Dynamic | 103.54 | 0 |  |  | 1242.45 | 161.5185 | 1403.9685 | 2021-09-01 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979120210901-5Rock Truck - 30 Ton- After Jan 1091242.45 | Corbiere and Sons Contracting979120210901-5Rock Truck - 30 Ton- After Jan 1091242.45INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9791 | 20210901-5 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 9 | Dynamic | 103.54 | 0 |  |  | 1242.45 | 161.5185 | 1403.9685 | 2021-09-01 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979120210901-5Rock Truck - 30 Ton- After Jan 1091242.45 | Corbiere and Sons Contracting979120210901-5Rock Truck - 30 Ton- After Jan 1091242.45INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9791 | 20210901-5 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 9 | Dynamic | 103.54 | 0 |  |  | 1242.45 | 161.5185 | 1403.9685 | 2021-09-01 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979120210901-5Rock Truck - 30 Ton- After Jan 1091242.45 | Corbiere and Sons Contracting979120210901-5Rock Truck - 30 Ton- After Jan 1091242.45INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9791 | 20210901-5 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 9 | Dynamic | 103.54 | 0 |  |  | 1242.45 | 161.5185 | 1403.9685 | 2021-09-01 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979120210901-5Rock Truck - 30 Ton- After Jan 1091242.45 | Corbiere and Sons Contracting979120210901-5Rock Truck - 30 Ton- After Jan 1091242.45INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9791 | 20210901-5 | 53511012 | Access | 0 | Marooka- After Jan 10 | 144.6 | 5 | Dynamic | 108.45 | 0 |  |  | 723 | 93.99 | 816.99 | 2021-09-01 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979120210901-5Marooka- After Jan 105723 | Corbiere and Sons Contracting979120210901-5Marooka- After Jan 105723INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9791 | 20210901-5 | 53511012 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 7 | DAY | 182.81 | 0 |  |  | 1706.25 | 221.8125 | 1928.0625 | 2021-09-01 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979120210901-5Light Truck - Pick up- After Jan 1071706.25 | Corbiere and Sons Contracting979120210901-5Light Truck - Pick up- After Jan 1071706.25INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9791 | 20210901-5 | 53511012 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 9 | HR | 47.54 | 0 |  |  | 570.42 | 74.1546 | 644.5746 | 2021-09-01 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979120210901-5Excavator Hammer - 30 - 50 ton- After Jan 109570.42 | Corbiere and Sons Contracting979120210901-5Excavator Hammer - 30 - 50 ton- After Jan 109570.42INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9791 | 20210901-5 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-09-01 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979120210901-5Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting979120210901-5Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9791 | 20210901-5 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-09-01 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979120210901-5Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting979120210901-5Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9791 | 20210901-5 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-09-01 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979120210901-5Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting979120210901-5Excavator - 36 ton- After Jan 1091322.64INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9791 | 20210901-5 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-09-01 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979120210901-5Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting979120210901-5Excavator - 36 ton- After Jan 1091322.64INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9791 | 20210901-5 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-09-01 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979120210901-5Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting979120210901-5Excavator - 36 ton- After Jan 1091322.64INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9791 | 20210901-5 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 103.84 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2021-09-01 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979120210901-5Excavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting979120210901-5Excavator - 30 ton- After Jan 1091246.05INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9790 | 20210831-5 | 53511012 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 110 | HR |  |  | 75 | 0 | 8250 | 1072.5 | 9322.5 | 2021-08-31 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979020210831-5Operator - Principle - After Jan 101108250 | Corbiere and Sons Contracting979020210831-5Operator - Principle - After Jan 101108250INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9790 | 20210831-5 | 53511012 | Access | 0 | L.O.A. | 210 | 11 | DAY |  |  |  | 0 | 2310 | 300.3 | 2610.3 | 2021-08-31 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979020210831-5L.O.A.112310 | Corbiere and Sons Contracting979020210831-5L.O.A.112310INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9790 | 20210831-5 | 53511012 | Access | 0 | Foreman | 95 | 11 | HR |  |  | 95 | 0 | 1045 | 135.85 | 1180.85 | 2021-08-31 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979020210831-5Foreman111045 | Corbiere and Sons Contracting979020210831-5Foreman111045INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9790 | 20210831-5 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 9 | Dynamic | 103.54 | 0 |  |  | 1242.45 | 161.5185 | 1403.9685 | 2021-08-31 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979020210831-5Rock Truck - 30 Ton- After Jan 1091242.45 | Corbiere and Sons Contracting979020210831-5Rock Truck - 30 Ton- After Jan 1091242.45INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9790 | 20210831-5 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 9 | Dynamic | 103.54 | 0 |  |  | 1242.45 | 161.5185 | 1403.9685 | 2021-08-31 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979020210831-5Rock Truck - 30 Ton- After Jan 1091242.45 | Corbiere and Sons Contracting979020210831-5Rock Truck - 30 Ton- After Jan 1091242.45INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9790 | 20210831-5 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 9 | Dynamic | 103.54 | 0 |  |  | 1242.45 | 161.5185 | 1403.9685 | 2021-08-31 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979020210831-5Rock Truck - 30 Ton- After Jan 1091242.45 | Corbiere and Sons Contracting979020210831-5Rock Truck - 30 Ton- After Jan 1091242.45INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9790 | 20210831-5 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 9 | Dynamic | 103.54 | 0 |  |  | 1242.45 | 161.5185 | 1403.9685 | 2021-08-31 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979020210831-5Rock Truck - 30 Ton- After Jan 1091242.45 | Corbiere and Sons Contracting979020210831-5Rock Truck - 30 Ton- After Jan 1091242.45INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9790 | 20210831-5 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 9 | Dynamic | 103.54 | 0 |  |  | 1242.45 | 161.5185 | 1403.9685 | 2021-08-31 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979020210831-5Rock Truck - 30 Ton- After Jan 1091242.45 | Corbiere and Sons Contracting979020210831-5Rock Truck - 30 Ton- After Jan 1091242.45INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9790 | 20210831-5 | 53511012 | Access | 0 | Marooka- After Jan 10 | 144.6 | 5 | Dynamic | 108.45 | 0 |  |  | 723 | 93.99 | 816.99 | 2021-08-31 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979020210831-5Marooka- After Jan 105723 | Corbiere and Sons Contracting979020210831-5Marooka- After Jan 105723INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9790 | 20210831-5 | 53511012 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 7 | DAY | 182.81 | 0 |  |  | 1706.25 | 221.8125 | 1928.0625 | 2021-08-31 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979020210831-5Light Truck - Pick up- After Jan 1071706.25 | Corbiere and Sons Contracting979020210831-5Light Truck - Pick up- After Jan 1071706.25INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9790 | 20210831-5 | 53511012 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 9 | HR | 47.54 | 0 |  |  | 570.42 | 74.1546 | 644.5746 | 2021-08-31 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979020210831-5Excavator Hammer - 30 - 50 ton- After Jan 109570.42 | Corbiere and Sons Contracting979020210831-5Excavator Hammer - 30 - 50 ton- After Jan 109570.42INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9790 | 20210831-5 | 53511012 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 9 | HR | 47.54 | 0 |  |  | 570.42 | 74.1546 | 644.5746 | 2021-08-31 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979020210831-5Excavator Hammer - 30 - 50 ton- After Jan 109570.42 | Corbiere and Sons Contracting979020210831-5Excavator Hammer - 30 - 50 ton- After Jan 109570.42INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9790 | 20210831-5 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-08-31 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979020210831-5Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting979020210831-5Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9790 | 20210831-5 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-08-31 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979020210831-5Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting979020210831-5Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9790 | 20210831-5 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-08-31 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979020210831-5Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting979020210831-5Excavator - 36 ton- After Jan 1091322.64INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9790 | 20210831-5 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-08-31 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979020210831-5Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting979020210831-5Excavator - 36 ton- After Jan 1091322.64INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9790 | 20210831-5 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-08-31 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979020210831-5Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting979020210831-5Excavator - 36 ton- After Jan 1091322.64INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9790 | 20210831-5 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 103.84 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2021-08-31 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979020210831-5Excavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting979020210831-5Excavator - 30 ton- After Jan 1091246.05INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9790 | 20210831-5 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 103.84 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2021-08-31 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26 and KM36 on Paint Lake 2 | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting979020210831-5Excavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting979020210831-5Excavator - 30 ton- After Jan 1091246.05INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9789 | 20210830-6 | 53511012 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-08-30 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Richard hauling with Kabi on Henson from KM17 | 6 | Km 17 F118 | Hensen Road | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting978920210830-6Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting978920210830-6Operator - Principle - After Jan 1011825INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9789 | 20210830-6 | 53511012 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-08-30 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Richard hauling with Kabi on Henson from KM17 | 6 | Km 17 F118 | Hensen Road | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting978920210830-6L.O.A.1210 | Corbiere and Sons Contracting978920210830-6L.O.A.1210INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9789 | 20210830-6 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 9 | Dynamic | 103.54 | 0 |  |  | 1242.45 | 161.5185 | 1403.9685 | 2021-08-30 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Richard hauling with Kabi on Henson from KM17 | 6 | Km 17 F118 | Hensen Road | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting978920210830-6Rock Truck - 30 Ton- After Jan 1091242.45 | Corbiere and Sons Contracting978920210830-6Rock Truck - 30 Ton- After Jan 1091242.45INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9789 | 20210830-6 | 53511012 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-08-30 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Richard hauling with Kabi on Henson from KM17 | 6 | Km 17 F118 | Hensen Road | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting978920210830-6Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting978920210830-6Light Truck - Pick up- After Jan 101243.75INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9788 | 20210830-5 | 53511012 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 20 | HR |  |  | 75 | 0 | 1500 | 195 | 1695 | 2021-08-30 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26, KM34-KM36 and KM38-KM44 - RT's shut down early | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting978820210830-5Operator - Principle - After Jan 10201500 | Corbiere and Sons Contracting978820210830-5Operator - Principle - After Jan 10201500INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9788 | 20210830-5 | 53511012 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 55 | HR |  |  | 75 | 0 | 4125 | 536.25 | 4661.25 | 2021-08-30 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26, KM34-KM36 and KM38-KM44 - RT's shut down early | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting978820210830-5Operator - Principle - After Jan 10554125 | Corbiere and Sons Contracting978820210830-5Operator - Principle - After Jan 10554125INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9788 | 20210830-5 | 53511012 | Access | 0 | L.O.A. | 210 | 10 | DAY |  |  |  | 0 | 2100 | 273 | 2373 | 2021-08-30 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26, KM34-KM36 and KM38-KM44 - RT's shut down early | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting978820210830-5L.O.A.102100 | Corbiere and Sons Contracting978820210830-5L.O.A.102100INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9788 | 20210830-5 | 53511012 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-08-30 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26, KM34-KM36 and KM38-KM44 - RT's shut down early | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting978820210830-5Foreman121140 | Corbiere and Sons Contracting978820210830-5Foreman121140INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9788 | 20210830-5 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 5 | Dynamic | 103.54 | 0 |  |  | 690.25 | 89.7325 | 779.9825 | 2021-08-30 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26, KM34-KM36 and KM38-KM44 - RT's shut down early | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting978820210830-5Rock Truck - 30 Ton- After Jan 105690.25 | Corbiere and Sons Contracting978820210830-5Rock Truck - 30 Ton- After Jan 105690.25INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9788 | 20210830-5 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 5 | Dynamic | 103.54 | 0 |  |  | 690.25 | 89.7325 | 779.9825 | 2021-08-30 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26, KM34-KM36 and KM38-KM44 - RT's shut down early | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting978820210830-5Rock Truck - 30 Ton- After Jan 105690.25 | Corbiere and Sons Contracting978820210830-5Rock Truck - 30 Ton- After Jan 105690.25INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9788 | 20210830-5 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 5 | Dynamic | 103.54 | 0 |  |  | 690.25 | 89.7325 | 779.9825 | 2021-08-30 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26, KM34-KM36 and KM38-KM44 - RT's shut down early | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting978820210830-5Rock Truck - 30 Ton- After Jan 105690.25 | Corbiere and Sons Contracting978820210830-5Rock Truck - 30 Ton- After Jan 105690.25INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9788 | 20210830-5 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 5 | Dynamic | 103.54 | 0 |  |  | 690.25 | 89.7325 | 779.9825 | 2021-08-30 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26, KM34-KM36 and KM38-KM44 - RT's shut down early | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting978820210830-5Rock Truck - 30 Ton- After Jan 105690.25 | Corbiere and Sons Contracting978820210830-5Rock Truck - 30 Ton- After Jan 105690.25INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9788 | 20210830-5 | 53511012 | Access | 0 | Marooka- After Jan 10 | 144.6 | 5 | Dynamic | 108.45 | 0 |  |  | 723 | 93.99 | 816.99 | 2021-08-30 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26, KM34-KM36 and KM38-KM44 - RT's shut down early | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting978820210830-5Marooka- After Jan 105723 | Corbiere and Sons Contracting978820210830-5Marooka- After Jan 105723INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9788 | 20210830-5 | 53511012 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 5 | DAY | 182.81 | 0 |  |  | 1218.75 | 158.4375 | 1377.1875 | 2021-08-30 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26, KM34-KM36 and KM38-KM44 - RT's shut down early | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting978820210830-5Light Truck - Pick up- After Jan 1051218.75 | Corbiere and Sons Contracting978820210830-5Light Truck - Pick up- After Jan 1051218.75INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9788 | 20210830-5 | 53511012 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-08-30 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26, KM34-KM36 and KM38-KM44 - RT's shut down early | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting978820210830-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting978820210830-5Light Truck - Pick up- After Jan 101243.75INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9788 | 20210830-5 | 53511012 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 9 | HR | 47.54 | 0 |  |  | 570.42 | 74.1546 | 644.5746 | 2021-08-30 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26, KM34-KM36 and KM38-KM44 - RT's shut down early | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting978820210830-5Excavator Hammer - 30 - 50 ton- After Jan 109570.42 | Corbiere and Sons Contracting978820210830-5Excavator Hammer - 30 - 50 ton- After Jan 109570.42INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9788 | 20210830-5 | 53511012 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 9 | HR | 47.54 | 0 |  |  | 570.42 | 74.1546 | 644.5746 | 2021-08-30 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26, KM34-KM36 and KM38-KM44 - RT's shut down early | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting978820210830-5Excavator Hammer - 30 - 50 ton- After Jan 109570.42 | Corbiere and Sons Contracting978820210830-5Excavator Hammer - 30 - 50 ton- After Jan 109570.42INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9788 | 20210830-5 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-08-30 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26, KM34-KM36 and KM38-KM44 - RT's shut down early | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting978820210830-5Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting978820210830-5Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9788 | 20210830-5 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-08-30 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26, KM34-KM36 and KM38-KM44 - RT's shut down early | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting978820210830-5Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting978820210830-5Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9788 | 20210830-5 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-08-30 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26, KM34-KM36 and KM38-KM44 - RT's shut down early | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting978820210830-5Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting978820210830-5Excavator - 36 ton- After Jan 1091322.64INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9788 | 20210830-5 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-08-30 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26, KM34-KM36 and KM38-KM44 - RT's shut down early | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting978820210830-5Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting978820210830-5Excavator - 36 ton- After Jan 1091322.64INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9788 | 20210830-5 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-08-30 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26, KM34-KM36 and KM38-KM44 - RT's shut down early | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting978820210830-5Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting978820210830-5Excavator - 36 ton- After Jan 1091322.64INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9788 | 20210830-5 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 103.84 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2021-08-30 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26, KM34-KM36 and KM38-KM44 - RT's shut down early | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting978820210830-5Excavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting978820210830-5Excavator - 30 ton- After Jan 1091246.05INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9788 | 20210830-5 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 103.84 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2021-08-30 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26, KM34-KM36 and KM38-KM44 - RT's shut down early | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting978820210830-5Excavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting978820210830-5Excavator - 30 ton- After Jan 1091246.05INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9774 | 20210829-5 | 53511012 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-08-29 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | RT hauling from KM17 on Henson Road | 6 | F118 | Hensen Road | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting977420210829-5Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting977420210829-5Operator - Principle - After Jan 1011825INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9774 | 20210829-5 | 53511012 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-08-29 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | RT hauling from KM17 on Henson Road | 6 | F118 | Hensen Road | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting977420210829-5L.O.A.1210 | Corbiere and Sons Contracting977420210829-5L.O.A.1210INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9774 | 20210829-5 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 9 | Dynamic | 103.54 | 0 |  |  | 1242.45 | 161.5185 | 1403.9685 | 2021-08-29 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | RT hauling from KM17 on Henson Road | 6 | F118 | Hensen Road | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting977420210829-5Rock Truck - 30 Ton- After Jan 1091242.45 | Corbiere and Sons Contracting977420210829-5Rock Truck - 30 Ton- After Jan 1091242.45INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9773 | 20210829-4 | 53511012 | Access | 0 | Labourer - General - After Jan 10 | 60 | 5 | HR |  |  | 60 | 0 | 300 | 39 | 339 | 2021-08-29 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26, KM34-KM36 and KM38-KM44 - Work shutdown early due to conditions | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting977320210829-4Labourer - General - After Jan 105300 | Corbiere and Sons Contracting977320210829-4Labourer - General - After Jan 105300INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9773 | 20210829-4 | 53511012 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 12 | HR |  |  | 70 | 0 | 840 | 109.2 | 949.2 | 2021-08-29 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26, KM34-KM36 and KM38-KM44 - Work shutdown early due to conditions | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting977320210829-4Driver - AZ - After Jan 1012840 | Corbiere and Sons Contracting977320210829-4Driver - AZ - After Jan 1012840INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9773 | 20210829-4 | 53511012 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 55 | HR |  |  | 75 | 0 | 4125 | 536.25 | 4661.25 | 2021-08-29 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26, KM34-KM36 and KM38-KM44 - Work shutdown early due to conditions | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting977320210829-4Operator - Principle - After Jan 10554125 | Corbiere and Sons Contracting977320210829-4Operator - Principle - After Jan 10554125INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9773 | 20210829-4 | 53511012 | Access | 0 | L.O.A. | 210 | 14 | DAY |  |  |  | 0 | 2940 | 382.2 | 3322.2 | 2021-08-29 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26, KM34-KM36 and KM38-KM44 - Work shutdown early due to conditions | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting977320210829-4L.O.A.142940 | Corbiere and Sons Contracting977320210829-4L.O.A.142940INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9773 | 20210829-4 | 53511012 | Access | 0 | Foreman | 95 | 5 | HR |  |  | 95 | 0 | 475 | 61.75 | 536.75 | 2021-08-29 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26, KM34-KM36 and KM38-KM44 - Work shutdown early due to conditions | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting977320210829-4Foreman5475 | Corbiere and Sons Contracting977320210829-4Foreman5475INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9773 | 20210829-4 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 5 | Dynamic | 103.54 | 0 |  |  | 690.25 | 89.7325 | 779.9825 | 2021-08-29 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26, KM34-KM36 and KM38-KM44 - Work shutdown early due to conditions | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting977320210829-4Rock Truck - 30 Ton- After Jan 105690.25 | Corbiere and Sons Contracting977320210829-4Rock Truck - 30 Ton- After Jan 105690.25INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9773 | 20210829-4 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 5 | Dynamic | 103.54 | 0 |  |  | 690.25 | 89.7325 | 779.9825 | 2021-08-29 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26, KM34-KM36 and KM38-KM44 - Work shutdown early due to conditions | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting977320210829-4Rock Truck - 30 Ton- After Jan 105690.25 | Corbiere and Sons Contracting977320210829-4Rock Truck - 30 Ton- After Jan 105690.25INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9773 | 20210829-4 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 5 | Dynamic | 103.54 | 0 |  |  | 690.25 | 89.7325 | 779.9825 | 2021-08-29 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26, KM34-KM36 and KM38-KM44 - Work shutdown early due to conditions | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting977320210829-4Rock Truck - 30 Ton- After Jan 105690.25 | Corbiere and Sons Contracting977320210829-4Rock Truck - 30 Ton- After Jan 105690.25INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9773 | 20210829-4 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 5 | Dynamic | 103.54 | 0 |  |  | 690.25 | 89.7325 | 779.9825 | 2021-08-29 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26, KM34-KM36 and KM38-KM44 - Work shutdown early due to conditions | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting977320210829-4Rock Truck - 30 Ton- After Jan 105690.25 | Corbiere and Sons Contracting977320210829-4Rock Truck - 30 Ton- After Jan 105690.25INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9773 | 20210829-4 | 53511012 | Access | 0 | Marooka- After Jan 10 | 144.6 | 5 | Dynamic | 108.45 | 0 |  |  | 723 | 93.99 | 816.99 | 2021-08-29 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26, KM34-KM36 and KM38-KM44 - Work shutdown early due to conditions | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting977320210829-4Marooka- After Jan 105723 | Corbiere and Sons Contracting977320210829-4Marooka- After Jan 105723INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9773 | 20210829-4 | 53511012 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 6 | DAY | 182.81 | 0 |  |  | 1462.5 | 190.125 | 1652.625 | 2021-08-29 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26, KM34-KM36 and KM38-KM44 - Work shutdown early due to conditions | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting977320210829-4Light Truck - Pick up- After Jan 1061462.5 | Corbiere and Sons Contracting977320210829-4Light Truck - Pick up- After Jan 1061462.5INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9773 | 20210829-4 | 53511012 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-08-29 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26, KM34-KM36 and KM38-KM44 - Work shutdown early due to conditions | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting977320210829-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting977320210829-4Light Truck - Pick up- After Jan 101243.75INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9773 | 20210829-4 | 53511012 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 5 | HR | 47.54 | 0 |  |  | 316.9 | 41.197 | 358.097 | 2021-08-29 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26, KM34-KM36 and KM38-KM44 - Work shutdown early due to conditions | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting977320210829-4Excavator Hammer - 30 - 50 ton- After Jan 105316.9 | Corbiere and Sons Contracting977320210829-4Excavator Hammer - 30 - 50 ton- After Jan 105316.9INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9773 | 20210829-4 | 53511012 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 5 | HR | 47.54 | 0 |  |  | 316.9 | 41.197 | 358.097 | 2021-08-29 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26, KM34-KM36 and KM38-KM44 - Work shutdown early due to conditions | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting977320210829-4Excavator Hammer - 30 - 50 ton- After Jan 105316.9 | Corbiere and Sons Contracting977320210829-4Excavator Hammer - 30 - 50 ton- After Jan 105316.9INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9773 | 20210829-4 | 53511012 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 5 | HR | 47.54 | 0 |  |  | 316.9 | 41.197 | 358.097 | 2021-08-29 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26, KM34-KM36 and KM38-KM44 - Work shutdown early due to conditions | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting977320210829-4Excavator Hammer - 30 - 50 ton- After Jan 105316.9 | Corbiere and Sons Contracting977320210829-4Excavator Hammer - 30 - 50 ton- After Jan 105316.9INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9773 | 20210829-4 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 5 | HR | 9.16 | 0 |  |  | 61.05 | 7.9365 | 68.9865 | 2021-08-29 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26, KM34-KM36 and KM38-KM44 - Work shutdown early due to conditions | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting977320210829-4Excavator Thumb - 30 - 50 ton- After Jan 10561.05 | Corbiere and Sons Contracting977320210829-4Excavator Thumb - 30 - 50 ton- After Jan 10561.05INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9773 | 20210829-4 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 5 | HR | 9.16 | 0 |  |  | 61.05 | 7.9365 | 68.9865 | 2021-08-29 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26, KM34-KM36 and KM38-KM44 - Work shutdown early due to conditions | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting977320210829-4Excavator Thumb - 30 - 50 ton- After Jan 10561.05 | Corbiere and Sons Contracting977320210829-4Excavator Thumb - 30 - 50 ton- After Jan 10561.05INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9773 | 20210829-4 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 5 | Dynamic | 110.22 | 0 |  |  | 734.8 | 95.524 | 830.324 | 2021-08-29 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26, KM34-KM36 and KM38-KM44 - Work shutdown early due to conditions | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting977320210829-4Excavator - 36 ton- After Jan 105734.8 | Corbiere and Sons Contracting977320210829-4Excavator - 36 ton- After Jan 105734.8INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9773 | 20210829-4 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 5 | Dynamic | 110.22 | 0 |  |  | 734.8 | 95.524 | 830.324 | 2021-08-29 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26, KM34-KM36 and KM38-KM44 - Work shutdown early due to conditions | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting977320210829-4Excavator - 36 ton- After Jan 105734.8 | Corbiere and Sons Contracting977320210829-4Excavator - 36 ton- After Jan 105734.8INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9773 | 20210829-4 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 5 | Dynamic | 110.22 | 0 |  |  | 734.8 | 95.524 | 830.324 | 2021-08-29 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26, KM34-KM36 and KM38-KM44 - Work shutdown early due to conditions | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting977320210829-4Excavator - 36 ton- After Jan 105734.8 | Corbiere and Sons Contracting977320210829-4Excavator - 36 ton- After Jan 105734.8INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9773 | 20210829-4 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 5 | Dynamic | 103.84 | 0 |  |  | 692.25 | 89.9925 | 782.2425 | 2021-08-29 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26, KM34-KM36 and KM38-KM44 - Work shutdown early due to conditions | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting977320210829-4Excavator - 30 ton- After Jan 105692.25 | Corbiere and Sons Contracting977320210829-4Excavator - 30 ton- After Jan 105692.25INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9773 | 20210829-4 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 5 | Dynamic | 103.84 | 0 |  |  | 692.25 | 89.9925 | 782.2425 | 2021-08-29 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26, KM34-KM36 and KM38-KM44 - Work shutdown early due to conditions | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting977320210829-4Excavator - 30 ton- After Jan 105692.25 | Corbiere and Sons Contracting977320210829-4Excavator - 30 ton- After Jan 105692.25INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9773 | 20210829-4 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 5 | Dynamic | 103.84 | 0 |  |  | 692.25 | 89.9925 | 782.2425 | 2021-08-29 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM26, KM34-KM36 and KM38-KM44 - Work shutdown early due to conditions | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-09-06 |  | 37 | 2021-09-10 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting977320210829-4Excavator - 30 ton- After Jan 105692.25 | Corbiere and Sons Contracting977320210829-4Excavator - 30 ton- After Jan 105692.25INV #148 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9857 | 20210916-7 | 53510602 | Access | 0 | Labourer - General - After Jan 10 | 60 | 12 | HR |  |  | 60 | 0 | 720 | 93.6 | 813.6 | 2021-09-16 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Del Lake Road from WC8120.01 to WC8130.01 - Ex moved from East to West | 6 | C186-C195 | Del Lake | 0 | 2021-09-20 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting985720210916-7Labourer - General - After Jan 1012720 | Corbiere and Sons Contracting985720210916-7Labourer - General - After Jan 1012720INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9857 | 20210916-7 | 53510602 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 3 | HR |  |  | 70 | 0 | 210 | 27.3 | 237.3 | 2021-09-16 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Del Lake Road from WC8120.01 to WC8130.01 - Ex moved from East to West | 6 | C186-C195 | Del Lake | 0 | 2021-09-20 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting985720210916-7Driver - AZ - After Jan 103210 | Corbiere and Sons Contracting985720210916-7Driver - AZ - After Jan 103210INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9857 | 20210916-7 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 44 | HR |  |  | 75 | 0 | 3300 | 429 | 3729 | 2021-09-16 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Del Lake Road from WC8120.01 to WC8130.01 - Ex moved from East to West | 6 | C186-C195 | Del Lake | 0 | 2021-09-20 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting985720210916-7Operator - Principle - After Jan 10443300 | Corbiere and Sons Contracting985720210916-7Operator - Principle - After Jan 10443300INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9857 | 20210916-7 | 53510602 | Access | 0 | L.O.A. | 210 | 7 | DAY |  |  |  | 0 | 1470 | 191.1 | 1661.1 | 2021-09-16 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Del Lake Road from WC8120.01 to WC8130.01 - Ex moved from East to West | 6 | C186-C195 | Del Lake | 0 | 2021-09-20 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting985720210916-7L.O.A.71470 | Corbiere and Sons Contracting985720210916-7L.O.A.71470INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9857 | 20210916-7 | 53510602 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-09-16 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Del Lake Road from WC8120.01 to WC8130.01 - Ex moved from East to West | 6 | C186-C195 | Del Lake | 0 | 2021-09-20 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting985720210916-7Foreman121140 | Corbiere and Sons Contracting985720210916-7Foreman121140INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9857 | 20210916-7 | 53510602 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 3 | Dynamic | 91.79 | 0 |  |  | 367.17 | 47.7321 | 414.9021 | 2021-09-16 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Del Lake Road from WC8120.01 to WC8130.01 - Ex moved from East to West | 6 | C186-C195 | Del Lake | 0 | 2021-09-20 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting985720210916-7Tractor Trailer - 60 Ton- After Jan 103367.17 | Corbiere and Sons Contracting985720210916-7Tractor Trailer - 60 Ton- After Jan 103367.17INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9857 | 20210916-7 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 10 | Dynamic | 103.54 | 0 |  |  | 1380.5 | 179.465 | 1559.965 | 2021-09-16 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Del Lake Road from WC8120.01 to WC8130.01 - Ex moved from East to West | 6 | C186-C195 | Del Lake | 0 | 2021-09-20 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting985720210916-7Rock Truck - 30 Ton- After Jan 10101380.5 | Corbiere and Sons Contracting985720210916-7Rock Truck - 30 Ton- After Jan 10101380.5INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9857 | 20210916-7 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2021-09-16 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Del Lake Road from WC8120.01 to WC8130.01 - Ex moved from East to West | 6 | C186-C195 | Del Lake | 0 | 2021-09-20 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting985720210916-7Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting985720210916-7Light Truck - Pick up- After Jan 103731.25INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9857 | 20210916-7 | 53510602 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 10 | HR | 47.54 | 0 |  |  | 633.8 | 82.394 | 716.194 | 2021-09-16 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Del Lake Road from WC8120.01 to WC8130.01 - Ex moved from East to West | 6 | C186-C195 | Del Lake | 0 | 2021-09-20 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting985720210916-7Excavator Hammer - 30 - 50 ton- After Jan 1010633.8 | Corbiere and Sons Contracting985720210916-7Excavator Hammer - 30 - 50 ton- After Jan 1010633.8INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9857 | 20210916-7 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10 | Dynamic | 110.22 | 0 |  |  | 1469.6 | 191.048 | 1660.648 | 2021-09-16 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Del Lake Road from WC8120.01 to WC8130.01 - Ex moved from East to West | 6 | C186-C195 | Del Lake | 0 | 2021-09-20 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting985720210916-7Excavator - 36 ton- After Jan 10101469.6 | Corbiere and Sons Contracting985720210916-7Excavator - 36 ton- After Jan 10101469.6INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9857 | 20210916-7 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-16 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Del Lake Road from WC8120.01 to WC8130.01 - Ex moved from East to West | 6 | C186-C195 | Del Lake | 0 | 2021-09-20 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting985720210916-7Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting985720210916-7Excavator - 36 ton- After Jan 10111616.56INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9857 | 20210916-7 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 7 | Dynamic | 103.84 | 0 |  |  | 969.15 | 125.9895 | 1095.1395 | 2021-09-16 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Del Lake Road from WC8120.01 to WC8130.01 - Ex moved from East to West | 6 | C186-C195 | Del Lake | 0 | 2021-09-20 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting985720210916-7Excavator - 30 ton- After Jan 107969.15 | Corbiere and Sons Contracting985720210916-7Excavator - 30 ton- After Jan 107969.15INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9855 | 20210916-5 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 48 | HR |  |  | 75 | 0 | 3600 | 468 | 4068 | 2021-09-16 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Hare Lake road from entrance towards C264 | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-09-20 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting985520210916-5Operator - Principle - After Jan 10483600 | Corbiere and Sons Contracting985520210916-5Operator - Principle - After Jan 10483600INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9855 | 20210916-5 | 53510602 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2021-09-16 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Hare Lake road from entrance towards C264 | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-09-20 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting985520210916-5L.O.A.4840 | Corbiere and Sons Contracting985520210916-5L.O.A.4840INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9855 | 20210916-5 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-09-16 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Hare Lake road from entrance towards C264 | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-09-20 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting985520210916-5Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting985520210916-5Rock Truck - 30 Ton- After Jan 10111518.55INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9855 | 20210916-5 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-09-16 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Hare Lake road from entrance towards C264 | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-09-20 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting985520210916-5Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting985520210916-5Light Truck - Pick up- After Jan 102487.5INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9855 | 20210916-5 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-16 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Hare Lake road from entrance towards C264 | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-09-20 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting985520210916-5Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting985520210916-5Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9855 | 20210916-5 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-16 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Hare Lake road from entrance towards C264 | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-09-20 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting985520210916-5Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting985520210916-5Excavator - 30 ton- After Jan 10111522.95INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9855 | 20210916-5 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-16 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Hare Lake road from entrance towards C264 | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-09-20 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting985520210916-5Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting985520210916-5Excavator - 30 ton- After Jan 10111522.95INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9855 | 20210916-5 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-09-16 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Hare Lake road from entrance towards C264 | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-09-20 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting985520210916-5Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting985520210916-5Dozer D6 or equal- After Jan 10111446.28INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9864 | 20210916-14 | 53510602 | Access | 0 | Labourer - General - After Jan 10 | 60 | 12 | HR |  |  | 60 | 0 | 720 | 93.6 | 813.6 | 2021-09-16 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Neys | 6 | C219-C235 | Neys | 0 | 2021-09-20 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting986420210916-14Labourer - General - After Jan 1012720 | Corbiere and Sons Contracting986420210916-14Labourer - General - After Jan 1012720INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9864 | 20210916-14 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 60 | HR |  |  | 75 | 0 | 4500 | 585 | 5085 | 2021-09-16 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Neys | 6 | C219-C235 | Neys | 0 | 2021-09-20 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting986420210916-14Operator - Principle - After Jan 10604500 | Corbiere and Sons Contracting986420210916-14Operator - Principle - After Jan 10604500INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9864 | 20210916-14 | 53510602 | Access | 0 | L.O.A. | 210 | 8 | DAY |  |  |  | 0 | 1680 | 218.4 | 1898.4 | 2021-09-16 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Neys | 6 | C219-C235 | Neys | 0 | 2021-09-20 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting986420210916-14L.O.A.81680 | Corbiere and Sons Contracting986420210916-14L.O.A.81680INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9864 | 20210916-14 | 53510602 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-09-16 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Neys | 6 | C219-C235 | Neys | 0 | 2021-09-20 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting986420210916-14Foreman121140 | Corbiere and Sons Contracting986420210916-14Foreman121140INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9864 | 20210916-14 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-09-16 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Neys | 6 | C219-C235 | Neys | 0 | 2021-09-20 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting986420210916-14Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting986420210916-14Rock Truck - 30 Ton- After Jan 10111518.55INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9864 | 20210916-14 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-09-16 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Neys | 6 | C219-C235 | Neys | 0 | 2021-09-20 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting986420210916-14Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting986420210916-14Rock Truck - 30 Ton- After Jan 10111518.55INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9864 | 20210916-14 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 4 | DAY | 182.81 | 0 |  |  | 975 | 126.75 | 1101.75 | 2021-09-16 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Neys | 6 | C219-C235 | Neys | 0 | 2021-09-20 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting986420210916-14Light Truck - Pick up- After Jan 104975 | Corbiere and Sons Contracting986420210916-14Light Truck - Pick up- After Jan 104975INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9864 | 20210916-14 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-16 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Neys | 6 | C219-C235 | Neys | 0 | 2021-09-20 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting986420210916-14Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting986420210916-14Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9864 | 20210916-14 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-16 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Neys | 6 | C219-C235 | Neys | 0 | 2021-09-20 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting986420210916-14Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting986420210916-14Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9864 | 20210916-14 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-16 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Neys | 6 | C219-C235 | Neys | 0 | 2021-09-20 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting986420210916-14Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting986420210916-14Excavator - 36 ton- After Jan 10111616.56INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9864 | 20210916-14 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-16 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Neys | 6 | C219-C235 | Neys | 0 | 2021-09-20 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting986420210916-14Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting986420210916-14Excavator - 30 ton- After Jan 10111522.95INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9864 | 20210916-14 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-09-16 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Neys | 6 | C219-C235 | Neys | 0 | 2021-09-20 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting986420210916-14Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting986420210916-14Dozer D6 or equal- After Jan 10111446.28INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9863 | 20210916-13 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 36 | HR |  |  | 75 | 0 | 2700 | 351 | 3051 | 2021-09-16 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Little Red Sucker Access | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-09-20 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting986320210916-13Operator - Principle - After Jan 10362700 | Corbiere and Sons Contracting986320210916-13Operator - Principle - After Jan 10362700INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9863 | 20210916-13 | 53510602 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-09-16 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Little Red Sucker Access | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-09-20 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting986320210916-13L.O.A.3630 | Corbiere and Sons Contracting986320210916-13L.O.A.3630INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9863 | 20210916-13 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-09-16 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Little Red Sucker Access | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-09-20 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting986320210916-13Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting986320210916-13Rock Truck - 30 Ton- After Jan 10111518.55INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9863 | 20210916-13 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-09-16 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Little Red Sucker Access | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-09-20 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting986320210916-13Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting986320210916-13Light Truck - Pick up- After Jan 102487.5INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9863 | 20210916-13 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-16 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Little Red Sucker Access | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-09-20 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting986320210916-13Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting986320210916-13Excavator - 30 ton- After Jan 10111522.95INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9863 | 20210916-13 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-09-16 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Little Red Sucker Access | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-09-20 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting986320210916-13Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting986320210916-13Dozer D6 or equal- After Jan 10111446.28INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9862 | 20210916-12 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 24 | HR |  |  | 75 | 0 | 1800 | 234 | 2034 | 2021-09-16 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from C217 | 6 | C217 | Highway 17 | 0 | 2021-09-20 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting986220210916-12Operator - Principle - After Jan 10241800 | Corbiere and Sons Contracting986220210916-12Operator - Principle - After Jan 10241800INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9862 | 20210916-12 | 53510602 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-09-16 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from C217 | 6 | C217 | Highway 17 | 0 | 2021-09-20 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting986220210916-12L.O.A.2420 | Corbiere and Sons Contracting986220210916-12L.O.A.2420INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9862 | 20210916-12 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-09-16 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from C217 | 6 | C217 | Highway 17 | 0 | 2021-09-20 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting986220210916-12Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting986220210916-12Rock Truck - 30 Ton- After Jan 10111518.55INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9862 | 20210916-12 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-09-16 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from C217 | 6 | C217 | Highway 17 | 0 | 2021-09-20 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting986220210916-12Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting986220210916-12Light Truck - Pick up- After Jan 101243.75INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9862 | 20210916-12 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-16 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from C217 | 6 | C217 | Highway 17 | 0 | 2021-09-20 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting986220210916-12Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting986220210916-12Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9862 | 20210916-12 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-16 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from C217 | 6 | C217 | Highway 17 | 0 | 2021-09-20 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting986220210916-12Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting986220210916-12Excavator - 30 ton- After Jan 10111522.95INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9861 | 20210916-11 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 24 | HR |  |  | 75 | 0 | 1800 | 234 | 2034 | 2021-09-16 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Ripple Creek | 6 | C197-C202 | Ripple Lake | 0 | 2021-09-20 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting986120210916-11Operator - Principle - After Jan 10241800 | Corbiere and Sons Contracting986120210916-11Operator - Principle - After Jan 10241800INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9861 | 20210916-11 | 53510602 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-09-16 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Ripple Creek | 6 | C197-C202 | Ripple Lake | 0 | 2021-09-20 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting986120210916-11L.O.A.3630 | Corbiere and Sons Contracting986120210916-11L.O.A.3630INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9861 | 20210916-11 | 53510602 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-09-16 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Ripple Creek | 6 | C197-C202 | Ripple Lake | 0 | 2021-09-20 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting986120210916-11Foreman121140 | Corbiere and Sons Contracting986120210916-11Foreman121140INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9861 | 20210916-11 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-09-16 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Ripple Creek | 6 | C197-C202 | Ripple Lake | 0 | 2021-09-20 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting986120210916-11Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting986120210916-11Light Truck - Pick up- After Jan 102487.5INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9861 | 20210916-11 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-16 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Ripple Creek | 6 | C197-C202 | Ripple Lake | 0 | 2021-09-20 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting986120210916-11Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting986120210916-11Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9861 | 20210916-11 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 22 | Dynamic | 110.22 | 0 |  |  | 3233.12 | 420.3056 | 3653.4256 | 2021-09-16 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Ripple Creek | 6 | C197-C202 | Ripple Lake | 0 | 2021-09-20 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting986120210916-11Excavator - 36 ton- After Jan 10223233.12 | Corbiere and Sons Contracting986120210916-11Excavator - 36 ton- After Jan 10223233.12INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9860 | 20210916-10 | 53510602 | Access | 0 | Labourer - General - After Jan 10 | 60 | 12 | HR |  |  | 60 | 0 | 720 | 93.6 | 813.6 | 2021-09-16 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-20 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting986020210916-10Labourer - General - After Jan 1012720 | Corbiere and Sons Contracting986020210916-10Labourer - General - After Jan 1012720INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9860 | 20210916-10 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 24 | HR |  |  | 75 | 0 | 1800 | 234 | 2034 | 2021-09-16 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-20 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting986020210916-10Operator - Principle - After Jan 10241800 | Corbiere and Sons Contracting986020210916-10Operator - Principle - After Jan 10241800INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9860 | 20210916-10 | 53510602 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-09-16 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-20 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting986020210916-10L.O.A.3630 | Corbiere and Sons Contracting986020210916-10L.O.A.3630INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9860 | 20210916-10 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 22 | Dynamic | 103.54 | 0 |  |  | 3037.1 | 394.823 | 3431.923 | 2021-09-16 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-20 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting986020210916-10Rock Truck - 30 Ton- After Jan 10223037.1 | Corbiere and Sons Contracting986020210916-10Rock Truck - 30 Ton- After Jan 10223037.1INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9860 | 20210916-10 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-09-16 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-20 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting986020210916-10Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting986020210916-10Light Truck - Pick up- After Jan 102487.5INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9860 | 20210916-10 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-16 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-20 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting986020210916-10Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting986020210916-10Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9860 | 20210916-10 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-16 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-20 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting986020210916-10Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting986020210916-10Excavator - 36 ton- After Jan 10111616.56INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9850 | 20210915-9 | 53510602 | Access | 0 | Labourer - General - After Jan 10 | 60 | 22 | HR |  |  | 60 | 0 | 1320 | 171.6 | 1491.6 | 2021-09-15 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Neys | 6 | C219-C235 | Neys Road | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting985020210915-9Labourer - General - After Jan 10221320 | Corbiere and Sons Contracting985020210915-9Labourer - General - After Jan 10221320INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9850 | 20210915-9 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 44 | HR |  |  | 75 | 0 | 3300 | 429 | 3729 | 2021-09-15 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Neys | 6 | C219-C235 | Neys Road | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting985020210915-9Operator - Principle - After Jan 10443300 | Corbiere and Sons Contracting985020210915-9Operator - Principle - After Jan 10443300INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9850 | 20210915-9 | 53510602 | Access | 0 | L.O.A. | 210 | 7 | DAY |  |  |  | 0 | 1470 | 191.1 | 1661.1 | 2021-09-15 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Neys | 6 | C219-C235 | Neys Road | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting985020210915-9L.O.A.71470 | Corbiere and Sons Contracting985020210915-9L.O.A.71470INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9850 | 20210915-9 | 53510602 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-09-15 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Neys | 6 | C219-C235 | Neys Road | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting985020210915-9Foreman121140 | Corbiere and Sons Contracting985020210915-9Foreman121140INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9850 | 20210915-9 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 8 | Dynamic | 103.54 | 0 |  |  | 1104.4 | 143.572 | 1247.972 | 2021-09-15 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Neys | 6 | C219-C235 | Neys Road | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting985020210915-9Rock Truck - 30 Ton- After Jan 1081104.4 | Corbiere and Sons Contracting985020210915-9Rock Truck - 30 Ton- After Jan 1081104.4INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9850 | 20210915-9 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 6 | Dynamic | 103.54 | 0 |  |  | 828.3 | 107.679 | 935.979 | 2021-09-15 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Neys | 6 | C219-C235 | Neys Road | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting985020210915-9Rock Truck - 30 Ton- After Jan 106828.3 | Corbiere and Sons Contracting985020210915-9Rock Truck - 30 Ton- After Jan 106828.3INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9850 | 20210915-9 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 4 | DAY | 182.81 | 0 |  |  | 975 | 126.75 | 1101.75 | 2021-09-15 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Neys | 6 | C219-C235 | Neys Road | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting985020210915-9Light Truck - Pick up- After Jan 104975 | Corbiere and Sons Contracting985020210915-9Light Truck - Pick up- After Jan 104975INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9850 | 20210915-9 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 9.16 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2021-09-15 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Neys | 6 | C219-C235 | Neys Road | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting985020210915-9Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting985020210915-9Excavator Thumb - 30 - 50 ton- After Jan 1010122.1INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9850 | 20210915-9 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 9.16 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2021-09-15 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Neys | 6 | C219-C235 | Neys Road | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting985020210915-9Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting985020210915-9Excavator Thumb - 30 - 50 ton- After Jan 1010122.1INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9850 | 20210915-9 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10 | Dynamic | 110.22 | 0 |  |  | 1469.6 | 191.048 | 1660.648 | 2021-09-15 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Neys | 6 | C219-C235 | Neys Road | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting985020210915-9Excavator - 36 ton- After Jan 10101469.6 | Corbiere and Sons Contracting985020210915-9Excavator - 36 ton- After Jan 10101469.6INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9850 | 20210915-9 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10 | Dynamic | 103.84 | 0 |  |  | 1384.5 | 179.985 | 1564.485 | 2021-09-15 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Neys | 6 | C219-C235 | Neys Road | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting985020210915-9Excavator - 30 ton- After Jan 10101384.5 | Corbiere and Sons Contracting985020210915-9Excavator - 30 ton- After Jan 10101384.5INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9849 | 20210915-8 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 33 | HR |  |  | 75 | 0 | 2475 | 321.75 | 2796.75 | 2021-09-15 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Little Red Sucker Access | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting984920210915-8Operator - Principle - After Jan 10332475 | Corbiere and Sons Contracting984920210915-8Operator - Principle - After Jan 10332475INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9849 | 20210915-8 | 53510602 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-09-15 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Little Red Sucker Access | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting984920210915-8L.O.A.3630 | Corbiere and Sons Contracting984920210915-8L.O.A.3630INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9849 | 20210915-8 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 10 | Dynamic | 103.54 | 0 |  |  | 1380.5 | 179.465 | 1559.965 | 2021-09-15 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Little Red Sucker Access | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting984920210915-8Rock Truck - 30 Ton- After Jan 10101380.5 | Corbiere and Sons Contracting984920210915-8Rock Truck - 30 Ton- After Jan 10101380.5INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9849 | 20210915-8 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-09-15 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Little Red Sucker Access | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting984920210915-8Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting984920210915-8Light Truck - Pick up- After Jan 102487.5INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9849 | 20210915-8 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10 | Dynamic | 103.84 | 0 |  |  | 1384.5 | 179.985 | 1564.485 | 2021-09-15 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Little Red Sucker Access | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting984920210915-8Excavator - 30 ton- After Jan 10101384.5 | Corbiere and Sons Contracting984920210915-8Excavator - 30 ton- After Jan 10101384.5INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9849 | 20210915-8 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10 | Dynamic | 98.61 | 0 |  |  | 1314.8 | 170.924 | 1485.724 | 2021-09-15 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Little Red Sucker Access | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting984920210915-8Dozer D6 or equal- After Jan 10101314.8 | Corbiere and Sons Contracting984920210915-8Dozer D6 or equal- After Jan 10101314.8INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9848 | 20210915-7 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-09-15 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from C217 | 6 | C217 | Highway 17 | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting984820210915-7Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting984820210915-7Operator - Principle - After Jan 1011825INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9848 | 20210915-7 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-09-15 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from C217 | 6 | C217 | Highway 17 | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting984820210915-7Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting984820210915-7Operator - Principle - After Jan 1011825INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9848 | 20210915-7 | 53510602 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-09-15 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from C217 | 6 | C217 | Highway 17 | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting984820210915-7L.O.A.2420 | Corbiere and Sons Contracting984820210915-7L.O.A.2420INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9848 | 20210915-7 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 6 | Dynamic | 103.54 | 0 |  |  | 828.3 | 107.679 | 935.979 | 2021-09-15 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from C217 | 6 | C217 | Highway 17 | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting984820210915-7Rock Truck - 30 Ton- After Jan 106828.3 | Corbiere and Sons Contracting984820210915-7Rock Truck - 30 Ton- After Jan 106828.3INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9848 | 20210915-7 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-09-15 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from C217 | 6 | C217 | Highway 17 | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting984820210915-7Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting984820210915-7Light Truck - Pick up- After Jan 101243.75INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9848 | 20210915-7 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 6 | HR | 9.16 | 0 |  |  | 73.26 | 9.5238 | 82.7838 | 2021-09-15 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from C217 | 6 | C217 | Highway 17 | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting984820210915-7Excavator Thumb - 30 - 50 ton- After Jan 10673.26 | Corbiere and Sons Contracting984820210915-7Excavator Thumb - 30 - 50 ton- After Jan 10673.26INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9848 | 20210915-7 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 6 | Dynamic | 103.84 | 0 |  |  | 830.7 | 107.991 | 938.691 | 2021-09-15 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from C217 | 6 | C217 | Highway 17 | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting984820210915-7Excavator - 30 ton- After Jan 106830.7 | Corbiere and Sons Contracting984820210915-7Excavator - 30 ton- After Jan 106830.7INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9847 | 20210915-6 | 53510602 | Access | 0 | Labourer - General - After Jan 10 | 60 | 12 | HR |  |  | 60 | 0 | 720 | 93.6 | 813.6 | 2021-09-15 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting984720210915-6Labourer - General - After Jan 1012720 | Corbiere and Sons Contracting984720210915-6Labourer - General - After Jan 1012720INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9847 | 20210915-6 | 53510602 | Access | 0 | Labourer - General - After Jan 10 | 60 | 12 | HR |  |  | 60 | 0 | 720 | 93.6 | 813.6 | 2021-09-15 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting984720210915-6Labourer - General - After Jan 1012720 | Corbiere and Sons Contracting984720210915-6Labourer - General - After Jan 1012720INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9847 | 20210915-6 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2021-09-15 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting984720210915-6Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting984720210915-6Operator - Principle - After Jan 1012900INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9847 | 20210915-6 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2021-09-15 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting984720210915-6Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting984720210915-6Operator - Principle - After Jan 1012900INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9847 | 20210915-6 | 53510602 | Access | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2021-09-15 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting984720210915-6L.O.A.51050 | Corbiere and Sons Contracting984720210915-6L.O.A.51050INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9847 | 20210915-6 | 53510602 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-09-15 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting984720210915-6Foreman121140 | Corbiere and Sons Contracting984720210915-6Foreman121140INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9847 | 20210915-6 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 6 | Dynamic | 103.54 | 0 |  |  | 828.3 | 107.679 | 935.979 | 2021-09-15 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting984720210915-6Rock Truck - 30 Ton- After Jan 106828.3 | Corbiere and Sons Contracting984720210915-6Rock Truck - 30 Ton- After Jan 106828.3INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9847 | 20210915-6 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-09-15 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting984720210915-6Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting984720210915-6Light Truck - Pick up- After Jan 102487.5INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9847 | 20210915-6 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10.5 | HR | 9.16 | 0 |  |  | 128.205 | 16.6667 | 144.8716 | 2021-09-15 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting984720210915-6Excavator Thumb - 30 - 50 ton- After Jan 1010.5128.205 | Corbiere and Sons Contracting984720210915-6Excavator Thumb - 30 - 50 ton- After Jan 1010.5128.205INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9847 | 20210915-6 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10.5 | Dynamic | 110.22 | 0 |  |  | 1543.08 | 200.6004 | 1743.6804 | 2021-09-15 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting984720210915-6Excavator - 36 ton- After Jan 1010.51543.08 | Corbiere and Sons Contracting984720210915-6Excavator - 36 ton- After Jan 1010.51543.08INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9845 | 20210915-4 | 53510602 | Access | 0 | Labourer - General - After Jan 10 | 60 | 5 | HR |  |  | 60 | 0 | 300 | 39 | 339 | 2021-09-15 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Hare Lake road from entrance towards C264 | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting984520210915-4Labourer - General - After Jan 105300 | Corbiere and Sons Contracting984520210915-4Labourer - General - After Jan 105300INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9845 | 20210915-4 | 53510602 | Access | 0 | Labourer - General - After Jan 10 | 60 | 6 | HR |  |  | 60 | 0 | 360 | 46.8 | 406.8 | 2021-09-15 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Hare Lake road from entrance towards C264 | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting984520210915-4Labourer - General - After Jan 106360 | Corbiere and Sons Contracting984520210915-4Labourer - General - After Jan 106360INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9845 | 20210915-4 | 53510602 | Access | 0 | Labourer - General - After Jan 10 | 60 | 6 | HR |  |  | 60 | 0 | 360 | 46.8 | 406.8 | 2021-09-15 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Hare Lake road from entrance towards C264 | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting984520210915-4Labourer - General - After Jan 106360 | Corbiere and Sons Contracting984520210915-4Labourer - General - After Jan 106360INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9845 | 20210915-4 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5 | HR |  |  | 75 | 0 | 375 | 48.75 | 423.75 | 2021-09-15 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Hare Lake road from entrance towards C264 | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting984520210915-4Operator - Principle - After Jan 105375 | Corbiere and Sons Contracting984520210915-4Operator - Principle - After Jan 105375INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9845 | 20210915-4 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2021-09-15 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Hare Lake road from entrance towards C264 | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting984520210915-4Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting984520210915-4Operator - Principle - After Jan 1012900INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9845 | 20210915-4 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2021-09-15 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Hare Lake road from entrance towards C264 | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting984520210915-4Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting984520210915-4Operator - Principle - After Jan 1012900INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9845 | 20210915-4 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2021-09-15 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Hare Lake road from entrance towards C264 | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting984520210915-4Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting984520210915-4Operator - Principle - After Jan 1012900INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9845 | 20210915-4 | 53510602 | Access | 0 | L.O.A. | 210 | 7 | DAY |  |  |  | 0 | 1470 | 191.1 | 1661.1 | 2021-09-15 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Hare Lake road from entrance towards C264 | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting984520210915-4L.O.A.71470 | Corbiere and Sons Contracting984520210915-4L.O.A.71470INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9845 | 20210915-4 | 53510602 | Access | 0 | Foreman | 95 | 4 | HR |  |  | 95 | 0 | 380 | 49.4 | 429.4 | 2021-09-15 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Hare Lake road from entrance towards C264 | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting984520210915-4Foreman4380 | Corbiere and Sons Contracting984520210915-4Foreman4380INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9845 | 20210915-4 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-09-15 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Hare Lake road from entrance towards C264 | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting984520210915-4Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting984520210915-4Rock Truck - 30 Ton- After Jan 10111518.55INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9845 | 20210915-4 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2021-09-15 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Hare Lake road from entrance towards C264 | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting984520210915-4Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting984520210915-4Light Truck - Pick up- After Jan 103731.25INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9845 | 20210915-4 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-15 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Hare Lake road from entrance towards C264 | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting984520210915-4Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting984520210915-4Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9845 | 20210915-4 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-15 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Hare Lake road from entrance towards C264 | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting984520210915-4Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting984520210915-4Excavator - 30 ton- After Jan 10111522.95INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9845 | 20210915-4 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-09-15 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Hare Lake road from entrance towards C264 | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting984520210915-4Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting984520210915-4Dozer D6 or equal- After Jan 10111446.28INV #148 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9859 | 20210916-9 | 53530601 | Rig/Access Mats | 0 | Driver - AZ - After Jan 10 | 70 | 8 | HR |  |  | 70 | 0 | 560 | 72.8 | 632.8 | 2021-09-16 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float delivering rig mats to Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-09-20 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting985920210916-9Driver - AZ - After Jan 108560 | Corbiere and Sons Contracting985920210916-9Driver - AZ - After Jan 108560INV #148 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Corbiere and Sons Contracting | 6 | 0 | 9859 | 20210916-9 | 53530601 | Rig/Access Mats | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-09-16 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float delivering rig mats to Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-09-20 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting985920210916-9L.O.A.1210 | Corbiere and Sons Contracting985920210916-9L.O.A.1210INV #148 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Corbiere and Sons Contracting | 6 | 0 | 9859 | 20210916-9 | 53530601 | Rig/Access Mats | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 8 | Dynamic | 91.79 | 0 |  |  | 979.12 | 127.2856 | 1106.4056 | 2021-09-16 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float delivering rig mats to Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-09-20 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting985920210916-9Tractor Trailer - 60 Ton- After Jan 108979.12 | Corbiere and Sons Contracting985920210916-9Tractor Trailer - 60 Ton- After Jan 108979.12INV #148 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Corbiere and Sons Contracting | 6 | 0 | 9854 | 20210916-4 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 42.5 | HR |  |  | 70 | 0 | 2975 | 386.75 | 3361.75 | 2021-09-16 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-09-20 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting985420210916-4Driver - AZ - After Jan 1042.52975 | Corbiere and Sons Contracting985420210916-4Driver - AZ - After Jan 1042.52975INV #148 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9854 | 20210916-4 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 69 | HR |  |  | 70 | 0 | 4830 | 627.9 | 5457.9 | 2021-09-16 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-09-20 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting985420210916-4Driver - AZ - After Jan 10694830 | Corbiere and Sons Contracting985420210916-4Driver - AZ - After Jan 10694830INV #148 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9854 | 20210916-4 | 53510604 | Access | 0 | L.O.A. | 210 | 11 | DAY |  |  |  | 0 | 2310 | 300.3 | 2610.3 | 2021-09-16 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-09-20 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting985420210916-4L.O.A.112310 | Corbiere and Sons Contracting985420210916-4L.O.A.112310INV #148 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9854 | 20210916-4 | 53510604 | Access | 0 | Construction Coordinator | 80 | 7 | HR |  |  | 80 | 0 | 560 | 72.8 | 632.8 | 2021-09-16 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-09-20 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting985420210916-4Construction Coordinator7560 | Corbiere and Sons Contracting985420210916-4Construction Coordinator7560INV #148 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9854 | 20210916-4 | 53510604 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-09-16 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-09-20 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting985420210916-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting985420210916-4Light Truck - Pick up- After Jan 101243.75INV #148 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9854 | 20210916-4 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 42.5 | Dynamic | 41.4 | 0 |  |  | 2346 | 304.98 | 2650.98 | 2021-09-16 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-09-20 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting985420210916-4Dump - Triaxle- After Jan 1042.52346 | Corbiere and Sons Contracting985420210916-4Dump - Triaxle- After Jan 1042.52346INV #148 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9854 | 20210916-4 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 69 | Dynamic | 41.4 | 0 |  |  | 3808.8 | 495.144 | 4303.944 | 2021-09-16 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-09-20 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting985420210916-4Dump - Triaxle- After Jan 10693808.8 | Corbiere and Sons Contracting985420210916-4Dump - Triaxle- After Jan 10693808.8INV #148 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9844 | 20210915-3 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 56 | HR |  |  | 70 | 0 | 3920 | 509.6 | 4429.6 | 2021-09-15 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting984420210915-3Driver - AZ - After Jan 10563920 | Corbiere and Sons Contracting984420210915-3Driver - AZ - After Jan 10563920INV #148 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9844 | 20210915-3 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 68.5 | HR |  |  | 70 | 0 | 4795 | 623.35 | 5418.35 | 2021-09-15 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting984420210915-3Driver - AZ - After Jan 1068.54795 | Corbiere and Sons Contracting984420210915-3Driver - AZ - After Jan 1068.54795INV #148 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9844 | 20210915-3 | 53510604 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2021-09-15 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting984420210915-3Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting984420210915-3Operator - Principle - After Jan 1012900INV #148 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9844 | 20210915-3 | 53510604 | Access | 0 | L.O.A. | 210 | 12 | DAY |  |  |  | 0 | 2520 | 327.6 | 2847.6 | 2021-09-15 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting984420210915-3L.O.A.122520 | Corbiere and Sons Contracting984420210915-3L.O.A.122520INV #148 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9844 | 20210915-3 | 53510604 | Access | 0 | Foreman | 95 | 4 | HR |  |  | 95 | 0 | 380 | 49.4 | 429.4 | 2021-09-15 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting984420210915-3Foreman4380 | Corbiere and Sons Contracting984420210915-3Foreman4380INV #148 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9844 | 20210915-3 | 53510604 | Access | 0 | Construction Coordinator | 80 | 7 | HR |  |  | 80 | 0 | 560 | 72.8 | 632.8 | 2021-09-15 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting984420210915-3Construction Coordinator7560 | Corbiere and Sons Contracting984420210915-3Construction Coordinator7560INV #148 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9844 | 20210915-3 | 53510604 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-09-15 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting984420210915-3Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting984420210915-3Light Truck - Pick up- After Jan 102487.5INV #148 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9844 | 20210915-3 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 56 | Dynamic | 41.4 | 0 |  |  | 3091.2 | 401.856 | 3493.056 | 2021-09-15 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting984420210915-3Dump - Triaxle- After Jan 10563091.2 | Corbiere and Sons Contracting984420210915-3Dump - Triaxle- After Jan 10563091.2INV #148 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9844 | 20210915-3 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 69.5 | Dynamic | 41.4 | 0 |  |  | 3836.4 | 498.732 | 4335.132 | 2021-09-15 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting984420210915-3Dump - Triaxle- After Jan 1069.53836.4 | Corbiere and Sons Contracting984420210915-3Dump - Triaxle- After Jan 1069.53836.4INV #148 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9844 | 20210915-3 | 53510604 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-15 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting984420210915-3Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting984420210915-3Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #148 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9844 | 20210915-3 | 53510604 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-15 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting984420210915-3Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting984420210915-3Excavator - 36 ton- After Jan 10111616.56INV #148 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9841 | 20210914-4 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 69.5 | HR |  |  | 70 | 0 | 4865 | 632.45 | 5497.45 | 2021-09-14 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting984120210914-4Driver - AZ - After Jan 1069.54865 | Corbiere and Sons Contracting984120210914-4Driver - AZ - After Jan 1069.54865INV #148 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9841 | 20210914-4 | 53510604 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2021-09-14 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting984120210914-4Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting984120210914-4Operator - Principle - After Jan 1012900INV #148 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9841 | 20210914-4 | 53510604 | Access | 0 | L.O.A. | 210 | 7 | DAY |  |  |  | 0 | 1470 | 191.1 | 1661.1 | 2021-09-14 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting984120210914-4L.O.A.71470 | Corbiere and Sons Contracting984120210914-4L.O.A.71470INV #148 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9841 | 20210914-4 | 53510604 | Access | 0 | Construction Coordinator | 80 | 7 | HR |  |  | 80 | 0 | 560 | 72.8 | 632.8 | 2021-09-14 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting984120210914-4Construction Coordinator7560 | Corbiere and Sons Contracting984120210914-4Construction Coordinator7560INV #148 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9841 | 20210914-4 | 53510604 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-09-14 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting984120210914-4Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting984120210914-4Light Truck - Pick up- After Jan 102487.5INV #148 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9841 | 20210914-4 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 69.5 | Dynamic | 41.4 | 0 |  |  | 3836.4 | 498.732 | 4335.132 | 2021-09-14 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting984120210914-4Dump - Triaxle- After Jan 1069.53836.4 | Corbiere and Sons Contracting984120210914-4Dump - Triaxle- After Jan 1069.53836.4INV #148 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9841 | 20210914-4 | 53510604 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-14 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting984120210914-4Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting984120210914-4Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #148 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9841 | 20210914-4 | 53510604 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-14 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting984120210914-4Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting984120210914-4Excavator - 36 ton- After Jan 10111616.56INV #148 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9840 | 20210913-5 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 141 | HR |  |  | 70 | 0 | 9870 | 1283.1 | 11153.1 | 2021-09-13 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling from Cress Pit to Hare Lake Road Stock Pile - 6 Trucks for day + Previous day travel - Tickets attached. | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting984020210913-5Driver - AZ - After Jan 101419870 | Corbiere and Sons Contracting984020210913-5Driver - AZ - After Jan 101419870INV #148 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9840 | 20210913-5 | 53510604 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2021-09-13 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling from Cress Pit to Hare Lake Road Stock Pile - 6 Trucks for day + Previous day travel - Tickets attached. | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting984020210913-5Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting984020210913-5Operator - Principle - After Jan 1012900INV #148 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9840 | 20210913-5 | 53510604 | Access | 0 | L.O.A. | 210 | 14 | DAY |  |  |  | 0 | 2940 | 382.2 | 3322.2 | 2021-09-13 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling from Cress Pit to Hare Lake Road Stock Pile - 6 Trucks for day + Previous day travel - Tickets attached. | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting984020210913-5L.O.A.142940 | Corbiere and Sons Contracting984020210913-5L.O.A.142940INV #148 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9840 | 20210913-5 | 53510604 | Access | 0 | Construction Coordinator | 80 | 7 | HR |  |  | 80 | 0 | 560 | 72.8 | 632.8 | 2021-09-13 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling from Cress Pit to Hare Lake Road Stock Pile - 6 Trucks for day + Previous day travel - Tickets attached. | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting984020210913-5Construction Coordinator7560 | Corbiere and Sons Contracting984020210913-5Construction Coordinator7560INV #148 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9840 | 20210913-5 | 53510604 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-09-13 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling from Cress Pit to Hare Lake Road Stock Pile - 6 Trucks for day + Previous day travel - Tickets attached. | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting984020210913-5Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting984020210913-5Light Truck - Pick up- After Jan 102487.5INV #148 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9840 | 20210913-5 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 141 | Dynamic | 41.4 | 0 |  |  | 7783.2 | 1011.816 | 8795.016 | 2021-09-13 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling from Cress Pit to Hare Lake Road Stock Pile - 6 Trucks for day + Previous day travel - Tickets attached. | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting984020210913-5Dump - Triaxle- After Jan 101417783.2 | Corbiere and Sons Contracting984020210913-5Dump - Triaxle- After Jan 101417783.2INV #148 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9840 | 20210913-5 | 53510604 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-13 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling from Cress Pit to Hare Lake Road Stock Pile - 6 Trucks for day + Previous day travel - Tickets attached. | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting984020210913-5Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting984020210913-5Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #148 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9840 | 20210913-5 | 53510604 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-13 | 0 | INV #148 | 2021-09-22 | 163 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling from Cress Pit to Hare Lake Road Stock Pile - 6 Trucks for day + Previous day travel - Tickets attached. | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-09-19 |  | 36 | 2021-09-21 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting984020210913-5Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting984020210913-5Excavator - 36 ton- After Jan 10111616.56INV #148 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10074 | 20210927-8 | 53510602 | Access | 0 | Labourer - General - After Jan 10 | 60 | 8 | HR |  |  | 60 | 0 | 480 | 62.4 | 542.4 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C258-C267 | Hare Lake | 0 | 2021-10-05 |  | 37 | 2021-10-06 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1007420210927-8Labourer - General - After Jan 108480 | Corbiere and Sons Contracting1007420210927-8Labourer - General - After Jan 108480INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10074 | 20210927-8 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 32 | HR |  |  | 75 | 0 | 2400 | 312 | 2712 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C258-C267 | Hare Lake | 0 | 2021-10-05 |  | 37 | 2021-10-06 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1007420210927-8Operator - Principle - After Jan 10322400 | Corbiere and Sons Contracting1007420210927-8Operator - Principle - After Jan 10322400INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10074 | 20210927-8 | 53510602 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C258-C267 | Hare Lake | 0 | 2021-10-05 |  | 37 | 2021-10-06 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1007420210927-8L.O.A.4840 | Corbiere and Sons Contracting1007420210927-8L.O.A.4840INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10074 | 20210927-8 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C258-C267 | Hare Lake | 0 | 2021-10-05 |  | 37 | 2021-10-06 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1007420210927-8Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting1007420210927-8Rock Truck - 30 Ton- After Jan 10111518.55INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10074 | 20210927-8 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C258-C267 | Hare Lake | 0 | 2021-10-05 |  | 37 | 2021-10-06 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1007420210927-8Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting1007420210927-8Light Truck - Pick up- After Jan 103731.25INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10074 | 20210927-8 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 7 | HR | 9.16 | 0 |  |  | 85.47 | 11.1111 | 96.5811 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C258-C267 | Hare Lake | 0 | 2021-10-05 |  | 37 | 2021-10-06 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1007420210927-8Excavator Thumb - 30 - 50 ton- After Jan 10785.47 | Corbiere and Sons Contracting1007420210927-8Excavator Thumb - 30 - 50 ton- After Jan 10785.47INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10074 | 20210927-8 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 7 | Dynamic | 103.84 | 0 |  |  | 969.15 | 125.9895 | 1095.1395 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C258-C267 | Hare Lake | 0 | 2021-10-05 |  | 37 | 2021-10-06 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1007420210927-8Excavator - 30 ton- After Jan 107969.15 | Corbiere and Sons Contracting1007420210927-8Excavator - 30 ton- After Jan 107969.15INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10074 | 20210927-8 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C258-C267 | Hare Lake | 0 | 2021-10-05 |  | 37 | 2021-10-06 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1007420210927-8Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting1007420210927-8Excavator - 30 ton- After Jan 10111522.95INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10073 | 20210927-7 | 53510602 | Access | 0 | Labourer - General - After Jan 10 | 60 | 12 | HR |  |  | 60 | 0 | 720 | 93.6 | 813.6 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-05 |  | 37 | 2021-10-06 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1007320210927-7Labourer - General - After Jan 1012720 | Corbiere and Sons Contracting1007320210927-7Labourer - General - After Jan 1012720INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10073 | 20210927-7 | 53510602 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 22 | HR |  |  | 70 | 0 | 1540 | 200.2 | 1740.2 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-05 |  | 37 | 2021-10-06 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1007320210927-7Driver - AZ - After Jan 10221540 | Corbiere and Sons Contracting1007320210927-7Driver - AZ - After Jan 10221540INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10073 | 20210927-7 | 53510602 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 3 | HR |  |  | 70 | 0 | 210 | 27.3 | 237.3 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-05 |  | 37 | 2021-10-06 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1007320210927-7Driver - AZ - After Jan 103210 | Corbiere and Sons Contracting1007320210927-7Driver - AZ - After Jan 103210INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10073 | 20210927-7 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 76 | HR |  |  | 75 | 0 | 5700 | 741 | 6441 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-05 |  | 37 | 2021-10-06 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1007320210927-7Operator - Principle - After Jan 10765700 | Corbiere and Sons Contracting1007320210927-7Operator - Principle - After Jan 10765700INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10073 | 20210927-7 | 53510602 | Access | 0 | L.O.A. | 210 | 9 | DAY |  |  |  | 0 | 1890 | 245.7 | 2135.7 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-05 |  | 37 | 2021-10-06 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1007320210927-7L.O.A.91890 | Corbiere and Sons Contracting1007320210927-7L.O.A.91890INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10073 | 20210927-7 | 53510602 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-05 |  | 37 | 2021-10-06 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1007320210927-7Foreman121140 | Corbiere and Sons Contracting1007320210927-7Foreman121140INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10073 | 20210927-7 | 53510602 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 25 | Dynamic | 91.79 | 0 |  |  | 3059.75 | 397.7675 | 3457.5175 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-05 |  | 37 | 2021-10-06 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1007320210927-7Tractor Trailer - 60 Ton- After Jan 10253059.75 | Corbiere and Sons Contracting1007320210927-7Tractor Trailer - 60 Ton- After Jan 10253059.75INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10073 | 20210927-7 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 36 | Dynamic | 103.54 | 0 |  |  | 4969.8 | 646.074 | 5615.874 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-05 |  | 37 | 2021-10-06 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1007320210927-7Rock Truck - 30 Ton- After Jan 10364969.8 | Corbiere and Sons Contracting1007320210927-7Rock Truck - 30 Ton- After Jan 10364969.8INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10073 | 20210927-7 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 4 | DAY | 182.81 | 0 |  |  | 975 | 126.75 | 1101.75 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-05 |  | 37 | 2021-10-06 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1007320210927-7Light Truck - Pick up- After Jan 104975 | Corbiere and Sons Contracting1007320210927-7Light Truck - Pick up- After Jan 104975INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10073 | 20210927-7 | 53510602 | Access | 0 | ATV - Side by Side w/ roll bar- After Jan 10 | 18.45 | 10 | HR | 13.84 | 0 |  |  | 184.5 | 23.985 | 208.485 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-05 |  | 37 | 2021-10-06 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1007320210927-7ATV - Side by Side w/ roll bar- After Jan 1010184.5 | Corbiere and Sons Contracting1007320210927-7ATV - Side by Side w/ roll bar- After Jan 1010184.5INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10073 | 20210927-7 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-05 |  | 37 | 2021-10-06 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1007320210927-7Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1007320210927-7Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10073 | 20210927-7 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-05 |  | 37 | 2021-10-06 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1007320210927-7Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1007320210927-7Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10073 | 20210927-7 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-05 |  | 37 | 2021-10-06 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1007320210927-7Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting1007320210927-7Excavator - 36 ton- After Jan 10111616.56INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10073 | 20210927-7 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-05 |  | 37 | 2021-10-06 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1007320210927-7Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting1007320210927-7Excavator - 30 ton- After Jan 10111522.95INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10073 | 20210927-7 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-05 |  | 37 | 2021-10-06 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1007320210927-7Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting1007320210927-7Dozer D6 or equal- After Jan 10111446.28INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10072 | 20210927-6 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 36 | HR |  |  | 75 | 0 | 2700 | 351 | 3051 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker | 0 | 2021-10-05 |  | 37 | 2021-10-06 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1007220210927-6Operator - Principle - After Jan 10362700 | Corbiere and Sons Contracting1007220210927-6Operator - Principle - After Jan 10362700INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10072 | 20210927-6 | 53510602 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker | 0 | 2021-10-05 |  | 37 | 2021-10-06 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1007220210927-6L.O.A.3630 | Corbiere and Sons Contracting1007220210927-6L.O.A.3630INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10072 | 20210927-6 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker | 0 | 2021-10-05 |  | 37 | 2021-10-06 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1007220210927-6Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting1007220210927-6Light Truck - Pick up- After Jan 102487.5INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10072 | 20210927-6 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker | 0 | 2021-10-05 |  | 37 | 2021-10-06 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1007220210927-6Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1007220210927-6Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10072 | 20210927-6 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10 | Dynamic | 110.22 | 0 |  |  | 1469.6 | 191.048 | 1660.648 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker | 0 | 2021-10-05 |  | 37 | 2021-10-06 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1007220210927-6Excavator - 36 ton- After Jan 10101469.6 | Corbiere and Sons Contracting1007220210927-6Excavator - 36 ton- After Jan 10101469.6INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10072 | 20210927-6 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker | 0 | 2021-10-05 |  | 37 | 2021-10-06 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1007220210927-6Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting1007220210927-6Excavator - 30 ton- After Jan 10111522.95INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10072 | 20210927-6 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker | 0 | 2021-10-05 |  | 37 | 2021-10-06 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1007220210927-6Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting1007220210927-6Dozer D6 or equal- After Jan 10111446.28INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10083 | 20210927-17 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 56 | HR |  |  | 75 | 0 | 4200 | 546 | 4746 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-05 |  | 58 | 2021-10-06 | [6 empty] | 06 | Corbiere and Sons Contracting1008320210927-17Operator - Principle - After Jan 10564200 | Corbiere and Sons Contracting1008320210927-17Operator - Principle - After Jan 10564200INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10083 | 20210927-17 | 53510602 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-05 |  | 58 | 2021-10-06 | [6 empty] | 06 | Corbiere and Sons Contracting1008320210927-17Foreman121140 | Corbiere and Sons Contracting1008320210927-17Foreman121140INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10083 | 20210927-17 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 22 | Dynamic | 103.54 | 0 |  |  | 3037.1 | 394.823 | 3431.923 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-05 |  | 58 | 2021-10-06 | [6 empty] | 06 | Corbiere and Sons Contracting1008320210927-17Rock Truck - 30 Ton- After Jan 10223037.1 | Corbiere and Sons Contracting1008320210927-17Rock Truck - 30 Ton- After Jan 10223037.1INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10083 | 20210927-17 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 4 | DAY | 182.81 | 0 |  |  | 975 | 126.75 | 1101.75 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-05 |  | 58 | 2021-10-06 | [6 empty] | 06 | Corbiere and Sons Contracting1008320210927-17Light Truck - Pick up- After Jan 104975 | Corbiere and Sons Contracting1008320210927-17Light Truck - Pick up- After Jan 104975INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10083 | 20210927-17 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-05 |  | 58 | 2021-10-06 | [6 empty] | 06 | Corbiere and Sons Contracting1008320210927-17Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1008320210927-17Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10083 | 20210927-17 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-05 |  | 58 | 2021-10-06 | [6 empty] | 06 | Corbiere and Sons Contracting1008320210927-17Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting1008320210927-17Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10083 | 20210927-17 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-05 |  | 58 | 2021-10-06 | [6 empty] | 06 | Corbiere and Sons Contracting1008320210927-17Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting1008320210927-17Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10083 | 20210927-17 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-05 |  | 58 | 2021-10-06 | [6 empty] | 06 | Corbiere and Sons Contracting1008320210927-17Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1008320210927-17Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10083 | 20210927-17 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-05 |  | 58 | 2021-10-06 | [6 empty] | 06 | Corbiere and Sons Contracting1008320210927-17Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting1008320210927-17Excavator - 36 ton- After Jan 10111616.56INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10083 | 20210927-17 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-05 |  | 58 | 2021-10-06 | [6 empty] | 06 | Corbiere and Sons Contracting1008320210927-17Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting1008320210927-17Excavator - 36 ton- After Jan 1091322.64INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10083 | 20210927-17 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-05 |  | 58 | 2021-10-06 | [6 empty] | 06 | Corbiere and Sons Contracting1008320210927-17Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting1008320210927-17Excavator - 36 ton- After Jan 1091322.64INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10083 | 20210927-17 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-05 |  | 58 | 2021-10-06 | [6 empty] | 06 | Corbiere and Sons Contracting1008320210927-17Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting1008320210927-17Excavator - 30 ton- After Jan 10111522.95INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10082 | 20210927-16 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 36 | HR |  |  | 75 | 0 | 2700 | 351 | 3051 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Lake | 0 | 2021-10-05 |  | 58 | 2021-10-06 | [6 empty] | 06 | Corbiere and Sons Contracting1008220210927-16Operator - Principle - After Jan 10362700 | Corbiere and Sons Contracting1008220210927-16Operator - Principle - After Jan 10362700INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10082 | 20210927-16 | 53510602 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Lake | 0 | 2021-10-05 |  | 58 | 2021-10-06 | [6 empty] | 06 | Corbiere and Sons Contracting1008220210927-16L.O.A.3630 | Corbiere and Sons Contracting1008220210927-16L.O.A.3630INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10082 | 20210927-16 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Lake | 0 | 2021-10-05 |  | 58 | 2021-10-06 | [6 empty] | 06 | Corbiere and Sons Contracting1008220210927-16Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting1008220210927-16Rock Truck - 30 Ton- After Jan 10111518.55INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10082 | 20210927-16 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Lake | 0 | 2021-10-05 |  | 58 | 2021-10-06 | [6 empty] | 06 | Corbiere and Sons Contracting1008220210927-16Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting1008220210927-16Light Truck - Pick up- After Jan 102487.5INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10082 | 20210927-16 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Lake | 0 | 2021-10-05 |  | 58 | 2021-10-06 | [6 empty] | 06 | Corbiere and Sons Contracting1008220210927-16Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1008220210927-16Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10082 | 20210927-16 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Lake | 0 | 2021-10-05 |  | 58 | 2021-10-06 | [6 empty] | 06 | Corbiere and Sons Contracting1008220210927-16Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting1008220210927-16Excavator - 36 ton- After Jan 10111616.56INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10082 | 20210927-16 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Lake | 0 | 2021-10-05 |  | 58 | 2021-10-06 | [6 empty] | 06 | Corbiere and Sons Contracting1008220210927-16Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting1008220210927-16Dozer D6 or equal- After Jan 10111446.28INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10081 | 20210927-15 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 15 | HR |  |  | 75 | 0 | 1125 | 146.25 | 1271.25 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acvitites on Mink Creek - Leslie was floated over to get started | 6 | C237-C247 | Mink Creek | 0 | 2021-10-05 |  | 58 | 2021-10-06 | [6 empty] | 06 | Corbiere and Sons Contracting1008120210927-15Operator - Principle - After Jan 10151125 | Corbiere and Sons Contracting1008120210927-15Operator - Principle - After Jan 10151125INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10081 | 20210927-15 | 53510602 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acvitites on Mink Creek - Leslie was floated over to get started | 6 | C237-C247 | Mink Creek | 0 | 2021-10-05 |  | 58 | 2021-10-06 | [6 empty] | 06 | Corbiere and Sons Contracting1008120210927-15L.O.A.1210 | Corbiere and Sons Contracting1008120210927-15L.O.A.1210INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10081 | 20210927-15 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acvitites on Mink Creek - Leslie was floated over to get started | 6 | C237-C247 | Mink Creek | 0 | 2021-10-05 |  | 58 | 2021-10-06 | [6 empty] | 06 | Corbiere and Sons Contracting1008120210927-15Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1008120210927-15Light Truck - Pick up- After Jan 101243.75INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10081 | 20210927-15 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 1 | HR | 9.16 | 0 |  |  | 12.21 | 1.5873 | 13.7973 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acvitites on Mink Creek - Leslie was floated over to get started | 6 | C237-C247 | Mink Creek | 0 | 2021-10-05 |  | 58 | 2021-10-06 | [6 empty] | 06 | Corbiere and Sons Contracting1008120210927-15Excavator Thumb - 30 - 50 ton- After Jan 10112.21 | Corbiere and Sons Contracting1008120210927-15Excavator Thumb - 30 - 50 ton- After Jan 10112.21INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10081 | 20210927-15 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 1 | Dynamic | 110.22 | 0 |  |  | 146.96 | 19.1048 | 166.0648 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acvitites on Mink Creek - Leslie was floated over to get started | 6 | C237-C247 | Mink Creek | 0 | 2021-10-05 |  | 58 | 2021-10-06 | [6 empty] | 06 | Corbiere and Sons Contracting1008120210927-15Excavator - 36 ton- After Jan 101146.96 | Corbiere and Sons Contracting1008120210927-15Excavator - 36 ton- After Jan 101146.96INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10081 | 20210927-15 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acvitites on Mink Creek - Leslie was floated over to get started | 6 | C237-C247 | Mink Creek | 0 | 2021-10-05 |  | 58 | 2021-10-06 | [6 empty] | 06 | Corbiere and Sons Contracting1008120210927-15Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting1008120210927-15Excavator - 36 ton- After Jan 10111616.56INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10080 | 20210927-14 | 53510602 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 10 | HR |  |  | 70 | 0 | 700 | 91 | 791 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Crew floated from Middleton and getting started at this site | 6 | C215-C216 | Little Pic River | 0 | 2021-10-05 |  | 58 | 2021-10-06 | [6 empty] | 06 | Corbiere and Sons Contracting1008020210927-14Driver - AZ - After Jan 1010700 | Corbiere and Sons Contracting1008020210927-14Driver - AZ - After Jan 1010700INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10080 | 20210927-14 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 20 | HR |  |  | 75 | 0 | 1500 | 195 | 1695 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Crew floated from Middleton and getting started at this site | 6 | C215-C216 | Little Pic River | 0 | 2021-10-05 |  | 58 | 2021-10-06 | [6 empty] | 06 | Corbiere and Sons Contracting1008020210927-14Operator - Principle - After Jan 10201500 | Corbiere and Sons Contracting1008020210927-14Operator - Principle - After Jan 10201500INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10080 | 20210927-14 | 53510602 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Crew floated from Middleton and getting started at this site | 6 | C215-C216 | Little Pic River | 0 | 2021-10-05 |  | 58 | 2021-10-06 | [6 empty] | 06 | Corbiere and Sons Contracting1008020210927-14L.O.A.2420 | Corbiere and Sons Contracting1008020210927-14L.O.A.2420INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10080 | 20210927-14 | 53510602 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 10 | Dynamic | 91.79 | 0 |  |  | 1223.9 | 159.107 | 1383.007 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Crew floated from Middleton and getting started at this site | 6 | C215-C216 | Little Pic River | 0 | 2021-10-05 |  | 58 | 2021-10-06 | [6 empty] | 06 | Corbiere and Sons Contracting1008020210927-14Tractor Trailer - 60 Ton- After Jan 10101223.9 | Corbiere and Sons Contracting1008020210927-14Tractor Trailer - 60 Ton- After Jan 10101223.9INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10080 | 20210927-14 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 2.5 | Dynamic | 103.54 | 0 |  |  | 345.125 | 44.8663 | 389.9912 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Crew floated from Middleton and getting started at this site | 6 | C215-C216 | Little Pic River | 0 | 2021-10-05 |  | 58 | 2021-10-06 | [6 empty] | 06 | Corbiere and Sons Contracting1008020210927-14Rock Truck - 30 Ton- After Jan 102.5345.125 | Corbiere and Sons Contracting1008020210927-14Rock Truck - 30 Ton- After Jan 102.5345.125INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10080 | 20210927-14 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Crew floated from Middleton and getting started at this site | 6 | C215-C216 | Little Pic River | 0 | 2021-10-05 |  | 58 | 2021-10-06 | [6 empty] | 06 | Corbiere and Sons Contracting1008020210927-14Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1008020210927-14Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10080 | 20210927-14 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Crew floated from Middleton and getting started at this site | 6 | C215-C216 | Little Pic River | 0 | 2021-10-05 |  | 58 | 2021-10-06 | [6 empty] | 06 | Corbiere and Sons Contracting1008020210927-14Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting1008020210927-14Excavator - 36 ton- After Jan 10111616.56INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10080 | 20210927-14 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 2.5 | Dynamic | 98.61 | 0 |  |  | 328.7 | 42.731 | 371.431 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Crew floated from Middleton and getting started at this site | 6 | C215-C216 | Little Pic River | 0 | 2021-10-05 |  | 58 | 2021-10-06 | [6 empty] | 06 | Corbiere and Sons Contracting1008020210927-14Dozer D6 or equal- After Jan 102.5328.7 | Corbiere and Sons Contracting1008020210927-14Dozer D6 or equal- After Jan 102.5328.7INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10078 | 20210927-12 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 32 | HR |  |  | 75 | 0 | 2400 | 312 | 2712 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Middleton - Completed at 3pm/4pm and floated over to Little Pic/Mink | 6 | C210-C213 | Middleton | 0 | 2021-10-05 |  | 58 | 2021-10-06 | [6 empty] | 06 | Corbiere and Sons Contracting1007820210927-12Operator - Principle - After Jan 10322400 | Corbiere and Sons Contracting1007820210927-12Operator - Principle - After Jan 10322400INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10078 | 20210927-12 | 53510602 | Access | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Middleton - Completed at 3pm/4pm and floated over to Little Pic/Mink | 6 | C210-C213 | Middleton | 0 | 2021-10-05 |  | 58 | 2021-10-06 | [6 empty] | 06 | Corbiere and Sons Contracting1007820210927-12L.O.A.51050 | Corbiere and Sons Contracting1007820210927-12L.O.A.51050INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10078 | 20210927-12 | 53510602 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Middleton - Completed at 3pm/4pm and floated over to Little Pic/Mink | 6 | C210-C213 | Middleton | 0 | 2021-10-05 |  | 58 | 2021-10-06 | [6 empty] | 06 | Corbiere and Sons Contracting1007820210927-12Foreman121140 | Corbiere and Sons Contracting1007820210927-12Foreman121140INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10078 | 20210927-12 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 16 | Dynamic | 103.54 | 0 |  |  | 2208.8 | 287.144 | 2495.944 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Middleton - Completed at 3pm/4pm and floated over to Little Pic/Mink | 6 | C210-C213 | Middleton | 0 | 2021-10-05 |  | 58 | 2021-10-06 | [6 empty] | 06 | Corbiere and Sons Contracting1007820210927-12Rock Truck - 30 Ton- After Jan 10162208.8 | Corbiere and Sons Contracting1007820210927-12Rock Truck - 30 Ton- After Jan 10162208.8INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10078 | 20210927-12 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Middleton - Completed at 3pm/4pm and floated over to Little Pic/Mink | 6 | C210-C213 | Middleton | 0 | 2021-10-05 |  | 58 | 2021-10-06 | [6 empty] | 06 | Corbiere and Sons Contracting1007820210927-12Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting1007820210927-12Light Truck - Pick up- After Jan 103731.25INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10078 | 20210927-12 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 8 | HR | 9.16 | 0 |  |  | 97.68 | 12.6984 | 110.3784 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Middleton - Completed at 3pm/4pm and floated over to Little Pic/Mink | 6 | C210-C213 | Middleton | 0 | 2021-10-05 |  | 58 | 2021-10-06 | [6 empty] | 06 | Corbiere and Sons Contracting1007820210927-12Excavator Thumb - 30 - 50 ton- After Jan 10897.68 | Corbiere and Sons Contracting1007820210927-12Excavator Thumb - 30 - 50 ton- After Jan 10897.68INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10078 | 20210927-12 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 8 | Dynamic | 110.22 | 0 |  |  | 1175.68 | 152.8384 | 1328.5184 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Middleton - Completed at 3pm/4pm and floated over to Little Pic/Mink | 6 | C210-C213 | Middleton | 0 | 2021-10-05 |  | 58 | 2021-10-06 | [6 empty] | 06 | Corbiere and Sons Contracting1007820210927-12Excavator - 36 ton- After Jan 1081175.68 | Corbiere and Sons Contracting1007820210927-12Excavator - 36 ton- After Jan 1081175.68INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10078 | 20210927-12 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 8 | Dynamic | 98.61 | 0 |  |  | 1051.84 | 136.7392 | 1188.5792 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Middleton - Completed at 3pm/4pm and floated over to Little Pic/Mink | 6 | C210-C213 | Middleton | 0 | 2021-10-05 |  | 58 | 2021-10-06 | [6 empty] | 06 | Corbiere and Sons Contracting1007820210927-12Dozer D6 or equal- After Jan 1081051.84 | Corbiere and Sons Contracting1007820210927-12Dozer D6 or equal- After Jan 1081051.84INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10076 | 20210927-10 | 53510602 | Access | 0 | Labourer - General - After Jan 10 | 60 | 8 | HR |  |  | 60 | 0 | 480 | 62.4 | 542.4 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake West | 0 | 2021-10-05 |  | 37 | 2021-10-06 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1007620210927-10Labourer - General - After Jan 108480 | Corbiere and Sons Contracting1007620210927-10Labourer - General - After Jan 108480INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10076 | 20210927-10 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 56 | HR |  |  | 75 | 0 | 4200 | 546 | 4746 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake West | 0 | 2021-10-05 |  | 37 | 2021-10-06 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1007620210927-10Operator - Principle - After Jan 10564200 | Corbiere and Sons Contracting1007620210927-10Operator - Principle - After Jan 10564200INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10076 | 20210927-10 | 53510602 | Access | 0 | L.O.A. | 210 | 7 | DAY |  |  |  | 0 | 1470 | 191.1 | 1661.1 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake West | 0 | 2021-10-05 |  | 37 | 2021-10-06 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1007620210927-10L.O.A.71470 | Corbiere and Sons Contracting1007620210927-10L.O.A.71470INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10076 | 20210927-10 | 53510602 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake West | 0 | 2021-10-05 |  | 37 | 2021-10-06 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1007620210927-10Foreman121140 | Corbiere and Sons Contracting1007620210927-10Foreman121140INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10076 | 20210927-10 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake West | 0 | 2021-10-05 |  | 37 | 2021-10-06 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1007620210927-10Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting1007620210927-10Rock Truck - 30 Ton- After Jan 10111518.55INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10076 | 20210927-10 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake West | 0 | 2021-10-05 |  | 37 | 2021-10-06 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1007620210927-10Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting1007620210927-10Light Truck - Pick up- After Jan 102487.5INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10076 | 20210927-10 | 53510602 | Access | 0 | ATV - Side by Side w/ roll bar- After Jan 10 | 18.45 | 10 | HR | 13.84 | 0 |  |  | 184.5 | 23.985 | 208.485 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake West | 0 | 2021-10-05 |  | 37 | 2021-10-06 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1007620210927-10ATV - Side by Side w/ roll bar- After Jan 1010184.5 | Corbiere and Sons Contracting1007620210927-10ATV - Side by Side w/ roll bar- After Jan 1010184.5INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10076 | 20210927-10 | 53510602 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 11 | HR | 47.54 | 0 |  |  | 697.18 | 90.6334 | 787.8134 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake West | 0 | 2021-10-05 |  | 37 | 2021-10-06 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1007620210927-10Excavator Hammer - 30 - 50 ton- After Jan 1011697.18 | Corbiere and Sons Contracting1007620210927-10Excavator Hammer - 30 - 50 ton- After Jan 1011697.18INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10076 | 20210927-10 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 22 | Dynamic | 110.22 | 0 |  |  | 3233.12 | 420.3056 | 3653.4256 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake West | 0 | 2021-10-05 |  | 37 | 2021-10-06 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1007620210927-10Excavator - 36 ton- After Jan 10223233.12 | Corbiere and Sons Contracting1007620210927-10Excavator - 36 ton- After Jan 10223233.12INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10076 | 20210927-10 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 7 | Dynamic | 103.84 | 0 |  |  | 969.15 | 125.9895 | 1095.1395 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake West | 0 | 2021-10-05 |  | 37 | 2021-10-06 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1007620210927-10Excavator - 30 ton- After Jan 107969.15 | Corbiere and Sons Contracting1007620210927-10Excavator - 30 ton- After Jan 107969.15INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10076 | 20210927-10 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake West | 0 | 2021-10-05 |  | 37 | 2021-10-06 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1007620210927-10Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting1007620210927-10Dozer D6 or equal- After Jan 10111446.28INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10057 | 20210926-9 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 60 | HR |  |  | 75 | 0 | 4500 | 585 | 5085 | 2021-09-26 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-04 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1005720210926-9Operator - Principle - After Jan 10604500 | Corbiere and Sons Contracting1005720210926-9Operator - Principle - After Jan 10604500INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10057 | 20210926-9 | 53510602 | Access | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2021-09-26 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-04 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1005720210926-9L.O.A.61260 | Corbiere and Sons Contracting1005720210926-9L.O.A.61260INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10057 | 20210926-9 | 53510602 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-09-26 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-04 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1005720210926-9Foreman121140 | Corbiere and Sons Contracting1005720210926-9Foreman121140INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10057 | 20210926-9 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-09-26 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-04 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1005720210926-9Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting1005720210926-9Rock Truck - 30 Ton- After Jan 10111518.55INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10057 | 20210926-9 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2021-09-26 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-04 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1005720210926-9Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting1005720210926-9Light Truck - Pick up- After Jan 103731.25INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10057 | 20210926-9 | 53510602 | Access | 0 | ATV - Side by Side w/ roll bar- After Jan 10 | 18.45 | 10 | HR | 13.84 | 0 |  |  | 184.5 | 23.985 | 208.485 | 2021-09-26 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-04 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1005720210926-9ATV - Side by Side w/ roll bar- After Jan 1010184.5 | Corbiere and Sons Contracting1005720210926-9ATV - Side by Side w/ roll bar- After Jan 1010184.5INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10057 | 20210926-9 | 53510602 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 11 | HR | 47.54 | 0 |  |  | 697.18 | 90.6334 | 787.8134 | 2021-09-26 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-04 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1005720210926-9Excavator Hammer - 30 - 50 ton- After Jan 1011697.18 | Corbiere and Sons Contracting1005720210926-9Excavator Hammer - 30 - 50 ton- After Jan 1011697.18INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10057 | 20210926-9 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 22 | Dynamic | 110.22 | 0 |  |  | 3233.12 | 420.3056 | 3653.4256 | 2021-09-26 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-04 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1005720210926-9Excavator - 36 ton- After Jan 10223233.12 | Corbiere and Sons Contracting1005720210926-9Excavator - 36 ton- After Jan 10223233.12INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10057 | 20210926-9 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-26 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-04 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1005720210926-9Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting1005720210926-9Excavator - 30 ton- After Jan 10111522.95INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10057 | 20210926-9 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-09-26 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-04 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1005720210926-9Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting1005720210926-9Dozer D6 or equal- After Jan 10111446.28INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10056 | 20210926-8 | 53510602 | Access | 0 | Labourer - General - After Jan 10 | 60 | 12 | HR |  |  | 60 | 0 | 720 | 93.6 | 813.6 | 2021-09-26 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C258-C267 | Hare Lake | 0 | 2021-10-04 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1005620210926-8Labourer - General - After Jan 1012720 | Corbiere and Sons Contracting1005620210926-8Labourer - General - After Jan 1012720INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10056 | 20210926-8 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 48 | HR |  |  | 75 | 0 | 3600 | 468 | 4068 | 2021-09-26 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C258-C267 | Hare Lake | 0 | 2021-10-04 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1005620210926-8Operator - Principle - After Jan 10483600 | Corbiere and Sons Contracting1005620210926-8Operator - Principle - After Jan 10483600INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10056 | 20210926-8 | 53510602 | Access | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2021-09-26 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C258-C267 | Hare Lake | 0 | 2021-10-04 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1005620210926-8L.O.A.51050 | Corbiere and Sons Contracting1005620210926-8L.O.A.51050INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10056 | 20210926-8 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-09-26 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C258-C267 | Hare Lake | 0 | 2021-10-04 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1005620210926-8Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting1005620210926-8Rock Truck - 30 Ton- After Jan 10111518.55INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10056 | 20210926-8 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-09-26 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C258-C267 | Hare Lake | 0 | 2021-10-04 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1005620210926-8Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting1005620210926-8Light Truck - Pick up- After Jan 102487.5INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10056 | 20210926-8 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-26 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C258-C267 | Hare Lake | 0 | 2021-10-04 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1005620210926-8Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1005620210926-8Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10056 | 20210926-8 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-26 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C258-C267 | Hare Lake | 0 | 2021-10-04 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1005620210926-8Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting1005620210926-8Excavator - 30 ton- After Jan 10111522.95INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10056 | 20210926-8 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-26 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C258-C267 | Hare Lake | 0 | 2021-10-04 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1005620210926-8Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting1005620210926-8Excavator - 30 ton- After Jan 10111522.95INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10056 | 20210926-8 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 9 | Dynamic | 98.61 | 0 |  |  | 1183.32 | 153.8316 | 1337.1516 | 2021-09-26 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C258-C267 | Hare Lake | 0 | 2021-10-04 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1005620210926-8Dozer D6 or equal- After Jan 1091183.32 | Corbiere and Sons Contracting1005620210926-8Dozer D6 or equal- After Jan 1091183.32INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10055 | 20210926-7 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 72 | HR |  |  | 75 | 0 | 5400 | 702 | 6102 | 2021-09-29 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-04 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1005520210926-7Operator - Principle - After Jan 10725400 | Corbiere and Sons Contracting1005520210926-7Operator - Principle - After Jan 10725400INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10055 | 20210926-7 | 53510602 | Access | 0 | L.O.A. | 210 | 7 | DAY |  |  |  | 0 | 1470 | 191.1 | 1661.1 | 2021-09-29 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-04 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1005520210926-7L.O.A.71470 | Corbiere and Sons Contracting1005520210926-7L.O.A.71470INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10055 | 20210926-7 | 53510602 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-09-29 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-04 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1005520210926-7Foreman121140 | Corbiere and Sons Contracting1005520210926-7Foreman121140INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10055 | 20210926-7 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 33 | Dynamic | 103.54 | 0 |  |  | 4555.65 | 592.2345 | 5147.8845 | 2021-09-29 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-04 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1005520210926-7Rock Truck - 30 Ton- After Jan 10334555.65 | Corbiere and Sons Contracting1005520210926-7Rock Truck - 30 Ton- After Jan 10334555.65INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10055 | 20210926-7 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 4 | DAY | 182.81 | 0 |  |  | 975 | 126.75 | 1101.75 | 2021-09-29 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-04 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1005520210926-7Light Truck - Pick up- After Jan 104975 | Corbiere and Sons Contracting1005520210926-7Light Truck - Pick up- After Jan 104975INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10055 | 20210926-7 | 53510602 | Access | 0 | ATV - Side by Side w/ roll bar- After Jan 10 | 18.45 | 10 | HR | 13.84 | 0 |  |  | 184.5 | 23.985 | 208.485 | 2021-09-29 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-04 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1005520210926-7ATV - Side by Side w/ roll bar- After Jan 1010184.5 | Corbiere and Sons Contracting1005520210926-7ATV - Side by Side w/ roll bar- After Jan 1010184.5INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10055 | 20210926-7 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-29 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-04 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1005520210926-7Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1005520210926-7Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10055 | 20210926-7 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-29 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-04 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1005520210926-7Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1005520210926-7Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10055 | 20210926-7 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-29 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-04 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1005520210926-7Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting1005520210926-7Excavator - 36 ton- After Jan 10111616.56INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10055 | 20210926-7 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-29 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-04 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1005520210926-7Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting1005520210926-7Excavator - 30 ton- After Jan 10111522.95INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10055 | 20210926-7 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-09-29 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-04 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1005520210926-7Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting1005520210926-7Dozer D6 or equal- After Jan 10111446.28INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10054 | 20210926-6 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 36 | HR |  |  | 75 | 0 | 2700 | 351 | 3051 | 2021-09-26 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-10-04 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1005420210926-6Operator - Principle - After Jan 10362700 | Corbiere and Sons Contracting1005420210926-6Operator - Principle - After Jan 10362700INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10054 | 20210926-6 | 53510602 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-09-26 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-10-04 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1005420210926-6L.O.A.3630 | Corbiere and Sons Contracting1005420210926-6L.O.A.3630INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10054 | 20210926-6 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-09-26 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-10-04 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1005420210926-6Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting1005420210926-6Light Truck - Pick up- After Jan 102487.5INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10054 | 20210926-6 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-26 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-10-04 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1005420210926-6Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1005420210926-6Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10054 | 20210926-6 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10 | Dynamic | 110.22 | 0 |  |  | 1469.6 | 191.048 | 1660.648 | 2021-09-26 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-10-04 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1005420210926-6Excavator - 36 ton- After Jan 10101469.6 | Corbiere and Sons Contracting1005420210926-6Excavator - 36 ton- After Jan 10101469.6INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10054 | 20210926-6 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-26 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-10-04 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1005420210926-6Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting1005420210926-6Excavator - 30 ton- After Jan 10111522.95INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10054 | 20210926-6 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-09-26 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-10-04 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1005420210926-6Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting1005420210926-6Dozer D6 or equal- After Jan 10111446.28INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10060 | 20210926-12 | 53510602 | Access | 0 | Labourer - General - After Jan 10 | 60 | 24 | HR |  |  | 60 | 0 | 1440 | 187.2 | 1627.2 | 2021-09-26 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-10-04 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1006020210926-12Labourer - General - After Jan 10241440 | Corbiere and Sons Contracting1006020210926-12Labourer - General - After Jan 10241440INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10060 | 20210926-12 | 53510602 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 12 | HR |  |  | 70 | 0 | 840 | 109.2 | 949.2 | 2021-09-26 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-10-04 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1006020210926-12Driver - AZ - After Jan 1012840 | Corbiere and Sons Contracting1006020210926-12Driver - AZ - After Jan 1012840INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10060 | 20210926-12 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 36 | HR |  |  | 75 | 0 | 2700 | 351 | 3051 | 2021-09-26 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-10-04 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1006020210926-12Operator - Principle - After Jan 10362700 | Corbiere and Sons Contracting1006020210926-12Operator - Principle - After Jan 10362700INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10060 | 20210926-12 | 53510602 | Access | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2021-09-26 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-10-04 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1006020210926-12L.O.A.61260 | Corbiere and Sons Contracting1006020210926-12L.O.A.61260INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10060 | 20210926-12 | 53510602 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 12 | Dynamic | 91.79 | 0 |  |  | 1468.68 | 190.9284 | 1659.6084 | 2021-09-26 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-10-04 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1006020210926-12Tractor Trailer - 60 Ton- After Jan 10121468.68 | Corbiere and Sons Contracting1006020210926-12Tractor Trailer - 60 Ton- After Jan 10121468.68INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10060 | 20210926-12 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-09-26 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-10-04 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1006020210926-12Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting1006020210926-12Rock Truck - 30 Ton- After Jan 10111518.55INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10060 | 20210926-12 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2021-09-26 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-10-04 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1006020210926-12Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting1006020210926-12Light Truck - Pick up- After Jan 103731.25INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10060 | 20210926-12 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-26 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-10-04 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1006020210926-12Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1006020210926-12Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10060 | 20210926-12 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-26 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-10-04 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1006020210926-12Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting1006020210926-12Excavator - 36 ton- After Jan 10111616.56INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10060 | 20210926-12 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-09-26 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-10-04 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1006020210926-12Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting1006020210926-12Dozer D6 or equal- After Jan 10111446.28INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10059 | 20210926-11 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2021-09-26 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acvitites on Mink Creek | 6 | C237-C247 | Mink | 0 | 2021-10-04 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1005920210926-11Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1005920210926-11Operator - Principle - After Jan 1012900INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10059 | 20210926-11 | 53510602 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-09-26 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acvitites on Mink Creek | 6 | C237-C247 | Mink | 0 | 2021-10-04 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1005920210926-11L.O.A.1210 | Corbiere and Sons Contracting1005920210926-11L.O.A.1210INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10059 | 20210926-11 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-09-26 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acvitites on Mink Creek | 6 | C237-C247 | Mink | 0 | 2021-10-04 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1005920210926-11Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1005920210926-11Light Truck - Pick up- After Jan 101243.75INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10059 | 20210926-11 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-26 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acvitites on Mink Creek | 6 | C237-C247 | Mink | 0 | 2021-10-04 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1005920210926-11Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting1005920210926-11Excavator - 36 ton- After Jan 10111616.56INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10058 | 20210926-10 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 48 | HR |  |  | 75 | 0 | 3600 | 468 | 4068 | 2021-09-26 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Middleton | 6 | C210-C213 | Middleton | 0 | 2021-10-04 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1005820210926-10Operator - Principle - After Jan 10483600 | Corbiere and Sons Contracting1005820210926-10Operator - Principle - After Jan 10483600INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10058 | 20210926-10 | 53510602 | Access | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2021-09-26 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Middleton | 6 | C210-C213 | Middleton | 0 | 2021-10-04 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1005820210926-10L.O.A.51050 | Corbiere and Sons Contracting1005820210926-10L.O.A.51050INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10058 | 20210926-10 | 53510602 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-09-26 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Middleton | 6 | C210-C213 | Middleton | 0 | 2021-10-04 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1005820210926-10Foreman121140 | Corbiere and Sons Contracting1005820210926-10Foreman121140INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10058 | 20210926-10 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 18 | Dynamic | 103.54 | 0 |  |  | 2484.9 | 323.037 | 2807.937 | 2021-09-26 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Middleton | 6 | C210-C213 | Middleton | 0 | 2021-10-04 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1005820210926-10Rock Truck - 30 Ton- After Jan 10182484.9 | Corbiere and Sons Contracting1005820210926-10Rock Truck - 30 Ton- After Jan 10182484.9INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10058 | 20210926-10 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2021-09-26 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Middleton | 6 | C210-C213 | Middleton | 0 | 2021-10-04 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1005820210926-10Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting1005820210926-10Light Truck - Pick up- After Jan 103731.25INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10058 | 20210926-10 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-09-26 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Middleton | 6 | C210-C213 | Middleton | 0 | 2021-10-04 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1005820210926-10Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting1005820210926-10Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10058 | 20210926-10 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-09-26 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Middleton | 6 | C210-C213 | Middleton | 0 | 2021-10-04 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1005820210926-10Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting1005820210926-10Excavator - 36 ton- After Jan 1091322.64INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10058 | 20210926-10 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-09-26 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Middleton | 6 | C210-C213 | Middleton | 0 | 2021-10-04 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1005820210926-10Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting1005820210926-10Dozer D6 or equal- After Jan 10111446.28INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10024 | 20210924-8 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 36 | HR |  |  | 75 | 0 | 2700 | 351 | 3051 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C258-C267 | Hare Lake | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1002420210924-8Operator - Principle - After Jan 10362700 | Corbiere and Sons Contracting1002420210924-8Operator - Principle - After Jan 10362700INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10024 | 20210924-8 | 53510602 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C258-C267 | Hare Lake | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1002420210924-8L.O.A.3630 | Corbiere and Sons Contracting1002420210924-8L.O.A.3630INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10024 | 20210924-8 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C258-C267 | Hare Lake | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1002420210924-8Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting1002420210924-8Rock Truck - 30 Ton- After Jan 10111518.55INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10024 | 20210924-8 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C258-C267 | Hare Lake | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1002420210924-8Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting1002420210924-8Light Truck - Pick up- After Jan 102487.5INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10024 | 20210924-8 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C258-C267 | Hare Lake | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1002420210924-8Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting1002420210924-8Excavator - 30 ton- After Jan 10111522.95INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10024 | 20210924-8 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C258-C267 | Hare Lake | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1002420210924-8Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting1002420210924-8Dozer D6 or equal- After Jan 10111446.28INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10023 | 20210924-7 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 60 | HR |  |  | 75 | 0 | 4500 | 585 | 5085 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1002320210924-7Operator - Principle - After Jan 10604500 | Corbiere and Sons Contracting1002320210924-7Operator - Principle - After Jan 10604500INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10023 | 20210924-7 | 53510602 | Access | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1002320210924-7L.O.A.61260 | Corbiere and Sons Contracting1002320210924-7L.O.A.61260INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10023 | 20210924-7 | 53510602 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1002320210924-7Foreman121140 | Corbiere and Sons Contracting1002320210924-7Foreman121140INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10023 | 20210924-7 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 25 | Dynamic | 103.54 | 0 |  |  | 3451.25 | 448.6625 | 3899.9125 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1002320210924-7Rock Truck - 30 Ton- After Jan 10253451.25 | Corbiere and Sons Contracting1002320210924-7Rock Truck - 30 Ton- After Jan 10253451.25INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10023 | 20210924-7 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 4 | DAY | 182.81 | 0 |  |  | 975 | 126.75 | 1101.75 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1002320210924-7Light Truck - Pick up- After Jan 104975 | Corbiere and Sons Contracting1002320210924-7Light Truck - Pick up- After Jan 104975INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10023 | 20210924-7 | 53510602 | Access | 0 | ATV - Side by Side w/ roll bar- After Jan 10 | 18.45 | 10 | HR | 13.84 | 0 |  |  | 184.5 | 23.985 | 208.485 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1002320210924-7ATV - Side by Side w/ roll bar- After Jan 1010184.5 | Corbiere and Sons Contracting1002320210924-7ATV - Side by Side w/ roll bar- After Jan 1010184.5INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10023 | 20210924-7 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 9.16 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1002320210924-7Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting1002320210924-7Excavator Thumb - 30 - 50 ton- After Jan 1010122.1INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10023 | 20210924-7 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 9.16 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1002320210924-7Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting1002320210924-7Excavator Thumb - 30 - 50 ton- After Jan 1010122.1INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10023 | 20210924-7 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10 | Dynamic | 110.22 | 0 |  |  | 1469.6 | 191.048 | 1660.648 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1002320210924-7Excavator - 36 ton- After Jan 10101469.6 | Corbiere and Sons Contracting1002320210924-7Excavator - 36 ton- After Jan 10101469.6INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10023 | 20210924-7 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10 | Dynamic | 103.84 | 0 |  |  | 1384.5 | 179.985 | 1564.485 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1002320210924-7Excavator - 30 ton- After Jan 10101384.5 | Corbiere and Sons Contracting1002320210924-7Excavator - 30 ton- After Jan 10101384.5INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10023 | 20210924-7 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10 | Dynamic | 98.61 | 0 |  |  | 1314.8 | 170.924 | 1485.724 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1002320210924-7Dozer D6 or equal- After Jan 10101314.8 | Corbiere and Sons Contracting1002320210924-7Dozer D6 or equal- After Jan 10101314.8INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10022 | 20210924-6 | 53510602 | Access | 0 | Labourer - General - After Jan 10 | 60 | 11 | HR |  |  | 60 | 0 | 660 | 85.8 | 745.8 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1002220210924-6Labourer - General - After Jan 1011660 | Corbiere and Sons Contracting1002220210924-6Labourer - General - After Jan 1011660INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10022 | 20210924-6 | 53510602 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 5 | HR |  |  | 70 | 0 | 350 | 45.5 | 395.5 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1002220210924-6Driver - AZ - After Jan 105350 | Corbiere and Sons Contracting1002220210924-6Driver - AZ - After Jan 105350INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10022 | 20210924-6 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 39 | HR |  |  | 75 | 0 | 2925 | 380.25 | 3305.25 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1002220210924-6Operator - Principle - After Jan 10392925 | Corbiere and Sons Contracting1002220210924-6Operator - Principle - After Jan 10392925INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10022 | 20210924-6 | 53510602 | Access | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1002220210924-6L.O.A.61260 | Corbiere and Sons Contracting1002220210924-6L.O.A.61260INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10022 | 20210924-6 | 53510602 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 5 | Dynamic | 91.79 | 0 |  |  | 611.95 | 79.5535 | 691.5035 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1002220210924-6Tractor Trailer - 60 Ton- After Jan 105611.95 | Corbiere and Sons Contracting1002220210924-6Tractor Trailer - 60 Ton- After Jan 105611.95INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10022 | 20210924-6 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 4 | Dynamic | 103.54 | 0 |  |  | 552.2 | 71.786 | 623.986 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1002220210924-6Rock Truck - 30 Ton- After Jan 104552.2 | Corbiere and Sons Contracting1002220210924-6Rock Truck - 30 Ton- After Jan 104552.2INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10022 | 20210924-6 | 53510602 | Access | 0 | Light Truck w/ Tandum Trailer- After Jan 10 | 337.5 | 1 | DAY | 253.13 | 0 |  |  | 337.5 | 43.875 | 381.375 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1002220210924-6Light Truck w/ Tandum Trailer- After Jan 101337.5 | Corbiere and Sons Contracting1002220210924-6Light Truck w/ Tandum Trailer- After Jan 101337.5INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10022 | 20210924-6 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1002220210924-6Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting1002220210924-6Light Truck - Pick up- After Jan 102487.5INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10022 | 20210924-6 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 9.16 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1002220210924-6Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting1002220210924-6Excavator Thumb - 30 - 50 ton- After Jan 1010122.1INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10022 | 20210924-6 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10 | Dynamic | 110.22 | 0 |  |  | 1469.6 | 191.048 | 1660.648 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1002220210924-6Excavator - 36 ton- After Jan 10101469.6 | Corbiere and Sons Contracting1002220210924-6Excavator - 36 ton- After Jan 10101469.6INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10022 | 20210924-6 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10 | Dynamic | 103.84 | 0 |  |  | 1384.5 | 179.985 | 1564.485 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1002220210924-6Excavator - 30 ton- After Jan 10101384.5 | Corbiere and Sons Contracting1002220210924-6Excavator - 30 ton- After Jan 10101384.5INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10022 | 20210924-6 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10 | Dynamic | 98.61 | 0 |  |  | 1314.8 | 170.924 | 1485.724 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1002220210924-6Dozer D6 or equal- After Jan 10101314.8 | Corbiere and Sons Contracting1002220210924-6Dozer D6 or equal- After Jan 10101314.8INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10021 | 20210924-5 | 53510602 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 13 | HR |  |  | 70 | 0 | 910 | 118.3 | 1028.3 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 4 Trucks from Padda and 1 Valentino hauling to Neys Road | 6 | C219-C236 | Neys | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1002120210924-5Driver - AZ - After Jan 1013910 | Corbiere and Sons Contracting1002120210924-5Driver - AZ - After Jan 1013910INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10021 | 20210924-5 | 53510602 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 46.5 | HR |  |  | 70 | 0 | 3255 | 423.15 | 3678.15 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 4 Trucks from Padda and 1 Valentino hauling to Neys Road | 6 | C219-C236 | Neys | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1002120210924-5Driver - AZ - After Jan 1046.53255 | Corbiere and Sons Contracting1002120210924-5Driver - AZ - After Jan 1046.53255INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10021 | 20210924-5 | 53510602 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 4 Trucks from Padda and 1 Valentino hauling to Neys Road | 6 | C219-C236 | Neys | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1002120210924-5L.O.A.4840 | Corbiere and Sons Contracting1002120210924-5L.O.A.4840INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10021 | 20210924-5 | 53510602 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 13 | Dynamic | 41.4 | 0 |  |  | 717.6 | 93.288 | 810.888 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 4 Trucks from Padda and 1 Valentino hauling to Neys Road | 6 | C219-C236 | Neys | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1002120210924-5Dump - Triaxle- After Jan 1013717.6 | Corbiere and Sons Contracting1002120210924-5Dump - Triaxle- After Jan 1013717.6INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10021 | 20210924-5 | 53510602 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 46 | Dynamic | 41.4 | 0 |  |  | 2539.2 | 330.096 | 2869.296 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 4 Trucks from Padda and 1 Valentino hauling to Neys Road | 6 | C219-C236 | Neys | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1002120210924-5Dump - Triaxle- After Jan 10462539.2 | Corbiere and Sons Contracting1002120210924-5Dump - Triaxle- After Jan 10462539.2INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10020 | 20210924-4 | 53510602 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 23.5 | HR |  |  | 70 | 0 | 1645 | 213.85 | 1858.85 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 3 Trucks from Padda hauling over to Pic River West | 6 | D018-D024 | Pic River | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1002020210924-4Driver - AZ - After Jan 1023.51645 | Corbiere and Sons Contracting1002020210924-4Driver - AZ - After Jan 1023.51645INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10020 | 20210924-4 | 53510602 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 3 Trucks from Padda hauling over to Pic River West | 6 | D018-D024 | Pic River | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1002020210924-4L.O.A.2420 | Corbiere and Sons Contracting1002020210924-4L.O.A.2420INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10020 | 20210924-4 | 53510602 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 23.5 | Dynamic | 41.4 | 0 |  |  | 1297.2 | 168.636 | 1465.836 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 3 Trucks from Padda hauling over to Pic River West | 6 | D018-D024 | Pic River | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1002020210924-4Dump - Triaxle- After Jan 1023.51297.2 | Corbiere and Sons Contracting1002020210924-4Dump - Triaxle- After Jan 1023.51297.2INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10019 | 20210924-3 | 53510602 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 71 | HR |  |  | 70 | 0 | 4970 | 646.1 | 5616.1 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit (6 trucks) | 6 | C257-C267 | Hare Lake | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1001920210924-3Driver - AZ - After Jan 10714970 | Corbiere and Sons Contracting1001920210924-3Driver - AZ - After Jan 10714970INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10019 | 20210924-3 | 53510602 | Access | 0 | L.O.A. | 210 | 7 | DAY |  |  |  | 0 | 1470 | 191.1 | 1661.1 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit (6 trucks) | 6 | C257-C267 | Hare Lake | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1001920210924-3L.O.A.71470 | Corbiere and Sons Contracting1001920210924-3L.O.A.71470INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10019 | 20210924-3 | 53510602 | Access | 0 | Construction Coordinator | 80 | 7 | HR |  |  | 80 | 0 | 560 | 72.8 | 632.8 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit (6 trucks) | 6 | C257-C267 | Hare Lake | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1001920210924-3Construction Coordinator7560 | Corbiere and Sons Contracting1001920210924-3Construction Coordinator7560INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10019 | 20210924-3 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit (6 trucks) | 6 | C257-C267 | Hare Lake | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1001920210924-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1001920210924-3Light Truck - Pick up- After Jan 101243.75INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10019 | 20210924-3 | 53510602 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 71 | Dynamic | 41.4 | 0 |  |  | 3919.2 | 509.496 | 4428.696 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit (6 trucks) | 6 | C257-C267 | Hare Lake | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1001920210924-3Dump - Triaxle- After Jan 10713919.2 | Corbiere and Sons Contracting1001920210924-3Dump - Triaxle- After Jan 10713919.2INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10032 | 20210924-16 | 53510602 | Access | 0 | L.O.A. | 210 | 0.5 | DAY |  |  | 0 | 0 | 105 | 13.65 | 118.65 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Billable time for Safety Advisor working in WF6 | 6 | C130-C277 | WF6 | 0 | 2021-09-30 |  | 36 | 2021-10-04 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1003220210924-16L.O.A.0.5105 | Corbiere and Sons Contracting1003220210924-16L.O.A.0.5105INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10032 | 20210924-16 | 53510602 | Access | 0 | Safety Advisor | 85 | 7 | HR |  |  | 0 | 0 | 595 | 77.35 | 672.35 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Billable time for Safety Advisor working in WF6 | 6 | C130-C277 | WF6 | 0 | 2021-09-30 |  | 36 | 2021-10-04 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1003220210924-16Safety Advisor7595 | Corbiere and Sons Contracting1003220210924-16Safety Advisor7595INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10032 | 20210924-16 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Billable time for Safety Advisor working in WF6 | 6 | C130-C277 | WF6 | 0 | 2021-09-30 |  | 36 | 2021-10-04 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1003220210924-16Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1003220210924-16Light Truck - Pick up- After Jan 101243.75INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10031 | 20210924-15 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 60 | HR |  |  | 0 | 0 | 4500 | 585 | 5085 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1003120210924-15Operator - Principle - After Jan 10604500 | Corbiere and Sons Contracting1003120210924-15Operator - Principle - After Jan 10604500INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10031 | 20210924-15 | 53510602 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 0 | 0 | 1140 | 148.2 | 1288.2 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1003120210924-15Foreman121140 | Corbiere and Sons Contracting1003120210924-15Foreman121140INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10031 | 20210924-15 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 22 | Dynamic | 0 | 0 |  |  | 3037.1 | 394.823 | 3431.923 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1003120210924-15Rock Truck - 30 Ton- After Jan 10223037.1 | Corbiere and Sons Contracting1003120210924-15Rock Truck - 30 Ton- After Jan 10223037.1INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10031 | 20210924-15 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 4 | DAY | 0 | 0 |  |  | 975 | 126.75 | 1101.75 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1003120210924-15Light Truck - Pick up- After Jan 104975 | Corbiere and Sons Contracting1003120210924-15Light Truck - Pick up- After Jan 104975INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10031 | 20210924-15 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 0 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1003120210924-15Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1003120210924-15Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10031 | 20210924-15 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 0 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1003120210924-15Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1003120210924-15Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10031 | 20210924-15 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 0 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1003120210924-15Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1003120210924-15Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10031 | 20210924-15 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 0 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1003120210924-15Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1003120210924-15Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10031 | 20210924-15 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 0 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1003120210924-15Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting1003120210924-15Excavator - 36 ton- After Jan 10111616.56INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10031 | 20210924-15 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 0 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1003120210924-15Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting1003120210924-15Excavator - 36 ton- After Jan 10111616.56INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10031 | 20210924-15 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 0 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1003120210924-15Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting1003120210924-15Excavator - 36 ton- After Jan 10111616.56INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10031 | 20210924-15 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 0 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1003120210924-15Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting1003120210924-15Excavator - 30 ton- After Jan 10111522.95INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10030 | 20210924-14 | 53510602 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 6 | HR |  |  | 70 | 0 | 420 | 54.6 | 474.6 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acvitites on Mink Creek | 6 | C244-C247 | Mink Creek | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1003020210924-14Driver - AZ - After Jan 106420 | Corbiere and Sons Contracting1003020210924-14Driver - AZ - After Jan 106420INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10030 | 20210924-14 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 10 | HR |  |  | 75 | 0 | 750 | 97.5 | 847.5 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acvitites on Mink Creek | 6 | C244-C247 | Mink Creek | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1003020210924-14Operator - Principle - After Jan 1010750 | Corbiere and Sons Contracting1003020210924-14Operator - Principle - After Jan 1010750INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10030 | 20210924-14 | 53510602 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acvitites on Mink Creek | 6 | C244-C247 | Mink Creek | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1003020210924-14L.O.A.1210 | Corbiere and Sons Contracting1003020210924-14L.O.A.1210INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10030 | 20210924-14 | 53510602 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 6 | Dynamic | 91.79 | 0 |  |  | 734.34 | 95.4642 | 829.8042 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acvitites on Mink Creek | 6 | C244-C247 | Mink Creek | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1003020210924-14Tractor Trailer - 60 Ton- After Jan 106734.34 | Corbiere and Sons Contracting1003020210924-14Tractor Trailer - 60 Ton- After Jan 106734.34INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10030 | 20210924-14 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 7 | HR | 9.16 | 0 |  |  | 85.47 | 11.1111 | 96.5811 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acvitites on Mink Creek | 6 | C244-C247 | Mink Creek | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1003020210924-14Excavator Thumb - 30 - 50 ton- After Jan 10785.47 | Corbiere and Sons Contracting1003020210924-14Excavator Thumb - 30 - 50 ton- After Jan 10785.47INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10030 | 20210924-14 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 7 | Dynamic | 110.22 | 0 |  |  | 1028.72 | 133.7336 | 1162.4536 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acvitites on Mink Creek | 6 | C244-C247 | Mink Creek | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1003020210924-14Excavator - 36 ton- After Jan 1071028.72 | Corbiere and Sons Contracting1003020210924-14Excavator - 36 ton- After Jan 1071028.72INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10029 | 20210924-13 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 32 | HR |  |  | 75 | 0 | 2400 | 312 | 2712 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1002920210924-13Operator - Principle - After Jan 10322400 | Corbiere and Sons Contracting1002920210924-13Operator - Principle - After Jan 10322400INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10029 | 20210924-13 | 53510602 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1002920210924-13L.O.A.3630 | Corbiere and Sons Contracting1002920210924-13L.O.A.3630INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10029 | 20210924-13 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 8 | Dynamic | 103.54 | 0 |  |  | 1104.4 | 143.572 | 1247.972 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1002920210924-13Rock Truck - 30 Ton- After Jan 1081104.4 | Corbiere and Sons Contracting1002920210924-13Rock Truck - 30 Ton- After Jan 1081104.4INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10029 | 20210924-13 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1002920210924-13Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting1002920210924-13Light Truck - Pick up- After Jan 102487.5INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10029 | 20210924-13 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 8 | Dynamic | 110.22 | 0 |  |  | 1175.68 | 152.8384 | 1328.5184 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1002920210924-13Excavator - 36 ton- After Jan 1081175.68 | Corbiere and Sons Contracting1002920210924-13Excavator - 36 ton- After Jan 1081175.68INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10029 | 20210924-13 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1002920210924-13Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting1002920210924-13Dozer D6 or equal- After Jan 10111446.28INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10028 | 20210924-12 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 50 | HR |  |  | 75 | 0 | 3750 | 487.5 | 4237.5 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1002820210924-12Operator - Principle - After Jan 10503750 | Corbiere and Sons Contracting1002820210924-12Operator - Principle - After Jan 10503750INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10028 | 20210924-12 | 53510602 | Access | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1002820210924-12L.O.A.51050 | Corbiere and Sons Contracting1002820210924-12L.O.A.51050INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10028 | 20210924-12 | 53510602 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1002820210924-12Foreman121140 | Corbiere and Sons Contracting1002820210924-12Foreman121140INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10028 | 20210924-12 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 22 | Dynamic | 103.54 | 0 |  |  | 3037.1 | 394.823 | 3431.923 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1002820210924-12Rock Truck - 30 Ton- After Jan 10223037.1 | Corbiere and Sons Contracting1002820210924-12Rock Truck - 30 Ton- After Jan 10223037.1INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10028 | 20210924-12 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1002820210924-12Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting1002820210924-12Light Truck - Pick up- After Jan 103731.25INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10028 | 20210924-12 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 12.5 | HR | 9.16 | 0 |  |  | 152.625 | 19.8412 | 172.4663 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1002820210924-12Excavator Thumb - 30 - 50 ton- After Jan 1012.5152.625 | Corbiere and Sons Contracting1002820210924-12Excavator Thumb - 30 - 50 ton- After Jan 1012.5152.625INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10028 | 20210924-12 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 12.5 | Dynamic | 110.22 | 0 |  |  | 1837 | 238.81 | 2075.81 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1002820210924-12Excavator - 36 ton- After Jan 1012.51837 | Corbiere and Sons Contracting1002820210924-12Excavator - 36 ton- After Jan 1012.51837INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10028 | 20210924-12 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1002820210924-12Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting1002820210924-12Dozer D6 or equal- After Jan 10111446.28INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10027 | 20210924-11 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 10 | HR |  |  | 75 | 0 | 750 | 97.5 | 847.5 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities from C214 | 6 | C214 | Highway 17 | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1002720210924-11Operator - Principle - After Jan 1010750 | Corbiere and Sons Contracting1002720210924-11Operator - Principle - After Jan 1010750INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10027 | 20210924-11 | 53510602 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities from C214 | 6 | C214 | Highway 17 | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1002720210924-11L.O.A.1210 | Corbiere and Sons Contracting1002720210924-11L.O.A.1210INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10027 | 20210924-11 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 8 | HR | 9.16 | 0 |  |  | 97.68 | 12.6984 | 110.3784 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities from C214 | 6 | C214 | Highway 17 | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1002720210924-11Excavator Thumb - 30 - 50 ton- After Jan 10897.68 | Corbiere and Sons Contracting1002720210924-11Excavator Thumb - 30 - 50 ton- After Jan 10897.68INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10027 | 20210924-11 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 8 | Dynamic | 110.22 | 0 |  |  | 1175.68 | 152.8384 | 1328.5184 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities from C214 | 6 | C214 | Highway 17 | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1002720210924-11Excavator - 36 ton- After Jan 1081175.68 | Corbiere and Sons Contracting1002720210924-11Excavator - 36 ton- After Jan 1081175.68INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10026 | 20210924-10 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 48 | HR |  |  | 75 | 0 | 3600 | 468 | 4068 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1002620210924-10Operator - Principle - After Jan 10483600 | Corbiere and Sons Contracting1002620210924-10Operator - Principle - After Jan 10483600INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10026 | 20210924-10 | 53510602 | Access | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1002620210924-10L.O.A.51050 | Corbiere and Sons Contracting1002620210924-10L.O.A.51050INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10026 | 20210924-10 | 53510602 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1002620210924-10Foreman121140 | Corbiere and Sons Contracting1002620210924-10Foreman121140INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10026 | 20210924-10 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1002620210924-10Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting1002620210924-10Rock Truck - 30 Ton- After Jan 10111518.55INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10026 | 20210924-10 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1002620210924-10Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting1002620210924-10Light Truck - Pick up- After Jan 103731.25INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10026 | 20210924-10 | 53510602 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 11 | HR | 47.54 | 0 |  |  | 697.18 | 90.6334 | 787.8134 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1002620210924-10Excavator Hammer - 30 - 50 ton- After Jan 1011697.18 | Corbiere and Sons Contracting1002620210924-10Excavator Hammer - 30 - 50 ton- After Jan 1011697.18INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10026 | 20210924-10 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 22 | Dynamic | 110.22 | 0 |  |  | 3233.12 | 420.3056 | 3653.4256 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1002620210924-10Excavator - 36 ton- After Jan 10223233.12 | Corbiere and Sons Contracting1002620210924-10Excavator - 36 ton- After Jan 10223233.12INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10026 | 20210924-10 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1002620210924-10Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting1002620210924-10Excavator - 30 ton- After Jan 10111522.95INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10010 | 20210923-9 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 48 | HR |  |  | 75 | 0 | 3600 | 468 | 4068 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C258-C267 | Hare Lake | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1001020210923-9Operator - Principle - After Jan 10483600 | Corbiere and Sons Contracting1001020210923-9Operator - Principle - After Jan 10483600INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10010 | 20210923-9 | 53510602 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C258-C267 | Hare Lake | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1001020210923-9L.O.A.4840 | Corbiere and Sons Contracting1001020210923-9L.O.A.4840INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10010 | 20210923-9 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C258-C267 | Hare Lake | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1001020210923-9Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting1001020210923-9Light Truck - Pick up- After Jan 102487.5INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10010 | 20210923-9 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C258-C267 | Hare Lake | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1001020210923-9Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1001020210923-9Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10010 | 20210923-9 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 22 | Dynamic | 103.84 | 0 |  |  | 3045.9 | 395.967 | 3441.867 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C258-C267 | Hare Lake | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1001020210923-9Excavator - 30 ton- After Jan 10223045.9 | Corbiere and Sons Contracting1001020210923-9Excavator - 30 ton- After Jan 10223045.9INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10010 | 20210923-9 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C258-C267 | Hare Lake | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1001020210923-9Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting1001020210923-9Dozer D6 or equal- After Jan 10111446.28INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10009 | 20210923-8 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 60 | HR |  |  | 75 | 0 | 4500 | 585 | 5085 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1000920210923-8Operator - Principle - After Jan 10604500 | Corbiere and Sons Contracting1000920210923-8Operator - Principle - After Jan 10604500INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10009 | 20210923-8 | 53510602 | Access | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1000920210923-8L.O.A.61260 | Corbiere and Sons Contracting1000920210923-8L.O.A.61260INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10009 | 20210923-8 | 53510602 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1000920210923-8Foreman121140 | Corbiere and Sons Contracting1000920210923-8Foreman121140INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10009 | 20210923-8 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1000920210923-8Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting1000920210923-8Rock Truck - 30 Ton- After Jan 10111518.55INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10009 | 20210923-8 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1000920210923-8Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting1000920210923-8Rock Truck - 30 Ton- After Jan 10111518.55INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10009 | 20210923-8 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 4 | DAY | 182.81 | 0 |  |  | 975 | 126.75 | 1101.75 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1000920210923-8Light Truck - Pick up- After Jan 104975 | Corbiere and Sons Contracting1000920210923-8Light Truck - Pick up- After Jan 104975INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10009 | 20210923-8 | 53510602 | Access | 0 | ATV - Side by Side w/ roll bar- After Jan 10 | 18.45 | 10 | HR | 13.84 | 0 |  |  | 184.5 | 23.985 | 208.485 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1000920210923-8ATV - Side by Side w/ roll bar- After Jan 1010184.5 | Corbiere and Sons Contracting1000920210923-8ATV - Side by Side w/ roll bar- After Jan 1010184.5INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10009 | 20210923-8 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1000920210923-8Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1000920210923-8Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10009 | 20210923-8 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1000920210923-8Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1000920210923-8Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10009 | 20210923-8 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1000920210923-8Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting1000920210923-8Excavator - 36 ton- After Jan 10111616.56INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10009 | 20210923-8 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1000920210923-8Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting1000920210923-8Excavator - 30 ton- After Jan 10111522.95INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10009 | 20210923-8 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1000920210923-8Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting1000920210923-8Dozer D6 or equal- After Jan 10111446.28INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10008 | 20210923-7-R1 | 53510602 | Access | 0 | Labourer - General - After Jan 10 | 60 | 12 | HR |  |  | 60 | 0 | 720 | 93.6 | 813.6 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1000820210923-7-R1Labourer - General - After Jan 1012720 | Corbiere and Sons Contracting1000820210923-7-R1Labourer - General - After Jan 1012720INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10008 | 20210923-7-R1 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 48 | HR |  |  | 75 | 0 | 3600 | 468 | 4068 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1000820210923-7-R1Operator - Principle - After Jan 10483600 | Corbiere and Sons Contracting1000820210923-7-R1Operator - Principle - After Jan 10483600INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10008 | 20210923-7-R1 | 53510602 | Access | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1000820210923-7-R1L.O.A.51050 | Corbiere and Sons Contracting1000820210923-7-R1L.O.A.51050INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10008 | 20210923-7-R1 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1000820210923-7-R1Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting1000820210923-7-R1Rock Truck - 30 Ton- After Jan 10111518.55INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10008 | 20210923-7-R1 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1000820210923-7-R1Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting1000820210923-7-R1Light Truck - Pick up- After Jan 103731.25INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10008 | 20210923-7-R1 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1000820210923-7-R1Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1000820210923-7-R1Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10008 | 20210923-7-R1 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1000820210923-7-R1Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting1000820210923-7-R1Excavator - 36 ton- After Jan 10111616.56INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10008 | 20210923-7-R1 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1000820210923-7-R1Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting1000820210923-7-R1Excavator - 30 ton- After Jan 10111522.95INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10008 | 20210923-7-R1 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1000820210923-7-R1Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting1000820210923-7-R1Dozer D6 or equal- After Jan 10111446.28INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10018 | 20210923-15 | 53510602 | Access | 0 | L.O.A. | 210 | 0.5 | DAY |  |  |  | 0 | 105 | 13.65 | 118.65 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Billable time for Safety Advisor working in WF6 | 6 | C130-C277 | WF6 | 0 | 2021-09-30 |  | 36 | 2021-10-04 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1001820210923-15L.O.A.0.5105 | Corbiere and Sons Contracting1001820210923-15L.O.A.0.5105INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10018 | 20210923-15 | 53510602 | Access | 0 | Safety Advisor | 85 | 7 | HR |  |  | 85 | 0 | 595 | 77.35 | 672.35 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Billable time for Safety Advisor working in WF6 | 6 | C130-C277 | WF6 | 0 | 2021-09-30 |  | 36 | 2021-10-04 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1001820210923-15Safety Advisor7595 | Corbiere and Sons Contracting1001820210923-15Safety Advisor7595INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10018 | 20210923-15 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Billable time for Safety Advisor working in WF6 | 6 | C130-C277 | WF6 | 0 | 2021-09-30 |  | 36 | 2021-10-04 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1001820210923-15Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1001820210923-15Light Truck - Pick up- After Jan 101243.75INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10017 | 20210923-14 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 60 | HR |  |  | 75 | 0 | 4500 | 585 | 5085 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1001720210923-14Operator - Principle - After Jan 10604500 | Corbiere and Sons Contracting1001720210923-14Operator - Principle - After Jan 10604500INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10017 | 20210923-14 | 53510602 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1001720210923-14Foreman121140 | Corbiere and Sons Contracting1001720210923-14Foreman121140INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10017 | 20210923-14 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 22 | Dynamic | 103.54 | 0 |  |  | 3037.1 | 394.823 | 3431.923 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1001720210923-14Rock Truck - 30 Ton- After Jan 10223037.1 | Corbiere and Sons Contracting1001720210923-14Rock Truck - 30 Ton- After Jan 10223037.1INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10017 | 20210923-14 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 4 | DAY | 182.81 | 0 |  |  | 975 | 126.75 | 1101.75 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1001720210923-14Light Truck - Pick up- After Jan 104975 | Corbiere and Sons Contracting1001720210923-14Light Truck - Pick up- After Jan 104975INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10017 | 20210923-14 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1001720210923-14Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1001720210923-14Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10017 | 20210923-14 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1001720210923-14Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1001720210923-14Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10017 | 20210923-14 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1001720210923-14Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1001720210923-14Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10017 | 20210923-14 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1001720210923-14Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1001720210923-14Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10017 | 20210923-14 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1001720210923-14Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting1001720210923-14Excavator - 36 ton- After Jan 10111616.56INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10017 | 20210923-14 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1001720210923-14Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting1001720210923-14Excavator - 36 ton- After Jan 10111616.56INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10017 | 20210923-14 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1001720210923-14Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting1001720210923-14Excavator - 36 ton- After Jan 10111616.56INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10017 | 20210923-14 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1001720210923-14Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting1001720210923-14Excavator - 30 ton- After Jan 10111522.95INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10016 | 20210923-13 | 53510602 | Access | 0 | Labourer - General - After Jan 10 | 60 | 24 | HR |  |  | 60 | 0 | 1440 | 187.2 | 1627.2 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1001620210923-13Labourer - General - After Jan 10241440 | Corbiere and Sons Contracting1001620210923-13Labourer - General - After Jan 10241440INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10016 | 20210923-13 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 48 | HR |  |  | 75 | 0 | 3600 | 468 | 4068 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1001620210923-13Operator - Principle - After Jan 10483600 | Corbiere and Sons Contracting1001620210923-13Operator - Principle - After Jan 10483600INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10016 | 20210923-13 | 53510602 | Access | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1001620210923-13L.O.A.61260 | Corbiere and Sons Contracting1001620210923-13L.O.A.61260INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10016 | 20210923-13 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 10 | Dynamic | 103.54 | 0 |  |  | 1380.5 | 179.465 | 1559.965 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1001620210923-13Rock Truck - 30 Ton- After Jan 10101380.5 | Corbiere and Sons Contracting1001620210923-13Rock Truck - 30 Ton- After Jan 10101380.5INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10016 | 20210923-13 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1001620210923-13Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting1001620210923-13Light Truck - Pick up- After Jan 103731.25INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10016 | 20210923-13 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1001620210923-13Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1001620210923-13Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10016 | 20210923-13 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10 | Dynamic | 110.22 | 0 |  |  | 1469.6 | 191.048 | 1660.648 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1001620210923-13Excavator - 36 ton- After Jan 10101469.6 | Corbiere and Sons Contracting1001620210923-13Excavator - 36 ton- After Jan 10101469.6INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10016 | 20210923-13 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1001620210923-13Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting1001620210923-13Excavator - 36 ton- After Jan 10111616.56INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10016 | 20210923-13 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1001620210923-13Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting1001620210923-13Dozer D6 or equal- After Jan 10111446.28INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10015 | 20210923-12 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 36 | HR |  |  | 75 | 0 | 2700 | 351 | 3051 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1001520210923-12Operator - Principle - After Jan 10362700 | Corbiere and Sons Contracting1001520210923-12Operator - Principle - After Jan 10362700INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10015 | 20210923-12 | 53510602 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1001520210923-12L.O.A.4840 | Corbiere and Sons Contracting1001520210923-12L.O.A.4840INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10015 | 20210923-12 | 53510602 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1001520210923-12Foreman121140 | Corbiere and Sons Contracting1001520210923-12Foreman121140INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10015 | 20210923-12 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1001520210923-12Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting1001520210923-12Rock Truck - 30 Ton- After Jan 10111518.55INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10015 | 20210923-12 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1001520210923-12Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting1001520210923-12Light Truck - Pick up- After Jan 103731.25INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10015 | 20210923-12 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1001520210923-12Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1001520210923-12Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10015 | 20210923-12 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1001520210923-12Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting1001520210923-12Excavator - 36 ton- After Jan 10111616.56INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10015 | 20210923-12 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1001520210923-12Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting1001520210923-12Dozer D6 or equal- After Jan 10111446.28INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10014 | 20210923-11 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 24 | HR |  |  | 75 | 0 | 1800 | 234 | 2034 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities from C214 | 6 | C214 | Highway 17 | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1001420210923-11Operator - Principle - After Jan 10241800 | Corbiere and Sons Contracting1001420210923-11Operator - Principle - After Jan 10241800INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10014 | 20210923-11 | 53510602 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities from C214 | 6 | C214 | Highway 17 | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1001420210923-11L.O.A.2420 | Corbiere and Sons Contracting1001420210923-11L.O.A.2420INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10014 | 20210923-11 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities from C214 | 6 | C214 | Highway 17 | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1001420210923-11Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting1001420210923-11Rock Truck - 30 Ton- After Jan 10111518.55INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10014 | 20210923-11 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities from C214 | 6 | C214 | Highway 17 | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1001420210923-11Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1001420210923-11Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10014 | 20210923-11 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities from C214 | 6 | C214 | Highway 17 | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1001420210923-11Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting1001420210923-11Excavator - 36 ton- After Jan 10111616.56INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10011 | 20210923-10 | 53510602 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 12 | HR |  |  | 70 | 0 | 840 | 109.2 | 949.2 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1001120210923-10Driver - AZ - After Jan 1012840 | Corbiere and Sons Contracting1001120210923-10Driver - AZ - After Jan 1012840INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10011 | 20210923-10 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 60 | HR |  |  | 75 | 0 | 4500 | 585 | 5085 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1001120210923-10Operator - Principle - After Jan 10604500 | Corbiere and Sons Contracting1001120210923-10Operator - Principle - After Jan 10604500INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10011 | 20210923-10 | 53510602 | Access | 0 | L.O.A. | 210 | 7 | DAY |  |  |  | 0 | 1470 | 191.1 | 1661.1 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1001120210923-10L.O.A.71470 | Corbiere and Sons Contracting1001120210923-10L.O.A.71470INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10011 | 20210923-10 | 53510602 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1001120210923-10Foreman121140 | Corbiere and Sons Contracting1001120210923-10Foreman121140INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10011 | 20210923-10 | 53510602 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 12 | Dynamic | 91.79 | 0 |  |  | 1468.68 | 190.9284 | 1659.6084 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1001120210923-10Tractor Trailer - 60 Ton- After Jan 10121468.68 | Corbiere and Sons Contracting1001120210923-10Tractor Trailer - 60 Ton- After Jan 10121468.68INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10011 | 20210923-10 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1001120210923-10Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting1001120210923-10Rock Truck - 30 Ton- After Jan 10111518.55INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10011 | 20210923-10 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1001120210923-10Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting1001120210923-10Light Truck - Pick up- After Jan 103731.25INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10011 | 20210923-10 | 53510602 | Access | 0 | ATV - Side by Side w/ roll bar- After Jan 10 | 18.45 | 10 | HR | 13.84 | 0 |  |  | 184.5 | 23.985 | 208.485 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1001120210923-10ATV - Side by Side w/ roll bar- After Jan 1010184.5 | Corbiere and Sons Contracting1001120210923-10ATV - Side by Side w/ roll bar- After Jan 1010184.5INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10011 | 20210923-10 | 53510602 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 11 | HR | 47.54 | 0 |  |  | 697.18 | 90.6334 | 787.8134 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1001120210923-10Excavator Hammer - 30 - 50 ton- After Jan 1011697.18 | Corbiere and Sons Contracting1001120210923-10Excavator Hammer - 30 - 50 ton- After Jan 1011697.18INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10011 | 20210923-10 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1001120210923-10Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting1001120210923-10Excavator - 36 ton- After Jan 10111616.56INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10011 | 20210923-10 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1001120210923-10Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting1001120210923-10Excavator - 36 ton- After Jan 10111616.56INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10011 | 20210923-10 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1001120210923-10Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting1001120210923-10Excavator - 30 ton- After Jan 10111522.95INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10011 | 20210923-10 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 7.5 | Dynamic | 98.61 | 0 |  |  | 986.1 | 128.193 | 1114.293 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1001120210923-10Dozer D6 or equal- After Jan 107.5986.1 | Corbiere and Sons Contracting1001120210923-10Dozer D6 or equal- After Jan 107.5986.1INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9997 | 20210922-9-R1 | 53510602 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 11 | HR |  |  | 70 | 0 | 770 | 100.1 | 870.1 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Floats moved equipment over to C214 - Operatos worked on access road | 6 | C214 | Highway 17 | 0 | 2021-09-30 |  | 37 | 2021-10-05 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting999720210922-9-R1Driver - AZ - After Jan 1011770 | Corbiere and Sons Contracting999720210922-9-R1Driver - AZ - After Jan 1011770INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9997 | 20210922-9-R1 | 53510602 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 6 | HR |  |  | 70 | 0 | 420 | 54.6 | 474.6 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Floats moved equipment over to C214 - Operatos worked on access road | 6 | C214 | Highway 17 | 0 | 2021-09-30 |  | 37 | 2021-10-05 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting999720210922-9-R1Driver - AZ - After Jan 106420 | Corbiere and Sons Contracting999720210922-9-R1Driver - AZ - After Jan 106420INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9997 | 20210922-9-R1 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 14 | HR |  |  | 75 | 0 | 1050 | 136.5 | 1186.5 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Floats moved equipment over to C214 - Operatos worked on access road | 6 | C214 | Highway 17 | 0 | 2021-09-30 |  | 37 | 2021-10-05 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting999720210922-9-R1Operator - Principle - After Jan 10141050 | Corbiere and Sons Contracting999720210922-9-R1Operator - Principle - After Jan 10141050INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9997 | 20210922-9-R1 | 53510602 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Floats moved equipment over to C214 - Operatos worked on access road | 6 | C214 | Highway 17 | 0 | 2021-09-30 |  | 37 | 2021-10-05 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting999720210922-9-R1L.O.A.3630 | Corbiere and Sons Contracting999720210922-9-R1L.O.A.3630INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9997 | 20210922-9-R1 | 53510602 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 17 | Dynamic | 91.79 | 0 |  |  | 2080.63 | 270.4819 | 2351.1119 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Floats moved equipment over to C214 - Operatos worked on access road | 6 | C214 | Highway 17 | 0 | 2021-09-30 |  | 37 | 2021-10-05 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting999720210922-9-R1Tractor Trailer - 60 Ton- After Jan 10172080.63 | Corbiere and Sons Contracting999720210922-9-R1Tractor Trailer - 60 Ton- After Jan 10172080.63INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9997 | 20210922-9-R1 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 2 | Dynamic | 103.54 | 0 |  |  | 276.1 | 35.893 | 311.993 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Floats moved equipment over to C214 - Operatos worked on access road | 6 | C214 | Highway 17 | 0 | 2021-09-30 |  | 37 | 2021-10-05 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting999720210922-9-R1Rock Truck - 30 Ton- After Jan 102276.1 | Corbiere and Sons Contracting999720210922-9-R1Rock Truck - 30 Ton- After Jan 102276.1INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9997 | 20210922-9-R1 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 9.16 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Floats moved equipment over to C214 - Operatos worked on access road | 6 | C214 | Highway 17 | 0 | 2021-09-30 |  | 37 | 2021-10-05 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting999720210922-9-R1Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting999720210922-9-R1Excavator Thumb - 30 - 50 ton- After Jan 1010122.1INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9997 | 20210922-9-R1 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10 | Dynamic | 110.22 | 0 |  |  | 1469.6 | 191.048 | 1660.648 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Floats moved equipment over to C214 - Operatos worked on access road | 6 | C214 | Highway 17 | 0 | 2021-09-30 |  | 37 | 2021-10-05 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting999720210922-9-R1Excavator - 36 ton- After Jan 10101469.6 | Corbiere and Sons Contracting999720210922-9-R1Excavator - 36 ton- After Jan 10101469.6INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9996 | 20210922-8 | 53510602 | Access | 0 | Labourer - General - After Jan 10 | 60 | 12 | HR |  |  | 60 | 0 | 720 | 93.6 | 813.6 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting999620210922-8Labourer - General - After Jan 1012720 | Corbiere and Sons Contracting999620210922-8Labourer - General - After Jan 1012720INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9996 | 20210922-8 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 48 | HR |  |  | 75 | 0 | 3600 | 468 | 4068 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting999620210922-8Operator - Principle - After Jan 10483600 | Corbiere and Sons Contracting999620210922-8Operator - Principle - After Jan 10483600INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9996 | 20210922-8 | 53510602 | Access | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting999620210922-8L.O.A.61260 | Corbiere and Sons Contracting999620210922-8L.O.A.61260INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9996 | 20210922-8 | 53510602 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting999620210922-8Foreman121140 | Corbiere and Sons Contracting999620210922-8Foreman121140INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9996 | 20210922-8 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting999620210922-8Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting999620210922-8Rock Truck - 30 Ton- After Jan 10111518.55INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9996 | 20210922-8 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting999620210922-8Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting999620210922-8Light Truck - Pick up- After Jan 103731.25INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9996 | 20210922-8 | 53510602 | Access | 0 | ATV - Side by Side w/ roll bar- After Jan 10 | 18.45 | 10 | HR | 13.84 | 0 |  |  | 184.5 | 23.985 | 208.485 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting999620210922-8ATV - Side by Side w/ roll bar- After Jan 1010184.5 | Corbiere and Sons Contracting999620210922-8ATV - Side by Side w/ roll bar- After Jan 1010184.5INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9996 | 20210922-8 | 53510602 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 11 | HR | 47.54 | 0 |  |  | 697.18 | 90.6334 | 787.8134 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting999620210922-8Excavator Hammer - 30 - 50 ton- After Jan 1011697.18 | Corbiere and Sons Contracting999620210922-8Excavator Hammer - 30 - 50 ton- After Jan 1011697.18INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9996 | 20210922-8 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 22 | Dynamic | 110.22 | 0 |  |  | 3233.12 | 420.3056 | 3653.4256 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting999620210922-8Excavator - 36 ton- After Jan 10223233.12 | Corbiere and Sons Contracting999620210922-8Excavator - 36 ton- After Jan 10223233.12INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9996 | 20210922-8 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting999620210922-8Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting999620210922-8Excavator - 30 ton- After Jan 10111522.95INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9995 | 20210922-7 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 48 | HR |  |  | 75 | 0 | 3600 | 468 | 4068 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C258-C267 | Hare Lake | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting999520210922-7Operator - Principle - After Jan 10483600 | Corbiere and Sons Contracting999520210922-7Operator - Principle - After Jan 10483600INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9995 | 20210922-7 | 53510602 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C258-C267 | Hare Lake | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting999520210922-7L.O.A.4840 | Corbiere and Sons Contracting999520210922-7L.O.A.4840INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9995 | 20210922-7 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 6 | Dynamic | 103.54 | 0 |  |  | 828.3 | 107.679 | 935.979 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C258-C267 | Hare Lake | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting999520210922-7Rock Truck - 30 Ton- After Jan 106828.3 | Corbiere and Sons Contracting999520210922-7Rock Truck - 30 Ton- After Jan 106828.3INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9995 | 20210922-7 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C258-C267 | Hare Lake | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting999520210922-7Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting999520210922-7Light Truck - Pick up- After Jan 102487.5INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9995 | 20210922-7 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C258-C267 | Hare Lake | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting999520210922-7Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting999520210922-7Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9995 | 20210922-7 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C258-C267 | Hare Lake | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting999520210922-7Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting999520210922-7Excavator - 30 ton- After Jan 10111522.95INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9995 | 20210922-7 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C258-C267 | Hare Lake | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting999520210922-7Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting999520210922-7Excavator - 30 ton- After Jan 10111522.95INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9995 | 20210922-7 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 5 | Dynamic | 98.61 | 0 |  |  | 657.4 | 85.462 | 742.862 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C258-C267 | Hare Lake | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting999520210922-7Dozer D6 or equal- After Jan 105657.4 | Corbiere and Sons Contracting999520210922-7Dozer D6 or equal- After Jan 105657.4INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9994 | 20210922-6 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 60 | HR |  |  | 75 | 0 | 4500 | 585 | 5085 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting999420210922-6Operator - Principle - After Jan 10604500 | Corbiere and Sons Contracting999420210922-6Operator - Principle - After Jan 10604500INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9994 | 20210922-6 | 53510602 | Access | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting999420210922-6L.O.A.61260 | Corbiere and Sons Contracting999420210922-6L.O.A.61260INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9994 | 20210922-6 | 53510602 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting999420210922-6Foreman121140 | Corbiere and Sons Contracting999420210922-6Foreman121140INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9994 | 20210922-6 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 22 | Dynamic | 103.54 | 0 |  |  | 3037.1 | 394.823 | 3431.923 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting999420210922-6Rock Truck - 30 Ton- After Jan 10223037.1 | Corbiere and Sons Contracting999420210922-6Rock Truck - 30 Ton- After Jan 10223037.1INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9994 | 20210922-6 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 4 | DAY | 182.81 | 0 |  |  | 975 | 126.75 | 1101.75 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting999420210922-6Light Truck - Pick up- After Jan 104975 | Corbiere and Sons Contracting999420210922-6Light Truck - Pick up- After Jan 104975INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9994 | 20210922-6 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting999420210922-6Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting999420210922-6Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9994 | 20210922-6 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting999420210922-6Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting999420210922-6Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9994 | 20210922-6 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting999420210922-6Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting999420210922-6Excavator - 36 ton- After Jan 10111616.56INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9994 | 20210922-6 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting999420210922-6Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting999420210922-6Excavator - 30 ton- After Jan 10111522.95INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9994 | 20210922-6 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting999420210922-6Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting999420210922-6Dozer D6 or equal- After Jan 10111446.28INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9993 | 20210922-5 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 24 | HR |  |  | 75 | 0 | 1800 | 234 | 2034 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-09-29 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting999320210922-5Operator - Principle - After Jan 10241800 | Corbiere and Sons Contracting999320210922-5Operator - Principle - After Jan 10241800INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9993 | 20210922-5 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 36 | HR |  |  | 75 | 0 | 2700 | 351 | 3051 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-09-29 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting999320210922-5Operator - Principle - After Jan 10362700 | Corbiere and Sons Contracting999320210922-5Operator - Principle - After Jan 10362700INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9993 | 20210922-5 | 53510602 | Access | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-09-29 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting999320210922-5L.O.A.61260 | Corbiere and Sons Contracting999320210922-5L.O.A.61260INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9993 | 20210922-5 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 19 | Dynamic | 103.54 | 0 |  |  | 2622.95 | 340.9835 | 2963.9335 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-09-29 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting999320210922-5Rock Truck - 30 Ton- After Jan 10192622.95 | Corbiere and Sons Contracting999320210922-5Rock Truck - 30 Ton- After Jan 10192622.95INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9993 | 20210922-5 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-09-29 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting999320210922-5Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting999320210922-5Light Truck - Pick up- After Jan 102487.5INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9993 | 20210922-5 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 6 | HR | 9.16 | 0 |  |  | 73.26 | 9.5238 | 82.7838 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-09-29 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting999320210922-5Excavator Thumb - 30 - 50 ton- After Jan 10673.26 | Corbiere and Sons Contracting999320210922-5Excavator Thumb - 30 - 50 ton- After Jan 10673.26INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9993 | 20210922-5 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-09-29 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting999320210922-5Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting999320210922-5Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9993 | 20210922-5 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 6 | Dynamic | 110.22 | 0 |  |  | 881.76 | 114.6288 | 996.3888 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-09-29 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting999320210922-5Excavator - 36 ton- After Jan 106881.76 | Corbiere and Sons Contracting999320210922-5Excavator - 36 ton- After Jan 106881.76INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9993 | 20210922-5 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-09-29 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting999320210922-5Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting999320210922-5Excavator - 36 ton- After Jan 10111616.56INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9993 | 20210922-5 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-09-29 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting999320210922-5Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting999320210922-5Excavator - 30 ton- After Jan 10111522.95INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9993 | 20210922-5 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-09-29 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting999320210922-5Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting999320210922-5Dozer D6 or equal- After Jan 10111446.28INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10002 | 20210922-14 | 53510602 | Access | 0 | ATV - Side by Side w/ roll bar- After Jan 10 | 18.45 | 10 | HR | 13.84 | 0 |  |  | 184.5 | 23.985 | 208.485 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Missed time for billable ATV | 6 | C219-C236 | Neys | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting1000220210922-14ATV - Side by Side w/ roll bar- After Jan 1010184.5 | Corbiere and Sons Contracting1000220210922-14ATV - Side by Side w/ roll bar- After Jan 1010184.5INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10000 | 20210922-12-R1 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 55 | HR |  |  | 75 | 0 | 4125 | 536.25 | 4661.25 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting1000020210922-12-R1Operator - Principle - After Jan 10554125 | Corbiere and Sons Contracting1000020210922-12-R1Operator - Principle - After Jan 10554125INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10000 | 20210922-12-R1 | 53510602 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting1000020210922-12-R1Foreman121140 | Corbiere and Sons Contracting1000020210922-12-R1Foreman121140INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10000 | 20210922-12-R1 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 18 | Dynamic | 103.54 | 0 |  |  | 2484.9 | 323.037 | 2807.937 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting1000020210922-12-R1Rock Truck - 30 Ton- After Jan 10182484.9 | Corbiere and Sons Contracting1000020210922-12-R1Rock Truck - 30 Ton- After Jan 10182484.9INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10000 | 20210922-12-R1 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 4 | DAY | 182.81 | 0 |  |  | 975 | 126.75 | 1101.75 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting1000020210922-12-R1Light Truck - Pick up- After Jan 104975 | Corbiere and Sons Contracting1000020210922-12-R1Light Truck - Pick up- After Jan 104975INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10000 | 20210922-12-R1 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting1000020210922-12-R1Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1000020210922-12-R1Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10000 | 20210922-12-R1 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting1000020210922-12-R1Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1000020210922-12-R1Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10000 | 20210922-12-R1 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting1000020210922-12-R1Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1000020210922-12-R1Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10000 | 20210922-12-R1 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting1000020210922-12-R1Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1000020210922-12-R1Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10000 | 20210922-12-R1 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting1000020210922-12-R1Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting1000020210922-12-R1Excavator - 36 ton- After Jan 10111616.56INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10000 | 20210922-12-R1 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting1000020210922-12-R1Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting1000020210922-12-R1Excavator - 36 ton- After Jan 10111616.56INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10000 | 20210922-12-R1 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting1000020210922-12-R1Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting1000020210922-12-R1Excavator - 36 ton- After Jan 10111616.56INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10000 | 20210922-12-R1 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting1000020210922-12-R1Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting1000020210922-12-R1Excavator - 30 ton- After Jan 10111522.95INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9999 | 20210922-11 | 53510602 | Access | 0 | Labourer - General - After Jan 10 | 60 | 24 | HR |  |  | 60 | 0 | 1440 | 187.2 | 1627.2 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting999920210922-11Labourer - General - After Jan 10241440 | Corbiere and Sons Contracting999920210922-11Labourer - General - After Jan 10241440INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9999 | 20210922-11 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 48 | HR |  |  | 75 | 0 | 3600 | 468 | 4068 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting999920210922-11Operator - Principle - After Jan 10483600 | Corbiere and Sons Contracting999920210922-11Operator - Principle - After Jan 10483600INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9999 | 20210922-11 | 53510602 | Access | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting999920210922-11L.O.A.61260 | Corbiere and Sons Contracting999920210922-11L.O.A.61260INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9999 | 20210922-11 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 10 | Dynamic | 103.54 | 0 |  |  | 1380.5 | 179.465 | 1559.965 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting999920210922-11Rock Truck - 30 Ton- After Jan 10101380.5 | Corbiere and Sons Contracting999920210922-11Rock Truck - 30 Ton- After Jan 10101380.5INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9999 | 20210922-11 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting999920210922-11Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting999920210922-11Light Truck - Pick up- After Jan 103731.25INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9999 | 20210922-11 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting999920210922-11Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting999920210922-11Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9999 | 20210922-11 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10 | Dynamic | 110.22 | 0 |  |  | 1469.6 | 191.048 | 1660.648 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting999920210922-11Excavator - 36 ton- After Jan 10101469.6 | Corbiere and Sons Contracting999920210922-11Excavator - 36 ton- After Jan 10101469.6INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9999 | 20210922-11 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting999920210922-11Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting999920210922-11Excavator - 36 ton- After Jan 10111616.56INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9999 | 20210922-11 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting999920210922-11Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting999920210922-11Dozer D6 or equal- After Jan 10111446.28INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9998 | 20210922-10 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 36 | HR |  |  | 75 | 0 | 2700 | 351 | 3051 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | oad building activities on Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting999820210922-10Operator - Principle - After Jan 10362700 | Corbiere and Sons Contracting999820210922-10Operator - Principle - After Jan 10362700INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9998 | 20210922-10 | 53510602 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | oad building activities on Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting999820210922-10L.O.A.4840 | Corbiere and Sons Contracting999820210922-10L.O.A.4840INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9998 | 20210922-10 | 53510602 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | oad building activities on Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting999820210922-10Foreman121140 | Corbiere and Sons Contracting999820210922-10Foreman121140INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9998 | 20210922-10 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | oad building activities on Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting999820210922-10Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting999820210922-10Rock Truck - 30 Ton- After Jan 10111518.55INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9998 | 20210922-10 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | oad building activities on Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting999820210922-10Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting999820210922-10Light Truck - Pick up- After Jan 103731.25INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9998 | 20210922-10 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | oad building activities on Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting999820210922-10Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting999820210922-10Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9998 | 20210922-10 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | oad building activities on Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting999820210922-10Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting999820210922-10Excavator - 36 ton- After Jan 10111616.56INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9998 | 20210922-10 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | oad building activities on Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting999820210922-10Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting999820210922-10Dozer D6 or equal- After Jan 10111446.28INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9976 | 20210921-9 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997620210921-9Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting997620210921-9Operator - Principle - After Jan 1012900INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9976 | 20210921-9 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997620210921-9Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting997620210921-9Operator - Principle - After Jan 1012900INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9976 | 20210921-9 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997620210921-9Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting997620210921-9Operator - Principle - After Jan 1012900INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9976 | 20210921-9 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997620210921-9Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting997620210921-9Operator - Principle - After Jan 1012900INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9976 | 20210921-9 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997620210921-9Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting997620210921-9Operator - Principle - After Jan 1012900INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9976 | 20210921-9 | 53510602 | Access | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997620210921-9L.O.A.61260 | Corbiere and Sons Contracting997620210921-9L.O.A.61260INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9976 | 20210921-9 | 53510602 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997620210921-9Foreman121140 | Corbiere and Sons Contracting997620210921-9Foreman121140INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9976 | 20210921-9 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 22 | Dynamic | 103.54 | 0 |  |  | 3037.1 | 394.823 | 3431.923 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997620210921-9Rock Truck - 30 Ton- After Jan 10223037.1 | Corbiere and Sons Contracting997620210921-9Rock Truck - 30 Ton- After Jan 10223037.1INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9976 | 20210921-9 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997620210921-9Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting997620210921-9Light Truck - Pick up- After Jan 103731.25INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9976 | 20210921-9 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997620210921-9Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting997620210921-9Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9976 | 20210921-9 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997620210921-9Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting997620210921-9Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9976 | 20210921-9 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997620210921-9Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting997620210921-9Excavator - 36 ton- After Jan 10111616.56INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9976 | 20210921-9 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997620210921-9Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting997620210921-9Excavator - 30 ton- After Jan 10111522.95INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9976 | 20210921-9 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997620210921-9Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting997620210921-9Dozer D6 or equal- After Jan 10111446.28INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9975 | 20210921-8 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997520210921-8Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting997520210921-8Operator - Principle - After Jan 1012900INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9975 | 20210921-8 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997520210921-8Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting997520210921-8Operator - Principle - After Jan 1012900INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9975 | 20210921-8 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997520210921-8Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting997520210921-8Operator - Principle - After Jan 1012900INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9975 | 20210921-8 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997520210921-8Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting997520210921-8Operator - Principle - After Jan 1012900INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9975 | 20210921-8 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 8 | HR |  |  | 75 | 0 | 600 | 78 | 678 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997520210921-8Operator - Principle - After Jan 108600 | Corbiere and Sons Contracting997520210921-8Operator - Principle - After Jan 108600INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9975 | 20210921-8 | 53510602 | Access | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997520210921-8L.O.A.51050 | Corbiere and Sons Contracting997520210921-8L.O.A.51050INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9975 | 20210921-8 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997520210921-8Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting997520210921-8Rock Truck - 30 Ton- After Jan 10111518.55INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9975 | 20210921-8 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997520210921-8Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting997520210921-8Rock Truck - 30 Ton- After Jan 10111518.55INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9975 | 20210921-8 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997520210921-8Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting997520210921-8Light Truck - Pick up- After Jan 102487.5INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9975 | 20210921-8 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 7 | HR | 9.16 | 0 |  |  | 85.47 | 11.1111 | 96.5811 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997520210921-8Excavator Thumb - 30 - 50 ton- After Jan 10785.47 | Corbiere and Sons Contracting997520210921-8Excavator Thumb - 30 - 50 ton- After Jan 10785.47INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9975 | 20210921-8 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997520210921-8Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting997520210921-8Excavator - 36 ton- After Jan 10111616.56INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9975 | 20210921-8 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 7 | Dynamic | 103.84 | 0 |  |  | 969.15 | 125.9895 | 1095.1395 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997520210921-8Excavator - 30 ton- After Jan 107969.15 | Corbiere and Sons Contracting997520210921-8Excavator - 30 ton- After Jan 107969.15INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9975 | 20210921-8 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997520210921-8Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting997520210921-8Dozer D6 or equal- After Jan 10111446.28INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9982 | 20210921-15 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 40 | HR |  |  | 75 | 0 | 3000 | 390 | 3390 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting998220210921-15Operator - Principle - After Jan 10403000 | Corbiere and Sons Contracting998220210921-15Operator - Principle - After Jan 10403000INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9982 | 20210921-15 | 53510602 | Access | 0 | Foreman | 95 | 9 | HR |  |  | 95 | 0 | 855 | 111.15 | 966.15 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting998220210921-15Foreman9855 | Corbiere and Sons Contracting998220210921-15Foreman9855INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9982 | 20210921-15 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 7 | Dynamic | 103.54 | 0 |  |  | 966.35 | 125.6255 | 1091.9755 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting998220210921-15Rock Truck - 30 Ton- After Jan 107966.35 | Corbiere and Sons Contracting998220210921-15Rock Truck - 30 Ton- After Jan 107966.35INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9982 | 20210921-15 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 4 | DAY | 182.81 | 0 |  |  | 975 | 126.75 | 1101.75 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting998220210921-15Light Truck - Pick up- After Jan 104975 | Corbiere and Sons Contracting998220210921-15Light Truck - Pick up- After Jan 104975INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9982 | 20210921-15 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting998220210921-15Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting998220210921-15Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9982 | 20210921-15 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting998220210921-15Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting998220210921-15Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9982 | 20210921-15 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 8 | HR | 9.16 | 0 |  |  | 97.68 | 12.6984 | 110.3784 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting998220210921-15Excavator Thumb - 30 - 50 ton- After Jan 10897.68 | Corbiere and Sons Contracting998220210921-15Excavator Thumb - 30 - 50 ton- After Jan 10897.68INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9982 | 20210921-15 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting998220210921-15Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting998220210921-15Excavator - 36 ton- After Jan 10111616.56INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9982 | 20210921-15 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting998220210921-15Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting998220210921-15Excavator - 36 ton- After Jan 10111616.56INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9982 | 20210921-15 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 8 | Dynamic | 103.84 | 0 |  |  | 1107.6 | 143.988 | 1251.588 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting998220210921-15Excavator - 30 ton- After Jan 1081107.6 | Corbiere and Sons Contracting998220210921-15Excavator - 30 ton- After Jan 1081107.6INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9982 | 20210921-15 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 2 | Dynamic | 98.61 | 0 |  |  | 262.96 | 34.1848 | 297.1448 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting998220210921-15Dozer D6 or equal- After Jan 102262.96 | Corbiere and Sons Contracting998220210921-15Dozer D6 or equal- After Jan 102262.96INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9981 | 20210921-14 | 53510602 | Access | 0 | ATV - Side by Side w/ roll bar- After Jan 10 | 18.45 | 10 | HR | 13.84 | 0 |  |  | 184.5 | 23.985 | 208.485 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Billable ATV usage on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting998120210921-14ATV - Side by Side w/ roll bar- After Jan 1010184.5 | Corbiere and Sons Contracting998120210921-14ATV - Side by Side w/ roll bar- After Jan 1010184.5INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9980 | 20210921-13-R1 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 36 | HR |  |  | 75 | 0 | 2700 | 351 | 3051 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-09-29 |  | 37 | 2021-10-05 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting998020210921-13-R1Operator - Principle - After Jan 10362700 | Corbiere and Sons Contracting998020210921-13-R1Operator - Principle - After Jan 10362700INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9980 | 20210921-13-R1 | 53510602 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-09-29 |  | 37 | 2021-10-05 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting998020210921-13-R1L.O.A.3630 | Corbiere and Sons Contracting998020210921-13-R1L.O.A.3630INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9980 | 20210921-13-R1 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 9 | Dynamic | 103.54 | 0 |  |  | 1242.45 | 161.5185 | 1403.9685 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-09-29 |  | 37 | 2021-10-05 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting998020210921-13-R1Rock Truck - 30 Ton- After Jan 1091242.45 | Corbiere and Sons Contracting998020210921-13-R1Rock Truck - 30 Ton- After Jan 1091242.45INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9980 | 20210921-13-R1 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-09-29 |  | 37 | 2021-10-05 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting998020210921-13-R1Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting998020210921-13-R1Light Truck - Pick up- After Jan 101243.75INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9980 | 20210921-13-R1 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-09-29 |  | 37 | 2021-10-05 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting998020210921-13-R1Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting998020210921-13-R1Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9980 | 20210921-13-R1 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-09-29 |  | 37 | 2021-10-05 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting998020210921-13-R1Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting998020210921-13-R1Excavator - 36 ton- After Jan 1091322.64INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9980 | 20210921-13-R1 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-09-29 |  | 37 | 2021-10-05 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting998020210921-13-R1Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting998020210921-13-R1Excavator - 36 ton- After Jan 10111616.56INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9980 | 20210921-13-R1 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-09-29 |  | 37 | 2021-10-05 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting998020210921-13-R1Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting998020210921-13-R1Dozer D6 or equal- After Jan 10111446.28INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9979 | 20210921-12 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 48 | HR |  |  | 75 | 0 | 3600 | 468 | 4068 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Middleton | 6 | C210-C213 | Middleton Road | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997920210921-12Operator - Principle - After Jan 10483600 | Corbiere and Sons Contracting997920210921-12Operator - Principle - After Jan 10483600INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9979 | 20210921-12 | 53510602 | Access | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Middleton | 6 | C210-C213 | Middleton Road | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997920210921-12L.O.A.51050 | Corbiere and Sons Contracting997920210921-12L.O.A.51050INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9979 | 20210921-12 | 53510602 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Middleton | 6 | C210-C213 | Middleton Road | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997920210921-12Foreman121140 | Corbiere and Sons Contracting997920210921-12Foreman121140INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9979 | 20210921-12 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Middleton | 6 | C210-C213 | Middleton Road | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997920210921-12Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting997920210921-12Rock Truck - 30 Ton- After Jan 10111518.55INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9979 | 20210921-12 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Middleton | 6 | C210-C213 | Middleton Road | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997920210921-12Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting997920210921-12Light Truck - Pick up- After Jan 103731.25INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9979 | 20210921-12 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Middleton | 6 | C210-C213 | Middleton Road | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997920210921-12Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting997920210921-12Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9979 | 20210921-12 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Middleton | 6 | C210-C213 | Middleton Road | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997920210921-12Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting997920210921-12Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9979 | 20210921-12 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Middleton | 6 | C210-C213 | Middleton Road | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997920210921-12Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting997920210921-12Excavator - 36 ton- After Jan 10111616.56INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9979 | 20210921-12 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Middleton | 6 | C210-C213 | Middleton Road | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997920210921-12Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting997920210921-12Excavator - 36 ton- After Jan 10111616.56INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9979 | 20210921-12 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Middleton | 6 | C210-C213 | Middleton Road | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997920210921-12Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting997920210921-12Dozer D6 or equal- After Jan 10111446.28INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9978 | 20210921-11 | 53510602 | Access | 0 | Labourer - General - After Jan 10 | 60 | 12 | HR |  |  | 60 | 0 | 720 | 93.6 | 813.6 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake Road | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997820210921-11Labourer - General - After Jan 1012720 | Corbiere and Sons Contracting997820210921-11Labourer - General - After Jan 1012720INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9978 | 20210921-11 | 53510602 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 12 | HR |  |  | 70 | 0 | 840 | 109.2 | 949.2 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake Road | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997820210921-11Driver - AZ - After Jan 1012840 | Corbiere and Sons Contracting997820210921-11Driver - AZ - After Jan 1012840INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9978 | 20210921-11 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 48 | HR |  |  | 75 | 0 | 3600 | 468 | 4068 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake Road | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997820210921-11Operator - Principle - After Jan 10483600 | Corbiere and Sons Contracting997820210921-11Operator - Principle - After Jan 10483600INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9978 | 20210921-11 | 53510602 | Access | 0 | L.O.A. | 210 | 7 | DAY |  |  |  | 0 | 1470 | 191.1 | 1661.1 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake Road | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997820210921-11L.O.A.71470 | Corbiere and Sons Contracting997820210921-11L.O.A.71470INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9978 | 20210921-11 | 53510602 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake Road | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997820210921-11Foreman121140 | Corbiere and Sons Contracting997820210921-11Foreman121140INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9978 | 20210921-11 | 53510602 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 12 | Dynamic | 91.79 | 0 |  |  | 1468.68 | 190.9284 | 1659.6084 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake Road | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997820210921-11Tractor Trailer - 60 Ton- After Jan 10121468.68 | Corbiere and Sons Contracting997820210921-11Tractor Trailer - 60 Ton- After Jan 10121468.68INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9978 | 20210921-11 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake Road | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997820210921-11Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting997820210921-11Rock Truck - 30 Ton- After Jan 10111518.55INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9978 | 20210921-11 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake Road | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997820210921-11Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting997820210921-11Light Truck - Pick up- After Jan 103731.25INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9978 | 20210921-11 | 53510602 | Access | 0 | ATV - Side by Side w/ roll bar- After Jan 10 | 18.45 | 10 | HR | 13.84 | 0 |  |  | 184.5 | 23.985 | 208.485 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake Road | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997820210921-11ATV - Side by Side w/ roll bar- After Jan 1010184.5 | Corbiere and Sons Contracting997820210921-11ATV - Side by Side w/ roll bar- After Jan 1010184.5INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9978 | 20210921-11 | 53510602 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 11 | HR | 47.54 | 0 |  |  | 697.18 | 90.6334 | 787.8134 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake Road | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997820210921-11Excavator Hammer - 30 - 50 ton- After Jan 1011697.18 | Corbiere and Sons Contracting997820210921-11Excavator Hammer - 30 - 50 ton- After Jan 1011697.18INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9978 | 20210921-11 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake Road | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997820210921-11Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting997820210921-11Excavator - 36 ton- After Jan 10111616.56INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9978 | 20210921-11 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake Road | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997820210921-11Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting997820210921-11Excavator - 36 ton- After Jan 10111616.56INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9978 | 20210921-11 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake Road | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997820210921-11Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting997820210921-11Excavator - 30 ton- After Jan 10111522.95INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9977 | 20210921-10 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C258-C267 | Hare Lake | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997720210921-10Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting997720210921-10Operator - Principle - After Jan 1012900INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9977 | 20210921-10 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C258-C267 | Hare Lake | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997720210921-10Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting997720210921-10Operator - Principle - After Jan 1012900INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9977 | 20210921-10 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C258-C267 | Hare Lake | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997720210921-10Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting997720210921-10Operator - Principle - After Jan 1011.5862.5INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9977 | 20210921-10 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C258-C267 | Hare Lake | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997720210921-10Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting997720210921-10Operator - Principle - After Jan 1012900INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9977 | 20210921-10 | 53510602 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C258-C267 | Hare Lake | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997720210921-10L.O.A.4840 | Corbiere and Sons Contracting997720210921-10L.O.A.4840INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9977 | 20210921-10 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C258-C267 | Hare Lake | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997720210921-10Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting997720210921-10Rock Truck - 30 Ton- After Jan 10111518.55INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9977 | 20210921-10 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C258-C267 | Hare Lake | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997720210921-10Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting997720210921-10Light Truck - Pick up- After Jan 102487.5INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9977 | 20210921-10 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C258-C267 | Hare Lake | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997720210921-10Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting997720210921-10Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9977 | 20210921-10 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C258-C267 | Hare Lake | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997720210921-10Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting997720210921-10Excavator - 30 ton- After Jan 10111522.95INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9977 | 20210921-10 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10.5 | Dynamic | 103.84 | 0 |  |  | 1453.725 | 188.9843 | 1642.7093 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C258-C267 | Hare Lake | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997720210921-10Excavator - 30 ton- After Jan 1010.51453.725 | Corbiere and Sons Contracting997720210921-10Excavator - 30 ton- After Jan 1010.51453.725INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9977 | 20210921-10 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 2 | Dynamic | 98.61 | 0 |  |  | 262.96 | 34.1848 | 297.1448 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C258-C267 | Hare Lake | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997720210921-10Dozer D6 or equal- After Jan 102262.96 | Corbiere and Sons Contracting997720210921-10Dozer D6 or equal- After Jan 102262.96INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9939 | 20210920-8 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 4 | HR |  |  | 75 | 0 | 300 | 39 | 339 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Installation of WC605.01 | 6 | C186-C195 | Del Lake | 0 | 2021-09-23 |  | 37 | 2021-09-25 |  |  | 605.01 |  |  | Harold Furlong | 06 | Corbiere and Sons Contracting993920210920-8Operator - Principle - After Jan 104300 | Corbiere and Sons Contracting993920210920-8Operator - Principle - After Jan 104300INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9939 | 20210920-8 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 4 | Dynamic | 110.22 | 0 |  |  | 587.84 | 76.4192 | 664.2592 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Installation of WC605.01 | 6 | C186-C195 | Del Lake | 0 | 2021-09-23 |  | 37 | 2021-09-25 |  |  | 605.01 |  |  | Harold Furlong | 06 | Corbiere and Sons Contracting993920210920-8Excavator - 36 ton- After Jan 104587.84 | Corbiere and Sons Contracting993920210920-8Excavator - 36 ton- After Jan 104587.84INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9938 | 20210920-7 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 44 | HR |  |  | 75 | 0 | 3300 | 429 | 3729 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Del Lake Road towards C195 - Hammering towards C194 | 6 | C186-C195 | Del Lake | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting993820210920-7Operator - Principle - After Jan 10443300 | Corbiere and Sons Contracting993820210920-7Operator - Principle - After Jan 10443300INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9938 | 20210920-7 | 53510602 | Access | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Del Lake Road towards C195 - Hammering towards C194 | 6 | C186-C195 | Del Lake | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting993820210920-7L.O.A.51050 | Corbiere and Sons Contracting993820210920-7L.O.A.51050INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9938 | 20210920-7 | 53510602 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Del Lake Road towards C195 - Hammering towards C194 | 6 | C186-C195 | Del Lake | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting993820210920-7Foreman121140 | Corbiere and Sons Contracting993820210920-7Foreman121140INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9938 | 20210920-7 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Del Lake Road towards C195 - Hammering towards C194 | 6 | C186-C195 | Del Lake | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting993820210920-7Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting993820210920-7Rock Truck - 30 Ton- After Jan 10111518.55INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9938 | 20210920-7 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Del Lake Road towards C195 - Hammering towards C194 | 6 | C186-C195 | Del Lake | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting993820210920-7Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting993820210920-7Light Truck - Pick up- After Jan 102487.5INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9938 | 20210920-7 | 53510602 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 11 | HR | 47.54 | 0 |  |  | 697.18 | 90.6334 | 787.8134 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Del Lake Road towards C195 - Hammering towards C194 | 6 | C186-C195 | Del Lake | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting993820210920-7Excavator Hammer - 30 - 50 ton- After Jan 1011697.18 | Corbiere and Sons Contracting993820210920-7Excavator Hammer - 30 - 50 ton- After Jan 1011697.18INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9938 | 20210920-7 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Del Lake Road towards C195 - Hammering towards C194 | 6 | C186-C195 | Del Lake | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting993820210920-7Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting993820210920-7Excavator - 36 ton- After Jan 10111616.56INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9938 | 20210920-7 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 7 | Dynamic | 110.22 | 0 |  |  | 1028.72 | 133.7336 | 1162.4536 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Del Lake Road towards C195 - Hammering towards C194 | 6 | C186-C195 | Del Lake | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting993820210920-7Excavator - 36 ton- After Jan 1071028.72 | Corbiere and Sons Contracting993820210920-7Excavator - 36 ton- After Jan 1071028.72INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9938 | 20210920-7 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 6 | Dynamic | 103.84 | 0 |  |  | 830.7 | 107.991 | 938.691 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Del Lake Road towards C195 - Hammering towards C194 | 6 | C186-C195 | Del Lake | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting993820210920-7Excavator - 30 ton- After Jan 106830.7 | Corbiere and Sons Contracting993820210920-7Excavator - 30 ton- After Jan 106830.7INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9938 | 20210920-7 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 4 | Dynamic | 98.61 | 0 |  |  | 525.92 | 68.3696 | 594.2896 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Del Lake Road towards C195 - Hammering towards C194 | 6 | C186-C195 | Del Lake | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting993820210920-7Dozer D6 or equal- After Jan 104525.92 | Corbiere and Sons Contracting993820210920-7Dozer D6 or equal- After Jan 104525.92INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9937 | 20210920-6 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 36 | HR |  |  | 75 | 0 | 2700 | 351 | 3051 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Hare Lake road from entrance towards C264 | 6 | C257-C267 | Hare Lake | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting993720210920-6Operator - Principle - After Jan 10362700 | Corbiere and Sons Contracting993720210920-6Operator - Principle - After Jan 10362700INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9937 | 20210920-6 | 53510602 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Hare Lake road from entrance towards C264 | 6 | C257-C267 | Hare Lake | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting993720210920-6L.O.A.3630 | Corbiere and Sons Contracting993720210920-6L.O.A.3630INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9937 | 20210920-6 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Hare Lake road from entrance towards C264 | 6 | C257-C267 | Hare Lake | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting993720210920-6Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting993720210920-6Rock Truck - 30 Ton- After Jan 10111518.55INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9937 | 20210920-6 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Hare Lake road from entrance towards C264 | 6 | C257-C267 | Hare Lake | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting993720210920-6Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting993720210920-6Light Truck - Pick up- After Jan 102487.5INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9937 | 20210920-6 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Hare Lake road from entrance towards C264 | 6 | C257-C267 | Hare Lake | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting993720210920-6Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting993720210920-6Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9937 | 20210920-6 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Hare Lake road from entrance towards C264 | 6 | C257-C267 | Hare Lake | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting993720210920-6Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting993720210920-6Excavator - 30 ton- After Jan 10111522.95INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9937 | 20210920-6 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Hare Lake road from entrance towards C264 | 6 | C257-C267 | Hare Lake | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting993720210920-6Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting993720210920-6Excavator - 30 ton- After Jan 10111522.95INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9967 | 20210920-19 | 53510602 | Access | 0 | ATV - Side by Side w/ roll bar- After Jan 10 | 18.45 | 10 | HR | 0 | 0 |  |  | 184.5 | 23.985 | 208.485 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Billable ATV usage on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-09-29 |  | 37 | 2021-09-30 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting996720210920-19ATV - Side by Side w/ roll bar- After Jan 1010184.5 | Corbiere and Sons Contracting996720210920-19ATV - Side by Side w/ roll bar- After Jan 1010184.5INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9966 | 20210920-18 | 53510602 | Access | 0 | ATV - Side by Side w/ roll bar- After Jan 10 | 18.45 | 10 | HR | 0 | 0 |  |  | 184.5 | 23.985 | 208.485 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Billable ATV usage from Hare Lake Road | 6 | C257-C267 | Hare Lake | 0 | 2021-09-29 |  | 37 | 2021-09-30 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting996620210920-18ATV - Side by Side w/ roll bar- After Jan 1010184.5 | Corbiere and Sons Contracting996620210920-18ATV - Side by Side w/ roll bar- After Jan 1010184.5INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9948 | 20210920-17 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 60 | HR |  |  | 75 | 0 | 4500 | 585 | 5085 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Road on Dead Horse Creek | 6 | C203-C209 | Dead Horse Creek Road | 0 | 2021-09-23 |  | 37 | 2021-09-27 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting994820210920-17Operator - Principle - After Jan 10604500 | Corbiere and Sons Contracting994820210920-17Operator - Principle - After Jan 10604500INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9948 | 20210920-17 | 53510602 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Road on Dead Horse Creek | 6 | C203-C209 | Dead Horse Creek Road | 0 | 2021-09-23 |  | 37 | 2021-09-27 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting994820210920-17Foreman121140 | Corbiere and Sons Contracting994820210920-17Foreman121140INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9948 | 20210920-17 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 22 | Dynamic | 103.54 | 0 |  |  | 3037.1 | 394.823 | 3431.923 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Road on Dead Horse Creek | 6 | C203-C209 | Dead Horse Creek Road | 0 | 2021-09-23 |  | 37 | 2021-09-27 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting994820210920-17Rock Truck - 30 Ton- After Jan 10223037.1 | Corbiere and Sons Contracting994820210920-17Rock Truck - 30 Ton- After Jan 10223037.1INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9948 | 20210920-17 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 4 | DAY | 182.81 | 0 |  |  | 975 | 126.75 | 1101.75 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Road on Dead Horse Creek | 6 | C203-C209 | Dead Horse Creek Road | 0 | 2021-09-23 |  | 37 | 2021-09-27 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting994820210920-17Light Truck - Pick up- After Jan 104975 | Corbiere and Sons Contracting994820210920-17Light Truck - Pick up- After Jan 104975INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9948 | 20210920-17 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Road on Dead Horse Creek | 6 | C203-C209 | Dead Horse Creek Road | 0 | 2021-09-23 |  | 37 | 2021-09-27 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting994820210920-17Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting994820210920-17Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9948 | 20210920-17 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Road on Dead Horse Creek | 6 | C203-C209 | Dead Horse Creek Road | 0 | 2021-09-23 |  | 37 | 2021-09-27 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting994820210920-17Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting994820210920-17Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9948 | 20210920-17 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Road on Dead Horse Creek | 6 | C203-C209 | Dead Horse Creek Road | 0 | 2021-09-23 |  | 37 | 2021-09-27 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting994820210920-17Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting994820210920-17Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9948 | 20210920-17 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Road on Dead Horse Creek | 6 | C203-C209 | Dead Horse Creek Road | 0 | 2021-09-23 |  | 37 | 2021-09-27 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting994820210920-17Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting994820210920-17Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9948 | 20210920-17 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Road on Dead Horse Creek | 6 | C203-C209 | Dead Horse Creek Road | 0 | 2021-09-23 |  | 37 | 2021-09-27 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting994820210920-17Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting994820210920-17Excavator - 36 ton- After Jan 10111616.56INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9948 | 20210920-17 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Road on Dead Horse Creek | 6 | C203-C209 | Dead Horse Creek Road | 0 | 2021-09-23 |  | 37 | 2021-09-27 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting994820210920-17Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting994820210920-17Excavator - 36 ton- After Jan 10111616.56INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9948 | 20210920-17 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Road on Dead Horse Creek | 6 | C203-C209 | Dead Horse Creek Road | 0 | 2021-09-23 |  | 37 | 2021-09-27 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting994820210920-17Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting994820210920-17Excavator - 36 ton- After Jan 10111616.56INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9948 | 20210920-17 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Road on Dead Horse Creek | 6 | C203-C209 | Dead Horse Creek Road | 0 | 2021-09-23 |  | 37 | 2021-09-27 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting994820210920-17Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting994820210920-17Excavator - 30 ton- After Jan 10111522.95INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9948 | 20210920-17 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 4 | Dynamic | 98.61 | 0 |  |  | 525.92 | 68.3696 | 594.2896 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Road on Dead Horse Creek | 6 | C203-C209 | Dead Horse Creek Road | 0 | 2021-09-23 |  | 37 | 2021-09-27 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting994820210920-17Dozer D6 or equal- After Jan 104525.92 | Corbiere and Sons Contracting994820210920-17Dozer D6 or equal- After Jan 104525.92INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9947 | 20210920-16 | 53510602 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 5 | HR |  |  | 70 | 0 | 350 | 45.5 | 395.5 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Neys - Float moved 329 from Red Sucker over to neys | 6 | C219-C235 | Neys | 0 | 2021-09-23 |  | 37 | 2021-09-27 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting994720210920-16Driver - AZ - After Jan 105350 | Corbiere and Sons Contracting994720210920-16Driver - AZ - After Jan 105350INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9947 | 20210920-16 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 60 | HR |  |  | 75 | 0 | 4500 | 585 | 5085 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Neys - Float moved 329 from Red Sucker over to neys | 6 | C219-C235 | Neys | 0 | 2021-09-23 |  | 37 | 2021-09-27 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting994720210920-16Operator - Principle - After Jan 10604500 | Corbiere and Sons Contracting994720210920-16Operator - Principle - After Jan 10604500INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9947 | 20210920-16 | 53510602 | Access | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Neys - Float moved 329 from Red Sucker over to neys | 6 | C219-C235 | Neys | 0 | 2021-09-23 |  | 37 | 2021-09-27 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting994720210920-16L.O.A.61260 | Corbiere and Sons Contracting994720210920-16L.O.A.61260INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9947 | 20210920-16 | 53510602 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Neys - Float moved 329 from Red Sucker over to neys | 6 | C219-C235 | Neys | 0 | 2021-09-23 |  | 37 | 2021-09-27 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting994720210920-16Foreman121140 | Corbiere and Sons Contracting994720210920-16Foreman121140INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9947 | 20210920-16 | 53510602 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 5 | Dynamic | 91.79 | 0 |  |  | 611.95 | 79.5535 | 691.5035 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Neys - Float moved 329 from Red Sucker over to neys | 6 | C219-C235 | Neys | 0 | 2021-09-23 |  | 37 | 2021-09-27 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting994720210920-16Tractor Trailer - 60 Ton- After Jan 105611.95 | Corbiere and Sons Contracting994720210920-16Tractor Trailer - 60 Ton- After Jan 105611.95INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9947 | 20210920-16 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 22 | Dynamic | 103.54 | 0 |  |  | 3037.1 | 394.823 | 3431.923 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Neys - Float moved 329 from Red Sucker over to neys | 6 | C219-C235 | Neys | 0 | 2021-09-23 |  | 37 | 2021-09-27 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting994720210920-16Rock Truck - 30 Ton- After Jan 10223037.1 | Corbiere and Sons Contracting994720210920-16Rock Truck - 30 Ton- After Jan 10223037.1INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9947 | 20210920-16 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 4 | DAY | 182.81 | 0 |  |  | 975 | 126.75 | 1101.75 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Neys - Float moved 329 from Red Sucker over to neys | 6 | C219-C235 | Neys | 0 | 2021-09-23 |  | 37 | 2021-09-27 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting994720210920-16Light Truck - Pick up- After Jan 104975 | Corbiere and Sons Contracting994720210920-16Light Truck - Pick up- After Jan 104975INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9947 | 20210920-16 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 8.5 | HR | 9.16 | 0 |  |  | 103.785 | 13.4921 | 117.2771 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Neys - Float moved 329 from Red Sucker over to neys | 6 | C219-C235 | Neys | 0 | 2021-09-23 |  | 37 | 2021-09-27 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting994720210920-16Excavator Thumb - 30 - 50 ton- After Jan 108.5103.785 | Corbiere and Sons Contracting994720210920-16Excavator Thumb - 30 - 50 ton- After Jan 108.5103.785INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9947 | 20210920-16 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Neys - Float moved 329 from Red Sucker over to neys | 6 | C219-C235 | Neys | 0 | 2021-09-23 |  | 37 | 2021-09-27 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting994720210920-16Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting994720210920-16Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9947 | 20210920-16 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 8.5 | Dynamic | 110.22 | 0 |  |  | 1249.16 | 162.3908 | 1411.5508 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Neys - Float moved 329 from Red Sucker over to neys | 6 | C219-C235 | Neys | 0 | 2021-09-23 |  | 37 | 2021-09-27 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting994720210920-16Excavator - 36 ton- After Jan 108.51249.16 | Corbiere and Sons Contracting994720210920-16Excavator - 36 ton- After Jan 108.51249.16INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9947 | 20210920-16 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Neys - Float moved 329 from Red Sucker over to neys | 6 | C219-C235 | Neys | 0 | 2021-09-23 |  | 37 | 2021-09-27 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting994720210920-16Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting994720210920-16Excavator - 30 ton- After Jan 10111522.95INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9947 | 20210920-16 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Neys - Float moved 329 from Red Sucker over to neys | 6 | C219-C235 | Neys | 0 | 2021-09-23 |  | 37 | 2021-09-27 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting994720210920-16Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting994720210920-16Dozer D6 or equal- After Jan 10111446.28INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9945 | 20210920-14-R1 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 48 | HR |  |  | 75 | 0 | 3600 | 468 | 4068 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building on Little Red Sucker | 6 | C257 - C267 | Little Red Sucker Creek | 0 | 2021-09-23 |  | 37 | 2021-09-25 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting994520210920-14-R1Operator - Principle - After Jan 10483600 | Corbiere and Sons Contracting994520210920-14-R1Operator - Principle - After Jan 10483600INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9945 | 20210920-14-R1 | 53510602 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building on Little Red Sucker | 6 | C257 - C267 | Little Red Sucker Creek | 0 | 2021-09-23 |  | 37 | 2021-09-25 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting994520210920-14-R1L.O.A.4840 | Corbiere and Sons Contracting994520210920-14-R1L.O.A.4840INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9945 | 20210920-14-R1 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 9 | Dynamic | 103.54 | 0 |  |  | 1242.45 | 161.5185 | 1403.9685 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building on Little Red Sucker | 6 | C257 - C267 | Little Red Sucker Creek | 0 | 2021-09-23 |  | 37 | 2021-09-25 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting994520210920-14-R1Rock Truck - 30 Ton- After Jan 1091242.45 | Corbiere and Sons Contracting994520210920-14-R1Rock Truck - 30 Ton- After Jan 1091242.45INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9945 | 20210920-14-R1 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building on Little Red Sucker | 6 | C257 - C267 | Little Red Sucker Creek | 0 | 2021-09-23 |  | 37 | 2021-09-25 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting994520210920-14-R1Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting994520210920-14-R1Rock Truck - 30 Ton- After Jan 10111518.55INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9945 | 20210920-14-R1 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building on Little Red Sucker | 6 | C257 - C267 | Little Red Sucker Creek | 0 | 2021-09-23 |  | 37 | 2021-09-25 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting994520210920-14-R1Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting994520210920-14-R1Light Truck - Pick up- After Jan 101243.75INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9945 | 20210920-14-R1 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building on Little Red Sucker | 6 | C257 - C267 | Little Red Sucker Creek | 0 | 2021-09-23 |  | 37 | 2021-09-25 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting994520210920-14-R1Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting994520210920-14-R1Light Truck - Pick up- After Jan 101243.75INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9945 | 20210920-14-R1 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building on Little Red Sucker | 6 | C257 - C267 | Little Red Sucker Creek | 0 | 2021-09-23 |  | 37 | 2021-09-25 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting994520210920-14-R1Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting994520210920-14-R1Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9945 | 20210920-14-R1 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building on Little Red Sucker | 6 | C257 - C267 | Little Red Sucker Creek | 0 | 2021-09-23 |  | 37 | 2021-09-25 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting994520210920-14-R1Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting994520210920-14-R1Excavator - 30 ton- After Jan 10111522.95INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9945 | 20210920-14-R1 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building on Little Red Sucker | 6 | C257 - C267 | Little Red Sucker Creek | 0 | 2021-09-23 |  | 37 | 2021-09-25 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting994520210920-14-R1Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting994520210920-14-R1Excavator - 30 ton- After Jan 10111522.95INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9943 | 20210920-12 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 30 | HR |  |  | 75 | 0 | 2250 | 292.5 | 2542.5 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting994320210920-12Operator - Principle - After Jan 10302250 | Corbiere and Sons Contracting994320210920-12Operator - Principle - After Jan 10302250INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9943 | 20210920-12 | 53510602 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting994320210920-12L.O.A.2420 | Corbiere and Sons Contracting994320210920-12L.O.A.2420INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9943 | 20210920-12 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting994320210920-12Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting994320210920-12Light Truck - Pick up- After Jan 101243.75INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9943 | 20210920-12 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 5.5 | HR | 9.16 | 0 |  |  | 67.155 | 8.7302 | 75.8851 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting994320210920-12Excavator Thumb - 30 - 50 ton- After Jan 105.567.155 | Corbiere and Sons Contracting994320210920-12Excavator Thumb - 30 - 50 ton- After Jan 105.567.155INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9943 | 20210920-12 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting994320210920-12Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting994320210920-12Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9943 | 20210920-12 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 5.5 | Dynamic | 110.22 | 0 |  |  | 808.28 | 105.0764 | 913.3564 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting994320210920-12Excavator - 36 ton- After Jan 105.5808.28 | Corbiere and Sons Contracting994320210920-12Excavator - 36 ton- After Jan 105.5808.28INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9943 | 20210920-12 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting994320210920-12Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting994320210920-12Excavator - 36 ton- After Jan 10111616.56INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9943 | 20210920-12 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10 | Dynamic | 98.61 | 0 |  |  | 1314.8 | 170.924 | 1485.724 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting994320210920-12Dozer D6 or equal- After Jan 10101314.8 | Corbiere and Sons Contracting994320210920-12Dozer D6 or equal- After Jan 10101314.8INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9941 | 20210920-10 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 42 | HR |  |  | 75 | 0 | 3150 | 409.5 | 3559.5 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting994120210920-10Operator - Principle - After Jan 10423150 | Corbiere and Sons Contracting994120210920-10Operator - Principle - After Jan 10423150INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9941 | 20210920-10 | 53510602 | Access | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting994120210920-10L.O.A.51050 | Corbiere and Sons Contracting994120210920-10L.O.A.51050INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9941 | 20210920-10 | 53510602 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting994120210920-10Foreman121140 | Corbiere and Sons Contracting994120210920-10Foreman121140INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9941 | 20210920-10 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting994120210920-10Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting994120210920-10Rock Truck - 30 Ton- After Jan 10111518.55INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9941 | 20210920-10 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting994120210920-10Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting994120210920-10Light Truck - Pick up- After Jan 103731.25INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9941 | 20210920-10 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 5.5 | HR | 9.16 | 0 |  |  | 67.155 | 8.7302 | 75.8851 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting994120210920-10Excavator Thumb - 30 - 50 ton- After Jan 105.567.155 | Corbiere and Sons Contracting994120210920-10Excavator Thumb - 30 - 50 ton- After Jan 105.567.155INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9941 | 20210920-10 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting994120210920-10Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting994120210920-10Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9941 | 20210920-10 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 5.5 | Dynamic | 110.22 | 0 |  |  | 808.28 | 105.0764 | 913.3564 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting994120210920-10Excavator - 36 ton- After Jan 105.5808.28 | Corbiere and Sons Contracting994120210920-10Excavator - 36 ton- After Jan 105.5808.28INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9941 | 20210920-10 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting994120210920-10Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting994120210920-10Excavator - 36 ton- After Jan 10111616.56INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9941 | 20210920-10 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting994120210920-10Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting994120210920-10Dozer D6 or equal- After Jan 10111446.28INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9928 | 20210919-9 | 53510602 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 4 | HR |  |  | 70 | 0 | 280 | 36.4 | 316.4 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Ripple Creek - DZ floated over from C217 | 6 | C197-C202 | Ripple Creek | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting992820210919-9Driver - AZ - After Jan 104280 | Corbiere and Sons Contracting992820210919-9Driver - AZ - After Jan 104280INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9928 | 20210919-9 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Ripple Creek - DZ floated over from C217 | 6 | C197-C202 | Ripple Creek | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting992820210919-9Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting992820210919-9Operator - Principle - After Jan 1012900INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9928 | 20210919-9 | 53510602 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Ripple Creek - DZ floated over from C217 | 6 | C197-C202 | Ripple Creek | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting992820210919-9L.O.A.1210 | Corbiere and Sons Contracting992820210919-9L.O.A.1210INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9928 | 20210919-9 | 53510602 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 4 | Dynamic | 91.79 | 0 |  |  | 489.56 | 63.6428 | 553.2028 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Ripple Creek - DZ floated over from C217 | 6 | C197-C202 | Ripple Creek | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting992820210919-9Tractor Trailer - 60 Ton- After Jan 104489.56 | Corbiere and Sons Contracting992820210919-9Tractor Trailer - 60 Ton- After Jan 104489.56INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9928 | 20210919-9 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Ripple Creek - DZ floated over from C217 | 6 | C197-C202 | Ripple Creek | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting992820210919-9Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting992820210919-9Light Truck - Pick up- After Jan 101243.75INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9928 | 20210919-9 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Ripple Creek - DZ floated over from C217 | 6 | C197-C202 | Ripple Creek | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting992820210919-9Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting992820210919-9Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9928 | 20210919-9 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Ripple Creek - DZ floated over from C217 | 6 | C197-C202 | Ripple Creek | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting992820210919-9Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting992820210919-9Excavator - 36 ton- After Jan 10111616.56INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9926 | 20210919-7 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 44 | HR |  |  | 75 | 0 | 3300 | 429 | 3729 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting992620210919-7Operator - Principle - After Jan 10443300 | Corbiere and Sons Contracting992620210919-7Operator - Principle - After Jan 10443300INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9926 | 20210919-7 | 53510602 | Access | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting992620210919-7L.O.A.51050 | Corbiere and Sons Contracting992620210919-7L.O.A.51050INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9926 | 20210919-7 | 53510602 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting992620210919-7Foreman121140 | Corbiere and Sons Contracting992620210919-7Foreman121140INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9926 | 20210919-7 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting992620210919-7Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting992620210919-7Rock Truck - 30 Ton- After Jan 10111518.55INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9926 | 20210919-7 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting992620210919-7Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting992620210919-7Light Truck - Pick up- After Jan 103731.25INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9926 | 20210919-7 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 7 | HR | 9.16 | 0 |  |  | 85.47 | 11.1111 | 96.5811 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting992620210919-7Excavator Thumb - 30 - 50 ton- After Jan 10785.47 | Corbiere and Sons Contracting992620210919-7Excavator Thumb - 30 - 50 ton- After Jan 10785.47INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9926 | 20210919-7 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting992620210919-7Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting992620210919-7Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9926 | 20210919-7 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 7 | Dynamic | 110.22 | 0 |  |  | 1028.72 | 133.7336 | 1162.4536 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting992620210919-7Excavator - 36 ton- After Jan 1071028.72 | Corbiere and Sons Contracting992620210919-7Excavator - 36 ton- After Jan 1071028.72INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9926 | 20210919-7 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting992620210919-7Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting992620210919-7Excavator - 36 ton- After Jan 10111616.56INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9926 | 20210919-7 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting992620210919-7Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting992620210919-7Dozer D6 or equal- After Jan 10111446.28INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9925 | 20210919-6 | 53510602 | Access | 0 | Labourer - General - After Jan 10 | 60 | 24 | HR |  |  | 60 | 0 | 1440 | 187.2 | 1627.2 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Del Lake Road towards C195 - Hammering towards C194 | 6 | C186-C195 | Del Lake Road | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting992520210919-6Labourer - General - After Jan 10241440 | Corbiere and Sons Contracting992520210919-6Labourer - General - After Jan 10241440INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9925 | 20210919-6 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 60 | HR |  |  | 75 | 0 | 4500 | 585 | 5085 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Del Lake Road towards C195 - Hammering towards C194 | 6 | C186-C195 | Del Lake Road | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting992520210919-6Operator - Principle - After Jan 10604500 | Corbiere and Sons Contracting992520210919-6Operator - Principle - After Jan 10604500INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9925 | 20210919-6 | 53510602 | Access | 0 | L.O.A. | 210 | 8 | DAY |  |  |  | 0 | 1680 | 218.4 | 1898.4 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Del Lake Road towards C195 - Hammering towards C194 | 6 | C186-C195 | Del Lake Road | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting992520210919-6L.O.A.81680 | Corbiere and Sons Contracting992520210919-6L.O.A.81680INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9925 | 20210919-6 | 53510602 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Del Lake Road towards C195 - Hammering towards C194 | 6 | C186-C195 | Del Lake Road | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting992520210919-6Foreman121140 | Corbiere and Sons Contracting992520210919-6Foreman121140INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9925 | 20210919-6 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Del Lake Road towards C195 - Hammering towards C194 | 6 | C186-C195 | Del Lake Road | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting992520210919-6Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting992520210919-6Rock Truck - 30 Ton- After Jan 10111518.55INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9925 | 20210919-6 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 4 | DAY | 182.81 | 0 |  |  | 975 | 126.75 | 1101.75 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Del Lake Road towards C195 - Hammering towards C194 | 6 | C186-C195 | Del Lake Road | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting992520210919-6Light Truck - Pick up- After Jan 104975 | Corbiere and Sons Contracting992520210919-6Light Truck - Pick up- After Jan 104975INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9925 | 20210919-6 | 53510602 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 11 | HR | 47.54 | 0 |  |  | 697.18 | 90.6334 | 787.8134 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Del Lake Road towards C195 - Hammering towards C194 | 6 | C186-C195 | Del Lake Road | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting992520210919-6Excavator Hammer - 30 - 50 ton- After Jan 1011697.18 | Corbiere and Sons Contracting992520210919-6Excavator Hammer - 30 - 50 ton- After Jan 1011697.18INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9925 | 20210919-6 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Del Lake Road towards C195 - Hammering towards C194 | 6 | C186-C195 | Del Lake Road | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting992520210919-6Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting992520210919-6Excavator - 36 ton- After Jan 10111616.56INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9925 | 20210919-6 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Del Lake Road towards C195 - Hammering towards C194 | 6 | C186-C195 | Del Lake Road | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting992520210919-6Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting992520210919-6Excavator - 36 ton- After Jan 10111616.56INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9925 | 20210919-6 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Del Lake Road towards C195 - Hammering towards C194 | 6 | C186-C195 | Del Lake Road | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting992520210919-6Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting992520210919-6Excavator - 30 ton- After Jan 10111522.95INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9925 | 20210919-6 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Del Lake Road towards C195 - Hammering towards C194 | 6 | C186-C195 | Del Lake Road | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting992520210919-6Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting992520210919-6Dozer D6 or equal- After Jan 10111446.28INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9924 | 20210919-5 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 36 | HR |  |  | 75 | 0 | 2700 | 351 | 3051 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Hare Lake road from entrance towards C264 | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting992420210919-5Operator - Principle - After Jan 10362700 | Corbiere and Sons Contracting992420210919-5Operator - Principle - After Jan 10362700INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9924 | 20210919-5 | 53510602 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Hare Lake road from entrance towards C264 | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting992420210919-5L.O.A.3630 | Corbiere and Sons Contracting992420210919-5L.O.A.3630INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9924 | 20210919-5 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Hare Lake road from entrance towards C264 | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting992420210919-5Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting992420210919-5Rock Truck - 30 Ton- After Jan 10111518.55INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9924 | 20210919-5 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Hare Lake road from entrance towards C264 | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting992420210919-5Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting992420210919-5Light Truck - Pick up- After Jan 102487.5INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9924 | 20210919-5 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Hare Lake road from entrance towards C264 | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting992420210919-5Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting992420210919-5Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9924 | 20210919-5 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Hare Lake road from entrance towards C264 | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting992420210919-5Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting992420210919-5Excavator - 30 ton- After Jan 10111522.95INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9924 | 20210919-5 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Hare Lake road from entrance towards C264 | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting992420210919-5Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting992420210919-5Excavator - 30 ton- After Jan 10111522.95INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9965 | 20210919-16 | 53510602 | Access | 0 | ATV - Side by Side w/ roll bar- After Jan 10 | 18.45 | 10 | HR | 0 | 0 |  |  | 184.5 | 23.985 | 208.485 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Billable time for ATV usage on Little Red Sucker | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-09-29 |  | 37 | 2021-09-30 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting996520210919-16ATV - Side by Side w/ roll bar- After Jan 1010184.5 | Corbiere and Sons Contracting996520210919-16ATV - Side by Side w/ roll bar- After Jan 1010184.5INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9964 | 20210919-15 | 53510602 | Access | 0 | ATV - Side by Side w/ roll bar- After Jan 10 | 18.45 | 10 | HR | 0 | 0 |  |  | 184.5 | 23.985 | 208.485 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Billable ATV usage on Del | 6 | C186-C195 | Del Lake Road | 0 | 2021-09-29 |  | 37 | 2021-09-30 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting996420210919-15ATV - Side by Side w/ roll bar- After Jan 1010184.5 | Corbiere and Sons Contracting996420210919-15ATV - Side by Side w/ roll bar- After Jan 1010184.5INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9932 | 20210919-13 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 24 | HR |  |  | 75 | 0 | 1800 | 234 | 2034 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Road on Dead Horse Creek | 6 | C203-C209 | Dead Horse Creek Road | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting993220210919-13Operator - Principle - After Jan 10241800 | Corbiere and Sons Contracting993220210919-13Operator - Principle - After Jan 10241800INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9932 | 20210919-13 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 16 | HR |  |  | 75 | 0 | 1200 | 156 | 1356 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Road on Dead Horse Creek | 6 | C203-C209 | Dead Horse Creek Road | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting993220210919-13Operator - Principle - After Jan 10161200 | Corbiere and Sons Contracting993220210919-13Operator - Principle - After Jan 10161200INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9932 | 20210919-13 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Road on Dead Horse Creek | 6 | C203-C209 | Dead Horse Creek Road | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting993220210919-13Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting993220210919-13Operator - Principle - After Jan 1011825INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9932 | 20210919-13 | 53510602 | Access | 0 | Foreman | 95 | 8 | HR |  |  | 95 | 0 | 760 | 98.8 | 858.8 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Road on Dead Horse Creek | 6 | C203-C209 | Dead Horse Creek Road | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting993220210919-13Foreman8760 | Corbiere and Sons Contracting993220210919-13Foreman8760INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9932 | 20210919-13 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 22 | Dynamic | 103.54 | 0 |  |  | 3037.1 | 394.823 | 3431.923 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Road on Dead Horse Creek | 6 | C203-C209 | Dead Horse Creek Road | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting993220210919-13Rock Truck - 30 Ton- After Jan 10223037.1 | Corbiere and Sons Contracting993220210919-13Rock Truck - 30 Ton- After Jan 10223037.1INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9932 | 20210919-13 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 4 | DAY | 182.81 | 0 |  |  | 975 | 126.75 | 1101.75 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Road on Dead Horse Creek | 6 | C203-C209 | Dead Horse Creek Road | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting993220210919-13Light Truck - Pick up- After Jan 104975 | Corbiere and Sons Contracting993220210919-13Light Truck - Pick up- After Jan 104975INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9932 | 20210919-13 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 7 | HR | 9.16 | 0 |  |  | 85.47 | 11.1111 | 96.5811 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Road on Dead Horse Creek | 6 | C203-C209 | Dead Horse Creek Road | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting993220210919-13Excavator Thumb - 30 - 50 ton- After Jan 10785.47 | Corbiere and Sons Contracting993220210919-13Excavator Thumb - 30 - 50 ton- After Jan 10785.47INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9932 | 20210919-13 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 7 | HR | 9.16 | 0 |  |  | 85.47 | 11.1111 | 96.5811 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Road on Dead Horse Creek | 6 | C203-C209 | Dead Horse Creek Road | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting993220210919-13Excavator Thumb - 30 - 50 ton- After Jan 10785.47 | Corbiere and Sons Contracting993220210919-13Excavator Thumb - 30 - 50 ton- After Jan 10785.47INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9932 | 20210919-13 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Road on Dead Horse Creek | 6 | C203-C209 | Dead Horse Creek Road | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting993220210919-13Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting993220210919-13Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9932 | 20210919-13 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 7 | Dynamic | 110.22 | 0 |  |  | 1028.72 | 133.7336 | 1162.4536 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Road on Dead Horse Creek | 6 | C203-C209 | Dead Horse Creek Road | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting993220210919-13Excavator - 36 ton- After Jan 1071028.72 | Corbiere and Sons Contracting993220210919-13Excavator - 36 ton- After Jan 1071028.72INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9932 | 20210919-13 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 7 | Dynamic | 110.22 | 0 |  |  | 1028.72 | 133.7336 | 1162.4536 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Road on Dead Horse Creek | 6 | C203-C209 | Dead Horse Creek Road | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting993220210919-13Excavator - 36 ton- After Jan 1071028.72 | Corbiere and Sons Contracting993220210919-13Excavator - 36 ton- After Jan 1071028.72INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9932 | 20210919-13 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Road on Dead Horse Creek | 6 | C203-C209 | Dead Horse Creek Road | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting993220210919-13Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting993220210919-13Excavator - 30 ton- After Jan 10111522.95INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9932 | 20210919-13 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 9 | Dynamic | 98.61 | 0 |  |  | 1183.32 | 153.8316 | 1337.1516 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Road on Dead Horse Creek | 6 | C203-C209 | Dead Horse Creek Road | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting993220210919-13Dozer D6 or equal- After Jan 1091183.32 | Corbiere and Sons Contracting993220210919-13Dozer D6 or equal- After Jan 1091183.32INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9931 | 20210919-12 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 60 | HR |  |  | 75 | 0 | 4500 | 585 | 5085 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Neys | 6 | C219-C235 | Neys | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting993120210919-12Operator - Principle - After Jan 10604500 | Corbiere and Sons Contracting993120210919-12Operator - Principle - After Jan 10604500INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9931 | 20210919-12 | 53510602 | Access | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Neys | 6 | C219-C235 | Neys | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting993120210919-12L.O.A.51050 | Corbiere and Sons Contracting993120210919-12L.O.A.51050INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9931 | 20210919-12 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 22 | Dynamic | 103.54 | 0 |  |  | 3037.1 | 394.823 | 3431.923 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Neys | 6 | C219-C235 | Neys | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting993120210919-12Rock Truck - 30 Ton- After Jan 10223037.1 | Corbiere and Sons Contracting993120210919-12Rock Truck - 30 Ton- After Jan 10223037.1INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9931 | 20210919-12 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Neys | 6 | C219-C235 | Neys | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting993120210919-12Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting993120210919-12Light Truck - Pick up- After Jan 103731.25INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9931 | 20210919-12 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Neys | 6 | C219-C235 | Neys | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting993120210919-12Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting993120210919-12Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9931 | 20210919-12 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Neys | 6 | C219-C235 | Neys | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting993120210919-12Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting993120210919-12Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9931 | 20210919-12 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Neys | 6 | C219-C235 | Neys | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting993120210919-12Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting993120210919-12Excavator - 36 ton- After Jan 10111616.56INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9931 | 20210919-12 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Neys | 6 | C219-C235 | Neys | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting993120210919-12Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting993120210919-12Excavator - 30 ton- After Jan 10111522.95INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9931 | 20210919-12 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Neys | 6 | C219-C235 | Neys | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting993120210919-12Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting993120210919-12Dozer D6 or equal- After Jan 10111446.28INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9930 | 20210919-11 | 53510602 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 7 | HR |  |  | 70 | 0 | 490 | 63.7 | 553.7 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building on Little Red Sucker - Float moved Ex and RT to this site | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting993020210919-11Driver - AZ - After Jan 107490 | Corbiere and Sons Contracting993020210919-11Driver - AZ - After Jan 107490INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9930 | 20210919-11 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 60 | HR |  |  | 75 | 0 | 4500 | 585 | 5085 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building on Little Red Sucker - Float moved Ex and RT to this site | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting993020210919-11Operator - Principle - After Jan 10604500 | Corbiere and Sons Contracting993020210919-11Operator - Principle - After Jan 10604500INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9930 | 20210919-11 | 53510602 | Access | 0 | L.O.A. | 210 | 7 | DAY |  |  |  | 0 | 1470 | 191.1 | 1661.1 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building on Little Red Sucker - Float moved Ex and RT to this site | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting993020210919-11L.O.A.71470 | Corbiere and Sons Contracting993020210919-11L.O.A.71470INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9930 | 20210919-11 | 53510602 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building on Little Red Sucker - Float moved Ex and RT to this site | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting993020210919-11Foreman121140 | Corbiere and Sons Contracting993020210919-11Foreman121140INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9930 | 20210919-11 | 53510602 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 7 | Dynamic | 91.79 | 0 |  |  | 856.73 | 111.3749 | 968.1049 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building on Little Red Sucker - Float moved Ex and RT to this site | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting993020210919-11Tractor Trailer - 60 Ton- After Jan 107856.73 | Corbiere and Sons Contracting993020210919-11Tractor Trailer - 60 Ton- After Jan 107856.73INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9930 | 20210919-11 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 10 | Dynamic | 103.54 | 0 |  |  | 1380.5 | 179.465 | 1559.965 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building on Little Red Sucker - Float moved Ex and RT to this site | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting993020210919-11Rock Truck - 30 Ton- After Jan 10101380.5 | Corbiere and Sons Contracting993020210919-11Rock Truck - 30 Ton- After Jan 10101380.5INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9930 | 20210919-11 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building on Little Red Sucker - Float moved Ex and RT to this site | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting993020210919-11Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting993020210919-11Rock Truck - 30 Ton- After Jan 10111518.55INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9930 | 20210919-11 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 4 | DAY | 182.81 | 0 |  |  | 975 | 126.75 | 1101.75 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building on Little Red Sucker - Float moved Ex and RT to this site | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting993020210919-11Light Truck - Pick up- After Jan 104975 | Corbiere and Sons Contracting993020210919-11Light Truck - Pick up- After Jan 104975INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9930 | 20210919-11 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 9.16 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building on Little Red Sucker - Float moved Ex and RT to this site | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting993020210919-11Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting993020210919-11Excavator Thumb - 30 - 50 ton- After Jan 1010122.1INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9930 | 20210919-11 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10 | Dynamic | 103.84 | 0 |  |  | 1384.5 | 179.985 | 1564.485 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building on Little Red Sucker - Float moved Ex and RT to this site | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting993020210919-11Excavator - 30 ton- After Jan 10101384.5 | Corbiere and Sons Contracting993020210919-11Excavator - 30 ton- After Jan 10101384.5INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9930 | 20210919-11 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building on Little Red Sucker - Float moved Ex and RT to this site | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting993020210919-11Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting993020210919-11Excavator - 30 ton- After Jan 10111522.95INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9930 | 20210919-11 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building on Little Red Sucker - Float moved Ex and RT to this site | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting993020210919-11Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting993020210919-11Dozer D6 or equal- After Jan 10111446.28INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9909 | 20210918-8 | 53510602 | Access | 0 | Labourer - General - After Jan 10 | 60 | 8 | HR |  |  | 60 | 0 | 480 | 62.4 | 542.4 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Del Lake Road towards C195 | 6 | C186-C195 | Del Lake | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting990920210918-8Labourer - General - After Jan 108480 | Corbiere and Sons Contracting990920210918-8Labourer - General - After Jan 108480INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9909 | 20210918-8 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 46 | HR |  |  | 75 | 0 | 3450 | 448.5 | 3898.5 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Del Lake Road towards C195 | 6 | C186-C195 | Del Lake | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting990920210918-8Operator - Principle - After Jan 10463450 | Corbiere and Sons Contracting990920210918-8Operator - Principle - After Jan 10463450INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9909 | 20210918-8 | 53510602 | Access | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Del Lake Road towards C195 | 6 | C186-C195 | Del Lake | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting990920210918-8L.O.A.51050 | Corbiere and Sons Contracting990920210918-8L.O.A.51050INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9909 | 20210918-8 | 53510602 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Del Lake Road towards C195 | 6 | C186-C195 | Del Lake | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting990920210918-8Foreman121140 | Corbiere and Sons Contracting990920210918-8Foreman121140INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9909 | 20210918-8 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Del Lake Road towards C195 | 6 | C186-C195 | Del Lake | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting990920210918-8Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting990920210918-8Rock Truck - 30 Ton- After Jan 10111518.55INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9909 | 20210918-8 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Del Lake Road towards C195 | 6 | C186-C195 | Del Lake | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting990920210918-8Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting990920210918-8Light Truck - Pick up- After Jan 103731.25INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9909 | 20210918-8 | 53510602 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 11 | HR | 47.54 | 0 |  |  | 697.18 | 90.6334 | 787.8134 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Del Lake Road towards C195 | 6 | C186-C195 | Del Lake | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting990920210918-8Excavator Hammer - 30 - 50 ton- After Jan 1011697.18 | Corbiere and Sons Contracting990920210918-8Excavator Hammer - 30 - 50 ton- After Jan 1011697.18INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9909 | 20210918-8 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Del Lake Road towards C195 | 6 | C186-C195 | Del Lake | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting990920210918-8Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting990920210918-8Excavator - 36 ton- After Jan 10111616.56INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9909 | 20210918-8 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 5.5 | Dynamic | 110.22 | 0 |  |  | 808.28 | 105.0764 | 913.3564 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Del Lake Road towards C195 | 6 | C186-C195 | Del Lake | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting990920210918-8Excavator - 36 ton- After Jan 105.5808.28 | Corbiere and Sons Contracting990920210918-8Excavator - 36 ton- After Jan 105.5808.28INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9909 | 20210918-8 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 3 | Dynamic | 103.84 | 0 |  |  | 415.35 | 53.9955 | 469.3455 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Del Lake Road towards C195 | 6 | C186-C195 | Del Lake | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting990920210918-8Excavator - 30 ton- After Jan 103415.35 | Corbiere and Sons Contracting990920210918-8Excavator - 30 ton- After Jan 103415.35INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9909 | 20210918-8 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Del Lake Road towards C195 | 6 | C186-C195 | Del Lake | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting990920210918-8Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting990920210918-8Dozer D6 or equal- After Jan 10111446.28INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9907 | 20210918-6 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 19 | HR |  |  | 75 | 0 | 1425 | 185.25 | 1610.25 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Hare Lake road from entrance towards C264 | 6 | C257-C267 | Hare Lake | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting990720210918-6Operator - Principle - After Jan 10191425 | Corbiere and Sons Contracting990720210918-6Operator - Principle - After Jan 10191425INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9907 | 20210918-6 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Hare Lake road from entrance towards C264 | 6 | C257-C267 | Hare Lake | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting990720210918-6Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting990720210918-6Operator - Principle - After Jan 1012900INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9907 | 20210918-6 | 53510602 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Hare Lake road from entrance towards C264 | 6 | C257-C267 | Hare Lake | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting990720210918-6L.O.A.3630 | Corbiere and Sons Contracting990720210918-6L.O.A.3630INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9907 | 20210918-6 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Hare Lake road from entrance towards C264 | 6 | C257-C267 | Hare Lake | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting990720210918-6Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting990720210918-6Rock Truck - 30 Ton- After Jan 10111518.55INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9907 | 20210918-6 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Hare Lake road from entrance towards C264 | 6 | C257-C267 | Hare Lake | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting990720210918-6Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting990720210918-6Light Truck - Pick up- After Jan 102487.5INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9907 | 20210918-6 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Hare Lake road from entrance towards C264 | 6 | C257-C267 | Hare Lake | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting990720210918-6Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting990720210918-6Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9907 | 20210918-6 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Hare Lake road from entrance towards C264 | 6 | C257-C267 | Hare Lake | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting990720210918-6Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting990720210918-6Excavator - 30 ton- After Jan 10111522.95INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9907 | 20210918-6 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10 | Dynamic | 103.84 | 0 |  |  | 1384.5 | 179.985 | 1564.485 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Hare Lake road from entrance towards C264 | 6 | C257-C267 | Hare Lake | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting990720210918-6Excavator - 30 ton- After Jan 10101384.5 | Corbiere and Sons Contracting990720210918-6Excavator - 30 ton- After Jan 10101384.5INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9962 | 20210918-22 | 53510602 | Access | 0 | ATV - Side by Side w/ roll bar- After Jan 10 | 18.45 | 10 | HR | 0 | 0 |  |  | 184.5 | 23.985 | 208.485 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Billable ATV usage on Hare Lake Road | 6 | C219-C236 | Neys | 0 | 2021-09-29 |  | 37 | 2021-09-30 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting996220210918-22ATV - Side by Side w/ roll bar- After Jan 1010184.5 | Corbiere and Sons Contracting996220210918-22ATV - Side by Side w/ roll bar- After Jan 1010184.5INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9961 | 20210918-21 | 53510602 | Access | 0 | ATV - Side by Side w/ roll bar- After Jan 10 | 18.45 | 10 | HR | 13.84 | 0 |  |  | 184.5 | 23.985 | 208.485 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Billable ATV usage on Hare Lake Road | 6 | C257-C267 | Hare Lake | 0 | 2021-09-29 |  | 37 | 2021-09-30 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting996120210918-21ATV - Side by Side w/ roll bar- After Jan 1010184.5 | Corbiere and Sons Contracting996120210918-21ATV - Side by Side w/ roll bar- After Jan 1010184.5INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9919 | 20210918-18 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 52 | HR |  |  | 75 | 0 | 3900 | 507 | 4407 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Road on Dead Horse Creek | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting991920210918-18Operator - Principle - After Jan 10523900 | Corbiere and Sons Contracting991920210918-18Operator - Principle - After Jan 10523900INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9919 | 20210918-18 | 53510602 | Access | 0 | Foreman | 95 | 9 | HR |  |  | 95 | 0 | 855 | 111.15 | 966.15 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Road on Dead Horse Creek | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting991920210918-18Foreman9855 | Corbiere and Sons Contracting991920210918-18Foreman9855INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9919 | 20210918-18 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 8 | Dynamic | 103.54 | 0 |  |  | 1104.4 | 143.572 | 1247.972 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Road on Dead Horse Creek | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting991920210918-18Rock Truck - 30 Ton- After Jan 1081104.4 | Corbiere and Sons Contracting991920210918-18Rock Truck - 30 Ton- After Jan 1081104.4INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9919 | 20210918-18 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 4 | DAY | 182.81 | 0 |  |  | 975 | 126.75 | 1101.75 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Road on Dead Horse Creek | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting991920210918-18Light Truck - Pick up- After Jan 104975 | Corbiere and Sons Contracting991920210918-18Light Truck - Pick up- After Jan 104975INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9919 | 20210918-18 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Road on Dead Horse Creek | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting991920210918-18Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting991920210918-18Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9919 | 20210918-18 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Road on Dead Horse Creek | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting991920210918-18Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting991920210918-18Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9919 | 20210918-18 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 8 | HR | 9.16 | 0 |  |  | 97.68 | 12.6984 | 110.3784 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Road on Dead Horse Creek | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting991920210918-18Excavator Thumb - 30 - 50 ton- After Jan 10897.68 | Corbiere and Sons Contracting991920210918-18Excavator Thumb - 30 - 50 ton- After Jan 10897.68INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9919 | 20210918-18 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 8 | HR | 9.16 | 0 |  |  | 97.68 | 12.6984 | 110.3784 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Road on Dead Horse Creek | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting991920210918-18Excavator Thumb - 30 - 50 ton- After Jan 10897.68 | Corbiere and Sons Contracting991920210918-18Excavator Thumb - 30 - 50 ton- After Jan 10897.68INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9919 | 20210918-18 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Road on Dead Horse Creek | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting991920210918-18Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting991920210918-18Excavator - 36 ton- After Jan 10111616.56INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9919 | 20210918-18 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Road on Dead Horse Creek | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting991920210918-18Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting991920210918-18Excavator - 36 ton- After Jan 10111616.56INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9919 | 20210918-18 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 8 | Dynamic | 110.22 | 0 |  |  | 1175.68 | 152.8384 | 1328.5184 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Road on Dead Horse Creek | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting991920210918-18Excavator - 36 ton- After Jan 1081175.68 | Corbiere and Sons Contracting991920210918-18Excavator - 36 ton- After Jan 1081175.68INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9919 | 20210918-18 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 8 | Dynamic | 103.84 | 0 |  |  | 1107.6 | 143.988 | 1251.588 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Road on Dead Horse Creek | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting991920210918-18Excavator - 30 ton- After Jan 1081107.6 | Corbiere and Sons Contracting991920210918-18Excavator - 30 ton- After Jan 1081107.6INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9919 | 20210918-18 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10 | Dynamic | 98.61 | 0 |  |  | 1314.8 | 170.924 | 1485.724 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Road on Dead Horse Creek | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting991920210918-18Dozer D6 or equal- After Jan 10101314.8 | Corbiere and Sons Contracting991920210918-18Dozer D6 or equal- After Jan 10101314.8INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9918 | 20210918-17 | 53510602 | Access | 0 | Labourer - General - After Jan 10 | 60 | 12 | HR |  |  | 60 | 0 | 720 | 93.6 | 813.6 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Neys | 6 | C219-C235 | Neys | 0 | 2021-09-23 |  | 37 | 2021-09-25 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting991820210918-17Labourer - General - After Jan 1012720 | Corbiere and Sons Contracting991820210918-17Labourer - General - After Jan 1012720INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9918 | 20210918-17 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 60 | HR |  |  | 75 | 0 | 4500 | 585 | 5085 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Neys | 6 | C219-C235 | Neys | 0 | 2021-09-23 |  | 37 | 2021-09-25 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting991820210918-17Operator - Principle - After Jan 10604500 | Corbiere and Sons Contracting991820210918-17Operator - Principle - After Jan 10604500INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9918 | 20210918-17 | 53510602 | Access | 0 | L.O.A. | 210 | 7 | DAY |  |  |  | 0 | 1470 | 191.1 | 1661.1 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Neys | 6 | C219-C235 | Neys | 0 | 2021-09-23 |  | 37 | 2021-09-25 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting991820210918-17L.O.A.71470 | Corbiere and Sons Contracting991820210918-17L.O.A.71470INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9918 | 20210918-17 | 53510602 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Neys | 6 | C219-C235 | Neys | 0 | 2021-09-23 |  | 37 | 2021-09-25 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting991820210918-17Foreman121140 | Corbiere and Sons Contracting991820210918-17Foreman121140INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9918 | 20210918-17 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Neys | 6 | C219-C235 | Neys | 0 | 2021-09-23 |  | 37 | 2021-09-25 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting991820210918-17Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting991820210918-17Rock Truck - 30 Ton- After Jan 10111518.55INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9918 | 20210918-17 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Neys | 6 | C219-C235 | Neys | 0 | 2021-09-23 |  | 37 | 2021-09-25 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting991820210918-17Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting991820210918-17Rock Truck - 30 Ton- After Jan 10111518.55INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9918 | 20210918-17 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 4 | DAY | 182.81 | 0 |  |  | 975 | 126.75 | 1101.75 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Neys | 6 | C219-C235 | Neys | 0 | 2021-09-23 |  | 37 | 2021-09-25 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting991820210918-17Light Truck - Pick up- After Jan 104975 | Corbiere and Sons Contracting991820210918-17Light Truck - Pick up- After Jan 104975INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9918 | 20210918-17 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Neys | 6 | C219-C235 | Neys | 0 | 2021-09-23 |  | 37 | 2021-09-25 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting991820210918-17Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting991820210918-17Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9918 | 20210918-17 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Neys | 6 | C219-C235 | Neys | 0 | 2021-09-23 |  | 37 | 2021-09-25 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting991820210918-17Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting991820210918-17Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9918 | 20210918-17 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Neys | 6 | C219-C235 | Neys | 0 | 2021-09-23 |  | 37 | 2021-09-25 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting991820210918-17Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting991820210918-17Excavator - 36 ton- After Jan 10111616.56INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9918 | 20210918-17 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Neys | 6 | C219-C235 | Neys | 0 | 2021-09-23 |  | 37 | 2021-09-25 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting991820210918-17Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting991820210918-17Excavator - 30 ton- After Jan 10111522.95INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9918 | 20210918-17 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Neys | 6 | C219-C235 | Neys | 0 | 2021-09-23 |  | 37 | 2021-09-25 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting991820210918-17Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting991820210918-17Dozer D6 or equal- After Jan 10111446.28INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9915 | 20210918-14 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 28 | HR |  |  | 75 | 0 | 2100 | 273 | 2373 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Little Red Sucker Access | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting991520210918-14Operator - Principle - After Jan 10282100 | Corbiere and Sons Contracting991520210918-14Operator - Principle - After Jan 10282100INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9915 | 20210918-14 | 53510602 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Little Red Sucker Access | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting991520210918-14L.O.A.3630 | Corbiere and Sons Contracting991520210918-14L.O.A.3630INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9915 | 20210918-14 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Little Red Sucker Access | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting991520210918-14Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting991520210918-14Rock Truck - 30 Ton- After Jan 10111518.55INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9915 | 20210918-14 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Little Red Sucker Access | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting991520210918-14Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting991520210918-14Light Truck - Pick up- After Jan 102487.5INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9915 | 20210918-14 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Little Red Sucker Access | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting991520210918-14Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting991520210918-14Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9915 | 20210918-14 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Little Red Sucker Access | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting991520210918-14Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting991520210918-14Excavator - 30 ton- After Jan 10111522.95INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9915 | 20210918-14 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 3 | Dynamic | 103.84 | 0 |  |  | 415.35 | 53.9955 | 469.3455 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Little Red Sucker Access | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting991520210918-14Excavator - 30 ton- After Jan 103415.35 | Corbiere and Sons Contracting991520210918-14Excavator - 30 ton- After Jan 103415.35INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9914 | 20210918-13 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 36 | HR |  |  | 75 | 0 | 2700 | 351 | 3051 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Little Pic from C215 to C216 | 6 | C215-C216 | Little Pic River | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting991420210918-13Operator - Principle - After Jan 10362700 | Corbiere and Sons Contracting991420210918-13Operator - Principle - After Jan 10362700INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9914 | 20210918-13 | 53510602 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Little Pic from C215 to C216 | 6 | C215-C216 | Little Pic River | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting991420210918-13L.O.A.3630 | Corbiere and Sons Contracting991420210918-13L.O.A.3630INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9914 | 20210918-13 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Little Pic from C215 to C216 | 6 | C215-C216 | Little Pic River | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting991420210918-13Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting991420210918-13Rock Truck - 30 Ton- After Jan 10111518.55INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9914 | 20210918-13 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Little Pic from C215 to C216 | 6 | C215-C216 | Little Pic River | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting991420210918-13Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting991420210918-13Light Truck - Pick up- After Jan 101243.75INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9914 | 20210918-13 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Little Pic from C215 to C216 | 6 | C215-C216 | Little Pic River | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting991420210918-13Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting991420210918-13Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9914 | 20210918-13 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Little Pic from C215 to C216 | 6 | C215-C216 | Little Pic River | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting991420210918-13Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting991420210918-13Excavator - 30 ton- After Jan 10111522.95INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9914 | 20210918-13 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Little Pic from C215 to C216 | 6 | C215-C216 | Little Pic River | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting991420210918-13Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting991420210918-13Dozer D6 or equal- After Jan 10111446.28INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9913 | 20210918-12 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting991320210918-12Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting991320210918-12Operator - Principle - After Jan 1012900INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9913 | 20210918-12 | 53510602 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting991320210918-12L.O.A.1210 | Corbiere and Sons Contracting991320210918-12L.O.A.1210INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9913 | 20210918-12 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting991320210918-12Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting991320210918-12Light Truck - Pick up- After Jan 101243.75INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9913 | 20210918-12 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting991320210918-12Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting991320210918-12Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9913 | 20210918-12 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting991320210918-12Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting991320210918-12Excavator - 36 ton- After Jan 10111616.56INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9911 | 20210918-10 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 44 | HR |  |  | 75 | 0 | 3300 | 429 | 3729 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting991120210918-10Operator - Principle - After Jan 10443300 | Corbiere and Sons Contracting991120210918-10Operator - Principle - After Jan 10443300INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9911 | 20210918-10 | 53510602 | Access | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting991120210918-10L.O.A.51050 | Corbiere and Sons Contracting991120210918-10L.O.A.51050INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9911 | 20210918-10 | 53510602 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting991120210918-10Foreman121140 | Corbiere and Sons Contracting991120210918-10Foreman121140INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9911 | 20210918-10 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting991120210918-10Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting991120210918-10Rock Truck - 30 Ton- After Jan 10111518.55INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9911 | 20210918-10 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting991120210918-10Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting991120210918-10Light Truck - Pick up- After Jan 103731.25INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9911 | 20210918-10 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 7 | HR | 9.16 | 0 |  |  | 85.47 | 11.1111 | 96.5811 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting991120210918-10Excavator Thumb - 30 - 50 ton- After Jan 10785.47 | Corbiere and Sons Contracting991120210918-10Excavator Thumb - 30 - 50 ton- After Jan 10785.47INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9911 | 20210918-10 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting991120210918-10Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting991120210918-10Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9911 | 20210918-10 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 7 | Dynamic | 110.22 | 0 |  |  | 1028.72 | 133.7336 | 1162.4536 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting991120210918-10Excavator - 36 ton- After Jan 1071028.72 | Corbiere and Sons Contracting991120210918-10Excavator - 36 ton- After Jan 1071028.72INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9911 | 20210918-10 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting991120210918-10Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting991120210918-10Excavator - 36 ton- After Jan 10111616.56INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9911 | 20210918-10 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from Middleton | 6 | C210-C213 | Middleton | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting991120210918-10Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting991120210918-10Dozer D6 or equal- After Jan 10111446.28INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9875 | 20210917-8 | 53510602 | Access | 0 | Labourer - General - After Jan 10 | 60 | 12 | HR |  |  | 60 | 0 | 720 | 93.6 | 813.6 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Del Lake towards WC8110.01 and hammering towards C195; Labourers rolling out and bringing geo | 6 | C186-C195 | Del Lake | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting987520210917-8Labourer - General - After Jan 1012720 | Corbiere and Sons Contracting987520210917-8Labourer - General - After Jan 1012720INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9875 | 20210917-8 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 48 | HR |  |  | 75 | 0 | 3600 | 468 | 4068 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Del Lake towards WC8110.01 and hammering towards C195; Labourers rolling out and bringing geo | 6 | C186-C195 | Del Lake | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting987520210917-8Operator - Principle - After Jan 10483600 | Corbiere and Sons Contracting987520210917-8Operator - Principle - After Jan 10483600INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9875 | 20210917-8 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 8 | HR |  |  | 75 | 0 | 600 | 78 | 678 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Del Lake towards WC8110.01 and hammering towards C195; Labourers rolling out and bringing geo | 6 | C186-C195 | Del Lake | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting987520210917-8Operator - Principle - After Jan 108600 | Corbiere and Sons Contracting987520210917-8Operator - Principle - After Jan 108600INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9875 | 20210917-8 | 53510602 | Access | 0 | L.O.A. | 210 | 8 | DAY |  |  |  | 0 | 1680 | 218.4 | 1898.4 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Del Lake towards WC8110.01 and hammering towards C195; Labourers rolling out and bringing geo | 6 | C186-C195 | Del Lake | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting987520210917-8L.O.A.81680 | Corbiere and Sons Contracting987520210917-8L.O.A.81680INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9875 | 20210917-8 | 53510602 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Del Lake towards WC8110.01 and hammering towards C195; Labourers rolling out and bringing geo | 6 | C186-C195 | Del Lake | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting987520210917-8Foreman121140 | Corbiere and Sons Contracting987520210917-8Foreman121140INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9875 | 20210917-8 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Del Lake towards WC8110.01 and hammering towards C195; Labourers rolling out and bringing geo | 6 | C186-C195 | Del Lake | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting987520210917-8Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting987520210917-8Rock Truck - 30 Ton- After Jan 10111518.55INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9875 | 20210917-8 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Del Lake towards WC8110.01 and hammering towards C195; Labourers rolling out and bringing geo | 6 | C186-C195 | Del Lake | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting987520210917-8Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting987520210917-8Light Truck - Pick up- After Jan 103731.25INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9875 | 20210917-8 | 53510602 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 11 | HR | 47.54 | 0 |  |  | 697.18 | 90.6334 | 787.8134 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Del Lake towards WC8110.01 and hammering towards C195; Labourers rolling out and bringing geo | 6 | C186-C195 | Del Lake | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting987520210917-8Excavator Hammer - 30 - 50 ton- After Jan 1011697.18 | Corbiere and Sons Contracting987520210917-8Excavator Hammer - 30 - 50 ton- After Jan 1011697.18INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9875 | 20210917-8 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Del Lake towards WC8110.01 and hammering towards C195; Labourers rolling out and bringing geo | 6 | C186-C195 | Del Lake | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting987520210917-8Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting987520210917-8Excavator - 36 ton- After Jan 10111616.56INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9875 | 20210917-8 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 7 | Dynamic | 110.22 | 0 |  |  | 1028.72 | 133.7336 | 1162.4536 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Del Lake towards WC8110.01 and hammering towards C195; Labourers rolling out and bringing geo | 6 | C186-C195 | Del Lake | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting987520210917-8Excavator - 36 ton- After Jan 1071028.72 | Corbiere and Sons Contracting987520210917-8Excavator - 36 ton- After Jan 1071028.72INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9875 | 20210917-8 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Del Lake towards WC8110.01 and hammering towards C195; Labourers rolling out and bringing geo | 6 | C186-C195 | Del Lake | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting987520210917-8Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting987520210917-8Excavator - 30 ton- After Jan 10111522.95INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9875 | 20210917-8 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Del Lake towards WC8110.01 and hammering towards C195; Labourers rolling out and bringing geo | 6 | C186-C195 | Del Lake | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting987520210917-8Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting987520210917-8Dozer D6 or equal- After Jan 10111446.28INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9872 | 20210917-5 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 8 | HR |  |  | 75 | 0 | 600 | 78 | 678 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Hare Lake road from entrance towards C264, John Hunter build subgrade to C266 and then walk to entrance to dig out, punch out, and place access mats, Darwin dug ditch and swale pot holes, Keeegan K worked as a labourer after road become to soft for RT | 6 | C257-C267 | Hare Lake | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting987220210917-5Operator - Principle - After Jan 108600 | Corbiere and Sons Contracting987220210917-5Operator - Principle - After Jan 108600INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9872 | 20210917-5 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Hare Lake road from entrance towards C264, John Hunter build subgrade to C266 and then walk to entrance to dig out, punch out, and place access mats, Darwin dug ditch and swale pot holes, Keeegan K worked as a labourer after road become to soft for RT | 6 | C257-C267 | Hare Lake | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting987220210917-5Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting987220210917-5Operator - Principle - After Jan 1012900INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9872 | 20210917-5 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Hare Lake road from entrance towards C264, John Hunter build subgrade to C266 and then walk to entrance to dig out, punch out, and place access mats, Darwin dug ditch and swale pot holes, Keeegan K worked as a labourer after road become to soft for RT | 6 | C257-C267 | Hare Lake | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting987220210917-5Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting987220210917-5Operator - Principle - After Jan 1012900INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9872 | 20210917-5 | 53510602 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Hare Lake road from entrance towards C264, John Hunter build subgrade to C266 and then walk to entrance to dig out, punch out, and place access mats, Darwin dug ditch and swale pot holes, Keeegan K worked as a labourer after road become to soft for RT | 6 | C257-C267 | Hare Lake | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting987220210917-5L.O.A.3630 | Corbiere and Sons Contracting987220210917-5L.O.A.3630INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9872 | 20210917-5 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 5 | Dynamic | 103.54 | 0 |  |  | 690.25 | 89.7325 | 779.9825 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Hare Lake road from entrance towards C264, John Hunter build subgrade to C266 and then walk to entrance to dig out, punch out, and place access mats, Darwin dug ditch and swale pot holes, Keeegan K worked as a labourer after road become to soft for RT | 6 | C257-C267 | Hare Lake | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting987220210917-5Rock Truck - 30 Ton- After Jan 105690.25 | Corbiere and Sons Contracting987220210917-5Rock Truck - 30 Ton- After Jan 105690.25INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9872 | 20210917-5 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Hare Lake road from entrance towards C264, John Hunter build subgrade to C266 and then walk to entrance to dig out, punch out, and place access mats, Darwin dug ditch and swale pot holes, Keeegan K worked as a labourer after road become to soft for RT | 6 | C257-C267 | Hare Lake | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting987220210917-5Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting987220210917-5Light Truck - Pick up- After Jan 102487.5INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9872 | 20210917-5 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 7 | HR | 9.16 | 0 |  |  | 85.47 | 11.1111 | 96.5811 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Hare Lake road from entrance towards C264, John Hunter build subgrade to C266 and then walk to entrance to dig out, punch out, and place access mats, Darwin dug ditch and swale pot holes, Keeegan K worked as a labourer after road become to soft for RT | 6 | C257-C267 | Hare Lake | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting987220210917-5Excavator Thumb - 30 - 50 ton- After Jan 10785.47 | Corbiere and Sons Contracting987220210917-5Excavator Thumb - 30 - 50 ton- After Jan 10785.47INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9872 | 20210917-5 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 7 | Dynamic | 103.84 | 0 |  |  | 969.15 | 125.9895 | 1095.1395 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Hare Lake road from entrance towards C264, John Hunter build subgrade to C266 and then walk to entrance to dig out, punch out, and place access mats, Darwin dug ditch and swale pot holes, Keeegan K worked as a labourer after road become to soft for RT | 6 | C257-C267 | Hare Lake | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting987220210917-5Excavator - 30 ton- After Jan 107969.15 | Corbiere and Sons Contracting987220210917-5Excavator - 30 ton- After Jan 107969.15INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9872 | 20210917-5 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Hare Lake road from entrance towards C264, John Hunter build subgrade to C266 and then walk to entrance to dig out, punch out, and place access mats, Darwin dug ditch and swale pot holes, Keeegan K worked as a labourer after road become to soft for RT | 6 | C257-C267 | Hare Lake | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting987220210917-5Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting987220210917-5Excavator - 30 ton- After Jan 10111522.95INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9960 | 20210917-21 | 53510602 | Access | 0 | ATV - Side by Side w/ roll bar- After Jan 10 | 18.45 | 10 | HR | 13.84 | 0 |  |  | 184.5 | 23.985 | 208.485 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Billable time for ATV used on site | 6 | C186-C195 | Del Lake | 0 | 2021-09-29 |  | 37 | 2021-09-30 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting996020210917-21ATV - Side by Side w/ roll bar- After Jan 1010184.5 | Corbiere and Sons Contracting996020210917-21ATV - Side by Side w/ roll bar- After Jan 1010184.5INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9897 | 20210917-16 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 33 | HR |  |  | 75 | 0 | 2475 | 321.75 | 2796.75 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building from Dead Horse Creek Road | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-21 |  | 37 | 2021-09-02 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting989720210917-16Operator - Principle - After Jan 10332475 | Corbiere and Sons Contracting989720210917-16Operator - Principle - After Jan 10332475INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9897 | 20210917-16 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 2 | HR |  |  | 75 | 0 | 150 | 19.5 | 169.5 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building from Dead Horse Creek Road | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-21 |  | 37 | 2021-09-02 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting989720210917-16Operator - Principle - After Jan 102150 | Corbiere and Sons Contracting989720210917-16Operator - Principle - After Jan 102150INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9897 | 20210917-16 | 53510602 | Access | 0 | Foreman | 95 | 5 | HR |  |  | 95 | 0 | 475 | 61.75 | 536.75 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building from Dead Horse Creek Road | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-21 |  | 37 | 2021-09-02 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting989720210917-16Foreman5475 | Corbiere and Sons Contracting989720210917-16Foreman5475INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9897 | 20210917-16 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 4 | DAY | 182.81 | 0 |  |  | 975 | 126.75 | 1101.75 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building from Dead Horse Creek Road | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-21 |  | 37 | 2021-09-02 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting989720210917-16Light Truck - Pick up- After Jan 104975 | Corbiere and Sons Contracting989720210917-16Light Truck - Pick up- After Jan 104975INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9897 | 20210917-16 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building from Dead Horse Creek Road | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-21 |  | 37 | 2021-09-02 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting989720210917-16Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting989720210917-16Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9897 | 20210917-16 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building from Dead Horse Creek Road | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-21 |  | 37 | 2021-09-02 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting989720210917-16Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting989720210917-16Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9897 | 20210917-16 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building from Dead Horse Creek Road | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-21 |  | 37 | 2021-09-02 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting989720210917-16Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting989720210917-16Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9897 | 20210917-16 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 3 | HR | 9.16 | 0 |  |  | 36.63 | 4.7619 | 41.3919 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building from Dead Horse Creek Road | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-21 |  | 37 | 2021-09-02 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting989720210917-16Excavator Thumb - 30 - 50 ton- After Jan 10336.63 | Corbiere and Sons Contracting989720210917-16Excavator Thumb - 30 - 50 ton- After Jan 10336.63INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9897 | 20210917-16 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building from Dead Horse Creek Road | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-21 |  | 37 | 2021-09-02 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting989720210917-16Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting989720210917-16Excavator - 36 ton- After Jan 10111616.56INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9897 | 20210917-16 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building from Dead Horse Creek Road | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-21 |  | 37 | 2021-09-02 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting989720210917-16Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting989720210917-16Excavator - 36 ton- After Jan 10111616.56INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9897 | 20210917-16 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building from Dead Horse Creek Road | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-21 |  | 37 | 2021-09-02 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting989720210917-16Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting989720210917-16Excavator - 36 ton- After Jan 1091322.64INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9897 | 20210917-16 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 3 | Dynamic | 103.84 | 0 |  |  | 415.35 | 53.9955 | 469.3455 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building from Dead Horse Creek Road | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-21 |  | 37 | 2021-09-02 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting989720210917-16Excavator - 30 ton- After Jan 103415.35 | Corbiere and Sons Contracting989720210917-16Excavator - 30 ton- After Jan 103415.35INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9881 | 20210917-14 | 53510602 | Access | 0 | Labourer - General - After Jan 10 | 60 | 12 | HR |  |  | 60 | 0 | 720 | 93.6 | 813.6 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Neys | 6 | C219-C235 | Neys | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting988120210917-14Labourer - General - After Jan 1012720 | Corbiere and Sons Contracting988120210917-14Labourer - General - After Jan 1012720INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9881 | 20210917-14 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 60 | HR |  |  | 75 | 0 | 4500 | 585 | 5085 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Neys | 6 | C219-C235 | Neys | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting988120210917-14Operator - Principle - After Jan 10604500 | Corbiere and Sons Contracting988120210917-14Operator - Principle - After Jan 10604500INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9881 | 20210917-14 | 53510602 | Access | 0 | L.O.A. | 210 | 8 | DAY |  |  |  | 0 | 1680 | 218.4 | 1898.4 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Neys | 6 | C219-C235 | Neys | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting988120210917-14L.O.A.81680 | Corbiere and Sons Contracting988120210917-14L.O.A.81680INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9881 | 20210917-14 | 53510602 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Neys | 6 | C219-C235 | Neys | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting988120210917-14Foreman121140 | Corbiere and Sons Contracting988120210917-14Foreman121140INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9881 | 20210917-14 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 22 | Dynamic | 103.54 | 0 |  |  | 3037.1 | 394.823 | 3431.923 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Neys | 6 | C219-C235 | Neys | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting988120210917-14Rock Truck - 30 Ton- After Jan 10223037.1 | Corbiere and Sons Contracting988120210917-14Rock Truck - 30 Ton- After Jan 10223037.1INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9881 | 20210917-14 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 4 | DAY | 182.81 | 0 |  |  | 975 | 126.75 | 1101.75 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Neys | 6 | C219-C235 | Neys | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting988120210917-14Light Truck - Pick up- After Jan 104975 | Corbiere and Sons Contracting988120210917-14Light Truck - Pick up- After Jan 104975INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9881 | 20210917-14 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 22 | HR | 9.16 | 0 |  |  | 268.62 | 34.9206 | 303.5406 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Neys | 6 | C219-C235 | Neys | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting988120210917-14Excavator Thumb - 30 - 50 ton- After Jan 1022268.62 | Corbiere and Sons Contracting988120210917-14Excavator Thumb - 30 - 50 ton- After Jan 1022268.62INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9881 | 20210917-14 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Neys | 6 | C219-C235 | Neys | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting988120210917-14Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting988120210917-14Excavator - 36 ton- After Jan 10111616.56INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9881 | 20210917-14 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Neys | 6 | C219-C235 | Neys | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting988120210917-14Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting988120210917-14Excavator - 30 ton- After Jan 10111522.95INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9881 | 20210917-14 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Neys | 6 | C219-C235 | Neys | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting988120210917-14Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting988120210917-14Dozer D6 or equal- After Jan 10111446.28INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9880 | 20210917-13 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 36 | HR |  |  | 75 | 0 | 2700 | 351 | 3051 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Little Red Sucker Access | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting988020210917-13Operator - Principle - After Jan 10362700 | Corbiere and Sons Contracting988020210917-13Operator - Principle - After Jan 10362700INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9880 | 20210917-13 | 53510602 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Little Red Sucker Access | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting988020210917-13L.O.A.3630 | Corbiere and Sons Contracting988020210917-13L.O.A.3630INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9880 | 20210917-13 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Little Red Sucker Access | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting988020210917-13Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting988020210917-13Rock Truck - 30 Ton- After Jan 10111518.55INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9880 | 20210917-13 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Little Red Sucker Access | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting988020210917-13Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting988020210917-13Light Truck - Pick up- After Jan 102487.5INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9880 | 20210917-13 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Little Red Sucker Access | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting988020210917-13Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting988020210917-13Excavator - 30 ton- After Jan 10111522.95INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9880 | 20210917-13 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building on Little Red Sucker Access | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting988020210917-13Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting988020210917-13Dozer D6 or equal- After Jan 10111446.28INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9879 | 20210917-12 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 24 | HR |  |  | 75 | 0 | 1800 | 234 | 2034 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from C217 | 6 | C217 | Highway 17 | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting987920210917-12Operator - Principle - After Jan 10241800 | Corbiere and Sons Contracting987920210917-12Operator - Principle - After Jan 10241800INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9879 | 20210917-12 | 53510602 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from C217 | 6 | C217 | Highway 17 | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting987920210917-12L.O.A.2420 | Corbiere and Sons Contracting987920210917-12L.O.A.2420INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9879 | 20210917-12 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from C217 | 6 | C217 | Highway 17 | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting987920210917-12Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting987920210917-12Rock Truck - 30 Ton- After Jan 10111518.55INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9879 | 20210917-12 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from C217 | 6 | C217 | Highway 17 | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting987920210917-12Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting987920210917-12Light Truck - Pick up- After Jan 101243.75INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9879 | 20210917-12 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from C217 | 6 | C217 | Highway 17 | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting987920210917-12Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting987920210917-12Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9879 | 20210917-12 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from C217 | 6 | C217 | Highway 17 | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting987920210917-12Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting987920210917-12Excavator - 30 ton- After Jan 10111522.95INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9877 | 20210917-10 | 53510602 | Access | 0 | Labourer - General - After Jan 10 | 60 | 12 | HR |  |  | 60 | 0 | 720 | 93.6 | 813.6 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from Middleton | 6 | C210-C213 | Middleton Road | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting987720210917-10Labourer - General - After Jan 1012720 | Corbiere and Sons Contracting987720210917-10Labourer - General - After Jan 1012720INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9877 | 20210917-10 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 24 | HR |  |  | 75 | 0 | 1800 | 234 | 2034 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from Middleton | 6 | C210-C213 | Middleton Road | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting987720210917-10Operator - Principle - After Jan 10241800 | Corbiere and Sons Contracting987720210917-10Operator - Principle - After Jan 10241800INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9877 | 20210917-10 | 53510602 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from Middleton | 6 | C210-C213 | Middleton Road | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting987720210917-10L.O.A.4840 | Corbiere and Sons Contracting987720210917-10L.O.A.4840INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9877 | 20210917-10 | 53510602 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from Middleton | 6 | C210-C213 | Middleton Road | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting987720210917-10Foreman121140 | Corbiere and Sons Contracting987720210917-10Foreman121140INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9877 | 20210917-10 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from Middleton | 6 | C210-C213 | Middleton Road | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting987720210917-10Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting987720210917-10Rock Truck - 30 Ton- After Jan 10111518.55INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9877 | 20210917-10 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from Middleton | 6 | C210-C213 | Middleton Road | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting987720210917-10Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting987720210917-10Light Truck - Pick up- After Jan 103731.25INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9877 | 20210917-10 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from Middleton | 6 | C210-C213 | Middleton Road | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting987720210917-10Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting987720210917-10Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9877 | 20210917-10 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from Middleton | 6 | C210-C213 | Middleton Road | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting987720210917-10Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting987720210917-10Excavator - 36 ton- After Jan 10111616.56INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9877 | 20210917-10 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work from Middleton | 6 | C210-C213 | Middleton Road | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting987720210917-10Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting987720210917-10Dozer D6 or equal- After Jan 10111446.28INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9959 | 20210916-20 | 53510602 | Access | 0 | ATV - Side by Side w/ roll bar- After Jan 10 | 18.45 | 10 | HR | 13.84 | 0 |  |  | 184.5 | 23.985 | 208.485 | 2021-09-16 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Billable time for ATV used in field | 6 | C257-C267 | Hare Lake | 0 | 2021-09-29 |  | 37 | 2021-09-30 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting995920210916-20ATV - Side by Side w/ roll bar- After Jan 1010184.5 | Corbiere and Sons Contracting995920210916-20ATV - Side by Side w/ roll bar- After Jan 1010184.5INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9894 | 20210916-16 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 36 | HR |  |  | 75 | 0 | 2700 | 351 | 3051 | 2021-09-16 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building road on Dead Horse Creek | 6 | C203-C209 | Dead Horse Creek Road | 0 | 2021-09-21 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting989420210916-16Operator - Principle - After Jan 10362700 | Corbiere and Sons Contracting989420210916-16Operator - Principle - After Jan 10362700INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9894 | 20210916-16 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5 | HR |  |  | 75 | 0 | 375 | 48.75 | 423.75 | 2021-09-16 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building road on Dead Horse Creek | 6 | C203-C209 | Dead Horse Creek Road | 0 | 2021-09-21 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting989420210916-16Operator - Principle - After Jan 105375 | Corbiere and Sons Contracting989420210916-16Operator - Principle - After Jan 105375INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9894 | 20210916-16 | 53510602 | Access | 0 | Foreman | 95 | 7 | HR |  |  | 95 | 0 | 665 | 86.45 | 751.45 | 2021-09-16 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building road on Dead Horse Creek | 6 | C203-C209 | Dead Horse Creek Road | 0 | 2021-09-21 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting989420210916-16Foreman7665 | Corbiere and Sons Contracting989420210916-16Foreman7665INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9894 | 20210916-16 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 5 | Dynamic | 103.54 | 0 |  |  | 690.25 | 89.7325 | 779.9825 | 2021-09-16 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building road on Dead Horse Creek | 6 | C203-C209 | Dead Horse Creek Road | 0 | 2021-09-21 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting989420210916-16Rock Truck - 30 Ton- After Jan 105690.25 | Corbiere and Sons Contracting989420210916-16Rock Truck - 30 Ton- After Jan 105690.25INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9894 | 20210916-16 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 4 | DAY | 182.81 | 0 |  |  | 975 | 126.75 | 1101.75 | 2021-09-16 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building road on Dead Horse Creek | 6 | C203-C209 | Dead Horse Creek Road | 0 | 2021-09-21 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting989420210916-16Light Truck - Pick up- After Jan 104975 | Corbiere and Sons Contracting989420210916-16Light Truck - Pick up- After Jan 104975INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9894 | 20210916-16 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-09-16 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building road on Dead Horse Creek | 6 | C203-C209 | Dead Horse Creek Road | 0 | 2021-09-21 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting989420210916-16Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting989420210916-16Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9894 | 20210916-16 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-16 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building road on Dead Horse Creek | 6 | C203-C209 | Dead Horse Creek Road | 0 | 2021-09-21 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting989420210916-16Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting989420210916-16Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9894 | 20210916-16 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-16 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building road on Dead Horse Creek | 6 | C203-C209 | Dead Horse Creek Road | 0 | 2021-09-21 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting989420210916-16Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting989420210916-16Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9894 | 20210916-16 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 1 | HR | 9.16 | 0 |  |  | 12.21 | 1.5873 | 13.7973 | 2021-09-16 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building road on Dead Horse Creek | 6 | C203-C209 | Dead Horse Creek Road | 0 | 2021-09-21 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting989420210916-16Excavator Thumb - 30 - 50 ton- After Jan 10112.21 | Corbiere and Sons Contracting989420210916-16Excavator Thumb - 30 - 50 ton- After Jan 10112.21INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9894 | 20210916-16 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-09-16 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building road on Dead Horse Creek | 6 | C203-C209 | Dead Horse Creek Road | 0 | 2021-09-21 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting989420210916-16Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting989420210916-16Excavator - 36 ton- After Jan 1091322.64INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9894 | 20210916-16 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-16 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building road on Dead Horse Creek | 6 | C203-C209 | Dead Horse Creek Road | 0 | 2021-09-21 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting989420210916-16Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting989420210916-16Excavator - 36 ton- After Jan 10111616.56INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9894 | 20210916-16 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-16 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building road on Dead Horse Creek | 6 | C203-C209 | Dead Horse Creek Road | 0 | 2021-09-21 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting989420210916-16Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting989420210916-16Excavator - 36 ton- After Jan 10111616.56INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9894 | 20210916-16 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 1 | Dynamic | 103.84 | 0 |  |  | 138.45 | 17.9985 | 156.4485 | 2021-09-16 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building road on Dead Horse Creek | 6 | C203-C209 | Dead Horse Creek Road | 0 | 2021-09-21 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting989420210916-16Excavator - 30 ton- After Jan 101138.45 | Corbiere and Sons Contracting989420210916-16Excavator - 30 ton- After Jan 101138.45INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9894 | 20210916-16 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 7 | Dynamic | 98.61 | 0 |  |  | 920.36 | 119.6468 | 1040.0068 | 2021-09-16 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building road on Dead Horse Creek | 6 | C203-C209 | Dead Horse Creek Road | 0 | 2021-09-21 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting989420210916-16Dozer D6 or equal- After Jan 107920.36 | Corbiere and Sons Contracting989420210916-16Dozer D6 or equal- After Jan 107920.36INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9890 | 20210915-11 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 35 | HR |  |  | 75 | 0 | 2625 | 341.25 | 2966.25 | 2021-09-15 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building road from entrance into access of Deadhorse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-21 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting989020210915-11Operator - Principle - After Jan 10352625 | Corbiere and Sons Contracting989020210915-11Operator - Principle - After Jan 10352625INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9890 | 20210915-11 | 53510602 | Access | 0 | Foreman | 95 | 6 | HR |  |  | 95 | 0 | 570 | 74.1 | 644.1 | 2021-09-15 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building road from entrance into access of Deadhorse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-21 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting989020210915-11Foreman6570 | Corbiere and Sons Contracting989020210915-11Foreman6570INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9890 | 20210915-11 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2021-09-15 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building road from entrance into access of Deadhorse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-21 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting989020210915-11Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting989020210915-11Light Truck - Pick up- After Jan 103731.25INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9890 | 20210915-11 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 8 | HR | 9.16 | 0 |  |  | 97.68 | 12.6984 | 110.3784 | 2021-09-15 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building road from entrance into access of Deadhorse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-21 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting989020210915-11Excavator Thumb - 30 - 50 ton- After Jan 10897.68 | Corbiere and Sons Contracting989020210915-11Excavator Thumb - 30 - 50 ton- After Jan 10897.68INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9890 | 20210915-11 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-15 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building road from entrance into access of Deadhorse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-21 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting989020210915-11Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting989020210915-11Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9890 | 20210915-11 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-15 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building road from entrance into access of Deadhorse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-21 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting989020210915-11Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting989020210915-11Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9890 | 20210915-11 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 2 | HR | 9.16 | 0 |  |  | 24.42 | 3.1746 | 27.5946 | 2021-09-15 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building road from entrance into access of Deadhorse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-21 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting989020210915-11Excavator Thumb - 30 - 50 ton- After Jan 10224.42 | Corbiere and Sons Contracting989020210915-11Excavator Thumb - 30 - 50 ton- After Jan 10224.42INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9890 | 20210915-11 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 8 | Dynamic | 110.22 | 0 |  |  | 1175.68 | 152.8384 | 1328.5184 | 2021-09-15 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building road from entrance into access of Deadhorse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-21 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting989020210915-11Excavator - 36 ton- After Jan 1081175.68 | Corbiere and Sons Contracting989020210915-11Excavator - 36 ton- After Jan 1081175.68INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9890 | 20210915-11 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-15 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building road from entrance into access of Deadhorse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-21 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting989020210915-11Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting989020210915-11Excavator - 36 ton- After Jan 10111616.56INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9890 | 20210915-11 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-15 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building road from entrance into access of Deadhorse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-21 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting989020210915-11Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting989020210915-11Excavator - 36 ton- After Jan 10111616.56INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9890 | 20210915-11 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 2 | Dynamic | 103.84 | 0 |  |  | 276.9 | 35.997 | 312.897 | 2021-09-15 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building road from entrance into access of Deadhorse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-21 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting989020210915-11Excavator - 30 ton- After Jan 102276.9 | Corbiere and Sons Contracting989020210915-11Excavator - 30 ton- After Jan 102276.9INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9890 | 20210915-11 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 6 | Dynamic | 98.61 | 0 |  |  | 788.88 | 102.5544 | 891.4344 | 2021-09-15 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building road from entrance into access of Deadhorse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-21 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting989020210915-11Dozer D6 or equal- After Jan 106788.88 | Corbiere and Sons Contracting989020210915-11Dozer D6 or equal- After Jan 106788.88INV #149 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 9940 | 20210920-9 | 53530601 | Rig/Access Mats | 0 | Driver - AZ - After Jan 10 | 70 | 6 | HR |  |  | 70 | 0 | 420 | 54.6 | 474.6 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float delivered 4x20' rig mats to Del Lake East | 6 | C191-C195 | Del Lake East | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting994020210920-9Driver - AZ - After Jan 106420 | Corbiere and Sons Contracting994020210920-9Driver - AZ - After Jan 106420INV #149 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Corbiere and Sons Contracting | 6 | 0 | 9940 | 20210920-9 | 53530601 | Rig/Access Mats | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float delivered 4x20' rig mats to Del Lake East | 6 | C191-C195 | Del Lake East | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting994020210920-9L.O.A.1210 | Corbiere and Sons Contracting994020210920-9L.O.A.1210INV #149 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Corbiere and Sons Contracting | 6 | 0 | 9940 | 20210920-9 | 53530601 | Rig/Access Mats | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 6 | Dynamic | 91.79 | 0 |  |  | 734.34 | 95.4642 | 829.8042 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float delivered 4x20' rig mats to Del Lake East | 6 | C191-C195 | Del Lake East | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting994020210920-9Tractor Trailer - 60 Ton- After Jan 106734.34 | Corbiere and Sons Contracting994020210920-9Tractor Trailer - 60 Ton- After Jan 106734.34INV #149 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Corbiere and Sons Contracting | 6 | 0 | 9917 | 20210918-16 | 53530601 | Rig/Access Mats | 0 | Driver - AZ - After Jan 10 | 70 | 4 | HR |  |  | 70 | 0 | 280 | 36.4 | 316.4 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Shawn and float delivered rig mats to Little Red Sucker Creek | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting991720210918-16Driver - AZ - After Jan 104280 | Corbiere and Sons Contracting991720210918-16Driver - AZ - After Jan 104280INV #149 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Corbiere and Sons Contracting | 6 | 0 | 9917 | 20210918-16 | 53530601 | Rig/Access Mats | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 4 | Dynamic | 91.79 | 0 |  |  | 489.56 | 63.6428 | 553.2028 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Shawn and float delivered rig mats to Little Red Sucker Creek | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting991720210918-16Tractor Trailer - 60 Ton- After Jan 104489.56 | Corbiere and Sons Contracting991720210918-16Tractor Trailer - 60 Ton- After Jan 104489.56INV #149 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Corbiere and Sons Contracting | 6 | 0 | 9912 | 20210918-11 | 53530601 | Rig/Access Mats | 0 | Driver - AZ - After Jan 10 | 70 | 7 | HR |  |  | 70 | 0 | 490 | 63.7 | 553.7 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float dropped off 2 loads of mats and Op unloaded with Ex | 6 | C210-C213 | Middleton | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting991220210918-11Driver - AZ - After Jan 107490 | Corbiere and Sons Contracting991220210918-11Driver - AZ - After Jan 107490INV #149 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Corbiere and Sons Contracting | 6 | 0 | 9912 | 20210918-11 | 53530601 | Rig/Access Mats | 0 | Operator - Principle - After Jan 10 | 75 | 4 | HR |  |  | 75 | 0 | 300 | 39 | 339 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float dropped off 2 loads of mats and Op unloaded with Ex | 6 | C210-C213 | Middleton | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting991220210918-11Operator - Principle - After Jan 104300 | Corbiere and Sons Contracting991220210918-11Operator - Principle - After Jan 104300INV #149 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Corbiere and Sons Contracting | 6 | 0 | 9912 | 20210918-11 | 53530601 | Rig/Access Mats | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float dropped off 2 loads of mats and Op unloaded with Ex | 6 | C210-C213 | Middleton | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting991220210918-11L.O.A.1210 | Corbiere and Sons Contracting991220210918-11L.O.A.1210INV #149 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Corbiere and Sons Contracting | 6 | 0 | 9873 | 20210917-6 | 53530601 | Rig/Access Mats | 0 | Operator - Principle - After Jan 10 | 75 | 4 | HR |  |  | 75 | 0 | 300 | 39 | 339 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Placing Rig Mats on Hare Lake Road | 6 | C257-C267 | Hare Lake | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting987320210917-6Operator - Principle - After Jan 104300 | Corbiere and Sons Contracting987320210917-6Operator - Principle - After Jan 104300INV #149 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Corbiere and Sons Contracting | 6 | 0 | 9873 | 20210917-6 | 53530601 | Rig/Access Mats | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 4 | HR | 9.16 | 0 |  |  | 48.84 | 6.3492 | 55.1892 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Placing Rig Mats on Hare Lake Road | 6 | C257-C267 | Hare Lake | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting987320210917-6Excavator Thumb - 30 - 50 ton- After Jan 10448.84 | Corbiere and Sons Contracting987320210917-6Excavator Thumb - 30 - 50 ton- After Jan 10448.84INV #149 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Corbiere and Sons Contracting | 6 | 0 | 9873 | 20210917-6 | 53530601 | Rig/Access Mats | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 4 | Dynamic | 103.84 | 0 |  |  | 553.8 | 71.994 | 625.794 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Placing Rig Mats on Hare Lake Road | 6 | C257-C267 | Hare Lake | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting987320210917-6Excavator - 30 ton- After Jan 104553.8 | Corbiere and Sons Contracting987320210917-6Excavator - 30 ton- After Jan 104553.8INV #149 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Corbiere and Sons Contracting | 6 | 0 | 10064 | 20210916-22 | 53530601 | Rig/Access Mats | 0 | Driver - AZ - After Jan 10 | 70 | 3 | HR |  |  | 70 | 0 | 210 | 27.3 | 237.3 | 2021-09-16 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Move 4x20' rig mats and 2 swamps mats from Marathon Laydown to Dead Horse Road | 6 | C203-C209 | Dead Horse Creek Road | 0 | 2021-10-05 |  | 36 | 2021-10-07 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1006420210916-22Driver - AZ - After Jan 103210 | Corbiere and Sons Contracting1006420210916-22Driver - AZ - After Jan 103210INV #149 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Corbiere and Sons Contracting | 6 | 0 | 10064 | 20210916-22 | 53530601 | Rig/Access Mats | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 3 | Dynamic | 91.79 | 0 |  |  | 367.17 | 47.7321 | 414.9021 | 2021-09-16 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Move 4x20' rig mats and 2 swamps mats from Marathon Laydown to Dead Horse Road | 6 | C203-C209 | Dead Horse Creek Road | 0 | 2021-10-05 |  | 36 | 2021-10-07 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1006420210916-22Tractor Trailer - 60 Ton- After Jan 103367.17 | Corbiere and Sons Contracting1006420210916-22Tractor Trailer - 60 Ton- After Jan 103367.17INV #149 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Corbiere and Sons Contracting | 6 | 0 | 10071 | 20210927-5 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 12 | HR |  |  | 70 | 0 | 840 | 109.2 | 949.2 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 4 Taranis and 1 Hurd Bros Truck hauling to Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-05 |  | 37 | 2021-10-06 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1007120210927-5Driver - AZ - After Jan 1012840 | Corbiere and Sons Contracting1007120210927-5Driver - AZ - After Jan 1012840INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10071 | 20210927-5 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 56 | HR |  |  | 70 | 0 | 3920 | 509.6 | 4429.6 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 4 Taranis and 1 Hurd Bros Truck hauling to Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-05 |  | 37 | 2021-10-06 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1007120210927-5Driver - AZ - After Jan 10563920 | Corbiere and Sons Contracting1007120210927-5Driver - AZ - After Jan 10563920INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10071 | 20210927-5 | 53510604 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 4 Taranis and 1 Hurd Bros Truck hauling to Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-05 |  | 37 | 2021-10-06 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1007120210927-5L.O.A.4840 | Corbiere and Sons Contracting1007120210927-5L.O.A.4840INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10071 | 20210927-5 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 12 | Dynamic | 41.4 | 0 |  |  | 662.4 | 86.112 | 748.512 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 4 Taranis and 1 Hurd Bros Truck hauling to Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-05 |  | 37 | 2021-10-06 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1007120210927-5Dump - Triaxle- After Jan 1012662.4 | Corbiere and Sons Contracting1007120210927-5Dump - Triaxle- After Jan 1012662.4INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10071 | 20210927-5 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 56 | Dynamic | 41.4 | 0 |  |  | 3091.2 | 401.856 | 3493.056 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 4 Taranis and 1 Hurd Bros Truck hauling to Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-05 |  | 37 | 2021-10-06 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1007120210927-5Dump - Triaxle- After Jan 10563091.2 | Corbiere and Sons Contracting1007120210927-5Dump - Triaxle- After Jan 10563091.2INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10070 | 20210927-4 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 34.5 | HR |  |  | 70 | 0 | 2415 | 313.95 | 2728.95 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 3 Trucks from Padda Roadlines hauling from Cress Pit to Pic River West | 6 | D004-D015 | Pic River | 0 | 2021-10-05 |  | 37 | 2021-10-06 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1007020210927-4Driver - AZ - After Jan 1034.52415 | Corbiere and Sons Contracting1007020210927-4Driver - AZ - After Jan 1034.52415INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10070 | 20210927-4 | 53510604 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 3 Trucks from Padda Roadlines hauling from Cress Pit to Pic River West | 6 | D004-D015 | Pic River | 0 | 2021-10-05 |  | 37 | 2021-10-06 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1007020210927-4L.O.A.3630 | Corbiere and Sons Contracting1007020210927-4L.O.A.3630INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10070 | 20210927-4 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 34.5 | Dynamic | 41.4 | 0 |  |  | 1904.4 | 247.572 | 2151.972 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 3 Trucks from Padda Roadlines hauling from Cress Pit to Pic River West | 6 | D004-D015 | Pic River | 0 | 2021-10-05 |  | 37 | 2021-10-06 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1007020210927-4Dump - Triaxle- After Jan 1034.51904.4 | Corbiere and Sons Contracting1007020210927-4Dump - Triaxle- After Jan 1034.51904.4INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10069 | 20210927-3 | 53510604 | Access | 0 | Labourer - General - After Jan 10 | 60 | 12 | HR |  |  | 60 | 0 | 720 | 93.6 | 813.6 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit (8 trucks) - 1 Valentino Truck | 6 | C257-C267 | Hare Lake Road | 0 | 2021-10-05 |  | 37 | 2021-10-06 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1006920210927-3Labourer - General - After Jan 1012720 | Corbiere and Sons Contracting1006920210927-3Labourer - General - After Jan 1012720INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10069 | 20210927-3 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 12 | HR |  |  | 70 | 0 | 840 | 109.2 | 949.2 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit (8 trucks) - 1 Valentino Truck | 6 | C257-C267 | Hare Lake Road | 0 | 2021-10-05 |  | 37 | 2021-10-06 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1006920210927-3Driver - AZ - After Jan 1012840 | Corbiere and Sons Contracting1006920210927-3Driver - AZ - After Jan 1012840INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10069 | 20210927-3 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 92 | HR |  |  | 70 | 0 | 6440 | 837.2 | 7277.2 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit (8 trucks) - 1 Valentino Truck | 6 | C257-C267 | Hare Lake Road | 0 | 2021-10-05 |  | 37 | 2021-10-06 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1006920210927-3Driver - AZ - After Jan 10926440 | Corbiere and Sons Contracting1006920210927-3Driver - AZ - After Jan 10926440INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10069 | 20210927-3 | 53510604 | Access | 0 | L.O.A. | 210 | 9 | DAY |  |  |  | 0 | 1890 | 245.7 | 2135.7 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit (8 trucks) - 1 Valentino Truck | 6 | C257-C267 | Hare Lake Road | 0 | 2021-10-05 |  | 37 | 2021-10-06 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1006920210927-3L.O.A.91890 | Corbiere and Sons Contracting1006920210927-3L.O.A.91890INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10069 | 20210927-3 | 53510604 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit (8 trucks) - 1 Valentino Truck | 6 | C257-C267 | Hare Lake Road | 0 | 2021-10-05 |  | 37 | 2021-10-06 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1006920210927-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1006920210927-3Light Truck - Pick up- After Jan 101243.75INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10069 | 20210927-3 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 12 | Dynamic | 41.4 | 0 |  |  | 662.4 | 86.112 | 748.512 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit (8 trucks) - 1 Valentino Truck | 6 | C257-C267 | Hare Lake Road | 0 | 2021-10-05 |  | 37 | 2021-10-06 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1006920210927-3Dump - Triaxle- After Jan 1012662.4 | Corbiere and Sons Contracting1006920210927-3Dump - Triaxle- After Jan 1012662.4INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10069 | 20210927-3 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 92 | Dynamic | 41.4 | 0 |  |  | 5078.4 | 660.192 | 5738.592 | 2021-09-27 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit (8 trucks) - 1 Valentino Truck | 6 | C257-C267 | Hare Lake Road | 0 | 2021-10-05 |  | 37 | 2021-10-06 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1006920210927-3Dump - Triaxle- After Jan 10925078.4 | Corbiere and Sons Contracting1006920210927-3Dump - Triaxle- After Jan 10925078.4INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10033 | 20210924-18 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 12 | HR |  |  | 70 | 0 | 840 | 109.2 | 949.2 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Missed gravel hauling ticket for Hurd Bros hauling to Neys Road | 6 | C219-C236 | Neys | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1003320210924-18Driver - AZ - After Jan 1012840 | Corbiere and Sons Contracting1003320210924-18Driver - AZ - After Jan 1012840INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10033 | 20210924-18 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 12 | Dynamic | 41.4 | 0 |  |  | 662.4 | 86.112 | 748.512 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Missed gravel hauling ticket for Hurd Bros hauling to Neys Road | 6 | C219-C236 | Neys | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1003320210924-18Dump - Triaxle- After Jan 1012662.4 | Corbiere and Sons Contracting1003320210924-18Dump - Triaxle- After Jan 1012662.4INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10065 | 20210924-17-R1 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 50 | HR |  |  | 70 | 0 | 3500 | 455 | 3955 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Additional gravel hauling tickets for Ripple Creek | 6 | C197-C202 | Ripple Lake | 0 | 2021-10-05 |  | 37 | 2021-10-04 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1006520210924-17-R1Driver - AZ - After Jan 10503500 | Corbiere and Sons Contracting1006520210924-17-R1Driver - AZ - After Jan 10503500INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10065 | 20210924-17-R1 | 53510604 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Additional gravel hauling tickets for Ripple Creek | 6 | C197-C202 | Ripple Lake | 0 | 2021-10-05 |  | 37 | 2021-10-04 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1006520210924-17-R1L.O.A.4840 | Corbiere and Sons Contracting1006520210924-17-R1L.O.A.4840INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10065 | 20210924-17-R1 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 50 | Dynamic | 41.4 | 0 |  |  | 2760 | 358.8 | 3118.8 | 2021-09-24 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Additional gravel hauling tickets for Ripple Creek | 6 | C197-C202 | Ripple Lake | 0 | 2021-10-05 |  | 37 | 2021-10-04 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1006520210924-17-R1Dump - Triaxle- After Jan 10502760 | Corbiere and Sons Contracting1006520210924-17-R1Dump - Triaxle- After Jan 10502760INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10007 | 20210923-6 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 12 | HR |  |  | 70 | 0 | 840 | 109.2 | 949.2 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling Activities on Del Lake Road - 3 Taranis, 1 Valentino and 1 Hurd Bros | 6 | C186-C195 | Del Lake | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1000720210923-6Driver - AZ - After Jan 1012840 | Corbiere and Sons Contracting1000720210923-6Driver - AZ - After Jan 1012840INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10007 | 20210923-6 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 12 | HR |  |  | 70 | 0 | 840 | 109.2 | 949.2 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling Activities on Del Lake Road - 3 Taranis, 1 Valentino and 1 Hurd Bros | 6 | C186-C195 | Del Lake | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1000720210923-6Driver - AZ - After Jan 1012840 | Corbiere and Sons Contracting1000720210923-6Driver - AZ - After Jan 1012840INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10007 | 20210923-6 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 27.5 | HR |  |  | 70 | 0 | 1925 | 250.25 | 2175.25 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling Activities on Del Lake Road - 3 Taranis, 1 Valentino and 1 Hurd Bros | 6 | C186-C195 | Del Lake | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1000720210923-6Driver - AZ - After Jan 1027.51925 | Corbiere and Sons Contracting1000720210923-6Driver - AZ - After Jan 1027.51925INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10007 | 20210923-6 | 53510604 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling Activities on Del Lake Road - 3 Taranis, 1 Valentino and 1 Hurd Bros | 6 | C186-C195 | Del Lake | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1000720210923-6L.O.A.3630 | Corbiere and Sons Contracting1000720210923-6L.O.A.3630INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10007 | 20210923-6 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 24 | Dynamic | 41.4 | 0 |  |  | 1324.8 | 172.224 | 1497.024 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling Activities on Del Lake Road - 3 Taranis, 1 Valentino and 1 Hurd Bros | 6 | C186-C195 | Del Lake | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1000720210923-6Dump - Triaxle- After Jan 10241324.8 | Corbiere and Sons Contracting1000720210923-6Dump - Triaxle- After Jan 10241324.8INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10007 | 20210923-6 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 27.5 | Dynamic | 41.4 | 0 |  |  | 1518 | 197.34 | 1715.34 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling Activities on Del Lake Road - 3 Taranis, 1 Valentino and 1 Hurd Bros | 6 | C186-C195 | Del Lake | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1000720210923-6Dump - Triaxle- After Jan 1027.51518 | Corbiere and Sons Contracting1000720210923-6Dump - Triaxle- After Jan 1027.51518INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10006 | 20210923-5 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 11.5 | HR |  |  | 70 | 0 | 805 | 104.65 | 909.65 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 4 Trucks from Padda and 1 from Taranis hauling to Neys Road | 6 | C219-C236 | Neys | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1000620210923-5Driver - AZ - After Jan 1011.5805 | Corbiere and Sons Contracting1000620210923-5Driver - AZ - After Jan 1011.5805INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10006 | 20210923-5 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 46 | HR |  |  | 70 | 0 | 3220 | 418.6 | 3638.6 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 4 Trucks from Padda and 1 from Taranis hauling to Neys Road | 6 | C219-C236 | Neys | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1000620210923-5Driver - AZ - After Jan 10463220 | Corbiere and Sons Contracting1000620210923-5Driver - AZ - After Jan 10463220INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10006 | 20210923-5 | 53510604 | Access | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 4 Trucks from Padda and 1 from Taranis hauling to Neys Road | 6 | C219-C236 | Neys | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1000620210923-5L.O.A.51050 | Corbiere and Sons Contracting1000620210923-5L.O.A.51050INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10006 | 20210923-5 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 11.5 | Dynamic | 41.4 | 0 |  |  | 634.8 | 82.524 | 717.324 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 4 Trucks from Padda and 1 from Taranis hauling to Neys Road | 6 | C219-C236 | Neys | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1000620210923-5Dump - Triaxle- After Jan 1011.5634.8 | Corbiere and Sons Contracting1000620210923-5Dump - Triaxle- After Jan 1011.5634.8INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10006 | 20210923-5 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 46 | Dynamic | 41.4 | 0 |  |  | 2539.2 | 330.096 | 2869.296 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 4 Trucks from Padda and 1 from Taranis hauling to Neys Road | 6 | C219-C236 | Neys | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1000620210923-5Dump - Triaxle- After Jan 10462539.2 | Corbiere and Sons Contracting1000620210923-5Dump - Triaxle- After Jan 10462539.2INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10004 | 20210923-3 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 60.5 | HR |  |  | 70 | 0 | 4235 | 550.55 | 4785.55 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit (5 trucks) | 6 | C257-C267 | Hare Lake | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1000420210923-3Driver - AZ - After Jan 1060.54235 | Corbiere and Sons Contracting1000420210923-3Driver - AZ - After Jan 1060.54235INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10004 | 20210923-3 | 53510604 | Access | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit (5 trucks) | 6 | C257-C267 | Hare Lake | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1000420210923-3L.O.A.61260 | Corbiere and Sons Contracting1000420210923-3L.O.A.61260INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10004 | 20210923-3 | 53510604 | Access | 0 | Construction Coordinator | 80 | 7 | HR |  |  | 80 | 0 | 560 | 72.8 | 632.8 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit (5 trucks) | 6 | C257-C267 | Hare Lake | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1000420210923-3Construction Coordinator7560 | Corbiere and Sons Contracting1000420210923-3Construction Coordinator7560INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10004 | 20210923-3 | 53510604 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit (5 trucks) | 6 | C257-C267 | Hare Lake | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1000420210923-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1000420210923-3Light Truck - Pick up- After Jan 101243.75INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10004 | 20210923-3 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 60.5 | Dynamic | 41.4 | 0 |  |  | 3339.6 | 434.148 | 3773.748 | 2021-09-23 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit (5 trucks) | 6 | C257-C267 | Hare Lake | 0 | 2021-09-30 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1000420210923-3Dump - Triaxle- After Jan 1060.53339.6 | Corbiere and Sons Contracting1000420210923-3Dump - Triaxle- After Jan 1060.53339.6INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9992 | 20210922-4 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 48 | HR |  |  | 70 | 0 | 3360 | 436.8 | 3796.8 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 4 Taranis, 1 Hurd and 1 Valentino Truck hauling to Neys | 6 | C219-C236 | Neys | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting999220210922-4Driver - AZ - After Jan 10483360 | Corbiere and Sons Contracting999220210922-4Driver - AZ - After Jan 10483360INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9992 | 20210922-4 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 13 | HR |  |  | 70 | 0 | 910 | 118.3 | 1028.3 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 4 Taranis, 1 Hurd and 1 Valentino Truck hauling to Neys | 6 | C219-C236 | Neys | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting999220210922-4Driver - AZ - After Jan 1013910 | Corbiere and Sons Contracting999220210922-4Driver - AZ - After Jan 1013910INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9992 | 20210922-4 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 12 | HR |  |  | 70 | 0 | 840 | 109.2 | 949.2 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 4 Taranis, 1 Hurd and 1 Valentino Truck hauling to Neys | 6 | C219-C236 | Neys | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting999220210922-4Driver - AZ - After Jan 1012840 | Corbiere and Sons Contracting999220210922-4Driver - AZ - After Jan 1012840INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9992 | 20210922-4 | 53510604 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 4 Taranis, 1 Hurd and 1 Valentino Truck hauling to Neys | 6 | C219-C236 | Neys | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting999220210922-4L.O.A.4840 | Corbiere and Sons Contracting999220210922-4L.O.A.4840INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9992 | 20210922-4 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 48 | Dynamic | 41.4 | 0 |  |  | 2649.6 | 344.448 | 2994.048 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 4 Taranis, 1 Hurd and 1 Valentino Truck hauling to Neys | 6 | C219-C236 | Neys | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting999220210922-4Dump - Triaxle- After Jan 10482649.6 | Corbiere and Sons Contracting999220210922-4Dump - Triaxle- After Jan 10482649.6INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9992 | 20210922-4 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 13 | Dynamic | 41.4 | 0 |  |  | 717.6 | 93.288 | 810.888 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 4 Taranis, 1 Hurd and 1 Valentino Truck hauling to Neys | 6 | C219-C236 | Neys | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting999220210922-4Dump - Triaxle- After Jan 1013717.6 | Corbiere and Sons Contracting999220210922-4Dump - Triaxle- After Jan 1013717.6INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9992 | 20210922-4 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 12 | Dynamic | 41.4 | 0 |  |  | 662.4 | 86.112 | 748.512 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 4 Taranis, 1 Hurd and 1 Valentino Truck hauling to Neys | 6 | C219-C236 | Neys | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting999220210922-4Dump - Triaxle- After Jan 1012662.4 | Corbiere and Sons Contracting999220210922-4Dump - Triaxle- After Jan 1012662.4INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9991 | 20210922-3 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 139 | HR |  |  | 70 | 0 | 9730 | 1264.9 | 10994.9 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit (10 trucks) - 2 Trucks mobilized | 6 | C257-C267 | Hare Lake | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting999120210922-3Driver - AZ - After Jan 101399730 | Corbiere and Sons Contracting999120210922-3Driver - AZ - After Jan 101399730INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9991 | 20210922-3 | 53510604 | Access | 0 | L.O.A. | 210 | 13 | DAY |  |  |  | 0 | 2730 | 354.9 | 3084.9 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit (10 trucks) - 2 Trucks mobilized | 6 | C257-C267 | Hare Lake | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting999120210922-3L.O.A.132730 | Corbiere and Sons Contracting999120210922-3L.O.A.132730INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9991 | 20210922-3 | 53510604 | Access | 0 | Construction Coordinator | 80 | 7 | HR |  |  | 80 | 0 | 560 | 72.8 | 632.8 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit (10 trucks) - 2 Trucks mobilized | 6 | C257-C267 | Hare Lake | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting999120210922-3Construction Coordinator7560 | Corbiere and Sons Contracting999120210922-3Construction Coordinator7560INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9991 | 20210922-3 | 53510604 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit (10 trucks) - 2 Trucks mobilized | 6 | C257-C267 | Hare Lake | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting999120210922-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting999120210922-3Light Truck - Pick up- After Jan 101243.75INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9991 | 20210922-3 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 139 | Dynamic | 41.4 | 0 |  |  | 7672.8 | 997.464 | 8670.264 | 2021-09-22 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit (10 trucks) - 2 Trucks mobilized | 6 | C257-C267 | Hare Lake | 0 | 2021-09-30 |  | 58 | 2021-10-02 | [6 empty] | 06 | Corbiere and Sons Contracting999120210922-3Dump - Triaxle- After Jan 101397672.8 | Corbiere and Sons Contracting999120210922-3Dump - Triaxle- After Jan 101397672.8INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9972 | 20210921-5 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 46 | HR |  |  | 70 | 0 | 3220 | 418.6 | 3638.6 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 4 trucks from Padda Roadlines hauling to Neys road | 6 | C219-C236 | Neys | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997220210921-5Driver - AZ - After Jan 10463220 | Corbiere and Sons Contracting997220210921-5Driver - AZ - After Jan 10463220INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9972 | 20210921-5 | 53510604 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 4 trucks from Padda Roadlines hauling to Neys road | 6 | C219-C236 | Neys | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997220210921-5L.O.A.4840 | Corbiere and Sons Contracting997220210921-5L.O.A.4840INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9972 | 20210921-5 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 46 | Dynamic | 41.4 | 0 |  |  | 2539.2 | 330.096 | 2869.296 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 4 trucks from Padda Roadlines hauling to Neys road | 6 | C219-C236 | Neys | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997220210921-5Dump - Triaxle- After Jan 10462539.2 | Corbiere and Sons Contracting997220210921-5Dump - Triaxle- After Jan 10462539.2INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9971 | 20210921-4 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 46 | HR |  |  | 70 | 0 | 3220 | 418.6 | 3638.6 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 1 Hurd, 4 Taranis and 1 Valentino Truck hauling to Ripple | 6 | C197-C202 | Ripple Creek Road | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997120210921-4Driver - AZ - After Jan 10463220 | Corbiere and Sons Contracting997120210921-4Driver - AZ - After Jan 10463220INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9971 | 20210921-4 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 12 | HR |  |  | 70 | 0 | 840 | 109.2 | 949.2 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 1 Hurd, 4 Taranis and 1 Valentino Truck hauling to Ripple | 6 | C197-C202 | Ripple Creek Road | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997120210921-4Driver - AZ - After Jan 1012840 | Corbiere and Sons Contracting997120210921-4Driver - AZ - After Jan 1012840INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9971 | 20210921-4 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 12 | HR |  |  | 70 | 0 | 840 | 109.2 | 949.2 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 1 Hurd, 4 Taranis and 1 Valentino Truck hauling to Ripple | 6 | C197-C202 | Ripple Creek Road | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997120210921-4Driver - AZ - After Jan 1012840 | Corbiere and Sons Contracting997120210921-4Driver - AZ - After Jan 1012840INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9971 | 20210921-4 | 53510604 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 1 Hurd, 4 Taranis and 1 Valentino Truck hauling to Ripple | 6 | C197-C202 | Ripple Creek Road | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997120210921-4L.O.A.4840 | Corbiere and Sons Contracting997120210921-4L.O.A.4840INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9971 | 20210921-4 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 46 | Dynamic | 41.4 | 0 |  |  | 2539.2 | 330.096 | 2869.296 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 1 Hurd, 4 Taranis and 1 Valentino Truck hauling to Ripple | 6 | C197-C202 | Ripple Creek Road | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997120210921-4Dump - Triaxle- After Jan 10462539.2 | Corbiere and Sons Contracting997120210921-4Dump - Triaxle- After Jan 10462539.2INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9971 | 20210921-4 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 24 | Dynamic | 41.4 | 0 |  |  | 1324.8 | 172.224 | 1497.024 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 1 Hurd, 4 Taranis and 1 Valentino Truck hauling to Ripple | 6 | C197-C202 | Ripple Creek Road | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997120210921-4Dump - Triaxle- After Jan 10241324.8 | Corbiere and Sons Contracting997120210921-4Dump - Triaxle- After Jan 10241324.8INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9970 | 20210921-3 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 69 | HR |  |  | 70 | 0 | 4830 | 627.9 | 5457.9 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit ( 6 trucks) | 6 | C257-C267 | Hare Lake | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997020210921-3Driver - AZ - After Jan 10694830 | Corbiere and Sons Contracting997020210921-3Driver - AZ - After Jan 10694830INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9970 | 20210921-3 | 53510604 | Access | 0 | L.O.A. | 210 | 7 | DAY |  |  |  | 0 | 1470 | 191.1 | 1661.1 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit ( 6 trucks) | 6 | C257-C267 | Hare Lake | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997020210921-3L.O.A.71470 | Corbiere and Sons Contracting997020210921-3L.O.A.71470INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9970 | 20210921-3 | 53510604 | Access | 0 | Construction Coordinator | 80 | 7 | HR |  |  | 80 | 0 | 560 | 72.8 | 632.8 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit ( 6 trucks) | 6 | C257-C267 | Hare Lake | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997020210921-3Construction Coordinator7560 | Corbiere and Sons Contracting997020210921-3Construction Coordinator7560INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9970 | 20210921-3 | 53510604 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit ( 6 trucks) | 6 | C257-C267 | Hare Lake | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997020210921-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting997020210921-3Light Truck - Pick up- After Jan 101243.75INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9970 | 20210921-3 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 69 | Dynamic | 41.4 | 0 |  |  | 3808.8 | 495.144 | 4303.944 | 2021-09-21 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit ( 6 trucks) | 6 | C257-C267 | Hare Lake | 0 | 2021-09-29 |  | 58 | 2021-09-30 | [6 empty] | 06 | Corbiere and Sons Contracting997020210921-3Dump - Triaxle- After Jan 10693808.8 | Corbiere and Sons Contracting997020210921-3Dump - Triaxle- After Jan 10693808.8INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9936 | 20210920-5 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 57.5 | HR |  |  | 70 | 0 | 4025 | 523.25 | 4548.25 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 5 trucks from Padda Roadlines hauling to Neys road | 6 | C219-C236 | Neys | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting993620210920-5Driver - AZ - After Jan 1057.54025 | Corbiere and Sons Contracting993620210920-5Driver - AZ - After Jan 1057.54025INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9936 | 20210920-5 | 53510604 | Access | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 5 trucks from Padda Roadlines hauling to Neys road | 6 | C219-C236 | Neys | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting993620210920-5L.O.A.51050 | Corbiere and Sons Contracting993620210920-5L.O.A.51050INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9936 | 20210920-5 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 57.5 | Dynamic | 41.4 | 0 |  |  | 3174 | 412.62 | 3586.62 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 5 trucks from Padda Roadlines hauling to Neys road | 6 | C219-C236 | Neys | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting993620210920-5Dump - Triaxle- After Jan 1057.53174 | Corbiere and Sons Contracting993620210920-5Dump - Triaxle- After Jan 1057.53174INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9934 | 20210920-3 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 46 | HR |  |  | 70 | 0 | 3220 | 418.6 | 3638.6 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit ( 4 trucks) | 6 | C257-C267 | Hare Lake Road | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting993420210920-3Driver - AZ - After Jan 10463220 | Corbiere and Sons Contracting993420210920-3Driver - AZ - After Jan 10463220INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9934 | 20210920-3 | 53510604 | Access | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit ( 4 trucks) | 6 | C257-C267 | Hare Lake Road | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting993420210920-3L.O.A.51050 | Corbiere and Sons Contracting993420210920-3L.O.A.51050INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9934 | 20210920-3 | 53510604 | Access | 0 | Construction Coordinator | 80 | 7 | HR |  |  | 80 | 0 | 560 | 72.8 | 632.8 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit ( 4 trucks) | 6 | C257-C267 | Hare Lake Road | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting993420210920-3Construction Coordinator7560 | Corbiere and Sons Contracting993420210920-3Construction Coordinator7560INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9934 | 20210920-3 | 53510604 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit ( 4 trucks) | 6 | C257-C267 | Hare Lake Road | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting993420210920-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting993420210920-3Light Truck - Pick up- After Jan 101243.75INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9934 | 20210920-3 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 46 | Dynamic | 41.4 | 0 |  |  | 2539.2 | 330.096 | 2869.296 | 2021-09-20 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit ( 4 trucks) | 6 | C257-C267 | Hare Lake Road | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting993420210920-3Dump - Triaxle- After Jan 10462539.2 | Corbiere and Sons Contracting993420210920-3Dump - Triaxle- After Jan 10462539.2INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9923 | 20210919-4 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 49.5 | HR |  |  | 70 | 0 | 3465 | 450.45 | 3915.45 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 5Padda Tri-axles hauling from Cress pit to Ripple | 6 | C197-C202 | Ripple Creek Road | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting992320210919-4Driver - AZ - After Jan 1049.53465 | Corbiere and Sons Contracting992320210919-4Driver - AZ - After Jan 1049.53465INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9923 | 20210919-4 | 53510604 | Access | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 5Padda Tri-axles hauling from Cress pit to Ripple | 6 | C197-C202 | Ripple Creek Road | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting992320210919-4L.O.A.51050 | Corbiere and Sons Contracting992320210919-4L.O.A.51050INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9923 | 20210919-4 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 49.5 | Dynamic | 41.4 | 0 |  |  | 2732.4 | 355.212 | 3087.612 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 5Padda Tri-axles hauling from Cress pit to Ripple | 6 | C197-C202 | Ripple Creek Road | 0 | 2021-09-23 |  | 37 | 2021-09-24 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting992320210919-4Dump - Triaxle- After Jan 1049.52732.4 | Corbiere and Sons Contracting992320210919-4Dump - Triaxle- After Jan 1049.52732.4INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9922 | 20210919-3 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 85 | HR |  |  | 70 | 0 | 5950 | 773.5 | 6723.5 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit - 2 Trucks mobilized | 6 | C257-C267 | Hare Lake Road | 0 | 2021-09-23 |  | 37 | 2021-09-25 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting992220210919-3Driver - AZ - After Jan 10855950 | Corbiere and Sons Contracting992220210919-3Driver - AZ - After Jan 10855950INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9922 | 20210919-3 | 53510604 | Access | 0 | L.O.A. | 210 | 9 | DAY |  |  |  | 0 | 1890 | 245.7 | 2135.7 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit - 2 Trucks mobilized | 6 | C257-C267 | Hare Lake Road | 0 | 2021-09-23 |  | 37 | 2021-09-25 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting992220210919-3L.O.A.91890 | Corbiere and Sons Contracting992220210919-3L.O.A.91890INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9922 | 20210919-3 | 53510604 | Access | 0 | Construction Coordinator | 80 | 7 | HR |  |  | 80 | 0 | 560 | 72.8 | 632.8 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit - 2 Trucks mobilized | 6 | C257-C267 | Hare Lake Road | 0 | 2021-09-23 |  | 37 | 2021-09-25 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting992220210919-3Construction Coordinator7560 | Corbiere and Sons Contracting992220210919-3Construction Coordinator7560INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9922 | 20210919-3 | 53510604 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit - 2 Trucks mobilized | 6 | C257-C267 | Hare Lake Road | 0 | 2021-09-23 |  | 37 | 2021-09-25 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting992220210919-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting992220210919-3Light Truck - Pick up- After Jan 101243.75INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9922 | 20210919-3 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 85 | Dynamic | 41.4 | 0 |  |  | 4692 | 609.96 | 5301.96 | 2021-09-19 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit - 2 Trucks mobilized | 6 | C257-C267 | Hare Lake Road | 0 | 2021-09-23 |  | 37 | 2021-09-25 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting992220210919-3Dump - Triaxle- After Jan 10854692 | Corbiere and Sons Contracting992220210919-3Dump - Triaxle- After Jan 10854692INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9906 | 20210918-5 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 46 | HR |  |  | 70 | 0 | 3220 | 418.6 | 3638.6 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 4 Padda Tri-axles hauling from Cress pit to Neys Road | 6 | C219-C236 | Neys Road | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting990620210918-5Driver - AZ - After Jan 10463220 | Corbiere and Sons Contracting990620210918-5Driver - AZ - After Jan 10463220INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9906 | 20210918-5 | 53510604 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 4 Padda Tri-axles hauling from Cress pit to Neys Road | 6 | C219-C236 | Neys Road | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting990620210918-5L.O.A.4840 | Corbiere and Sons Contracting990620210918-5L.O.A.4840INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9906 | 20210918-5 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 46 | Dynamic | 41.4 | 0 |  |  | 2539.2 | 330.096 | 2869.296 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 4 Padda Tri-axles hauling from Cress pit to Neys Road | 6 | C219-C236 | Neys Road | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting990620210918-5Dump - Triaxle- After Jan 10462539.2 | Corbiere and Sons Contracting990620210918-5Dump - Triaxle- After Jan 10462539.2INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9905 | 20210918-4 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 34.5 | HR |  |  | 70 | 0 | 2415 | 313.95 | 2728.95 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling from Jackfish Pit to Del Lake Road | 6 | C186-C195 | Del Lake Road | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting990520210918-4Driver - AZ - After Jan 1034.52415 | Corbiere and Sons Contracting990520210918-4Driver - AZ - After Jan 1034.52415INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9905 | 20210918-4 | 53510604 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling from Jackfish Pit to Del Lake Road | 6 | C186-C195 | Del Lake Road | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting990520210918-4L.O.A.3630 | Corbiere and Sons Contracting990520210918-4L.O.A.3630INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9905 | 20210918-4 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 34.5 | Dynamic | 41.4 | 0 |  |  | 1904.4 | 247.572 | 2151.972 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling from Jackfish Pit to Del Lake Road | 6 | C186-C195 | Del Lake Road | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting990520210918-4Dump - Triaxle- After Jan 1034.51904.4 | Corbiere and Sons Contracting990520210918-4Dump - Triaxle- After Jan 1034.51904.4INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9904 | 20210918-3 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 57.5 | HR |  |  | 70 | 0 | 4025 | 523.25 | 4548.25 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit | 6 | C257-C267 | Hare Lake Road | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting990420210918-3Driver - AZ - After Jan 1057.54025 | Corbiere and Sons Contracting990420210918-3Driver - AZ - After Jan 1057.54025INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9904 | 20210918-3 | 53510604 | Access | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit | 6 | C257-C267 | Hare Lake Road | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting990420210918-3L.O.A.61260 | Corbiere and Sons Contracting990420210918-3L.O.A.61260INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9904 | 20210918-3 | 53510604 | Access | 0 | Construction Coordinator | 80 | 7 | HR |  |  | 80 | 0 | 560 | 72.8 | 632.8 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit | 6 | C257-C267 | Hare Lake Road | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting990420210918-3Construction Coordinator7560 | Corbiere and Sons Contracting990420210918-3Construction Coordinator7560INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9904 | 20210918-3 | 53510604 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit | 6 | C257-C267 | Hare Lake Road | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting990420210918-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting990420210918-3Light Truck - Pick up- After Jan 101243.75INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9904 | 20210918-3 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 57.5 | Dynamic | 41.4 | 0 |  |  | 3174 | 412.62 | 3586.62 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit | 6 | C257-C267 | Hare Lake Road | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting990420210918-3Dump - Triaxle- After Jan 1057.53174 | Corbiere and Sons Contracting990420210918-3Dump - Triaxle- After Jan 1057.53174INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9921 | 20210918-20 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 12 | HR |  |  | 70 | 0 | 840 | 109.2 | 949.2 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel hauling from Jackfish pit to Del Lake East | 6 | C186-C195 | Del Lake East | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting992120210918-20Driver - AZ - After Jan 1012840 | Corbiere and Sons Contracting992120210918-20Driver - AZ - After Jan 1012840INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9921 | 20210918-20 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 12.5 | HR |  |  | 70 | 0 | 875 | 113.75 | 988.75 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel hauling from Jackfish pit to Del Lake East | 6 | C186-C195 | Del Lake East | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting992120210918-20Driver - AZ - After Jan 1012.5875 | Corbiere and Sons Contracting992120210918-20Driver - AZ - After Jan 1012.5875INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9921 | 20210918-20 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 12 | Dynamic | 41.4 | 0 |  |  | 662.4 | 86.112 | 748.512 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel hauling from Jackfish pit to Del Lake East | 6 | C186-C195 | Del Lake East | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting992120210918-20Dump - Triaxle- After Jan 1012662.4 | Corbiere and Sons Contracting992120210918-20Dump - Triaxle- After Jan 1012662.4INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9921 | 20210918-20 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 12.5 | Dynamic | 41.4 | 0 |  |  | 690 | 89.7 | 779.7 | 2021-09-18 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel hauling from Jackfish pit to Del Lake East | 6 | C186-C195 | Del Lake East | 0 | 2021-09-23 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting992120210918-20Dump - Triaxle- After Jan 1012.5690 | Corbiere and Sons Contracting992120210918-20Dump - Triaxle- After Jan 1012.5690INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9871 | 20210917-4 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 12 | HR |  |  | 70 | 0 | 840 | 109.2 | 949.2 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling from Jackfish Pit to Del Lake Road Valentino and Tarranis | 6 | C186-C195 | Del Lake Road | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting987120210917-4Driver - AZ - After Jan 1012840 | Corbiere and Sons Contracting987120210917-4Driver - AZ - After Jan 1012840INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9871 | 20210917-4 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 52 | HR |  |  | 70 | 0 | 3640 | 473.2 | 4113.2 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling from Jackfish Pit to Del Lake Road Valentino and Tarranis | 6 | C186-C195 | Del Lake Road | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting987120210917-4Driver - AZ - After Jan 10523640 | Corbiere and Sons Contracting987120210917-4Driver - AZ - After Jan 10523640INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9871 | 20210917-4 | 53510604 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling from Jackfish Pit to Del Lake Road Valentino and Tarranis | 6 | C186-C195 | Del Lake Road | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting987120210917-4L.O.A.4840 | Corbiere and Sons Contracting987120210917-4L.O.A.4840INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9871 | 20210917-4 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 12 | Dynamic | 41.4 | 0 |  |  | 662.4 | 86.112 | 748.512 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling from Jackfish Pit to Del Lake Road Valentino and Tarranis | 6 | C186-C195 | Del Lake Road | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting987120210917-4Dump - Triaxle- After Jan 1012662.4 | Corbiere and Sons Contracting987120210917-4Dump - Triaxle- After Jan 1012662.4INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9871 | 20210917-4 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 52 | Dynamic | 41.4 | 0 |  |  | 2870.4 | 373.152 | 3243.552 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling from Jackfish Pit to Del Lake Road Valentino and Tarranis | 6 | C186-C195 | Del Lake Road | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting987120210917-4Dump - Triaxle- After Jan 10522870.4 | Corbiere and Sons Contracting987120210917-4Dump - Triaxle- After Jan 10522870.4INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9870 | 20210917-3 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 157.5 | HR |  |  | 70 | 0 | 11025 | 1433.25 | 12458.25 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit. Padda trucks mobe to Marathon and from Cress Pit to Heron and Neys Roads | 6 | C257-C267 | Hare Lake Road | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting987020210917-3Driver - AZ - After Jan 10157.511025 | Corbiere and Sons Contracting987020210917-3Driver - AZ - After Jan 10157.511025INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9870 | 20210917-3 | 53510604 | Access | 0 | L.O.A. | 210 | 15 | DAY |  |  |  | 0 | 3150 | 409.5 | 3559.5 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit. Padda trucks mobe to Marathon and from Cress Pit to Heron and Neys Roads | 6 | C257-C267 | Hare Lake Road | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting987020210917-3L.O.A.153150 | Corbiere and Sons Contracting987020210917-3L.O.A.153150INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9870 | 20210917-3 | 53510604 | Access | 0 | Construction Coordinator | 80 | 7 | HR |  |  | 80 | 0 | 560 | 72.8 | 632.8 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit. Padda trucks mobe to Marathon and from Cress Pit to Heron and Neys Roads | 6 | C257-C267 | Hare Lake Road | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting987020210917-3Construction Coordinator7560 | Corbiere and Sons Contracting987020210917-3Construction Coordinator7560INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9870 | 20210917-3 | 53510604 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit. Padda trucks mobe to Marathon and from Cress Pit to Heron and Neys Roads | 6 | C257-C267 | Hare Lake Road | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting987020210917-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting987020210917-3Light Truck - Pick up- After Jan 101243.75INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9870 | 20210917-3 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 157.5 | Dynamic | 41.4 | 0 |  |  | 8694 | 1130.22 | 9824.22 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit. Padda trucks mobe to Marathon and from Cress Pit to Heron and Neys Roads | 6 | C257-C267 | Hare Lake Road | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting987020210917-3Dump - Triaxle- After Jan 10157.58694 | Corbiere and Sons Contracting987020210917-3Dump - Triaxle- After Jan 10157.58694INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9901 | 20210917-20 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 12 | HR |  |  | 70 | 0 | 840 | 109.2 | 949.2 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel hauling from Jackfish pit to Del Lake East access | 6 | C186-C195 | Del Lake East | 0 | 2021-09-23 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting990120210917-20Driver - AZ - After Jan 1012840 | Corbiere and Sons Contracting990120210917-20Driver - AZ - After Jan 1012840INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9901 | 20210917-20 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 12 | Dynamic | 41.4 | 0 |  |  | 662.4 | 86.112 | 748.512 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel hauling from Jackfish pit to Del Lake East access | 6 | C186-C195 | Del Lake East | 0 | 2021-09-23 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting990120210917-20Dump - Triaxle- After Jan 1012662.4 | Corbiere and Sons Contracting990120210917-20Dump - Triaxle- After Jan 1012662.4INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9898 | 20210917-17 | 53510604 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 10 | HR |  |  | 75 | 0 | 750 | 97.5 | 847.5 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Moving gravel from stockpile | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting989820210917-17Operator - Principle - After Jan 1010750 | Corbiere and Sons Contracting989820210917-17Operator - Principle - After Jan 1010750INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9898 | 20210917-17 | 53510604 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 5 | Dynamic | 103.54 | 0 |  |  | 690.25 | 89.7325 | 779.9825 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Moving gravel from stockpile | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting989820210917-17Rock Truck - 30 Ton- After Jan 105690.25 | Corbiere and Sons Contracting989820210917-17Rock Truck - 30 Ton- After Jan 105690.25INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9898 | 20210917-17 | 53510604 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 5 | HR | 9.16 | 0 |  |  | 61.05 | 7.9365 | 68.9865 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Moving gravel from stockpile | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting989820210917-17Excavator Thumb - 30 - 50 ton- After Jan 10561.05 | Corbiere and Sons Contracting989820210917-17Excavator Thumb - 30 - 50 ton- After Jan 10561.05INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9898 | 20210917-17 | 53510604 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 5 | Dynamic | 103.84 | 0 |  |  | 692.25 | 89.9925 | 782.2425 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Moving gravel from stockpile | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting989820210917-17Excavator - 30 ton- After Jan 105692.25 | Corbiere and Sons Contracting989820210917-17Excavator - 30 ton- After Jan 105692.25INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9898 | 20210917-17 | 53510604 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 5 | Dynamic | 98.61 | 0 |  |  | 657.4 | 85.462 | 742.862 | 2021-09-17 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Moving gravel from stockpile | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-21 |  | 37 | 2021-09-22 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting989820210917-17Dozer D6 or equal- After Jan 105657.4 | Corbiere and Sons Contracting989820210917-17Dozer D6 or equal- After Jan 105657.4INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9895 | 20210916-17 | 53510604 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 16 | HR |  |  | 75 | 0 | 1200 | 156 | 1356 | 2021-09-16 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Moving gravel from stockpile at Dead Horse Creek | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-21 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting989520210916-17Operator - Principle - After Jan 10161200 | Corbiere and Sons Contracting989520210916-17Operator - Principle - After Jan 10161200INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9895 | 20210916-17 | 53510604 | Access | 0 | Foreman | 95 | 2 | HR |  |  | 95 | 0 | 190 | 24.7 | 214.7 | 2021-09-16 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Moving gravel from stockpile at Dead Horse Creek | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-21 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting989520210916-17Foreman2190 | Corbiere and Sons Contracting989520210916-17Foreman2190INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9895 | 20210916-17 | 53510604 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 5 | Dynamic | 103.54 | 0 |  |  | 690.25 | 89.7325 | 779.9825 | 2021-09-16 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Moving gravel from stockpile at Dead Horse Creek | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-21 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting989520210916-17Rock Truck - 30 Ton- After Jan 105690.25 | Corbiere and Sons Contracting989520210916-17Rock Truck - 30 Ton- After Jan 105690.25INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9895 | 20210916-17 | 53510604 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 9.16 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2021-09-16 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Moving gravel from stockpile at Dead Horse Creek | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-21 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting989520210916-17Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting989520210916-17Excavator Thumb - 30 - 50 ton- After Jan 1010122.1INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9895 | 20210916-17 | 53510604 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10 | Dynamic | 103.84 | 0 |  |  | 1384.5 | 179.985 | 1564.485 | 2021-09-16 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Moving gravel from stockpile at Dead Horse Creek | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-21 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting989520210916-17Excavator - 30 ton- After Jan 10101384.5 | Corbiere and Sons Contracting989520210916-17Excavator - 30 ton- After Jan 10101384.5INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9895 | 20210916-17 | 53510604 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 2 | Dynamic | 98.61 | 0 |  |  | 262.96 | 34.1848 | 297.1448 | 2021-09-16 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Moving gravel from stockpile at Dead Horse Creek | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-21 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting989520210916-17Dozer D6 or equal- After Jan 102262.96 | Corbiere and Sons Contracting989520210916-17Dozer D6 or equal- After Jan 102262.96INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9891 | 20210915-12 | 53510604 | Access | 0 | Labourer - General - After Jan 10 | 60 | 1 | HR |  |  | 60 | 0 | 60 | 7.8 | 67.8 | 2021-09-15 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Moving gravel from stockpile on deadhorse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-21 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting989120210915-12Labourer - General - After Jan 10160 | Corbiere and Sons Contracting989120210915-12Labourer - General - After Jan 10160INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9891 | 20210915-12 | 53510604 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 8 | HR |  |  | 75 | 0 | 600 | 78 | 678 | 2021-09-15 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Moving gravel from stockpile on deadhorse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-21 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting989120210915-12Operator - Principle - After Jan 108600 | Corbiere and Sons Contracting989120210915-12Operator - Principle - After Jan 108600INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9891 | 20210915-12 | 53510604 | Access | 0 | Foreman | 95 | 2 | HR |  |  | 95 | 0 | 190 | 24.7 | 214.7 | 2021-09-15 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Moving gravel from stockpile on deadhorse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-21 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting989120210915-12Foreman2190 | Corbiere and Sons Contracting989120210915-12Foreman2190INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9891 | 20210915-12 | 53510604 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 7 | HR | 9.16 | 0 |  |  | 85.47 | 11.1111 | 96.5811 | 2021-09-15 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Moving gravel from stockpile on deadhorse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-21 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting989120210915-12Excavator Thumb - 30 - 50 ton- After Jan 10785.47 | Corbiere and Sons Contracting989120210915-12Excavator Thumb - 30 - 50 ton- After Jan 10785.47INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9891 | 20210915-12 | 53510604 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 7 | Dynamic | 103.84 | 0 |  |  | 969.15 | 125.9895 | 1095.1395 | 2021-09-15 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Moving gravel from stockpile on deadhorse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-21 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting989120210915-12Excavator - 30 ton- After Jan 107969.15 | Corbiere and Sons Contracting989120210915-12Excavator - 30 ton- After Jan 107969.15INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 9891 | 20210915-12 | 53510604 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 3 | Dynamic | 98.61 | 0 |  |  | 394.44 | 51.2772 | 445.7172 | 2021-09-15 | 0 | INV #149 | 2021-10-08 | 164 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Moving gravel from stockpile on deadhorse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-09-21 |  | 37 | 2021-09-23 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting989120210915-12Dozer D6 or equal- After Jan 103394.44 | Corbiere and Sons Contracting989120210915-12Dozer D6 or equal- After Jan 103394.44INV #149 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10186 | 20211004-9 | 53510602 | Access | 0 | Labourer - General - After Jan 10 | 60 | 13 | HR |  |  | 60 | 0 | 780 | 101.4 | 881.4 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1018620211004-9Labourer - General - After Jan 1013780 | Corbiere and Sons Contracting1018620211004-9Labourer - General - After Jan 1013780INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10186 | 20211004-9 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 91 | HR |  |  | 75 | 0 | 6825 | 887.25 | 7712.25 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1018620211004-9Operator - Principle - After Jan 10916825 | Corbiere and Sons Contracting1018620211004-9Operator - Principle - After Jan 10916825INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10186 | 20211004-9 | 53510602 | Access | 0 | L.O.A. | 210 | 9 | DAY |  |  |  | 0 | 1890 | 245.7 | 2135.7 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1018620211004-9L.O.A.91890 | Corbiere and Sons Contracting1018620211004-9L.O.A.91890INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10186 | 20211004-9 | 53510602 | Access | 0 | Foreman | 95 | 13 | HR |  |  | 95 | 0 | 1235 | 160.55 | 1395.55 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1018620211004-9Foreman131235 | Corbiere and Sons Contracting1018620211004-9Foreman131235INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10186 | 20211004-9 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 24 | Dynamic | 103.54 | 0 |  |  | 3313.2 | 430.716 | 3743.916 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1018620211004-9Rock Truck - 30 Ton- After Jan 10243313.2 | Corbiere and Sons Contracting1018620211004-9Rock Truck - 30 Ton- After Jan 10243313.2INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10186 | 20211004-9 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 5 | DAY | 182.81 | 0 |  |  | 1218.75 | 158.4375 | 1377.1875 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1018620211004-9Light Truck - Pick up- After Jan 1051218.75 | Corbiere and Sons Contracting1018620211004-9Light Truck - Pick up- After Jan 1051218.75INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10186 | 20211004-9 | 53510602 | Access | 0 | ATV - Side by Side w/ roll bar- After Jan 10 | 18.45 | 10 | HR | 13.84 | 0 |  |  | 184.5 | 23.985 | 208.485 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1018620211004-9ATV - Side by Side w/ roll bar- After Jan 1010184.5 | Corbiere and Sons Contracting1018620211004-9ATV - Side by Side w/ roll bar- After Jan 1010184.5INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10186 | 20211004-9 | 53510602 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 12 | HR | 47.54 | 0 |  |  | 760.56 | 98.8728 | 859.4328 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1018620211004-9Excavator Hammer - 30 - 50 ton- After Jan 1012760.56 | Corbiere and Sons Contracting1018620211004-9Excavator Hammer - 30 - 50 ton- After Jan 1012760.56INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10186 | 20211004-9 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 36 | HR | 9.16 | 0 |  |  | 439.56 | 57.1428 | 496.7028 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1018620211004-9Excavator Thumb - 30 - 50 ton- After Jan 1036439.56 | Corbiere and Sons Contracting1018620211004-9Excavator Thumb - 30 - 50 ton- After Jan 1036439.56INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10186 | 20211004-9 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 48 | Dynamic | 110.22 | 0 |  |  | 7054.08 | 917.0304 | 7971.1104 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1018620211004-9Excavator - 36 ton- After Jan 10487054.08 | Corbiere and Sons Contracting1018620211004-9Excavator - 36 ton- After Jan 10487054.08INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10186 | 20211004-9 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 12 | Dynamic | 103.84 | 0 |  |  | 1661.4 | 215.982 | 1877.382 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1018620211004-9Excavator - 30 ton- After Jan 10121661.4 | Corbiere and Sons Contracting1018620211004-9Excavator - 30 ton- After Jan 10121661.4INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10184 | 20211004-7 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 65 | HR |  |  | 75 | 0 | 4875 | 633.75 | 5508.75 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C236 - C243 | Neys | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1018420211004-7Operator - Principle - After Jan 10654875 | Corbiere and Sons Contracting1018420211004-7Operator - Principle - After Jan 10654875INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10184 | 20211004-7 | 53510602 | Access | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C236 - C243 | Neys | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1018420211004-7L.O.A.51050 | Corbiere and Sons Contracting1018420211004-7L.O.A.51050INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10184 | 20211004-7 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 36 | Dynamic | 103.54 | 0 |  |  | 4969.8 | 646.074 | 5615.874 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C236 - C243 | Neys | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1018420211004-7Rock Truck - 30 Ton- After Jan 10364969.8 | Corbiere and Sons Contracting1018420211004-7Rock Truck - 30 Ton- After Jan 10364969.8INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10184 | 20211004-7 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C236 - C243 | Neys | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1018420211004-7Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting1018420211004-7Light Truck - Pick up- After Jan 102487.5INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10184 | 20211004-7 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 12 | HR | 9.16 | 0 |  |  | 146.52 | 19.0476 | 165.5676 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C236 - C243 | Neys | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1018420211004-7Excavator Thumb - 30 - 50 ton- After Jan 1012146.52 | Corbiere and Sons Contracting1018420211004-7Excavator Thumb - 30 - 50 ton- After Jan 1012146.52INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10184 | 20211004-7 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 12 | Dynamic | 103.84 | 0 |  |  | 1661.4 | 215.982 | 1877.382 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C236 - C243 | Neys | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1018420211004-7Excavator - 30 ton- After Jan 10121661.4 | Corbiere and Sons Contracting1018420211004-7Excavator - 30 ton- After Jan 10121661.4INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10184 | 20211004-7 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 12 | Dynamic | 98.61 | 0 |  |  | 1577.76 | 205.1088 | 1782.8688 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C236 - C243 | Neys | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1018420211004-7Dozer D6 or equal- After Jan 10121577.76 | Corbiere and Sons Contracting1018420211004-7Dozer D6 or equal- After Jan 10121577.76INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10183 | 20211004-6 | 53510602 | Access | 0 | Labourer - General - After Jan 10 | 60 | 21 | HR |  |  | 60 | 0 | 1260 | 163.8 | 1423.8 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1018320211004-6Labourer - General - After Jan 10211260 | Corbiere and Sons Contracting1018320211004-6Labourer - General - After Jan 10211260INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10183 | 20211004-6 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 70 | HR |  |  | 75 | 0 | 5250 | 682.5 | 5932.5 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1018320211004-6Operator - Principle - After Jan 10705250 | Corbiere and Sons Contracting1018320211004-6Operator - Principle - After Jan 10705250INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10183 | 20211004-6 | 53510602 | Access | 0 | L.O.A. | 210 | 8 | DAY |  |  |  | 0 | 1680 | 218.4 | 1898.4 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1018320211004-6L.O.A.81680 | Corbiere and Sons Contracting1018320211004-6L.O.A.81680INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10183 | 20211004-6 | 53510602 | Access | 0 | Foreman | 95 | 13 | HR |  |  | 95 | 0 | 1235 | 160.55 | 1395.55 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1018320211004-6Foreman131235 | Corbiere and Sons Contracting1018320211004-6Foreman131235INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10183 | 20211004-6 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 24 | Dynamic | 103.54 | 0 |  |  | 3313.2 | 430.716 | 3743.916 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1018320211004-6Rock Truck - 30 Ton- After Jan 10243313.2 | Corbiere and Sons Contracting1018320211004-6Rock Truck - 30 Ton- After Jan 10243313.2INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10183 | 20211004-6 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 5 | DAY | 182.81 | 0 |  |  | 1218.75 | 158.4375 | 1377.1875 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1018320211004-6Light Truck - Pick up- After Jan 1051218.75 | Corbiere and Sons Contracting1018320211004-6Light Truck - Pick up- After Jan 1051218.75INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10183 | 20211004-6 | 53510602 | Access | 0 | ATV - Side by Side w/ roll bar- After Jan 10 | 18.45 | 10 | HR | 13.84 | 0 |  |  | 184.5 | 23.985 | 208.485 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1018320211004-6ATV - Side by Side w/ roll bar- After Jan 1010184.5 | Corbiere and Sons Contracting1018320211004-6ATV - Side by Side w/ roll bar- After Jan 1010184.5INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10183 | 20211004-6 | 53510602 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 12 | HR | 47.54 | 0 |  |  | 760.56 | 98.8728 | 859.4328 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1018320211004-6Excavator Hammer - 30 - 50 ton- After Jan 1012760.56 | Corbiere and Sons Contracting1018320211004-6Excavator Hammer - 30 - 50 ton- After Jan 1012760.56INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10183 | 20211004-6 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 17 | HR | 9.16 | 0 |  |  | 207.57 | 26.9841 | 234.5541 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1018320211004-6Excavator Thumb - 30 - 50 ton- After Jan 1017207.57 | Corbiere and Sons Contracting1018320211004-6Excavator Thumb - 30 - 50 ton- After Jan 1017207.57INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10183 | 20211004-6 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 24 | Dynamic | 110.22 | 0 |  |  | 3527.04 | 458.5152 | 3985.5552 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1018320211004-6Excavator - 36 ton- After Jan 10243527.04 | Corbiere and Sons Contracting1018320211004-6Excavator - 36 ton- After Jan 10243527.04INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10183 | 20211004-6 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 5 | Dynamic | 103.84 | 0 |  |  | 692.25 | 89.9925 | 782.2425 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1018320211004-6Excavator - 30 ton- After Jan 105692.25 | Corbiere and Sons Contracting1018320211004-6Excavator - 30 ton- After Jan 105692.25INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10183 | 20211004-6 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 12 | Dynamic | 98.61 | 0 |  |  | 1577.76 | 205.1088 | 1782.8688 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1018320211004-6Dozer D6 or equal- After Jan 10121577.76 | Corbiere and Sons Contracting1018320211004-6Dozer D6 or equal- After Jan 10121577.76INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10191 | 20211004-14 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ex working on road for access to C197 | 6 | C197 | Highway 17 | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1019120211004-14Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1019120211004-14Operator - Principle - After Jan 1012900INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10191 | 20211004-14 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ex working on road for access to C197 | 6 | C197 | Highway 17 | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1019120211004-14Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1019120211004-14Light Truck - Pick up- After Jan 101243.75INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10191 | 20211004-14 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ex working on road for access to C197 | 6 | C197 | Highway 17 | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1019120211004-14Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1019120211004-14Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10191 | 20211004-14 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ex working on road for access to C197 | 6 | C197 | Highway 17 | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1019120211004-14Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting1019120211004-14Excavator - 36 ton- After Jan 10111616.56INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10190 | 20211004-13 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 20 | HR |  |  | 75 | 0 | 1500 | 195 | 1695 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1019020211004-13Operator - Principle - After Jan 10201500 | Corbiere and Sons Contracting1019020211004-13Operator - Principle - After Jan 10201500INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10190 | 20211004-13 | 53510602 | Access | 0 | Foreman | 95 | 6 | HR |  |  | 95 | 0 | 570 | 74.1 | 644.1 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1019020211004-13Foreman6570 | Corbiere and Sons Contracting1019020211004-13Foreman6570INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10190 | 20211004-13 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 1 | Dynamic | 103.54 | 0 |  |  | 138.05 | 17.9465 | 155.9965 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1019020211004-13Rock Truck - 30 Ton- After Jan 101138.05 | Corbiere and Sons Contracting1019020211004-13Rock Truck - 30 Ton- After Jan 101138.05INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10190 | 20211004-13 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 4 | DAY | 182.81 | 0 |  |  | 975 | 126.75 | 1101.75 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1019020211004-13Light Truck - Pick up- After Jan 104975 | Corbiere and Sons Contracting1019020211004-13Light Truck - Pick up- After Jan 104975INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10190 | 20211004-13 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 7 | HR | 9.16 | 0 |  |  | 85.47 | 11.1111 | 96.5811 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1019020211004-13Excavator Thumb - 30 - 50 ton- After Jan 10785.47 | Corbiere and Sons Contracting1019020211004-13Excavator Thumb - 30 - 50 ton- After Jan 10785.47INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10190 | 20211004-13 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 1 | HR | 9.16 | 0 |  |  | 12.21 | 1.5873 | 13.7973 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1019020211004-13Excavator Thumb - 30 - 50 ton- After Jan 10112.21 | Corbiere and Sons Contracting1019020211004-13Excavator Thumb - 30 - 50 ton- After Jan 10112.21INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10190 | 20211004-13 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 5.5 | HR | 9.16 | 0 |  |  | 67.155 | 8.7302 | 75.8851 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1019020211004-13Excavator Thumb - 30 - 50 ton- After Jan 105.567.155 | Corbiere and Sons Contracting1019020211004-13Excavator Thumb - 30 - 50 ton- After Jan 105.567.155INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10190 | 20211004-13 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 7 | Dynamic | 110.22 | 0 |  |  | 1028.72 | 133.7336 | 1162.4536 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1019020211004-13Excavator - 36 ton- After Jan 1071028.72 | Corbiere and Sons Contracting1019020211004-13Excavator - 36 ton- After Jan 1071028.72INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10190 | 20211004-13 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 1 | Dynamic | 110.22 | 0 |  |  | 146.96 | 19.1048 | 166.0648 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1019020211004-13Excavator - 36 ton- After Jan 101146.96 | Corbiere and Sons Contracting1019020211004-13Excavator - 36 ton- After Jan 101146.96INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10190 | 20211004-13 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 5.5 | Dynamic | 103.84 | 0 |  |  | 761.475 | 98.9917 | 860.4668 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1019020211004-13Excavator - 30 ton- After Jan 105.5761.475 | Corbiere and Sons Contracting1019020211004-13Excavator - 30 ton- After Jan 105.5761.475INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10190 | 20211004-13 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 7 | Dynamic | 98.61 | 0 |  |  | 920.36 | 119.6468 | 1040.0068 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1019020211004-13Dozer D6 or equal- After Jan 107920.36 | Corbiere and Sons Contracting1019020211004-13Dozer D6 or equal- After Jan 107920.36INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10188 | 20211004-11 | 53510602 | Access | 0 | Labourer - General - After Jan 10 | 60 | 13 | HR |  |  | 60 | 0 | 780 | 101.4 | 881.4 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acitivities from Mink Creek | 6 | C237-C247 | Mink | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1018820211004-11Labourer - General - After Jan 1013780 | Corbiere and Sons Contracting1018820211004-11Labourer - General - After Jan 1013780INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10188 | 20211004-11 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 52 | HR |  |  | 75 | 0 | 3900 | 507 | 4407 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acitivities from Mink Creek | 6 | C237-C247 | Mink | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1018820211004-11Operator - Principle - After Jan 10523900 | Corbiere and Sons Contracting1018820211004-11Operator - Principle - After Jan 10523900INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10188 | 20211004-11 | 53510602 | Access | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acitivities from Mink Creek | 6 | C237-C247 | Mink | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1018820211004-11L.O.A.61260 | Corbiere and Sons Contracting1018820211004-11L.O.A.61260INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10188 | 20211004-11 | 53510602 | Access | 0 | Foreman | 95 | 13 | HR |  |  | 95 | 0 | 1235 | 160.55 | 1395.55 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acitivities from Mink Creek | 6 | C237-C247 | Mink | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1018820211004-11Foreman131235 | Corbiere and Sons Contracting1018820211004-11Foreman131235INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10188 | 20211004-11 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 12 | Dynamic | 103.54 | 0 |  |  | 1656.6 | 215.358 | 1871.958 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acitivities from Mink Creek | 6 | C237-C247 | Mink | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1018820211004-11Rock Truck - 30 Ton- After Jan 10121656.6 | Corbiere and Sons Contracting1018820211004-11Rock Truck - 30 Ton- After Jan 10121656.6INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10188 | 20211004-11 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 5 | DAY | 182.81 | 0 |  |  | 1218.75 | 158.4375 | 1377.1875 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acitivities from Mink Creek | 6 | C237-C247 | Mink | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1018820211004-11Light Truck - Pick up- After Jan 1051218.75 | Corbiere and Sons Contracting1018820211004-11Light Truck - Pick up- After Jan 1051218.75INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10188 | 20211004-11 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 12 | HR | 9.16 | 0 |  |  | 146.52 | 19.0476 | 165.5676 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acitivities from Mink Creek | 6 | C237-C247 | Mink | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1018820211004-11Excavator Thumb - 30 - 50 ton- After Jan 1012146.52 | Corbiere and Sons Contracting1018820211004-11Excavator Thumb - 30 - 50 ton- After Jan 1012146.52INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10188 | 20211004-11 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 12 | Dynamic | 110.22 | 0 |  |  | 1763.52 | 229.2576 | 1992.7776 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acitivities from Mink Creek | 6 | C237-C247 | Mink | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1018820211004-11Excavator - 36 ton- After Jan 10121763.52 | Corbiere and Sons Contracting1018820211004-11Excavator - 36 ton- After Jan 10121763.52INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10188 | 20211004-11 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 12 | Dynamic | 110.22 | 0 |  |  | 1763.52 | 229.2576 | 1992.7776 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acitivities from Mink Creek | 6 | C237-C247 | Mink | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1018820211004-11Excavator - 36 ton- After Jan 10121763.52 | Corbiere and Sons Contracting1018820211004-11Excavator - 36 ton- After Jan 10121763.52INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10188 | 20211004-11 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 12 | Dynamic | 98.61 | 0 |  |  | 1577.76 | 205.1088 | 1782.8688 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acitivities from Mink Creek | 6 | C237-C247 | Mink | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1018820211004-11Dozer D6 or equal- After Jan 10121577.76 | Corbiere and Sons Contracting1018820211004-11Dozer D6 or equal- After Jan 10121577.76INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10187 | 20211004-10 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 35 | HR |  |  | 75 | 0 | 2625 | 341.25 | 2966.25 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1018720211004-10Operator - Principle - After Jan 10352625 | Corbiere and Sons Contracting1018720211004-10Operator - Principle - After Jan 10352625INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10187 | 20211004-10 | 53510602 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1018720211004-10L.O.A.3630 | Corbiere and Sons Contracting1018720211004-10L.O.A.3630INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10187 | 20211004-10 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 12 | Dynamic | 103.54 | 0 |  |  | 1656.6 | 215.358 | 1871.958 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1018720211004-10Rock Truck - 30 Ton- After Jan 10121656.6 | Corbiere and Sons Contracting1018720211004-10Rock Truck - 30 Ton- After Jan 10121656.6INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10187 | 20211004-10 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1018720211004-10Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1018720211004-10Light Truck - Pick up- After Jan 101243.75INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10187 | 20211004-10 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 8 | HR | 9.16 | 0 |  |  | 97.68 | 12.6984 | 110.3784 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1018720211004-10Excavator Thumb - 30 - 50 ton- After Jan 10897.68 | Corbiere and Sons Contracting1018720211004-10Excavator Thumb - 30 - 50 ton- After Jan 10897.68INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10187 | 20211004-10 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 8 | Dynamic | 110.22 | 0 |  |  | 1175.68 | 152.8384 | 1328.5184 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1018720211004-10Excavator - 36 ton- After Jan 1081175.68 | Corbiere and Sons Contracting1018720211004-10Excavator - 36 ton- After Jan 1081175.68INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10187 | 20211004-10 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 8 | Dynamic | 98.61 | 0 |  |  | 1051.84 | 136.7392 | 1188.5792 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1018720211004-10Dozer D6 or equal- After Jan 1081051.84 | Corbiere and Sons Contracting1018720211004-10Dozer D6 or equal- After Jan 1081051.84INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10173 | 20211003-9 | 53510602 | Access | 0 | Labourer - General - After Jan 10 | 60 | 13 | HR |  |  | 60 | 0 | 780 | 101.4 | 881.4 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017320211003-9Labourer - General - After Jan 1013780 | Corbiere and Sons Contracting1017320211003-9Labourer - General - After Jan 1013780INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10173 | 20211003-9 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 104 | HR |  |  | 75 | 0 | 7800 | 1014 | 8814 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017320211003-9Operator - Principle - After Jan 101047800 | Corbiere and Sons Contracting1017320211003-9Operator - Principle - After Jan 101047800INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10173 | 20211003-9 | 53510602 | Access | 0 | L.O.A. | 210 | 10 | DAY |  |  |  | 0 | 2100 | 273 | 2373 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017320211003-9L.O.A.102100 | Corbiere and Sons Contracting1017320211003-9L.O.A.102100INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10173 | 20211003-9 | 53510602 | Access | 0 | Foreman | 95 | 13 | HR |  |  | 95 | 0 | 1235 | 160.55 | 1395.55 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017320211003-9Foreman131235 | Corbiere and Sons Contracting1017320211003-9Foreman131235INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10173 | 20211003-9 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 12 | Dynamic | 103.54 | 0 |  |  | 1656.6 | 215.358 | 1871.958 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017320211003-9Rock Truck - 30 Ton- After Jan 10121656.6 | Corbiere and Sons Contracting1017320211003-9Rock Truck - 30 Ton- After Jan 10121656.6INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10173 | 20211003-9 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 12 | Dynamic | 103.54 | 0 |  |  | 1656.6 | 215.358 | 1871.958 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017320211003-9Rock Truck - 30 Ton- After Jan 10121656.6 | Corbiere and Sons Contracting1017320211003-9Rock Truck - 30 Ton- After Jan 10121656.6INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10173 | 20211003-9 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 5 | DAY | 182.81 | 0 |  |  | 1218.75 | 158.4375 | 1377.1875 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017320211003-9Light Truck - Pick up- After Jan 1051218.75 | Corbiere and Sons Contracting1017320211003-9Light Truck - Pick up- After Jan 1051218.75INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10173 | 20211003-9 | 53510602 | Access | 0 | ATV - Side by Side w/ roll bar- After Jan 10 | 18.45 | 10 | HR | 13.84 | 0 |  |  | 184.5 | 23.985 | 208.485 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017320211003-9ATV - Side by Side w/ roll bar- After Jan 1010184.5 | Corbiere and Sons Contracting1017320211003-9ATV - Side by Side w/ roll bar- After Jan 1010184.5INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10173 | 20211003-9 | 53510602 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 12 | HR | 47.54 | 0 |  |  | 760.56 | 98.8728 | 859.4328 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017320211003-9Excavator Hammer - 30 - 50 ton- After Jan 1012760.56 | Corbiere and Sons Contracting1017320211003-9Excavator Hammer - 30 - 50 ton- After Jan 1012760.56INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10173 | 20211003-9 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 12 | HR | 9.16 | 0 |  |  | 146.52 | 19.0476 | 165.5676 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017320211003-9Excavator Thumb - 30 - 50 ton- After Jan 1012146.52 | Corbiere and Sons Contracting1017320211003-9Excavator Thumb - 30 - 50 ton- After Jan 1012146.52INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10173 | 20211003-9 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 12 | HR | 9.16 | 0 |  |  | 146.52 | 19.0476 | 165.5676 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017320211003-9Excavator Thumb - 30 - 50 ton- After Jan 1012146.52 | Corbiere and Sons Contracting1017320211003-9Excavator Thumb - 30 - 50 ton- After Jan 1012146.52INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10173 | 20211003-9 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 12 | HR | 9.16 | 0 |  |  | 146.52 | 19.0476 | 165.5676 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017320211003-9Excavator Thumb - 30 - 50 ton- After Jan 1012146.52 | Corbiere and Sons Contracting1017320211003-9Excavator Thumb - 30 - 50 ton- After Jan 1012146.52INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10173 | 20211003-9 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 12 | Dynamic | 110.22 | 0 |  |  | 1763.52 | 229.2576 | 1992.7776 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017320211003-9Excavator - 36 ton- After Jan 10121763.52 | Corbiere and Sons Contracting1017320211003-9Excavator - 36 ton- After Jan 10121763.52INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10173 | 20211003-9 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 12 | Dynamic | 110.22 | 0 |  |  | 1763.52 | 229.2576 | 1992.7776 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017320211003-9Excavator - 36 ton- After Jan 10121763.52 | Corbiere and Sons Contracting1017320211003-9Excavator - 36 ton- After Jan 10121763.52INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10173 | 20211003-9 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 24 | Dynamic | 110.22 | 0 |  |  | 3527.04 | 458.5152 | 3985.5552 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017320211003-9Excavator - 36 ton- After Jan 10243527.04 | Corbiere and Sons Contracting1017320211003-9Excavator - 36 ton- After Jan 10243527.04INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10173 | 20211003-9 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 12 | Dynamic | 103.84 | 0 |  |  | 1661.4 | 215.982 | 1877.382 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017320211003-9Excavator - 30 ton- After Jan 10121661.4 | Corbiere and Sons Contracting1017320211003-9Excavator - 30 ton- After Jan 10121661.4INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10173 | 20211003-9 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 12 | Dynamic | 98.61 | 0 |  |  | 1577.76 | 205.1088 | 1782.8688 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017320211003-9Dozer D6 or equal- After Jan 10121577.76 | Corbiere and Sons Contracting1017320211003-9Dozer D6 or equal- After Jan 10121577.76INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10172 | 20211003-8 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 13 | HR |  |  | 75 | 0 | 975 | 126.75 | 1101.75 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C257-C267 | Hare Lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017220211003-8Operator - Principle - After Jan 1013975 | Corbiere and Sons Contracting1017220211003-8Operator - Principle - After Jan 1013975INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10172 | 20211003-8 | 53510602 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C257-C267 | Hare Lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017220211003-8L.O.A.1210 | Corbiere and Sons Contracting1017220211003-8L.O.A.1210INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10172 | 20211003-8 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C257-C267 | Hare Lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017220211003-8Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1017220211003-8Light Truck - Pick up- After Jan 101243.75INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10172 | 20211003-8 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 12 | Dynamic | 103.84 | 0 |  |  | 1661.4 | 215.982 | 1877.382 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C257-C267 | Hare Lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017220211003-8Excavator - 30 ton- After Jan 10121661.4 | Corbiere and Sons Contracting1017220211003-8Excavator - 30 ton- After Jan 10121661.4INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10171 | 20211003-7 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 59 | HR |  |  | 75 | 0 | 4425 | 575.25 | 5000.25 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017120211003-7Operator - Principle - After Jan 10594425 | Corbiere and Sons Contracting1017120211003-7Operator - Principle - After Jan 10594425INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10171 | 20211003-7 | 53510602 | Access | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017120211003-7L.O.A.51050 | Corbiere and Sons Contracting1017120211003-7L.O.A.51050INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10171 | 20211003-7 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 19 | Dynamic | 103.54 | 0 |  |  | 2622.95 | 340.9835 | 2963.9335 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017120211003-7Rock Truck - 30 Ton- After Jan 10192622.95 | Corbiere and Sons Contracting1017120211003-7Rock Truck - 30 Ton- After Jan 10192622.95INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10171 | 20211003-7 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017120211003-7Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting1017120211003-7Light Truck - Pick up- After Jan 102487.5INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10171 | 20211003-7 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 12 | HR | 9.16 | 0 |  |  | 146.52 | 19.0476 | 165.5676 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017120211003-7Excavator Thumb - 30 - 50 ton- After Jan 1012146.52 | Corbiere and Sons Contracting1017120211003-7Excavator Thumb - 30 - 50 ton- After Jan 1012146.52INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10171 | 20211003-7 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 12 | HR | 9.16 | 0 |  |  | 146.52 | 19.0476 | 165.5676 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017120211003-7Excavator Thumb - 30 - 50 ton- After Jan 1012146.52 | Corbiere and Sons Contracting1017120211003-7Excavator Thumb - 30 - 50 ton- After Jan 1012146.52INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10171 | 20211003-7 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 12 | Dynamic | 110.22 | 0 |  |  | 1763.52 | 229.2576 | 1992.7776 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017120211003-7Excavator - 36 ton- After Jan 10121763.52 | Corbiere and Sons Contracting1017120211003-7Excavator - 36 ton- After Jan 10121763.52INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10171 | 20211003-7 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 12 | Dynamic | 103.84 | 0 |  |  | 1661.4 | 215.982 | 1877.382 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017120211003-7Excavator - 30 ton- After Jan 10121661.4 | Corbiere and Sons Contracting1017120211003-7Excavator - 30 ton- After Jan 10121661.4INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10171 | 20211003-7 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 12 | Dynamic | 98.61 | 0 |  |  | 1577.76 | 205.1088 | 1782.8688 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017120211003-7Dozer D6 or equal- After Jan 10121577.76 | Corbiere and Sons Contracting1017120211003-7Dozer D6 or equal- After Jan 10121577.76INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10170 | 20211003-6 | 53510602 | Access | 0 | Labourer - General - After Jan 10 | 60 | 13 | HR |  |  | 60 | 0 | 780 | 101.4 | 881.4 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017020211003-6Labourer - General - After Jan 1013780 | Corbiere and Sons Contracting1017020211003-6Labourer - General - After Jan 1013780INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10170 | 20211003-6 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 78 | HR |  |  | 75 | 0 | 5850 | 760.5 | 6610.5 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017020211003-6Operator - Principle - After Jan 10785850 | Corbiere and Sons Contracting1017020211003-6Operator - Principle - After Jan 10785850INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10170 | 20211003-6 | 53510602 | Access | 0 | L.O.A. | 210 | 8 | DAY |  |  |  | 0 | 1680 | 218.4 | 1898.4 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017020211003-6L.O.A.81680 | Corbiere and Sons Contracting1017020211003-6L.O.A.81680INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10170 | 20211003-6 | 53510602 | Access | 0 | Foreman | 95 | 13 | HR |  |  | 95 | 0 | 1235 | 160.55 | 1395.55 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017020211003-6Foreman131235 | Corbiere and Sons Contracting1017020211003-6Foreman131235INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10170 | 20211003-6 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 24 | Dynamic | 103.54 | 0 |  |  | 3313.2 | 430.716 | 3743.916 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017020211003-6Rock Truck - 30 Ton- After Jan 10243313.2 | Corbiere and Sons Contracting1017020211003-6Rock Truck - 30 Ton- After Jan 10243313.2INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10170 | 20211003-6 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 5 | DAY | 182.81 | 0 |  |  | 1218.75 | 158.4375 | 1377.1875 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017020211003-6Light Truck - Pick up- After Jan 1051218.75 | Corbiere and Sons Contracting1017020211003-6Light Truck - Pick up- After Jan 1051218.75INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10170 | 20211003-6 | 53510602 | Access | 0 | ATV - Side by Side w/ roll bar- After Jan 10 | 18.45 | 10 | HR | 13.84 | 0 |  |  | 184.5 | 23.985 | 208.485 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017020211003-6ATV - Side by Side w/ roll bar- After Jan 1010184.5 | Corbiere and Sons Contracting1017020211003-6ATV - Side by Side w/ roll bar- After Jan 1010184.5INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10170 | 20211003-6 | 53510602 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 12 | HR | 47.54 | 0 |  |  | 760.56 | 98.8728 | 859.4328 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017020211003-6Excavator Hammer - 30 - 50 ton- After Jan 1012760.56 | Corbiere and Sons Contracting1017020211003-6Excavator Hammer - 30 - 50 ton- After Jan 1012760.56INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10170 | 20211003-6 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 12 | HR | 9.16 | 0 |  |  | 146.52 | 19.0476 | 165.5676 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017020211003-6Excavator Thumb - 30 - 50 ton- After Jan 1012146.52 | Corbiere and Sons Contracting1017020211003-6Excavator Thumb - 30 - 50 ton- After Jan 1012146.52INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10170 | 20211003-6 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 12 | HR | 9.16 | 0 |  |  | 146.52 | 19.0476 | 165.5676 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017020211003-6Excavator Thumb - 30 - 50 ton- After Jan 1012146.52 | Corbiere and Sons Contracting1017020211003-6Excavator Thumb - 30 - 50 ton- After Jan 1012146.52INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10170 | 20211003-6 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 12 | Dynamic | 110.22 | 0 |  |  | 1763.52 | 229.2576 | 1992.7776 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017020211003-6Excavator - 36 ton- After Jan 10121763.52 | Corbiere and Sons Contracting1017020211003-6Excavator - 36 ton- After Jan 10121763.52INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10170 | 20211003-6 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 12 | Dynamic | 110.22 | 0 |  |  | 1763.52 | 229.2576 | 1992.7776 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017020211003-6Excavator - 36 ton- After Jan 10121763.52 | Corbiere and Sons Contracting1017020211003-6Excavator - 36 ton- After Jan 10121763.52INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10170 | 20211003-6 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 12 | Dynamic | 103.84 | 0 |  |  | 1661.4 | 215.982 | 1877.382 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017020211003-6Excavator - 30 ton- After Jan 10121661.4 | Corbiere and Sons Contracting1017020211003-6Excavator - 30 ton- After Jan 10121661.4INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10170 | 20211003-6 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 12 | Dynamic | 98.61 | 0 |  |  | 1577.76 | 205.1088 | 1782.8688 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017020211003-6Dozer D6 or equal- After Jan 10121577.76 | Corbiere and Sons Contracting1017020211003-6Dozer D6 or equal- After Jan 10121577.76INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10179 | 20211003-15 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 4 | HR |  |  | 75 | 0 | 300 | 39 | 339 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gervais RT hauling with Corbiere crew on Del | 6 | C186-C195 | Del Lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017920211003-15Operator - Principle - After Jan 104300 | Corbiere and Sons Contracting1017920211003-15Operator - Principle - After Jan 104300INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10179 | 20211003-15 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 4 | Dynamic | 103.54 | 0 |  |  | 552.2 | 71.786 | 623.986 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gervais RT hauling with Corbiere crew on Del | 6 | C186-C195 | Del Lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017920211003-15Rock Truck - 30 Ton- After Jan 104552.2 | Corbiere and Sons Contracting1017920211003-15Rock Truck - 30 Ton- After Jan 104552.2INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10178 | 20211003-14 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 7 | HR |  |  | 75 | 0 | 525 | 68.25 | 593.25 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ex working on road for access to C197 | 6 | C197 | Highway 17 | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017820211003-14Operator - Principle - After Jan 107525 | Corbiere and Sons Contracting1017820211003-14Operator - Principle - After Jan 107525INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10178 | 20211003-14 | 53510602 | Access | 0 | Foreman | 95 | 1 | HR |  |  | 95 | 0 | 95 | 12.35 | 107.35 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ex working on road for access to C197 | 6 | C197 | Highway 17 | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017820211003-14Foreman195 | Corbiere and Sons Contracting1017820211003-14Foreman195INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10178 | 20211003-14 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 7 | HR | 9.16 | 0 |  |  | 85.47 | 11.1111 | 96.5811 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ex working on road for access to C197 | 6 | C197 | Highway 17 | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017820211003-14Excavator Thumb - 30 - 50 ton- After Jan 10785.47 | Corbiere and Sons Contracting1017820211003-14Excavator Thumb - 30 - 50 ton- After Jan 10785.47INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10178 | 20211003-14 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 7 | Dynamic | 110.22 | 0 |  |  | 1028.72 | 133.7336 | 1162.4536 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ex working on road for access to C197 | 6 | C197 | Highway 17 | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017820211003-14Excavator - 36 ton- After Jan 1071028.72 | Corbiere and Sons Contracting1017820211003-14Excavator - 36 ton- After Jan 1071028.72INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10177 | 20211003-13 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 53 | HR |  |  | 75 | 0 | 3975 | 516.75 | 4491.75 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017720211003-13Operator - Principle - After Jan 10533975 | Corbiere and Sons Contracting1017720211003-13Operator - Principle - After Jan 10533975INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10177 | 20211003-13 | 53510602 | Access | 0 | Foreman | 95 | 10 | HR |  |  | 95 | 0 | 950 | 123.5 | 1073.5 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017720211003-13Foreman10950 | Corbiere and Sons Contracting1017720211003-13Foreman10950INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10177 | 20211003-13 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 18 | Dynamic | 103.54 | 0 |  |  | 2484.9 | 323.037 | 2807.937 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017720211003-13Rock Truck - 30 Ton- After Jan 10182484.9 | Corbiere and Sons Contracting1017720211003-13Rock Truck - 30 Ton- After Jan 10182484.9INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10177 | 20211003-13 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 5 | DAY | 182.81 | 0 |  |  | 1218.75 | 158.4375 | 1377.1875 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017720211003-13Light Truck - Pick up- After Jan 1051218.75 | Corbiere and Sons Contracting1017720211003-13Light Truck - Pick up- After Jan 1051218.75INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10177 | 20211003-13 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017720211003-13Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1017720211003-13Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10177 | 20211003-13 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 7 | HR | 9.16 | 0 |  |  | 85.47 | 11.1111 | 96.5811 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017720211003-13Excavator Thumb - 30 - 50 ton- After Jan 10785.47 | Corbiere and Sons Contracting1017720211003-13Excavator Thumb - 30 - 50 ton- After Jan 10785.47INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10177 | 20211003-13 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 7 | HR | 9.16 | 0 |  |  | 85.47 | 11.1111 | 96.5811 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017720211003-13Excavator Thumb - 30 - 50 ton- After Jan 10785.47 | Corbiere and Sons Contracting1017720211003-13Excavator Thumb - 30 - 50 ton- After Jan 10785.47INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10177 | 20211003-13 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017720211003-13Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting1017720211003-13Excavator - 36 ton- After Jan 10111616.56INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10177 | 20211003-13 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 7 | Dynamic | 110.22 | 0 |  |  | 1028.72 | 133.7336 | 1162.4536 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017720211003-13Excavator - 36 ton- After Jan 1071028.72 | Corbiere and Sons Contracting1017720211003-13Excavator - 36 ton- After Jan 1071028.72INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10177 | 20211003-13 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 7 | Dynamic | 103.84 | 0 |  |  | 969.15 | 125.9895 | 1095.1395 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017720211003-13Excavator - 30 ton- After Jan 107969.15 | Corbiere and Sons Contracting1017720211003-13Excavator - 30 ton- After Jan 107969.15INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10177 | 20211003-13 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017720211003-13Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting1017720211003-13Dozer D6 or equal- After Jan 10111446.28INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10175 | 20211003-11 | 53510602 | Access | 0 | Labourer - General - After Jan 10 | 60 | 13 | HR |  |  | 60 | 0 | 780 | 101.4 | 881.4 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acitivities from Mink Creek | 6 | C237-C247 | Mink Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017520211003-11Labourer - General - After Jan 1013780 | Corbiere and Sons Contracting1017520211003-11Labourer - General - After Jan 1013780INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10175 | 20211003-11 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 52 | HR |  |  | 75 | 0 | 3900 | 507 | 4407 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acitivities from Mink Creek | 6 | C237-C247 | Mink Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017520211003-11Operator - Principle - After Jan 10523900 | Corbiere and Sons Contracting1017520211003-11Operator - Principle - After Jan 10523900INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10175 | 20211003-11 | 53510602 | Access | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acitivities from Mink Creek | 6 | C237-C247 | Mink Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017520211003-11L.O.A.61260 | Corbiere and Sons Contracting1017520211003-11L.O.A.61260INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10175 | 20211003-11 | 53510602 | Access | 0 | Foreman | 95 | 13 | HR |  |  | 95 | 0 | 1235 | 160.55 | 1395.55 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acitivities from Mink Creek | 6 | C237-C247 | Mink Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017520211003-11Foreman131235 | Corbiere and Sons Contracting1017520211003-11Foreman131235INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10175 | 20211003-11 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 12 | Dynamic | 103.54 | 0 |  |  | 1656.6 | 215.358 | 1871.958 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acitivities from Mink Creek | 6 | C237-C247 | Mink Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017520211003-11Rock Truck - 30 Ton- After Jan 10121656.6 | Corbiere and Sons Contracting1017520211003-11Rock Truck - 30 Ton- After Jan 10121656.6INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10175 | 20211003-11 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 5 | DAY | 182.81 | 0 |  |  | 1218.75 | 158.4375 | 1377.1875 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acitivities from Mink Creek | 6 | C237-C247 | Mink Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017520211003-11Light Truck - Pick up- After Jan 1051218.75 | Corbiere and Sons Contracting1017520211003-11Light Truck - Pick up- After Jan 1051218.75INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10175 | 20211003-11 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 12 | HR | 9.16 | 0 |  |  | 146.52 | 19.0476 | 165.5676 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acitivities from Mink Creek | 6 | C237-C247 | Mink Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017520211003-11Excavator Thumb - 30 - 50 ton- After Jan 1012146.52 | Corbiere and Sons Contracting1017520211003-11Excavator Thumb - 30 - 50 ton- After Jan 1012146.52INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10175 | 20211003-11 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 12 | Dynamic | 110.22 | 0 |  |  | 1763.52 | 229.2576 | 1992.7776 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acitivities from Mink Creek | 6 | C237-C247 | Mink Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017520211003-11Excavator - 36 ton- After Jan 10121763.52 | Corbiere and Sons Contracting1017520211003-11Excavator - 36 ton- After Jan 10121763.52INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10175 | 20211003-11 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 12 | Dynamic | 110.22 | 0 |  |  | 1763.52 | 229.2576 | 1992.7776 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acitivities from Mink Creek | 6 | C237-C247 | Mink Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017520211003-11Excavator - 36 ton- After Jan 10121763.52 | Corbiere and Sons Contracting1017520211003-11Excavator - 36 ton- After Jan 10121763.52INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10175 | 20211003-11 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 12 | Dynamic | 98.61 | 0 |  |  | 1577.76 | 205.1088 | 1782.8688 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acitivities from Mink Creek | 6 | C237-C247 | Mink Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017520211003-11Dozer D6 or equal- After Jan 10121577.76 | Corbiere and Sons Contracting1017520211003-11Dozer D6 or equal- After Jan 10121577.76INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10174 | 20211003-10 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 39 | HR |  |  | 75 | 0 | 2925 | 380.25 | 3305.25 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017420211003-10Operator - Principle - After Jan 10392925 | Corbiere and Sons Contracting1017420211003-10Operator - Principle - After Jan 10392925INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10174 | 20211003-10 | 53510602 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017420211003-10L.O.A.3630 | Corbiere and Sons Contracting1017420211003-10L.O.A.3630INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10174 | 20211003-10 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 12 | Dynamic | 103.54 | 0 |  |  | 1656.6 | 215.358 | 1871.958 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017420211003-10Rock Truck - 30 Ton- After Jan 10121656.6 | Corbiere and Sons Contracting1017420211003-10Rock Truck - 30 Ton- After Jan 10121656.6INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10174 | 20211003-10 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017420211003-10Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1017420211003-10Light Truck - Pick up- After Jan 101243.75INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10174 | 20211003-10 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 12 | HR | 9.16 | 0 |  |  | 146.52 | 19.0476 | 165.5676 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017420211003-10Excavator Thumb - 30 - 50 ton- After Jan 1012146.52 | Corbiere and Sons Contracting1017420211003-10Excavator Thumb - 30 - 50 ton- After Jan 1012146.52INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10174 | 20211003-10 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 12 | Dynamic | 110.22 | 0 |  |  | 1763.52 | 229.2576 | 1992.7776 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017420211003-10Excavator - 36 ton- After Jan 10121763.52 | Corbiere and Sons Contracting1017420211003-10Excavator - 36 ton- After Jan 10121763.52INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10174 | 20211003-10 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 12 | Dynamic | 98.61 | 0 |  |  | 1577.76 | 205.1088 | 1782.8688 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1017420211003-10Dozer D6 or equal- After Jan 10121577.76 | Corbiere and Sons Contracting1017420211003-10Dozer D6 or equal- After Jan 10121577.76INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10159 | 20211002-9 | 53510602 | Access | 0 | Labourer - General - After Jan 10 | 60 | 13 | HR |  |  | 60 | 0 | 780 | 101.4 | 881.4 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road - Float moved RT, Ex, and D6 from Hare to Del | 6 | C186-C195 | Del Lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1015920211002-9Labourer - General - After Jan 1013780 | Corbiere and Sons Contracting1015920211002-9Labourer - General - After Jan 1013780INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10159 | 20211002-9 | 53510602 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 7 | HR |  |  | 70 | 0 | 490 | 63.7 | 553.7 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road - Float moved RT, Ex, and D6 from Hare to Del | 6 | C186-C195 | Del Lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1015920211002-9Driver - AZ - After Jan 107490 | Corbiere and Sons Contracting1015920211002-9Driver - AZ - After Jan 107490INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10159 | 20211002-9 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 96 | HR |  |  | 75 | 0 | 7200 | 936 | 8136 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road - Float moved RT, Ex, and D6 from Hare to Del | 6 | C186-C195 | Del Lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1015920211002-9Operator - Principle - After Jan 10967200 | Corbiere and Sons Contracting1015920211002-9Operator - Principle - After Jan 10967200INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10159 | 20211002-9 | 53510602 | Access | 0 | L.O.A. | 210 | 9 | DAY |  |  |  | 0 | 1890 | 245.7 | 2135.7 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road - Float moved RT, Ex, and D6 from Hare to Del | 6 | C186-C195 | Del Lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1015920211002-9L.O.A.91890 | Corbiere and Sons Contracting1015920211002-9L.O.A.91890INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10159 | 20211002-9 | 53510602 | Access | 0 | Foreman | 95 | 13 | HR |  |  | 95 | 0 | 1235 | 160.55 | 1395.55 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road - Float moved RT, Ex, and D6 from Hare to Del | 6 | C186-C195 | Del Lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1015920211002-9Foreman131235 | Corbiere and Sons Contracting1015920211002-9Foreman131235INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10159 | 20211002-9 | 53510602 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 7 | Dynamic | 91.79 |  |  |  | 856.73 | 111.3749 | 968.1049 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road - Float moved RT, Ex, and D6 from Hare to Del | 6 | C186-C195 | Del Lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1015920211002-9Tractor Trailer - 60 Ton- After Jan 107856.73 | Corbiere and Sons Contracting1015920211002-9Tractor Trailer - 60 Ton- After Jan 107856.73INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10159 | 20211002-9 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 6 | Dynamic | 103.54 | 0 |  |  | 828.3 | 107.679 | 935.979 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road - Float moved RT, Ex, and D6 from Hare to Del | 6 | C186-C195 | Del Lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1015920211002-9Rock Truck - 30 Ton- After Jan 106828.3 | Corbiere and Sons Contracting1015920211002-9Rock Truck - 30 Ton- After Jan 106828.3INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10159 | 20211002-9 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 24 | Dynamic | 103.54 | 0 |  |  | 3313.2 | 430.716 | 3743.916 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road - Float moved RT, Ex, and D6 from Hare to Del | 6 | C186-C195 | Del Lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1015920211002-9Rock Truck - 30 Ton- After Jan 10243313.2 | Corbiere and Sons Contracting1015920211002-9Rock Truck - 30 Ton- After Jan 10243313.2INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10159 | 20211002-9 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 4 | DAY | 182.81 | 0 |  |  | 975 | 126.75 | 1101.75 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road - Float moved RT, Ex, and D6 from Hare to Del | 6 | C186-C195 | Del Lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1015920211002-9Light Truck - Pick up- After Jan 104975 | Corbiere and Sons Contracting1015920211002-9Light Truck - Pick up- After Jan 104975INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10159 | 20211002-9 | 53510602 | Access | 0 | ATV - Side by Side w/ roll bar- After Jan 10 | 18.45 | 10 | HR | 13.84 | 0 |  |  | 184.5 | 23.985 | 208.485 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road - Float moved RT, Ex, and D6 from Hare to Del | 6 | C186-C195 | Del Lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1015920211002-9ATV - Side by Side w/ roll bar- After Jan 1010184.5 | Corbiere and Sons Contracting1015920211002-9ATV - Side by Side w/ roll bar- After Jan 1010184.5INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10159 | 20211002-9 | 53510602 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 12 | HR | 47.54 | 0 |  |  | 760.56 | 98.8728 | 859.4328 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road - Float moved RT, Ex, and D6 from Hare to Del | 6 | C186-C195 | Del Lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1015920211002-9Excavator Hammer - 30 - 50 ton- After Jan 1012760.56 | Corbiere and Sons Contracting1015920211002-9Excavator Hammer - 30 - 50 ton- After Jan 1012760.56INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10159 | 20211002-9 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 6 | HR | 9.16 | 0 |  |  | 73.26 | 9.5238 | 82.7838 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road - Float moved RT, Ex, and D6 from Hare to Del | 6 | C186-C195 | Del Lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1015920211002-9Excavator Thumb - 30 - 50 ton- After Jan 10673.26 | Corbiere and Sons Contracting1015920211002-9Excavator Thumb - 30 - 50 ton- After Jan 10673.26INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10159 | 20211002-9 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 24 | HR | 9.16 | 0 |  |  | 293.04 | 38.0952 | 331.1352 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road - Float moved RT, Ex, and D6 from Hare to Del | 6 | C186-C195 | Del Lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1015920211002-9Excavator Thumb - 30 - 50 ton- After Jan 1024293.04 | Corbiere and Sons Contracting1015920211002-9Excavator Thumb - 30 - 50 ton- After Jan 1024293.04INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10159 | 20211002-9 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 24 | Dynamic | 110.22 | 0 |  |  | 3527.04 | 458.5152 | 3985.5552 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road - Float moved RT, Ex, and D6 from Hare to Del | 6 | C186-C195 | Del Lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1015920211002-9Excavator - 36 ton- After Jan 10243527.04 | Corbiere and Sons Contracting1015920211002-9Excavator - 36 ton- After Jan 10243527.04INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10159 | 20211002-9 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 24 | Dynamic | 110.22 | 0 |  |  | 3527.04 | 458.5152 | 3985.5552 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road - Float moved RT, Ex, and D6 from Hare to Del | 6 | C186-C195 | Del Lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1015920211002-9Excavator - 36 ton- After Jan 10243527.04 | Corbiere and Sons Contracting1015920211002-9Excavator - 36 ton- After Jan 10243527.04INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10159 | 20211002-9 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 6 | Dynamic | 103.84 | 0 |  |  | 830.7 | 107.991 | 938.691 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road - Float moved RT, Ex, and D6 from Hare to Del | 6 | C186-C195 | Del Lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1015920211002-9Excavator - 30 ton- After Jan 106830.7 | Corbiere and Sons Contracting1015920211002-9Excavator - 30 ton- After Jan 106830.7INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10158 | 20211002-8 | 53510602 | Access | 0 | Labourer - General - After Jan 10 | 60 | 4 | HR |  |  | 60 | 0 | 240 | 31.2 | 271.2 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C257-C267 | Hare Lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1015820211002-8Labourer - General - After Jan 104240 | Corbiere and Sons Contracting1015820211002-8Labourer - General - After Jan 104240INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10158 | 20211002-8 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 13 | HR |  |  | 75 | 0 | 975 | 126.75 | 1101.75 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C257-C267 | Hare Lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1015820211002-8Operator - Principle - After Jan 1013975 | Corbiere and Sons Contracting1015820211002-8Operator - Principle - After Jan 1013975INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10158 | 20211002-8 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 4 | HR |  |  | 75 | 0 | 300 | 39 | 339 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C257-C267 | Hare Lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1015820211002-8Operator - Principle - After Jan 104300 | Corbiere and Sons Contracting1015820211002-8Operator - Principle - After Jan 104300INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10158 | 20211002-8 | 53510602 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C257-C267 | Hare Lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1015820211002-8L.O.A.3630 | Corbiere and Sons Contracting1015820211002-8L.O.A.3630INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10158 | 20211002-8 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 4 | Dynamic | 103.54 | 0 |  |  | 552.2 | 71.786 | 623.986 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C257-C267 | Hare Lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1015820211002-8Rock Truck - 30 Ton- After Jan 104552.2 | Corbiere and Sons Contracting1015820211002-8Rock Truck - 30 Ton- After Jan 104552.2INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10158 | 20211002-8 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C257-C267 | Hare Lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1015820211002-8Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting1015820211002-8Light Truck - Pick up- After Jan 102487.5INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10158 | 20211002-8 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 4 | HR | 9.16 | 0 |  |  | 48.84 | 6.3492 | 55.1892 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C257-C267 | Hare Lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1015820211002-8Excavator Thumb - 30 - 50 ton- After Jan 10448.84 | Corbiere and Sons Contracting1015820211002-8Excavator Thumb - 30 - 50 ton- After Jan 10448.84INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10158 | 20211002-8 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 4 | Dynamic | 103.84 | 0 |  |  | 553.8 | 71.994 | 625.794 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C257-C267 | Hare Lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1015820211002-8Excavator - 30 ton- After Jan 104553.8 | Corbiere and Sons Contracting1015820211002-8Excavator - 30 ton- After Jan 104553.8INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10158 | 20211002-8 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 12 | Dynamic | 103.84 | 0 |  |  | 1661.4 | 215.982 | 1877.382 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C257-C267 | Hare Lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1015820211002-8Excavator - 30 ton- After Jan 10121661.4 | Corbiere and Sons Contracting1015820211002-8Excavator - 30 ton- After Jan 10121661.4INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10157 | 20211002-7 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 59 | HR |  |  | 75 | 0 | 4425 | 575.25 | 5000.25 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1015720211002-7Operator - Principle - After Jan 10594425 | Corbiere and Sons Contracting1015720211002-7Operator - Principle - After Jan 10594425INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10157 | 20211002-7 | 53510602 | Access | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1015720211002-7L.O.A.51050 | Corbiere and Sons Contracting1015720211002-7L.O.A.51050INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10157 | 20211002-7 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 19 | Dynamic | 103.54 | 0 |  |  | 2622.95 | 340.9835 | 2963.9335 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1015720211002-7Rock Truck - 30 Ton- After Jan 10192622.95 | Corbiere and Sons Contracting1015720211002-7Rock Truck - 30 Ton- After Jan 10192622.95INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10157 | 20211002-7 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1015720211002-7Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting1015720211002-7Light Truck - Pick up- After Jan 102487.5INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10157 | 20211002-7 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 12 | HR | 9.16 | 0 |  |  | 146.52 | 19.0476 | 165.5676 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1015720211002-7Excavator Thumb - 30 - 50 ton- After Jan 1012146.52 | Corbiere and Sons Contracting1015720211002-7Excavator Thumb - 30 - 50 ton- After Jan 1012146.52INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10157 | 20211002-7 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 12 | HR | 9.16 | 0 |  |  | 146.52 | 19.0476 | 165.5676 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1015720211002-7Excavator Thumb - 30 - 50 ton- After Jan 1012146.52 | Corbiere and Sons Contracting1015720211002-7Excavator Thumb - 30 - 50 ton- After Jan 1012146.52INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10157 | 20211002-7 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 12 | Dynamic | 110.22 | 0 |  |  | 1763.52 | 229.2576 | 1992.7776 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1015720211002-7Excavator - 36 ton- After Jan 10121763.52 | Corbiere and Sons Contracting1015720211002-7Excavator - 36 ton- After Jan 10121763.52INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10157 | 20211002-7 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 12 | Dynamic | 103.84 | 0 |  |  | 1661.4 | 215.982 | 1877.382 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1015720211002-7Excavator - 30 ton- After Jan 10121661.4 | Corbiere and Sons Contracting1015720211002-7Excavator - 30 ton- After Jan 10121661.4INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10157 | 20211002-7 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 12 | Dynamic | 98.61 | 0 |  |  | 1577.76 | 205.1088 | 1782.8688 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1015720211002-7Dozer D6 or equal- After Jan 10121577.76 | Corbiere and Sons Contracting1015720211002-7Dozer D6 or equal- After Jan 10121577.76INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10156 | 20211002-6 | 53510602 | Access | 0 | Labourer - General - After Jan 10 | 60 | 13 | HR |  |  | 0 | 0 | 780 | 101.4 | 881.4 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Roa | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1015620211002-6Labourer - General - After Jan 1013780 | Corbiere and Sons Contracting1015620211002-6Labourer - General - After Jan 1013780INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10156 | 20211002-6 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 78 | HR |  |  | 0 | 0 | 5850 | 760.5 | 6610.5 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Roa | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1015620211002-6Operator - Principle - After Jan 10785850 | Corbiere and Sons Contracting1015620211002-6Operator - Principle - After Jan 10785850INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10156 | 20211002-6 | 53510602 | Access | 0 | L.O.A. | 210 | 8 | DAY |  |  | 0 | 0 | 1680 | 218.4 | 1898.4 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Roa | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1015620211002-6L.O.A.81680 | Corbiere and Sons Contracting1015620211002-6L.O.A.81680INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10156 | 20211002-6 | 53510602 | Access | 0 | Foreman | 95 | 13 | HR |  |  | 0 | 0 | 1235 | 160.55 | 1395.55 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Roa | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1015620211002-6Foreman131235 | Corbiere and Sons Contracting1015620211002-6Foreman131235INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10156 | 20211002-6 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 24 | Dynamic | 103.54 | 0 |  |  | 3313.2 | 430.716 | 3743.916 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Roa | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1015620211002-6Rock Truck - 30 Ton- After Jan 10243313.2 | Corbiere and Sons Contracting1015620211002-6Rock Truck - 30 Ton- After Jan 10243313.2INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10156 | 20211002-6 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 5 | DAY | 182.81 | 0 |  |  | 1218.75 | 158.4375 | 1377.1875 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Roa | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1015620211002-6Light Truck - Pick up- After Jan 1051218.75 | Corbiere and Sons Contracting1015620211002-6Light Truck - Pick up- After Jan 1051218.75INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10156 | 20211002-6 | 53510602 | Access | 0 | ATV - Side by Side w/ roll bar- After Jan 10 | 18.45 | 10 | HR | 13.84 | 0 |  |  | 184.5 | 23.985 | 208.485 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Roa | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1015620211002-6ATV - Side by Side w/ roll bar- After Jan 1010184.5 | Corbiere and Sons Contracting1015620211002-6ATV - Side by Side w/ roll bar- After Jan 1010184.5INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10156 | 20211002-6 | 53510602 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 12 | HR | 47.54 | 0 |  |  | 760.56 | 98.8728 | 859.4328 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Roa | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1015620211002-6Excavator Hammer - 30 - 50 ton- After Jan 1012760.56 | Corbiere and Sons Contracting1015620211002-6Excavator Hammer - 30 - 50 ton- After Jan 1012760.56INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10156 | 20211002-6 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 12 | HR | 9.16 | 0 |  |  | 146.52 | 19.0476 | 165.5676 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Roa | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1015620211002-6Excavator Thumb - 30 - 50 ton- After Jan 1012146.52 | Corbiere and Sons Contracting1015620211002-6Excavator Thumb - 30 - 50 ton- After Jan 1012146.52INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10156 | 20211002-6 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 12 | HR | 9.16 | 0 |  |  | 146.52 | 19.0476 | 165.5676 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Roa | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1015620211002-6Excavator Thumb - 30 - 50 ton- After Jan 1012146.52 | Corbiere and Sons Contracting1015620211002-6Excavator Thumb - 30 - 50 ton- After Jan 1012146.52INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10156 | 20211002-6 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 12 | Dynamic | 0 | 0 |  |  | 1763.52 | 229.2576 | 1992.7776 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Roa | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1015620211002-6Excavator - 36 ton- After Jan 10121763.52 | Corbiere and Sons Contracting1015620211002-6Excavator - 36 ton- After Jan 10121763.52INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10156 | 20211002-6 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 12 | Dynamic | 0 | 0 |  |  | 1763.52 | 229.2576 | 1992.7776 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Roa | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1015620211002-6Excavator - 36 ton- After Jan 10121763.52 | Corbiere and Sons Contracting1015620211002-6Excavator - 36 ton- After Jan 10121763.52INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10156 | 20211002-6 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 12 | Dynamic | 103.84 | 0 |  |  | 1661.4 | 215.982 | 1877.382 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Roa | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1015620211002-6Excavator - 30 ton- After Jan 10121661.4 | Corbiere and Sons Contracting1015620211002-6Excavator - 30 ton- After Jan 10121661.4INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10156 | 20211002-6 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 12 | Dynamic | 0 | 0 |  |  | 1577.76 | 205.1088 | 1782.8688 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Roa | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1015620211002-6Dozer D6 or equal- After Jan 10121577.76 | Corbiere and Sons Contracting1015620211002-6Dozer D6 or equal- After Jan 10121577.76INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10163 | 20211002-13 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 43 | HR |  |  | 75 | 0 | 3225 | 419.25 | 3644.25 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1016320211002-13Operator - Principle - After Jan 10433225 | Corbiere and Sons Contracting1016320211002-13Operator - Principle - After Jan 10433225INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10163 | 20211002-13 | 53510602 | Access | 0 | Foreman | 95 | 10 | HR |  |  | 95 | 0 | 950 | 123.5 | 1073.5 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1016320211002-13Foreman10950 | Corbiere and Sons Contracting1016320211002-13Foreman10950INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10163 | 20211002-13 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 14 | Dynamic | 103.54 | 0 |  |  | 1932.7 | 251.251 | 2183.951 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1016320211002-13Rock Truck - 30 Ton- After Jan 10141932.7 | Corbiere and Sons Contracting1016320211002-13Rock Truck - 30 Ton- After Jan 10141932.7INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10163 | 20211002-13 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 4 | DAY | 182.81 | 0 |  |  | 975 | 126.75 | 1101.75 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1016320211002-13Light Truck - Pick up- After Jan 104975 | Corbiere and Sons Contracting1016320211002-13Light Truck - Pick up- After Jan 104975INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10163 | 20211002-13 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 9.16 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1016320211002-13Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting1016320211002-13Excavator Thumb - 30 - 50 ton- After Jan 1010122.1INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10163 | 20211002-13 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 9.16 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1016320211002-13Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting1016320211002-13Excavator Thumb - 30 - 50 ton- After Jan 1010122.1INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10163 | 20211002-13 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 4 | HR | 9.16 | 0 |  |  | 48.84 | 6.3492 | 55.1892 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1016320211002-13Excavator Thumb - 30 - 50 ton- After Jan 10448.84 | Corbiere and Sons Contracting1016320211002-13Excavator Thumb - 30 - 50 ton- After Jan 10448.84INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10163 | 20211002-13 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10 | Dynamic | 110.22 | 0 |  |  | 1469.6 | 191.048 | 1660.648 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1016320211002-13Excavator - 36 ton- After Jan 10101469.6 | Corbiere and Sons Contracting1016320211002-13Excavator - 36 ton- After Jan 10101469.6INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10163 | 20211002-13 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10 | Dynamic | 110.22 | 0 |  |  | 1469.6 | 191.048 | 1660.648 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1016320211002-13Excavator - 36 ton- After Jan 10101469.6 | Corbiere and Sons Contracting1016320211002-13Excavator - 36 ton- After Jan 10101469.6INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10163 | 20211002-13 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 4 | Dynamic | 103.84 | 0 |  |  | 553.8 | 71.994 | 625.794 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1016320211002-13Excavator - 30 ton- After Jan 104553.8 | Corbiere and Sons Contracting1016320211002-13Excavator - 30 ton- After Jan 104553.8INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10163 | 20211002-13 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1016320211002-13Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting1016320211002-13Dozer D6 or equal- After Jan 10111446.28INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10162 | 20211002-12 | 53510602 | Access | 0 | Labourer - General - After Jan 10 | 60 | 13 | HR |  |  | 60 | 0 | 780 | 101.4 | 881.4 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acitivities from Mink Creek - Jeff did float moves | 6 | C237-C247 | Mink Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1016220211002-12Labourer - General - After Jan 1013780 | Corbiere and Sons Contracting1016220211002-12Labourer - General - After Jan 1013780INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10162 | 20211002-12 | 53510602 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 6 | HR |  |  | 70 | 0 | 420 | 54.6 | 474.6 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acitivities from Mink Creek - Jeff did float moves | 6 | C237-C247 | Mink Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1016220211002-12Driver - AZ - After Jan 106420 | Corbiere and Sons Contracting1016220211002-12Driver - AZ - After Jan 106420INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10162 | 20211002-12 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 55 | HR |  |  | 75 | 0 | 4125 | 536.25 | 4661.25 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acitivities from Mink Creek - Jeff did float moves | 6 | C237-C247 | Mink Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1016220211002-12Operator - Principle - After Jan 10554125 | Corbiere and Sons Contracting1016220211002-12Operator - Principle - After Jan 10554125INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10162 | 20211002-12 | 53510602 | Access | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acitivities from Mink Creek - Jeff did float moves | 6 | C237-C247 | Mink Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1016220211002-12L.O.A.61260 | Corbiere and Sons Contracting1016220211002-12L.O.A.61260INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10162 | 20211002-12 | 53510602 | Access | 0 | Foreman | 95 | 13 | HR |  |  | 95 | 0 | 1235 | 160.55 | 1395.55 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acitivities from Mink Creek - Jeff did float moves | 6 | C237-C247 | Mink Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1016220211002-12Foreman131235 | Corbiere and Sons Contracting1016220211002-12Foreman131235INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10162 | 20211002-12 | 53510602 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 6 | Dynamic | 91.79 | 0 |  |  | 734.34 | 95.4642 | 829.8042 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acitivities from Mink Creek - Jeff did float moves | 6 | C237-C247 | Mink Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1016220211002-12Tractor Trailer - 60 Ton- After Jan 106734.34 | Corbiere and Sons Contracting1016220211002-12Tractor Trailer - 60 Ton- After Jan 106734.34INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10162 | 20211002-12 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 4 | Dynamic | 103.54 | 0 |  |  | 552.2 | 71.786 | 623.986 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acitivities from Mink Creek - Jeff did float moves | 6 | C237-C247 | Mink Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1016220211002-12Rock Truck - 30 Ton- After Jan 104552.2 | Corbiere and Sons Contracting1016220211002-12Rock Truck - 30 Ton- After Jan 104552.2INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10162 | 20211002-12 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 10 | Dynamic | 103.54 | 0 |  |  | 1380.5 | 179.465 | 1559.965 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acitivities from Mink Creek - Jeff did float moves | 6 | C237-C247 | Mink Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1016220211002-12Rock Truck - 30 Ton- After Jan 10101380.5 | Corbiere and Sons Contracting1016220211002-12Rock Truck - 30 Ton- After Jan 10101380.5INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10162 | 20211002-12 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 5 | DAY | 182.81 | 0 |  |  | 1218.75 | 158.4375 | 1377.1875 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acitivities from Mink Creek - Jeff did float moves | 6 | C237-C247 | Mink Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1016220211002-12Light Truck - Pick up- After Jan 1051218.75 | Corbiere and Sons Contracting1016220211002-12Light Truck - Pick up- After Jan 1051218.75INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10162 | 20211002-12 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 12 | HR | 9.16 | 0 |  |  | 146.52 | 19.0476 | 165.5676 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acitivities from Mink Creek - Jeff did float moves | 6 | C237-C247 | Mink Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1016220211002-12Excavator Thumb - 30 - 50 ton- After Jan 1012146.52 | Corbiere and Sons Contracting1016220211002-12Excavator Thumb - 30 - 50 ton- After Jan 1012146.52INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10162 | 20211002-12 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 12 | Dynamic | 110.22 | 0 |  |  | 1763.52 | 229.2576 | 1992.7776 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acitivities from Mink Creek - Jeff did float moves | 6 | C237-C247 | Mink Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1016220211002-12Excavator - 36 ton- After Jan 10121763.52 | Corbiere and Sons Contracting1016220211002-12Excavator - 36 ton- After Jan 10121763.52INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10162 | 20211002-12 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acitivities from Mink Creek - Jeff did float moves | 6 | C237-C247 | Mink Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1016220211002-12Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting1016220211002-12Excavator - 36 ton- After Jan 10111616.56INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10162 | 20211002-12 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 8 | Dynamic | 98.61 | 0 |  |  | 1051.84 | 136.7392 | 1188.5792 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acitivities from Mink Creek - Jeff did float moves | 6 | C237-C247 | Mink Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1016220211002-12Dozer D6 or equal- After Jan 1081051.84 | Corbiere and Sons Contracting1016220211002-12Dozer D6 or equal- After Jan 1081051.84INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10139 | 20211001-9 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 55 | HR |  |  | 75 | 0 | 4125 | 536.25 | 4661.25 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1013920211001-9Operator - Principle - After Jan 10554125 | Corbiere and Sons Contracting1013920211001-9Operator - Principle - After Jan 10554125INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10139 | 20211001-9 | 53510602 | Access | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1013920211001-9L.O.A.51050 | Corbiere and Sons Contracting1013920211001-9L.O.A.51050INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10139 | 20211001-9 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 20 | Dynamic | 103.54 | 0 |  |  | 2761 | 358.93 | 3119.93 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1013920211001-9Rock Truck - 30 Ton- After Jan 10202761 | Corbiere and Sons Contracting1013920211001-9Rock Truck - 30 Ton- After Jan 10202761INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10139 | 20211001-9 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1013920211001-9Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting1013920211001-9Light Truck - Pick up- After Jan 103731.25INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10139 | 20211001-9 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 9.16 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1013920211001-9Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting1013920211001-9Excavator Thumb - 30 - 50 ton- After Jan 1010122.1INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10139 | 20211001-9 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 9.16 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1013920211001-9Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting1013920211001-9Excavator Thumb - 30 - 50 ton- After Jan 1010122.1INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10139 | 20211001-9 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10 | Dynamic | 110.22 | 0 |  |  | 1469.6 | 191.048 | 1660.648 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1013920211001-9Excavator - 36 ton- After Jan 10101469.6 | Corbiere and Sons Contracting1013920211001-9Excavator - 36 ton- After Jan 10101469.6INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10139 | 20211001-9 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10 | Dynamic | 103.84 | 0 |  |  | 1384.5 | 179.985 | 1564.485 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1013920211001-9Excavator - 30 ton- After Jan 10101384.5 | Corbiere and Sons Contracting1013920211001-9Excavator - 30 ton- After Jan 10101384.5INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10139 | 20211001-9 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10 | Dynamic | 98.61 | 0 |  |  | 1314.8 | 170.924 | 1485.724 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1013920211001-9Dozer D6 or equal- After Jan 10101314.8 | Corbiere and Sons Contracting1013920211001-9Dozer D6 or equal- After Jan 10101314.8INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10138 | 20211001-8 | 53510602 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 4 | HR |  |  | 70 | 0 | 280 | 36.4 | 316.4 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road - Float moved RT over from Little Pic | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1013820211001-8Driver - AZ - After Jan 104280 | Corbiere and Sons Contracting1013820211001-8Driver - AZ - After Jan 104280INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10138 | 20211001-8 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 60 | HR |  |  | 75 | 0 | 4500 | 585 | 5085 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road - Float moved RT over from Little Pic | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1013820211001-8Operator - Principle - After Jan 10604500 | Corbiere and Sons Contracting1013820211001-8Operator - Principle - After Jan 10604500INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10138 | 20211001-8 | 53510602 | Access | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road - Float moved RT over from Little Pic | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1013820211001-8L.O.A.61260 | Corbiere and Sons Contracting1013820211001-8L.O.A.61260INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10138 | 20211001-8 | 53510602 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road - Float moved RT over from Little Pic | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1013820211001-8Foreman121140 | Corbiere and Sons Contracting1013820211001-8Foreman121140INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10138 | 20211001-8 | 53510602 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 4 | Dynamic | 91.79 | 0 |  |  | 489.56 | 63.6428 | 553.2028 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road - Float moved RT over from Little Pic | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1013820211001-8Tractor Trailer - 60 Ton- After Jan 104489.56 | Corbiere and Sons Contracting1013820211001-8Tractor Trailer - 60 Ton- After Jan 104489.56INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10138 | 20211001-8 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 21 | Dynamic | 103.54 | 0 |  |  | 2899.05 | 376.8765 | 3275.9265 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road - Float moved RT over from Little Pic | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1013820211001-8Rock Truck - 30 Ton- After Jan 10212899.05 | Corbiere and Sons Contracting1013820211001-8Rock Truck - 30 Ton- After Jan 10212899.05INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10138 | 20211001-8 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road - Float moved RT over from Little Pic | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1013820211001-8Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting1013820211001-8Light Truck - Pick up- After Jan 103731.25INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10138 | 20211001-8 | 53510602 | Access | 0 | ATV - Side by Side w/ roll bar- After Jan 10 | 18.45 | 10 | HR | 13.84 | 0 |  |  | 184.5 | 23.985 | 208.485 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road - Float moved RT over from Little Pic | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1013820211001-8ATV - Side by Side w/ roll bar- After Jan 1010184.5 | Corbiere and Sons Contracting1013820211001-8ATV - Side by Side w/ roll bar- After Jan 1010184.5INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10138 | 20211001-8 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road - Float moved RT over from Little Pic | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1013820211001-8Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1013820211001-8Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10138 | 20211001-8 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road - Float moved RT over from Little Pic | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1013820211001-8Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting1013820211001-8Excavator - 36 ton- After Jan 10111616.56INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10138 | 20211001-8 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road - Float moved RT over from Little Pic | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1013820211001-8Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting1013820211001-8Excavator - 30 ton- After Jan 10111522.95INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10138 | 20211001-8 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road - Float moved RT over from Little Pic | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1013820211001-8Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting1013820211001-8Dozer D6 or equal- After Jan 10111446.28INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10151 | 20211001-21 | 53510602 | Access | 0 | 3rd Party Charges | 1 | 20607 | Unit |  |  |  |  | 20607 | 2678.91 | 23285.91 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Flagging done by Best Towing from Sept 22nd to Oct 1st | 6 | C130-C277 | WF6 | 0 | 2021-10-12 |  | 58 | 2021-10-13 | NO NUMBER AVAILABLE | Flagging by Best Towing |  |  |  |  | 06 | Corbiere and Sons Contracting1015120211001-213rd Party Charges2060720607 | Corbiere and Sons Contracting1015120211001-213rd Party Charges2060720607INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10146 | 20211001-16 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 65 | HR |  |  | 75 | 0 | 4875 | 633.75 | 5508.75 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse - Float brought mats | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1014620211001-16Operator - Principle - After Jan 10654875 | Corbiere and Sons Contracting1014620211001-16Operator - Principle - After Jan 10654875INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10146 | 20211001-16 | 53510602 | Access | 0 | Foreman | 95 | 9 | HR |  |  | 95 | 0 | 855 | 111.15 | 966.15 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse - Float brought mats | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1014620211001-16Foreman9855 | Corbiere and Sons Contracting1014620211001-16Foreman9855INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10146 | 20211001-16 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 21 | Dynamic | 103.54 | 0 |  |  | 2899.05 | 376.8765 | 3275.9265 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse - Float brought mats | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1014620211001-16Rock Truck - 30 Ton- After Jan 10212899.05 | Corbiere and Sons Contracting1014620211001-16Rock Truck - 30 Ton- After Jan 10212899.05INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10146 | 20211001-16 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 4 | DAY | 182.81 | 0 |  |  | 975 | 126.75 | 1101.75 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse - Float brought mats | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1014620211001-16Light Truck - Pick up- After Jan 104975 | Corbiere and Sons Contracting1014620211001-16Light Truck - Pick up- After Jan 104975INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10146 | 20211001-16 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 9.16 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse - Float brought mats | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1014620211001-16Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting1014620211001-16Excavator Thumb - 30 - 50 ton- After Jan 1010122.1INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10146 | 20211001-16 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 9.16 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse - Float brought mats | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1014620211001-16Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting1014620211001-16Excavator Thumb - 30 - 50 ton- After Jan 1010122.1INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10146 | 20211001-16 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 7 | HR | 9.16 | 0 |  |  | 85.47 | 11.1111 | 96.5811 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse - Float brought mats | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1014620211001-16Excavator Thumb - 30 - 50 ton- After Jan 10785.47 | Corbiere and Sons Contracting1014620211001-16Excavator Thumb - 30 - 50 ton- After Jan 10785.47INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10146 | 20211001-16 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse - Float brought mats | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1014620211001-16Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1014620211001-16Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10146 | 20211001-16 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10 | Dynamic | 110.22 | 0 |  |  | 1469.6 | 191.048 | 1660.648 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse - Float brought mats | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1014620211001-16Excavator - 36 ton- After Jan 10101469.6 | Corbiere and Sons Contracting1014620211001-16Excavator - 36 ton- After Jan 10101469.6INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10146 | 20211001-16 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10 | Dynamic | 110.22 | 0 |  |  | 1469.6 | 191.048 | 1660.648 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse - Float brought mats | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1014620211001-16Excavator - 36 ton- After Jan 10101469.6 | Corbiere and Sons Contracting1014620211001-16Excavator - 36 ton- After Jan 10101469.6INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10146 | 20211001-16 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 7 | Dynamic | 110.22 | 0 |  |  | 1028.72 | 133.7336 | 1162.4536 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse - Float brought mats | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1014620211001-16Excavator - 36 ton- After Jan 1071028.72 | Corbiere and Sons Contracting1014620211001-16Excavator - 36 ton- After Jan 1071028.72INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10146 | 20211001-16 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse - Float brought mats | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1014620211001-16Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting1014620211001-16Excavator - 30 ton- After Jan 10111522.95INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10146 | 20211001-16 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse - Float brought mats | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1014620211001-16Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting1014620211001-16Dozer D6 or equal- After Jan 10111446.28INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10145 | 20211001-15 | 53510602 | Access | 0 | Labourer - General - After Jan 10 | 60 | 10 | HR |  |  | 60 | 0 | 600 | 78 | 678 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acitivities from Mink Creek - Jeff did float moves | 6 | C237-C247 | Mink Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1014520211001-15Labourer - General - After Jan 1010600 | Corbiere and Sons Contracting1014520211001-15Labourer - General - After Jan 1010600INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10145 | 20211001-15 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 26 | HR |  |  | 75 | 0 | 1950 | 253.5 | 2203.5 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acitivities from Mink Creek - Jeff did float moves | 6 | C237-C247 | Mink Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1014520211001-15Operator - Principle - After Jan 10261950 | Corbiere and Sons Contracting1014520211001-15Operator - Principle - After Jan 10261950INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10145 | 20211001-15 | 53510602 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acitivities from Mink Creek - Jeff did float moves | 6 | C237-C247 | Mink Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1014520211001-15L.O.A.3630 | Corbiere and Sons Contracting1014520211001-15L.O.A.3630INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10145 | 20211001-15 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acitivities from Mink Creek - Jeff did float moves | 6 | C237-C247 | Mink Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1014520211001-15Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting1014520211001-15Rock Truck - 30 Ton- After Jan 10111518.55INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10145 | 20211001-15 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acitivities from Mink Creek - Jeff did float moves | 6 | C237-C247 | Mink Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1014520211001-15Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1014520211001-15Light Truck - Pick up- After Jan 101243.75INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10145 | 20211001-15 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 12 | HR | 9.16 | 0 |  |  | 146.52 | 19.0476 | 165.5676 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acitivities from Mink Creek - Jeff did float moves | 6 | C237-C247 | Mink Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1014520211001-15Excavator Thumb - 30 - 50 ton- After Jan 1012146.52 | Corbiere and Sons Contracting1014520211001-15Excavator Thumb - 30 - 50 ton- After Jan 1012146.52INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10145 | 20211001-15 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 12 | Dynamic | 110.22 | 0 |  |  | 1763.52 | 229.2576 | 1992.7776 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acitivities from Mink Creek - Jeff did float moves | 6 | C237-C247 | Mink Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1014520211001-15Excavator - 36 ton- After Jan 10121763.52 | Corbiere and Sons Contracting1014520211001-15Excavator - 36 ton- After Jan 10121763.52INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10144 | 20211001-14 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 38 | HR |  |  | 75 | 0 | 2850 | 370.5 | 3220.5 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1014420211001-14Operator - Principle - After Jan 10382850 | Corbiere and Sons Contracting1014420211001-14Operator - Principle - After Jan 10382850INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10144 | 20211001-14 | 53510602 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1014420211001-14L.O.A.4840 | Corbiere and Sons Contracting1014420211001-14L.O.A.4840INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10144 | 20211001-14 | 53510602 | Access | 0 | Foreman | 95 | 13 | HR |  |  | 95 | 0 | 1235 | 160.55 | 1395.55 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1014420211001-14Foreman131235 | Corbiere and Sons Contracting1014420211001-14Foreman131235INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10144 | 20211001-14 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 9.5 | Dynamic | 103.54 | 0 |  |  | 1311.475 | 170.4917 | 1481.9668 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1014420211001-14Rock Truck - 30 Ton- After Jan 109.51311.475 | Corbiere and Sons Contracting1014420211001-14Rock Truck - 30 Ton- After Jan 109.51311.475INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10144 | 20211001-14 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1014420211001-14Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting1014420211001-14Light Truck - Pick up- After Jan 102487.5INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10144 | 20211001-14 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1014420211001-14Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1014420211001-14Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10144 | 20211001-14 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1014420211001-14Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting1014420211001-14Excavator - 36 ton- After Jan 10111616.56INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10144 | 20211001-14 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 9.5 | Dynamic | 98.61 | 0 |  |  | 1249.06 | 162.3778 | 1411.4378 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1014420211001-14Dozer D6 or equal- After Jan 109.51249.06 | Corbiere and Sons Contracting1014420211001-14Dozer D6 or equal- After Jan 109.51249.06INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10143 | 20211001-13 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 39 | HR |  |  | 75 | 0 | 2925 | 380.25 | 3305.25 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Pic | 6 | C215-C216 | Little Pic River | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1014320211001-13Operator - Principle - After Jan 10392925 | Corbiere and Sons Contracting1014320211001-13Operator - Principle - After Jan 10392925INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10143 | 20211001-13 | 53510602 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Pic | 6 | C215-C216 | Little Pic River | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1014320211001-13L.O.A.3630 | Corbiere and Sons Contracting1014320211001-13L.O.A.3630INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10143 | 20211001-13 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 12 | Dynamic | 103.54 | 0 |  |  | 1656.6 | 215.358 | 1871.958 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Pic | 6 | C215-C216 | Little Pic River | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1014320211001-13Rock Truck - 30 Ton- After Jan 10121656.6 | Corbiere and Sons Contracting1014320211001-13Rock Truck - 30 Ton- After Jan 10121656.6INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10143 | 20211001-13 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Pic | 6 | C215-C216 | Little Pic River | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1014320211001-13Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting1014320211001-13Light Truck - Pick up- After Jan 102487.5INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10143 | 20211001-13 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 12 | Dynamic | 110.22 | 0 |  |  | 1763.52 | 229.2576 | 1992.7776 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Pic | 6 | C215-C216 | Little Pic River | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1014320211001-13Excavator - 36 ton- After Jan 10121763.52 | Corbiere and Sons Contracting1014320211001-13Excavator - 36 ton- After Jan 10121763.52INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10143 | 20211001-13 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 12 | Dynamic | 98.61 | 0 |  |  | 1577.76 | 205.1088 | 1782.8688 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Pic | 6 | C215-C216 | Little Pic River | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1014320211001-13Dozer D6 or equal- After Jan 10121577.76 | Corbiere and Sons Contracting1014320211001-13Dozer D6 or equal- After Jan 10121577.76INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10141 | 20211001-11 | 53510602 | Access | 0 | Labourer - General - After Jan 10 | 60 | 13 | HR |  |  | 60 | 0 | 780 | 101.4 | 881.4 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1014120211001-11Labourer - General - After Jan 1013780 | Corbiere and Sons Contracting1014120211001-11Labourer - General - After Jan 1013780INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10141 | 20211001-11 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 78 | HR |  |  | 75 | 0 | 5850 | 760.5 | 6610.5 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1014120211001-11Operator - Principle - After Jan 10785850 | Corbiere and Sons Contracting1014120211001-11Operator - Principle - After Jan 10785850INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10141 | 20211001-11 | 53510602 | Access | 0 | L.O.A. | 210 | 8 | DAY |  |  |  | 0 | 1680 | 218.4 | 1898.4 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1014120211001-11L.O.A.81680 | Corbiere and Sons Contracting1014120211001-11L.O.A.81680INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10141 | 20211001-11 | 53510602 | Access | 0 | Foreman | 95 | 13 | HR |  |  | 95 | 0 | 1235 | 160.55 | 1395.55 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1014120211001-11Foreman131235 | Corbiere and Sons Contracting1014120211001-11Foreman131235INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10141 | 20211001-11 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 12 | Dynamic | 103.54 | 0 |  |  | 1656.6 | 215.358 | 1871.958 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1014120211001-11Rock Truck - 30 Ton- After Jan 10121656.6 | Corbiere and Sons Contracting1014120211001-11Rock Truck - 30 Ton- After Jan 10121656.6INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10141 | 20211001-11 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 4 | DAY | 182.81 | 0 |  |  | 975 | 126.75 | 1101.75 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1014120211001-11Light Truck - Pick up- After Jan 104975 | Corbiere and Sons Contracting1014120211001-11Light Truck - Pick up- After Jan 104975INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10141 | 20211001-11 | 53510602 | Access | 0 | ATV - Side by Side w/ roll bar- After Jan 10 | 18.45 | 10 | HR | 13.84 | 0 |  |  | 184.5 | 23.985 | 208.485 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1014120211001-11ATV - Side by Side w/ roll bar- After Jan 1010184.5 | Corbiere and Sons Contracting1014120211001-11ATV - Side by Side w/ roll bar- After Jan 1010184.5INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10141 | 20211001-11 | 53510602 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 12 | HR | 47.54 | 0 |  |  | 760.56 | 98.8728 | 859.4328 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1014120211001-11Excavator Hammer - 30 - 50 ton- After Jan 1012760.56 | Corbiere and Sons Contracting1014120211001-11Excavator Hammer - 30 - 50 ton- After Jan 1012760.56INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10141 | 20211001-11 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 12 | HR | 9.16 | 0 |  |  | 146.52 | 19.0476 | 165.5676 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1014120211001-11Excavator Thumb - 30 - 50 ton- After Jan 1012146.52 | Corbiere and Sons Contracting1014120211001-11Excavator Thumb - 30 - 50 ton- After Jan 1012146.52INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10141 | 20211001-11 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 12 | HR | 9.16 | 0 |  |  | 146.52 | 19.0476 | 165.5676 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1014120211001-11Excavator Thumb - 30 - 50 ton- After Jan 1012146.52 | Corbiere and Sons Contracting1014120211001-11Excavator Thumb - 30 - 50 ton- After Jan 1012146.52INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10141 | 20211001-11 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 12 | Dynamic | 110.22 | 0 |  |  | 1763.52 | 229.2576 | 1992.7776 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1014120211001-11Excavator - 36 ton- After Jan 10121763.52 | Corbiere and Sons Contracting1014120211001-11Excavator - 36 ton- After Jan 10121763.52INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10141 | 20211001-11 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 12 | Dynamic | 110.22 | 0 |  |  | 1763.52 | 229.2576 | 1992.7776 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1014120211001-11Excavator - 36 ton- After Jan 10121763.52 | Corbiere and Sons Contracting1014120211001-11Excavator - 36 ton- After Jan 10121763.52INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10141 | 20211001-11 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 12 | Dynamic | 110.22 | 0 |  |  | 1763.52 | 229.2576 | 1992.7776 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1014120211001-11Excavator - 36 ton- After Jan 10121763.52 | Corbiere and Sons Contracting1014120211001-11Excavator - 36 ton- After Jan 10121763.52INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10141 | 20211001-11 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1014120211001-11Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting1014120211001-11Excavator - 36 ton- After Jan 1091322.64INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10141 | 20211001-11 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 9 | Dynamic | 98.61 | 0 |  |  | 1183.32 | 153.8316 | 1337.1516 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1014120211001-11Dozer D6 or equal- After Jan 1091183.32 | Corbiere and Sons Contracting1014120211001-11Dozer D6 or equal- After Jan 1091183.32INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10125 | 20210930-9 | 53510602 | Access | 0 | Labourer - General - After Jan 10 | 60 | 13 | HR |  |  | 60 | 0 | 780 | 101.4 | 881.4 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C257-C267 | Hare Lake Road | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1012520210930-9Labourer - General - After Jan 1013780 | Corbiere and Sons Contracting1012520210930-9Labourer - General - After Jan 1013780INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10125 | 20210930-9 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 39 | HR |  |  | 75 | 0 | 2925 | 380.25 | 3305.25 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C257-C267 | Hare Lake Road | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1012520210930-9Operator - Principle - After Jan 10392925 | Corbiere and Sons Contracting1012520210930-9Operator - Principle - After Jan 10392925INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10125 | 20210930-9 | 53510602 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C257-C267 | Hare Lake Road | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1012520210930-9L.O.A.4840 | Corbiere and Sons Contracting1012520210930-9L.O.A.4840INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10125 | 20210930-9 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 12 | Dynamic | 103.54 | 0 |  |  | 1656.6 | 215.358 | 1871.958 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C257-C267 | Hare Lake Road | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1012520210930-9Rock Truck - 30 Ton- After Jan 10121656.6 | Corbiere and Sons Contracting1012520210930-9Rock Truck - 30 Ton- After Jan 10121656.6INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10125 | 20210930-9 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C257-C267 | Hare Lake Road | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1012520210930-9Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting1012520210930-9Light Truck - Pick up- After Jan 103731.25INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10125 | 20210930-9 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 12 | HR | 9.16 | 0 |  |  | 146.52 | 19.0476 | 165.5676 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C257-C267 | Hare Lake Road | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1012520210930-9Excavator Thumb - 30 - 50 ton- After Jan 1012146.52 | Corbiere and Sons Contracting1012520210930-9Excavator Thumb - 30 - 50 ton- After Jan 1012146.52INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10125 | 20210930-9 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 24 | Dynamic | 103.84 | 0 |  |  | 3322.8 | 431.964 | 3754.764 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C257-C267 | Hare Lake Road | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1012520210930-9Excavator - 30 ton- After Jan 10243322.8 | Corbiere and Sons Contracting1012520210930-9Excavator - 30 ton- After Jan 10243322.8INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10124 | 20210930-8 | 53510602 | Access | 0 | Labourer - General - After Jan 10 | 60 | 12 | HR |  |  | 60 | 0 | 720 | 93.6 | 813.6 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-05 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1012420210930-8Labourer - General - After Jan 1012720 | Corbiere and Sons Contracting1012420210930-8Labourer - General - After Jan 1012720INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10124 | 20210930-8 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 60 | HR |  |  | 75 | 0 | 4500 | 585 | 5085 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-05 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1012420210930-8Operator - Principle - After Jan 10604500 | Corbiere and Sons Contracting1012420210930-8Operator - Principle - After Jan 10604500INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10124 | 20210930-8 | 53510602 | Access | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-05 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1012420210930-8L.O.A.61260 | Corbiere and Sons Contracting1012420210930-8L.O.A.61260INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10124 | 20210930-8 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 18 | Dynamic | 103.54 | 0 |  |  | 2484.9 | 323.037 | 2807.937 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-05 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1012420210930-8Rock Truck - 30 Ton- After Jan 10182484.9 | Corbiere and Sons Contracting1012420210930-8Rock Truck - 30 Ton- After Jan 10182484.9INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10124 | 20210930-8 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-05 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1012420210930-8Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting1012420210930-8Light Truck - Pick up- After Jan 103731.25INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10124 | 20210930-8 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-05 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1012420210930-8Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1012420210930-8Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10124 | 20210930-8 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-05 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1012420210930-8Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1012420210930-8Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10124 | 20210930-8 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-05 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1012420210930-8Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting1012420210930-8Excavator - 36 ton- After Jan 10111616.56INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10124 | 20210930-8 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-05 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1012420210930-8Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting1012420210930-8Excavator - 30 ton- After Jan 10111522.95INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10124 | 20210930-8 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-05 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1012420210930-8Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting1012420210930-8Dozer D6 or equal- After Jan 10111446.28INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10123 | 20210930-7-R1 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 48 | HR |  |  | 75 | 0 | 3600 | 468 | 4068 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1012320210930-7-R1Operator - Principle - After Jan 10483600 | Corbiere and Sons Contracting1012320210930-7-R1Operator - Principle - After Jan 10483600INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10123 | 20210930-7-R1 | 53510602 | Access | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1012320210930-7-R1L.O.A.51050 | Corbiere and Sons Contracting1012320210930-7-R1L.O.A.51050INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10123 | 20210930-7-R1 | 53510602 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1012320210930-7-R1Foreman121140 | Corbiere and Sons Contracting1012320210930-7-R1Foreman121140INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10123 | 20210930-7-R1 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1012320210930-7-R1Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting1012320210930-7-R1Rock Truck - 30 Ton- After Jan 10111518.55INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10123 | 20210930-7-R1 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1012320210930-7-R1Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting1012320210930-7-R1Light Truck - Pick up- After Jan 103731.25INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10123 | 20210930-7-R1 | 53510602 | Access | 0 | ATV - Side by Side w/ roll bar- After Jan 10 | 18.45 | 10 | HR | 13.84 | 0 |  |  | 184.5 | 23.985 | 208.485 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1012320210930-7-R1ATV - Side by Side w/ roll bar- After Jan 1010184.5 | Corbiere and Sons Contracting1012320210930-7-R1ATV - Side by Side w/ roll bar- After Jan 1010184.5INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10123 | 20210930-7-R1 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1012320210930-7-R1Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1012320210930-7-R1Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10123 | 20210930-7-R1 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1012320210930-7-R1Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting1012320210930-7-R1Excavator - 36 ton- After Jan 10111616.56INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10123 | 20210930-7-R1 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1012320210930-7-R1Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting1012320210930-7-R1Excavator - 30 ton- After Jan 10111522.95INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10123 | 20210930-7-R1 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1012320210930-7-R1Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting1012320210930-7-R1Dozer D6 or equal- After Jan 10111446.28INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10130 | 20210930-14 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 67 | HR |  |  | 75 | 0 | 5025 | 653.25 | 5678.25 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1013020210930-14Operator - Principle - After Jan 10675025 | Corbiere and Sons Contracting1013020210930-14Operator - Principle - After Jan 10675025INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10130 | 20210930-14 | 53510602 | Access | 0 | Foreman | 95 | 10 | HR |  |  | 95 | 0 | 950 | 123.5 | 1073.5 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1013020210930-14Foreman10950 | Corbiere and Sons Contracting1013020210930-14Foreman10950INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10130 | 20210930-14 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 22 | Dynamic | 103.54 | 0 |  |  | 3037.1 | 394.823 | 3431.923 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1013020210930-14Rock Truck - 30 Ton- After Jan 10223037.1 | Corbiere and Sons Contracting1013020210930-14Rock Truck - 30 Ton- After Jan 10223037.1INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10130 | 20210930-14 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 5 | DAY | 182.81 | 0 |  |  | 1218.75 | 158.4375 | 1377.1875 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1013020210930-14Light Truck - Pick up- After Jan 1051218.75 | Corbiere and Sons Contracting1013020210930-14Light Truck - Pick up- After Jan 1051218.75INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10130 | 20210930-14 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1013020210930-14Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1013020210930-14Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10130 | 20210930-14 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 9.16 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1013020210930-14Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting1013020210930-14Excavator Thumb - 30 - 50 ton- After Jan 1010122.1INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10130 | 20210930-14 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1013020210930-14Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1013020210930-14Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10130 | 20210930-14 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 7 | HR | 9.16 | 0 |  |  | 85.47 | 11.1111 | 96.5811 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1013020210930-14Excavator Thumb - 30 - 50 ton- After Jan 10785.47 | Corbiere and Sons Contracting1013020210930-14Excavator Thumb - 30 - 50 ton- After Jan 10785.47INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10130 | 20210930-14 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1013020210930-14Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting1013020210930-14Excavator - 36 ton- After Jan 10111616.56INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10130 | 20210930-14 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10 | Dynamic | 110.22 | 0 |  |  | 1469.6 | 191.048 | 1660.648 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1013020210930-14Excavator - 36 ton- After Jan 10101469.6 | Corbiere and Sons Contracting1013020210930-14Excavator - 36 ton- After Jan 10101469.6INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10130 | 20210930-14 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1013020210930-14Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting1013020210930-14Excavator - 36 ton- After Jan 10111616.56INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10130 | 20210930-14 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 7 | Dynamic | 103.84 | 0 |  |  | 969.15 | 125.9895 | 1095.1395 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1013020210930-14Excavator - 30 ton- After Jan 107969.15 | Corbiere and Sons Contracting1013020210930-14Excavator - 30 ton- After Jan 107969.15INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10129 | 20210930-13 | 53510602 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 12 | HR |  |  | 70 | 0 | 840 | 109.2 | 949.2 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acitivities from Mink Creek - Jeff did float moves. | 6 | C237-C247 | Mink Creek | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1012920210930-13Driver - AZ - After Jan 1012840 | Corbiere and Sons Contracting1012920210930-13Driver - AZ - After Jan 1012840INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10129 | 20210930-13 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 26 | HR |  |  | 75 | 0 | 1950 | 253.5 | 2203.5 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acitivities from Mink Creek - Jeff did float moves. | 6 | C237-C247 | Mink Creek | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1012920210930-13Operator - Principle - After Jan 10261950 | Corbiere and Sons Contracting1012920210930-13Operator - Principle - After Jan 10261950INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10129 | 20210930-13 | 53510602 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acitivities from Mink Creek - Jeff did float moves. | 6 | C237-C247 | Mink Creek | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1012920210930-13L.O.A.3630 | Corbiere and Sons Contracting1012920210930-13L.O.A.3630INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10129 | 20210930-13 | 53510602 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 12 | Dynamic | 91.79 | 0 |  |  | 1468.68 | 190.9284 | 1659.6084 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acitivities from Mink Creek - Jeff did float moves. | 6 | C237-C247 | Mink Creek | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1012920210930-13Tractor Trailer - 60 Ton- After Jan 10121468.68 | Corbiere and Sons Contracting1012920210930-13Tractor Trailer - 60 Ton- After Jan 10121468.68INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10129 | 20210930-13 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 12 | Dynamic | 103.54 | 0 |  |  | 1656.6 | 215.358 | 1871.958 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acitivities from Mink Creek - Jeff did float moves. | 6 | C237-C247 | Mink Creek | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1012920210930-13Rock Truck - 30 Ton- After Jan 10121656.6 | Corbiere and Sons Contracting1012920210930-13Rock Truck - 30 Ton- After Jan 10121656.6INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10129 | 20210930-13 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acitivities from Mink Creek - Jeff did float moves. | 6 | C237-C247 | Mink Creek | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1012920210930-13Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1012920210930-13Light Truck - Pick up- After Jan 101243.75INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10129 | 20210930-13 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 12 | HR | 9.16 | 0 |  |  | 146.52 | 19.0476 | 165.5676 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acitivities from Mink Creek - Jeff did float moves. | 6 | C237-C247 | Mink Creek | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1012920210930-13Excavator Thumb - 30 - 50 ton- After Jan 1012146.52 | Corbiere and Sons Contracting1012920210930-13Excavator Thumb - 30 - 50 ton- After Jan 1012146.52INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10129 | 20210930-13 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 12 | Dynamic | 110.22 | 0 |  |  | 1763.52 | 229.2576 | 1992.7776 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acitivities from Mink Creek - Jeff did float moves. | 6 | C237-C247 | Mink Creek | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1012920210930-13Excavator - 36 ton- After Jan 10121763.52 | Corbiere and Sons Contracting1012920210930-13Excavator - 36 ton- After Jan 10121763.52INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10128 | 20210930-12 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 39 | HR |  |  | 75 | 0 | 2925 | 380.25 | 3305.25 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1012820210930-12Operator - Principle - After Jan 10392925 | Corbiere and Sons Contracting1012820210930-12Operator - Principle - After Jan 10392925INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10128 | 20210930-12 | 53510602 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1012820210930-12L.O.A.4840 | Corbiere and Sons Contracting1012820210930-12L.O.A.4840INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10128 | 20210930-12 | 53510602 | Access | 0 | Foreman | 95 | 13 | HR |  |  | 95 | 0 | 1235 | 160.55 | 1395.55 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1012820210930-12Foreman131235 | Corbiere and Sons Contracting1012820210930-12Foreman131235INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10128 | 20210930-12 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1012820210930-12Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting1012820210930-12Rock Truck - 30 Ton- After Jan 10111518.55INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10128 | 20210930-12 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1012820210930-12Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting1012820210930-12Light Truck - Pick up- After Jan 102487.5INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10128 | 20210930-12 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1012820210930-12Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1012820210930-12Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10128 | 20210930-12 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1012820210930-12Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting1012820210930-12Excavator - 36 ton- After Jan 10111616.56INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10128 | 20210930-12 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1012820210930-12Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting1012820210930-12Dozer D6 or equal- After Jan 10111446.28INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10127 | 20210930-11 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 36 | HR |  |  | 75 | 0 | 2700 | 351 | 3051 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Pic | 6 | C215-C216 | Little Pic River | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1012720210930-11Operator - Principle - After Jan 10362700 | Corbiere and Sons Contracting1012720210930-11Operator - Principle - After Jan 10362700INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10127 | 20210930-11 | 53510602 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Pic | 6 | C215-C216 | Little Pic River | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1012720210930-11L.O.A.3630 | Corbiere and Sons Contracting1012720210930-11L.O.A.3630INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10127 | 20210930-11 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Pic | 6 | C215-C216 | Little Pic River | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1012720210930-11Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting1012720210930-11Rock Truck - 30 Ton- After Jan 10111518.55INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10127 | 20210930-11 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Pic | 6 | C215-C216 | Little Pic River | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1012720210930-11Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting1012720210930-11Light Truck - Pick up- After Jan 102487.5INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10127 | 20210930-11 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Pic | 6 | C215-C216 | Little Pic River | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1012720210930-11Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting1012720210930-11Excavator - 36 ton- After Jan 10111616.56INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10127 | 20210930-11 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Pic | 6 | C215-C216 | Little Pic River | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1012720210930-11Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting1012720210930-11Dozer D6 or equal- After Jan 10111446.28INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10126 | 20210930-10 | 53510602 | Access | 0 | Labourer - General - After Jan 10 | 60 | 13 | HR |  |  | 60 | 0 | 780 | 101.4 | 881.4 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1012620210930-10Labourer - General - After Jan 1013780 | Corbiere and Sons Contracting1012620210930-10Labourer - General - After Jan 1013780INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10126 | 20210930-10 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 78 | HR |  |  | 75 | 0 | 5850 | 760.5 | 6610.5 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1012620210930-10Operator - Principle - After Jan 10785850 | Corbiere and Sons Contracting1012620210930-10Operator - Principle - After Jan 10785850INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10126 | 20210930-10 | 53510602 | Access | 0 | L.O.A. | 210 | 8 | DAY |  |  |  | 0 | 1680 | 218.4 | 1898.4 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1012620210930-10L.O.A.81680 | Corbiere and Sons Contracting1012620210930-10L.O.A.81680INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10126 | 20210930-10 | 53510602 | Access | 0 | Foreman | 95 | 13 | HR |  |  | 95 | 0 | 1235 | 160.55 | 1395.55 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1012620210930-10Foreman131235 | Corbiere and Sons Contracting1012620210930-10Foreman131235INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10126 | 20210930-10 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 12 | Dynamic | 103.54 | 0 |  |  | 1656.6 | 215.358 | 1871.958 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1012620210930-10Rock Truck - 30 Ton- After Jan 10121656.6 | Corbiere and Sons Contracting1012620210930-10Rock Truck - 30 Ton- After Jan 10121656.6INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10126 | 20210930-10 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 4 | DAY | 182.81 | 0 |  |  | 975 | 126.75 | 1101.75 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1012620210930-10Light Truck - Pick up- After Jan 104975 | Corbiere and Sons Contracting1012620210930-10Light Truck - Pick up- After Jan 104975INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10126 | 20210930-10 | 53510602 | Access | 0 | ATV - Side by Side w/ roll bar- After Jan 10 | 18.45 | 10 | HR | 13.84 | 0 |  |  | 184.5 | 23.985 | 208.485 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1012620210930-10ATV - Side by Side w/ roll bar- After Jan 1010184.5 | Corbiere and Sons Contracting1012620210930-10ATV - Side by Side w/ roll bar- After Jan 1010184.5INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10126 | 20210930-10 | 53510602 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 12 | HR | 47.54 | 0 |  |  | 760.56 | 98.8728 | 859.4328 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1012620210930-10Excavator Hammer - 30 - 50 ton- After Jan 1012760.56 | Corbiere and Sons Contracting1012620210930-10Excavator Hammer - 30 - 50 ton- After Jan 1012760.56INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10126 | 20210930-10 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 24 | HR | 9.16 | 0 |  |  | 293.04 | 38.0952 | 331.1352 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1012620210930-10Excavator Thumb - 30 - 50 ton- After Jan 1024293.04 | Corbiere and Sons Contracting1012620210930-10Excavator Thumb - 30 - 50 ton- After Jan 1024293.04INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10126 | 20210930-10 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 48 | Dynamic | 110.22 | 0 |  |  | 7054.08 | 917.0304 | 7971.1104 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1012620210930-10Excavator - 36 ton- After Jan 10487054.08 | Corbiere and Sons Contracting1012620210930-10Excavator - 36 ton- After Jan 10487054.08INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10126 | 20210930-10 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 12 | Dynamic | 98.61 | 0 |  |  | 1577.76 | 205.1088 | 1782.8688 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1012620210930-10Dozer D6 or equal- After Jan 10121577.76 | Corbiere and Sons Contracting1012620210930-10Dozer D6 or equal- After Jan 10121577.76INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10109 | 20210929-9 | 53510602 | Access | 0 | Labourer - General - After Jan 10 | 60 | 12 | HR |  |  | 60 | 0 | 720 | 93.6 | 813.6 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C257-C267 | Hare Lake Road | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1010920210929-9Labourer - General - After Jan 1012720 | Corbiere and Sons Contracting1010920210929-9Labourer - General - After Jan 1012720INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10109 | 20210929-9 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 36 | HR |  |  | 75 | 0 | 2700 | 351 | 3051 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C257-C267 | Hare Lake Road | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1010920210929-9Operator - Principle - After Jan 10362700 | Corbiere and Sons Contracting1010920210929-9Operator - Principle - After Jan 10362700INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10109 | 20210929-9 | 53510602 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C257-C267 | Hare Lake Road | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1010920210929-9L.O.A.4840 | Corbiere and Sons Contracting1010920210929-9L.O.A.4840INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10109 | 20210929-9 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C257-C267 | Hare Lake Road | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1010920210929-9Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting1010920210929-9Rock Truck - 30 Ton- After Jan 10111518.55INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10109 | 20210929-9 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C257-C267 | Hare Lake Road | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1010920210929-9Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting1010920210929-9Light Truck - Pick up- After Jan 103731.25INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10109 | 20210929-9 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C257-C267 | Hare Lake Road | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1010920210929-9Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1010920210929-9Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10109 | 20210929-9 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C257-C267 | Hare Lake Road | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1010920210929-9Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting1010920210929-9Excavator - 30 ton- After Jan 10111522.95INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10109 | 20210929-9 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C257-C267 | Hare Lake Road | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1010920210929-9Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting1010920210929-9Excavator - 30 ton- After Jan 10111522.95INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10108 | 20210929-8-R1 | 53510602 | Access | 0 | Labourer - General - After Jan 10 | 60 | 12 | HR |  |  | 60 | 0 | 720 | 93.6 | 813.6 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1010820210929-8-R1Labourer - General - After Jan 1012720 | Corbiere and Sons Contracting1010820210929-8-R1Labourer - General - After Jan 1012720INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10108 | 20210929-8-R1 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 72 | HR |  |  | 75 | 0 | 5400 | 702 | 6102 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1010820210929-8-R1Operator - Principle - After Jan 10725400 | Corbiere and Sons Contracting1010820210929-8-R1Operator - Principle - After Jan 10725400INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10108 | 20210929-8-R1 | 53510602 | Access | 0 | L.O.A. | 210 | 8 | DAY |  |  |  | 0 | 1680 | 218.4 | 1898.4 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1010820210929-8-R1L.O.A.81680 | Corbiere and Sons Contracting1010820210929-8-R1L.O.A.81680INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10108 | 20210929-8-R1 | 53510602 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1010820210929-8-R1Foreman121140 | Corbiere and Sons Contracting1010820210929-8-R1Foreman121140INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10108 | 20210929-8-R1 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 29 | Dynamic | 103.54 | 0 |  |  | 4003.45 | 520.4485 | 4523.8985 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1010820210929-8-R1Rock Truck - 30 Ton- After Jan 10294003.45 | Corbiere and Sons Contracting1010820210929-8-R1Rock Truck - 30 Ton- After Jan 10294003.45INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10108 | 20210929-8-R1 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 4 | DAY | 182.81 | 0 |  |  | 975 | 126.75 | 1101.75 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1010820210929-8-R1Light Truck - Pick up- After Jan 104975 | Corbiere and Sons Contracting1010820210929-8-R1Light Truck - Pick up- After Jan 104975INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10108 | 20210929-8-R1 | 53510602 | Access | 0 | ATV - Side by Side w/ roll bar- After Jan 10 | 18.45 | 10 | HR | 13.84 | 0 |  |  | 184.5 | 23.985 | 208.485 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1010820210929-8-R1ATV - Side by Side w/ roll bar- After Jan 1010184.5 | Corbiere and Sons Contracting1010820210929-8-R1ATV - Side by Side w/ roll bar- After Jan 1010184.5INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10108 | 20210929-8-R1 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1010820210929-8-R1Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1010820210929-8-R1Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10108 | 20210929-8-R1 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1010820210929-8-R1Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1010820210929-8-R1Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10108 | 20210929-8-R1 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1010820210929-8-R1Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting1010820210929-8-R1Excavator - 36 ton- After Jan 10111616.56INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10108 | 20210929-8-R1 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1010820210929-8-R1Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting1010820210929-8-R1Excavator - 30 ton- After Jan 10111522.95INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10108 | 20210929-8-R1 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1010820210929-8-R1Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting1010820210929-8-R1Dozer D6 or equal- After Jan 10111446.28INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10106 | 20210929-7 | 53510602 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 22 | HR |  |  | 70 | 0 | 1540 | 200.2 | 1740.2 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1010620210929-7Driver - AZ - After Jan 10221540 | Corbiere and Sons Contracting1010620210929-7Driver - AZ - After Jan 10221540INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10106 | 20210929-7 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 48 | HR |  |  | 75 | 0 | 3600 | 468 | 4068 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1010620210929-7Operator - Principle - After Jan 10483600 | Corbiere and Sons Contracting1010620210929-7Operator - Principle - After Jan 10483600INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10106 | 20210929-7 | 53510602 | Access | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1010620210929-7L.O.A.51050 | Corbiere and Sons Contracting1010620210929-7L.O.A.51050INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10106 | 20210929-7 | 53510602 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 22 | Dynamic | 91.79 | 0 |  |  | 2692.58 | 350.0354 | 3042.6154 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1010620210929-7Tractor Trailer - 60 Ton- After Jan 10222692.58 | Corbiere and Sons Contracting1010620210929-7Tractor Trailer - 60 Ton- After Jan 10222692.58INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10106 | 20210929-7 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 10 | Dynamic | 103.54 | 0 |  |  | 1380.5 | 179.465 | 1559.965 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1010620210929-7Rock Truck - 30 Ton- After Jan 10101380.5 | Corbiere and Sons Contracting1010620210929-7Rock Truck - 30 Ton- After Jan 10101380.5INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10106 | 20210929-7 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1010620210929-7Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting1010620210929-7Light Truck - Pick up- After Jan 102487.5INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10106 | 20210929-7 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1010620210929-7Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1010620210929-7Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10106 | 20210929-7 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1010620210929-7Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting1010620210929-7Excavator - 36 ton- After Jan 10111616.56INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10106 | 20210929-7 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1010620210929-7Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting1010620210929-7Excavator - 30 ton- After Jan 10111522.95INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10106 | 20210929-7 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1010620210929-7Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting1010620210929-7Dozer D6 or equal- After Jan 10111446.28INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10117 | 20210929-17 | 53510602 | Access | 0 | Driver - Other - After Jan 10 | 60 | 16 | HR |  |  | 60 | 0 | 960 | 124.8 | 1084.8 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Mobilization and demobilization of pickups | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1011720210929-17Driver - Other - After Jan 1016960 | Corbiere and Sons Contracting1011720210929-17Driver - Other - After Jan 1016960INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10117 | 20210929-17 | 53510602 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Mobilization and demobilization of pickups | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1011720210929-17L.O.A.2420 | Corbiere and Sons Contracting1011720210929-17L.O.A.2420INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10117 | 20210929-17 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Mobilization and demobilization of pickups | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1011720210929-17Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting1011720210929-17Light Truck - Pick up- After Jan 102487.5INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10115 | 20210929-15 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 60 | HR |  |  | 75 | 0 | 4500 | 585 | 5085 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1011520210929-15Operator - Principle - After Jan 10604500 | Corbiere and Sons Contracting1011520210929-15Operator - Principle - After Jan 10604500INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10115 | 20210929-15 | 53510602 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1011520210929-15Foreman121140 | Corbiere and Sons Contracting1011520210929-15Foreman121140INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10115 | 20210929-15 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 22 | Dynamic | 103.54 | 0 |  |  | 3037.1 | 394.823 | 3431.923 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1011520210929-15Rock Truck - 30 Ton- After Jan 10223037.1 | Corbiere and Sons Contracting1011520210929-15Rock Truck - 30 Ton- After Jan 10223037.1INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10115 | 20210929-15 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 4 | DAY | 182.81 | 0 |  |  | 975 | 126.75 | 1101.75 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1011520210929-15Light Truck - Pick up- After Jan 104975 | Corbiere and Sons Contracting1011520210929-15Light Truck - Pick up- After Jan 104975INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10115 | 20210929-15 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1011520210929-15Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1011520210929-15Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10115 | 20210929-15 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1011520210929-15Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1011520210929-15Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10115 | 20210929-15 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1011520210929-15Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1011520210929-15Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10115 | 20210929-15 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1011520210929-15Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1011520210929-15Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10115 | 20210929-15 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1011520210929-15Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting1011520210929-15Excavator - 36 ton- After Jan 10111616.56INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10115 | 20210929-15 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1011520210929-15Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting1011520210929-15Excavator - 36 ton- After Jan 10111616.56INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10115 | 20210929-15 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1011520210929-15Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting1011520210929-15Excavator - 36 ton- After Jan 10111616.56INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10115 | 20210929-15 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1011520210929-15Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting1011520210929-15Excavator - 30 ton- After Jan 10111522.95INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10114 | 20210929-14 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acitivities from Mink Creek | 6 | C237-C247 | Mink | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1011420210929-14Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1011420210929-14Operator - Principle - After Jan 1012900INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10114 | 20210929-14 | 53510602 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acitivities from Mink Creek | 6 | C237-C247 | Mink | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1011420210929-14L.O.A.1210 | Corbiere and Sons Contracting1011420210929-14L.O.A.1210INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10114 | 20210929-14 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acitivities from Mink Creek | 6 | C237-C247 | Mink | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1011420210929-14Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1011420210929-14Light Truck - Pick up- After Jan 101243.75INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10114 | 20210929-14 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acitivities from Mink Creek | 6 | C237-C247 | Mink | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1011420210929-14Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1011420210929-14Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10114 | 20210929-14 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acitivities from Mink Creek | 6 | C237-C247 | Mink | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1011420210929-14Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting1011420210929-14Excavator - 36 ton- After Jan 10111616.56INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10113 | 20210929-13 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 31.5 | HR |  |  | 75 | 0 | 2362.5 | 307.125 | 2669.625 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Lake | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1011320210929-13Operator - Principle - After Jan 1031.52362.5 | Corbiere and Sons Contracting1011320210929-13Operator - Principle - After Jan 1031.52362.5INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10113 | 20210929-13 | 53510602 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Lake | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1011320210929-13L.O.A.4840 | Corbiere and Sons Contracting1011320210929-13L.O.A.4840INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10113 | 20210929-13 | 53510602 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Lake | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1011320210929-13Foreman121140 | Corbiere and Sons Contracting1011320210929-13Foreman121140INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10113 | 20210929-13 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 9.5 | Dynamic | 103.54 | 0 |  |  | 1311.475 | 170.4917 | 1481.9668 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Lake | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1011320210929-13Rock Truck - 30 Ton- After Jan 109.51311.475 | Corbiere and Sons Contracting1011320210929-13Rock Truck - 30 Ton- After Jan 109.51311.475INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10113 | 20210929-13 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Lake | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1011320210929-13Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting1011320210929-13Light Truck - Pick up- After Jan 102487.5INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10113 | 20210929-13 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9.5 | HR | 9.16 | 0 |  |  | 115.995 | 15.0793 | 131.0744 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Lake | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1011320210929-13Excavator Thumb - 30 - 50 ton- After Jan 109.5115.995 | Corbiere and Sons Contracting1011320210929-13Excavator Thumb - 30 - 50 ton- After Jan 109.5115.995INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10113 | 20210929-13 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9.5 | Dynamic | 110.22 | 0 |  |  | 1396.12 | 181.4956 | 1577.6156 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Lake | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1011320210929-13Excavator - 36 ton- After Jan 109.51396.12 | Corbiere and Sons Contracting1011320210929-13Excavator - 36 ton- After Jan 109.51396.12INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10113 | 20210929-13 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 9.5 | Dynamic | 98.61 | 0 |  |  | 1249.06 | 162.3778 | 1411.4378 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Lake | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1011320210929-13Dozer D6 or equal- After Jan 109.51249.06 | Corbiere and Sons Contracting1011320210929-13Dozer D6 or equal- After Jan 109.51249.06INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10112 | 20210929-12 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 36 | HR |  |  | 75 | 0 | 2700 | 351 | 3051 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Pic | 6 | C215-C216 | Little Pic River | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1011220210929-12Operator - Principle - After Jan 10362700 | Corbiere and Sons Contracting1011220210929-12Operator - Principle - After Jan 10362700INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10112 | 20210929-12 | 53510602 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Pic | 6 | C215-C216 | Little Pic River | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1011220210929-12L.O.A.3630 | Corbiere and Sons Contracting1011220210929-12L.O.A.3630INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10112 | 20210929-12 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Pic | 6 | C215-C216 | Little Pic River | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1011220210929-12Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting1011220210929-12Rock Truck - 30 Ton- After Jan 10111518.55INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10112 | 20210929-12 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Pic | 6 | C215-C216 | Little Pic River | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1011220210929-12Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting1011220210929-12Light Truck - Pick up- After Jan 102487.5INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10112 | 20210929-12 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Pic | 6 | C215-C216 | Little Pic River | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1011220210929-12Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting1011220210929-12Excavator - 36 ton- After Jan 10111616.56INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10112 | 20210929-12 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Pic | 6 | C215-C216 | Little Pic River | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1011220210929-12Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting1011220210929-12Dozer D6 or equal- After Jan 10111446.28INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10110 | 20210929-10 | 53510602 | Access | 0 | Labourer - General - After Jan 10 | 60 | 12 | HR |  |  | 60 | 0 | 720 | 93.6 | 813.6 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-05 |  | 37 | 2021-10-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1011020210929-10Labourer - General - After Jan 1012720 | Corbiere and Sons Contracting1011020210929-10Labourer - General - After Jan 1012720INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10110 | 20210929-10 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 60 | HR |  |  | 75 | 0 | 4500 | 585 | 5085 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-05 |  | 37 | 2021-10-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1011020210929-10Operator - Principle - After Jan 10604500 | Corbiere and Sons Contracting1011020210929-10Operator - Principle - After Jan 10604500INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10110 | 20210929-10 | 53510602 | Access | 0 | L.O.A. | 210 | 7 | DAY |  |  |  | 0 | 1470 | 191.1 | 1661.1 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-05 |  | 37 | 2021-10-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1011020210929-10L.O.A.71470 | Corbiere and Sons Contracting1011020210929-10L.O.A.71470INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10110 | 20210929-10 | 53510602 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-05 |  | 37 | 2021-10-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1011020210929-10Foreman121140 | Corbiere and Sons Contracting1011020210929-10Foreman121140INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10110 | 20210929-10 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-05 |  | 37 | 2021-10-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1011020210929-10Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting1011020210929-10Rock Truck - 30 Ton- After Jan 10111518.55INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10110 | 20210929-10 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-05 |  | 37 | 2021-10-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1011020210929-10Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting1011020210929-10Light Truck - Pick up- After Jan 103731.25INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10110 | 20210929-10 | 53510602 | Access | 0 | ATV - Side by Side w/ roll bar- After Jan 10 | 18.45 | 10 | HR | 13.84 | 0 |  |  | 184.5 | 23.985 | 208.485 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-05 |  | 37 | 2021-10-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1011020210929-10ATV - Side by Side w/ roll bar- After Jan 1010184.5 | Corbiere and Sons Contracting1011020210929-10ATV - Side by Side w/ roll bar- After Jan 1010184.5INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10110 | 20210929-10 | 53510602 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 11 | HR | 47.54 | 0 |  |  | 697.18 | 90.6334 | 787.8134 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-05 |  | 37 | 2021-10-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1011020210929-10Excavator Hammer - 30 - 50 ton- After Jan 1011697.18 | Corbiere and Sons Contracting1011020210929-10Excavator Hammer - 30 - 50 ton- After Jan 1011697.18INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10110 | 20210929-10 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 22 | Dynamic | 110.22 | 0 |  |  | 3233.12 | 420.3056 | 3653.4256 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-05 |  | 37 | 2021-10-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1011020210929-10Excavator - 36 ton- After Jan 10223233.12 | Corbiere and Sons Contracting1011020210929-10Excavator - 36 ton- After Jan 10223233.12INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10110 | 20210929-10 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-05 |  | 37 | 2021-10-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1011020210929-10Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting1011020210929-10Excavator - 30 ton- After Jan 10111522.95INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10110 | 20210929-10 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-05 |  | 37 | 2021-10-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1011020210929-10Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting1011020210929-10Dozer D6 or equal- After Jan 10111446.28INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10094 | 20210928-9 | 53510602 | Access | 0 | Labourer - General - After Jan 10 | 60 | 12 | HR |  |  | 60 | 0 | 720 | 93.6 | 813.6 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C257-C267 | Hare Lake | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1009420210928-9Labourer - General - After Jan 1012720 | Corbiere and Sons Contracting1009420210928-9Labourer - General - After Jan 1012720INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10094 | 20210928-9 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 36 | HR |  |  | 75 | 0 | 2700 | 351 | 3051 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C257-C267 | Hare Lake | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1009420210928-9Operator - Principle - After Jan 10362700 | Corbiere and Sons Contracting1009420210928-9Operator - Principle - After Jan 10362700INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10094 | 20210928-9 | 53510602 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C257-C267 | Hare Lake | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1009420210928-9L.O.A.4840 | Corbiere and Sons Contracting1009420210928-9L.O.A.4840INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10094 | 20210928-9 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C257-C267 | Hare Lake | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1009420210928-9Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting1009420210928-9Rock Truck - 30 Ton- After Jan 10111518.55INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10094 | 20210928-9 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C257-C267 | Hare Lake | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1009420210928-9Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting1009420210928-9Light Truck - Pick up- After Jan 103731.25INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10094 | 20210928-9 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C257-C267 | Hare Lake | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1009420210928-9Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1009420210928-9Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10094 | 20210928-9 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C257-C267 | Hare Lake | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1009420210928-9Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting1009420210928-9Excavator - 30 ton- After Jan 10111522.95INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10094 | 20210928-9 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C257-C267 | Hare Lake | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1009420210928-9Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting1009420210928-9Excavator - 30 ton- After Jan 10111522.95INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10093 | 20210928-8 | 53510602 | Access | 0 | Labourer - General - After Jan 10 | 60 | 12 | HR |  |  | 60 | 0 | 720 | 93.6 | 813.6 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1009320210928-8Labourer - General - After Jan 1012720 | Corbiere and Sons Contracting1009320210928-8Labourer - General - After Jan 1012720INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10093 | 20210928-8 | 53510602 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 12 | HR |  |  | 70 | 0 | 840 | 109.2 | 949.2 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1009320210928-8Driver - AZ - After Jan 1012840 | Corbiere and Sons Contracting1009320210928-8Driver - AZ - After Jan 1012840INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10093 | 20210928-8 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 72 | HR |  |  | 75 | 0 | 5400 | 702 | 6102 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1009320210928-8Operator - Principle - After Jan 10725400 | Corbiere and Sons Contracting1009320210928-8Operator - Principle - After Jan 10725400INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10093 | 20210928-8 | 53510602 | Access | 0 | L.O.A. | 210 | 9 | DAY |  |  |  | 0 | 1890 | 245.7 | 2135.7 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1009320210928-8L.O.A.91890 | Corbiere and Sons Contracting1009320210928-8L.O.A.91890INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10093 | 20210928-8 | 53510602 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1009320210928-8Foreman121140 | Corbiere and Sons Contracting1009320210928-8Foreman121140INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10093 | 20210928-8 | 53510602 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 12 | Dynamic | 91.79 | 0 |  |  | 1468.68 | 190.9284 | 1659.6084 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1009320210928-8Tractor Trailer - 60 Ton- After Jan 10121468.68 | Corbiere and Sons Contracting1009320210928-8Tractor Trailer - 60 Ton- After Jan 10121468.68INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10093 | 20210928-8 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 33 | Dynamic | 103.54 | 0 |  |  | 4555.65 | 592.2345 | 5147.8845 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1009320210928-8Rock Truck - 30 Ton- After Jan 10334555.65 | Corbiere and Sons Contracting1009320210928-8Rock Truck - 30 Ton- After Jan 10334555.65INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10093 | 20210928-8 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 4 | DAY | 182.81 | 0 |  |  | 975 | 126.75 | 1101.75 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1009320210928-8Light Truck - Pick up- After Jan 104975 | Corbiere and Sons Contracting1009320210928-8Light Truck - Pick up- After Jan 104975INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10093 | 20210928-8 | 53510602 | Access | 0 | ATV - Side by Side w/ roll bar- After Jan 10 | 18.45 | 10 | HR | 13.84 | 0 |  |  | 184.5 | 23.985 | 208.485 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1009320210928-8ATV - Side by Side w/ roll bar- After Jan 1010184.5 | Corbiere and Sons Contracting1009320210928-8ATV - Side by Side w/ roll bar- After Jan 1010184.5INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10093 | 20210928-8 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1009320210928-8Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1009320210928-8Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10093 | 20210928-8 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1009320210928-8Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1009320210928-8Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10093 | 20210928-8 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1009320210928-8Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting1009320210928-8Excavator - 36 ton- After Jan 10111616.56INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10093 | 20210928-8 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1009320210928-8Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting1009320210928-8Excavator - 30 ton- After Jan 10111522.95INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10093 | 20210928-8 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1009320210928-8Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting1009320210928-8Dozer D6 or equal- After Jan 10111446.28INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10092 | 20210928-7 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 48 | HR |  |  | 75 | 0 | 3600 | 468 | 4068 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1009220210928-7Operator - Principle - After Jan 10483600 | Corbiere and Sons Contracting1009220210928-7Operator - Principle - After Jan 10483600INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10092 | 20210928-7 | 53510602 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1009220210928-7L.O.A.4840 | Corbiere and Sons Contracting1009220210928-7L.O.A.4840INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10092 | 20210928-7 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 10 | Dynamic | 103.54 | 0 |  |  | 1380.5 | 179.465 | 1559.965 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1009220210928-7Rock Truck - 30 Ton- After Jan 10101380.5 | Corbiere and Sons Contracting1009220210928-7Rock Truck - 30 Ton- After Jan 10101380.5INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10092 | 20210928-7 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1009220210928-7Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting1009220210928-7Light Truck - Pick up- After Jan 102487.5INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10092 | 20210928-7 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1009220210928-7Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1009220210928-7Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10092 | 20210928-7 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1009220210928-7Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting1009220210928-7Excavator - 36 ton- After Jan 10111616.56INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10092 | 20210928-7 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1009220210928-7Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting1009220210928-7Excavator - 30 ton- After Jan 10111522.95INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10092 | 20210928-7 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1009220210928-7Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting1009220210928-7Dozer D6 or equal- After Jan 10111446.28INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10100 | 20210928-15 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 72 | HR |  |  | 75 | 0 | 5400 | 702 | 6102 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-05 |  | 37 | 2021-10-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1010020210928-15Operator - Principle - After Jan 10725400 | Corbiere and Sons Contracting1010020210928-15Operator - Principle - After Jan 10725400INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10100 | 20210928-15 | 53510602 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-05 |  | 37 | 2021-10-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1010020210928-15Foreman121140 | Corbiere and Sons Contracting1010020210928-15Foreman121140INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10100 | 20210928-15 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 22 | Dynamic | 103.54 | 0 |  |  | 3037.1 | 394.823 | 3431.923 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-05 |  | 37 | 2021-10-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1010020210928-15Rock Truck - 30 Ton- After Jan 10223037.1 | Corbiere and Sons Contracting1010020210928-15Rock Truck - 30 Ton- After Jan 10223037.1INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10100 | 20210928-15 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 5 | DAY | 182.81 | 0 |  |  | 1218.75 | 158.4375 | 1377.1875 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-05 |  | 37 | 2021-10-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1010020210928-15Light Truck - Pick up- After Jan 1051218.75 | Corbiere and Sons Contracting1010020210928-15Light Truck - Pick up- After Jan 1051218.75INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10100 | 20210928-15 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-05 |  | 37 | 2021-10-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1010020210928-15Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1010020210928-15Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10100 | 20210928-15 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-05 |  | 37 | 2021-10-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1010020210928-15Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1010020210928-15Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10100 | 20210928-15 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-05 |  | 37 | 2021-10-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1010020210928-15Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1010020210928-15Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10100 | 20210928-15 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-05 |  | 37 | 2021-10-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1010020210928-15Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1010020210928-15Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10100 | 20210928-15 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-05 |  | 37 | 2021-10-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1010020210928-15Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting1010020210928-15Excavator - 36 ton- After Jan 10111616.56INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10100 | 20210928-15 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-05 |  | 37 | 2021-10-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1010020210928-15Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting1010020210928-15Excavator - 36 ton- After Jan 10111616.56INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10100 | 20210928-15 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-05 |  | 37 | 2021-10-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1010020210928-15Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting1010020210928-15Excavator - 36 ton- After Jan 10111616.56INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10100 | 20210928-15 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-05 |  | 37 | 2021-10-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1010020210928-15Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting1010020210928-15Excavator - 30 ton- After Jan 10111522.95INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10098 | 20210928-13 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 8 | HR |  |  | 75 | 0 | 600 | 78 | 678 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acvitites on Mink Creek - Leslie was floated over to get started | 6 | C237-C247 | Mink Creek | 0 | 2021-10-05 |  | 37 | 2021-10-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1009820210928-13Operator - Principle - After Jan 108600 | Corbiere and Sons Contracting1009820210928-13Operator - Principle - After Jan 108600INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10098 | 20210928-13 | 53510602 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acvitites on Mink Creek - Leslie was floated over to get started | 6 | C237-C247 | Mink Creek | 0 | 2021-10-05 |  | 37 | 2021-10-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1009820210928-13L.O.A.1210 | Corbiere and Sons Contracting1009820210928-13L.O.A.1210INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10098 | 20210928-13 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acvitites on Mink Creek - Leslie was floated over to get started | 6 | C237-C247 | Mink Creek | 0 | 2021-10-05 |  | 37 | 2021-10-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1009820210928-13Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1009820210928-13Light Truck - Pick up- After Jan 101243.75INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10098 | 20210928-13 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 6.5 | HR | 9.16 | 0 |  |  | 79.365 | 10.3174 | 89.6825 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acvitites on Mink Creek - Leslie was floated over to get started | 6 | C237-C247 | Mink Creek | 0 | 2021-10-05 |  | 37 | 2021-10-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1009820210928-13Excavator Thumb - 30 - 50 ton- After Jan 106.579.365 | Corbiere and Sons Contracting1009820210928-13Excavator Thumb - 30 - 50 ton- After Jan 106.579.365INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10098 | 20210928-13 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 6.5 | Dynamic | 110.22 | 0 |  |  | 955.24 | 124.1812 | 1079.4212 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acvitites on Mink Creek - Leslie was floated over to get started | 6 | C237-C247 | Mink Creek | 0 | 2021-10-05 |  | 37 | 2021-10-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1009820210928-13Excavator - 36 ton- After Jan 106.5955.24 | Corbiere and Sons Contracting1009820210928-13Excavator - 36 ton- After Jan 106.5955.24INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10097 | 20210928-12 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 36 | HR |  |  | 75 | 0 | 2700 | 351 | 3051 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Lake | 0 | 2021-10-05 |  | 37 | 2021-10-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1009720210928-12Operator - Principle - After Jan 10362700 | Corbiere and Sons Contracting1009720210928-12Operator - Principle - After Jan 10362700INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10097 | 20210928-12 | 53510602 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Lake | 0 | 2021-10-05 |  | 37 | 2021-10-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1009720210928-12L.O.A.3630 | Corbiere and Sons Contracting1009720210928-12L.O.A.3630INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10097 | 20210928-12 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Lake | 0 | 2021-10-05 |  | 37 | 2021-10-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1009720210928-12Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting1009720210928-12Rock Truck - 30 Ton- After Jan 10111518.55INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10097 | 20210928-12 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Lake | 0 | 2021-10-05 |  | 37 | 2021-10-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1009720210928-12Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1009720210928-12Light Truck - Pick up- After Jan 101243.75INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10097 | 20210928-12 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Lake | 0 | 2021-10-05 |  | 37 | 2021-10-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1009720210928-12Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1009720210928-12Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10097 | 20210928-12 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Lake | 0 | 2021-10-05 |  | 37 | 2021-10-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1009720210928-12Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting1009720210928-12Excavator - 36 ton- After Jan 10111616.56INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10097 | 20210928-12 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Lake | 0 | 2021-10-05 |  | 37 | 2021-10-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1009720210928-12Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting1009720210928-12Dozer D6 or equal- After Jan 10111446.28INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10096 | 20210928-11 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 36 | HR |  |  | 75 | 0 | 2700 | 351 | 3051 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Crew floated from Middleton and getting started at this site - | 6 | C215-C216 | Little Pic River | 0 | 2021-10-05 |  | 37 | 2021-10-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1009620210928-11Operator - Principle - After Jan 10362700 | Corbiere and Sons Contracting1009620210928-11Operator - Principle - After Jan 10362700INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10096 | 20210928-11 | 53510602 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Crew floated from Middleton and getting started at this site - | 6 | C215-C216 | Little Pic River | 0 | 2021-10-05 |  | 37 | 2021-10-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1009620210928-11L.O.A.3630 | Corbiere and Sons Contracting1009620210928-11L.O.A.3630INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10096 | 20210928-11 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Crew floated from Middleton and getting started at this site - | 6 | C215-C216 | Little Pic River | 0 | 2021-10-05 |  | 37 | 2021-10-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1009620210928-11Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting1009620210928-11Rock Truck - 30 Ton- After Jan 10111518.55INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10096 | 20210928-11 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Crew floated from Middleton and getting started at this site - | 6 | C215-C216 | Little Pic River | 0 | 2021-10-05 |  | 37 | 2021-10-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1009620210928-11Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting1009620210928-11Light Truck - Pick up- After Jan 102487.5INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10096 | 20210928-11 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Crew floated from Middleton and getting started at this site - | 6 | C215-C216 | Little Pic River | 0 | 2021-10-05 |  | 37 | 2021-10-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1009620210928-11Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting1009620210928-11Excavator - 36 ton- After Jan 10111616.56INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10096 | 20210928-11 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Crew floated from Middleton and getting started at this site - | 6 | C215-C216 | Little Pic River | 0 | 2021-10-05 |  | 37 | 2021-10-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1009620210928-11Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting1009620210928-11Dozer D6 or equal- After Jan 10111446.28INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10095 | 20210928-10 | 53510602 | Access | 0 | Labourer - General - After Jan 10 | 60 | 12 | HR |  |  | 60 | 0 | 720 | 93.6 | 813.6 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-05 |  | 37 | 2021-10-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1009520210928-10Labourer - General - After Jan 1012720 | Corbiere and Sons Contracting1009520210928-10Labourer - General - After Jan 1012720INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10095 | 20210928-10 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 60 | HR |  |  | 75 | 0 | 4500 | 585 | 5085 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-05 |  | 37 | 2021-10-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1009520210928-10Operator - Principle - After Jan 10604500 | Corbiere and Sons Contracting1009520210928-10Operator - Principle - After Jan 10604500INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10095 | 20210928-10 | 53510602 | Access | 0 | L.O.A. | 210 | 7 | DAY |  |  |  | 0 | 1470 | 191.1 | 1661.1 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-05 |  | 37 | 2021-10-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1009520210928-10L.O.A.71470 | Corbiere and Sons Contracting1009520210928-10L.O.A.71470INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10095 | 20210928-10 | 53510602 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-05 |  | 37 | 2021-10-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1009520210928-10Foreman121140 | Corbiere and Sons Contracting1009520210928-10Foreman121140INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10095 | 20210928-10 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-05 |  | 37 | 2021-10-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1009520210928-10Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting1009520210928-10Rock Truck - 30 Ton- After Jan 10111518.55INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10095 | 20210928-10 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-05 |  | 37 | 2021-10-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1009520210928-10Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting1009520210928-10Light Truck - Pick up- After Jan 103731.25INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10095 | 20210928-10 | 53510602 | Access | 0 | ATV - Side by Side w/ roll bar- After Jan 10 | 18.45 | 10 | HR | 13.84 | 0 |  |  | 184.5 | 23.985 | 208.485 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-05 |  | 37 | 2021-10-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1009520210928-10ATV - Side by Side w/ roll bar- After Jan 1010184.5 | Corbiere and Sons Contracting1009520210928-10ATV - Side by Side w/ roll bar- After Jan 1010184.5INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10095 | 20210928-10 | 53510602 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 11 | HR | 47.54 | 0 |  |  | 697.18 | 90.6334 | 787.8134 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-05 |  | 37 | 2021-10-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1009520210928-10Excavator Hammer - 30 - 50 ton- After Jan 1011697.18 | Corbiere and Sons Contracting1009520210928-10Excavator Hammer - 30 - 50 ton- After Jan 1011697.18INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10095 | 20210928-10 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 22 | Dynamic | 110.22 | 0 |  |  | 3233.12 | 420.3056 | 3653.4256 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-05 |  | 37 | 2021-10-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1009520210928-10Excavator - 36 ton- After Jan 10223233.12 | Corbiere and Sons Contracting1009520210928-10Excavator - 36 ton- After Jan 10223233.12INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10095 | 20210928-10 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-05 |  | 37 | 2021-10-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1009520210928-10Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting1009520210928-10Excavator - 30 ton- After Jan 10111522.95INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10095 | 20210928-10 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-05 |  | 37 | 2021-10-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1009520210928-10Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting1009520210928-10Dozer D6 or equal- After Jan 10111446.28INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10062 | 20210926-14 | 53510602 | Access | 0 | L.O.A. | 210 | 0.5 | DAY |  |  |  | 0 | 105 | 13.65 | 118.65 | 2021-09-26 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Billable time for Safety Advisor present in WF6 | 6 | C130-C277 | WF6 | 0 | 2021-10-04 |  | 36 | 2021-10-08 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1006220210926-14L.O.A.0.5105 | Corbiere and Sons Contracting1006220210926-14L.O.A.0.5105INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10062 | 20210926-14 | 53510602 | Access | 0 | Safety Advisor | 85 | 7 | HR |  |  | 85 | 0 | 595 | 77.35 | 672.35 | 2021-09-26 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Billable time for Safety Advisor present in WF6 | 6 | C130-C277 | WF6 | 0 | 2021-10-04 |  | 36 | 2021-10-08 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1006220210926-14Safety Advisor7595 | Corbiere and Sons Contracting1006220210926-14Safety Advisor7595INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10062 | 20210926-14 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-09-26 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Billable time for Safety Advisor present in WF6 | 6 | C130-C277 | WF6 | 0 | 2021-10-04 |  | 36 | 2021-10-08 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1006220210926-14Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1006220210926-14Light Truck - Pick up- After Jan 101243.75INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10061 | 20210926-13 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 55 | HR |  |  | 75 | 0 | 4125 | 536.25 | 4661.25 | 2021-09-26 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-04 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1006120210926-13Operator - Principle - After Jan 10554125 | Corbiere and Sons Contracting1006120210926-13Operator - Principle - After Jan 10554125INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10061 | 20210926-13 | 53510602 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-09-26 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-04 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1006120210926-13Foreman121140 | Corbiere and Sons Contracting1006120210926-13Foreman121140INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10061 | 20210926-13 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 22 | Dynamic | 103.54 | 0 |  |  | 3037.1 | 394.823 | 3431.923 | 2021-09-26 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-04 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1006120210926-13Rock Truck - 30 Ton- After Jan 10223037.1 | Corbiere and Sons Contracting1006120210926-13Rock Truck - 30 Ton- After Jan 10223037.1INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10061 | 20210926-13 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 4 | DAY | 182.81 | 0 |  |  | 975 | 126.75 | 1101.75 | 2021-09-26 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-04 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1006120210926-13Light Truck - Pick up- After Jan 104975 | Corbiere and Sons Contracting1006120210926-13Light Truck - Pick up- After Jan 104975INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10061 | 20210926-13 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-26 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-04 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1006120210926-13Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1006120210926-13Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10061 | 20210926-13 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 6 | HR | 9.16 | 0 |  |  | 73.26 | 9.5238 | 82.7838 | 2021-09-26 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-04 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1006120210926-13Excavator Thumb - 30 - 50 ton- After Jan 10673.26 | Corbiere and Sons Contracting1006120210926-13Excavator Thumb - 30 - 50 ton- After Jan 10673.26INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10061 | 20210926-13 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-26 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-04 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1006120210926-13Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1006120210926-13Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10061 | 20210926-13 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-26 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-04 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1006120210926-13Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting1006120210926-13Excavator - 36 ton- After Jan 10111616.56INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10061 | 20210926-13 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 6 | Dynamic | 110.22 | 0 |  |  | 881.76 | 114.6288 | 996.3888 | 2021-09-26 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-04 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1006120210926-13Excavator - 36 ton- After Jan 106881.76 | Corbiere and Sons Contracting1006120210926-13Excavator - 36 ton- After Jan 106881.76INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10061 | 20210926-13 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-26 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-04 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1006120210926-13Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting1006120210926-13Excavator - 30 ton- After Jan 10111522.95INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10061 | 20210926-13 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-09-26 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-04 |  | 58 | 2021-10-04 | [6 empty] | 06 | Corbiere and Sons Contracting1006120210926-13Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting1006120210926-13Dozer D6 or equal- After Jan 10111446.28INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10041 | 20210925-8 | 53510602 | Access | 0 | Labourer - General - After Jan 10 | 60 | 6 | HR |  |  | 60 | 0 | 360 | 46.8 | 406.8 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C257-C267 | Hare Lake | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004120210925-8Labourer - General - After Jan 106360 | Corbiere and Sons Contracting1004120210925-8Labourer - General - After Jan 106360INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10041 | 20210925-8 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 42 | HR |  |  | 75 | 0 | 3150 | 409.5 | 3559.5 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C257-C267 | Hare Lake | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004120210925-8Operator - Principle - After Jan 10423150 | Corbiere and Sons Contracting1004120210925-8Operator - Principle - After Jan 10423150INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10041 | 20210925-8 | 53510602 | Access | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C257-C267 | Hare Lake | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004120210925-8L.O.A.51050 | Corbiere and Sons Contracting1004120210925-8L.O.A.51050INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10041 | 20210925-8 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C257-C267 | Hare Lake | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004120210925-8Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting1004120210925-8Rock Truck - 30 Ton- After Jan 10111518.55INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10041 | 20210925-8 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C257-C267 | Hare Lake | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004120210925-8Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting1004120210925-8Light Truck - Pick up- After Jan 102487.5INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10041 | 20210925-8 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 5.5 | HR | 9.16 | 0 |  |  | 67.155 | 8.7302 | 75.8851 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C257-C267 | Hare Lake | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004120210925-8Excavator Thumb - 30 - 50 ton- After Jan 105.567.155 | Corbiere and Sons Contracting1004120210925-8Excavator Thumb - 30 - 50 ton- After Jan 105.567.155INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10041 | 20210925-8 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 5.5 | Dynamic | 103.84 | 0 |  |  | 761.475 | 98.9917 | 860.4668 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C257-C267 | Hare Lake | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004120210925-8Excavator - 30 ton- After Jan 105.5761.475 | Corbiere and Sons Contracting1004120210925-8Excavator - 30 ton- After Jan 105.5761.475INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10041 | 20210925-8 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C257-C267 | Hare Lake | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004120210925-8Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting1004120210925-8Excavator - 30 ton- After Jan 10111522.95INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10041 | 20210925-8 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Hare Lake road | 6 | C257-C267 | Hare Lake | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004120210925-8Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting1004120210925-8Dozer D6 or equal- After Jan 10111446.28INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10040 | 20210925-7 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 72 | HR |  |  | 75 | 0 | 5400 | 702 | 6102 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004020210925-7Operator - Principle - After Jan 10725400 | Corbiere and Sons Contracting1004020210925-7Operator - Principle - After Jan 10725400INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10040 | 20210925-7 | 53510602 | Access | 0 | L.O.A. | 210 | 7 | DAY |  |  |  | 0 | 1470 | 191.1 | 1661.1 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004020210925-7L.O.A.71470 | Corbiere and Sons Contracting1004020210925-7L.O.A.71470INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10040 | 20210925-7 | 53510602 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004020210925-7Foreman121140 | Corbiere and Sons Contracting1004020210925-7Foreman121140INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10040 | 20210925-7 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 33 | Dynamic | 103.54 | 0 |  |  | 4555.65 | 592.2345 | 5147.8845 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004020210925-7Rock Truck - 30 Ton- After Jan 10334555.65 | Corbiere and Sons Contracting1004020210925-7Rock Truck - 30 Ton- After Jan 10334555.65INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10040 | 20210925-7 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 4 | DAY | 182.81 | 0 |  |  | 975 | 126.75 | 1101.75 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004020210925-7Light Truck - Pick up- After Jan 104975 | Corbiere and Sons Contracting1004020210925-7Light Truck - Pick up- After Jan 104975INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10040 | 20210925-7 | 53510602 | Access | 0 | ATV - Side by Side w/ roll bar- After Jan 10 | 18.45 | 10 | HR | 13.84 | 0 |  |  | 184.5 | 23.985 | 208.485 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004020210925-7ATV - Side by Side w/ roll bar- After Jan 1010184.5 | Corbiere and Sons Contracting1004020210925-7ATV - Side by Side w/ roll bar- After Jan 1010184.5INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10040 | 20210925-7 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004020210925-7Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1004020210925-7Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10040 | 20210925-7 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004020210925-7Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1004020210925-7Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10040 | 20210925-7 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004020210925-7Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting1004020210925-7Excavator - 36 ton- After Jan 10111616.56INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10040 | 20210925-7 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004020210925-7Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting1004020210925-7Excavator - 30 ton- After Jan 10111522.95INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10040 | 20210925-7 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004020210925-7Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting1004020210925-7Dozer D6 or equal- After Jan 10111446.28INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10039 | 20210925-6 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 36 | HR |  |  | 75 | 0 | 2700 | 351 | 3051 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1003920210925-6Operator - Principle - After Jan 10362700 | Corbiere and Sons Contracting1003920210925-6Operator - Principle - After Jan 10362700INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10039 | 20210925-6 | 53510602 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1003920210925-6L.O.A.3630 | Corbiere and Sons Contracting1003920210925-6L.O.A.3630INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10039 | 20210925-6 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1003920210925-6Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting1003920210925-6Light Truck - Pick up- After Jan 102487.5INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10039 | 20210925-6 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1003920210925-6Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1003920210925-6Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10039 | 20210925-6 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10 | Dynamic | 110.22 | 0 |  |  | 1469.6 | 191.048 | 1660.648 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1003920210925-6Excavator - 36 ton- After Jan 10101469.6 | Corbiere and Sons Contracting1003920210925-6Excavator - 36 ton- After Jan 10101469.6INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10039 | 20210925-6 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1003920210925-6Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting1003920210925-6Excavator - 30 ton- After Jan 10111522.95INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10039 | 20210925-6 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1003920210925-6Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting1003920210925-6Dozer D6 or equal- After Jan 10111446.28INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10049 | 20210925-16 | 53510602 | Access | 0 | L.O.A. | 210 | 0.5 | DAY |  |  |  | 0 | 105 | 13.65 | 118.65 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Billable time for Safety Advisor present in WF6 | 6 | C130-C277 | WF6 | 0 | 2021-10-04 |  | 36 | 2021-10-04 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1004920210925-16L.O.A.0.5105 | Corbiere and Sons Contracting1004920210925-16L.O.A.0.5105INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10049 | 20210925-16 | 53510602 | Access | 0 | Safety Advisor | 85 | 7 | HR |  |  | 85 | 0 | 595 | 77.35 | 672.35 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Billable time for Safety Advisor present in WF6 | 6 | C130-C277 | WF6 | 0 | 2021-10-04 |  | 36 | 2021-10-04 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1004920210925-16Safety Advisor7595 | Corbiere and Sons Contracting1004920210925-16Safety Advisor7595INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10049 | 20210925-16 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Billable time for Safety Advisor present in WF6 | 6 | C130-C277 | WF6 | 0 | 2021-10-04 |  | 36 | 2021-10-04 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1004920210925-16Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1004920210925-16Light Truck - Pick up- After Jan 101243.75INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10048 | 20210925-15 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 40 | HR |  |  | 75 | 0 | 3000 | 390 | 3390 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004820210925-15Operator - Principle - After Jan 10403000 | Corbiere and Sons Contracting1004820210925-15Operator - Principle - After Jan 10403000INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10048 | 20210925-15 | 53510602 | Access | 0 | Foreman | 95 | 4 | HR |  |  | 95 | 0 | 380 | 49.4 | 429.4 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004820210925-15Foreman4380 | Corbiere and Sons Contracting1004820210925-15Foreman4380INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10048 | 20210925-15 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004820210925-15Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting1004820210925-15Rock Truck - 30 Ton- After Jan 10111518.55INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10048 | 20210925-15 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 4 | DAY | 182.81 | 0 |  |  | 975 | 126.75 | 1101.75 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004820210925-15Light Truck - Pick up- After Jan 104975 | Corbiere and Sons Contracting1004820210925-15Light Truck - Pick up- After Jan 104975INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10048 | 20210925-15 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 3 | HR | 9.16 | 0 |  |  | 36.63 | 4.7619 | 41.3919 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004820210925-15Excavator Thumb - 30 - 50 ton- After Jan 10336.63 | Corbiere and Sons Contracting1004820210925-15Excavator Thumb - 30 - 50 ton- After Jan 10336.63INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10048 | 20210925-15 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004820210925-15Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting1004820210925-15Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10048 | 20210925-15 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 3 | HR | 9.16 | 0 |  |  | 36.63 | 4.7619 | 41.3919 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004820210925-15Excavator Thumb - 30 - 50 ton- After Jan 10336.63 | Corbiere and Sons Contracting1004820210925-15Excavator Thumb - 30 - 50 ton- After Jan 10336.63INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10048 | 20210925-15 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004820210925-15Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1004820210925-15Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10048 | 20210925-15 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 3 | Dynamic | 110.22 | 0 |  |  | 440.88 | 57.3144 | 498.1944 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004820210925-15Excavator - 36 ton- After Jan 103440.88 | Corbiere and Sons Contracting1004820210925-15Excavator - 36 ton- After Jan 103440.88INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10048 | 20210925-15 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004820210925-15Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting1004820210925-15Excavator - 36 ton- After Jan 1091322.64INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10048 | 20210925-15 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 3 | Dynamic | 110.22 | 0 |  |  | 440.88 | 57.3144 | 498.1944 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004820210925-15Excavator - 36 ton- After Jan 103440.88 | Corbiere and Sons Contracting1004820210925-15Excavator - 36 ton- After Jan 103440.88INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10048 | 20210925-15 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004820210925-15Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting1004820210925-15Excavator - 30 ton- After Jan 10111522.95INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10048 | 20210925-15 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004820210925-15Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting1004820210925-15Dozer D6 or equal- After Jan 10111446.28INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10047 | 20210925-14 | 53510602 | Access | 0 | Labourer - General - After Jan 10 | 60 | 24 | HR |  |  | 60 | 0 | 1440 | 187.2 | 1627.2 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Lake | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004720210925-14Labourer - General - After Jan 10241440 | Corbiere and Sons Contracting1004720210925-14Labourer - General - After Jan 10241440INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10047 | 20210925-14 | 53510602 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 12 | HR |  |  | 70 | 0 | 840 | 109.2 | 949.2 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Lake | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004720210925-14Driver - AZ - After Jan 1012840 | Corbiere and Sons Contracting1004720210925-14Driver - AZ - After Jan 1012840INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10047 | 20210925-14 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 41 | HR |  |  | 75 | 0 | 3075 | 399.75 | 3474.75 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Lake | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004720210925-14Operator - Principle - After Jan 10413075 | Corbiere and Sons Contracting1004720210925-14Operator - Principle - After Jan 10413075INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10047 | 20210925-14 | 53510602 | Access | 0 | L.O.A. | 210 | 8 | DAY |  |  |  | 0 | 1680 | 218.4 | 1898.4 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Lake | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004720210925-14L.O.A.81680 | Corbiere and Sons Contracting1004720210925-14L.O.A.81680INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10047 | 20210925-14 | 53510602 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Lake | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004720210925-14Foreman121140 | Corbiere and Sons Contracting1004720210925-14Foreman121140INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10047 | 20210925-14 | 53510602 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 12 | Dynamic | 91.79 | 0 |  |  | 1468.68 | 190.9284 | 1659.6084 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Lake | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004720210925-14Tractor Trailer - 60 Ton- After Jan 10121468.68 | Corbiere and Sons Contracting1004720210925-14Tractor Trailer - 60 Ton- After Jan 10121468.68INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10047 | 20210925-14 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 9.5 | Dynamic | 103.54 | 0 |  |  | 1311.475 | 170.4917 | 1481.9668 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Lake | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004720210925-14Rock Truck - 30 Ton- After Jan 109.51311.475 | Corbiere and Sons Contracting1004720210925-14Rock Truck - 30 Ton- After Jan 109.51311.475INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10047 | 20210925-14 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Lake | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004720210925-14Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting1004720210925-14Light Truck - Pick up- After Jan 103731.25INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10047 | 20210925-14 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Lake | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004720210925-14Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting1004720210925-14Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10047 | 20210925-14 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Lake | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004720210925-14Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting1004720210925-14Excavator - 36 ton- After Jan 1091322.64INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10047 | 20210925-14 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Lake | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004720210925-14Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting1004720210925-14Dozer D6 or equal- After Jan 10111446.28INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10046 | 20210925-13 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acvitites on Mink Creek | 6 | C237-C247 | Mink Creek | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004620210925-13Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1004620210925-13Operator - Principle - After Jan 1012900INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10046 | 20210925-13 | 53510602 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acvitites on Mink Creek | 6 | C237-C247 | Mink Creek | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004620210925-13L.O.A.1210 | Corbiere and Sons Contracting1004620210925-13L.O.A.1210INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10046 | 20210925-13 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acvitites on Mink Creek | 6 | C237-C247 | Mink Creek | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004620210925-13Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1004620210925-13Light Truck - Pick up- After Jan 101243.75INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10046 | 20210925-13 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acvitites on Mink Creek | 6 | C237-C247 | Mink Creek | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004620210925-13Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting1004620210925-13Excavator - 36 ton- After Jan 10111616.56INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10045 | 20210925-12 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 42 | HR |  |  | 75 | 0 | 3150 | 409.5 | 3559.5 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Middleton | 6 | C210-C213 | Middleton | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004520210925-12Operator - Principle - After Jan 10423150 | Corbiere and Sons Contracting1004520210925-12Operator - Principle - After Jan 10423150INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10045 | 20210925-12 | 53510602 | Access | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Middleton | 6 | C210-C213 | Middleton | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004520210925-12L.O.A.51050 | Corbiere and Sons Contracting1004520210925-12L.O.A.51050INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10045 | 20210925-12 | 53510602 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Middleton | 6 | C210-C213 | Middleton | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004520210925-12Foreman121140 | Corbiere and Sons Contracting1004520210925-12Foreman121140INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10045 | 20210925-12 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 15 | Dynamic | 103.54 | 0 |  |  | 2070.75 | 269.1975 | 2339.9475 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Middleton | 6 | C210-C213 | Middleton | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004520210925-12Rock Truck - 30 Ton- After Jan 10152070.75 | Corbiere and Sons Contracting1004520210925-12Rock Truck - 30 Ton- After Jan 10152070.75INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10045 | 20210925-12 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Middleton | 6 | C210-C213 | Middleton | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004520210925-12Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting1004520210925-12Light Truck - Pick up- After Jan 103731.25INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10045 | 20210925-12 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 8 | HR | 9.16 | 0 |  |  | 97.68 | 12.6984 | 110.3784 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Middleton | 6 | C210-C213 | Middleton | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004520210925-12Excavator Thumb - 30 - 50 ton- After Jan 10897.68 | Corbiere and Sons Contracting1004520210925-12Excavator Thumb - 30 - 50 ton- After Jan 10897.68INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10045 | 20210925-12 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 8 | Dynamic | 110.22 | 0 |  |  | 1175.68 | 152.8384 | 1328.5184 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Middleton | 6 | C210-C213 | Middleton | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004520210925-12Excavator - 36 ton- After Jan 1081175.68 | Corbiere and Sons Contracting1004520210925-12Excavator - 36 ton- After Jan 1081175.68INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10045 | 20210925-12 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 7 | Dynamic | 98.61 | 0 |  |  | 920.36 | 119.6468 | 1040.0068 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Middleton | 6 | C210-C213 | Middleton | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004520210925-12Dozer D6 or equal- After Jan 107920.36 | Corbiere and Sons Contracting1004520210925-12Dozer D6 or equal- After Jan 107920.36INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10044 | 20210925-11 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities from Little Pic River | 6 | C215-C216 | Little Pic River | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004420210925-11Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1004420210925-11Operator - Principle - After Jan 1012900INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10044 | 20210925-11 | 53510602 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities from Little Pic River | 6 | C215-C216 | Little Pic River | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004420210925-11L.O.A.1210 | Corbiere and Sons Contracting1004420210925-11L.O.A.1210INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10044 | 20210925-11 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities from Little Pic River | 6 | C215-C216 | Little Pic River | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004420210925-11Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1004420210925-11Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10044 | 20210925-11 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities from Little Pic River | 6 | C215-C216 | Little Pic River | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004420210925-11Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting1004420210925-11Excavator - 36 ton- After Jan 10111616.56INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10043 | 20210925-10-R1 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 58 | HR |  |  | 75 | 0 | 4350 | 565.5 | 4915.5 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004320210925-10-R1Operator - Principle - After Jan 10584350 | Corbiere and Sons Contracting1004320210925-10-R1Operator - Principle - After Jan 10584350INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10043 | 20210925-10-R1 | 53510602 | Access | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004320210925-10-R1L.O.A.61260 | Corbiere and Sons Contracting1004320210925-10-R1L.O.A.61260INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10043 | 20210925-10-R1 | 53510602 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004320210925-10-R1Foreman121140 | Corbiere and Sons Contracting1004320210925-10-R1Foreman121140INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10043 | 20210925-10-R1 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004320210925-10-R1Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting1004320210925-10-R1Rock Truck - 30 Ton- After Jan 10111518.55INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10043 | 20210925-10-R1 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004320210925-10-R1Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting1004320210925-10-R1Light Truck - Pick up- After Jan 103731.25INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10043 | 20210925-10-R1 | 53510602 | Access | 0 | ATV - Side by Side w/ roll bar- After Jan 10 | 18.45 | 10 | HR | 13.84 | 0 |  |  | 184.5 | 23.985 | 208.485 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004320210925-10-R1ATV - Side by Side w/ roll bar- After Jan 1010184.5 | Corbiere and Sons Contracting1004320210925-10-R1ATV - Side by Side w/ roll bar- After Jan 1010184.5INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10043 | 20210925-10-R1 | 53510602 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 11 | HR | 47.54 | 0 |  |  | 697.18 | 90.6334 | 787.8134 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004320210925-10-R1Excavator Hammer - 30 - 50 ton- After Jan 1011697.18 | Corbiere and Sons Contracting1004320210925-10-R1Excavator Hammer - 30 - 50 ton- After Jan 1011697.18INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10043 | 20210925-10-R1 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004320210925-10-R1Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting1004320210925-10-R1Excavator - 36 ton- After Jan 10111616.56INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10043 | 20210925-10-R1 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004320210925-10-R1Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting1004320210925-10-R1Excavator - 36 ton- After Jan 10111616.56INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10043 | 20210925-10-R1 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004320210925-10-R1Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting1004320210925-10-R1Excavator - 30 ton- After Jan 10111522.95INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10043 | 20210925-10-R1 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 8 | Dynamic | 98.61 | 0 |  |  | 1051.84 | 136.7392 | 1188.5792 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1004320210925-10-R1Dozer D6 or equal- After Jan 1081051.84 | Corbiere and Sons Contracting1004320210925-10-R1Dozer D6 or equal- After Jan 1081051.84INV #150 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10147 | 20211001-17 | 53530601 | Rig/Access Mats | 0 | Driver - AZ - After Jan 10 | 70 | 3 | HR |  |  | 70 | 0 | 210 | 27.3 | 237.3 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float brought mats over to Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1014720211001-17Driver - AZ - After Jan 103210 | Corbiere and Sons Contracting1014720211001-17Driver - AZ - After Jan 103210INV #150 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Corbiere and Sons Contracting | 6 | 0 | 10147 | 20211001-17 | 53530601 | Rig/Access Mats | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 3 | Dynamic | 91.79 | 0 |  |  | 367.17 | 47.7321 | 414.9021 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float brought mats over to Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1014720211001-17Tractor Trailer - 60 Ton- After Jan 103367.17 | Corbiere and Sons Contracting1014720211001-17Tractor Trailer - 60 Ton- After Jan 103367.17INV #150 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Corbiere and Sons Contracting | 6 | 0 | 10142 | 20211001-12 | 53530601 | Rig/Access Mats | 0 | Driver - AZ - After Jan 10 | 70 | 3 | HR |  |  | 70 | 0 | 210 | 27.3 | 237.3 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rig and swamps mats being delivered, unloaded and dragged to site | 6 | C186-C195 | Del Lake West | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1014220211001-12Driver - AZ - After Jan 103210 | Corbiere and Sons Contracting1014220211001-12Driver - AZ - After Jan 103210INV #150 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Corbiere and Sons Contracting | 6 | 0 | 10142 | 20211001-12 | 53530601 | Rig/Access Mats | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 75 | 0 | 450 | 58.5 | 508.5 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rig and swamps mats being delivered, unloaded and dragged to site | 6 | C186-C195 | Del Lake West | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1014220211001-12Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting1014220211001-12Operator - Principle - After Jan 106450INV #150 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Corbiere and Sons Contracting | 6 | 0 | 10142 | 20211001-12 | 53530601 | Rig/Access Mats | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rig and swamps mats being delivered, unloaded and dragged to site | 6 | C186-C195 | Del Lake West | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1014220211001-12L.O.A.1210 | Corbiere and Sons Contracting1014220211001-12L.O.A.1210INV #150 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Corbiere and Sons Contracting | 6 | 0 | 10142 | 20211001-12 | 53530601 | Rig/Access Mats | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 3 | Dynamic | 91.79 | 0 |  |  | 367.17 | 47.7321 | 414.9021 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rig and swamps mats being delivered, unloaded and dragged to site | 6 | C186-C195 | Del Lake West | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1014220211001-12Tractor Trailer - 60 Ton- After Jan 103367.17 | Corbiere and Sons Contracting1014220211001-12Tractor Trailer - 60 Ton- After Jan 103367.17INV #150 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Corbiere and Sons Contracting | 6 | 0 | 10142 | 20211001-12 | 53530601 | Rig/Access Mats | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 3 | Dynamic | 110.22 | 0 |  |  | 440.88 | 57.3144 | 498.1944 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rig and swamps mats being delivered, unloaded and dragged to site | 6 | C186-C195 | Del Lake West | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1014220211001-12Excavator - 36 ton- After Jan 103440.88 | Corbiere and Sons Contracting1014220211001-12Excavator - 36 ton- After Jan 103440.88INV #150 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Corbiere and Sons Contracting | 6 | 0 | 10142 | 20211001-12 | 53530601 | Rig/Access Mats | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 3 | Dynamic | 98.61 | 0 |  |  | 394.44 | 51.2772 | 445.7172 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rig and swamps mats being delivered, unloaded and dragged to site | 6 | C186-C195 | Del Lake West | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1014220211001-12Dozer D6 or equal- After Jan 103394.44 | Corbiere and Sons Contracting1014220211001-12Dozer D6 or equal- After Jan 103394.44INV #150 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Corbiere and Sons Contracting | 6 | 0 | 10111 | 20210929-11 | 53530601 | Rig/Access Mats | 0 | Driver - AZ - After Jan 10 | 70 | 12 | HR |  |  | 70 | 0 | 840 | 109.2 | 949.2 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float delivered mats to Del Lake - OP unloaded | 6 | C186-C195 | Del Lake | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1011120210929-11Driver - AZ - After Jan 1012840 | Corbiere and Sons Contracting1011120210929-11Driver - AZ - After Jan 1012840INV #150 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Corbiere and Sons Contracting | 6 | 0 | 10111 | 20210929-11 | 53530601 | Rig/Access Mats | 0 | Operator - Principle - After Jan 10 | 75 | 5 | HR |  |  | 75 | 0 | 375 | 48.75 | 423.75 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float delivered mats to Del Lake - OP unloaded | 6 | C186-C195 | Del Lake | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1011120210929-11Operator - Principle - After Jan 105375 | Corbiere and Sons Contracting1011120210929-11Operator - Principle - After Jan 105375INV #150 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Corbiere and Sons Contracting | 6 | 0 | 10111 | 20210929-11 | 53530601 | Rig/Access Mats | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float delivered mats to Del Lake - OP unloaded | 6 | C186-C195 | Del Lake | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1011120210929-11L.O.A.2420 | Corbiere and Sons Contracting1011120210929-11L.O.A.2420INV #150 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Corbiere and Sons Contracting | 6 | 0 | 10111 | 20210929-11 | 53530601 | Rig/Access Mats | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 12 | Dynamic | 91.79 | 0 |  |  | 1468.68 | 190.9284 | 1659.6084 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float delivered mats to Del Lake - OP unloaded | 6 | C186-C195 | Del Lake | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1011120210929-11Tractor Trailer - 60 Ton- After Jan 10121468.68 | Corbiere and Sons Contracting1011120210929-11Tractor Trailer - 60 Ton- After Jan 10121468.68INV #150 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Corbiere and Sons Contracting | 6 | 0 | 10111 | 20210929-11 | 53530601 | Rig/Access Mats | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 2 | Dynamic | 110.22 | 0 |  |  | 293.92 | 38.2096 | 332.1296 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float delivered mats to Del Lake - OP unloaded | 6 | C186-C195 | Del Lake | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1011120210929-11Excavator - 36 ton- After Jan 102293.92 | Corbiere and Sons Contracting1011120210929-11Excavator - 36 ton- After Jan 102293.92INV #150 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Corbiere and Sons Contracting | 6 | 0 | 10185 | 20211004-8 | 53510612 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 7 | HR |  |  | 75 | 0 | 525 | 68.25 | 593.25 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance activities on Hare Lake road | 6 | C257-C267 | Hare Lake Road | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1018520211004-8Operator - Principle - After Jan 107525 | Corbiere and Sons Contracting1018520211004-8Operator - Principle - After Jan 107525INV #150 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10185 | 20211004-8 | 53510612 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance activities on Hare Lake road | 6 | C257-C267 | Hare Lake Road | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1018520211004-8L.O.A.1210 | Corbiere and Sons Contracting1018520211004-8L.O.A.1210INV #150 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10185 | 20211004-8 | 53510612 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 6 | Dynamic | 103.84 | 0 |  |  | 830.7 | 107.991 | 938.691 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance activities on Hare Lake road | 6 | C257-C267 | Hare Lake Road | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1018520211004-8Excavator - 30 ton- After Jan 106830.7 | Corbiere and Sons Contracting1018520211004-8Excavator - 30 ton- After Jan 106830.7INV #150 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10182 | 20211004-5 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 12.5 | HR |  |  | 70 | 0 | 875 | 113.75 | 988.75 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 4 Padda Trucks and 1 Valentino Truck hauling from Cress Pit to Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1018220211004-5Driver - AZ - After Jan 1012.5875 | Corbiere and Sons Contracting1018220211004-5Driver - AZ - After Jan 1012.5875INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10182 | 20211004-5 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 44 | HR |  |  | 70 | 0 | 3080 | 400.4 | 3480.4 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 4 Padda Trucks and 1 Valentino Truck hauling from Cress Pit to Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1018220211004-5Driver - AZ - After Jan 10443080 | Corbiere and Sons Contracting1018220211004-5Driver - AZ - After Jan 10443080INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10182 | 20211004-5 | 53510604 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 4 Padda Trucks and 1 Valentino Truck hauling from Cress Pit to Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1018220211004-5L.O.A.4840 | Corbiere and Sons Contracting1018220211004-5L.O.A.4840INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10182 | 20211004-5 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 12.5 | Dynamic | 41.4 | 0 |  |  | 690 | 89.7 | 779.7 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 4 Padda Trucks and 1 Valentino Truck hauling from Cress Pit to Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1018220211004-5Dump - Triaxle- After Jan 1012.5690 | Corbiere and Sons Contracting1018220211004-5Dump - Triaxle- After Jan 1012.5690INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10182 | 20211004-5 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 44 | Dynamic | 41.4 | 0 |  |  | 2428.8 | 315.744 | 2744.544 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 4 Padda Trucks and 1 Valentino Truck hauling from Cress Pit to Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1018220211004-5Dump - Triaxle- After Jan 10442428.8 | Corbiere and Sons Contracting1018220211004-5Dump - Triaxle- After Jan 10442428.8INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10181 | 20211004-4 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 77.5 | HR |  |  | 70 | 0 | 5425 | 705.25 | 6130.25 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 7 Padda Trucks hauling from Cress Pit to Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1018120211004-4Driver - AZ - After Jan 1077.55425 | Corbiere and Sons Contracting1018120211004-4Driver - AZ - After Jan 1077.55425INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10181 | 20211004-4 | 53510604 | Access | 0 | L.O.A. | 210 | 7 | DAY |  |  |  | 0 | 1470 | 191.1 | 1661.1 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 7 Padda Trucks hauling from Cress Pit to Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1018120211004-4L.O.A.71470 | Corbiere and Sons Contracting1018120211004-4L.O.A.71470INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10181 | 20211004-4 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 77.5 | Dynamic | 41.4 | 0 |  |  | 4278 | 556.14 | 4834.14 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 7 Padda Trucks hauling from Cress Pit to Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1018120211004-4Dump - Triaxle- After Jan 1077.54278 | Corbiere and Sons Contracting1018120211004-4Dump - Triaxle- After Jan 1077.54278INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10192 | 20211004-15 | 53510604 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gervais RT hauling with Corbiere crew on Del | 6 | C186-C195 | Del Lake | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1019220211004-15Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1019220211004-15Operator - Principle - After Jan 1012900INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10192 | 20211004-15 | 53510604 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-10-04 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gervais RT hauling with Corbiere crew on Del | 6 | C186-C195 | Del Lake | 0 | 2021-10-12 |  | 58 | 2021-10-14 | [6 empty] | 06 | Corbiere and Sons Contracting1019220211004-15Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting1019220211004-15Rock Truck - 30 Ton- After Jan 10111518.55INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10169 | 20211003-5 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 92 | HR |  |  | 70 | 0 | 6440 | 837.2 | 7277.2 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 8 Padda Trucks hauling from Cress Pit to Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1016920211003-5Driver - AZ - After Jan 10926440 | Corbiere and Sons Contracting1016920211003-5Driver - AZ - After Jan 10926440INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10169 | 20211003-5 | 53510604 | Access | 0 | L.O.A. | 210 | 8 | DAY |  |  |  | 0 | 1680 | 218.4 | 1898.4 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 8 Padda Trucks hauling from Cress Pit to Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1016920211003-5L.O.A.81680 | Corbiere and Sons Contracting1016920211003-5L.O.A.81680INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10169 | 20211003-5 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 92 | Dynamic | 41.4 | 0 |  |  | 5078.4 | 660.192 | 5738.592 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 8 Padda Trucks hauling from Cress Pit to Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1016920211003-5Dump - Triaxle- After Jan 10925078.4 | Corbiere and Sons Contracting1016920211003-5Dump - Triaxle- After Jan 10925078.4INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10168 | 20211003-4 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 46 | HR |  |  | 70 | 0 | 3220 | 418.6 | 3638.6 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 4 Padda Trucks hauling from Cress Pit to Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1016820211003-4Driver - AZ - After Jan 10463220 | Corbiere and Sons Contracting1016820211003-4Driver - AZ - After Jan 10463220INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10168 | 20211003-4 | 53510604 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 4 Padda Trucks hauling from Cress Pit to Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1016820211003-4L.O.A.4840 | Corbiere and Sons Contracting1016820211003-4L.O.A.4840INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10168 | 20211003-4 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 46 | Dynamic | 41.4 | 0 |  |  | 2539.2 | 330.096 | 2869.296 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 4 Padda Trucks hauling from Cress Pit to Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1016820211003-4Dump - Triaxle- After Jan 10462539.2 | Corbiere and Sons Contracting1016820211003-4Dump - Triaxle- After Jan 10462539.2INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10167 | 20211003-3 | 53510604 | Access | 0 | Labourer - General - After Jan 10 | 60 | 12 | HR |  |  | 60 | 0 | 720 | 93.6 | 813.6 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit (4 Trucks Hauling) | 6 | C256-C267 | Hare Lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1016720211003-3Labourer - General - After Jan 1012720 | Corbiere and Sons Contracting1016720211003-3Labourer - General - After Jan 1012720INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10167 | 20211003-3 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 41.5 | HR |  |  | 70 | 0 | 2905 | 377.65 | 3282.65 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit (4 Trucks Hauling) | 6 | C256-C267 | Hare Lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1016720211003-3Driver - AZ - After Jan 1041.52905 | Corbiere and Sons Contracting1016720211003-3Driver - AZ - After Jan 1041.52905INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10167 | 20211003-3 | 53510604 | Access | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit (4 Trucks Hauling) | 6 | C256-C267 | Hare Lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1016720211003-3L.O.A.51050 | Corbiere and Sons Contracting1016720211003-3L.O.A.51050INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10167 | 20211003-3 | 53510604 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit (4 Trucks Hauling) | 6 | C256-C267 | Hare Lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1016720211003-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1016720211003-3Light Truck - Pick up- After Jan 101243.75INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10167 | 20211003-3 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 41.5 | Dynamic | 41.4 | 0 |  |  | 2290.8 | 297.804 | 2588.604 | 2021-10-03 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit (4 Trucks Hauling) | 6 | C256-C267 | Hare Lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1016720211003-3Dump - Triaxle- After Jan 1041.52290.8 | Corbiere and Sons Contracting1016720211003-3Dump - Triaxle- After Jan 1041.52290.8INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10154 | 20211002-5 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 12 | HR |  |  | 70 | 0 | 840 | 109.2 | 949.2 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 3 Padda Trucks, 1 Valentino and 1 Alan Hurd truck hauling from Jackfish Pit to Del West | 6 | C186-C195 | Del Lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1015420211002-5Driver - AZ - After Jan 1012840 | Corbiere and Sons Contracting1015420211002-5Driver - AZ - After Jan 1012840INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10154 | 20211002-5 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 34.5 | HR |  |  | 70 | 0 | 2415 | 313.95 | 2728.95 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 3 Padda Trucks, 1 Valentino and 1 Alan Hurd truck hauling from Jackfish Pit to Del West | 6 | C186-C195 | Del Lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1015420211002-5Driver - AZ - After Jan 1034.52415 | Corbiere and Sons Contracting1015420211002-5Driver - AZ - After Jan 1034.52415INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10154 | 20211002-5 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 12.5 | HR |  |  | 70 | 0 | 875 | 113.75 | 988.75 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 3 Padda Trucks, 1 Valentino and 1 Alan Hurd truck hauling from Jackfish Pit to Del West | 6 | C186-C195 | Del Lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1015420211002-5Driver - AZ - After Jan 1012.5875 | Corbiere and Sons Contracting1015420211002-5Driver - AZ - After Jan 1012.5875INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10154 | 20211002-5 | 53510604 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 3 Padda Trucks, 1 Valentino and 1 Alan Hurd truck hauling from Jackfish Pit to Del West | 6 | C186-C195 | Del Lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1015420211002-5L.O.A.3630 | Corbiere and Sons Contracting1015420211002-5L.O.A.3630INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10154 | 20211002-5 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 12 | Dynamic | 41.4 | 0 |  |  | 662.4 | 86.112 | 748.512 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 3 Padda Trucks, 1 Valentino and 1 Alan Hurd truck hauling from Jackfish Pit to Del West | 6 | C186-C195 | Del Lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1015420211002-5Dump - Triaxle- After Jan 1012662.4 | Corbiere and Sons Contracting1015420211002-5Dump - Triaxle- After Jan 1012662.4INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10154 | 20211002-5 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 34.5 | Dynamic | 41.4 | 0 |  |  | 1904.4 | 247.572 | 2151.972 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 3 Padda Trucks, 1 Valentino and 1 Alan Hurd truck hauling from Jackfish Pit to Del West | 6 | C186-C195 | Del Lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1015420211002-5Dump - Triaxle- After Jan 1034.51904.4 | Corbiere and Sons Contracting1015420211002-5Dump - Triaxle- After Jan 1034.51904.4INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10154 | 20211002-5 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 12.5 | Dynamic | 41.4 | 0 |  |  | 690 | 89.7 | 779.7 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 3 Padda Trucks, 1 Valentino and 1 Alan Hurd truck hauling from Jackfish Pit to Del West | 6 | C186-C195 | Del Lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1015420211002-5Dump - Triaxle- After Jan 1012.5690 | Corbiere and Sons Contracting1015420211002-5Dump - Triaxle- After Jan 1012.5690INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10153 | 20211002-4 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 46 | HR |  |  | 70 | 0 | 3220 | 418.6 | 3638.6 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 4 Padda Trucks hauling from Cress Pit to Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1015320211002-4Driver - AZ - After Jan 10463220 | Corbiere and Sons Contracting1015320211002-4Driver - AZ - After Jan 10463220INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10153 | 20211002-4 | 53510604 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 4 Padda Trucks hauling from Cress Pit to Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1015320211002-4L.O.A.4840 | Corbiere and Sons Contracting1015320211002-4L.O.A.4840INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10153 | 20211002-4 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 46 | Dynamic | 41.4 | 0 |  |  | 2539.2 | 330.096 | 2869.296 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 4 Padda Trucks hauling from Cress Pit to Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1015320211002-4Dump - Triaxle- After Jan 10462539.2 | Corbiere and Sons Contracting1015320211002-4Dump - Triaxle- After Jan 10462539.2INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10152 | 20211002-3 | 53510604 | Access | 0 | Labourer - General - After Jan 10 | 60 | 12 | HR |  |  | 60 | 0 | 720 | 93.6 | 813.6 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit (9 trucks working - 4 travel) | 6 | C257-C267 | Hare Lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1015220211002-3Labourer - General - After Jan 1012720 | Corbiere and Sons Contracting1015220211002-3Labourer - General - After Jan 1012720INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10152 | 20211002-3 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 151.5 | HR |  |  | 70 | 0 | 10605 | 1378.65 | 11983.65 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit (9 trucks working - 4 travel) | 6 | C257-C267 | Hare Lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1015220211002-3Driver - AZ - After Jan 10151.510605 | Corbiere and Sons Contracting1015220211002-3Driver - AZ - After Jan 10151.510605INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10152 | 20211002-3 | 53510604 | Access | 0 | L.O.A. | 210 | 14 | DAY |  |  |  | 0 | 2940 | 382.2 | 3322.2 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit (9 trucks working - 4 travel) | 6 | C257-C267 | Hare Lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1015220211002-3L.O.A.142940 | Corbiere and Sons Contracting1015220211002-3L.O.A.142940INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10152 | 20211002-3 | 53510604 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit (9 trucks working - 4 travel) | 6 | C257-C267 | Hare Lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1015220211002-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1015220211002-3Light Truck - Pick up- After Jan 101243.75INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10152 | 20211002-3 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 151.5 | Dynamic | 41.4 | 0 |  |  | 8362.8 | 1087.164 | 9449.964 | 2021-10-02 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit (9 trucks working - 4 travel) | 6 | C257-C267 | Hare Lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1015220211002-3Dump - Triaxle- After Jan 10151.58362.8 | Corbiere and Sons Contracting1015220211002-3Dump - Triaxle- After Jan 10151.58362.8INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10137 | 20211001-7 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 24.5 | HR |  |  | 70 | 0 | 1715 | 222.95 | 1937.95 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 1 Taranis Truck and 1 Valentino truck hauling to Mink Creek | 6 | C244-C247 | Mink Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1013720211001-7Driver - AZ - After Jan 1024.51715 | Corbiere and Sons Contracting1013720211001-7Driver - AZ - After Jan 1024.51715INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10137 | 20211001-7 | 53510604 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 1 Taranis Truck and 1 Valentino truck hauling to Mink Creek | 6 | C244-C247 | Mink Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1013720211001-7L.O.A.1210 | Corbiere and Sons Contracting1013720211001-7L.O.A.1210INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10137 | 20211001-7 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 24.5 | Dynamic | 41.4 | 0 |  |  | 1352.4 | 175.812 | 1528.212 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 1 Taranis Truck and 1 Valentino truck hauling to Mink Creek | 6 | C244-C247 | Mink Creek | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1013720211001-7Dump - Triaxle- After Jan 1024.51352.4 | Corbiere and Sons Contracting1013720211001-7Dump - Triaxle- After Jan 1024.51352.4INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10136 | 20211001-6 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 33 | HR |  |  | 70 | 0 | 2310 | 300.3 | 2610.3 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 3 Taranis Trucks, 1 Hurd Bros Trucks hauling to Del Lake | 6 | C186-C195 | Del Lake Road | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1013620211001-6Driver - AZ - After Jan 10332310 | Corbiere and Sons Contracting1013620211001-6Driver - AZ - After Jan 10332310INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10136 | 20211001-6 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 12 | HR |  |  | 70 | 0 | 840 | 109.2 | 949.2 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 3 Taranis Trucks, 1 Hurd Bros Trucks hauling to Del Lake | 6 | C186-C195 | Del Lake Road | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1013620211001-6Driver - AZ - After Jan 1012840 | Corbiere and Sons Contracting1013620211001-6Driver - AZ - After Jan 1012840INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10136 | 20211001-6 | 53510604 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 3 Taranis Trucks, 1 Hurd Bros Trucks hauling to Del Lake | 6 | C186-C195 | Del Lake Road | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1013620211001-6L.O.A.3630 | Corbiere and Sons Contracting1013620211001-6L.O.A.3630INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10136 | 20211001-6 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 33 | Dynamic | 41.4 | 0 |  |  | 1821.6 | 236.808 | 2058.408 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 3 Taranis Trucks, 1 Hurd Bros Trucks hauling to Del Lake | 6 | C186-C195 | Del Lake Road | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1013620211001-6Dump - Triaxle- After Jan 10331821.6 | Corbiere and Sons Contracting1013620211001-6Dump - Triaxle- After Jan 10331821.6INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10136 | 20211001-6 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 12 | Dynamic | 41.4 | 0 |  |  | 662.4 | 86.112 | 748.512 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 3 Taranis Trucks, 1 Hurd Bros Trucks hauling to Del Lake | 6 | C186-C195 | Del Lake Road | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1013620211001-6Dump - Triaxle- After Jan 1012662.4 | Corbiere and Sons Contracting1013620211001-6Dump - Triaxle- After Jan 1012662.4INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10135 | 20211001-5 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 23 | HR |  |  | 70 | 0 | 1610 | 209.3 | 1819.3 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 2 Padda Trucks hauling from Cress Pit to Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1013520211001-5Driver - AZ - After Jan 10231610 | Corbiere and Sons Contracting1013520211001-5Driver - AZ - After Jan 10231610INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10135 | 20211001-5 | 53510604 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 2 Padda Trucks hauling from Cress Pit to Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1013520211001-5L.O.A.2420 | Corbiere and Sons Contracting1013520211001-5L.O.A.2420INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10135 | 20211001-5 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 23 | Dynamic | 41.4 | 0 |  |  | 1269.6 | 165.048 | 1434.648 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 2 Padda Trucks hauling from Cress Pit to Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1013520211001-5Dump - Triaxle- After Jan 10231269.6 | Corbiere and Sons Contracting1013520211001-5Dump - Triaxle- After Jan 10231269.6INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10134 | 20211001-4 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 34.5 | HR |  |  | 70 | 0 | 2415 | 313.95 | 2728.95 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 3 Trucks from Padda Roadlines hauling from Cress Pit to Pic River West | 6 | D004-D015 | Pic River West | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1013420211001-4Driver - AZ - After Jan 1034.52415 | Corbiere and Sons Contracting1013420211001-4Driver - AZ - After Jan 1034.52415INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10134 | 20211001-4 | 53510604 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 3 Trucks from Padda Roadlines hauling from Cress Pit to Pic River West | 6 | D004-D015 | Pic River West | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1013420211001-4L.O.A.3630 | Corbiere and Sons Contracting1013420211001-4L.O.A.3630INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10134 | 20211001-4 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 34.5 | Dynamic | 41.4 | 0 |  |  | 1904.4 | 247.572 | 2151.972 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 3 Trucks from Padda Roadlines hauling from Cress Pit to Pic River West | 6 | D004-D015 | Pic River West | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1013420211001-4Dump - Triaxle- After Jan 1034.51904.4 | Corbiere and Sons Contracting1013420211001-4Dump - Triaxle- After Jan 1034.51904.4INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10133 | 20211001-3 | 53510604 | Access | 0 | Labourer - General - After Jan 10 | 60 | 12 | HR |  |  | 60 | 0 | 720 | 93.6 | 813.6 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit (7 trucks) | 6 | C257-C267 | Hare Lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1013320211001-3Labourer - General - After Jan 1012720 | Corbiere and Sons Contracting1013320211001-3Labourer - General - After Jan 1012720INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10133 | 20211001-3 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 80.5 | HR |  |  | 70 | 0 | 5635 | 732.55 | 6367.55 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit (7 trucks) | 6 | C257-C267 | Hare Lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1013320211001-3Driver - AZ - After Jan 1080.55635 | Corbiere and Sons Contracting1013320211001-3Driver - AZ - After Jan 1080.55635INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10133 | 20211001-3 | 53510604 | Access | 0 | L.O.A. | 210 | 8 | DAY |  |  |  | 0 | 1680 | 218.4 | 1898.4 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit (7 trucks) | 6 | C257-C267 | Hare Lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1013320211001-3L.O.A.81680 | Corbiere and Sons Contracting1013320211001-3L.O.A.81680INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10133 | 20211001-3 | 53510604 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit (7 trucks) | 6 | C257-C267 | Hare Lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1013320211001-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1013320211001-3Light Truck - Pick up- After Jan 101243.75INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10133 | 20211001-3 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 80.5 | Dynamic | 41.4 | 0 |  |  | 4443.6 | 577.668 | 5021.268 | 2021-10-01 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit (7 trucks) | 6 | C257-C267 | Hare Lake | 0 | 2021-10-12 |  | 58 | 2021-10-13 | [6 empty] | 06 | Corbiere and Sons Contracting1013320211001-3Dump - Triaxle- After Jan 1080.54443.6 | Corbiere and Sons Contracting1013320211001-3Dump - Triaxle- After Jan 1080.54443.6INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10122 | 20210930-6 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 43 | HR |  |  | 70 | 0 | 3010 | 391.3 | 3401.3 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 4 Taranis Trucks, 1 Hurd Bros and 2 Padda Trucks hauling to Del Lake | 6 | C186-C195 | Del Lake West | 0 | 2021-10-05 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1012220210930-6Driver - AZ - After Jan 10433010 | Corbiere and Sons Contracting1012220210930-6Driver - AZ - After Jan 10433010INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10122 | 20210930-6 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 12 | HR |  |  | 70 | 0 | 840 | 109.2 | 949.2 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 4 Taranis Trucks, 1 Hurd Bros and 2 Padda Trucks hauling to Del Lake | 6 | C186-C195 | Del Lake West | 0 | 2021-10-05 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1012220210930-6Driver - AZ - After Jan 1012840 | Corbiere and Sons Contracting1012220210930-6Driver - AZ - After Jan 1012840INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10122 | 20210930-6 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 23 | HR |  |  | 70 | 0 | 1610 | 209.3 | 1819.3 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 4 Taranis Trucks, 1 Hurd Bros and 2 Padda Trucks hauling to Del Lake | 6 | C186-C195 | Del Lake West | 0 | 2021-10-05 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1012220210930-6Driver - AZ - After Jan 10231610 | Corbiere and Sons Contracting1012220210930-6Driver - AZ - After Jan 10231610INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10122 | 20210930-6 | 53510604 | Access | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 4 Taranis Trucks, 1 Hurd Bros and 2 Padda Trucks hauling to Del Lake | 6 | C186-C195 | Del Lake West | 0 | 2021-10-05 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1012220210930-6L.O.A.61260 | Corbiere and Sons Contracting1012220210930-6L.O.A.61260INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10122 | 20210930-6 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 43 | Dynamic | 41.4 | 0 |  |  | 2373.6 | 308.568 | 2682.168 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 4 Taranis Trucks, 1 Hurd Bros and 2 Padda Trucks hauling to Del Lake | 6 | C186-C195 | Del Lake West | 0 | 2021-10-05 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1012220210930-6Dump - Triaxle- After Jan 10432373.6 | Corbiere and Sons Contracting1012220210930-6Dump - Triaxle- After Jan 10432373.6INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10122 | 20210930-6 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 12 | Dynamic | 41.4 | 0 |  |  | 662.4 | 86.112 | 748.512 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 4 Taranis Trucks, 1 Hurd Bros and 2 Padda Trucks hauling to Del Lake | 6 | C186-C195 | Del Lake West | 0 | 2021-10-05 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1012220210930-6Dump - Triaxle- After Jan 1012662.4 | Corbiere and Sons Contracting1012220210930-6Dump - Triaxle- After Jan 1012662.4INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10122 | 20210930-6 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 23 | Dynamic | 41.4 | 0 |  |  | 1269.6 | 165.048 | 1434.648 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 4 Taranis Trucks, 1 Hurd Bros and 2 Padda Trucks hauling to Del Lake | 6 | C186-C195 | Del Lake West | 0 | 2021-10-05 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1012220210930-6Dump - Triaxle- After Jan 10231269.6 | Corbiere and Sons Contracting1012220210930-6Dump - Triaxle- After Jan 10231269.6INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10121 | 20210930-5 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 13 | HR |  |  | 70 | 0 | 910 | 118.3 | 1028.3 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 1 Valentino truck hauling to Mink Creek from Cress Pit | 6 | C244-C247 | Mink Creek | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1012120210930-5Driver - AZ - After Jan 1013910 | Corbiere and Sons Contracting1012120210930-5Driver - AZ - After Jan 1013910INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10121 | 20210930-5 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 13 | Dynamic | 41.4 | 0 |  |  | 717.6 | 93.288 | 810.888 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 1 Valentino truck hauling to Mink Creek from Cress Pit | 6 | C244-C247 | Mink Creek | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1012120210930-5Dump - Triaxle- After Jan 1013717.6 | Corbiere and Sons Contracting1012120210930-5Dump - Triaxle- After Jan 1013717.6INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10119 | 20210930-4 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 34.5 | HR |  |  | 70 | 0 | 2415 | 313.95 | 2728.95 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 3 Trucks from Padda Roadlines hauling from Cress Pit to Pic River West | 6 | D004-D015 | Pic River West | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1011920210930-4Driver - AZ - After Jan 1034.52415 | Corbiere and Sons Contracting1011920210930-4Driver - AZ - After Jan 1034.52415INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10119 | 20210930-4 | 53510604 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 3 Trucks from Padda Roadlines hauling from Cress Pit to Pic River West | 6 | D004-D015 | Pic River West | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1011920210930-4L.O.A.3630 | Corbiere and Sons Contracting1011920210930-4L.O.A.3630INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10119 | 20210930-4 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 34.5 | Dynamic | 41.4 | 0 |  |  | 1904.4 | 247.572 | 2151.972 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 3 Trucks from Padda Roadlines hauling from Cress Pit to Pic River West | 6 | D004-D015 | Pic River West | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1011920210930-4Dump - Triaxle- After Jan 1034.51904.4 | Corbiere and Sons Contracting1011920210930-4Dump - Triaxle- After Jan 1034.51904.4INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10118 | 20210930-3 | 53510604 | Access | 0 | Labourer - General - After Jan 10 | 60 | 12 | HR |  |  | 60 | 0 | 720 | 93.6 | 813.6 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit (7 trucks) | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1011820210930-3Labourer - General - After Jan 1012720 | Corbiere and Sons Contracting1011820210930-3Labourer - General - After Jan 1012720INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10118 | 20210930-3 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 80.5 | HR |  |  | 70 | 0 | 5635 | 732.55 | 6367.55 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit (7 trucks) | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1011820210930-3Driver - AZ - After Jan 1080.55635 | Corbiere and Sons Contracting1011820210930-3Driver - AZ - After Jan 1080.55635INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10118 | 20210930-3 | 53510604 | Access | 0 | L.O.A. | 210 | 8 | DAY |  |  |  | 0 | 1680 | 218.4 | 1898.4 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit (7 trucks) | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1011820210930-3L.O.A.81680 | Corbiere and Sons Contracting1011820210930-3L.O.A.81680INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10118 | 20210930-3 | 53510604 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit (7 trucks) | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1011820210930-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1011820210930-3Light Truck - Pick up- After Jan 101243.75INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10118 | 20210930-3 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 80.5 | Dynamic | 41.4 | 0 |  |  | 4443.6 | 577.668 | 5021.268 | 2021-09-30 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit (7 trucks) | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-10-06 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1011820210930-3Dump - Triaxle- After Jan 1080.54443.6 | Corbiere and Sons Contracting1011820210930-3Dump - Triaxle- After Jan 1080.54443.6INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10105 | 20210929-6 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 46 | HR |  |  | 70 | 0 | 3220 | 418.6 | 3638.6 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling from Jackfish Pit to Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1010520210929-6Driver - AZ - After Jan 10463220 | Corbiere and Sons Contracting1010520210929-6Driver - AZ - After Jan 10463220INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10105 | 20210929-6 | 53510604 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling from Jackfish Pit to Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1010520210929-6L.O.A.4840 | Corbiere and Sons Contracting1010520210929-6L.O.A.4840INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10105 | 20210929-6 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 46 | Dynamic | 41.4 | 0 |  |  | 2539.2 | 330.096 | 2869.296 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling from Jackfish Pit to Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1010520210929-6Dump - Triaxle- After Jan 10462539.2 | Corbiere and Sons Contracting1010520210929-6Dump - Triaxle- After Jan 10462539.2INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10104 | 20210929-5 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 12 | HR |  |  | 70 | 0 | 840 | 109.2 | 949.2 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 3 Padda Trucks and 1 Hurd Bros Truck hauling to Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1010420210929-5Driver - AZ - After Jan 1012840 | Corbiere and Sons Contracting1010420210929-5Driver - AZ - After Jan 1012840INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10104 | 20210929-5 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 34.5 | HR |  |  | 70 | 0 | 2415 | 313.95 | 2728.95 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 3 Padda Trucks and 1 Hurd Bros Truck hauling to Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1010420210929-5Driver - AZ - After Jan 1034.52415 | Corbiere and Sons Contracting1010420210929-5Driver - AZ - After Jan 1034.52415INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10104 | 20210929-5 | 53510604 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 3 Padda Trucks and 1 Hurd Bros Truck hauling to Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1010420210929-5L.O.A.3630 | Corbiere and Sons Contracting1010420210929-5L.O.A.3630INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10104 | 20210929-5 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 12 | Dynamic | 41.4 | 0 |  |  | 662.4 | 86.112 | 748.512 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 3 Padda Trucks and 1 Hurd Bros Truck hauling to Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1010420210929-5Dump - Triaxle- After Jan 1012662.4 | Corbiere and Sons Contracting1010420210929-5Dump - Triaxle- After Jan 1012662.4INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10104 | 20210929-5 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 34.5 | Dynamic | 41.4 | 0 |  |  | 1904.4 | 247.572 | 2151.972 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 3 Padda Trucks and 1 Hurd Bros Truck hauling to Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1010420210929-5Dump - Triaxle- After Jan 1034.51904.4 | Corbiere and Sons Contracting1010420210929-5Dump - Triaxle- After Jan 1034.51904.4INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10103 | 20210929-4 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 34.5 | HR |  |  | 70 | 0 | 2415 | 313.95 | 2728.95 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 3 Trucks from Padda Roadlines hauling from Cress Pit to Pic River West | 6 | D004-D015 | Pic River | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1010320210929-4Driver - AZ - After Jan 1034.52415 | Corbiere and Sons Contracting1010320210929-4Driver - AZ - After Jan 1034.52415INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10103 | 20210929-4 | 53510604 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 3 Trucks from Padda Roadlines hauling from Cress Pit to Pic River West | 6 | D004-D015 | Pic River | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1010320210929-4L.O.A.3630 | Corbiere and Sons Contracting1010320210929-4L.O.A.3630INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10103 | 20210929-4 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 34.5 | Dynamic | 41.4 | 0 |  |  | 1904.4 | 247.572 | 2151.972 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 3 Trucks from Padda Roadlines hauling from Cress Pit to Pic River West | 6 | D004-D015 | Pic River | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1010320210929-4Dump - Triaxle- After Jan 1034.51904.4 | Corbiere and Sons Contracting1010320210929-4Dump - Triaxle- After Jan 1034.51904.4INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10102 | 20210929-3 | 53510604 | Access | 0 | Labourer - General - After Jan 10 | 60 | 12 | HR |  |  | 60 | 0 | 720 | 93.6 | 813.6 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit (7 trucks) - 1 Valentino Truck | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1010220210929-3Labourer - General - After Jan 1012720 | Corbiere and Sons Contracting1010220210929-3Labourer - General - After Jan 1012720INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10102 | 20210929-3 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 12 | HR |  |  | 70 | 0 | 840 | 109.2 | 949.2 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit (7 trucks) - 1 Valentino Truck | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1010220210929-3Driver - AZ - After Jan 1012840 | Corbiere and Sons Contracting1010220210929-3Driver - AZ - After Jan 1012840INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10102 | 20210929-3 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 81 | HR |  |  | 70 | 0 | 5670 | 737.1 | 6407.1 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit (7 trucks) - 1 Valentino Truck | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1010220210929-3Driver - AZ - After Jan 10815670 | Corbiere and Sons Contracting1010220210929-3Driver - AZ - After Jan 10815670INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10102 | 20210929-3 | 53510604 | Access | 0 | L.O.A. | 210 | 8 | DAY |  |  |  | 0 | 1680 | 218.4 | 1898.4 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit (7 trucks) - 1 Valentino Truck | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1010220210929-3L.O.A.81680 | Corbiere and Sons Contracting1010220210929-3L.O.A.81680INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10102 | 20210929-3 | 53510604 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit (7 trucks) - 1 Valentino Truck | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1010220210929-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1010220210929-3Light Truck - Pick up- After Jan 101243.75INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10102 | 20210929-3 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 12 | Dynamic | 41.4 | 0 |  |  | 662.4 | 86.112 | 748.512 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit (7 trucks) - 1 Valentino Truck | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1010220210929-3Dump - Triaxle- After Jan 1012662.4 | Corbiere and Sons Contracting1010220210929-3Dump - Triaxle- After Jan 1012662.4INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10102 | 20210929-3 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 81 | Dynamic | 41.4 | 0 |  |  | 4471.2 | 581.256 | 5052.456 | 2021-09-29 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit (7 trucks) - 1 Valentino Truck | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1010220210929-3Dump - Triaxle- After Jan 10814471.2 | Corbiere and Sons Contracting1010220210929-3Dump - Triaxle- After Jan 10814471.2INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10091 | 20210928-6 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 46 | HR |  |  | 70 | 0 | 3220 | 418.6 | 3638.6 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling from Jackfish Pit to Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1009120210928-6Driver - AZ - After Jan 10463220 | Corbiere and Sons Contracting1009120210928-6Driver - AZ - After Jan 10463220INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10091 | 20210928-6 | 53510604 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling from Jackfish Pit to Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1009120210928-6L.O.A.4840 | Corbiere and Sons Contracting1009120210928-6L.O.A.4840INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10091 | 20210928-6 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 46 | Dynamic | 41.4 | 0 |  |  | 2539.2 | 330.096 | 2869.296 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling from Jackfish Pit to Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1009120210928-6Dump - Triaxle- After Jan 10462539.2 | Corbiere and Sons Contracting1009120210928-6Dump - Triaxle- After Jan 10462539.2INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10090 | 20210928-5 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 12 | HR |  |  | 70 | 0 | 840 | 109.2 | 949.2 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 4 Padda Trucks and 1 Hurd Bros Truck hauling to Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1009020210928-5Driver - AZ - After Jan 1012840 | Corbiere and Sons Contracting1009020210928-5Driver - AZ - After Jan 1012840INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10090 | 20210928-5 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 45.5 | HR |  |  | 70 | 0 | 3185 | 414.05 | 3599.05 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 4 Padda Trucks and 1 Hurd Bros Truck hauling to Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1009020210928-5Driver - AZ - After Jan 1045.53185 | Corbiere and Sons Contracting1009020210928-5Driver - AZ - After Jan 1045.53185INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10090 | 20210928-5 | 53510604 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 4 Padda Trucks and 1 Hurd Bros Truck hauling to Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1009020210928-5L.O.A.4840 | Corbiere and Sons Contracting1009020210928-5L.O.A.4840INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10090 | 20210928-5 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 12 | Dynamic | 41.4 | 0 |  |  | 662.4 | 86.112 | 748.512 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 4 Padda Trucks and 1 Hurd Bros Truck hauling to Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1009020210928-5Dump - Triaxle- After Jan 1012662.4 | Corbiere and Sons Contracting1009020210928-5Dump - Triaxle- After Jan 1012662.4INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10090 | 20210928-5 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 45.5 | Dynamic | 41.4 | 0 |  |  | 2511.6 | 326.508 | 2838.108 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 4 Padda Trucks and 1 Hurd Bros Truck hauling to Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1009020210928-5Dump - Triaxle- After Jan 1045.52511.6 | Corbiere and Sons Contracting1009020210928-5Dump - Triaxle- After Jan 1045.52511.6INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10088 | 20210928-4 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 23 | HR |  |  | 70 | 0 | 1610 | 209.3 | 1819.3 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 2 Trucks from Padda Roadlines hauling from Cress Pit to Pic River West | 6 | D004-D015 | Pic River | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1008820210928-4Driver - AZ - After Jan 10231610 | Corbiere and Sons Contracting1008820210928-4Driver - AZ - After Jan 10231610INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10088 | 20210928-4 | 53510604 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 2 Trucks from Padda Roadlines hauling from Cress Pit to Pic River West | 6 | D004-D015 | Pic River | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1008820210928-4L.O.A.2420 | Corbiere and Sons Contracting1008820210928-4L.O.A.2420INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10088 | 20210928-4 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 23 | Dynamic | 41.4 |  |  |  | 1269.6 | 165.048 | 1434.648 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 2 Trucks from Padda Roadlines hauling from Cress Pit to Pic River West | 6 | D004-D015 | Pic River | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1008820210928-4Dump - Triaxle- After Jan 10231269.6 | Corbiere and Sons Contracting1008820210928-4Dump - Triaxle- After Jan 10231269.6INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10087 | 20210928-3 | 53510604 | Access | 0 | Labourer - General - After Jan 10 | 60 | 12 | HR |  |  | 60 | 0 | 720 | 93.6 | 813.6 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit (5 trucks) - 1 Valentino Truck | 6 | C257-C267 | Hare Lake | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1008720210928-3Labourer - General - After Jan 1012720 | Corbiere and Sons Contracting1008720210928-3Labourer - General - After Jan 1012720INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10087 | 20210928-3 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 12 | HR |  |  | 70 | 0 | 840 | 109.2 | 949.2 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit (5 trucks) - 1 Valentino Truck | 6 | C257-C267 | Hare Lake | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1008720210928-3Driver - AZ - After Jan 1012840 | Corbiere and Sons Contracting1008720210928-3Driver - AZ - After Jan 1012840INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10087 | 20210928-3 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 56.5 | HR |  |  | 70 | 0 | 3955 | 514.15 | 4469.15 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit (5 trucks) - 1 Valentino Truck | 6 | C257-C267 | Hare Lake | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1008720210928-3Driver - AZ - After Jan 1056.53955 | Corbiere and Sons Contracting1008720210928-3Driver - AZ - After Jan 1056.53955INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10087 | 20210928-3 | 53510604 | Access | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit (5 trucks) - 1 Valentino Truck | 6 | C257-C267 | Hare Lake | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1008720210928-3L.O.A.61260 | Corbiere and Sons Contracting1008720210928-3L.O.A.61260INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10087 | 20210928-3 | 53510604 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit (5 trucks) - 1 Valentino Truck | 6 | C257-C267 | Hare Lake | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1008720210928-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1008720210928-3Light Truck - Pick up- After Jan 101243.75INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10087 | 20210928-3 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 12 | Dynamic | 41.4 | 0 |  |  | 662.4 | 86.112 | 748.512 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit (5 trucks) - 1 Valentino Truck | 6 | C257-C267 | Hare Lake | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1008720210928-3Dump - Triaxle- After Jan 1012662.4 | Corbiere and Sons Contracting1008720210928-3Dump - Triaxle- After Jan 1012662.4INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10087 | 20210928-3 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 56.5 | Dynamic | 41.4 | 0 |  |  | 3118.8 | 405.444 | 3524.244 | 2021-09-28 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit (5 trucks) - 1 Valentino Truck | 6 | C257-C267 | Hare Lake | 0 | 2021-10-05 |  | 58 | 2021-10-07 | [6 empty] | 06 | Corbiere and Sons Contracting1008720210928-3Dump - Triaxle- After Jan 1056.53118.8 | Corbiere and Sons Contracting1008720210928-3Dump - Triaxle- After Jan 1056.53118.8INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10053 | 20210926-5 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 69 | HR |  |  | 70 | 0 | 4830 | 627.9 | 5457.9 | 2021-09-26 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 6 Padda trucks hauling from Cress Pit to Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-04 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1005320210926-5Driver - AZ - After Jan 10694830 | Corbiere and Sons Contracting1005320210926-5Driver - AZ - After Jan 10694830INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10053 | 20210926-5 | 53510604 | Access | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2021-09-26 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 6 Padda trucks hauling from Cress Pit to Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-04 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1005320210926-5L.O.A.61260 | Corbiere and Sons Contracting1005320210926-5L.O.A.61260INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10053 | 20210926-5 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 69 | Dynamic | 41.4 | 0 |  |  | 3808.8 | 495.144 | 4303.944 | 2021-09-26 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 6 Padda trucks hauling from Cress Pit to Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-04 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1005320210926-5Dump - Triaxle- After Jan 10693808.8 | Corbiere and Sons Contracting1005320210926-5Dump - Triaxle- After Jan 10693808.8INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10052 | 20210926-4 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 34.5 | HR |  |  | 70 | 0 | 2415 | 313.95 | 2728.95 | 2021-09-26 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 3Trucks from Padda Roadlines hauling from Cress Pit to Dead Horse | 6 | C203-C209 | Dead Horse | 0 | 2021-10-04 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1005220210926-4Driver - AZ - After Jan 1034.52415 | Corbiere and Sons Contracting1005220210926-4Driver - AZ - After Jan 1034.52415INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10052 | 20210926-4 | 53510604 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-09-26 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 3Trucks from Padda Roadlines hauling from Cress Pit to Dead Horse | 6 | C203-C209 | Dead Horse | 0 | 2021-10-04 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1005220210926-4L.O.A.3630 | Corbiere and Sons Contracting1005220210926-4L.O.A.3630INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10052 | 20210926-4 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 34.5 | Dynamic | 41.4 | 0 |  |  | 1904.4 | 247.572 | 2151.972 | 2021-09-26 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 3Trucks from Padda Roadlines hauling from Cress Pit to Dead Horse | 6 | C203-C209 | Dead Horse | 0 | 2021-10-04 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1005220210926-4Dump - Triaxle- After Jan 1034.51904.4 | Corbiere and Sons Contracting1005220210926-4Dump - Triaxle- After Jan 1034.51904.4INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10051 | 20210926-3 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 103.5 | HR |  |  | 70 | 0 | 7245 | 941.85 | 8186.85 | 2021-09-26 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit (9 trucks) | 6 | C257-C267 | Hare Lake | 0 | 2021-10-04 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1005120210926-3Driver - AZ - After Jan 10103.57245 | Corbiere and Sons Contracting1005120210926-3Driver - AZ - After Jan 10103.57245INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10051 | 20210926-3 | 53510604 | Access | 0 | L.O.A. | 210 | 10 | DAY |  |  |  | 0 | 2100 | 273 | 2373 | 2021-09-26 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit (9 trucks) | 6 | C257-C267 | Hare Lake | 0 | 2021-10-04 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1005120210926-3L.O.A.102100 | Corbiere and Sons Contracting1005120210926-3L.O.A.102100INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10051 | 20210926-3 | 53510604 | Access | 0 | Construction Coordinator | 80 | 7 | HR |  |  | 80 | 0 | 560 | 72.8 | 632.8 | 2021-09-26 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit (9 trucks) | 6 | C257-C267 | Hare Lake | 0 | 2021-10-04 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1005120210926-3Construction Coordinator7560 | Corbiere and Sons Contracting1005120210926-3Construction Coordinator7560INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10051 | 20210926-3 | 53510604 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-09-26 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit (9 trucks) | 6 | C257-C267 | Hare Lake | 0 | 2021-10-04 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1005120210926-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1005120210926-3Light Truck - Pick up- After Jan 101243.75INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10051 | 20210926-3 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 103.5 | Dynamic | 41.4 | 0 |  |  | 5713.2 | 742.716 | 6455.916 | 2021-09-26 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit (9 trucks) | 6 | C257-C267 | Hare Lake | 0 | 2021-10-04 |  | 58 | 2021-10-08 | [6 empty] | 06 | Corbiere and Sons Contracting1005120210926-3Dump - Triaxle- After Jan 10103.55713.2 | Corbiere and Sons Contracting1005120210926-3Dump - Triaxle- After Jan 10103.55713.2INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10038 | 20210925-5 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 13 | HR |  |  | 70 | 0 | 910 | 118.3 | 1028.3 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 1 Valentino and 1 Hurd truck hauling to Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1003820210925-5Driver - AZ - After Jan 1013910 | Corbiere and Sons Contracting1003820210925-5Driver - AZ - After Jan 1013910INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10038 | 20210925-5 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 4 | HR |  |  | 70 | 0 | 280 | 36.4 | 316.4 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 1 Valentino and 1 Hurd truck hauling to Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1003820210925-5Driver - AZ - After Jan 104280 | Corbiere and Sons Contracting1003820210925-5Driver - AZ - After Jan 104280INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10038 | 20210925-5 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 13 | Dynamic | 41.4 | 0 |  |  | 717.6 | 93.288 | 810.888 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 1 Valentino and 1 Hurd truck hauling to Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1003820210925-5Dump - Triaxle- After Jan 1013717.6 | Corbiere and Sons Contracting1003820210925-5Dump - Triaxle- After Jan 1013717.6INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10038 | 20210925-5 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 4 | Dynamic | 41.4 | 0 |  |  | 220.8 | 28.704 | 249.504 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 1 Valentino and 1 Hurd truck hauling to Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1003820210925-5Dump - Triaxle- After Jan 104220.8 | Corbiere and Sons Contracting1003820210925-5Dump - Triaxle- After Jan 104220.8INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10037 | 20210925-4 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 57.5 | HR |  |  | 70 | 0 | 4025 | 523.25 | 4548.25 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 5 Trucks from Padda Roadlines hauling from Cress Pit to Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1003720210925-4Driver - AZ - After Jan 1057.54025 | Corbiere and Sons Contracting1003720210925-4Driver - AZ - After Jan 1057.54025INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10037 | 20210925-4 | 53510604 | Access | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 5 Trucks from Padda Roadlines hauling from Cress Pit to Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1003720210925-4L.O.A.51050 | Corbiere and Sons Contracting1003720210925-4L.O.A.51050INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10037 | 20210925-4 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 57.5 | Dynamic | 41.4 | 0 |  |  | 3174 | 412.62 | 3586.62 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 5 Trucks from Padda Roadlines hauling from Cress Pit to Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1003720210925-4Dump - Triaxle- After Jan 1057.53174 | Corbiere and Sons Contracting1003720210925-4Dump - Triaxle- After Jan 1057.53174INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10035 | 20210925-3 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 150.5 | HR |  |  | 70 | 0 | 10535 | 1369.55 | 11904.55 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit (11 trucks) - 2 Trucks Mobilized | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1003520210925-3Driver - AZ - After Jan 10150.510535 | Corbiere and Sons Contracting1003520210925-3Driver - AZ - After Jan 10150.510535INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10035 | 20210925-3 | 53510604 | Access | 0 | L.O.A. | 210 | 14 | DAY |  |  |  | 0 | 2940 | 382.2 | 3322.2 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit (11 trucks) - 2 Trucks Mobilized | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1003520210925-3L.O.A.142940 | Corbiere and Sons Contracting1003520210925-3L.O.A.142940INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10035 | 20210925-3 | 53510604 | Access | 0 | Construction Coordinator | 80 | 7 | HR |  |  | 80 | 0 | 560 | 72.8 | 632.8 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit (11 trucks) - 2 Trucks Mobilized | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1003520210925-3Construction Coordinator7560 | Corbiere and Sons Contracting1003520210925-3Construction Coordinator7560INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10035 | 20210925-3 | 53510604 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit (11 trucks) - 2 Trucks Mobilized | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1003520210925-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1003520210925-3Light Truck - Pick up- After Jan 101243.75INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10035 | 20210925-3 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 150.5 | Dynamic | 41.4 | 0 |  |  | 8307.6 | 1079.988 | 9387.588 | 2021-09-25 | 0 | INV #150 | 2021-10-15 | 165 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling to Hare Lake road stockpile from Cress Pit (11 trucks) - 2 Trucks Mobilized | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-10-04 |  | 37 | 2021-10-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1003520210925-3Dump - Triaxle- After Jan 10150.58307.6 | Corbiere and Sons Contracting1003520210925-3Dump - Triaxle- After Jan 10150.58307.6INV #150 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10215 | 20211007-6 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 2 | Dynamic | 98.61 | 0 |  |  | 262.96 | 34.1848 | 297.1448 | 2021-10-07 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Utilization of DZ to pull out pickup | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-14 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1021520211007-6Dozer D6 or equal- After Jan 102262.96 | Corbiere and Sons Contracting1021520211007-6Dozer D6 or equal- After Jan 102262.96INV #151 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10199 | 20211005-9 | 53510602 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 12 | HR |  |  | 70 | 0 | 840 | 109.2 | 949.2 | 2021-10-05 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1019920211005-9Driver - AZ - After Jan 1012840 | Corbiere and Sons Contracting1019920211005-9Driver - AZ - After Jan 1012840INV #151 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10199 | 20211005-9 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 32 | HR |  |  | 75 | 0 | 2400 | 312 | 2712 | 2021-10-05 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1019920211005-9Operator - Principle - After Jan 10322400 | Corbiere and Sons Contracting1019920211005-9Operator - Principle - After Jan 10322400INV #151 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10199 | 20211005-9 | 53510602 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2021-10-05 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1019920211005-9L.O.A.4840 | Corbiere and Sons Contracting1019920211005-9L.O.A.4840INV #151 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10199 | 20211005-9 | 53510602 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 12 | Dynamic | 91.79 | 0 |  |  | 1468.68 | 190.9284 | 1659.6084 | 2021-10-05 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1019920211005-9Tractor Trailer - 60 Ton- After Jan 10121468.68 | Corbiere and Sons Contracting1019920211005-9Tractor Trailer - 60 Ton- After Jan 10121468.68INV #151 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10199 | 20211005-9 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 10 | Dynamic | 103.54 | 0 |  |  | 1380.5 | 179.465 | 1559.965 | 2021-10-05 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1019920211005-9Rock Truck - 30 Ton- After Jan 10101380.5 | Corbiere and Sons Contracting1019920211005-9Rock Truck - 30 Ton- After Jan 10101380.5INV #151 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10199 | 20211005-9 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-10-05 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1019920211005-9Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1019920211005-9Light Truck - Pick up- After Jan 101243.75INV #151 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10199 | 20211005-9 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 7 | HR | 9.16 | 0 |  |  | 85.47 | 11.1111 | 96.5811 | 2021-10-05 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1019920211005-9Excavator Thumb - 30 - 50 ton- After Jan 10785.47 | Corbiere and Sons Contracting1019920211005-9Excavator Thumb - 30 - 50 ton- After Jan 10785.47INV #151 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10199 | 20211005-9 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10 | Dynamic | 110.22 | 0 |  |  | 1469.6 | 191.048 | 1660.648 | 2021-10-05 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1019920211005-9Excavator - 36 ton- After Jan 10101469.6 | Corbiere and Sons Contracting1019920211005-9Excavator - 36 ton- After Jan 10101469.6INV #151 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10199 | 20211005-9 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 7 | Dynamic | 110.22 | 0 |  |  | 1028.72 | 133.7336 | 1162.4536 | 2021-10-05 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Creek | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1019920211005-9Excavator - 36 ton- After Jan 1071028.72 | Corbiere and Sons Contracting1019920211005-9Excavator - 36 ton- After Jan 1071028.72INV #151 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10198 | 20211005-8 | 53510602 | Access | 0 | Labourer - General - After Jan 10 | 60 | 13 | HR |  |  | 60 | 0 | 780 | 101.4 | 881.4 | 2021-10-05 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acitivities from Mink Cre | 6 | C237-C247 | Mink | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1019820211005-8Labourer - General - After Jan 1013780 | Corbiere and Sons Contracting1019820211005-8Labourer - General - After Jan 1013780INV #151 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10198 | 20211005-8 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 48 | HR |  |  | 75 | 0 | 3600 | 468 | 4068 | 2021-10-05 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acitivities from Mink Cre | 6 | C237-C247 | Mink | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1019820211005-8Operator - Principle - After Jan 10483600 | Corbiere and Sons Contracting1019820211005-8Operator - Principle - After Jan 10483600INV #151 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10198 | 20211005-8 | 53510602 | Access | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2021-10-05 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acitivities from Mink Cre | 6 | C237-C247 | Mink | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1019820211005-8L.O.A.61260 | Corbiere and Sons Contracting1019820211005-8L.O.A.61260INV #151 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10198 | 20211005-8 | 53510602 | Access | 0 | Foreman | 95 | 13 | HR |  |  | 95 | 0 | 1235 | 160.55 | 1395.55 | 2021-10-05 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acitivities from Mink Cre | 6 | C237-C247 | Mink | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1019820211005-8Foreman131235 | Corbiere and Sons Contracting1019820211005-8Foreman131235INV #151 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10198 | 20211005-8 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 12 | Dynamic | 103.54 | 0 |  |  | 1656.6 | 215.358 | 1871.958 | 2021-10-05 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acitivities from Mink Cre | 6 | C237-C247 | Mink | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1019820211005-8Rock Truck - 30 Ton- After Jan 10121656.6 | Corbiere and Sons Contracting1019820211005-8Rock Truck - 30 Ton- After Jan 10121656.6INV #151 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10198 | 20211005-8 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 5 | DAY | 182.81 | 0 |  |  | 1218.75 | 158.4375 | 1377.1875 | 2021-10-05 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acitivities from Mink Cre | 6 | C237-C247 | Mink | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1019820211005-8Light Truck - Pick up- After Jan 1051218.75 | Corbiere and Sons Contracting1019820211005-8Light Truck - Pick up- After Jan 1051218.75INV #151 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10198 | 20211005-8 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 8 | HR | 9.16 | 0 |  |  | 97.68 | 12.6984 | 110.3784 | 2021-10-05 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acitivities from Mink Cre | 6 | C237-C247 | Mink | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1019820211005-8Excavator Thumb - 30 - 50 ton- After Jan 10897.68 | Corbiere and Sons Contracting1019820211005-8Excavator Thumb - 30 - 50 ton- After Jan 10897.68INV #151 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10198 | 20211005-8 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 8 | Dynamic | 110.22 | 0 |  |  | 1175.68 | 152.8384 | 1328.5184 | 2021-10-05 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acitivities from Mink Cre | 6 | C237-C247 | Mink | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1019820211005-8Excavator - 36 ton- After Jan 1081175.68 | Corbiere and Sons Contracting1019820211005-8Excavator - 36 ton- After Jan 1081175.68INV #151 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10198 | 20211005-8 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 12 | Dynamic | 110.22 | 0 |  |  | 1763.52 | 229.2576 | 1992.7776 | 2021-10-05 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acitivities from Mink Cre | 6 | C237-C247 | Mink | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1019820211005-8Excavator - 36 ton- After Jan 10121763.52 | Corbiere and Sons Contracting1019820211005-8Excavator - 36 ton- After Jan 10121763.52INV #151 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10198 | 20211005-8 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 12 | Dynamic | 98.61 | 0 |  |  | 1577.76 | 205.1088 | 1782.8688 | 2021-10-05 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building acitivities from Mink Cre | 6 | C237-C247 | Mink | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1019820211005-8Dozer D6 or equal- After Jan 10121577.76 | Corbiere and Sons Contracting1019820211005-8Dozer D6 or equal- After Jan 10121577.76INV #151 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10197 | 20211005-7 | 53510602 | Access | 0 | Labourer - General - After Jan 10 | 60 | 13 | HR |  |  | 60 | 0 | 780 | 101.4 | 881.4 | 2021-10-05 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake Road | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1019720211005-7Labourer - General - After Jan 1013780 | Corbiere and Sons Contracting1019720211005-7Labourer - General - After Jan 1013780INV #151 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10197 | 20211005-7 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 78 | HR |  |  | 75 | 0 | 5850 | 760.5 | 6610.5 | 2021-10-05 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake Road | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1019720211005-7Operator - Principle - After Jan 10785850 | Corbiere and Sons Contracting1019720211005-7Operator - Principle - After Jan 10785850INV #151 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10197 | 20211005-7 | 53510602 | Access | 0 | L.O.A. | 210 | 8 | DAY |  |  |  | 0 | 1680 | 218.4 | 1898.4 | 2021-10-05 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake Road | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1019720211005-7L.O.A.81680 | Corbiere and Sons Contracting1019720211005-7L.O.A.81680INV #151 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10197 | 20211005-7 | 53510602 | Access | 0 | Foreman | 95 | 13 | HR |  |  | 95 | 0 | 1235 | 160.55 | 1395.55 | 2021-10-05 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake Road | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1019720211005-7Foreman131235 | Corbiere and Sons Contracting1019720211005-7Foreman131235INV #151 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10197 | 20211005-7 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 24 | Dynamic | 103.54 | 0 |  |  | 3313.2 | 430.716 | 3743.916 | 2021-10-05 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake Road | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1019720211005-7Rock Truck - 30 Ton- After Jan 10243313.2 | Corbiere and Sons Contracting1019720211005-7Rock Truck - 30 Ton- After Jan 10243313.2INV #151 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10197 | 20211005-7 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 5 | DAY | 182.81 | 0 |  |  | 1218.75 | 158.4375 | 1377.1875 | 2021-10-05 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake Road | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1019720211005-7Light Truck - Pick up- After Jan 1051218.75 | Corbiere and Sons Contracting1019720211005-7Light Truck - Pick up- After Jan 1051218.75INV #151 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10197 | 20211005-7 | 53510602 | Access | 0 | ATV - Side by Side w/ roll bar- After Jan 10 | 18.45 | 10 | HR | 13.84 | 0 |  |  | 184.5 | 23.985 | 208.485 | 2021-10-05 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake Road | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1019720211005-7ATV - Side by Side w/ roll bar- After Jan 1010184.5 | Corbiere and Sons Contracting1019720211005-7ATV - Side by Side w/ roll bar- After Jan 1010184.5INV #151 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10197 | 20211005-7 | 53510602 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 12 | HR | 47.54 | 0 |  |  | 760.56 | 98.8728 | 859.4328 | 2021-10-05 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake Road | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1019720211005-7Excavator Hammer - 30 - 50 ton- After Jan 1012760.56 | Corbiere and Sons Contracting1019720211005-7Excavator Hammer - 30 - 50 ton- After Jan 1012760.56INV #151 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10197 | 20211005-7 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 36 | HR | 9.16 | 0 |  |  | 439.56 | 57.1428 | 496.7028 | 2021-10-05 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake Road | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1019720211005-7Excavator Thumb - 30 - 50 ton- After Jan 1036439.56 | Corbiere and Sons Contracting1019720211005-7Excavator Thumb - 30 - 50 ton- After Jan 1036439.56INV #151 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10197 | 20211005-7 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 24 | Dynamic | 110.22 | 0 |  |  | 3527.04 | 458.5152 | 3985.5552 | 2021-10-05 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake Road | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1019720211005-7Excavator - 36 ton- After Jan 10243527.04 | Corbiere and Sons Contracting1019720211005-7Excavator - 36 ton- After Jan 10243527.04INV #151 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10197 | 20211005-7 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 12 | Dynamic | 110.22 | 0 |  |  | 1763.52 | 229.2576 | 1992.7776 | 2021-10-05 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake Road | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1019720211005-7Excavator - 36 ton- After Jan 10121763.52 | Corbiere and Sons Contracting1019720211005-7Excavator - 36 ton- After Jan 10121763.52INV #151 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10197 | 20211005-7 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 12 | Dynamic | 103.84 | 0 |  |  | 1661.4 | 215.982 | 1877.382 | 2021-10-05 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Del Lake Road | 6 | C186-C195 | Del Lake Road | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1019720211005-7Excavator - 30 ton- After Jan 10121661.4 | Corbiere and Sons Contracting1019720211005-7Excavator - 30 ton- After Jan 10121661.4INV #151 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10195 | 20211005-5 | 53510602 | Access | 0 | Labourer - General - After Jan 10 | 60 | 12 | HR |  |  | 60 | 0 | 720 | 93.6 | 813.6 | 2021-10-05 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1019520211005-5Labourer - General - After Jan 1012720 | Corbiere and Sons Contracting1019520211005-5Labourer - General - After Jan 1012720INV #151 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10195 | 20211005-5 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 70 | HR |  |  | 75 | 0 | 5250 | 682.5 | 5932.5 | 2021-10-05 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1019520211005-5Operator - Principle - After Jan 10705250 | Corbiere and Sons Contracting1019520211005-5Operator - Principle - After Jan 10705250INV #151 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10195 | 20211005-5 | 53510602 | Access | 0 | L.O.A. | 210 | 7 | DAY |  |  |  | 0 | 1470 | 191.1 | 1661.1 | 2021-10-05 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1019520211005-5L.O.A.71470 | Corbiere and Sons Contracting1019520211005-5L.O.A.71470INV #151 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10195 | 20211005-5 | 53510602 | Access | 0 | Foreman | 95 | 13 | HR |  |  | 95 | 0 | 1235 | 160.55 | 1395.55 | 2021-10-05 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1019520211005-5Foreman131235 | Corbiere and Sons Contracting1019520211005-5Foreman131235INV #151 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10195 | 20211005-5 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 39 | Dynamic | 103.54 | 0 |  |  | 5383.95 | 699.9135 | 6083.8635 | 2021-10-05 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1019520211005-5Rock Truck - 30 Ton- After Jan 10395383.95 | Corbiere and Sons Contracting1019520211005-5Rock Truck - 30 Ton- After Jan 10395383.95INV #151 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10195 | 20211005-5 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 4 | DAY | 182.81 | 0 |  |  | 975 | 126.75 | 1101.75 | 2021-10-05 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1019520211005-5Light Truck - Pick up- After Jan 104975 | Corbiere and Sons Contracting1019520211005-5Light Truck - Pick up- After Jan 104975INV #151 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10195 | 20211005-5 | 53510602 | Access | 0 | ATV - Side by Side w/ roll bar- After Jan 10 | 18.45 | 10 | HR | 13.84 | 0 |  |  | 184.5 | 23.985 | 208.485 | 2021-10-05 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1019520211005-5ATV - Side by Side w/ roll bar- After Jan 1010184.5 | Corbiere and Sons Contracting1019520211005-5ATV - Side by Side w/ roll bar- After Jan 1010184.5INV #151 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10195 | 20211005-5 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 13 | HR | 9.16 | 0 |  |  | 158.73 | 20.6349 | 179.3649 | 2021-10-05 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1019520211005-5Excavator Thumb - 30 - 50 ton- After Jan 1013158.73 | Corbiere and Sons Contracting1019520211005-5Excavator Thumb - 30 - 50 ton- After Jan 1013158.73INV #151 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10195 | 20211005-5 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 13 | Dynamic | 103.84 | 0 |  |  | 1799.85 | 233.9805 | 2033.8305 | 2021-10-05 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1019520211005-5Excavator - 30 ton- After Jan 10131799.85 | Corbiere and Sons Contracting1019520211005-5Excavator - 30 ton- After Jan 10131799.85INV #151 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10195 | 20211005-5 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 13 | Dynamic | 98.61 | 0 |  |  | 1709.24 | 222.2012 | 1931.4412 | 2021-10-05 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Building activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1019520211005-5Dozer D6 or equal- After Jan 10131709.24 | Corbiere and Sons Contracting1019520211005-5Dozer D6 or equal- After Jan 10131709.24INV #151 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10194 | 20211005-4 | 53510602 | Access | 0 | Labourer - General - After Jan 10 | 60 | 13 | HR |  |  | 60 | 0 | 780 | 101.4 | 881.4 | 2021-10-04 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1019420211005-4Labourer - General - After Jan 1013780 | Corbiere and Sons Contracting1019420211005-4Labourer - General - After Jan 1013780INV #151 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10194 | 20211005-4 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 65 | HR |  |  | 75 | 0 | 4875 | 633.75 | 5508.75 | 2021-10-04 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1019420211005-4Operator - Principle - After Jan 10654875 | Corbiere and Sons Contracting1019420211005-4Operator - Principle - After Jan 10654875INV #151 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10194 | 20211005-4 | 53510602 | Access | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2021-10-04 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1019420211005-4L.O.A.61260 | Corbiere and Sons Contracting1019420211005-4L.O.A.61260INV #151 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10194 | 20211005-4 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 24 | Dynamic | 103.54 | 0 |  |  | 3313.2 | 430.716 | 3743.916 | 2021-10-04 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1019420211005-4Rock Truck - 30 Ton- After Jan 10243313.2 | Corbiere and Sons Contracting1019420211005-4Rock Truck - 30 Ton- After Jan 10243313.2INV #151 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10194 | 20211005-4 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2021-10-04 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1019420211005-4Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting1019420211005-4Light Truck - Pick up- After Jan 103731.25INV #151 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10194 | 20211005-4 | 53510602 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 12 | HR | 47.54 | 0 |  |  | 760.56 | 98.8728 | 859.4328 | 2021-10-04 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1019420211005-4Excavator Hammer - 30 - 50 ton- After Jan 1012760.56 | Corbiere and Sons Contracting1019420211005-4Excavator Hammer - 30 - 50 ton- After Jan 1012760.56INV #151 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10194 | 20211005-4 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 12 | HR | 9.16 | 0 |  |  | 146.52 | 19.0476 | 165.5676 | 2021-10-04 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1019420211005-4Excavator Thumb - 30 - 50 ton- After Jan 1012146.52 | Corbiere and Sons Contracting1019420211005-4Excavator Thumb - 30 - 50 ton- After Jan 1012146.52INV #151 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10194 | 20211005-4 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 12 | Dynamic | 110.22 | 0 |  |  | 1763.52 | 229.2576 | 1992.7776 | 2021-10-04 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1019420211005-4Excavator - 36 ton- After Jan 10121763.52 | Corbiere and Sons Contracting1019420211005-4Excavator - 36 ton- After Jan 10121763.52INV #151 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10194 | 20211005-4 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 12 | Dynamic | 103.84 | 0 |  |  | 1661.4 | 215.982 | 1877.382 | 2021-10-04 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1019420211005-4Excavator - 30 ton- After Jan 10121661.4 | Corbiere and Sons Contracting1019420211005-4Excavator - 30 ton- After Jan 10121661.4INV #151 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10194 | 20211005-4 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 12 | Dynamic | 98.61 | 0 |  |  | 1577.76 | 205.1088 | 1782.8688 | 2021-10-04 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Little Red Sucker Creek Road | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1019420211005-4Dozer D6 or equal- After Jan 10121577.76 | Corbiere and Sons Contracting1019420211005-4Dozer D6 or equal- After Jan 10121577.76INV #151 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10201 | 20211005-11 | 53510602 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 54 | HR |  |  | 75 | 0 | 4050 | 526.5 | 4576.5 | 2021-10-05 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1020120211005-11Operator - Principle - After Jan 10544050 | Corbiere and Sons Contracting1020120211005-11Operator - Principle - After Jan 10544050INV #151 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10201 | 20211005-11 | 53510602 | Access | 0 | Foreman | 95 | 10 | HR |  |  | 95 | 0 | 950 | 123.5 | 1073.5 | 2021-10-05 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1020120211005-11Foreman10950 | Corbiere and Sons Contracting1020120211005-11Foreman10950INV #151 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10201 | 20211005-11 | 53510602 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 10 | Dynamic | 103.54 | 0 |  |  | 1380.5 | 179.465 | 1559.965 | 2021-10-05 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1020120211005-11Rock Truck - 30 Ton- After Jan 10101380.5 | Corbiere and Sons Contracting1020120211005-11Rock Truck - 30 Ton- After Jan 10101380.5INV #151 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10201 | 20211005-11 | 53510602 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 5 | DAY | 182.81 | 0 |  |  | 1218.75 | 158.4375 | 1377.1875 | 2021-10-05 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1020120211005-11Light Truck - Pick up- After Jan 1051218.75 | Corbiere and Sons Contracting1020120211005-11Light Truck - Pick up- After Jan 1051218.75INV #151 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10201 | 20211005-11 | 53510602 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 28 | HR | 9.16 | 0 |  |  | 341.88 | 44.4444 | 386.3244 | 2021-10-05 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1020120211005-11Excavator Thumb - 30 - 50 ton- After Jan 1028341.88 | Corbiere and Sons Contracting1020120211005-11Excavator Thumb - 30 - 50 ton- After Jan 1028341.88INV #151 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10201 | 20211005-11 | 53510602 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 17 | Dynamic | 110.22 | 0 |  |  | 2498.32 | 324.7816 | 2823.1016 | 2021-10-05 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1020120211005-11Excavator - 36 ton- After Jan 10172498.32 | Corbiere and Sons Contracting1020120211005-11Excavator - 36 ton- After Jan 10172498.32INV #151 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10201 | 20211005-11 | 53510602 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2021-10-05 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1020120211005-11Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting1020120211005-11Excavator - 30 ton- After Jan 10111522.95INV #151 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10201 | 20211005-11 | 53510602 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-10-05 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1020120211005-11Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting1020120211005-11Dozer D6 or equal- After Jan 10111446.28INV #151 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 10222 | 20211008-4 | 53530601 | Rig/Access Mats | 0 | Driver - AZ - After Jan 10 | 70 | 5 | HR |  |  | 70 | 0 | 350 | 45.5 | 395.5 | 2021-10-08 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Floating swamp mats over to 3 Fingers Lake Road | 6 | D009-D017 | Three Finger | 0 | 2021-10-15 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1022220211008-4Driver - AZ - After Jan 105350 | Corbiere and Sons Contracting1022220211008-4Driver - AZ - After Jan 105350INV #151 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Corbiere and Sons Contracting | 6 | 0 | 10222 | 20211008-4 | 53530601 | Rig/Access Mats | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-10-08 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Floating swamp mats over to 3 Fingers Lake Road | 6 | D009-D017 | Three Finger | 0 | 2021-10-15 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1022220211008-4L.O.A.1210 | Corbiere and Sons Contracting1022220211008-4L.O.A.1210INV #151 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Corbiere and Sons Contracting | 6 | 0 | 10222 | 20211008-4 | 53530601 | Rig/Access Mats | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 5 | Dynamic | 91.79 | 0 |  |  | 611.95 | 79.5535 | 691.5035 | 2021-10-08 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Floating swamp mats over to 3 Fingers Lake Road | 6 | D009-D017 | Three Finger | 0 | 2021-10-15 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1022220211008-4Tractor Trailer - 60 Ton- After Jan 105611.95 | Corbiere and Sons Contracting1022220211008-4Tractor Trailer - 60 Ton- After Jan 105611.95INV #151 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Corbiere and Sons Contracting | 6 | 0 | 10259 | 20211015-3 | 53510612 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 9 | HR |  |  | 75 | 0 | 675 | 87.75 | 762.75 | 2021-10-15 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance activities for 3 hours on Little Red Sucker | 6 | C248-C257 | Little Red Sucker | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1025920211015-3Operator - Principle - After Jan 109675 | Corbiere and Sons Contracting1025920211015-3Operator - Principle - After Jan 109675INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10259 | 20211015-3 | 53510612 | Access | 0 | Foreman | 95 | 4 | HR |  |  | 95 | 0 | 380 | 49.4 | 429.4 | 2021-10-15 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance activities for 3 hours on Little Red Sucker | 6 | C248-C257 | Little Red Sucker | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1025920211015-3Foreman4380 | Corbiere and Sons Contracting1025920211015-3Foreman4380INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10259 | 20211015-3 | 53510612 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 3 | Dynamic | 103.54 | 0 |  |  | 414.15 | 53.8395 | 467.9895 | 2021-10-15 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance activities for 3 hours on Little Red Sucker | 6 | C248-C257 | Little Red Sucker | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1025920211015-3Rock Truck - 30 Ton- After Jan 103414.15 | Corbiere and Sons Contracting1025920211015-3Rock Truck - 30 Ton- After Jan 103414.15INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10259 | 20211015-3 | 53510612 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-10-15 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance activities for 3 hours on Little Red Sucker | 6 | C248-C257 | Little Red Sucker | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1025920211015-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1025920211015-3Light Truck - Pick up- After Jan 101243.75INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10259 | 20211015-3 | 53510612 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 3 | HR | 9.16 | 0 |  |  | 36.63 | 4.7619 | 41.3919 | 2021-10-15 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance activities for 3 hours on Little Red Sucker | 6 | C248-C257 | Little Red Sucker | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1025920211015-3Excavator Thumb - 30 - 50 ton- After Jan 10336.63 | Corbiere and Sons Contracting1025920211015-3Excavator Thumb - 30 - 50 ton- After Jan 10336.63INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10259 | 20211015-3 | 53510612 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 3 | Dynamic | 110.22 | 0 |  |  | 440.88 | 57.3144 | 498.1944 | 2021-10-15 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance activities for 3 hours on Little Red Sucker | 6 | C248-C257 | Little Red Sucker | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1025920211015-3Excavator - 36 ton- After Jan 103440.88 | Corbiere and Sons Contracting1025920211015-3Excavator - 36 ton- After Jan 103440.88INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10259 | 20211015-3 | 53510612 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 3 | Dynamic | 98.61 | 0 |  |  | 394.44 | 51.2772 | 445.7172 | 2021-10-15 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance activities for 3 hours on Little Red Sucker | 6 | C248-C257 | Little Red Sucker | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1025920211015-3Dozer D6 or equal- After Jan 103394.44 | Corbiere and Sons Contracting1025920211015-3Dozer D6 or equal- After Jan 103394.44INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10256 | 20211014-5 | 53510612 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 24 | HR |  |  | 75 | 0 | 1800 | 234 | 2034 | 2021-10-14 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road capping and maintenance on Del from C190-C189 | 6 | C186-C195 | Del lake | 0 | 2021-10-18 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1025620211014-5Operator - Principle - After Jan 10241800 | Corbiere and Sons Contracting1025620211014-5Operator - Principle - After Jan 10241800INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10256 | 20211014-5 | 53510612 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-10-14 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road capping and maintenance on Del from C190-C189 | 6 | C186-C195 | Del lake | 0 | 2021-10-18 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1025620211014-5L.O.A.3630 | Corbiere and Sons Contracting1025620211014-5L.O.A.3630INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10256 | 20211014-5 | 53510612 | Access | 0 | Foreman | 95 | 6 | HR |  |  | 95 | 0 | 570 | 74.1 | 644.1 | 2021-10-14 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road capping and maintenance on Del from C190-C189 | 6 | C186-C195 | Del lake | 0 | 2021-10-18 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1025620211014-5Foreman6570 | Corbiere and Sons Contracting1025620211014-5Foreman6570INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10256 | 20211014-5 | 53510612 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-10-14 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road capping and maintenance on Del from C190-C189 | 6 | C186-C195 | Del lake | 0 | 2021-10-18 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1025620211014-5Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting1025620211014-5Rock Truck - 30 Ton- After Jan 10111518.55INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10256 | 20211014-5 | 53510612 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2021-10-14 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road capping and maintenance on Del from C190-C189 | 6 | C186-C195 | Del lake | 0 | 2021-10-18 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1025620211014-5Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting1025620211014-5Light Truck - Pick up- After Jan 103731.25INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10256 | 20211014-5 | 53510612 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-10-14 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road capping and maintenance on Del from C190-C189 | 6 | C186-C195 | Del lake | 0 | 2021-10-18 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1025620211014-5Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1025620211014-5Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10256 | 20211014-5 | 53510612 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-10-14 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road capping and maintenance on Del from C190-C189 | 6 | C186-C195 | Del lake | 0 | 2021-10-18 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1025620211014-5Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting1025620211014-5Excavator - 36 ton- After Jan 10111616.56INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10256 | 20211014-5 | 53510612 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-10-14 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road capping and maintenance on Del from C190-C189 | 6 | C186-C195 | Del lake | 0 | 2021-10-18 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1025620211014-5Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting1025620211014-5Dozer D6 or equal- After Jan 10111446.28INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10254 | 20211014-3 | 53510612 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 36 | HR |  |  | 75 | 0 | 2700 | 351 | 3051 | 2021-10-14 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance activities on Little Red Sucker | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1025420211014-3Operator - Principle - After Jan 10362700 | Corbiere and Sons Contracting1025420211014-3Operator - Principle - After Jan 10362700INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10254 | 20211014-3 | 53510612 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2021-10-14 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance activities on Little Red Sucker | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1025420211014-3L.O.A.4840 | Corbiere and Sons Contracting1025420211014-3L.O.A.4840INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10254 | 20211014-3 | 53510612 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-10-14 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance activities on Little Red Sucker | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1025420211014-3Foreman121140 | Corbiere and Sons Contracting1025420211014-3Foreman121140INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10254 | 20211014-3 | 53510612 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-10-14 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance activities on Little Red Sucker | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1025420211014-3Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting1025420211014-3Rock Truck - 30 Ton- After Jan 10111518.55INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10254 | 20211014-3 | 53510612 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2021-10-14 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance activities on Little Red Sucker | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1025420211014-3Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting1025420211014-3Light Truck - Pick up- After Jan 103731.25INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10254 | 20211014-3 | 53510612 | Access | 0 | ATV - Side by Side w/ roll bar- After Jan 10 | 18.45 | 10 | HR | 13.84 | 0 |  |  | 184.5 | 23.985 | 208.485 | 2021-10-14 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance activities on Little Red Sucker | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1025420211014-3ATV - Side by Side w/ roll bar- After Jan 1010184.5 | Corbiere and Sons Contracting1025420211014-3ATV - Side by Side w/ roll bar- After Jan 1010184.5INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10254 | 20211014-3 | 53510612 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-10-14 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance activities on Little Red Sucker | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1025420211014-3Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1025420211014-3Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10254 | 20211014-3 | 53510612 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-10-14 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance activities on Little Red Sucker | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1025420211014-3Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting1025420211014-3Excavator - 36 ton- After Jan 10111616.56INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10254 | 20211014-3 | 53510612 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-10-14 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance activities on Little Red Sucker | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1025420211014-3Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting1025420211014-3Dozer D6 or equal- After Jan 10111446.28INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10252 | 20211013-5 | 53510612 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 36 | HR |  |  | 75 | 0 | 2700 | 351 | 3051 | 2021-10-13 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road capping and maintenance on Del from C190-C189 | 6 | C186-C195 | Del Lake | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1025220211013-5Operator - Principle - After Jan 10362700 | Corbiere and Sons Contracting1025220211013-5Operator - Principle - After Jan 10362700INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10252 | 20211013-5 | 53510612 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2021-10-13 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road capping and maintenance on Del from C190-C189 | 6 | C186-C195 | Del Lake | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1025220211013-5L.O.A.4840 | Corbiere and Sons Contracting1025220211013-5L.O.A.4840INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10252 | 20211013-5 | 53510612 | Access | 0 | Foreman | 95 | 6 | HR |  |  | 95 | 0 | 570 | 74.1 | 644.1 | 2021-10-13 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road capping and maintenance on Del from C190-C189 | 6 | C186-C195 | Del Lake | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1025220211013-5Foreman6570 | Corbiere and Sons Contracting1025220211013-5Foreman6570INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10252 | 20211013-5 | 53510612 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-10-13 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road capping and maintenance on Del from C190-C189 | 6 | C186-C195 | Del Lake | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1025220211013-5Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting1025220211013-5Rock Truck - 30 Ton- After Jan 10111518.55INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10252 | 20211013-5 | 53510612 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2021-10-13 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road capping and maintenance on Del from C190-C189 | 6 | C186-C195 | Del Lake | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1025220211013-5Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting1025220211013-5Light Truck - Pick up- After Jan 103731.25INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10252 | 20211013-5 | 53510612 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 20 | HR | 9.16 | 0 |  |  | 244.2 | 31.746 | 275.946 | 2021-10-13 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road capping and maintenance on Del from C190-C189 | 6 | C186-C195 | Del Lake | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1025220211013-5Excavator Thumb - 30 - 50 ton- After Jan 1020244.2 | Corbiere and Sons Contracting1025220211013-5Excavator Thumb - 30 - 50 ton- After Jan 1020244.2INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10252 | 20211013-5 | 53510612 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 20 | Dynamic | 110.22 | 0 |  |  | 2939.2 | 382.096 | 3321.296 | 2021-10-13 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road capping and maintenance on Del from C190-C189 | 6 | C186-C195 | Del Lake | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1025220211013-5Excavator - 36 ton- After Jan 10202939.2 | Corbiere and Sons Contracting1025220211013-5Excavator - 36 ton- After Jan 10202939.2INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10250 | 20211013-3 | 53510612 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 36 | HR |  |  | 75 | 0 | 2700 | 351 | 3051 | 2021-10-13 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance activities on Little Red Sucker | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1025020211013-3Operator - Principle - After Jan 10362700 | Corbiere and Sons Contracting1025020211013-3Operator - Principle - After Jan 10362700INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10250 | 20211013-3 | 53510612 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2021-10-13 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance activities on Little Red Sucker | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1025020211013-3L.O.A.4840 | Corbiere and Sons Contracting1025020211013-3L.O.A.4840INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10250 | 20211013-3 | 53510612 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-10-13 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance activities on Little Red Sucker | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1025020211013-3Foreman121140 | Corbiere and Sons Contracting1025020211013-3Foreman121140INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10250 | 20211013-3 | 53510612 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-10-13 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance activities on Little Red Sucker | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1025020211013-3Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting1025020211013-3Rock Truck - 30 Ton- After Jan 10111518.55INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10250 | 20211013-3 | 53510612 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2021-10-13 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance activities on Little Red Sucker | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1025020211013-3Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting1025020211013-3Light Truck - Pick up- After Jan 103731.25INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10250 | 20211013-3 | 53510612 | Access | 0 | ATV - Side by Side w/ roll bar- After Jan 10 | 18.45 | 10 | HR | 13.84 | 0 |  |  | 184.5 | 23.985 | 208.485 | 2021-10-13 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance activities on Little Red Sucker | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1025020211013-3ATV - Side by Side w/ roll bar- After Jan 1010184.5 | Corbiere and Sons Contracting1025020211013-3ATV - Side by Side w/ roll bar- After Jan 1010184.5INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10250 | 20211013-3 | 53510612 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 9 | HR | 47.54 | 0 |  |  | 570.42 | 74.1546 | 644.5746 | 2021-10-13 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance activities on Little Red Sucker | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1025020211013-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42 | Corbiere and Sons Contracting1025020211013-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10250 | 20211013-3 | 53510612 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-10-13 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance activities on Little Red Sucker | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1025020211013-3Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1025020211013-3Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10250 | 20211013-3 | 53510612 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-10-13 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance activities on Little Red Sucker | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1025020211013-3Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting1025020211013-3Excavator - 36 ton- After Jan 10111616.56INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10250 | 20211013-3 | 53510612 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 103.84 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2021-10-13 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance activities on Little Red Sucker | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1025020211013-3Excavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting1025020211013-3Excavator - 30 ton- After Jan 1091246.05INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10250 | 20211013-3 | 53510612 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-10-13 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance activities on Little Red Sucker | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1025020211013-3Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting1025020211013-3Dozer D6 or equal- After Jan 10111446.28INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10248 | 20211012-5 | 53510612 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 36 | HR |  |  | 75 | 0 | 2700 | 351 | 3051 | 2021-10-12 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road capping and maintenance on Del from C193-C190 | 6 | C186-C195 | Del Lake | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1024820211012-5Operator - Principle - After Jan 10362700 | Corbiere and Sons Contracting1024820211012-5Operator - Principle - After Jan 10362700INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10248 | 20211012-5 | 53510612 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2021-10-12 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road capping and maintenance on Del from C193-C190 | 6 | C186-C195 | Del Lake | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1024820211012-5L.O.A.4840 | Corbiere and Sons Contracting1024820211012-5L.O.A.4840INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10248 | 20211012-5 | 53510612 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-10-12 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road capping and maintenance on Del from C193-C190 | 6 | C186-C195 | Del Lake | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1024820211012-5Foreman121140 | Corbiere and Sons Contracting1024820211012-5Foreman121140INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10248 | 20211012-5 | 53510612 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2021-10-12 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road capping and maintenance on Del from C193-C190 | 6 | C186-C195 | Del Lake | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1024820211012-5Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting1024820211012-5Light Truck - Pick up- After Jan 103731.25INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10248 | 20211012-5 | 53510612 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 11 | HR | 47.54 | 0 |  |  | 697.18 | 90.6334 | 787.8134 | 2021-10-12 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road capping and maintenance on Del from C193-C190 | 6 | C186-C195 | Del Lake | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1024820211012-5Excavator Hammer - 30 - 50 ton- After Jan 1011697.18 | Corbiere and Sons Contracting1024820211012-5Excavator Hammer - 30 - 50 ton- After Jan 1011697.18INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10248 | 20211012-5 | 53510612 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 22 | HR | 9.16 | 0 |  |  | 268.62 | 34.9206 | 303.5406 | 2021-10-12 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road capping and maintenance on Del from C193-C190 | 6 | C186-C195 | Del Lake | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1024820211012-5Excavator Thumb - 30 - 50 ton- After Jan 1022268.62 | Corbiere and Sons Contracting1024820211012-5Excavator Thumb - 30 - 50 ton- After Jan 1022268.62INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10248 | 20211012-5 | 53510612 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 33 | Dynamic | 110.22 | 0 |  |  | 4849.68 | 630.4584 | 5480.1384 | 2021-10-12 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road capping and maintenance on Del from C193-C190 | 6 | C186-C195 | Del Lake | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1024820211012-5Excavator - 36 ton- After Jan 10334849.68 | Corbiere and Sons Contracting1024820211012-5Excavator - 36 ton- After Jan 10334849.68INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10246 | 20211012-3 | 53510612 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 36 | HR |  |  | 75 | 0 | 2700 | 351 | 3051 | 2021-10-12 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance activities on Little Red Sucker | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1024620211012-3Operator - Principle - After Jan 10362700 | Corbiere and Sons Contracting1024620211012-3Operator - Principle - After Jan 10362700INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10246 | 20211012-3 | 53510612 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2021-10-12 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance activities on Little Red Sucker | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1024620211012-3L.O.A.4840 | Corbiere and Sons Contracting1024620211012-3L.O.A.4840INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10246 | 20211012-3 | 53510612 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-10-12 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance activities on Little Red Sucker | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1024620211012-3Foreman121140 | Corbiere and Sons Contracting1024620211012-3Foreman121140INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10246 | 20211012-3 | 53510612 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-10-12 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance activities on Little Red Sucker | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1024620211012-3Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting1024620211012-3Rock Truck - 30 Ton- After Jan 10111518.55INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10246 | 20211012-3 | 53510612 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2021-10-12 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance activities on Little Red Sucker | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1024620211012-3Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting1024620211012-3Light Truck - Pick up- After Jan 103731.25INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10246 | 20211012-3 | 53510612 | Access | 0 | ATV - Side by Side w/ roll bar- After Jan 10 | 18.45 | 10 | HR | 13.84 | 0 |  |  | 184.5 | 23.985 | 208.485 | 2021-10-12 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance activities on Little Red Sucker | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1024620211012-3ATV - Side by Side w/ roll bar- After Jan 1010184.5 | Corbiere and Sons Contracting1024620211012-3ATV - Side by Side w/ roll bar- After Jan 1010184.5INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10246 | 20211012-3 | 53510612 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 5 | HR | 47.54 | 0 |  |  | 316.9 | 41.197 | 358.097 | 2021-10-12 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance activities on Little Red Sucker | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1024620211012-3Excavator Hammer - 30 - 50 ton- After Jan 105316.9 | Corbiere and Sons Contracting1024620211012-3Excavator Hammer - 30 - 50 ton- After Jan 105316.9INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10246 | 20211012-3 | 53510612 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-10-12 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance activities on Little Red Sucker | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1024620211012-3Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1024620211012-3Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10246 | 20211012-3 | 53510612 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-10-12 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance activities on Little Red Sucker | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1024620211012-3Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting1024620211012-3Excavator - 36 ton- After Jan 10111616.56INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10246 | 20211012-3 | 53510612 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 5 | Dynamic | 103.84 | 0 |  |  | 692.25 | 89.9925 | 782.2425 | 2021-10-12 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance activities on Little Red Sucker | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1024620211012-3Excavator - 30 ton- After Jan 105692.25 | Corbiere and Sons Contracting1024620211012-3Excavator - 30 ton- After Jan 105692.25INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10246 | 20211012-3 | 53510612 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-10-12 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance activities on Little Red Sucker | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1024620211012-3Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting1024620211012-3Dozer D6 or equal- After Jan 10111446.28INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10245 | 20211011-6 | 53510612 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 27 | HR |  |  | 75 | 0 | 2025 | 263.25 | 2288.25 | 2021-10-11 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance Activities on Del Lake Road | 6 | C186-C195 | Del lake | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1024520211011-6Operator - Principle - After Jan 10272025 | Corbiere and Sons Contracting1024520211011-6Operator - Principle - After Jan 10272025INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10245 | 20211011-6 | 53510612 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2021-10-11 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance Activities on Del Lake Road | 6 | C186-C195 | Del lake | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1024520211011-6L.O.A.4840 | Corbiere and Sons Contracting1024520211011-6L.O.A.4840INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10245 | 20211011-6 | 53510612 | Access | 0 | Foreman | 95 | 9 | HR |  |  | 95 | 0 | 855 | 111.15 | 966.15 | 2021-10-11 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance Activities on Del Lake Road | 6 | C186-C195 | Del lake | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1024520211011-6Foreman9855 | Corbiere and Sons Contracting1024520211011-6Foreman9855INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10245 | 20211011-6 | 53510612 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 8 | Dynamic | 103.54 | 0 |  |  | 1104.4 | 143.572 | 1247.972 | 2021-10-11 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance Activities on Del Lake Road | 6 | C186-C195 | Del lake | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1024520211011-6Rock Truck - 30 Ton- After Jan 1081104.4 | Corbiere and Sons Contracting1024520211011-6Rock Truck - 30 Ton- After Jan 1081104.4INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10245 | 20211011-6 | 53510612 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2021-10-11 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance Activities on Del Lake Road | 6 | C186-C195 | Del lake | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1024520211011-6Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting1024520211011-6Light Truck - Pick up- After Jan 103731.25INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10245 | 20211011-6 | 53510612 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 8 | HR | 47.54 | 0 |  |  | 507.04 | 65.9152 | 572.9552 | 2021-10-11 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance Activities on Del Lake Road | 6 | C186-C195 | Del lake | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1024520211011-6Excavator Hammer - 30 - 50 ton- After Jan 108507.04 | Corbiere and Sons Contracting1024520211011-6Excavator Hammer - 30 - 50 ton- After Jan 108507.04INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10245 | 20211011-6 | 53510612 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 16 | HR | 9.16 | 0 |  |  | 195.36 | 25.3968 | 220.7568 | 2021-10-11 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance Activities on Del Lake Road | 6 | C186-C195 | Del lake | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1024520211011-6Excavator Thumb - 30 - 50 ton- After Jan 1016195.36 | Corbiere and Sons Contracting1024520211011-6Excavator Thumb - 30 - 50 ton- After Jan 1016195.36INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10245 | 20211011-6 | 53510612 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 24 | Dynamic | 110.22 | 0 |  |  | 3527.04 | 458.5152 | 3985.5552 | 2021-10-11 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance Activities on Del Lake Road | 6 | C186-C195 | Del lake | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1024520211011-6Excavator - 36 ton- After Jan 10243527.04 | Corbiere and Sons Contracting1024520211011-6Excavator - 36 ton- After Jan 10243527.04INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10242 | 20211011-4 | 53510612 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 32 | HR |  |  | 75 | 0 | 2400 | 312 | 2712 | 2021-10-11 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance Activities on Mink Creek | 6 | C244-C247 | Mink Creek | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1024220211011-4Operator - Principle - After Jan 10322400 | Corbiere and Sons Contracting1024220211011-4Operator - Principle - After Jan 10322400INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10242 | 20211011-4 | 53510612 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2021-10-11 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance Activities on Mink Creek | 6 | C244-C247 | Mink Creek | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1024220211011-4L.O.A.4840 | Corbiere and Sons Contracting1024220211011-4L.O.A.4840INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10242 | 20211011-4 | 53510612 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-10-11 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance Activities on Mink Creek | 6 | C244-C247 | Mink Creek | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1024220211011-4Foreman121140 | Corbiere and Sons Contracting1024220211011-4Foreman121140INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10242 | 20211011-4 | 53510612 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-10-11 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance Activities on Mink Creek | 6 | C244-C247 | Mink Creek | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1024220211011-4Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting1024220211011-4Rock Truck - 30 Ton- After Jan 10111518.55INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10242 | 20211011-4 | 53510612 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2021-10-11 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance Activities on Mink Creek | 6 | C244-C247 | Mink Creek | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1024220211011-4Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting1024220211011-4Light Truck - Pick up- After Jan 103731.25INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10242 | 20211011-4 | 53510612 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-10-11 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance Activities on Mink Creek | 6 | C244-C247 | Mink Creek | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1024220211011-4Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1024220211011-4Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10242 | 20211011-4 | 53510612 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-10-11 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance Activities on Mink Creek | 6 | C244-C247 | Mink Creek | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1024220211011-4Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting1024220211011-4Excavator - 36 ton- After Jan 10111616.56INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10242 | 20211011-4 | 53510612 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 7 | Dynamic | 110.22 | 0 |  |  | 1028.72 | 133.7336 | 1162.4536 | 2021-10-11 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance Activities on Mink Creek | 6 | C244-C247 | Mink Creek | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1024220211011-4Excavator - 36 ton- After Jan 1071028.72 | Corbiere and Sons Contracting1024220211011-4Excavator - 36 ton- After Jan 1071028.72INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10242 | 20211011-4 | 53510612 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-10-11 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance Activities on Mink Creek | 6 | C244-C247 | Mink Creek | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1024220211011-4Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting1024220211011-4Dozer D6 or equal- After Jan 10111446.28INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10241 | 20211011-3 | 53510612 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 36 | HR |  |  | 75 | 0 | 2700 | 351 | 3051 | 2021-10-11 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance Activities on Red Sucker | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1024120211011-3Operator - Principle - After Jan 10362700 | Corbiere and Sons Contracting1024120211011-3Operator - Principle - After Jan 10362700INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10241 | 20211011-3 | 53510612 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2021-10-11 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance Activities on Red Sucker | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1024120211011-3L.O.A.4840 | Corbiere and Sons Contracting1024120211011-3L.O.A.4840INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10241 | 20211011-3 | 53510612 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-10-11 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance Activities on Red Sucker | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1024120211011-3Foreman121140 | Corbiere and Sons Contracting1024120211011-3Foreman121140INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10241 | 20211011-3 | 53510612 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-10-11 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance Activities on Red Sucker | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1024120211011-3Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting1024120211011-3Rock Truck - 30 Ton- After Jan 10111518.55INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10241 | 20211011-3 | 53510612 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2021-10-11 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance Activities on Red Sucker | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1024120211011-3Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting1024120211011-3Light Truck - Pick up- After Jan 103731.25INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10241 | 20211011-3 | 53510612 | Access | 0 | ATV - Side by Side w/ roll bar- After Jan 10 | 18.45 | 10 | HR | 13.84 | 0 |  |  | 184.5 | 23.985 | 208.485 | 2021-10-11 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance Activities on Red Sucker | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1024120211011-3ATV - Side by Side w/ roll bar- After Jan 1010184.5 | Corbiere and Sons Contracting1024120211011-3ATV - Side by Side w/ roll bar- After Jan 1010184.5INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10241 | 20211011-3 | 53510612 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 5 | HR | 47.54 | 0 |  |  | 316.9 | 41.197 | 358.097 | 2021-10-11 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance Activities on Red Sucker | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1024120211011-3Excavator Hammer - 30 - 50 ton- After Jan 105316.9 | Corbiere and Sons Contracting1024120211011-3Excavator Hammer - 30 - 50 ton- After Jan 105316.9INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10241 | 20211011-3 | 53510612 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-10-11 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance Activities on Red Sucker | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1024120211011-3Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1024120211011-3Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10241 | 20211011-3 | 53510612 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-10-11 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance Activities on Red Sucker | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1024120211011-3Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting1024120211011-3Excavator - 36 ton- After Jan 10111616.56INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10241 | 20211011-3 | 53510612 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 5 | Dynamic | 103.84 | 0 |  |  | 692.25 | 89.9925 | 782.2425 | 2021-10-11 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance Activities on Red Sucker | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1024120211011-3Excavator - 30 ton- After Jan 105692.25 | Corbiere and Sons Contracting1024120211011-3Excavator - 30 ton- After Jan 105692.25INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10241 | 20211011-3 | 53510612 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-10-11 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance Activities on Red Sucker | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1024120211011-3Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting1024120211011-3Dozer D6 or equal- After Jan 10111446.28INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10240 | 20211010-5 | 53510612 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 27 | HR |  |  | 75 | 0 | 2025 | 263.25 | 2288.25 | 2021-10-10 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1024020211010-5Operator - Principle - After Jan 10272025 | Corbiere and Sons Contracting1024020211010-5Operator - Principle - After Jan 10272025INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10240 | 20211010-5 | 53510612 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-10-10 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1024020211010-5L.O.A.3630 | Corbiere and Sons Contracting1024020211010-5L.O.A.3630INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10240 | 20211010-5 | 53510612 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 8 | Dynamic | 103.54 | 0 |  |  | 1104.4 | 143.572 | 1247.972 | 2021-10-10 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1024020211010-5Rock Truck - 30 Ton- After Jan 1081104.4 | Corbiere and Sons Contracting1024020211010-5Rock Truck - 30 Ton- After Jan 1081104.4INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10240 | 20211010-5 | 53510612 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-10-10 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1024020211010-5Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting1024020211010-5Light Truck - Pick up- After Jan 102487.5INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10240 | 20211010-5 | 53510612 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 16 | HR | 9.16 | 0 |  |  | 195.36 | 25.3968 | 220.7568 | 2021-10-10 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1024020211010-5Excavator Thumb - 30 - 50 ton- After Jan 1016195.36 | Corbiere and Sons Contracting1024020211010-5Excavator Thumb - 30 - 50 ton- After Jan 1016195.36INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10240 | 20211010-5 | 53510612 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 8 | Dynamic | 110.22 | 0 |  |  | 1175.68 | 152.8384 | 1328.5184 | 2021-10-10 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1024020211010-5Excavator - 36 ton- After Jan 1081175.68 | Corbiere and Sons Contracting1024020211010-5Excavator - 36 ton- After Jan 1081175.68INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10240 | 20211010-5 | 53510612 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 8 | Dynamic | 103.84 | 0 |  |  | 1107.6 | 143.988 | 1251.588 | 2021-10-10 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1024020211010-5Excavator - 30 ton- After Jan 1081107.6 | Corbiere and Sons Contracting1024020211010-5Excavator - 30 ton- After Jan 1081107.6INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10238 | 20211010-3 | 53510612 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5 | HR |  |  | 75 | 0 | 375 | 48.75 | 423.75 | 2021-10-10 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance on Mink Creek | 6 | C244-C247 | Mink Creek | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1023820211010-3Operator - Principle - After Jan 105375 | Corbiere and Sons Contracting1023820211010-3Operator - Principle - After Jan 105375INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10238 | 20211010-3 | 53510612 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 2 | Dynamic | 110.22 | 0 |  |  | 293.92 | 38.2096 | 332.1296 | 2021-10-10 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance on Mink Creek | 6 | C244-C247 | Mink Creek | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1023820211010-3Excavator - 36 ton- After Jan 102293.92 | Corbiere and Sons Contracting1023820211010-3Excavator - 36 ton- After Jan 102293.92INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10238 | 20211010-3 | 53510612 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 3 | Dynamic | 98.61 | 0 |  |  | 394.44 | 51.2772 | 445.7172 | 2021-10-10 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance on Mink Creek | 6 | C244-C247 | Mink Creek | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1023820211010-3Dozer D6 or equal- After Jan 103394.44 | Corbiere and Sons Contracting1023820211010-3Dozer D6 or equal- After Jan 103394.44INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10236 | 20211009-8 | 53510612 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2021-10-09 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1023620211009-8Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1023620211009-8Operator - Principle - After Jan 1012900INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10236 | 20211009-8 | 53510612 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-10-09 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1023620211009-8L.O.A.1210 | Corbiere and Sons Contracting1023620211009-8L.O.A.1210INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10236 | 20211009-8 | 53510612 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-10-09 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1023620211009-8Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1023620211009-8Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10236 | 20211009-8 | 53510612 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-10-09 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1023620211009-8Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting1023620211009-8Excavator - 36 ton- After Jan 10111616.56INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10235 | 20211009-7 | 53510612 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2021-10-09 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maitenance Activities on Little Red Sucker | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1023520211009-7Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1023520211009-7Operator - Principle - After Jan 1012900INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10235 | 20211009-7 | 53510612 | Access | 0 | Foreman | 95 | 4 | HR |  |  | 95 | 0 | 380 | 49.4 | 429.4 | 2021-10-09 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maitenance Activities on Little Red Sucker | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1023520211009-7Foreman4380 | Corbiere and Sons Contracting1023520211009-7Foreman4380INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10235 | 20211009-7 | 53510612 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 5.5 | Dynamic | 103.54 | 0 |  |  | 759.275 | 98.7057 | 857.9807 | 2021-10-09 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maitenance Activities on Little Red Sucker | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1023520211009-7Rock Truck - 30 Ton- After Jan 105.5759.275 | Corbiere and Sons Contracting1023520211009-7Rock Truck - 30 Ton- After Jan 105.5759.275INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10235 | 20211009-7 | 53510612 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 5.5 | HR | 9.16 | 0 |  |  | 67.155 | 8.7302 | 75.8851 | 2021-10-09 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maitenance Activities on Little Red Sucker | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1023520211009-7Excavator Thumb - 30 - 50 ton- After Jan 105.567.155 | Corbiere and Sons Contracting1023520211009-7Excavator Thumb - 30 - 50 ton- After Jan 105.567.155INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10235 | 20211009-7 | 53510612 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 5.5 | Dynamic | 110.22 | 0 |  |  | 808.28 | 105.0764 | 913.3564 | 2021-10-09 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maitenance Activities on Little Red Sucker | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1023520211009-7Excavator - 36 ton- After Jan 105.5808.28 | Corbiere and Sons Contracting1023520211009-7Excavator - 36 ton- After Jan 105.5808.28INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10235 | 20211009-7 | 53510612 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 4 | Dynamic | 98.61 | 0 |  |  | 525.92 | 68.3696 | 594.2896 | 2021-10-09 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maitenance Activities on Little Red Sucker | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1023520211009-7Dozer D6 or equal- After Jan 104525.92 | Corbiere and Sons Contracting1023520211009-7Dozer D6 or equal- After Jan 104525.92INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10232 | 20211009-4 | 53510612 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2021-10-09 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maitnenance on Ripple Creek | 6 | C198-C202 | Ripple Creek | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1023220211009-4Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1023220211009-4Operator - Principle - After Jan 1012900INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10232 | 20211009-4 | 53510612 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-10-09 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maitnenance on Ripple Creek | 6 | C198-C202 | Ripple Creek | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1023220211009-4L.O.A.2420 | Corbiere and Sons Contracting1023220211009-4L.O.A.2420INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10232 | 20211009-4 | 53510612 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 5 | Dynamic | 103.54 | 0 |  |  | 690.25 | 89.7325 | 779.9825 | 2021-10-09 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maitnenance on Ripple Creek | 6 | C198-C202 | Ripple Creek | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1023220211009-4Rock Truck - 30 Ton- After Jan 105690.25 | Corbiere and Sons Contracting1023220211009-4Rock Truck - 30 Ton- After Jan 105690.25INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10232 | 20211009-4 | 53510612 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-10-09 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maitnenance on Ripple Creek | 6 | C198-C202 | Ripple Creek | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1023220211009-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1023220211009-4Light Truck - Pick up- After Jan 101243.75INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10232 | 20211009-4 | 53510612 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 5 | Dynamic | 110.22 | 0 |  |  | 734.8 | 95.524 | 830.324 | 2021-10-09 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maitnenance on Ripple Creek | 6 | C198-C202 | Ripple Creek | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1023220211009-4Excavator - 36 ton- After Jan 105734.8 | Corbiere and Sons Contracting1023220211009-4Excavator - 36 ton- After Jan 105734.8INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10231 | 20211009-3 | 53510612 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 9 | HR |  |  | 75 | 0 | 675 | 87.75 | 762.75 | 2021-10-09 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance on Mink Creek - Building a diversion at shoefly for C246 | 6 | C244-C247 | Mink Creek | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1023120211009-3Operator - Principle - After Jan 109675 | Corbiere and Sons Contracting1023120211009-3Operator - Principle - After Jan 109675INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10231 | 20211009-3 | 53510612 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 5 | Dynamic | 110.22 | 0 |  |  | 734.8 | 95.524 | 830.324 | 2021-10-09 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance on Mink Creek - Building a diversion at shoefly for C246 | 6 | C244-C247 | Mink Creek | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1023120211009-3Excavator - 36 ton- After Jan 105734.8 | Corbiere and Sons Contracting1023120211009-3Excavator - 36 ton- After Jan 105734.8INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10231 | 20211009-3 | 53510612 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 3 | Dynamic | 98.61 | 0 |  |  | 394.44 | 51.2772 | 445.7172 | 2021-10-09 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance on Mink Creek - Building a diversion at shoefly for C246 | 6 | C244-C247 | Mink Creek | 0 | 2021-10-18 |  | 58 | 2021-10-19 | [6 empty] | 06 | Corbiere and Sons Contracting1023120211009-3Dozer D6 or equal- After Jan 103394.44 | Corbiere and Sons Contracting1023120211009-3Dozer D6 or equal- After Jan 103394.44INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10225 | 20211008-7 | 53510612 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 14.5 | HR |  |  | 75 | 0 | 1087.5 | 141.375 | 1228.875 | 2021-10-08 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Spot dumping and road maintenance activities on Hare Lake Road | 6 | C257-C267 | Hare lake Road | 0 | 2021-10-15 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1022520211008-7Operator - Principle - After Jan 1014.51087.5 | Corbiere and Sons Contracting1022520211008-7Operator - Principle - After Jan 1014.51087.5INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10225 | 20211008-7 | 53510612 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-10-08 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Spot dumping and road maintenance activities on Hare Lake Road | 6 | C257-C267 | Hare lake Road | 0 | 2021-10-15 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1022520211008-7L.O.A.2420 | Corbiere and Sons Contracting1022520211008-7L.O.A.2420INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10225 | 20211008-7 | 53510612 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 5 | Dynamic | 103.54 | 0 |  |  | 690.25 | 89.7325 | 779.9825 | 2021-10-08 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Spot dumping and road maintenance activities on Hare Lake Road | 6 | C257-C267 | Hare lake Road | 0 | 2021-10-15 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1022520211008-7Rock Truck - 30 Ton- After Jan 105690.25 | Corbiere and Sons Contracting1022520211008-7Rock Truck - 30 Ton- After Jan 105690.25INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10225 | 20211008-7 | 53510612 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 7.5 | Dynamic | 103.84 | 0 |  |  | 1038.375 | 134.9888 | 1173.3637 | 2021-10-08 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Spot dumping and road maintenance activities on Hare Lake Road | 6 | C257-C267 | Hare lake Road | 0 | 2021-10-15 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1022520211008-7Excavator - 30 ton- After Jan 107.51038.375 | Corbiere and Sons Contracting1022520211008-7Excavator - 30 ton- After Jan 107.51038.375INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10223 | 20211008-5 | 53510612 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 24 | HR |  |  | 75 | 0 | 1800 | 234 | 2034 | 2021-10-08 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-15 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1022320211008-5Operator - Principle - After Jan 10241800 | Corbiere and Sons Contracting1022320211008-5Operator - Principle - After Jan 10241800INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10223 | 20211008-5 | 53510612 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-10-08 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-15 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1022320211008-5L.O.A.1210 | Corbiere and Sons Contracting1022320211008-5L.O.A.1210INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10223 | 20211008-5 | 53510612 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 6 | Dynamic | 103.54 | 0 |  |  | 828.3 | 107.679 | 935.979 | 2021-10-08 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-15 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1022320211008-5Rock Truck - 30 Ton- After Jan 106828.3 | Corbiere and Sons Contracting1022320211008-5Rock Truck - 30 Ton- After Jan 106828.3INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10223 | 20211008-5 | 53510612 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 14 | HR | 9.16 | 0 |  |  | 170.94 | 22.2222 | 193.1622 | 2021-10-08 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-15 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1022320211008-5Excavator Thumb - 30 - 50 ton- After Jan 1014170.94 | Corbiere and Sons Contracting1022320211008-5Excavator Thumb - 30 - 50 ton- After Jan 1014170.94INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10223 | 20211008-5 | 53510612 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-10-08 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-15 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1022320211008-5Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting1022320211008-5Excavator - 36 ton- After Jan 10111616.56INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10223 | 20211008-5 | 53510612 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 3 | Dynamic | 103.84 | 0 |  |  | 415.35 | 53.9955 | 469.3455 | 2021-10-08 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-15 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1022320211008-5Excavator - 30 ton- After Jan 103415.35 | Corbiere and Sons Contracting1022320211008-5Excavator - 30 ton- After Jan 103415.35INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10223 | 20211008-5 | 53510612 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 3 | Dynamic | 98.61 | 0 |  |  | 394.44 | 51.2772 | 445.7172 | 2021-10-08 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-15 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1022320211008-5Dozer D6 or equal- After Jan 103394.44 | Corbiere and Sons Contracting1022320211008-5Dozer D6 or equal- After Jan 103394.44INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10229 | 20211008-11 | 53510612 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 36 | HR |  |  | 75 | 0 | 2700 | 351 | 3051 | 2021-10-08 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance activities in Ripple Lake Access | 6 | C198-C202 | Ripple Lake | 0 | 2021-10-15 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1022920211008-11Operator - Principle - After Jan 10362700 | Corbiere and Sons Contracting1022920211008-11Operator - Principle - After Jan 10362700INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10229 | 20211008-11 | 53510612 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-10-08 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance activities in Ripple Lake Access | 6 | C198-C202 | Ripple Lake | 0 | 2021-10-15 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1022920211008-11L.O.A.3630 | Corbiere and Sons Contracting1022920211008-11L.O.A.3630INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10229 | 20211008-11 | 53510612 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-10-08 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance activities in Ripple Lake Access | 6 | C198-C202 | Ripple Lake | 0 | 2021-10-15 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1022920211008-11Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting1022920211008-11Rock Truck - 30 Ton- After Jan 10111518.55INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10229 | 20211008-11 | 53510612 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-10-08 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance activities in Ripple Lake Access | 6 | C198-C202 | Ripple Lake | 0 | 2021-10-15 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1022920211008-11Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1022920211008-11Light Truck - Pick up- After Jan 101243.75INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10229 | 20211008-11 | 53510612 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-10-08 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance activities in Ripple Lake Access | 6 | C198-C202 | Ripple Lake | 0 | 2021-10-15 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1022920211008-11Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1022920211008-11Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10229 | 20211008-11 | 53510612 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-10-08 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance activities in Ripple Lake Access | 6 | C198-C202 | Ripple Lake | 0 | 2021-10-15 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1022920211008-11Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting1022920211008-11Excavator - 36 ton- After Jan 10111616.56INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10229 | 20211008-11 | 53510612 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-10-08 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance activities in Ripple Lake Access | 6 | C198-C202 | Ripple Lake | 0 | 2021-10-15 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1022920211008-11Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting1022920211008-11Excavator - 36 ton- After Jan 10111616.56INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10228 | 20211008-10 | 53510612 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 8 | HR |  |  | 75 | 0 | 600 | 78 | 678 | 2021-10-08 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance activities on Mink Creek | 6 | C244-C246 | Mink Creek | 0 | 2021-10-15 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1022820211008-10Operator - Principle - After Jan 108600 | Corbiere and Sons Contracting1022820211008-10Operator - Principle - After Jan 108600INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10228 | 20211008-10 | 53510612 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5 | HR |  |  | 75 | 0 | 375 | 48.75 | 423.75 | 2021-10-08 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance activities on Mink Creek | 6 | C244-C246 | Mink Creek | 0 | 2021-10-15 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1022820211008-10Operator - Principle - After Jan 105375 | Corbiere and Sons Contracting1022820211008-10Operator - Principle - After Jan 105375INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10228 | 20211008-10 | 53510612 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 5 | Dynamic | 110.22 | 0 |  |  | 734.8 | 95.524 | 830.324 | 2021-10-08 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance activities on Mink Creek | 6 | C244-C246 | Mink Creek | 0 | 2021-10-15 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1022820211008-10Excavator - 36 ton- After Jan 105734.8 | Corbiere and Sons Contracting1022820211008-10Excavator - 36 ton- After Jan 105734.8INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10228 | 20211008-10 | 53510612 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 7 | Dynamic | 98.61 | 0 |  |  | 920.36 | 119.6468 | 1040.0068 | 2021-10-08 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance activities on Mink Creek | 6 | C244-C246 | Mink Creek | 0 | 2021-10-15 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1022820211008-10Dozer D6 or equal- After Jan 107920.36 | Corbiere and Sons Contracting1022820211008-10Dozer D6 or equal- After Jan 107920.36INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10218 | 20211007-9 | 53510612 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2021-10-07 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixing road punchouts on Hare Lake Road | 6 | C267 | Hare Lake | 0 | 2021-10-14 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1021820211007-9Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1021820211007-9Operator - Principle - After Jan 1012900INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10218 | 20211007-9 | 53510612 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-10-07 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixing road punchouts on Hare Lake Road | 6 | C267 | Hare Lake | 0 | 2021-10-14 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1021820211007-9L.O.A.2420 | Corbiere and Sons Contracting1021820211007-9L.O.A.2420INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10218 | 20211007-9 | 53510612 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 5.5 | Dynamic | 103.54 | 0 |  |  | 759.275 | 98.7057 | 857.9807 | 2021-10-07 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixing road punchouts on Hare Lake Road | 6 | C267 | Hare Lake | 0 | 2021-10-14 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1021820211007-9Rock Truck - 30 Ton- After Jan 105.5759.275 | Corbiere and Sons Contracting1021820211007-9Rock Truck - 30 Ton- After Jan 105.5759.275INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10218 | 20211007-9 | 53510612 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 5.5 | Dynamic | 103.84 | 0 |  |  | 761.475 | 98.9917 | 860.4668 | 2021-10-07 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixing road punchouts on Hare Lake Road | 6 | C267 | Hare Lake | 0 | 2021-10-14 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1021820211007-9Excavator - 30 ton- After Jan 105.5761.475 | Corbiere and Sons Contracting1021820211007-9Excavator - 30 ton- After Jan 105.5761.475INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10217 | 20211007-8 | 53510612 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 36 | HR |  |  | 75 | 0 | 2700 | 351 | 3051 | 2021-10-07 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maitnenance activities on Ripple | 6 | C198-C202 | Ripple Lake | 0 | 2021-10-14 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1021720211007-8Operator - Principle - After Jan 10362700 | Corbiere and Sons Contracting1021720211007-8Operator - Principle - After Jan 10362700INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10217 | 20211007-8 | 53510612 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-10-07 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maitnenance activities on Ripple | 6 | C198-C202 | Ripple Lake | 0 | 2021-10-14 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1021720211007-8L.O.A.3630 | Corbiere and Sons Contracting1021720211007-8L.O.A.3630INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10217 | 20211007-8 | 53510612 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-10-07 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maitnenance activities on Ripple | 6 | C198-C202 | Ripple Lake | 0 | 2021-10-14 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1021720211007-8Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting1021720211007-8Rock Truck - 30 Ton- After Jan 10111518.55INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10217 | 20211007-8 | 53510612 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-10-07 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maitnenance activities on Ripple | 6 | C198-C202 | Ripple Lake | 0 | 2021-10-14 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1021720211007-8Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting1021720211007-8Light Truck - Pick up- After Jan 102487.5INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10217 | 20211007-8 | 53510612 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-10-07 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maitnenance activities on Ripple | 6 | C198-C202 | Ripple Lake | 0 | 2021-10-14 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1021720211007-8Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1021720211007-8Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10217 | 20211007-8 | 53510612 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-10-07 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maitnenance activities on Ripple | 6 | C198-C202 | Ripple Lake | 0 | 2021-10-14 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1021720211007-8Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting1021720211007-8Excavator - 36 ton- After Jan 10111616.56INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10217 | 20211007-8 | 53510612 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-10-07 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maitnenance activities on Ripple | 6 | C198-C202 | Ripple Lake | 0 | 2021-10-14 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1021720211007-8Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting1021720211007-8Excavator - 36 ton- After Jan 10111616.56INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10216 | 20211007-7 | 53510612 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2021-10-07 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance being done on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-14 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1021620211007-7Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1021620211007-7Operator - Principle - After Jan 1012900INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10216 | 20211007-7 | 53510612 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-10-07 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance being done on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-14 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1021620211007-7L.O.A.1210 | Corbiere and Sons Contracting1021620211007-7L.O.A.1210INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10216 | 20211007-7 | 53510612 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-10-07 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance being done on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-14 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1021620211007-7Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1021620211007-7Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10216 | 20211007-7 | 53510612 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-10-07 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance being done on Neys Road | 6 | C219-C236 | Neys | 0 | 2021-10-14 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1021620211007-7Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting1021620211007-7Excavator - 36 ton- After Jan 10111616.56INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10219 | 20211007-10 | 53510612 | Access | 0 | Labourer - General - After Jan 10 | 60 | 6 | HR |  |  | 60 | 0 | 360 | 46.8 | 406.8 | 2021-10-07 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-14 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1021920211007-10Labourer - General - After Jan 106360 | Corbiere and Sons Contracting1021920211007-10Labourer - General - After Jan 106360INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10219 | 20211007-10 | 53510612 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2021-10-07 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-14 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1021920211007-10Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1021920211007-10Operator - Principle - After Jan 1012900INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10219 | 20211007-10 | 53510612 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2021-10-07 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-14 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1021920211007-10L.O.A.4840 | Corbiere and Sons Contracting1021920211007-10L.O.A.4840INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10219 | 20211007-10 | 53510612 | Access | 0 | Foreman | 95 | 6 | HR |  |  | 95 | 0 | 570 | 74.1 | 644.1 | 2021-10-07 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-14 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1021920211007-10Foreman6570 | Corbiere and Sons Contracting1021920211007-10Foreman6570INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10219 | 20211007-10 | 53510612 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-10-07 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-14 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1021920211007-10Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1021920211007-10Light Truck - Pick up- After Jan 101243.75INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10219 | 20211007-10 | 53510612 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 5.5 | HR | 9.16 | 0 |  |  | 67.155 | 8.7302 | 75.8851 | 2021-10-07 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-14 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1021920211007-10Excavator Thumb - 30 - 50 ton- After Jan 105.567.155 | Corbiere and Sons Contracting1021920211007-10Excavator Thumb - 30 - 50 ton- After Jan 105.567.155INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10219 | 20211007-10 | 53510612 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 5.5 | HR | 9.16 | 0 |  |  | 67.155 | 8.7302 | 75.8851 | 2021-10-07 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-14 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1021920211007-10Excavator Thumb - 30 - 50 ton- After Jan 105.567.155 | Corbiere and Sons Contracting1021920211007-10Excavator Thumb - 30 - 50 ton- After Jan 105.567.155INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10219 | 20211007-10 | 53510612 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 5.5 | Dynamic | 110.22 | 0 |  |  | 808.28 | 105.0764 | 913.3564 | 2021-10-07 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-14 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1021920211007-10Excavator - 36 ton- After Jan 105.5808.28 | Corbiere and Sons Contracting1021920211007-10Excavator - 36 ton- After Jan 105.5808.28INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10219 | 20211007-10 | 53510612 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 5.5 | Dynamic | 110.22 | 0 |  |  | 808.28 | 105.0764 | 913.3564 | 2021-10-07 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-14 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1021920211007-10Excavator - 36 ton- After Jan 105.5808.28 | Corbiere and Sons Contracting1021920211007-10Excavator - 36 ton- After Jan 105.5808.28INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10219 | 20211007-10 | 53510612 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 5.5 | Dynamic | 110.22 | 0 |  |  | 808.28 | 105.0764 | 913.3564 | 2021-10-07 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance activities on Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-10-14 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1021920211007-10Excavator - 36 ton- After Jan 105.5808.28 | Corbiere and Sons Contracting1021920211007-10Excavator - 36 ton- After Jan 105.5808.28INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10210 | 20211006-9 | 53510612 | Access | 0 | Labourer - General - After Jan 10 | 60 | 9 | HR |  |  | 60 | 0 | 540 | 70.2 | 610.2 | 2021-10-06 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance activities on Mink Creek Road | 6 | C237-C247 | Mink Creek | 0 | 2021-10-13 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1021020211006-9Labourer - General - After Jan 109540 | Corbiere and Sons Contracting1021020211006-9Labourer - General - After Jan 109540INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10210 | 20211006-9 | 53510612 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 29 | HR |  |  | 75 | 0 | 2175 | 282.75 | 2457.75 | 2021-10-06 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance activities on Mink Creek Road | 6 | C237-C247 | Mink Creek | 0 | 2021-10-13 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1021020211006-9Operator - Principle - After Jan 10292175 | Corbiere and Sons Contracting1021020211006-9Operator - Principle - After Jan 10292175INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10210 | 20211006-9 | 53510612 | Access | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2021-10-06 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance activities on Mink Creek Road | 6 | C237-C247 | Mink Creek | 0 | 2021-10-13 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1021020211006-9L.O.A.51050 | Corbiere and Sons Contracting1021020211006-9L.O.A.51050INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10210 | 20211006-9 | 53510612 | Access | 0 | Foreman | 95 | 8 | HR |  |  | 95 | 0 | 760 | 98.8 | 858.8 | 2021-10-06 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance activities on Mink Creek Road | 6 | C237-C247 | Mink Creek | 0 | 2021-10-13 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1021020211006-9Foreman8760 | Corbiere and Sons Contracting1021020211006-9Foreman8760INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10210 | 20211006-9 | 53510612 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 9 | Dynamic | 103.54 | 0 |  |  | 1242.45 | 161.5185 | 1403.9685 | 2021-10-06 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance activities on Mink Creek Road | 6 | C237-C247 | Mink Creek | 0 | 2021-10-13 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1021020211006-9Rock Truck - 30 Ton- After Jan 1091242.45 | Corbiere and Sons Contracting1021020211006-9Rock Truck - 30 Ton- After Jan 1091242.45INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10210 | 20211006-9 | 53510612 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 4 | DAY | 182.81 | 0 |  |  | 975 | 126.75 | 1101.75 | 2021-10-06 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance activities on Mink Creek Road | 6 | C237-C247 | Mink Creek | 0 | 2021-10-13 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1021020211006-9Light Truck - Pick up- After Jan 104975 | Corbiere and Sons Contracting1021020211006-9Light Truck - Pick up- After Jan 104975INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10210 | 20211006-9 | 53510612 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-10-06 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance activities on Mink Creek Road | 6 | C237-C247 | Mink Creek | 0 | 2021-10-13 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1021020211006-9Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting1021020211006-9Excavator - 36 ton- After Jan 1091322.64INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10210 | 20211006-9 | 53510612 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 8 | Dynamic | 98.61 | 0 |  |  | 1051.84 | 136.7392 | 1188.5792 | 2021-10-06 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance activities on Mink Creek Road | 6 | C237-C247 | Mink Creek | 0 | 2021-10-13 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1021020211006-9Dozer D6 or equal- After Jan 1081051.84 | Corbiere and Sons Contracting1021020211006-9Dozer D6 or equal- After Jan 1081051.84INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10206 | 20211006-5 | 53510612 | Access | 0 | Labourer - General - After Jan 10 | 60 | 19 | HR |  |  | 60 | 0 | 1140 | 148.2 | 1288.2 | 2021-10-06 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance Activities on Del Lake Road | 6 | C186-C195 | Del Lake Road | 0 | 2021-10-12 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1020620211006-5Labourer - General - After Jan 10191140 | Corbiere and Sons Contracting1020620211006-5Labourer - General - After Jan 10191140INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10206 | 20211006-5 | 53510612 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 71 | HR |  |  | 75 | 0 | 5325 | 692.25 | 6017.25 | 2021-10-06 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance Activities on Del Lake Road | 6 | C186-C195 | Del Lake Road | 0 | 2021-10-12 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1020620211006-5Operator - Principle - After Jan 10715325 | Corbiere and Sons Contracting1020620211006-5Operator - Principle - After Jan 10715325INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10206 | 20211006-5 | 53510612 | Access | 0 | L.O.A. | 210 | 9 | DAY |  |  |  | 0 | 1890 | 245.7 | 2135.7 | 2021-10-06 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance Activities on Del Lake Road | 6 | C186-C195 | Del Lake Road | 0 | 2021-10-12 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1020620211006-5L.O.A.91890 | Corbiere and Sons Contracting1020620211006-5L.O.A.91890INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10206 | 20211006-5 | 53510612 | Access | 0 | Foreman | 95 | 8 | HR |  |  | 95 | 0 | 760 | 98.8 | 858.8 | 2021-10-06 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance Activities on Del Lake Road | 6 | C186-C195 | Del Lake Road | 0 | 2021-10-12 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1020620211006-5Foreman8760 | Corbiere and Sons Contracting1020620211006-5Foreman8760INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10206 | 20211006-5 | 53510612 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 15 | Dynamic | 103.54 | 0 |  |  | 2070.75 | 269.1975 | 2339.9475 | 2021-10-06 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance Activities on Del Lake Road | 6 | C186-C195 | Del Lake Road | 0 | 2021-10-12 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1020620211006-5Rock Truck - 30 Ton- After Jan 10152070.75 | Corbiere and Sons Contracting1020620211006-5Rock Truck - 30 Ton- After Jan 10152070.75INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10206 | 20211006-5 | 53510612 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 5 | DAY | 182.81 | 0 |  |  | 1218.75 | 158.4375 | 1377.1875 | 2021-10-06 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance Activities on Del Lake Road | 6 | C186-C195 | Del Lake Road | 0 | 2021-10-12 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1020620211006-5Light Truck - Pick up- After Jan 1051218.75 | Corbiere and Sons Contracting1020620211006-5Light Truck - Pick up- After Jan 1051218.75INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10206 | 20211006-5 | 53510612 | Access | 0 | ATV - Side by Side w/ roll bar- After Jan 10 | 18.45 | 10 | HR | 13.84 | 0 |  |  | 184.5 | 23.985 | 208.485 | 2021-10-06 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance Activities on Del Lake Road | 6 | C186-C195 | Del Lake Road | 0 | 2021-10-12 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1020620211006-5ATV - Side by Side w/ roll bar- After Jan 1010184.5 | Corbiere and Sons Contracting1020620211006-5ATV - Side by Side w/ roll bar- After Jan 1010184.5INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10206 | 20211006-5 | 53510612 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 12 | HR | 47.54 | 0 |  |  | 760.56 | 98.8728 | 859.4328 | 2021-10-06 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance Activities on Del Lake Road | 6 | C186-C195 | Del Lake Road | 0 | 2021-10-12 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1020620211006-5Excavator Hammer - 30 - 50 ton- After Jan 1012760.56 | Corbiere and Sons Contracting1020620211006-5Excavator Hammer - 30 - 50 ton- After Jan 1012760.56INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10206 | 20211006-5 | 53510612 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 12 | HR | 9.16 | 0 |  |  | 146.52 | 19.0476 | 165.5676 | 2021-10-06 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance Activities on Del Lake Road | 6 | C186-C195 | Del Lake Road | 0 | 2021-10-12 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1020620211006-5Excavator Thumb - 30 - 50 ton- After Jan 1012146.52 | Corbiere and Sons Contracting1020620211006-5Excavator Thumb - 30 - 50 ton- After Jan 1012146.52INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10206 | 20211006-5 | 53510612 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 12 | HR | 9.16 | 0 |  |  | 146.52 | 19.0476 | 165.5676 | 2021-10-06 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance Activities on Del Lake Road | 6 | C186-C195 | Del Lake Road | 0 | 2021-10-12 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1020620211006-5Excavator Thumb - 30 - 50 ton- After Jan 1012146.52 | Corbiere and Sons Contracting1020620211006-5Excavator Thumb - 30 - 50 ton- After Jan 1012146.52INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10206 | 20211006-5 | 53510612 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 12 | HR | 9.16 | 0 |  |  | 146.52 | 19.0476 | 165.5676 | 2021-10-06 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance Activities on Del Lake Road | 6 | C186-C195 | Del Lake Road | 0 | 2021-10-12 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1020620211006-5Excavator Thumb - 30 - 50 ton- After Jan 1012146.52 | Corbiere and Sons Contracting1020620211006-5Excavator Thumb - 30 - 50 ton- After Jan 1012146.52INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10206 | 20211006-5 | 53510612 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 7 | Dynamic | 110.22 | 0 |  |  | 1028.72 | 133.7336 | 1162.4536 | 2021-10-06 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance Activities on Del Lake Road | 6 | C186-C195 | Del Lake Road | 0 | 2021-10-12 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1020620211006-5Excavator - 36 ton- After Jan 1071028.72 | Corbiere and Sons Contracting1020620211006-5Excavator - 36 ton- After Jan 1071028.72INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10206 | 20211006-5 | 53510612 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 12 | Dynamic | 110.22 | 0 |  |  | 1763.52 | 229.2576 | 1992.7776 | 2021-10-06 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance Activities on Del Lake Road | 6 | C186-C195 | Del Lake Road | 0 | 2021-10-12 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1020620211006-5Excavator - 36 ton- After Jan 10121763.52 | Corbiere and Sons Contracting1020620211006-5Excavator - 36 ton- After Jan 10121763.52INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10206 | 20211006-5 | 53510612 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 12 | Dynamic | 110.22 | 0 |  |  | 1763.52 | 229.2576 | 1992.7776 | 2021-10-06 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance Activities on Del Lake Road | 6 | C186-C195 | Del Lake Road | 0 | 2021-10-12 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1020620211006-5Excavator - 36 ton- After Jan 10121763.52 | Corbiere and Sons Contracting1020620211006-5Excavator - 36 ton- After Jan 10121763.52INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10206 | 20211006-5 | 53510612 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 12 | Dynamic | 110.22 | 0 |  |  | 1763.52 | 229.2576 | 1992.7776 | 2021-10-06 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance Activities on Del Lake Road | 6 | C186-C195 | Del Lake Road | 0 | 2021-10-12 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1020620211006-5Excavator - 36 ton- After Jan 10121763.52 | Corbiere and Sons Contracting1020620211006-5Excavator - 36 ton- After Jan 10121763.52INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10206 | 20211006-5 | 53510612 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 12 | Dynamic | 103.84 | 0 |  |  | 1661.4 | 215.982 | 1877.382 | 2021-10-06 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance Activities on Del Lake Road | 6 | C186-C195 | Del Lake Road | 0 | 2021-10-12 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1020620211006-5Excavator - 30 ton- After Jan 10121661.4 | Corbiere and Sons Contracting1020620211006-5Excavator - 30 ton- After Jan 10121661.4INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10205 | 20211006-4 | 53510612 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 14 | HR |  |  | 75 | 0 | 1050 | 136.5 | 1186.5 | 2021-10-06 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance activities on Hare Lake road | 6 | C257-C267 | Hare Lake | 0 | 2021-10-13 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1020520211006-4Operator - Principle - After Jan 10141050 | Corbiere and Sons Contracting1020520211006-4Operator - Principle - After Jan 10141050INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10205 | 20211006-4 | 53510612 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-10-06 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance activities on Hare Lake road | 6 | C257-C267 | Hare Lake | 0 | 2021-10-13 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1020520211006-4L.O.A.2420 | Corbiere and Sons Contracting1020520211006-4L.O.A.2420INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10205 | 20211006-4 | 53510612 | Access | 0 | Foreman | 95 | 5 | HR |  |  | 95 | 0 | 475 | 61.75 | 536.75 | 2021-10-06 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance activities on Hare Lake road | 6 | C257-C267 | Hare Lake | 0 | 2021-10-13 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1020520211006-4Foreman5475 | Corbiere and Sons Contracting1020520211006-4Foreman5475INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10205 | 20211006-4 | 53510612 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 5 | Dynamic | 91.79 | 0 |  |  | 611.95 | 79.5535 | 691.5035 | 2021-10-06 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance activities on Hare Lake road | 6 | C257-C267 | Hare Lake | 0 | 2021-10-13 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1020520211006-4Tractor Trailer - 60 Ton- After Jan 105611.95 | Corbiere and Sons Contracting1020520211006-4Tractor Trailer - 60 Ton- After Jan 105611.95INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10205 | 20211006-4 | 53510612 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 6 | Dynamic | 103.54 | 0 |  |  | 828.3 | 107.679 | 935.979 | 2021-10-06 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance activities on Hare Lake road | 6 | C257-C267 | Hare Lake | 0 | 2021-10-13 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1020520211006-4Rock Truck - 30 Ton- After Jan 106828.3 | Corbiere and Sons Contracting1020520211006-4Rock Truck - 30 Ton- After Jan 106828.3INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10205 | 20211006-4 | 53510612 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 6 | Dynamic | 103.84 | 0 |  |  | 830.7 | 107.991 | 938.691 | 2021-10-06 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance activities on Hare Lake road | 6 | C257-C267 | Hare Lake | 0 | 2021-10-13 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1020520211006-4Excavator - 30 ton- After Jan 106830.7 | Corbiere and Sons Contracting1020520211006-4Excavator - 30 ton- After Jan 106830.7INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10204 | 20211006-3 | 53510612 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 10 | HR |  |  | 75 | 0 | 750 | 97.5 | 847.5 | 2021-10-06 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance on Little Red Sucker | 6 | C248-C257 | Little Red Sucker | 0 | 2021-10-13 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1020420211006-3Operator - Principle - After Jan 1010750 | Corbiere and Sons Contracting1020420211006-3Operator - Principle - After Jan 1010750INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10204 | 20211006-3 | 53510612 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-10-06 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance on Little Red Sucker | 6 | C248-C257 | Little Red Sucker | 0 | 2021-10-13 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1020420211006-3L.O.A.1210 | Corbiere and Sons Contracting1020420211006-3L.O.A.1210INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10204 | 20211006-3 | 53510612 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-10-06 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance on Little Red Sucker | 6 | C248-C257 | Little Red Sucker | 0 | 2021-10-13 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1020420211006-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting1020420211006-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10204 | 20211006-3 | 53510612 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-10-06 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance on Little Red Sucker | 6 | C248-C257 | Little Red Sucker | 0 | 2021-10-13 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1020420211006-3Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting1020420211006-3Excavator - 36 ton- After Jan 1091322.64INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10211 | 20211006-10 | 53510612 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 30 | HR |  |  | 75 | 0 | 2250 | 292.5 | 2542.5 | 2021-10-06 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Lake | 0 | 2021-10-13 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1021120211006-10Operator - Principle - After Jan 10302250 | Corbiere and Sons Contracting1021120211006-10Operator - Principle - After Jan 10302250INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10211 | 20211006-10 | 53510612 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-10-06 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Lake | 0 | 2021-10-13 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1021120211006-10L.O.A.3630 | Corbiere and Sons Contracting1021120211006-10L.O.A.3630INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10211 | 20211006-10 | 53510612 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 8 | Dynamic | 103.54 | 0 |  |  | 1104.4 | 143.572 | 1247.972 | 2021-10-06 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Lake | 0 | 2021-10-13 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1021120211006-10Rock Truck - 30 Ton- After Jan 1081104.4 | Corbiere and Sons Contracting1021120211006-10Rock Truck - 30 Ton- After Jan 1081104.4INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10211 | 20211006-10 | 53510612 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-10-06 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Lake | 0 | 2021-10-13 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1021120211006-10Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1021120211006-10Light Truck - Pick up- After Jan 101243.75INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10211 | 20211006-10 | 53510612 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 8 | HR | 9.16 | 0 |  |  | 97.68 | 12.6984 | 110.3784 | 2021-10-06 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Lake | 0 | 2021-10-13 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1021120211006-10Excavator Thumb - 30 - 50 ton- After Jan 10897.68 | Corbiere and Sons Contracting1021120211006-10Excavator Thumb - 30 - 50 ton- After Jan 10897.68INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10211 | 20211006-10 | 53510612 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10 | Dynamic | 110.22 | 0 |  |  | 1469.6 | 191.048 | 1660.648 | 2021-10-06 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Lake | 0 | 2021-10-13 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1021120211006-10Excavator - 36 ton- After Jan 10101469.6 | Corbiere and Sons Contracting1021120211006-10Excavator - 36 ton- After Jan 10101469.6INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10211 | 20211006-10 | 53510612 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 8 | Dynamic | 110.22 | 0 |  |  | 1175.68 | 152.8384 | 1328.5184 | 2021-10-06 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road building activities on Ripple Creek | 6 | C197-C202 | Ripple Lake | 0 | 2021-10-13 |  | 58 | 2021-10-16 | [6 empty] | 06 | Corbiere and Sons Contracting1021120211006-10Excavator - 36 ton- After Jan 1081175.68 | Corbiere and Sons Contracting1021120211006-10Excavator - 36 ton- After Jan 1081175.68INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10196 | 20211005-6 | 53510612 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 7 | HR |  |  | 75 | 0 | 525 | 68.25 | 593.25 | 2021-10-05 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance activities on Hare Lake road | 6 | C257-C267 | Hare Lake Road | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1019620211005-6Operator - Principle - After Jan 107525 | Corbiere and Sons Contracting1019620211005-6Operator - Principle - After Jan 107525INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10196 | 20211005-6 | 53510612 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-10-05 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance activities on Hare Lake road | 6 | C257-C267 | Hare Lake Road | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1019620211005-6L.O.A.1210 | Corbiere and Sons Contracting1019620211005-6L.O.A.1210INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10196 | 20211005-6 | 53510612 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 6 | Dynamic | 103.84 | 0 |  |  | 830.7 | 107.991 | 938.691 | 2021-10-05 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance activities on Hare Lake road | 6 | C257-C267 | Hare Lake Road | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1019620211005-6Excavator - 30 ton- After Jan 106830.7 | Corbiere and Sons Contracting1019620211005-6Excavator - 30 ton- After Jan 106830.7INV #151 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10193 | 20211005-3-R1 | 53510604 | Access | 0 | Labourer - General - After Jan 10 | 60 | 12 | HR |  |  | 60 | 0 | 720 | 93.6 | 813.6 | 2021-10-05 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 9 Padda Trucks and 1 Valentino Truck hauling to Neys Road - Padda Trucks also demobilizing from Project | 6 | C219-C236 | Neys | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1019320211005-3-R1Labourer - General - After Jan 1012720 | Corbiere and Sons Contracting1019320211005-3-R1Labourer - General - After Jan 1012720INV #151 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10193 | 20211005-3-R1 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 11.5 | HR |  |  | 70 | 0 | 805 | 104.65 | 909.65 | 2021-10-05 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 9 Padda Trucks and 1 Valentino Truck hauling to Neys Road - Padda Trucks also demobilizing from Project | 6 | C219-C236 | Neys | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1019320211005-3-R1Driver - AZ - After Jan 1011.5805 | Corbiere and Sons Contracting1019320211005-3-R1Driver - AZ - After Jan 1011.5805INV #151 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10193 | 20211005-3-R1 | 53510604 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 93.5 | HR |  |  | 70 | 0 | 6545 | 850.85 | 7395.85 | 2021-10-05 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 9 Padda Trucks and 1 Valentino Truck hauling to Neys Road - Padda Trucks also demobilizing from Project | 6 | C219-C236 | Neys | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1019320211005-3-R1Driver - AZ - After Jan 1093.56545 | Corbiere and Sons Contracting1019320211005-3-R1Driver - AZ - After Jan 1093.56545INV #151 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10193 | 20211005-3-R1 | 53510604 | Access | 0 | L.O.A. | 210 | 10 | DAY |  |  |  | 0 | 2100 | 273 | 2373 | 2021-10-05 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 9 Padda Trucks and 1 Valentino Truck hauling to Neys Road - Padda Trucks also demobilizing from Project | 6 | C219-C236 | Neys | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1019320211005-3-R1L.O.A.102100 | Corbiere and Sons Contracting1019320211005-3-R1L.O.A.102100INV #151 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10193 | 20211005-3-R1 | 53510604 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-10-05 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 9 Padda Trucks and 1 Valentino Truck hauling to Neys Road - Padda Trucks also demobilizing from Project | 6 | C219-C236 | Neys | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1019320211005-3-R1Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1019320211005-3-R1Light Truck - Pick up- After Jan 101243.75INV #151 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10193 | 20211005-3-R1 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 11.5 | Dynamic | 41.4 | 0 |  |  | 634.8 | 82.524 | 717.324 | 2021-10-05 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 9 Padda Trucks and 1 Valentino Truck hauling to Neys Road - Padda Trucks also demobilizing from Project | 6 | C219-C236 | Neys | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1019320211005-3-R1Dump - Triaxle- After Jan 1011.5634.8 | Corbiere and Sons Contracting1019320211005-3-R1Dump - Triaxle- After Jan 1011.5634.8INV #151 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10193 | 20211005-3-R1 | 53510604 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 93.5 | Dynamic | 41.4 | 0 |  |  | 5161.2 | 670.956 | 5832.156 | 2021-10-05 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 9 Padda Trucks and 1 Valentino Truck hauling to Neys Road - Padda Trucks also demobilizing from Project | 6 | C219-C236 | Neys | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1019320211005-3-R1Dump - Triaxle- After Jan 1093.55161.2 | Corbiere and Sons Contracting1019320211005-3-R1Dump - Triaxle- After Jan 1093.55161.2INV #151 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10202 | 20211005-12 | 53510604 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2021-10-05 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gervais RT hauling with Corbiere crew on Del | 6 | C186-C195 | Del Lake West | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1020220211005-12Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1020220211005-12Operator - Principle - After Jan 1012900INV #151 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10202 | 20211005-12 | 53510604 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-10-05 | 0 | INV #151 | 2021-10-21 | 168 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gervais RT hauling with Corbiere crew on Del | 6 | C186-C195 | Del Lake West | 0 | 2021-10-12 |  | 58 | 2021-10-15 | [6 empty] | 06 | Corbiere and Sons Contracting1020220211005-12Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting1020220211005-12Rock Truck - 30 Ton- After Jan 10111518.55INV #151 | Gravel Hauling |  | Gravel Hauling
Corbiere and Sons Contracting | 6 | 0 | 10562 | 20211122-3 | 53530601 | Rig/Access Mats | 0 | Driver - AZ - After Jan 10 | 70 | 9.5 | HR |  |  | 70 | 0 | 665 | 86.45 | 751.45 | 2021-11-22 | 0 | INV #155 | 2021-12-02 | 171 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float delivered 15 swamp mats to Hare Lake Road | 6 | C257 | Hare Lake Creek | 0 | 2021-11-25 |  | 36 | 2021-11-26 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1056220211122-3Driver - AZ - After Jan 109.5665 | Corbiere and Sons Contracting1056220211122-3Driver - AZ - After Jan 109.5665INV #155 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Corbiere and Sons Contracting | 6 | 0 | 10562 | 20211122-3 | 53530601 | Rig/Access Mats | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-11-22 | 0 | INV #155 | 2021-12-02 | 171 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float delivered 15 swamp mats to Hare Lake Road | 6 | C257 | Hare Lake Creek | 0 | 2021-11-25 |  | 36 | 2021-11-26 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1056220211122-3L.O.A.1210 | Corbiere and Sons Contracting1056220211122-3L.O.A.1210INV #155 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Corbiere and Sons Contracting | 6 | 0 | 10562 | 20211122-3 | 53530601 | Rig/Access Mats | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 9.5 | Dynamic | 91.79 | 0 |  |  | 1162.705 | 151.1516 | 1313.8566 | 2021-11-22 | 0 | INV #155 | 2021-12-02 | 171 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float delivered 15 swamp mats to Hare Lake Road | 6 | C257 | Hare Lake Creek | 0 | 2021-11-25 |  | 36 | 2021-11-26 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1056220211122-3Tractor Trailer - 60 Ton- After Jan 109.51162.705 | Corbiere and Sons Contracting1056220211122-3Tractor Trailer - 60 Ton- After Jan 109.51162.705INV #155 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Corbiere and Sons Contracting | 6 | 0 | 10335 | 20211026-3 | 53510612 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 9 | HR |  |  | 75 | 0 | 675 | 87.75 | 762.75 | 2021-10-26 | 0 | INV #155 | 2021-12-02 | 171 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work finished up at Cavers | 6 | C223 | Neys | 0 | 2021-11-01 |  | 36 | 2021-11-02 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1033520211026-3Operator - Principle - After Jan 109675 | Corbiere and Sons Contracting1033520211026-3Operator - Principle - After Jan 109675INV #155 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10335 | 20211026-3 | 53510612 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-10-26 | 0 | INV #155 | 2021-12-02 | 171 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work finished up at Cavers | 6 | C223 | Neys | 0 | 2021-11-01 |  | 36 | 2021-11-02 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1033520211026-3L.O.A.1210 | Corbiere and Sons Contracting1033520211026-3L.O.A.1210INV #155 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10335 | 20211026-3 | 53510612 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-10-26 | 0 | INV #155 | 2021-12-02 | 171 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work finished up at Cavers | 6 | C223 | Neys | 0 | 2021-11-01 |  | 36 | 2021-11-02 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1033520211026-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1033520211026-3Light Truck - Pick up- After Jan 101243.75INV #155 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10335 | 20211026-3 | 53510612 | Access | 0 | Dump - Tandum- After Jan 10 | 51.78 | 5 | Dynamic | 38.84 | 0 |  |  | 258.9 | 33.657 | 292.557 | 2021-10-26 | 0 | INV #155 | 2021-12-02 | 171 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work finished up at Cavers | 6 | C223 | Neys | 0 | 2021-11-01 |  | 36 | 2021-11-02 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1033520211026-3Dump - Tandum- After Jan 105258.9 | Corbiere and Sons Contracting1033520211026-3Dump - Tandum- After Jan 105258.9INV #155 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10335 | 20211026-3 | 53510612 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 8 | HR | 9.16 | 0 |  |  | 97.68 | 12.6984 | 110.3784 | 2021-10-26 | 0 | INV #155 | 2021-12-02 | 171 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work finished up at Cavers | 6 | C223 | Neys | 0 | 2021-11-01 |  | 36 | 2021-11-02 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1033520211026-3Excavator Thumb - 30 - 50 ton- After Jan 10897.68 | Corbiere and Sons Contracting1033520211026-3Excavator Thumb - 30 - 50 ton- After Jan 10897.68INV #155 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10335 | 20211026-3 | 53510612 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 8 | Dynamic | 110.22 | 0 |  |  | 1175.68 | 152.8384 | 1328.5184 | 2021-10-26 | 0 | INV #155 | 2021-12-02 | 171 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work finished up at Cavers | 6 | C223 | Neys | 0 | 2021-11-01 |  | 36 | 2021-11-02 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1033520211026-3Excavator - 36 ton- After Jan 1081175.68 | Corbiere and Sons Contracting1033520211026-3Excavator - 36 ton- After Jan 1081175.68INV #155 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10330 | 20211024-3 | 53510612 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-10-24 | 0 | INV #155 | 2021-12-02 | 171 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance work on Neys - Widening Road for Crane Access | 6 | C223 | Neys | 0 | 2021-11-01 |  | 36 | 2021-11-02 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1033020211024-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1033020211024-3Operator - Principle - After Jan 1011825INV #155 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10330 | 20211024-3 | 53510612 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-10-24 | 0 | INV #155 | 2021-12-02 | 171 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance work on Neys - Widening Road for Crane Access | 6 | C223 | Neys | 0 | 2021-11-01 |  | 36 | 2021-11-02 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1033020211024-3L.O.A.1210 | Corbiere and Sons Contracting1033020211024-3L.O.A.1210INV #155 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10330 | 20211024-3 | 53510612 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-10-24 | 0 | INV #155 | 2021-12-02 | 171 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance work on Neys - Widening Road for Crane Access | 6 | C223 | Neys | 0 | 2021-11-01 |  | 36 | 2021-11-02 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1033020211024-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1033020211024-3Light Truck - Pick up- After Jan 101243.75INV #155 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10330 | 20211024-3 | 53510612 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 9.16 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2021-10-24 | 0 | INV #155 | 2021-12-02 | 171 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance work on Neys - Widening Road for Crane Access | 6 | C223 | Neys | 0 | 2021-11-01 |  | 36 | 2021-11-02 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1033020211024-3Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting1033020211024-3Excavator Thumb - 30 - 50 ton- After Jan 1010122.1INV #155 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10330 | 20211024-3 | 53510612 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10 | Dynamic | 110.22 | 0 |  |  | 1469.6 | 191.048 | 1660.648 | 2021-10-24 | 0 | INV #155 | 2021-12-02 | 171 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance work on Neys - Widening Road for Crane Access | 6 | C223 | Neys | 0 | 2021-11-01 |  | 36 | 2021-11-02 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1033020211024-3Excavator - 36 ton- After Jan 10101469.6 | Corbiere and Sons Contracting1033020211024-3Excavator - 36 ton- After Jan 10101469.6INV #155 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10328 | 20211023-3 | 53510612 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-10-23 | 0 | INV #155 | 2021-12-02 | 171 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance work on Neys - Widening Road for Crane Access | 6 | C223 | Neys | 0 | 2021-11-01 |  | 36 | 2021-11-02 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1032820211023-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1032820211023-3Operator - Principle - After Jan 1011825INV #155 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10328 | 20211023-3 | 53510612 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-10-23 | 0 | INV #155 | 2021-12-02 | 171 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance work on Neys - Widening Road for Crane Access | 6 | C223 | Neys | 0 | 2021-11-01 |  | 36 | 2021-11-02 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1032820211023-3L.O.A.1210 | Corbiere and Sons Contracting1032820211023-3L.O.A.1210INV #155 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10328 | 20211023-3 | 53510612 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-10-23 | 0 | INV #155 | 2021-12-02 | 171 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance work on Neys - Widening Road for Crane Access | 6 | C223 | Neys | 0 | 2021-11-01 |  | 36 | 2021-11-02 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1032820211023-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1032820211023-3Light Truck - Pick up- After Jan 101243.75INV #155 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10328 | 20211023-3 | 53510612 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 6 | HR | 47.54 | 0 |  |  | 380.28 | 49.4364 | 429.7164 | 2021-10-23 | 0 | INV #155 | 2021-12-02 | 171 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance work on Neys - Widening Road for Crane Access | 6 | C223 | Neys | 0 | 2021-11-01 |  | 36 | 2021-11-02 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1032820211023-3Excavator Hammer - 30 - 50 ton- After Jan 106380.28 | Corbiere and Sons Contracting1032820211023-3Excavator Hammer - 30 - 50 ton- After Jan 106380.28INV #155 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10328 | 20211023-3 | 53510612 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 4 | HR | 9.16 | 0 |  |  | 48.84 | 6.3492 | 55.1892 | 2021-10-23 | 0 | INV #155 | 2021-12-02 | 171 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance work on Neys - Widening Road for Crane Access | 6 | C223 | Neys | 0 | 2021-11-01 |  | 36 | 2021-11-02 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1032820211023-3Excavator Thumb - 30 - 50 ton- After Jan 10448.84 | Corbiere and Sons Contracting1032820211023-3Excavator Thumb - 30 - 50 ton- After Jan 10448.84INV #155 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10328 | 20211023-3 | 53510612 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10 | Dynamic | 110.22 | 0 |  |  | 1469.6 | 191.048 | 1660.648 | 2021-10-23 | 0 | INV #155 | 2021-12-02 | 171 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance work on Neys - Widening Road for Crane Access | 6 | C223 | Neys | 0 | 2021-11-01 |  | 36 | 2021-11-02 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1032820211023-3Excavator - 36 ton- After Jan 10101469.6 | Corbiere and Sons Contracting1032820211023-3Excavator - 36 ton- After Jan 10101469.6INV #155 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10298 | 20211020-3 | 53510612 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5.5 | HR |  |  | 75 | 0 | 412.5 | 53.625 | 466.125 | 2021-10-20 | 0 | INV #155 | 2021-12-02 | 171 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance on Mink Creek | 6 | C244-C247 | Mink Creek | 0 | 2021-10-28 |  | 36 | 2021-10-28 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1029820211020-3Operator - Principle - After Jan 105.5412.5 | Corbiere and Sons Contracting1029820211020-3Operator - Principle - After Jan 105.5412.5INV #155 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10298 | 20211020-3 | 53510612 | Access | 0 | Foreman | 95 | 5.5 | HR |  |  | 95 | 0 | 522.5 | 67.925 | 590.425 | 2021-10-20 | 0 | INV #155 | 2021-12-02 | 171 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance on Mink Creek | 6 | C244-C247 | Mink Creek | 0 | 2021-10-28 |  | 36 | 2021-10-28 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1029820211020-3Foreman5.5522.5 | Corbiere and Sons Contracting1029820211020-3Foreman5.5522.5INV #155 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10298 | 20211020-3 | 53510612 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-10-20 | 0 | INV #155 | 2021-12-02 | 171 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance on Mink Creek | 6 | C244-C247 | Mink Creek | 0 | 2021-10-28 |  | 36 | 2021-10-28 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1029820211020-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1029820211020-3Light Truck - Pick up- After Jan 101243.75INV #155 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10298 | 20211020-3 | 53510612 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 5 | HR | 47.54 | 0 |  |  | 316.9 | 41.197 | 358.097 | 2021-10-20 | 0 | INV #155 | 2021-12-02 | 171 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance on Mink Creek | 6 | C244-C247 | Mink Creek | 0 | 2021-10-28 |  | 36 | 2021-10-28 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1029820211020-3Excavator Hammer - 30 - 50 ton- After Jan 105316.9 | Corbiere and Sons Contracting1029820211020-3Excavator Hammer - 30 - 50 ton- After Jan 105316.9INV #155 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10298 | 20211020-3 | 53510612 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 5 | HR | 9.16 | 0 |  |  | 61.05 | 7.9365 | 68.9865 | 2021-10-20 | 0 | INV #155 | 2021-12-02 | 171 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance on Mink Creek | 6 | C244-C247 | Mink Creek | 0 | 2021-10-28 |  | 36 | 2021-10-28 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1029820211020-3Excavator Thumb - 30 - 50 ton- After Jan 10561.05 | Corbiere and Sons Contracting1029820211020-3Excavator Thumb - 30 - 50 ton- After Jan 10561.05INV #155 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10298 | 20211020-3 | 53510612 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 5 | Dynamic | 110.22 | 0 |  |  | 734.8 | 95.524 | 830.324 | 2021-10-20 | 0 | INV #155 | 2021-12-02 | 171 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance on Mink Creek | 6 | C244-C247 | Mink Creek | 0 | 2021-10-28 |  | 36 | 2021-10-28 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1029820211020-3Excavator - 36 ton- After Jan 105734.8 | Corbiere and Sons Contracting1029820211020-3Excavator - 36 ton- After Jan 105734.8INV #155 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10298 | 20211020-3 | 53510612 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 5 | Dynamic | 103.84 | 0 |  |  | 692.25 | 89.9925 | 782.2425 | 2021-10-20 | 0 | INV #155 | 2021-12-02 | 171 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance on Mink Creek | 6 | C244-C247 | Mink Creek | 0 | 2021-10-28 |  | 36 | 2021-10-28 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1029820211020-3Excavator - 30 ton- After Jan 105692.25 | Corbiere and Sons Contracting1029820211020-3Excavator - 30 ton- After Jan 105692.25INV #155 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10294 | 20211019-3 | 53510612 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2021-10-19 | 0 | INV #155 | 2021-12-02 | 171 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Capping on Del Lake from C190-C189 | 6 | C186-C195 | Del Lake | 0 | 2021-10-26 |  | 36 | 2021-10-27 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1029420211019-3Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1029420211019-3Operator - Principle - After Jan 1012900INV #155 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10294 | 20211019-3 | 53510612 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-10-19 | 0 | INV #155 | 2021-12-02 | 171 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Capping on Del Lake from C190-C189 | 6 | C186-C195 | Del Lake | 0 | 2021-10-26 |  | 36 | 2021-10-27 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1029420211019-3L.O.A.2420 | Corbiere and Sons Contracting1029420211019-3L.O.A.2420INV #155 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10294 | 20211019-3 | 53510612 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 5 | Dynamic | 103.54 | 0 |  |  | 690.25 | 89.7325 | 779.9825 | 2021-10-19 | 0 | INV #155 | 2021-12-02 | 171 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Capping on Del Lake from C190-C189 | 6 | C186-C195 | Del Lake | 0 | 2021-10-26 |  | 36 | 2021-10-27 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1029420211019-3Rock Truck - 30 Ton- After Jan 105690.25 | Corbiere and Sons Contracting1029420211019-3Rock Truck - 30 Ton- After Jan 105690.25INV #155 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10294 | 20211019-3 | 53510612 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-10-19 | 0 | INV #155 | 2021-12-02 | 171 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Capping on Del Lake from C190-C189 | 6 | C186-C195 | Del Lake | 0 | 2021-10-26 |  | 36 | 2021-10-27 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1029420211019-3Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting1029420211019-3Light Truck - Pick up- After Jan 102487.5INV #155 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10294 | 20211019-3 | 53510612 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 3 | HR | 9.16 | 0 |  |  | 36.63 | 4.7619 | 41.3919 | 2021-10-19 | 0 | INV #155 | 2021-12-02 | 171 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Capping on Del Lake from C190-C189 | 6 | C186-C195 | Del Lake | 0 | 2021-10-26 |  | 36 | 2021-10-27 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1029420211019-3Excavator Thumb - 30 - 50 ton- After Jan 10336.63 | Corbiere and Sons Contracting1029420211019-3Excavator Thumb - 30 - 50 ton- After Jan 10336.63INV #155 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10294 | 20211019-3 | 53510612 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 3 | Dynamic | 110.22 | 0 |  |  | 440.88 | 57.3144 | 498.1944 | 2021-10-19 | 0 | INV #155 | 2021-12-02 | 171 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Capping on Del Lake from C190-C189 | 6 | C186-C195 | Del Lake | 0 | 2021-10-26 |  | 36 | 2021-10-27 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1029420211019-3Excavator - 36 ton- After Jan 103440.88 | Corbiere and Sons Contracting1029420211019-3Excavator - 36 ton- After Jan 103440.88INV #155 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10294 | 20211019-3 | 53510612 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 3 | Dynamic | 98.61 | 0 |  |  | 394.44 | 51.2772 | 445.7172 | 2021-10-19 | 0 | INV #155 | 2021-12-02 | 171 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Capping on Del Lake from C190-C189 | 6 | C186-C195 | Del Lake | 0 | 2021-10-26 |  | 36 | 2021-10-27 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1029420211019-3Dozer D6 or equal- After Jan 103394.44 | Corbiere and Sons Contracting1029420211019-3Dozer D6 or equal- After Jan 103394.44INV #155 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10292 | 20211018-3 | 53510612 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 24 | HR |  |  | 75 | 0 | 1800 | 234 | 2034 | 2021-10-18 | 0 | INV #155 | 2021-12-02 | 171 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Capping on Del Lake from C190-C189 | 6 | C186-C195 | Del Lake | 0 | 2021-10-26 |  | 36 | 2021-10-27 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1029220211018-3Operator - Principle - After Jan 10241800 | Corbiere and Sons Contracting1029220211018-3Operator - Principle - After Jan 10241800INV #155 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10292 | 20211018-3 | 53510612 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-10-18 | 0 | INV #155 | 2021-12-02 | 171 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Capping on Del Lake from C190-C189 | 6 | C186-C195 | Del Lake | 0 | 2021-10-26 |  | 36 | 2021-10-27 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1029220211018-3L.O.A.2420 | Corbiere and Sons Contracting1029220211018-3L.O.A.2420INV #155 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10292 | 20211018-3 | 53510612 | Access | 0 | Foreman | 95 | 4 | HR |  |  | 95 | 0 | 380 | 49.4 | 429.4 | 2021-10-18 | 0 | INV #155 | 2021-12-02 | 171 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Capping on Del Lake from C190-C189 | 6 | C186-C195 | Del Lake | 0 | 2021-10-26 |  | 36 | 2021-10-27 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1029220211018-3Foreman4380 | Corbiere and Sons Contracting1029220211018-3Foreman4380INV #155 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10292 | 20211018-3 | 53510612 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-10-18 | 0 | INV #155 | 2021-12-02 | 171 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Capping on Del Lake from C190-C189 | 6 | C186-C195 | Del Lake | 0 | 2021-10-26 |  | 36 | 2021-10-27 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1029220211018-3Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting1029220211018-3Rock Truck - 30 Ton- After Jan 10111518.55INV #155 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10292 | 20211018-3 | 53510612 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-10-18 | 0 | INV #155 | 2021-12-02 | 171 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Capping on Del Lake from C190-C189 | 6 | C186-C195 | Del Lake | 0 | 2021-10-26 |  | 36 | 2021-10-27 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1029220211018-3Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting1029220211018-3Light Truck - Pick up- After Jan 102487.5INV #155 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10292 | 20211018-3 | 53510612 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 6 | HR | 9.16 | 0 |  |  | 73.26 | 9.5238 | 82.7838 | 2021-10-18 | 0 | INV #155 | 2021-12-02 | 171 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Capping on Del Lake from C190-C189 | 6 | C186-C195 | Del Lake | 0 | 2021-10-26 |  | 36 | 2021-10-27 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1029220211018-3Excavator Thumb - 30 - 50 ton- After Jan 10673.26 | Corbiere and Sons Contracting1029220211018-3Excavator Thumb - 30 - 50 ton- After Jan 10673.26INV #155 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10292 | 20211018-3 | 53510612 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 6 | Dynamic | 110.22 | 0 |  |  | 881.76 | 114.6288 | 996.3888 | 2021-10-18 | 0 | INV #155 | 2021-12-02 | 171 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Capping on Del Lake from C190-C189 | 6 | C186-C195 | Del Lake | 0 | 2021-10-26 |  | 36 | 2021-10-27 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1029220211018-3Excavator - 36 ton- After Jan 106881.76 | Corbiere and Sons Contracting1029220211018-3Excavator - 36 ton- After Jan 106881.76INV #155 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10292 | 20211018-3 | 53510612 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 5 | Dynamic | 98.61 | 0 |  |  | 657.4 | 85.462 | 742.862 | 2021-10-18 | 0 | INV #155 | 2021-12-02 | 171 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Capping on Del Lake from C190-C189 | 6 | C186-C195 | Del Lake | 0 | 2021-10-26 |  | 36 | 2021-10-27 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1029220211018-3Dozer D6 or equal- After Jan 105657.4 | Corbiere and Sons Contracting1029220211018-3Dozer D6 or equal- After Jan 105657.4INV #155 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10289 | 20211017-3 | 53510612 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 34 | HR |  |  | 75 | 0 | 2550 | 331.5 | 2881.5 | 2021-10-17 | 0 | INV #155 | 2021-12-02 | 171 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Capping on Del Lake from C190-C189 | 6 | C186-C195 | Del Lake | 0 | 2021-10-26 |  | 36 | 2021-10-27 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1028920211017-3Operator - Principle - After Jan 10342550 | Corbiere and Sons Contracting1028920211017-3Operator - Principle - After Jan 10342550INV #155 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10289 | 20211017-3 | 53510612 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2021-10-17 | 0 | INV #155 | 2021-12-02 | 171 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Capping on Del Lake from C190-C189 | 6 | C186-C195 | Del Lake | 0 | 2021-10-26 |  | 36 | 2021-10-27 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1028920211017-3L.O.A.3630 | Corbiere and Sons Contracting1028920211017-3L.O.A.3630INV #155 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10289 | 20211017-3 | 53510612 | Access | 0 | Foreman | 95 | 4 | HR |  |  | 95 | 0 | 380 | 49.4 | 429.4 | 2021-10-17 | 0 | INV #155 | 2021-12-02 | 171 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Capping on Del Lake from C190-C189 | 6 | C186-C195 | Del Lake | 0 | 2021-10-26 |  | 36 | 2021-10-27 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1028920211017-3Foreman4380 | Corbiere and Sons Contracting1028920211017-3Foreman4380INV #155 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10289 | 20211017-3 | 53510612 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-10-17 | 0 | INV #155 | 2021-12-02 | 171 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Capping on Del Lake from C190-C189 | 6 | C186-C195 | Del Lake | 0 | 2021-10-26 |  | 36 | 2021-10-27 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1028920211017-3Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting1028920211017-3Rock Truck - 30 Ton- After Jan 10111518.55INV #155 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10289 | 20211017-3 | 53510612 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-10-17 | 0 | INV #155 | 2021-12-02 | 171 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Capping on Del Lake from C190-C189 | 6 | C186-C195 | Del Lake | 0 | 2021-10-26 |  | 36 | 2021-10-27 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1028920211017-3Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting1028920211017-3Light Truck - Pick up- After Jan 102487.5INV #155 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10289 | 20211017-3 | 53510612 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2021-10-17 | 0 | INV #155 | 2021-12-02 | 171 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Capping on Del Lake from C190-C189 | 6 | C186-C195 | Del Lake | 0 | 2021-10-26 |  | 36 | 2021-10-27 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1028920211017-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting1028920211017-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV #155 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10289 | 20211017-3 | 53510612 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-10-17 | 0 | INV #155 | 2021-12-02 | 171 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Capping on Del Lake from C190-C189 | 6 | C186-C195 | Del Lake | 0 | 2021-10-26 |  | 36 | 2021-10-27 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1028920211017-3Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting1028920211017-3Excavator - 36 ton- After Jan 1091322.64INV #155 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10289 | 20211017-3 | 53510612 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2021-10-17 | 0 | INV #155 | 2021-12-02 | 171 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Capping on Del Lake from C190-C189 | 6 | C186-C195 | Del Lake | 0 | 2021-10-26 |  | 36 | 2021-10-27 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1028920211017-3Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting1028920211017-3Dozer D6 or equal- After Jan 10111446.28INV #155 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10287 | 20211016-4 | 53510612 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 6 | HR |  |  | 70 | 0 | 420 | 54.6 | 474.6 | 2021-10-16 | 0 | INV #155 | 2021-12-02 | 171 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Capping on Del Lake from C190-C189 | 6 | C186-C195 | Del lake | 0 | 2021-10-26 |  | 36 | 2021-10-27 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1028720211016-4Driver - AZ - After Jan 106420 | Corbiere and Sons Contracting1028720211016-4Driver - AZ - After Jan 106420INV #155 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10287 | 20211016-4 | 53510612 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 24 | HR |  |  | 75 | 0 | 1800 | 234 | 2034 | 2021-10-16 | 0 | INV #155 | 2021-12-02 | 171 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Capping on Del Lake from C190-C189 | 6 | C186-C195 | Del lake | 0 | 2021-10-26 |  | 36 | 2021-10-27 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1028720211016-4Operator - Principle - After Jan 10241800 | Corbiere and Sons Contracting1028720211016-4Operator - Principle - After Jan 10241800INV #155 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10287 | 20211016-4 | 53510612 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-10-16 | 0 | INV #155 | 2021-12-02 | 171 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Capping on Del Lake from C190-C189 | 6 | C186-C195 | Del lake | 0 | 2021-10-26 |  | 36 | 2021-10-27 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1028720211016-4L.O.A.2420 | Corbiere and Sons Contracting1028720211016-4L.O.A.2420INV #155 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10287 | 20211016-4 | 53510612 | Access | 0 | Foreman | 95 | 4 | HR |  |  | 95 | 0 | 380 | 49.4 | 429.4 | 2021-10-16 | 0 | INV #155 | 2021-12-02 | 171 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Capping on Del Lake from C190-C189 | 6 | C186-C195 | Del lake | 0 | 2021-10-26 |  | 36 | 2021-10-27 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1028720211016-4Foreman4380 | Corbiere and Sons Contracting1028720211016-4Foreman4380INV #155 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10287 | 20211016-4 | 53510612 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 11 | Dynamic | 103.54 | 0 |  |  | 1518.55 | 197.4115 | 1715.9615 | 2021-10-16 | 0 | INV #155 | 2021-12-02 | 171 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Capping on Del Lake from C190-C189 | 6 | C186-C195 | Del lake | 0 | 2021-10-26 |  | 36 | 2021-10-27 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1028720211016-4Rock Truck - 30 Ton- After Jan 10111518.55 | Corbiere and Sons Contracting1028720211016-4Rock Truck - 30 Ton- After Jan 10111518.55INV #155 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10287 | 20211016-4 | 53510612 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-10-16 | 0 | INV #155 | 2021-12-02 | 171 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Capping on Del Lake from C190-C189 | 6 | C186-C195 | Del lake | 0 | 2021-10-26 |  | 36 | 2021-10-27 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1028720211016-4Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting1028720211016-4Light Truck - Pick up- After Jan 102487.5INV #155 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10287 | 20211016-4 | 53510612 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2021-10-16 | 0 | INV #155 | 2021-12-02 | 171 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Capping on Del Lake from C190-C189 | 6 | C186-C195 | Del lake | 0 | 2021-10-26 |  | 36 | 2021-10-27 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1028720211016-4Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting1028720211016-4Excavator Thumb - 30 - 50 ton- After Jan 1011134.31INV #155 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10287 | 20211016-4 | 53510612 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2021-10-16 | 0 | INV #155 | 2021-12-02 | 171 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Capping on Del Lake from C190-C189 | 6 | C186-C195 | Del lake | 0 | 2021-10-26 |  | 36 | 2021-10-27 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1028720211016-4Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting1028720211016-4Excavator - 36 ton- After Jan 10111616.56INV #155 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10287 | 20211016-4 | 53510612 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 6 | Dynamic | 98.61 | 0 |  |  | 788.88 | 102.5544 | 891.4344 | 2021-10-16 | 0 | INV #155 | 2021-12-02 | 171 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Capping on Del Lake from C190-C189 | 6 | C186-C195 | Del lake | 0 | 2021-10-26 |  | 36 | 2021-10-27 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1028720211016-4Dozer D6 or equal- After Jan 106788.88 | Corbiere and Sons Contracting1028720211016-4Dozer D6 or equal- After Jan 106788.88INV #155 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10564 | 20211123-3 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-11-23 | 0 | INV #155 | 2021-12-02 | 171 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Access Maintenance on Hare Lake Road | 6 | C257 | Hare Lake Creek | 0 | 2021-11-25 |  | 36 | 2021-11-26 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1056420211123-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1056420211123-3Operator - Principle - After Jan 1011825INV #155 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10564 | 20211123-3 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-11-23 | 0 | INV #155 | 2021-12-02 | 171 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Access Maintenance on Hare Lake Road | 6 | C257 | Hare Lake Creek | 0 | 2021-11-25 |  | 36 | 2021-11-26 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1056420211123-3L.O.A.1210 | Corbiere and Sons Contracting1056420211123-3L.O.A.1210INV #155 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10564 | 20211123-3 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-11-23 | 0 | INV #155 | 2021-12-02 | 171 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Access Maintenance on Hare Lake Road | 6 | C257 | Hare Lake Creek | 0 | 2021-11-25 |  | 36 | 2021-11-26 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1056420211123-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1056420211123-3Light Truck - Pick up- After Jan 101243.75INV #155 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10564 | 20211123-3 | 53510611 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 9.16 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2021-11-23 | 0 | INV #155 | 2021-12-02 | 171 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Access Maintenance on Hare Lake Road | 6 | C257 | Hare Lake Creek | 0 | 2021-11-25 |  | 36 | 2021-11-26 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1056420211123-3Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting1056420211123-3Excavator Thumb - 30 - 50 ton- After Jan 1010122.1INV #155 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10564 | 20211123-3 | 53510611 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10 | Dynamic | 110.22 | 0 |  |  | 1469.6 | 191.048 | 1660.648 | 2021-11-23 | 0 | INV #155 | 2021-12-02 | 171 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Access Maintenance on Hare Lake Road | 6 | C257 | Hare Lake Creek | 0 | 2021-11-25 |  | 36 | 2021-11-26 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1056420211123-3Excavator - 36 ton- After Jan 10101469.6 | Corbiere and Sons Contracting1056420211123-3Excavator - 36 ton- After Jan 10101469.6INV #155 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11033 | 20220111-9 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 1 | HR |  |  | 75 | 0 | 75 | 9.75 | 84.75 | 2022-01-11 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | OP walked 350 Ex out of Red Sucker | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-01-13 |  | 37 | 2022-01-14 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1103320220111-9Operator - Principle - After Jan 10175 | Corbiere and Sons Contracting1103320220111-9Operator - Principle - After Jan 10175INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11033 | 20220111-9 | 53510611 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 1 | Dynamic | 110.22 | 0 |  |  | 146.96 | 19.1048 | 166.0648 | 2022-01-11 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | OP walked 350 Ex out of Red Sucker | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-01-13 |  | 37 | 2022-01-14 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1103320220111-9Excavator - 36 ton- After Jan 101146.96 | Corbiere and Sons Contracting1103320220111-9Excavator - 36 ton- After Jan 101146.96INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11032 | 20220111-8 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 5.5 | HR |  |  | 70 | 0 | 385 | 50.05 | 435.05 | 2022-01-11 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dz floated over to Neys and did Road Maintenace rest of day | 6 | C219-C235 | Neys | 0 | 2022-01-13 |  | 37 | 2022-01-14 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1103220220111-8Driver - AZ - After Jan 105.5385 | Corbiere and Sons Contracting1103220220111-8Driver - AZ - After Jan 105.5385INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11032 | 20220111-8 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 8 | HR |  |  | 75 | 0 | 600 | 78 | 678 | 2022-01-11 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dz floated over to Neys and did Road Maintenace rest of day | 6 | C219-C235 | Neys | 0 | 2022-01-13 |  | 37 | 2022-01-14 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1103220220111-8Operator - Principle - After Jan 108600 | Corbiere and Sons Contracting1103220220111-8Operator - Principle - After Jan 108600INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11032 | 20220111-8 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2022-01-11 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dz floated over to Neys and did Road Maintenace rest of day | 6 | C219-C235 | Neys | 0 | 2022-01-13 |  | 37 | 2022-01-14 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1103220220111-8L.O.A.1210 | Corbiere and Sons Contracting1103220220111-8L.O.A.1210INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11032 | 20220111-8 | 53510611 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 5.5 | Dynamic | 91.79 | 0 |  |  | 673.145 | 87.5088 | 760.6539 | 2022-01-11 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dz floated over to Neys and did Road Maintenace rest of day | 6 | C219-C235 | Neys | 0 | 2022-01-13 |  | 37 | 2022-01-14 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1103220220111-8Tractor Trailer - 60 Ton- After Jan 105.5673.145 | Corbiere and Sons Contracting1103220220111-8Tractor Trailer - 60 Ton- After Jan 105.5673.145INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11032 | 20220111-8 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-11 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dz floated over to Neys and did Road Maintenace rest of day | 6 | C219-C235 | Neys | 0 | 2022-01-13 |  | 37 | 2022-01-14 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1103220220111-8Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1103220220111-8Light Truck - Pick up- After Jan 101243.75INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11032 | 20220111-8 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 5.5 | Dynamic | 98.61 | 0 |  |  | 723.14 | 94.0082 | 817.1482 | 2022-01-11 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dz floated over to Neys and did Road Maintenace rest of day | 6 | C219-C235 | Neys | 0 | 2022-01-13 |  | 37 | 2022-01-14 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1103220220111-8Dozer D6 or equal- After Jan 105.5723.14 | Corbiere and Sons Contracting1103220220111-8Dozer D6 or equal- After Jan 105.5723.14INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11023 | 20220110-9 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 5 | HR |  |  | 70 | 0 | 350 | 45.5 | 395.5 | 2022-01-10 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved D6 into Lake A and OP did WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-01-12 |  | 37 | 2022-01-14 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1102320220110-9Driver - AZ - After Jan 105350 | Corbiere and Sons Contracting1102320220110-9Driver - AZ - After Jan 105350INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11023 | 20220110-9 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 9 | HR |  |  | 75 | 0 | 675 | 87.75 | 762.75 | 2022-01-10 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved D6 into Lake A and OP did WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-01-12 |  | 37 | 2022-01-14 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1102320220110-9Operator - Principle - After Jan 109675 | Corbiere and Sons Contracting1102320220110-9Operator - Principle - After Jan 109675INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11023 | 20220110-9 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2022-01-10 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved D6 into Lake A and OP did WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-01-12 |  | 37 | 2022-01-14 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1102320220110-9L.O.A.1210 | Corbiere and Sons Contracting1102320220110-9L.O.A.1210INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11023 | 20220110-9 | 53510611 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 5 | Dynamic | 91.79 | 0 |  |  | 611.95 | 79.5535 | 691.5035 | 2022-01-10 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved D6 into Lake A and OP did WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-01-12 |  | 37 | 2022-01-14 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1102320220110-9Tractor Trailer - 60 Ton- After Jan 105611.95 | Corbiere and Sons Contracting1102320220110-9Tractor Trailer - 60 Ton- After Jan 105611.95INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11023 | 20220110-9 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-10 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved D6 into Lake A and OP did WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-01-12 |  | 37 | 2022-01-14 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1102320220110-9Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1102320220110-9Light Truck - Pick up- After Jan 101243.75INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11023 | 20220110-9 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 5 | Dynamic | 98.61 | 0 |  |  | 657.4 | 85.462 | 742.862 | 2022-01-10 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved D6 into Lake A and OP did WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-01-12 |  | 37 | 2022-01-14 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1102320220110-9Dozer D6 or equal- After Jan 105657.4 | Corbiere and Sons Contracting1102320220110-9Dozer D6 or equal- After Jan 105657.4INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11026 | 20220110-12 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 4 | HR |  |  | 0 | 0 | 300 | 39 | 339 | 2022-01-10 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C203-C209 | Dead Horse Creek | 0 | 2022-01-12 |  | 37 | 2022-01-14 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1102620220110-12Operator - Principle - After Jan 104300 | Corbiere and Sons Contracting1102620220110-12Operator - Principle - After Jan 104300INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11026 | 20220110-12 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 4 |  | 0 | 0 |  |  | 320 | 41.6 | 361.6 | 2022-01-10 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C203-C209 | Dead Horse Creek | 0 | 2022-01-12 |  | 37 | 2022-01-14 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1102620220110-12Pickup w/ plow and sander4320 | Corbiere and Sons Contracting1102620220110-12Pickup w/ plow and sander4320INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11025 | 20220110-11 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 4 | HR |  |  | 0 | 0 | 300 | 39 | 339 | 2022-01-10 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C215-C216 | Little Pic River | 0 | 2022-01-12 |  | 37 | 2022-01-14 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1102520220110-11Operator - Principle - After Jan 104300 | Corbiere and Sons Contracting1102520220110-11Operator - Principle - After Jan 104300INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11025 | 20220110-11 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 4 |  | 0 | 0 |  |  | 320 | 41.6 | 361.6 | 2022-01-10 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C215-C216 | Little Pic River | 0 | 2022-01-12 |  | 37 | 2022-01-14 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1102520220110-11Pickup w/ plow and sander4320 | Corbiere and Sons Contracting1102520220110-11Pickup w/ plow and sander4320INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11024 | 20220110-10 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 4 | HR |  |  | 75 | 0 | 300 | 39 | 339 | 2022-01-10 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C210-C213 | Middleton | 0 | 2022-01-12 |  | 37 | 2022-01-14 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1102420220110-10Operator - Principle - After Jan 104300 | Corbiere and Sons Contracting1102420220110-10Operator - Principle - After Jan 104300INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11024 | 20220110-10 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2022-01-10 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C210-C213 | Middleton | 0 | 2022-01-12 |  | 37 | 2022-01-14 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1102420220110-10L.O.A.1210 | Corbiere and Sons Contracting1102420220110-10L.O.A.1210INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11024 | 20220110-10 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 4 |  | 0 | 0 |  |  | 320 | 41.6 | 361.6 | 2022-01-10 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C210-C213 | Middleton | 0 | 2022-01-12 |  | 37 | 2022-01-14 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1102420220110-10Pickup w/ plow and sander4320 | Corbiere and Sons Contracting1102420220110-10Pickup w/ plow and sander4320INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11012 | 20220109-9 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 4 | HR |  |  | 0 | 0 | 300 | 39 | 339 | 2022-01-09 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Del Lake | 6 | C186-C195 | Del Lake | 0 | 2022-01-12 |  | 37 | 2022-01-14 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1101220220109-9Operator - Principle - After Jan 104300 | Corbiere and Sons Contracting1101220220109-9Operator - Principle - After Jan 104300INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11012 | 20220109-9 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 4 |  | 0 | 0 |  |  | 320 | 41.6 | 361.6 | 2022-01-09 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Del Lake | 6 | C186-C195 | Del Lake | 0 | 2022-01-12 |  | 37 | 2022-01-14 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1101220220109-9Pickup w/ plow and sander4320 | Corbiere and Sons Contracting1101220220109-9Pickup w/ plow and sander4320INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11011 | 20220109-8 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 4 | HR |  |  | 0 | 0 | 300 | 39 | 339 | 2022-01-09 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Lake A | 6 | C130-C151 | Lake A | 0 | 2022-01-12 |  | 37 | 2022-01-14 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1101120220109-8Operator - Principle - After Jan 104300 | Corbiere and Sons Contracting1101120220109-8Operator - Principle - After Jan 104300INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11011 | 20220109-8 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 4 |  | 0 | 0 |  |  | 320 | 41.6 | 361.6 | 2022-01-09 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Lake A | 6 | C130-C151 | Lake A | 0 | 2022-01-12 |  | 37 | 2022-01-14 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1101120220109-8Pickup w/ plow and sander4320 | Corbiere and Sons Contracting1101120220109-8Pickup w/ plow and sander4320INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11016 | 20220109-13 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 22 | HR |  |  | 70 | 0 | 1540 | 200.2 | 1740.2 | 2022-01-09 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Demobbing 336 Ex from Neys Road | 6 | C219-C235 | Neys | 0 | 2022-01-12 |  | 37 | 2022-01-14 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1101620220109-13Driver - AZ - After Jan 10221540 | Corbiere and Sons Contracting1101620220109-13Driver - AZ - After Jan 10221540INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11016 | 20220109-13 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2022-01-09 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Demobbing 336 Ex from Neys Road | 6 | C219-C235 | Neys | 0 | 2022-01-12 |  | 37 | 2022-01-14 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1101620220109-13L.O.A.1210 | Corbiere and Sons Contracting1101620220109-13L.O.A.1210INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11016 | 20220109-13 | 53510611 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 22 | Dynamic | 91.79 | 0 |  |  | 2692.58 | 350.0354 | 3042.6154 | 2022-01-09 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Demobbing 336 Ex from Neys Road | 6 | C219-C235 | Neys | 0 | 2022-01-12 |  | 37 | 2022-01-14 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1101620220109-13Tractor Trailer - 60 Ton- After Jan 10222692.58 | Corbiere and Sons Contracting1101620220109-13Tractor Trailer - 60 Ton- After Jan 10222692.58INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11014 | 20220109-11 | 53510611 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 3 | HR | 0 | 0 |  |  | 36.63 | 4.7619 | 41.3919 | 2022-01-09 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Roads in Neys | 6 | C219-C236 | Neys | 0 | 2022-01-12 |  | 37 | 2022-01-14 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1101420220109-11Excavator Thumb - 30 - 50 ton- After Jan 10336.63 | Corbiere and Sons Contracting1101420220109-11Excavator Thumb - 30 - 50 ton- After Jan 10336.63INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11013 | 20220109-10 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 4 | HR |  |  | 0 | 0 | 300 | 39 | 339 | 2022-01-09 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Neys | 6 | C219-C235 | Neys | 0 | 2022-01-12 |  | 37 | 2022-01-14 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1101320220109-10Operator - Principle - After Jan 104300 | Corbiere and Sons Contracting1101320220109-10Operator - Principle - After Jan 104300INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11013 | 20220109-10 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2022-01-09 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Neys | 6 | C219-C235 | Neys | 0 | 2022-01-12 |  | 37 | 2022-01-14 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1101320220109-10L.O.A.1210 | Corbiere and Sons Contracting1101320220109-10L.O.A.1210INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11013 | 20220109-10 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-09 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Neys | 6 | C219-C235 | Neys | 0 | 2022-01-12 |  | 37 | 2022-01-14 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1101320220109-10Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1101320220109-10Light Truck - Pick up- After Jan 101243.75INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11013 | 20220109-10 | 53510611 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 3 | HR | 9.16 | 0 |  |  | 36.63 | 4.7619 | 41.3919 | 2022-01-09 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Neys | 6 | C219-C235 | Neys | 0 | 2022-01-12 |  | 37 | 2022-01-14 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1101320220109-10Excavator Thumb - 30 - 50 ton- After Jan 10336.63 | Corbiere and Sons Contracting1101320220109-10Excavator Thumb - 30 - 50 ton- After Jan 10336.63INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11013 | 20220109-10 | 53510611 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 3 | Dynamic | 103.84 | 0 |  |  | 415.35 | 53.9955 | 469.3455 | 2022-01-09 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Neys | 6 | C219-C235 | Neys | 0 | 2022-01-12 |  | 37 | 2022-01-14 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1101320220109-10Excavator - 30 ton- After Jan 103415.35 | Corbiere and Sons Contracting1101320220109-10Excavator - 30 ton- After Jan 103415.35INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11005 | 20220108-7 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5 | HR |  |  | 75 | 0 | 375 | 48.75 | 423.75 | 2022-01-08 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Work shutdown on Neys Early due to safety concerns with weather | 6 | C219-C235 | Neys | 0 | 2022-01-11 |  | 37 | 2022-01-14 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1100520220108-7Operator - Principle - After Jan 105375 | Corbiere and Sons Contracting1100520220108-7Operator - Principle - After Jan 105375INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11005 | 20220108-7 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2022-01-08 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Work shutdown on Neys Early due to safety concerns with weather | 6 | C219-C235 | Neys | 0 | 2022-01-11 |  | 37 | 2022-01-14 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1100520220108-7L.O.A.1210 | Corbiere and Sons Contracting1100520220108-7L.O.A.1210INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11005 | 20220108-7 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-08 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Work shutdown on Neys Early due to safety concerns with weather | 6 | C219-C235 | Neys | 0 | 2022-01-11 |  | 37 | 2022-01-14 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1100520220108-7Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1100520220108-7Light Truck - Pick up- After Jan 101243.75INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11005 | 20220108-7 | 53510611 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 5 | Dynamic | 103.84 | 0 |  |  | 692.25 | 89.9925 | 782.2425 | 2022-01-08 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Work shutdown on Neys Early due to safety concerns with weather | 6 | C219-C235 | Neys | 0 | 2022-01-11 |  | 37 | 2022-01-14 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1100520220108-7Excavator - 30 ton- After Jan 105692.25 | Corbiere and Sons Contracting1100520220108-7Excavator - 30 ton- After Jan 105692.25INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10999 | 20220107-7 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2022-01-07 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Lake A | 6 | C130-C151 | Lake A | 0 | 2022-01-11 |  | 37 | 2022-01-14 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1099920220107-7Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1099920220107-7Operator - Principle - After Jan 1011825INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10999 | 20220107-7 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2022-01-07 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Lake A | 6 | C130-C151 | Lake A | 0 | 2022-01-11 |  | 37 | 2022-01-14 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1099920220107-7L.O.A.1210 | Corbiere and Sons Contracting1099920220107-7L.O.A.1210INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10999 | 20220107-7 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-07 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Lake A | 6 | C130-C151 | Lake A | 0 | 2022-01-11 |  | 37 | 2022-01-14 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1099920220107-7Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1099920220107-7Light Truck - Pick up- After Jan 101243.75INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10999 | 20220107-7 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10 | Dynamic | 98.61 | 0 |  |  | 1314.8 | 170.924 | 1485.724 | 2022-01-07 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Lake A | 6 | C130-C151 | Lake A | 0 | 2022-01-11 |  | 37 | 2022-01-14 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1099920220107-7Dozer D6 or equal- After Jan 10101314.8 | Corbiere and Sons Contracting1099920220107-7Dozer D6 or equal- After Jan 10101314.8INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10994 | 20220106-7 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 8 | HR |  |  | 70 | 0 | 560 | 72.8 | 632.8 | 2022-01-06 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved Dz over to Lake A and he did WAM Activities for rest of day | 6 | C130-C151 | Lake A | 0 | 2022-01-11 |  | 37 | 2022-01-14 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1099420220106-7Driver - AZ - After Jan 108560 | Corbiere and Sons Contracting1099420220106-7Driver - AZ - After Jan 108560INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10994 | 20220106-7 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2022-01-06 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved Dz over to Lake A and he did WAM Activities for rest of day | 6 | C130-C151 | Lake A | 0 | 2022-01-11 |  | 37 | 2022-01-14 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1099420220106-7Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1099420220106-7Operator - Principle - After Jan 1011825INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10994 | 20220106-7 | 53510611 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2022-01-06 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved Dz over to Lake A and he did WAM Activities for rest of day | 6 | C130-C151 | Lake A | 0 | 2022-01-11 |  | 37 | 2022-01-14 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1099420220106-7L.O.A.2420 | Corbiere and Sons Contracting1099420220106-7L.O.A.2420INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10994 | 20220106-7 | 53510611 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 8 | Dynamic | 91.79 | 0 |  |  | 979.12 | 127.2856 | 1106.4056 | 2022-01-06 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved Dz over to Lake A and he did WAM Activities for rest of day | 6 | C130-C151 | Lake A | 0 | 2022-01-11 |  | 37 | 2022-01-14 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1099420220106-7Tractor Trailer - 60 Ton- After Jan 108979.12 | Corbiere and Sons Contracting1099420220106-7Tractor Trailer - 60 Ton- After Jan 108979.12INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10994 | 20220106-7 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-06 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved Dz over to Lake A and he did WAM Activities for rest of day | 6 | C130-C151 | Lake A | 0 | 2022-01-11 |  | 37 | 2022-01-14 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1099420220106-7Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1099420220106-7Light Truck - Pick up- After Jan 101243.75INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10994 | 20220106-7 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 5 | Dynamic | 98.61 | 0 |  |  | 657.4 | 85.462 | 742.862 | 2022-01-06 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved Dz over to Lake A and he did WAM Activities for rest of day | 6 | C130-C151 | Lake A | 0 | 2022-01-11 |  | 37 | 2022-01-14 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1099420220106-7Dozer D6 or equal- After Jan 105657.4 | Corbiere and Sons Contracting1099420220106-7Dozer D6 or equal- After Jan 105657.4INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10989 | 20220105-8 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 3 | HR |  |  | 0 | 0 | 225 | 29.25 | 254.25 | 2022-01-05 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Neys Road | 6 | C219-C235 | Neys | 0 | 2022-01-11 |  | 37 | 2022-01-14 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1098920220105-8Operator - Principle - After Jan 103225 | Corbiere and Sons Contracting1098920220105-8Operator - Principle - After Jan 103225INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10989 | 20220105-8 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 3 |  | 0 | 0 |  |  | 240 | 31.2 | 271.2 | 2022-01-05 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Neys Road | 6 | C219-C235 | Neys | 0 | 2022-01-11 |  | 37 | 2022-01-14 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1098920220105-8Pickup w/ plow and sander3240 | Corbiere and Sons Contracting1098920220105-8Pickup w/ plow and sander3240INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10988 | 20220105-7 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 3 | HR |  |  | 0 | 0 | 225 | 29.25 | 254.25 | 2022-01-05 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities for C129 | 6 | C129 | Lake B | 0 | 2022-01-11 |  | 37 | 2022-01-14 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1098820220105-7Operator - Principle - After Jan 103225 | Corbiere and Sons Contracting1098820220105-7Operator - Principle - After Jan 103225INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10988 | 20220105-7 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 3 |  | 0 | 0 |  |  | 240 | 31.2 | 271.2 | 2022-01-05 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities for C129 | 6 | C129 | Lake B | 0 | 2022-01-11 |  | 37 | 2022-01-14 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1098820220105-7Pickup w/ plow and sander3240 | Corbiere and Sons Contracting1098820220105-7Pickup w/ plow and sander3240INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10980 | 20220103-8 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 3 | HR |  |  | 70 | 0 | 210 | 27.3 | 237.3 | 2022-01-03 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2022-01-11 |  | 37 | 2022-01-13 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1098020220103-8Operator - Intermdiate - After Jan 103210 | Corbiere and Sons Contracting1098020220103-8Operator - Intermdiate - After Jan 103210INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10980 | 20220103-8 | 53510611 | Access | 0 | Pickup w/ plow | 50 | 3 | HR | 0 | 0 |  |  | 150 | 19.5 | 169.5 | 2022-01-03 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2022-01-11 |  | 37 | 2022-01-13 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1098020220103-8Pickup w/ plow3150 | Corbiere and Sons Contracting1098020220103-8Pickup w/ plow3150INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10979 | 20220103-7 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 3 | HR |  |  | 0 | 0 | 225 | 29.25 | 254.25 | 2022-01-03 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Neys | 6 | C219-C235 | Neys | 0 | 2022-01-11 |  | 37 | 2022-01-13 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1097920220103-7Operator - Principle - After Jan 103225 | Corbiere and Sons Contracting1097920220103-7Operator - Principle - After Jan 103225INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10979 | 20220103-7 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-01-03 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Neys | 6 | C219-C235 | Neys | 0 | 2022-01-11 |  | 37 | 2022-01-13 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1097920220103-7Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1097920220103-7Operator - Principle - After Jan 1011825INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10979 | 20220103-7 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-01-03 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Neys | 6 | C219-C235 | Neys | 0 | 2022-01-11 |  | 37 | 2022-01-13 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1097920220103-7L.O.A.1210 | Corbiere and Sons Contracting1097920220103-7L.O.A.1210INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10979 | 20220103-7 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 3 |  | 0 | 0 |  |  | 240 | 31.2 | 271.2 | 2022-01-03 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Neys | 6 | C219-C235 | Neys | 0 | 2022-01-11 |  | 37 | 2022-01-13 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1097920220103-7Pickup w/ plow and sander3240 | Corbiere and Sons Contracting1097920220103-7Pickup w/ plow and sander3240INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10979 | 20220103-7 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-03 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Neys | 6 | C219-C235 | Neys | 0 | 2022-01-11 |  | 37 | 2022-01-13 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1097920220103-7Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1097920220103-7Light Truck - Pick up- After Jan 101243.75INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10979 | 20220103-7 | 53510611 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2022-01-03 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Neys | 6 | C219-C235 | Neys | 0 | 2022-01-11 |  | 37 | 2022-01-13 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1097920220103-7Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting1097920220103-7Excavator Thumb - 30 - 50 ton- After Jan 109109.89INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10979 | 20220103-7 | 53510611 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2022-01-03 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Neys | 6 | C219-C235 | Neys | 1 | 2022-01-11 |  | 37 | 2022-01-13 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1097920220103-7Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting1097920220103-7Excavator - 36 ton- After Jan 1091322.64INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10969 | 20220102-9 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 0 | 0 | 450 | 58.5 | 508.5 | 2022-01-02 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Little Pic | 6 | C215-C216 | Little Pie River | 0 | 2022-01-10 |  | 37 | 2022-01-12 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1096920220102-9Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting1096920220102-9Operator - Principle - After Jan 106450INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10969 | 20220102-9 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-01-02 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Little Pic | 6 | C215-C216 | Little Pie River | 0 | 2022-01-10 |  | 37 | 2022-01-12 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1096920220102-9L.O.A.1210 | Corbiere and Sons Contracting1096920220102-9L.O.A.1210INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10969 | 20220102-9 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 6 |  | 0 | 0 |  |  | 480 | 62.4 | 542.4 | 2022-01-02 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Little Pic | 6 | C215-C216 | Little Pie River | 0 | 2022-01-10 |  | 37 | 2022-01-12 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1096920220102-9Pickup w/ plow and sander6480 | Corbiere and Sons Contracting1096920220102-9Pickup w/ plow and sander6480INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10968 | 20220102-8 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5 | HR |  |  | 0 | 0 | 375 | 48.75 | 423.75 | 2022-01-02 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jesse building road on Red Sucker towards C256 (Used Valard Ex - Corbiere fuel) | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2022-01-10 |  | 37 | 2022-01-12 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1096820220102-8Operator - Principle - After Jan 105375 | Corbiere and Sons Contracting1096820220102-8Operator - Principle - After Jan 105375INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10968 | 20220102-8 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2022-01-02 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jesse building road on Red Sucker towards C256 (Used Valard Ex - Corbiere fuel) | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2022-01-10 |  | 37 | 2022-01-12 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1096820220102-8L.O.A.1210 | Corbiere and Sons Contracting1096820220102-8L.O.A.1210INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10968 | 20220102-8 | 53510611 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 1 | HR | 9.16 | 0 |  |  | 12.21 | 1.5873 | 13.7973 | 2022-01-02 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jesse building road on Red Sucker towards C256 (Used Valard Ex - Corbiere fuel) | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2022-01-10 |  | 37 | 2022-01-12 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1096820220102-8Excavator Thumb - 30 - 50 ton- After Jan 10112.21 | Corbiere and Sons Contracting1096820220102-8Excavator Thumb - 30 - 50 ton- After Jan 10112.21INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10968 | 20220102-8 | 53510611 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 1 | Dynamic | 110.22 | 0 |  |  | 146.96 | 19.1048 | 166.0648 | 2022-01-02 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jesse building road on Red Sucker towards C256 (Used Valard Ex - Corbiere fuel) | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2022-01-10 |  | 37 | 2022-01-12 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1096820220102-8Excavator - 36 ton- After Jan 101146.96 | Corbiere and Sons Contracting1096820220102-8Excavator - 36 ton- After Jan 101146.96INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10967 | 20220102-7 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 3 | HR |  |  | 75 | 0 | 225 | 29.25 | 254.25 | 2022-01-02 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Walking out D8 back to front of Red Sucker - Grader working at Red Sucker | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2022-01-10 |  | 37 | 2022-01-12 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1096720220102-7Operator - Principle - After Jan 103225 | Corbiere and Sons Contracting1096720220102-7Operator - Principle - After Jan 103225INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10967 | 20220102-7 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 1 | HR |  |  | 75 | 0 | 75 | 9.75 | 84.75 | 2022-01-02 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Walking out D8 back to front of Red Sucker - Grader working at Red Sucker | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2022-01-10 |  | 37 | 2022-01-12 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1096720220102-7Operator - Principle - After Jan 10175 | Corbiere and Sons Contracting1096720220102-7Operator - Principle - After Jan 10175INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10967 | 20220102-7 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-02 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Walking out D8 back to front of Red Sucker - Grader working at Red Sucker | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2022-01-10 |  | 37 | 2022-01-12 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1096720220102-7Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1096720220102-7Light Truck - Pick up- After Jan 101243.75INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10967 | 20220102-7 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 3 | Dynamic | 95.24 | 0 |  |  | 380.94 | 49.5222 | 430.4622 | 2022-01-02 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Walking out D8 back to front of Red Sucker - Grader working at Red Sucker | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2022-01-10 |  | 37 | 2022-01-12 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1096720220102-7Grader - Cat 12 to 14 or equal- After Jan 103380.94 | Corbiere and Sons Contracting1096720220102-7Grader - Cat 12 to 14 or equal- After Jan 103380.94INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10967 | 20220102-7 | 53510611 | Access | 0 | Dozer D8 or equal- After Jan 10 | 217.5 | 1 | Dynamic | 163.13 | 0 |  |  | 217.5 | 28.275 | 245.775 | 2022-01-02 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Walking out D8 back to front of Red Sucker - Grader working at Red Sucker | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2022-01-10 |  | 37 | 2022-01-12 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1096720220102-7Dozer D8 or equal- After Jan 101217.5 | Corbiere and Sons Contracting1096720220102-7Dozer D8 or equal- After Jan 101217.5INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10974 | 20220102-14 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 2 | HR |  |  | 0 | 0 | 140 | 18.2 | 158.2 | 2022-01-02 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Santoy Lake | 6 | C158-C170 | Santoy Lake | 0 | 2022-01-10 |  | 37 | 2022-01-12 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1097420220102-14Operator - Intermdiate - After Jan 102140 | Corbiere and Sons Contracting1097420220102-14Operator - Intermdiate - After Jan 102140INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10974 | 20220102-14 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 2 |  | 0 | 0 |  |  | 160 | 20.8 | 180.8 | 2022-01-02 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Santoy Lake | 6 | C158-C170 | Santoy Lake | 0 | 2022-01-10 |  | 37 | 2022-01-12 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1097420220102-14Pickup w/ plow and sander2160 | Corbiere and Sons Contracting1097420220102-14Pickup w/ plow and sander2160INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10973 | 20220102-13 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 3 | HR |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-01-02 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Ripple | 6 | C198-C202 | Ripple Lake | 0 | 2022-01-10 |  | 37 | 2022-01-12 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1097320220102-13Operator - Intermdiate - After Jan 103210 | Corbiere and Sons Contracting1097320220102-13Operator - Intermdiate - After Jan 103210INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10973 | 20220102-13 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 3 |  | 0 | 0 |  |  | 240 | 31.2 | 271.2 | 2022-01-02 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Ripple | 6 | C198-C202 | Ripple Lake | 0 | 2022-01-10 |  | 37 | 2022-01-12 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1097320220102-13Pickup w/ plow and sander3240 | Corbiere and Sons Contracting1097320220102-13Pickup w/ plow and sander3240INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10972 | 20220102-12 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 3 | HR |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-01-02 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities onNeys | 6 | C219-C235 | Neys | 0 | 2022-01-10 |  | 37 | 2022-01-12 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1097220220102-12Operator - Intermdiate - After Jan 103210 | Corbiere and Sons Contracting1097220220102-12Operator - Intermdiate - After Jan 103210INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10972 | 20220102-12 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 3 |  | 0 | 0 |  |  | 240 | 31.2 | 271.2 | 2022-01-02 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities onNeys | 6 | C219-C235 | Neys | 0 | 2022-01-10 |  | 37 | 2022-01-12 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1097220220102-12Pickup w/ plow and sander3240 | Corbiere and Sons Contracting1097220220102-12Pickup w/ plow and sander3240INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10971 | 20220102-11 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 3 | HR |  |  | 70 | 0 | 210 | 27.3 | 237.3 | 2022-01-02 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Prairie | 6 | C171-C185 | Prairie River | 0 | 2022-01-10 |  | 37 | 2022-01-12 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1097120220102-11Operator - Intermdiate - After Jan 103210 | Corbiere and Sons Contracting1097120220102-11Operator - Intermdiate - After Jan 103210INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10971 | 20220102-11 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2022-01-02 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Prairie | 6 | C171-C185 | Prairie River | 0 | 2022-01-10 |  | 37 | 2022-01-12 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1097120220102-11L.O.A.1210 | Corbiere and Sons Contracting1097120220102-11L.O.A.1210INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10971 | 20220102-11 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 3 |  | 0 | 0 |  |  | 240 | 31.2 | 271.2 | 2022-01-02 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Prairie | 6 | C171-C185 | Prairie River | 0 | 2022-01-10 |  | 37 | 2022-01-12 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1097120220102-11Pickup w/ plow and sander3240 | Corbiere and Sons Contracting1097120220102-11Pickup w/ plow and sander3240INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10970 | 20220102-10 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 0 | 0 | 450 | 58.5 | 508.5 | 2022-01-02 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Del West | 6 | C186-C190 | Del Lake West | 0 | 2022-01-10 |  | 37 | 2022-01-12 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1097020220102-10Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting1097020220102-10Operator - Principle - After Jan 106450INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10970 | 20220102-10 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 6 |  | 0 | 0 |  |  | 480 | 62.4 | 542.4 | 2022-01-02 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Del West | 6 | C186-C190 | Del Lake West | 0 | 2022-01-10 |  | 37 | 2022-01-12 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1097020220102-10Pickup w/ plow and sander6480 | Corbiere and Sons Contracting1097020220102-10Pickup w/ plow and sander6480INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10959 | 20220101-9 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 3 | HR |  |  | 70 | 0 | 210 | 27.3 | 237.3 | 2022-01-01 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Del Lake | 6 | C186-C195 | Del Lake | 0 | 2022-01-02 |  | 37 | 2022-01-11 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1095920220101-9Operator - Intermdiate - After Jan 103210 | Corbiere and Sons Contracting1095920220101-9Operator - Intermdiate - After Jan 103210INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10959 | 20220101-9 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 3 | HR |  |  | 0 | 0 | 225 | 29.25 | 254.25 | 2022-01-01 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Del Lake | 6 | C186-C195 | Del Lake | 0 | 2022-01-02 |  | 37 | 2022-01-11 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1095920220101-9Operator - Principle - After Jan 103225 | Corbiere and Sons Contracting1095920220101-9Operator - Principle - After Jan 103225INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10959 | 20220101-9 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2022-01-01 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Del Lake | 6 | C186-C195 | Del Lake | 0 | 2022-01-02 |  | 37 | 2022-01-11 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1095920220101-9L.O.A.1210 | Corbiere and Sons Contracting1095920220101-9L.O.A.1210INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10959 | 20220101-9 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 3 |  | 0 | 0 |  |  | 240 | 31.2 | 271.2 | 2022-01-01 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Del Lake | 6 | C186-C195 | Del Lake | 0 | 2022-01-02 |  | 37 | 2022-01-11 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1095920220101-9Pickup w/ plow and sander3240 | Corbiere and Sons Contracting1095920220101-9Pickup w/ plow and sander3240INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10959 | 20220101-9 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 3 |  | 0 | 0 |  |  | 240 | 31.2 | 271.2 | 2022-01-01 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Del Lake | 6 | C186-C195 | Del Lake | 0 | 2022-01-02 |  | 37 | 2022-01-11 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1095920220101-9Pickup w/ plow and sander3240 | Corbiere and Sons Contracting1095920220101-9Pickup w/ plow and sander3240INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10958 | 20220101-8 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 3 | HR |  |  | 0 | 0 | 225 | 29.25 | 254.25 | 2022-01-01 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Ripple | 6 | C198-C202 | Ripple Lake | 0 | 2022-01-02 |  | 37 | 2022-01-11 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1095820220101-8Operator - Principle - After Jan 103225 | Corbiere and Sons Contracting1095820220101-8Operator - Principle - After Jan 103225INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10958 | 20220101-8 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 3 |  | 0 | 0 |  |  | 240 | 31.2 | 271.2 | 2022-01-01 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Ripple | 6 | C198-C202 | Ripple Lake | 0 | 2022-01-02 |  | 37 | 2022-01-11 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1095820220101-8Pickup w/ plow and sander3240 | Corbiere and Sons Contracting1095820220101-8Pickup w/ plow and sander3240INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10957 | 20220101-7 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 3 | HR |  |  | 0 | 0 | 225 | 29.25 | 254.25 | 2022-01-01 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Little Pic | 6 | C215-C216 | Little Pie River | 0 | 2022-01-02 |  | 37 | 2022-01-11 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1095720220101-7Operator - Principle - After Jan 103225 | Corbiere and Sons Contracting1095720220101-7Operator - Principle - After Jan 103225INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10957 | 20220101-7 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 3 |  | 0 | 0 |  |  | 240 | 31.2 | 271.2 | 2022-01-01 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Little Pic | 6 | C215-C216 | Little Pie River | 0 | 2022-01-02 |  | 37 | 2022-01-11 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1095720220101-7Pickup w/ plow and sander3240 | Corbiere and Sons Contracting1095720220101-7Pickup w/ plow and sander3240INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10955 | 20220101-5 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 3 | HR |  |  | 75 | 0 | 225 | 29.25 | 254.25 | 2022-01-01 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2022-01-02 |  | 37 | 2022-01-11 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1095520220101-5Operator - Principle - After Jan 103225 | Corbiere and Sons Contracting1095520220101-5Operator - Principle - After Jan 103225INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10955 | 20220101-5 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-01-01 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2022-01-02 |  | 37 | 2022-01-11 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1095520220101-5Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1095520220101-5Operator - Principle - After Jan 1011825INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10955 | 20220101-5 | 53510611 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2022-01-01 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2022-01-02 |  | 37 | 2022-01-11 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1095520220101-5L.O.A.2420 | Corbiere and Sons Contracting1095520220101-5L.O.A.2420INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10955 | 20220101-5 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 3 |  | 0 | 0 |  |  | 240 | 31.2 | 271.2 | 2022-01-01 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2022-01-02 |  | 37 | 2022-01-11 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1095520220101-5Pickup w/ plow and sander3240 | Corbiere and Sons Contracting1095520220101-5Pickup w/ plow and sander3240INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10955 | 20220101-5 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-01 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2022-01-02 |  | 37 | 2022-01-11 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1095520220101-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1095520220101-5Light Truck - Pick up- After Jan 101243.75INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10955 | 20220101-5 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 7 | Dynamic | 0 | 0 |  |  | 888.86 | 115.5518 | 1004.4118 | 2022-01-01 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Neys Road | 6 | C219-C236 | Neys | 0 | 2022-01-02 |  | 37 | 2022-01-11 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1095520220101-5Grader - Cat 12 to 14 or equal- After Jan 107888.86 | Corbiere and Sons Contracting1095520220101-5Grader - Cat 12 to 14 or equal- After Jan 107888.86INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10962 | 20220101-12 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 2 | HR |  |  | 0 | 0 | 140 | 18.2 | 158.2 | 2022-01-01 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Jackfish | 6 | C152-C157 | Jackfish Lake | 0 | 2022-01-02 |  | 37 | 2022-01-11 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1096220220101-12Operator - Intermdiate - After Jan 102140 | Corbiere and Sons Contracting1096220220101-12Operator - Intermdiate - After Jan 102140INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10962 | 20220101-12 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 2 |  | 0 | 0 |  |  | 160 | 20.8 | 180.8 | 2022-01-01 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Jackfish | 6 | C152-C157 | Jackfish Lake | 0 | 2022-01-02 |  | 37 | 2022-01-11 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1096220220101-12Pickup w/ plow and sander2160 | Corbiere and Sons Contracting1096220220101-12Pickup w/ plow and sander2160INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10961 | 20220101-11 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 3 | HR |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-01-01 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Santoy Lake | 6 | C158-C170 | Santoy Lake | 0 | 2022-01-02 |  | 37 | 2022-01-11 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1096120220101-11Operator - Intermdiate - After Jan 103210 | Corbiere and Sons Contracting1096120220101-11Operator - Intermdiate - After Jan 103210INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10961 | 20220101-11 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 3 |  | 0 | 0 |  |  | 240 | 31.2 | 271.2 | 2022-01-01 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Santoy Lake | 6 | C158-C170 | Santoy Lake | 0 | 2022-01-02 |  | 37 | 2022-01-11 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1096120220101-11Pickup w/ plow and sander3240 | Corbiere and Sons Contracting1096120220101-11Pickup w/ plow and sander3240INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10960 | 20220101-10 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 3 | HR |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-01-01 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Lake A | 6 | C130-C151 | Lake A | 0 | 2022-01-02 |  | 37 | 2022-01-11 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1096020220101-10Operator - Intermdiate - After Jan 103210 | Corbiere and Sons Contracting1096020220101-10Operator - Intermdiate - After Jan 103210INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10960 | 20220101-10 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 3 |  | 0 | 0 |  |  | 240 | 31.2 | 271.2 | 2022-01-01 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Lake A | 6 | C130-C151 | Lake A | 0 | 2022-01-02 |  | 37 | 2022-01-11 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1096020220101-10Pickup w/ plow and sander3240 | Corbiere and Sons Contracting1096020220101-10Pickup w/ plow and sander3240INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10950 | 20211231-9 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 1 | HR |  |  | 0 | 0 | 75 | 9.75 | 84.75 | 2021-12-31 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on C214 | 6 | C214 | Highway 17 | 0 |  |  | 37 | 2022-01-11 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1095020211231-9Operator - Principle - After Jan 10175 | Corbiere and Sons Contracting1095020211231-9Operator - Principle - After Jan 10175INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10950 | 20211231-9 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 1 |  | 0 | 0 |  |  | 80 | 10.4 | 90.4 | 2021-12-31 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on C214 | 6 | C214 | Highway 17 | 0 |  |  | 37 | 2022-01-11 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1095020211231-9Pickup w/ plow and sander180 | Corbiere and Sons Contracting1095020211231-9Pickup w/ plow and sander180INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10949 | 20211231-8 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 3 | HR |  |  | 0 | 0 | 225 | 29.25 | 254.25 | 2021-12-31 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities onon Middleton | 6 | C210-C213 | Middleton | 0 |  |  | 37 | 2022-01-11 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1094920211231-8Operator - Principle - After Jan 103225 | Corbiere and Sons Contracting1094920211231-8Operator - Principle - After Jan 103225INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10949 | 20211231-8 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 3 |  | 0 | 0 |  |  | 240 | 31.2 | 271.2 | 2021-12-31 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities onon Middleton | 6 | C210-C213 | Middleton | 0 |  |  | 37 | 2022-01-11 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1094920211231-8Pickup w/ plow and sander3240 | Corbiere and Sons Contracting1094920211231-8Pickup w/ plow and sander3240INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10948 | 20211231-7 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 3 | HR |  |  | 0 | 0 | 225 | 29.25 | 254.25 | 2021-12-31 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities onon Mink Creek | 6 | C237-C247 | Mink Creek | 0 |  |  | 37 | 2022-01-11 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1094820211231-7Operator - Principle - After Jan 103225 | Corbiere and Sons Contracting1094820211231-7Operator - Principle - After Jan 103225INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10948 | 20211231-7 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-12-31 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities onon Mink Creek | 6 | C237-C247 | Mink Creek | 0 |  |  | 37 | 2022-01-11 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1094820211231-7L.O.A.1210 | Corbiere and Sons Contracting1094820211231-7L.O.A.1210INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10948 | 20211231-7 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 3 |  | 0 | 0 |  |  | 240 | 31.2 | 271.2 | 2021-12-31 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities onon Mink Creek | 6 | C237-C247 | Mink Creek | 0 |  |  | 37 | 2022-01-11 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1094820211231-7Pickup w/ plow and sander3240 | Corbiere and Sons Contracting1094820211231-7Pickup w/ plow and sander3240INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10947 | 20211231-6 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2021-12-31 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Neys Road | 6 | C219-C236 | Neys | 0 |  |  | 37 | 2022-01-11 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1094720211231-6Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1094720211231-6Operator - Principle - After Jan 1011825INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10947 | 20211231-6 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-12-31 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Neys Road | 6 | C219-C236 | Neys | 0 |  |  | 37 | 2022-01-11 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1094720211231-6L.O.A.1210 | Corbiere and Sons Contracting1094720211231-6L.O.A.1210INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10947 | 20211231-6 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-12-31 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Neys Road | 6 | C219-C236 | Neys | 0 |  |  | 37 | 2022-01-11 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1094720211231-6Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1094720211231-6Light Truck - Pick up- After Jan 101243.75INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10947 | 20211231-6 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 95.24 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2021-12-31 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Neys Road | 6 | C219-C236 | Neys | 0 |  |  | 37 | 2022-01-11 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1094720211231-6Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1094720211231-6Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10952 | 20211231-11 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 4 | HR |  |  | 0 | 0 | 300 | 39 | 339 | 2021-12-31 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Hare Lake Road | 6 | C257-C267 | Hare Lake Creek | 0 |  |  | 37 | 2022-01-11 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1095220211231-11Operator - Principle - After Jan 104300 | Corbiere and Sons Contracting1095220211231-11Operator - Principle - After Jan 104300INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10952 | 20211231-11 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 4 |  | 0 | 0 |  |  | 320 | 41.6 | 361.6 | 2021-12-31 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Hare Lake Road | 6 | C257-C267 | Hare Lake Creek | 0 |  |  | 37 | 2022-01-11 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1095220211231-11Pickup w/ plow and sander4320 | Corbiere and Sons Contracting1095220211231-11Pickup w/ plow and sander4320INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10951 | 20211231-10 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 1 | HR |  |  | 0 | 0 | 75 | 9.75 | 84.75 | 2021-12-31 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on C217 | 6 | C217 | Highway 17 | 0 |  |  | 37 | 2022-01-11 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1095120211231-10Operator - Principle - After Jan 10175 | Corbiere and Sons Contracting1095120211231-10Operator - Principle - After Jan 10175INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10951 | 20211231-10 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 1 |  | 0 | 0 |  |  | 80 | 10.4 | 90.4 | 2021-12-31 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on C217 | 6 | C217 | Highway 17 | 0 |  |  | 37 | 2022-01-11 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1095120211231-10Pickup w/ plow and sander180 | Corbiere and Sons Contracting1095120211231-10Pickup w/ plow and sander180INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10943 | 20211230-8 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 2 | HR |  |  | 0 | 0 | 150 | 19.5 | 169.5 | 2021-12-30 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Middleton | 6 | C210-C213 | Middleton | 0 |  |  | 37 | 2022-01-11 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1094320211230-8Operator - Principle - After Jan 102150 | Corbiere and Sons Contracting1094320211230-8Operator - Principle - After Jan 102150INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10943 | 20211230-8 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 2 |  | 0 | 0 |  |  | 160 | 20.8 | 180.8 | 2021-12-30 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Middleton | 6 | C210-C213 | Middleton | 0 |  |  | 37 | 2022-01-11 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1094320211230-8Pickup w/ plow and sander2160 | Corbiere and Sons Contracting1094320211230-8Pickup w/ plow and sander2160INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10942 | 20211230-7 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 2 | HR |  |  | 0 | 0 | 150 | 19.5 | 169.5 | 2021-12-30 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Deadhorse | 6 | C203-C209 | Dead Horse Creek | 0 |  |  | 37 | 2022-01-11 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1094220211230-7Operator - Principle - After Jan 102150 | Corbiere and Sons Contracting1094220211230-7Operator - Principle - After Jan 102150INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10942 | 20211230-7 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 2 |  | 0 | 0 |  |  | 160 | 20.8 | 180.8 | 2021-12-30 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Deadhorse | 6 | C203-C209 | Dead Horse Creek | 0 |  |  | 37 | 2022-01-11 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1094220211230-7Pickup w/ plow and sander2160 | Corbiere and Sons Contracting1094220211230-7Pickup w/ plow and sander2160INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10941 | 20211230-6 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 4 | HR |  |  | 75 | 0 | 300 | 39 | 339 | 2021-12-30 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Neys Road | 6 | C219-C236 | Neys | 0 |  |  | 37 | 2022-01-11 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1094120211230-6Operator - Principle - After Jan 104300 | Corbiere and Sons Contracting1094120211230-6Operator - Principle - After Jan 104300INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10941 | 20211230-6 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 4 |  | 0 | 0 |  |  | 320 | 41.6 | 361.6 | 2021-12-30 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Neys Road | 6 | C219-C236 | Neys | 0 |  |  | 37 | 2022-01-11 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1094120211230-6Pickup w/ plow and sander4320 | Corbiere and Sons Contracting1094120211230-6Pickup w/ plow and sander4320INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10936 | 20211229-6 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 3 | HR |  |  | 75 | 0 | 225 | 29.25 | 254.25 | 2021-12-29 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C248-C256 | Little Red Sucker Creek | 0 |  |  | 37 | 2022-01-11 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1093620211229-6Operator - Principle - After Jan 103225 | Corbiere and Sons Contracting1093620211229-6Operator - Principle - After Jan 103225INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10936 | 20211229-6 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 0 | 0 | 450 | 58.5 | 508.5 | 2021-12-29 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C248-C256 | Little Red Sucker Creek | 0 |  |  | 37 | 2022-01-11 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1093620211229-6Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting1093620211229-6Operator - Principle - After Jan 106450INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10936 | 20211229-6 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 4 |  | 0 | 0 |  |  | 320 | 41.6 | 361.6 | 2021-12-29 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C248-C256 | Little Red Sucker Creek | 0 |  |  | 37 | 2022-01-11 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1093620211229-6Pickup w/ plow and sander4320 | Corbiere and Sons Contracting1093620211229-6Pickup w/ plow and sander4320INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10936 | 20211229-6 | 53510611 | Access | 0 | Dozer D8 or equal- After Jan 10 | 217.5 | 3 | Dynamic | 163.13 | 0 |  |  | 652.5 | 84.825 | 737.325 | 2021-12-29 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C248-C256 | Little Red Sucker Creek | 0 |  |  | 37 | 2022-01-11 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1093620211229-6Dozer D8 or equal- After Jan 103652.5 | Corbiere and Sons Contracting1093620211229-6Dozer D8 or equal- After Jan 103652.5INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10932 | 20211228-6 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 4 | HR |  |  | 75 | 0 | 300 | 39 | 339 | 2021-12-28 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Neys Road | 6 | C219-C235 | Neys | 0 |  |  | 37 | 2022-01-11 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1093220211228-6Operator - Principle - After Jan 104300 | Corbiere and Sons Contracting1093220211228-6Operator - Principle - After Jan 104300INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10932 | 20211228-6 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 4 |  | 0 | 0 |  |  | 320 | 41.6 | 361.6 | 2021-12-28 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Neys Road | 6 | C219-C235 | Neys | 0 |  |  | 37 | 2022-01-11 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1093220211228-6Pickup w/ plow and sander4320 | Corbiere and Sons Contracting1093220211228-6Pickup w/ plow and sander4320INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10931 | 20211228-5 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 4 | HR |  |  | 75 | 0 | 300 | 39 | 339 | 2021-12-28 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C248-C256 | Little Red Sucker Creek | 0 |  |  | 37 | 2022-01-11 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1093120211228-5Operator - Principle - After Jan 104300 | Corbiere and Sons Contracting1093120211228-5Operator - Principle - After Jan 104300INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10931 | 20211228-5 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 4 |  | 0 | 0 |  |  | 320 | 41.6 | 361.6 | 2021-12-28 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C248-C256 | Little Red Sucker Creek | 0 |  |  | 37 | 2022-01-11 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1093120211228-5Pickup w/ plow and sander4320 | Corbiere and Sons Contracting1093120211228-5Pickup w/ plow and sander4320INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10927 | 20211219-6 | 53510611 | Access | 0 | Labourer - General - After Jan 10 | 60 | 11 | HR |  |  | 60 | 0 | 660 | 85.8 | 745.8 | 2021-12-19 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Doug and Cole continuing to demob pickups/supplies and cleaning up/closing the marathon laydown for holiday break | 6 | C130-C151 | Lake A | 0 |  |  | 36 | 2022-01-10 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1092720211219-6Labourer - General - After Jan 1011660 | Corbiere and Sons Contracting1092720211219-6Labourer - General - After Jan 1011660INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10927 | 20211219-6 | 53510611 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-12-19 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Doug and Cole continuing to demob pickups/supplies and cleaning up/closing the marathon laydown for holiday break | 6 | C130-C151 | Lake A | 0 |  |  | 36 | 2022-01-10 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1092720211219-6L.O.A.2420 | Corbiere and Sons Contracting1092720211219-6L.O.A.2420INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10927 | 20211219-6 | 53510611 | Access | 0 | Foreman | 95 | 6 | HR |  |  | 95 | 0 | 570 | 74.1 | 644.1 | 2021-12-19 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Doug and Cole continuing to demob pickups/supplies and cleaning up/closing the marathon laydown for holiday break | 6 | C130-C151 | Lake A | 0 |  |  | 36 | 2022-01-10 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1092720211219-6Foreman6570 | Corbiere and Sons Contracting1092720211219-6Foreman6570INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10927 | 20211219-6 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-12-19 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Doug and Cole continuing to demob pickups/supplies and cleaning up/closing the marathon laydown for holiday break | 6 | C130-C151 | Lake A | 0 |  |  | 36 | 2022-01-10 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1092720211219-6Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1092720211219-6Light Truck - Pick up- After Jan 101243.75INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10926 | 20211219-5 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2021-12-19 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Scratching hills in Red Sucker with 336ex | 6 | C248-C256 | Little Red Sucker Creek | 0 |  |  | 36 | 2022-01-10 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1092620211219-5Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1092620211219-5Operator - Principle - After Jan 1011825INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10926 | 20211219-5 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-12-19 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Scratching hills in Red Sucker with 336ex | 6 | C248-C256 | Little Red Sucker Creek | 0 |  |  | 36 | 2022-01-10 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1092620211219-5L.O.A.1210 | Corbiere and Sons Contracting1092620211219-5L.O.A.1210INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10926 | 20211219-5 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-12-19 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Scratching hills in Red Sucker with 336ex | 6 | C248-C256 | Little Red Sucker Creek | 0 |  |  | 36 | 2022-01-10 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1092620211219-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1092620211219-5Light Truck - Pick up- After Jan 101243.75INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10926 | 20211219-5 | 53510611 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 0 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2021-12-19 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Scratching hills in Red Sucker with 336ex | 6 | C248-C256 | Little Red Sucker Creek | 0 |  |  | 36 | 2022-01-10 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1092620211219-5Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting1092620211219-5Excavator Thumb - 30 - 50 ton- After Jan 1010122.1INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10926 | 20211219-5 | 53510611 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10 | Dynamic | 0 | 0 |  |  | 1469.6 | 191.048 | 1660.648 | 2021-12-19 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Scratching hills in Red Sucker with 336ex | 6 | C248-C256 | Little Red Sucker Creek | 0 |  |  | 36 | 2022-01-10 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1092620211219-5Excavator - 36 ton- After Jan 10101469.6 | Corbiere and Sons Contracting1092620211219-5Excavator - 36 ton- After Jan 10101469.6INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10923 | 20211218-7 | 53510611 | Access | 0 | Labourer - General - After Jan 10 | 60 | 6 | HR |  |  | 60 | 0 | 360 | 46.8 | 406.8 | 2021-12-18 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Demob of 350X4 from Lake A back to Manitoulin Island; Demob of other equipment and supplies done Doug | 6 | C130-C151 | Lake A | 0 |  |  | 36 | 2022-01-10 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1092320211218-7Labourer - General - After Jan 106360 | Corbiere and Sons Contracting1092320211218-7Labourer - General - After Jan 106360INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10923 | 20211218-7 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 22 | HR |  |  | 70 | 0 | 1540 | 200.2 | 1740.2 | 2021-12-18 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Demob of 350X4 from Lake A back to Manitoulin Island; Demob of other equipment and supplies done Doug | 6 | C130-C151 | Lake A | 0 |  |  | 36 | 2022-01-10 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1092320211218-7Driver - AZ - After Jan 10221540 | Corbiere and Sons Contracting1092320211218-7Driver - AZ - After Jan 10221540INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10923 | 20211218-7 | 53510611 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-12-18 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Demob of 350X4 from Lake A back to Manitoulin Island; Demob of other equipment and supplies done Doug | 6 | C130-C151 | Lake A | 0 |  |  | 36 | 2022-01-10 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1092320211218-7L.O.A.2420 | Corbiere and Sons Contracting1092320211218-7L.O.A.2420INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10923 | 20211218-7 | 53510611 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 22 | Dynamic | 91.79 | 0 |  |  | 2692.58 | 350.0354 | 3042.6154 | 2021-12-18 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Demob of 350X4 from Lake A back to Manitoulin Island; Demob of other equipment and supplies done Doug | 6 | C130-C151 | Lake A | 0 |  |  | 36 | 2022-01-10 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1092320211218-7Tractor Trailer - 60 Ton- After Jan 10222692.58 | Corbiere and Sons Contracting1092320211218-7Tractor Trailer - 60 Ton- After Jan 10222692.58INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10923 | 20211218-7 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-12-18 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Demob of 350X4 from Lake A back to Manitoulin Island; Demob of other equipment and supplies done Doug | 6 | C130-C151 | Lake A | 0 |  |  | 36 | 2022-01-10 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1092320211218-7Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1092320211218-7Light Truck - Pick up- After Jan 101243.75INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10922 | 20211218-6 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5.5 | HR |  |  | 75 | 0 | 412.5 | 53.625 | 466.125 | 2021-12-18 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Scratching hills in Red Sucker with 336ex | 6 | C248-C256 | Little Red Sucker Creek | 0 |  |  | 36 | 2022-01-10 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1092220211218-6Operator - Principle - After Jan 105.5412.5 | Corbiere and Sons Contracting1092220211218-6Operator - Principle - After Jan 105.5412.5INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10922 | 20211218-6 | 53510611 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 5 | HR | 9.16 | 0 |  |  | 61.05 | 7.9365 | 68.9865 | 2021-12-18 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Scratching hills in Red Sucker with 336ex | 6 | C248-C256 | Little Red Sucker Creek | 0 |  |  | 36 | 2022-01-10 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1092220211218-6Excavator Thumb - 30 - 50 ton- After Jan 10561.05 | Corbiere and Sons Contracting1092220211218-6Excavator Thumb - 30 - 50 ton- After Jan 10561.05INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10922 | 20211218-6 | 53510611 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 5 | Dynamic | 110.22 | 0 |  |  | 734.8 | 95.524 | 830.324 | 2021-12-18 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Scratching hills in Red Sucker with 336ex | 6 | C248-C256 | Little Red Sucker Creek | 0 |  |  | 36 | 2022-01-10 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1092220211218-6Excavator - 36 ton- After Jan 105734.8 | Corbiere and Sons Contracting1092220211218-6Excavator - 36 ton- After Jan 105734.8INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10921 | 20211218-5 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5.5 | HR |  |  | 0 | 0 | 412.5 | 53.625 | 466.125 | 2021-12-18 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Repairing washed out road in Neys | 6 | C219-C239 | Neys | 0 |  |  | 36 | 2022-01-10 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1092120211218-5Operator - Principle - After Jan 105.5412.5 | Corbiere and Sons Contracting1092120211218-5Operator - Principle - After Jan 105.5412.5INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10921 | 20211218-5 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2021-12-18 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Repairing washed out road in Neys | 6 | C219-C239 | Neys | 0 |  |  | 36 | 2022-01-10 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1092120211218-5L.O.A.1210 | Corbiere and Sons Contracting1092120211218-5L.O.A.1210INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10921 | 20211218-5 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-12-18 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Repairing washed out road in Neys | 6 | C219-C239 | Neys | 0 |  |  | 36 | 2022-01-10 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1092120211218-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1092120211218-5Light Truck - Pick up- After Jan 101243.75INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10921 | 20211218-5 | 53510611 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 5 | HR | 0 | 0 |  |  | 61.05 | 7.9365 | 68.9865 | 2021-12-18 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Repairing washed out road in Neys | 6 | C219-C239 | Neys | 0 |  |  | 36 | 2022-01-10 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1092120211218-5Excavator Thumb - 30 - 50 ton- After Jan 10561.05 | Corbiere and Sons Contracting1092120211218-5Excavator Thumb - 30 - 50 ton- After Jan 10561.05INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10921 | 20211218-5 | 53510611 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 5 | Dynamic | 0 | 0 |  |  | 734.8 | 95.524 | 830.324 | 2021-12-18 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Repairing washed out road in Neys | 6 | C219-C239 | Neys | 0 |  |  | 36 | 2022-01-10 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1092120211218-5Excavator - 36 ton- After Jan 105734.8 | Corbiere and Sons Contracting1092120211218-5Excavator - 36 ton- After Jan 105734.8INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10917 | 20211217-5 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-12-17 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Repairing washed out road in Neys | 6 | C219-C235 | Neys | 0 |  |  | 37 | 2022-01-11 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1091720211217-5Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1091720211217-5Operator - Principle - After Jan 1011825INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10917 | 20211217-5 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-12-17 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Repairing washed out road in Neys | 6 | C219-C235 | Neys | 0 |  |  | 37 | 2022-01-11 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1091720211217-5L.O.A.1210 | Corbiere and Sons Contracting1091720211217-5L.O.A.1210INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10917 | 20211217-5 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-12-17 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Repairing washed out road in Neys | 6 | C219-C235 | Neys | 0 |  |  | 37 | 2022-01-11 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1091720211217-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1091720211217-5Light Truck - Pick up- After Jan 101243.75INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10917 | 20211217-5 | 53510611 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 8 | HR | 9.16 | 0 |  |  | 97.68 | 12.6984 | 110.3784 | 2021-12-17 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Repairing washed out road in Neys | 6 | C219-C235 | Neys | 0 |  |  | 37 | 2022-01-11 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1091720211217-5Excavator Thumb - 30 - 50 ton- After Jan 10897.68 | Corbiere and Sons Contracting1091720211217-5Excavator Thumb - 30 - 50 ton- After Jan 10897.68INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10917 | 20211217-5 | 53510611 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 8 | Dynamic | 110.22 | 0 |  |  | 1175.68 | 152.8384 | 1328.5184 | 2021-12-17 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Repairing washed out road in Neys | 6 | C219-C235 | Neys | 0 |  |  | 37 | 2022-01-11 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1091720211217-5Excavator - 36 ton- After Jan 1081175.68 | Corbiere and Sons Contracting1091720211217-5Excavator - 36 ton- After Jan 1081175.68INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10911 | 20211216-6 | 53510511 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 3 | HR |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2021-12-16 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 |  |  | 36 | 2022-01-12 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1091120211216-6Operator - Intermdiate - After Jan 103210 | Corbiere and Sons Contracting1091120211216-6Operator - Intermdiate - After Jan 103210INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10911 | 20211216-6 | 53510511 | Access | 0 | Pickup w/ plow and sander | 80 | 3 |  | 0 | 0 |  |  | 240 | 31.2 | 271.2 | 2021-12-16 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 |  |  | 36 | 2022-01-12 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1091120211216-6Pickup w/ plow and sander3240 | Corbiere and Sons Contracting1091120211216-6Pickup w/ plow and sander3240INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10904 | 20211215-6 | 53510511 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 3 | HR |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2021-12-15 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Lake A | 6 | C130-C151 | Lake A | 0 |  |  | 36 | 2022-01-12 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1090420211215-6Operator - Intermdiate - After Jan 103210 | Corbiere and Sons Contracting1090420211215-6Operator - Intermdiate - After Jan 103210INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10904 | 20211215-6 | 53510511 | Access | 0 | Pickup w/ plow and sander | 80 | 3 |  | 0 | 0 |  |  | 240 | 31.2 | 271.2 | 2021-12-15 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Lake A | 6 | C130-C151 | Lake A | 0 |  |  | 36 | 2022-01-12 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting1090420211215-6Pickup w/ plow and sander3240 | Corbiere and Sons Contracting1090420211215-6Pickup w/ plow and sander3240INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10886 | 20211212-14 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 2 | HR |  |  | 0 | 0 | 140 | 18.2 | 158.2 | 2021-12-12 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Lake A | 6 | C130-C151 | Lake A | 0 | 2021-12-31 |  | 36 | 2022-01-06 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1088620211212-14Operator - Intermdiate - After Jan 102140 | Corbiere and Sons Contracting1088620211212-14Operator - Intermdiate - After Jan 102140INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10886 | 20211212-14 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 2 |  | 0 | 0 |  |  | 160 | 20.8 | 180.8 | 2021-12-12 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Lake A | 6 | C130-C151 | Lake A | 0 | 2021-12-31 |  | 36 | 2022-01-06 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1088620211212-14Pickup w/ plow and sander2160 | Corbiere and Sons Contracting1088620211212-14Pickup w/ plow and sander2160INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10885 | 20211212-13 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 2 | HR |  |  | 0 | 0 | 140 | 18.2 | 158.2 | 2021-12-12 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Neys | 6 | C152 - C157 | Jackfish Lake | 0 | 2021-12-31 |  | 36 | 2022-01-06 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1088520211212-13Operator - Intermdiate - After Jan 102140 | Corbiere and Sons Contracting1088520211212-13Operator - Intermdiate - After Jan 102140INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10885 | 20211212-13 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 2 |  | 0 | 0 |  |  | 160 | 20.8 | 180.8 | 2021-12-12 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Neys | 6 | C152 - C157 | Jackfish Lake | 0 | 2021-12-31 |  | 36 | 2022-01-06 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1088520211212-13Pickup w/ plow and sander2160 | Corbiere and Sons Contracting1088520211212-13Pickup w/ plow and sander2160INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10884 | 20211212-12 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 3 | HR |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2021-12-12 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Neys | 6 | C186 - C195 | Del Lake West | 0 | 2021-12-31 |  | 36 | 2022-01-06 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1088420211212-12Operator - Intermdiate - After Jan 103210 | Corbiere and Sons Contracting1088420211212-12Operator - Intermdiate - After Jan 103210INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10884 | 20211212-12 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 3 |  | 0 | 0 |  |  | 240 | 31.2 | 271.2 | 2021-12-12 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Neys | 6 | C186 - C195 | Del Lake West | 0 | 2021-12-31 |  | 36 | 2022-01-06 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1088420211212-12Pickup w/ plow and sander3240 | Corbiere and Sons Contracting1088420211212-12Pickup w/ plow and sander3240INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10883 | 20211212-11 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 4 | HR |  |  | 70 | 0 | 280 | 36.4 | 316.4 | 2021-12-12 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Neys | 6 | C219-C235 | Neys | 0 | 2021-12-31 |  | 36 | 2022-01-06 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1088320211212-11Operator - Intermdiate - After Jan 104280 | Corbiere and Sons Contracting1088320211212-11Operator - Intermdiate - After Jan 104280INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10883 | 20211212-11 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-12-12 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Neys | 6 | C219-C235 | Neys | 0 | 2021-12-31 |  | 36 | 2022-01-06 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1088320211212-11L.O.A.1210 | Corbiere and Sons Contracting1088320211212-11L.O.A.1210INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10883 | 20211212-11 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 4 |  | 0 | 0 |  |  | 320 | 41.6 | 361.6 | 2021-12-12 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Neys | 6 | C219-C235 | Neys | 0 | 2021-12-31 |  | 36 | 2022-01-06 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1088320211212-11Pickup w/ plow and sander4320 | Corbiere and Sons Contracting1088320211212-11Pickup w/ plow and sander4320INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10772 | 20211211-9 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 3.5 | HR |  |  | 75 | 0 | 262.5 | 34.125 | 296.625 | 2021-12-11 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Plowing snow towards WC603 | 6 | C171-C185 | Prairie River | 0 | 2021-12-12 |  | 36 | 2021-12-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1077220211211-9Operator - Principle - After Jan 103.5262.5 | Corbiere and Sons Contracting1077220211211-9Operator - Principle - After Jan 103.5262.5INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10772 | 20211211-9 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 3.5 | Dynamic | 98.61 | 0 |  |  | 460.18 | 59.8234 | 520.0034 | 2021-12-11 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Plowing snow towards WC603 | 6 | C171-C185 | Prairie River | 0 | 2021-12-12 |  | 36 | 2021-12-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1077220211211-9Dozer D6 or equal- After Jan 103.5460.18 | Corbiere and Sons Contracting1077220211211-9Dozer D6 or equal- After Jan 103.5460.18INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10778 | 20211211-15 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 3 | HR |  |  | 70 | 0 | 210 | 27.3 | 237.3 | 2021-12-11 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Santoy Lake | 6 | C158-C170 | Santoy Lake | 0 | 2021-12-12 |  | 36 | 2021-12-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1077820211211-15Operator - Intermdiate - After Jan 103210 | Corbiere and Sons Contracting1077820211211-15Operator - Intermdiate - After Jan 103210INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10778 | 20211211-15 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 3 |  | 0 | 0 |  |  | 240 | 31.2 | 271.2 | 2021-12-11 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Santoy Lake | 6 | C158-C170 | Santoy Lake | 0 | 2021-12-12 |  | 36 | 2021-12-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1077820211211-15Pickup w/ plow and sander3240 | Corbiere and Sons Contracting1077820211211-15Pickup w/ plow and sander3240INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10777 | 20211211-14 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 4 | HR |  |  | 70 | 0 | 280 | 36.4 | 316.4 | 2021-12-11 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Del Lake | 6 | C186-C190 | Del Lake West | 0 | 2021-12-12 |  | 36 | 2021-12-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1077720211211-14Operator - Intermdiate - After Jan 104280 | Corbiere and Sons Contracting1077720211211-14Operator - Intermdiate - After Jan 104280INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10777 | 20211211-14 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 4 |  | 0 | 0 |  |  | 320 | 41.6 | 361.6 | 2021-12-11 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Del Lake | 6 | C186-C190 | Del Lake West | 0 | 2021-12-12 |  | 36 | 2021-12-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1077720211211-14Pickup w/ plow and sander4320 | Corbiere and Sons Contracting1077720211211-14Pickup w/ plow and sander4320INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10776 | 20211211-13 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 4 | HR |  |  | 70 | 0 | 280 | 36.4 | 316.4 | 2021-12-11 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Neys | 6 | C219-C235 | Neys | 0 | 2021-12-12 |  | 36 | 2021-12-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1077620211211-13Operator - Intermdiate - After Jan 104280 | Corbiere and Sons Contracting1077620211211-13Operator - Intermdiate - After Jan 104280INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10776 | 20211211-13 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-12-11 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Neys | 6 | C219-C235 | Neys | 0 | 2021-12-12 |  | 36 | 2021-12-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1077620211211-13L.O.A.1210 | Corbiere and Sons Contracting1077620211211-13L.O.A.1210INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10776 | 20211211-13 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 4 |  | 0 | 0 |  |  | 320 | 41.6 | 361.6 | 2021-12-11 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Neys | 6 | C219-C235 | Neys | 0 | 2021-12-12 |  | 36 | 2021-12-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1077620211211-13Pickup w/ plow and sander4320 | Corbiere and Sons Contracting1077620211211-13Pickup w/ plow and sander4320INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10644 | 20211201-6-R1 | 53510611 | Access | 0 | 3rd Party Charges | 1 | 1914 | Unit |  |  |  |  | 1914 | 248.82 | 2162.82 | 2021-12-01 | 0 | INV #162 | 2022-01-17 | 175 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  | Mike disputed and had hours reduced |  | Approved |  |  | Float went to North Shore pit to get mats, turned around after it was cancelled and went back to Dorion to mobilize fuel Buggy | 6 | C130-C277 | WF6 | 0 | 2021-12-08 |  | 36 | 2022-01-06 | 347 |  |  |  |  | Mike Lecocq | 06 | Corbiere and Sons Contracting1064420211201-6-R13rd Party Charges19141914 | Corbiere and Sons Contracting1064420211201-6-R13rd Party Charges19141914INV #162 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11527 | 20220213-8 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 11 | HR |  |  | 70 | 0 | 770 | 100.1 | 870.1 | 2022-02-13 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-02-13 |  | 36 | 2022-02-19 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1152720220213-8Operator - Intermdiate - After Jan 1011770 | Corbiere and Sons Contracting1152720220213-8Operator - Intermdiate - After Jan 1011770INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11527 | 20220213-8 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 4 | HR |  |  | 0 | 0 | 300 | 39 | 339 | 2022-02-13 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-02-13 |  | 36 | 2022-02-19 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1152720220213-8Operator - Principle - After Jan 104300 | Corbiere and Sons Contracting1152720220213-8Operator - Principle - After Jan 104300INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11527 | 20220213-8 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2022-02-13 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-02-13 |  | 36 | 2022-02-19 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1152720220213-8L.O.A.1210 | Corbiere and Sons Contracting1152720220213-8L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11527 | 20220213-8 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 11 |  | 0 | 0 |  |  | 880 | 114.4 | 994.4 | 2022-02-13 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-02-13 |  | 36 | 2022-02-19 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1152720220213-8Pickup w/ plow and sander11880 | Corbiere and Sons Contracting1152720220213-8Pickup w/ plow and sander11880INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11527 | 20220213-8 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 2 | Dynamic | 95.24 | 0 |  |  | 253.96 | 33.0148 | 286.9748 | 2022-02-13 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-02-13 |  | 36 | 2022-02-19 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1152720220213-8Grader - Cat 12 to 14 or equal- After Jan 102253.96 | Corbiere and Sons Contracting1152720220213-8Grader - Cat 12 to 14 or equal- After Jan 102253.96INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11524 | 20220213-5 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 7 | HR |  |  | 0 | 0 | 525 | 68.25 | 593.25 | 2022-02-13 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Neys | 6 | C219-C235 | Neys | 0 | 2022-02-13 |  | 36 | 2022-02-19 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1152420220213-5Operator - Principle - After Jan 107525 | Corbiere and Sons Contracting1152420220213-5Operator - Principle - After Jan 107525INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11524 | 20220213-5 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-13 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Neys | 6 | C219-C235 | Neys | 0 | 2022-02-13 |  | 36 | 2022-02-19 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1152420220213-5L.O.A.1210 | Corbiere and Sons Contracting1152420220213-5L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11524 | 20220213-5 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-13 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Neys | 6 | C219-C235 | Neys | 0 | 2022-02-13 |  | 36 | 2022-02-19 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1152420220213-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1152420220213-5Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11524 | 20220213-5 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 7 | Dynamic | 0 | 0 |  |  | 888.86 | 115.5518 | 1004.4118 | 2022-02-13 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Neys | 6 | C219-C235 | Neys | 0 | 2022-02-13 |  | 36 | 2022-02-19 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1152420220213-5Grader - Cat 12 to 14 or equal- After Jan 107888.86 | Corbiere and Sons Contracting1152420220213-5Grader - Cat 12 to 14 or equal- After Jan 107888.86INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11523 | 20220213-4 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-02-13 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Prairie | 6 | C171-C185 | Prairie River | 0 | 2022-02-13 |  | 36 | 2022-02-19 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1152320220213-4Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1152320220213-4Operator - Principle - After Jan 1011825INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11523 | 20220213-4 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-13 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Prairie | 6 | C171-C185 | Prairie River | 0 | 2022-02-13 |  | 36 | 2022-02-19 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1152320220213-4L.O.A.1210 | Corbiere and Sons Contracting1152320220213-4L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11523 | 20220213-4 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-13 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Prairie | 6 | C171-C185 | Prairie River | 0 | 2022-02-13 |  | 36 | 2022-02-19 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1152320220213-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1152320220213-4Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11523 | 20220213-4 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-02-13 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Prairie | 6 | C171-C185 | Prairie River | 0 | 2022-02-13 |  | 36 | 2022-02-19 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1152320220213-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1152320220213-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11522 | 20220213-3 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-02-13 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Little Red Sucker Creek | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2022-02-13 |  | 36 | 2022-02-19 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1152220220213-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1152220220213-3Operator - Principle - After Jan 1011825INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11522 | 20220213-3 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-13 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Little Red Sucker Creek | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2022-02-13 |  | 36 | 2022-02-19 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1152220220213-3L.O.A.1210 | Corbiere and Sons Contracting1152220220213-3L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11522 | 20220213-3 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-13 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Little Red Sucker Creek | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2022-02-13 |  | 36 | 2022-02-19 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1152220220213-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1152220220213-3Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11522 | 20220213-3 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-02-13 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Little Red Sucker Creek | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2022-02-13 |  | 36 | 2022-02-19 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1152220220213-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1152220220213-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11519 | 20220212-6 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 0 | 0 | 900 | 117 | 1017 | 2022-02-12 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-02-13 |  | 36 | 2022-02-19 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1151920220212-6Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1151920220212-6Operator - Principle - After Jan 1012900INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11519 | 20220212-6 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-12 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-02-13 |  | 36 | 2022-02-19 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1151920220212-6L.O.A.1210 | Corbiere and Sons Contracting1151920220212-6L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11519 | 20220212-6 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 12 |  | 0 | 0 |  |  | 960 | 124.8 | 1084.8 | 2022-02-12 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-02-13 |  | 36 | 2022-02-19 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1151920220212-6Pickup w/ plow and sander12960 | Corbiere and Sons Contracting1151920220212-6Pickup w/ plow and sander12960INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11518 | 20220212-5 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-02-12 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Neys | 6 | C219-C236 | Neys | 0 | 2022-02-13 |  | 36 | 2022-02-19 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1151820220212-5Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1151820220212-5Operator - Principle - After Jan 1011825INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11518 | 20220212-5 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-12 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Neys | 6 | C219-C236 | Neys | 0 | 2022-02-13 |  | 36 | 2022-02-19 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1151820220212-5L.O.A.1210 | Corbiere and Sons Contracting1151820220212-5L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11518 | 20220212-5 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-12 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Neys | 6 | C219-C236 | Neys | 0 | 2022-02-13 |  | 36 | 2022-02-19 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1151820220212-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1151820220212-5Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11518 | 20220212-5 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 7 | Dynamic | 0 | 0 |  |  | 888.86 | 115.5518 | 1004.4118 | 2022-02-12 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Neys | 6 | C219-C236 | Neys | 0 | 2022-02-13 |  | 36 | 2022-02-19 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1151820220212-5Grader - Cat 12 to 14 or equal- After Jan 107888.86 | Corbiere and Sons Contracting1151820220212-5Grader - Cat 12 to 14 or equal- After Jan 107888.86INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11517 | 20220212-4 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 0 | 0 | 900 | 117 | 1017 | 2022-02-12 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Prairie River | 6 | C171-C185 | Prairie River | 0 | 2022-02-13 |  | 36 | 2022-02-18 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1151720220212-4Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1151720220212-4Operator - Principle - After Jan 1012900INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11517 | 20220212-4 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-12 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Prairie River | 6 | C171-C185 | Prairie River | 0 | 2022-02-13 |  | 36 | 2022-02-18 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1151720220212-4L.O.A.1210 | Corbiere and Sons Contracting1151720220212-4L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11517 | 20220212-4 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-12 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Prairie River | 6 | C171-C185 | Prairie River | 0 | 2022-02-13 |  | 36 | 2022-02-18 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1151720220212-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1151720220212-4Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11517 | 20220212-4 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 11 | Dynamic | 0 | 0 |  |  | 1396.78 | 181.5814 | 1578.3614 | 2022-02-12 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Prairie River | 6 | C171-C185 | Prairie River | 0 | 2022-02-13 |  | 36 | 2022-02-18 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1151720220212-4Grader - Cat 12 to 14 or equal- After Jan 10111396.78 | Corbiere and Sons Contracting1151720220212-4Grader - Cat 12 to 14 or equal- After Jan 10111396.78INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11516 | 20220212-3 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-02-12 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Little Red Sucker Creek | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-02-13 |  | 36 | 2022-02-19 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1151620220212-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1151620220212-3Operator - Principle - After Jan 1011825INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11516 | 20220212-3 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-12 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Little Red Sucker Creek | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-02-13 |  | 36 | 2022-02-19 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1151620220212-3L.O.A.1210 | Corbiere and Sons Contracting1151620220212-3L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11516 | 20220212-3 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-12 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Little Red Sucker Creek | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-02-13 |  | 36 | 2022-02-19 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1151620220212-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1151620220212-3Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11516 | 20220212-3 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-02-12 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Little Red Sucker Creek | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-02-13 |  | 36 | 2022-02-19 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1151620220212-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1151620220212-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11513 | 20220211-6 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 0 | 0 | 900 | 117 | 1017 | 2022-02-11 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-02-13 |  | 36 | 2022-02-18 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1151320220211-6Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1151320220211-6Operator - Principle - After Jan 1012900INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11513 | 20220211-6 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-11 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-02-13 |  | 36 | 2022-02-18 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1151320220211-6L.O.A.1210 | Corbiere and Sons Contracting1151320220211-6L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11513 | 20220211-6 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 12 |  | 0 | 0 |  |  | 960 | 124.8 | 1084.8 | 2022-02-11 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-02-13 |  | 36 | 2022-02-18 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1151320220211-6Pickup w/ plow and sander12960 | Corbiere and Sons Contracting1151320220211-6Pickup w/ plow and sander12960INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11512 | 20220211-5 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-02-11 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Neys | 6 | C219-C235 | Neys | 0 | 2022-02-13 |  | 36 | 2022-02-18 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1151220220211-5Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1151220220211-5Operator - Principle - After Jan 1011825INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11512 | 20220211-5 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-11 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Neys | 6 | C219-C235 | Neys | 0 | 2022-02-13 |  | 36 | 2022-02-18 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1151220220211-5L.O.A.1210 | Corbiere and Sons Contracting1151220220211-5L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11512 | 20220211-5 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-11 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Neys | 6 | C219-C235 | Neys | 0 | 2022-02-13 |  | 36 | 2022-02-18 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1151220220211-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1151220220211-5Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11512 | 20220211-5 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-02-11 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Neys | 6 | C219-C235 | Neys | 0 | 2022-02-13 |  | 36 | 2022-02-18 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1151220220211-5Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1151220220211-5Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11511 | 20220211-4 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-02-11 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Prairie River | 6 | C171-C185 | Prairie River | 0 | 2022-02-13 |  | 36 | 2022-02-18 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1151120220211-4Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1151120220211-4Operator - Principle - After Jan 1011825INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11511 | 20220211-4 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-11 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Prairie River | 6 | C171-C185 | Prairie River | 0 | 2022-02-13 |  | 36 | 2022-02-18 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1151120220211-4L.O.A.1210 | Corbiere and Sons Contracting1151120220211-4L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11511 | 20220211-4 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-11 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Prairie River | 6 | C171-C185 | Prairie River | 0 | 2022-02-13 |  | 36 | 2022-02-18 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1151120220211-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1151120220211-4Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11511 | 20220211-4 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-02-11 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Prairie River | 6 | C171-C185 | Prairie River | 0 | 2022-02-13 |  | 36 | 2022-02-18 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1151120220211-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1151120220211-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11510 | 20220211-3 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-02-11 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Little Red Sucker Creek | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-02-13 |  | 36 | 2022-02-18 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1151020220211-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1151020220211-3Operator - Principle - After Jan 1011825INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11510 | 20220211-3 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-11 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Little Red Sucker Creek | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-02-13 |  | 36 | 2022-02-18 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1151020220211-3L.O.A.1210 | Corbiere and Sons Contracting1151020220211-3L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11510 | 20220211-3 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-11 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Little Red Sucker Creek | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-02-13 |  | 36 | 2022-02-18 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1151020220211-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1151020220211-3Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11510 | 20220211-3 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-02-11 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Little Red Sucker Creek | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-02-13 |  | 36 | 2022-02-18 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1151020220211-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1151020220211-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11507 | 20220210-6 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2022-02-10 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-02-13 |  | 36 | 2022-02-18 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1150720220210-6Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1150720220210-6Operator - Principle - After Jan 1012900INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11507 | 20220210-6 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2022-02-10 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-02-13 |  | 36 | 2022-02-18 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1150720220210-6L.O.A.1210 | Corbiere and Sons Contracting1150720220210-6L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11507 | 20220210-6 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 10 |  | 0 | 0 |  |  | 800 | 104 | 904 | 2022-02-10 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-02-13 |  | 36 | 2022-02-18 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1150720220210-6Pickup w/ plow and sander10800 | Corbiere and Sons Contracting1150720220210-6Pickup w/ plow and sander10800INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11505 | 20220210-5 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-02-10 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C219-C236 | Neys | 0 | 2022-02-13 |  | 36 | 2022-02-18 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1150520220210-5Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1150520220210-5Operator - Principle - After Jan 1011825INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11505 | 20220210-5 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-10 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C219-C236 | Neys | 0 | 2022-02-13 |  | 36 | 2022-02-18 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1150520220210-5L.O.A.1210 | Corbiere and Sons Contracting1150520220210-5L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11505 | 20220210-5 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-10 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C219-C236 | Neys | 0 | 2022-02-13 |  | 36 | 2022-02-18 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1150520220210-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1150520220210-5Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11505 | 20220210-5 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-02-10 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C219-C236 | Neys | 0 | 2022-02-13 |  | 36 | 2022-02-18 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1150520220210-5Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1150520220210-5Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11504 | 20220210-4 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-02-10 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C171-C185 | Prairie River | 0 | 2022-02-13 |  | 36 | 2022-02-18 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1150420220210-4Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1150420220210-4Operator - Principle - After Jan 1011825INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11504 | 20220210-4 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-10 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C171-C185 | Prairie River | 0 | 2022-02-13 |  | 36 | 2022-02-18 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1150420220210-4L.O.A.1210 | Corbiere and Sons Contracting1150420220210-4L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11504 | 20220210-4 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-10 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C171-C185 | Prairie River | 0 | 2022-02-13 |  | 36 | 2022-02-18 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1150420220210-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1150420220210-4Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11504 | 20220210-4 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-02-10 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C171-C185 | Prairie River | 0 | 2022-02-13 |  | 36 | 2022-02-18 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1150420220210-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1150420220210-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11503 | 20220210-3 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-02-10 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-02-13 |  | 36 | 2022-02-18 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1150320220210-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1150320220210-3Operator - Principle - After Jan 1011825INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11503 | 20220210-3 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-10 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-02-13 |  | 36 | 2022-02-18 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1150320220210-3L.O.A.1210 | Corbiere and Sons Contracting1150320220210-3L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11503 | 20220210-3 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-10 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-02-13 |  | 36 | 2022-02-18 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1150320220210-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1150320220210-3Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11503 | 20220210-3 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-02-10 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-02-13 |  | 36 | 2022-02-18 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1150320220210-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1150320220210-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11500 | 20220209-7 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 0.5 | HR |  |  | 0 | 0 | 37.5 | 4.875 | 42.375 | 2022-02-09 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C203-C209 | Dead Horse Creek | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1150020220209-7Operator - Principle - After Jan 100.537.5 | Corbiere and Sons Contracting1150020220209-7Operator - Principle - After Jan 100.537.5INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11500 | 20220209-7 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 0 | 0 | 450 | 58.5 | 508.5 | 2022-02-09 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C203-C209 | Dead Horse Creek | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1150020220209-7Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting1150020220209-7Operator - Principle - After Jan 106450INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11500 | 20220209-7 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-09 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C203-C209 | Dead Horse Creek | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1150020220209-7L.O.A.1210 | Corbiere and Sons Contracting1150020220209-7L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11500 | 20220209-7 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 6 |  | 0 | 0 |  |  | 480 | 62.4 | 542.4 | 2022-02-09 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C203-C209 | Dead Horse Creek | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1150020220209-7Pickup w/ plow and sander6480 | Corbiere and Sons Contracting1150020220209-7Pickup w/ plow and sander6480INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11499 | 20220209-6 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 0.5 | HR |  |  | 75 | 0 | 37.5 | 4.875 | 42.375 | 2022-02-09 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C258-C269 | Hare Lake Creek | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1149920220209-6Operator - Principle - After Jan 100.537.5 | Corbiere and Sons Contracting1149920220209-6Operator - Principle - After Jan 100.537.5INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11499 | 20220209-6 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 10 | HR |  |  | 75 | 0 | 750 | 97.5 | 847.5 | 2022-02-09 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C258-C269 | Hare Lake Creek | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1149920220209-6Operator - Principle - After Jan 1010750 | Corbiere and Sons Contracting1149920220209-6Operator - Principle - After Jan 1010750INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11499 | 20220209-6 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2022-02-09 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C258-C269 | Hare Lake Creek | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1149920220209-6L.O.A.1210 | Corbiere and Sons Contracting1149920220209-6L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11499 | 20220209-6 | 53510611 | Access | 0 | Light Truck - 1 to 3 Ton- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-09 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C258-C269 | Hare Lake Creek | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1149920220209-6Light Truck - 1 to 3 Ton- After Jan 101243.75 | Corbiere and Sons Contracting1149920220209-6Light Truck - 1 to 3 Ton- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11499 | 20220209-6 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 7.5 | Dynamic | 98.61 | 0 |  |  | 986.1 | 128.193 | 1114.293 | 2022-02-09 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C258-C269 | Hare Lake Creek | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1149920220209-6Dozer D6 or equal- After Jan 107.5986.1 | Corbiere and Sons Contracting1149920220209-6Dozer D6 or equal- After Jan 107.5986.1INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11498 | 20220209-5 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-02-09 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1149820220209-5Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1149820220209-5Operator - Principle - After Jan 1011825INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11498 | 20220209-5 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-09 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1149820220209-5L.O.A.1210 | Corbiere and Sons Contracting1149820220209-5L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11498 | 20220209-5 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-09 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1149820220209-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1149820220209-5Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11498 | 20220209-5 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-02-09 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1149820220209-5Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1149820220209-5Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11497 | 20220209-4 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 3 | HR |  |  | 70 | 0 | 210 | 27.3 | 237.3 | 2022-02-09 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1149720220209-4Driver - AZ - After Jan 103210 | Corbiere and Sons Contracting1149720220209-4Driver - AZ - After Jan 103210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11497 | 20220209-4 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-02-09 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1149720220209-4Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1149720220209-4Operator - Principle - After Jan 1011825INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11497 | 20220209-4 | 53510611 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2022-02-09 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1149720220209-4L.O.A.2420 | Corbiere and Sons Contracting1149720220209-4L.O.A.2420INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11497 | 20220209-4 | 53510611 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 3 | Dynamic | 91.79 | 0 |  |  | 367.17 | 47.7321 | 414.9021 | 2022-02-09 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1149720220209-4Tractor Trailer - 60 Ton- After Jan 103367.17 | Corbiere and Sons Contracting1149720220209-4Tractor Trailer - 60 Ton- After Jan 103367.17INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11497 | 20220209-4 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-09 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1149720220209-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1149720220209-4Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11497 | 20220209-4 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-02-09 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1149720220209-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1149720220209-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11496 | 20220209-3 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-02-09 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1149620220209-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1149620220209-3Operator - Principle - After Jan 1011825INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11496 | 20220209-3 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-09 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1149620220209-3L.O.A.1210 | Corbiere and Sons Contracting1149620220209-3L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11496 | 20220209-3 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-09 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1149620220209-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1149620220209-3Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11496 | 20220209-3 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-02-09 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1149620220209-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1149620220209-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11494 | 20220208-7 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 3 | HR |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-08 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jesse and DZ floated over to Hare Lake and he spent rest of day there | 6 | C257-C267 | Hare Lake Creek | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1149420220208-7Driver - AZ - After Jan 103210 | Corbiere and Sons Contracting1149420220208-7Driver - AZ - After Jan 103210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11494 | 20220208-7 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-02-08 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jesse and DZ floated over to Hare Lake and he spent rest of day there | 6 | C257-C267 | Hare Lake Creek | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1149420220208-7Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1149420220208-7Operator - Principle - After Jan 1011825INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11494 | 20220208-7 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-08 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jesse and DZ floated over to Hare Lake and he spent rest of day there | 6 | C257-C267 | Hare Lake Creek | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1149420220208-7L.O.A.1210 | Corbiere and Sons Contracting1149420220208-7L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11494 | 20220208-7 | 53510611 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 3 | Dynamic | 0 | 0 |  |  | 367.17 | 47.7321 | 414.9021 | 2022-02-08 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jesse and DZ floated over to Hare Lake and he spent rest of day there | 6 | C257-C267 | Hare Lake Creek | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1149420220208-7Tractor Trailer - 60 Ton- After Jan 103367.17 | Corbiere and Sons Contracting1149420220208-7Tractor Trailer - 60 Ton- After Jan 103367.17INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11494 | 20220208-7 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-08 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jesse and DZ floated over to Hare Lake and he spent rest of day there | 6 | C257-C267 | Hare Lake Creek | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1149420220208-7Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1149420220208-7Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11494 | 20220208-7 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 9 | Dynamic | 0 | 0 |  |  | 1183.32 | 153.8316 | 1337.1516 | 2022-02-08 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jesse and DZ floated over to Hare Lake and he spent rest of day there | 6 | C257-C267 | Hare Lake Creek | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1149420220208-7Dozer D6 or equal- After Jan 1091183.32 | Corbiere and Sons Contracting1149420220208-7Dozer D6 or equal- After Jan 1091183.32INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11493 | 20220208-6 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 0 | 0 | 450 | 58.5 | 508.5 | 2022-02-08 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1149320220208-6Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting1149320220208-6Operator - Principle - After Jan 106450INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11493 | 20220208-6 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-08 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1149320220208-6L.O.A.1210 | Corbiere and Sons Contracting1149320220208-6L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11493 | 20220208-6 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-08 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1149320220208-6Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1149320220208-6Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11493 | 20220208-6 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 5 | Dynamic | 0 | 0 |  |  | 634.9 | 82.537 | 717.437 | 2022-02-08 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1149320220208-6Grader - Cat 12 to 14 or equal- After Jan 105634.9 | Corbiere and Sons Contracting1149320220208-6Grader - Cat 12 to 14 or equal- After Jan 105634.9INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11492 | 20220208-5 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 0 | 0 | 900 | 117 | 1017 | 2022-02-08 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1149220220208-5Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1149220220208-5Operator - Principle - After Jan 1012900INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11492 | 20220208-5 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-02-08 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1149220220208-5Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1149220220208-5Operator - Principle - After Jan 1011825INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11492 | 20220208-5 | 53510611 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  | 0 | 0 | 420 | 54.6 | 474.6 | 2022-02-08 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1149220220208-5L.O.A.2420 | Corbiere and Sons Contracting1149220220208-5L.O.A.2420INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11492 | 20220208-5 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 12 |  | 0 | 0 |  |  | 960 | 124.8 | 1084.8 | 2022-02-08 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1149220220208-5Pickup w/ plow and sander12960 | Corbiere and Sons Contracting1149220220208-5Pickup w/ plow and sander12960INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11492 | 20220208-5 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-08 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1149220220208-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1149220220208-5Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11492 | 20220208-5 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-02-08 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1149220220208-5Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1149220220208-5Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11491 | 20220208-4 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 3.5 | HR |  |  | 70 | 0 | 245 | 31.85 | 276.85 | 2022-02-08 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1149120220208-4Driver - AZ - After Jan 103.5245 | Corbiere and Sons Contracting1149120220208-4Driver - AZ - After Jan 103.5245INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11491 | 20220208-4 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 0 | 0 | 450 | 58.5 | 508.5 | 2022-02-08 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1149120220208-4Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting1149120220208-4Operator - Principle - After Jan 106450INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11491 | 20220208-4 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2022-02-08 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1149120220208-4L.O.A.1210 | Corbiere and Sons Contracting1149120220208-4L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11491 | 20220208-4 | 53510611 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 3.5 | Dynamic | 91.79 | 0 |  |  | 428.365 | 55.6874 | 484.0525 | 2022-02-08 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1149120220208-4Tractor Trailer - 60 Ton- After Jan 103.5428.365 | Corbiere and Sons Contracting1149120220208-4Tractor Trailer - 60 Ton- After Jan 103.5428.365INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11491 | 20220208-4 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 4 | Dynamic | 0 | 0 |  |  | 507.92 | 66.0296 | 573.9496 | 2022-02-08 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1149120220208-4Grader - Cat 12 to 14 or equal- After Jan 104507.92 | Corbiere and Sons Contracting1149120220208-4Grader - Cat 12 to 14 or equal- After Jan 104507.92INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11490 | 20220208-3 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5 | HR |  |  | 0 | 0 | 375 | 48.75 | 423.75 | 2022-02-08 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C171-C185 | Prairie River | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1149020220208-3Operator - Principle - After Jan 105375 | Corbiere and Sons Contracting1149020220208-3Operator - Principle - After Jan 105375INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11490 | 20220208-3 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-08 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C171-C185 | Prairie River | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1149020220208-3L.O.A.1210 | Corbiere and Sons Contracting1149020220208-3L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11490 | 20220208-3 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-08 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C171-C185 | Prairie River | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1149020220208-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1149020220208-3Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11490 | 20220208-3 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 5 | Dynamic | 0 | 0 |  |  | 634.9 | 82.537 | 717.437 | 2022-02-08 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C171-C185 | Prairie River | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1149020220208-3Grader - Cat 12 to 14 or equal- After Jan 105634.9 | Corbiere and Sons Contracting1149020220208-3Grader - Cat 12 to 14 or equal- After Jan 105634.9INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11488 | 20220207-5 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2022-02-07 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1148820220207-5Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1148820220207-5Operator - Principle - After Jan 1012900INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11488 | 20220207-5 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2022-02-07 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1148820220207-5Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1148820220207-5Operator - Principle - After Jan 1012900INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11488 | 20220207-5 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5 | HR |  |  | 75 | 0 | 375 | 48.75 | 423.75 | 2022-02-07 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1148820220207-5Operator - Principle - After Jan 105375 | Corbiere and Sons Contracting1148820220207-5Operator - Principle - After Jan 105375INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11488 | 20220207-5 | 53510611 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2022-02-07 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1148820220207-5L.O.A.3630 | Corbiere and Sons Contracting1148820220207-5L.O.A.3630INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11488 | 20220207-5 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 12 |  | 0 | 0 |  |  | 960 | 124.8 | 1084.8 | 2022-02-07 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1148820220207-5Pickup w/ plow and sander12960 | Corbiere and Sons Contracting1148820220207-5Pickup w/ plow and sander12960INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11488 | 20220207-5 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-07 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1148820220207-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1148820220207-5Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11488 | 20220207-5 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-07 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1148820220207-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1148820220207-5Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11488 | 20220207-5 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 4 | Dynamic | 95.24 | 0 |  |  | 507.92 | 66.0296 | 573.9496 | 2022-02-07 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1148820220207-5Grader - Cat 12 to 14 or equal- After Jan 104507.92 | Corbiere and Sons Contracting1148820220207-5Grader - Cat 12 to 14 or equal- After Jan 104507.92INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11488 | 20220207-5 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 9 | Dynamic | 98.61 | 0 |  |  | 1183.32 | 153.8316 | 1337.1516 | 2022-02-07 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1148820220207-5Dozer D6 or equal- After Jan 1091183.32 | Corbiere and Sons Contracting1148820220207-5Dozer D6 or equal- After Jan 1091183.32INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11487 | 20220207-4 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 0 | 0 | 900 | 117 | 1017 | 2022-02-07 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1148720220207-4Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1148720220207-4Operator - Principle - After Jan 1012900INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11487 | 20220207-4 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-07 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1148720220207-4L.O.A.1210 | Corbiere and Sons Contracting1148720220207-4L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11487 | 20220207-4 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-07 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1148720220207-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1148720220207-4Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11487 | 20220207-4 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 11 | Dynamic | 0 | 0 |  |  | 1396.78 | 181.5814 | 1578.3614 | 2022-02-07 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1148720220207-4Grader - Cat 12 to 14 or equal- After Jan 10111396.78 | Corbiere and Sons Contracting1148720220207-4Grader - Cat 12 to 14 or equal- After Jan 10111396.78INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11486 | 20220207-3 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 0 | 0 | 900 | 117 | 1017 | 2022-02-07 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C198-C202 | Ripple Lake | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1148620220207-3Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1148620220207-3Operator - Principle - After Jan 1012900INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11486 | 20220207-3 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-07 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C198-C202 | Ripple Lake | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1148620220207-3L.O.A.1210 | Corbiere and Sons Contracting1148620220207-3L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11486 | 20220207-3 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-07 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C198-C202 | Ripple Lake | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1148620220207-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1148620220207-3Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11486 | 20220207-3 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 11 | Dynamic | 0 | 0 |  |  | 1396.78 | 181.5814 | 1578.3614 | 2022-02-07 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C198-C202 | Ripple Lake | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1148620220207-3Grader - Cat 12 to 14 or equal- After Jan 10111396.78 | Corbiere and Sons Contracting1148620220207-3Grader - Cat 12 to 14 or equal- After Jan 10111396.78INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11484 | 20220206-7 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 4 | HR |  |  | 70 | 0 | 280 | 36.4 | 316.4 | 2022-02-06 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Armand running grader - Shawn floating DZ over; Jesse on DZ remainder of day | 6 | C219-C235 | Neys Road | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1148420220206-7Driver - AZ - After Jan 104280 | Corbiere and Sons Contracting1148420220206-7Driver - AZ - After Jan 104280INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11484 | 20220206-7 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 75 | 0 | 450 | 58.5 | 508.5 | 2022-02-06 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Armand running grader - Shawn floating DZ over; Jesse on DZ remainder of day | 6 | C219-C235 | Neys Road | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1148420220206-7Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting1148420220206-7Operator - Principle - After Jan 106450INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11484 | 20220206-7 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 8 | HR |  |  | 0 | 0 | 600 | 78 | 678 | 2022-02-06 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Armand running grader - Shawn floating DZ over; Jesse on DZ remainder of day | 6 | C219-C235 | Neys Road | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1148420220206-7Operator - Principle - After Jan 108600 | Corbiere and Sons Contracting1148420220206-7Operator - Principle - After Jan 108600INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11484 | 20220206-7 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2022-02-06 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Armand running grader - Shawn floating DZ over; Jesse on DZ remainder of day | 6 | C219-C235 | Neys Road | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1148420220206-7L.O.A.1210 | Corbiere and Sons Contracting1148420220206-7L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11484 | 20220206-7 | 53510611 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 4 | Dynamic | 0 | 0 |  |  | 489.56 | 63.6428 | 553.2028 | 2022-02-06 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Armand running grader - Shawn floating DZ over; Jesse on DZ remainder of day | 6 | C219-C235 | Neys Road | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1148420220206-7Tractor Trailer - 60 Ton- After Jan 104489.56 | Corbiere and Sons Contracting1148420220206-7Tractor Trailer - 60 Ton- After Jan 104489.56INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11484 | 20220206-7 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-06 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Armand running grader - Shawn floating DZ over; Jesse on DZ remainder of day | 6 | C219-C235 | Neys Road | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1148420220206-7Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1148420220206-7Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11484 | 20220206-7 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 5 | Dynamic | 95.24 | 0 |  |  | 634.9 | 82.537 | 717.437 | 2022-02-06 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Armand running grader - Shawn floating DZ over; Jesse on DZ remainder of day | 6 | C219-C235 | Neys Road | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1148420220206-7Grader - Cat 12 to 14 or equal- After Jan 105634.9 | Corbiere and Sons Contracting1148420220206-7Grader - Cat 12 to 14 or equal- After Jan 105634.9INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11484 | 20220206-7 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 5 | Dynamic | 0 | 0 |  |  | 657.4 | 85.462 | 742.862 | 2022-02-06 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Armand running grader - Shawn floating DZ over; Jesse on DZ remainder of day | 6 | C219-C235 | Neys Road | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1148420220206-7Dozer D6 or equal- After Jan 105657.4 | Corbiere and Sons Contracting1148420220206-7Dozer D6 or equal- After Jan 105657.4INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11482 | 20220206-5 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 0 | 0 | 900 | 117 | 1017 | 2022-02-06 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C210-C213 | Middleton | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1148220220206-5Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1148220220206-5Operator - Principle - After Jan 1012900INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11482 | 20220206-5 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-06 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C210-C213 | Middleton | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1148220220206-5L.O.A.1210 | Corbiere and Sons Contracting1148220220206-5L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11482 | 20220206-5 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 8 |  | 0 | 0 |  |  | 640 | 83.2 | 723.2 | 2022-02-06 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C210-C213 | Middleton | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1148220220206-5Pickup w/ plow and sander8640 | Corbiere and Sons Contracting1148220220206-5Pickup w/ plow and sander8640INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11481 | 20220206-4 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 0 | 0 | 900 | 117 | 1017 | 2022-02-06 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1148120220206-4Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1148120220206-4Operator - Principle - After Jan 1012900INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11481 | 20220206-4 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-06 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1148120220206-4L.O.A.1210 | Corbiere and Sons Contracting1148120220206-4L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11481 | 20220206-4 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-06 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1148120220206-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1148120220206-4Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11481 | 20220206-4 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 11 | Dynamic | 0 | 0 |  |  | 1396.78 | 181.5814 | 1578.3614 | 2022-02-06 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1148120220206-4Grader - Cat 12 to 14 or equal- After Jan 10111396.78 | Corbiere and Sons Contracting1148120220206-4Grader - Cat 12 to 14 or equal- After Jan 10111396.78INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11480 | 20220206-3 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 4 | HR |  |  | 0 | 0 | 280 | 36.4 | 316.4 | 2022-02-06 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C198-C202 | Ripple Creek | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1148020220206-3Driver - AZ - After Jan 104280 | Corbiere and Sons Contracting1148020220206-3Driver - AZ - After Jan 104280INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11480 | 20220206-3 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 14 | HR |  |  | 0 | 0 | 1050 | 136.5 | 1186.5 | 2022-02-06 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C198-C202 | Ripple Creek | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1148020220206-3Operator - Principle - After Jan 10141050 | Corbiere and Sons Contracting1148020220206-3Operator - Principle - After Jan 10141050INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11480 | 20220206-3 | 53510611 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  | 0 | 0 | 420 | 54.6 | 474.6 | 2022-02-06 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C198-C202 | Ripple Creek | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1148020220206-3L.O.A.2420 | Corbiere and Sons Contracting1148020220206-3L.O.A.2420INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11480 | 20220206-3 | 53510611 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 4 | Dynamic | 0 | 0 |  |  | 489.56 | 63.6428 | 553.2028 | 2022-02-06 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C198-C202 | Ripple Creek | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1148020220206-3Tractor Trailer - 60 Ton- After Jan 104489.56 | Corbiere and Sons Contracting1148020220206-3Tractor Trailer - 60 Ton- After Jan 104489.56INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11480 | 20220206-3 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-06 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C198-C202 | Ripple Creek | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1148020220206-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1148020220206-3Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11480 | 20220206-3 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 9 | Dynamic | 0 | 0 |  |  | 1142.82 | 148.5666 | 1291.3866 | 2022-02-06 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C198-C202 | Ripple Creek | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1148020220206-3Grader - Cat 12 to 14 or equal- After Jan 1091142.82 | Corbiere and Sons Contracting1148020220206-3Grader - Cat 12 to 14 or equal- After Jan 1091142.82INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11477 | 20220205-5 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 0 | 0 | 900 | 117 | 1017 | 2022-02-05 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C186-C195 | Del Lake | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1147720220205-5Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1147720220205-5Operator - Principle - After Jan 1012900INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11477 | 20220205-5 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-05 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C186-C195 | Del Lake | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1147720220205-5L.O.A.1210 | Corbiere and Sons Contracting1147720220205-5L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11477 | 20220205-5 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 8 |  | 0 | 0 |  |  | 640 | 83.2 | 723.2 | 2022-02-05 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C186-C195 | Del Lake | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1147720220205-5Pickup w/ plow and sander8640 | Corbiere and Sons Contracting1147720220205-5Pickup w/ plow and sander8640INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11476 | 20220205-4 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-02-05 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1147620220205-4Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1147620220205-4Operator - Principle - After Jan 1011825INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11476 | 20220205-4 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-05 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1147620220205-4L.O.A.1210 | Corbiere and Sons Contracting1147620220205-4L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11476 | 20220205-4 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-05 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1147620220205-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1147620220205-4Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11476 | 20220205-4 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-02-05 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-02-13 |  | 36 | 2022-02-17 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1147620220205-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1147620220205-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11475 | 20220205-3 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 5 | HR |  |  | 0 | 0 | 350 | 45.5 | 395.5 | 2022-02-05 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1147520220205-3Driver - AZ - After Jan 105350 | Corbiere and Sons Contracting1147520220205-3Driver - AZ - After Jan 105350INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11475 | 20220205-3 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-02-05 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1147520220205-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1147520220205-3Operator - Principle - After Jan 1011825INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11475 | 20220205-3 | 53510611 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  | 0 | 0 | 420 | 54.6 | 474.6 | 2022-02-05 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1147520220205-3L.O.A.2420 | Corbiere and Sons Contracting1147520220205-3L.O.A.2420INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11475 | 20220205-3 | 53510611 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 5 | Dynamic | 0 | 0 |  |  | 611.95 | 79.5535 | 691.5035 | 2022-02-05 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1147520220205-3Tractor Trailer - 60 Ton- After Jan 105611.95 | Corbiere and Sons Contracting1147520220205-3Tractor Trailer - 60 Ton- After Jan 105611.95INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11475 | 20220205-3 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-05 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1147520220205-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1147520220205-3Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11475 | 20220205-3 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 9 | Dynamic | 0 | 0 |  |  | 1142.82 | 148.5666 | 1291.3866 | 2022-02-05 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1147520220205-3Grader - Cat 12 to 14 or equal- After Jan 1091142.82 | Corbiere and Sons Contracting1147520220205-3Grader - Cat 12 to 14 or equal- After Jan 1091142.82INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11472 | 20220204-6 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 4 | HR |  |  | 0 | 0 | 300 | 39 | 339 | 2022-02-04 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jesse finished up on DZ in Peninsula East | 6 | C270-C277 | Peninsula | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1147220220204-6Operator - Principle - After Jan 104300 | Corbiere and Sons Contracting1147220220204-6Operator - Principle - After Jan 104300INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11472 | 20220204-6 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-04 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jesse finished up on DZ in Peninsula East | 6 | C270-C277 | Peninsula | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1147220220204-6L.O.A.1210 | Corbiere and Sons Contracting1147220220204-6L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11472 | 20220204-6 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-04 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jesse finished up on DZ in Peninsula East | 6 | C270-C277 | Peninsula | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1147220220204-6Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1147220220204-6Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11472 | 20220204-6 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 4 | Dynamic | 0 | 0 |  |  | 525.92 | 68.3696 | 594.2896 | 2022-02-04 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jesse finished up on DZ in Peninsula East | 6 | C270-C277 | Peninsula | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1147220220204-6Dozer D6 or equal- After Jan 104525.92 | Corbiere and Sons Contracting1147220220204-6Dozer D6 or equal- After Jan 104525.92INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11471 | 20220204-5 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 0 | 0 | 900 | 117 | 1017 | 2022-02-04 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C244-C247 | Mink Creek | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1147120220204-5Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1147120220204-5Operator - Principle - After Jan 1012900INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11471 | 20220204-5 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-04 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C244-C247 | Mink Creek | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1147120220204-5L.O.A.1210 | Corbiere and Sons Contracting1147120220204-5L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11471 | 20220204-5 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 12 |  | 0 | 0 |  |  | 960 | 124.8 | 1084.8 | 2022-02-04 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C244-C247 | Mink Creek | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1147120220204-5Pickup w/ plow and sander12960 | Corbiere and Sons Contracting1147120220204-5Pickup w/ plow and sander12960INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11470 | 20220204-4 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 10 | HR |  |  | 0 | 0 | 750 | 97.5 | 847.5 | 2022-02-04 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1147020220204-4Operator - Principle - After Jan 1010750 | Corbiere and Sons Contracting1147020220204-4Operator - Principle - After Jan 1010750INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11470 | 20220204-4 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-04 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1147020220204-4L.O.A.1210 | Corbiere and Sons Contracting1147020220204-4L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11470 | 20220204-4 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-04 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1147020220204-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1147020220204-4Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11470 | 20220204-4 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 9 | Dynamic | 0 | 0 |  |  | 1142.82 | 148.5666 | 1291.3866 | 2022-02-04 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1147020220204-4Grader - Cat 12 to 14 or equal- After Jan 1091142.82 | Corbiere and Sons Contracting1147020220204-4Grader - Cat 12 to 14 or equal- After Jan 1091142.82INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11469 | 20220204-3 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 4 | HR |  |  | 0 | 0 | 280 | 36.4 | 316.4 | 2022-02-04 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1146920220204-3Driver - AZ - After Jan 104280 | Corbiere and Sons Contracting1146920220204-3Driver - AZ - After Jan 104280INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11469 | 20220204-3 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-02-04 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1146920220204-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1146920220204-3Operator - Principle - After Jan 1011825INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11469 | 20220204-3 | 53510611 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  | 0 | 0 | 420 | 54.6 | 474.6 | 2022-02-04 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1146920220204-3L.O.A.2420 | Corbiere and Sons Contracting1146920220204-3L.O.A.2420INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11469 | 20220204-3 | 53510611 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 4 | Dynamic | 0 | 0 |  |  | 489.56 | 63.6428 | 553.2028 | 2022-02-04 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1146920220204-3Tractor Trailer - 60 Ton- After Jan 104489.56 | Corbiere and Sons Contracting1146920220204-3Tractor Trailer - 60 Ton- After Jan 104489.56INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11469 | 20220204-3 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-04 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1146920220204-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1146920220204-3Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11469 | 20220204-3 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 9 | Dynamic | 0 | 0 |  |  | 1142.82 | 148.5666 | 1291.3866 | 2022-02-04 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1146920220204-3Grader - Cat 12 to 14 or equal- After Jan 1091142.82 | Corbiere and Sons Contracting1146920220204-3Grader - Cat 12 to 14 or equal- After Jan 1091142.82INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11467 | 20220203-6 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-02-03 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jesse worked on Peninsula East and West | 6 | C270-C277 | Peninsula | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1146720220203-6Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1146720220203-6Operator - Principle - After Jan 1011825INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11467 | 20220203-6 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-03 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jesse worked on Peninsula East and West | 6 | C270-C277 | Peninsula | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1146720220203-6L.O.A.1210 | Corbiere and Sons Contracting1146720220203-6L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11467 | 20220203-6 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-03 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jesse worked on Peninsula East and West | 6 | C270-C277 | Peninsula | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1146720220203-6Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1146720220203-6Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11467 | 20220203-6 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 9 | Dynamic | 98.61 | 0 |  |  | 1183.32 | 153.8316 | 1337.1516 | 2022-02-03 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jesse worked on Peninsula East and West | 6 | C270-C277 | Peninsula | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1146720220203-6Dozer D6 or equal- After Jan 1091183.32 | Corbiere and Sons Contracting1146720220203-6Dozer D6 or equal- After Jan 1091183.32INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11466 | 20220203-5 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2022-02-03 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C203-C209 | Dead Horse Creek | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1146620220203-5Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1146620220203-5Operator - Principle - After Jan 1012900INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11466 | 20220203-5 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2022-02-03 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C203-C209 | Dead Horse Creek | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1146620220203-5L.O.A.1210 | Corbiere and Sons Contracting1146620220203-5L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11466 | 20220203-5 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 12 |  | 0 | 0 |  |  | 960 | 124.8 | 1084.8 | 2022-02-03 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C203-C209 | Dead Horse Creek | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1146620220203-5Pickup w/ plow and sander12960 | Corbiere and Sons Contracting1146620220203-5Pickup w/ plow and sander12960INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11465 | 20220203-4 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2022-02-03 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1146520220203-4Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1146520220203-4Operator - Principle - After Jan 1011825INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11465 | 20220203-4 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2022-02-03 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1146520220203-4L.O.A.1210 | Corbiere and Sons Contracting1146520220203-4L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11465 | 20220203-4 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-03 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1146520220203-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1146520220203-4Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11465 | 20220203-4 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 95.24 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-02-03 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1146520220203-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1146520220203-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11464 | 20220203-3 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 6 | HR |  |  | 0 | 0 | 420 | 54.6 | 474.6 | 2022-02-03 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C257-C269 | Hare Lake Creek | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1146420220203-3Driver - AZ - After Jan 106420 | Corbiere and Sons Contracting1146420220203-3Driver - AZ - After Jan 106420INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11464 | 20220203-3 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 0 | 0 | 900 | 117 | 1017 | 2022-02-03 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C257-C269 | Hare Lake Creek | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1146420220203-3Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1146420220203-3Operator - Principle - After Jan 1012900INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11464 | 20220203-3 | 53510611 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2022-02-03 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C257-C269 | Hare Lake Creek | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1146420220203-3L.O.A.2420 | Corbiere and Sons Contracting1146420220203-3L.O.A.2420INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11464 | 20220203-3 | 53510611 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 6 | Dynamic | 0 | 0 |  |  | 734.34 | 95.4642 | 829.8042 | 2022-02-03 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C257-C269 | Hare Lake Creek | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1146420220203-3Tractor Trailer - 60 Ton- After Jan 106734.34 | Corbiere and Sons Contracting1146420220203-3Tractor Trailer - 60 Ton- After Jan 106734.34INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11464 | 20220203-3 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-03 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C257-C269 | Hare Lake Creek | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1146420220203-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1146420220203-3Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11464 | 20220203-3 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 9.5 | Dynamic | 95.24 | 0 |  |  | 1206.31 | 156.8203 | 1363.1303 | 2022-02-03 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C257-C269 | Hare Lake Creek | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1146420220203-3Grader - Cat 12 to 14 or equal- After Jan 109.51206.31 | Corbiere and Sons Contracting1146420220203-3Grader - Cat 12 to 14 or equal- After Jan 109.51206.31INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11461 | 20220202-9 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 8 | HR |  |  | 70 | 0 | 560 | 72.8 | 632.8 | 2022-02-02 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved DZ over and then he worked there rest of day | 6 | C268-D005 | Peninsula | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1146120220202-9Driver - AZ - After Jan 108560 | Corbiere and Sons Contracting1146120220202-9Driver - AZ - After Jan 108560INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11461 | 20220202-9 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 8 | HR |  |  | 75 | 0 | 600 | 78 | 678 | 2022-02-02 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved DZ over and then he worked there rest of day | 6 | C268-D005 | Peninsula | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1146120220202-9Operator - Principle - After Jan 108600 | Corbiere and Sons Contracting1146120220202-9Operator - Principle - After Jan 108600INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11461 | 20220202-9 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2022-02-02 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved DZ over and then he worked there rest of day | 6 | C268-D005 | Peninsula | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1146120220202-9L.O.A.1210 | Corbiere and Sons Contracting1146120220202-9L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11461 | 20220202-9 | 53510611 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 8 | Dynamic | 91.79 | 0 |  |  | 979.12 | 127.2856 | 1106.4056 | 2022-02-02 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved DZ over and then he worked there rest of day | 6 | C268-D005 | Peninsula | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1146120220202-9Tractor Trailer - 60 Ton- After Jan 108979.12 | Corbiere and Sons Contracting1146120220202-9Tractor Trailer - 60 Ton- After Jan 108979.12INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11461 | 20220202-9 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 6 | Dynamic | 98.61 | 0 |  |  | 788.88 | 102.5544 | 891.4344 | 2022-02-02 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved DZ over and then he worked there rest of day | 6 | C268-D005 | Peninsula | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1146120220202-9Dozer D6 or equal- After Jan 106788.88 | Corbiere and Sons Contracting1146120220202-9Dozer D6 or equal- After Jan 106788.88INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11460 | 20220202-8 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 3 | HR |  |  | 75 | 0 | 225 | 29.25 | 254.25 | 2022-02-02 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jesse started on DZ in Culvert and then went to Peninsula | 6 | C236-C243 | Culvert Creek | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1146020220202-8Operator - Principle - After Jan 103225 | Corbiere and Sons Contracting1146020220202-8Operator - Principle - After Jan 103225INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11460 | 20220202-8 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2022-02-02 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jesse started on DZ in Culvert and then went to Peninsula | 6 | C236-C243 | Culvert Creek | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1146020220202-8L.O.A.1210 | Corbiere and Sons Contracting1146020220202-8L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11460 | 20220202-8 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-02 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jesse started on DZ in Culvert and then went to Peninsula | 6 | C236-C243 | Culvert Creek | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1146020220202-8Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1146020220202-8Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11460 | 20220202-8 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 3 | Dynamic | 98.61 | 0 |  |  | 394.44 | 51.2772 | 445.7172 | 2022-02-02 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jesse started on DZ in Culvert and then went to Peninsula | 6 | C236-C243 | Culvert Creek | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1146020220202-8Dozer D6 or equal- After Jan 103394.44 | Corbiere and Sons Contracting1146020220202-8Dozer D6 or equal- After Jan 103394.44INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11459 | 20220202-7 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2022-02-02 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C219-C235 | Neys Road | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1145920220202-7Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1145920220202-7Operator - Principle - After Jan 1012900INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11459 | 20220202-7 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2022-02-02 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C219-C235 | Neys Road | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1145920220202-7L.O.A.1210 | Corbiere and Sons Contracting1145920220202-7L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11459 | 20220202-7 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 12 |  | 0 | 0 |  |  | 960 | 124.8 | 1084.8 | 2022-02-02 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C219-C235 | Neys Road | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1145920220202-7Pickup w/ plow and sander12960 | Corbiere and Sons Contracting1145920220202-7Pickup w/ plow and sander12960INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11458 | 20220202-6 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-02-02 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Lake A | 6 | C130-C151 | Lake A | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1145820220202-6Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1145820220202-6Operator - Principle - After Jan 1011825INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11458 | 20220202-6 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-02 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Lake A | 6 | C130-C151 | Lake A | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1145820220202-6L.O.A.1210 | Corbiere and Sons Contracting1145820220202-6L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11458 | 20220202-6 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-02 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Lake A | 6 | C130-C151 | Lake A | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1145820220202-6Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1145820220202-6Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11458 | 20220202-6 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-02-02 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Lake A | 6 | C130-C151 | Lake A | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1145820220202-6Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1145820220202-6Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11456 | 20220202-4 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 3 | HR |  |  | 0 | 0 | 225 | 29.25 | 254.25 | 2022-02-02 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Mink | 6 | C244-C247 | Mink Creek | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1145620220202-4Operator - Principle - After Jan 103225 | Corbiere and Sons Contracting1145620220202-4Operator - Principle - After Jan 103225INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11456 | 20220202-4 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-02 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Mink | 6 | C244-C247 | Mink Creek | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1145620220202-4L.O.A.1210 | Corbiere and Sons Contracting1145620220202-4L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11456 | 20220202-4 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-02 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Mink | 6 | C244-C247 | Mink Creek | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1145620220202-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1145620220202-4Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11456 | 20220202-4 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 2 | Dynamic | 0 | 0 |  |  | 253.96 | 33.0148 | 286.9748 | 2022-02-02 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Mink | 6 | C244-C247 | Mink Creek | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1145620220202-4Grader - Cat 12 to 14 or equal- After Jan 102253.96 | Corbiere and Sons Contracting1145620220202-4Grader - Cat 12 to 14 or equal- After Jan 102253.96INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11455 | 20220202-3 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-02-02 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Prairie River | 6 | C171-C185 | Prairie River | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1145520220202-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1145520220202-3Operator - Principle - After Jan 1011825INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11455 | 20220202-3 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-02 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Prairie River | 6 | C171-C185 | Prairie River | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1145520220202-3L.O.A.1210 | Corbiere and Sons Contracting1145520220202-3L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11455 | 20220202-3 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-02 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Prairie River | 6 | C171-C185 | Prairie River | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1145520220202-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1145520220202-3Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11455 | 20220202-3 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-02-02 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Prairie River | 6 | C171-C185 | Prairie River | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1145520220202-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1145520220202-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11452 | 20220201-9 | 53510611 | Access | 0 | 3rd Party Charges | 1 | 53.35 | Unit |  |  |  |  | 53.35 | 6.9355 | 60.2855 | 2022-02-01 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Sand provided by Valentino | 6 | C129-D005 | WF6 | 0 | 2022-02-13 |  | 36 | 2022-02-16 | 418 | Winter road sand |  |  |  | Mike Lecocq | 06 | Corbiere and Sons Contracting1145220220201-93rd Party Charges53.3553.35 | Corbiere and Sons Contracting1145220220201-93rd Party Charges53.3553.35INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11451 | 20220201-8 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 5 | HR |  |  | 70 | 0 | 350 | 45.5 | 395.5 | 2022-02-01 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Shawn and float moved Dozer from Jackpine to Culvert Creek | 6 | C236-C243 | Culvert Creek | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1145120220201-8Driver - AZ - After Jan 105350 | Corbiere and Sons Contracting1145120220201-8Driver - AZ - After Jan 105350INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11451 | 20220201-8 | 53510611 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 5 | Dynamic | 91.79 | 0 |  |  | 611.95 | 79.5535 | 691.5035 | 2022-02-01 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Shawn and float moved Dozer from Jackpine to Culvert Creek | 6 | C236-C243 | Culvert Creek | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1145120220201-8Tractor Trailer - 60 Ton- After Jan 105611.95 | Corbiere and Sons Contracting1145120220201-8Tractor Trailer - 60 Ton- After Jan 105611.95INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11448 | 20220201-6 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2022-02-01 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1144820220201-6Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1144820220201-6Operator - Principle - After Jan 1012900INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11448 | 20220201-6 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2022-02-01 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1144820220201-6L.O.A.1210 | Corbiere and Sons Contracting1144820220201-6L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11448 | 20220201-6 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 12 |  | 0 | 0 |  |  | 960 | 124.8 | 1084.8 | 2022-02-01 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1144820220201-6Pickup w/ plow and sander12960 | Corbiere and Sons Contracting1144820220201-6Pickup w/ plow and sander12960INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11447 | 20220201-5 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-02-01 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Lake A | 6 | C130-C151 | Lake A | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1144720220201-5Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1144720220201-5Operator - Principle - After Jan 1011825INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11447 | 20220201-5 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-01 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Lake A | 6 | C130-C151 | Lake A | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1144720220201-5L.O.A.1210 | Corbiere and Sons Contracting1144720220201-5L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11447 | 20220201-5 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-01 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Lake A | 6 | C130-C151 | Lake A | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1144720220201-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1144720220201-5Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11447 | 20220201-5 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-02-01 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Lake A | 6 | C130-C151 | Lake A | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1144720220201-5Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1144720220201-5Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11446 | 20220201-4 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-02-01 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Mink Creek | 6 | C244-C247 | Mink Creek | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1144620220201-4Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1144620220201-4Operator - Principle - After Jan 1011825INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11446 | 20220201-4 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-01 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Mink Creek | 6 | C244-C247 | Mink Creek | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1144620220201-4L.O.A.1210 | Corbiere and Sons Contracting1144620220201-4L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11446 | 20220201-4 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-01 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Mink Creek | 6 | C244-C247 | Mink Creek | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1144620220201-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1144620220201-4Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11446 | 20220201-4 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-02-01 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Mink Creek | 6 | C244-C247 | Mink Creek | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1144620220201-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1144620220201-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11445 | 20220201-3 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-02-01 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Prairie River | 6 | C171-C185 | Prairie River | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1144520220201-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1144520220201-3Operator - Principle - After Jan 1011825INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11445 | 20220201-3 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-01 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Prairie River | 6 | C171-C185 | Prairie River | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1144520220201-3L.O.A.1210 | Corbiere and Sons Contracting1144520220201-3L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11445 | 20220201-3 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-01 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Prairie River | 6 | C171-C185 | Prairie River | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1144520220201-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1144520220201-3Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11445 | 20220201-3 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-02-01 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Prairie River | 6 | C171-C185 | Prairie River | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1144520220201-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1144520220201-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11443 | 20220131-5 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2022-01-31 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Del Lake | 6 | C130-C151 | Lake A | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1144320220131-5Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1144320220131-5Operator - Principle - After Jan 1012900INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11443 | 20220131-5 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-01-31 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Del Lake | 6 | C130-C151 | Lake A | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1144320220131-5Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1144320220131-5Operator - Principle - After Jan 1011825INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11443 | 20220131-5 | 53510611 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2022-01-31 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Del Lake | 6 | C130-C151 | Lake A | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1144320220131-5L.O.A.2420 | Corbiere and Sons Contracting1144320220131-5L.O.A.2420INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11443 | 20220131-5 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 12 |  | 0 | 0 |  |  | 960 | 124.8 | 1084.8 | 2022-01-31 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Del Lake | 6 | C130-C151 | Lake A | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1144320220131-5Pickup w/ plow and sander12960 | Corbiere and Sons Contracting1144320220131-5Pickup w/ plow and sander12960INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11443 | 20220131-5 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-31 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Del Lake | 6 | C130-C151 | Lake A | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1144320220131-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1144320220131-5Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11443 | 20220131-5 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-01-31 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Del Lake | 6 | C130-C151 | Lake A | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1144320220131-5Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1144320220131-5Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11442 | 20220131-4 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-01-31 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Del Lake | 6 | C244-C247 | Mink Creek | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1144220220131-4Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1144220220131-4Operator - Principle - After Jan 1011825INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11442 | 20220131-4 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-01-31 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Del Lake | 6 | C244-C247 | Mink Creek | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1144220220131-4L.O.A.1210 | Corbiere and Sons Contracting1144220220131-4L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11442 | 20220131-4 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-31 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Del Lake | 6 | C244-C247 | Mink Creek | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1144220220131-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1144220220131-4Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11442 | 20220131-4 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-01-31 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Del Lake | 6 | C244-C247 | Mink Creek | 0 | 2022-02-13 |  | 36 | 2022-02-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1144220220131-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1144220220131-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11439 | 20220130-6 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5 | HR |  |  | 0 | 0 | 375 | 48.75 | 423.75 | 2022-01-30 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Peninsula | 6 | C268-D005 | Peninsula | 0 | 2022-02-04 |  | 37 | 2022-02-05 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1143920220130-6Operator - Principle - After Jan 105375 | Corbiere and Sons Contracting1143920220130-6Operator - Principle - After Jan 105375INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11439 | 20220130-6 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-30 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Peninsula | 6 | C268-D005 | Peninsula | 0 | 2022-02-04 |  | 37 | 2022-02-05 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1143920220130-6Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1143920220130-6Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11439 | 20220130-6 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 4 | Dynamic | 98.61 | 0 |  |  | 525.92 | 68.3696 | 594.2896 | 2022-01-30 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Peninsula | 6 | C268-D005 | Peninsula | 0 | 2022-02-04 |  | 37 | 2022-02-05 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1143920220130-6Dozer D6 or equal- After Jan 104525.92 | Corbiere and Sons Contracting1143920220130-6Dozer D6 or equal- After Jan 104525.92INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11438 | 20220130-5 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2022-01-30 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in LAKE A | 6 | C130-C151 | Lake A | 0 | 2022-02-04 |  | 37 | 2022-02-05 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1143820220130-5Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1143820220130-5Operator - Principle - After Jan 1012900INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11438 | 20220130-5 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-01-30 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in LAKE A | 6 | C130-C151 | Lake A | 0 | 2022-02-04 |  | 37 | 2022-02-05 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1143820220130-5Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1143820220130-5Operator - Principle - After Jan 1011825INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11438 | 20220130-5 | 53510611 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2022-01-30 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in LAKE A | 6 | C130-C151 | Lake A | 0 | 2022-02-04 |  | 37 | 2022-02-05 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1143820220130-5L.O.A.2420 | Corbiere and Sons Contracting1143820220130-5L.O.A.2420INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11438 | 20220130-5 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 12 |  | 0 | 0 |  |  | 960 | 124.8 | 1084.8 | 2022-01-30 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in LAKE A | 6 | C130-C151 | Lake A | 0 | 2022-02-04 |  | 37 | 2022-02-05 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1143820220130-5Pickup w/ plow and sander12960 | Corbiere and Sons Contracting1143820220130-5Pickup w/ plow and sander12960INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11438 | 20220130-5 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-30 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in LAKE A | 6 | C130-C151 | Lake A | 0 | 2022-02-04 |  | 37 | 2022-02-05 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1143820220130-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1143820220130-5Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11438 | 20220130-5 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-01-30 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in LAKE A | 6 | C130-C151 | Lake A | 0 | 2022-02-04 |  | 37 | 2022-02-05 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1143820220130-5Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1143820220130-5Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11437 | 20220130-4 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 9 | HR |  |  | 0 | 0 | 675 | 87.75 | 762.75 | 2022-01-30 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in MINK | 6 | C244-C247 | Mink Creek | 0 | 2022-02-04 |  | 37 | 2022-02-05 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1143720220130-4Operator - Principle - After Jan 109675 | Corbiere and Sons Contracting1143720220130-4Operator - Principle - After Jan 109675INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11437 | 20220130-4 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-01-30 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in MINK | 6 | C244-C247 | Mink Creek | 0 | 2022-02-04 |  | 37 | 2022-02-05 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1143720220130-4L.O.A.1210 | Corbiere and Sons Contracting1143720220130-4L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11437 | 20220130-4 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-30 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in MINK | 6 | C244-C247 | Mink Creek | 0 | 2022-02-04 |  | 37 | 2022-02-05 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1143720220130-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1143720220130-4Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11437 | 20220130-4 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 8 | Dynamic | 0 | 0 |  |  | 1015.84 | 132.0592 | 1147.8992 | 2022-01-30 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in MINK | 6 | C244-C247 | Mink Creek | 0 | 2022-02-04 |  | 37 | 2022-02-05 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1143720220130-4Grader - Cat 12 to 14 or equal- After Jan 1081015.84 | Corbiere and Sons Contracting1143720220130-4Grader - Cat 12 to 14 or equal- After Jan 1081015.84INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11436 | 20220130-3 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2022-01-30 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Del Lake | 6 | C186-C195 | Del Lake | 0 | 2022-02-04 |  | 37 | 2022-02-05 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1143620220130-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1143620220130-3Operator - Principle - After Jan 1011825INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11436 | 20220130-3 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2022-01-30 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Del Lake | 6 | C186-C195 | Del Lake | 0 | 2022-02-04 |  | 37 | 2022-02-05 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1143620220130-3L.O.A.1210 | Corbiere and Sons Contracting1143620220130-3L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11436 | 20220130-3 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-30 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Del Lake | 6 | C186-C195 | Del Lake | 0 | 2022-02-04 |  | 37 | 2022-02-05 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1143620220130-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1143620220130-3Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11436 | 20220130-3 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 95.24 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-01-30 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Del Lake | 6 | C186-C195 | Del Lake | 0 | 2022-02-04 |  | 37 | 2022-02-05 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1143620220130-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1143620220130-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11434 | 20220129-8 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 0 | 0 | 450 | 58.5 | 508.5 | 2022-01-29 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Dead Horse Creek | 6 | C203-C209 | Dead Horse Creek | 0 | 2022-01-31 |  | 37 | 2022-02-04 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1143420220129-8Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting1143420220129-8Operator - Principle - After Jan 106450INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11434 | 20220129-8 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2022-01-29 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Dead Horse Creek | 6 | C203-C209 | Dead Horse Creek | 0 | 2022-01-31 |  | 37 | 2022-02-04 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1143420220129-8L.O.A.1210 | Corbiere and Sons Contracting1143420220129-8L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11434 | 20220129-8 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 6 |  | 0 | 0 |  |  | 480 | 62.4 | 542.4 | 2022-01-29 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Dead Horse Creek | 6 | C203-C209 | Dead Horse Creek | 0 | 2022-01-31 |  | 37 | 2022-02-04 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1143420220129-8Pickup w/ plow and sander6480 | Corbiere and Sons Contracting1143420220129-8Pickup w/ plow and sander6480INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11433 | 20220129-7 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 5.5 | HR |  |  | 70 | 0 | 385 | 50.05 | 435.05 | 2022-01-29 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Peninsula | 6 | C268-D005 | Peninsula | 0 | 2022-01-31 |  | 37 | 2022-02-05 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1143320220129-7Driver - AZ - After Jan 105.5385 | Corbiere and Sons Contracting1143320220129-7Driver - AZ - After Jan 105.5385INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11433 | 20220129-7 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5.5 | HR |  |  | 0 | 0 | 412.5 | 53.625 | 466.125 | 2022-01-29 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Peninsula | 6 | C268-D005 | Peninsula | 0 | 2022-01-31 |  | 37 | 2022-02-05 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1143320220129-7Operator - Principle - After Jan 105.5412.5 | Corbiere and Sons Contracting1143320220129-7Operator - Principle - After Jan 105.5412.5INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11433 | 20220129-7 | 53510611 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 5.5 | Dynamic | 91.79 | 0 |  |  | 673.145 | 87.5088 | 760.6539 | 2022-01-29 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Peninsula | 6 | C268-D005 | Peninsula | 0 | 2022-01-31 |  | 37 | 2022-02-05 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1143320220129-7Tractor Trailer - 60 Ton- After Jan 105.5673.145 | Corbiere and Sons Contracting1143320220129-7Tractor Trailer - 60 Ton- After Jan 105.5673.145INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11433 | 20220129-7 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 4.5 | Dynamic | 0 | 0 |  |  | 591.66 | 76.9158 | 668.5758 | 2022-01-29 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Peninsula | 6 | C268-D005 | Peninsula | 0 | 2022-01-31 |  | 37 | 2022-02-05 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1143320220129-7Dozer D6 or equal- After Jan 104.5591.66 | Corbiere and Sons Contracting1143320220129-7Dozer D6 or equal- After Jan 104.5591.66INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11416 | 20220129-5 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-01-29 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Neys | 6 | C219-C235 | Neys | 0 | 2022-01-31 |  | 37 | 2022-02-04 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1141620220129-5Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1141620220129-5Operator - Principle - After Jan 1011825INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11416 | 20220129-5 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-01-29 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Neys | 6 | C219-C235 | Neys | 0 | 2022-01-31 |  | 37 | 2022-02-04 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1141620220129-5L.O.A.1210 | Corbiere and Sons Contracting1141620220129-5L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11416 | 20220129-5 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-29 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Neys | 6 | C219-C235 | Neys | 0 | 2022-01-31 |  | 37 | 2022-02-04 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1141620220129-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1141620220129-5Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11416 | 20220129-5 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-01-29 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Neys | 6 | C219-C235 | Neys | 0 | 2022-01-31 |  | 37 | 2022-02-04 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1141620220129-5Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1141620220129-5Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11415 | 20220129-4 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 5.5 | HR |  |  | 70 | 0 | 385 | 50.05 | 435.05 | 2022-01-29 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Mink Creek | 6 | C248 - C256 | Mink Creek | 0 | 2022-01-31 |  | 37 | 2022-02-01 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1141520220129-4Driver - AZ - After Jan 105.5385 | Corbiere and Sons Contracting1141520220129-4Driver - AZ - After Jan 105.5385INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11415 | 20220129-4 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-01-29 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Mink Creek | 6 | C248 - C256 | Mink Creek | 0 | 2022-01-31 |  | 37 | 2022-02-01 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1141520220129-4Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1141520220129-4Operator - Principle - After Jan 1011825INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11415 | 20220129-4 | 53510611 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2022-01-29 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Mink Creek | 6 | C248 - C256 | Mink Creek | 0 | 2022-01-31 |  | 37 | 2022-02-01 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1141520220129-4L.O.A.2420 | Corbiere and Sons Contracting1141520220129-4L.O.A.2420INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11415 | 20220129-4 | 53510611 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 5.5 | Dynamic | 91.79 | 0 |  |  | 673.145 | 87.5088 | 760.6539 | 2022-01-29 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Mink Creek | 6 | C248 - C256 | Mink Creek | 0 | 2022-01-31 |  | 37 | 2022-02-01 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1141520220129-4Tractor Trailer - 60 Ton- After Jan 105.5673.145 | Corbiere and Sons Contracting1141520220129-4Tractor Trailer - 60 Ton- After Jan 105.5673.145INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11415 | 20220129-4 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-29 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Mink Creek | 6 | C248 - C256 | Mink Creek | 0 | 2022-01-31 |  | 37 | 2022-02-01 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1141520220129-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1141520220129-4Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11415 | 20220129-4 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 8 | Dynamic | 0 | 0 |  |  | 1015.84 | 132.0592 | 1147.8992 | 2022-01-29 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Mink Creek | 6 | C248 - C256 | Mink Creek | 0 | 2022-01-31 |  | 37 | 2022-02-01 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1141520220129-4Grader - Cat 12 to 14 or equal- After Jan 1081015.84 | Corbiere and Sons Contracting1141520220129-4Grader - Cat 12 to 14 or equal- After Jan 1081015.84INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11414 | 20220129-3 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-01-29 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Prairie River | 6 | C171-C185 | Prairie River | 0 | 2022-01-31 |  | 37 | 2022-02-01 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1141420220129-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1141420220129-3Operator - Principle - After Jan 1011825INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11414 | 20220129-3 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-01-29 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Prairie River | 6 | C171-C185 | Prairie River | 0 | 2022-01-31 |  | 37 | 2022-02-01 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1141420220129-3L.O.A.1210 | Corbiere and Sons Contracting1141420220129-3L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11414 | 20220129-3 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-29 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Prairie River | 6 | C171-C185 | Prairie River | 0 | 2022-01-31 |  | 37 | 2022-02-01 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1141420220129-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1141420220129-3Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11414 | 20220129-3 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-01-29 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Prairie River | 6 | C171-C185 | Prairie River | 0 | 2022-01-31 |  | 37 | 2022-02-01 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1141420220129-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1141420220129-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11296 | 20220128-7 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2022-01-28 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 | 2022-01-30 |  | 37 | 2022-02-01 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1129620220128-7Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1129620220128-7Operator - Principle - After Jan 1012900INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11296 | 20220128-7 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2022-01-28 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 | 2022-01-30 |  | 37 | 2022-02-01 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1129620220128-7L.O.A.1210 | Corbiere and Sons Contracting1129620220128-7L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11296 | 20220128-7 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 12 |  | 0 | 0 |  |  | 960 | 124.8 | 1084.8 | 2022-01-28 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 | 2022-01-30 |  | 37 | 2022-02-01 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1129620220128-7Pickup w/ plow and sander12960 | Corbiere and Sons Contracting1129620220128-7Pickup w/ plow and sander12960INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11294 | 20220128-5 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-01-28 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Lake A | 6 | C130-C151 | Lake A | 0 | 2022-01-30 |  | 37 | 2022-02-01 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1129420220128-5Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1129420220128-5Operator - Principle - After Jan 1011825INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11294 | 20220128-5 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-01-28 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Lake A | 6 | C130-C151 | Lake A | 0 | 2022-01-30 |  | 37 | 2022-02-01 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1129420220128-5L.O.A.1210 | Corbiere and Sons Contracting1129420220128-5L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11294 | 20220128-5 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-28 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Lake A | 6 | C130-C151 | Lake A | 0 | 2022-01-30 |  | 37 | 2022-02-01 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1129420220128-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1129420220128-5Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11294 | 20220128-5 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-01-28 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Lake A | 6 | C130-C151 | Lake A | 0 | 2022-01-30 |  | 37 | 2022-02-01 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1129420220128-5Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1129420220128-5Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11292 | 20220128-3 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-01-28 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Prairie River | 6 | C171-C185 | Prairie River | 0 | 2022-01-30 |  | 37 | 2022-02-01 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1129220220128-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1129220220128-3Operator - Principle - After Jan 1011825INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11292 | 20220128-3 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-01-28 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Prairie River | 6 | C171-C185 | Prairie River | 0 | 2022-01-30 |  | 37 | 2022-02-01 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1129220220128-3L.O.A.1210 | Corbiere and Sons Contracting1129220220128-3L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11292 | 20220128-3 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-28 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Prairie River | 6 | C171-C185 | Prairie River | 0 | 2022-01-30 |  | 37 | 2022-02-01 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1129220220128-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1129220220128-3Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11292 | 20220128-3 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-01-28 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Prairie River | 6 | C171-C185 | Prairie River | 0 | 2022-01-30 |  | 37 | 2022-02-01 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1129220220128-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1129220220128-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11290 | 20220127-9 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 4 | HR |  |  | 0 | 0 | 300 | 39 | 339 | 2022-01-27 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Little Pic | 6 | C215-C216 | Little Pie River | 0 | 2022-01-30 |  | 37 | 2022-02-01 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1129020220127-9Operator - Principle - After Jan 104300 | Corbiere and Sons Contracting1129020220127-9Operator - Principle - After Jan 104300INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11290 | 20220127-9 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 4 |  | 0 | 0 |  |  | 320 | 41.6 | 361.6 | 2022-01-27 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Little Pic | 6 | C215-C216 | Little Pie River | 0 | 2022-01-30 |  | 37 | 2022-02-01 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1129020220127-9Pickup w/ plow and sander4320 | Corbiere and Sons Contracting1129020220127-9Pickup w/ plow and sander4320INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11289 | 20220127-8 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 4 | HR |  |  | 0 | 0 | 300 | 39 | 339 | 2022-01-27 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Middleton | 6 | C210-C213 | Middleton | 0 | 2022-01-30 |  | 37 | 2022-02-01 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1128920220127-8Operator - Principle - After Jan 104300 | Corbiere and Sons Contracting1128920220127-8Operator - Principle - After Jan 104300INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11289 | 20220127-8 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-01-27 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Middleton | 6 | C210-C213 | Middleton | 0 | 2022-01-30 |  | 37 | 2022-02-01 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1128920220127-8L.O.A.1210 | Corbiere and Sons Contracting1128920220127-8L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11289 | 20220127-8 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 4 |  | 0 | 0 |  |  | 320 | 41.6 | 361.6 | 2022-01-27 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Middleton | 6 | C210-C213 | Middleton | 0 | 2022-01-30 |  | 37 | 2022-02-01 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1128920220127-8Pickup w/ plow and sander4320 | Corbiere and Sons Contracting1128920220127-8Pickup w/ plow and sander4320INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11287 | 20220127-6 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5 | HR |  |  | 0 | 0 | 375 | 48.75 | 423.75 | 2022-01-27 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Santoy | 6 | C158-C170 | Santoy Lake | 0 | 2022-01-30 |  | 37 | 2022-02-01 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1128720220127-6Operator - Principle - After Jan 105375 | Corbiere and Sons Contracting1128720220127-6Operator - Principle - After Jan 105375INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11287 | 20220127-6 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-01-27 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Santoy | 6 | C158-C170 | Santoy Lake | 0 | 2022-01-30 |  | 37 | 2022-02-01 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1128720220127-6L.O.A.1210 | Corbiere and Sons Contracting1128720220127-6L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11287 | 20220127-6 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-27 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Santoy | 6 | C158-C170 | Santoy Lake | 0 | 2022-01-30 |  | 37 | 2022-02-01 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1128720220127-6Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1128720220127-6Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11287 | 20220127-6 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 5 | Dynamic | 0 | 0 |  |  | 657.4 | 85.462 | 742.862 | 2022-01-27 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Santoy | 6 | C158-C170 | Santoy Lake | 0 | 2022-01-30 |  | 37 | 2022-02-01 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1128720220127-6Dozer D6 or equal- After Jan 105657.4 | Corbiere and Sons Contracting1128720220127-6Dozer D6 or equal- After Jan 105657.4INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11286 | 20220127-5 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 0 | 0 | 900 | 117 | 1017 | 2022-01-27 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Lake A | 6 | C130-C151 | Lake A | 0 | 2022-01-30 |  | 37 | 2022-02-01 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1128620220127-5Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1128620220127-5Operator - Principle - After Jan 1012900INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11286 | 20220127-5 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-01-27 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Lake A | 6 | C130-C151 | Lake A | 0 | 2022-01-30 |  | 37 | 2022-02-01 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1128620220127-5L.O.A.1210 | Corbiere and Sons Contracting1128620220127-5L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11286 | 20220127-5 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-27 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Lake A | 6 | C130-C151 | Lake A | 0 | 2022-01-30 |  | 37 | 2022-02-01 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1128620220127-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1128620220127-5Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11286 | 20220127-5 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 9 | Dynamic | 0 | 0 |  |  | 1142.82 | 148.5666 | 1291.3866 | 2022-01-27 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Lake A | 6 | C130-C151 | Lake A | 0 | 2022-01-30 |  | 37 | 2022-02-01 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1128620220127-5Grader - Cat 12 to 14 or equal- After Jan 1091142.82 | Corbiere and Sons Contracting1128620220127-5Grader - Cat 12 to 14 or equal- After Jan 1091142.82INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11284 | 20220127-3-R1 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 0 | 0 | 900 | 117 | 1017 | 2022-01-27 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Del Lake | 6 | C186-C195 | Del Lake | 0 | 2022-01-30 |  | 37 | 2022-01-31 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1128420220127-3-R1Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1128420220127-3-R1Operator - Principle - After Jan 1012900INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11284 | 20220127-3-R1 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-01-27 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Del Lake | 6 | C186-C195 | Del Lake | 0 | 2022-01-30 |  | 37 | 2022-01-31 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1128420220127-3-R1L.O.A.1210 | Corbiere and Sons Contracting1128420220127-3-R1L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11284 | 20220127-3-R1 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-27 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Del Lake | 6 | C186-C195 | Del Lake | 0 | 2022-01-30 |  | 37 | 2022-01-31 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1128420220127-3-R1Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1128420220127-3-R1Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11284 | 20220127-3-R1 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 11 | Dynamic | 0 | 0 |  |  | 1396.78 | 181.5814 | 1578.3614 | 2022-01-27 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Del Lake | 6 | C186-C195 | Del Lake | 0 | 2022-01-30 |  | 37 | 2022-01-31 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1128420220127-3-R1Grader - Cat 12 to 14 or equal- After Jan 10111396.78 | Corbiere and Sons Contracting1128420220127-3-R1Grader - Cat 12 to 14 or equal- After Jan 10111396.78INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11291 | 20220127-10 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 4 | HR |  |  | 0 | 0 | 300 | 39 | 339 | 2022-01-27 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Neys | 6 | C219-C235 | Neys | 0 | 2022-01-30 |  | 37 | 2022-02-01 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1129120220127-10Operator - Principle - After Jan 104300 | Corbiere and Sons Contracting1129120220127-10Operator - Principle - After Jan 104300INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11291 | 20220127-10 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 4 |  | 0 | 0 |  |  | 320 | 41.6 | 361.6 | 2022-01-27 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Neys | 6 | C219-C235 | Neys | 0 | 2022-01-30 |  | 37 | 2022-02-01 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1129120220127-10Pickup w/ plow and sander4320 | Corbiere and Sons Contracting1129120220127-10Pickup w/ plow and sander4320INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11283 | 20220126-7 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 10 | HR |  |  | 70 | 0 | 700 | 91 | 791 | 2022-01-26 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Santoy | 6 | C158-C170 | Santoy Lake | 0 | 2022-01-30 |  | 37 | 2022-01-31 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1128320220126-7Driver - AZ - After Jan 1010700 | Corbiere and Sons Contracting1128320220126-7Driver - AZ - After Jan 1010700INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11283 | 20220126-7 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5 | HR |  |  | 0 | 0 | 375 | 48.75 | 423.75 | 2022-01-26 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Santoy | 6 | C158-C170 | Santoy Lake | 0 | 2022-01-30 |  | 37 | 2022-01-31 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1128320220126-7Operator - Principle - After Jan 105375 | Corbiere and Sons Contracting1128320220126-7Operator - Principle - After Jan 105375INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11283 | 20220126-7 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2022-01-26 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Santoy | 6 | C158-C170 | Santoy Lake | 0 | 2022-01-30 |  | 37 | 2022-01-31 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1128320220126-7L.O.A.1210 | Corbiere and Sons Contracting1128320220126-7L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11283 | 20220126-7 | 53510611 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 10 | Dynamic | 91.79 | 0 |  |  | 1223.9 | 159.107 | 1383.007 | 2022-01-26 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Santoy | 6 | C158-C170 | Santoy Lake | 0 | 2022-01-30 |  | 37 | 2022-01-31 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1128320220126-7Tractor Trailer - 60 Ton- After Jan 10101223.9 | Corbiere and Sons Contracting1128320220126-7Tractor Trailer - 60 Ton- After Jan 10101223.9INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11283 | 20220126-7 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 4 | Dynamic | 98.61 | 0 |  |  | 525.92 | 68.3696 | 594.2896 | 2022-01-26 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Santoy | 6 | C158-C170 | Santoy Lake | 0 | 2022-01-30 |  | 37 | 2022-01-31 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1128320220126-7Dozer D6 or equal- After Jan 104525.92 | Corbiere and Sons Contracting1128320220126-7Dozer D6 or equal- After Jan 104525.92INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11282 | 20220126-6 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 0 | 0 | 450 | 58.5 | 508.5 | 2022-01-26 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2022-01-30 |  | 37 | 2022-01-31 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1128220220126-6Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting1128220220126-6Operator - Principle - After Jan 106450INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11282 | 20220126-6 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 6 |  | 0 | 0 |  |  | 480 | 62.4 | 542.4 | 2022-01-26 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Dead Horse | 6 | C203-C209 | Dead Horse Creek | 0 | 2022-01-30 |  | 37 | 2022-01-31 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1128220220126-6Pickup w/ plow and sander6480 | Corbiere and Sons Contracting1128220220126-6Pickup w/ plow and sander6480INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11281 | 20220126-5 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 0 | 0 | 450 | 58.5 | 508.5 | 2022-01-26 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Lake A | 6 | C130-C151 | Lake A | 0 | 2022-01-30 |  | 37 | 2022-01-31 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1128120220126-5Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting1128120220126-5Operator - Principle - After Jan 106450INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11281 | 20220126-5 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-01-26 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Lake A | 6 | C130-C151 | Lake A | 0 | 2022-01-30 |  | 37 | 2022-01-31 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1128120220126-5L.O.A.1210 | Corbiere and Sons Contracting1128120220126-5L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11281 | 20220126-5 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-26 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Lake A | 6 | C130-C151 | Lake A | 0 | 2022-01-30 |  | 37 | 2022-01-31 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1128120220126-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1128120220126-5Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11281 | 20220126-5 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 6 | Dynamic | 0 | 0 |  |  | 761.88 | 99.0444 | 860.9244 | 2022-01-26 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Lake A | 6 | C130-C151 | Lake A | 0 | 2022-01-30 |  | 37 | 2022-01-31 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1128120220126-5Grader - Cat 12 to 14 or equal- After Jan 106761.88 | Corbiere and Sons Contracting1128120220126-5Grader - Cat 12 to 14 or equal- After Jan 106761.88INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11279 | 20220126-3 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 75 | 0 | 450 | 58.5 | 508.5 | 2022-01-26 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Del Lake | 6 | C186-C195 | Del Lake | 0 |  |  | 37 | 2022-01-31 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1127920220126-3Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting1127920220126-3Operator - Principle - After Jan 106450INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11279 | 20220126-3 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-01-26 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Del Lake | 6 | C186-C195 | Del Lake | 0 |  |  | 37 | 2022-01-31 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1127920220126-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1127920220126-3Operator - Principle - After Jan 1011825INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11279 | 20220126-3 | 53510611 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2022-01-26 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Del Lake | 6 | C186-C195 | Del Lake | 0 |  |  | 37 | 2022-01-31 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1127920220126-3L.O.A.2420 | Corbiere and Sons Contracting1127920220126-3L.O.A.2420INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11279 | 20220126-3 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 6 |  | 0 | 0 |  |  | 480 | 62.4 | 542.4 | 2022-01-26 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Del Lake | 6 | C186-C195 | Del Lake | 0 |  |  | 37 | 2022-01-31 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1127920220126-3Pickup w/ plow and sander6480 | Corbiere and Sons Contracting1127920220126-3Pickup w/ plow and sander6480INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11279 | 20220126-3 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-26 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Del Lake | 6 | C186-C195 | Del Lake | 0 |  |  | 37 | 2022-01-31 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1127920220126-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1127920220126-3Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11279 | 20220126-3 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-01-26 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Del Lake | 6 | C186-C195 | Del Lake | 0 |  |  | 37 | 2022-01-31 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1127920220126-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1127920220126-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11277 | 20220125-5 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 6 | HR |  |  | 70 | 0 | 420 | 54.6 | 474.6 | 2022-01-25 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities onLake A | 6 | C130-C151 | Lake A | 0 | 2022-01-30 |  | 37 | 2022-01-31 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1127720220125-5Operator - Intermdiate - After Jan 106420 | Corbiere and Sons Contracting1127720220125-5Operator - Intermdiate - After Jan 106420INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11277 | 20220125-5 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-01-25 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities onLake A | 6 | C130-C151 | Lake A | 0 | 2022-01-30 |  | 37 | 2022-01-31 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1127720220125-5Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1127720220125-5Operator - Principle - After Jan 1011825INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11277 | 20220125-5 | 53510611 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2022-01-25 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities onLake A | 6 | C130-C151 | Lake A | 0 | 2022-01-30 |  | 37 | 2022-01-31 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1127720220125-5L.O.A.2420 | Corbiere and Sons Contracting1127720220125-5L.O.A.2420INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11277 | 20220125-5 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 6 |  | 0 | 0 |  |  | 480 | 62.4 | 542.4 | 2022-01-25 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities onLake A | 6 | C130-C151 | Lake A | 0 | 2022-01-30 |  | 37 | 2022-01-31 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1127720220125-5Pickup w/ plow and sander6480 | Corbiere and Sons Contracting1127720220125-5Pickup w/ plow and sander6480INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11277 | 20220125-5 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-25 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities onLake A | 6 | C130-C151 | Lake A | 0 | 2022-01-30 |  | 37 | 2022-01-31 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1127720220125-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1127720220125-5Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11277 | 20220125-5 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-01-25 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities onLake A | 6 | C130-C151 | Lake A | 0 | 2022-01-30 |  | 37 | 2022-01-31 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1127720220125-5Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1127720220125-5Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11275 | 20220125-3 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-01-25 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Del Lake | 6 | C186-C195 | Del Lake | 0 | 2022-01-30 |  | 37 | 2022-01-31 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1127520220125-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1127520220125-3Operator - Principle - After Jan 1011825INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11275 | 20220125-3 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-01-25 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Del Lake | 6 | C186-C195 | Del Lake | 0 | 2022-01-30 |  | 37 | 2022-01-31 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1127520220125-3L.O.A.1210 | Corbiere and Sons Contracting1127520220125-3L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11275 | 20220125-3 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-25 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Del Lake | 6 | C186-C195 | Del Lake | 0 | 2022-01-30 |  | 37 | 2022-01-31 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1127520220125-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1127520220125-3Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11275 | 20220125-3 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 8 | Dynamic | 0 | 0 |  |  | 1015.84 | 132.0592 | 1147.8992 | 2022-01-25 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities in Del Lake | 6 | C186-C195 | Del Lake | 0 | 2022-01-30 |  | 37 | 2022-01-31 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1127520220125-3Grader - Cat 12 to 14 or equal- After Jan 1081015.84 | Corbiere and Sons Contracting1127520220125-3Grader - Cat 12 to 14 or equal- After Jan 1081015.84INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11274 | 20220124-8 | 53510611 | Access | 0 | 3rd Party Charges | 1 | 4972.8 | Unit |  |  |  |  | 4972.8 | 646.464 | 5619.264 | 2022-01-24 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Charges for Sand used | 6 | C129-D005 |  | 0 | 2022-01-30 |  | 37 | 2022-01-31 | 18520 | Sand |  |  |  | Harold Furlong | 06 | Corbiere and Sons Contracting1127420220124-83rd Party Charges4972.84972.8 | Corbiere and Sons Contracting1127420220124-83rd Party Charges4972.84972.8INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11274 | 20220124-8 | 53510611 | Access | 0 | 3rd Party Charges | 1 | 3824.9 | Unit |  |  |  |  | 3824.9 | 497.237 | 4322.137 | 2022-01-24 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Charges for Sand used | 6 | C129-D005 |  | 0 | 2022-01-30 |  | 37 | 2022-01-31 | 414-413 | Sand |  |  |  | Harold Furlong | 06 | Corbiere and Sons Contracting1127420220124-83rd Party Charges3824.93824.9 | Corbiere and Sons Contracting1127420220124-83rd Party Charges3824.93824.9INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11272 | 20220124-6 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5.5 | HR |  |  | 0 | 0 | 412.5 | 53.625 | 466.125 | 2022-01-24 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities onPeninsula | 6 | C268-D005 | Peninsula | 0 | 2022-01-30 |  | 37 | 2022-01-31 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1127220220124-6Operator - Principle - After Jan 105.5412.5 | Corbiere and Sons Contracting1127220220124-6Operator - Principle - After Jan 105.5412.5INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11272 | 20220124-6 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-01-24 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities onPeninsula | 6 | C268-D005 | Peninsula | 0 | 2022-01-30 |  | 37 | 2022-01-31 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1127220220124-6L.O.A.1210 | Corbiere and Sons Contracting1127220220124-6L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11272 | 20220124-6 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-24 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities onPeninsula | 6 | C268-D005 | Peninsula | 0 | 2022-01-30 |  | 37 | 2022-01-31 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1127220220124-6Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1127220220124-6Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11272 | 20220124-6 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 3.5 | Dynamic | 98.61 | 0 |  |  | 460.18 | 59.8234 | 520.0034 | 2022-01-24 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities onPeninsula | 6 | C268-D005 | Peninsula | 0 | 2022-01-30 |  | 37 | 2022-01-31 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1127220220124-6Dozer D6 or equal- After Jan 103.5460.18 | Corbiere and Sons Contracting1127220220124-6Dozer D6 or equal- After Jan 103.5460.18INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11271 | 20220124-5 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 5.5 | HR |  |  | 0 | 0 | 385 | 50.05 | 435.05 | 2022-01-24 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Lake A | 6 | C130-C151 | Lake A | 0 | 2022-01-30 |  | 37 | 2022-01-31 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1127120220124-5Operator - Intermdiate - After Jan 105.5385 | Corbiere and Sons Contracting1127120220124-5Operator - Intermdiate - After Jan 105.5385INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11271 | 20220124-5 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-01-24 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Lake A | 6 | C130-C151 | Lake A | 0 | 2022-01-30 |  | 37 | 2022-01-31 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1127120220124-5Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1127120220124-5Operator - Principle - After Jan 1011825INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11271 | 20220124-5 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-01-24 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Lake A | 6 | C130-C151 | Lake A | 0 | 2022-01-30 |  | 37 | 2022-01-31 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1127120220124-5L.O.A.1210 | Corbiere and Sons Contracting1127120220124-5L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11271 | 20220124-5 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 5.5 |  | 0 | 0 |  |  | 440 | 57.2 | 497.2 | 2022-01-24 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Lake A | 6 | C130-C151 | Lake A | 0 | 2022-01-30 |  | 37 | 2022-01-31 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1127120220124-5Pickup w/ plow and sander5.5440 | Corbiere and Sons Contracting1127120220124-5Pickup w/ plow and sander5.5440INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11271 | 20220124-5 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-24 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Lake A | 6 | C130-C151 | Lake A | 0 | 2022-01-30 |  | 37 | 2022-01-31 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1127120220124-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1127120220124-5Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11271 | 20220124-5 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-01-24 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Lake A | 6 | C130-C151 | Lake A | 0 | 2022-01-30 |  | 37 | 2022-01-31 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1127120220124-5Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1127120220124-5Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11268 | 20220123-8 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 2 | HR |  |  | 0 | 0 | 140 | 18.2 | 158.2 | 2022-01-23 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C219-C236 | Neys | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1126820220123-8Operator - Intermdiate - After Jan 102140 | Corbiere and Sons Contracting1126820220123-8Operator - Intermdiate - After Jan 102140INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11268 | 20220123-8 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 2 |  | 0 | 0 |  |  | 160 | 20.8 | 180.8 | 2022-01-23 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C219-C236 | Neys | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1126820220123-8Pickup w/ plow and sander2160 | Corbiere and Sons Contracting1126820220123-8Pickup w/ plow and sander2160INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11267 | 20220123-7 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 3 | HR |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-01-23 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1126720220123-7Operator - Intermdiate - After Jan 103210 | Corbiere and Sons Contracting1126720220123-7Operator - Intermdiate - After Jan 103210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11267 | 20220123-7 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 3 |  | 0 | 0 |  |  | 240 | 31.2 | 271.2 | 2022-01-23 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1126720220123-7Pickup w/ plow and sander3240 | Corbiere and Sons Contracting1126720220123-7Pickup w/ plow and sander3240INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11266 | 20220123-6 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 3 | HR |  |  | 70 | 0 | 210 | 27.3 | 237.3 | 2022-01-23 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C185-C195 | Del Lake West | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1126620220123-6Operator - Intermdiate - After Jan 103210 | Corbiere and Sons Contracting1126620220123-6Operator - Intermdiate - After Jan 103210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11266 | 20220123-6 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 3 |  | 0 | 0 |  |  | 240 | 31.2 | 271.2 | 2022-01-23 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C185-C195 | Del Lake West | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1126620220123-6Pickup w/ plow and sander3240 | Corbiere and Sons Contracting1126620220123-6Pickup w/ plow and sander3240INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11265 | 20220123-5 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 3 | HR |  |  | 70 | 0 | 210 | 27.3 | 237.3 | 2022-01-23 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Lake A | 6 | C130-C151 | Lake A | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1126520220123-5Operator - Intermdiate - After Jan 103210 | Corbiere and Sons Contracting1126520220123-5Operator - Intermdiate - After Jan 103210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11265 | 20220123-5 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2022-01-23 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Lake A | 6 | C130-C151 | Lake A | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1126520220123-5Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1126520220123-5Operator - Principle - After Jan 1011825INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11265 | 20220123-5 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-01-23 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Lake A | 6 | C130-C151 | Lake A | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1126520220123-5Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1126520220123-5Operator - Principle - After Jan 1011825INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11265 | 20220123-5 | 53510611 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2022-01-23 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Lake A | 6 | C130-C151 | Lake A | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1126520220123-5L.O.A.3630 | Corbiere and Sons Contracting1126520220123-5L.O.A.3630INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11265 | 20220123-5 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 3 |  | 0 | 0 |  |  | 240 | 31.2 | 271.2 | 2022-01-23 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Lake A | 6 | C130-C151 | Lake A | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1126520220123-5Pickup w/ plow and sander3240 | Corbiere and Sons Contracting1126520220123-5Pickup w/ plow and sander3240INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11265 | 20220123-5 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-23 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Lake A | 6 | C130-C151 | Lake A | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1126520220123-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1126520220123-5Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11265 | 20220123-5 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-23 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Lake A | 6 | C130-C151 | Lake A | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1126520220123-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1126520220123-5Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11265 | 20220123-5 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-01-23 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Lake A | 6 | C130-C151 | Lake A | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1126520220123-5Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1126520220123-5Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11265 | 20220123-5 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10 | Dynamic | 98.61 | 0 |  |  | 1314.8 | 170.924 | 1485.724 | 2022-01-23 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Lake A | 6 | C130-C151 | Lake A | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1126520220123-5Dozer D6 or equal- After Jan 10101314.8 | Corbiere and Sons Contracting1126520220123-5Dozer D6 or equal- After Jan 10101314.8INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11260 | 20220122-9 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 2 | HR |  |  | 0 | 0 | 140 | 18.2 | 158.2 | 2022-01-22 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1126020220122-9Operator - Intermdiate - After Jan 102140 | Corbiere and Sons Contracting1126020220122-9Operator - Intermdiate - After Jan 102140INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11260 | 20220122-9 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 2 |  | 0 | 0 |  |  | 160 | 20.8 | 180.8 | 2022-01-22 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1126020220122-9Pickup w/ plow and sander2160 | Corbiere and Sons Contracting1126020220122-9Pickup w/ plow and sander2160INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11259 | 20220122-8 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 2 | HR |  |  | 0 | 0 | 140 | 18.2 | 158.2 | 2022-01-22 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C210-C213 | Middleton | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1125920220122-8Operator - Intermdiate - After Jan 102140 | Corbiere and Sons Contracting1125920220122-8Operator - Intermdiate - After Jan 102140INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11259 | 20220122-8 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 2 |  | 0 | 0 |  |  | 160 | 20.8 | 180.8 | 2022-01-22 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C210-C213 | Middleton | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1125920220122-8Pickup w/ plow and sander2160 | Corbiere and Sons Contracting1125920220122-8Pickup w/ plow and sander2160INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11258 | 20220122-7 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 2 | HR |  |  | 0 | 0 | 140 | 18.2 | 158.2 | 2022-01-22 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C203-C209 | Dead Horse Creek | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1125820220122-7Operator - Intermdiate - After Jan 102140 | Corbiere and Sons Contracting1125820220122-7Operator - Intermdiate - After Jan 102140INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11258 | 20220122-7 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2022-01-22 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C203-C209 | Dead Horse Creek | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1125820220122-7L.O.A.1210 | Corbiere and Sons Contracting1125820220122-7L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11258 | 20220122-7 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 2 |  | 0 | 0 |  |  | 160 | 20.8 | 180.8 | 2022-01-22 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C203-C209 | Dead Horse Creek | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1125820220122-7Pickup w/ plow and sander2160 | Corbiere and Sons Contracting1125820220122-7Pickup w/ plow and sander2160INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11257 | 20220122-6 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 7 | HR |  |  | 0 | 0 | 525 | 68.25 | 593.25 | 2022-01-22 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C186-C195 | Del Lake | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1125720220122-6Operator - Principle - After Jan 107525 | Corbiere and Sons Contracting1125720220122-6Operator - Principle - After Jan 107525INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11257 | 20220122-6 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-01-22 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C186-C195 | Del Lake | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1125720220122-6L.O.A.1210 | Corbiere and Sons Contracting1125720220122-6L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11257 | 20220122-6 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-22 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C186-C195 | Del Lake | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1125720220122-6Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1125720220122-6Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11257 | 20220122-6 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 5 | Dynamic | 0 | 0 |  |  | 657.4 | 85.462 | 742.862 | 2022-01-22 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C186-C195 | Del Lake | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1125720220122-6Dozer D6 or equal- After Jan 105657.4 | Corbiere and Sons Contracting1125720220122-6Dozer D6 or equal- After Jan 105657.4INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11256 | 20220122-5 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 0 | 0 | 900 | 117 | 1017 | 2022-01-22 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Lake A | 6 | C130-C151 | Lake A | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1125620220122-5Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1125620220122-5Operator - Principle - After Jan 1012900INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11256 | 20220122-5 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-01-22 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Lake A | 6 | C130-C151 | Lake A | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1125620220122-5L.O.A.1210 | Corbiere and Sons Contracting1125620220122-5L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11256 | 20220122-5 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-22 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Lake A | 6 | C130-C151 | Lake A | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1125620220122-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1125620220122-5Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11256 | 20220122-5 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 9 | Dynamic | 0 | 0 |  |  | 1142.82 | 148.5666 | 1291.3866 | 2022-01-22 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Lake A | 6 | C130-C151 | Lake A | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1125620220122-5Grader - Cat 12 to 14 or equal- After Jan 1091142.82 | Corbiere and Sons Contracting1125620220122-5Grader - Cat 12 to 14 or equal- After Jan 1091142.82INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11261 | 20220122-10 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 3 | HR |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-01-22 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C236-C243 | Culvert Creek | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1126120220122-10Operator - Intermdiate - After Jan 103210 | Corbiere and Sons Contracting1126120220122-10Operator - Intermdiate - After Jan 103210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11261 | 20220122-10 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 3 |  | 0 | 0 |  |  | 240 | 31.2 | 271.2 | 2022-01-22 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C236-C243 | Culvert Creek | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1126120220122-10Pickup w/ plow and sander3240 | Corbiere and Sons Contracting1126120220122-10Pickup w/ plow and sander3240INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11252 | 20220121-6 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 4 | HR |  |  | 0 | 0 | 280 | 36.4 | 316.4 | 2022-01-21 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C215-C216 | Little Pic River | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1125220220121-6Operator - Intermdiate - After Jan 104280 | Corbiere and Sons Contracting1125220220121-6Operator - Intermdiate - After Jan 104280INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11252 | 20220121-6 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 4 |  | 0 | 0 |  |  | 320 | 41.6 | 361.6 | 2022-01-21 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C215-C216 | Little Pic River | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1125220220121-6Pickup w/ plow and sander4320 | Corbiere and Sons Contracting1125220220121-6Pickup w/ plow and sander4320INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11251 | 20220121-5 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 4 | HR |  |  | 0 | 0 | 280 | 36.4 | 316.4 | 2022-01-21 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Lake A | 6 | C130-C151 | Lake A | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1125120220121-5Operator - Intermdiate - After Jan 104280 | Corbiere and Sons Contracting1125120220121-5Operator - Intermdiate - After Jan 104280INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11251 | 20220121-5 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-01-21 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Lake A | 6 | C130-C151 | Lake A | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1125120220121-5Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1125120220121-5Operator - Principle - After Jan 1011825INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11251 | 20220121-5 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-01-21 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Lake A | 6 | C130-C151 | Lake A | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1125120220121-5L.O.A.1210 | Corbiere and Sons Contracting1125120220121-5L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11251 | 20220121-5 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 4 |  | 0 | 0 |  |  | 320 | 41.6 | 361.6 | 2022-01-21 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Lake A | 6 | C130-C151 | Lake A | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1125120220121-5Pickup w/ plow and sander4320 | Corbiere and Sons Contracting1125120220121-5Pickup w/ plow and sander4320INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11251 | 20220121-5 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-21 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Lake A | 6 | C130-C151 | Lake A | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1125120220121-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1125120220121-5Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11251 | 20220121-5 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-01-21 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Lake A | 6 | C130-C151 | Lake A | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1125120220121-5Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1125120220121-5Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11248 | 20220120-8 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 4 | HR |  |  | 70 | 0 | 280 | 36.4 | 316.4 | 2022-01-20 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C244-C247 | Mink Creek | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1124820220120-8Driver - AZ - After Jan 104280 | Corbiere and Sons Contracting1124820220120-8Driver - AZ - After Jan 104280INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11248 | 20220120-8 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2022-01-20 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C244-C247 | Mink Creek | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1124820220120-8Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1124820220120-8Operator - Principle - After Jan 1011825INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11248 | 20220120-8 | 53510611 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2022-01-20 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C244-C247 | Mink Creek | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1124820220120-8L.O.A.2420 | Corbiere and Sons Contracting1124820220120-8L.O.A.2420INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11248 | 20220120-8 | 53510611 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 4 | Dynamic | 91.79 | 0 |  |  | 489.56 | 63.6428 | 553.2028 | 2022-01-20 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C244-C247 | Mink Creek | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1124820220120-8Tractor Trailer - 60 Ton- After Jan 104489.56 | Corbiere and Sons Contracting1124820220120-8Tractor Trailer - 60 Ton- After Jan 104489.56INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11248 | 20220120-8 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-20 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C244-C247 | Mink Creek | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1124820220120-8Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1124820220120-8Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11248 | 20220120-8 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 8 | Dynamic | 98.61 | 0 |  |  | 1051.84 | 136.7392 | 1188.5792 | 2022-01-20 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C244-C247 | Mink Creek | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1124820220120-8Dozer D6 or equal- After Jan 1081051.84 | Corbiere and Sons Contracting1124820220120-8Dozer D6 or equal- After Jan 1081051.84INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11247 | 20220120-7 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 3 | HR |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-01-20 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 | 2021-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1124720220120-7Operator - Intermdiate - After Jan 103210 | Corbiere and Sons Contracting1124720220120-7Operator - Intermdiate - After Jan 103210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11247 | 20220120-7 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 3 |  | 0 | 0 |  |  | 240 | 31.2 | 271.2 | 2022-01-20 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 | 2021-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1124720220120-7Pickup w/ plow and sander3240 | Corbiere and Sons Contracting1124720220120-7Pickup w/ plow and sander3240INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11245 | 20220120-5 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 3 | HR |  |  | 70 | 0 | 210 | 27.3 | 237.3 | 2022-01-20 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1124520220120-5Operator - Intermdiate - After Jan 103210 | Corbiere and Sons Contracting1124520220120-5Operator - Intermdiate - After Jan 103210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11245 | 20220120-5 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2022-01-20 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1124520220120-5Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1124520220120-5Operator - Principle - After Jan 1011825INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11245 | 20220120-5 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2022-01-20 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1124520220120-5L.O.A.1210 | Corbiere and Sons Contracting1124520220120-5L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11245 | 20220120-5 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 3 |  | 0 | 0 |  |  | 240 | 31.2 | 271.2 | 2022-01-20 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1124520220120-5Pickup w/ plow and sander3240 | Corbiere and Sons Contracting1124520220120-5Pickup w/ plow and sander3240INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11245 | 20220120-5 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-20 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1124520220120-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1124520220120-5Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11245 | 20220120-5 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 95.24 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-01-20 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1124520220120-5Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1124520220120-5Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11241 | 20220119-9 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 2.5 | HR |  |  | 0 | 0 | 175 | 22.75 | 197.75 | 2022-01-19 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C203-C209 | Dead Horse Creek | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1124120220119-9Operator - Intermdiate - After Jan 102.5175 | Corbiere and Sons Contracting1124120220119-9Operator - Intermdiate - After Jan 102.5175INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11241 | 20220119-9 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 2.5 |  | 0 | 0 |  |  | 200 | 26 | 226 | 2022-01-19 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C203-C209 | Dead Horse Creek | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1124120220119-9Pickup w/ plow and sander2.5200 | Corbiere and Sons Contracting1124120220119-9Pickup w/ plow and sander2.5200INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11240 | 20220119-8 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 2.5 | HR |  |  | 0 | 0 | 175 | 22.75 | 197.75 | 2022-01-19 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1124020220119-8Operator - Intermdiate - After Jan 102.5175 | Corbiere and Sons Contracting1124020220119-8Operator - Intermdiate - After Jan 102.5175INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11240 | 20220119-8 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 2.5 |  | 0 | 0 |  |  | 200 | 26 | 226 | 2022-01-19 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1124020220119-8Pickup w/ plow and sander2.5200 | Corbiere and Sons Contracting1124020220119-8Pickup w/ plow and sander2.5200INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11239 | 20220119-7 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 2.5 | HR |  |  | 0 | 0 | 175 | 22.75 | 197.75 | 2022-01-19 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C186-C195 | Del Lake West | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1123920220119-7Operator - Intermdiate - After Jan 102.5175 | Corbiere and Sons Contracting1123920220119-7Operator - Intermdiate - After Jan 102.5175INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11239 | 20220119-7 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 2.5 |  | 0 | 0 |  |  | 200 | 26 | 226 | 2022-01-19 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C186-C195 | Del Lake West | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1123920220119-7Pickup w/ plow and sander2.5200 | Corbiere and Sons Contracting1123920220119-7Pickup w/ plow and sander2.5200INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11238 | 20220119-6 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 2.5 | HR |  |  | 70 | 0 | 175 | 22.75 | 197.75 | 2022-01-19 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1123820220119-6Operator - Intermdiate - After Jan 102.5175 | Corbiere and Sons Contracting1123820220119-6Operator - Intermdiate - After Jan 102.5175INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11238 | 20220119-6 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2022-01-19 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1123820220119-6L.O.A.1210 | Corbiere and Sons Contracting1123820220119-6L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11238 | 20220119-6 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 2.5 |  | 0 | 0 |  |  | 200 | 26 | 226 | 2022-01-19 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1123820220119-6Pickup w/ plow and sander2.5200 | Corbiere and Sons Contracting1123820220119-6Pickup w/ plow and sander2.5200INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11242 | 20220119-10 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 2.5 | HR |  |  | 0 | 0 | 175 | 22.75 | 197.75 | 2022-01-19 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1124220220119-10Operator - Intermdiate - After Jan 102.5175 | Corbiere and Sons Contracting1124220220119-10Operator - Intermdiate - After Jan 102.5175INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11242 | 20220119-10 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 2.5 |  | 0 | 0 |  |  | 200 | 26 | 226 | 2022-01-19 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1124220220119-10Pickup w/ plow and sander2.5200 | Corbiere and Sons Contracting1124220220119-10Pickup w/ plow and sander2.5200INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11230 | 20220117-9 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 3 | HR |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-01-17 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C186-C195 | Del Lake | 0 | 2022-01-28 |  | 37 | 2022-01-31 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1123020220117-9Operator - Intermdiate - After Jan 103210 | Corbiere and Sons Contracting1123020220117-9Operator - Intermdiate - After Jan 103210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11230 | 20220117-9 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 3 |  | 0 | 0 |  |  | 240 | 31.2 | 271.2 | 2022-01-17 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C186-C195 | Del Lake | 0 | 2022-01-28 |  | 37 | 2022-01-31 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1123020220117-9Pickup w/ plow and sander3240 | Corbiere and Sons Contracting1123020220117-9Pickup w/ plow and sander3240INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11229 | 20220117-8 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 3 | HR |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-01-17 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C203-C209 | Dead Horse Creek | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1122920220117-8Operator - Intermdiate - After Jan 103210 | Corbiere and Sons Contracting1122920220117-8Operator - Intermdiate - After Jan 103210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11229 | 20220117-8 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 3 |  | 0 | 0 |  |  | 240 | 31.2 | 271.2 | 2022-01-17 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C203-C209 | Dead Horse Creek | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1122920220117-8Pickup w/ plow and sander3240 | Corbiere and Sons Contracting1122920220117-8Pickup w/ plow and sander3240INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11228 | 20220117-7 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 2 | HR |  |  | 0 | 0 | 140 | 18.2 | 158.2 | 2022-01-17 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C210-C213 | Middleton | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1122820220117-7Operator - Intermdiate - After Jan 102140 | Corbiere and Sons Contracting1122820220117-7Operator - Intermdiate - After Jan 102140INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11228 | 20220117-7 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-01-17 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C210-C213 | Middleton | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1122820220117-7L.O.A.1210 | Corbiere and Sons Contracting1122820220117-7L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11228 | 20220117-7 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 2 |  | 0 | 0 |  |  | 160 | 20.8 | 180.8 | 2022-01-17 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C210-C213 | Middleton | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1122820220117-7Pickup w/ plow and sander2160 | Corbiere and Sons Contracting1122820220117-7Pickup w/ plow and sander2160INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11227 | 20220117-6 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-01-17 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1122720220117-6Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1122720220117-6Operator - Principle - After Jan 1011825INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11227 | 20220117-6 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-17 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1122720220117-6Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1122720220117-6Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11227 | 20220117-6 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10 | Dynamic | 0 | 0 |  |  | 1314.8 | 170.924 | 1485.724 | 2022-01-17 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1122720220117-6Dozer D6 or equal- After Jan 10101314.8 | Corbiere and Sons Contracting1122720220117-6Dozer D6 or equal- After Jan 10101314.8INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11231 | 20220117-10 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 3 | HR |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-01-17 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1123120220117-10Operator - Intermdiate - After Jan 103210 | Corbiere and Sons Contracting1123120220117-10Operator - Intermdiate - After Jan 103210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11231 | 20220117-10 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 3 |  | 0 | 0 |  |  | 240 | 31.2 | 271.2 | 2022-01-17 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1123120220117-10Pickup w/ plow and sander3240 | Corbiere and Sons Contracting1123120220117-10Pickup w/ plow and sander3240INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11221 | 20220116-8 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 4 | HR |  |  | 0 | 0 | 280 | 36.4 | 316.4 | 2022-01-16 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C203-C209 | Dead Horse Creek | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1122120220116-8Operator - Intermdiate - After Jan 104280 | Corbiere and Sons Contracting1122120220116-8Operator - Intermdiate - After Jan 104280INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11221 | 20220116-8 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 4 |  | 0 | 0 |  |  | 320 | 41.6 | 361.6 | 2022-01-16 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C203-C209 | Dead Horse Creek | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1122120220116-8Pickup w/ plow and sander4320 | Corbiere and Sons Contracting1122120220116-8Pickup w/ plow and sander4320INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11219 | 20220116-6 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 0 | 0 | 900 | 117 | 1017 | 2022-01-16 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1121920220116-6Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1121920220116-6Operator - Principle - After Jan 1012900INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11219 | 20220116-6 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-16 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1121920220116-6Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1121920220116-6Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11219 | 20220116-6 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2022-01-16 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1121920220116-6Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting1121920220116-6Dozer D6 or equal- After Jan 10111446.28INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11223 | 20220116-10 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 11 | HR |  |  | 70 | 0 | 770 | 100.1 | 870.1 | 2022-01-16 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C129-D005 | WF6 | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1122320220116-10Driver - AZ - After Jan 1011770 | Corbiere and Sons Contracting1122320220116-10Driver - AZ - After Jan 1011770INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11223 | 20220116-10 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2022-01-16 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C129-D005 | WF6 | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1122320220116-10L.O.A.1210 | Corbiere and Sons Contracting1122320220116-10L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11223 | 20220116-10 | 53510611 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 11 | Dynamic | 91.79 | 0 |  |  | 1346.29 | 175.0177 | 1521.3077 | 2022-01-16 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C129-D005 | WF6 | 0 | 2022-01-28 |  | 36 | 2022-01-29 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1122320220116-10Tractor Trailer - 60 Ton- After Jan 10111346.29 | Corbiere and Sons Contracting1122320220116-10Tractor Trailer - 60 Ton- After Jan 10111346.29INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11172 | 20220115-8 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 5.5 | HR |  |  | 70 | 0 | 385 | 50.05 | 435.05 | 2022-01-15 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C186-C195 | Del Lake | 0 | 2022-01-27 |  | 36 | 2022-01-27 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1117220220115-8Operator - Intermdiate - After Jan 105.5385 | Corbiere and Sons Contracting1117220220115-8Operator - Intermdiate - After Jan 105.5385INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11172 | 20220115-8 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2022-01-15 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C186-C195 | Del Lake | 0 | 2022-01-27 |  | 36 | 2022-01-27 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1117220220115-8L.O.A.1210 | Corbiere and Sons Contracting1117220220115-8L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11172 | 20220115-8 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 5.5 |  | 0 | 0 |  |  | 440 | 57.2 | 497.2 | 2022-01-15 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C186-C195 | Del Lake | 0 | 2022-01-27 |  | 36 | 2022-01-27 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1117220220115-8Pickup w/ plow and sander5.5440 | Corbiere and Sons Contracting1117220220115-8Pickup w/ plow and sander5.5440INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11170 | 20220115-6 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 3 | HR |  |  | 75 | 0 | 225 | 29.25 | 254.25 | 2022-01-15 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C129-C151 | Lake A | 0 | 2022-01-27 |  | 36 | 2022-01-27 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1117020220115-6Operator - Principle - After Jan 103225 | Corbiere and Sons Contracting1117020220115-6Operator - Principle - After Jan 103225INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11170 | 20220115-6 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 3 | Dynamic | 98.61 | 0 |  |  | 394.44 | 51.2772 | 445.7172 | 2022-01-15 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C129-C151 | Lake A | 0 | 2022-01-27 |  | 36 | 2022-01-27 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1117020220115-6Dozer D6 or equal- After Jan 103394.44 | Corbiere and Sons Contracting1117020220115-6Dozer D6 or equal- After Jan 103394.44INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11169 | 20220115-5 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 5.5 | HR |  |  | 0 | 0 | 385 | 50.05 | 435.05 | 2022-01-15 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-01-27 |  | 36 | 2022-01-27 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1116920220115-5Operator - Intermdiate - After Jan 105.5385 | Corbiere and Sons Contracting1116920220115-5Operator - Intermdiate - After Jan 105.5385INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11169 | 20220115-5 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 5.5 |  | 0 | 0 |  |  | 440 | 57.2 | 497.2 | 2022-01-15 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-01-27 |  | 36 | 2022-01-27 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1116920220115-5Pickup w/ plow and sander5.5440 | Corbiere and Sons Contracting1116920220115-5Pickup w/ plow and sander5.5440INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11166 | 20220114-8 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 3 | HR |  |  | 70 | 0 | 210 | 27.3 | 237.3 | 2022-01-14 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C129-C151 | Lake A | 0 | 2022-01-27 |  | 36 | 2022-01-27 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1116620220114-8Driver - AZ - After Jan 103210 | Corbiere and Sons Contracting1116620220114-8Driver - AZ - After Jan 103210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11166 | 20220114-8 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 7 | HR |  |  | 75 | 0 | 525 | 68.25 | 593.25 | 2022-01-14 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C129-C151 | Lake A | 0 | 2022-01-27 |  | 36 | 2022-01-27 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1116620220114-8Operator - Principle - After Jan 107525 | Corbiere and Sons Contracting1116620220114-8Operator - Principle - After Jan 107525INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11166 | 20220114-8 | 53510611 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 3 | Dynamic | 91.79 | 0 |  |  | 367.17 | 47.7321 | 414.9021 | 2022-01-14 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C129-C151 | Lake A | 0 | 2022-01-27 |  | 36 | 2022-01-27 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1116620220114-8Tractor Trailer - 60 Ton- After Jan 103367.17 | Corbiere and Sons Contracting1116620220114-8Tractor Trailer - 60 Ton- After Jan 103367.17INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11166 | 20220114-8 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 5 | Dynamic | 98.61 | 0 |  |  | 657.4 | 85.462 | 742.862 | 2022-01-14 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C129-C151 | Lake A | 0 | 2022-01-27 |  | 36 | 2022-01-27 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1116620220114-8Dozer D6 or equal- After Jan 105657.4 | Corbiere and Sons Contracting1116620220114-8Dozer D6 or equal- After Jan 105657.4INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11165 | 20220114-7 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 5.5 | HR |  |  | 0 | 0 | 385 | 50.05 | 435.05 | 2022-01-14 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-01-27 |  | 36 | 2022-01-27 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1116520220114-7Operator - Intermdiate - After Jan 105.5385 | Corbiere and Sons Contracting1116520220114-7Operator - Intermdiate - After Jan 105.5385INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11165 | 20220114-7 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 5.5 |  | 0 | 0 |  |  | 440 | 57.2 | 497.2 | 2022-01-14 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-01-27 |  | 36 | 2022-01-27 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1116520220114-7Pickup w/ plow and sander5.5440 | Corbiere and Sons Contracting1116520220114-7Pickup w/ plow and sander5.5440INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11159 | 20220113-7 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 5.5 | HR |  |  | 70 | 0 | 385 | 50.05 | 435.05 | 2022-01-13 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer worked clearing snow; Pickup w/plow worked clearing snow and sanding | 6 | C257-C267 | Hare Lake Creek | 0 | 2022-01-27 |  | 37 | 2022-01-27 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1115920220113-7Operator - Intermdiate - After Jan 105.5385 | Corbiere and Sons Contracting1115920220113-7Operator - Intermdiate - After Jan 105.5385INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11159 | 20220113-7 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2022-01-13 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer worked clearing snow; Pickup w/plow worked clearing snow and sanding | 6 | C257-C267 | Hare Lake Creek | 0 | 2022-01-27 |  | 37 | 2022-01-27 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1115920220113-7Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1115920220113-7Operator - Principle - After Jan 1011825INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11159 | 20220113-7 | 53510611 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2022-01-13 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer worked clearing snow; Pickup w/plow worked clearing snow and sanding | 6 | C257-C267 | Hare Lake Creek | 0 | 2022-01-27 |  | 37 | 2022-01-27 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1115920220113-7L.O.A.2420 | Corbiere and Sons Contracting1115920220113-7L.O.A.2420INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11159 | 20220113-7 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 5.5 |  | 0 | 0 |  |  | 440 | 57.2 | 497.2 | 2022-01-13 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer worked clearing snow; Pickup w/plow worked clearing snow and sanding | 6 | C257-C267 | Hare Lake Creek | 0 | 2022-01-27 |  | 37 | 2022-01-27 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1115920220113-7Pickup w/ plow and sander5.5440 | Corbiere and Sons Contracting1115920220113-7Pickup w/ plow and sander5.5440INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11159 | 20220113-7 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-13 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer worked clearing snow; Pickup w/plow worked clearing snow and sanding | 6 | C257-C267 | Hare Lake Creek | 0 | 2022-01-27 |  | 37 | 2022-01-27 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1115920220113-7Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1115920220113-7Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11159 | 20220113-7 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 4 | Dynamic | 98.61 | 0 |  |  | 525.92 | 68.3696 | 594.2896 | 2022-01-13 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer worked clearing snow; Pickup w/plow worked clearing snow and sanding | 6 | C257-C267 | Hare Lake Creek | 0 | 2022-01-27 |  | 37 | 2022-01-27 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1115920220113-7Dozer D6 or equal- After Jan 104525.92 | Corbiere and Sons Contracting1115920220113-7Dozer D6 or equal- After Jan 104525.92INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11084 | 20220112-9 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 5 | HR |  |  | 70 | 0 | 350 | 45.5 | 395.5 | 2022-01-12 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | OP was floated over to Hare Lake and then did WAM Activities | 6 | C257-C267 | Hare Lake Creek | 0 | 2022-01-25 |  | 37 | 2022-01-26 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1108420220112-9Driver - AZ - After Jan 105350 | Corbiere and Sons Contracting1108420220112-9Driver - AZ - After Jan 105350INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11084 | 20220112-9 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 0 | 0 | 450 | 58.5 | 508.5 | 2022-01-12 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | OP was floated over to Hare Lake and then did WAM Activities | 6 | C257-C267 | Hare Lake Creek | 0 | 2022-01-25 |  | 37 | 2022-01-26 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1108420220112-9Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting1108420220112-9Operator - Principle - After Jan 106450INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11084 | 20220112-9 | 53510611 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 5 | Dynamic | 91.79 | 0 |  |  | 611.95 | 79.5535 | 691.5035 | 2022-01-12 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | OP was floated over to Hare Lake and then did WAM Activities | 6 | C257-C267 | Hare Lake Creek | 0 | 2022-01-25 |  | 37 | 2022-01-26 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1108420220112-9Tractor Trailer - 60 Ton- After Jan 105611.95 | Corbiere and Sons Contracting1108420220112-9Tractor Trailer - 60 Ton- After Jan 105611.95INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11084 | 20220112-9 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 4 | Dynamic | 0 | 0 |  |  | 525.92 | 68.3696 | 594.2896 | 2022-01-12 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | OP was floated over to Hare Lake and then did WAM Activities | 6 | C257-C267 | Hare Lake Creek | 0 | 2022-01-25 |  | 37 | 2022-01-26 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1108420220112-9Dozer D6 or equal- After Jan 104525.92 | Corbiere and Sons Contracting1108420220112-9Dozer D6 or equal- After Jan 104525.92INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11083 | 20220112-8 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5 | HR |  |  | 0 | 0 | 375 | 48.75 | 423.75 | 2022-01-12 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Neys | 6 | C219-C235 | Neys | 0 | 2022-01-25 |  | 37 | 2022-01-26 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1108320220112-8Operator - Principle - After Jan 105375 | Corbiere and Sons Contracting1108320220112-8Operator - Principle - After Jan 105375INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11083 | 20220112-8 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2022-01-12 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Neys | 6 | C219-C235 | Neys | 0 | 2022-01-25 |  | 37 | 2022-01-26 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1108320220112-8L.O.A.1210 | Corbiere and Sons Contracting1108320220112-8L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11083 | 20220112-8 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-01-12 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Neys | 6 | C219-C235 | Neys | 0 | 2022-01-25 |  | 37 | 2022-01-26 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1108320220112-8Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1108320220112-8Light Truck - Pick up- After Jan 101243.75INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11083 | 20220112-8 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 4.5 | Dynamic | 98.61 | 0 |  |  | 591.66 | 76.9158 | 668.5758 | 2022-01-12 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities on Neys | 6 | C219-C235 | Neys | 0 | 2022-01-25 |  | 37 | 2022-01-26 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1108320220112-8Dozer D6 or equal- After Jan 104.5591.66 | Corbiere and Sons Contracting1108320220112-8Dozer D6 or equal- After Jan 104.5591.66INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11130 | 20220112-11-R1 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 5.5 | HR |  |  | 0 | 0 | 385 | 50.05 | 435.05 | 2022-01-12 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C152 - C154 | Lake A | 0 | 2022-01-25 |  | 37 | 2022-01-26 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1113020220112-11-R1Operator - Intermdiate - After Jan 105.5385 | Corbiere and Sons Contracting1113020220112-11-R1Operator - Intermdiate - After Jan 105.5385INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11130 | 20220112-11-R1 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 5.5 |  | 0 | 0 |  |  | 440 | 57.2 | 497.2 | 2022-01-12 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C152 - C154 | Lake A | 0 | 2022-01-25 |  | 37 | 2022-01-26 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1113020220112-11-R1Pickup w/ plow and sander5.5440 | Corbiere and Sons Contracting1113020220112-11-R1Pickup w/ plow and sander5.5440INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11085 | 20220112-10 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 5.5 | HR |  |  | 70 | 0 | 385 | 50.05 | 435.05 | 2022-01-12 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C244-C247 | Mink Creek | 0 | 2022-01-25 |  | 37 | 2022-01-26 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1108520220112-10Operator - Intermdiate - After Jan 105.5385 | Corbiere and Sons Contracting1108520220112-10Operator - Intermdiate - After Jan 105.5385INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11085 | 20220112-10 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2022-01-12 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C244-C247 | Mink Creek | 0 | 2022-01-25 |  | 37 | 2022-01-26 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1108520220112-10L.O.A.1210 | Corbiere and Sons Contracting1108520220112-10L.O.A.1210INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11085 | 20220112-10 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 5.5 |  | 0 | 0 |  |  | 440 | 57.2 | 497.2 | 2022-01-12 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C244-C247 | Mink Creek | 0 | 2022-01-25 |  | 37 | 2022-01-26 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1108520220112-10Pickup w/ plow and sander5.5440 | Corbiere and Sons Contracting1108520220112-10Pickup w/ plow and sander5.5440INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11432 | 20220106-8 | 53510611 | Access | 0 | 3rd Party Charges | 1 | 1763.2 | Unit |  |  |  |  | 1763.2 | 229.216 | 1992.416 | 2022-01-06 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Flagging done by Best Towing - Lake A | 6 | C130-C151 | Lake A | 0 | 2022-01-31 |  | 37 | 2022-02-04 | no number provided | Flagging done by Best Towing - Lake A |  |  |  | Harold Furlong | 06 | Corbiere and Sons Contracting1143220220106-83rd Party Charges1763.21763.2 | Corbiere and Sons Contracting1143220220106-83rd Party Charges1763.21763.2INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11430 | 20220102-17 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 4 | HR |  |  | 0 | 0 | 280 | 36.4 | 316.4 | 2022-01-02 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | North Shore float moving Grader | 6 | C203-C209 | Dead Horse Creek | 0 | 2022-01-31 |  | 37 | 2022-02-04 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1143020220102-17Driver - AZ - After Jan 104280 | Corbiere and Sons Contracting1143020220102-17Driver - AZ - After Jan 104280INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11430 | 20220102-17 | 53510611 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 4 | Dynamic | 0 | 0 |  |  | 489.56 | 63.6428 | 553.2028 | 2022-01-02 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | North Shore float moving Grader | 6 | C203-C209 | Dead Horse Creek | 0 | 2022-01-31 |  | 37 | 2022-02-04 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1143020220102-17Tractor Trailer - 60 Ton- After Jan 104489.56 | Corbiere and Sons Contracting1143020220102-17Tractor Trailer - 60 Ton- After Jan 104489.56INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11429 | 20220102-16 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 4 | HR |  |  | 70 | 0 | 280 | 36.4 | 316.4 | 2022-01-02 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | North Shore float moving Grader | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2022-01-31 |  | 37 | 2022-02-04 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1142920220102-16Driver - AZ - After Jan 104280 | Corbiere and Sons Contracting1142920220102-16Driver - AZ - After Jan 104280INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11429 | 20220102-16 | 53510611 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 4 | Dynamic | 91.79 | 0 |  |  | 489.56 | 63.6428 | 553.2028 | 2022-01-02 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | North Shore float moving Grader | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2022-01-31 |  | 37 | 2022-02-04 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1142920220102-16Tractor Trailer - 60 Ton- After Jan 104489.56 | Corbiere and Sons Contracting1142920220102-16Tractor Trailer - 60 Ton- After Jan 104489.56INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11428 | 20220102-15 | 53510611 | Access | 0 | 3rd Party Charges | 1 | 2204 | Unit |  |  |  |  | 2204 | 286.52 | 2490.52 | 2022-01-02 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Flagging done by Best Towing - Little Red Sucker Creek | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-01-31 |  | 37 | 2022-02-04 | no number provided | Flagging done by Best Towing - Little Red Sucker Creek |  |  |  | Harold Furlong | 06 | Corbiere and Sons Contracting1142820220102-153rd Party Charges22042204 | Corbiere and Sons Contracting1142820220102-153rd Party Charges22042204INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11427 | 20211216-10 | 53510611 | Access | 0 | 3rd Party Charges | 1 | 1102 | Unit |  |  |  |  | 1102 | 143.26 | 1245.26 | 2021-12-16 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Flagging done by Best Towing - Jackfish Lake | 6 | C152-C157 | Jackfish Lake | 0 | 2022-01-31 |  | 37 | 2022-02-03 | no number provided | Flagging done by Best Towing - Jackfish Lake |  |  |  | Harold Furlong | 06 | Corbiere and Sons Contracting1142720211216-103rd Party Charges11021102 | Corbiere and Sons Contracting1142720211216-103rd Party Charges11021102INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11426 | 20211213-11 | 53510611 | Access | 0 | 3rd Party Charges | 1 | 1454.64 | Unit |  |  |  |  | 1454.64 | 189.1032 | 1643.7432 | 2021-12-13 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Flagging done by Best Towing - Jackfish Lake | 6 | C152-C157 | Jackfish Lake | 0 | 2022-01-31 |  | 37 | 2022-02-03 | no number provided | Flagging done by Best Towing - Jackfish Lake |  |  |  | Harold Furlong | 06 | Corbiere and Sons Contracting1142620211213-113rd Party Charges1454.641454.64 | Corbiere and Sons Contracting1142620211213-113rd Party Charges1454.641454.64INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11425 | 20211129-13 | 53510611 | Access | 0 | 3rd Party Charges | 1 | 1895.44 | Unit |  |  |  |  | 1895.44 | 246.4072 | 2141.8472 | 2021-11-29 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Flagging done by Best Towing - Lake A | 6 | C130-C151 | Lake A | 0 | 2022-01-31 |  | 37 | 2022-02-03 | no number provided | Flagging done by Best Towing - Lake A |  |  |  | Harold Furlong | 06 | Corbiere and Sons Contracting1142520211129-133rd Party Charges1895.441895.44 | Corbiere and Sons Contracting1142520211129-133rd Party Charges1895.441895.44INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11424 | 20211128-12 | 53510611 | Access | 0 | 3rd Party Charges | 1 | 1763.2 | Unit |  |  |  |  | 1763.2 | 229.216 | 1992.416 | 2021-11-28 | 0 | INV #164 | 2022-02-23 | 177 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Flagging done by Best Towing - Dead Horse Creek and Lake A | 6 | C203-C209 | Dead Horse Creek | 0 | 2022-01-31 |  | 37 | 2022-02-03 | no number provided | Flagging done by Best Towing - Dead Horse Creek |  |  |  | Harold Furlong | 06 | Corbiere and Sons Contracting1142420211128-123rd Party Charges1763.21763.2 | Corbiere and Sons Contracting1142420211128-123rd Party Charges1763.21763.2INV #164 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11866 | 20211012-8 | 53510612 | Access | 0 | 3rd Party Charges | 1 | 2865.2 | Unit |  |  |  |  | 2865.2 | 372.476 | 3237.676 | 2021-10-12 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Flagging done by Best Towing, Dead Horse Creek, Ripple Lake Road, Mink Creek Road | 6 | C129-D005 | WF6 | 0 |  |  | 36 | 2022-02-23 | Not available | Best Towing price before mark up 2470.00 |  |  |  | Mike Lecocq | 06 | Corbiere and Sons Contracting1186620211012-83rd Party Charges2865.22865.2 | Corbiere and Sons Contracting1186620211012-83rd Party Charges2865.22865.2INV #165 | New All Season Development |  | New All Season Development
Corbiere and Sons Contracting | 6 | 0 | 11566 | 20220219-7 | 53510711 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 4 | HR |  |  | 0 | 0 | 300 | 39 | 339 | 2022-02-19 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  | Shouldl be WF7 winter maint CC |  | Approved |  |  | WAM Activities Pic River - WWF7 | 6 | D018-D024 | Pic River | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 07 | Corbiere and Sons Contracting1156620220219-7Operator - Principle - After Jan 104300 | Corbiere and Sons Contracting1156620220219-7Operator - Principle - After Jan 104300INV #165 | CZ - All Season Access Maintenance |  | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11566 | 20220219-7 | 53510711 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 4 | Dynamic | 0 | 0 |  |  | 507.92 | 66.0296 | 573.9496 | 2022-02-19 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  | Shouldl be WF7 winter maint CC |  | Approved |  |  | WAM Activities Pic River - WWF7 | 6 | D018-D024 | Pic River | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 07 | Corbiere and Sons Contracting1156620220219-7Grader - Cat 12 to 14 or equal- After Jan 104507.92 | Corbiere and Sons Contracting1156620220219-7Grader - Cat 12 to 14 or equal- After Jan 104507.92INV #165 | CZ - All Season Access Maintenance |  | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11565 | 20220219-6 | 53510711 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5 | HR |  |  | 0 | 0 | 375 | 48.75 | 423.75 | 2022-02-19 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM ActivitiesThreee Fingers - WWF7 | 6 | D006-D017 | Three Fingers - WF7 | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 07 | Corbiere and Sons Contracting1156520220219-6Operator - Principle - After Jan 105375 | Corbiere and Sons Contracting1156520220219-6Operator - Principle - After Jan 105375INV #165 | CZ - All Season Access Maintenance |  | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11565 | 20220219-6 | 53510711 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 3 | Dynamic | 0 | 0 |  |  | 380.94 | 49.5222 | 430.4622 | 2022-02-19 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM ActivitiesThreee Fingers - WWF7 | 6 | D006-D017 | Three Fingers - WF7 | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 07 | Corbiere and Sons Contracting1156520220219-6Grader - Cat 12 to 14 or equal- After Jan 103380.94 | Corbiere and Sons Contracting1156520220219-6Grader - Cat 12 to 14 or equal- After Jan 103380.94INV #165 | CZ - All Season Access Maintenance |  | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11624 | 20220301-5 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-03-01 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C219-C236 | Neys | 0 | 2022-03-03 |  | 37 | 2022-03-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1162420220301-5Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1162420220301-5Operator - Principle - After Jan 1011825INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11624 | 20220301-5 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2022-03-01 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C219-C236 | Neys | 0 | 2022-03-03 |  | 37 | 2022-03-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1162420220301-5L.O.A.1210 | Corbiere and Sons Contracting1162420220301-5L.O.A.1210INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11624 | 20220301-5 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-03-01 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C219-C236 | Neys | 0 | 2022-03-03 |  | 37 | 2022-03-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1162420220301-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1162420220301-5Light Truck - Pick up- After Jan 101243.75INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11624 | 20220301-5 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10 | Dynamic | 0 | 0 |  |  | 1314.8 | 170.924 | 1485.724 | 2022-03-01 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C219-C236 | Neys | 0 | 2022-03-03 |  | 37 | 2022-03-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1162420220301-5Dozer D6 or equal- After Jan 10101314.8 | Corbiere and Sons Contracting1162420220301-5Dozer D6 or equal- After Jan 10101314.8INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11623 | 20220301-4 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-03-01 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C171-C185 | Prairie River | 0 | 2022-03-03 |  | 37 | 2022-03-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1162320220301-4Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1162320220301-4Operator - Principle - After Jan 1011825INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11623 | 20220301-4 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2022-03-01 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C171-C185 | Prairie River | 0 | 2022-03-03 |  | 37 | 2022-03-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1162320220301-4L.O.A.1210 | Corbiere and Sons Contracting1162320220301-4L.O.A.1210INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11623 | 20220301-4 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-03-01 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C171-C185 | Prairie River | 0 | 2022-03-03 |  | 37 | 2022-03-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1162320220301-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1162320220301-4Light Truck - Pick up- After Jan 101243.75INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11623 | 20220301-4 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-03-01 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C171-C185 | Prairie River | 0 | 2022-03-03 |  | 37 | 2022-03-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1162320220301-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1162320220301-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11622 | 20220301-3 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2022-03-01 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-03-03 |  | 37 | 2022-03-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1162220220301-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1162220220301-3Operator - Principle - After Jan 1011825INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11622 | 20220301-3 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2022-03-01 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-03-03 |  | 37 | 2022-03-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1162220220301-3L.O.A.1210 | Corbiere and Sons Contracting1162220220301-3L.O.A.1210INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11622 | 20220301-3 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-03-01 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-03-03 |  | 37 | 2022-03-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1162220220301-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1162220220301-3Light Truck - Pick up- After Jan 101243.75INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11622 | 20220301-3 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 95.24 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-03-01 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-03-03 |  | 37 | 2022-03-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1162220220301-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1162220220301-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11620 | 20220228-6 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 7 | HR |  |  | 0 | 0 | 490 | 63.7 | 553.7 | 2022-02-28 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C257-C267 | Hare Lake Creek | 0 | 2022-03-03 |  | 37 | 2022-03-05 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1162020220228-6Operator - Intermdiate - After Jan 107490 | Corbiere and Sons Contracting1162020220228-6Operator - Intermdiate - After Jan 107490INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11620 | 20220228-6 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-28 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C257-C267 | Hare Lake Creek | 0 | 2022-03-03 |  | 37 | 2022-03-05 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1162020220228-6L.O.A.1210 | Corbiere and Sons Contracting1162020220228-6L.O.A.1210INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11620 | 20220228-6 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 7 |  | 0 | 0 |  |  | 560 | 72.8 | 632.8 | 2022-02-28 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C257-C267 | Hare Lake Creek | 0 | 2022-03-03 |  | 37 | 2022-03-05 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1162020220228-6Pickup w/ plow and sander7560 | Corbiere and Sons Contracting1162020220228-6Pickup w/ plow and sander7560INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11619 | 20220228-5 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5 | HR |  |  | 75 | 0 | 375 | 48.75 | 423.75 | 2022-02-28 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C219-C236 | Neys | 0 | 2022-03-03 |  | 37 | 2022-03-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1161920220228-5Operator - Principle - After Jan 105375 | Corbiere and Sons Contracting1161920220228-5Operator - Principle - After Jan 105375INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11619 | 20220228-5 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 4 | Dynamic | 98.61 | 0 |  |  | 525.92 | 68.3696 | 594.2896 | 2022-02-28 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C219-C236 | Neys | 0 | 2022-03-03 |  | 37 | 2022-03-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1161920220228-5Dozer D6 or equal- After Jan 104525.92 | Corbiere and Sons Contracting1161920220228-5Dozer D6 or equal- After Jan 104525.92INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11618 | 20220228-4 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-02-28 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C171-C185 | Prairie River | 0 | 2022-03-03 |  | 37 | 2022-03-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1161820220228-4Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1161820220228-4Operator - Principle - After Jan 1011825INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11618 | 20220228-4 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2022-02-28 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C171-C185 | Prairie River | 0 | 2022-03-03 |  | 37 | 2022-03-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1161820220228-4L.O.A.1210 | Corbiere and Sons Contracting1161820220228-4L.O.A.1210INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11618 | 20220228-4 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-28 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C171-C185 | Prairie River | 0 | 2022-03-03 |  | 37 | 2022-03-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1161820220228-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1161820220228-4Light Truck - Pick up- After Jan 101243.75INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11618 | 20220228-4 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-02-28 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C171-C185 | Prairie River | 0 | 2022-03-03 |  | 37 | 2022-03-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1161820220228-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1161820220228-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11617 | 20220228-3 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 8.5 | HR |  |  | 0 | 0 | 595 | 77.35 | 672.35 | 2022-02-28 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-03-03 |  | 37 | 2022-03-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1161720220228-3Driver - AZ - After Jan 108.5595 | Corbiere and Sons Contracting1161720220228-3Driver - AZ - After Jan 108.5595INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11617 | 20220228-3 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 0 | 0 | 900 | 117 | 1017 | 2022-02-28 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-03-03 |  | 37 | 2022-03-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1161720220228-3Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1161720220228-3Operator - Principle - After Jan 1012900INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11617 | 20220228-3 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 0 | 0 | 450 | 58.5 | 508.5 | 2022-02-28 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-03-03 |  | 37 | 2022-03-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1161720220228-3Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting1161720220228-3Operator - Principle - After Jan 106450INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11617 | 20220228-3 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-02-28 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-03-03 |  | 37 | 2022-03-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1161720220228-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1161720220228-3Operator - Principle - After Jan 1011825INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11617 | 20220228-3 | 53510611 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2022-02-28 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-03-03 |  | 37 | 2022-03-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1161720220228-3L.O.A.4840 | Corbiere and Sons Contracting1161720220228-3L.O.A.4840INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11617 | 20220228-3 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 5 |  | 0 | 0 |  |  | 400 | 52 | 452 | 2022-02-28 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-03-03 |  | 37 | 2022-03-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1161720220228-3Pickup w/ plow and sander5400 | Corbiere and Sons Contracting1161720220228-3Pickup w/ plow and sander5400INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11617 | 20220228-3 | 53510611 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 8.5 | Dynamic | 0 | 0 |  |  | 1040.315 | 135.2409 | 1175.5559 | 2022-02-28 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-03-03 |  | 37 | 2022-03-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1161720220228-3Tractor Trailer - 60 Ton- After Jan 108.51040.315 | Corbiere and Sons Contracting1161720220228-3Tractor Trailer - 60 Ton- After Jan 108.51040.315INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11617 | 20220228-3 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-28 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-03-03 |  | 37 | 2022-03-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1161720220228-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1161720220228-3Light Truck - Pick up- After Jan 101243.75INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11617 | 20220228-3 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-28 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-03-03 |  | 37 | 2022-03-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1161720220228-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1161720220228-3Light Truck - Pick up- After Jan 101243.75INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11617 | 20220228-3 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 6.5 | Dynamic | 0 | 0 |  |  | 825.37 | 107.2981 | 932.6681 | 2022-02-28 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-03-03 |  | 37 | 2022-03-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1161720220228-3Grader - Cat 12 to 14 or equal- After Jan 106.5825.37 | Corbiere and Sons Contracting1161720220228-3Grader - Cat 12 to 14 or equal- After Jan 106.5825.37INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11617 | 20220228-3 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 4 | Dynamic | 0 | 0 |  |  | 525.92 | 68.3696 | 594.2896 | 2022-02-28 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-03-03 |  | 37 | 2022-03-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1161720220228-3Dozer D6 or equal- After Jan 104525.92 | Corbiere and Sons Contracting1161720220228-3Dozer D6 or equal- After Jan 104525.92INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11615 | 20220227-7 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 8 | HR |  |  | 0 | 0 | 600 | 78 | 678 | 2022-02-27 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Peninsula | 6 | C268-D005 | Peninsula | 0 | 2022-03-03 |  | 37 | 2022-03-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1161520220227-7Operator - Principle - After Jan 108600 | Corbiere and Sons Contracting1161520220227-7Operator - Principle - After Jan 108600INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11615 | 20220227-7 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-27 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Peninsula | 6 | C268-D005 | Peninsula | 0 | 2022-03-03 |  | 37 | 2022-03-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1161520220227-7L.O.A.1210 | Corbiere and Sons Contracting1161520220227-7L.O.A.1210INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11615 | 20220227-7 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-27 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Peninsula | 6 | C268-D005 | Peninsula | 0 | 2022-03-03 |  | 37 | 2022-03-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1161520220227-7Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1161520220227-7Light Truck - Pick up- After Jan 101243.75INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11615 | 20220227-7 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 5 | Dynamic | 98.61 | 0 |  |  | 657.4 | 85.462 | 742.862 | 2022-02-27 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Peninsula | 6 | C268-D005 | Peninsula | 0 | 2022-03-03 |  | 37 | 2022-03-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1161520220227-7Dozer D6 or equal- After Jan 105657.4 | Corbiere and Sons Contracting1161520220227-7Dozer D6 or equal- After Jan 105657.4INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11614 | 20220227-6 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 11 | HR |  |  | 70 | 0 | 770 | 100.1 | 870.1 | 2022-02-27 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-03-03 |  | 37 | 2022-03-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1161420220227-6Operator - Intermdiate - After Jan 1011770 | Corbiere and Sons Contracting1161420220227-6Operator - Intermdiate - After Jan 1011770INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11614 | 20220227-6 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-27 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-03-03 |  | 37 | 2022-03-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1161420220227-6L.O.A.1210 | Corbiere and Sons Contracting1161420220227-6L.O.A.1210INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11614 | 20220227-6 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 11 |  | 0 | 0 |  |  | 880 | 114.4 | 994.4 | 2022-02-27 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-03-03 |  | 37 | 2022-03-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1161420220227-6Pickup w/ plow and sander11880 | Corbiere and Sons Contracting1161420220227-6Pickup w/ plow and sander11880INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11613 | 20220227-5 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 0 | 0 | 900 | 117 | 1017 | 2022-02-27 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 | 2022-03-03 |  | 37 | 2022-03-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1161320220227-5Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1161320220227-5Operator - Principle - After Jan 1012900INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11613 | 20220227-5 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2022-02-27 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 | 2022-03-03 |  | 37 | 2022-03-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1161320220227-5L.O.A.1210 | Corbiere and Sons Contracting1161320220227-5L.O.A.1210INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11613 | 20220227-5 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 12 |  | 0 | 0 |  |  | 960 | 124.8 | 1084.8 | 2022-02-27 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 | 2022-03-03 |  | 37 | 2022-03-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1161320220227-5Pickup w/ plow and sander12960 | Corbiere and Sons Contracting1161320220227-5Pickup w/ plow and sander12960INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11612 | 20220227-4 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 75 | 0 | 450 | 58.5 | 508.5 | 2022-02-27 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C171-C185 | Prairie River | 0 | 2022-03-03 |  | 37 | 2022-03-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1161220220227-4Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting1161220220227-4Operator - Principle - After Jan 106450INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11612 | 20220227-4 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 6 | Dynamic | 95.24 | 0 |  |  | 761.88 | 99.0444 | 860.9244 | 2022-02-27 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C171-C185 | Prairie River | 0 | 2022-03-03 |  | 37 | 2022-03-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1161220220227-4Grader - Cat 12 to 14 or equal- After Jan 106761.88 | Corbiere and Sons Contracting1161220220227-4Grader - Cat 12 to 14 or equal- After Jan 106761.88INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11611 | 20220227-3 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 11 | HR |  |  | 0 | 0 | 770 | 100.1 | 870.1 | 2022-02-27 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-03-03 |  | 37 | 2022-03-09 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1161120220227-3Driver - AZ - After Jan 1011770 | Corbiere and Sons Contracting1161120220227-3Driver - AZ - After Jan 1011770INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11611 | 20220227-3 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5 | HR |  |  | 0 | 0 | 375 | 48.75 | 423.75 | 2022-02-27 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-03-03 |  | 37 | 2022-03-09 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1161120220227-3Operator - Principle - After Jan 105375 | Corbiere and Sons Contracting1161120220227-3Operator - Principle - After Jan 105375INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11611 | 20220227-3 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-02-27 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-03-03 |  | 37 | 2022-03-09 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1161120220227-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1161120220227-3Operator - Principle - After Jan 1011825INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11611 | 20220227-3 | 53510611 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  | 0 | 0 | 630 | 81.9 | 711.9 | 2022-02-27 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-03-03 |  | 37 | 2022-03-09 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1161120220227-3L.O.A.3630 | Corbiere and Sons Contracting1161120220227-3L.O.A.3630INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11611 | 20220227-3 | 53510611 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 11 | Dynamic | 0 | 0 |  |  | 1346.29 | 175.0177 | 1521.3077 | 2022-02-27 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-03-03 |  | 37 | 2022-03-09 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1161120220227-3Tractor Trailer - 60 Ton- After Jan 10111346.29 | Corbiere and Sons Contracting1161120220227-3Tractor Trailer - 60 Ton- After Jan 10111346.29INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11611 | 20220227-3 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-27 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-03-03 |  | 37 | 2022-03-09 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1161120220227-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1161120220227-3Light Truck - Pick up- After Jan 101243.75INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11611 | 20220227-3 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-27 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-03-03 |  | 37 | 2022-03-09 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1161120220227-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1161120220227-3Light Truck - Pick up- After Jan 101243.75INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11611 | 20220227-3 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-02-27 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-03-03 |  | 37 | 2022-03-09 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1161120220227-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1161120220227-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11611 | 20220227-3 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 3 | Dynamic | 0 | 0 |  |  | 394.44 | 51.2772 | 445.7172 | 2022-02-27 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-03-03 |  | 37 | 2022-03-09 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1161120220227-3Dozer D6 or equal- After Jan 103394.44 | Corbiere and Sons Contracting1161120220227-3Dozer D6 or equal- After Jan 103394.44INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11609 | 20220226-5 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2022-02-26 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C219-C236 | Neys | 0 | 2022-03-03 |  | 37 | 2022-03-09 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1160920220226-5L.O.A.1210 | Corbiere and Sons Contracting1160920220226-5L.O.A.1210INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11609 | 20220226-5 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 11 |  | 0 | 0 |  |  | 880 | 114.4 | 994.4 | 2022-02-26 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C219-C236 | Neys | 0 | 2022-03-03 |  | 37 | 2022-03-09 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1160920220226-5Pickup w/ plow and sander11880 | Corbiere and Sons Contracting1160920220226-5Pickup w/ plow and sander11880INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11608 | 20220226-4 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5 | HR |  |  | 75 | 0 | 375 | 48.75 | 423.75 | 2022-02-26 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-03-03 |  | 37 | 2022-03-09 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1160820220226-4Operator - Principle - After Jan 105375 | Corbiere and Sons Contracting1160820220226-4Operator - Principle - After Jan 105375INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11608 | 20220226-4 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 5 | Dynamic | 95.24 | 0 |  |  | 634.9 | 82.537 | 717.437 | 2022-02-26 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-03-03 |  | 37 | 2022-03-09 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1160820220226-4Grader - Cat 12 to 14 or equal- After Jan 105634.9 | Corbiere and Sons Contracting1160820220226-4Grader - Cat 12 to 14 or equal- After Jan 105634.9INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11607 | 20220226-3 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 6 | HR |  |  | 70 | 0 | 420 | 54.6 | 474.6 | 2022-02-26 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-03-03 |  | 37 | 2022-03-09 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1160720220226-3Driver - AZ - After Jan 106420 | Corbiere and Sons Contracting1160720220226-3Driver - AZ - After Jan 106420INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11607 | 20220226-3 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 13 | HR |  |  | 75 | 0 | 975 | 126.75 | 1101.75 | 2022-02-26 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-03-03 |  | 37 | 2022-03-09 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1160720220226-3Operator - Principle - After Jan 1013975 | Corbiere and Sons Contracting1160720220226-3Operator - Principle - After Jan 1013975INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11607 | 20220226-3 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 9 | HR |  |  | 75 | 0 | 675 | 87.75 | 762.75 | 2022-02-26 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-03-03 |  | 37 | 2022-03-09 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1160720220226-3Operator - Principle - After Jan 109675 | Corbiere and Sons Contracting1160720220226-3Operator - Principle - After Jan 109675INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11607 | 20220226-3 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 75 | 0 | 450 | 58.5 | 508.5 | 2022-02-26 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-03-03 |  | 37 | 2022-03-09 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1160720220226-3Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting1160720220226-3Operator - Principle - After Jan 106450INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11607 | 20220226-3 | 53510611 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2022-02-26 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-03-03 |  | 37 | 2022-03-09 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1160720220226-3L.O.A.3630 | Corbiere and Sons Contracting1160720220226-3L.O.A.3630INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11607 | 20220226-3 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 9 |  | 0 | 0 |  |  | 720 | 93.6 | 813.6 | 2022-02-26 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-03-03 |  | 37 | 2022-03-09 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1160720220226-3Pickup w/ plow and sander9720 | Corbiere and Sons Contracting1160720220226-3Pickup w/ plow and sander9720INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11607 | 20220226-3 | 53510611 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 6 | Dynamic | 91.79 | 0 |  |  | 734.34 | 95.4642 | 829.8042 | 2022-02-26 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-03-03 |  | 37 | 2022-03-09 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1160720220226-3Tractor Trailer - 60 Ton- After Jan 106734.34 | Corbiere and Sons Contracting1160720220226-3Tractor Trailer - 60 Ton- After Jan 106734.34INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11607 | 20220226-3 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-26 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-03-03 |  | 37 | 2022-03-09 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1160720220226-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1160720220226-3Light Truck - Pick up- After Jan 101243.75INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11607 | 20220226-3 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-26 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-03-03 |  | 37 | 2022-03-09 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1160720220226-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1160720220226-3Light Truck - Pick up- After Jan 101243.75INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11607 | 20220226-3 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 4 | Dynamic | 95.24 | 0 |  |  | 507.92 | 66.0296 | 573.9496 | 2022-02-26 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-03-03 |  | 37 | 2022-03-09 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1160720220226-3Grader - Cat 12 to 14 or equal- After Jan 104507.92 | Corbiere and Sons Contracting1160720220226-3Grader - Cat 12 to 14 or equal- After Jan 104507.92INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11607 | 20220226-3 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 12 | Dynamic | 98.61 | 0 |  |  | 1577.76 | 205.1088 | 1782.8688 | 2022-02-26 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-03-03 |  | 37 | 2022-03-09 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1160720220226-3Dozer D6 or equal- After Jan 10121577.76 | Corbiere and Sons Contracting1160720220226-3Dozer D6 or equal- After Jan 10121577.76INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11605 | 20220225-6 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-25 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C257-C267 | Hare Lake Creek | 0 | 2022-03-03 |  | 37 | 2022-03-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1160520220225-6L.O.A.1210 | Corbiere and Sons Contracting1160520220225-6L.O.A.1210INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11605 | 20220225-6 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 11 |  | 0 | 0 |  |  | 880 | 114.4 | 994.4 | 2022-02-25 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C257-C267 | Hare Lake Creek | 0 | 2022-03-03 |  | 37 | 2022-03-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1160520220225-6Pickup w/ plow and sander11880 | Corbiere and Sons Contracting1160520220225-6Pickup w/ plow and sander11880INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11604 | 20220225-5 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 10 | HR |  |  | 0 | 0 | 750 | 97.5 | 847.5 | 2022-02-25 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Prairie River | 6 | C171-C185 | Prairie River | 0 | 2022-03-03 |  | 37 | 2022-03-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1160420220225-5Operator - Principle - After Jan 1010750 | Corbiere and Sons Contracting1160420220225-5Operator - Principle - After Jan 1010750INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11604 | 20220225-5 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-25 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Prairie River | 6 | C171-C185 | Prairie River | 0 | 2022-03-03 |  | 37 | 2022-03-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1160420220225-5L.O.A.1210 | Corbiere and Sons Contracting1160420220225-5L.O.A.1210INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11604 | 20220225-5 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-25 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Prairie River | 6 | C171-C185 | Prairie River | 0 | 2022-03-03 |  | 37 | 2022-03-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1160420220225-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1160420220225-5Light Truck - Pick up- After Jan 101243.75INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11604 | 20220225-5 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 9 | Dynamic | 0 | 0 |  |  | 1142.82 | 148.5666 | 1291.3866 | 2022-02-25 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Prairie River | 6 | C171-C185 | Prairie River | 0 | 2022-03-03 |  | 37 | 2022-03-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1160420220225-5Grader - Cat 12 to 14 or equal- After Jan 1091142.82 | Corbiere and Sons Contracting1160420220225-5Grader - Cat 12 to 14 or equal- After Jan 1091142.82INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11603 | 20220225-4 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-02-25 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Peninsula | 6 | C268-D005 | Peninsula | 0 | 2022-03-03 |  | 37 | 2022-03-09 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1160320220225-4Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1160320220225-4Operator - Principle - After Jan 1011825INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11603 | 20220225-4 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-25 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Peninsula | 6 | C268-D005 | Peninsula | 0 | 2022-03-03 |  | 37 | 2022-03-09 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1160320220225-4L.O.A.1210 | Corbiere and Sons Contracting1160320220225-4L.O.A.1210INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11603 | 20220225-4 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-25 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Peninsula | 6 | C268-D005 | Peninsula | 0 | 2022-03-03 |  | 37 | 2022-03-09 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1160320220225-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1160320220225-4Light Truck - Pick up- After Jan 101243.75INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11603 | 20220225-4 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 8 | Dynamic | 0 | 0 |  |  | 1015.84 | 132.0592 | 1147.8992 | 2022-02-25 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Peninsula | 6 | C268-D005 | Peninsula | 0 | 2022-03-03 |  | 37 | 2022-03-09 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1160320220225-4Grader - Cat 12 to 14 or equal- After Jan 1081015.84 | Corbiere and Sons Contracting1160320220225-4Grader - Cat 12 to 14 or equal- After Jan 1081015.84INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11602 | 20220225-3 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 0 | 0 | 900 | 117 | 1017 | 2022-02-25 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Lake A | 6 | C130-C151 | Lake A | 0 | 2022-03-03 |  | 37 | 2022-03-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1160220220225-3Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1160220220225-3Operator - Principle - After Jan 1012900INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11602 | 20220225-3 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-02-25 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Lake A | 6 | C130-C151 | Lake A | 0 | 2022-03-03 |  | 37 | 2022-03-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1160220220225-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1160220220225-3Operator - Principle - After Jan 1011825INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11602 | 20220225-3 | 53510611 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2022-02-25 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Lake A | 6 | C130-C151 | Lake A | 0 | 2022-03-03 |  | 37 | 2022-03-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1160220220225-3L.O.A.2420 | Corbiere and Sons Contracting1160220220225-3L.O.A.2420INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11602 | 20220225-3 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 12 |  | 0 | 0 |  |  | 960 | 124.8 | 1084.8 | 2022-02-25 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Lake A | 6 | C130-C151 | Lake A | 0 | 2022-03-03 |  | 37 | 2022-03-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1160220220225-3Pickup w/ plow and sander12960 | Corbiere and Sons Contracting1160220220225-3Pickup w/ plow and sander12960INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11602 | 20220225-3 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-25 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Lake A | 6 | C130-C151 | Lake A | 0 | 2022-03-03 |  | 37 | 2022-03-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1160220220225-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1160220220225-3Light Truck - Pick up- After Jan 101243.75INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11602 | 20220225-3 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10 | Dynamic | 0 | 0 |  |  | 1314.8 | 170.924 | 1485.724 | 2022-02-25 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Lake A | 6 | C130-C151 | Lake A | 0 | 2022-03-03 |  | 37 | 2022-03-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1160220220225-3Dozer D6 or equal- After Jan 10101314.8 | Corbiere and Sons Contracting1160220220225-3Dozer D6 or equal- After Jan 10101314.8INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11600 | 20220224-7 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 12 | HR |  |  | 0 | 0 | 840 | 109.2 | 949.2 | 2022-02-24 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Lake A | 6 | C130-C151 | Lake A | 0 | 2022-03-03 |  | 37 | 2022-03-09 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1160020220224-7Driver - AZ - After Jan 1012840 | Corbiere and Sons Contracting1160020220224-7Driver - AZ - After Jan 1012840INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11600 | 20220224-7 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2022-02-24 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Lake A | 6 | C130-C151 | Lake A | 0 | 2022-03-03 |  | 37 | 2022-03-09 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1160020220224-7Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1160020220224-7Operator - Principle - After Jan 1012900INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11600 | 20220224-7 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 0 | 0 | 450 | 58.5 | 508.5 | 2022-02-24 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Lake A | 6 | C130-C151 | Lake A | 0 | 2022-03-03 |  | 37 | 2022-03-09 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1160020220224-7Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting1160020220224-7Operator - Principle - After Jan 106450INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11600 | 20220224-7 | 53510611 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2022-02-24 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Lake A | 6 | C130-C151 | Lake A | 0 | 2022-03-03 |  | 37 | 2022-03-09 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1160020220224-7L.O.A.2420 | Corbiere and Sons Contracting1160020220224-7L.O.A.2420INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11600 | 20220224-7 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 12 |  | 0 | 0 |  |  | 960 | 124.8 | 1084.8 | 2022-02-24 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Lake A | 6 | C130-C151 | Lake A | 0 | 2022-03-03 |  | 37 | 2022-03-09 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1160020220224-7Pickup w/ plow and sander12960 | Corbiere and Sons Contracting1160020220224-7Pickup w/ plow and sander12960INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11600 | 20220224-7 | 53510611 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 12 | Dynamic | 0 | 0 |  |  | 1468.68 | 190.9284 | 1659.6084 | 2022-02-24 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Lake A | 6 | C130-C151 | Lake A | 0 | 2022-03-03 |  | 37 | 2022-03-09 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1160020220224-7Tractor Trailer - 60 Ton- After Jan 10121468.68 | Corbiere and Sons Contracting1160020220224-7Tractor Trailer - 60 Ton- After Jan 10121468.68INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11600 | 20220224-7 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 4 | Dynamic | 0 | 0 |  |  | 525.92 | 68.3696 | 594.2896 | 2022-02-24 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Lake A | 6 | C130-C151 | Lake A | 0 | 2022-03-03 |  | 37 | 2022-03-09 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1160020220224-7Dozer D6 or equal- After Jan 104525.92 | Corbiere and Sons Contracting1160020220224-7Dozer D6 or equal- After Jan 104525.92INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11599 | 20220224-6 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-24 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C257-C267 | Hare Lake Creek | 0 | 2022-03-03 |  | 37 | 2022-03-09 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1159920220224-6L.O.A.1210 | Corbiere and Sons Contracting1159920220224-6L.O.A.1210INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11599 | 20220224-6 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 11 |  | 0 | 0 |  |  | 880 | 114.4 | 994.4 | 2022-02-24 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C257-C267 | Hare Lake Creek | 0 | 2022-03-03 |  | 37 | 2022-03-09 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1159920220224-6Pickup w/ plow and sander11880 | Corbiere and Sons Contracting1159920220224-6Pickup w/ plow and sander11880INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11598 | 20220224-5 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-02-24 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Prairie River | 6 | C171-C185 | Prairie River | 0 | 2022-03-03 |  | 37 | 2022-03-09 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1159820220224-5Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1159820220224-5Operator - Principle - After Jan 1011825INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11598 | 20220224-5 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-24 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Prairie River | 6 | C171-C185 | Prairie River | 0 | 2022-03-03 |  | 37 | 2022-03-09 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1159820220224-5L.O.A.1210 | Corbiere and Sons Contracting1159820220224-5L.O.A.1210INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11598 | 20220224-5 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-24 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Prairie River | 6 | C171-C185 | Prairie River | 0 | 2022-03-03 |  | 37 | 2022-03-09 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1159820220224-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1159820220224-5Light Truck - Pick up- After Jan 101243.75INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11598 | 20220224-5 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 5 | Dynamic | 0 | 0 |  |  | 634.9 | 82.537 | 717.437 | 2022-02-24 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Prairie River | 6 | C171-C185 | Prairie River | 0 | 2022-03-03 |  | 37 | 2022-03-09 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1159820220224-5Grader - Cat 12 to 14 or equal- After Jan 105634.9 | Corbiere and Sons Contracting1159820220224-5Grader - Cat 12 to 14 or equal- After Jan 105634.9INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11598 | 20220224-5 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 4 | Dynamic | 98.61 | 0 |  |  | 525.92 | 68.3696 | 594.2896 | 2022-02-24 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Prairie River | 6 | C171-C185 | Prairie River | 0 | 2022-03-03 |  | 37 | 2022-03-09 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1159820220224-5Dozer D6 or equal- After Jan 104525.92 | Corbiere and Sons Contracting1159820220224-5Dozer D6 or equal- After Jan 104525.92INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11597 | 20220224-4 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-02-24 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Peninsula | 6 | C268-D005 | Peninsula | 0 | 2022-03-03 |  | 37 | 2022-03-09 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1159720220224-4Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1159720220224-4Operator - Principle - After Jan 1011825INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11597 | 20220224-4 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-24 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Peninsula | 6 | C268-D005 | Peninsula | 0 | 2022-03-03 |  | 37 | 2022-03-09 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1159720220224-4L.O.A.1210 | Corbiere and Sons Contracting1159720220224-4L.O.A.1210INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11597 | 20220224-4 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-24 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Peninsula | 6 | C268-D005 | Peninsula | 0 | 2022-03-03 |  | 37 | 2022-03-09 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1159720220224-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1159720220224-4Light Truck - Pick up- After Jan 101243.75INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11597 | 20220224-4 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-02-24 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Peninsula | 6 | C268-D005 | Peninsula | 0 | 2022-03-03 |  | 37 | 2022-03-09 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1159720220224-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1159720220224-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11596 | 20220224-3 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5 | HR |  |  | 0 | 0 | 375 | 48.75 | 423.75 | 2022-02-24 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Little Red Sucker Creek | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-03-03 |  | 37 | 2022-03-09 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1159620220224-3Operator - Principle - After Jan 105375 | Corbiere and Sons Contracting1159620220224-3Operator - Principle - After Jan 105375INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11596 | 20220224-3 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-24 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Little Red Sucker Creek | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-03-03 |  | 37 | 2022-03-09 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1159620220224-3L.O.A.1210 | Corbiere and Sons Contracting1159620220224-3L.O.A.1210INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11596 | 20220224-3 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-24 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Little Red Sucker Creek | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-03-03 |  | 37 | 2022-03-09 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1159620220224-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1159620220224-3Light Truck - Pick up- After Jan 101243.75INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11596 | 20220224-3 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 5 | Dynamic | 0 | 0 |  |  | 634.9 | 82.537 | 717.437 | 2022-02-24 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Little Red Sucker Creek | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-03-03 |  | 37 | 2022-03-09 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1159620220224-3Grader - Cat 12 to 14 or equal- After Jan 105634.9 | Corbiere and Sons Contracting1159620220224-3Grader - Cat 12 to 14 or equal- After Jan 105634.9INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11593 | 20220223-7 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2022-02-23 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C257-C267 | Hare Lake Creek | 0 | 2022-03-03 |  | 37 | 2022-03-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1159320220223-7Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1159320220223-7Operator - Principle - After Jan 1012900INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11593 | 20220223-7 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-23 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C257-C267 | Hare Lake Creek | 0 | 2022-03-03 |  | 37 | 2022-03-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1159320220223-7L.O.A.1210 | Corbiere and Sons Contracting1159320220223-7L.O.A.1210INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11593 | 20220223-7 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 12 |  | 0 | 0 |  |  | 960 | 124.8 | 1084.8 | 2022-02-23 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C257-C267 | Hare Lake Creek | 0 | 2022-03-03 |  | 37 | 2022-03-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1159320220223-7Pickup w/ plow and sander12960 | Corbiere and Sons Contracting1159320220223-7Pickup w/ plow and sander12960INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11592 | 20220223-6 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 11 | HR |  |  | 0 | 0 | 770 | 100.1 | 870.1 | 2022-02-23 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C198-C202 | Ripple Lake | 0 | 2022-03-03 |  | 37 | 2022-03-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1159220220223-6Operator - Intermdiate - After Jan 1011770 | Corbiere and Sons Contracting1159220220223-6Operator - Intermdiate - After Jan 1011770INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11592 | 20220223-6 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-23 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C198-C202 | Ripple Lake | 0 | 2022-03-03 |  | 37 | 2022-03-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1159220220223-6L.O.A.1210 | Corbiere and Sons Contracting1159220220223-6L.O.A.1210INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11592 | 20220223-6 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 11 |  | 0 | 0 |  |  | 880 | 114.4 | 994.4 | 2022-02-23 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C198-C202 | Ripple Lake | 0 | 2022-03-03 |  | 37 | 2022-03-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1159220220223-6Pickup w/ plow and sander11880 | Corbiere and Sons Contracting1159220220223-6Pickup w/ plow and sander11880INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11591 | 20220223-5 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 13.5 | HR |  |  | 0 | 0 | 1012.5 | 131.625 | 1144.125 | 2022-02-23 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Peninsula | 6 | C268-D005 | Peninsula | 0 | 2022-03-03 |  | 37 | 2022-03-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1159120220223-5Operator - Principle - After Jan 1013.51012.5 | Corbiere and Sons Contracting1159120220223-5Operator - Principle - After Jan 1013.51012.5INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11591 | 20220223-5 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-23 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Peninsula | 6 | C268-D005 | Peninsula | 0 | 2022-03-03 |  | 37 | 2022-03-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1159120220223-5L.O.A.1210 | Corbiere and Sons Contracting1159120220223-5L.O.A.1210INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11591 | 20220223-5 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-23 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Peninsula | 6 | C268-D005 | Peninsula | 0 | 2022-03-03 |  | 37 | 2022-03-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1159120220223-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1159120220223-5Light Truck - Pick up- After Jan 101243.75INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11591 | 20220223-5 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 12.5 | Dynamic | 0 | 0 |  |  | 1587.25 | 206.3425 | 1793.5925 | 2022-02-23 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Peninsula | 6 | C268-D005 | Peninsula | 0 | 2022-03-03 |  | 37 | 2022-03-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1159120220223-5Grader - Cat 12 to 14 or equal- After Jan 1012.51587.25 | Corbiere and Sons Contracting1159120220223-5Grader - Cat 12 to 14 or equal- After Jan 1012.51587.25INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11590 | 20220223-4 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 3 | HR |  |  | 0 | 0 | 225 | 29.25 | 254.25 | 2022-02-23 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Prairie River | 6 | C171-C185 | Prairie River | 0 | 2022-03-03 |  | 37 | 2022-03-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1159020220223-4Operator - Principle - After Jan 103225 | Corbiere and Sons Contracting1159020220223-4Operator - Principle - After Jan 103225INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11590 | 20220223-4 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-23 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Prairie River | 6 | C171-C185 | Prairie River | 0 | 2022-03-03 |  | 37 | 2022-03-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1159020220223-4L.O.A.1210 | Corbiere and Sons Contracting1159020220223-4L.O.A.1210INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11590 | 20220223-4 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-23 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Prairie River | 6 | C171-C185 | Prairie River | 0 | 2022-03-03 |  | 37 | 2022-03-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1159020220223-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1159020220223-4Light Truck - Pick up- After Jan 101243.75INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11590 | 20220223-4 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 3 | Dynamic | 0 | 0 |  |  | 380.94 | 49.5222 | 430.4622 | 2022-02-23 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Prairie River | 6 | C171-C185 | Prairie River | 0 | 2022-03-03 |  | 37 | 2022-03-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1159020220223-4Grader - Cat 12 to 14 or equal- After Jan 103380.94 | Corbiere and Sons Contracting1159020220223-4Grader - Cat 12 to 14 or equal- After Jan 103380.94INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11589 | 20220223-3 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-02-23 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Little Red Sucker Creek | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-03-03 |  | 37 | 2022-03-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1158920220223-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1158920220223-3Operator - Principle - After Jan 1011825INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11589 | 20220223-3 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-23 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Little Red Sucker Creek | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-03-03 |  | 37 | 2022-03-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1158920220223-3L.O.A.1210 | Corbiere and Sons Contracting1158920220223-3L.O.A.1210INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11589 | 20220223-3 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-23 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Little Red Sucker Creek | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-03-03 |  | 37 | 2022-03-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1158920220223-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1158920220223-3Light Truck - Pick up- After Jan 101243.75INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11589 | 20220223-3 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-02-23 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Little Red Sucker Creek | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-03-03 |  | 37 | 2022-03-08 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1158920220223-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1158920220223-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11587 | 20220222-6 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 11 | HR |  |  | 70 | 0 | 770 | 100.1 | 870.1 | 2022-02-22 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-03-03 |  | 37 | 2022-03-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1158720220222-6Operator - Intermdiate - After Jan 1011770 | Corbiere and Sons Contracting1158720220222-6Operator - Intermdiate - After Jan 1011770INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11587 | 20220222-6 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-22 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-03-03 |  | 37 | 2022-03-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1158720220222-6L.O.A.1210 | Corbiere and Sons Contracting1158720220222-6L.O.A.1210INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11587 | 20220222-6 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 11 |  | 0 | 0 |  |  | 880 | 114.4 | 994.4 | 2022-02-22 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-03-03 |  | 37 | 2022-03-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1158720220222-6Pickup w/ plow and sander11880 | Corbiere and Sons Contracting1158720220222-6Pickup w/ plow and sander11880INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11586 | 20220222-5 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-02-22 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Neys | 6 | C219-C235 | Neys | 0 | 2022-03-03 |  | 37 | 2022-03-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1158620220222-5Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1158620220222-5Operator - Principle - After Jan 1011825INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11586 | 20220222-5 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2022-02-22 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Neys | 6 | C219-C235 | Neys | 0 | 2022-03-03 |  | 37 | 2022-03-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1158620220222-5Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1158620220222-5Operator - Principle - After Jan 1011825INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11586 | 20220222-5 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 0 | 0 | 450 | 58.5 | 508.5 | 2022-02-22 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Neys | 6 | C219-C235 | Neys | 0 | 2022-03-03 |  | 37 | 2022-03-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1158620220222-5Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting1158620220222-5Operator - Principle - After Jan 106450INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11586 | 20220222-5 | 53510611 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2022-02-22 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Neys | 6 | C219-C235 | Neys | 0 | 2022-03-03 |  | 37 | 2022-03-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1158620220222-5L.O.A.3630 | Corbiere and Sons Contracting1158620220222-5L.O.A.3630INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11586 | 20220222-5 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 11 |  | 0 | 0 |  |  | 880 | 114.4 | 994.4 | 2022-02-22 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Neys | 6 | C219-C235 | Neys | 0 | 2022-03-03 |  | 37 | 2022-03-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1158620220222-5Pickup w/ plow and sander11880 | Corbiere and Sons Contracting1158620220222-5Pickup w/ plow and sander11880INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11586 | 20220222-5 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-22 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Neys | 6 | C219-C235 | Neys | 0 | 2022-03-03 |  | 37 | 2022-03-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1158620220222-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1158620220222-5Light Truck - Pick up- After Jan 101243.75INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11586 | 20220222-5 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-22 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Neys | 6 | C219-C235 | Neys | 0 | 2022-03-03 |  | 37 | 2022-03-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1158620220222-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1158620220222-5Light Truck - Pick up- After Jan 101243.75INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11586 | 20220222-5 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 3 | Dynamic | 0 | 0 |  |  | 380.94 | 49.5222 | 430.4622 | 2022-02-22 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Neys | 6 | C219-C235 | Neys | 0 | 2022-03-03 |  | 37 | 2022-03-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1158620220222-5Grader - Cat 12 to 14 or equal- After Jan 103380.94 | Corbiere and Sons Contracting1158620220222-5Grader - Cat 12 to 14 or equal- After Jan 103380.94INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11586 | 20220222-5 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10 | Dynamic | 98.61 | 0 |  |  | 1314.8 | 170.924 | 1485.724 | 2022-02-22 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Neys | 6 | C219-C235 | Neys | 0 | 2022-03-03 |  | 37 | 2022-03-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1158620220222-5Dozer D6 or equal- After Jan 10101314.8 | Corbiere and Sons Contracting1158620220222-5Dozer D6 or equal- After Jan 10101314.8INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11585 | 20220222-4 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-02-22 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Del Lake | 6 | C186-C195 | Del Lake | 0 | 2022-03-03 |  | 37 | 2022-03-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1158520220222-4Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1158520220222-4Operator - Principle - After Jan 1011825INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11585 | 20220222-4 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-22 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Del Lake | 6 | C186-C195 | Del Lake | 0 | 2022-03-03 |  | 37 | 2022-03-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1158520220222-4L.O.A.1210 | Corbiere and Sons Contracting1158520220222-4L.O.A.1210INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11585 | 20220222-4 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-22 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Del Lake | 6 | C186-C195 | Del Lake | 0 | 2022-03-03 |  | 37 | 2022-03-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1158520220222-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1158520220222-4Light Truck - Pick up- After Jan 101243.75INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11585 | 20220222-4 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-02-22 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Del Lake | 6 | C186-C195 | Del Lake | 0 | 2022-03-03 |  | 37 | 2022-03-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1158520220222-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1158520220222-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11584 | 20220222-3 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-02-22 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Little Red Sucker Creek | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-03-03 |  | 37 | 2022-03-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1158420220222-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1158420220222-3Operator - Principle - After Jan 1011825INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11584 | 20220222-3 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-22 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Little Red Sucker Creek | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-03-03 |  | 37 | 2022-03-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1158420220222-3L.O.A.1210 | Corbiere and Sons Contracting1158420220222-3L.O.A.1210INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11584 | 20220222-3 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-22 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Little Red Sucker Creek | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-03-03 |  | 37 | 2022-03-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1158420220222-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1158420220222-3Light Truck - Pick up- After Jan 101243.75INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11584 | 20220222-3 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-02-22 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Little Red Sucker Creek | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-03-03 |  | 37 | 2022-03-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1158420220222-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1158420220222-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11582 | 20220221-8 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2022-02-21 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C244-C247 | Mink Creek | 0 | 2022-03-03 |  | 37 | 2022-03-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1158220220221-8Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1158220220221-8Operator - Principle - After Jan 1012900INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11582 | 20220221-8 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2022-02-21 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C244-C247 | Mink Creek | 0 | 2022-03-03 |  | 37 | 2022-03-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1158220220221-8L.O.A.1210 | Corbiere and Sons Contracting1158220220221-8L.O.A.1210INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11582 | 20220221-8 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 12 |  | 0 | 0 |  |  | 960 | 124.8 | 1084.8 | 2022-02-21 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C244-C247 | Mink Creek | 0 | 2022-03-03 |  | 37 | 2022-03-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1158220220221-8Pickup w/ plow and sander12960 | Corbiere and Sons Contracting1158220220221-8Pickup w/ plow and sander12960INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11581 | 20220221-7 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 11 | HR |  |  | 0 | 0 | 770 | 100.1 | 870.1 | 2022-02-21 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 | 2022-03-03 |  | 37 | 2022-03-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1158120220221-7Operator - Intermdiate - After Jan 1011770 | Corbiere and Sons Contracting1158120220221-7Operator - Intermdiate - After Jan 1011770INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11581 | 20220221-7 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-21 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 | 2022-03-03 |  | 37 | 2022-03-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1158120220221-7L.O.A.1210 | Corbiere and Sons Contracting1158120220221-7L.O.A.1210INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11581 | 20220221-7 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 11 |  | 0 | 0 |  |  | 880 | 114.4 | 994.4 | 2022-02-21 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 | 2022-03-03 |  | 37 | 2022-03-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1158120220221-7Pickup w/ plow and sander11880 | Corbiere and Sons Contracting1158120220221-7Pickup w/ plow and sander11880INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11579 | 20220221-5 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-02-21 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Neys | 6 | C219-C235 | Neys | 0 | 2022-03-03 |  | 37 | 2022-03-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1157920220221-5Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1157920220221-5Operator - Principle - After Jan 1011825INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11579 | 20220221-5 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-21 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Neys | 6 | C219-C235 | Neys | 0 | 2022-03-03 |  | 37 | 2022-03-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1157920220221-5L.O.A.1210 | Corbiere and Sons Contracting1157920220221-5L.O.A.1210INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11579 | 20220221-5 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-21 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Neys | 6 | C219-C235 | Neys | 0 | 2022-03-03 |  | 37 | 2022-03-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1157920220221-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1157920220221-5Light Truck - Pick up- After Jan 101243.75INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11579 | 20220221-5 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 7 | Dynamic | 0 | 0 |  |  | 888.86 | 115.5518 | 1004.4118 | 2022-02-21 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Neys | 6 | C219-C235 | Neys | 0 | 2022-03-03 |  | 37 | 2022-03-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1157920220221-5Grader - Cat 12 to 14 or equal- After Jan 107888.86 | Corbiere and Sons Contracting1157920220221-5Grader - Cat 12 to 14 or equal- After Jan 107888.86INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11578 | 20220221-4 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-02-21 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Del Lake | 6 | C186-C195 | Del Lake | 0 | 2022-03-03 |  | 37 | 2022-03-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1157820220221-4Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1157820220221-4Operator - Principle - After Jan 1011825INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11578 | 20220221-4 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-21 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Del Lake | 6 | C186-C195 | Del Lake | 0 | 2022-03-03 |  | 37 | 2022-03-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1157820220221-4L.O.A.1210 | Corbiere and Sons Contracting1157820220221-4L.O.A.1210INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11578 | 20220221-4 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-21 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Del Lake | 6 | C186-C195 | Del Lake | 0 | 2022-03-03 |  | 37 | 2022-03-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1157820220221-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1157820220221-4Light Truck - Pick up- After Jan 101243.75INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11578 | 20220221-4 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-02-21 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Del Lake | 6 | C186-C195 | Del Lake | 0 | 2022-03-03 |  | 37 | 2022-03-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1157820220221-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1157820220221-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11577 | 20220221-3 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-02-21 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Little Red Sucker Creek | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-03-03 |  | 37 | 2022-03-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1157720220221-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1157720220221-3Operator - Principle - After Jan 1011825INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11577 | 20220221-3 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-21 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Little Red Sucker Creek | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-03-03 |  | 37 | 2022-03-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1157720220221-3L.O.A.1210 | Corbiere and Sons Contracting1157720220221-3L.O.A.1210INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11577 | 20220221-3 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-21 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Little Red Sucker Creek | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-03-03 |  | 37 | 2022-03-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1157720220221-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1157720220221-3Light Truck - Pick up- After Jan 101243.75INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11577 | 20220221-3 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-02-21 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Little Red Sucker Creek | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-03-03 |  | 37 | 2022-03-07 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1157720220221-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1157720220221-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11574 | 20220220-7 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 11 | HR |  |  | 70 | 0 | 770 | 100.1 | 870.1 | 2022-02-20 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1157420220220-7Operator - Intermdiate - After Jan 1011770 | Corbiere and Sons Contracting1157420220220-7Operator - Intermdiate - After Jan 1011770INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11574 | 20220220-7 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2022-02-20 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1157420220220-7L.O.A.1210 | Corbiere and Sons Contracting1157420220220-7L.O.A.1210INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11574 | 20220220-7 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 11 |  | 0 | 0 |  |  | 880 | 114.4 | 994.4 | 2022-02-20 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1157420220220-7Pickup w/ plow and sander11880 | Corbiere and Sons Contracting1157420220220-7Pickup w/ plow and sander11880INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11572 | 20220220-5 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5 | HR |  |  | 0 | 0 | 375 | 48.75 | 423.75 | 2022-02-20 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Neys | 6 | C219-C235 | Neys | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1157220220220-5Operator - Principle - After Jan 105375 | Corbiere and Sons Contracting1157220220220-5Operator - Principle - After Jan 105375INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11572 | 20220220-5 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-20 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Neys | 6 | C219-C235 | Neys | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1157220220220-5L.O.A.1210 | Corbiere and Sons Contracting1157220220220-5L.O.A.1210INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11572 | 20220220-5 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-20 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Neys | 6 | C219-C235 | Neys | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1157220220220-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1157220220220-5Light Truck - Pick up- After Jan 101243.75INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11572 | 20220220-5 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 4 | Dynamic | 0 | 0 |  |  | 507.92 | 66.0296 | 573.9496 | 2022-02-20 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Neys | 6 | C219-C235 | Neys | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1157220220220-5Grader - Cat 12 to 14 or equal- After Jan 104507.92 | Corbiere and Sons Contracting1157220220220-5Grader - Cat 12 to 14 or equal- After Jan 104507.92INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11571 | 20220220-4 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-02-20 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Prairie River | 6 | C171-C185 | Prairie River | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1157120220220-4Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1157120220220-4Operator - Principle - After Jan 1011825INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11571 | 20220220-4 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-20 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Prairie River | 6 | C171-C185 | Prairie River | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1157120220220-4L.O.A.1210 | Corbiere and Sons Contracting1157120220220-4L.O.A.1210INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11571 | 20220220-4 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-20 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Prairie River | 6 | C171-C185 | Prairie River | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1157120220220-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1157120220220-4Light Truck - Pick up- After Jan 101243.75INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11571 | 20220220-4 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-02-20 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Prairie River | 6 | C171-C185 | Prairie River | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1157120220220-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1157120220220-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11570 | 20220220-3 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-02-20 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Little Red Sucker Creek | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1157020220220-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1157020220220-3Operator - Principle - After Jan 1011825INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11570 | 20220220-3 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-20 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Little Red Sucker Creek | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1157020220220-3L.O.A.1210 | Corbiere and Sons Contracting1157020220220-3L.O.A.1210INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11570 | 20220220-3 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-20 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Little Red Sucker Creek | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1157020220220-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1157020220220-3Light Truck - Pick up- After Jan 101243.75INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11570 | 20220220-3 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-02-20 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Little Red Sucker Creek | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1157020220220-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1157020220220-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11567 | 20220219-8 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 11 | HR |  |  | 0 | 0 | 770 | 100.1 | 870.1 | 2022-02-19 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C257-C267 | Hare Lake Creek | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1156720220219-8Operator - Intermdiate - After Jan 1011770 | Corbiere and Sons Contracting1156720220219-8Operator - Intermdiate - After Jan 1011770INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11567 | 20220219-8 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-19 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C257-C267 | Hare Lake Creek | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1156720220219-8L.O.A.1210 | Corbiere and Sons Contracting1156720220219-8L.O.A.1210INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11567 | 20220219-8 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 11 |  | 0 | 0 |  |  | 880 | 114.4 | 994.4 | 2022-02-19 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C257-C267 | Hare Lake Creek | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1156720220219-8Pickup w/ plow and sander11880 | Corbiere and Sons Contracting1156720220219-8Pickup w/ plow and sander11880INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11564 | 20220219-5 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 3 | HR |  |  | 0 | 0 | 225 | 29.25 | 254.25 | 2022-02-19 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities neys | 6 | C219-C235 | Neys | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1156420220219-5Operator - Principle - After Jan 103225 | Corbiere and Sons Contracting1156420220219-5Operator - Principle - After Jan 103225INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11564 | 20220219-5 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-19 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities neys | 6 | C219-C235 | Neys | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1156420220219-5L.O.A.1210 | Corbiere and Sons Contracting1156420220219-5L.O.A.1210INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11564 | 20220219-5 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-19 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities neys | 6 | C219-C235 | Neys | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1156420220219-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1156420220219-5Light Truck - Pick up- After Jan 101243.75INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11564 | 20220219-5 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 3 | Dynamic | 0 | 0 |  |  | 380.94 | 49.5222 | 430.4622 | 2022-02-19 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities neys | 6 | C219-C235 | Neys | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1156420220219-5Grader - Cat 12 to 14 or equal- After Jan 103380.94 | Corbiere and Sons Contracting1156420220219-5Grader - Cat 12 to 14 or equal- After Jan 103380.94INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11563 | 20220219-4 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-02-19 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Prairie River | 6 | C171-C185 | Prairie River | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1156320220219-4Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1156320220219-4Operator - Principle - After Jan 1011825INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11563 | 20220219-4 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-19 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Prairie River | 6 | C171-C185 | Prairie River | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1156320220219-4L.O.A.1210 | Corbiere and Sons Contracting1156320220219-4L.O.A.1210INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11563 | 20220219-4 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-19 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Prairie River | 6 | C171-C185 | Prairie River | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1156320220219-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1156320220219-4Light Truck - Pick up- After Jan 101243.75INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11563 | 20220219-4 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-02-19 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Prairie River | 6 | C171-C185 | Prairie River | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1156320220219-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1156320220219-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11562 | 20220219-3 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-02-19 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Little Red Sucker Creek | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1156220220219-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1156220220219-3Operator - Principle - After Jan 1011825INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11562 | 20220219-3 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-19 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Little Red Sucker Creek | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1156220220219-3L.O.A.1210 | Corbiere and Sons Contracting1156220220219-3L.O.A.1210INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11562 | 20220219-3 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-19 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Little Red Sucker Creek | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1156220220219-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1156220220219-3Light Truck - Pick up- After Jan 101243.75INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11562 | 20220219-3 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-02-19 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Little Red Sucker Creek | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1156220220219-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1156220220219-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11560 | 20220218-7 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2022-02-18 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1156020220218-7Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1156020220218-7Operator - Principle - After Jan 1012900INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11560 | 20220218-7 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-18 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1156020220218-7L.O.A.1210 | Corbiere and Sons Contracting1156020220218-7L.O.A.1210INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11560 | 20220218-7 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 12 |  | 0 | 0 |  |  | 960 | 124.8 | 1084.8 | 2022-02-18 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1156020220218-7Pickup w/ plow and sander12960 | Corbiere and Sons Contracting1156020220218-7Pickup w/ plow and sander12960INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11558 | 20220218-5 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-02-18 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Neys | 6 | C219-C235 | Neys | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1155820220218-5Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1155820220218-5Operator - Principle - After Jan 1011825INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11558 | 20220218-5 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-18 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Neys | 6 | C219-C235 | Neys | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1155820220218-5L.O.A.1210 | Corbiere and Sons Contracting1155820220218-5L.O.A.1210INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11558 | 20220218-5 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-18 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Neys | 6 | C219-C235 | Neys | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1155820220218-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1155820220218-5Light Truck - Pick up- After Jan 101243.75INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11558 | 20220218-5 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 8 | Dynamic | 0 | 0 |  |  | 1015.84 | 132.0592 | 1147.8992 | 2022-02-18 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Neys | 6 | C219-C235 | Neys | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1155820220218-5Grader - Cat 12 to 14 or equal- After Jan 1081015.84 | Corbiere and Sons Contracting1155820220218-5Grader - Cat 12 to 14 or equal- After Jan 1081015.84INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11557 | 20220218-4 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-02-18 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Del Lake | 6 | C186-C195 | Del Lake | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1155720220218-4Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1155720220218-4Operator - Principle - After Jan 1011825INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11557 | 20220218-4 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-18 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Del Lake | 6 | C186-C195 | Del Lake | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1155720220218-4L.O.A.1210 | Corbiere and Sons Contracting1155720220218-4L.O.A.1210INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11557 | 20220218-4 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-18 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Del Lake | 6 | C186-C195 | Del Lake | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1155720220218-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1155720220218-4Light Truck - Pick up- After Jan 101243.75INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11557 | 20220218-4 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-02-18 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Del Lake | 6 | C186-C195 | Del Lake | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1155720220218-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1155720220218-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11556 | 20220218-3 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-02-18 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Little Red Sucker Creek | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1155620220218-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1155620220218-3Operator - Principle - After Jan 1011825INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11556 | 20220218-3 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-18 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Little Red Sucker Creek | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1155620220218-3L.O.A.1210 | Corbiere and Sons Contracting1155620220218-3L.O.A.1210INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11556 | 20220218-3 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-18 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Little Red Sucker Creek | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1155620220218-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1155620220218-3Light Truck - Pick up- After Jan 101243.75INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11556 | 20220218-3 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-02-18 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Little Red Sucker Creek | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1155620220218-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1155620220218-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11554 | 20220217-7 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 9 | HR |  |  | 75 | 0 | 675 | 87.75 | 762.75 | 2022-02-17 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C268-D005 | Peninsula | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1155420220217-7Operator - Principle - After Jan 109675 | Corbiere and Sons Contracting1155420220217-7Operator - Principle - After Jan 109675INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11554 | 20220217-7 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5 | HR |  |  | 75 | 0 | 375 | 48.75 | 423.75 | 2022-02-17 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C268-D005 | Peninsula | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1155420220217-7Operator - Principle - After Jan 105375 | Corbiere and Sons Contracting1155420220217-7Operator - Principle - After Jan 105375INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11554 | 20220217-7 | 53510611 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2022-02-17 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C268-D005 | Peninsula | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1155420220217-7L.O.A.2420 | Corbiere and Sons Contracting1155420220217-7L.O.A.2420INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11554 | 20220217-7 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 10 |  | 0 | 0 |  |  | 800 | 104 | 904 | 2022-02-17 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C268-D005 | Peninsula | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1155420220217-7Pickup w/ plow and sander10800 | Corbiere and Sons Contracting1155420220217-7Pickup w/ plow and sander10800INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11553 | 20220217-6 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 11 | HR |  |  | 0 | 0 | 770 | 100.1 | 870.1 | 2022-02-17 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1155320220217-6Operator - Intermdiate - After Jan 1011770 | Corbiere and Sons Contracting1155320220217-6Operator - Intermdiate - After Jan 1011770INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11553 | 20220217-6 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-17 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1155320220217-6L.O.A.1210 | Corbiere and Sons Contracting1155320220217-6L.O.A.1210INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11553 | 20220217-6 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 11 |  | 0 | 0 |  |  | 880 | 114.4 | 994.4 | 2022-02-17 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C130-C151 | Lake A | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1155320220217-6Pickup w/ plow and sander11880 | Corbiere and Sons Contracting1155320220217-6Pickup w/ plow and sander11880INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11552 | 20220217-5 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-02-17 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities neys | 6 | C219-C235 | Neys | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1155220220217-5Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1155220220217-5Operator - Principle - After Jan 1011825INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11552 | 20220217-5 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-17 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities neys | 6 | C219-C235 | Neys | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1155220220217-5L.O.A.1210 | Corbiere and Sons Contracting1155220220217-5L.O.A.1210INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11552 | 20220217-5 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-17 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities neys | 6 | C219-C235 | Neys | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1155220220217-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1155220220217-5Light Truck - Pick up- After Jan 101243.75INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11552 | 20220217-5 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-02-17 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities neys | 6 | C219-C235 | Neys | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1155220220217-5Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1155220220217-5Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11550 | 20220217-3 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-02-17 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Little Red Sucker Creek | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1155020220217-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1155020220217-3Operator - Principle - After Jan 1011825INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11550 | 20220217-3 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-17 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Little Red Sucker Creek | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1155020220217-3L.O.A.1210 | Corbiere and Sons Contracting1155020220217-3L.O.A.1210INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11550 | 20220217-3 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-17 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Little Red Sucker Creek | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1155020220217-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1155020220217-3Light Truck - Pick up- After Jan 101243.75INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11550 | 20220217-3 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-02-17 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Little Red Sucker Creek | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1155020220217-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1155020220217-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11548 | 20220216-8 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2022-02-16 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C268-D005 | Peninsula | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1154820220216-8Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1154820220216-8Operator - Principle - After Jan 1012900INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11548 | 20220216-8 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-16 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C268-D005 | Peninsula | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1154820220216-8L.O.A.1210 | Corbiere and Sons Contracting1154820220216-8L.O.A.1210INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11548 | 20220216-8 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 12 |  | 0 | 0 |  |  | 960 | 124.8 | 1084.8 | 2022-02-16 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C268-D005 | Peninsula | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1154820220216-8Pickup w/ plow and sander12960 | Corbiere and Sons Contracting1154820220216-8Pickup w/ plow and sander12960INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11547 | 20220216-7 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 0 | 0 | 900 | 117 | 1017 | 2022-02-16 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1154720220216-7Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1154720220216-7Operator - Principle - After Jan 1012900INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11547 | 20220216-7 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-16 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1154720220216-7Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1154720220216-7Light Truck - Pick up- After Jan 101243.75INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11547 | 20220216-7 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 8 | Dynamic | 0 | 0 |  |  | 1051.84 | 136.7392 | 1188.5792 | 2022-02-16 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1154720220216-7Dozer D6 or equal- After Jan 1081051.84 | Corbiere and Sons Contracting1154720220216-7Dozer D6 or equal- After Jan 1081051.84INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11546 | 20220216-6 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 12 | HR |  |  | 70 | 0 | 840 | 109.2 | 949.2 | 2022-02-16 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C171-C185 | Prairie River | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1154620220216-6Operator - Intermdiate - After Jan 1012840 | Corbiere and Sons Contracting1154620220216-6Operator - Intermdiate - After Jan 1012840INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11546 | 20220216-6 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2022-02-16 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C171-C185 | Prairie River | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1154620220216-6L.O.A.1210 | Corbiere and Sons Contracting1154620220216-6L.O.A.1210INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11546 | 20220216-6 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 7 |  | 0 | 0 |  |  | 560 | 72.8 | 632.8 | 2022-02-16 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C171-C185 | Prairie River | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1154620220216-6Pickup w/ plow and sander7560 | Corbiere and Sons Contracting1154620220216-6Pickup w/ plow and sander7560INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11545 | 20220216-5 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 0 | 0 | 900 | 117 | 1017 | 2022-02-16 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Neys | 6 | C219-C235 | Neys | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1154520220216-5Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1154520220216-5Operator - Principle - After Jan 1012900INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11545 | 20220216-5 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-16 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Neys | 6 | C219-C235 | Neys | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1154520220216-5L.O.A.1210 | Corbiere and Sons Contracting1154520220216-5L.O.A.1210INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11545 | 20220216-5 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-16 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Neys | 6 | C219-C235 | Neys | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1154520220216-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1154520220216-5Light Truck - Pick up- After Jan 101243.75INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11545 | 20220216-5 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 11 | Dynamic | 0 | 0 |  |  | 1396.78 | 181.5814 | 1578.3614 | 2022-02-16 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Neys | 6 | C219-C235 | Neys | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1154520220216-5Grader - Cat 12 to 14 or equal- After Jan 10111396.78 | Corbiere and Sons Contracting1154520220216-5Grader - Cat 12 to 14 or equal- After Jan 10111396.78INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11544 | 20220216-4 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 0 | 0 | 900 | 117 | 1017 | 2022-02-16 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Del Lake | 6 | C186-C195 | Del Lake | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1154420220216-4Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1154420220216-4Operator - Principle - After Jan 1012900INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11544 | 20220216-4 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-16 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Del Lake | 6 | C186-C195 | Del Lake | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1154420220216-4L.O.A.1210 | Corbiere and Sons Contracting1154420220216-4L.O.A.1210INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11544 | 20220216-4 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-16 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Del Lake | 6 | C186-C195 | Del Lake | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1154420220216-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1154420220216-4Light Truck - Pick up- After Jan 101243.75INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11544 | 20220216-4 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 8.5 | Dynamic | 0 | 0 |  |  | 1079.33 | 140.3129 | 1219.6429 | 2022-02-16 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Del Lake | 6 | C186-C195 | Del Lake | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1154420220216-4Grader - Cat 12 to 14 or equal- After Jan 108.51079.33 | Corbiere and Sons Contracting1154420220216-4Grader - Cat 12 to 14 or equal- After Jan 108.51079.33INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11543 | 20220216-3 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 0 | 0 | 900 | 117 | 1017 | 2022-02-16 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Little Red Sucker Creek | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1154320220216-3Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1154320220216-3Operator - Principle - After Jan 1012900INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11543 | 20220216-3 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-16 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Little Red Sucker Creek | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1154320220216-3L.O.A.1210 | Corbiere and Sons Contracting1154320220216-3L.O.A.1210INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11543 | 20220216-3 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-16 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Little Red Sucker Creek | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1154320220216-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1154320220216-3Light Truck - Pick up- After Jan 101243.75INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11543 | 20220216-3 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 11 | Dynamic | 0 | 0 |  |  | 1396.78 | 181.5814 | 1578.3614 | 2022-02-16 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Little Red Sucker Creek | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2022-02-23 |  | 36 | 2022-02-24 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1154320220216-3Grader - Cat 12 to 14 or equal- After Jan 10111396.78 | Corbiere and Sons Contracting1154320220216-3Grader - Cat 12 to 14 or equal- After Jan 10111396.78INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11541 | 20220215-8 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 11 | HR |  |  | 70 | 0 | 770 | 100.1 | 870.1 | 2022-02-15 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-02-23 |  | 36 | 2022-02-25 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1154120220215-8Driver - AZ - After Jan 1011770 | Corbiere and Sons Contracting1154120220215-8Driver - AZ - After Jan 1011770INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11541 | 20220215-8 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 7 | HR |  |  | 0 | 0 | 525 | 68.25 | 593.25 | 2022-02-15 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-02-23 |  | 36 | 2022-02-25 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1154120220215-8Operator - Principle - After Jan 107525 | Corbiere and Sons Contracting1154120220215-8Operator - Principle - After Jan 107525INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11541 | 20220215-8 | 53510611 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 11 | Dynamic | 91.79 | 0 |  |  | 1346.29 | 175.0177 | 1521.3077 | 2022-02-15 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-02-23 |  | 36 | 2022-02-25 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1154120220215-8Tractor Trailer - 60 Ton- After Jan 10111346.29 | Corbiere and Sons Contracting1154120220215-8Tractor Trailer - 60 Ton- After Jan 10111346.29INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11541 | 20220215-8 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 4 | Dynamic | 0 | 0 |  |  | 525.92 | 68.3696 | 594.2896 | 2022-02-15 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-02-23 |  | 36 | 2022-02-25 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1154120220215-8Dozer D6 or equal- After Jan 104525.92 | Corbiere and Sons Contracting1154120220215-8Dozer D6 or equal- After Jan 104525.92INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11540 | 20220215-7 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 10 | HR |  |  | 0 | 0 | 700 | 91 | 791 | 2022-02-15 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C171-C185 | Prairie River | 0 | 2022-02-23 |  | 36 | 2022-02-25 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1154020220215-7Operator - Intermdiate - After Jan 1010700 | Corbiere and Sons Contracting1154020220215-7Operator - Intermdiate - After Jan 1010700INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11540 | 20220215-7 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-15 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C171-C185 | Prairie River | 0 | 2022-02-23 |  | 36 | 2022-02-25 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1154020220215-7L.O.A.1210 | Corbiere and Sons Contracting1154020220215-7L.O.A.1210INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11540 | 20220215-7 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 10 |  | 0 | 0 |  |  | 800 | 104 | 904 | 2022-02-15 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C171-C185 | Prairie River | 0 | 2022-02-23 |  | 36 | 2022-02-25 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1154020220215-7Pickup w/ plow and sander10800 | Corbiere and Sons Contracting1154020220215-7Pickup w/ plow and sander10800INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11538 | 20220215-5 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2022-02-15 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities neys | 6 | C219-C236 | Neys | 0 | 2022-02-23 |  | 36 | 2022-02-25 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1153820220215-5Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1153820220215-5Operator - Principle - After Jan 1012900INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11538 | 20220215-5 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 10 | HR |  |  | 0 | 0 | 750 | 97.5 | 847.5 | 2022-02-15 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities neys | 6 | C219-C236 | Neys | 0 | 2022-02-23 |  | 36 | 2022-02-25 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1153820220215-5Operator - Principle - After Jan 1010750 | Corbiere and Sons Contracting1153820220215-5Operator - Principle - After Jan 1010750INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11538 | 20220215-5 | 53510611 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2022-02-15 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities neys | 6 | C219-C236 | Neys | 0 | 2022-02-23 |  | 36 | 2022-02-25 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1153820220215-5L.O.A.2420 | Corbiere and Sons Contracting1153820220215-5L.O.A.2420INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11538 | 20220215-5 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 12 |  | 0 | 0 |  |  | 960 | 124.8 | 1084.8 | 2022-02-15 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities neys | 6 | C219-C236 | Neys | 0 | 2022-02-23 |  | 36 | 2022-02-25 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1153820220215-5Pickup w/ plow and sander12960 | Corbiere and Sons Contracting1153820220215-5Pickup w/ plow and sander12960INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11538 | 20220215-5 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-15 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities neys | 6 | C219-C236 | Neys | 0 | 2022-02-23 |  | 36 | 2022-02-25 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1153820220215-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1153820220215-5Light Truck - Pick up- After Jan 101243.75INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11538 | 20220215-5 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 9 | Dynamic | 0 | 0 |  |  | 1142.82 | 148.5666 | 1291.3866 | 2022-02-15 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities neys | 6 | C219-C236 | Neys | 0 | 2022-02-23 |  | 36 | 2022-02-25 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1153820220215-5Grader - Cat 12 to 14 or equal- After Jan 1091142.82 | Corbiere and Sons Contracting1153820220215-5Grader - Cat 12 to 14 or equal- After Jan 1091142.82INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11537 | 20220215-3 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 10 | HR |  |  | 0 | 0 | 750 | 97.5 | 847.5 | 2022-02-15 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Little Red Sucker Creek | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2022-02-23 |  | 36 | 2022-02-25 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1153720220215-3Operator - Principle - After Jan 1010750 | Corbiere and Sons Contracting1153720220215-3Operator - Principle - After Jan 1010750INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11537 | 20220215-3 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-15 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Little Red Sucker Creek | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2022-02-23 |  | 36 | 2022-02-25 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1153720220215-3L.O.A.1210 | Corbiere and Sons Contracting1153720220215-3L.O.A.1210INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11537 | 20220215-3 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-15 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Little Red Sucker Creek | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2022-02-23 |  | 36 | 2022-02-25 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1153720220215-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1153720220215-3Light Truck - Pick up- After Jan 101243.75INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11537 | 20220215-3 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 9 | Dynamic | 0 | 0 |  |  | 1142.82 | 148.5666 | 1291.3866 | 2022-02-15 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Little Red Sucker Creek | 6 | C248-C257 | Little Red Sucker Creek | 0 | 2022-02-23 |  | 36 | 2022-02-25 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1153720220215-3Grader - Cat 12 to 14 or equal- After Jan 1091142.82 | Corbiere and Sons Contracting1153720220215-3Grader - Cat 12 to 14 or equal- After Jan 1091142.82INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11535 | 20220214-9 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2022-02-14 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C268-D005 | Peninsula | 0 | 2022-02-18 |  | 36 | 2022-02-23 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1153520220214-9Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1153520220214-9Operator - Principle - After Jan 1012900INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11535 | 20220214-9 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2022-02-14 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C268-D005 | Peninsula | 0 | 2022-02-18 |  | 36 | 2022-02-23 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1153520220214-9L.O.A.1210 | Corbiere and Sons Contracting1153520220214-9L.O.A.1210INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11535 | 20220214-9 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 12 |  | 0 | 0 |  |  | 960 | 124.8 | 1084.8 | 2022-02-14 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C268-D005 | Peninsula | 0 | 2022-02-18 |  | 36 | 2022-02-23 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1153520220214-9Pickup w/ plow and sander12960 | Corbiere and Sons Contracting1153520220214-9Pickup w/ plow and sander12960INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11534 | 20220214-8 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 7 | HR |  |  | 75 | 0 | 525 | 68.25 | 593.25 | 2022-02-14 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activitites Santoy Lake | 6 | C158-C170 | Santoy Lake | 0 | 2022-02-18 |  | 36 | 2022-02-23 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1153420220214-8Operator - Principle - After Jan 107525 | Corbiere and Sons Contracting1153420220214-8Operator - Principle - After Jan 107525INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11534 | 20220214-8 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 7 | Dynamic | 95.24 | 0 |  |  | 888.86 | 115.5518 | 1004.4118 | 2022-02-14 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM activitites Santoy Lake | 6 | C158-C170 | Santoy Lake | 0 | 2022-02-18 |  | 36 | 2022-02-23 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1153420220214-8Grader - Cat 12 to 14 or equal- After Jan 107888.86 | Corbiere and Sons Contracting1153420220214-8Grader - Cat 12 to 14 or equal- After Jan 107888.86INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11533 | 20220214-7 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 11 | HR |  |  | 70 | 0 | 770 | 100.1 | 870.1 | 2022-02-14 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C152-C157 | Jackfish Lake | 0 | 2022-02-18 |  | 36 | 2022-02-23 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1153320220214-7Operator - Intermdiate - After Jan 1011770 | Corbiere and Sons Contracting1153320220214-7Operator - Intermdiate - After Jan 1011770INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11533 | 20220214-7 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-14 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C152-C157 | Jackfish Lake | 0 | 2022-02-18 |  | 36 | 2022-02-23 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1153320220214-7L.O.A.1210 | Corbiere and Sons Contracting1153320220214-7L.O.A.1210INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11533 | 20220214-7 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 11 |  | 0 | 0 |  |  | 880 | 114.4 | 994.4 | 2022-02-14 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C152-C157 | Jackfish Lake | 0 | 2022-02-18 |  | 36 | 2022-02-23 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1153320220214-7Pickup w/ plow and sander11880 | Corbiere and Sons Contracting1153320220214-7Pickup w/ plow and sander11880INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11531 | 20220214-5 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 4 | HR |  |  | 70 | 0 | 280 | 36.4 | 316.4 | 2022-02-14 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Neys | 6 | C219-C236 | Neys | 0 | 2022-02-18 |  | 36 | 2022-02-23 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1153120220214-5Driver - AZ - After Jan 104280 | Corbiere and Sons Contracting1153120220214-5Driver - AZ - After Jan 104280INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11531 | 20220214-5 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 4 | HR |  |  | 0 | 0 | 300 | 39 | 339 | 2022-02-14 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Neys | 6 | C219-C236 | Neys | 0 | 2022-02-18 |  | 36 | 2022-02-23 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1153120220214-5Operator - Principle - After Jan 104300 | Corbiere and Sons Contracting1153120220214-5Operator - Principle - After Jan 104300INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11531 | 20220214-5 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2022-02-14 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Neys | 6 | C219-C236 | Neys | 0 | 2022-02-18 |  | 36 | 2022-02-23 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1153120220214-5L.O.A.1210 | Corbiere and Sons Contracting1153120220214-5L.O.A.1210INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11531 | 20220214-5 | 53510611 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 4 | Dynamic | 91.79 | 0 |  |  | 489.56 | 63.6428 | 553.2028 | 2022-02-14 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Neys | 6 | C219-C236 | Neys | 0 | 2022-02-18 |  | 36 | 2022-02-23 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1153120220214-5Tractor Trailer - 60 Ton- After Jan 104489.56 | Corbiere and Sons Contracting1153120220214-5Tractor Trailer - 60 Ton- After Jan 104489.56INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11531 | 20220214-5 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-14 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Neys | 6 | C219-C236 | Neys | 0 | 2022-02-18 |  | 36 | 2022-02-23 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1153120220214-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1153120220214-5Light Truck - Pick up- After Jan 101243.75INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11531 | 20220214-5 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 2 | Dynamic | 0 | 0 |  |  | 253.96 | 33.0148 | 286.9748 | 2022-02-14 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Neys | 6 | C219-C236 | Neys | 0 | 2022-02-18 |  | 36 | 2022-02-23 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1153120220214-5Grader - Cat 12 to 14 or equal- After Jan 102253.96 | Corbiere and Sons Contracting1153120220214-5Grader - Cat 12 to 14 or equal- After Jan 102253.96INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11530 | 20220214-4 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-02-14 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Prairie River | 6 | C171-C185 | Prairie River | 0 | 2022-02-18 |  | 36 | 2022-02-23 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1153020220214-4Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1153020220214-4Operator - Principle - After Jan 1011825INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11530 | 20220214-4 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-14 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Prairie River | 6 | C171-C185 | Prairie River | 0 | 2022-02-18 |  | 36 | 2022-02-23 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1153020220214-4L.O.A.1210 | Corbiere and Sons Contracting1153020220214-4L.O.A.1210INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11530 | 20220214-4 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-14 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Prairie River | 6 | C171-C185 | Prairie River | 0 | 2022-02-18 |  | 36 | 2022-02-23 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1153020220214-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1153020220214-4Light Truck - Pick up- After Jan 101243.75INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11530 | 20220214-4 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 6 | Dynamic | 0 | 0 |  |  | 761.88 | 99.0444 | 860.9244 | 2022-02-14 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Prairie River | 6 | C171-C185 | Prairie River | 0 | 2022-02-18 |  | 36 | 2022-02-23 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1153020220214-4Grader - Cat 12 to 14 or equal- After Jan 106761.88 | Corbiere and Sons Contracting1153020220214-4Grader - Cat 12 to 14 or equal- After Jan 106761.88INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11529 | 20220214-3 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-02-14 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Little Red Sucker Creek | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-02-18 |  | 36 | 2022-02-23 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1152920220214-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1152920220214-3Operator - Principle - After Jan 1011825INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11529 | 20220214-3 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-02-14 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Little Red Sucker Creek | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-02-18 |  | 36 | 2022-02-23 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1152920220214-3L.O.A.1210 | Corbiere and Sons Contracting1152920220214-3L.O.A.1210INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11529 | 20220214-3 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-02-14 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Little Red Sucker Creek | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-02-18 |  | 36 | 2022-02-23 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1152920220214-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1152920220214-3Light Truck - Pick up- After Jan 101243.75INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11529 | 20220214-3 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-02-14 | 0 | INV #165 | 2022-03-14 | 178 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities Little Red Sucker Creek | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2022-02-18 |  | 36 | 2022-02-23 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1152920220214-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1152920220214-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #165 | CZ - Winter Maintenance |  | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10638 | 20211130-9 | 53530601 | Rig/Access Mats | 0 | Driver - AZ - After Jan 10 | 70 | 5 | HR |  |  | 70 | 0 | 350 | 45.5 | 395.5 | 2021-11-30 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float mobilized 7 Rig Mats to Lake A | 6 | C130-C151 | Lake A | 0 | 2021-12-08 |  | 37 | 2021-12-12 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1063820211130-9Driver - AZ - After Jan 105350 | Corbiere and Sons Contracting1063820211130-9Driver - AZ - After Jan 105350INV# 157 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Corbiere and Sons Contracting | 6 | 0 | 10638 | 20211130-9 | 53530601 | Rig/Access Mats | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-11-30 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float mobilized 7 Rig Mats to Lake A | 6 | C130-C151 | Lake A | 0 | 2021-12-08 |  | 37 | 2021-12-12 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1063820211130-9L.O.A.1210 | Corbiere and Sons Contracting1063820211130-9L.O.A.1210INV# 157 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Corbiere and Sons Contracting | 6 | 0 | 10638 | 20211130-9 | 53530601 | Rig/Access Mats | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 5 | Dynamic | 91.79 | 0 |  |  | 611.95 | 79.5535 | 691.5035 | 2021-11-30 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float mobilized 7 Rig Mats to Lake A | 6 | C130-C151 | Lake A | 0 | 2021-12-08 |  | 37 | 2021-12-12 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1063820211130-9Tractor Trailer - 60 Ton- After Jan 105611.95 | Corbiere and Sons Contracting1063820211130-9Tractor Trailer - 60 Ton- After Jan 105611.95INV# 157 | Rig/Access Mat Handling |  | Rig/Access Mat Handling
Corbiere and Sons Contracting | 6 | 0 | 10607 | 20211012-7 | 53510612 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 8 | HR |  |  | 70 | 0 | 560 | 72.8 | 632.8 | 2021-10-12 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader floated to Jackfish Pit to fix road | 6 | C152 - C157 | Jackfish Lake | 0 | 2021-12-08 |  | 36 | 2021-12-10 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1060720211012-7Driver - AZ - After Jan 108560 | Corbiere and Sons Contracting1060720211012-7Driver - AZ - After Jan 108560INV# 157 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10607 | 20211012-7 | 53510612 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 8 | HR |  |  | 75 | 0 | 600 | 78 | 678 | 2021-10-12 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader floated to Jackfish Pit to fix road | 6 | C152 - C157 | Jackfish Lake | 0 | 2021-12-08 |  | 36 | 2021-12-10 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1060720211012-7Operator - Principle - After Jan 108600 | Corbiere and Sons Contracting1060720211012-7Operator - Principle - After Jan 108600INV# 157 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10607 | 20211012-7 | 53510612 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 8 | Dynamic | 91.79 | 0 |  |  | 979.12 | 127.2856 | 1106.4056 | 2021-10-12 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader floated to Jackfish Pit to fix road | 6 | C152 - C157 | Jackfish Lake | 0 | 2021-12-08 |  | 36 | 2021-12-10 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1060720211012-7Tractor Trailer - 60 Ton- After Jan 108979.12 | Corbiere and Sons Contracting1060720211012-7Tractor Trailer - 60 Ton- After Jan 108979.12INV# 157 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10607 | 20211012-7 | 53510612 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-10-12 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader floated to Jackfish Pit to fix road | 6 | C152 - C157 | Jackfish Lake | 0 | 2021-12-08 |  | 36 | 2021-12-10 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1060720211012-7Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1060720211012-7Light Truck - Pick up- After Jan 101243.75INV# 157 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10607 | 20211012-7 | 53510612 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 3 | Dynamic | 95.24 | 0 |  |  | 380.94 | 49.5222 | 430.4622 | 2021-10-12 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader floated to Jackfish Pit to fix road | 6 | C152 - C157 | Jackfish Lake | 0 | 2021-12-08 |  | 36 | 2021-12-10 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1060720211012-7Grader - Cat 12 to 14 or equal- After Jan 103380.94 | Corbiere and Sons Contracting1060720211012-7Grader - Cat 12 to 14 or equal- After Jan 103380.94INV# 157 |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10744 | 20211208-14 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 5.5 | HR |  |  | 70 | 0 | 385 | 50.05 | 435.05 | 2021-12-08 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2021-12-12 |  | 36 | 2021-12-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1074420211208-14Operator - Intermdiate - After Jan 105.5385 | Corbiere and Sons Contracting1074420211208-14Operator - Intermdiate - After Jan 105.5385INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10744 | 20211208-14 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 5.5 |  | 0 | 0 |  |  | 440 | 57.2 | 497.2 | 2021-12-08 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2021-12-12 |  | 36 | 2021-12-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1074420211208-14Pickup w/ plow and sander5.5440 | Corbiere and Sons Contracting1074420211208-14Pickup w/ plow and sander5.5440INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10743 | 20211208-13 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 5.5 | HR |  |  | 70 | 0 | 385 | 50.05 | 435.05 | 2021-12-08 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Pickup w/plow and Sander working across Neys | 6 | C219-C235 | Neys | 0 | 2021-12-12 |  | 36 | 2021-12-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1074320211208-13Operator - Intermdiate - After Jan 105.5385 | Corbiere and Sons Contracting1074320211208-13Operator - Intermdiate - After Jan 105.5385INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10743 | 20211208-13 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-12-08 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Pickup w/plow and Sander working across Neys | 6 | C219-C235 | Neys | 0 | 2021-12-12 |  | 36 | 2021-12-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1074320211208-13L.O.A.1210 | Corbiere and Sons Contracting1074320211208-13L.O.A.1210INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10743 | 20211208-13 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 5.5 |  | 0 | 0 |  |  | 440 | 57.2 | 497.2 | 2021-12-08 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Pickup w/plow and Sander working across Neys | 6 | C219-C235 | Neys | 0 | 2021-12-12 |  | 36 | 2021-12-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1074320211208-13Pickup w/ plow and sander5.5440 | Corbiere and Sons Contracting1074320211208-13Pickup w/ plow and sander5.5440INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10741 | 20211208-11 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 9 | HR |  |  | 75 | 0 | 675 | 87.75 | 762.75 | 2021-12-08 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ron did WAM on Prairie River Road for 9 hours | 6 | C171-C185 | Prairie River | 0 | 2021-12-12 |  | 36 | 2021-12-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1074120211208-11Operator - Principle - After Jan 109675 | Corbiere and Sons Contracting1074120211208-11Operator - Principle - After Jan 109675INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10741 | 20211208-11 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-12-08 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ron did WAM on Prairie River Road for 9 hours | 6 | C171-C185 | Prairie River | 0 | 2021-12-12 |  | 36 | 2021-12-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1074120211208-11L.O.A.1210 | Corbiere and Sons Contracting1074120211208-11L.O.A.1210INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10741 | 20211208-11 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 8 | Dynamic | 98.61 | 0 |  |  | 1051.84 | 136.7392 | 1188.5792 | 2021-12-08 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ron did WAM on Prairie River Road for 9 hours | 6 | C171-C185 | Prairie River | 0 | 2021-12-12 |  | 36 | 2021-12-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1074120211208-11Dozer D6 or equal- After Jan 1081051.84 | Corbiere and Sons Contracting1074120211208-11Dozer D6 or equal- After Jan 1081051.84INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10724 | 20211207-7 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-12-07 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ex scratching hill and clearing snow towards snow making activities | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-12-12 |  | 36 | 2021-12-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1072420211207-7Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1072420211207-7Operator - Principle - After Jan 1011825INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10724 | 20211207-7 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-12-07 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ex scratching hill and clearing snow towards snow making activities | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-12-12 |  | 36 | 2021-12-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1072420211207-7L.O.A.1210 | Corbiere and Sons Contracting1072420211207-7L.O.A.1210INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10724 | 20211207-7 | 53510611 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 9.16 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2021-12-07 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ex scratching hill and clearing snow towards snow making activities | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-12-12 |  | 36 | 2021-12-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1072420211207-7Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting1072420211207-7Excavator Thumb - 30 - 50 ton- After Jan 1010122.1INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10724 | 20211207-7 | 53510611 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10 | Dynamic | 110.22 | 0 |  |  | 1469.6 | 191.048 | 1660.648 | 2021-12-07 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ex scratching hill and clearing snow towards snow making activities | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-12-12 |  | 36 | 2021-12-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1072420211207-7Excavator - 36 ton- After Jan 10101469.6 | Corbiere and Sons Contracting1072420211207-7Excavator - 36 ton- After Jan 10101469.6INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10732 | 20211207-15 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 3 | HR |  |  | 70 | 0 | 210 | 27.3 | 237.3 | 2021-12-07 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2021-12-12 |  | 36 | 2021-12-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1073220211207-15Operator - Intermdiate - After Jan 103210 | Corbiere and Sons Contracting1073220211207-15Operator - Intermdiate - After Jan 103210INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10732 | 20211207-15 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 3 |  | 0 | 0 |  |  | 240 | 31.2 | 271.2 | 2021-12-07 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2021-12-12 |  | 36 | 2021-12-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1073220211207-15Pickup w/ plow and sander3240 | Corbiere and Sons Contracting1073220211207-15Pickup w/ plow and sander3240INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10731 | 20211207-14 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 3 | HR |  |  | 70 | 0 | 210 | 27.3 | 237.3 | 2021-12-07 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-12-12 |  | 36 | 2021-12-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1073120211207-14Operator - Intermdiate - After Jan 103210 | Corbiere and Sons Contracting1073120211207-14Operator - Intermdiate - After Jan 103210INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10731 | 20211207-14 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 3 |  | 0 | 0 |  |  | 240 | 31.2 | 271.2 | 2021-12-07 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WAM Activities | 6 | C257-C267 | Hare Lake Creek | 0 | 2021-12-12 |  | 36 | 2021-12-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1073120211207-14Pickup w/ plow and sander3240 | Corbiere and Sons Contracting1073120211207-14Pickup w/ plow and sander3240INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10729 | 20211207-12 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 3 | HR |  |  | 70 | 0 | 210 | 27.3 | 237.3 | 2021-12-07 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Pickup w/plow and Sander working across Neys | 6 | C219-C235 | Neys | 0 | 2021-12-12 |  | 36 | 2021-12-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1072920211207-12Operator - Intermdiate - After Jan 103210 | Corbiere and Sons Contracting1072920211207-12Operator - Intermdiate - After Jan 103210INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10729 | 20211207-12 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-12-07 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Pickup w/plow and Sander working across Neys | 6 | C219-C235 | Neys | 0 | 2021-12-12 |  | 36 | 2021-12-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1072920211207-12L.O.A.1210 | Corbiere and Sons Contracting1072920211207-12L.O.A.1210INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10729 | 20211207-12 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 3 |  | 0 | 0 |  |  | 240 | 31.2 | 271.2 | 2021-12-07 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Pickup w/plow and Sander working across Neys | 6 | C219-C235 | Neys | 0 | 2021-12-12 |  | 36 | 2021-12-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1072920211207-12Pickup w/ plow and sander3240 | Corbiere and Sons Contracting1072920211207-12Pickup w/ plow and sander3240INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10727 | 20211207-10 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 3 | HR |  |  | 75 | 0 | 225 | 29.25 | 254.25 | 2021-12-07 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ron and DZ did Winter Access Maitnenance for 3 hours | 6 | C171-C185 | Prairie River | 0 | 2021-12-12 |  | 36 | 2021-12-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1072720211207-10Operator - Principle - After Jan 103225 | Corbiere and Sons Contracting1072720211207-10Operator - Principle - After Jan 103225INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10727 | 20211207-10 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 3 | Dynamic | 98.61 | 0 |  |  | 394.44 | 51.2772 | 445.7172 | 2021-12-07 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ron and DZ did Winter Access Maitnenance for 3 hours | 6 | C171-C185 | Prairie River | 0 | 2021-12-12 |  | 36 | 2021-12-16 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1072720211207-10Dozer D6 or equal- After Jan 103394.44 | Corbiere and Sons Contracting1072720211207-10Dozer D6 or equal- After Jan 103394.44INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10702 | 20211206-8 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 11 | HR |  |  | 70 | 0 | 770 | 100.1 | 870.1 | 2021-12-06 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ex floated over to Little Red Sucker and then did WAM activities for the day | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-12-12 |  | 36 | 2021-12-15 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1070220211206-8Driver - AZ - After Jan 1011770 | Corbiere and Sons Contracting1070220211206-8Driver - AZ - After Jan 1011770INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10702 | 20211206-8 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 10 | HR |  |  | 75 | 0 | 750 | 97.5 | 847.5 | 2021-12-06 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ex floated over to Little Red Sucker and then did WAM activities for the day | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-12-12 |  | 36 | 2021-12-15 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1070220211206-8Operator - Principle - After Jan 1010750 | Corbiere and Sons Contracting1070220211206-8Operator - Principle - After Jan 1010750INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10702 | 20211206-8 | 53510611 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-12-06 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ex floated over to Little Red Sucker and then did WAM activities for the day | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-12-12 |  | 36 | 2021-12-15 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1070220211206-8L.O.A.2420 | Corbiere and Sons Contracting1070220211206-8L.O.A.2420INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10702 | 20211206-8 | 53510611 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 11 | Dynamic | 91.79 | 0 |  |  | 1346.29 | 175.0177 | 1521.3077 | 2021-12-06 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ex floated over to Little Red Sucker and then did WAM activities for the day | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-12-12 |  | 36 | 2021-12-15 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1070220211206-8Tractor Trailer - 60 Ton- After Jan 10111346.29 | Corbiere and Sons Contracting1070220211206-8Tractor Trailer - 60 Ton- After Jan 10111346.29INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10702 | 20211206-8 | 53510611 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 8 | HR | 9.16 | 0 |  |  | 97.68 | 12.6984 | 110.3784 | 2021-12-06 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ex floated over to Little Red Sucker and then did WAM activities for the day | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-12-12 |  | 36 | 2021-12-15 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1070220211206-8Excavator Thumb - 30 - 50 ton- After Jan 10897.68 | Corbiere and Sons Contracting1070220211206-8Excavator Thumb - 30 - 50 ton- After Jan 10897.68INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10702 | 20211206-8 | 53510611 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 8 | Dynamic | 110.22 | 0 |  |  | 1175.68 | 152.8384 | 1328.5184 | 2021-12-06 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ex floated over to Little Red Sucker and then did WAM activities for the day | 6 | C248-C256 | Little Red Sucker Creek | 0 | 2021-12-12 |  | 36 | 2021-12-15 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1070220211206-8Excavator - 36 ton- After Jan 1081175.68 | Corbiere and Sons Contracting1070220211206-8Excavator - 36 ton- After Jan 1081175.68INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10677 | 20211204-8 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 4 | HR |  |  | 70 | 0 | 280 | 36.4 | 316.4 | 2021-12-04 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Sanding and Plowing of Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-12-11 |  | 36 | 2021-12-14 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1067720211204-8Driver - AZ - After Jan 104280 | Corbiere and Sons Contracting1067720211204-8Driver - AZ - After Jan 104280INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10677 | 20211204-8 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 4 |  | 0 | 0 |  |  | 320 | 41.6 | 361.6 | 2021-12-04 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Sanding and Plowing of Del Lake Road | 6 | C186-C195 | Del Lake | 0 | 2021-12-11 |  | 36 | 2021-12-14 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1067720211204-8Pickup w/ plow and sander4320 | Corbiere and Sons Contracting1067720211204-8Pickup w/ plow and sander4320INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10666 | 20211203-9 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 2 | HR |  |  | 0 | 0 | 140 | 18.2 | 158.2 | 2021-12-03 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Sanding and Plowing on Dead Horse Creek Road | 6 | C203-C209 | Dead Horse Creek Road | 0 | 2021-12-11 |  | 36 | 2021-12-14 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1066620211203-9Operator - Intermdiate - After Jan 102140 | Corbiere and Sons Contracting1066620211203-9Operator - Intermdiate - After Jan 102140INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10666 | 20211203-9 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 2 |  | 0 | 0 |  |  | 160 | 20.8 | 180.8 | 2021-12-03 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Sanding and Plowing on Dead Horse Creek Road | 6 | C203-C209 | Dead Horse Creek Road | 0 | 2021-12-11 |  | 36 | 2021-12-14 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1066620211203-9Pickup w/ plow and sander2160 | Corbiere and Sons Contracting1066620211203-9Pickup w/ plow and sander2160INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10667 | 20211203-10 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 2 | HR |  |  | 0 | 0 | 140 | 18.2 | 158.2 | 2021-12-03 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Sanding and Plowing on Dead Horse Creek Road | 6 | C130-C151 | Lake A | 0 | 2021-12-11 |  | 36 | 2021-12-14 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1066720211203-10Operator - Intermdiate - After Jan 102140 | Corbiere and Sons Contracting1066720211203-10Operator - Intermdiate - After Jan 102140INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10667 | 20211203-10 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 2 |  | 0 | 0 |  |  | 160 | 20.8 | 180.8 | 2021-12-03 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Sanding and Plowing on Dead Horse Creek Road | 6 | C130-C151 | Lake A | 0 | 2021-12-11 |  | 36 | 2021-12-14 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1066720211203-10Pickup w/ plow and sander2160 | Corbiere and Sons Contracting1066720211203-10Pickup w/ plow and sander2160INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10653 | 20211202-8 | 53510611 | Access | 0 | 3rd Party Charges | 1 | 1726.02 | Unit |  |  |  |  | 1726.02 | 224.3826 | 1950.4026 | 2021-12-02 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Relocation of office trailer by Secure Store back to Marathon Laydown for work over the next few months | 6 | C130-C277 | WF6 | 0 | 2021-12-09 |  | 37 | 2021-12-12 | 2112044 | $1487.95 marked up to $1726.02 |  |  |  | Harold Furlong | 06 | Corbiere and Sons Contracting1065320211202-83rd Party Charges1726.021726.02 | Corbiere and Sons Contracting1065320211202-83rd Party Charges1726.021726.02INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10652 | 20211202-7 | 53510611 | Access | 0 | 3rd Party Charges | 1 | 1531.2 | Unit |  |  |  |  | 1531.2 | 199.056 | 1730.256 | 2021-12-02 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Mobilization of Fuel Buggy for use in Prairie And Lake A - 2 hours deducted for delay caused by Corbiere | 6 | C130-C277 | WF6 | 0 | 2021-12-09 |  | 37 | 2021-12-12 | 381 | $1320 marked up to $1531.20 |  |  |  | Harold Furlong | 06 | Corbiere and Sons Contracting1065220211202-73rd Party Charges1531.21531.2 | Corbiere and Sons Contracting1065220211202-73rd Party Charges1531.21531.2INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10621 | 20211128-5 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 3 | HR |  |  | 70 | 0 | 210 | 27.3 | 237.3 | 2021-11-28 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Sanding on Ripple Creek Road to the tracks | 6 | C198-C202 | Ripple Creek Road | 0 | 2021-12-08 |  | 37 | 2021-12-09 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1062120211128-5Operator - Intermdiate - After Jan 103210 | Corbiere and Sons Contracting1062120211128-5Operator - Intermdiate - After Jan 103210INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10621 | 20211128-5 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 3 |  | 0 | 0 |  |  | 240 | 31.2 | 271.2 | 2021-11-28 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Sanding on Ripple Creek Road to the tracks | 6 | C198-C202 | Ripple Creek Road | 0 | 2021-12-08 |  | 37 | 2021-12-09 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1062120211128-5Pickup w/ plow and sander3240 | Corbiere and Sons Contracting1062120211128-5Pickup w/ plow and sander3240INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10620 | 20211128-4 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 3 | HR |  |  | 70 | 0 | 210 | 27.3 | 237.3 | 2021-11-28 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Sanding on Dead Horse Creek Road | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-12-08 |  | 37 | 2021-12-09 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1062020211128-4Operator - Intermdiate - After Jan 103210 | Corbiere and Sons Contracting1062020211128-4Operator - Intermdiate - After Jan 103210INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10620 | 20211128-4 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 3 |  | 0 | 0 |  |  | 240 | 31.2 | 271.2 | 2021-11-28 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Sanding on Dead Horse Creek Road | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-12-08 |  | 37 | 2021-12-09 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1062020211128-4Pickup w/ plow and sander3240 | Corbiere and Sons Contracting1062020211128-4Pickup w/ plow and sander3240INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10618 | 20211128-3 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 22 | HR |  |  | 70 | 0 | 1540 | 200.2 | 1740.2 | 2021-11-28 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Access Maintenance on Dead Horse Creek Road - float mobilized backhow for winter maintenance. | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-12-08 |  | 37 | 2021-12-09 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1061820211128-3Driver - AZ - After Jan 10221540 | Corbiere and Sons Contracting1061820211128-3Driver - AZ - After Jan 10221540INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10618 | 20211128-3 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 75 | 0 | 450 | 58.5 | 508.5 | 2021-11-28 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Access Maintenance on Dead Horse Creek Road - float mobilized backhow for winter maintenance. | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-12-08 |  | 37 | 2021-12-09 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1061820211128-3Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting1061820211128-3Operator - Principle - After Jan 106450INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10618 | 20211128-3 | 53510611 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-11-28 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Access Maintenance on Dead Horse Creek Road - float mobilized backhow for winter maintenance. | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-12-08 |  | 37 | 2021-12-09 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1061820211128-3L.O.A.2420 | Corbiere and Sons Contracting1061820211128-3L.O.A.2420INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10618 | 20211128-3 | 53510611 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 22 | Dynamic | 91.79 | 0 |  |  | 2692.58 | 350.0354 | 3042.6154 | 2021-11-28 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Access Maintenance on Dead Horse Creek Road - float mobilized backhow for winter maintenance. | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-12-08 |  | 37 | 2021-12-09 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1061820211128-3Tractor Trailer - 60 Ton- After Jan 10222692.58 | Corbiere and Sons Contracting1061820211128-3Tractor Trailer - 60 Ton- After Jan 10222692.58INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10618 | 20211128-3 | 53510611 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 4 | HR | 9.16 | 0 |  |  | 48.84 | 6.3492 | 55.1892 | 2021-11-28 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Access Maintenance on Dead Horse Creek Road - float mobilized backhow for winter maintenance. | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-12-08 |  | 37 | 2021-12-09 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1061820211128-3Excavator Thumb - 30 - 50 ton- After Jan 10448.84 | Corbiere and Sons Contracting1061820211128-3Excavator Thumb - 30 - 50 ton- After Jan 10448.84INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10618 | 20211128-3 | 53510611 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 4 | Dynamic | 110.22 | 0 |  |  | 587.84 | 76.4192 | 664.2592 | 2021-11-28 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Access Maintenance on Dead Horse Creek Road - float mobilized backhow for winter maintenance. | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-12-08 |  | 37 | 2021-12-09 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1061820211128-3Excavator - 36 ton- After Jan 104587.84 | Corbiere and Sons Contracting1061820211128-3Excavator - 36 ton- After Jan 104587.84INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10615 | 20211127-4 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 22 | HR |  |  | 70 | 0 | 1540 | 200.2 | 1740.2 | 2021-11-27 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float mobilized 2nd grader from Sudbury | 6 | C129-C151 | Lake A | 0 | 2021-12-08 |  | 37 | 2021-12-09 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1061520211127-4Driver - AZ - After Jan 10221540 | Corbiere and Sons Contracting1061520211127-4Driver - AZ - After Jan 10221540INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10615 | 20211127-4 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-11-27 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float mobilized 2nd grader from Sudbury | 6 | C129-C151 | Lake A | 0 | 2021-12-08 |  | 37 | 2021-12-09 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1061520211127-4L.O.A.1210 | Corbiere and Sons Contracting1061520211127-4L.O.A.1210INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10615 | 20211127-4 | 53510611 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 22 | Dynamic | 91.79 | 0 |  |  | 2692.58 | 350.0354 | 3042.6154 | 2021-11-27 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float mobilized 2nd grader from Sudbury | 6 | C129-C151 | Lake A | 0 | 2021-12-08 |  | 37 | 2021-12-09 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1061520211127-4Tractor Trailer - 60 Ton- After Jan 10222692.58 | Corbiere and Sons Contracting1061520211127-4Tractor Trailer - 60 Ton- After Jan 10222692.58INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10614 | 20211127-3 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-11-27 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Access Maintenance on Dead Horse Creek Road | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-12-08 |  | 37 | 2021-12-09 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1061420211127-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1061420211127-3Operator - Principle - After Jan 1011825INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10614 | 20211127-3 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-11-27 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Access Maintenance on Dead Horse Creek Road | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-12-08 |  | 37 | 2021-12-09 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1061420211127-3L.O.A.1210 | Corbiere and Sons Contracting1061420211127-3L.O.A.1210INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10614 | 20211127-3 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-11-27 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Access Maintenance on Dead Horse Creek Road | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-12-08 |  | 37 | 2021-12-09 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1061420211127-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1061420211127-3Light Truck - Pick up- After Jan 101243.75INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10614 | 20211127-3 | 53510611 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 9.16 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2021-11-27 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Access Maintenance on Dead Horse Creek Road | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-12-08 |  | 37 | 2021-12-09 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1061420211127-3Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting1061420211127-3Excavator Thumb - 30 - 50 ton- After Jan 1010122.1INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10614 | 20211127-3 | 53510611 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10 | Dynamic | 110.22 | 0 |  |  | 1469.6 | 191.048 | 1660.648 | 2021-11-27 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Access Maintenance on Dead Horse Creek Road | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-12-08 |  | 37 | 2021-12-09 | [5 empty] | Harold Furlong | 06 | Corbiere and Sons Contracting1061420211127-3Excavator - 36 ton- After Jan 10101469.6 | Corbiere and Sons Contracting1061420211127-3Excavator - 36 ton- After Jan 10101469.6INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10611 | 20211126-4 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 8 | HR |  |  | 70 | 0 | 560 | 72.8 | 632.8 | 2021-11-26 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float mobed in Ex and DZ and OP mob in DZ to get started on Winter Roads | 6 | C130-C151 | Lake A | 0 | 2021-12-07 |  | 36 | 2021-12-09 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1061120211126-4Driver - AZ - After Jan 108560 | Corbiere and Sons Contracting1061120211126-4Driver - AZ - After Jan 108560INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10611 | 20211126-4 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 4 | HR |  |  | 75 | 0 | 300 | 39 | 339 | 2021-11-26 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float mobed in Ex and DZ and OP mob in DZ to get started on Winter Roads | 6 | C130-C151 | Lake A | 0 | 2021-12-07 |  | 36 | 2021-12-09 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1061120211126-4Operator - Principle - After Jan 104300 | Corbiere and Sons Contracting1061120211126-4Operator - Principle - After Jan 104300INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10611 | 20211126-4 | 53510611 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2021-11-26 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float mobed in Ex and DZ and OP mob in DZ to get started on Winter Roads | 6 | C130-C151 | Lake A | 0 | 2021-12-07 |  | 36 | 2021-12-09 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1061120211126-4L.O.A.2420 | Corbiere and Sons Contracting1061120211126-4L.O.A.2420INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10611 | 20211126-4 | 53510611 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 8 | Dynamic | 91.79 | 0 |  |  | 979.12 | 127.2856 | 1106.4056 | 2021-11-26 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float mobed in Ex and DZ and OP mob in DZ to get started on Winter Roads | 6 | C130-C151 | Lake A | 0 | 2021-12-07 |  | 36 | 2021-12-09 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1061120211126-4Tractor Trailer - 60 Ton- After Jan 108979.12 | Corbiere and Sons Contracting1061120211126-4Tractor Trailer - 60 Ton- After Jan 108979.12INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10611 | 20211126-4 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-11-26 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float mobed in Ex and DZ and OP mob in DZ to get started on Winter Roads | 6 | C130-C151 | Lake A | 0 | 2021-12-07 |  | 36 | 2021-12-09 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1061120211126-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1061120211126-4Light Truck - Pick up- After Jan 101243.75INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10611 | 20211126-4 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 2 | Dynamic | 98.61 | 0 |  |  | 262.96 | 34.1848 | 297.1448 | 2021-11-26 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float mobed in Ex and DZ and OP mob in DZ to get started on Winter Roads | 6 | C130-C151 | Lake A | 0 | 2021-12-07 |  | 36 | 2021-12-09 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1061120211126-4Dozer D6 or equal- After Jan 102262.96 | Corbiere and Sons Contracting1061120211126-4Dozer D6 or equal- After Jan 102262.96INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10610 | 20211126-3 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-11-26 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Access Maintenance on Dead Horse Creek Road | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-12-07 |  | 36 | 2021-12-09 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1061020211126-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1061020211126-3Operator - Principle - After Jan 1011825INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10610 | 20211126-3 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-11-26 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Access Maintenance on Dead Horse Creek Road | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-12-07 |  | 36 | 2021-12-09 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1061020211126-3L.O.A.1210 | Corbiere and Sons Contracting1061020211126-3L.O.A.1210INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10610 | 20211126-3 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-11-26 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Access Maintenance on Dead Horse Creek Road | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-12-07 |  | 36 | 2021-12-09 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1061020211126-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1061020211126-3Light Truck - Pick up- After Jan 101243.75INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10610 | 20211126-3 | 53510611 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 9.16 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2021-11-26 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Access Maintenance on Dead Horse Creek Road | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-12-07 |  | 36 | 2021-12-09 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1061020211126-3Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting1061020211126-3Excavator Thumb - 30 - 50 ton- After Jan 1010122.1INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10610 | 20211126-3 | 53510611 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10 | Dynamic | 110.22 | 0 |  |  | 1469.6 | 191.048 | 1660.648 | 2021-11-26 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Access Maintenance on Dead Horse Creek Road | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-12-07 |  | 36 | 2021-12-09 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1061020211126-3Excavator - 36 ton- After Jan 10101469.6 | Corbiere and Sons Contracting1061020211126-3Excavator - 36 ton- After Jan 10101469.6INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10572 | 20211125-3 | 53510611 | Access | 0 | Labourer - General - After Jan 10 | 60 | 5 | HR |  |  | 60 | 0 | 300 | 39 | 339 | 2021-11-25 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Access Maintenance on Dead Horse Creek Road | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-11-29 |  | 36 | 2021-12-02 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1057220211125-3Labourer - General - After Jan 105300 | Corbiere and Sons Contracting1057220211125-3Labourer - General - After Jan 105300INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10572 | 20211125-3 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2021-11-25 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Access Maintenance on Dead Horse Creek Road | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-11-29 |  | 36 | 2021-12-02 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1057220211125-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1057220211125-3Operator - Principle - After Jan 1011825INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10572 | 20211125-3 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-11-25 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Access Maintenance on Dead Horse Creek Road | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-11-29 |  | 36 | 2021-12-02 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1057220211125-3L.O.A.1210 | Corbiere and Sons Contracting1057220211125-3L.O.A.1210INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10572 | 20211125-3 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-11-25 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Access Maintenance on Dead Horse Creek Road | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-11-29 |  | 36 | 2021-12-02 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1057220211125-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1057220211125-3Light Truck - Pick up- After Jan 101243.75INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10572 | 20211125-3 | 53510611 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 9.16 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2021-11-25 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Access Maintenance on Dead Horse Creek Road | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-11-29 |  | 36 | 2021-12-02 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1057220211125-3Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting1057220211125-3Excavator Thumb - 30 - 50 ton- After Jan 1010122.1INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10572 | 20211125-3 | 53510611 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10 | Dynamic | 110.22 | 0 |  |  | 1469.6 | 191.048 | 1660.648 | 2021-11-25 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Access Maintenance on Dead Horse Creek Road | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-11-29 |  | 36 | 2021-12-02 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1057220211125-3Excavator - 36 ton- After Jan 10101469.6 | Corbiere and Sons Contracting1057220211125-3Excavator - 36 ton- After Jan 10101469.6INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10570 | 20211124-4 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5 | HR |  |  | 75 | 0 | 375 | 48.75 | 423.75 | 2021-11-24 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Access Maintenance on Dead Horse Creek Road | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-11-29 |  | 36 | 2021-12-02 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1057020211124-4Operator - Principle - After Jan 105375 | Corbiere and Sons Contracting1057020211124-4Operator - Principle - After Jan 105375INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10570 | 20211124-4 | 53510611 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 3 | HR | 9.16 | 0 |  |  | 36.63 | 4.7619 | 41.3919 | 2021-11-24 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Access Maintenance on Dead Horse Creek Road | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-11-29 |  | 36 | 2021-12-02 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1057020211124-4Excavator Thumb - 30 - 50 ton- After Jan 10336.63 | Corbiere and Sons Contracting1057020211124-4Excavator Thumb - 30 - 50 ton- After Jan 10336.63INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10570 | 20211124-4 | 53510611 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 3 | Dynamic | 110.22 | 0 |  |  | 440.88 | 57.3144 | 498.1944 | 2021-11-24 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Access Maintenance on Dead Horse Creek Road | 6 | C203-C209 | Dead Horse Creek | 0 | 2021-11-29 |  | 36 | 2021-12-02 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1057020211124-4Excavator - 36 ton- After Jan 103440.88 | Corbiere and Sons Contracting1057020211124-4Excavator - 36 ton- After Jan 103440.88INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10569 | 20211124-3 | 53510611 | Access | 0 | Labourer - General - After Jan 10 | 60 | 5 | HR |  |  | 60 | 0 | 300 | 39 | 339 | 2021-11-24 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Access Maintenance on Hare Lake Road | 6 | C257 | Hare Lake | 0 | 2021-11-29 |  | 36 | 2021-12-02 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1056920211124-3Labourer - General - After Jan 105300 | Corbiere and Sons Contracting1056920211124-3Labourer - General - After Jan 105300INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10569 | 20211124-3 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 75 | 0 | 450 | 58.5 | 508.5 | 2021-11-24 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Access Maintenance on Hare Lake Road | 6 | C257 | Hare Lake | 0 | 2021-11-29 |  | 36 | 2021-12-02 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1056920211124-3Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting1056920211124-3Operator - Principle - After Jan 106450INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10569 | 20211124-3 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2021-11-24 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Access Maintenance on Hare Lake Road | 6 | C257 | Hare Lake | 0 | 2021-11-29 |  | 36 | 2021-12-02 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1056920211124-3L.O.A.1210 | Corbiere and Sons Contracting1056920211124-3L.O.A.1210INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10569 | 20211124-3 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2021-11-24 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Access Maintenance on Hare Lake Road | 6 | C257 | Hare Lake | 0 | 2021-11-29 |  | 36 | 2021-12-02 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1056920211124-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1056920211124-3Light Truck - Pick up- After Jan 101243.75INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10569 | 20211124-3 | 53510611 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 5 | HR | 9.16 | 0 |  |  | 61.05 | 7.9365 | 68.9865 | 2021-11-24 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Access Maintenance on Hare Lake Road | 6 | C257 | Hare Lake | 0 | 2021-11-29 |  | 36 | 2021-12-02 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1056920211124-3Excavator Thumb - 30 - 50 ton- After Jan 10561.05 | Corbiere and Sons Contracting1056920211124-3Excavator Thumb - 30 - 50 ton- After Jan 10561.05INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 10569 | 20211124-3 | 53510611 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 5 | Dynamic | 110.22 | 0 |  |  | 734.8 | 95.524 | 830.324 | 2021-11-24 | 0 | INV# 157 | 2021-12-17 | 173 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Access Maintenance on Hare Lake Road | 6 | C257 | Hare Lake | 0 | 2021-11-29 |  | 36 | 2021-12-02 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting1056920211124-3Excavator - 36 ton- After Jan 105734.8 | Corbiere and Sons Contracting1056920211124-3Excavator - 36 ton- After Jan 105734.8INV# 157 |  | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9708 | 20210815-3 | 53511012 | Access | 0 | Labourer - General - After Jan 10 | 60 | 11 | HR |  |  | 0 | 0 | 660 | 85.8 | 745.8 | 2021-08-15 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM18, KM25, KM30, KM37 and KM48 | 0 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970820210815-3Labourer - General - After Jan 1011660 | Corbiere and Sons Contracting970820210815-3Labourer - General - After Jan 1011660Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9708 | 20210815-3 | 53511012 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 20 | HR |  |  | 70 | 0 | 1400 | 182 | 1582 | 2021-08-15 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM18, KM25, KM30, KM37 and KM48 | 0 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970820210815-3Driver - AZ - After Jan 10201400 | Corbiere and Sons Contracting970820210815-3Driver - AZ - After Jan 10201400Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9708 | 20210815-3 | 53511012 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 165 | HR |  |  | 0 | 0 | 12375 | 1608.75 | 13983.75 | 2021-08-15 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM18, KM25, KM30, KM37 and KM48 | 0 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970820210815-3Operator - Principle - After Jan 1016512375 | Corbiere and Sons Contracting970820210815-3Operator - Principle - After Jan 1016512375Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9708 | 20210815-3 | 53511012 | Access | 0 | L.O.A. | 210 | 18 | DAY |  |  | 0 | 0 | 3780 | 491.4 | 4271.4 | 2021-08-15 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM18, KM25, KM30, KM37 and KM48 | 0 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970820210815-3L.O.A.183780 | Corbiere and Sons Contracting970820210815-3L.O.A.183780Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9708 | 20210815-3 | 53511012 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 0 | 0 | 1140 | 148.2 | 1288.2 | 2021-08-15 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM18, KM25, KM30, KM37 and KM48 | 0 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970820210815-3Foreman121140 | Corbiere and Sons Contracting970820210815-3Foreman121140Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9708 | 20210815-3 | 53511012 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 20 | Dynamic | 91.79 | 0 |  |  | 2447.8 | 318.214 | 2766.014 | 2021-08-15 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM18, KM25, KM30, KM37 and KM48 | 0 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970820210815-3Tractor Trailer - 60 Ton- After Jan 10202447.8 | Corbiere and Sons Contracting970820210815-3Tractor Trailer - 60 Ton- After Jan 10202447.8Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9708 | 20210815-3 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 54 | Dynamic | 0 | 0 |  |  | 7454.7 | 969.111 | 8423.811 | 2021-08-15 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM18, KM25, KM30, KM37 and KM48 | 0 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970820210815-3Rock Truck - 30 Ton- After Jan 10547454.7 | Corbiere and Sons Contracting970820210815-3Rock Truck - 30 Ton- After Jan 10547454.7Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9708 | 20210815-3 | 53511012 | Access | 0 | Marooka- After Jan 10 | 144.6 | 5 | Dynamic | 0 | 0 |  |  | 723 | 93.99 | 816.99 | 2021-08-15 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM18, KM25, KM30, KM37 and KM48 | 0 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970820210815-3Marooka- After Jan 105723 | Corbiere and Sons Contracting970820210815-3Marooka- After Jan 105723Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9708 | 20210815-3 | 53511012 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 10 | DAY | 0 | 0 |  |  | 2437.5 | 316.875 | 2754.375 | 2021-08-15 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM18, KM25, KM30, KM37 and KM48 | 0 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970820210815-3Light Truck - Pick up- After Jan 10102437.5 | Corbiere and Sons Contracting970820210815-3Light Truck - Pick up- After Jan 10102437.5Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9708 | 20210815-3 | 53511012 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 27 | HR | 0 | 0 |  |  | 1711.26 | 222.4638 | 1933.7238 | 2021-08-15 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM18, KM25, KM30, KM37 and KM48 | 0 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970820210815-3Excavator Hammer - 30 - 50 ton- After Jan 10271711.26 | Corbiere and Sons Contracting970820210815-3Excavator Hammer - 30 - 50 ton- After Jan 10271711.26Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9708 | 20210815-3 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 36 | HR | 0 | 0 |  |  | 439.56 | 57.1428 | 496.7028 | 2021-08-15 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM18, KM25, KM30, KM37 and KM48 | 0 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970820210815-3Excavator Thumb - 30 - 50 ton- After Jan 1036439.56 | Corbiere and Sons Contracting970820210815-3Excavator Thumb - 30 - 50 ton- After Jan 1036439.56Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9708 | 20210815-3 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 27 | Dynamic | 0 | 0 |  |  | 3967.92 | 515.8296 | 4483.7496 | 2021-08-15 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM18, KM25, KM30, KM37 and KM48 | 0 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970820210815-3Excavator - 36 ton- After Jan 10273967.92 | Corbiere and Sons Contracting970820210815-3Excavator - 36 ton- After Jan 10273967.92Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9708 | 20210815-3 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 45 | Dynamic | 0 | 0 |  |  | 6230.25 | 809.9325 | 7040.1825 | 2021-08-15 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM18, KM25, KM30, KM37 and KM48 | 0 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970820210815-3Excavator - 30 ton- After Jan 10456230.25 | Corbiere and Sons Contracting970820210815-3Excavator - 30 ton- After Jan 10456230.25Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9708 | 20210815-3 | 53511012 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 9 | Dynamic | 0 | 0 |  |  | 1183.32 | 153.8316 | 1337.1516 | 2021-08-15 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM18, KM25, KM30, KM37 and KM48 | 0 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970820210815-3Dozer D6 or equal- After Jan 1091183.32 | Corbiere and Sons Contracting970820210815-3Dozer D6 or equal- After Jan 1091183.32Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9707 | 20210814-3 | 53511012 | Access | 0 | Labourer - General - After Jan 10 | 60 | 11 | HR |  |  | 0 | 0 | 660 | 85.8 | 745.8 | 2021-08-14 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM18, KM19, KM25, KM30. KM37 and KM48 | 0 | F066-F118 | Paint Lake 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970720210814-3Labourer - General - After Jan 1011660 | Corbiere and Sons Contracting970720210814-3Labourer - General - After Jan 1011660Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9707 | 20210814-3 | 53511012 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 154 | HR |  |  | 0 | 0 | 11550 | 1501.5 | 13051.5 | 2021-08-14 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM18, KM19, KM25, KM30. KM37 and KM48 | 0 | F066-F118 | Paint Lake 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970720210814-3Operator - Principle - After Jan 1015411550 | Corbiere and Sons Contracting970720210814-3Operator - Principle - After Jan 1015411550Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9707 | 20210814-3 | 53511012 | Access | 0 | L.O.A. | 210 | 16 | DAY |  |  | 0 | 0 | 3360 | 436.8 | 3796.8 | 2021-08-14 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM18, KM19, KM25, KM30. KM37 and KM48 | 0 | F066-F118 | Paint Lake 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970720210814-3L.O.A.163360 | Corbiere and Sons Contracting970720210814-3L.O.A.163360Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9707 | 20210814-3 | 53511012 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 0 | 0 | 1140 | 148.2 | 1288.2 | 2021-08-14 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM18, KM19, KM25, KM30. KM37 and KM48 | 0 | F066-F118 | Paint Lake 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970720210814-3Foreman121140 | Corbiere and Sons Contracting970720210814-3Foreman121140Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9707 | 20210814-3 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 54 | Dynamic | 0 | 0 |  |  | 7454.7 | 969.111 | 8423.811 | 2021-08-14 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM18, KM19, KM25, KM30. KM37 and KM48 | 0 | F066-F118 | Paint Lake 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970720210814-3Rock Truck - 30 Ton- After Jan 10547454.7 | Corbiere and Sons Contracting970720210814-3Rock Truck - 30 Ton- After Jan 10547454.7Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9707 | 20210814-3 | 53511012 | Access | 0 | Marooka- After Jan 10 | 144.6 | 5 | Dynamic | 0 | 0 |  |  | 723 | 93.99 | 816.99 | 2021-08-14 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM18, KM19, KM25, KM30. KM37 and KM48 | 0 | F066-F118 | Paint Lake 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970720210814-3Marooka- After Jan 105723 | Corbiere and Sons Contracting970720210814-3Marooka- After Jan 105723Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9707 | 20210814-3 | 53511012 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 10 | DAY | 0 | 0 |  |  | 2437.5 | 316.875 | 2754.375 | 2021-08-14 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM18, KM19, KM25, KM30. KM37 and KM48 | 0 | F066-F118 | Paint Lake 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970720210814-3Light Truck - Pick up- After Jan 10102437.5 | Corbiere and Sons Contracting970720210814-3Light Truck - Pick up- After Jan 10102437.5Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9707 | 20210814-3 | 53511012 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 18 | HR | 0 | 0 |  |  | 1140.84 | 148.3092 | 1289.1492 | 2021-08-14 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM18, KM19, KM25, KM30. KM37 and KM48 | 0 | F066-F118 | Paint Lake 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970720210814-3Excavator Hammer - 30 - 50 ton- After Jan 10181140.84 | Corbiere and Sons Contracting970720210814-3Excavator Hammer - 30 - 50 ton- After Jan 10181140.84Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9707 | 20210814-3 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 36 | HR | 0 | 0 |  |  | 439.56 | 57.1428 | 496.7028 | 2021-08-14 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM18, KM19, KM25, KM30. KM37 and KM48 | 0 | F066-F118 | Paint Lake 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970720210814-3Excavator Thumb - 30 - 50 ton- After Jan 1036439.56 | Corbiere and Sons Contracting970720210814-3Excavator Thumb - 30 - 50 ton- After Jan 1036439.56Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9707 | 20210814-3 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 18 | Dynamic | 0 | 0 |  |  | 2645.28 | 343.8864 | 2989.1664 | 2021-08-14 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM18, KM19, KM25, KM30. KM37 and KM48 | 0 | F066-F118 | Paint Lake 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970720210814-3Excavator - 36 ton- After Jan 10182645.28 | Corbiere and Sons Contracting970720210814-3Excavator - 36 ton- After Jan 10182645.28Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9707 | 20210814-3 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 45 | Dynamic | 0 | 0 |  |  | 6230.25 | 809.9325 | 7040.1825 | 2021-08-14 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM18, KM19, KM25, KM30. KM37 and KM48 | 0 | F066-F118 | Paint Lake 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970720210814-3Excavator - 30 ton- After Jan 10456230.25 | Corbiere and Sons Contracting970720210814-3Excavator - 30 ton- After Jan 10456230.25Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9707 | 20210814-3 | 53511012 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 9 | Dynamic | 0 | 0 |  |  | 1183.32 | 153.8316 | 1337.1516 | 2021-08-14 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM18, KM19, KM25, KM30. KM37 and KM48 | 0 | F066-F118 | Paint Lake 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970720210814-3Dozer D6 or equal- After Jan 1091183.32 | Corbiere and Sons Contracting970720210814-3Dozer D6 or equal- After Jan 1091183.32Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9706 | 20210813-3 | 53511012 | Access | 0 | Labourer - General - After Jan 10 | 60 | 10 | HR |  |  | 0 | 0 | 600 | 78 | 678 | 2021-08-13 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM37 on Paint Lake 2 | 0 | F066-F118 | Paint Lake 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970620210813-3Labourer - General - After Jan 1010600 | Corbiere and Sons Contracting970620210813-3Labourer - General - After Jan 1010600Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9706 | 20210813-3 | 53511012 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 140 | HR |  |  | 0 | 0 | 10500 | 1365 | 11865 | 2021-08-13 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM37 on Paint Lake 2 | 0 | F066-F118 | Paint Lake 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970620210813-3Operator - Principle - After Jan 1014010500 | Corbiere and Sons Contracting970620210813-3Operator - Principle - After Jan 1014010500Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9706 | 20210813-3 | 53511012 | Access | 0 | L.O.A. | 210 | 16 | DAY |  |  | 0 | 0 | 3360 | 436.8 | 3796.8 | 2021-08-13 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM37 on Paint Lake 2 | 0 | F066-F118 | Paint Lake 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970620210813-3L.O.A.163360 | Corbiere and Sons Contracting970620210813-3L.O.A.163360Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9706 | 20210813-3 | 53511012 | Access | 0 | Foreman | 95 | 11 | HR |  |  | 0 | 0 | 1045 | 135.85 | 1180.85 | 2021-08-13 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM37 on Paint Lake 2 | 0 | F066-F118 | Paint Lake 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970620210813-3Foreman111045 | Corbiere and Sons Contracting970620210813-3Foreman111045Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9706 | 20210813-3 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 48 | Dynamic | 0 | 0 |  |  | 6626.4 | 861.432 | 7487.832 | 2021-08-13 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM37 on Paint Lake 2 | 0 | F066-F118 | Paint Lake 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970620210813-3Rock Truck - 30 Ton- After Jan 10486626.4 | Corbiere and Sons Contracting970620210813-3Rock Truck - 30 Ton- After Jan 10486626.4Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9706 | 20210813-3 | 53511012 | Access | 0 | Marooka- After Jan 10 | 144.6 | 5 | Dynamic | 0 | 0 |  |  | 723 | 93.99 | 816.99 | 2021-08-13 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM37 on Paint Lake 2 | 0 | F066-F118 | Paint Lake 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970620210813-3Marooka- After Jan 105723 | Corbiere and Sons Contracting970620210813-3Marooka- After Jan 105723Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9706 | 20210813-3 | 53511012 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 10 | DAY | 0 | 0 |  |  | 2437.5 | 316.875 | 2754.375 | 2021-08-13 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM37 on Paint Lake 2 | 0 | F066-F118 | Paint Lake 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970620210813-3Light Truck - Pick up- After Jan 10102437.5 | Corbiere and Sons Contracting970620210813-3Light Truck - Pick up- After Jan 10102437.5Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9706 | 20210813-3 | 53511012 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 16 | HR | 0 | 0 |  |  | 1014.08 | 131.8304 | 1145.9104 | 2021-08-13 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM37 on Paint Lake 2 | 0 | F066-F118 | Paint Lake 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970620210813-3Excavator Hammer - 30 - 50 ton- After Jan 10161014.08 | Corbiere and Sons Contracting970620210813-3Excavator Hammer - 30 - 50 ton- After Jan 10161014.08Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9706 | 20210813-3 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 32 | HR | 0 | 0 |  |  | 390.72 | 50.7936 | 441.5136 | 2021-08-13 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM37 on Paint Lake 2 | 0 | F066-F118 | Paint Lake 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970620210813-3Excavator Thumb - 30 - 50 ton- After Jan 1032390.72 | Corbiere and Sons Contracting970620210813-3Excavator Thumb - 30 - 50 ton- After Jan 1032390.72Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9706 | 20210813-3 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 16 | Dynamic | 0 | 0 |  |  | 2351.36 | 305.6768 | 2657.0368 | 2021-08-13 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM37 on Paint Lake 2 | 0 | F066-F118 | Paint Lake 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970620210813-3Excavator - 36 ton- After Jan 10162351.36 | Corbiere and Sons Contracting970620210813-3Excavator - 36 ton- After Jan 10162351.36Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9706 | 20210813-3 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 40 | Dynamic | 0 | 0 |  |  | 5538 | 719.94 | 6257.94 | 2021-08-13 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM37 on Paint Lake 2 | 0 | F066-F118 | Paint Lake 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970620210813-3Excavator - 30 ton- After Jan 10405538 | Corbiere and Sons Contracting970620210813-3Excavator - 30 ton- After Jan 10405538Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9706 | 20210813-3 | 53511012 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 8 | Dynamic | 98.61 | 0 |  |  | 1051.84 | 136.7392 | 1188.5792 | 2021-08-13 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM37 on Paint Lake 2 | 0 | F066-F118 | Paint Lake 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970620210813-3Dozer D6 or equal- After Jan 1081051.84 | Corbiere and Sons Contracting970620210813-3Dozer D6 or equal- After Jan 1081051.84Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9705 | 20210812-3 | 53511012 | Access | 0 | Labourer - General - After Jan 10 | 60 | 11 | HR |  |  | 0 | 0 | 660 | 85.8 | 745.8 | 2021-08-12 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM37 on Paint Lake 2 | 0 | F066-F118 | Paint Lake 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970520210812-3Labourer - General - After Jan 1011660 | Corbiere and Sons Contracting970520210812-3Labourer - General - After Jan 1011660Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9705 | 20210812-3 | 53511012 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 12 | HR |  |  | 70 | 0 | 840 | 109.2 | 949.2 | 2021-08-12 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM37 on Paint Lake 2 | 0 | F066-F118 | Paint Lake 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970520210812-3Driver - AZ - After Jan 1012840 | Corbiere and Sons Contracting970520210812-3Driver - AZ - After Jan 1012840Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9705 | 20210812-3 | 53511012 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 153 | HR |  |  | 0 | 0 | 11475 | 1491.75 | 12966.75 | 2021-08-12 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM37 on Paint Lake 2 | 0 | F066-F118 | Paint Lake 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970520210812-3Operator - Principle - After Jan 1015311475 | Corbiere and Sons Contracting970520210812-3Operator - Principle - After Jan 1015311475Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9705 | 20210812-3 | 53511012 | Access | 0 | L.O.A. | 210 | 17 | DAY |  |  | 0 | 0 | 3570 | 464.1 | 4034.1 | 2021-08-12 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM37 on Paint Lake 2 | 0 | F066-F118 | Paint Lake 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970520210812-3L.O.A.173570 | Corbiere and Sons Contracting970520210812-3L.O.A.173570Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9705 | 20210812-3 | 53511012 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 0 | 0 | 1140 | 148.2 | 1288.2 | 2021-08-12 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM37 on Paint Lake 2 | 0 | F066-F118 | Paint Lake 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970520210812-3Foreman121140 | Corbiere and Sons Contracting970520210812-3Foreman121140Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9705 | 20210812-3 | 53511012 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 12 | Dynamic | 91.79 | 0 |  |  | 1468.68 | 190.9284 | 1659.6084 | 2021-08-12 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM37 on Paint Lake 2 | 0 | F066-F118 | Paint Lake 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970520210812-3Tractor Trailer - 60 Ton- After Jan 10121468.68 | Corbiere and Sons Contracting970520210812-3Tractor Trailer - 60 Ton- After Jan 10121468.68Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9705 | 20210812-3 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 54 | Dynamic | 0 | 0 |  |  | 7454.7 | 969.111 | 8423.811 | 2021-08-12 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM37 on Paint Lake 2 | 0 | F066-F118 | Paint Lake 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970520210812-3Rock Truck - 30 Ton- After Jan 10547454.7 | Corbiere and Sons Contracting970520210812-3Rock Truck - 30 Ton- After Jan 10547454.7Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9705 | 20210812-3 | 53511012 | Access | 0 | Marooka- After Jan 10 | 144.6 | 5 | Dynamic | 0 | 0 |  |  | 723 | 93.99 | 816.99 | 2021-08-12 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM37 on Paint Lake 2 | 0 | F066-F118 | Paint Lake 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970520210812-3Marooka- After Jan 105723 | Corbiere and Sons Contracting970520210812-3Marooka- After Jan 105723Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9705 | 20210812-3 | 53511012 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 10 | DAY | 0 | 0 |  |  | 2437.5 | 316.875 | 2754.375 | 2021-08-12 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM37 on Paint Lake 2 | 0 | F066-F118 | Paint Lake 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970520210812-3Light Truck - Pick up- After Jan 10102437.5 | Corbiere and Sons Contracting970520210812-3Light Truck - Pick up- After Jan 10102437.5Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9705 | 20210812-3 | 53511012 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 9 | HR | 0 | 0 |  |  | 570.42 | 74.1546 | 644.5746 | 2021-08-12 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM37 on Paint Lake 2 | 0 | F066-F118 | Paint Lake 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970520210812-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42 | Corbiere and Sons Contracting970520210812-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9705 | 20210812-3 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 45 | HR | 0 | 0 |  |  | 549.45 | 71.4285 | 620.8785 | 2021-08-12 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM37 on Paint Lake 2 | 0 | F066-F118 | Paint Lake 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970520210812-3Excavator Thumb - 30 - 50 ton- After Jan 1045549.45 | Corbiere and Sons Contracting970520210812-3Excavator Thumb - 30 - 50 ton- After Jan 1045549.45Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9705 | 20210812-3 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 18 | Dynamic | 0 | 0 |  |  | 2645.28 | 343.8864 | 2989.1664 | 2021-08-12 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM37 on Paint Lake 2 | 0 | F066-F118 | Paint Lake 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970520210812-3Excavator - 36 ton- After Jan 10182645.28 | Corbiere and Sons Contracting970520210812-3Excavator - 36 ton- After Jan 10182645.28Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9705 | 20210812-3 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 45 | Dynamic | 0 | 0 |  |  | 6230.25 | 809.9325 | 7040.1825 | 2021-08-12 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM37 on Paint Lake 2 | 0 | F066-F118 | Paint Lake 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970520210812-3Excavator - 30 ton- After Jan 10456230.25 | Corbiere and Sons Contracting970520210812-3Excavator - 30 ton- After Jan 10456230.25Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9704 | 20210811-3 | 53511012 | Access | 0 | Labourer - General - After Jan 10 | 60 | 11 | HR |  |  | 0 | 0 | 660 | 85.8 | 745.8 | 2021-08-11 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM38 on Paint Lake 2 | 0 | F066-F118 | Paint Lake 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970420210811-3Labourer - General - After Jan 1011660 | Corbiere and Sons Contracting970420210811-3Labourer - General - After Jan 1011660Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9704 | 20210811-3 | 53511012 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 143 | HR |  |  | 0 | 0 | 10725 | 1394.25 | 12119.25 | 2021-08-11 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM38 on Paint Lake 2 | 0 | F066-F118 | Paint Lake 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970420210811-3Operator - Principle - After Jan 1014310725 | Corbiere and Sons Contracting970420210811-3Operator - Principle - After Jan 1014310725Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9704 | 20210811-3 | 53511012 | Access | 0 | L.O.A. | 210 | 15 | DAY |  |  | 0 | 0 | 3150 | 409.5 | 3559.5 | 2021-08-11 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM38 on Paint Lake 2 | 0 | F066-F118 | Paint Lake 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970420210811-3L.O.A.153150 | Corbiere and Sons Contracting970420210811-3L.O.A.153150Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9704 | 20210811-3 | 53511012 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 0 | 0 | 1140 | 148.2 | 1288.2 | 2021-08-11 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM38 on Paint Lake 2 | 0 | F066-F118 | Paint Lake 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970420210811-3Foreman121140 | Corbiere and Sons Contracting970420210811-3Foreman121140Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9704 | 20210811-3 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 54 | Dynamic | 0 | 0 |  |  | 7454.7 | 969.111 | 8423.811 | 2021-08-11 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM38 on Paint Lake 2 | 0 | F066-F118 | Paint Lake 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970420210811-3Rock Truck - 30 Ton- After Jan 10547454.7 | Corbiere and Sons Contracting970420210811-3Rock Truck - 30 Ton- After Jan 10547454.7Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9704 | 20210811-3 | 53511012 | Access | 0 | Marooka- After Jan 10 | 144.6 | 5 | Dynamic | 0 | 0 |  |  | 723 | 93.99 | 816.99 | 2021-08-11 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM38 on Paint Lake 2 | 0 | F066-F118 | Paint Lake 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970420210811-3Marooka- After Jan 105723 | Corbiere and Sons Contracting970420210811-3Marooka- After Jan 105723Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9704 | 20210811-3 | 53511012 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 9 | DAY | 0 | 0 |  |  | 2193.75 | 285.1875 | 2478.9375 | 2021-08-11 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM38 on Paint Lake 2 | 0 | F066-F118 | Paint Lake 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970420210811-3Light Truck - Pick up- After Jan 1092193.75 | Corbiere and Sons Contracting970420210811-3Light Truck - Pick up- After Jan 1092193.75Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9704 | 20210811-3 | 53511012 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 9 | HR | 0 | 0 |  |  | 570.42 | 74.1546 | 644.5746 | 2021-08-11 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM38 on Paint Lake 2 | 0 | F066-F118 | Paint Lake 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970420210811-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42 | Corbiere and Sons Contracting970420210811-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9704 | 20210811-3 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 45 | HR | 0 | 0 |  |  | 549.45 | 71.4285 | 620.8785 | 2021-08-11 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM38 on Paint Lake 2 | 0 | F066-F118 | Paint Lake 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970420210811-3Excavator Thumb - 30 - 50 ton- After Jan 1045549.45 | Corbiere and Sons Contracting970420210811-3Excavator Thumb - 30 - 50 ton- After Jan 1045549.45Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9704 | 20210811-3 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 18 | Dynamic | 0 | 0 |  |  | 2645.28 | 343.8864 | 2989.1664 | 2021-08-11 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM38 on Paint Lake 2 | 0 | F066-F118 | Paint Lake 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970420210811-3Excavator - 36 ton- After Jan 10182645.28 | Corbiere and Sons Contracting970420210811-3Excavator - 36 ton- After Jan 10182645.28Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9704 | 20210811-3 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 45 | Dynamic | 0 | 0 |  |  | 6230.25 | 809.9325 | 7040.1825 | 2021-08-11 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM38 on Paint Lake 2 | 0 | F066-F118 | Paint Lake 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970420210811-3Excavator - 30 ton- After Jan 10456230.25 | Corbiere and Sons Contracting970420210811-3Excavator - 30 ton- After Jan 10456230.25Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9703 | 20210810-3 | 53511012 | Access | 0 | Labourer - General - After Jan 10 | 60 | 11 | HR |  |  | 0 | 0 | 660 | 85.8 | 745.8 | 2021-08-10 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM38 on Paint Lake 2 | 0 | F066-F118 | Paint Lake 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970320210810-3Labourer - General - After Jan 1011660 | Corbiere and Sons Contracting970320210810-3Labourer - General - After Jan 1011660Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9703 | 20210810-3 | 53511012 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 24 | HR |  |  | 70 | 0 | 1680 | 218.4 | 1898.4 | 2021-08-10 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM38 on Paint Lake 2 | 0 | F066-F118 | Paint Lake 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970320210810-3Driver - AZ - After Jan 10241680 | Corbiere and Sons Contracting970320210810-3Driver - AZ - After Jan 10241680Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9703 | 20210810-3 | 53511012 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 143 | HR |  |  | 0 | 0 | 10725 | 1394.25 | 12119.25 | 2021-08-10 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM38 on Paint Lake 2 | 0 | F066-F118 | Paint Lake 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970320210810-3Operator - Principle - After Jan 1014310725 | Corbiere and Sons Contracting970320210810-3Operator - Principle - After Jan 1014310725Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9703 | 20210810-3 | 53511012 | Access | 0 | L.O.A. | 210 | 16 | DAY |  |  | 0 | 0 | 3360 | 436.8 | 3796.8 | 2021-08-10 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM38 on Paint Lake 2 | 0 | F066-F118 | Paint Lake 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970320210810-3L.O.A.163360 | Corbiere and Sons Contracting970320210810-3L.O.A.163360Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9703 | 20210810-3 | 53511012 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 0 | 0 | 1140 | 148.2 | 1288.2 | 2021-08-10 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM38 on Paint Lake 2 | 0 | F066-F118 | Paint Lake 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970320210810-3Foreman121140 | Corbiere and Sons Contracting970320210810-3Foreman121140Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9703 | 20210810-3 | 53511012 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 24 | Dynamic | 91.79 | 0 |  |  | 2937.36 | 381.8568 | 3319.2168 | 2021-08-10 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM38 on Paint Lake 2 | 0 | F066-F118 | Paint Lake 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970320210810-3Tractor Trailer - 60 Ton- After Jan 10242937.36 | Corbiere and Sons Contracting970320210810-3Tractor Trailer - 60 Ton- After Jan 10242937.36Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9703 | 20210810-3 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 45 | Dynamic | 0 | 0 |  |  | 6212.25 | 807.5925 | 7019.8425 | 2021-08-10 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM38 on Paint Lake 2 | 0 | F066-F118 | Paint Lake 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970320210810-3Rock Truck - 30 Ton- After Jan 10456212.25 | Corbiere and Sons Contracting970320210810-3Rock Truck - 30 Ton- After Jan 10456212.25Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9703 | 20210810-3 | 53511012 | Access | 0 | Marooka- After Jan 10 | 144.6 | 5 | Dynamic | 0 | 0 |  |  | 723 | 93.99 | 816.99 | 2021-08-10 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM38 on Paint Lake 2 | 0 | F066-F118 | Paint Lake 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970320210810-3Marooka- After Jan 105723 | Corbiere and Sons Contracting970320210810-3Marooka- After Jan 105723Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9703 | 20210810-3 | 53511012 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 9 | DAY | 0 | 0 |  |  | 2193.75 | 285.1875 | 2478.9375 | 2021-08-10 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM38 on Paint Lake 2 | 0 | F066-F118 | Paint Lake 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970320210810-3Light Truck - Pick up- After Jan 1092193.75 | Corbiere and Sons Contracting970320210810-3Light Truck - Pick up- After Jan 1092193.75Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9703 | 20210810-3 | 53511012 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 9 | HR | 0 | 0 |  |  | 570.42 | 74.1546 | 644.5746 | 2021-08-10 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM38 on Paint Lake 2 | 0 | F066-F118 | Paint Lake 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970320210810-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42 | Corbiere and Sons Contracting970320210810-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9703 | 20210810-3 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 45 | HR | 0 | 0 |  |  | 549.45 | 71.4285 | 620.8785 | 2021-08-10 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM38 on Paint Lake 2 | 0 | F066-F118 | Paint Lake 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970320210810-3Excavator Thumb - 30 - 50 ton- After Jan 1045549.45 | Corbiere and Sons Contracting970320210810-3Excavator Thumb - 30 - 50 ton- After Jan 1045549.45Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9703 | 20210810-3 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 18 | Dynamic | 0 | 0 |  |  | 2645.28 | 343.8864 | 2989.1664 | 2021-08-10 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM38 on Paint Lake 2 | 0 | F066-F118 | Paint Lake 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970320210810-3Excavator - 36 ton- After Jan 10182645.28 | Corbiere and Sons Contracting970320210810-3Excavator - 36 ton- After Jan 10182645.28Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9703 | 20210810-3 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 45 | Dynamic | 0 | 0 |  |  | 6230.25 | 809.9325 | 7040.1825 | 2021-08-10 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM38 on Paint Lake 2 | 0 | F066-F118 | Paint Lake 2 | 0 | 2021-08-16 |  | 57 | 2021-08-18 | [6 empty] | 10 | Corbiere and Sons Contracting970320210810-3Excavator - 30 ton- After Jan 10456230.25 | Corbiere and Sons Contracting970320210810-3Excavator - 30 ton- After Jan 10456230.25Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9689 | 20210809-3 | 53511012 | Access | 0 | Labourer - General - After Jan 10 | 60 | 11 | HR |  |  | 0 | 0 | 660 | 85.8 | 745.8 | 2021-08-09 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM38 on Paint Lake 2 | 0 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-13 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting968920210809-3Labourer - General - After Jan 1011660 | Corbiere and Sons Contracting968920210809-3Labourer - General - After Jan 1011660Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9689 | 20210809-3 | 53511012 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 110 | HR |  |  | 0 | 0 | 8250 | 1072.5 | 9322.5 | 2021-08-09 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM38 on Paint Lake 2 | 0 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-13 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting968920210809-3Operator - Principle - After Jan 101108250 | Corbiere and Sons Contracting968920210809-3Operator - Principle - After Jan 101108250Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9689 | 20210809-3 | 53511012 | Access | 0 | L.O.A. | 210 | 12 | DAY |  |  | 0 | 0 | 2520 | 327.6 | 2847.6 | 2021-08-09 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM38 on Paint Lake 2 | 0 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-13 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting968920210809-3L.O.A.122520 | Corbiere and Sons Contracting968920210809-3L.O.A.122520Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9689 | 20210809-3 | 53511012 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 0 | 0 | 1140 | 148.2 | 1288.2 | 2021-08-09 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM38 on Paint Lake 2 | 0 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-13 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting968920210809-3Foreman121140 | Corbiere and Sons Contracting968920210809-3Foreman121140Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9689 | 20210809-3 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 36 | Dynamic | 0 | 0 |  |  | 4969.8 | 646.074 | 5615.874 | 2021-08-09 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM38 on Paint Lake 2 | 0 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-13 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting968920210809-3Rock Truck - 30 Ton- After Jan 10364969.8 | Corbiere and Sons Contracting968920210809-3Rock Truck - 30 Ton- After Jan 10364969.8Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9689 | 20210809-3 | 53511012 | Access | 0 | Marooka- After Jan 10 | 144.6 | 5 | Dynamic | 0 | 0 |  |  | 723 | 93.99 | 816.99 | 2021-08-09 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM38 on Paint Lake 2 | 0 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-13 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting968920210809-3Marooka- After Jan 105723 | Corbiere and Sons Contracting968920210809-3Marooka- After Jan 105723Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9689 | 20210809-3 | 53511012 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 8 | DAY | 0 | 0 |  |  | 1950 | 253.5 | 2203.5 | 2021-08-09 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM38 on Paint Lake 2 | 0 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-13 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting968920210809-3Light Truck - Pick up- After Jan 1081950 | Corbiere and Sons Contracting968920210809-3Light Truck - Pick up- After Jan 1081950Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9689 | 20210809-3 | 53511012 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 9 | HR | 0 | 0 |  |  | 570.42 | 74.1546 | 644.5746 | 2021-08-09 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM38 on Paint Lake 2 | 0 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-13 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting968920210809-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42 | Corbiere and Sons Contracting968920210809-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9689 | 20210809-3 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 36 | HR | 0 | 0 |  |  | 439.56 | 57.1428 | 496.7028 | 2021-08-09 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM38 on Paint Lake 2 | 0 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-13 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting968920210809-3Excavator Thumb - 30 - 50 ton- After Jan 1036439.56 | Corbiere and Sons Contracting968920210809-3Excavator Thumb - 30 - 50 ton- After Jan 1036439.56Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9689 | 20210809-3 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 18 | Dynamic | 0 | 0 |  |  | 2645.28 | 343.8864 | 2989.1664 | 2021-08-09 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM38 on Paint Lake 2 | 0 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-13 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting968920210809-3Excavator - 36 ton- After Jan 10182645.28 | Corbiere and Sons Contracting968920210809-3Excavator - 36 ton- After Jan 10182645.28Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9689 | 20210809-3 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 36 | Dynamic | 0 | 0 |  |  | 4984.2 | 647.946 | 5632.146 | 2021-08-09 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM38 on Paint Lake 2 | 0 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-13 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting968920210809-3Excavator - 30 ton- After Jan 10364984.2 | Corbiere and Sons Contracting968920210809-3Excavator - 30 ton- After Jan 10364984.2Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9688 | 20210808-3 | 53511012 | Access | 0 | Labourer - General - After Jan 10 | 60 | 11 | HR |  |  | 0 | 0 | 660 | 85.8 | 745.8 | 2021-08-08 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM37 on Paint Lake 2 | 0 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-13 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting968820210808-3Labourer - General - After Jan 1011660 | Corbiere and Sons Contracting968820210808-3Labourer - General - After Jan 1011660Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9688 | 20210808-3 | 53511012 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 110 | HR |  |  | 0 | 0 | 8250 | 1072.5 | 9322.5 | 2021-08-08 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM37 on Paint Lake 2 | 0 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-13 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting968820210808-3Operator - Principle - After Jan 101108250 | Corbiere and Sons Contracting968820210808-3Operator - Principle - After Jan 101108250Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9688 | 20210808-3 | 53511012 | Access | 0 | L.O.A. | 210 | 12 | DAY |  |  | 0 | 0 | 2520 | 327.6 | 2847.6 | 2021-08-08 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM37 on Paint Lake 2 | 0 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-13 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting968820210808-3L.O.A.122520 | Corbiere and Sons Contracting968820210808-3L.O.A.122520Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9688 | 20210808-3 | 53511012 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 0 | 0 | 1140 | 148.2 | 1288.2 | 2021-08-08 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM37 on Paint Lake 2 | 0 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-13 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting968820210808-3Foreman121140 | Corbiere and Sons Contracting968820210808-3Foreman121140Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9688 | 20210808-3 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 36 | Dynamic | 0 | 0 |  |  | 4969.8 | 646.074 | 5615.874 | 2021-08-08 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM37 on Paint Lake 2 | 0 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-13 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting968820210808-3Rock Truck - 30 Ton- After Jan 10364969.8 | Corbiere and Sons Contracting968820210808-3Rock Truck - 30 Ton- After Jan 10364969.8Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9688 | 20210808-3 | 53511012 | Access | 0 | Marooka- After Jan 10 | 144.6 | 5 | Dynamic | 0 | 0 |  |  | 723 | 93.99 | 816.99 | 2021-08-08 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM37 on Paint Lake 2 | 0 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-13 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting968820210808-3Marooka- After Jan 105723 | Corbiere and Sons Contracting968820210808-3Marooka- After Jan 105723Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9688 | 20210808-3 | 53511012 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 8 | DAY | 0 | 0 |  |  | 1950 | 253.5 | 2203.5 | 2021-08-08 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM37 on Paint Lake 2 | 0 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-13 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting968820210808-3Light Truck - Pick up- After Jan 1081950 | Corbiere and Sons Contracting968820210808-3Light Truck - Pick up- After Jan 1081950Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9688 | 20210808-3 | 53511012 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 9 | HR | 0 | 0 |  |  | 570.42 | 74.1546 | 644.5746 | 2021-08-08 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM37 on Paint Lake 2 | 0 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-13 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting968820210808-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42 | Corbiere and Sons Contracting968820210808-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9688 | 20210808-3 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 36 | HR | 0 | 0 |  |  | 439.56 | 57.1428 | 496.7028 | 2021-08-08 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM37 on Paint Lake 2 | 0 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-13 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting968820210808-3Excavator Thumb - 30 - 50 ton- After Jan 1036439.56 | Corbiere and Sons Contracting968820210808-3Excavator Thumb - 30 - 50 ton- After Jan 1036439.56Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9688 | 20210808-3 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 18 | Dynamic | 0 | 0 |  |  | 2645.28 | 343.8864 | 2989.1664 | 2021-08-08 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM37 on Paint Lake 2 | 0 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-13 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting968820210808-3Excavator - 36 ton- After Jan 10182645.28 | Corbiere and Sons Contracting968820210808-3Excavator - 36 ton- After Jan 10182645.28Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9688 | 20210808-3 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 36 | Dynamic | 0 | 0 |  |  | 4984.2 | 647.946 | 5632.146 | 2021-08-08 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM37 on Paint Lake 2 | 0 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-13 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting968820210808-3Excavator - 30 ton- After Jan 10364984.2 | Corbiere and Sons Contracting968820210808-3Excavator - 30 ton- After Jan 10364984.2Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9687 | 20210807-3 | 53511012 | Access | 0 | Labourer - General - After Jan 10 | 60 | 11 | HR |  |  | 0 | 0 | 660 | 85.8 | 745.8 | 2021-08-07 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM37 on Paint Lake 2 | 0 | F066-F118 | WF 10 Paint Lake Road 2 | 0 | 2021-08-13 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting968720210807-3Labourer - General - After Jan 1011660 | Corbiere and Sons Contracting968720210807-3Labourer - General - After Jan 1011660Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9687 | 20210807-3 | 53511012 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 121 | HR |  |  | 0 | 0 | 9075 | 1179.75 | 10254.75 | 2021-08-07 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM37 on Paint Lake 2 | 0 | F066-F118 | WF 10 Paint Lake Road 2 | 0 | 2021-08-13 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting968720210807-3Operator - Principle - After Jan 101219075 | Corbiere and Sons Contracting968720210807-3Operator - Principle - After Jan 101219075Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9687 | 20210807-3 | 53511012 | Access | 0 | L.O.A. | 210 | 13 | DAY |  |  | 0 | 0 | 2730 | 354.9 | 3084.9 | 2021-08-07 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM37 on Paint Lake 2 | 0 | F066-F118 | WF 10 Paint Lake Road 2 | 0 | 2021-08-13 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting968720210807-3L.O.A.132730 | Corbiere and Sons Contracting968720210807-3L.O.A.132730Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9687 | 20210807-3 | 53511012 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 0 | 0 | 1140 | 148.2 | 1288.2 | 2021-08-07 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM37 on Paint Lake 2 | 0 | F066-F118 | WF 10 Paint Lake Road 2 | 0 | 2021-08-13 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting968720210807-3Foreman121140 | Corbiere and Sons Contracting968720210807-3Foreman121140Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9687 | 20210807-3 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 36 | Dynamic | 0 | 0 |  |  | 4969.8 | 646.074 | 5615.874 | 2021-08-07 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM37 on Paint Lake 2 | 0 | F066-F118 | WF 10 Paint Lake Road 2 | 0 | 2021-08-13 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting968720210807-3Rock Truck - 30 Ton- After Jan 10364969.8 | Corbiere and Sons Contracting968720210807-3Rock Truck - 30 Ton- After Jan 10364969.8Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9687 | 20210807-3 | 53511012 | Access | 0 | Marooka- After Jan 10 | 144.6 | 5 | Dynamic | 0 | 0 |  |  | 723 | 93.99 | 816.99 | 2021-08-07 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM37 on Paint Lake 2 | 0 | F066-F118 | WF 10 Paint Lake Road 2 | 0 | 2021-08-13 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting968720210807-3Marooka- After Jan 105723 | Corbiere and Sons Contracting968720210807-3Marooka- After Jan 105723Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9687 | 20210807-3 | 53511012 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 8 | DAY | 0 | 0 |  |  | 1950 | 253.5 | 2203.5 | 2021-08-07 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM37 on Paint Lake 2 | 0 | F066-F118 | WF 10 Paint Lake Road 2 | 0 | 2021-08-13 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting968720210807-3Light Truck - Pick up- After Jan 1081950 | Corbiere and Sons Contracting968720210807-3Light Truck - Pick up- After Jan 1081950Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9687 | 20210807-3 | 53511012 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 9 | HR | 0 | 0 |  |  | 570.42 | 74.1546 | 644.5746 | 2021-08-07 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM37 on Paint Lake 2 | 0 | F066-F118 | WF 10 Paint Lake Road 2 | 0 | 2021-08-13 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting968720210807-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42 | Corbiere and Sons Contracting968720210807-3Excavator Hammer - 30 - 50 ton- After Jan 109570.42Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9687 | 20210807-3 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 34 | HR | 0 | 0 |  |  | 415.14 | 53.9682 | 469.1082 | 2021-08-07 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM37 on Paint Lake 2 | 0 | F066-F118 | WF 10 Paint Lake Road 2 | 0 | 2021-08-13 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting968720210807-3Excavator Thumb - 30 - 50 ton- After Jan 1034415.14 | Corbiere and Sons Contracting968720210807-3Excavator Thumb - 30 - 50 ton- After Jan 1034415.14Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9687 | 20210807-3 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 18 | Dynamic | 0 | 0 |  |  | 2645.28 | 343.8864 | 2989.1664 | 2021-08-07 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM37 on Paint Lake 2 | 0 | F066-F118 | WF 10 Paint Lake Road 2 | 0 | 2021-08-13 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting968720210807-3Excavator - 36 ton- After Jan 10182645.28 | Corbiere and Sons Contracting968720210807-3Excavator - 36 ton- After Jan 10182645.28Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9687 | 20210807-3 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 34 | Dynamic | 0 | 0 |  |  | 4707.3 | 611.949 | 5319.249 | 2021-08-07 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM 16-KM 18- KM30 and KM37 on Paint Lake 2 | 0 | F066-F118 | WF 10 Paint Lake Road 2 | 0 | 2021-08-13 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting968720210807-3Excavator - 30 ton- After Jan 10344707.3 | Corbiere and Sons Contracting968720210807-3Excavator - 30 ton- After Jan 10344707.3Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9680 | 20210806-3 | 53511012 | Access | 0 | Labourer - General - After Jan 10 | 60 | 5 | HR |  |  | 0 | 0 | 300 | 39 | 339 | 2021-08-06 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM30 and KM38 on Paint Lake 2 - Crews shut down early due to conditions | 0 | F066-F118 | WF10 Paint Lake Road 2 | 0 | 2021-08-12 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting968020210806-3Labourer - General - After Jan 105300 | Corbiere and Sons Contracting968020210806-3Labourer - General - After Jan 105300Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9680 | 20210806-3 | 53511012 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 60 | HR |  |  | 0 | 0 | 4500 | 585 | 5085 | 2021-08-06 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM30 and KM38 on Paint Lake 2 - Crews shut down early due to conditions | 0 | F066-F118 | WF10 Paint Lake Road 2 | 0 | 2021-08-12 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting968020210806-3Operator - Principle - After Jan 10604500 | Corbiere and Sons Contracting968020210806-3Operator - Principle - After Jan 10604500Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9680 | 20210806-3 | 53511012 | Access | 0 | L.O.A. | 210 | 14 | DAY |  |  | 0 | 0 | 2940 | 382.2 | 3322.2 | 2021-08-06 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM30 and KM38 on Paint Lake 2 - Crews shut down early due to conditions | 0 | F066-F118 | WF10 Paint Lake Road 2 | 0 | 2021-08-12 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting968020210806-3L.O.A.142940 | Corbiere and Sons Contracting968020210806-3L.O.A.142940Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9680 | 20210806-3 | 53511012 | Access | 0 | Foreman | 95 | 5 | HR |  |  | 0 | 0 | 475 | 61.75 | 536.75 | 2021-08-06 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM30 and KM38 on Paint Lake 2 - Crews shut down early due to conditions | 0 | F066-F118 | WF10 Paint Lake Road 2 | 0 | 2021-08-12 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting968020210806-3Foreman5475 | Corbiere and Sons Contracting968020210806-3Foreman5475Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9680 | 20210806-3 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 30 | Dynamic | 0 | 0 |  |  | 4141.5 | 538.395 | 4679.895 | 2021-08-06 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM30 and KM38 on Paint Lake 2 - Crews shut down early due to conditions | 0 | F066-F118 | WF10 Paint Lake Road 2 | 0 | 2021-08-12 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting968020210806-3Rock Truck - 30 Ton- After Jan 10304141.5 | Corbiere and Sons Contracting968020210806-3Rock Truck - 30 Ton- After Jan 10304141.5Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9680 | 20210806-3 | 53511012 | Access | 0 | Marooka- After Jan 10 | 144.6 | 5 | Dynamic | 0 | 0 |  |  | 723 | 93.99 | 816.99 | 2021-08-06 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM30 and KM38 on Paint Lake 2 - Crews shut down early due to conditions | 0 | F066-F118 | WF10 Paint Lake Road 2 | 0 | 2021-08-12 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting968020210806-3Marooka- After Jan 105723 | Corbiere and Sons Contracting968020210806-3Marooka- After Jan 105723Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9680 | 20210806-3 | 53511012 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 8 | DAY | 0 | 0 |  |  | 1950 | 253.5 | 2203.5 | 2021-08-06 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM30 and KM38 on Paint Lake 2 - Crews shut down early due to conditions | 0 | F066-F118 | WF10 Paint Lake Road 2 | 0 | 2021-08-12 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting968020210806-3Light Truck - Pick up- After Jan 1081950 | Corbiere and Sons Contracting968020210806-3Light Truck - Pick up- After Jan 1081950Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9680 | 20210806-3 | 53511012 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 5 | HR | 47.54 | 0 |  |  | 316.9 | 41.197 | 358.097 | 2021-08-06 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM30 and KM38 on Paint Lake 2 - Crews shut down early due to conditions | 0 | F066-F118 | WF10 Paint Lake Road 2 | 0 | 2021-08-12 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting968020210806-3Excavator Hammer - 30 - 50 ton- After Jan 105316.9 | Corbiere and Sons Contracting968020210806-3Excavator Hammer - 30 - 50 ton- After Jan 105316.9Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9680 | 20210806-3 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 20 | HR | 0 | 0 |  |  | 244.2 | 31.746 | 275.946 | 2021-08-06 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM30 and KM38 on Paint Lake 2 - Crews shut down early due to conditions | 0 | F066-F118 | WF10 Paint Lake Road 2 | 0 | 2021-08-12 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting968020210806-3Excavator Thumb - 30 - 50 ton- After Jan 1020244.2 | Corbiere and Sons Contracting968020210806-3Excavator Thumb - 30 - 50 ton- After Jan 1020244.2Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9680 | 20210806-3 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10 | Dynamic | 0 | 0 |  |  | 1469.6 | 191.048 | 1660.648 | 2021-08-06 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM30 and KM38 on Paint Lake 2 - Crews shut down early due to conditions | 0 | F066-F118 | WF10 Paint Lake Road 2 | 0 | 2021-08-12 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting968020210806-3Excavator - 36 ton- After Jan 10101469.6 | Corbiere and Sons Contracting968020210806-3Excavator - 36 ton- After Jan 10101469.6Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9680 | 20210806-3 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 20 | Dynamic | 0 | 0 |  |  | 2769 | 359.97 | 3128.97 | 2021-08-06 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work being done from KM30 and KM38 on Paint Lake 2 - Crews shut down early due to conditions | 0 | F066-F118 | WF10 Paint Lake Road 2 | 0 | 2021-08-12 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting968020210806-3Excavator - 30 ton- After Jan 10202769 | Corbiere and Sons Contracting968020210806-3Excavator - 30 ton- After Jan 10202769Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9679 | 20210805-3 | 53511012 | Access | 0 | Labourer - General - After Jan 10 | 60 | 11 | HR |  |  | 0 | 0 | 660 | 85.8 | 745.8 | 2021-08-05 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work continuing from KM30 and KM38 on Paint Lake Road 2 | 0 | F066-F118 | WF 10 Paint Lake Road 2 | 0 | 2021-08-12 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting967920210805-3Labourer - General - After Jan 1011660 | Corbiere and Sons Contracting967920210805-3Labourer - General - After Jan 1011660Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9679 | 20210805-3 | 53511012 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 11 | HR |  |  | 0 | 0 | 770 | 100.1 | 870.1 | 2021-08-05 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work continuing from KM30 and KM38 on Paint Lake Road 2 | 0 | F066-F118 | WF 10 Paint Lake Road 2 | 0 | 2021-08-12 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting967920210805-3Driver - AZ - After Jan 1011770 | Corbiere and Sons Contracting967920210805-3Driver - AZ - After Jan 1011770Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9679 | 20210805-3 | 53511012 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 104 | HR |  |  | 0 | 0 | 7800 | 1014 | 8814 | 2021-08-05 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work continuing from KM30 and KM38 on Paint Lake Road 2 | 0 | F066-F118 | WF 10 Paint Lake Road 2 | 0 | 2021-08-12 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting967920210805-3Operator - Principle - After Jan 101047800 | Corbiere and Sons Contracting967920210805-3Operator - Principle - After Jan 101047800Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9679 | 20210805-3 | 53511012 | Access | 0 | L.O.A. | 210 | 13 | DAY |  |  | 0 | 0 | 2730 | 354.9 | 3084.9 | 2021-08-05 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work continuing from KM30 and KM38 on Paint Lake Road 2 | 0 | F066-F118 | WF 10 Paint Lake Road 2 | 0 | 2021-08-12 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting967920210805-3L.O.A.132730 | Corbiere and Sons Contracting967920210805-3L.O.A.132730Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9679 | 20210805-3 | 53511012 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 0 | 0 | 1140 | 148.2 | 1288.2 | 2021-08-05 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work continuing from KM30 and KM38 on Paint Lake Road 2 | 0 | F066-F118 | WF 10 Paint Lake Road 2 | 0 | 2021-08-12 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting967920210805-3Foreman121140 | Corbiere and Sons Contracting967920210805-3Foreman121140Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9679 | 20210805-3 | 53511012 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 11 | Dynamic | 0 | 0 |  |  | 1346.29 | 175.0177 | 1521.3077 | 2021-08-05 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work continuing from KM30 and KM38 on Paint Lake Road 2 | 0 | F066-F118 | WF 10 Paint Lake Road 2 | 0 | 2021-08-12 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting967920210805-3Tractor Trailer - 60 Ton- After Jan 10111346.29 | Corbiere and Sons Contracting967920210805-3Tractor Trailer - 60 Ton- After Jan 10111346.29Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9679 | 20210805-3 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 36 | Dynamic | 0 | 0 |  |  | 4969.8 | 646.074 | 5615.874 | 2021-08-05 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work continuing from KM30 and KM38 on Paint Lake Road 2 | 0 | F066-F118 | WF 10 Paint Lake Road 2 | 0 | 2021-08-12 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting967920210805-3Rock Truck - 30 Ton- After Jan 10364969.8 | Corbiere and Sons Contracting967920210805-3Rock Truck - 30 Ton- After Jan 10364969.8Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9679 | 20210805-3 | 53511012 | Access | 0 | Marooka- After Jan 10 | 144.6 | 5 | Dynamic | 0 | 0 |  |  | 723 | 93.99 | 816.99 | 2021-08-05 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work continuing from KM30 and KM38 on Paint Lake Road 2 | 0 | F066-F118 | WF 10 Paint Lake Road 2 | 0 | 2021-08-12 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting967920210805-3Marooka- After Jan 105723 | Corbiere and Sons Contracting967920210805-3Marooka- After Jan 105723Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9679 | 20210805-3 | 53511012 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 8 | DAY | 0 | 0 |  |  | 1950 | 253.5 | 2203.5 | 2021-08-05 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work continuing from KM30 and KM38 on Paint Lake Road 2 | 0 | F066-F118 | WF 10 Paint Lake Road 2 | 0 | 2021-08-12 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting967920210805-3Light Truck - Pick up- After Jan 1081950 | Corbiere and Sons Contracting967920210805-3Light Truck - Pick up- After Jan 1081950Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9679 | 20210805-3 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 33 | HR | 0 | 0 |  |  | 402.93 | 52.3809 | 455.3109 | 2021-08-05 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work continuing from KM30 and KM38 on Paint Lake Road 2 | 0 | F066-F118 | WF 10 Paint Lake Road 2 | 0 | 2021-08-12 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting967920210805-3Excavator Thumb - 30 - 50 ton- After Jan 1033402.93 | Corbiere and Sons Contracting967920210805-3Excavator Thumb - 30 - 50 ton- After Jan 1033402.93Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9679 | 20210805-3 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 18 | Dynamic | 0 | 0 |  |  | 2645.28 | 343.8864 | 2989.1664 | 2021-08-05 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work continuing from KM30 and KM38 on Paint Lake Road 2 | 0 | F066-F118 | WF 10 Paint Lake Road 2 | 0 | 2021-08-12 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting967920210805-3Excavator - 36 ton- After Jan 10182645.28 | Corbiere and Sons Contracting967920210805-3Excavator - 36 ton- After Jan 10182645.28Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9679 | 20210805-3 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 24 | Dynamic | 0 | 0 |  |  | 3322.8 | 431.964 | 3754.764 | 2021-08-05 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work continuing from KM30 and KM38 on Paint Lake Road 2 | 0 | F066-F118 | WF 10 Paint Lake Road 2 | 0 | 2021-08-12 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting967920210805-3Excavator - 30 ton- After Jan 10243322.8 | Corbiere and Sons Contracting967920210805-3Excavator - 30 ton- After Jan 10243322.8Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9678 | 20210804-3 | 53511012 | Access | 0 | Labourer - General - After Jan 10 | 60 | 11 | HR |  |  | 0 | 0 | 660 | 85.8 | 745.8 | 2021-08-04 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work continuing from KM30 and KM38 on Paint Lake Road 2 | 0 | F066-F118 | WF10 Paint Lake Road 2 | 0 | 2021-08-12 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting967820210804-3Labourer - General - After Jan 1011660 | Corbiere and Sons Contracting967820210804-3Labourer - General - After Jan 1011660Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9678 | 20210804-3 | 53511012 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 44 | HR |  |  | 70 | 0 | 3080 | 400.4 | 3480.4 | 2021-08-04 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work continuing from KM30 and KM38 on Paint Lake Road 2 | 0 | F066-F118 | WF10 Paint Lake Road 2 | 0 | 2021-08-12 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting967820210804-3Driver - AZ - After Jan 10443080 | Corbiere and Sons Contracting967820210804-3Driver - AZ - After Jan 10443080Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9678 | 20210804-3 | 53511012 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 77 | HR |  |  | 0 | 0 | 5775 | 750.75 | 6525.75 | 2021-08-04 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work continuing from KM30 and KM38 on Paint Lake Road 2 | 0 | F066-F118 | WF10 Paint Lake Road 2 | 0 | 2021-08-12 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting967820210804-3Operator - Principle - After Jan 10775775 | Corbiere and Sons Contracting967820210804-3Operator - Principle - After Jan 10775775Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9678 | 20210804-3 | 53511012 | Access | 0 | L.O.A. | 210 | 10 | DAY |  |  | 0 | 0 | 2100 | 273 | 2373 | 2021-08-04 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work continuing from KM30 and KM38 on Paint Lake Road 2 | 0 | F066-F118 | WF10 Paint Lake Road 2 | 0 | 2021-08-12 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting967820210804-3L.O.A.102100 | Corbiere and Sons Contracting967820210804-3L.O.A.102100Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9678 | 20210804-3 | 53511012 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 0 | 0 | 1140 | 148.2 | 1288.2 | 2021-08-04 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work continuing from KM30 and KM38 on Paint Lake Road 2 | 0 | F066-F118 | WF10 Paint Lake Road 2 | 0 | 2021-08-12 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting967820210804-3Foreman121140 | Corbiere and Sons Contracting967820210804-3Foreman121140Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9678 | 20210804-3 | 53511012 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 44 | Dynamic | 91.79 | 0 |  |  | 5385.16 | 700.0708 | 6085.2308 | 2021-08-04 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work continuing from KM30 and KM38 on Paint Lake Road 2 | 0 | F066-F118 | WF10 Paint Lake Road 2 | 0 | 2021-08-12 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting967820210804-3Tractor Trailer - 60 Ton- After Jan 10445385.16 | Corbiere and Sons Contracting967820210804-3Tractor Trailer - 60 Ton- After Jan 10445385.16Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9678 | 20210804-3 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 9 | Dynamic | 0 | 0 |  |  | 1242.45 | 161.5185 | 1403.9685 | 2021-08-04 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work continuing from KM30 and KM38 on Paint Lake Road 2 | 0 | F066-F118 | WF10 Paint Lake Road 2 | 0 | 2021-08-12 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting967820210804-3Rock Truck - 30 Ton- After Jan 1091242.45 | Corbiere and Sons Contracting967820210804-3Rock Truck - 30 Ton- After Jan 1091242.45Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9678 | 20210804-3 | 53511012 | Access | 0 | Marooka- After Jan 10 | 144.6 | 5 | Dynamic | 0 | 0 |  |  | 723 | 93.99 | 816.99 | 2021-08-04 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work continuing from KM30 and KM38 on Paint Lake Road 2 | 0 | F066-F118 | WF10 Paint Lake Road 2 | 0 | 2021-08-12 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting967820210804-3Marooka- After Jan 105723 | Corbiere and Sons Contracting967820210804-3Marooka- After Jan 105723Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9678 | 20210804-3 | 53511012 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 5 | DAY | 0 | 0 |  |  | 1218.75 | 158.4375 | 1377.1875 | 2021-08-04 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work continuing from KM30 and KM38 on Paint Lake Road 2 | 0 | F066-F118 | WF10 Paint Lake Road 2 | 0 | 2021-08-12 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting967820210804-3Light Truck - Pick up- After Jan 1051218.75 | Corbiere and Sons Contracting967820210804-3Light Truck - Pick up- After Jan 1051218.75Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9678 | 20210804-3 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 36 | HR | 0 | 0 |  |  | 439.56 | 57.1428 | 496.7028 | 2021-08-04 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work continuing from KM30 and KM38 on Paint Lake Road 2 | 0 | F066-F118 | WF10 Paint Lake Road 2 | 0 | 2021-08-12 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting967820210804-3Excavator Thumb - 30 - 50 ton- After Jan 1036439.56 | Corbiere and Sons Contracting967820210804-3Excavator Thumb - 30 - 50 ton- After Jan 1036439.56Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9678 | 20210804-3 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 18 | Dynamic | 0 | 0 |  |  | 2645.28 | 343.8864 | 2989.1664 | 2021-08-04 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work continuing from KM30 and KM38 on Paint Lake Road 2 | 0 | F066-F118 | WF10 Paint Lake Road 2 | 0 | 2021-08-12 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting967820210804-3Excavator - 36 ton- After Jan 10182645.28 | Corbiere and Sons Contracting967820210804-3Excavator - 36 ton- After Jan 10182645.28Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9678 | 20210804-3 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 27 | Dynamic | 0 | 0 |  |  | 3738.15 | 485.9595 | 4224.1095 | 2021-08-04 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work continuing from KM30 and KM38 on Paint Lake Road 2 | 0 | F066-F118 | WF10 Paint Lake Road 2 | 0 | 2021-08-12 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting967820210804-3Excavator - 30 ton- After Jan 10273738.15 | Corbiere and Sons Contracting967820210804-3Excavator - 30 ton- After Jan 10273738.15Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9671 | 20210803-3 | 53511012 | Access | 0 | Labourer - General - After Jan 10 | 60 | 11 | HR |  |  | 60 | 0 | 660 | 85.8 | 745.8 | 2021-08-03 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work continuing from KM30 and KM38 on Paint Lake Road 2 |  | F066-F118 | WF10 Paint Lake 2 | 0 | 2021-08-12 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting967120210803-3Labourer - General - After Jan 1011660 | Corbiere and Sons Contracting967120210803-3Labourer - General - After Jan 1011660Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9671 | 20210803-3 | 53511012 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 77 | HR |  |  | 75 | 0 | 5775 | 750.75 | 6525.75 | 2021-08-03 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work continuing from KM30 and KM38 on Paint Lake Road 2 |  | F066-F118 | WF10 Paint Lake 2 | 0 | 2021-08-12 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting967120210803-3Operator - Principle - After Jan 10775775 | Corbiere and Sons Contracting967120210803-3Operator - Principle - After Jan 10775775Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9671 | 20210803-3 | 53511012 | Access | 0 | L.O.A. | 210 | 9 | DAY |  |  |  | 0 | 1890 | 245.7 | 2135.7 | 2021-08-03 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work continuing from KM30 and KM38 on Paint Lake Road 2 |  | F066-F118 | WF10 Paint Lake 2 | 0 | 2021-08-12 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting967120210803-3L.O.A.91890 | Corbiere and Sons Contracting967120210803-3L.O.A.91890Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9671 | 20210803-3 | 53511012 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2021-08-03 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work continuing from KM30 and KM38 on Paint Lake Road 2 |  | F066-F118 | WF10 Paint Lake 2 | 0 | 2021-08-12 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting967120210803-3Foreman121140 | Corbiere and Sons Contracting967120210803-3Foreman121140Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9671 | 20210803-3 | 53511012 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 9 | Dynamic | 103.54 | 0 |  |  | 1242.45 | 161.5185 | 1403.9685 | 2021-08-03 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work continuing from KM30 and KM38 on Paint Lake Road 2 |  | F066-F118 | WF10 Paint Lake 2 | 0 | 2021-08-12 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting967120210803-3Rock Truck - 30 Ton- After Jan 1091242.45 | Corbiere and Sons Contracting967120210803-3Rock Truck - 30 Ton- After Jan 1091242.45Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9671 | 20210803-3 | 53511012 | Access | 0 | Marooka- After Jan 10 | 144.6 | 5 | Dynamic | 108.45 | 0 |  |  | 723 | 93.99 | 816.99 | 2021-08-03 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work continuing from KM30 and KM38 on Paint Lake Road 2 |  | F066-F118 | WF10 Paint Lake 2 | 0 | 2021-08-12 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting967120210803-3Marooka- After Jan 105723 | Corbiere and Sons Contracting967120210803-3Marooka- After Jan 105723Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9671 | 20210803-3 | 53511012 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 5 | DAY | 182.81 | 0 |  |  | 1218.75 | 158.4375 | 1377.1875 | 2021-08-03 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work continuing from KM30 and KM38 on Paint Lake Road 2 |  | F066-F118 | WF10 Paint Lake 2 | 0 | 2021-08-12 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting967120210803-3Light Truck - Pick up- After Jan 1051218.75 | Corbiere and Sons Contracting967120210803-3Light Truck - Pick up- After Jan 1051218.75Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9671 | 20210803-3 | 53511012 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 36 | HR | 9.16 | 0 |  |  | 439.56 | 57.1428 | 496.7028 | 2021-08-03 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work continuing from KM30 and KM38 on Paint Lake Road 2 |  | F066-F118 | WF10 Paint Lake 2 | 0 | 2021-08-12 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting967120210803-3Excavator Thumb - 30 - 50 ton- After Jan 1036439.56 | Corbiere and Sons Contracting967120210803-3Excavator Thumb - 30 - 50 ton- After Jan 1036439.56Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9671 | 20210803-3 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 18 | Dynamic | 110.22 | 0 |  |  | 2645.28 | 343.8864 | 2989.1664 | 2021-08-03 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work continuing from KM30 and KM38 on Paint Lake Road 2 |  | F066-F118 | WF10 Paint Lake 2 | 0 | 2021-08-12 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting967120210803-3Excavator - 36 ton- After Jan 10182645.28 | Corbiere and Sons Contracting967120210803-3Excavator - 36 ton- After Jan 10182645.28Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9671 | 20210803-3 | 53511012 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 27 | Dynamic | 103.84 | 0 |  |  | 3738.15 | 485.9595 | 4224.1095 | 2021-08-03 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work continuing from KM30 and KM38 on Paint Lake Road 2 |  | F066-F118 | WF10 Paint Lake 2 | 0 | 2021-08-12 |  | 43 | 2021-08-13 | [5 empty] | Will Ouimet | 10 | Corbiere and Sons Contracting967120210803-3Excavator - 30 ton- After Jan 10273738.15 | Corbiere and Sons Contracting967120210803-3Excavator - 30 ton- After Jan 10273738.15Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9638 | 20210727-3 | 53511012 | Access | 0 | Marooka- After Jan 10 | 144.6 | 5 | Dynamic | 108.45 | 0 |  |  | 723 | 93.99 | 816.99 | 2021-07-27 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Paint Lake 2 from KM34-KM37 and KM44-KM45 | 6 | F066-F118 | Paint lake Road 2 | 0 | 2021-08-02 |  | 37 | 2021-08-02 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting963820210727-3Marooka- After Jan 105723 | Corbiere and Sons Contracting963820210727-3Marooka- After Jan 105723Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9636 | 20210726-3 | 53511012 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2021-07-26 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Paint Lake 2 from KM43-KM40 and from F066-F073 | 6 | F066-F118 | Paint lake Road 2 | 0 | 2021-08-02 |  | 37 | 2021-08-02 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting963620210726-3Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting963620210726-3Light Truck - Pick up- After Jan 103731.25Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9636 | 20210726-3 | 53511012 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2021-07-26 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Paint Lake 2 from KM43-KM40 and from F066-F073 | 6 | F066-F118 | Paint lake Road 2 | 0 | 2021-08-02 |  | 37 | 2021-08-02 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting963620210726-3Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting963620210726-3Excavator - 36 ton- After Jan 1091322.64Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
Corbiere and Sons Contracting | 6 | 0 | 9634 | 20210725-3 | 53511012 | Access | 0 | Marooka- After Jan 10 | 144.6 | 5 | Dynamic | 108.45 | 0 |  |  | 723 | 93.99 | 816.99 | 2021-07-25 | 0 | Inv#142-R01 | 2021-08-19 | 159 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road work on Paint Lake Road from KM29-KM34, KM45-KM43 and KM27-KM30 - Darwin spent part of day on Henson at KM17.5 - Time split | 6 | F066-F118 | Paint Lake Road 2 | 0 | 2021-08-02 |  | 37 | 2021-08-02 | [5 empty] | Harold Furlong | 10 | Corbiere and Sons Contracting963420210725-3Marooka- After Jan 105723 | Corbiere and Sons Contracting963420210725-3Marooka- After Jan 105723Inv#142-R01 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7181 | KL-20210725-1 | 53511012 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2021-07-25 | 0 | OEWT-PA19-Lem-R1 | 2021-08-03 | 62 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul existing material from ROW to F036 access | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-07-28 |  | 36 | 2021-07-30 | [5 empty] | Mike Lecocq | 10 | KABI LAKE FOREST PRODUCTS LTD7181KL-20210725-1Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD7181KL-20210725-1Supervisor3252OEWT-PA19-Lem-R1 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7181 | KL-20210725-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.90909 | DAY |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-07-25 | 0 | OEWT-PA19-Lem-R1 | 2021-08-03 | 62 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul existing material from ROW to F036 access | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-07-28 |  | 36 | 2021-07-30 | [5 empty] | Mike Lecocq | 10 | KABI LAKE FOREST PRODUCTS LTD7181KL-20210725-1L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7181KL-20210725-1L.O.A.0.9090909221.8182OEWT-PA19-Lem-R1 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7181 | KL-20210725-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.90909 | DAY |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-07-25 | 0 | OEWT-PA19-Lem-R1 | 2021-08-03 | 62 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul existing material from ROW to F036 access | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-07-28 |  | 36 | 2021-07-30 | [5 empty] | Mike Lecocq | 10 | KABI LAKE FOREST PRODUCTS LTD7181KL-20210725-1L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7181KL-20210725-1L.O.A.0.9090909221.8182OEWT-PA19-Lem-R1 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7181 | KL-20210725-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.90909 | DAY |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-07-25 | 0 | OEWT-PA19-Lem-R1 | 2021-08-03 | 62 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul existing material from ROW to F036 access | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-07-28 |  | 36 | 2021-07-30 | [5 empty] | Mike Lecocq | 10 | KABI LAKE FOREST PRODUCTS LTD7181KL-20210725-1L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7181KL-20210725-1L.O.A.0.9090909221.8182OEWT-PA19-Lem-R1 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7181 | KL-20210725-1 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 23 | HR | 19 | 0 |  |  | 575 | 74.75 | 649.75 | 2021-07-25 | 0 | OEWT-PA19-Lem-R1 | 2021-08-03 | 62 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul existing material from ROW to F036 access | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-07-28 |  | 36 | 2021-07-30 | [5 empty] | Mike Lecocq | 10 | KABI LAKE FOREST PRODUCTS LTD7181KL-20210725-1Pickup 1/2 Ton23575 | KABI LAKE FOREST PRODUCTS LTD7181KL-20210725-1Pickup 1/2 Ton23575OEWT-PA19-Lem-R1 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7181 | KL-20210725-1 | 53511012 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 10 | HR | 134 | 0 |  |  | 1780 | 231.4 | 2011.4 | 2021-07-25 | 0 | OEWT-PA19-Lem-R1 | 2021-08-03 | 62 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul existing material from ROW to F036 access | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-07-28 |  | 36 | 2021-07-30 | [5 empty] | Mike Lecocq | 10 | KABI LAKE FOREST PRODUCTS LTD7181KL-20210725-1CAT 25 ton Articulated Truck101780 | KABI LAKE FOREST PRODUCTS LTD7181KL-20210725-1CAT 25 ton Articulated Truck101780OEWT-PA19-Lem-R1 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7181 | KL-20210725-1 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 20 | HR | 147 | 0 |  |  | 3900 | 507 | 4407 | 2021-07-25 | 0 | OEWT-PA19-Lem-R1 | 2021-08-03 | 62 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul existing material from ROW to F036 access | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-07-28 |  | 36 | 2021-07-30 | [5 empty] | Mike Lecocq | 10 | KABI LAKE FOREST PRODUCTS LTD7181KL-20210725-130 Ton Excavator c/w Hydraulic Thumb203900 | KABI LAKE FOREST PRODUCTS LTD7181KL-20210725-130 Ton Excavator c/w Hydraulic Thumb203900OEWT-PA19-Lem-R1 |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7279 | KL-20210825-3 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2323.64 | Each |  |  |  |  | 2323.64 | 302.0732 | 2625.7132 | 2021-08-25 | 0 | OEWT-PA20-Lem | 2021-09-08 | 81 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator starting sloping and cleaning up excavation @ km 49/rock truck hauling existing material from Km 42 to Morin Excavator/ Excavator 2 fixing up access from Km 44 to Km 46 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-09-05 | MC-20210825-1 | Excavator spreading existing material on road sections @ km 41/42 - MC-13132 |  |  |  | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7279KL-20210825-33rd Party Services2323.642323.64 | KABI LAKE FOREST PRODUCTS LTD7279KL-20210825-33rd Party Services2323.642323.64OEWT-PA20-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7275 | KL-20210824-3 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2065.45 | Each |  |  |  |  | 2065.45 | 268.5085 | 2333.9585 | 2021-08-24 | 0 | OEWT-PA20-Lem | 2021-09-08 | 81 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul material from km 17 on Hensen Road to Corbiere Dozer@km 44.5/43.5/3 rock trucks Kabi, Corbiere and Valard/ Excavator 2 working ahead @km 42 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-09-05 | MC-20210824-1 | Slope and clean up excavations @ F108/level ruts and shape road F107 to F108 - MC-13131 |  |  |  | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7275KL-20210824-33rd Party Services2065.452065.45 | KABI LAKE FOREST PRODUCTS LTD7275KL-20210824-33rd Party Services2065.452065.45OEWT-PA20-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7275 | KL-20210824-3 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2452.73 | Each |  |  |  |  | 2452.73 | 318.8549 | 2771.5849 | 2021-08-24 | 0 | OEWT-PA20-Lem | 2021-09-08 | 81 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul material from km 17 on Hensen Road to Corbiere Dozer@km 44.5/43.5/3 rock trucks Kabi, Corbiere and Valard/ Excavator 2 working ahead @km 42 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-09-05 | SSF-20210824-2 | Continue leveling ruts and replacing access mats fromKm 45 to Km 44 for gravel - SSF-14346 |  |  |  | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7275KL-20210824-33rd Party Services2452.732452.73 | KABI LAKE FOREST PRODUCTS LTD7275KL-20210824-33rd Party Services2452.732452.73OEWT-PA20-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7271 | KL-20210823-5 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2323.64 | Each |  |  |  |  | 2323.64 | 302.0732 | 2625.7132 | 2021-08-23 | 0 | OEWT-PA20-Lem | 2021-09-08 | 81 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load & Haul existing material from Km 17 on Hensen road to Corbiere dozer@ Km 45/44. One Kabi rock truck, Corbiere and Valard/ 2nd Ex working ahead of dozer. | 10 | F033-F118 | Paint Lake Road 2 | 0 |  |  | 37 | 2021-08-31 | MC-20210823-1 | Check for capping material & pile up stockpile @ F-108. |  |  |  | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7271KL-20210823-53rd Party Services2323.642323.64 | KABI LAKE FOREST PRODUCTS LTD7271KL-20210823-53rd Party Services2323.642323.64OEWT-PA20-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7271 | KL-20210823-5 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2323.64 | Each |  |  |  |  | 2323.64 | 302.0732 | 2625.7132 | 2021-08-23 | 0 | OEWT-PA20-Lem | 2021-09-08 | 81 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load & Haul existing material from Km 17 on Hensen road to Corbiere dozer@ Km 45/44. One Kabi rock truck, Corbiere and Valard/ 2nd Ex working ahead of dozer. | 10 | F033-F118 | Paint Lake Road 2 | 0 |  |  | 37 | 2021-08-31 | SSF-20210823-2 | Continue leveling ruts and shaping road from 46 Km to 44 Km for gravel haul. SSF-14343 |  |  |  | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7271KL-20210823-53rd Party Services2323.642323.64 | KABI LAKE FOREST PRODUCTS LTD7271KL-20210823-53rd Party Services2323.642323.64OEWT-PA20-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7267 | KL-20210822-4 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2323.64 | Each |  |  |  |  | 2323.64 | 302.0732 | 2625.7132 | 2021-08-22 | 0 | OEWT-PA20-Lem | 2021-09-08 | 81 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load & Haul existing material from Km 17 on Hensen road to Corbiere dozer@ Km 45/4. One Kabi rock truck, one Corbiere, and 1 Valard. 2nd excavator working ahead of dozer. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 50 | 2021-09-01 | MC-20210822-1 | Continue road maintenance and shaping road from F110 to F111 - MC-13128 |  |  |  | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7267KL-20210822-43rd Party Services2323.642323.64 | KABI LAKE FOREST PRODUCTS LTD7267KL-20210822-43rd Party Services2323.642323.64OEWT-PA20-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7267 | KL-20210822-4 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2581.82 | Each |  |  |  |  | 2581.82 | 335.6366 | 2917.4566 | 2021-08-22 | 0 | OEWT-PA20-Lem | 2021-09-08 | 81 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load & Haul existing material from Km 17 on Hensen road to Corbiere dozer@ Km 45/4. One Kabi rock truck, one Corbiere, and 1 Valard. 2nd excavator working ahead of dozer. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 50 | 2021-09-01 | SSF-20210822-1 | Continue leveling ruts and shaping road from 46.5 Km to 45 Km for gravel haul and spreading gravel where required. - SSF-14341 |  |  |  | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7267KL-20210822-43rd Party Services2581.822581.82 | KABI LAKE FOREST PRODUCTS LTD7267KL-20210822-43rd Party Services2581.822581.82OEWT-PA20-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7257 | KL-20210821-5 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2323.64 | Each |  |  |  |  | 2323.64 | 302.0732 | 2625.7132 | 2021-08-21 | 0 | OEWT-PA20-Lem | 2021-09-08 | 81 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load & Haul existing material from Km 17 on Hensen road to Corbiere dozer@ Km 45/46/3 rock trucks Kabi, Corbiere and Valard/ 2nd Ex working ahead of dozer | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-08-26 |  | 50 | 2021-08-27 | MC-20210821-1 | Continue road maintenance and shaping road from F110 to F111 - MC-13128 |  |  |  | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7257KL-20210821-53rd Party Services2323.642323.64 | KABI LAKE FOREST PRODUCTS LTD7257KL-20210821-53rd Party Services2323.642323.64OEWT-PA20-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7257 | KL-20210821-5 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2581.82 | Each |  |  |  |  | 2581.82 | 335.6366 | 2917.4566 | 2021-08-21 | 0 | OEWT-PA20-Lem | 2021-09-08 | 81 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load & Haul existing material from Km 17 on Hensen road to Corbiere dozer@ Km 45/46/3 rock trucks Kabi, Corbiere and Valard/ 2nd Ex working ahead of dozer | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-08-26 |  | 50 | 2021-08-27 | SSF-20210821-2 | Continue leveling ruts and shaping road from 46.5 Km to 45 Km for gravel haul - SSF-14340 |  |  |  | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7257KL-20210821-53rd Party Services2581.822581.82 | KABI LAKE FOREST PRODUCTS LTD7257KL-20210821-53rd Party Services2581.822581.82OEWT-PA20-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7252 | KL-20210820-5 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2323.64 | Each |  |  |  |  | 2323.64 | 302.0732 | 2625.7132 | 2021-08-20 | 0 | OEWT-PA20-Lem | 2021-09-08 | 81 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul existing material from Km 17 on Hensen Road to Corbiere Dozer @Km 45/46/ 3 rock trucks Kabi, Corbiere and Valard/2nd Ex working ahead of Dozer | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-08-25 |  | 50 | 2021-08-27 | MC-20210820-1 | Continue road maintenace shaping road to ROW and from F109 to F110 - MC-13127 |  |  |  | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7252KL-20210820-53rd Party Services2323.642323.64 | KABI LAKE FOREST PRODUCTS LTD7252KL-20210820-53rd Party Services2323.642323.64OEWT-PA20-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7252 | KL-20210820-5 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2194.55 | Each |  |  |  |  | 2194.55 | 285.2915 | 2479.8415 | 2021-08-20 | 0 | OEWT-PA20-Lem | 2021-09-08 | 81 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul existing material from Km 17 on Hensen Road to Corbiere Dozer @Km 45/46/ 3 rock trucks Kabi, Corbiere and Valard/2nd Ex working ahead of Dozer | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-08-25 |  | 50 | 2021-08-27 | SSF-20210820-2 | Continue Leveling ruts and shaping road from Km 47 to km 45 For gravel haul - SSF-14337 |  |  |  | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7252KL-20210820-53rd Party Services2194.552194.55 | KABI LAKE FOREST PRODUCTS LTD7252KL-20210820-53rd Party Services2194.552194.55OEWT-PA20-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7248 | KL-20210819-4 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2323.64 | Each |  |  |  |  | 2323.64 | 302.0732 | 2625.7132 | 2021-08-19 | 0 | OEWT-PA20-Lem | 2021-09-08 | 81 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul existing material from Km 17 on Hensen Road to Corbiere Dozer @Km 45/46/ 3 rock trucks Kabi, Corbiere and Valard/2nd Ex working ahead of Dozer | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-08-25 |  | 50 | 2021-08-27 | MC-20210819-1 | Excavator Tracking from Km 49 to Km 44 and start road maintenace shaping ahead of gravel crew - MC-13126 |  |  |  | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7248KL-20210819-43rd Party Services2323.642323.64 | KABI LAKE FOREST PRODUCTS LTD7248KL-20210819-43rd Party Services2323.642323.64OEWT-PA20-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7213 | KL-20210812-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2425.41 | Each |  |  |  |  | 2425.41 | 315.3033 | 2740.7133 | 2021-08-12 | 0 | OEWT-PA20-Lem | 2021-09-08 | 81 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading Existing material from KM 17 on Hensen Road and gravel access mat sections @ 45/44 km on Paint Lake Road 2/ 1 Kabi Rock Truck and 1 Valard Rock truck/load mats on Valard 2nd rock truck. Finish grading Paint Lake Road 2 to Km 13 and touch up on way out to Paint Lake Road - SSF-14325 | 10 | F033-F118 | Paint ake Road 2 | 0 | 2021-08-19 |  | 50 | 2021-08-20 | SSF-20210812-1 | grading road - SSF-14324 |  |  |  | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7213KL-20210812-13rd Party Services2425.412425.41 | KABI LAKE FOREST PRODUCTS LTD7213KL-20210812-13rd Party Services2425.412425.41OEWT-PA20-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7212 | KL-20210811-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2425.41 | Each |  |  |  |  | 2425.41 | 315.3033 | 2740.7133 | 2021-08-11 | 0 | OEWT-PA20-Lem | 2021-09-08 | 81 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading Existing material from KM 17 on Hensen Road and gravel road sections @ 45/44 km on Paint Lake Road 2 as per Valard/ 1 Kabi Rock Truck and 1 Valard Rock truck/2 Valard Rock truck. Continue grading Paint Lake Road 2 from Km 7.5 to Km 11.5 - SSF-14324 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-08-19 |  | 50 | 2021-08-20 | SSF-20210811-1 | grading road - SSF-14324 |  |  |  | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7212KL-20210811-13rd Party Services2425.412425.41 | KABI LAKE FOREST PRODUCTS LTD7212KL-20210811-13rd Party Services2425.412425.41OEWT-PA20-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7211 | KL-20210810-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2529 | Each |  |  |  |  | 2529 | 328.77 | 2857.77 | 2021-08-10 | 0 | OEWT-PA20-Lem | 2021-09-08 | 81 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading Existing material from KM 17 on Hensen Road and gravel road sections @ 46/44 km on Paint Lake Road 2 as per Valard/ 1 Kabi Rock Truck and 1 Valard Rock truck/loading mats on Valard Rock truck. | 10 | F033-F118 | Paint Lake Road2 | 0 | 2021-08-19 |  | 50 | 2021-08-20 | SSF-20210810-1 | Grading road - SSF-14323 |  |  |  | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7211KL-20210810-13rd Party Services25292529 | KABI LAKE FOREST PRODUCTS LTD7211KL-20210810-13rd Party Services25292529OEWT-PA20-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7210 | KL-20210809-3 | 53511012 | Access | 0 | 3rd Party Services | 1 | 1160.91 | Each |  |  |  |  | 1160.91 | 150.9183 | 1311.8283 | 2021-08-09 | 0 | OEWT-PA20-Lem | 2021-09-08 | 81 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float grader from Hensen road to Paint Lake Road #2, start grading Paint Lake Road 2 from Km 0 to Km 2 - SSF-14322 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-08-19 |  | 50 | 2021-08-20 | SSF-20210809-2 | Grading road - SSF-14321 |  |  |  | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7210KL-20210809-33rd Party Services1160.911160.91 | KABI LAKE FOREST PRODUCTS LTD7210KL-20210809-33rd Party Services1160.911160.91OEWT-PA20-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7198 | KL-20210803-3 | 53511012 | Access | 0 | Labourer | 65 | 3 | HR |  |  | 65 | 0 | 195 | 25.35 | 220.35 | 2021-08-03 | 0 | OEWT-PA20-Lem | 2021-09-08 | 81 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Labourer & Operatortracking excavators from F-036 to 12km on Paint Lake Road 2 for float access. | 10 | F118-F127 | Paint Lake Road 2 | 0 | 2021-08-12 |  | 14 | 2021-08-13 | [5 empty] | William Ouimet | 10 | KABI LAKE FOREST PRODUCTS LTD7198KL-20210803-3Labourer3195 | KABI LAKE FOREST PRODUCTS LTD7198KL-20210803-3Labourer3195OEWT-PA20-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7198 | KL-20210803-3 | 53511012 | Access | 0 | Supervisor | 84 | 0.5 | HR |  |  | 84 | 0 | 42 | 5.46 | 47.46 | 2021-08-03 | 0 | OEWT-PA20-Lem | 2021-09-08 | 81 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Labourer & Operatortracking excavators from F-036 to 12km on Paint Lake Road 2 for float access. | 10 | F118-F127 | Paint Lake Road 2 | 0 | 2021-08-12 |  | 14 | 2021-08-13 | [5 empty] | William Ouimet | 10 | KABI LAKE FOREST PRODUCTS LTD7198KL-20210803-3Supervisor0.542 | KABI LAKE FOREST PRODUCTS LTD7198KL-20210803-3Supervisor0.542OEWT-PA20-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7192 | KL-20210729-1 | 53511012 | Access | 0 | Supervisor | 84 | 0.5 | HR |  |  | 84 | 0 | 42 | 5.46 | 47.46 | 2021-07-29 | 0 | OEWT-PA20-Lem | 2021-09-08 | 81 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working to F034 access, moving road @ F036 & moving log deck @ F037. | 10 | F009-F065 | Paint Lake Road | 0 | 2021-08-06 |  | 14 | 2021-08-08 | [5 empty] | William Ouimet | 10 | KABI LAKE FOREST PRODUCTS LTD7192KL-20210729-1Supervisor0.542 | KABI LAKE FOREST PRODUCTS LTD7192KL-20210729-1Supervisor0.542OEWT-PA20-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7191 | KL-20210728-1 | 53511012 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2021-07-28 | 0 | OEWT-PA20-Lem | 2021-09-08 | 81 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavtor 1 loading rock truck, RT hauling material to excavator 2. Excavator 2 spreading material and working on road from F036 to F034 Access. | 10 | F009-F065 | Paint Lake Road | 0 | 2021-08-06 |  | 14 | 2021-08-08 | [5 empty] | William Ouimet | 10 | KABI LAKE FOREST PRODUCTS LTD7191KL-20210728-1Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD7191KL-20210728-1Supervisor3252OEWT-PA20-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7186 | KL-20210727-1 | 53511012 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2021-07-27 | 0 | OEWT-PA20-Lem | 2021-09-08 | 81 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavtor 1 loading rock truck, RT hauling material to excavator 2. Excavator 2 spreading material and working on road from F036 to F035 Access. | 10 | F009-F065 | Paint Lake Road | 0 | 2021-08-06 |  | 14 | 2021-08-08 | [5 empty] | William Ouimet | 10 | KABI LAKE FOREST PRODUCTS LTD7186KL-20210727-1Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD7186KL-20210727-1Supervisor3252OEWT-PA20-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7185 | KL-20210726-1 | 53511012 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2021-07-26 | 0 | OEWT-PA20-Lem | 2021-09-08 | 81 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavtor 1 working on F037 access / Excavator 2 working from F035 to 10660.01 WC | 10 | F009-F065 | Paint Lake Road | 0 | 2021-08-06 |  | 14 | 2021-08-08 | [5 empty] | William Ouimet | 10 | KABI LAKE FOREST PRODUCTS LTD7185KL-20210726-1Supervisor184 | KABI LAKE FOREST PRODUCTS LTD7185KL-20210726-1Supervisor184OEWT-PA20-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7198 | KL-20210803-3 | 53511012 | Access | 0 | L.O.A. | 244 | 0.090909 | DAY |  | 0 |  |  | 22.1818 | 2.8836 | 25.0654 | 2021-08-03 | 0 | OEWT-PA20-Lem | 2021-09-08 | 81 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Labourer & Operatortracking excavators from F-036 to 12km on Paint Lake Road 2 for float access. | 10 | F118-F127 | Paint Lake Road 2 | 0 | 2021-08-12 |  | 14 | 2021-08-13 | [5 empty] | William Ouimet | 10 | KABI LAKE FOREST PRODUCTS LTD7198KL-20210803-3L.O.A.0.090909122.1818 | KABI LAKE FOREST PRODUCTS LTD7198KL-20210803-3L.O.A.0.090909122.1818OEWT-PA20-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7198 | KL-20210803-3 | 53511012 | Access | 0 | L.O.A. | 244 | 0.090909 | DAY |  | 0 |  |  | 22.1818 | 2.8836 | 25.0654 | 2021-08-03 | 0 | OEWT-PA20-Lem | 2021-09-08 | 81 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Labourer & Operatortracking excavators from F-036 to 12km on Paint Lake Road 2 for float access. | 10 | F118-F127 | Paint Lake Road 2 | 0 | 2021-08-12 |  | 14 | 2021-08-13 | [5 empty] | William Ouimet | 10 | KABI LAKE FOREST PRODUCTS LTD7198KL-20210803-3L.O.A.0.090909122.1818 | KABI LAKE FOREST PRODUCTS LTD7198KL-20210803-3L.O.A.0.090909122.1818OEWT-PA20-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7192 | KL-20210729-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.68182 | DAY |  | 0 |  |  | 166.3636 | 21.6273 | 187.9909 | 2021-07-29 | 0 | OEWT-PA20-Lem | 2021-09-08 | 81 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working to F034 access, moving road @ F036 & moving log deck @ F037. | 10 | F009-F065 | Paint Lake Road | 0 | 2021-08-06 |  | 14 | 2021-08-08 | [5 empty] | William Ouimet | 10 | KABI LAKE FOREST PRODUCTS LTD7192KL-20210729-1L.O.A.0.6818182166.3636 | KABI LAKE FOREST PRODUCTS LTD7192KL-20210729-1L.O.A.0.6818182166.3636OEWT-PA20-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7191 | KL-20210728-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.90909 | DAY |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-07-28 | 0 | OEWT-PA20-Lem | 2021-09-08 | 81 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavtor 1 loading rock truck, RT hauling material to excavator 2. Excavator 2 spreading material and working on road from F036 to F034 Access. | 10 | F009-F065 | Paint Lake Road | 0 | 2021-08-06 |  | 14 | 2021-08-08 | [5 empty] | William Ouimet | 10 | KABI LAKE FOREST PRODUCTS LTD7191KL-20210728-1L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7191KL-20210728-1L.O.A.0.9090909221.8182OEWT-PA20-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7186 | KL-20210727-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.90909 | DAY |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-07-27 | 0 | OEWT-PA20-Lem | 2021-09-08 | 81 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavtor 1 loading rock truck, RT hauling material to excavator 2. Excavator 2 spreading material and working on road from F036 to F035 Access. | 10 | F009-F065 | Paint Lake Road | 0 | 2021-08-06 |  | 14 | 2021-08-08 | [5 empty] | William Ouimet | 10 | KABI LAKE FOREST PRODUCTS LTD7186KL-20210727-1L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7186KL-20210727-1L.O.A.0.9090909221.8182OEWT-PA20-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7185 | KL-20210726-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.90909 | DAY |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-07-26 | 0 | OEWT-PA20-Lem | 2021-09-08 | 81 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavtor 1 working on F037 access / Excavator 2 working from F035 to 10660.01 WC | 10 | F009-F065 | Paint Lake Road | 0 | 2021-08-06 |  | 14 | 2021-08-08 | [5 empty] | William Ouimet | 10 | KABI LAKE FOREST PRODUCTS LTD7185KL-20210726-1L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7185KL-20210726-1L.O.A.0.9090909221.8182OEWT-PA20-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7185 | KL-20210726-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.90909 | DAY |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-07-26 | 0 | OEWT-PA20-Lem | 2021-09-08 | 81 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavtor 1 working on F037 access / Excavator 2 working from F035 to 10660.01 WC | 10 | F009-F065 | Paint Lake Road | 0 | 2021-08-06 |  | 14 | 2021-08-08 | [5 empty] | William Ouimet | 10 | KABI LAKE FOREST PRODUCTS LTD7185KL-20210726-1L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7185KL-20210726-1L.O.A.0.9090909221.8182OEWT-PA20-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7198 | KL-20210803-3 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 2 | HR | 147 | 0 |  |  | 390 | 50.7 | 440.7 | 2021-08-03 | 0 | OEWT-PA20-Lem | 2021-09-08 | 81 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Labourer & Operatortracking excavators from F-036 to 12km on Paint Lake Road 2 for float access. | 10 | F118-F127 | Paint Lake Road 2 | 0 | 2021-08-12 |  | 14 | 2021-08-13 | [5 empty] | William Ouimet | 10 | KABI LAKE FOREST PRODUCTS LTD7198KL-20210803-330 Ton Excavator c/w Hydraulic Thumb2390 | KABI LAKE FOREST PRODUCTS LTD7198KL-20210803-330 Ton Excavator c/w Hydraulic Thumb2390OEWT-PA20-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7192 | KL-20210729-1 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 7.5 | HR | 147 | 0 |  |  | 1462.5 | 190.125 | 1652.625 | 2021-07-29 | 0 | OEWT-PA20-Lem | 2021-09-08 | 81 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working to F034 access, moving road @ F036 & moving log deck @ F037. | 10 | F009-F065 | Paint Lake Road | 0 | 2021-08-06 |  | 14 | 2021-08-08 | [5 empty] | William Ouimet | 10 | KABI LAKE FOREST PRODUCTS LTD7192KL-20210729-130 Ton Excavator c/w Hydraulic Thumb7.51462.5 | KABI LAKE FOREST PRODUCTS LTD7192KL-20210729-130 Ton Excavator c/w Hydraulic Thumb7.51462.5OEWT-PA20-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7191 | KL-20210728-1 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 10 | HR | 147 | 0 |  |  | 1950 | 253.5 | 2203.5 | 2021-07-28 | 0 | OEWT-PA20-Lem | 2021-09-08 | 81 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavtor 1 loading rock truck, RT hauling material to excavator 2. Excavator 2 spreading material and working on road from F036 to F034 Access. | 10 | F009-F065 | Paint Lake Road | 0 | 2021-08-06 |  | 14 | 2021-08-08 | [5 empty] | William Ouimet | 10 | KABI LAKE FOREST PRODUCTS LTD7191KL-20210728-130 Ton Excavator c/w Hydraulic Thumb101950 | KABI LAKE FOREST PRODUCTS LTD7191KL-20210728-130 Ton Excavator c/w Hydraulic Thumb101950OEWT-PA20-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7186 | KL-20210727-1 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 10 | HR | 147 | 0 |  |  | 1950 | 253.5 | 2203.5 | 2021-07-27 | 0 | OEWT-PA20-Lem | 2021-09-08 | 81 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavtor 1 loading rock truck, RT hauling material to excavator 2. Excavator 2 spreading material and working on road from F036 to F035 Access. | 10 | F009-F065 | Paint Lake Road | 0 | 2021-08-06 |  | 14 | 2021-08-08 | [5 empty] | William Ouimet | 10 | KABI LAKE FOREST PRODUCTS LTD7186KL-20210727-130 Ton Excavator c/w Hydraulic Thumb101950 | KABI LAKE FOREST PRODUCTS LTD7186KL-20210727-130 Ton Excavator c/w Hydraulic Thumb101950OEWT-PA20-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7185 | KL-20210726-1 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 10 | HR | 147 | 0 |  |  | 1950 | 253.5 | 2203.5 | 2021-07-26 | 0 | OEWT-PA20-Lem | 2021-09-08 | 81 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavtor 1 working on F037 access / Excavator 2 working from F035 to 10660.01 WC | 10 | F009-F065 | Paint Lake Road | 0 | 2021-08-06 |  | 14 | 2021-08-08 | [5 empty] | William Ouimet | 10 | KABI LAKE FOREST PRODUCTS LTD7185KL-20210726-130 Ton Excavator c/w Hydraulic Thumb101950 | KABI LAKE FOREST PRODUCTS LTD7185KL-20210726-130 Ton Excavator c/w Hydraulic Thumb101950OEWT-PA20-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7185 | KL-20210726-1 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 10 | HR | 147 | 0 |  |  | 1950 | 253.5 | 2203.5 | 2021-07-26 | 0 | OEWT-PA20-Lem | 2021-09-08 | 81 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavtor 1 working on F037 access / Excavator 2 working from F035 to 10660.01 WC | 10 | F009-F065 | Paint Lake Road | 0 | 2021-08-06 |  | 14 | 2021-08-08 | [5 empty] | William Ouimet | 10 | KABI LAKE FOREST PRODUCTS LTD7185KL-20210726-130 Ton Excavator c/w Hydraulic Thumb101950 | KABI LAKE FOREST PRODUCTS LTD7185KL-20210726-130 Ton Excavator c/w Hydraulic Thumb101950OEWT-PA20-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7198 | KL-20210803-3 | 53511012 | Access | 0 | Pickup Truck - Truck Only | 25 | 3.5 | HR | 19 | 0 |  |  | 87.5 | 11.375 | 98.875 | 2021-08-03 | 0 | OEWT-PA20-Lem | 2021-09-08 | 81 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Labourer & Operatortracking excavators from F-036 to 12km on Paint Lake Road 2 for float access. | 10 | F118-F127 | Paint Lake Road 2 | 0 | 2021-08-12 |  | 14 | 2021-08-13 | [5 empty] | William Ouimet | 10 | KABI LAKE FOREST PRODUCTS LTD7198KL-20210803-3Pickup Truck - Truck Only3.587.5 | KABI LAKE FOREST PRODUCTS LTD7198KL-20210803-3Pickup Truck - Truck Only3.587.5OEWT-PA20-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7192 | KL-20210729-1 | 53511012 | Access | 0 | Pickup Truck - Truck Only | 25 | 8 | HR | 19 | 0 |  |  | 200 | 26 | 226 | 2021-07-29 | 0 | OEWT-PA20-Lem | 2021-09-08 | 81 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working to F034 access, moving road @ F036 & moving log deck @ F037. | 10 | F009-F065 | Paint Lake Road | 0 | 2021-08-06 |  | 14 | 2021-08-08 | [5 empty] | William Ouimet | 10 | KABI LAKE FOREST PRODUCTS LTD7192KL-20210729-1Pickup Truck - Truck Only8200 | KABI LAKE FOREST PRODUCTS LTD7192KL-20210729-1Pickup Truck - Truck Only8200OEWT-PA20-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7191 | KL-20210728-1 | 53511012 | Access | 0 | Pickup Truck - Truck Only | 25 | 13 | HR | 19 | 0 |  |  | 325 | 42.25 | 367.25 | 2021-07-28 | 0 | OEWT-PA20-Lem | 2021-09-08 | 81 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavtor 1 loading rock truck, RT hauling material to excavator 2. Excavator 2 spreading material and working on road from F036 to F034 Access. | 10 | F009-F065 | Paint Lake Road | 0 | 2021-08-06 |  | 14 | 2021-08-08 | [5 empty] | William Ouimet | 10 | KABI LAKE FOREST PRODUCTS LTD7191KL-20210728-1Pickup Truck - Truck Only13325 | KABI LAKE FOREST PRODUCTS LTD7191KL-20210728-1Pickup Truck - Truck Only13325OEWT-PA20-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7186 | KL-20210727-1 | 53511012 | Access | 0 | Pickup Truck - Truck Only | 25 | 13 | HR | 19 | 0 |  |  | 325 | 42.25 | 367.25 | 2021-07-27 | 0 | OEWT-PA20-Lem | 2021-09-08 | 81 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavtor 1 loading rock truck, RT hauling material to excavator 2. Excavator 2 spreading material and working on road from F036 to F035 Access. | 10 | F009-F065 | Paint Lake Road | 0 | 2021-08-06 |  | 14 | 2021-08-08 | [5 empty] | William Ouimet | 10 | KABI LAKE FOREST PRODUCTS LTD7186KL-20210727-1Pickup Truck - Truck Only13325 | KABI LAKE FOREST PRODUCTS LTD7186KL-20210727-1Pickup Truck - Truck Only13325OEWT-PA20-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7185 | KL-20210726-1 | 53511012 | Access | 0 | Pickup Truck - Truck Only | 25 | 21 | HR | 19 | 0 |  |  | 525 | 68.25 | 593.25 | 2021-07-26 | 0 | OEWT-PA20-Lem | 2021-09-08 | 81 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavtor 1 working on F037 access / Excavator 2 working from F035 to 10660.01 WC | 10 | F009-F065 | Paint Lake Road | 0 | 2021-08-06 |  | 14 | 2021-08-08 | [5 empty] | William Ouimet | 10 | KABI LAKE FOREST PRODUCTS LTD7185KL-20210726-1Pickup Truck - Truck Only21525 | KABI LAKE FOREST PRODUCTS LTD7185KL-20210726-1Pickup Truck - Truck Only21525OEWT-PA20-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7389 | KL-20210925-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 4792.37 | Each |  |  |  |  | 4792.37 | 623.0081 | 5415.3781 | 2021-09-25 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 loading rock trucks with trees, excavator 2 finishing placing trees @Km 21 hill and working out to 16.5/Supervision of Morin and Skagen | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-29 |  | 50 | 2021-10-01 | SFF-20210925-1 | Excavator placing trees @ km 40.5 and shaping road/ grader starting sections of Paint Lake Road 2 to Km 5 - SFF-14381 |  |  |  | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7389KL-20210925-13rd Party Services4792.374792.37 | KABI LAKE FOREST PRODUCTS LTD7389KL-20210925-13rd Party Services4792.374792.37OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7374 | KL-20210922-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 6450.96 | Each |  |  |  |  | 6450.96 | 838.6248 | 7289.5848 | 2021-09-22 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator working on road maintenance @ 21 km hill/Chapman rock truck hauling trees from F104 to Morin @ km 43/Supervision of Morin and Skagen | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-28 |  | 61 | 2021-09-28 | MC-20210922-1 | Excavator 1 placing corduroy in low areas @ km 43 Hill and building road around a broken down drill/Excavator tracking from km 46 and loading trees/rock truck hauling trees from F104 to Km 43 hill - MC- 13159-1 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7374KL-20210922-13rd Party Services6450.966450.96 | KABI LAKE FOREST PRODUCTS LTD7374KL-20210922-13rd Party Services6450.966450.96OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7374 | KL-20210922-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2702.73 | Each |  |  |  |  | 2702.73 | 351.3549 | 3054.0849 | 2021-09-22 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator working on road maintenance @ 21 km hill/Chapman rock truck hauling trees from F104 to Morin @ km 43/Supervision of Morin and Skagen | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-28 |  | 61 | 2021-09-28 | SSF-20210922-1 | Excavator loading Chapman Rock Truck and Morin rock truck with trees for corduroy and Carrying trees from F104.5 to F104 for loading - SSF-14379 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7374KL-20210922-13rd Party Services2702.732702.73 | KABI LAKE FOREST PRODUCTS LTD7374KL-20210922-13rd Party Services2702.732702.73OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7370 | KL-20210921-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 968.73 | Each |  |  |  |  | 968.73 | 125.9349 | 1094.6649 | 2021-09-21 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator working on road maintenance @ 17 to 20 km/Chapman rock truck hauling trees from F104 to Morin @ km 43/Supervision of Morin and Skagen | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-28 |  | 50 | 2021-09-28 | MC-20210921-1 | Excavator 1 placing corduroy in low areas @ km 43 Hill/Excavator 2 working on ditching for drainage/rock truck driving in from Hwy and hauling trees from F104 to Km 43 hill - MC- 13158 |  |  |  | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7370KL-20210921-13rd Party Services968.73968.73 | KABI LAKE FOREST PRODUCTS LTD7370KL-20210921-13rd Party Services968.73968.73OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7365 | KL-20210920-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 1937.45 | Each |  |  |  |  | 1937.45 | 251.8685 | 2189.3185 | 2021-09-20 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator working on road maintenance @ 18 to21.5 km and Carrying trees for moving road@ 19.5km/Chapman rock truck hauling trees from F104 to Morin @ km 43 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-27 |  | 50 | 2021-09-27 | MC-20210920-1 | Road maintenance - MC-13157 |  |  |  | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7365KL-20210920-13rd Party Services1937.451937.45 | KABI LAKE FOREST PRODUCTS LTD7365KL-20210920-13rd Party Services1937.451937.45OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7361 | KL-20210919-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2179.64 | Each |  |  |  |  | 2179.64 | 283.3532 | 2462.9932 | 2021-09-19 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator working on road maintenance @ 18 to21 km and pulling pickups @ end of shift /Chapman rock truck hauling trees from F104 to Morin @ km 41 and 42. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-27 |  | 50 | 2021-09-27 | MC-20210919-1 | Excavator 1 placing corduroy in low areas @ km 41 and 42/Excavator 2 working on road maintenance @ km 44/46 - MC- 13156 |  |  |  | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7361KL-20210919-13rd Party Services2179.642179.64 | KABI LAKE FOREST PRODUCTS LTD7361KL-20210919-13rd Party Services2179.642179.64OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7355 | KL-20210918-1-R1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2421.82 | Each |  |  |  |  | 2421.82 | 314.8366 | 2736.6566 | 2021-09-18 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator working on road maintenance @ 18 to21 km /Chapman rock truck hauling access mats and hauling out broken mats for Morin @ Km 44 to 46 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-24 |  | 50 | 2021-09-27 | MC-20210918-1 | Excavator leveling ruts, working on drainage and shaping road, fixing access mats and cleaning up broken mats from km 44 to 46 - MC- 13155 |  |  |  | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7355KL-20210918-1-R13rd Party Services2421.822421.82 | KABI LAKE FOREST PRODUCTS LTD7355KL-20210918-1-R13rd Party Services2421.822421.82OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7355 | KL-20210918-1-R1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2573.64 | Each |  |  |  |  | 2573.64 | 334.5732 | 2908.2132 | 2021-09-18 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator working on road maintenance @ 18 to21 km /Chapman rock truck hauling access mats and hauling out broken mats for Morin @ Km 44 to 46 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-24 |  | 50 | 2021-09-27 | SSF-20210918-1 | Excavator working on drainage and shaping road from km 39 to 42.5 - SSF-14375 |  |  |  | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7355KL-20210918-1-R13rd Party Services2573.642573.64 | KABI LAKE FOREST PRODUCTS LTD7355KL-20210918-1-R13rd Party Services2573.642573.64OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7326 | KL-20210908-2 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2323.64 | Each |  |  |  |  | 2323.64 | 302.0732 | 2625.7132 | 2021-09-08 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator continuing sloping and shaping excavation @ 49 km/ operator Called out to operate Valard rock breaker / Supervision of Morin Contracting and Skagen and Sons | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-15 |  | 50 | 2021-09-23 | MC-20210908-1 | Excavator Continuing road repairs with access mats and working on drainage @ km 44 to 42 Km - MC-13145 |  |  |  | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7326KL-20210908-23rd Party Services2323.642323.64 | KABI LAKE FOREST PRODUCTS LTD7326KL-20210908-23rd Party Services2323.642323.64OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7326 | KL-20210908-2 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2323.64 | Each |  |  |  |  | 2323.64 | 302.0732 | 2625.7132 | 2021-09-08 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator continuing sloping and shaping excavation @ 49 km/ operator Called out to operate Valard rock breaker / Supervision of Morin Contracting and Skagen and Sons | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-15 |  | 50 | 2021-09-23 | SSF-20210908-1 | Excavator Continuing Shaping road and fixing access mats from 36 to 38 km - SSF-14364 |  |  |  | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7326KL-20210908-23rd Party Services2323.642323.64 | KABI LAKE FOREST PRODUCTS LTD7326KL-20210908-23rd Party Services2323.642323.64OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7325 | KL-20210907-2 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2323.64 | Each |  |  |  |  | 2323.64 | 302.0732 | 2625.7132 | 2021-09-07 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator continuing sloping and shaping excavation @ 49 km/ Supervision of Morin Contracting and Skagen and Sons Shaping road and fixing access mats from 36 to 33 km and @ km 40.5 to 43.5 Km | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-15 |  | 50 | 2021-09-23 | MC-20210908-1 | Excavator Continuing road repairs with access mats and working on drainage @ km 40.5 to 43.5 Km - MC-13144 |  |  |  | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7325KL-20210907-23rd Party Services2323.642323.64 | KABI LAKE FOREST PRODUCTS LTD7325KL-20210907-23rd Party Services2323.642323.64OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7325 | KL-20210907-2 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2581.82 | Each |  |  |  |  | 2581.82 | 335.6366 | 2917.4566 | 2021-09-07 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator continuing sloping and shaping excavation @ 49 km/ Supervision of Morin Contracting and Skagen and Sons Shaping road and fixing access mats from 36 to 33 km and @ km 40.5 to 43.5 Km | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-15 |  | 50 | 2021-09-23 | SSF-20210907-1 | Excavator Continuing Shaping road and fixing access mats from 36 to 33 km - SSF-14363 |  |  |  | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7325KL-20210907-23rd Party Services2581.822581.82 | KABI LAKE FOREST PRODUCTS LTD7325KL-20210907-23rd Party Services2581.822581.82OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7316 | KL-20210906-2 | 53511012 | Access | 0 | 3rd Party Services | 1 | 1161.82 | Each |  |  |  |  | 1161.82 | 151.0366 | 1312.8566 | 2021-09-06 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator Continuing road repairs with access mats and working on drainage @ km 40 to 43 Km - MC-13143. Shaping road and fixing access mats from 38 to 36 km - SSF-14362 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-10 |  | 50 | 2021-09-11 | MC-20210906-1 | Excavator Continuing road repairs with access mats and working on drainage @ km 40 to 43 Km - MC-13143 |  |  |  | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7316KL-20210906-23rd Party Services1161.821161.82 | KABI LAKE FOREST PRODUCTS LTD7316KL-20210906-23rd Party Services1161.821161.82OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7316 | KL-20210906-2 | 53511012 | Access | 0 | 3rd Party Services | 1 | 1807.27 | Each |  |  |  |  | 1807.27 | 234.9451 | 2042.2151 | 2021-09-06 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator Continuing road repairs with access mats and working on drainage @ km 40 to 43 Km - MC-13143. Shaping road and fixing access mats from 38 to 36 km - SSF-14362 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-10 |  | 50 | 2021-09-11 | SSF-20210906-1 | Excavator Continuing Shaping road and fixing access mats from 38 to 36 km - SSF-14362 |  |  |  | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7316KL-20210906-23rd Party Services1807.271807.27 | KABI LAKE FOREST PRODUCTS LTD7316KL-20210906-23rd Party Services1807.271807.27OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7315 | KL-20210905-2 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2323.64 | Each |  |  |  |  | 2323.64 | 302.0732 | 2625.7132 | 2021-09-05 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator doing road repairs with access mats and working on drainage @ km 40 to 43 Km - MC-13142. Shaping road and fixing access mats from 43 to 48 km - SSF-14361 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-10 |  | 50 | 2021-09-11 | MC-20210905-1 | Excavator doing road repairs with access mats and working on drainage @ km 40 to 43 Km - MC-13142 |  |  |  | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7315KL-20210905-23rd Party Services2323.642323.64 | KABI LAKE FOREST PRODUCTS LTD7315KL-20210905-23rd Party Services2323.642323.64OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7315 | KL-20210905-2 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2581.82 | Each |  |  |  |  | 2581.82 | 335.6366 | 2917.4566 | 2021-09-05 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator doing road repairs with access mats and working on drainage @ km 40 to 43 Km - MC-13142. Shaping road and fixing access mats from 43 to 48 km - SSF-14361 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-10 |  | 50 | 2021-09-11 | SSF-20210905-1 | Excavator Continuing Shaping road and fixing access mats from 43 to 48 km - SSF-14361 |  |  |  | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7315KL-20210905-23rd Party Services2581.822581.82 | KABI LAKE FOREST PRODUCTS LTD7315KL-20210905-23rd Party Services2581.822581.82OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7313 | KL-20210904-2 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2323.64 | Each |  |  |  |  | 2323.64 | 302.0732 | 2625.7132 | 2021-09-04 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator doing road repairs with access mats and working on drainage @ km 40.5 to 43 Km - MC-13141. Shaping road and fixing access mats from 45 to 47 km - SSF-14360 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-10 |  | 50 | 2021-09-11 | MC-20210904-1 | Excavator doing road repairs with access mats and working on drainage @ km 40.5 to 43 Km - MC-13141 |  |  |  | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7313KL-20210904-23rd Party Services2323.642323.64 | KABI LAKE FOREST PRODUCTS LTD7313KL-20210904-23rd Party Services2323.642323.64OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7313 | KL-20210904-2 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2581.82 | Each |  |  |  |  | 2581.82 | 335.6366 | 2917.4566 | 2021-09-04 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator doing road repairs with access mats and working on drainage @ km 40.5 to 43 Km - MC-13141. Shaping road and fixing access mats from 45 to 47 km - SSF-14360 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-10 |  | 50 | 2021-09-11 | SSF-20210904-1 | Excavator Continuing Shaping road and fixing access mats from 45 to 47 km - SSF-14360 |  |  |  | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7313KL-20210904-23rd Party Services2581.822581.82 | KABI LAKE FOREST PRODUCTS LTD7313KL-20210904-23rd Party Services2581.822581.82OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7312 | KL-20210903-2 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2581.82 | Each |  |  |  |  | 2581.82 | 335.6366 | 2917.4566 | 2021-09-03 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul gravel from 38.5 km Morin excavator @ km 40/41 for road capping | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-10 |  | 50 | 2021-09-11 | SSF-20210903-1 | Excavator Continuing Shaping road and fixing access mats from 43 to 45 km - SSF-14359 |  |  |  | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7312KL-20210903-23rd Party Services2581.822581.82 | KABI LAKE FOREST PRODUCTS LTD7312KL-20210903-23rd Party Services2581.822581.82OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7311 | KL-20210902-2 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2581.82 | Each |  |  |  |  | 2581.82 | 335.6366 | 2917.4566 | 2021-09-02 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul gravel from 38.5 km Morin excavator @ km 40/41 for road capping | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-10 |  | 37 | 2021-09-18 | SSF-20210902-1 | Excavator Shaping road and fixing access mats from 43 to 45 km - SSF-14358 |  |  |  | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7311KL-20210902-23rd Party Services2581.822581.82 | KABI LAKE FOREST PRODUCTS LTD7311KL-20210902-23rd Party Services2581.822581.82OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7307 | KL-20210901-2 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2323.64 | Each |  |  |  |  | 2323.64 | 302.0732 | 2625.7132 | 2021-09-01 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul material from @ km49 to Skagen excavator @ km 43/ 2 Kabi , 1 Chapman and 3 Cobiere rock trucks/ excavator 2 preping access @km 35 to 34 for gravel Haul. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-10 |  | 37 | 2021-09-18 | MC-20210901-1 | Excavator continuing leveling ruts, working on drainage and shaping road sections @ km 40/42 for gravel haul - MC-13138 |  |  |  | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7307KL-20210901-23rd Party Services2323.642323.64 | KABI LAKE FOREST PRODUCTS LTD7307KL-20210901-23rd Party Services2323.642323.64OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7307 | KL-20210901-2 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2581.82 | Each |  |  |  |  | 2581.82 | 335.6366 | 2917.4566 | 2021-09-01 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul material from @ km49 to Skagen excavator @ km 43/ 2 Kabi , 1 Chapman and 3 Cobiere rock trucks/ excavator 2 preping access @km 35 to 34 for gravel Haul. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-10 |  | 37 | 2021-09-18 | SSF-20210901-1 | Excavator Shaping road and spreading Gravel, @ km 44/43 - SSF-14357 |  |  |  | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7307KL-20210901-23rd Party Services2581.822581.82 | KABI LAKE FOREST PRODUCTS LTD7307KL-20210901-23rd Party Services2581.822581.82OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7292 | KL-20210831-2 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2323.64 | Each |  |  |  |  | 2323.64 | 302.0732 | 2625.7132 | 2021-08-31 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul existing material from 49 Km to 44/43Km. 1 Kabi rock truck, 2 Corbiere Rock Trucks & 1 Chapman Rock Truck. Excavator 2 tracking from 49Km to F-086 for gravel haul. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-03 |  | 37 | 2021-09-06 | MC-20210831-1 | Excavator leveling ruts, working on drainage & shaping road sections @ 40/42km. MC-13137 |  |  |  | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7292KL-20210831-23rd Party Services2323.642323.64 | KABI LAKE FOREST PRODUCTS LTD7292KL-20210831-23rd Party Services2323.642323.64OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7292 | KL-20210831-2 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2581.82 | Each |  |  |  |  | 2581.82 | 335.6366 | 2917.4566 | 2021-08-31 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul existing material from 49 Km to 44/43Km. 1 Kabi rock truck, 2 Corbiere Rock Trucks & 1 Chapman Rock Truck. Excavator 2 tracking from 49Km to F-086 for gravel haul. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-03 |  | 37 | 2021-09-06 | SSF-20210831-1 | Excavator spreading gravel, placing corduroy & shaping road from 44km to 43km |  |  |  | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7292KL-20210831-23rd Party Services2581.822581.82 | KABI LAKE FOREST PRODUCTS LTD7292KL-20210831-23rd Party Services2581.822581.82OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7288 | KL-20210830-2 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2581.82 | Each |  |  |  |  | 2581.82 | 335.6366 | 2917.4566 | 2021-08-30 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul existing material for excavation clean up @ km49 - 1 Kabi , 1 Valard and 1 Cobiere rock trucks/ excavator 2 shaping and leveling slopes | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-08-31 |  | 37 | 2021-09-05 | SSF-20210830-1 | Load and haul existing material for excavation clean up @ km49 - 1 Kabi , 1 Valard and 1 Cobiere rock trucks/ excavator 2 shaping and leveling slopes |  |  |  | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7288KL-20210830-23rd Party Services2581.822581.82 | KABI LAKE FOREST PRODUCTS LTD7288KL-20210830-23rd Party Services2581.822581.82OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7287 | KL-20210829-2 | 53511012 | Access | 0 | 3rd Party Services | 1 | 774.55 | Each |  |  |  |  | 774.55 | 100.6915 | 875.2415 | 2021-08-29 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul existing material for excavation clean up @ km49 - 1 Kabi , 1 Valard and 1 Cobiere rock trucks | 10 | F033-F118 | 600 Road | 0 | 2021-08-31 |  | 37 | 2021-09-05 | MC-20210829-1 | Excavator leveling ruts, working on drainage and shaping road sections @ 40/42 - MC-13136 |  |  |  | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7287KL-20210829-23rd Party Services774.55774.55 | KABI LAKE FOREST PRODUCTS LTD7287KL-20210829-23rd Party Services774.55774.55OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7285 | KL-20210828-3 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2452.73 | Each |  |  |  |  | 2452.73 | 318.8549 | 2771.5849 | 2021-08-28 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul gravel from km49 to Skagen excavator @ 46/45 km - 1 Kabi , 1 Chapman and 2 Cobiere rock trucks | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-09-05 | MC-20210828-1 | Excavator leveling ruts and shaping road sections @ km 41/43- Pulls pick ups as required - MC-13135 |  |  |  | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7285KL-20210828-33rd Party Services2452.732452.73 | KABI LAKE FOREST PRODUCTS LTD7285KL-20210828-33rd Party Services2452.732452.73OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7285 | KL-20210828-3 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2581.82 | Each |  |  |  |  | 2581.82 | 335.6366 | 2917.4566 | 2021-08-28 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul gravel from km49 to Skagen excavator @ 46/45 km - 1 Kabi , 1 Chapman and 2 Cobiere rock trucks | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-09-05 | SSF-20210828-2 | Track to km 46 and spread gravel in soft sections to km 45 - SSF-14354 |  |  |  | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7285KL-20210828-33rd Party Services2581.822581.82 | KABI LAKE FOREST PRODUCTS LTD7285KL-20210828-33rd Party Services2581.822581.82OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7283 | KL-20210827-3 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2452.73 | Each |  |  |  |  | 2452.73 | 318.8549 | 2771.5849 | 2021-08-27 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator starting sloping and cleaning up excavation @ km 49/rock truck hauling existing material from Km 39 to Morin Excavator/ Excavator 2 start sloping Km 49 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-09-05 | MC-20210827-1 | Excavator continuing spreading existing material and lay corduroy on road sections @ km 41/42 - MC-13134 |  |  |  | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7283KL-20210827-33rd Party Services2452.732452.73 | KABI LAKE FOREST PRODUCTS LTD7283KL-20210827-33rd Party Services2452.732452.73OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7283 | KL-20210827-3 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2581.82 | Each |  |  |  |  | 2581.82 | 335.6366 | 2917.4566 | 2021-08-27 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator starting sloping and cleaning up excavation @ km 49/rock truck hauling existing material from Km 39 to Morin Excavator/ Excavator 2 start sloping Km 49 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-09-05 | SSF-20210827-2 | Excavator doing road repairs and replacing access mats @ 44/46 km - SSF- 14352 |  |  |  | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7283KL-20210827-33rd Party Services2581.822581.82 | KABI LAKE FOREST PRODUCTS LTD7283KL-20210827-33rd Party Services2581.822581.82OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7281 | KL-20210826-3 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2581.82 | Each |  |  |  |  | 2581.82 | 335.6366 | 2917.4566 | 2021-08-26 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 Continuing sloping & cleaning up Excavation @ 49Km. Rock Truck hauling existing material from 39Km to Morin Excavator. Excavator 2 fixing access from 44Km to 47Km. | 10 | F033-F118 | Paint lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-09-05 | MC-20210826-1 | Excavator continuing spreading existing material and lay corduroy on road sections @ km 41/42 - MC-13133 |  |  |  | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7281KL-20210826-33rd Party Services2581.822581.82 | KABI LAKE FOREST PRODUCTS LTD7281KL-20210826-33rd Party Services2581.822581.82OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7281 | KL-20210826-3 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2581.82 | Each |  |  |  |  | 2581.82 | 335.6366 | 2917.4566 | 2021-08-26 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 Continuing sloping & cleaning up Excavation @ 49Km. Rock Truck hauling existing material from 39Km to Morin Excavator. Excavator 2 fixing access from 44Km to 47Km. | 10 | F033-F118 | Paint lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-09-05 | SSF-20210826-2 | Excavator cleaning up gravel haul excavations @ 42/43 km and shaping road @ 43 to 45 km - SSF- 14350 |  |  |  | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7281KL-20210826-33rd Party Services2581.822581.82 | KABI LAKE FOREST PRODUCTS LTD7281KL-20210826-33rd Party Services2581.822581.82OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7353 | KL-20210917-1-R1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2194.55 | Each |  |  |  |  | 2194.55 | 285.2915 | 2479.8415 | 2021-09-17 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator working on road maintenance @ 18 to20 km /Chapman rock truck hauling access mats from .5 on hensen to km 43/ Kabi rock trucks driving out for float | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-24 |  | 50 | 2021-09-27 | MC-20210917-1 | Excavator leveling ruts, working on drainage and shaping road from km 43 to 40.5 - MC- 13154 |  |  |  | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7353KL-20210917-1-R13rd Party Services2194.552194.55 | KABI LAKE FOREST PRODUCTS LTD7353KL-20210917-1-R13rd Party Services2194.552194.55OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7353 | KL-20210917-1-R1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2702.73 | Each |  |  |  |  | 2702.73 | 351.3549 | 3054.0849 | 2021-09-17 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator working on road maintenance @ 18 to20 km /Chapman rock truck hauling access mats from .5 on hensen to km 43/ Kabi rock trucks driving out for float | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-24 |  | 50 | 2021-09-27 | SSF-20210917-1 | Excavator working on drainage and shaping road from km 38 to 40.5 - SSF-14374 |  |  |  | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7353KL-20210917-1-R13rd Party Services2702.732702.73 | KABI LAKE FOREST PRODUCTS LTD7353KL-20210917-1-R13rd Party Services2702.732702.73OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7350 | KL-20210916-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 4752.45 | Each |  |  |  |  | 4752.45 | 617.8185 | 5370.2685 | 2021-09-16 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  | Approved by Mark McLeod |  | Approved |  |  | Excavator loading and hauling from 18 to19.5 km /Chapman rock truck and Kabi 30 ton rock truck hauling from 38 to 42/43 km with Skagen and Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-24 |  |  | 2021-09-25 | MC-20210916-1 | Excavator spreading gravel @ km 42 and doing road work / leveling ruts after hours for pickup access/ Excavator 2 leveling ruts and shaping access mats from km 46 to 44 - MC- 13153 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7350KL-20210916-13rd Party Services4752.454752.45 | KABI LAKE FOREST PRODUCTS LTD7350KL-20210916-13rd Party Services4752.454752.45OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7347 | KL-20210915-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 4519.27 | Each |  |  |  |  | 4519.27 | 587.5051 | 5106.7751 | 2021-09-15 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  | Approved by Mark McLeod |  | Approved |  |  | Excavator working from 18 to 19.5 km leveling ruts and shaping road for pick up access /Chapman rock truck and Kabi 30 ton rock truck on site to haul with Skagen and Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-15 |  |  | 2021-09-25 | MC-20210915-1 | Excavator 1 working from km 43 to km 44 doing road repairs and replacing access mats/ Excavator 2 leveling ruts and shaping road from km 49 to 46 - MC- 13152 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7347KL-20210915-13rd Party Services4519.274519.27 | KABI LAKE FOREST PRODUCTS LTD7347KL-20210915-13rd Party Services4519.274519.27OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7347 | KL-20210915-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2186.36 | Each |  |  |  |  | 2186.36 | 284.2268 | 2470.5868 | 2021-09-15 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  | Approved by Mark McLeod |  | Approved |  |  | Excavator working from 18 to 19.5 km leveling ruts and shaping road for pick up access /Chapman rock truck and Kabi 30 ton rock truck on site to haul with Skagen and Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-15 |  |  | 2021-09-25 | SSF-20210915-1 | Excavator working on road maintenance from Km 40.5 to 43 - SSF-14371 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7347KL-20210915-13rd Party Services2186.362186.36 | KABI LAKE FOREST PRODUCTS LTD7347KL-20210915-13rd Party Services2186.362186.36OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7336 | KL-20210914-2 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2815 | Each |  |  |  |  | 2815 | 365.95 | 3180.95 | 2021-09-14 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  | Mark McLeod Approved |  | Approved |  |  | Kabi loading and hauling from km 17 to km 18.5/Chapman rock truck and Kabi 30 ton rock truck hauling from km 38 to km 40.5 with Skagen and Morin | 10 | F033-F118 | Paint lake Road 2 | 0 | 2021-09-21 |  |  | 2021-09-22 | MC-20210914-1 | Excavator Continuing road repairs and spreading gravel @ km 40.5 to 43.5 Km/ doing road repairs after hours for pickup access - MC-13151 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7336KL-20210914-23rd Party Services28152815 | KABI LAKE FOREST PRODUCTS LTD7336KL-20210914-23rd Party Services28152815OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7336 | KL-20210914-2 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2603.64 | Each |  |  |  |  | 2603.64 | 338.4732 | 2942.1132 | 2021-09-14 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  | Mark McLeod Approved |  | Approved |  |  | Kabi loading and hauling from km 17 to km 18.5/Chapman rock truck and Kabi 30 ton rock truck hauling from km 38 to km 40.5 with Skagen and Morin | 10 | F033-F118 | Paint lake Road 2 | 0 | 2021-09-21 |  |  | 2021-09-22 | SSF-20210914-1 | Excavator loading Existing material and cleaning up excavation @ km 38 /working on road maintenance from Km 38 to 40.5 - SSF-14370 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7336KL-20210914-23rd Party Services2603.642603.64 | KABI LAKE FOREST PRODUCTS LTD7336KL-20210914-23rd Party Services2603.642603.64OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7335 | KL-20210913-2 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2815 | Each |  |  |  |  | 2815 | 365.95 | 3180.95 | 2021-09-13 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  | Mark McLeod Approved |  | Approved |  |  | Kabi loading and hauling from km 17 to km 18.5/Chapman rock truck and Kabi 30 ton rock truck hauling from km 38 to km 40.5 with Skagen and Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-21 |  |  | 2021-09-22 | MC-20210913-1 | Excavator Continuing road repairs and spreading gravel @ km 43 to 40.5 Km/ doing road repairs after hours for pickup access - MC-13150 |  |  |  |  | 10 | KABI LAKE FOREST PRODUCTS LTD7335KL-20210913-23rd Party Services28152815 | KABI LAKE FOREST PRODUCTS LTD7335KL-20210913-23rd Party Services28152815OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7334 | KL-20210912-2 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2581.82 | Each |  |  |  |  | 2581.82 | 335.6366 | 2917.4566 | 2021-09-12 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi loading and hauling from km 17 to km 19/Chapman rock truck and Kabi 30 ton rock truck hauling from km 38 to km 40 with Skagen and Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-21 |  | 50 | 2021-09-23 | MC-20210912-1 | Excavator Continuing road repairs and spreading Gravel @ km 40.5 to 42.5 Km - MC-13149 |  |  |  | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7334KL-20210912-23rd Party Services2581.822581.82 | KABI LAKE FOREST PRODUCTS LTD7334KL-20210912-23rd Party Services2581.822581.82OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7334 | KL-20210912-2 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2581.82 | Each |  |  |  |  | 2581.82 | 335.6366 | 2917.4566 | 2021-09-12 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi loading and hauling from km 17 to km 19/Chapman rock truck and Kabi 30 ton rock truck hauling from km 38 to km 40 with Skagen and Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-21 |  | 50 | 2021-09-23 | SSF-20210912-1 | Excavator Continue loading Gravel @ km 38 /leveling ruts for pick up access from Km 38 to Km 40 - SSF-14368 |  |  |  | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7334KL-20210912-23rd Party Services2581.822581.82 | KABI LAKE FOREST PRODUCTS LTD7334KL-20210912-23rd Party Services2581.822581.82OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7332 | KL-20210911-2 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2581.82 | Each |  |  |  |  | 2581.82 | 335.6366 | 2917.4566 | 2021-09-11 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi loading and hauling from km 17 to km 18.5/Chapman rock truck hauling from km 38 to km 40 with Skagen and Morin/Kabi rock truck driving from km .5 on Hensen to km 38 for gravel haul | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-21 |  | 50 | 2021-09-23 | MC-20210911-1 | Excavator Continuing road repairs for pick up access due to rain @ km 43 to 40 Km - MC-13148 |  |  |  | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7332KL-20210911-23rd Party Services2581.822581.82 | KABI LAKE FOREST PRODUCTS LTD7332KL-20210911-23rd Party Services2581.822581.82OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7332 | KL-20210911-2 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2581.82 | Each |  |  |  |  | 2581.82 | 335.6366 | 2917.4566 | 2021-09-11 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi loading and hauling from km 17 to km 18.5/Chapman rock truck hauling from km 38 to km 40 with Skagen and Morin/Kabi rock truck driving from km .5 on Hensen to km 38 for gravel haul | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-21 |  | 50 | 2021-09-23 | SSF-20210911-1 | Excavator Continue loading Gravel @ km 38 /leveling ruts for pick up access from Km 38 to Km 40 - SSF-14367 |  |  |  | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7332KL-20210911-23rd Party Services2581.822581.82 | KABI LAKE FOREST PRODUCTS LTD7332KL-20210911-23rd Party Services2581.822581.82OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7330 | KL-20210910-2 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2581.82 | Each |  |  |  |  | 2581.82 | 335.6366 | 2917.4566 | 2021-09-10 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator leveling ruts and tracking from Km 12 and Km 5 to Km 19 / 1 rock truck hauling from 38 km to Morin Excavator @ 40/42 km/rock truck 2 driving from Hwy to Km 38 and haul gravel | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-15 |  | 50 | 2021-09-23 | MC-20210910-1 | Excavator Continuing road repairs and spreading gravel @ km 43 to 40 Km - MC-13147 |  |  |  | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7330KL-20210910-23rd Party Services2581.822581.82 | KABI LAKE FOREST PRODUCTS LTD7330KL-20210910-23rd Party Services2581.822581.82OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7330 | KL-20210910-2 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2452.73 | Each |  |  |  |  | 2452.73 | 318.8549 | 2771.5849 | 2021-09-10 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator leveling ruts and tracking from Km 12 and Km 5 to Km 19 / 1 rock truck hauling from 38 km to Morin Excavator @ 40/42 km/rock truck 2 driving from Hwy to Km 38 and haul gravel | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-15 |  | 50 | 2021-09-23 | SSF-20210910-1 | Excavator Continue loading Gravel @ km 38 /leveling ruts for pick up access- SSF-14366 |  |  |  | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7330KL-20210910-23rd Party Services2452.732452.73 | KABI LAKE FOREST PRODUCTS LTD7330KL-20210910-23rd Party Services2452.732452.73OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7326 | KL-20210908-2 | 53511012 | Access | 0 | Operator | 80 | 4 | HR |  |  | 80 | 0 | 320 | 41.6 | 361.6 | 2021-09-08 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator continuing sloping and shaping excavation @ 49 km/ operator Called out to operate Valard rock breaker / Supervision of Morin Contracting and Skagen and Sons | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-15 |  | 50 | 2021-09-23 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7326KL-20210908-2Operator4320 | KABI LAKE FOREST PRODUCTS LTD7326KL-20210908-2Operator4320OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7374 | KL-20210922-1 | 53511012 | Access | 0 | Supervisor | 84 | 10 | HR |  |  | 84 | 0 | 840 | 109.2 | 949.2 | 2021-09-22 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator working on road maintenance @ 21 km hill/Chapman rock truck hauling trees from F104 to Morin @ km 43/Supervision of Morin and Skagen | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-28 |  | 61 | 2021-09-28 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7374KL-20210922-1Supervisor10840 | KABI LAKE FOREST PRODUCTS LTD7374KL-20210922-1Supervisor10840OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7370 | KL-20210921-1 | 53511012 | Access | 0 | Supervisor | 84 | 8 | HR |  |  | 84 | 0 | 672 | 87.36 | 759.36 | 2021-09-21 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator working on road maintenance @ 17 to 20 km/Chapman rock truck hauling trees from F104 to Morin @ km 43/Supervision of Morin and Skagen | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-28 |  | 50 | 2021-09-28 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7370KL-20210921-1Supervisor8672 | KABI LAKE FOREST PRODUCTS LTD7370KL-20210921-1Supervisor8672OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7365 | KL-20210920-1 | 53511012 | Access | 0 | Supervisor | 84 | 8 | HR |  |  | 84 | 0 | 672 | 87.36 | 759.36 | 2021-09-20 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator working on road maintenance @ 18 to21.5 km and Carrying trees for moving road@ 19.5km/Chapman rock truck hauling trees from F104 to Morin @ km 43 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-27 |  | 50 | 2021-09-27 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7365KL-20210920-1Supervisor8672 | KABI LAKE FOREST PRODUCTS LTD7365KL-20210920-1Supervisor8672OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7361 | KL-20210919-1 | 53511012 | Access | 0 | Supervisor | 84 | 7 | HR |  |  | 84 | 0 | 588 | 76.44 | 664.44 | 2021-09-19 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator working on road maintenance @ 18 to21 km and pulling pickups @ end of shift /Chapman rock truck hauling trees from F104 to Morin @ km 41 and 42. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-27 |  | 50 | 2021-09-27 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7361KL-20210919-1Supervisor7588 | KABI LAKE FOREST PRODUCTS LTD7361KL-20210919-1Supervisor7588OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7355 | KL-20210918-1-R1 | 53511012 | Access | 0 | Supervisor | 84 | 7 | HR |  |  | 84 | 0 | 588 | 76.44 | 664.44 | 2021-09-18 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator working on road maintenance @ 18 to21 km /Chapman rock truck hauling access mats and hauling out broken mats for Morin @ Km 44 to 46 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-24 |  | 50 | 2021-09-27 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7355KL-20210918-1-R1Supervisor7588 | KABI LAKE FOREST PRODUCTS LTD7355KL-20210918-1-R1Supervisor7588OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7353 | KL-20210917-1-R1 | 53511012 | Access | 0 | Supervisor | 84 | 7 | HR |  |  | 84 | 0 | 588 | 76.44 | 664.44 | 2021-09-17 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator working on road maintenance @ 18 to20 km /Chapman rock truck hauling access mats from .5 on hensen to km 43/ Kabi rock trucks driving out for float | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-24 |  | 50 | 2021-09-27 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7353KL-20210917-1-R1Supervisor7588 | KABI LAKE FOREST PRODUCTS LTD7353KL-20210917-1-R1Supervisor7588OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7350 | KL-20210916-1 | 53511012 | Access | 0 | Supervisor | 84 | 8 | HR |  |  | 84 | 0 | 672 | 87.36 | 759.36 | 2021-09-16 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  | Approved by Mark McLeod |  | Approved |  |  | Excavator loading and hauling from 18 to19.5 km /Chapman rock truck and Kabi 30 ton rock truck hauling from 38 to 42/43 km with Skagen and Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-24 |  |  | 2021-09-25 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7350KL-20210916-1Supervisor8672 | KABI LAKE FOREST PRODUCTS LTD7350KL-20210916-1Supervisor8672OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7347 | KL-20210915-1 | 53511012 | Access | 0 | Supervisor | 84 | 8 | HR |  |  | 84 | 0 | 672 | 87.36 | 759.36 | 2021-09-15 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  | Approved by Mark McLeod |  | Approved |  |  | Excavator working from 18 to 19.5 km leveling ruts and shaping road for pick up access /Chapman rock truck and Kabi 30 ton rock truck on site to haul with Skagen and Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-15 |  |  | 2021-09-25 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7347KL-20210915-1Supervisor8672 | KABI LAKE FOREST PRODUCTS LTD7347KL-20210915-1Supervisor8672OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7336 | KL-20210914-2 | 53511012 | Access | 0 | Supervisor | 84 | 8 | HR |  |  | 84 | 0 | 672 | 87.36 | 759.36 | 2021-09-14 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  | Mark McLeod Approved |  | Approved |  |  | Kabi loading and hauling from km 17 to km 18.5/Chapman rock truck and Kabi 30 ton rock truck hauling from km 38 to km 40.5 with Skagen and Morin | 10 | F033-F118 | Paint lake Road 2 | 0 | 2021-09-21 |  |  | 2021-09-22 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7336KL-20210914-2Supervisor8672 | KABI LAKE FOREST PRODUCTS LTD7336KL-20210914-2Supervisor8672OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7335 | KL-20210913-2 | 53511012 | Access | 0 | Supervisor | 84 | 10 | HR |  |  | 84 | 0 | 840 | 109.2 | 949.2 | 2021-09-13 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  | Mark McLeod Approved |  | Approved |  |  | Kabi loading and hauling from km 17 to km 18.5/Chapman rock truck and Kabi 30 ton rock truck hauling from km 38 to km 40.5 with Skagen and Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-21 |  |  | 2021-09-22 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7335KL-20210913-2Supervisor10840 | KABI LAKE FOREST PRODUCTS LTD7335KL-20210913-2Supervisor10840OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7334 | KL-20210912-2 | 53511012 | Access | 0 | Supervisor | 84 | 10 | HR |  |  | 84 | 0 | 840 | 109.2 | 949.2 | 2021-09-12 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi loading and hauling from km 17 to km 19/Chapman rock truck and Kabi 30 ton rock truck hauling from km 38 to km 40 with Skagen and Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-21 |  | 50 | 2021-09-23 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7334KL-20210912-2Supervisor10840 | KABI LAKE FOREST PRODUCTS LTD7334KL-20210912-2Supervisor10840OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7332 | KL-20210911-2 | 53511012 | Access | 0 | Supervisor | 84 | 10 | HR |  |  | 84 | 0 | 840 | 109.2 | 949.2 | 2021-09-11 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi loading and hauling from km 17 to km 18.5/Chapman rock truck hauling from km 38 to km 40 with Skagen and Morin/Kabi rock truck driving from km .5 on Hensen to km 38 for gravel haul | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-21 |  | 50 | 2021-09-23 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7332KL-20210911-2Supervisor10840 | KABI LAKE FOREST PRODUCTS LTD7332KL-20210911-2Supervisor10840OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7330 | KL-20210910-2 | 53511012 | Access | 0 | Supervisor | 84 | 5 | HR |  |  | 84 | 0 | 420 | 54.6 | 474.6 | 2021-09-10 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator leveling ruts and tracking from Km 12 and Km 5 to Km 19 / 1 rock truck hauling from 38 km to Morin Excavator @ 40/42 km/rock truck 2 driving from Hwy to Km 38 and haul gravel | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-15 |  | 50 | 2021-09-23 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7330KL-20210910-2Supervisor5420 | KABI LAKE FOREST PRODUCTS LTD7330KL-20210910-2Supervisor5420OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7327 | KL-20210909-2 | 53511012 | Access | 0 | Supervisor | 84 | 5 | HR |  |  | 84 | 0 | 420 | 54.6 | 474.6 | 2021-09-09 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator leveling ruts and tracking from Km 38 to Km 16 / rock truck hauling from 38 km to Morin Excavator @ 40/42 km | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-15 |  | 50 | 2021-09-23 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7327KL-20210909-2Supervisor5420 | KABI LAKE FOREST PRODUCTS LTD7327KL-20210909-2Supervisor5420OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7326 | KL-20210908-2 | 53511012 | Access | 0 | Supervisor | 84 | 4 | HR |  |  | 84 | 0 | 336 | 43.68 | 379.68 | 2021-09-08 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator continuing sloping and shaping excavation @ 49 km/ operator Called out to operate Valard rock breaker / Supervision of Morin Contracting and Skagen and Sons | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-15 |  | 50 | 2021-09-23 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7326KL-20210908-2Supervisor4336 | KABI LAKE FOREST PRODUCTS LTD7326KL-20210908-2Supervisor4336OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7325 | KL-20210907-2 | 53511012 | Access | 0 | Supervisor | 84 | 4 | HR |  |  | 84 | 0 | 336 | 43.68 | 379.68 | 2021-09-07 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator continuing sloping and shaping excavation @ 49 km/ Supervision of Morin Contracting and Skagen and Sons Shaping road and fixing access mats from 36 to 33 km and @ km 40.5 to 43.5 Km | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-15 |  | 50 | 2021-09-23 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7325KL-20210907-2Supervisor4336 | KABI LAKE FOREST PRODUCTS LTD7325KL-20210907-2Supervisor4336OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7288 | KL-20210830-2 | 53511012 | Access | 0 | Supervisor | 84 | 4 | HR |  |  | 84 | 0 | 336 | 43.68 | 379.68 | 2021-08-30 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul existing material for excavation clean up @ km49 - 1 Kabi , 1 Valard and 1 Cobiere rock trucks/ excavator 2 shaping and leveling slopes | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-08-31 |  | 37 | 2021-09-05 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7288KL-20210830-2Supervisor4336 | KABI LAKE FOREST PRODUCTS LTD7288KL-20210830-2Supervisor4336OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7287 | KL-20210829-2 | 53511012 | Access | 0 | Supervisor | 84 | 4 | HR |  |  | 84 | 0 | 336 | 43.68 | 379.68 | 2021-08-29 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul existing material for excavation clean up @ km49 - 1 Kabi , 1 Valard and 1 Cobiere rock trucks | 10 | F033-F118 | 600 Road | 0 | 2021-08-31 |  | 37 | 2021-09-05 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7287KL-20210829-2Supervisor4336 | KABI LAKE FOREST PRODUCTS LTD7287KL-20210829-2Supervisor4336OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7283 | KL-20210827-3 | 53511012 | Access | 0 | Supervisor | 84 | 4 | HR |  |  | 84 | 0 | 336 | 43.68 | 379.68 | 2021-08-27 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator starting sloping and cleaning up excavation @ km 49/rock truck hauling existing material from Km 39 to Morin Excavator/ Excavator 2 start sloping Km 49 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-09-05 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7283KL-20210827-3Supervisor4336 | KABI LAKE FOREST PRODUCTS LTD7283KL-20210827-3Supervisor4336OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7281 | KL-20210826-3 | 53511012 | Access | 0 | Supervisor | 84 | 4 | HR |  |  | 84 | 0 | 336 | 43.68 | 379.68 | 2021-08-26 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 Continuing sloping & cleaning up Excavation @ 49Km. Rock Truck hauling existing material from 39Km to Morin Excavator. Excavator 2 fixing access from 44Km to 47Km. | 10 | F033-F118 | Paint lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-09-05 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7281KL-20210826-3Supervisor4336 | KABI LAKE FOREST PRODUCTS LTD7281KL-20210826-3Supervisor4336OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7374 | KL-20210922-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.90909 | DAY |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-09-22 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator working on road maintenance @ 21 km hill/Chapman rock truck hauling trees from F104 to Morin @ km 43/Supervision of Morin and Skagen | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-28 |  | 61 | 2021-09-28 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7374KL-20210922-1L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7374KL-20210922-1L.O.A.0.9090909221.8182OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7374 | KL-20210922-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | DAY |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-09-22 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator working on road maintenance @ 21 km hill/Chapman rock truck hauling trees from F104 to Morin @ km 43/Supervision of Morin and Skagen | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-28 |  | 61 | 2021-09-28 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7374KL-20210922-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7374KL-20210922-1L.O.A.0.8181818199.6364OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7374 | KL-20210922-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | DAY |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-09-22 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator working on road maintenance @ 21 km hill/Chapman rock truck hauling trees from F104 to Morin @ km 43/Supervision of Morin and Skagen | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-28 |  | 61 | 2021-09-28 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7374KL-20210922-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7374KL-20210922-1L.O.A.0.8181818199.6364OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7370 | KL-20210921-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | DAY |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-09-21 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator working on road maintenance @ 17 to 20 km/Chapman rock truck hauling trees from F104 to Morin @ km 43/Supervision of Morin and Skagen | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-28 |  | 50 | 2021-09-28 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7370KL-20210921-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7370KL-20210921-1L.O.A.0.8181818199.6364OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7370 | KL-20210921-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | DAY |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-09-21 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator working on road maintenance @ 17 to 20 km/Chapman rock truck hauling trees from F104 to Morin @ km 43/Supervision of Morin and Skagen | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-28 |  | 50 | 2021-09-28 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7370KL-20210921-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7370KL-20210921-1L.O.A.0.8181818199.6364OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7361 | KL-20210919-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.90909 | DAY |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-09-19 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator working on road maintenance @ 18 to21 km and pulling pickups @ end of shift /Chapman rock truck hauling trees from F104 to Morin @ km 41 and 42. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-27 |  | 50 | 2021-09-27 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7361KL-20210919-1L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7361KL-20210919-1L.O.A.0.9090909221.8182OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7361 | KL-20210919-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.90909 | DAY |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-09-19 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator working on road maintenance @ 18 to21 km and pulling pickups @ end of shift /Chapman rock truck hauling trees from F104 to Morin @ km 41 and 42. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-27 |  | 50 | 2021-09-27 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7361KL-20210919-1L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7361KL-20210919-1L.O.A.0.9090909221.8182OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7355 | KL-20210918-1-R1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.63636 | DAY |  | 0 |  |  | 155.2727 | 20.1855 | 175.4582 | 2021-09-18 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator working on road maintenance @ 18 to21 km /Chapman rock truck hauling access mats and hauling out broken mats for Morin @ Km 44 to 46 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-24 |  | 50 | 2021-09-27 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7355KL-20210918-1-R1L.O.A.0.6363636155.2727 | KABI LAKE FOREST PRODUCTS LTD7355KL-20210918-1-R1L.O.A.0.6363636155.2727OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7355 | KL-20210918-1-R1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | DAY |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-09-18 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator working on road maintenance @ 18 to21 km /Chapman rock truck hauling access mats and hauling out broken mats for Morin @ Km 44 to 46 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-24 |  | 50 | 2021-09-27 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7355KL-20210918-1-R1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7355KL-20210918-1-R1L.O.A.0.8181818199.6364OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7355 | KL-20210918-1-R1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | DAY |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-09-18 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator working on road maintenance @ 18 to21 km /Chapman rock truck hauling access mats and hauling out broken mats for Morin @ Km 44 to 46 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-24 |  | 50 | 2021-09-27 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7355KL-20210918-1-R1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7355KL-20210918-1-R1L.O.A.0.8181818199.6364OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7336 | KL-20210914-2 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | DAY |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-09-14 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  | Mark McLeod Approved |  | Approved |  |  | Kabi loading and hauling from km 17 to km 18.5/Chapman rock truck and Kabi 30 ton rock truck hauling from km 38 to km 40.5 with Skagen and Morin | 10 | F033-F118 | Paint lake Road 2 | 0 | 2021-09-21 |  |  | 2021-09-22 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7336KL-20210914-2L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7336KL-20210914-2L.O.A.0.8181818199.6364OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7335 | KL-20210913-2 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | DAY |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-09-13 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  | Mark McLeod Approved |  | Approved |  |  | Kabi loading and hauling from km 17 to km 18.5/Chapman rock truck and Kabi 30 ton rock truck hauling from km 38 to km 40.5 with Skagen and Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-21 |  |  | 2021-09-22 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7335KL-20210913-2L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7335KL-20210913-2L.O.A.0.8181818199.6364OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7334 | KL-20210912-2 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | DAY |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-09-12 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi loading and hauling from km 17 to km 19/Chapman rock truck and Kabi 30 ton rock truck hauling from km 38 to km 40 with Skagen and Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-21 |  | 50 | 2021-09-23 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7334KL-20210912-2L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7334KL-20210912-2L.O.A.0.8181818199.6364OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7353 | KL-20210917-1-R1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | DAY |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-09-17 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator working on road maintenance @ 18 to20 km /Chapman rock truck hauling access mats from .5 on hensen to km 43/ Kabi rock trucks driving out for float | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-24 |  | 50 | 2021-09-27 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7353KL-20210917-1-R1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7353KL-20210917-1-R1L.O.A.0.8181818199.6364OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7353 | KL-20210917-1-R1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | DAY |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-09-17 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator working on road maintenance @ 18 to20 km /Chapman rock truck hauling access mats from .5 on hensen to km 43/ Kabi rock trucks driving out for float | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-24 |  | 50 | 2021-09-27 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7353KL-20210917-1-R1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7353KL-20210917-1-R1L.O.A.0.8181818199.6364OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7350 | KL-20210916-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | DAY |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-09-16 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  | Approved by Mark McLeod |  | Approved |  |  | Excavator loading and hauling from 18 to19.5 km /Chapman rock truck and Kabi 30 ton rock truck hauling from 38 to 42/43 km with Skagen and Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-24 |  |  | 2021-09-25 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7350KL-20210916-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7350KL-20210916-1L.O.A.0.8181818199.6364OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7332 | KL-20210911-2 | 53511012 | Access | 0 | L.O.A. | 244 | 0.86364 | DAY |  | 0 |  |  | 210.7273 | 27.3945 | 238.1218 | 2021-09-11 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi loading and hauling from km 17 to km 18.5/Chapman rock truck hauling from km 38 to km 40 with Skagen and Morin/Kabi rock truck driving from km .5 on Hensen to km 38 for gravel haul | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-21 |  | 50 | 2021-09-23 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7332KL-20210911-2L.O.A.0.8636364210.7273 | KABI LAKE FOREST PRODUCTS LTD7332KL-20210911-2L.O.A.0.8636364210.7273OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7330 | KL-20210910-2 | 53511012 | Access | 0 | L.O.A. | 244 | 0.86364 | DAY |  | 0 |  |  | 210.7273 | 27.3945 | 238.1218 | 2021-09-10 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator leveling ruts and tracking from Km 12 and Km 5 to Km 19 / 1 rock truck hauling from 38 km to Morin Excavator @ 40/42 km/rock truck 2 driving from Hwy to Km 38 and haul gravel | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-15 |  | 50 | 2021-09-23 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7330KL-20210910-2L.O.A.0.8636364210.7273 | KABI LAKE FOREST PRODUCTS LTD7330KL-20210910-2L.O.A.0.8636364210.7273OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7327 | KL-20210909-2 | 53511012 | Access | 0 | L.O.A. | 244 | 1.5909 | DAY |  | 0 |  |  | 388.1818 | 50.4636 | 438.6454 | 2021-09-09 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator leveling ruts and tracking from Km 38 to Km 16 / rock truck hauling from 38 km to Morin Excavator @ 40/42 km | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-15 |  | 50 | 2021-09-23 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7327KL-20210909-2L.O.A.1.5909091388.1818 | KABI LAKE FOREST PRODUCTS LTD7327KL-20210909-2L.O.A.1.5909091388.1818OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7326 | KL-20210908-2 | 53511012 | Access | 0 | L.O.A. | 244 | 0.86364 | DAY |  | 0 |  |  | 210.7273 | 27.3945 | 238.1218 | 2021-09-08 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator continuing sloping and shaping excavation @ 49 km/ operator Called out to operate Valard rock breaker / Supervision of Morin Contracting and Skagen and Sons | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-15 |  | 50 | 2021-09-23 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7326KL-20210908-2L.O.A.0.8636364210.7273 | KABI LAKE FOREST PRODUCTS LTD7326KL-20210908-2L.O.A.0.8636364210.7273OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7325 | KL-20210907-2 | 53511012 | Access | 0 | L.O.A. | 244 | 0.86364 | DAY |  | 0 |  |  | 210.7273 | 27.3945 | 238.1218 | 2021-09-07 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator continuing sloping and shaping excavation @ 49 km/ Supervision of Morin Contracting and Skagen and Sons Shaping road and fixing access mats from 36 to 33 km and @ km 40.5 to 43.5 Km | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-15 |  | 50 | 2021-09-23 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7325KL-20210907-2L.O.A.0.8636364210.7273 | KABI LAKE FOREST PRODUCTS LTD7325KL-20210907-2L.O.A.0.8636364210.7273OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7288 | KL-20210830-2 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | DAY |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-08-30 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul existing material for excavation clean up @ km49 - 1 Kabi , 1 Valard and 1 Cobiere rock trucks/ excavator 2 shaping and leveling slopes | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-08-31 |  | 37 | 2021-09-05 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7288KL-20210830-2L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7288KL-20210830-2L.O.A.0.8181818199.6364OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7287 | KL-20210829-2 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | DAY |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-08-29 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul existing material for excavation clean up @ km49 - 1 Kabi , 1 Valard and 1 Cobiere rock trucks | 10 | F033-F118 | 600 Road | 0 | 2021-08-31 |  | 37 | 2021-09-05 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7287KL-20210829-2L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7287KL-20210829-2L.O.A.0.8181818199.6364OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7287 | KL-20210829-2 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | DAY |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-08-29 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul existing material for excavation clean up @ km49 - 1 Kabi , 1 Valard and 1 Cobiere rock trucks | 10 | F033-F118 | 600 Road | 0 | 2021-08-31 |  | 37 | 2021-09-05 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7287KL-20210829-2L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7287KL-20210829-2L.O.A.0.8181818199.6364OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7287 | KL-20210829-2 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | DAY |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-08-29 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul existing material for excavation clean up @ km49 - 1 Kabi , 1 Valard and 1 Cobiere rock trucks | 10 | F033-F118 | 600 Road | 0 | 2021-08-31 |  | 37 | 2021-09-05 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7287KL-20210829-2L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7287KL-20210829-2L.O.A.0.8181818199.6364OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7283 | KL-20210827-3 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | DAY |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-08-27 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator starting sloping and cleaning up excavation @ km 49/rock truck hauling existing material from Km 39 to Morin Excavator/ Excavator 2 start sloping Km 49 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-09-05 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7283KL-20210827-3L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7283KL-20210827-3L.O.A.0.8181818199.6364OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7283 | KL-20210827-3 | 53511012 | Access | 0 | L.O.A. | 244 | 0.54545 | DAY |  | 0 |  |  | 133.0909 | 17.3018 | 150.3927 | 2021-08-27 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator starting sloping and cleaning up excavation @ km 49/rock truck hauling existing material from Km 39 to Morin Excavator/ Excavator 2 start sloping Km 49 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-09-05 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7283KL-20210827-3L.O.A.0.5454545133.0909 | KABI LAKE FOREST PRODUCTS LTD7283KL-20210827-3L.O.A.0.5454545133.0909OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7283 | KL-20210827-3 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | DAY |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-08-27 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator starting sloping and cleaning up excavation @ km 49/rock truck hauling existing material from Km 39 to Morin Excavator/ Excavator 2 start sloping Km 49 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-09-05 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7283KL-20210827-3L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7283KL-20210827-3L.O.A.0.8181818199.6364OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7281 | KL-20210826-3 | 53511012 | Access | 0 | L.O.A. | 244 | 0.77273 | DAY |  | 0 |  |  | 188.5455 | 24.5109 | 213.0564 | 2021-08-26 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 Continuing sloping & cleaning up Excavation @ 49Km. Rock Truck hauling existing material from 39Km to Morin Excavator. Excavator 2 fixing access from 44Km to 47Km. | 10 | F033-F118 | Paint lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-09-05 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7281KL-20210826-3L.O.A.0.7727273188.5455 | KABI LAKE FOREST PRODUCTS LTD7281KL-20210826-3L.O.A.0.7727273188.5455OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7281 | KL-20210826-3 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | DAY |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-08-26 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 Continuing sloping & cleaning up Excavation @ 49Km. Rock Truck hauling existing material from 39Km to Morin Excavator. Excavator 2 fixing access from 44Km to 47Km. | 10 | F033-F118 | Paint lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-09-05 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7281KL-20210826-3L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7281KL-20210826-3L.O.A.0.8181818199.6364OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7281 | KL-20210826-3 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | DAY |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-08-26 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 Continuing sloping & cleaning up Excavation @ 49Km. Rock Truck hauling existing material from 39Km to Morin Excavator. Excavator 2 fixing access from 44Km to 47Km. | 10 | F033-F118 | Paint lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-09-05 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7281KL-20210826-3L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7281KL-20210826-3L.O.A.0.8181818199.6364OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7365 | KL-20210920-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | DAY |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-09-20 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator working on road maintenance @ 18 to21.5 km and Carrying trees for moving road@ 19.5km/Chapman rock truck hauling trees from F104 to Morin @ km 43 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-27 |  | 50 | 2021-09-27 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7365KL-20210920-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7365KL-20210920-1L.O.A.0.8181818199.6364OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7370 | KL-20210921-1 | 53511003 | Access | 0 | L.O.A. | 244 | 0.81818 | DAY |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-09-21 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator working on road maintenance @ 17 to 20 km/Chapman rock truck hauling trees from F104 to Morin @ km 43/Supervision of Morin and Skagen | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-28 |  | 50 | 2021-09-28 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7370KL-20210921-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7370KL-20210921-1L.O.A.0.8181818199.6364OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7365 | KL-20210920-1 | 53511003 | Access | 0 | L.O.A. | 244 | 0.81818 | DAY |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-09-20 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator working on road maintenance @ 18 to21.5 km and Carrying trees for moving road@ 19.5km/Chapman rock truck hauling trees from F104 to Morin @ km 43 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-27 |  | 50 | 2021-09-27 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7365KL-20210920-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7365KL-20210920-1L.O.A.0.8181818199.6364OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7374 | KL-20210922-1 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 38 | HR | 19 | 0 |  |  | 950 | 123.5 | 1073.5 | 2021-09-22 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator working on road maintenance @ 21 km hill/Chapman rock truck hauling trees from F104 to Morin @ km 43/Supervision of Morin and Skagen | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-28 |  | 61 | 2021-09-28 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7374KL-20210922-1Pickup 1/2 Ton38950 | KABI LAKE FOREST PRODUCTS LTD7374KL-20210922-1Pickup 1/2 Ton38950OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7370 | KL-20210921-1 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 26 | HR | 19 | 0 |  |  | 650 | 84.5 | 734.5 | 2021-09-21 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator working on road maintenance @ 17 to 20 km/Chapman rock truck hauling trees from F104 to Morin @ km 43/Supervision of Morin and Skagen | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-28 |  | 50 | 2021-09-28 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7370KL-20210921-1Pickup 1/2 Ton26650 | KABI LAKE FOREST PRODUCTS LTD7370KL-20210921-1Pickup 1/2 Ton26650OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7355 | KL-20210918-1-R1 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 32 | HR | 19 | 0 |  |  | 800 | 104 | 904 | 2021-09-18 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator working on road maintenance @ 18 to21 km /Chapman rock truck hauling access mats and hauling out broken mats for Morin @ Km 44 to 46 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-24 |  | 50 | 2021-09-27 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7355KL-20210918-1-R1Pickup 1/2 Ton32800 | KABI LAKE FOREST PRODUCTS LTD7355KL-20210918-1-R1Pickup 1/2 Ton32800OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7336 | KL-20210914-2 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 17 | HR | 19 | 0 |  |  | 425 | 55.25 | 480.25 | 2021-09-14 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  | Mark McLeod Approved |  | Approved |  |  | Kabi loading and hauling from km 17 to km 18.5/Chapman rock truck and Kabi 30 ton rock truck hauling from km 38 to km 40.5 with Skagen and Morin | 10 | F033-F118 | Paint lake Road 2 | 0 | 2021-09-21 |  |  | 2021-09-22 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7336KL-20210914-2Pickup 1/2 Ton17425 | KABI LAKE FOREST PRODUCTS LTD7336KL-20210914-2Pickup 1/2 Ton17425OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7330 | KL-20210910-2 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 14.5 | HR | 19 | 0 |  |  | 362.5 | 47.125 | 409.625 | 2021-09-10 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator leveling ruts and tracking from Km 12 and Km 5 to Km 19 / 1 rock truck hauling from 38 km to Morin Excavator @ 40/42 km/rock truck 2 driving from Hwy to Km 38 and haul gravel | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-15 |  | 50 | 2021-09-23 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7330KL-20210910-2Pickup 1/2 Ton14.5362.5 | KABI LAKE FOREST PRODUCTS LTD7330KL-20210910-2Pickup 1/2 Ton14.5362.5OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7327 | KL-20210909-2 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 21.5 | HR | 19 | 0 |  |  | 537.5 | 69.875 | 607.375 | 2021-09-09 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator leveling ruts and tracking from Km 38 to Km 16 / rock truck hauling from 38 km to Morin Excavator @ 40/42 km | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-15 |  | 50 | 2021-09-23 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7327KL-20210909-2Pickup 1/2 Ton21.5537.5 | KABI LAKE FOREST PRODUCTS LTD7327KL-20210909-2Pickup 1/2 Ton21.5537.5OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7326 | KL-20210908-2 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 8 | HR | 19 | 0 |  |  | 200 | 26 | 226 | 2021-09-08 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator continuing sloping and shaping excavation @ 49 km/ operator Called out to operate Valard rock breaker / Supervision of Morin Contracting and Skagen and Sons | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-15 |  | 50 | 2021-09-23 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7326KL-20210908-2Pickup 1/2 Ton8200 | KABI LAKE FOREST PRODUCTS LTD7326KL-20210908-2Pickup 1/2 Ton8200OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7326 | KL-20210908-2 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 9.5 | HR | 19 | 0 |  |  | 237.5 | 30.875 | 268.375 | 2021-09-08 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator continuing sloping and shaping excavation @ 49 km/ operator Called out to operate Valard rock breaker / Supervision of Morin Contracting and Skagen and Sons | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-15 |  | 50 | 2021-09-23 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7326KL-20210908-2Pickup 1/2 Ton9.5237.5 | KABI LAKE FOREST PRODUCTS LTD7326KL-20210908-2Pickup 1/2 Ton9.5237.5OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7325 | KL-20210907-2 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 13.5 | HR | 19 | 0 |  |  | 337.5 | 43.875 | 381.375 | 2021-09-07 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator continuing sloping and shaping excavation @ 49 km/ Supervision of Morin Contracting and Skagen and Sons Shaping road and fixing access mats from 36 to 33 km and @ km 40.5 to 43.5 Km | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-15 |  | 50 | 2021-09-23 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7325KL-20210907-2Pickup 1/2 Ton13.5337.5 | KABI LAKE FOREST PRODUCTS LTD7325KL-20210907-2Pickup 1/2 Ton13.5337.5OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7288 | KL-20210830-2 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 13 | HR | 19 | 0 |  |  | 325 | 42.25 | 367.25 | 2021-08-30 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul existing material for excavation clean up @ km49 - 1 Kabi , 1 Valard and 1 Cobiere rock trucks/ excavator 2 shaping and leveling slopes | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-08-31 |  | 37 | 2021-09-05 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7288KL-20210830-2Pickup 1/2 Ton13325 | KABI LAKE FOREST PRODUCTS LTD7288KL-20210830-2Pickup 1/2 Ton13325OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7287 | KL-20210829-2 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 22 | HR | 19 | 0 |  |  | 550 | 71.5 | 621.5 | 2021-08-29 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul existing material for excavation clean up @ km49 - 1 Kabi , 1 Valard and 1 Cobiere rock trucks | 10 | F033-F118 | 600 Road | 0 | 2021-08-31 |  | 37 | 2021-09-05 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7287KL-20210829-2Pickup 1/2 Ton22550 | KABI LAKE FOREST PRODUCTS LTD7287KL-20210829-2Pickup 1/2 Ton22550OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7283 | KL-20210827-3 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 19 | HR | 19 | 0 |  |  | 475 | 61.75 | 536.75 | 2021-08-27 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator starting sloping and cleaning up excavation @ km 49/rock truck hauling existing material from Km 39 to Morin Excavator/ Excavator 2 start sloping Km 49 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-09-05 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7283KL-20210827-3Pickup 1/2 Ton19475 | KABI LAKE FOREST PRODUCTS LTD7283KL-20210827-3Pickup 1/2 Ton19475OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7281 | KL-20210826-3 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 22 | HR | 19 | 0 |  |  | 550 | 71.5 | 621.5 | 2021-08-26 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 Continuing sloping & cleaning up Excavation @ 49Km. Rock Truck hauling existing material from 39Km to Morin Excavator. Excavator 2 fixing access from 44Km to 47Km. | 10 | F033-F118 | Paint lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-09-05 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7281KL-20210826-3Pickup 1/2 Ton22550 | KABI LAKE FOREST PRODUCTS LTD7281KL-20210826-3Pickup 1/2 Ton22550OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7374 | KL-20210922-1 | 53511012 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 10 | HR | 134 | 0 |  |  | 1780 | 231.4 | 2011.4 | 2021-09-22 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator working on road maintenance @ 21 km hill/Chapman rock truck hauling trees from F104 to Morin @ km 43/Supervision of Morin and Skagen | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-28 |  | 61 | 2021-09-28 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7374KL-20210922-1CAT 25 ton Articulated Truck101780 | KABI LAKE FOREST PRODUCTS LTD7374KL-20210922-1CAT 25 ton Articulated Truck101780OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7355 | KL-20210918-1-R1 | 53511012 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 7 | HR | 134 | 0 |  |  | 1246 | 161.98 | 1407.98 | 2021-09-18 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator working on road maintenance @ 18 to21 km /Chapman rock truck hauling access mats and hauling out broken mats for Morin @ Km 44 to 46 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-24 |  | 50 | 2021-09-27 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7355KL-20210918-1-R1CAT 25 ton Articulated Truck71246 | KABI LAKE FOREST PRODUCTS LTD7355KL-20210918-1-R1CAT 25 ton Articulated Truck71246OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7327 | KL-20210909-2 | 53511012 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 6.5 | HR | 134 | 0 |  |  | 1157 | 150.41 | 1307.41 | 2021-09-09 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator leveling ruts and tracking from Km 38 to Km 16 / rock truck hauling from 38 km to Morin Excavator @ 40/42 km | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-15 |  | 50 | 2021-09-23 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7327KL-20210909-2CAT 25 ton Articulated Truck6.51157 | KABI LAKE FOREST PRODUCTS LTD7327KL-20210909-2CAT 25 ton Articulated Truck6.51157OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7287 | KL-20210829-2 | 53511012 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 9 | HR | 134 | 0 |  |  | 1602 | 208.26 | 1810.26 | 2021-08-29 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul existing material for excavation clean up @ km49 - 1 Kabi , 1 Valard and 1 Cobiere rock trucks | 10 | F033-F118 | 600 Road | 0 | 2021-08-31 |  | 37 | 2021-09-05 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7287KL-20210829-2CAT 25 ton Articulated Truck91602 | KABI LAKE FOREST PRODUCTS LTD7287KL-20210829-2CAT 25 ton Articulated Truck91602OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7283 | KL-20210827-3 | 53511012 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 9 | HR | 134 | 0 |  |  | 1602 | 208.26 | 1810.26 | 2021-08-27 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator starting sloping and cleaning up excavation @ km 49/rock truck hauling existing material from Km 39 to Morin Excavator/ Excavator 2 start sloping Km 49 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-09-05 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7283KL-20210827-3CAT 25 ton Articulated Truck91602 | KABI LAKE FOREST PRODUCTS LTD7283KL-20210827-3CAT 25 ton Articulated Truck91602OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7281 | KL-20210826-3 | 53511012 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 8.5 | HR | 134 | 0 |  |  | 1513 | 196.69 | 1709.69 | 2021-08-26 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 Continuing sloping & cleaning up Excavation @ 49Km. Rock Truck hauling existing material from 39Km to Morin Excavator. Excavator 2 fixing access from 44Km to 47Km. | 10 | F033-F118 | Paint lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-09-05 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7281KL-20210826-3CAT 25 ton Articulated Truck8.51513 | KABI LAKE FOREST PRODUCTS LTD7281KL-20210826-3CAT 25 ton Articulated Truck8.51513OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7374 | KL-20210922-1 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 9 | HR | 147 | 0 |  |  | 1755 | 228.15 | 1983.15 | 2021-09-22 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator working on road maintenance @ 21 km hill/Chapman rock truck hauling trees from F104 to Morin @ km 43/Supervision of Morin and Skagen | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-28 |  | 61 | 2021-09-28 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7374KL-20210922-130 Ton Excavator c/w Hydraulic Thumb91755 | KABI LAKE FOREST PRODUCTS LTD7374KL-20210922-130 Ton Excavator c/w Hydraulic Thumb91755OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7374 | KL-20210922-1 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 9 | HR | 147 | 0 |  |  | 1755 | 228.15 | 1983.15 | 2021-09-22 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator working on road maintenance @ 21 km hill/Chapman rock truck hauling trees from F104 to Morin @ km 43/Supervision of Morin and Skagen | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-28 |  | 61 | 2021-09-28 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7374KL-20210922-130 Ton Excavator c/w Hydraulic Thumb91755 | KABI LAKE FOREST PRODUCTS LTD7374KL-20210922-130 Ton Excavator c/w Hydraulic Thumb91755OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7370 | KL-20210921-1 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 9 | HR | 147 | 0 |  |  | 1755 | 228.15 | 1983.15 | 2021-09-21 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator working on road maintenance @ 17 to 20 km/Chapman rock truck hauling trees from F104 to Morin @ km 43/Supervision of Morin and Skagen | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-28 |  | 50 | 2021-09-28 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7370KL-20210921-130 Ton Excavator c/w Hydraulic Thumb91755 | KABI LAKE FOREST PRODUCTS LTD7370KL-20210921-130 Ton Excavator c/w Hydraulic Thumb91755OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7370 | KL-20210921-1 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 9 | HR | 147 | 0 |  |  | 1755 | 228.15 | 1983.15 | 2021-09-21 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator working on road maintenance @ 17 to 20 km/Chapman rock truck hauling trees from F104 to Morin @ km 43/Supervision of Morin and Skagen | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-28 |  | 50 | 2021-09-28 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7370KL-20210921-130 Ton Excavator c/w Hydraulic Thumb91755 | KABI LAKE FOREST PRODUCTS LTD7370KL-20210921-130 Ton Excavator c/w Hydraulic Thumb91755OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7361 | KL-20210919-1 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 10 | HR | 147 | 0 |  |  | 1950 | 253.5 | 2203.5 | 2021-09-19 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator working on road maintenance @ 18 to21 km and pulling pickups @ end of shift /Chapman rock truck hauling trees from F104 to Morin @ km 41 and 42. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-27 |  | 50 | 2021-09-27 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7361KL-20210919-130 Ton Excavator c/w Hydraulic Thumb101950 | KABI LAKE FOREST PRODUCTS LTD7361KL-20210919-130 Ton Excavator c/w Hydraulic Thumb101950OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7361 | KL-20210919-1 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 10 | HR | 147 | 0 |  |  | 1950 | 253.5 | 2203.5 | 2021-09-19 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator working on road maintenance @ 18 to21 km and pulling pickups @ end of shift /Chapman rock truck hauling trees from F104 to Morin @ km 41 and 42. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-27 |  | 50 | 2021-09-27 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7361KL-20210919-130 Ton Excavator c/w Hydraulic Thumb101950 | KABI LAKE FOREST PRODUCTS LTD7361KL-20210919-130 Ton Excavator c/w Hydraulic Thumb101950OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7355 | KL-20210918-1-R1 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 9 | HR | 147 | 0 |  |  | 1755 | 228.15 | 1983.15 | 2021-09-18 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator working on road maintenance @ 18 to21 km /Chapman rock truck hauling access mats and hauling out broken mats for Morin @ Km 44 to 46 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-24 |  | 50 | 2021-09-27 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7355KL-20210918-1-R130 Ton Excavator c/w Hydraulic Thumb91755 | KABI LAKE FOREST PRODUCTS LTD7355KL-20210918-1-R130 Ton Excavator c/w Hydraulic Thumb91755OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7336 | KL-20210914-2 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 9 | HR | 147 | 0 |  |  | 1755 | 228.15 | 1983.15 | 2021-09-14 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  | Mark McLeod Approved |  | Approved |  |  | Kabi loading and hauling from km 17 to km 18.5/Chapman rock truck and Kabi 30 ton rock truck hauling from km 38 to km 40.5 with Skagen and Morin | 10 | F033-F118 | Paint lake Road 2 | 0 | 2021-09-21 |  |  | 2021-09-22 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7336KL-20210914-230 Ton Excavator c/w Hydraulic Thumb91755 | KABI LAKE FOREST PRODUCTS LTD7336KL-20210914-230 Ton Excavator c/w Hydraulic Thumb91755OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7335 | KL-20210913-2 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 9 | HR | 147 | 0 |  |  | 1755 | 228.15 | 1983.15 | 2021-09-13 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  | Mark McLeod Approved |  | Approved |  |  | Kabi loading and hauling from km 17 to km 18.5/Chapman rock truck and Kabi 30 ton rock truck hauling from km 38 to km 40.5 with Skagen and Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-21 |  |  | 2021-09-22 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7335KL-20210913-230 Ton Excavator c/w Hydraulic Thumb91755 | KABI LAKE FOREST PRODUCTS LTD7335KL-20210913-230 Ton Excavator c/w Hydraulic Thumb91755OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7334 | KL-20210912-2 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 9 | HR | 147 | 0 |  |  | 1755 | 228.15 | 1983.15 | 2021-09-12 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi loading and hauling from km 17 to km 19/Chapman rock truck and Kabi 30 ton rock truck hauling from km 38 to km 40 with Skagen and Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-21 |  | 50 | 2021-09-23 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7334KL-20210912-230 Ton Excavator c/w Hydraulic Thumb91755 | KABI LAKE FOREST PRODUCTS LTD7334KL-20210912-230 Ton Excavator c/w Hydraulic Thumb91755OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7355 | KL-20210918-1-R1 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 9 | HR | 147 | 0 |  |  | 1755 | 228.15 | 1983.15 | 2021-09-18 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator working on road maintenance @ 18 to21 km /Chapman rock truck hauling access mats and hauling out broken mats for Morin @ Km 44 to 46 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-24 |  | 50 | 2021-09-27 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7355KL-20210918-1-R130 Ton Excavator c/w Hydraulic Thumb91755 | KABI LAKE FOREST PRODUCTS LTD7355KL-20210918-1-R130 Ton Excavator c/w Hydraulic Thumb91755OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7353 | KL-20210917-1-R1 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 9 | HR | 147 | 0 |  |  | 1755 | 228.15 | 1983.15 | 2021-09-17 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator working on road maintenance @ 18 to20 km /Chapman rock truck hauling access mats from .5 on hensen to km 43/ Kabi rock trucks driving out for float | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-24 |  | 50 | 2021-09-27 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7353KL-20210917-1-R130 Ton Excavator c/w Hydraulic Thumb91755 | KABI LAKE FOREST PRODUCTS LTD7353KL-20210917-1-R130 Ton Excavator c/w Hydraulic Thumb91755OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7353 | KL-20210917-1-R1 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 9 | HR | 147 | 0 |  |  | 1755 | 228.15 | 1983.15 | 2021-09-17 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator working on road maintenance @ 18 to20 km /Chapman rock truck hauling access mats from .5 on hensen to km 43/ Kabi rock trucks driving out for float | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-24 |  | 50 | 2021-09-27 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7353KL-20210917-1-R130 Ton Excavator c/w Hydraulic Thumb91755 | KABI LAKE FOREST PRODUCTS LTD7353KL-20210917-1-R130 Ton Excavator c/w Hydraulic Thumb91755OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7350 | KL-20210916-1 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 9 | HR | 147 | 0 |  |  | 1755 | 228.15 | 1983.15 | 2021-09-16 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  | Approved by Mark McLeod |  | Approved |  |  | Excavator loading and hauling from 18 to19.5 km /Chapman rock truck and Kabi 30 ton rock truck hauling from 38 to 42/43 km with Skagen and Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-24 |  |  | 2021-09-25 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7350KL-20210916-130 Ton Excavator c/w Hydraulic Thumb91755 | KABI LAKE FOREST PRODUCTS LTD7350KL-20210916-130 Ton Excavator c/w Hydraulic Thumb91755OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7332 | KL-20210911-2 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 9.5 | HR | 147 | 0 |  |  | 1852.5 | 240.825 | 2093.325 | 2021-09-11 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi loading and hauling from km 17 to km 18.5/Chapman rock truck hauling from km 38 to km 40 with Skagen and Morin/Kabi rock truck driving from km .5 on Hensen to km 38 for gravel haul | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-21 |  | 50 | 2021-09-23 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7332KL-20210911-230 Ton Excavator c/w Hydraulic Thumb9.51852.5 | KABI LAKE FOREST PRODUCTS LTD7332KL-20210911-230 Ton Excavator c/w Hydraulic Thumb9.51852.5OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7330 | KL-20210910-2 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 9.5 | HR | 147 | 0 |  |  | 1852.5 | 240.825 | 2093.325 | 2021-09-10 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator leveling ruts and tracking from Km 12 and Km 5 to Km 19 / 1 rock truck hauling from 38 km to Morin Excavator @ 40/42 km/rock truck 2 driving from Hwy to Km 38 and haul gravel | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-15 |  | 50 | 2021-09-23 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7330KL-20210910-230 Ton Excavator c/w Hydraulic Thumb9.51852.5 | KABI LAKE FOREST PRODUCTS LTD7330KL-20210910-230 Ton Excavator c/w Hydraulic Thumb9.51852.5OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7327 | KL-20210909-2 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 12 | HR | 147 | 0 |  |  | 2340 | 304.2 | 2644.2 | 2021-09-09 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator leveling ruts and tracking from Km 38 to Km 16 / rock truck hauling from 38 km to Morin Excavator @ 40/42 km | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-15 |  | 50 | 2021-09-23 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7327KL-20210909-230 Ton Excavator c/w Hydraulic Thumb122340 | KABI LAKE FOREST PRODUCTS LTD7327KL-20210909-230 Ton Excavator c/w Hydraulic Thumb122340OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7326 | KL-20210908-2 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 9.5 | HR | 147 | 0 |  |  | 1852.5 | 240.825 | 2093.325 | 2021-09-08 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator continuing sloping and shaping excavation @ 49 km/ operator Called out to operate Valard rock breaker / Supervision of Morin Contracting and Skagen and Sons | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-15 |  | 50 | 2021-09-23 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7326KL-20210908-230 Ton Excavator c/w Hydraulic Thumb9.51852.5 | KABI LAKE FOREST PRODUCTS LTD7326KL-20210908-230 Ton Excavator c/w Hydraulic Thumb9.51852.5OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7325 | KL-20210907-2 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 9.5 | HR | 147 | 0 |  |  | 1852.5 | 240.825 | 2093.325 | 2021-09-07 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator continuing sloping and shaping excavation @ 49 km/ Supervision of Morin Contracting and Skagen and Sons Shaping road and fixing access mats from 36 to 33 km and @ km 40.5 to 43.5 Km | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-15 |  | 50 | 2021-09-23 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7325KL-20210907-230 Ton Excavator c/w Hydraulic Thumb9.51852.5 | KABI LAKE FOREST PRODUCTS LTD7325KL-20210907-230 Ton Excavator c/w Hydraulic Thumb9.51852.5OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7288 | KL-20210830-2 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 9 | HR | 147 | 0 |  |  | 1755 | 228.15 | 1983.15 | 2021-08-30 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul existing material for excavation clean up @ km49 - 1 Kabi , 1 Valard and 1 Cobiere rock trucks/ excavator 2 shaping and leveling slopes | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-08-31 |  | 37 | 2021-09-05 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7288KL-20210830-230 Ton Excavator c/w Hydraulic Thumb91755 | KABI LAKE FOREST PRODUCTS LTD7288KL-20210830-230 Ton Excavator c/w Hydraulic Thumb91755OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7287 | KL-20210829-2 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 9 | HR | 147 | 0 |  |  | 1755 | 228.15 | 1983.15 | 2021-08-29 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul existing material for excavation clean up @ km49 - 1 Kabi , 1 Valard and 1 Cobiere rock trucks | 10 | F033-F118 | 600 Road | 0 | 2021-08-31 |  | 37 | 2021-09-05 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7287KL-20210829-230 Ton Excavator c/w Hydraulic Thumb91755 | KABI LAKE FOREST PRODUCTS LTD7287KL-20210829-230 Ton Excavator c/w Hydraulic Thumb91755OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7287 | KL-20210829-2 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 9 | HR | 147 | 0 |  |  | 1755 | 228.15 | 1983.15 | 2021-08-29 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul existing material for excavation clean up @ km49 - 1 Kabi , 1 Valard and 1 Cobiere rock trucks | 10 | F033-F118 | 600 Road | 0 | 2021-08-31 |  | 37 | 2021-09-05 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7287KL-20210829-230 Ton Excavator c/w Hydraulic Thumb91755 | KABI LAKE FOREST PRODUCTS LTD7287KL-20210829-230 Ton Excavator c/w Hydraulic Thumb91755OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7283 | KL-20210827-3 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 6 | HR | 147 | 0 |  |  | 1170 | 152.1 | 1322.1 | 2021-08-27 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator starting sloping and cleaning up excavation @ km 49/rock truck hauling existing material from Km 39 to Morin Excavator/ Excavator 2 start sloping Km 49 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-09-05 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7283KL-20210827-330 Ton Excavator c/w Hydraulic Thumb61170 | KABI LAKE FOREST PRODUCTS LTD7283KL-20210827-330 Ton Excavator c/w Hydraulic Thumb61170OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7283 | KL-20210827-3 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 9 | HR | 147 | 0 |  |  | 1755 | 228.15 | 1983.15 | 2021-08-27 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator starting sloping and cleaning up excavation @ km 49/rock truck hauling existing material from Km 39 to Morin Excavator/ Excavator 2 start sloping Km 49 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-09-05 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7283KL-20210827-330 Ton Excavator c/w Hydraulic Thumb91755 | KABI LAKE FOREST PRODUCTS LTD7283KL-20210827-330 Ton Excavator c/w Hydraulic Thumb91755OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7281 | KL-20210826-3 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 9 | HR | 147 | 0 |  |  | 1755 | 228.15 | 1983.15 | 2021-08-26 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 Continuing sloping & cleaning up Excavation @ 49Km. Rock Truck hauling existing material from 39Km to Morin Excavator. Excavator 2 fixing access from 44Km to 47Km. | 10 | F033-F118 | Paint lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-09-05 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7281KL-20210826-330 Ton Excavator c/w Hydraulic Thumb91755 | KABI LAKE FOREST PRODUCTS LTD7281KL-20210826-330 Ton Excavator c/w Hydraulic Thumb91755OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7281 | KL-20210826-3 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 9 | HR | 147 | 0 |  |  | 1755 | 228.15 | 1983.15 | 2021-08-26 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator 1 Continuing sloping & cleaning up Excavation @ 49Km. Rock Truck hauling existing material from 39Km to Morin Excavator. Excavator 2 fixing access from 44Km to 47Km. | 10 | F033-F118 | Paint lake Road 2 | 0 | 2021-08-30 |  | 37 | 2021-09-05 | [5 empty] | Harold Furlong | 10 | KABI LAKE FOREST PRODUCTS LTD7281KL-20210826-330 Ton Excavator c/w Hydraulic Thumb91755 | KABI LAKE FOREST PRODUCTS LTD7281KL-20210826-330 Ton Excavator c/w Hydraulic Thumb91755OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7365 | KL-20210920-1 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 9 | HR | 147 | 0 |  |  | 1755 | 228.15 | 1983.15 | 2021-09-20 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator working on road maintenance @ 18 to21.5 km and Carrying trees for moving road@ 19.5km/Chapman rock truck hauling trees from F104 to Morin @ km 43 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-27 |  | 50 | 2021-09-27 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7365KL-20210920-130 Ton Excavator c/w Hydraulic Thumb91755 | KABI LAKE FOREST PRODUCTS LTD7365KL-20210920-130 Ton Excavator c/w Hydraulic Thumb91755OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7365 | KL-20210920-1 | 53511003 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 9 | HR | 147 | 0 |  |  | 1755 | 228.15 | 1983.15 | 2021-09-20 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator working on road maintenance @ 18 to21.5 km and Carrying trees for moving road@ 19.5km/Chapman rock truck hauling trees from F104 to Morin @ km 43 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-27 |  | 50 | 2021-09-27 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7365KL-20210920-130 Ton Excavator c/w Hydraulic Thumb91755 | KABI LAKE FOREST PRODUCTS LTD7365KL-20210920-130 Ton Excavator c/w Hydraulic Thumb91755OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7353 | KL-20210917-1-R1 | 53511012 | Access | 0 | Pickup Truck - Truck Only | 25 | 21 | HR | 19 | 0 |  |  | 525 | 68.25 | 593.25 | 2021-09-17 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator working on road maintenance @ 18 to20 km /Chapman rock truck hauling access mats from .5 on hensen to km 43/ Kabi rock trucks driving out for float | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-24 |  | 50 | 2021-09-27 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7353KL-20210917-1-R1Pickup Truck - Truck Only21525 | KABI LAKE FOREST PRODUCTS LTD7353KL-20210917-1-R1Pickup Truck - Truck Only21525OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7353 | KL-20210917-1-R1 | 53511012 | Access | 0 | Pickup Truck - Truck Only | 25 | 9 | HR | 19 | 0 |  |  | 225 | 29.25 | 254.25 | 2021-09-17 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator working on road maintenance @ 18 to20 km /Chapman rock truck hauling access mats from .5 on hensen to km 43/ Kabi rock trucks driving out for float | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-24 |  | 50 | 2021-09-27 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7353KL-20210917-1-R1Pickup Truck - Truck Only9225 | KABI LAKE FOREST PRODUCTS LTD7353KL-20210917-1-R1Pickup Truck - Truck Only9225OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7350 | KL-20210916-1 | 53511012 | Access | 0 | Pickup Truck - Truck Only | 25 | 9 | HR | 19 | 0 |  |  | 225 | 29.25 | 254.25 | 2021-09-16 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  | Approved by Mark McLeod |  | Approved |  |  | Excavator loading and hauling from 18 to19.5 km /Chapman rock truck and Kabi 30 ton rock truck hauling from 38 to 42/43 km with Skagen and Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-24 |  |  | 2021-09-25 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7350KL-20210916-1Pickup Truck - Truck Only9225 | KABI LAKE FOREST PRODUCTS LTD7350KL-20210916-1Pickup Truck - Truck Only9225OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7374 | KL-20210922-1 | 53511012 | Access | 0 | Single Axle Trailer - without pickup - Daily | 30 | 1 | Daily |  | 0 |  |  | 30 | 3.9 | 33.9 | 2021-09-22 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator working on road maintenance @ 21 km hill/Chapman rock truck hauling trees from F104 to Morin @ km 43/Supervision of Morin and Skagen | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-28 |  | 61 | 2021-09-28 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7374KL-20210922-1Single Axle Trailer - without pickup - Daily130 | KABI LAKE FOREST PRODUCTS LTD7374KL-20210922-1Single Axle Trailer - without pickup - Daily130OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7355 | KL-20210918-1-R1 | 53511012 | Access | 0 | Single Axle Trailer - without pickup - Daily | 30 | 1 | Daily |  | 0 |  |  | 30 | 3.9 | 33.9 | 2021-09-18 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator working on road maintenance @ 18 to21 km /Chapman rock truck hauling access mats and hauling out broken mats for Morin @ Km 44 to 46 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-24 |  | 50 | 2021-09-27 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7355KL-20210918-1-R1Single Axle Trailer - without pickup - Daily130 | KABI LAKE FOREST PRODUCTS LTD7355KL-20210918-1-R1Single Axle Trailer - without pickup - Daily130OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7336 | KL-20210914-2 | 53511012 | Access | 0 | Single Axle Trailer - without pickup - Daily | 30 | 1 | Daily |  | 0 |  |  | 30 | 3.9 | 33.9 | 2021-09-14 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  | Mark McLeod Approved |  | Approved |  |  | Kabi loading and hauling from km 17 to km 18.5/Chapman rock truck and Kabi 30 ton rock truck hauling from km 38 to km 40.5 with Skagen and Morin | 10 | F033-F118 | Paint lake Road 2 | 0 | 2021-09-21 |  |  | 2021-09-22 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7336KL-20210914-2Single Axle Trailer - without pickup - Daily130 | KABI LAKE FOREST PRODUCTS LTD7336KL-20210914-2Single Axle Trailer - without pickup - Daily130OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7335 | KL-20210913-2 | 53511012 | Access | 0 | Single Axle Trailer - without pickup - Daily | 30 | 1 | Daily |  | 0 |  |  | 30 | 3.9 | 33.9 | 2021-09-13 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  | Mark McLeod Approved |  | Approved |  |  | Kabi loading and hauling from km 17 to km 18.5/Chapman rock truck and Kabi 30 ton rock truck hauling from km 38 to km 40.5 with Skagen and Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-21 |  |  | 2021-09-22 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7335KL-20210913-2Single Axle Trailer - without pickup - Daily130 | KABI LAKE FOREST PRODUCTS LTD7335KL-20210913-2Single Axle Trailer - without pickup - Daily130OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7374 | KL-20210922-1 | 53511012 | Access | 0 | ATV - side by side - Daily | 250 | 1 | Daily |  | 0 |  |  | 250 | 32.5 | 282.5 | 2021-09-22 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator working on road maintenance @ 21 km hill/Chapman rock truck hauling trees from F104 to Morin @ km 43/Supervision of Morin and Skagen | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-28 |  | 61 | 2021-09-28 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7374KL-20210922-1ATV - side by side - Daily1250 | KABI LAKE FOREST PRODUCTS LTD7374KL-20210922-1ATV - side by side - Daily1250OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7355 | KL-20210918-1-R1 | 53511012 | Access | 0 | ATV - side by side - Daily | 250 | 1 | Daily |  | 0 |  |  | 250 | 32.5 | 282.5 | 2021-09-18 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Kabi Excavator working on road maintenance @ 18 to21 km /Chapman rock truck hauling access mats and hauling out broken mats for Morin @ Km 44 to 46 | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-24 |  | 50 | 2021-09-27 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7355KL-20210918-1-R1ATV - side by side - Daily1250 | KABI LAKE FOREST PRODUCTS LTD7355KL-20210918-1-R1ATV - side by side - Daily1250OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7336 | KL-20210914-2 | 53511012 | Access | 0 | ATV - side by side - Daily | 250 | 1 | Daily |  | 0 |  |  | 250 | 32.5 | 282.5 | 2021-09-14 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  | Mark McLeod Approved |  | Approved |  |  | Kabi loading and hauling from km 17 to km 18.5/Chapman rock truck and Kabi 30 ton rock truck hauling from km 38 to km 40.5 with Skagen and Morin | 10 | F033-F118 | Paint lake Road 2 | 0 | 2021-09-21 |  |  | 2021-09-22 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7336KL-20210914-2ATV - side by side - Daily1250 | KABI LAKE FOREST PRODUCTS LTD7336KL-20210914-2ATV - side by side - Daily1250OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7335 | KL-20210913-2 | 53511012 | Access | 0 | ATV - side by side - Daily | 250 | 1 | Daily |  | 0 |  |  | 250 | 32.5 | 282.5 | 2021-09-13 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  | Mark McLeod Approved |  | Approved |  |  | Kabi loading and hauling from km 17 to km 18.5/Chapman rock truck and Kabi 30 ton rock truck hauling from km 38 to km 40.5 with Skagen and Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-09-21 |  |  | 2021-09-22 | [6 empty] | 10 | KABI LAKE FOREST PRODUCTS LTD7335KL-20210913-2ATV - side by side - Daily1250 | KABI LAKE FOREST PRODUCTS LTD7335KL-20210913-2ATV - side by side - Daily1250OEWT-PA21-LEM |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7392 | KL-20210925-4 | 53510703 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2021-09-25 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working on drainage and shaping road from D011 to D013/Track packing wetland at D012/ rock truck on site for graveling | 7 | D009-D017 | Three Finger Lake | 0 | 2021-06-29 |  | 62 | 2021-10-02 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7392KL-20210925-4Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD7392KL-20210925-4Supervisor3252OEWT-PA21-LEM | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7388 | KL-20210924-5 | 53510703 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2021-09-24 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Load and haul stumps, grubbing and trees for crossing of wetlands from D012 to D013 due to no access mats | 7 | D006-D017 | Three Finger Lake | 0 | 2021-09-25 |  | 62 | 2021-10-02 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7388KL-20210924-5Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD7388KL-20210924-5Supervisor3252OEWT-PA21-LEM | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7383 | KL-20210923-5 | 53510703 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2021-09-23 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Load and haul stumps, grubbing and trees for crossing of wetlands from D012 to D013 due to no access mats | 7 | D006-D017 | Three Finger Lake | 0 | 2021-09-29 |  | 62 | 2021-10-02 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7383KL-20210923-5Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD7383KL-20210923-5Supervisor3252OEWT-PA21-LEM | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7378 | KL-20210922-5 | 53510703 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2021-09-22 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Load And haul stumps, grubbing and trees for crossing of wetlands @ D012 | 7 | D006-D017 | Three Finger Lake | 0 | 2021-09-28 |  | 37 | 2021-09-28 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7378KL-20210922-5Supervisor184 | KABI LAKE FOREST PRODUCTS LTD7378KL-20210922-5Supervisor184OEWT-PA21-LEM | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7372 | KL-20210921-3 | 53510703 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2021-09-21 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load And haul stumps, grubbing and trees for crossing of wetlands @ D012 | 7 | D006-D017 | Three Finger Lake | 0 | 2021-09-28 |  | 37 | 2021-09-28 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7372KL-20210921-3Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD7372KL-20210921-3Supervisor3252OEWT-PA21-LEM | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7392 | KL-20210925-4 | 53510703 | Access | 0 | L.O.A. | 244 | 0.45455 | DAY |  | 0 |  |  | 110.9091 | 14.4182 | 125.3273 | 2021-09-25 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working on drainage and shaping road from D011 to D013/Track packing wetland at D012/ rock truck on site for graveling | 7 | D009-D017 | Three Finger Lake | 0 | 2021-06-29 |  | 62 | 2021-10-02 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7392KL-20210925-4L.O.A.0.4545455110.9091 | KABI LAKE FOREST PRODUCTS LTD7392KL-20210925-4L.O.A.0.4545455110.9091OEWT-PA21-LEM | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7392 | KL-20210925-4 | 53510703 | Access | 0 | L.O.A. | 244 | 0.90909 | DAY |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-09-25 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working on drainage and shaping road from D011 to D013/Track packing wetland at D012/ rock truck on site for graveling | 7 | D009-D017 | Three Finger Lake | 0 | 2021-06-29 |  | 62 | 2021-10-02 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7392KL-20210925-4L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7392KL-20210925-4L.O.A.0.9090909221.8182OEWT-PA21-LEM | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7388 | KL-20210924-5 | 53510703 | Access | 0 | L.O.A. | 244 | 0.81818 | DAY |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-09-24 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Load and haul stumps, grubbing and trees for crossing of wetlands from D012 to D013 due to no access mats | 7 | D006-D017 | Three Finger Lake | 0 | 2021-09-25 |  | 62 | 2021-10-02 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7388KL-20210924-5L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7388KL-20210924-5L.O.A.0.8181818199.6364OEWT-PA21-LEM | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7388 | KL-20210924-5 | 53510703 | Access | 0 | L.O.A. | 244 | 0.90909 | DAY |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-09-24 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Load and haul stumps, grubbing and trees for crossing of wetlands from D012 to D013 due to no access mats | 7 | D006-D017 | Three Finger Lake | 0 | 2021-09-25 |  | 62 | 2021-10-02 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7388KL-20210924-5L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7388KL-20210924-5L.O.A.0.9090909221.8182OEWT-PA21-LEM | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7383 | KL-20210923-5 | 53510703 | Access | 0 | L.O.A. | 244 | 0.90909 | DAY |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-09-23 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Load and haul stumps, grubbing and trees for crossing of wetlands from D012 to D013 due to no access mats | 7 | D006-D017 | Three Finger Lake | 0 | 2021-09-29 |  | 62 | 2021-10-02 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7383KL-20210923-5L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7383KL-20210923-5L.O.A.0.9090909221.8182OEWT-PA21-LEM | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7383 | KL-20210923-5 | 53510703 | Access | 0 | L.O.A. | 244 | 0.90909 | DAY |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-09-23 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Load and haul stumps, grubbing and trees for crossing of wetlands from D012 to D013 due to no access mats | 7 | D006-D017 | Three Finger Lake | 0 | 2021-09-29 |  | 62 | 2021-10-02 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7383KL-20210923-5L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7383KL-20210923-5L.O.A.0.9090909221.8182OEWT-PA21-LEM | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7378 | KL-20210922-5 | 53510703 | Access | 0 | L.O.A. | 244 | 0.90909 | DAY |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-09-22 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Load And haul stumps, grubbing and trees for crossing of wetlands @ D012 | 7 | D006-D017 | Three Finger Lake | 0 | 2021-09-28 |  | 37 | 2021-09-28 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7378KL-20210922-5L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7378KL-20210922-5L.O.A.0.9090909221.8182OEWT-PA21-LEM | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7378 | KL-20210922-5 | 53510703 | Access | 0 | L.O.A. | 244 | 0.90909 | DAY |  |  |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-09-22 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Load And haul stumps, grubbing and trees for crossing of wetlands @ D012 | 7 | D006-D017 | Three Finger Lake | 0 | 2021-09-28 |  | 37 | 2021-09-28 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7378KL-20210922-5L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7378KL-20210922-5L.O.A.0.9090909221.8182OEWT-PA21-LEM | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7378 | KL-20210922-5 | 53510703 | Access | 0 | L.O.A. | 244 | 0.90909 | DAY |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-09-22 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Load And haul stumps, grubbing and trees for crossing of wetlands @ D012 | 7 | D006-D017 | Three Finger Lake | 0 | 2021-09-28 |  | 37 | 2021-09-28 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7378KL-20210922-5L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7378KL-20210922-5L.O.A.0.9090909221.8182OEWT-PA21-LEM | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7372 | KL-20210921-3 | 53510703 | Access | 0 | L.O.A. | 244 | 0.90909 | DAY |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-09-21 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load And haul stumps, grubbing and trees for crossing of wetlands @ D012 | 7 | D006-D017 | Three Finger Lake | 0 | 2021-09-28 |  | 37 | 2021-09-28 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7372KL-20210921-3L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7372KL-20210921-3L.O.A.0.9090909221.8182OEWT-PA21-LEM | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7372 | KL-20210921-3 | 53510703 | Access | 0 | L.O.A. | 244 | 0.90909 | DAY |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-09-21 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load And haul stumps, grubbing and trees for crossing of wetlands @ D012 | 7 | D006-D017 | Three Finger Lake | 0 | 2021-09-28 |  | 37 | 2021-09-28 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7372KL-20210921-3L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7372KL-20210921-3L.O.A.0.9090909221.8182OEWT-PA21-LEM | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7372 | KL-20210921-3 | 53510703 | Access | 0 | L.O.A. | 244 | 0.90909 | DAY |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-09-21 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load And haul stumps, grubbing and trees for crossing of wetlands @ D012 | 7 | D006-D017 | Three Finger Lake | 0 | 2021-09-28 |  | 37 | 2021-09-28 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7372KL-20210921-3L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7372KL-20210921-3L.O.A.0.9090909221.8182OEWT-PA21-LEM | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7392 | KL-20210925-4 | 53510703 | Access | 0 | Pickup 1/2 Ton | 25 | 13 | HR | 19 | 0 |  |  | 325 | 42.25 | 367.25 | 2021-09-25 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working on drainage and shaping road from D011 to D013/Track packing wetland at D012/ rock truck on site for graveling | 7 | D009-D017 | Three Finger Lake | 0 | 2021-06-29 |  | 62 | 2021-10-02 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7392KL-20210925-4Pickup 1/2 Ton13325 | KABI LAKE FOREST PRODUCTS LTD7392KL-20210925-4Pickup 1/2 Ton13325OEWT-PA21-LEM | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7388 | KL-20210924-5 | 53510703 | Access | 0 | Pickup 1/2 Ton | 25 | 13 | HR | 19 | 0 |  |  | 325 | 42.25 | 367.25 | 2021-09-24 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Load and haul stumps, grubbing and trees for crossing of wetlands from D012 to D013 due to no access mats | 7 | D006-D017 | Three Finger Lake | 0 | 2021-09-25 |  | 62 | 2021-10-02 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7388KL-20210924-5Pickup 1/2 Ton13325 | KABI LAKE FOREST PRODUCTS LTD7388KL-20210924-5Pickup 1/2 Ton13325OEWT-PA21-LEM | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7383 | KL-20210923-5 | 53510703 | Access | 0 | Pickup 1/2 Ton | 25 | 13 | HR | 19 | 0 |  |  | 325 | 42.25 | 367.25 | 2021-09-23 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Load and haul stumps, grubbing and trees for crossing of wetlands from D012 to D013 due to no access mats | 7 | D006-D017 | Three Finger Lake | 0 | 2021-09-29 |  | 62 | 2021-10-02 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7383KL-20210923-5Pickup 1/2 Ton13325 | KABI LAKE FOREST PRODUCTS LTD7383KL-20210923-5Pickup 1/2 Ton13325OEWT-PA21-LEM | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7378 | KL-20210922-5 | 53510703 | Access | 0 | Pickup 1/2 Ton | 25 | 21 | HR | 19 | 0 |  |  | 525 | 68.25 | 593.25 | 2021-09-22 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Load And haul stumps, grubbing and trees for crossing of wetlands @ D012 | 7 | D006-D017 | Three Finger Lake | 0 | 2021-09-28 |  | 37 | 2021-09-28 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7378KL-20210922-5Pickup 1/2 Ton21525 | KABI LAKE FOREST PRODUCTS LTD7378KL-20210922-5Pickup 1/2 Ton21525OEWT-PA21-LEM | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7372 | KL-20210921-3 | 53510703 | Access | 0 | Pickup 1/2 Ton | 25 | 23 | HR | 19 | 0 |  |  | 575 | 74.75 | 649.75 | 2021-09-21 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load And haul stumps, grubbing and trees for crossing of wetlands @ D012 | 7 | D006-D017 | Three Finger Lake | 0 | 2021-09-28 |  | 37 | 2021-09-28 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7372KL-20210921-3Pickup 1/2 Ton23575 | KABI LAKE FOREST PRODUCTS LTD7372KL-20210921-3Pickup 1/2 Ton23575OEWT-PA21-LEM | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7392 | KL-20210925-4 | 53510703 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 5 | HR | 134 | 0 |  |  | 890 | 115.7 | 1005.7 | 2021-09-25 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working on drainage and shaping road from D011 to D013/Track packing wetland at D012/ rock truck on site for graveling | 7 | D009-D017 | Three Finger Lake | 0 | 2021-06-29 |  | 62 | 2021-10-02 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7392KL-20210925-4CAT 25 ton Articulated Truck5890 | KABI LAKE FOREST PRODUCTS LTD7392KL-20210925-4CAT 25 ton Articulated Truck5890OEWT-PA21-LEM | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7388 | KL-20210924-5 | 53510703 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 9 | HR | 134 | 0 |  |  | 1602 | 208.26 | 1810.26 | 2021-09-24 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Load and haul stumps, grubbing and trees for crossing of wetlands from D012 to D013 due to no access mats | 7 | D006-D017 | Three Finger Lake | 0 | 2021-09-25 |  | 62 | 2021-10-02 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7388KL-20210924-5CAT 25 ton Articulated Truck91602 | KABI LAKE FOREST PRODUCTS LTD7388KL-20210924-5CAT 25 ton Articulated Truck91602OEWT-PA21-LEM | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7383 | KL-20210923-5 | 53510703 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 10 | HR | 134 | 0 |  |  | 1780 | 231.4 | 2011.4 | 2021-09-23 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Load and haul stumps, grubbing and trees for crossing of wetlands from D012 to D013 due to no access mats | 7 | D006-D017 | Three Finger Lake | 0 | 2021-09-29 |  | 62 | 2021-10-02 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7383KL-20210923-5CAT 25 ton Articulated Truck101780 | KABI LAKE FOREST PRODUCTS LTD7383KL-20210923-5CAT 25 ton Articulated Truck101780OEWT-PA21-LEM | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7378 | KL-20210922-5 | 53510703 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 10 | HR | 134 | 0 |  |  | 1780 | 231.4 | 2011.4 | 2021-09-22 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Load And haul stumps, grubbing and trees for crossing of wetlands @ D012 | 7 | D006-D017 | Three Finger Lake | 0 | 2021-09-28 |  | 37 | 2021-09-28 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7378KL-20210922-5CAT 25 ton Articulated Truck101780 | KABI LAKE FOREST PRODUCTS LTD7378KL-20210922-5CAT 25 ton Articulated Truck101780OEWT-PA21-LEM | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7372 | KL-20210921-3 | 53510703 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 10 | HR | 134 | 0 |  |  | 1780 | 231.4 | 2011.4 | 2021-09-21 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load And haul stumps, grubbing and trees for crossing of wetlands @ D012 | 7 | D006-D017 | Three Finger Lake | 0 | 2021-09-28 |  | 37 | 2021-09-28 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7372KL-20210921-3CAT 25 ton Articulated Truck101780 | KABI LAKE FOREST PRODUCTS LTD7372KL-20210921-3CAT 25 ton Articulated Truck101780OEWT-PA21-LEM | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7392 | KL-20210925-4 | 53510703 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 10 | HR | 147 | 0 |  |  | 1950 | 253.5 | 2203.5 | 2021-09-25 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working on drainage and shaping road from D011 to D013/Track packing wetland at D012/ rock truck on site for graveling | 7 | D009-D017 | Three Finger Lake | 0 | 2021-06-29 |  | 62 | 2021-10-02 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7392KL-20210925-430 Ton Excavator c/w Hydraulic Thumb101950 | KABI LAKE FOREST PRODUCTS LTD7392KL-20210925-430 Ton Excavator c/w Hydraulic Thumb101950OEWT-PA21-LEM | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7388 | KL-20210924-5 | 53510703 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 10 | HR | 147 | 0 |  |  | 1950 | 253.5 | 2203.5 | 2021-09-24 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Load and haul stumps, grubbing and trees for crossing of wetlands from D012 to D013 due to no access mats | 7 | D006-D017 | Three Finger Lake | 0 | 2021-09-25 |  | 62 | 2021-10-02 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7388KL-20210924-530 Ton Excavator c/w Hydraulic Thumb101950 | KABI LAKE FOREST PRODUCTS LTD7388KL-20210924-530 Ton Excavator c/w Hydraulic Thumb101950OEWT-PA21-LEM | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7383 | KL-20210923-5 | 53510703 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 10 | HR | 147 | 0 |  |  | 1950 | 253.5 | 2203.5 | 2021-09-23 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Load and haul stumps, grubbing and trees for crossing of wetlands from D012 to D013 due to no access mats | 7 | D006-D017 | Three Finger Lake | 0 | 2021-09-29 |  | 62 | 2021-10-02 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7383KL-20210923-530 Ton Excavator c/w Hydraulic Thumb101950 | KABI LAKE FOREST PRODUCTS LTD7383KL-20210923-530 Ton Excavator c/w Hydraulic Thumb101950OEWT-PA21-LEM | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7378 | KL-20210922-5 | 53510703 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 10 | HR | 147 | 0 |  |  | 1950 | 253.5 | 2203.5 | 2021-09-22 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Load And haul stumps, grubbing and trees for crossing of wetlands @ D012 | 7 | D006-D017 | Three Finger Lake | 0 | 2021-09-28 |  | 37 | 2021-09-28 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7378KL-20210922-530 Ton Excavator c/w Hydraulic Thumb101950 | KABI LAKE FOREST PRODUCTS LTD7378KL-20210922-530 Ton Excavator c/w Hydraulic Thumb101950OEWT-PA21-LEM | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7378 | KL-20210922-5 | 53510703 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 10 | HR | 147 | 0 |  |  | 1950 | 253.5 | 2203.5 | 2021-09-22 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Load And haul stumps, grubbing and trees for crossing of wetlands @ D012 | 7 | D006-D017 | Three Finger Lake | 0 | 2021-09-28 |  | 37 | 2021-09-28 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7378KL-20210922-530 Ton Excavator c/w Hydraulic Thumb101950 | KABI LAKE FOREST PRODUCTS LTD7378KL-20210922-530 Ton Excavator c/w Hydraulic Thumb101950OEWT-PA21-LEM | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7372 | KL-20210921-3 | 53510703 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 10 | HR | 147 | 0 |  |  | 1950 | 253.5 | 2203.5 | 2021-09-21 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load And haul stumps, grubbing and trees for crossing of wetlands @ D012 | 7 | D006-D017 | Three Finger Lake | 0 | 2021-09-28 |  | 37 | 2021-09-28 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7372KL-20210921-330 Ton Excavator c/w Hydraulic Thumb101950 | KABI LAKE FOREST PRODUCTS LTD7372KL-20210921-330 Ton Excavator c/w Hydraulic Thumb101950OEWT-PA21-LEM | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7372 | KL-20210921-3 | 53510703 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 10 | HR | 147 | 0 |  |  | 1950 | 253.5 | 2203.5 | 2021-09-21 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load And haul stumps, grubbing and trees for crossing of wetlands @ D012 | 7 | D006-D017 | Three Finger Lake | 0 | 2021-09-28 |  | 37 | 2021-09-28 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7372KL-20210921-330 Ton Excavator c/w Hydraulic Thumb101950 | KABI LAKE FOREST PRODUCTS LTD7372KL-20210921-330 Ton Excavator c/w Hydraulic Thumb101950OEWT-PA21-LEM | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7388 | KL-20210924-5 | 53510703 | Access | 0 | Single Axle Trailer - without pickup - Daily | 30 | 1 | Daily |  | 0 |  |  | 30 | 3.9 | 33.9 | 2021-09-24 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Load and haul stumps, grubbing and trees for crossing of wetlands from D012 to D013 due to no access mats | 7 | D006-D017 | Three Finger Lake | 0 | 2021-09-25 |  | 62 | 2021-10-02 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7388KL-20210924-5Single Axle Trailer - without pickup - Daily130 | KABI LAKE FOREST PRODUCTS LTD7388KL-20210924-5Single Axle Trailer - without pickup - Daily130OEWT-PA21-LEM | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7383 | KL-20210923-5 | 53510703 | Access | 0 | Single Axle Trailer - without pickup - Daily | 30 | 1 | Daily |  | 0 |  |  | 30 | 3.9 | 33.9 | 2021-09-23 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Load and haul stumps, grubbing and trees for crossing of wetlands from D012 to D013 due to no access mats | 7 | D006-D017 | Three Finger Lake | 0 | 2021-09-29 |  | 62 | 2021-10-02 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7383KL-20210923-5Single Axle Trailer - without pickup - Daily130 | KABI LAKE FOREST PRODUCTS LTD7383KL-20210923-5Single Axle Trailer - without pickup - Daily130OEWT-PA21-LEM | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7372 | KL-20210921-3 | 53510703 | Access | 0 | Single Axle Trailer - without pickup - Daily | 30 | 1 | Daily |  | 0 |  |  | 30 | 3.9 | 33.9 | 2021-09-21 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load And haul stumps, grubbing and trees for crossing of wetlands @ D012 | 7 | D006-D017 | Three Finger Lake | 0 | 2021-09-28 |  | 37 | 2021-09-28 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7372KL-20210921-3Single Axle Trailer - without pickup - Daily130 | KABI LAKE FOREST PRODUCTS LTD7372KL-20210921-3Single Axle Trailer - without pickup - Daily130OEWT-PA21-LEM | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7388 | KL-20210924-5 | 53510703 | Access | 0 | ATV - side by side - Daily | 250 | 1 | Daily |  | 0 |  |  | 250 | 32.5 | 282.5 | 2021-09-24 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Load and haul stumps, grubbing and trees for crossing of wetlands from D012 to D013 due to no access mats | 7 | D006-D017 | Three Finger Lake | 0 | 2021-09-25 |  | 62 | 2021-10-02 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7388KL-20210924-5ATV - side by side - Daily1250 | KABI LAKE FOREST PRODUCTS LTD7388KL-20210924-5ATV - side by side - Daily1250OEWT-PA21-LEM | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7383 | KL-20210923-5 | 53510703 | Access | 0 | ATV - side by side - Daily | 250 | 1 | Daily |  | 0 |  |  | 250 | 32.5 | 282.5 | 2021-09-23 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue Load and haul stumps, grubbing and trees for crossing of wetlands from D012 to D013 due to no access mats | 7 | D006-D017 | Three Finger Lake | 0 | 2021-09-29 |  | 62 | 2021-10-02 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7383KL-20210923-5ATV - side by side - Daily1250 | KABI LAKE FOREST PRODUCTS LTD7383KL-20210923-5ATV - side by side - Daily1250OEWT-PA21-LEM | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7372 | KL-20210921-3 | 53510703 | Access | 0 | ATV - side by side - Daily | 250 | 1 | Daily |  | 0 |  |  | 250 | 32.5 | 282.5 | 2021-09-21 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load And haul stumps, grubbing and trees for crossing of wetlands @ D012 | 7 | D006-D017 | Three Finger Lake | 0 | 2021-09-28 |  | 37 | 2021-09-28 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7372KL-20210921-3ATV - side by side - Daily1250 | KABI LAKE FOREST PRODUCTS LTD7372KL-20210921-3ATV - side by side - Daily1250OEWT-PA21-LEM | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7390 | KL-20210925-2 | 53510604 | Access | 0 | Supervisor | 84 | 0.5 | HR |  |  | 84 | 0 | 42 | 5.46 | 47.46 | 2021-09-25 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling | Gravel Hauling | VC7556-2019-016 | 938 OF |  | THIS NEEDS TO BE CHARGED TO WF6 NEYS gravel haul |  | Approved |  |  | Haul Pit run from Cress Pit to Stockpile @ Neys Road WF 6 | 7 | C219-C235 | Neys | 0 | 2021-09-29 |  | 62 | 2021-10-02 | [6 empty] | 06 | KABI LAKE FOREST PRODUCTS LTD7390KL-20210925-2Supervisor0.542 | KABI LAKE FOREST PRODUCTS LTD7390KL-20210925-2Supervisor0.542OEWT-PA21-LEM | Gravel Hauling |  | Gravel Hauling
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7367 | KL-20210920-3 | 53510704 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2021-09-20 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continuing Load and haul existing material from D010 to D011/D012 access for capping | 7 | D006-D017 | Three Finger Lake | 0 | 2021-09-27 |  | 36 | 2021-09-27 | [5 empty] | Mike Lecocq | 07 | KABI LAKE FOREST PRODUCTS LTD7367KL-20210920-3Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD7367KL-20210920-3Supervisor3252OEWT-PA21-LEM | Gravel Hauling |  | Gravel Hauling
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7364 | KL-20210919-3 | 53510704 | Access | 0 | Supervisor | 84 | 4 | HR |  |  | 84 | 0 | 336 | 43.68 | 379.68 | 2021-09-19 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continuing Load and haul existing material from D010 to D011/D012 access for capping | 7 | D006-D017 | Three Finger Lake | 0 | 2021-09-27 |  | 36 | 2021-09-27 | [5 empty] | Mike Lecocq | 07 | KABI LAKE FOREST PRODUCTS LTD7364KL-20210919-3Supervisor4336 | KABI LAKE FOREST PRODUCTS LTD7364KL-20210919-3Supervisor4336OEWT-PA21-LEM | Gravel Hauling |  | Gravel Hauling
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7357 | KL-20210918-3 | 53510704 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2021-09-18 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul existing material from D010 to D011/D012 access for capping | 7 | D006-D017 | Three Finger Lake | 0 | 2021-09-24 |  | 36 | 2021-09-24 | [5 empty] | Mike Lecocq | 07 | KABI LAKE FOREST PRODUCTS LTD7357KL-20210918-3Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD7357KL-20210918-3Supervisor3252OEWT-PA21-LEM | Gravel Hauling |  | Gravel Hauling
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7390 | KL-20210925-2 | 53510604 | Access | 0 | L.O.A. | 244 | 0.86364 | DAY |  | 0 |  |  | 210.7273 | 27.3945 | 238.1218 | 2021-09-25 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling | Gravel Hauling | VC7556-2019-016 | 938 OF |  | THIS NEEDS TO BE CHARGED TO WF6 NEYS gravel haul |  | Approved |  |  | Haul Pit run from Cress Pit to Stockpile @ Neys Road WF 6 | 7 | C219-C235 | Neys | 0 | 2021-09-29 |  | 62 | 2021-10-02 | [6 empty] | 06 | KABI LAKE FOREST PRODUCTS LTD7390KL-20210925-2L.O.A.0.8636364210.7273 | KABI LAKE FOREST PRODUCTS LTD7390KL-20210925-2L.O.A.0.8636364210.7273OEWT-PA21-LEM | Gravel Hauling |  | Gravel Hauling
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7367 | KL-20210920-3 | 53510704 | Access | 0 | L.O.A. | 244 | 0.90909 | DAY |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-09-20 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continuing Load and haul existing material from D010 to D011/D012 access for capping | 7 | D006-D017 | Three Finger Lake | 0 | 2021-09-27 |  | 36 | 2021-09-27 | [5 empty] | Mike Lecocq | 07 | KABI LAKE FOREST PRODUCTS LTD7367KL-20210920-3L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7367KL-20210920-3L.O.A.0.9090909221.8182OEWT-PA21-LEM | Gravel Hauling |  | Gravel Hauling
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7367 | KL-20210920-3 | 53510704 | Access | 0 | L.O.A. | 244 | 0.90909 | DAY |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-09-20 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continuing Load and haul existing material from D010 to D011/D012 access for capping | 7 | D006-D017 | Three Finger Lake | 0 | 2021-09-27 |  | 36 | 2021-09-27 | [5 empty] | Mike Lecocq | 07 | KABI LAKE FOREST PRODUCTS LTD7367KL-20210920-3L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7367KL-20210920-3L.O.A.0.9090909221.8182OEWT-PA21-LEM | Gravel Hauling |  | Gravel Hauling
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7367 | KL-20210920-3 | 53510704 | Access | 0 | L.O.A. | 244 | 0.90909 | DAY |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-09-20 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continuing Load and haul existing material from D010 to D011/D012 access for capping | 7 | D006-D017 | Three Finger Lake | 0 | 2021-09-27 |  | 36 | 2021-09-27 | [5 empty] | Mike Lecocq | 07 | KABI LAKE FOREST PRODUCTS LTD7367KL-20210920-3L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7367KL-20210920-3L.O.A.0.9090909221.8182OEWT-PA21-LEM | Gravel Hauling |  | Gravel Hauling
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7367 | KL-20210920-3 | 53510704 | Access | 0 | L.O.A. | 244 | 0.90909 | DAY |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-09-20 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continuing Load and haul existing material from D010 to D011/D012 access for capping | 7 | D006-D017 | Three Finger Lake | 0 | 2021-09-27 |  | 36 | 2021-09-27 | [5 empty] | Mike Lecocq | 07 | KABI LAKE FOREST PRODUCTS LTD7367KL-20210920-3L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7367KL-20210920-3L.O.A.0.9090909221.8182OEWT-PA21-LEM | Gravel Hauling |  | Gravel Hauling
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7357 | KL-20210918-3 | 53510704 | Access | 0 | L.O.A. | 244 | 0.72727 | DAY |  | 0 |  |  | 177.4545 | 23.0691 | 200.5236 | 2021-09-18 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul existing material from D010 to D011/D012 access for capping | 7 | D006-D017 | Three Finger Lake | 0 | 2021-09-24 |  | 36 | 2021-09-24 | [5 empty] | Mike Lecocq | 07 | KABI LAKE FOREST PRODUCTS LTD7357KL-20210918-3L.O.A.0.7272727177.4545 | KABI LAKE FOREST PRODUCTS LTD7357KL-20210918-3L.O.A.0.7272727177.4545OEWT-PA21-LEM | Gravel Hauling |  | Gravel Hauling
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7357 | KL-20210918-3 | 53510704 | Access | 0 | L.O.A. | 244 | 0.90909 | DAY |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-09-18 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul existing material from D010 to D011/D012 access for capping | 7 | D006-D017 | Three Finger Lake | 0 | 2021-09-24 |  | 36 | 2021-09-24 | [5 empty] | Mike Lecocq | 07 | KABI LAKE FOREST PRODUCTS LTD7357KL-20210918-3L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7357KL-20210918-3L.O.A.0.9090909221.8182OEWT-PA21-LEM | Gravel Hauling |  | Gravel Hauling
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7357 | KL-20210918-3 | 53510704 | Access | 0 | L.O.A. | 244 | 0.90909 | DAY |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-09-18 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul existing material from D010 to D011/D012 access for capping | 7 | D006-D017 | Three Finger Lake | 0 | 2021-09-24 |  | 36 | 2021-09-24 | [5 empty] | Mike Lecocq | 07 | KABI LAKE FOREST PRODUCTS LTD7357KL-20210918-3L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7357KL-20210918-3L.O.A.0.9090909221.8182OEWT-PA21-LEM | Gravel Hauling |  | Gravel Hauling
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7357 | KL-20210918-3 | 53510704 | Access | 0 | L.O.A. | 244 | 0.90909 | DAY |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-09-18 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul existing material from D010 to D011/D012 access for capping | 7 | D006-D017 | Three Finger Lake | 0 | 2021-09-24 |  | 36 | 2021-09-24 | [5 empty] | Mike Lecocq | 07 | KABI LAKE FOREST PRODUCTS LTD7357KL-20210918-3L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7357KL-20210918-3L.O.A.0.9090909221.8182OEWT-PA21-LEM | Gravel Hauling |  | Gravel Hauling
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7364 | KL-20210919-3 | 53510704 | Access | 0 | L.O.A. | 244 | 0.72727 | DAY |  | 0 |  |  | 177.4545 | 23.0691 | 200.5236 | 2021-09-19 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continuing Load and haul existing material from D010 to D011/D012 access for capping | 7 | D006-D017 | Three Finger Lake | 0 | 2021-09-27 |  | 36 | 2021-09-27 | [5 empty] | Mike Lecocq | 07 | KABI LAKE FOREST PRODUCTS LTD7364KL-20210919-3L.O.A.0.7272727177.4545 | KABI LAKE FOREST PRODUCTS LTD7364KL-20210919-3L.O.A.0.7272727177.4545OEWT-PA21-LEM | Gravel Hauling |  | Gravel Hauling
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7364 | KL-20210919-3 | 53510704 | Access | 0 | L.O.A. | 244 | 0.90909 | DAY |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-09-19 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continuing Load and haul existing material from D010 to D011/D012 access for capping | 7 | D006-D017 | Three Finger Lake | 0 | 2021-09-27 |  | 36 | 2021-09-27 | [5 empty] | Mike Lecocq | 07 | KABI LAKE FOREST PRODUCTS LTD7364KL-20210919-3L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7364KL-20210919-3L.O.A.0.9090909221.8182OEWT-PA21-LEM | Gravel Hauling |  | Gravel Hauling
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7364 | KL-20210919-3 | 53510704 | Access | 0 | L.O.A. | 244 | 0.90909 | DAY |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-09-19 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continuing Load and haul existing material from D010 to D011/D012 access for capping | 7 | D006-D017 | Three Finger Lake | 0 | 2021-09-27 |  | 36 | 2021-09-27 | [5 empty] | Mike Lecocq | 07 | KABI LAKE FOREST PRODUCTS LTD7364KL-20210919-3L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7364KL-20210919-3L.O.A.0.9090909221.8182OEWT-PA21-LEM | Gravel Hauling |  | Gravel Hauling
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7364 | KL-20210919-3 | 53510704 | Access | 0 | L.O.A. | 244 | 0.90909 | DAY |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-09-19 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continuing Load and haul existing material from D010 to D011/D012 access for capping | 7 | D006-D017 | Three Finger Lake | 0 | 2021-09-27 |  | 36 | 2021-09-27 | [5 empty] | Mike Lecocq | 07 | KABI LAKE FOREST PRODUCTS LTD7364KL-20210919-3L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7364KL-20210919-3L.O.A.0.9090909221.8182OEWT-PA21-LEM | Gravel Hauling |  | Gravel Hauling
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7390 | KL-20210925-2 | 53510604 | Access | 0 | Pickup 1/2 Ton | 25 | 0.5 | HR | 19 | 0 |  |  | 12.5 | 1.625 | 14.125 | 2021-09-25 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling | Gravel Hauling | VC7556-2019-016 | 938 OF |  | THIS NEEDS TO BE CHARGED TO WF6 NEYS gravel haul |  | Approved |  |  | Haul Pit run from Cress Pit to Stockpile @ Neys Road WF 6 | 7 | C219-C235 | Neys | 0 | 2021-09-29 |  | 62 | 2021-10-02 | [6 empty] | 06 | KABI LAKE FOREST PRODUCTS LTD7390KL-20210925-2Pickup 1/2 Ton0.512.5 | KABI LAKE FOREST PRODUCTS LTD7390KL-20210925-2Pickup 1/2 Ton0.512.5OEWT-PA21-LEM | Gravel Hauling |  | Gravel Hauling
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7367 | KL-20210920-3 | 53510704 | Access | 0 | Pickup 1/2 Ton | 25 | 33 | HR | 19 | 0 |  |  | 825 | 107.25 | 932.25 | 2021-09-20 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continuing Load and haul existing material from D010 to D011/D012 access for capping | 7 | D006-D017 | Three Finger Lake | 0 | 2021-09-27 |  | 36 | 2021-09-27 | [5 empty] | Mike Lecocq | 07 | KABI LAKE FOREST PRODUCTS LTD7367KL-20210920-3Pickup 1/2 Ton33825 | KABI LAKE FOREST PRODUCTS LTD7367KL-20210920-3Pickup 1/2 Ton33825OEWT-PA21-LEM | Gravel Hauling |  | Gravel Hauling
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7357 | KL-20210918-3 | 53510704 | Access | 0 | Pickup 1/2 Ton | 25 | 30.5 | HR | 19 | 0 |  |  | 762.5 | 99.125 | 861.625 | 2021-09-18 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul existing material from D010 to D011/D012 access for capping | 7 | D006-D017 | Three Finger Lake | 0 | 2021-09-24 |  | 36 | 2021-09-24 | [5 empty] | Mike Lecocq | 07 | KABI LAKE FOREST PRODUCTS LTD7357KL-20210918-3Pickup 1/2 Ton30.5762.5 | KABI LAKE FOREST PRODUCTS LTD7357KL-20210918-3Pickup 1/2 Ton30.5762.5OEWT-PA21-LEM | Gravel Hauling |  | Gravel Hauling
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7364 | KL-20210919-3 | 53510704 | Access | 0 | Pickup 1/2 Ton | 25 | 34 | HR | 19 | 0 |  |  | 850 | 110.5 | 960.5 | 2021-09-19 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continuing Load and haul existing material from D010 to D011/D012 access for capping | 7 | D006-D017 | Three Finger Lake | 0 | 2021-09-27 |  | 36 | 2021-09-27 | [5 empty] | Mike Lecocq | 07 | KABI LAKE FOREST PRODUCTS LTD7364KL-20210919-3Pickup 1/2 Ton34850 | KABI LAKE FOREST PRODUCTS LTD7364KL-20210919-3Pickup 1/2 Ton34850OEWT-PA21-LEM | Gravel Hauling |  | Gravel Hauling
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7357 | KL-20210918-3 | 53510704 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 10 | HR | 134 | 0 |  |  | 1780 | 231.4 | 2011.4 | 2021-09-18 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul existing material from D010 to D011/D012 access for capping | 7 | D006-D017 | Three Finger Lake | 0 | 2021-09-24 |  | 36 | 2021-09-24 | [5 empty] | Mike Lecocq | 07 | KABI LAKE FOREST PRODUCTS LTD7357KL-20210918-3CAT 25 ton Articulated Truck101780 | KABI LAKE FOREST PRODUCTS LTD7357KL-20210918-3CAT 25 ton Articulated Truck101780OEWT-PA21-LEM | Gravel Hauling |  | Gravel Hauling
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7367 | KL-20210920-3 | 53510704 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 10 | HR | 134 | 0 |  |  | 1780 | 231.4 | 2011.4 | 2021-09-20 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continuing Load and haul existing material from D010 to D011/D012 access for capping | 7 | D006-D017 | Three Finger Lake | 0 | 2021-09-27 |  | 36 | 2021-09-27 | [5 empty] | Mike Lecocq | 07 | KABI LAKE FOREST PRODUCTS LTD7367KL-20210920-3CAT 25 ton Articulated Truck101780 | KABI LAKE FOREST PRODUCTS LTD7367KL-20210920-3CAT 25 ton Articulated Truck101780OEWT-PA21-LEM | Gravel Hauling |  | Gravel Hauling
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7364 | KL-20210919-3 | 53510704 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 10 | HR | 134 | 0 |  |  | 1780 | 231.4 | 2011.4 | 2021-09-19 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continuing Load and haul existing material from D010 to D011/D012 access for capping | 7 | D006-D017 | Three Finger Lake | 0 | 2021-09-27 |  | 36 | 2021-09-27 | [5 empty] | Mike Lecocq | 07 | KABI LAKE FOREST PRODUCTS LTD7364KL-20210919-3CAT 25 ton Articulated Truck101780 | KABI LAKE FOREST PRODUCTS LTD7364KL-20210919-3CAT 25 ton Articulated Truck101780OEWT-PA21-LEM | Gravel Hauling |  | Gravel Hauling
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7357 | KL-20210918-3 | 53510704 | Access | 0 | CAT 30 ton Articulated Truck | 189 | 7.5 | HR | 142 | 0 |  |  | 1417.5 | 184.275 | 1601.775 | 2021-09-18 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul existing material from D010 to D011/D012 access for capping | 7 | D006-D017 | Three Finger Lake | 0 | 2021-09-24 |  | 36 | 2021-09-24 | [5 empty] | Mike Lecocq | 07 | KABI LAKE FOREST PRODUCTS LTD7357KL-20210918-3CAT 30 ton Articulated Truck7.51417.5 | KABI LAKE FOREST PRODUCTS LTD7357KL-20210918-3CAT 30 ton Articulated Truck7.51417.5OEWT-PA21-LEM | Gravel Hauling |  | Gravel Hauling
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7367 | KL-20210920-3 | 53510704 | Access | 0 | CAT 30 ton Articulated Truck | 189 | 10 | HR | 142 | 0 |  |  | 1890 | 245.7 | 2135.7 | 2021-09-20 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continuing Load and haul existing material from D010 to D011/D012 access for capping | 7 | D006-D017 | Three Finger Lake | 0 | 2021-09-27 |  | 36 | 2021-09-27 | [5 empty] | Mike Lecocq | 07 | KABI LAKE FOREST PRODUCTS LTD7367KL-20210920-3CAT 30 ton Articulated Truck101890 | KABI LAKE FOREST PRODUCTS LTD7367KL-20210920-3CAT 30 ton Articulated Truck101890OEWT-PA21-LEM | Gravel Hauling |  | Gravel Hauling
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7364 | KL-20210919-3 | 53510704 | Access | 0 | CAT 30 ton Articulated Truck | 189 | 10 | HR | 142 | 0 |  |  | 1890 | 245.7 | 2135.7 | 2021-09-19 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continuing Load and haul existing material from D010 to D011/D012 access for capping | 7 | D006-D017 | Three Finger Lake | 0 | 2021-09-27 |  | 36 | 2021-09-27 | [5 empty] | Mike Lecocq | 07 | KABI LAKE FOREST PRODUCTS LTD7364KL-20210919-3CAT 30 ton Articulated Truck101890 | KABI LAKE FOREST PRODUCTS LTD7364KL-20210919-3CAT 30 ton Articulated Truck101890OEWT-PA21-LEM | Gravel Hauling |  | Gravel Hauling
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7357 | KL-20210918-3 | 53510704 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 10 | HR | 147 | 0 |  |  | 1950 | 253.5 | 2203.5 | 2021-09-18 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul existing material from D010 to D011/D012 access for capping | 7 | D006-D017 | Three Finger Lake | 0 | 2021-09-24 |  | 36 | 2021-09-24 | [5 empty] | Mike Lecocq | 07 | KABI LAKE FOREST PRODUCTS LTD7357KL-20210918-330 Ton Excavator c/w Hydraulic Thumb101950 | KABI LAKE FOREST PRODUCTS LTD7357KL-20210918-330 Ton Excavator c/w Hydraulic Thumb101950OEWT-PA21-LEM | Gravel Hauling |  | Gravel Hauling
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7357 | KL-20210918-3 | 53510704 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 10 | HR | 147 | 0 |  |  | 1950 | 253.5 | 2203.5 | 2021-09-18 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load and haul existing material from D010 to D011/D012 access for capping | 7 | D006-D017 | Three Finger Lake | 0 | 2021-09-24 |  | 36 | 2021-09-24 | [5 empty] | Mike Lecocq | 07 | KABI LAKE FOREST PRODUCTS LTD7357KL-20210918-330 Ton Excavator c/w Hydraulic Thumb101950 | KABI LAKE FOREST PRODUCTS LTD7357KL-20210918-330 Ton Excavator c/w Hydraulic Thumb101950OEWT-PA21-LEM | Gravel Hauling |  | Gravel Hauling
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7367 | KL-20210920-3 | 53510704 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 10 | HR | 147 | 0 |  |  | 1950 | 253.5 | 2203.5 | 2021-09-20 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continuing Load and haul existing material from D010 to D011/D012 access for capping | 7 | D006-D017 | Three Finger Lake | 0 | 2021-09-27 |  | 36 | 2021-09-27 | [5 empty] | Mike Lecocq | 07 | KABI LAKE FOREST PRODUCTS LTD7367KL-20210920-330 Ton Excavator c/w Hydraulic Thumb101950 | KABI LAKE FOREST PRODUCTS LTD7367KL-20210920-330 Ton Excavator c/w Hydraulic Thumb101950OEWT-PA21-LEM | Gravel Hauling |  | Gravel Hauling
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7367 | KL-20210920-3 | 53510704 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 10 | HR | 147 | 0 |  |  | 1950 | 253.5 | 2203.5 | 2021-09-20 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continuing Load and haul existing material from D010 to D011/D012 access for capping | 7 | D006-D017 | Three Finger Lake | 0 | 2021-09-27 |  | 36 | 2021-09-27 | [5 empty] | Mike Lecocq | 07 | KABI LAKE FOREST PRODUCTS LTD7367KL-20210920-330 Ton Excavator c/w Hydraulic Thumb101950 | KABI LAKE FOREST PRODUCTS LTD7367KL-20210920-330 Ton Excavator c/w Hydraulic Thumb101950OEWT-PA21-LEM | Gravel Hauling |  | Gravel Hauling
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7364 | KL-20210919-3 | 53510704 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 10 | HR | 147 | 0 |  |  | 1950 | 253.5 | 2203.5 | 2021-09-19 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continuing Load and haul existing material from D010 to D011/D012 access for capping | 7 | D006-D017 | Three Finger Lake | 0 | 2021-09-27 |  | 36 | 2021-09-27 | [5 empty] | Mike Lecocq | 07 | KABI LAKE FOREST PRODUCTS LTD7364KL-20210919-330 Ton Excavator c/w Hydraulic Thumb101950 | KABI LAKE FOREST PRODUCTS LTD7364KL-20210919-330 Ton Excavator c/w Hydraulic Thumb101950OEWT-PA21-LEM | Gravel Hauling |  | Gravel Hauling
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7364 | KL-20210919-3 | 53510704 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 10 | HR | 147 | 0 |  |  | 1950 | 253.5 | 2203.5 | 2021-09-19 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continuing Load and haul existing material from D010 to D011/D012 access for capping | 7 | D006-D017 | Three Finger Lake | 0 | 2021-09-27 |  | 36 | 2021-09-27 | [5 empty] | Mike Lecocq | 07 | KABI LAKE FOREST PRODUCTS LTD7364KL-20210919-330 Ton Excavator c/w Hydraulic Thumb101950 | KABI LAKE FOREST PRODUCTS LTD7364KL-20210919-330 Ton Excavator c/w Hydraulic Thumb101950OEWT-PA21-LEM | Gravel Hauling |  | Gravel Hauling
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7390 | KL-20210925-2 | 53510604 | Access | 0 | Tri-Axle Gravel Dump Truck | 122 | 9.5 | HR | 92 | 0 |  |  | 1159 | 150.67 | 1309.67 | 2021-09-25 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling | Gravel Hauling | VC7556-2019-016 | 938 OF |  | THIS NEEDS TO BE CHARGED TO WF6 NEYS gravel haul |  | Approved |  |  | Haul Pit run from Cress Pit to Stockpile @ Neys Road WF 6 | 7 | C219-C235 | Neys | 0 | 2021-09-29 |  | 62 | 2021-10-02 | [6 empty] | 06 | KABI LAKE FOREST PRODUCTS LTD7390KL-20210925-2Tri-Axle Gravel Dump Truck9.51159 | KABI LAKE FOREST PRODUCTS LTD7390KL-20210925-2Tri-Axle Gravel Dump Truck9.51159OEWT-PA21-LEM | Gravel Hauling |  | Gravel Hauling
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7367 | KL-20210920-3 | 53510704 | Access | 0 | Single Axle Trailer - without pickup - Daily | 30 | 1 | Daily |  | 0 |  |  | 30 | 3.9 | 33.9 | 2021-09-20 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continuing Load and haul existing material from D010 to D011/D012 access for capping | 7 | D006-D017 | Three Finger Lake | 0 | 2021-09-27 |  | 36 | 2021-09-27 | [5 empty] | Mike Lecocq | 07 | KABI LAKE FOREST PRODUCTS LTD7367KL-20210920-3Single Axle Trailer - without pickup - Daily130 | KABI LAKE FOREST PRODUCTS LTD7367KL-20210920-3Single Axle Trailer - without pickup - Daily130OEWT-PA21-LEM | Gravel Hauling |  | Gravel Hauling
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7364 | KL-20210919-3 | 53510704 | Access | 0 | Single Axle Trailer - without pickup - Daily | 30 | 1 | Daily |  | 0 |  |  | 30 | 3.9 | 33.9 | 2021-09-19 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continuing Load and haul existing material from D010 to D011/D012 access for capping | 7 | D006-D017 | Three Finger Lake | 0 | 2021-09-27 |  | 36 | 2021-09-27 | [5 empty] | Mike Lecocq | 07 | KABI LAKE FOREST PRODUCTS LTD7364KL-20210919-3Single Axle Trailer - without pickup - Daily130 | KABI LAKE FOREST PRODUCTS LTD7364KL-20210919-3Single Axle Trailer - without pickup - Daily130OEWT-PA21-LEM | Gravel Hauling |  | Gravel Hauling
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7367 | KL-20210920-3 | 53510704 | Access | 0 | ATV - side by side - Daily | 250 | 1 | Daily |  | 0 |  |  | 250 | 32.5 | 282.5 | 2021-09-20 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continuing Load and haul existing material from D010 to D011/D012 access for capping | 7 | D006-D017 | Three Finger Lake | 0 | 2021-09-27 |  | 36 | 2021-09-27 | [5 empty] | Mike Lecocq | 07 | KABI LAKE FOREST PRODUCTS LTD7367KL-20210920-3ATV - side by side - Daily1250 | KABI LAKE FOREST PRODUCTS LTD7367KL-20210920-3ATV - side by side - Daily1250OEWT-PA21-LEM | Gravel Hauling |  | Gravel Hauling
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7364 | KL-20210919-3 | 53510704 | Access | 0 | ATV - side by side - Daily | 250 | 1 | Daily |  | 0 |  |  | 250 | 32.5 | 282.5 | 2021-09-19 | 0 | OEWT-PA21-LEM | 2021-10-08 | 76 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continuing Load and haul existing material from D010 to D011/D012 access for capping | 7 | D006-D017 | Three Finger Lake | 0 | 2021-09-27 |  | 36 | 2021-09-27 | [5 empty] | Mike Lecocq | 07 | KABI LAKE FOREST PRODUCTS LTD7364KL-20210919-3ATV - side by side - Daily1250 | KABI LAKE FOREST PRODUCTS LTD7364KL-20210919-3ATV - side by side - Daily1250OEWT-PA21-LEM | Gravel Hauling |  | Gravel Hauling
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7403 | KL-20210928-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 5431.28 | Each |  |  |  |  | 5431.28 | 706.0664 | 6137.3464 | 2021-09-28 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working on road maintenance; drainage and fixing bridge approaches to F108 & F109. Rock trucks hauling trees & gravel from 38km to Morin @42km. Supervision of this work as well as Skagen/Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-10-06 |  | 50 | 2021-10-09 | MC-20210928-1 | Excavator 1 shaping, ditching & capping corduroy @42.5km. Excavator 2 loading trees & existing materials to 38km. Rock truck hauling from 38km to 42.5km. |  |  |  | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7403KL-20210928-13rd Party Services5431.285431.28 | KABI LAKE FOREST PRODUCTS LTD7403KL-20210928-13rd Party Services5431.285431.28OEWT-PA22-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7403 | KL-20210928-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 5153.64 | Each |  |  |  |  | 5153.64 | 669.9732 | 5823.6132 | 2021-09-28 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working on road maintenance; drainage and fixing bridge approaches to F108 & F109. Rock trucks hauling trees & gravel from 38km to Morin @42km. Supervision of this work as well as Skagen/Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-10-06 |  | 50 | 2021-10-09 | SFF-20210928-1 | Excavator starting road repairs @36km, loading trees and existing material @38km. Grader finishing grading of Paint Lake Road 2 to 13km. SSF-14384 |  |  |  | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7403KL-20210928-13rd Party Services5153.645153.64 | KABI LAKE FOREST PRODUCTS LTD7403KL-20210928-13rd Party Services5153.645153.64OEWT-PA22-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7397 | KL-20210927-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 6304.92 | Each |  |  |  |  | 6304.92 | 819.6396 | 7124.5596 | 2021-09-27 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Start road maintenance and fix bridge approaches from 49km to 45km. Chapman rock truck hauling gravel from 38km to Morin @43km. Supervision of this work as well as Skagen/Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-10-06 |  | 50 | 2021-10-09 | MC-20210927-1 | Excavator 1 shaping, ditching & capping corduroy @43km. Excavator 2 loading existing materials at 38km. Rock truck hauling from 38km to 42.5km. MC-13164 |  |  |  | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7397KL-20210927-13rd Party Services6304.926304.92 | KABI LAKE FOREST PRODUCTS LTD7397KL-20210927-13rd Party Services6304.926304.92OEWT-PA22-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7397 | KL-20210927-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 4766.37 | Each |  |  |  |  | 4766.37 | 619.6281 | 5385.9981 | 2021-09-27 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Start road maintenance and fix bridge approaches from 49km to 45km. Chapman rock truck hauling gravel from 38km to Morin @43km. Supervision of this work as well as Skagen/Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-10-06 |  | 50 | 2021-10-09 | SFF-20210927-1 | Excavator shaping road from 41 to 36km. Grader continuing grading sections of Paint Lake Road from 5 to 10km. SSF-14383 |  |  |  | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7397KL-20210927-13rd Party Services4766.374766.37 | KABI LAKE FOREST PRODUCTS LTD7397KL-20210927-13rd Party Services4766.374766.37OEWT-PA22-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7393 | KL-20210926-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 6087.73 | Each |  |  |  |  | 6087.73 | 791.4049 | 6879.1349 | 2021-09-26 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load, haul & place trees @16.5km & tracking to 12km float access. Rock truck hauling gravel to grader & drive to Hwy. Chapman rock truck hauling trees & gravel from 38km to Skagen 40.5km. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-10-06 |  | 50 | 2021-10-09 | MC-20210926-1 | Excavator 1 shaping, ditching & spreading gravel @ 42 to 43km. Excavator 2 loading trees at 38km. Rock truck hauling trees from 38km to 40.5km. MC-13163 |  |  |  | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7393KL-20210926-13rd Party Services6087.736087.73 | KABI LAKE FOREST PRODUCTS LTD7393KL-20210926-13rd Party Services6087.736087.73OEWT-PA22-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7393 | KL-20210926-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 4869.96 | Each |  |  |  |  | 4869.96 | 633.0948 | 5503.0548 | 2021-09-26 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load, haul & place trees @16.5km & tracking to 12km float access. Rock truck hauling gravel to grader & drive to Hwy. Chapman rock truck hauling trees & gravel from 38km to Skagen 40.5km. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-10-06 |  | 50 | 2021-10-09 | SFF-20210926-1 | Excavator finishing placing trees @ 40.5km & shaping road. Grader continue grading sections of Paint Lake Road from 5km to 8km, and spread gravel @ 7 & 5 km. SSF-14382 |  |  |  | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7393KL-20210926-13rd Party Services4869.964869.96 | KABI LAKE FOREST PRODUCTS LTD7393KL-20210926-13rd Party Services4869.964869.96OEWT-PA22-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7410 | KL-20210930-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 4575.46 | Each |  |  |  |  | 4575.46 | 594.8098 | 5170.2698 | 2021-09-29 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working on road maintenance, drainage & fixing bridge approaches to F110 & to F104, rock trucks hauling trees & gravel from 38km to Skagen @ 35/34km. Supervision of Morin/Skagen | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-10-07 |  | 50 | 2021-10-09 | MC-20210930-1 | Excavator tracking from 400km to 38km for loading trees & existing material. Rock truck hauling trees & existing material from 38km to 35/34km. MC-13168 |  |  |  | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7410KL-20210930-13rd Party Services4575.464575.46 | KABI LAKE FOREST PRODUCTS LTD7410KL-20210930-13rd Party Services4575.464575.46OEWT-PA22-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7410 | KL-20210930-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2702.74 | Each |  |  |  |  | 2702.74 | 351.3562 | 3054.0962 | 2021-09-29 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working on road maintenance, drainage & fixing bridge approaches to F110 & to F104, rock trucks hauling trees & gravel from 38km to Skagen @ 35/34km. Supervision of Morin/Skagen | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-10-07 |  | 50 | 2021-10-09 | SFF-20210930-1 | Tracking from 38km to 35km, placing trees in low/soft areas & shaping road. SSF-14386 |  |  |  | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7410KL-20210930-13rd Party Services2702.742702.74 | KABI LAKE FOREST PRODUCTS LTD7410KL-20210930-13rd Party Services2702.742702.74OEWT-PA22-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7407 | KL-20210929-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 5267 | Each |  |  |  |  | 5267 | 684.71 | 5951.71 | 2021-09-28 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working on road maintenance; drainage and fixing bridge approac to F111. Rock trucks hauling trees & gravel from 38km to Morin @42km. Supervision including of Skagen/Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-10-06 |  | 50 | 2021-10-09 | MC-20210929-1 | Excavator shaping, ditching, placing trees & capping with existing material @ 42 km. Rock truck hauling trees/existing material from 38km to 42km. MC-13167 |  |  |  | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7407KL-20210929-13rd Party Services52675267 | KABI LAKE FOREST PRODUCTS LTD7407KL-20210929-13rd Party Services52675267OEWT-PA22-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7407 | KL-20210929-1 | 53511012 | Access | 0 | 3rd Party Services | 1 | 2948.42 | Each |  |  |  |  | 2948.42 | 383.2946 | 3331.7146 | 2021-09-28 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working on road maintenance; drainage and fixing bridge approac to F111. Rock trucks hauling trees & gravel from 38km to Morin @42km. Supervision including of Skagen/Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-10-06 |  | 50 | 2021-10-09 | SFF-20210929-1 | Loading trees & existing material on rock trucks @ 38 km. SSF-14385 |  |  |  | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7407KL-20210929-13rd Party Services2948.422948.42 | KABI LAKE FOREST PRODUCTS LTD7407KL-20210929-13rd Party Services2948.422948.42OEWT-PA22-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7410 | KL-20210930-1 | 53511012 | Access | 0 | Supervisor | 84 | 8 | HR |  |  | 84 | 0 | 672 | 87.36 | 759.36 | 2021-09-29 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working on road maintenance, drainage & fixing bridge approaches to F110 & to F104, rock trucks hauling trees & gravel from 38km to Skagen @ 35/34km. Supervision of Morin/Skagen | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-10-07 |  | 50 | 2021-10-09 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7410KL-20210930-1Supervisor8672 | KABI LAKE FOREST PRODUCTS LTD7410KL-20210930-1Supervisor8672OEWT-PA22-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7407 | KL-20210929-1 | 53511012 | Access | 0 | Supervisor | 84 | 7 | HR |  |  | 84 | 0 | 588 | 76.44 | 664.44 | 2021-09-28 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working on road maintenance; drainage and fixing bridge approac to F111. Rock trucks hauling trees & gravel from 38km to Morin @42km. Supervision including of Skagen/Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-10-06 |  | 50 | 2021-10-09 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7407KL-20210929-1Supervisor7588 | KABI LAKE FOREST PRODUCTS LTD7407KL-20210929-1Supervisor7588OEWT-PA22-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7403 | KL-20210928-1 | 53511012 | Access | 0 | Supervisor | 84 | 8 | HR |  |  | 84 | 0 | 672 | 87.36 | 759.36 | 2021-09-28 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working on road maintenance; drainage and fixing bridge approaches to F108 & F109. Rock trucks hauling trees & gravel from 38km to Morin @42km. Supervision of this work as well as Skagen/Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-10-06 |  | 50 | 2021-10-09 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7403KL-20210928-1Supervisor8672 | KABI LAKE FOREST PRODUCTS LTD7403KL-20210928-1Supervisor8672OEWT-PA22-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7397 | KL-20210927-1 | 53511012 | Access | 0 | Supervisor | 84 | 8.5 | HR |  |  | 84 | 0 | 714 | 92.82 | 806.82 | 2021-09-27 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Start road maintenance and fix bridge approaches from 49km to 45km. Chapman rock truck hauling gravel from 38km to Morin @43km. Supervision of this work as well as Skagen/Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-10-06 |  | 50 | 2021-10-09 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7397KL-20210927-1Supervisor8.5714 | KABI LAKE FOREST PRODUCTS LTD7397KL-20210927-1Supervisor8.5714OEWT-PA22-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7393 | KL-20210926-1 | 53511012 | Access | 0 | Supervisor | 84 | 8 | HR |  |  | 84 | 0 | 672 | 87.36 | 759.36 | 2021-09-26 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load, haul & place trees @16.5km & tracking to 12km float access. Rock truck hauling gravel to grader & drive to Hwy. Chapman rock truck hauling trees & gravel from 38km to Skagen 40.5km. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-10-06 |  | 50 | 2021-10-09 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7393KL-20210926-1Supervisor8672 | KABI LAKE FOREST PRODUCTS LTD7393KL-20210926-1Supervisor8672OEWT-PA22-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7410 | KL-20210930-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.54545 | DAY |  | 0 |  |  | 133.0909 | 17.3018 | 150.3927 | 2021-09-29 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working on road maintenance, drainage & fixing bridge approaches to F110 & to F104, rock trucks hauling trees & gravel from 38km to Skagen @ 35/34km. Supervision of Morin/Skagen | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-10-07 |  | 50 | 2021-10-09 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7410KL-20210930-1L.O.A.0.5454545133.0909 | KABI LAKE FOREST PRODUCTS LTD7410KL-20210930-1L.O.A.0.5454545133.0909OEWT-PA22-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7410 | KL-20210930-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | DAY |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-09-29 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working on road maintenance, drainage & fixing bridge approaches to F110 & to F104, rock trucks hauling trees & gravel from 38km to Skagen @ 35/34km. Supervision of Morin/Skagen | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-10-07 |  | 50 | 2021-10-09 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7410KL-20210930-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7410KL-20210930-1L.O.A.0.8181818199.6364OEWT-PA22-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7410 | KL-20210930-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | DAY |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-09-29 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working on road maintenance, drainage & fixing bridge approaches to F110 & to F104, rock trucks hauling trees & gravel from 38km to Skagen @ 35/34km. Supervision of Morin/Skagen | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-10-07 |  | 50 | 2021-10-09 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7410KL-20210930-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7410KL-20210930-1L.O.A.0.8181818199.6364OEWT-PA22-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7410 | KL-20210930-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | DAY |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-09-29 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working on road maintenance, drainage & fixing bridge approaches to F110 & to F104, rock trucks hauling trees & gravel from 38km to Skagen @ 35/34km. Supervision of Morin/Skagen | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-10-07 |  | 50 | 2021-10-09 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7410KL-20210930-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7410KL-20210930-1L.O.A.0.8181818199.6364OEWT-PA22-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7407 | KL-20210929-1 | 53511012 | Access | 0 | L.O.A. | 244 | 1.7727 | DAY |  | 0 |  |  | 432.5455 | 56.2309 | 488.7764 | 2021-09-28 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working on road maintenance; drainage and fixing bridge approac to F111. Rock trucks hauling trees & gravel from 38km to Morin @42km. Supervision including of Skagen/Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-10-06 |  | 50 | 2021-10-09 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7407KL-20210929-1L.O.A.1.7727273432.5455 | KABI LAKE FOREST PRODUCTS LTD7407KL-20210929-1L.O.A.1.7727273432.5455OEWT-PA22-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7407 | KL-20210929-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | DAY |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-09-28 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working on road maintenance; drainage and fixing bridge approac to F111. Rock trucks hauling trees & gravel from 38km to Morin @42km. Supervision including of Skagen/Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-10-06 |  | 50 | 2021-10-09 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7407KL-20210929-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7407KL-20210929-1L.O.A.0.8181818199.6364OEWT-PA22-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7407 | KL-20210929-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | DAY |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-09-28 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working on road maintenance; drainage and fixing bridge approac to F111. Rock trucks hauling trees & gravel from 38km to Morin @42km. Supervision including of Skagen/Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-10-06 |  | 50 | 2021-10-09 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7407KL-20210929-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7407KL-20210929-1L.O.A.0.8181818199.6364OEWT-PA22-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7403 | KL-20210928-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | DAY |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-09-28 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working on road maintenance; drainage and fixing bridge approaches to F108 & F109. Rock trucks hauling trees & gravel from 38km to Morin @42km. Supervision of this work as well as Skagen/Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-10-06 |  | 50 | 2021-10-09 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7403KL-20210928-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7403KL-20210928-1L.O.A.0.8181818199.6364OEWT-PA22-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7403 | KL-20210928-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.90909 | DAY |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-09-28 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working on road maintenance; drainage and fixing bridge approaches to F108 & F109. Rock trucks hauling trees & gravel from 38km to Morin @42km. Supervision of this work as well as Skagen/Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-10-06 |  | 50 | 2021-10-09 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7403KL-20210928-1L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7403KL-20210928-1L.O.A.0.9090909221.8182OEWT-PA22-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7403 | KL-20210928-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | DAY |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-09-28 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working on road maintenance; drainage and fixing bridge approaches to F108 & F109. Rock trucks hauling trees & gravel from 38km to Morin @42km. Supervision of this work as well as Skagen/Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-10-06 |  | 50 | 2021-10-09 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7403KL-20210928-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7403KL-20210928-1L.O.A.0.8181818199.6364OEWT-PA22-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7403 | KL-20210928-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | DAY |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-09-28 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working on road maintenance; drainage and fixing bridge approaches to F108 & F109. Rock trucks hauling trees & gravel from 38km to Morin @42km. Supervision of this work as well as Skagen/Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-10-06 |  | 50 | 2021-10-09 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7403KL-20210928-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7403KL-20210928-1L.O.A.0.8181818199.6364OEWT-PA22-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7397 | KL-20210927-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | DAY |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-09-27 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Start road maintenance and fix bridge approaches from 49km to 45km. Chapman rock truck hauling gravel from 38km to Morin @43km. Supervision of this work as well as Skagen/Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-10-06 |  | 50 | 2021-10-09 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7397KL-20210927-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7397KL-20210927-1L.O.A.0.8181818199.6364OEWT-PA22-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7397 | KL-20210927-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | DAY |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-09-27 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Start road maintenance and fix bridge approaches from 49km to 45km. Chapman rock truck hauling gravel from 38km to Morin @43km. Supervision of this work as well as Skagen/Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-10-06 |  | 50 | 2021-10-09 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7397KL-20210927-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7397KL-20210927-1L.O.A.0.8181818199.6364OEWT-PA22-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7393 | KL-20210926-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.90909 | DAY |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-09-26 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load, haul & place trees @16.5km & tracking to 12km float access. Rock truck hauling gravel to grader & drive to Hwy. Chapman rock truck hauling trees & gravel from 38km to Skagen 40.5km. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-10-06 |  | 50 | 2021-10-09 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7393KL-20210926-1L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7393KL-20210926-1L.O.A.0.9090909221.8182OEWT-PA22-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7393 | KL-20210926-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | DAY |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-09-26 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load, haul & place trees @16.5km & tracking to 12km float access. Rock truck hauling gravel to grader & drive to Hwy. Chapman rock truck hauling trees & gravel from 38km to Skagen 40.5km. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-10-06 |  | 50 | 2021-10-09 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7393KL-20210926-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7393KL-20210926-1L.O.A.0.8181818199.6364OEWT-PA22-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7393 | KL-20210926-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | DAY |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-09-26 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load, haul & place trees @16.5km & tracking to 12km float access. Rock truck hauling gravel to grader & drive to Hwy. Chapman rock truck hauling trees & gravel from 38km to Skagen 40.5km. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-10-06 |  | 50 | 2021-10-09 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7393KL-20210926-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7393KL-20210926-1L.O.A.0.8181818199.6364OEWT-PA22-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7393 | KL-20210926-1 | 53511012 | Access | 0 | L.O.A. | 244 | 0.81818 | DAY |  | 0 |  |  | 199.6364 | 25.9527 | 225.5891 | 2021-09-26 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load, haul & place trees @16.5km & tracking to 12km float access. Rock truck hauling gravel to grader & drive to Hwy. Chapman rock truck hauling trees & gravel from 38km to Skagen 40.5km. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-10-06 |  | 50 | 2021-10-09 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7393KL-20210926-1L.O.A.0.8181818199.6364 | KABI LAKE FOREST PRODUCTS LTD7393KL-20210926-1L.O.A.0.8181818199.6364OEWT-PA22-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7410 | KL-20210930-1 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 32 | HR | 19 | 0 |  |  | 800 | 104 | 904 | 2021-09-29 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working on road maintenance, drainage & fixing bridge approaches to F110 & to F104, rock trucks hauling trees & gravel from 38km to Skagen @ 35/34km. Supervision of Morin/Skagen | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-10-07 |  | 50 | 2021-10-09 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7410KL-20210930-1Pickup 1/2 Ton32800 | KABI LAKE FOREST PRODUCTS LTD7410KL-20210930-1Pickup 1/2 Ton32800OEWT-PA22-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7407 | KL-20210929-1 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 34.5 | HR | 19 | 0 |  |  | 862.5 | 112.125 | 974.625 | 2021-09-28 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working on road maintenance; drainage and fixing bridge approac to F111. Rock trucks hauling trees & gravel from 38km to Morin @42km. Supervision including of Skagen/Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-10-06 |  | 50 | 2021-10-09 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7407KL-20210929-1Pickup 1/2 Ton34.5862.5 | KABI LAKE FOREST PRODUCTS LTD7407KL-20210929-1Pickup 1/2 Ton34.5862.5OEWT-PA22-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7397 | KL-20210927-1 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 17.5 | HR | 19 | 0 |  |  | 437.5 | 56.875 | 494.375 | 2021-09-27 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Start road maintenance and fix bridge approaches from 49km to 45km. Chapman rock truck hauling gravel from 38km to Morin @43km. Supervision of this work as well as Skagen/Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-10-06 |  | 50 | 2021-10-09 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7397KL-20210927-1Pickup 1/2 Ton17.5437.5 | KABI LAKE FOREST PRODUCTS LTD7397KL-20210927-1Pickup 1/2 Ton17.5437.5OEWT-PA22-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7393 | KL-20210926-1 | 53511012 | Access | 0 | Pickup 1/2 Ton | 25 | 36 | HR | 19 | 0 |  |  | 900 | 117 | 1017 | 2021-09-26 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load, haul & place trees @16.5km & tracking to 12km float access. Rock truck hauling gravel to grader & drive to Hwy. Chapman rock truck hauling trees & gravel from 38km to Skagen 40.5km. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-10-06 |  | 50 | 2021-10-09 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7393KL-20210926-1Pickup 1/2 Ton36900 | KABI LAKE FOREST PRODUCTS LTD7393KL-20210926-1Pickup 1/2 Ton36900OEWT-PA22-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7410 | KL-20210930-1 | 53511012 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 9 | HR | 134 | 0 |  |  | 1602 | 208.26 | 1810.26 | 2021-09-29 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working on road maintenance, drainage & fixing bridge approaches to F110 & to F104, rock trucks hauling trees & gravel from 38km to Skagen @ 35/34km. Supervision of Morin/Skagen | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-10-07 |  | 50 | 2021-10-09 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7410KL-20210930-1CAT 25 ton Articulated Truck91602 | KABI LAKE FOREST PRODUCTS LTD7410KL-20210930-1CAT 25 ton Articulated Truck91602OEWT-PA22-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7407 | KL-20210929-1 | 53511012 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 11 | HR | 134 | 0 |  |  | 1958 | 254.54 | 2212.54 | 2021-09-28 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working on road maintenance; drainage and fixing bridge approac to F111. Rock trucks hauling trees & gravel from 38km to Morin @42km. Supervision including of Skagen/Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-10-06 |  | 50 | 2021-10-09 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7407KL-20210929-1CAT 25 ton Articulated Truck111958 | KABI LAKE FOREST PRODUCTS LTD7407KL-20210929-1CAT 25 ton Articulated Truck111958OEWT-PA22-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7403 | KL-20210928-1 | 53511012 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 10 | HR | 134 | 0 |  |  | 1780 | 231.4 | 2011.4 | 2021-09-28 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working on road maintenance; drainage and fixing bridge approaches to F108 & F109. Rock trucks hauling trees & gravel from 38km to Morin @42km. Supervision of this work as well as Skagen/Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-10-06 |  | 50 | 2021-10-09 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7403KL-20210928-1CAT 25 ton Articulated Truck101780 | KABI LAKE FOREST PRODUCTS LTD7403KL-20210928-1CAT 25 ton Articulated Truck101780OEWT-PA22-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7393 | KL-20210926-1 | 53511012 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 9 | HR | 134 | 0 |  |  | 1602 | 208.26 | 1810.26 | 2021-09-26 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load, haul & place trees @16.5km & tracking to 12km float access. Rock truck hauling gravel to grader & drive to Hwy. Chapman rock truck hauling trees & gravel from 38km to Skagen 40.5km. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-10-06 |  | 50 | 2021-10-09 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7393KL-20210926-1CAT 25 ton Articulated Truck91602 | KABI LAKE FOREST PRODUCTS LTD7393KL-20210926-1CAT 25 ton Articulated Truck91602OEWT-PA22-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7410 | KL-20210930-1 | 53511012 | Access | 0 | CAT 30 ton Articulated Truck | 189 | 6 | HR | 142 | 0 |  |  | 1134 | 147.42 | 1281.42 | 2021-09-29 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working on road maintenance, drainage & fixing bridge approaches to F110 & to F104, rock trucks hauling trees & gravel from 38km to Skagen @ 35/34km. Supervision of Morin/Skagen | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-10-07 |  | 50 | 2021-10-09 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7410KL-20210930-1CAT 30 ton Articulated Truck61134 | KABI LAKE FOREST PRODUCTS LTD7410KL-20210930-1CAT 30 ton Articulated Truck61134OEWT-PA22-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7407 | KL-20210929-1 | 53511012 | Access | 0 | CAT 30 ton Articulated Truck | 189 | 8.5 | HR | 142 | 0 |  |  | 1606.5 | 208.845 | 1815.345 | 2021-09-28 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working on road maintenance; drainage and fixing bridge approac to F111. Rock trucks hauling trees & gravel from 38km to Morin @42km. Supervision including of Skagen/Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-10-06 |  | 50 | 2021-10-09 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7407KL-20210929-1CAT 30 ton Articulated Truck8.51606.5 | KABI LAKE FOREST PRODUCTS LTD7407KL-20210929-1CAT 30 ton Articulated Truck8.51606.5OEWT-PA22-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7403 | KL-20210928-1 | 53511012 | Access | 0 | CAT 30 ton Articulated Truck | 189 | 9 | HR | 142 | 0 |  |  | 1701 | 221.13 | 1922.13 | 2021-09-28 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working on road maintenance; drainage and fixing bridge approaches to F108 & F109. Rock trucks hauling trees & gravel from 38km to Morin @42km. Supervision of this work as well as Skagen/Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-10-06 |  | 50 | 2021-10-09 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7403KL-20210928-1CAT 30 ton Articulated Truck91701 | KABI LAKE FOREST PRODUCTS LTD7403KL-20210928-1CAT 30 ton Articulated Truck91701OEWT-PA22-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7393 | KL-20210926-1 | 53511012 | Access | 0 | CAT 30 ton Articulated Truck | 189 | 10 | HR | 142 | 0 |  |  | 1890 | 245.7 | 2135.7 | 2021-09-26 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load, haul & place trees @16.5km & tracking to 12km float access. Rock truck hauling gravel to grader & drive to Hwy. Chapman rock truck hauling trees & gravel from 38km to Skagen 40.5km. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-10-06 |  | 50 | 2021-10-09 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7393KL-20210926-1CAT 30 ton Articulated Truck101890 | KABI LAKE FOREST PRODUCTS LTD7393KL-20210926-1CAT 30 ton Articulated Truck101890OEWT-PA22-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7410 | KL-20210930-1 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 18 | HR | 147 | 0 |  |  | 3510 | 456.3 | 3966.3 | 2021-09-29 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working on road maintenance, drainage & fixing bridge approaches to F110 & to F104, rock trucks hauling trees & gravel from 38km to Skagen @ 35/34km. Supervision of Morin/Skagen | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-10-07 |  | 50 | 2021-10-09 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7410KL-20210930-130 Ton Excavator c/w Hydraulic Thumb183510 | KABI LAKE FOREST PRODUCTS LTD7410KL-20210930-130 Ton Excavator c/w Hydraulic Thumb183510OEWT-PA22-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7407 | KL-20210929-1 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 18 | HR | 147 | 0 |  |  | 3510 | 456.3 | 3966.3 | 2021-09-28 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working on road maintenance; drainage and fixing bridge approac to F111. Rock trucks hauling trees & gravel from 38km to Morin @42km. Supervision including of Skagen/Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-10-06 |  | 50 | 2021-10-09 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7407KL-20210929-130 Ton Excavator c/w Hydraulic Thumb183510 | KABI LAKE FOREST PRODUCTS LTD7407KL-20210929-130 Ton Excavator c/w Hydraulic Thumb183510OEWT-PA22-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7403 | KL-20210928-1 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 18 | HR | 147 | 0 |  |  | 3510 | 456.3 | 3966.3 | 2021-09-28 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working on road maintenance; drainage and fixing bridge approaches to F108 & F109. Rock trucks hauling trees & gravel from 38km to Morin @42km. Supervision of this work as well as Skagen/Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-10-06 |  | 50 | 2021-10-09 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7403KL-20210928-130 Ton Excavator c/w Hydraulic Thumb183510 | KABI LAKE FOREST PRODUCTS LTD7403KL-20210928-130 Ton Excavator c/w Hydraulic Thumb183510OEWT-PA22-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7397 | KL-20210927-1 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 9 | HR | 147 | 0 |  |  | 1755 | 228.15 | 1983.15 | 2021-09-27 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Start road maintenance and fix bridge approaches from 49km to 45km. Chapman rock truck hauling gravel from 38km to Morin @43km. Supervision of this work as well as Skagen/Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-10-06 |  | 50 | 2021-10-09 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7397KL-20210927-130 Ton Excavator c/w Hydraulic Thumb91755 | KABI LAKE FOREST PRODUCTS LTD7397KL-20210927-130 Ton Excavator c/w Hydraulic Thumb91755OEWT-PA22-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7397 | KL-20210927-1 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 9 | HR | 147 | 0 |  |  | 1755 | 228.15 | 1983.15 | 2021-09-27 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Start road maintenance and fix bridge approaches from 49km to 45km. Chapman rock truck hauling gravel from 38km to Morin @43km. Supervision of this work as well as Skagen/Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-10-06 |  | 50 | 2021-10-09 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7397KL-20210927-130 Ton Excavator c/w Hydraulic Thumb91755 | KABI LAKE FOREST PRODUCTS LTD7397KL-20210927-130 Ton Excavator c/w Hydraulic Thumb91755OEWT-PA22-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7393 | KL-20210926-1 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 9 | HR | 147 | 0 |  |  | 1755 | 228.15 | 1983.15 | 2021-09-26 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load, haul & place trees @16.5km & tracking to 12km float access. Rock truck hauling gravel to grader & drive to Hwy. Chapman rock truck hauling trees & gravel from 38km to Skagen 40.5km. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-10-06 |  | 50 | 2021-10-09 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7393KL-20210926-130 Ton Excavator c/w Hydraulic Thumb91755 | KABI LAKE FOREST PRODUCTS LTD7393KL-20210926-130 Ton Excavator c/w Hydraulic Thumb91755OEWT-PA22-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7393 | KL-20210926-1 | 53511012 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 9 | HR | 147 | 0 |  |  | 1755 | 228.15 | 1983.15 | 2021-09-26 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load, haul & place trees @16.5km & tracking to 12km float access. Rock truck hauling gravel to grader & drive to Hwy. Chapman rock truck hauling trees & gravel from 38km to Skagen 40.5km. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-10-06 |  | 50 | 2021-10-09 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7393KL-20210926-130 Ton Excavator c/w Hydraulic Thumb91755 | KABI LAKE FOREST PRODUCTS LTD7393KL-20210926-130 Ton Excavator c/w Hydraulic Thumb91755OEWT-PA22-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7403 | KL-20210928-1 | 53511012 | Access | 0 | Pickup Truck - Truck Only | 25 | 36 | HR | 19 | 0 |  |  | 900 | 117 | 1017 | 2021-09-28 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working on road maintenance; drainage and fixing bridge approaches to F108 & F109. Rock trucks hauling trees & gravel from 38km to Morin @42km. Supervision of this work as well as Skagen/Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-10-06 |  | 50 | 2021-10-09 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7403KL-20210928-1Pickup Truck - Truck Only36900 | KABI LAKE FOREST PRODUCTS LTD7403KL-20210928-1Pickup Truck - Truck Only36900OEWT-PA22-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7410 | KL-20210930-1 | 53511012 | Access | 0 | Single Axle Trailer - without pickup - Daily | 30 | 1 | Daily |  | 0 |  |  | 30 | 3.9 | 33.9 | 2021-09-29 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working on road maintenance, drainage & fixing bridge approaches to F110 & to F104, rock trucks hauling trees & gravel from 38km to Skagen @ 35/34km. Supervision of Morin/Skagen | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-10-07 |  | 50 | 2021-10-09 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7410KL-20210930-1Single Axle Trailer - without pickup - Daily130 | KABI LAKE FOREST PRODUCTS LTD7410KL-20210930-1Single Axle Trailer - without pickup - Daily130OEWT-PA22-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7407 | KL-20210929-1 | 53511012 | Access | 0 | Single Axle Trailer - without pickup - Daily | 30 | 1 | Daily |  | 0 |  |  | 30 | 3.9 | 33.9 | 2021-09-28 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working on road maintenance; drainage and fixing bridge approac to F111. Rock trucks hauling trees & gravel from 38km to Morin @42km. Supervision including of Skagen/Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-10-06 |  | 50 | 2021-10-09 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7407KL-20210929-1Single Axle Trailer - without pickup - Daily130 | KABI LAKE FOREST PRODUCTS LTD7407KL-20210929-1Single Axle Trailer - without pickup - Daily130OEWT-PA22-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7403 | KL-20210928-1 | 53511012 | Access | 0 | Single Axle Trailer - without pickup - Daily | 30 | 1 | Daily |  | 0 |  |  | 30 | 3.9 | 33.9 | 2021-09-28 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working on road maintenance; drainage and fixing bridge approaches to F108 & F109. Rock trucks hauling trees & gravel from 38km to Morin @42km. Supervision of this work as well as Skagen/Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-10-06 |  | 50 | 2021-10-09 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7403KL-20210928-1Single Axle Trailer - without pickup - Daily130 | KABI LAKE FOREST PRODUCTS LTD7403KL-20210928-1Single Axle Trailer - without pickup - Daily130OEWT-PA22-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7397 | KL-20210927-1 | 53511012 | Access | 0 | Single Axle Trailer - without pickup - Daily | 30 | 1 | Daily |  | 0 |  |  | 30 | 3.9 | 33.9 | 2021-09-27 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Start road maintenance and fix bridge approaches from 49km to 45km. Chapman rock truck hauling gravel from 38km to Morin @43km. Supervision of this work as well as Skagen/Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-10-06 |  | 50 | 2021-10-09 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7397KL-20210927-1Single Axle Trailer - without pickup - Daily130 | KABI LAKE FOREST PRODUCTS LTD7397KL-20210927-1Single Axle Trailer - without pickup - Daily130OEWT-PA22-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7393 | KL-20210926-1 | 53511012 | Access | 0 | Single Axle Trailer - without pickup - Daily | 30 | 1 | Daily |  | 0 |  |  | 30 | 3.9 | 33.9 | 2021-09-26 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load, haul & place trees @16.5km & tracking to 12km float access. Rock truck hauling gravel to grader & drive to Hwy. Chapman rock truck hauling trees & gravel from 38km to Skagen 40.5km. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-10-06 |  | 50 | 2021-10-09 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7393KL-20210926-1Single Axle Trailer - without pickup - Daily130 | KABI LAKE FOREST PRODUCTS LTD7393KL-20210926-1Single Axle Trailer - without pickup - Daily130OEWT-PA22-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7410 | KL-20210930-1 | 53511012 | Access | 0 | ATV - side by side - Daily | 250 | 1 | Daily |  | 0 |  |  | 250 | 32.5 | 282.5 | 2021-09-29 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working on road maintenance, drainage & fixing bridge approaches to F110 & to F104, rock trucks hauling trees & gravel from 38km to Skagen @ 35/34km. Supervision of Morin/Skagen | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-10-07 |  | 50 | 2021-10-09 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7410KL-20210930-1ATV - side by side - Daily1250 | KABI LAKE FOREST PRODUCTS LTD7410KL-20210930-1ATV - side by side - Daily1250OEWT-PA22-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7407 | KL-20210929-1 | 53511012 | Access | 0 | ATV - side by side - Daily | 250 | 1 | Daily |  | 0 |  |  | 250 | 32.5 | 282.5 | 2021-09-28 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working on road maintenance; drainage and fixing bridge approac to F111. Rock trucks hauling trees & gravel from 38km to Morin @42km. Supervision including of Skagen/Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-10-06 |  | 50 | 2021-10-09 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7407KL-20210929-1ATV - side by side - Daily1250 | KABI LAKE FOREST PRODUCTS LTD7407KL-20210929-1ATV - side by side - Daily1250OEWT-PA22-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7403 | KL-20210928-1 | 53511012 | Access | 0 | ATV - side by side - Daily | 250 | 1 | Daily |  | 0 |  |  | 250 | 32.5 | 282.5 | 2021-09-28 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavators working on road maintenance; drainage and fixing bridge approaches to F108 & F109. Rock trucks hauling trees & gravel from 38km to Morin @42km. Supervision of this work as well as Skagen/Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-10-06 |  | 50 | 2021-10-09 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7403KL-20210928-1ATV - side by side - Daily1250 | KABI LAKE FOREST PRODUCTS LTD7403KL-20210928-1ATV - side by side - Daily1250OEWT-PA22-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7397 | KL-20210927-1 | 53511012 | Access | 0 | ATV - side by side - Daily | 250 | 1 | Daily |  | 0 |  |  | 250 | 32.5 | 282.5 | 2021-09-27 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Start road maintenance and fix bridge approaches from 49km to 45km. Chapman rock truck hauling gravel from 38km to Morin @43km. Supervision of this work as well as Skagen/Morin | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-10-06 |  | 50 | 2021-10-09 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7397KL-20210927-1ATV - side by side - Daily1250 | KABI LAKE FOREST PRODUCTS LTD7397KL-20210927-1ATV - side by side - Daily1250OEWT-PA22-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7393 | KL-20210926-1 | 53511012 | Access | 0 | ATV - side by side - Daily | 250 | 1 | Daily |  | 0 |  |  | 250 | 32.5 | 282.5 | 2021-09-26 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Load, haul & place trees @16.5km & tracking to 12km float access. Rock truck hauling gravel to grader & drive to Hwy. Chapman rock truck hauling trees & gravel from 38km to Skagen 40.5km. | 10 | F033-F118 | Paint Lake Road 2 | 0 | 2021-10-06 |  | 50 | 2021-10-09 | [5 empty] | Jim Budgell | 10 | KABI LAKE FOREST PRODUCTS LTD7393KL-20210926-1ATV - side by side - Daily1250 | KABI LAKE FOREST PRODUCTS LTD7393KL-20210926-1ATV - side by side - Daily1250OEWT-PA22-Lem |  | WF10-All Season Maintenance | WF10-All Season Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7459 | KL-20211015-3 | 53530701 | Rig/Access Mats | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2021-10-15 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Finish hauling & placing 45 access mats from D009 to D014 soft areas. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-18 |  | 37 | 2021-10-26 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7459KL-20211015-3Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD7459KL-20211015-3Supervisor3252OEWT-PA22-Lem | Rig/Access Mat Handling |  | Rig/Access Mat Handling
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7454 | KL-20211014-2 | 53530701 | Rig/Access Mats | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2021-10-14 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Start hauling & placing access mats from D009 to D014 soft areas. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-18 |  | 37 | 2021-10-26 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7454KL-20211014-2Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD7454KL-20211014-2Supervisor3252OEWT-PA22-Lem | Rig/Access Mat Handling |  | Rig/Access Mat Handling
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7466 | KL-20211017-2 | 53530701 | Rig/Access Mats | 0 | L.O.A. | 244 | 0.18182 | DAY |  | 0 |  |  | 44.3636 | 5.7673 | 50.1309 | 2021-10-17 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float 40 foot rig mat back to Valard Marathon Yard | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-25 |  | 37 | 2021-10-27 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7466KL-20211017-2L.O.A.0.181818244.3636 | KABI LAKE FOREST PRODUCTS LTD7466KL-20211017-2L.O.A.0.181818244.3636OEWT-PA22-Lem | Rig/Access Mat Handling |  | Rig/Access Mat Handling
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7450 | KL-20211013-3 | 53530701 | Rig/Access Mats | 0 | L.O.A. | 244 | 0.18182 | DAY |  | 0 |  |  | 44.3636 | 5.7673 | 50.1309 | 2021-10-13 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float 40 foot rig mat from Pic River West for dragging of Access Mats to D014. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-18 |  | 37 | 2021-10-26 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7450KL-20211013-3L.O.A.0.181818244.3636 | KABI LAKE FOREST PRODUCTS LTD7450KL-20211013-3L.O.A.0.181818244.3636OEWT-PA22-Lem | Rig/Access Mat Handling |  | Rig/Access Mat Handling
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7459 | KL-20211015-3 | 53530701 | Rig/Access Mats | 0 | L.O.A. | 244 | 0.90909 | DAY |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-10-15 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Finish hauling & placing 45 access mats from D009 to D014 soft areas. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-18 |  | 37 | 2021-10-26 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7459KL-20211015-3L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7459KL-20211015-3L.O.A.0.9090909221.8182OEWT-PA22-Lem | Rig/Access Mat Handling |  | Rig/Access Mat Handling
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7459 | KL-20211015-3 | 53530701 | Rig/Access Mats | 0 | L.O.A. | 244 | 0.90909 | DAY |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-10-15 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Finish hauling & placing 45 access mats from D009 to D014 soft areas. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-18 |  | 37 | 2021-10-26 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7459KL-20211015-3L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7459KL-20211015-3L.O.A.0.9090909221.8182OEWT-PA22-Lem | Rig/Access Mat Handling |  | Rig/Access Mat Handling
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7455 | KL-20211014-3 | 53530701 | Rig/Access Mats | 0 | L.O.A. | 244 | 0.31818 | DAY |  | 0 |  |  | 77.6364 | 10.0927 | 87.7291 | 2021-10-14 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float Cat D6 Dozer from Pic River West for hauling of access mats to D014. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-18 |  | 37 | 2021-10-26 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7455KL-20211014-3L.O.A.0.318181877.6364 | KABI LAKE FOREST PRODUCTS LTD7455KL-20211014-3L.O.A.0.318181877.6364OEWT-PA22-Lem | Rig/Access Mat Handling |  | Rig/Access Mat Handling
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7454 | KL-20211014-2 | 53530701 | Rig/Access Mats | 0 | L.O.A. | 244 | 0.5 | DAY |  | 0 |  |  | 122 | 15.86 | 137.86 | 2021-10-14 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Start hauling & placing access mats from D009 to D014 soft areas. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-18 |  | 37 | 2021-10-26 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7454KL-20211014-2L.O.A.0.5122 | KABI LAKE FOREST PRODUCTS LTD7454KL-20211014-2L.O.A.0.5122OEWT-PA22-Lem | Rig/Access Mat Handling |  | Rig/Access Mat Handling
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7454 | KL-20211014-2 | 53530701 | Rig/Access Mats | 0 | L.O.A. | 244 | 0.90909 | DAY |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-10-14 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Start hauling & placing access mats from D009 to D014 soft areas. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-18 |  | 37 | 2021-10-26 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7454KL-20211014-2L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7454KL-20211014-2L.O.A.0.9090909221.8182OEWT-PA22-Lem | Rig/Access Mat Handling |  | Rig/Access Mat Handling
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7459 | KL-20211015-3 | 53530701 | Rig/Access Mats | 0 | Pickup 1/2 Ton | 25 | 23 | HR | 19 | 0 |  |  | 575 | 74.75 | 649.75 | 2021-10-15 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Finish hauling & placing 45 access mats from D009 to D014 soft areas. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-18 |  | 37 | 2021-10-26 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7459KL-20211015-3Pickup 1/2 Ton23575 | KABI LAKE FOREST PRODUCTS LTD7459KL-20211015-3Pickup 1/2 Ton23575OEWT-PA22-Lem | Rig/Access Mat Handling |  | Rig/Access Mat Handling
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7454 | KL-20211014-2 | 53530701 | Rig/Access Mats | 0 | Pickup 1/2 Ton | 25 | 18.5 | HR | 19 | 0 |  |  | 462.5 | 60.125 | 522.625 | 2021-10-14 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Start hauling & placing access mats from D009 to D014 soft areas. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-18 |  | 37 | 2021-10-26 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7454KL-20211014-2Pickup 1/2 Ton18.5462.5 | KABI LAKE FOREST PRODUCTS LTD7454KL-20211014-2Pickup 1/2 Ton18.5462.5OEWT-PA22-Lem | Rig/Access Mat Handling |  | Rig/Access Mat Handling
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7459 | KL-20211015-3 | 53530701 | Rig/Access Mats | 0 | CAT D6 - LPG | 179 | 10 | HR | 135 | 0 |  |  | 1790 | 232.7 | 2022.7 | 2021-10-15 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Finish hauling & placing 45 access mats from D009 to D014 soft areas. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-18 |  | 37 | 2021-10-26 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7459KL-20211015-3CAT D6 - LPG101790 | KABI LAKE FOREST PRODUCTS LTD7459KL-20211015-3CAT D6 - LPG101790OEWT-PA22-Lem | Rig/Access Mat Handling |  | Rig/Access Mat Handling
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7454 | KL-20211014-2 | 53530701 | Rig/Access Mats | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 15.5 | HR | 147 | 0 |  |  | 3022.5 | 392.925 | 3415.425 | 2021-10-14 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Start hauling & placing access mats from D009 to D014 soft areas. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-18 |  | 37 | 2021-10-26 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7454KL-20211014-230 Ton Excavator c/w Hydraulic Thumb15.53022.5 | KABI LAKE FOREST PRODUCTS LTD7454KL-20211014-230 Ton Excavator c/w Hydraulic Thumb15.53022.5OEWT-PA22-Lem | Rig/Access Mat Handling |  | Rig/Access Mat Handling
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7459 | KL-20211015-3 | 53530701 | Rig/Access Mats | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 10 | HR | 147 | 0 |  |  | 1950 | 253.5 | 2203.5 | 2021-10-15 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Finish hauling & placing 45 access mats from D009 to D014 soft areas. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-18 |  | 37 | 2021-10-26 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7459KL-20211015-330 Ton Excavator c/w Hydraulic Thumb101950 | KABI LAKE FOREST PRODUCTS LTD7459KL-20211015-330 Ton Excavator c/w Hydraulic Thumb101950OEWT-PA22-Lem | Rig/Access Mat Handling |  | Rig/Access Mat Handling
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7466 | KL-20211017-2 | 53530701 | Rig/Access Mats | 0 | Float Truck - 60 ton | 188 | 2 | HR | 141 | 0 |  |  | 376 | 48.88 | 424.88 | 2021-10-17 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float 40 foot rig mat back to Valard Marathon Yard | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-25 |  | 37 | 2021-10-27 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7466KL-20211017-2Float Truck - 60 ton2376 | KABI LAKE FOREST PRODUCTS LTD7466KL-20211017-2Float Truck - 60 ton2376OEWT-PA22-Lem | Rig/Access Mat Handling |  | Rig/Access Mat Handling
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7450 | KL-20211013-3 | 53530701 | Rig/Access Mats | 0 | Float Truck - 60 ton | 188 | 2 | HR | 141 | 0 |  |  | 376 | 48.88 | 424.88 | 2021-10-13 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float 40 foot rig mat from Pic River West for dragging of Access Mats to D014. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-18 |  | 37 | 2021-10-26 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7450KL-20211013-3Float Truck - 60 ton2376 | KABI LAKE FOREST PRODUCTS LTD7450KL-20211013-3Float Truck - 60 ton2376OEWT-PA22-Lem | Rig/Access Mat Handling |  | Rig/Access Mat Handling
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7455 | KL-20211014-3 | 53530701 | Rig/Access Mats | 0 | Float Truck - 60 ton | 188 | 3.5 | HR | 141 | 0 |  |  | 658 | 85.54 | 743.54 | 2021-10-14 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Rig/Access Mat Handling |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Float Cat D6 Dozer from Pic River West for hauling of access mats to D014. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-18 |  | 37 | 2021-10-26 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7455KL-20211014-3Float Truck - 60 ton3.5658 | KABI LAKE FOREST PRODUCTS LTD7455KL-20211014-3Float Truck - 60 ton3.5658OEWT-PA22-Lem | Rig/Access Mat Handling |  | Rig/Access Mat Handling
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7418 | KL-20211001-5 | 53510703 | Access | 0 | Labourer | 65 | 2 | HR |  |  | 65 | 0 | 130 | 16.9 | 146.9 | 2021-10-01 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading & hauling existing material for capping of wetland @ D-012 to D-013.Labourer delivering GEO from Marathon yard. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-08 |  | 62 | 2021-10-09 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7418KL-20211001-5Labourer2130 | KABI LAKE FOREST PRODUCTS LTD7418KL-20211001-5Labourer2130OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7404 | KL-20210928-2 | 53510703 | Access | 0 | Labourer | 65 | 6 | HR |  |  | 65 | 0 | 390 | 50.7 | 440.7 | 2021-09-28 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading & hauling stumps, grubbing. Hauling trees/existing material for crossing of Wetland @D012 to D013. Excavator/labourers delivering 6 rolls of GEO from Marathon yard. | 7 | D009-D017 | Three Finger Lake | 0 | 2021-10-06 |  | 62 | 2021-10-09 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7404KL-20210928-2Labourer6390 | KABI LAKE FOREST PRODUCTS LTD7404KL-20210928-2Labourer6390OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7423 | KL-20211003-3 | 53510703 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2021-10-03 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working on drainage & shaping access from D011 to D013. Piling material up for capping. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-08 |  | 37 | 2021-10-09 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7423KL-20211003-3Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD7423KL-20211003-3Supervisor2168OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7418 | KL-20211001-5 | 53510703 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2021-10-01 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading & hauling existing material for capping of wetland @ D-012 to D-013.Labourer delivering GEO from Marathon yard. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-08 |  | 62 | 2021-10-09 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7418KL-20211001-5Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD7418KL-20211001-5Supervisor3252OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7412 | KL-20210930-3 | 53510703 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2021-09-30 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading & hauling existing material for capping of wetland @ D-012 to D-013. Excavator laying geo. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-07 |  | 62 | 2021-10-09 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7412KL-20210930-3Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD7412KL-20210930-3Supervisor2168OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7408 | KL-20210929-2 | 53510703 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2021-09-29 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading & hauling stumps, grubbing & capping with existing material for crossing of wetland @ D012 to D013. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-07 |  | 62 | 2021-10-09 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7408KL-20210929-2Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD7408KL-20210929-2Supervisor2168OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7404 | KL-20210928-2 | 53510703 | Access | 0 | Supervisor | 84 | 4 | HR |  |  | 84 | 0 | 336 | 43.68 | 379.68 | 2021-09-28 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading & hauling stumps, grubbing. Hauling trees/existing material for crossing of Wetland @D012 to D013. Excavator/labourers delivering 6 rolls of GEO from Marathon yard. | 7 | D009-D017 | Three Finger Lake | 0 | 2021-10-06 |  | 62 | 2021-10-09 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7404KL-20210928-2Supervisor4336 | KABI LAKE FOREST PRODUCTS LTD7404KL-20210928-2Supervisor4336OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7398 | KL-20210927-2 | 53510703 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2021-09-27 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading & hauling stumps, grubbing & trees for crossing of wetland D012 to D013. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-06 |  | 62 | 2021-10-09 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7398KL-20210927-2Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD7398KL-20210927-2Supervisor3252OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7438 | KL-20211008-3 | 53510703 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2021-10-08 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Shape road, ditch & add material in low areas @ D012/D013. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-15 |  | 37 | 2021-10-26 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7438KL-20211008-3Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD7438KL-20211008-3Supervisor2168OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7436 | KL-20211007-3 | 53510703 | Access | 0 | Supervisor | 84 | 3 | HR |  |  | 84 | 0 | 252 | 32.76 | 284.76 | 2021-10-07 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Finish loading and hauling existing material from D010 for road repairs out to D011 | 7 | D009-D017 | Three Finger Lake | 0 | 2021-10-15 |  | 37 | 2021-10-26 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7436KL-20211007-3Supervisor3252 | KABI LAKE FOREST PRODUCTS LTD7436KL-20211007-3Supervisor3252OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7433 | KL-20211006-3 | 53510703 | Access | 0 | Supervisor | 84 | 3.5 | HR |  |  | 84 | 0 | 294 | 38.22 | 332.22 | 2021-10-06 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Finish loading and hauling existing material from D010 for capping of wetlands @ D012 and start road repairs out to D011 | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-15 |  | 63 | 2021-10-15 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7433KL-20211006-3Supervisor3.5294 | KABI LAKE FOREST PRODUCTS LTD7433KL-20211006-3Supervisor3.5294OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7429 | KL-20211005-3 | 53510703 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2021-10-05 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading & hauling existing material from D-010 for capping of wetland @ D012. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-08 |  | 37 | 2021-10-26 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7429KL-20211005-3Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD7429KL-20211005-3Supervisor2168OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7426 | KL-20211004-3 | 53510703 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2021-10-04 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading & hauling existing material for capping of wetland @ D012 to D013. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-08 |  | 37 | 2021-10-09 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7426KL-20211004-3Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD7426KL-20211004-3Supervisor2168OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7438 | KL-20211008-3 | 53510703 | Access | 0 | L.O.A. | 244 | 0.77273 | DAY |  | 0 |  |  | 188.5455 | 24.5109 | 213.0564 | 2021-10-08 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Shape road, ditch & add material in low areas @ D012/D013. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-15 |  | 37 | 2021-10-26 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7438KL-20211008-3L.O.A.0.7727273188.5455 | KABI LAKE FOREST PRODUCTS LTD7438KL-20211008-3L.O.A.0.7727273188.5455OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7436 | KL-20211007-3 | 53510703 | Access | 0 | L.O.A. | 244 | 0.59091 | DAY |  | 0 |  |  | 144.1818 | 18.7436 | 162.9254 | 2021-10-07 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Finish loading and hauling existing material from D010 for road repairs out to D011 | 7 | D009-D017 | Three Finger Lake | 0 | 2021-10-15 |  | 37 | 2021-10-26 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7436KL-20211007-3L.O.A.0.5909091144.1818 | KABI LAKE FOREST PRODUCTS LTD7436KL-20211007-3L.O.A.0.5909091144.1818OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7436 | KL-20211007-3 | 53510703 | Access | 0 | L.O.A. | 244 | 0.59091 | DAY |  | 0 |  |  | 144.1818 | 18.7436 | 162.9254 | 2021-10-07 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Finish loading and hauling existing material from D010 for road repairs out to D011 | 7 | D009-D017 | Three Finger Lake | 0 | 2021-10-15 |  | 37 | 2021-10-26 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7436KL-20211007-3L.O.A.0.5909091144.1818 | KABI LAKE FOREST PRODUCTS LTD7436KL-20211007-3L.O.A.0.5909091144.1818OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7436 | KL-20211007-3 | 53510703 | Access | 0 | L.O.A. | 244 | 0.95455 | DAY |  | 0 |  |  | 232.9091 | 30.2782 | 263.1873 | 2021-10-07 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Finish loading and hauling existing material from D010 for road repairs out to D011 | 7 | D009-D017 | Three Finger Lake | 0 | 2021-10-15 |  | 37 | 2021-10-26 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7436KL-20211007-3L.O.A.0.9545455232.9091 | KABI LAKE FOREST PRODUCTS LTD7436KL-20211007-3L.O.A.0.9545455232.9091OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7433 | KL-20211006-3 | 53510703 | Access | 0 | L.O.A. | 244 | 0.90909 | DAY |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-10-06 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Finish loading and hauling existing material from D010 for capping of wetlands @ D012 and start road repairs out to D011 | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-15 |  | 63 | 2021-10-15 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7433KL-20211006-3L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7433KL-20211006-3L.O.A.0.9090909221.8182OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7433 | KL-20211006-3 | 53510703 | Access | 0 | L.O.A. | 244 | 0.90909 | DAY |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-10-06 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Finish loading and hauling existing material from D010 for capping of wetlands @ D012 and start road repairs out to D011 | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-15 |  | 63 | 2021-10-15 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7433KL-20211006-3L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7433KL-20211006-3L.O.A.0.9090909221.8182OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7433 | KL-20211006-3 | 53510703 | Access | 0 | L.O.A. | 244 | 0.90909 | DAY |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-10-06 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Finish loading and hauling existing material from D010 for capping of wetlands @ D012 and start road repairs out to D011 | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-15 |  | 63 | 2021-10-15 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7433KL-20211006-3L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7433KL-20211006-3L.O.A.0.9090909221.8182OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7423 | KL-20211003-3 | 53510703 | Access | 0 | L.O.A. | 244 | 0.95455 | DAY |  | 0 |  |  | 232.9091 | 30.2782 | 263.1873 | 2021-10-03 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working on drainage & shaping access from D011 to D013. Piling material up for capping. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-08 |  | 37 | 2021-10-09 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7423KL-20211003-3L.O.A.0.9545455232.9091 | KABI LAKE FOREST PRODUCTS LTD7423KL-20211003-3L.O.A.0.9545455232.9091OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7418 | KL-20211001-5 | 53510703 | Access | 0 | L.O.A. | 244 | 0.95455 | DAY |  |  |  |  | 232.9091 | 30.2782 | 263.1873 | 2021-10-01 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading & hauling existing material for capping of wetland @ D-012 to D-013.Labourer delivering GEO from Marathon yard. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-08 |  | 62 | 2021-10-09 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7418KL-20211001-5L.O.A.0.9545455232.9091 | KABI LAKE FOREST PRODUCTS LTD7418KL-20211001-5L.O.A.0.9545455232.9091OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7418 | KL-20211001-5 | 53510703 | Access | 0 | L.O.A. | 244 | 0.95455 | DAY |  | 0 |  |  | 232.9091 | 30.2782 | 263.1873 | 2021-10-01 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading & hauling existing material for capping of wetland @ D-012 to D-013.Labourer delivering GEO from Marathon yard. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-08 |  | 62 | 2021-10-09 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7418KL-20211001-5L.O.A.0.9545455232.9091 | KABI LAKE FOREST PRODUCTS LTD7418KL-20211001-5L.O.A.0.9545455232.9091OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7418 | KL-20211001-5 | 53510703 | Access | 0 | L.O.A. | 244 | 0.95455 | DAY |  | 0 |  |  | 232.9091 | 30.2782 | 263.1873 | 2021-10-01 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading & hauling existing material for capping of wetland @ D-012 to D-013.Labourer delivering GEO from Marathon yard. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-08 |  | 62 | 2021-10-09 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7418KL-20211001-5L.O.A.0.9545455232.9091 | KABI LAKE FOREST PRODUCTS LTD7418KL-20211001-5L.O.A.0.9545455232.9091OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7412 | KL-20210930-3 | 53510703 | Access | 0 | L.O.A. | 244 | 0.90909 | DAY |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-09-30 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading & hauling existing material for capping of wetland @ D-012 to D-013. Excavator laying geo. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-07 |  | 62 | 2021-10-09 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7412KL-20210930-3L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7412KL-20210930-3L.O.A.0.9090909221.8182OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7412 | KL-20210930-3 | 53510703 | Access | 0 | L.O.A. | 244 | 0.90909 | DAY |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-09-30 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading & hauling existing material for capping of wetland @ D-012 to D-013. Excavator laying geo. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-07 |  | 62 | 2021-10-09 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7412KL-20210930-3L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7412KL-20210930-3L.O.A.0.9090909221.8182OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7412 | KL-20210930-3 | 53510703 | Access | 0 | L.O.A. | 244 | 0.90909 | DAY |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-09-30 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading & hauling existing material for capping of wetland @ D-012 to D-013. Excavator laying geo. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-07 |  | 62 | 2021-10-09 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7412KL-20210930-3L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7412KL-20210930-3L.O.A.0.9090909221.8182OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7408 | KL-20210929-2 | 53510703 | Access | 0 | L.O.A. | 244 | 0.90909 | DAY |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-09-29 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading & hauling stumps, grubbing & capping with existing material for crossing of wetland @ D012 to D013. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-07 |  | 62 | 2021-10-09 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7408KL-20210929-2L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7408KL-20210929-2L.O.A.0.9090909221.8182OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7408 | KL-20210929-2 | 53510703 | Access | 0 | L.O.A. | 244 | 0.90909 | DAY |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-09-29 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading & hauling stumps, grubbing & capping with existing material for crossing of wetland @ D012 to D013. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-07 |  | 62 | 2021-10-09 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7408KL-20210929-2L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7408KL-20210929-2L.O.A.0.9090909221.8182OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7408 | KL-20210929-2 | 53510703 | Access | 0 | L.O.A. | 244 | 0.90909 | DAY |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-09-29 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading & hauling stumps, grubbing & capping with existing material for crossing of wetland @ D012 to D013. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-07 |  | 62 | 2021-10-09 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7408KL-20210929-2L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7408KL-20210929-2L.O.A.0.9090909221.8182OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7404 | KL-20210928-2 | 53510703 | Access | 0 | L.O.A. | 244 | 0.90909 | DAY |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-09-28 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading & hauling stumps, grubbing. Hauling trees/existing material for crossing of Wetland @D012 to D013. Excavator/labourers delivering 6 rolls of GEO from Marathon yard. | 7 | D009-D017 | Three Finger Lake | 0 | 2021-10-06 |  | 62 | 2021-10-09 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7404KL-20210928-2L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7404KL-20210928-2L.O.A.0.9090909221.8182OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7404 | KL-20210928-2 | 53510703 | Access | 0 | L.O.A. | 244 | 0.90909 | DAY |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-09-28 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading & hauling stumps, grubbing. Hauling trees/existing material for crossing of Wetland @D012 to D013. Excavator/labourers delivering 6 rolls of GEO from Marathon yard. | 7 | D009-D017 | Three Finger Lake | 0 | 2021-10-06 |  | 62 | 2021-10-09 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7404KL-20210928-2L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7404KL-20210928-2L.O.A.0.9090909221.8182OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7404 | KL-20210928-2 | 53510703 | Access | 0 | L.O.A. | 244 | 0.90909 | DAY |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-09-28 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading & hauling stumps, grubbing. Hauling trees/existing material for crossing of Wetland @D012 to D013. Excavator/labourers delivering 6 rolls of GEO from Marathon yard. | 7 | D009-D017 | Three Finger Lake | 0 | 2021-10-06 |  | 62 | 2021-10-09 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7404KL-20210928-2L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7404KL-20210928-2L.O.A.0.9090909221.8182OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7398 | KL-20210927-2 | 53510703 | Access | 0 | L.O.A. | 244 | 0.90909 | DAY |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-09-27 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading & hauling stumps, grubbing & trees for crossing of wetland D012 to D013. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-06 |  | 62 | 2021-10-09 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7398KL-20210927-2L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7398KL-20210927-2L.O.A.0.9090909221.8182OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7398 | KL-20210927-2 | 53510703 | Access | 0 | L.O.A. | 244 | 0.90909 | DAY |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-09-27 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading & hauling stumps, grubbing & trees for crossing of wetland D012 to D013. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-06 |  | 62 | 2021-10-09 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7398KL-20210927-2L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7398KL-20210927-2L.O.A.0.9090909221.8182OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7398 | KL-20210927-2 | 53510703 | Access | 0 | L.O.A. | 244 | 0.90909 | DAY |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-09-27 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading & hauling stumps, grubbing & trees for crossing of wetland D012 to D013. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-06 |  | 62 | 2021-10-09 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7398KL-20210927-2L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7398KL-20210927-2L.O.A.0.9090909221.8182OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7429 | KL-20211005-3 | 53510703 | Access | 0 | L.O.A. | 244 | 0.90909 | DAY |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-10-05 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading & hauling existing material from D-010 for capping of wetland @ D012. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-08 |  | 37 | 2021-10-26 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7429KL-20211005-3L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7429KL-20211005-3L.O.A.0.9090909221.8182OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7429 | KL-20211005-3 | 53510703 | Access | 0 | L.O.A. | 244 | 0.90909 | DAY |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-10-05 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading & hauling existing material from D-010 for capping of wetland @ D012. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-08 |  | 37 | 2021-10-26 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7429KL-20211005-3L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7429KL-20211005-3L.O.A.0.9090909221.8182OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7429 | KL-20211005-3 | 53510703 | Access | 0 | L.O.A. | 244 | 0.90909 | DAY |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-10-05 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading & hauling existing material from D-010 for capping of wetland @ D012. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-08 |  | 37 | 2021-10-26 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7429KL-20211005-3L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7429KL-20211005-3L.O.A.0.9090909221.8182OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7426 | KL-20211004-3 | 53510703 | Access | 0 | L.O.A. | 244 | 0.90909 | DAY |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-10-04 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading & hauling existing material for capping of wetland @ D012 to D013. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-08 |  | 37 | 2021-10-09 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7426KL-20211004-3L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7426KL-20211004-3L.O.A.0.9090909221.8182OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7426 | KL-20211004-3 | 53510703 | Access | 0 | L.O.A. | 244 | 0.90909 | DAY |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-10-04 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading & hauling existing material for capping of wetland @ D012 to D013. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-08 |  | 37 | 2021-10-09 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7426KL-20211004-3L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7426KL-20211004-3L.O.A.0.9090909221.8182OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7426 | KL-20211004-3 | 53510703 | Access | 0 | L.O.A. | 244 | 0.90909 | DAY |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-10-04 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading & hauling existing material for capping of wetland @ D012 to D013. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-08 |  | 37 | 2021-10-09 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7426KL-20211004-3L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7426KL-20211004-3L.O.A.0.9090909221.8182OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7438 | KL-20211008-3 | 53510703 | Access | 0 | Pickup 1/2 Ton | 25 | 10.5 | HR | 19 | 0 |  |  | 262.5 | 34.125 | 296.625 | 2021-10-08 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Shape road, ditch & add material in low areas @ D012/D013. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-15 |  | 37 | 2021-10-26 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7438KL-20211008-3Pickup 1/2 Ton10.5262.5 | KABI LAKE FOREST PRODUCTS LTD7438KL-20211008-3Pickup 1/2 Ton10.5262.5OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7436 | KL-20211007-3 | 53510703 | Access | 0 | Pickup 1/2 Ton | 25 | 19.5 | HR | 19 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2021-10-07 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Finish loading and hauling existing material from D010 for road repairs out to D011 | 7 | D009-D017 | Three Finger Lake | 0 | 2021-10-15 |  | 37 | 2021-10-26 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7436KL-20211007-3Pickup 1/2 Ton19.5487.5 | KABI LAKE FOREST PRODUCTS LTD7436KL-20211007-3Pickup 1/2 Ton19.5487.5OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7433 | KL-20211006-3 | 53510703 | Access | 0 | Pickup 1/2 Ton | 25 | 23.5 | HR | 19 | 0 |  |  | 587.5 | 76.375 | 663.875 | 2021-10-06 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Finish loading and hauling existing material from D010 for capping of wetlands @ D012 and start road repairs out to D011 | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-15 |  | 63 | 2021-10-15 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7433KL-20211006-3Pickup 1/2 Ton23.5587.5 | KABI LAKE FOREST PRODUCTS LTD7433KL-20211006-3Pickup 1/2 Ton23.5587.5OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7423 | KL-20211003-3 | 53510703 | Access | 0 | Pickup 1/2 Ton | 25 | 12 | HR | 19 | 0 |  |  | 300 | 39 | 339 | 2021-10-03 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working on drainage & shaping access from D011 to D013. Piling material up for capping. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-08 |  | 37 | 2021-10-09 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7423KL-20211003-3Pickup 1/2 Ton12300 | KABI LAKE FOREST PRODUCTS LTD7423KL-20211003-3Pickup 1/2 Ton12300OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7418 | KL-20211001-5 | 53510703 | Access | 0 | Pickup 1/2 Ton | 25 | 25 | HR | 19 | 0 |  |  | 625 | 81.25 | 706.25 | 2021-10-01 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading & hauling existing material for capping of wetland @ D-012 to D-013.Labourer delivering GEO from Marathon yard. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-08 |  | 62 | 2021-10-09 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7418KL-20211001-5Pickup 1/2 Ton25625 | KABI LAKE FOREST PRODUCTS LTD7418KL-20211001-5Pickup 1/2 Ton25625OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7412 | KL-20210930-3 | 53510703 | Access | 0 | Pickup 1/2 Ton | 25 | 22 | HR | 19 | 0 |  |  | 550 | 71.5 | 621.5 | 2021-09-30 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading & hauling existing material for capping of wetland @ D-012 to D-013. Excavator laying geo. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-07 |  | 62 | 2021-10-09 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7412KL-20210930-3Pickup 1/2 Ton22550 | KABI LAKE FOREST PRODUCTS LTD7412KL-20210930-3Pickup 1/2 Ton22550OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7408 | KL-20210929-2 | 53510703 | Access | 0 | Pickup 1/2 Ton | 25 | 22 | HR | 19 | 0 |  |  | 550 | 71.5 | 621.5 | 2021-09-29 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading & hauling stumps, grubbing & capping with existing material for crossing of wetland @ D012 to D013. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-07 |  | 62 | 2021-10-09 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7408KL-20210929-2Pickup 1/2 Ton22550 | KABI LAKE FOREST PRODUCTS LTD7408KL-20210929-2Pickup 1/2 Ton22550OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7404 | KL-20210928-2 | 53510703 | Access | 0 | Pickup 1/2 Ton | 25 | 27 | HR | 19 | 0 |  |  | 675 | 87.75 | 762.75 | 2021-09-28 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading & hauling stumps, grubbing. Hauling trees/existing material for crossing of Wetland @D012 to D013. Excavator/labourers delivering 6 rolls of GEO from Marathon yard. | 7 | D009-D017 | Three Finger Lake | 0 | 2021-10-06 |  | 62 | 2021-10-09 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7404KL-20210928-2Pickup 1/2 Ton27675 | KABI LAKE FOREST PRODUCTS LTD7404KL-20210928-2Pickup 1/2 Ton27675OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7398 | KL-20210927-2 | 53510703 | Access | 0 | Pickup 1/2 Ton | 25 | 23 | HR | 19 | 0 |  |  | 575 | 74.75 | 649.75 | 2021-09-27 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading & hauling stumps, grubbing & trees for crossing of wetland D012 to D013. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-06 |  | 62 | 2021-10-09 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7398KL-20210927-2Pickup 1/2 Ton23575 | KABI LAKE FOREST PRODUCTS LTD7398KL-20210927-2Pickup 1/2 Ton23575OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7429 | KL-20211005-3 | 53510703 | Access | 0 | Pickup 1/2 Ton | 25 | 22 | HR | 19 | 0 |  |  | 550 | 71.5 | 621.5 | 2021-10-05 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading & hauling existing material from D-010 for capping of wetland @ D012. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-08 |  | 37 | 2021-10-26 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7429KL-20211005-3Pickup 1/2 Ton22550 | KABI LAKE FOREST PRODUCTS LTD7429KL-20211005-3Pickup 1/2 Ton22550OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7436 | KL-20211007-3 | 53510703 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 6.5 | HR | 134 | 0 |  |  | 1157 | 150.41 | 1307.41 | 2021-10-07 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Finish loading and hauling existing material from D010 for road repairs out to D011 | 7 | D009-D017 | Three Finger Lake | 0 | 2021-10-15 |  | 37 | 2021-10-26 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7436KL-20211007-3CAT 25 ton Articulated Truck6.51157 | KABI LAKE FOREST PRODUCTS LTD7436KL-20211007-3CAT 25 ton Articulated Truck6.51157OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7433 | KL-20211006-3 | 53510703 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 10 | HR | 134 | 0 |  |  | 1780 | 231.4 | 2011.4 | 2021-10-06 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Finish loading and hauling existing material from D010 for capping of wetlands @ D012 and start road repairs out to D011 | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-15 |  | 63 | 2021-10-15 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7433KL-20211006-3CAT 25 ton Articulated Truck101780 | KABI LAKE FOREST PRODUCTS LTD7433KL-20211006-3CAT 25 ton Articulated Truck101780OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7418 | KL-20211001-5 | 53510703 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 10.5 | HR | 134 | 0 |  |  | 1869 | 242.97 | 2111.97 | 2021-10-01 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading & hauling existing material for capping of wetland @ D-012 to D-013.Labourer delivering GEO from Marathon yard. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-08 |  | 62 | 2021-10-09 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7418KL-20211001-5CAT 25 ton Articulated Truck10.51869 | KABI LAKE FOREST PRODUCTS LTD7418KL-20211001-5CAT 25 ton Articulated Truck10.51869OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7412 | KL-20210930-3 | 53510703 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 10 | HR | 134 | 0 |  |  | 1780 | 231.4 | 2011.4 | 2021-09-30 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading & hauling existing material for capping of wetland @ D-012 to D-013. Excavator laying geo. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-07 |  | 62 | 2021-10-09 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7412KL-20210930-3CAT 25 ton Articulated Truck101780 | KABI LAKE FOREST PRODUCTS LTD7412KL-20210930-3CAT 25 ton Articulated Truck101780OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7408 | KL-20210929-2 | 53510703 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 10 | HR | 134 | 0 |  |  | 1780 | 231.4 | 2011.4 | 2021-09-29 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading & hauling stumps, grubbing & capping with existing material for crossing of wetland @ D012 to D013. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-07 |  | 62 | 2021-10-09 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7408KL-20210929-2CAT 25 ton Articulated Truck101780 | KABI LAKE FOREST PRODUCTS LTD7408KL-20210929-2CAT 25 ton Articulated Truck101780OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7404 | KL-20210928-2 | 53510703 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 10 | HR | 134 | 0 |  |  | 1780 | 231.4 | 2011.4 | 2021-09-28 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading & hauling stumps, grubbing. Hauling trees/existing material for crossing of Wetland @D012 to D013. Excavator/labourers delivering 6 rolls of GEO from Marathon yard. | 7 | D009-D017 | Three Finger Lake | 0 | 2021-10-06 |  | 62 | 2021-10-09 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7404KL-20210928-2CAT 25 ton Articulated Truck101780 | KABI LAKE FOREST PRODUCTS LTD7404KL-20210928-2CAT 25 ton Articulated Truck101780OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7398 | KL-20210927-2 | 53510703 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 10 | HR | 134 | 0 |  |  | 1780 | 231.4 | 2011.4 | 2021-09-27 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading & hauling stumps, grubbing & trees for crossing of wetland D012 to D013. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-06 |  | 62 | 2021-10-09 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7398KL-20210927-2CAT 25 ton Articulated Truck101780 | KABI LAKE FOREST PRODUCTS LTD7398KL-20210927-2CAT 25 ton Articulated Truck101780OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7429 | KL-20211005-3 | 53510703 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 10 | HR | 134 | 0 |  |  | 1780 | 231.4 | 2011.4 | 2021-10-05 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading & hauling existing material from D-010 for capping of wetland @ D012. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-08 |  | 37 | 2021-10-26 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7429KL-20211005-3CAT 25 ton Articulated Truck101780 | KABI LAKE FOREST PRODUCTS LTD7429KL-20211005-3CAT 25 ton Articulated Truck101780OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7426 | KL-20211004-3 | 53510703 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 10 | HR | 134 | 0 |  |  | 1780 | 231.4 | 2011.4 | 2021-10-04 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading & hauling existing material for capping of wetland @ D012 to D013. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-08 |  | 37 | 2021-10-09 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7426KL-20211004-3CAT 25 ton Articulated Truck101780 | KABI LAKE FOREST PRODUCTS LTD7426KL-20211004-3CAT 25 ton Articulated Truck101780OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7438 | KL-20211008-3 | 53510703 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 8.5 | HR | 147 | 0 |  |  | 1657.5 | 215.475 | 1872.975 | 2021-10-08 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Shape road, ditch & add material in low areas @ D012/D013. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-15 |  | 37 | 2021-10-26 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7438KL-20211008-330 Ton Excavator c/w Hydraulic Thumb8.51657.5 | KABI LAKE FOREST PRODUCTS LTD7438KL-20211008-330 Ton Excavator c/w Hydraulic Thumb8.51657.5OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7436 | KL-20211007-3 | 53510703 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 17 | HR | 147 | 0 |  |  | 3315 | 430.95 | 3745.95 | 2021-10-07 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Finish loading and hauling existing material from D010 for road repairs out to D011 | 7 | D009-D017 | Three Finger Lake | 0 | 2021-10-15 |  | 37 | 2021-10-26 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7436KL-20211007-330 Ton Excavator c/w Hydraulic Thumb173315 | KABI LAKE FOREST PRODUCTS LTD7436KL-20211007-330 Ton Excavator c/w Hydraulic Thumb173315OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7433 | KL-20211006-3 | 53510703 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 20 | HR | 147 | 0 |  |  | 3900 | 507 | 4407 | 2021-10-06 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Finish loading and hauling existing material from D010 for capping of wetlands @ D012 and start road repairs out to D011 | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-15 |  | 63 | 2021-10-15 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7433KL-20211006-330 Ton Excavator c/w Hydraulic Thumb203900 | KABI LAKE FOREST PRODUCTS LTD7433KL-20211006-330 Ton Excavator c/w Hydraulic Thumb203900OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7426 | KL-20211004-3 | 53510703 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 20 | HR | 147 | 0 |  |  | 3900 | 507 | 4407 | 2021-10-04 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading & hauling existing material for capping of wetland @ D012 to D013. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-08 |  | 37 | 2021-10-09 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7426KL-20211004-330 Ton Excavator c/w Hydraulic Thumb203900 | KABI LAKE FOREST PRODUCTS LTD7426KL-20211004-330 Ton Excavator c/w Hydraulic Thumb203900OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7423 | KL-20211003-3 | 53510703 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 10.5 | HR | 147 | 0 |  |  | 2047.5 | 266.175 | 2313.675 | 2021-10-03 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working on drainage & shaping access from D011 to D013. Piling material up for capping. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-08 |  | 37 | 2021-10-09 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7423KL-20211003-330 Ton Excavator c/w Hydraulic Thumb10.52047.5 | KABI LAKE FOREST PRODUCTS LTD7423KL-20211003-330 Ton Excavator c/w Hydraulic Thumb10.52047.5OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7418 | KL-20211001-5 | 53510703 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 21 | HR | 147 | 0 |  |  | 4095 | 532.35 | 4627.35 | 2021-10-01 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading & hauling existing material for capping of wetland @ D-012 to D-013.Labourer delivering GEO from Marathon yard. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-08 |  | 62 | 2021-10-09 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7418KL-20211001-530 Ton Excavator c/w Hydraulic Thumb214095 | KABI LAKE FOREST PRODUCTS LTD7418KL-20211001-530 Ton Excavator c/w Hydraulic Thumb214095OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7412 | KL-20210930-3 | 53510703 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 20 | HR | 147 | 0 |  |  | 3900 | 507 | 4407 | 2021-09-30 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading & hauling existing material for capping of wetland @ D-012 to D-013. Excavator laying geo. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-07 |  | 62 | 2021-10-09 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7412KL-20210930-330 Ton Excavator c/w Hydraulic Thumb203900 | KABI LAKE FOREST PRODUCTS LTD7412KL-20210930-330 Ton Excavator c/w Hydraulic Thumb203900OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7408 | KL-20210929-2 | 53510703 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 20 | HR | 147 | 0 |  |  | 3900 | 507 | 4407 | 2021-09-29 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading & hauling stumps, grubbing & capping with existing material for crossing of wetland @ D012 to D013. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-07 |  | 62 | 2021-10-09 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7408KL-20210929-230 Ton Excavator c/w Hydraulic Thumb203900 | KABI LAKE FOREST PRODUCTS LTD7408KL-20210929-230 Ton Excavator c/w Hydraulic Thumb203900OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7404 | KL-20210928-2 | 53510703 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 20 | HR | 147 | 0 |  |  | 3900 | 507 | 4407 | 2021-09-28 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading & hauling stumps, grubbing. Hauling trees/existing material for crossing of Wetland @D012 to D013. Excavator/labourers delivering 6 rolls of GEO from Marathon yard. | 7 | D009-D017 | Three Finger Lake | 0 | 2021-10-06 |  | 62 | 2021-10-09 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7404KL-20210928-230 Ton Excavator c/w Hydraulic Thumb203900 | KABI LAKE FOREST PRODUCTS LTD7404KL-20210928-230 Ton Excavator c/w Hydraulic Thumb203900OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7398 | KL-20210927-2 | 53510703 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 20 | HR | 147 | 0 |  |  | 3900 | 507 | 4407 | 2021-09-27 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading & hauling stumps, grubbing & trees for crossing of wetland D012 to D013. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-06 |  | 62 | 2021-10-09 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7398KL-20210927-230 Ton Excavator c/w Hydraulic Thumb203900 | KABI LAKE FOREST PRODUCTS LTD7398KL-20210927-230 Ton Excavator c/w Hydraulic Thumb203900OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7429 | KL-20211005-3 | 53510703 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 20 | HR | 147 | 0 |  |  | 3900 | 507 | 4407 | 2021-10-05 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading & hauling existing material from D-010 for capping of wetland @ D012. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-08 |  | 37 | 2021-10-26 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7429KL-20211005-330 Ton Excavator c/w Hydraulic Thumb203900 | KABI LAKE FOREST PRODUCTS LTD7429KL-20211005-330 Ton Excavator c/w Hydraulic Thumb203900OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7426 | KL-20211004-3 | 53510703 | Access | 0 | Pickup Truck - Truck Only | 25 | 22 | HR | 19 | 0 |  |  | 550 | 71.5 | 621.5 | 2021-10-04 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading & hauling existing material for capping of wetland @ D012 to D013. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-08 |  | 37 | 2021-10-09 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7426KL-20211004-3Pickup Truck - Truck Only22550 | KABI LAKE FOREST PRODUCTS LTD7426KL-20211004-3Pickup Truck - Truck Only22550OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7404 | KL-20210928-2 | 53510703 | Access | 0 | Tandum Trailer - without pickup - Daily | 75 | 1 | Daily |  | 0 |  |  | 75 | 9.75 | 84.75 | 2021-09-28 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading & hauling stumps, grubbing. Hauling trees/existing material for crossing of Wetland @D012 to D013. Excavator/labourers delivering 6 rolls of GEO from Marathon yard. | 7 | D009-D017 | Three Finger Lake | 0 | 2021-10-06 |  | 62 | 2021-10-09 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7404KL-20210928-2Tandum Trailer - without pickup - Daily175 | KABI LAKE FOREST PRODUCTS LTD7404KL-20210928-2Tandum Trailer - without pickup - Daily175OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7408 | KL-20210929-2 | 53510703 | Access | 0 | Single Axle Trailer - without pickup - Daily | 30 | 1 | Daily |  | 0 |  |  | 30 | 3.9 | 33.9 | 2021-09-29 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading & hauling stumps, grubbing & capping with existing material for crossing of wetland @ D012 to D013. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-07 |  | 62 | 2021-10-09 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7408KL-20210929-2Single Axle Trailer - without pickup - Daily130 | KABI LAKE FOREST PRODUCTS LTD7408KL-20210929-2Single Axle Trailer - without pickup - Daily130OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7404 | KL-20210928-2 | 53510703 | Access | 0 | Single Axle Trailer - without pickup - Daily | 30 | 1 | Daily |  | 0 |  |  | 30 | 3.9 | 33.9 | 2021-09-28 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading & hauling stumps, grubbing. Hauling trees/existing material for crossing of Wetland @D012 to D013. Excavator/labourers delivering 6 rolls of GEO from Marathon yard. | 7 | D009-D017 | Three Finger Lake | 0 | 2021-10-06 |  | 62 | 2021-10-09 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7404KL-20210928-2Single Axle Trailer - without pickup - Daily130 | KABI LAKE FOREST PRODUCTS LTD7404KL-20210928-2Single Axle Trailer - without pickup - Daily130OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7398 | KL-20210927-2 | 53510703 | Access | 0 | Single Axle Trailer - without pickup - Daily | 30 | 1 | Daily |  | 0 |  |  | 30 | 3.9 | 33.9 | 2021-09-27 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading & hauling stumps, grubbing & trees for crossing of wetland D012 to D013. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-06 |  | 62 | 2021-10-09 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7398KL-20210927-2Single Axle Trailer - without pickup - Daily130 | KABI LAKE FOREST PRODUCTS LTD7398KL-20210927-2Single Axle Trailer - without pickup - Daily130OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7408 | KL-20210929-2 | 53510703 | Access | 0 | ATV - side by side - Daily | 250 | 1 | Daily |  | 0 |  |  | 250 | 32.5 | 282.5 | 2021-09-29 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading & hauling stumps, grubbing & capping with existing material for crossing of wetland @ D012 to D013. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-07 |  | 62 | 2021-10-09 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7408KL-20210929-2ATV - side by side - Daily1250 | KABI LAKE FOREST PRODUCTS LTD7408KL-20210929-2ATV - side by side - Daily1250OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7404 | KL-20210928-2 | 53510703 | Access | 0 | ATV - side by side - Daily | 250 | 1 | Daily |  | 0 |  |  | 250 | 32.5 | 282.5 | 2021-09-28 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading & hauling stumps, grubbing. Hauling trees/existing material for crossing of Wetland @D012 to D013. Excavator/labourers delivering 6 rolls of GEO from Marathon yard. | 7 | D009-D017 | Three Finger Lake | 0 | 2021-10-06 |  | 62 | 2021-10-09 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7404KL-20210928-2ATV - side by side - Daily1250 | KABI LAKE FOREST PRODUCTS LTD7404KL-20210928-2ATV - side by side - Daily1250OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7398 | KL-20210927-2 | 53510703 | Access | 0 | ATV - side by side - Daily | 250 | 1 | Daily |  | 0 |  |  | 250 | 32.5 | 282.5 | 2021-09-27 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Continue loading & hauling stumps, grubbing & trees for crossing of wetland D012 to D013. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-06 |  | 62 | 2021-10-09 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7398KL-20210927-2ATV - side by side - Daily1250 | KABI LAKE FOREST PRODUCTS LTD7398KL-20210927-2ATV - side by side - Daily1250OEWT-PA22-Lem | Wetland Access Development |  | Wetland Access Development
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7394 | KL-20210926-2 | 53510712 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2021-09-26 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator continuing work on drainage & shaping road from D-011 to D-013. Piling up stumps @ D-012 for wetland. Rock truck on site for gravelling. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-05 |  | 62 | 2021-10-09 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7394KL-20210926-2Supervisor184 | KABI LAKE FOREST PRODUCTS LTD7394KL-20210926-2Supervisor184OEWT-PA22-Lem |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7461 | KL-20211016-2 | 53510712 | Access | 0 | Supervisor | 84 | 1 | HR |  |  | 84 | 0 | 84 | 10.92 | 94.92 | 2021-10-16 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Finish capping soft areas with grindings @ D025 /Shaping , ditch and leveling ruts working out | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-25 |  | 37 | 2021-10-27 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7461KL-20211016-2Supervisor184 | KABI LAKE FOREST PRODUCTS LTD7461KL-20211016-2Supervisor184OEWT-PA22-Lem |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7447 | KL-20211012-3 | 53510712 | Access | 0 | Supervisor | 84 | 2 | HR |  |  | 84 | 0 | 168 | 21.84 | 189.84 | 2021-10-12 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working on drainage, shaping road, ditching & adding material in low areas @ D012/D013. Start cleaning up & sloping excavation @ D010. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-18 |  | 37 | 2021-10-26 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7447KL-20211012-3Supervisor2168 | KABI LAKE FOREST PRODUCTS LTD7447KL-20211012-3Supervisor2168OEWT-PA22-Lem |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7461 | KL-20211016-2 | 53510712 | Access | 0 | L.O.A. | 244 | 0.90909 | DAY |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-10-16 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Finish capping soft areas with grindings @ D025 /Shaping , ditch and leveling ruts working out | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-25 |  | 37 | 2021-10-27 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7461KL-20211016-2L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7461KL-20211016-2L.O.A.0.9090909221.8182OEWT-PA22-Lem |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7461 | KL-20211016-2 | 53510712 | Access | 0 | L.O.A. | 244 | 0.90909 | DAY |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-10-16 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Finish capping soft areas with grindings @ D025 /Shaping , ditch and leveling ruts working out | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-25 |  | 37 | 2021-10-27 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7461KL-20211016-2L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7461KL-20211016-2L.O.A.0.9090909221.8182OEWT-PA22-Lem |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7447 | KL-20211012-3 | 53510712 | Access | 0 | L.O.A. | 244 | 0.77273 | DAY |  | 0 |  |  | 188.5455 | 24.5109 | 213.0564 | 2021-10-12 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working on drainage, shaping road, ditching & adding material in low areas @ D012/D013. Start cleaning up & sloping excavation @ D010. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-18 |  | 37 | 2021-10-26 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7447KL-20211012-3L.O.A.0.7727273188.5455 | KABI LAKE FOREST PRODUCTS LTD7447KL-20211012-3L.O.A.0.7727273188.5455OEWT-PA22-Lem |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7394 | KL-20210926-2 | 53510712 | Access | 0 | L.O.A. | 244 | 0.45455 | DAY |  | 0 |  |  | 110.9091 | 14.4182 | 125.3273 | 2021-09-26 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator continuing work on drainage & shaping road from D-011 to D-013. Piling up stumps @ D-012 for wetland. Rock truck on site for gravelling. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-05 |  | 62 | 2021-10-09 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7394KL-20210926-2L.O.A.0.4545455110.9091 | KABI LAKE FOREST PRODUCTS LTD7394KL-20210926-2L.O.A.0.4545455110.9091OEWT-PA22-Lem |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7394 | KL-20210926-2 | 53510712 | Access | 0 | L.O.A. | 244 | 0.90909 | DAY |  | 0 |  |  | 221.8182 | 28.8364 | 250.6546 | 2021-09-26 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator continuing work on drainage & shaping road from D-011 to D-013. Piling up stumps @ D-012 for wetland. Rock truck on site for gravelling. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-05 |  | 62 | 2021-10-09 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7394KL-20210926-2L.O.A.0.9090909221.8182 | KABI LAKE FOREST PRODUCTS LTD7394KL-20210926-2L.O.A.0.9090909221.8182OEWT-PA22-Lem |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7461 | KL-20211016-2 | 53510712 | Access | 0 | Pickup 1/2 Ton | 25 | 21 | HR | 19 | 0 |  |  | 525 | 68.25 | 593.25 | 2021-10-16 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Finish capping soft areas with grindings @ D025 /Shaping , ditch and leveling ruts working out | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-25 |  | 37 | 2021-10-27 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7461KL-20211016-2Pickup 1/2 Ton21525 | KABI LAKE FOREST PRODUCTS LTD7461KL-20211016-2Pickup 1/2 Ton21525OEWT-PA22-Lem |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7447 | KL-20211012-3 | 53510712 | Access | 0 | Pickup 1/2 Ton | 25 | 2 | HR | 19 | 0 |  |  | 50 | 6.5 | 56.5 | 2021-10-12 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working on drainage, shaping road, ditching & adding material in low areas @ D012/D013. Start cleaning up & sloping excavation @ D010. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-18 |  | 37 | 2021-10-26 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7447KL-20211012-3Pickup 1/2 Ton250 | KABI LAKE FOREST PRODUCTS LTD7447KL-20211012-3Pickup 1/2 Ton250OEWT-PA22-Lem |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7447 | KL-20211012-3 | 53510712 | Access | 0 | Pickup 1/2 Ton | 25 | 8.5 | HR | 19 | 0 |  |  | 212.5 | 27.625 | 240.125 | 2021-10-12 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working on drainage, shaping road, ditching & adding material in low areas @ D012/D013. Start cleaning up & sloping excavation @ D010. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-18 |  | 37 | 2021-10-26 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7447KL-20211012-3Pickup 1/2 Ton8.5212.5 | KABI LAKE FOREST PRODUCTS LTD7447KL-20211012-3Pickup 1/2 Ton8.5212.5OEWT-PA22-Lem |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7394 | KL-20210926-2 | 53510712 | Access | 0 | Pickup 1/2 Ton | 25 | 11 | HR | 19 | 0 |  |  | 275 | 35.75 | 310.75 | 2021-09-26 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator continuing work on drainage & shaping road from D-011 to D-013. Piling up stumps @ D-012 for wetland. Rock truck on site for gravelling. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-05 |  | 62 | 2021-10-09 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7394KL-20210926-2Pickup 1/2 Ton11275 | KABI LAKE FOREST PRODUCTS LTD7394KL-20210926-2Pickup 1/2 Ton11275OEWT-PA22-Lem |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7394 | KL-20210926-2 | 53510712 | Access | 0 | CAT 25 ton Articulated Truck | 178 | 5 | HR | 134 | 0 |  |  | 890 | 115.7 | 1005.7 | 2021-09-26 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator continuing work on drainage & shaping road from D-011 to D-013. Piling up stumps @ D-012 for wetland. Rock truck on site for gravelling. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-05 |  | 62 | 2021-10-09 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7394KL-20210926-2CAT 25 ton Articulated Truck5890 | KABI LAKE FOREST PRODUCTS LTD7394KL-20210926-2CAT 25 ton Articulated Truck5890OEWT-PA22-Lem |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7461 | KL-20211016-2 | 53510712 | Access | 0 | CAT D6 - LPG | 179 | 10 | HR | 135 | 0 |  |  | 1790 | 232.7 | 2022.7 | 2021-10-16 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Finish capping soft areas with grindings @ D025 /Shaping , ditch and leveling ruts working out | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-25 |  | 37 | 2021-10-27 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7461KL-20211016-2CAT D6 - LPG101790 | KABI LAKE FOREST PRODUCTS LTD7461KL-20211016-2CAT D6 - LPG101790OEWT-PA22-Lem |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7461 | KL-20211016-2 | 53510712 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 10 | HR | 147 | 0 |  |  | 1950 | 253.5 | 2203.5 | 2021-10-16 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Finish capping soft areas with grindings @ D025 /Shaping , ditch and leveling ruts working out | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-25 |  | 37 | 2021-10-27 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7461KL-20211016-230 Ton Excavator c/w Hydraulic Thumb101950 | KABI LAKE FOREST PRODUCTS LTD7461KL-20211016-230 Ton Excavator c/w Hydraulic Thumb101950OEWT-PA22-Lem |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7447 | KL-20211012-3 | 53510712 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 8.5 | HR | 147 | 0 |  |  | 1657.5 | 215.475 | 1872.975 | 2021-10-12 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator working on drainage, shaping road, ditching & adding material in low areas @ D012/D013. Start cleaning up & sloping excavation @ D010. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-18 |  | 37 | 2021-10-26 | [5 empty] | Harold Furlong | 07 | KABI LAKE FOREST PRODUCTS LTD7447KL-20211012-330 Ton Excavator c/w Hydraulic Thumb8.51657.5 | KABI LAKE FOREST PRODUCTS LTD7447KL-20211012-330 Ton Excavator c/w Hydraulic Thumb8.51657.5OEWT-PA22-Lem |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
KABI LAKE FOREST PRODUCTS LTD | 12 | 0 | 7394 | KL-20210926-2 | 53510712 | Access | 0 | 30 Ton Excavator c/w Hydraulic Thumb | 195 | 10 | HR | 147 | 0 |  |  | 1950 | 253.5 | 2203.5 | 2021-09-26 | 0 | OEWT-PA22-Lem | 2021-11-02 | 78 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-016 | 938 OF |  |  |  | Approved |  |  | Excavator continuing work on drainage & shaping road from D-011 to D-013. Piling up stumps @ D-012 for wetland. Rock truck on site for gravelling. | 7 | D-009 to D-017 | Three Finger Lake | 0 | 2021-10-05 |  | 62 | 2021-10-09 | [6 empty] | 07 | KABI LAKE FOREST PRODUCTS LTD7394KL-20210926-230 Ton Excavator c/w Hydraulic Thumb101950 | KABI LAKE FOREST PRODUCTS LTD7394KL-20210926-230 Ton Excavator c/w Hydraulic Thumb101950OEWT-PA22-Lem |  | CZ - All Season Access Maintenance | WF6/WF7 - All Season Access Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11765 | 20220309-5 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-03-09 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C236-C243 | Culvert Creek | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1176520220309-5Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1176520220309-5Operator - Principle - After Jan 1011825 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11765 | 20220309-5 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2022-03-09 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C236-C243 | Culvert Creek | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1176520220309-5L.O.A.1210 | Corbiere and Sons Contracting1176520220309-5L.O.A.1210 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11765 | 20220309-5 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-03-09 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C236-C243 | Culvert Creek | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1176520220309-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1176520220309-5Light Truck - Pick up- After Jan 101243.75 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11765 | 20220309-5 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10 | Dynamic | 0 | 0 |  |  | 1314.8 | 170.924 | 1485.724 | 2022-03-09 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C236-C243 | Culvert Creek | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1176520220309-5Dozer D6 or equal- After Jan 10101314.8 | Corbiere and Sons Contracting1176520220309-5Dozer D6 or equal- After Jan 10101314.8 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11763 | 20220309-3 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 0 | 0 | 900 | 117 | 1017 | 2022-03-09 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1176320220309-3Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1176320220309-3Operator - Principle - After Jan 1012900 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11763 | 20220309-3 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-03-09 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1176320220309-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1176320220309-3Operator - Principle - After Jan 1011825 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11763 | 20220309-3 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-03-09 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1176320220309-3L.O.A.1210 | Corbiere and Sons Contracting1176320220309-3L.O.A.1210 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11763 | 20220309-3 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-03-09 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1176320220309-3L.O.A.1210 | Corbiere and Sons Contracting1176320220309-3L.O.A.1210 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11763 | 20220309-3 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 0 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2022-03-09 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1176320220309-3Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting1176320220309-3Light Truck - Pick up- After Jan 102487.5 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11763 | 20220309-3 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 9 | Dynamic | 0 | 0 |  |  | 1142.82 | 148.5666 | 1291.3866 | 2022-03-09 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1176320220309-3Grader - Cat 12 to 14 or equal- After Jan 1091142.82 | Corbiere and Sons Contracting1176320220309-3Grader - Cat 12 to 14 or equal- After Jan 1091142.82 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11761 | 20220308-6 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 5 | HR |  |  | 70 | 0 | 350 | 45.5 | 395.5 | 2022-03-08 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C236-C243 | Culvert Creek | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1176120220308-6Driver - AZ - After Jan 105350 | Corbiere and Sons Contracting1176120220308-6Driver - AZ - After Jan 105350 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11761 | 20220308-6 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5 | HR |  |  | 0 | 0 | 375 | 48.75 | 423.75 | 2022-03-08 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C236-C243 | Culvert Creek | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1176120220308-6Operator - Principle - After Jan 105375 | Corbiere and Sons Contracting1176120220308-6Operator - Principle - After Jan 105375 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11761 | 20220308-6 | 53510611 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 5 | Dynamic | 91.79 | 0 |  |  | 611.95 | 79.5535 | 691.5035 | 2022-03-08 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C236-C243 | Culvert Creek | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1176120220308-6Tractor Trailer - 60 Ton- After Jan 105611.95 | Corbiere and Sons Contracting1176120220308-6Tractor Trailer - 60 Ton- After Jan 105611.95 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11761 | 20220308-6 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 2 | Dynamic | 0 | 0 |  |  | 262.96 | 34.1848 | 297.1448 | 2022-03-08 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C236-C243 | Culvert Creek | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1176120220308-6Dozer D6 or equal- After Jan 102262.96 | Corbiere and Sons Contracting1176120220308-6Dozer D6 or equal- After Jan 102262.96 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11758 | 20220308-3 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 6 | HR |  |  | 70 | 0 | 420 | 54.6 | 474.6 | 2022-03-08 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1175820220308-3Driver - AZ - After Jan 106420 | Corbiere and Sons Contracting1175820220308-3Driver - AZ - After Jan 106420 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11758 | 20220308-3 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 0 | 0 | 900 | 117 | 1017 | 2022-03-08 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1175820220308-3Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1175820220308-3Operator - Principle - After Jan 1012900 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11758 | 20220308-3 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-03-08 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1175820220308-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1175820220308-3Operator - Principle - After Jan 1011825 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11758 | 20220308-3 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2022-03-08 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1175820220308-3L.O.A.1210 | Corbiere and Sons Contracting1175820220308-3L.O.A.1210 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11758 | 20220308-3 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-03-08 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1175820220308-3L.O.A.1210 | Corbiere and Sons Contracting1175820220308-3L.O.A.1210 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11758 | 20220308-3 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-03-08 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1175820220308-3L.O.A.1210 | Corbiere and Sons Contracting1175820220308-3L.O.A.1210 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11758 | 20220308-3 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 6 |  | 0 | 0 |  |  | 480 | 62.4 | 542.4 | 2022-03-08 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1175820220308-3Pickup w/ plow and sander6480 | Corbiere and Sons Contracting1175820220308-3Pickup w/ plow and sander6480 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11758 | 20220308-3 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-03-08 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1175820220308-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1175820220308-3Light Truck - Pick up- After Jan 101243.75 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11758 | 20220308-3 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-03-08 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1175820220308-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1175820220308-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11755 | 20220307-4 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-03-07 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C171-C185 | Prairie River | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1175520220307-4Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1175520220307-4Operator - Principle - After Jan 1011825 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11755 | 20220307-4 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-03-07 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C171-C185 | Prairie River | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1175520220307-4L.O.A.1210 | Corbiere and Sons Contracting1175520220307-4L.O.A.1210 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11755 | 20220307-4 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-03-07 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C171-C185 | Prairie River | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1175520220307-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1175520220307-4Light Truck - Pick up- After Jan 101243.75 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11755 | 20220307-4 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 7 | Dynamic | 0 | 0 |  |  | 888.86 | 115.5518 | 1004.4118 | 2022-03-07 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C171-C185 | Prairie River | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1175520220307-4Grader - Cat 12 to 14 or equal- After Jan 107888.86 | Corbiere and Sons Contracting1175520220307-4Grader - Cat 12 to 14 or equal- After Jan 107888.86 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11754 | 20220307-3 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 0 | 0 | 900 | 117 | 1017 | 2022-03-07 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1175420220307-3Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1175420220307-3Operator - Principle - After Jan 1012900 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11754 | 20220307-3 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-03-07 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1175420220307-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1175420220307-3Operator - Principle - After Jan 1011825 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11754 | 20220307-3 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-03-07 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1175420220307-3L.O.A.1210 | Corbiere and Sons Contracting1175420220307-3L.O.A.1210 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11754 | 20220307-3 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-03-07 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1175420220307-3L.O.A.1210 | Corbiere and Sons Contracting1175420220307-3L.O.A.1210 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11754 | 20220307-3 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-03-07 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1175420220307-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1175420220307-3Light Truck - Pick up- After Jan 101243.75 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11754 | 20220307-3 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 7 | Dynamic | 0 | 0 |  |  | 888.86 | 115.5518 | 1004.4118 | 2022-03-07 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1175420220307-3Grader - Cat 12 to 14 or equal- After Jan 107888.86 | Corbiere and Sons Contracting1175420220307-3Grader - Cat 12 to 14 or equal- After Jan 107888.86 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11752 | 20220306-5 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 4 | HR |  |  | 70 | 0 | 280 | 36.4 | 316.4 | 2022-03-06 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C158 - C170 | Santoy Mountain | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1175220220306-5Driver - AZ - After Jan 104280 | Corbiere and Sons Contracting1175220220306-5Driver - AZ - After Jan 104280 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11752 | 20220306-5 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 2.5 | HR |  |  | 75 | 0 | 187.5 | 24.375 | 211.875 | 2022-03-06 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C158 - C170 | Santoy Mountain | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1175220220306-5Operator - Principle - After Jan 102.5187.5 | Corbiere and Sons Contracting1175220220306-5Operator - Principle - After Jan 102.5187.5 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11752 | 20220306-5 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2022-03-06 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C158 - C170 | Santoy Mountain | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1175220220306-5L.O.A.1210 | Corbiere and Sons Contracting1175220220306-5L.O.A.1210 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11752 | 20220306-5 | 53510611 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 4 | Dynamic | 91.79 | 0 |  |  | 489.56 | 63.6428 | 553.2028 | 2022-03-06 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C158 - C170 | Santoy Mountain | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1175220220306-5Tractor Trailer - 60 Ton- After Jan 104489.56 | Corbiere and Sons Contracting1175220220306-5Tractor Trailer - 60 Ton- After Jan 104489.56 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11752 | 20220306-5 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 2.5 | Dynamic | 98.61 | 0 |  |  | 328.7 | 42.731 | 371.431 | 2022-03-06 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C158 - C170 | Santoy Mountain | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1175220220306-5Dozer D6 or equal- After Jan 102.5328.7 | Corbiere and Sons Contracting1175220220306-5Dozer D6 or equal- After Jan 102.5328.7 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11749 | 20220306-4 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-03-06 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C171-C185 | Prairie River | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1174920220306-4Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1174920220306-4Operator - Principle - After Jan 1011825 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11749 | 20220306-4 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-03-06 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C171-C185 | Prairie River | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1174920220306-4L.O.A.1210 | Corbiere and Sons Contracting1174920220306-4L.O.A.1210 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11749 | 20220306-4 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-03-06 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C171-C185 | Prairie River | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1174920220306-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1174920220306-4Light Truck - Pick up- After Jan 101243.75 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11749 | 20220306-4 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 9 | Dynamic | 0 | 0 |  |  | 1142.82 | 148.5666 | 1291.3866 | 2022-03-06 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C171-C185 | Prairie River | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1174920220306-4Grader - Cat 12 to 14 or equal- After Jan 1091142.82 | Corbiere and Sons Contracting1174920220306-4Grader - Cat 12 to 14 or equal- After Jan 1091142.82 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11748 | 20220306-3 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2022-03-06 |  | INV# 169 | 2022-04-07 |  | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF | [6 empty] | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1174820220306-3Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting1174820220306-3Operator - Principle - After Jan 1012900 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11748 | 20220306-3 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-03-06 |  | INV# 169 | 2022-04-07 |  | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF | [6 empty] | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1174820220306-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1174820220306-3Operator - Principle - After Jan 1011825 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11748 | 20220306-3 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2022-03-06 |  | INV# 169 | 2022-04-07 |  | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF | [6 empty] | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1174820220306-3L.O.A.1210 | Corbiere and Sons Contracting1174820220306-3L.O.A.1210 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11748 | 20220306-3 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-03-06 |  | INV# 169 | 2022-04-07 |  | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF | [6 empty] | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1174820220306-3L.O.A.1210 | Corbiere and Sons Contracting1174820220306-3L.O.A.1210 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11748 | 20220306-3 | 53510611 | Access | 0 | Pickup w/ plow and sander | 80 | 12 |  | 0 | 0 |  |  | 960 | 124.8 | 1084.8 | 2022-03-06 |  | INV# 169 | 2022-04-07 |  | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF | [6 empty] | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1174820220306-3Pickup w/ plow and sander12960 | Corbiere and Sons Contracting1174820220306-3Pickup w/ plow and sander12960 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11748 | 20220306-3 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-03-06 |  | INV# 169 | 2022-04-07 |  | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF | [6 empty] | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1174820220306-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1174820220306-3Light Truck - Pick up- After Jan 101243.75 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11748 | 20220306-3 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-03-06 |  | INV# 169 | 2022-04-07 |  | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF | [6 empty] | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1174820220306-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1174820220306-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11744 | 20220305-5 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 8 | HR |  |  | 0 | 0 | 600 | 78 | 678 | 2022-03-05 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1174420220305-5Operator - Principle - After Jan 108600 | Corbiere and Sons Contracting1174420220305-5Operator - Principle - After Jan 108600 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11744 | 20220305-5 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-03-05 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1174420220305-5L.O.A.1210 | Corbiere and Sons Contracting1174420220305-5L.O.A.1210 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11744 | 20220305-5 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-03-05 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1174420220305-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1174420220305-5Light Truck - Pick up- After Jan 101243.75 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11744 | 20220305-5 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 7 | Dynamic | 0 | 0 |  |  | 920.36 | 119.6468 | 1040.0068 | 2022-03-05 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1174420220305-5Dozer D6 or equal- After Jan 107920.36 | Corbiere and Sons Contracting1174420220305-5Dozer D6 or equal- After Jan 107920.36 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11742 | 20220305-4 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-03-05 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C171-C185 | Prairie River | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1174220220305-4Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1174220220305-4Operator - Principle - After Jan 1011825 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11742 | 20220305-4 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-03-05 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C171-C185 | Prairie River | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1174220220305-4L.O.A.1210 | Corbiere and Sons Contracting1174220220305-4L.O.A.1210 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11742 | 20220305-4 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-03-05 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C171-C185 | Prairie River | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1174220220305-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1174220220305-4Light Truck - Pick up- After Jan 101243.75 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11742 | 20220305-4 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 9 | Dynamic | 0 | 0 |  |  | 1142.82 | 148.5666 | 1291.3866 | 2022-03-05 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C171-C185 | Prairie River | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1174220220305-4Grader - Cat 12 to 14 or equal- After Jan 1091142.82 | Corbiere and Sons Contracting1174220220305-4Grader - Cat 12 to 14 or equal- After Jan 1091142.82 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11743 | 20220305-3 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 3 | HR |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-03-05 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1174320220305-3Driver - AZ - After Jan 103210 | Corbiere and Sons Contracting1174320220305-3Driver - AZ - After Jan 103210 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11743 | 20220305-3 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-03-05 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1174320220305-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1174320220305-3Operator - Principle - After Jan 1011825 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11743 | 20220305-3 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-03-05 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1174320220305-3L.O.A.1210 | Corbiere and Sons Contracting1174320220305-3L.O.A.1210 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11743 | 20220305-3 | 53510611 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 3 | Dynamic | 0 | 0 |  |  | 367.17 | 47.7321 | 414.9021 | 2022-03-05 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1174320220305-3Tractor Trailer - 60 Ton- After Jan 103367.17 | Corbiere and Sons Contracting1174320220305-3Tractor Trailer - 60 Ton- After Jan 103367.17 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11743 | 20220305-3 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-03-05 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1174320220305-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1174320220305-3Light Truck - Pick up- After Jan 101243.75 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11743 | 20220305-3 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-03-05 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1174320220305-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1174320220305-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11735 | 20220304-5 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 7 | HR |  |  | 0 | 0 | 525 | 68.25 | 593.25 | 2022-03-04 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1173520220304-5Operator - Principle - After Jan 107525 | Corbiere and Sons Contracting1173520220304-5Operator - Principle - After Jan 107525 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11735 | 20220304-5 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-03-04 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1173520220304-5L.O.A.1210 | Corbiere and Sons Contracting1173520220304-5L.O.A.1210 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11735 | 20220304-5 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-03-04 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1173520220304-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1173520220304-5Light Truck - Pick up- After Jan 101243.75 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11735 | 20220304-5 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 6 | Dynamic | 0 | 0 |  |  | 788.88 | 102.5544 | 891.4344 | 2022-03-04 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1173520220304-5Dozer D6 or equal- After Jan 106788.88 | Corbiere and Sons Contracting1173520220304-5Dozer D6 or equal- After Jan 106788.88 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11734 | 20220304-4 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-03-04 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C171-C185 | Prairie River | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1173420220304-4Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1173420220304-4Operator - Principle - After Jan 1011825 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11734 | 20220304-4 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-03-04 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C171-C185 | Prairie River | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1173420220304-4L.O.A.1210 | Corbiere and Sons Contracting1173420220304-4L.O.A.1210 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11734 | 20220304-4 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-03-04 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C171-C185 | Prairie River | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1173420220304-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1173420220304-4Light Truck - Pick up- After Jan 101243.75 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11734 | 20220304-4 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-03-04 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C171-C185 | Prairie River | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1173420220304-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1173420220304-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11741 | 20220304-3 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 3 | HR |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-03-04 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1174120220304-3Driver - AZ - After Jan 103210 | Corbiere and Sons Contracting1174120220304-3Driver - AZ - After Jan 103210 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11741 | 20220304-3 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-03-04 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1174120220304-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1174120220304-3Operator - Principle - After Jan 1011825 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11741 | 20220304-3 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-03-04 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1174120220304-3L.O.A.1210 | Corbiere and Sons Contracting1174120220304-3L.O.A.1210 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11741 | 20220304-3 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-03-04 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1174120220304-3L.O.A.1210 | Corbiere and Sons Contracting1174120220304-3L.O.A.1210 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11741 | 20220304-3 | 53510611 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 3 | Dynamic | 0 | 0 |  |  | 367.17 | 47.7321 | 414.9021 | 2022-03-04 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1174120220304-3Tractor Trailer - 60 Ton- After Jan 103367.17 | Corbiere and Sons Contracting1174120220304-3Tractor Trailer - 60 Ton- After Jan 103367.17 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11741 | 20220304-3 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-03-04 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1174120220304-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1174120220304-3Light Truck - Pick up- After Jan 101243.75 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11741 | 20220304-3 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-03-04 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1174120220304-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1174120220304-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11730 | 20220303-5 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-03-03 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1173020220303-5Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1173020220303-5Operator - Principle - After Jan 1011825 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11730 | 20220303-5 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-03-03 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1173020220303-5L.O.A.1210 | Corbiere and Sons Contracting1173020220303-5L.O.A.1210 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11730 | 20220303-5 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-03-03 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1173020220303-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1173020220303-5Light Truck - Pick up- After Jan 101243.75 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11730 | 20220303-5 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 6.5 | Dynamic | 98.61 | 0 |  |  | 854.62 | 111.1006 | 965.7206 | 2022-03-03 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1173020220303-5Dozer D6 or equal- After Jan 106.5854.62 | Corbiere and Sons Contracting1173020220303-5Dozer D6 or equal- After Jan 106.5854.62 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11729 | 20220303-4 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-03-03 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C171-C185 | Prairie River | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1172920220303-4Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1172920220303-4Operator - Principle - After Jan 1011825 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11729 | 20220303-4 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-03-03 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C171-C185 | Prairie River | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1172920220303-4L.O.A.1210 | Corbiere and Sons Contracting1172920220303-4L.O.A.1210 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11729 | 20220303-4 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-03-03 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C171-C185 | Prairie River | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1172920220303-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1172920220303-4Light Truck - Pick up- After Jan 101243.75 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11729 | 20220303-4 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-03-03 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C171-C185 | Prairie River | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1172920220303-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1172920220303-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11728 | 20220303-3 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 11 | HR |  |  | 0 | 0 | 770 | 100.1 | 870.1 | 2022-03-03 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1172820220303-3Driver - AZ - After Jan 1011770 | Corbiere and Sons Contracting1172820220303-3Driver - AZ - After Jan 1011770 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11728 | 20220303-3 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-03-03 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1172820220303-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1172820220303-3Operator - Principle - After Jan 1011825 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11728 | 20220303-3 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-03-03 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1172820220303-3L.O.A.1210 | Corbiere and Sons Contracting1172820220303-3L.O.A.1210 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11728 | 20220303-3 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-03-03 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1172820220303-3L.O.A.1210 | Corbiere and Sons Contracting1172820220303-3L.O.A.1210 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11728 | 20220303-3 | 53510611 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 11 | Dynamic | 0 | 0 |  |  | 1346.29 | 175.0177 | 1521.3077 | 2022-03-03 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1172820220303-3Tractor Trailer - 60 Ton- After Jan 10111346.29 | Corbiere and Sons Contracting1172820220303-3Tractor Trailer - 60 Ton- After Jan 10111346.29 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11728 | 20220303-3 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-03-03 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1172820220303-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1172820220303-3Light Truck - Pick up- After Jan 101243.75 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11728 | 20220303-3 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 0 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2022-03-03 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1172820220303-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting1172820220303-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11724 | 20220302-6 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-03-02 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1172420220302-6Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1172420220302-6Operator - Principle - After Jan 1011825 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11724 | 20220302-6 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2022-03-02 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1172420220302-6L.O.A.1210 | Corbiere and Sons Contracting1172420220302-6L.O.A.1210 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11724 | 20220302-6 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-03-02 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1172420220302-6Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1172420220302-6Light Truck - Pick up- After Jan 101243.75 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11724 | 20220302-6 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 6.5 | Dynamic | 98.61 | 0 |  |  | 854.62 | 111.1006 | 965.7206 | 2022-03-02 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C219-C235 | Neys | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1172420220302-6Dozer D6 or equal- After Jan 106.5854.62 | Corbiere and Sons Contracting1172420220302-6Dozer D6 or equal- After Jan 106.5854.62 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11723 | 20220302-4 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 8 | HR |  |  | 0 | 0 | 600 | 78 | 678 | 2022-03-02 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C171-C185 | Prairie River | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1172320220302-4Operator - Principle - After Jan 108600 | Corbiere and Sons Contracting1172320220302-4Operator - Principle - After Jan 108600 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11723 | 20220302-4 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-03-02 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C171-C185 | Prairie River | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1172320220302-4L.O.A.1210 | Corbiere and Sons Contracting1172320220302-4L.O.A.1210 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11723 | 20220302-4 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-03-02 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C171-C185 | Prairie River | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1172320220302-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1172320220302-4Light Truck - Pick up- After Jan 101243.75 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11723 | 20220302-4 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 6 | Dynamic | 0 | 0 |  |  | 761.88 | 99.0444 | 860.9244 | 2022-03-02 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C171-C185 | Prairie River | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1172320220302-4Grader - Cat 12 to 14 or equal- After Jan 106761.88 | Corbiere and Sons Contracting1172320220302-4Grader - Cat 12 to 14 or equal- After Jan 106761.88 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11722 | 20220302-3 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 11 | HR |  |  | 70 | 0 | 770 | 100.1 | 870.1 | 2022-03-02 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1172220220302-3Driver - AZ - After Jan 1011770 | Corbiere and Sons Contracting1172220220302-3Driver - AZ - After Jan 1011770 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11722 | 20220302-3 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 0 | 0 | 825 | 107.25 | 932.25 | 2022-03-02 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1172220220302-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting1172220220302-3Operator - Principle - After Jan 1011825 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11722 | 20220302-3 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2022-03-02 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1172220220302-3L.O.A.1210 | Corbiere and Sons Contracting1172220220302-3L.O.A.1210 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11722 | 20220302-3 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2022-03-02 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1172220220302-3L.O.A.1210 | Corbiere and Sons Contracting1172220220302-3L.O.A.1210 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11722 | 20220302-3 | 53510611 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 11 | Dynamic | 91.79 | 0 |  |  | 1346.29 | 175.0177 | 1521.3077 | 2022-03-02 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1172220220302-3Tractor Trailer - 60 Ton- After Jan 10111346.29 | Corbiere and Sons Contracting1172220220302-3Tractor Trailer - 60 Ton- After Jan 10111346.29 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11722 | 20220302-3 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2022-03-02 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1172220220302-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting1172220220302-3Light Truck - Pick up- After Jan 101243.75 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance
Corbiere and Sons Contracting | 6 | 0 | 11722 | 20220302-3 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 9 | Dynamic | 0 | 0 |  |  | 1142.82 | 148.5666 | 1291.3866 | 2022-03-02 |  | INV# 169 | 2022-04-07 |  | 1 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Pending |  |  | WAM Activities | 6 | C158-C170 | Santoy Lake | 0 | 2022-03-16 | [9 empty] | 06 | Corbiere and Sons Contracting1172220220302-3Grader - Cat 12 to 14 or equal- After Jan 1091142.82 | Corbiere and Sons Contracting1172220220302-3Grader - Cat 12 to 14 or equal- After Jan 1091142.82 | CZ - Winter Maintenance | CZ - Winter Maintenance | WF6/WF7 - Winter Maintenance

## DPCache_Seedlings Forecast (hidden)
POLY_ID | Structure | RIPARIAN | AREA_HA | Segment | SUBC_CLEAR | FDMS_CAT | RD_TYPE | WF | MAP | STRUCTURES | ROW | ROAD | LAYDOWN | RET_REV | COMMENTS
WF5_6455 | C106 | NO | 0.21566 |  | Harvest Processing | Non-Mulch |  | 5 | 54 | C106-C108 | 1 | 0 | 0 | 0
WF5_2306 | C106 | NO | 0.12525 |  | Harvest Processing | Non-Mulch | AN | 5 | 54 | C106-C108 | 0 | 1 | 0 | 0
WF5_7828 | C106 | NO | 1.241 |  | Harvest Processing | Non-Mulch |  | 5 | 54 | C106-C108 | 1 | 0 | 0 | 0 | Clearing type change based on field request
WF5_6456 | C107 | NO | 0.79355 |  | Harvest Processing | Non-Mulch |  | 5 | 54 | C106-C108 | 1 | 0 | 0 | 0
WF5_6892 | C107 | NO | 0.61212 |  | Hand Fall / Lop and Scatter | Handfall |  | 5 | 54 | C106-C108 | 1 | 0 | 0 | 0
WF5_6893 | C107 | NO | 0.1468 |  | Hand Fall / Lop and Scatter | Handfall |  | 5 | 54 | C106-C108 | 1 | 0 | 0 | 0
WF5_6894 | C107 | NO | 0.057519 |  | Hand Fall / Lop and Scatter | Handfall |  | 5 | 54 | C106-C108 | 1 | 0 | 0 | 0
WF5_2313 | C107 | NO | 0.087571 |  | Retention | Retention |  | 5 | 54 | C106-C108 | 1 | 0 | 0 | 8
WF5_7769 | C107 | NO | 0.37839 |  | Harvest Processing | Non-Mulch |  | 5 | 54 | C106-C108 | 1 | 0 | 0 | 0
WF5_8056 | C107 | NO | 0.26492 |  | Hand Fall / Lop and Scatter | Handfall |  | 5 | 54 | C106-C108 | 1 | 0 | 0 | 0 | Clearing type change based on field request
WF5_8072 | C107 | NO | 0.066851 |  | Hand Fall / Lop and Scatter | Handfall | AN | 5 | 54 | C106-C108 | 0 | 1 | 0 | 0 | Clearing type change based on field request
WF5_2316 | C108 | YES | 0.04455 |  | Hand Fall / Lop and Scatter | Handfall |  | 5 | 55 | C108-C110 | 1 | 0 | 0 | 0
WF5_6559 | C108 | YES | 0.079494 |  | Hand Fall / Lop and Scatter | Handfall |  | 5 | 55 | C108-C110 | 1 | 0 | 0 | 0
WF5_6888 | C108 | NO | 0.053026 |  | Hand Fall / Lop and Scatter | Handfall |  | 5 | 55 | C108-C110 | 1 | 0 | 0 | 0
WF5_6889 | C108 | NO | 0.088744 |  | Hand Fall / Lop and Scatter | Handfall |  | 5 | 55 | C108-C110 | 1 | 0 | 0 | 0
WF5_6890 | C108 | NO | 0.010405 |  | Hand Fall / Lop and Scatter | Handfall |  | 5 | 55 | C108-C110 | 1 | 0 | 0 | 0
WF5_6891 | C108 | NO | 0.11708 |  | Hand Fall / Lop and Scatter | Handfall |  | 5 | 55 | C108-C110 | 1 | 0 | 0 | 0
WF5_6892 | C108 | NO | 0.056425 |  | Hand Fall / Lop and Scatter | Handfall |  | 5 | 55 | C108-C110 | 1 | 0 | 0 | 0
WF5_2310 | C108 | NO | 0.71615 |  | Non-Merch Disposal | Mulch | AN | 5 | 55 | C108-C110 | 0 | 1 | 0 | 0
WF5_2314 | C108 | NO | 0.25116 |  | Retention | Retention |  | 5 | 55 | C108-C110 | 1 | 0 | 0 | 8
WF5_2315 | C108 | NO | 0.044328 |  | Retention | Retention |  | 5 | 55 | C108-C110 | 1 | 0 | 0 | 8
WF5_2318 | C108 | NO | 0.40813 |  | Retention | Retention |  | 5 | 55 | C108-C110 | 1 | 0 | 0 | 8
WF5_7643 | C108 | NO | 0.35151 |  | Harvest Processing | Non-Mulch |  | 5 | 55 | C108-C110 | 1 | 0 | 0 | 0
WF5_7770 | C108 | NO | 0.71766 |  | Harvest Processing | Non-Mulch |  | 5 | 55 | C108-C110 | 1 | 0 | 0 | 0
WF5_8056 | C108 | NO | 0.050269 |  | Hand Fall / Lop and Scatter | Handfall |  | 5 | 55 | C108-C110 | 1 | 0 | 0 | 0 | Clearing type change based on field request
WF5_8072 | C108 | NO | 0.035085 |  | Hand Fall / Lop and Scatter | Handfall | AN | 5 | 55 | C108-C110 | 0 | 1 | 0 | 0 | Clearing type change based on field request
WF5_2317 | C109 | NO | 0.22937 |  | Harvest Processing | Non-Mulch |  | 5 | 55 | C108-C110 | 1 | 0 | 0 | 0
WF5_6457 | C109 | NO | 0.18077 |  | Harvest Processing | Non-Mulch |  | 5 | 55 | C108-C110 | 1 | 0 | 0 | 0
WF5_6897 | C109 | NO | 0.062948 |  | Hand Fall / Lop and Scatter | Handfall |  | 5 | 55 | C108-C110 | 1 | 0 | 0 | 0
WF5_6898 | C109 | NO | 0.088698 |  | Hand Fall / Lop and Scatter | Handfall |  | 5 | 55 | C108-C110 | 1 | 0 | 0 | 0
WF5_6899 | C109 | NO | 0.99311 |  | Harvest Processing | Non-Mulch |  | 5 | 55 | C108-C110 | 1 | 0 | 0 | 0 | Clearing type change based on field request
WF5_2310 | C109 | NO | 0.4434 |  | Non-Merch Disposal | Mulch | AN | 5 | 55 | C108-C110 | 0 | 1 | 0 | 0
WF5_2310 | C109 | NO | 0.3028 |  | Non-Merch Disposal | Mulch | AN | 5 | 55 | C108-C110 | 0 | 1 | 0 | 0
WF5_2310 | C109 | NO | 0.14488 |  | Non-Merch Disposal | Mulch | AN | 5 | 55 | C108-C110 | 0 | 1 | 0 | 0
WF5_2310 | C109 | NO | 0.083399 |  | Non-Merch Disposal | Mulch | AN | 5 | 55 | C108-C110 | 0 | 1 | 0 | 0
WF5_2310 | C109 | NO | 0.013255 |  | Non-Merch Disposal | Mulch | AN | 5 | 56 | C110-C112 | 0 | 1 | 0 | 0
WF5_2319 | C109 | NO | 0.039634 |  | Retention | Retention |  | 5 | 55 | C108-C110 | 1 | 0 | 0 | 8
WF5_2320 | C109 | NO | 0.085978 |  | Retention | Retention |  | 5 | 55 | C108-C110 | 1 | 0 | 0 | 8
WF5_2310 | C109 | NO | 0.048209 |  | Non-Merch Disposal | Mulch | AN | 5 | 55 | C108-C110 | 0 | 1 | 0 | 0
WF5_2310 | C109 | NO | 0.048209 |  | Non-Merch Disposal | Mulch | AN | 5 | 55 | C108-C110 | 0 | 1 | 0 | 0
WF5_2323 | C110 | YES | 0.18006 |  | Hand Fall / Lop and Scatter | Handfall |  | 5 | 56 | C110-C112 | 1 | 0 | 0 | 0
WF5_2328 | C110 | YES | 0.11798 |  | Hand Fall / Lop and Scatter | Handfall |  | 5 | 56 | C110-C112 | 1 | 0 | 0 | 0
WF5_6458 | C110 | NO | 0.097886 |  | Harvest Processing | Non-Mulch |  | 5 | 56 | C110-C112 | 1 | 0 | 0 | 0
WF5_6896 | C110 | NO | 0.58002 |  | Harvest Processing | Non-Mulch |  | 5 | 56 | C110-C112 | 1 | 0 | 0 | 0 | Clearing type change based on field request
WF5_6901 | C110 | NO | 0.20274 |  | Harvest Processing | Non-Mulch |  | 5 | 56 | C110-C112 | 1 | 0 | 0 | 0 | Clearing type change based on field request
WF5_2310 | C110 | NO | 0.38567 |  | Non-Merch Disposal | Mulch | AN | 5 | 56 | C110-C112 | 0 | 1 | 0 | 0
WF5_2324 | C110 | NO | 0.083685 |  | Non Productive | Non-Treed |  | 5 | 56 | C110-C112 | 1 | 0 | 0 | 0
WF5_2321 | C110 | NO | 0.23394 |  | Retention | Retention |  | 5 | 56 | C110-C112 | 1 | 0 | 0 | 8
WF5_2322 | C110 | YES | 0.051331 |  | Retention | Retention |  | 5 | 56 | C110-C112 | 1 | 0 | 0 | 8
WF5_2325 | C110 | NO | 0.27117 |  | Retention | Retention |  | 5 | 56 | C110-C112 | 1 | 0 | 0 | 8
WF5_2330 | C110 | NO | 0.43828 |  | Retention | Retention |  | 5 | 56 | C110-C112 | 1 | 0 | 0 | 8
WF5_2332 | C110 | NO | 0.58527 |  | Retention | Retention |  | 5 | 56 | C110-C112 | 1 | 0 | 0 | 8
WF5_7644 | C110 | NO | 0.083277 |  | Harvest Processing | Non-Mulch |  | 5 | 56 | C110-C112 | 1 | 0 | 0 | 0
WF5_7645 | C110 | NO | 0.39898 |  | Harvest Processing | Non-Mulch |  | 5 | 56 | C110-C112 | 1 | 0 | 0 | 0
WF5_7771 | C110 | NO | 0.13665 |  | Harvest Processing | Non-Mulch |  | 5 | 56 | C110-C112 | 1 | 0 | 0 | 0
WF5_2327 | C111 | NO | 0.2174 |  | Harvest Processing | Non-Mulch |  | 5 | 56 | C110-C112 | 1 | 0 | 0 | 0
WF5_2331 | C111 | NO | 0.5123 |  | Harvest Processing | Non-Mulch |  | 5 | 56 | C110-C112 | 1 | 0 | 0 | 0
WF5_2329 | C111 | YES | 0.11212 |  | Hand Fall / Lop and Scatter | Handfall |  | 5 | 56 | C110-C112 | 1 | 0 | 0 | 0
WF5_2335 | C111 | YES | 0.075132 |  | Hand Fall / Lop and Scatter | Handfall |  | 5 | 56 | C110-C112 | 1 | 0 | 0 | 0
WF5_6560 | C111 | YES | 0.15822 |  | Hand Fall / Lop and Scatter | Handfall |  | 5 | 56 | C110-C112 | 1 | 0 | 0 | 0
WF5_6561 | C111 | YES | 0.10529 |  | Hand Fall / Lop and Scatter | Handfall |  | 5 | 56 | C110-C112 | 1 | 0 | 0 | 0
WF5_6563 | C111 | YES | 0.1175 |  | Hand Fall / Lop and Scatter | Handfall |  | 5 | 56 | C110-C112 | 1 | 0 | 0 | 0
WF5_6900 | C111 | NO | 0.078741 |  | Hand Fall / Lop and Scatter | Handfall |  | 5 | 56 | C110-C112 | 1 | 0 | 0 | 0
WF5_6901 | C111 | NO | 0.014033 |  | Harvest Processing | Non-Mulch |  | 5 | 56 | C110-C112 | 1 | 0 | 0 | 0 | Clearing type change based on field request
WF5_6911 | C111 | NO | 0.11136 |  | Hand Fall / Lop and Scatter | Handfall |  | 5 | 56 | C110-C112 | 1 | 0 | 0 | 0
WF5_2326 | C111 | YES | 0.27776 |  | Harvest Processing | Non-Mulch | AN | 5 | 56 | C110-C112 | 1 | 1 | 0 | 0 | Clearing type change based on field request
WF5_2337 | C111 | NO | 0.15266 |  | Non Productive | Non-Treed |  | 5 | 56 | C110-C112 | 1 | 0 | 0 | 0
WF5_2332 | C111 | NO | 0.81049 |  | Retention | Retention |  | 5 | 56 | C110-C112 | 1 | 0 | 0 | 8
WF5_2340 | C112 | YES | 0.10193 |  | Hand Fall / Lop and Scatter | Handfall |  | 5 | 57 | C112-C114 | 1 | 0 | 0 | 0
WF5_6562 | C112 | YES | 0.01277 |  | Hand Fall / Lop and Scatter | Handfall |  | 5 | 57 | C112-C114 | 1 | 0 | 0 | 0
WF5_6564 | C112 | YES | 0.06398 |  | Hand Fall / Lop and Scatter | Handfall |  | 5 | 57 | C112-C114 | 1 | 0 | 0 | 0
WF5_6912 | C112 | NO | 0.099146 |  | Hand Fall / Lop and Scatter | Handfall |  | 5 | 57 | C112-C114 | 1 | 0 | 0 | 0
WF5_2337 | C112 | NO | 0.14499 |  | Non Productive | Non-Treed |  | 5 | 57 | C112-C114 | 1 | 0 | 0 | 0
WF5_2343 | C112 | NO | 0.018775 |  | Non Productive | Non-Treed |  | 5 | 57 | C112-C114 | 1 | 0 | 0 | 0
WF5_2336 | C112 | NO | 0.49146 |  | Retention | Retention |  | 5 | 57 | C112-C114 | 1 | 0 | 0 | 8
WF5_7647 | C112 | NO | 1.0683 |  | Harvest Processing | Non-Mulch |  | 5 | 57 | C112-C114 | 1 | 0 | 0 | 0
WF5_7713 | C112 | YES | 0.052136 |  | Hand Fall / Lop and Scatter | Handfall |  | 5 | 57 | C112-C114 | 1 | 0 | 0 | 0
WF5_7802 | C112 | YES | 0.071379 |  | Hand Fall / Lop and Scatter | Handfall |  | 5 | 57 | C112-C114 | 1 | 0 | 0 | 0
WF5_6908 | C113 | NO | 0.13377 |  | Hand Fall / Lop and Scatter | Handfall |  | 5 | 57 | C112-C114 | 1 | 0 | 0 | 0
WF5_6909 | C113 | NO | 0.07249 |  | Hand Fall / Lop and Scatter | Handfall |  | 5 | 57 | C112-C114 | 1 | 0 | 0 | 0
WF5_6910 | C113 | NO | 0.031688 |  | Hand Fall / Lop and Scatter | Handfall |  | 5 | 57 | C112-C114 | 1 | 0 | 0 | 0
WF5_2342 | C113 | NO | 0.062295 |  | Harvest Processing | Non-Mulch | AN | 5 | 57 | C112-C114 | 0 | 1 | 0 | 0
WF5_2344 | C113 | NO | 0.045165 |  | Non Productive | Non-Treed |  | 5 | 57 | C112-C114 | 1 | 0 | 0 | 0
WF5_2347 | C113 | NO | 0.01272 |  | Non Productive | Non-Treed |  | 5 | 57 | C112-C114 | 1 | 0 | 0 | 0
WF5_2345 | C113 | NO | 0.3228 |  | Retention | Retention |  | 5 | 57 | C112-C114 | 1 | 0 | 0 | 8
WF5_7648 | C113 | NO | 0.95851 |  | Harvest Processing | Non-Mulch |  | 5 | 57 | C112-C114 | 1 | 0 | 0 | 0
WF5_7803 | C113 | YES | 0.024706 |  | Hand Fall / Lop and Scatter | Handfall |  | 5 | 57 | C112-C114 | 1 | 0 | 0 | 0
WF5_6905 | C114 | NO | 0.073905 |  | Hand Fall / Lop and Scatter | Handfall |  | 5 | 58 | C114-C116 | 1 | 0 | 0 | 0
WF5_6906 | C114 | NO | 0.24823 |  | Hand Fall / Lop and Scatter | Handfall |  | 5 | 58 | C114-C116 | 1 | 0 | 0 | 0
WF5_6907 | C114 | NO | 0.016182 |  | Hand Fall / Lop and Scatter | Handfall |  | 5 | 58 | C114-C116 | 1 | 0 | 0 | 0
WF5_2346 | C114 | NO | 0.15058 |  | Retention | Retention |  | 5 | 58 | C114-C116 | 1 | 0 | 0 | 8
WF5_2348 | C114 | NO | 0.10177 |  | Retention | Retention |  | 5 | 58 | C114-C116 | 1 | 0 | 0 | 8
WF5_7649 | C114 | NO | 1.1885 |  | Harvest Processing | Non-Mulch |  | 5 | 58 | C114-C116 | 1 | 0 | 0 | 0
WF5_7829 | C114 | NO | 0.14704 |  | Hand Fall / Lop and Scatter | Handfall |  | 5 | 58 | C114-C116 | 1 | 0 | 0 | 0
WF5_6903 | C115 | NO | 0.27611 |  | Hand Fall / Lop and Scatter | Handfall |  | 5 | 58 | C114-C116 | 1 | 0 | 0 | 0
WF5_2353 | C115 | NO | 0.18612 |  | Non-Merch Disposal | Mulch | AN | 5 | 58 | C114-C116 | 0 | 1 | 0 | 0
WF5_2356 | C115 | NO | 0.27612 |  | Non-Merch Disposal | Mulch | AN | 5 | 58 | C114-C116 | 0 | 1 | 0 | 0
WF5_2360 | C115 | NO | 0.0045028 |  | Non-Merch Disposal | Mulch | AN | 5 | 58 | C114-C116 | 0 | 1 | 0 | 0
WF5_7650 | C115 | NO | 1.0285 |  | Harvest Processing | Non-Mulch |  | 5 | 58 | C114-C116 | 1 | 0 | 0 | 0
WF5_7898 | C115 | NO | 0.24255 |  | Hand Fall / Lop and Scatter | Handfall |  | 5 | 58 | C114-C116 | 1 | 0 | 0 | 0 | Clearing type change based on field request
WF5_2351 | C116 | YES | 0.017334 |  | Hand Fall / Lop and Scatter | Handfall |  | 5 | 59 | C116-C118 | 1 | 0 | 0 | 0
WF5_2355 | C116 | YES | 0.15918 |  | Hand Fall / Lop and Scatter | Handfall |  | 5 | 59 | C116-C118 | 1 | 0 | 0 | 0
WF5_6565 | C116 | YES | 0.063433 |  | Hand Fall / Lop and Scatter | Handfall |  | 5 | 59 | C116-C118 | 1 | 0 | 0 | 0
WF5_6566 | C116 | YES | 0.040969 |  | Hand Fall / Lop and Scatter | Handfall |  | 5 | 59 | C116-C118 | 1 | 0 | 0 | 0
WF5_6902 | C116 | NO | 0.013849 |  | Hand Fall / Lop and Scatter | Handfall |  | 5 | 59 | C116-C118 | 1 | 0 | 0 | 0
WF5_6904 | C116 | NO | 0.035847 |  | Hand Fall / Lop and Scatter | Handfall |  | 5 | 59 | C116-C118 | 1 | 0 | 0 | 0
WF5_2360 | C116 | NO | 0.08723 |  | Non-Merch Disposal | Mulch | AN | 5 | 59 | C116-C118 | 0 | 1 | 0 | 0
WF5_2350 | C116 | NO | 1.4024 |  | Non Productive | Non-Treed |  | 5 | 59 | C116-C118 | 1 | 0 | 0 | 0
WF5_2349 | C116 | YES | 0.12049 |  | Retention | Retention |  | 5 | 59 | C116-C118 | 1 | 0 | 0 | 8
WF5_2352 | C116 | YES | 0.076175 |  | Retention | Retention |  | 5 | 59 | C116-C118 | 1 | 0 | 0 | 8
WF5_2354 | C116 | YES | 0.086232 |  | Retention | Retention |  | 5 | 59 | C116-C118 | 1 | 0 | 0 | 8
WF5_2359 | C116 | YES | 0.053088 |  | Retention | Retention |  | 5 | 59 | C116-C118 | 1 | 0 | 0 | 8
WF5_7646 | C116 | NO | 0.29761 |  | Hand Fall / Lop and Scatter | Handfall |  | 5 | 59 | C116-C118 | 1 | 0 | 0 | 0 | Clearing type change based on field request
WF5_7651 | C116 | NO | 0.38417 |  | Harvest Processing | Non-Mulch |  | 5 | 59 | C116-C118 | 1 | 0 | 0 | 0
WF5_2361 | C117 | NO | 0.067577 |  | Retention | Retention |  | 5 | 59 | C116-C118 | 1 | 0 | 0 | 8
WF5_7652 | C117 | NO | 1.8555 |  | Harvest Processing | Non-Mulch |  | 5 | 59 | C116-C118 | 1 | 0 | 0 | 0
WF5_2363 | C118 | NO | 0.04153 |  | Harvest Processing | Non-Mulch |  | 5 | 60 | C118-C120 | 1 | 0 | 0 | 0
WF5_2357 | C118 | NO | 1.7578 |  | Harvest Processing | Non-Mulch |  | 5 | 60 | C118-C120 | 1 | 0 | 0 | 0
WF5_2364 | C118 | NO | 0.011584 |  | Harvest Processing | Non-Mulch |  | 5 | 60 | C118-C120 | 1 | 0 | 0 | 0
WF5_6913 | C118 | NO | 0.096073 |  | Hand Fall / Lop and Scatter | Handfall |  | 5 | 60 | C118-C120 | 1 | 0 | 0 | 0
WF5_6916 | C118 | NO | 0.10383 |  | Hand Fall / Lop and Scatter | Handfall |  | 5 | 60 | C118-C120 | 1 | 0 | 0 | 0
WF5_2362 | C118 | NO | 0.14656 |  | Retention | Retention |  | 5 | 60 | C118-C120 | 1 | 0 | 0 | 8
WF5_7653 | C118 | NO | 0.10851 |  | Hand Fall / Lop and Scatter | Handfall |  | 5 | 60 | C118-C120 | 1 | 0 | 0 | 0 | Clearing type change based on field request
WF5_6915 | C119 | NO | 0.70943 |  | Hand Fall / Lop and Scatter | Handfall |  | 5 | 60 | C118-C120 | 1 | 0 | 0 | 0
WF5_6917 | C119 | NO | 0.034731 |  | Hand Fall / Lop and Scatter | Handfall |  | 5 | 60 | C118-C120 | 1 | 0 | 0 | 0
WF5_2368 | C119 | NO | 0.25203 |  | Non-Merch Disposal | Mulch | AU1 | 5 | 60 | C118-C120 | 0 | 1 | 0 | 0
WF5_2368 | C119 | NO | 0.21664 |  | Non-Merch Disposal | Mulch | AU1 | 5 | 60 | C118-C120 | 0 | 1 | 0 | 0
WF5_2365 | C119 | NO | 0.071552 |  | Retention | Retention |  | 5 | 60 | C118-C120 | 1 | 0 | 0 | 8
WF5_7657 | C119 | NO | 0.25611 |  | Harvest Processing | Non-Mulch |  | 5 | 60 | C118-C120 | 1 | 0 | 0 | 0
WF5_7830 | C119 | NO | 0.026716 |  | Hand Fall / Lop and Scatter | Handfall |  | 5 | 60 | C118-C120 | 1 | 0 | 0 | 0
WF5_7899 | C119 | NO | 0.37315 |  | Hand Fall / Lop and Scatter | Handfall |  | 5 | 60 | C118-C120 | 1 | 0 | 0 | 0 | Clearing type change based on field request
WF5_8070 | C119 | NO | 0.23812 |  | Hand Fall / Lop and Scatter | Handfall |  | 5 | 60 | C118-C120 | 1 | 0 | 0 | 0 | Clearing type change based on field request
WF5_6162 | C120 | NO | 0.1723 |  | Non-Merch Disposal | Mulch | AN | 5 | 61 | C120-C122 | 0 | 1 | 0 | 0
WF5_2366 | C120 | NO | 0.089991 |  | Retention | Retention |  | 5 | 61 | C120-C122 | 1 | 0 | 0 | 8
WF5_2367 | C120 | NO | 0.052064 |  | Retention | Retention |  | 5 | 61 | C120-C122 | 1 | 0 | 0 | 8
WF5_7656 | C120 | NO | 2.0672 |  | Harvest Processing | Non-Mulch |  | 5 | 61 | C120-C122 | 1 | 0 | 0 | 0
WF5_8033 | C120 | NO | 0.094428 |  | Hand Fall / Lop and Scatter | Handfall |  | 5 | 61 | C120-C122 | 1 | 0 | 0 | 0 | Clearing type change based on field request
WF5_6914 | C121 | NO | 0.12495 |  | Hand Fall / Lop and Scatter | Handfall |  | 5 | 61 | C120-C122 | 1 | 0 | 0 | 0
WF5_2369 | C121 | NO | 0.094871 |  | Retention | Retention |  | 5 | 61 | C120-C122 | 1 | 0 | 0 | 8
WF5_7654 | C121 | NO | 1.6673 |  | Harvest Processing | Non-Mulch |  | 5 | 61 | C120-C122 | 1 | 0 | 0 | 0
WF5_8034 | C121 | NO | 0.13635 |  | Hand Fall / Lop and Scatter | Handfall |  | 5 | 61 | C120-C122 | 1 | 0 | 0 | 0 | Clearing type change based on field request
WF5_8035 | C121 | NO | 0.062134 |  | Hand Fall / Lop and Scatter | Handfall |  | 5 | 61 | C120-C122 | 1 | 0 | 0 | 0 | Clearing type change based on field request
WF5_2370 | C122 | NO | 0.036332 |  | Harvest Processing | Non-Mulch |  | 5 | 62 | C122-C124 | 1 | 0 | 0 | 0
WF5_2374 | C122 | NO | 0.21902 |  | Non-Merch Disposal | Mulch |  | 5 | 62 | C122-C124 | 1 | 0 | 0 | 0
WF5_2371 | C122 | NO | 0.38656 |  | Non Productive | Non-Treed |  | 5 | 62 | C122-C124 | 1 | 0 | 0 | 0
WF5_7655 | C122 | NO | 0.91956 |  | Harvest Processing | Non-Mulch |  | 5 | 62 | C122-C124 | 1 | 0 | 0 | 0
WF5_2373 | C123 | NO | 0.36656 |  | Non-Merch Disposal | Mulch |  | 5 | 62 | C122-C124 | 1 | 0 | 0 | 0
WF5_2374 | C123 | NO | 0.23909 |  | Non-Merch Disposal | Mulch |  | 5 | 62 | C122-C124 | 1 | 0 | 0 | 0
WF5_2376 | C123 | NO | 1.0252 |  | Harvest Processing | Non-Mulch |  | 5 | 62 | C122-C124 | 1 | 0 | 0 | 0
WF5_2371 | C123 | NO | 0.29334 |  | Non Productive | Non-Treed |  | 5 | 62 | C122-C124 | 1 | 0 | 0 | 0
WF5_2375 | C123 | NO | 0.12168 |  | Non Productive | Non-Treed |  | 5 | 62 | C122-C124 | 1 | 0 | 0 | 0
WF5_2372 | C123 | NO | 0.11559 |  | Retention | Retention |  | 5 | 62 | C122-C124 | 1 | 0 | 0 | 8
WF5_2376 | C124 | NO | 0.13223 |  | Harvest Processing | Non-Mulch |  | 5 | 63 | C124-C126 | 1 | 0 | 0 | 0
WF5_2378 | C124 | NO | 1.7768 |  | Harvest Processing | Non-Mulch |  | 5 | 63 | C124-C126 | 1 | 0 | 0 | 0
WF5_2377 | C124 | NO | 0.1142 |  | Non Productive | Non-Treed |  | 5 | 63 | C124-C126 | 1 | 0 | 0 | 0
WF5_2379 | C124 | NO | 0.099251 |  | Retention | Retention |  | 5 | 63 | C124-C126 | 1 | 0 | 0 | 8
WF5_2380 | C125 | NO | 0.023676 |  | Harvest Processing | Non-Mulch |  | 5 | 63 | C124-C126 | 1 | 0 | 0 | 0
WF5_2378 | C125 | NO | 1.5941 |  | Harvest Processing | Non-Mulch |  | 5 | 63 | C124-C126 | 1 | 0 | 0 | 0
WF5_2384 | C125 | NO | 0.22397 |  | Harvest Processing | Non-Mulch |  | 5 | 63 | C124-C126 | 1 | 0 | 0 | 0
WF5_2381 | C125 | NO | 0.19704 |  | Retention | Retention |  | 5 | 63 | C124-C126 | 1 | 0 | 0 | 8
WF5_2382 | C125 | NO | 0.11025 |  | Retention | Retention |  | 5 | 63 | C124-C126 | 1 | 0 | 0 | 8
WF5_8057 | C125 | NO | 0.091528 |  | Hand Fall / Lop and Scatter | Handfall |  | 5 | 63 | C124-C126 | 1 | 0 | 0 | 0 | Clearing type change based on field request
WF5_2384 | C126 | NO | 2.3231 |  | Harvest Processing | Non-Mulch |  | 5 | 64 | C126-C128 | 1 | 0 | 0 | 0
WF5_2385 | C126 | NO | 0.02913 |  | Harvest Processing | Non-Mulch |  | 5 | 64 | C126-C128 | 1 | 0 | 0 | 0
WF5_2386 | C126 | NO | 0.031655 |  | Harvest Processing | Non-Mulch |  | 5 | 64 | C126-C128 | 1 | 0 | 0 | 0
WF5_2384 | C127 | NO | 1.89 |  | Harvest Processing | Non-Mulch |  | 5 | 64 | C126-C128 | 1 | 0 | 0 | 0
WF5_2895 | C128 | NO | 0.29402 |  | Non-Merch Disposal | Mulch | AU1 | 5 | 65 | C128-C129 | 0 | 1 | 0 | 0
WF5_2388 | C128 | NO | 0.56531 |  | Hand Fall / Lop and Scatter | Handfall |  | 5 | 65 | C128-C129 | 1 | 0 | 0 | 0 | Clearing type change based on field request
WF5_6918 | C128 | NO | 0.55306 |  | Hand Fall / Lop and Scatter | Handfall |  | 5 | 65 | C128-C129 | 1 | 0 | 0 | 0
WF5_7291 | C128 | NO | 0.23112 |  | Hand Fall / Lop and Scatter | Handfall |  | 5 | 65 | C128-C129 | 1 | 0 | 0 | 0 | Clearing type change based on field request
WF5_2384 | C128 | NO | 0.095013 |  | Harvest Processing | Non-Mulch |  | 5 | 65 | C128-C129 | 1 | 0 | 0 | 0
WF5_2387 | C128 | NO | 0.30481 |  | Non Productive | Non-Treed |  | 5 | 65 | C128-C129 | 1 | 0 | 0 | 0
WF5_2389 | C128 | NO | 0.11115 |  | Retention | Retention |  | 5 | 65 | C128-C129 | 1 | 0 | 0 | 8
WF6_2402 | C129 | YES | 0.028122 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 1 | C129-C131 | 1 | 0 | 0 | 0
WF6_2403 | C129 | YES | 0.038143 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 1 | C129-C131 | 1 | 0 | 0 | 0
WF5_2388 | C129 | NO | 0.078628 |  | Hand Fall / Lop and Scatter | Handfall |  | 5 | 1 | C129-C131 | 1 | 0 | 0 | 0 | Clearing type change based on field request
WF5_2390 | C129 | NO | 0.042984 |  | Hand Fall / Lop and Scatter | Handfall |  | 5 | 1 | C129-C131 | 1 | 0 | 0 | 0 | Clearing type change based on field request
WF5_2397 | C129 | NO | 0.02056 |  | Harvest Processing | Non-Mulch |  | 5 | 1 | C129-C131 | 1 | 0 | 0 | 0
WF5_2404 | C129 | NO | 0.053949 |  | Harvest Processing | Non-Mulch |  | 5 | 1 | C129-C131 | 1 | 0 | 0 | 0
WF6_7043 | C129 | YES | 0.23764 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 1 | C129-C131 | 1 | 0 | 0 | 0
WF6_7184 | C129 | NO | 0.097484 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 1 | C129-C131 | 1 | 0 | 0 | 0
WF6_2400 | C129 | NO | 1.1467 |  | Harvest Processing | Non-Mulch |  | 6 | 1 | C129-C131 | 1 | 0 | 0 | 0
WF6_2391 | C129 | NO | 0.027951 |  | Non Productive | Non-Treed |  | 6 | 1 | C129-C131 | 1 | 0 | 0 | 0
WF6_2395 | C129 | NO | 0.09076 |  | Non Productive | Non-Treed |  | 6 | 1 | C129-C131 | 1 | 0 | 0 | 0
WF6_2394 | C129 | YES | 0.028843 |  | Retention | Retention |  | 6 | 1 | C129-C131 | 1 | 0 | 0 | 8
WF6_2396 | C129 | YES | 0.06116 |  | Retention | Retention |  | 6 | 1 | C129-C131 | 1 | 0 | 0 | 8
WF6_2405 | C129 | YES | 0.15933 |  | Retention | Retention |  | 6 | 1 | C129-C131 | 1 | 0 | 0 | 8
WF6_2408 | C129 | NO | 0.078111 |  | Retention | Retention |  | 6 | 1 | C129-C131 | 1 | 0 | 0 | 8
WF6_2409 | C129 | NO | 0.06475 |  | Retention | Retention |  | 6 | 1 | C129-C131 | 1 | 0 | 0 | 8
WF6_2413 | C129 | NO | 0.17114 |  | Retention | Retention |  | 6 | 1 | C129-C131 | 1 | 0 | 0 | 8
WF6_2400 | C130 | NO | 1.7871 |  | Harvest Processing | Non-Mulch |  | 6 | 1 | C129-C131 | 1 | 0 | 0 | 0
WF6_2414 | C130 | NO | 0.055606 |  | Retention | Retention |  | 6 | 1 | C129-C131 | 1 | 0 | 0 | 8
WF6_2400 | C131 | NO | 1.6871 |  | Harvest Processing | Non-Mulch |  | 6 | 2 | C131-C133 | 1 | 0 | 0 | 0
WF6_2416 | C131 | NO | 0.22394 |  | Harvest Processing | Non-Mulch |  | 6 | 2 | C131-C133 | 1 | 0 | 0 | 0
WF6_2415 | C131 | NO | 0.066456 |  | Retention | Retention |  | 6 | 2 | C131-C133 | 1 | 0 | 0 | 8
WF6_2416 | C132 | NO | 1.5186 |  | Harvest Processing | Non-Mulch |  | 6 | 2 | C131-C133 | 1 | 0 | 0 | 0
WF6_2416 | C133 | NO | 1.9621 |  | Harvest Processing | Non-Mulch |  | 6 | 3 | C133-C135 | 1 | 0 | 0 | 0
WF6_2422 | C133 | NO | 0.22394 |  | Harvest Processing | Non-Mulch |  | 6 | 3 | C133-C135 | 1 | 0 | 0 | 0
WF6_2420 | C133 | NO | 0.017745 |  | Retention | Retention |  | 6 | 3 | C133-C135 | 1 | 0 | 0 | 8
WF6_2421 | C133 | NO | 0.052322 |  | Retention | Retention |  | 6 | 3 | C133-C135 | 1 | 0 | 0 | 8
WF6_2424 | C133 | NO | 0.084027 |  | Retention | Retention |  | 6 | 3 | C133-C135 | 1 | 0 | 0 | 8
WF6_2423 | C134 | NO | 0.051534 |  | Non-Merch Disposal | Mulch |  | 6 | 3 | C133-C135 | 1 | 0 | 0 | 0
WF6_2422 | C134 | NO | 2.077 |  | Harvest Processing | Non-Mulch |  | 6 | 3 | C133-C135 | 1 | 0 | 0 | 0
WF6_2422 | C135 | NO | 1.6064 |  | Harvest Processing | Non-Mulch |  | 6 | 4 | C135-C137 | 1 | 0 | 0 | 0
WF6_6333 | C136 | NO | 0.61679 |  | Non-Merch Disposal | Mulch | AU1 | 6 | 8 | C137-C139 | 0 | 1 | 0 | 0
WF6_6113 | C136 | NO | 0.61312 |  | Non-Merch Disposal | Mulch | AU1 | 6 | 8 | C137-C139 | 0 | 1 | 0 | 0
WF6_6404 | C136 | NO | 0.36074 |  | Non-Merch Disposal | Mulch | AU2 | 6 | 6 | C137-C139 | 0 | 1 | 0 | 0
WF6_6404 | C136 | NO | 0.35024 |  | Non-Merch Disposal | Mulch | AU2 | 6 | 7 | C137-C139 | 0 | 1 | 0 | 0
WF6_6404 | C136 | NO | 0.19713 |  | Non-Merch Disposal | Mulch | AU2 | 6 | 7 | C137-C139 | 0 | 1 | 0 | 0
WF6_6404 | C136 | NO | 0.015937 |  | Non-Merch Disposal | Mulch | AU2 | 6 | 7 | C137-C139 | 0 | 1 | 0 | 0
WF6_6100 | C136 | NO | 0.27461 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 4 | C135-C137 | 0 | 1 | 0 | 0
WF6_6100 | C136 | NO | 0.65728 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 4 | C135-C137 | 0 | 1 | 0 | 0
WF6_6100 | C136 | NO | 0.098753 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 6 | C137-C139 | 0 | 1 | 0 | 0
WF6_2288 | C136 | NO | 0.16013 |  | Non-Merch Disposal | Mulch | AU2 | 6 | 6 | C137-C139 | 0 | 1 | 0 | 0
WF6_2288 | C136 | NO | 0.1806 |  | Non-Merch Disposal | Mulch | AU2 | 6 | 6 | C137-C139 | 0 | 1 | 0 | 0
WF6_2288 | C136 | NO | 0.35396 |  | Non-Merch Disposal | Mulch | AU2 | 6 | 7 | C137-C139 | 0 | 1 | 0 | 0
WF6_2288 | C136 | NO | 0.19274 |  | Non-Merch Disposal | Mulch | AU2 | 6 | 7 | C137-C139 | 0 | 1 | 0 | 0
WF6_2288 | C136 | NO | 0.037811 |  | Non-Merch Disposal | Mulch | AU2 | 6 | 7 | C137-C139 | 0 | 1 | 0 | 0
WF6_2422 | C136 | NO | 1.7855 |  | Harvest Processing | Non-Mulch |  | 6 | 4 | C135-C137 | 1 | 0 | 0 | 0
WF6_2426 | C136 | NO | 0.52039 |  | Retention | Retention |  | 6 | 4 | C135-C137 | 1 | 0 | 0 | 8
WF6_2427 | C136 | NO | 0.099778 |  | Retention | Retention |  | 6 | 4 | C135-C137 | 1 | 0 | 0 | 8
WF6_7044 | C137 | YES | 0.0214 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 5 | C137-C139 | 1 | 0 | 0 | 0
WF6_7185 | C137 | NO | 0.03056 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 5 | C137-C139 | 1 | 0 | 0 | 0
WF6_7186 | C137 | NO | 0.25585 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 5 | C137-C139 | 1 | 0 | 0 | 0
WF6_6404 | C137 | NO | 0.016617 |  | Non-Merch Disposal | Mulch | AU2 | 6 | 6 | C137-C139 | 0 | 1 | 0 | 0
WF6_2428 | C137 | YES | 0.025255 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 5 | C137-C139 | 1 | 0 | 0 | 0
WF6_6101 | C137 | NO | 0.19908 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 5 | C137-C139 | 0 | 1 | 0 | 0
WF6_6101 | C137 | NO | 0.058764 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 5 | C137-C139 | 0 | 1 | 0 | 0
WF6_6101 | C137 | NO | 0.86918 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 6 | C137-C139 | 0 | 1 | 0 | 0
WF6_2288 | C137 | NO | 0.011718 |  | Non-Merch Disposal | Mulch | AU2 | 6 | 6 | C137-C139 | 0 | 1 | 0 | 0
WF6_2422 | C137 | NO | 0.30569 |  | Harvest Processing | Non-Mulch |  | 6 | 5 | C137-C139 | 1 | 0 | 0 | 0
WF6_2431 | C137 | NO | 0.061102 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 5 | C137-C139 | 1 | 0 | 0 | 0
WF6_2437 | C137 | YES | 0.041782 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 5 | C137-C139 | 1 | 0 | 0 | 0
WF6_2438 | C137 | YES | 0.066729 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 5 | C137-C139 | 1 | 0 | 0 | 0
WF6_2430 | C137 | NO | 2.8077 |  | Non Productive | Non-Treed |  | 6 | 5 | C137-C139 | 1 | 0 | 0 | 0
WF6_2429 | C137 | YES | 0.083748 |  | Retention | Retention |  | 6 | 5 | C137-C139 | 1 | 0 | 0 | 8
WF6_2432 | C137 | NO | 0.069034 |  | Retention | Retention |  | 6 | 5 | C137-C139 | 1 | 0 | 0 | 8
WF6_2433 | C137 | YES | 0.070748 |  | Retention | Retention |  | 6 | 5 | C137-C139 | 1 | 0 | 0 | 8
WF6_2434 | C137 | NO | 0.040107 |  | Retention | Retention |  | 6 | 5 | C137-C139 | 1 | 0 | 0 | 8
WF6_2439 | C137 | YES | 0.094722 |  | Retention | Retention |  | 6 | 5 | C137-C139 | 1 | 0 | 0 | 8
WF6_7188 | C138 | NO | 0.080796 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 5 | C137-C139 | 1 | 0 | 0 | 0
WF6_2436 | C138 | NO | 0.284 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 5 | C137-C139 | 0 | 1 | 0 | 0
WF6_6101 | C138 | NO | 0.24158 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 5 | C137-C139 | 0 | 1 | 0 | 0
WF6_2435 | C138 | NO | 0.85062 |  | Harvest Processing | Non-Mulch |  | 6 | 5 | C137-C139 | 1 | 0 | 0 | 0
WF6_2440 | C138 | NO | 0.33827 |  | Retention | Retention |  | 6 | 5 | C137-C139 | 1 | 0 | 0 | 8
WF6_7772 | C138 | NO | 0.67921 |  | Harvest Processing | Non-Mulch |  | 6 | 5 | C137-C139 | 1 | 0 | 0 | 0
WF6_7876 | C138 | NO | 0.50235 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 5 | C137-C139 | 1 | 0 | 0 | 0
WF6_6335 | C139 | NO | 0.089704 |  | Harvest Disposal | Mulch |  | 6 | 9 | C139-C141 | 1 | 0 | 0 | 0
WF6_6459 | C139 | NO | 0.13768 |  | Harvest Processing | Non-Mulch |  | 6 | 9 | C139-C141 | 1 | 0 | 0 | 0
WF6_7079 | C139 | NO | 0.20339 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 9 | C139-C141 | 1 | 0 | 0 | 0
WF6_7080 | C139 | NO | 0.58828 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 9 | C139-C141 | 1 | 0 | 0 | 0
WF6_7081 | C139 | NO | 0.078884 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 9 | C139-C141 | 1 | 0 | 0 | 0
WF6_7189 | C139 | NO | 0.075276 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 9 | C139-C141 | 1 | 0 | 0 | 0
WF6_2441 | C139 | NO | 0.30942 |  | Harvest Disposal | Mulch |  | 6 | 9 | C139-C141 | 1 | 0 | 0 | 0
WF6_2444 | C139 | NO | 0.077326 |  | Harvest Disposal | Mulch |  | 6 | 9 | C139-C141 | 1 | 0 | 0 | 0
WF6_2445 | C139 | NO | 0.14643 |  | Harvest Processing | Non-Mulch |  | 6 | 9 | C139-C141 | 1 | 0 | 0 | 0
WF6_2443 | C139 | NO | 0.043126 |  | Non Productive | Non-Treed |  | 6 | 9 | C139-C141 | 1 | 0 | 0 | 0
WF6_2442 | C139 | NO | 0.17106 |  | Retention | Retention |  | 6 | 9 | C139-C141 | 1 | 0 | 0 | 8
WF6_2446 | C139 | NO | 0.30339 |  | Retention | Retention |  | 6 | 9 | C139-C141 | 1 | 0 | 0 | 8
WF6_7259 | C139 | NO | 0.039859 |  | Non Productive | Non-Treed |  | 6 | 9 | C139-C141 | 1 | 0 | 0 | 0
WF6_7190 | C140 | NO | 0.044526 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 9 | C139-C141 | 1 | 0 | 0 | 0
WF6_2450 | C140 | NO | 0.037091 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 9 | C139-C141 | 0 | 1 | 0 | 0
WF6_2445 | C140 | NO | 2.0508 |  | Harvest Processing | Non-Mulch |  | 6 | 9 | C139-C141 | 1 | 0 | 0 | 0
WF6_7877 | C140 | NO | 0.18456 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 9 | C139-C141 | 1 | 0 | 0 | 0
WF6_6336 | C141 | NO | 0.19083 |  | Harvest Disposal | Mulch |  | 6 | 10 | C141-C143 | 1 | 0 | 0 | 0
WF6_7082 | C141 | NO | 0.077691 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 10 | C141-C143 | 1 | 0 | 0 | 0
WF6_7083 | C141 | NO | 0.36252 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 10 | C141-C143 | 1 | 0 | 0 | 0
WF6_2447 | C141 | NO | 0.084783 |  | Harvest Disposal | Mulch |  | 6 | 10 | C141-C143 | 1 | 0 | 0 | 0
WF6_2460 | C141 | NO | 0.19837 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 10 | C141-C143 | 0 | 1 | 0 | 0
WF6_2460 | C141 | NO | 0.11191 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 10 | C141-C143 | 0 | 1 | 0 | 0
WF6_2445 | C141 | NO | 0.88692 |  | Harvest Processing | Non-Mulch |  | 6 | 10 | C141-C143 | 1 | 0 | 0 | 0
WF6_7500 | C141 | YES | 0.019469 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 10 | C141-C143 | 1 | 0 | 0 | 0
WF6_7730 | C141 | NO | 0.2308 |  | Harvest Disposal | Mulch |  | 6 | 10 | C141-C143 | 1 | 0 | 0 | 0
WF6_7851 | C141 | YES | 0.010114 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 10 | C141-C143 | 1 | 0 | 0 | 0
WF6_2452 | C142 | YES | 0.058356 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 10 | C141-C143 | 1 | 0 | 0 | 0
WF6_2455 | C142 | YES | 0.011223 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 10 | C141-C143 | 1 | 0 | 0 | 0
WF6_2457 | C142 | YES | 0.039444 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 10 | C141-C143 | 1 | 0 | 0 | 0
WF6_2459 | C142 | YES | 0.021274 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 10 | C141-C143 | 1 | 0 | 0 | 0
WF6_6337 | C142 | NO | 0.083654 |  | Harvest Disposal | Mulch |  | 6 | 10 | C141-C143 | 1 | 0 | 0 | 0
WF6_7045 | C142 | YES | 0.17682 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 10 | C141-C143 | 1 | 0 | 0 | 0
WF6_7084 | C142 | NO | 0.013761 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 10 | C141-C143 | 1 | 0 | 0 | 0
WF6_7191 | C142 | NO | 0.25236 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 10 | C141-C143 | 1 | 0 | 0 | 0
WF6_2460 | C142 | NO | 1.4734 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 10 | C141-C143 | 0 | 1 | 0 | 0
WF6_2460 | C142 | NO | 0.086568 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 11 | C143-C145 | 0 | 1 | 0 | 0
WF6_2458 | C142 | NO | 0.18565 |  | Harvest Processing | Non-Mulch |  | 6 | 10 | C141-C143 | 1 | 0 | 0 | 0
WF6_2453 | C142 | NO | 0.019596 |  | Non Productive | Non-Treed |  | 6 | 10 | C141-C143 | 1 | 0 | 0 | 0
WF6_2454 | C142 | NO | 0.48723 |  | Non Productive | Non-Treed |  | 6 | 10 | C141-C143 | 1 | 0 | 0 | 0
WF6_2449 | C142 | YES | 0.90975 |  | Retention | Retention |  | 6 | 10 | C141-C143 | 1 | 0 | 0 | 8
WF6_2456 | C142 | NO | 0.16981 |  | Retention | Retention |  | 6 | 10 | C141-C143 | 1 | 0 | 0 | 8
WF6_2451 | C143 | NO | 0.72605 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 11 | C143-C145 | 0 | 1 | 0 | 0
WF6_2460 | C143 | NO | 0.087117 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 11 | C143-C145 | 0 | 1 | 0 | 0
WF6_2460 | C143 | NO | 1.9525 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 11 | C143-C145 | 0 | 1 | 0 | 0
WF6_2570 | C143 | NO | 0.31408 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 11 | C143-C145 | 0 | 1 | 0 | 0
WF6_2458 | C143 | NO | 2.0832 |  | Harvest Processing | Non-Mulch |  | 6 | 11 | C143-C145 | 1 | 0 | 0 | 0
WF6_2462 | C143 | NO | 0.149 |  | Retention | Retention |  | 6 | 11 | C143-C145 | 1 | 0 | 0 | 8
WF6_2467 | C143 | NO | 0.28823 |  | Retention | Retention |  | 6 | 11 | C143-C145 | 1 | 0 | 0 | 8
WF6_7085 | C144 | NO | 0.83519 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 11 | C143-C145 | 1 | 0 | 0 | 0
WF6_7192 | C144 | NO | 0.019699 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 11 | C143-C145 | 1 | 0 | 0 | 0
WF6_7193 | C144 | NO | 0.067386 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 11 | C143-C145 | 1 | 0 | 0 | 0
WF6_2460 | C144 | NO | 0.070062 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 11 | C143-C145 | 0 | 1 | 0 | 0
WF6_2466 | C144 | NO | 0.020399 |  | Harvest Disposal | Mulch |  | 6 | 11 | C143-C145 | 1 | 0 | 0 | 0
WF6_2458 | C144 | NO | 0.47431 |  | Harvest Processing | Non-Mulch |  | 6 | 11 | C143-C145 | 1 | 0 | 0 | 0
WF6_2468 | C144 | NO | 0.13149 |  | Harvest Processing | Non-Mulch |  | 6 | 11 | C143-C145 | 1 | 0 | 0 | 0 | Reduced retention area due to violation in C145-C146 (BMC-TRN-1349/1358)
WF6_2470 | C144 | NO | 0.18096 |  | Retention | Retention |  | 6 | 11 | C143-C145 | 1 | 0 | 0 | 8
WF6_2468 | C144 | NO | 0.03268 |  | Harvest Processing | Non-Mulch |  | 6 | 11 | C143-C145 | 1 | 0 | 0 | 0 | Reduced retention area due to violation in C145-C146 (BMC-TRN-1349/1358)
WF6_2468 | C144 | NO | 0.031172 |  | Harvest Processing | Non-Mulch |  | 6 | 12 | C145-C148 | 1 | 0 | 0 | 0 | Reduced retention area due to violation in C145-C146 (BMC-TRN-1349/1358)
WF6_6460 | C145 | NO | 0.28023 |  | Harvest Processing | Non-Mulch |  | 6 | 12 | C145-C148 | 1 | 0 | 0 | 0
WF6_7194 | C145 | NO | 0.48016 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 12 | C145-C148 | 1 | 0 | 0 | 0
WF6_2461 | C145 | NO | 0.49097 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 12 | C145-C148 | 0 | 1 | 0 | 0
WF6_2489 | C145 | NO | 0.15458 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 12 | C145-C148 | 0 | 1 | 0 | 0
WF6_2489 | C145 | NO | 0.68502 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 12 | C145-C148 | 0 | 1 | 0 | 0
WF6_2570 | C145 | NO | 0.20297 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 11 | C143-C145 | 0 | 1 | 0 | 0
WF6_2570 | C145 | NO | 0.4134 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 12 | C145-C148 | 0 | 1 | 0 | 0
WF6_2468 | C145 | NO | 0.85388 |  | Harvest Processing | Non-Mulch |  | 6 | 12 | C145-C148 | 1 | 0 | 0 | 0 | Reduced retention area due to violation in C145-C146 (BMC-TRN-1349/1358)
WF6_2472 | C145 | NO | 0.04773 |  | Harvest Processing | Non-Mulch |  | 6 | 12 | C145-C148 | 1 | 0 | 0 | 0
WF6_2471 | C145 | NO | 0.039246 |  | Non Productive | Non-Treed |  | 6 | 12 | C145-C148 | 1 | 0 | 0 | 0
WF6_2469 | C145 | NO | 0.21394 |  | Retention | Retention |  | 6 | 12 | C145-C148 | 1 | 0 | 0 | 8
WF6_2473 | C145 | NO | 0.069853 |  | Retention | Retention |  | 6 | 12 | C145-C148 | 1 | 0 | 0 | 8
WF6_2477 | C145 | NO | 0.12136 |  | Retention | Retention |  | 6 | 12 | C145-C148 | 1 | 0 | 0 | 8
WF6_2481 | C145 | NO | 0.19199 |  | Retention | Retention |  | 6 | 12 | C145-C148 | 1 | 0 | 0 | 8
WF6_7195 | C146 | NO | 0.063593 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 12 | C145-C148 | 1 | 0 | 0 | 0
WF6_2461 | C146 | NO | 0.081137 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 12 | C145-C148 | 0 | 1 | 0 | 0
WF6_2495 | C146 | NO | 0.50919 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 12 | C145-C148 | 0 | 1 | 0 | 0
WF6_2479 | C146 | NO | 1.854 |  | Harvest Processing | Non-Mulch |  | 6 | 12 | C145-C148 | 1 | 0 | 0 | 0
WF6_2478 | C146 | NO | 0.041319 |  | Non Productive | Non-Treed |  | 6 | 12 | C145-C148 | 1 | 0 | 0 | 0
WF6_2482 | C146 | NO | 0.1511 |  | Retention | Retention |  | 6 | 12 | C145-C148 | 1 | 0 | 0 | 8
WF6_2487 | C146 | NO | 0.11939 |  | Retention | Retention |  | 6 | 12 | C145-C148 | 1 | 0 | 0 | 8
WF6_7725 | C146 | YES | 0.014877 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 12 | C145-C148 | 1 | 0 | 0 | 0
WF6_7773 | C146 | NO | 0.16897 |  | Harvest Processing | Non-Mulch |  | 6 | 12 | C145-C148 | 1 | 0 | 0 | 0
WF6_2483 | C148 | YES | 0.32931 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 13 | C148-C150 | 1 | 0 | 0 | 0
WF6_2488 | C148 | YES | 0.16339 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 13 | C148-C150 | 1 | 0 | 0 | 0
WF6_2493 | C148 | YES | 0.1423 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 13 | C148-C150 | 1 | 0 | 0 | 0
WF6_2497 | C148 | YES | 0.053696 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 13 | C148-C150 | 1 | 0 | 0 | 0
WF6_7196 | C148 | NO | 0.011447 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 13 | C148-C150 | 1 | 0 | 0 | 0
WF6_7198 | C148 | NO | 0.034789 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 13 | C148-C150 | 1 | 0 | 0 | 0
WF6_2507 | C148 | NO | 0.70054 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 13 | C148-C150 | 0 | 1 | 0 | 0
WF6_2479 | C148 | NO | 0.071075 |  | Harvest Processing | Non-Mulch |  | 6 | 13 | C148-C150 | 1 | 0 | 0 | 0
WF6_2491 | C148 | NO | 0.31089 |  | Harvest Processing | Non-Mulch |  | 6 | 13 | C148-C150 | 1 | 0 | 0 | 0
WF6_2484 | C148 | NO | 0.1897 |  | Non Productive | Non-Treed |  | 6 | 13 | C148-C150 | 1 | 0 | 0 | 0
WF6_2486 | C148 | NO | 0.63736 |  | Non Productive | Non-Treed |  | 6 | 13 | C148-C150 | 1 | 0 | 0 | 0
WF6_2485 | C148 | YES | 0.15006 |  | Retention | Retention |  | 6 | 13 | C148-C150 | 1 | 0 | 0 | 8
WF6_2490 | C148 | NO | 0.1409 |  | Retention | Retention |  | 6 | 13 | C148-C150 | 1 | 0 | 0 | 8
WF6_2494 | C148 | YES | 0.15827 |  | Retention | Retention |  | 6 | 13 | C148-C150 | 1 | 0 | 0 | 8
WF6_2496 | C148 | YES | 0.012699 |  | Retention | Retention |  | 6 | 13 | C148-C150 | 1 | 0 | 0 | 8
WF6_7260 | C148 | NO | 0.049331 |  | Non Productive | Non-Treed |  | 6 | 13 | C148-C150 | 1 | 0 | 0 | 0
WF6_7261 | C148 | NO | 0.023063 |  | Non Productive | Non-Treed |  | 6 | 13 | C148-C150 | 1 | 0 | 0 | 0
WF6_6461 | C149 | NO | 1.2114 |  | Harvest Processing | Non-Mulch |  | 6 | 13 | C148-C150 | 1 | 0 | 0 | 0
WF6_7197 | C149 | NO | 0.28443 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 13 | C148-C150 | 1 | 0 | 0 | 0
WF6_2492 | C149 | NO | 0.10401 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 13 | C148-C150 | 0 | 1 | 0 | 0
WF6_2499 | C149 | NO | 0.68626 |  | Harvest Disposal | Mulch |  | 6 | 13 | C148-C150 | 1 | 0 | 0 | 0
WF6_2499 | C149 | NO | 0.014928 |  | Harvest Disposal | Mulch |  | 6 | 14 | C150-C152 | 1 | 0 | 0 | 0
WF6_2507 | C149 | NO | 0.20846 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 13 | C148-C150 | 0 | 1 | 0 | 0
WF6_2491 | C149 | NO | 0.37823 |  | Harvest Processing | Non-Mulch |  | 6 | 13 | C148-C150 | 1 | 0 | 0 | 0
WF6_2498 | C149 | NO | 0.10965 |  | Non Productive | Non-Treed |  | 6 | 13 | C148-C150 | 1 | 0 | 0 | 0
WF6_2502 | C149 | NO | 0.11995 |  | Retention | Retention |  | 6 | 13 | C148-C150 | 1 | 0 | 0 | 8
WF6_2520 | C151 | YES | 0.09587 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 14 | C150-C152 | 1 | 0 | 0 | 0
WF6_2521 | C151 | NO | 0.043577 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 14 | C150-C152 | 1 | 0 | 0 | 0
WF6_2501 | C151 | NO | 0.099837 |  | Harvest Disposal | Mulch |  | 6 | 14 | C150-C152 | 1 | 0 | 0 | 0
WF6_2508 | C151 | NO | 0.33768 |  | Harvest Disposal | Mulch |  | 6 | 14 | C150-C152 | 1 | 0 | 0 | 0
WF6_2519 | C151 | NO | 0.20704 |  | Harvest Processing | Non-Mulch |  | 6 | 14 | C150-C152 | 1 | 0 | 0 | 0
WF6_7086 | C151 | NO | 0.57795 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 14 | C150-C152 | 1 | 0 | 0 | 0
WF6_7087 | C151 | NO | 0.43899 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 14 | C150-C152 | 1 | 0 | 0 | 0
WF6_7088 | C151 | NO | 0.14539 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 14 | C150-C152 | 1 | 0 | 0 | 0
WF6_2492 | C151 | NO | 0.62628 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 14 | C150-C152 | 0 | 1 | 0 | 0
WF6_2499 | C151 | NO | 0.068394 |  | Harvest Disposal | Mulch |  | 6 | 14 | C150-C152 | 1 | 0 | 0 | 0
WF6_2505 | C151 | NO | 0.57178 |  | Non Productive | Non-Treed |  | 6 | 14 | C150-C152 | 1 | 0 | 0 | 0
WF6_2511 | C151 | NO | 0.036366 |  | Non Productive | Non-Treed |  | 6 | 14 | C150-C152 | 1 | 0 | 0 | 0
WF6_2513 | C151 | NO | 2.4667 |  | Non Productive | Non-Treed |  | 6 | 14 | C150-C152 | 1 | 0 | 0 | 0
WF6_2518 | C151 | NO | 0.077743 |  | Non Productive | Non-Treed |  | 6 | 14 | C150-C152 | 1 | 0 | 0 | 0
WF6_2500 | C151 | NO | 0.80604 |  | Retention | Retention |  | 6 | 14 | C150-C152 | 1 | 0 | 0 | 8
WF6_2509 | C151 | NO | 0.18488 |  | Retention | Retention |  | 6 | 14 | C150-C152 | 1 | 0 | 0 | 8
WF6_2510 | C151 | NO | 0.16738 |  | Retention | Retention |  | 6 | 14 | C150-C152 | 1 | 0 | 0 | 8
WF6_2512 | C151 | NO | 0.48491 |  | Retention | Retention |  | 6 | 14 | C150-C152 | 1 | 0 | 0 | 8
WF6_2517 | C151 | YES | 0.16707 |  | Retention | Retention |  | 6 | 14 | C150-C152 | 1 | 0 | 0 | 8
WF6_2525 | C151 | YES | 0.26637 |  | Retention | Retention |  | 6 | 14 | C150-C152 | 1 | 0 | 0 | 8
WF6_2515 | C151 | NO | 0.14909 |  | Retention | Retention |  | 6 | 14 | C150-C152 | 1 | 0 | 0 | 8
WF6_7262 | C151 | NO | 0.025711 |  | Non Productive | Non-Treed |  | 6 | 14 | C150-C152 | 1 | 0 | 0 | 0
WF6_7263 | C151 | NO | 0.054775 |  | Non Productive | Non-Treed |  | 6 | 14 | C150-C152 | 1 | 0 | 0 | 0
WF6_7857 | C151 | NO | 0.37041 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 14 | C150-C152 | 1 | 0 | 0 | 0
WF6_2464 | C152 | NO | 0.043125 |  | Non-Merch Disposal | Mulch | AU1 | 6 | 15 | C152-C154 | 0 | 1 | 0 | 0
WF6_6338 | C152 | NO | 0.037734 |  | Non-Merch Disposal | Mulch | AU1 | 6 | 15 | C152-C154 | 0 | 1 | 0 | 0
WF6_2480 | C152 | NO | 0.18666 |  | Non-Merch Disposal | Mulch | AU2 | 6 | 15 | C152-C154 | 0 | 1 | 0 | 0
WF6_2480 | C152 | NO | 0.25269 |  | Non-Merch Disposal | Mulch | AU2 | 6 | 15 | C152-C154 | 0 | 1 | 0 | 0
WF6_2522 | C152 | NO | 0.035624 |  | Non Productive | Non-Treed |  | 6 | 15 | C152-C154 | 1 | 0 | 0 | 0
WF6_2524 | C152 | NO | 0.21008 |  | Retention | Retention |  | 6 | 15 | C152-C154 | 1 | 0 | 0 | 8
WF6_7658 | C152 | NO | 1.5862 |  | Harvest Processing | Non-Mulch |  | 6 | 15 | C152-C154 | 1 | 0 | 0 | 0
WF6_7660 | C152 | NO | 1.2336 |  | Harvest Processing | Non-Mulch |  | 6 | 15 | C152-C154 | 1 | 0 | 0 | 0
WF6_2526 | C153 | NO | 0.10319 |  | Harvest Processing | Non-Mulch | ANWIN | 6 | 15 | C152-C154 | 0 | 1 | 0 | 0
WF6_7659 | C153 | NO | 2.1478 |  | Harvest Processing | Non-Mulch |  | 6 | 15 | C152-C154 | 1 | 0 | 0 | 0
WF6_2523 | C154 | NO | 0.42967 |  | Harvest Processing | Non-Mulch |  | 6 | 16 | C154-C156 | 1 | 0 | 0 | 0
WF6_7089 | C154 | NO | 0.65107 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 16 | C154-C156 | 1 | 0 | 0 | 0
WF6_7091 | C154 | NO | 0.30376 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 16 | C154-C156 | 1 | 0 | 0 | 0
WF6_2530 | C154 | NO | 0.10923 |  | Harvest Disposal | Mulch |  | 6 | 16 | C154-C156 | 1 | 0 | 0 | 0
WF6_2528 | C154 | NO | 0.076976 |  | Non Productive | Non-Treed |  | 6 | 16 | C154-C156 | 1 | 0 | 0 | 0
WF6_2527 | C154 | NO | 0.35162 |  | Retention | Retention |  | 6 | 16 | C154-C156 | 1 | 0 | 0 | 8
WF6_2529 | C154 | NO | 0.16454 |  | Retention | Retention |  | 6 | 16 | C154-C156 | 1 | 0 | 0 | 8
WF6_2531 | C154 | NO | 0.13976 |  | Retention | Retention |  | 6 | 16 | C154-C156 | 1 | 0 | 0 | 8
WF6_7090 | C155 | NO | 0.82923 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 16 | C154-C156 | 1 | 0 | 0 | 0
WF6_2516 | C155 | NO | 0.27488 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 16 | C154-C156 | 0 | 1 | 0 | 0
WF6_2516 | C155 | NO | 0.27083 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 16 | C154-C156 | 0 | 1 | 0 | 0
WF6_2516 | C155 | NO | 0.29812 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 16 | C154-C156 | 0 | 1 | 0 | 0
WF6_2530 | C155 | NO | 0.59154 |  | Harvest Disposal | Mulch |  | 6 | 16 | C154-C156 | 1 | 0 | 0 | 0
WF6_6406 | C156 | NO | 0.24621 |  | Non-Merch Disposal | Mulch | AU1 | 6 | 19 | C156-C158 | 0 | 1 | 0 | 0
WF6_6115 | C156 | NO | 0.24163 |  | Non-Merch Disposal | Mulch | AU1 | 6 | 19 | C156-C158 | 0 | 1 | 0 | 0
WF6_7092 | C156 | NO | 0.16452 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 17 | C156-C158 | 1 | 0 | 0 | 0
WF6_2530 | C156 | NO | 2.1884 |  | Harvest Disposal | Mulch |  | 6 | 17 | C156-C158 | 1 | 0 | 0 | 0
WF6_2572 | C156 | NO | 0.15561 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 17 | C156-C158 | 0 | 1 | 0 | 0
WF6_2572 | C156 | NO | 0.028348 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 17 | C156-C158 | 0 | 1 | 0 | 0
WF6_2572 | C156 | NO | 0.899 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 18 | C156-C158 | 0 | 1 | 0 | 0
WF6_2533 | C156 | NO | 0.096645 |  | Retention | Retention |  | 6 | 17 | C156-C158 | 1 | 0 | 0 | 8
WF6_7046 | C157 | YES | 0.14579 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 17 | C156-C158 | 1 | 0 | 0 | 0
WF6_7093 | C157 | NO | 1.0079 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 17 | C156-C158 | 1 | 0 | 0 | 0
WF6_2542 | C157 | YES | 0.061137 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 17 | C156-C158 | 1 | 0 | 0 | 0
WF6_2530 | C157 | NO | 0.31183 |  | Harvest Disposal | Mulch |  | 6 | 17 | C156-C158 | 1 | 0 | 0 | 0
WF6_2535 | C157 | NO | 0.1388 |  | Non-Merch Disposal | Mulch |  | 6 | 17 | C156-C158 | 1 | 0 | 0 | 0
WF6_2548 | C157 | YES | 0.088784 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 17 | C156-C158 | 1 | 0 | 0 | 0
WF6_2550 | C157 | NO | 0.014131 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 17 | C156-C158 | 1 | 0 | 0 | 0
WF6_2534 | C157 | NO | 0.28199 |  | Retention | Retention |  | 6 | 17 | C156-C158 | 1 | 0 | 0 | 8
WF6_2555 | C157 | NO | 0.061689 |  | Retention | Retention |  | 6 | 17 | C156-C158 | 1 | 0 | 0 | 8
WF6_7048 | C158 | YES | 0.10647 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 20 | C158-C160 | 1 | 0 | 0 | 0
WF6_7094 | C158 | NO | 0.019833 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 20 | C158-C160 | 1 | 0 | 0 | 0
WF6_6342 | C158 | NO | 0.042617 |  | Non-Merch Disposal | Mulch | AU2 | 6 | 20 | C158-C160 | 0 | 1 | 0 | 0
WF6_6342 | C158 | NO | 0.010947 |  | Non-Merch Disposal | Mulch | AU2 | 6 | 20 | C158-C160 | 0 | 1 | 0 | 0
WF6_2544 | C158 | YES | 0.058211 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 20 | C158-C160 | 1 | 0 | 0 | 0
WF6_2535 | C158 | NO | 0.37447 |  | Non-Merch Disposal | Mulch |  | 6 | 20 | C158-C160 | 1 | 0 | 0 | 0
WF6_2537 | C158 | NO | 1.4269 |  | Non-Merch Disposal | Mulch |  | 6 | 20 | C158-C160 | 1 | 0 | 0 | 0
WF6_2574 | C158 | NO | 0.042909 |  | Non-Merch Disposal | Mulch | AU2 | 6 | 20 | C158-C160 | 0 | 1 | 0 | 0
WF6_2574 | C158 | NO | 0.015608 |  | Non-Merch Disposal | Mulch | AU2 | 6 | 20 | C158-C160 | 0 | 1 | 0 | 0
WF6_2536 | C158 | NO | 0.13955 |  | Retention | Retention |  | 6 | 20 | C158-C160 | 1 | 0 | 0 | 8
WF6_2556 | C158 | NO | 0.13517 |  | Retention | Retention |  | 6 | 20 | C158-C160 | 1 | 0 | 0 | 8
WF6_2552 | C159 | YES | 0.14867 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 20 | C158-C160 | 1 | 0 | 0 | 0
WF6_7095 | C159 | NO | 0.34434 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 20 | C158-C160 | 1 | 0 | 0 | 0
WF6_2537 | C159 | NO | 0.68017 |  | Non-Merch Disposal | Mulch |  | 6 | 20 | C158-C160 | 1 | 0 | 0 | 0
WF6_2538 | C159 | NO | 0.086391 |  | Retention | Retention |  | 6 | 20 | C158-C160 | 1 | 0 | 0 | 8
WF6_2539 | C159 | NO | 0.19795 |  | Retention | Retention |  | 6 | 20 | C158-C160 | 1 | 0 | 0 | 8
WF6_2557 | C159 | NO | 0.29359 |  | Retention | Retention |  | 6 | 20 | C158-C160 | 1 | 0 | 0 | 8
WF6_7731 | C159 | NO | 0.62383 |  | Non-Merch Disposal | Mulch |  | 6 | 20 | C158-C160 | 1 | 0 | 0 | 0
WF6_6340 | C160 | NO | 1.7153 |  | Non-Merch Disposal | Mulch |  | 6 | 21 | C160-C162 | 1 | 0 | 0 | 0
WF6_2541 | C160 | NO | 0.43062 |  | Non-Merch Disposal | Mulch |  | 6 | 21 | C160-C162 | 1 | 0 | 0 | 0
WF6_2540 | C160 | NO | 0.11478 |  | Non Productive | Non-Treed |  | 6 | 21 | C160-C162 | 1 | 0 | 0 | 0
WF6_2541 | C161 | NO | 2.2964 |  | Non-Merch Disposal | Mulch |  | 6 | 21 | C160-C162 | 1 | 0 | 0 | 0
WF6_7047 | C162 | YES | 0.4515 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 22 | C162-C164 | 1 | 0 | 0 | 0
WF6_7096 | C162 | NO | 0.10892 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 22 | C162-C164 | 1 | 0 | 0 | 0
WF6_7097 | C162 | NO | 0.055834 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 22 | C162-C164 | 1 | 0 | 0 | 0
WF6_2543 | C162 | YES | 0.057548 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 22 | C162-C164 | 1 | 0 | 0 | 0
WF6_2541 | C162 | NO | 0.018924 |  | Non-Merch Disposal | Mulch |  | 6 | 21 | C160-C162 | 1 | 0 | 0 | 0
WF6_2541 | C162 | NO | 0.94825 |  | Non-Merch Disposal | Mulch |  | 6 | 22 | C162-C164 | 1 | 0 | 0 | 0
WF6_2546 | C162 | NO | 0.48593 |  | Non-Merch Disposal | Mulch |  | 6 | 22 | C162-C164 | 1 | 0 | 0 | 0
WF6_2545 | C162 | YES | 0.10122 |  | Retention | Retention |  | 6 | 22 | C162-C164 | 1 | 0 | 0 | 8
WF6_2558 | C162 | NO | 0.07434 |  | Retention | Retention |  | 6 | 22 | C162-C164 | 1 | 0 | 0 | 8
WF6_2546 | C163 | NO | 2.2169 |  | Non-Merch Disposal | Mulch |  | 6 | 22 | C162-C164 | 1 | 0 | 0 | 0
WF6_7098 | C164 | NO | 0.060644 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 23 | C164-C166 | 1 | 0 | 0 | 0
WF6_7099 | C164 | NO | 0.010821 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 23 | C164-C166 | 1 | 0 | 0 | 0
WF6_2546 | C164 | NO | 0.20999 |  | Non-Merch Disposal | Mulch |  | 6 | 23 | C164-C166 | 1 | 0 | 0 | 0
WF6_2549 | C164 | NO | 1.9567 |  | Harvest Disposal | Mulch |  | 6 | 23 | C164-C166 | 1 | 0 | 0 | 0
WF6_2547 | C164 | NO | 0.052652 |  | Retention | Retention |  | 6 | 23 | C164-C166 | 1 | 0 | 0 | 8
WF6_2559 | C164 | NO | 0.046272 |  | Retention | Retention |  | 6 | 23 | C164-C166 | 1 | 0 | 0 | 8
WF6_2549 | C165 | NO | 1.5329 |  | Harvest Disposal | Mulch |  | 6 | 23 | C164-C166 | 1 | 0 | 0 | 0
WF6_2551 | C165 | NO | 0.13053 |  | Retention | Retention |  | 6 | 23 | C164-C166 | 1 | 0 | 0 | 8
WF6_2549 | C166 | NO | 0.45926 |  | Harvest Disposal | Mulch |  | 6 | 24 | C166-C168 | 1 | 0 | 0 | 0
WF6_2553 | C166 | NO | 1.3113 |  | Non-Merch Disposal | Mulch |  | 6 | 24 | C166-C168 | 1 | 0 | 0 | 0
WF6_2554 | C166 | NO | 0.049653 |  | Non Productive | Non-Treed |  | 6 | 24 | C166-C168 | 1 | 0 | 0 | 0
WF6_2553 | C167 | NO | 0.70793 |  | Non-Merch Disposal | Mulch |  | 6 | 24 | C166-C168 | 1 | 0 | 0 | 0
WF6_2561 | C167 | NO | 0.85254 |  | Non-Merch Disposal | Mulch |  | 6 | 24 | C166-C168 | 1 | 0 | 0 | 0
WF6_2564 | C167 | NO | 0.58385 |  | Harvest Disposal | Mulch |  | 6 | 24 | C166-C168 | 1 | 0 | 0 | 0
WF6_2560 | C167 | NO | 0.036613 |  | Non Productive | Non-Treed |  | 6 | 24 | C166-C168 | 1 | 0 | 0 | 0
WF6_6341 | C168 | NO | 1.3505 |  | Harvest Disposal | Mulch |  | 6 | 25 | C168-C170 | 1 | 0 | 0 | 0
WF6_7100 | C168 | NO | 0.49916 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 25 | C168-C170 | 1 | 0 | 0 | 0
WF6_7101 | C168 | NO | 0.055486 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 25 | C168-C170 | 1 | 0 | 0 | 0
WF6_2562 | C168 | NO | 0.17689 |  | Harvest Disposal | Mulch | ANWIN | 6 | 25 | C168-C170 | 0 | 1 | 0 | 0
WF6_2564 | C168 | NO | 0.21239 |  | Harvest Disposal | Mulch |  | 6 | 25 | C168-C170 | 1 | 0 | 0 | 0
WF6_2583 | C168 | NO | 0.19606 |  | Retention | Retention |  | 6 | 25 | C168-C170 | 1 | 0 | 0 | 8
WF6_2568 | C169 | NO | 0.045745 |  | Harvest Disposal | Mulch |  | 6 | 25 | C168-C170 | 1 | 0 | 0 | 0
WF6_7102 | C169 | NO | 0.072506 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 25 | C168-C170 | 1 | 0 | 0 | 0
WF6_2566 | C169 | NO | 0.13072 |  | Harvest Disposal | Mulch |  | 6 | 25 | C168-C170 | 1 | 0 | 0 | 0
WF6_2567 | C169 | NO | 0.025441 |  | Non Productive | Non-Treed |  | 6 | 25 | C168-C170 | 1 | 0 | 0 | 0
WF6_2569 | C169 | NO | 0.44246 |  | Retention | Retention |  | 6 | 25 | C168-C170 | 1 | 0 | 0 | 8
WF6_2582 | C169 | NO | 0.40217 |  | Retention | Retention |  | 6 | 25 | C168-C170 | 1 | 0 | 0 | 8
WF6_7732 | C169 | NO | 0.70586 |  | Harvest Disposal | Mulch |  | 6 | 25 | C168-C170 | 1 | 0 | 0 | 0
WF6_2592 | C170 | YES | 0.06275 |  | Retention | Retention |  | 6 | 26 | C170-C172 | 1 | 0 | 0 | 0 | Changed to retention as per review of clearance
WF6_2578 | C170 | NO | 0.0135 |  | Harvest Disposal | Mulch |  | 6 | 26 | C170-C172 | 1 | 0 | 0 | 0
WF6_2594 | C170 | NO | 0.085007 |  | Retention | Retention |  | 6 | 26 | C170-C172 | 1 | 0 | 0 | 0 | Changed to retention as per review of clearance
WF6_3738 | C170 | NO | 0.014217 |  | Harvest Disposal | Mulch |  | 6 | 26 | C170-C172 | 1 | 0 | 0 | 0
WF6_2580 | C170 | YES | 0.13297 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 26 | C170-C172 | 1 | 0 | 0 | 0
WF6_2581 | C170 | YES | 0.11946 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 26 | C170-C172 | 1 | 0 | 0 | 0
WF6_7103 | C170 | NO | 0.48748 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 26 | C170-C172 | 1 | 0 | 0 | 0
WF6_7104 | C170 | NO | 0.47462 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 26 | C170-C172 | 1 | 0 | 0 | 0
WF6_2566 | C170 | NO | 0.26845 |  | Harvest Disposal | Mulch |  | 6 | 26 | C170-C172 | 1 | 0 | 0 | 0
WF6_2579 | C170 | NO | 0.28467 |  | Harvest Disposal | Mulch |  | 6 | 26 | C170-C172 | 1 | 0 | 0 | 0
WF6_2576 | C170 | NO | 0.31347 |  | Non Productive | Non-Treed |  | 6 | 26 | C170-C172 | 1 | 0 | 0 | 0
WF6_2565 | C170 | NO | 0.49975 |  | Retention | Retention |  | 6 | 26 | C170-C172 | 1 | 0 | 0 | 8
WF6_2573 | C170 | NO | 0.31289 |  | Retention | Retention |  | 6 | 26 | C170-C172 | 1 | 0 | 0 | 8
WF6_2582 | C170 | NO | 0.010744 |  | Retention | Retention |  | 6 | 25 | C168-C170 | 1 | 0 | 0 | 8
WF6_2582 | C170 | NO | 1.0109 |  | Retention | Retention |  | 6 | 26 | C170-C172 | 1 | 0 | 0 | 8
WF6_2589 | C170 | NO | 0.6653 |  | Retention | Retention |  | 6 | 26 | C170-C172 | 1 | 0 | 0 | 8
WF6_7264 | C170 | NO | 0.018536 |  | Non Productive | Non-Treed |  | 6 | 26 | C170-C172 | 1 | 0 | 0 | 0
WF6_7532 | C170 | NO | 0.033908 |  | Harvest Disposal | Mulch |  | 6 | 26 | C170-C172 | 1 | 0 | 0 | 0
WF6_7533 | C170 | NO | 0.046237 |  | Retention | Retention |  | 6 | 26 | C170-C172 | 1 | 0 | 0 | 0 | Changed to retention as per review of clearance
WF6_7732 | C170 | NO | 0.092017 |  | Harvest Disposal | Mulch |  | 6 | 26 | C170-C172 | 1 | 0 | 0 | 0
WF6_2603 | C171 | YES | 0.044923 |  | Retention | Retention |  | 6 | 26 | C170-C172 | 1 | 0 | 0 | 0 | Changed to retention as per review of clearance
WF6_2590 | C171 | NO | 0.03518 |  | Harvest Disposal | Mulch |  | 6 | 26 | C170-C172 | 1 | 0 | 0 | 0
WF6_2584 | C171 | YES | 0.088083 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 26 | C170-C172 | 1 | 0 | 0 | 0
WF6_2585 | C171 | YES | 0.28755 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 26 | C170-C172 | 1 | 0 | 0 | 0
WF6_7049 | C171 | YES | 0.093333 |  | Retention | Retention |  | 6 | 26 | C170-C172 | 1 | 0 | 0 | 0 | Changed to retention as per review of clearance
WF6_7105 | C171 | NO | 1.2434 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 26 | C170-C172 | 1 | 0 | 0 | 0
WF6_7106 | C171 | NO | 0.12009 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 26 | C170-C172 | 1 | 0 | 0 | 0
WF6_7108 | C171 | NO | 0.3064 |  | Retention | Retention |  | 6 | 26 | C170-C172 | 1 | 0 | 0 | 0 | Changed to retention as per review of clearance
WF6_2579 | C171 | NO | 0.64878 |  | Harvest Disposal | Mulch |  | 6 | 26 | C170-C172 | 1 | 0 | 0 | 0
WF6_2586 | C171 | NO | 0.32962 |  | Harvest Disposal | Mulch |  | 6 | 26 | C170-C172 | 1 | 0 | 0 | 0
WF6_2616 | C171 | NO | 0.36778 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 26 | C170-C172 | 0 | 1 | 0 | 0
WF6_2589 | C171 | NO | 0.48927 |  | Retention | Retention |  | 6 | 26 | C170-C172 | 1 | 0 | 0 | 8
WF6_2593 | C171 | NO | 0.65044 |  | Retention | Retention |  | 6 | 26 | C170-C172 | 1 | 0 | 0 | 8
WF6_7501 | C171 | YES | 0.1032 |  | Retention | Retention |  | 6 | 26 | C170-C172 | 1 | 0 | 0 | 0 | Changed to retention as per review of clearance
WF6_7533 | C171 | NO | 0.22278 |  | Retention | Retention |  | 6 | 26 | C170-C172 | 1 | 0 | 0 | 0 | Changed to retention as per review of clearance
WF6_2591 | C171 | NO | 0.17331 |  | Harvest Disposal | Mulch |  | 6 | 26 | C170-C172 | 1 | 0 | 0 | 0
WF6_2604 | C172 | YES | 0.13403 |  | Retention | Retention |  | 6 | 27 | C172-C174 | 1 | 0 | 0 | 0 | Changed to retention as per review of clearance
WF6_2607 | C172 | NO | 0.014423 |  | Harvest Disposal | Mulch |  | 6 | 27 | C172-C174 | 1 | 0 | 0 | 0
WF6_2588 | C172 | YES | 0.17089 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 27 | C172-C174 | 1 | 0 | 0 | 0
WF6_2600 | C172 | NO | 0.026805 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 27 | C172-C174 | 1 | 0 | 0 | 0
WF6_7107 | C172 | NO | 0.35845 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 27 | C172-C174 | 1 | 0 | 0 | 0
WF6_7109 | C172 | NO | 0.05275 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 27 | C172-C174 | 1 | 0 | 0 | 0
WF6_2586 | C172 | NO | 0.018702 |  | Harvest Disposal | Mulch |  | 6 | 26 | C170-C172 | 1 | 0 | 0 | 0
WF6_2586 | C172 | NO | 0.23855 |  | Harvest Disposal | Mulch |  | 6 | 27 | C172-C174 | 1 | 0 | 0 | 0
WF6_2605 | C172 | NO | 0.56282 |  | Harvest Disposal | Mulch |  | 6 | 27 | C172-C174 | 1 | 0 | 0 | 0
WF6_2616 | C172 | NO | 0.012588 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 26 | C170-C172 | 0 | 1 | 0 | 0
WF6_2616 | C172 | NO | 0.12933 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 27 | C172-C174 | 0 | 1 | 0 | 0
WF6_2596 | C172 | NO | 1.1028 |  | Retention | Retention |  | 6 | 27 | C172-C174 | 1 | 0 | 0 | 8
WF6_7858 | C172 | NO | 0.05621 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 27 | C172-C174 | 1 | 0 | 0 | 0
WF6_2606 | C173 | YES | 0.021305 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 27 | C172-C174 | 1 | 0 | 0 | 0
WF6_7050 | C173 | YES | 0.33055 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 27 | C172-C174 | 1 | 0 | 0 | 0
WF6_7110 | C173 | NO | 0.10912 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 27 | C172-C174 | 1 | 0 | 0 | 0
WF6_2605 | C173 | NO | 0.95339 |  | Harvest Disposal | Mulch |  | 6 | 27 | C172-C174 | 1 | 0 | 0 | 0
WF6_2609 | C173 | NO | 0.33105 |  | Harvest Disposal | Mulch |  | 6 | 27 | C172-C174 | 1 | 0 | 0 | 0
WF6_2609 | C174 | NO | 1.4573 |  | Harvest Disposal | Mulch |  | 6 | 28 | C174-C176 | 1 | 0 | 0 | 0
WF6_2614 | C175 | YES | 0.022294 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 28 | C174-C176 | 1 | 0 | 0 | 0
WF6_7051 | C175 | YES | 0.18694 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 28 | C174-C176 | 1 | 0 | 0 | 0
WF6_7053 | C175 | YES | 0.056678 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 28 | C174-C176 | 1 | 0 | 0 | 0
WF6_7111 | C175 | NO | 0.44678 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 28 | C174-C176 | 1 | 0 | 0 | 0
WF6_2609 | C175 | NO | 0.27904 |  | Harvest Disposal | Mulch |  | 6 | 28 | C174-C176 | 1 | 0 | 0 | 0
WF6_2610 | C175 | NO | 0.087473 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 28 | C174-C176 | 0 | 1 | 0 | 0
WF6_2631 | C175 | NO | 0.10404 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 28 | C174-C176 | 0 | 1 | 0 | 0
WF6_2619 | C175 | NO | 0.21817 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 28 | C174-C176 | 1 | 0 | 0 | 0
WF6_7852 | C175 | YES | 0.15621 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 28 | C174-C176 | 1 | 0 | 0 | 0
WF6_7052 | C176 | YES | 0.96733 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 29 | C176-C178 | 1 | 0 | 0 | 0
WF6_7112 | C176 | NO | 0.98284 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 29 | C176-C178 | 1 | 0 | 0 | 0
WF6_7113 | C176 | NO | 0.032321 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 29 | C176-C178 | 1 | 0 | 0 | 0
WF6_2598 | C176 | NO | 0.12837 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 29 | C176-C178 | 0 | 1 | 0 | 0
WF6_2599 | C176 | NO | 0.01176 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 29 | C176-C178 | 0 | 1 | 0 | 0
WF6_2613 | C176 | NO | 0.11276 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 29 | C176-C178 | 0 | 1 | 0 | 0
WF6_2618 | C176 | NO | 0.55037 |  | Harvest Disposal | Mulch |  | 6 | 29 | C176-C178 | 1 | 0 | 0 | 0
WF6_2619 | C176 | NO | 0.015359 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 29 | C176-C178 | 1 | 0 | 0 | 0
WF6_2622 | C177 | YES | 0.028565 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 29 | C176-C178 | 1 | 0 | 0 | 0
WF6_2620 | C177 | YES | 0.34456 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 29 | C176-C178 | 1 | 0 | 0 | 0
WF6_2623 | C177 | NO | 0.10356 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 29 | C176-C178 | 1 | 0 | 0 | 0
WF6_7054 | C177 | YES | 0.6263 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 29 | C176-C178 | 1 | 0 | 0 | 0
WF6_7114 | C177 | NO | 0.033976 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 29 | C176-C178 | 1 | 0 | 0 | 0
WF6_2595 | C177 | NO | 0.32553 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 29 | C176-C178 | 0 | 1 | 0 | 0
WF6_2599 | C177 | NO | 0.041341 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 29 | C176-C178 | 0 | 1 | 0 | 0
WF6_2612 | C177 | NO | 0.31168 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 29 | C176-C178 | 0 | 1 | 0 | 0
WF6_2618 | C177 | NO | 0.28989 |  | Harvest Disposal | Mulch |  | 6 | 29 | C176-C178 | 1 | 0 | 0 | 0
WF6_2625 | C177 | NO | 0.39961 |  | Harvest Disposal | Mulch |  | 6 | 29 | C176-C178 | 1 | 0 | 0 | 0
WF6_2621 | C177 | YES | 0.18657 |  | Non Productive | Non-Treed |  | 6 | 29 | C176-C178 | 1 | 0 | 0 | 0
WF6_2628 | C177 | YES | 0.31603 |  | Retention | Retention |  | 6 | 29 | C176-C178 | 1 | 0 | 0 | 8
WF6_2633 | C177 | NO | 0.060521 |  | Retention | Retention |  | 6 | 29 | C176-C178 | 1 | 0 | 0 | 8
WF6_7265 | C177 | YES | 0.44009 |  | Non Productive | Non-Treed |  | 6 | 29 | C176-C178 | 1 | 0 | 0 | 0
WF6_7859 | C177 | NO | 0.60787 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 29 | C176-C178 | 1 | 0 | 0 | 0
WF6_7115 | C178 | NO | 0.070707 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 30 | C178-C180 | 1 | 0 | 0 | 0
WF6_7116 | C178 | NO | 0.73634 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 30 | C178-C180 | 1 | 0 | 0 | 0
WF6_2608 | C178 | NO | 0.24557 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 30 | C178-C180 | 0 | 1 | 0 | 0
WF6_2612 | C178 | NO | 0.2554 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 30 | C178-C180 | 0 | 1 | 0 | 0
WF6_2625 | C178 | NO | 2.1972 |  | Harvest Disposal | Mulch |  | 6 | 30 | C178-C180 | 1 | 0 | 0 | 0
WF6_2642 | C178 | YES | 0.092366 |  | Non Productive | Non-Treed |  | 6 | 30 | C178-C180 | 1 | 0 | 0 | 0
WF6_2633 | C178 | NO | 0.34854 |  | Retention | Retention |  | 6 | 30 | C178-C180 | 1 | 0 | 0 | 8
WF6_2637 | C178 | NO | 0.29497 |  | Retention | Retention |  | 6 | 30 | C178-C180 | 1 | 0 | 0 | 8
WF6_2638 | C178 | NO | 0.071407 |  | Retention | Retention |  | 6 | 30 | C178-C180 | 1 | 0 | 0 | 8
WF6_7734 | C178 | NO | 0.051937 |  | Harvest Disposal | Mulch |  | 6 | 30 | C178-C180 | 1 | 0 | 0 | 0
WF6_7117 | C179 | NO | 0.78942 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 30 | C178-C180 | 1 | 0 | 0 | 0
WF6_2608 | C179 | NO | 0.80778 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 30 | C178-C180 | 0 | 1 | 0 | 0
WF6_2642 | C179 | YES | 0.37651 |  | Non Productive | Non-Treed |  | 6 | 30 | C178-C180 | 1 | 0 | 0 | 0
WF6_2638 | C179 | NO | 1.1299 |  | Retention | Retention |  | 6 | 30 | C178-C180 | 1 | 0 | 0 | 8
WF6_7733 | C179 | NO | 1.1335 |  | Harvest Disposal | Mulch |  | 6 | 30 | C178-C180 | 1 | 0 | 0 | 0
WF6_2646 | C180 | YES | 0.039988 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 31 | C180-C182 | 1 | 0 | 0 | 0
WF6_6343 | C180 | NO | 1.2579 |  | Harvest Disposal | Mulch |  | 6 | 31 | C180-C182 | 1 | 0 | 0 | 0
WF6_7118 | C180 | NO | 0.088088 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 31 | C180-C182 | 1 | 0 | 0 | 0
WF6_7119 | C180 | NO | 0.088226 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 31 | C180-C182 | 1 | 0 | 0 | 0
WF6_2608 | C180 | NO | 0.14185 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 31 | C180-C182 | 0 | 1 | 0 | 0
WF6_2636 | C180 | NO | 0.69228 |  | Harvest Disposal | Mulch |  | 6 | 31 | C180-C182 | 1 | 0 | 0 | 0
WF6_2653 | C180 | NO | 0.14472 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 31 | C180-C182 | 0 | 1 | 0 | 0
WF6_2639 | C180 | YES | 0.05094 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 31 | C180-C182 | 1 | 0 | 0 | 0
WF6_2640 | C180 | YES | 0.05594 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 31 | C180-C182 | 1 | 0 | 0 | 0
WF6_2635 | C180 | NO | 0.031438 |  | Non Productive | Non-Treed |  | 6 | 31 | C180-C182 | 1 | 0 | 0 | 0
WF6_2643 | C180 | YES | 0.029071 |  | Non Productive | Non-Treed |  | 6 | 31 | C180-C182 | 1 | 0 | 0 | 0
WF6_2632 | C180 | NO | 0.24764 |  | Retention | Retention |  | 6 | 31 | C180-C182 | 1 | 0 | 0 | 8
WF6_2634 | C180 | NO | 0.061944 |  | Retention | Retention |  | 6 | 31 | C180-C182 | 1 | 0 | 0 | 8
WF6_2638 | C180 | NO | 0.012652 |  | Retention | Retention |  | 6 | 30 | C178-C180 | 1 | 0 | 0 | 8
WF6_2638 | C180 | NO | 0.24318 |  | Retention | Retention |  | 6 | 31 | C180-C182 | 1 | 0 | 0 | 8
WF6_2641 | C180 | NO | 0.97877 |  | Retention | Retention |  | 6 | 31 | C180-C182 | 1 | 0 | 0 | 8
WF6_2644 | C180 | NO | 0.47945 |  | Retention | Retention |  | 6 | 31 | C180-C182 | 1 | 0 | 0 | 8
WF6_2647 | C180 | NO | 0.11948 |  | Retention | Retention |  | 6 | 31 | C180-C182 | 1 | 0 | 0 | 8
WF6_7266 | C180 | NO | 0.01291 |  | Non Productive | Non-Treed |  | 6 | 31 | C180-C182 | 1 | 0 | 0 | 0
WF6_7120 | C181 | NO | 0.083887 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 31 | C180-C182 | 1 | 0 | 0 | 0
WF6_7121 | C181 | NO | 0.08381 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 31 | C180-C182 | 1 | 0 | 0 | 0
WF6_2636 | C181 | NO | 2.4781 |  | Harvest Disposal | Mulch |  | 6 | 31 | C180-C182 | 1 | 0 | 0 | 0
WF6_2653 | C181 | NO | 0.89529 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 31 | C180-C182 | 0 | 1 | 0 | 0
WF6_2647 | C181 | NO | 0.64417 |  | Retention | Retention |  | 6 | 31 | C180-C182 | 1 | 0 | 0 | 8
WF6_2648 | C181 | NO | 0.21394 |  | Retention | Retention |  | 6 | 31 | C180-C182 | 1 | 0 | 0 | 8
WF6_6344 | C182 | NO | 0.19753 |  | Harvest Disposal | Mulch |  | 6 | 32 | C182-C184 | 1 | 0 | 0 | 0
WF6_2636 | C182 | NO | 0.72877 |  | Harvest Disposal | Mulch |  | 6 | 32 | C182-C184 | 1 | 0 | 0 | 0
WF6_2653 | C182 | NO | 0.30234 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 32 | C182-C184 | 0 | 1 | 0 | 0
WF6_7860 | C182 | NO | 1.4914 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 32 | C182-C184 | 1 | 0 | 0 | 0
WF6_7055 | C183 | YES | 0.22546 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 32 | C182-C184 | 1 | 0 | 0 | 0
WF6_7056 | C183 | YES | 0.18617 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 32 | C182-C184 | 1 | 0 | 0 | 0
WF6_7122 | C183 | NO | 0.01952 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 32 | C182-C184 | 1 | 0 | 0 | 0
WF6_2650 | C183 | YES | 0.25726 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 32 | C182-C184 | 1 | 0 | 0 | 0
WF6_2649 | C183 | NO | 0.14047 |  | Harvest Disposal | Mulch | ANWIN | 6 | 32 | C182-C184 | 0 | 1 | 0 | 0
WF6_2651 | C183 | NO | 0.081493 |  | Harvest Disposal | Mulch |  | 6 | 32 | C182-C184 | 1 | 0 | 0 | 0
WF6_2654 | C183 | NO | 0.1066 |  | Retention | Retention |  | 6 | 32 | C182-C184 | 1 | 0 | 0 | 8
WF6_2655 | C183 | YES | 0.10411 |  | Retention | Retention |  | 6 | 32 | C182-C184 | 1 | 0 | 0 | 8
WF6_7735 | C183 | NO | 0.44734 |  | Harvest Disposal | Mulch |  | 6 | 32 | C182-C184 | 1 | 0 | 0 | 0
WF6_7861 | C183 | NO | 0.17292 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 32 | C182-C184 | 1 | 0 | 0 | 0
WF6_7862 | C183 | NO | 0.82017 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 32 | C182-C184 | 1 | 0 | 0 | 0
WF6_6345 | C184 | NO | 0.39795 |  | Harvest Disposal | Mulch |  | 6 | 33 | C184-C186 | 1 | 0 | 0 | 0
WF6_7123 | C184 | NO | 1.2583 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 33 | C184-C186 | 1 | 0 | 0 | 0
WF6_7124 | C184 | NO | 0.0626 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 33 | C184-C186 | 1 | 0 | 0 | 0
WF6_6346 | C184 | NO | 0.37299 |  | Non-Merch Disposal | Mulch | AU1 | 6 | 33 | C184-C186 | 0 | 1 | 0 | 0
WF6_2659 | C184 | NO | 0.42279 |  | Harvest Disposal | Mulch |  | 6 | 33 | C184-C186 | 1 | 0 | 0 | 0
WF6_2676 | C184 | NO | 0.3751 |  | Non-Merch Disposal | Mulch | AU1 | 6 | 33 | C184-C186 | 0 | 1 | 0 | 0
WF6_2674 | C184 | NO | 0.15512 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 33 | C184-C186 | 0 | 1 | 0 | 0
WF6_2657 | C184 | NO | 0.026852 |  | Non Productive | Non-Treed |  | 6 | 33 | C184-C186 | 1 | 0 | 0 | 0
WF6_2656 | C184 | NO | 0.022383 |  | Retention | Retention |  | 6 | 33 | C184-C186 | 1 | 0 | 0 | 8
WF6_2658 | C184 | NO | 0.078919 |  | Retention | Retention |  | 6 | 33 | C184-C186 | 1 | 0 | 0 | 8
WF6_6300 | C185 | NO | 0.016112 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 33 | C184-C186 | 1 | 0 | 0 | 0
WF6_7057 | C185 | NO | 0.29407 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 33 | C184-C186 | 1 | 0 | 0 | 0
WF6_7125 | C185 | NO | 0.014572 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 33 | C184-C186 | 1 | 0 | 0 | 0
WF6_7199 | C185 | NO | 0.018519 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 33 | C184-C186 | 1 | 0 | 0 | 0
WF6_2663 | C185 | NO | 0.11079 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 33 | C184-C186 | 1 | 0 | 0 | 0
WF6_2659 | C185 | NO | 0.29544 |  | Harvest Disposal | Mulch |  | 6 | 33 | C184-C186 | 1 | 0 | 0 | 0
WF6_2684 | C185 | NO | 0.13137 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 33 | C184-C186 | 0 | 1 | 0 | 0
WF6_2668 | C185 | NO | 0.23125 |  | Harvest Processing | Non-Mulch |  | 6 | 33 | C184-C186 | 1 | 0 | 0 | 0
WF6_2670 | C185 | NO | 0.1751 |  | Harvest Processing | Non-Mulch |  | 6 | 33 | C184-C186 | 1 | 0 | 0 | 0
WF6_2665 | C185 | YES | 0.12568 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 33 | C184-C186 | 1 | 0 | 0 | 0
WF6_2669 | C185 | YES | 0.07387 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 33 | C184-C186 | 1 | 0 | 0 | 0
WF6_2661 | C185 | NO | 0.14605 |  | Non Productive | Non-Treed |  | 6 | 33 | C184-C186 | 1 | 0 | 0 | 0
WF6_2667 | C185 | NO | 0.042064 |  | Non Productive | Non-Treed |  | 6 | 33 | C184-C186 | 1 | 0 | 0 | 0
WF6_2660 | C185 | NO | 0.13462 |  | Retention | Retention |  | 6 | 33 | C184-C186 | 1 | 0 | 0 | 8
WF6_2662 | C185 | NO | 0.14863 |  | Retention | Retention |  | 6 | 33 | C184-C186 | 1 | 0 | 0 | 8
WF6_2666 | C185 | NO | 0.02779 |  | Retention | Retention |  | 6 | 33 | C184-C186 | 1 | 0 | 0 | 8
WF6_2671 | C185 | YES | 0.24796 |  | Retention | Retention |  | 6 | 33 | C184-C186 | 1 | 0 | 0 | 8
WF6_2672 | C185 | NO | 0.095889 |  | Retention | Retention |  | 6 | 33 | C184-C186 | 1 | 0 | 0 | 8
WF6_7276 | C185 | NO | 0.046412 |  | Retention | Retention |  | 6 | 33 | C184-C186 | 1 | 0 | 0 | 8
WF6_7277 | C185 | NO | 0.045913 |  | Retention | Retention |  | 6 | 33 | C184-C186 | 1 | 0 | 0 | 8
WF6_2684 | C186 | NO | 0.10017 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 34 | C186-C188 | 0 | 1 | 0 | 0
WF6_2684 | C186 | NO | 0.82853 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 34 | C186-C188 | 0 | 1 | 0 | 0
WF6_2668 | C186 | NO | 1.6761 |  | Harvest Processing | Non-Mulch |  | 6 | 34 | C186-C188 | 1 | 0 | 0 | 0
WF6_2677 | C186 | NO | 0.081844 |  | Non Productive | Non-Treed |  | 6 | 34 | C186-C188 | 1 | 0 | 0 | 0
WF6_2699 | C187 | NO | 0.07672 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 34 | C186-C188 | 0 | 1 | 0 | 0
WF6_2668 | C187 | NO | 1.688 |  | Harvest Processing | Non-Mulch |  | 6 | 34 | C186-C188 | 1 | 0 | 0 | 0
WF6_2673 | C187 | NO | 0.059106 |  | Retention | Retention |  | 6 | 34 | C186-C188 | 1 | 0 | 0 | 8
WF6_2681 | C187 | NO | 0.096974 |  | Retention | Retention |  | 6 | 34 | C186-C188 | 1 | 0 | 0 | 8
WF6_6347 | C188 | NO | 0.020325 |  | Harvest Disposal | Mulch |  | 6 | 35 | C188-C190 | 1 | 0 | 0 | 0
WF6_7126 | C188 | NO | 0.50044 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 35 | C188-C190 | 1 | 0 | 0 | 0
WF6_7127 | C188 | NO | 0.13356 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 35 | C188-C190 | 1 | 0 | 0 | 0
WF6_2664 | C188 | NO | 0.098355 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 35 | C188-C190 | 0 | 1 | 0 | 0
WF6_2678 | C188 | NO | 0.31202 |  | Harvest Disposal | Mulch |  | 6 | 35 | C188-C190 | 1 | 0 | 0 | 0
WF6_2699 | C188 | NO | 0.084412 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 34 | C186-C188 | 0 | 1 | 0 | 0
WF6_2699 | C188 | NO | 0.038507 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 34 | C186-C188 | 0 | 1 | 0 | 0
WF6_2699 | C188 | NO | 0.18621 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 35 | C188-C190 | 0 | 1 | 0 | 0
WF6_2699 | C188 | NO | 0.36961 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 35 | C188-C190 | 0 | 1 | 0 | 0
WF6_2668 | C188 | NO | 0.30402 |  | Harvest Processing | Non-Mulch |  | 6 | 35 | C188-C190 | 1 | 0 | 0 | 0
WF6_2675 | C188 | NO | 0.16436 |  | Retention | Retention |  | 6 | 35 | C188-C190 | 1 | 0 | 0 | 8
WF6_2682 | C188 | NO | 0.082835 |  | Retention | Retention |  | 6 | 35 | C188-C190 | 1 | 0 | 0 | 8
WF6_7128 | C189 | NO | 0.1736 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 35 | C188-C190 | 1 | 0 | 0 | 0
WF6_7129 | C189 | NO | 0.10716 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 35 | C188-C190 | 1 | 0 | 0 | 0
WF6_7130 | C189 | NO | 0.048283 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 35 | C188-C190 | 1 | 0 | 0 | 0
WF6_2664 | C189 | NO | 0.73686 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 35 | C188-C190 | 0 | 1 | 0 | 0
WF6_2678 | C189 | NO | 1.2298 |  | Harvest Disposal | Mulch |  | 6 | 35 | C188-C190 | 1 | 0 | 0 | 0
WF6_2680 | C189 | NO | 0.073411 |  | Retention | Retention |  | 6 | 35 | C188-C190 | 1 | 0 | 0 | 8
WF6_7863 | C189 | NO | 0.096278 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 35 | C188-C190 | 1 | 0 | 0 | 0
WF6_2690 | C190 | YES | 0.04131 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 36 | C190-C192 | 1 | 0 | 0 | 0
WF6_2696 | C190 | NO | 0.032499 |  | Harvest Disposal | Mulch |  | 6 | 36 | C190-C192 | 1 | 0 | 0 | 0
WF6_2689 | C190 | NO | 0.066494 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 36 | C190-C192 | 1 | 0 | 0 | 0
WF6_2692 | C190 | YES | 0.15502 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 36 | C190-C192 | 1 | 0 | 0 | 0
WF6_7131 | C190 | NO | 0.034501 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 36 | C190-C192 | 1 | 0 | 0 | 0
WF6_7132 | C190 | NO | 0.14884 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 36 | C190-C192 | 1 | 0 | 0 | 0
WF6_7200 | C190 | NO | 0.029354 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 36 | C190-C192 | 1 | 0 | 0 | 0
WF6_2664 | C190 | NO | 0.28283 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 36 | C190-C192 | 0 | 1 | 0 | 0
WF6_2678 | C190 | NO | 0.35316 |  | Harvest Disposal | Mulch |  | 6 | 36 | C190-C192 | 1 | 0 | 0 | 0
WF6_2686 | C190 | NO | 0.41222 |  | Harvest Disposal | Mulch |  | 6 | 36 | C190-C192 | 1 | 0 | 0 | 0
WF6_2714 | C190 | NO | 0.24256 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 36 | C190-C192 | 0 | 1 | 0 | 0
WF6_2691 | C190 | NO | 0.065366 |  | Harvest Processing | Non-Mulch |  | 6 | 36 | C190-C192 | 1 | 0 | 0 | 0
WF6_2685 | C190 | NO | 0.12099 |  | Retention | Retention |  | 6 | 36 | C190-C192 | 1 | 0 | 0 | 8
WF6_2687 | C190 | NO | 0.47626 |  | Retention | Retention |  | 6 | 36 | C190-C192 | 1 | 0 | 0 | 8
WF6_2694 | C190 | NO | 0.086853 |  | Retention | Retention |  | 6 | 36 | C190-C192 | 1 | 0 | 0 | 8
WF6_2697 | C190 | NO | 0.40992 |  | Retention | Retention |  | 6 | 36 | C190-C192 | 1 | 0 | 0 | 8
WF6_7278 | C190 | NO | 0.013491 |  | Retention | Retention |  | 6 | 36 | C190-C192 | 1 | 0 | 0 | 8
WF6_7279 | C190 | NO | 0.021345 |  | Retention | Retention |  | 6 | 36 | C190-C192 | 1 | 0 | 0 | 8
WF6_2693 | C191 | YES | 0.014537 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 36 | C190-C192 | 1 | 0 | 0 | 0
WF6_2695 | C191 | YES | 0.12738 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 36 | C190-C192 | 1 | 0 | 0 | 0
WF6_2703 | C191 | YES | 0.017661 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 36 | C190-C192 | 1 | 0 | 0 | 0
WF6_2700 | C191 | NO | 0.023563 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 36 | C190-C192 | 1 | 0 | 0 | 0
WF6_7058 | C191 | YES | 0.29392 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 36 | C190-C192 | 1 | 0 | 0 | 0
WF6_7059 | C191 | YES | 0.24925 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 36 | C190-C192 | 1 | 0 | 0 | 0
WF6_7201 | C191 | NO | 0.34763 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 36 | C190-C192 | 1 | 0 | 0 | 0
WF6_7203 | C191 | NO | 0.084732 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 36 | C190-C192 | 1 | 0 | 0 | 0
WF6_2722 | C191 | NO | 0.55491 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 36 | C190-C192 | 0 | 1 | 0 | 0
WF6_2714 | C191 | NO | 0.01668 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 36 | C190-C192 | 0 | 1 | 0 | 0
WF6_2691 | C191 | NO | 0.51061 |  | Harvest Processing | Non-Mulch |  | 6 | 36 | C190-C192 | 1 | 0 | 0 | 0
WF6_2704 | C191 | NO | 0.04737 |  | Harvest Processing | Non-Mulch |  | 6 | 36 | C190-C192 | 1 | 0 | 0 | 0
WF6_2701 | C191 | NO | 0.6625 |  | Non Productive | Non-Treed |  | 6 | 36 | C190-C192 | 1 | 0 | 0 | 0
WF6_7878 | C191 | NO | 0.054203 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 36 | C190-C192 | 1 | 0 | 0 | 0
WF6_2704 | C192 | NO | 1.4006 |  | Harvest Processing | Non-Mulch |  | 6 | 37 | C192-C194 | 1 | 0 | 0 | 0
WF6_2705 | C192 | NO | 0.092919 |  | Retention | Retention |  | 6 | 37 | C192-C194 | 1 | 0 | 0 | 8
WF6_2706 | C192 | NO | 0.090367 |  | Retention | Retention |  | 6 | 37 | C192-C194 | 1 | 0 | 0 | 8
WF6_7879 | C192 | NO | 0.12542 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 37 | C192-C194 | 1 | 0 | 0 | 0
WF6_2709 | C193 | YES | 0.1969 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 37 | C192-C194 | 1 | 0 | 0 | 0
WF6_2712 | C193 | YES | 0.018417 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 37 | C192-C194 | 1 | 0 | 0 | 0
WF6_2713 | C193 | YES | 0.054629 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 37 | C192-C194 | 1 | 0 | 0 | 0
WF6_7202 | C193 | NO | 0.11494 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 37 | C192-C194 | 1 | 0 | 0 | 0
WF6_6199 | C193 | NO | 0.15593 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 37 | C192-C194 | 0 | 1 | 0 | 0
WF6_6199 | C193 | NO | 0.18736 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 37 | C192-C194 | 0 | 1 | 0 | 0
WF6_2729 | C193 | NO | 0.1763 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 37 | C192-C194 | 0 | 1 | 0 | 0
WF6_2729 | C193 | NO | 0.64013 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 37 | C192-C194 | 0 | 1 | 0 | 0
WF6_2729 | C193 | NO | 0.035472 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 38 | C194-C197 | 0 | 1 | 0 | 0
WF6_2704 | C193 | NO | 0.22352 |  | Harvest Processing | Non-Mulch |  | 6 | 37 | C192-C194 | 1 | 0 | 0 | 0
WF6_2708 | C193 | NO | 0.46129 |  | Non Productive | Non-Treed |  | 6 | 37 | C192-C194 | 1 | 0 | 0 | 0
WF6_2707 | C193 | NO | 0.098167 |  | Retention | Retention |  | 6 | 37 | C192-C194 | 1 | 0 | 0 | 8
WF6_2721 | C193 | NO | 0.057625 |  | Retention | Retention |  | 6 | 37 | C192-C194 | 1 | 0 | 0 | 8
WF6_7726 | C193 | NO | 0.18273 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 37 | C192-C194 | 1 | 0 | 0 | 0
WF6_2715 | C194 | YES | 0.13561 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 38 | C194-C197 | 1 | 0 | 0 | 0
WF6_2723 | C194 | YES | 0.10503 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 38 | C194-C197 | 1 | 0 | 0 | 0
WF6_2710 | C194 | NO | 0.52657 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 38 | C194-C197 | 1 | 0 | 0 | 0
WF6_7133 | C194 | NO | 0.048956 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 38 | C194-C197 | 1 | 0 | 0 | 0
WF6_2720 | C194 | NO | 1.0301 |  | Harvest Disposal | Mulch |  | 6 | 38 | C194-C197 | 1 | 0 | 0 | 0
WF6_2729 | C194 | NO | 0.73127 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 38 | C194-C197 | 0 | 1 | 0 | 0
WF6_2729 | C194 | NO | 0.23194 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 38 | C194-C197 | 0 | 1 | 0 | 0
WF6_2729 | C194 | NO | 0.62473 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 38 | C194-C197 | 0 | 1 | 0 | 0
WF6_2711 | C194 | NO | 0.15671 |  | Retention | Retention |  | 6 | 38 | C194-C197 | 1 | 0 | 0 | 8
WF6_2716 | C194 | YES | 0.056502 |  | Retention | Retention |  | 6 | 38 | C194-C197 | 1 | 0 | 0 | 8
WF6_2719 | C194 | NO | 0.029132 |  | Retention | Retention |  | 6 | 38 | C194-C197 | 1 | 0 | 0 | 8
WF6_2724 | C194 | NO | 0.2452 |  | Retention | Retention |  | 6 | 38 | C194-C197 | 1 | 0 | 0 | 8
WF6_2725 | C194 | NO | 0.05583 |  | Retention | Retention |  | 6 | 38 | C194-C197 | 1 | 0 | 0 | 8
WF6_2717 | C194 | YES | 0.019321 |  | Non Productive | Non-Treed |  | 6 | 38 | C194-C197 | 1 | 0 | 0 | 0
WF6_2718 | C194 | NO | 0.031351 |  | Non Productive | Non-Treed |  | 6 | 38 | C194-C197 | 1 | 0 | 0 | 0
WF6_6348 | C195 | NO | 0.018646 |  | Harvest Disposal | Mulch |  | 6 | 38 | C194-C197 | 1 | 0 | 0 | 0
WF6_7136 | C195 | NO | 0.085488 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 38 | C194-C197 | 1 | 0 | 0 | 0
WF6_6349 | C195 | NO | 0.0023091 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 38 | C194-C197 | 0 | 1 | 0 | 0
WF6_2720 | C195 | NO | 1.8213 |  | Harvest Disposal | Mulch |  | 6 | 38 | C194-C197 | 1 | 0 | 0 | 0
WF6_2745 | C195 | NO | 0.017506 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 38 | C194-C197 | 0 | 1 | 0 | 0
WF6_2734 | C195 | NO | 0.099529 |  | Retention | Retention |  | 6 | 38 | C194-C197 | 1 | 0 | 0 | 8
WF6_7864 | C195 | NO | 0.02946 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 38 | C194-C197 | 1 | 0 | 0 | 0
WF6_7865 | C195 | NO | 0.079798 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 38 | C194-C197 | 1 | 0 | 0 | 0
WF6_7866 | C195 | NO | 0.024558 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 38 | C194-C197 | 1 | 0 | 0 | 0
WF6_2733 | C197 | NO | 0.10342 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 39 | C197-C199 | 1 | 0 | 0 | 0
WF6_7134 | C197 | NO | 0.038987 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 39 | C197-C199 | 1 | 0 | 0 | 0
WF6_7135 | C197 | NO | 0.04517 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 39 | C197-C199 | 1 | 0 | 0 | 0
WF6_7137 | C197 | NO | 0.20761 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 39 | C197-C199 | 1 | 0 | 0 | 0
WF6_7138 | C197 | NO | 0.17654 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 39 | C197-C199 | 1 | 0 | 0 | 0
WF6_6349 | C197 | NO | 0.0080222 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 38 | C194-C197 | 0 | 1 | 0 | 0
WF6_2731 | C197 | NO | 0.50102 |  | Harvest Disposal | Mulch |  | 6 | 39 | C197-C199 | 1 | 0 | 0 | 0
WF6_2749 | C197 | NO | 0.23552 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 38 | C194-C197 | 0 | 1 | 0 | 0
WF6_2749 | C197 | NO | 0.24018 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 39 | C197-C199 | 0 | 1 | 0 | 0
WF6_2749 | C197 | NO | 0.25351 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 39 | C197-C199 | 0 | 1 | 0 | 0
WF6_2749 | C197 | NO | 0.33406 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 39 | C197-C199 | 0 | 1 | 0 | 0
WF6_2727 | C197 | NO | 0.21723 |  | Non Productive | Non-Treed |  | 6 | 39 | C197-C199 | 1 | 0 | 0 | 0
WF6_2730 | C197 | NO | 0.21385 |  | Non Productive | Non-Treed |  | 6 | 39 | C197-C199 | 1 | 0 | 0 | 0
WF6_2726 | C197 | NO | 0.087579 |  | Retention | Retention |  | 6 | 39 | C197-C199 | 1 | 0 | 0 | 8
WF6_2728 | C197 | NO | 0.11384 |  | Retention | Retention |  | 6 | 39 | C197-C199 | 1 | 0 | 0 | 8
WF6_2732 | C197 | NO | 0.24057 |  | Retention | Retention |  | 6 | 39 | C197-C199 | 1 | 0 | 0 | 8
WF6_2736 | C197 | NO | 0.07689 |  | Retention | Retention |  | 6 | 39 | C197-C199 | 1 | 0 | 0 | 8
WF6_2737 | C197 | NO | 0.16927 |  | Retention | Retention |  | 6 | 39 | C197-C199 | 1 | 0 | 0 | 8
WF6_7267 | C197 | NO | 0.020793 |  | Non Productive | Non-Treed |  | 6 | 39 | C197-C199 | 1 | 0 | 0 | 0
WF6_2749 | C197 | NO | 0.024582 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 39 | C197-C199 | 0 | 1 | 0 | 0
WF6_2749 | C197 | NO | 0.024582 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 39 | C197-C199 | 0 | 1 | 0 | 0
WF6_2731 | C198 | NO | 0.28991 |  | Harvest Disposal | Mulch |  | 6 | 39 | C197-C199 | 1 | 0 | 0 | 0
WF6_2735 | C198 | NO | 1.5391 |  | Harvest Processing | Non-Mulch |  | 6 | 39 | C197-C199 | 1 | 0 | 0 | 0
WF6_2740 | C199 | NO | 0.023494 |  | Harvest Disposal | Mulch |  | 6 | 40 | C199-C201 | 1 | 0 | 0 | 0
WF6_2743 | C199 | NO | 0.46199 |  | Harvest Disposal | Mulch |  | 6 | 40 | C199-C201 | 1 | 0 | 0 | 0
WF6_2735 | C199 | NO | 1.1711 |  | Harvest Processing | Non-Mulch |  | 6 | 40 | C199-C201 | 1 | 0 | 0 | 0
WF6_2744 | C199 | NO | 0.31124 |  | Harvest Processing | Non-Mulch |  | 6 | 40 | C199-C201 | 1 | 0 | 0 | 0
WF6_2741 | C199 | NO | 0.28143 |  | Retention | Retention |  | 6 | 40 | C199-C201 | 1 | 0 | 0 | 8
WF6_2744 | C200 | NO | 2.6769 |  | Harvest Processing | Non-Mulch |  | 6 | 40 | C199-C201 | 1 | 0 | 0 | 0
WF6_2750 | C202 | YES | 0.019709 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 41 | C201-C203 | 1 | 0 | 0 | 0
WF6_2764 | C202 | YES | 0.091147 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 41 | C201-C203 | 1 | 0 | 0 | 0
WF6_7060 | C202 | YES | 0.46813 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 41 | C201-C203 | 1 | 0 | 0 | 0
WF6_7061 | C202 | NO | 0.25905 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 41 | C201-C203 | 1 | 0 | 0 | 0
WF6_7139 | C202 | NO | 0.056934 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 41 | C201-C203 | 1 | 0 | 0 | 0
WF6_7204 | C202 | NO | 0.13717 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 41 | C201-C203 | 1 | 0 | 0 | 0
WF6_2758 | C202 | NO | 0.088872 |  | Harvest Disposal | Mulch |  | 6 | 41 | C201-C203 | 1 | 0 | 0 | 0
WF6_2744 | C202 | NO | 0.031918 |  | Harvest Processing | Non-Mulch |  | 6 | 41 | C201-C203 | 1 | 0 | 0 | 0
WF6_2744 | C202 | NO | 2.2012 |  | Harvest Processing | Non-Mulch |  | 6 | 41 | C201-C203 | 1 | 0 | 0 | 0
WF6_2751 | C202 | NO | 3.0673 |  | Non Productive | Non-Treed |  | 6 | 41 | C201-C203 | 1 | 0 | 0 | 0
WF6_2747 | C202 | NO | 0.17842 |  | Retention | Retention |  | 6 | 41 | C201-C203 | 1 | 0 | 0 | 8
WF6_2748 | C202 | NO | 0.16061 |  | Retention | Retention |  | 6 | 41 | C201-C203 | 1 | 0 | 0 | 8
WF6_2753 | C202 | YES | 0.03653 |  | Retention | Retention |  | 6 | 41 | C201-C203 | 1 | 0 | 0 | 8
WF6_2754 | C202 | NO | 0.1544 |  | Retention | Retention |  | 6 | 41 | C201-C203 | 1 | 0 | 0 | 8
WF6_2756 | C202 | NO | 0.26486 |  | Retention | Retention |  | 6 | 41 | C201-C203 | 1 | 0 | 0 | 8
WF6_2757 | C202 | YES | 0.10962 |  | Retention | Retention |  | 6 | 41 | C201-C203 | 1 | 0 | 0 | 8
WF6_2760 | C202 | NO | 0.023881 |  | Retention | Retention |  | 6 | 41 | C201-C203 | 1 | 0 | 0 | 8
WF6_2761 | C202 | YES | 0.11621 |  | Retention | Retention |  | 6 | 41 | C201-C203 | 1 | 0 | 0 | 8
WF6_2762 | C202 | YES | 0.061263 |  | Retention | Retention |  | 6 | 41 | C201-C203 | 1 | 0 | 0 | 8
WF6_2767 | C202 | YES | 0.076006 |  | Retention | Retention |  | 6 | 41 | C201-C203 | 1 | 0 | 0 | 8
WF6_7853 | C202 | YES | 0.044486 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 41 | C201-C203 | 1 | 0 | 0 | 0
WF6_7880 | C202 | NO | 0.047143 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 41 | C201-C203 | 1 | 0 | 0 | 0
WF6_2766 | C203 | YES | 0.34025 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 42 | C203-C205 | 1 | 0 | 0 | 0
WF6_7140 | C203 | NO | 0.063582 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 42 | C203-C205 | 1 | 0 | 0 | 0
WF6_7141 | C203 | NO | 0.34827 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 42 | C203-C205 | 1 | 0 | 0 | 0
WF6_7142 | C203 | NO | 0.068359 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 42 | C203-C205 | 1 | 0 | 0 | 0
WF6_7143 | C203 | NO | 0.020368 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 42 | C203-C205 | 1 | 0 | 0 | 0
WF6_7145 | C203 | NO | 0.018548 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 42 | C203-C205 | 1 | 0 | 0 | 0
WF6_2758 | C203 | NO | 1.0673 |  | Harvest Disposal | Mulch |  | 6 | 42 | C203-C205 | 1 | 0 | 0 | 0
WF6_2768 | C203 | NO | 0.042352 |  | Harvest Disposal | Mulch |  | 6 | 42 | C203-C205 | 1 | 0 | 0 | 0
WF6_2772 | C203 | NO | 0.1472 |  | Retention | Retention |  | 6 | 42 | C203-C205 | 1 | 0 | 0 | 8
WF6_7146 | C204 | NO | 0.25636 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 42 | C203-C205 | 1 | 0 | 0 | 0
WF6_2768 | C204 | NO | 0.54751 |  | Harvest Disposal | Mulch |  | 6 | 42 | C203-C205 | 1 | 0 | 0 | 0
WF6_2771 | C204 | NO | 0.73769 |  | Harvest Disposal | Mulch |  | 6 | 42 | C203-C205 | 1 | 0 | 0 | 0
WF6_2786 | C204 | NO | 0.50431 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 42 | C203-C205 | 0 | 1 | 0 | 0
WF6_2770 | C204 | NO | 0.074474 |  | Non Productive | Non-Treed |  | 6 | 42 | C203-C205 | 1 | 0 | 0 | 0
WF6_2769 | C204 | NO | 0.1016 |  | Retention | Retention |  | 6 | 42 | C203-C205 | 1 | 0 | 0 | 8
WF6_2774 | C204 | NO | 0.13451 |  | Retention | Retention |  | 6 | 42 | C203-C205 | 1 | 0 | 0 | 8
WF6_2776 | C205 | YES | 0.14993 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 43 | C205-C207 | 1 | 0 | 0 | 0
WF6_2781 | C205 | YES | 0.14964 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 43 | C205-C207 | 1 | 0 | 0 | 0
WF6_7147 | C205 | NO | 0.15154 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 43 | C205-C207 | 1 | 0 | 0 | 0
WF6_7148 | C205 | NO | 0.17122 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 43 | C205-C207 | 1 | 0 | 0 | 0
WF6_2777 | C205 | NO | 0.024738 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 43 | C205-C207 | 0 | 1 | 0 | 0
WF6_2771 | C205 | NO | 0.67291 |  | Harvest Disposal | Mulch |  | 6 | 43 | C205-C207 | 1 | 0 | 0 | 0
WF6_2780 | C205 | NO | 0.32573 |  | Harvest Disposal | Mulch |  | 6 | 43 | C205-C207 | 1 | 0 | 0 | 0
WF6_2792 | C205 | NO | 0.070251 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 43 | C205-C207 | 0 | 1 | 0 | 0
WF6_2775 | C205 | NO | 0.046732 |  | Non Productive | Non-Treed |  | 6 | 43 | C205-C207 | 1 | 0 | 0 | 0
WF6_2773 | C205 | NO | 0.24914 |  | Retention | Retention |  | 6 | 43 | C205-C207 | 1 | 0 | 0 | 8
WF6_2779 | C205 | NO | 0.069511 |  | Retention | Retention |  | 6 | 43 | C205-C207 | 1 | 0 | 0 | 8
WF6_2782 | C205 | NO | 0.11347 |  | Retention | Retention |  | 6 | 43 | C205-C207 | 1 | 0 | 0 | 8
WF6_2784 | C205 | NO | 0.0919 |  | Retention | Retention |  | 6 | 43 | C205-C207 | 1 | 0 | 0 | 8
WF6_6350 | C206 | NO | 0.07516 |  | Harvest Disposal | Mulch |  | 6 | 43 | C205-C207 | 1 | 0 | 0 | 0
WF6_7149 | C206 | NO | 0.72938 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 43 | C205-C207 | 1 | 0 | 0 | 0
WF6_7151 | C206 | NO | 0.052003 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 43 | C205-C207 | 1 | 0 | 0 | 0
WF6_2777 | C206 | NO | 0.010482 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 43 | C205-C207 | 0 | 1 | 0 | 0
WF6_6339 | C206 | NO | 0.38259 |  | Non-Merch Disposal | Mulch | AU2 | 6 | 45 | C205-C207 | 0 | 1 | 0 | 0
WF6_6407 | C206 | NO | 0.29706 |  | Non-Merch Disposal | Mulch | AU2 | 6 | 44 | C205-C207 | 0 | 1 | 0 | 0
WF6_6407 | C206 | NO | 0.038041 |  | Non-Merch Disposal | Mulch | AU2 | 6 | 45 | C205-C207 | 0 | 1 | 0 | 0
WF6_2504 | C206 | NO | 0.38239 |  | Non-Merch Disposal | Mulch | AU2 | 6 | 45 | C205-C207 | 0 | 1 | 0 | 0
WF6_2630 | C206 | NO | 0.37694 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 43 | C205-C207 | 0 | 1 | 0 | 0
WF6_2630 | C206 | NO | 0.0466 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 44 | C205-C207 | 0 | 1 | 0 | 0
WF6_2630 | C206 | NO | 0.10017 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 44 | C205-C207 | 0 | 1 | 0 | 0
WF6_2630 | C206 | NO | 0.68955 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 44 | C205-C207 | 0 | 1 | 0 | 0
WF6_2780 | C206 | NO | 0.35145 |  | Harvest Disposal | Mulch |  | 6 | 43 | C205-C207 | 1 | 0 | 0 | 0
WF6_6116 | C206 | NO | 0.30379 |  | Non-Merch Disposal | Mulch | AU2 | 6 | 44 | C205-C207 | 0 | 1 | 0 | 0
WF6_6116 | C206 | NO | 0.037246 |  | Non-Merch Disposal | Mulch | AU2 | 6 | 45 | C205-C207 | 0 | 1 | 0 | 0
WF6_2630 | C206 | NO | 0.019503 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 44 | C205-C207 | 0 | 1 | 0 | 0
WF6_2630 | C206 | NO | 0.019503 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 44 | C205-C207 | 0 | 1 | 0 | 0
WF6_7150 | C207 | NO | 1.117 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 46 | C207-C209 | 1 | 0 | 0 | 0
WF6_7205 | C207 | NO | 0.042883 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 46 | C207-C209 | 1 | 0 | 0 | 0
WF6_2630 | C207 | NO | 0.8892 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 46 | C207-C209 | 0 | 1 | 0 | 0
WF6_2785 | C207 | NO | 0.58415 |  | Harvest Processing | Non-Mulch |  | 6 | 46 | C207-C209 | 1 | 0 | 0 | 0
WF6_2783 | C207 | NO | 0.22042 |  | Retention | Retention |  | 6 | 46 | C207-C209 | 1 | 0 | 0 | 8
WF6_2787 | C207 | NO | 0.20903 |  | Retention | Retention |  | 6 | 46 | C207-C209 | 1 | 0 | 0 | 8
WF6_7736 | C207 | NO | 0.17393 |  | Harvest Disposal | Mulch |  | 6 | 46 | C207-C209 | 1 | 0 | 0 | 0
WF6_2630 | C208 | NO | 0.25656 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 46 | C207-C209 | 0 | 1 | 0 | 0
WF6_2785 | C208 | NO | 1.7764 |  | Harvest Processing | Non-Mulch |  | 6 | 46 | C207-C209 | 1 | 0 | 0 | 0
WF6_2790 | C208 | NO | 0.097509 |  | Retention | Retention |  | 6 | 46 | C207-C209 | 1 | 0 | 0 | 8
WF6_2804 | C208 | NO | 0.12906 |  | Retention | Retention |  | 6 | 46 | C207-C209 | 1 | 0 | 0 | 8
WF6_2794 | C209 | NO | 0.072397 |  | Harvest Disposal | Mulch |  | 6 | 47 | C209-C211 | 1 | 0 | 0 | 0
WF6_6352 | C209 | NO | 0.040312 |  | Harvest Disposal | Mulch |  | 6 | 47 | C209-C211 | 1 | 0 | 0 | 0
WF6_7157 | C209 | NO | 0.62155 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 47 | C209-C211 | 1 | 0 | 0 | 0
WF6_2785 | C209 | NO | 0.10847 |  | Harvest Processing | Non-Mulch |  | 6 | 47 | C209-C211 | 1 | 0 | 0 | 0
WF6_2798 | C209 | NO | 0.6887 |  | Harvest Processing | Non-Mulch |  | 6 | 47 | C209-C211 | 1 | 0 | 0 | 0
WF6_2810 | C209 | NO | 0.23183 |  | Retention | Retention |  | 6 | 47 | C209-C211 | 1 | 0 | 0 | 8
WF6_2798 | C210 | NO | 1.2793 |  | Harvest Processing | Non-Mulch |  | 6 | 47 | C209-C211 | 1 | 0 | 0 | 0
WF6_2816 | C211 | YES | 0.096861 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 48 | C211-C213 | 1 | 0 | 0 | 0
WF6_2825 | C211 | YES | 0.13383 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 48 | C211-C213 | 1 | 0 | 0 | 0
WF6_2830 | C211 | YES | 0.037706 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 48 | C211-C213 | 1 | 0 | 0 | 0
WF6_7206 | C211 | NO | 0.38585 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 48 | C211-C213 | 1 | 0 | 0 | 0
WF6_7210 | C211 | NO | 0.020712 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 48 | C211-C213 | 1 | 0 | 0 | 0
WF6_2844 | C211 | NO | 0.15784 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 48 | C211-C213 | 0 | 1 | 0 | 0
WF6_2844 | C211 | NO | 0.37754 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 48 | C211-C213 | 0 | 1 | 0 | 0
WF6_2798 | C211 | NO | 0.4338 |  | Harvest Processing | Non-Mulch |  | 6 | 48 | C211-C213 | 1 | 0 | 0 | 0
WF6_2827 | C211 | NO | 0.14627 |  | Harvest Processing | Non-Mulch |  | 6 | 48 | C211-C213 | 1 | 0 | 0 | 0
WF6_2817 | C211 | NO | 0.047377 |  | Non Productive | Non-Treed |  | 6 | 48 | C211-C213 | 1 | 0 | 0 | 0
WF6_2821 | C211 | NO | 0.052202 |  | Non Productive | Non-Treed |  | 6 | 48 | C211-C213 | 1 | 0 | 0 | 0
WF6_2814 | C211 | NO | 0.038987 |  | Retention | Retention |  | 6 | 48 | C211-C213 | 1 | 0 | 0 | 8
WF6_2815 | C211 | YES | 0.060226 |  | Retention | Retention |  | 6 | 48 | C211-C213 | 1 | 0 | 0 | 8
WF6_2820 | C211 | YES | 0.035832 |  | Retention | Retention |  | 6 | 48 | C211-C213 | 1 | 0 | 0 | 8
WF6_2824 | C211 | YES | 0.046208 |  | Retention | Retention |  | 6 | 48 | C211-C213 | 1 | 0 | 0 | 8
WF6_2835 | C211 | NO | 0.21599 |  | Retention | Retention |  | 6 | 48 | C211-C213 | 1 | 0 | 0 | 8
WF6_2838 | C211 | YES | 0.07958 |  | Retention | Retention |  | 6 | 48 | C211-C213 | 1 | 0 | 0 | 8
WF6_7211 | C212 | NO | 0.28505 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 48 | C211-C213 | 1 | 0 | 0 | 0
WF6_2791 | C212 | NO | 0.51524 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 48 | C211-C213 | 0 | 1 | 0 | 0
WF6_2844 | C212 | NO | 0.24985 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 48 | C211-C213 | 0 | 1 | 0 | 0
WF6_2844 | C212 | NO | 0.33683 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 48 | C211-C213 | 0 | 1 | 0 | 0
WF6_2827 | C212 | NO | 1.2328 |  | Harvest Processing | Non-Mulch |  | 6 | 48 | C211-C213 | 1 | 0 | 0 | 0
WF6_2829 | C212 | NO | 0.174 |  | Retention | Retention |  | 6 | 48 | C211-C213 | 1 | 0 | 0 | 8
WF6_2839 | C212 | NO | 0.21178 |  | Retention | Retention |  | 6 | 48 | C211-C213 | 1 | 0 | 0 | 8
WF6_2844 | C212 | NO | 0.012404 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 48 | C211-C213 | 0 | 1 | 0 | 0
WF6_2844 | C212 | NO | 0.012404 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 48 | C211-C213 | 0 | 1 | 0 | 0
WF6_6301 | C213 | YES | 0.061761 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 49 | C213-C215 | 1 | 0 | 0 | 0
WF6_6462 | C213 | NO | 0.012775 |  | Harvest Processing | Non-Mulch |  | 6 | 49 | C213-C215 | 1 | 0 | 0 | 0
WF6_7062 | C213 | YES | 0.090278 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 49 | C213-C215 | 1 | 0 | 0 | 0
WF6_7063 | C213 | YES | 0.021627 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 49 | C213-C215 | 1 | 0 | 0 | 0
WF6_7207 | C213 | NO | 0.12435 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 49 | C213-C215 | 1 | 0 | 0 | 0
WF6_7208 | C213 | NO | 0.02246 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 49 | C213-C215 | 1 | 0 | 0 | 0
WF6_7209 | C213 | NO | 0.022764 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 49 | C213-C215 | 1 | 0 | 0 | 0
WF6_2802 | C213 | NO | 0.33799 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 49 | C213-C215 | 0 | 1 | 0 | 0
WF6_2848 | C213 | NO | 0.16365 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 49 | C213-C215 | 0 | 1 | 0 | 0
WF6_2848 | C213 | NO | 0.35993 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 49 | C213-C215 | 0 | 1 | 0 | 0
WF6_2801 | C213 | NO | 1.8465 |  | Harvest Processing | Non-Mulch |  | 6 | 49 | C213-C215 | 1 | 0 | 0 | 0
WF6_2827 | C213 | NO | 0.17084 |  | Harvest Processing | Non-Mulch |  | 6 | 49 | C213-C215 | 1 | 0 | 0 | 0
WF6_2795 | C213 | YES | 0.28983 |  | Non Productive | Non-Treed |  | 6 | 49 | C213-C215 | 1 | 0 | 0 | 0
WF6_2831 | C213 | NO | 0.29417 |  | Non Productive | Non-Treed |  | 6 | 49 | C213-C215 | 1 | 0 | 0 | 0
WF6_2811 | C213 | YES | 1.3655 |  | Retention | Retention |  | 6 | 49 | C213-C215 | 1 | 0 | 0 | 8
WF6_7881 | C213 | NO | 0.44607 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 49 | C213-C215 | 1 | 0 | 0 | 0
WF6_2809 | C214 | YES | 0.034237 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 49 | C213-C215 | 1 | 0 | 0 | 0
WF6_2812 | C214 | YES | 0.15242 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 49 | C213-C215 | 1 | 0 | 0 | 0
WF6_2846 | C214 | NO | 0.054855 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 49 | C213-C215 | 1 | 0 | 0 | 0
WF6_2799 | C214 | YES | 0.048165 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 49 | C213-C215 | 1 | 0 | 0 | 0
WF6_7156 | C214 | NO | 0.031466 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 49 | C213-C215 | 1 | 0 | 0 | 0
WF6_2788 | C214 | NO | 0.33314 |  | Harvest Disposal | Mulch |  | 6 | 49 | C213-C215 | 1 | 0 | 0 | 0
WF6_2788 | C214 | NO | 0.051841 |  | Harvest Disposal | Mulch |  | 6 | 50 | C215-C217 | 1 | 0 | 0 | 0
WF6_2801 | C214 | NO | 0.1363 |  | Harvest Processing | Non-Mulch |  | 6 | 49 | C213-C215 | 1 | 0 | 0 | 0
WF6_2795 | C214 | YES | 2.3244 |  | Non Productive | Non-Treed |  | 6 | 49 | C213-C215 | 1 | 0 | 0 | 0
WF6_2807 | C214 | NO | 0.28748 |  | Non Productive | Non-Treed |  | 6 | 49 | C213-C215 | 1 | 0 | 0 | 0
WF6_2807 | C214 | NO | 0.051429 |  | Non Productive | Non-Treed |  | 6 | 50 | C215-C217 | 1 | 0 | 0 | 0
WF6_2789 | C214 | NO | 0.13722 |  | Retention | Retention |  | 6 | 49 | C213-C215 | 1 | 0 | 0 | 8
WF6_2796 | C214 | YES | 0.022253 |  | Retention | Retention |  | 6 | 49 | C213-C215 | 1 | 0 | 0 | 8
WF6_2797 | C214 | NO | 0.153 |  | Retention | Retention |  | 6 | 49 | C213-C215 | 1 | 0 | 0 | 8
WF6_2806 | C214 | NO | 0.15123 |  | Retention | Retention |  | 6 | 49 | C213-C215 | 1 | 0 | 0 | 8
WF6_2811 | C214 | YES | 0.1502 |  | Retention | Retention |  | 6 | 49 | C213-C215 | 1 | 0 | 0 | 8
WF6_2832 | C214 | NO | 0.01013 |  | Retention | Retention |  | 6 | 49 | C213-C215 | 1 | 0 | 0 | 8
WF6_2836 | C214 | NO | 0.85022 |  | Retention | Retention |  | 6 | 49 | C213-C215 | 1 | 0 | 0 | 8
WF6_2836 | C214 | NO | 0.19821 |  | Retention | Retention |  | 6 | 50 | C215-C217 | 1 | 0 | 0 | 8
WF6_7854 | C214 | YES | 0.18109 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 49 | C213-C215 | 1 | 0 | 0 | 0
WF6_2841 | C215 | NO | 0.27446 |  | Harvest Disposal | Mulch |  | 6 | 50 | C215-C217 | 1 | 0 | 0 | 0
WF6_2841 | C215 | NO | 0.083279 |  | Harvest Disposal | Mulch |  | 6 | 50 | C215-C217 | 1 | 0 | 0 | 0
WF6_6351 | C215 | NO | 0.98071 |  | Harvest Disposal | Mulch |  | 6 | 50 | C215-C217 | 1 | 0 | 0 | 0
WF6_7152 | C215 | NO | 0.062943 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 50 | C215-C217 | 1 | 0 | 0 | 0
WF6_7153 | C215 | NO | 0.13393 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 50 | C215-C217 | 1 | 0 | 0 | 0
WF6_7154 | C215 | NO | 0.36816 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 50 | C215-C217 | 1 | 0 | 0 | 0
WF6_7158 | C215 | NO | 0.10351 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 50 | C215-C217 | 1 | 0 | 0 | 0
WF6_2788 | C215 | NO | 0.80476 |  | Harvest Disposal | Mulch |  | 6 | 50 | C215-C217 | 1 | 0 | 0 | 0
WF6_2851 | C215 | NO | 1.1144 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 50 | C215-C217 | 0 | 1 | 0 | 0
WF6_2807 | C215 | NO | 1.0765 |  | Non Productive | Non-Treed |  | 6 | 50 | C215-C217 | 1 | 0 | 0 | 0
WF6_2834 | C215 | YES | 0.011412 |  | Non Productive | Non-Treed |  | 6 | 50 | C215-C217 | 1 | 0 | 0 | 0
WF6_2793 | C215 | NO | 0.080706 |  | Retention | Retention |  | 6 | 50 | C215-C217 | 1 | 0 | 0 | 8
WF6_2833 | C215 | NO | 0.18981 |  | Retention | Retention |  | 6 | 50 | C215-C217 | 1 | 0 | 0 | 8
WF6_2836 | C215 | NO | 0.45381 |  | Retention | Retention |  | 6 | 50 | C215-C217 | 1 | 0 | 0 | 8
WF6_2843 | C215 | NO | 0.2063 |  | Retention | Retention |  | 6 | 50 | C215-C217 | 1 | 0 | 0 | 8
WF6_2845 | C215 | NO | 1.3377 |  | Retention | Retention |  | 6 | 50 | C215-C217 | 1 | 0 | 0 | 8
WF6_7269 | C215 | NO | 0.021981 |  | Non Productive | Non-Treed |  | 6 | 50 | C215-C217 | 1 | 0 | 0 | 0
WF6_7867 | C215 | NO | 0.43393 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 50 | C215-C217 | 1 | 0 | 0 | 0
WF6_2847 | C216 | NO | 0.25346 |  | Harvest Disposal | Mulch |  | 6 | 50 | C215-C217 | 1 | 0 | 0 | 0
WF6_7155 | C216 | NO | 1.0333 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 50 | C215-C217 | 1 | 0 | 0 | 0
WF6_7159 | C216 | NO | 0.56574 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 50 | C215-C217 | 1 | 0 | 0 | 0
WF6_7160 | C216 | NO | 0.097424 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 50 | C215-C217 | 1 | 0 | 0 | 0
WF6_7161 | C216 | NO | 0.049234 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 50 | C215-C217 | 1 | 0 | 0 | 0
WF6_7162 | C216 | NO | 0.036104 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 50 | C215-C217 | 1 | 0 | 0 | 0
WF6_2859 | C216 | NO | 0.11815 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 50 | C215-C217 | 0 | 1 | 0 | 0
WF6_2859 | C216 | NO | 0.069818 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 50 | C215-C217 | 0 | 1 | 0 | 0
WF6_2807 | C216 | NO | 0.6649 |  | Non Productive | Non-Treed |  | 6 | 50 | C215-C217 | 1 | 0 | 0 | 0
WF6_2845 | C216 | NO | 0.68719 |  | Retention | Retention |  | 6 | 50 | C215-C217 | 1 | 0 | 0 | 8
WF6_2849 | C216 | NO | 0.13214 |  | Retention | Retention |  | 6 | 50 | C215-C217 | 1 | 0 | 0 | 8
WF6_7268 | C216 | NO | 0.020583 |  | Non Productive | Non-Treed |  | 6 | 50 | C215-C217 | 1 | 0 | 0 | 0
WF6_7269 | C216 | NO | 0.050675 |  | Non Productive | Non-Treed |  | 6 | 50 | C215-C217 | 1 | 0 | 0 | 0
WF6_7270 | C216 | NO | 0.026734 |  | Non Productive | Non-Treed |  | 6 | 50 | C215-C217 | 1 | 0 | 0 | 0
WF6_7869 | C216 | NO | 0.087417 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 50 | C215-C217 | 1 | 0 | 0 | 0
WF6_2853 | C217 | NO | 0.023538 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 51 | C217-C219 | 1 | 0 | 0 | 0
WF6_7064 | C217 | NO | 0.36558 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 51 | C217-C219 | 1 | 0 | 0 | 0
WF6_7164 | C217 | NO | 0.012351 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 51 | C217-C219 | 1 | 0 | 0 | 0
WF6_6118 | C217 | NO | 0.080169 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 51 | C217-C219 | 0 | 1 | 0 | 0
WF6_2842 | C217 | NO | 0.26774 |  | Non-Merch Disposal | Mulch | AU1 | 6 | 51 | C217-C219 | 0 | 1 | 0 | 0
WF6_2860 | C217 | NO | 0.28909 |  | Harvest Disposal | Mulch |  | 6 | 51 | C217-C219 | 1 | 0 | 0 | 0
WF6_2861 | C217 | NO | 0.15743 |  | Harvest Disposal | Mulch |  | 6 | 51 | C217-C219 | 1 | 0 | 0 | 0
WF6_2857 | C217 | NO | 0.081267 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 51 | C217-C219 | 1 | 0 | 0 | 0
WF6_2852 | C217 | NO | 0.30003 |  | Non Productive | Non-Treed |  | 6 | 51 | C217-C219 | 1 | 0 | 0 | 0
WF6_2855 | C217 | YES | 0.36481 |  | Non Productive | Non-Treed |  | 6 | 51 | C217-C219 | 1 | 0 | 0 | 0
WF6_2858 | C217 | NO | 0.036844 |  | Non Productive | Non-Treed |  | 6 | 51 | C217-C219 | 1 | 0 | 0 | 0
WF6_2850 | C217 | NO | 0.21363 |  | Retention | Retention |  | 6 | 51 | C217-C219 | 1 | 0 | 0 | 8
WF6_2854 | C217 | NO | 0.25325 |  | Retention | Retention |  | 6 | 51 | C217-C219 | 1 | 0 | 0 | 8
WF6_2856 | C217 | NO | 0.5854 |  | Retention | Retention |  | 6 | 51 | C217-C219 | 1 | 0 | 0 | 8
WF6_7280 | C217 | NO | 0.10686 |  | Retention | Retention |  | 6 | 51 | C217-C219 | 1 | 0 | 0 | 8
WF6_7281 | C217 | NO | 0.01086 |  | Retention | Retention |  | 6 | 51 | C217-C219 | 1 | 0 | 0 | 8
WF6_7534 | C217 | NO | 0.046215 |  | Harvest Disposal | Mulch |  | 6 | 51 | C217-C219 | 1 | 0 | 0 | 0
WF6_7868 | C217 | NO | 0.018091 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 51 | C217-C219 | 1 | 0 | 0 | 0
WF6_7870 | C217 | NO | 0.18121 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 51 | C217-C219 | 1 | 0 | 0 | 0
WF6_7163 | C218 | NO | 0.4179 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 51 | C217-C219 | 1 | 0 | 0 | 0
WF6_2860 | C218 | NO | 0.49078 |  | Harvest Disposal | Mulch |  | 6 | 51 | C217-C219 | 1 | 0 | 0 | 0
WF6_2866 | C218 | NO | 0.30473 |  | Harvest Disposal | Mulch |  | 6 | 51 | C217-C219 | 1 | 0 | 0 | 0
WF6_2865 | C218 | NO | 0.10352 |  | Non Productive | Non-Treed |  | 6 | 51 | C217-C219 | 1 | 0 | 0 | 0
WF6_2862 | C218 | NO | 0.62522 |  | Retention | Retention |  | 6 | 51 | C217-C219 | 1 | 0 | 0 | 8
WF6_2863 | C218 | NO | 0.63541 |  | Retention | Retention |  | 6 | 51 | C217-C219 | 1 | 0 | 0 | 8
WF6_2867 | C218 | NO | 0.093109 |  | Retention | Retention |  | 6 | 51 | C217-C219 | 1 | 0 | 0 | 8
WF6_2871 | C218 | NO | 0.053398 |  | Retention | Retention |  | 6 | 51 | C217-C219 | 1 | 0 | 0 | 8
WF6_7212 | C219 | NO | 0.046917 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 52 | C219-C221 | 1 | 0 | 0 | 0
WF6_2866 | C219 | NO | 0.7203 |  | Harvest Disposal | Mulch |  | 6 | 52 | C219-C221 | 1 | 0 | 0 | 0
WF6_2869 | C219 | NO | 0.4375 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 52 | C219-C221 | 0 | 1 | 0 | 0
WF6_2872 | C219 | NO | 0.86979 |  | Harvest Processing | Non-Mulch |  | 6 | 52 | C219-C221 | 1 | 0 | 0 | 0
WF6_2870 | C219 | NO | 0.15675 |  | Retention | Retention |  | 6 | 52 | C219-C221 | 1 | 0 | 0 | 8
WF6_2873 | C219 | NO | 0.12562 |  | Retention | Retention |  | 6 | 52 | C219-C221 | 1 | 0 | 0 | 8
WF6_2874 | C219 | NO | 0.22247 |  | Retention | Retention |  | 6 | 52 | C219-C221 | 1 | 0 | 0 | 8
WF6_2869 | C220 | NO | 0.33277 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 52 | C219-C221 | 0 | 1 | 0 | 0
WF6_2876 | C220 | NO | 0.011456 |  | Non-Merch Disposal | Mulch |  | 6 | 52 | C219-C221 | 1 | 0 | 0 | 0
WF6_2872 | C220 | NO | 1.7577 |  | Harvest Processing | Non-Mulch |  | 6 | 52 | C219-C221 | 1 | 0 | 0 | 0
WF6_7213 | C221 | NO | 0.081061 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 53 | C221-C223 | 1 | 0 | 0 | 0
WF6_2885 | C221 | NO | 0.16757 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 53 | C221-C223 | 0 | 1 | 0 | 0
WF6_2885 | C221 | NO | 0.16182 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 53 | C221-C223 | 0 | 1 | 0 | 0
WF6_2885 | C221 | NO | 0.14239 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 53 | C221-C223 | 0 | 1 | 0 | 0
WF6_2887 | C221 | NO | 0.13582 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 53 | C221-C223 | 0 | 1 | 0 | 0
WF6_2872 | C221 | NO | 1.179 |  | Harvest Processing | Non-Mulch |  | 6 | 53 | C221-C223 | 1 | 0 | 0 | 0
WF6_2881 | C221 | NO | 0.22347 |  | Harvest Processing | Non-Mulch |  | 6 | 53 | C221-C223 | 1 | 0 | 0 | 0
WF6_2878 | C221 | NO | 0.58045 |  | Retention | Retention |  | 6 | 53 | C221-C223 | 1 | 0 | 0 | 8
WF6_2879 | C221 | NO | 0.23932 |  | Retention | Retention |  | 6 | 53 | C221-C223 | 1 | 0 | 0 | 8
WF6_6463 | C222 | NO | 0.011131 |  | Harvest Processing | Non-Mulch |  | 6 | 53 | C221-C223 | 1 | 0 | 0 | 0
WF6_7214 | C222 | NO | 0.13215 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 53 | C221-C223 | 1 | 0 | 0 | 0
WF6_7215 | C222 | NO | 0.40984 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 53 | C221-C223 | 1 | 0 | 0 | 0
WF6_7216 | C222 | NO | 0.11076 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 53 | C221-C223 | 1 | 0 | 0 | 0
WF6_2887 | C222 | NO | 0.041164 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 53 | C221-C223 | 0 | 1 | 0 | 0
WF6_2887 | C222 | NO | 0.16478 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 53 | C221-C223 | 0 | 1 | 0 | 0
WF6_2887 | C222 | NO | 0.50541 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 53 | C221-C223 | 0 | 1 | 0 | 0
WF6_2881 | C222 | NO | 0.38525 |  | Harvest Processing | Non-Mulch |  | 6 | 53 | C221-C223 | 1 | 0 | 0 | 0
WF6_2882 | C222 | NO | 0.050837 |  | Retention | Retention |  | 6 | 53 | C221-C223 | 1 | 0 | 0 | 8
WF6_2884 | C222 | NO | 0.085209 |  | Retention | Retention |  | 6 | 53 | C221-C223 | 1 | 0 | 0 | 8
WF6_7774 | C222 | NO | 0.31874 |  | Harvest Processing | Non-Mulch |  | 6 | 53 | C221-C223 | 1 | 0 | 0 | 0
WF6_6464 | C223 | NO | 0.92708 |  | Harvest Processing | Non-Mulch |  | 6 | 54 | C223-C225 | 1 | 0 | 0 | 0
WF6_7219 | C223 | NO | 0.10374 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 54 | C223-C225 | 1 | 0 | 0 | 0
WF6_2883 | C223 | NO | 0.32035 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 54 | C223-C225 | 0 | 1 | 0 | 0
WF6_2887 | C223 | NO | 0.10435 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 54 | C223-C225 | 0 | 1 | 0 | 0
WF6_2886 | C223 | NO | 0.095537 |  | Retention | Retention |  | 6 | 54 | C223-C225 | 1 | 0 | 0 | 8
WF6_2889 | C223 | NO | 0.10326 |  | Retention | Retention |  | 6 | 54 | C223-C225 | 1 | 0 | 0 | 8
WF6_7775 | C223 | NO | 0.37235 |  | Harvest Processing | Non-Mulch |  | 6 | 54 | C223-C225 | 1 | 0 | 0 | 0
WF6_6465 | C224 | NO | 1.7559 |  | Harvest Processing | Non-Mulch |  | 6 | 54 | C223-C225 | 1 | 0 | 0 | 0
WF6_7217 | C224 | NO | 0.033227 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 54 | C223-C225 | 1 | 0 | 0 | 0
WF6_2883 | C224 | NO | 0.61874 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 54 | C223-C225 | 0 | 1 | 0 | 0
WF6_2888 | C224 | NO | 0.087495 |  | Retention | Retention |  | 6 | 54 | C223-C225 | 1 | 0 | 0 | 8
WF6_2891 | C224 | NO | 0.12342 |  | Retention | Retention |  | 6 | 54 | C223-C225 | 1 | 0 | 0 | 8
WF6_7218 | C225 | NO | 1.0837 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 55 | C225-C227 | 1 | 0 | 0 | 0
WF6_2892 | C225 | NO | 0.27456 |  | Retention | Retention |  | 6 | 55 | C225-C227 | 1 | 0 | 0 | 8
WF6_2897 | C225 | NO | 0.11015 |  | Retention | Retention |  | 6 | 55 | C225-C227 | 1 | 0 | 0 | 8
WF6_7727 | C225 | NO | 0.97472 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 55 | C225-C227 | 1 | 0 | 0 | 0
WF6_2910 | C226 | NO | 0.039258 |  | Non-Merch Disposal | Mulch | AU1 | 6 | 55 | C225-C227 | 0 | 1 | 0 | 0
WF6_2898 | C226 | NO | 0.013619 |  | Non-Merch Disposal | Mulch |  | 6 | 55 | C225-C227 | 1 | 0 | 0 | 0
WF6_2893 | C226 | NO | 0.25148 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 55 | C225-C227 | 1 | 0 | 0 | 0
WF6_7165 | C226 | NO | 0.68468 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 55 | C225-C227 | 1 | 0 | 0 | 0
WF6_2894 | C226 | NO | 0.24585 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 55 | C225-C227 | 0 | 1 | 0 | 0
WF6_2910 | C226 | NO | 0.32764 |  | Non-Merch Disposal | Mulch | AU1 | 6 | 55 | C225-C227 | 0 | 1 | 0 | 0
WF6_2902 | C226 | NO | 0.32272 |  | Non Productive | Non-Treed |  | 6 | 55 | C225-C227 | 1 | 0 | 0 | 0
WF6_2896 | C226 | NO | 0.10586 |  | Retention | Retention |  | 6 | 55 | C225-C227 | 1 | 0 | 0 | 8
WF6_2900 | C226 | NO | 0.078745 |  | Retention | Retention |  | 6 | 55 | C225-C227 | 1 | 0 | 0 | 8
WF6_2901 | C226 | NO | 0.030668 |  | Retention | Retention |  | 6 | 55 | C225-C227 | 1 | 0 | 0 | 8
WF6_2903 | C226 | NO | 0.093863 |  | Retention | Retention |  | 6 | 55 | C225-C227 | 1 | 0 | 0 | 8
WF6_2906 | C226 | NO | 0.092965 |  | Retention | Retention |  | 6 | 55 | C225-C227 | 1 | 0 | 0 | 8
WF6_2910 | C227 | NO | 1.0557 |  | Non-Merch Disposal | Mulch | AU1 | 6 | 57 | C225-C227 | 0 | 1 | 0 | 0
WF6_2905 | C227 | NO | 0.23936 |  | Non-Merch Disposal | Mulch |  | 6 | 58 | C227-C229 | 1 | 0 | 0 | 0
WF6_6354 | C227 | NO | 0.027233 |  | Non-Merch Disposal | Mulch |  | 6 | 58 | C227-C229 | 1 | 0 | 0 | 0
WF6_7166 | C227 | NO | 1.7743 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 58 | C227-C229 | 1 | 0 | 0 | 0
WF6_6119 | C227 | NO | 9.2591 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 56 | C225-C227 | 0 | 1 | 0 | 0
WF6_2910 | C227 | NO | 1.1023 |  | Non-Merch Disposal | Mulch | AU1 | 6 | 56 | C225-C227 | 0 | 1 | 0 | 0
WF6_2910 | C227 | NO | 0.1443 |  | Non-Merch Disposal | Mulch | AU1 | 6 | 58 | C227-C229 | 0 | 1 | 0 | 0
WF6_2910 | C227 | NO | 0.15098 |  | Non-Merch Disposal | Mulch | AU1 | 6 | 58 | C227-C229 | 0 | 1 | 0 | 0
WF6_2902 | C227 | NO | 0.17083 |  | Non Productive | Non-Treed |  | 6 | 58 | C227-C229 | 1 | 0 | 0 | 0
WF6_2904 | C227 | NO | 0.15017 |  | Retention | Retention |  | 6 | 58 | C227-C229 | 1 | 0 | 0 | 8
WF6_2907 | C227 | NO | 0.15588 |  | Retention | Retention |  | 6 | 58 | C227-C229 | 1 | 0 | 0 | 8
WF6_6354 | C228 | NO | 0.27086 |  | Non-Merch Disposal | Mulch |  | 6 | 58 | C227-C229 | 1 | 0 | 0 | 0
WF6_7220 | C228 | NO | 0.063975 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 58 | C227-C229 | 1 | 0 | 0 | 0
WF6_2913 | C228 | NO | 0.13668 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 58 | C227-C229 | 0 | 1 | 0 | 0
WF6_2908 | C228 | NO | 0.31116 |  | Harvest Processing | Non-Mulch |  | 6 | 58 | C227-C229 | 1 | 0 | 0 | 0
WF6_2909 | C228 | NO | 0.17998 |  | Retention | Retention |  | 6 | 58 | C227-C229 | 1 | 0 | 0 | 8
WF6_2911 | C228 | NO | 0.26848 |  | Retention | Retention |  | 6 | 58 | C227-C229 | 1 | 0 | 0 | 8
WF6_7777 | C228 | NO | 0.6504 |  | Harvest Processing | Non-Mulch |  | 6 | 58 | C227-C229 | 1 | 0 | 0 | 0
WF6_6466 | C229 | NO | 1.3713 |  | Harvest Processing | Non-Mulch |  | 6 | 59 | C229-C231 | 1 | 0 | 0 | 0
WF6_2913 | C229 | NO | 0.24711 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 59 | C229-C231 | 0 | 1 | 0 | 0
WF6_6120 | C229 | NO | 0.073332 |  | Non-Merch Disposal | Mulch | AU2 | 6 | 59 | C229-C231 | 0 | 1 | 0 | 0
WF6_6121 | C229 | NO | 0.021666 |  | Non-Merch Disposal | Mulch | AU2 | 6 | 59 | C229-C231 | 0 | 1 | 0 | 0
WF6_7221 | C230 | NO | 0.24066 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 59 | C229-C231 | 1 | 0 | 0 | 0
WF6_2916 | C230 | NO | 0.062852 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 59 | C229-C231 | 0 | 1 | 0 | 0
WF6_2918 | C230 | NO | 0.13624 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 59 | C229-C231 | 0 | 1 | 0 | 0
WF6_6121 | C230 | NO | 0.033391 |  | Non-Merch Disposal | Mulch | AU2 | 6 | 59 | C229-C231 | 0 | 1 | 0 | 0
WF6_7776 | C230 | NO | 0.4253 |  | Harvest Processing | Non-Mulch |  | 6 | 59 | C229-C231 | 1 | 0 | 0 | 0
WF6_7778 | C230 | NO | 0.90655 |  | Harvest Processing | Non-Mulch |  | 6 | 59 | C229-C231 | 1 | 0 | 0 | 0
WF6_7779 | C231 | NO | 1.7245 |  | Harvest Processing | Non-Mulch |  | 6 | 60 | C231-C233 | 1 | 0 | 0 | 0
WF6_2922 | C232 | YES | 0.027973 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 60 | C231-C233 | 1 | 0 | 0 | 0
WF6_2924 | C232 | YES | 0.067492 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 60 | C231-C233 | 1 | 0 | 0 | 0
WF6_2926 | C232 | YES | 0.01242 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 60 | C231-C233 | 1 | 0 | 0 | 0
WF6_6467 | C232 | NO | 1.4284 |  | Harvest Processing | Non-Mulch |  | 6 | 60 | C231-C233 | 1 | 0 | 0 | 0
WF6_7065 | C232 | YES | 0.081416 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 60 | C231-C233 | 1 | 0 | 0 | 0
WF6_7066 | C232 | YES | 0.064749 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 60 | C231-C233 | 1 | 0 | 0 | 0
WF6_7222 | C232 | NO | 0.017759 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 60 | C231-C233 | 1 | 0 | 0 | 0
WF6_7223 | C232 | NO | 0.08437 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 60 | C231-C233 | 1 | 0 | 0 | 0
WF6_7224 | C232 | NO | 0.036338 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 60 | C231-C233 | 1 | 0 | 0 | 0
WF6_7225 | C232 | NO | 0.03305 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 60 | C231-C233 | 1 | 0 | 0 | 0
WF6_6355 | C232 | NO | 0.04768 |  | Non-Merch Disposal | Mulch | AU2 | 6 | 60 | C231-C233 | 0 | 1 | 0 | 0
WF6_6355 | C232 | NO | 0.050886 |  | Non-Merch Disposal | Mulch | AU2 | 6 | 60 | C231-C233 | 0 | 1 | 0 | 0
WF6_2929 | C232 | NO | 0.054618 |  | Non-Merch Disposal | Mulch | AU2 | 6 | 60 | C231-C233 | 0 | 1 | 0 | 0
WF6_2929 | C232 | NO | 0.05474 |  | Non-Merch Disposal | Mulch | AU2 | 6 | 60 | C231-C233 | 0 | 1 | 0 | 0
WF6_2925 | C232 | NO | 0.56513 |  | Harvest Processing | Non-Mulch |  | 6 | 60 | C231-C233 | 1 | 0 | 0 | 0
WF6_2921 | C232 | YES | 0.70595 |  | Non Productive | Non-Treed |  | 6 | 60 | C231-C233 | 1 | 0 | 0 | 0
WF6_2919 | C232 | NO | 0.027114 |  | Retention | Retention |  | 6 | 60 | C231-C233 | 1 | 0 | 0 | 8
WF6_2920 | C232 | YES | 0.046296 |  | Retention | Retention |  | 6 | 60 | C231-C233 | 1 | 0 | 0 | 8
WF6_2923 | C232 | NO | 0.075276 |  | Retention | Retention |  | 6 | 60 | C231-C233 | 1 | 0 | 0 | 8
WF6_2927 | C232 | NO | 0.71352 |  | Retention | Retention |  | 6 | 60 | C231-C233 | 1 | 0 | 0 | 8
WF6_6355 | C233 | NO | 0.059781 |  | Non-Merch Disposal | Mulch | AU2 | 6 | 61 | C233-C235 | 0 | 1 | 0 | 0
WF6_6355 | C233 | NO | 0.027804 |  | Non-Merch Disposal | Mulch | AU2 | 6 | 61 | C233-C235 | 0 | 1 | 0 | 0
WF6_2928 | C233 | NO | 0.030638 |  | Non-Merch Disposal | Mulch |  | 6 | 61 | C233-C235 | 1 | 0 | 0 | 0
WF6_2929 | C233 | NO | 0.064074 |  | Non-Merch Disposal | Mulch | AU2 | 6 | 61 | C233-C235 | 0 | 1 | 0 | 0
WF6_2929 | C233 | NO | 0.027774 |  | Non-Merch Disposal | Mulch | AU2 | 6 | 61 | C233-C235 | 0 | 1 | 0 | 0
WF6_2925 | C233 | NO | 2.5836 |  | Harvest Processing | Non-Mulch |  | 6 | 61 | C233-C235 | 1 | 0 | 0 | 0
WF6_2927 | C233 | NO | 0.55556 |  | Retention | Retention |  | 6 | 61 | C233-C235 | 1 | 0 | 0 | 8
WF6_2932 | C233 | NO | 0.074281 |  | Retention | Retention |  | 6 | 61 | C233-C235 | 1 | 0 | 0 | 8
WF6_2935 | C234 | NO | 0.066353 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 61 | C233-C235 | 1 | 0 | 0 | 0
WF6_2936 | C234 | YES | 0.078551 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 61 | C233-C235 | 1 | 0 | 0 | 0
WF6_2938 | C234 | YES | 0.068967 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 61 | C233-C235 | 1 | 0 | 0 | 0
WF6_7226 | C234 | NO | 0.16102 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 61 | C233-C235 | 1 | 0 | 0 | 0
WF6_7227 | C234 | NO | 0.097821 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 61 | C233-C235 | 1 | 0 | 0 | 0
WF6_7229 | C234 | NO | 0.020543 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 61 | C233-C235 | 1 | 0 | 0 | 0
WF6_2914 | C234 | NO | 0.24499 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 61 | C233-C235 | 0 | 1 | 0 | 0
WF6_2914 | C234 | NO | 0.1144 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 61 | C233-C235 | 0 | 1 | 0 | 0
WF6_2915 | C234 | NO | 0.22555 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 61 | C233-C235 | 0 | 1 | 0 | 0
WF6_2915 | C234 | NO | 0.32393 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 61 | C233-C235 | 0 | 1 | 0 | 0
WF6_2915 | C234 | NO | 0.015282 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 62 | C235-C237 | 0 | 1 | 0 | 0
WF6_2925 | C234 | NO | 0.38957 |  | Harvest Processing | Non-Mulch |  | 6 | 61 | C233-C235 | 1 | 0 | 0 | 0
WF6_2933 | C234 | NO | 0.016299 |  | Harvest Processing | Non-Mulch |  | 6 | 61 | C233-C235 | 1 | 0 | 0 | 0
WF6_2937 | C234 | NO | 0.24791 |  | Harvest Processing | Non-Mulch |  | 6 | 61 | C233-C235 | 1 | 0 | 0 | 0
WF6_2940 | C234 | NO | 0.012402 |  | Harvest Processing | Non-Mulch |  | 6 | 61 | C233-C235 | 1 | 0 | 0 | 0
WF6_2931 | C234 | NO | 0.090334 |  | Retention | Retention |  | 6 | 61 | C233-C235 | 1 | 0 | 0 | 8
WF6_2934 | C234 | NO | 0.44717 |  | Retention | Retention |  | 6 | 61 | C233-C235 | 1 | 0 | 0 | 8
WF6_6468 | C235 | NO | 0.73498 |  | Harvest Processing | Non-Mulch |  | 6 | 62 | C235-C237 | 1 | 0 | 0 | 0
WF6_7228 | C235 | NO | 0.14113 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 62 | C235-C237 | 1 | 0 | 0 | 0
WF6_2915 | C235 | NO | 0.040752 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 62 | C235-C237 | 0 | 1 | 0 | 0
WF6_2917 | C235 | NO | 0.81043 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 62 | C235-C237 | 0 | 1 | 0 | 0
WF6_2937 | C235 | NO | 0.88499 |  | Harvest Processing | Non-Mulch |  | 6 | 62 | C235-C237 | 1 | 0 | 0 | 0
WF6_2917 | C235 | NO | 0.015691 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 62 | C235-C237 | 0 | 1 | 0 | 0
WF6_2947 | C236 | YES | 0.10368 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 62 | C235-C237 | 1 | 0 | 0 | 0
WF6_2948 | C236 | YES | 0.12929 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 62 | C235-C237 | 1 | 0 | 0 | 0
WF6_2951 | C236 | YES | 0.069652 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 62 | C235-C237 | 1 | 0 | 0 | 0
WF6_7067 | C236 | YES | 0.080531 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 62 | C235-C237 | 1 | 0 | 0 | 0
WF6_7230 | C236 | NO | 0.016278 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 62 | C235-C237 | 1 | 0 | 0 | 0
WF6_7231 | C236 | NO | 0.016734 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 62 | C235-C237 | 1 | 0 | 0 | 0
WF6_2917 | C236 | NO | 0.90709 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 62 | C235-C237 | 0 | 1 | 0 | 0
WF6_2945 | C236 | NO | 1.0085 |  | Harvest Processing | Non-Mulch |  | 6 | 62 | C235-C237 | 1 | 0 | 0 | 0
WF6_2950 | C236 | NO | 0.42376 |  | Harvest Processing | Non-Mulch |  | 6 | 62 | C235-C237 | 1 | 0 | 0 | 0
WF6_2944 | C236 | NO | 0.04736 |  | Non Productive | Non-Treed |  | 6 | 62 | C235-C237 | 1 | 0 | 0 | 0
WF6_7780 | C236 | NO | 0.17234 |  | Harvest Processing | Non-Mulch |  | 6 | 62 | C235-C237 | 1 | 0 | 0 | 0
WF6_2917 | C236 | NO | 0.015691 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 62 | C235-C237 | 0 | 1 | 0 | 0
WF6_2950 | C237 | NO | 1.4179 |  | Harvest Processing | Non-Mulch |  | 6 | 63 | C237-C239 | 1 | 0 | 0 | 0
WF6_7232 | C238 | NO | 0.10616 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 63 | C237-C239 | 1 | 0 | 0 | 0
WF6_2949 | C238 | NO | 0.29372 |  | Non-Merch Disposal | Mulch | AU2 | 6 | 63 | C237-C239 | 0 | 1 | 0 | 0
WF6_2950 | C238 | NO | 1.8929 |  | Harvest Processing | Non-Mulch |  | 6 | 63 | C237-C239 | 1 | 0 | 0 | 0
WF6_2956 | C238 | NO | 0.11067 |  | Retention | Retention |  | 6 | 63 | C237-C239 | 1 | 0 | 0 | 8
WF6_7233 | C239 | NO | 0.067676 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 64 | C239-C241 | 1 | 0 | 0 | 0
WF6_7234 | C239 | NO | 0.25502 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 64 | C239-C241 | 1 | 0 | 0 | 0
WF6_2950 | C239 | NO | 1.8014 |  | Harvest Processing | Non-Mulch |  | 6 | 64 | C239-C241 | 1 | 0 | 0 | 0
WF6_7235 | C240 | NO | 0.049572 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 64 | C239-C241 | 1 | 0 | 0 | 0
WF6_6122 | C240 | NO | 0.22012 |  | Non-Merch Disposal | Mulch | AU2 | 6 | 64 | C239-C241 | 0 | 1 | 0 | 0
WF6_6122 | C240 | NO | 0.040396 |  | Non-Merch Disposal | Mulch | AU2 | 6 | 64 | C239-C241 | 0 | 1 | 0 | 0
WF6_2950 | C240 | NO | 1.8933 |  | Harvest Processing | Non-Mulch |  | 6 | 64 | C239-C241 | 1 | 0 | 0 | 0
WF6_2946 | C240 | NO | 0.38756 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 64 | C239-C241 | 0 | 1 | 0 | 0
WF6_2946 | C240 | NO | 0.059514 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 64 | C239-C241 | 0 | 1 | 0 | 0
WF6_7167 | C241 | NO | 0.50145 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 65 | C241-C243 | 1 | 0 | 0 | 0
WF6_7236 | C241 | NO | 0.017285 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 65 | C241-C243 | 1 | 0 | 0 | 0
WF6_7237 | C241 | NO | 0.021178 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 65 | C241-C243 | 1 | 0 | 0 | 0
WF6_7317 | C241 | NO | 0.27503 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 65 | C241-C243 | 0 | 1 | 0 | 0
WF6_7317 | C241 | NO | 0.10576 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 65 | C241-C243 | 0 | 1 | 0 | 0
WF6_7317 | C241 | NO | 0.12939 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 65 | C241-C243 | 0 | 1 | 0 | 0
WF6_2959 | C241 | NO | 0.066074 |  | Harvest Disposal | Mulch |  | 6 | 65 | C241-C243 | 1 | 0 | 0 | 0
WF6_2950 | C241 | NO | 0.73583 |  | Harvest Processing | Non-Mulch |  | 6 | 65 | C241-C243 | 1 | 0 | 0 | 0
WF6_2960 | C241 | NO | 0.13847 |  | Retention | Retention |  | 6 | 65 | C241-C243 | 1 | 0 | 0 | 8
WF6_7535 | C241 | NO | 0.22431 |  | Harvest Disposal | Mulch |  | 6 | 65 | C241-C243 | 1 | 0 | 0 | 0
WF6_7871 | C241 | NO | 0.01827 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 65 | C241-C243 | 1 | 0 | 0 | 0
WF6_6356 | C242 | NO | 0.23654 |  | Non-Merch Disposal | Mulch | AU1 | 6 | 67 | C241-C243 | 0 | 1 | 0 | 0
WF6_2980 | C242 | NO | 0.24011 |  | Non-Merch Disposal | Mulch | AU1 | 6 | 67 | C241-C243 | 0 | 1 | 0 | 0
WF6_2962 | C242 | NO | 0.15279 |  | Harvest Disposal | Mulch |  | 6 | 65 | C241-C243 | 1 | 0 | 0 | 0
WF6_2964 | C242 | NO | 0.011702 |  | Non-Merch Disposal | Mulch |  | 6 | 65 | C241-C243 | 1 | 0 | 0 | 0
WF6_2965 | C242 | NO | 0.020632 |  | Harvest Disposal | Mulch |  | 6 | 65 | C241-C243 | 1 | 0 | 0 | 0
WF6_2975 | C242 | NO | 0.010189 |  | Non-Merch Disposal | Mulch |  | 6 | 65 | C241-C243 | 1 | 0 | 0 | 0
WF6_7168 | C242 | NO | 0.071271 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 65 | C241-C243 | 1 | 0 | 0 | 0
WF6_7238 | C242 | NO | 0.13214 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 65 | C241-C243 | 1 | 0 | 0 | 0
WF6_6356 | C242 | NO | 0.32739 |  | Non-Merch Disposal | Mulch | AU1 | 6 | 65 | C241-C243 | 0 | 1 | 0 | 0
WF6_7317 | C242 | NO | 0.23059 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 65 | C241-C243 | 0 | 1 | 0 | 0
WF6_2952 | C242 | NO | 0.30611 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 65 | C241-C243 | 0 | 1 | 0 | 0
WF6_2952 | C242 | NO | 0.51797 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 65 | C241-C243 | 0 | 1 | 0 | 0
WF6_2978 | C242 | NO | 0.18411 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 65 | C241-C243 | 0 | 1 | 0 | 0
WF6_2980 | C242 | NO | 0.3384 |  | Non-Merch Disposal | Mulch | AU1 | 6 | 65 | C241-C243 | 0 | 1 | 0 | 0
WF6_6123 | C242 | NO | 0.51989 |  | Non-Merch Disposal | Mulch | AU1 | 6 | 65 | C241-C243 | 0 | 1 | 0 | 0
WF6_2967 | C242 | NO | 0.11957 |  | Harvest Processing | Non-Mulch |  | 6 | 65 | C241-C243 | 1 | 0 | 0 | 0
WF6_2971 | C242 | NO | 0.030463 |  | Harvest Processing | Non-Mulch |  | 6 | 65 | C241-C243 | 1 | 0 | 0 | 0
WF6_2973 | C242 | NO | 0.3901 |  | Harvest Processing | Non-Mulch |  | 6 | 65 | C241-C243 | 1 | 0 | 0 | 0
WF6_2972 | C242 | NO | 0.044389 |  | Non Productive | Non-Treed |  | 6 | 65 | C241-C243 | 1 | 0 | 0 | 0
WF6_2963 | C242 | NO | 0.32534 |  | Retention | Retention |  | 6 | 65 | C241-C243 | 1 | 0 | 0 | 8
WF6_2966 | C242 | NO | 0.095548 |  | Retention | Retention |  | 6 | 65 | C241-C243 | 1 | 0 | 0 | 8
WF6_2970 | C242 | NO | 0.3036 |  | Retention | Retention |  | 6 | 65 | C241-C243 | 1 | 0 | 0 | 8
WF6_2976 | C242 | NO | 0.25296 |  | Retention | Retention |  | 6 | 65 | C241-C243 | 1 | 0 | 0 | 8
WF6_7282 | C242 | NO | 0.75295 |  | Retention | Retention |  | 6 | 65 | C241-C243 | 1 | 0 | 0 | 8
WF6_7069 | C243 | NO | 0.29648 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 68 | C243-C245 | 1 | 0 | 0 | 0
WF6_7239 | C243 | NO | 0.53892 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 68 | C243-C245 | 1 | 0 | 0 | 0
WF6_2973 | C243 | NO | 0.23861 |  | Harvest Processing | Non-Mulch |  | 6 | 68 | C243-C245 | 1 | 0 | 0 | 0
WF6_2979 | C243 | NO | 0.096897 |  | Non Productive | Non-Treed |  | 6 | 68 | C243-C245 | 1 | 0 | 0 | 0
WF6_2982 | C243 | NO | 0.10886 |  | Non Productive | Non-Treed |  | 6 | 68 | C243-C245 | 1 | 0 | 0 | 0
WF6_2977 | C243 | NO | 1.0703 |  | Retention | Retention |  | 6 | 68 | C243-C245 | 1 | 0 | 0 | 8
WF6_2981 | C243 | YES | 0.087267 |  | Retention | Retention |  | 6 | 68 | C243-C245 | 1 | 0 | 0 | 8
WF6_7502 | C243 | NO | 0.012786 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 68 | C243-C245 | 1 | 0 | 0 | 0
WF6_2984 | C244 | NO | 0.05115 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 68 | C243-C245 | 1 | 0 | 0 | 0
WF6_7068 | C244 | NO | 0.025465 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 68 | C243-C245 | 1 | 0 | 0 | 0
WF6_7240 | C244 | NO | 0.078826 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 68 | C243-C245 | 1 | 0 | 0 | 0
WF6_7241 | C244 | NO | 0.090862 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 68 | C243-C245 | 1 | 0 | 0 | 0
WF6_2987 | C244 | NO | 0.23493 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 68 | C243-C245 | 0 | 1 | 0 | 0
WF6_2987 | C244 | NO | 0.95649 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 68 | C243-C245 | 0 | 1 | 0 | 0
WF6_2985 | C244 | NO | 1.6075 |  | Harvest Processing | Non-Mulch |  | 6 | 68 | C243-C245 | 1 | 0 | 0 | 0
WF6_2986 | C244 | NO | 0.030029 |  | Harvest Processing | Non-Mulch |  | 6 | 68 | C243-C245 | 1 | 0 | 0 | 0
WF6_7169 | C245 | NO | 0.5655 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 69 | C245-C247 | 1 | 0 | 0 | 0
WF6_2990 | C245 | NO | 0.015246 |  | Harvest Disposal | Mulch |  | 6 | 69 | C245-C247 | 1 | 0 | 0 | 0
WF6_2995 | C245 | NO | 0.37808 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 69 | C245-C247 | 0 | 1 | 0 | 0
WF6_2985 | C245 | NO | 1.5453 |  | Harvest Processing | Non-Mulch |  | 6 | 69 | C245-C247 | 1 | 0 | 0 | 0
WF6_2989 | C245 | NO | 0.029925 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 69 | C245-C247 | 1 | 0 | 0 | 0
WF6_2974 | C245 | NO | 0.25594 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 69 | C245-C247 | 0 | 1 | 0 | 0
WF6_2974 | C245 | NO | 0.31287 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 69 | C245-C247 | 0 | 1 | 0 | 0
WF6_2974 | C245 | NO | 0.32745 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 69 | C245-C247 | 0 | 1 | 0 | 0
WF6_2988 | C245 | NO | 0.119 |  | Retention | Retention |  | 6 | 69 | C245-C247 | 1 | 0 | 0 | 8
WF6_2991 | C245 | NO | 0.18283 |  | Retention | Retention |  | 6 | 69 | C245-C247 | 1 | 0 | 0 | 8
WF6_6357 | C246 | NO | 0.055017 |  | Harvest Disposal | Mulch |  | 6 | 69 | C245-C247 | 1 | 0 | 0 | 0
WF6_7242 | C246 | NO | 0.12842 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 69 | C245-C247 | 1 | 0 | 0 | 0
WF6_2995 | C246 | NO | 0.15317 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 69 | C245-C247 | 0 | 1 | 0 | 0
WF6_2992 | C246 | NO | 0.032053 |  | Harvest Processing | Non-Mulch |  | 6 | 69 | C245-C247 | 1 | 0 | 0 | 0
WF6_2993 | C246 | NO | 1.5404 |  | Harvest Processing | Non-Mulch |  | 6 | 69 | C245-C247 | 1 | 0 | 0 | 0
WF6_7872 | C246 | NO | 0.35416 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 69 | C245-C247 | 1 | 0 | 0 | 0
WF6_2999 | C247 | NO | 0.055453 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 70 | C247-C249 | 1 | 0 | 0 | 0
WF6_2996 | C247 | NO | 0.23628 |  | Harvest Disposal | Mulch |  | 6 | 70 | C247-C249 | 1 | 0 | 0 | 0
WF6_2997 | C247 | NO | 0.12492 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 70 | C247-C249 | 1 | 0 | 0 | 0
WF6_7070 | C247 | NO | 0.16781 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 70 | C247-C249 | 1 | 0 | 0 | 0
WF6_7170 | C247 | NO | 0.38758 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 70 | C247-C249 | 1 | 0 | 0 | 0
WF6_2942 | C247 | NO | 1.9641 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 71 | C247-C249 | 0 | 1 | 0 | 0
WF6_2958 | C247 | NO | 0.29565 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 70 | C247-C249 | 0 | 1 | 0 | 0
WF6_2958 | C247 | NO | 0.8218 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 70 | C247-C249 | 0 | 1 | 0 | 0
WF6_2958 | C247 | NO | 0.31796 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 71 | C247-C249 | 0 | 1 | 0 | 0
WF6_2993 | C247 | NO | 0.22407 |  | Harvest Processing | Non-Mulch |  | 6 | 70 | C247-C249 | 1 | 0 | 0 | 0
WF6_2998 | C247 | NO | 0.55483 |  | Retention | Retention |  | 6 | 70 | C247-C249 | 1 | 0 | 0 | 8
WF6_2958 | C247 | NO | 0.011688 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 70 | C247-C249 | 0 | 1 | 0 | 0
WF6_3001 | C248 | YES | 0.10687 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 70 | C247-C249 | 1 | 0 | 0 | 0
WF6_3009 | C248 | YES | 0.084072 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 70 | C247-C249 | 1 | 0 | 0 | 0
WF6_3011 | C248 | NO | 0.17658 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 70 | C247-C249 | 1 | 0 | 0 | 0
WF6_7171 | C248 | NO | 0.017446 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 70 | C247-C249 | 1 | 0 | 0 | 0
WF6_3010 | C248 | NO | 0.23504 |  | Harvest Disposal | Mulch |  | 6 | 70 | C247-C249 | 1 | 0 | 0 | 0
WF6_3003 | C248 | NO | 1.2176 |  | Non Productive | Non-Treed |  | 6 | 70 | C247-C249 | 1 | 0 | 0 | 0
WF6_3000 | C248 | YES | 0.0566 |  | Retention | Retention |  | 6 | 70 | C247-C249 | 1 | 0 | 0 | 8
WF6_3006 | C248 | NO | 0.24969 |  | Retention | Retention |  | 6 | 70 | C247-C249 | 1 | 0 | 0 | 8
WF6_3007 | C248 | YES | 0.034938 |  | Retention | Retention |  | 6 | 70 | C247-C249 | 1 | 0 | 0 | 8
WF6_3012 | C248 | NO | 0.24434 |  | Retention | Retention |  | 6 | 70 | C247-C249 | 1 | 0 | 0 | 8
WF6_7855 | C248 | NO | 0.17318 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 70 | C247-C249 | 1 | 0 | 0 | 0
WF6_2958 | C248 | NO | 0.011688 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 70 | C247-C249 | 0 | 1 | 0 | 0
WF6_3013 | C249 | NO | 0.12578 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 72 | C249-C251 | 1 | 0 | 0 | 0
WF6_7172 | C249 | NO | 0.020875 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 72 | C249-C251 | 1 | 0 | 0 | 0
WF6_7173 | C249 | NO | 0.42735 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 72 | C249-C251 | 1 | 0 | 0 | 0
WF6_2942 | C249 | NO | 0.32899 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 71 | C247-C249 | 0 | 1 | 0 | 0
WF6_2968 | C249 | NO | 0.02996 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 71 | C247-C249 | 0 | 1 | 0 | 0
WF6_2968 | C249 | NO | 0.71442 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 72 | C249-C251 | 0 | 1 | 0 | 0
WF6_2968 | C249 | NO | 0.767 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 72 | C249-C251 | 0 | 1 | 0 | 0
WF6_3010 | C249 | NO | 0.64808 |  | Harvest Disposal | Mulch |  | 6 | 72 | C249-C251 | 1 | 0 | 0 | 0
WF6_3014 | C249 | NO | 0.53263 |  | Harvest Disposal | Mulch |  | 6 | 72 | C249-C251 | 1 | 0 | 0 | 0
WF6_3015 | C249 | NO | 0.093906 |  | Retention | Retention |  | 6 | 72 | C249-C251 | 1 | 0 | 0 | 8
WF6_6516 | C249 | NO | 0.01259 |  | Retention | Retention |  | 6 | 72 | C249-C251 | 1 | 0 | 0 | 8
WF6_7283 | C249 | NO | 0.021136 |  | Retention | Retention |  | 6 | 72 | C249-C251 | 1 | 0 | 0 | 8
WF6_7284 | C249 | NO | 0.058701 |  | Retention | Retention |  | 6 | 72 | C249-C251 | 1 | 0 | 0 | 8
WF6_7174 | C250 | NO | 1.1359 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 72 | C249-C251 | 1 | 0 | 0 | 0
WF6_7175 | C250 | NO | 0.054772 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 72 | C249-C251 | 1 | 0 | 0 | 0
WF6_3014 | C250 | NO | 0.39443 |  | Harvest Disposal | Mulch |  | 6 | 72 | C249-C251 | 1 | 0 | 0 | 0
WF6_3017 | C250 | NO | 0.15519 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 72 | C249-C251 | 0 | 1 | 0 | 0
WF6_3025 | C250 | NO | 0.26099 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 72 | C249-C251 | 0 | 1 | 0 | 0
WF6_3020 | C250 | NO | 0.26188 |  | Retention | Retention |  | 6 | 72 | C249-C251 | 1 | 0 | 0 | 8
WF6_7737 | C250 | NO | 0.54869 |  | Harvest Disposal | Mulch |  | 6 | 72 | C249-C251 | 1 | 0 | 0 | 0
WF6_7873 | C250 | NO | 0.029525 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 72 | C249-C251 | 1 | 0 | 0 | 0
WF6_3021 | C251 | NO | 0.030383 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 73 | C251-C253 | 1 | 0 | 0 | 0
WF6_6302 | C251 | NO | 0.019707 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 73 | C251-C253 | 1 | 0 | 0 | 0
WF6_6303 | C251 | NO | 0.028065 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 73 | C251-C253 | 1 | 0 | 0 | 0
WF6_6358 | C251 | NO | 0.2456 |  | Harvest Disposal | Mulch |  | 6 | 73 | C251-C253 | 1 | 0 | 0 | 0
WF6_6359 | C251 | NO | 0.032567 |  | Harvest Disposal | Mulch |  | 6 | 73 | C251-C253 | 1 | 0 | 0 | 0
WF6_7071 | C251 | NO | 0.63388 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 73 | C251-C253 | 1 | 0 | 0 | 0
WF6_7176 | C251 | NO | 0.037882 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 73 | C251-C253 | 1 | 0 | 0 | 0
WF6_7177 | C251 | NO | 0.028593 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 73 | C251-C253 | 1 | 0 | 0 | 0
WF6_7178 | C251 | NO | 0.23923 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 73 | C251-C253 | 1 | 0 | 0 | 0
WF6_7244 | C251 | NO | 0.023615 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 73 | C251-C253 | 1 | 0 | 0 | 0
WF6_3017 | C251 | NO | 0.45314 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 73 | C251-C253 | 0 | 1 | 0 | 0
WF6_3022 | C251 | NO | 0.5587 |  | Harvest Disposal | Mulch |  | 6 | 73 | C251-C253 | 1 | 0 | 0 | 0
WF6_3019 | C251 | NO | 0.056078 |  | Retention | Retention |  | 6 | 73 | C251-C253 | 1 | 0 | 0 | 8
WF6_3023 | C251 | NO | 0.13838 |  | Retention | Retention |  | 6 | 73 | C251-C253 | 1 | 0 | 0 | 8
WF6_3024 | C251 | NO | 0.030306 |  | Retention | Retention |  | 6 | 73 | C251-C253 | 1 | 0 | 0 | 8
WF6_3027 | C251 | NO | 0.096388 |  | Retention | Retention |  | 6 | 73 | C251-C253 | 1 | 0 | 0 | 8
WF6_7285 | C251 | NO | 0.016608 |  | Retention | Retention |  | 6 | 73 | C251-C253 | 1 | 0 | 0 | 8
WF6_3035 | C252 | NO | 0.041736 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 73 | C251-C253 | 1 | 0 | 0 | 0
WF6_7243 | C252 | NO | 0.049184 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 73 | C251-C253 | 1 | 0 | 0 | 0
WF6_7245 | C252 | NO | 0.023093 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 73 | C251-C253 | 1 | 0 | 0 | 0
WF6_7246 | C252 | NO | 0.052251 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 73 | C251-C253 | 1 | 0 | 0 | 0
WF6_7247 | C252 | NO | 0.013689 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 73 | C251-C253 | 1 | 0 | 0 | 0
WF6_3004 | C252 | NO | 0.3271 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 73 | C251-C253 | 0 | 1 | 0 | 0
WF6_3004 | C252 | NO | 0.29116 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 73 | C251-C253 | 0 | 1 | 0 | 0
WF6_3004 | C252 | NO | 0.734 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 73 | C251-C253 | 0 | 1 | 0 | 0
WF6_3028 | C252 | NO | 1.3814 |  | Harvest Processing | Non-Mulch |  | 6 | 73 | C251-C253 | 1 | 0 | 0 | 0
WF6_3033 | C252 | NO | 0.11157 |  | Harvest Processing | Non-Mulch |  | 6 | 73 | C251-C253 | 1 | 0 | 0 | 0
WF6_3030 | C252 | NO | 0.37947 |  | Retention | Retention |  | 6 | 73 | C251-C253 | 1 | 0 | 0 | 8
WF6_3031 | C252 | NO | 0.056496 |  | Retention | Retention |  | 6 | 73 | C251-C253 | 1 | 0 | 0 | 8
WF6_6517 | C252 | NO | 0.05309 |  | Retention | Retention |  | 6 | 73 | C251-C253 | 1 | 0 | 0 | 8
WF6_7286 | C252 | NO | 0.090153 |  | Retention | Retention |  | 6 | 73 | C251-C253 | 1 | 0 | 0 | 8
WF6_7287 | C252 | NO | 0.068876 |  | Retention | Retention |  | 6 | 73 | C251-C253 | 1 | 0 | 0 | 8
WF6_7738 | C252 | NO | 0.090328 |  | Harvest Disposal | Mulch |  | 6 | 73 | C251-C253 | 1 | 0 | 0 | 0
WF6_7874 | C252 | NO | 0.16385 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 73 | C251-C253 | 1 | 0 | 0 | 0
WF6_7882 | C252 | NO | 0.075291 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 73 | C251-C253 | 1 | 0 | 0 | 0
WF6_3004 | C252 | NO | 0.015367 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 73 | C251-C253 | 0 | 1 | 0 | 0
WF6_3039 | C253 | NO | 0.047705 |  | Harvest Disposal | Mulch |  | 6 | 74 | C253-C255 | 1 | 0 | 0 | 0
WF6_3043 | C253 | NO | 0.013592 |  | Harvest Processing | Non-Mulch |  | 6 | 74 | C253-C255 | 1 | 0 | 0 | 0
WF6_3038 | C253 | NO | 0.029533 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 74 | C253-C255 | 1 | 0 | 0 | 0
WF6_3042 | C253 | YES | 0.11722 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 74 | C253-C255 | 1 | 0 | 0 | 0
WF6_3037 | C253 | NO | 0.032564 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 74 | C253-C255 | 1 | 0 | 0 | 0
WF6_7248 | C253 | NO | 0.011782 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 74 | C253-C255 | 1 | 0 | 0 | 0
WF6_7249 | C253 | NO | 0.05737 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 74 | C253-C255 | 1 | 0 | 0 | 0
WF6_3004 | C253 | NO | 0.18485 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 73 | C251-C253 | 0 | 1 | 0 | 0
WF6_3004 | C253 | NO | 0.1091 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 74 | C253-C255 | 0 | 1 | 0 | 0
WF6_3004 | C253 | NO | 0.49732 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 74 | C253-C255 | 0 | 1 | 0 | 0
WF6_3004 | C253 | NO | 0.11953 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 74 | C253-C255 | 0 | 1 | 0 | 0
WF6_3034 | C253 | NO | 0.12847 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 74 | C253-C255 | 0 | 1 | 0 | 0
WF6_6198 | C253 | NO | 0.22835 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 74 | C253-C255 | 0 | 1 | 0 | 0
WF6_3033 | C253 | NO | 1.0471 |  | Harvest Processing | Non-Mulch |  | 6 | 74 | C253-C255 | 1 | 0 | 0 | 0
WF6_3036 | C253 | NO | 0.32301 |  | Retention | Retention |  | 6 | 74 | C253-C255 | 1 | 0 | 0 | 8
WF6_3041 | C253 | NO | 0.29741 |  | Retention | Retention |  | 6 | 74 | C253-C255 | 1 | 0 | 0 | 8
WF6_3004 | C253 | NO | 0.015367 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 73 | C251-C253 | 0 | 1 | 0 | 0
WF6_3046 | C254 | NO | 0.22395 |  | Harvest Disposal | Mulch |  | 6 | 74 | C253-C255 | 1 | 0 | 0 | 0
WF6_3040 | C254 | NO | 1.4545 |  | Harvest Processing | Non-Mulch |  | 6 | 74 | C253-C255 | 1 | 0 | 0 | 0
WF6_3034 | C254 | NO | 0.10611 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 74 | C253-C255 | 0 | 1 | 0 | 0
WF6_6198 | C254 | NO | 0.29671 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 74 | C253-C255 | 0 | 1 | 0 | 0
WF6_6198 | C254 | NO | 0.52547 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 74 | C253-C255 | 0 | 1 | 0 | 0
WF6_3044 | C254 | NO | 0.067405 |  | Retention | Retention |  | 6 | 74 | C253-C255 | 1 | 0 | 0 | 8
WF6_3045 | C254 | NO | 0.083102 |  | Retention | Retention |  | 6 | 74 | C253-C255 | 1 | 0 | 0 | 8
WF6_3048 | C254 | NO | 0.069259 |  | Retention | Retention |  | 6 | 74 | C253-C255 | 1 | 0 | 0 | 8
WF6_8197 | C254 | NO | 0.057505 |  | Hand Fall / Lop and Scatter | Mulch |  | 6 | 74 | C253-C255 | 1 | 0 | 0 | 0
WF6_7661 | C254 | NO | 0.036359 |  | Harvest Processing | Non-Mulch |  | 6 | 74 | C253-C255 | 1 | 0 | 0 | 0
WF6_7536 | C254 | NO | 0.053333 |  | Harvest Disposal | Mulch |  | 6 | 74 | C253-C255 | 1 | 0 | 0 | 0
WF6_8228 | C254 | NO | 0.037762 |  | Harvest Disposal | Mulch |  | 6 | 74 | C253-C255 | 1 | 0 | 0 | 0
WF6_8229 | C254 | NO | 0.095963 |  | Hand Fall / Lop and Scatter | Mulch |  | 6 | 74 | C253-C255 | 1 | 0 | 0 | 0
WF6_7538 | C255 | NO | 1.4538 |  | Harvest Disposal | Mulch |  | 6 | 75 | C255-C257 | 1 | 0 | 0 | 0
WF6_8230 | C255 | NO | 0.16305 |  | Hand Fall / Lop and Scatter | Mulch |  | 6 | 75 | C255-C257 | 1 | 0 | 0 | 0
WF6_3049 | C256 | NO | 0.22973 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 75 | C255-C257 | 1 | 0 | 0 | 0
WF6_3052 | C256 | NO | 0.44079 |  | Harvest Disposal | Mulch |  | 6 | 75 | C255-C257 | 1 | 0 | 0 | 0
WF6_3056 | C256 | NO | 0.16953 |  | Harvest Disposal | Mulch |  | 6 | 75 | C255-C257 | 1 | 0 | 0 | 0
WF6_3055 | C256 | NO | 0.10409 |  | Non Productive | Non-Treed |  | 6 | 75 | C255-C257 | 1 | 0 | 0 | 0
WF6_3050 | C256 | NO | 0.5416 |  | Retention | Retention |  | 6 | 75 | C255-C257 | 1 | 0 | 0 | 8
WF6_3054 | C256 | NO | 0.39417 |  | Retention | Retention |  | 6 | 75 | C255-C257 | 1 | 0 | 0 | 8
WF6_3057 | C256 | NO | 0.032888 |  | Retention | Retention |  | 6 | 75 | C255-C257 | 1 | 0 | 0 | 8
WF6_8198 | C256 | NO | 0.17061 |  | Hand Fall / Lop and Scatter | Mulch |  | 6 | 75 | C255-C257 | 1 | 0 | 0 | 0
WF6_7537 | C256 | NO | 0.058296 |  | Harvest Disposal | Mulch |  | 6 | 75 | C255-C257 | 1 | 0 | 0 | 0
WF6_7179 | C257 | NO | 0.79644 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 76 | C257-C259 | 1 | 0 | 0 | 0
WF6_3053 | C257 | NO | 0.34647 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 76 | C257-C259 | 0 | 1 | 0 | 0
WF6_3056 | C257 | NO | 0.54854 |  | Harvest Disposal | Mulch |  | 6 | 76 | C257-C259 | 1 | 0 | 0 | 0
WF6_7875 | C257 | NO | 0.029992 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 76 | C257-C259 | 1 | 0 | 0 | 0
WF6_3062 | C258 | YES | 0.03107 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 76 | C257-C259 | 1 | 0 | 0 | 0
WF6_6304 | C258 | YES | 0.03026 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 76 | C257-C259 | 1 | 0 | 0 | 0
WF6_6360 | C258 | NO | 0.33292 |  | Harvest Disposal | Mulch |  | 6 | 76 | C257-C259 | 1 | 0 | 0 | 0
WF6_7072 | C258 | YES | 0.40191 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 76 | C257-C259 | 1 | 0 | 0 | 0
WF6_7180 | C258 | NO | 0.92001 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 76 | C257-C259 | 1 | 0 | 0 | 0
WF6_7250 | C258 | NO | 0.079551 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 76 | C257-C259 | 1 | 0 | 0 | 0
WF6_3053 | C258 | NO | 0.16918 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 76 | C257-C259 | 0 | 1 | 0 | 0
WF6_3060 | C258 | NO | 0.14208 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 76 | C257-C259 | 0 | 1 | 0 | 0
WF6_3063 | C258 | NO | 0.23088 |  | Harvest Processing | Non-Mulch |  | 6 | 76 | C257-C259 | 1 | 0 | 0 | 0
WF6_3059 | C258 | NO | 0.13929 |  | Retention | Retention |  | 6 | 76 | C257-C259 | 1 | 0 | 0 | 8
WF6_3070 | C259 | YES | 0.40056 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 77 | C259-C261 | 1 | 0 | 0 | 0
WF6_3064 | C259 | YES | 0.20371 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 77 | C259-C261 | 1 | 0 | 0 | 0
WF6_3066 | C259 | YES | 0.94426 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 77 | C259-C261 | 1 | 0 | 0 | 0
WF6_3069 | C259 | YES | 0.02957 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 77 | C259-C261 | 1 | 0 | 0 | 0
WF6_7251 | C259 | NO | 0.10634 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 77 | C259-C261 | 1 | 0 | 0 | 0
WF6_3058 | C259 | NO | 0.70497 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 77 | C259-C261 | 0 | 1 | 0 | 0
WF6_3063 | C259 | NO | 0.17497 |  | Harvest Processing | Non-Mulch |  | 6 | 77 | C259-C261 | 1 | 0 | 0 | 0
WF6_3072 | C259 | NO | 0.039219 |  | Harvest Processing | Non-Mulch |  | 6 | 77 | C259-C261 | 1 | 0 | 0 | 0
WF6_3065 | C259 | YES | 0.059874 |  | Non Productive | Non-Treed |  | 6 | 77 | C259-C261 | 1 | 0 | 0 | 0
WF6_3068 | C259 | YES | 0.24989 |  | Non Productive | Non-Treed |  | 6 | 77 | C259-C261 | 1 | 0 | 0 | 0
WF6_7271 | C259 | YES | 0.023112 |  | Non Productive | Non-Treed |  | 6 | 77 | C259-C261 | 1 | 0 | 0 | 0
WF6_7272 | C259 | YES | 0.012546 |  | Non Productive | Non-Treed |  | 6 | 77 | C259-C261 | 1 | 0 | 0 | 0
WF6_7273 | C259 | YES | 0.016072 |  | Non Productive | Non-Treed |  | 6 | 77 | C259-C261 | 1 | 0 | 0 | 0
WF6_3077 | C260 | YES | 0.33676 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 77 | C259-C261 | 1 | 0 | 0 | 0
WF6_3085 | C260 | YES | 0.02669 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 77 | C259-C261 | 1 | 0 | 0 | 0
WF6_7252 | C260 | NO | 0.14151 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 77 | C259-C261 | 1 | 0 | 0 | 0
WF6_3071 | C260 | NO | 0.47146 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 77 | C259-C261 | 0 | 1 | 0 | 0
WF6_3072 | C260 | NO | 0.16536 |  | Harvest Processing | Non-Mulch |  | 6 | 77 | C259-C261 | 1 | 0 | 0 | 0
WF6_3078 | C260 | NO | 0.14023 |  | Harvest Processing | Non-Mulch |  | 6 | 77 | C259-C261 | 1 | 0 | 0 | 0
WF6_3074 | C260 | YES | 0.10437 |  | Non Productive | Non-Treed |  | 6 | 77 | C259-C261 | 1 | 0 | 0 | 0
WF6_3075 | C260 | YES | 0.032662 |  | Non Productive | Non-Treed |  | 6 | 77 | C259-C261 | 1 | 0 | 0 | 0
WF6_3073 | C260 | YES | 0.033663 |  | Retention | Retention |  | 6 | 77 | C259-C261 | 1 | 0 | 0 | 8
WF6_3076 | C260 | YES | 0.086622 |  | Retention | Retention |  | 6 | 77 | C259-C261 | 1 | 0 | 0 | 8
WF6_3084 | C260 | YES | 0.1256 |  | Retention | Retention |  | 6 | 77 | C259-C261 | 1 | 0 | 0 | 8
WF6_7274 | C260 | YES | 0.035372 |  | Non Productive | Non-Treed |  | 6 | 77 | C259-C261 | 1 | 0 | 0 | 0
WF6_7503 | C260 | YES | 0.35282 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 77 | C259-C261 | 1 | 0 | 0 | 0
WF6_7253 | C261 | NO | 0.17724 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 78 | C261-C263 | 1 | 0 | 0 | 0
WF6_6197 | C261 | NO | 0.16646 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 78 | C261-C263 | 0 | 1 | 0 | 0
WF6_6197 | C261 | NO | 0.015932 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 78 | C261-C263 | 0 | 1 | 0 | 0
WF6_3071 | C261 | NO | 0.016644 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 78 | C261-C263 | 0 | 1 | 0 | 0
WF6_3088 | C261 | NO | 0.21985 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 78 | C261-C263 | 0 | 1 | 0 | 0
WF6_3088 | C261 | NO | 0.026751 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 78 | C261-C263 | 0 | 1 | 0 | 0
WF6_3078 | C261 | NO | 0.26599 |  | Harvest Processing | Non-Mulch |  | 6 | 78 | C261-C263 | 1 | 0 | 0 | 0
WF6_3083 | C261 | NO | 0.53253 |  | Harvest Processing | Non-Mulch |  | 6 | 78 | C261-C263 | 0 | 1 | 0 | 0
WF6_3067 | C261 | NO | 0.71685 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 78 | C261-C263 | 1 | 0 | 0 | 0
WF6_3082 | C261 | NO | 0.047519 |  | Non Productive | Non-Treed |  | 6 | 78 | C261-C263 | 1 | 0 | 0 | 0
WF6_3061 | C261 | NO | 0.31596 |  | Retention | Retention |  | 6 | 78 | C261-C263 | 1 | 0 | 0 | 8
WF6_7254 | C262 | NO | 0.37557 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 78 | C261-C263 | 1 | 1 | 0 | 0
WF6_3083 | C262 | NO | 1.8222 |  | Harvest Processing | Non-Mulch |  | 6 | 78 | C261-C263 | 0 | 1 | 0 | 0
WF6_3086 | C262 | NO | 0.6513 |  | Harvest Processing | Non-Mulch |  | 6 | 78 | C261-C263 | 1 | 0 | 0 | 0
WF6_3087 | C262 | NO | 0.38347 |  | Retention | Retention |  | 6 | 78 | C261-C263 | 1 | 0 | 0 | 8
WF6_3083 | C263 | NO | 2.2285 |  | Harvest Processing | Non-Mulch |  | 6 | 79 | C263-C265 | 0 | 1 | 0 | 0
WF6_6207 | C264 | NO | 0.017191 |  | Non-Merch Disposal | Mulch | AU2 | 6 | 79 | C263-C265 | 0 | 1 | 0 | 0
WF6_6361 | C264 | NO | 0.18422 |  | Non-Merch Disposal | Mulch | AU2 | 6 | 80 | C263-C265 | 0 | 1 | 0 | 0
WF6_6409 | C264 | NO | 0.017019 |  | Non-Merch Disposal | Mulch | AU2 | 6 | 79 | C263-C265 | 0 | 1 | 0 | 0
WF6_3080 | C264 | NO | 0.17974 |  | Non-Merch Disposal | Mulch | AU2 | 6 | 80 | C263-C265 | 0 | 1 | 0 | 0
WF6_3089 | C264 | NO | 0.15804 |  | Non-Merch Disposal | Mulch | AU2 | 6 | 79 | C263-C265 | 0 | 1 | 0 | 0
WF6_3089 | C264 | NO | 0.03102 |  | Non-Merch Disposal | Mulch | AU2 | 6 | 79 | C263-C265 | 0 | 1 | 0 | 0
WF6_3089 | C264 | NO | 0.033998 |  | Non-Merch Disposal | Mulch | AU2 | 6 | 79 | C263-C265 | 0 | 1 | 0 | 0
WF6_3089 | C264 | NO | 0.34847 |  | Non-Merch Disposal | Mulch | AU2 | 6 | 80 | C263-C265 | 0 | 1 | 0 | 0
WF6_3089 | C264 | NO | 0.34471 |  | Non-Merch Disposal | Mulch | AU2 | 6 | 80 | C263-C265 | 0 | 1 | 0 | 0
WF6_3094 | C264 | NO | 0.058585 |  | Non-Merch Disposal | Mulch | AU2 | 6 | 79 | C263-C265 | 0 | 1 | 0 | 0
WF6_3095 | C264 | NO | 0.60782 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 79 | C263-C265 | 0 | 1 | 0 | 0
WF6_6124 | C264 | NO | 0.060172 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 79 | C263-C265 | 0 | 1 | 0 | 0
WF6_3083 | C264 | NO | 2.2328 |  | Harvest Processing | Non-Mulch |  | 6 | 79 | C263-C265 | 0 | 1 | 0 | 0
WF6_3093 | C264 | NO | 0.075216 |  | Harvest Processing | Non-Mulch |  | 6 | 79 | C263-C265 | 1 | 0 | 0 | 0
WF6_3095 | C265 | NO | 0.080845 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 79 | C263-C265 | 0 | 1 | 0 | 0
WF6_3095 | C265 | NO | 0.51692 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 81 | C265-C267 | 0 | 1 | 0 | 0
WF6_3083 | C265 | NO | 0.023785 |  | Harvest Processing | Non-Mulch |  | 6 | 79 | C263-C265 | 0 | 1 | 0 | 0
WF6_3083 | C265 | NO | 1.8436 |  | Harvest Processing | Non-Mulch |  | 6 | 81 | C265-C267 | 0 | 1 | 0 | 0
WF6_3093 | C265 | NO | 0.020131 |  | Harvest Processing | Non-Mulch |  | 6 | 81 | C265-C267 | 1 | 0 | 0 | 0
WF6_3096 | C265 | NO | 0.95963 |  | Harvest Processing | Non-Mulch |  | 6 | 81 | C265-C267 | 1 | 0 | 0 | 0
WF6_3097 | C266 | YES | 0.02262 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 81 | C265-C267 | 1 | 0 | 0 | 0
WF6_6469 | C266 | NO | 0.65416 |  | Harvest Processing | Non-Mulch |  | 6 | 81 | C265-C267 | 1 | 0 | 0 | 0
WF6_7073 | C266 | YES | 0.42019 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 81 | C265-C267 | 1 | 0 | 0 | 0
WF6_7255 | C266 | NO | 0.29261 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 81 | C265-C267 | 1 | 0 | 0 | 0
WF6_7256 | C266 | NO | 0.083269 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 81 | C265-C267 | 1 | 0 | 0 | 0
WF6_3101 | C266 | NO | 0.61653 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 81 | C265-C267 | 0 | 1 | 0 | 0
WF6_3101 | C266 | NO | 0.20267 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 82 | C267-C269 | 0 | 1 | 0 | 0
WF6_3083 | C266 | NO | 0.078606 |  | Harvest Processing | Non-Mulch |  | 6 | 81 | C265-C267 | 0 | 1 | 0 | 0
WF6_3098 | C266 | NO | 0.014504 |  | Harvest Processing | Non-Mulch |  | 6 | 81 | C265-C267 | 1 | 0 | 0 | 0
WF6_3099 | C266 | NO | 1.7293 |  | Harvest Processing | Non-Mulch |  | 6 | 81 | C265-C267 | 1 | 0 | 0 | 0
WF6_3101 | C267 | NO | 0.069658 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 82 | C267-C269 | 0 | 1 | 0 | 0
WF6_3102 | C267 | NO | 0.087093 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 82 | C267-C269 | 0 | 1 | 0 | 0
WF6_3099 | C267 | NO | 2.5336 |  | Harvest Processing | Non-Mulch |  | 6 | 82 | C267-C269 | 1 | 0 | 0 | 0
WF6_6195 | C268 | NO | 0.21282 |  | Harvest Disposal | Mulch |  | 6 | 82 | C267-C269 | 1 | 0 | 0 | 0
WF6_6195 | C268 | NO | 0.011131 |  | Harvest Disposal | Mulch |  | 6 | 83 | C269-C271 | 1 | 0 | 0 | 0
WF6_3103 | C268 | NO | 0.28329 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 82 | C267-C269 | 0 | 1 | 0 | 0
WF6_3103 | C268 | NO | 0.26696 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 82 | C267-C269 | 0 | 1 | 0 | 0
WF6_3103 | C268 | NO | 0.26019 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 82 | C267-C269 | 0 | 1 | 0 | 0
WF6_3099 | C268 | NO | 1.466 |  | Harvest Processing | Non-Mulch |  | 6 | 82 | C267-C269 | 1 | 0 | 0 | 0
WF6_3104 | C268 | NO | 0.13755 |  | Retention | Retention |  | 6 | 82 | C267-C269 | 1 | 0 | 0 | 8
WF6_3105 | C268 | NO | 0.21727 |  | Retention | Retention |  | 6 | 82 | C267-C269 | 1 | 0 | 0 | 8
WF6_3103 | C268 | NO | 0.024094 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 82 | C267-C269 | 0 | 1 | 0 | 0
WF6_3103 | C268 | NO | 0.024094 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 82 | C267-C269 | 0 | 1 | 0 | 0
WF6_7182 | C269 | NO | 0.48098 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 83 | C269-C271 | 1 | 0 | 0 | 0
WF6_3103 | C269 | NO | 0.053912 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 82 | C267-C269 | 0 | 1 | 0 | 0
WF6_3103 | C269 | NO | 0.59699 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 83 | C269-C271 | 0 | 1 | 0 | 0
WF6_3110 | C269 | NO | 0.15953 |  | Non Productive | Non-Treed |  | 6 | 83 | C269-C271 | 1 | 0 | 0 | 0
WF6_3107 | C269 | NO | 0.2147 |  | Retention | Retention |  | 6 | 83 | C269-C271 | 1 | 0 | 0 | 8
WF6_3108 | C269 | NO | 0.41261 |  | Retention | Retention |  | 6 | 83 | C269-C271 | 1 | 0 | 0 | 8
WF6_3109 | C269 | NO | 0.81964 |  | Retention | Retention |  | 6 | 83 | C269-C271 | 1 | 0 | 0 | 8
WF6_3111 | C269 | NO | 0.022662 |  | Retention | Retention |  | 6 | 83 | C269-C271 | 1 | 0 | 0 | 8
WF6_7615 | C269 | NO | 0.12929 |  | Harvest Disposal | Mulch |  | 6 | 83 | C269-C271 | 1 | 0 | 0 | 0
WF6_7616 | C269 | NO | 0.018186 |  | Harvest Disposal | Mulch |  | 6 | 83 | C269-C271 | 1 | 0 | 0 | 0
WF6_7765 | C269 | NO | 0.57172 |  | Harvest Disposal | Mulch |  | 6 | 83 | C269-C271 | 1 | 0 | 0 | 0
WF6_6196 | C270 | NO | 0.31075 |  | Harvest Disposal | Mulch |  | 6 | 83 | C269-C271 | 1 | 0 | 0 | 0
WF6_6421 | C270 | NO | 0.017417 |  | Harvest Disposal | Mulch |  | 6 | 83 | C269-C271 | 1 | 0 | 0 | 0
WF6_6422 | C270 | NO | 0.12563 |  | Harvest Disposal | Mulch |  | 6 | 83 | C269-C271 | 1 | 0 | 0 | 0
WF6_7183 | C270 | NO | 1.0783 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 83 | C269-C271 | 1 | 0 | 0 | 0
WF6_3113 | C270 | NO | 0.35994 |  | Non Productive | Non-Treed |  | 6 | 83 | C269-C271 | 1 | 0 | 0 | 0
WF6_3114 | C270 | NO | 0.24303 |  | Retention | Retention |  | 6 | 83 | C269-C271 | 1 | 0 | 0 | 8
WF6_3116 | C270 | NO | 0.082095 |  | Retention | Retention |  | 6 | 83 | C269-C271 | 1 | 0 | 0 | 8
WF6_7275 | C270 | NO | 0.23762 |  | Non Productive | Non-Treed |  | 6 | 83 | C269-C271 | 1 | 0 | 0 | 0
WF6_7288 | C270 | NO | 0.32583 |  | Retention | Retention |  | 6 | 83 | C269-C271 | 1 | 0 | 0 | 8
WF6_3106 | C271 | NO | 0.49092 |  | Harvest Disposal | Mulch |  | 6 | 84 | C271-C273 | 1 | 0 | 0 | 0
WF6_6362 | C271 | NO | 0.12061 |  | Harvest Disposal | Mulch |  | 6 | 84 | C271-C273 | 1 | 0 | 0 | 0
WF6_7181 | C271 | NO | 0.5471 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 84 | C271-C273 | 1 | 0 | 0 | 0
WF6_3115 | C271 | NO | 0.53343 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 84 | C271-C273 | 0 | 1 | 0 | 0
WF6_3117 | C271 | NO | 0.19151 |  | Retention | Retention |  | 6 | 84 | C271-C273 | 1 | 0 | 0 | 8
WF6_3118 | C271 | NO | 0.45362 |  | Retention | Retention |  | 6 | 84 | C271-C273 | 1 | 0 | 0 | 8
WF6_3120 | C272 | NO | 0.10097 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 84 | C271-C273 | 0 | 1 | 0 | 0
WF6_3122 | C272 | NO | 0.18017 |  | Harvest Processing | Non-Mulch |  | 6 | 84 | C271-C273 | 1 | 0 | 0 | 0
WF6_3121 | C272 | NO | 0.079516 |  | Non Productive | Non-Treed |  | 6 | 84 | C271-C273 | 1 | 0 | 0 | 0
WF6_3119 | C272 | NO | 0.1461 |  | Retention | Retention |  | 6 | 84 | C271-C273 | 1 | 0 | 0 | 8
WF6_3123 | C272 | NO | 0.064273 |  | Retention | Retention |  | 6 | 84 | C271-C273 | 1 | 0 | 0 | 8
WF6_7739 | C272 | NO | 1.1881 |  | Harvest Disposal | Mulch |  | 6 | 84 | C271-C273 | 1 | 0 | 0 | 0
WF6_7257 | C273 | NO | 0.013831 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 85 | C273-C275 | 1 | 0 | 0 | 0
WF6_3122 | C273 | NO | 1.8311 |  | Harvest Processing | Non-Mulch |  | 6 | 85 | C273-C275 | 1 | 0 | 0 | 0
WF6_3124 | C274 | NO | 0.012373 |  | Harvest Processing | Non-Mulch |  | 6 | 85 | C273-C275 | 1 | 0 | 0 | 0
WF6_6470 | C274 | NO | 1.9185 |  | Harvest Processing | Non-Mulch |  | 6 | 85 | C273-C275 | 1 | 0 | 0 | 0
WF6_7257 | C274 | NO | 0.14013 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 85 | C273-C275 | 1 | 0 | 0 | 0
WF6_3132 | C274 | NO | 0.1021 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 85 | C273-C275 | 0 | 1 | 0 | 0
WF6_3132 | C274 | NO | 0.013908 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 86 | C275-C277 | 0 | 1 | 0 | 0
WF6_3122 | C274 | NO | 0.092615 |  | Harvest Processing | Non-Mulch |  | 6 | 85 | C273-C275 | 1 | 0 | 0 | 0
WF6_3127 | C275 | YES | 0.019357 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 86 | C275-C277 | 1 | 0 | 0 | 0
WF6_3130 | C275 | YES | 0.14847 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 86 | C275-C277 | 1 | 0 | 0 | 0
WF6_6305 | C275 | YES | 0.014823 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 86 | C275-C277 | 1 | 0 | 0 | 0
WF6_7074 | C275 | YES | 0.12057 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 86 | C275-C277 | 1 | 0 | 0 | 0
WF6_7075 | C275 | YES | 0.31229 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 86 | C275-C277 | 1 | 0 | 0 | 0
WF6_3132 | C275 | NO | 0.26398 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 86 | C275-C277 | 0 | 1 | 0 | 0
WF6_3132 | C275 | NO | 0.082492 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 86 | C275-C277 | 0 | 1 | 0 | 0
WF6_3132 | C275 | NO | 0.31487 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 86 | C275-C277 | 0 | 1 | 0 | 0
WF6_3131 | C275 | NO | 0.27063 |  | Harvest Processing | Non-Mulch |  | 6 | 86 | C275-C277 | 1 | 0 | 0 | 0
WF6_3128 | C275 | YES | 0.45816 |  | Non Productive | Non-Treed |  | 6 | 86 | C275-C277 | 1 | 0 | 0 | 0
WF6_3126 | C275 | YES | 0.070916 |  | Retention | Retention |  | 6 | 86 | C275-C277 | 1 | 0 | 0 | 8
WF6_3129 | C275 | NO | 0.18307 |  | Retention | Retention |  | 6 | 86 | C275-C277 | 1 | 0 | 0 | 8
WF6_3133 | C275 | YES | 0.11685 |  | Retention | Retention |  | 6 | 86 | C275-C277 | 1 | 0 | 0 | 8
WF6_7781 | C275 | NO | 0.27489 |  | Harvest Processing | Non-Mulch |  | 6 | 86 | C275-C277 | 1 | 0 | 0 | 0
WF6_3134 | C276 | YES | 0.010882 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 86 | C275-C277 | 1 | 0 | 0 | 0
WF6_3136 | C276 | YES | 0.012829 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 86 | C275-C277 | 1 | 0 | 0 | 0
WF6_3139 | C276 | YES | 0.030908 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 86 | C275-C277 | 1 | 0 | 0 | 0
WF6_6306 | C276 | YES | 0.012393 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 86 | C275-C277 | 1 | 0 | 0 | 0
WF6_7076 | C276 | YES | 0.058264 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 86 | C275-C277 | 1 | 0 | 0 | 0
WF6_7077 | C276 | YES | 0.011946 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 86 | C275-C277 | 1 | 0 | 0 | 0
WF6_7078 | C276 | YES | 0.031975 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 86 | C275-C277 | 1 | 0 | 0 | 0
WF6_7258 | C276 | NO | 0.18039 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 86 | C275-C277 | 1 | 0 | 0 | 0
WF6_3131 | C276 | NO | 0.90316 |  | Harvest Processing | Non-Mulch |  | 6 | 86 | C275-C277 | 1 | 0 | 0 | 0
WF6_3137 | C276 | NO | 0.038344 |  | Non Productive | Non-Treed |  | 6 | 86 | C275-C277 | 1 | 0 | 0 | 0
WF6_3135 | C276 | YES | 0.054518 |  | Retention | Retention |  | 6 | 86 | C275-C277 | 1 | 0 | 0 | 8
WF6_3138 | C276 | NO | 0.1826 |  | Retention | Retention |  | 6 | 86 | C275-C277 | 1 | 0 | 0 | 8
WF6_3140 | C276 | YES | 0.063172 |  | Retention | Retention |  | 6 | 86 | C275-C277 | 1 | 0 | 0 | 8
WF6_3142 | C276 | NO | 0.018262 |  | Retention | Retention |  | 6 | 86 | C275-C277 | 1 | 0 | 0 | 8
WF6_6518 | C276 | NO | 0.22935 |  | Retention | Retention |  | 6 | 86 | C275-C277 | 1 | 0 | 0 | 8
WF6_7289 | C276 | YES | 0.034153 |  | Retention | Retention |  | 6 | 86 | C275-C277 | 1 | 0 | 0 | 8
WF6_7290 | C276 | NO | 0.066229 |  | Retention | Retention |  | 6 | 86 | C275-C277 | 1 | 0 | 0 | 8
WF6_7504 | C276 | YES | 0.12355 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 86 | C275-C277 | 1 | 0 | 0 | 0
WF6_7663 | C276 | NO | 0.39784 |  | Harvest Processing | Non-Mulch |  | 6 | 86 | C275-C277 | 1 | 0 | 0 | 0
WF6_7856 | C276 | YES | 0.02 |  | Hand Fall / Lop and Scatter | Handfall |  | 6 | 86 | C275-C277 | 1 | 0 | 0 | 0
WF6_3143 | C277 | NO | 0.10915 |  | Retention | Retention |  | 6 | 87 | C277-C279 | 1 | 0 | 0 | 8
WF6_3144 | C277 | NO | 0.10831 |  | Retention | Retention |  | 6 | 87 | C277-C279 | 1 | 0 | 0 | 8
WF6_7662 | C277 | NO | 1.9486 |  | Harvest Processing | Non-Mulch |  | 6 | 87 | C277-C279 | 1 | 0 | 0 | 0
WF6_3150 | C278 | NO |  |  | Harvest Disposal | Mulch |  | 6 | 87 | C277-C279 | 0 | 0 | 1 | 0
WF6_3145 | C278 | NO |  |  | Harvest Processing | Non-Mulch |  | 6 | 87 | C277-C279 | 0 | 0 | 1 | 0
WF6_3166 | C278 | NO | 0.074562 |  | Non-Merch Disposal | Mulch |  | 6 | 87 | C277-C279 | 1 | 0 | 0 | 0
WF6_3141 | C278 | NO | 1.8761 |  | Harvest Processing | Non-Mulch |  | 6 | 87 | C277-C279 | 1 | 0 | 0 | 0
WF6_3141 | C278 | NO | 0.019042 |  | Harvest Processing | Non-Mulch |  | 6 | 87 | C277-C279 | 1 | 0 | 0 | 0
WF6_3163 | C278 | NO | 0.26685 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 87 | C277-C279 | 0 | 1 | 0 | 0
WF5_2229 | C99 | NO | 0.35204 |  | Non-Merch Disposal | Mulch | AN | 5 | 50 | C098-C100 | 0 | 1 | 0 | 0
WF6_3163 | D001 | NO | 0.01782 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 87 | C277-C279 | 0 | 1 | 0 | 0
WF6_6363 | D001 | NO | 0.072539 |  | Non-Merch Disposal | Mulch | ANWIN | 6 | 87 | C277-C279 | 0 | 1 | 0 | 0
WF7_3176 | D001 | NO | 1.3699 |  | Harvest Disposal | Mulch |  | 7 | 1 | D001-D003 | 1 | 0 | 0 | 0
WF7_3171 | D001 | NO | 0.10132 |  | Non Productive | Non-Treed | AU1 | 7 | 1 | D001-D003 | 0 | 1 | 0 | 0
WF7_3172 | D001 | NO | 0.17643 |  | Non Productive | Non-Treed |  | 7 | 1 | D001-D003 | 1 | 0 | 0 | 0
WF7_3173 | D001 | NO | 0.029811 |  | Non Productive | Non-Treed |  | 7 | 1 | D001-D003 | 1 | 0 | 0 | 0
WF7_3174 | D001 | NO | 0.08557 |  | Non Productive | Non-Treed |  | 7 | 1 | D001-D003 | 1 | 0 | 0 | 0
WF7_3176 | D002 | NO | 0.11827 |  | Harvest Disposal | Mulch |  | 7 | 1 | D001-D003 | 1 | 0 | 0 | 0
WF7_3195 | D002 | NO | 0.27858 |  | Harvest Disposal | Mulch |  | 7 | 1 | D001-D003 | 1 | 0 | 0 | 0
WF7_3206 | D002 | NO | 0.72927 |  | Harvest Disposal | Mulch |  | 7 | 1 | D001-D003 | 1 | 0 | 0 | 0
WF7_3191 | D002 | NO | 1.0039 |  | Harvest Processing | Non-Mulch |  | 7 | 1 | D001-D003 | 1 | 0 | 0 | 0
WF7_3204 | D002 | NO | 0.026577 |  | Non Productive | Non-Treed |  | 7 | 1 | D001-D003 | 1 | 0 | 0 | 0
WF7_3220 | D002 | NO | 0.052054 |  | Non Productive | Non-Treed |  | 7 | 1 | D001-D003 | 1 | 0 | 0 | 0
WF7_3206 | D003 | NO | 2.1972 |  | Harvest Disposal | Mulch |  | 7 | 2 | D003-D005 | 1 | 0 | 0 | 0
WF7_3220 | D003 | NO | 0.067981 |  | Non Productive | Non-Treed |  | 7 | 2 | D003-D005 | 1 | 0 | 0 | 0
WF7_3206 | D004 | NO | 2.0651 |  | Harvest Disposal | Mulch |  | 7 | 2 | D003-D005 | 1 | 0 | 0 | 0
WF7_3247 | D005 | YES | 0.13641 |  | Hand Fall / Lop and Scatter | Handfall |  | 7 | 3 | D005-D007 | 1 | 0 | 0 | 0
WF7_3263 | D005 | NO | 1.0938 |  | Non-Merch Disposal | Mulch |  | 7 | 3 | D005-D007 | 1 | 0 | 0 | 0
WF7_3206 | D005 | NO | 0.085957 |  | Harvest Disposal | Mulch |  | 7 | 3 | D005-D007 | 1 | 0 | 0 | 0
WF7_3273 | D005 | NO | 0.16566 |  | Harvest Disposal | Mulch |  | 7 | 3 | D005-D007 | 1 | 0 | 0 | 0
WF7_3253 | D005 | NO | 0.18753 |  | Non Productive | Non-Treed |  | 7 | 3 | D005-D007 | 1 | 0 | 0 | 0
WF7_3259 | D005 | NO | 0.038073 |  | Non Productive | Non-Treed |  | 7 | 3 | D005-D007 | 1 | 0 | 0 | 0
WF7_3252 | D005 | YES | 0.044357 |  | Retention | Retention |  | 7 | 3 | D005-D007 | 1 | 0 | 0 | 8
WF7_3257 | D005 | YES | 0.40222 |  | Retention | Retention |  | 7 | 3 | D005-D007 | 1 | 0 | 0 | 8
WF7_3261 | D005 | NO | 0.22573 |  | Retention | Retention |  | 7 | 3 | D005-D007 | 1 | 0 | 0 | 8
WF7_3263 | D006 | NO | 0.31932 |  | Non-Merch Disposal | Mulch |  | 7 | 3 | D005-D007 | 1 | 0 | 0 | 0
WF7_3273 | D006 | NO | 0.046389 |  | Harvest Disposal | Mulch |  | 7 | 3 | D005-D007 | 1 | 0 | 0 | 0
WF7_3278 | D006 | NO | 1.8431 |  | Harvest Disposal | Mulch |  | 7 | 3 | D005-D007 | 1 | 0 | 0 | 0
WF7_3277 | D006 | NO | 0.1295 |  | Retention | Retention |  | 7 | 3 | D005-D007 | 1 | 0 | 0 | 8
WF7_3288 | D006 | NO | 0.066637 |  | Retention | Retention |  | 7 | 3 | D005-D007 | 1 | 0 | 0 | 8
WF7_3278 | D007 | NO | 2.2746 |  | Harvest Disposal | Mulch |  | 7 | 4 | D007-D009 | 1 | 0 | 0 | 0
WF7_3335 | D007 | NO | 0.45876 |  | Non Productive | Non-Treed |  | 7 | 4 | D007-D009 | 1 | 0 | 0 | 0
WF7_3336 | D007 | NO | 0.59486 |  | Retention | Retention |  | 7 | 4 | D007-D009 | 1 | 0 | 0 | 8
WF7_3343 | D008 | NO | 0.27328 |  | Harvest Disposal | Mulch |  | 7 | 4 | D007-D009 | 1 | 0 | 0 | 0
WF7_3278 | D008 | NO | 1.2785 |  | Harvest Disposal | Mulch |  | 7 | 4 | D007-D009 | 1 | 0 | 0 | 0
WF7_3303 | D008 | NO | 0.020756 |  | Harvest Disposal | Mulch | AU1 | 7 | 4 | D007-D009 | 0 | 1 | 0 | 0
WF7_3331 | D008 | NO | 0.41397 |  | Harvest Disposal | Mulch |  | 7 | 4 | D007-D009 | 1 | 0 | 0 | 0
WF7_3334 | D008 | NO | 0.11616 |  | Harvest Disposal | Mulch |  | 7 | 4 | D007-D009 | 1 | 0 | 0 | 0
WF7_3332 | D008 | NO | 0.044431 |  | Non Productive | Non-Treed |  | 7 | 4 | D007-D009 | 1 | 0 | 0 | 0
WF7_3333 | D008 | NO | 0.29159 |  | Non Productive | Non-Treed |  | 7 | 4 | D007-D009 | 1 | 0 | 0 | 0
WF7_3344 | D008 | NO | 0.78034 |  | Retention | Retention |  | 7 | 4 | D007-D009 | 1 | 0 | 0 | 8
WF7_3297 | D009 | YES | 0.1792 |  | Hand Fall / Lop and Scatter | Handfall | AN | 7 | 5 | D009-D011 | 0 | 1 | 0 | 0
WF7_6290 | D009 | YES | 0.046524 |  | Hand Fall / Lop and Scatter | Handfall | AU1 | 7 | 5 | D009-D011 | 0 | 1 | 0 | 0
WF7_3309 | D009 | YES | 0.011045 |  | Hand Fall / Lop and Scatter | Handfall | AN | 7 | 5 | D009-D011 | 0 | 1 | 0 | 0
WF7_3300 | D009 | NO | 0.041697 |  | Harvest Disposal | Mulch | AN | 7 | 5 | D009-D011 | 0 | 1 | 0 | 0
WF7_3304 | D009 | NO | 0.034203 |  | Harvest Processing | Non-Mulch | AN | 7 | 5 | D009-D011 | 0 | 1 | 0 | 0
WF7_3299 | D009 | YES | 0.021816 |  | Hand Fall / Lop and Scatter | Handfall | AU1 | 7 | 5 | D009-D011 | 0 | 1 | 0 | 0
WF7_3322 | D009 | YES | 0.15226 |  | Hand Fall / Lop and Scatter | Handfall |  | 7 | 5 | D009-D011 | 1 | 0 | 0 | 0
WF7_3323 | D009 | YES | 0.029681 |  | Hand Fall / Lop and Scatter | Handfall |  | 7 | 5 | D009-D011 | 1 | 0 | 0 | 0
WF7_3325 | D009 | YES | 0.55089 |  | Hand Fall / Lop and Scatter | Handfall |  | 7 | 5 | D009-D011 | 1 | 0 | 0 | 0
WF7_3327 | D009 | YES | 0.1775 |  | Hand Fall / Lop and Scatter | Handfall |  | 7 | 5 | D009-D011 | 1 | 0 | 0 | 0
WF7_3303 | D009 | NO | 0.032974 |  | Harvest Disposal | Mulch | AU1 | 7 | 5 | D009-D011 | 0 | 1 | 0 | 0
WF7_3329 | D009 | NO | 0.013761 |  | Harvest Disposal | Mulch |  | 7 | 5 | D009-D011 | 1 | 0 | 0 | 0
WF7_3331 | D009 | NO | 0.48319 |  | Harvest Disposal | Mulch |  | 7 | 5 | D009-D011 | 1 | 0 | 0 | 0
WF7_7351 | D009 | NO | 0.02267 |  | Harvest Disposal | Mulch | AU1 | 7 | 5 | D009-D011 | 0 | 1 | 0 | 0
WF7_3301 | D009 | NO | 0.011418 |  | Non Productive | Non-Treed | AU1 | 7 | 5 | D009-D011 | 0 | 1 | 0 | 0
WF7_3324 | D009 | NO | 0.58798 |  | Non Productive | Non-Treed |  | 7 | 5 | D009-D011 | 1 | 0 | 0 | 0
WF7_3326 | D009 | YES | 0.058755 |  | Non Productive | Non-Treed |  | 7 | 5 | D009-D011 | 1 | 0 | 0 | 0
WF7_3328 | D009 | NO | 0.063501 |  | Non Productive | Non-Treed |  | 7 | 5 | D009-D011 | 1 | 0 | 0 | 0
WF7_3330 | D009 | NO | 0.017735 |  | Non Productive | Non-Treed |  | 7 | 5 | D009-D011 | 1 | 0 | 0 | 0
WF7_3338 | D009 | NO | 0.067409 |  | Non Productive | Non-Treed |  | 7 | 5 | D009-D011 | 1 | 0 | 0 | 0
WF7_3340 | D010 | NO | 0.18787 |  | Hand Fall / Lop and Scatter | Handfall | AN | 7 | 5 | D009-D011 | 0 | 1 | 0 | 0
WF7_3342 | D010 | NO | 0.038113 |  | Harvest Processing | Non-Mulch | AN | 7 | 5 | D009-D011 | 0 | 1 | 0 | 0
WF7_3318 | D010 | YES | 0.22758 |  | Hand Fall / Lop and Scatter | Handfall |  | 7 | 5 | D009-D011 | 1 | 0 | 0 | 0
WF7_3320 | D010 | YES | 0.21445 |  | Hand Fall / Lop and Scatter | Handfall |  | 7 | 5 | D009-D011 | 1 | 0 | 0 | 0
WF7_3322 | D010 | YES | 0.018414 |  | Hand Fall / Lop and Scatter | Handfall |  | 7 | 5 | D009-D011 | 1 | 0 | 0 | 0
WF7_3341 | D010 | YES | 0.037262 |  | Hand Fall / Lop and Scatter | Handfall | AN | 7 | 5 | D009-D011 | 0 | 1 | 0 | 0
WF7_3317 | D010 | NO | 0.1902 |  | Harvest Disposal | Mulch |  | 7 | 5 | D009-D011 | 1 | 0 | 0 | 0
WF7_3315 | D010 | NO | 1.2374 |  | Harvest Processing | Non-Mulch |  | 7 | 5 | D009-D011 | 1 | 0 | 0 | 0
WF7_3321 | D010 | NO | 0.14346 |  | Harvest Processing | Non-Mulch |  | 7 | 5 | D009-D011 | 1 | 0 | 0 | 0
WF7_3319 | D010 | NO | 0.14316 |  | Non Productive | Non-Treed |  | 7 | 5 | D009-D011 | 1 | 0 | 0 | 0
WF7_3314 | D011 | NO | 0.12385 |  | Harvest Disposal | Mulch |  | 7 | 6 | D011-D013 | 1 | 0 | 0 | 0
WF7_3315 | D011 | NO | 2.1363 |  | Harvest Processing | Non-Mulch |  | 7 | 6 | D011-D013 | 1 | 0 | 0 | 0
WF7_3313 | D012 | NO | 0.049608 |  | Harvest Disposal | Mulch |  | 7 | 6 | D011-D013 | 1 | 0 | 0 | 0
WF7_3314 | D012 | NO | 1.5133 |  | Harvest Disposal | Mulch |  | 7 | 6 | D011-D013 | 1 | 0 | 0 | 0
WF7_3312 | D012 | NO | 0.67475 |  | Harvest Processing | Non-Mulch |  | 7 | 6 | D011-D013 | 1 | 0 | 0 | 0
WF7_3315 | D012 | NO | 0.048987 |  | Harvest Processing | Non-Mulch |  | 7 | 6 | D011-D013 | 1 | 0 | 0 | 0
WF7_3311 | D013 | NO | 0.72063 |  | Harvest Disposal | Mulch |  | 7 | 7 | D013-D015 | 1 | 0 | 0 | 0
WF7_3313 | D013 | NO | 0.18812 |  | Harvest Disposal | Mulch |  | 7 | 7 | D013-D015 | 1 | 0 | 0 | 0
WF7_3310 | D013 | NO | 0.47753 |  | Harvest Processing | Non-Mulch |  | 7 | 7 | D013-D015 | 1 | 0 | 0 | 0
WF7_3312 | D013 | NO | 0.48046 |  | Harvest Processing | Non-Mulch |  | 7 | 7 | D013-D015 | 1 | 0 | 0 | 0
WF7_3306 | D014 | YES | 0.1399 |  | Hand Fall / Lop and Scatter | Handfall |  | 7 | 7 | D013-D015 | 1 | 0 | 0 | 0
WF7_3308 | D014 | YES | 0.60324 |  | Hand Fall / Lop and Scatter | Handfall |  | 7 | 7 | D013-D015 | 1 | 0 | 0 | 0
WF7_3307 | D014 | NO | 1.2711 |  | Harvest Processing | Non-Mulch |  | 7 | 7 | D013-D015 | 1 | 0 | 0 | 0
WF7_3307 | D014 | NO | 0.010131 |  | Harvest Processing | Non-Mulch |  | 7 | 8 | D015-D017 | 1 | 0 | 0 | 0
WF7_3310 | D014 | NO | 0.26137 |  | Harvest Processing | Non-Mulch |  | 7 | 7 | D013-D015 | 1 | 0 | 0 | 0
WF7_3306 | D015 | YES | 0.012141 |  | Hand Fall / Lop and Scatter | Handfall |  | 7 | 7 | D013-D015 | 1 | 0 | 0 | 0
WF7_3306 | D015 | YES | 0.069951 |  | Hand Fall / Lop and Scatter | Handfall |  | 7 | 8 | D015-D017 | 1 | 0 | 0 | 0
WF7_3339 | D015 | YES | 0.047754 |  | Hand Fall / Lop and Scatter | Handfall |  | 7 | 8 | D015-D017 | 1 | 0 | 0 | 0
WF7_3346 | D015 | NO | 0.22201 |  | Harvest Disposal | Mulch |  | 7 | 8 | D015-D017 | 1 | 0 | 0 | 0
WF7_3307 | D015 | NO | 1.3685 |  | Harvest Processing | Non-Mulch |  | 7 | 8 | D015-D017 | 1 | 0 | 0 | 0
WF7_3346 | D016 | NO | 1.0702 |  | Harvest Disposal | Mulch |  | 7 | 8 | D015-D017 | 1 | 0 | 0 | 0
WF7_3351 | D016 | NO | 0.74447 |  | Harvest Processing | Non-Mulch |  | 7 | 8 | D015-D017 | 1 | 0 | 0 | 0
WF7_3352 | D017 | YES | 0.16355 |  | Hand Fall / Lop and Scatter | Handfall |  | 7 | 9 | D017-D019 | 1 | 0 | 0 | 0
WF7_3356 | D017 | YES | 0.379 |  | Hand Fall / Lop and Scatter | Handfall |  | 7 | 9 | D017-D019 | 1 | 0 | 0 | 0
WF7_3358 | D017 | YES | 0.20448 |  | Hand Fall / Lop and Scatter | Handfall |  | 7 | 9 | D017-D019 | 1 | 0 | 0 | 0
WF7_3359 | D017 | NO | 0.66055 |  | Harvest Processing | Non-Mulch |  | 7 | 9 | D017-D019 | 1 | 0 | 0 | 0
WF7_3361 | D017 | YES | 0.43021 |  | Hand Fall / Lop and Scatter | Handfall |  | 7 | 9 | D017-D019 | 1 | 0 | 0 | 0
WF7_3351 | D017 | NO | 0.15427 |  | Harvest Processing | Non-Mulch |  | 7 | 9 | D017-D019 | 1 | 0 | 0 | 0
WF7_3362 | D017 | NO | 0.47973 |  | Harvest Processing | Non-Mulch |  | 7 | 9 | D017-D019 | 1 | 0 | 0 | 0
WF7_3357 | D017 | NO | 0.43698 |  | Non Productive | Non-Treed |  | 7 | 9 | D017-D019 | 1 | 0 | 0 | 0
WF7_3376 | D018 | YES | 0.069121 |  | Hand Fall / Lop and Scatter | Handfall |  | 7 | 9 | D017-D019 | 1 | 0 | 0 | 0
WF7_3362 | D018 | NO | 1.7834 |  | Harvest Processing | Non-Mulch |  | 7 | 9 | D017-D019 | 1 | 0 | 0 | 0
WF7_3387 | D019 | YES | 0.06869 |  | Hand Fall / Lop and Scatter | Handfall |  | 7 | 10 | D019-D021 | 1 | 0 | 0 | 0
WF7_3376 | D019 | YES | 0.39 |  | Hand Fall / Lop and Scatter | Handfall |  | 7 | 10 | D019-D021 | 1 | 0 | 0 | 0
WF7_3384 | D019 | YES | 0.27113 |  | Hand Fall / Lop and Scatter | Handfall |  | 7 | 10 | D019-D021 | 1 | 0 | 0 | 0
WF7_3379 | D019 | NO | 0.82082 |  | Harvest Disposal | Mulch |  | 7 | 10 | D019-D021 | 1 | 0 | 0 | 0
WF7_3383 | D019 | NO | 0.26456 |  | Harvest Disposal | Mulch | AN | 7 | 10 | D019-D021 | 0 | 1 | 0 | 0
WF7_3383 | D019 | NO | 0.21773 |  | Harvest Disposal | Mulch | AN | 7 | 11 | D019-D021 | 0 | 1 | 0 | 0
WF7_3446 | D019 | NO | 0.35981 |  | Harvest Disposal | Mulch | AN | 7 | 11 | D019-D021 | 0 | 1 | 0 | 0
WF7_3477 | D019 | NO | 0.079373 |  | Harvest Disposal | Mulch | AU2 | 7 | 11 | D019-D021 | 0 | 1 | 0 | 0
WF7_3362 | D019 | NO | 0.26256 |  | Harvest Processing | Non-Mulch |  | 7 | 10 | D019-D021 | 1 | 0 | 0 | 0
WF7_3386 | D019 | NO | 0.069076 |  | Harvest Processing | Non-Mulch |  | 7 | 10 | D019-D021 | 1 | 0 | 0 | 0
WF7_3389 | D019 | NO | 0.35206 |  | Harvest Processing | Non-Mulch |  | 7 | 10 | D019-D021 | 1 | 0 | 0 | 0
WF7_3399 | D019 | NO | 0.3394 |  | Harvest Processing | Non-Mulch | AN | 7 | 11 | D019-D021 | 0 | 1 | 0 | 0
WF7_3504 | D019 | NO | 0.14296 |  | Harvest Processing | Non-Mulch | AU2 | 7 | 11 | D019-D021 | 0 | 1 | 0 | 0
WF7_7354 | D019 | NO | 0.081421 |  | Harvest Disposal | Mulch | AU2 | 7 | 11 | D019-D021 | 0 | 1 | 0 | 0
WF7_7405 | D019 | NO | 0.1427 |  | Harvest Processing | Non-Mulch | AU2 | 7 | 11 | D019-D021 | 0 | 1 | 0 | 0
WF7_3392 | D020 | YES | 0.33644 |  | Hand Fall / Lop and Scatter | Handfall |  | 7 | 10 | D019-D021 | 1 | 0 | 0 | 0
WF7_3397 | D020 | NO | 0.43296 |  | Harvest Disposal | Mulch |  | 7 | 10 | D019-D021 | 1 | 0 | 0 | 0
WF7_3389 | D020 | NO | 1.1281 |  | Harvest Processing | Non-Mulch |  | 7 | 10 | D019-D021 | 1 | 0 | 0 | 0
WF7_7335 | D021 |  | 0.010345 |  | Harvest Disposal | Mulch |  | 7 | 12 | D021-D023 | 0 | 1 | 0 | 0
WF7_7336 | D021 |  | 0.11933 |  | Harvest Disposal | Mulch |  | 7 | 12 | D021-D023 | 0 | 1 | 0 | 0
WF7_3397 | D021 | NO | 1.8592 |  | Harvest Disposal | Mulch |  | 7 | 12 | D021-D023 | 1 | 0 | 0 | 0
WF7_3405 | D022 | NO |  |  | Harvest Disposal | Mulch | AN | 7 | 12 | D021-D023 | 0 | 0 | 1 | 0
WF7_3438 | D022 | NO | 0.019552 |  | Harvest Disposal | Mulch | AN | 7 | 12 | D021-D023 | 0 | 0 | 1 | 0
WF7_3461 | D022 | NO | 0.064955 |  | Harvest Disposal | Mulch | AN | 7 | 12 | D021-D023 | 0 | 0 | 1 | 0
WF7_3418 | D022 | NO | 0.47244 |  | Harvest Processing | Non-Mulch | AN | 7 | 12 | D021-D023 | 0 | 0 | 1 | 0
WF7_3443 | D022 | NO |  |  | Harvest Processing | Non-Mulch | AN | 7 | 12 | D021-D023 | 0 | 0 | 1 | 0
WF7_3397 | D022 | NO | 0.41637 |  | Harvest Disposal | Mulch |  | 7 | 12 | D021-D023 | 1 | 0 | 0 | 0
WF7_3453 | D022 | NO | 0.47634 |  | Harvest Disposal | Mulch |  | 7 | 12 | D021-D023 | 1 | 0 | 0 | 0
WF7_3430 | D022 | NO | 1.1681 |  | Harvest Processing | Non-Mulch |  | 7 | 12 | D021-D023 | 1 | 0 | 1 | 0
WF7_3462 | D022 | NO | 0.11683 |  | Harvest Processing | Non-Mulch |  | 7 | 12 | D021-D023 | 1 | 0 | 0 | 0
WF7_8202 | D022 | NO | 0.084341 |  | Hand Fall / Lop and Scatter | Mulch |  | 7 | 12 | D021-D023 | 1 | 0 | 0 | 0
WF7_3493 | D023 | NO | 0.10803 |  | Hand Fall / Lop and Scatter | Handfall |  | 7 | 13 | D023-D025 | 1 | 0 | 0 | 0
WF7_3453 | D023 | NO | 0.039471 |  | Harvest Disposal | Mulch |  | 7 | 13 | D023-D025 | 1 | 0 | 0 | 0
WF7_3462 | D023 | NO | 1.6491 |  | Harvest Processing | Non-Mulch |  | 7 | 13 | D023-D025 | 1 | 0 | 0 | 0
WF7_3492 | D023 | NO | 0.15343 |  | Non Productive | Non-Treed | AN | 7 | 13 | D023-D025 | 0 | 1 | 0 | 0
WF7_3493 | D024 | NO | 0.90819 |  | Hand Fall / Lop and Scatter | Handfall |  | 7 | 13 | D023-D025 | 1 | 0 | 0 | 0
WF7_3462 | D024 | NO | 0.31829 |  | Harvest Processing | Non-Mulch |  | 7 | 13 | D023-D025 | 1 | 0 | 0 | 0
WF7_3513 | D024 | NO | 0.3877 |  | Harvest Processing | Non-Mulch |  | 7 | 13 | D023-D025 | 1 | 0 | 0 | 0
WF7_3492 | D024 | NO | 0.091003 |  | Non Productive | Non-Treed | AN | 7 | 13 | D023-D025 | 0 | 1 | 0 | 0