Corbiere and Sons Contracting | 6 | 0 | 1296 | 20200123-1 | 53520101 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 0.21716 | DAY | 182.81 | 0 |  |  | 52.9339 | 6.8814 | 59.8153 | 2020-01-23 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Nathan Kyme | Merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43861 |  | 12 | 43869 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting129620200123-1Light Truck - Pick up- After Jan 100.217164752.9339 | Corbiere and Sons Contracting129620200123-1Light Truck - Pick up- After Jan 100.217164752.9339Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 52.9339 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1296 | 20200123-1 | 53520102 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 0.868 | DAY | 182.81 | 0 |  |  | 211.5748 | 27.5047 | 239.0795 | 2020-01-23 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43861 |  | 12 | 43869 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting129620200123-1Light Truck - Pick up- After Jan 100.8679992211.5748 | Corbiere and Sons Contracting129620200123-1Light Truck - Pick up- After Jan 100.8679992211.5748Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 211.5748 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1296 | 20200123-1 | 53520104 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 0.38243 | DAY | 182.81 | 0 |  |  | 93.2178 | 12.1183 | 105.3361 | 2020-01-23 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43861 |  | 12 | 43869 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting129620200123-1Light Truck - Pick up- After Jan 100.38243293.2178 | Corbiere and Sons Contracting129620200123-1Light Truck - Pick up- After Jan 100.38243293.2178Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 93.2178 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1296 | 20200123-1 | 53520107 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 0.081829 | DAY | 182.81 | 0 |  |  | 19.9458 | 2.593 | 22.5388 | 2020-01-23 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Nathan Kyme | Hazard Tree Clearing |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43861 |  | 12 | 43869 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting129620200123-1Light Truck - Pick up- After Jan 100.081828919.9458 | Corbiere and Sons Contracting129620200123-1Light Truck - Pick up- After Jan 100.081828919.9458Inv#007-R01 |  |  | WF1-Hazard Tree Clearing |  |  | 1 | 19.9458 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1296 | 20200123-1 | 53510106 | Access | 0 | Project Manager | 110 | 1.0116 | HR |  |  | 110 | 0 | 111.2718 | 14.4653 | 125.7371 | 2020-01-23 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43861 |  | 12 | 43869 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting129620200123-1Project Manager1.0115618111.2718 | Corbiere and Sons Contracting129620200123-1Project Manager1.0115618111.2718Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 111.2718 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1296 | 20200123-1 | 53510111 | Access | 0 | Project Manager | 110 | 1.169 | HR |  |  | 110 | 0 | 128.5879 | 16.7164 | 145.3043 | 2020-01-23 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43861 |  | 12 | 43869 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting129620200123-1Project Manager1.1689807128.5879 | Corbiere and Sons Contracting129620200123-1Project Manager1.1689807128.5879Inv#007-R01 | [5 empty] | 1 | 128.5879 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1296 | 20200123-1 | 53520101 | Clearing | 0 | Project Manager | 110 | 0.5212 | HR |  |  | 110 | 0 | 57.3315 | 7.4531 | 64.7846 | 2020-01-23 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Nathan Kyme | Merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43861 |  | 12 | 43869 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting129620200123-1Project Manager0.521195357.3315 | Corbiere and Sons Contracting129620200123-1Project Manager0.521195357.3315Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 57.3315 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1296 | 20200123-1 | 53520102 | Clearing | 0 | Project Manager | 110 | 2.0832 | HR |  |  | 110 | 0 | 229.1518 | 29.7897 | 258.9415 | 2020-01-23 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43861 |  | 12 | 43869 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting129620200123-1Project Manager2.0831981229.1518 | Corbiere and Sons Contracting129620200123-1Project Manager2.0831981229.1518Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 229.1518 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1296 | 20200123-1 | 53520104 | Clearing | 0 | Project Manager | 110 | 0.91784 | HR |  |  | 110 | 0 | 100.9621 | 13.1251 | 114.0872 | 2020-01-23 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43861 |  | 12 | 43869 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting129620200123-1Project Manager0.9178369100.9621 | Corbiere and Sons Contracting129620200123-1Project Manager0.9178369100.9621Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 100.9621 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1296 | 20200123-1 | 53520107 | Clearing | 0 | Project Manager | 110 | 0.19639 | HR |  |  | 110 | 0 | 21.6028 | 2.8084 | 24.4112 | 2020-01-23 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Nathan Kyme | Hazard Tree Clearing |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43861 |  | 12 | 43869 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting129620200123-1Project Manager0.196389321.6028 | Corbiere and Sons Contracting129620200123-1Project Manager0.196389321.6028Inv#007-R01 |  |  | WF1-Hazard Tree Clearing |  |  | 1 | 21.6028 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1296 | 20200123-1 | 53510106 | Access | 0 | Superintendent | 105 | 1.0116 | HR |  |  | 105 | 0 | 106.214 | 13.8078 | 120.0218 | 2020-01-23 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43861 |  | 12 | 43869 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting129620200123-1Superintendent1.0115618106.214 | Corbiere and Sons Contracting129620200123-1Superintendent1.0115618106.214Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 106.214 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1296 | 20200123-1 | 53510111 | Access | 0 | Superintendent | 105 | 1.169 | HR |  |  | 105 | 0 | 122.743 | 15.9566 | 138.6996 | 2020-01-23 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43861 |  | 12 | 43869 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting129620200123-1Superintendent1.1689807122.743 | Corbiere and Sons Contracting129620200123-1Superintendent1.1689807122.743Inv#007-R01 | [5 empty] | 1 | 122.743 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1296 | 20200123-1 | 53520101 | Clearing | 0 | Superintendent | 105 | 0.5212 | HR |  |  | 105 | 0 | 54.7255 | 7.1143 | 61.8398 | 2020-01-23 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Nathan Kyme | Merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43861 |  | 12 | 43869 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting129620200123-1Superintendent0.521195354.7255 | Corbiere and Sons Contracting129620200123-1Superintendent0.521195354.7255Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 54.7255 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1296 | 20200123-1 | 53520102 | Clearing | 0 | Superintendent | 105 | 2.0832 | HR |  |  | 105 | 0 | 218.7358 | 28.4357 | 247.1715 | 2020-01-23 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43861 |  | 12 | 43869 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting129620200123-1Superintendent2.0831981218.7358 | Corbiere and Sons Contracting129620200123-1Superintendent2.0831981218.7358Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 218.7358 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1296 | 20200123-1 | 53520104 | Clearing | 0 | Superintendent | 105 | 0.91784 | HR |  |  | 105 | 0 | 96.3729 | 12.5285 | 108.9014 | 2020-01-23 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43861 |  | 12 | 43869 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting129620200123-1Superintendent0.917836996.3729 | Corbiere and Sons Contracting129620200123-1Superintendent0.917836996.3729Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 96.3729 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1296 | 20200123-1 | 53520107 | Clearing | 0 | Superintendent | 105 | 0.19639 | HR |  |  | 105 | 0 | 20.6209 | 2.6807 | 23.3016 | 2020-01-23 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Nathan Kyme | Hazard Tree Clearing |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43861 |  | 12 | 43869 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting129620200123-1Superintendent0.196389320.6209 | Corbiere and Sons Contracting129620200123-1Superintendent0.196389320.6209Inv#007-R01 |  |  | WF1-Hazard Tree Clearing |  |  | 1 | 20.6209 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1296 | 20200123-1 | 53510106 | Access | 0 | Project Coordinator | 80 | 1.0116 | HR |  |  | 80 | 0 | 80.9249 | 10.5202 | 91.4451 | 2020-01-23 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43861 |  | 12 | 43869 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting129620200123-1Project Coordinator1.011561880.9249 | Corbiere and Sons Contracting129620200123-1Project Coordinator1.011561880.9249Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 80.9249 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1296 | 20200123-1 | 53510111 | Access | 0 | Project Coordinator | 80 | 1.169 | HR |  |  | 80 | 0 | 93.5185 | 12.1574 | 105.6759 | 2020-01-23 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43861 |  | 12 | 43869 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting129620200123-1Project Coordinator1.168980793.5185 | Corbiere and Sons Contracting129620200123-1Project Coordinator1.168980793.5185Inv#007-R01 | [5 empty] | 1 | 93.5185 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1296 | 20200123-1 | 53520101 | Clearing | 0 | Project Coordinator | 80 | 0.5212 | HR |  |  | 80 | 0 | 41.6956 | 5.4204 | 47.116 | 2020-01-23 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Nathan Kyme | Merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43861 |  | 12 | 43869 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting129620200123-1Project Coordinator0.521195341.6956 | Corbiere and Sons Contracting129620200123-1Project Coordinator0.521195341.6956Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 41.6956 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1296 | 20200123-1 | 53520102 | Clearing | 0 | Project Coordinator | 80 | 2.0832 | HR |  |  | 80 | 0 | 166.6558 | 21.6653 | 188.3211 | 2020-01-23 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43861 |  | 12 | 43869 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting129620200123-1Project Coordinator2.0831981166.6558 | Corbiere and Sons Contracting129620200123-1Project Coordinator2.0831981166.6558Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 166.6558 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1296 | 20200123-1 | 53520104 | Clearing | 0 | Project Coordinator | 80 | 0.91784 | HR |  |  | 80 | 0 | 73.427 | 9.5455 | 82.9725 | 2020-01-23 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43861 |  | 12 | 43869 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting129620200123-1Project Coordinator0.917836973.427 | Corbiere and Sons Contracting129620200123-1Project Coordinator0.917836973.427Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 73.427 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1296 | 20200123-1 | 53520107 | Clearing | 0 | Project Coordinator | 80 | 0.19639 | HR |  |  | 80 | 0 | 15.7111 | 2.0424 | 17.7535 | 2020-01-23 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Nathan Kyme | Hazard Tree Clearing |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43861 |  | 12 | 43869 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting129620200123-1Project Coordinator0.196389315.7111 | Corbiere and Sons Contracting129620200123-1Project Coordinator0.196389315.7111Inv#007-R01 |  |  | WF1-Hazard Tree Clearing |  |  | 1 | 15.7111 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1296 | 20200123-1 | 53510106 | Access | 0 | Safety Advisor | 85 | 1.0116 | HR |  |  | 85 | 0 | 85.9828 | 11.1778 | 97.1606 | 2020-01-23 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43861 |  | 12 | 43869 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting129620200123-1Safety Advisor1.011561885.9828 | Corbiere and Sons Contracting129620200123-1Safety Advisor1.011561885.9828Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 85.9828 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1296 | 20200123-1 | 53510111 | Access | 0 | Safety Advisor | 85 | 1.169 | HR |  |  | 85 | 0 | 99.3634 | 12.9172 | 112.2806 | 2020-01-23 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43861 |  | 12 | 43869 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting129620200123-1Safety Advisor1.168980799.3634 | Corbiere and Sons Contracting129620200123-1Safety Advisor1.168980799.3634Inv#007-R01 | [5 empty] | 1 | 99.3634 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1296 | 20200123-1 | 53520101 | Clearing | 0 | Safety Advisor | 85 | 0.5212 | HR |  |  | 85 | 0 | 44.3016 | 5.7592 | 50.0608 | 2020-01-23 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Nathan Kyme | Merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43861 |  | 12 | 43869 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting129620200123-1Safety Advisor0.521195344.3016 | Corbiere and Sons Contracting129620200123-1Safety Advisor0.521195344.3016Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 44.3016 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1296 | 20200123-1 | 53520102 | Clearing | 0 | Safety Advisor | 85 | 2.0832 | HR |  |  | 85 | 0 | 177.0718 | 23.0193 | 200.0911 | 2020-01-23 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43861 |  | 12 | 43869 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting129620200123-1Safety Advisor2.0831981177.0718 | Corbiere and Sons Contracting129620200123-1Safety Advisor2.0831981177.0718Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 177.0718 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1296 | 20200123-1 | 53520104 | Clearing | 0 | Safety Advisor | 85 | 0.91784 | HR |  |  | 85 | 0 | 78.0161 | 10.1421 | 88.1582 | 2020-01-23 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43861 |  | 12 | 43869 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting129620200123-1Safety Advisor0.917836978.0161 | Corbiere and Sons Contracting129620200123-1Safety Advisor0.917836978.0161Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 78.0161 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1296 | 20200123-1 | 53520107 | Clearing | 0 | Safety Advisor | 85 | 0.19639 | HR |  |  | 85 | 0 | 16.6931 | 2.1701 | 18.8632 | 2020-01-23 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Nathan Kyme | Hazard Tree Clearing |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43861 |  | 12 | 43869 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting129620200123-1Safety Advisor0.196389316.6931 | Corbiere and Sons Contracting129620200123-1Safety Advisor0.196389316.6931Inv#007-R01 |  |  | WF1-Hazard Tree Clearing |  |  | 1 | 16.6931 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1296 | 20200123-1 | 53510106 | Access | 0 | Site Administrator | 50 | 0.84297 | HR |  |  | 50 | 0 | 42.1484 | 5.4793 | 47.6277 | 2020-01-23 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43861 |  | 12 | 43869 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting129620200123-1Site Administrator0.842968142.1484 | Corbiere and Sons Contracting129620200123-1Site Administrator0.842968142.1484Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 42.1484 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1296 | 20200123-1 | 53510111 | Access | 0 | Site Administrator | 50 | 0.97415 | HR |  |  | 50 | 0 | 48.7075 | 6.332 | 55.0395 | 2020-01-23 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43861 |  | 12 | 43869 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting129620200123-1Site Administrator0.974150648.7075 | Corbiere and Sons Contracting129620200123-1Site Administrator0.974150648.7075Inv#007-R01 | [5 empty] | 1 | 48.7075 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1296 | 20200123-1 | 53520101 | Clearing | 0 | Site Administrator | 50 | 0.43433 | HR |  |  | 50 | 0 | 21.7165 | 2.8231 | 24.5396 | 2020-01-23 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Nathan Kyme | Merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43861 |  | 12 | 43869 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting129620200123-1Site Administrator0.434329421.7165 | Corbiere and Sons Contracting129620200123-1Site Administrator0.434329421.7165Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 21.7165 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1296 | 20200123-1 | 53520102 | Clearing | 0 | Site Administrator | 50 | 1.736 | HR |  |  | 50 | 0 | 86.7999 | 11.284 | 98.0839 | 2020-01-23 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43861 |  | 12 | 43869 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting129620200123-1Site Administrator1.735998486.7999 | Corbiere and Sons Contracting129620200123-1Site Administrator1.735998486.7999Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 86.7999 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1296 | 20200123-1 | 53520104 | Clearing | 0 | Site Administrator | 50 | 0.76486 | HR |  |  | 50 | 0 | 38.2432 | 4.9716 | 43.2148 | 2020-01-23 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43861 |  | 12 | 43869 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting129620200123-1Site Administrator0.764864138.2432 | Corbiere and Sons Contracting129620200123-1Site Administrator0.764864138.2432Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 38.2432 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1296 | 20200123-1 | 53520107 | Clearing | 0 | Site Administrator | 50 | 0.16366 | HR |  |  | 50 | 0 | 8.1829 | 1.0638 | 9.2467 | 2020-01-23 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Nathan Kyme | Hazard Tree Clearing |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43861 |  | 12 | 43869 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting129620200123-1Site Administrator0.16365788.1829 | Corbiere and Sons Contracting129620200123-1Site Administrator0.16365788.1829Inv#007-R01 |  |  | WF1-Hazard Tree Clearing |  |  | 1 | 8.1829 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1296 | 20200123-1 | 53510106 | Access | 0 | Project Controls | 70 | 1.0116 | HR |  |  | 70 | 0 | 70.8093 | 9.2052 | 80.0145 | 2020-01-23 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43861 |  | 12 | 43869 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting129620200123-1Project Controls1.011561870.8093 | Corbiere and Sons Contracting129620200123-1Project Controls1.011561870.8093Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 70.8093 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1296 | 20200123-1 | 53510111 | Access | 0 | Project Controls | 70 | 1.169 | HR |  |  | 70 | 0 | 81.8286 | 10.6377 | 92.4663 | 2020-01-23 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43861 |  | 12 | 43869 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting129620200123-1Project Controls1.168980781.8286 | Corbiere and Sons Contracting129620200123-1Project Controls1.168980781.8286Inv#007-R01 | [5 empty] | 1 | 81.8286 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1296 | 20200123-1 | 53520101 | Clearing | 0 | Project Controls | 70 | 0.5212 | HR |  |  | 70 | 0 | 36.4837 | 4.7429 | 41.2266 | 2020-01-23 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Nathan Kyme | Merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43861 |  | 12 | 43869 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting129620200123-1Project Controls0.521195336.4837 | Corbiere and Sons Contracting129620200123-1Project Controls0.521195336.4837Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 36.4837 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1296 | 20200123-1 | 53520102 | Clearing | 0 | Project Controls | 70 | 2.0832 | HR |  |  | 70 | 0 | 145.8239 | 18.9571 | 164.781 | 2020-01-23 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43861 |  | 12 | 43869 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting129620200123-1Project Controls2.0831981145.8239 | Corbiere and Sons Contracting129620200123-1Project Controls2.0831981145.8239Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 145.8239 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1296 | 20200123-1 | 53520104 | Clearing | 0 | Project Controls | 70 | 0.91784 | HR |  |  | 70 | 0 | 64.2486 | 8.3523 | 72.6009 | 2020-01-23 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43861 |  | 12 | 43869 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting129620200123-1Project Controls0.917836964.2486 | Corbiere and Sons Contracting129620200123-1Project Controls0.917836964.2486Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 64.2486 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1296 | 20200123-1 | 53520107 | Clearing | 0 | Project Controls | 70 | 0.19639 | HR |  |  | 70 | 0 | 13.7473 | 1.7871 | 15.5344 | 2020-01-23 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Nathan Kyme | Hazard Tree Clearing |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43861 |  | 12 | 43869 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting129620200123-1Project Controls0.196389313.7473 | Corbiere and Sons Contracting129620200123-1Project Controls0.196389313.7473Inv#007-R01 |  |  | WF1-Hazard Tree Clearing |  |  | 1 | 13.7473 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1296 | 20200123-1 | 53510106 | Access | 0 | L.O.A. | 210 | 0.50578 | DAY |  |  |  | 0 | 106.214 | 13.8078 | 120.0218 | 2020-01-23 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43861 |  | 12 | 43869 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting129620200123-1L.O.A.0.5057809106.214 | Corbiere and Sons Contracting129620200123-1L.O.A.0.5057809106.214Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 106.214 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1296 | 20200123-1 | 53510111 | Access | 0 | L.O.A. | 210 | 0.58449 | DAY |  |  |  | 0 | 122.743 | 15.9566 | 138.6996 | 2020-01-23 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43861 |  | 12 | 43869 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting129620200123-1L.O.A.0.5844904122.743 | Corbiere and Sons Contracting129620200123-1L.O.A.0.5844904122.743Inv#007-R01 | [5 empty] | 1 | 122.743 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1296 | 20200123-1 | 53520101 | Clearing | 0 | L.O.A. | 210 | 0.2606 | DAY |  |  |  | 0 | 54.7255 | 7.1143 | 61.8398 | 2020-01-23 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Nathan Kyme | Merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43861 |  | 12 | 43869 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting129620200123-1L.O.A.0.260597654.7255 | Corbiere and Sons Contracting129620200123-1L.O.A.0.260597654.7255Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 54.7255 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1296 | 20200123-1 | 53520102 | Clearing | 0 | L.O.A. | 210 | 1.0416 | DAY |  |  |  | 0 | 218.7358 | 28.4357 | 247.1715 | 2020-01-23 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43861 |  | 12 | 43869 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting129620200123-1L.O.A.1.041599218.7358 | Corbiere and Sons Contracting129620200123-1L.O.A.1.041599218.7358Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 218.7358 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1296 | 20200123-1 | 53520104 | Clearing | 0 | L.O.A. | 210 | 0.45892 | DAY |  |  |  | 0 | 96.3729 | 12.5285 | 108.9014 | 2020-01-23 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43861 |  | 12 | 43869 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting129620200123-1L.O.A.0.458918496.3729 | Corbiere and Sons Contracting129620200123-1L.O.A.0.458918496.3729Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 96.3729 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1296 | 20200123-1 | 53520107 | Clearing | 0 | L.O.A. | 210 | 0.098195 | DAY |  |  |  | 0 | 20.6209 | 2.6807 | 23.3016 | 2020-01-23 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Nathan Kyme | Hazard Tree Clearing |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43861 |  | 12 | 43869 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting129620200123-1L.O.A.0.098194720.6209 | Corbiere and Sons Contracting129620200123-1L.O.A.0.098194720.6209Inv#007-R01 |  |  | WF1-Hazard Tree Clearing |  |  | 1 | 20.6209 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1286 | 20200123-10 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 6 | Dynamic | 98.61 | 0 |  |  | 788.88 | 102.5544 | 891.4344 | 2020-01-23 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Plowed road from neys main access to tower C228; NEYS ROAD |  |  |  | 0 | 43861 |  | 17 | 43863 | [5 empty] | David Mercer | 06 | Corbiere and Sons Contracting128620200123-10Dozer D6 or equal- After Jan 106788.88 | Corbiere and Sons Contracting128620200123-10Dozer D6 or equal- After Jan 106788.88Inv#007-R01 | [5 empty] | 1 | 788.88 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1286 | 20200123-10 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-01-23 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Plowed road from neys main access to tower C228; NEYS ROAD |  |  |  | 0 | 43861 |  | 17 | 43863 | [5 empty] | David Mercer | 06 | Corbiere and Sons Contracting128620200123-10L.O.A.1210 | Corbiere and Sons Contracting128620200123-10L.O.A.1210Inv#007-R01 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1286 | 20200123-10 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 75 | 0 | 450 | 58.5 | 508.5 | 2020-01-23 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Plowed road from neys main access to tower C228; NEYS ROAD |  |  |  | 0 | 43861 |  | 17 | 43863 | [5 empty] | David Mercer | 06 | Corbiere and Sons Contracting128620200123-10Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting128620200123-10Operator - Principle - After Jan 106450Inv#007-R01 | [5 empty] | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1285 | 20200123-11 | 53520101 | Clearing | 0 | Feller Buncher | 240 | 7 | HR | 180 | 0 |  |  | 1680 | 218.4 | 1898.4 | 2020-01-23 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Nathan Kyme | Merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 2 FBs, 1 SKD finishing up clearing at B009-B010; 1 Mobilized to Lofty Davies to start clearing; FISH HATCHERY. |  |  |  | 0 | 43861 |  | 36 | 43866 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting128520200123-11Feller Buncher71680 | Corbiere and Sons Contracting128520200123-11Feller Buncher71680Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1680 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1285 | 20200123-11 | 53520102 | Clearing | 0 | Feller Buncher | 240 | 4 | HR | 180 | 0 |  |  | 960 | 124.8 | 1084.8 | 2020-01-23 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 2 FBs, 1 SKD finishing up clearing at B009-B010; 1 Mobilized to Lofty Davies to start clearing; FISH HATCHERY. |  |  |  | 0 | 43861 |  | 36 | 43866 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting128520200123-11Feller Buncher4960 | Corbiere and Sons Contracting128520200123-11Feller Buncher4960Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1285 | 20200123-11 | 53520101 | Clearing | 0 | Skidder | 171 | 4 | HR | 128.25 | 0 |  |  | 684 | 88.92 | 772.92 | 2020-01-23 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Nathan Kyme | Merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 2 FBs, 1 SKD finishing up clearing at B009-B010; 1 Mobilized to Lofty Davies to start clearing; FISH HATCHERY. |  |  |  | 0 | 43861 |  | 36 | 43866 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting128520200123-11Skidder 4684 | Corbiere and Sons Contracting128520200123-11Skidder 4684Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 684 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1285 | 20200123-11 | 53520102 | Clearing | 0 | Skidder | 171 | 5 | HR | 128.25 | 0 |  |  | 855 | 111.15 | 966.15 | 2020-01-23 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 2 FBs, 1 SKD finishing up clearing at B009-B010; 1 Mobilized to Lofty Davies to start clearing; FISH HATCHERY. |  |  |  | 0 | 43861 |  | 36 | 43866 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting128520200123-11Skidder 5855 | Corbiere and Sons Contracting128520200123-11Skidder 5855Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 855 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1285 | 20200123-11 | 53520101 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2020-01-23 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Nathan Kyme | Merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 2 FBs, 1 SKD finishing up clearing at B009-B010; 1 Mobilized to Lofty Davies to start clearing; FISH HATCHERY. |  |  |  | 0 | 43861 |  | 36 | 43866 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting128520200123-11Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting128520200123-11Light Truck - Pick up- After Jan 103731.25Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 731.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1285 | 20200123-11 | 53520107 | Clearing | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 9 | Dynamic | 91.79 | 0 |  |  | 1101.51 | 143.1963 | 1244.7063 | 2020-01-23 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Nathan Kyme | Hazard Tree Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 2 FBs, 1 SKD finishing up clearing at B009-B010; 1 Mobilized to Lofty Davies to start clearing; FISH HATCHERY. |  |  |  | 0 | 43861 |  | 36 | 43866 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting128520200123-11Tractor Trailer - 60 Ton- After Jan 1091101.51 | Corbiere and Sons Contracting128520200123-11Tractor Trailer - 60 Ton- After Jan 1091101.51Inv#007-R01 |  |  | WF1-Hazard Tree Clearing |  |  | 1 | 1101.51 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1285 | 20200123-11 | 53520101 | Clearing | 0 | Foreman | 95 | 6 | HR |  |  | 95 | 0 | 570 | 74.1 | 644.1 | 2020-01-23 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Nathan Kyme | Merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 2 FBs, 1 SKD finishing up clearing at B009-B010; 1 Mobilized to Lofty Davies to start clearing; FISH HATCHERY. |  |  |  | 0 | 43861 |  | 36 | 43866 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting128520200123-11Foreman6570 | Corbiere and Sons Contracting128520200123-11Foreman6570Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 570 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1285 | 20200123-11 | 53520102 | Clearing | 0 | Foreman | 95 | 6 | HR |  |  | 95 | 0 | 570 | 74.1 | 644.1 | 2020-01-23 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 2 FBs, 1 SKD finishing up clearing at B009-B010; 1 Mobilized to Lofty Davies to start clearing; FISH HATCHERY. |  |  |  | 0 | 43861 |  | 36 | 43866 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting128520200123-11Foreman6570 | Corbiere and Sons Contracting128520200123-11Foreman6570Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 570 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1285 | 20200123-11 | 53520101 | Clearing | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2020-01-23 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Nathan Kyme | Merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 2 FBs, 1 SKD finishing up clearing at B009-B010; 1 Mobilized to Lofty Davies to start clearing; FISH HATCHERY. |  |  |  | 0 | 43861 |  | 36 | 43866 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting128520200123-11L.O.A.4840 | Corbiere and Sons Contracting128520200123-11L.O.A.4840Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1285 | 20200123-11 | 53520107 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-01-23 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Nathan Kyme | Hazard Tree Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 2 FBs, 1 SKD finishing up clearing at B009-B010; 1 Mobilized to Lofty Davies to start clearing; FISH HATCHERY. |  |  |  | 0 | 43861 |  | 36 | 43866 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting128520200123-11L.O.A.1210 | Corbiere and Sons Contracting128520200123-11L.O.A.1210Inv#007-R01 |  |  | WF1-Hazard Tree Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1285 | 20200123-11 | 53520101 | Clearing | 0 | Operator - Principle - After Jan 10 | 75 | 15 | HR |  |  | 75 | 0 | 1125 | 146.25 | 1271.25 | 2020-01-23 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Nathan Kyme | Merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 2 FBs, 1 SKD finishing up clearing at B009-B010; 1 Mobilized to Lofty Davies to start clearing; FISH HATCHERY. |  |  |  | 0 | 43861 |  | 36 | 43866 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting128520200123-11Operator - Principle - After Jan 10151125 | Corbiere and Sons Contracting128520200123-11Operator - Principle - After Jan 10151125Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1125 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1285 | 20200123-11 | 53520102 | Clearing | 0 | Operator - Principle - After Jan 10 | 75 | 10 | HR |  |  | 75 | 0 | 750 | 97.5 | 847.5 | 2020-01-23 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 2 FBs, 1 SKD finishing up clearing at B009-B010; 1 Mobilized to Lofty Davies to start clearing; FISH HATCHERY. |  |  |  | 0 | 43861 |  | 36 | 43866 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting128520200123-11Operator - Principle - After Jan 1010750 | Corbiere and Sons Contracting128520200123-11Operator - Principle - After Jan 1010750Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 750 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1285 | 20200123-11 | 53520107 | Clearing | 0 | Driver - AZ - After Jan 10 | 70 | 9 | HR |  |  | 70 | 0 | 630 | 81.9 | 711.9 | 2020-01-23 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Nathan Kyme | Hazard Tree Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 2 FBs, 1 SKD finishing up clearing at B009-B010; 1 Mobilized to Lofty Davies to start clearing; FISH HATCHERY. |  |  |  | 0 | 43861 |  | 36 | 43866 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting128520200123-11Driver - AZ - After Jan 109630 | Corbiere and Sons Contracting128520200123-11Driver - AZ - After Jan 109630Inv#007-R01 |  |  | WF1-Hazard Tree Clearing |  |  | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1284 | 20200123-12 | 53510111 | Access | 0 | Sander Truck - Forestry- After Jan 10 | 86.38 | 2 | Dynamic | 64.79 | 0 |  |  | 172.76 | 22.4588 | 195.2188 | 2020-01-23 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 1 Load of sand delivered to lofty davies b054-b064 |  |  |  | 0 | 43861 |  | 36 | 43866 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting128420200123-12Sander Truck - Forestry- After Jan 102172.76 | Corbiere and Sons Contracting128420200123-12Sander Truck - Forestry- After Jan 102172.76Inv#007-R01 | [5 empty] | 1 | 172.76 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1284 | 20200123-12 | 53510111 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-01-23 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 1 Load of sand delivered to lofty davies b054-b064 |  |  |  | 0 | 43861 |  | 36 | 43866 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting128420200123-12L.O.A.1210 | Corbiere and Sons Contracting128420200123-12L.O.A.1210Inv#007-R01 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1284 | 20200123-12 | 53510111 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 2 | HR |  |  | 70 | 0 | 140 | 18.2 | 158.2 | 2020-01-23 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 1 Load of sand delivered to lofty davies b054-b064 |  |  |  | 0 | 43861 |  | 36 | 43866 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting128420200123-12Driver - AZ - After Jan 102140 | Corbiere and Sons Contracting128420200123-12Driver - AZ - After Jan 102140Inv#007-R01 | [5 empty] | 1 | 140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1385 | 20200123-15-R1 | 53510611 | Access | 0 | Loader JD 524 to 624 or equal | 99 | 1.5043 | HR | 74.25 | 0 |  |  | 148.9264 | 19.3604 | 168.2868 | 2020-01-23 | 1 | Inv#009 | 43894 | 86 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 26 | Approved | ROW INTERNAL - Corbiere Yard Maintenance LEM's Terrace Bay | 9025 | Yard Maintenance | 6 |  | Schreiber Yard | 1 | 43868 |  | 40 | 43869 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting138520200123-15-R1Loader JD 524 to 624 or equal1.5043073148.9264 | Corbiere and Sons Contracting138520200123-15-R1Loader JD 524 to 624 or equal1.5043073148.9264Inv#009 | [5 empty] | 1 | 148.9264 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1385 | 20200123-15-R1 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 0.30086 | DAY | 182.81 | 0 |  |  | 73.335 | 9.5335 | 82.8685 | 2020-01-23 | 1 | Inv#009 | 43894 | 86 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 26 | Approved | ROW INTERNAL - Corbiere Yard Maintenance LEM's Terrace Bay | 9025 | Yard Maintenance | 6 |  | Schreiber Yard | 1 | 43868 |  | 40 | 43869 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting138520200123-15-R1Light Truck - Pick up- After Jan 100.300861573.335 | Corbiere and Sons Contracting138520200123-15-R1Light Truck - Pick up- After Jan 100.300861573.335Inv#009 | [5 empty] | 1 | 73.335 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1385 | 20200123-15-R1 | 53510611 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 3.0086 | Dynamic | 91.79 | 0 |  |  | 368.2244 | 47.8692 | 416.0936 | 2020-01-23 | 1 | Inv#009 | 43894 | 86 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 26 | Approved | ROW INTERNAL - Corbiere Yard Maintenance LEM's Terrace Bay | 9025 | Yard Maintenance | 6 |  | Schreiber Yard | 1 | 43868 |  | 40 | 43869 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting138520200123-15-R1Tractor Trailer - 60 Ton- After Jan 103.0086147368.2244 | Corbiere and Sons Contracting138520200123-15-R1Tractor Trailer - 60 Ton- After Jan 103.0086147368.2244Inv#009 | [5 empty] | 1 | 368.2244 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1385 | 20200123-15-R1 | 53510611 | Access | 0 | L.O.A. | 210 | 0.60172 | DAY |  |  |  | 0 | 126.3618 | 16.427 | 142.7888 | 2020-01-23 | 1 | Inv#009 | 43894 | 86 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 26 | Approved | ROW INTERNAL - Corbiere Yard Maintenance LEM's Terrace Bay | 9025 | Yard Maintenance | 6 |  | Schreiber Yard | 1 | 43868 |  | 40 | 43869 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting138520200123-15-R1L.O.A.0.6017229126.3618 | Corbiere and Sons Contracting138520200123-15-R1L.O.A.0.6017229126.3618Inv#009 | [5 empty] | 1 | 126.3618 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1385 | 20200123-15-R1 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 3.3095 | HR |  |  | 70 | 0 | 231.6633 | 30.1162 | 261.7795 | 2020-01-23 | 1 | Inv#009 | 43894 | 86 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 26 | Approved | ROW INTERNAL - Corbiere Yard Maintenance LEM's Terrace Bay | 9025 | Yard Maintenance | 6 |  | Schreiber Yard | 1 | 43868 |  | 40 | 43869 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting138520200123-15-R1Operator - Intermdiate - After Jan 103.3094762231.6633 | Corbiere and Sons Contracting138520200123-15-R1Operator - Intermdiate - After Jan 103.3094762231.6633Inv#009 | [5 empty] | 1 | 231.6633 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1385 | 20200123-15-R1 | 53510611 | Access | 0 | Labourer - General - After Jan 10 | 60 | 3.3095 | HR |  |  | 60 | 0 | 198.5686 | 25.8139 | 224.3825 | 2020-01-23 | 1 | Inv#009 | 43894 | 86 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 26 | Approved | ROW INTERNAL - Corbiere Yard Maintenance LEM's Terrace Bay | 9025 | Yard Maintenance | 6 |  | Schreiber Yard | 1 | 43868 |  | 40 | 43869 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting138520200123-15-R1Labourer - General - After Jan 103.3094762198.5686 | Corbiere and Sons Contracting138520200123-15-R1Labourer - General - After Jan 103.3094762198.5686Inv#009 | [5 empty] | 1 | 198.5686 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1313 | 20200123-17 | 53510611 | Access | 0 | Loader JD 524 to 624 or equal | 99 | 5 | HR | 74.25 | 0 |  |  | 495 | 64.35 | 559.35 | 2020-01-23 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Clearing snow; | 0 |  | Lake A | 0 | 43864 |  | 40 | 43890 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting131320200123-17Loader JD 524 to 624 or equal5495 | Corbiere and Sons Contracting131320200123-17Loader JD 524 to 624 or equal5495Inv#009 | [5 empty] | 1 | 495 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1313 | 20200123-17 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 6 | Dynamic | 98.61 | 0 |  |  | 788.88 | 102.5544 | 891.4344 | 2020-01-23 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Clearing snow; | 0 |  | Lake A | 0 | 43864 |  | 40 | 43890 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting131320200123-17Dozer D6 or equal- After Jan 106788.88 | Corbiere and Sons Contracting131320200123-17Dozer D6 or equal- After Jan 106788.88Inv#009 | [5 empty] | 1 | 788.88 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1313 | 20200123-17 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-01-23 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Clearing snow; | 0 |  | Lake A | 0 | 43864 |  | 40 | 43890 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting131320200123-17Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting131320200123-17Light Truck - Pick up- After Jan 101243.75Inv#009 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1313 | 20200123-17 | 53510611 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-01-23 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Clearing snow; | 0 |  | Lake A | 0 | 43864 |  | 40 | 43890 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting131320200123-17L.O.A.2420 | Corbiere and Sons Contracting131320200123-17L.O.A.2420Inv#009 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1313 | 20200123-17 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 13 | HR |  |  | 70 | 0 | 910 | 118.3 | 1028.3 | 2020-01-23 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Clearing snow; | 0 |  | Lake A | 0 | 43864 |  | 40 | 43890 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting131320200123-17Operator - Intermdiate - After Jan 1013910 | Corbiere and Sons Contracting131320200123-17Operator - Intermdiate - After Jan 1013910Inv#009 | [5 empty] | 1 | 910 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1386 | 20200123-18 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 0.74838 | DAY | 182.81 | 0 |  |  | 182.4187 | 23.7144 | 206.1331 | 2020-01-21 | 1 | Inv#009 | 43894 | 86 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 25 | Approved | INTERNAL Supervision for Terrace Bay Yard | 9024 | Project Supervision | 6 |  | Schrieber Yard Supervision | 1 | 43868 |  | 40 | 43869 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting138620200123-18Light Truck - Pick up- After Jan 100.7483843182.4187 | Corbiere and Sons Contracting138620200123-18Light Truck - Pick up- After Jan 100.7483843182.4187Inv#009 | [5 empty] | 1 | 182.4187 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1386 | 20200123-18 | 53510611 | Access | 0 | Project Coordinator | 80 | 4.4903 | HR |  |  | 80 | 0 | 359.2245 | 46.6992 | 405.9237 | 2020-01-21 | 1 | Inv#009 | 43894 | 86 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 25 | Approved | INTERNAL Supervision for Terrace Bay Yard | 9024 | Project Supervision | 6 |  | Schrieber Yard Supervision | 1 | 43868 |  | 40 | 43869 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting138620200123-18Project Coordinator4.490306359.2245 | Corbiere and Sons Contracting138620200123-18Project Coordinator4.490306359.2245Inv#009 | [5 empty] | 1 | 359.2245 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1386 | 20200123-18 | 53510611 | Access | 0 | Foreman | 95 | 4.4903 | HR |  |  | 95 | 0 | 426.5791 | 55.4553 | 482.0344 | 2020-01-21 | 1 | Inv#009 | 43894 | 86 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 25 | Approved | INTERNAL Supervision for Terrace Bay Yard | 9024 | Project Supervision | 6 |  | Schrieber Yard Supervision | 1 | 43868 |  | 40 | 43869 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting138620200123-18Foreman4.490306426.5791 | Corbiere and Sons Contracting138620200123-18Foreman4.490306426.5791Inv#009 | [5 empty] | 1 | 426.5791 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1386 | 20200123-18 | 53510611 | Access | 0 | L.O.A. | 210 | 0.74838 | DAY |  |  |  | 0 | 157.1607 | 20.4309 | 177.5916 | 2020-01-21 | 1 | Inv#009 | 43894 | 86 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 25 | Approved | INTERNAL Supervision for Terrace Bay Yard | 9024 | Project Supervision | 6 |  | Schrieber Yard Supervision | 1 | 43868 |  | 40 | 43869 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting138620200123-18L.O.A.0.7483843157.1607 | Corbiere and Sons Contracting138620200123-18L.O.A.0.7483843157.1607Inv#009 | [5 empty] | 1 | 157.1607 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1295 | 20200123-2 | 53510106 | Access | 0 | Loader JD 524 to 624 or equal | 99 | 0.42148 | HR | 74.25 | 0 |  |  | 41.7269 | 5.4245 | 47.1514 | 2020-01-23 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General yard maintenace | 1 |  |  | 1 | 43861 |  | 36 | 43866 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting129520200123-2Loader JD 524 to 624 or equal0.421484141.7269 | Corbiere and Sons Contracting129520200123-2Loader JD 524 to 624 or equal0.421484141.7269Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 41.7269 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1295 | 20200123-2 | 53510111 | Access | 0 | Loader JD 524 to 624 or equal | 99 | 0.48708 | HR | 74.25 | 0 |  |  | 48.2205 | 6.2687 | 54.4892 | 2020-01-23 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General yard maintenace | 1 |  |  | 1 | 43861 |  | 36 | 43866 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting129520200123-2Loader JD 524 to 624 or equal0.487075348.2205 | Corbiere and Sons Contracting129520200123-2Loader JD 524 to 624 or equal0.487075348.2205Inv#007-R01 | [5 empty] | 1 | 48.2205 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1295 | 20200123-2 | 53520101 | Clearing | 0 | Loader JD 524 to 624 or equal | 99 | 0.21716 | HR | 74.25 | 0 |  |  | 21.4993 | 2.7949 | 24.2942 | 2020-01-23 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Nathan Kyme | Merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General yard maintenace | 1 |  |  | 1 | 43861 |  | 36 | 43866 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting129520200123-2Loader JD 524 to 624 or equal0.217164721.4993 | Corbiere and Sons Contracting129520200123-2Loader JD 524 to 624 or equal0.217164721.4993Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 21.4993 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1295 | 20200123-2 | 53520102 | Clearing | 0 | Loader JD 524 to 624 or equal | 99 | 0.868 | HR | 74.25 | 0 |  |  | 85.9319 | 11.1711 | 97.103 | 2020-01-23 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General yard maintenace | 1 |  |  | 1 | 43861 |  | 36 | 43866 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting129520200123-2Loader JD 524 to 624 or equal0.867999285.9319 | Corbiere and Sons Contracting129520200123-2Loader JD 524 to 624 or equal0.867999285.9319Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 85.9319 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1295 | 20200123-2 | 53520104 | Clearing | 0 | Loader JD 524 to 624 or equal | 99 | 0.38243 | HR | 74.25 | 0 |  |  | 37.8608 | 4.9219 | 42.7827 | 2020-01-23 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General yard maintenace | 1 |  |  | 1 | 43861 |  | 36 | 43866 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting129520200123-2Loader JD 524 to 624 or equal0.38243237.8608 | Corbiere and Sons Contracting129520200123-2Loader JD 524 to 624 or equal0.38243237.8608Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 37.8608 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1295 | 20200123-2 | 53520107 | Clearing | 0 | Loader JD 524 to 624 or equal | 99 | 0.081829 | HR | 74.25 | 0 |  |  | 8.1011 | 1.0531 | 9.1542 | 2020-01-23 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Nathan Kyme | Hazard Tree Clearing |  | VC7556-2019-017 | 929 OF |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General yard maintenace | 1 |  |  | 1 | 43861 |  | 36 | 43866 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting129520200123-2Loader JD 524 to 624 or equal0.08182898.1011 | Corbiere and Sons Contracting129520200123-2Loader JD 524 to 624 or equal0.08182898.1011Inv#007-R01 |  |  | WF1-Hazard Tree Clearing |  |  | 1 | 8.1011 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1295 | 20200123-2 | 53510106 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 0.084297 | DAY | 182.81 | 0 |  |  | 20.5473 | 2.6711 | 23.2184 | 2020-01-23 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General yard maintenace | 1 |  |  | 1 | 43861 |  | 36 | 43866 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting129520200123-2Light Truck - Pick up- After Jan 100.084296820.5473 | Corbiere and Sons Contracting129520200123-2Light Truck - Pick up- After Jan 100.084296820.5473Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 20.5473 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1295 | 20200123-2 | 53510111 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 0.097415 | DAY | 182.81 | 0 |  |  | 23.7449 | 3.0868 | 26.8317 | 2020-01-23 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General yard maintenace | 1 |  |  | 1 | 43861 |  | 36 | 43866 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting129520200123-2Light Truck - Pick up- After Jan 100.097415123.7449 | Corbiere and Sons Contracting129520200123-2Light Truck - Pick up- After Jan 100.097415123.7449Inv#007-R01 | [5 empty] | 1 | 23.7449 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1295 | 20200123-2 | 53520101 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 0.043433 | DAY | 182.81 | 0 |  |  | 10.5868 | 1.3763 | 11.9631 | 2020-01-23 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Nathan Kyme | Merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General yard maintenace | 1 |  |  | 1 | 43861 |  | 36 | 43866 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting129520200123-2Light Truck - Pick up- After Jan 100.043432910.5868 | Corbiere and Sons Contracting129520200123-2Light Truck - Pick up- After Jan 100.043432910.5868Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 10.5868 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1295 | 20200123-2 | 53520102 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 0.1736 | DAY | 182.81 | 0 |  |  | 42.315 | 5.5009 | 47.816 | 2020-01-23 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General yard maintenace | 1 |  |  | 1 | 43861 |  | 36 | 43866 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting129520200123-2Light Truck - Pick up- After Jan 100.173599842.315 | Corbiere and Sons Contracting129520200123-2Light Truck - Pick up- After Jan 100.173599842.315Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 42.315 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1295 | 20200123-2 | 53520104 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 0.076486 | DAY | 182.81 | 0 |  |  | 18.6436 | 2.4237 | 21.0673 | 2020-01-23 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General yard maintenace | 1 |  |  | 1 | 43861 |  | 36 | 43866 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting129520200123-2Light Truck - Pick up- After Jan 100.076486418.6436 | Corbiere and Sons Contracting129520200123-2Light Truck - Pick up- After Jan 100.076486418.6436Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 18.6436 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1295 | 20200123-2 | 53520107 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 0.016366 | DAY | 182.81 | 0 |  |  | 3.9892 | 0.5186 | 4.5078 | 2020-01-23 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Nathan Kyme | Hazard Tree Clearing |  | VC7556-2019-017 | 929 OF |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General yard maintenace | 1 |  |  | 1 | 43861 |  | 36 | 43866 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting129520200123-2Light Truck - Pick up- After Jan 100.01636583.9892 | Corbiere and Sons Contracting129520200123-2Light Truck - Pick up- After Jan 100.01636583.9892Inv#007-R01 |  |  | WF1-Hazard Tree Clearing |  |  | 1 | 3.9892 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1295 | 20200123-2 | 53510106 | Access | 0 | Operator - Apprentice | 60 | 0.84297 | HR |  |  | 60 | 0 | 50.5781 | 6.5752 | 57.1533 | 2020-01-23 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General yard maintenace | 1 |  |  | 1 | 43861 |  | 36 | 43866 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting129520200123-2Operator - Apprentice0.842968150.5781 | Corbiere and Sons Contracting129520200123-2Operator - Apprentice0.842968150.5781Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 50.5781 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1295 | 20200123-2 | 53510111 | Access | 0 | Operator - Apprentice | 60 | 0.97415 | HR |  |  | 60 | 0 | 58.449 | 7.5984 | 66.0474 | 2020-01-23 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General yard maintenace | 1 |  |  | 1 | 43861 |  | 36 | 43866 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting129520200123-2Operator - Apprentice0.974150658.449 | Corbiere and Sons Contracting129520200123-2Operator - Apprentice0.974150658.449Inv#007-R01 | [5 empty] | 1 | 58.449 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1295 | 20200123-2 | 53520101 | Clearing | 0 | Operator - Apprentice | 60 | 0.43433 | HR |  |  | 60 | 0 | 26.0598 | 3.3878 | 29.4476 | 2020-01-23 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Nathan Kyme | Merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General yard maintenace | 1 |  |  | 1 | 43861 |  | 36 | 43866 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting129520200123-2Operator - Apprentice0.434329426.0598 | Corbiere and Sons Contracting129520200123-2Operator - Apprentice0.434329426.0598Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 26.0598 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1295 | 20200123-2 | 53520102 | Clearing | 0 | Operator - Apprentice | 60 | 1.736 | HR |  |  | 60 | 0 | 104.1599 | 13.5408 | 117.7007 | 2020-01-23 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General yard maintenace | 1 |  |  | 1 | 43861 |  | 36 | 43866 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting129520200123-2Operator - Apprentice1.7359984104.1599 | Corbiere and Sons Contracting129520200123-2Operator - Apprentice1.7359984104.1599Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 104.1599 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1295 | 20200123-2 | 53520104 | Clearing | 0 | Operator - Apprentice | 60 | 0.76486 | HR |  |  | 60 | 0 | 45.8918 | 5.9659 | 51.8577 | 2020-01-23 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General yard maintenace | 1 |  |  | 1 | 43861 |  | 36 | 43866 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting129520200123-2Operator - Apprentice0.764864145.8918 | Corbiere and Sons Contracting129520200123-2Operator - Apprentice0.764864145.8918Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 45.8918 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1295 | 20200123-2 | 53520107 | Clearing | 0 | Operator - Apprentice | 60 | 0.16366 | HR |  |  | 60 | 0 | 9.8195 | 1.2765 | 11.096 | 2020-01-23 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Nathan Kyme | Hazard Tree Clearing |  | VC7556-2019-017 | 929 OF |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General yard maintenace | 1 |  |  | 1 | 43861 |  | 36 | 43866 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting129520200123-2Operator - Apprentice0.16365789.8195 | Corbiere and Sons Contracting129520200123-2Operator - Apprentice0.16365789.8195Inv#007-R01 |  |  | WF1-Hazard Tree Clearing |  |  | 1 | 9.8195 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1293 | 20200123-3 | 53520102 | Clearing | 0 | Brusher | 202.5 | 9 | HR | 151.88 | 0 |  |  | 1822.5 | 236.925 | 2059.425 | 2020-01-23 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grinding of Material from A061; Brusher working from A068-A070 | 1 | A-055 to A-084 | Eldorado | 0 | 43861 |  | 36 | 43866 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting129320200123-3Brusher91822.5 | Corbiere and Sons Contracting129320200123-3Brusher91822.5Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1822.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1293 | 20200123-3 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 9 | HR | 417.6 | 0 |  |  | 5011.2 | 651.456 | 5662.656 | 2020-01-23 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grinding of Material from A061; Brusher working from A068-A070 | 1 | A-055 to A-084 | Eldorado | 0 | 43861 |  | 36 | 43866 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting129320200123-3Grinder - 4710 Peterson or equal95011.2 | Corbiere and Sons Contracting129320200123-3Grinder - 4710 Peterson or equal95011.2Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 5011.2 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1293 | 20200123-3 | 53520102 | Clearing | 0 | Log Loader | 153 | 9 | HR | 114.75 | 0 |  |  | 1377 | 179.01 | 1556.01 | 2020-01-23 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grinding of Material from A061; Brusher working from A068-A070 | 1 | A-055 to A-084 | Eldorado | 0 | 43861 |  | 36 | 43866 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting129320200123-3Log Loader91377 | Corbiere and Sons Contracting129320200123-3Log Loader91377Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1377 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1293 | 20200123-3 | 53520102 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2020-01-23 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grinding of Material from A061; Brusher working from A068-A070 | 1 | A-055 to A-084 | Eldorado | 0 | 43861 |  | 36 | 43866 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting129320200123-3Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting129320200123-3Light Truck - Pick up- After Jan 103731.25Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 731.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1293 | 20200123-3 | 53520102 | Clearing | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2020-01-23 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grinding of Material from A061; Brusher working from A068-A070 | 1 | A-055 to A-084 | Eldorado | 0 | 43861 |  | 36 | 43866 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting129320200123-3L.O.A.3630 | Corbiere and Sons Contracting129320200123-3L.O.A.3630Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1293 | 20200123-3 | 53520102 | Clearing | 0 | Operator - Principle - After Jan 10 | 75 | 22 | HR |  |  | 75 | 0 | 1650 | 214.5 | 1864.5 | 2020-01-23 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grinding of Material from A061; Brusher working from A068-A070 | 1 | A-055 to A-084 | Eldorado | 0 | 43861 |  | 36 | 43866 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting129320200123-3Operator - Principle - After Jan 10221650 | Corbiere and Sons Contracting129320200123-3Operator - Principle - After Jan 10221650Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1650 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1293 | 20200123-3 | 53520102 | Clearing | 0 | Labourer - General - After Jan 10 | 60 | 8 | HR |  |  | 60 | 0 | 480 | 62.4 | 542.4 | 2020-01-23 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grinding of Material from A061; Brusher working from A068-A070 | 1 | A-055 to A-084 | Eldorado | 0 | 43861 |  | 36 | 43866 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting129320200123-3Labourer - General - After Jan 108480 | Corbiere and Sons Contracting129320200123-3Labourer - General - After Jan 108480Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 480 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1293 | 20200123-3 | 53520107 | Clearing | 0 | Labourer - General - After Jan 10 | 60 | 3 | HR |  |  | 60 | 0 | 180 | 23.4 | 203.4 | 2020-01-23 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Nathan Kyme | Hazard Tree Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grinding of Material from A061; Brusher working from A068-A070 | 1 | A-055 to A-084 | Eldorado | 0 | 43861 |  | 36 | 43866 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting129320200123-3Labourer - General - After Jan 103180 | Corbiere and Sons Contracting129320200123-3Labourer - General - After Jan 103180Inv#007-R01 |  |  | WF1-Hazard Tree Clearing |  |  | 1 | 180 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1291 | 20200123-5 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 9 | HR | 417.6 | 0 |  |  | 5011.2 | 651.456 | 5662.656 | 2020-01-23 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling from A096; Grinding of Material from A085; | 1 | A-085 to A-117 | Windfarm | 0 | 43861 |  | 36 | 43866 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting129120200123-5Grinder - 4710 Peterson or equal95011.2 | Corbiere and Sons Contracting129120200123-5Grinder - 4710 Peterson or equal95011.2Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 5011.2 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1291 | 20200123-5 | 53520102 | Clearing | 0 | Log Loader | 153 | 9 | HR | 114.75 | 0 |  |  | 1377 | 179.01 | 1556.01 | 2020-01-23 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling from A096; Grinding of Material from A085; | 1 | A-085 to A-117 | Windfarm | 0 | 43861 |  | 36 | 43866 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting129120200123-5Log Loader91377 | Corbiere and Sons Contracting129120200123-5Log Loader91377Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1377 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1291 | 20200123-5 | 53520104 | Clearing | 0 | Chainsaw and consumables- After Jan 10 | 60 | 3 | unit/man/day | 0 | 0 |  |  | 180 | 23.4 | 203.4 | 2020-01-23 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling from A096; Grinding of Material from A085; | 1 | A-085 to A-117 | Windfarm | 0 | 43861 |  | 36 | 43866 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting129120200123-5Chainsaw and consumables- After Jan 103180 | Corbiere and Sons Contracting129120200123-5Chainsaw and consumables- After Jan 103180Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 180 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1291 | 20200123-5 | 53520102 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-01-23 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling from A096; Grinding of Material from A085; | 1 | A-085 to A-117 | Windfarm | 0 | 43861 |  | 36 | 43866 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting129120200123-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting129120200123-5Light Truck - Pick up- After Jan 101243.75Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1291 | 20200123-5 | 53520104 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-01-23 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling from A096; Grinding of Material from A085; | 1 | A-085 to A-117 | Windfarm | 0 | 43861 |  | 36 | 43866 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting129120200123-5Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting129120200123-5Light Truck - Pick up- After Jan 102487.5Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1291 | 20200123-5 | 53520104 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2020-01-23 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling from A096; Grinding of Material from A085; | 1 | A-085 to A-117 | Windfarm | 0 | 43861 |  | 36 | 43866 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting129120200123-5Foreman121140 | Corbiere and Sons Contracting129120200123-5Foreman121140Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1291 | 20200123-5 | 53520102 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-01-23 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling from A096; Grinding of Material from A085; | 1 | A-085 to A-117 | Windfarm | 0 | 43861 |  | 36 | 43866 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting129120200123-5L.O.A.1210 | Corbiere and Sons Contracting129120200123-5L.O.A.1210Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1291 | 20200123-5 | 53520104 | Clearing | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2020-01-23 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling from A096; Grinding of Material from A085; | 1 | A-085 to A-117 | Windfarm | 0 | 43861 |  | 36 | 43866 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting129120200123-5L.O.A.4840 | Corbiere and Sons Contracting129120200123-5L.O.A.4840Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1291 | 20200123-5 | 53520102 | Clearing | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2020-01-23 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling from A096; Grinding of Material from A085; | 1 | A-085 to A-117 | Windfarm | 0 | 43861 |  | 36 | 43866 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting129120200123-5Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting129120200123-5Operator - Principle - After Jan 1011825Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1291 | 20200123-5 | 53520104 | Clearing | 0 | Labourer - Specialized - After Jan 10 | 70 | 33 | HR |  |  | 70 | 0 | 2310 | 300.3 | 2610.3 | 2020-01-23 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling from A096; Grinding of Material from A085; | 1 | A-085 to A-117 | Windfarm | 0 | 43861 |  | 36 | 43866 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting129120200123-5Labourer - Specialized - After Jan 10332310 | Corbiere and Sons Contracting129120200123-5Labourer - Specialized - After Jan 10332310Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 2310 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1290 | 20200123-6 | 53510111 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 5 | Dynamic | 110.22 | 0 |  |  | 734.8 | 95.524 | 830.324 | 2020-01-23 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float Moves; Graders working across access roads; link belt loading sander truck in pit; | 1 | A-085 to A-117 | Windfarm | 0 | 43861 |  | 36 | 43866 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting129020200123-6Excavator - 36 ton- After Jan 105734.8 | Corbiere and Sons Contracting129020200123-6Excavator - 36 ton- After Jan 105734.8Inv#007-R01 | [5 empty] | 1 | 734.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1290 | 20200123-6 | 53510111 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 18 | Dynamic | 95.24 | 0 |  |  | 2285.64 | 297.1332 | 2582.7732 | 2020-01-23 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float Moves; Graders working across access roads; link belt loading sander truck in pit; | 1 | A-085 to A-117 | Windfarm | 0 | 43861 |  | 36 | 43866 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting129020200123-6Grader - Cat 12 to 14 or equal- After Jan 10182285.64 | Corbiere and Sons Contracting129020200123-6Grader - Cat 12 to 14 or equal- After Jan 10182285.64Inv#007-R01 | [5 empty] | 1 | 2285.64 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1290 | 20200123-6 | 53510111 | Access | 0 | Sander Truck - Forestry- After Jan 10 | 86.38 | 9 | Dynamic | 64.79 | 0 |  |  | 777.42 | 101.0646 | 878.4846 | 2020-01-23 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float Moves; Graders working across access roads; link belt loading sander truck in pit; | 1 | A-085 to A-117 | Windfarm | 0 | 43861 |  | 36 | 43866 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting129020200123-6Sander Truck - Forestry- After Jan 109777.42 | Corbiere and Sons Contracting129020200123-6Sander Truck - Forestry- After Jan 109777.42Inv#007-R01 | [5 empty] | 1 | 777.42 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1290 | 20200123-6 | 53510111 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-01-23 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float Moves; Graders working across access roads; link belt loading sander truck in pit; | 1 | A-085 to A-117 | Windfarm | 0 | 43861 |  | 36 | 43866 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting129020200123-6Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting129020200123-6Light Truck - Pick up- After Jan 102487.5Inv#007-R01 | [5 empty] | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1290 | 20200123-6 | 53510111 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 9 | Dynamic | 91.79 | 0 |  |  | 1101.51 | 143.1963 | 1244.7063 | 2020-01-23 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float Moves; Graders working across access roads; link belt loading sander truck in pit; | 1 | A-085 to A-117 | Windfarm | 0 | 43861 |  | 36 | 43866 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting129020200123-6Tractor Trailer - 60 Ton- After Jan 1091101.51 | Corbiere and Sons Contracting129020200123-6Tractor Trailer - 60 Ton- After Jan 1091101.51Inv#007-R01 | [5 empty] | 1 | 1101.51 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1290 | 20200123-6 | 53510111 | Access | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2020-01-23 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float Moves; Graders working across access roads; link belt loading sander truck in pit; | 1 | A-085 to A-117 | Windfarm | 0 | 43861 |  | 36 | 43866 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting129020200123-6L.O.A.51050 | Corbiere and Sons Contracting129020200123-6L.O.A.51050Inv#007-R01 | [5 empty] | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1290 | 20200123-6 | 53510111 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 33 | HR |  |  | 75 | 0 | 2475 | 321.75 | 2796.75 | 2020-01-23 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float Moves; Graders working across access roads; link belt loading sander truck in pit; | 1 | A-085 to A-117 | Windfarm | 0 | 43861 |  | 36 | 43866 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting129020200123-6Operator - Principle - After Jan 10332475 | Corbiere and Sons Contracting129020200123-6Operator - Principle - After Jan 10332475Inv#007-R01 | [5 empty] | 1 | 2475 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1290 | 20200123-6 | 53510111 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 11 | HR |  |  | 70 | 0 | 770 | 100.1 | 870.1 | 2020-01-23 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float Moves; Graders working across access roads; link belt loading sander truck in pit; | 1 | A-085 to A-117 | Windfarm | 0 | 43861 |  | 36 | 43866 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting129020200123-6Operator - Intermdiate - After Jan 1011770 | Corbiere and Sons Contracting129020200123-6Operator - Intermdiate - After Jan 1011770Inv#007-R01 | [5 empty] | 1 | 770 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1290 | 20200123-6 | 53510111 | Access | 0 | Labourer - General - After Jan 10 | 60 | 11 | HR |  |  | 60 | 0 | 660 | 85.8 | 745.8 | 2020-01-23 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float Moves; Graders working across access roads; link belt loading sander truck in pit; | 1 | A-085 to A-117 | Windfarm | 0 | 43861 |  | 36 | 43866 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting129020200123-6Labourer - General - After Jan 1011660 | Corbiere and Sons Contracting129020200123-6Labourer - General - After Jan 1011660Inv#007-R01 | [5 empty] | 1 | 660 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1289 | 20200123-7 | 53520104 | Clearing | 0 | Chainsaw and consumables- After Jan 10 | 60 | 3 | unit/man/day | 0 | 0 |  |  | 180 | 23.4 | 203.4 | 2020-01-23 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling from A118; | 1 | A-118 to A-127 | Innes Lake | 0 | 43861 |  | 36 | 43866 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting128920200123-7Chainsaw and consumables- After Jan 103180 | Corbiere and Sons Contracting128920200123-7Chainsaw and consumables- After Jan 103180Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 180 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1289 | 20200123-7 | 53520104 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-01-23 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling from A118; | 1 | A-118 to A-127 | Innes Lake | 0 | 43861 |  | 36 | 43866 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting128920200123-7Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting128920200123-7Light Truck - Pick up- After Jan 102487.5Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1289 | 20200123-7 | 53520104 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2020-01-23 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling from A118; | 1 | A-118 to A-127 | Innes Lake | 0 | 43861 |  | 36 | 43866 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting128920200123-7Foreman121140 | Corbiere and Sons Contracting128920200123-7Foreman121140Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1289 | 20200123-7 | 53520104 | Clearing | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2020-01-23 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling from A118; | 1 | A-118 to A-127 | Innes Lake | 0 | 43861 |  | 36 | 43866 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting128920200123-7L.O.A.4840 | Corbiere and Sons Contracting128920200123-7L.O.A.4840Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1289 | 20200123-7 | 53520104 | Clearing | 0 | Labourer - Specialized - After Jan 10 | 70 | 33 | HR |  |  | 70 | 0 | 2310 | 300.3 | 2610.3 | 2020-01-23 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling from A118; | 1 | A-118 to A-127 | Innes Lake | 0 | 43861 |  | 36 | 43866 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting128920200123-7Labourer - Specialized - After Jan 10332310 | Corbiere and Sons Contracting128920200123-7Labourer - Specialized - After Jan 10332310Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 2310 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1288 | 20200123-8 | 53510111 | Access | 0 | Dozer - D5 or equal- After Jan 10 | 80.93 | 9 | Dynamic | 60.7 | 0 |  |  | 728.37 | 94.6881 | 823.0581 | 2020-01-23 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Rd. Building and Maintenance from A124-A127; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43861 |  | 36 | 43866 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting128820200123-8Dozer - D5 or equal- After Jan 109728.37 | Corbiere and Sons Contracting128820200123-8Dozer - D5 or equal- After Jan 109728.37Inv#007-R01 | [5 empty] | 1 | 728.37 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1288 | 20200123-8 | 53510106 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 103.84 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2020-01-23 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Rd. Building and Maintenance from A124-A127; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43861 |  | 36 | 43866 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting128820200123-8Excavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting128820200123-8Excavator - 30 ton- After Jan 1091246.05Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 1246.05 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1288 | 20200123-8 | 53510106 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 18 | Dynamic | 110.22 | 0 |  |  | 2645.28 | 343.8864 | 2989.1664 | 2020-01-23 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Rd. Building and Maintenance from A124-A127; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43861 |  | 36 | 43866 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting128820200123-8Excavator - 36 ton- After Jan 10182645.28 | Corbiere and Sons Contracting128820200123-8Excavator - 36 ton- After Jan 10182645.28Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 2645.28 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1288 | 20200123-8 | 53510106 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2020-01-23 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Rd. Building and Maintenance from A124-A127; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43861 |  | 36 | 43866 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting128820200123-8Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting128820200123-8Excavator Thumb - 30 - 50 ton- After Jan 109109.89Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 109.89 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1288 | 20200123-8 | 53510106 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2020-01-23 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Rd. Building and Maintenance from A124-A127; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43861 |  | 36 | 43866 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting128820200123-8Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting128820200123-8Light Truck - Pick up- After Jan 103731.25Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 731.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1288 | 20200123-8 | 53510106 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2020-01-23 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Rd. Building and Maintenance from A124-A127; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43861 |  | 36 | 43866 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting128820200123-8Foreman121140 | Corbiere and Sons Contracting128820200123-8Foreman121140Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1288 | 20200123-8 | 53510106 | Access | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2020-01-23 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Rd. Building and Maintenance from A124-A127; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43861 |  | 36 | 43866 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting128820200123-8L.O.A.61260 | Corbiere and Sons Contracting128820200123-8L.O.A.61260Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1288 | 20200123-8 | 53510111 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-01-23 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Rd. Building and Maintenance from A124-A127; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43861 |  | 36 | 43866 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting128820200123-8L.O.A.1210 | Corbiere and Sons Contracting128820200123-8L.O.A.1210Inv#007-R01 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1288 | 20200123-8 | 53510106 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 33 | HR |  |  | 75 | 0 | 2475 | 321.75 | 2796.75 | 2020-01-23 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Rd. Building and Maintenance from A124-A127; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43861 |  | 36 | 43866 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting128820200123-8Operator - Principle - After Jan 10332475 | Corbiere and Sons Contracting128820200123-8Operator - Principle - After Jan 10332475Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 2475 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1288 | 20200123-8 | 53510111 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2020-01-23 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Rd. Building and Maintenance from A124-A127; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43861 |  | 36 | 43866 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting128820200123-8Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting128820200123-8Operator - Principle - After Jan 1011825Inv#007-R01 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1288 | 20200123-8 | 53510106 | Access | 0 | Labourer - General - After Jan 10 | 60 | 22 | HR |  |  | 60 | 0 | 1320 | 171.6 | 1491.6 | 2020-01-23 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Rd. Building and Maintenance from A124-A127; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43861 |  | 36 | 43866 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting128820200123-8Labourer - General - After Jan 10221320 | Corbiere and Sons Contracting128820200123-8Labourer - General - After Jan 10221320Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 1320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1287 | 20200123-9-R1 | 53510211 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 9 | Dynamic | 98.61 | 0 |  |  | 1183.32 | 153.8316 | 1337.1516 | 2020-01-23 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Clearing access into Black Sturgeon at B024-B022 |  |  |  | 0 | 43861 |  | 36 | 43864 | [5 empty] | Mike Lecocq | 02 | Corbiere and Sons Contracting128720200123-9-R1Dozer D6 or equal- After Jan 1091183.32 | Corbiere and Sons Contracting128720200123-9-R1Dozer D6 or equal- After Jan 1091183.32Inv#007-R01 | [5 empty] | 1 | 1183.32 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1287 | 20200123-9-R1 | 53510211 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 103.84 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2020-01-23 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Clearing access into Black Sturgeon at B024-B022 |  |  |  | 0 | 43861 |  | 36 | 43864 | [5 empty] | Mike Lecocq | 02 | Corbiere and Sons Contracting128720200123-9-R1Excavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting128720200123-9-R1Excavator - 30 ton- After Jan 1091246.05Inv#007-R01 | [5 empty] | 1 | 1246.05 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1287 | 20200123-9-R1 | 53510211 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-01-23 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Clearing access into Black Sturgeon at B024-B022 |  |  |  | 0 | 43861 |  | 36 | 43864 | [5 empty] | Mike Lecocq | 02 | Corbiere and Sons Contracting128720200123-9-R1Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting128720200123-9-R1Light Truck - Pick up- After Jan 101243.75Inv#007-R01 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1287 | 20200123-9-R1 | 53510211 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-01-23 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Clearing access into Black Sturgeon at B024-B022 |  |  |  | 0 | 43861 |  | 36 | 43864 | [5 empty] | Mike Lecocq | 02 | Corbiere and Sons Contracting128720200123-9-R1L.O.A.2420 | Corbiere and Sons Contracting128720200123-9-R1L.O.A.2420Inv#007-R01 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1287 | 20200123-9-R1 | 53510211 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 22 | HR |  |  | 75 | 0 | 1650 | 214.5 | 1864.5 | 2020-01-23 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Clearing access into Black Sturgeon at B024-B022 |  |  |  | 0 | 43861 |  | 36 | 43864 | [5 empty] | Mike Lecocq | 02 | Corbiere and Sons Contracting128720200123-9-R1Operator - Principle - After Jan 10221650 | Corbiere and Sons Contracting128720200123-9-R1Operator - Principle - After Jan 10221650Inv#007-R01 | [5 empty] | 1 | 1650 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1315 | 20200124-1 | 53510106 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 0.20517 | DAY | 182.81 | 0 |  |  | 50.0091 | 6.5012 | 56.5103 | 2020-01-24 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43861 |  | 12 | 43865 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting131520200124-1Light Truck - Pick up- After Jan 100.205165550.0091 | Corbiere and Sons Contracting131520200124-1Light Truck - Pick up- After Jan 100.205165550.0091Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 50.0091 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1315 | 20200124-1 | 53510107 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 0.090763 | DAY | 182.81 | 0 |  |  | 22.1236 | 2.8761 | 24.9997 | 2020-01-24 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Nathan Kyme | Access Mob/Demob |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43861 |  | 12 | 43865 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting131520200124-1Light Truck - Pick up- After Jan 100.090763322.1236 | Corbiere and Sons Contracting131520200124-1Light Truck - Pick up- After Jan 100.090763322.1236Inv#007-R01 |  | WF1 Mob/Demob | WF1 Mob/Demob |  | 0.5 | 0.5 | 11.0618 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1315 | 20200124-1 | 53510111 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 0.33664 | DAY | 182.81 | 0 |  |  | 82.0556 | 10.6672 | 92.7228 | 2020-01-24 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43861 |  | 12 | 43865 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting131520200124-1Light Truck - Pick up- After Jan 100.336638582.0556 | Corbiere and Sons Contracting131520200124-1Light Truck - Pick up- After Jan 100.336638582.0556Inv#007-R01 | [5 empty] | 1 | 82.0556 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1315 | 20200124-1 | 53520102 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 0.75546 | DAY | 182.81 | 0 |  |  | 184.1423 | 23.9385 | 208.0808 | 2020-01-24 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43861 |  | 12 | 43865 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting131520200124-1Light Truck - Pick up- After Jan 100.7554555184.1423 | Corbiere and Sons Contracting131520200124-1Light Truck - Pick up- After Jan 100.7554555184.1423Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 184.1423 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1315 | 20200124-1 | 53520104 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 0.44297 | DAY | 182.81 | 0 |  |  | 107.9734 | 14.0365 | 122.0099 | 2020-01-24 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43861 |  | 12 | 43865 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting131520200124-1Light Truck - Pick up- After Jan 100.4429678107.9734 | Corbiere and Sons Contracting131520200124-1Light Truck - Pick up- After Jan 100.4429678107.9734Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 107.9734 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1315 | 20200124-1 | 53510106 | Access | 0 | Project Manager | 110 | 0.4924 | HR |  |  | 110 | 0 | 54.1637 | 7.0413 | 61.205 | 2020-01-24 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43861 |  | 12 | 43865 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting131520200124-1Project Manager0.492397354.1637 | Corbiere and Sons Contracting131520200124-1Project Manager0.492397354.1637Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 54.1637 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1315 | 20200124-1 | 53510107 | Access | 0 | Project Manager | 110 | 0.21783 | HR |  |  | 110 | 0 | 23.9615 | 3.115 | 27.0765 | 2020-01-24 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Nathan Kyme | Access Mob/Demob |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43861 |  | 12 | 43865 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting131520200124-1Project Manager0.21783223.9615 | Corbiere and Sons Contracting131520200124-1Project Manager0.21783223.9615Inv#007-R01 |  | WF1 Mob/Demob | WF1 Mob/Demob |  | 0.5 | 0.5 | 11.9808 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1315 | 20200124-1 | 53510111 | Access | 0 | Project Manager | 110 | 0.80793 | HR |  |  | 110 | 0 | 88.8726 | 11.5534 | 100.426 | 2020-01-24 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43861 |  | 12 | 43865 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting131520200124-1Project Manager0.807932488.8726 | Corbiere and Sons Contracting131520200124-1Project Manager0.807932488.8726Inv#007-R01 | [5 empty] | 1 | 88.8726 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1315 | 20200124-1 | 53520102 | Clearing | 0 | Project Manager | 110 | 1.8131 | HR |  |  | 110 | 0 | 199.4402 | 25.9272 | 225.3674 | 2020-01-24 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43861 |  | 12 | 43865 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting131520200124-1Project Manager1.8130931199.4402 | Corbiere and Sons Contracting131520200124-1Project Manager1.8130931199.4402Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 199.4402 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1315 | 20200124-1 | 53520104 | Clearing | 0 | Project Manager | 110 | 1.0631 | HR |  |  | 110 | 0 | 116.9435 | 15.2027 | 132.1462 | 2020-01-24 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43861 |  | 12 | 43865 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting131520200124-1Project Manager1.0631227116.9435 | Corbiere and Sons Contracting131520200124-1Project Manager1.0631227116.9435Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 116.9435 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1315 | 20200124-1 | 53510106 | Access | 0 | Superintendent | 105 | 0.4924 | HR |  |  | 105 | 0 | 51.7017 | 6.7212 | 58.4229 | 2020-01-24 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43861 |  | 12 | 43865 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting131520200124-1Superintendent0.492397351.7017 | Corbiere and Sons Contracting131520200124-1Superintendent0.492397351.7017Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 51.7017 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1315 | 20200124-1 | 53510107 | Access | 0 | Superintendent | 105 | 0.21783 | HR |  |  | 105 | 0 | 22.8724 | 2.9734 | 25.8458 | 2020-01-24 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Nathan Kyme | Access Mob/Demob |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43861 |  | 12 | 43865 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting131520200124-1Superintendent0.21783222.8724 | Corbiere and Sons Contracting131520200124-1Superintendent0.21783222.8724Inv#007-R01 |  | WF1 Mob/Demob | WF1 Mob/Demob |  | 0.5 | 0.5 | 11.4362 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1315 | 20200124-1 | 53510111 | Access | 0 | Superintendent | 105 | 0.80793 | HR |  |  | 105 | 0 | 84.8329 | 11.0283 | 95.8612 | 2020-01-24 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43861 |  | 12 | 43865 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting131520200124-1Superintendent0.807932484.8329 | Corbiere and Sons Contracting131520200124-1Superintendent0.807932484.8329Inv#007-R01 | [5 empty] | 1 | 84.8329 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1315 | 20200124-1 | 53520102 | Clearing | 0 | Superintendent | 105 | 1.8131 | HR |  |  | 105 | 0 | 190.3748 | 24.7487 | 215.1235 | 2020-01-24 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43861 |  | 12 | 43865 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting131520200124-1Superintendent1.8130931190.3748 | Corbiere and Sons Contracting131520200124-1Superintendent1.8130931190.3748Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 190.3748 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1315 | 20200124-1 | 53520104 | Clearing | 0 | Superintendent | 105 | 1.0631 | HR |  |  | 105 | 0 | 111.6279 | 14.5116 | 126.1395 | 2020-01-24 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43861 |  | 12 | 43865 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting131520200124-1Superintendent1.0631227111.6279 | Corbiere and Sons Contracting131520200124-1Superintendent1.0631227111.6279Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 111.6279 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1315 | 20200124-1 | 53510106 | Access | 0 | Project Coordinator | 80 | 0.4924 | HR |  |  | 80 | 0 | 39.3918 | 5.1209 | 44.5127 | 2020-01-24 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43861 |  | 12 | 43865 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting131520200124-1Project Coordinator0.492397339.3918 | Corbiere and Sons Contracting131520200124-1Project Coordinator0.492397339.3918Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 39.3918 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1315 | 20200124-1 | 53510107 | Access | 0 | Project Coordinator | 80 | 0.21783 | HR |  |  | 80 | 0 | 17.4266 | 2.2655 | 19.6921 | 2020-01-24 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Nathan Kyme | Access Mob/Demob |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43861 |  | 12 | 43865 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting131520200124-1Project Coordinator0.21783217.4266 | Corbiere and Sons Contracting131520200124-1Project Coordinator0.21783217.4266Inv#007-R01 |  | WF1 Mob/Demob | WF1 Mob/Demob |  | 0.5 | 0.5 | 8.7133 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1315 | 20200124-1 | 53510111 | Access | 0 | Project Coordinator | 80 | 0.80793 | HR |  |  | 80 | 0 | 64.6346 | 8.4025 | 73.0371 | 2020-01-24 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43861 |  | 12 | 43865 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting131520200124-1Project Coordinator0.807932464.6346 | Corbiere and Sons Contracting131520200124-1Project Coordinator0.807932464.6346Inv#007-R01 | [5 empty] | 1 | 64.6346 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1315 | 20200124-1 | 53520102 | Clearing | 0 | Project Coordinator | 80 | 1.8131 | HR |  |  | 80 | 0 | 145.0474 | 18.8562 | 163.9036 | 2020-01-24 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43861 |  | 12 | 43865 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting131520200124-1Project Coordinator1.8130931145.0474 | Corbiere and Sons Contracting131520200124-1Project Coordinator1.8130931145.0474Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 145.0474 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1315 | 20200124-1 | 53520104 | Clearing | 0 | Project Coordinator | 80 | 1.0631 | HR |  |  | 80 | 0 | 85.0498 | 11.0565 | 96.1063 | 2020-01-24 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43861 |  | 12 | 43865 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting131520200124-1Project Coordinator1.063122785.0498 | Corbiere and Sons Contracting131520200124-1Project Coordinator1.063122785.0498Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 85.0498 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1315 | 20200124-1 | 53510106 | Access | 0 | Safety Advisor | 85 | 0.4924 | HR |  |  | 85 | 0 | 41.8538 | 5.441 | 47.2948 | 2020-01-24 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43861 |  | 12 | 43865 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting131520200124-1Safety Advisor0.492397341.8538 | Corbiere and Sons Contracting131520200124-1Safety Advisor0.492397341.8538Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 41.8538 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1315 | 20200124-1 | 53510107 | Access | 0 | Safety Advisor | 85 | 0.21783 | HR |  |  | 85 | 0 | 18.5157 | 2.407 | 20.9227 | 2020-01-24 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Nathan Kyme | Access Mob/Demob |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43861 |  | 12 | 43865 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting131520200124-1Safety Advisor0.21783218.5157 | Corbiere and Sons Contracting131520200124-1Safety Advisor0.21783218.5157Inv#007-R01 |  | WF1 Mob/Demob | WF1 Mob/Demob |  | 0.5 | 0.5 | 9.2578 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1315 | 20200124-1 | 53510111 | Access | 0 | Safety Advisor | 85 | 0.80793 | HR |  |  | 85 | 0 | 68.6743 | 8.9277 | 77.602 | 2020-01-24 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43861 |  | 12 | 43865 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting131520200124-1Safety Advisor0.807932468.6743 | Corbiere and Sons Contracting131520200124-1Safety Advisor0.807932468.6743Inv#007-R01 | [5 empty] | 1 | 68.6743 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1315 | 20200124-1 | 53520102 | Clearing | 0 | Safety Advisor | 85 | 1.8131 | HR |  |  | 85 | 0 | 154.1129 | 20.0347 | 174.1476 | 2020-01-24 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43861 |  | 12 | 43865 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting131520200124-1Safety Advisor1.8130931154.1129 | Corbiere and Sons Contracting131520200124-1Safety Advisor1.8130931154.1129Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 154.1129 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1315 | 20200124-1 | 53520104 | Clearing | 0 | Safety Advisor | 85 | 1.0631 | HR |  |  | 85 | 0 | 90.3654 | 11.7475 | 102.1129 | 2020-01-24 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43861 |  | 12 | 43865 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting131520200124-1Safety Advisor1.063122790.3654 | Corbiere and Sons Contracting131520200124-1Safety Advisor1.063122790.3654Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 90.3654 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1315 | 20200124-1 | 53510106 | Access | 0 | Site Administrator | 50 | 0.45136 | HR |  |  | 50 | 0 | 22.5682 | 2.9339 | 25.5021 | 2020-01-24 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43861 |  | 12 | 43865 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting131520200124-1Site Administrator0.451364222.5682 | Corbiere and Sons Contracting131520200124-1Site Administrator0.451364222.5682Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 22.5682 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1315 | 20200124-1 | 53510107 | Access | 0 | Site Administrator | 50 | 0.19968 | HR |  |  | 50 | 0 | 9.984 | 1.2979 | 11.2819 | 2020-01-24 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Nathan Kyme | Access Mob/Demob |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43861 |  | 12 | 43865 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting131520200124-1Site Administrator0.19967939.984 | Corbiere and Sons Contracting131520200124-1Site Administrator0.19967939.984Inv#007-R01 |  | WF1 Mob/Demob | WF1 Mob/Demob |  | 0.5 | 0.5 | 4.992 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1315 | 20200124-1 | 53510111 | Access | 0 | Site Administrator | 50 | 0.7406 | HR |  |  | 50 | 0 | 37.0302 | 4.8139 | 41.8441 | 2020-01-24 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43861 |  | 12 | 43865 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting131520200124-1Site Administrator0.740604737.0302 | Corbiere and Sons Contracting131520200124-1Site Administrator0.740604737.0302Inv#007-R01 | [5 empty] | 1 | 37.0302 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1315 | 20200124-1 | 53520102 | Clearing | 0 | Site Administrator | 50 | 1.662 | HR |  |  | 50 | 0 | 83.1001 | 10.803 | 93.9031 | 2020-01-24 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43861 |  | 12 | 43865 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting131520200124-1Site Administrator1.66200283.1001 | Corbiere and Sons Contracting131520200124-1Site Administrator1.66200283.1001Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 83.1001 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1315 | 20200124-1 | 53520104 | Clearing | 0 | Site Administrator | 50 | 0.97453 | HR |  |  | 50 | 0 | 48.7265 | 6.3344 | 55.0609 | 2020-01-24 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43861 |  | 12 | 43865 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting131520200124-1Site Administrator0.974529148.7265 | Corbiere and Sons Contracting131520200124-1Site Administrator0.974529148.7265Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 48.7265 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1315 | 20200124-1 | 53510106 | Access | 0 | Project Controls | 70 | 0.4924 | HR |  |  | 70 | 0 | 34.4678 | 4.4808 | 38.9486 | 2020-01-24 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43861 |  | 12 | 43865 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting131520200124-1Project Controls0.492397334.4678 | Corbiere and Sons Contracting131520200124-1Project Controls0.492397334.4678Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 34.4678 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1315 | 20200124-1 | 53510107 | Access | 0 | Project Controls | 70 | 0.21783 | HR |  |  | 70 | 0 | 15.2482 | 1.9823 | 17.2305 | 2020-01-24 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Nathan Kyme | Access Mob/Demob |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43861 |  | 12 | 43865 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting131520200124-1Project Controls0.21783215.2482 | Corbiere and Sons Contracting131520200124-1Project Controls0.21783215.2482Inv#007-R01 |  | WF1 Mob/Demob | WF1 Mob/Demob |  | 0.5 | 0.5 | 7.6241 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1315 | 20200124-1 | 53510111 | Access | 0 | Project Controls | 70 | 0.80793 | HR |  |  | 70 | 0 | 56.5553 | 7.3522 | 63.9075 | 2020-01-24 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43861 |  | 12 | 43865 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting131520200124-1Project Controls0.807932456.5553 | Corbiere and Sons Contracting131520200124-1Project Controls0.807932456.5553Inv#007-R01 | [5 empty] | 1 | 56.5553 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1315 | 20200124-1 | 53520102 | Clearing | 0 | Project Controls | 70 | 1.8131 | HR |  |  | 70 | 0 | 126.9165 | 16.4991 | 143.4156 | 2020-01-24 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43861 |  | 12 | 43865 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting131520200124-1Project Controls1.8130931126.9165 | Corbiere and Sons Contracting131520200124-1Project Controls1.8130931126.9165Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 126.9165 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1315 | 20200124-1 | 53520104 | Clearing | 0 | Project Controls | 70 | 1.0631 | HR |  |  | 70 | 0 | 74.4186 | 9.6744 | 84.093 | 2020-01-24 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43861 |  | 12 | 43865 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting131520200124-1Project Controls1.063122774.4186 | Corbiere and Sons Contracting131520200124-1Project Controls1.063122774.4186Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 74.4186 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1315 | 20200124-1 | 53510106 | Access | 0 | L.O.A. | 210 | 0.2462 | DAY |  |  |  | 0 | 51.7017 | 6.7212 | 58.4229 | 2020-01-24 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43861 |  | 12 | 43865 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting131520200124-1L.O.A.0.246198651.7017 | Corbiere and Sons Contracting131520200124-1L.O.A.0.246198651.7017Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 51.7017 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1315 | 20200124-1 | 53510107 | Access | 0 | L.O.A. | 210 | 0.10892 | DAY |  |  |  | 0 | 22.8724 | 2.9734 | 25.8458 | 2020-01-24 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Nathan Kyme | Access Mob/Demob |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43861 |  | 12 | 43865 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting131520200124-1L.O.A.0.10891622.8724 | Corbiere and Sons Contracting131520200124-1L.O.A.0.10891622.8724Inv#007-R01 |  | WF1 Mob/Demob | WF1 Mob/Demob |  | 0.5 | 0.5 | 11.4362 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1315 | 20200124-1 | 53510111 | Access | 0 | L.O.A. | 210 | 0.40397 | DAY |  |  |  | 0 | 84.8329 | 11.0283 | 95.8612 | 2020-01-24 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43861 |  | 12 | 43865 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting131520200124-1L.O.A.0.403966284.8329 | Corbiere and Sons Contracting131520200124-1L.O.A.0.403966284.8329Inv#007-R01 | [5 empty] | 1 | 84.8329 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1315 | 20200124-1 | 53520102 | Clearing | 0 | L.O.A. | 210 | 0.90655 | DAY |  |  |  | 0 | 190.3748 | 24.7487 | 215.1235 | 2020-01-24 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43861 |  | 12 | 43865 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting131520200124-1L.O.A.0.9065465190.3748 | Corbiere and Sons Contracting131520200124-1L.O.A.0.9065465190.3748Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 190.3748 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1315 | 20200124-1 | 53520104 | Clearing | 0 | L.O.A. | 210 | 0.53156 | DAY |  |  |  | 0 | 111.6279 | 14.5116 | 126.1395 | 2020-01-24 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43861 |  | 12 | 43865 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting131520200124-1L.O.A.0.5315613111.6279 | Corbiere and Sons Contracting131520200124-1L.O.A.0.5315613111.6279Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 111.6279 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1324 | 20200124-10-R1 | 53510611 | Access | 0 | Loader JD 524 to 624 or equal | 99 | 2.2382 | HR | 74.25 | 0 |  |  | 221.5863 | 28.8062 | 250.3925 | 2020-01-24 | 1 | Inv#009 | 43894 | 86 | 0 | 1 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  | Moved to WF6 since the cost codes were for WF6 | 26 | Approved | ROW INTERNAL - Corbiere Yard Maintenance LEM's Terrace Bay | 9025 | Float Moves, FB from Gull Bay to Schreiber; Supervision and Orientation. | 6 |  |  | 1 | 43837 |  | 40 | 43869 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting132420200124-10-R1Loader JD 524 to 624 or equal2.2382455221.5863 | Corbiere and Sons Contracting132420200124-10-R1Loader JD 524 to 624 or equal2.2382455221.5863Inv#009 | [5 empty] | 1 | 221.5863 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1324 | 20200124-10-R1 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 0.8953 | DAY | 182.81 | 0 |  |  | 218.2289 | 28.3698 | 246.5987 | 2020-01-24 | 1 | Inv#009 | 43894 | 86 | 0 | 1 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  | Moved to WF6 since the cost codes were for WF6 | 26 | Approved | ROW INTERNAL - Corbiere Yard Maintenance LEM's Terrace Bay | 9025 | Float Moves, FB from Gull Bay to Schreiber; Supervision and Orientation. | 6 |  |  | 1 | 43837 |  | 40 | 43869 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting132420200124-10-R1Light Truck - Pick up- After Jan 100.8952982218.2289 | Corbiere and Sons Contracting132420200124-10-R1Light Truck - Pick up- After Jan 100.8952982218.2289Inv#009 | [5 empty] | 1 | 218.2289 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1324 | 20200124-10-R1 | 53510611 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 4.4765 | Dynamic | 91.79 | 0 |  |  | 547.8777 | 71.2241 | 619.1018 | 2020-01-24 | 1 | Inv#009 | 43894 | 86 | 0 | 1 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  | Moved to WF6 since the cost codes were for WF6 | 26 | Approved | ROW INTERNAL - Corbiere Yard Maintenance LEM's Terrace Bay | 9025 | Float Moves, FB from Gull Bay to Schreiber; Supervision and Orientation. | 6 |  |  | 1 | 43837 |  | 40 | 43869 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting132420200124-10-R1Tractor Trailer - 60 Ton- After Jan 104.4764911547.8777 | Corbiere and Sons Contracting132420200124-10-R1Tractor Trailer - 60 Ton- After Jan 104.4764911547.8777Inv#009 | [5 empty] | 1 | 547.8777 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1324 | 20200124-10-R1 | 53510611 | Access | 0 | L.O.A. | 210 | 2.6859 | DAY |  |  |  | 0 | 564.0379 | 73.3249 | 637.3628 | 2020-01-24 | 1 | Inv#009 | 43894 | 86 | 0 | 1 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  | Moved to WF6 since the cost codes were for WF6 | 26 | Approved | ROW INTERNAL - Corbiere Yard Maintenance LEM's Terrace Bay | 9025 | Float Moves, FB from Gull Bay to Schreiber; Supervision and Orientation. | 6 |  |  | 1 | 43837 |  | 40 | 43869 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting132420200124-10-R1L.O.A.2.6858946564.0379 | Corbiere and Sons Contracting132420200124-10-R1L.O.A.2.6858946564.0379Inv#009 | [5 empty] | 1 | 564.0379 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1324 | 20200124-10-R1 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 4.4765 | HR |  |  | 75 | 0 | 335.7368 | 43.6458 | 379.3826 | 2020-01-24 | 1 | Inv#009 | 43894 | 86 | 0 | 1 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  | Moved to WF6 since the cost codes were for WF6 | 26 | Approved | ROW INTERNAL - Corbiere Yard Maintenance LEM's Terrace Bay | 9025 | Float Moves, FB from Gull Bay to Schreiber; Supervision and Orientation. | 6 |  |  | 1 | 43837 |  | 40 | 43869 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting132420200124-10-R1Operator - Principle - After Jan 104.4764911335.7368 | Corbiere and Sons Contracting132420200124-10-R1Operator - Principle - After Jan 104.4764911335.7368Inv#009 | [5 empty] | 1 | 335.7368 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1324 | 20200124-10-R1 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 4.9241 | HR |  |  | 70 | 0 | 344.6898 | 44.8097 | 389.4995 | 2020-01-24 | 1 | Inv#009 | 43894 | 86 | 0 | 1 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  | Moved to WF6 since the cost codes were for WF6 | 26 | Approved | ROW INTERNAL - Corbiere Yard Maintenance LEM's Terrace Bay | 9025 | Float Moves, FB from Gull Bay to Schreiber; Supervision and Orientation. | 6 |  |  | 1 | 43837 |  | 40 | 43869 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting132420200124-10-R1Operator - Intermdiate - After Jan 104.9241402344.6898 | Corbiere and Sons Contracting132420200124-10-R1Operator - Intermdiate - After Jan 104.9241402344.6898Inv#009 | [5 empty] | 1 | 344.6898 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1324 | 20200124-10-R1 | 53510611 | Access | 0 | Labourer - Specialized - After Jan 10 | 70 | 4.4765 | HR |  |  | 70 | 0 | 313.3544 | 40.7361 | 354.0905 | 2020-01-24 | 1 | Inv#009 | 43894 | 86 | 0 | 1 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  | Moved to WF6 since the cost codes were for WF6 | 26 | Approved | ROW INTERNAL - Corbiere Yard Maintenance LEM's Terrace Bay | 9025 | Float Moves, FB from Gull Bay to Schreiber; Supervision and Orientation. | 6 |  |  | 1 | 43837 |  | 40 | 43869 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting132420200124-10-R1Labourer - Specialized - After Jan 104.4764911313.3544 | Corbiere and Sons Contracting132420200124-10-R1Labourer - Specialized - After Jan 104.4764911313.3544Inv#009 | [5 empty] | 1 | 313.3544 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1324 | 20200124-10-R1 | 53510611 | Access | 0 | Labourer - General - After Jan 10 | 60 | 4.9241 | HR |  |  | 60 | 0 | 295.4484 | 38.4083 | 333.8567 | 2020-01-24 | 1 | Inv#009 | 43894 | 86 | 0 | 1 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  | Moved to WF6 since the cost codes were for WF6 | 26 | Approved | ROW INTERNAL - Corbiere Yard Maintenance LEM's Terrace Bay | 9025 | Float Moves, FB from Gull Bay to Schreiber; Supervision and Orientation. | 6 |  |  | 1 | 43837 |  | 40 | 43869 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting132420200124-10-R1Labourer - General - After Jan 104.9241402295.4484 | Corbiere and Sons Contracting132420200124-10-R1Labourer - General - After Jan 104.9241402295.4484Inv#009 | [5 empty] | 1 | 295.4484 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1350 | 20200124-11-R1 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 9 | Dynamic | 95.24 | 0 |  |  | 1142.82 | 148.5666 | 1291.3866 | 2020-01-24 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  | Light Truck - Pick up coded wrong |  | Approved |  |  | Winter Rd. Building and Access at Santoy Mountain | 6 | C155-C157 | Santoy Moutain | 0 | 43861 |  | 40 | 43869 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting135020200124-11-R1Grader - Cat 12 to 14 or equal- After Jan 1091142.82 | Corbiere and Sons Contracting135020200124-11-R1Grader - Cat 12 to 14 or equal- After Jan 1091142.82Inv#007-R01 | [5 empty] | 1 | 1142.82 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1350 | 20200124-11-R1 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-01-24 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  | Light Truck - Pick up coded wrong |  | Approved |  |  | Winter Rd. Building and Access at Santoy Mountain | 6 | C155-C157 | Santoy Moutain | 0 | 43861 |  | 40 | 43869 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting135020200124-11-R1L.O.A.1210 | Corbiere and Sons Contracting135020200124-11-R1L.O.A.1210Inv#007-R01 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1350 | 20200124-11-R1 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2020-01-24 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  | Light Truck - Pick up coded wrong |  | Approved |  |  | Winter Rd. Building and Access at Santoy Mountain | 6 | C155-C157 | Santoy Moutain | 0 | 43861 |  | 40 | 43869 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting135020200124-11-R1Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting135020200124-11-R1Operator - Principle - After Jan 1011825Inv#007-R01 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1328 | 20200124-14 | 53510611 | Access | 0 | Loader JD 524 to 624 or equal | 99 | 6 | HR | 74.25 | 0 |  |  | 594 | 77.22 | 671.22 | 2020-01-24 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Clearing Access into Lake A and clearing access for bridge install; | 6 | C129-C151 | Lake "A" | 0 | 43861 |  | 40 | 43869 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting132820200124-14Loader JD 524 to 624 or equal6594 | Corbiere and Sons Contracting132820200124-14Loader JD 524 to 624 or equal6594Inv#007-R01 | [5 empty] | 1 | 594 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1328 | 20200124-14 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 6 | Dynamic | 98.61 | 0 |  |  | 788.88 | 102.5544 | 891.4344 | 2020-01-24 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Clearing Access into Lake A and clearing access for bridge install; | 6 | C129-C151 | Lake "A" | 0 | 43861 |  | 40 | 43869 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting132820200124-14Dozer D6 or equal- After Jan 106788.88 | Corbiere and Sons Contracting132820200124-14Dozer D6 or equal- After Jan 106788.88Inv#007-R01 | [5 empty] | 1 | 788.88 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1328 | 20200124-14 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-01-24 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Clearing Access into Lake A and clearing access for bridge install; | 6 | C129-C151 | Lake "A" | 0 | 43861 |  | 40 | 43869 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting132820200124-14Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting132820200124-14Light Truck - Pick up- After Jan 101243.75Inv#007-R01 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1328 | 20200124-14 | 53510611 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-01-24 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Clearing Access into Lake A and clearing access for bridge install; | 6 | C129-C151 | Lake "A" | 0 | 43861 |  | 40 | 43869 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting132820200124-14L.O.A.2420 | Corbiere and Sons Contracting132820200124-14L.O.A.2420Inv#007-R01 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1328 | 20200124-14 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 22 | HR |  |  | 75 | 0 | 1650 | 214.5 | 1864.5 | 2020-01-24 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Clearing Access into Lake A and clearing access for bridge install; | 6 | C129-C151 | Lake "A" | 0 | 43861 |  | 40 | 43869 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting132820200124-14Operator - Principle - After Jan 10221650 | Corbiere and Sons Contracting132820200124-14Operator - Principle - After Jan 10221650Inv#007-R01 | [5 empty] | 1 | 1650 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1387 | 20200124-17 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 0.8953 | DAY | 182.81 | 0 |  |  | 218.2289 | 28.3698 | 246.5987 | 2020-01-24 | 1 | Inv#009 | 43894 | 86 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 25 | Approved | INTERNAL Supervision for Terrace Bay Yard | 9024 | Project Supervision | 6 |  | Supervision Schrieber Yard | 1 | 43868 |  | 40 | 43869 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting138720200124-17Light Truck - Pick up- After Jan 100.8952982218.2289 | Corbiere and Sons Contracting138720200124-17Light Truck - Pick up- After Jan 100.8952982218.2289Inv#009 | [5 empty] | 1 | 218.2289 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1387 | 20200124-17 | 53510611 | Access | 0 | Project Coordinator | 80 | 5.3718 | HR |  |  | 80 | 0 | 429.7431 | 55.8666 | 485.6097 | 2020-01-24 | 1 | Inv#009 | 43894 | 86 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 25 | Approved | INTERNAL Supervision for Terrace Bay Yard | 9024 | Project Supervision | 6 |  | Supervision Schrieber Yard | 1 | 43868 |  | 40 | 43869 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting138720200124-17Project Coordinator5.3717893429.7431 | Corbiere and Sons Contracting138720200124-17Project Coordinator5.3717893429.7431Inv#009 | [5 empty] | 1 | 429.7431 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1387 | 20200124-17 | 53510611 | Access | 0 | Foreman | 95 | 5.3718 | HR |  |  | 95 | 0 | 510.32 | 66.3416 | 576.6616 | 2020-01-24 | 1 | Inv#009 | 43894 | 86 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 25 | Approved | INTERNAL Supervision for Terrace Bay Yard | 9024 | Project Supervision | 6 |  | Supervision Schrieber Yard | 1 | 43868 |  | 40 | 43869 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting138720200124-17Foreman5.3717893510.32 | Corbiere and Sons Contracting138720200124-17Foreman5.3717893510.32Inv#009 | [5 empty] | 1 | 510.32 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1387 | 20200124-17 | 53510611 | Access | 0 | L.O.A. | 210 | 0.8953 | DAY |  |  |  | 0 | 188.0126 | 24.4416 | 212.4542 | 2020-01-24 | 1 | Inv#009 | 43894 | 86 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 25 | Approved | INTERNAL Supervision for Terrace Bay Yard | 9024 | Project Supervision | 6 |  | Supervision Schrieber Yard | 1 | 43868 |  | 40 | 43869 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting138720200124-17L.O.A.0.8952982188.0126 | Corbiere and Sons Contracting138720200124-17L.O.A.0.8952982188.0126Inv#009 | [5 empty] | 1 | 188.0126 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1316 | 20200124-2 | 53510106 | Access | 0 | Loader JD 524 to 624 or equal | 99 | 0.20517 | HR | 74.25 | 0 |  |  | 20.3114 | 2.6405 | 22.9519 | 2020-01-24 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General yard maintenace | 1 |  |  | 1 | 43861 |  | 12 | 43865 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting131620200124-2Loader JD 524 to 624 or equal0.205165520.3114 | Corbiere and Sons Contracting131620200124-2Loader JD 524 to 624 or equal0.205165520.3114Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 20.3114 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1316 | 20200124-2 | 53510111 | Access | 0 | Loader JD 524 to 624 or equal | 99 | 0.33664 | HR | 74.25 | 0 |  |  | 33.3272 | 4.3325 | 37.6597 | 2020-01-24 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General yard maintenace | 1 |  |  | 1 | 43861 |  | 12 | 43865 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting131620200124-2Loader JD 524 to 624 or equal0.336638533.3272 | Corbiere and Sons Contracting131620200124-2Loader JD 524 to 624 or equal0.336638533.3272Inv#007-R01 | [5 empty] | 1 | 33.3272 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1316 | 20200124-2 | 53520102 | Clearing | 0 | Loader JD 524 to 624 or equal | 99 | 0.75546 | HR | 74.25 | 0 |  |  | 74.7901 | 9.7227 | 84.5128 | 2020-01-24 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General yard maintenace | 1 |  |  | 1 | 43861 |  | 12 | 43865 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting131620200124-2Loader JD 524 to 624 or equal0.755455574.7901 | Corbiere and Sons Contracting131620200124-2Loader JD 524 to 624 or equal0.755455574.7901Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 74.7901 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1316 | 20200124-2 | 53520104 | Clearing | 0 | Loader JD 524 to 624 or equal | 99 | 0.44297 | HR | 74.25 | 0 |  |  | 43.8538 | 5.701 | 49.5548 | 2020-01-24 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General yard maintenace | 1 |  |  | 1 | 43861 |  | 12 | 43865 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting131620200124-2Loader JD 524 to 624 or equal0.442967843.8538 | Corbiere and Sons Contracting131620200124-2Loader JD 524 to 624 or equal0.442967843.8538Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 43.8538 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1316 | 20200124-2 | 53510106 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 0.041033 | DAY | 182.81 | 0 |  |  | 10.0018 | 1.3002 | 11.302 | 2020-01-24 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General yard maintenace | 1 |  |  | 1 | 43861 |  | 12 | 43865 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting131620200124-2Light Truck - Pick up- After Jan 100.041033110.0018 | Corbiere and Sons Contracting131620200124-2Light Truck - Pick up- After Jan 100.041033110.0018Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 10.0018 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1316 | 20200124-2 | 53510111 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 0.067328 | DAY | 182.81 | 0 |  |  | 16.4111 | 2.1334 | 18.5445 | 2020-01-24 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General yard maintenace | 1 |  |  | 1 | 43861 |  | 12 | 43865 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting131620200124-2Light Truck - Pick up- After Jan 100.067327716.4111 | Corbiere and Sons Contracting131620200124-2Light Truck - Pick up- After Jan 100.067327716.4111Inv#007-R01 | [5 empty] | 1 | 16.4111 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1316 | 20200124-2 | 53520102 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 0.15109 | DAY | 182.81 | 0 |  |  | 36.8285 | 4.7877 | 41.6162 | 2020-01-24 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General yard maintenace | 1 |  |  | 1 | 43861 |  | 12 | 43865 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting131620200124-2Light Truck - Pick up- After Jan 100.151091136.8285 | Corbiere and Sons Contracting131620200124-2Light Truck - Pick up- After Jan 100.151091136.8285Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 36.8285 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1316 | 20200124-2 | 53520104 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 0.088594 | DAY | 182.81 | 0 |  |  | 21.5947 | 2.8073 | 24.402 | 2020-01-24 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General yard maintenace | 1 |  |  | 1 | 43861 |  | 12 | 43865 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting131620200124-2Light Truck - Pick up- After Jan 100.088593621.5947 | Corbiere and Sons Contracting131620200124-2Light Truck - Pick up- After Jan 100.088593621.5947Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 21.5947 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1316 | 20200124-2 | 53510106 | Access | 0 | Operator - Apprentice | 60 | 0.41033 | HR |  |  | 60 | 0 | 24.6199 | 3.2006 | 27.8205 | 2020-01-24 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General yard maintenace | 1 |  |  | 1 | 43861 |  | 12 | 43865 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting131620200124-2Operator - Apprentice0.410331124.6199 | Corbiere and Sons Contracting131620200124-2Operator - Apprentice0.410331124.6199Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 24.6199 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1316 | 20200124-2 | 53510111 | Access | 0 | Operator - Apprentice | 60 | 0.67328 | HR |  |  | 60 | 0 | 40.3966 | 5.2516 | 45.6482 | 2020-01-24 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General yard maintenace | 1 |  |  | 1 | 43861 |  | 12 | 43865 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting131620200124-2Operator - Apprentice0.67327740.3966 | Corbiere and Sons Contracting131620200124-2Operator - Apprentice0.67327740.3966Inv#007-R01 | [5 empty] | 1 | 40.3966 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1316 | 20200124-2 | 53520102 | Clearing | 0 | Operator - Apprentice | 60 | 1.5109 | HR |  |  | 60 | 0 | 90.6547 | 11.7851 | 102.4398 | 2020-01-24 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General yard maintenace | 1 |  |  | 1 | 43861 |  | 12 | 43865 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting131620200124-2Operator - Apprentice1.510910990.6547 | Corbiere and Sons Contracting131620200124-2Operator - Apprentice1.510910990.6547Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 90.6547 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1316 | 20200124-2 | 53520104 | Clearing | 0 | Operator - Apprentice | 60 | 0.88594 | HR |  |  | 60 | 0 | 53.1561 | 6.9103 | 60.0664 | 2020-01-24 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General yard maintenace | 1 |  |  | 1 | 43861 |  | 12 | 43865 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting131620200124-2Operator - Apprentice0.885935553.1561 | Corbiere and Sons Contracting131620200124-2Operator - Apprentice0.885935553.1561Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 53.1561 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1317 | 20200124-3 | 53520102 | Clearing | 0 | Brusher | 202.5 | 5 | HR | 151.88 |  |  |  | 1012.5 | 131.625 | 1144.125 | 2020-01-24 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grinding of Material at A061 and A079; Brusher working from A068-A069; | 1 | A-055 to A-084 | Eldorado | 0 | 43861 |  | 36 | 43866 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting131720200124-3Brusher51012.5 | Corbiere and Sons Contracting131720200124-3Brusher51012.5Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1012.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1317 | 20200124-3 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 18 | HR | 417.6 | 0 |  |  | 10022.4 | 1302.912 | 11325.312 | 2020-01-24 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grinding of Material at A061 and A079; Brusher working from A068-A069; | 1 | A-055 to A-084 | Eldorado | 0 | 43861 |  | 36 | 43866 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting131720200124-3Grinder - 4710 Peterson or equal1810022.4 | Corbiere and Sons Contracting131720200124-3Grinder - 4710 Peterson or equal1810022.4Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 10022.4 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1317 | 20200124-3 | 53520102 | Clearing | 0 | Log Loader | 153 | 18 | HR | 114.75 | 0 |  |  | 2754 | 358.02 | 3112.02 | 2020-01-24 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grinding of Material at A061 and A079; Brusher working from A068-A069; | 1 | A-055 to A-084 | Eldorado | 0 | 43861 |  | 36 | 43866 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting131720200124-3Log Loader182754 | Corbiere and Sons Contracting131720200124-3Log Loader182754Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2754 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1317 | 20200124-3 | 53520102 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2020-01-24 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grinding of Material at A061 and A079; Brusher working from A068-A069; | 1 | A-055 to A-084 | Eldorado | 0 | 43861 |  | 36 | 43866 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting131720200124-3Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting131720200124-3Light Truck - Pick up- After Jan 103731.25Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 731.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1317 | 20200124-3 | 53520102 | Clearing | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2020-01-24 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grinding of Material at A061 and A079; Brusher working from A068-A069; | 1 | A-055 to A-084 | Eldorado | 0 | 43861 |  | 36 | 43866 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting131720200124-3L.O.A.3630 | Corbiere and Sons Contracting131720200124-3L.O.A.3630Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1317 | 20200124-3 | 53520102 | Clearing | 0 | Operator - Principle - After Jan 10 | 75 | 29 | HR |  |  | 75 | 0 | 2175 | 282.75 | 2457.75 | 2020-01-24 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grinding of Material at A061 and A079; Brusher working from A068-A069; | 1 | A-055 to A-084 | Eldorado | 0 | 43861 |  | 36 | 43866 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting131720200124-3Operator - Principle - After Jan 10292175 | Corbiere and Sons Contracting131720200124-3Operator - Principle - After Jan 10292175Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2175 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1318 | 20200124-4 | 53510111 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 18 | Dynamic | 95.24 | 0 |  |  | 2285.64 | 297.1332 | 2582.7732 | 2020-01-24 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moves; Graders clearing up access roadsy | 1 | A-085 to A-117 | Windfarm | 0 | 43861 |  | 36 | 43868 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting131820200124-4Grader - Cat 12 to 14 or equal- After Jan 10182285.64 | Corbiere and Sons Contracting131820200124-4Grader - Cat 12 to 14 or equal- After Jan 10182285.64Inv#009 | [5 empty] | 1 | 2285.64 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1318 | 20200124-4 | 53510111 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-01-24 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moves; Graders clearing up access roadsy | 1 | A-085 to A-117 | Windfarm | 0 | 43861 |  | 36 | 43868 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting131820200124-4Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting131820200124-4Light Truck - Pick up- After Jan 102487.5Inv#009 | [5 empty] | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1318 | 20200124-4 | 53510111 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2020-01-24 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moves; Graders clearing up access roadsy | 1 | A-085 to A-117 | Windfarm | 0 | 43861 |  | 36 | 43868 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting131820200124-4L.O.A.3630 | Corbiere and Sons Contracting131820200124-4L.O.A.3630Inv#009 | [5 empty] | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1318 | 20200124-4 | 53510111 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 22 | HR |  |  | 75 | 0 | 1650 | 214.5 | 1864.5 | 2020-01-24 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moves; Graders clearing up access roadsy | 1 | A-085 to A-117 | Windfarm | 0 | 43861 |  | 36 | 43868 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting131820200124-4Operator - Principle - After Jan 10221650 | Corbiere and Sons Contracting131820200124-4Operator - Principle - After Jan 10221650Inv#009 | [5 empty] | 1 | 1650 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1318 | 20200124-4 | 53510111 | Access | 0 | Labourer - General - After Jan 10 | 60 | 11 | HR |  |  | 60 | 0 | 660 | 85.8 | 745.8 | 2020-01-24 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moves; Graders clearing up access roadsy | 1 | A-085 to A-117 | Windfarm | 0 | 43861 |  | 36 | 43868 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting131820200124-4Labourer - General - After Jan 1011660 | Corbiere and Sons Contracting131820200124-4Labourer - General - After Jan 1011660Inv#009 | [5 empty] | 1 | 660 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1319 | 20200124-5 | 53520104 | Clearing | 0 | Chainsaw and consumables- After Jan 10 | 60 | 3 | unit/man/day | 0 | 0 |  |  | 180 | 23.4 | 203.4 | 2020-01-24 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling from A096; | 1 | A-085 to A-117 | Windfarm | 0 | 43861 |  | 36 | 43868 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting131920200124-5Chainsaw and consumables- After Jan 103180 | Corbiere and Sons Contracting131920200124-5Chainsaw and consumables- After Jan 103180Inv#009 |  |  | WF1-Handfalling |  |  | 1 | 180 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1319 | 20200124-5 | 53520104 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-01-24 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling from A096; | 1 | A-085 to A-117 | Windfarm | 0 | 43861 |  | 36 | 43868 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting131920200124-5Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting131920200124-5Light Truck - Pick up- After Jan 102487.5Inv#009 |  |  | WF1-Handfalling |  |  | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1319 | 20200124-5 | 53520104 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2020-01-24 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling from A096; | 1 | A-085 to A-117 | Windfarm | 0 | 43861 |  | 36 | 43868 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting131920200124-5Foreman121140 | Corbiere and Sons Contracting131920200124-5Foreman121140Inv#009 |  |  | WF1-Handfalling |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1319 | 20200124-5 | 53520104 | Clearing | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2020-01-24 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling from A096; | 1 | A-085 to A-117 | Windfarm | 0 | 43861 |  | 36 | 43868 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting131920200124-5L.O.A.4840 | Corbiere and Sons Contracting131920200124-5L.O.A.4840Inv#009 |  |  | WF1-Handfalling |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1319 | 20200124-5 | 53520104 | Clearing | 0 | Labourer - Specialized - After Jan 10 | 70 | 33 | HR |  |  | 70 | 0 | 2310 | 300.3 | 2610.3 | 2020-01-24 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling from A096; | 1 | A-085 to A-117 | Windfarm | 0 | 43861 |  | 36 | 43868 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting131920200124-5Labourer - Specialized - After Jan 10332310 | Corbiere and Sons Contracting131920200124-5Labourer - Specialized - After Jan 10332310Inv#009 |  |  | WF1-Handfalling |  |  | 1 | 2310 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1320 | 20200124-6 | 53520104 | Clearing | 0 | Chainsaw and consumables- After Jan 10 | 60 | 3 | unit/man/day | 0 | 0 |  |  | 180 | 23.4 | 203.4 | 2020-01-24 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling from A125; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43861 |  | 36 | 43868 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting132020200124-6Chainsaw and consumables- After Jan 103180 | Corbiere and Sons Contracting132020200124-6Chainsaw and consumables- After Jan 103180Inv#009 |  |  | WF1-Handfalling |  |  | 1 | 180 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1320 | 20200124-6 | 53520104 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2020-01-24 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling from A125; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43861 |  | 36 | 43868 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting132020200124-6Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting132020200124-6Light Truck - Pick up- After Jan 103731.25Inv#009 |  |  | WF1-Handfalling |  |  | 1 | 731.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1320 | 20200124-6 | 53520104 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2020-01-24 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling from A125; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43861 |  | 36 | 43868 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting132020200124-6Foreman121140 | Corbiere and Sons Contracting132020200124-6Foreman121140Inv#009 |  |  | WF1-Handfalling |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1320 | 20200124-6 | 53520104 | Clearing | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2020-01-24 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling from A125; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43861 |  | 36 | 43868 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting132020200124-6L.O.A.4840 | Corbiere and Sons Contracting132020200124-6L.O.A.4840Inv#009 |  |  | WF1-Handfalling |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1320 | 20200124-6 | 53520104 | Clearing | 0 | Labourer - Specialized - After Jan 10 | 70 | 33 | HR |  |  | 70 | 0 | 2310 | 300.3 | 2610.3 | 2020-01-24 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling from A125; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43861 |  | 36 | 43868 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting132020200124-6Labourer - Specialized - After Jan 10332310 | Corbiere and Sons Contracting132020200124-6Labourer - Specialized - After Jan 10332310Inv#009 |  |  | WF1-Handfalling |  |  | 1 | 2310 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1321 | 20200124-7 | 53510111 | Access | 0 | Dozer - D5 or equal- After Jan 10 | 80.93 | 9 | Dynamic | 60.7 | 0 |  |  | 728.37 | 94.6881 | 823.0581 | 2020-01-24 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Road Access and maintenance complete to A127; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43861 |  | 36 | 43868 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting132120200124-7Dozer - D5 or equal- After Jan 109728.37 | Corbiere and Sons Contracting132120200124-7Dozer - D5 or equal- After Jan 109728.37Inv#009 | [5 empty] | 1 | 728.37 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1321 | 20200124-7 | 53510106 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2020-01-24 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Road Access and maintenance complete to A127; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43861 |  | 36 | 43868 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting132120200124-7Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting132120200124-7Excavator - 36 ton- After Jan 1091322.64Inv#009 |  | WF1-Access | WF1-Access |  | 0 | 1 | 1322.64 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1321 | 20200124-7 | 53510106 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-01-24 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Road Access and maintenance complete to A127; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43861 |  | 36 | 43868 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting132120200124-7Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting132120200124-7Light Truck - Pick up- After Jan 102487.5Inv#009 |  | WF1-Access | WF1-Access |  | 0 | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1321 | 20200124-7 | 53510111 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-01-24 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Road Access and maintenance complete to A127; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43861 |  | 36 | 43868 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting132120200124-7Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting132120200124-7Light Truck - Pick up- After Jan 101243.75Inv#009 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1321 | 20200124-7 | 53510106 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2020-01-24 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Road Access and maintenance complete to A127; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43861 |  | 36 | 43868 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting132120200124-7Foreman121140 | Corbiere and Sons Contracting132120200124-7Foreman121140Inv#009 |  | WF1-Access | WF1-Access |  | 0 | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1321 | 20200124-7 | 53510106 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2020-01-24 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Road Access and maintenance complete to A127; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43861 |  | 36 | 43868 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting132120200124-7L.O.A.3630 | Corbiere and Sons Contracting132120200124-7L.O.A.3630Inv#009 |  | WF1-Access | WF1-Access |  | 0 | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1321 | 20200124-7 | 53510111 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-01-24 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Road Access and maintenance complete to A127; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43861 |  | 36 | 43868 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting132120200124-7L.O.A.1210 | Corbiere and Sons Contracting132120200124-7L.O.A.1210Inv#009 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1321 | 20200124-7 | 53510106 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2020-01-24 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Road Access and maintenance complete to A127; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43861 |  | 36 | 43868 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting132120200124-7Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting132120200124-7Operator - Principle - After Jan 1011825Inv#009 |  | WF1-Access | WF1-Access |  | 0 | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1321 | 20200124-7 | 53510111 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2020-01-24 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Road Access and maintenance complete to A127; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43861 |  | 36 | 43868 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting132120200124-7Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting132120200124-7Operator - Principle - After Jan 1011825Inv#009 |  | WF1-Access |  |  | 0 | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1321 | 20200124-7 | 53510106 | Access | 0 | Labourer - General - After Jan 10 | 60 | 5 | HR |  |  | 60 | 0 | 300 | 39 | 339 | 2020-01-24 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Road Access and maintenance complete to A127; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43861 |  | 36 | 43868 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting132120200124-7Labourer - General - After Jan 105300 | Corbiere and Sons Contracting132120200124-7Labourer - General - After Jan 105300Inv#009 |  | WF1-Access | WF1-Access |  | 0 | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1323 | 20200124-9 | 53510211 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 9 | Dynamic | 98.61 | 0 |  |  | 1183.32 | 153.8316 | 1337.1516 | 2020-01-24 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Widening and plowing road at B022-B024; | 1 | B018-B029 | Black Sturgeon Road | 0 | 43861 |  | 36 | 43868 | [5 empty] | Mike Lecocq | 02 | Corbiere and Sons Contracting132320200124-9Dozer D6 or equal- After Jan 1091183.32 | Corbiere and Sons Contracting132320200124-9Dozer D6 or equal- After Jan 1091183.32Inv#009 | [5 empty] | 1 | 1183.32 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1323 | 20200124-9 | 53510211 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-01-24 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Widening and plowing road at B022-B024; | 1 | B018-B029 | Black Sturgeon Road | 0 | 43861 |  | 36 | 43868 | [5 empty] | Mike Lecocq | 02 | Corbiere and Sons Contracting132320200124-9L.O.A.2420 | Corbiere and Sons Contracting132320200124-9L.O.A.2420Inv#009 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1323 | 20200124-9 | 53510211 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 16 | HR |  |  | 75 | 0 | 1200 | 156 | 1356 | 2020-01-24 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Widening and plowing road at B022-B024; | 1 | B018-B029 | Black Sturgeon Road | 0 | 43861 |  | 36 | 43868 | [5 empty] | Mike Lecocq | 02 | Corbiere and Sons Contracting132320200124-9Operator - Principle - After Jan 10161200 | Corbiere and Sons Contracting132320200124-9Operator - Principle - After Jan 10161200Inv#009 | [5 empty] | 1 | 1200 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1302 | 20200125-10 | 53510211 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 3 | Dynamic | 98.61 | 0 |  |  | 394.44 | 51.2772 | 445.7172 | 2020-01-25 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Walked out D6 to be floated | 2 |  | Black Sturgeon | 0 | 43861 |  | 36 | 43864 | [5 empty] | Mike Lecocq | 02 | Corbiere and Sons Contracting130220200125-10Dozer D6 or equal- After Jan 103394.44 | Corbiere and Sons Contracting130220200125-10Dozer D6 or equal- After Jan 103394.44Inv#007-R01 | [5 empty] | 1 | 394.44 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1302 | 20200125-10 | 53510211 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-01-25 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Walked out D6 to be floated | 2 |  | Black Sturgeon | 0 | 43861 |  | 36 | 43864 | [5 empty] | Mike Lecocq | 02 | Corbiere and Sons Contracting130220200125-10L.O.A.1210 | Corbiere and Sons Contracting130220200125-10L.O.A.1210Inv#007-R01 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1302 | 20200125-10 | 53510211 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 4 | HR |  |  | 75 | 0 | 300 | 39 | 339 | 2020-01-25 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Walked out D6 to be floated | 2 |  | Black Sturgeon | 0 | 43861 |  | 36 | 43864 | [5 empty] | Mike Lecocq | 02 | Corbiere and Sons Contracting130220200125-10Operator - Principle - After Jan 104300 | Corbiere and Sons Contracting130220200125-10Operator - Principle - After Jan 104300Inv#007-R01 | [5 empty] | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1303 | 20200125-11 | 53510611 | Access | 0 | Loader JD 524 to 624 or equal | 99 | 5 | HR | 74.25 | 0 |  |  | 495 | 64.35 | 559.35 | 2020-01-25 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Clearing Access into A186; | 6 |  | Del Lake | 0 | 43861 |  | 40 | 43890 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting130320200125-11Loader JD 524 to 624 or equal5495 | Corbiere and Sons Contracting130320200125-11Loader JD 524 to 624 or equal5495Inv#009 | [5 empty] | 1 | 495 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1303 | 20200125-11 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-01-25 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Clearing Access into A186; | 6 |  | Del Lake | 0 | 43861 |  | 40 | 43890 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting130320200125-11L.O.A.1210 | Corbiere and Sons Contracting130320200125-11L.O.A.1210Inv#009 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1303 | 20200125-11 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 75 | 0 | 450 | 58.5 | 508.5 | 2020-01-25 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Clearing Access into A186; | 6 |  | Del Lake | 0 | 43861 |  | 40 | 43890 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting130320200125-11Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting130320200125-11Operator - Principle - After Jan 106450Inv#009 | [5 empty] | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1305 | 20200125-13 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 3 | Dynamic | 95.24 | 0 |  |  | 380.94 | 49.5222 | 430.4622 | 2020-01-25 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Rd. into shoefly; Grader doing road maintenance; | 6 |  | Santoy Mountain | 0 | 43861 |  | 40 | 43890 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting130520200125-13Grader - Cat 12 to 14 or equal- After Jan 103380.94 | Corbiere and Sons Contracting130520200125-13Grader - Cat 12 to 14 or equal- After Jan 103380.94Inv#009 | [5 empty] | 1 | 380.94 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1305 | 20200125-13 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-01-25 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Rd. into shoefly; Grader doing road maintenance; | 6 |  | Santoy Mountain | 0 | 43861 |  | 40 | 43890 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting130520200125-13L.O.A.1210 | Corbiere and Sons Contracting130520200125-13L.O.A.1210Inv#009 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1305 | 20200125-13 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 75 | 0 | 450 | 58.5 | 508.5 | 2020-01-25 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Winter Rd. into shoefly; Grader doing road maintenance; | 6 |  | Santoy Mountain | 0 | 43861 |  | 40 | 43890 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting130520200125-13Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting130520200125-13Operator - Principle - After Jan 106450Inv#009 | [5 empty] | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1307 | 20200125-15 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 3 | Dynamic | 95.24 | 0 |  |  | 380.94 | 49.5222 | 430.4622 | 2020-01-25 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF | [6 empty] | Grader performing road maintenance | 6 |  | Santoy Lake | 0 | 43861 | [9 empty] | 06 | Corbiere and Sons Contracting130720200125-15Grader - Cat 12 to 14 or equal- After Jan 103380.94 | Corbiere and Sons Contracting130720200125-15Grader - Cat 12 to 14 or equal- After Jan 103380.94Inv#009 | [5 empty] | 1 | 380.94 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1307 | 20200125-15 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5 | HR |  |  | 75 | 0 | 375 | 48.75 | 423.75 | 2020-01-25 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF | [6 empty] | Grader performing road maintenance | 6 |  | Santoy Lake | 0 | 43861 | [9 empty] | 06 | Corbiere and Sons Contracting130720200125-15Operator - Principle - After Jan 105375 | Corbiere and Sons Contracting130720200125-15Operator - Principle - After Jan 105375Inv#009 | [5 empty] | 1 | 375 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1310 | 20200125-18-R1 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 0.68726 | DAY | 182.81 | 0 |  |  | 167.5201 | 21.7776 | 189.2977 | 2020-01-25 | 1 | Inv#009 | 43894 | 86 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 25 | Approved | INTERNAL Supervision for Terrace Bay Yard | 9024 | Project Supervision, Yard Maintenance and Orientations; Meeting requested at WF6 to go over plan; | 6 |  | Screiber Yard | 1 | 43868 |  | 40 | 43869 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting131020200125-18-R1Light Truck - Pick up- After Jan 100.6872618167.5201 | Corbiere and Sons Contracting131020200125-18-R1Light Truck - Pick up- After Jan 100.6872618167.5201Inv#009 | [5 empty] | 1 | 167.5201 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1310 | 20200125-18-R1 | 53510611 | Access | 0 | Superintendent | 105 | 3.2989 | HR |  |  | 105 | 0 | 346.3799 | 45.0294 | 391.4093 | 2020-01-25 | 1 | Inv#009 | 43894 | 86 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 25 | Approved | INTERNAL Supervision for Terrace Bay Yard | 9024 | Project Supervision, Yard Maintenance and Orientations; Meeting requested at WF6 to go over plan; | 6 |  | Screiber Yard | 1 | 43868 |  | 40 | 43869 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting131020200125-18-R1Superintendent3.2988565346.3799 | Corbiere and Sons Contracting131020200125-18-R1Superintendent3.2988565346.3799Inv#009 | [5 empty] | 1 | 346.3799 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1310 | 20200125-18-R1 | 53510611 | Access | 0 | Project Coordinator | 80 | 3.2989 | HR |  |  | 80 | 0 | 263.9085 | 34.3081 | 298.2166 | 2020-01-25 | 1 | Inv#009 | 43894 | 86 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 25 | Approved | INTERNAL Supervision for Terrace Bay Yard | 9024 | Project Supervision, Yard Maintenance and Orientations; Meeting requested at WF6 to go over plan; | 6 |  | Screiber Yard | 1 | 43868 |  | 40 | 43869 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting131020200125-18-R1Project Coordinator3.2988565263.9085 | Corbiere and Sons Contracting131020200125-18-R1Project Coordinator3.2988565263.9085Inv#009 | [5 empty] | 1 | 263.9085 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1310 | 20200125-18-R1 | 53510611 | Access | 0 | Foreman | 95 | 1.6494 | HR |  |  | 95 | 0 | 156.6957 | 20.3704 | 177.0661 | 2020-01-25 | 1 | Inv#009 | 43894 | 86 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 25 | Approved | INTERNAL Supervision for Terrace Bay Yard | 9024 | Project Supervision, Yard Maintenance and Orientations; Meeting requested at WF6 to go over plan; | 6 |  | Screiber Yard | 1 | 43868 |  | 40 | 43869 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting131020200125-18-R1Foreman1.6494282156.6957 | Corbiere and Sons Contracting131020200125-18-R1Foreman1.6494282156.6957Inv#009 | [5 empty] | 1 | 156.6957 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1310 | 20200125-18-R1 | 53510611 | Access | 0 | L.O.A. | 210 | 0.68726 | DAY |  |  |  | 0 | 144.325 | 18.7623 | 163.0873 | 2020-01-25 | 1 | Inv#009 | 43894 | 86 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 25 | Approved | INTERNAL Supervision for Terrace Bay Yard | 9024 | Project Supervision, Yard Maintenance and Orientations; Meeting requested at WF6 to go over plan; | 6 |  | Screiber Yard | 1 | 43868 |  | 40 | 43869 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting131020200125-18-R1L.O.A.0.6872618144.325 | Corbiere and Sons Contracting131020200125-18-R1L.O.A.0.6872618144.325Inv#009 | [5 empty] | 1 | 144.325 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1276 | 20200125-1-R1 | 53510106 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 0.63537 | DAY | 182.81 | 0 |  |  | 154.8706 | 20.1332 | 175.0038 | 2020-01-25 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43861 |  | 12 | 43868 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting127620200125-1-R1Light Truck - Pick up- After Jan 100.6353666154.8706 | Corbiere and Sons Contracting127620200125-1-R1Light Truck - Pick up- After Jan 100.6353666154.8706Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 154.8706 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1276 | 20200125-1-R1 | 53510111 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 0.27417 | DAY | 182.81 | 0 |  |  | 66.8285 | 8.6877 | 75.5162 | 2020-01-25 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43861 |  | 12 | 43868 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting127620200125-1-R1Light Truck - Pick up- After Jan 100.27416866.8285 | Corbiere and Sons Contracting127620200125-1-R1Light Truck - Pick up- After Jan 100.27416866.8285Inv#007-R01 | [5 empty] | 1 | 66.8285 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1276 | 20200125-1-R1 | 53520101 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 0.040311 | DAY | 182.81 | 0 |  |  | 9.8258 | 1.2774 | 11.1032 | 2020-01-25 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43861 |  | 12 | 43868 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting127620200125-1-R1Light Truck - Pick up- After Jan 100.04031089.8258 | Corbiere and Sons Contracting127620200125-1-R1Light Truck - Pick up- After Jan 100.04031089.8258Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 9.8258 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1276 | 20200125-1-R1 | 53520102 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 0.73586 | DAY | 182.81 | 0 |  |  | 179.3656 | 23.3175 | 202.6831 | 2020-01-25 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43861 |  | 12 | 43868 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting127620200125-1-R1Light Truck - Pick up- After Jan 100.735859179.3656 | Corbiere and Sons Contracting127620200125-1-R1Light Truck - Pick up- After Jan 100.735859179.3656Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 179.3656 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1276 | 20200125-1-R1 | 53520104 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 0.28577 | DAY | 182.81 | 0 |  |  | 69.6576 | 9.0555 | 78.7131 | 2020-01-25 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43861 |  | 12 | 43868 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting127620200125-1-R1Light Truck - Pick up- After Jan 100.285774769.6576 | Corbiere and Sons Contracting127620200125-1-R1Light Truck - Pick up- After Jan 100.285774769.6576Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 69.6576 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1276 | 20200125-1-R1 | 53510106 | Access | 0 | Project Manager | 110 | 2.5415 | HR |  |  | 110 | 0 | 279.5613 | 36.343 | 315.9043 | 2020-01-25 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43861 |  | 12 | 43868 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting127620200125-1-R1Project Manager2.5414663279.5613 | Corbiere and Sons Contracting127620200125-1-R1Project Manager2.5414663279.5613Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 279.5613 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1276 | 20200125-1-R1 | 53510111 | Access | 0 | Project Manager | 110 | 1.0967 | HR |  |  | 110 | 0 | 120.6339 | 15.6824 | 136.3163 | 2020-01-25 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43861 |  | 12 | 43868 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting127620200125-1-R1Project Manager1.0966721120.6339 | Corbiere and Sons Contracting127620200125-1-R1Project Manager1.0966721120.6339Inv#007-R01 | [5 empty] | 1 | 120.6339 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1276 | 20200125-1-R1 | 53520101 | Clearing | 0 | Project Manager | 110 | 0.16124 | HR |  |  | 110 | 0 | 17.7367 | 2.3058 | 20.0425 | 2020-01-25 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43861 |  | 12 | 43868 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting127620200125-1-R1Project Manager0.161243117.7367 | Corbiere and Sons Contracting127620200125-1-R1Project Manager0.161243117.7367Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 17.7367 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1276 | 20200125-1-R1 | 53520102 | Clearing | 0 | Project Manager | 110 | 2.9434 | HR |  |  | 110 | 0 | 323.7779 | 42.0911 | 365.869 | 2020-01-25 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43861 |  | 12 | 43868 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting127620200125-1-R1Project Manager2.9434358323.7779 | Corbiere and Sons Contracting127620200125-1-R1Project Manager2.9434358323.7779Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 323.7779 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1276 | 20200125-1-R1 | 53520104 | Clearing | 0 | Project Manager | 110 | 1.1431 | HR |  |  | 110 | 0 | 125.7408 | 16.3463 | 142.0871 | 2020-01-25 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43861 |  | 12 | 43868 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting127620200125-1-R1Project Manager1.1430986125.7408 | Corbiere and Sons Contracting127620200125-1-R1Project Manager1.1430986125.7408Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 125.7408 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1276 | 20200125-1-R1 | 53510106 | Access | 0 | Safety Advisor | 85 | 2.5415 | HR |  |  | 85 | 0 | 216.0246 | 28.0832 | 244.1078 | 2020-01-25 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43861 |  | 12 | 43868 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting127620200125-1-R1Safety Advisor2.5414663216.0246 | Corbiere and Sons Contracting127620200125-1-R1Safety Advisor2.5414663216.0246Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 216.0246 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1276 | 20200125-1-R1 | 53510111 | Access | 0 | Safety Advisor | 85 | 1.0967 | HR |  |  | 85 | 0 | 93.2171 | 12.1182 | 105.3353 | 2020-01-25 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43861 |  | 12 | 43868 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting127620200125-1-R1Safety Advisor1.096672193.2171 | Corbiere and Sons Contracting127620200125-1-R1Safety Advisor1.096672193.2171Inv#007-R01 | [5 empty] | 1 | 93.2171 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1276 | 20200125-1-R1 | 53520101 | Clearing | 0 | Safety Advisor | 85 | 0.16124 | HR |  |  | 85 | 0 | 13.7057 | 1.7817 | 15.4874 | 2020-01-25 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43861 |  | 12 | 43868 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting127620200125-1-R1Safety Advisor0.161243113.7057 | Corbiere and Sons Contracting127620200125-1-R1Safety Advisor0.161243113.7057Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 13.7057 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1276 | 20200125-1-R1 | 53520102 | Clearing | 0 | Safety Advisor | 85 | 2.9434 | HR |  |  | 85 | 0 | 250.192 | 32.525 | 282.717 | 2020-01-25 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43861 |  | 12 | 43868 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting127620200125-1-R1Safety Advisor2.9434358250.192 | Corbiere and Sons Contracting127620200125-1-R1Safety Advisor2.9434358250.192Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 250.192 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1276 | 20200125-1-R1 | 53520104 | Clearing | 0 | Safety Advisor | 85 | 1.1431 | HR |  |  | 85 | 0 | 97.1634 | 12.6312 | 109.7946 | 2020-01-25 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43861 |  | 12 | 43868 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting127620200125-1-R1Safety Advisor1.143098697.1634 | Corbiere and Sons Contracting127620200125-1-R1Safety Advisor1.143098697.1634Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 97.1634 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1276 | 20200125-1-R1 | 53510106 | Access | 0 | Site Administrator | 50 | 2.3297 | HR |  |  | 50 | 0 | 116.4839 | 15.1429 | 131.6268 | 2020-01-25 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43861 |  | 12 | 43868 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting127620200125-1-R1Site Administrator2.3296774116.4839 | Corbiere and Sons Contracting127620200125-1-R1Site Administrator2.3296774116.4839Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 116.4839 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1276 | 20200125-1-R1 | 53510111 | Access | 0 | Site Administrator | 50 | 1.0053 | HR |  |  | 50 | 0 | 50.2641 | 6.5343 | 56.7984 | 2020-01-25 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43861 |  | 12 | 43868 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting127620200125-1-R1Site Administrator1.005282850.2641 | Corbiere and Sons Contracting127620200125-1-R1Site Administrator1.005282850.2641Inv#007-R01 | [5 empty] | 1 | 50.2641 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1276 | 20200125-1-R1 | 53520101 | Clearing | 0 | Site Administrator | 50 | 0.14781 | HR |  |  | 50 | 0 | 7.3903 | 0.96074 | 8.351 | 2020-01-25 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43861 |  | 12 | 43868 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting127620200125-1-R1Site Administrator0.14780627.3903 | Corbiere and Sons Contracting127620200125-1-R1Site Administrator0.14780627.3903Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 7.3903 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1276 | 20200125-1-R1 | 53520102 | Clearing | 0 | Site Administrator | 50 | 2.6981 | HR |  |  | 50 | 0 | 134.9075 | 17.538 | 152.4455 | 2020-01-25 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43861 |  | 12 | 43868 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting127620200125-1-R1Site Administrator2.6981495134.9075 | Corbiere and Sons Contracting127620200125-1-R1Site Administrator2.6981495134.9075Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 134.9075 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1276 | 20200125-1-R1 | 53520104 | Clearing | 0 | Site Administrator | 50 | 1.0478 | HR |  |  | 50 | 0 | 52.392 | 6.811 | 59.203 | 2020-01-25 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43861 |  | 12 | 43868 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting127620200125-1-R1Site Administrator1.047840452.392 | Corbiere and Sons Contracting127620200125-1-R1Site Administrator1.047840452.392Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 52.392 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1276 | 20200125-1-R1 | 53510106 | Access | 0 | Project Controls | 70 | 2.5415 | HR |  |  | 70 | 0 | 177.9026 | 23.1273 | 201.0299 | 2020-01-25 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43861 |  | 12 | 43868 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting127620200125-1-R1Project Controls2.5414663177.9026 | Corbiere and Sons Contracting127620200125-1-R1Project Controls2.5414663177.9026Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 177.9026 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1276 | 20200125-1-R1 | 53510111 | Access | 0 | Project Controls | 70 | 1.0967 | HR |  |  | 70 | 0 | 76.767 | 9.9797 | 86.7467 | 2020-01-25 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43861 |  | 12 | 43868 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting127620200125-1-R1Project Controls1.096672176.767 | Corbiere and Sons Contracting127620200125-1-R1Project Controls1.096672176.767Inv#007-R01 | [5 empty] | 1 | 76.767 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1276 | 20200125-1-R1 | 53520101 | Clearing | 0 | Project Controls | 70 | 0.16124 | HR |  |  | 70 | 0 | 11.287 | 1.4673 | 12.7543 | 2020-01-25 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43861 |  | 12 | 43868 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting127620200125-1-R1Project Controls0.161243111.287 | Corbiere and Sons Contracting127620200125-1-R1Project Controls0.161243111.287Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 11.287 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1276 | 20200125-1-R1 | 53520102 | Clearing | 0 | Project Controls | 70 | 2.9434 | HR |  |  | 70 | 0 | 206.0405 | 26.7853 | 232.8258 | 2020-01-25 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43861 |  | 12 | 43868 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting127620200125-1-R1Project Controls2.9434358206.0405 | Corbiere and Sons Contracting127620200125-1-R1Project Controls2.9434358206.0405Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 206.0405 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1276 | 20200125-1-R1 | 53520104 | Clearing | 0 | Project Controls | 70 | 1.1431 | HR |  |  | 70 | 0 | 80.0169 | 10.4022 | 90.4191 | 2020-01-25 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43861 |  | 12 | 43868 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting127620200125-1-R1Project Controls1.143098680.0169 | Corbiere and Sons Contracting127620200125-1-R1Project Controls1.143098680.0169Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 80.0169 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1276 | 20200125-1-R1 | 53510106 | Access | 0 | L.O.A. | 210 | 0.84716 | DAY |  |  |  | 0 | 177.9026 | 23.1273 | 201.0299 | 2020-01-25 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43861 |  | 12 | 43868 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting127620200125-1-R1L.O.A.0.8471554177.9026 | Corbiere and Sons Contracting127620200125-1-R1L.O.A.0.8471554177.9026Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 177.9026 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1276 | 20200125-1-R1 | 53510111 | Access | 0 | L.O.A. | 210 | 0.36556 | DAY |  |  |  | 0 | 76.7671 | 9.9797 | 86.7468 | 2020-01-25 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43861 |  | 12 | 43868 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting127620200125-1-R1L.O.A.0.365557476.7671 | Corbiere and Sons Contracting127620200125-1-R1L.O.A.0.365557476.7671Inv#007-R01 | [5 empty] | 1 | 76.7671 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1276 | 20200125-1-R1 | 53520101 | Clearing | 0 | L.O.A. | 210 | 0.053748 | DAY |  |  |  | 0 | 11.287 | 1.4673 | 12.7543 | 2020-01-25 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43861 |  | 12 | 43868 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting127620200125-1-R1L.O.A.0.053747711.287 | Corbiere and Sons Contracting127620200125-1-R1L.O.A.0.053747711.287Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 11.287 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1276 | 20200125-1-R1 | 53520102 | Clearing | 0 | L.O.A. | 210 | 0.98115 | DAY |  |  |  | 0 | 206.0405 | 26.7853 | 232.8258 | 2020-01-25 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43861 |  | 12 | 43868 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting127620200125-1-R1L.O.A.0.9811453206.0405 | Corbiere and Sons Contracting127620200125-1-R1L.O.A.0.9811453206.0405Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 206.0405 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1276 | 20200125-1-R1 | 53520104 | Clearing | 0 | L.O.A. | 210 | 0.38103 | DAY |  |  |  | 0 | 80.0169 | 10.4022 | 90.4191 | 2020-01-25 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  | 18 | Approved | ROW INTERNAL - Corbiere Supervision LEMS | 9018 | Project Supervision | 1 |  |  | 1 | 43861 |  | 12 | 43868 | [5 empty] | Gord Bryan | 01 | Corbiere and Sons Contracting127620200125-1-R1L.O.A.0.381032980.0169 | Corbiere and Sons Contracting127620200125-1-R1L.O.A.0.381032980.0169Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 80.0169 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1277 | 20200125-2 | 53510106 | Access | 0 | Loader JD 524 to 624 or equal | 99 | 1.0589 | HR | 74.25 | 0 |  |  | 104.8355 | 13.6286 | 118.4641 | 2020-01-25 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance | 0 |  | Yard | 1 | 43861 |  | 36 | 43864 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting127720200125-2Loader JD 524 to 624 or equal1.0589443104.8355 | Corbiere and Sons Contracting127720200125-2Loader JD 524 to 624 or equal1.0589443104.8355Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 104.8355 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1277 | 20200125-2 | 53510111 | Access | 0 | Loader JD 524 to 624 or equal | 99 | 0.45695 | HR | 74.25 | 0 |  |  | 45.2377 | 5.8809 | 51.1186 | 2020-01-25 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance | 0 |  | Yard | 1 | 43861 |  | 36 | 43864 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting127720200125-2Loader JD 524 to 624 or equal0.456946745.2377 | Corbiere and Sons Contracting127720200125-2Loader JD 524 to 624 or equal0.456946745.2377Inv#007-R01 | [5 empty] | 1 | 45.2377 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1277 | 20200125-2 | 53520101 | Clearing | 0 | Loader JD 524 to 624 or equal | 99 | 0.067185 | HR | 74.25 | 0 |  |  | 6.6513 | 0.86467 | 7.516 | 2020-01-25 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance | 0 |  | Yard | 1 | 43861 |  | 36 | 43864 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting127720200125-2Loader JD 524 to 624 or equal0.06718466.6513 | Corbiere and Sons Contracting127720200125-2Loader JD 524 to 624 or equal0.06718466.6513Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 6.6513 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1277 | 20200125-2 | 53520102 | Clearing | 0 | Loader JD 524 to 624 or equal | 99 | 1.2264 | HR | 74.25 | 0 |  |  | 121.4167 | 15.7842 | 137.2009 | 2020-01-25 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance | 0 |  | Yard | 1 | 43861 |  | 36 | 43864 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting127720200125-2Loader JD 524 to 624 or equal1.2264316121.4167 | Corbiere and Sons Contracting127720200125-2Loader JD 524 to 624 or equal1.2264316121.4167Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 121.4167 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1277 | 20200125-2 | 53520104 | Clearing | 0 | Loader JD 524 to 624 or equal | 99 | 0.47629 | HR | 74.25 | 0 |  |  | 47.1528 | 6.1299 | 53.2827 | 2020-01-25 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance | 0 |  | Yard | 1 | 43861 |  | 36 | 43864 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting127720200125-2Loader JD 524 to 624 or equal0.476291147.1528 | Corbiere and Sons Contracting127720200125-2Loader JD 524 to 624 or equal0.476291147.1528Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 47.1528 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1277 | 20200125-2 | 53510106 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 0.21179 | DAY | 182.81 | 0 |  |  | 51.6235 | 6.7111 | 58.3346 | 2020-01-25 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance | 0 |  | Yard | 1 | 43861 |  | 36 | 43864 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting127720200125-2Light Truck - Pick up- After Jan 100.211788951.6235 | Corbiere and Sons Contracting127720200125-2Light Truck - Pick up- After Jan 100.211788951.6235Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 51.6235 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1277 | 20200125-2 | 53510111 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 0.091389 | DAY | 182.81 | 0 |  |  | 22.2761 | 2.8959 | 25.172 | 2020-01-25 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance | 0 |  | Yard | 1 | 43861 |  | 36 | 43864 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting127720200125-2Light Truck - Pick up- After Jan 100.091389322.2761 | Corbiere and Sons Contracting127720200125-2Light Truck - Pick up- After Jan 100.091389322.2761Inv#007-R01 | [5 empty] | 1 | 22.2761 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1277 | 20200125-2 | 53520101 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 0.013437 | DAY | 182.81 | 0 |  |  | 3.2752 | 0.42578 | 3.701 | 2020-01-25 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance | 0 |  | Yard | 1 | 43861 |  | 36 | 43864 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting127720200125-2Light Truck - Pick up- After Jan 100.01343693.2752 | Corbiere and Sons Contracting127720200125-2Light Truck - Pick up- After Jan 100.01343693.2752Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 3.2752 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1277 | 20200125-2 | 53520102 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 0.24529 | DAY | 182.81 | 0 |  |  | 59.7885 | 7.7725 | 67.561 | 2020-01-25 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance | 0 |  | Yard | 1 | 43861 |  | 36 | 43864 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting127720200125-2Light Truck - Pick up- After Jan 100.245286359.7885 | Corbiere and Sons Contracting127720200125-2Light Truck - Pick up- After Jan 100.245286359.7885Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 59.7885 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1277 | 20200125-2 | 53520104 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 0.095258 | DAY | 182.81 | 0 |  |  | 23.2192 | 3.0185 | 26.2377 | 2020-01-25 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance | 0 |  | Yard | 1 | 43861 |  | 36 | 43864 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting127720200125-2Light Truck - Pick up- After Jan 100.095258223.2192 | Corbiere and Sons Contracting127720200125-2Light Truck - Pick up- After Jan 100.095258223.2192Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 23.2192 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1277 | 20200125-2 | 53510106 | Access | 0 | Operator - Apprentice | 60 | 2.1179 | HR |  |  | 60 | 0 | 127.0733 | 16.5195 | 143.5928 | 2020-01-25 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance | 0 |  | Yard | 1 | 43861 |  | 36 | 43864 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting127720200125-2Operator - Apprentice2.1178886127.0733 | Corbiere and Sons Contracting127720200125-2Operator - Apprentice2.1178886127.0733Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 127.0733 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1277 | 20200125-2 | 53510111 | Access | 0 | Operator - Apprentice | 60 | 0.91389 | HR |  |  | 60 | 0 | 54.8336 | 7.1284 | 61.962 | 2020-01-25 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance | 0 |  | Yard | 1 | 43861 |  | 36 | 43864 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting127720200125-2Operator - Apprentice0.913893454.8336 | Corbiere and Sons Contracting127720200125-2Operator - Apprentice0.913893454.8336Inv#007-R01 | [5 empty] | 1 | 54.8336 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1277 | 20200125-2 | 53520101 | Clearing | 0 | Operator - Apprentice | 60 | 0.13437 | HR |  |  | 60 | 0 | 8.0622 | 1.0481 | 9.1103 | 2020-01-25 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance | 0 |  | Yard | 1 | 43861 |  | 36 | 43864 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting127720200125-2Operator - Apprentice0.13436938.0622 | Corbiere and Sons Contracting127720200125-2Operator - Apprentice0.13436938.0622Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 8.0622 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1277 | 20200125-2 | 53520102 | Clearing | 0 | Operator - Apprentice | 60 | 2.4529 | HR |  |  | 60 | 0 | 147.1718 | 19.1323 | 166.3041 | 2020-01-25 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance | 0 |  | Yard | 1 | 43861 |  | 36 | 43864 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting127720200125-2Operator - Apprentice2.4528632147.1718 | Corbiere and Sons Contracting127720200125-2Operator - Apprentice2.4528632147.1718Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 147.1718 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1277 | 20200125-2 | 53520104 | Clearing | 0 | Operator - Apprentice | 60 | 0.95258 | HR |  |  | 60 | 0 | 57.1549 | 7.4301 | 64.585 | 2020-01-25 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 1 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | General Yard Maintenance | 0 |  | Yard | 1 | 43861 |  | 36 | 43864 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting127720200125-2Operator - Apprentice0.952582257.1549 | Corbiere and Sons Contracting127720200125-2Operator - Apprentice0.952582257.1549Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 57.1549 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1388 | 20200125-20 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 0.13745 | DAY | 182.81 | 0 |  |  | 33.504 | 4.3555 | 37.8595 | 2020-01-25 | 1 | Inv#009 | 43894 | 86 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 26 | Approved | ROW INTERNAL - Corbiere Yard Maintenance LEM's Terrace Bay | 9025 | Yard Maintenance and Orientations | 6 |  | Schrieber Yard | 1 | 43868 |  | 40 | 43869 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting138820200125-20Light Truck - Pick up- After Jan 100.137452433.504 | Corbiere and Sons Contracting138820200125-20Light Truck - Pick up- After Jan 100.137452433.504Inv#009 | [5 empty] | 1 | 33.504 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1388 | 20200125-20 | 53510611 | Access | 0 | L.O.A. | 210 | 0.41236 | DAY |  |  |  | 0 | 86.595 | 11.2574 | 97.8524 | 2020-01-25 | 1 | Inv#009 | 43894 | 86 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 26 | Approved | ROW INTERNAL - Corbiere Yard Maintenance LEM's Terrace Bay | 9025 | Yard Maintenance and Orientations | 6 |  | Schrieber Yard | 1 | 43868 |  | 40 | 43869 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting138820200125-20L.O.A.0.412357186.595 | Corbiere and Sons Contracting138820200125-20L.O.A.0.412357186.595Inv#009 | [5 empty] | 1 | 86.595 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1388 | 20200125-20 | 53510611 | Access | 0 | Labourer - Specialized - After Jan 10 | 70 | 0.68726 | HR |  |  | 70 | 0 | 48.1083 | 6.2541 | 54.3624 | 2020-01-25 | 1 | Inv#009 | 43894 | 86 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 26 | Approved | ROW INTERNAL - Corbiere Yard Maintenance LEM's Terrace Bay | 9025 | Yard Maintenance and Orientations | 6 |  | Schrieber Yard | 1 | 43868 |  | 40 | 43869 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting138820200125-20Labourer - Specialized - After Jan 100.687261848.1083 | Corbiere and Sons Contracting138820200125-20Labourer - Specialized - After Jan 100.687261848.1083Inv#009 | [5 empty] | 1 | 48.1083 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1388 | 20200125-20 | 53510611 | Access | 0 | Labourer - General - After Jan 10 | 60 | 2.1992 | HR |  |  | 60 | 0 | 131.9543 | 17.1541 | 149.1084 | 2020-01-25 | 1 | Inv#009 | 43894 | 86 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 26 | Approved | ROW INTERNAL - Corbiere Yard Maintenance LEM's Terrace Bay | 9025 | Yard Maintenance and Orientations | 6 |  | Schrieber Yard | 1 | 43868 |  | 40 | 43869 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting138820200125-20Labourer - General - After Jan 102.1992376131.9543 | Corbiere and Sons Contracting138820200125-20Labourer - General - After Jan 102.1992376131.9543Inv#009 | [5 empty] | 1 | 131.9543 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1278 | 20200125-3-R1 | 53520104 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-01-25 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Foreman snowshoed work paths in preperation of handfelling at this location; | 1 | A-036 to A-054 | Beck Road | 0 | 43861 |  | 40 | 43931 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting127820200125-3-R1Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting127820200125-3-R1Light Truck - Pick up- After Jan 101243.75Inv#022 |  |  | WF1-Handfalling |  |  | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1278 | 20200125-3-R1 | 53520104 | Clearing | 0 | Foreman | 95 | 7 | HR |  |  | 95 | 0 | 665 | 86.45 | 751.45 | 2020-01-25 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Foreman snowshoed work paths in preperation of handfelling at this location; | 1 | A-036 to A-054 | Beck Road | 0 | 43861 |  | 40 | 43931 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting127820200125-3-R1Foreman7665 | Corbiere and Sons Contracting127820200125-3-R1Foreman7665Inv#022 |  |  | WF1-Handfalling |  |  | 1 | 665 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1278 | 20200125-3-R1 | 53520104 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-01-25 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Foreman snowshoed work paths in preperation of handfelling at this location; | 1 | A-036 to A-054 | Beck Road | 0 | 43861 |  | 40 | 43931 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting127820200125-3-R1L.O.A.1210 | Corbiere and Sons Contracting127820200125-3-R1L.O.A.1210Inv#022 |  |  | WF1-Handfalling |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1282 | 20200125-6 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 18 | HR | 417.6 | 0 |  |  | 10022.4 | 1302.912 | 11325.312 | 2020-01-25 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grinding of material at A061 and at A079; | 1 | A-055 to A-084 | Eldorado | 0 | 43861 |  | 36 | 43864 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting128220200125-6Grinder - 4710 Peterson or equal1810022.4 | Corbiere and Sons Contracting128220200125-6Grinder - 4710 Peterson or equal1810022.4Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 10022.4 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1282 | 20200125-6 | 53520102 | Clearing | 0 | Log Loader | 153 | 18 | HR | 114.75 | 0 |  |  | 2754 | 358.02 | 3112.02 | 2020-01-25 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grinding of material at A061 and at A079; | 1 | A-055 to A-084 | Eldorado | 0 | 43861 |  | 36 | 43864 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting128220200125-6Log Loader182754 | Corbiere and Sons Contracting128220200125-6Log Loader182754Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2754 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1282 | 20200125-6 | 53520102 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-01-25 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grinding of material at A061 and at A079; | 1 | A-055 to A-084 | Eldorado | 0 | 43861 |  | 36 | 43864 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting128220200125-6Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting128220200125-6Light Truck - Pick up- After Jan 102487.5Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1282 | 20200125-6 | 53520102 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-01-25 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grinding of material at A061 and at A079; | 1 | A-055 to A-084 | Eldorado | 0 | 43861 |  | 36 | 43864 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting128220200125-6L.O.A.2420 | Corbiere and Sons Contracting128220200125-6L.O.A.2420Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1282 | 20200125-6 | 53520102 | Clearing | 0 | Operator - Principle - After Jan 10 | 75 | 22 | HR |  |  | 75 | 0 | 1650 | 214.5 | 1864.5 | 2020-01-25 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grinding of material at A061 and at A079; | 1 | A-055 to A-084 | Eldorado | 0 | 43861 |  | 36 | 43864 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting128220200125-6Operator - Principle - After Jan 10221650 | Corbiere and Sons Contracting128220200125-6Operator - Principle - After Jan 10221650Inv#007-R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1650 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1299 | 20200125-7 | 53510111 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 18 | Dynamic | 95.24 | 0 |  |  | 2285.64 | 297.1332 | 2582.7732 | 2020-01-25 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Graders working across all access roads where necessary; | 1 | A-085 to A-117 | Windfarm | 0 | 43861 |  | 36 | 43864 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting129920200125-7Grader - Cat 12 to 14 or equal- After Jan 10182285.64 | Corbiere and Sons Contracting129920200125-7Grader - Cat 12 to 14 or equal- After Jan 10182285.64Inv#007-R01 | [5 empty] | 1 | 2285.64 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1299 | 20200125-7 | 53510111 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-01-25 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Graders working across all access roads where necessary; | 1 | A-085 to A-117 | Windfarm | 0 | 43861 |  | 36 | 43864 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting129920200125-7Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting129920200125-7Light Truck - Pick up- After Jan 102487.5Inv#007-R01 | [5 empty] | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1299 | 20200125-7 | 53510111 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2020-01-25 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Graders working across all access roads where necessary; | 1 | A-085 to A-117 | Windfarm | 0 | 43861 |  | 36 | 43864 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting129920200125-7L.O.A.3630 | Corbiere and Sons Contracting129920200125-7L.O.A.3630Inv#007-R01 | [5 empty] | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1299 | 20200125-7 | 53510111 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2020-01-25 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Graders working across all access roads where necessary; | 1 | A-085 to A-117 | Windfarm | 0 | 43861 |  | 36 | 43864 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting129920200125-7Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting129920200125-7Operator - Principle - After Jan 1011825Inv#007-R01 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1299 | 20200125-7 | 53510111 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2020-01-25 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Graders working across all access roads where necessary; | 1 | A-085 to A-117 | Windfarm | 0 | 43861 |  | 36 | 43864 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting129920200125-7Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting129920200125-7Operator - Principle - After Jan 1011825Inv#007-R01 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1299 | 20200125-7 | 53510111 | Access | 0 | Labourer - General - After Jan 10 | 60 | 11 | HR |  |  | 60 | 0 | 660 | 85.8 | 745.8 | 2020-01-25 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Graders working across all access roads where necessary; | 1 | A-085 to A-117 | Windfarm | 0 | 43861 |  | 36 | 43864 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting129920200125-7Labourer - General - After Jan 1011660 | Corbiere and Sons Contracting129920200125-7Labourer - General - After Jan 1011660Inv#007-R01 | [5 empty] | 1 | 660 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1300 | 20200125-8 | 53520104 | Clearing | 0 | Chainsaw and consumables- After Jan 10 | 60 | 3 | unit/man/day | 0 | 0 |  |  | 180 | 23.4 | 203.4 | 2020-01-25 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling from A125; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43861 |  | 36 | 43864 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting130020200125-8Chainsaw and consumables- After Jan 103180 | Corbiere and Sons Contracting130020200125-8Chainsaw and consumables- After Jan 103180Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 180 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1300 | 20200125-8 | 53520104 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2020-01-25 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling from A125; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43861 |  | 36 | 43864 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting130020200125-8Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting130020200125-8Light Truck - Pick up- After Jan 103731.25Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 731.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1300 | 20200125-8 | 53520104 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2020-01-25 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling from A125; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43861 |  | 36 | 43864 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting130020200125-8Foreman121140 | Corbiere and Sons Contracting130020200125-8Foreman121140Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1300 | 20200125-8 | 53520101 | Clearing | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2020-01-25 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling from A125; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43861 |  | 36 | 43864 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting130020200125-8L.O.A.4840 | Corbiere and Sons Contracting130020200125-8L.O.A.4840Inv#007-R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1300 | 20200125-8 | 53520104 | Clearing | 0 | Labourer - Specialized - After Jan 10 | 70 | 33 | HR |  |  | 70 | 0 | 2310 | 300.3 | 2610.3 | 2020-01-25 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling from A125; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43861 |  | 36 | 43864 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting130020200125-8Labourer - Specialized - After Jan 10332310 | Corbiere and Sons Contracting130020200125-8Labourer - Specialized - After Jan 10332310Inv#007-R01 |  |  | WF1-Handfalling |  |  | 1 | 2310 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1301 | 20200125-9 | 53510106 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 103.84 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2020-01-25 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Rd. Building from A118-A122 and from A125-A127; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43861 |  | 36 | 43864 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting130120200125-9Excavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting130120200125-9Excavator - 30 ton- After Jan 1091246.05Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 1246.05 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1301 | 20200125-9 | 53510106 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2020-01-25 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Rd. Building from A118-A122 and from A125-A127; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43861 |  | 36 | 43864 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting130120200125-9Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting130120200125-9Excavator - 36 ton- After Jan 1091322.64Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 1322.64 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1301 | 20200125-9 | 53510106 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2020-01-25 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Rd. Building from A118-A122 and from A125-A127; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43861 |  | 36 | 43864 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting130120200125-9Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting130120200125-9Excavator Thumb - 30 - 50 ton- After Jan 109109.89Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 109.89 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1301 | 20200125-9 | 53510106 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2020-01-25 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Rd. Building from A118-A122 and from A125-A127; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43861 |  | 36 | 43864 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting130120200125-9Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting130120200125-9Light Truck - Pick up- After Jan 103731.25Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 731.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1301 | 20200125-9 | 53510106 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2020-01-25 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Rd. Building from A118-A122 and from A125-A127; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43861 |  | 36 | 43864 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting130120200125-9Foreman121140 | Corbiere and Sons Contracting130120200125-9Foreman121140Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1301 | 20200125-9 | 53510106 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2020-01-25 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Rd. Building from A118-A122 and from A125-A127; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43861 |  | 36 | 43864 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting130120200125-9L.O.A.4840 | Corbiere and Sons Contracting130120200125-9L.O.A.4840Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1301 | 20200125-9 | 53510106 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 22 | HR |  |  | 75 | 0 | 1650 | 214.5 | 1864.5 | 2020-01-25 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Rd. Building from A118-A122 and from A125-A127; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43861 |  | 36 | 43864 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting130120200125-9Operator - Principle - After Jan 10221650 | Corbiere and Sons Contracting130120200125-9Operator - Principle - After Jan 10221650Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 1650 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1301 | 20200125-9 | 53510106 | Access | 0 | Labourer - General - After Jan 10 | 60 | 11 | HR |  |  | 60 | 0 | 660 | 85.8 | 745.8 | 2020-01-25 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Rd. Building from A118-A122 and from A125-A127; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43861 |  | 36 | 43864 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting130120200125-9Labourer - General - After Jan 1011660 | Corbiere and Sons Contracting130120200125-9Labourer - General - After Jan 1011660Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 660 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1472 | 20200126-11 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 9 | Dynamic | 98.61 | 0 |  |  | 1183.32 | 153.8316 | 1337.1516 | 2020-01-26 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Clearing access with DZ; | 6 |  |  | 0 | 43862 |  | 40 | 43890 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting147220200126-11Dozer D6 or equal- After Jan 1091183.32 | Corbiere and Sons Contracting147220200126-11Dozer D6 or equal- After Jan 1091183.32Inv#009 | [5 empty] | 1 | 1183.32 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1472 | 20200126-11 | 53510611 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-01-26 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Clearing access with DZ; | 6 |  |  | 0 | 43862 |  | 40 | 43890 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting147220200126-11L.O.A.2420 | Corbiere and Sons Contracting147220200126-11L.O.A.2420Inv#009 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1472 | 20200126-11 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2020-01-26 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Clearing access with DZ; | 6 |  |  | 0 | 43862 |  | 40 | 43890 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting147220200126-11Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting147220200126-11Operator - Principle - After Jan 1011825Inv#009 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1474 | 20200126-13 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 4 | Dynamic | 95.24 | 0 |  |  | 507.92 | 66.0296 | 573.9496 | 2020-01-26 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance at Santoy Lake with Grader; | 6 | C129-C151 | Santoy Lake | 0 | 43862 |  | 40 | 43890 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting147420200126-13Grader - Cat 12 to 14 or equal- After Jan 104507.92 | Corbiere and Sons Contracting147420200126-13Grader - Cat 12 to 14 or equal- After Jan 104507.92Inv#009 | [5 empty] | 1 | 507.92 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1474 | 20200126-13 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-01-26 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance at Santoy Lake with Grader; | 6 | C129-C151 | Santoy Lake | 0 | 43862 |  | 40 | 43890 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting147420200126-13L.O.A.1210 | Corbiere and Sons Contracting147420200126-13L.O.A.1210Inv#009 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1474 | 20200126-13 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5 | HR |  |  | 75 | 0 | 375 | 48.75 | 423.75 | 2020-01-26 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance at Santoy Lake with Grader; | 6 | C129-C151 | Santoy Lake | 0 | 43862 |  | 40 | 43890 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting147420200126-13Operator - Principle - After Jan 105375 | Corbiere and Sons Contracting147420200126-13Operator - Principle - After Jan 105375Inv#009 | [5 empty] | 1 | 375 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1476 | 20200126-15 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 9 | Dynamic | 98.61 | 0 |  |  | 1183.32 | 153.8316 | 1337.1516 | 2020-01-26 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Clearing access into Del L West; | 6 |  | Del Lake | 0 | 43862 |  | 40 | 43890 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting147620200126-15Dozer D6 or equal- After Jan 1091183.32 | Corbiere and Sons Contracting147620200126-15Dozer D6 or equal- After Jan 1091183.32Inv#009 | [5 empty] | 1 | 1183.32 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1476 | 20200126-15 | 53510611 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 9 | Dynamic | 91.79 | 0 |  |  | 1101.51 | 143.1963 | 1244.7063 | 2020-01-26 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Clearing access into Del L West; | 6 |  | Del Lake | 0 | 43862 |  | 40 | 43890 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting147620200126-15Tractor Trailer - 60 Ton- After Jan 1091101.51 | Corbiere and Sons Contracting147620200126-15Tractor Trailer - 60 Ton- After Jan 1091101.51Inv#009 | [5 empty] | 1 | 1101.51 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1476 | 20200126-15 | 53510611 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-01-26 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Clearing access into Del L West; | 6 |  | Del Lake | 0 | 43862 |  | 40 | 43890 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting147620200126-15L.O.A.2420 | Corbiere and Sons Contracting147620200126-15L.O.A.2420Inv#009 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1476 | 20200126-15 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2020-01-26 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Clearing access into Del L West; | 6 |  | Del Lake | 0 | 43862 |  | 40 | 43890 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting147620200126-15Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting147620200126-15Operator - Principle - After Jan 1011825Inv#009 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1476 | 20200126-15 | 53510611 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 9 | HR |  |  | 70 | 0 | 630 | 81.9 | 711.9 | 2020-01-26 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Clearing access into Del L West; | 6 |  | Del Lake | 0 | 43862 |  | 40 | 43890 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting147620200126-15Operator - Intermdiate - After Jan 109630 | Corbiere and Sons Contracting147620200126-15Operator - Intermdiate - After Jan 109630Inv#009 | [5 empty] | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1477 | 20200126-16 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 2 | Dynamic | 98.61 | 0 |  |  | 262.96 | 34.1848 | 297.1448 | 2020-01-26 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Maintenance across Neys road; | 6 | C129-C236 | Ney's Road | 0 | 43862 |  | 17 | 43865 | [5 empty] | David Mercer | 06 | Corbiere and Sons Contracting147720200126-16Dozer D6 or equal- After Jan 102262.96 | Corbiere and Sons Contracting147720200126-16Dozer D6 or equal- After Jan 102262.96Inv#007-R01 | [5 empty] | 1 | 262.96 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1477 | 20200126-16 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 9 | Dynamic | 95.24 | 0 |  |  | 1142.82 | 148.5666 | 1291.3866 | 2020-01-26 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Maintenance across Neys road; | 6 | C129-C236 | Ney's Road | 0 | 43862 |  | 17 | 43865 | [5 empty] | David Mercer | 06 | Corbiere and Sons Contracting147720200126-16Grader - Cat 12 to 14 or equal- After Jan 1091142.82 | Corbiere and Sons Contracting147720200126-16Grader - Cat 12 to 14 or equal- After Jan 1091142.82Inv#007-R01 | [5 empty] | 1 | 1142.82 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1477 | 20200126-16 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2020-01-26 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Maintenance across Neys road; | 6 | C129-C236 | Ney's Road | 0 | 43862 |  | 17 | 43865 | [5 empty] | David Mercer | 06 | Corbiere and Sons Contracting147720200126-16Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting147720200126-16Operator - Principle - After Jan 1011825Inv#007-R01 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1478 | 20200126-17-R1 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 0.57018 | DAY | 182.81 | 0 |  |  | 138.9807 | 18.0675 | 157.0482 | 2020-01-26 | 1 | Inv#009 | 43894 | 86 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 25 | Approved | INTERNAL Supervision for Terrace Bay Yard | 9024 | Supervision and Yard Maintenance | 6 |  | Supervision/Yard | 1 | 43862 |  | 40 | 43869 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting147820200126-17-R1Light Truck - Pick up- After Jan 100.5701771138.9807 | Corbiere and Sons Contracting147820200126-17-R1Light Truck - Pick up- After Jan 100.5701771138.9807Inv#009 | [5 empty] | 1 | 138.9807 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1478 | 20200126-17-R1 | 53510611 | Access | 0 | Superintendent | 105 | 3.136 | HR |  |  | 105 | 0 | 329.2773 | 42.806 | 372.0833 | 2020-01-26 | 1 | Inv#009 | 43894 | 86 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 25 | Approved | INTERNAL Supervision for Terrace Bay Yard | 9024 | Supervision and Yard Maintenance | 6 |  | Supervision/Yard | 1 | 43862 |  | 40 | 43869 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting147820200126-17-R1Superintendent3.1359739329.2773 | Corbiere and Sons Contracting147820200126-17-R1Superintendent3.1359739329.2773Inv#009 | [5 empty] | 1 | 329.2773 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1478 | 20200126-17-R1 | 53510611 | Access | 0 | Project Coordinator | 80 | 3.136 | HR |  |  | 80 | 0 | 250.8779 | 32.6141 | 283.492 | 2020-01-26 | 1 | Inv#009 | 43894 | 86 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 25 | Approved | INTERNAL Supervision for Terrace Bay Yard | 9024 | Supervision and Yard Maintenance | 6 |  | Supervision/Yard | 1 | 43862 |  | 40 | 43869 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting147820200126-17-R1Project Coordinator3.1359739250.8779 | Corbiere and Sons Contracting147820200126-17-R1Project Coordinator3.1359739250.8779Inv#009 | [5 empty] | 1 | 250.8779 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1478 | 20200126-17-R1 | 53510611 | Access | 0 | L.O.A. | 210 | 0.57018 | DAY |  |  |  | 0 | 119.7372 | 15.5658 | 135.303 | 2020-01-26 | 1 | Inv#009 | 43894 | 86 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 25 | Approved | INTERNAL Supervision for Terrace Bay Yard | 9024 | Supervision and Yard Maintenance | 6 |  | Supervision/Yard | 1 | 43862 |  | 40 | 43869 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting147820200126-17-R1L.O.A.0.5701771119.7372 | Corbiere and Sons Contracting147820200126-17-R1L.O.A.0.5701771119.7372Inv#009 | [5 empty] | 1 | 119.7372 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1389 | 20200126-19 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 0.28509 | DAY | 182.81 | 0 |  |  | 69.4903 | 9.0337 | 78.524 | 2020-01-26 | 1 | Inv#009 | 43894 | 86 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  | Deena to advise if new COR needed for Schreiber Yard Crew | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | Yard Maintenance | 6 |  | Schreiber Yard | 1 | 43868 |  | 40 | 43869 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting138920200126-19Light Truck - Pick up- After Jan 100.285088569.4903 | Corbiere and Sons Contracting138920200126-19Light Truck - Pick up- After Jan 100.285088569.4903Inv#009 | [5 empty] | 1 | 69.4903 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1389 | 20200126-19 | 53510611 | Access | 0 | L.O.A. | 210 | 0.28509 | DAY |  |  |  | 0 | 59.8686 | 7.7829 | 67.6515 | 2020-01-26 | 1 | Inv#009 | 43894 | 86 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  | Deena to advise if new COR needed for Schreiber Yard Crew | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | Yard Maintenance | 6 |  | Schreiber Yard | 1 | 43868 |  | 40 | 43869 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting138920200126-19L.O.A.0.285088559.8686 | Corbiere and Sons Contracting138920200126-19L.O.A.0.285088559.8686Inv#009 | [5 empty] | 1 | 59.8686 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1389 | 20200126-19 | 53510611 | Access | 0 | Labourer - General - After Jan 10 | 60 | 3.136 | HR |  |  | 60 | 0 | 188.1584 | 24.4606 | 212.619 | 2020-01-26 | 1 | Inv#009 | 43894 | 86 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  | Deena to advise if new COR needed for Schreiber Yard Crew | 17 | Approved | ROW INTERNAL - Corbiere Yard maintenance LEMs | 9017 | Yard Maintenance | 6 |  | Schreiber Yard | 1 | 43868 |  | 40 | 43869 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting138920200126-19Labourer - General - After Jan 103.1359739188.1584 | Corbiere and Sons Contracting138920200126-19Labourer - General - After Jan 103.1359739188.1584Inv#009 | [5 empty] | 1 | 188.1584 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1464 | 20200126-3 | 53510111 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 9 | Dynamic | 95.24 | 0 |  |  | 1142.82 | 148.5666 | 1291.3866 | 2020-01-26 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grading of access roads; Sander Truck working across all access roads; | 1 | A-055 to A-084 | Eldorado | 0 | 43862 |  | 36 | 43866 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting146420200126-3Grader - Cat 12 to 14 or equal- After Jan 1091142.82 | Corbiere and Sons Contracting146420200126-3Grader - Cat 12 to 14 or equal- After Jan 1091142.82Inv#009 | [5 empty] | 1 | 1142.82 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1464 | 20200126-3 | 53510111 | Access | 0 | Sander Truck - Forestry- After Jan 10 | 86.38 | 10 | Dynamic | 64.79 | 0 |  |  | 863.8 | 112.294 | 976.094 | 2020-01-26 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grading of access roads; Sander Truck working across all access roads; | 1 | A-055 to A-084 | Eldorado | 0 | 43862 |  | 36 | 43866 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting146420200126-3Sander Truck - Forestry- After Jan 1010863.8 | Corbiere and Sons Contracting146420200126-3Sander Truck - Forestry- After Jan 1010863.8Inv#009 | [5 empty] | 1 | 863.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1464 | 20200126-3 | 53510111 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-01-26 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grading of access roads; Sander Truck working across all access roads; | 1 | A-055 to A-084 | Eldorado | 0 | 43862 |  | 36 | 43866 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting146420200126-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting146420200126-3Light Truck - Pick up- After Jan 101243.75Inv#009 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1464 | 20200126-3 | 53510111 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2020-01-26 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grading of access roads; Sander Truck working across all access roads; | 1 | A-055 to A-084 | Eldorado | 0 | 43862 |  | 36 | 43866 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting146420200126-3L.O.A.3630 | Corbiere and Sons Contracting146420200126-3L.O.A.3630Inv#009 | [5 empty] | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1464 | 20200126-3 | 53510111 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2020-01-26 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grading of access roads; Sander Truck working across all access roads; | 1 | A-055 to A-084 | Eldorado | 0 | 43862 |  | 36 | 43866 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting146420200126-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting146420200126-3Operator - Principle - After Jan 1011825Inv#009 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1464 | 20200126-3 | 53510111 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 10 | HR |  |  | 70 | 0 | 700 | 91 | 791 | 2020-01-26 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grading of access roads; Sander Truck working across all access roads; | 1 | A-055 to A-084 | Eldorado | 0 | 43862 |  | 36 | 43866 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting146420200126-3Driver - AZ - After Jan 1010700 | Corbiere and Sons Contracting146420200126-3Driver - AZ - After Jan 1010700Inv#009 | [5 empty] | 1 | 700 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1464 | 20200126-3 | 53510111 | Access | 0 | Labourer - General - After Jan 10 | 60 | 5.5 | HR |  |  | 60 | 0 | 330 | 42.9 | 372.9 | 2020-01-26 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grading of access roads; Sander Truck working across all access roads; | 1 | A-055 to A-084 | Eldorado | 0 | 43862 |  | 36 | 43866 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting146420200126-3Labourer - General - After Jan 105.5330 | Corbiere and Sons Contracting146420200126-3Labourer - General - After Jan 105.5330Inv#009 | [5 empty] | 1 | 330 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1466 | 20200126-5 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 9 | HR | 417.6 | 0 |  |  | 5011.2 | 651.456 | 5662.656 | 2020-01-26 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grinding of Material at A085; | 1 | A-085 to A-117 | Windfarm | 0 | 43862 |  | 36 | 43866 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting146620200126-5Grinder - 4710 Peterson or equal95011.2 | Corbiere and Sons Contracting146620200126-5Grinder - 4710 Peterson or equal95011.2Inv#009 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 5011.2 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1466 | 20200126-5 | 53520102 | Clearing | 0 | Log Loader | 153 | 9 | HR | 114.75 | 0 |  |  | 1377 | 179.01 | 1556.01 | 2020-01-26 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grinding of Material at A085; | 1 | A-085 to A-117 | Windfarm | 0 | 43862 |  | 36 | 43866 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting146620200126-5Log Loader91377 | Corbiere and Sons Contracting146620200126-5Log Loader91377Inv#009 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1377 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1466 | 20200126-5 | 53520102 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-01-26 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grinding of Material at A085; | 1 | A-085 to A-117 | Windfarm | 0 | 43862 |  | 36 | 43866 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting146620200126-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting146620200126-5Light Truck - Pick up- After Jan 101243.75Inv#009 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1466 | 20200126-5 | 53520102 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-01-26 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grinding of Material at A085; | 1 | A-085 to A-117 | Windfarm | 0 | 43862 |  | 36 | 43866 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting146620200126-5L.O.A.1210 | Corbiere and Sons Contracting146620200126-5L.O.A.1210Inv#009 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1466 | 20200126-5 | 53520102 | Clearing | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2020-01-26 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grinding of Material at A085; | 1 | A-085 to A-117 | Windfarm | 0 | 43862 |  | 36 | 43866 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting146620200126-5Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting146620200126-5Operator - Principle - After Jan 1011825Inv#009 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1467 | 20200126-6 | 53510106 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 103.84 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2020-01-26 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Removing riprap from wetland; Repairing winter road from A122-A128; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43862 |  | 36 | 43866 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting146720200126-6Excavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting146720200126-6Excavator - 30 ton- After Jan 1091246.05Inv#009 |  | WF1-Access | WF1-Access |  | 0 | 1 | 1246.05 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1467 | 20200126-6 | 53510106 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2020-01-26 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Removing riprap from wetland; Repairing winter road from A122-A128; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43862 |  | 36 | 43866 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting146720200126-6Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting146720200126-6Excavator - 36 ton- After Jan 1091322.64Inv#009 |  | WF1-Access | WF1-Access |  | 0 | 1 | 1322.64 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1467 | 20200126-6 | 53510106 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2020-01-26 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Removing riprap from wetland; Repairing winter road from A122-A128; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43862 |  | 36 | 43866 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting146720200126-6Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting146720200126-6Excavator Thumb - 30 - 50 ton- After Jan 109109.89Inv#009 |  | WF1-Access | WF1-Access |  | 0 | 1 | 109.89 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1467 | 20200126-6 | 53510106 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2020-01-26 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Removing riprap from wetland; Repairing winter road from A122-A128; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43862 |  | 36 | 43866 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting146720200126-6Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting146720200126-6Light Truck - Pick up- After Jan 103731.25Inv#009 |  | WF1-Access | WF1-Access |  | 0 | 1 | 731.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1467 | 20200126-6 | 53510106 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2020-01-26 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Removing riprap from wetland; Repairing winter road from A122-A128; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43862 |  | 36 | 43866 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting146720200126-6Foreman121140 | Corbiere and Sons Contracting146720200126-6Foreman121140Inv#009 |  | WF1-Access | WF1-Access |  | 0 | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1467 | 20200126-6 | 53510106 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2020-01-26 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Removing riprap from wetland; Repairing winter road from A122-A128; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43862 |  | 36 | 43866 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting146720200126-6L.O.A.4840 | Corbiere and Sons Contracting146720200126-6L.O.A.4840Inv#009 |  | WF1-Access | WF1-Access |  | 0 | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1467 | 20200126-6 | 53510106 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 22 | HR |  |  | 75 | 0 | 1650 | 214.5 | 1864.5 | 2020-01-26 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Removing riprap from wetland; Repairing winter road from A122-A128; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43862 |  | 36 | 43866 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting146720200126-6Operator - Principle - After Jan 10221650 | Corbiere and Sons Contracting146720200126-6Operator - Principle - After Jan 10221650Inv#009 |  | WF1-Access | WF1-Access |  | 0 | 1 | 1650 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1467 | 20200126-6 | 53510106 | Access | 0 | Labourer - General - After Jan 10 | 60 | 11 | HR |  |  | 60 | 0 | 660 | 85.8 | 745.8 | 2020-01-26 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Removing riprap from wetland; Repairing winter road from A122-A128; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43862 |  | 36 | 43866 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting146720200126-6Labourer - General - After Jan 1011660 | Corbiere and Sons Contracting146720200126-6Labourer - General - After Jan 1011660Inv#009 |  | WF1-Access | WF1-Access |  | 0 | 1 | 660 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1468 | 20200126-7 | 53520104 | Clearing | 0 | Chainsaw and consumables- After Jan 10 | 60 | 2 | unit/man/day | 0 | 0 |  |  | 120 | 15.6 | 135.6 | 2020-01-26 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling at A125; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43862 |  | 36 | 43866 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting146820200126-7Chainsaw and consumables- After Jan 102120 | Corbiere and Sons Contracting146820200126-7Chainsaw and consumables- After Jan 102120Inv#009 |  |  | WF1-Handfalling |  |  | 1 | 120 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1468 | 20200126-7 | 53520104 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-01-26 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling at A125; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43862 |  | 36 | 43866 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting146820200126-7Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting146820200126-7Light Truck - Pick up- After Jan 102487.5Inv#009 |  |  | WF1-Handfalling |  |  | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1468 | 20200126-7 | 53520104 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-01-26 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling at A125; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43862 |  | 36 | 43866 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting146820200126-7L.O.A.2420 | Corbiere and Sons Contracting146820200126-7L.O.A.2420Inv#009 |  |  | WF1-Handfalling |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1468 | 20200126-7 | 53520104 | Clearing | 0 | Labourer - Specialized - After Jan 10 | 70 | 22 | HR |  |  | 70 | 0 | 1540 | 200.2 | 1740.2 | 2020-01-26 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling at A125; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43862 |  | 36 | 43866 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting146820200126-7Labourer - Specialized - After Jan 10221540 | Corbiere and Sons Contracting146820200126-7Labourer - Specialized - After Jan 10221540Inv#009 |  |  | WF1-Handfalling |  |  | 1 | 1540 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1469 | 20200126-8 | 53510106 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2020-01-26 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Rd. Building at A129 and B009-B010; | 0 | A128-B012 | Fish Hatchery | 0 | 43862 |  | 36 | 43866 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting146920200126-8Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting146920200126-8Excavator - 36 ton- After Jan 1091322.64Inv#009 |  | WF1-Access | WF1-Access |  | 0 | 1 | 1322.64 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1469 | 20200126-8 | 53510106 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2020-01-26 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Rd. Building at A129 and B009-B010; | 0 | A128-B012 | Fish Hatchery | 0 | 43862 |  | 36 | 43866 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting146920200126-8Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting146920200126-8Excavator - 36 ton- After Jan 1091322.64Inv#009 |  | WF1-Access | WF1-Access |  | 0 | 1 | 1322.64 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1469 | 20200126-8 | 53510106 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2020-01-26 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Rd. Building at A129 and B009-B010; | 0 | A128-B012 | Fish Hatchery | 0 | 43862 |  | 36 | 43866 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting146920200126-8Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting146920200126-8Excavator Thumb - 30 - 50 ton- After Jan 109109.89Inv#009 |  | WF1-Access | WF1-Access |  | 0 | 1 | 109.89 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1469 | 20200126-8 | 53510106 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-01-26 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Rd. Building at A129 and B009-B010; | 0 | A128-B012 | Fish Hatchery | 0 | 43862 |  | 36 | 43866 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting146920200126-8Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting146920200126-8Light Truck - Pick up- After Jan 101243.75Inv#009 |  | WF1-Access | WF1-Access |  | 0 | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1469 | 20200126-8 | 53510106 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-01-26 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Rd. Building at A129 and B009-B010; | 0 | A128-B012 | Fish Hatchery | 0 | 43862 |  | 36 | 43866 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting146920200126-8L.O.A.2420 | Corbiere and Sons Contracting146920200126-8L.O.A.2420Inv#009 |  | WF1-Access | WF1-Access |  | 0 | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1469 | 20200126-8 | 53510106 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 22 | HR |  |  | 75 | 0 | 1650 | 214.5 | 1864.5 | 2020-01-26 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Rd. Building at A129 and B009-B010; | 0 | A128-B012 | Fish Hatchery | 0 | 43862 |  | 36 | 43866 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting146920200126-8Operator - Principle - After Jan 10221650 | Corbiere and Sons Contracting146920200126-8Operator - Principle - After Jan 10221650Inv#009 |  | WF1-Access | WF1-Access |  | 0 | 1 | 1650 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1341 | 20200127-10 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 9 | Dynamic | 98.61 | 0 |  |  | 1183.32 | 153.8316 | 1337.1516 | 2020-01-27 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Clearing Access into Hwy 17 to allow triaxle in for Bridge Installation; | 6 | C129-C151 | Lake A | 0 | 43861 |  | 40 | 43869 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting134120200127-10Dozer D6 or equal- After Jan 1091183.32 | Corbiere and Sons Contracting134120200127-10Dozer D6 or equal- After Jan 1091183.32Inv#007-R01 | [5 empty] | 1 | 1183.32 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1341 | 20200127-10 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-01-27 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Clearing Access into Hwy 17 to allow triaxle in for Bridge Installation; | 6 | C129-C151 | Lake A | 0 | 43861 |  | 40 | 43869 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting134120200127-10L.O.A.1210 | Corbiere and Sons Contracting134120200127-10L.O.A.1210Inv#007-R01 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1341 | 20200127-10 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2020-01-27 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Clearing Access into Hwy 17 to allow triaxle in for Bridge Installation; | 6 | C129-C151 | Lake A | 0 | 43861 |  | 40 | 43869 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting134120200127-10Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting134120200127-10Operator - Principle - After Jan 1011825Inv#007-R01 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1345 | 20200127-15 | 53510611 | Access | 0 | Feller Buncher | 240 | 9 | HR | 180 | 0 |  |  | 2160 | 280.8 | 2440.8 | 2020-01-27 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Access Maintenance from C186 | 6 | C186-C195 | Del Lake | 0 | 43865 |  | 40 | 43869 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting134520200127-15Feller Buncher92160 | Corbiere and Sons Contracting134520200127-15Feller Buncher92160Inv#007-R01 | [5 empty] | 1 | 2160 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1345 | 20200127-15 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 9 | Dynamic | 98.61 | 0 |  |  | 1183.32 | 153.8316 | 1337.1516 | 2020-01-27 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Access Maintenance from C186 | 6 | C186-C195 | Del Lake | 0 | 43865 |  | 40 | 43869 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting134520200127-15Dozer D6 or equal- After Jan 1091183.32 | Corbiere and Sons Contracting134520200127-15Dozer D6 or equal- After Jan 1091183.32Inv#007-R01 | [5 empty] | 1 | 1183.32 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1345 | 20200127-15 | 53510611 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-01-27 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Access Maintenance from C186 | 6 | C186-C195 | Del Lake | 0 | 43865 |  | 40 | 43869 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting134520200127-15L.O.A.2420 | Corbiere and Sons Contracting134520200127-15L.O.A.2420Inv#007-R01 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1345 | 20200127-15 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 22 | HR |  |  | 75 | 0 | 1650 | 214.5 | 1864.5 | 2020-01-27 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Access Maintenance from C186 | 6 | C186-C195 | Del Lake | 0 | 43865 |  | 40 | 43869 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting134520200127-15Operator - Principle - After Jan 10221650 | Corbiere and Sons Contracting134520200127-15Operator - Principle - After Jan 10221650Inv#007-R01 | [5 empty] | 1 | 1650 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1334 | 20200127-3 | 53520104 | Clearing | 0 | Chainsaw and consumables- After Jan 10 | 60 | 4 | unit/man/day | 0 | 0 |  |  | 240 | 31.2 | 271.2 | 2020-01-27 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  |  | 1 | A036-A046 | Beck Road W | 0 | 43865 |  | 36 | 43868 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting133420200127-3Chainsaw and consumables- After Jan 104240 | Corbiere and Sons Contracting133420200127-3Chainsaw and consumables- After Jan 104240Inv#009 |  |  | WF1-Handfalling |  |  | 1 | 240 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1334 | 20200127-3 | 53520104 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-01-27 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  |  | 1 | A036-A046 | Beck Road W | 0 | 43865 |  | 36 | 43868 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting133420200127-3Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting133420200127-3Light Truck - Pick up- After Jan 102487.5Inv#009 |  |  | WF1-Handfalling |  |  | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1334 | 20200127-3 | 53520104 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2020-01-27 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  |  | 1 | A036-A046 | Beck Road W | 0 | 43865 |  | 36 | 43868 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting133420200127-3Foreman121140 | Corbiere and Sons Contracting133420200127-3Foreman121140Inv#009 |  |  | WF1-Handfalling |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1334 | 20200127-3 | 53520104 | Clearing | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2020-01-27 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  |  | 1 | A036-A046 | Beck Road W | 0 | 43865 |  | 36 | 43868 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting133420200127-3L.O.A.51050 | Corbiere and Sons Contracting133420200127-3L.O.A.51050Inv#009 |  |  | WF1-Handfalling |  |  | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1334 | 20200127-3 | 53520104 | Clearing | 0 | Labourer - Specialized - After Jan 10 | 70 | 44 | HR |  |  | 70 | 0 | 3080 | 400.4 | 3480.4 | 2020-01-27 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  |  | 1 | A036-A046 | Beck Road W | 0 | 43865 |  | 36 | 43868 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting133420200127-3Labourer - Specialized - After Jan 10443080 | Corbiere and Sons Contracting133420200127-3Labourer - Specialized - After Jan 10443080Inv#009 |  |  | WF1-Handfalling |  |  | 1 | 3080 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1335 | 20200127-4 | 53520101 | Clearing | 0 | Brusher | 202.5 | 9 | HR | 151.88 | 0 |  |  | 1822.5 | 236.925 | 2059.425 | 2020-01-27 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brushing up to the Bridge at A070; | 1 | A-055 to A-084 | Eldorado | 0 | 43865 |  | 36 | 43868 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting133520200127-4Brusher91822.5 | Corbiere and Sons Contracting133520200127-4Brusher91822.5Inv#009 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1822.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1335 | 20200127-4 | 53520101 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-01-27 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brushing up to the Bridge at A070; | 1 | A-055 to A-084 | Eldorado | 0 | 43865 |  | 36 | 43868 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting133520200127-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting133520200127-4Light Truck - Pick up- After Jan 101243.75Inv#009 |  |  | WF1-Merchantable Clearing |  |  | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1335 | 20200127-4 | 53520101 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-01-27 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brushing up to the Bridge at A070; | 1 | A-055 to A-084 | Eldorado | 0 | 43865 |  | 36 | 43868 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting133520200127-4L.O.A.1210 | Corbiere and Sons Contracting133520200127-4L.O.A.1210Inv#009 |  |  | WF1-Merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1335 | 20200127-4 | 53520101 | Clearing | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2020-01-27 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brushing up to the Bridge at A070; | 1 | A-055 to A-084 | Eldorado | 0 | 43865 |  | 36 | 43868 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting133520200127-4Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting133520200127-4Operator - Principle - After Jan 1011825Inv#009 |  |  | WF1-Merchantable Clearing |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1337 | 20200127-6 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 9 | HR | 417.6 | 0 |  |  | 5011.2 | 651.456 | 5662.656 | 2020-01-27 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling from A097-A096; Grinding of Material at A115; | 1 | A-085 to A-117 | Windfarm | 0 | 43861 |  | 36 | 43868 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting133720200127-6Grinder - 4710 Peterson or equal95011.2 | Corbiere and Sons Contracting133720200127-6Grinder - 4710 Peterson or equal95011.2Inv#009 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 5011.2 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1337 | 20200127-6 | 53520102 | Clearing | 0 | Log Loader | 153 | 9 | HR | 114.75 | 0 |  |  | 1377 | 179.01 | 1556.01 | 2020-01-27 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling from A097-A096; Grinding of Material at A115; | 1 | A-085 to A-117 | Windfarm | 0 | 43861 |  | 36 | 43868 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting133720200127-6Log Loader91377 | Corbiere and Sons Contracting133720200127-6Log Loader91377Inv#009 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1377 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1337 | 20200127-6 | 53520104 | Clearing | 0 | Chainsaw and consumables- After Jan 10 | 60 | 3 | unit/man/day | 0 | 0 |  |  | 180 | 23.4 | 203.4 | 2020-01-27 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling from A097-A096; Grinding of Material at A115; | 1 | A-085 to A-117 | Windfarm | 0 | 43861 |  | 36 | 43868 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting133720200127-6Chainsaw and consumables- After Jan 103180 | Corbiere and Sons Contracting133720200127-6Chainsaw and consumables- After Jan 103180Inv#009 |  |  | WF1-Handfalling |  |  | 1 | 180 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1337 | 20200127-6 | 53520102 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-01-27 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling from A097-A096; Grinding of Material at A115; | 1 | A-085 to A-117 | Windfarm | 0 | 43861 |  | 36 | 43868 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting133720200127-6Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting133720200127-6Light Truck - Pick up- After Jan 101243.75Inv#009 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1337 | 20200127-6 | 53520104 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-01-27 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling from A097-A096; Grinding of Material at A115; | 1 | A-085 to A-117 | Windfarm | 0 | 43861 |  | 36 | 43868 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting133720200127-6Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting133720200127-6Light Truck - Pick up- After Jan 101243.75Inv#009 |  |  | WF1-Handfalling |  |  | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1337 | 20200127-6 | 53520107 | Clearing | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 10 | Dynamic | 91.79 | 0 |  |  | 1223.9 | 159.107 | 1383.007 | 2020-01-27 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Hazard Tree Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling from A097-A096; Grinding of Material at A115; | 1 | A-085 to A-117 | Windfarm | 0 | 43861 |  | 36 | 43868 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting133720200127-6Tractor Trailer - 60 Ton- After Jan 10101223.9 | Corbiere and Sons Contracting133720200127-6Tractor Trailer - 60 Ton- After Jan 10101223.9Inv#009 |  |  | WF1-Hazard Tree Clearing |  |  | 1 | 1223.9 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1337 | 20200127-6 | 53520102 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-01-27 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling from A097-A096; Grinding of Material at A115; | 1 | A-085 to A-117 | Windfarm | 0 | 43861 |  | 36 | 43868 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting133720200127-6L.O.A.1210 | Corbiere and Sons Contracting133720200127-6L.O.A.1210Inv#009 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1337 | 20200127-6 | 53520104 | Clearing | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2020-01-27 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling from A097-A096; Grinding of Material at A115; | 1 | A-085 to A-117 | Windfarm | 0 | 43861 |  | 36 | 43868 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting133720200127-6L.O.A.3630 | Corbiere and Sons Contracting133720200127-6L.O.A.3630Inv#009 |  |  | WF1-Handfalling |  |  | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1337 | 20200127-6 | 53520107 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-01-27 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Hazard Tree Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling from A097-A096; Grinding of Material at A115; | 1 | A-085 to A-117 | Windfarm | 0 | 43861 |  | 36 | 43868 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting133720200127-6L.O.A.1210 | Corbiere and Sons Contracting133720200127-6L.O.A.1210Inv#009 |  |  | WF1-Hazard Tree Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1337 | 20200127-6 | 53520102 | Clearing | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2020-01-27 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling from A097-A096; Grinding of Material at A115; | 1 | A-085 to A-117 | Windfarm | 0 | 43861 |  | 36 | 43868 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting133720200127-6Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting133720200127-6Operator - Principle - After Jan 1011825Inv#009 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1337 | 20200127-6 | 53520107 | Clearing | 0 | Operator - Intermdiate - After Jan 10 | 70 | 11 | HR |  |  | 70 | 0 | 770 | 100.1 | 870.1 | 2020-01-27 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Hazard Tree Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling from A097-A096; Grinding of Material at A115; | 1 | A-085 to A-117 | Windfarm | 0 | 43861 |  | 36 | 43868 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting133720200127-6Operator - Intermdiate - After Jan 1011770 | Corbiere and Sons Contracting133720200127-6Operator - Intermdiate - After Jan 1011770Inv#009 |  |  | WF1-Hazard Tree Clearing |  |  | 1 | 770 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1337 | 20200127-6 | 53520104 | Clearing | 0 | Labourer - Specialized - After Jan 10 | 70 | 33 | HR |  |  | 70 | 0 | 2310 | 300.3 | 2610.3 | 2020-01-27 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling from A097-A096; Grinding of Material at A115; | 1 | A-085 to A-117 | Windfarm | 0 | 43861 |  | 36 | 43868 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting133720200127-6Labourer - Specialized - After Jan 10332310 | Corbiere and Sons Contracting133720200127-6Labourer - Specialized - After Jan 10332310Inv#009 |  |  | WF1-Handfalling |  |  | 1 | 2310 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1338 | 20200127-7 | 53510106 | Access | 0 | Dozer - D5 or equal- After Jan 10 | 80.93 | 9 | Dynamic | 60.7 | 0 |  |  | 728.37 | 94.6881 | 823.0581 | 2020-01-27 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Packing Frost in Wetland at A126-127 | 1 | A-128 to B-017 | Wolf Lake | 0 | 43865 |  | 37 | 43890 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting133820200127-7Dozer - D5 or equal- After Jan 109728.37 | Corbiere and Sons Contracting133820200127-7Dozer - D5 or equal- After Jan 109728.37Inv#009 |  | WF1-Access | WF1-Access |  | 0 | 1 | 728.37 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1338 | 20200127-7 | 53510106 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-01-27 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Packing Frost in Wetland at A126-127 | 1 | A-128 to B-017 | Wolf Lake | 0 | 43865 |  | 37 | 43890 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting133820200127-7Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting133820200127-7Light Truck - Pick up- After Jan 102487.5Inv#009 |  | WF1-Access | WF1-Access |  | 0 | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1338 | 20200127-7 | 53510106 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2020-01-27 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Packing Frost in Wetland at A126-127 | 1 | A-128 to B-017 | Wolf Lake | 0 | 43865 |  | 37 | 43890 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting133820200127-7Foreman121140 | Corbiere and Sons Contracting133820200127-7Foreman121140Inv#009 |  | WF1-Access | WF1-Access |  | 0 | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1338 | 20200127-7 | 53510106 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2020-01-27 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Packing Frost in Wetland at A126-127 | 1 | A-128 to B-017 | Wolf Lake | 0 | 43865 |  | 37 | 43890 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting133820200127-7L.O.A.3630 | Corbiere and Sons Contracting133820200127-7L.O.A.3630Inv#009 |  | WF1-Access | WF1-Access |  | 0 | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1338 | 20200127-7 | 53510106 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2020-01-27 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Packing Frost in Wetland at A126-127 | 1 | A-128 to B-017 | Wolf Lake | 0 | 43865 |  | 37 | 43890 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting133820200127-7Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting133820200127-7Operator - Principle - After Jan 1011825Inv#009 |  | WF1-Access | WF1-Access |  | 0 | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1338 | 20200127-7 | 53510106 | Access | 0 | Labourer - General - After Jan 10 | 60 | 11 | HR |  |  | 60 | 0 | 660 | 85.8 | 745.8 | 2020-01-27 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Packing Frost in Wetland at A126-127 | 1 | A-128 to B-017 | Wolf Lake | 0 | 43865 |  | 37 | 43890 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting133820200127-7Labourer - General - After Jan 1011660 | Corbiere and Sons Contracting133820200127-7Labourer - General - After Jan 1011660Inv#009 |  | WF1-Access | WF1-Access |  | 0 | 1 | 660 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1339 | 20200127-8 | 53510106 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 18 | Dynamic | 110.22 | 0 |  |  | 2645.28 | 343.8864 | 2989.1664 | 2020-01-27 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Finishing Winter Rd. at B009-B010 and Repairing Winter Rd. at A129-A128; | 1 | A128-B012 | Fish Hatchery | 0 | 43865 |  | 40 | 43931 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting133920200127-8Excavator - 36 ton- After Jan 10182645.28 | Corbiere and Sons Contracting133920200127-8Excavator - 36 ton- After Jan 10182645.28Inv#022 |  | WF1-Access | WF1-Access |  | 0 | 1 | 2645.28 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1339 | 20200127-8 | 53510106 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2020-01-27 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Finishing Winter Rd. at B009-B010 and Repairing Winter Rd. at A129-A128; | 1 | A128-B012 | Fish Hatchery | 0 | 43865 |  | 40 | 43931 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting133920200127-8Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting133920200127-8Excavator Thumb - 30 - 50 ton- After Jan 109109.89Inv#022 |  | WF1-Access | WF1-Access |  | 0 | 1 | 109.89 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1339 | 20200127-8 | 53510106 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-01-27 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Finishing Winter Rd. at B009-B010 and Repairing Winter Rd. at A129-A128; | 1 | A128-B012 | Fish Hatchery | 0 | 43865 |  | 40 | 43931 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting133920200127-8Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting133920200127-8Light Truck - Pick up- After Jan 102487.5Inv#022 |  | WF1-Access | WF1-Access |  | 0 | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1339 | 20200127-8 | 53510106 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2020-01-27 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Finishing Winter Rd. at B009-B010 and Repairing Winter Rd. at A129-A128; | 1 | A128-B012 | Fish Hatchery | 0 | 43865 |  | 40 | 43931 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting133920200127-8L.O.A.3630 | Corbiere and Sons Contracting133920200127-8L.O.A.3630Inv#022 |  | WF1-Access | WF1-Access |  | 0 | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1339 | 20200127-8 | 53510106 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 22 | HR |  |  | 75 | 0 | 1650 | 214.5 | 1864.5 | 2020-01-27 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Finishing Winter Rd. at B009-B010 and Repairing Winter Rd. at A129-A128; | 1 | A128-B012 | Fish Hatchery | 0 | 43865 |  | 40 | 43931 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting133920200127-8Operator - Principle - After Jan 10221650 | Corbiere and Sons Contracting133920200127-8Operator - Principle - After Jan 10221650Inv#022 |  | WF1-Access | WF1-Access |  | 0 | 1 | 1650 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1339 | 20200127-8 | 53510106 | Access | 0 | Labourer - General - After Jan 10 | 60 | 11 | HR |  |  | 60 | 0 | 660 | 85.8 | 745.8 | 2020-01-27 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Finishing Winter Rd. at B009-B010 and Repairing Winter Rd. at A129-A128; | 1 | A128-B012 | Fish Hatchery | 0 | 43865 |  | 40 | 43931 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting133920200127-8Labourer - General - After Jan 1011660 | Corbiere and Sons Contracting133920200127-8Labourer - General - After Jan 1011660Inv#022 |  | WF1-Access | WF1-Access |  | 0 | 1 | 660 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1363 | 20200128-12 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 9 | Dynamic | 98.61 | 0 |  |  | 1183.32 | 153.8316 | 1337.1516 | 2020-01-28 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Clearing access into Lake A | 6 | C129-C151 | Lake A | 0 | 43866 |  | 40 | 43869 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting136320200128-12Dozer D6 or equal- After Jan 1091183.32 | Corbiere and Sons Contracting136320200128-12Dozer D6 or equal- After Jan 1091183.32Inv#007-R01 | [5 empty] | 1 | 1183.32 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1363 | 20200128-12 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-01-28 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Clearing access into Lake A | 6 | C129-C151 | Lake A | 0 | 43866 |  | 40 | 43869 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting136320200128-12L.O.A.1210 | Corbiere and Sons Contracting136320200128-12L.O.A.1210Inv#007-R01 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1363 | 20200128-12 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2020-01-28 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Clearing access into Lake A | 6 | C129-C151 | Lake A | 0 | 43866 |  | 40 | 43869 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting136320200128-12Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting136320200128-12Operator - Principle - After Jan 1011825Inv#007-R01 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1354 | 20200128-3 | 53520104 | Clearing | 0 | Chainsaw and consumables- After Jan 10 | 60 | 3 | unit/man/day | 0 | 0 |  |  | 180 | 23.4 | 203.4 | 2020-01-28 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling towards A036; | 1 | A-036 to A-054 | Beck Road | 0 | 43866 |  | 36 | 43868 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting135420200128-3Chainsaw and consumables- After Jan 103180 | Corbiere and Sons Contracting135420200128-3Chainsaw and consumables- After Jan 103180Inv#009 |  |  | WF1-Handfalling |  |  | 1 | 180 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1354 | 20200128-3 | 53520104 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-01-28 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling towards A036; | 1 | A-036 to A-054 | Beck Road | 0 | 43866 |  | 36 | 43868 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting135420200128-3Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting135420200128-3Light Truck - Pick up- After Jan 102487.5Inv#009 |  |  | WF1-Handfalling |  |  | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1354 | 20200128-3 | 53520104 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2020-01-28 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling towards A036; | 1 | A-036 to A-054 | Beck Road | 0 | 43866 |  | 36 | 43868 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting135420200128-3Foreman121140 | Corbiere and Sons Contracting135420200128-3Foreman121140Inv#009 |  |  | WF1-Handfalling |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1354 | 20200128-3 | 53520104 | Clearing | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2020-01-28 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling towards A036; | 1 | A-036 to A-054 | Beck Road | 0 | 43866 |  | 36 | 43868 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting135420200128-3L.O.A.4840 | Corbiere and Sons Contracting135420200128-3L.O.A.4840Inv#009 |  |  | WF1-Handfalling |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1354 | 20200128-3 | 53520104 | Clearing | 0 | Labourer - Specialized - After Jan 10 | 70 | 33 | HR |  |  | 70 | 0 | 2310 | 300.3 | 2610.3 | 2020-01-28 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling towards A036; | 1 | A-036 to A-054 | Beck Road | 0 | 43866 |  | 36 | 43868 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting135420200128-3Labourer - Specialized - After Jan 10332310 | Corbiere and Sons Contracting135420200128-3Labourer - Specialized - After Jan 10332310Inv#009 |  |  | WF1-Handfalling |  |  | 1 | 2310 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1356 | 20200128-5 | 53520101 | Clearing | 0 | Brusher | 202.5 | 9 | HR | 151.88 | 0 |  |  | 1822.5 | 236.925 | 2059.425 | 2020-01-28 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher clearing up to crossing at A070 and waiting to cross; | 1 | A-055 to A-084 | Eldorado | 0 | 43866 |  | 36 | 43868 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting135620200128-5Brusher91822.5 | Corbiere and Sons Contracting135620200128-5Brusher91822.5Inv#009 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1822.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1356 | 20200128-5 | 53520101 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-01-28 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher clearing up to crossing at A070 and waiting to cross; | 1 | A-055 to A-084 | Eldorado | 0 | 43866 |  | 36 | 43868 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting135620200128-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting135620200128-5Light Truck - Pick up- After Jan 101243.75Inv#009 |  |  | WF1-Merchantable Clearing |  |  | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1356 | 20200128-5 | 53520101 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-01-28 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher clearing up to crossing at A070 and waiting to cross; | 1 | A-055 to A-084 | Eldorado | 0 | 43866 |  | 36 | 43868 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting135620200128-5L.O.A.1210 | Corbiere and Sons Contracting135620200128-5L.O.A.1210Inv#009 |  |  | WF1-Merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1356 | 20200128-5 | 53520101 | Clearing | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2020-01-28 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher clearing up to crossing at A070 and waiting to cross; | 1 | A-055 to A-084 | Eldorado | 0 | 43866 |  | 36 | 43868 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting135620200128-5Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting135620200128-5Operator - Principle - After Jan 1011825Inv#009 |  |  | WF1-Merchantable Clearing |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1357 | 20200128-6 | 53520101 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 9 | HR | 417.6 | 0 |  |  | 5011.2 | 651.456 | 5662.656 | 2020-01-28 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Finished up Grinding of Material at A115; | 1 | A-085 to A-117 | Windfarm | 0 | 43866 |  | 36 | 43868 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting135720200128-6Grinder - 4710 Peterson or equal95011.2 | Corbiere and Sons Contracting135720200128-6Grinder - 4710 Peterson or equal95011.2Inv#009 |  |  | WF1-Merchantable Clearing |  |  | 1 | 5011.2 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1357 | 20200128-6 | 53520101 | Clearing | 0 | Log Loader | 153 | 9 | HR | 114.75 | 0 |  |  | 1377 | 179.01 | 1556.01 | 2020-01-28 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Finished up Grinding of Material at A115; | 1 | A-085 to A-117 | Windfarm | 0 | 43866 |  | 36 | 43868 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting135720200128-6Log Loader91377 | Corbiere and Sons Contracting135720200128-6Log Loader91377Inv#009 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1377 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1357 | 20200128-6 | 53520101 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-01-28 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Finished up Grinding of Material at A115; | 1 | A-085 to A-117 | Windfarm | 0 | 43866 |  | 36 | 43868 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting135720200128-6Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting135720200128-6Light Truck - Pick up- After Jan 101243.75Inv#009 |  |  | WF1-Merchantable Clearing |  |  | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1357 | 20200128-6 | 53520102 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-01-28 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Finished up Grinding of Material at A115; | 1 | A-085 to A-117 | Windfarm | 0 | 43866 |  | 36 | 43868 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting135720200128-6L.O.A.1210 | Corbiere and Sons Contracting135720200128-6L.O.A.1210Inv#009 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1357 | 20200128-6 | 53520102 | Clearing | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2020-01-28 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Finished up Grinding of Material at A115; | 1 | A-085 to A-117 | Windfarm | 0 | 43866 |  | 36 | 43868 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting135720200128-6Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting135720200128-6Operator - Principle - After Jan 1011825Inv#009 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1359 | 20200128-8 | 53520104 | Clearing | 0 | Chainsaw and consumables- After Jan 10 | 60 | 3 | unit/man/day | 0 | 0 |  |  | 180 | 23.4 | 203.4 | 2020-01-28 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling from A127; | 1 | A-118 to A-127 | Innes Lake | 0 | 43866 |  | 36 | 43868 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting135920200128-8Chainsaw and consumables- After Jan 103180 | Corbiere and Sons Contracting135920200128-8Chainsaw and consumables- After Jan 103180Inv#009 |  |  | WF1-Handfalling |  |  | 1 | 180 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1359 | 20200128-8 | 53520104 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-01-28 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling from A127; | 1 | A-118 to A-127 | Innes Lake | 0 | 43866 |  | 36 | 43868 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting135920200128-8Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting135920200128-8Light Truck - Pick up- After Jan 101243.75Inv#009 |  |  | WF1-Handfalling |  |  | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1359 | 20200128-8 | 53520104 | Clearing | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2020-01-28 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling from A127; | 1 | A-118 to A-127 | Innes Lake | 0 | 43866 |  | 36 | 43868 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting135920200128-8L.O.A.3630 | Corbiere and Sons Contracting135920200128-8L.O.A.3630Inv#009 |  |  | WF1-Handfalling |  |  | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1359 | 20200128-8 | 53520104 | Clearing | 0 | Labourer - Specialized - After Jan 10 | 70 | 33 | HR |  |  | 70 | 0 | 2310 | 300.3 | 2610.3 | 2020-01-28 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling from A127; | 1 | A-118 to A-127 | Innes Lake | 0 | 43866 |  | 36 | 43868 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting135920200128-8Labourer - Specialized - After Jan 10332310 | Corbiere and Sons Contracting135920200128-8Labourer - Specialized - After Jan 10332310Inv#009 |  |  | WF1-Handfalling |  |  | 1 | 2310 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1360 | 20200128-9 | 53510106 | Access | 0 | Skidder | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2020-01-28 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Repairing Riprap on winter road at A132; Continue building Winter Rd. from A129-A128; | 1 | A128-B012 | Fish Hatchery | 0 | 43866 |  | 37 | 43874 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting136020200128-9Skidder 91539 | Corbiere and Sons Contracting136020200128-9Skidder 91539Inv#009 |  | WF1-Access | WF1-Access |  | 0 | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1360 | 20200128-9 | 53510106 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 18 | Dynamic | 110.22 | 0 |  |  | 2645.28 | 343.8864 | 2989.1664 | 2020-01-28 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Repairing Riprap on winter road at A132; Continue building Winter Rd. from A129-A128; | 1 | A128-B012 | Fish Hatchery | 0 | 43866 |  | 37 | 43874 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting136020200128-9Excavator - 36 ton- After Jan 10182645.28 | Corbiere and Sons Contracting136020200128-9Excavator - 36 ton- After Jan 10182645.28Inv#009 |  | WF1-Access | WF1-Access |  | 0 | 1 | 2645.28 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1360 | 20200128-9 | 53510106 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2020-01-28 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Repairing Riprap on winter road at A132; Continue building Winter Rd. from A129-A128; | 1 | A128-B012 | Fish Hatchery | 0 | 43866 |  | 37 | 43874 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting136020200128-9Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting136020200128-9Excavator Thumb - 30 - 50 ton- After Jan 109109.89Inv#009 |  | WF1-Access | WF1-Access |  | 0 | 1 | 109.89 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1360 | 20200128-9 | 53510106 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2020-01-28 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Repairing Riprap on winter road at A132; Continue building Winter Rd. from A129-A128; | 1 | A128-B012 | Fish Hatchery | 0 | 43866 |  | 37 | 43874 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting136020200128-9Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting136020200128-9Light Truck - Pick up- After Jan 103731.25Inv#009 |  | WF1-Access | WF1-Access |  | 0 | 1 | 731.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1360 | 20200128-9 | 53510106 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2020-01-28 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Repairing Riprap on winter road at A132; Continue building Winter Rd. from A129-A128; | 1 | A128-B012 | Fish Hatchery | 0 | 43866 |  | 37 | 43874 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting136020200128-9Foreman121140 | Corbiere and Sons Contracting136020200128-9Foreman121140Inv#009 |  | WF1-Access | WF1-Access |  | 0 | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1360 | 20200128-9 | 53510106 | Access | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2020-01-28 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Repairing Riprap on winter road at A132; Continue building Winter Rd. from A129-A128; | 1 | A128-B012 | Fish Hatchery | 0 | 43866 |  | 37 | 43874 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting136020200128-9L.O.A.51050 | Corbiere and Sons Contracting136020200128-9L.O.A.51050Inv#009 |  | WF1-Access | WF1-Access |  | 0 | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1360 | 20200128-9 | 53510106 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 33 | HR |  |  | 75 | 0 | 2475 | 321.75 | 2796.75 | 2020-01-28 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Repairing Riprap on winter road at A132; Continue building Winter Rd. from A129-A128; | 1 | A128-B012 | Fish Hatchery | 0 | 43866 |  | 37 | 43874 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting136020200128-9Operator - Principle - After Jan 10332475 | Corbiere and Sons Contracting136020200128-9Operator - Principle - After Jan 10332475Inv#009 |  | WF1-Access | WF1-Access |  | 0 | 1 | 2475 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1360 | 20200128-9 | 53510106 | Access | 0 | Labourer - General - After Jan 10 | 60 | 11 | HR |  |  | 60 | 0 | 660 | 85.8 | 745.8 | 2020-01-28 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Repairing Riprap on winter road at A132; Continue building Winter Rd. from A129-A128; | 1 | A128-B012 | Fish Hatchery | 0 | 43866 |  | 37 | 43874 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting136020200128-9Labourer - General - After Jan 1011660 | Corbiere and Sons Contracting136020200128-9Labourer - General - After Jan 1011660Inv#009 |  | WF1-Access | WF1-Access |  | 0 | 1 | 660 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1379 | 20200129-10 | 53510611 | Access | 0 | Sander Truck - Forestry- After Jan 10 | 86.38 | 2 | Dynamic | 64.79 | 0 |  |  | 172.76 | 22.4588 | 195.2188 | 2020-01-29 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Sanding at Valard Camps in Marathon | 0 |  | Marathon camps | 0 | 43867 |  | 40 | 43889 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting137920200129-10Sander Truck - Forestry- After Jan 102172.76 | Corbiere and Sons Contracting137920200129-10Sander Truck - Forestry- After Jan 102172.76Inv#009 | [5 empty] | 1 | 172.76 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1379 | 20200129-10 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 2 | HR |  |  | 70 | 0 | 140 | 18.2 | 158.2 | 2020-01-29 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Sanding at Valard Camps in Marathon | 0 |  | Marathon camps | 0 | 43867 |  | 40 | 43889 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting137920200129-10Driver - AZ - After Jan 102140 | Corbiere and Sons Contracting137920200129-10Driver - AZ - After Jan 102140Inv#009 | [5 empty] | 1 | 140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1380 | 20200129-11 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 9 | Dynamic | 98.61 | 0 |  |  | 1183.32 | 153.8316 | 1337.1516 | 2020-01-29 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Clearing Access into Lake A; | 0 | C129-C151 | Lake A | 0 | 43867 |  | 40 | 43869 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting138020200129-11Dozer D6 or equal- After Jan 1091183.32 | Corbiere and Sons Contracting138020200129-11Dozer D6 or equal- After Jan 1091183.32Inv#007-R01 | [5 empty] | 1 | 1183.32 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1380 | 20200129-11 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-01-29 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Clearing Access into Lake A; | 0 | C129-C151 | Lake A | 0 | 43867 |  | 40 | 43869 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting138020200129-11L.O.A.1210 | Corbiere and Sons Contracting138020200129-11L.O.A.1210Inv#007-R01 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1380 | 20200129-11 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2020-01-29 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Clearing Access into Lake A; | 0 | C129-C151 | Lake A | 0 | 43867 |  | 40 | 43869 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting138020200129-11Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting138020200129-11Operator - Principle - After Jan 1011825Inv#007-R01 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1372 | 20200129-3 | 53520104 | Clearing | 0 | Chainsaw and consumables- After Jan 10 | 60 | 3 | unit/man/day | 0 | 0 |  |  | 180 | 23.4 | 203.4 | 2020-01-29 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling towards A036; | 1 | A-036 to A-054 | Beck Road | 0 | 43867 |  | 36 | 43868 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting137220200129-3Chainsaw and consumables- After Jan 103180 | Corbiere and Sons Contracting137220200129-3Chainsaw and consumables- After Jan 103180Inv#009 |  |  | WF1-Handfalling |  |  | 1 | 180 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1372 | 20200129-3 | 53520104 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-01-29 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling towards A036; | 1 | A-036 to A-054 | Beck Road | 0 | 43867 |  | 36 | 43868 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting137220200129-3Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting137220200129-3Light Truck - Pick up- After Jan 102487.5Inv#009 |  |  | WF1-Handfalling |  |  | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1372 | 20200129-3 | 53520104 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2020-01-29 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling towards A036; | 1 | A-036 to A-054 | Beck Road | 0 | 43867 |  | 36 | 43868 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting137220200129-3Foreman121140 | Corbiere and Sons Contracting137220200129-3Foreman121140Inv#009 |  |  | WF1-Handfalling |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1372 | 20200129-3 | 53520104 | Clearing | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2020-01-29 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling towards A036; | 1 | A-036 to A-054 | Beck Road | 0 | 43867 |  | 36 | 43868 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting137220200129-3L.O.A.51050 | Corbiere and Sons Contracting137220200129-3L.O.A.51050Inv#009 |  |  | WF1-Handfalling |  |  | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1372 | 20200129-3 | 53520104 | Clearing | 0 | Labourer - Specialized - After Jan 10 | 70 | 38 | HR |  |  | 70 | 0 | 2660 | 345.8 | 3005.8 | 2020-01-29 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling towards A036; | 1 | A-036 to A-054 | Beck Road | 0 | 43867 |  | 36 | 43868 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting137220200129-3Labourer - Specialized - After Jan 10382660 | Corbiere and Sons Contracting137220200129-3Labourer - Specialized - After Jan 10382660Inv#009 |  |  | WF1-Handfalling |  |  | 1 | 2660 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1376 | 20200129-7 | 53510106 | Access | 0 | Skidder | 171 | 5 | HR | 128.25 | 0 |  |  | 855 | 111.15 | 966.15 | 2020-01-29 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Rd. Building from A128 to A1234 and then a float move; | 1 | A128-B012 | Fish Hatchery | 0 | 43867 |  | 40 | 43869 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting137620200129-7Skidder 5855 | Corbiere and Sons Contracting137620200129-7Skidder 5855Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 855 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1376 | 20200129-7 | 53510106 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 18 | Dynamic | 110.22 | 0 |  |  | 2645.28 | 343.8864 | 2989.1664 | 2020-01-29 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Rd. Building from A128 to A1234 and then a float move; | 1 | A128-B012 | Fish Hatchery | 0 | 43867 |  | 40 | 43869 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting137620200129-7Excavator - 36 ton- After Jan 10182645.28 | Corbiere and Sons Contracting137620200129-7Excavator - 36 ton- After Jan 10182645.28Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 2645.28 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1376 | 20200129-7 | 53510106 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2020-01-29 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Rd. Building from A128 to A1234 and then a float move; | 1 | A128-B012 | Fish Hatchery | 0 | 43867 |  | 40 | 43869 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting137620200129-7Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting137620200129-7Excavator Thumb - 30 - 50 ton- After Jan 109109.89Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 109.89 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1376 | 20200129-7 | 53510106 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2020-01-29 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Rd. Building from A128 to A1234 and then a float move; | 1 | A128-B012 | Fish Hatchery | 0 | 43867 |  | 40 | 43869 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting137620200129-7Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting137620200129-7Light Truck - Pick up- After Jan 103731.25Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 731.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1376 | 20200129-7 | 53510106 | Access | 0 | Foreman | 95 | 7 | HR |  |  | 95 | 0 | 665 | 86.45 | 751.45 | 2020-01-29 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Rd. Building from A128 to A1234 and then a float move; | 1 | A128-B012 | Fish Hatchery | 0 | 43867 |  | 40 | 43869 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting137620200129-7Foreman7665 | Corbiere and Sons Contracting137620200129-7Foreman7665Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 665 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1376 | 20200129-7 | 53510106 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2020-01-29 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Rd. Building from A128 to A1234 and then a float move; | 1 | A128-B012 | Fish Hatchery | 0 | 43867 |  | 40 | 43869 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting137620200129-7L.O.A.4840 | Corbiere and Sons Contracting137620200129-7L.O.A.4840Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1376 | 20200129-7 | 53510106 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 28 | HR |  |  | 75 | 0 | 2100 | 273 | 2373 | 2020-01-29 | 1 | Inv#007-R01 | 43881 | 85 | 0 | 0 | Nathan Kyme | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Rd. Building from A128 to A1234 and then a float move; | 1 | A128-B012 | Fish Hatchery | 0 | 43867 |  | 40 | 43869 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting137620200129-7Operator - Principle - After Jan 10282100 | Corbiere and Sons Contracting137620200129-7Operator - Principle - After Jan 10282100Inv#007-R01 |  | WF1-Access | WF1-Access |  | 0 | 1 | 2100 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1377 | 20200129-8-R1 | 53510211 | Access | 0 | Sander Truck - Forestry- After Jan 10 | 86.38 | 2 | Dynamic | 64.79 | 0 |  |  | 172.76 | 22.4588 | 195.2188 | 2020-01-29 | 1 | Inv#009 | 43894 | 86 | 0 | 1 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 15 | Approved | ROW INTERNAL - Sand for Road Maintenance - 3rd Party | 9015 | 1 Load of Sand brough from pit to Lofty Davies; | 2 | B054-B064 | Lofty Davies | 1 | 43867 |  | 36 | 43874 | [5 empty] | Mike Lecocq | 02 | Corbiere and Sons Contracting137720200129-8-R1Sander Truck - Forestry- After Jan 102172.76 | Corbiere and Sons Contracting137720200129-8-R1Sander Truck - Forestry- After Jan 102172.76Inv#009 | [5 empty] | 1 | 172.76 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1377 | 20200129-8-R1 | 53510211 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 2 | HR |  |  | 70 | 0 | 140 | 18.2 | 158.2 | 2020-01-29 | 1 | Inv#009 | 43894 | 86 | 0 | 1 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 15 | Approved | ROW INTERNAL - Sand for Road Maintenance - 3rd Party | 9015 | 1 Load of Sand brough from pit to Lofty Davies; | 2 | B054-B064 | Lofty Davies | 1 | 43867 |  | 36 | 43874 | [5 empty] | Mike Lecocq | 02 | Corbiere and Sons Contracting137720200129-8-R1Driver - AZ - After Jan 102140 | Corbiere and Sons Contracting137720200129-8-R1Driver - AZ - After Jan 102140Inv#009 | [5 empty] | 1 | 140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1378 | 20200129-9 | 53510611 | Access | 0 | Sander Truck - Forestry- After Jan 10 | 86.38 | 2 | Dynamic | 64.79 | 0 |  |  | 172.76 | 22.4588 | 195.2188 | 2020-01-29 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Sanded Valard Laydown near the water; | 6 |  | Valard Laydown by Water | 0 | 43867 |  | 36 | 43868 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting137820200129-9Sander Truck - Forestry- After Jan 102172.76 | Corbiere and Sons Contracting137820200129-9Sander Truck - Forestry- After Jan 102172.76Inv#009 | [5 empty] | 1 | 172.76 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1378 | 20200129-9 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 2 | HR |  |  | 70 | 0 | 140 | 18.2 | 158.2 | 2020-01-29 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Sanded Valard Laydown near the water; | 6 |  | Valard Laydown by Water | 0 | 43867 |  | 36 | 43868 | [5 empty] | Mike Lecocq | 06 | Corbiere and Sons Contracting137820200129-9Driver - AZ - After Jan 102140 | Corbiere and Sons Contracting137820200129-9Driver - AZ - After Jan 102140Inv#009 | [5 empty] | 1 | 140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1442 | 20200130-17 | 53510611 | Access | 0 | Sander Truck - Forestry- After Jan 10 | 86.38 | 2 | Dynamic | 64.79 | 0 |  |  | 172.76 | 22.4588 | 195.2188 | 2020-01-30 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Sanded Valard Laydown Yard in Marathon | 6 |  | Laydown Yard Marathon | 0 | 43871 |  | 40 | 43890 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting144220200130-17Sander Truck - Forestry- After Jan 102172.76 | Corbiere and Sons Contracting144220200130-17Sander Truck - Forestry- After Jan 102172.76Inv#009 | [5 empty] | 1 | 172.76 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1442 | 20200130-17 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 2 | HR |  |  | 70 | 0 | 140 | 18.2 | 158.2 | 2020-01-30 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Sanded Valard Laydown Yard in Marathon | 6 |  | Laydown Yard Marathon | 0 | 43871 |  | 40 | 43890 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting144220200130-17Driver - AZ - After Jan 102140 | Corbiere and Sons Contracting144220200130-17Driver - AZ - After Jan 102140Inv#009 | [5 empty] | 1 | 140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1393 | 20200130-4 | 53520102 | Clearing | 0 | Brusher | 202.5 | 9 | HR | 151.88 | 0 |  |  | 1822.5 | 236.925 | 2059.425 | 2020-01-30 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher finished up sctretch from A061-A072; Walk out to be floated in morning; | 1 | A-055 to A-084 | Eldorado | 0 | 43869 |  | 36 | 43870 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting139320200130-4Brusher91822.5 | Corbiere and Sons Contracting139320200130-4Brusher91822.5Inv#009 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1822.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1393 | 20200130-4 | 53520102 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-01-30 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher finished up sctretch from A061-A072; Walk out to be floated in morning; | 1 | A-055 to A-084 | Eldorado | 0 | 43869 |  | 36 | 43870 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting139320200130-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting139320200130-4Light Truck - Pick up- After Jan 101243.75Inv#009 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1393 | 20200130-4 | 53520102 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-01-30 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher finished up sctretch from A061-A072; Walk out to be floated in morning; | 1 | A-055 to A-084 | Eldorado | 0 | 43869 |  | 36 | 43870 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting139320200130-4L.O.A.1210 | Corbiere and Sons Contracting139320200130-4L.O.A.1210Inv#009 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1393 | 20200130-4 | 53520102 | Clearing | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2020-01-30 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher finished up sctretch from A061-A072; Walk out to be floated in morning; | 1 | A-055 to A-084 | Eldorado | 0 | 43869 |  | 36 | 43870 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting139320200130-4Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting139320200130-4Operator - Principle - After Jan 1011825Inv#009 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1394 | 20200130-5 | 53520104 | Clearing | 0 | Chainsaw and consumables- After Jan 10 | 60 | 3 | unit/man/day | 0 | 0 |  |  | 180 | 23.4 | 203.4 | 2020-01-30 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling from A096; | 1 | A-085 to A-117 | Windfarm | 0 | 43869 |  | 36 | 43870 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting139420200130-5Chainsaw and consumables- After Jan 103180 | Corbiere and Sons Contracting139420200130-5Chainsaw and consumables- After Jan 103180Inv#009 |  |  | WF1-Handfalling |  |  | 1 | 180 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1394 | 20200130-5 | 53520104 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-01-30 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling from A096; | 1 | A-085 to A-117 | Windfarm | 0 | 43869 |  | 36 | 43870 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting139420200130-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting139420200130-5Light Truck - Pick up- After Jan 101243.75Inv#009 |  |  | WF1-Handfalling |  |  | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1394 | 20200130-5 | 53520104 | Clearing | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2020-01-30 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling from A096; | 1 | A-085 to A-117 | Windfarm | 0 | 43869 |  | 36 | 43870 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting139420200130-5L.O.A.3630 | Corbiere and Sons Contracting139420200130-5L.O.A.3630Inv#009 |  |  | WF1-Handfalling |  |  | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1394 | 20200130-5 | 53520104 | Clearing | 0 | Labourer - Specialized - After Jan 10 | 70 | 33 | HR |  |  | 70 | 0 | 2310 | 300.3 | 2610.3 | 2020-01-30 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling from A096; | 1 | A-085 to A-117 | Windfarm | 0 | 43869 |  | 36 | 43870 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting139420200130-5Labourer - Specialized - After Jan 10332310 | Corbiere and Sons Contracting139420200130-5Labourer - Specialized - After Jan 10332310Inv#009 |  |  | WF1-Handfalling |  |  | 1 | 2310 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1395 | 20200130-6 | 53510111 | Access | 0 | Sander Truck - Forestry- After Jan 10 | 86.38 | 4 | Dynamic | 64.79 | 0 |  |  | 345.52 | 44.9176 | 390.4376 | 2020-01-30 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Sander Truck working across access roads; | 1 | A-085 to A-117 | Windfarm | 0 | 43869 |  | 36 | 43870 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting139520200130-6Sander Truck - Forestry- After Jan 104345.52 | Corbiere and Sons Contracting139520200130-6Sander Truck - Forestry- After Jan 104345.52Inv#009 | [5 empty] | 1 | 345.52 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1395 | 20200130-6 | 53510111 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-01-30 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Sander Truck working across access roads; | 1 | A-085 to A-117 | Windfarm | 0 | 43869 |  | 36 | 43870 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting139520200130-6L.O.A.1210 | Corbiere and Sons Contracting139520200130-6L.O.A.1210Inv#009 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1395 | 20200130-6 | 53510111 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 4 | HR |  |  | 70 | 0 | 280 | 36.4 | 316.4 | 2020-01-30 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Sander Truck working across access roads; | 1 | A-085 to A-117 | Windfarm | 0 | 43869 |  | 36 | 43870 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting139520200130-6Driver - AZ - After Jan 104280 | Corbiere and Sons Contracting139520200130-6Driver - AZ - After Jan 104280Inv#009 | [5 empty] | 1 | 280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1396 | 20200130-7 | 53510106 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 103.84 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2020-01-30 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Bulding Winter Rd., laying riprap at A134; | 1 | A128-B012 | Fish Hatchery | 0 | 43869 |  | 40 | 43931 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting139620200130-7Excavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting139620200130-7Excavator - 30 ton- After Jan 1091246.05Inv#022 |  | WF1-Access | WF1-Access |  | 0 | 1 | 1246.05 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1396 | 20200130-7 | 53510106 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2020-01-30 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Bulding Winter Rd., laying riprap at A134; | 1 | A128-B012 | Fish Hatchery | 0 | 43869 |  | 40 | 43931 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting139620200130-7Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting139620200130-7Excavator Thumb - 30 - 50 ton- After Jan 109109.89Inv#022 |  | WF1-Access | WF1-Access |  | 0 | 1 | 109.89 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1396 | 20200130-7 | 53510106 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-01-30 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Bulding Winter Rd., laying riprap at A134; | 1 | A128-B012 | Fish Hatchery | 0 | 43869 |  | 40 | 43931 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting139620200130-7Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting139620200130-7Light Truck - Pick up- After Jan 102487.5Inv#022 |  | WF1-Access | WF1-Access |  | 0 | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1396 | 20200130-7 | 53510106 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2020-01-30 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Bulding Winter Rd., laying riprap at A134; | 1 | A128-B012 | Fish Hatchery | 0 | 43869 |  | 40 | 43931 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting139620200130-7Foreman121140 | Corbiere and Sons Contracting139620200130-7Foreman121140Inv#022 |  | WF1-Access | WF1-Access |  | 0 | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1396 | 20200130-7 | 53510106 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-01-30 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Bulding Winter Rd., laying riprap at A134; | 1 | A128-B012 | Fish Hatchery | 0 | 43869 |  | 40 | 43931 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting139620200130-7L.O.A.2420 | Corbiere and Sons Contracting139620200130-7L.O.A.2420Inv#022 |  | WF1-Access | WF1-Access |  | 0 | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1396 | 20200130-7 | 53510106 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2020-01-30 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Bulding Winter Rd., laying riprap at A134; | 1 | A128-B012 | Fish Hatchery | 0 | 43869 |  | 40 | 43931 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting139620200130-7Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting139620200130-7Operator - Principle - After Jan 1011825Inv#022 |  | WF1-Access | WF1-Access |  | 0 | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1398 | 20200130-9 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2020-01-30 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Clearing access at Lake A; | 6 | C129-C151 | Lake A | 0 | 43869 |  | 40 | 43889 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting139820200130-9Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting139820200130-9Dozer D6 or equal- After Jan 10111446.28Inv#009 | [5 empty] | 1 | 1446.28 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1398 | 20200130-9 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-01-30 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Clearing access at Lake A; | 6 | C129-C151 | Lake A | 0 | 43869 |  | 40 | 43889 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting139820200130-9L.O.A.1210 | Corbiere and Sons Contracting139820200130-9L.O.A.1210Inv#009 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1398 | 20200130-9 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2020-01-30 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Clearing access at Lake A; | 6 | C129-C151 | Lake A | 0 | 43869 |  | 40 | 43889 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting139820200130-9Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting139820200130-9Operator - Principle - After Jan 1011825Inv#009 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1415 | 20200131-10 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 9 | Dynamic | 98.61 | 0 |  |  | 1183.32 | 153.8316 | 1337.1516 | 2020-01-31 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Clearing Access for bridge install at Lake A; | 6 | C129-C151 | Lake A | 0 | 43869 |  | 40 | 43890 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting141520200131-10Dozer D6 or equal- After Jan 1091183.32 | Corbiere and Sons Contracting141520200131-10Dozer D6 or equal- After Jan 1091183.32Inv#009 | [5 empty] | 1 | 1183.32 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1415 | 20200131-10 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-01-31 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Clearing Access for bridge install at Lake A; | 6 | C129-C151 | Lake A | 0 | 43869 |  | 40 | 43890 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting141520200131-10L.O.A.1210 | Corbiere and Sons Contracting141520200131-10L.O.A.1210Inv#009 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1415 | 20200131-10 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2020-01-31 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Clearing Access for bridge install at Lake A; | 6 | C129-C151 | Lake A | 0 | 43869 |  | 40 | 43890 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting141520200131-10Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting141520200131-10Operator - Principle - After Jan 1011825Inv#009 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1408 | 20200131-3 | 53520104 | Clearing | 0 | Chainsaw and consumables- After Jan 10 | 60 | 3 | unit/man/day | 0 | 0 |  |  | 180 | 23.4 | 203.4 | 2020-01-31 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling completed to A036; | 0 |  |  | 0 | 43869 |  | 36 | 43870 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting140820200131-3Chainsaw and consumables- After Jan 103180 | Corbiere and Sons Contracting140820200131-3Chainsaw and consumables- After Jan 103180Inv#009 |  |  | WF1-Handfalling |  |  | 1 | 180 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1408 | 20200131-3 | 53520104 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-01-31 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling completed to A036; | 0 |  |  | 0 | 43869 |  | 36 | 43870 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting140820200131-3Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting140820200131-3Light Truck - Pick up- After Jan 102487.5Inv#009 |  |  | WF1-Handfalling |  |  | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1408 | 20200131-3 | 53520104 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2020-01-31 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling completed to A036; | 0 |  |  | 0 | 43869 |  | 36 | 43870 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting140820200131-3Foreman121140 | Corbiere and Sons Contracting140820200131-3Foreman121140Inv#009 |  |  | WF1-Handfalling |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1408 | 20200131-3 | 53520104 | Clearing | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2020-01-31 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling completed to A036; | 0 |  |  | 0 | 43869 |  | 36 | 43870 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting140820200131-3L.O.A.4840 | Corbiere and Sons Contracting140820200131-3L.O.A.4840Inv#009 |  |  | WF1-Handfalling |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1408 | 20200131-3 | 53520104 | Clearing | 0 | Labourer - Specialized - After Jan 10 | 70 | 33 | HR |  |  | 70 | 0 | 2310 | 300.3 | 2610.3 | 2020-01-31 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling completed to A036; | 0 |  |  | 0 | 43869 |  | 36 | 43870 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting140820200131-3Labourer - Specialized - After Jan 10332310 | Corbiere and Sons Contracting140820200131-3Labourer - Specialized - After Jan 10332310Inv#009 |  |  | WF1-Handfalling |  |  | 1 | 2310 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1410 | 20200131-5 | 53520102 | Clearing | 0 | Brusher | 202.5 | 5 | HR | 151.88 | 0 |  |  | 1012.5 | 131.625 | 1144.125 | 2020-01-31 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling at A068; Brushing being demobed from Eldorado after completing and walking out; | 1 | A-055 to A-084 | Eldorado | 0 | 43869 |  | 36 | 43870 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting141020200131-5Brusher51012.5 | Corbiere and Sons Contracting141020200131-5Brusher51012.5Inv#009 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1012.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1410 | 20200131-5 | 53520104 | Clearing | 0 | Chainsaw and consumables- After Jan 10 | 60 | 1 | unit/man/day | 0 | 0 |  |  | 60 | 7.8 | 67.8 | 2020-01-31 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling at A068; Brushing being demobed from Eldorado after completing and walking out; | 1 | A-055 to A-084 | Eldorado | 0 | 43869 |  | 36 | 43870 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting141020200131-5Chainsaw and consumables- After Jan 10160 | Corbiere and Sons Contracting141020200131-5Chainsaw and consumables- After Jan 10160Inv#009 |  |  | WF1-Handfalling |  |  | 1 | 60 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1410 | 20200131-5 | 53520104 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-01-31 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling at A068; Brushing being demobed from Eldorado after completing and walking out; | 1 | A-055 to A-084 | Eldorado | 0 | 43869 |  | 36 | 43870 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting141020200131-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting141020200131-5Light Truck - Pick up- After Jan 101243.75Inv#009 |  |  | WF1-Handfalling |  |  | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1410 | 20200131-5 | 53520102 | Clearing | 0 | Tractor Trailer - 50 Ton- After Jan 10 | 111.75 | 5 | Dynamic | 83.81 | 0 |  |  | 558.75 | 72.6375 | 631.3875 | 2020-01-31 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling at A068; Brushing being demobed from Eldorado after completing and walking out; | 1 | A-055 to A-084 | Eldorado | 0 | 43869 |  | 36 | 43870 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting141020200131-5Tractor Trailer - 50 Ton- After Jan 105558.75 | Corbiere and Sons Contracting141020200131-5Tractor Trailer - 50 Ton- After Jan 105558.75Inv#009 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 558.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1410 | 20200131-5 | 53520104 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-01-31 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling at A068; Brushing being demobed from Eldorado after completing and walking out; | 1 | A-055 to A-084 | Eldorado | 0 | 43869 |  | 36 | 43870 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting141020200131-5L.O.A.1210 | Corbiere and Sons Contracting141020200131-5L.O.A.1210Inv#009 |  |  | WF1-Handfalling |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1410 | 20200131-5 | 53520104 | Clearing | 0 | Labourer - Specialized - After Jan 10 | 70 | 11 | HR |  |  | 70 | 0 | 770 | 100.1 | 870.1 | 2020-01-31 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling at A068; Brushing being demobed from Eldorado after completing and walking out; | 1 | A-055 to A-084 | Eldorado | 0 | 43869 |  | 36 | 43870 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting141020200131-5Labourer - Specialized - After Jan 1011770 | Corbiere and Sons Contracting141020200131-5Labourer - Specialized - After Jan 1011770Inv#009 |  |  | WF1-Handfalling |  |  | 1 | 770 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1411 | 20200131-6 | 53510111 | Access | 0 | Sander Truck - Forestry- After Jan 10 | 86.38 | 11.5 | Dynamic | 64.79 | 0 |  |  | 993.37 | 129.1381 | 1122.5081 | 2020-01-31 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Sander Truck working across all access roads; | 1 | A-055 to A-084 | Eldorado | 0 | 43869 |  | 36 | 43870 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting141120200131-6Sander Truck - Forestry- After Jan 1011.5993.37 | Corbiere and Sons Contracting141120200131-6Sander Truck - Forestry- After Jan 1011.5993.37Inv#009 | [5 empty] | 1 | 993.37 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1411 | 20200131-6 | 53510111 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-01-31 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Sander Truck working across all access roads; | 1 | A-055 to A-084 | Eldorado | 0 | 43869 |  | 36 | 43870 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting141120200131-6L.O.A.1210 | Corbiere and Sons Contracting141120200131-6L.O.A.1210Inv#009 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1411 | 20200131-6 | 53510111 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 11.5 | HR |  |  | 70 | 0 | 805 | 104.65 | 909.65 | 2020-01-31 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Sander Truck working across all access roads; | 1 | A-055 to A-084 | Eldorado | 0 | 43869 |  | 36 | 43870 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting141120200131-6Driver - AZ - After Jan 1011.5805 | Corbiere and Sons Contracting141120200131-6Driver - AZ - After Jan 1011.5805Inv#009 | [5 empty] | 1 | 805 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1412 | 20200131-7 | 53510106 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2020-01-31 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Completed to A134; | 1 |  | Fish Hatchery | 0 | 43869 |  | 36 | 43870 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting141220200131-7Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting141220200131-7Excavator - 30 ton- After Jan 10111522.95Inv#009 |  | WF1-Access | WF1-Access |  | 0 | 1 | 1522.95 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1412 | 20200131-7 | 53510106 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2020-01-31 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Completed to A134; | 1 |  | Fish Hatchery | 0 | 43869 |  | 36 | 43870 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting141220200131-7Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting141220200131-7Excavator Thumb - 30 - 50 ton- After Jan 1011134.31Inv#009 |  | WF1-Access | WF1-Access |  | 0 | 1 | 134.31 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1412 | 20200131-7 | 53510106 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-01-31 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Completed to A134; | 1 |  | Fish Hatchery | 0 | 43869 |  | 36 | 43870 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting141220200131-7Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting141220200131-7Light Truck - Pick up- After Jan 102487.5Inv#009 |  | WF1-Access | WF1-Access |  | 0 | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1412 | 20200131-7 | 53510106 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2020-01-31 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Completed to A134; | 1 |  | Fish Hatchery | 0 | 43869 |  | 36 | 43870 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting141220200131-7Foreman121140 | Corbiere and Sons Contracting141220200131-7Foreman121140Inv#009 |  | WF1-Access | WF1-Access |  | 0 | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1412 | 20200131-7 | 53510106 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-01-31 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Completed to A134; | 1 |  | Fish Hatchery | 0 | 43869 |  | 36 | 43870 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting141220200131-7L.O.A.2420 | Corbiere and Sons Contracting141220200131-7L.O.A.2420Inv#009 |  | WF1-Access | WF1-Access |  | 0 | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1412 | 20200131-7 | 53510106 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2020-01-31 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Completed to A134; | 1 |  | Fish Hatchery | 0 | 43869 |  | 36 | 43870 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting141220200131-7Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting141220200131-7Operator - Principle - After Jan 1011825Inv#009 |  | WF1-Access | WF1-Access |  | 0 | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1437 | 20200201-11 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 6.5 | Dynamic | 98.61 | 0 |  |  | 854.62 | 111.1006 | 965.7206 | 2020-02-01 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Clearing Rd. for Access; | 6 | C237-C243 | Culvert Creek | 0 | 43870 |  | 40 | 43890 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting143720200201-11Dozer D6 or equal- After Jan 106.5854.62 | Corbiere and Sons Contracting143720200201-11Dozer D6 or equal- After Jan 106.5854.62Inv#009 | [5 empty] | 1 | 854.62 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1437 | 20200201-11 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6.5 | HR |  |  | 75 | 0 | 487.5 | 63.375 | 550.875 | 2020-02-01 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Clearing Rd. for Access; | 6 | C237-C243 | Culvert Creek | 0 | 43870 |  | 40 | 43890 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting143720200201-11Operator - Principle - After Jan 106.5487.5 | Corbiere and Sons Contracting143720200201-11Operator - Principle - After Jan 106.5487.5Inv#009 | [5 empty] | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1439 | 20200201-13 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 9 | Dynamic | 95.24 | 0 |  |  | 1142.82 | 148.5666 | 1291.3866 | 2020-02-01 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Clearing access on all roads with Grader; | 6 | C156-C170 | Santoy Lake | 0 | 43870 |  | 40 | 43890 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting143920200201-13Grader - Cat 12 to 14 or equal- After Jan 1091142.82 | Corbiere and Sons Contracting143920200201-13Grader - Cat 12 to 14 or equal- After Jan 1091142.82Inv#009 | [5 empty] | 1 | 1142.82 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1439 | 20200201-13 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-02-01 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Clearing access on all roads with Grader; | 6 | C156-C170 | Santoy Lake | 0 | 43870 |  | 40 | 43890 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting143920200201-13L.O.A.1210 | Corbiere and Sons Contracting143920200201-13L.O.A.1210Inv#009 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1439 | 20200201-13 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2020-02-01 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Clearing access on all roads with Grader; | 6 | C156-C170 | Santoy Lake | 0 | 43870 |  | 40 | 43890 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting143920200201-13Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting143920200201-13Operator - Principle - After Jan 1011825Inv#009 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1429 | 20200201-3 | 53520104 | Clearing | 0 | Chainsaw and consumables- After Jan 10 | 60 | 3 | unit/man/day | 0 | 0 |  |  | 180 | 23.4 | 203.4 | 2020-02-01 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling from A068; | 1 | A-055 to A-084 | Eldorado | 0 | 43870 |  | 36 | 43871 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting142920200201-3Chainsaw and consumables- After Jan 103180 | Corbiere and Sons Contracting142920200201-3Chainsaw and consumables- After Jan 103180Inv#009 |  |  | WF1-Handfalling |  |  | 1 | 180 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1429 | 20200201-3 | 53520104 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-02-01 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling from A068; | 1 | A-055 to A-084 | Eldorado | 0 | 43870 |  | 36 | 43871 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting142920200201-3Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting142920200201-3Light Truck - Pick up- After Jan 102487.5Inv#009 |  |  | WF1-Handfalling |  |  | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1429 | 20200201-3 | 53520104 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2020-02-01 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling from A068; | 1 | A-055 to A-084 | Eldorado | 0 | 43870 |  | 36 | 43871 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting142920200201-3Foreman121140 | Corbiere and Sons Contracting142920200201-3Foreman121140Inv#009 |  |  | WF1-Handfalling |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1429 | 20200201-3 | 53520104 | Clearing | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2020-02-01 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling from A068; | 1 | A-055 to A-084 | Eldorado | 0 | 43870 |  | 36 | 43871 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting142920200201-3L.O.A.4840 | Corbiere and Sons Contracting142920200201-3L.O.A.4840Inv#009 |  |  | WF1-Handfalling |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1429 | 20200201-3 | 53520104 | Clearing | 0 | Labourer - Specialized - After Jan 10 | 70 | 33 | HR |  |  | 70 | 0 | 2310 | 300.3 | 2610.3 | 2020-02-01 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling from A068; | 1 | A-055 to A-084 | Eldorado | 0 | 43870 |  | 36 | 43871 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting142920200201-3Labourer - Specialized - After Jan 10332310 | Corbiere and Sons Contracting142920200201-3Labourer - Specialized - After Jan 10332310Inv#009 |  |  | WF1-Handfalling |  |  | 1 | 2310 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1431 | 20200201-5 | 53510106 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 4 | Dynamic | 103.84 | 0 |  |  | 553.8 | 71.994 | 625.794 | 2020-02-01 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Final touch ups of Road and then walked out to be floated; | 1 | A128-B012 | Fish Hatchery | 0 | 43870 |  | 36 | 43871 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting143120200201-5Excavator - 30 ton- After Jan 104553.8 | Corbiere and Sons Contracting143120200201-5Excavator - 30 ton- After Jan 104553.8Inv#009 |  | WF1-Access | WF1-Access |  | 0 | 1 | 553.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1431 | 20200201-5 | 53510106 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 4 | HR | 9.16 | 0 |  |  | 48.84 | 6.3492 | 55.1892 | 2020-02-01 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Final touch ups of Road and then walked out to be floated; | 1 | A128-B012 | Fish Hatchery | 0 | 43870 |  | 36 | 43871 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting143120200201-5Excavator Thumb - 30 - 50 ton- After Jan 10448.84 | Corbiere and Sons Contracting143120200201-5Excavator Thumb - 30 - 50 ton- After Jan 10448.84Inv#009 |  | WF1-Access | WF1-Access |  | 0 | 1 | 48.84 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1431 | 20200201-5 | 53510106 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-02-01 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Final touch ups of Road and then walked out to be floated; | 1 | A128-B012 | Fish Hatchery | 0 | 43870 |  | 36 | 43871 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting143120200201-5Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting143120200201-5Light Truck - Pick up- After Jan 102487.5Inv#009 |  | WF1-Access | WF1-Access |  | 0 | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1431 | 20200201-5 | 53510106 | Access | 0 | Foreman | 95 | 6 | HR |  |  | 95 | 0 | 570 | 74.1 | 644.1 | 2020-02-01 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Final touch ups of Road and then walked out to be floated; | 1 | A128-B012 | Fish Hatchery | 0 | 43870 |  | 36 | 43871 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting143120200201-5Foreman6570 | Corbiere and Sons Contracting143120200201-5Foreman6570Inv#009 |  | WF1-Access | WF1-Access |  | 0 | 1 | 570 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1431 | 20200201-5 | 53510106 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-02-01 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Final touch ups of Road and then walked out to be floated; | 1 | A128-B012 | Fish Hatchery | 0 | 43870 |  | 36 | 43871 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting143120200201-5L.O.A.2420 | Corbiere and Sons Contracting143120200201-5L.O.A.2420Inv#009 |  | WF1-Access | WF1-Access |  | 0 | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1431 | 20200201-5 | 53510106 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5 | HR |  |  | 75 | 0 | 375 | 48.75 | 423.75 | 2020-02-01 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Winter Road Freeze-In |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Final touch ups of Road and then walked out to be floated; | 1 | A128-B012 | Fish Hatchery | 0 | 43870 |  | 36 | 43871 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting143120200201-5Operator - Principle - After Jan 105375 | Corbiere and Sons Contracting143120200201-5Operator - Principle - After Jan 105375Inv#009 |  | WF1-Access | WF1-Access |  | 0 | 1 | 375 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1432 | 20200201-6 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 9 | Dynamic | 98.61 | 0 |  |  | 1183.32 | 153.8316 | 1337.1516 | 2020-02-01 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer clearing access into Del Lake; | 6 | C186-C195 | Del Lake | 0 | 43870 |  | 40 | 43890 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting143220200201-6Dozer D6 or equal- After Jan 1091183.32 | Corbiere and Sons Contracting143220200201-6Dozer D6 or equal- After Jan 1091183.32Inv#009 | [5 empty] | 1 | 1183.32 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1432 | 20200201-6 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-02-01 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer clearing access into Del Lake; | 6 | C186-C195 | Del Lake | 0 | 43870 |  | 40 | 43890 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting143220200201-6Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting143220200201-6Light Truck - Pick up- After Jan 101243.75Inv#009 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1432 | 20200201-6 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-02-01 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer clearing access into Del Lake; | 6 | C186-C195 | Del Lake | 0 | 43870 |  | 40 | 43890 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting143220200201-6L.O.A.1210 | Corbiere and Sons Contracting143220200201-6L.O.A.1210Inv#009 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1432 | 20200201-6 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2020-02-01 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer clearing access into Del Lake; | 6 | C186-C195 | Del Lake | 0 | 43870 |  | 40 | 43890 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting143220200201-6Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting143220200201-6Operator - Principle - After Jan 1011825Inv#009 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1495 | 20200202-10 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 9 | Dynamic | 98.61 | 0 |  |  | 1183.32 | 153.8316 | 1337.1516 | 2020-02-02 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Access Maintenance for all road in Lake A; | 6 | C129-C151 | Lake A | 0 | 43871 |  | 40 | 43889 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting149520200202-10Dozer D6 or equal- After Jan 1091183.32 | Corbiere and Sons Contracting149520200202-10Dozer D6 or equal- After Jan 1091183.32Inv#009 | [5 empty] | 1 | 1183.32 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1495 | 20200202-10 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-02-02 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Access Maintenance for all road in Lake A; | 6 | C129-C151 | Lake A | 0 | 43871 |  | 40 | 43889 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting149520200202-10L.O.A.1210 | Corbiere and Sons Contracting149520200202-10L.O.A.1210Inv#009 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1495 | 20200202-10 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2020-02-02 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Access Maintenance for all road in Lake A; | 6 | C129-C151 | Lake A | 0 | 43871 |  | 40 | 43889 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting149520200202-10Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting149520200202-10Operator - Principle - After Jan 1011825Inv#009 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1488 | 20200202-3 | 53520104 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-02-02 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Checked out A082 area and then walked and prepped area from A062-A069; | 1 | A-055 to A-084 | Eldorado | 1 | 43871 |  | 36 | 43873 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting148820200202-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting148820200202-3Light Truck - Pick up- After Jan 101243.75Inv#009 |  |  | WF1-Handfalling |  |  | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1488 | 20200202-3 | 53520104 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2020-02-02 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Checked out A082 area and then walked and prepped area from A062-A069; | 1 | A-055 to A-084 | Eldorado | 1 | 43871 |  | 36 | 43873 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting148820200202-3Foreman121140 | Corbiere and Sons Contracting148820200202-3Foreman121140Inv#009 |  |  | WF1-Handfalling |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1488 | 20200202-3 | 53520104 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-02-02 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Checked out A082 area and then walked and prepped area from A062-A069; | 1 | A-055 to A-084 | Eldorado | 1 | 43871 |  | 36 | 43873 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting148820200202-3L.O.A.1210 | Corbiere and Sons Contracting148820200202-3L.O.A.1210Inv#009 |  |  | WF1-Handfalling |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1493 | 20200202-8 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 9 | Dynamic | 95.24 | 0 |  |  | 1142.82 | 148.5666 | 1291.3866 | 2020-02-02 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Clearing snow for all access roads; | 6 | C156-C170 | Santoy Lake | 0 | 43871 |  | 40 | 43889 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting149320200202-8Grader - Cat 12 to 14 or equal- After Jan 1091142.82 | Corbiere and Sons Contracting149320200202-8Grader - Cat 12 to 14 or equal- After Jan 1091142.82Inv#009 | [5 empty] | 1 | 1142.82 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1493 | 20200202-8 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-02-02 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Clearing snow for all access roads; | 6 | C156-C170 | Santoy Lake | 0 | 43871 |  | 40 | 43889 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting149320200202-8L.O.A.1210 | Corbiere and Sons Contracting149320200202-8L.O.A.1210Inv#009 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1493 | 20200202-8 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2020-02-02 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Clearing snow for all access roads; | 6 | C156-C170 | Santoy Lake | 0 | 43871 |  | 40 | 43889 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting149320200202-8Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting149320200202-8Operator - Principle - After Jan 1011825Inv#009 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1456 | 20200203-13 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 9 | Dynamic | 95.24 | 0 |  |  | 1142.82 | 148.5666 | 1291.3866 | 2020-02-03 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Maintenance of access roads; | 6 | C156-C170 | Santoy Lake | 0 | 43871 |  | 40 | 43896 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting145620200203-13Grader - Cat 12 to 14 or equal- After Jan 1091142.82 | Corbiere and Sons Contracting145620200203-13Grader - Cat 12 to 14 or equal- After Jan 1091142.82Inv#018 | [5 empty] | 1 | 1142.82 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1456 | 20200203-13 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-02-03 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Maintenance of access roads; | 6 | C156-C170 | Santoy Lake | 0 | 43871 |  | 40 | 43896 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting145620200203-13L.O.A.1210 | Corbiere and Sons Contracting145620200203-13L.O.A.1210Inv#018 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1456 | 20200203-13 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2020-02-03 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Maintenance of access roads; | 6 | C156-C170 | Santoy Lake | 0 | 43871 |  | 40 | 43896 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting145620200203-13Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting145620200203-13Operator - Principle - After Jan 1011825Inv#018 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1458 | 20200203-15 | 53510611 | Access | 0 | Loader JD 524 to 624 or equal | 99 | 6 | HR | 74.25 | 0 |  |  | 594 | 77.22 | 671.22 | 2020-02-03 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Clearing access into Middleton Road; | 6 | C210-C214 | Middleton Road | 0 | 43871 |  | 40 | 43890 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting145820200203-15Loader JD 524 to 624 or equal6594 | Corbiere and Sons Contracting145820200203-15Loader JD 524 to 624 or equal6594Inv#009 | [5 empty] | 1 | 594 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1458 | 20200203-15 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-02-03 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Clearing access into Middleton Road; | 6 | C210-C214 | Middleton Road | 0 | 43871 |  | 40 | 43890 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting145820200203-15L.O.A.1210 | Corbiere and Sons Contracting145820200203-15L.O.A.1210Inv#009 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1458 | 20200203-15 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 75 | 0 | 450 | 58.5 | 508.5 | 2020-02-03 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Clearing access into Middleton Road; | 6 | C210-C214 | Middleton Road | 0 | 43871 |  | 40 | 43890 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting145820200203-15Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting145820200203-15Operator - Principle - After Jan 106450Inv#009 | [5 empty] | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1446 | 20200203-3 | 53520104 | Clearing | 0 | Chainsaw and consumables- After Jan 10 | 60 | 4 | unit/man/day | 0 | 0 |  |  | 240 | 31.2 | 271.2 | 2020-02-03 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling from A068-A067; | 1 | A-055 to A-084 | Eldorado | 0 | 43871 |  | 36 | 43871 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting144620200203-3Chainsaw and consumables- After Jan 104240 | Corbiere and Sons Contracting144620200203-3Chainsaw and consumables- After Jan 104240Inv#009 |  |  | WF1-Handfalling |  |  | 1 | 240 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1446 | 20200203-3 | 53520104 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-02-03 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling from A068-A067; | 1 | A-055 to A-084 | Eldorado | 0 | 43871 |  | 36 | 43871 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting144620200203-3Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting144620200203-3Light Truck - Pick up- After Jan 102487.5Inv#009 |  |  | WF1-Handfalling |  |  | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1446 | 20200203-3 | 53520104 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2020-02-03 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling from A068-A067; | 1 | A-055 to A-084 | Eldorado | 0 | 43871 |  | 36 | 43871 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting144620200203-3Foreman121140 | Corbiere and Sons Contracting144620200203-3Foreman121140Inv#009 |  |  | WF1-Handfalling |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1446 | 20200203-3 | 53520104 | Clearing | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2020-02-03 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling from A068-A067; | 1 | A-055 to A-084 | Eldorado | 0 | 43871 |  | 36 | 43871 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting144620200203-3L.O.A.51050 | Corbiere and Sons Contracting144620200203-3L.O.A.51050Inv#009 |  |  | WF1-Handfalling |  |  | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1446 | 20200203-3 | 53520104 | Clearing | 0 | Labourer - Specialized - After Jan 10 | 70 | 44 | HR |  |  | 70 | 0 | 3080 | 400.4 | 3480.4 | 2020-02-03 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling from A068-A067; | 1 | A-055 to A-084 | Eldorado | 0 | 43871 |  | 36 | 43871 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting144620200203-3Labourer - Specialized - After Jan 10443080 | Corbiere and Sons Contracting144620200203-3Labourer - Specialized - After Jan 10443080Inv#009 |  |  | WF1-Handfalling |  |  | 1 | 3080 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1448 | 20200203-5 | 53520104 | Clearing | 0 | Chainsaw and consumables- After Jan 10 | 60 | 3 | unit/man/day | 0 | 0 |  |  | 180 | 23.4 | 203.4 | 2020-02-03 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling from A098-A096; | 1 | A-085 to A-117 | Windfarm | 0 | 43871 |  | 36 | 43871 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting144820200203-5Chainsaw and consumables- After Jan 103180 | Corbiere and Sons Contracting144820200203-5Chainsaw and consumables- After Jan 103180Inv#009 |  |  | WF1-Handfalling |  |  | 1 | 180 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1448 | 20200203-5 | 53520104 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-02-03 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling from A098-A096; | 1 | A-085 to A-117 | Windfarm | 0 | 43871 |  | 36 | 43871 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting144820200203-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting144820200203-5Light Truck - Pick up- After Jan 101243.75Inv#009 |  |  | WF1-Handfalling |  |  | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1448 | 20200203-5 | 53520104 | Clearing | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2020-02-03 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling from A098-A096; | 1 | A-085 to A-117 | Windfarm | 0 | 43871 |  | 36 | 43871 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting144820200203-5L.O.A.3630 | Corbiere and Sons Contracting144820200203-5L.O.A.3630Inv#009 |  |  | WF1-Handfalling |  |  | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1448 | 20200203-5 | 53520104 | Clearing | 0 | Labourer - Specialized - After Jan 10 | 70 | 33 | HR |  |  | 70 | 0 | 2310 | 300.3 | 2610.3 | 2020-02-03 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling from A098-A096; | 1 | A-085 to A-117 | Windfarm | 0 | 43871 |  | 36 | 43871 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting144820200203-5Labourer - Specialized - After Jan 10332310 | Corbiere and Sons Contracting144820200203-5Labourer - Specialized - After Jan 10332310Inv#009 |  |  | WF1-Handfalling |  |  | 1 | 2310 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1449 | 20200203-6-R1 | 53520104 | Clearing | 0 | Chainsaw and consumables- After Jan 10 | 60 | 4 | unit/man/day | 0 | 0 |  |  | 240 | 31.2 | 271.2 | 2020-02-03 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling | 1 | A-128 to B-017 | Wolf Lake | 0 | 43886 |  | 37 | 43888 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting144920200203-6-R1Chainsaw and consumables- After Jan 104240 | Corbiere and Sons Contracting144920200203-6-R1Chainsaw and consumables- After Jan 104240Inv#009 |  |  | WF1-Handfalling |  |  | 1 | 240 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1449 | 20200203-6-R1 | 53520104 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2020-02-03 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling | 1 | A-128 to B-017 | Wolf Lake | 0 | 43886 |  | 37 | 43888 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting144920200203-6-R1Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting144920200203-6-R1Light Truck - Pick up- After Jan 103731.25Inv#009 |  |  | WF1-Handfalling |  |  | 1 | 731.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1449 | 20200203-6-R1 | 53520104 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2020-02-03 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling | 1 | A-128 to B-017 | Wolf Lake | 0 | 43886 |  | 37 | 43888 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting144920200203-6-R1Foreman121140 | Corbiere and Sons Contracting144920200203-6-R1Foreman121140Inv#009 |  |  | WF1-Handfalling |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1449 | 20200203-6-R1 | 53520104 | Clearing | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2020-02-03 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling | 1 | A-128 to B-017 | Wolf Lake | 0 | 43886 |  | 37 | 43888 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting144920200203-6-R1L.O.A.61260 | Corbiere and Sons Contracting144920200203-6-R1L.O.A.61260Inv#009 |  |  | WF1-Handfalling |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1449 | 20200203-6-R1 | 53520104 | Clearing | 0 | Labourer - Specialized - After Jan 10 | 70 | 49 | HR |  |  | 70 | 0 | 3430 | 445.9 | 3875.9 | 2020-02-03 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling | 1 | A-128 to B-017 | Wolf Lake | 0 | 43886 |  | 37 | 43888 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting144920200203-6-R1Labourer - Specialized - After Jan 10493430 | Corbiere and Sons Contracting144920200203-6-R1Labourer - Specialized - After Jan 10493430Inv#009 |  |  | WF1-Handfalling |  |  | 1 | 3430 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1450 | 20200203-7 | 53510107 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 2 | Dynamic | 103.84 | 0 |  |  | 276.9 | 35.997 | 312.897 | 2020-02-03 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Access Mob/Demob |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Mobilization to A118 for Bridge; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43871 |  | 36 | 43871 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting145020200203-7Excavator - 30 ton- After Jan 102276.9 | Corbiere and Sons Contracting145020200203-7Excavator - 30 ton- After Jan 102276.9Inv#009 |  | WF1 Mob/Demob | WF1 Mob/Demob |  | 1 | 1 | 276.9 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1450 | 20200203-7 | 53510107 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 4 | Dynamic | 91.79 | 0 |  |  | 489.56 | 63.6428 | 553.2028 | 2020-02-03 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Access Mob/Demob |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Mobilization to A118 for Bridge; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43871 |  | 36 | 43871 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting145020200203-7Tractor Trailer - 60 Ton- After Jan 104489.56 | Corbiere and Sons Contracting145020200203-7Tractor Trailer - 60 Ton- After Jan 104489.56Inv#009 |  | WF1 Mob/Demob | WF1 Mob/Demob |  | 1 | 1 | 489.56 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1450 | 20200203-7 | 53510107 | Access | 0 | Foreman | 95 | 3 | HR |  |  | 95 | 0 | 285 | 37.05 | 322.05 | 2020-02-03 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Access Mob/Demob |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Mobilization to A118 for Bridge; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43871 |  | 36 | 43871 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting145020200203-7Foreman3285 | Corbiere and Sons Contracting145020200203-7Foreman3285Inv#009 |  | WF1 Mob/Demob | WF1 Mob/Demob |  | 1 | 1 | 285 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1450 | 20200203-7 | 53510107 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2020-02-03 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Access Mob/Demob |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Mobilization to A118 for Bridge; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43871 |  | 36 | 43871 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting145020200203-7L.O.A.3630 | Corbiere and Sons Contracting145020200203-7L.O.A.3630Inv#009 |  | WF1 Mob/Demob | WF1 Mob/Demob |  | 1 | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1450 | 20200203-7 | 53510107 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 3 | HR |  |  | 75 | 0 | 225 | 29.25 | 254.25 | 2020-02-03 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Access Mob/Demob |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Mobilization to A118 for Bridge; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43871 |  | 36 | 43871 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting145020200203-7Operator - Principle - After Jan 103225 | Corbiere and Sons Contracting145020200203-7Operator - Principle - After Jan 103225Inv#009 |  | WF1 Mob/Demob | WF1 Mob/Demob |  | 1 | 1 | 225 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1450 | 20200203-7 | 53510107 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 5 | HR |  |  | 70 | 0 | 350 | 45.5 | 395.5 | 2020-02-03 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Access Mob/Demob |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Mobilization to A118 for Bridge; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43871 |  | 36 | 43871 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting145020200203-7Operator - Intermdiate - After Jan 105350 | Corbiere and Sons Contracting145020200203-7Operator - Intermdiate - After Jan 105350Inv#009 |  | WF1 Mob/Demob | WF1 Mob/Demob |  | 1 | 1 | 350 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1452 | 20200203-9 | 53520102 | Clearing | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 4 | Dynamic | 98.61 | 0 |  |  | 525.92 | 68.3696 | 594.2896 | 2020-02-03 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Realigning road and maintenance at B061; | 2 |  | Lofty Davies | 0 | 43871 |  | 36 | 43871 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting145220200203-9Dozer D6 or equal- After Jan 104525.92 | Corbiere and Sons Contracting145220200203-9Dozer D6 or equal- After Jan 104525.92Inv#009 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 525.92 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1452 | 20200203-9 | 53520102 | Clearing | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 8 | Dynamic | 110.22 | 0 |  |  | 1175.68 | 152.8384 | 1328.5184 | 2020-02-03 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Realigning road and maintenance at B061; | 2 |  | Lofty Davies | 0 | 43871 |  | 36 | 43871 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting145220200203-9Excavator - 36 ton- After Jan 1081175.68 | Corbiere and Sons Contracting145220200203-9Excavator - 36 ton- After Jan 1081175.68Inv#009 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1175.68 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1452 | 20200203-9 | 53520102 | Clearing | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 8 | HR | 9.16 | 0 |  |  | 97.68 | 12.6984 | 110.3784 | 2020-02-03 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Realigning road and maintenance at B061; | 2 |  | Lofty Davies | 0 | 43871 |  | 36 | 43871 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting145220200203-9Excavator Thumb - 30 - 50 ton- After Jan 10897.68 | Corbiere and Sons Contracting145220200203-9Excavator Thumb - 30 - 50 ton- After Jan 10897.68Inv#009 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 97.68 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1452 | 20200203-9 | 53520102 | Clearing | 0 | Sander Truck - Forestry- After Jan 10 | 86.38 | 3 | Dynamic | 64.79 | 0 |  |  | 259.14 | 33.6882 | 292.8282 | 2020-02-03 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Realigning road and maintenance at B061; | 2 |  | Lofty Davies | 0 | 43871 |  | 36 | 43871 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting145220200203-9Sander Truck - Forestry- After Jan 103259.14 | Corbiere and Sons Contracting145220200203-9Sander Truck - Forestry- After Jan 103259.14Inv#009 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 259.14 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1452 | 20200203-9 | 53520102 | Clearing | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 3 | Dynamic | 91.79 | 0 |  |  | 367.17 | 47.7321 | 414.9021 | 2020-02-03 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Realigning road and maintenance at B061; | 2 |  | Lofty Davies | 0 | 43871 |  | 36 | 43871 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting145220200203-9Tractor Trailer - 60 Ton- After Jan 103367.17 | Corbiere and Sons Contracting145220200203-9Tractor Trailer - 60 Ton- After Jan 103367.17Inv#009 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 367.17 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1452 | 20200203-9 | 53520102 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-02-03 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Realigning road and maintenance at B061; | 2 |  | Lofty Davies | 0 | 43871 |  | 36 | 43871 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting145220200203-9L.O.A.2420 | Corbiere and Sons Contracting145220200203-9L.O.A.2420Inv#009 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1452 | 20200203-9 | 53520102 | Clearing | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2020-02-03 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Realigning road and maintenance at B061; | 2 |  | Lofty Davies | 0 | 43871 |  | 36 | 43871 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting145220200203-9Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting145220200203-9Operator - Principle - After Jan 1012900Inv#009 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1452 | 20200203-9 | 53520102 | Clearing | 0 | Driver - AZ - After Jan 10 | 70 | 6 | HR |  |  | 70 | 0 | 420 | 54.6 | 474.6 | 2020-02-03 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Realigning road and maintenance at B061; | 2 |  | Lofty Davies | 0 | 43871 |  | 36 | 43871 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting145220200203-9Driver - AZ - After Jan 106420 | Corbiere and Sons Contracting145220200203-9Driver - AZ - After Jan 106420Inv#009 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1503 | 20200204-3 | 53520104 | Clearing | 0 | Chainsaw and consumables- After Jan 10 | 60 | 6 | unit/man/day | 0 | 0 |  |  | 360 | 46.8 | 406.8 | 2020-02-04 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling at A067 and A064; | 1 | A-055 to A-084 | Eldorado | 0 | 43871 |  | 36 | 43873 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting150320200204-3Chainsaw and consumables- After Jan 106360 | Corbiere and Sons Contracting150320200204-3Chainsaw and consumables- After Jan 106360Inv#009 |  |  | WF1-Handfalling |  |  | 1 | 360 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1503 | 20200204-3 | 53520104 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2020-02-04 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling at A067 and A064; | 1 | A-055 to A-084 | Eldorado | 0 | 43871 |  | 36 | 43873 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting150320200204-3Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting150320200204-3Light Truck - Pick up- After Jan 103731.25Inv#009 |  |  | WF1-Handfalling |  |  | 1 | 731.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1503 | 20200204-3 | 53520104 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2020-02-04 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling at A067 and A064; | 1 | A-055 to A-084 | Eldorado | 0 | 43871 |  | 36 | 43873 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting150320200204-3Foreman121140 | Corbiere and Sons Contracting150320200204-3Foreman121140Inv#009 |  |  | WF1-Handfalling |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1503 | 20200204-3 | 53520104 | Clearing | 0 | L.O.A. | 210 | 7 | DAY |  |  |  | 0 | 1470 | 191.1 | 1661.1 | 2020-02-04 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling at A067 and A064; | 1 | A-055 to A-084 | Eldorado | 0 | 43871 |  | 36 | 43873 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting150320200204-3L.O.A.71470 | Corbiere and Sons Contracting150320200204-3L.O.A.71470Inv#009 |  |  | WF1-Handfalling |  |  | 1 | 1470 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1503 | 20200204-3 | 53520104 | Clearing | 0 | Labourer - Specialized - After Jan 10 | 70 | 66 | HR |  |  | 70 | 0 | 4620 | 600.6 | 5220.6 | 2020-02-04 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling at A067 and A064; | 1 | A-055 to A-084 | Eldorado | 0 | 43871 |  | 36 | 43873 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting150320200204-3Labourer - Specialized - After Jan 10664620 | Corbiere and Sons Contracting150320200204-3Labourer - Specialized - After Jan 10664620Inv#009 |  |  | WF1-Handfalling |  |  | 1 | 4620 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1505 | 20200204-5 | 53520104 | Clearing | 0 | Chainsaw and consumables- After Jan 10 | 60 | 5 | unit/man/day | 0 | 0 |  |  | 300 | 39 | 339 | 2020-02-04 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling from A126-A127; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43871 |  | 36 | 43873 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting150520200204-5Chainsaw and consumables- After Jan 105300 | Corbiere and Sons Contracting150520200204-5Chainsaw and consumables- After Jan 105300Inv#009 |  |  | WF1-Handfalling |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1505 | 20200204-5 | 53520104 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2020-02-04 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling from A126-A127; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43871 |  | 36 | 43873 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting150520200204-5Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting150520200204-5Light Truck - Pick up- After Jan 103731.25Inv#009 |  |  | WF1-Handfalling |  |  | 1 | 731.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1505 | 20200204-5 | 53520104 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2020-02-04 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling from A126-A127; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43871 |  | 36 | 43873 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting150520200204-5Foreman121140 | Corbiere and Sons Contracting150520200204-5Foreman121140Inv#009 |  |  | WF1-Handfalling |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1505 | 20200204-5 | 53520104 | Clearing | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2020-02-04 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling from A126-A127; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43871 |  | 36 | 43873 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting150520200204-5L.O.A.61260 | Corbiere and Sons Contracting150520200204-5L.O.A.61260Inv#009 |  |  | WF1-Handfalling |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1505 | 20200204-5 | 53520104 | Clearing | 0 | Labourer - Specialized - After Jan 10 | 70 | 55 | HR |  |  | 70 | 0 | 3850 | 500.5 | 4350.5 | 2020-02-04 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling from A126-A127; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43871 |  | 36 | 43873 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting150520200204-5Labourer - Specialized - After Jan 10553850 | Corbiere and Sons Contracting150520200204-5Labourer - Specialized - After Jan 10553850Inv#009 |  |  | WF1-Handfalling |  |  | 1 | 3850 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1507 | 20200204-7 | 53510211 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 6 | Dynamic | 98.61 | 0 |  |  | 788.88 | 102.5544 | 891.4344 | 2020-02-04 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Clearing Snow and Rd. Repair at B066; | 2 | B065-B077 | Red Rock | 0 | 43871 |  | 36 | 43873 | [5 empty] | Mike Lecocq | 02 | Corbiere and Sons Contracting150720200204-7Dozer D6 or equal- After Jan 106788.88 | Corbiere and Sons Contracting150720200204-7Dozer D6 or equal- After Jan 106788.88Inv#009 | [5 empty] | 1 | 788.88 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1507 | 20200204-7 | 53510211 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 1 | Dynamic | 110.22 | 0 |  |  | 146.96 | 19.1048 | 166.0648 | 2020-02-04 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Clearing Snow and Rd. Repair at B066; | 2 | B065-B077 | Red Rock | 0 | 43871 |  | 36 | 43873 | [5 empty] | Mike Lecocq | 02 | Corbiere and Sons Contracting150720200204-7Excavator - 36 ton- After Jan 101146.96 | Corbiere and Sons Contracting150720200204-7Excavator - 36 ton- After Jan 101146.96Inv#009 | [5 empty] | 1 | 146.96 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1507 | 20200204-7 | 53510211 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 1 | HR | 9.16 | 0 |  |  | 12.21 | 1.5873 | 13.7973 | 2020-02-04 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Clearing Snow and Rd. Repair at B066; | 2 | B065-B077 | Red Rock | 0 | 43871 |  | 36 | 43873 | [5 empty] | Mike Lecocq | 02 | Corbiere and Sons Contracting150720200204-7Excavator Thumb - 30 - 50 ton- After Jan 10112.21 | Corbiere and Sons Contracting150720200204-7Excavator Thumb - 30 - 50 ton- After Jan 10112.21Inv#009 | [5 empty] | 1 | 12.21 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1507 | 20200204-7 | 53510211 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-02-04 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Clearing Snow and Rd. Repair at B066; | 2 | B065-B077 | Red Rock | 0 | 43871 |  | 36 | 43873 | [5 empty] | Mike Lecocq | 02 | Corbiere and Sons Contracting150720200204-7L.O.A.1210 | Corbiere and Sons Contracting150720200204-7L.O.A.1210Inv#009 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1507 | 20200204-7 | 53510211 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 7 | HR |  |  | 75 | 0 | 525 | 68.25 | 593.25 | 2020-02-04 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Clearing Snow and Rd. Repair at B066; | 2 | B065-B077 | Red Rock | 0 | 43871 |  | 36 | 43873 | [5 empty] | Mike Lecocq | 02 | Corbiere and Sons Contracting150720200204-7Operator - Principle - After Jan 107525 | Corbiere and Sons Contracting150720200204-7Operator - Principle - After Jan 107525Inv#009 | [5 empty] | 1 | 525 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1630 | 20200205-19 | 53510611 | Access | 0 | 3rd Party Charges | 1 | 2662.36 | unit |  |  |  |  | 2662.36 | 346.1068 | 3008.4668 | 2020-02-05 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Invoice for Screened sand and 4.5 hours to open up pit a pit | 0 |  |  | 0 | 43876 |  | 40 | 43887 | 17672 | Screened Sand and 4.5 hours to open up pit |  |  |  | Dean MacArthur | 06 | Corbiere and Sons Contracting163020200205-193rd Party Charges2662.362662.36 | Corbiere and Sons Contracting163020200205-193rd Party Charges2662.362662.36Inv#009 | [5 empty] | 1 | 2662.36 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1539 | 20200205-21 | 53510611 | Access | 0 | 3rd Party Charges | 1 | 1122.54 | unit |  |  |  |  | 1122.54 | 145.9302 | 1268.4702 | 2020-02-05 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Crusher Dust and Winter Sand | 6 |  |  | 0 | 43876 |  | 40 | 43886 | 114266 |  |  |  |  | Dean MacArthur | 06 | Corbiere and Sons Contracting153920200205-213rd Party Charges1122.541122.54 | Corbiere and Sons Contracting153920200205-213rd Party Charges1122.541122.54Inv#009 | [5 empty] | 1 | 1122.54 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1519 | 20200205-3 | 53520104 | Clearing | 0 | Chainsaw and consumables- After Jan 10 | 60 | 5 | unit/man/day | 0 | 0 |  |  | 300 | 39 | 339 | 2020-02-05 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling from A067 and A064; | 1 | A-055 to A-084 | Eldorado | 0 | 43871 |  | 36 | 43874 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting151920200205-3Chainsaw and consumables- After Jan 105300 | Corbiere and Sons Contracting151920200205-3Chainsaw and consumables- After Jan 105300Inv#009 |  |  | WF1-Handfalling |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1519 | 20200205-3 | 53520104 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2020-02-05 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling from A067 and A064; | 1 | A-055 to A-084 | Eldorado | 0 | 43871 |  | 36 | 43874 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting151920200205-3Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting151920200205-3Light Truck - Pick up- After Jan 103731.25Inv#009 |  |  | WF1-Handfalling |  |  | 1 | 731.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1519 | 20200205-3 | 53520104 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2020-02-05 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling from A067 and A064; | 1 | A-055 to A-084 | Eldorado | 0 | 43871 |  | 36 | 43874 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting151920200205-3Foreman121140 | Corbiere and Sons Contracting151920200205-3Foreman121140Inv#009 |  |  | WF1-Handfalling |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1519 | 20200205-3 | 53520104 | Clearing | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2020-02-05 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling from A067 and A064; | 1 | A-055 to A-084 | Eldorado | 0 | 43871 |  | 36 | 43874 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting151920200205-3L.O.A.61260 | Corbiere and Sons Contracting151920200205-3L.O.A.61260Inv#009 |  |  | WF1-Handfalling |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1519 | 20200205-3 | 53520104 | Clearing | 0 | Labourer - Specialized - After Jan 10 | 70 | 55 | HR |  |  | 70 | 0 | 3850 | 500.5 | 4350.5 | 2020-02-05 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling from A067 and A064; | 1 | A-055 to A-084 | Eldorado | 0 | 43871 |  | 36 | 43874 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting151920200205-3Labourer - Specialized - After Jan 10553850 | Corbiere and Sons Contracting151920200205-3Labourer - Specialized - After Jan 10553850Inv#009 |  |  | WF1-Handfalling |  |  | 1 | 3850 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1520 | 20200205-4 | 53510111 | Access | 0 | Loader JD 524 to 624 or equal | 99 | 2 | HR | 74.25 | 0 |  |  | 198 | 25.74 | 223.74 | 2020-02-05 | 1 | Inv#018 | 43923 | 88 | 0 | 1 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 14 | Approved | snow removal on assembly and crane pads - ongoing | 9013 | Clearing pads for Valard | 1 | A-055 to A-084 | Eldorado | 1 | 43871 |  | 36 | 43874 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting152020200205-4Loader JD 524 to 624 or equal2198 | Corbiere and Sons Contracting152020200205-4Loader JD 524 to 624 or equal2198Inv#018 | [5 empty] | 1 | 198 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1520 | 20200205-4 | 53510111 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 5 | Dynamic | 110.22 | 0 |  |  | 734.8 | 95.524 | 830.324 | 2020-02-05 | 1 | Inv#018 | 43923 | 88 | 0 | 1 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 14 | Approved | snow removal on assembly and crane pads - ongoing | 9013 | Clearing pads for Valard | 1 | A-055 to A-084 | Eldorado | 1 | 43871 |  | 36 | 43874 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting152020200205-4Excavator - 36 ton- After Jan 105734.8 | Corbiere and Sons Contracting152020200205-4Excavator - 36 ton- After Jan 105734.8Inv#018 | [5 empty] | 1 | 734.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1520 | 20200205-4 | 53510111 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-02-05 | 1 | Inv#018 | 43923 | 88 | 0 | 1 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 14 | Approved | snow removal on assembly and crane pads - ongoing | 9013 | Clearing pads for Valard | 1 | A-055 to A-084 | Eldorado | 1 | 43871 |  | 36 | 43874 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting152020200205-4L.O.A.1210 | Corbiere and Sons Contracting152020200205-4L.O.A.1210Inv#018 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1520 | 20200205-4 | 53510111 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 8 | HR |  |  | 75 | 0 | 600 | 78 | 678 | 2020-02-05 | 1 | Inv#018 | 43923 | 88 | 0 | 1 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 14 | Approved | snow removal on assembly and crane pads - ongoing | 9013 | Clearing pads for Valard | 1 | A-055 to A-084 | Eldorado | 1 | 43871 |  | 36 | 43874 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting152020200205-4Operator - Principle - After Jan 108600 | Corbiere and Sons Contracting152020200205-4Operator - Principle - After Jan 108600Inv#018 | [5 empty] | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1521 | 20200205-5 | 53520104 | Clearing | 0 | Chainsaw and consumables- After Jan 10 | 60 | 5 | unit/man/day | 0 | 0 |  |  | 300 | 39 | 339 | 2020-02-05 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling from A127-A128; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43871 |  | 36 | 43874 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting152120200205-5Chainsaw and consumables- After Jan 105300 | Corbiere and Sons Contracting152120200205-5Chainsaw and consumables- After Jan 105300Inv#009 |  |  | WF1-Handfalling |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1521 | 20200205-5 | 53520104 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2020-02-05 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling from A127-A128; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43871 |  | 36 | 43874 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting152120200205-5Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting152120200205-5Light Truck - Pick up- After Jan 103731.25Inv#009 |  |  | WF1-Handfalling |  |  | 1 | 731.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1521 | 20200205-5 | 53520104 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2020-02-05 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling from A127-A128; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43871 |  | 36 | 43874 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting152120200205-5Foreman121140 | Corbiere and Sons Contracting152120200205-5Foreman121140Inv#009 |  |  | WF1-Handfalling |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1521 | 20200205-5 | 53520104 | Clearing | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2020-02-05 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling from A127-A128; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43871 |  | 36 | 43874 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting152120200205-5L.O.A.61260 | Corbiere and Sons Contracting152120200205-5L.O.A.61260Inv#009 |  |  | WF1-Handfalling |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1521 | 20200205-5 | 53520104 | Clearing | 0 | Labourer - Specialized - After Jan 10 | 70 | 55 | HR |  |  | 70 | 0 | 3850 | 500.5 | 4350.5 | 2020-02-05 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling from A127-A128; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43871 |  | 36 | 43874 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting152120200205-5Labourer - Specialized - After Jan 10553850 | Corbiere and Sons Contracting152120200205-5Labourer - Specialized - After Jan 10553850Inv#009 |  |  | WF1-Handfalling |  |  | 1 | 3850 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1542 | 20200206-3 | 53520104 | Clearing | 0 | Chainsaw and consumables- After Jan 10 | 60 | 5 | unit/man/day | 0 | 0 |  |  | 300 | 39 | 339 | 2020-02-06 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling from A067 and A064-A063; | 1 | A-055 to A-084 | Eldorado | 0 | 43880 |  | 37 | 43883 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting154220200206-3Chainsaw and consumables- After Jan 105300 | Corbiere and Sons Contracting154220200206-3Chainsaw and consumables- After Jan 105300Inv#018 |  |  | WF1-Handfalling |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1542 | 20200206-3 | 53520104 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2020-02-06 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling from A067 and A064-A063; | 1 | A-055 to A-084 | Eldorado | 0 | 43880 |  | 37 | 43883 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting154220200206-3Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting154220200206-3Light Truck - Pick up- After Jan 103731.25Inv#018 |  |  | WF1-Handfalling |  |  | 1 | 731.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1542 | 20200206-3 | 53520104 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2020-02-06 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling from A067 and A064-A063; | 1 | A-055 to A-084 | Eldorado | 0 | 43880 |  | 37 | 43883 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting154220200206-3Foreman121140 | Corbiere and Sons Contracting154220200206-3Foreman121140Inv#018 |  |  | WF1-Handfalling |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1542 | 20200206-3 | 53520104 | Clearing | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2020-02-06 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling from A067 and A064-A063; | 1 | A-055 to A-084 | Eldorado | 0 | 43880 |  | 37 | 43883 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting154220200206-3L.O.A.61260 | Corbiere and Sons Contracting154220200206-3L.O.A.61260Inv#018 |  |  | WF1-Handfalling |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1542 | 20200206-3 | 53520104 | Clearing | 0 | Labourer - Specialized - After Jan 10 | 70 | 55 | HR |  |  | 70 | 0 | 3850 | 500.5 | 4350.5 | 2020-02-06 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling from A067 and A064-A063; | 1 | A-055 to A-084 | Eldorado | 0 | 43880 |  | 37 | 43883 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting154220200206-3Labourer - Specialized - After Jan 10553850 | Corbiere and Sons Contracting154220200206-3Labourer - Specialized - After Jan 10553850Inv#018 |  |  | WF1-Handfalling |  |  | 1 | 3850 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1543 | 20200206-4 | 53510111 | Access | 0 | Loader JD 524 to 624 or equal | 99 | 9 | HR | 74.25 | 0 |  |  | 891 | 115.83 | 1006.83 | 2020-02-06 | 1 | Inv#018 | 43923 | 88 | 0 | 1 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 14 | Approved | snow removal on assembly and crane pads - ongoing | 9013 | Clearing pads for Valard from A084-A087; | 1 | A-085 to A-117 | Windfarm | 1 | 43880 |  | 37 | 43883 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting154320200206-4Loader JD 524 to 624 or equal9891 | Corbiere and Sons Contracting154320200206-4Loader JD 524 to 624 or equal9891Inv#018 | [5 empty] | 1 | 891 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1543 | 20200206-4 | 53510111 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-02-06 | 1 | Inv#018 | 43923 | 88 | 0 | 1 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 14 | Approved | snow removal on assembly and crane pads - ongoing | 9013 | Clearing pads for Valard from A084-A087; | 1 | A-085 to A-117 | Windfarm | 1 | 43880 |  | 37 | 43883 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting154320200206-4L.O.A.1210 | Corbiere and Sons Contracting154320200206-4L.O.A.1210Inv#018 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1543 | 20200206-4 | 53510111 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2020-02-06 | 1 | Inv#018 | 43923 | 88 | 0 | 1 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 14 | Approved | snow removal on assembly and crane pads - ongoing | 9013 | Clearing pads for Valard from A084-A087; | 1 | A-085 to A-117 | Windfarm | 1 | 43880 |  | 37 | 43883 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting154320200206-4Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting154320200206-4Operator - Principle - After Jan 1011825Inv#018 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1545 | 20200206-6 | 53520104 | Clearing | 0 | Chainsaw and consumables- After Jan 10 | 60 | 5 | unit/man/day | 0 | 0 |  |  | 300 | 39 | 339 | 2020-02-06 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling from A129; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43880 |  | 37 | 43883 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting154520200206-6Chainsaw and consumables- After Jan 105300 | Corbiere and Sons Contracting154520200206-6Chainsaw and consumables- After Jan 105300Inv#018 |  |  | WF1-Handfalling |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1545 | 20200206-6 | 53520104 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2020-02-06 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling from A129; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43880 |  | 37 | 43883 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting154520200206-6Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting154520200206-6Light Truck - Pick up- After Jan 103731.25Inv#018 |  |  | WF1-Handfalling |  |  | 1 | 731.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1545 | 20200206-6 | 53520104 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2020-02-06 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling from A129; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43880 |  | 37 | 43883 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting154520200206-6Foreman121140 | Corbiere and Sons Contracting154520200206-6Foreman121140Inv#018 |  |  | WF1-Handfalling |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1545 | 20200206-6 | 53520104 | Clearing | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2020-02-06 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling from A129; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43880 |  | 37 | 43883 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting154520200206-6L.O.A.61260 | Corbiere and Sons Contracting154520200206-6L.O.A.61260Inv#018 |  |  | WF1-Handfalling |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1545 | 20200206-6 | 53520104 | Clearing | 0 | Labourer - Specialized - After Jan 10 | 70 | 55 | HR |  |  | 70 | 0 | 3850 | 500.5 | 4350.5 | 2020-02-06 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling from A129; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43880 |  | 37 | 43883 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting154520200206-6Labourer - Specialized - After Jan 10553850 | Corbiere and Sons Contracting154520200206-6Labourer - Specialized - After Jan 10553850Inv#018 |  |  | WF1-Handfalling |  |  | 1 | 3850 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1565 | 20200207-11 | 53510611 | Access | 0 | Dozer - D5 or equal- After Jan 10 | 80.93 | 9 | Dynamic | 60.7 | 0 |  |  | 728.37 | 94.6881 | 823.0581 | 2020-02-07 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Clearing access into Del Lake W | 6 | C186-C195 | Del Lake | 0 | 43880 |  | 40 | 43889 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting156520200207-11Dozer - D5 or equal- After Jan 109728.37 | Corbiere and Sons Contracting156520200207-11Dozer - D5 or equal- After Jan 109728.37Inv#009 | [5 empty] | 1 | 728.37 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1565 | 20200207-11 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-02-07 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Clearing access into Del Lake W | 6 | C186-C195 | Del Lake | 0 | 43880 |  | 40 | 43889 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting156520200207-11Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting156520200207-11Light Truck - Pick up- After Jan 101243.75Inv#009 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1565 | 20200207-11 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-02-07 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Clearing access into Del Lake W | 6 | C186-C195 | Del Lake | 0 | 43880 |  | 40 | 43889 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting156520200207-11L.O.A.1210 | Corbiere and Sons Contracting156520200207-11L.O.A.1210Inv#009 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1565 | 20200207-11 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2020-02-07 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Clearing access into Del Lake W | 6 | C186-C195 | Del Lake | 0 | 43880 |  | 40 | 43889 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting156520200207-11Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting156520200207-11Operator - Principle - After Jan 1011825Inv#009 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1558 | 20200207-3 | 53520104 | Clearing | 0 | Chainsaw and consumables- After Jan 10 | 60 | 5 | unit/man/day | 0 | 0 |  |  | 300 | 39 | 339 | 2020-02-07 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling from A067; | 1 | A-055 to A-084 | Eldorado | 0 | 43880 |  | 37 | 43883 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting155820200207-3Chainsaw and consumables- After Jan 105300 | Corbiere and Sons Contracting155820200207-3Chainsaw and consumables- After Jan 105300Inv#018 |  |  | WF1-Handfalling |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1558 | 20200207-3 | 53520104 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2020-02-07 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling from A067; | 1 | A-055 to A-084 | Eldorado | 0 | 43880 |  | 37 | 43883 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting155820200207-3Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting155820200207-3Light Truck - Pick up- After Jan 103731.25Inv#018 |  |  | WF1-Handfalling |  |  | 1 | 731.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1558 | 20200207-3 | 53520104 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2020-02-07 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling from A067; | 1 | A-055 to A-084 | Eldorado | 0 | 43880 |  | 37 | 43883 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting155820200207-3Foreman121140 | Corbiere and Sons Contracting155820200207-3Foreman121140Inv#018 |  |  | WF1-Handfalling |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1558 | 20200207-3 | 53520104 | Clearing | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2020-02-07 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling from A067; | 1 | A-055 to A-084 | Eldorado | 0 | 43880 |  | 37 | 43883 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting155820200207-3L.O.A.61260 | Corbiere and Sons Contracting155820200207-3L.O.A.61260Inv#018 |  |  | WF1-Handfalling |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1558 | 20200207-3 | 53520104 | Clearing | 0 | Labourer - Specialized - After Jan 10 | 70 | 55 | HR |  |  | 70 | 0 | 3850 | 500.5 | 4350.5 | 2020-02-07 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfelling from A067; | 1 | A-055 to A-084 | Eldorado | 0 | 43880 |  | 37 | 43883 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting155820200207-3Labourer - Specialized - After Jan 10553850 | Corbiere and Sons Contracting155820200207-3Labourer - Specialized - After Jan 10553850Inv#018 |  |  | WF1-Handfalling |  |  | 1 | 3850 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1559 | 20200207-4 | 53520104 | Clearing | 0 | Chainsaw and consumables- After Jan 10 | 60 | 5 | unit/man/day | 0 | 0 |  |  | 300 | 39 | 339 | 2020-02-07 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hand Falling from A129; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43880 |  | 37 | 43883 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting155920200207-4Chainsaw and consumables- After Jan 105300 | Corbiere and Sons Contracting155920200207-4Chainsaw and consumables- After Jan 105300Inv#018 |  |  | WF1-Handfalling |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1559 | 20200207-4 | 53520104 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2020-02-07 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hand Falling from A129; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43880 |  | 37 | 43883 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting155920200207-4Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting155920200207-4Light Truck - Pick up- After Jan 103731.25Inv#018 |  |  | WF1-Handfalling |  |  | 1 | 731.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1559 | 20200207-4 | 53520104 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2020-02-07 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hand Falling from A129; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43880 |  | 37 | 43883 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting155920200207-4Foreman121140 | Corbiere and Sons Contracting155920200207-4Foreman121140Inv#018 |  |  | WF1-Handfalling |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1559 | 20200207-4 | 53520104 | Clearing | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2020-02-07 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hand Falling from A129; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43880 |  | 37 | 43883 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting155920200207-4L.O.A.61260 | Corbiere and Sons Contracting155920200207-4L.O.A.61260Inv#018 |  |  | WF1-Handfalling |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1559 | 20200207-4 | 53520104 | Clearing | 0 | Labourer - Specialized - After Jan 10 | 70 | 55 | HR |  |  | 70 | 0 | 3850 | 500.5 | 4350.5 | 2020-02-07 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hand Falling from A129; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43880 |  | 37 | 43883 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting155920200207-4Labourer - Specialized - After Jan 10553850 | Corbiere and Sons Contracting155920200207-4Labourer - Specialized - After Jan 10553850Inv#018 |  |  | WF1-Handfalling |  |  | 1 | 3850 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1560 | 20200207-5 | 53510111 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 9 | Dynamic | 95.24 | 0 |  |  | 1142.82 | 148.5666 | 1291.3866 | 2020-02-07 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grading on windfarm access roads | 1 | A-085 to A-117 | Windfarm | 0 | 43880 |  | 37 | 43883 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting156020200207-5Grader - Cat 12 to 14 or equal- After Jan 1091142.82 | Corbiere and Sons Contracting156020200207-5Grader - Cat 12 to 14 or equal- After Jan 1091142.82Inv#018 | [5 empty] | 1 | 1142.82 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1560 | 20200207-5 | 53510111 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-02-07 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grading on windfarm access roads | 1 | A-085 to A-117 | Windfarm | 0 | 43880 |  | 37 | 43883 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting156020200207-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting156020200207-5Light Truck - Pick up- After Jan 101243.75Inv#018 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1560 | 20200207-5 | 53510111 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-02-07 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grading on windfarm access roads | 1 | A-085 to A-117 | Windfarm | 0 | 43880 |  | 37 | 43883 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting156020200207-5L.O.A.1210 | Corbiere and Sons Contracting156020200207-5L.O.A.1210Inv#018 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1560 | 20200207-5 | 53510111 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 |  | 825 | 107.25 | 932.25 | 2020-02-07 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grading on windfarm access roads | 1 | A-085 to A-117 | Windfarm | 0 | 43880 |  | 37 | 43883 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting156020200207-5Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting156020200207-5Operator - Principle - After Jan 1011825Inv#018 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1584 | 20200208-10 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 9 | Dynamic | 98.61 | 0 |  |  | 1183.32 | 153.8316 | 1337.1516 | 2020-02-08 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Traffic Control and snow removal for access roads; | 6 | C171-C185 | Prairie River | 0 | 43881 |  | 40 | 43889 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting158420200208-10Dozer D6 or equal- After Jan 1091183.32 | Corbiere and Sons Contracting158420200208-10Dozer D6 or equal- After Jan 1091183.32Inv#009 | [5 empty] | 1 | 1183.32 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1584 | 20200208-10 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-02-08 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Traffic Control and snow removal for access roads; | 6 | C171-C185 | Prairie River | 0 | 43881 |  | 40 | 43889 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting158420200208-10Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting158420200208-10Light Truck - Pick up- After Jan 101243.75Inv#009 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1584 | 20200208-10 | 53510611 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-02-08 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Traffic Control and snow removal for access roads; | 6 | C171-C185 | Prairie River | 0 | 43881 |  | 40 | 43889 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting158420200208-10L.O.A.2420 | Corbiere and Sons Contracting158420200208-10L.O.A.2420Inv#009 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1584 | 20200208-10 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2020-02-08 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Traffic Control and snow removal for access roads; | 6 | C171-C185 | Prairie River | 0 | 43881 |  | 40 | 43889 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting158420200208-10Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting158420200208-10Operator - Principle - After Jan 1011825Inv#009 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1584 | 20200208-10 | 53510611 | Access | 0 | Labourer - General - After Jan 10 | 60 | 11 | HR |  |  | 60 | 0 | 660 | 85.8 | 745.8 | 2020-02-08 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Traffic Control and snow removal for access roads; | 6 | C171-C185 | Prairie River | 0 | 43881 |  | 40 | 43889 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting158420200208-10Labourer - General - After Jan 1011660 | Corbiere and Sons Contracting158420200208-10Labourer - General - After Jan 1011660Inv#009 | [5 empty] | 1 | 660 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1585 | 20200208-11 | 53510611 | Access | 0 | Dozer - D5 or equal- After Jan 10 | 80.93 | 9 | Dynamic | 60.7 | 0 |  |  | 728.37 | 94.6881 | 823.0581 | 2020-02-08 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Access Maintenance at Del Lake | 6 | C186-C195 | Del Lake | 0 | 43881 |  | 40 | 43889 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting158520200208-11Dozer - D5 or equal- After Jan 109728.37 | Corbiere and Sons Contracting158520200208-11Dozer - D5 or equal- After Jan 109728.37Inv#009 | [5 empty] | 1 | 728.37 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1585 | 20200208-11 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-02-08 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Access Maintenance at Del Lake | 6 | C186-C195 | Del Lake | 0 | 43881 |  | 40 | 43889 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting158520200208-11L.O.A.1210 | Corbiere and Sons Contracting158520200208-11L.O.A.1210Inv#009 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1585 | 20200208-11 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2020-02-08 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Access Maintenance at Del Lake | 6 | C186-C195 | Del Lake | 0 | 43881 |  | 40 | 43889 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting158520200208-11Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting158520200208-11Operator - Principle - After Jan 1011825Inv#009 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1593 | 20200208-3 | 53520104 | Clearing | 0 | Chainsaw and consumables- After Jan 10 | 60 | 3 | unit/man/day | 0 | 0 |  |  | 180 | 23.4 | 203.4 | 2020-02-08 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | finish up handfalling between A061-A067 | 1 | A-055 to A-084 | Eldorado | 0 | 43878 |  | 37 | 43883 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting159320200208-3Chainsaw and consumables- After Jan 103180 | Corbiere and Sons Contracting159320200208-3Chainsaw and consumables- After Jan 103180Inv#018 |  |  | WF1-Handfalling |  |  | 1 | 180 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1593 | 20200208-3 | 53520104 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-02-08 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | finish up handfalling between A061-A067 | 1 | A-055 to A-084 | Eldorado | 0 | 43878 |  | 37 | 43883 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting159320200208-3Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting159320200208-3Light Truck - Pick up- After Jan 102487.5Inv#018 |  |  | WF1-Handfalling |  |  | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1593 | 20200208-3 | 53520104 | Clearing | 0 | Foreman | 95 | 7 | HR |  |  | 95 | 0 | 665 | 86.45 | 751.45 | 2020-02-08 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | finish up handfalling between A061-A067 | 1 | A-055 to A-084 | Eldorado | 0 | 43878 |  | 37 | 43883 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting159320200208-3Foreman7665 | Corbiere and Sons Contracting159320200208-3Foreman7665Inv#018 |  |  | WF1-Handfalling |  |  | 1 | 665 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1593 | 20200208-3 | 53520104 | Clearing | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2020-02-08 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | finish up handfalling between A061-A067 | 1 | A-055 to A-084 | Eldorado | 0 | 43878 |  | 37 | 43883 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting159320200208-3L.O.A.4840 | Corbiere and Sons Contracting159320200208-3L.O.A.4840Inv#018 |  |  | WF1-Handfalling |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1593 | 20200208-3 | 53520104 | Clearing | 0 | Labourer - Specialized - After Jan 10 | 70 | 27 | HR |  |  | 70 | 0 | 1890 | 245.7 | 2135.7 | 2020-02-08 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | finish up handfalling between A061-A067 | 1 | A-055 to A-084 | Eldorado | 0 | 43878 |  | 37 | 43883 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting159320200208-3Labourer - Specialized - After Jan 10271890 | Corbiere and Sons Contracting159320200208-3Labourer - Specialized - After Jan 10271890Inv#018 |  |  | WF1-Handfalling |  |  | 1 | 1890 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1578 | 20200208-4 | 53510111 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 9 | Dynamic | 95.24 | 0 |  |  | 1142.82 | 148.5666 | 1291.3866 | 2020-02-08 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grading of access roads in Ouimet Canyon | 1 | A-085 to A-117 | Windfarm | 0 | 43881 |  | 37 | 43883 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting157820200208-4Grader - Cat 12 to 14 or equal- After Jan 1091142.82 | Corbiere and Sons Contracting157820200208-4Grader - Cat 12 to 14 or equal- After Jan 1091142.82Inv#018 | [5 empty] | 1 | 1142.82 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1578 | 20200208-4 | 53510111 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-02-08 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grading of access roads in Ouimet Canyon | 1 | A-085 to A-117 | Windfarm | 0 | 43881 |  | 37 | 43883 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting157820200208-4L.O.A.1210 | Corbiere and Sons Contracting157820200208-4L.O.A.1210Inv#018 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1578 | 20200208-4 | 53510111 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2020-02-08 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grading of access roads in Ouimet Canyon | 1 | A-085 to A-117 | Windfarm | 0 | 43881 |  | 37 | 43883 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting157820200208-4Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting157820200208-4Operator - Principle - After Jan 1011825Inv#018 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1579 | 20200208-5 | 53520104 | Clearing | 0 | Chainsaw and consumables- After Jan 10 | 60 | 5 | unit/man/day | 0 | 0 |  |  | 300 | 39 | 339 | 2020-02-08 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfalling from A129 Eastward | 1 | A-128 to B-017 | Wolf Lake | 0 | 43881 |  | 37 | 43883 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting157920200208-5Chainsaw and consumables- After Jan 105300 | Corbiere and Sons Contracting157920200208-5Chainsaw and consumables- After Jan 105300Inv#018 |  |  | WF1-Handfalling |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1579 | 20200208-5 | 53520104 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2020-02-08 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfalling from A129 Eastward | 1 | A-128 to B-017 | Wolf Lake | 0 | 43881 |  | 37 | 43883 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting157920200208-5Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting157920200208-5Light Truck - Pick up- After Jan 103731.25Inv#018 |  |  | WF1-Handfalling |  |  | 1 | 731.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1579 | 20200208-5 | 53520104 | Clearing | 0 | Foreman | 95 | 6 | HR |  |  | 95 | 0 | 570 | 74.1 | 644.1 | 2020-02-08 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfalling from A129 Eastward | 1 | A-128 to B-017 | Wolf Lake | 0 | 43881 |  | 37 | 43883 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting157920200208-5Foreman6570 | Corbiere and Sons Contracting157920200208-5Foreman6570Inv#018 |  |  | WF1-Handfalling |  |  | 1 | 570 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1579 | 20200208-5 | 53520104 | Clearing | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2020-02-08 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfalling from A129 Eastward | 1 | A-128 to B-017 | Wolf Lake | 0 | 43881 |  | 37 | 43883 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting157920200208-5L.O.A.61260 | Corbiere and Sons Contracting157920200208-5L.O.A.61260Inv#018 |  |  | WF1-Handfalling |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1579 | 20200208-5 | 53520104 | Clearing | 0 | Labourer - Specialized - After Jan 10 | 70 | 55 | HR |  |  | 70 | 0 | 3850 | 500.5 | 4350.5 | 2020-02-08 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfalling from A129 Eastward | 1 | A-128 to B-017 | Wolf Lake | 0 | 43881 |  | 37 | 43883 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting157920200208-5Labourer - Specialized - After Jan 10553850 | Corbiere and Sons Contracting157920200208-5Labourer - Specialized - After Jan 10553850Inv#018 |  |  | WF1-Handfalling |  |  | 1 | 3850 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1602 | 20200209-3 | 53520104 | Clearing | 0 | Chainsaw and consumables- After Jan 10 | 60 | 5 | unit/man/day | 0 | 0 |  |  | 300 | 39 | 339 | 2020-02-09 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hand Falling from A129-A130 | 1 | A-128 to B-017 | Wolf Lake | 0 | 43879 |  | 37 | 43886 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting160220200209-3Chainsaw and consumables- After Jan 105300 | Corbiere and Sons Contracting160220200209-3Chainsaw and consumables- After Jan 105300Inv#009 |  |  | WF1-Handfalling |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1602 | 20200209-3 | 53520104 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2020-02-09 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hand Falling from A129-A130 | 1 | A-128 to B-017 | Wolf Lake | 0 | 43879 |  | 37 | 43886 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting160220200209-3Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting160220200209-3Light Truck - Pick up- After Jan 103731.25Inv#009 |  |  | WF1-Handfalling |  |  | 1 | 731.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1602 | 20200209-3 | 53520104 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2020-02-09 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hand Falling from A129-A130 | 1 | A-128 to B-017 | Wolf Lake | 0 | 43879 |  | 37 | 43886 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting160220200209-3Foreman121140 | Corbiere and Sons Contracting160220200209-3Foreman121140Inv#009 |  |  | WF1-Handfalling |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1602 | 20200209-3 | 53520104 | Clearing | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2020-02-09 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hand Falling from A129-A130 | 1 | A-128 to B-017 | Wolf Lake | 0 | 43879 |  | 37 | 43886 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting160220200209-3L.O.A.61260 | Corbiere and Sons Contracting160220200209-3L.O.A.61260Inv#009 |  |  | WF1-Handfalling |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1602 | 20200209-3 | 53520104 | Clearing | 0 | Labourer - Specialized - After Jan 10 | 70 | 54 | HR |  |  | 70 | 0 | 3780 | 491.4 | 4271.4 | 2020-02-09 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hand Falling from A129-A130 | 1 | A-128 to B-017 | Wolf Lake | 0 | 43879 |  | 37 | 43886 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting160220200209-3Labourer - Specialized - After Jan 10543780 | Corbiere and Sons Contracting160220200209-3Labourer - Specialized - After Jan 10543780Inv#009 |  |  | WF1-Handfalling |  |  | 1 | 3780 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1604 | 20200209-5 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 9 | Dynamic | 98.61 | 0 |  |  | 1183.32 | 153.8316 | 1337.1516 | 2020-02-09 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Access Maintenance and Traffic Control at Prairie River Road; | 6 | C171-C185 | Prairie River | 0 | 43879 |  | 40 | 43889 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting160420200209-5Dozer D6 or equal- After Jan 1091183.32 | Corbiere and Sons Contracting160420200209-5Dozer D6 or equal- After Jan 1091183.32Inv#009 | [5 empty] | 1 | 1183.32 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1604 | 20200209-5 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-02-09 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Access Maintenance and Traffic Control at Prairie River Road; | 6 | C171-C185 | Prairie River | 0 | 43879 |  | 40 | 43889 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting160420200209-5Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting160420200209-5Light Truck - Pick up- After Jan 102487.5Inv#009 | [5 empty] | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1604 | 20200209-5 | 53510611 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2020-02-09 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Access Maintenance and Traffic Control at Prairie River Road; | 6 | C171-C185 | Prairie River | 0 | 43879 |  | 40 | 43889 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting160420200209-5L.O.A.3630 | Corbiere and Sons Contracting160420200209-5L.O.A.3630Inv#009 | [5 empty] | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1604 | 20200209-5 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2020-02-09 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Access Maintenance and Traffic Control at Prairie River Road; | 6 | C171-C185 | Prairie River | 0 | 43879 |  | 40 | 43889 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting160420200209-5Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting160420200209-5Operator - Principle - After Jan 1011825Inv#009 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1604 | 20200209-5 | 53510611 | Access | 0 | Labourer - General - After Jan 10 | 60 | 22 | HR |  |  | 60 | 0 | 1320 | 171.6 | 1491.6 | 2020-02-09 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Access Maintenance and Traffic Control at Prairie River Road; | 6 | C171-C185 | Prairie River | 0 | 43879 |  | 40 | 43889 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting160420200209-5Labourer - General - After Jan 10221320 | Corbiere and Sons Contracting160420200209-5Labourer - General - After Jan 10221320Inv#009 | [5 empty] | 1 | 1320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1606 | 20200209-7 | 53510611 | Access | 0 | Loader JD 524 to 624 or equal | 99 | 4 | HR | 74.25 | 0 |  |  | 396 | 51.48 | 447.48 | 2020-02-09 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Clearing access along Del E and W | 6 | C186-C195 | Del Lake | 0 | 43879 |  | 40 | 43889 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting160620200209-7Loader JD 524 to 624 or equal4396 | Corbiere and Sons Contracting160620200209-7Loader JD 524 to 624 or equal4396Inv#009 | [5 empty] | 1 | 396 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1606 | 20200209-7 | 53510611 | Access | 0 | Dozer - D5 or equal- After Jan 10 | 80.93 | 9 | Dynamic | 60.7 | 0 |  |  | 728.37 | 94.6881 | 823.0581 | 2020-02-09 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Clearing access along Del E and W | 6 | C186-C195 | Del Lake | 0 | 43879 |  | 40 | 43889 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting160620200209-7Dozer - D5 or equal- After Jan 109728.37 | Corbiere and Sons Contracting160620200209-7Dozer - D5 or equal- After Jan 109728.37Inv#009 | [5 empty] | 1 | 728.37 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1606 | 20200209-7 | 53510611 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-02-09 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Clearing access along Del E and W | 6 | C186-C195 | Del Lake | 0 | 43879 |  | 40 | 43889 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting160620200209-7L.O.A.2420 | Corbiere and Sons Contracting160620200209-7L.O.A.2420Inv#009 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1606 | 20200209-7 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2020-02-09 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Clearing access along Del E and W | 6 | C186-C195 | Del Lake | 0 | 43879 |  | 40 | 43889 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting160620200209-7Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting160620200209-7Operator - Principle - After Jan 1011825Inv#009 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1606 | 20200209-7 | 53510611 | Access | 0 | Labourer - Specialized - After Jan 10 | 70 | 5 | HR |  |  | 70 | 0 | 350 | 45.5 | 395.5 | 2020-02-09 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Clearing access along Del E and W | 6 | C186-C195 | Del Lake | 0 | 43879 |  | 40 | 43889 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting160620200209-7Labourer - Specialized - After Jan 105350 | Corbiere and Sons Contracting160620200209-7Labourer - Specialized - After Jan 105350Inv#009 | [5 empty] | 1 | 350 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1616 | 20200210-3 | 53520104 | Clearing | 0 | Chainsaw and consumables- After Jan 10 | 60 | 6 | unit/man/day | 0 | 0 |  |  | 360 | 46.8 | 406.8 | 2020-02-10 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hand Falling from A131 Eastward | 1 | A-128 to B-017 | Wolf Lake | 0 | 43881 |  | 37 | 43886 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting161620200210-3Chainsaw and consumables- After Jan 106360 | Corbiere and Sons Contracting161620200210-3Chainsaw and consumables- After Jan 106360Inv#009 |  |  | WF1-Handfalling |  |  | 1 | 360 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1616 | 20200210-3 | 53520104 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2020-02-10 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hand Falling from A131 Eastward | 1 | A-128 to B-017 | Wolf Lake | 0 | 43881 |  | 37 | 43886 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting161620200210-3Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting161620200210-3Light Truck - Pick up- After Jan 103731.25Inv#009 |  |  | WF1-Handfalling |  |  | 1 | 731.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1616 | 20200210-3 | 53520104 | Clearing | 0 | L.O.A. | 210 | 7 | DAY |  |  |  | 0 | 1470 | 191.1 | 1661.1 | 2020-02-10 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hand Falling from A131 Eastward | 1 | A-128 to B-017 | Wolf Lake | 0 | 43881 |  | 37 | 43886 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting161620200210-3L.O.A.71470 | Corbiere and Sons Contracting161620200210-3L.O.A.71470Inv#009 |  |  | WF1-Handfalling |  |  | 1 | 1470 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1616 | 20200210-3 | 53520104 | Clearing | 0 | Labourer - Specialized - After Jan 10 | 70 | 69 | HR |  |  | 70 | 0 | 4830 | 627.9 | 5457.9 | 2020-02-10 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hand Falling from A131 Eastward | 1 | A-128 to B-017 | Wolf Lake | 0 | 43881 |  | 37 | 43886 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting161620200210-3Labourer - Specialized - After Jan 10694830 | Corbiere and Sons Contracting161620200210-3Labourer - Specialized - After Jan 10694830Inv#009 |  |  | WF1-Handfalling |  |  | 1 | 4830 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1645 | 20200211-10 | 53510611 | Access | 0 | Loader JD 524 to 624 or equal | 99 | 9 | HR | 74.25 | 0 |  |  | 891 | 115.83 | 1006.83 |  | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Deena Kruper | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  |  | 6 |  | Middleton Road | 0 | 43885 |  | 41 | 43889 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting164520200211-10Loader JD 524 to 624 or equal9891 | Corbiere and Sons Contracting164520200211-10Loader JD 524 to 624 or equal9891Inv#009 | [5 empty] | 1 | 891 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1645 | 20200211-10 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 |  | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Deena Kruper | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  |  | 6 |  | Middleton Road | 0 | 43885 |  | 41 | 43889 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting164520200211-10Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting164520200211-10Light Truck - Pick up- After Jan 101243.75Inv#009 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1645 | 20200211-10 | 53510611 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 |  | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Deena Kruper | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  |  | 6 |  | Middleton Road | 0 | 43885 |  | 41 | 43889 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting164520200211-10L.O.A.2420 | Corbiere and Sons Contracting164520200211-10L.O.A.2420Inv#009 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1645 | 20200211-10 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 |  | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Deena Kruper | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  |  | 6 |  | Middleton Road | 0 | 43885 |  | 41 | 43889 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting164520200211-10Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting164520200211-10Operator - Principle - After Jan 1011825Inv#009 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1645 | 20200211-10 | 53510611 | Access | 0 | Labourer - General - After Jan 10 | 60 | 11 | HR |  |  | 60 | 0 | 660 | 85.8 | 745.8 |  | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Deena Kruper | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  |  | 6 |  | Middleton Road | 0 | 43885 |  | 41 | 43889 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting164520200211-10Labourer - General - After Jan 1011660 | Corbiere and Sons Contracting164520200211-10Labourer - General - After Jan 1011660Inv#009 | [5 empty] | 1 | 660 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1648 | 20200211-13 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 5 | Dynamic | 98.61 | 0 |  |  | 657.4 | 85.462 | 742.862 | 2020-02-11 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Deena Kruper | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Mike doing winter access maintenance with DZ004 for part of the day | 6 |  | Prairie River | 0 | 43885 |  | 41 | 43889 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting164820200211-13Dozer D6 or equal- After Jan 105657.4 | Corbiere and Sons Contracting164820200211-13Dozer D6 or equal- After Jan 105657.4Inv#009 | [5 empty] | 1 | 657.4 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1648 | 20200211-13 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-02-11 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Deena Kruper | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Mike doing winter access maintenance with DZ004 for part of the day | 6 |  | Prairie River | 0 | 43885 |  | 41 | 43889 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting164820200211-13L.O.A.1210 | Corbiere and Sons Contracting164820200211-13L.O.A.1210Inv#009 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1648 | 20200211-13 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 75 | 0 | 450 | 58.5 | 508.5 | 2020-02-11 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Deena Kruper | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Mike doing winter access maintenance with DZ004 for part of the day | 6 |  | Prairie River | 0 | 43885 |  | 41 | 43889 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting164820200211-13Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting164820200211-13Operator - Principle - After Jan 106450Inv#009 | [5 empty] | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1650 | 20200211-18 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 6 | Dynamic | 98.61 | 0 |  |  | 788.88 | 102.5544 | 891.4344 | 2020-02-11 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Deena Kruper | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Maintenance of access roads along Lake A | 6 |  | Lake A | 0 | 43885 |  | 41 | 43889 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting165020200211-18Dozer D6 or equal- After Jan 106788.88 | Corbiere and Sons Contracting165020200211-18Dozer D6 or equal- After Jan 106788.88Inv#009 | [5 empty] | 1 | 788.88 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1650 | 20200211-18 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 9 | Dynamic | 95.24 | 0 |  |  | 1142.82 | 148.5666 | 1291.3866 | 2020-02-11 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Deena Kruper | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Maintenance of access roads along Lake A | 6 |  | Lake A | 0 | 43885 |  | 41 | 43889 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting165020200211-18Grader - Cat 12 to 14 or equal- After Jan 1091142.82 | Corbiere and Sons Contracting165020200211-18Grader - Cat 12 to 14 or equal- After Jan 1091142.82Inv#009 | [5 empty] | 1 | 1142.82 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1650 | 20200211-18 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-02-11 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Deena Kruper | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Maintenance of access roads along Lake A | 6 |  | Lake A | 0 | 43885 |  | 41 | 43889 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting165020200211-18Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting165020200211-18Light Truck - Pick up- After Jan 101243.75Inv#009 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1650 | 20200211-18 | 53510611 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-02-11 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Deena Kruper | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Maintenance of access roads along Lake A | 6 |  | Lake A | 0 | 43885 |  | 41 | 43889 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting165020200211-18L.O.A.2420 | Corbiere and Sons Contracting165020200211-18L.O.A.2420Inv#009 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1650 | 20200211-18 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 17 | HR |  |  | 75 | 0 | 1275 | 165.75 | 1440.75 | 2020-02-11 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Deena Kruper | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Maintenance of access roads along Lake A | 6 |  | Lake A | 0 | 43885 |  | 41 | 43889 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting165020200211-18Operator - Principle - After Jan 10171275 | Corbiere and Sons Contracting165020200211-18Operator - Principle - After Jan 10171275Inv#009 | [5 empty] | 1 | 1275 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1653 | 20200211-3-R1 | 53520104 | Clearing | 0 | Chainsaw and consumables- After Jan 10 | 60 | 2 | unit/man/day | 0 | 0 |  |  | 120 | 15.6 | 135.6 | 2020-02-11 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hand Falling from A133-A132 | 1 | A-128 to B-017 | Wolf Lake | 0 | 43886 |  | 37 | 43888 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting165320200211-3-R1Chainsaw and consumables- After Jan 102120 | Corbiere and Sons Contracting165320200211-3-R1Chainsaw and consumables- After Jan 102120Inv#009 |  |  | WF1-Handfalling |  |  | 1 | 120 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1653 | 20200211-3-R1 | 53520104 | Clearing | 0 | Chainsaw and consumables- After Jan 10 | 60 | 5 | unit/man/day | 0 | 0 |  |  | 300 | 39 | 339 | 2020-02-11 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hand Falling from A133-A132 | 1 | A-128 to B-017 | Wolf Lake | 0 | 43886 |  | 37 | 43888 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting165320200211-3-R1Chainsaw and consumables- After Jan 105300 | Corbiere and Sons Contracting165320200211-3-R1Chainsaw and consumables- After Jan 105300Inv#009 |  |  | WF1-Handfalling |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1653 | 20200211-3-R1 | 53520104 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2020-02-11 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hand Falling from A133-A132 | 1 | A-128 to B-017 | Wolf Lake | 0 | 43886 |  | 37 | 43888 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting165320200211-3-R1Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting165320200211-3-R1Light Truck - Pick up- After Jan 103731.25Inv#009 |  |  | WF1-Handfalling |  |  | 1 | 731.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1653 | 20200211-3-R1 | 53520104 | Clearing | 0 | Foreman | 95 | 4 | HR |  |  | 95 | 0 | 380 | 49.4 | 429.4 | 2020-02-11 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hand Falling from A133-A132 | 1 | A-128 to B-017 | Wolf Lake | 0 | 43886 |  | 37 | 43888 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting165320200211-3-R1Foreman4380 | Corbiere and Sons Contracting165320200211-3-R1Foreman4380Inv#009 |  |  | WF1-Handfalling |  |  | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1653 | 20200211-3-R1 | 53520104 | Clearing | 0 | L.O.A. | 210 | 8 | DAY |  |  |  | 0 | 1680 | 218.4 | 1898.4 | 2020-02-11 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hand Falling from A133-A132 | 1 | A-128 to B-017 | Wolf Lake | 0 | 43886 |  | 37 | 43888 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting165320200211-3-R1L.O.A.81680 | Corbiere and Sons Contracting165320200211-3-R1L.O.A.81680Inv#009 |  |  | WF1-Handfalling |  |  | 1 | 1680 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1653 | 20200211-3-R1 | 53520104 | Clearing | 0 | Labourer - Specialized - After Jan 10 | 70 | 77 | HR |  |  | 70 | 0 | 5390 | 700.7 | 6090.7 | 2020-02-11 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hand Falling from A133-A132 | 1 | A-128 to B-017 | Wolf Lake | 0 | 43886 |  | 37 | 43888 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting165320200211-3-R1Labourer - Specialized - After Jan 10775390 | Corbiere and Sons Contracting165320200211-3-R1Labourer - Specialized - After Jan 10775390Inv#009 |  |  | WF1-Handfalling |  |  | 1 | 5390 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1643 | 20200211-8 | 53510611 | Access | 0 | Dozer - D5 or equal- After Jan 10 | 80.93 | 9 | Dynamic | 60.7 | 0 |  |  | 728.37 | 94.6881 | 823.0581 | 2020-02-11 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Deena Kruper | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Snow removal and Traffic control for Del Rd East | 6 |  | Del Lake | 0 | 43885 |  | 41 | 43889 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting164320200211-8Dozer - D5 or equal- After Jan 109728.37 | Corbiere and Sons Contracting164320200211-8Dozer - D5 or equal- After Jan 109728.37Inv#009 | [5 empty] | 1 | 728.37 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1643 | 20200211-8 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-02-11 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Deena Kruper | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Snow removal and Traffic control for Del Rd East | 6 |  | Del Lake | 0 | 43885 |  | 41 | 43889 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting164320200211-8Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting164320200211-8Light Truck - Pick up- After Jan 101243.75Inv#009 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1643 | 20200211-8 | 53510611 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-02-11 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Deena Kruper | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Snow removal and Traffic control for Del Rd East | 6 |  | Del Lake | 0 | 43885 |  | 41 | 43889 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting164320200211-8L.O.A.2420 | Corbiere and Sons Contracting164320200211-8L.O.A.2420Inv#009 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1643 | 20200211-8 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2020-02-11 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Deena Kruper | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Snow removal and Traffic control for Del Rd East | 6 |  | Del Lake | 0 | 43885 |  | 41 | 43889 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting164320200211-8Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting164320200211-8Operator - Principle - After Jan 1011825Inv#009 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1643 | 20200211-8 | 53510611 | Access | 0 | Labourer - General - After Jan 10 | 60 | 11 | HR |  |  | 60 | 0 | 660 | 85.8 | 745.8 | 2020-02-11 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Deena Kruper | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Snow removal and Traffic control for Del Rd East | 6 |  | Del Lake | 0 | 43885 |  | 41 | 43889 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting164320200211-8Labourer - General - After Jan 1011660 | Corbiere and Sons Contracting164320200211-8Labourer - General - After Jan 1011660Inv#009 | [5 empty] | 1 | 660 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1657 | 20200212-3 | 53510111 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 9 | Dynamic | 95.24 | 0 |  |  | 1142.82 | 148.5666 | 1291.3866 | 2020-02-12 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across as access roads where necessary at Valard's request; Labourer escorting grader in some areas; | 1 | A-055 to A-084 | Eldorado | 0 | 43885 |  | 37 | 43888 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting165720200212-3Grader - Cat 12 to 14 or equal- After Jan 1091142.82 | Corbiere and Sons Contracting165720200212-3Grader - Cat 12 to 14 or equal- After Jan 1091142.82Inv#009 | [5 empty] | 1 | 1142.82 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1657 | 20200212-3 | 53510111 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-02-12 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across as access roads where necessary at Valard's request; Labourer escorting grader in some areas; | 1 | A-055 to A-084 | Eldorado | 0 | 43885 |  | 37 | 43888 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting165720200212-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting165720200212-3Light Truck - Pick up- After Jan 101243.75Inv#009 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1657 | 20200212-3 | 53510111 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-02-12 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across as access roads where necessary at Valard's request; Labourer escorting grader in some areas; | 1 | A-055 to A-084 | Eldorado | 0 | 43885 |  | 37 | 43888 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting165720200212-3L.O.A.2420 | Corbiere and Sons Contracting165720200212-3L.O.A.2420Inv#009 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1657 | 20200212-3 | 53510111 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2020-02-12 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across as access roads where necessary at Valard's request; Labourer escorting grader in some areas; | 1 | A-055 to A-084 | Eldorado | 0 | 43885 |  | 37 | 43888 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting165720200212-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting165720200212-3Operator - Principle - After Jan 1011825Inv#009 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1657 | 20200212-3 | 53510111 | Access | 0 | Labourer - General - After Jan 10 | 60 | 3 | HR |  |  | 60 | 0 | 180 | 23.4 | 203.4 | 2020-02-12 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across as access roads where necessary at Valard's request; Labourer escorting grader in some areas; | 1 | A-055 to A-084 | Eldorado | 0 | 43885 |  | 37 | 43888 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting165720200212-3Labourer - General - After Jan 103180 | Corbiere and Sons Contracting165720200212-3Labourer - General - After Jan 103180Inv#009 | [5 empty] | 1 | 180 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1658 | 20200212-4 | 53520104 | Clearing | 0 | Chainsaw and consumables- After Jan 10 | 60 | 5 | unit/man/day | 0 | 0 |  |  | 300 | 39 | 339 | 2020-02-12 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hand Falling from A134-A135; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43885 |  | 37 | 43888 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting165820200212-4Chainsaw and consumables- After Jan 105300 | Corbiere and Sons Contracting165820200212-4Chainsaw and consumables- After Jan 105300Inv#009 |  |  | WF1-Handfalling |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1658 | 20200212-4 | 53520104 | Clearing | 0 | Chainsaw and consumables- After Jan 10 | 60 | 3 | unit/man/day | 0 | 0 |  |  | 180 | 23.4 | 203.4 | 2020-02-12 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hand Falling from A134-A135; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43885 |  | 37 | 43888 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting165820200212-4Chainsaw and consumables- After Jan 103180 | Corbiere and Sons Contracting165820200212-4Chainsaw and consumables- After Jan 103180Inv#009 |  |  | WF1-Handfalling |  |  | 1 | 180 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1658 | 20200212-4 | 53520104 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 4 | DAY | 182.81 | 0 |  |  | 975 | 126.75 | 1101.75 | 2020-02-12 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hand Falling from A134-A135; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43885 |  | 37 | 43888 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting165820200212-4Light Truck - Pick up- After Jan 104975 | Corbiere and Sons Contracting165820200212-4Light Truck - Pick up- After Jan 104975Inv#009 |  |  | WF1-Handfalling |  |  | 1 | 975 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1658 | 20200212-4 | 53520104 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2020-02-12 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hand Falling from A134-A135; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43885 |  | 37 | 43888 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting165820200212-4Foreman121140 | Corbiere and Sons Contracting165820200212-4Foreman121140Inv#009 |  |  | WF1-Handfalling |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1658 | 20200212-4 | 53520104 | Clearing | 0 | L.O.A. | 210 | 9 | DAY |  |  |  | 0 | 1890 | 245.7 | 2135.7 | 2020-02-12 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hand Falling from A134-A135; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43885 |  | 37 | 43888 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting165820200212-4L.O.A.91890 | Corbiere and Sons Contracting165820200212-4L.O.A.91890Inv#009 |  |  | WF1-Handfalling |  |  | 1 | 1890 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1658 | 20200212-4 | 53520104 | Clearing | 0 | Labourer - Specialized - After Jan 10 | 70 | 88 | HR |  |  | 70 | 0 | 6160 | 800.8 | 6960.8 | 2020-02-12 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hand Falling from A134-A135; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43885 |  | 37 | 43888 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting165820200212-4Labourer - Specialized - After Jan 10886160 | Corbiere and Sons Contracting165820200212-4Labourer - Specialized - After Jan 10886160Inv#009 |  |  | WF1-Handfalling |  |  | 1 | 6160 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1725 | 20200213-18 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 6 | Dynamic | 98.61 | 0 |  |  | 788.88 | 102.5544 | 891.4344 | 2020-02-13 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Rachelle Russell | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Cleaned Road and Entrance for Peninsula Rd. away from hone station | 6 | C268-C279 | Peninsula Road | 0 | 43887 |  | 41 | 43889 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting172520200213-18Dozer D6 or equal- After Jan 106788.88 | Corbiere and Sons Contracting172520200213-18Dozer D6 or equal- After Jan 106788.88Inv#009 | [5 empty] | 1 | 788.88 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1725 | 20200213-18 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-02-13 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Rachelle Russell | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Cleaned Road and Entrance for Peninsula Rd. away from hone station | 6 | C268-C279 | Peninsula Road | 0 | 43887 |  | 41 | 43889 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting172520200213-18Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting172520200213-18Light Truck - Pick up- After Jan 101243.75Inv#009 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1725 | 20200213-18 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-02-13 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Rachelle Russell | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Cleaned Road and Entrance for Peninsula Rd. away from hone station | 6 | C268-C279 | Peninsula Road | 0 | 43887 |  | 41 | 43889 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting172520200213-18L.O.A.1210 | Corbiere and Sons Contracting172520200213-18L.O.A.1210Inv#009 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1725 | 20200213-18 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 75 | 0 | 450 | 58.5 | 508.5 | 2020-02-13 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Rachelle Russell | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Cleaned Road and Entrance for Peninsula Rd. away from hone station | 6 | C268-C279 | Peninsula Road | 0 | 43887 |  | 41 | 43889 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting172520200213-18Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting172520200213-18Operator - Principle - After Jan 106450Inv#009 | [5 empty] | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1710 | 20200213-3 | 53520104 | Clearing | 0 | Chainsaw and consumables- After Jan 10 | 60 | 8 | unit/man/day | 0 | 0 |  |  | 480 | 62.4 | 542.4 | 2020-02-13 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Rachelle Russell | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hand Falling from A134-A135 | 1 | A-128 to B-017 | Wolf Lake | 0 | 43887 |  | 37 | 43890 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting171020200213-3Chainsaw and consumables- After Jan 108480 | Corbiere and Sons Contracting171020200213-3Chainsaw and consumables- After Jan 108480Inv#009 |  |  | WF1-Handfalling |  |  | 1 | 480 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1710 | 20200213-3 | 53520104 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 4 | DAY | 182.81 | 0 |  |  | 975 | 126.75 | 1101.75 | 2020-02-13 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Rachelle Russell | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hand Falling from A134-A135 | 1 | A-128 to B-017 | Wolf Lake | 0 | 43887 |  | 37 | 43890 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting171020200213-3Light Truck - Pick up- After Jan 104975 | Corbiere and Sons Contracting171020200213-3Light Truck - Pick up- After Jan 104975Inv#009 |  |  | WF1-Handfalling |  |  | 1 | 975 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1710 | 20200213-3 | 53520104 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2020-02-13 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Rachelle Russell | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hand Falling from A134-A135 | 1 | A-128 to B-017 | Wolf Lake | 0 | 43887 |  | 37 | 43890 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting171020200213-3Foreman121140 | Corbiere and Sons Contracting171020200213-3Foreman121140Inv#009 |  |  | WF1-Handfalling |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1710 | 20200213-3 | 53520104 | Clearing | 0 | L.O.A. | 210 | 9 | DAY |  |  |  | 0 | 1890 | 245.7 | 2135.7 | 2020-02-13 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Rachelle Russell | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hand Falling from A134-A135 | 1 | A-128 to B-017 | Wolf Lake | 0 | 43887 |  | 37 | 43890 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting171020200213-3L.O.A.91890 | Corbiere and Sons Contracting171020200213-3L.O.A.91890Inv#009 |  |  | WF1-Handfalling |  |  | 1 | 1890 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1710 | 20200213-3 | 53520104 | Clearing | 0 | Labourer - Specialized - After Jan 10 | 70 | 88 | HR |  |  | 70 | 0 | 6160 | 800.8 | 6960.8 | 2020-02-13 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Rachelle Russell | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hand Falling from A134-A135 | 1 | A-128 to B-017 | Wolf Lake | 0 | 43887 |  | 37 | 43890 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting171020200213-3Labourer - Specialized - After Jan 10886160 | Corbiere and Sons Contracting171020200213-3Labourer - Specialized - After Jan 10886160Inv#009 |  |  | WF1-Handfalling |  |  | 1 | 6160 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1713 | 20200213-6 | 53510211 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 9 | Dynamic | 95.24 | 0 |  |  | 1142.82 | 148.5666 | 1291.3866 | 2020-02-13 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Rachelle Russell | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grading of access roads. | 2 | B018-B029 | Black Sturgeon | 0 | 43887 |  | 37 | 43890 | [5 empty] | Harold Furlong | 02 | Corbiere and Sons Contracting171320200213-6Grader - Cat 12 to 14 or equal- After Jan 1091142.82 | Corbiere and Sons Contracting171320200213-6Grader - Cat 12 to 14 or equal- After Jan 1091142.82Inv#009 | [5 empty] | 1 | 1142.82 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1713 | 20200213-6 | 53510211 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-02-13 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Rachelle Russell | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grading of access roads. | 2 | B018-B029 | Black Sturgeon | 0 | 43887 |  | 37 | 43890 | [5 empty] | Harold Furlong | 02 | Corbiere and Sons Contracting171320200213-6Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting171320200213-6Light Truck - Pick up- After Jan 101243.75Inv#009 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1713 | 20200213-6 | 53510211 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-02-13 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Rachelle Russell | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grading of access roads. | 2 | B018-B029 | Black Sturgeon | 0 | 43887 |  | 37 | 43890 | [5 empty] | Harold Furlong | 02 | Corbiere and Sons Contracting171320200213-6L.O.A.1210 | Corbiere and Sons Contracting171320200213-6L.O.A.1210Inv#009 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1713 | 20200213-6 | 53510211 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2020-02-13 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Rachelle Russell | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grading of access roads. | 2 | B018-B029 | Black Sturgeon | 0 | 43887 |  | 37 | 43890 | [5 empty] | Harold Furlong | 02 | Corbiere and Sons Contracting171320200213-6Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting171320200213-6Operator - Principle - After Jan 1011825Inv#009 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1732 | 20200214-16 | 53510611 | Access | 0 | Dozer D8 or equal- After Jan 10 | 217.5 | 5 | Dynamic | 163.13 | 0 |  |  | 1087.5 | 141.375 | 1228.875 | 2020-02-14 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Built turnaround off Hwy on Hare Lake Rd. for Valard; | 6 | C257-C267 | Hare Lake Creek | 0 | 43887 |  | 41 | 43889 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting173220200214-16Dozer D8 or equal- After Jan 1051087.5 | Corbiere and Sons Contracting173220200214-16Dozer D8 or equal- After Jan 1051087.5Inv#009 | [5 empty] | 1 | 1087.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1732 | 20200214-16 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-02-14 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Built turnaround off Hwy on Hare Lake Rd. for Valard; | 6 | C257-C267 | Hare Lake Creek | 0 | 43887 |  | 41 | 43889 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting173220200214-16Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting173220200214-16Light Truck - Pick up- After Jan 101243.75Inv#009 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1732 | 20200214-16 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-02-14 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Built turnaround off Hwy on Hare Lake Rd. for Valard; | 6 | C257-C267 | Hare Lake Creek | 0 | 43887 |  | 41 | 43889 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting173220200214-16L.O.A.1210 | Corbiere and Sons Contracting173220200214-16L.O.A.1210Inv#009 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1732 | 20200214-16 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5 | HR |  |  | 75 | 0 | 375 | 48.75 | 423.75 | 2020-02-14 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Built turnaround off Hwy on Hare Lake Rd. for Valard; | 6 | C257-C267 | Hare Lake Creek | 0 | 43887 |  | 41 | 43889 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting173220200214-16Operator - Principle - After Jan 105375 | Corbiere and Sons Contracting173220200214-16Operator - Principle - After Jan 105375Inv#009 | [5 empty] | 1 | 375 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1733 | 20200214-17 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 5 | Dynamic | 95.24 | 0 |  |  | 634.9 | 82.537 | 717.437 | 2020-02-14 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Graded road on Culvert Creek | 6 | C237-C243 | Culvert Creek | 0 | 43887 |  | 41 | 43889 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting173320200214-17Grader - Cat 12 to 14 or equal- After Jan 105634.9 | Corbiere and Sons Contracting173320200214-17Grader - Cat 12 to 14 or equal- After Jan 105634.9Inv#009 | [5 empty] | 1 | 634.9 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1733 | 20200214-17 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-02-14 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Graded road on Culvert Creek | 6 | C237-C243 | Culvert Creek | 0 | 43887 |  | 41 | 43889 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting173320200214-17Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting173320200214-17Light Truck - Pick up- After Jan 101243.75Inv#009 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1733 | 20200214-17 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-02-14 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Graded road on Culvert Creek | 6 | C237-C243 | Culvert Creek | 0 | 43887 |  | 41 | 43889 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting173320200214-17L.O.A.1210 | Corbiere and Sons Contracting173320200214-17L.O.A.1210Inv#009 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1733 | 20200214-17 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5 | HR |  |  | 75 | 0 | 375 | 48.75 | 423.75 | 2020-02-14 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Graded road on Culvert Creek | 6 | C237-C243 | Culvert Creek | 0 | 43887 |  | 41 | 43889 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting173320200214-17Operator - Principle - After Jan 105375 | Corbiere and Sons Contracting173320200214-17Operator - Principle - After Jan 105375Inv#009 | [5 empty] | 1 | 375 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1697 | 20200214-3 | 53520104 | Clearing | 0 | Chainsaw and consumables- After Jan 10 | 60 | 6 | unit/man/day | 0 | 0 |  |  | 360 | 46.8 | 406.8 | 2020-02-14 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hand Falling from A134-A135, B001-B002; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43887 |  | 37 | 43890 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting169720200214-3Chainsaw and consumables- After Jan 106360 | Corbiere and Sons Contracting169720200214-3Chainsaw and consumables- After Jan 106360Inv#009 |  |  | WF1-Handfalling |  |  | 1 | 360 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1697 | 20200214-3 | 53520104 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 4 | DAY | 182.81 | 0 |  |  | 975 | 126.75 | 1101.75 | 2020-02-14 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hand Falling from A134-A135, B001-B002; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43887 |  | 37 | 43890 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting169720200214-3Light Truck - Pick up- After Jan 104975 | Corbiere and Sons Contracting169720200214-3Light Truck - Pick up- After Jan 104975Inv#009 |  |  | WF1-Handfalling |  |  | 1 | 975 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1697 | 20200214-3 | 53520104 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2020-02-14 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hand Falling from A134-A135, B001-B002; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43887 |  | 37 | 43890 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting169720200214-3Foreman121140 | Corbiere and Sons Contracting169720200214-3Foreman121140Inv#009 |  |  | WF1-Handfalling |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1697 | 20200214-3 | 53520104 | Clearing | 0 | L.O.A. | 210 | 7 | DAY |  |  |  | 0 | 1470 | 191.1 | 1661.1 | 2020-02-14 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hand Falling from A134-A135, B001-B002; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43887 |  | 37 | 43890 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting169720200214-3L.O.A.71470 | Corbiere and Sons Contracting169720200214-3L.O.A.71470Inv#009 |  |  | WF1-Handfalling |  |  | 1 | 1470 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1697 | 20200214-3 | 53520104 | Clearing | 0 | Labourer - Specialized - After Jan 10 | 70 | 58 | HR |  |  | 70 | 0 | 4060 | 527.8 | 4587.8 | 2020-02-14 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hand Falling from A134-A135, B001-B002; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43887 |  | 37 | 43890 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting169720200214-3Labourer - Specialized - After Jan 10584060 | Corbiere and Sons Contracting169720200214-3Labourer - Specialized - After Jan 10584060Inv#009 |  |  | WF1-Handfalling |  |  | 1 | 4060 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1699 | 20200214-4 | 53510211 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 9 | Dynamic | 95.24 | 0 |  |  | 1142.82 | 148.5666 | 1291.3866 | 2020-02-14 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grading of access roads; | 2 | B018-B029 | Black Sturgeon | 0 | 43887 |  | 37 | 43890 | [5 empty] | Harold Furlong | 02 | Corbiere and Sons Contracting169920200214-4Grader - Cat 12 to 14 or equal- After Jan 1091142.82 | Corbiere and Sons Contracting169920200214-4Grader - Cat 12 to 14 or equal- After Jan 1091142.82Inv#009 | [5 empty] | 1 | 1142.82 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1699 | 20200214-4 | 53510211 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-02-14 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grading of access roads; | 2 | B018-B029 | Black Sturgeon | 0 | 43887 |  | 37 | 43890 | [5 empty] | Harold Furlong | 02 | Corbiere and Sons Contracting169920200214-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting169920200214-4Light Truck - Pick up- After Jan 101243.75Inv#009 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1699 | 20200214-4 | 53510211 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-02-14 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grading of access roads; | 2 | B018-B029 | Black Sturgeon | 0 | 43887 |  | 37 | 43890 | [5 empty] | Harold Furlong | 02 | Corbiere and Sons Contracting169920200214-4L.O.A.1210 | Corbiere and Sons Contracting169920200214-4L.O.A.1210Inv#009 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1699 | 20200214-4 | 53510211 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2020-02-14 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grading of access roads; | 2 | B018-B029 | Black Sturgeon | 0 | 43887 |  | 37 | 43890 | [5 empty] | Harold Furlong | 02 | Corbiere and Sons Contracting169920200214-4Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting169920200214-4Operator - Principle - After Jan 1011825Inv#009 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1686 | 20200215-12 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 4 | Dynamic | 98.61 | 0 |  |  | 525.92 | 68.3696 | 594.2896 | 2020-02-15 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF | [6 empty] | Clearing snow for access; | 6 | C129-C151 | Lake A | 0 | 43888 | [9 empty] | 06 | Corbiere and Sons Contracting168620200215-12Dozer D6 or equal- After Jan 104525.92 | Corbiere and Sons Contracting168620200215-12Dozer D6 or equal- After Jan 104525.92Inv#009 | [5 empty] | 1 | 525.92 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1686 | 20200215-12 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 9 | Dynamic | 95.24 | 0 |  |  | 1142.82 | 148.5666 | 1291.3866 | 2020-02-15 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF | [6 empty] | Clearing snow for access; | 6 | C129-C151 | Lake A | 0 | 43888 | [9 empty] | 06 | Corbiere and Sons Contracting168620200215-12Grader - Cat 12 to 14 or equal- After Jan 1091142.82 | Corbiere and Sons Contracting168620200215-12Grader - Cat 12 to 14 or equal- After Jan 1091142.82Inv#009 | [5 empty] | 1 | 1142.82 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1686 | 20200215-12 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-02-15 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF | [6 empty] | Clearing snow for access; | 6 | C129-C151 | Lake A | 0 | 43888 | [9 empty] | 06 | Corbiere and Sons Contracting168620200215-12Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting168620200215-12Light Truck - Pick up- After Jan 101243.75Inv#009 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1686 | 20200215-12 | 53510611 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-02-15 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF | [6 empty] | Clearing snow for access; | 6 | C129-C151 | Lake A | 0 | 43888 | [9 empty] | 06 | Corbiere and Sons Contracting168620200215-12L.O.A.2420 | Corbiere and Sons Contracting168620200215-12L.O.A.2420Inv#009 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1686 | 20200215-12 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 4 | HR |  |  | 75 | 0 | 300 | 39 | 339 | 2020-02-15 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF | [6 empty] | Clearing snow for access; | 6 | C129-C151 | Lake A | 0 | 43888 | [9 empty] | 06 | Corbiere and Sons Contracting168620200215-12Operator - Principle - After Jan 104300 | Corbiere and Sons Contracting168620200215-12Operator - Principle - After Jan 104300Inv#009 | [5 empty] | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1686 | 20200215-12 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2020-02-15 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF | [6 empty] | Clearing snow for access; | 6 | C129-C151 | Lake A | 0 | 43888 | [9 empty] | 06 | Corbiere and Sons Contracting168620200215-12Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting168620200215-12Operator - Principle - After Jan 1011825Inv#009 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1689 | 20200215-15 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 4 | Dynamic | 98.61 | 0 |  |  | 525.92 | 68.3696 | 594.2896 | 2020-02-15 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF | [6 empty] | Snowplowed Neys Road from Hwy to C-241 | 6 | C219-C236 | Ney's Road | 0 | 43888 | [9 empty] | 06 | Corbiere and Sons Contracting168920200215-15Dozer D6 or equal- After Jan 104525.92 | Corbiere and Sons Contracting168920200215-15Dozer D6 or equal- After Jan 104525.92Inv#009 | [5 empty] | 1 | 525.92 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1689 | 20200215-15 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 4 | Dynamic | 95.24 | 0 |  |  | 507.92 | 66.0296 | 573.9496 | 2020-02-15 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF | [6 empty] | Snowplowed Neys Road from Hwy to C-241 | 6 | C219-C236 | Ney's Road | 0 | 43888 | [9 empty] | 06 | Corbiere and Sons Contracting168920200215-15Grader - Cat 12 to 14 or equal- After Jan 104507.92 | Corbiere and Sons Contracting168920200215-15Grader - Cat 12 to 14 or equal- After Jan 104507.92Inv#009 | [5 empty] | 1 | 507.92 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1689 | 20200215-15 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-02-15 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF | [6 empty] | Snowplowed Neys Road from Hwy to C-241 | 6 | C219-C236 | Ney's Road | 0 | 43888 | [9 empty] | 06 | Corbiere and Sons Contracting168920200215-15Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting168920200215-15Light Truck - Pick up- After Jan 102487.5Inv#009 | [5 empty] | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1689 | 20200215-15 | 53510611 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-02-15 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF | [6 empty] | Snowplowed Neys Road from Hwy to C-241 | 6 | C219-C236 | Ney's Road | 0 | 43888 | [9 empty] | 06 | Corbiere and Sons Contracting168920200215-15L.O.A.2420 | Corbiere and Sons Contracting168920200215-15L.O.A.2420Inv#009 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1689 | 20200215-15 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 8 | HR |  |  | 75 | 0 | 600 | 78 | 678 | 2020-02-15 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF | [6 empty] | Snowplowed Neys Road from Hwy to C-241 | 6 | C219-C236 | Ney's Road | 0 | 43888 | [9 empty] | 06 | Corbiere and Sons Contracting168920200215-15Operator - Principle - After Jan 108600 | Corbiere and Sons Contracting168920200215-15Operator - Principle - After Jan 108600Inv#009 | [5 empty] | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1678 | 20200215-4 | 53520104 | Clearing | 0 | Chainsaw and consumables- After Jan 10 | 60 | 4 | unit/man/day | 0 | 0 |  |  | 240 | 31.2 | 271.2 | 2020-02-15 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hand Falling from A134 and B002-B003; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43888 |  | 37 | 43890 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting167820200215-4Chainsaw and consumables- After Jan 104240 | Corbiere and Sons Contracting167820200215-4Chainsaw and consumables- After Jan 104240Inv#009 |  |  | WF1-Handfalling |  |  | 1 | 240 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1678 | 20200215-4 | 53520104 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2020-02-15 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hand Falling from A134 and B002-B003; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43888 |  | 37 | 43890 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting167820200215-4Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting167820200215-4Light Truck - Pick up- After Jan 103731.25Inv#009 |  |  | WF1-Handfalling |  |  | 1 | 731.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1678 | 20200215-4 | 53520104 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2020-02-15 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hand Falling from A134 and B002-B003; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43888 |  | 37 | 43890 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting167820200215-4Foreman121140 | Corbiere and Sons Contracting167820200215-4Foreman121140Inv#009 |  |  | WF1-Handfalling |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1678 | 20200215-4 | 53520104 | Clearing | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2020-02-15 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hand Falling from A134 and B002-B003; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43888 |  | 37 | 43890 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting167820200215-4L.O.A.51050 | Corbiere and Sons Contracting167820200215-4L.O.A.51050Inv#009 |  |  | WF1-Handfalling |  |  | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1678 | 20200215-4 | 53520104 | Clearing | 0 | Labourer - Specialized - After Jan 10 | 70 | 44 | HR |  |  | 70 | 0 | 3080 | 400.4 | 3480.4 | 2020-02-15 | 1 | Inv#009 | 43894 | 86 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hand Falling from A134 and B002-B003; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43888 |  | 37 | 43890 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting167820200215-4Labourer - Specialized - After Jan 10443080 | Corbiere and Sons Contracting167820200215-4Labourer - Specialized - After Jan 10443080Inv#009 |  |  | WF1-Handfalling |  |  | 1 | 3080 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1680 | 20200215-6 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-02-15 | 1 | Inv#009 | 43894 | 86 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 10 |  | Corbeire - Standby - Ongoing | 9010 | Blade Collins on SB due to float moves being shut down by road conditions; | 6 | C171-C185 | Prairie River | 1 | 43888 | [9 empty] | 06 | Corbiere and Sons Contracting168020200215-6L.O.A.1210 | Corbiere and Sons Contracting168020200215-6L.O.A.1210Inv#009 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1680 | 20200215-6 | 53510611 | Access | 0 | Labourer - General - After Jan 10 | 60 | 5 | HR |  |  | 60 | 0 | 300 | 39 | 339 | 2020-02-15 | 1 | Inv#009 | 43894 | 86 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 10 |  | Corbeire - Standby - Ongoing | 9010 | Blade Collins on SB due to float moves being shut down by road conditions; | 6 | C171-C185 | Prairie River | 1 | 43888 | [9 empty] | 06 | Corbiere and Sons Contracting168020200215-6Labourer - General - After Jan 105300 | Corbiere and Sons Contracting168020200215-6Labourer - General - After Jan 105300Inv#009 | [5 empty] | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1745 | 20200216-10 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 9 | Dynamic | 95.24 | 0 |  |  | 1142.82 | 148.5666 | 1291.3866 | 2020-02-16 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Plowing across all access roads; | 6 | C186 - C190 | Prairie River | 0 | 43894 |  | 41 | 43894 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting174520200216-10Grader - Cat 12 to 14 or equal- After Jan 1091142.82 | Corbiere and Sons Contracting174520200216-10Grader - Cat 12 to 14 or equal- After Jan 1091142.82Inv#018 | [5 empty] | 1 | 1142.82 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1745 | 20200216-10 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 |  |  |  | 243.75 | 31.6875 | 275.4375 | 2020-02-16 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Plowing across all access roads; | 6 | C186 - C190 | Prairie River | 0 | 43894 |  | 41 | 43894 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting174520200216-10Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting174520200216-10Light Truck - Pick up- After Jan 101243.75Inv#018 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1745 | 20200216-10 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-02-16 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Plowing across all access roads; | 6 | C186 - C190 | Prairie River | 0 | 43894 |  | 41 | 43894 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting174520200216-10L.O.A.1210 | Corbiere and Sons Contracting174520200216-10L.O.A.1210Inv#018 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1745 | 20200216-10 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2020-02-16 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Plowing across all access roads; | 6 | C186 - C190 | Prairie River | 0 | 43894 |  | 41 | 43894 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting174520200216-10Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting174520200216-10Operator - Principle - After Jan 1011825Inv#018 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1748 | 20200216-13 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 5 | Dynamic | 98.61 | 0 |  |  | 657.4 | 85.462 | 742.862 | 2020-02-16 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Access maintenance from C138-C141 | 6 | C152 - C154 | Lake A | 0 | 43894 |  | 41 | 43894 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting174820200216-13Dozer D6 or equal- After Jan 105657.4 | Corbiere and Sons Contracting174820200216-13Dozer D6 or equal- After Jan 105657.4Inv#018 | [5 empty] | 1 | 657.4 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1748 | 20200216-13 | 53510611 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 4 | Dynamic | 110.22 | 0 |  |  | 587.84 | 76.4192 | 664.2592 | 2020-02-16 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Access maintenance from C138-C141 | 6 | C152 - C154 | Lake A | 0 | 43894 |  | 41 | 43894 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting174820200216-13Excavator - 36 ton- After Jan 104587.84 | Corbiere and Sons Contracting174820200216-13Excavator - 36 ton- After Jan 104587.84Inv#018 | [5 empty] | 1 | 587.84 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1748 | 20200216-13 | 53510611 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-02-16 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Access maintenance from C138-C141 | 6 | C152 - C154 | Lake A | 0 | 43894 |  | 41 | 43894 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting174820200216-13L.O.A.2420 | Corbiere and Sons Contracting174820200216-13L.O.A.2420Inv#018 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1748 | 20200216-13 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2020-02-16 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Access maintenance from C138-C141 | 6 | C152 - C154 | Lake A | 0 | 43894 |  | 41 | 43894 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting174820200216-13Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting174820200216-13Operator - Principle - After Jan 1011825Inv#018 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1753 | 20200216-18 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 95.24 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2020-02-16 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Plowed and Graded turn around to Hwy for access roads; | 6 | C257-C267 | Hare Lake | 0 | 43894 |  | 41 | 43894 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting175320200216-18Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting175320200216-18Grader - Cat 12 to 14 or equal- After Jan 10101269.8Inv#018 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1753 | 20200216-18 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-02-16 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Plowed and Graded turn around to Hwy for access roads; | 6 | C257-C267 | Hare Lake | 0 | 43894 |  | 41 | 43894 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting175320200216-18Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting175320200216-18Light Truck - Pick up- After Jan 101243.75Inv#018 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1753 | 20200216-18 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-02-16 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Plowed and Graded turn around to Hwy for access roads; | 6 | C257-C267 | Hare Lake | 0 | 43894 |  | 41 | 43894 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting175320200216-18L.O.A.1210 | Corbiere and Sons Contracting175320200216-18L.O.A.1210Inv#018 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1753 | 20200216-18 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 10 | HR |  |  | 75 | 0 | 750 | 97.5 | 847.5 | 2020-02-16 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Plowed and Graded turn around to Hwy for access roads; | 6 | C257-C267 | Hare Lake | 0 | 43894 |  | 41 | 43894 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting175320200216-18Operator - Principle - After Jan 1010750 | Corbiere and Sons Contracting175320200216-18Operator - Principle - After Jan 1010750Inv#018 | [5 empty] | 1 | 750 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1737 | 20200216-3 | 53520104 | Clearing | 0 | Chainsaw and consumables- After Jan 10 | 60 | 5 | unit/man/day | 0 | 0 |  |  | 300 | 39 | 339 | 2020-02-16 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hand Falling from A135, B002-B004; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43894 |  | 36 | 43894 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting173720200216-3Chainsaw and consumables- After Jan 105300 | Corbiere and Sons Contracting173720200216-3Chainsaw and consumables- After Jan 105300Inv#018 |  |  | WF1-Handfalling |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1737 | 20200216-3 | 53520104 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-02-16 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hand Falling from A135, B002-B004; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43894 |  | 36 | 43894 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting173720200216-3Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting173720200216-3Light Truck - Pick up- After Jan 102487.5Inv#018 |  |  | WF1-Handfalling |  |  | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1737 | 20200216-3 | 53520104 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2020-02-16 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hand Falling from A135, B002-B004; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43894 |  | 36 | 43894 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting173720200216-3Foreman121140 | Corbiere and Sons Contracting173720200216-3Foreman121140Inv#018 |  |  | WF1-Handfalling |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1737 | 20200216-3 | 53520104 | Clearing | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2020-02-16 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hand Falling from A135, B002-B004; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43894 |  | 36 | 43894 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting173720200216-3L.O.A.61260 | Corbiere and Sons Contracting173720200216-3L.O.A.61260Inv#018 |  |  | WF1-Handfalling |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1737 | 20200216-3 | 53520104 | Clearing | 0 | Labourer - Specialized - After Jan 10 | 70 | 55 | HR |  |  | 70 | 0 | 3850 | 500.5 | 4350.5 | 2020-02-16 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hand Falling from A135, B002-B004; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43894 |  | 36 | 43894 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting173720200216-3Labourer - Specialized - After Jan 10553850 | Corbiere and Sons Contracting173720200216-3Labourer - Specialized - After Jan 10553850Inv#018 |  |  | WF1-Handfalling |  |  | 1 | 3850 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1738 | 20200216-4-R1 | 53520104 | Clearing | 0 | Chainsaw and consumables- After Jan 10 | 60 | 3 | unit/man/day | 0 | 0 |  |  | 180 | 23.4 | 203.4 | 2020-02-16 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hand Falling at A078 | 1 | A-055 to A-084 | Eldorado | 0 | 43894 |  | 36 | 43917 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting173820200216-4-R1Chainsaw and consumables- After Jan 103180 | Corbiere and Sons Contracting173820200216-4-R1Chainsaw and consumables- After Jan 103180Inv#022 |  |  | WF1-Handfalling |  |  | 1 | 180 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1738 | 20200216-4-R1 | 53520104 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-02-16 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hand Falling at A078 | 1 | A-055 to A-084 | Eldorado | 0 | 43894 |  | 36 | 43917 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting173820200216-4-R1Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting173820200216-4-R1Light Truck - Pick up- After Jan 102487.5Inv#022 |  |  | WF1-Handfalling |  |  | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1738 | 20200216-4-R1 | 53520104 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2020-02-16 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hand Falling at A078 | 1 | A-055 to A-084 | Eldorado | 0 | 43894 |  | 36 | 43917 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting173820200216-4-R1Foreman121140 | Corbiere and Sons Contracting173820200216-4-R1Foreman121140Inv#022 |  |  | WF1-Handfalling |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1738 | 20200216-4-R1 | 53520104 | Clearing | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2020-02-16 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hand Falling at A078 | 1 | A-055 to A-084 | Eldorado | 0 | 43894 |  | 36 | 43917 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting173820200216-4-R1L.O.A.4840 | Corbiere and Sons Contracting173820200216-4-R1L.O.A.4840Inv#022 |  |  | WF1-Handfalling |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1738 | 20200216-4-R1 | 53520104 | Clearing | 0 | Labourer - Specialized - After Jan 10 | 70 | 33 | HR |  |  | 70 | 0 | 2310 | 300.3 | 2610.3 | 2020-02-16 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hand Falling at A078 | 1 | A-055 to A-084 | Eldorado | 0 | 43894 |  | 36 | 43917 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting173820200216-4-R1Labourer - Specialized - After Jan 10332310 | Corbiere and Sons Contracting173820200216-4-R1Labourer - Specialized - After Jan 10332310Inv#022 |  |  | WF1-Handfalling |  |  | 1 | 2310 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1759 | 20200217-11 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 9 | Dynamic | 95.24 | 0 |  |  | 1142.82 | 148.5666 | 1291.3866 | 2020-02-17 | 1 | Inv#010 | 43906 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Plowing and maintenance of access roads | 6 | C152 - C154 | Lake A | 0 | 43894 |  | 41 | 43897 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting175920200217-11Grader - Cat 12 to 14 or equal- After Jan 1091142.82 | Corbiere and Sons Contracting175920200217-11Grader - Cat 12 to 14 or equal- After Jan 1091142.82Inv#010 | [5 empty] | 1 | 1142.82 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1759 | 20200217-11 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-02-17 | 1 | Inv#010 | 43906 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Plowing and maintenance of access roads | 6 | C152 - C154 | Lake A | 0 | 43894 |  | 41 | 43897 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting175920200217-11L.O.A.1210 | Corbiere and Sons Contracting175920200217-11L.O.A.1210Inv#010 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1759 | 20200217-11 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2020-02-17 | 1 | Inv#010 | 43906 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Plowing and maintenance of access roads | 6 | C152 - C154 | Lake A | 0 | 43894 |  | 41 | 43897 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting175920200217-11Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting175920200217-11Operator - Principle - After Jan 1011825Inv#010 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1771 | 20200217-23 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 7 | Dynamic | 95.24 | 0 |  |  | 888.86 | 115.5518 | 1004.4118 | 2020-02-17 | 1 | Inv#010 | 43906 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Plowing of Neys Rd. | 6 | C236 - C243 | Neys | 0 | 43894 |  | 41 | 43895 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting177120200217-23Grader - Cat 12 to 14 or equal- After Jan 107888.86 | Corbiere and Sons Contracting177120200217-23Grader - Cat 12 to 14 or equal- After Jan 107888.86Inv#010 | [5 empty] | 1 | 888.86 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1771 | 20200217-23 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-02-17 | 1 | Inv#010 | 43906 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Plowing of Neys Rd. | 6 | C236 - C243 | Neys | 0 | 43894 |  | 41 | 43895 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting177120200217-23Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting177120200217-23Light Truck - Pick up- After Jan 101243.75Inv#010 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1771 | 20200217-23 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 7 | HR |  |  | 75 | 0 | 525 | 68.25 | 593.25 | 2020-02-17 | 1 | Inv#010 | 43906 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Plowing of Neys Rd. | 6 | C236 - C243 | Neys | 0 | 43894 |  | 41 | 43895 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting177120200217-23Operator - Principle - After Jan 107525 | Corbiere and Sons Contracting177120200217-23Operator - Principle - After Jan 107525Inv#010 | [5 empty] | 1 | 525 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1961 | 20200217-3 | 53520104 | Clearing | 0 | Chainsaw and consumables- After Jan 10 | 60 | 4 | unit/man/day | 0 | 0 |  |  | 240 | 31.2 | 271.2 | 2020-02-17 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hand Falling from B008-B009 and from A134 and B010; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43894 |  | 36 | 43894 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting196120200217-3Chainsaw and consumables- After Jan 104240 | Corbiere and Sons Contracting196120200217-3Chainsaw and consumables- After Jan 104240Inv#018 |  |  | WF1-Handfalling |  |  | 1 | 240 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1961 | 20200217-3 | 53520104 | Clearing | 0 | Chainsaw and consumables- After Jan 10 | 60 | 6 | unit/man/day | 0 | 0 |  |  | 360 | 46.8 | 406.8 | 2020-02-17 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hand Falling from B008-B009 and from A134 and B010; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43894 |  | 36 | 43894 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting196120200217-3Chainsaw and consumables- After Jan 106360 | Corbiere and Sons Contracting196120200217-3Chainsaw and consumables- After Jan 106360Inv#018 |  |  | WF1-Handfalling |  |  | 1 | 360 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1961 | 20200217-3 | 53520104 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 5 | DAY | 182.81 | 0 |  |  | 1218.75 | 158.4375 | 1377.1875 | 2020-02-17 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hand Falling from B008-B009 and from A134 and B010; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43894 |  | 36 | 43894 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting196120200217-3Light Truck - Pick up- After Jan 1051218.75 | Corbiere and Sons Contracting196120200217-3Light Truck - Pick up- After Jan 1051218.75Inv#018 |  |  | WF1-Handfalling |  |  | 1 | 1218.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1961 | 20200217-3 | 53520104 | Clearing | 0 | Foreman | 95 | 24 | HR |  |  | 95 | 0 | 2280 | 296.4 | 2576.4 | 2020-02-17 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hand Falling from B008-B009 and from A134 and B010; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43894 |  | 36 | 43894 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting196120200217-3Foreman242280 | Corbiere and Sons Contracting196120200217-3Foreman242280Inv#018 |  |  | WF1-Handfalling |  |  | 1 | 2280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1961 | 20200217-3 | 53520104 | Clearing | 0 | L.O.A. | 210 | 12 | DAY |  |  |  | 0 | 2520 | 327.6 | 2847.6 | 2020-02-17 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hand Falling from B008-B009 and from A134 and B010; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43894 |  | 36 | 43894 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting196120200217-3L.O.A.122520 | Corbiere and Sons Contracting196120200217-3L.O.A.122520Inv#018 |  |  | WF1-Handfalling |  |  | 1 | 2520 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1961 | 20200217-3 | 53520104 | Clearing | 0 | Labourer - Specialized - After Jan 10 | 70 | 110 | HR |  |  | 70 | 0 | 7700 | 1001 | 8701 | 2020-02-17 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hand Falling from B008-B009 and from A134 and B010; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43894 |  | 36 | 43894 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting196120200217-3Labourer - Specialized - After Jan 101107700 | Corbiere and Sons Contracting196120200217-3Labourer - Specialized - After Jan 101107700Inv#018 |  |  | WF1-Handfalling |  |  | 1 | 7700 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1788 | 20200218-12 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 7 | Dynamic | 98.61 | 0 |  |  | 920.36 | 119.6468 | 1040.0068 | 2020-02-18 | 1 | Inv#010 | 43906 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Maintenance of access roads; | 6 | C186 - C190 | Prairie River | 0 | 43895 |  | 41 | 43895 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting178820200218-12Dozer D6 or equal- After Jan 107920.36 | Corbiere and Sons Contracting178820200218-12Dozer D6 or equal- After Jan 107920.36Inv#010 | [5 empty] | 1 | 920.36 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1788 | 20200218-12 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-02-18 | 1 | Inv#010 | 43906 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Maintenance of access roads; | 6 | C186 - C190 | Prairie River | 0 | 43895 |  | 41 | 43895 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting178820200218-12L.O.A.1210 | Corbiere and Sons Contracting178820200218-12L.O.A.1210Inv#010 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1788 | 20200218-12 | 53510311 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 8 | HR |  |  | 75 | 0 | 600 | 78 | 678 | 2020-02-18 | 1 | Inv#010 | 43906 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Maintenance of access roads; | 6 | C186 - C190 | Prairie River | 0 | 43895 |  | 41 | 43895 | [5 empty] | Martin Hunt | 03 | Corbiere and Sons Contracting178820200218-12Operator - Principle - After Jan 108600 | Corbiere and Sons Contracting178820200218-12Operator - Principle - After Jan 108600Inv#010 | [5 empty] | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1794 | 20200218-18 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 4 | Dynamic | 98.61 | 0 |  |  | 525.92 | 68.3696 | 594.2896 | 2020-02-18 | 1 | Inv#010 | 43906 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Snow removal and plowing of access roads; | 6 | C152 - C154 | Lake A | 0 | 43895 |  | 41 | 43895 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting179420200218-18Dozer D6 or equal- After Jan 104525.92 | Corbiere and Sons Contracting179420200218-18Dozer D6 or equal- After Jan 104525.92Inv#010 | [5 empty] | 1 | 525.92 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1794 | 20200218-18 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 9 | Dynamic | 95.24 | 0 |  |  | 1142.82 | 148.5666 | 1291.3866 | 2020-02-18 | 1 | Inv#010 | 43906 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Snow removal and plowing of access roads; | 6 | C152 - C154 | Lake A | 0 | 43895 |  | 41 | 43895 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting179420200218-18Grader - Cat 12 to 14 or equal- After Jan 1091142.82 | Corbiere and Sons Contracting179420200218-18Grader - Cat 12 to 14 or equal- After Jan 1091142.82Inv#010 | [5 empty] | 1 | 1142.82 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1794 | 20200218-18 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-02-18 | 1 | Inv#010 | 43906 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Snow removal and plowing of access roads; | 6 | C152 - C154 | Lake A | 0 | 43895 |  | 41 | 43895 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting179420200218-18Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting179420200218-18Light Truck - Pick up- After Jan 101243.75Inv#010 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1794 | 20200218-18 | 53510611 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2020-02-18 | 1 | Inv#010 | 43906 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Snow removal and plowing of access roads; | 6 | C152 - C154 | Lake A | 0 | 43895 |  | 41 | 43895 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting179420200218-18L.O.A.3630 | Corbiere and Sons Contracting179420200218-18L.O.A.3630Inv#010 | [5 empty] | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1794 | 20200218-18 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 28 | HR |  |  | 75 | 0 | 2100 | 273 | 2373 | 2020-02-18 | 1 | Inv#010 | 43906 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Snow removal and plowing of access roads; | 6 | C152 - C154 | Lake A | 0 | 43895 |  | 41 | 43895 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting179420200218-18Operator - Principle - After Jan 10282100 | Corbiere and Sons Contracting179420200218-18Operator - Principle - After Jan 10282100Inv#010 | [5 empty] | 1 | 2100 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1797 | 20200218-21 | 53510611 | Access | 0 | Dozer - D5 or equal- After Jan 10 | 80.93 | 5 | Dynamic | 60.7 |  |  |  | 404.65 | 52.6045 | 457.2545 | 2020-02-18 | 1 | Inv#010 | 43906 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter maintenance done at C191 | 6 | C191 - C195 | Del Lake West | 0 | 43895 |  | 41 | 43895 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting179720200218-21Dozer - D5 or equal- After Jan 105404.65 | Corbiere and Sons Contracting179720200218-21Dozer - D5 or equal- After Jan 105404.65Inv#010 | [5 empty] | 1 | 404.65 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1797 | 20200218-21 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5 | HR |  |  | 75 | 0 | 375 | 48.75 | 423.75 | 2020-02-18 | 1 | Inv#010 | 43906 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter maintenance done at C191 | 6 | C191 - C195 | Del Lake West | 0 | 43895 |  | 41 | 43895 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting179720200218-21Operator - Principle - After Jan 105375 | Corbiere and Sons Contracting179720200218-21Operator - Principle - After Jan 105375Inv#010 | [5 empty] | 1 | 375 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1804 | 20200218-28 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 5 | Dynamic | 98.61 | 0 |  |  | 657.4 | 85.462 | 742.862 | 2020-02-18 | 1 | Inv#010 | 43906 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Plowing of snow across various areas | 6 | C257-C267 | Hare Lake | 0 | 43895 |  | 41 | 43895 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting180420200218-28Dozer D6 or equal- After Jan 105657.4 | Corbiere and Sons Contracting180420200218-28Dozer D6 or equal- After Jan 105657.4Inv#010 | [5 empty] | 1 | 657.4 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1804 | 20200218-28 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 12 | Dynamic | 95.24 | 0 |  |  | 1523.76 | 198.0888 | 1721.8488 | 2020-02-18 | 1 | Inv#010 | 43906 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Plowing of snow across various areas | 6 | C257-C267 | Hare Lake | 0 | 43895 |  | 41 | 43895 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting180420200218-28Grader - Cat 12 to 14 or equal- After Jan 10121523.76 | Corbiere and Sons Contracting180420200218-28Grader - Cat 12 to 14 or equal- After Jan 10121523.76Inv#010 | [5 empty] | 1 | 1523.76 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1804 | 20200218-28 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-02-18 | 1 | Inv#010 | 43906 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Plowing of snow across various areas | 6 | C257-C267 | Hare Lake | 0 | 43895 |  | 41 | 43895 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting180420200218-28Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting180420200218-28Light Truck - Pick up- After Jan 101243.75Inv#010 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1804 | 20200218-28 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-02-18 | 1 | Inv#010 | 43906 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Plowing of snow across various areas | 6 | C257-C267 | Hare Lake | 0 | 43895 |  | 41 | 43895 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting180420200218-28L.O.A.1210 | Corbiere and Sons Contracting180420200218-28L.O.A.1210Inv#010 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1804 | 20200218-28 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 17 | HR |  |  | 75 | 0 | 1275 | 165.75 | 1440.75 | 2020-02-18 | 1 | Inv#010 | 43906 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Plowing of snow across various areas | 6 | C257-C267 | Hare Lake | 0 | 43895 |  | 41 | 43895 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting180420200218-28Operator - Principle - After Jan 10171275 | Corbiere and Sons Contracting180420200218-28Operator - Principle - After Jan 10171275Inv#010 | [5 empty] | 1 | 1275 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1779 | 20200218-3 | 53520104 | Clearing | 0 | Chainsaw and consumables- After Jan 10 | 60 | 11 | unit/man/day | 0 | 0 |  |  | 660 | 85.8 | 745.8 | 2020-02-18 | 1 | Inv#010 | 43906 | 87 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hand Falling from B008,B009,B010 and at A134-A135; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43895 | . | 36 | 43897 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting177920200218-3Chainsaw and consumables- After Jan 1011660 | Corbiere and Sons Contracting177920200218-3Chainsaw and consumables- After Jan 1011660Inv#010 |  |  | WF1-Handfalling |  |  | 1 | 660 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1779 | 20200218-3 | 53520104 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 6 | DAY | 182.81 | 0 |  |  | 1462.5 | 190.125 | 1652.625 | 2020-02-18 | 1 | Inv#010 | 43906 | 87 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hand Falling from B008,B009,B010 and at A134-A135; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43895 | . | 36 | 43897 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting177920200218-3Light Truck - Pick up- After Jan 1061462.5 | Corbiere and Sons Contracting177920200218-3Light Truck - Pick up- After Jan 1061462.5Inv#010 |  |  | WF1-Handfalling |  |  | 1 | 1462.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1779 | 20200218-3 | 53520104 | Clearing | 0 | Foreman | 95 | 24 | HR |  |  | 95 | 0 | 2280 | 296.4 | 2576.4 | 2020-02-18 | 1 | Inv#010 | 43906 | 87 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hand Falling from B008,B009,B010 and at A134-A135; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43895 | . | 36 | 43897 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting177920200218-3Foreman242280 | Corbiere and Sons Contracting177920200218-3Foreman242280Inv#010 |  |  | WF1-Handfalling |  |  | 1 | 2280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1779 | 20200218-3 | 53520104 | Clearing | 0 | L.O.A. | 210 | 13 | DAY |  |  |  | 0 | 2730 | 354.9 | 3084.9 | 2020-02-18 | 1 | Inv#010 | 43906 | 87 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hand Falling from B008,B009,B010 and at A134-A135; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43895 | . | 36 | 43897 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting177920200218-3L.O.A.132730 | Corbiere and Sons Contracting177920200218-3L.O.A.132730Inv#010 |  |  | WF1-Handfalling |  |  | 1 | 2730 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1779 | 20200218-3 | 53520104 | Clearing | 0 | Labourer - Specialized - After Jan 10 | 70 | 121 | HR |  |  | 70 | 0 | 8470 | 1101.1 | 9571.1 | 2020-02-18 | 1 | Inv#010 | 43906 | 87 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hand Falling from B008,B009,B010 and at A134-A135; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43895 | . | 36 | 43897 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting177920200218-3Labourer - Specialized - After Jan 101218470 | Corbiere and Sons Contracting177920200218-3Labourer - Specialized - After Jan 101218470Inv#010 |  |  | WF1-Handfalling |  |  | 1 | 8470 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1781 | 20200218-5 | 53510211 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 9 | Dynamic | 95.24 | 0 |  |  | 1142.82 | 148.5666 | 1291.3866 | 2020-02-18 | 1 | Inv#010 | 43906 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grading of access roads | 2 | B018 - B029 | Black Sturgeon | 0 | 43895 |  | 36 | 43897 | [5 empty] | Mike Lecocq | 02 | Corbiere and Sons Contracting178120200218-5Grader - Cat 12 to 14 or equal- After Jan 1091142.82 | Corbiere and Sons Contracting178120200218-5Grader - Cat 12 to 14 or equal- After Jan 1091142.82Inv#010 | [5 empty] | 1 | 1142.82 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1781 | 20200218-5 | 53510211 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-02-18 | 1 | Inv#010 | 43906 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grading of access roads | 2 | B018 - B029 | Black Sturgeon | 0 | 43895 |  | 36 | 43897 | [5 empty] | Mike Lecocq | 02 | Corbiere and Sons Contracting178120200218-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting178120200218-5Light Truck - Pick up- After Jan 101243.75Inv#010 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1781 | 20200218-5 | 53510211 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-02-18 | 1 | Inv#010 | 43906 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grading of access roads | 2 | B018 - B029 | Black Sturgeon | 0 | 43895 |  | 36 | 43897 | [5 empty] | Mike Lecocq | 02 | Corbiere and Sons Contracting178120200218-5L.O.A.1210 | Corbiere and Sons Contracting178120200218-5L.O.A.1210Inv#010 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1781 | 20200218-5 | 53510211 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2020-02-18 | 1 | Inv#010 | 43906 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grading of access roads | 2 | B018 - B029 | Black Sturgeon | 0 | 43895 |  | 36 | 43897 | [5 empty] | Mike Lecocq | 02 | Corbiere and Sons Contracting178120200218-5Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting178120200218-5Operator - Principle - After Jan 1011825Inv#010 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1815 | 20200219-10 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 8 | Dynamic | 98.61 | 0 |  |  | 1051.84 | 136.7392 | 1188.5792 | 2020-02-19 | 1 | Inv#010 | 43906 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Maintenance from laydown to ROW; | 6 | C152 - C154 | Lake A | 0 | 43895 |  | 41 | 43897 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting181520200219-10Dozer D6 or equal- After Jan 1081051.84 | Corbiere and Sons Contracting181520200219-10Dozer D6 or equal- After Jan 1081051.84Inv#010 | [5 empty] | 1 | 1051.84 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1815 | 20200219-10 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-02-19 | 1 | Inv#010 | 43906 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Maintenance from laydown to ROW; | 6 | C152 - C154 | Lake A | 0 | 43895 |  | 41 | 43897 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting181520200219-10Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting181520200219-10Light Truck - Pick up- After Jan 101243.75Inv#010 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1815 | 20200219-10 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-02-19 | 1 | Inv#010 | 43906 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Maintenance from laydown to ROW; | 6 | C152 - C154 | Lake A | 0 | 43895 |  | 41 | 43897 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting181520200219-10L.O.A.1210 | Corbiere and Sons Contracting181520200219-10L.O.A.1210Inv#010 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1815 | 20200219-10 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 8 | HR |  |  | 75 | 0 | 600 | 78 | 678 | 2020-02-19 | 1 | Inv#010 | 43906 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Maintenance from laydown to ROW; | 6 | C152 - C154 | Lake A | 0 | 43895 |  | 41 | 43897 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting181520200219-10Operator - Principle - After Jan 108600 | Corbiere and Sons Contracting181520200219-10Operator - Principle - After Jan 108600Inv#010 | [5 empty] | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1816 | 20200219-11 | 53510611 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 6 | Dynamic | 110.22 | 0 |  |  | 881.76 | 114.6288 | 996.3888 | 2020-02-19 | 1 | Inv#010 | 43906 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Access maintenance and C214; Traffic Control for maintenance and float; | 6 | C215 - C216 | Middleton | 0 | 43895 |  | 41 | 43897 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting181620200219-11Excavator - 36 ton- After Jan 106881.76 | Corbiere and Sons Contracting181620200219-11Excavator - 36 ton- After Jan 106881.76Inv#010 | [5 empty] | 1 | 881.76 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1816 | 20200219-11 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-02-19 | 1 | Inv#010 | 43906 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Access maintenance and C214; Traffic Control for maintenance and float; | 6 | C215 - C216 | Middleton | 0 | 43895 |  | 41 | 43897 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting181620200219-11Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting181620200219-11Light Truck - Pick up- After Jan 102487.5Inv#010 | [5 empty] | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1816 | 20200219-11 | 53510611 | Access | 0 | Foreman | 95 | 11 | HR |  |  | 95 | 0 | 1045 | 135.85 | 1180.85 | 2020-02-19 | 1 | Inv#010 | 43906 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Access maintenance and C214; Traffic Control for maintenance and float; | 6 | C215 - C216 | Middleton | 0 | 43895 |  | 41 | 43897 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting181620200219-11Foreman111045 | Corbiere and Sons Contracting181620200219-11Foreman111045Inv#010 | [5 empty] | 1 | 1045 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1816 | 20200219-11 | 53510611 | Access | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2020-02-19 | 1 | Inv#010 | 43906 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Access maintenance and C214; Traffic Control for maintenance and float; | 6 | C215 - C216 | Middleton | 0 | 43895 |  | 41 | 43897 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting181620200219-11L.O.A.51050 | Corbiere and Sons Contracting181620200219-11L.O.A.51050Inv#010 | [5 empty] | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1816 | 20200219-11 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 75 | 0 | 450 | 58.5 | 508.5 | 2020-02-19 | 1 | Inv#010 | 43906 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Access maintenance and C214; Traffic Control for maintenance and float; | 6 | C215 - C216 | Middleton | 0 | 43895 |  | 41 | 43897 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting181620200219-11Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting181620200219-11Operator - Principle - After Jan 106450Inv#010 | [5 empty] | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1816 | 20200219-11 | 53510611 | Access | 0 | Labourer - General - After Jan 10 | 60 | 33 | HR |  |  | 60 | 0 | 1980 | 257.4 | 2237.4 | 2020-02-19 | 1 | Inv#010 | 43906 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Access maintenance and C214; Traffic Control for maintenance and float; | 6 | C215 - C216 | Middleton | 0 | 43895 |  | 41 | 43897 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting181620200219-11Labourer - General - After Jan 10331980 | Corbiere and Sons Contracting181620200219-11Labourer - General - After Jan 10331980Inv#010 | [5 empty] | 1 | 1980 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1819 | 20200219-14 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 5 | Dynamic | 98.61 | 0 |  |  | 657.4 | 85.462 | 742.862 | 2020-02-19 | 1 | Inv#010 | 43906 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter access maintenance being done at C191; | 6 | C191 - C195 | Del Lake West | 0 | 43895 |  | 41 | 43897 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting181920200219-14Dozer D6 or equal- After Jan 105657.4 | Corbiere and Sons Contracting181920200219-14Dozer D6 or equal- After Jan 105657.4Inv#010 | [5 empty] | 1 | 657.4 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1819 | 20200219-14 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-02-19 | 1 | Inv#010 | 43906 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter access maintenance being done at C191; | 6 | C191 - C195 | Del Lake West | 0 | 43895 |  | 41 | 43897 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting181920200219-14L.O.A.1210 | Corbiere and Sons Contracting181920200219-14L.O.A.1210Inv#010 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1819 | 20200219-14 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5 | HR |  |  | 75 | 0 | 375 | 48.75 | 423.75 | 2020-02-19 | 1 | Inv#010 | 43906 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter access maintenance being done at C191; | 6 | C191 - C195 | Del Lake West | 0 | 43895 |  | 41 | 43897 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting181920200219-14Operator - Principle - After Jan 105375 | Corbiere and Sons Contracting181920200219-14Operator - Principle - After Jan 105375Inv#010 | [5 empty] | 1 | 375 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1825 | 20200219-20 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 4 | Dynamic | 98.61 | 0 |  |  | 525.92 | 68.3696 | 594.2896 | 2020-02-19 | 1 | Inv#010 | 43906 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Plowing hills and peninsula road as directed by Valard; | 6 | C268-C279 | Peninsula Road | 0 | 43895 |  | 41 | 43897 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting182520200219-20Dozer D6 or equal- After Jan 104525.92 | Corbiere and Sons Contracting182520200219-20Dozer D6 or equal- After Jan 104525.92Inv#010 | [5 empty] | 1 | 525.92 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1825 | 20200219-20 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 2 | Dynamic | 95.24 | 0 |  |  | 253.96 | 33.0148 | 286.9748 | 2020-02-19 | 1 | Inv#010 | 43906 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Plowing hills and peninsula road as directed by Valard; | 6 | C268-C279 | Peninsula Road | 0 | 43895 |  | 41 | 43897 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting182520200219-20Grader - Cat 12 to 14 or equal- After Jan 102253.96 | Corbiere and Sons Contracting182520200219-20Grader - Cat 12 to 14 or equal- After Jan 102253.96Inv#010 | [5 empty] | 1 | 253.96 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1825 | 20200219-20 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-02-19 | 1 | Inv#010 | 43906 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Plowing hills and peninsula road as directed by Valard; | 6 | C268-C279 | Peninsula Road | 0 | 43895 |  | 41 | 43897 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting182520200219-20Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting182520200219-20Light Truck - Pick up- After Jan 102487.5Inv#010 | [5 empty] | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1825 | 20200219-20 | 53510611 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 2 | Dynamic | 91.79 | 0 |  |  | 244.78 | 31.8214 | 276.6014 | 2020-02-19 | 1 | Inv#010 | 43906 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Plowing hills and peninsula road as directed by Valard; | 6 | C268-C279 | Peninsula Road | 0 | 43895 |  | 41 | 43897 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting182520200219-20Tractor Trailer - 60 Ton- After Jan 102244.78 | Corbiere and Sons Contracting182520200219-20Tractor Trailer - 60 Ton- After Jan 102244.78Inv#010 | [5 empty] | 1 | 244.78 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1825 | 20200219-20 | 53510611 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2020-02-19 | 1 | Inv#010 | 43906 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Plowing hills and peninsula road as directed by Valard; | 6 | C268-C279 | Peninsula Road | 0 | 43895 |  | 41 | 43897 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting182520200219-20L.O.A.3630 | Corbiere and Sons Contracting182520200219-20L.O.A.3630Inv#010 | [5 empty] | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1825 | 20200219-20 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 75 | 0 | 450 | 58.5 | 508.5 | 2020-02-19 | 1 | Inv#010 | 43906 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Plowing hills and peninsula road as directed by Valard; | 6 | C268-C279 | Peninsula Road | 0 | 43895 |  | 41 | 43897 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting182520200219-20Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting182520200219-20Operator - Principle - After Jan 106450Inv#010 | [5 empty] | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1825 | 20200219-20 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 2 | HR |  |  | 70 | 0 | 140 | 18.2 | 158.2 | 2020-02-19 | 1 | Inv#010 | 43906 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Plowing hills and peninsula road as directed by Valard; | 6 | C268-C279 | Peninsula Road | 0 | 43895 |  | 41 | 43897 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting182520200219-20Driver - AZ - After Jan 102140 | Corbiere and Sons Contracting182520200219-20Driver - AZ - After Jan 102140Inv#010 | [5 empty] | 1 | 140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1808 | 20200219-3 | 53520104 | Clearing | 0 | Chainsaw and consumables- After Jan 10 | 60 | 13 | unit/man/day | 0 | 0 |  |  | 780 | 101.4 | 881.4 | 2020-02-19 | 1 | Inv#010 | 43906 | 87 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hand Falling from B017, and then down to B010 and A134; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43895 |  | 36 | 43897 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting180820200219-3Chainsaw and consumables- After Jan 1013780 | Corbiere and Sons Contracting180820200219-3Chainsaw and consumables- After Jan 1013780Inv#010 |  |  | WF1-Handfalling |  |  | 1 | 780 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1808 | 20200219-3 | 53520104 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 6 | DAY | 182.81 | 0 |  |  | 1462.5 | 190.125 | 1652.625 | 2020-02-19 | 1 | Inv#010 | 43906 | 87 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hand Falling from B017, and then down to B010 and A134; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43895 |  | 36 | 43897 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting180820200219-3Light Truck - Pick up- After Jan 1061462.5 | Corbiere and Sons Contracting180820200219-3Light Truck - Pick up- After Jan 1061462.5Inv#010 |  |  | WF1-Handfalling |  |  | 1 | 1462.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1808 | 20200219-3 | 53520104 | Clearing | 0 | Foreman | 95 | 24 | HR |  |  | 95 | 0 | 2280 | 296.4 | 2576.4 | 2020-02-19 | 1 | Inv#010 | 43906 | 87 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hand Falling from B017, and then down to B010 and A134; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43895 |  | 36 | 43897 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting180820200219-3Foreman242280 | Corbiere and Sons Contracting180820200219-3Foreman242280Inv#010 |  |  | WF1-Handfalling |  |  | 1 | 2280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1808 | 20200219-3 | 53520104 | Clearing | 0 | L.O.A. | 210 | 15 | DAY |  |  |  | 0 | 3150 | 409.5 | 3559.5 | 2020-02-19 | 1 | Inv#010 | 43906 | 87 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hand Falling from B017, and then down to B010 and A134; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43895 |  | 36 | 43897 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting180820200219-3L.O.A.153150 | Corbiere and Sons Contracting180820200219-3L.O.A.153150Inv#010 |  |  | WF1-Handfalling |  |  | 1 | 3150 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1808 | 20200219-3 | 53520104 | Clearing | 0 | Labourer - Specialized - After Jan 10 | 70 | 143 | HR |  |  | 70 | 0 | 10010 | 1301.3 | 11311.3 | 2020-02-19 | 1 | Inv#010 | 43906 | 87 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hand Falling from B017, and then down to B010 and A134; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43895 |  | 36 | 43897 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting180820200219-3Labourer - Specialized - After Jan 1014310010 | Corbiere and Sons Contracting180820200219-3Labourer - Specialized - After Jan 1014310010Inv#010 |  |  | WF1-Handfalling |  |  | 1 | 10010 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1847 | 20200220-17 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 4 | Dynamic | 95.24 | 0 |  |  | 507.92 | 66.0296 | 573.9496 | 2020-02-20 | 1 | Inv#010 | 43906 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grading Neys road up to the hills on the East and West Side | 6 | C236 - C243 | Neys | 0 | 43896 |  | 40 | 43897 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting184720200220-17Grader - Cat 12 to 14 or equal- After Jan 104507.92 | Corbiere and Sons Contracting184720200220-17Grader - Cat 12 to 14 or equal- After Jan 104507.92Inv#010 | [5 empty] | 1 | 507.92 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1847 | 20200220-17 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-02-20 | 1 | Inv#010 | 43906 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grading Neys road up to the hills on the East and West Side | 6 | C236 - C243 | Neys | 0 | 43896 |  | 40 | 43897 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting184720200220-17L.O.A.1210 | Corbiere and Sons Contracting184720200220-17L.O.A.1210Inv#010 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1847 | 20200220-17 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 4 | HR |  |  | 75 | 0 | 300 | 39 | 339 | 2020-02-20 | 1 | Inv#010 | 43906 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grading Neys road up to the hills on the East and West Side | 6 | C236 - C243 | Neys | 0 | 43896 |  | 40 | 43897 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting184720200220-17Operator - Principle - After Jan 104300 | Corbiere and Sons Contracting184720200220-17Operator - Principle - After Jan 104300Inv#010 | [5 empty] | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1833 | 20200220-3 | 53520104 | Clearing | 0 | Chainsaw and consumables- After Jan 10 | 60 | 6 | unit/man/day | 0 | 0 |  |  | 360 | 46.8 | 406.8 | 2020-02-20 | 1 | Inv#010 | 43906 | 87 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hand Falling finished at A134 and B010 and moved onto B011; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43896 |  | 36 | 43898 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting183320200220-3Chainsaw and consumables- After Jan 106360 | Corbiere and Sons Contracting183320200220-3Chainsaw and consumables- After Jan 106360Inv#010 |  |  | WF1-Handfalling |  |  | 1 | 360 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1833 | 20200220-3 | 53520104 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2020-02-20 | 1 | Inv#010 | 43906 | 87 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hand Falling finished at A134 and B010 and moved onto B011; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43896 |  | 36 | 43898 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting183320200220-3Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting183320200220-3Light Truck - Pick up- After Jan 103731.25Inv#010 |  |  | WF1-Handfalling |  |  | 1 | 731.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1833 | 20200220-3 | 53520104 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2020-02-20 | 1 | Inv#010 | 43906 | 87 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hand Falling finished at A134 and B010 and moved onto B011; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43896 |  | 36 | 43898 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting183320200220-3Foreman121140 | Corbiere and Sons Contracting183320200220-3Foreman121140Inv#010 |  |  | WF1-Handfalling |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1833 | 20200220-3 | 53520104 | Clearing | 0 | L.O.A. | 210 | 7 | DAY |  |  |  | 0 | 1470 | 191.1 | 1661.1 | 2020-02-20 | 1 | Inv#010 | 43906 | 87 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hand Falling finished at A134 and B010 and moved onto B011; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43896 |  | 36 | 43898 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting183320200220-3L.O.A.71470 | Corbiere and Sons Contracting183320200220-3L.O.A.71470Inv#010 |  |  | WF1-Handfalling |  |  | 1 | 1470 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1833 | 20200220-3 | 53520104 | Clearing | 0 | Labourer - Specialized - After Jan 10 | 70 | 66 | HR |  |  | 70 | 0 | 4620 | 600.6 | 5220.6 | 2020-02-20 | 1 | Inv#010 | 43906 | 87 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hand Falling finished at A134 and B010 and moved onto B011; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43896 |  | 36 | 43898 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting183320200220-3Labourer - Specialized - After Jan 10664620 | Corbiere and Sons Contracting183320200220-3Labourer - Specialized - After Jan 10664620Inv#010 |  |  | WF1-Handfalling |  |  | 1 | 4620 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1863 | 20200221-11 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 5 | Dynamic | 98.61 | 0 |  |  | 657.4 | 85.462 | 742.862 | 2020-02-21 | 1 | Inv#010 | 43906 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Clearing rail crossing at Ripple Lake; | 6 | C203 - C209 | Ripple Lake | 0 | 43896 |  | 41 | 43897 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting186320200221-11Dozer D6 or equal- After Jan 105657.4 | Corbiere and Sons Contracting186320200221-11Dozer D6 or equal- After Jan 105657.4Inv#010 | [5 empty] | 1 | 657.4 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1863 | 20200221-11 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-02-21 | 1 | Inv#010 | 43906 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Clearing rail crossing at Ripple Lake; | 6 | C203 - C209 | Ripple Lake | 0 | 43896 |  | 41 | 43897 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting186320200221-11L.O.A.1210 | Corbiere and Sons Contracting186320200221-11L.O.A.1210Inv#010 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1863 | 20200221-11 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 75 | 0 | 450 | 58.5 | 508.5 | 2020-02-21 | 1 | Inv#010 | 43906 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Clearing rail crossing at Ripple Lake; | 6 | C203 - C209 | Ripple Lake | 0 | 43896 |  | 41 | 43897 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting186320200221-11Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting186320200221-11Operator - Principle - After Jan 106450Inv#010 | [5 empty] | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1855 | 20200221-3 | 53520104 | Clearing | 0 | Chainsaw and consumables- After Jan 10 | 60 | 5 | unit/man/day | 0 | 0 |  |  | 300 | 39 | 339 | 2020-02-21 | 1 | Inv#010 | 43906 | 87 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hand Falling completed at A124 and B011 | 1 | A-128 to B-017 | Wolf Lake | 0 | 43896 |  | 36 | 43898 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting185520200221-3Chainsaw and consumables- After Jan 105300 | Corbiere and Sons Contracting185520200221-3Chainsaw and consumables- After Jan 105300Inv#010 |  |  | WF1-Handfalling |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1855 | 20200221-3 | 53520104 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2020-02-21 | 1 | Inv#010 | 43906 | 87 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hand Falling completed at A124 and B011 | 1 | A-128 to B-017 | Wolf Lake | 0 | 43896 |  | 36 | 43898 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting185520200221-3Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting185520200221-3Light Truck - Pick up- After Jan 103731.25Inv#010 |  |  | WF1-Handfalling |  |  | 1 | 731.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1855 | 20200221-3 | 53520104 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2020-02-21 | 1 | Inv#010 | 43906 | 87 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hand Falling completed at A124 and B011 | 1 | A-128 to B-017 | Wolf Lake | 0 | 43896 |  | 36 | 43898 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting185520200221-3Foreman121140 | Corbiere and Sons Contracting185520200221-3Foreman121140Inv#010 |  |  | WF1-Handfalling |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1855 | 20200221-3 | 53520104 | Clearing | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2020-02-21 | 1 | Inv#010 | 43906 | 87 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hand Falling completed at A124 and B011 | 1 | A-128 to B-017 | Wolf Lake | 0 | 43896 |  | 36 | 43898 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting185520200221-3L.O.A.61260 | Corbiere and Sons Contracting185520200221-3L.O.A.61260Inv#010 |  |  | WF1-Handfalling |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1855 | 20200221-3 | 53520104 | Clearing | 0 | Labourer - Specialized - After Jan 10 | 70 | 55 | HR |  |  | 70 | 0 | 3850 | 500.5 | 4350.5 | 2020-02-21 | 1 | Inv#010 | 43906 | 87 | 0 | 0 | Nathan Kyme | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hand Falling completed at A124 and B011 | 1 | A-128 to B-017 | Wolf Lake | 0 | 43896 |  | 36 | 43898 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting185520200221-3Labourer - Specialized - After Jan 10553850 | Corbiere and Sons Contracting185520200221-3Labourer - Specialized - After Jan 10553850Inv#010 |  |  | WF1-Handfalling |  |  | 1 | 3850 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1908 | 20200223-16 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 5 | Dynamic | 98.61 | 0 |  |  | 657.4 | 85.462 | 742.862 | 2020-02-23 | 1 | Inv#010 | 43906 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Plow Neys Road up to 241 | 6 |  | Neys Road | 0 | 43896 |  | 40 | 43898 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting190820200223-16Dozer D6 or equal- After Jan 105657.4 | Corbiere and Sons Contracting190820200223-16Dozer D6 or equal- After Jan 105657.4Inv#010 | [5 empty] | 1 | 657.4 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1908 | 20200223-16 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-02-23 | 1 | Inv#010 | 43906 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Plow Neys Road up to 241 | 6 |  | Neys Road | 0 | 43896 |  | 40 | 43898 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting190820200223-16Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting190820200223-16Light Truck - Pick up- After Jan 101243.75Inv#010 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1908 | 20200223-16 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-02-23 | 1 | Inv#010 | 43906 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Plow Neys Road up to 241 | 6 |  | Neys Road | 0 | 43896 |  | 40 | 43898 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting190820200223-16L.O.A.1210 | Corbiere and Sons Contracting190820200223-16L.O.A.1210Inv#010 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1908 | 20200223-16 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5 | HR |  |  | 75 | 0 | 375 | 48.75 | 423.75 | 2020-02-23 | 1 | Inv#010 | 43906 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Plow Neys Road up to 241 | 6 |  | Neys Road | 0 | 43896 |  | 40 | 43898 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting190820200223-16Operator - Principle - After Jan 105375 | Corbiere and Sons Contracting190820200223-16Operator - Principle - After Jan 105375Inv#010 | [5 empty] | 1 | 375 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1927 | 20200224-15 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 4 | Dynamic | 98.61 | 0 |  |  | 525.92 | 68.3696 | 594.2896 | 2020-02-24 | 1 | Inv#010 | 43906 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter maintenance along access roads for part of day; | 6 | C186 - C190 | Prairie River | 0 | 43897 |  | 41 | 43897 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting192720200224-15Dozer D6 or equal- After Jan 104525.92 | Corbiere and Sons Contracting192720200224-15Dozer D6 or equal- After Jan 104525.92Inv#010 | [5 empty] | 1 | 525.92 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1927 | 20200224-15 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-02-24 | 1 | Inv#010 | 43906 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter maintenance along access roads for part of day; | 6 | C186 - C190 | Prairie River | 0 | 43897 |  | 41 | 43897 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting192720200224-15Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting192720200224-15Light Truck - Pick up- After Jan 101243.75Inv#010 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1927 | 20200224-15 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-02-24 | 1 | Inv#010 | 43906 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter maintenance along access roads for part of day; | 6 | C186 - C190 | Prairie River | 0 | 43897 |  | 41 | 43897 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting192720200224-15L.O.A.1210 | Corbiere and Sons Contracting192720200224-15L.O.A.1210Inv#010 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1927 | 20200224-15 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 4 | HR |  |  | 75 | 0 | 300 | 39 | 339 | 2020-02-24 | 1 | Inv#010 | 43906 | 87 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter maintenance along access roads for part of day; | 6 | C186 - C190 | Prairie River | 0 | 43897 |  | 41 | 43897 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting192720200224-15Operator - Principle - After Jan 104300 | Corbiere and Sons Contracting192720200224-15Operator - Principle - After Jan 104300Inv#010 | [5 empty] | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1947 | 20200225-12 | 53510611 | Access | 0 | Dozer - D5 or equal- After Jan 10 | 80.93 | 5 | Dynamic | 60.7 |  |  |  | 404.65 | 52.6045 | 457.2545 | 2020-02-25 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | C248-C256 Operator plowed snow for blasting crew to be able to reach their magazine storage; Repairing Road after blast; | 6 | C257 - C267 | Little Red Sucker Creek | 0 | 43897 |  | 42 | 43914 | [5 empty] | Jarod Okemow | 06 | Corbiere and Sons Contracting194720200225-12Dozer - D5 or equal- After Jan 105404.65 | Corbiere and Sons Contracting194720200225-12Dozer - D5 or equal- After Jan 105404.65Inv#018 | [5 empty] | 1 | 404.65 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1947 | 20200225-12 | 53510611 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 12 | Dynamic | 110.22 | 0 |  |  | 1763.52 | 229.2576 | 1992.7776 | 2020-02-25 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | C248-C256 Operator plowed snow for blasting crew to be able to reach their magazine storage; Repairing Road after blast; | 6 | C257 - C267 | Little Red Sucker Creek | 0 | 43897 |  | 42 | 43914 | [5 empty] | Jarod Okemow | 06 | Corbiere and Sons Contracting194720200225-12Excavator - 36 ton- After Jan 10121763.52 | Corbiere and Sons Contracting194720200225-12Excavator - 36 ton- After Jan 10121763.52Inv#018 | [5 empty] | 1 | 1763.52 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1947 | 20200225-12 | 53510611 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 12 | HR | 9.16 | 0 |  |  | 146.52 | 19.0476 | 165.5676 | 2020-02-25 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | C248-C256 Operator plowed snow for blasting crew to be able to reach their magazine storage; Repairing Road after blast; | 6 | C257 - C267 | Little Red Sucker Creek | 0 | 43897 |  | 42 | 43914 | [5 empty] | Jarod Okemow | 06 | Corbiere and Sons Contracting194720200225-12Excavator Thumb - 30 - 50 ton- After Jan 1012146.52 | Corbiere and Sons Contracting194720200225-12Excavator Thumb - 30 - 50 ton- After Jan 1012146.52Inv#018 | [5 empty] | 1 | 146.52 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1947 | 20200225-12 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2020-02-25 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | C248-C256 Operator plowed snow for blasting crew to be able to reach their magazine storage; Repairing Road after blast; | 6 | C257 - C267 | Little Red Sucker Creek | 0 | 43897 |  | 42 | 43914 | [5 empty] | Jarod Okemow | 06 | Corbiere and Sons Contracting194720200225-12Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting194720200225-12Light Truck - Pick up- After Jan 103731.25Inv#018 | [5 empty] | 1 | 731.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1947 | 20200225-12 | 53510611 | Access | 0 | Foreman | 95 | 4 | HR |  |  | 95 | 0 | 380 | 49.4 | 429.4 | 2020-02-25 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | C248-C256 Operator plowed snow for blasting crew to be able to reach their magazine storage; Repairing Road after blast; | 6 | C257 - C267 | Little Red Sucker Creek | 0 | 43897 |  | 42 | 43914 | [5 empty] | Jarod Okemow | 06 | Corbiere and Sons Contracting194720200225-12Foreman4380 | Corbiere and Sons Contracting194720200225-12Foreman4380Inv#018 | [5 empty] | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1947 | 20200225-12 | 53510611 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2020-02-25 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | C248-C256 Operator plowed snow for blasting crew to be able to reach their magazine storage; Repairing Road after blast; | 6 | C257 - C267 | Little Red Sucker Creek | 0 | 43897 |  | 42 | 43914 | [5 empty] | Jarod Okemow | 06 | Corbiere and Sons Contracting194720200225-12L.O.A.3630 | Corbiere and Sons Contracting194720200225-12L.O.A.3630Inv#018 | [5 empty] | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 1947 | 20200225-12 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 17 | HR |  |  | 75 | 0 | 1275 | 165.75 | 1440.75 | 2020-02-25 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | C248-C256 Operator plowed snow for blasting crew to be able to reach their magazine storage; Repairing Road after blast; | 6 | C257 - C267 | Little Red Sucker Creek | 0 | 43897 |  | 42 | 43914 | [5 empty] | Jarod Okemow | 06 | Corbiere and Sons Contracting194720200225-12Operator - Principle - After Jan 10171275 | Corbiere and Sons Contracting194720200225-12Operator - Principle - After Jan 10171275Inv#018 | [5 empty] | 1 | 1275 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2580 | 20200226-16 | 53510611 | Access | 0 | Skidder | 171 | 3 | HR | 128.25 | 0 |  |  | 513 | 66.69 | 579.69 | 2020-02-26 | 1 | INV#027 | 43973 | 91 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixing Parts of Road on Neys; | 6 | C219 - C236 | Neys | 0 | 43964 |  | 40 | 43969 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting258020200226-16Skidder 3513 | Corbiere and Sons Contracting258020200226-16Skidder 3513INV#027 | [5 empty] | 1 | 513 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2580 | 20200226-16 | 53510611 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 6 | Dynamic | 110.22 | 0 |  |  | 881.76 | 114.6288 | 996.3888 | 2020-02-26 | 1 | INV#027 | 43973 | 91 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixing Parts of Road on Neys; | 6 | C219 - C236 | Neys | 0 | 43964 |  | 40 | 43969 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting258020200226-16Excavator - 36 ton- After Jan 106881.76 | Corbiere and Sons Contracting258020200226-16Excavator - 36 ton- After Jan 106881.76INV#027 | [5 empty] | 1 | 881.76 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2580 | 20200226-16 | 53510611 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 6 | HR | 9.16 | 0 |  |  | 73.26 | 9.5238 | 82.7838 | 2020-02-26 | 1 | INV#027 | 43973 | 91 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixing Parts of Road on Neys; | 6 | C219 - C236 | Neys | 0 | 43964 |  | 40 | 43969 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting258020200226-16Excavator Thumb - 30 - 50 ton- After Jan 10673.26 | Corbiere and Sons Contracting258020200226-16Excavator Thumb - 30 - 50 ton- After Jan 10673.26INV#027 | [5 empty] | 1 | 73.26 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2580 | 20200226-16 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-02-26 | 1 | INV#027 | 43973 | 91 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixing Parts of Road on Neys; | 6 | C219 - C236 | Neys | 0 | 43964 |  | 40 | 43969 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting258020200226-16Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting258020200226-16Light Truck - Pick up- After Jan 102487.5INV#027 | [5 empty] | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2580 | 20200226-16 | 53510611 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 3 | Dynamic | 91.79 | 0 |  |  | 367.17 | 47.7321 | 414.9021 | 2020-02-26 | 1 | INV#027 | 43973 | 91 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixing Parts of Road on Neys; | 6 | C219 - C236 | Neys | 0 | 43964 |  | 40 | 43969 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting258020200226-16Tractor Trailer - 60 Ton- After Jan 103367.17 | Corbiere and Sons Contracting258020200226-16Tractor Trailer - 60 Ton- After Jan 103367.17INV#027 | [5 empty] | 1 | 367.17 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2580 | 20200226-16 | 53510611 | Access | 0 | Foreman | 95 | 1 | HR |  |  | 95 | 0 | 95 | 12.35 | 107.35 | 2020-02-26 | 1 | INV#027 | 43973 | 91 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixing Parts of Road on Neys; | 6 | C219 - C236 | Neys | 0 | 43964 |  | 40 | 43969 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting258020200226-16Foreman195 | Corbiere and Sons Contracting258020200226-16Foreman195INV#027 | [5 empty] | 1 | 95 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2580 | 20200226-16 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-02-26 | 1 | INV#027 | 43973 | 91 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixing Parts of Road on Neys; | 6 | C219 - C236 | Neys | 0 | 43964 |  | 40 | 43969 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting258020200226-16L.O.A.1210 | Corbiere and Sons Contracting258020200226-16L.O.A.1210INV#027 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2580 | 20200226-16 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 10 | HR |  |  | 75 | 0 | 750 | 97.5 | 847.5 | 2020-02-26 | 1 | INV#027 | 43973 | 91 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixing Parts of Road on Neys; | 6 | C219 - C236 | Neys | 0 | 43964 |  | 40 | 43969 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting258020200226-16Operator - Principle - After Jan 1010750 | Corbiere and Sons Contracting258020200226-16Operator - Principle - After Jan 1010750INV#027 | [5 empty] | 1 | 750 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2580 | 20200226-16 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 3 | HR |  |  | 70 | 0 | 210 | 27.3 | 237.3 | 2020-02-26 | 1 | INV#027 | 43973 | 91 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixing Parts of Road on Neys; | 6 | C219 - C236 | Neys | 0 | 43964 |  | 40 | 43969 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting258020200226-16Driver - AZ - After Jan 103210 | Corbiere and Sons Contracting258020200226-16Driver - AZ - After Jan 103210INV#027 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2580 | 20200226-16 | 53510611 | Access | 0 | Labourer - General - After Jan 10 | 60 | 4 | HR |  |  | 60 | 0 | 240 | 31.2 | 271.2 | 2020-02-26 | 1 | INV#027 | 43973 | 91 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixing Parts of Road on Neys; | 6 | C219 - C236 | Neys | 0 | 43964 |  | 40 | 43969 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting258020200226-16Labourer - General - After Jan 104240 | Corbiere and Sons Contracting258020200226-16Labourer - General - After Jan 104240INV#027 | [5 empty] | 1 | 240 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2004 | 20200227-15 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 2 | Dynamic | 95.24 | 0 |  |  | 253.96 | 33.0148 | 286.9748 | 2020-02-27 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grading of Valard shop yard and laydown for bridges | 6 |  | Valard Shop | 0 | 43898 |  | 42 | 43912 | [5 empty] | Jarod Okemow | 06 | Corbiere and Sons Contracting200420200227-15Grader - Cat 12 to 14 or equal- After Jan 102253.96 | Corbiere and Sons Contracting200420200227-15Grader - Cat 12 to 14 or equal- After Jan 102253.96Inv#018 | [5 empty] | 1 | 253.96 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2004 | 20200227-15 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-02-27 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grading of Valard shop yard and laydown for bridges | 6 |  | Valard Shop | 0 | 43898 |  | 42 | 43912 | [5 empty] | Jarod Okemow | 06 | Corbiere and Sons Contracting200420200227-15L.O.A.1210 | Corbiere and Sons Contracting200420200227-15L.O.A.1210Inv#018 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2004 | 20200227-15 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 2 | HR |  |  | 75 | 0 | 150 | 19.5 | 169.5 | 2020-02-27 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grading of Valard shop yard and laydown for bridges | 6 |  | Valard Shop | 0 | 43898 |  | 42 | 43912 | [5 empty] | Jarod Okemow | 06 | Corbiere and Sons Contracting200420200227-15Operator - Principle - After Jan 102150 | Corbiere and Sons Contracting200420200227-15Operator - Principle - After Jan 102150Inv#018 | [5 empty] | 1 | 150 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2021 | 20200228-13 | 53510611 | Access | 0 | Sander Truck - Forestry- After Jan 10 | 86.38 | 5 | Dynamic | 64.79 | 0 |  |  | 431.9 | 56.147 | 488.047 | 2020-02-28 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Sanding of Valard's Yard | 6 |  | Valard Yard | 0 | 43898 |  | 40 | 43912 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting202120200228-13Sander Truck - Forestry- After Jan 105431.9 | Corbiere and Sons Contracting202120200228-13Sander Truck - Forestry- After Jan 105431.9Inv#018 | [5 empty] | 1 | 431.9 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2021 | 20200228-13 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-02-28 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Sanding of Valard's Yard | 6 |  | Valard Yard | 0 | 43898 |  | 40 | 43912 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting202120200228-13L.O.A.1210 | Corbiere and Sons Contracting202120200228-13L.O.A.1210Inv#018 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2021 | 20200228-13 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 5 | HR |  |  | 70 | 0 | 350 | 45.5 | 395.5 | 2020-02-28 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Sanding of Valard's Yard | 6 |  | Valard Yard | 0 | 43898 |  | 40 | 43912 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting202120200228-13Driver - AZ - After Jan 105350 | Corbiere and Sons Contracting202120200228-13Driver - AZ - After Jan 105350Inv#018 | [5 empty] | 1 | 350 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2033 | 20200229-11 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 5 | Dynamic | 95.24 | 0 |  |  | 634.9 | 82.537 | 717.437 | 2020-02-29 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grading and Sanding of Neys Road; | 6 | C219 - C236 | Neys | 0 | 43898 |  | 42 | 43912 | [5 empty] | Jarod Okemow | 06 | Corbiere and Sons Contracting203320200229-11Grader - Cat 12 to 14 or equal- After Jan 105634.9 | Corbiere and Sons Contracting203320200229-11Grader - Cat 12 to 14 or equal- After Jan 105634.9Inv#018 | [5 empty] | 1 | 634.9 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2033 | 20200229-11 | 53510611 | Access | 0 | Sander Truck - Forestry- After Jan 10 | 86.38 | 3 | Dynamic | 64.79 | 0 |  |  | 259.14 | 33.6882 | 292.8282 | 2020-02-29 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grading and Sanding of Neys Road; | 6 | C219 - C236 | Neys | 0 | 43898 |  | 42 | 43912 | [5 empty] | Jarod Okemow | 06 | Corbiere and Sons Contracting203320200229-11Sander Truck - Forestry- After Jan 103259.14 | Corbiere and Sons Contracting203320200229-11Sander Truck - Forestry- After Jan 103259.14Inv#018 | [5 empty] | 1 | 259.14 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2033 | 20200229-11 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-02-29 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grading and Sanding of Neys Road; | 6 | C219 - C236 | Neys | 0 | 43898 |  | 42 | 43912 | [5 empty] | Jarod Okemow | 06 | Corbiere and Sons Contracting203320200229-11Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting203320200229-11Light Truck - Pick up- After Jan 101243.75Inv#018 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2033 | 20200229-11 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-02-29 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grading and Sanding of Neys Road; | 6 | C219 - C236 | Neys | 0 | 43898 |  | 42 | 43912 | [5 empty] | Jarod Okemow | 06 | Corbiere and Sons Contracting203320200229-11L.O.A.1210 | Corbiere and Sons Contracting203320200229-11L.O.A.1210Inv#018 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2033 | 20200229-11 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5 | HR |  |  | 75 | 0 | 375 | 48.75 | 423.75 | 2020-02-29 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grading and Sanding of Neys Road; | 6 | C219 - C236 | Neys | 0 | 43898 |  | 42 | 43912 | [5 empty] | Jarod Okemow | 06 | Corbiere and Sons Contracting203320200229-11Operator - Principle - After Jan 105375 | Corbiere and Sons Contracting203320200229-11Operator - Principle - After Jan 105375Inv#018 | [5 empty] | 1 | 375 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2033 | 20200229-11 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 3 | HR |  |  | 70 | 0 | 210 | 27.3 | 237.3 | 2020-02-29 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grading and Sanding of Neys Road; | 6 | C219 - C236 | Neys | 0 | 43898 |  | 42 | 43912 | [5 empty] | Jarod Okemow | 06 | Corbiere and Sons Contracting203320200229-11Driver - AZ - After Jan 103210 | Corbiere and Sons Contracting203320200229-11Driver - AZ - After Jan 103210Inv#018 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2078 | 20200304-11 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 12 | Dynamic | 95.24 | 0 |  |  | 1523.76 | 198.0888 | 1721.8488 | 2020-03-04 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Removal of snow from roadways; | 6 | C129-C151 | Lake A | 0 | 43901 |  | 42 | 43913 | [5 empty] | Jarod Okemow | 06 | Corbiere and Sons Contracting207820200304-11Grader - Cat 12 to 14 or equal- After Jan 10121523.76 | Corbiere and Sons Contracting207820200304-11Grader - Cat 12 to 14 or equal- After Jan 10121523.76Inv#018 | [5 empty] | 1 | 1523.76 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2078 | 20200304-11 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-03-04 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Removal of snow from roadways; | 6 | C129-C151 | Lake A | 0 | 43901 |  | 42 | 43913 | [5 empty] | Jarod Okemow | 06 | Corbiere and Sons Contracting207820200304-11Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting207820200304-11Light Truck - Pick up- After Jan 101243.75Inv#018 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2078 | 20200304-11 | 53510611 | Access | 0 | Foreman | 95 | 2 | HR |  |  | 95 | 0 | 190 | 24.7 | 214.7 | 2020-03-04 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Removal of snow from roadways; | 6 | C129-C151 | Lake A | 0 | 43901 |  | 42 | 43913 | [5 empty] | Jarod Okemow | 06 | Corbiere and Sons Contracting207820200304-11Foreman2190 | Corbiere and Sons Contracting207820200304-11Foreman2190Inv#018 | [5 empty] | 1 | 190 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2078 | 20200304-11 | 53510611 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2020-03-04 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Removal of snow from roadways; | 6 | C129-C151 | Lake A | 0 | 43901 |  | 42 | 43913 | [5 empty] | Jarod Okemow | 06 | Corbiere and Sons Contracting207820200304-11L.O.A.3630 | Corbiere and Sons Contracting207820200304-11L.O.A.3630Inv#018 | [5 empty] | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2078 | 20200304-11 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 13 | HR |  |  | 75 | 0 | 975 | 126.75 | 1101.75 | 2020-03-04 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Removal of snow from roadways; | 6 | C129-C151 | Lake A | 0 | 43901 |  | 42 | 43913 | [5 empty] | Jarod Okemow | 06 | Corbiere and Sons Contracting207820200304-11Operator - Principle - After Jan 1013975 | Corbiere and Sons Contracting207820200304-11Operator - Principle - After Jan 1013975Inv#018 | [5 empty] | 1 | 975 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2080 | 20200304-13 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 3 | Dynamic | 98.61 | 0 |  |  | 394.44 | 51.2772 | 445.7172 | 2020-03-04 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Snow removal across access roads | 6 | C171-C185 | Prairie River | 0 | 43901 |  | 42 | 43913 | [5 empty] | Jarod Okemow | 06 | Corbiere and Sons Contracting208020200304-13Dozer D6 or equal- After Jan 103394.44 | Corbiere and Sons Contracting208020200304-13Dozer D6 or equal- After Jan 103394.44Inv#018 | [5 empty] | 1 | 394.44 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2080 | 20200304-13 | 53510611 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 2 | Dynamic | 110.22 | 0 |  |  | 293.92 | 38.2096 | 332.1296 | 2020-03-04 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Snow removal across access roads | 6 | C171-C185 | Prairie River | 0 | 43901 |  | 42 | 43913 | [5 empty] | Jarod Okemow | 06 | Corbiere and Sons Contracting208020200304-13Excavator - 36 ton- After Jan 102293.92 | Corbiere and Sons Contracting208020200304-13Excavator - 36 ton- After Jan 102293.92Inv#018 | [5 empty] | 1 | 293.92 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2080 | 20200304-13 | 53510611 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 2 | HR | 9.16 | 0 |  |  | 24.42 | 3.1746 | 27.5946 | 2020-03-04 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Snow removal across access roads | 6 | C171-C185 | Prairie River | 0 | 43901 |  | 42 | 43913 | [5 empty] | Jarod Okemow | 06 | Corbiere and Sons Contracting208020200304-13Excavator Thumb - 30 - 50 ton- After Jan 10224.42 | Corbiere and Sons Contracting208020200304-13Excavator Thumb - 30 - 50 ton- After Jan 10224.42Inv#018 | [5 empty] | 1 | 24.42 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2080 | 20200304-13 | 53510611 | Access | 0 | Foreman | 95 | 2 | HR |  |  | 95 | 0 | 190 | 24.7 | 214.7 | 2020-03-04 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Snow removal across access roads | 6 | C171-C185 | Prairie River | 0 | 43901 |  | 42 | 43913 | [5 empty] | Jarod Okemow | 06 | Corbiere and Sons Contracting208020200304-13Foreman2190 | Corbiere and Sons Contracting208020200304-13Foreman2190Inv#018 | [5 empty] | 1 | 190 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2080 | 20200304-13 | 53510611 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-03-04 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Snow removal across access roads | 6 | C171-C185 | Prairie River | 0 | 43901 |  | 42 | 43913 | [5 empty] | Jarod Okemow | 06 | Corbiere and Sons Contracting208020200304-13L.O.A.2420 | Corbiere and Sons Contracting208020200304-13L.O.A.2420Inv#018 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2080 | 20200304-13 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 75 | 0 | 450 | 58.5 | 508.5 | 2020-03-04 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Snow removal across access roads | 6 | C171-C185 | Prairie River | 0 | 43901 |  | 42 | 43913 | [5 empty] | Jarod Okemow | 06 | Corbiere and Sons Contracting208020200304-13Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting208020200304-13Operator - Principle - After Jan 106450Inv#018 | [5 empty] | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2086 | 20200304-19 | 53510611 | Access | 0 | Mechanics Truck | 55 | 3 | HR | 41.25 | 0 |  |  | 165 | 21.45 | 186.45 | 2020-03-04 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grading across many WF6 access roads with late notice, 3:30am start; | 6 |  | All Areas | 0 | 43901 |  | 40 | 43913 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting208620200304-19Mechanics Truck3165 | Corbiere and Sons Contracting208620200304-19Mechanics Truck3165Inv#018 | [5 empty] | 1 | 165 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2086 | 20200304-19 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 14 | Dynamic | 95.24 | 0 |  |  | 1777.72 | 231.1036 | 2008.8236 | 2020-03-04 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grading across many WF6 access roads with late notice, 3:30am start; | 6 |  | All Areas | 0 | 43901 |  | 40 | 43913 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting208620200304-19Grader - Cat 12 to 14 or equal- After Jan 10141777.72 | Corbiere and Sons Contracting208620200304-19Grader - Cat 12 to 14 or equal- After Jan 10141777.72Inv#018 | [5 empty] | 1 | 1777.72 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2086 | 20200304-19 | 53510611 | Access | 0 | Mechanic | 90 | 3 | HR |  |  | 90 | 0 | 270 | 35.1 | 305.1 | 2020-03-04 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grading across many WF6 access roads with late notice, 3:30am start; | 6 |  | All Areas | 0 | 43901 |  | 40 | 43913 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting208620200304-19Mechanic3270 | Corbiere and Sons Contracting208620200304-19Mechanic3270Inv#018 | [5 empty] | 1 | 270 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2086 | 20200304-19 | 53510611 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-03-04 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grading across many WF6 access roads with late notice, 3:30am start; | 6 |  | All Areas | 0 | 43901 |  | 40 | 43913 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting208620200304-19L.O.A.2420 | Corbiere and Sons Contracting208620200304-19L.O.A.2420Inv#018 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2086 | 20200304-19 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 14 | HR |  |  | 75 | 0 | 1050 | 136.5 | 1186.5 | 2020-03-04 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grading across many WF6 access roads with late notice, 3:30am start; | 6 |  | All Areas | 0 | 43901 |  | 40 | 43913 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting208620200304-19Operator - Principle - After Jan 10141050 | Corbiere and Sons Contracting208620200304-19Operator - Principle - After Jan 10141050Inv#018 | [5 empty] | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2073 | 20200304-6 | 53510111 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 6 | Dynamic | 95.24 | 0 |  |  | 761.88 | 99.0444 | 860.9244 | 2020-03-04 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grading of Fish Hatchery access roads | 1 |  | Fish Hatchery | 0 | 43901 |  | 36 | 43914 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting207320200304-6Grader - Cat 12 to 14 or equal- After Jan 106761.88 | Corbiere and Sons Contracting207320200304-6Grader - Cat 12 to 14 or equal- After Jan 106761.88Inv#018 | [5 empty] | 1 | 761.88 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2073 | 20200304-6 | 53510111 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-03-04 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grading of Fish Hatchery access roads | 1 |  | Fish Hatchery | 0 | 43901 |  | 36 | 43914 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting207320200304-6Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting207320200304-6Light Truck - Pick up- After Jan 101243.75Inv#018 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2073 | 20200304-6 | 53510111 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 75 | 0 | 450 | 58.5 | 508.5 | 2020-03-04 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grading of Fish Hatchery access roads | 1 |  | Fish Hatchery | 0 | 43901 |  | 36 | 43914 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting207320200304-6Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting207320200304-6Operator - Principle - After Jan 106450Inv#018 | [5 empty] | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2096 | 20200305-9 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 6 | Dynamic | 95.24 | 0 |  |  | 761.88 | 99.0444 | 860.9244 | 2020-03-05 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Removed snow on Hare Lake Rd. | 6 | C257-C267 | Hare Lake | 0 |  |  | 42 | 43914 | [5 empty] | Jarod Okemow | 06 | Corbiere and Sons Contracting209620200305-9Grader - Cat 12 to 14 or equal- After Jan 106761.88 | Corbiere and Sons Contracting209620200305-9Grader - Cat 12 to 14 or equal- After Jan 106761.88Inv#018 | [5 empty] | 1 | 761.88 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2096 | 20200305-9 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-03-05 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Removed snow on Hare Lake Rd. | 6 | C257-C267 | Hare Lake | 0 |  |  | 42 | 43914 | [5 empty] | Jarod Okemow | 06 | Corbiere and Sons Contracting209620200305-9L.O.A.1210 | Corbiere and Sons Contracting209620200305-9L.O.A.1210Inv#018 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2096 | 20200305-9 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 75 | 0 | 450 | 58.5 | 508.5 | 2020-03-05 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Removed snow on Hare Lake Rd. | 6 | C257-C267 | Hare Lake | 0 |  |  | 42 | 43914 | [5 empty] | Jarod Okemow | 06 | Corbiere and Sons Contracting209620200305-9Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting209620200305-9Operator - Principle - After Jan 106450Inv#018 | [5 empty] | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2100 | 20200306-3 | 53510311 | Access | 0 | Loader JD 524 to 624 or equal | 99 | 4 | HR | 74.25 | 0 |  |  | 396 | 51.48 | 447.48 | 2020-03-06 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Clearing snow for access into B119-B123 and into Jackfish Road; Crystal Flagging; Equipement being mobed in to begin work | 3 | B119-B123 | Jackfish Road | 0 | 43905 |  | 36 | 43914 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting210020200306-3Loader JD 524 to 624 or equal4396 | Corbiere and Sons Contracting210020200306-3Loader JD 524 to 624 or equal4396Inv#018 | [5 empty] | 1 | 396 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2100 | 20200306-3 | 53510311 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 5 | Dynamic | 110.22 | 0 |  |  | 734.8 | 95.524 | 830.324 | 2020-03-06 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Clearing snow for access into B119-B123 and into Jackfish Road; Crystal Flagging; Equipement being mobed in to begin work | 3 | B119-B123 | Jackfish Road | 0 | 43905 |  | 36 | 43914 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting210020200306-3Excavator - 36 ton- After Jan 105734.8 | Corbiere and Sons Contracting210020200306-3Excavator - 36 ton- After Jan 105734.8Inv#018 | [5 empty] | 1 | 734.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2100 | 20200306-3 | 53510311 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 5 | HR | 9.16 | 0 |  |  | 61.05 | 7.9365 | 68.9865 | 2020-03-06 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Clearing snow for access into B119-B123 and into Jackfish Road; Crystal Flagging; Equipement being mobed in to begin work | 3 | B119-B123 | Jackfish Road | 0 | 43905 |  | 36 | 43914 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting210020200306-3Excavator Thumb - 30 - 50 ton- After Jan 10561.05 | Corbiere and Sons Contracting210020200306-3Excavator Thumb - 30 - 50 ton- After Jan 10561.05Inv#018 | [5 empty] | 1 | 61.05 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2100 | 20200306-3 | 53510311 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-03-06 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Clearing snow for access into B119-B123 and into Jackfish Road; Crystal Flagging; Equipement being mobed in to begin work | 3 | B119-B123 | Jackfish Road | 0 | 43905 |  | 36 | 43914 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting210020200306-3L.O.A.1210 | Corbiere and Sons Contracting210020200306-3L.O.A.1210Inv#018 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2100 | 20200306-3 | 53510311 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2020-03-06 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Clearing snow for access into B119-B123 and into Jackfish Road; Crystal Flagging; Equipement being mobed in to begin work | 3 | B119-B123 | Jackfish Road | 0 | 43905 |  | 36 | 43914 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting210020200306-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting210020200306-3Operator - Principle - After Jan 1011825Inv#018 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2103 | 20200306-6 | 53510112 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 4 | Dynamic | 95.24 | 0 |  |  | 507.92 | 66.0296 | 573.9496 | 2020-03-06 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grading of access roads as per Valards Request | 1 | A-085 to A-117 | Windfarm | 0 | 43905 |  | 36 | 43914 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting210320200306-6Grader - Cat 12 to 14 or equal- After Jan 104507.92 | Corbiere and Sons Contracting210320200306-6Grader - Cat 12 to 14 or equal- After Jan 104507.92Inv#018 | [5 empty] | 1 | 507.92 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2103 | 20200306-6 | 53510112 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-03-06 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grading of access roads as per Valards Request | 1 | A-085 to A-117 | Windfarm | 0 | 43905 |  | 36 | 43914 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting210320200306-6Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting210320200306-6Light Truck - Pick up- After Jan 101243.75Inv#018 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2103 | 20200306-6 | 53510112 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 3 | Dynamic | 91.79 | 0 |  |  | 367.17 | 47.7321 | 414.9021 | 2020-03-06 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grading of access roads as per Valards Request | 1 | A-085 to A-117 | Windfarm | 0 | 43905 |  | 36 | 43914 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting210320200306-6Tractor Trailer - 60 Ton- After Jan 103367.17 | Corbiere and Sons Contracting210320200306-6Tractor Trailer - 60 Ton- After Jan 103367.17Inv#018 | [5 empty] | 1 | 367.17 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2103 | 20200306-6 | 53510112 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-03-06 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grading of access roads as per Valards Request | 1 | A-085 to A-117 | Windfarm | 0 | 43905 |  | 36 | 43914 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting210320200306-6L.O.A.2420 | Corbiere and Sons Contracting210320200306-6L.O.A.2420Inv#018 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2103 | 20200306-6 | 53510112 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5 | HR |  |  | 75 | 0 | 375 | 48.75 | 423.75 | 2020-03-06 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grading of access roads as per Valards Request | 1 | A-085 to A-117 | Windfarm | 0 | 43905 |  | 36 | 43914 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting210320200306-6Operator - Principle - After Jan 105375 | Corbiere and Sons Contracting210320200306-6Operator - Principle - After Jan 105375Inv#018 | [5 empty] | 1 | 375 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2103 | 20200306-6 | 53510112 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 3 | HR |  |  | 70 | 0 | 210 | 27.3 | 237.3 | 2020-03-06 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grading of access roads as per Valards Request | 1 | A-085 to A-117 | Windfarm | 0 | 43905 |  | 36 | 43914 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting210320200306-6Driver - AZ - After Jan 103210 | Corbiere and Sons Contracting210320200306-6Driver - AZ - After Jan 103210Inv#018 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2106 | 20200306-9 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 11 | Dynamic | 95.24 | 0 |  |  | 1396.78 | 181.5814 | 1578.3614 | 2020-03-06 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Maintenance of roads at Del Lake | 6 | C186-C195 | Del Lake | 0 | 43905 |  | 42 | 43914 | [5 empty] | Jarod Okemow | 06 | Corbiere and Sons Contracting210620200306-9Grader - Cat 12 to 14 or equal- After Jan 10111396.78 | Corbiere and Sons Contracting210620200306-9Grader - Cat 12 to 14 or equal- After Jan 10111396.78Inv#018 | [5 empty] | 1 | 1396.78 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2106 | 20200306-9 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-03-06 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Maintenance of roads at Del Lake | 6 | C186-C195 | Del Lake | 0 | 43905 |  | 42 | 43914 | [5 empty] | Jarod Okemow | 06 | Corbiere and Sons Contracting210620200306-9L.O.A.1210 | Corbiere and Sons Contracting210620200306-9L.O.A.1210Inv#018 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2106 | 20200306-9 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 |  | 825 | 107.25 | 932.25 | 2020-03-06 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Maintenance of roads at Del Lake | 6 | C186-C195 | Del Lake | 0 | 43905 |  | 42 | 43914 | [5 empty] | Jarod Okemow | 06 | Corbiere and Sons Contracting210620200306-9Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting210620200306-9Operator - Principle - After Jan 1011825Inv#018 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2112 | 20200307-3 | 53510311 | Access | 0 | Loader JD 524 to 624 or equal | 99 | 8.5 | HR | 74.25 | 0 |  |  | 841.5 | 109.395 | 950.895 | 2020-03-07 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Clearing access into B127-B133 | 3 | B124-B132 | Fire Hill Creek Rd. E | 0 | 43905 |  | 43 | 43914 | [5 empty] | Will Ouimet | 03 | Corbiere and Sons Contracting211220200307-3Loader JD 524 to 624 or equal8.5841.5 | Corbiere and Sons Contracting211220200307-3Loader JD 524 to 624 or equal8.5841.5Inv#018 | [5 empty] | 1 | 841.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2112 | 20200307-3 | 53510311 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-03-07 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Clearing access into B127-B133 | 3 | B124-B132 | Fire Hill Creek Rd. E | 0 | 43905 |  | 43 | 43914 | [5 empty] | Will Ouimet | 03 | Corbiere and Sons Contracting211220200307-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting211220200307-3Light Truck - Pick up- After Jan 101243.75Inv#018 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2112 | 20200307-3 | 53510311 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-03-07 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Clearing access into B127-B133 | 3 | B124-B132 | Fire Hill Creek Rd. E | 0 | 43905 |  | 43 | 43914 | [5 empty] | Will Ouimet | 03 | Corbiere and Sons Contracting211220200307-3L.O.A.1210 | Corbiere and Sons Contracting211220200307-3L.O.A.1210Inv#018 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2112 | 20200307-3 | 53510311 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2020-03-07 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Clearing access into B127-B133 | 3 | B124-B132 | Fire Hill Creek Rd. E | 0 | 43905 |  | 43 | 43914 | [5 empty] | Will Ouimet | 03 | Corbiere and Sons Contracting211220200307-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting211220200307-3Operator - Principle - After Jan 1011825Inv#018 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2114 | 20200307-5 | 53510112 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 6.5 | Dynamic | 95.24 | 0 |  |  | 825.37 | 107.2981 | 932.6681 | 2020-03-07 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Finish opening up roads into Greenwich and Harold Roads | 1 | A-085 to A-117 | Windfarm | 0 | 43905 |  | 36 | 43915 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting211420200307-5Grader - Cat 12 to 14 or equal- After Jan 106.5825.37 | Corbiere and Sons Contracting211420200307-5Grader - Cat 12 to 14 or equal- After Jan 106.5825.37Inv#018 | [5 empty] | 1 | 825.37 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2114 | 20200307-5 | 53510112 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-03-07 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Finish opening up roads into Greenwich and Harold Roads | 1 | A-085 to A-117 | Windfarm | 0 | 43905 |  | 36 | 43915 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting211420200307-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting211420200307-5Light Truck - Pick up- After Jan 101243.75Inv#018 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2114 | 20200307-5 | 53510112 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-03-07 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Finish opening up roads into Greenwich and Harold Roads | 1 | A-085 to A-117 | Windfarm | 0 | 43905 |  | 36 | 43915 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting211420200307-5L.O.A.1210 | Corbiere and Sons Contracting211420200307-5L.O.A.1210Inv#018 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2114 | 20200307-5 | 53510112 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 8.5 | HR |  |  | 75 | 0 | 637.5 | 82.875 | 720.375 | 2020-03-07 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Finish opening up roads into Greenwich and Harold Roads | 1 | A-085 to A-117 | Windfarm | 0 | 43905 |  | 36 | 43915 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting211420200307-5Operator - Principle - After Jan 108.5637.5 | Corbiere and Sons Contracting211420200307-5Operator - Principle - After Jan 108.5637.5Inv#018 | [5 empty] | 1 | 637.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2169 | 20200308-4 | 53510311 | Access | 0 | Loader JD 524 to 624 or equal | 99 | 4 | HR | 74.25 | 0 |  |  | 396 | 51.48 | 447.48 | 2020-03-08 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Clearing access | 3 | B124-B132 | Fire Hill Creek Road E | 0 | 43905 |  | 43 | 43914 | [5 empty] | Will Ouimet | 03 | Corbiere and Sons Contracting216920200308-4Loader JD 524 to 624 or equal4396 | Corbiere and Sons Contracting216920200308-4Loader JD 524 to 624 or equal4396Inv#018 | [5 empty] | 1 | 396 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2169 | 20200308-4 | 53510311 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-03-08 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Clearing access | 3 | B124-B132 | Fire Hill Creek Road E | 0 | 43905 |  | 43 | 43914 | [5 empty] | Will Ouimet | 03 | Corbiere and Sons Contracting216920200308-4L.O.A.1210 | Corbiere and Sons Contracting216920200308-4L.O.A.1210Inv#018 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2169 | 20200308-4 | 53510311 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5 | HR |  |  | 75 | 0 | 375 | 48.75 | 423.75 | 2020-03-08 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Clearing access | 3 | B124-B132 | Fire Hill Creek Road E | 0 | 43905 |  | 43 | 43914 | [5 empty] | Will Ouimet | 03 | Corbiere and Sons Contracting216920200308-4Operator - Principle - After Jan 105375 | Corbiere and Sons Contracting216920200308-4Operator - Principle - After Jan 105375Inv#018 | [5 empty] | 1 | 375 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2146 | 20200309-11 | 53510312 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 8 | Dynamic | 98.61 | 0 |  |  | 1051.84 | 136.7392 | 1188.5792 | 2020-03-09 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Mobilization and clearing access into WF3 | 3 | B11-B181 | Lachance Road | 0 | 43913 |  | 43 | 43916 | [5 empty] | Will Ouimet | 03 | Corbiere and Sons Contracting214620200309-11Dozer D6 or equal- After Jan 1081051.84 | Corbiere and Sons Contracting214620200309-11Dozer D6 or equal- After Jan 1081051.84Inv#018 | [5 empty] | 1 | 1051.84 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2146 | 20200309-11 | 53510312 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 6 | Dynamic | 95.24 | 0 |  |  | 761.88 | 99.0444 | 860.9244 | 2020-03-09 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Mobilization and clearing access into WF3 | 3 | B11-B181 | Lachance Road | 0 | 43913 |  | 43 | 43916 | [5 empty] | Will Ouimet | 03 | Corbiere and Sons Contracting214620200309-11Grader - Cat 12 to 14 or equal- After Jan 106761.88 | Corbiere and Sons Contracting214620200309-11Grader - Cat 12 to 14 or equal- After Jan 106761.88Inv#018 | [5 empty] | 1 | 761.88 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2146 | 20200309-11 | 53510312 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-03-09 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Mobilization and clearing access into WF3 | 3 | B11-B181 | Lachance Road | 0 | 43913 |  | 43 | 43916 | [5 empty] | Will Ouimet | 03 | Corbiere and Sons Contracting214620200309-11Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting214620200309-11Light Truck - Pick up- After Jan 102487.5Inv#018 | [5 empty] | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2146 | 20200309-11 | 53510312 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 8 | HR |  |  | 75 | 0 | 600 | 78 | 678 | 2020-03-09 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Mobilization and clearing access into WF3 | 3 | B11-B181 | Lachance Road | 0 | 43913 |  | 43 | 43916 | [5 empty] | Will Ouimet | 03 | Corbiere and Sons Contracting214620200309-11Operator - Principle - After Jan 108600 | Corbiere and Sons Contracting214620200309-11Operator - Principle - After Jan 108600Inv#018 | [5 empty] | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2146 | 20200309-11 | 53510312 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 75 | 0 | 450 | 58.5 | 508.5 | 2020-03-09 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Mobilization and clearing access into WF3 | 3 | B11-B181 | Lachance Road | 0 | 43913 |  | 43 | 43916 | [5 empty] | Will Ouimet | 03 | Corbiere and Sons Contracting214620200309-11Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting214620200309-11Operator - Principle - After Jan 106450Inv#018 | [5 empty] | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2120 | 20200309-3 | 53520104 | Clearing | 0 | Chainsaw and consumables- After Jan 10 | 60 | 2 | unit/man/day | 0 | 0 |  |  | 120 | 15.6 | 135.6 | 2020-03-09 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hand Falling at B009 | 1 | B009 | Fish Hatchery | 0 | 43905 |  | 36 | 43915 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting212020200309-3Chainsaw and consumables- After Jan 102120 | Corbiere and Sons Contracting212020200309-3Chainsaw and consumables- After Jan 102120Inv#018 |  |  | WF1-Handfalling |  |  | 1 | 120 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2120 | 20200309-3 | 53520104 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-03-09 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hand Falling at B009 | 1 | B009 | Fish Hatchery | 0 | 43905 |  | 36 | 43915 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting212020200309-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting212020200309-3Light Truck - Pick up- After Jan 101243.75Inv#018 |  |  | WF1-Handfalling |  |  | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2120 | 20200309-3 | 53520104 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-03-09 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hand Falling at B009 | 1 | B009 | Fish Hatchery | 0 | 43905 |  | 36 | 43915 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting212020200309-3L.O.A.2420 | Corbiere and Sons Contracting212020200309-3L.O.A.2420Inv#018 |  |  | WF1-Handfalling |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2120 | 20200309-3 | 53520104 | Clearing | 0 | Labourer - Specialized - After Jan 10 | 70 | 14 | HR |  |  | 70 | 0 | 980 | 127.4 | 1107.4 | 2020-03-09 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hand Falling at B009 | 1 | B009 | Fish Hatchery | 0 | 43905 |  | 36 | 43915 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting212020200309-3Labourer - Specialized - After Jan 1014980 | Corbiere and Sons Contracting212020200309-3Labourer - Specialized - After Jan 1014980Inv#018 |  |  | WF1-Handfalling |  |  | 1 | 980 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2122 | 20200309-5 | 53510312 | Access | 0 | Loader JD 524 to 624 or equal | 99 | 4 | HR | 74.25 | 0 |  |  | 396 | 51.48 | 447.48 | 2020-03-09 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Clearing snow from B126 and area | 3 | B124-B132 | Fire Hill Creek Road E | 0 | 43905 |  | 43 | 43914 | [5 empty] | Will Ouimet | 03 | Corbiere and Sons Contracting212220200309-5Loader JD 524 to 624 or equal4396 | Corbiere and Sons Contracting212220200309-5Loader JD 524 to 624 or equal4396Inv#018 | [5 empty] | 1 | 396 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2122 | 20200309-5 | 53510312 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 2 | Dynamic | 103.84 | 0 |  |  | 276.9 | 35.997 | 312.897 | 2020-03-09 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Clearing snow from B126 and area | 3 | B124-B132 | Fire Hill Creek Road E | 0 | 43905 |  | 43 | 43914 | [5 empty] | Will Ouimet | 03 | Corbiere and Sons Contracting212220200309-5Excavator - 30 ton- After Jan 102276.9 | Corbiere and Sons Contracting212220200309-5Excavator - 30 ton- After Jan 102276.9Inv#018 | [5 empty] | 1 | 276.9 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2122 | 20200309-5 | 53510312 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-03-09 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Clearing snow from B126 and area | 3 | B124-B132 | Fire Hill Creek Road E | 0 | 43905 |  | 43 | 43914 | [5 empty] | Will Ouimet | 03 | Corbiere and Sons Contracting212220200309-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting212220200309-5Light Truck - Pick up- After Jan 101243.75Inv#018 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2122 | 20200309-5 | 53510312 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 7.5 | HR |  |  | 75 | 0 | 562.5 | 73.125 | 635.625 | 2020-03-09 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Clearing snow from B126 and area | 3 | B124-B132 | Fire Hill Creek Road E | 0 | 43905 |  | 43 | 43914 | [5 empty] | Will Ouimet | 03 | Corbiere and Sons Contracting212220200309-5Operator - Principle - After Jan 107.5562.5 | Corbiere and Sons Contracting212220200309-5Operator - Principle - After Jan 107.5562.5Inv#018 | [5 empty] | 1 | 562.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2206 | 20200310-9 | 53510312 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 3 | Dynamic | 95.24 | 0 |  |  | 380.94 | 49.5222 | 430.4622 | 2020-03-10 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Mobilization into Lachance Road; 2 Pieces of equipment on SB due to trapper. Opening up of accesses; | 3 | B161-B181 | Lachance Road | 0 | 43906 |  | 43 | 43917 | [5 empty] | Will Ouimet | 03 | Corbiere and Sons Contracting220620200310-9Grader - Cat 12 to 14 or equal- After Jan 103380.94 | Corbiere and Sons Contracting220620200310-9Grader - Cat 12 to 14 or equal- After Jan 103380.94Inv#018 | [5 empty] | 1 | 380.94 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2206 | 20200310-9 | 53510312 | Access | 0 | Sander Truck - Forestry- After Jan 10 | 86.38 | 4 | Dynamic | 64.79 | 0 |  |  | 345.52 | 44.9176 | 390.4376 | 2020-03-10 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Mobilization into Lachance Road; 2 Pieces of equipment on SB due to trapper. Opening up of accesses; | 3 | B161-B181 | Lachance Road | 0 | 43906 |  | 43 | 43917 | [5 empty] | Will Ouimet | 03 | Corbiere and Sons Contracting220620200310-9Sander Truck - Forestry- After Jan 104345.52 | Corbiere and Sons Contracting220620200310-9Sander Truck - Forestry- After Jan 104345.52Inv#018 | [5 empty] | 1 | 345.52 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2206 | 20200310-9 | 53510312 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2020-03-10 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Mobilization into Lachance Road; 2 Pieces of equipment on SB due to trapper. Opening up of accesses; | 3 | B161-B181 | Lachance Road | 0 | 43906 |  | 43 | 43917 | [5 empty] | Will Ouimet | 03 | Corbiere and Sons Contracting220620200310-9Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting220620200310-9Light Truck - Pick up- After Jan 103731.25Inv#018 | [5 empty] | 1 | 731.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2206 | 20200310-9 | 53510312 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-03-10 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Mobilization into Lachance Road; 2 Pieces of equipment on SB due to trapper. Opening up of accesses; | 3 | B161-B181 | Lachance Road | 0 | 43906 |  | 43 | 43917 | [5 empty] | Will Ouimet | 03 | Corbiere and Sons Contracting220620200310-9L.O.A.1210 | Corbiere and Sons Contracting220620200310-9L.O.A.1210Inv#018 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2206 | 20200310-9 | 53510312 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 75 | 0 | 450 | 58.5 | 508.5 | 2020-03-10 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Mobilization into Lachance Road; 2 Pieces of equipment on SB due to trapper. Opening up of accesses; | 3 | B161-B181 | Lachance Road | 0 | 43906 |  | 43 | 43917 | [5 empty] | Will Ouimet | 03 | Corbiere and Sons Contracting220620200310-9Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting220620200310-9Operator - Principle - After Jan 106450Inv#018 | [5 empty] | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2206 | 20200310-9 | 53510312 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 4 | HR |  |  | 70 | 0 | 280 | 36.4 | 316.4 | 2020-03-10 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Mobilization into Lachance Road; 2 Pieces of equipment on SB due to trapper. Opening up of accesses; | 3 | B161-B181 | Lachance Road | 0 | 43906 |  | 43 | 43917 | [5 empty] | Will Ouimet | 03 | Corbiere and Sons Contracting220620200310-9Driver - AZ - After Jan 104280 | Corbiere and Sons Contracting220620200310-9Driver - AZ - After Jan 104280Inv#018 | [5 empty] | 1 | 280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2131 | 20200313-4 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2020-03-13 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Snow removal and maintenance of access roads performed both day and night, labourers escorting the graders and doing traffic control | 6 | All Areas | WF6 | 0 | 43913 |  | 41 | 43922 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting213120200313-4Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting213120200313-4Dozer D6 or equal- After Jan 10111446.28Inv#018 | [5 empty] | 1 | 1446.28 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2131 | 20200313-4 | 53510611 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10 | Dynamic | 110.22 | 0 |  |  | 1469.6 | 191.048 | 1660.648 | 2020-03-13 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Snow removal and maintenance of access roads performed both day and night, labourers escorting the graders and doing traffic control | 6 | All Areas | WF6 | 0 | 43913 |  | 41 | 43922 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting213120200313-4Excavator - 36 ton- After Jan 10101469.6 | Corbiere and Sons Contracting213120200313-4Excavator - 36 ton- After Jan 10101469.6Inv#018 | [5 empty] | 1 | 1469.6 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2131 | 20200313-4 | 53510611 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 9.16 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2020-03-13 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Snow removal and maintenance of access roads performed both day and night, labourers escorting the graders and doing traffic control | 6 | All Areas | WF6 | 0 | 43913 |  | 41 | 43922 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting213120200313-4Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting213120200313-4Excavator Thumb - 30 - 50 ton- After Jan 1010122.1Inv#018 | [5 empty] | 1 | 122.1 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2131 | 20200313-4 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 42 | Dynamic | 95.24 | 0 |  |  | 5333.16 | 693.3108 | 6026.4708 | 2020-03-13 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Snow removal and maintenance of access roads performed both day and night, labourers escorting the graders and doing traffic control | 6 | All Areas | WF6 | 0 | 43913 |  | 41 | 43922 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting213120200313-4Grader - Cat 12 to 14 or equal- After Jan 10425333.16 | Corbiere and Sons Contracting213120200313-4Grader - Cat 12 to 14 or equal- After Jan 10425333.16Inv#018 | [5 empty] | 1 | 5333.16 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2131 | 20200313-4 | 53510611 | Access | 0 | Snow Plow- After Jan 10 | 95 | 10 | Dynamic | 71.25 | 0 |  |  | 950 | 123.5 | 1073.5 | 2020-03-13 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Snow removal and maintenance of access roads performed both day and night, labourers escorting the graders and doing traffic control | 6 | All Areas | WF6 | 0 | 43913 |  | 41 | 43922 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting213120200313-4Snow Plow- After Jan 1010950 | Corbiere and Sons Contracting213120200313-4Snow Plow- After Jan 1010950Inv#018 | [5 empty] | 1 | 950 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2131 | 20200313-4 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 5 | DAY | 182.81 | 0 |  |  | 1218.75 | 158.4375 | 1377.1875 | 2020-03-13 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Snow removal and maintenance of access roads performed both day and night, labourers escorting the graders and doing traffic control | 6 | All Areas | WF6 | 0 | 43913 |  | 41 | 43922 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting213120200313-4Light Truck - Pick up- After Jan 1051218.75 | Corbiere and Sons Contracting213120200313-4Light Truck - Pick up- After Jan 1051218.75Inv#018 | [5 empty] | 1 | 1218.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2131 | 20200313-4 | 53510611 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2020-03-13 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Snow removal and maintenance of access roads performed both day and night, labourers escorting the graders and doing traffic control | 6 | All Areas | WF6 | 0 | 43913 |  | 41 | 43922 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting213120200313-4Foreman121140 | Corbiere and Sons Contracting213120200313-4Foreman121140Inv#018 | [5 empty] | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2131 | 20200313-4 | 53510611 | Access | 0 | L.O.A. | 210 | 10 | DAY |  |  |  | 0 | 2100 | 273 | 2373 | 2020-03-13 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Snow removal and maintenance of access roads performed both day and night, labourers escorting the graders and doing traffic control | 6 | All Areas | WF6 | 0 | 43913 |  | 41 | 43922 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting213120200313-4L.O.A.102100 | Corbiere and Sons Contracting213120200313-4L.O.A.102100Inv#018 | [5 empty] | 1 | 2100 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2131 | 20200313-4 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 83 | HR |  |  | 75 | 0 | 6225 | 809.25 | 7034.25 | 2020-03-13 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Snow removal and maintenance of access roads performed both day and night, labourers escorting the graders and doing traffic control | 6 | All Areas | WF6 | 0 | 43913 |  | 41 | 43922 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting213120200313-4Operator - Principle - After Jan 10836225 | Corbiere and Sons Contracting213120200313-4Operator - Principle - After Jan 10836225Inv#018 | [5 empty] | 1 | 6225 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2131 | 20200313-4 | 53510611 | Access | 0 | Labourer - General - After Jan 10 | 60 | 24 | HR |  |  | 60 | 0 | 1440 | 187.2 | 1627.2 | 2020-03-13 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Snow removal and maintenance of access roads performed both day and night, labourers escorting the graders and doing traffic control | 6 | All Areas | WF6 | 0 | 43913 |  | 41 | 43922 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting213120200313-4Labourer - General - After Jan 10241440 | Corbiere and Sons Contracting213120200313-4Labourer - General - After Jan 10241440Inv#018 | [5 empty] | 1 | 1440 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2135 | 20200313-8 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10 | Dynamic | 98.61 | 0 |  |  | 1314.8 | 170.924 | 1485.724 | 2020-03-13 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Snow Removal across various areas of Work Front 6 | 6 | Various Areas | WF6 | 0 | 43913 |  | 41 | 43922 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting213520200313-8Dozer D6 or equal- After Jan 10101314.8 | Corbiere and Sons Contracting213520200313-8Dozer D6 or equal- After Jan 10101314.8Inv#018 | [5 empty] | 1 | 1314.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2135 | 20200313-8 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 14 | Dynamic | 95.24 | 0 |  |  | 1777.72 | 231.1036 | 2008.8236 | 2020-03-13 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Snow Removal across various areas of Work Front 6 | 6 | Various Areas | WF6 | 0 | 43913 |  | 41 | 43922 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting213520200313-8Grader - Cat 12 to 14 or equal- After Jan 10141777.72 | Corbiere and Sons Contracting213520200313-8Grader - Cat 12 to 14 or equal- After Jan 10141777.72Inv#018 | [5 empty] | 1 | 1777.72 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2135 | 20200313-8 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-03-13 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Snow Removal across various areas of Work Front 6 | 6 | Various Areas | WF6 | 0 | 43913 |  | 41 | 43922 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting213520200313-8Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting213520200313-8Light Truck - Pick up- After Jan 101243.75Inv#018 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2135 | 20200313-8 | 53510611 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 3 | Dynamic | 91.79 | 0 |  |  | 367.17 | 47.7321 | 414.9021 | 2020-03-13 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Snow Removal across various areas of Work Front 6 | 6 | Various Areas | WF6 | 0 | 43913 |  | 41 | 43922 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting213520200313-8Tractor Trailer - 60 Ton- After Jan 103367.17 | Corbiere and Sons Contracting213520200313-8Tractor Trailer - 60 Ton- After Jan 103367.17Inv#018 | [5 empty] | 1 | 367.17 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2135 | 20200313-8 | 53510611 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-03-13 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Snow Removal across various areas of Work Front 6 | 6 | Various Areas | WF6 | 0 | 43913 |  | 41 | 43922 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting213520200313-8L.O.A.2420 | Corbiere and Sons Contracting213520200313-8L.O.A.2420Inv#018 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2135 | 20200313-8 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 24 | HR |  |  | 75 | 0 | 1800 | 234 | 2034 | 2020-03-13 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Snow Removal across various areas of Work Front 6 | 6 | Various Areas | WF6 | 0 | 43913 |  | 41 | 43922 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting213520200313-8Operator - Principle - After Jan 10241800 | Corbiere and Sons Contracting213520200313-8Operator - Principle - After Jan 10241800Inv#018 | [5 empty] | 1 | 1800 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2135 | 20200313-8 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 3 | HR |  |  | 70 | 0 | 210 | 27.3 | 237.3 | 2020-03-13 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Snow Removal across various areas of Work Front 6 | 6 | Various Areas | WF6 | 0 | 43913 |  | 41 | 43922 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting213520200313-8Driver - AZ - After Jan 103210 | Corbiere and Sons Contracting213520200313-8Driver - AZ - After Jan 103210Inv#018 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2201 | 20200314-3 | 53510312 | Access | 0 | Loader JD 524 to 624 or equal | 99 | 6 | HR | 74.25 | 0 |  |  | 594 | 77.22 | 671.22 | 2020-03-14 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Maintenance of various access entrances in WF3 B100-B104, B110-B115, B116-B117 | 3 |  |  | 0 | 43913 |  | 43 | 43915 | [5 empty] | Will Ouimet | 03 | Corbiere and Sons Contracting220120200314-3Loader JD 524 to 624 or equal6594 | Corbiere and Sons Contracting220120200314-3Loader JD 524 to 624 or equal6594Inv#018 | [5 empty] | 1 | 594 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2201 | 20200314-3 | 53510312 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-03-14 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Maintenance of various access entrances in WF3 B100-B104, B110-B115, B116-B117 | 3 |  |  | 0 | 43913 |  | 43 | 43915 | [5 empty] | Will Ouimet | 03 | Corbiere and Sons Contracting220120200314-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting220120200314-3Light Truck - Pick up- After Jan 101243.75Inv#018 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2201 | 20200314-3 | 53510312 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-03-14 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Maintenance of various access entrances in WF3 B100-B104, B110-B115, B116-B117 | 3 |  |  | 0 | 43913 |  | 43 | 43915 | [5 empty] | Will Ouimet | 03 | Corbiere and Sons Contracting220120200314-3L.O.A.1210 | Corbiere and Sons Contracting220120200314-3L.O.A.1210Inv#018 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2201 | 20200314-3 | 53510312 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 7 | HR |  |  | 75 | 0 | 525 | 68.25 | 593.25 | 2020-03-14 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Maintenance of various access entrances in WF3 B100-B104, B110-B115, B116-B117 | 3 |  |  | 0 | 43913 |  | 43 | 43915 | [5 empty] | Will Ouimet | 03 | Corbiere and Sons Contracting220120200314-3Operator - Principle - After Jan 107525 | Corbiere and Sons Contracting220120200314-3Operator - Principle - After Jan 107525Inv#018 | [5 empty] | 1 | 525 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2203 | 20200314-5 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2020-03-14 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Snow removal performed across Lake A and Prairie River overnight | 6 | C129-C151 | Lake A | 0 | 43913 |  | 42 | 43914 | [5 empty] | Jarod Okemow | 06 | Corbiere and Sons Contracting220320200314-5Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting220320200314-5Dozer D6 or equal- After Jan 10111446.28Inv#018 | [5 empty] | 1 | 1446.28 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2203 | 20200314-5 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-03-14 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Snow removal performed across Lake A and Prairie River overnight | 6 | C129-C151 | Lake A | 0 | 43913 |  | 42 | 43914 | [5 empty] | Jarod Okemow | 06 | Corbiere and Sons Contracting220320200314-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting220320200314-5Light Truck - Pick up- After Jan 101243.75Inv#018 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2203 | 20200314-5 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-03-14 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Snow removal performed across Lake A and Prairie River overnight | 6 | C129-C151 | Lake A | 0 | 43913 |  | 42 | 43914 | [5 empty] | Jarod Okemow | 06 | Corbiere and Sons Contracting220320200314-5L.O.A.1210 | Corbiere and Sons Contracting220320200314-5L.O.A.1210Inv#018 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2203 | 20200314-5 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2020-03-14 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Snow removal performed across Lake A and Prairie River overnight | 6 | C129-C151 | Lake A | 0 | 43913 |  | 42 | 43914 | [5 empty] | Jarod Okemow | 06 | Corbiere and Sons Contracting220320200314-5Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting220320200314-5Operator - Principle - After Jan 1012900Inv#018 | [5 empty] | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2140 | 20200315-3 | 53510311 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 5 | Dynamic | 103.84 | 0 |  |  | 692.25 | 89.9925 | 782.2425 | 2020-03-15 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Clearing snow and floating of EX; | 3 | All Areas |  | 0 | 43913 |  | 43 | 43916 | [5 empty] | Will Ouimet | 03 | Corbiere and Sons Contracting214020200315-3Excavator - 30 ton- After Jan 105692.25 | Corbiere and Sons Contracting214020200315-3Excavator - 30 ton- After Jan 105692.25Inv#018 | [5 empty] | 1 | 692.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2140 | 20200315-3 | 53510311 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-03-15 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Clearing snow and floating of EX; | 3 | All Areas |  | 0 | 43913 |  | 43 | 43916 | [5 empty] | Will Ouimet | 03 | Corbiere and Sons Contracting214020200315-3L.O.A.1210 | Corbiere and Sons Contracting214020200315-3L.O.A.1210Inv#018 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2140 | 20200315-3 | 53510311 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 75 | 0 | 450 | 58.5 | 508.5 | 2020-03-15 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Clearing snow and floating of EX; | 3 | All Areas |  | 0 | 43913 |  | 43 | 43916 | [5 empty] | Will Ouimet | 03 | Corbiere and Sons Contracting214020200315-3Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting214020200315-3Operator - Principle - After Jan 106450Inv#018 | [5 empty] | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2143 | 20200315-6 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2020-03-15 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Snow Removal across all access roads on Lake A and Prairie Road | 6 | C129-C151 | Lake A | 0 | 43913 |  | 42 | 43915 | [5 empty] | Jarod Okemow | 06 | Corbiere and Sons Contracting214320200315-6Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting214320200315-6Dozer D6 or equal- After Jan 10111446.28Inv#018 | [5 empty] | 1 | 1446.28 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2143 | 20200315-6 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 11 | Dynamic | 95.24 | 0 |  |  | 1396.78 | 181.5814 | 1578.3614 | 2020-03-15 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Snow Removal across all access roads on Lake A and Prairie Road | 6 | C129-C151 | Lake A | 0 | 43913 |  | 42 | 43915 | [5 empty] | Jarod Okemow | 06 | Corbiere and Sons Contracting214320200315-6Grader - Cat 12 to 14 or equal- After Jan 10111396.78 | Corbiere and Sons Contracting214320200315-6Grader - Cat 12 to 14 or equal- After Jan 10111396.78Inv#018 | [5 empty] | 1 | 1396.78 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2143 | 20200315-6 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-03-15 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Snow Removal across all access roads on Lake A and Prairie Road | 6 | C129-C151 | Lake A | 0 | 43913 |  | 42 | 43915 | [5 empty] | Jarod Okemow | 06 | Corbiere and Sons Contracting214320200315-6Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting214320200315-6Light Truck - Pick up- After Jan 101243.75Inv#018 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2143 | 20200315-6 | 53510611 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-03-15 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Snow Removal across all access roads on Lake A and Prairie Road | 6 | C129-C151 | Lake A | 0 | 43913 |  | 42 | 43915 | [5 empty] | Jarod Okemow | 06 | Corbiere and Sons Contracting214320200315-6L.O.A.2420 | Corbiere and Sons Contracting214320200315-6L.O.A.2420Inv#018 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2143 | 20200315-6 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 24 | HR |  |  | 75 | 0 | 1800 | 234 | 2034 | 2020-03-15 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Snow Removal across all access roads on Lake A and Prairie Road | 6 | C129-C151 | Lake A | 0 | 43913 |  | 42 | 43915 | [5 empty] | Jarod Okemow | 06 | Corbiere and Sons Contracting214320200315-6Operator - Principle - After Jan 10241800 | Corbiere and Sons Contracting214320200315-6Operator - Principle - After Jan 10241800Inv#018 | [5 empty] | 1 | 1800 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2536 | 20200316-10 | 53510611 | Access | 0 | Dozer D8 or equal- After Jan 10 | 217.5 | 6 | Dynamic | 163.13 | 0 |  |  | 1305 | 169.65 | 1474.65 | 2020-03-16 | 1 | INV#027 | 43973 | 91 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader clearing snow across Neys Road and Hare Lake Road; Dozer Clearing snow across Peninsula Road | 6 |  |  | 0 | 43959 |  | 42 | 43965 | [5 empty] | Jarod Okemow | 06 | Corbiere and Sons Contracting253620200316-10Dozer D8 or equal- After Jan 1061305 | Corbiere and Sons Contracting253620200316-10Dozer D8 or equal- After Jan 1061305INV#027 | [5 empty] | 1 | 1305 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2536 | 20200316-10 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 8 | Dynamic | 95.24 | 0 |  |  | 1015.84 | 132.0592 | 1147.8992 | 2020-03-16 | 1 | INV#027 | 43973 | 91 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader clearing snow across Neys Road and Hare Lake Road; Dozer Clearing snow across Peninsula Road | 6 |  |  | 0 | 43959 |  | 42 | 43965 | [5 empty] | Jarod Okemow | 06 | Corbiere and Sons Contracting253620200316-10Grader - Cat 12 to 14 or equal- After Jan 1081015.84 | Corbiere and Sons Contracting253620200316-10Grader - Cat 12 to 14 or equal- After Jan 1081015.84INV#027 | [5 empty] | 1 | 1015.84 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2536 | 20200316-10 | 53510611 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-03-16 | 1 | INV#027 | 43973 | 91 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader clearing snow across Neys Road and Hare Lake Road; Dozer Clearing snow across Peninsula Road | 6 |  |  | 0 | 43959 |  | 42 | 43965 | [5 empty] | Jarod Okemow | 06 | Corbiere and Sons Contracting253620200316-10L.O.A.2420 | Corbiere and Sons Contracting253620200316-10L.O.A.2420INV#027 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2536 | 20200316-10 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 14 | HR |  |  | 75 | 0 | 1050 | 136.5 | 1186.5 | 2020-03-16 | 1 | INV#027 | 43973 | 91 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader clearing snow across Neys Road and Hare Lake Road; Dozer Clearing snow across Peninsula Road | 6 |  |  | 0 | 43959 |  | 42 | 43965 | [5 empty] | Jarod Okemow | 06 | Corbiere and Sons Contracting253620200316-10Operator - Principle - After Jan 10141050 | Corbiere and Sons Contracting253620200316-10Operator - Principle - After Jan 10141050INV#027 | [5 empty] | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2149 | 20200316-3 | 53510212 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 2.5 | Dynamic | 95.24 | 0 |  |  | 317.45 | 41.2685 | 358.7185 | 2020-03-16 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grading access roads on Black Sturgeon | 2 | B018 - B029 | Black Sturgeon | 0 | 43913 |  | 43 | 43916 | [5 empty] | Will Ouimet | 02 | Corbiere and Sons Contracting214920200316-3Grader - Cat 12 to 14 or equal- After Jan 102.5317.45 | Corbiere and Sons Contracting214920200316-3Grader - Cat 12 to 14 or equal- After Jan 102.5317.45Inv#018 | [5 empty] | 1 | 317.45 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2149 | 20200316-3 | 53510212 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-03-16 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grading access roads on Black Sturgeon | 2 | B018 - B029 | Black Sturgeon | 0 | 43913 |  | 43 | 43916 | [5 empty] | Will Ouimet | 02 | Corbiere and Sons Contracting214920200316-3L.O.A.1210 | Corbiere and Sons Contracting214920200316-3L.O.A.1210Inv#018 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2149 | 20200316-3 | 53510212 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 3 | HR |  |  | 75 | 0 | 225 | 29.25 | 254.25 | 2020-03-16 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grading access roads on Black Sturgeon | 2 | B018 - B029 | Black Sturgeon | 0 | 43913 |  | 43 | 43916 | [5 empty] | Will Ouimet | 02 | Corbiere and Sons Contracting214920200316-3Operator - Principle - After Jan 103225 | Corbiere and Sons Contracting214920200316-3Operator - Principle - After Jan 103225Inv#018 | [5 empty] | 1 | 225 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2153 | 20200316-7 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 30.5 | Dynamic | 95.24 | 0 |  |  | 3872.89 | 503.4757 | 4376.3657 | 2020-03-16 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Snow Removal on Prairie Rd., Del Lake, Lake A, Middleton Road both during the day and overnight | 6 | Multiple Areas | WF6 | 0 | 43913 |  | 42 | 43915 | [5 empty] | Jarod Okemow | 06 | Corbiere and Sons Contracting215320200316-7Grader - Cat 12 to 14 or equal- After Jan 1030.53872.89 | Corbiere and Sons Contracting215320200316-7Grader - Cat 12 to 14 or equal- After Jan 1030.53872.89Inv#018 | [5 empty] | 1 | 3872.89 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2153 | 20200316-7 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-03-16 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Snow Removal on Prairie Rd., Del Lake, Lake A, Middleton Road both during the day and overnight | 6 | Multiple Areas | WF6 | 0 | 43913 |  | 42 | 43915 | [5 empty] | Jarod Okemow | 06 | Corbiere and Sons Contracting215320200316-7Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting215320200316-7Light Truck - Pick up- After Jan 102487.5Inv#018 | [5 empty] | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2153 | 20200316-7 | 53510611 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2020-03-16 | 1 | Inv#018 | 43923 | 88 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Snow Removal on Prairie Rd., Del Lake, Lake A, Middleton Road both during the day and overnight | 6 | Multiple Areas | WF6 | 0 | 43913 |  | 42 | 43915 | [5 empty] | Jarod Okemow | 06 | Corbiere and Sons Contracting215320200316-7L.O.A.3630 | Corbiere and Sons Contracting215320200316-7L.O.A.3630Inv#018 | [5 empty] | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2537 | 20200317-12 | 53510611 | Access | 0 | Loader JD 744 to 844 or equal | 162 | 12 | HR | 121.5 | 0 |  |  | 1944 | 252.72 | 2196.72 | 2020-03-17 | 1 | INV#027 | 43973 | 91 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Open up entrance and level out pit run at Dead Horse Creek; Plow Neys Road and Dead Horse Creek Road with DOZ-08; Snow Removal on Hare Lake Road with Grader; Float DZ-08 from Neys to Dead Horse Creek and EXC015 from laydown to Little Red Sucker Creek; | 6 |  |  | 0 | 43959 |  | 42 | 43965 | [5 empty] | Jarod Okemow | 06 | Corbiere and Sons Contracting253720200317-12Loader JD 744 to 844 or equal121944 | Corbiere and Sons Contracting253720200317-12Loader JD 744 to 844 or equal121944INV#027 | [5 empty] | 1 | 1944 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2537 | 20200317-12 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 12 | Dynamic | 98.61 | 0 |  |  | 1577.76 | 205.1088 | 1782.8688 | 2020-03-17 | 1 | INV#027 | 43973 | 91 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Open up entrance and level out pit run at Dead Horse Creek; Plow Neys Road and Dead Horse Creek Road with DOZ-08; Snow Removal on Hare Lake Road with Grader; Float DZ-08 from Neys to Dead Horse Creek and EXC015 from laydown to Little Red Sucker Creek; | 6 |  |  | 0 | 43959 |  | 42 | 43965 | [5 empty] | Jarod Okemow | 06 | Corbiere and Sons Contracting253720200317-12Dozer D6 or equal- After Jan 10121577.76 | Corbiere and Sons Contracting253720200317-12Dozer D6 or equal- After Jan 10121577.76INV#027 | [5 empty] | 1 | 1577.76 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2537 | 20200317-12 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 6 | Dynamic | 95.24 | 0 |  |  | 761.88 | 99.0444 | 860.9244 | 2020-03-17 | 1 | INV#027 | 43973 | 91 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Open up entrance and level out pit run at Dead Horse Creek; Plow Neys Road and Dead Horse Creek Road with DOZ-08; Snow Removal on Hare Lake Road with Grader; Float DZ-08 from Neys to Dead Horse Creek and EXC015 from laydown to Little Red Sucker Creek; | 6 |  |  | 0 | 43959 |  | 42 | 43965 | [5 empty] | Jarod Okemow | 06 | Corbiere and Sons Contracting253720200317-12Grader - Cat 12 to 14 or equal- After Jan 106761.88 | Corbiere and Sons Contracting253720200317-12Grader - Cat 12 to 14 or equal- After Jan 106761.88INV#027 | [5 empty] | 1 | 761.88 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2537 | 20200317-12 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 4 | DAY | 182.81 | 0 |  |  | 975 | 126.75 | 1101.75 | 2020-03-17 | 1 | INV#027 | 43973 | 91 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Open up entrance and level out pit run at Dead Horse Creek; Plow Neys Road and Dead Horse Creek Road with DOZ-08; Snow Removal on Hare Lake Road with Grader; Float DZ-08 from Neys to Dead Horse Creek and EXC015 from laydown to Little Red Sucker Creek; | 6 |  |  | 0 | 43959 |  | 42 | 43965 | [5 empty] | Jarod Okemow | 06 | Corbiere and Sons Contracting253720200317-12Light Truck - Pick up- After Jan 104975 | Corbiere and Sons Contracting253720200317-12Light Truck - Pick up- After Jan 104975INV#027 | [5 empty] | 1 | 975 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2537 | 20200317-12 | 53510611 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 5 | Dynamic | 91.79 | 0 |  |  | 611.95 | 79.5535 | 691.5035 | 2020-03-17 | 1 | INV#027 | 43973 | 91 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Open up entrance and level out pit run at Dead Horse Creek; Plow Neys Road and Dead Horse Creek Road with DOZ-08; Snow Removal on Hare Lake Road with Grader; Float DZ-08 from Neys to Dead Horse Creek and EXC015 from laydown to Little Red Sucker Creek; | 6 |  |  | 0 | 43959 |  | 42 | 43965 | [5 empty] | Jarod Okemow | 06 | Corbiere and Sons Contracting253720200317-12Tractor Trailer - 60 Ton- After Jan 105611.95 | Corbiere and Sons Contracting253720200317-12Tractor Trailer - 60 Ton- After Jan 105611.95INV#027 | [5 empty] | 1 | 611.95 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2537 | 20200317-12 | 53510611 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2020-03-17 | 1 | INV#027 | 43973 | 91 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Open up entrance and level out pit run at Dead Horse Creek; Plow Neys Road and Dead Horse Creek Road with DOZ-08; Snow Removal on Hare Lake Road with Grader; Float DZ-08 from Neys to Dead Horse Creek and EXC015 from laydown to Little Red Sucker Creek; | 6 |  |  | 0 | 43959 |  | 42 | 43965 | [5 empty] | Jarod Okemow | 06 | Corbiere and Sons Contracting253720200317-12Foreman121140 | Corbiere and Sons Contracting253720200317-12Foreman121140INV#027 | [5 empty] | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2537 | 20200317-12 | 53510611 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2020-03-17 | 1 | INV#027 | 43973 | 91 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Open up entrance and level out pit run at Dead Horse Creek; Plow Neys Road and Dead Horse Creek Road with DOZ-08; Snow Removal on Hare Lake Road with Grader; Float DZ-08 from Neys to Dead Horse Creek and EXC015 from laydown to Little Red Sucker Creek; | 6 |  |  | 0 | 43959 |  | 42 | 43965 | [5 empty] | Jarod Okemow | 06 | Corbiere and Sons Contracting253720200317-12L.O.A.4840 | Corbiere and Sons Contracting253720200317-12L.O.A.4840INV#027 | [5 empty] | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2537 | 20200317-12 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 30 | HR |  |  | 75 | 0 | 2250 | 292.5 | 2542.5 | 2020-03-17 | 1 | INV#027 | 43973 | 91 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Open up entrance and level out pit run at Dead Horse Creek; Plow Neys Road and Dead Horse Creek Road with DOZ-08; Snow Removal on Hare Lake Road with Grader; Float DZ-08 from Neys to Dead Horse Creek and EXC015 from laydown to Little Red Sucker Creek; | 6 |  |  | 0 | 43959 |  | 42 | 43965 | [5 empty] | Jarod Okemow | 06 | Corbiere and Sons Contracting253720200317-12Operator - Principle - After Jan 10302250 | Corbiere and Sons Contracting253720200317-12Operator - Principle - After Jan 10302250INV#027 | [5 empty] | 1 | 2250 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2537 | 20200317-12 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 5 | HR |  |  | 70 | 0 | 350 | 45.5 | 395.5 | 2020-03-17 | 1 | INV#027 | 43973 | 91 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Open up entrance and level out pit run at Dead Horse Creek; Plow Neys Road and Dead Horse Creek Road with DOZ-08; Snow Removal on Hare Lake Road with Grader; Float DZ-08 from Neys to Dead Horse Creek and EXC015 from laydown to Little Red Sucker Creek; | 6 |  |  | 0 | 43959 |  | 42 | 43965 | [5 empty] | Jarod Okemow | 06 | Corbiere and Sons Contracting253720200317-12Driver - AZ - After Jan 105350 | Corbiere and Sons Contracting253720200317-12Driver - AZ - After Jan 105350INV#027 | [5 empty] | 1 | 350 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2158 | 20200317-4 | 53510212 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 95.24 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2020-03-17 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grading from Black Sturgeon heading Eastward | 2 | B018 - B029 | Black Sturgeon | 0 | 43916 |  | 37 | 43916 | [5 empty] | Harold Furlong | 02 | Corbiere and Sons Contracting215820200317-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting215820200317-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8Inv#022 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2158 | 20200317-4 | 53510212 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-03-17 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grading from Black Sturgeon heading Eastward | 2 | B018 - B029 | Black Sturgeon | 0 | 43916 |  | 37 | 43916 | [5 empty] | Harold Furlong | 02 | Corbiere and Sons Contracting215820200317-4L.O.A.1210 | Corbiere and Sons Contracting215820200317-4L.O.A.1210Inv#022 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2158 | 20200317-4 | 53510212 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2020-03-17 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grading from Black Sturgeon heading Eastward | 2 | B018 - B029 | Black Sturgeon | 0 | 43916 |  | 37 | 43916 | [5 empty] | Harold Furlong | 02 | Corbiere and Sons Contracting215820200317-4Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting215820200317-4Operator - Principle - After Jan 1011825Inv#022 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2161 | 20200317-7 | 53510612 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 20 | Dynamic | 95.24 | 0 |  |  | 2539.6 | 330.148 | 2869.748 | 2020-03-17 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Overnight maintenance of roads on Santoy Lake, Prairie Road, and Del West; Labourers needed to escort graders on highway and put on and remove chains | 6 | Multiple Areas | Santoy Lake, Prairie Road and Del West | 0 | 43916 |  | 41 | 43923 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting216120200317-7Grader - Cat 12 to 14 or equal- After Jan 10202539.6 | Corbiere and Sons Contracting216120200317-7Grader - Cat 12 to 14 or equal- After Jan 10202539.6Inv#022 | [5 empty] | 1 | 2539.6 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2161 | 20200317-7 | 53510612 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-03-17 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Overnight maintenance of roads on Santoy Lake, Prairie Road, and Del West; Labourers needed to escort graders on highway and put on and remove chains | 6 | Multiple Areas | Santoy Lake, Prairie Road and Del West | 0 | 43916 |  | 41 | 43923 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting216120200317-7Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting216120200317-7Light Truck - Pick up- After Jan 102487.5Inv#022 | [5 empty] | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2161 | 20200317-7 | 53510612 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2020-03-17 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Overnight maintenance of roads on Santoy Lake, Prairie Road, and Del West; Labourers needed to escort graders on highway and put on and remove chains | 6 | Multiple Areas | Santoy Lake, Prairie Road and Del West | 0 | 43916 |  | 41 | 43923 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting216120200317-7L.O.A.4840 | Corbiere and Sons Contracting216120200317-7L.O.A.4840Inv#022 | [5 empty] | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2161 | 20200317-7 | 53510612 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 22 | HR |  |  | 75 | 0 | 1650 | 214.5 | 1864.5 | 2020-03-17 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Overnight maintenance of roads on Santoy Lake, Prairie Road, and Del West; Labourers needed to escort graders on highway and put on and remove chains | 6 | Multiple Areas | Santoy Lake, Prairie Road and Del West | 0 | 43916 |  | 41 | 43923 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting216120200317-7Operator - Principle - After Jan 10221650 | Corbiere and Sons Contracting216120200317-7Operator - Principle - After Jan 10221650Inv#022 | [5 empty] | 1 | 1650 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2161 | 20200317-7 | 53510612 | Access | 0 | Labourer - General - After Jan 10 | 60 | 6 | HR |  |  | 60 | 0 | 360 | 46.8 | 406.8 | 2020-03-17 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Overnight maintenance of roads on Santoy Lake, Prairie Road, and Del West; Labourers needed to escort graders on highway and put on and remove chains | 6 | Multiple Areas | Santoy Lake, Prairie Road and Del West | 0 | 43916 |  | 41 | 43923 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting216120200317-7Labourer - General - After Jan 106360 | Corbiere and Sons Contracting216120200317-7Labourer - General - After Jan 106360Inv#022 | [5 empty] | 1 | 360 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2221 | 20200318-11 | 53510612 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 20 | Dynamic | 95.24 | 0 |  |  | 2539.6 | 330.148 | 2869.748 | 2020-03-18 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Overnight snow removal and maintenance of access roads across all area | 6 | All Areas | All Areas | 0 | 43915 |  | 41 | 43922 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting222120200318-11Grader - Cat 12 to 14 or equal- After Jan 10202539.6 | Corbiere and Sons Contracting222120200318-11Grader - Cat 12 to 14 or equal- After Jan 10202539.6Inv#022 | [5 empty] | 1 | 2539.6 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2221 | 20200318-11 | 53510612 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-03-18 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Overnight snow removal and maintenance of access roads across all area | 6 | All Areas | All Areas | 0 | 43915 |  | 41 | 43922 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting222120200318-11Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting222120200318-11Light Truck - Pick up- After Jan 102487.5Inv#022 | [5 empty] | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2221 | 20200318-11 | 53510612 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2020-03-18 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Overnight snow removal and maintenance of access roads across all area | 6 | All Areas | All Areas | 0 | 43915 |  | 41 | 43922 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting222120200318-11L.O.A.4840 | Corbiere and Sons Contracting222120200318-11L.O.A.4840Inv#022 | [5 empty] | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2221 | 20200318-11 | 53510612 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 22 | HR |  |  | 75 | 0 | 1650 | 214.5 | 1864.5 | 2020-03-18 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Overnight snow removal and maintenance of access roads across all area | 6 | All Areas | All Areas | 0 | 43915 |  | 41 | 43922 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting222120200318-11Operator - Principle - After Jan 10221650 | Corbiere and Sons Contracting222120200318-11Operator - Principle - After Jan 10221650Inv#022 | [5 empty] | 1 | 1650 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2221 | 20200318-11 | 53510612 | Access | 0 | Labourer - General - After Jan 10 | 60 | 6 | HR |  |  | 60 | 0 | 360 | 46.8 | 406.8 | 2020-03-18 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Overnight snow removal and maintenance of access roads across all area | 6 | All Areas | All Areas | 0 | 43915 |  | 41 | 43922 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting222120200318-11Labourer - General - After Jan 106360 | Corbiere and Sons Contracting222120200318-11Labourer - General - After Jan 106360Inv#022 | [5 empty] | 1 | 360 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2213 | 20200318-3 | 53510312 | Access | 0 | Loader JD 524 to 624 or equal | 99 | 4 | HR | 74.25 | 0 |  |  | 396 | 51.48 | 447.48 | 2020-03-18 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Clearing snow on existing roads from B100-B109 | 3 | B100-B109 | All Areas | 0 | 43915 |  | 43 | 43917 | [5 empty] | Will Ouimet | 03 | Corbiere and Sons Contracting221320200318-3Loader JD 524 to 624 or equal4396 | Corbiere and Sons Contracting221320200318-3Loader JD 524 to 624 or equal4396Inv#022 | [5 empty] | 1 | 396 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2213 | 20200318-3 | 53510312 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 6 | Dynamic | 95.24 | 0 |  |  | 761.88 | 99.0444 | 860.9244 | 2020-03-18 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Clearing snow on existing roads from B100-B109 | 3 | B100-B109 | All Areas | 0 | 43915 |  | 43 | 43917 | [5 empty] | Will Ouimet | 03 | Corbiere and Sons Contracting221320200318-3Grader - Cat 12 to 14 or equal- After Jan 106761.88 | Corbiere and Sons Contracting221320200318-3Grader - Cat 12 to 14 or equal- After Jan 106761.88Inv#022 | [5 empty] | 1 | 761.88 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2213 | 20200318-3 | 53510312 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-03-18 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Clearing snow on existing roads from B100-B109 | 3 | B100-B109 | All Areas | 0 | 43915 |  | 43 | 43917 | [5 empty] | Will Ouimet | 03 | Corbiere and Sons Contracting221320200318-3L.O.A.1210 | Corbiere and Sons Contracting221320200318-3L.O.A.1210Inv#022 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2213 | 20200318-3 | 53510312 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2020-03-18 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Clearing snow on existing roads from B100-B109 | 3 | B100-B109 | All Areas | 0 | 43915 |  | 43 | 43917 | [5 empty] | Will Ouimet | 03 | Corbiere and Sons Contracting221320200318-3Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting221320200318-3Operator - Principle - After Jan 1011825Inv#022 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2216 | 20200318-6 | 53510212 | Access | 0 | Sander Truck - Forestry- After Jan 10 | 86.38 | 4 | Dynamic | 64.79 | 0 |  |  | 345.52 | 44.9176 | 390.4376 | 2020-03-18 | 1 | INV#027 | 43973 | 91 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Mobilization of a grinder, skidder and log loader into WF2; Sanding of access roads | 2 | B054 - B064 | Lofty Davies | 0 | 43916 |  | 36 | 43917 | [5 empty] | Mike Lecocq | 02 | Corbiere and Sons Contracting221620200318-6Sander Truck - Forestry- After Jan 104345.52 | Corbiere and Sons Contracting221620200318-6Sander Truck - Forestry- After Jan 104345.52INV#027 | [5 empty] | 1 | 345.52 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2216 | 20200318-6 | 53510212 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-03-18 | 1 | INV#027 | 43973 | 91 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Mobilization of a grinder, skidder and log loader into WF2; Sanding of access roads | 2 | B054 - B064 | Lofty Davies | 0 | 43916 |  | 36 | 43917 | [5 empty] | Mike Lecocq | 02 | Corbiere and Sons Contracting221620200318-6L.O.A.1210 | Corbiere and Sons Contracting221620200318-6L.O.A.1210INV#027 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2216 | 20200318-6 | 53510212 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 4 | HR |  |  | 70 | 0 | 280 | 36.4 | 316.4 | 2020-03-18 | 1 | INV#027 | 43973 | 91 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Mobilization of a grinder, skidder and log loader into WF2; Sanding of access roads | 2 | B054 - B064 | Lofty Davies | 0 | 43916 |  | 36 | 43917 | [5 empty] | Mike Lecocq | 02 | Corbiere and Sons Contracting221620200318-6Driver - AZ - After Jan 104280 | Corbiere and Sons Contracting221620200318-6Driver - AZ - After Jan 104280INV#027 | [5 empty] | 1 | 280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2540 | 20200319-11 | 53510512 | Access | 0 | Dozer D8 or equal- After Jan 10 | 217.5 | 2 | Dynamic | 163.13 | 0 |  |  | 435 | 56.55 | 491.55 | 2020-03-19 | 1 | INV#027 | 43973 | 91 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Snow Removal done with D-8 from C124-C126 | 5 | C124-C126 |  | 0 | 43959 |  | 42 | 43965 | [5 empty] | Jarod Okemow | 05 | Corbiere and Sons Contracting254020200319-11Dozer D8 or equal- After Jan 102435 | Corbiere and Sons Contracting254020200319-11Dozer D8 or equal- After Jan 102435INV#027 | [5 empty] | 1 | 435 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2540 | 20200319-11 | 53510512 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-03-19 | 1 | INV#027 | 43973 | 91 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Snow Removal done with D-8 from C124-C126 | 5 | C124-C126 |  | 0 | 43959 |  | 42 | 43965 | [5 empty] | Jarod Okemow | 05 | Corbiere and Sons Contracting254020200319-11Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting254020200319-11Light Truck - Pick up- After Jan 101243.75INV#027 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2540 | 20200319-11 | 53510512 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-03-19 | 1 | INV#027 | 43973 | 91 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Snow Removal done with D-8 from C124-C126 | 5 | C124-C126 |  | 0 | 43959 |  | 42 | 43965 | [5 empty] | Jarod Okemow | 05 | Corbiere and Sons Contracting254020200319-11L.O.A.1210 | Corbiere and Sons Contracting254020200319-11L.O.A.1210INV#027 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2540 | 20200319-11 | 53510512 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 2 | HR |  |  | 75 | 0 | 150 | 19.5 | 169.5 | 2020-03-19 | 1 | INV#027 | 43973 | 91 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Snow Removal done with D-8 from C124-C126 | 5 | C124-C126 |  | 0 | 43959 |  | 42 | 43965 | [5 empty] | Jarod Okemow | 05 | Corbiere and Sons Contracting254020200319-11Operator - Principle - After Jan 102150 | Corbiere and Sons Contracting254020200319-11Operator - Principle - After Jan 102150INV#027 | [5 empty] | 1 | 150 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2542 | 20200319-12 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 4 | Dynamic | 95.24 | 0 |  |  | 507.92 | 66.0296 | 573.9496 | 2020-03-19 | 1 | INV#027 | 43973 | 91 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader plowing on Hare Lake Road | 6 | C257-C267 | Hare Lake Road | 0 | 43959 |  | 42 | 43965 | [5 empty] | Jarod Okemow | 06 | Corbiere and Sons Contracting254220200319-12Grader - Cat 12 to 14 or equal- After Jan 104507.92 | Corbiere and Sons Contracting254220200319-12Grader - Cat 12 to 14 or equal- After Jan 104507.92INV#027 | [5 empty] | 1 | 507.92 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2542 | 20200319-12 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 4 | HR |  |  | 75 | 0 | 300 | 39 | 339 | 2020-03-19 | 1 | INV#027 | 43973 | 91 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader plowing on Hare Lake Road | 6 | C257-C267 | Hare Lake Road | 0 | 43959 |  | 42 | 43965 | [5 empty] | Jarod Okemow | 06 | Corbiere and Sons Contracting254220200319-12Operator - Principle - After Jan 104300 | Corbiere and Sons Contracting254220200319-12Operator - Principle - After Jan 104300INV#027 | [5 empty] | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2227 | 20200319-4 | 53510212 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 95.24 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2020-03-19 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Clearing and doing maintenance across all WF2 access roads; | 2 | All WF2 Areas | All WF2 Access Roads | 0 | 43915 |  | 37 | 43922 | [5 empty] | Harold Furlong | 02 | Corbiere and Sons Contracting222720200319-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting222720200319-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8Inv#022 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2227 | 20200319-4 | 53510212 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-03-19 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Clearing and doing maintenance across all WF2 access roads; | 2 | All WF2 Areas | All WF2 Access Roads | 0 | 43915 |  | 37 | 43922 | [5 empty] | Harold Furlong | 02 | Corbiere and Sons Contracting222720200319-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting222720200319-4Light Truck - Pick up- After Jan 101243.75Inv#022 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2227 | 20200319-4 | 53510212 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-03-19 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Clearing and doing maintenance across all WF2 access roads; | 2 | All WF2 Areas | All WF2 Access Roads | 0 | 43915 |  | 37 | 43922 | [5 empty] | Harold Furlong | 02 | Corbiere and Sons Contracting222720200319-4L.O.A.1210 | Corbiere and Sons Contracting222720200319-4L.O.A.1210Inv#022 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2227 | 20200319-4 | 53510212 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2020-03-19 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Clearing and doing maintenance across all WF2 access roads; | 2 | All WF2 Areas | All WF2 Access Roads | 0 | 43915 |  | 37 | 43922 | [5 empty] | Harold Furlong | 02 | Corbiere and Sons Contracting222720200319-4Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting222720200319-4Operator - Principle - After Jan 1011825Inv#022 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2229 | 20200319-6 | 53510612 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 22 | Dynamic | 95.24 | 0 |  |  | 2793.56 | 363.1628 | 3156.7228 | 2020-03-19 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Maintenance and continuous scraping of all access roads to keep safe; work done across multiple segments, Lake A up to Del Lake; Work done both day and night; Laboures escorting floats and changing chains when necessary | 6 |  | Lake A, Del Lake, Prairie River | 0 | 43915 |  | 41 | 43925 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting222920200319-6Grader - Cat 12 to 14 or equal- After Jan 10222793.56 | Corbiere and Sons Contracting222920200319-6Grader - Cat 12 to 14 or equal- After Jan 10222793.56Inv#022 | [5 empty] | 1 | 2793.56 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2229 | 20200319-6 | 53510612 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 20 | Dynamic | 95.24 | 0 |  |  | 2539.6 | 330.148 | 2869.748 | 2020-03-19 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Maintenance and continuous scraping of all access roads to keep safe; work done across multiple segments, Lake A up to Del Lake; Work done both day and night; Laboures escorting floats and changing chains when necessary | 6 |  | Lake A, Del Lake, Prairie River | 0 | 43915 |  | 41 | 43925 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting222920200319-6Grader - Cat 12 to 14 or equal- After Jan 10202539.6 | Corbiere and Sons Contracting222920200319-6Grader - Cat 12 to 14 or equal- After Jan 10202539.6Inv#022 | [5 empty] | 1 | 2539.6 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2229 | 20200319-6 | 53510612 | Access | 0 | Snow Plow- After Jan 10 | 95 | 11 | Dynamic | 71.25 | 0 |  |  | 1045 | 135.85 | 1180.85 | 2020-03-19 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Maintenance and continuous scraping of all access roads to keep safe; work done across multiple segments, Lake A up to Del Lake; Work done both day and night; Laboures escorting floats and changing chains when necessary | 6 |  | Lake A, Del Lake, Prairie River | 0 | 43915 |  | 41 | 43925 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting222920200319-6Snow Plow- After Jan 10111045 | Corbiere and Sons Contracting222920200319-6Snow Plow- After Jan 10111045Inv#022 | [5 empty] | 1 | 1045 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2229 | 20200319-6 | 53510612 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2020-03-19 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Maintenance and continuous scraping of all access roads to keep safe; work done across multiple segments, Lake A up to Del Lake; Work done both day and night; Laboures escorting floats and changing chains when necessary | 6 |  | Lake A, Del Lake, Prairie River | 0 | 43915 |  | 41 | 43925 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting222920200319-6Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting222920200319-6Light Truck - Pick up- After Jan 103731.25Inv#022 | [5 empty] | 1 | 731.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2229 | 20200319-6 | 53510612 | Access | 0 | L.O.A. | 210 | 7 | DAY |  |  |  | 0 | 1470 | 191.1 | 1661.1 | 2020-03-19 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Maintenance and continuous scraping of all access roads to keep safe; work done across multiple segments, Lake A up to Del Lake; Work done both day and night; Laboures escorting floats and changing chains when necessary | 6 |  | Lake A, Del Lake, Prairie River | 0 | 43915 |  | 41 | 43925 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting222920200319-6L.O.A.71470 | Corbiere and Sons Contracting222920200319-6L.O.A.71470Inv#022 | [5 empty] | 1 | 1470 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2229 | 20200319-6 | 53510612 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 58 | HR |  |  | 75 | 0 | 4350 | 565.5 | 4915.5 | 2020-03-19 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Maintenance and continuous scraping of all access roads to keep safe; work done across multiple segments, Lake A up to Del Lake; Work done both day and night; Laboures escorting floats and changing chains when necessary | 6 |  | Lake A, Del Lake, Prairie River | 0 | 43915 |  | 41 | 43925 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting222920200319-6Operator - Principle - After Jan 10584350 | Corbiere and Sons Contracting222920200319-6Operator - Principle - After Jan 10584350Inv#022 | [5 empty] | 1 | 4350 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2229 | 20200319-6 | 53510612 | Access | 0 | Labourer - General - After Jan 10 | 60 | 6 | HR |  |  | 60 | 0 | 360 | 46.8 | 406.8 | 2020-03-19 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Maintenance and continuous scraping of all access roads to keep safe; work done across multiple segments, Lake A up to Del Lake; Work done both day and night; Laboures escorting floats and changing chains when necessary | 6 |  | Lake A, Del Lake, Prairie River | 0 | 43915 |  | 41 | 43925 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting222920200319-6Labourer - General - After Jan 106360 | Corbiere and Sons Contracting222920200319-6Labourer - General - After Jan 106360Inv#022 | [5 empty] | 1 | 360 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2244 | 20200320-10 | 53510612 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 95.24 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2020-03-20 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grading and plowing of snow across, Prairie Road, Lake A, Little Pic River, Santoy Lake; | 6 | C129-C218 | WF6 | 0 | 43923 |  | 41 | 43925 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting224420200320-10Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting224420200320-10Grader - Cat 12 to 14 or equal- After Jan 10101269.8Inv#022 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2244 | 20200320-10 | 53510612 | Access | 0 | Snow Plow- After Jan 10 | 95 | 10 | Dynamic | 71.25 | 0 |  |  | 950 | 123.5 | 1073.5 | 2020-03-20 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grading and plowing of snow across, Prairie Road, Lake A, Little Pic River, Santoy Lake; | 6 | C129-C218 | WF6 | 0 | 43923 |  | 41 | 43925 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting224420200320-10Snow Plow- After Jan 1010950 | Corbiere and Sons Contracting224420200320-10Snow Plow- After Jan 1010950Inv#022 | [5 empty] | 1 | 950 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2244 | 20200320-10 | 53510612 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-03-20 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grading and plowing of snow across, Prairie Road, Lake A, Little Pic River, Santoy Lake; | 6 | C129-C218 | WF6 | 0 | 43923 |  | 41 | 43925 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting224420200320-10Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting224420200320-10Light Truck - Pick up- After Jan 101243.75Inv#022 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2244 | 20200320-10 | 53510612 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-03-20 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grading and plowing of snow across, Prairie Road, Lake A, Little Pic River, Santoy Lake; | 6 | C129-C218 | WF6 | 0 | 43923 |  | 41 | 43925 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting224420200320-10L.O.A.2420 | Corbiere and Sons Contracting224420200320-10L.O.A.2420Inv#022 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2244 | 20200320-10 | 53510612 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 22 | HR |  |  | 75 | 0 | 1650 | 214.5 | 1864.5 | 2020-03-20 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grading and plowing of snow across, Prairie Road, Lake A, Little Pic River, Santoy Lake; | 6 | C129-C218 | WF6 | 0 | 43923 |  | 41 | 43925 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting224420200320-10Operator - Principle - After Jan 10221650 | Corbiere and Sons Contracting224420200320-10Operator - Principle - After Jan 10221650Inv#022 | [5 empty] | 1 | 1650 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2249 | 20200320-15 | 53510511 | Access | 0 | Dozer D8 or equal- After Jan 10 | 217.5 | 4 | Dynamic | 163.13 | 0 |  |  | 870 | 113.1 | 983.1 | 2020-03-20 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WF5 Clearing and Access from C124 to C128; | 5 | C124-C128 | WF5 | 0 | 43923 |  | 41 | 43925 | [5 empty] | Martin Hunt | 05 | Corbiere and Sons Contracting224920200320-15Dozer D8 or equal- After Jan 104870 | Corbiere and Sons Contracting224920200320-15Dozer D8 or equal- After Jan 104870Inv#022 | [5 empty] | 1 | 870 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2249 | 20200320-15 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-03-20 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WF5 Clearing and Access from C124 to C128; | 5 | C124-C128 | WF5 | 0 | 43923 |  | 41 | 43925 | [5 empty] | Martin Hunt | 05 | Corbiere and Sons Contracting224920200320-15L.O.A.1210 | Corbiere and Sons Contracting224920200320-15L.O.A.1210Inv#022 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2249 | 20200320-15 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 4 | HR |  |  | 75 | 0 | 300 | 39 | 339 | 2020-03-20 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | WF5 Clearing and Access from C124 to C128; | 5 | C124-C128 | WF5 | 0 | 43923 |  | 41 | 43925 | [5 empty] | Martin Hunt | 05 | Corbiere and Sons Contracting224920200320-15Operator - Principle - After Jan 104300 | Corbiere and Sons Contracting224920200320-15Operator - Principle - After Jan 104300Inv#022 | [5 empty] | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2251 | 20200320-17 | 53510611 | Access | 0 | Mechanics Truck | 55 | 3 | HR | 41.25 | 0 |  |  | 165 | 21.45 | 186.45 | 2020-03-20 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Plowing and Grading of Neys Road, Hare Lake, Culvert Creek, Peninsula Road and Dead Horse Creek | 6 | C129-C167 | WF6 | 0 | 43923 |  | 41 | 43925 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting225120200320-17Mechanics Truck3165 | Corbiere and Sons Contracting225120200320-17Mechanics Truck3165Inv#022 | [5 empty] | 1 | 165 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2251 | 20200320-17 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 3 | Dynamic | 98.61 | 0 |  |  | 394.44 | 51.2772 | 445.7172 | 2020-03-20 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Plowing and Grading of Neys Road, Hare Lake, Culvert Creek, Peninsula Road and Dead Horse Creek | 6 | C129-C167 | WF6 | 0 | 43923 |  | 41 | 43925 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting225120200320-17Dozer D6 or equal- After Jan 103394.44 | Corbiere and Sons Contracting225120200320-17Dozer D6 or equal- After Jan 103394.44Inv#022 | [5 empty] | 1 | 394.44 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2251 | 20200320-17 | 53510611 | Access | 0 | Dozer D8 or equal- After Jan 10 | 217.5 | 3 | Dynamic | 163.13 | 0 |  |  | 652.5 | 84.825 | 737.325 | 2020-03-20 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Plowing and Grading of Neys Road, Hare Lake, Culvert Creek, Peninsula Road and Dead Horse Creek | 6 | C129-C167 | WF6 | 0 | 43923 |  | 41 | 43925 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting225120200320-17Dozer D8 or equal- After Jan 103652.5 | Corbiere and Sons Contracting225120200320-17Dozer D8 or equal- After Jan 103652.5Inv#022 | [5 empty] | 1 | 652.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2251 | 20200320-17 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 9 | Dynamic | 95.24 | 0 |  |  | 1142.82 | 148.5666 | 1291.3866 | 2020-03-20 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Plowing and Grading of Neys Road, Hare Lake, Culvert Creek, Peninsula Road and Dead Horse Creek | 6 | C129-C167 | WF6 | 0 | 43923 |  | 41 | 43925 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting225120200320-17Grader - Cat 12 to 14 or equal- After Jan 1091142.82 | Corbiere and Sons Contracting225120200320-17Grader - Cat 12 to 14 or equal- After Jan 1091142.82Inv#022 | [5 empty] | 1 | 1142.82 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2251 | 20200320-17 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-03-20 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Plowing and Grading of Neys Road, Hare Lake, Culvert Creek, Peninsula Road and Dead Horse Creek | 6 | C129-C167 | WF6 | 0 | 43923 |  | 41 | 43925 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting225120200320-17Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting225120200320-17Light Truck - Pick up- After Jan 102487.5Inv#022 | [5 empty] | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2251 | 20200320-17 | 53510611 | Access | 0 | Mechanic | 90 | 3 | HR |  |  | 90 | 0 | 270 | 35.1 | 305.1 | 2020-03-20 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Plowing and Grading of Neys Road, Hare Lake, Culvert Creek, Peninsula Road and Dead Horse Creek | 6 | C129-C167 | WF6 | 0 | 43923 |  | 41 | 43925 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting225120200320-17Mechanic3270 | Corbiere and Sons Contracting225120200320-17Mechanic3270Inv#022 | [5 empty] | 1 | 270 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2251 | 20200320-17 | 53510611 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2020-03-20 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Plowing and Grading of Neys Road, Hare Lake, Culvert Creek, Peninsula Road and Dead Horse Creek | 6 | C129-C167 | WF6 | 0 | 43923 |  | 41 | 43925 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting225120200320-17L.O.A.3630 | Corbiere and Sons Contracting225120200320-17L.O.A.3630Inv#022 | [5 empty] | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2251 | 20200320-17 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 15 | HR |  |  | 75 | 0 | 1125 | 146.25 | 1271.25 | 2020-03-20 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Plowing and Grading of Neys Road, Hare Lake, Culvert Creek, Peninsula Road and Dead Horse Creek | 6 | C129-C167 | WF6 | 0 | 43923 |  | 41 | 43925 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting225120200320-17Operator - Principle - After Jan 10151125 | Corbiere and Sons Contracting225120200320-17Operator - Principle - After Jan 10151125Inv#022 | [5 empty] | 1 | 1125 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2238 | 20200320-4 | 53510312 | Access | 0 | Loader JD 524 to 624 or equal | 99 | 8 | HR | 74.25 | 0 |  |  | 792 | 102.96 | 894.96 | 2020-03-20 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Clearing snow with Loader between towers B100 and B134 | 3 | B100-B134 | B100-B134 | 0 | 43923 |  | 43 | 43923 | [5 empty] | Will Ouimet | 03 | Corbiere and Sons Contracting223820200320-4Loader JD 524 to 624 or equal8792 | Corbiere and Sons Contracting223820200320-4Loader JD 524 to 624 or equal8792Inv#022 | [5 empty] | 1 | 792 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2238 | 20200320-4 | 53510312 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-03-20 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Clearing snow with Loader between towers B100 and B134 | 3 | B100-B134 | B100-B134 | 0 | 43923 |  | 43 | 43923 | [5 empty] | Will Ouimet | 03 | Corbiere and Sons Contracting223820200320-4L.O.A.1210 | Corbiere and Sons Contracting223820200320-4L.O.A.1210Inv#022 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2238 | 20200320-4 | 53510312 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 8 | HR |  |  | 75 | 0 | 600 | 78 | 678 | 2020-03-20 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Clearing snow with Loader between towers B100 and B134 | 3 | B100-B134 | B100-B134 | 0 | 43923 |  | 43 | 43923 | [5 empty] | Will Ouimet | 03 | Corbiere and Sons Contracting223820200320-4Operator - Principle - After Jan 108600 | Corbiere and Sons Contracting223820200320-4Operator - Principle - After Jan 108600Inv#022 | [5 empty] | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2240 | 20200320-6 | 53510212 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 95.24 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2020-03-20 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grading of all access roads at Valard direction; | 2 | B018-B077 | Access Roads | 0 | 43923 |  | 37 | 43923 | [5 empty] | Harold Furlong | 02 | Corbiere and Sons Contracting224020200320-6Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting224020200320-6Grader - Cat 12 to 14 or equal- After Jan 10101269.8Inv#022 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2240 | 20200320-6 | 53510212 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-03-20 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grading of all access roads at Valard direction; | 2 | B018-B077 | Access Roads | 0 | 43923 |  | 37 | 43923 | [5 empty] | Harold Furlong | 02 | Corbiere and Sons Contracting224020200320-6Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting224020200320-6Light Truck - Pick up- After Jan 101243.75Inv#022 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2240 | 20200320-6 | 53510212 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-03-20 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grading of all access roads at Valard direction; | 2 | B018-B077 | Access Roads | 0 | 43923 |  | 37 | 43923 | [5 empty] | Harold Furlong | 02 | Corbiere and Sons Contracting224020200320-6L.O.A.1210 | Corbiere and Sons Contracting224020200320-6L.O.A.1210Inv#022 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2240 | 20200320-6 | 53510212 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2020-03-20 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grading of all access roads at Valard direction; | 2 | B018-B077 | Access Roads | 0 | 43923 |  | 37 | 43923 | [5 empty] | Harold Furlong | 02 | Corbiere and Sons Contracting224020200320-6Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting224020200320-6Operator - Principle - After Jan 1011825Inv#022 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2241 | 20200320-7 | 53510212 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2020-03-20 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved in EX and it did road realignment | 2 | B067 | Red Rock | 0 | 43923 |  | 36 | 43925 | [5 empty] | Mike Lecocq | 02 | Corbiere and Sons Contracting224120200320-7Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting224120200320-7Excavator - 36 ton- After Jan 1091322.64Inv#022 | [5 empty] | 1 | 1322.64 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2241 | 20200320-7 | 53510212 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2020-03-20 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved in EX and it did road realignment | 2 | B067 | Red Rock | 0 | 43923 |  | 36 | 43925 | [5 empty] | Mike Lecocq | 02 | Corbiere and Sons Contracting224120200320-7Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting224120200320-7Excavator Thumb - 30 - 50 ton- After Jan 109109.89Inv#022 | [5 empty] | 1 | 109.89 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2241 | 20200320-7 | 53510212 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-03-20 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved in EX and it did road realignment | 2 | B067 | Red Rock | 0 | 43923 |  | 36 | 43925 | [5 empty] | Mike Lecocq | 02 | Corbiere and Sons Contracting224120200320-7Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting224120200320-7Light Truck - Pick up- After Jan 101243.75Inv#022 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2241 | 20200320-7 | 53510212 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 4 | Dynamic | 91.79 | 0 |  |  | 489.56 | 63.6428 | 553.2028 | 2020-03-20 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved in EX and it did road realignment | 2 | B067 | Red Rock | 0 | 43923 |  | 36 | 43925 | [5 empty] | Mike Lecocq | 02 | Corbiere and Sons Contracting224120200320-7Tractor Trailer - 60 Ton- After Jan 104489.56 | Corbiere and Sons Contracting224120200320-7Tractor Trailer - 60 Ton- After Jan 104489.56Inv#022 | [5 empty] | 1 | 489.56 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2241 | 20200320-7 | 53510212 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-03-20 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved in EX and it did road realignment | 2 | B067 | Red Rock | 0 | 43923 |  | 36 | 43925 | [5 empty] | Mike Lecocq | 02 | Corbiere and Sons Contracting224120200320-7L.O.A.2420 | Corbiere and Sons Contracting224120200320-7L.O.A.2420Inv#022 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2241 | 20200320-7 | 53510212 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2020-03-20 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved in EX and it did road realignment | 2 | B067 | Red Rock | 0 | 43923 |  | 36 | 43925 | [5 empty] | Mike Lecocq | 02 | Corbiere and Sons Contracting224120200320-7Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting224120200320-7Operator - Principle - After Jan 1011825Inv#022 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2241 | 20200320-7 | 53510212 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 4 | HR |  |  | 70 | 0 | 280 | 36.4 | 316.4 | 2020-03-20 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved in EX and it did road realignment | 2 | B067 | Red Rock | 0 | 43923 |  | 36 | 43925 | [5 empty] | Mike Lecocq | 02 | Corbiere and Sons Contracting224120200320-7Driver - AZ - After Jan 104280 | Corbiere and Sons Contracting224120200320-7Driver - AZ - After Jan 104280Inv#022 | [5 empty] | 1 | 280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2263 | 20200321-12 | 53510612 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 20 | Dynamic | 95.24 | 0 |  |  | 2539.6 | 330.148 | 2869.748 | 2020-03-21 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Maintenance of access roads in Lake A, Santoy Lake, Santoy Mountain and Prairie River Road overnight | 6 | C129-C267 | WF6 | 0 |  |  | 41 | 43925 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting226320200321-12Grader - Cat 12 to 14 or equal- After Jan 10202539.6 | Corbiere and Sons Contracting226320200321-12Grader - Cat 12 to 14 or equal- After Jan 10202539.6Inv#022 | [5 empty] | 1 | 2539.6 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2263 | 20200321-12 | 53510612 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-03-21 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Maintenance of access roads in Lake A, Santoy Lake, Santoy Mountain and Prairie River Road overnight | 6 | C129-C267 | WF6 | 0 |  |  | 41 | 43925 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting226320200321-12Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting226320200321-12Light Truck - Pick up- After Jan 102487.5Inv#022 | [5 empty] | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2263 | 20200321-12 | 53510612 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2020-03-21 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Maintenance of access roads in Lake A, Santoy Lake, Santoy Mountain and Prairie River Road overnight | 6 | C129-C267 | WF6 | 0 |  |  | 41 | 43925 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting226320200321-12L.O.A.4840 | Corbiere and Sons Contracting226320200321-12L.O.A.4840Inv#022 | [5 empty] | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2263 | 20200321-12 | 53510612 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 22 | HR |  |  | 75 | 0 | 1650 | 214.5 | 1864.5 | 2020-03-21 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Maintenance of access roads in Lake A, Santoy Lake, Santoy Mountain and Prairie River Road overnight | 6 | C129-C267 | WF6 | 0 |  |  | 41 | 43925 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting226320200321-12Operator - Principle - After Jan 10221650 | Corbiere and Sons Contracting226320200321-12Operator - Principle - After Jan 10221650Inv#022 | [5 empty] | 1 | 1650 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2263 | 20200321-12 | 53510612 | Access | 0 | Labourer - General - After Jan 10 | 60 | 6 | HR |  |  | 60 | 0 | 360 | 46.8 | 406.8 | 2020-03-21 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Maintenance of access roads in Lake A, Santoy Lake, Santoy Mountain and Prairie River Road overnight | 6 | C129-C267 | WF6 | 0 |  |  | 41 | 43925 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting226320200321-12Labourer - General - After Jan 106360 | Corbiere and Sons Contracting226320200321-12Labourer - General - After Jan 106360Inv#022 | [5 empty] | 1 | 360 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2264 | 20200321-13-R1 | 53510611 | Access | 0 | Mechanics Truck | 55 | 3 | HR | 41.25 | 0 |  |  | 165 | 21.45 | 186.45 | 2020-03-21 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Snow Removal on Culvert Creek up to C243 | 6 | C237-C243 | Culvert Creek | 0 | 43923 |  | 41 | 43925 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting226420200321-13-R1Mechanics Truck3165 | Corbiere and Sons Contracting226420200321-13-R1Mechanics Truck3165Inv#022 | [5 empty] | 1 | 165 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2264 | 20200321-13-R1 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 3 | Dynamic | 98.61 | 0 |  |  | 394.44 | 51.2772 | 445.7172 | 2020-03-21 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Snow Removal on Culvert Creek up to C243 | 6 | C237-C243 | Culvert Creek | 0 | 43923 |  | 41 | 43925 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting226420200321-13-R1Dozer D6 or equal- After Jan 103394.44 | Corbiere and Sons Contracting226420200321-13-R1Dozer D6 or equal- After Jan 103394.44Inv#022 | [5 empty] | 1 | 394.44 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2264 | 20200321-13-R1 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 3 | Dynamic | 95.24 | 0 |  |  | 380.94 | 49.5222 | 430.4622 | 2020-03-21 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Snow Removal on Culvert Creek up to C243 | 6 | C237-C243 | Culvert Creek | 0 | 43923 |  | 41 | 43925 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting226420200321-13-R1Grader - Cat 12 to 14 or equal- After Jan 103380.94 | Corbiere and Sons Contracting226420200321-13-R1Grader - Cat 12 to 14 or equal- After Jan 103380.94Inv#022 | [5 empty] | 1 | 380.94 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2264 | 20200321-13-R1 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-03-21 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Snow Removal on Culvert Creek up to C243 | 6 | C237-C243 | Culvert Creek | 0 | 43923 |  | 41 | 43925 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting226420200321-13-R1Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting226420200321-13-R1Light Truck - Pick up- After Jan 101243.75Inv#022 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2264 | 20200321-13-R1 | 53510611 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 2 | Dynamic | 91.79 | 0 |  |  | 244.78 | 31.8214 | 276.6014 | 2020-03-21 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Snow Removal on Culvert Creek up to C243 | 6 | C237-C243 | Culvert Creek | 0 | 43923 |  | 41 | 43925 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting226420200321-13-R1Tractor Trailer - 60 Ton- After Jan 102244.78 | Corbiere and Sons Contracting226420200321-13-R1Tractor Trailer - 60 Ton- After Jan 102244.78Inv#022 | [5 empty] | 1 | 244.78 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2264 | 20200321-13-R1 | 53510611 | Access | 0 | Mechanic | 90 | 3 | HR |  |  | 90 | 0 | 270 | 35.1 | 305.1 | 2020-03-21 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Snow Removal on Culvert Creek up to C243 | 6 | C237-C243 | Culvert Creek | 0 | 43923 |  | 41 | 43925 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting226420200321-13-R1Mechanic3270 | Corbiere and Sons Contracting226420200321-13-R1Mechanic3270Inv#022 | [5 empty] | 1 | 270 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2264 | 20200321-13-R1 | 53510611 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2020-03-21 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Snow Removal on Culvert Creek up to C243 | 6 | C237-C243 | Culvert Creek | 0 | 43923 |  | 41 | 43925 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting226420200321-13-R1L.O.A.4840 | Corbiere and Sons Contracting226420200321-13-R1L.O.A.4840Inv#022 | [5 empty] | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2264 | 20200321-13-R1 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 3 | HR |  |  | 75 | 0 | 225 | 29.25 | 254.25 | 2020-03-21 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Snow Removal on Culvert Creek up to C243 | 6 | C237-C243 | Culvert Creek | 0 | 43923 |  | 41 | 43925 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting226420200321-13-R1Operator - Principle - After Jan 103225 | Corbiere and Sons Contracting226420200321-13-R1Operator - Principle - After Jan 103225Inv#022 | [5 empty] | 1 | 225 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2264 | 20200321-13-R1 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 3 | HR |  |  | 75 | 0 | 225 | 29.25 | 254.25 | 2020-03-21 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Snow Removal on Culvert Creek up to C243 | 6 | C237-C243 | Culvert Creek | 0 | 43923 |  | 41 | 43925 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting226420200321-13-R1Operator - Principle - After Jan 103225 | Corbiere and Sons Contracting226420200321-13-R1Operator - Principle - After Jan 103225Inv#022 | [5 empty] | 1 | 225 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2264 | 20200321-13-R1 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 2 | HR |  |  | 70 | 0 | 140 | 18.2 | 158.2 | 2020-03-21 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Snow Removal on Culvert Creek up to C243 | 6 | C237-C243 | Culvert Creek | 0 | 43923 |  | 41 | 43925 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting226420200321-13-R1Driver - AZ - After Jan 102140 | Corbiere and Sons Contracting226420200321-13-R1Driver - AZ - After Jan 102140Inv#022 | [5 empty] | 1 | 140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2254 | 20200321-3 | 53510212 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 8 | Dynamic | 95.24 | 0 |  |  | 1015.84 | 132.0592 | 1147.8992 | 2020-03-21 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grading of all access roads in WF2 at Valards Direction | 2 | B018-B077 | WF2 | 0 | 43923 |  | 36 | 43925 | [5 empty] | Mike Lecocq | 02 | Corbiere and Sons Contracting225420200321-3Grader - Cat 12 to 14 or equal- After Jan 1081015.84 | Corbiere and Sons Contracting225420200321-3Grader - Cat 12 to 14 or equal- After Jan 1081015.84Inv#022 | [5 empty] | 1 | 1015.84 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2254 | 20200321-3 | 53510212 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-03-21 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grading of all access roads in WF2 at Valards Direction | 2 | B018-B077 | WF2 | 0 | 43923 |  | 36 | 43925 | [5 empty] | Mike Lecocq | 02 | Corbiere and Sons Contracting225420200321-3L.O.A.1210 | Corbiere and Sons Contracting225420200321-3L.O.A.1210Inv#022 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2254 | 20200321-3 | 53510212 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 8 | HR |  |  | 75 | 0 | 600 | 78 | 678 | 2020-03-21 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grading of all access roads in WF2 at Valards Direction | 2 | B018-B077 | WF2 | 0 | 43923 |  | 36 | 43925 | [5 empty] | Mike Lecocq | 02 | Corbiere and Sons Contracting225420200321-3Operator - Principle - After Jan 108600 | Corbiere and Sons Contracting225420200321-3Operator - Principle - After Jan 108600Inv#022 | [5 empty] | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2276 | 20200322-10 | 53510612 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 20 | Dynamic | 95.24 | 0 |  |  | 2539.6 | 330.148 | 2869.748 | 2020-03-22 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Maintenance of access roads on WF6 across various segments | 6 | C129-C267 | WF6 | 0 | 43923 |  | 41 | 43925 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting227620200322-10Grader - Cat 12 to 14 or equal- After Jan 10202539.6 | Corbiere and Sons Contracting227620200322-10Grader - Cat 12 to 14 or equal- After Jan 10202539.6Inv#022 | [5 empty] | 1 | 2539.6 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2276 | 20200322-10 | 53510612 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-03-22 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Maintenance of access roads on WF6 across various segments | 6 | C129-C267 | WF6 | 0 | 43923 |  | 41 | 43925 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting227620200322-10L.O.A.2420 | Corbiere and Sons Contracting227620200322-10L.O.A.2420Inv#022 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2276 | 20200322-10 | 53510612 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 22 | HR |  |  | 75 | 0 | 1650 | 214.5 | 1864.5 | 2020-03-22 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Maintenance of access roads on WF6 across various segments | 6 | C129-C267 | WF6 | 0 | 43923 |  | 41 | 43925 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting227620200322-10Operator - Principle - After Jan 10221650 | Corbiere and Sons Contracting227620200322-10Operator - Principle - After Jan 10221650Inv#022 | [5 empty] | 1 | 1650 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2278 | 20200322-12 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 4 | Dynamic | 95.24 | 0 |  |  | 507.92 | 66.0296 | 573.9496 | 2020-03-22 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Attempted to go grade neys road but couldn't make it up the hill | 6 | C219-C236 | Neys | 0 | 43923 |  | 41 | 43925 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting227820200322-12Grader - Cat 12 to 14 or equal- After Jan 104507.92 | Corbiere and Sons Contracting227820200322-12Grader - Cat 12 to 14 or equal- After Jan 104507.92Inv#022 | [5 empty] | 1 | 507.92 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2278 | 20200322-12 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-03-22 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Attempted to go grade neys road but couldn't make it up the hill | 6 | C219-C236 | Neys | 0 | 43923 |  | 41 | 43925 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting227820200322-12Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting227820200322-12Light Truck - Pick up- After Jan 101243.75Inv#022 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2278 | 20200322-12 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-03-22 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Attempted to go grade neys road but couldn't make it up the hill | 6 | C219-C236 | Neys | 0 | 43923 |  | 41 | 43925 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting227820200322-12L.O.A.1210 | Corbiere and Sons Contracting227820200322-12L.O.A.1210Inv#022 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2278 | 20200322-12 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 4 | HR |  |  | 75 | 0 | 300 | 39 | 339 | 2020-03-22 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Attempted to go grade neys road but couldn't make it up the hill | 6 | C219-C236 | Neys | 0 | 43923 |  | 41 | 43925 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting227820200322-12Operator - Principle - After Jan 104300 | Corbiere and Sons Contracting227820200322-12Operator - Principle - After Jan 104300Inv#022 | [5 empty] | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2289 | 20200323-10 | 53520102 | Clearing | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 21 | Dynamic | 103.84 | 0 |  |  | 2907.45 | 377.9685 | 3285.4185 | 2020-03-23 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Burning from towers A117, A120 and 127; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43923 |  | 37 | 43924 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting228920200323-10Excavator - 30 ton- After Jan 10212907.45 | Corbiere and Sons Contracting228920200323-10Excavator - 30 ton- After Jan 10212907.45Inv#022 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2907.45 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2289 | 20200323-10 | 53520102 | Clearing | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 42 | Dynamic | 110.22 | 0 |  |  | 6172.32 | 802.4016 | 6974.7216 | 2020-03-23 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Burning from towers A117, A120 and 127; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43923 |  | 37 | 43924 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting228920200323-10Excavator - 36 ton- After Jan 10426172.32 | Corbiere and Sons Contracting228920200323-10Excavator - 36 ton- After Jan 10426172.32Inv#022 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 6172.32 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2289 | 20200323-10 | 53520102 | Clearing | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 42 | HR | 9.16 | 0 |  |  | 512.82 | 66.6666 | 579.4866 | 2020-03-23 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Burning from towers A117, A120 and 127; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43923 |  | 37 | 43924 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting228920200323-10Excavator Thumb - 30 - 50 ton- After Jan 1042512.82 | Corbiere and Sons Contracting228920200323-10Excavator Thumb - 30 - 50 ton- After Jan 1042512.82Inv#022 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 512.82 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2289 | 20200323-10 | 53520102 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 4 | DAY | 182.81 | 0 |  |  | 975 | 126.75 | 1101.75 | 2020-03-23 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Burning from towers A117, A120 and 127; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43923 |  | 37 | 43924 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting228920200323-10Light Truck - Pick up- After Jan 104975 | Corbiere and Sons Contracting228920200323-10Light Truck - Pick up- After Jan 104975Inv#022 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 975 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2289 | 20200323-10 | 53520102 | Clearing | 0 | L.O.A. | 210 | 10 | DAY |  |  |  | 0 | 2100 | 273 | 2373 | 2020-03-23 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Burning from towers A117, A120 and 127; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43923 |  | 37 | 43924 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting228920200323-10L.O.A.102100 | Corbiere and Sons Contracting228920200323-10L.O.A.102100Inv#022 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2100 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2289 | 20200323-10 | 53520102 | Clearing | 0 | Operator - Principle - After Jan 10 | 75 | 69 | HR |  |  | 75 | 0 | 5175 | 672.75 | 5847.75 | 2020-03-23 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Burning from towers A117, A120 and 127; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43923 |  | 37 | 43924 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting228920200323-10Operator - Principle - After Jan 10695175 | Corbiere and Sons Contracting228920200323-10Operator - Principle - After Jan 10695175Inv#022 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 5175 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2289 | 20200323-10 | 53520102 | Clearing | 0 | Labourer - General - After Jan 10 | 60 | 46 | HR |  |  | 60 | 0 | 2760 | 358.8 | 3118.8 | 2020-03-23 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Burning from towers A117, A120 and 127; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43923 |  | 37 | 43924 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting228920200323-10Labourer - General - After Jan 10462760 | Corbiere and Sons Contracting228920200323-10Labourer - General - After Jan 10462760Inv#022 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2760 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2290 | 20200323-11 | 53510212 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2020-03-23 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Finishing road realignment as B067 and then moving to B052; | 2 | B065-B077 | Red Rock | 0 | 43923 |  | 36 | 43925 | [5 empty] | Mike Lecocq | 02 | Corbiere and Sons Contracting229020200323-11Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting229020200323-11Excavator - 36 ton- After Jan 1091322.64Inv#022 | [5 empty] | 1 | 1322.64 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2290 | 20200323-11 | 53510212 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2020-03-23 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Finishing road realignment as B067 and then moving to B052; | 2 | B065-B077 | Red Rock | 0 | 43923 |  | 36 | 43925 | [5 empty] | Mike Lecocq | 02 | Corbiere and Sons Contracting229020200323-11Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting229020200323-11Excavator Thumb - 30 - 50 ton- After Jan 109109.89Inv#022 | [5 empty] | 1 | 109.89 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2290 | 20200323-11 | 53510212 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-03-23 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Finishing road realignment as B067 and then moving to B052; | 2 | B065-B077 | Red Rock | 0 | 43923 |  | 36 | 43925 | [5 empty] | Mike Lecocq | 02 | Corbiere and Sons Contracting229020200323-11Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting229020200323-11Light Truck - Pick up- After Jan 101243.75Inv#022 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2290 | 20200323-11 | 53510212 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-03-23 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Finishing road realignment as B067 and then moving to B052; | 2 | B065-B077 | Red Rock | 0 | 43923 |  | 36 | 43925 | [5 empty] | Mike Lecocq | 02 | Corbiere and Sons Contracting229020200323-11L.O.A.1210 | Corbiere and Sons Contracting229020200323-11L.O.A.1210Inv#022 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2290 | 20200323-11 | 53510212 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2020-03-23 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Finishing road realignment as B067 and then moving to B052; | 2 | B065-B077 | Red Rock | 0 | 43923 |  | 36 | 43925 | [5 empty] | Mike Lecocq | 02 | Corbiere and Sons Contracting229020200323-11Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting229020200323-11Operator - Principle - After Jan 1011825Inv#022 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2292 | 20200323-13 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 4 | Dynamic | 95.24 | 0 |  |  | 507.92 | 66.0296 | 573.9496 | 2020-03-23 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grading of access roads | 6 | C268-C279 | Peninsula Road | 0 | 43923 |  | 41 | 43925 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting229220200323-13Grader - Cat 12 to 14 or equal- After Jan 104507.92 | Corbiere and Sons Contracting229220200323-13Grader - Cat 12 to 14 or equal- After Jan 104507.92Inv#022 | [5 empty] | 1 | 507.92 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2292 | 20200323-13 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-03-23 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grading of access roads | 6 | C268-C279 | Peninsula Road | 0 | 43923 |  | 41 | 43925 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting229220200323-13Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting229220200323-13Light Truck - Pick up- After Jan 101243.75Inv#022 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2292 | 20200323-13 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 4 | HR |  |  | 75 | 0 | 300 | 39 | 339 | 2020-03-23 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grading of access roads | 6 | C268-C279 | Peninsula Road | 0 | 43923 |  | 41 | 43925 | [5 empty] | Martin Hunt | 06 | Corbiere and Sons Contracting229220200323-13Operator - Principle - After Jan 104300 | Corbiere and Sons Contracting229220200323-13Operator - Principle - After Jan 104300Inv#022 | [5 empty] | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2306 | 20200324-12 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 95.24 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2020-03-24 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Plowing and widening of Neys road E with Grader | 6 | C219-C236 | Neys | 0 | 43933 |  | 44 | 43934 | [5 empty] | Howard Beaudet | 06 | Corbiere and Sons Contracting230620200324-12Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting230620200324-12Grader - Cat 12 to 14 or equal- After Jan 10101269.8Inv#022 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2306 | 20200324-12 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-03-24 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Plowing and widening of Neys road E with Grader | 6 | C219-C236 | Neys | 0 | 43933 |  | 44 | 43934 | [5 empty] | Howard Beaudet | 06 | Corbiere and Sons Contracting230620200324-12L.O.A.1210 | Corbiere and Sons Contracting230620200324-12L.O.A.1210Inv#022 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2306 | 20200324-12 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 10 | HR |  |  | 75 | 0 | 750 | 97.5 | 847.5 | 2020-03-24 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Plowing and widening of Neys road E with Grader | 6 | C219-C236 | Neys | 0 | 43933 |  | 44 | 43934 | [5 empty] | Howard Beaudet | 06 | Corbiere and Sons Contracting230620200324-12Operator - Principle - After Jan 1010750 | Corbiere and Sons Contracting230620200324-12Operator - Principle - After Jan 1010750Inv#022 | [5 empty] | 1 | 750 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2307 | 20200324-13 | 53510611 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 5 | Dynamic | 95.24 | 0 |  |  | 634.9 | 82.537 | 717.437 | 2020-03-24 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grading of accesses along Santoy Lake Road | 6 | C156-C170 | Santoy Lake | 0 | 43933 |  | 44 | 43934 | [5 empty] | Howard Beaudet | 06 | Corbiere and Sons Contracting230720200324-13Grader - Cat 12 to 14 or equal- After Jan 105634.9 | Corbiere and Sons Contracting230720200324-13Grader - Cat 12 to 14 or equal- After Jan 105634.9Inv#022 | [5 empty] | 1 | 634.9 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2307 | 20200324-13 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-03-24 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grading of accesses along Santoy Lake Road | 6 | C156-C170 | Santoy Lake | 0 | 43933 |  | 44 | 43934 | [5 empty] | Howard Beaudet | 06 | Corbiere and Sons Contracting230720200324-13L.O.A.1210 | Corbiere and Sons Contracting230720200324-13L.O.A.1210Inv#022 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2307 | 20200324-13 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5 | HR |  |  | 75 | 0 | 375 | 48.75 | 423.75 | 2020-03-24 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grading of accesses along Santoy Lake Road | 6 | C156-C170 | Santoy Lake | 0 | 43933 |  | 44 | 43934 | [5 empty] | Howard Beaudet | 06 | Corbiere and Sons Contracting230720200324-13Operator - Principle - After Jan 105375 | Corbiere and Sons Contracting230720200324-13Operator - Principle - After Jan 105375Inv#022 | [5 empty] | 1 | 375 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2308 | 20200324-14 | 53510312 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 9 | Dynamic | 98.61 | 0 |  |  | 1183.32 | 153.8316 | 1337.1516 | 2020-03-24 | 1 | Inv#022 | 43938 | 89 | 0 | 1 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  | Standby Operator Principle 11 Hours Buncher 5 hours, D6Cat 3 Hours, Excavator 3 hours | 10 | Approved | Corbeire - Standby - Ongoing | 9010 | unchers on Standby - DZ openin up access for floats and envoronmental - Cleaned off legacy bridge | 3 | B161-B191 |  | 0 | 43933 |  | 44 | 43934 | [5 empty] | Howard Beaudet | 03 | Corbiere and Sons Contracting230820200324-14Dozer D6 or equal- After Jan 1091183.32 | Corbiere and Sons Contracting230820200324-14Dozer D6 or equal- After Jan 1091183.32Inv#022 | [5 empty] | 1 | 1183.32 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2308 | 20200324-14 | 53510312 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 7 | Dynamic | 110.22 | 0 |  |  | 1028.72 | 133.7336 | 1162.4536 | 2020-03-24 | 1 | Inv#022 | 43938 | 89 | 0 | 1 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  | Standby Operator Principle 11 Hours Buncher 5 hours, D6Cat 3 Hours, Excavator 3 hours | 10 | Approved | Corbeire - Standby - Ongoing | 9010 | unchers on Standby - DZ openin up access for floats and envoronmental - Cleaned off legacy bridge | 3 | B161-B191 |  | 0 | 43933 |  | 44 | 43934 | [5 empty] | Howard Beaudet | 03 | Corbiere and Sons Contracting230820200324-14Excavator - 36 ton- After Jan 1071028.72 | Corbiere and Sons Contracting230820200324-14Excavator - 36 ton- After Jan 1071028.72Inv#022 | [5 empty] | 1 | 1028.72 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2308 | 20200324-14 | 53510312 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 7 | HR | 9.16 | 0 |  |  | 85.47 | 11.1111 | 96.5811 | 2020-03-24 | 1 | Inv#022 | 43938 | 89 | 0 | 1 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  | Standby Operator Principle 11 Hours Buncher 5 hours, D6Cat 3 Hours, Excavator 3 hours | 10 | Approved | Corbeire - Standby - Ongoing | 9010 | unchers on Standby - DZ openin up access for floats and envoronmental - Cleaned off legacy bridge | 3 | B161-B191 |  | 0 | 43933 |  | 44 | 43934 | [5 empty] | Howard Beaudet | 03 | Corbiere and Sons Contracting230820200324-14Excavator Thumb - 30 - 50 ton- After Jan 10785.47 | Corbiere and Sons Contracting230820200324-14Excavator Thumb - 30 - 50 ton- After Jan 10785.47Inv#022 | [5 empty] | 1 | 85.47 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2308 | 20200324-14 | 53510312 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-03-24 | 1 | Inv#022 | 43938 | 89 | 0 | 1 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  | Standby Operator Principle 11 Hours Buncher 5 hours, D6Cat 3 Hours, Excavator 3 hours | 10 | Approved | Corbeire - Standby - Ongoing | 9010 | unchers on Standby - DZ openin up access for floats and envoronmental - Cleaned off legacy bridge | 3 | B161-B191 |  | 0 | 43933 |  | 44 | 43934 | [5 empty] | Howard Beaudet | 03 | Corbiere and Sons Contracting230820200324-14Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting230820200324-14Light Truck - Pick up- After Jan 102487.5Inv#022 | [5 empty] | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2308 | 20200324-14 | 53510312 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-03-24 | 1 | Inv#022 | 43938 | 89 | 0 | 1 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  | Standby Operator Principle 11 Hours Buncher 5 hours, D6Cat 3 Hours, Excavator 3 hours | 10 | Approved | Corbeire - Standby - Ongoing | 9010 | unchers on Standby - DZ openin up access for floats and envoronmental - Cleaned off legacy bridge | 3 | B161-B191 |  | 0 | 43933 |  | 44 | 43934 | [5 empty] | Howard Beaudet | 03 | Corbiere and Sons Contracting230820200324-14L.O.A.2420 | Corbiere and Sons Contracting230820200324-14L.O.A.2420Inv#022 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2308 | 20200324-14 | 53510312 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 19 | HR |  |  | 75 | 0 | 1425 | 185.25 | 1610.25 | 2020-03-24 | 1 | Inv#022 | 43938 | 89 | 0 | 1 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  | Standby Operator Principle 11 Hours Buncher 5 hours, D6Cat 3 Hours, Excavator 3 hours | 10 | Approved | Corbeire - Standby - Ongoing | 9010 | unchers on Standby - DZ openin up access for floats and envoronmental - Cleaned off legacy bridge | 3 | B161-B191 |  | 0 | 43933 |  | 44 | 43934 | [5 empty] | Howard Beaudet | 03 | Corbiere and Sons Contracting230820200324-14Operator - Principle - After Jan 10191425 | Corbiere and Sons Contracting230820200324-14Operator - Principle - After Jan 10191425Inv#022 | [5 empty] | 1 | 1425 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2309 | 20200324-15 | 53510212 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 6 | Dynamic | 95.24 | 0 |  |  | 761.88 | 99.0444 | 860.9244 | 2020-03-24 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Floated of Grader and EX - Grader working across lofty davies; Road being reliagned at B052 | 2 | B045-B054 | Lofty Davies | 0 | 43933 |  | 44 | 43934 | [5 empty] | Howard Beaudet | 02 | Corbiere and Sons Contracting230920200324-15Grader - Cat 12 to 14 or equal- After Jan 106761.88 | Corbiere and Sons Contracting230920200324-15Grader - Cat 12 to 14 or equal- After Jan 106761.88Inv#022 | [5 empty] | 1 | 761.88 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2309 | 20200324-15 | 53510212 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-03-24 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Floated of Grader and EX - Grader working across lofty davies; Road being reliagned at B052 | 2 | B045-B054 | Lofty Davies | 0 | 43933 |  | 44 | 43934 | [5 empty] | Howard Beaudet | 02 | Corbiere and Sons Contracting230920200324-15Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting230920200324-15Light Truck - Pick up- After Jan 101243.75Inv#022 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2309 | 20200324-15 | 53510212 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 75 | 0 | 450 | 58.5 | 508.5 | 2020-03-24 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Floated of Grader and EX - Grader working across lofty davies; Road being reliagned at B052 | 2 | B045-B054 | Lofty Davies | 0 | 43933 |  | 44 | 43934 | [5 empty] | Howard Beaudet | 02 | Corbiere and Sons Contracting230920200324-15Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting230920200324-15Operator - Principle - After Jan 106450Inv#022 | [5 empty] | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2315 | 20200324-4-R1 | 53510112 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 5 | Dynamic | 95.24 | 0 |  |  | 634.9 | 82.537 | 717.437 | 2020-03-24 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grading of access roads across windfarm | 1 | A-085 to A-117 | Windfarm | 0 | 43933 |  | 44 | 43934 | [5 empty] | Howard Beaudet | 01 | Corbiere and Sons Contracting231520200324-4-R1Grader - Cat 12 to 14 or equal- After Jan 105634.9 | Corbiere and Sons Contracting231520200324-4-R1Grader - Cat 12 to 14 or equal- After Jan 105634.9Inv#022 | [5 empty] | 1 | 634.9 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2315 | 20200324-4-R1 | 53510112 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-03-24 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grading of access roads across windfarm | 1 | A-085 to A-117 | Windfarm | 0 | 43933 |  | 44 | 43934 | [5 empty] | Howard Beaudet | 01 | Corbiere and Sons Contracting231520200324-4-R1L.O.A.1210 | Corbiere and Sons Contracting231520200324-4-R1L.O.A.1210Inv#022 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2315 | 20200324-4-R1 | 53510112 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5 | HR |  |  | 75 | 0 | 375 | 48.75 | 423.75 | 2020-03-24 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grading of access roads across windfarm | 1 | A-085 to A-117 | Windfarm | 0 | 43933 |  | 44 | 43934 | [5 empty] | Howard Beaudet | 01 | Corbiere and Sons Contracting231520200324-4-R1Operator - Principle - After Jan 105375 | Corbiere and Sons Contracting231520200324-4-R1Operator - Principle - After Jan 105375Inv#022 | [5 empty] | 1 | 375 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2300 | 20200324-6 | 53520102 | Clearing | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 24 | Dynamic | 103.84 | 0 |  |  | 3322.8 | 431.964 | 3754.764 | 2020-03-24 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  | Thumb not included in backup? |  | Approved |  |  | Burning from towers A110, A101, A117 - Day and night | 1 | A-085 to A-117 | Windfarm | 0 | 43933 |  | 44 | 43934 | [5 empty] | Howard Beaudet | 01 | Corbiere and Sons Contracting230020200324-6Excavator - 30 ton- After Jan 10243322.8 | Corbiere and Sons Contracting230020200324-6Excavator - 30 ton- After Jan 10243322.8Inv#022 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 3322.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2300 | 20200324-6 | 53520102 | Clearing | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 72 | Dynamic | 110.22 | 0 |  |  | 10581.12 | 1375.5456 | 11956.6656 | 2020-03-24 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  | Thumb not included in backup? |  | Approved |  |  | Burning from towers A110, A101, A117 - Day and night | 1 | A-085 to A-117 | Windfarm | 0 | 43933 |  | 44 | 43934 | [5 empty] | Howard Beaudet | 01 | Corbiere and Sons Contracting230020200324-6Excavator - 36 ton- After Jan 107210581.12 | Corbiere and Sons Contracting230020200324-6Excavator - 36 ton- After Jan 107210581.12Inv#022 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 10581.12 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2300 | 20200324-6 | 53520102 | Clearing | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 48 | HR | 9.16 | 0 |  |  | 586.08 | 76.1904 | 662.2704 | 2020-03-24 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  | Thumb not included in backup? |  | Approved |  |  | Burning from towers A110, A101, A117 - Day and night | 1 | A-085 to A-117 | Windfarm | 0 | 43933 |  | 44 | 43934 | [5 empty] | Howard Beaudet | 01 | Corbiere and Sons Contracting230020200324-6Excavator Thumb - 30 - 50 ton- After Jan 1048586.08 | Corbiere and Sons Contracting230020200324-6Excavator Thumb - 30 - 50 ton- After Jan 1048586.08Inv#022 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 586.08 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2300 | 20200324-6 | 53520102 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 6 | DAY | 182.81 | 0 |  |  | 1462.5 | 190.125 | 1652.625 | 2020-03-24 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  | Thumb not included in backup? |  | Approved |  |  | Burning from towers A110, A101, A117 - Day and night | 1 | A-085 to A-117 | Windfarm | 0 | 43933 |  | 44 | 43934 | [5 empty] | Howard Beaudet | 01 | Corbiere and Sons Contracting230020200324-6Light Truck - Pick up- After Jan 1061462.5 | Corbiere and Sons Contracting230020200324-6Light Truck - Pick up- After Jan 1061462.5Inv#022 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1462.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2300 | 20200324-6 | 53520102 | Clearing | 0 | Operator - Principle - After Jan 10 | 75 | 102 | HR |  |  | 75 | 0 | 7650 | 994.5 | 8644.5 | 2020-03-24 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  | Thumb not included in backup? |  | Approved |  |  | Burning from towers A110, A101, A117 - Day and night | 1 | A-085 to A-117 | Windfarm | 0 | 43933 |  | 44 | 43934 | [5 empty] | Howard Beaudet | 01 | Corbiere and Sons Contracting230020200324-6Operator - Principle - After Jan 101027650 | Corbiere and Sons Contracting230020200324-6Operator - Principle - After Jan 101027650Inv#022 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 7650 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2321 | 20200325-4 | 53520102 | Clearing | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 24 | Dynamic | 103.84 | 0 |  |  | 3322.8 | 431.964 | 3754.764 | 2020-03-25 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Burning from A100, A117 and A121 | 1 | A-085 to A-117 | Windfarm | 0 | 43933 |  | 40 | 43936 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting232120200325-4Excavator - 30 ton- After Jan 10243322.8 | Corbiere and Sons Contracting232120200325-4Excavator - 30 ton- After Jan 10243322.8Inv#022 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 3322.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2321 | 20200325-4 | 53520102 | Clearing | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 72 | Dynamic | 110.22 | 0 |  |  | 10581.12 | 1375.5456 | 11956.6656 | 2020-03-25 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Burning from A100, A117 and A121 | 1 | A-085 to A-117 | Windfarm | 0 | 43933 |  | 40 | 43936 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting232120200325-4Excavator - 36 ton- After Jan 107210581.12 | Corbiere and Sons Contracting232120200325-4Excavator - 36 ton- After Jan 107210581.12Inv#022 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 10581.12 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2321 | 20200325-4 | 53520102 | Clearing | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 72 | HR | 9.16 | 0 |  |  | 879.12 | 114.2856 | 993.4056 | 2020-03-25 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Burning from A100, A117 and A121 | 1 | A-085 to A-117 | Windfarm | 0 | 43933 |  | 40 | 43936 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting232120200325-4Excavator Thumb - 30 - 50 ton- After Jan 1072879.12 | Corbiere and Sons Contracting232120200325-4Excavator Thumb - 30 - 50 ton- After Jan 1072879.12Inv#022 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 879.12 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2321 | 20200325-4 | 53520102 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 6 | DAY | 182.81 | 0 |  |  | 1462.5 | 190.125 | 1652.625 | 2020-03-25 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Burning from A100, A117 and A121 | 1 | A-085 to A-117 | Windfarm | 0 | 43933 |  | 40 | 43936 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting232120200325-4Light Truck - Pick up- After Jan 1061462.5 | Corbiere and Sons Contracting232120200325-4Light Truck - Pick up- After Jan 1061462.5Inv#022 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1462.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2321 | 20200325-4 | 53520102 | Clearing | 0 | L.O.A. | 210 | 12 | DAY |  |  |  | 0 | 2520 | 327.6 | 2847.6 | 2020-03-25 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Burning from A100, A117 and A121 | 1 | A-085 to A-117 | Windfarm | 0 | 43933 |  | 40 | 43936 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting232120200325-4L.O.A.122520 | Corbiere and Sons Contracting232120200325-4L.O.A.122520Inv#022 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2520 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2321 | 20200325-4 | 53520102 | Clearing | 0 | Operator - Principle - After Jan 10 | 75 | 102 | HR |  |  | 75 | 0 | 7650 | 994.5 | 8644.5 | 2020-03-25 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Burning from A100, A117 and A121 | 1 | A-085 to A-117 | Windfarm | 0 | 43933 |  | 40 | 43936 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting232120200325-4Operator - Principle - After Jan 101027650 | Corbiere and Sons Contracting232120200325-4Operator - Principle - After Jan 101027650Inv#022 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 7650 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2321 | 20200325-4 | 53520102 | Clearing | 0 | Labourer - General - After Jan 10 | 60 | 51 | HR |  |  | 60 | 0 | 3060 | 397.8 | 3457.8 | 2020-03-25 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Burning from A100, A117 and A121 | 1 | A-085 to A-117 | Windfarm | 0 | 43933 |  | 40 | 43936 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting232120200325-4Labourer - General - After Jan 10513060 | Corbiere and Sons Contracting232120200325-4Labourer - General - After Jan 10513060Inv#022 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 3060 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2334 | 20200326-4 | 53520102 | Clearing | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 48 | Dynamic | 103.84 | 0 |  |  | 6645.6 | 863.928 | 7509.528 | 2020-03-26 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Burning from A116, A120, A121 and A125 | 1 | A-128 to B-017 | Wolf Lake | 0 | 43933 |  | 40 | 43936 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting233420200326-4Excavator - 30 ton- After Jan 10486645.6 | Corbiere and Sons Contracting233420200326-4Excavator - 30 ton- After Jan 10486645.6Inv#022 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 6645.6 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2334 | 20200326-4 | 53520102 | Clearing | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 48 | Dynamic | 110.22 | 0 |  |  | 7054.08 | 917.0304 | 7971.1104 | 2020-03-26 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Burning from A116, A120, A121 and A125 | 1 | A-128 to B-017 | Wolf Lake | 0 | 43933 |  | 40 | 43936 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting233420200326-4Excavator - 36 ton- After Jan 10487054.08 | Corbiere and Sons Contracting233420200326-4Excavator - 36 ton- After Jan 10487054.08Inv#022 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 7054.08 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2334 | 20200326-4 | 53520102 | Clearing | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 48 | HR | 9.16 | 0 |  |  | 586.08 | 76.1904 | 662.2704 | 2020-03-26 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Burning from A116, A120, A121 and A125 | 1 | A-128 to B-017 | Wolf Lake | 0 | 43933 |  | 40 | 43936 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting233420200326-4Excavator Thumb - 30 - 50 ton- After Jan 1048586.08 | Corbiere and Sons Contracting233420200326-4Excavator Thumb - 30 - 50 ton- After Jan 1048586.08Inv#022 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 586.08 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2334 | 20200326-4 | 53520102 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 6 | DAY | 182.81 | 0 |  |  | 1462.5 | 190.125 | 1652.625 | 2020-03-26 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Burning from A116, A120, A121 and A125 | 1 | A-128 to B-017 | Wolf Lake | 0 | 43933 |  | 40 | 43936 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting233420200326-4Light Truck - Pick up- After Jan 1061462.5 | Corbiere and Sons Contracting233420200326-4Light Truck - Pick up- After Jan 1061462.5Inv#022 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1462.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2334 | 20200326-4 | 53520102 | Clearing | 0 | L.O.A. | 210 | 12 | DAY |  |  |  | 0 | 2520 | 327.6 | 2847.6 | 2020-03-26 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Burning from A116, A120, A121 and A125 | 1 | A-128 to B-017 | Wolf Lake | 0 | 43933 |  | 40 | 43936 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting233420200326-4L.O.A.122520 | Corbiere and Sons Contracting233420200326-4L.O.A.122520Inv#022 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2520 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2334 | 20200326-4 | 53520102 | Clearing | 0 | Operator - Principle - After Jan 10 | 75 | 102 | HR |  |  | 75 | 0 | 7650 | 994.5 | 8644.5 | 2020-03-26 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Burning from A116, A120, A121 and A125 | 1 | A-128 to B-017 | Wolf Lake | 0 | 43933 |  | 40 | 43936 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting233420200326-4Operator - Principle - After Jan 101027650 | Corbiere and Sons Contracting233420200326-4Operator - Principle - After Jan 101027650Inv#022 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 7650 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2334 | 20200326-4 | 53520102 | Clearing | 0 | Labourer - General - After Jan 10 | 60 | 51 | HR |  |  | 60 | 0 | 3060 | 397.8 | 3457.8 | 2020-03-26 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Burning from A116, A120, A121 and A125 | 1 | A-128 to B-017 | Wolf Lake | 0 | 43933 |  | 40 | 43936 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting233420200326-4Labourer - General - After Jan 10513060 | Corbiere and Sons Contracting233420200326-4Labourer - General - After Jan 10513060Inv#022 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 3060 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2339 | 20200326-9 | 53510612 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 95.24 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2020-03-26 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grading of access roads across many segments - Neys Road, Santoy Lake - Prairie River | 6 | C129-C267 | WF6 | 0 | 43933 |  | 40 | 43936 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting233920200326-9Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting233920200326-9Grader - Cat 12 to 14 or equal- After Jan 10101269.8Inv#022 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2339 | 20200326-9 | 53510612 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-03-26 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grading of access roads across many segments - Neys Road, Santoy Lake - Prairie River | 6 | C129-C267 | WF6 | 0 | 43933 |  | 40 | 43936 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting233920200326-9Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting233920200326-9Light Truck - Pick up- After Jan 101243.75Inv#022 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2339 | 20200326-9 | 53510612 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-03-26 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grading of access roads across many segments - Neys Road, Santoy Lake - Prairie River | 6 | C129-C267 | WF6 | 0 | 43933 |  | 40 | 43936 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting233920200326-9L.O.A.1210 | Corbiere and Sons Contracting233920200326-9L.O.A.1210Inv#022 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2339 | 20200326-9 | 53510612 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2020-03-26 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grading of access roads across many segments - Neys Road, Santoy Lake - Prairie River | 6 | C129-C267 | WF6 | 0 | 43933 |  | 40 | 43936 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting233920200326-9Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting233920200326-9Operator - Principle - After Jan 1011825Inv#022 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2349 | 20200327-4 | 53520102 | Clearing | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 30 | Dynamic | 103.84 | 0 |  |  | 4153.5 | 539.955 | 4693.455 | 2020-03-27 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Burning at towers A117, A125, A128 and A129 | 1 | A-128 to B-017 | Wolf Lake | 0 | 43933 |  | 40 | 43936 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting234920200327-4Excavator - 30 ton- After Jan 10304153.5 | Corbiere and Sons Contracting234920200327-4Excavator - 30 ton- After Jan 10304153.5Inv#022 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 4153.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2349 | 20200327-4 | 53520102 | Clearing | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 48 | Dynamic | 110.22 | 0 |  |  | 7054.08 | 917.0304 | 7971.1104 | 2020-03-27 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Burning at towers A117, A125, A128 and A129 | 1 | A-128 to B-017 | Wolf Lake | 0 | 43933 |  | 40 | 43936 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting234920200327-4Excavator - 36 ton- After Jan 10487054.08 | Corbiere and Sons Contracting234920200327-4Excavator - 36 ton- After Jan 10487054.08Inv#022 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 7054.08 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2349 | 20200327-4 | 53520102 | Clearing | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 30 | HR | 9.16 | 0 |  |  | 366.3 | 47.619 | 413.919 | 2020-03-27 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Burning at towers A117, A125, A128 and A129 | 1 | A-128 to B-017 | Wolf Lake | 0 | 43933 |  | 40 | 43936 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting234920200327-4Excavator Thumb - 30 - 50 ton- After Jan 1030366.3 | Corbiere and Sons Contracting234920200327-4Excavator Thumb - 30 - 50 ton- After Jan 1030366.3Inv#022 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 366.3 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2349 | 20200327-4 | 53520102 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 6 | DAY | 182.81 | 0 |  |  | 1462.5 | 190.125 | 1652.625 | 2020-03-27 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Burning at towers A117, A125, A128 and A129 | 1 | A-128 to B-017 | Wolf Lake | 0 | 43933 |  | 40 | 43936 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting234920200327-4Light Truck - Pick up- After Jan 1061462.5 | Corbiere and Sons Contracting234920200327-4Light Truck - Pick up- After Jan 1061462.5Inv#022 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1462.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2349 | 20200327-4 | 53520102 | Clearing | 0 | L.O.A. | 210 | 11 | DAY |  |  |  | 0 | 2310 | 300.3 | 2610.3 | 2020-03-27 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Burning at towers A117, A125, A128 and A129 | 1 | A-128 to B-017 | Wolf Lake | 0 | 43933 |  | 40 | 43936 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting234920200327-4L.O.A.112310 | Corbiere and Sons Contracting234920200327-4L.O.A.112310Inv#022 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2310 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2349 | 20200327-4 | 53520102 | Clearing | 0 | Operator - Principle - After Jan 10 | 75 | 83.5 | HR |  |  | 75 | 0 | 6262.5 | 814.125 | 7076.625 | 2020-03-27 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Burning at towers A117, A125, A128 and A129 | 1 | A-128 to B-017 | Wolf Lake | 0 | 43933 |  | 40 | 43936 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting234920200327-4Operator - Principle - After Jan 1083.56262.5 | Corbiere and Sons Contracting234920200327-4Operator - Principle - After Jan 1083.56262.5Inv#022 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 6262.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2349 | 20200327-4 | 53520102 | Clearing | 0 | Labourer - General - After Jan 10 | 60 | 51 | HR |  |  | 60 | 0 | 3060 | 397.8 | 3457.8 | 2020-03-27 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Burning at towers A117, A125, A128 and A129 | 1 | A-128 to B-017 | Wolf Lake | 0 | 43933 |  | 40 | 43936 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting234920200327-4Labourer - General - After Jan 10513060 | Corbiere and Sons Contracting234920200327-4Labourer - General - After Jan 10513060Inv#022 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 3060 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2380 | 20200328-3 | 53520102 | Clearing | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 24 | Dynamic | 103.84 | 0 |  |  | 3322.8 | 431.964 | 3754.764 | 2020-03-28 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Burning at A128, A129, A135 and B002 | 1 | A-128 to B-017 | Wolf Lake | 0 | 43933 |  | 44 | 43937 | [5 empty] | Howard Beaudet | 01 | Corbiere and Sons Contracting238020200328-3Excavator - 30 ton- After Jan 10243322.8 | Corbiere and Sons Contracting238020200328-3Excavator - 30 ton- After Jan 10243322.8Inv#022 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 3322.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2380 | 20200328-3 | 53520102 | Clearing | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 48 | Dynamic | 110.22 | 0 |  |  | 7054.08 | 917.0304 | 7971.1104 | 2020-03-28 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Burning at A128, A129, A135 and B002 | 1 | A-128 to B-017 | Wolf Lake | 0 | 43933 |  | 44 | 43937 | [5 empty] | Howard Beaudet | 01 | Corbiere and Sons Contracting238020200328-3Excavator - 36 ton- After Jan 10487054.08 | Corbiere and Sons Contracting238020200328-3Excavator - 36 ton- After Jan 10487054.08Inv#022 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 7054.08 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2380 | 20200328-3 | 53520102 | Clearing | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 48 | HR | 9.16 | 0 |  |  | 586.08 | 76.1904 | 662.2704 | 2020-03-28 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Burning at A128, A129, A135 and B002 | 1 | A-128 to B-017 | Wolf Lake | 0 | 43933 |  | 44 | 43937 | [5 empty] | Howard Beaudet | 01 | Corbiere and Sons Contracting238020200328-3Excavator Thumb - 30 - 50 ton- After Jan 1048586.08 | Corbiere and Sons Contracting238020200328-3Excavator Thumb - 30 - 50 ton- After Jan 1048586.08Inv#022 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 586.08 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2380 | 20200328-3 | 53520102 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 6 | DAY | 182.81 | 0 |  |  | 1462.5 | 190.125 | 1652.625 | 2020-03-28 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Burning at A128, A129, A135 and B002 | 1 | A-128 to B-017 | Wolf Lake | 0 | 43933 |  | 44 | 43937 | [5 empty] | Howard Beaudet | 01 | Corbiere and Sons Contracting238020200328-3Light Truck - Pick up- After Jan 1061462.5 | Corbiere and Sons Contracting238020200328-3Light Truck - Pick up- After Jan 1061462.5Inv#022 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1462.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2380 | 20200328-3 | 53520102 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2020-03-28 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Burning at A128, A129, A135 and B002 | 1 | A-128 to B-017 | Wolf Lake | 0 | 43933 |  | 44 | 43937 | [5 empty] | Howard Beaudet | 01 | Corbiere and Sons Contracting238020200328-3Foreman121140 | Corbiere and Sons Contracting238020200328-3Foreman121140Inv#022 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2380 | 20200328-3 | 53520102 | Clearing | 0 | L.O.A. | 210 | 11 | DAY |  |  |  | 0 | 2310 | 300.3 | 2610.3 | 2020-03-28 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Burning at A128, A129, A135 and B002 | 1 | A-128 to B-017 | Wolf Lake | 0 | 43933 |  | 44 | 43937 | [5 empty] | Howard Beaudet | 01 | Corbiere and Sons Contracting238020200328-3L.O.A.112310 | Corbiere and Sons Contracting238020200328-3L.O.A.112310Inv#022 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2310 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2380 | 20200328-3 | 53520102 | Clearing | 0 | Operator - Principle - After Jan 10 | 75 | 76.5 | HR |  |  | 75 | 0 | 5737.5 | 745.875 | 6483.375 | 2020-03-28 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Burning at A128, A129, A135 and B002 | 1 | A-128 to B-017 | Wolf Lake | 0 | 43933 |  | 44 | 43937 | [5 empty] | Howard Beaudet | 01 | Corbiere and Sons Contracting238020200328-3Operator - Principle - After Jan 1076.55737.5 | Corbiere and Sons Contracting238020200328-3Operator - Principle - After Jan 1076.55737.5Inv#022 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 5737.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2380 | 20200328-3 | 53520102 | Clearing | 0 | Labourer - General - After Jan 10 | 60 | 51 | HR |  |  | 60 | 0 | 3060 | 397.8 | 3457.8 | 2020-03-28 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Burning at A128, A129, A135 and B002 | 1 | A-128 to B-017 | Wolf Lake | 0 | 43933 |  | 44 | 43937 | [5 empty] | Howard Beaudet | 01 | Corbiere and Sons Contracting238020200328-3Labourer - General - After Jan 10513060 | Corbiere and Sons Contracting238020200328-3Labourer - General - After Jan 10513060Inv#022 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 3060 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2359 | 20200329-3 | 53520102 | Clearing | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 24 | Dynamic | 103.84 | 0 |  |  | 3322.8 | 431.964 | 3754.764 | 2020-03-29 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Burning from A129, A132, A135 and B001 | 1 | A-128 to B-017 | Wolf Lake | 0 | 43933 |  | 44 | 43936 | [5 empty] | Howard Beaudet | 01 | Corbiere and Sons Contracting235920200329-3Excavator - 30 ton- After Jan 10243322.8 | Corbiere and Sons Contracting235920200329-3Excavator - 30 ton- After Jan 10243322.8Inv#022 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 3322.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2359 | 20200329-3 | 53520102 | Clearing | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 31 | Dynamic | 110.22 | 0 |  |  | 4555.76 | 592.2488 | 5148.0088 | 2020-03-29 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Burning from A129, A132, A135 and B001 | 1 | A-128 to B-017 | Wolf Lake | 0 | 43933 |  | 44 | 43936 | [5 empty] | Howard Beaudet | 01 | Corbiere and Sons Contracting235920200329-3Excavator - 36 ton- After Jan 10314555.76 | Corbiere and Sons Contracting235920200329-3Excavator - 36 ton- After Jan 10314555.76Inv#022 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 4555.76 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2359 | 20200329-3 | 53520102 | Clearing | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 42 | HR | 9.16 | 0 |  |  | 512.82 | 66.6666 | 579.4866 | 2020-03-29 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Burning from A129, A132, A135 and B001 | 1 | A-128 to B-017 | Wolf Lake | 0 | 43933 |  | 44 | 43936 | [5 empty] | Howard Beaudet | 01 | Corbiere and Sons Contracting235920200329-3Excavator Thumb - 30 - 50 ton- After Jan 1042512.82 | Corbiere and Sons Contracting235920200329-3Excavator Thumb - 30 - 50 ton- After Jan 1042512.82Inv#022 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 512.82 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2359 | 20200329-3 | 53520102 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 5 | DAY | 182.81 | 0 |  |  | 1218.75 | 158.4375 | 1377.1875 | 2020-03-29 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Burning from A129, A132, A135 and B001 | 1 | A-128 to B-017 | Wolf Lake | 0 | 43933 |  | 44 | 43936 | [5 empty] | Howard Beaudet | 01 | Corbiere and Sons Contracting235920200329-3Light Truck - Pick up- After Jan 1051218.75 | Corbiere and Sons Contracting235920200329-3Light Truck - Pick up- After Jan 1051218.75Inv#022 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1218.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2359 | 20200329-3 | 53520102 | Clearing | 0 | L.O.A. | 210 | 8 | DAY |  |  |  | 0 | 1680 | 218.4 | 1898.4 | 2020-03-29 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Burning from A129, A132, A135 and B001 | 1 | A-128 to B-017 | Wolf Lake | 0 | 43933 |  | 44 | 43936 | [5 empty] | Howard Beaudet | 01 | Corbiere and Sons Contracting235920200329-3L.O.A.81680 | Corbiere and Sons Contracting235920200329-3L.O.A.81680Inv#022 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1680 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2359 | 20200329-3 | 53520102 | Clearing | 0 | Operator - Principle - After Jan 10 | 75 | 58.5 | HR |  |  | 75 | 0 | 4387.5 | 570.375 | 4957.875 | 2020-03-29 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Burning from A129, A132, A135 and B001 | 1 | A-128 to B-017 | Wolf Lake | 0 | 43933 |  | 44 | 43936 | [5 empty] | Howard Beaudet | 01 | Corbiere and Sons Contracting235920200329-3Operator - Principle - After Jan 1058.54387.5 | Corbiere and Sons Contracting235920200329-3Operator - Principle - After Jan 1058.54387.5Inv#022 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 4387.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2359 | 20200329-3 | 53520102 | Clearing | 0 | Labourer - General - After Jan 10 | 60 | 39 | HR |  |  | 60 | 0 | 2340 | 304.2 | 2644.2 | 2020-03-29 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Burning from A129, A132, A135 and B001 | 1 | A-128 to B-017 | Wolf Lake | 0 | 43933 |  | 44 | 43936 | [5 empty] | Howard Beaudet | 01 | Corbiere and Sons Contracting235920200329-3Labourer - General - After Jan 10392340 | Corbiere and Sons Contracting235920200329-3Labourer - General - After Jan 10392340Inv#022 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2340 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2369 | 20200330-3 | 53520102 | Clearing | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 24 | Dynamic | 103.84 | 0 |  |  | 3322.8 | 431.964 | 3754.764 | 2020-03-30 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Burning at A129. A132, A135 and B001 | 1 | A-128 to B-017 | Wolf Lake | 0 | 43933 |  | 44 | 43936 | [5 empty] | Howard Beaudet | 01 | Corbiere and Sons Contracting236920200330-3Excavator - 30 ton- After Jan 10243322.8 | Corbiere and Sons Contracting236920200330-3Excavator - 30 ton- After Jan 10243322.8Inv#022 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 3322.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2369 | 20200330-3 | 53520102 | Clearing | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 30 | Dynamic | 110.22 | 0 |  |  | 4408.8 | 573.144 | 4981.944 | 2020-03-30 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Burning at A129. A132, A135 and B001 | 1 | A-128 to B-017 | Wolf Lake | 0 | 43933 |  | 44 | 43936 | [5 empty] | Howard Beaudet | 01 | Corbiere and Sons Contracting236920200330-3Excavator - 36 ton- After Jan 10304408.8 | Corbiere and Sons Contracting236920200330-3Excavator - 36 ton- After Jan 10304408.8Inv#022 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 4408.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2369 | 20200330-3 | 53520102 | Clearing | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 48 | HR | 9.16 | 0 |  |  | 586.08 | 76.1904 | 662.2704 | 2020-03-30 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Burning at A129. A132, A135 and B001 | 1 | A-128 to B-017 | Wolf Lake | 0 | 43933 |  | 44 | 43936 | [5 empty] | Howard Beaudet | 01 | Corbiere and Sons Contracting236920200330-3Excavator Thumb - 30 - 50 ton- After Jan 1048586.08 | Corbiere and Sons Contracting236920200330-3Excavator Thumb - 30 - 50 ton- After Jan 1048586.08Inv#022 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 586.08 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2369 | 20200330-3 | 53520102 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 5 | DAY | 182.81 | 0 |  |  | 1218.75 | 158.4375 | 1377.1875 | 2020-03-30 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Burning at A129. A132, A135 and B001 | 1 | A-128 to B-017 | Wolf Lake | 0 | 43933 |  | 44 | 43936 | [5 empty] | Howard Beaudet | 01 | Corbiere and Sons Contracting236920200330-3Light Truck - Pick up- After Jan 1051218.75 | Corbiere and Sons Contracting236920200330-3Light Truck - Pick up- After Jan 1051218.75Inv#022 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1218.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2369 | 20200330-3 | 53520102 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2020-03-30 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Burning at A129. A132, A135 and B001 | 1 | A-128 to B-017 | Wolf Lake | 0 | 43933 |  | 44 | 43936 | [5 empty] | Howard Beaudet | 01 | Corbiere and Sons Contracting236920200330-3Foreman121140 | Corbiere and Sons Contracting236920200330-3Foreman121140Inv#022 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2369 | 20200330-3 | 53520102 | Clearing | 0 | L.O.A. | 210 | 10 | DAY |  |  |  | 0 | 2100 | 273 | 2373 | 2020-03-30 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Burning at A129. A132, A135 and B001 | 1 | A-128 to B-017 | Wolf Lake | 0 | 43933 |  | 44 | 43936 | [5 empty] | Howard Beaudet | 01 | Corbiere and Sons Contracting236920200330-3L.O.A.102100 | Corbiere and Sons Contracting236920200330-3L.O.A.102100Inv#022 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2100 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2369 | 20200330-3 | 53520102 | Clearing | 0 | Operator - Principle - After Jan 10 | 75 | 63 | HR |  |  | 75 | 0 | 4725 | 614.25 | 5339.25 | 2020-03-30 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Burning at A129. A132, A135 and B001 | 1 | A-128 to B-017 | Wolf Lake | 0 | 43933 |  | 44 | 43936 | [5 empty] | Howard Beaudet | 01 | Corbiere and Sons Contracting236920200330-3Operator - Principle - After Jan 10634725 | Corbiere and Sons Contracting236920200330-3Operator - Principle - After Jan 10634725Inv#022 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 4725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2369 | 20200330-3 | 53520102 | Clearing | 0 | Labourer - General - After Jan 10 | 60 | 51 | HR |  |  | 60 | 0 | 3060 | 397.8 | 3457.8 | 2020-03-30 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Burning at A129. A132, A135 and B001 | 1 | A-128 to B-017 | Wolf Lake | 0 | 43933 |  | 44 | 43936 | [5 empty] | Howard Beaudet | 01 | Corbiere and Sons Contracting236920200330-3Labourer - General - After Jan 10513060 | Corbiere and Sons Contracting236920200330-3Labourer - General - After Jan 10513060Inv#022 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 3060 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2400 | 20200331-10 | 53510611 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 4 | Dynamic | 110.22 | 0 |  |  | 587.84 | 76.4192 | 664.2592 | 2020-03-31 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | General demob - cleaning of sand piles and tools | 6 | C129-C151 | Lake A | 0 | 43933 |  | 40 | 43937 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting240020200331-10Excavator - 36 ton- After Jan 104587.84 | Corbiere and Sons Contracting240020200331-10Excavator - 36 ton- After Jan 104587.84Inv#022 | [5 empty] | 1 | 587.84 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2400 | 20200331-10 | 53510611 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 4 | HR | 9.16 | 0 |  |  | 48.84 | 6.3492 | 55.1892 | 2020-03-31 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | General demob - cleaning of sand piles and tools | 6 | C129-C151 | Lake A | 0 | 43933 |  | 40 | 43937 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting240020200331-10Excavator Thumb - 30 - 50 ton- After Jan 10448.84 | Corbiere and Sons Contracting240020200331-10Excavator Thumb - 30 - 50 ton- After Jan 10448.84Inv#022 | [5 empty] | 1 | 48.84 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2400 | 20200331-10 | 53510611 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 4 | Dynamic | 41.4 | 0 |  |  | 220.8 | 28.704 | 249.504 | 2020-03-31 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | General demob - cleaning of sand piles and tools | 6 | C129-C151 | Lake A | 0 | 43933 |  | 40 | 43937 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting240020200331-10Dump - Triaxle- After Jan 104220.8 | Corbiere and Sons Contracting240020200331-10Dump - Triaxle- After Jan 104220.8Inv#022 | [5 empty] | 1 | 220.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2400 | 20200331-10 | 53510611 | Access | 0 | Foreman | 95 | 5 | HR |  |  | 95 | 0 | 475 | 61.75 | 536.75 | 2020-03-31 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | General demob - cleaning of sand piles and tools | 6 | C129-C151 | Lake A | 0 | 43933 |  | 40 | 43937 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting240020200331-10Foreman5475 | Corbiere and Sons Contracting240020200331-10Foreman5475Inv#022 | [5 empty] | 1 | 475 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2400 | 20200331-10 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 4 | HR |  |  | 75 | 0 | 300 | 39 | 339 | 2020-03-31 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | General demob - cleaning of sand piles and tools | 6 | C129-C151 | Lake A | 0 | 43933 |  | 40 | 43937 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting240020200331-10Operator - Principle - After Jan 104300 | Corbiere and Sons Contracting240020200331-10Operator - Principle - After Jan 104300Inv#022 | [5 empty] | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2400 | 20200331-10 | 53510611 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 4 | HR |  |  | 70 | 0 | 280 | 36.4 | 316.4 | 2020-03-31 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | General demob - cleaning of sand piles and tools | 6 | C129-C151 | Lake A | 0 | 43933 |  | 40 | 43937 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting240020200331-10Driver - AZ - After Jan 104280 | Corbiere and Sons Contracting240020200331-10Driver - AZ - After Jan 104280Inv#022 | [5 empty] | 1 | 280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2400 | 20200331-10 | 53510611 | Access | 0 | Labourer - General - After Jan 10 | 60 | 8 | HR |  |  | 60 | 0 | 480 | 62.4 | 542.4 | 2020-03-31 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | General demob - cleaning of sand piles and tools | 6 | C129-C151 | Lake A | 0 | 43933 |  | 40 | 43937 | [5 empty] | Dean MacArthur | 06 | Corbiere and Sons Contracting240020200331-10Labourer - General - After Jan 108480 | Corbiere and Sons Contracting240020200331-10Labourer - General - After Jan 108480Inv#022 | [5 empty] | 1 | 480 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2403 | 20200331-13 | 53510312 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 9 | Dynamic | 98.61 | 0 |  |  | 1183.32 | 153.8316 | 1337.1516 | 2020-03-31 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Clearing access into Gurney Lake Road | 3 | C186-C191 | Gurney Lake Road | 0 | 43933 |  | 40 | 43937 | [5 empty] | Dean MacArthur | 03 | Corbiere and Sons Contracting240320200331-13Dozer D6 or equal- After Jan 1091183.32 | Corbiere and Sons Contracting240320200331-13Dozer D6 or equal- After Jan 1091183.32Inv#022 | [5 empty] | 1 | 1183.32 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2403 | 20200331-13 | 53510312 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2020-03-31 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Clearing access into Gurney Lake Road | 3 | C186-C191 | Gurney Lake Road | 0 | 43933 |  | 40 | 43937 | [5 empty] | Dean MacArthur | 03 | Corbiere and Sons Contracting240320200331-13Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting240320200331-13Excavator - 36 ton- After Jan 1091322.64Inv#022 | [5 empty] | 1 | 1322.64 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2403 | 20200331-13 | 53510312 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2020-03-31 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Clearing access into Gurney Lake Road | 3 | C186-C191 | Gurney Lake Road | 0 | 43933 |  | 40 | 43937 | [5 empty] | Dean MacArthur | 03 | Corbiere and Sons Contracting240320200331-13Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting240320200331-13Excavator Thumb - 30 - 50 ton- After Jan 109109.89Inv#022 | [5 empty] | 1 | 109.89 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2403 | 20200331-13 | 53510312 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-03-31 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Clearing access into Gurney Lake Road | 3 | C186-C191 | Gurney Lake Road | 0 | 43933 |  | 40 | 43937 | [5 empty] | Dean MacArthur | 03 | Corbiere and Sons Contracting240320200331-13Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting240320200331-13Light Truck - Pick up- After Jan 102487.5Inv#022 | [5 empty] | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2403 | 20200331-13 | 53510312 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-03-31 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Clearing access into Gurney Lake Road | 3 | C186-C191 | Gurney Lake Road | 0 | 43933 |  | 40 | 43937 | [5 empty] | Dean MacArthur | 03 | Corbiere and Sons Contracting240320200331-13L.O.A.2420 | Corbiere and Sons Contracting240320200331-13L.O.A.2420Inv#022 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2403 | 20200331-13 | 53510312 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 22 | HR |  |  | 75 | 0 | 1650 | 214.5 | 1864.5 | 2020-03-31 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Clearing access into Gurney Lake Road | 3 | C186-C191 | Gurney Lake Road | 0 | 43933 |  | 40 | 43937 | [5 empty] | Dean MacArthur | 03 | Corbiere and Sons Contracting240320200331-13Operator - Principle - After Jan 10221650 | Corbiere and Sons Contracting240320200331-13Operator - Principle - After Jan 10221650Inv#022 | [5 empty] | 1 | 1650 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2393 | 20200331-3 | 53520102 | Clearing | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 4 | Dynamic | 110.22 | 0 |  |  | 587.84 | 76.4192 | 664.2592 | 2020-03-31 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Verification that all fires are out - Walking out of Equipment | 1 | A-128 to B-017 | Wolf Lake | 0 | 43933 |  | 40 | 43937 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting239320200331-3Excavator - 36 ton- After Jan 104587.84 | Corbiere and Sons Contracting239320200331-3Excavator - 36 ton- After Jan 104587.84Inv#022 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 587.84 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2393 | 20200331-3 | 53520102 | Clearing | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 2 | HR | 9.16 | 0 |  |  | 24.42 | 3.1746 | 27.5946 | 2020-03-31 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Verification that all fires are out - Walking out of Equipment | 1 | A-128 to B-017 | Wolf Lake | 0 | 43933 |  | 40 | 43937 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting239320200331-3Excavator Thumb - 30 - 50 ton- After Jan 10224.42 | Corbiere and Sons Contracting239320200331-3Excavator Thumb - 30 - 50 ton- After Jan 10224.42Inv#022 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 24.42 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2393 | 20200331-3 | 53520102 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-03-31 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Verification that all fires are out - Walking out of Equipment | 1 | A-128 to B-017 | Wolf Lake | 0 | 43933 |  | 40 | 43937 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting239320200331-3Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting239320200331-3Light Truck - Pick up- After Jan 102487.5Inv#022 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2393 | 20200331-3 | 53520102 | Clearing | 0 | Foreman | 95 | 6 | HR |  |  | 95 | 0 | 570 | 74.1 | 644.1 | 2020-03-31 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Verification that all fires are out - Walking out of Equipment | 1 | A-128 to B-017 | Wolf Lake | 0 | 43933 |  | 40 | 43937 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting239320200331-3Foreman6570 | Corbiere and Sons Contracting239320200331-3Foreman6570Inv#022 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 570 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2393 | 20200331-3 | 53520102 | Clearing | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2020-03-31 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Verification that all fires are out - Walking out of Equipment | 1 | A-128 to B-017 | Wolf Lake | 0 | 43933 |  | 40 | 43937 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting239320200331-3L.O.A.3630 | Corbiere and Sons Contracting239320200331-3L.O.A.3630Inv#022 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2393 | 20200331-3 | 53520102 | Clearing | 0 | Labourer - General - After Jan 10 | 60 | 24 | HR |  |  | 60 | 0 | 1440 | 187.2 | 1627.2 | 2020-03-31 | 1 | Inv#022 | 43938 | 89 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Verification that all fires are out - Walking out of Equipment | 1 | A-128 to B-017 | Wolf Lake | 0 | 43933 |  | 40 | 43937 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting239320200331-3Labourer - General - After Jan 10241440 | Corbiere and Sons Contracting239320200331-3Labourer - General - After Jan 10241440Inv#022 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1440 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2417 | 20200401-3 | 53520102 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-04-01 | 1 | INV#024 | 43953 | 90 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Labourers went out to ensure all burn piles were properly put out | 1 | A-128-B-017 | Wolf Lake | 0 | 43938 |  | 40 | 43944 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting241720200401-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting241720200401-3Light Truck - Pick up- After Jan 101243.75INV#024 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2417 | 20200401-3 | 53520102 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-04-01 | 1 | INV#024 | 43953 | 90 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Labourers went out to ensure all burn piles were properly put out | 1 | A-128-B-017 | Wolf Lake | 0 | 43938 |  | 40 | 43944 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting241720200401-3L.O.A.2420 | Corbiere and Sons Contracting241720200401-3L.O.A.2420INV#024 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2417 | 20200401-3 | 53520102 | Clearing | 0 | Labourer - General - After Jan 10 | 60 | 8 | HR |  |  | 60 | 0 | 480 | 62.4 | 542.4 | 2020-04-01 | 1 | INV#024 | 43953 | 90 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Labourers went out to ensure all burn piles were properly put out | 1 | A-128-B-017 | Wolf Lake | 0 | 43938 |  | 40 | 43944 | [5 empty] | Dean MacArthur | 01 | Corbiere and Sons Contracting241720200401-3Labourer - General - After Jan 108480 | Corbiere and Sons Contracting241720200401-3Labourer - General - After Jan 108480INV#024 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 480 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2445 | 20200402-12 | 53510312 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 5 | Dynamic | 98.61 | 0 |  |  | 657.4 | 85.462 | 742.862 | 2020-04-02 | 1 | INV#024 | 43953 | 90 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | All season access maintenance at Gurney Lake Road | 3 | B186-B191 | Gurney Lake Road | 0 | 43938 |  | 40 | 43944 | [5 empty] | Dean MacArthur | 03 | Corbiere and Sons Contracting244520200402-12Dozer D6 or equal- After Jan 105657.4 | Corbiere and Sons Contracting244520200402-12Dozer D6 or equal- After Jan 105657.4INV#024 | [5 empty] | 1 | 657.4 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2445 | 20200402-12 | 53510312 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 3 | Dynamic | 110.22 | 0 |  |  | 440.88 | 57.3144 | 498.1944 | 2020-04-02 | 1 | INV#024 | 43953 | 90 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | All season access maintenance at Gurney Lake Road | 3 | B186-B191 | Gurney Lake Road | 0 | 43938 |  | 40 | 43944 | [5 empty] | Dean MacArthur | 03 | Corbiere and Sons Contracting244520200402-12Excavator - 36 ton- After Jan 103440.88 | Corbiere and Sons Contracting244520200402-12Excavator - 36 ton- After Jan 103440.88INV#024 | [5 empty] | 1 | 440.88 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2445 | 20200402-12 | 53510312 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 3 | HR | 9.16 | 0 |  |  | 36.63 | 4.7619 | 41.3919 | 2020-04-02 | 1 | INV#024 | 43953 | 90 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | All season access maintenance at Gurney Lake Road | 3 | B186-B191 | Gurney Lake Road | 0 | 43938 |  | 40 | 43944 | [5 empty] | Dean MacArthur | 03 | Corbiere and Sons Contracting244520200402-12Excavator Thumb - 30 - 50 ton- After Jan 10336.63 | Corbiere and Sons Contracting244520200402-12Excavator Thumb - 30 - 50 ton- After Jan 10336.63INV#024 | [5 empty] | 1 | 36.63 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2445 | 20200402-12 | 53510312 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-04-02 | 1 | INV#024 | 43953 | 90 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | All season access maintenance at Gurney Lake Road | 3 | B186-B191 | Gurney Lake Road | 0 | 43938 |  | 40 | 43944 | [5 empty] | Dean MacArthur | 03 | Corbiere and Sons Contracting244520200402-12Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting244520200402-12Light Truck - Pick up- After Jan 101243.75INV#024 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2445 | 20200402-12 | 53510312 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-04-02 | 1 | INV#024 | 43953 | 90 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | All season access maintenance at Gurney Lake Road | 3 | B186-B191 | Gurney Lake Road | 0 | 43938 |  | 40 | 43944 | [5 empty] | Dean MacArthur | 03 | Corbiere and Sons Contracting244520200402-12L.O.A.2420 | Corbiere and Sons Contracting244520200402-12L.O.A.2420INV#024 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2445 | 20200402-12 | 53510312 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2020-04-02 | 1 | INV#024 | 43953 | 90 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | All season access maintenance at Gurney Lake Road | 3 | B186-B191 | Gurney Lake Road | 0 | 43938 |  | 40 | 43944 | [5 empty] | Dean MacArthur | 03 | Corbiere and Sons Contracting244520200402-12Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting244520200402-12Operator - Principle - After Jan 1012900INV#024 | [5 empty] | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2506 | 20200404-13 | 53510612 | Access | 0 | 3rd Party Charges | 1 | 908.15 | unit |  |  |  |  | 908.15 | 118.0595 | 1026.2095 | 2020-04-04 | 1 | INV#024 | 43953 | 90 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Sand for maintenance of access roads | 6 | C129-C267 | WF6 | 0 | 43938 |  | 40 | 43948 | 114407 | Sand for maintenance of access roads |  |  |  | Dean MacArthur | 06 | Corbiere and Sons Contracting250620200404-133rd Party Charges908.15908.15 | Corbiere and Sons Contracting250620200404-133rd Party Charges908.15908.15INV#024 | [5 empty] | 1 | 908.15 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2507 | 20200404-14 | 53510111 | Access | 0 | 3rd Party Charges | 1 | 4466 | unit |  |  |  |  | 4466 | 580.58 | 5046.58 | 2020-04-04 | 1 | INV#027 | 43973 | 91 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Charges for screen sand brought to Dorion Yard for maintenance of access roads | 1 |  | WF1 | 0 | 43938 |  | 40 | 43950 | C20191349 | Sand delivered for access Maintenance |  |  |  | Dean MacArthur | 01 | Corbiere and Sons Contracting250720200404-143rd Party Charges44664466 | Corbiere and Sons Contracting250720200404-143rd Party Charges44664466INV#027 | [5 empty] | 1 | 4466 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2511 | 20200404-17 | 53510611 | Access | 0 | 3rd Party Charges | 1 | 3744.7 | unit |  |  |  |  | 3744.7 | 486.811 | 4231.511 | 2020-04-04 | 1 | INV#027 | 43973 | 91 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | B Gravel, screened sand, and triaxle rental from 777628 Ontario LTD. (o/a NORCON). | 6 | C129-C267 |  | 0 | 43950 |  | 40 | 43972 | 18017 | Screened sand charges off norcon invoice 18017 |  |  |  | Dean MacArthur | 06 | Corbiere and Sons Contracting251120200404-173rd Party Charges3744.73744.7 | Corbiere and Sons Contracting251120200404-173rd Party Charges3744.73744.7INV#027 | [5 empty] | 1 | 3744.7 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2511 | 20200404-17 | 53510611 | Access | 0 | 3rd Party Charges | 1 | 165 | unit |  |  |  |  | 165 | 21.45 | 186.45 | 2020-04-04 | 1 | INV#027 | 43973 | 91 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | B Gravel, screened sand, and triaxle rental from 777628 Ontario LTD. (o/a NORCON). | 6 | C129-C267 |  | 0 | 43950 |  | 40 | 43972 | 18017 | Winter const. sand charges off norcon invoice 18017 |  |  |  | Dean MacArthur | 06 | Corbiere and Sons Contracting251120200404-173rd Party Charges165165 | Corbiere and Sons Contracting251120200404-173rd Party Charges165165INV#027 | [5 empty] | 1 | 165 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2565 | 20200514-3 | 53510112 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 9 | Dynamic | 95.24 | 0 |  |  | 1142.82 | 148.5666 | 1291.3866 | 2020-05-14 | 1 | INV#027 | 43973 | 91 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Mobilization of a grader into WF1 and then grading across Harold Road/Windfarm/Eldorado | 1 | A-085 to A-117 | Windfarm | 0 | 43968 |  | 37 | 43970 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting256520200514-3Grader - Cat 12 to 14 or equal- After Jan 1091142.82 | Corbiere and Sons Contracting256520200514-3Grader - Cat 12 to 14 or equal- After Jan 1091142.82INV#027 | [5 empty] | 1 | 1142.82 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2565 | 20200514-3 | 53510112 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-05-14 | 1 | INV#027 | 43973 | 91 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Mobilization of a grader into WF1 and then grading across Harold Road/Windfarm/Eldorado | 1 | A-085 to A-117 | Windfarm | 0 | 43968 |  | 37 | 43970 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting256520200514-3L.O.A.1210 | Corbiere and Sons Contracting256520200514-3L.O.A.1210INV#027 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2565 | 20200514-3 | 53510112 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 10 | HR |  |  | 75 |  | 750 | 97.5 | 847.5 | 2020-05-14 | 1 | INV#027 | 43973 | 91 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Mobilization of a grader into WF1 and then grading across Harold Road/Windfarm/Eldorado | 1 | A-085 to A-117 | Windfarm | 0 | 43968 |  | 37 | 43970 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting256520200514-3Operator - Principle - After Jan 1010750 | Corbiere and Sons Contracting256520200514-3Operator - Principle - After Jan 1010750INV#027 | [5 empty] | 1 | 750 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2572 | 20200515-5 | 53510112 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 6 | Dynamic | 95.24 | 0 |  |  | 761.88 | 99.0444 | 860.9244 | 2020-05-15 | 1 | INV#027 | 43973 | 91 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  | 9029 |  | Approved |  |  | Grading of access roads throughout windfarm area. 9029 RESTART OPERATIONS | 1 | A-085 to A-117 | Windfarm | 0 | 43969 |  | 37 | 43970 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting257220200515-5Grader - Cat 12 to 14 or equal- After Jan 106761.88 | Corbiere and Sons Contracting257220200515-5Grader - Cat 12 to 14 or equal- After Jan 106761.88INV#027 | [5 empty] | 1 | 761.88 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2572 | 20200515-5 | 53510112 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 7 | HR |  |  | 75 | 0 | 525 | 68.25 | 593.25 | 2020-05-15 | 1 | INV#027 | 43973 | 91 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  | 9029 |  | Approved |  |  | Grading of access roads throughout windfarm area. 9029 RESTART OPERATIONS | 1 | A-085 to A-117 | Windfarm | 0 | 43969 |  | 37 | 43970 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting257220200515-5Operator - Principle - After Jan 107525 | Corbiere and Sons Contracting257220200515-5Operator - Principle - After Jan 107525INV#027 | [5 empty] | 1 | 525 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3004 | 20200518-3 | 53510112 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 6 | Dynamic | 98.61 | 0 |  |  | 788.88 | 102.5544 | 891.4344 | 2020-05-18 | 1 | INV #31 | 43997 | 93 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Floating of EX006 into Ouimet Canyon and then Grading from A124; Road Repairs at A061; Rd. Building at A076; DZ working from A082-A083; Ex working from A124 | 1 | A-085 to A-117 | Windfarm | 0 | 43972 |  | 37 | 43972 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting300420200518-3Dozer D6 or equal- After Jan 106788.88 | Corbiere and Sons Contracting300420200518-3Dozer D6 or equal- After Jan 106788.88INV #31 | [5 empty] | 1 | 788.88 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3004 | 20200518-3 | 53510112 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 18 | Dynamic | 103.84 | 0 |  |  | 2492.1 | 323.973 | 2816.073 | 2020-05-18 | 1 | INV #31 | 43997 | 93 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Floating of EX006 into Ouimet Canyon and then Grading from A124; Road Repairs at A061; Rd. Building at A076; DZ working from A082-A083; Ex working from A124 | 1 | A-085 to A-117 | Windfarm | 0 | 43972 |  | 37 | 43972 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting300420200518-3Excavator - 30 ton- After Jan 10182492.1 | Corbiere and Sons Contracting300420200518-3Excavator - 30 ton- After Jan 10182492.1INV #31 | [5 empty] | 1 | 2492.1 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3004 | 20200518-3 | 53510112 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2020-05-18 | 1 | INV #31 | 43997 | 93 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Floating of EX006 into Ouimet Canyon and then Grading from A124; Road Repairs at A061; Rd. Building at A076; DZ working from A082-A083; Ex working from A124 | 1 | A-085 to A-117 | Windfarm | 0 | 43972 |  | 37 | 43972 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting300420200518-3Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting300420200518-3Excavator - 36 ton- After Jan 1091322.64INV #31 | [5 empty] | 1 | 1322.64 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3004 | 20200518-3 | 53510112 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 18 | HR | 9.16 | 0 |  |  | 219.78 | 28.5714 | 248.3514 | 2020-05-18 | 1 | INV #31 | 43997 | 93 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Floating of EX006 into Ouimet Canyon and then Grading from A124; Road Repairs at A061; Rd. Building at A076; DZ working from A082-A083; Ex working from A124 | 1 | A-085 to A-117 | Windfarm | 0 | 43972 |  | 37 | 43972 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting300420200518-3Excavator Thumb - 30 - 50 ton- After Jan 1018219.78 | Corbiere and Sons Contracting300420200518-3Excavator Thumb - 30 - 50 ton- After Jan 1018219.78INV #31 | [5 empty] | 1 | 219.78 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3004 | 20200518-3 | 53510112 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 8 | Dynamic | 95.24 | 0 |  |  | 1015.84 | 132.0592 | 1147.8992 | 2020-05-18 | 1 | INV #31 | 43997 | 93 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Floating of EX006 into Ouimet Canyon and then Grading from A124; Road Repairs at A061; Rd. Building at A076; DZ working from A082-A083; Ex working from A124 | 1 | A-085 to A-117 | Windfarm | 0 | 43972 |  | 37 | 43972 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting300420200518-3Grader - Cat 12 to 14 or equal- After Jan 1081015.84 | Corbiere and Sons Contracting300420200518-3Grader - Cat 12 to 14 or equal- After Jan 1081015.84INV #31 | [5 empty] | 1 | 1015.84 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3004 | 20200518-3 | 53510112 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2020-05-18 | 1 | INV #31 | 43997 | 93 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Floating of EX006 into Ouimet Canyon and then Grading from A124; Road Repairs at A061; Rd. Building at A076; DZ working from A082-A083; Ex working from A124 | 1 | A-085 to A-117 | Windfarm | 0 | 43972 |  | 37 | 43972 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting300420200518-3Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting300420200518-3Light Truck - Pick up- After Jan 103731.25INV #31 | [5 empty] | 1 | 731.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3004 | 20200518-3 | 53510112 | Access | 0 | Superintendent | 105 | 8 | HR |  |  | 105 | 0 | 840 | 109.2 | 949.2 | 2020-05-18 | 1 | INV #31 | 43997 | 93 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Floating of EX006 into Ouimet Canyon and then Grading from A124; Road Repairs at A061; Rd. Building at A076; DZ working from A082-A083; Ex working from A124 | 1 | A-085 to A-117 | Windfarm | 0 | 43972 |  | 37 | 43972 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting300420200518-3Superintendent8840 | Corbiere and Sons Contracting300420200518-3Superintendent8840INV #31 | [5 empty] | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3004 | 20200518-3 | 53510112 | Access | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2020-05-18 | 1 | INV #31 | 43997 | 93 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Floating of EX006 into Ouimet Canyon and then Grading from A124; Road Repairs at A061; Rd. Building at A076; DZ working from A082-A083; Ex working from A124 | 1 | A-085 to A-117 | Windfarm | 0 | 43972 |  | 37 | 43972 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting300420200518-3L.O.A.61260 | Corbiere and Sons Contracting300420200518-3L.O.A.61260INV #31 | [5 empty] | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3004 | 20200518-3 | 53510112 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 53 | HR |  |  | 75 | 0 | 3975 | 516.75 | 4491.75 | 2020-05-18 | 1 | INV #31 | 43997 | 93 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Floating of EX006 into Ouimet Canyon and then Grading from A124; Road Repairs at A061; Rd. Building at A076; DZ working from A082-A083; Ex working from A124 | 1 | A-085 to A-117 | Windfarm | 0 | 43972 |  | 37 | 43972 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting300420200518-3Operator - Principle - After Jan 10533975 | Corbiere and Sons Contracting300420200518-3Operator - Principle - After Jan 10533975INV #31 | [5 empty] | 1 | 3975 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2596 | 20200519-4 | 53510112 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 6 | Dynamic | 95.24 | 0 |  |  | 761.88 | 99.0444 | 860.9244 | 2020-05-19 | 1 | INV#30-R02 | 43993 | 92 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grading across Harold Road | 1 | A-085 to A-117 | Windfarm | 0 | 43973 |  | 37 | 43973 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting259620200519-4Grader - Cat 12 to 14 or equal- After Jan 106761.88 | Corbiere and Sons Contracting259620200519-4Grader - Cat 12 to 14 or equal- After Jan 106761.88INV#30-R02 | [5 empty] | 1 | 761.88 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2596 | 20200519-4 | 53510112 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-05-19 | 1 | INV#30-R02 | 43993 | 92 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grading across Harold Road | 1 | A-085 to A-117 | Windfarm | 0 | 43973 |  | 37 | 43973 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting259620200519-4L.O.A.1210 | Corbiere and Sons Contracting259620200519-4L.O.A.1210INV#30-R02 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2596 | 20200519-4 | 53510112 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 75 | 0 | 450 | 58.5 | 508.5 | 2020-05-19 | 1 | INV#30-R02 | 43993 | 92 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grading across Harold Road | 1 | A-085 to A-117 | Windfarm | 0 | 43973 |  | 37 | 43973 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting259620200519-4Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting259620200519-4Operator - Principle - After Jan 106450INV#30-R02 | [5 empty] | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2613 | 20200520-7 | 53510212 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 9.5 | Dynamic | 95.24 | 0 |  |  | 1206.31 | 156.8203 | 1363.1303 | 2020-05-20 | 1 | INV#30-R02 | 43993 | 92 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grading of access roads | 2 | B018 - B029 | Black Sturgeon | 0 | 43981 |  | 36 | 43982 | [5 empty] | Mike Lecocq | 02 | Corbiere and Sons Contracting261320200520-7Grader - Cat 12 to 14 or equal- After Jan 109.51206.31 | Corbiere and Sons Contracting261320200520-7Grader - Cat 12 to 14 or equal- After Jan 109.51206.31INV#30-R02 | [5 empty] | 1 | 1206.31 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2613 | 20200520-7 | 53510212 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-05-20 | 1 | INV#30-R02 | 43993 | 92 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grading of access roads | 2 | B018 - B029 | Black Sturgeon | 0 | 43981 |  | 36 | 43982 | [5 empty] | Mike Lecocq | 02 | Corbiere and Sons Contracting261320200520-7L.O.A.1210 | Corbiere and Sons Contracting261320200520-7L.O.A.1210INV#30-R02 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2613 | 20200520-7 | 53510212 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2020-05-20 | 1 | INV#30-R02 | 43993 | 92 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grading of access roads | 2 | B018 - B029 | Black Sturgeon | 0 | 43981 |  | 36 | 43982 | [5 empty] | Mike Lecocq | 02 | Corbiere and Sons Contracting261320200520-7Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting261320200520-7Operator - Principle - After Jan 1011825INV#30-R02 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2638 | 20200522-6 | 53510112 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 5 | Dynamic | 95.24 | 0 |  |  | 634.9 | 82.537 | 717.437 | 2020-05-22 | 1 | INV#30-R02 | 43993 | 92 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grading from B004 to B012 | 1 | A-128 to B-017 | Wolf Lake | 0 | 43981 |  | 37 | 43982 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting263820200522-6Grader - Cat 12 to 14 or equal- After Jan 105634.9 | Corbiere and Sons Contracting263820200522-6Grader - Cat 12 to 14 or equal- After Jan 105634.9INV#30-R02 | [5 empty] | 1 | 634.9 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2638 | 20200522-6 | 53510112 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 75 | 0 | 450 | 58.5 | 508.5 | 2020-05-22 | 1 | INV#30-R02 | 43993 | 92 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grading from B004 to B012 | 1 | A-128 to B-017 | Wolf Lake | 0 | 43981 |  | 37 | 43982 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting263820200522-6Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting263820200522-6Operator - Principle - After Jan 106450INV#30-R02 | [5 empty] | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2657 | 20200523-5 | 53510112 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9.5 | Dynamic | 110.22 | 0 |  |  | 1396.12 | 181.4956 | 1577.6156 | 2020-05-23 | 1 | INV#30-R02 | 43993 | 92 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF | [6 empty] | Fixing Road at A064 E | 1 | A-055 to A-084 | Eldorado | 0 | 43983 | [9 empty] | 01 | Corbiere and Sons Contracting265720200523-5Excavator - 36 ton- After Jan 109.51396.12 | Corbiere and Sons Contracting265720200523-5Excavator - 36 ton- After Jan 109.51396.12INV#30-R02 | [5 empty] | 1 | 1396.12 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2657 | 20200523-5 | 53510112 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-05-23 | 1 | INV#30-R02 | 43993 | 92 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF | [6 empty] | Fixing Road at A064 E | 1 | A-055 to A-084 | Eldorado | 0 | 43983 | [9 empty] | 01 | Corbiere and Sons Contracting265720200523-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting265720200523-5Light Truck - Pick up- After Jan 101243.75INV#30-R02 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2657 | 20200523-5 | 53510112 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-05-23 | 1 | INV#30-R02 | 43993 | 92 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF | [6 empty] | Fixing Road at A064 E | 1 | A-055 to A-084 | Eldorado | 0 | 43983 | [9 empty] | 01 | Corbiere and Sons Contracting265720200523-5L.O.A.1210 | Corbiere and Sons Contracting265720200523-5L.O.A.1210INV#30-R02 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2657 | 20200523-5 | 53510112 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-05-23 | 1 | INV#30-R02 | 43993 | 92 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF | [6 empty] | Fixing Road at A064 E | 1 | A-055 to A-084 | Eldorado | 0 | 43983 | [9 empty] | 01 | Corbiere and Sons Contracting265720200523-5Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting265720200523-5Operator - Principle - After Jan 1011.5862.5INV#30-R02 | [5 empty] | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2658 | 20200523-6 | 53510112 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9.5 | Dynamic | 110.22 | 0 |  |  | 1396.12 | 181.4956 | 1577.6156 | 2020-05-23 | 1 | INV#30-R02 | 43993 | 92 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF | [6 empty] | Fixing road at A114 and Grading across all access roads | 1 | A-085 to A-117 | Windfarm | 0 | 43983 | [9 empty] | 01 | Corbiere and Sons Contracting265820200523-6Excavator - 36 ton- After Jan 109.51396.12 | Corbiere and Sons Contracting265820200523-6Excavator - 36 ton- After Jan 109.51396.12INV#30-R02 | [5 empty] | 1 | 1396.12 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2658 | 20200523-6 | 53510112 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 9.5 | Dynamic | 95.24 | 0 |  |  | 1206.31 | 156.8203 | 1363.1303 | 2020-05-23 | 1 | INV#30-R02 | 43993 | 92 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF | [6 empty] | Fixing road at A114 and Grading across all access roads | 1 | A-085 to A-117 | Windfarm | 0 | 43983 | [9 empty] | 01 | Corbiere and Sons Contracting265820200523-6Grader - Cat 12 to 14 or equal- After Jan 109.51206.31 | Corbiere and Sons Contracting265820200523-6Grader - Cat 12 to 14 or equal- After Jan 109.51206.31INV#30-R02 | [5 empty] | 1 | 1206.31 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2658 | 20200523-6 | 53510112 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-05-23 | 1 | INV#30-R02 | 43993 | 92 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF | [6 empty] | Fixing road at A114 and Grading across all access roads | 1 | A-085 to A-117 | Windfarm | 0 | 43983 | [9 empty] | 01 | Corbiere and Sons Contracting265820200523-6Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting265820200523-6Light Truck - Pick up- After Jan 101243.75INV#30-R02 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2658 | 20200523-6 | 53510112 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-05-23 | 1 | INV#30-R02 | 43993 | 92 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF | [6 empty] | Fixing road at A114 and Grading across all access roads | 1 | A-085 to A-117 | Windfarm | 0 | 43983 | [9 empty] | 01 | Corbiere and Sons Contracting265820200523-6L.O.A.2420 | Corbiere and Sons Contracting265820200523-6L.O.A.2420INV#30-R02 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2658 | 20200523-6 | 53510112 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 23 | HR |  |  | 75 | 0 | 1725 | 224.25 | 1949.25 | 2020-05-23 | 1 | INV#30-R02 | 43993 | 92 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF | [6 empty] | Fixing road at A114 and Grading across all access roads | 1 | A-085 to A-117 | Windfarm | 0 | 43983 | [9 empty] | 01 | Corbiere and Sons Contracting265820200523-6Operator - Principle - After Jan 10231725 | Corbiere and Sons Contracting265820200523-6Operator - Principle - After Jan 10231725INV#30-R02 | [5 empty] | 1 | 1725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2674 | 20200525-5 | 53510112 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 7 | Dynamic | 95.24 | 0 |  |  | 888.86 | 115.5518 | 1004.4118 | 2020-05-25 | 1 | INV#30-R02 | 43993 | 92 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF | [6 empty] | Grader working across access roads | 1 | A-085 to A-117 | Windfarm | 0 | 43983 | [9 empty] | 01 | Corbiere and Sons Contracting267420200525-5Grader - Cat 12 to 14 or equal- After Jan 107888.86 | Corbiere and Sons Contracting267420200525-5Grader - Cat 12 to 14 or equal- After Jan 107888.86INV#30-R02 | [5 empty] | 1 | 888.86 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2674 | 20200525-5 | 53510112 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-05-25 | 1 | INV#30-R02 | 43993 | 92 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF | [6 empty] | Grader working across access roads | 1 | A-085 to A-117 | Windfarm | 0 | 43983 | [9 empty] | 01 | Corbiere and Sons Contracting267420200525-5L.O.A.1210 | Corbiere and Sons Contracting267420200525-5L.O.A.1210INV#30-R02 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2674 | 20200525-5 | 53510112 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 10.5 | HR |  |  | 75 | 0 | 787.5 | 102.375 | 889.875 | 2020-05-25 | 1 | INV#30-R02 | 43993 | 92 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF | [6 empty] | Grader working across access roads | 1 | A-085 to A-117 | Windfarm | 0 | 43983 | [9 empty] | 01 | Corbiere and Sons Contracting267420200525-5Operator - Principle - After Jan 1010.5787.5 | Corbiere and Sons Contracting267420200525-5Operator - Principle - After Jan 1010.5787.5INV#30-R02 | [5 empty] | 1 | 787.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2804 | 20200528-4 | 53510112 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 16 | Dynamic | 110.22 | 0 |  |  | 2351.36 | 305.6768 | 2657.0368 | 2020-05-28 | 1 | INV#30-R02 | 43993 | 92 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Repairs to Nash road at 2Km Mark; Fix road at A071; Fix Road at A064 E and redo after trucks drove over it; Grader working across all access roads | 1 | A-055 to A-084 | Eldorado | 0 | 43984 |  | 37 | 43986 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting280420200528-4Excavator - 36 ton- After Jan 10162351.36 | Corbiere and Sons Contracting280420200528-4Excavator - 36 ton- After Jan 10162351.36INV#30-R02 | [5 empty] | 1 | 2351.36 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2804 | 20200528-4 | 53510112 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 9.5 | Dynamic | 95.24 | 0 |  |  | 1206.31 | 156.8203 | 1363.1303 | 2020-05-28 | 1 | INV#30-R02 | 43993 | 92 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Repairs to Nash road at 2Km Mark; Fix road at A071; Fix Road at A064 E and redo after trucks drove over it; Grader working across all access roads | 1 | A-055 to A-084 | Eldorado | 0 | 43984 |  | 37 | 43986 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting280420200528-4Grader - Cat 12 to 14 or equal- After Jan 109.51206.31 | Corbiere and Sons Contracting280420200528-4Grader - Cat 12 to 14 or equal- After Jan 109.51206.31INV#30-R02 | [5 empty] | 1 | 1206.31 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2804 | 20200528-4 | 53510112 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-05-28 | 1 | INV#30-R02 | 43993 | 92 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Repairs to Nash road at 2Km Mark; Fix road at A071; Fix Road at A064 E and redo after trucks drove over it; Grader working across all access roads | 1 | A-055 to A-084 | Eldorado | 0 | 43984 |  | 37 | 43986 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting280420200528-4Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting280420200528-4Light Truck - Pick up- After Jan 102487.5INV#30-R02 | [5 empty] | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2804 | 20200528-4 | 53510112 | Access | 0 | Foreman | 95 | 6 | HR |  |  | 95 | 0 | 570 | 74.1 | 644.1 | 2020-05-28 | 1 | INV#30-R02 | 43993 | 92 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Repairs to Nash road at 2Km Mark; Fix road at A071; Fix Road at A064 E and redo after trucks drove over it; Grader working across all access roads | 1 | A-055 to A-084 | Eldorado | 0 | 43984 |  | 37 | 43986 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting280420200528-4Foreman6570 | Corbiere and Sons Contracting280420200528-4Foreman6570INV#30-R02 | [5 empty] | 1 | 570 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2804 | 20200528-4 | 53510112 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2020-05-28 | 1 | INV#30-R02 | 43993 | 92 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Repairs to Nash road at 2Km Mark; Fix road at A071; Fix Road at A064 E and redo after trucks drove over it; Grader working across all access roads | 1 | A-055 to A-084 | Eldorado | 0 | 43984 |  | 37 | 43986 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting280420200528-4L.O.A.4840 | Corbiere and Sons Contracting280420200528-4L.O.A.4840INV#30-R02 | [5 empty] | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2804 | 20200528-4 | 53510112 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 30.5 | HR |  |  | 75 | 0 | 2287.5 | 297.375 | 2584.875 | 2020-05-28 | 1 | INV#30-R02 | 43993 | 92 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Repairs to Nash road at 2Km Mark; Fix road at A071; Fix Road at A064 E and redo after trucks drove over it; Grader working across all access roads | 1 | A-055 to A-084 | Eldorado | 0 | 43984 |  | 37 | 43986 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting280420200528-4Operator - Principle - After Jan 1030.52287.5 | Corbiere and Sons Contracting280420200528-4Operator - Principle - After Jan 1030.52287.5INV#30-R02 | [5 empty] | 1 | 2287.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2712 | 20200528-5 | 53510112 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 7 | Dynamic | 103.84 | 0 |  |  | 969.15 | 125.9895 | 1095.1395 | 2020-05-28 | 1 | INV#30-R02 | 43993 | 92 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixing Road at A115 | 1 | A-085 to A-117 | Windfarm | 0 | 43985 |  | 37 | 43986 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting271220200528-5Excavator - 30 ton- After Jan 107969.15 | Corbiere and Sons Contracting271220200528-5Excavator - 30 ton- After Jan 107969.15INV#30-R02 | [5 empty] | 1 | 969.15 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2712 | 20200528-5 | 53510112 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-05-28 | 1 | INV#30-R02 | 43993 | 92 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixing Road at A115 | 1 | A-085 to A-117 | Windfarm | 0 | 43985 |  | 37 | 43986 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting271220200528-5L.O.A.1210 | Corbiere and Sons Contracting271220200528-5L.O.A.1210INV#30-R02 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2712 | 20200528-5 | 53510112 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 8 | HR |  |  | 75 | 0 | 600 | 78 | 678 | 2020-05-28 | 1 | INV#30-R02 | 43993 | 92 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixing Road at A115 | 1 | A-085 to A-117 | Windfarm | 0 | 43985 |  | 37 | 43986 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting271220200528-5Operator - Principle - After Jan 108600 | Corbiere and Sons Contracting271220200528-5Operator - Principle - After Jan 108600INV#30-R02 | [5 empty] | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2726 | 20200529-6 | 53510112 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 95.24 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2020-05-29 | 1 | INV #032 | 44000 | 94 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across the Harold and the Nash | 1 | A-055 to A-084 | Eldorado | 0 | 43985 |  | 37 | 43996 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting272620200529-6Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting272620200529-6Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #032 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2726 | 20200529-6 | 53510112 | Access | 0 | Foreman | 95 | 6 | HR |  |  | 95 | 0 | 570 | 74.1 | 644.1 | 2020-05-29 | 1 | INV #032 | 44000 | 94 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across the Harold and the Nash | 1 | A-055 to A-084 | Eldorado | 0 | 43985 |  | 37 | 43996 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting272620200529-6Foreman6570 | Corbiere and Sons Contracting272620200529-6Foreman6570INV #032 | [5 empty] | 1 | 570 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2726 | 20200529-6 | 53510112 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-05-29 | 1 | INV #032 | 44000 | 94 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across the Harold and the Nash | 1 | A-055 to A-084 | Eldorado | 0 | 43985 |  | 37 | 43996 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting272620200529-6L.O.A.1210 | Corbiere and Sons Contracting272620200529-6L.O.A.1210INV #032 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2726 | 20200529-6 | 53510112 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-05-29 | 1 | INV #032 | 44000 | 94 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across the Harold and the Nash | 1 | A-055 to A-084 | Eldorado | 0 | 43985 |  | 37 | 43996 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting272620200529-6Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting272620200529-6Operator - Principle - After Jan 1011.5862.5INV #032 | [5 empty] | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2728 | 20200529-8 | 53510112 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10 | Dynamic | 110.22 | 0 |  |  | 1469.6 | 191.048 | 1660.648 | 2020-05-29 | 1 | INV #032 | 44000 | 94 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building road from A127 | 1 | A-128 to B-017 | Wolf Lake | 0 | 43985 |  | 37 | 43996 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting272820200529-8Excavator - 36 ton- After Jan 10101469.6 | Corbiere and Sons Contracting272820200529-8Excavator - 36 ton- After Jan 10101469.6INV #032 | [5 empty] | 1 | 1469.6 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2728 | 20200529-8 | 53510112 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-05-29 | 1 | INV #032 | 44000 | 94 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building road from A127 | 1 | A-128 to B-017 | Wolf Lake | 0 | 43985 |  | 37 | 43996 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting272820200529-8Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting272820200529-8Light Truck - Pick up- After Jan 101243.75INV #032 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2728 | 20200529-8 | 53510112 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-05-29 | 1 | INV #032 | 44000 | 94 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building road from A127 | 1 | A-128 to B-017 | Wolf Lake | 0 | 43985 |  | 37 | 43996 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting272820200529-8L.O.A.1210 | Corbiere and Sons Contracting272820200529-8L.O.A.1210INV #032 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2728 | 20200529-8 | 53510112 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-05-29 | 1 | INV #032 | 44000 | 94 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building road from A127 | 1 | A-128 to B-017 | Wolf Lake | 0 | 43985 |  | 37 | 43996 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting272820200529-8Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting272820200529-8Operator - Principle - After Jan 1011.5862.5INV #032 | [5 empty] | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2743 | 20200530-7 | 53510112 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 95.24 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2020-05-30 | 1 | INV#30-R02 | 43993 | 92 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Innes Road; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43986 |  | 37 | 43988 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting274320200530-7Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting274320200530-7Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV#30-R02 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2743 | 20200530-7 | 53510112 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-05-30 | 1 | INV#30-R02 | 43993 | 92 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Innes Road; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43986 |  | 37 | 43988 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting274320200530-7L.O.A.1210 | Corbiere and Sons Contracting274320200530-7L.O.A.1210INV#30-R02 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2743 | 20200530-7 | 53510112 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-05-30 | 1 | INV#30-R02 | 43993 | 92 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Innes Road; | 1 | A-128 to B-017 | Wolf Lake | 0 | 43986 |  | 37 | 43988 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting274320200530-7Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting274320200530-7Operator - Principle - After Jan 1011.5862.5INV#30-R02 | [5 empty] | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2758 | 20200601-5 | 53510112 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 95.24 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2020-06-01 | 1 | INV#30-R02 | 43993 | 92 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Barry working with Grader across Wolf Lake and Fish Hatchery Road | 1 | A-128 to B-017 | Wolf Lake | 0 | 43986 |  | 37 | 43988 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting275820200601-5Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting275820200601-5Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV#30-R02 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2758 | 20200601-5 | 53510112 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-06-01 | 1 | INV#30-R02 | 43993 | 92 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Barry working with Grader across Wolf Lake and Fish Hatchery Road | 1 | A-128 to B-017 | Wolf Lake | 0 | 43986 |  | 37 | 43988 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting275820200601-5L.O.A.1210 | Corbiere and Sons Contracting275820200601-5L.O.A.1210INV#30-R02 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2758 | 20200601-5 | 53510112 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-06-01 | 1 | INV#30-R02 | 43993 | 92 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Barry working with Grader across Wolf Lake and Fish Hatchery Road | 1 | A-128 to B-017 | Wolf Lake | 0 | 43986 |  | 37 | 43988 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting275820200601-5Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting275820200601-5Operator - Principle - After Jan 1011.5862.5INV#30-R02 | [5 empty] | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2768 | 20200602-3 | 53510112 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 95.24 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2020-06-02 | 1 | INV#30-R02 | 43993 | 92 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader Working across Carvern Lake Road | 1 | A-085 to A-117 | Windfarm | 0 | 43986 |  | 37 | 43988 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting276820200602-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting276820200602-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV#30-R02 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2768 | 20200602-3 | 53510112 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-06-02 | 1 | INV#30-R02 | 43993 | 92 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader Working across Carvern Lake Road | 1 | A-085 to A-117 | Windfarm | 0 | 43986 |  | 37 | 43988 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting276820200602-3L.O.A.1210 | Corbiere and Sons Contracting276820200602-3L.O.A.1210INV#30-R02 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2768 | 20200602-3 | 53510112 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-06-02 | 1 | INV#30-R02 | 43993 | 92 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader Working across Carvern Lake Road | 1 | A-085 to A-117 | Windfarm | 0 | 43986 |  | 37 | 43988 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting276820200602-3Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting276820200602-3Operator - Principle - After Jan 1011.5862.5INV#30-R02 | [5 empty] | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2787 | 20200603-3 | 53510112 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 5.5 | Dynamic | 95.24 | 0 |  |  | 698.39 | 90.7907 | 789.1807 | 2020-06-03 | 1 | INV #31 | 43997 | 93 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grading across Innes Road | 1 | A-128 to B-017 | Wolf Lake | 0 | 43988 |  | 37 | 43995 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting278720200603-3Grader - Cat 12 to 14 or equal- After Jan 105.5698.39 | Corbiere and Sons Contracting278720200603-3Grader - Cat 12 to 14 or equal- After Jan 105.5698.39INV #31 | [5 empty] | 1 | 698.39 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2787 | 20200603-3 | 53510112 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-06-03 | 1 | INV #31 | 43997 | 93 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grading across Innes Road | 1 | A-128 to B-017 | Wolf Lake | 0 | 43988 |  | 37 | 43995 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting278720200603-3L.O.A.1210 | Corbiere and Sons Contracting278720200603-3L.O.A.1210INV #31 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2787 | 20200603-3 | 53510112 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6.5 | HR |  |  | 75 | 0 | 487.5 | 63.375 | 550.875 | 2020-06-03 | 1 | INV #31 | 43997 | 93 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grading across Innes Road | 1 | A-128 to B-017 | Wolf Lake | 0 | 43988 |  | 37 | 43995 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting278720200603-3Operator - Principle - After Jan 106.5487.5 | Corbiere and Sons Contracting278720200603-3Operator - Principle - After Jan 106.5487.5INV #31 | [5 empty] | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2811 | 20200604-3 | 53510112 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10 | Dynamic | 103.84 | 0 |  |  | 1384.5 | 179.985 | 1564.485 |  | 1 | INV #31 | 43997 | 93 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Repairing road at A063, A078-A079; Grader working across Harold Road | 1 | A-055 to A-084 | Eldorado | 0 | 43989 |  | 37 | 43992 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting281120200604-3Excavator - 30 ton- After Jan 10101384.5 | Corbiere and Sons Contracting281120200604-3Excavator - 30 ton- After Jan 10101384.5INV #31 | [5 empty] | 1 | 1384.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2811 | 20200604-3 | 53510112 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10 | Dynamic | 110.22 | 0 |  |  | 1469.6 | 191.048 | 1660.648 |  | 1 | INV #31 | 43997 | 93 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Repairing road at A063, A078-A079; Grader working across Harold Road | 1 | A-055 to A-084 | Eldorado | 0 | 43989 |  | 37 | 43992 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting281120200604-3Excavator - 36 ton- After Jan 10101469.6 | Corbiere and Sons Contracting281120200604-3Excavator - 36 ton- After Jan 10101469.6INV #31 | [5 empty] | 1 | 1469.6 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2811 | 20200604-3 | 53510112 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 20 | HR | 9.16 | 0 |  |  | 244.2 | 31.746 | 275.946 |  | 1 | INV #31 | 43997 | 93 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Repairing road at A063, A078-A079; Grader working across Harold Road | 1 | A-055 to A-084 | Eldorado | 0 | 43989 |  | 37 | 43992 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting281120200604-3Excavator Thumb - 30 - 50 ton- After Jan 1020244.2 | Corbiere and Sons Contracting281120200604-3Excavator Thumb - 30 - 50 ton- After Jan 1020244.2INV #31 | [5 empty] | 1 | 244.2 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2811 | 20200604-3 | 53510112 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 7 | Dynamic | 95.24 | 0 |  |  | 888.86 | 115.5518 | 1004.4118 |  | 1 | INV #31 | 43997 | 93 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Repairing road at A063, A078-A079; Grader working across Harold Road | 1 | A-055 to A-084 | Eldorado | 0 | 43989 |  | 37 | 43992 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting281120200604-3Grader - Cat 12 to 14 or equal- After Jan 107888.86 | Corbiere and Sons Contracting281120200604-3Grader - Cat 12 to 14 or equal- After Jan 107888.86INV #31 | [5 empty] | 1 | 888.86 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2811 | 20200604-3 | 53510112 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 |  | 1 | INV #31 | 43997 | 93 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Repairing road at A063, A078-A079; Grader working across Harold Road | 1 | A-055 to A-084 | Eldorado | 0 | 43989 |  | 37 | 43992 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting281120200604-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting281120200604-3Light Truck - Pick up- After Jan 101243.75INV #31 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2811 | 20200604-3 | 53510112 | Access | 0 | Foreman | 95 | 6 | HR |  |  | 95 | 0 | 570 | 74.1 | 644.1 |  | 1 | INV #31 | 43997 | 93 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Repairing road at A063, A078-A079; Grader working across Harold Road | 1 | A-055 to A-084 | Eldorado | 0 | 43989 |  | 37 | 43992 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting281120200604-3Foreman6570 | Corbiere and Sons Contracting281120200604-3Foreman6570INV #31 | [5 empty] | 1 | 570 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2811 | 20200604-3 | 53510112 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 |  | 1 | INV #31 | 43997 | 93 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Repairing road at A063, A078-A079; Grader working across Harold Road | 1 | A-055 to A-084 | Eldorado | 0 | 43989 |  | 37 | 43992 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting281120200604-3L.O.A.4840 | Corbiere and Sons Contracting281120200604-3L.O.A.4840INV #31 | [5 empty] | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2811 | 20200604-3 | 53510112 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 33 | HR |  |  | 75 | 0 | 2475 | 321.75 | 2796.75 |  | 1 | INV #31 | 43997 | 93 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Repairing road at A063, A078-A079; Grader working across Harold Road | 1 | A-055 to A-084 | Eldorado | 0 | 43989 |  | 37 | 43992 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting281120200604-3Operator - Principle - After Jan 10332475 | Corbiere and Sons Contracting281120200604-3Operator - Principle - After Jan 10332475INV #31 | [5 empty] | 1 | 2475 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2812 | 20200604-4 | 53510112 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10 | Dynamic | 110.22 | 0 |  |  | 1469.6 | 191.048 | 1660.648 | 2020-06-04 | 1 | INV #31 | 43997 | 93 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Terry Fixing road from A114-A115 | 1 | A-055 to A-084 | Eldorado | 0 | 43989 |  | 37 | 43992 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting281220200604-4Excavator - 36 ton- After Jan 10101469.6 | Corbiere and Sons Contracting281220200604-4Excavator - 36 ton- After Jan 10101469.6INV #31 | [5 empty] | 1 | 1469.6 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2812 | 20200604-4 | 53510112 | Access | 0 | Light Truck - 1 to 3 Ton- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-06-04 | 1 | INV #31 | 43997 | 93 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Terry Fixing road from A114-A115 | 1 | A-055 to A-084 | Eldorado | 0 | 43989 |  | 37 | 43992 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting281220200604-4Light Truck - 1 to 3 Ton- After Jan 101243.75 | Corbiere and Sons Contracting281220200604-4Light Truck - 1 to 3 Ton- After Jan 101243.75INV #31 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2812 | 20200604-4 | 53510112 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-06-04 | 1 | INV #31 | 43997 | 93 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Terry Fixing road from A114-A115 | 1 | A-055 to A-084 | Eldorado | 0 | 43989 |  | 37 | 43992 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting281220200604-4L.O.A.1210 | Corbiere and Sons Contracting281220200604-4L.O.A.1210INV #31 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2812 | 20200604-4 | 53510112 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-06-04 | 1 | INV #31 | 43997 | 93 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Terry Fixing road from A114-A115 | 1 | A-055 to A-084 | Eldorado | 0 | 43989 |  | 37 | 43992 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting281220200604-4Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting281220200604-4Operator - Principle - After Jan 1011.5862.5INV #31 | [5 empty] | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2826 | 20200605-3 | 53510112 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 8.5 | Dynamic | 95.24 | 0 |  |  | 1079.33 | 140.3129 | 1219.6429 | 2020-06-05 | 1 | INV #31 | 43997 | 93 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working acceoss Eldorado and Nash Road | 1 | A-055 to A-084 | Eldorado | 0 | 43990 |  | 37 | 43992 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting282620200605-3Grader - Cat 12 to 14 or equal- After Jan 108.51079.33 | Corbiere and Sons Contracting282620200605-3Grader - Cat 12 to 14 or equal- After Jan 108.51079.33INV #31 | [5 empty] | 1 | 1079.33 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2826 | 20200605-3 | 53510112 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-06-05 | 1 | INV #31 | 43997 | 93 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working acceoss Eldorado and Nash Road | 1 | A-055 to A-084 | Eldorado | 0 | 43990 |  | 37 | 43992 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting282620200605-3L.O.A.1210 | Corbiere and Sons Contracting282620200605-3L.O.A.1210INV #31 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2826 | 20200605-3 | 53510112 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 8.5 | HR |  |  | 75 | 0 | 637.5 | 82.875 | 720.375 | 2020-06-05 | 1 | INV #31 | 43997 | 93 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working acceoss Eldorado and Nash Road | 1 | A-055 to A-084 | Eldorado | 0 | 43990 |  | 37 | 43992 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting282620200605-3Operator - Principle - After Jan 108.5637.5 | Corbiere and Sons Contracting282620200605-3Operator - Principle - After Jan 108.5637.5INV #31 | [5 empty] | 1 | 637.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2839 | 20200606-3 | 53510112 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10 | Dynamic | 110.22 | 0 |  |  | 1469.6 | 191.048 | 1660.648 | 2020-06-06 | 1 | INV #31 | 43997 | 93 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF | [6 empty] | Maintenance of access road across Harold and from A066-A070; | 1 | A-055 to A-084 | Eldorado | 0 | 43990 | [9 empty] | 01 | Corbiere and Sons Contracting283920200606-3Excavator - 36 ton- After Jan 10101469.6 | Corbiere and Sons Contracting283920200606-3Excavator - 36 ton- After Jan 10101469.6INV #31 | [5 empty] | 1 | 1469.6 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2839 | 20200606-3 | 53510112 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 9.16 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2020-06-06 | 1 | INV #31 | 43997 | 93 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF | [6 empty] | Maintenance of access road across Harold and from A066-A070; | 1 | A-055 to A-084 | Eldorado | 0 | 43990 | [9 empty] | 01 | Corbiere and Sons Contracting283920200606-3Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting283920200606-3Excavator Thumb - 30 - 50 ton- After Jan 1010122.1INV #31 | [5 empty] | 1 | 122.1 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2839 | 20200606-3 | 53510112 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 3.5 | Dynamic | 95.24 | 0 |  |  | 444.43 | 57.7759 | 502.2059 | 2020-06-06 | 1 | INV #31 | 43997 | 93 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF | [6 empty] | Maintenance of access road across Harold and from A066-A070; | 1 | A-055 to A-084 | Eldorado | 0 | 43990 | [9 empty] | 01 | Corbiere and Sons Contracting283920200606-3Grader - Cat 12 to 14 or equal- After Jan 103.5444.43 | Corbiere and Sons Contracting283920200606-3Grader - Cat 12 to 14 or equal- After Jan 103.5444.43INV #31 | [5 empty] | 1 | 444.43 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2839 | 20200606-3 | 53510112 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-06-06 | 1 | INV #31 | 43997 | 93 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF | [6 empty] | Maintenance of access road across Harold and from A066-A070; | 1 | A-055 to A-084 | Eldorado | 0 | 43990 | [9 empty] | 01 | Corbiere and Sons Contracting283920200606-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting283920200606-3Light Truck - Pick up- After Jan 101243.75INV #31 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2839 | 20200606-3 | 53510112 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-06-06 | 1 | INV #31 | 43997 | 93 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF | [6 empty] | Maintenance of access road across Harold and from A066-A070; | 1 | A-055 to A-084 | Eldorado | 0 | 43990 | [9 empty] | 01 | Corbiere and Sons Contracting283920200606-3L.O.A.2420 | Corbiere and Sons Contracting283920200606-3L.O.A.2420INV #31 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2839 | 20200606-3 | 53510112 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 15.5 | HR |  |  | 75 | 0 | 1162.5 | 151.125 | 1313.625 | 2020-06-06 | 1 | INV #31 | 43997 | 93 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF | [6 empty] | Maintenance of access road across Harold and from A066-A070; | 1 | A-055 to A-084 | Eldorado | 0 | 43990 | [9 empty] | 01 | Corbiere and Sons Contracting283920200606-3Operator - Principle - After Jan 1015.51162.5 | Corbiere and Sons Contracting283920200606-3Operator - Principle - After Jan 1015.51162.5INV #31 | [5 empty] | 1 | 1162.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2852 | 20200607-2 | 53510112 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 7 | Dynamic | 110.22 | 0 |  |  | 1028.72 | 133.7336 | 1162.4536 | 2020-06-07 | 1 | INV #31 | 43997 | 93 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Repairs to road washout a A132 | 1 | A-128 to B-017 | Wolf Lake | 0 | 43993 |  | 37 | 43993 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting285220200607-2Excavator - 36 ton- After Jan 1071028.72 | Corbiere and Sons Contracting285220200607-2Excavator - 36 ton- After Jan 1071028.72INV #31 | [5 empty] | 1 | 1028.72 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2852 | 20200607-2 | 53510112 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 7 | HR | 9.16 | 0 |  |  | 85.47 | 11.1111 | 96.5811 | 2020-06-07 | 1 | INV #31 | 43997 | 93 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Repairs to road washout a A132 | 1 | A-128 to B-017 | Wolf Lake | 0 | 43993 |  | 37 | 43993 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting285220200607-2Excavator Thumb - 30 - 50 ton- After Jan 10785.47 | Corbiere and Sons Contracting285220200607-2Excavator Thumb - 30 - 50 ton- After Jan 10785.47INV #31 | [5 empty] | 1 | 85.47 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2852 | 20200607-2 | 53510112 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-06-07 | 1 | INV #31 | 43997 | 93 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Repairs to road washout a A132 | 1 | A-128 to B-017 | Wolf Lake | 0 | 43993 |  | 37 | 43993 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting285220200607-2Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting285220200607-2Light Truck - Pick up- After Jan 102487.5INV #31 | [5 empty] | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2852 | 20200607-2 | 53510112 | Access | 0 | Foreman | 95 | 5 | HR |  |  | 95 | 0 | 475 | 61.75 | 536.75 | 2020-06-07 | 1 | INV #31 | 43997 | 93 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Repairs to road washout a A132 | 1 | A-128 to B-017 | Wolf Lake | 0 | 43993 |  | 37 | 43993 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting285220200607-2Foreman5475 | Corbiere and Sons Contracting285220200607-2Foreman5475INV #31 | [5 empty] | 1 | 475 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2852 | 20200607-2 | 53510112 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-06-07 | 1 | INV #31 | 43997 | 93 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Repairs to road washout a A132 | 1 | A-128 to B-017 | Wolf Lake | 0 | 43993 |  | 37 | 43993 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting285220200607-2L.O.A.2420 | Corbiere and Sons Contracting285220200607-2L.O.A.2420INV #31 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2852 | 20200607-2 | 53510112 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 7 | HR |  |  | 75 | 0 | 525 | 68.25 | 593.25 | 2020-06-07 | 1 | INV #31 | 43997 | 93 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Repairs to road washout a A132 | 1 | A-128 to B-017 | Wolf Lake | 0 | 43993 |  | 37 | 43993 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting285220200607-2Operator - Principle - After Jan 107525 | Corbiere and Sons Contracting285220200607-2Operator - Principle - After Jan 107525INV #31 | [5 empty] | 1 | 525 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2854 | 20200607-4 | 53510112 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 1 | Dynamic | 103.84 | 0 |  |  | 138.45 | 17.9985 | 156.4485 | 2020-06-07 | 1 | INV #31 | 43997 | 93 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Maintenance of access road from A132 - 2-4'' riverstone delivered - Invoice to follow at later date | 1 | A-128 to B-017 | Wolf Lake | 0 | 43993 |  | 37 | 43993 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting285420200607-4Excavator - 30 ton- After Jan 101138.45 | Corbiere and Sons Contracting285420200607-4Excavator - 30 ton- After Jan 101138.45INV #31 | [5 empty] | 1 | 138.45 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2854 | 20200607-4 | 53510112 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 1 | HR | 9.16 | 0 |  |  | 12.21 | 1.5873 | 13.7973 | 2020-06-07 | 1 | INV #31 | 43997 | 93 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Maintenance of access road from A132 - 2-4'' riverstone delivered - Invoice to follow at later date | 1 | A-128 to B-017 | Wolf Lake | 0 | 43993 |  | 37 | 43993 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting285420200607-4Excavator Thumb - 30 - 50 ton- After Jan 10112.21 | Corbiere and Sons Contracting285420200607-4Excavator Thumb - 30 - 50 ton- After Jan 10112.21INV #31 | [5 empty] | 1 | 12.21 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2854 | 20200607-4 | 53510112 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 2 | Dynamic | 41.4 | 0 |  |  | 110.4 | 14.352 | 124.752 | 2020-06-07 | 1 | INV #31 | 43997 | 93 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Maintenance of access road from A132 - 2-4'' riverstone delivered - Invoice to follow at later date | 1 | A-128 to B-017 | Wolf Lake | 0 | 43993 |  | 37 | 43993 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting285420200607-4Dump - Triaxle- After Jan 102110.4 | Corbiere and Sons Contracting285420200607-4Dump - Triaxle- After Jan 102110.4INV #31 | [5 empty] | 1 | 110.4 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2854 | 20200607-4 | 53510112 | Access | 0 | Foreman | 95 | 1 | HR |  |  | 95 | 0 | 95 | 12.35 | 107.35 | 2020-06-07 | 1 | INV #31 | 43997 | 93 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Maintenance of access road from A132 - 2-4'' riverstone delivered - Invoice to follow at later date | 1 | A-128 to B-017 | Wolf Lake | 0 | 43993 |  | 37 | 43993 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting285420200607-4Foreman195 | Corbiere and Sons Contracting285420200607-4Foreman195INV #31 | [5 empty] | 1 | 95 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2854 | 20200607-4 | 53510112 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-06-07 | 1 | INV #31 | 43997 | 93 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Maintenance of access road from A132 - 2-4'' riverstone delivered - Invoice to follow at later date | 1 | A-128 to B-017 | Wolf Lake | 0 | 43993 |  | 37 | 43993 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting285420200607-4L.O.A.1210 | Corbiere and Sons Contracting285420200607-4L.O.A.1210INV #31 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2854 | 20200607-4 | 53510112 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 1 | HR |  |  | 75 | 0 | 75 | 9.75 | 84.75 | 2020-06-07 | 1 | INV #31 | 43997 | 93 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Maintenance of access road from A132 - 2-4'' riverstone delivered - Invoice to follow at later date | 1 | A-128 to B-017 | Wolf Lake | 0 | 43993 |  | 37 | 43993 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting285420200607-4Operator - Principle - After Jan 10175 | Corbiere and Sons Contracting285420200607-4Operator - Principle - After Jan 10175INV #31 | [5 empty] | 1 | 75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2854 | 20200607-4 | 53510112 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 2 | HR |  |  | 70 | 0 | 140 | 18.2 | 158.2 | 2020-06-07 | 1 | INV #31 | 43997 | 93 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Maintenance of access road from A132 - 2-4'' riverstone delivered - Invoice to follow at later date | 1 | A-128 to B-017 | Wolf Lake | 0 | 43993 |  | 37 | 43993 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting285420200607-4Driver - AZ - After Jan 102140 | Corbiere and Sons Contracting285420200607-4Driver - AZ - After Jan 102140INV #31 | [5 empty] | 1 | 140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2888 | 20200608-6 | 53510112 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10 | Dynamic | 98.61 | 0 |  |  | 1314.8 | 170.924 | 1485.724 | 2020-06-08 | 1 | INV #032 | 44000 | 94 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | vMike and greg fixing road at A068-A069; Grader working across the Nash and Harold; | 1 | A-055 to A-084 | Eldorado | 0 | 43993 |  | 37 | 43996 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting288820200608-6Dozer D6 or equal- After Jan 10101314.8 | Corbiere and Sons Contracting288820200608-6Dozer D6 or equal- After Jan 10101314.8INV #032 | [5 empty] | 1 | 1314.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2888 | 20200608-6 | 53510112 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10 | Dynamic | 110.22 | 0 |  |  | 1469.6 | 191.048 | 1660.648 | 2020-06-08 | 1 | INV #032 | 44000 | 94 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | vMike and greg fixing road at A068-A069; Grader working across the Nash and Harold; | 1 | A-055 to A-084 | Eldorado | 0 | 43993 |  | 37 | 43996 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting288820200608-6Excavator - 36 ton- After Jan 10101469.6 | Corbiere and Sons Contracting288820200608-6Excavator - 36 ton- After Jan 10101469.6INV #032 | [5 empty] | 1 | 1469.6 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2888 | 20200608-6 | 53510112 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 9.16 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2020-06-08 | 1 | INV #032 | 44000 | 94 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | vMike and greg fixing road at A068-A069; Grader working across the Nash and Harold; | 1 | A-055 to A-084 | Eldorado | 0 | 43993 |  | 37 | 43996 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting288820200608-6Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting288820200608-6Excavator Thumb - 30 - 50 ton- After Jan 1010122.1INV #032 | [5 empty] | 1 | 122.1 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2888 | 20200608-6 | 53510112 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 5 | Dynamic | 95.24 | 0 |  |  | 634.9 | 82.537 | 717.437 | 2020-06-08 | 1 | INV #032 | 44000 | 94 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | vMike and greg fixing road at A068-A069; Grader working across the Nash and Harold; | 1 | A-055 to A-084 | Eldorado | 0 | 43993 |  | 37 | 43996 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting288820200608-6Grader - Cat 12 to 14 or equal- After Jan 105634.9 | Corbiere and Sons Contracting288820200608-6Grader - Cat 12 to 14 or equal- After Jan 105634.9INV #032 | [5 empty] | 1 | 634.9 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2888 | 20200608-6 | 53510112 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-06-08 | 1 | INV #032 | 44000 | 94 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | vMike and greg fixing road at A068-A069; Grader working across the Nash and Harold; | 1 | A-055 to A-084 | Eldorado | 0 | 43993 |  | 37 | 43996 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting288820200608-6Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting288820200608-6Light Truck - Pick up- After Jan 102487.5INV #032 | [5 empty] | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2888 | 20200608-6 | 53510112 | Access | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2020-06-08 | 1 | INV #032 | 44000 | 94 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | vMike and greg fixing road at A068-A069; Grader working across the Nash and Harold; | 1 | A-055 to A-084 | Eldorado | 0 | 43993 |  | 37 | 43996 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting288820200608-6Foreman121140 | Corbiere and Sons Contracting288820200608-6Foreman121140INV #032 | [5 empty] | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2888 | 20200608-6 | 53510112 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2020-06-08 | 1 | INV #032 | 44000 | 94 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | vMike and greg fixing road at A068-A069; Grader working across the Nash and Harold; | 1 | A-055 to A-084 | Eldorado | 0 | 43993 |  | 37 | 43996 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting288820200608-6L.O.A.4840 | Corbiere and Sons Contracting288820200608-6L.O.A.4840INV #032 | [5 empty] | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2888 | 20200608-6 | 53510112 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 29 | HR |  |  | 75 | 0 | 2175 | 282.75 | 2457.75 | 2020-06-08 | 1 | INV #032 | 44000 | 94 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | vMike and greg fixing road at A068-A069; Grader working across the Nash and Harold; | 1 | A-055 to A-084 | Eldorado | 0 | 43993 |  | 37 | 43996 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting288820200608-6Operator - Principle - After Jan 10292175 | Corbiere and Sons Contracting288820200608-6Operator - Principle - After Jan 10292175INV #032 | [5 empty] | 1 | 2175 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2889 | 20200608-7 | 53510112 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 8 | Dynamic | 103.84 | 0 |  |  | 1107.6 | 143.988 | 1251.588 | 2020-06-08 | 1 | INV #032 | 44000 | 94 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Cole and EX009 building road from A093-A094; Aaron and EX005 working from A085; | 1 | A-085 to A-117 | Windfarm | 0 | 43993 |  | 37 | 43996 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting288920200608-7Excavator - 30 ton- After Jan 1081107.6 | Corbiere and Sons Contracting288920200608-7Excavator - 30 ton- After Jan 1081107.6INV #032 | [5 empty] | 1 | 1107.6 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2889 | 20200608-7 | 53510112 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10 | Dynamic | 110.22 | 0 |  |  | 1469.6 | 191.048 | 1660.648 | 2020-06-08 | 1 | INV #032 | 44000 | 94 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Cole and EX009 building road from A093-A094; Aaron and EX005 working from A085; | 1 | A-085 to A-117 | Windfarm | 0 | 43993 |  | 37 | 43996 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting288920200608-7Excavator - 36 ton- After Jan 10101469.6 | Corbiere and Sons Contracting288920200608-7Excavator - 36 ton- After Jan 10101469.6INV #032 | [5 empty] | 1 | 1469.6 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2889 | 20200608-7 | 53510112 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-06-08 | 1 | INV #032 | 44000 | 94 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Cole and EX009 building road from A093-A094; Aaron and EX005 working from A085; | 1 | A-085 to A-117 | Windfarm | 0 | 43993 |  | 37 | 43996 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting288920200608-7Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting288920200608-7Light Truck - Pick up- After Jan 101243.75INV #032 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2889 | 20200608-7 | 53510112 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-06-08 | 1 | INV #032 | 44000 | 94 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Cole and EX009 building road from A093-A094; Aaron and EX005 working from A085; | 1 | A-085 to A-117 | Windfarm | 0 | 43993 |  | 37 | 43996 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting288920200608-7L.O.A.1210 | Corbiere and Sons Contracting288920200608-7L.O.A.1210INV #032 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2889 | 20200608-7 | 53510112 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 21 | HR |  |  | 75 | 0 | 1575 | 204.75 | 1779.75 | 2020-06-08 | 1 | INV #032 | 44000 | 94 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Cole and EX009 building road from A093-A094; Aaron and EX005 working from A085; | 1 | A-085 to A-117 | Windfarm | 0 | 43993 |  | 37 | 43996 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting288920200608-7Operator - Principle - After Jan 10211575 | Corbiere and Sons Contracting288920200608-7Operator - Principle - After Jan 10211575INV #032 | [5 empty] | 1 | 1575 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2902 | 20200609-3 | 53510112 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9.5 | Dynamic | 103.84 | 0 |  |  | 1315.275 | 170.9857 | 1486.2607 | 2020-06-09 | 1 | INV #032 | 44000 | 94 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixing road from A085 | 1 | A-085 to A-117 | Windfarm | 0 | 43994 |  | 37 | 43996 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting290220200609-3Excavator - 30 ton- After Jan 109.51315.275 | Corbiere and Sons Contracting290220200609-3Excavator - 30 ton- After Jan 109.51315.275INV #032 | [5 empty] | 1 | 1315.275 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2902 | 20200609-3 | 53510112 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9.5 | HR | 9.16 | 0 |  |  | 115.995 | 15.0793 | 131.0744 | 2020-06-09 | 1 | INV #032 | 44000 | 94 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixing road from A085 | 1 | A-085 to A-117 | Windfarm | 0 | 43994 |  | 37 | 43996 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting290220200609-3Excavator Thumb - 30 - 50 ton- After Jan 109.5115.995 | Corbiere and Sons Contracting290220200609-3Excavator Thumb - 30 - 50 ton- After Jan 109.5115.995INV #032 | [5 empty] | 1 | 115.995 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2902 | 20200609-3 | 53510112 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-06-09 | 1 | INV #032 | 44000 | 94 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixing road from A085 | 1 | A-085 to A-117 | Windfarm | 0 | 43994 |  | 37 | 43996 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting290220200609-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting290220200609-3Light Truck - Pick up- After Jan 101243.75INV #032 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2902 | 20200609-3 | 53510112 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-06-09 | 1 | INV #032 | 44000 | 94 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixing road from A085 | 1 | A-085 to A-117 | Windfarm | 0 | 43994 |  | 37 | 43996 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting290220200609-3L.O.A.1210 | Corbiere and Sons Contracting290220200609-3L.O.A.1210INV #032 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2902 | 20200609-3 | 53510112 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-06-09 | 1 | INV #032 | 44000 | 94 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixing road from A085 | 1 | A-085 to A-117 | Windfarm | 0 | 43994 |  | 37 | 43996 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting290220200609-3Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting290220200609-3Operator - Principle - After Jan 1011.5862.5INV #032 | [5 empty] | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2930 | 20200611-4 | 53510112 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 8 | Dynamic | 95.24 | 0 |  |  | 1015.84 | 132.0592 | 1147.8992 | 2020-06-11 | 1 | INV #032 | 44000 | 94 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Nash Road | 1 | A-055 to A-084 | Eldorado | 0 | 43998 |  | 37 | 43998 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting293020200611-4Grader - Cat 12 to 14 or equal- After Jan 1081015.84 | Corbiere and Sons Contracting293020200611-4Grader - Cat 12 to 14 or equal- After Jan 1081015.84INV #032 | [5 empty] | 1 | 1015.84 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2930 | 20200611-4 | 53510112 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-06-11 | 1 | INV #032 | 44000 | 94 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Nash Road | 1 | A-055 to A-084 | Eldorado | 0 | 43998 |  | 37 | 43998 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting293020200611-4L.O.A.1210 | Corbiere and Sons Contracting293020200611-4L.O.A.1210INV #032 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2930 | 20200611-4 | 53510112 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 10 | HR |  |  | 75 | 0 | 750 | 97.5 | 847.5 | 2020-06-11 | 1 | INV #032 | 44000 | 94 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Nash Road | 1 | A-055 to A-084 | Eldorado | 0 | 43998 |  | 37 | 43998 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting293020200611-4Operator - Principle - After Jan 1010750 | Corbiere and Sons Contracting293020200611-4Operator - Principle - After Jan 1010750INV #032 | [5 empty] | 1 | 750 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2937 | 20200612-4 | 53510112 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10 | Dynamic | 98.61 | 0 |  |  | 1314.8 | 170.924 | 1485.724 | 2020-06-12 | 1 | INV #032 | 44000 | 94 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | DZ and grader doing maintenance from A071-A061; | 1 | A-055 to A-084 | Eldorado | 0 | 43998 |  | 37 | 43998 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting293720200612-4Dozer D6 or equal- After Jan 10101314.8 | Corbiere and Sons Contracting293720200612-4Dozer D6 or equal- After Jan 10101314.8INV #032 | [5 empty] | 1 | 1314.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2937 | 20200612-4 | 53510112 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 95.24 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2020-06-12 | 1 | INV #032 | 44000 | 94 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | DZ and grader doing maintenance from A071-A061; | 1 | A-055 to A-084 | Eldorado | 0 | 43998 |  | 37 | 43998 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting293720200612-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting293720200612-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #032 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2937 | 20200612-4 | 53510112 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-06-12 | 1 | INV #032 | 44000 | 94 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | DZ and grader doing maintenance from A071-A061; | 1 | A-055 to A-084 | Eldorado | 0 | 43998 |  | 37 | 43998 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting293720200612-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting293720200612-4Light Truck - Pick up- After Jan 101243.75INV #032 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2937 | 20200612-4 | 53510112 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-06-12 | 1 | INV #032 | 44000 | 94 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | DZ and grader doing maintenance from A071-A061; | 1 | A-055 to A-084 | Eldorado | 0 | 43998 |  | 37 | 43998 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting293720200612-4L.O.A.2420 | Corbiere and Sons Contracting293720200612-4L.O.A.2420INV #032 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2937 | 20200612-4 | 53510112 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 23 | HR |  |  | 75 | 0 | 1725 | 224.25 | 1949.25 | 2020-06-12 | 1 | INV #032 | 44000 | 94 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | DZ and grader doing maintenance from A071-A061; | 1 | A-055 to A-084 | Eldorado | 0 | 43998 |  | 37 | 43998 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting293720200612-4Operator - Principle - After Jan 10231725 | Corbiere and Sons Contracting293720200612-4Operator - Principle - After Jan 10231725INV #032 | [5 empty] | 1 | 1725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2952 | 20200613-3 | 53510112 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 95.24 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2020-06-13 | 1 | INV #032 | 44000 | 94 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across the Harold and the Nash | 1 | A-055 to A-084 | Eldorado | 0 | 43998 |  | 37 | 43998 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting295220200613-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting295220200613-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #032 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2952 | 20200613-3 | 53510112 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-06-13 | 1 | INV #032 | 44000 | 94 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across the Harold and the Nash | 1 | A-055 to A-084 | Eldorado | 0 | 43998 |  | 37 | 43998 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting295220200613-3L.O.A.1210 | Corbiere and Sons Contracting295220200613-3L.O.A.1210INV #032 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2952 | 20200613-3 | 53510112 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-06-13 | 1 | INV #032 | 44000 | 94 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across the Harold and the Nash | 1 | A-055 to A-084 | Eldorado | 0 | 43998 |  | 37 | 43998 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting295220200613-3Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting295220200613-3Operator - Principle - After Jan 1011.5862.5INV #032 | [5 empty] | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2968 | 20200614-4 | 53510112 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 20 | Dynamic | 110.22 | 0 |  |  | 2939.2 | 382.096 | 3321.296 | 2020-06-14 | 1 | INV #032 | 44000 | 94 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixing road from A118-A119 and from A124 | 1 | A-118 to A-127 | Innes Lake | 0 | 43998 |  | 37 | 43999 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting296820200614-4Excavator - 36 ton- After Jan 10202939.2 | Corbiere and Sons Contracting296820200614-4Excavator - 36 ton- After Jan 10202939.2INV #032 | [5 empty] | 1 | 2939.2 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2968 | 20200614-4 | 53510112 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 9.16 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2020-06-14 | 1 | INV #032 | 44000 | 94 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixing road from A118-A119 and from A124 | 1 | A-118 to A-127 | Innes Lake | 0 | 43998 |  | 37 | 43999 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting296820200614-4Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting296820200614-4Excavator Thumb - 30 - 50 ton- After Jan 1010122.1INV #032 | [5 empty] | 1 | 122.1 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2968 | 20200614-4 | 53510112 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-06-14 | 1 | INV #032 | 44000 | 94 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixing road from A118-A119 and from A124 | 1 | A-118 to A-127 | Innes Lake | 0 | 43998 |  | 37 | 43999 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting296820200614-4Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting296820200614-4Light Truck - Pick up- After Jan 102487.5INV #032 | [5 empty] | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2968 | 20200614-4 | 53510112 | Access | 0 | Foreman | 95 | 6 | HR |  |  | 95 | 0 | 570 | 74.1 | 644.1 | 2020-06-14 | 1 | INV #032 | 44000 | 94 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixing road from A118-A119 and from A124 | 1 | A-118 to A-127 | Innes Lake | 0 | 43998 |  | 37 | 43999 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting296820200614-4Foreman6570 | Corbiere and Sons Contracting296820200614-4Foreman6570INV #032 | [5 empty] | 1 | 570 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2968 | 20200614-4 | 53510112 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2020-06-14 | 1 | INV #032 | 44000 | 94 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixing road from A118-A119 and from A124 | 1 | A-118 to A-127 | Innes Lake | 0 | 43998 |  | 37 | 43999 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting296820200614-4L.O.A.3630 | Corbiere and Sons Contracting296820200614-4L.O.A.3630INV #032 | [5 empty] | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2968 | 20200614-4 | 53510112 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 23 | HR |  |  | 75 | 0 | 1725 | 224.25 | 1949.25 | 2020-06-14 | 1 | INV #032 | 44000 | 94 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixing road from A118-A119 and from A124 | 1 | A-118 to A-127 | Innes Lake | 0 | 43998 |  | 37 | 43999 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting296820200614-4Operator - Principle - After Jan 10231725 | Corbiere and Sons Contracting296820200614-4Operator - Principle - After Jan 10231725INV #032 | [5 empty] | 1 | 1725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2972 | 20200614-8 | 53510212 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 95.24 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2020-06-14 | 1 | INV #032 | 44000 | 94 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across access roads along Black Sturgeon Road | 2 | B018 - B029 | Black Sturgeon | 0 | 43998 |  | 36 | 43999 | [5 empty] | Mike Lecocq | 02 | Corbiere and Sons Contracting297220200614-8Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting297220200614-8Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #032 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2972 | 20200614-8 | 53510212 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-06-14 | 1 | INV #032 | 44000 | 94 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across access roads along Black Sturgeon Road | 2 | B018 - B029 | Black Sturgeon | 0 | 43998 |  | 36 | 43999 | [5 empty] | Mike Lecocq | 02 | Corbiere and Sons Contracting297220200614-8Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting297220200614-8Light Truck - Pick up- After Jan 101243.75INV #032 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2972 | 20200614-8 | 53510212 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-06-14 | 1 | INV #032 | 44000 | 94 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across access roads along Black Sturgeon Road | 2 | B018 - B029 | Black Sturgeon | 0 | 43998 |  | 36 | 43999 | [5 empty] | Mike Lecocq | 02 | Corbiere and Sons Contracting297220200614-8L.O.A.1210 | Corbiere and Sons Contracting297220200614-8L.O.A.1210INV #032 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2972 | 20200614-8 | 53510212 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2020-06-14 | 1 | INV #032 | 44000 | 94 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across access roads along Black Sturgeon Road | 2 | B018 - B029 | Black Sturgeon | 0 | 43998 |  | 36 | 43999 | [5 empty] | Mike Lecocq | 02 | Corbiere and Sons Contracting297220200614-8Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting297220200614-8Operator - Principle - After Jan 1011825INV #032 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2997 | 20200615-10 | 53510212 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10.5 | Dynamic | 95.24 | 0 |  |  | 1333.29 | 173.3277 | 1506.6177 | 2020-06-15 | 1 | INV #032 | 44000 | 94 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across access roads from B018-B030 | 2 | B018 - B029 | Black Sturgeon | 0 | 43999 |  | 36 | 43999 | [5 empty] | Mike Lecocq | 02 | Corbiere and Sons Contracting299720200615-10Grader - Cat 12 to 14 or equal- After Jan 1010.51333.29 | Corbiere and Sons Contracting299720200615-10Grader - Cat 12 to 14 or equal- After Jan 1010.51333.29INV #032 | [5 empty] | 1 | 1333.29 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2997 | 20200615-10 | 53510212 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-06-15 | 1 | INV #032 | 44000 | 94 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across access roads from B018-B030 | 2 | B018 - B029 | Black Sturgeon | 0 | 43999 |  | 36 | 43999 | [5 empty] | Mike Lecocq | 02 | Corbiere and Sons Contracting299720200615-10Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting299720200615-10Light Truck - Pick up- After Jan 101243.75INV #032 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2997 | 20200615-10 | 53510212 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-06-15 | 1 | INV #032 | 44000 | 94 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across access roads from B018-B030 | 2 | B018 - B029 | Black Sturgeon | 0 | 43999 |  | 36 | 43999 | [5 empty] | Mike Lecocq | 02 | Corbiere and Sons Contracting299720200615-10L.O.A.1210 | Corbiere and Sons Contracting299720200615-10L.O.A.1210INV #032 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2997 | 20200615-10 | 53510212 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2020-06-15 | 1 | INV #032 | 44000 | 94 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across access roads from B018-B030 | 2 | B018 - B029 | Black Sturgeon | 0 | 43999 |  | 36 | 43999 | [5 empty] | Mike Lecocq | 02 | Corbiere and Sons Contracting299720200615-10Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting299720200615-10Operator - Principle - After Jan 1011825INV #032 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2990 | 20200615-3 | 53510112 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10 | Dynamic | 98.61 | 0 |  |  | 1314.8 | 170.924 | 1485.724 | 2020-06-15 | 1 | INV #032 | 44000 | 94 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer and Grader doing maintenance across harold road to improve conditions | 1 | A-055 to A-084 | Eldorado | 0 | 43999 |  | 37 | 43999 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting299020200615-3Dozer D6 or equal- After Jan 10101314.8 | Corbiere and Sons Contracting299020200615-3Dozer D6 or equal- After Jan 10101314.8INV #032 | [5 empty] | 1 | 1314.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2990 | 20200615-3 | 53510112 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 95.24 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2020-06-15 | 1 | INV #032 | 44000 | 94 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer and Grader doing maintenance across harold road to improve conditions | 1 | A-055 to A-084 | Eldorado | 0 | 43999 |  | 37 | 43999 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting299020200615-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting299020200615-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8INV #032 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2990 | 20200615-3 | 53510112 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-06-15 | 1 | INV #032 | 44000 | 94 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer and Grader doing maintenance across harold road to improve conditions | 1 | A-055 to A-084 | Eldorado | 0 | 43999 |  | 37 | 43999 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting299020200615-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting299020200615-3Light Truck - Pick up- After Jan 101243.75INV #032 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2990 | 20200615-3 | 53510112 | Access | 0 | Foreman | 95 | 6 | HR |  |  | 95 | 0 | 570 | 74.1 | 644.1 | 2020-06-15 | 1 | INV #032 | 44000 | 94 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer and Grader doing maintenance across harold road to improve conditions | 1 | A-055 to A-084 | Eldorado | 0 | 43999 |  | 37 | 43999 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting299020200615-3Foreman6570 | Corbiere and Sons Contracting299020200615-3Foreman6570INV #032 | [5 empty] | 1 | 570 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2990 | 20200615-3 | 53510112 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2020-06-15 | 1 | INV #032 | 44000 | 94 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer and Grader doing maintenance across harold road to improve conditions | 1 | A-055 to A-084 | Eldorado | 0 | 43999 |  | 37 | 43999 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting299020200615-3L.O.A.3630 | Corbiere and Sons Contracting299020200615-3L.O.A.3630INV #032 | [5 empty] | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2990 | 20200615-3 | 53510112 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 23 | HR |  |  | 75 | 0 | 1725 | 224.25 | 1949.25 | 2020-06-15 | 1 | INV #032 | 44000 | 94 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer and Grader doing maintenance across harold road to improve conditions | 1 | A-055 to A-084 | Eldorado | 0 | 43999 |  | 37 | 43999 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting299020200615-3Operator - Principle - After Jan 10231725 | Corbiere and Sons Contracting299020200615-3Operator - Principle - After Jan 10231725INV #032 | [5 empty] | 1 | 1725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2991 | 20200615-4 | 53510112 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10 | Dynamic | 110.22 | 0 |  |  | 1469.6 | 191.048 | 1660.648 | 2020-06-15 | 1 | INV #032 | 44000 | 94 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixing road from A118-A120 | 1 | A-118 to A-127 | Innes Lake | 0 | 43999 |  | 37 | 43999 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting299120200615-4Excavator - 36 ton- After Jan 10101469.6 | Corbiere and Sons Contracting299120200615-4Excavator - 36 ton- After Jan 10101469.6INV #032 | [5 empty] | 1 | 1469.6 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2991 | 20200615-4 | 53510112 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-06-15 | 1 | INV #032 | 44000 | 94 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixing road from A118-A120 | 1 | A-118 to A-127 | Innes Lake | 0 | 43999 |  | 37 | 43999 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting299120200615-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting299120200615-4Light Truck - Pick up- After Jan 101243.75INV #032 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2991 | 20200615-4 | 53510112 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-06-15 | 1 | INV #032 | 44000 | 94 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixing road from A118-A120 | 1 | A-118 to A-127 | Innes Lake | 0 | 43999 |  | 37 | 43999 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting299120200615-4L.O.A.1210 | Corbiere and Sons Contracting299120200615-4L.O.A.1210INV #032 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 2991 | 20200615-4 | 53510112 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-06-15 | 1 | INV #032 | 44000 | 94 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixing road from A118-A120 | 1 | A-118 to A-127 | Innes Lake | 0 | 43999 |  | 37 | 43999 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting299120200615-4Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting299120200615-4Operator - Principle - After Jan 1011.5862.5INV #032 | [5 empty] | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3020 | 20200616-10 | 53510212 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 11 | Dynamic | 95.24 | 0 |  |  | 1396.78 | 181.5814 | 1578.3614 | 2020-06-16 | 1 | Inv #036 | 44013 | 95 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across access roads from B018-B030 | 2 | B018 - B029 | Black Sturgeon | 0 | 44003 |  | 36 | 44003 | [5 empty] | Mike Lecocq | 02 | Corbiere and Sons Contracting302020200616-10Grader - Cat 12 to 14 or equal- After Jan 10111396.78 | Corbiere and Sons Contracting302020200616-10Grader - Cat 12 to 14 or equal- After Jan 10111396.78Inv #036 | [5 empty] | 1 | 1396.78 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3020 | 20200616-10 | 53510212 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-06-16 | 1 | Inv #036 | 44013 | 95 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across access roads from B018-B030 | 2 | B018 - B029 | Black Sturgeon | 0 | 44003 |  | 36 | 44003 | [5 empty] | Mike Lecocq | 02 | Corbiere and Sons Contracting302020200616-10Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting302020200616-10Light Truck - Pick up- After Jan 101243.75Inv #036 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3020 | 20200616-10 | 53510212 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-06-16 | 1 | Inv #036 | 44013 | 95 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across access roads from B018-B030 | 2 | B018 - B029 | Black Sturgeon | 0 | 44003 |  | 36 | 44003 | [5 empty] | Mike Lecocq | 02 | Corbiere and Sons Contracting302020200616-10L.O.A.1210 | Corbiere and Sons Contracting302020200616-10L.O.A.1210Inv #036 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3020 | 20200616-10 | 53510212 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2020-06-16 | 1 | Inv #036 | 44013 | 95 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across access roads from B018-B030 | 2 | B018 - B029 | Black Sturgeon | 0 | 44003 |  | 36 | 44003 | [5 empty] | Mike Lecocq | 02 | Corbiere and Sons Contracting302020200616-10Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting302020200616-10Operator - Principle - After Jan 1012900Inv #036 | [5 empty] | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3040 | 20200617-10 | 53510212 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 95.24 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2020-06-17 | 1 | Inv #036 | 44013 | 95 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across access roads from B018-B030 | 2 | B018 - B029 | Black Sturgeon | 0 | 44003 |  | 36 | 44003 | [5 empty] | Mike Lecocq | 02 | Corbiere and Sons Contracting304020200617-10Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting304020200617-10Grader - Cat 12 to 14 or equal- After Jan 10101269.8Inv #036 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3040 | 20200617-10 | 53510212 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-06-17 | 1 | Inv #036 | 44013 | 95 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across access roads from B018-B030 | 2 | B018 - B029 | Black Sturgeon | 0 | 44003 |  | 36 | 44003 | [5 empty] | Mike Lecocq | 02 | Corbiere and Sons Contracting304020200617-10Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting304020200617-10Light Truck - Pick up- After Jan 101243.75Inv #036 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3040 | 20200617-10 | 53510212 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-06-17 | 1 | Inv #036 | 44013 | 95 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across access roads from B018-B030 | 2 | B018 - B029 | Black Sturgeon | 0 | 44003 |  | 36 | 44003 | [5 empty] | Mike Lecocq | 02 | Corbiere and Sons Contracting304020200617-10L.O.A.1210 | Corbiere and Sons Contracting304020200617-10L.O.A.1210Inv #036 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3040 | 20200617-10 | 53510212 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2020-06-17 | 1 | Inv #036 | 44013 | 95 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across access roads from B018-B030 | 2 | B018 - B029 | Black Sturgeon | 0 | 44003 |  | 36 | 44003 | [5 empty] | Mike Lecocq | 02 | Corbiere and Sons Contracting304020200617-10Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting304020200617-10Operator - Principle - After Jan 1011825Inv #036 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3069 | 20200619-4 | 53510112 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9.5 | Dynamic | 110.22 | 0 |  |  | 1396.12 | 181.4956 | 1577.6156 | 2020-06-19 | 1 | Inv #036 | 44013 | 95 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Mike finishing up at A127 and then walked out to be floated to Beck Road - Gary and Grader starting from A124 | 1 | A-118 to A-127 | Innes Lake | 0 | 44005 |  | 37 | 44009 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting306920200619-4Excavator - 36 ton- After Jan 109.51396.12 | Corbiere and Sons Contracting306920200619-4Excavator - 36 ton- After Jan 109.51396.12Inv #036 | [5 empty] | 1 | 1396.12 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3069 | 20200619-4 | 53510112 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9.5 | HR | 9.16 | 0 |  |  | 115.995 | 15.0793 | 131.0744 | 2020-06-19 | 1 | Inv #036 | 44013 | 95 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Mike finishing up at A127 and then walked out to be floated to Beck Road - Gary and Grader starting from A124 | 1 | A-118 to A-127 | Innes Lake | 0 | 44005 |  | 37 | 44009 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting306920200619-4Excavator Thumb - 30 - 50 ton- After Jan 109.5115.995 | Corbiere and Sons Contracting306920200619-4Excavator Thumb - 30 - 50 ton- After Jan 109.5115.995Inv #036 | [5 empty] | 1 | 115.995 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3069 | 20200619-4 | 53510112 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 95.24 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2020-06-19 | 1 | Inv #036 | 44013 | 95 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Mike finishing up at A127 and then walked out to be floated to Beck Road - Gary and Grader starting from A124 | 1 | A-118 to A-127 | Innes Lake | 0 | 44005 |  | 37 | 44009 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting306920200619-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting306920200619-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8Inv #036 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3069 | 20200619-4 | 53510112 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-06-19 | 1 | Inv #036 | 44013 | 95 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Mike finishing up at A127 and then walked out to be floated to Beck Road - Gary and Grader starting from A124 | 1 | A-118 to A-127 | Innes Lake | 0 | 44005 |  | 37 | 44009 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting306920200619-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting306920200619-4Light Truck - Pick up- After Jan 101243.75Inv #036 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3069 | 20200619-4 | 53510112 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-06-19 | 1 | Inv #036 | 44013 | 95 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Mike finishing up at A127 and then walked out to be floated to Beck Road - Gary and Grader starting from A124 | 1 | A-118 to A-127 | Innes Lake | 0 | 44005 |  | 37 | 44009 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting306920200619-4L.O.A.2420 | Corbiere and Sons Contracting306920200619-4L.O.A.2420Inv #036 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3069 | 20200619-4 | 53510112 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 23 | HR |  |  | 75 | 0 | 1725 | 224.25 | 1949.25 | 2020-06-19 | 1 | Inv #036 | 44013 | 95 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Mike finishing up at A127 and then walked out to be floated to Beck Road - Gary and Grader starting from A124 | 1 | A-118 to A-127 | Innes Lake | 0 | 44005 |  | 37 | 44009 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting306920200619-4Operator - Principle - After Jan 10231725 | Corbiere and Sons Contracting306920200619-4Operator - Principle - After Jan 10231725Inv #036 | [5 empty] | 1 | 1725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3094 | 20200620-10 | 53510212 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 95.24 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2020-06-20 | 1 | Inv#037 | 44021 | 97 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Lofty Davies | 2 | B054 - B064 | Lofty Davies | 0 | 44007 |  | 36 | 44016 | [5 empty] | Mike Lecocq | 02 | Corbiere and Sons Contracting309420200620-10Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting309420200620-10Grader - Cat 12 to 14 or equal- After Jan 10101269.8Inv#037 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3094 | 20200620-10 | 53510212 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-06-20 | 1 | Inv#037 | 44021 | 97 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Lofty Davies | 2 | B054 - B064 | Lofty Davies | 0 | 44007 |  | 36 | 44016 | [5 empty] | Mike Lecocq | 02 | Corbiere and Sons Contracting309420200620-10L.O.A.1210 | Corbiere and Sons Contracting309420200620-10L.O.A.1210Inv#037 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3094 | 20200620-10 | 53510212 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-06-20 | 1 | Inv#037 | 44021 | 97 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Lofty Davies | 2 | B054 - B064 | Lofty Davies | 0 | 44007 |  | 36 | 44016 | [5 empty] | Mike Lecocq | 02 | Corbiere and Sons Contracting309420200620-10Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting309420200620-10Operator - Principle - After Jan 1011.5862.5Inv#037 | [5 empty] | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3123 | 20200622-4 | 53510212 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 95.24 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2020-06-22 | 1 | Inv#037 | 44021 | 97 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across access roads | 2 | B018 - B029 | Black Sturgeon | 0 | 44008 |  | 36 | 44016 | [5 empty] | Mike Lecocq | 02 | Corbiere and Sons Contracting312320200622-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting312320200622-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8Inv#037 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3123 | 20200622-4 | 53510212 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-06-22 | 1 | Inv#037 | 44021 | 97 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across access roads | 2 | B018 - B029 | Black Sturgeon | 0 | 44008 |  | 36 | 44016 | [5 empty] | Mike Lecocq | 02 | Corbiere and Sons Contracting312320200622-4L.O.A.1210 | Corbiere and Sons Contracting312320200622-4L.O.A.1210Inv#037 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3123 | 20200622-4 | 53510212 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-06-22 | 1 | Inv#037 | 44021 | 97 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across access roads | 2 | B018 - B029 | Black Sturgeon | 0 | 44008 |  | 36 | 44016 | [5 empty] | Mike Lecocq | 02 | Corbiere and Sons Contracting312320200622-4Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting312320200622-4Operator - Principle - After Jan 1011.5862.5Inv#037 | [5 empty] | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3146 | 20200623-3 | 53510112 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10 | Dynamic | 110.22 | 0 |  |  | 1469.6 | 191.048 | 1660.648 | 2020-06-23 | 1 | Inv #036 | 44013 | 95 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixing road from B061-B063 | 1 | A-055 to A-084 | Eldorado | 0 | 44008 |  | 37 | 44010 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting314620200623-3Excavator - 36 ton- After Jan 10101469.6 | Corbiere and Sons Contracting314620200623-3Excavator - 36 ton- After Jan 10101469.6Inv #036 | [5 empty] | 1 | 1469.6 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3146 | 20200623-3 | 53510112 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 9.16 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2020-06-23 | 1 | Inv #036 | 44013 | 95 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixing road from B061-B063 | 1 | A-055 to A-084 | Eldorado | 0 | 44008 |  | 37 | 44010 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting314620200623-3Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting314620200623-3Excavator Thumb - 30 - 50 ton- After Jan 1010122.1Inv #036 | [5 empty] | 1 | 122.1 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3146 | 20200623-3 | 53510112 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-06-23 | 1 | Inv #036 | 44013 | 95 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixing road from B061-B063 | 1 | A-055 to A-084 | Eldorado | 0 | 44008 |  | 37 | 44010 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting314620200623-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting314620200623-3Light Truck - Pick up- After Jan 101243.75Inv #036 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3146 | 20200623-3 | 53510112 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-06-23 | 1 | Inv #036 | 44013 | 95 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixing road from B061-B063 | 1 | A-055 to A-084 | Eldorado | 0 | 44008 |  | 37 | 44010 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting314620200623-3L.O.A.1210 | Corbiere and Sons Contracting314620200623-3L.O.A.1210Inv #036 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3146 | 20200623-3 | 53510112 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-06-23 | 1 | Inv #036 | 44013 | 95 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixing road from B061-B063 | 1 | A-055 to A-084 | Eldorado | 0 | 44008 |  | 37 | 44010 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting314620200623-3Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting314620200623-3Operator - Principle - After Jan 1011.5862.5Inv #036 | [5 empty] | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3151 | 20200623-8 | 53510212 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 95.24 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2020-06-23 | 1 | Inv#037 | 44021 | 97 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across access roads | 2 | B054 - B064 | Lofty Davies | 0 | 44008 |  | 36 | 44016 | [5 empty] | Mike Lecocq | 02 | Corbiere and Sons Contracting315120200623-8Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting315120200623-8Grader - Cat 12 to 14 or equal- After Jan 10101269.8Inv#037 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3151 | 20200623-8 | 53510212 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-06-23 | 1 | Inv#037 | 44021 | 97 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across access roads | 2 | B054 - B064 | Lofty Davies | 0 | 44008 |  | 36 | 44016 | [5 empty] | Mike Lecocq | 02 | Corbiere and Sons Contracting315120200623-8L.O.A.1210 | Corbiere and Sons Contracting315120200623-8L.O.A.1210Inv#037 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3151 | 20200623-8 | 53510212 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-06-23 | 1 | Inv#037 | 44021 | 97 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across access roads | 2 | B054 - B064 | Lofty Davies | 0 | 44008 |  | 36 | 44016 | [5 empty] | Mike Lecocq | 02 | Corbiere and Sons Contracting315120200623-8Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting315120200623-8Operator - Principle - After Jan 1011.5862.5Inv#037 | [5 empty] | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3168 | 20200624-8 | 53510312 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 8 | Dynamic | 103.84 | 0 |  |  | 1107.6 | 143.988 | 1251.588 | 2020-06-24 | 1 | Inv #036 | 44013 | 95 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator doing road maintenance on Lachance | 3 | B161-B181 | Lachance Road | 0 | 44010 |  | 16 | 44011 | [5 empty] | Dave Ofukany | 03 | Corbiere and Sons Contracting316820200624-8Excavator - 30 ton- After Jan 1081107.6 | Corbiere and Sons Contracting316820200624-8Excavator - 30 ton- After Jan 1081107.6Inv #036 | [5 empty] | 1 | 1107.6 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3168 | 20200624-8 | 53510312 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 8 | HR | 9.16 | 0 |  |  | 97.68 | 12.6984 | 110.3784 | 2020-06-24 | 1 | Inv #036 | 44013 | 95 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator doing road maintenance on Lachance | 3 | B161-B181 | Lachance Road | 0 | 44010 |  | 16 | 44011 | [5 empty] | Dave Ofukany | 03 | Corbiere and Sons Contracting316820200624-8Excavator Thumb - 30 - 50 ton- After Jan 10897.68 | Corbiere and Sons Contracting316820200624-8Excavator Thumb - 30 - 50 ton- After Jan 10897.68Inv #036 | [5 empty] | 1 | 97.68 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3168 | 20200624-8 | 53510312 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-06-24 | 1 | Inv #036 | 44013 | 95 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator doing road maintenance on Lachance | 3 | B161-B181 | Lachance Road | 0 | 44010 |  | 16 | 44011 | [5 empty] | Dave Ofukany | 03 | Corbiere and Sons Contracting316820200624-8Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting316820200624-8Light Truck - Pick up- After Jan 101243.75Inv #036 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3168 | 20200624-8 | 53510312 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-06-24 | 1 | Inv #036 | 44013 | 95 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator doing road maintenance on Lachance | 3 | B161-B181 | Lachance Road | 0 | 44010 |  | 16 | 44011 | [5 empty] | Dave Ofukany | 03 | Corbiere and Sons Contracting316820200624-8L.O.A.1210 | Corbiere and Sons Contracting316820200624-8L.O.A.1210Inv #036 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3168 | 20200624-8 | 53510312 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 9 | HR |  |  | 75 | 0 | 675 | 87.75 | 762.75 | 2020-06-24 | 1 | Inv #036 | 44013 | 95 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator doing road maintenance on Lachance | 3 | B161-B181 | Lachance Road | 0 | 44010 |  | 16 | 44011 | [5 empty] | Dave Ofukany | 03 | Corbiere and Sons Contracting316820200624-8Operator - Principle - After Jan 109675 | Corbiere and Sons Contracting316820200624-8Operator - Principle - After Jan 109675Inv #036 | [5 empty] | 1 | 675 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3184 | 20200625-11 | 53510312 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10 | Dynamic | 103.84 | 0 |  |  | 1384.5 | 179.985 | 1564.485 | 2020-06-25 | 1 | Inv #036 | 44013 | 95 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Doing maintenance in North Shore pit | 1 | B161-B181 | Lachance Road | 0 | 44010 |  | 16 | 44007 | [5 empty] | Dave Ofukany | 03 | Corbiere and Sons Contracting318420200625-11Excavator - 30 ton- After Jan 10101384.5 | Corbiere and Sons Contracting318420200625-11Excavator - 30 ton- After Jan 10101384.5Inv #036 | [5 empty] | 1 | 1384.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3184 | 20200625-11 | 53510312 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 9.16 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2020-06-25 | 1 | Inv #036 | 44013 | 95 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Doing maintenance in North Shore pit | 1 | B161-B181 | Lachance Road | 0 | 44010 |  | 16 | 44007 | [5 empty] | Dave Ofukany | 03 | Corbiere and Sons Contracting318420200625-11Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting318420200625-11Excavator Thumb - 30 - 50 ton- After Jan 1010122.1Inv #036 | [5 empty] | 1 | 122.1 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3184 | 20200625-11 | 53510312 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-06-25 | 1 | Inv #036 | 44013 | 95 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Doing maintenance in North Shore pit | 1 | B161-B181 | Lachance Road | 0 | 44010 |  | 16 | 44007 | [5 empty] | Dave Ofukany | 03 | Corbiere and Sons Contracting318420200625-11Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting318420200625-11Light Truck - Pick up- After Jan 101243.75Inv #036 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3184 | 20200625-11 | 53510312 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-06-25 | 1 | Inv #036 | 44013 | 95 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Doing maintenance in North Shore pit | 1 | B161-B181 | Lachance Road | 0 | 44010 |  | 16 | 44007 | [5 empty] | Dave Ofukany | 03 | Corbiere and Sons Contracting318420200625-11L.O.A.1210 | Corbiere and Sons Contracting318420200625-11L.O.A.1210Inv #036 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3184 | 20200625-11 | 53510312 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2020-06-25 | 1 | Inv #036 | 44013 | 95 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Doing maintenance in North Shore pit | 1 | B161-B181 | Lachance Road | 0 | 44010 |  | 16 | 44007 | [5 empty] | Dave Ofukany | 03 | Corbiere and Sons Contracting318420200625-11Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting318420200625-11Operator - Principle - After Jan 1011825Inv #036 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3176 | 20200625-3 | 53510112 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9.5 | Dynamic | 110.22 | 0 |  |  | 1396.12 | 181.4956 | 1577.6156 | 2020-06-25 | 1 | Inv #036 | 44013 | 95 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixing road from A065-A067 | 1 | A-055 to A-084 | Eldorado | 0 | 44010 |  | 37 | 44011 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting317620200625-3Excavator - 36 ton- After Jan 109.51396.12 | Corbiere and Sons Contracting317620200625-3Excavator - 36 ton- After Jan 109.51396.12Inv #036 | [5 empty] | 1 | 1396.12 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3176 | 20200625-3 | 53510112 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9.5 | HR | 9.16 | 0 |  |  | 115.995 | 15.0793 | 131.0744 | 2020-06-25 | 1 | Inv #036 | 44013 | 95 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixing road from A065-A067 | 1 | A-055 to A-084 | Eldorado | 0 | 44010 |  | 37 | 44011 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting317620200625-3Excavator Thumb - 30 - 50 ton- After Jan 109.5115.995 | Corbiere and Sons Contracting317620200625-3Excavator Thumb - 30 - 50 ton- After Jan 109.5115.995Inv #036 | [5 empty] | 1 | 115.995 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3176 | 20200625-3 | 53510112 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-06-25 | 1 | Inv #036 | 44013 | 95 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixing road from A065-A067 | 1 | A-055 to A-084 | Eldorado | 0 | 44010 |  | 37 | 44011 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting317620200625-3Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting317620200625-3Light Truck - Pick up- After Jan 102487.5Inv #036 | [5 empty] | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3176 | 20200625-3 | 53510112 | Access | 0 | Foreman | 95 | 4 | HR |  |  | 95 | 0 | 380 | 49.4 | 429.4 | 2020-06-25 | 1 | Inv #036 | 44013 | 95 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixing road from A065-A067 | 1 | A-055 to A-084 | Eldorado | 0 | 44010 |  | 37 | 44011 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting317620200625-3Foreman4380 | Corbiere and Sons Contracting317620200625-3Foreman4380Inv #036 | [5 empty] | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3176 | 20200625-3 | 53510112 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-06-25 | 1 | Inv #036 | 44013 | 95 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixing road from A065-A067 | 1 | A-055 to A-084 | Eldorado | 0 | 44010 |  | 37 | 44011 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting317620200625-3L.O.A.2420 | Corbiere and Sons Contracting317620200625-3L.O.A.2420Inv #036 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3176 | 20200625-3 | 53510112 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-06-25 | 1 | Inv #036 | 44013 | 95 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixing road from A065-A067 | 1 | A-055 to A-084 | Eldorado | 0 | 44010 |  | 37 | 44011 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting317620200625-3Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting317620200625-3Operator - Principle - After Jan 1011.5862.5Inv #036 | [5 empty] | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3177 | 20200625-4 | 53510112 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9.5 | Dynamic | 103.84 | 0 |  |  | 1315.275 | 170.9857 | 1486.2607 | 2020-06-25 | 1 | Inv #036 | 44013 | 95 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixing Road from A109-A110 | 1 | A-085 to A-117 | Windfarm | 0 | 44010 |  | 37 | 44011 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting317720200625-4Excavator - 30 ton- After Jan 109.51315.275 | Corbiere and Sons Contracting317720200625-4Excavator - 30 ton- After Jan 109.51315.275Inv #036 | [5 empty] | 1 | 1315.275 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3177 | 20200625-4 | 53510112 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-06-25 | 1 | Inv #036 | 44013 | 95 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixing Road from A109-A110 | 1 | A-085 to A-117 | Windfarm | 0 | 44010 |  | 37 | 44011 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting317720200625-4L.O.A.1210 | Corbiere and Sons Contracting317720200625-4L.O.A.1210Inv #036 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3177 | 20200625-4 | 53510112 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-06-25 | 1 | Inv #036 | 44013 | 95 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixing Road from A109-A110 | 1 | A-085 to A-117 | Windfarm | 0 | 44010 |  | 37 | 44011 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting317720200625-4Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting317720200625-4Operator - Principle - After Jan 1011.5862.5Inv #036 | [5 empty] | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3179 | 20200625-6 | 53510212 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 95.24 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2020-06-25 | 1 | Inv #036 | 44013 | 95 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader doing maintenance along access roads | 2 | B065-B077 | Red Rock | 0 | 44010 |  | 37 | 44011 | [5 empty] | Harold Furlong | 02 | Corbiere and Sons Contracting317920200625-6Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting317920200625-6Grader - Cat 12 to 14 or equal- After Jan 10101269.8Inv #036 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3179 | 20200625-6 | 53510212 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-06-25 | 1 | Inv #036 | 44013 | 95 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader doing maintenance along access roads | 2 | B065-B077 | Red Rock | 0 | 44010 |  | 37 | 44011 | [5 empty] | Harold Furlong | 02 | Corbiere and Sons Contracting317920200625-6L.O.A.1210 | Corbiere and Sons Contracting317920200625-6L.O.A.1210Inv #036 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3179 | 20200625-6 | 53510212 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-06-25 | 1 | Inv #036 | 44013 | 95 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader doing maintenance along access roads | 2 | B065-B077 | Red Rock | 0 | 44010 |  | 37 | 44011 | [5 empty] | Harold Furlong | 02 | Corbiere and Sons Contracting317920200625-6Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting317920200625-6Operator - Principle - After Jan 1011.5862.5Inv #036 | [5 empty] | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3200 | 20200626-11 | 53510112 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9.5 | Dynamic | 110.22 | 0 |  |  | 1396.12 | 181.4956 | 1577.6156 | 2020-06-26 | 1 | Inv#037 | 44021 | 97 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixing road from A067-A069 | 1 | A-055 to A-084 | Eldorado | 0 | 44012 |  | 46 | 44013 | [5 empty] | Glen Greening | 01 | Corbiere and Sons Contracting320020200626-11Excavator - 36 ton- After Jan 109.51396.12 | Corbiere and Sons Contracting320020200626-11Excavator - 36 ton- After Jan 109.51396.12Inv#037 | [5 empty] | 1 | 1396.12 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3200 | 20200626-11 | 53510112 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9.5 | HR | 9.16 | 0 |  |  | 115.995 | 15.0793 | 131.0744 | 2020-06-26 | 1 | Inv#037 | 44021 | 97 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixing road from A067-A069 | 1 | A-055 to A-084 | Eldorado | 0 | 44012 |  | 46 | 44013 | [5 empty] | Glen Greening | 01 | Corbiere and Sons Contracting320020200626-11Excavator Thumb - 30 - 50 ton- After Jan 109.5115.995 | Corbiere and Sons Contracting320020200626-11Excavator Thumb - 30 - 50 ton- After Jan 109.5115.995Inv#037 | [5 empty] | 1 | 115.995 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3200 | 20200626-11 | 53510112 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-06-26 | 1 | Inv#037 | 44021 | 97 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixing road from A067-A069 | 1 | A-055 to A-084 | Eldorado | 0 | 44012 |  | 46 | 44013 | [5 empty] | Glen Greening | 01 | Corbiere and Sons Contracting320020200626-11Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting320020200626-11Light Truck - Pick up- After Jan 101243.75Inv#037 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3200 | 20200626-11 | 53510112 | Access | 0 | Foreman | 95 | 4 | HR |  |  | 95 | 0 | 380 | 49.4 | 429.4 | 2020-06-26 | 1 | Inv#037 | 44021 | 97 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixing road from A067-A069 | 1 | A-055 to A-084 | Eldorado | 0 | 44012 |  | 46 | 44013 | [5 empty] | Glen Greening | 01 | Corbiere and Sons Contracting320020200626-11Foreman4380 | Corbiere and Sons Contracting320020200626-11Foreman4380Inv#037 | [5 empty] | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3200 | 20200626-11 | 53510112 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-06-26 | 1 | Inv#037 | 44021 | 97 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixing road from A067-A069 | 1 | A-055 to A-084 | Eldorado | 0 | 44012 |  | 46 | 44013 | [5 empty] | Glen Greening | 01 | Corbiere and Sons Contracting320020200626-11L.O.A.2420 | Corbiere and Sons Contracting320020200626-11L.O.A.2420Inv#037 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3200 | 20200626-11 | 53510112 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-06-26 | 1 | Inv#037 | 44021 | 97 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixing road from A067-A069 | 1 | A-055 to A-084 | Eldorado | 0 | 44012 |  | 46 | 44013 | [5 empty] | Glen Greening | 01 | Corbiere and Sons Contracting320020200626-11Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting320020200626-11Operator - Principle - After Jan 1011.5862.5Inv#037 | [5 empty] | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3256 | 20200626-23 | 53510212 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 95.24 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2020-06-26 | 1 | Inv#037 | 44021 | 97 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader Working across landfill road for gravel haul | 2 | B065-B077 | Red Rock | 0 | 44018 |  | 46 | 44021 | [5 empty] | Glen Greening | 02 | Corbiere and Sons Contracting325620200626-23Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting325620200626-23Grader - Cat 12 to 14 or equal- After Jan 10101269.8Inv#037 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3256 | 20200626-23 | 53510212 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-06-26 | 1 | Inv#037 | 44021 | 97 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader Working across landfill road for gravel haul | 2 | B065-B077 | Red Rock | 0 | 44018 |  | 46 | 44021 | [5 empty] | Glen Greening | 02 | Corbiere and Sons Contracting325620200626-23L.O.A.1210 | Corbiere and Sons Contracting325620200626-23L.O.A.1210Inv#037 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3256 | 20200626-23 | 53510212 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-06-26 | 1 | Inv#037 | 44021 | 97 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader Working across landfill road for gravel haul | 2 | B065-B077 | Red Rock | 0 | 44018 |  | 46 | 44021 | [5 empty] | Glen Greening | 02 | Corbiere and Sons Contracting325620200626-23Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting325620200626-23Operator - Principle - After Jan 1011.5862.5Inv#037 | [5 empty] | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3260 | 20200627-10 | 53510212 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 6 | Dynamic | 95.24 | 0 |  |  | 761.88 | 99.0444 | 860.9244 | 2020-06-27 | 1 | Inv#037 | 44021 | 97 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across landfill road for gravel Haul | 2 | B065-B077 | Red Rock | 0 | 44019 |  | 46 | 44021 | [5 empty] | Glen Greening | 02 | Corbiere and Sons Contracting326020200627-10Grader - Cat 12 to 14 or equal- After Jan 106761.88 | Corbiere and Sons Contracting326020200627-10Grader - Cat 12 to 14 or equal- After Jan 106761.88Inv#037 | [5 empty] | 1 | 761.88 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3260 | 20200627-10 | 53510212 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-06-27 | 1 | Inv#037 | 44021 | 97 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across landfill road for gravel Haul | 2 | B065-B077 | Red Rock | 0 | 44019 |  | 46 | 44021 | [5 empty] | Glen Greening | 02 | Corbiere and Sons Contracting326020200627-10L.O.A.1210 | Corbiere and Sons Contracting326020200627-10L.O.A.1210Inv#037 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3260 | 20200627-10 | 53510212 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 7 | HR |  |  | 75 | 0 | 525 | 68.25 | 593.25 | 2020-06-27 | 1 | Inv#037 | 44021 | 97 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across landfill road for gravel Haul | 2 | B065-B077 | Red Rock | 0 | 44019 |  | 46 | 44021 | [5 empty] | Glen Greening | 02 | Corbiere and Sons Contracting326020200627-10Operator - Principle - After Jan 107525 | Corbiere and Sons Contracting326020200627-10Operator - Principle - After Jan 107525Inv#037 | [5 empty] | 1 | 525 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3276 | 20200628-4 | 53510212 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 2 | Dynamic | 95.24 | 0 |  |  | 253.96 | 33.0148 | 286.9748 | 2020-06-28 | 1 | Inv#039 | 44035 | 99 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working out landfill road to smooth out for gravel haul | 2 | B065-B077 | Red Rock | 0 | 44019 |  | 47 | 44020 | [5 empty] | Clint Maerz | 02 | Corbiere and Sons Contracting327620200628-4Grader - Cat 12 to 14 or equal- After Jan 102253.96 | Corbiere and Sons Contracting327620200628-4Grader - Cat 12 to 14 or equal- After Jan 102253.96Inv#039 | [5 empty] | 1 | 253.96 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3276 | 20200628-4 | 53510212 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-06-28 | 1 | Inv#039 | 44035 | 99 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working out landfill road to smooth out for gravel haul | 2 | B065-B077 | Red Rock | 0 | 44019 |  | 47 | 44020 | [5 empty] | Clint Maerz | 02 | Corbiere and Sons Contracting327620200628-4L.O.A.1210 | Corbiere and Sons Contracting327620200628-4L.O.A.1210Inv#039 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3276 | 20200628-4 | 53510212 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 3 | HR |  |  | 75 | 0 | 225 | 29.25 | 254.25 | 2020-06-28 | 1 | Inv#039 | 44035 | 99 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working out landfill road to smooth out for gravel haul | 2 | B065-B077 | Red Rock | 0 | 44019 |  | 47 | 44020 | [5 empty] | Clint Maerz | 02 | Corbiere and Sons Contracting327620200628-4Operator - Principle - After Jan 103225 | Corbiere and Sons Contracting327620200628-4Operator - Principle - After Jan 103225Inv#039 | [5 empty] | 1 | 225 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3311 | 20200630-12 | 53510312 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10 | Dynamic | 103.84 | 0 |  |  | 1384.5 | 179.985 | 1564.485 | 2020-06-30 | 1 | Inv#039 | 44035 | 99 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Doing maintenance on existing roads on Gurney Lake Road waiting on environmental for further update | 3 | B175-B176 | Gurney Lake Road | 0 | 44020 |  | 16 | 44021 | [5 empty] | Dave Ofukany | 03 | Corbiere and Sons Contracting331120200630-12Excavator - 30 ton- After Jan 10101384.5 | Corbiere and Sons Contracting331120200630-12Excavator - 30 ton- After Jan 10101384.5Inv#039 | [5 empty] | 1 | 1384.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3311 | 20200630-12 | 53510312 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10 | Dynamic | 110.22 | 0 |  |  | 1469.6 | 191.048 | 1660.648 | 2020-06-30 | 1 | Inv#039 | 44035 | 99 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Doing maintenance on existing roads on Gurney Lake Road waiting on environmental for further update | 3 | B175-B176 | Gurney Lake Road | 0 | 44020 |  | 16 | 44021 | [5 empty] | Dave Ofukany | 03 | Corbiere and Sons Contracting331120200630-12Excavator - 36 ton- After Jan 10101469.6 | Corbiere and Sons Contracting331120200630-12Excavator - 36 ton- After Jan 10101469.6Inv#039 | [5 empty] | 1 | 1469.6 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3311 | 20200630-12 | 53510312 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 9.16 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2020-06-30 | 1 | Inv#039 | 44035 | 99 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Doing maintenance on existing roads on Gurney Lake Road waiting on environmental for further update | 3 | B175-B176 | Gurney Lake Road | 0 | 44020 |  | 16 | 44021 | [5 empty] | Dave Ofukany | 03 | Corbiere and Sons Contracting331120200630-12Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting331120200630-12Excavator Thumb - 30 - 50 ton- After Jan 1010122.1Inv#039 | [5 empty] | 1 | 122.1 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3311 | 20200630-12 | 53510312 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 9.16 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2020-06-30 | 1 | Inv#039 | 44035 | 99 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Doing maintenance on existing roads on Gurney Lake Road waiting on environmental for further update | 3 | B175-B176 | Gurney Lake Road | 0 | 44020 |  | 16 | 44021 | [5 empty] | Dave Ofukany | 03 | Corbiere and Sons Contracting331120200630-12Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting331120200630-12Excavator Thumb - 30 - 50 ton- After Jan 1010122.1Inv#039 | [5 empty] | 1 | 122.1 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3311 | 20200630-12 | 53510312 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-06-30 | 1 | Inv#039 | 44035 | 99 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Doing maintenance on existing roads on Gurney Lake Road waiting on environmental for further update | 3 | B175-B176 | Gurney Lake Road | 0 | 44020 |  | 16 | 44021 | [5 empty] | Dave Ofukany | 03 | Corbiere and Sons Contracting331120200630-12Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting331120200630-12Light Truck - Pick up- After Jan 101243.75Inv#039 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3311 | 20200630-12 | 53510312 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-06-30 | 1 | Inv#039 | 44035 | 99 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Doing maintenance on existing roads on Gurney Lake Road waiting on environmental for further update | 3 | B175-B176 | Gurney Lake Road | 0 | 44020 |  | 16 | 44021 | [5 empty] | Dave Ofukany | 03 | Corbiere and Sons Contracting331120200630-12L.O.A.2420 | Corbiere and Sons Contracting331120200630-12L.O.A.2420Inv#039 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3311 | 20200630-12 | 53510312 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 22 | HR |  |  | 75 | 0 | 1650 | 214.5 | 1864.5 | 2020-06-30 | 1 | Inv#039 | 44035 | 99 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Doing maintenance on existing roads on Gurney Lake Road waiting on environmental for further update | 3 | B175-B176 | Gurney Lake Road | 0 | 44020 |  | 16 | 44021 | [5 empty] | Dave Ofukany | 03 | Corbiere and Sons Contracting331120200630-12Operator - Principle - After Jan 10221650 | Corbiere and Sons Contracting331120200630-12Operator - Principle - After Jan 10221650Inv#039 | [5 empty] | 1 | 1650 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3304 | 20200630-5 | 53510112 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 5.5 | Dynamic | 95.24 | 0 |  |  | 698.39 | 90.7907 | 789.1807 | 2020-06-30 | 1 | Inv#039 | 44035 | 99 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Running grader along Innes lake access roads | 1 | A-118 to A-127 | Innes Lake | 0 | 44020 |  | 47 | 44021 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting330420200630-5Grader - Cat 12 to 14 or equal- After Jan 105.5698.39 | Corbiere and Sons Contracting330420200630-5Grader - Cat 12 to 14 or equal- After Jan 105.5698.39Inv#039 | [5 empty] | 1 | 698.39 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3304 | 20200630-5 | 53510112 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-06-30 | 1 | Inv#039 | 44035 | 99 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Running grader along Innes lake access roads | 1 | A-118 to A-127 | Innes Lake | 0 | 44020 |  | 47 | 44021 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting330420200630-5L.O.A.1210 | Corbiere and Sons Contracting330420200630-5L.O.A.1210Inv#039 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3304 | 20200630-5 | 53510112 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6.5 | HR |  |  | 75 | 0 | 487.5 | 63.375 | 550.875 | 2020-06-30 | 1 | Inv#039 | 44035 | 99 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Running grader along Innes lake access roads | 1 | A-118 to A-127 | Innes Lake | 0 | 44020 |  | 47 | 44021 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting330420200630-5Operator - Principle - After Jan 106.5487.5 | Corbiere and Sons Contracting330420200630-5Operator - Principle - After Jan 106.5487.5Inv#039 | [5 empty] | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3306 | 20200630-7 | 53510212 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 4.5 | Dynamic | 95.24 | 0 |  |  | 571.41 | 74.2833 | 645.6933 | 2020-06-30 | 1 | Inv#039 | 44035 | 99 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Landfill Road | 2 | B065-B077 | Red Rock | 0 | 44020 |  | 47 | 44021 | [5 empty] | Clint Maerz | 02 | Corbiere and Sons Contracting330620200630-7Grader - Cat 12 to 14 or equal- After Jan 104.5571.41 | Corbiere and Sons Contracting330620200630-7Grader - Cat 12 to 14 or equal- After Jan 104.5571.41Inv#039 | [5 empty] | 1 | 571.41 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3306 | 20200630-7 | 53510212 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5 | HR |  |  | 75 | 0 | 375 | 48.75 | 423.75 | 2020-06-30 | 1 | Inv#039 | 44035 | 99 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Landfill Road | 2 | B065-B077 | Red Rock | 0 | 44020 |  | 47 | 44021 | [5 empty] | Clint Maerz | 02 | Corbiere and Sons Contracting330620200630-7Operator - Principle - After Jan 105375 | Corbiere and Sons Contracting330620200630-7Operator - Principle - After Jan 105375Inv#039 | [5 empty] | 1 | 375 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3388 | 20200701-7 | 53510112 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 9.5 | Dynamic | 95.24 | 0 |  |  | 1206.31 | 156.8203 | 1363.1303 | 2020-07-01 | 1 | Inv#039 | 44035 | 99 | 0 | 0 | Arlene Dahl | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Carvern Lake Road and Fish Hatchery | 1 | A-128 to B-017 | Wolf Lake | 0 | 44023 |  | 47 | 44024 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting338820200701-7Grader - Cat 12 to 14 or equal- After Jan 109.51206.31 | Corbiere and Sons Contracting338820200701-7Grader - Cat 12 to 14 or equal- After Jan 109.51206.31Inv#039 | [5 empty] | 1 | 1206.31 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3388 | 20200701-7 | 53510112 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-07-01 | 1 | Inv#039 | 44035 | 99 | 0 | 0 | Arlene Dahl | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Carvern Lake Road and Fish Hatchery | 1 | A-128 to B-017 | Wolf Lake | 0 | 44023 |  | 47 | 44024 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting338820200701-7L.O.A.1210 | Corbiere and Sons Contracting338820200701-7L.O.A.1210Inv#039 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3388 | 20200701-7 | 53510112 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-07-01 | 1 | Inv#039 | 44035 | 99 | 0 | 0 | Arlene Dahl | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Carvern Lake Road and Fish Hatchery | 1 | A-128 to B-017 | Wolf Lake | 0 | 44023 |  | 47 | 44024 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting338820200701-7Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting338820200701-7Operator - Principle - After Jan 1011.5862.5Inv#039 | [5 empty] | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3408 | 20200702-4 | 53510112 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 6 | Dynamic | 103.84 | 0 |  |  | 830.7 | 107.991 | 938.691 | 2020-07-02 | 1 | Inv#039 | 44035 | 99 | 0 | 0 | Arlene Dahl | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixing road from A118 | 1 | A-118 to A-127 | Innes Lake | 0 | 44025 |  | 47 | 44026 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting340820200702-4Excavator - 30 ton- After Jan 106830.7 | Corbiere and Sons Contracting340820200702-4Excavator - 30 ton- After Jan 106830.7Inv#039 | [5 empty] | 1 | 830.7 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3408 | 20200702-4 | 53510112 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 6 | HR | 9.16 | 0 |  |  | 73.26 | 9.5238 | 82.7838 | 2020-07-02 | 1 | Inv#039 | 44035 | 99 | 0 | 0 | Arlene Dahl | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixing road from A118 | 1 | A-118 to A-127 | Innes Lake | 0 | 44025 |  | 47 | 44026 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting340820200702-4Excavator Thumb - 30 - 50 ton- After Jan 10673.26 | Corbiere and Sons Contracting340820200702-4Excavator Thumb - 30 - 50 ton- After Jan 10673.26Inv#039 | [5 empty] | 1 | 73.26 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3408 | 20200702-4 | 53510112 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 75 | 0 | 450 | 58.5 | 508.5 | 2020-07-02 | 1 | Inv#039 | 44035 | 99 | 0 | 0 | Arlene Dahl | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixing road from A118 | 1 | A-118 to A-127 | Innes Lake | 0 | 44025 |  | 47 | 44026 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting340820200702-4Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting340820200702-4Operator - Principle - After Jan 106450Inv#039 | [5 empty] | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3412 | 20200702-8 | 53510112 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 9.5 | Dynamic | 95.24 | 0 |  |  | 1206.31 | 156.8203 | 1363.1303 | 2020-07-02 | 1 | Inv#039 | 44035 | 99 | 0 | 0 | Arlene Dahl | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Fish Hatchery and Cavern Lake access Roads | 1 | A-128 to B-017 | Wolf Lake | 0 | 44025 |  | 47 | 44026 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting341220200702-8Grader - Cat 12 to 14 or equal- After Jan 109.51206.31 | Corbiere and Sons Contracting341220200702-8Grader - Cat 12 to 14 or equal- After Jan 109.51206.31Inv#039 | [5 empty] | 1 | 1206.31 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3412 | 20200702-8 | 53510112 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-07-02 | 1 | Inv#039 | 44035 | 99 | 0 | 0 | Arlene Dahl | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Fish Hatchery and Cavern Lake access Roads | 1 | A-128 to B-017 | Wolf Lake | 0 | 44025 |  | 47 | 44026 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting341220200702-8L.O.A.1210 | Corbiere and Sons Contracting341220200702-8L.O.A.1210Inv#039 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3412 | 20200702-8 | 53510112 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-07-02 | 1 | Inv#039 | 44035 | 99 | 0 | 0 | Arlene Dahl | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Fish Hatchery and Cavern Lake access Roads | 1 | A-128 to B-017 | Wolf Lake | 0 | 44025 |  | 47 | 44026 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting341220200702-8Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting341220200702-8Operator - Principle - After Jan 1011.5862.5Inv#039 | [5 empty] | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3486 | 20200703-3 | 53510112 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 9.5 | Dynamic | 95.24 | 0 |  |  | 1206.31 | 156.8203 | 1363.1303 | 2020-07-03 | 1 | Inv#039 | 44035 | 99 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Innes Lake Road | 1 | A-118 to A-127 | Innes Lake | 0 | 44026 |  | 47 | 44014 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting348620200703-3Grader - Cat 12 to 14 or equal- After Jan 109.51206.31 | Corbiere and Sons Contracting348620200703-3Grader - Cat 12 to 14 or equal- After Jan 109.51206.31Inv#039 | [5 empty] | 1 | 1206.31 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3486 | 20200703-3 | 53510112 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-07-03 | 1 | Inv#039 | 44035 | 99 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Innes Lake Road | 1 | A-118 to A-127 | Innes Lake | 0 | 44026 |  | 47 | 44014 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting348620200703-3L.O.A.1210 | Corbiere and Sons Contracting348620200703-3L.O.A.1210Inv#039 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3486 | 20200703-3 | 53510112 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-07-03 | 1 | Inv#039 | 44035 | 99 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Innes Lake Road | 1 | A-118 to A-127 | Innes Lake | 0 | 44026 |  | 47 | 44014 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting348620200703-3Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting348620200703-3Operator - Principle - After Jan 1011.5862.5Inv#039 | [5 empty] | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3487 | 20200703-4 | 53510112 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 6 | Dynamic | 103.84 | 0 |  |  | 830.7 | 107.991 | 938.691 | 2020-07-03 | 1 | Inv#039 | 44035 | 99 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixing Road from A118 | 1 | A-118 to A-127 | Innes Lake | 0 | 44026 |  | 47 | 44032 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting348720200703-4Excavator - 30 ton- After Jan 106830.7 | Corbiere and Sons Contracting348720200703-4Excavator - 30 ton- After Jan 106830.7Inv#039 | [5 empty] | 1 | 830.7 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3487 | 20200703-4 | 53510112 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-07-03 | 1 | Inv#039 | 44035 | 99 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixing Road from A118 | 1 | A-118 to A-127 | Innes Lake | 0 | 44026 |  | 47 | 44032 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting348720200703-4Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting348720200703-4Light Truck - Pick up- After Jan 102487.5Inv#039 | [5 empty] | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3487 | 20200703-4 | 53510112 | Access | 0 | Foreman | 95 | 4 | HR |  |  | 95 | 0 | 380 | 49.4 | 429.4 | 2020-07-03 | 1 | Inv#039 | 44035 | 99 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixing Road from A118 | 1 | A-118 to A-127 | Innes Lake | 0 | 44026 |  | 47 | 44032 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting348720200703-4Foreman4380 | Corbiere and Sons Contracting348720200703-4Foreman4380Inv#039 | [5 empty] | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3487 | 20200703-4 | 53510112 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  |  | 630 | 81.9 | 711.9 | 2020-07-03 | 1 | Inv#039 | 44035 | 99 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixing Road from A118 | 1 | A-118 to A-127 | Innes Lake | 0 | 44026 |  | 47 | 44032 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting348720200703-4L.O.A.3630 | Corbiere and Sons Contracting348720200703-4L.O.A.3630Inv#039 | [5 empty] | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3487 | 20200703-4 | 53510112 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 8 | HR |  |  | 75 | 0 | 600 | 78 | 678 | 2020-07-03 | 1 | Inv#039 | 44035 | 99 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixing Road from A118 | 1 | A-118 to A-127 | Innes Lake | 0 | 44026 |  | 47 | 44032 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting348720200703-4Operator - Principle - After Jan 108600 | Corbiere and Sons Contracting348720200703-4Operator - Principle - After Jan 108600Inv#039 | [5 empty] | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3487 | 20200703-4 | 53510112 | Access | 0 | Labourer - General - After Jan 10 | 60 | 8 | HR |  |  | 60 | 0 | 480 | 62.4 | 542.4 | 2020-07-03 | 1 | Inv#039 | 44035 | 99 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixing Road from A118 | 1 | A-118 to A-127 | Innes Lake | 0 | 44026 |  | 47 | 44032 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting348720200703-4Labourer - General - After Jan 108480 | Corbiere and Sons Contracting348720200703-4Labourer - General - After Jan 108480Inv#039 | [5 empty] | 1 | 480 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3503 | 20200704-4 | 53510112 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 9.5 | Dynamic | 95.24 | 0 |  |  | 1206.31 | 156.8203 | 1363.1303 | 2020-07-04 | 1 | Inv#039 | 44035 | 99 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gary worked on grader on Innes Lake Rd. down to A117 for the rest of the day. | 1 | A-118 to A-127 | Innes Lake | 0 | 44026 |  | 47 | 44029 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting350320200704-4Grader - Cat 12 to 14 or equal- After Jan 109.51206.31 | Corbiere and Sons Contracting350320200704-4Grader - Cat 12 to 14 or equal- After Jan 109.51206.31Inv#039 | [5 empty] | 1 | 1206.31 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3503 | 20200704-4 | 53510112 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-07-04 | 1 | Inv#039 | 44035 | 99 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gary worked on grader on Innes Lake Rd. down to A117 for the rest of the day. | 1 | A-118 to A-127 | Innes Lake | 0 | 44026 |  | 47 | 44029 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting350320200704-4L.O.A.1210 | Corbiere and Sons Contracting350320200704-4L.O.A.1210Inv#039 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3503 | 20200704-4 | 53510112 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-07-04 | 1 | Inv#039 | 44035 | 99 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gary worked on grader on Innes Lake Rd. down to A117 for the rest of the day. | 1 | A-118 to A-127 | Innes Lake | 0 | 44026 |  | 47 | 44029 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting350320200704-4Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting350320200704-4Operator - Principle - After Jan 1011.5862.5Inv#039 | [5 empty] | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3504 | 20200704-5 | 53510212 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-07-04 | 1 | Inv#039 | 44035 | 99 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Meeting with Valard then to B029 to discuss access road issues and plan for the fix. | 2 | B018 - B029 | Black Sturgeon | 0 | 44026 |  | 47 | 44029 | [5 empty] | Clint Maerz | 02 | Corbiere and Sons Contracting350420200704-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting350420200704-5Light Truck - Pick up- After Jan 101243.75Inv#039 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3504 | 20200704-5 | 53510212 | Access | 0 | Foreman | 95 | 3 | HR |  |  | 95 | 0 | 285 | 37.05 | 322.05 | 2020-07-04 | 1 | Inv#039 | 44035 | 99 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Meeting with Valard then to B029 to discuss access road issues and plan for the fix. | 2 | B018 - B029 | Black Sturgeon | 0 | 44026 |  | 47 | 44029 | [5 empty] | Clint Maerz | 02 | Corbiere and Sons Contracting350420200704-5Foreman3285 | Corbiere and Sons Contracting350420200704-5Foreman3285Inv#039 | [5 empty] | 1 | 285 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3517 | 20200705-3 | 53510212 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 5 | Dynamic | 103.84 | 0 |  |  | 692.25 | 89.9925 | 782.2425 | 2020-07-05 | 1 | Inv#039 | 44035 | 99 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Repair sto road leading up to B029 | 2 | B018 - B029 | Black Sturgeon | 0 | 44027 |  | 47 | 44029 | [5 empty] | Clint Maerz | 02 | Corbiere and Sons Contracting351720200705-3Excavator - 30 ton- After Jan 105692.25 | Corbiere and Sons Contracting351720200705-3Excavator - 30 ton- After Jan 105692.25Inv#039 | [5 empty] | 1 | 692.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3517 | 20200705-3 | 53510212 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 5 | HR | 9.16 | 0 |  |  | 61.05 | 7.9365 | 68.9865 | 2020-07-05 | 1 | Inv#039 | 44035 | 99 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Repair sto road leading up to B029 | 2 | B018 - B029 | Black Sturgeon | 0 | 44027 |  | 47 | 44029 | [5 empty] | Clint Maerz | 02 | Corbiere and Sons Contracting351720200705-3Excavator Thumb - 30 - 50 ton- After Jan 10561.05 | Corbiere and Sons Contracting351720200705-3Excavator Thumb - 30 - 50 ton- After Jan 10561.05Inv#039 | [5 empty] | 1 | 61.05 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3517 | 20200705-3 | 53510212 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-07-05 | 1 | Inv#039 | 44035 | 99 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Repair sto road leading up to B029 | 2 | B018 - B029 | Black Sturgeon | 0 | 44027 |  | 47 | 44029 | [5 empty] | Clint Maerz | 02 | Corbiere and Sons Contracting351720200705-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting351720200705-3Light Truck - Pick up- After Jan 101243.75Inv#039 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3517 | 20200705-3 | 53510212 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 75 | 0 | 450 | 58.5 | 508.5 | 2020-07-05 | 1 | Inv#039 | 44035 | 99 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Repair sto road leading up to B029 | 2 | B018 - B029 | Black Sturgeon | 0 | 44027 |  | 47 | 44029 | [5 empty] | Clint Maerz | 02 | Corbiere and Sons Contracting351720200705-3Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting351720200705-3Operator - Principle - After Jan 106450Inv#039 | [5 empty] | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3523 | 20200705-9 | 53510312 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 8 | Dynamic | 95.24 | 0 |  |  | 1015.84 | 132.0592 | 1147.8992 | 2020-07-05 | 1 | Inv#039 | 44035 | 99 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Lachance | 3 | B161-B181 | Lachance Road | 0 | 44027 |  | 9 | 44033 | [5 empty] | Mandy Sandhu | 03 | Corbiere and Sons Contracting352320200705-9Grader - Cat 12 to 14 or equal- After Jan 1081015.84 | Corbiere and Sons Contracting352320200705-9Grader - Cat 12 to 14 or equal- After Jan 1081015.84Inv#039 | [5 empty] | 1 | 1015.84 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3523 | 20200705-9 | 53510312 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-07-05 | 1 | Inv#039 | 44035 | 99 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Lachance | 3 | B161-B181 | Lachance Road | 0 | 44027 |  | 9 | 44033 | [5 empty] | Mandy Sandhu | 03 | Corbiere and Sons Contracting352320200705-9Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting352320200705-9Light Truck - Pick up- After Jan 101243.75Inv#039 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3523 | 20200705-9 | 53510312 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-07-05 | 1 | Inv#039 | 44035 | 99 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Lachance | 3 | B161-B181 | Lachance Road | 0 | 44027 |  | 9 | 44033 | [5 empty] | Mandy Sandhu | 03 | Corbiere and Sons Contracting352320200705-9L.O.A.1210 | Corbiere and Sons Contracting352320200705-9L.O.A.1210Inv#039 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3523 | 20200705-9 | 53510312 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 8 | HR |  |  | 75 | 0 | 600 | 78 | 678 | 2020-07-05 | 1 | Inv#039 | 44035 | 99 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Lachance | 3 | B161-B181 | Lachance Road | 0 | 44027 |  | 9 | 44033 | [5 empty] | Mandy Sandhu | 03 | Corbiere and Sons Contracting352320200705-9Operator - Principle - After Jan 108600 | Corbiere and Sons Contracting352320200705-9Operator - Principle - After Jan 108600Inv#039 | [5 empty] | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3558 | 20200706-18 | 53510112 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 9.5 | Dynamic | 95.24 | 0 |  |  | 1206.31 | 156.8203 | 1363.1303 | 2020-07-06 | 1 | Inv#039 | 44035 | 99 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Greenwich access | 1 | A-085 to A-117 | Windfarm | 0 | 44029 |  | 47 | 44032 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting355820200706-18Grader - Cat 12 to 14 or equal- After Jan 109.51206.31 | Corbiere and Sons Contracting355820200706-18Grader - Cat 12 to 14 or equal- After Jan 109.51206.31Inv#039 | [5 empty] | 1 | 1206.31 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3558 | 20200706-18 | 53510112 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-07-06 | 1 | Inv#039 | 44035 | 99 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Greenwich access | 1 | A-085 to A-117 | Windfarm | 0 | 44029 |  | 47 | 44032 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting355820200706-18L.O.A.1210 | Corbiere and Sons Contracting355820200706-18L.O.A.1210Inv#039 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3558 | 20200706-18 | 53510112 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-07-06 | 1 | Inv#039 | 44035 | 99 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Greenwich access | 1 | A-085 to A-117 | Windfarm | 0 | 44029 |  | 47 | 44032 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting355820200706-18Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting355820200706-18Operator - Principle - After Jan 1011.5862.5Inv#039 | [5 empty] | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3552 | 20200707-12 | 53510312 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 4 | Dynamic | 98.61 | 0 |  |  | 525.92 | 68.3696 | 594.2896 | 2020-07-07 | 1 | Inv#039 | 44035 | 99 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | All Season Access Maintenance on Ruby Lake Road | 3 | B110-B115 | Ruby lake Road | 0 | 44027 |  | 9 | 44033 | [5 empty] | Mandy Sandhu | 03 | Corbiere and Sons Contracting355220200707-12Dozer D6 or equal- After Jan 104525.92 | Corbiere and Sons Contracting355220200707-12Dozer D6 or equal- After Jan 104525.92Inv#039 | [5 empty] | 1 | 525.92 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3552 | 20200707-12 | 53510312 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5 | HR |  |  | 75 | 0 | 375 | 48.75 | 423.75 | 2020-07-07 | 1 | Inv#039 | 44035 | 99 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | All Season Access Maintenance on Ruby Lake Road | 3 | B110-B115 | Ruby lake Road | 0 | 44027 |  | 9 | 44033 | [5 empty] | Mandy Sandhu | 03 | Corbiere and Sons Contracting355220200707-12Operator - Principle - After Jan 105375 | Corbiere and Sons Contracting355220200707-12Operator - Principle - After Jan 105375Inv#039 | [5 empty] | 1 | 375 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3564 | 20200707-20 | 53510112 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 9.5 | Dynamic | 95.24 | 0 |  |  | 1206.31 | 156.8203 | 1363.1303 | 2020-07-07 | 1 | Inv#039 | 44035 | 99 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Eldorado and Nash | 1 | A-055 to A-084 | Eldorado | 0 | 44028 |  | 47 | 44032 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting356420200707-20Grader - Cat 12 to 14 or equal- After Jan 109.51206.31 | Corbiere and Sons Contracting356420200707-20Grader - Cat 12 to 14 or equal- After Jan 109.51206.31Inv#039 | [5 empty] | 1 | 1206.31 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3564 | 20200707-20 | 53510112 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-07-07 | 1 | Inv#039 | 44035 | 99 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Eldorado and Nash | 1 | A-055 to A-084 | Eldorado | 0 | 44028 |  | 47 | 44032 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting356420200707-20L.O.A.1210 | Corbiere and Sons Contracting356420200707-20L.O.A.1210Inv#039 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3564 | 20200707-20 | 53510112 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-07-07 | 1 | Inv#039 | 44035 | 99 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Eldorado and Nash | 1 | A-055 to A-084 | Eldorado | 0 | 44028 |  | 47 | 44032 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting356420200707-20Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting356420200707-20Operator - Principle - After Jan 1011.5862.5Inv#039 | [5 empty] | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3565 | 20200707-21 | 53510112 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 7.5 | Dynamic | 103.84 | 0 |  |  | 1038.375 | 134.9888 | 1173.3637 | 2020-07-07 | 1 | Inv#039 | 44035 | 99 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Mike finishing up at A081 and moving to A082-A084 | 1 | A-085 to A-117 | Windfarm | 0 | 44028 |  | 47 | 44032 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting356520200707-21Excavator - 30 ton- After Jan 107.51038.375 | Corbiere and Sons Contracting356520200707-21Excavator - 30 ton- After Jan 107.51038.375Inv#039 | [5 empty] | 1 | 1038.375 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3565 | 20200707-21 | 53510112 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-07-07 | 1 | Inv#039 | 44035 | 99 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Mike finishing up at A081 and moving to A082-A084 | 1 | A-085 to A-117 | Windfarm | 0 | 44028 |  | 47 | 44032 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting356520200707-21Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting356520200707-21Light Truck - Pick up- After Jan 101243.75Inv#039 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3565 | 20200707-21 | 53510112 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-07-07 | 1 | Inv#039 | 44035 | 99 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Mike finishing up at A081 and moving to A082-A084 | 1 | A-085 to A-117 | Windfarm | 0 | 44028 |  | 47 | 44032 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting356520200707-21Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting356520200707-21Operator - Principle - After Jan 1011.5862.5Inv#039 | [5 empty] | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3575 | 20200708-5 | 53510112 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 103.84 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2020-07-08 | 1 | Inv#040 | 44047 | 101 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Mike and EX005 fixing road from A096-A098; Gary and Grader across Harold and Greenwhich | 1 | A-085 to A-117 | Windfarm | 0 | 44041 |  | 37 | 44041 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting357520200708-5Excavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting357520200708-5Excavator - 30 ton- After Jan 1091246.05Inv#040 | [5 empty] | 1 | 1246.05 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3575 | 20200708-5 | 53510112 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2020-07-08 | 1 | Inv#040 | 44047 | 101 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Mike and EX005 fixing road from A096-A098; Gary and Grader across Harold and Greenwhich | 1 | A-085 to A-117 | Windfarm | 0 | 44041 |  | 37 | 44041 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting357520200708-5Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting357520200708-5Excavator Thumb - 30 - 50 ton- After Jan 109109.89Inv#040 | [5 empty] | 1 | 109.89 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3575 | 20200708-5 | 53510112 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 9.5 | Dynamic | 95.24 | 0 |  |  | 1206.31 | 156.8203 | 1363.1303 | 2020-07-08 | 1 | Inv#040 | 44047 | 101 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Mike and EX005 fixing road from A096-A098; Gary and Grader across Harold and Greenwhich | 1 | A-085 to A-117 | Windfarm | 0 | 44041 |  | 37 | 44041 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting357520200708-5Grader - Cat 12 to 14 or equal- After Jan 109.51206.31 | Corbiere and Sons Contracting357520200708-5Grader - Cat 12 to 14 or equal- After Jan 109.51206.31Inv#040 | [5 empty] | 1 | 1206.31 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3575 | 20200708-5 | 53510112 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-07-08 | 1 | Inv#040 | 44047 | 101 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Mike and EX005 fixing road from A096-A098; Gary and Grader across Harold and Greenwhich | 1 | A-085 to A-117 | Windfarm | 0 | 44041 |  | 37 | 44041 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting357520200708-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting357520200708-5Light Truck - Pick up- After Jan 101243.75Inv#040 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3575 | 20200708-5 | 53510112 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-07-08 | 1 | Inv#040 | 44047 | 101 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Mike and EX005 fixing road from A096-A098; Gary and Grader across Harold and Greenwhich | 1 | A-085 to A-117 | Windfarm | 0 | 44041 |  | 37 | 44041 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting357520200708-5L.O.A.2420 | Corbiere and Sons Contracting357520200708-5L.O.A.2420Inv#040 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3575 | 20200708-5 | 53510112 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 23 | HR |  |  | 75 | 0 | 1725 | 224.25 | 1949.25 | 2020-07-08 | 1 | Inv#040 | 44047 | 101 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Mike and EX005 fixing road from A096-A098; Gary and Grader across Harold and Greenwhich | 1 | A-085 to A-117 | Windfarm | 0 | 44041 |  | 37 | 44041 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting357520200708-5Operator - Principle - After Jan 10231725 | Corbiere and Sons Contracting357520200708-5Operator - Principle - After Jan 10231725Inv#040 | [5 empty] | 1 | 1725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3831 | 20200709-13 | 53510312 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 5 | Dynamic | 95.24 | 0 |  |  | 634.9 | 82.537 | 717.437 | 2020-07-09 | 1 | Inv#040 | 44047 | 101 | 0 | 0 | Arlene Dahl | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Lachance Road fixing up punchouts | 3 | B161-B181 | Lachance | 0 | 44041 |  | 36 | 44044 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting383120200709-13Grader - Cat 12 to 14 or equal- After Jan 105634.9 | Corbiere and Sons Contracting383120200709-13Grader - Cat 12 to 14 or equal- After Jan 105634.9Inv#040 | [5 empty] | 1 | 634.9 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3831 | 20200709-13 | 53510312 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-07-09 | 1 | Inv#040 | 44047 | 101 | 0 | 0 | Arlene Dahl | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Lachance Road fixing up punchouts | 3 | B161-B181 | Lachance | 0 | 44041 |  | 36 | 44044 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting383120200709-13L.O.A.1210 | Corbiere and Sons Contracting383120200709-13L.O.A.1210Inv#040 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3831 | 20200709-13 | 53510312 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5 | HR |  |  | 75 | 0 | 375 | 48.75 | 423.75 | 2020-07-09 | 1 | Inv#040 | 44047 | 101 | 0 | 0 | Arlene Dahl | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Lachance Road fixing up punchouts | 3 | B161-B181 | Lachance | 0 | 44041 |  | 36 | 44044 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting383120200709-13Operator - Principle - After Jan 105375 | Corbiere and Sons Contracting383120200709-13Operator - Principle - After Jan 105375Inv#040 | [5 empty] | 1 | 375 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3822 | 20200709-4 | 53510112 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9.5 | Dynamic | 103.84 | 0 |  |  | 1315.275 | 170.9857 | 1486.2607 | 2020-07-09 | 1 | Inv#040 | 44047 | 101 | 0 | 0 | Arlene Dahl | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixing road from A082-A084 | 1 | A-085 to A-117 | Windfarm | 0 | 44041 |  | 37 | 44041 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting382220200709-4Excavator - 30 ton- After Jan 109.51315.275 | Corbiere and Sons Contracting382220200709-4Excavator - 30 ton- After Jan 109.51315.275Inv#040 | [5 empty] | 1 | 1315.275 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3822 | 20200709-4 | 53510112 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9.5 | HR | 9.16 | 0 |  |  | 115.995 | 15.0793 | 131.0744 | 2020-07-09 | 1 | Inv#040 | 44047 | 101 | 0 | 0 | Arlene Dahl | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixing road from A082-A084 | 1 | A-085 to A-117 | Windfarm | 0 | 44041 |  | 37 | 44041 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting382220200709-4Excavator Thumb - 30 - 50 ton- After Jan 109.5115.995 | Corbiere and Sons Contracting382220200709-4Excavator Thumb - 30 - 50 ton- After Jan 109.5115.995Inv#040 | [5 empty] | 1 | 115.995 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3822 | 20200709-4 | 53510112 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-07-09 | 1 | Inv#040 | 44047 | 101 | 0 | 0 | Arlene Dahl | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixing road from A082-A084 | 1 | A-085 to A-117 | Windfarm | 0 | 44041 |  | 37 | 44041 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting382220200709-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting382220200709-4Light Truck - Pick up- After Jan 101243.75Inv#040 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3822 | 20200709-4 | 53510112 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-07-09 | 1 | Inv#040 | 44047 | 101 | 0 | 0 | Arlene Dahl | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixing road from A082-A084 | 1 | A-085 to A-117 | Windfarm | 0 | 44041 |  | 37 | 44041 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting382220200709-4L.O.A.1210 | Corbiere and Sons Contracting382220200709-4L.O.A.1210Inv#040 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3822 | 20200709-4 | 53510112 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-07-09 | 1 | Inv#040 | 44047 | 101 | 0 | 0 | Arlene Dahl | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixing road from A082-A084 | 1 | A-085 to A-117 | Windfarm | 0 | 44041 |  | 37 | 44041 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting382220200709-4Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting382220200709-4Operator - Principle - After Jan 1011.5862.5Inv#040 | [5 empty] | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3823 | 20200709-5 | 53510112 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 9.5 | Dynamic | 95.24 | 0 |  |  | 1206.31 | 156.8203 | 1363.1303 | 2020-07-09 | 1 | Inv#040 | 44047 | 101 | 0 | 0 | Arlene Dahl | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across access roads on Eldorado | 1 | A-055 to A-084 | Eldorado | 0 | 44041 |  | 37 | 44041 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting382320200709-5Grader - Cat 12 to 14 or equal- After Jan 109.51206.31 | Corbiere and Sons Contracting382320200709-5Grader - Cat 12 to 14 or equal- After Jan 109.51206.31Inv#040 | [5 empty] | 1 | 1206.31 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3823 | 20200709-5 | 53510112 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-07-09 | 1 | Inv#040 | 44047 | 101 | 0 | 0 | Arlene Dahl | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across access roads on Eldorado | 1 | A-055 to A-084 | Eldorado | 0 | 44041 |  | 37 | 44041 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting382320200709-5L.O.A.1210 | Corbiere and Sons Contracting382320200709-5L.O.A.1210Inv#040 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3823 | 20200709-5 | 53510112 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-07-09 | 1 | Inv#040 | 44047 | 101 | 0 | 0 | Arlene Dahl | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across access roads on Eldorado | 1 | A-055 to A-084 | Eldorado | 0 | 44041 |  | 37 | 44041 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting382320200709-5Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting382320200709-5Operator - Principle - After Jan 1011.5862.5Inv#040 | [5 empty] | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3598 | 20200710-3 | 53510112 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9.5 | Dynamic | 103.84 | 0 |  |  | 1315.275 | 170.9857 | 1486.2607 | 2020-07-10 | 1 | Inv#040 | 44047 | 101 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Mike McArthur fixing road from A083 | 1 | A-083 to A-117 | Windfarm | 0 | 44041 |  | 37 | 44041 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting359820200710-3Excavator - 30 ton- After Jan 109.51315.275 | Corbiere and Sons Contracting359820200710-3Excavator - 30 ton- After Jan 109.51315.275Inv#040 | [5 empty] | 1 | 1315.275 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3598 | 20200710-3 | 53510112 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-07-10 | 1 | Inv#040 | 44047 | 101 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Mike McArthur fixing road from A083 | 1 | A-083 to A-117 | Windfarm | 0 | 44041 |  | 37 | 44041 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting359820200710-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting359820200710-3Light Truck - Pick up- After Jan 101243.75Inv#040 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3598 | 20200710-3 | 53510112 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-07-10 | 1 | Inv#040 | 44047 | 101 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Mike McArthur fixing road from A083 | 1 | A-083 to A-117 | Windfarm | 0 | 44041 |  | 37 | 44041 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting359820200710-3L.O.A.1210 | Corbiere and Sons Contracting359820200710-3L.O.A.1210Inv#040 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3598 | 20200710-3 | 53510112 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-07-10 | 1 | Inv#040 | 44047 | 101 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Mike McArthur fixing road from A083 | 1 | A-083 to A-117 | Windfarm | 0 | 44041 |  | 37 | 44041 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting359820200710-3Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting359820200710-3Operator - Principle - After Jan 1011.5862.5Inv#040 | [5 empty] | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3601 | 20200710-6 | 53510212 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 9.5 | Dynamic | 95.24 | 0 |  |  | 1206.31 | 156.8203 | 1363.1303 | 2020-07-10 | 1 | Inv#040 | 44047 | 101 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Landfill access road | 2 | B065-B077 | Red Rock | 0 | 44041 |  | 37 | 44041 | [5 empty] | Harold Furlong | 02 | Corbiere and Sons Contracting360120200710-6Grader - Cat 12 to 14 or equal- After Jan 109.51206.31 | Corbiere and Sons Contracting360120200710-6Grader - Cat 12 to 14 or equal- After Jan 109.51206.31Inv#040 | [5 empty] | 1 | 1206.31 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3601 | 20200710-6 | 53510212 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-07-10 | 1 | Inv#040 | 44047 | 101 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Landfill access road | 2 | B065-B077 | Red Rock | 0 | 44041 |  | 37 | 44041 | [5 empty] | Harold Furlong | 02 | Corbiere and Sons Contracting360120200710-6L.O.A.1210 | Corbiere and Sons Contracting360120200710-6L.O.A.1210Inv#040 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3601 | 20200710-6 | 53510212 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-07-10 | 1 | Inv#040 | 44047 | 101 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Landfill access road | 2 | B065-B077 | Red Rock | 0 | 44041 |  | 37 | 44041 | [5 empty] | Harold Furlong | 02 | Corbiere and Sons Contracting360120200710-6Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting360120200710-6Operator - Principle - After Jan 1011.5862.5Inv#040 | [5 empty] | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3621 | 20200711-4 | 53510112 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 6.5 | Dynamic | 103.84 | 0 |  |  | 899.925 | 116.9903 | 1016.9153 | 2020-07-11 | 1 | Inv#040 | 44047 | 101 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working from A106 | 1 | A-085 to A-117 | Windfarm | 0 | 44041 |  | 37 | 44041 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting362120200711-4Excavator - 30 ton- After Jan 106.5899.925 | Corbiere and Sons Contracting362120200711-4Excavator - 30 ton- After Jan 106.5899.925Inv#040 | [5 empty] | 1 | 899.925 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3621 | 20200711-4 | 53510112 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-07-11 | 1 | Inv#040 | 44047 | 101 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working from A106 | 1 | A-085 to A-117 | Windfarm | 0 | 44041 |  | 37 | 44041 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting362120200711-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting362120200711-4Light Truck - Pick up- After Jan 101243.75Inv#040 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3621 | 20200711-4 | 53510112 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  |  | 210 | 27.3 | 237.3 | 2020-07-11 | 1 | Inv#040 | 44047 | 101 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working from A106 | 1 | A-085 to A-117 | Windfarm | 0 | 44041 |  | 37 | 44041 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting362120200711-4L.O.A.1210 | Corbiere and Sons Contracting362120200711-4L.O.A.1210Inv#040 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3621 | 20200711-4 | 53510112 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-07-11 | 1 | Inv#040 | 44047 | 101 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working from A106 | 1 | A-085 to A-117 | Windfarm | 0 | 44041 |  | 37 | 44041 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting362120200711-4Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting362120200711-4Operator - Principle - After Jan 1011.5862.5Inv#040 | [5 empty] | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3622 | 20200711-5 | 53510212 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 9.5 | Dynamic | 95.24 | 0 |  |  | 1206.31 | 156.8203 | 1363.1303 | 2020-07-11 | 1 | Inv#040 | 44047 | 101 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across access roads | 2 | B054 - B064 | Lofty Davies | 0 | 44041 |  | 37 | 44041 | [5 empty] | Harold Furlong | 02 | Corbiere and Sons Contracting362220200711-5Grader - Cat 12 to 14 or equal- After Jan 109.51206.31 | Corbiere and Sons Contracting362220200711-5Grader - Cat 12 to 14 or equal- After Jan 109.51206.31Inv#040 | [5 empty] | 1 | 1206.31 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3622 | 20200711-5 | 53510212 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-07-11 | 1 | Inv#040 | 44047 | 101 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across access roads | 2 | B054 - B064 | Lofty Davies | 0 | 44041 |  | 37 | 44041 | [5 empty] | Harold Furlong | 02 | Corbiere and Sons Contracting362220200711-5L.O.A.1210 | Corbiere and Sons Contracting362220200711-5L.O.A.1210Inv#040 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3622 | 20200711-5 | 53510212 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-07-11 | 1 | Inv#040 | 44047 | 101 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across access roads | 2 | B054 - B064 | Lofty Davies | 0 | 44041 |  | 37 | 44041 | [5 empty] | Harold Furlong | 02 | Corbiere and Sons Contracting362220200711-5Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting362220200711-5Operator - Principle - After Jan 1011.5862.5Inv#040 | [5 empty] | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3642 | 20200712-4 | 53510312 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10 | Dynamic | 98.61 | 0 |  |  | 1314.8 | 170.924 | 1485.724 | 2020-07-12 | 1 | Inv#040 | 44047 | 101 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer fixing up road on Lachance from B168 to B181 | 3 | B168-B181 | Lachance Road | 0 | 44043 |  | 36 | 44043 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting364220200712-4Dozer D6 or equal- After Jan 10101314.8 | Corbiere and Sons Contracting364220200712-4Dozer D6 or equal- After Jan 10101314.8Inv#040 | [5 empty] | 1 | 1314.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3642 | 20200712-4 | 53510312 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-07-12 | 1 | Inv#040 | 44047 | 101 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer fixing up road on Lachance from B168 to B181 | 3 | B168-B181 | Lachance Road | 0 | 44043 |  | 36 | 44043 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting364220200712-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting364220200712-4Light Truck - Pick up- After Jan 101243.75Inv#040 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3642 | 20200712-4 | 53510312 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-07-12 | 1 | Inv#040 | 44047 | 101 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer fixing up road on Lachance from B168 to B181 | 3 | B168-B181 | Lachance Road | 0 | 44043 |  | 36 | 44043 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting364220200712-4L.O.A.1210 | Corbiere and Sons Contracting364220200712-4L.O.A.1210Inv#040 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3642 | 20200712-4 | 53510312 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2020-07-12 | 1 | Inv#040 | 44047 | 101 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer fixing up road on Lachance from B168 to B181 | 3 | B168-B181 | Lachance Road | 0 | 44043 |  | 36 | 44043 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting364220200712-4Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting364220200712-4Operator - Principle - After Jan 1011825Inv#040 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3643 | 20200712-5 | 53510312 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 8 | Dynamic | 95.24 | 0 |  |  | 1015.84 | 132.0592 | 1147.8992 | 2020-07-12 | 1 | Inv#040 | 44047 | 101 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Gurney Lake Road and North Shore pit | 3 | B187-B193 | Gurney | 0 | 44043 |  | 36 | 44044 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting364320200712-5Grader - Cat 12 to 14 or equal- After Jan 1081015.84 | Corbiere and Sons Contracting364320200712-5Grader - Cat 12 to 14 or equal- After Jan 1081015.84Inv#040 | [5 empty] | 1 | 1015.84 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3643 | 20200712-5 | 53510312 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-07-12 | 1 | Inv#040 | 44047 | 101 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Gurney Lake Road and North Shore pit | 3 | B187-B193 | Gurney | 0 | 44043 |  | 36 | 44044 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting364320200712-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting364320200712-5Light Truck - Pick up- After Jan 101243.75Inv#040 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3643 | 20200712-5 | 53510312 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-07-12 | 1 | Inv#040 | 44047 | 101 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Gurney Lake Road and North Shore pit | 3 | B187-B193 | Gurney | 0 | 44043 |  | 36 | 44044 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting364320200712-5L.O.A.1210 | Corbiere and Sons Contracting364320200712-5L.O.A.1210Inv#040 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3643 | 20200712-5 | 53510312 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 8 | HR |  |  | 75 | 0 | 600 | 78 | 678 | 2020-07-12 | 1 | Inv#040 | 44047 | 101 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Gurney Lake Road and North Shore pit | 3 | B187-B193 | Gurney | 0 | 44043 |  | 36 | 44044 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting364320200712-5Operator - Principle - After Jan 108600 | Corbiere and Sons Contracting364320200712-5Operator - Principle - After Jan 108600Inv#040 | [5 empty] | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3845 | 20200713-3 | 53510112 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9.5 | Dynamic | 103.84 | 0 |  |  | 1315.275 | 170.9857 | 1486.2607 | 2020-07-13 | 1 | Inv#040 | 44047 | 101 | 0 | 0 | Arlene Dahl | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Mike and EX005 fixing road from A106 | 1 | A-085 to A-117 | Windfarm | 0 | 44041 |  | 37 | 44042 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting384520200713-3Excavator - 30 ton- After Jan 109.51315.275 | Corbiere and Sons Contracting384520200713-3Excavator - 30 ton- After Jan 109.51315.275Inv#040 | [5 empty] | 1 | 1315.275 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3845 | 20200713-3 | 53510112 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-07-13 | 1 | Inv#040 | 44047 | 101 | 0 | 0 | Arlene Dahl | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Mike and EX005 fixing road from A106 | 1 | A-085 to A-117 | Windfarm | 0 | 44041 |  | 37 | 44042 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting384520200713-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting384520200713-3Light Truck - Pick up- After Jan 101243.75Inv#040 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3845 | 20200713-3 | 53510112 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-07-13 | 1 | Inv#040 | 44047 | 101 | 0 | 0 | Arlene Dahl | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Mike and EX005 fixing road from A106 | 1 | A-085 to A-117 | Windfarm | 0 | 44041 |  | 37 | 44042 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting384520200713-3L.O.A.1210 | Corbiere and Sons Contracting384520200713-3L.O.A.1210Inv#040 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3845 | 20200713-3 | 53510112 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-07-13 | 1 | Inv#040 | 44047 | 101 | 0 | 0 | Arlene Dahl | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Mike and EX005 fixing road from A106 | 1 | A-085 to A-117 | Windfarm | 0 | 44041 |  | 37 | 44042 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting384520200713-3Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting384520200713-3Operator - Principle - After Jan 1011.5862.5Inv#040 | [5 empty] | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3846 | 20200713-4 | 53510212 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 9.5 | Dynamic | 95.24 | 0 |  |  | 1206.31 | 156.8203 | 1363.1303 | 2020-07-13 | 1 | Inv#040 | 44047 | 101 | 0 | 0 | Arlene Dahl | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across lofty davies access roads | 2 | B054 - B064 | Lofty Davies | 0 | 44041 |  | 37 | 44042 | [5 empty] | Harold Furlong | 02 | Corbiere and Sons Contracting384620200713-4Grader - Cat 12 to 14 or equal- After Jan 109.51206.31 | Corbiere and Sons Contracting384620200713-4Grader - Cat 12 to 14 or equal- After Jan 109.51206.31Inv#040 | [5 empty] | 1 | 1206.31 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3846 | 20200713-4 | 53510212 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-07-13 | 1 | Inv#040 | 44047 | 101 | 0 | 0 | Arlene Dahl | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across lofty davies access roads | 2 | B054 - B064 | Lofty Davies | 0 | 44041 |  | 37 | 44042 | [5 empty] | Harold Furlong | 02 | Corbiere and Sons Contracting384620200713-4L.O.A.1210 | Corbiere and Sons Contracting384620200713-4L.O.A.1210Inv#040 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3846 | 20200713-4 | 53510212 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-07-13 | 1 | Inv#040 | 44047 | 101 | 0 | 0 | Arlene Dahl | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across lofty davies access roads | 2 | B054 - B064 | Lofty Davies | 0 | 44041 |  | 37 | 44042 | [5 empty] | Harold Furlong | 02 | Corbiere and Sons Contracting384620200713-4Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting384620200713-4Operator - Principle - After Jan 1011.5862.5Inv#040 | [5 empty] | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3849 | 20200713-7 | 53510312 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 5 | Dynamic | 110.22 | 0 |  |  | 734.8 | 95.524 | 830.324 | 2020-07-13 | 1 | Inv#040 | 44047 | 101 | 0 | 0 | Arlene Dahl | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixing up Lachance road E - Punchouts | 3 | B161-B181 | Lachance | 0 | 44041 |  | 36 | 44042 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting384920200713-7Excavator - 36 ton- After Jan 105734.8 | Corbiere and Sons Contracting384920200713-7Excavator - 36 ton- After Jan 105734.8Inv#040 | [5 empty] | 1 | 734.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3849 | 20200713-7 | 53510312 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 5 | HR | 9.16 | 0 |  |  | 61.05 | 7.9365 | 68.9865 | 2020-07-13 | 1 | Inv#040 | 44047 | 101 | 0 | 0 | Arlene Dahl | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixing up Lachance road E - Punchouts | 3 | B161-B181 | Lachance | 0 | 44041 |  | 36 | 44042 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting384920200713-7Excavator Thumb - 30 - 50 ton- After Jan 10561.05 | Corbiere and Sons Contracting384920200713-7Excavator Thumb - 30 - 50 ton- After Jan 10561.05Inv#040 | [5 empty] | 1 | 61.05 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3849 | 20200713-7 | 53510312 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-07-13 | 1 | Inv#040 | 44047 | 101 | 0 | 0 | Arlene Dahl | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixing up Lachance road E - Punchouts | 3 | B161-B181 | Lachance | 0 | 44041 |  | 36 | 44042 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting384920200713-7Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting384920200713-7Light Truck - Pick up- After Jan 101243.75Inv#040 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3849 | 20200713-7 | 53510312 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-07-13 | 1 | Inv#040 | 44047 | 101 | 0 | 0 | Arlene Dahl | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixing up Lachance road E - Punchouts | 3 | B161-B181 | Lachance | 0 | 44041 |  | 36 | 44042 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting384920200713-7Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting384920200713-7Light Truck - Pick up- After Jan 101243.75Inv#040 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3849 | 20200713-7 | 53510312 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2020-07-13 | 1 | Inv#040 | 44047 | 101 | 0 | 0 | Arlene Dahl | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixing up Lachance road E - Punchouts | 3 | B161-B181 | Lachance | 0 | 44041 |  | 36 | 44042 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting384920200713-7L.O.A.3630 | Corbiere and Sons Contracting384920200713-7L.O.A.3630Inv#040 | [5 empty] | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3849 | 20200713-7 | 53510312 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5 | HR |  |  | 75 | 0 | 375 | 48.75 | 423.75 | 2020-07-13 | 1 | Inv#040 | 44047 | 101 | 0 | 0 | Arlene Dahl | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixing up Lachance road E - Punchouts | 3 | B161-B181 | Lachance | 0 | 44041 |  | 36 | 44042 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting384920200713-7Operator - Principle - After Jan 105375 | Corbiere and Sons Contracting384920200713-7Operator - Principle - After Jan 105375Inv#040 | [5 empty] | 1 | 375 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3849 | 20200713-7 | 53510312 | Access | 0 | Labourer - General - After Jan 10 | 60 | 5 | HR |  |  | 60 | 0 | 300 | 39 | 339 | 2020-07-13 | 1 | Inv#040 | 44047 | 101 | 0 | 0 | Arlene Dahl | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixing up Lachance road E - Punchouts | 3 | B161-B181 | Lachance | 0 | 44041 |  | 36 | 44042 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting384920200713-7Labourer - General - After Jan 105300 | Corbiere and Sons Contracting384920200713-7Labourer - General - After Jan 105300Inv#040 | [5 empty] | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3849 | 20200713-7 | 53510312 | Access | 0 | Labourer - General - After Jan 10 | 60 | 5 | HR |  |  | 60 | 0 | 300 | 39 | 339 | 2020-07-13 | 1 | Inv#040 | 44047 | 101 | 0 | 0 | Arlene Dahl | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixing up Lachance road E - Punchouts | 3 | B161-B181 | Lachance | 0 | 44041 |  | 36 | 44042 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting384920200713-7Labourer - General - After Jan 105300 | Corbiere and Sons Contracting384920200713-7Labourer - General - After Jan 105300Inv#040 | [5 empty] | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3651 | 20200714-3 | 53510112 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9.5 | Dynamic | 103.84 | 0 |  |  | 1315.275 | 170.9857 | 1486.2607 | 2020-07-14 | 1 | Inv#040 | 44047 | 101 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixing Road from A106; | 1 | A-085 to A-117 | Windfarm | 0 | 44043 |  | 37 | 44043 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting365120200714-3Excavator - 30 ton- After Jan 109.51315.275 | Corbiere and Sons Contracting365120200714-3Excavator - 30 ton- After Jan 109.51315.275Inv#040 | [5 empty] | 1 | 1315.275 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3651 | 20200714-3 | 53510112 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9.5 | HR | 9.16 | 0 |  |  | 115.995 | 15.0793 | 131.0744 | 2020-07-14 | 1 | Inv#040 | 44047 | 101 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixing Road from A106; | 1 | A-085 to A-117 | Windfarm | 0 | 44043 |  | 37 | 44043 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting365120200714-3Excavator Thumb - 30 - 50 ton- After Jan 109.5115.995 | Corbiere and Sons Contracting365120200714-3Excavator Thumb - 30 - 50 ton- After Jan 109.5115.995Inv#040 | [5 empty] | 1 | 115.995 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3651 | 20200714-3 | 53510112 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-07-14 | 1 | Inv#040 | 44047 | 101 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixing Road from A106; | 1 | A-085 to A-117 | Windfarm | 0 | 44043 |  | 37 | 44043 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting365120200714-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting365120200714-3Light Truck - Pick up- After Jan 101243.75Inv#040 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3651 | 20200714-3 | 53510112 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-07-14 | 1 | Inv#040 | 44047 | 101 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixing Road from A106; | 1 | A-085 to A-117 | Windfarm | 0 | 44043 |  | 37 | 44043 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting365120200714-3L.O.A.1210 | Corbiere and Sons Contracting365120200714-3L.O.A.1210Inv#040 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3651 | 20200714-3 | 53510112 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-07-14 | 1 | Inv#040 | 44047 | 101 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixing Road from A106; | 1 | A-085 to A-117 | Windfarm | 0 | 44043 |  | 37 | 44043 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting365120200714-3Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting365120200714-3Operator - Principle - After Jan 1011.5862.5Inv#040 | [5 empty] | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3652 | 20200714-4 | 53510212 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 8 | Dynamic | 95.24 | 0 |  |  | 1015.84 | 132.0592 | 1147.8992 | 2020-07-14 | 1 | Inv#040 | 44047 | 101 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Landfill access roads | 2 | B065-B077 | Red Rock | 0 | 44043 |  | 37 | 44043 | [5 empty] | Harold Furlong | 02 | Corbiere and Sons Contracting365220200714-4Grader - Cat 12 to 14 or equal- After Jan 1081015.84 | Corbiere and Sons Contracting365220200714-4Grader - Cat 12 to 14 or equal- After Jan 1081015.84Inv#040 | [5 empty] | 1 | 1015.84 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3652 | 20200714-4 | 53510212 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-07-14 | 1 | Inv#040 | 44047 | 101 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Landfill access roads | 2 | B065-B077 | Red Rock | 0 | 44043 |  | 37 | 44043 | [5 empty] | Harold Furlong | 02 | Corbiere and Sons Contracting365220200714-4L.O.A.1210 | Corbiere and Sons Contracting365220200714-4L.O.A.1210Inv#040 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3652 | 20200714-4 | 53510212 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 9 | HR |  |  | 75 | 0 | 675 | 87.75 | 762.75 | 2020-07-14 | 1 | Inv#040 | 44047 | 101 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Landfill access roads | 2 | B065-B077 | Red Rock | 0 | 44043 |  | 37 | 44043 | [5 empty] | Harold Furlong | 02 | Corbiere and Sons Contracting365220200714-4Operator - Principle - After Jan 109675 | Corbiere and Sons Contracting365220200714-4Operator - Principle - After Jan 109675Inv#040 | [5 empty] | 1 | 675 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3656 | 20200714-8 | 53510312 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 4 | Dynamic | 95.24 | 0 |  |  | 507.92 | 66.0296 | 573.9496 | 2020-07-14 | 1 | Inv#040 | 44047 | 101 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gurney working across Gurney Access | 3 | B187-B193 | Gurney Lake Road | 0 | 44043 |  | 36 | 44043 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting365620200714-8Grader - Cat 12 to 14 or equal- After Jan 104507.92 | Corbiere and Sons Contracting365620200714-8Grader - Cat 12 to 14 or equal- After Jan 104507.92Inv#040 | [5 empty] | 1 | 507.92 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3656 | 20200714-8 | 53510312 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 4 | HR |  |  | 75 | 0 | 300 | 39 | 339 | 2020-07-14 | 1 | Inv#040 | 44047 | 101 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gurney working across Gurney Access | 3 | B187-B193 | Gurney Lake Road | 0 | 44043 |  | 36 | 44043 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting365620200714-8Operator - Principle - After Jan 104300 | Corbiere and Sons Contracting365620200714-8Operator - Principle - After Jan 104300Inv#040 | [5 empty] | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3740 | 20200715-10 | 53510312 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 95.24 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2020-07-15 | 1 | Inv#040 | 44047 | 101 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Lachance and NS pit | 2 | B161-B181 | Lachance | 0 | 44045 |  | 36 | 44046 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting374020200715-10Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting374020200715-10Grader - Cat 12 to 14 or equal- After Jan 10101269.8Inv#040 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3740 | 20200715-10 | 53510312 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-07-15 | 1 | Inv#040 | 44047 | 101 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Lachance and NS pit | 2 | B161-B181 | Lachance | 0 | 44045 |  | 36 | 44046 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting374020200715-10Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting374020200715-10Light Truck - Pick up- After Jan 101243.75Inv#040 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3740 | 20200715-10 | 53510312 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-07-15 | 1 | Inv#040 | 44047 | 101 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Lachance and NS pit | 2 | B161-B181 | Lachance | 0 | 44045 |  | 36 | 44046 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting374020200715-10L.O.A.1210 | Corbiere and Sons Contracting374020200715-10L.O.A.1210Inv#040 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3740 | 20200715-10 | 53510312 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2020-07-15 | 1 | Inv#040 | 44047 | 101 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Lachance and NS pit | 2 | B161-B181 | Lachance | 0 | 44045 |  | 36 | 44046 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting374020200715-10Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting374020200715-10Operator - Principle - After Jan 1011825Inv#040 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3733 | 20200715-3 | 53510112 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9.5 | Dynamic | 103.84 | 0 |  |  | 1315.275 | 170.9857 | 1486.2607 | 2020-07-15 | 1 | Inv#040 | 44047 | 101 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Finished fixing road from A096 | 1 | A-085 to A-117 | Windfarm | 0 | 44045 |  | 47 | 44046 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting373320200715-3Excavator - 30 ton- After Jan 109.51315.275 | Corbiere and Sons Contracting373320200715-3Excavator - 30 ton- After Jan 109.51315.275Inv#040 | [5 empty] | 1 | 1315.275 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3733 | 20200715-3 | 53510112 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9.5 | HR | 9.16 | 0 |  |  | 115.995 | 15.0793 | 131.0744 | 2020-07-15 | 1 | Inv#040 | 44047 | 101 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Finished fixing road from A096 | 1 | A-085 to A-117 | Windfarm | 0 | 44045 |  | 47 | 44046 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting373320200715-3Excavator Thumb - 30 - 50 ton- After Jan 109.5115.995 | Corbiere and Sons Contracting373320200715-3Excavator Thumb - 30 - 50 ton- After Jan 109.5115.995Inv#040 | [5 empty] | 1 | 115.995 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3733 | 20200715-3 | 53510112 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-07-15 | 1 | Inv#040 | 44047 | 101 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Finished fixing road from A096 | 1 | A-085 to A-117 | Windfarm | 0 | 44045 |  | 47 | 44046 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting373320200715-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting373320200715-3Light Truck - Pick up- After Jan 101243.75Inv#040 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3733 | 20200715-3 | 53510112 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-07-15 | 1 | Inv#040 | 44047 | 101 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Finished fixing road from A096 | 1 | A-085 to A-117 | Windfarm | 0 | 44045 |  | 47 | 44046 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting373320200715-3L.O.A.1210 | Corbiere and Sons Contracting373320200715-3L.O.A.1210Inv#040 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3733 | 20200715-3 | 53510112 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-07-15 | 1 | Inv#040 | 44047 | 101 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Finished fixing road from A096 | 1 | A-085 to A-117 | Windfarm | 0 | 44045 |  | 47 | 44046 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting373320200715-3Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting373320200715-3Operator - Principle - After Jan 1011.5862.5Inv#040 | [5 empty] | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3734 | 20200715-4 | 53510212 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 9.5 | Dynamic | 95.24 | 0 |  |  | 1206.31 | 156.8203 | 1363.1303 | 2020-07-15 | 1 | Inv#040 | 44047 | 101 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Lofty Davies | 2 | B030 - B044 | Stewart Lake | 0 | 44045 |  | 47 | 44046 | [5 empty] | Clint Maerz | 02 | Corbiere and Sons Contracting373420200715-4Grader - Cat 12 to 14 or equal- After Jan 109.51206.31 | Corbiere and Sons Contracting373420200715-4Grader - Cat 12 to 14 or equal- After Jan 109.51206.31Inv#040 | [5 empty] | 1 | 1206.31 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3734 | 20200715-4 | 53510212 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-07-15 | 1 | Inv#040 | 44047 | 101 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Lofty Davies | 2 | B030 - B044 | Stewart Lake | 0 | 44045 |  | 47 | 44046 | [5 empty] | Clint Maerz | 02 | Corbiere and Sons Contracting373420200715-4L.O.A.1210 | Corbiere and Sons Contracting373420200715-4L.O.A.1210Inv#040 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3734 | 20200715-4 | 53510212 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-07-15 | 1 | Inv#040 | 44047 | 101 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Lofty Davies | 2 | B030 - B044 | Stewart Lake | 0 | 44045 |  | 47 | 44046 | [5 empty] | Clint Maerz | 02 | Corbiere and Sons Contracting373420200715-4Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting373420200715-4Operator - Principle - After Jan 1011.5862.5Inv#040 | [5 empty] | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3681 | 20200716-10 | 53510312 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 95.24 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2020-07-16 | 1 | Inv#040 | 44047 | 101 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Gurney Lake Road accesses | 3 | B187-B193 | Gurney Lake Road | 0 | 44043 |  | 36 | 44044 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting368120200716-10Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting368120200716-10Grader - Cat 12 to 14 or equal- After Jan 10101269.8Inv#040 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3681 | 20200716-10 | 53510312 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-07-16 | 1 | Inv#040 | 44047 | 101 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Gurney Lake Road accesses | 3 | B187-B193 | Gurney Lake Road | 0 | 44043 |  | 36 | 44044 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting368120200716-10Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting368120200716-10Light Truck - Pick up- After Jan 101243.75Inv#040 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3681 | 20200716-10 | 53510312 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-07-16 | 1 | Inv#040 | 44047 | 101 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Gurney Lake Road accesses | 3 | B187-B193 | Gurney Lake Road | 0 | 44043 |  | 36 | 44044 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting368120200716-10L.O.A.1210 | Corbiere and Sons Contracting368120200716-10L.O.A.1210Inv#040 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3681 | 20200716-10 | 53510312 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2020-07-16 | 1 | Inv#040 | 44047 | 101 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Gurney Lake Road accesses | 3 | B187-B193 | Gurney Lake Road | 0 | 44043 |  | 36 | 44044 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting368120200716-10Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting368120200716-10Operator - Principle - After Jan 1011825Inv#040 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3676 | 20200716-5 | 53510212 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 9.5 | Dynamic | 95.24 | 0 |  |  | 1206.31 | 156.8203 | 1363.1303 | 2020-07-16 | 1 | Inv#040 | 44047 | 101 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Lofty Davies accesses | 2 | B054 - B064 | Lofty Davies | 0 | 44043 |  | 47 | 44045 | [5 empty] | Clint Maerz | 02 | Corbiere and Sons Contracting367620200716-5Grader - Cat 12 to 14 or equal- After Jan 109.51206.31 | Corbiere and Sons Contracting367620200716-5Grader - Cat 12 to 14 or equal- After Jan 109.51206.31Inv#040 | [5 empty] | 1 | 1206.31 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3676 | 20200716-5 | 53510212 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-07-16 | 1 | Inv#040 | 44047 | 101 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Lofty Davies accesses | 2 | B054 - B064 | Lofty Davies | 0 | 44043 |  | 47 | 44045 | [5 empty] | Clint Maerz | 02 | Corbiere and Sons Contracting367620200716-5L.O.A.1210 | Corbiere and Sons Contracting367620200716-5L.O.A.1210Inv#040 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3676 | 20200716-5 | 53510212 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-07-16 | 1 | Inv#040 | 44047 | 101 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Lofty Davies accesses | 2 | B054 - B064 | Lofty Davies | 0 | 44043 |  | 47 | 44045 | [5 empty] | Clint Maerz | 02 | Corbiere and Sons Contracting367620200716-5Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting367620200716-5Operator - Principle - After Jan 1011.5862.5Inv#040 | [5 empty] | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3704 | 20200717-10 | 53510312 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 95.24 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2020-07-17 | 1 | Inv#040 | 44047 | 101 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Gurney Lake access | 3 | B187-B193 | Gurney lake Road | 0 | 44043 |  | 36 | 44044 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting370420200717-10Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting370420200717-10Grader - Cat 12 to 14 or equal- After Jan 10101269.8Inv#040 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3704 | 20200717-10 | 53510312 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-07-17 | 1 | Inv#040 | 44047 | 101 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Gurney Lake access | 3 | B187-B193 | Gurney lake Road | 0 | 44043 |  | 36 | 44044 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting370420200717-10L.O.A.1210 | Corbiere and Sons Contracting370420200717-10L.O.A.1210Inv#040 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3704 | 20200717-10 | 53510312 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2020-07-17 | 1 | Inv#040 | 44047 | 101 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Gurney Lake access | 3 | B187-B193 | Gurney lake Road | 0 | 44043 |  | 36 | 44044 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting370420200717-10Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting370420200717-10Operator - Principle - After Jan 1011825Inv#040 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3698 | 20200717-4 | 53510112 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 5.5 | Dynamic | 103.84 | 0 |  |  | 761.475 | 98.9917 | 860.4668 | 2020-07-17 | 1 | Inv#040 | 44047 | 101 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixing road from A037 | 1 | A-036 to A-054 | Beck Road | 0 | 44043 |  | 47 | 44044 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting369820200717-4Excavator - 30 ton- After Jan 105.5761.475 | Corbiere and Sons Contracting369820200717-4Excavator - 30 ton- After Jan 105.5761.475Inv#040 | [5 empty] | 1 | 761.475 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3698 | 20200717-4 | 53510112 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 5.5 | HR | 9.16 | 0 |  |  | 67.155 | 8.7302 | 75.8851 | 2020-07-17 | 1 | Inv#040 | 44047 | 101 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixing road from A037 | 1 | A-036 to A-054 | Beck Road | 0 | 44043 |  | 47 | 44044 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting369820200717-4Excavator Thumb - 30 - 50 ton- After Jan 105.567.155 | Corbiere and Sons Contracting369820200717-4Excavator Thumb - 30 - 50 ton- After Jan 105.567.155Inv#040 | [5 empty] | 1 | 67.155 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3698 | 20200717-4 | 53510112 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-07-17 | 1 | Inv#040 | 44047 | 101 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixing road from A037 | 1 | A-036 to A-054 | Beck Road | 0 | 44043 |  | 47 | 44044 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting369820200717-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting369820200717-4Light Truck - Pick up- After Jan 101243.75Inv#040 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3698 | 20200717-4 | 53510112 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 7.5 | HR |  |  | 75 | 0 | 562.5 | 73.125 | 635.625 | 2020-07-17 | 1 | Inv#040 | 44047 | 101 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixing road from A037 | 1 | A-036 to A-054 | Beck Road | 0 | 44043 |  | 47 | 44044 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting369820200717-4Operator - Principle - After Jan 107.5562.5 | Corbiere and Sons Contracting369820200717-4Operator - Principle - After Jan 107.5562.5Inv#040 | [5 empty] | 1 | 562.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3699 | 20200717-5 | 53510212 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 9.5 | Dynamic | 95.24 | 0 |  |  | 1206.31 | 156.8203 | 1363.1303 | 2020-07-17 | 1 | Inv#040 | 44047 | 101 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gary on grader working across Stewart Lake Road accesses | 2 | B030 - B044 | Stewart Lake | 0 | 44043 |  | 47 | 44044 | [5 empty] | Clint Maerz | 02 | Corbiere and Sons Contracting369920200717-5Grader - Cat 12 to 14 or equal- After Jan 109.51206.31 | Corbiere and Sons Contracting369920200717-5Grader - Cat 12 to 14 or equal- After Jan 109.51206.31Inv#040 | [5 empty] | 1 | 1206.31 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3699 | 20200717-5 | 53510212 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-07-17 | 1 | Inv#040 | 44047 | 101 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gary on grader working across Stewart Lake Road accesses | 2 | B030 - B044 | Stewart Lake | 0 | 44043 |  | 47 | 44044 | [5 empty] | Clint Maerz | 02 | Corbiere and Sons Contracting369920200717-5L.O.A.1210 | Corbiere and Sons Contracting369920200717-5L.O.A.1210Inv#040 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3699 | 20200717-5 | 53510212 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-07-17 | 1 | Inv#040 | 44047 | 101 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gary on grader working across Stewart Lake Road accesses | 2 | B030 - B044 | Stewart Lake | 0 | 44043 |  | 47 | 44044 | [5 empty] | Clint Maerz | 02 | Corbiere and Sons Contracting369920200717-5Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting369920200717-5Operator - Principle - After Jan 1011.5862.5Inv#040 | [5 empty] | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3703 | 20200717-9 | 53510212 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10 | Dynamic | 110.22 | 0 |  |  | 1469.6 | 191.048 | 1660.648 | 2020-07-17 | 1 | Inv#040 | 44047 | 101 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Realigning road from B035 | 2 | B030 - B044 | Stewart Lake | 0 | 44043 |  | 47 | 44044 | [5 empty] | Clint Maerz | 02 | Corbiere and Sons Contracting370320200717-9Excavator - 36 ton- After Jan 10101469.6 | Corbiere and Sons Contracting370320200717-9Excavator - 36 ton- After Jan 10101469.6Inv#040 | [5 empty] | 1 | 1469.6 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3703 | 20200717-9 | 53510212 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 9.16 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2020-07-17 | 1 | Inv#040 | 44047 | 101 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Realigning road from B035 | 2 | B030 - B044 | Stewart Lake | 0 | 44043 |  | 47 | 44044 | [5 empty] | Clint Maerz | 02 | Corbiere and Sons Contracting370320200717-9Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting370320200717-9Excavator Thumb - 30 - 50 ton- After Jan 1010122.1Inv#040 | [5 empty] | 1 | 122.1 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3703 | 20200717-9 | 53510212 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-07-17 | 1 | Inv#040 | 44047 | 101 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Realigning road from B035 | 2 | B030 - B044 | Stewart Lake | 0 | 44043 |  | 47 | 44044 | [5 empty] | Clint Maerz | 02 | Corbiere and Sons Contracting370320200717-9Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting370320200717-9Light Truck - Pick up- After Jan 101243.75Inv#040 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3703 | 20200717-9 | 53510212 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-07-17 | 1 | Inv#040 | 44047 | 101 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Realigning road from B035 | 2 | B030 - B044 | Stewart Lake | 0 | 44043 |  | 47 | 44044 | [5 empty] | Clint Maerz | 02 | Corbiere and Sons Contracting370320200717-9L.O.A.1210 | Corbiere and Sons Contracting370320200717-9L.O.A.1210Inv#040 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3703 | 20200717-9 | 53510212 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2020-07-17 | 1 | Inv#040 | 44047 | 101 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Realigning road from B035 | 2 | B030 - B044 | Stewart Lake | 0 | 44043 |  | 47 | 44044 | [5 empty] | Clint Maerz | 02 | Corbiere and Sons Contracting370320200717-9Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting370320200717-9Operator - Principle - After Jan 1011825Inv#040 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3725 | 20200718-11 | 53510312 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 6 | Dynamic | 98.61 | 0 |  |  | 788.88 | 102.5544 | 891.4344 | 2020-07-18 | 1 | Inv#040 | 44047 | 101 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Realigning Road from B136 | 3 | B136-B144 | Fire Hill Road East | 0 | 44043 |  | 36 | 44044 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting372520200718-11Dozer D6 or equal- After Jan 106788.88 | Corbiere and Sons Contracting372520200718-11Dozer D6 or equal- After Jan 106788.88Inv#040 | [5 empty] | 1 | 788.88 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3725 | 20200718-11 | 53510312 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 7.5 | Dynamic | 103.84 | 0 |  |  | 1038.375 | 134.9888 | 1173.3637 | 2020-07-18 | 1 | Inv#040 | 44047 | 101 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Realigning Road from B136 | 3 | B136-B144 | Fire Hill Road East | 0 | 44043 |  | 36 | 44044 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting372520200718-11Excavator - 30 ton- After Jan 107.51038.375 | Corbiere and Sons Contracting372520200718-11Excavator - 30 ton- After Jan 107.51038.375Inv#040 | [5 empty] | 1 | 1038.375 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3725 | 20200718-11 | 53510312 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-07-18 | 1 | Inv#040 | 44047 | 101 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Realigning Road from B136 | 3 | B136-B144 | Fire Hill Road East | 0 | 44043 |  | 36 | 44044 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting372520200718-11Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting372520200718-11Light Truck - Pick up- After Jan 101243.75Inv#040 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3725 | 20200718-11 | 53510312 | Access | 0 | Foreman | 95 | 8 | HR |  |  | 95 | 0 | 760 | 98.8 | 858.8 | 2020-07-18 | 1 | Inv#040 | 44047 | 101 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Realigning Road from B136 | 3 | B136-B144 | Fire Hill Road East | 0 | 44043 |  | 36 | 44044 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting372520200718-11Foreman8760 | Corbiere and Sons Contracting372520200718-11Foreman8760Inv#040 | [5 empty] | 1 | 760 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3725 | 20200718-11 | 53510312 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2020-07-18 | 1 | Inv#040 | 44047 | 101 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Realigning Road from B136 | 3 | B136-B144 | Fire Hill Road East | 0 | 44043 |  | 36 | 44044 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting372520200718-11L.O.A.3630 | Corbiere and Sons Contracting372520200718-11L.O.A.3630Inv#040 | [5 empty] | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3725 | 20200718-11 | 53510312 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 16 | HR |  |  | 75 | 0 | 1200 | 156 | 1356 | 2020-07-18 | 1 | Inv#040 | 44047 | 101 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Realigning Road from B136 | 3 | B136-B144 | Fire Hill Road East | 0 | 44043 |  | 36 | 44044 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting372520200718-11Operator - Principle - After Jan 10161200 | Corbiere and Sons Contracting372520200718-11Operator - Principle - After Jan 10161200Inv#040 | [5 empty] | 1 | 1200 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3717 | 20200718-3 | 53510112 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9.5 | Dynamic | 103.84 | 0 |  |  | 1315.275 | 170.9857 | 1486.2607 | 2020-07-18 | 1 | Inv#040 | 44047 | 101 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Mike fixing road from A037 | 1 | A-036 to A-054 | Beck Road | 0 | 44043 |  | 47 | 44044 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting371720200718-3Excavator - 30 ton- After Jan 109.51315.275 | Corbiere and Sons Contracting371720200718-3Excavator - 30 ton- After Jan 109.51315.275Inv#040 | [5 empty] | 1 | 1315.275 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3717 | 20200718-3 | 53510112 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9.5 | HR | 9.16 | 0 |  |  | 115.995 | 15.0793 | 131.0744 | 2020-07-18 | 1 | Inv#040 | 44047 | 101 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Mike fixing road from A037 | 1 | A-036 to A-054 | Beck Road | 0 | 44043 |  | 47 | 44044 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting371720200718-3Excavator Thumb - 30 - 50 ton- After Jan 109.5115.995 | Corbiere and Sons Contracting371720200718-3Excavator Thumb - 30 - 50 ton- After Jan 109.5115.995Inv#040 | [5 empty] | 1 | 115.995 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3717 | 20200718-3 | 53510112 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-07-18 | 1 | Inv#040 | 44047 | 101 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Mike fixing road from A037 | 1 | A-036 to A-054 | Beck Road | 0 | 44043 |  | 47 | 44044 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting371720200718-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting371720200718-3Light Truck - Pick up- After Jan 101243.75Inv#040 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3717 | 20200718-3 | 53510112 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-07-18 | 1 | Inv#040 | 44047 | 101 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Mike fixing road from A037 | 1 | A-036 to A-054 | Beck Road | 0 | 44043 |  | 47 | 44044 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting371720200718-3L.O.A.1210 | Corbiere and Sons Contracting371720200718-3L.O.A.1210Inv#040 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3717 | 20200718-3 | 53510112 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-07-18 | 1 | Inv#040 | 44047 | 101 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Mike fixing road from A037 | 1 | A-036 to A-054 | Beck Road | 0 | 44043 |  | 47 | 44044 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting371720200718-3Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting371720200718-3Operator - Principle - After Jan 1011.5862.5Inv#040 | [5 empty] | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3721 | 20200718-7 | 53510312 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 5 | Dynamic | 110.22 | 0 |  |  | 734.8 | 95.524 | 830.324 | 2020-07-18 | 1 | Inv#040 | 44047 | 101 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road realignment at B178 | 3 | B161-B181 | Lachance | 0 | 44043 |  | 36 | 44044 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting372120200718-7Excavator - 36 ton- After Jan 105734.8 | Corbiere and Sons Contracting372120200718-7Excavator - 36 ton- After Jan 105734.8Inv#040 | [5 empty] | 1 | 734.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3721 | 20200718-7 | 53510312 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 5 | HR | 9.16 | 0 |  |  | 61.05 | 7.9365 | 68.9865 | 2020-07-18 | 1 | Inv#040 | 44047 | 101 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road realignment at B178 | 3 | B161-B181 | Lachance | 0 | 44043 |  | 36 | 44044 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting372120200718-7Excavator Thumb - 30 - 50 ton- After Jan 10561.05 | Corbiere and Sons Contracting372120200718-7Excavator Thumb - 30 - 50 ton- After Jan 10561.05Inv#040 | [5 empty] | 1 | 61.05 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3721 | 20200718-7 | 53510312 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-07-18 | 1 | Inv#040 | 44047 | 101 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road realignment at B178 | 3 | B161-B181 | Lachance | 0 | 44043 |  | 36 | 44044 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting372120200718-7L.O.A.1210 | Corbiere and Sons Contracting372120200718-7L.O.A.1210Inv#040 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3721 | 20200718-7 | 53510312 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5 | HR |  |  | 75 | 0 | 375 | 48.75 | 423.75 | 2020-07-18 | 1 | Inv#040 | 44047 | 101 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road realignment at B178 | 3 | B161-B181 | Lachance | 0 | 44043 |  | 36 | 44044 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting372120200718-7Operator - Principle - After Jan 105375 | Corbiere and Sons Contracting372120200718-7Operator - Principle - After Jan 105375Inv#040 | [5 empty] | 1 | 375 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3770 | 20200719-2 | 53510112 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 7.5 | Dynamic | 103.84 | 0 |  |  | 1038.375 | 134.9888 | 1173.3637 | 2020-07-19 | 1 | Inv#040 | 44047 | 101 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Finished fixing up road from A037 | 1 | A-036 to A-054 | Beck Road | 0 | 44046 |  | 47 | 44046 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting377020200719-2Excavator - 30 ton- After Jan 107.51038.375 | Corbiere and Sons Contracting377020200719-2Excavator - 30 ton- After Jan 107.51038.375Inv#040 | [5 empty] | 1 | 1038.375 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3770 | 20200719-2 | 53510112 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 7.5 | HR | 9.16 | 0 |  |  | 91.575 | 11.9047 | 103.4797 | 2020-07-19 | 1 | Inv#040 | 44047 | 101 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Finished fixing up road from A037 | 1 | A-036 to A-054 | Beck Road | 0 | 44046 |  | 47 | 44046 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting377020200719-2Excavator Thumb - 30 - 50 ton- After Jan 107.591.575 | Corbiere and Sons Contracting377020200719-2Excavator Thumb - 30 - 50 ton- After Jan 107.591.575Inv#040 | [5 empty] | 1 | 91.575 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3770 | 20200719-2 | 53510112 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-07-19 | 1 | Inv#040 | 44047 | 101 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Finished fixing up road from A037 | 1 | A-036 to A-054 | Beck Road | 0 | 44046 |  | 47 | 44046 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting377020200719-2Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting377020200719-2Light Truck - Pick up- After Jan 101243.75Inv#040 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3770 | 20200719-2 | 53510112 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-07-19 | 1 | Inv#040 | 44047 | 101 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Finished fixing up road from A037 | 1 | A-036 to A-054 | Beck Road | 0 | 44046 |  | 47 | 44046 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting377020200719-2L.O.A.1210 | Corbiere and Sons Contracting377020200719-2L.O.A.1210Inv#040 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3770 | 20200719-2 | 53510112 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 8.5 | HR |  |  | 75 | 0 | 637.5 | 82.875 | 720.375 | 2020-07-19 | 1 | Inv#040 | 44047 | 101 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Finished fixing up road from A037 | 1 | A-036 to A-054 | Beck Road | 0 | 44046 |  | 47 | 44046 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting377020200719-2Operator - Principle - After Jan 108.5637.5 | Corbiere and Sons Contracting377020200719-2Operator - Principle - After Jan 108.5637.5Inv#040 | [5 empty] | 1 | 637.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3773 | 20200719-5 | 53510212 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 1 | Dynamic | 98.61 | 0 |  |  | 131.48 | 17.0924 | 148.5724 | 2020-07-19 | 1 | Inv#040 | 44047 | 101 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixing Road from B052-B053 | 2 | B054 - B064 | Lofty Davies | 0 | 44046 |  | 47 | 44046 | [5 empty] | Clint Maerz | 02 | Corbiere and Sons Contracting377320200719-5Dozer D6 or equal- After Jan 101131.48 | Corbiere and Sons Contracting377320200719-5Dozer D6 or equal- After Jan 101131.48Inv#040 | [5 empty] | 1 | 131.48 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3773 | 20200719-5 | 53510212 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-07-19 | 1 | Inv#040 | 44047 | 101 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixing Road from B052-B053 | 2 | B054 - B064 | Lofty Davies | 0 | 44046 |  | 47 | 44046 | [5 empty] | Clint Maerz | 02 | Corbiere and Sons Contracting377320200719-5L.O.A.1210 | Corbiere and Sons Contracting377320200719-5L.O.A.1210Inv#040 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3773 | 20200719-5 | 53510212 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 2 | HR |  |  | 75 | 0 | 150 | 19.5 | 169.5 | 2020-07-19 | 1 | Inv#040 | 44047 | 101 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixing Road from B052-B053 | 2 | B054 - B064 | Lofty Davies | 0 | 44046 |  | 47 | 44046 | [5 empty] | Clint Maerz | 02 | Corbiere and Sons Contracting377320200719-5Operator - Principle - After Jan 102150 | Corbiere and Sons Contracting377320200719-5Operator - Principle - After Jan 102150Inv#040 | [5 empty] | 1 | 150 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3804 | 20200720-4 | 53510212 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 9.5 | Dynamic | 98.61 | 0 |  |  | 1249.06 | 162.3778 | 1411.4378 | 2020-07-20 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixing road with DZ from B052-B053 | 2 | B054 - B064 | Lofty Davies | 0 | 44047 |  | 47 | 44047 | [5 empty] | Clint Maerz | 02 | Corbiere and Sons Contracting380420200720-4Dozer D6 or equal- After Jan 109.51249.06 | Corbiere and Sons Contracting380420200720-4Dozer D6 or equal- After Jan 109.51249.06Inv#043 | [5 empty] | 1 | 1249.06 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3804 | 20200720-4 | 53510212 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-07-20 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixing road with DZ from B052-B053 | 2 | B054 - B064 | Lofty Davies | 0 | 44047 |  | 47 | 44047 | [5 empty] | Clint Maerz | 02 | Corbiere and Sons Contracting380420200720-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting380420200720-4Light Truck - Pick up- After Jan 101243.75Inv#043 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3804 | 20200720-4 | 53510212 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-07-20 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixing road with DZ from B052-B053 | 2 | B054 - B064 | Lofty Davies | 0 | 44047 |  | 47 | 44047 | [5 empty] | Clint Maerz | 02 | Corbiere and Sons Contracting380420200720-4L.O.A.1210 | Corbiere and Sons Contracting380420200720-4L.O.A.1210Inv#043 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3804 | 20200720-4 | 53510212 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-07-20 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixing road with DZ from B052-B053 | 2 | B054 - B064 | Lofty Davies | 0 | 44047 |  | 47 | 44047 | [5 empty] | Clint Maerz | 02 | Corbiere and Sons Contracting380420200720-4Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting380420200720-4Operator - Principle - After Jan 1011.5862.5Inv#043 | [5 empty] | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3805 | 20200720-5 | 53510212 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 9.5 | Dynamic | 95.24 | 0 |  |  | 1206.31 | 156.8203 | 1363.1303 | 2020-07-20 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Black Sturgeon access roads | 2 | B018 - B029 | Black Sturgeon | 0 | 44047 |  | 47 | 44047 | [5 empty] | Clint Maerz | 02 | Corbiere and Sons Contracting380520200720-5Grader - Cat 12 to 14 or equal- After Jan 109.51206.31 | Corbiere and Sons Contracting380520200720-5Grader - Cat 12 to 14 or equal- After Jan 109.51206.31Inv#043 | [5 empty] | 1 | 1206.31 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3805 | 20200720-5 | 53510212 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-07-20 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Black Sturgeon access roads | 2 | B018 - B029 | Black Sturgeon | 0 | 44047 |  | 47 | 44047 | [5 empty] | Clint Maerz | 02 | Corbiere and Sons Contracting380520200720-5L.O.A.1210 | Corbiere and Sons Contracting380520200720-5L.O.A.1210Inv#043 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3805 | 20200720-5 | 53510212 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-07-20 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Black Sturgeon access roads | 2 | B018 - B029 | Black Sturgeon | 0 | 44047 |  | 47 | 44047 | [5 empty] | Clint Maerz | 02 | Corbiere and Sons Contracting380520200720-5Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting380520200720-5Operator - Principle - After Jan 1011.5862.5Inv#043 | [5 empty] | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3878 | 20200721-14 | 53510312 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 3 | Dynamic | 95.24 | 0 |  |  | 380.94 | 49.5222 | 430.4622 | 2020-07-21 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working on Gurney Lake | 3 | B187-B193 | Gurney Lake Road | 0 | 44048 |  | 37 | 44048 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting387820200721-14Grader - Cat 12 to 14 or equal- After Jan 103380.94 | Corbiere and Sons Contracting387820200721-14Grader - Cat 12 to 14 or equal- After Jan 103380.94Inv#043 | [5 empty] | 1 | 380.94 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3878 | 20200721-14 | 53510312 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 3 | HR |  |  | 75 | 0 | 225 | 29.25 | 254.25 | 2020-07-21 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working on Gurney Lake | 3 | B187-B193 | Gurney Lake Road | 0 | 44048 |  | 37 | 44048 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting387820200721-14Operator - Principle - After Jan 103225 | Corbiere and Sons Contracting387820200721-14Operator - Principle - After Jan 103225Inv#043 | [5 empty] | 1 | 225 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3867 | 20200721-3 | 53510112 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 4.5 | Dynamic | 95.24 | 0 |  |  | 571.41 | 74.2833 | 645.6933 | 2020-07-21 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working in Fish Hatchery for part of day | 1 | A-128 to B-017 | Wolf Lake | 0 | 44048 |  | 47 | 44049 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting386720200721-3Grader - Cat 12 to 14 or equal- After Jan 104.5571.41 | Corbiere and Sons Contracting386720200721-3Grader - Cat 12 to 14 or equal- After Jan 104.5571.41Inv#043 | [5 empty] | 1 | 571.41 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3867 | 20200721-3 | 53510112 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-07-21 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working in Fish Hatchery for part of day | 1 | A-128 to B-017 | Wolf Lake | 0 | 44048 |  | 47 | 44049 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting386720200721-3L.O.A.1210 | Corbiere and Sons Contracting386720200721-3L.O.A.1210Inv#043 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3867 | 20200721-3 | 53510112 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5.5 | HR |  |  | 75 | 0 | 412.5 | 53.625 | 466.125 | 2020-07-21 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working in Fish Hatchery for part of day | 1 | A-128 to B-017 | Wolf Lake | 0 | 44048 |  | 47 | 44049 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting386720200721-3Operator - Principle - After Jan 105.5412.5 | Corbiere and Sons Contracting386720200721-3Operator - Principle - After Jan 105.5412.5Inv#043 | [5 empty] | 1 | 412.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3868 | 20200721-4 | 53510212 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 5 | Dynamic | 95.24 | 0 |  |  | 634.9 | 82.537 | 717.437 | 2020-07-21 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Black Sturgeon access roads | 2 | B018 - B029 | Black Sturgeon | 0 | 44048 |  | 47 | 44049 | [5 empty] | Clint Maerz | 02 | Corbiere and Sons Contracting386820200721-4Grader - Cat 12 to 14 or equal- After Jan 105634.9 | Corbiere and Sons Contracting386820200721-4Grader - Cat 12 to 14 or equal- After Jan 105634.9Inv#043 | [5 empty] | 1 | 634.9 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3868 | 20200721-4 | 53510212 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 75 | 0 | 450 | 58.5 | 508.5 | 2020-07-21 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Black Sturgeon access roads | 2 | B018 - B029 | Black Sturgeon | 0 | 44048 |  | 47 | 44049 | [5 empty] | Clint Maerz | 02 | Corbiere and Sons Contracting386820200721-4Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting386820200721-4Operator - Principle - After Jan 106450Inv#043 | [5 empty] | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3869 | 20200721-5 | 53510212 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 9.5 | Dynamic | 98.61 | 0 |  |  | 1249.06 | 162.3778 | 1411.4378 | 2020-07-21 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixing road with DZ from B049-B051 | 2 | B045 - B053 | Squaw Valley | 0 | 44048 |  | 47 | 44049 | [5 empty] | Clint Maerz | 02 | Corbiere and Sons Contracting386920200721-5Dozer D6 or equal- After Jan 109.51249.06 | Corbiere and Sons Contracting386920200721-5Dozer D6 or equal- After Jan 109.51249.06Inv#043 | [5 empty] | 1 | 1249.06 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3869 | 20200721-5 | 53510212 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-07-21 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixing road with DZ from B049-B051 | 2 | B045 - B053 | Squaw Valley | 0 | 44048 |  | 47 | 44049 | [5 empty] | Clint Maerz | 02 | Corbiere and Sons Contracting386920200721-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting386920200721-5Light Truck - Pick up- After Jan 101243.75Inv#043 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3869 | 20200721-5 | 53510212 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-07-21 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixing road with DZ from B049-B051 | 2 | B045 - B053 | Squaw Valley | 0 | 44048 |  | 47 | 44049 | [5 empty] | Clint Maerz | 02 | Corbiere and Sons Contracting386920200721-5L.O.A.1210 | Corbiere and Sons Contracting386920200721-5L.O.A.1210Inv#043 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3869 | 20200721-5 | 53510212 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-07-21 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixing road with DZ from B049-B051 | 2 | B045 - B053 | Squaw Valley | 0 | 44048 |  | 47 | 44049 | [5 empty] | Clint Maerz | 02 | Corbiere and Sons Contracting386920200721-5Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting386920200721-5Operator - Principle - After Jan 1011.5862.5Inv#043 | [5 empty] | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3873 | 20200721-9 | 53510312 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9.5 | Dynamic | 110.22 | 0 |  |  | 1396.12 | 181.4956 | 1577.6156 | 2020-07-21 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Realigning road from B108 | 3 | B100-B109 | Doghead | 0 | 44048 |  | 37 | 44048 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting387320200721-9Excavator - 36 ton- After Jan 109.51396.12 | Corbiere and Sons Contracting387320200721-9Excavator - 36 ton- After Jan 109.51396.12Inv#043 | [5 empty] | 1 | 1396.12 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3873 | 20200721-9 | 53510312 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9.5 | HR | 9.16 | 0 |  |  | 115.995 | 15.0793 | 131.0744 | 2020-07-21 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Realigning road from B108 | 3 | B100-B109 | Doghead | 0 | 44048 |  | 37 | 44048 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting387320200721-9Excavator Thumb - 30 - 50 ton- After Jan 109.5115.995 | Corbiere and Sons Contracting387320200721-9Excavator Thumb - 30 - 50 ton- After Jan 109.5115.995Inv#043 | [5 empty] | 1 | 115.995 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3873 | 20200721-9 | 53510312 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-07-21 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Realigning road from B108 | 3 | B100-B109 | Doghead | 0 | 44048 |  | 37 | 44048 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting387320200721-9Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting387320200721-9Light Truck - Pick up- After Jan 101243.75Inv#043 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3873 | 20200721-9 | 53510312 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-07-21 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Realigning road from B108 | 3 | B100-B109 | Doghead | 0 | 44048 |  | 37 | 44048 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting387320200721-9L.O.A.1210 | Corbiere and Sons Contracting387320200721-9L.O.A.1210Inv#043 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3873 | 20200721-9 | 53510312 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-07-21 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Realigning road from B108 | 3 | B100-B109 | Doghead | 0 | 44048 |  | 37 | 44048 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting387320200721-9Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting387320200721-9Operator - Principle - After Jan 1011.5862.5Inv#043 | [5 empty] | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3886 | 20200722-3 | 53510112 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 8.5 | Dynamic | 103.84 | 0 |  |  | 1176.825 | 152.9872 | 1329.8122 | 2020-07-22 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixing road from A131-A130 | 1 | A-128 to B-017 | Wolf Lake | 0 | 44049 |  | 47 | 44051 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting388620200722-3Excavator - 30 ton- After Jan 108.51176.825 | Corbiere and Sons Contracting388620200722-3Excavator - 30 ton- After Jan 108.51176.825Inv#043 | [5 empty] | 1 | 1176.825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3886 | 20200722-3 | 53510112 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-07-22 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixing road from A131-A130 | 1 | A-128 to B-017 | Wolf Lake | 0 | 44049 |  | 47 | 44051 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting388620200722-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting388620200722-3Light Truck - Pick up- After Jan 101243.75Inv#043 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3886 | 20200722-3 | 53510112 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-07-22 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixing road from A131-A130 | 1 | A-128 to B-017 | Wolf Lake | 0 | 44049 |  | 47 | 44051 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting388620200722-3L.O.A.1210 | Corbiere and Sons Contracting388620200722-3L.O.A.1210Inv#043 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3886 | 20200722-3 | 53510112 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-07-22 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixing road from A131-A130 | 1 | A-128 to B-017 | Wolf Lake | 0 | 44049 |  | 47 | 44051 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting388620200722-3Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting388620200722-3Operator - Principle - After Jan 1011.5862.5Inv#043 | [5 empty] | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3892 | 20200722-9 | 53510312 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 95.24 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2020-07-22 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Gurney Lake Road | 3 | B187-B193 | Gurney Lake Road | 0 | 44049 |  | 37 | 44052 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting389220200722-9Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting389220200722-9Grader - Cat 12 to 14 or equal- After Jan 10101269.8Inv#043 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3892 | 20200722-9 | 53510312 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-07-22 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Gurney Lake Road | 3 | B187-B193 | Gurney Lake Road | 0 | 44049 |  | 37 | 44052 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting389220200722-9Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting389220200722-9Light Truck - Pick up- After Jan 101243.75Inv#043 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3892 | 20200722-9 | 53510312 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-07-22 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Gurney Lake Road | 3 | B187-B193 | Gurney Lake Road | 0 | 44049 |  | 37 | 44052 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting389220200722-9L.O.A.1210 | Corbiere and Sons Contracting389220200722-9L.O.A.1210Inv#043 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3892 | 20200722-9 | 53510312 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2020-07-22 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Gurney Lake Road | 3 | B187-B193 | Gurney Lake Road | 0 | 44049 |  | 37 | 44052 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting389220200722-9Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting389220200722-9Operator - Principle - After Jan 1011825Inv#043 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3903 | 20200723-3 | 53510112 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9.5 | Dynamic | 103.84 | 0 |  |  | 1315.275 | 170.9857 | 1486.2607 | 2020-07-23 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Mike fixing road from A131; Grader working on Cavern Lake Road | 1 | A-128 to B-017 | Wolf Lake | 0 | 44049 |  | 37 | 44052 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting390320200723-3Excavator - 30 ton- After Jan 109.51315.275 | Corbiere and Sons Contracting390320200723-3Excavator - 30 ton- After Jan 109.51315.275Inv#043 | [5 empty] | 1 | 1315.275 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3903 | 20200723-3 | 53510112 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9.5 | HR | 9.16 | 0 |  |  | 115.995 | 15.0793 | 131.0744 | 2020-07-23 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Mike fixing road from A131; Grader working on Cavern Lake Road | 1 | A-128 to B-017 | Wolf Lake | 0 | 44049 |  | 37 | 44052 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting390320200723-3Excavator Thumb - 30 - 50 ton- After Jan 109.5115.995 | Corbiere and Sons Contracting390320200723-3Excavator Thumb - 30 - 50 ton- After Jan 109.5115.995Inv#043 | [5 empty] | 1 | 115.995 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3903 | 20200723-3 | 53510112 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 9.5 | Dynamic | 95.24 | 0 |  |  | 1206.31 | 156.8203 | 1363.1303 | 2020-07-23 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Mike fixing road from A131; Grader working on Cavern Lake Road | 1 | A-128 to B-017 | Wolf Lake | 0 | 44049 |  | 37 | 44052 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting390320200723-3Grader - Cat 12 to 14 or equal- After Jan 109.51206.31 | Corbiere and Sons Contracting390320200723-3Grader - Cat 12 to 14 or equal- After Jan 109.51206.31Inv#043 | [5 empty] | 1 | 1206.31 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3903 | 20200723-3 | 53510112 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-07-23 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Mike fixing road from A131; Grader working on Cavern Lake Road | 1 | A-128 to B-017 | Wolf Lake | 0 | 44049 |  | 37 | 44052 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting390320200723-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting390320200723-3Light Truck - Pick up- After Jan 101243.75Inv#043 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3903 | 20200723-3 | 53510112 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-07-23 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Mike fixing road from A131; Grader working on Cavern Lake Road | 1 | A-128 to B-017 | Wolf Lake | 0 | 44049 |  | 37 | 44052 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting390320200723-3L.O.A.2420 | Corbiere and Sons Contracting390320200723-3L.O.A.2420Inv#043 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3903 | 20200723-3 | 53510112 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 23 | HR |  |  | 75 | 0 | 1725 | 224.25 | 1949.25 | 2020-07-23 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Mike fixing road from A131; Grader working on Cavern Lake Road | 1 | A-128 to B-017 | Wolf Lake | 0 | 44049 |  | 37 | 44052 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting390320200723-3Operator - Principle - After Jan 10231725 | Corbiere and Sons Contracting390320200723-3Operator - Principle - After Jan 10231725Inv#043 | [5 empty] | 1 | 1725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3922 | 20200724-4 | 53510112 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 7.5 | Dynamic | 103.84 | 0 |  |  | 1038.375 | 134.9888 | 1173.3637 | 2020-07-24 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Mike finishing road repairs from B132 - Grader working across Fish Hatchery | 1 | A-128 to B-017 | Wolf Lake | 0 | 44049 |  | 37 | 44054 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting392220200724-4Excavator - 30 ton- After Jan 107.51038.375 | Corbiere and Sons Contracting392220200724-4Excavator - 30 ton- After Jan 107.51038.375Inv#043 | [5 empty] | 1 | 1038.375 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3922 | 20200724-4 | 53510112 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 7.5 | HR | 9.16 | 0 |  |  | 91.575 | 11.9047 | 103.4797 | 2020-07-24 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Mike finishing road repairs from B132 - Grader working across Fish Hatchery | 1 | A-128 to B-017 | Wolf Lake | 0 | 44049 |  | 37 | 44054 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting392220200724-4Excavator Thumb - 30 - 50 ton- After Jan 107.591.575 | Corbiere and Sons Contracting392220200724-4Excavator Thumb - 30 - 50 ton- After Jan 107.591.575Inv#043 | [5 empty] | 1 | 91.575 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3922 | 20200724-4 | 53510112 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 9.5 | Dynamic | 95.24 | 0 |  |  | 1206.31 | 156.8203 | 1363.1303 | 2020-07-24 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Mike finishing road repairs from B132 - Grader working across Fish Hatchery | 1 | A-128 to B-017 | Wolf Lake | 0 | 44049 |  | 37 | 44054 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting392220200724-4Grader - Cat 12 to 14 or equal- After Jan 109.51206.31 | Corbiere and Sons Contracting392220200724-4Grader - Cat 12 to 14 or equal- After Jan 109.51206.31Inv#043 | [5 empty] | 1 | 1206.31 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3922 | 20200724-4 | 53510112 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-07-24 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Mike finishing road repairs from B132 - Grader working across Fish Hatchery | 1 | A-128 to B-017 | Wolf Lake | 0 | 44049 |  | 37 | 44054 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting392220200724-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting392220200724-4Light Truck - Pick up- After Jan 101243.75Inv#043 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3922 | 20200724-4 | 53510112 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-07-24 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Mike finishing road repairs from B132 - Grader working across Fish Hatchery | 1 | A-128 to B-017 | Wolf Lake | 0 | 44049 |  | 37 | 44054 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting392220200724-4L.O.A.2420 | Corbiere and Sons Contracting392220200724-4L.O.A.2420Inv#043 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3922 | 20200724-4 | 53510112 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 20.5 | HR |  |  | 75 | 0 | 1537.5 | 199.875 | 1737.375 | 2020-07-24 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Mike finishing road repairs from B132 - Grader working across Fish Hatchery | 1 | A-128 to B-017 | Wolf Lake | 0 | 44049 |  | 37 | 44054 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting392220200724-4Operator - Principle - After Jan 1020.51537.5 | Corbiere and Sons Contracting392220200724-4Operator - Principle - After Jan 1020.51537.5Inv#043 | [5 empty] | 1 | 1537.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3944 | 20200725-10 | 53510312 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9.5 | Dynamic | 110.22 | 0 |  |  | 1396.12 | 181.4956 | 1577.6156 | 2020-07-25 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance being done on Gurney Lake Road | 3 | B187-B193 | Gurney Lake Road | 0 | 44049 |  | 37 | 44054 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting394420200725-10Excavator - 36 ton- After Jan 109.51396.12 | Corbiere and Sons Contracting394420200725-10Excavator - 36 ton- After Jan 109.51396.12Inv#043 | [5 empty] | 1 | 1396.12 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3944 | 20200725-10 | 53510312 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9.5 | HR | 9.16 | 0 |  |  | 115.995 | 15.0793 | 131.0744 | 2020-07-25 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance being done on Gurney Lake Road | 3 | B187-B193 | Gurney Lake Road | 0 | 44049 |  | 37 | 44054 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting394420200725-10Excavator Thumb - 30 - 50 ton- After Jan 109.5115.995 | Corbiere and Sons Contracting394420200725-10Excavator Thumb - 30 - 50 ton- After Jan 109.5115.995Inv#043 | [5 empty] | 1 | 115.995 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3944 | 20200725-10 | 53510312 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 6 | Dynamic | 95.24 | 0 |  |  | 761.88 | 99.0444 | 860.9244 | 2020-07-25 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance being done on Gurney Lake Road | 3 | B187-B193 | Gurney Lake Road | 0 | 44049 |  | 37 | 44054 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting394420200725-10Grader - Cat 12 to 14 or equal- After Jan 106761.88 | Corbiere and Sons Contracting394420200725-10Grader - Cat 12 to 14 or equal- After Jan 106761.88Inv#043 | [5 empty] | 1 | 761.88 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3944 | 20200725-10 | 53510312 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-07-25 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance being done on Gurney Lake Road | 3 | B187-B193 | Gurney Lake Road | 0 | 44049 |  | 37 | 44054 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting394420200725-10Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting394420200725-10Light Truck - Pick up- After Jan 101243.75Inv#043 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3944 | 20200725-10 | 53510312 | Access | 0 | Foreman | 95 | 7.5 | HR |  |  | 95 | 0 | 712.5 | 92.625 | 805.125 | 2020-07-25 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance being done on Gurney Lake Road | 3 | B187-B193 | Gurney Lake Road | 0 | 44049 |  | 37 | 44054 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting394420200725-10Foreman7.5712.5 | Corbiere and Sons Contracting394420200725-10Foreman7.5712.5Inv#043 | [5 empty] | 1 | 712.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3944 | 20200725-10 | 53510312 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-07-25 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance being done on Gurney Lake Road | 3 | B187-B193 | Gurney Lake Road | 0 | 44049 |  | 37 | 44054 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting394420200725-10L.O.A.1210 | Corbiere and Sons Contracting394420200725-10L.O.A.1210Inv#043 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3944 | 20200725-10 | 53510312 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 16.5 | HR |  |  | 75 | 0 | 1237.5 | 160.875 | 1398.375 | 2020-07-25 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance being done on Gurney Lake Road | 3 | B187-B193 | Gurney Lake Road | 0 | 44049 |  | 37 | 44054 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting394420200725-10Operator - Principle - After Jan 1016.51237.5 | Corbiere and Sons Contracting394420200725-10Operator - Principle - After Jan 1016.51237.5Inv#043 | [5 empty] | 1 | 1237.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3937 | 20200725-3 | 53510112 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 9.5 | Dynamic | 95.24 | 0 |  |  | 1206.31 | 156.8203 | 1363.1303 | 2020-07-25 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across access roads in Fish Hatchery | 1 | A-128 to B-017 | Wolf Lake | 0 | 44049 |  | 37 | 44054 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting393720200725-3Grader - Cat 12 to 14 or equal- After Jan 109.51206.31 | Corbiere and Sons Contracting393720200725-3Grader - Cat 12 to 14 or equal- After Jan 109.51206.31Inv#043 | [5 empty] | 1 | 1206.31 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3937 | 20200725-3 | 53510112 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-07-25 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across access roads in Fish Hatchery | 1 | A-128 to B-017 | Wolf Lake | 0 | 44049 |  | 37 | 44054 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting393720200725-3L.O.A.1210 | Corbiere and Sons Contracting393720200725-3L.O.A.1210Inv#043 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3937 | 20200725-3 | 53510112 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-07-25 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across access roads in Fish Hatchery | 1 | A-128 to B-017 | Wolf Lake | 0 | 44049 |  | 37 | 44054 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting393720200725-3Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting393720200725-3Operator - Principle - After Jan 1011.5862.5Inv#043 | [5 empty] | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3938 | 20200725-4 | 53510212 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9.5 | Dynamic | 103.84 | 0 |  |  | 1315.275 | 170.9857 | 1486.2607 | 2020-07-25 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixing road from B066 | 2 | B065-B077 | Red Rock | 0 | 44049 |  | 37 | 44054 | [5 empty] | Harold Furlong | 02 | Corbiere and Sons Contracting393820200725-4Excavator - 30 ton- After Jan 109.51315.275 | Corbiere and Sons Contracting393820200725-4Excavator - 30 ton- After Jan 109.51315.275Inv#043 | [5 empty] | 1 | 1315.275 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3938 | 20200725-4 | 53510212 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9.5 | HR | 9.16 | 0 |  |  | 115.995 | 15.0793 | 131.0744 | 2020-07-25 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixing road from B066 | 2 | B065-B077 | Red Rock | 0 | 44049 |  | 37 | 44054 | [5 empty] | Harold Furlong | 02 | Corbiere and Sons Contracting393820200725-4Excavator Thumb - 30 - 50 ton- After Jan 109.5115.995 | Corbiere and Sons Contracting393820200725-4Excavator Thumb - 30 - 50 ton- After Jan 109.5115.995Inv#043 | [5 empty] | 1 | 115.995 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3938 | 20200725-4 | 53510212 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-07-25 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixing road from B066 | 2 | B065-B077 | Red Rock | 0 | 44049 |  | 37 | 44054 | [5 empty] | Harold Furlong | 02 | Corbiere and Sons Contracting393820200725-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting393820200725-4Light Truck - Pick up- After Jan 101243.75Inv#043 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3938 | 20200725-4 | 53510212 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-07-25 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixing road from B066 | 2 | B065-B077 | Red Rock | 0 | 44049 |  | 37 | 44054 | [5 empty] | Harold Furlong | 02 | Corbiere and Sons Contracting393820200725-4L.O.A.1210 | Corbiere and Sons Contracting393820200725-4L.O.A.1210Inv#043 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3938 | 20200725-4 | 53510212 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-07-25 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixing road from B066 | 2 | B065-B077 | Red Rock | 0 | 44049 |  | 37 | 44054 | [5 empty] | Harold Furlong | 02 | Corbiere and Sons Contracting393820200725-4Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting393820200725-4Operator - Principle - After Jan 1011.5862.5Inv#043 | [5 empty] | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3968 | 20200727-12 | 53510312 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-07-27 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Labourer cleaning up site | 3 | B187-B193 | Gurney Lake Road | 0 | 44049 |  | 37 | 44054 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting396820200727-12Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting396820200727-12Light Truck - Pick up- After Jan 101243.75Inv#043 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3968 | 20200727-12 | 53510312 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-07-27 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Labourer cleaning up site | 3 | B187-B193 | Gurney Lake Road | 0 | 44049 |  | 37 | 44054 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting396820200727-12L.O.A.1210 | Corbiere and Sons Contracting396820200727-12L.O.A.1210Inv#043 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3968 | 20200727-12 | 53510312 | Access | 0 | Labourer - General - After Jan 10 | 60 | 11 | HR |  |  | 60 | 0 | 660 | 85.8 | 745.8 | 2020-07-27 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Labourer cleaning up site | 3 | B187-B193 | Gurney Lake Road | 0 | 44049 |  | 37 | 44054 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting396820200727-12Labourer - General - After Jan 1011660 | Corbiere and Sons Contracting396820200727-12Labourer - General - After Jan 1011660Inv#043 | [5 empty] | 1 | 660 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3960 | 20200727-4 | 53520102 | Clearing | 0 | Brusher | 202.5 | 9.5 | HR | 151.88 | 0 |  |  | 1923.75 | 250.0875 | 2173.8375 | 2020-07-27 | 1 | Inv#045 | 44067 | 103 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  | Extra LOA for Jordan Messervia |  | Approved |  |  | Rake and brusher working from A071 | 1 | A-055 to A-084 | Eldorado | 0 | 44049 |  | 37 | 44060 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting396020200727-4Brusher9.51923.75 | Corbiere and Sons Contracting396020200727-4Brusher9.51923.75Inv#045 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1923.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3960 | 20200727-4 | 53520102 | Clearing | 0 | Excavator - 20 ton- After Jan 10 | 104.55 | 7 | Dynamic | 78.41 | 0 |  |  | 731.85 | 95.1405 | 826.9905 | 2020-07-27 | 1 | Inv#045 | 44067 | 103 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  | Extra LOA for Jordan Messervia |  | Approved |  |  | Rake and brusher working from A071 | 1 | A-055 to A-084 | Eldorado | 0 | 44049 |  | 37 | 44060 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting396020200727-4Excavator - 20 ton- After Jan 107731.85 | Corbiere and Sons Contracting396020200727-4Excavator - 20 ton- After Jan 107731.85Inv#045 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 731.85 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3960 | 20200727-4 | 53520102 | Clearing | 0 | Excavator Thumb - 8 -20 ton- After Jan 10 | 8.76 | 7 | HR | 6.57 | 0 |  |  | 61.32 | 7.9716 | 69.2916 | 2020-07-27 | 1 | Inv#045 | 44067 | 103 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  | Extra LOA for Jordan Messervia |  | Approved |  |  | Rake and brusher working from A071 | 1 | A-055 to A-084 | Eldorado | 0 | 44049 |  | 37 | 44060 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting396020200727-4Excavator Thumb - 8 -20 ton- After Jan 10761.32 | Corbiere and Sons Contracting396020200727-4Excavator Thumb - 8 -20 ton- After Jan 10761.32Inv#045 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 61.32 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3960 | 20200727-4 | 53520102 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2020-07-27 | 1 | Inv#045 | 44067 | 103 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  | Extra LOA for Jordan Messervia |  | Approved |  |  | Rake and brusher working from A071 | 1 | A-055 to A-084 | Eldorado | 0 | 44049 |  | 37 | 44060 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting396020200727-4Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting396020200727-4Light Truck - Pick up- After Jan 103731.25Inv#045 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 731.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3960 | 20200727-4 | 53520102 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2020-07-27 | 1 | Inv#045 | 44067 | 103 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  | Extra LOA for Jordan Messervia |  | Approved |  |  | Rake and brusher working from A071 | 1 | A-055 to A-084 | Eldorado | 0 | 44049 |  | 37 | 44060 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting396020200727-4Foreman121140 | Corbiere and Sons Contracting396020200727-4Foreman121140Inv#045 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3960 | 20200727-4 | 53520102 | Clearing | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2020-07-27 | 1 | Inv#045 | 44067 | 103 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  | Extra LOA for Jordan Messervia |  | Approved |  |  | Rake and brusher working from A071 | 1 | A-055 to A-084 | Eldorado | 0 | 44049 |  | 37 | 44060 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting396020200727-4L.O.A.3630 | Corbiere and Sons Contracting396020200727-4L.O.A.3630Inv#045 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3960 | 20200727-4 | 53520102 | Clearing | 0 | Operator - Principle - After Jan 10 | 75 | 20.5 | HR |  |  | 75 | 0 | 1537.5 | 199.875 | 1737.375 | 2020-07-27 | 1 | Inv#045 | 44067 | 103 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  | Extra LOA for Jordan Messervia |  | Approved |  |  | Rake and brusher working from A071 | 1 | A-055 to A-084 | Eldorado | 0 | 44049 |  | 37 | 44060 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting396020200727-4Operator - Principle - After Jan 1020.51537.5 | Corbiere and Sons Contracting396020200727-4Operator - Principle - After Jan 1020.51537.5Inv#045 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1537.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3960 | 20200727-4 | 53520102 | Clearing | 0 | Labourer - General - After Jan 10 | 60 | 11.5 | HR |  |  | 60 | 0 | 690 | 89.7 | 779.7 | 2020-07-27 | 1 | Inv#045 | 44067 | 103 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  | Extra LOA for Jordan Messervia |  | Approved |  |  | Rake and brusher working from A071 | 1 | A-055 to A-084 | Eldorado | 0 | 44049 |  | 37 | 44060 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting396020200727-4Labourer - General - After Jan 1011.5690 | Corbiere and Sons Contracting396020200727-4Labourer - General - After Jan 1011.5690Inv#045 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 690 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3961 | 20200727-5 | 53520102 | Clearing | 0 | Brusher | 202.5 | 4 | HR | 151.88 | 0 |  |  | 810 | 105.3 | 915.3 | 2020-07-27 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brushing starting from A128 | 1 | A-128 to B-017 | Wolf Lake | 0 | 44049 |  | 37 | 44054 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting396120200727-5Brusher4810 | Corbiere and Sons Contracting396120200727-5Brusher4810Inv#043 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 810 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3961 | 20200727-5 | 53520102 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-07-27 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brushing starting from A128 | 1 | A-128 to B-017 | Wolf Lake | 0 | 44049 |  | 37 | 44054 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting396120200727-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting396120200727-5Light Truck - Pick up- After Jan 101243.75Inv#043 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3961 | 20200727-5 | 53520102 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-07-27 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brushing starting from A128 | 1 | A-128 to B-017 | Wolf Lake | 0 | 44049 |  | 37 | 44054 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting396120200727-5L.O.A.1210 | Corbiere and Sons Contracting396120200727-5L.O.A.1210Inv#043 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3961 | 20200727-5 | 53520102 | Clearing | 0 | Operator - Principle - After Jan 10 | 75 | 4 | HR |  |  | 75 | 0 | 300 | 39 | 339 | 2020-07-27 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brushing starting from A128 | 1 | A-128 to B-017 | Wolf Lake | 0 | 44049 |  | 37 | 44054 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting396120200727-5Operator - Principle - After Jan 104300 | Corbiere and Sons Contracting396120200727-5Operator - Principle - After Jan 104300Inv#043 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3961 | 20200727-5 | 53520102 | Clearing | 0 | Labourer - General - After Jan 10 | 60 | 8 | HR |  |  | 60 | 0 | 480 | 62.4 | 542.4 | 2020-07-27 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brushing starting from A128 | 1 | A-128 to B-017 | Wolf Lake | 0 | 44049 |  | 37 | 44054 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting396120200727-5Labourer - General - After Jan 108480 | Corbiere and Sons Contracting396120200727-5Labourer - General - After Jan 108480Inv#043 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 480 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3964 | 20200727-8 | 53510212 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9.5 | Dynamic | 103.84 | 0 |  |  | 1315.275 | 170.9857 | 1486.2607 | 2020-07-27 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixing road from B077 | 2 | B065-B077 | Red Rock | 0 | 44049 |  | 37 | 44054 | [5 empty] | Harold Furlong | 02 | Corbiere and Sons Contracting396420200727-8Excavator - 30 ton- After Jan 109.51315.275 | Corbiere and Sons Contracting396420200727-8Excavator - 30 ton- After Jan 109.51315.275Inv#043 | [5 empty] | 1 | 1315.275 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3964 | 20200727-8 | 53510212 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9.5 | HR | 9.16 | 0 |  |  | 115.995 | 15.0793 | 131.0744 | 2020-07-27 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixing road from B077 | 2 | B065-B077 | Red Rock | 0 | 44049 |  | 37 | 44054 | [5 empty] | Harold Furlong | 02 | Corbiere and Sons Contracting396420200727-8Excavator Thumb - 30 - 50 ton- After Jan 109.5115.995 | Corbiere and Sons Contracting396420200727-8Excavator Thumb - 30 - 50 ton- After Jan 109.5115.995Inv#043 | [5 empty] | 1 | 115.995 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3964 | 20200727-8 | 53510212 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-07-27 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixing road from B077 | 2 | B065-B077 | Red Rock | 0 | 44049 |  | 37 | 44054 | [5 empty] | Harold Furlong | 02 | Corbiere and Sons Contracting396420200727-8Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting396420200727-8Light Truck - Pick up- After Jan 101243.75Inv#043 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3964 | 20200727-8 | 53510212 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-07-27 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixing road from B077 | 2 | B065-B077 | Red Rock | 0 | 44049 |  | 37 | 44054 | [5 empty] | Harold Furlong | 02 | Corbiere and Sons Contracting396420200727-8L.O.A.1210 | Corbiere and Sons Contracting396420200727-8L.O.A.1210Inv#043 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3964 | 20200727-8 | 53510212 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-07-27 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixing road from B077 | 2 | B065-B077 | Red Rock | 0 | 44049 |  | 37 | 44054 | [5 empty] | Harold Furlong | 02 | Corbiere and Sons Contracting396420200727-8Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting396420200727-8Operator - Principle - After Jan 1011.5862.5Inv#043 | [5 empty] | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3965 | 20200727-9 | 53510312 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 9.5 | Dynamic | 95.24 | 0 |  |  | 1206.31 | 156.8203 | 1363.1303 | 2020-07-27 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Doghead Access | 3 | B100-B109 | Doghead | 0 | 44049 |  | 37 | 44054 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting396520200727-9Grader - Cat 12 to 14 or equal- After Jan 109.51206.31 | Corbiere and Sons Contracting396520200727-9Grader - Cat 12 to 14 or equal- After Jan 109.51206.31Inv#043 | [5 empty] | 1 | 1206.31 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3965 | 20200727-9 | 53510312 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-07-27 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Doghead Access | 3 | B100-B109 | Doghead | 0 | 44049 |  | 37 | 44054 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting396520200727-9L.O.A.1210 | Corbiere and Sons Contracting396520200727-9L.O.A.1210Inv#043 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3965 | 20200727-9 | 53510312 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-07-27 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Doghead Access | 3 | B100-B109 | Doghead | 0 | 44049 |  | 37 | 44054 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting396520200727-9Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting396520200727-9Operator - Principle - After Jan 1011.5862.5Inv#043 | [5 empty] | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3975 | 20200728-3 | 53520102 | Clearing | 0 | Brusher | 202.5 | 9 | HR | 151.88 | 0 |  |  | 1822.5 | 236.925 | 2059.425 | 2020-07-28 | 1 | Inv#045 | 44067 | 103 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher and rake working from A071-A072 | 1 | A-055 to A-084 | Eldorado | 0 | 44049 |  | 37 | 44060 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting397520200728-3Brusher91822.5 | Corbiere and Sons Contracting397520200728-3Brusher91822.5Inv#045 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1822.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3975 | 20200728-3 | 53520102 | Clearing | 0 | Excavator - 20 ton- After Jan 10 | 104.55 | 9 | Dynamic | 78.41 | 0 |  |  | 940.95 | 122.3235 | 1063.2735 | 2020-07-28 | 1 | Inv#045 | 44067 | 103 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher and rake working from A071-A072 | 1 | A-055 to A-084 | Eldorado | 0 | 44049 |  | 37 | 44060 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting397520200728-3Excavator - 20 ton- After Jan 109940.95 | Corbiere and Sons Contracting397520200728-3Excavator - 20 ton- After Jan 109940.95Inv#045 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 940.95 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3975 | 20200728-3 | 53520102 | Clearing | 0 | Excavator Thumb - 8 -20 ton- After Jan 10 | 8.76 | 9 | HR | 6.57 | 0 |  |  | 78.84 | 10.2492 | 89.0892 | 2020-07-28 | 1 | Inv#045 | 44067 | 103 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher and rake working from A071-A072 | 1 | A-055 to A-084 | Eldorado | 0 | 44049 |  | 37 | 44060 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting397520200728-3Excavator Thumb - 8 -20 ton- After Jan 10978.84 | Corbiere and Sons Contracting397520200728-3Excavator Thumb - 8 -20 ton- After Jan 10978.84Inv#045 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 78.84 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3975 | 20200728-3 | 53520102 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2020-07-28 | 1 | Inv#045 | 44067 | 103 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher and rake working from A071-A072 | 1 | A-055 to A-084 | Eldorado | 0 | 44049 |  | 37 | 44060 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting397520200728-3Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting397520200728-3Light Truck - Pick up- After Jan 103731.25Inv#045 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 731.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3975 | 20200728-3 | 53520102 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2020-07-28 | 1 | Inv#045 | 44067 | 103 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher and rake working from A071-A072 | 1 | A-055 to A-084 | Eldorado | 0 | 44049 |  | 37 | 44060 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting397520200728-3Foreman121140 | Corbiere and Sons Contracting397520200728-3Foreman121140Inv#045 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3975 | 20200728-3 | 53520102 | Clearing | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2020-07-28 | 1 | Inv#045 | 44067 | 103 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher and rake working from A071-A072 | 1 | A-055 to A-084 | Eldorado | 0 | 44049 |  | 37 | 44060 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting397520200728-3L.O.A.4840 | Corbiere and Sons Contracting397520200728-3L.O.A.4840Inv#045 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3975 | 20200728-3 | 53520102 | Clearing | 0 | Operator - Principle - After Jan 10 | 75 | 23 | HR |  |  | 75 | 0 | 1725 | 224.25 | 1949.25 | 2020-07-28 | 1 | Inv#045 | 44067 | 103 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher and rake working from A071-A072 | 1 | A-055 to A-084 | Eldorado | 0 | 44049 |  | 37 | 44060 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting397520200728-3Operator - Principle - After Jan 10231725 | Corbiere and Sons Contracting397520200728-3Operator - Principle - After Jan 10231725Inv#045 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3975 | 20200728-3 | 53520102 | Clearing | 0 | Labourer - General - After Jan 10 | 60 | 11.5 | HR |  |  | 60 | 0 | 690 | 89.7 | 779.7 | 2020-07-28 | 1 | Inv#045 | 44067 | 103 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher and rake working from A071-A072 | 1 | A-055 to A-084 | Eldorado | 0 | 44049 |  | 37 | 44060 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting397520200728-3Labourer - General - After Jan 1011.5690 | Corbiere and Sons Contracting397520200728-3Labourer - General - After Jan 1011.5690Inv#045 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 690 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3976 | 20200728-4 | 53520102 | Clearing | 0 | Brusher | 202.5 | 9 | HR | 151.88 | 0 |  |  | 1822.5 | 236.925 | 2059.425 | 2020-07-28 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brushing from A129 | 1 | A-128 to B-017 | Wolf Lake | 0 | 44049 |  | 37 | 44056 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting397620200728-4Brusher91822.5 | Corbiere and Sons Contracting397620200728-4Brusher91822.5Inv#043 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1822.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3976 | 20200728-4 | 53520102 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-07-28 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brushing from A129 | 1 | A-128 to B-017 | Wolf Lake | 0 | 44049 |  | 37 | 44056 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting397620200728-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting397620200728-4Light Truck - Pick up- After Jan 101243.75Inv#043 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3976 | 20200728-4 | 53520102 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-07-28 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brushing from A129 | 1 | A-128 to B-017 | Wolf Lake | 0 | 44049 |  | 37 | 44056 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting397620200728-4L.O.A.2420 | Corbiere and Sons Contracting397620200728-4L.O.A.2420Inv#043 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3976 | 20200728-4 | 53520102 | Clearing | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-07-28 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brushing from A129 | 1 | A-128 to B-017 | Wolf Lake | 0 | 44049 |  | 37 | 44056 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting397620200728-4Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting397620200728-4Operator - Principle - After Jan 1011.5862.5Inv#043 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3976 | 20200728-4 | 53520102 | Clearing | 0 | Labourer - General - After Jan 10 | 60 | 11.5 | HR |  |  | 60 | 0 | 690 | 89.7 | 779.7 | 2020-07-28 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brushing from A129 | 1 | A-128 to B-017 | Wolf Lake | 0 | 44049 |  | 37 | 44056 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting397620200728-4Labourer - General - After Jan 1011.5690 | Corbiere and Sons Contracting397620200728-4Labourer - General - After Jan 1011.5690Inv#043 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 690 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3980 | 20200728-8 | 53510312 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 9.5 | Dynamic | 95.24 | 0 |  |  | 1206.31 | 156.8203 | 1363.1303 | 2020-07-28 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Ruby Lake Road Access | 3 | B110-B118 | Ruby Lake Road | 0 | 44049 |  | 37 | 44056 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting398020200728-8Grader - Cat 12 to 14 or equal- After Jan 109.51206.31 | Corbiere and Sons Contracting398020200728-8Grader - Cat 12 to 14 or equal- After Jan 109.51206.31Inv#043 | [5 empty] | 1 | 1206.31 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3980 | 20200728-8 | 53510312 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-07-28 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Ruby Lake Road Access | 3 | B110-B118 | Ruby Lake Road | 0 | 44049 |  | 37 | 44056 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting398020200728-8L.O.A.1210 | Corbiere and Sons Contracting398020200728-8L.O.A.1210Inv#043 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3980 | 20200728-8 | 53510312 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-07-28 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Ruby Lake Road Access | 3 | B110-B118 | Ruby Lake Road | 0 | 44049 |  | 37 | 44056 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting398020200728-8Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting398020200728-8Operator - Principle - After Jan 1011.5862.5Inv#043 | [5 empty] | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4212 | 20200729-11 | 53510312 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-07-29 | 1 | Inv#047 | 44074 | 104 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  |  | 3 | B116-B118 | Maata's Road | 0 | 44065 |  | 36 | 44070 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting421220200729-11Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting421220200729-11Light Truck - Pick up- After Jan 101243.75Inv#047 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4212 | 20200729-11 | 53510312 | Access | 0 | Light Truck w/ Tandum Trailer- After Jan 10 | 337.5 | 1 | DAY | 253.13 | 0 |  |  | 337.5 | 43.875 | 381.375 | 2020-07-29 | 1 | Inv#047 | 44074 | 104 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  |  | 3 | B116-B118 | Maata's Road | 0 | 44065 |  | 36 | 44070 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting421220200729-11Light Truck w/ Tandum Trailer- After Jan 101337.5 | Corbiere and Sons Contracting421220200729-11Light Truck w/ Tandum Trailer- After Jan 101337.5Inv#047 | [5 empty] | 1 | 337.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4212 | 20200729-11 | 53510312 | Access | 0 | Labourer - General - After Jan 10 | 60 | 22 | HR |  |  | 60 | 0 | 1320 | 171.6 | 1491.6 | 2020-07-29 | 1 | Inv#047 | 44074 | 104 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  |  | 3 | B116-B118 | Maata's Road | 0 | 44065 |  | 36 | 44070 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting421220200729-11Labourer - General - After Jan 10221320 | Corbiere and Sons Contracting421220200729-11Labourer - General - After Jan 10221320Inv#047 | [5 empty] | 1 | 1320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4212 | 20200729-11 | 53510312 | Access | 0 | 3rd Party Charges | 1 | 621.16 | unit |  |  |  |  | 621.16 | 80.7508 | 701.9108 | 2020-07-29 | 1 | Inv#047 | 44074 | 104 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  |  | 3 | B116-B118 | Maata's Road | 0 | 44065 |  | 36 | 44070 | 322 | Calcium Chloride Flakes for Road Protection |  |  |  | Mike Lecocq | 03 | Corbiere and Sons Contracting421220200729-113rd Party Charges621.16621.16 | Corbiere and Sons Contracting421220200729-113rd Party Charges621.16621.16Inv#047 | [5 empty] | 1 | 621.16 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3987 | 20200729-4 | 53520102 | Clearing | 0 | Brusher | 202.5 | 9.5 | HR | 151.88 | 0 |  |  | 1923.75 | 250.0875 | 2173.8375 | 2020-07-29 | 1 | Inv#045 | 44067 | 103 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  | Extra LOA for jordan that needs to be either removes or credited. Credit received. |  | Approved |  |  | Brusher working from A074 | 1 | A-055 to A-084 | Eldorado | 0 | 44049 |  | 37 | 44060 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting398720200729-4Brusher9.51923.75 | Corbiere and Sons Contracting398720200729-4Brusher9.51923.75Inv#045 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1923.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3987 | 20200729-4 | 53520102 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-07-29 | 1 | Inv#045 | 44067 | 103 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  | Extra LOA for jordan that needs to be either removes or credited. Credit received. |  | Approved |  |  | Brusher working from A074 | 1 | A-055 to A-084 | Eldorado | 0 | 44049 |  | 37 | 44060 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting398720200729-4Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting398720200729-4Light Truck - Pick up- After Jan 102487.5Inv#045 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3987 | 20200729-4 | 53520102 | Clearing | 0 | Foreman | 95 | 5 | HR |  |  | 95 | 0 | 475 | 61.75 | 536.75 | 2020-07-29 | 1 | Inv#045 | 44067 | 103 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  | Extra LOA for jordan that needs to be either removes or credited. Credit received. |  | Approved |  |  | Brusher working from A074 | 1 | A-055 to A-084 | Eldorado | 0 | 44049 |  | 37 | 44060 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting398720200729-4Foreman5475 | Corbiere and Sons Contracting398720200729-4Foreman5475Inv#045 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 475 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3987 | 20200729-4 | 53520102 | Clearing | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2020-07-29 | 1 | Inv#045 | 44067 | 103 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  | Extra LOA for jordan that needs to be either removes or credited. Credit received. |  | Approved |  |  | Brusher working from A074 | 1 | A-055 to A-084 | Eldorado | 0 | 44049 |  | 37 | 44060 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting398720200729-4L.O.A.3630 | Corbiere and Sons Contracting398720200729-4L.O.A.3630Inv#045 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3987 | 20200729-4 | 53520102 | Clearing | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-07-29 | 1 | Inv#045 | 44067 | 103 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  | Extra LOA for jordan that needs to be either removes or credited. Credit received. |  | Approved |  |  | Brusher working from A074 | 1 | A-055 to A-084 | Eldorado | 0 | 44049 |  | 37 | 44060 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting398720200729-4Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting398720200729-4Operator - Principle - After Jan 1011.5862.5Inv#045 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3987 | 20200729-4 | 53520102 | Clearing | 0 | Labourer - General - After Jan 10 | 60 | 11.5 | HR |  |  | 60 | 0 | 690 | 89.7 | 779.7 | 2020-07-29 | 1 | Inv#045 | 44067 | 103 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  | Extra LOA for jordan that needs to be either removes or credited. Credit received. |  | Approved |  |  | Brusher working from A074 | 1 | A-055 to A-084 | Eldorado | 0 | 44049 |  | 37 | 44060 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting398720200729-4Labourer - General - After Jan 1011.5690 | Corbiere and Sons Contracting398720200729-4Labourer - General - After Jan 1011.5690Inv#045 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 690 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3988 | 20200729-5 | 53520102 | Clearing | 0 | Brusher | 202.5 | 4 | HR | 151.88 | 0 |  |  | 810 | 105.3 | 915.3 | 2020-07-29 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher working from A128 | 1 | A-128 to B-017 | Wolf Lake | 0 | 44049 |  | 37 | 44056 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting398820200729-5Brusher4810 | Corbiere and Sons Contracting398820200729-5Brusher4810Inv#043 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 810 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3988 | 20200729-5 | 53520102 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-07-29 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher working from A128 | 1 | A-128 to B-017 | Wolf Lake | 0 | 44049 |  | 37 | 44056 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting398820200729-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting398820200729-5Light Truck - Pick up- After Jan 101243.75Inv#043 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3988 | 20200729-5 | 53520102 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-07-29 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher working from A128 | 1 | A-128 to B-017 | Wolf Lake | 0 | 44049 |  | 37 | 44056 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting398820200729-5L.O.A.2420 | Corbiere and Sons Contracting398820200729-5L.O.A.2420Inv#043 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3988 | 20200729-5 | 53520102 | Clearing | 0 | Operator - Principle - After Jan 10 | 75 | 5 | HR |  |  | 75 | 0 | 375 | 48.75 | 423.75 | 2020-07-29 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher working from A128 | 1 | A-128 to B-017 | Wolf Lake | 0 | 44049 |  | 37 | 44056 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting398820200729-5Operator - Principle - After Jan 105375 | Corbiere and Sons Contracting398820200729-5Operator - Principle - After Jan 105375Inv#043 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 375 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3988 | 20200729-5 | 53520102 | Clearing | 0 | Labourer - General - After Jan 10 | 60 | 5 | HR |  |  | 60 | 0 | 300 | 39 | 339 | 2020-07-29 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher working from A128 | 1 | A-128 to B-017 | Wolf Lake | 0 | 44049 |  | 37 | 44056 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting398820200729-5Labourer - General - After Jan 105300 | Corbiere and Sons Contracting398820200729-5Labourer - General - After Jan 105300Inv#043 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3989 | 20200729-6 | 53510312 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 9.5 | Dynamic | 95.24 | 0 |  |  | 1206.31 | 156.8203 | 1363.1303 | 2020-07-29 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Fire Hill Road E | 3 | B136-B144 | Fire Hill Road E | 0 | 44049 |  | 37 | 44056 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting398920200729-6Grader - Cat 12 to 14 or equal- After Jan 109.51206.31 | Corbiere and Sons Contracting398920200729-6Grader - Cat 12 to 14 or equal- After Jan 109.51206.31Inv#043 | [5 empty] | 1 | 1206.31 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3989 | 20200729-6 | 53510312 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-07-29 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Fire Hill Road E | 3 | B136-B144 | Fire Hill Road E | 0 | 44049 |  | 37 | 44056 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting398920200729-6L.O.A.1210 | Corbiere and Sons Contracting398920200729-6L.O.A.1210Inv#043 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3989 | 20200729-6 | 53510312 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-07-29 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Fire Hill Road E | 3 | B136-B144 | Fire Hill Road E | 0 | 44049 |  | 37 | 44056 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting398920200729-6Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting398920200729-6Operator - Principle - After Jan 1011.5862.5Inv#043 | [5 empty] | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3996 | 20200730-3 | 53520102 | Clearing | 0 | Brusher | 202.5 | 6 | HR | 151.88 | 0 |  |  | 1215 | 157.95 | 1372.95 | 2020-07-30 | 1 | Inv#045 | 44067 | 103 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  | Extra LOA for Jordan Mess that needs to be either removed or credited, credit received on another LEM. |  | Approved |  |  | Brusher and Rake working from A074 | 1 | A-055 to A-084 | Eldorado | 0 | 44049 |  | 37 | 44060 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting399620200730-3Brusher61215 | Corbiere and Sons Contracting399620200730-3Brusher61215Inv#045 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1215 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3996 | 20200730-3 | 53520102 | Clearing | 0 | Excavator - 20 ton- After Jan 10 | 104.55 | 9.5 | Dynamic | 78.41 | 0 |  |  | 993.225 | 129.1192 | 1122.3443 | 2020-07-30 | 1 | Inv#045 | 44067 | 103 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  | Extra LOA for Jordan Mess that needs to be either removed or credited, credit received on another LEM. |  | Approved |  |  | Brusher and Rake working from A074 | 1 | A-055 to A-084 | Eldorado | 0 | 44049 |  | 37 | 44060 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting399620200730-3Excavator - 20 ton- After Jan 109.5993.225 | Corbiere and Sons Contracting399620200730-3Excavator - 20 ton- After Jan 109.5993.225Inv#045 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 993.225 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3996 | 20200730-3 | 53520102 | Clearing | 0 | Excavator Thumb - 8 -20 ton- After Jan 10 | 8.76 | 9.5 | HR | 6.57 | 0 |  |  | 83.22 | 10.8186 | 94.0386 | 2020-07-30 | 1 | Inv#045 | 44067 | 103 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  | Extra LOA for Jordan Mess that needs to be either removed or credited, credit received on another LEM. |  | Approved |  |  | Brusher and Rake working from A074 | 1 | A-055 to A-084 | Eldorado | 0 | 44049 |  | 37 | 44060 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting399620200730-3Excavator Thumb - 8 -20 ton- After Jan 109.583.22 | Corbiere and Sons Contracting399620200730-3Excavator Thumb - 8 -20 ton- After Jan 109.583.22Inv#045 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 83.22 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3996 | 20200730-3 | 53520102 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-07-30 | 1 | Inv#045 | 44067 | 103 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  | Extra LOA for Jordan Mess that needs to be either removed or credited, credit received on another LEM. |  | Approved |  |  | Brusher and Rake working from A074 | 1 | A-055 to A-084 | Eldorado | 0 | 44049 |  | 37 | 44060 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting399620200730-3Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting399620200730-3Light Truck - Pick up- After Jan 102487.5Inv#045 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3996 | 20200730-3 | 53520102 | Clearing | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2020-07-30 | 1 | Inv#045 | 44067 | 103 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  | Extra LOA for Jordan Mess that needs to be either removed or credited, credit received on another LEM. |  | Approved |  |  | Brusher and Rake working from A074 | 1 | A-055 to A-084 | Eldorado | 0 | 44049 |  | 37 | 44060 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting399620200730-3L.O.A.3630 | Corbiere and Sons Contracting399620200730-3L.O.A.3630Inv#045 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3996 | 20200730-3 | 53520102 | Clearing | 0 | Operator - Principle - After Jan 10 | 75 | 23 | HR |  |  | 75 | 0 | 1725 | 224.25 | 1949.25 | 2020-07-30 | 1 | Inv#045 | 44067 | 103 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  | Extra LOA for Jordan Mess that needs to be either removed or credited, credit received on another LEM. |  | Approved |  |  | Brusher and Rake working from A074 | 1 | A-055 to A-084 | Eldorado | 0 | 44049 |  | 37 | 44060 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting399620200730-3Operator - Principle - After Jan 10231725 | Corbiere and Sons Contracting399620200730-3Operator - Principle - After Jan 10231725Inv#045 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3996 | 20200730-3 | 53520102 | Clearing | 0 | Labourer - General - After Jan 10 | 60 | 11.5 | HR |  |  | 60 | 0 | 690 | 89.7 | 779.7 | 2020-07-30 | 1 | Inv#045 | 44067 | 103 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  | Extra LOA for Jordan Mess that needs to be either removed or credited, credit received on another LEM. |  | Approved |  |  | Brusher and Rake working from A074 | 1 | A-055 to A-084 | Eldorado | 0 | 44049 |  | 37 | 44060 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting399620200730-3Labourer - General - After Jan 1011.5690 | Corbiere and Sons Contracting399620200730-3Labourer - General - After Jan 1011.5690Inv#045 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 690 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3997 | 20200730-4 | 53520102 | Clearing | 0 | Brusher | 202.5 | 9.5 | HR | 151.88 | 0 |  |  | 1923.75 | 250.0875 | 2173.8375 | 2020-07-30 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Raking and Brushing from A129 | 1 | A-128 to B-017 | Wolf Lake | 0 | 44049 |  | 37 | 44056 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting399720200730-4Brusher9.51923.75 | Corbiere and Sons Contracting399720200730-4Brusher9.51923.75Inv#043 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1923.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3997 | 20200730-4 | 53520102 | Clearing | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 6 | Dynamic | 110.22 | 0 |  |  | 881.76 | 114.6288 | 996.3888 | 2020-07-30 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Raking and Brushing from A129 | 1 | A-128 to B-017 | Wolf Lake | 0 | 44049 |  | 37 | 44056 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting399720200730-4Excavator - 36 ton- After Jan 106881.76 | Corbiere and Sons Contracting399720200730-4Excavator - 36 ton- After Jan 106881.76Inv#043 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 881.76 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3997 | 20200730-4 | 53520102 | Clearing | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 6 | HR | 9.16 | 0 |  |  | 73.26 | 9.5238 | 82.7838 | 2020-07-30 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Raking and Brushing from A129 | 1 | A-128 to B-017 | Wolf Lake | 0 | 44049 |  | 37 | 44056 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting399720200730-4Excavator Thumb - 30 - 50 ton- After Jan 10673.26 | Corbiere and Sons Contracting399720200730-4Excavator Thumb - 30 - 50 ton- After Jan 10673.26Inv#043 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 73.26 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3997 | 20200730-4 | 53520102 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2020-07-30 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Raking and Brushing from A129 | 1 | A-128 to B-017 | Wolf Lake | 0 | 44049 |  | 37 | 44056 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting399720200730-4Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting399720200730-4Light Truck - Pick up- After Jan 103731.25Inv#043 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 731.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3997 | 20200730-4 | 53520102 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2020-07-30 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Raking and Brushing from A129 | 1 | A-128 to B-017 | Wolf Lake | 0 | 44049 |  | 37 | 44056 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting399720200730-4Foreman121140 | Corbiere and Sons Contracting399720200730-4Foreman121140Inv#043 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3997 | 20200730-4 | 53520102 | Clearing | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2020-07-30 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Raking and Brushing from A129 | 1 | A-128 to B-017 | Wolf Lake | 0 | 44049 |  | 37 | 44056 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting399720200730-4L.O.A.4840 | Corbiere and Sons Contracting399720200730-4L.O.A.4840Inv#043 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3997 | 20200730-4 | 53520102 | Clearing | 0 | Operator - Principle - After Jan 10 | 75 | 18.5 | HR |  |  | 75 | 0 | 1387.5 | 180.375 | 1567.875 | 2020-07-30 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Raking and Brushing from A129 | 1 | A-128 to B-017 | Wolf Lake | 0 | 44049 |  | 37 | 44056 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting399720200730-4Operator - Principle - After Jan 1018.51387.5 | Corbiere and Sons Contracting399720200730-4Operator - Principle - After Jan 1018.51387.5Inv#043 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1387.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3997 | 20200730-4 | 53520102 | Clearing | 0 | Labourer - General - After Jan 10 | 60 | 11.5 | HR |  |  | 60 | 0 | 690 | 89.7 | 779.7 | 2020-07-30 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Raking and Brushing from A129 | 1 | A-128 to B-017 | Wolf Lake | 0 | 44049 |  | 37 | 44056 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting399720200730-4Labourer - General - After Jan 1011.5690 | Corbiere and Sons Contracting399720200730-4Labourer - General - After Jan 1011.5690Inv#043 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 690 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3999 | 20200730-6 | 53510212 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9.5 | Dynamic | 103.84 | 0 |  |  | 1315.275 | 170.9857 | 1486.2607 | 2020-07-30 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  |  | 2 | B065-B077 | Red Rock | 0 | 44049 |  | 37 | 44056 | [5 empty] | Harold Furlong | 02 | Corbiere and Sons Contracting399920200730-6Excavator - 30 ton- After Jan 109.51315.275 | Corbiere and Sons Contracting399920200730-6Excavator - 30 ton- After Jan 109.51315.275Inv#043 | [5 empty] | 1 | 1315.275 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3999 | 20200730-6 | 53510212 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9.5 | HR | 9.16 | 0 |  |  | 115.995 | 15.0793 | 131.0744 | 2020-07-30 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  |  | 2 | B065-B077 | Red Rock | 0 | 44049 |  | 37 | 44056 | [5 empty] | Harold Furlong | 02 | Corbiere and Sons Contracting399920200730-6Excavator Thumb - 30 - 50 ton- After Jan 109.5115.995 | Corbiere and Sons Contracting399920200730-6Excavator Thumb - 30 - 50 ton- After Jan 109.5115.995Inv#043 | [5 empty] | 1 | 115.995 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3999 | 20200730-6 | 53510212 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-07-30 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  |  | 2 | B065-B077 | Red Rock | 0 | 44049 |  | 37 | 44056 | [5 empty] | Harold Furlong | 02 | Corbiere and Sons Contracting399920200730-6Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting399920200730-6Light Truck - Pick up- After Jan 101243.75Inv#043 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3999 | 20200730-6 | 53510212 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-07-30 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  |  | 2 | B065-B077 | Red Rock | 0 | 44049 |  | 37 | 44056 | [5 empty] | Harold Furlong | 02 | Corbiere and Sons Contracting399920200730-6L.O.A.1210 | Corbiere and Sons Contracting399920200730-6L.O.A.1210Inv#043 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 3999 | 20200730-6 | 53510212 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-07-30 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  |  | 2 | B065-B077 | Red Rock | 0 | 44049 |  | 37 | 44056 | [5 empty] | Harold Furlong | 02 | Corbiere and Sons Contracting399920200730-6Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting399920200730-6Operator - Principle - After Jan 1011.5862.5Inv#043 | [5 empty] | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4001 | 20200730-8 | 53510312 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 7.5 | Dynamic | 95.24 | 0 |  |  | 952.35 | 123.8055 | 1076.1555 | 2020-07-30 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Gurney Lake Road | 3 | B187-B193 | Gurney Lake Road | 0 | 44049 |  | 37 | 44056 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting400120200730-8Grader - Cat 12 to 14 or equal- After Jan 107.5952.35 | Corbiere and Sons Contracting400120200730-8Grader - Cat 12 to 14 or equal- After Jan 107.5952.35Inv#043 | [5 empty] | 1 | 952.35 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4001 | 20200730-8 | 53510312 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-07-30 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Gurney Lake Road | 3 | B187-B193 | Gurney Lake Road | 0 | 44049 |  | 37 | 44056 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting400120200730-8L.O.A.1210 | Corbiere and Sons Contracting400120200730-8L.O.A.1210Inv#043 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4001 | 20200730-8 | 53510312 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 9.5 | HR |  |  | 75 | 0 | 712.5 | 92.625 | 805.125 | 2020-07-30 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Gurney Lake Road | 3 | B187-B193 | Gurney Lake Road | 0 | 44049 |  | 37 | 44056 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting400120200730-8Operator - Principle - After Jan 109.5712.5 | Corbiere and Sons Contracting400120200730-8Operator - Principle - After Jan 109.5712.5Inv#043 | [5 empty] | 1 | 712.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4002 | 20200730-9 | 53510312 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 2 | Dynamic | 98.61 | 0 |  |  | 262.96 | 34.1848 | 297.1448 | 2020-07-30 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road repairs with DZ | 3 | B136-B144 | Fire Hill Road E | 0 | 44049 |  | 37 | 44056 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting400220200730-9Dozer D6 or equal- After Jan 102262.96 | Corbiere and Sons Contracting400220200730-9Dozer D6 or equal- After Jan 102262.96Inv#043 | [5 empty] | 1 | 262.96 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4002 | 20200730-9 | 53510312 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-07-30 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road repairs with DZ | 3 | B136-B144 | Fire Hill Road E | 0 | 44049 |  | 37 | 44056 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting400220200730-9Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting400220200730-9Light Truck - Pick up- After Jan 101243.75Inv#043 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4002 | 20200730-9 | 53510312 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 2 | HR |  |  | 75 | 0 | 150 | 19.5 | 169.5 | 2020-07-30 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road repairs with DZ | 3 | B136-B144 | Fire Hill Road E | 0 | 44049 |  | 37 | 44056 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting400220200730-9Operator - Principle - After Jan 102150 | Corbiere and Sons Contracting400220200730-9Operator - Principle - After Jan 102150Inv#043 | [5 empty] | 1 | 150 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4017 | 20200731-4 | 53520102 | Clearing | 0 | Brusher | 202.5 | 9.5 | HR | 151.88 | 0 |  |  | 1923.75 | 250.0875 | 2173.8375 | 2020-07-31 | 1 | Inv#045 | 44067 | 103 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  | Extra LOA for Jordan Messrvia needs to be removed. Credit received on another LEM |  | Approved |  |  | Brusher and Rake working from A074-A075 | 1 | A-055 to A-084 | Eldorado | 0 | 44049 |  | 37 | 44060 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting401720200731-4Brusher9.51923.75 | Corbiere and Sons Contracting401720200731-4Brusher9.51923.75Inv#045 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1923.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4017 | 20200731-4 | 53520102 | Clearing | 0 | Excavator - 20 ton- After Jan 10 | 104.55 | 7.5 | Dynamic | 78.41 | 0 |  |  | 784.125 | 101.9363 | 886.0612 | 2020-07-31 | 1 | Inv#045 | 44067 | 103 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  | Extra LOA for Jordan Messrvia needs to be removed. Credit received on another LEM |  | Approved |  |  | Brusher and Rake working from A074-A075 | 1 | A-055 to A-084 | Eldorado | 0 | 44049 |  | 37 | 44060 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting401720200731-4Excavator - 20 ton- After Jan 107.5784.125 | Corbiere and Sons Contracting401720200731-4Excavator - 20 ton- After Jan 107.5784.125Inv#045 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 784.125 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4017 | 20200731-4 | 53520102 | Clearing | 0 | Excavator Thumb - 8 -20 ton- After Jan 10 | 8.76 | 7.5 | HR | 6.57 | 0 |  |  | 65.7 | 8.541 | 74.241 | 2020-07-31 | 1 | Inv#045 | 44067 | 103 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  | Extra LOA for Jordan Messrvia needs to be removed. Credit received on another LEM |  | Approved |  |  | Brusher and Rake working from A074-A075 | 1 | A-055 to A-084 | Eldorado | 0 | 44049 |  | 37 | 44060 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting401720200731-4Excavator Thumb - 8 -20 ton- After Jan 107.565.7 | Corbiere and Sons Contracting401720200731-4Excavator Thumb - 8 -20 ton- After Jan 107.565.7Inv#045 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 65.7 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4017 | 20200731-4 | 53520102 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-07-31 | 1 | Inv#045 | 44067 | 103 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  | Extra LOA for Jordan Messrvia needs to be removed. Credit received on another LEM |  | Approved |  |  | Brusher and Rake working from A074-A075 | 1 | A-055 to A-084 | Eldorado | 0 | 44049 |  | 37 | 44060 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting401720200731-4Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting401720200731-4Light Truck - Pick up- After Jan 102487.5Inv#045 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4017 | 20200731-4 | 53520102 | Clearing | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2020-07-31 | 1 | Inv#045 | 44067 | 103 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  | Extra LOA for Jordan Messrvia needs to be removed. Credit received on another LEM |  | Approved |  |  | Brusher and Rake working from A074-A075 | 1 | A-055 to A-084 | Eldorado | 0 | 44049 |  | 37 | 44060 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting401720200731-4L.O.A.3630 | Corbiere and Sons Contracting401720200731-4L.O.A.3630Inv#045 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4017 | 20200731-4 | 53520102 | Clearing | 0 | Operator - Principle - After Jan 10 | 75 | 21 | HR |  |  | 75 | 0 | 1575 | 204.75 | 1779.75 | 2020-07-31 | 1 | Inv#045 | 44067 | 103 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  | Extra LOA for Jordan Messrvia needs to be removed. Credit received on another LEM |  | Approved |  |  | Brusher and Rake working from A074-A075 | 1 | A-055 to A-084 | Eldorado | 0 | 44049 |  | 37 | 44060 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting401720200731-4Operator - Principle - After Jan 10211575 | Corbiere and Sons Contracting401720200731-4Operator - Principle - After Jan 10211575Inv#045 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1575 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4017 | 20200731-4 | 53520102 | Clearing | 0 | Labourer - General - After Jan 10 | 60 | 11.5 | HR |  |  | 60 | 0 | 690 | 89.7 | 779.7 | 2020-07-31 | 1 | Inv#045 | 44067 | 103 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  | Extra LOA for Jordan Messrvia needs to be removed. Credit received on another LEM |  | Approved |  |  | Brusher and Rake working from A074-A075 | 1 | A-055 to A-084 | Eldorado | 0 | 44049 |  | 37 | 44060 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting401720200731-4Labourer - General - After Jan 1011.5690 | Corbiere and Sons Contracting401720200731-4Labourer - General - After Jan 1011.5690Inv#045 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 690 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4018 | 20200731-5 | 53520102 | Clearing | 0 | Brusher | 202.5 | 9.5 | HR | 151.88 | 0 |  |  | 1923.75 | 250.0875 | 2173.8375 | 2020-07-31 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brushing and Raking from A130-A131 | 1 | A-128 to B-017 | Wolf Lake | 0 | 44049 |  | 37 | 44056 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting401820200731-5Brusher9.51923.75 | Corbiere and Sons Contracting401820200731-5Brusher9.51923.75Inv#043 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1923.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4018 | 20200731-5 | 53520102 | Clearing | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9.5 | Dynamic | 103.84 | 0 |  |  | 1315.275 | 170.9857 | 1486.2607 | 2020-07-31 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brushing and Raking from A130-A131 | 1 | A-128 to B-017 | Wolf Lake | 0 | 44049 |  | 37 | 44056 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting401820200731-5Excavator - 30 ton- After Jan 109.51315.275 | Corbiere and Sons Contracting401820200731-5Excavator - 30 ton- After Jan 109.51315.275Inv#043 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1315.275 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4018 | 20200731-5 | 53520102 | Clearing | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9.5 | HR | 9.16 | 0 |  |  | 115.995 | 15.0793 | 131.0744 | 2020-07-31 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brushing and Raking from A130-A131 | 1 | A-128 to B-017 | Wolf Lake | 0 | 44049 |  | 37 | 44056 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting401820200731-5Excavator Thumb - 30 - 50 ton- After Jan 109.5115.995 | Corbiere and Sons Contracting401820200731-5Excavator Thumb - 30 - 50 ton- After Jan 109.5115.995Inv#043 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 115.995 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4018 | 20200731-5 | 53520102 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2020-07-31 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brushing and Raking from A130-A131 | 1 | A-128 to B-017 | Wolf Lake | 0 | 44049 |  | 37 | 44056 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting401820200731-5Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting401820200731-5Light Truck - Pick up- After Jan 103731.25Inv#043 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 731.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4018 | 20200731-5 | 53520102 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2020-07-31 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brushing and Raking from A130-A131 | 1 | A-128 to B-017 | Wolf Lake | 0 | 44049 |  | 37 | 44056 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting401820200731-5Foreman121140 | Corbiere and Sons Contracting401820200731-5Foreman121140Inv#043 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4018 | 20200731-5 | 53520102 | Clearing | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2020-07-31 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brushing and Raking from A130-A131 | 1 | A-128 to B-017 | Wolf Lake | 0 | 44049 |  | 37 | 44056 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting401820200731-5L.O.A.4840 | Corbiere and Sons Contracting401820200731-5L.O.A.4840Inv#043 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4018 | 20200731-5 | 53520102 | Clearing | 0 | Operator - Principle - After Jan 10 | 75 | 23 | HR |  |  | 75 | 0 | 1725 | 224.25 | 1949.25 | 2020-07-31 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brushing and Raking from A130-A131 | 1 | A-128 to B-017 | Wolf Lake | 0 | 44049 |  | 37 | 44056 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting401820200731-5Operator - Principle - After Jan 10231725 | Corbiere and Sons Contracting401820200731-5Operator - Principle - After Jan 10231725Inv#043 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4018 | 20200731-5 | 53520102 | Clearing | 0 | Labourer - General - After Jan 10 | 60 | 11.5 | HR |  |  | 60 | 0 | 690 | 89.7 | 779.7 | 2020-07-31 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brushing and Raking from A130-A131 | 1 | A-128 to B-017 | Wolf Lake | 0 | 44049 |  | 37 | 44056 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting401820200731-5Labourer - General - After Jan 1011.5690 | Corbiere and Sons Contracting401820200731-5Labourer - General - After Jan 1011.5690Inv#043 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 690 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4019 | 20200731-6 | 53510212 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 5.5 | Dynamic | 103.84 | 0 |  |  | 761.475 | 98.9917 | 860.4668 | 2020-07-31 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Realigning road from B054 to B056 | 2 | B054 - B064 | Lofty Davies | 0 | 44049 |  | 37 | 44056 | [5 empty] | Harold Furlong | 02 | Corbiere and Sons Contracting401920200731-6Excavator - 30 ton- After Jan 105.5761.475 | Corbiere and Sons Contracting401920200731-6Excavator - 30 ton- After Jan 105.5761.475Inv#043 | [5 empty] | 1 | 761.475 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4019 | 20200731-6 | 53510212 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-07-31 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Realigning road from B054 to B056 | 2 | B054 - B064 | Lofty Davies | 0 | 44049 |  | 37 | 44056 | [5 empty] | Harold Furlong | 02 | Corbiere and Sons Contracting401920200731-6Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting401920200731-6Light Truck - Pick up- After Jan 101243.75Inv#043 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4019 | 20200731-6 | 53510212 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-07-31 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Realigning road from B054 to B056 | 2 | B054 - B064 | Lofty Davies | 0 | 44049 |  | 37 | 44056 | [5 empty] | Harold Furlong | 02 | Corbiere and Sons Contracting401920200731-6L.O.A.1210 | Corbiere and Sons Contracting401920200731-6L.O.A.1210Inv#043 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4019 | 20200731-6 | 53510212 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 7 | HR |  |  | 75 | 0 | 525 | 68.25 | 593.25 | 2020-07-31 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Realigning road from B054 to B056 | 2 | B054 - B064 | Lofty Davies | 0 | 44049 |  | 37 | 44056 | [5 empty] | Harold Furlong | 02 | Corbiere and Sons Contracting401920200731-6Operator - Principle - After Jan 107525 | Corbiere and Sons Contracting401920200731-6Operator - Principle - After Jan 107525Inv#043 | [5 empty] | 1 | 525 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4021 | 20200731-8 | 53510312 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 8 | Dynamic | 95.24 | 0 |  |  | 1015.84 | 132.0592 | 1147.8992 | 2020-07-31 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working on Lachance | 3 | B161-B181 | Lachance | 0 | 44049 |  | 37 | 44056 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting402120200731-8Grader - Cat 12 to 14 or equal- After Jan 1081015.84 | Corbiere and Sons Contracting402120200731-8Grader - Cat 12 to 14 or equal- After Jan 1081015.84Inv#043 | [5 empty] | 1 | 1015.84 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4021 | 20200731-8 | 53510312 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-07-31 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working on Lachance | 3 | B161-B181 | Lachance | 0 | 44049 |  | 37 | 44056 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting402120200731-8L.O.A.1210 | Corbiere and Sons Contracting402120200731-8L.O.A.1210Inv#043 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4021 | 20200731-8 | 53510312 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 9.5 | HR |  |  | 75 | 0 | 712.5 | 92.625 | 805.125 | 2020-07-31 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working on Lachance | 3 | B161-B181 | Lachance | 0 | 44049 |  | 37 | 44056 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting402120200731-8Operator - Principle - After Jan 109.5712.5 | Corbiere and Sons Contracting402120200731-8Operator - Principle - After Jan 109.5712.5Inv#043 | [5 empty] | 1 | 712.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4027 | 20200801-4 | 53520102 | Clearing | 0 | Brusher | 202.5 | 9.5 | HR | 151.88 | 0 |  |  | 1923.75 | 250.0875 | 2173.8375 | 2020-08-01 | 1 | Inv#045 | 44067 | 103 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher working from A075 | 1 | A-055 to A-084 | Eldorado | 0 | 44049 |  | 37 | 44056 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting402720200801-4Brusher9.51923.75 | Corbiere and Sons Contracting402720200801-4Brusher9.51923.75Inv#045 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1923.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4027 | 20200801-4 | 53520102 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-08-01 | 1 | Inv#045 | 44067 | 103 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher working from A075 | 1 | A-055 to A-084 | Eldorado | 0 | 44049 |  | 37 | 44056 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting402720200801-4Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting402720200801-4Light Truck - Pick up- After Jan 102487.5Inv#045 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4027 | 20200801-4 | 53520102 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-08-01 | 1 | Inv#045 | 44067 | 103 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher working from A075 | 1 | A-055 to A-084 | Eldorado | 0 | 44049 |  | 37 | 44056 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting402720200801-4L.O.A.1210 | Corbiere and Sons Contracting402720200801-4L.O.A.1210Inv#045 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4027 | 20200801-4 | 53520102 | Clearing | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-08-01 | 1 | Inv#045 | 44067 | 103 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher working from A075 | 1 | A-055 to A-084 | Eldorado | 0 | 44049 |  | 37 | 44056 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting402720200801-4Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting402720200801-4Operator - Principle - After Jan 1011.5862.5Inv#045 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4027 | 20200801-4 | 53520102 | Clearing | 0 | Labourer - General - After Jan 10 | 60 | 11.5 | HR |  |  | 60 | 0 | 690 | 89.7 | 779.7 | 2020-08-01 | 1 | Inv#045 | 44067 | 103 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher working from A075 | 1 | A-055 to A-084 | Eldorado | 0 | 44049 |  | 37 | 44056 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting402720200801-4Labourer - General - After Jan 1011.5690 | Corbiere and Sons Contracting402720200801-4Labourer - General - After Jan 1011.5690Inv#045 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 690 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4028 | 20200801-5 | 53520102 | Clearing | 0 | Brusher | 202.5 | 8.5 | HR | 151.88 | 0 |  |  | 1721.25 | 223.7625 | 1945.0125 | 2020-08-01 | 1 | Inv#045 | 44067 | 103 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher and rake working from A131-A132 | 1 | A-128 to B-017 | Wolf Lake | 0 | 44049 |  | 37 | 44056 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting402820200801-5Brusher8.51721.25 | Corbiere and Sons Contracting402820200801-5Brusher8.51721.25Inv#045 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1721.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4028 | 20200801-5 | 53520102 | Clearing | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 8.5 | Dynamic | 103.84 | 0 |  |  | 1176.825 | 152.9872 | 1329.8122 | 2020-08-01 | 1 | Inv#045 | 44067 | 103 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher and rake working from A131-A132 | 1 | A-128 to B-017 | Wolf Lake | 0 | 44049 |  | 37 | 44056 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting402820200801-5Excavator - 30 ton- After Jan 108.51176.825 | Corbiere and Sons Contracting402820200801-5Excavator - 30 ton- After Jan 108.51176.825Inv#045 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1176.825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4028 | 20200801-5 | 53520102 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-08-01 | 1 | Inv#045 | 44067 | 103 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher and rake working from A131-A132 | 1 | A-128 to B-017 | Wolf Lake | 0 | 44049 |  | 37 | 44056 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting402820200801-5Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting402820200801-5Light Truck - Pick up- After Jan 102487.5Inv#045 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4028 | 20200801-5 | 53520102 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2020-08-01 | 1 | Inv#045 | 44067 | 103 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher and rake working from A131-A132 | 1 | A-128 to B-017 | Wolf Lake | 0 | 44049 |  | 37 | 44056 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting402820200801-5Foreman121140 | Corbiere and Sons Contracting402820200801-5Foreman121140Inv#045 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4028 | 20200801-5 | 53520102 | Clearing | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2020-08-01 | 1 | Inv#045 | 44067 | 103 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher and rake working from A131-A132 | 1 | A-128 to B-017 | Wolf Lake | 0 | 44049 |  | 37 | 44056 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting402820200801-5L.O.A.4840 | Corbiere and Sons Contracting402820200801-5L.O.A.4840Inv#045 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4028 | 20200801-5 | 53520102 | Clearing | 0 | Operator - Principle - After Jan 10 | 75 | 21 | HR |  |  | 75 | 0 | 1575 | 204.75 | 1779.75 | 2020-08-01 | 1 | Inv#045 | 44067 | 103 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher and rake working from A131-A132 | 1 | A-128 to B-017 | Wolf Lake | 0 | 44049 |  | 37 | 44056 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting402820200801-5Operator - Principle - After Jan 10211575 | Corbiere and Sons Contracting402820200801-5Operator - Principle - After Jan 10211575Inv#045 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1575 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4028 | 20200801-5 | 53520102 | Clearing | 0 | Labourer - General - After Jan 10 | 60 | 10.5 | HR |  |  | 60 | 0 | 630 | 81.9 | 711.9 | 2020-08-01 | 1 | Inv#045 | 44067 | 103 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher and rake working from A131-A132 | 1 | A-128 to B-017 | Wolf Lake | 0 | 44049 |  | 37 | 44056 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting402820200801-5Labourer - General - After Jan 1010.5630 | Corbiere and Sons Contracting402820200801-5Labourer - General - After Jan 1010.5630Inv#045 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4015 | 20200802-2 | 53520102 | Clearing | 0 | Brusher | 202.5 | 9 | HR | 151.88 | 0 |  |  | 1822.5 | 236.925 | 2059.425 | 2020-08-02 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher working from A082 | 1 | A-085 to A-117 | Windfarm | 0 | 44051 |  | 47 | 44054 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting401520200802-2Brusher91822.5 | Corbiere and Sons Contracting401520200802-2Brusher91822.5Inv#043 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1822.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4015 | 20200802-2 | 53520102 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-08-02 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher working from A082 | 1 | A-085 to A-117 | Windfarm | 0 | 44051 |  | 47 | 44054 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting401520200802-2Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting401520200802-2Light Truck - Pick up- After Jan 101243.75Inv#043 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4015 | 20200802-2 | 53520102 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-08-02 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher working from A082 | 1 | A-085 to A-117 | Windfarm | 0 | 44051 |  | 47 | 44054 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting401520200802-2L.O.A.2420 | Corbiere and Sons Contracting401520200802-2L.O.A.2420Inv#043 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4015 | 20200802-2 | 53520102 | Clearing | 0 | Operator - Principle - After Jan 10 | 75 | 10.5 | HR |  |  | 75 | 0 | 787.5 | 102.375 | 889.875 | 2020-08-02 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher working from A082 | 1 | A-085 to A-117 | Windfarm | 0 | 44051 |  | 47 | 44054 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting401520200802-2Operator - Principle - After Jan 1010.5787.5 | Corbiere and Sons Contracting401520200802-2Operator - Principle - After Jan 1010.5787.5Inv#043 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 787.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4015 | 20200802-2 | 53520102 | Clearing | 0 | Labourer - General - After Jan 10 | 60 | 10.5 | HR |  |  | 60 | 0 | 630 | 81.9 | 711.9 | 2020-08-02 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher working from A082 | 1 | A-085 to A-117 | Windfarm | 0 | 44051 |  | 47 | 44054 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting401520200802-2Labourer - General - After Jan 1010.5630 | Corbiere and Sons Contracting401520200802-2Labourer - General - After Jan 1010.5630Inv#043 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4016 | 20200802-3 | 53520102 | Clearing | 0 | Brusher | 202.5 | 9 | HR | 151.88 | 0 |  |  | 1822.5 | 236.925 | 2059.425 | 2020-08-02 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rake and brusher working from A134-A135 | 1 | A-128 to B-017 | Wolf Lake | 0 | 44051 |  | 47 | 44054 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting401620200802-3Brusher91822.5 | Corbiere and Sons Contracting401620200802-3Brusher91822.5Inv#043 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1822.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4016 | 20200802-3 | 53520102 | Clearing | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 6.5 | Dynamic | 110.22 | 0 |  |  | 955.24 | 124.1812 | 1079.4212 | 2020-08-02 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rake and brusher working from A134-A135 | 1 | A-128 to B-017 | Wolf Lake | 0 | 44051 |  | 47 | 44054 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting401620200802-3Excavator - 36 ton- After Jan 106.5955.24 | Corbiere and Sons Contracting401620200802-3Excavator - 36 ton- After Jan 106.5955.24Inv#043 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 955.24 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4016 | 20200802-3 | 53520102 | Clearing | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 6.5 | HR | 9.16 | 0 |  |  | 79.365 | 10.3174 | 89.6825 | 2020-08-02 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rake and brusher working from A134-A135 | 1 | A-128 to B-017 | Wolf Lake | 0 | 44051 |  | 47 | 44054 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting401620200802-3Excavator Thumb - 30 - 50 ton- After Jan 106.579.365 | Corbiere and Sons Contracting401620200802-3Excavator Thumb - 30 - 50 ton- After Jan 106.579.365Inv#043 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 79.365 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4016 | 20200802-3 | 53520102 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2020-08-02 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rake and brusher working from A134-A135 | 1 | A-128 to B-017 | Wolf Lake | 0 | 44051 |  | 47 | 44054 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting401620200802-3Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting401620200802-3Light Truck - Pick up- After Jan 103731.25Inv#043 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 731.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4016 | 20200802-3 | 53520102 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2020-08-02 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rake and brusher working from A134-A135 | 1 | A-128 to B-017 | Wolf Lake | 0 | 44051 |  | 47 | 44054 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting401620200802-3Foreman121140 | Corbiere and Sons Contracting401620200802-3Foreman121140Inv#043 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4016 | 20200802-3 | 53520102 | Clearing | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2020-08-02 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rake and brusher working from A134-A135 | 1 | A-128 to B-017 | Wolf Lake | 0 | 44051 |  | 47 | 44054 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting401620200802-3L.O.A.4840 | Corbiere and Sons Contracting401620200802-3L.O.A.4840Inv#043 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4016 | 20200802-3 | 53520102 | Clearing | 0 | Operator - Principle - After Jan 10 | 75 | 18 | HR |  |  | 75 | 0 | 1350 | 175.5 | 1525.5 | 2020-08-02 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rake and brusher working from A134-A135 | 1 | A-128 to B-017 | Wolf Lake | 0 | 44051 |  | 47 | 44054 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting401620200802-3Operator - Principle - After Jan 10181350 | Corbiere and Sons Contracting401620200802-3Operator - Principle - After Jan 10181350Inv#043 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1350 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4016 | 20200802-3 | 53520102 | Clearing | 0 | Labourer - General - After Jan 10 | 60 | 10.5 | HR |  |  | 60 | 0 | 630 | 81.9 | 711.9 | 2020-08-02 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rake and brusher working from A134-A135 | 1 | A-128 to B-017 | Wolf Lake | 0 | 44051 |  | 47 | 44054 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting401620200802-3Labourer - General - After Jan 1010.5630 | Corbiere and Sons Contracting401620200802-3Labourer - General - After Jan 1010.5630Inv#043 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4048 | 20200803-3 | 53520102 | Clearing | 0 | Brusher | 202.5 | 8.5 | HR | 151.88 | 0 |  |  | 1721.25 | 223.7625 | 1945.0125 | 2020-08-03 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher working from A082-A094 | 1 | A-085 to A-117 | Windfarm | 0 | 44052 |  | 47 | 44054 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting404820200803-3Brusher8.51721.25 | Corbiere and Sons Contracting404820200803-3Brusher8.51721.25Inv#043 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1721.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4048 | 20200803-3 | 53520102 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-08-03 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher working from A082-A094 | 1 | A-085 to A-117 | Windfarm | 0 | 44052 |  | 47 | 44054 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting404820200803-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting404820200803-3Light Truck - Pick up- After Jan 101243.75Inv#043 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4048 | 20200803-3 | 53520102 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-08-03 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher working from A082-A094 | 1 | A-085 to A-117 | Windfarm | 0 | 44052 |  | 47 | 44054 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting404820200803-3L.O.A.1210 | Corbiere and Sons Contracting404820200803-3L.O.A.1210Inv#043 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4048 | 20200803-3 | 53520102 | Clearing | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-08-03 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher working from A082-A094 | 1 | A-085 to A-117 | Windfarm | 0 | 44052 |  | 47 | 44054 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting404820200803-3Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting404820200803-3Operator - Principle - After Jan 1011.5862.5Inv#043 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4048 | 20200803-3 | 53520102 | Clearing | 0 | Labourer - General - After Jan 10 | 60 | 11.5 | HR |  |  | 60 | 0 | 690 | 89.7 | 779.7 | 2020-08-03 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher working from A082-A094 | 1 | A-085 to A-117 | Windfarm | 0 | 44052 |  | 47 | 44054 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting404820200803-3Labourer - General - After Jan 1011.5690 | Corbiere and Sons Contracting404820200803-3Labourer - General - After Jan 1011.5690Inv#043 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 690 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4049 | 20200803-4 | 53520102 | Clearing | 0 | Brusher | 202.5 | 10 | HR | 151.88 | 0 |  |  | 2025 | 263.25 | 2288.25 | 2020-08-03 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher working from A134-B001 - Rake working from B001-B003 | 1 | A-128 to B-017 | Wolf Lake | 0 | 44052 |  | 47 | 44054 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting404920200803-4Brusher102025 | Corbiere and Sons Contracting404920200803-4Brusher102025Inv#043 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2025 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4049 | 20200803-4 | 53520102 | Clearing | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2020-08-03 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher working from A134-B001 - Rake working from B001-B003 | 1 | A-128 to B-017 | Wolf Lake | 0 | 44052 |  | 47 | 44054 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting404920200803-4Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting404920200803-4Excavator - 36 ton- After Jan 1091322.64Inv#043 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1322.64 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4049 | 20200803-4 | 53520102 | Clearing | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2020-08-03 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher working from A134-B001 - Rake working from B001-B003 | 1 | A-128 to B-017 | Wolf Lake | 0 | 44052 |  | 47 | 44054 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting404920200803-4Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting404920200803-4Excavator Thumb - 30 - 50 ton- After Jan 109109.89Inv#043 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 109.89 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4049 | 20200803-4 | 53520102 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2020-08-03 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher working from A134-B001 - Rake working from B001-B003 | 1 | A-128 to B-017 | Wolf Lake | 0 | 44052 |  | 47 | 44054 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting404920200803-4Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting404920200803-4Light Truck - Pick up- After Jan 103731.25Inv#043 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 731.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4049 | 20200803-4 | 53520102 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2020-08-03 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher working from A134-B001 - Rake working from B001-B003 | 1 | A-128 to B-017 | Wolf Lake | 0 | 44052 |  | 47 | 44054 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting404920200803-4Foreman121140 | Corbiere and Sons Contracting404920200803-4Foreman121140Inv#043 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4049 | 20200803-4 | 53520102 | Clearing | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2020-08-03 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher working from A134-B001 - Rake working from B001-B003 | 1 | A-128 to B-017 | Wolf Lake | 0 | 44052 |  | 47 | 44054 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting404920200803-4L.O.A.4840 | Corbiere and Sons Contracting404920200803-4L.O.A.4840Inv#043 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4049 | 20200803-4 | 53520102 | Clearing | 0 | Operator - Principle - After Jan 10 | 75 | 22 | HR |  |  | 75 | 0 | 1650 | 214.5 | 1864.5 | 2020-08-03 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher working from A134-B001 - Rake working from B001-B003 | 1 | A-128 to B-017 | Wolf Lake | 0 | 44052 |  | 47 | 44054 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting404920200803-4Operator - Principle - After Jan 10221650 | Corbiere and Sons Contracting404920200803-4Operator - Principle - After Jan 10221650Inv#043 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1650 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4049 | 20200803-4 | 53520102 | Clearing | 0 | Labourer - General - After Jan 10 | 60 | 11.5 | HR |  |  | 60 | 0 | 690 | 89.7 | 779.7 | 2020-08-03 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher working from A134-B001 - Rake working from B001-B003 | 1 | A-128 to B-017 | Wolf Lake | 0 | 44052 |  | 47 | 44054 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting404920200803-4Labourer - General - After Jan 1011.5690 | Corbiere and Sons Contracting404920200803-4Labourer - General - After Jan 1011.5690Inv#043 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 690 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4051 | 20200803-6 | 53510312 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 9.5 | Dynamic | 95.24 | 0 |  |  | 1206.31 | 156.8203 | 1363.1303 | 2020-08-03 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader fixing up roa along Lachance | 3 | B191-B181 | Lachance Road | 0 | 44052 |  | 47 | 44054 | [5 empty] | Clint Maerz | 03 | Corbiere and Sons Contracting405120200803-6Grader - Cat 12 to 14 or equal- After Jan 109.51206.31 | Corbiere and Sons Contracting405120200803-6Grader - Cat 12 to 14 or equal- After Jan 109.51206.31Inv#043 | [5 empty] | 1 | 1206.31 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4051 | 20200803-6 | 53510312 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-08-03 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader fixing up roa along Lachance | 3 | B191-B181 | Lachance Road | 0 | 44052 |  | 47 | 44054 | [5 empty] | Clint Maerz | 03 | Corbiere and Sons Contracting405120200803-6Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting405120200803-6Light Truck - Pick up- After Jan 101243.75Inv#043 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4051 | 20200803-6 | 53510312 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-08-03 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader fixing up roa along Lachance | 3 | B191-B181 | Lachance Road | 0 | 44052 |  | 47 | 44054 | [5 empty] | Clint Maerz | 03 | Corbiere and Sons Contracting405120200803-6L.O.A.1210 | Corbiere and Sons Contracting405120200803-6L.O.A.1210Inv#043 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4051 | 20200803-6 | 53510312 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-08-03 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader fixing up roa along Lachance | 3 | B191-B181 | Lachance Road | 0 | 44052 |  | 47 | 44054 | [5 empty] | Clint Maerz | 03 | Corbiere and Sons Contracting405120200803-6Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting405120200803-6Operator - Principle - After Jan 1011.5862.5Inv#043 | [5 empty] | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4055 | 20200804-3 | 53520102 | Clearing | 0 | Brusher | 202.5 | 9.5 | HR | 151.88 | 0 |  |  | 1923.75 | 250.0875 | 2173.8375 | 2020-08-04 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher and Rake working from A084-A087 - 1 Labourer on Firewatch | 1 | A-085 to A-117 | Windfarm | 0 | 44052 |  | 47 | 44054 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting405520200804-3Brusher9.51923.75 | Corbiere and Sons Contracting405520200804-3Brusher9.51923.75Inv#043 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1923.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4055 | 20200804-3 | 53520102 | Clearing | 0 | Excavator - 20 ton- After Jan 10 | 104.55 | 8.5 | Dynamic | 78.41 | 0 |  |  | 888.675 | 115.5277 | 1004.2028 | 2020-08-04 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher and Rake working from A084-A087 - 1 Labourer on Firewatch | 1 | A-085 to A-117 | Windfarm | 0 | 44052 |  | 47 | 44054 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting405520200804-3Excavator - 20 ton- After Jan 108.5888.675 | Corbiere and Sons Contracting405520200804-3Excavator - 20 ton- After Jan 108.5888.675Inv#043 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 888.675 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4055 | 20200804-3 | 53520102 | Clearing | 0 | Excavator Thumb - 8 -20 ton- After Jan 10 | 8.76 | 8.5 | HR | 6.57 | 0 |  |  | 74.46 | 9.6798 | 84.1398 | 2020-08-04 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher and Rake working from A084-A087 - 1 Labourer on Firewatch | 1 | A-085 to A-117 | Windfarm | 0 | 44052 |  | 47 | 44054 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting405520200804-3Excavator Thumb - 8 -20 ton- After Jan 108.574.46 | Corbiere and Sons Contracting405520200804-3Excavator Thumb - 8 -20 ton- After Jan 108.574.46Inv#043 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 74.46 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4055 | 20200804-3 | 53520102 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2020-08-04 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher and Rake working from A084-A087 - 1 Labourer on Firewatch | 1 | A-085 to A-117 | Windfarm | 0 | 44052 |  | 47 | 44054 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting405520200804-3Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting405520200804-3Light Truck - Pick up- After Jan 103731.25Inv#043 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 731.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4055 | 20200804-3 | 53520102 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2020-08-04 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher and Rake working from A084-A087 - 1 Labourer on Firewatch | 1 | A-085 to A-117 | Windfarm | 0 | 44052 |  | 47 | 44054 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting405520200804-3Foreman121140 | Corbiere and Sons Contracting405520200804-3Foreman121140Inv#043 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4055 | 20200804-3 | 53520102 | Clearing | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2020-08-04 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher and Rake working from A084-A087 - 1 Labourer on Firewatch | 1 | A-085 to A-117 | Windfarm | 0 | 44052 |  | 47 | 44054 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting405520200804-3L.O.A.4840 | Corbiere and Sons Contracting405520200804-3L.O.A.4840Inv#043 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4055 | 20200804-3 | 53520102 | Clearing | 0 | Operator - Principle - After Jan 10 | 75 | 23 | HR |  |  | 75 | 0 | 1725 | 224.25 | 1949.25 | 2020-08-04 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher and Rake working from A084-A087 - 1 Labourer on Firewatch | 1 | A-085 to A-117 | Windfarm | 0 | 44052 |  | 47 | 44054 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting405520200804-3Operator - Principle - After Jan 10231725 | Corbiere and Sons Contracting405520200804-3Operator - Principle - After Jan 10231725Inv#043 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4055 | 20200804-3 | 53520102 | Clearing | 0 | Labourer - General - After Jan 10 | 60 | 11.5 | HR |  |  | 60 | 0 | 690 | 89.7 | 779.7 | 2020-08-04 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher and Rake working from A084-A087 - 1 Labourer on Firewatch | 1 | A-085 to A-117 | Windfarm | 0 | 44052 |  | 47 | 44054 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting405520200804-3Labourer - General - After Jan 1011.5690 | Corbiere and Sons Contracting405520200804-3Labourer - General - After Jan 1011.5690Inv#043 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 690 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4056 | 20200804-4-R1 | 53520102 | Clearing | 0 | Brusher | 202.5 | 5 | HR | 151.88 | 0 |  |  | 1012.5 | 131.625 | 1144.125 | 2020-08-04 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher and Rake shutdown early due to waiting on information from Resolute Mill - Grinder mobed in and started grinding from A128 | 1 | A-128 to B-017 | Wolf Lake | 0 | 44052 |  | 47 | 44054 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting405620200804-4-R1Brusher51012.5 | Corbiere and Sons Contracting405620200804-4-R1Brusher51012.5Inv#043 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1012.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4056 | 20200804-4-R1 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 7.5 | HR | 417.6 | 0 |  |  | 4176 | 542.88 | 4718.88 | 2020-08-04 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher and Rake shutdown early due to waiting on information from Resolute Mill - Grinder mobed in and started grinding from A128 | 1 | A-128 to B-017 | Wolf Lake | 0 | 44052 |  | 47 | 44054 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting405620200804-4-R1Grinder - 4710 Peterson or equal7.54176 | Corbiere and Sons Contracting405620200804-4-R1Grinder - 4710 Peterson or equal7.54176Inv#043 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 4176 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4056 | 20200804-4-R1 | 53520102 | Clearing | 0 | Log Loader | 153 | 7.5 | HR | 114.75 | 0 |  |  | 1147.5 | 149.175 | 1296.675 | 2020-08-04 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher and Rake shutdown early due to waiting on information from Resolute Mill - Grinder mobed in and started grinding from A128 | 1 | A-128 to B-017 | Wolf Lake | 0 | 44052 |  | 47 | 44054 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting405620200804-4-R1Log Loader7.51147.5 | Corbiere and Sons Contracting405620200804-4-R1Log Loader7.51147.5Inv#043 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1147.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4056 | 20200804-4-R1 | 53520102 | Clearing | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 5 | Dynamic | 110.22 | 0 |  |  | 734.8 | 95.524 | 830.324 | 2020-08-04 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher and Rake shutdown early due to waiting on information from Resolute Mill - Grinder mobed in and started grinding from A128 | 1 | A-128 to B-017 | Wolf Lake | 0 | 44052 |  | 47 | 44054 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting405620200804-4-R1Excavator - 36 ton- After Jan 105734.8 | Corbiere and Sons Contracting405620200804-4-R1Excavator - 36 ton- After Jan 105734.8Inv#043 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 734.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4056 | 20200804-4-R1 | 53520102 | Clearing | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 5 | HR | 9.16 | 0 |  |  | 61.05 | 7.9365 | 68.9865 | 2020-08-04 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher and Rake shutdown early due to waiting on information from Resolute Mill - Grinder mobed in and started grinding from A128 | 1 | A-128 to B-017 | Wolf Lake | 0 | 44052 |  | 47 | 44054 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting405620200804-4-R1Excavator Thumb - 30 - 50 ton- After Jan 10561.05 | Corbiere and Sons Contracting405620200804-4-R1Excavator Thumb - 30 - 50 ton- After Jan 10561.05Inv#043 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 61.05 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4056 | 20200804-4-R1 | 53520102 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-08-04 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher and Rake shutdown early due to waiting on information from Resolute Mill - Grinder mobed in and started grinding from A128 | 1 | A-128 to B-017 | Wolf Lake | 0 | 44052 |  | 47 | 44054 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting405620200804-4-R1Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting405620200804-4-R1Light Truck - Pick up- After Jan 102487.5Inv#043 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4056 | 20200804-4-R1 | 53520102 | Clearing | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2020-08-04 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher and Rake shutdown early due to waiting on information from Resolute Mill - Grinder mobed in and started grinding from A128 | 1 | A-128 to B-017 | Wolf Lake | 0 | 44052 |  | 47 | 44054 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting405620200804-4-R1L.O.A.4840 | Corbiere and Sons Contracting405620200804-4-R1L.O.A.4840Inv#043 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4056 | 20200804-4-R1 | 53520102 | Clearing | 0 | Operator - Principle - After Jan 10 | 75 | 21.5 | HR |  |  | 75 | 0 | 1612.5 | 209.625 | 1822.125 | 2020-08-04 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher and Rake shutdown early due to waiting on information from Resolute Mill - Grinder mobed in and started grinding from A128 | 1 | A-128 to B-017 | Wolf Lake | 0 | 44052 |  | 47 | 44054 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting405620200804-4-R1Operator - Principle - After Jan 1021.51612.5 | Corbiere and Sons Contracting405620200804-4-R1Operator - Principle - After Jan 1021.51612.5Inv#043 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1612.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4056 | 20200804-4-R1 | 53520102 | Clearing | 0 | Labourer - General - After Jan 10 | 60 | 5 | HR |  |  | 60 | 0 | 300 | 39 | 339 | 2020-08-04 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher and Rake shutdown early due to waiting on information from Resolute Mill - Grinder mobed in and started grinding from A128 | 1 | A-128 to B-017 | Wolf Lake | 0 | 44052 |  | 47 | 44054 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting405620200804-4-R1Labourer - General - After Jan 105300 | Corbiere and Sons Contracting405620200804-4-R1Labourer - General - After Jan 105300Inv#043 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4058 | 20200804-6 | 53510312 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 95.24 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2020-08-04 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Lachance Road - Finished up and headed towards Gurney Lake Road access | 3 | B161-B181 | Lachance Road | 0 | 44052 |  | 47 | 44054 | [5 empty] | Clint Maerz | 03 | Corbiere and Sons Contracting405820200804-6Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting405820200804-6Grader - Cat 12 to 14 or equal- After Jan 10101269.8Inv#043 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4058 | 20200804-6 | 53510312 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-08-04 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Lachance Road - Finished up and headed towards Gurney Lake Road access | 3 | B161-B181 | Lachance Road | 0 | 44052 |  | 47 | 44054 | [5 empty] | Clint Maerz | 03 | Corbiere and Sons Contracting405820200804-6Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting405820200804-6Light Truck - Pick up- After Jan 101243.75Inv#043 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4058 | 20200804-6 | 53510312 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-08-04 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Lachance Road - Finished up and headed towards Gurney Lake Road access | 3 | B161-B181 | Lachance Road | 0 | 44052 |  | 47 | 44054 | [5 empty] | Clint Maerz | 03 | Corbiere and Sons Contracting405820200804-6L.O.A.1210 | Corbiere and Sons Contracting405820200804-6L.O.A.1210Inv#043 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4058 | 20200804-6 | 53510312 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-08-04 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Lachance Road - Finished up and headed towards Gurney Lake Road access | 3 | B161-B181 | Lachance Road | 0 | 44052 |  | 47 | 44054 | [5 empty] | Clint Maerz | 03 | Corbiere and Sons Contracting405820200804-6Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting405820200804-6Operator - Principle - After Jan 1011.5862.5Inv#043 | [5 empty] | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4033 | 20200805-4 | 53520102 | Clearing | 0 | Brusher | 202.5 | 9.5 | HR | 151.88 | 0 |  |  | 1923.75 | 250.0875 | 2173.8375 | 2020-08-05 | 1 | Inv#049 | 44088 | 105 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher and Rake working between A087 and A096 | 1 | A-085 to A-117 | Windfarm | 0 | 44051 |  | 47 | 44075 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting403320200805-4Brusher9.51923.75 | Corbiere and Sons Contracting403320200805-4Brusher9.51923.75Inv#049 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1923.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4033 | 20200805-4 | 53520102 | Clearing | 0 | Excavator - 20 ton- After Jan 10 | 104.55 | 9.5 | Dynamic | 78.41 | 0 |  |  | 993.225 | 129.1192 | 1122.3443 | 2020-08-05 | 1 | Inv#049 | 44088 | 105 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher and Rake working between A087 and A096 | 1 | A-085 to A-117 | Windfarm | 0 | 44051 |  | 47 | 44075 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting403320200805-4Excavator - 20 ton- After Jan 109.5993.225 | Corbiere and Sons Contracting403320200805-4Excavator - 20 ton- After Jan 109.5993.225Inv#049 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 993.225 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4033 | 20200805-4 | 53520102 | Clearing | 0 | Excavator Thumb - 8 -20 ton- After Jan 10 | 8.76 | 9.5 | HR | 6.57 | 0 |  |  | 83.22 | 10.8186 | 94.0386 | 2020-08-05 | 1 | Inv#049 | 44088 | 105 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher and Rake working between A087 and A096 | 1 | A-085 to A-117 | Windfarm | 0 | 44051 |  | 47 | 44075 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting403320200805-4Excavator Thumb - 8 -20 ton- After Jan 109.583.22 | Corbiere and Sons Contracting403320200805-4Excavator Thumb - 8 -20 ton- After Jan 109.583.22Inv#049 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 83.22 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4033 | 20200805-4 | 53520102 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-08-05 | 1 | Inv#049 | 44088 | 105 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher and Rake working between A087 and A096 | 1 | A-085 to A-117 | Windfarm | 0 | 44051 |  | 47 | 44075 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting403320200805-4Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting403320200805-4Light Truck - Pick up- After Jan 102487.5Inv#049 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4033 | 20200805-4 | 53520102 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-08-05 | 1 | Inv#049 | 44088 | 105 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher and Rake working between A087 and A096 | 1 | A-085 to A-117 | Windfarm | 0 | 44051 |  | 47 | 44075 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting403320200805-4L.O.A.2420 | Corbiere and Sons Contracting403320200805-4L.O.A.2420Inv#049 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4033 | 20200805-4 | 53520102 | Clearing | 0 | Operator - Principle - After Jan 10 | 75 | 23 | HR |  |  | 75 | 0 | 1725 | 224.25 | 1949.25 | 2020-08-05 | 1 | Inv#049 | 44088 | 105 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher and Rake working between A087 and A096 | 1 | A-085 to A-117 | Windfarm | 0 | 44051 |  | 47 | 44075 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting403320200805-4Operator - Principle - After Jan 10231725 | Corbiere and Sons Contracting403320200805-4Operator - Principle - After Jan 10231725Inv#049 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4033 | 20200805-4 | 53520102 | Clearing | 0 | Labourer - General - After Jan 10 | 60 | 11.5 | HR |  |  | 60 | 0 | 690 | 89.7 | 779.7 | 2020-08-05 | 1 | Inv#049 | 44088 | 105 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher and Rake working between A087 and A096 | 1 | A-085 to A-117 | Windfarm | 0 | 44051 |  | 47 | 44075 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting403320200805-4Labourer - General - After Jan 1011.5690 | Corbiere and Sons Contracting403320200805-4Labourer - General - After Jan 1011.5690Inv#049 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 690 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4034 | 20200805-5 | 53520102 | Clearing | 0 | Brusher | 202.5 | 9.5 | HR | 151.88 | 0 |  |  | 1923.75 | 250.0875 | 2173.8375 | 2020-08-05 | 1 | Inv#049 | 44088 | 105 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher, Rake and Grinder all working from B002-B003 | 1 | A-128 to B-017 | Wolf Lake | 0 | 44051 |  | 47 | 44075 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting403420200805-5Brusher9.51923.75 | Corbiere and Sons Contracting403420200805-5Brusher9.51923.75Inv#049 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1923.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4034 | 20200805-5 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 9.5 | HR | 417.6 | 0 |  |  | 5289.6 | 687.648 | 5977.248 | 2020-08-05 | 1 | Inv#049 | 44088 | 105 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher, Rake and Grinder all working from B002-B003 | 1 | A-128 to B-017 | Wolf Lake | 0 | 44051 |  | 47 | 44075 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting403420200805-5Grinder - 4710 Peterson or equal9.55289.6 | Corbiere and Sons Contracting403420200805-5Grinder - 4710 Peterson or equal9.55289.6Inv#049 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 5289.6 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4034 | 20200805-5 | 53520102 | Clearing | 0 | Log Loader | 153 | 9.5 | HR | 114.75 | 0 |  |  | 1453.5 | 188.955 | 1642.455 | 2020-08-05 | 1 | Inv#049 | 44088 | 105 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher, Rake and Grinder all working from B002-B003 | 1 | A-128 to B-017 | Wolf Lake | 0 | 44051 |  | 47 | 44075 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting403420200805-5Log Loader9.51453.5 | Corbiere and Sons Contracting403420200805-5Log Loader9.51453.5Inv#049 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1453.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4034 | 20200805-5 | 53520102 | Clearing | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 8.5 | Dynamic | 103.84 | 0 |  |  | 1176.825 | 152.9872 | 1329.8122 | 2020-08-05 | 1 | Inv#049 | 44088 | 105 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher, Rake and Grinder all working from B002-B003 | 1 | A-128 to B-017 | Wolf Lake | 0 | 44051 |  | 47 | 44075 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting403420200805-5Excavator - 30 ton- After Jan 108.51176.825 | Corbiere and Sons Contracting403420200805-5Excavator - 30 ton- After Jan 108.51176.825Inv#049 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1176.825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4034 | 20200805-5 | 53520102 | Clearing | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 8.5 | HR | 9.16 | 0 |  |  | 103.785 | 13.4921 | 117.2771 | 2020-08-05 | 1 | Inv#049 | 44088 | 105 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher, Rake and Grinder all working from B002-B003 | 1 | A-128 to B-017 | Wolf Lake | 0 | 44051 |  | 47 | 44075 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting403420200805-5Excavator Thumb - 30 - 50 ton- After Jan 108.5103.785 | Corbiere and Sons Contracting403420200805-5Excavator Thumb - 30 - 50 ton- After Jan 108.5103.785Inv#049 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 103.785 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4034 | 20200805-5 | 53520102 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 4 | DAY | 182.81 | 0 |  |  | 975 | 126.75 | 1101.75 | 2020-08-05 | 1 | Inv#049 | 44088 | 105 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher, Rake and Grinder all working from B002-B003 | 1 | A-128 to B-017 | Wolf Lake | 0 | 44051 |  | 47 | 44075 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting403420200805-5Light Truck - Pick up- After Jan 104975 | Corbiere and Sons Contracting403420200805-5Light Truck - Pick up- After Jan 104975Inv#049 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 975 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4034 | 20200805-5 | 53520102 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2020-08-05 | 1 | Inv#049 | 44088 | 105 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher, Rake and Grinder all working from B002-B003 | 1 | A-128 to B-017 | Wolf Lake | 0 | 44051 |  | 47 | 44075 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting403420200805-5Foreman121140 | Corbiere and Sons Contracting403420200805-5Foreman121140Inv#049 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4034 | 20200805-5 | 53520102 | Clearing | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2020-08-05 | 1 | Inv#049 | 44088 | 105 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher, Rake and Grinder all working from B002-B003 | 1 | A-128 to B-017 | Wolf Lake | 0 | 44051 |  | 47 | 44075 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting403420200805-5L.O.A.4840 | Corbiere and Sons Contracting403420200805-5L.O.A.4840Inv#049 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4034 | 20200805-5 | 53520102 | Clearing | 0 | Operator - Principle - After Jan 10 | 75 | 32.5 | HR |  |  | 75 | 0 | 2437.5 | 316.875 | 2754.375 | 2020-08-05 | 1 | Inv#049 | 44088 | 105 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher, Rake and Grinder all working from B002-B003 | 1 | A-128 to B-017 | Wolf Lake | 0 | 44051 |  | 47 | 44075 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting403420200805-5Operator - Principle - After Jan 1032.52437.5 | Corbiere and Sons Contracting403420200805-5Operator - Principle - After Jan 1032.52437.5Inv#049 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2437.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4034 | 20200805-5 | 53520102 | Clearing | 0 | Labourer - General - After Jan 10 | 60 | 11.5 | HR |  |  | 60 | 0 | 690 | 89.7 | 779.7 | 2020-08-05 | 1 | Inv#049 | 44088 | 105 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher, Rake and Grinder all working from B002-B003 | 1 | A-128 to B-017 | Wolf Lake | 0 | 44051 |  | 47 | 44075 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting403420200805-5Labourer - General - After Jan 1011.5690 | Corbiere and Sons Contracting403420200805-5Labourer - General - After Jan 1011.5690Inv#049 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 690 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4038 | 20200806-3 | 53520102 | Clearing | 0 | Brusher | 202.5 | 8 | HR | 151.88 |  |  |  | 1620 | 210.6 | 1830.6 | 2020-08-06 | 1 | Inv#045 | 44067 | 103 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Raking and brushing finished from A096 and A098 and then moved into get started at A112 | 1 | A-085 to A-117 | Windfarm | 0 | 44052 |  | 47 | 44059 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting403820200806-3Brusher81620 | Corbiere and Sons Contracting403820200806-3Brusher81620Inv#045 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1620 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4038 | 20200806-3 | 53520102 | Clearing | 0 | Excavator - 20 ton- After Jan 10 | 104.55 | 8 | Dynamic | 78.41 | 0 |  |  | 836.4 | 108.732 | 945.132 | 2020-08-06 | 1 | Inv#045 | 44067 | 103 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Raking and brushing finished from A096 and A098 and then moved into get started at A112 | 1 | A-085 to A-117 | Windfarm | 0 | 44052 |  | 47 | 44059 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting403820200806-3Excavator - 20 ton- After Jan 108836.4 | Corbiere and Sons Contracting403820200806-3Excavator - 20 ton- After Jan 108836.4Inv#045 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 836.4 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4038 | 20200806-3 | 53520102 | Clearing | 0 | Excavator Thumb - 8 -20 ton- After Jan 10 | 8.76 | 8 | HR | 6.57 | 0 |  |  | 70.08 | 9.1104 | 79.1904 | 2020-08-06 | 1 | Inv#045 | 44067 | 103 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Raking and brushing finished from A096 and A098 and then moved into get started at A112 | 1 | A-085 to A-117 | Windfarm | 0 | 44052 |  | 47 | 44059 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting403820200806-3Excavator Thumb - 8 -20 ton- After Jan 10870.08 | Corbiere and Sons Contracting403820200806-3Excavator Thumb - 8 -20 ton- After Jan 10870.08Inv#045 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 70.08 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4038 | 20200806-3 | 53520102 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-08-06 | 1 | Inv#045 | 44067 | 103 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Raking and brushing finished from A096 and A098 and then moved into get started at A112 | 1 | A-085 to A-117 | Windfarm | 0 | 44052 |  | 47 | 44059 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting403820200806-3Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting403820200806-3Light Truck - Pick up- After Jan 102487.5Inv#045 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4038 | 20200806-3 | 53520102 | Clearing | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2020-08-06 | 1 | Inv#045 | 44067 | 103 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Raking and brushing finished from A096 and A098 and then moved into get started at A112 | 1 | A-085 to A-117 | Windfarm | 0 | 44052 |  | 47 | 44059 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting403820200806-3L.O.A.3630 | Corbiere and Sons Contracting403820200806-3L.O.A.3630Inv#045 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4038 | 20200806-3 | 53520102 | Clearing | 0 | Operator - Principle - After Jan 10 | 75 | 23 | HR |  |  | 75 | 0 | 1725 | 224.25 | 1949.25 | 2020-08-06 | 1 | Inv#045 | 44067 | 103 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Raking and brushing finished from A096 and A098 and then moved into get started at A112 | 1 | A-085 to A-117 | Windfarm | 0 | 44052 |  | 47 | 44059 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting403820200806-3Operator - Principle - After Jan 10231725 | Corbiere and Sons Contracting403820200806-3Operator - Principle - After Jan 10231725Inv#045 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4038 | 20200806-3 | 53520102 | Clearing | 0 | Labourer - General - After Jan 10 | 60 | 11.5 | HR |  |  | 60 | 0 | 690 | 89.7 | 779.7 | 2020-08-06 | 1 | Inv#045 | 44067 | 103 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Raking and brushing finished from A096 and A098 and then moved into get started at A112 | 1 | A-085 to A-117 | Windfarm | 0 | 44052 |  | 47 | 44059 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting403820200806-3Labourer - General - After Jan 1011.5690 | Corbiere and Sons Contracting403820200806-3Labourer - General - After Jan 1011.5690Inv#045 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 690 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4040 | 20200806-5 | 53520102 | Clearing | 0 | Brusher | 202.5 | 9.5 | HR | 151.88 | 0 |  |  | 1923.75 | 250.0875 | 2173.8375 | 2020-08-06 | 1 | Inv#045 | 44067 | 103 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher, Rake and Grinder working from B003-B004 - Labourer on firewatch | 1 | A-128 to B-017 | Wolf Lake | 0 | 44052 |  | 47 | 44059 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting404020200806-5Brusher9.51923.75 | Corbiere and Sons Contracting404020200806-5Brusher9.51923.75Inv#045 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1923.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4040 | 20200806-5 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 7.5 | HR | 417.6 | 0 |  |  | 4176 | 542.88 | 4718.88 | 2020-08-06 | 1 | Inv#045 | 44067 | 103 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher, Rake and Grinder working from B003-B004 - Labourer on firewatch | 1 | A-128 to B-017 | Wolf Lake | 0 | 44052 |  | 47 | 44059 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting404020200806-5Grinder - 4710 Peterson or equal7.54176 | Corbiere and Sons Contracting404020200806-5Grinder - 4710 Peterson or equal7.54176Inv#045 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 4176 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4040 | 20200806-5 | 53520102 | Clearing | 0 | Log Loader | 153 | 7.5 | HR | 114.75 | 0 |  |  | 1147.5 | 149.175 | 1296.675 | 2020-08-06 | 1 | Inv#045 | 44067 | 103 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher, Rake and Grinder working from B003-B004 - Labourer on firewatch | 1 | A-128 to B-017 | Wolf Lake | 0 | 44052 |  | 47 | 44059 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting404020200806-5Log Loader7.51147.5 | Corbiere and Sons Contracting404020200806-5Log Loader7.51147.5Inv#045 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1147.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4040 | 20200806-5 | 53520102 | Clearing | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 4 | Dynamic | 103.84 | 0 |  |  | 553.8 | 71.994 | 625.794 | 2020-08-06 | 1 | Inv#045 | 44067 | 103 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher, Rake and Grinder working from B003-B004 - Labourer on firewatch | 1 | A-128 to B-017 | Wolf Lake | 0 | 44052 |  | 47 | 44059 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting404020200806-5Excavator - 30 ton- After Jan 104553.8 | Corbiere and Sons Contracting404020200806-5Excavator - 30 ton- After Jan 104553.8Inv#045 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 553.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4040 | 20200806-5 | 53520102 | Clearing | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 4 | HR | 9.16 | 0 |  |  | 48.84 | 6.3492 | 55.1892 | 2020-08-06 | 1 | Inv#045 | 44067 | 103 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher, Rake and Grinder working from B003-B004 - Labourer on firewatch | 1 | A-128 to B-017 | Wolf Lake | 0 | 44052 |  | 47 | 44059 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting404020200806-5Excavator Thumb - 30 - 50 ton- After Jan 10448.84 | Corbiere and Sons Contracting404020200806-5Excavator Thumb - 30 - 50 ton- After Jan 10448.84Inv#045 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 48.84 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4040 | 20200806-5 | 53520102 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2020-08-06 | 1 | Inv#045 | 44067 | 103 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher, Rake and Grinder working from B003-B004 - Labourer on firewatch | 1 | A-128 to B-017 | Wolf Lake | 0 | 44052 |  | 47 | 44059 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting404020200806-5Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting404020200806-5Light Truck - Pick up- After Jan 103731.25Inv#045 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 731.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4040 | 20200806-5 | 53520102 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2020-08-06 | 1 | Inv#045 | 44067 | 103 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher, Rake and Grinder working from B003-B004 - Labourer on firewatch | 1 | A-128 to B-017 | Wolf Lake | 0 | 44052 |  | 47 | 44059 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting404020200806-5Foreman121140 | Corbiere and Sons Contracting404020200806-5Foreman121140Inv#045 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4040 | 20200806-5 | 53520102 | Clearing | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2020-08-06 | 1 | Inv#045 | 44067 | 103 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher, Rake and Grinder working from B003-B004 - Labourer on firewatch | 1 | A-128 to B-017 | Wolf Lake | 0 | 44052 |  | 47 | 44059 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting404020200806-5L.O.A.51050 | Corbiere and Sons Contracting404020200806-5L.O.A.51050Inv#045 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4040 | 20200806-5 | 53520102 | Clearing | 0 | Operator - Principle - After Jan 10 | 75 | 28 | HR |  |  | 75 | 0 | 2100 | 273 | 2373 | 2020-08-06 | 1 | Inv#045 | 44067 | 103 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher, Rake and Grinder working from B003-B004 - Labourer on firewatch | 1 | A-128 to B-017 | Wolf Lake | 0 | 44052 |  | 47 | 44059 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting404020200806-5Operator - Principle - After Jan 10282100 | Corbiere and Sons Contracting404020200806-5Operator - Principle - After Jan 10282100Inv#045 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2100 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4040 | 20200806-5 | 53520102 | Clearing | 0 | Labourer - General - After Jan 10 | 60 | 11.5 | HR |  |  | 60 | 0 | 690 | 89.7 | 779.7 | 2020-08-06 | 1 | Inv#045 | 44067 | 103 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher, Rake and Grinder working from B003-B004 - Labourer on firewatch | 1 | A-128 to B-017 | Wolf Lake | 0 | 44052 |  | 47 | 44059 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting404020200806-5Labourer - General - After Jan 1011.5690 | Corbiere and Sons Contracting404020200806-5Labourer - General - After Jan 1011.5690Inv#045 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 690 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4041 | 20200806-6 | 53510212 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 4.5 | Dynamic | 110.22 | 0 |  |  | 661.32 | 85.9716 | 747.2916 | 2020-08-06 | 1 | Inv#045 | 44067 | 103 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Realignment of road from B018 | 2 | B018 - B029 | Black Sturgeon | 0 | 44052 |  | 47 | 44059 | [5 empty] | Clint Maerz | 02 | Corbiere and Sons Contracting404120200806-6Excavator - 36 ton- After Jan 104.5661.32 | Corbiere and Sons Contracting404120200806-6Excavator - 36 ton- After Jan 104.5661.32Inv#045 | [5 empty] | 1 | 661.32 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4041 | 20200806-6 | 53510212 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-08-06 | 1 | Inv#045 | 44067 | 103 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Realignment of road from B018 | 2 | B018 - B029 | Black Sturgeon | 0 | 44052 |  | 47 | 44059 | [5 empty] | Clint Maerz | 02 | Corbiere and Sons Contracting404120200806-6Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting404120200806-6Light Truck - Pick up- After Jan 101243.75Inv#045 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4041 | 20200806-6 | 53510212 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 75 | 0 | 450 | 58.5 | 508.5 | 2020-08-06 | 1 | Inv#045 | 44067 | 103 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Realignment of road from B018 | 2 | B018 - B029 | Black Sturgeon | 0 | 44052 |  | 47 | 44059 | [5 empty] | Clint Maerz | 02 | Corbiere and Sons Contracting404120200806-6Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting404120200806-6Operator - Principle - After Jan 106450Inv#045 | [5 empty] | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4043 | 20200806-8 | 53510312 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 9.5 | Dynamic | 95.24 | 0 |  |  | 1206.31 | 156.8203 | 1363.1303 | 2020-08-06 | 1 | Inv#045 | 44067 | 103 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader work being completed on Gurney Lake road and then moving to camp road | 3 | B187-B193 | Gurney Lake Road | 0 | 44052 |  | 47 | 44059 | [5 empty] | Clint Maerz | 03 | Corbiere and Sons Contracting404320200806-8Grader - Cat 12 to 14 or equal- After Jan 109.51206.31 | Corbiere and Sons Contracting404320200806-8Grader - Cat 12 to 14 or equal- After Jan 109.51206.31Inv#045 | [5 empty] | 1 | 1206.31 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4043 | 20200806-8 | 53510312 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-08-06 | 1 | Inv#045 | 44067 | 103 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader work being completed on Gurney Lake road and then moving to camp road | 3 | B187-B193 | Gurney Lake Road | 0 | 44052 |  | 47 | 44059 | [5 empty] | Clint Maerz | 03 | Corbiere and Sons Contracting404320200806-8Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting404320200806-8Light Truck - Pick up- After Jan 101243.75Inv#045 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4043 | 20200806-8 | 53510312 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-08-06 | 1 | Inv#045 | 44067 | 103 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader work being completed on Gurney Lake road and then moving to camp road | 3 | B187-B193 | Gurney Lake Road | 0 | 44052 |  | 47 | 44059 | [5 empty] | Clint Maerz | 03 | Corbiere and Sons Contracting404320200806-8L.O.A.1210 | Corbiere and Sons Contracting404320200806-8L.O.A.1210Inv#045 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4043 | 20200806-8 | 53510312 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-08-06 | 1 | Inv#045 | 44067 | 103 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader work being completed on Gurney Lake road and then moving to camp road | 3 | B187-B193 | Gurney Lake Road | 0 | 44052 |  | 47 | 44059 | [5 empty] | Clint Maerz | 03 | Corbiere and Sons Contracting404320200806-8Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting404320200806-8Operator - Principle - After Jan 1011.5862.5Inv#045 | [5 empty] | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4061 | 20200807-3 | 53520102 | Clearing | 0 | Brusher | 202.5 | 9.5 | HR | 151.88 | 0 |  |  | 1923.75 | 250.0875 | 2173.8375 | 2020-08-07 | 1 | Inv#045 | 44067 | 103 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher and Rake working from A111-A114 | 1 | A-085 to A-117 | Windfarm | 0 | 44053 |  | 47 | 44059 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting406120200807-3Brusher9.51923.75 | Corbiere and Sons Contracting406120200807-3Brusher9.51923.75Inv#045 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1923.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4061 | 20200807-3 | 53520102 | Clearing | 0 | Excavator - 20 ton- After Jan 10 | 104.55 | 9.5 | Dynamic | 78.41 | 0 |  |  | 993.225 | 129.1192 | 1122.3443 | 2020-08-07 | 1 | Inv#045 | 44067 | 103 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher and Rake working from A111-A114 | 1 | A-085 to A-117 | Windfarm | 0 | 44053 |  | 47 | 44059 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting406120200807-3Excavator - 20 ton- After Jan 109.5993.225 | Corbiere and Sons Contracting406120200807-3Excavator - 20 ton- After Jan 109.5993.225Inv#045 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 993.225 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4061 | 20200807-3 | 53520102 | Clearing | 0 | Excavator Thumb - 8 -20 ton- After Jan 10 | 8.76 | 9.5 | HR | 6.57 | 0 |  |  | 83.22 | 10.8186 | 94.0386 | 2020-08-07 | 1 | Inv#045 | 44067 | 103 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher and Rake working from A111-A114 | 1 | A-085 to A-117 | Windfarm | 0 | 44053 |  | 47 | 44059 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting406120200807-3Excavator Thumb - 8 -20 ton- After Jan 109.583.22 | Corbiere and Sons Contracting406120200807-3Excavator Thumb - 8 -20 ton- After Jan 109.583.22Inv#045 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 83.22 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4061 | 20200807-3 | 53520102 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-08-07 | 1 | Inv#045 | 44067 | 103 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher and Rake working from A111-A114 | 1 | A-085 to A-117 | Windfarm | 0 | 44053 |  | 47 | 44059 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting406120200807-3Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting406120200807-3Light Truck - Pick up- After Jan 102487.5Inv#045 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4061 | 20200807-3 | 53520102 | Clearing | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2020-08-07 | 1 | Inv#045 | 44067 | 103 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher and Rake working from A111-A114 | 1 | A-085 to A-117 | Windfarm | 0 | 44053 |  | 47 | 44059 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting406120200807-3L.O.A.3630 | Corbiere and Sons Contracting406120200807-3L.O.A.3630Inv#045 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4061 | 20200807-3 | 53520102 | Clearing | 0 | Operator - Principle - After Jan 10 | 75 | 23 | HR |  |  | 75 | 0 | 1725 | 224.25 | 1949.25 | 2020-08-07 | 1 | Inv#045 | 44067 | 103 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher and Rake working from A111-A114 | 1 | A-085 to A-117 | Windfarm | 0 | 44053 |  | 47 | 44059 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting406120200807-3Operator - Principle - After Jan 10231725 | Corbiere and Sons Contracting406120200807-3Operator - Principle - After Jan 10231725Inv#045 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4061 | 20200807-3 | 53520102 | Clearing | 0 | Labourer - General - After Jan 10 | 60 | 11.5 | HR |  |  | 60 | 0 | 690 | 89.7 | 779.7 | 2020-08-07 | 1 | Inv#045 | 44067 | 103 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher and Rake working from A111-A114 | 1 | A-085 to A-117 | Windfarm | 0 | 44053 |  | 47 | 44059 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting406120200807-3Labourer - General - After Jan 1011.5690 | Corbiere and Sons Contracting406120200807-3Labourer - General - After Jan 1011.5690Inv#045 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 690 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4062 | 20200807-4 | 53520102 | Clearing | 0 | Brusher | 202.5 | 9.5 | HR | 151.88 | 0 |  |  | 1923.75 | 250.0875 | 2173.8375 | 2020-08-07 | 1 | Inv#045 | 44067 | 103 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Raking, brushing and grinding being done from B002-B007 - Ron did orinetation and then hopped on the Grinder in the afternoon | 1 | A-128 to B-017 | Wolf Lake | 0 | 44053 |  | 47 | 44059 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting406220200807-4Brusher9.51923.75 | Corbiere and Sons Contracting406220200807-4Brusher9.51923.75Inv#045 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1923.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4062 | 20200807-4 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 5 | HR | 417.6 | 0 |  |  | 2784 | 361.92 | 3145.92 | 2020-08-07 | 1 | Inv#045 | 44067 | 103 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Raking, brushing and grinding being done from B002-B007 - Ron did orinetation and then hopped on the Grinder in the afternoon | 1 | A-128 to B-017 | Wolf Lake | 0 | 44053 |  | 47 | 44059 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting406220200807-4Grinder - 4710 Peterson or equal52784 | Corbiere and Sons Contracting406220200807-4Grinder - 4710 Peterson or equal52784Inv#045 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2784 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4062 | 20200807-4 | 53520102 | Clearing | 0 | Log Loader | 153 | 5 | HR | 114.75 | 0 |  |  | 765 | 99.45 | 864.45 | 2020-08-07 | 1 | Inv#045 | 44067 | 103 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Raking, brushing and grinding being done from B002-B007 - Ron did orinetation and then hopped on the Grinder in the afternoon | 1 | A-128 to B-017 | Wolf Lake | 0 | 44053 |  | 47 | 44059 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting406220200807-4Log Loader5765 | Corbiere and Sons Contracting406220200807-4Log Loader5765Inv#045 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 765 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4062 | 20200807-4 | 53520102 | Clearing | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 5.5 | Dynamic | 103.84 | 0 |  |  | 761.475 | 98.9917 | 860.4668 | 2020-08-07 | 1 | Inv#045 | 44067 | 103 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Raking, brushing and grinding being done from B002-B007 - Ron did orinetation and then hopped on the Grinder in the afternoon | 1 | A-128 to B-017 | Wolf Lake | 0 | 44053 |  | 47 | 44059 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting406220200807-4Excavator - 30 ton- After Jan 105.5761.475 | Corbiere and Sons Contracting406220200807-4Excavator - 30 ton- After Jan 105.5761.475Inv#045 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 761.475 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4062 | 20200807-4 | 53520102 | Clearing | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 5.5 | HR | 9.16 | 0 |  |  | 67.155 | 8.7302 | 75.8851 | 2020-08-07 | 1 | Inv#045 | 44067 | 103 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Raking, brushing and grinding being done from B002-B007 - Ron did orinetation and then hopped on the Grinder in the afternoon | 1 | A-128 to B-017 | Wolf Lake | 0 | 44053 |  | 47 | 44059 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting406220200807-4Excavator Thumb - 30 - 50 ton- After Jan 105.567.155 | Corbiere and Sons Contracting406220200807-4Excavator Thumb - 30 - 50 ton- After Jan 105.567.155Inv#045 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 67.155 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4062 | 20200807-4 | 53520102 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2020-08-07 | 1 | Inv#045 | 44067 | 103 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Raking, brushing and grinding being done from B002-B007 - Ron did orinetation and then hopped on the Grinder in the afternoon | 1 | A-128 to B-017 | Wolf Lake | 0 | 44053 |  | 47 | 44059 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting406220200807-4Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting406220200807-4Light Truck - Pick up- After Jan 103731.25Inv#045 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 731.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4062 | 20200807-4 | 53520102 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2020-08-07 | 1 | Inv#045 | 44067 | 103 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Raking, brushing and grinding being done from B002-B007 - Ron did orinetation and then hopped on the Grinder in the afternoon | 1 | A-128 to B-017 | Wolf Lake | 0 | 44053 |  | 47 | 44059 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting406220200807-4Foreman121140 | Corbiere and Sons Contracting406220200807-4Foreman121140Inv#045 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4062 | 20200807-4 | 53520102 | Clearing | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2020-08-07 | 1 | Inv#045 | 44067 | 103 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Raking, brushing and grinding being done from B002-B007 - Ron did orinetation and then hopped on the Grinder in the afternoon | 1 | A-128 to B-017 | Wolf Lake | 0 | 44053 |  | 47 | 44059 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting406220200807-4L.O.A.51050 | Corbiere and Sons Contracting406220200807-4L.O.A.51050Inv#045 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4062 | 20200807-4 | 53520102 | Clearing | 0 | Operator - Principle - After Jan 10 | 75 | 28.5 | HR |  |  | 75 | 0 | 2137.5 | 277.875 | 2415.375 | 2020-08-07 | 1 | Inv#045 | 44067 | 103 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Raking, brushing and grinding being done from B002-B007 - Ron did orinetation and then hopped on the Grinder in the afternoon | 1 | A-128 to B-017 | Wolf Lake | 0 | 44053 |  | 47 | 44059 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting406220200807-4Operator - Principle - After Jan 1028.52137.5 | Corbiere and Sons Contracting406220200807-4Operator - Principle - After Jan 1028.52137.5Inv#045 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2137.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4062 | 20200807-4 | 53520102 | Clearing | 0 | Labourer - General - After Jan 10 | 60 | 17 | HR |  |  | 60 | 0 | 1020 | 132.6 | 1152.6 | 2020-08-07 | 1 | Inv#045 | 44067 | 103 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Raking, brushing and grinding being done from B002-B007 - Ron did orinetation and then hopped on the Grinder in the afternoon | 1 | A-128 to B-017 | Wolf Lake | 0 | 44053 |  | 47 | 44059 | [5 empty] | Clint Maerz | 01 | Corbiere and Sons Contracting406220200807-4Labourer - General - After Jan 10171020 | Corbiere and Sons Contracting406220200807-4Labourer - General - After Jan 10171020Inv#045 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1020 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4063 | 20200807-5 | 53510312 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 9.5 | Dynamic | 95.24 | 0 |  |  | 1206.31 | 156.8203 | 1363.1303 | 2020-08-07 | 1 | Inv#045 | 44067 | 103 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working back across Gurney Lake road accesses | 3 | B187-B193 | Gurney Lake Road | 0 | 44053 |  | 47 | 44059 | [5 empty] | Clint Maerz | 03 | Corbiere and Sons Contracting406320200807-5Grader - Cat 12 to 14 or equal- After Jan 109.51206.31 | Corbiere and Sons Contracting406320200807-5Grader - Cat 12 to 14 or equal- After Jan 109.51206.31Inv#045 | [5 empty] | 1 | 1206.31 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4063 | 20200807-5 | 53510312 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-08-07 | 1 | Inv#045 | 44067 | 103 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working back across Gurney Lake road accesses | 3 | B187-B193 | Gurney Lake Road | 0 | 44053 |  | 47 | 44059 | [5 empty] | Clint Maerz | 03 | Corbiere and Sons Contracting406320200807-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting406320200807-5Light Truck - Pick up- After Jan 101243.75Inv#045 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4063 | 20200807-5 | 53510312 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-08-07 | 1 | Inv#045 | 44067 | 103 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working back across Gurney Lake road accesses | 3 | B187-B193 | Gurney Lake Road | 0 | 44053 |  | 47 | 44059 | [5 empty] | Clint Maerz | 03 | Corbiere and Sons Contracting406320200807-5L.O.A.1210 | Corbiere and Sons Contracting406320200807-5L.O.A.1210Inv#045 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4063 | 20200807-5 | 53510312 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 11.5 | HR |  |  | 70 | 0 | 805 | 104.65 | 909.65 | 2020-08-07 | 1 | Inv#045 | 44067 | 103 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working back across Gurney Lake road accesses | 3 | B187-B193 | Gurney Lake Road | 0 | 44053 |  | 47 | 44059 | [5 empty] | Clint Maerz | 03 | Corbiere and Sons Contracting406320200807-5Driver - AZ - After Jan 1011.5805 | Corbiere and Sons Contracting406320200807-5Driver - AZ - After Jan 1011.5805Inv#045 | [5 empty] | 1 | 805 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4067 | 20200808-3 | 53510312 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 9.5 | Dynamic | 95.24 | 0 |  |  | 1206.31 | 156.8203 | 1363.1303 | 2020-08-08 | 1 | Inv#049 | 44088 | 105 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader finishing up work on Gurney Lake Road | 3 | B187-B193 | Gurney Lake Road | 0 | 44053 |  | 47 | 44088 | [5 empty] | Clint Maerz | 03 | Corbiere and Sons Contracting406720200808-3Grader - Cat 12 to 14 or equal- After Jan 109.51206.31 | Corbiere and Sons Contracting406720200808-3Grader - Cat 12 to 14 or equal- After Jan 109.51206.31Inv#049 | [5 empty] | 1 | 1206.31 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4067 | 20200808-3 | 53510312 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-08-08 | 1 | Inv#049 | 44088 | 105 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader finishing up work on Gurney Lake Road | 3 | B187-B193 | Gurney Lake Road | 0 | 44053 |  | 47 | 44088 | [5 empty] | Clint Maerz | 03 | Corbiere and Sons Contracting406720200808-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting406720200808-3Light Truck - Pick up- After Jan 101243.75Inv#049 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4067 | 20200808-3 | 53510312 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-08-08 | 1 | Inv#049 | 44088 | 105 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader finishing up work on Gurney Lake Road | 3 | B187-B193 | Gurney Lake Road | 0 | 44053 |  | 47 | 44088 | [5 empty] | Clint Maerz | 03 | Corbiere and Sons Contracting406720200808-3L.O.A.1210 | Corbiere and Sons Contracting406720200808-3L.O.A.1210Inv#049 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4067 | 20200808-3 | 53510312 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-08-08 | 1 | Inv#049 | 44088 | 105 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader finishing up work on Gurney Lake Road | 3 | B187-B193 | Gurney Lake Road | 0 | 44053 |  | 47 | 44088 | [5 empty] | Clint Maerz | 03 | Corbiere and Sons Contracting406720200808-3Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting406720200808-3Operator - Principle - After Jan 1011.5862.5Inv#049 | [5 empty] | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4068 | 20200808-4 | 53520102 | Clearing | 0 | Brusher | 202.5 | 7.5 | HR | 151.88 | 0 |  |  | 1518.75 | 197.4375 | 1716.1875 | 2020-08-08 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher and Rake working from A115-A117 | 1 | A-085 to A-117 | Windfarm | 0 | 44053 |  | 46 | 44054 | [5 empty] | Glen Greening | 01 | Corbiere and Sons Contracting406820200808-4Brusher7.51518.75 | Corbiere and Sons Contracting406820200808-4Brusher7.51518.75Inv#043 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1518.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4068 | 20200808-4 | 53520102 | Clearing | 0 | Excavator - 20 ton- After Jan 10 | 104.55 | 9 | Dynamic | 78.41 | 0 |  |  | 940.95 | 122.3235 | 1063.2735 | 2020-08-08 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher and Rake working from A115-A117 | 1 | A-085 to A-117 | Windfarm | 0 | 44053 |  | 46 | 44054 | [5 empty] | Glen Greening | 01 | Corbiere and Sons Contracting406820200808-4Excavator - 20 ton- After Jan 109940.95 | Corbiere and Sons Contracting406820200808-4Excavator - 20 ton- After Jan 109940.95Inv#043 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 940.95 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4068 | 20200808-4 | 53520102 | Clearing | 0 | Excavator Thumb - 8 -20 ton- After Jan 10 | 8.76 | 9 | HR | 6.57 | 0 |  |  | 78.84 | 10.2492 | 89.0892 | 2020-08-08 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher and Rake working from A115-A117 | 1 | A-085 to A-117 | Windfarm | 0 | 44053 |  | 46 | 44054 | [5 empty] | Glen Greening | 01 | Corbiere and Sons Contracting406820200808-4Excavator Thumb - 8 -20 ton- After Jan 10978.84 | Corbiere and Sons Contracting406820200808-4Excavator Thumb - 8 -20 ton- After Jan 10978.84Inv#043 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 78.84 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4068 | 20200808-4 | 53520102 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-08-08 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher and Rake working from A115-A117 | 1 | A-085 to A-117 | Windfarm | 0 | 44053 |  | 46 | 44054 | [5 empty] | Glen Greening | 01 | Corbiere and Sons Contracting406820200808-4Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting406820200808-4Light Truck - Pick up- After Jan 102487.5Inv#043 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4068 | 20200808-4 | 53520102 | Clearing | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2020-08-08 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher and Rake working from A115-A117 | 1 | A-085 to A-117 | Windfarm | 0 | 44053 |  | 46 | 44054 | [5 empty] | Glen Greening | 01 | Corbiere and Sons Contracting406820200808-4L.O.A.3630 | Corbiere and Sons Contracting406820200808-4L.O.A.3630Inv#043 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4068 | 20200808-4 | 53520102 | Clearing | 0 | Operator - Principle - After Jan 10 | 75 | 21 | HR |  |  | 75 | 0 | 1575 | 204.75 | 1779.75 | 2020-08-08 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher and Rake working from A115-A117 | 1 | A-085 to A-117 | Windfarm | 0 | 44053 |  | 46 | 44054 | [5 empty] | Glen Greening | 01 | Corbiere and Sons Contracting406820200808-4Operator - Principle - After Jan 10211575 | Corbiere and Sons Contracting406820200808-4Operator - Principle - After Jan 10211575Inv#043 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1575 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4068 | 20200808-4 | 53520102 | Clearing | 0 | Labourer - General - After Jan 10 | 60 | 10.5 | HR |  |  | 60 | 0 | 630 | 81.9 | 711.9 | 2020-08-08 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher and Rake working from A115-A117 | 1 | A-085 to A-117 | Windfarm | 0 | 44053 |  | 46 | 44054 | [5 empty] | Glen Greening | 01 | Corbiere and Sons Contracting406820200808-4Labourer - General - After Jan 1010.5630 | Corbiere and Sons Contracting406820200808-4Labourer - General - After Jan 1010.5630Inv#043 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4069 | 20200808-5 | 53520102 | Clearing | 0 | Brusher | 202.5 | 7.5 | HR | 151.88 | 0 |  |  | 1518.75 | 197.4375 | 1716.1875 | 2020-08-08 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher, Rake and Grinder working from B005 Eastward | 1 | A-128 to B-017 | Wolf Lake | 0 | 44053 |  | 46 | 44054 | [5 empty] | Glen Greening | 01 | Corbiere and Sons Contracting406920200808-5Brusher7.51518.75 | Corbiere and Sons Contracting406920200808-5Brusher7.51518.75Inv#043 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1518.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4069 | 20200808-5 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 8 | HR | 417.6 | 0 |  |  | 4454.4 | 579.072 | 5033.472 | 2020-08-08 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher, Rake and Grinder working from B005 Eastward | 1 | A-128 to B-017 | Wolf Lake | 0 | 44053 |  | 46 | 44054 | [5 empty] | Glen Greening | 01 | Corbiere and Sons Contracting406920200808-5Grinder - 4710 Peterson or equal84454.4 | Corbiere and Sons Contracting406920200808-5Grinder - 4710 Peterson or equal84454.4Inv#043 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 4454.4 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4069 | 20200808-5 | 53520102 | Clearing | 0 | Log Loader | 153 | 8 | HR | 114.75 | 0 |  |  | 1224 | 159.12 | 1383.12 | 2020-08-08 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher, Rake and Grinder working from B005 Eastward | 1 | A-128 to B-017 | Wolf Lake | 0 | 44053 |  | 46 | 44054 | [5 empty] | Glen Greening | 01 | Corbiere and Sons Contracting406920200808-5Log Loader81224 | Corbiere and Sons Contracting406920200808-5Log Loader81224Inv#043 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1224 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4069 | 20200808-5 | 53520102 | Clearing | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9.5 | Dynamic | 103.84 | 0 |  |  | 1315.275 | 170.9857 | 1486.2607 | 2020-08-08 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher, Rake and Grinder working from B005 Eastward | 1 | A-128 to B-017 | Wolf Lake | 0 | 44053 |  | 46 | 44054 | [5 empty] | Glen Greening | 01 | Corbiere and Sons Contracting406920200808-5Excavator - 30 ton- After Jan 109.51315.275 | Corbiere and Sons Contracting406920200808-5Excavator - 30 ton- After Jan 109.51315.275Inv#043 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1315.275 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4069 | 20200808-5 | 53520102 | Clearing | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9.5 | HR | 9.16 | 0 |  |  | 115.995 | 15.0793 | 131.0744 | 2020-08-08 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher, Rake and Grinder working from B005 Eastward | 1 | A-128 to B-017 | Wolf Lake | 0 | 44053 |  | 46 | 44054 | [5 empty] | Glen Greening | 01 | Corbiere and Sons Contracting406920200808-5Excavator Thumb - 30 - 50 ton- After Jan 109.5115.995 | Corbiere and Sons Contracting406920200808-5Excavator Thumb - 30 - 50 ton- After Jan 109.5115.995Inv#043 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 115.995 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4069 | 20200808-5 | 53520102 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2020-08-08 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher, Rake and Grinder working from B005 Eastward | 1 | A-128 to B-017 | Wolf Lake | 0 | 44053 |  | 46 | 44054 | [5 empty] | Glen Greening | 01 | Corbiere and Sons Contracting406920200808-5Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting406920200808-5Light Truck - Pick up- After Jan 103731.25Inv#043 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 731.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4069 | 20200808-5 | 53520102 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2020-08-08 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher, Rake and Grinder working from B005 Eastward | 1 | A-128 to B-017 | Wolf Lake | 0 | 44053 |  | 46 | 44054 | [5 empty] | Glen Greening | 01 | Corbiere and Sons Contracting406920200808-5Foreman121140 | Corbiere and Sons Contracting406920200808-5Foreman121140Inv#043 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4069 | 20200808-5 | 53520102 | Clearing | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2020-08-08 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher, Rake and Grinder working from B005 Eastward | 1 | A-128 to B-017 | Wolf Lake | 0 | 44053 |  | 46 | 44054 | [5 empty] | Glen Greening | 01 | Corbiere and Sons Contracting406920200808-5L.O.A.51050 | Corbiere and Sons Contracting406920200808-5L.O.A.51050Inv#043 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4069 | 20200808-5 | 53520102 | Clearing | 0 | Operator - Principle - After Jan 10 | 75 | 34.5 | HR |  |  | 75 | 0 | 2587.5 | 336.375 | 2923.875 | 2020-08-08 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher, Rake and Grinder working from B005 Eastward | 1 | A-128 to B-017 | Wolf Lake | 0 | 44053 |  | 46 | 44054 | [5 empty] | Glen Greening | 01 | Corbiere and Sons Contracting406920200808-5Operator - Principle - After Jan 1034.52587.5 | Corbiere and Sons Contracting406920200808-5Operator - Principle - After Jan 1034.52587.5Inv#043 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2587.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4069 | 20200808-5 | 53520102 | Clearing | 0 | Labourer - General - After Jan 10 | 60 | 11.5 | HR |  |  | 60 | 0 | 690 | 89.7 | 779.7 | 2020-08-08 | 1 | Inv#043 | 44056 | 102 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher, Rake and Grinder working from B005 Eastward | 1 | A-128 to B-017 | Wolf Lake | 0 | 44053 |  | 46 | 44054 | [5 empty] | Glen Greening | 01 | Corbiere and Sons Contracting406920200808-5Labourer - General - After Jan 1011.5690 | Corbiere and Sons Contracting406920200808-5Labourer - General - After Jan 1011.5690Inv#043 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 690 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4075 | 20200809-2 | 53520102 | Clearing | 0 | Brusher | 202.5 | 7.5 | HR | 151.88 | 0 |  |  | 1518.75 | 197.4375 | 1716.1875 | 2020-08-09 | 1 | Inv#045 | 44067 | 103 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher working from B008-B008; Grinder working from B002-B003; | 1 | A-128 to B-017 | Wolf Lake | 0 | 44054 |  | 46 | 44060 | [5 empty] | Glen Greening | 01 | Corbiere and Sons Contracting407520200809-2Brusher7.51518.75 | Corbiere and Sons Contracting407520200809-2Brusher7.51518.75Inv#045 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1518.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4075 | 20200809-2 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 9.5 | HR | 417.6 | 0 |  |  | 5289.6 | 687.648 | 5977.248 | 2020-08-09 | 1 | Inv#045 | 44067 | 103 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher working from B008-B008; Grinder working from B002-B003; | 1 | A-128 to B-017 | Wolf Lake | 0 | 44054 |  | 46 | 44060 | [5 empty] | Glen Greening | 01 | Corbiere and Sons Contracting407520200809-2Grinder - 4710 Peterson or equal9.55289.6 | Corbiere and Sons Contracting407520200809-2Grinder - 4710 Peterson or equal9.55289.6Inv#045 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 5289.6 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4075 | 20200809-2 | 53520102 | Clearing | 0 | Log Loader | 153 | 9.5 | HR | 114.75 | 0 |  |  | 1453.5 | 188.955 | 1642.455 | 2020-08-09 | 1 | Inv#045 | 44067 | 103 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher working from B008-B008; Grinder working from B002-B003; | 1 | A-128 to B-017 | Wolf Lake | 0 | 44054 |  | 46 | 44060 | [5 empty] | Glen Greening | 01 | Corbiere and Sons Contracting407520200809-2Log Loader9.51453.5 | Corbiere and Sons Contracting407520200809-2Log Loader9.51453.5Inv#045 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1453.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4075 | 20200809-2 | 53520102 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-08-09 | 1 | Inv#045 | 44067 | 103 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher working from B008-B008; Grinder working from B002-B003; | 1 | A-128 to B-017 | Wolf Lake | 0 | 44054 |  | 46 | 44060 | [5 empty] | Glen Greening | 01 | Corbiere and Sons Contracting407520200809-2Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting407520200809-2Light Truck - Pick up- After Jan 102487.5Inv#045 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4075 | 20200809-2 | 53520102 | Clearing | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2020-08-09 | 1 | Inv#045 | 44067 | 103 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher working from B008-B008; Grinder working from B002-B003; | 1 | A-128 to B-017 | Wolf Lake | 0 | 44054 |  | 46 | 44060 | [5 empty] | Glen Greening | 01 | Corbiere and Sons Contracting407520200809-2L.O.A.3630 | Corbiere and Sons Contracting407520200809-2L.O.A.3630Inv#045 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4075 | 20200809-2 | 53520102 | Clearing | 0 | Operator - Principle - After Jan 10 | 75 | 23 | HR |  |  | 75 | 0 | 1725 | 224.25 | 1949.25 | 2020-08-09 | 1 | Inv#045 | 44067 | 103 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher working from B008-B008; Grinder working from B002-B003; | 1 | A-128 to B-017 | Wolf Lake | 0 | 44054 |  | 46 | 44060 | [5 empty] | Glen Greening | 01 | Corbiere and Sons Contracting407520200809-2Operator - Principle - After Jan 10231725 | Corbiere and Sons Contracting407520200809-2Operator - Principle - After Jan 10231725Inv#045 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4075 | 20200809-2 | 53520102 | Clearing | 0 | Labourer - General - After Jan 10 | 60 | 11.5 | HR |  |  | 60 | 0 | 690 | 89.7 | 779.7 | 2020-08-09 | 1 | Inv#045 | 44067 | 103 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher working from B008-B008; Grinder working from B002-B003; | 1 | A-128 to B-017 | Wolf Lake | 0 | 44054 |  | 46 | 44060 | [5 empty] | Glen Greening | 01 | Corbiere and Sons Contracting407520200809-2Labourer - General - After Jan 1011.5690 | Corbiere and Sons Contracting407520200809-2Labourer - General - After Jan 1011.5690Inv#045 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 690 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4085 | 20200810-10 | 53510212 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2020-08-10 | 1 | Inv#045 | 44067 | 103 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance from B035-B036 | 2 | B030 - B044 | Stewart Lake | 0 | 44055 |  | 47 | 44057 | [5 empty] | Clint Maerz | 02 | Corbiere and Sons Contracting408520200810-10Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting408520200810-10Dozer D6 or equal- After Jan 10111446.28Inv#045 | [5 empty] | 1 | 1446.28 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4085 | 20200810-10 | 53510212 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-08-10 | 1 | Inv#045 | 44067 | 103 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance from B035-B036 | 2 | B030 - B044 | Stewart Lake | 0 | 44055 |  | 47 | 44057 | [5 empty] | Clint Maerz | 02 | Corbiere and Sons Contracting408520200810-10Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting408520200810-10Light Truck - Pick up- After Jan 102487.5Inv#045 | [5 empty] | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4085 | 20200810-10 | 53510212 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-08-10 | 1 | Inv#045 | 44067 | 103 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance from B035-B036 | 2 | B030 - B044 | Stewart Lake | 0 | 44055 |  | 47 | 44057 | [5 empty] | Clint Maerz | 02 | Corbiere and Sons Contracting408520200810-10L.O.A.2420 | Corbiere and Sons Contracting408520200810-10L.O.A.2420Inv#045 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4085 | 20200810-10 | 53510212 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2020-08-10 | 1 | Inv#045 | 44067 | 103 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance from B035-B036 | 2 | B030 - B044 | Stewart Lake | 0 | 44055 |  | 47 | 44057 | [5 empty] | Clint Maerz | 02 | Corbiere and Sons Contracting408520200810-10Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting408520200810-10Operator - Principle - After Jan 1012900Inv#045 | [5 empty] | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4085 | 20200810-10 | 53510212 | Access | 0 | Labourer - General - After Jan 10 | 60 | 10 | HR |  |  | 60 | 0 | 600 | 78 | 678 | 2020-08-10 | 1 | Inv#045 | 44067 | 103 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance from B035-B036 | 2 | B030 - B044 | Stewart Lake | 0 | 44055 |  | 47 | 44057 | [5 empty] | Clint Maerz | 02 | Corbiere and Sons Contracting408520200810-10Labourer - General - After Jan 1010600 | Corbiere and Sons Contracting408520200810-10Labourer - General - After Jan 1010600Inv#045 | [5 empty] | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4086 | 20200810-11 | 53510312 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 4 | Dynamic | 91.79 | 0 |  |  | 489.56 | 63.6428 | 553.2028 | 2020-08-10 | 1 | Inv#045 | 44067 | 103 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Flaot moving in EX05 to do road repairs | 3 | B161-B181 | Lachance Road | 0 | 44055 |  | 9 | 44056 | [5 empty] | Mandy Sandhu | 03 | Corbiere and Sons Contracting408620200810-11Tractor Trailer - 60 Ton- After Jan 104489.56 | Corbiere and Sons Contracting408620200810-11Tractor Trailer - 60 Ton- After Jan 104489.56Inv#045 | [5 empty] | 1 | 489.56 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4086 | 20200810-11 | 53510312 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 4 | HR |  |  | 70 | 0 | 280 | 36.4 | 316.4 | 2020-08-10 | 1 | Inv#045 | 44067 | 103 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Flaot moving in EX05 to do road repairs | 3 | B161-B181 | Lachance Road | 0 | 44055 |  | 9 | 44056 | [5 empty] | Mandy Sandhu | 03 | Corbiere and Sons Contracting408620200810-11Driver - AZ - After Jan 104280 | Corbiere and Sons Contracting408620200810-11Driver - AZ - After Jan 104280Inv#045 | [5 empty] | 1 | 280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4087 | 20200810-12 | 53510312 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2020-08-10 | 1 | Inv#045 | 44067 | 103 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road repairs from B161-B162 | 3 | B161-B181 | Lachance Road | 0 | 44055 |  | 9 | 44056 | [5 empty] | Mandy Sandhu | 03 | Corbiere and Sons Contracting408720200810-12Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting408720200810-12Excavator - 36 ton- After Jan 1091322.64Inv#045 | [5 empty] | 1 | 1322.64 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4087 | 20200810-12 | 53510312 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2020-08-10 | 1 | Inv#045 | 44067 | 103 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road repairs from B161-B162 | 3 | B161-B181 | Lachance Road | 0 | 44055 |  | 9 | 44056 | [5 empty] | Mandy Sandhu | 03 | Corbiere and Sons Contracting408720200810-12Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting408720200810-12Excavator Thumb - 30 - 50 ton- After Jan 109109.89Inv#045 | [5 empty] | 1 | 109.89 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4087 | 20200810-12 | 53510312 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-08-10 | 1 | Inv#045 | 44067 | 103 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road repairs from B161-B162 | 3 | B161-B181 | Lachance Road | 0 | 44055 |  | 9 | 44056 | [5 empty] | Mandy Sandhu | 03 | Corbiere and Sons Contracting408720200810-12Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting408720200810-12Light Truck - Pick up- After Jan 101243.75Inv#045 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4087 | 20200810-12 | 53510312 | Access | 0 | Light Truck w/ Tandum Trailer- After Jan 10 | 337.5 | 1 | DAY | 253.13 | 0 |  |  | 337.5 | 43.875 | 381.375 | 2020-08-10 | 1 | Inv#045 | 44067 | 103 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road repairs from B161-B162 | 3 | B161-B181 | Lachance Road | 0 | 44055 |  | 9 | 44056 | [5 empty] | Mandy Sandhu | 03 | Corbiere and Sons Contracting408720200810-12Light Truck w/ Tandum Trailer- After Jan 101337.5 | Corbiere and Sons Contracting408720200810-12Light Truck w/ Tandum Trailer- After Jan 101337.5Inv#045 | [5 empty] | 1 | 337.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4087 | 20200810-12 | 53510312 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-08-10 | 1 | Inv#045 | 44067 | 103 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road repairs from B161-B162 | 3 | B161-B181 | Lachance Road | 0 | 44055 |  | 9 | 44056 | [5 empty] | Mandy Sandhu | 03 | Corbiere and Sons Contracting408720200810-12L.O.A.2420 | Corbiere and Sons Contracting408720200810-12L.O.A.2420Inv#045 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4087 | 20200810-12 | 53510312 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2020-08-10 | 1 | Inv#045 | 44067 | 103 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road repairs from B161-B162 | 3 | B161-B181 | Lachance Road | 0 | 44055 |  | 9 | 44056 | [5 empty] | Mandy Sandhu | 03 | Corbiere and Sons Contracting408720200810-12Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting408720200810-12Operator - Principle - After Jan 1011825Inv#045 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4087 | 20200810-12 | 53510312 | Access | 0 | Labourer - General - After Jan 10 | 60 | 11 | HR |  |  | 60 | 0 | 660 | 85.8 | 745.8 | 2020-08-10 | 1 | Inv#045 | 44067 | 103 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road repairs from B161-B162 | 3 | B161-B181 | Lachance Road | 0 | 44055 |  | 9 | 44056 | [5 empty] | Mandy Sandhu | 03 | Corbiere and Sons Contracting408720200810-12Labourer - General - After Jan 1011660 | Corbiere and Sons Contracting408720200810-12Labourer - General - After Jan 1011660Inv#045 | [5 empty] | 1 | 660 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4078 | 20200810-3 | 53520102 | Clearing | 0 | Brusher | 202.5 | 7 | HR | 151.88 | 0 |  |  | 1417.5 | 184.275 | 1601.775 | 2020-08-10 | 1 | Inv#045 | 44067 | 103 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher working from A123 | 1 | A-118 to A-127 | Innes Lake | 0 | 44055 |  | 46 | 44060 | [5 empty] | Glen Greening | 01 | Corbiere and Sons Contracting407820200810-3Brusher71417.5 | Corbiere and Sons Contracting407820200810-3Brusher71417.5Inv#045 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1417.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4078 | 20200810-3 | 53520102 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-08-10 | 1 | Inv#045 | 44067 | 103 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher working from A123 | 1 | A-118 to A-127 | Innes Lake | 0 | 44055 |  | 46 | 44060 | [5 empty] | Glen Greening | 01 | Corbiere and Sons Contracting407820200810-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting407820200810-3Light Truck - Pick up- After Jan 101243.75Inv#045 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4078 | 20200810-3 | 53520102 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-08-10 | 1 | Inv#045 | 44067 | 103 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher working from A123 | 1 | A-118 to A-127 | Innes Lake | 0 | 44055 |  | 46 | 44060 | [5 empty] | Glen Greening | 01 | Corbiere and Sons Contracting407820200810-3L.O.A.2420 | Corbiere and Sons Contracting407820200810-3L.O.A.2420Inv#045 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4078 | 20200810-3 | 53520102 | Clearing | 0 | Operator - Principle - After Jan 10 | 75 | 9 | HR |  |  | 75 | 0 | 675 | 87.75 | 762.75 | 2020-08-10 | 1 | Inv#045 | 44067 | 103 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher working from A123 | 1 | A-118 to A-127 | Innes Lake | 0 | 44055 |  | 46 | 44060 | [5 empty] | Glen Greening | 01 | Corbiere and Sons Contracting407820200810-3Operator - Principle - After Jan 109675 | Corbiere and Sons Contracting407820200810-3Operator - Principle - After Jan 109675Inv#045 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 675 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4078 | 20200810-3 | 53520102 | Clearing | 0 | Labourer - General - After Jan 10 | 60 | 11.5 | HR |  |  | 60 | 0 | 690 | 89.7 | 779.7 | 2020-08-10 | 1 | Inv#045 | 44067 | 103 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher working from A123 | 1 | A-118 to A-127 | Innes Lake | 0 | 44055 |  | 46 | 44060 | [5 empty] | Glen Greening | 01 | Corbiere and Sons Contracting407820200810-3Labourer - General - After Jan 1011.5690 | Corbiere and Sons Contracting407820200810-3Labourer - General - After Jan 1011.5690Inv#045 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 690 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4079 | 20200810-4 | 53520102 | Clearing | 0 | Excavator - 20 ton- After Jan 10 | 104.55 | 9.5 | Dynamic | 78.41 | 0 |  |  | 993.225 | 129.1192 | 1122.3443 | 2020-08-10 | 1 | Inv#045 | 44067 | 103 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rake working from A070; | 1 | A-055 to A-084 | Eldorado | 0 | 44055 |  | 46 | 44060 | [5 empty] | Glen Greening | 01 | Corbiere and Sons Contracting407920200810-4Excavator - 20 ton- After Jan 109.5993.225 | Corbiere and Sons Contracting407920200810-4Excavator - 20 ton- After Jan 109.5993.225Inv#045 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 993.225 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4079 | 20200810-4 | 53520102 | Clearing | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9.5 | HR | 9.16 | 0 |  |  | 115.995 | 15.0793 | 131.0744 | 2020-08-10 | 1 | Inv#045 | 44067 | 103 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rake working from A070; | 1 | A-055 to A-084 | Eldorado | 0 | 44055 |  | 46 | 44060 | [5 empty] | Glen Greening | 01 | Corbiere and Sons Contracting407920200810-4Excavator Thumb - 30 - 50 ton- After Jan 109.5115.995 | Corbiere and Sons Contracting407920200810-4Excavator Thumb - 30 - 50 ton- After Jan 109.5115.995Inv#045 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 115.995 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4079 | 20200810-4 | 53520102 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-08-10 | 1 | Inv#045 | 44067 | 103 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rake working from A070; | 1 | A-055 to A-084 | Eldorado | 0 | 44055 |  | 46 | 44060 | [5 empty] | Glen Greening | 01 | Corbiere and Sons Contracting407920200810-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting407920200810-4Light Truck - Pick up- After Jan 101243.75Inv#045 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4079 | 20200810-4 | 53520102 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-08-10 | 1 | Inv#045 | 44067 | 103 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rake working from A070; | 1 | A-055 to A-084 | Eldorado | 0 | 44055 |  | 46 | 44060 | [5 empty] | Glen Greening | 01 | Corbiere and Sons Contracting407920200810-4L.O.A.1210 | Corbiere and Sons Contracting407920200810-4L.O.A.1210Inv#045 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4079 | 20200810-4 | 53520102 | Clearing | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-08-10 | 1 | Inv#045 | 44067 | 103 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rake working from A070; | 1 | A-055 to A-084 | Eldorado | 0 | 44055 |  | 46 | 44060 | [5 empty] | Glen Greening | 01 | Corbiere and Sons Contracting407920200810-4Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting407920200810-4Operator - Principle - After Jan 1011.5862.5Inv#045 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4080 | 20200810-5 | 53520102 | Clearing | 0 | Brusher | 202.5 | 10 | HR | 151.88 | 0 |  |  | 2025 | 263.25 | 2288.25 | 2020-08-10 | 1 | Inv#045 | 44067 | 103 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher and Rake working from B007-B010; Grinder working from B002-B003; | 1 | A-128 to B-017 | Wolf Lake | 0 | 44055 |  | 46 | 44060 | [5 empty] | Glen Greening | 01 | Corbiere and Sons Contracting408020200810-5Brusher102025 | Corbiere and Sons Contracting408020200810-5Brusher102025Inv#045 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2025 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4080 | 20200810-5 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 6.5 | HR | 417.6 | 0 |  |  | 3619.2 | 470.496 | 4089.696 | 2020-08-10 | 1 | Inv#045 | 44067 | 103 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher and Rake working from B007-B010; Grinder working from B002-B003; | 1 | A-128 to B-017 | Wolf Lake | 0 | 44055 |  | 46 | 44060 | [5 empty] | Glen Greening | 01 | Corbiere and Sons Contracting408020200810-5Grinder - 4710 Peterson or equal6.53619.2 | Corbiere and Sons Contracting408020200810-5Grinder - 4710 Peterson or equal6.53619.2Inv#045 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 3619.2 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4080 | 20200810-5 | 53520102 | Clearing | 0 | Log Loader | 153 | 6.5 | HR | 114.75 | 0 |  |  | 994.5 | 129.285 | 1123.785 | 2020-08-10 | 1 | Inv#045 | 44067 | 103 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher and Rake working from B007-B010; Grinder working from B002-B003; | 1 | A-128 to B-017 | Wolf Lake | 0 | 44055 |  | 46 | 44060 | [5 empty] | Glen Greening | 01 | Corbiere and Sons Contracting408020200810-5Log Loader6.5994.5 | Corbiere and Sons Contracting408020200810-5Log Loader6.5994.5Inv#045 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 994.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4080 | 20200810-5 | 53520102 | Clearing | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 7.5 | Dynamic | 103.84 | 0 |  |  | 1038.375 | 134.9888 | 1173.3637 | 2020-08-10 | 1 | Inv#045 | 44067 | 103 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher and Rake working from B007-B010; Grinder working from B002-B003; | 1 | A-128 to B-017 | Wolf Lake | 0 | 44055 |  | 46 | 44060 | [5 empty] | Glen Greening | 01 | Corbiere and Sons Contracting408020200810-5Excavator - 30 ton- After Jan 107.51038.375 | Corbiere and Sons Contracting408020200810-5Excavator - 30 ton- After Jan 107.51038.375Inv#045 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1038.375 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4080 | 20200810-5 | 53520102 | Clearing | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 7.5 | HR | 9.16 | 0 |  |  | 91.575 | 11.9047 | 103.4797 | 2020-08-10 | 1 | Inv#045 | 44067 | 103 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher and Rake working from B007-B010; Grinder working from B002-B003; | 1 | A-128 to B-017 | Wolf Lake | 0 | 44055 |  | 46 | 44060 | [5 empty] | Glen Greening | 01 | Corbiere and Sons Contracting408020200810-5Excavator Thumb - 30 - 50 ton- After Jan 107.591.575 | Corbiere and Sons Contracting408020200810-5Excavator Thumb - 30 - 50 ton- After Jan 107.591.575Inv#045 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 91.575 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4080 | 20200810-5 | 53520102 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2020-08-10 | 1 | Inv#045 | 44067 | 103 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher and Rake working from B007-B010; Grinder working from B002-B003; | 1 | A-128 to B-017 | Wolf Lake | 0 | 44055 |  | 46 | 44060 | [5 empty] | Glen Greening | 01 | Corbiere and Sons Contracting408020200810-5Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting408020200810-5Light Truck - Pick up- After Jan 103731.25Inv#045 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 731.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4080 | 20200810-5 | 53520102 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2020-08-10 | 1 | Inv#045 | 44067 | 103 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher and Rake working from B007-B010; Grinder working from B002-B003; | 1 | A-128 to B-017 | Wolf Lake | 0 | 44055 |  | 46 | 44060 | [5 empty] | Glen Greening | 01 | Corbiere and Sons Contracting408020200810-5Foreman121140 | Corbiere and Sons Contracting408020200810-5Foreman121140Inv#045 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4080 | 20200810-5 | 53520102 | Clearing | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2020-08-10 | 1 | Inv#045 | 44067 | 103 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher and Rake working from B007-B010; Grinder working from B002-B003; | 1 | A-128 to B-017 | Wolf Lake | 0 | 44055 |  | 46 | 44060 | [5 empty] | Glen Greening | 01 | Corbiere and Sons Contracting408020200810-5L.O.A.51050 | Corbiere and Sons Contracting408020200810-5L.O.A.51050Inv#045 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4080 | 20200810-5 | 53520102 | Clearing | 0 | Operator - Principle - After Jan 10 | 75 | 34.5 | HR |  |  | 75 | 0 | 2587.5 | 336.375 | 2923.875 | 2020-08-10 | 1 | Inv#045 | 44067 | 103 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher and Rake working from B007-B010; Grinder working from B002-B003; | 1 | A-128 to B-017 | Wolf Lake | 0 | 44055 |  | 46 | 44060 | [5 empty] | Glen Greening | 01 | Corbiere and Sons Contracting408020200810-5Operator - Principle - After Jan 1034.52587.5 | Corbiere and Sons Contracting408020200810-5Operator - Principle - After Jan 1034.52587.5Inv#045 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2587.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4080 | 20200810-5 | 53520102 | Clearing | 0 | Labourer - General - After Jan 10 | 60 | 11.5 | HR |  |  | 60 | 0 | 690 | 89.7 | 779.7 | 2020-08-10 | 1 | Inv#045 | 44067 | 103 | 0 | 0 | Nathan Kyme | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher and Rake working from B007-B010; Grinder working from B002-B003; | 1 | A-128 to B-017 | Wolf Lake | 0 | 44055 |  | 46 | 44060 | [5 empty] | Glen Greening | 01 | Corbiere and Sons Contracting408020200810-5Labourer - General - After Jan 1011.5690 | Corbiere and Sons Contracting408020200810-5Labourer - General - After Jan 1011.5690Inv#045 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 690 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4215 | 20200811-3 | 53520102 | Clearing | 0 | Brusher | 202.5 | 7.5 | HR | 151.88 | 0 |  |  | 1518.75 | 197.4375 | 1716.1875 | 2020-08-11 | 1 | Inv#049 | 44088 | 105 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brushing from B010 - Grinding from B003 | 1 | A-128 to B-017 | Wolf Lake | 0 | 44066 |  | 37 | 44067 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting421520200811-3Brusher7.51518.75 | Corbiere and Sons Contracting421520200811-3Brusher7.51518.75Inv#049 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1518.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4215 | 20200811-3 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 13 | HR | 417.6 | 0 |  |  | 7238.4 | 940.992 | 8179.392 | 2020-08-11 | 1 | Inv#049 | 44088 | 105 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brushing from B010 - Grinding from B003 | 1 | A-128 to B-017 | Wolf Lake | 0 | 44066 |  | 37 | 44067 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting421520200811-3Grinder - 4710 Peterson or equal137238.4 | Corbiere and Sons Contracting421520200811-3Grinder - 4710 Peterson or equal137238.4Inv#049 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 7238.4 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4215 | 20200811-3 | 53520102 | Clearing | 0 | Log Loader | 153 | 13 | HR | 114.75 | 0 |  |  | 1989 | 258.57 | 2247.57 | 2020-08-11 | 1 | Inv#049 | 44088 | 105 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brushing from B010 - Grinding from B003 | 1 | A-128 to B-017 | Wolf Lake | 0 | 44066 |  | 37 | 44067 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting421520200811-3Log Loader131989 | Corbiere and Sons Contracting421520200811-3Log Loader131989Inv#049 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1989 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4215 | 20200811-3 | 53520102 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 4 | DAY | 182.81 | 0 |  |  | 975 | 126.75 | 1101.75 | 2020-08-11 | 1 | Inv#049 | 44088 | 105 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brushing from B010 - Grinding from B003 | 1 | A-128 to B-017 | Wolf Lake | 0 | 44066 |  | 37 | 44067 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting421520200811-3Light Truck - Pick up- After Jan 104975 | Corbiere and Sons Contracting421520200811-3Light Truck - Pick up- After Jan 104975Inv#049 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 975 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4215 | 20200811-3 | 53520102 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2020-08-11 | 1 | Inv#049 | 44088 | 105 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brushing from B010 - Grinding from B003 | 1 | A-128 to B-017 | Wolf Lake | 0 | 44066 |  | 37 | 44067 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting421520200811-3Foreman121140 | Corbiere and Sons Contracting421520200811-3Foreman121140Inv#049 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4215 | 20200811-3 | 53520102 | Clearing | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2020-08-11 | 1 | Inv#049 | 44088 | 105 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brushing from B010 - Grinding from B003 | 1 | A-128 to B-017 | Wolf Lake | 0 | 44066 |  | 37 | 44067 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting421520200811-3L.O.A.61260 | Corbiere and Sons Contracting421520200811-3L.O.A.61260Inv#049 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4215 | 20200811-3 | 53520102 | Clearing | 0 | Operator - Principle - After Jan 10 | 75 | 31 | HR |  |  | 75 | 0 | 2325 | 302.25 | 2627.25 | 2020-08-11 | 1 | Inv#049 | 44088 | 105 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brushing from B010 - Grinding from B003 | 1 | A-128 to B-017 | Wolf Lake | 0 | 44066 |  | 37 | 44067 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting421520200811-3Operator - Principle - After Jan 10312325 | Corbiere and Sons Contracting421520200811-3Operator - Principle - After Jan 10312325Inv#049 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2325 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4215 | 20200811-3 | 53520102 | Clearing | 0 | Labourer - General - After Jan 10 | 60 | 19.5 | HR |  |  | 60 | 0 | 1170 | 152.1 | 1322.1 | 2020-08-11 | 1 | Inv#049 | 44088 | 105 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brushing from B010 - Grinding from B003 | 1 | A-128 to B-017 | Wolf Lake | 0 | 44066 |  | 37 | 44067 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting421520200811-3Labourer - General - After Jan 1019.51170 | Corbiere and Sons Contracting421520200811-3Labourer - General - After Jan 1019.51170Inv#049 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1170 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4216 | 20200811-4 | 53520102 | Clearing | 0 | Excavator - 20 ton- After Jan 10 | 104.55 | 9.5 | Dynamic | 78.41 | 0 |  |  | 993.225 | 129.1192 | 1122.3443 | 2020-08-11 | 1 | Inv#049 | 44088 | 105 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rake working across A070; | 1 | A-055 to A-084 | Eldorado | 0 | 44066 |  | 37 | 44067 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting421620200811-4Excavator - 20 ton- After Jan 109.5993.225 | Corbiere and Sons Contracting421620200811-4Excavator - 20 ton- After Jan 109.5993.225Inv#049 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 993.225 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4216 | 20200811-4 | 53520102 | Clearing | 0 | Excavator Thumb - 8 -20 ton- After Jan 10 | 8.76 | 9.5 | HR | 6.57 | 0 |  |  | 83.22 | 10.8186 | 94.0386 | 2020-08-11 | 1 | Inv#049 | 44088 | 105 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rake working across A070; | 1 | A-055 to A-084 | Eldorado | 0 | 44066 |  | 37 | 44067 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting421620200811-4Excavator Thumb - 8 -20 ton- After Jan 109.583.22 | Corbiere and Sons Contracting421620200811-4Excavator Thumb - 8 -20 ton- After Jan 109.583.22Inv#049 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 83.22 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4216 | 20200811-4 | 53520102 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-08-11 | 1 | Inv#049 | 44088 | 105 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rake working across A070; | 1 | A-055 to A-084 | Eldorado | 0 | 44066 |  | 37 | 44067 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting421620200811-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting421620200811-4Light Truck - Pick up- After Jan 101243.75Inv#049 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4216 | 20200811-4 | 53520102 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-08-11 | 1 | Inv#049 | 44088 | 105 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rake working across A070; | 1 | A-055 to A-084 | Eldorado | 0 | 44066 |  | 37 | 44067 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting421620200811-4L.O.A.1210 | Corbiere and Sons Contracting421620200811-4L.O.A.1210Inv#049 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4216 | 20200811-4 | 53520102 | Clearing | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-08-11 | 1 | Inv#049 | 44088 | 105 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rake working across A070; | 1 | A-055 to A-084 | Eldorado | 0 | 44066 |  | 37 | 44067 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting421620200811-4Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting421620200811-4Operator - Principle - After Jan 1011.5862.5Inv#049 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4218 | 20200811-6 | 53510212 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10.5 | Dynamic | 98.61 | 0 |  |  | 1380.54 | 179.4702 | 1560.0102 | 2020-08-11 | 1 | Inv#049 | 44088 | 105 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road repairs from B035 - Gravel brought it - geo layed | 2 | B030 - B044 | Stewart Lake | 0 | 44066 |  | 37 | 44067 | [5 empty] | Harold Furlong | 02 | Corbiere and Sons Contracting421820200811-6Dozer D6 or equal- After Jan 1010.51380.54 | Corbiere and Sons Contracting421820200811-6Dozer D6 or equal- After Jan 1010.51380.54Inv#049 | [5 empty] | 1 | 1380.54 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4218 | 20200811-6 | 53510212 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 67.5 | Dynamic | 41.4 | 0 |  |  | 3726 | 484.38 | 4210.38 | 2020-08-11 | 1 | Inv#049 | 44088 | 105 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road repairs from B035 - Gravel brought it - geo layed | 2 | B030 - B044 | Stewart Lake | 0 | 44066 |  | 37 | 44067 | [5 empty] | Harold Furlong | 02 | Corbiere and Sons Contracting421820200811-6Dump - Triaxle- After Jan 1067.53726 | Corbiere and Sons Contracting421820200811-6Dump - Triaxle- After Jan 1067.53726Inv#049 | [5 empty] | 1 | 3726 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4218 | 20200811-6 | 53510212 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-08-11 | 1 | Inv#049 | 44088 | 105 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road repairs from B035 - Gravel brought it - geo layed | 2 | B030 - B044 | Stewart Lake | 0 | 44066 |  | 37 | 44067 | [5 empty] | Harold Furlong | 02 | Corbiere and Sons Contracting421820200811-6Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting421820200811-6Light Truck - Pick up- After Jan 102487.5Inv#049 | [5 empty] | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4218 | 20200811-6 | 53510212 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-08-11 | 1 | Inv#049 | 44088 | 105 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road repairs from B035 - Gravel brought it - geo layed | 2 | B030 - B044 | Stewart Lake | 0 | 44066 |  | 37 | 44067 | [5 empty] | Harold Furlong | 02 | Corbiere and Sons Contracting421820200811-6L.O.A.2420 | Corbiere and Sons Contracting421820200811-6L.O.A.2420Inv#049 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4218 | 20200811-6 | 53510212 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-08-11 | 1 | Inv#049 | 44088 | 105 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road repairs from B035 - Gravel brought it - geo layed | 2 | B030 - B044 | Stewart Lake | 0 | 44066 |  | 37 | 44067 | [5 empty] | Harold Furlong | 02 | Corbiere and Sons Contracting421820200811-6Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting421820200811-6Operator - Principle - After Jan 1011.5862.5Inv#049 | [5 empty] | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4218 | 20200811-6 | 53510212 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 67.5 | HR |  |  | 70 | 0 | 4725 | 614.25 | 5339.25 | 2020-08-11 | 1 | Inv#049 | 44088 | 105 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road repairs from B035 - Gravel brought it - geo layed | 2 | B030 - B044 | Stewart Lake | 0 | 44066 |  | 37 | 44067 | [5 empty] | Harold Furlong | 02 | Corbiere and Sons Contracting421820200811-6Driver - AZ - After Jan 1067.54725 | Corbiere and Sons Contracting421820200811-6Driver - AZ - After Jan 1067.54725Inv#049 | [5 empty] | 1 | 4725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4218 | 20200811-6 | 53510212 | Access | 0 | Labourer - General - After Jan 10 | 60 | 10 | HR |  |  | 60 | 0 | 600 | 78 | 678 | 2020-08-11 | 1 | Inv#049 | 44088 | 105 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road repairs from B035 - Gravel brought it - geo layed | 2 | B030 - B044 | Stewart Lake | 0 | 44066 |  | 37 | 44067 | [5 empty] | Harold Furlong | 02 | Corbiere and Sons Contracting421820200811-6Labourer - General - After Jan 1010600 | Corbiere and Sons Contracting421820200811-6Labourer - General - After Jan 1010600Inv#049 | [5 empty] | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4224 | 20200812-3 | 53510212 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2020-08-12 | 1 | Inv#049 | 44088 | 105 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road repairs from B035 | 2 | B030 - B044 | Stewart Lake | 0 | 44066 |  | 37 | 44067 | [5 empty] | Harold Furlong | 02 | Corbiere and Sons Contracting422420200812-3Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting422420200812-3Dozer D6 or equal- After Jan 10111446.28Inv#049 | [5 empty] | 1 | 1446.28 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4224 | 20200812-3 | 53510212 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 75.5 | Dynamic | 41.4 | 0 |  |  | 4167.6 | 541.788 | 4709.388 | 2020-08-12 | 1 | Inv#049 | 44088 | 105 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road repairs from B035 | 2 | B030 - B044 | Stewart Lake | 0 | 44066 |  | 37 | 44067 | [5 empty] | Harold Furlong | 02 | Corbiere and Sons Contracting422420200812-3Dump - Triaxle- After Jan 1075.54167.6 | Corbiere and Sons Contracting422420200812-3Dump - Triaxle- After Jan 1075.54167.6Inv#049 | [5 empty] | 1 | 4167.6 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4224 | 20200812-3 | 53510212 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-08-12 | 1 | Inv#049 | 44088 | 105 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road repairs from B035 | 2 | B030 - B044 | Stewart Lake | 0 | 44066 |  | 37 | 44067 | [5 empty] | Harold Furlong | 02 | Corbiere and Sons Contracting422420200812-3Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting422420200812-3Light Truck - Pick up- After Jan 102487.5Inv#049 | [5 empty] | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4224 | 20200812-3 | 53510212 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-08-12 | 1 | Inv#049 | 44088 | 105 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road repairs from B035 | 2 | B030 - B044 | Stewart Lake | 0 | 44066 |  | 37 | 44067 | [5 empty] | Harold Furlong | 02 | Corbiere and Sons Contracting422420200812-3L.O.A.2420 | Corbiere and Sons Contracting422420200812-3L.O.A.2420Inv#049 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4224 | 20200812-3 | 53510212 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2020-08-12 | 1 | Inv#049 | 44088 | 105 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road repairs from B035 | 2 | B030 - B044 | Stewart Lake | 0 | 44066 |  | 37 | 44067 | [5 empty] | Harold Furlong | 02 | Corbiere and Sons Contracting422420200812-3Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting422420200812-3Operator - Principle - After Jan 1012900Inv#049 | [5 empty] | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4224 | 20200812-3 | 53510212 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 75.5 | HR |  |  | 70 | 0 | 5285 | 687.05 | 5972.05 | 2020-08-12 | 1 | Inv#049 | 44088 | 105 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road repairs from B035 | 2 | B030 - B044 | Stewart Lake | 0 | 44066 |  | 37 | 44067 | [5 empty] | Harold Furlong | 02 | Corbiere and Sons Contracting422420200812-3Driver - AZ - After Jan 1075.55285 | Corbiere and Sons Contracting422420200812-3Driver - AZ - After Jan 1075.55285Inv#049 | [5 empty] | 1 | 5285 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4224 | 20200812-3 | 53510212 | Access | 0 | Labourer - General - After Jan 10 | 60 | 7 | HR |  |  | 60 | 0 | 420 | 54.6 | 474.6 | 2020-08-12 | 1 | Inv#049 | 44088 | 105 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road repairs from B035 | 2 | B030 - B044 | Stewart Lake | 0 | 44066 |  | 37 | 44067 | [5 empty] | Harold Furlong | 02 | Corbiere and Sons Contracting422420200812-3Labourer - General - After Jan 107420 | Corbiere and Sons Contracting422420200812-3Labourer - General - After Jan 107420Inv#049 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4226 | 20200812-5 | 53510112 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 9.5 | Dynamic | 95.24 | 0 |  |  | 1206.31 | 156.8203 | 1363.1303 | 2020-08-12 | 1 | Inv#049 | 44088 | 105 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Wolf Lake Access Roads | 1 | A-128 to B-017 | Wolf Lake | 0 | 44066 |  | 37 | 44067 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting422620200812-5Grader - Cat 12 to 14 or equal- After Jan 109.51206.31 | Corbiere and Sons Contracting422620200812-5Grader - Cat 12 to 14 or equal- After Jan 109.51206.31Inv#049 | [5 empty] | 1 | 1206.31 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4226 | 20200812-5 | 53510112 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-08-12 | 1 | Inv#049 | 44088 | 105 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Wolf Lake Access Roads | 1 | A-128 to B-017 | Wolf Lake | 0 | 44066 |  | 37 | 44067 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting422620200812-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting422620200812-5Light Truck - Pick up- After Jan 101243.75Inv#049 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4226 | 20200812-5 | 53510112 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-08-12 | 1 | Inv#049 | 44088 | 105 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Wolf Lake Access Roads | 1 | A-128 to B-017 | Wolf Lake | 0 | 44066 |  | 37 | 44067 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting422620200812-5L.O.A.1210 | Corbiere and Sons Contracting422620200812-5L.O.A.1210Inv#049 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4226 | 20200812-5 | 53510112 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-08-12 | 1 | Inv#049 | 44088 | 105 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Wolf Lake Access Roads | 1 | A-128 to B-017 | Wolf Lake | 0 | 44066 |  | 37 | 44067 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting422620200812-5Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting422620200812-5Operator - Principle - After Jan 1011.5862.5Inv#049 | [5 empty] | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4227 | 20200812-6 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 21.5 | HR | 417.6 | 0 |  |  | 11971.2 | 1556.256 | 13527.456 | 2020-08-12 | 1 | Inv#049 | 44088 | 105 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rake working from A069 - Grinder working from A070; | 1 | A-055 to A-084 | Eldorado | 0 | 44066 |  | 37 | 44067 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting422720200812-6Grinder - 4710 Peterson or equal21.511971.2 | Corbiere and Sons Contracting422720200812-6Grinder - 4710 Peterson or equal21.511971.2Inv#049 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 11971.2 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4227 | 20200812-6 | 53520102 | Clearing | 0 | Log Loader | 153 | 21.5 | HR | 114.75 | 0 |  |  | 3289.5 | 427.635 | 3717.135 | 2020-08-12 | 1 | Inv#049 | 44088 | 105 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rake working from A069 - Grinder working from A070; | 1 | A-055 to A-084 | Eldorado | 0 | 44066 |  | 37 | 44067 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting422720200812-6Log Loader21.53289.5 | Corbiere and Sons Contracting422720200812-6Log Loader21.53289.5Inv#049 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 3289.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4227 | 20200812-6 | 53520102 | Clearing | 0 | Excavator - 20 ton- After Jan 10 | 104.55 | 9.5 | Dynamic | 78.41 | 0 |  |  | 993.225 | 129.1192 | 1122.3443 | 2020-08-12 | 1 | Inv#049 | 44088 | 105 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rake working from A069 - Grinder working from A070; | 1 | A-055 to A-084 | Eldorado | 0 | 44066 |  | 37 | 44067 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting422720200812-6Excavator - 20 ton- After Jan 109.5993.225 | Corbiere and Sons Contracting422720200812-6Excavator - 20 ton- After Jan 109.5993.225Inv#049 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 993.225 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4227 | 20200812-6 | 53520102 | Clearing | 0 | Excavator Thumb - 8 -20 ton- After Jan 10 | 8.76 | 9.5 | HR | 6.57 | 0 |  |  | 83.22 | 10.8186 | 94.0386 | 2020-08-12 | 1 | Inv#049 | 44088 | 105 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rake working from A069 - Grinder working from A070; | 1 | A-055 to A-084 | Eldorado | 0 | 44066 |  | 37 | 44067 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting422720200812-6Excavator Thumb - 8 -20 ton- After Jan 109.583.22 | Corbiere and Sons Contracting422720200812-6Excavator Thumb - 8 -20 ton- After Jan 109.583.22Inv#049 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 83.22 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4227 | 20200812-6 | 53520102 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 4 | DAY | 182.81 | 0 |  |  | 975 | 126.75 | 1101.75 | 2020-08-12 | 1 | Inv#049 | 44088 | 105 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rake working from A069 - Grinder working from A070; | 1 | A-055 to A-084 | Eldorado | 0 | 44066 |  | 37 | 44067 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting422720200812-6Light Truck - Pick up- After Jan 104975 | Corbiere and Sons Contracting422720200812-6Light Truck - Pick up- After Jan 104975Inv#049 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 975 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4227 | 20200812-6 | 53520102 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2020-08-12 | 1 | Inv#049 | 44088 | 105 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rake working from A069 - Grinder working from A070; | 1 | A-055 to A-084 | Eldorado | 0 | 44066 |  | 37 | 44067 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting422720200812-6Foreman121140 | Corbiere and Sons Contracting422720200812-6Foreman121140Inv#049 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4227 | 20200812-6 | 53520102 | Clearing | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2020-08-12 | 1 | Inv#049 | 44088 | 105 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rake working from A069 - Grinder working from A070; | 1 | A-055 to A-084 | Eldorado | 0 | 44066 |  | 37 | 44067 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting422720200812-6L.O.A.61260 | Corbiere and Sons Contracting422720200812-6L.O.A.61260Inv#049 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4227 | 20200812-6 | 53520102 | Clearing | 0 | Operator - Principle - After Jan 10 | 75 | 37 | HR |  |  | 75 | 0 | 2775 | 360.75 | 3135.75 | 2020-08-12 | 1 | Inv#049 | 44088 | 105 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rake working from A069 - Grinder working from A070; | 1 | A-055 to A-084 | Eldorado | 0 | 44066 |  | 37 | 44067 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting422720200812-6Operator - Principle - After Jan 10372775 | Corbiere and Sons Contracting422720200812-6Operator - Principle - After Jan 10372775Inv#049 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2775 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4227 | 20200812-6 | 53520102 | Clearing | 0 | Labourer - General - After Jan 10 | 60 | 25.5 | HR |  |  | 60 | 0 | 1530 | 198.9 | 1728.9 | 2020-08-12 | 1 | Inv#049 | 44088 | 105 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rake working from A069 - Grinder working from A070; | 1 | A-055 to A-084 | Eldorado | 0 | 44066 |  | 37 | 44067 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting422720200812-6Labourer - General - After Jan 1025.51530 | Corbiere and Sons Contracting422720200812-6Labourer - General - After Jan 1025.51530Inv#049 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1530 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4228 | 20200812-7 | 53520102 | Clearing | 0 | Brusher | 202.5 | 4 | HR | 151.88 | 0 |  |  | 810 | 105.3 | 915.3 | 2020-08-12 | 1 | Inv#049 | 44088 | 105 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher working from A122-A120 | 1 | A-118 to A-127 | Innes Lake | 0 | 44066 |  | 37 | 44067 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting422820200812-7Brusher4810 | Corbiere and Sons Contracting422820200812-7Brusher4810Inv#049 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 810 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4228 | 20200812-7 | 53520102 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-08-12 | 1 | Inv#049 | 44088 | 105 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher working from A122-A120 | 1 | A-118 to A-127 | Innes Lake | 0 | 44066 |  | 37 | 44067 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting422820200812-7Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting422820200812-7Light Truck - Pick up- After Jan 101243.75Inv#049 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4228 | 20200812-7 | 53520102 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-08-12 | 1 | Inv#049 | 44088 | 105 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher working from A122-A120 | 1 | A-118 to A-127 | Innes Lake | 0 | 44066 |  | 37 | 44067 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting422820200812-7L.O.A.2420 | Corbiere and Sons Contracting422820200812-7L.O.A.2420Inv#049 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4228 | 20200812-7 | 53520102 | Clearing | 0 | Operator - Principle - After Jan 10 | 75 | 4.5 | HR |  |  | 75 | 0 | 337.5 | 43.875 | 381.375 | 2020-08-12 | 1 | Inv#049 | 44088 | 105 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher working from A122-A120 | 1 | A-118 to A-127 | Innes Lake | 0 | 44066 |  | 37 | 44067 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting422820200812-7Operator - Principle - After Jan 104.5337.5 | Corbiere and Sons Contracting422820200812-7Operator - Principle - After Jan 104.5337.5Inv#049 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 337.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4228 | 20200812-7 | 53520102 | Clearing | 0 | Labourer - General - After Jan 10 | 60 | 7 | HR |  |  | 60 | 0 | 420 | 54.6 | 474.6 | 2020-08-12 | 1 | Inv#049 | 44088 | 105 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher working from A122-A120 | 1 | A-118 to A-127 | Innes Lake | 0 | 44066 |  | 37 | 44067 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting422820200812-7Labourer - General - After Jan 107420 | Corbiere and Sons Contracting422820200812-7Labourer - General - After Jan 107420Inv#049 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4232 | 20200813-3 | 53510112 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 4 | Dynamic | 103.84 | 0 |  |  | 553.8 | 71.994 | 625.794 | 2020-08-13 | 1 | Inv#047 | 44074 | 104 | 0 | 0 | Rachelle Russell | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working accoss Greenwhich - Ex fixing road from A060; | 1 | A-055 to A-084 | Eldorado | 0 | 44057 |  | 37 | 44069 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting423220200813-3Excavator - 30 ton- After Jan 104553.8 | Corbiere and Sons Contracting423220200813-3Excavator - 30 ton- After Jan 104553.8Inv#047 | [5 empty] | 1 | 553.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4232 | 20200813-3 | 53510112 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 4 | HR | 9.16 | 0 |  |  | 48.84 | 6.3492 | 55.1892 | 2020-08-13 | 1 | Inv#047 | 44074 | 104 | 0 | 0 | Rachelle Russell | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working accoss Greenwhich - Ex fixing road from A060; | 1 | A-055 to A-084 | Eldorado | 0 | 44057 |  | 37 | 44069 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting423220200813-3Excavator Thumb - 30 - 50 ton- After Jan 10448.84 | Corbiere and Sons Contracting423220200813-3Excavator Thumb - 30 - 50 ton- After Jan 10448.84Inv#047 | [5 empty] | 1 | 48.84 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4232 | 20200813-3 | 53510112 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 95.24 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2020-08-13 | 1 | Inv#047 | 44074 | 104 | 0 | 0 | Rachelle Russell | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working accoss Greenwhich - Ex fixing road from A060; | 1 | A-055 to A-084 | Eldorado | 0 | 44057 |  | 37 | 44069 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting423220200813-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting423220200813-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8Inv#047 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4232 | 20200813-3 | 53510112 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-08-13 | 1 | Inv#047 | 44074 | 104 | 0 | 0 | Rachelle Russell | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working accoss Greenwhich - Ex fixing road from A060; | 1 | A-055 to A-084 | Eldorado | 0 | 44057 |  | 37 | 44069 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting423220200813-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting423220200813-3Light Truck - Pick up- After Jan 101243.75Inv#047 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4232 | 20200813-3 | 53510112 | Access | 0 | Operator - Intermdiate | 75 | 16 | HR |  |  | 70 | 0 | 1200 | 156 | 1356 | 2020-08-13 | 1 | Inv#047 | 44074 | 104 | 0 | 0 | Rachelle Russell | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working accoss Greenwhich - Ex fixing road from A060; | 1 | A-055 to A-084 | Eldorado | 0 | 44057 |  | 37 | 44069 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting423220200813-3Operator - Intermdiate161200 | Corbiere and Sons Contracting423220200813-3Operator - Intermdiate161200Inv#047 | [5 empty] | 1 | 1200 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4232 | 20200813-3 | 53510112 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-08-13 | 1 | Inv#047 | 44074 | 104 | 0 | 0 | Rachelle Russell | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working accoss Greenwhich - Ex fixing road from A060; | 1 | A-055 to A-084 | Eldorado | 0 | 44057 |  | 37 | 44069 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting423220200813-3L.O.A.2420 | Corbiere and Sons Contracting423220200813-3L.O.A.2420Inv#047 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4232 | 20200813-3 | 53510112 | Access | 0 | Labourer - General - After Jan 10 | 60 | 5 | HR |  |  | 60 | 0 | 300 | 39 | 339 | 2020-08-13 | 1 | Inv#047 | 44074 | 104 | 0 | 0 | Rachelle Russell | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working accoss Greenwhich - Ex fixing road from A060; | 1 | A-055 to A-084 | Eldorado | 0 | 44057 |  | 37 | 44069 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting423220200813-3Labourer - General - After Jan 105300 | Corbiere and Sons Contracting423220200813-3Labourer - General - After Jan 105300Inv#047 | [5 empty] | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4233 | 20200813-4 | 53520102 | Clearing | 0 | Brusher | 202.5 | 4 | HR | 151.88 | 0 |  |  | 810 | 105.3 | 915.3 | 2020-08-13 | 1 | Inv#047 | 44074 | 104 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Tim on Brusher from A119 - Moved log deck from A124 - Eric on Firewatch | 1 | A-118 to A-127 | Innes Lake | 0 | 44058 |  | 37 | 44069 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting423320200813-4Brusher4810 | Corbiere and Sons Contracting423320200813-4Brusher4810Inv#047 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 810 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4233 | 20200813-4 | 53520102 | Clearing | 0 | Skidder | 171 | 2.5 | HR | 128.25 | 0 |  |  | 427.5 | 55.575 | 483.075 | 2020-08-13 | 1 | Inv#047 | 44074 | 104 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Tim on Brusher from A119 - Moved log deck from A124 - Eric on Firewatch | 1 | A-118 to A-127 | Innes Lake | 0 | 44058 |  | 37 | 44069 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting423320200813-4Skidder 2.5427.5 | Corbiere and Sons Contracting423320200813-4Skidder 2.5427.5Inv#047 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 427.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4233 | 20200813-4 | 53520102 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-08-13 | 1 | Inv#047 | 44074 | 104 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Tim on Brusher from A119 - Moved log deck from A124 - Eric on Firewatch | 1 | A-118 to A-127 | Innes Lake | 0 | 44058 |  | 37 | 44069 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting423320200813-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting423320200813-4Light Truck - Pick up- After Jan 101243.75Inv#047 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4233 | 20200813-4 | 53520102 | Clearing | 0 | Operator - Intermdiate | 75 | 7 | HR |  |  | 0 | 0 | 525 | 68.25 | 593.25 | 2020-08-13 | 1 | Inv#047 | 44074 | 104 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Tim on Brusher from A119 - Moved log deck from A124 - Eric on Firewatch | 1 | A-118 to A-127 | Innes Lake | 0 | 44058 |  | 37 | 44069 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting423320200813-4Operator - Intermdiate7525 | Corbiere and Sons Contracting423320200813-4Operator - Intermdiate7525Inv#047 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 525 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4233 | 20200813-4 | 53520102 | Clearing | 0 | Labourer - General - After Jan 10 | 60 | 5.5 | HR |  |  | 0 | 0 | 330 | 42.9 | 372.9 | 2020-08-13 | 1 | Inv#047 | 44074 | 104 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Tim on Brusher from A119 - Moved log deck from A124 - Eric on Firewatch | 1 | A-118 to A-127 | Innes Lake | 0 | 44058 |  | 37 | 44069 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting423320200813-4Labourer - General - After Jan 105.5330 | Corbiere and Sons Contracting423320200813-4Labourer - General - After Jan 105.5330Inv#047 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 330 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4234 | 20200813-5 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 5.5 | HR | 417.6 | 0 |  |  | 3062.4 | 398.112 | 3460.512 | 2020-08-13 | 1 | Inv#047 | 44074 | 104 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grinder finishing up from A065 - Rake working from A066 | 1 | A-055 to A-084 | Eldorado | 0 | 44057 |  | 37 | 44069 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting423420200813-5Grinder - 4710 Peterson or equal5.53062.4 | Corbiere and Sons Contracting423420200813-5Grinder - 4710 Peterson or equal5.53062.4Inv#047 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 3062.4 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4234 | 20200813-5 | 53520102 | Clearing | 0 | Log Loader | 153 | 5.5 | HR | 114.75 | 0 |  |  | 841.5 | 109.395 | 950.895 | 2020-08-13 | 1 | Inv#047 | 44074 | 104 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grinder finishing up from A065 - Rake working from A066 | 1 | A-055 to A-084 | Eldorado | 0 | 44057 |  | 37 | 44069 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting423420200813-5Log Loader5.5841.5 | Corbiere and Sons Contracting423420200813-5Log Loader5.5841.5Inv#047 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 841.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4234 | 20200813-5 | 53520102 | Clearing | 0 | Excavator - 20 ton- After Jan 10 | 104.55 | 9.5 | Dynamic | 78.41 | 0 |  |  | 993.225 | 129.1192 | 1122.3443 | 2020-08-13 | 1 | Inv#047 | 44074 | 104 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grinder finishing up from A065 - Rake working from A066 | 1 | A-055 to A-084 | Eldorado | 0 | 44057 |  | 37 | 44069 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting423420200813-5Excavator - 20 ton- After Jan 109.5993.225 | Corbiere and Sons Contracting423420200813-5Excavator - 20 ton- After Jan 109.5993.225Inv#047 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 993.225 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4234 | 20200813-5 | 53520102 | Clearing | 0 | Excavator Thumb - 8 -20 ton- After Jan 10 | 8.76 | 9.5 | HR | 6.57 | 0 |  |  | 83.22 | 10.8186 | 94.0386 | 2020-08-13 | 1 | Inv#047 | 44074 | 104 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grinder finishing up from A065 - Rake working from A066 | 1 | A-055 to A-084 | Eldorado | 0 | 44057 |  | 37 | 44069 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting423420200813-5Excavator Thumb - 8 -20 ton- After Jan 109.583.22 | Corbiere and Sons Contracting423420200813-5Excavator Thumb - 8 -20 ton- After Jan 109.583.22Inv#047 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 83.22 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4234 | 20200813-5 | 53520102 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 0 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2020-08-13 | 1 | Inv#047 | 44074 | 104 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grinder finishing up from A065 - Rake working from A066 | 1 | A-055 to A-084 | Eldorado | 0 | 44057 |  | 37 | 44069 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting423420200813-5Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting423420200813-5Light Truck - Pick up- After Jan 103731.25Inv#047 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 731.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4234 | 20200813-5 | 53520102 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2020-08-13 | 1 | Inv#047 | 44074 | 104 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grinder finishing up from A065 - Rake working from A066 | 1 | A-055 to A-084 | Eldorado | 0 | 44057 |  | 37 | 44069 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting423420200813-5Foreman121140 | Corbiere and Sons Contracting423420200813-5Foreman121140Inv#047 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4234 | 20200813-5 | 53520102 | Clearing | 0 | Operator - Intermdiate | 75 | 23.5 | HR |  |  | 70 | 0 | 1762.5 | 229.125 | 1991.625 | 2020-08-13 | 1 | Inv#047 | 44074 | 104 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grinder finishing up from A065 - Rake working from A066 | 1 | A-055 to A-084 | Eldorado | 0 | 44057 |  | 37 | 44069 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting423420200813-5Operator - Intermdiate23.51762.5 | Corbiere and Sons Contracting423420200813-5Operator - Intermdiate23.51762.5Inv#047 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1762.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4234 | 20200813-5 | 53520102 | Clearing | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2020-08-13 | 1 | Inv#047 | 44074 | 104 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grinder finishing up from A065 - Rake working from A066 | 1 | A-055 to A-084 | Eldorado | 0 | 44057 |  | 37 | 44069 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting423420200813-5L.O.A.4840 | Corbiere and Sons Contracting423420200813-5L.O.A.4840Inv#047 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4234 | 20200813-5 | 53520102 | Clearing | 0 | Labourer - General - After Jan 10 | 60 | 12 | HR |  |  | 0 | 0 | 720 | 93.6 | 813.6 | 2020-08-13 | 1 | Inv#047 | 44074 | 104 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grinder finishing up from A065 - Rake working from A066 | 1 | A-055 to A-084 | Eldorado | 0 | 44057 |  | 37 | 44069 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting423420200813-5Labourer - General - After Jan 1012720 | Corbiere and Sons Contracting423420200813-5Labourer - General - After Jan 1012720Inv#047 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 720 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4238 | 20200813-9 | 53510212 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 5 | Dynamic | 98.61 | 0 |  |  | 657.4 | 85.462 | 742.862 | 2020-08-13 | 1 | Inv#047 | 44074 | 104 | 0 | 0 | Rachelle Russell | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road repairs from B035-B036 and putting down geo at B042 | 2 | B030 - B044 | Stewart Lake | 0 | 44057 |  | 9 | 44071 | [5 empty] | Mandy Sandhu | 02 | Corbiere and Sons Contracting423820200813-9Dozer D6 or equal- After Jan 105657.4 | Corbiere and Sons Contracting423820200813-9Dozer D6 or equal- After Jan 105657.4Inv#047 | [5 empty] | 1 | 657.4 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4238 | 20200813-9 | 53510212 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 0 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-08-13 | 1 | Inv#047 | 44074 | 104 | 0 | 0 | Rachelle Russell | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road repairs from B035-B036 and putting down geo at B042 | 2 | B030 - B044 | Stewart Lake | 0 | 44057 |  | 9 | 44071 | [5 empty] | Mandy Sandhu | 02 | Corbiere and Sons Contracting423820200813-9Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting423820200813-9Light Truck - Pick up- After Jan 102487.5Inv#047 | [5 empty] | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4238 | 20200813-9 | 53510212 | Access | 0 | Operator - Intermdiate | 75 | 6 | HR |  |  | 0 | 0 | 450 | 58.5 | 508.5 | 2020-08-13 | 1 | Inv#047 | 44074 | 104 | 0 | 0 | Rachelle Russell | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road repairs from B035-B036 and putting down geo at B042 | 2 | B030 - B044 | Stewart Lake | 0 | 44057 |  | 9 | 44071 | [5 empty] | Mandy Sandhu | 02 | Corbiere and Sons Contracting423820200813-9Operator - Intermdiate6450 | Corbiere and Sons Contracting423820200813-9Operator - Intermdiate6450Inv#047 | [5 empty] | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4238 | 20200813-9 | 53510212 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2020-08-13 | 1 | Inv#047 | 44074 | 104 | 0 | 0 | Rachelle Russell | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road repairs from B035-B036 and putting down geo at B042 | 2 | B030 - B044 | Stewart Lake | 0 | 44057 |  | 9 | 44071 | [5 empty] | Mandy Sandhu | 02 | Corbiere and Sons Contracting423820200813-9L.O.A.1210 | Corbiere and Sons Contracting423820200813-9L.O.A.1210Inv#047 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4238 | 20200813-9 | 53510212 | Access | 0 | Labourer - General - After Jan 10 | 60 | 4 | HR |  |  | 0 | 0 | 240 | 31.2 | 271.2 | 2020-08-13 | 1 | Inv#047 | 44074 | 104 | 0 | 0 | Rachelle Russell | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road repairs from B035-B036 and putting down geo at B042 | 2 | B030 - B044 | Stewart Lake | 0 | 44057 |  | 9 | 44071 | [5 empty] | Mandy Sandhu | 02 | Corbiere and Sons Contracting423820200813-9Labourer - General - After Jan 104240 | Corbiere and Sons Contracting423820200813-9Labourer - General - After Jan 104240Inv#047 | [5 empty] | 1 | 240 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4244 | 20200814-4 | 53510112 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 95.24 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2020-08-14 | 1 | Inv#047 | 44074 | 104 | 0 | 0 | Rachelle Russell | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Greenwich and Nash | 1 | A-055 to A-084 | Eldorado | 0 | 44058 |  | 37 | 44069 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting424420200814-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting424420200814-4Grader - Cat 12 to 14 or equal- After Jan 10101269.8Inv#047 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4244 | 20200814-4 | 53510112 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2020-08-14 | 1 | Inv#047 | 44074 | 104 | 0 | 0 | Rachelle Russell | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Greenwich and Nash | 1 | A-055 to A-084 | Eldorado | 0 | 44058 |  | 37 | 44069 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting424420200814-4L.O.A.1210 | Corbiere and Sons Contracting424420200814-4L.O.A.1210Inv#047 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4244 | 20200814-4 | 53510112 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-08-14 | 1 | Inv#047 | 44074 | 104 | 0 | 0 | Rachelle Russell | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Greenwich and Nash | 1 | A-055 to A-084 | Eldorado | 0 | 44058 |  | 37 | 44069 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting424420200814-4Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting424420200814-4Operator - Principle - After Jan 1011.5862.5Inv#047 | [5 empty] | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4245 | 20200814-5 | 53520102 | Clearing | 0 | Brusher | 202.5 | 10.5 | HR | 151.88 | 0 |  |  | 2126.25 | 276.4125 | 2402.6625 | 2020-08-14 | 1 | Inv#047 | 44074 | 104 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Tim on brusher from A118-A119moved log deck with skidder from A124 - Ben on firewatch Ron working brusher from A122. Grinder from A124 - Jesse on firewatch | 1 | A-118 to A-127 | Innes Lake | 0 | 44058 |  | 37 | 44069 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting424520200814-5Brusher10.52126.25 | Corbiere and Sons Contracting424520200814-5Brusher10.52126.25Inv#047 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2126.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4245 | 20200814-5 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 9 | HR | 417.6 | 0 |  |  | 5011.2 | 651.456 | 5662.656 | 2020-08-14 | 1 | Inv#047 | 44074 | 104 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Tim on brusher from A118-A119moved log deck with skidder from A124 - Ben on firewatch Ron working brusher from A122. Grinder from A124 - Jesse on firewatch | 1 | A-118 to A-127 | Innes Lake | 0 | 44058 |  | 37 | 44069 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting424520200814-5Grinder - 4710 Peterson or equal95011.2 | Corbiere and Sons Contracting424520200814-5Grinder - 4710 Peterson or equal95011.2Inv#047 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 5011.2 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4245 | 20200814-5 | 53520102 | Clearing | 0 | Log Loader | 153 | 9 | HR | 114.75 | 0 |  |  | 1377 | 179.01 | 1556.01 | 2020-08-14 | 1 | Inv#047 | 44074 | 104 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Tim on brusher from A118-A119moved log deck with skidder from A124 - Ben on firewatch Ron working brusher from A122. Grinder from A124 - Jesse on firewatch | 1 | A-118 to A-127 | Innes Lake | 0 | 44058 |  | 37 | 44069 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting424520200814-5Log Loader91377 | Corbiere and Sons Contracting424520200814-5Log Loader91377Inv#047 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1377 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4245 | 20200814-5 | 53520102 | Clearing | 0 | Skidder | 171 | 2.5 | HR | 128.25 | 0 |  |  | 427.5 | 55.575 | 483.075 | 2020-08-14 | 1 | Inv#047 | 44074 | 104 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Tim on brusher from A118-A119moved log deck with skidder from A124 - Ben on firewatch Ron working brusher from A122. Grinder from A124 - Jesse on firewatch | 1 | A-118 to A-127 | Innes Lake | 0 | 44058 |  | 37 | 44069 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting424520200814-5Skidder 2.5427.5 | Corbiere and Sons Contracting424520200814-5Skidder 2.5427.5Inv#047 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 427.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4245 | 20200814-5 | 53520102 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 4 | DAY | 182.81 | 0 |  |  | 975 | 126.75 | 1101.75 | 2020-08-14 | 1 | Inv#047 | 44074 | 104 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Tim on brusher from A118-A119moved log deck with skidder from A124 - Ben on firewatch Ron working brusher from A122. Grinder from A124 - Jesse on firewatch | 1 | A-118 to A-127 | Innes Lake | 0 | 44058 |  | 37 | 44069 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting424520200814-5Light Truck - Pick up- After Jan 104975 | Corbiere and Sons Contracting424520200814-5Light Truck - Pick up- After Jan 104975Inv#047 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 975 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4245 | 20200814-5 | 53520102 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2020-08-14 | 1 | Inv#047 | 44074 | 104 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Tim on brusher from A118-A119moved log deck with skidder from A124 - Ben on firewatch Ron working brusher from A122. Grinder from A124 - Jesse on firewatch | 1 | A-118 to A-127 | Innes Lake | 0 | 44058 |  | 37 | 44069 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting424520200814-5Foreman121140 | Corbiere and Sons Contracting424520200814-5Foreman121140Inv#047 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4245 | 20200814-5 | 53520102 | Clearing | 0 | L.O.A. | 210 | 5 | DAY |  |  | 0 | 0 | 1050 | 136.5 | 1186.5 | 2020-08-14 | 1 | Inv#047 | 44074 | 104 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Tim on brusher from A118-A119moved log deck with skidder from A124 - Ben on firewatch Ron working brusher from A122. Grinder from A124 - Jesse on firewatch | 1 | A-118 to A-127 | Innes Lake | 0 | 44058 |  | 37 | 44069 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting424520200814-5L.O.A.51050 | Corbiere and Sons Contracting424520200814-5L.O.A.51050Inv#047 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4245 | 20200814-5 | 53520102 | Clearing | 0 | Operator - Principle - After Jan 10 | 75 | 25 | HR |  |  | 0 | 0 | 1875 | 243.75 | 2118.75 | 2020-08-14 | 1 | Inv#047 | 44074 | 104 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Tim on brusher from A118-A119moved log deck with skidder from A124 - Ben on firewatch Ron working brusher from A122. Grinder from A124 - Jesse on firewatch | 1 | A-118 to A-127 | Innes Lake | 0 | 44058 |  | 37 | 44069 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting424520200814-5Operator - Principle - After Jan 10251875 | Corbiere and Sons Contracting424520200814-5Operator - Principle - After Jan 10251875Inv#047 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1875 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4245 | 20200814-5 | 53520102 | Clearing | 0 | Labourer - General - After Jan 10 | 60 | 26.5 | HR |  |  | 60 | 0 | 1590 | 206.7 | 1796.7 | 2020-08-14 | 1 | Inv#047 | 44074 | 104 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Tim on brusher from A118-A119moved log deck with skidder from A124 - Ben on firewatch Ron working brusher from A122. Grinder from A124 - Jesse on firewatch | 1 | A-118 to A-127 | Innes Lake | 0 | 44058 |  | 37 | 44069 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting424520200814-5Labourer - General - After Jan 1026.51590 | Corbiere and Sons Contracting424520200814-5Labourer - General - After Jan 1026.51590Inv#047 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1590 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4246 | 20200814-6 | 53520102 | Clearing | 0 | Brusher | 202.5 | 10 | HR | 0 | 0 |  |  | 2025 | 263.25 | 2288.25 | 2020-08-14 | 1 | Inv#047 | 44074 | 104 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brushing from B011-B012 all day - Eric on firewatch | 1 | A-128 to B-017 | Wolf Lake | 0 | 44058 |  | 37 | 44069 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting424620200814-6Brusher102025 | Corbiere and Sons Contracting424620200814-6Brusher102025Inv#047 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2025 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4246 | 20200814-6 | 53520102 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2020-08-14 | 1 | Inv#047 | 44074 | 104 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brushing from B011-B012 all day - Eric on firewatch | 1 | A-128 to B-017 | Wolf Lake | 0 | 44058 |  | 37 | 44069 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting424620200814-6L.O.A.1210 | Corbiere and Sons Contracting424620200814-6L.O.A.1210Inv#047 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4246 | 20200814-6 | 53520102 | Clearing | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 0 | 0 | 862.5 | 112.125 | 974.625 | 2020-08-14 | 1 | Inv#047 | 44074 | 104 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brushing from B011-B012 all day - Eric on firewatch | 1 | A-128 to B-017 | Wolf Lake | 0 | 44058 |  | 37 | 44069 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting424620200814-6Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting424620200814-6Operator - Principle - After Jan 1011.5862.5Inv#047 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4246 | 20200814-6 | 53520102 | Clearing | 0 | Labourer - General - After Jan 10 | 60 | 11.5 | HR |  |  | 0 | 0 | 690 | 89.7 | 779.7 | 2020-08-14 | 1 | Inv#047 | 44074 | 104 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brushing from B011-B012 all day - Eric on firewatch | 1 | A-128 to B-017 | Wolf Lake | 0 | 44058 |  | 37 | 44069 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting424620200814-6Labourer - General - After Jan 1011.5690 | Corbiere and Sons Contracting424620200814-6Labourer - General - After Jan 1011.5690Inv#047 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 690 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4247 | 20200814-7 | 53520102 | Clearing | 0 | Excavator - 20 ton- After Jan 10 | 104.55 | 9.5 | Dynamic | 78.41 | 0 |  |  | 993.225 | 129.1192 | 1122.3443 | 2020-08-14 | 1 | Inv#047 | 44074 | 104 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Raking from A065 | 1 | A-055 to A-084 | Eldorado | 0 | 44058 |  | 37 | 44069 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting424720200814-7Excavator - 20 ton- After Jan 109.5993.225 | Corbiere and Sons Contracting424720200814-7Excavator - 20 ton- After Jan 109.5993.225Inv#047 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 993.225 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4247 | 20200814-7 | 53520102 | Clearing | 0 | Excavator Thumb - 8 -20 ton- After Jan 10 | 8.76 | 9.5 | HR | 6.57 | 0 |  |  | 83.22 | 10.8186 | 94.0386 | 2020-08-14 | 1 | Inv#047 | 44074 | 104 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Raking from A065 | 1 | A-055 to A-084 | Eldorado | 0 | 44058 |  | 37 | 44069 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting424720200814-7Excavator Thumb - 8 -20 ton- After Jan 109.583.22 | Corbiere and Sons Contracting424720200814-7Excavator Thumb - 8 -20 ton- After Jan 109.583.22Inv#047 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 83.22 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4247 | 20200814-7 | 53520102 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-08-14 | 1 | Inv#047 | 44074 | 104 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Raking from A065 | 1 | A-055 to A-084 | Eldorado | 0 | 44058 |  | 37 | 44069 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting424720200814-7Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting424720200814-7Light Truck - Pick up- After Jan 101243.75Inv#047 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4247 | 20200814-7 | 53520102 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2020-08-14 | 1 | Inv#047 | 44074 | 104 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Raking from A065 | 1 | A-055 to A-084 | Eldorado | 0 | 44058 |  | 37 | 44069 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting424720200814-7L.O.A.1210 | Corbiere and Sons Contracting424720200814-7L.O.A.1210Inv#047 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4247 | 20200814-7 | 53520102 | Clearing | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 0 | 0 | 862.5 | 112.125 | 974.625 | 2020-08-14 | 1 | Inv#047 | 44074 | 104 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Raking from A065 | 1 | A-055 to A-084 | Eldorado | 0 | 44058 |  | 37 | 44069 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting424720200814-7Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting424720200814-7Operator - Principle - After Jan 1011.5862.5Inv#047 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4280 | 20200817-10 | 53520102 | Clearing | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 4 | Dynamic | 91.79 | 0 |  |  | 489.56 | 63.6428 | 553.2028 | 2020-08-17 | 1 | Inv#047 | 44074 | 104 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float RT-03 mobilized BR-03 into WF2 at Lofty Davies Rd. | 2 | B054 - B064 | Lofty Davies | 0 | 44061 |  | 37 | 44069 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting428020200817-10Tractor Trailer - 60 Ton- After Jan 104489.56 | Corbiere and Sons Contracting428020200817-10Tractor Trailer - 60 Ton- After Jan 104489.56Inv#047 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 489.56 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4275 | 20200817-5 | 53520102 | Clearing | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 5 | Dynamic | 110.22 | 0 |  |  | 734.8 | 95.524 | 830.324 | 2020-08-17 | 1 | Inv#047 | 44074 | 104 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Finished up raking from A-065. | 1 | A-055 to A-084 | Eldorado | 0 | 44061 |  | 37 | 44069 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting427520200817-5Excavator - 36 ton- After Jan 105734.8 | Corbiere and Sons Contracting427520200817-5Excavator - 36 ton- After Jan 105734.8Inv#047 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 734.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4275 | 20200817-5 | 53520102 | Clearing | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 5 | HR | 9.16 | 0 |  |  | 61.05 | 7.9365 | 68.9865 | 2020-08-17 | 1 | Inv#047 | 44074 | 104 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Finished up raking from A-065. | 1 | A-055 to A-084 | Eldorado | 0 | 44061 |  | 37 | 44069 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting427520200817-5Excavator Thumb - 30 - 50 ton- After Jan 10561.05 | Corbiere and Sons Contracting427520200817-5Excavator Thumb - 30 - 50 ton- After Jan 10561.05Inv#047 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 61.05 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4275 | 20200817-5 | 53520102 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-08-17 | 1 | Inv#047 | 44074 | 104 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Finished up raking from A-065. | 1 | A-055 to A-084 | Eldorado | 0 | 44061 |  | 37 | 44069 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting427520200817-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting427520200817-5Light Truck - Pick up- After Jan 101243.75Inv#047 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4275 | 20200817-5 | 53520102 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-08-17 | 1 | Inv#047 | 44074 | 104 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Finished up raking from A-065. | 1 | A-055 to A-084 | Eldorado | 0 | 44061 |  | 37 | 44069 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting427520200817-5L.O.A.1210 | Corbiere and Sons Contracting427520200817-5L.O.A.1210Inv#047 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4275 | 20200817-5 | 53520102 | Clearing | 0 | Operator - Principle - After Jan 10 | 75 | 7 | HR |  |  | 75 | 0 | 525 | 68.25 | 593.25 | 2020-08-17 | 1 | Inv#047 | 44074 | 104 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Finished up raking from A-065. | 1 | A-055 to A-084 | Eldorado | 0 | 44061 |  | 37 | 44069 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting427520200817-5Operator - Principle - After Jan 107525 | Corbiere and Sons Contracting427520200817-5Operator - Principle - After Jan 107525Inv#047 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 525 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4276 | 20200817-6 | 53520102 | Clearing | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 9.5 | Dynamic | 95.24 | 0 |  |  | 1206.31 | 156.8203 | 1363.1303 | 2020-08-17 | 1 | Inv#047 | 44074 | 104 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Finished up raking from A-065. | 0 |  |  | 0 | 44061 |  | 37 | 44069 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting427620200817-6Grader - Cat 12 to 14 or equal- After Jan 109.51206.31 | Corbiere and Sons Contracting427620200817-6Grader - Cat 12 to 14 or equal- After Jan 109.51206.31Inv#047 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1206.31 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4276 | 20200817-6 | 53520102 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-08-17 | 1 | Inv#047 | 44074 | 104 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Finished up raking from A-065. | 0 |  |  | 0 | 44061 |  | 37 | 44069 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting427620200817-6Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting427620200817-6Light Truck - Pick up- After Jan 101243.75Inv#047 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4276 | 20200817-6 | 53520102 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2020-08-17 | 1 | Inv#047 | 44074 | 104 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Finished up raking from A-065. | 0 |  |  | 0 | 44061 |  | 37 | 44069 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting427620200817-6L.O.A.1210 | Corbiere and Sons Contracting427620200817-6L.O.A.1210Inv#047 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4276 | 20200817-6 | 53520102 | Clearing | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 0 | 0 | 862.5 | 112.125 | 974.625 | 2020-08-17 | 1 | Inv#047 | 44074 | 104 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Finished up raking from A-065. | 0 |  |  | 0 | 44061 |  | 37 | 44069 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting427620200817-6Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting427620200817-6Operator - Principle - After Jan 1011.5862.5Inv#047 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4277 | 20200817-7 | 53520102 | Clearing | 0 | Brusher | 202.5 | 4 | HR | 151.88 | 0 |  |  | 810 | 105.3 | 915.3 | 2020-08-17 | 1 | Inv#047 | 44074 | 104 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher from B-012 to B-014 - Finished WF1 at 11am - Eric on fire watch | 1 | A-128 to B-017 | Wolf Lake | 0 | 44061 |  | 37 | 44069 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting427720200817-7Brusher4810 | Corbiere and Sons Contracting427720200817-7Brusher4810Inv#047 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 810 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4277 | 20200817-7 | 53520102 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 0 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-08-17 | 1 | Inv#047 | 44074 | 104 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher from B-012 to B-014 - Finished WF1 at 11am - Eric on fire watch | 1 | A-128 to B-017 | Wolf Lake | 0 | 44061 |  | 37 | 44069 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting427720200817-7Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting427720200817-7Light Truck - Pick up- After Jan 101243.75Inv#047 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4277 | 20200817-7 | 53520102 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  | 0 | 0 | 210 | 27.3 | 237.3 | 2020-08-17 | 1 | Inv#047 | 44074 | 104 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher from B-012 to B-014 - Finished WF1 at 11am - Eric on fire watch | 1 | A-128 to B-017 | Wolf Lake | 0 | 44061 |  | 37 | 44069 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting427720200817-7L.O.A.1210 | Corbiere and Sons Contracting427720200817-7L.O.A.1210Inv#047 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4277 | 20200817-7 | 53520102 | Clearing | 0 | Operator - Principle - After Jan 10 | 75 | 4.5 | HR |  |  | 0 | 0 | 337.5 | 43.875 | 381.375 | 2020-08-17 | 1 | Inv#047 | 44074 | 104 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher from B-012 to B-014 - Finished WF1 at 11am - Eric on fire watch | 1 | A-128 to B-017 | Wolf Lake | 0 | 44061 |  | 37 | 44069 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting427720200817-7Operator - Principle - After Jan 104.5337.5 | Corbiere and Sons Contracting427720200817-7Operator - Principle - After Jan 104.5337.5Inv#047 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 337.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4277 | 20200817-7 | 53520102 | Clearing | 0 | Labourer - General - After Jan 10 | 60 | 5.5 | HR |  |  | 60 | 0 | 330 | 42.9 | 372.9 | 2020-08-17 | 1 | Inv#047 | 44074 | 104 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher from B-012 to B-014 - Finished WF1 at 11am - Eric on fire watch | 1 | A-128 to B-017 | Wolf Lake | 0 | 44061 |  | 37 | 44069 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting427720200817-7Labourer - General - After Jan 105.5330 | Corbiere and Sons Contracting427720200817-7Labourer - General - After Jan 105.5330Inv#047 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 330 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4278 | 20200817-8 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 20.5 | HR | 417.6 | 0 |  |  | 11414.4 | 1483.872 | 12898.272 | 2020-08-17 | 1 | Inv#047 | 44074 | 104 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Day shift/night shift grinder from B-006 Eastward- Harley & Jesse on fire watch | 1 | A-128 to B-017 | Wolf Lake | 0 | 44061 |  | 37 | 44069 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting427820200817-8Grinder - 4710 Peterson or equal20.511414.4 | Corbiere and Sons Contracting427820200817-8Grinder - 4710 Peterson or equal20.511414.4Inv#047 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 11414.4 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4278 | 20200817-8 | 53520102 | Clearing | 0 | Log Loader | 153 | 20.5 | HR | 114.75 | 0 |  |  | 3136.5 | 407.745 | 3544.245 | 2020-08-17 | 1 | Inv#047 | 44074 | 104 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Day shift/night shift grinder from B-006 Eastward- Harley & Jesse on fire watch | 1 | A-128 to B-017 | Wolf Lake | 0 | 44061 |  | 37 | 44069 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting427820200817-8Log Loader20.53136.5 | Corbiere and Sons Contracting427820200817-8Log Loader20.53136.5Inv#047 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 3136.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4278 | 20200817-8 | 53520102 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 0 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2020-08-17 | 1 | Inv#047 | 44074 | 104 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Day shift/night shift grinder from B-006 Eastward- Harley & Jesse on fire watch | 1 | A-128 to B-017 | Wolf Lake | 0 | 44061 |  | 37 | 44069 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting427820200817-8Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting427820200817-8Light Truck - Pick up- After Jan 103731.25Inv#047 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 731.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4278 | 20200817-8 | 53520102 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2020-08-17 | 1 | Inv#047 | 44074 | 104 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Day shift/night shift grinder from B-006 Eastward- Harley & Jesse on fire watch | 1 | A-128 to B-017 | Wolf Lake | 0 | 44061 |  | 37 | 44069 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting427820200817-8Foreman121140 | Corbiere and Sons Contracting427820200817-8Foreman121140Inv#047 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4278 | 20200817-8 | 53520102 | Clearing | 0 | L.O.A. | 210 | 5 | DAY |  |  | 0 | 0 | 1050 | 136.5 | 1186.5 | 2020-08-17 | 1 | Inv#047 | 44074 | 104 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Day shift/night shift grinder from B-006 Eastward- Harley & Jesse on fire watch | 1 | A-128 to B-017 | Wolf Lake | 0 | 44061 |  | 37 | 44069 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting427820200817-8L.O.A.51050 | Corbiere and Sons Contracting427820200817-8L.O.A.51050Inv#047 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4278 | 20200817-8 | 53520102 | Clearing | 0 | Operator - Principle - After Jan 10 | 75 | 26 | HR |  |  | 0 | 0 | 1950 | 253.5 | 2203.5 | 2020-08-17 | 1 | Inv#047 | 44074 | 104 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Day shift/night shift grinder from B-006 Eastward- Harley & Jesse on fire watch | 1 | A-128 to B-017 | Wolf Lake | 0 | 44061 |  | 37 | 44069 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting427820200817-8Operator - Principle - After Jan 10261950 | Corbiere and Sons Contracting427820200817-8Operator - Principle - After Jan 10261950Inv#047 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1950 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4278 | 20200817-8 | 53520102 | Clearing | 0 | Labourer - General - After Jan 10 | 60 | 26 | HR |  |  | 0 | 0 | 1560 | 202.8 | 1762.8 | 2020-08-17 | 1 | Inv#047 | 44074 | 104 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Day shift/night shift grinder from B-006 Eastward- Harley & Jesse on fire watch | 1 | A-128 to B-017 | Wolf Lake | 0 | 44061 |  | 37 | 44069 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting427820200817-8Labourer - General - After Jan 10261560 | Corbiere and Sons Contracting427820200817-8Labourer - General - After Jan 10261560Inv#047 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1560 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4279 | 20200817-9-R1 | 53520102 | Clearing | 0 | Chainsaw and consumables- After Jan 10 | 60 | 11 | unit/man/day | 0 | 0 |  |  |  | 85.8 | 745.8 | 2020-08-17 | 1 | Inv#047 | 44074 | 104 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  | Truck- 5 instead of 50? |  | Approved |  |  | Hand Falling in designated bat areas in WF3 | 3 | B-151 to B-158 | Kama Hills Rd - W to Kama Hills Rd - E | 0 | 44061 |  | 48 | 44069 | [5 empty] | Tim Case | 01 | Corbiere and Sons Contracting427920200817-9-R1Chainsaw and consumables- After Jan 1011660 | Corbiere and Sons Contracting427920200817-9-R1Chainsaw and consumables- After Jan 1011660Inv#047 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 660 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4279 | 20200817-9-R1 | 53520102 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 5 | DAY | 0 | 0 |  |  |  | 158.4375 | 1377.1875 | 2020-08-17 | 1 | Inv#047 | 44074 | 104 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  | Truck- 5 instead of 50? |  | Approved |  |  | Hand Falling in designated bat areas in WF3 | 3 | B-151 to B-158 | Kama Hills Rd - W to Kama Hills Rd - E | 0 | 44061 |  | 48 | 44069 | [5 empty] | Tim Case | 01 | Corbiere and Sons Contracting427920200817-9-R1Light Truck - Pick up- After Jan 1051218.75 | Corbiere and Sons Contracting427920200817-9-R1Light Truck - Pick up- After Jan 1051218.75Inv#047 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1218.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4279 | 20200817-9-R1 | 53520102 | Clearing | 0 | L.O.A. | 210 | 11 | DAY |  |  | 0 | 0 |  | 300.3 | 2610.3 | 2020-08-17 | 1 | Inv#047 | 44074 | 104 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  | Truck- 5 instead of 50? |  | Approved |  |  | Hand Falling in designated bat areas in WF3 | 3 | B-151 to B-158 | Kama Hills Rd - W to Kama Hills Rd - E | 0 | 44061 |  | 48 | 44069 | [5 empty] | Tim Case | 01 | Corbiere and Sons Contracting427920200817-9-R1L.O.A.112310 | Corbiere and Sons Contracting427920200817-9-R1L.O.A.112310Inv#047 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2310 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4279 | 20200817-9-R1 | 53520102 | Clearing | 0 | Labourer - Specialized - After Jan 10 | 70 | 121 | HR |  |  | 70 | 0 |  | 1101.1 | 9571.1 | 2020-08-17 | 1 | Inv#047 | 44074 | 104 | 0 | 0 | Rachelle Russell | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  | Truck- 5 instead of 50? |  | Approved |  |  | Hand Falling in designated bat areas in WF3 | 3 | B-151 to B-158 | Kama Hills Rd - W to Kama Hills Rd - E | 0 | 44061 |  | 48 | 44069 | [5 empty] | Tim Case | 01 | Corbiere and Sons Contracting427920200817-9-R1Labourer - Specialized - After Jan 101218470 | Corbiere and Sons Contracting427920200817-9-R1Labourer - Specialized - After Jan 101218470Inv#047 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 8470 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4287 | 20200818-3 | 53510112 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 103.84 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2020-08-18 | 1 | Inv#049 | 44088 | 105 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance on Eldorado betweek KM14 and KM11Grader working across Eldorado and NashBen rolled out geo for road repair | 1 | A-055 to A-084 | Eldorado | 0 | 44068 |  | 37 | 44070 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting428720200818-3Excavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting428720200818-3Excavator - 30 ton- After Jan 1091246.05Inv#049 | [5 empty] | 1 | 1246.05 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4287 | 20200818-3 | 53510112 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2020-08-18 | 1 | Inv#049 | 44088 | 105 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance on Eldorado betweek KM14 and KM11Grader working across Eldorado and NashBen rolled out geo for road repair | 1 | A-055 to A-084 | Eldorado | 0 | 44068 |  | 37 | 44070 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting428720200818-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting428720200818-3Excavator Thumb - 30 - 50 ton- After Jan 109109.89Inv#049 | [5 empty] | 1 | 109.89 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4287 | 20200818-3 | 53510112 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 95.24 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2020-08-18 | 1 | Inv#049 | 44088 | 105 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance on Eldorado betweek KM14 and KM11Grader working across Eldorado and NashBen rolled out geo for road repair | 1 | A-055 to A-084 | Eldorado | 0 | 44068 |  | 37 | 44070 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting428720200818-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting428720200818-3Grader - Cat 12 to 14 or equal- After Jan 10101269.8Inv#049 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4287 | 20200818-3 | 53510112 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-08-18 | 1 | Inv#049 | 44088 | 105 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance on Eldorado betweek KM14 and KM11Grader working across Eldorado and NashBen rolled out geo for road repair | 1 | A-055 to A-084 | Eldorado | 0 | 44068 |  | 37 | 44070 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting428720200818-3Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting428720200818-3Light Truck - Pick up- After Jan 102487.5Inv#049 | [5 empty] | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4287 | 20200818-3 | 53510112 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2020-08-18 | 1 | Inv#049 | 44088 | 105 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance on Eldorado betweek KM14 and KM11Grader working across Eldorado and NashBen rolled out geo for road repair | 1 | A-055 to A-084 | Eldorado | 0 | 44068 |  | 37 | 44070 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting428720200818-3L.O.A.3630 | Corbiere and Sons Contracting428720200818-3L.O.A.3630Inv#049 | [5 empty] | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4287 | 20200818-3 | 53510112 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 22 | HR |  |  | 75 | 0 | 1650 | 214.5 | 1864.5 | 2020-08-18 | 1 | Inv#049 | 44088 | 105 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance on Eldorado betweek KM14 and KM11Grader working across Eldorado and NashBen rolled out geo for road repair | 1 | A-055 to A-084 | Eldorado | 0 | 44068 |  | 37 | 44070 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting428720200818-3Operator - Principle - After Jan 10221650 | Corbiere and Sons Contracting428720200818-3Operator - Principle - After Jan 10221650Inv#049 | [5 empty] | 1 | 1650 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4287 | 20200818-3 | 53510112 | Access | 0 | Labourer - General - After Jan 10 | 60 | 2 | HR |  |  | 60 | 0 | 120 | 15.6 | 135.6 | 2020-08-18 | 1 | Inv#049 | 44088 | 105 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance on Eldorado betweek KM14 and KM11Grader working across Eldorado and NashBen rolled out geo for road repair | 1 | A-055 to A-084 | Eldorado | 0 | 44068 |  | 37 | 44070 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting428720200818-3Labourer - General - After Jan 102120 | Corbiere and Sons Contracting428720200818-3Labourer - General - After Jan 102120Inv#049 | [5 empty] | 1 | 120 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4288 | 20200818-4 | 53520102 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-08-18 | 1 | Inv#049 | 44088 | 105 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Leslie mobed in brusherBen escorted SKD from A124Float moved SKD from Innes to shop and brusher back to Eldorado for touchups | 1 | A-055 to A-084 | Eldorado | 0 | 44068 |  | 37 | 44070 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting428820200818-4L.O.A.1210 | Corbiere and Sons Contracting428820200818-4L.O.A.1210Inv#049 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4289 | 20200818-5 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 23 | HR | 417.6 | 0 |  |  | 12806.4 | 1664.832 | 14471.232 | 2020-08-18 | 1 | Inv#049 | 44088 | 105 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Day shift grinder from B-006 to B-008 - Harley on fire watchNight shift grinder from B-008 to B-010 - Jesse on fire watch | 1 | A-128 to B-017 | Wolf Lake | 0 | 44068 |  | 37 | 44070 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting428920200818-5Grinder - 4710 Peterson or equal2312806.4 | Corbiere and Sons Contracting428920200818-5Grinder - 4710 Peterson or equal2312806.4Inv#049 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 12806.4 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4289 | 20200818-5 | 53520102 | Clearing | 0 | Log Loader | 153 | 23 | HR | 114.75 | 0 |  |  | 3519 | 457.47 | 3976.47 | 2020-08-18 | 1 | Inv#049 | 44088 | 105 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Day shift grinder from B-006 to B-008 - Harley on fire watchNight shift grinder from B-008 to B-010 - Jesse on fire watch | 1 | A-128 to B-017 | Wolf Lake | 0 | 44068 |  | 37 | 44070 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting428920200818-5Log Loader233519 | Corbiere and Sons Contracting428920200818-5Log Loader233519Inv#049 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 3519 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4289 | 20200818-5 | 53520102 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2020-08-18 | 1 | Inv#049 | 44088 | 105 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Day shift grinder from B-006 to B-008 - Harley on fire watchNight shift grinder from B-008 to B-010 - Jesse on fire watch | 1 | A-128 to B-017 | Wolf Lake | 0 | 44068 |  | 37 | 44070 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting428920200818-5Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting428920200818-5Light Truck - Pick up- After Jan 103731.25Inv#049 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 731.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4289 | 20200818-5 | 53520102 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2020-08-18 | 1 | Inv#049 | 44088 | 105 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Day shift grinder from B-006 to B-008 - Harley on fire watchNight shift grinder from B-008 to B-010 - Jesse on fire watch | 1 | A-128 to B-017 | Wolf Lake | 0 | 44068 |  | 37 | 44070 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting428920200818-5Foreman121140 | Corbiere and Sons Contracting428920200818-5Foreman121140Inv#049 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4289 | 20200818-5 | 53520102 | Clearing | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2020-08-18 | 1 | Inv#049 | 44088 | 105 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Day shift grinder from B-006 to B-008 - Harley on fire watchNight shift grinder from B-008 to B-010 - Jesse on fire watch | 1 | A-128 to B-017 | Wolf Lake | 0 | 44068 |  | 37 | 44070 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting428920200818-5L.O.A.51050 | Corbiere and Sons Contracting428920200818-5L.O.A.51050Inv#049 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4289 | 20200818-5 | 53520102 | Clearing | 0 | Operator - Principle - After Jan 10 | 75 | 26 | HR |  |  | 75 | 0 | 1950 | 253.5 | 2203.5 | 2020-08-18 | 1 | Inv#049 | 44088 | 105 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Day shift grinder from B-006 to B-008 - Harley on fire watchNight shift grinder from B-008 to B-010 - Jesse on fire watch | 1 | A-128 to B-017 | Wolf Lake | 0 | 44068 |  | 37 | 44070 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting428920200818-5Operator - Principle - After Jan 10261950 | Corbiere and Sons Contracting428920200818-5Operator - Principle - After Jan 10261950Inv#049 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1950 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4289 | 20200818-5 | 53520102 | Clearing | 0 | Labourer - General - After Jan 10 | 60 | 26 | HR |  |  | 60 | 0 | 1560 | 202.8 | 1762.8 | 2020-08-18 | 1 | Inv#049 | 44088 | 105 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Day shift grinder from B-006 to B-008 - Harley on fire watchNight shift grinder from B-008 to B-010 - Jesse on fire watch | 1 | A-128 to B-017 | Wolf Lake | 0 | 44068 |  | 37 | 44070 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting428920200818-5Labourer - General - After Jan 10261560 | Corbiere and Sons Contracting428920200818-5Labourer - General - After Jan 10261560Inv#049 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1560 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4295 | 20200819-3 | 53520102 | Clearing | 0 | Brusher | 202.5 | 8 | HR | 151.88 | 0 |  |  | 1620 | 210.6 | 1830.6 | 2020-08-19 | 1 | Inv#047 | 44074 | 104 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher from A-065 - Eric on FirewatchWilliam completed orientation and ran DZ spreading chip piles from A-070 to A-065. | 1 | A-055 to A-084 | Eldorado | 0 | 44068 |  | 37 | 44070 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting429520200819-3Brusher81620 | Corbiere and Sons Contracting429520200819-3Brusher81620Inv#047 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1620 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4295 | 20200819-3 | 53520102 | Clearing | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 3.5 | Dynamic | 98.61 | 0 |  |  | 460.18 | 59.8234 | 520.0034 | 2020-08-19 | 1 | Inv#047 | 44074 | 104 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher from A-065 - Eric on FirewatchWilliam completed orientation and ran DZ spreading chip piles from A-070 to A-065. | 1 | A-055 to A-084 | Eldorado | 0 | 44068 |  | 37 | 44070 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting429520200819-3Dozer D6 or equal- After Jan 103.5460.18 | Corbiere and Sons Contracting429520200819-3Dozer D6 or equal- After Jan 103.5460.18Inv#047 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 460.18 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4295 | 20200819-3 | 53520102 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-08-19 | 1 | Inv#047 | 44074 | 104 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher from A-065 - Eric on FirewatchWilliam completed orientation and ran DZ spreading chip piles from A-070 to A-065. | 1 | A-055 to A-084 | Eldorado | 0 | 44068 |  | 37 | 44070 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting429520200819-3Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting429520200819-3Light Truck - Pick up- After Jan 102487.5Inv#047 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4295 | 20200819-3 | 53520102 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-08-19 | 1 | Inv#047 | 44074 | 104 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher from A-065 - Eric on FirewatchWilliam completed orientation and ran DZ spreading chip piles from A-070 to A-065. | 1 | A-055 to A-084 | Eldorado | 0 | 44068 |  | 37 | 44070 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting429520200819-3L.O.A.2420 | Corbiere and Sons Contracting429520200819-3L.O.A.2420Inv#047 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4295 | 20200819-3 | 53520102 | Clearing | 0 | Operator - Principle - After Jan 10 | 75 | 20 | HR |  |  | 75 | 0 | 1500 | 195 | 1695 | 2020-08-19 | 1 | Inv#047 | 44074 | 104 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher from A-065 - Eric on FirewatchWilliam completed orientation and ran DZ spreading chip piles from A-070 to A-065. | 1 | A-055 to A-084 | Eldorado | 0 | 44068 |  | 37 | 44070 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting429520200819-3Operator - Principle - After Jan 10201500 | Corbiere and Sons Contracting429520200819-3Operator - Principle - After Jan 10201500Inv#047 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1500 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4295 | 20200819-3 | 53520102 | Clearing | 0 | Labourer - General - After Jan 10 | 60 | 10 | HR |  |  | 60 | 0 | 600 | 78 | 678 | 2020-08-19 | 1 | Inv#047 | 44074 | 104 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher from A-065 - Eric on FirewatchWilliam completed orientation and ran DZ spreading chip piles from A-070 to A-065. | 1 | A-055 to A-084 | Eldorado | 0 | 44068 |  | 37 | 44070 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting429520200819-3Labourer - General - After Jan 1010600 | Corbiere and Sons Contracting429520200819-3Labourer - General - After Jan 1010600Inv#047 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4296 | 20200819-4 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 21.5 | HR | 417.6 | 0 |  |  | 11971.2 | 1556.256 | 13527.456 | 2020-08-19 | 1 | Inv#047 | 44074 | 104 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Day shift/Night shift Grinder B-010 - Harley and Jesse on firewatch | 1 | A-128 to B-017 | Wolf Lake | 0 | 44068 |  | 37 | 44070 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting429620200819-4Grinder - 4710 Peterson or equal21.511971.2 | Corbiere and Sons Contracting429620200819-4Grinder - 4710 Peterson or equal21.511971.2Inv#047 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 11971.2 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4296 | 20200819-4 | 53520102 | Clearing | 0 | Log Loader | 153 | 21.5 | HR | 114.75 | 0 |  |  | 3289.5 | 427.635 | 3717.135 | 2020-08-19 | 1 | Inv#047 | 44074 | 104 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Day shift/Night shift Grinder B-010 - Harley and Jesse on firewatch | 1 | A-128 to B-017 | Wolf Lake | 0 | 44068 |  | 37 | 44070 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting429620200819-4Log Loader21.53289.5 | Corbiere and Sons Contracting429620200819-4Log Loader21.53289.5Inv#047 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 3289.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4296 | 20200819-4 | 53520102 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 4 | DAY | 182.81 | 0 |  |  | 975 | 126.75 | 1101.75 | 2020-08-19 | 1 | Inv#047 | 44074 | 104 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Day shift/Night shift Grinder B-010 - Harley and Jesse on firewatch | 1 | A-128 to B-017 | Wolf Lake | 0 | 44068 |  | 37 | 44070 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting429620200819-4Light Truck - Pick up- After Jan 104975 | Corbiere and Sons Contracting429620200819-4Light Truck - Pick up- After Jan 104975Inv#047 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 975 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4296 | 20200819-4 | 53520102 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2020-08-19 | 1 | Inv#047 | 44074 | 104 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Day shift/Night shift Grinder B-010 - Harley and Jesse on firewatch | 1 | A-128 to B-017 | Wolf Lake | 0 | 44068 |  | 37 | 44070 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting429620200819-4Foreman121140 | Corbiere and Sons Contracting429620200819-4Foreman121140Inv#047 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4296 | 20200819-4 | 53520102 | Clearing | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2020-08-19 | 1 | Inv#047 | 44074 | 104 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Day shift/Night shift Grinder B-010 - Harley and Jesse on firewatch | 1 | A-128 to B-017 | Wolf Lake | 0 | 44068 |  | 37 | 44070 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting429620200819-4L.O.A.51050 | Corbiere and Sons Contracting429620200819-4L.O.A.51050Inv#047 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4296 | 20200819-4 | 53520102 | Clearing | 0 | Operator - Principle - After Jan 10 | 75 | 24.5 | HR |  |  | 75 | 0 | 1837.5 | 238.875 | 2076.375 | 2020-08-19 | 1 | Inv#047 | 44074 | 104 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Day shift/Night shift Grinder B-010 - Harley and Jesse on firewatch | 1 | A-128 to B-017 | Wolf Lake | 0 | 44068 |  | 37 | 44070 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting429620200819-4Operator - Principle - After Jan 1024.51837.5 | Corbiere and Sons Contracting429620200819-4Operator - Principle - After Jan 1024.51837.5Inv#047 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1837.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4296 | 20200819-4 | 53520102 | Clearing | 0 | Labourer - General - After Jan 10 | 60 | 19 | HR |  |  | 60 | 0 | 1140 | 148.2 | 1288.2 | 2020-08-19 | 1 | Inv#047 | 44074 | 104 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Day shift/Night shift Grinder B-010 - Harley and Jesse on firewatch | 1 | A-128 to B-017 | Wolf Lake | 0 | 44068 |  | 37 | 44070 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting429620200819-4Labourer - General - After Jan 10191140 | Corbiere and Sons Contracting429620200819-4Labourer - General - After Jan 10191140Inv#047 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4306 | 20200820-4 | 53520102 | Clearing | 0 | Brusher | 202.5 | 7.5 | HR | 151.88 | 0 |  |  | 1518.75 | 197.4375 | 1716.1875 | 2020-08-20 | 1 | Inv#047 | 44074 | 104 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher from A-067 - Eric on fire watchDZ spreading ships from A-065 to A-071 | 1 | A-055 to A-084 | Eldorado | 0 | 44069 |  | 37 | 44070 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting430620200820-4Brusher7.51518.75 | Corbiere and Sons Contracting430620200820-4Brusher7.51518.75Inv#047 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1518.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4306 | 20200820-4 | 53520102 | Clearing | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 7.5 | Dynamic | 98.61 | 0 |  |  | 986.1 | 128.193 | 1114.293 | 2020-08-20 | 1 | Inv#047 | 44074 | 104 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher from A-067 - Eric on fire watchDZ spreading ships from A-065 to A-071 | 1 | A-055 to A-084 | Eldorado | 0 | 44069 |  | 37 | 44070 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting430620200820-4Dozer D6 or equal- After Jan 107.5986.1 | Corbiere and Sons Contracting430620200820-4Dozer D6 or equal- After Jan 107.5986.1Inv#047 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 986.1 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4306 | 20200820-4 | 53520102 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-08-20 | 1 | Inv#047 | 44074 | 104 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher from A-067 - Eric on fire watchDZ spreading ships from A-065 to A-071 | 1 | A-055 to A-084 | Eldorado | 0 | 44069 |  | 37 | 44070 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting430620200820-4Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting430620200820-4Light Truck - Pick up- After Jan 102487.5Inv#047 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4306 | 20200820-4 | 53520102 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-08-20 | 1 | Inv#047 | 44074 | 104 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher from A-067 - Eric on fire watchDZ spreading ships from A-065 to A-071 | 1 | A-055 to A-084 | Eldorado | 0 | 44069 |  | 37 | 44070 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting430620200820-4L.O.A.2420 | Corbiere and Sons Contracting430620200820-4L.O.A.2420Inv#047 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4306 | 20200820-4 | 53520102 | Clearing | 0 | Operator - Principle - After Jan 10 | 75 | 19 | HR |  |  | 75 | 0 | 1425 | 185.25 | 1610.25 | 2020-08-20 | 1 | Inv#047 | 44074 | 104 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher from A-067 - Eric on fire watchDZ spreading ships from A-065 to A-071 | 1 | A-055 to A-084 | Eldorado | 0 | 44069 |  | 37 | 44070 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting430620200820-4Operator - Principle - After Jan 10191425 | Corbiere and Sons Contracting430620200820-4Operator - Principle - After Jan 10191425Inv#047 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1425 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4306 | 20200820-4 | 53520102 | Clearing | 0 | Labourer - General - After Jan 10 | 60 | 9.5 | HR |  |  | 60 | 0 | 570 | 74.1 | 644.1 | 2020-08-20 | 1 | Inv#047 | 44074 | 104 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher from A-067 - Eric on fire watchDZ spreading ships from A-065 to A-071 | 1 | A-055 to A-084 | Eldorado | 0 | 44069 |  | 37 | 44070 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting430620200820-4Labourer - General - After Jan 109.5570 | Corbiere and Sons Contracting430620200820-4Labourer - General - After Jan 109.5570Inv#047 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 570 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4307 | 20200820-5 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 17 | HR | 417.6 | 0 |  |  | 9465.6 | 1230.528 | 10696.128 | 2020-08-20 | 1 | Inv#047 | 44074 | 104 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Day shift grinding at B-011 - Harley on fire watchNight shift grinding at B-011 to B-012 - Jesse on fire watch | 1 | A-128 to B-017 | Wolf Lake | 0 | 44069 |  | 37 | 44070 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting430720200820-5Grinder - 4710 Peterson or equal179465.6 | Corbiere and Sons Contracting430720200820-5Grinder - 4710 Peterson or equal179465.6Inv#047 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 9465.6 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4307 | 20200820-5 | 53520102 | Clearing | 0 | Log Loader | 153 | 17 | HR | 114.75 | 0 |  |  | 2601 | 338.13 | 2939.13 | 2020-08-20 | 1 | Inv#047 | 44074 | 104 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Day shift grinding at B-011 - Harley on fire watchNight shift grinding at B-011 to B-012 - Jesse on fire watch | 1 | A-128 to B-017 | Wolf Lake | 0 | 44069 |  | 37 | 44070 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting430720200820-5Log Loader172601 | Corbiere and Sons Contracting430720200820-5Log Loader172601Inv#047 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2601 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4307 | 20200820-5 | 53520102 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2020-08-20 | 1 | Inv#047 | 44074 | 104 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Day shift grinding at B-011 - Harley on fire watchNight shift grinding at B-011 to B-012 - Jesse on fire watch | 1 | A-128 to B-017 | Wolf Lake | 0 | 44069 |  | 37 | 44070 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting430720200820-5Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting430720200820-5Light Truck - Pick up- After Jan 103731.25Inv#047 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 731.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4307 | 20200820-5 | 53520102 | Clearing | 0 | Foreman | 95 | 8 | HR |  |  | 95 | 0 | 760 | 98.8 | 858.8 | 2020-08-20 | 1 | Inv#047 | 44074 | 104 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Day shift grinding at B-011 - Harley on fire watchNight shift grinding at B-011 to B-012 - Jesse on fire watch | 1 | A-128 to B-017 | Wolf Lake | 0 | 44069 |  | 37 | 44070 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting430720200820-5Foreman8760 | Corbiere and Sons Contracting430720200820-5Foreman8760Inv#047 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 760 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4307 | 20200820-5 | 53520102 | Clearing | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2020-08-20 | 1 | Inv#047 | 44074 | 104 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Day shift grinding at B-011 - Harley on fire watchNight shift grinding at B-011 to B-012 - Jesse on fire watch | 1 | A-128 to B-017 | Wolf Lake | 0 | 44069 |  | 37 | 44070 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting430720200820-5L.O.A.51050 | Corbiere and Sons Contracting430720200820-5L.O.A.51050Inv#047 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4307 | 20200820-5 | 53520102 | Clearing | 0 | Operator - Principle - After Jan 10 | 75 | 19.5 | HR |  |  | 75 | 0 | 1462.5 | 190.125 | 1652.625 | 2020-08-20 | 1 | Inv#047 | 44074 | 104 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Day shift grinding at B-011 - Harley on fire watchNight shift grinding at B-011 to B-012 - Jesse on fire watch | 1 | A-128 to B-017 | Wolf Lake | 0 | 44069 |  | 37 | 44070 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting430720200820-5Operator - Principle - After Jan 1019.51462.5 | Corbiere and Sons Contracting430720200820-5Operator - Principle - After Jan 1019.51462.5Inv#047 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1462.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4307 | 20200820-5 | 53520102 | Clearing | 0 | Labourer - General - After Jan 10 | 60 | 18 | HR |  |  | 60 | 0 | 1080 | 140.4 | 1220.4 | 2020-08-20 | 1 | Inv#047 | 44074 | 104 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Day shift grinding at B-011 - Harley on fire watchNight shift grinding at B-011 to B-012 - Jesse on fire watch | 1 | A-128 to B-017 | Wolf Lake | 0 | 44069 |  | 37 | 44070 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting430720200820-5Labourer - General - After Jan 10181080 | Corbiere and Sons Contracting430720200820-5Labourer - General - After Jan 10181080Inv#047 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1080 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4680 | 20200820-9 | 53520102 | Clearing | 0 | L.O.A. | 210 | -6 | DAY |  |  |  | 0 | -1260 | -163.8 | -1423.8 | 2020-08-20 | 1 | Inv#052 | 44092 | 106 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Credit for LOA billed on the following tickets:20200727-4 - July 27, 202020200728-3 - July 28, 202020200729-4 - July 29, 202020200730-3 - July 30, 202020200731-4 - July 31, 202020200801-4 - August 01, 2020 | 1 | A055-A084 | Eldorado | 0 | 44082 |  | 38 | 44092 | [5 empty] | Glenda Pevie | 01 | Corbiere and Sons Contracting468020200820-9L.O.A.-6-1260 | Corbiere and Sons Contracting468020200820-9L.O.A.-6-1260Inv#052 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | -1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4314 | 20200821-4 | 53520102 | Clearing | 0 | Brusher | 202.5 | 9.5 | HR | 151.88 | 0 |  |  | 1923.75 | 250.0875 | 2173.8375 | 2020-08-21 | 1 | Inv#047 | 44074 | 104 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher finishing up at A-071 - Ben on fire watch | 1 | A-055 to A-084 | Eldorado | 0 | 44069 |  | 37 | 44070 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting431420200821-4Brusher9.51923.75 | Corbiere and Sons Contracting431420200821-4Brusher9.51923.75Inv#047 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1923.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4314 | 20200821-4 | 53520102 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-08-21 | 1 | Inv#047 | 44074 | 104 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher finishing up at A-071 - Ben on fire watch | 1 | A-055 to A-084 | Eldorado | 0 | 44069 |  | 37 | 44070 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting431420200821-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting431420200821-4Light Truck - Pick up- After Jan 101243.75Inv#047 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4314 | 20200821-4 | 53520102 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-08-21 | 1 | Inv#047 | 44074 | 104 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher finishing up at A-071 - Ben on fire watch | 1 | A-055 to A-084 | Eldorado | 0 | 44069 |  | 37 | 44070 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting431420200821-4L.O.A.2420 | Corbiere and Sons Contracting431420200821-4L.O.A.2420Inv#047 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4314 | 20200821-4 | 53520102 | Clearing | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-08-21 | 1 | Inv#047 | 44074 | 104 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher finishing up at A-071 - Ben on fire watch | 1 | A-055 to A-084 | Eldorado | 0 | 44069 |  | 37 | 44070 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting431420200821-4Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting431420200821-4Operator - Principle - After Jan 1011.5862.5Inv#047 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4314 | 20200821-4 | 53520102 | Clearing | 0 | Labourer - General - After Jan 10 | 60 | 11.5 | HR |  |  | 60 | 0 | 690 | 89.7 | 779.7 | 2020-08-21 | 1 | Inv#047 | 44074 | 104 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brusher finishing up at A-071 - Ben on fire watch | 1 | A-055 to A-084 | Eldorado | 0 | 44069 |  | 37 | 44070 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting431420200821-4Labourer - General - After Jan 1011.5690 | Corbiere and Sons Contracting431420200821-4Labourer - General - After Jan 1011.5690Inv#047 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 690 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4315 | 20200821-5 | 53510112 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 95.24 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2020-08-21 | 1 | Inv#047 | 44074 | 104 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working grader across Eldorado | 1 | A-055 to A-084 | Eldorado | 0 | 44069 |  | 37 | 44070 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting431520200821-5Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting431520200821-5Grader - Cat 12 to 14 or equal- After Jan 10101269.8Inv#047 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4315 | 20200821-5 | 53510112 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-08-21 | 1 | Inv#047 | 44074 | 104 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working grader across Eldorado | 1 | A-055 to A-084 | Eldorado | 0 | 44069 |  | 37 | 44070 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting431520200821-5L.O.A.1210 | Corbiere and Sons Contracting431520200821-5L.O.A.1210Inv#047 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4315 | 20200821-5 | 53510112 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-08-21 | 1 | Inv#047 | 44074 | 104 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working grader across Eldorado | 1 | A-055 to A-084 | Eldorado | 0 | 44069 |  | 37 | 44070 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting431520200821-5Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting431520200821-5Operator - Principle - After Jan 1011.5862.5Inv#047 | [5 empty] | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4316 | 20200821-6 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 23 | HR | 417.6 | 0 |  |  | 12806.4 | 1664.832 | 14471.232 | 2020-08-21 | 1 | Inv#047 | 44074 | 104 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | DZ spreading chips from B-002 to B-004.5Day shift grinder from B-011 to B-012 - Harley on fire watchNight shift grinder from B-012 - Jesse on fire watch | 1 | A-128 to B-017 | Wolf Lake | 0 | 44069 |  | 37 | 44070 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting431620200821-6Grinder - 4710 Peterson or equal2312806.4 | Corbiere and Sons Contracting431620200821-6Grinder - 4710 Peterson or equal2312806.4Inv#047 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 12806.4 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4316 | 20200821-6 | 53520102 | Clearing | 0 | Log Loader | 153 | 23 | HR | 114.75 | 0 |  |  | 3519 | 457.47 | 3976.47 | 2020-08-21 | 1 | Inv#047 | 44074 | 104 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | DZ spreading chips from B-002 to B-004.5Day shift grinder from B-011 to B-012 - Harley on fire watchNight shift grinder from B-012 - Jesse on fire watch | 1 | A-128 to B-017 | Wolf Lake | 0 | 44069 |  | 37 | 44070 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting431620200821-6Log Loader233519 | Corbiere and Sons Contracting431620200821-6Log Loader233519Inv#047 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 3519 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4316 | 20200821-6 | 53520102 | Clearing | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10 | Dynamic | 98.61 | 0 |  |  | 1314.8 | 170.924 | 1485.724 | 2020-08-21 | 1 | Inv#047 | 44074 | 104 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | DZ spreading chips from B-002 to B-004.5Day shift grinder from B-011 to B-012 - Harley on fire watchNight shift grinder from B-012 - Jesse on fire watch | 1 | A-128 to B-017 | Wolf Lake | 0 | 44069 |  | 37 | 44070 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting431620200821-6Dozer D6 or equal- After Jan 10101314.8 | Corbiere and Sons Contracting431620200821-6Dozer D6 or equal- After Jan 10101314.8Inv#047 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1314.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4316 | 20200821-6 | 53520102 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 4 | DAY | 182.81 | 0 |  |  | 975 | 126.75 | 1101.75 | 2020-08-21 | 1 | Inv#047 | 44074 | 104 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | DZ spreading chips from B-002 to B-004.5Day shift grinder from B-011 to B-012 - Harley on fire watchNight shift grinder from B-012 - Jesse on fire watch | 1 | A-128 to B-017 | Wolf Lake | 0 | 44069 |  | 37 | 44070 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting431620200821-6Light Truck - Pick up- After Jan 104975 | Corbiere and Sons Contracting431620200821-6Light Truck - Pick up- After Jan 104975Inv#047 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 975 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4316 | 20200821-6 | 53520102 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  | 95 | 0 | 1140 | 148.2 | 1288.2 | 2020-08-21 | 1 | Inv#047 | 44074 | 104 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | DZ spreading chips from B-002 to B-004.5Day shift grinder from B-011 to B-012 - Harley on fire watchNight shift grinder from B-012 - Jesse on fire watch | 1 | A-128 to B-017 | Wolf Lake | 0 | 44069 |  | 37 | 44070 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting431620200821-6Foreman121140 | Corbiere and Sons Contracting431620200821-6Foreman121140Inv#047 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4316 | 20200821-6 | 53520102 | Clearing | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2020-08-21 | 1 | Inv#047 | 44074 | 104 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | DZ spreading chips from B-002 to B-004.5Day shift grinder from B-011 to B-012 - Harley on fire watchNight shift grinder from B-012 - Jesse on fire watch | 1 | A-128 to B-017 | Wolf Lake | 0 | 44069 |  | 37 | 44070 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting431620200821-6L.O.A.61260 | Corbiere and Sons Contracting431620200821-6L.O.A.61260Inv#047 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4316 | 20200821-6 | 53520102 | Clearing | 0 | Operator - Principle - After Jan 10 | 75 | 37.5 | HR |  |  | 75 | 0 | 2812.5 | 365.625 | 3178.125 | 2020-08-21 | 1 | Inv#047 | 44074 | 104 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | DZ spreading chips from B-002 to B-004.5Day shift grinder from B-011 to B-012 - Harley on fire watchNight shift grinder from B-012 - Jesse on fire watch | 1 | A-128 to B-017 | Wolf Lake | 0 | 44069 |  | 37 | 44070 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting431620200821-6Operator - Principle - After Jan 1037.52812.5 | Corbiere and Sons Contracting431620200821-6Operator - Principle - After Jan 1037.52812.5Inv#047 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2812.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4316 | 20200821-6 | 53520102 | Clearing | 0 | Labourer - General - After Jan 10 | 60 | 26 | HR |  |  | 60 | 0 | 1560 | 202.8 | 1762.8 | 2020-08-21 | 1 | Inv#047 | 44074 | 104 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | DZ spreading chips from B-002 to B-004.5Day shift grinder from B-011 to B-012 - Harley on fire watchNight shift grinder from B-012 - Jesse on fire watch | 1 | A-128 to B-017 | Wolf Lake | 0 | 44069 |  | 37 | 44070 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting431620200821-6Labourer - General - After Jan 10261560 | Corbiere and Sons Contracting431620200821-6Labourer - General - After Jan 10261560Inv#047 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1560 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4321 | 20200822-4 | 53520102 | Clearing | 0 | Brusher | 202.5 | 2 | HR | 151.88 | 0 |  |  | 405 | 52.65 | 457.65 | 2020-08-22 | 1 | Inv#047 | 44074 | 104 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Finished brusher and walked out until 9:30am - Ben on fire watch | 1 | A-055 to A-084 | Eldorado | 0 | 44069 |  | 37 | 44073 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting432120200822-4Brusher2405 | Corbiere and Sons Contracting432120200822-4Brusher2405Inv#047 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 405 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4321 | 20200822-4 | 53520102 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-08-22 | 1 | Inv#047 | 44074 | 104 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Finished brusher and walked out until 9:30am - Ben on fire watch | 1 | A-055 to A-084 | Eldorado | 0 | 44069 |  | 37 | 44073 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting432120200822-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting432120200822-4Light Truck - Pick up- After Jan 101243.75Inv#047 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4321 | 20200822-4 | 53520102 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-08-22 | 1 | Inv#047 | 44074 | 104 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Finished brusher and walked out until 9:30am - Ben on fire watch | 1 | A-055 to A-084 | Eldorado | 0 | 44069 |  | 37 | 44073 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting432120200822-4L.O.A.2420 | Corbiere and Sons Contracting432120200822-4L.O.A.2420Inv#047 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4321 | 20200822-4 | 53520102 | Clearing | 0 | Operator - Principle - After Jan 10 | 75 | 2.5 | HR |  |  | 75 | 0 | 187.5 | 24.375 | 211.875 | 2020-08-22 | 1 | Inv#047 | 44074 | 104 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Finished brusher and walked out until 9:30am - Ben on fire watch | 1 | A-055 to A-084 | Eldorado | 0 | 44069 |  | 37 | 44073 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting432120200822-4Operator - Principle - After Jan 102.5187.5 | Corbiere and Sons Contracting432120200822-4Operator - Principle - After Jan 102.5187.5Inv#047 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 187.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4321 | 20200822-4 | 53520102 | Clearing | 0 | Labourer - General - After Jan 10 | 60 | 2.5 | HR |  |  | 60 | 0 | 150 | 19.5 | 169.5 | 2020-08-22 | 1 | Inv#047 | 44074 | 104 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Finished brusher and walked out until 9:30am - Ben on fire watch | 1 | A-055 to A-084 | Eldorado | 0 | 44069 |  | 37 | 44073 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting432120200822-4Labourer - General - After Jan 102.5150 | Corbiere and Sons Contracting432120200822-4Labourer - General - After Jan 102.5150Inv#047 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 150 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4323 | 20200822-6 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 4.5 | HR | 417.6 | 0 |  |  | 2505.6 | 325.728 | 2831.328 | 2020-08-22 | 1 | Inv#047 | 44074 | 104 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | DZ spreading chips from B004.5 to B009.Grinder in WF1 until 1pm - then moved into WF2 - Harley on fire watch | 1 | A-128 to B-017 | Wolf Lake | 0 | 44069 |  | 37 | 44073 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting432320200822-6Grinder - 4710 Peterson or equal4.52505.6 | Corbiere and Sons Contracting432320200822-6Grinder - 4710 Peterson or equal4.52505.6Inv#047 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2505.6 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4323 | 20200822-6 | 53520102 | Clearing | 0 | Log Loader | 153 | 4.5 | HR | 114.75 | 0 |  |  | 688.5 | 89.505 | 778.005 | 2020-08-22 | 1 | Inv#047 | 44074 | 104 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | DZ spreading chips from B004.5 to B009.Grinder in WF1 until 1pm - then moved into WF2 - Harley on fire watch | 1 | A-128 to B-017 | Wolf Lake | 0 | 44069 |  | 37 | 44073 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting432320200822-6Log Loader4.5688.5 | Corbiere and Sons Contracting432320200822-6Log Loader4.5688.5Inv#047 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 688.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4323 | 20200822-6 | 53520102 | Clearing | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 9.5 | Dynamic | 98.61 | 0 |  |  | 1249.06 | 162.3778 | 1411.4378 | 2020-08-22 | 1 | Inv#047 | 44074 | 104 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | DZ spreading chips from B004.5 to B009.Grinder in WF1 until 1pm - then moved into WF2 - Harley on fire watch | 1 | A-128 to B-017 | Wolf Lake | 0 | 44069 |  | 37 | 44073 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting432320200822-6Dozer D6 or equal- After Jan 109.51249.06 | Corbiere and Sons Contracting432320200822-6Dozer D6 or equal- After Jan 109.51249.06Inv#047 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1249.06 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4323 | 20200822-6 | 53520102 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2020-08-22 | 1 | Inv#047 | 44074 | 104 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | DZ spreading chips from B004.5 to B009.Grinder in WF1 until 1pm - then moved into WF2 - Harley on fire watch | 1 | A-128 to B-017 | Wolf Lake | 0 | 44069 |  | 37 | 44073 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting432320200822-6Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting432320200822-6Light Truck - Pick up- After Jan 103731.25Inv#047 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 731.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4323 | 20200822-6 | 53520102 | Clearing | 0 | Foreman | 95 | 4 | HR |  |  | 95 | 0 | 380 | 49.4 | 429.4 | 2020-08-22 | 1 | Inv#047 | 44074 | 104 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | DZ spreading chips from B004.5 to B009.Grinder in WF1 until 1pm - then moved into WF2 - Harley on fire watch | 1 | A-128 to B-017 | Wolf Lake | 0 | 44069 |  | 37 | 44073 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting432320200822-6Foreman4380 | Corbiere and Sons Contracting432320200822-6Foreman4380Inv#047 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4323 | 20200822-6 | 53520102 | Clearing | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2020-08-22 | 1 | Inv#047 | 44074 | 104 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | DZ spreading chips from B004.5 to B009.Grinder in WF1 until 1pm - then moved into WF2 - Harley on fire watch | 1 | A-128 to B-017 | Wolf Lake | 0 | 44069 |  | 37 | 44073 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting432320200822-6L.O.A.4840 | Corbiere and Sons Contracting432320200822-6L.O.A.4840Inv#047 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4323 | 20200822-6 | 53520102 | Clearing | 0 | Operator - Principle - After Jan 10 | 75 | 18 | HR |  |  | 75 | 0 | 1350 | 175.5 | 1525.5 | 2020-08-22 | 1 | Inv#047 | 44074 | 104 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | DZ spreading chips from B004.5 to B009.Grinder in WF1 until 1pm - then moved into WF2 - Harley on fire watch | 1 | A-128 to B-017 | Wolf Lake | 0 | 44069 |  | 37 | 44073 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting432320200822-6Operator - Principle - After Jan 10181350 | Corbiere and Sons Contracting432320200822-6Operator - Principle - After Jan 10181350Inv#047 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1350 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4323 | 20200822-6 | 53520102 | Clearing | 0 | Labourer - General - After Jan 10 | 60 | 6.5 | HR |  |  | 60 | 0 | 390 | 50.7 | 440.7 | 2020-08-22 | 1 | Inv#047 | 44074 | 104 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | DZ spreading chips from B004.5 to B009.Grinder in WF1 until 1pm - then moved into WF2 - Harley on fire watch | 1 | A-128 to B-017 | Wolf Lake | 0 | 44069 |  | 37 | 44073 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting432320200822-6Labourer - General - After Jan 106.5390 | Corbiere and Sons Contracting432320200822-6Labourer - General - After Jan 106.5390Inv#047 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 390 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4324 | 20200822-7 | 53510112 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 95.24 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2020-08-22 | 1 | Inv#047 | 44074 | 104 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader across Beck Road Access | 1 | A-036 to A-054 | Beck Road | 0 | 44069 |  | 37 | 44073 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting432420200822-7Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting432420200822-7Grader - Cat 12 to 14 or equal- After Jan 10101269.8Inv#047 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4324 | 20200822-7 | 53510112 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-08-22 | 1 | Inv#047 | 44074 | 104 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader across Beck Road Access | 1 | A-036 to A-054 | Beck Road | 0 | 44069 |  | 37 | 44073 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting432420200822-7Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting432420200822-7Light Truck - Pick up- After Jan 101243.75Inv#047 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4324 | 20200822-7 | 53510112 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-08-22 | 1 | Inv#047 | 44074 | 104 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader across Beck Road Access | 1 | A-036 to A-054 | Beck Road | 0 | 44069 |  | 37 | 44073 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting432420200822-7L.O.A.1210 | Corbiere and Sons Contracting432420200822-7L.O.A.1210Inv#047 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4324 | 20200822-7 | 53510112 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-08-22 | 1 | Inv#047 | 44074 | 104 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader across Beck Road Access | 1 | A-036 to A-054 | Beck Road | 0 | 44069 |  | 37 | 44073 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting432420200822-7Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting432420200822-7Operator - Principle - After Jan 1011.5862.5Inv#047 | [5 empty] | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4332 | 20200824-3 | 53510112 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 9.5 | Dynamic | 95.24 | 0 |  |  | 1206.31 | 156.8203 | 1363.1303 | 2020-08-24 | 1 | Inv#049 | 44088 | 105 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working on Beck Road | 1 | A-036 to A-054 | Beck Road | 0 | 44074 |  | 37 | 44075 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting433220200824-3Grader - Cat 12 to 14 or equal- After Jan 109.51206.31 | Corbiere and Sons Contracting433220200824-3Grader - Cat 12 to 14 or equal- After Jan 109.51206.31Inv#049 | [5 empty] | 1 | 1206.31 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4332 | 20200824-3 | 53510112 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-08-24 | 1 | Inv#049 | 44088 | 105 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working on Beck Road | 1 | A-036 to A-054 | Beck Road | 0 | 44074 |  | 37 | 44075 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting433220200824-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting433220200824-3Light Truck - Pick up- After Jan 101243.75Inv#049 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4332 | 20200824-3 | 53510112 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-08-24 | 1 | Inv#049 | 44088 | 105 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working on Beck Road | 1 | A-036 to A-054 | Beck Road | 0 | 44074 |  | 37 | 44075 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting433220200824-3L.O.A.1210 | Corbiere and Sons Contracting433220200824-3L.O.A.1210Inv#049 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4332 | 20200824-3 | 53510112 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-08-24 | 1 | Inv#049 | 44088 | 105 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working on Beck Road | 1 | A-036 to A-054 | Beck Road | 0 | 44074 |  | 37 | 44075 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting433220200824-3Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting433220200824-3Operator - Principle - After Jan 1011.5862.5Inv#049 | [5 empty] | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4333 | 20200824-4 | 53520102 | Clearing | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 8 | Dynamic | 98.61 | 0 |  |  | 1051.84 | 136.7392 | 1188.5792 | 2020-08-24 | 1 | Inv#049 | 44088 | 105 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Will spreading chip piles from B-012. | 1 | A-128 to B-017 | Wolf Lake | 0 | 44074 |  | 37 | 44075 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting433320200824-4Dozer D6 or equal- After Jan 1081051.84 | Corbiere and Sons Contracting433320200824-4Dozer D6 or equal- After Jan 1081051.84Inv#049 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1051.84 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4333 | 20200824-4 | 53520102 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-08-24 | 1 | Inv#049 | 44088 | 105 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Will spreading chip piles from B-012. | 1 | A-128 to B-017 | Wolf Lake | 0 | 44074 |  | 37 | 44075 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting433320200824-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting433320200824-4Light Truck - Pick up- After Jan 101243.75Inv#049 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4333 | 20200824-4 | 53520102 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-08-24 | 1 | Inv#049 | 44088 | 105 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Will spreading chip piles from B-012. | 1 | A-128 to B-017 | Wolf Lake | 0 | 44074 |  | 37 | 44075 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting433320200824-4L.O.A.1210 | Corbiere and Sons Contracting433320200824-4L.O.A.1210Inv#049 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4333 | 20200824-4 | 53520102 | Clearing | 0 | Operator - Principle - After Jan 10 | 75 | 9.5 | HR |  |  | 75 | 0 | 712.5 | 92.625 | 805.125 | 2020-08-24 | 1 | Inv#049 | 44088 | 105 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Will spreading chip piles from B-012. | 1 | A-128 to B-017 | Wolf Lake | 0 | 44074 |  | 37 | 44075 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting433320200824-4Operator - Principle - After Jan 109.5712.5 | Corbiere and Sons Contracting433320200824-4Operator - Principle - After Jan 109.5712.5Inv#049 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 712.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4341 | 20200825-4 | 53520102 | Clearing | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 9.5 | Dynamic | 98.61 | 0 |  |  | 1249.06 | 162.3778 | 1411.4378 | 2020-08-25 | 1 | Inv#049 | 44088 | 105 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | DZ pushing piles from B-009 to B-012 | 1 | A-128 to B-017 | Wolf Lake | 0 | 44074 |  | 37 | 44075 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting434120200825-4Dozer D6 or equal- After Jan 109.51249.06 | Corbiere and Sons Contracting434120200825-4Dozer D6 or equal- After Jan 109.51249.06Inv#049 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1249.06 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4341 | 20200825-4 | 53520102 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-08-25 | 1 | Inv#049 | 44088 | 105 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | DZ pushing piles from B-009 to B-012 | 1 | A-128 to B-017 | Wolf Lake | 0 | 44074 |  | 37 | 44075 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting434120200825-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting434120200825-4Light Truck - Pick up- After Jan 101243.75Inv#049 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4341 | 20200825-4 | 53520102 | Clearing | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-08-25 | 1 | Inv#049 | 44088 | 105 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | DZ pushing piles from B-009 to B-012 | 1 | A-128 to B-017 | Wolf Lake | 0 | 44074 |  | 37 | 44075 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting434120200825-4L.O.A.1210 | Corbiere and Sons Contracting434120200825-4L.O.A.1210Inv#049 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4341 | 20200825-4 | 53520102 | Clearing | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-08-25 | 1 | Inv#049 | 44088 | 105 | 0 | 0 | Glenda Pevie | Non-merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | DZ pushing piles from B-009 to B-012 | 1 | A-128 to B-017 | Wolf Lake | 0 | 44074 |  | 37 | 44075 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting434120200825-4Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting434120200825-4Operator - Principle - After Jan 1011.5862.5Inv#049 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4342 | 20200825-5 | 53510112 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 7.5 | Dynamic | 95.24 | 0 |  |  | 952.35 | 123.8055 | 1076.1555 | 2020-08-25 | 1 | Inv#049 | 44088 | 105 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader at Beck Road - got to site at 8:30am | 1 | A-036 to A-054 | Beck Road | 0 | 44074 |  | 37 | 44075 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting434220200825-5Grader - Cat 12 to 14 or equal- After Jan 107.5952.35 | Corbiere and Sons Contracting434220200825-5Grader - Cat 12 to 14 or equal- After Jan 107.5952.35Inv#049 | [5 empty] | 1 | 952.35 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4342 | 20200825-5 | 53510112 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-08-25 | 1 | Inv#049 | 44088 | 105 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader at Beck Road - got to site at 8:30am | 1 | A-036 to A-054 | Beck Road | 0 | 44074 |  | 37 | 44075 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting434220200825-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting434220200825-5Light Truck - Pick up- After Jan 101243.75Inv#049 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4342 | 20200825-5 | 53510112 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-08-25 | 1 | Inv#049 | 44088 | 105 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader at Beck Road - got to site at 8:30am | 1 | A-036 to A-054 | Beck Road | 0 | 44074 |  | 37 | 44075 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting434220200825-5L.O.A.1210 | Corbiere and Sons Contracting434220200825-5L.O.A.1210Inv#049 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4342 | 20200825-5 | 53510112 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 8.5 | HR |  |  | 75 | 0 | 637.5 | 82.875 | 720.375 | 2020-08-25 | 1 | Inv#049 | 44088 | 105 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader at Beck Road - got to site at 8:30am | 1 | A-036 to A-054 | Beck Road | 0 | 44074 |  | 37 | 44075 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting434220200825-5Operator - Principle - After Jan 108.5637.5 | Corbiere and Sons Contracting434220200825-5Operator - Principle - After Jan 108.5637.5Inv#049 | [5 empty] | 1 | 637.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4349 | 20200826-4 | 53510312 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 9 | Dynamic | 95.24 | 0 |  |  | 1142.82 | 148.5666 | 1291.3866 | 2020-08-26 | 1 | Inv#049 | 44088 | 105 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Lachance access road | 3 | B161-B181 | Lachance Road | 0 | 44074 |  | 37 | 44075 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting434920200826-4Grader - Cat 12 to 14 or equal- After Jan 1091142.82 | Corbiere and Sons Contracting434920200826-4Grader - Cat 12 to 14 or equal- After Jan 1091142.82Inv#049 | [5 empty] | 1 | 1142.82 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4349 | 20200826-4 | 53510312 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-08-26 | 1 | Inv#049 | 44088 | 105 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Lachance access road | 3 | B161-B181 | Lachance Road | 0 | 44074 |  | 37 | 44075 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting434920200826-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting434920200826-4Light Truck - Pick up- After Jan 101243.75Inv#049 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4349 | 20200826-4 | 53510312 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-08-26 | 1 | Inv#049 | 44088 | 105 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Lachance access road | 3 | B161-B181 | Lachance Road | 0 | 44074 |  | 37 | 44075 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting434920200826-4L.O.A.1210 | Corbiere and Sons Contracting434920200826-4L.O.A.1210Inv#049 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4349 | 20200826-4 | 53510312 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-08-26 | 1 | Inv#049 | 44088 | 105 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Lachance access road | 3 | B161-B181 | Lachance Road | 0 | 44074 |  | 37 | 44075 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting434920200826-4Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting434920200826-4Operator - Principle - After Jan 1011.5862.5Inv#049 | [5 empty] | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4356 | 20200827-4 | 53510312 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 9.5 | Dynamic | 95.24 | 0 |  |  | 1206.31 | 156.8203 | 1363.1303 | 2020-08-27 | 1 | Inv#049 | 44088 | 105 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working grader across Lachance access roads | 3 |  | Lachance Road | 0 | 44074 |  | 37 | 44075 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting435620200827-4Grader - Cat 12 to 14 or equal- After Jan 109.51206.31 | Corbiere and Sons Contracting435620200827-4Grader - Cat 12 to 14 or equal- After Jan 109.51206.31Inv#049 | [5 empty] | 1 | 1206.31 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4356 | 20200827-4 | 53510312 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-08-27 | 1 | Inv#049 | 44088 | 105 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working grader across Lachance access roads | 3 |  | Lachance Road | 0 | 44074 |  | 37 | 44075 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting435620200827-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting435620200827-4Light Truck - Pick up- After Jan 101243.75Inv#049 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4356 | 20200827-4 | 53510312 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-08-27 | 1 | Inv#049 | 44088 | 105 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working grader across Lachance access roads | 3 |  | Lachance Road | 0 | 44074 |  | 37 | 44075 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting435620200827-4L.O.A.1210 | Corbiere and Sons Contracting435620200827-4L.O.A.1210Inv#049 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4356 | 20200827-4 | 53510312 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-08-27 | 1 | Inv#049 | 44088 | 105 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working grader across Lachance access roads | 3 |  | Lachance Road | 0 | 44074 |  | 37 | 44075 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting435620200827-4Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting435620200827-4Operator - Principle - After Jan 1011.5862.5Inv#049 | [5 empty] | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4427 | 20200901-4 | 53510212 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 5.5 | Dynamic | 95.24 | 0 |  |  | 698.39 | 90.7907 | 789.1807 | 2020-09-01 | 1 | Inv#049 | 44088 | 105 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader on Landfill road from 12pm-6pm. | 2 | B065-B077 | Red Rock | 0 | 44078 |  | 37 | 44087 | [5 empty] | Harold Furlong | 02 | Corbiere and Sons Contracting442720200901-4Grader - Cat 12 to 14 or equal- After Jan 105.5698.39 | Corbiere and Sons Contracting442720200901-4Grader - Cat 12 to 14 or equal- After Jan 105.5698.39Inv#049 | [5 empty] | 1 | 698.39 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4427 | 20200901-4 | 53510212 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-09-01 | 1 | Inv#049 | 44088 | 105 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader on Landfill road from 12pm-6pm. | 2 | B065-B077 | Red Rock | 0 | 44078 |  | 37 | 44087 | [5 empty] | Harold Furlong | 02 | Corbiere and Sons Contracting442720200901-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting442720200901-4Light Truck - Pick up- After Jan 101243.75Inv#049 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4427 | 20200901-4 | 53510212 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-09-01 | 1 | Inv#049 | 44088 | 105 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader on Landfill road from 12pm-6pm. | 2 | B065-B077 | Red Rock | 0 | 44078 |  | 37 | 44087 | [5 empty] | Harold Furlong | 02 | Corbiere and Sons Contracting442720200901-4L.O.A.1210 | Corbiere and Sons Contracting442720200901-4L.O.A.1210Inv#049 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4427 | 20200901-4 | 53510212 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 75 | 0 | 450 | 58.5 | 508.5 | 2020-09-01 | 1 | Inv#049 | 44088 | 105 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader on Landfill road from 12pm-6pm. | 2 | B065-B077 | Red Rock | 0 | 44078 |  | 37 | 44087 | [5 empty] | Harold Furlong | 02 | Corbiere and Sons Contracting442720200901-4Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting442720200901-4Operator - Principle - After Jan 106450Inv#049 | [5 empty] | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4447 | 20200902-4 | 53510212 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 7 | Dynamic | 95.24 | 0 |  |  | 888.86 | 115.5518 | 1004.4118 | 2020-09-02 | 1 | Inv#049 | 44088 | 105 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader on Black Sturgeon from 12pm-6pm. | 2 | B018 - B029 | Black Sturgeon | 0 | 44078 |  | 37 | 44087 | [5 empty] | Harold Furlong | 02 | Corbiere and Sons Contracting444720200902-4Grader - Cat 12 to 14 or equal- After Jan 107888.86 | Corbiere and Sons Contracting444720200902-4Grader - Cat 12 to 14 or equal- After Jan 107888.86Inv#049 | [5 empty] | 1 | 888.86 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4447 | 20200902-4 | 53510212 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-09-02 | 1 | Inv#049 | 44088 | 105 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader on Black Sturgeon from 12pm-6pm. | 2 | B018 - B029 | Black Sturgeon | 0 | 44078 |  | 37 | 44087 | [5 empty] | Harold Furlong | 02 | Corbiere and Sons Contracting444720200902-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting444720200902-4Light Truck - Pick up- After Jan 101243.75Inv#049 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4447 | 20200902-4 | 53510212 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-09-02 | 1 | Inv#049 | 44088 | 105 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader on Black Sturgeon from 12pm-6pm. | 2 | B018 - B029 | Black Sturgeon | 0 | 44078 |  | 37 | 44087 | [5 empty] | Harold Furlong | 02 | Corbiere and Sons Contracting444720200902-4L.O.A.1210 | Corbiere and Sons Contracting444720200902-4L.O.A.1210Inv#049 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4447 | 20200902-4 | 53510212 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 8 | HR |  |  | 75 | 0 | 600 | 78 | 678 | 2020-09-02 | 1 | Inv#049 | 44088 | 105 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader on Black Sturgeon from 12pm-6pm. | 2 | B018 - B029 | Black Sturgeon | 0 | 44078 |  | 37 | 44087 | [5 empty] | Harold Furlong | 02 | Corbiere and Sons Contracting444720200902-4Operator - Principle - After Jan 108600 | Corbiere and Sons Contracting444720200902-4Operator - Principle - After Jan 108600Inv#049 | [5 empty] | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4463 | 20200903-5 | 53510212 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 5 | Dynamic | 95.24 | 0 |  |  | 634.9 | 82.537 | 717.437 | 2020-09-03 | 1 | Inv#049 | 44088 | 105 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working in Black Sturgeon | 2 | B018 - B029 | Black Sturgeon | 0 | 44078 |  | 37 | 44087 | [5 empty] | Harold Furlong | 02 | Corbiere and Sons Contracting446320200903-5Grader - Cat 12 to 14 or equal- After Jan 105634.9 | Corbiere and Sons Contracting446320200903-5Grader - Cat 12 to 14 or equal- After Jan 105634.9Inv#049 | [5 empty] | 1 | 634.9 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4463 | 20200903-5 | 53510212 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-09-03 | 1 | Inv#049 | 44088 | 105 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working in Black Sturgeon | 2 | B018 - B029 | Black Sturgeon | 0 | 44078 |  | 37 | 44087 | [5 empty] | Harold Furlong | 02 | Corbiere and Sons Contracting446320200903-5L.O.A.1210 | Corbiere and Sons Contracting446320200903-5L.O.A.1210Inv#049 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4463 | 20200903-5 | 53510212 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5 | HR |  |  | 75 | 0 | 375 | 48.75 | 423.75 | 2020-09-03 | 1 | Inv#049 | 44088 | 105 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working in Black Sturgeon | 2 | B018 - B029 | Black Sturgeon | 0 | 44078 |  | 37 | 44087 | [5 empty] | Harold Furlong | 02 | Corbiere and Sons Contracting446320200903-5Operator - Principle - After Jan 105375 | Corbiere and Sons Contracting446320200903-5Operator - Principle - After Jan 105375Inv#049 | [5 empty] | 1 | 375 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4531 | 20200907-4 | 53510212 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 3 | Dynamic | 98.61 | 0 |  |  | 394.44 | 51.2772 | 445.7172 | 2020-09-07 | 1 | Inv#052 | 44092 | 106 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer doing road maintenance from B-021 to B-026. | 2 | B018 - B029 | Black Sturgeon | 0 | 44083 |  | 46 | 44092 | [5 empty] | Glen Greening | 02 | Corbiere and Sons Contracting453120200907-4Dozer D6 or equal- After Jan 103394.44 | Corbiere and Sons Contracting453120200907-4Dozer D6 or equal- After Jan 103394.44Inv#052 | [5 empty] | 1 | 394.44 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4531 | 20200907-4 | 53510212 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-09-07 | 1 | Inv#052 | 44092 | 106 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer doing road maintenance from B-021 to B-026. | 2 | B018 - B029 | Black Sturgeon | 0 | 44083 |  | 46 | 44092 | [5 empty] | Glen Greening | 02 | Corbiere and Sons Contracting453120200907-4Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting453120200907-4Light Truck - Pick up- After Jan 101243.75Inv#052 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4531 | 20200907-4 | 53510212 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-09-07 | 1 | Inv#052 | 44092 | 106 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer doing road maintenance from B-021 to B-026. | 2 | B018 - B029 | Black Sturgeon | 0 | 44083 |  | 46 | 44092 | [5 empty] | Glen Greening | 02 | Corbiere and Sons Contracting453120200907-4L.O.A.1210 | Corbiere and Sons Contracting453120200907-4L.O.A.1210Inv#052 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4531 | 20200907-4 | 53510212 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 3 | HR |  |  | 75 | 0 | 225 | 29.25 | 254.25 | 2020-09-07 | 1 | Inv#052 | 44092 | 106 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer doing road maintenance from B-021 to B-026. | 2 | B018 - B029 | Black Sturgeon | 0 | 44083 |  | 46 | 44092 | [5 empty] | Glen Greening | 02 | Corbiere and Sons Contracting453120200907-4Operator - Principle - After Jan 103225 | Corbiere and Sons Contracting453120200907-4Operator - Principle - After Jan 103225Inv#052 | [5 empty] | 1 | 225 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4559 | 20200908-19 | 53510504 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 67 | Dynamic | 41.4 | 0 |  |  | 3698.4 | 480.792 | 4179.192 | 2020-09-08 | 1 | Inv#052 | 44092 | 106 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel hauling from North Shore pit in Schreiber to Pays Platt and Antler Lake Access Roads. | 5 | C050-C069 | Antler Lake | 0 | 44086 |  | 9 | 44091 | [5 empty] | Mandy Sandhu | 05 | Corbiere and Sons Contracting455920200908-19Dump - Triaxle- After Jan 10673698.4 | Corbiere and Sons Contracting455920200908-19Dump - Triaxle- After Jan 10673698.4Inv#052 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 3698.4 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4559 | 20200908-19 | 53510504 | Access | 0 | L.O.A. | 210 | 7 | DAY |  |  |  | 0 | 1470 | 191.1 | 1661.1 | 2020-09-08 | 1 | Inv#052 | 44092 | 106 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel hauling from North Shore pit in Schreiber to Pays Platt and Antler Lake Access Roads. | 5 | C050-C069 | Antler Lake | 0 | 44086 |  | 9 | 44091 | [5 empty] | Mandy Sandhu | 05 | Corbiere and Sons Contracting455920200908-19L.O.A.71470 | Corbiere and Sons Contracting455920200908-19L.O.A.71470Inv#052 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1470 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4559 | 20200908-19 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 67 | HR |  |  | 70 | 0 | 4690 | 609.7 | 5299.7 | 2020-09-08 | 1 | Inv#052 | 44092 | 106 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel hauling from North Shore pit in Schreiber to Pays Platt and Antler Lake Access Roads. | 5 | C050-C069 | Antler Lake | 0 | 44086 |  | 9 | 44091 | [5 empty] | Mandy Sandhu | 05 | Corbiere and Sons Contracting455920200908-19Driver - AZ - After Jan 10674690 | Corbiere and Sons Contracting455920200908-19Driver - AZ - After Jan 10674690Inv#052 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 4690 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4561 | 20200908-21 | 53510504 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 8 | Dynamic | 98.61 | 0 |  |  | 1051.84 | 136.7392 | 1188.5792 | 2020-09-08 | 1 | Inv#052 | 44092 | 106 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Capping 150m of AN road with gravel, cleared slop for geo and capping | 5 | C050-C069 | Antler Lake | 0 | 44086 |  | 9 | 44091 | [5 empty] | Mandy Sandhu | 05 | Corbiere and Sons Contracting456120200908-21Dozer D6 or equal- After Jan 1081051.84 | Corbiere and Sons Contracting456120200908-21Dozer D6 or equal- After Jan 1081051.84Inv#052 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1051.84 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4561 | 20200908-21 | 53510504 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 3 | Dynamic | 103.84 | 0 |  |  | 415.35 | 53.9955 | 469.3455 | 2020-09-08 | 1 | Inv#052 | 44092 | 106 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Capping 150m of AN road with gravel, cleared slop for geo and capping | 5 | C050-C069 | Antler Lake | 0 | 44086 |  | 9 | 44091 | [5 empty] | Mandy Sandhu | 05 | Corbiere and Sons Contracting456120200908-21Excavator - 30 ton- After Jan 103415.35 | Corbiere and Sons Contracting456120200908-21Excavator - 30 ton- After Jan 103415.35Inv#052 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 415.35 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4561 | 20200908-21 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-09-08 | 1 | Inv#052 | 44092 | 106 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Capping 150m of AN road with gravel, cleared slop for geo and capping | 5 | C050-C069 | Antler Lake | 0 | 44086 |  | 9 | 44091 | [5 empty] | Mandy Sandhu | 05 | Corbiere and Sons Contracting456120200908-21Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting456120200908-21Light Truck - Pick up- After Jan 101243.75Inv#052 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4561 | 20200908-21 | 53510504 | Access | 0 | Foreman | 95 | 3 | HR |  |  | 95 | 0 | 285 | 37.05 | 322.05 | 2020-09-08 | 1 | Inv#052 | 44092 | 106 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Capping 150m of AN road with gravel, cleared slop for geo and capping | 5 | C050-C069 | Antler Lake | 0 | 44086 |  | 9 | 44091 | [5 empty] | Mandy Sandhu | 05 | Corbiere and Sons Contracting456120200908-21Foreman3285 | Corbiere and Sons Contracting456120200908-21Foreman3285Inv#052 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 285 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4561 | 20200908-21 | 53510504 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-09-08 | 1 | Inv#052 | 44092 | 106 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Capping 150m of AN road with gravel, cleared slop for geo and capping | 5 | C050-C069 | Antler Lake | 0 | 44086 |  | 9 | 44091 | [5 empty] | Mandy Sandhu | 05 | Corbiere and Sons Contracting456120200908-21L.O.A.1210 | Corbiere and Sons Contracting456120200908-21L.O.A.1210Inv#052 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4561 | 20200908-21 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2020-09-08 | 1 | Inv#052 | 44092 | 106 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Capping 150m of AN road with gravel, cleared slop for geo and capping | 5 | C050-C069 | Antler Lake | 0 | 44086 |  | 9 | 44091 | [5 empty] | Mandy Sandhu | 05 | Corbiere and Sons Contracting456120200908-21Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting456120200908-21Operator - Principle - After Jan 1011825Inv#052 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4561 | 20200908-21 | 53510504 | Access | 0 | Labourer - General - After Jan 10 | 60 | 1 | HR |  |  | 60 | 0 | 60 | 7.8 | 67.8 | 2020-09-08 | 1 | Inv#052 | 44092 | 106 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Capping 150m of AN road with gravel, cleared slop for geo and capping | 5 | C050-C069 | Antler Lake | 0 | 44086 |  | 9 | 44091 | [5 empty] | Mandy Sandhu | 05 | Corbiere and Sons Contracting456120200908-21Labourer - General - After Jan 10160 | Corbiere and Sons Contracting456120200908-21Labourer - General - After Jan 10160Inv#052 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 60 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5115 | 20200908-26 | 53510504 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 12 | Dynamic | 41.4 | 0 |  |  | 662.4 | 86.112 | 748.512 | 2020-09-08 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Missed gravel ticket hauling into WF5 that was caught after invoiced. | 5 | C050-C069 | Antler Lake | 0 | 44102 |  | 36 | 44102 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting511520200908-26Dump - Triaxle- After Jan 1012662.4 | Corbiere and Sons Contracting511520200908-26Dump - Triaxle- After Jan 1012662.4Inv#057 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 662.4 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5115 | 20200908-26 | 53510504 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-09-08 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Missed gravel ticket hauling into WF5 that was caught after invoiced. | 5 | C050-C069 | Antler Lake | 0 | 44102 |  | 36 | 44102 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting511520200908-26L.O.A.1210 | Corbiere and Sons Contracting511520200908-26L.O.A.1210Inv#057 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5115 | 20200908-26 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 12 | HR |  |  | 70 | 0 | 840 | 109.2 | 949.2 | 2020-09-08 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Missed gravel ticket hauling into WF5 that was caught after invoiced. | 5 | C050-C069 | Antler Lake | 0 | 44102 |  | 36 | 44102 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting511520200908-26Driver - AZ - After Jan 1012840 | Corbiere and Sons Contracting511520200908-26Driver - AZ - After Jan 1012840Inv#057 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4605 | 20200909-11 | 53510504 | Access | 0 | Loader JD 524 to 624 or equal | 99 | 10 | HR | 74.25 | 0 |  |  | 990 | 128.7 | 1118.7 | 2020-09-09 | 1 | Inv#052 | 44092 | 106 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | DZ and Loader spreading and packing road with gravel. | 5 | C050-C069 | Antler Lake | 0 | 44086 |  | 9 | 44091 | [5 empty] | Mandy Sandhu | 05 | Corbiere and Sons Contracting460520200909-11Loader JD 524 to 624 or equal10990 | Corbiere and Sons Contracting460520200909-11Loader JD 524 to 624 or equal10990Inv#052 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4605 | 20200909-11 | 53510504 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10 | Dynamic | 98.61 | 0 |  |  | 1314.8 | 170.924 | 1485.724 | 2020-09-09 | 1 | Inv#052 | 44092 | 106 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | DZ and Loader spreading and packing road with gravel. | 5 | C050-C069 | Antler Lake | 0 | 44086 |  | 9 | 44091 | [5 empty] | Mandy Sandhu | 05 | Corbiere and Sons Contracting460520200909-11Dozer D6 or equal- After Jan 10101314.8 | Corbiere and Sons Contracting460520200909-11Dozer D6 or equal- After Jan 10101314.8Inv#052 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1314.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4605 | 20200909-11 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-09-09 | 1 | Inv#052 | 44092 | 106 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | DZ and Loader spreading and packing road with gravel. | 5 | C050-C069 | Antler Lake | 0 | 44086 |  | 9 | 44091 | [5 empty] | Mandy Sandhu | 05 | Corbiere and Sons Contracting460520200909-11Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting460520200909-11Light Truck - Pick up- After Jan 102487.5Inv#052 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4605 | 20200909-11 | 53510504 | Access | 0 | Foreman | 95 | 4 | HR |  |  | 95 | 0 | 380 | 49.4 | 429.4 | 2020-09-09 | 1 | Inv#052 | 44092 | 106 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | DZ and Loader spreading and packing road with gravel. | 5 | C050-C069 | Antler Lake | 0 | 44086 |  | 9 | 44091 | [5 empty] | Mandy Sandhu | 05 | Corbiere and Sons Contracting460520200909-11Foreman4380 | Corbiere and Sons Contracting460520200909-11Foreman4380Inv#052 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4605 | 20200909-11 | 53510504 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2020-09-09 | 1 | Inv#052 | 44092 | 106 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | DZ and Loader spreading and packing road with gravel. | 5 | C050-C069 | Antler Lake | 0 | 44086 |  | 9 | 44091 | [5 empty] | Mandy Sandhu | 05 | Corbiere and Sons Contracting460520200909-11L.O.A.3630 | Corbiere and Sons Contracting460520200909-11L.O.A.3630Inv#052 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4605 | 20200909-11 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-09-09 | 1 | Inv#052 | 44092 | 106 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | DZ and Loader spreading and packing road with gravel. | 5 | C050-C069 | Antler Lake | 0 | 44086 |  | 9 | 44091 | [5 empty] | Mandy Sandhu | 05 | Corbiere and Sons Contracting460520200909-11Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting460520200909-11Operator - Principle - After Jan 1011.5862.5Inv#052 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4605 | 20200909-11 | 53510504 | Access | 0 | Operator - Intermdiate - After Jan 10 | 70 | 11.5 | HR |  |  | 70 | 0 | 805 | 104.65 | 909.65 | 2020-09-09 | 1 | Inv#052 | 44092 | 106 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | DZ and Loader spreading and packing road with gravel. | 5 | C050-C069 | Antler Lake | 0 | 44086 |  | 9 | 44091 | [5 empty] | Mandy Sandhu | 05 | Corbiere and Sons Contracting460520200909-11Operator - Intermdiate - After Jan 1011.5805 | Corbiere and Sons Contracting460520200909-11Operator - Intermdiate - After Jan 1011.5805Inv#052 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 805 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4636 | 20200910-14 | 53510503 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 1 | Dynamic | 110.22 | 0 |  |  | 146.96 | 19.1048 | 166.0648 | 2020-09-10 | 1 | Inv#052 | 44092 | 106 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX012 laying corduroy to reposition WC7400 (culvert) - 3-5m | 5 | C076-C116 | Cook Lake | 0 | 44087 |  | 9 | 44091 | [5 empty] | Mandy Sandhu | 05 | Corbiere and Sons Contracting463620200910-14Excavator - 36 ton- After Jan 101146.96 | Corbiere and Sons Contracting463620200910-14Excavator - 36 ton- After Jan 101146.96Inv#052 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 146.96 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4636 | 20200910-14 | 53510503 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 1 | HR |  |  | 75 | 0 | 75 | 9.75 | 84.75 | 2020-09-10 | 1 | Inv#052 | 44092 | 106 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX012 laying corduroy to reposition WC7400 (culvert) - 3-5m | 5 | C076-C116 | Cook Lake | 0 | 44087 |  | 9 | 44091 | [5 empty] | Mandy Sandhu | 05 | Corbiere and Sons Contracting463620200910-14Operator - Principle - After Jan 10175 | Corbiere and Sons Contracting463620200910-14Operator - Principle - After Jan 10175Inv#052 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4638 | 20200910-16 | 53510503 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 2 | Dynamic | 98.61 | 0 |  |  | 262.96 | 34.1848 | 297.1448 | 2020-09-10 | 1 | Inv#052 | 44092 | 106 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Covering corduroy sections, rolled out geo | 5 | C050-C069 | Antler Lake | 0 | 44087 |  | 9 | 44091 | [5 empty] | Mandy Sandhu | 05 | Corbiere and Sons Contracting463820200910-16Dozer D6 or equal- After Jan 102262.96 | Corbiere and Sons Contracting463820200910-16Dozer D6 or equal- After Jan 102262.96Inv#052 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 262.96 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4638 | 20200910-16 | 53510503 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 1 | Dynamic | 103.84 | 0 |  |  | 138.45 | 17.9985 | 156.4485 | 2020-09-10 | 1 | Inv#052 | 44092 | 106 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Covering corduroy sections, rolled out geo | 5 | C050-C069 | Antler Lake | 0 | 44087 |  | 9 | 44091 | [5 empty] | Mandy Sandhu | 05 | Corbiere and Sons Contracting463820200910-16Excavator - 30 ton- After Jan 101138.45 | Corbiere and Sons Contracting463820200910-16Excavator - 30 ton- After Jan 101138.45Inv#052 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 138.45 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4638 | 20200910-16 | 53510503 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 1 | Dynamic | 103.54 | 0 |  |  | 138.05 | 17.9465 | 155.9965 | 2020-09-10 | 1 | Inv#052 | 44092 | 106 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Covering corduroy sections, rolled out geo | 5 | C050-C069 | Antler Lake | 0 | 44087 |  | 9 | 44091 | [5 empty] | Mandy Sandhu | 05 | Corbiere and Sons Contracting463820200910-16Rock Truck - 30 Ton- After Jan 101138.05 | Corbiere and Sons Contracting463820200910-16Rock Truck - 30 Ton- After Jan 101138.05Inv#052 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 138.05 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4638 | 20200910-16 | 53510503 | Access | 0 | Foreman | 95 | 2 | HR |  |  | 95 | 0 | 190 | 24.7 | 214.7 | 2020-09-10 | 1 | Inv#052 | 44092 | 106 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Covering corduroy sections, rolled out geo | 5 | C050-C069 | Antler Lake | 0 | 44087 |  | 9 | 44091 | [5 empty] | Mandy Sandhu | 05 | Corbiere and Sons Contracting463820200910-16Foreman2190 | Corbiere and Sons Contracting463820200910-16Foreman2190Inv#052 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 190 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4638 | 20200910-16 | 53510503 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 3 | HR |  |  | 75 | 0 | 225 | 29.25 | 254.25 | 2020-09-10 | 1 | Inv#052 | 44092 | 106 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Covering corduroy sections, rolled out geo | 5 | C050-C069 | Antler Lake | 0 | 44087 |  | 9 | 44091 | [5 empty] | Mandy Sandhu | 05 | Corbiere and Sons Contracting463820200910-16Operator - Principle - After Jan 103225 | Corbiere and Sons Contracting463820200910-16Operator - Principle - After Jan 103225Inv#052 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 225 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4638 | 20200910-16 | 53510503 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 1 | HR |  |  | 70 | 0 | 70 | 9.1 | 79.1 | 2020-09-10 | 1 | Inv#052 | 44092 | 106 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Covering corduroy sections, rolled out geo | 5 | C050-C069 | Antler Lake | 0 | 44087 |  | 9 | 44091 | [5 empty] | Mandy Sandhu | 05 | Corbiere and Sons Contracting463820200910-16Driver - AZ - After Jan 10170 | Corbiere and Sons Contracting463820200910-16Driver - AZ - After Jan 10170Inv#052 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 70 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4638 | 20200910-16 | 53510503 | Access | 0 | Labourer - General - After Jan 10 | 60 | 1 | HR |  |  | 60 | 0 | 60 | 7.8 | 67.8 | 2020-09-10 | 1 | Inv#052 | 44092 | 106 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Covering corduroy sections, rolled out geo | 5 | C050-C069 | Antler Lake | 0 | 44087 |  | 9 | 44091 | [5 empty] | Mandy Sandhu | 05 | Corbiere and Sons Contracting463820200910-16Labourer - General - After Jan 10160 | Corbiere and Sons Contracting463820200910-16Labourer - General - After Jan 10160Inv#052 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 60 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4639 | 20200910-17 | 53510504 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 8 | Dynamic | 98.61 | 0 |  |  | 1051.84 | 136.7392 | 1188.5792 | 2020-09-10 | 1 | Inv#052 | 44092 | 106 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | JD300 loading rock truck for gravel haul, spreading gravel | 5 | C050-C069 | Antler Lake | 0 | 44087 |  | 9 | 44091 | [5 empty] | Mandy Sandhu | 05 | Corbiere and Sons Contracting463920200910-17Dozer D6 or equal- After Jan 1081051.84 | Corbiere and Sons Contracting463920200910-17Dozer D6 or equal- After Jan 1081051.84Inv#052 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1051.84 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4639 | 20200910-17 | 53510504 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 103.84 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2020-09-10 | 1 | Inv#052 | 44092 | 106 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | JD300 loading rock truck for gravel haul, spreading gravel | 5 | C050-C069 | Antler Lake | 0 | 44087 |  | 9 | 44091 | [5 empty] | Mandy Sandhu | 05 | Corbiere and Sons Contracting463920200910-17Excavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting463920200910-17Excavator - 30 ton- After Jan 1091246.05Inv#052 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1246.05 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4639 | 20200910-17 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-09-10 | 1 | Inv#052 | 44092 | 106 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | JD300 loading rock truck for gravel haul, spreading gravel | 5 | C050-C069 | Antler Lake | 0 | 44087 |  | 9 | 44091 | [5 empty] | Mandy Sandhu | 05 | Corbiere and Sons Contracting463920200910-17Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting463920200910-17Light Truck - Pick up- After Jan 102487.5Inv#052 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4639 | 20200910-17 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 8 | Dynamic | 103.54 | 0 |  |  | 1104.4 | 143.572 | 1247.972 | 2020-09-10 | 1 | Inv#052 | 44092 | 106 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | JD300 loading rock truck for gravel haul, spreading gravel | 5 | C050-C069 | Antler Lake | 0 | 44087 |  | 9 | 44091 | [5 empty] | Mandy Sandhu | 05 | Corbiere and Sons Contracting463920200910-17Rock Truck - 30 Ton- After Jan 1081104.4 | Corbiere and Sons Contracting463920200910-17Rock Truck - 30 Ton- After Jan 1081104.4Inv#052 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1104.4 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4639 | 20200910-17 | 53510504 | Access | 0 | Foreman | 95 | 4 | HR |  |  | 95 | 0 | 380 | 49.4 | 429.4 | 2020-09-10 | 1 | Inv#052 | 44092 | 106 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | JD300 loading rock truck for gravel haul, spreading gravel | 5 | C050-C069 | Antler Lake | 0 | 44087 |  | 9 | 44091 | [5 empty] | Mandy Sandhu | 05 | Corbiere and Sons Contracting463920200910-17Foreman4380 | Corbiere and Sons Contracting463920200910-17Foreman4380Inv#052 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4639 | 20200910-17 | 53510504 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2020-09-10 | 1 | Inv#052 | 44092 | 106 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | JD300 loading rock truck for gravel haul, spreading gravel | 5 | C050-C069 | Antler Lake | 0 | 44087 |  | 9 | 44091 | [5 empty] | Mandy Sandhu | 05 | Corbiere and Sons Contracting463920200910-17L.O.A.4840 | Corbiere and Sons Contracting463920200910-17L.O.A.4840Inv#052 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4639 | 20200910-17 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 17 | HR |  |  | 75 | 0 | 1275 | 165.75 | 1440.75 | 2020-09-10 | 1 | Inv#052 | 44092 | 106 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | JD300 loading rock truck for gravel haul, spreading gravel | 5 | C050-C069 | Antler Lake | 0 | 44087 |  | 9 | 44091 | [5 empty] | Mandy Sandhu | 05 | Corbiere and Sons Contracting463920200910-17Operator - Principle - After Jan 10171275 | Corbiere and Sons Contracting463920200910-17Operator - Principle - After Jan 10171275Inv#052 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1275 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4639 | 20200910-17 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 8 | HR |  |  | 70 | 0 | 560 | 72.8 | 632.8 | 2020-09-10 | 1 | Inv#052 | 44092 | 106 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | JD300 loading rock truck for gravel haul, spreading gravel | 5 | C050-C069 | Antler Lake | 0 | 44087 |  | 9 | 44091 | [5 empty] | Mandy Sandhu | 05 | Corbiere and Sons Contracting463920200910-17Driver - AZ - After Jan 108560 | Corbiere and Sons Contracting463920200910-17Driver - AZ - After Jan 108560Inv#052 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 560 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4630 | 20200910-8 | 53510212 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 8 | Dynamic | 95.24 | 0 |  |  | 1015.84 | 132.0592 | 1147.8992 | 2020-09-10 | 1 | Inv#052 | 44092 | 106 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Landfill and Black Sturgeon | 2 | B065-B077 | Red Rock | 0 | 44087 |  | 46 | 44093 | [5 empty] | Glen Greening | 02 | Corbiere and Sons Contracting463020200910-8Grader - Cat 12 to 14 or equal- After Jan 1081015.84 | Corbiere and Sons Contracting463020200910-8Grader - Cat 12 to 14 or equal- After Jan 1081015.84Inv#052 | [5 empty] | 1 | 1015.84 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4630 | 20200910-8 | 53510212 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-09-10 | 1 | Inv#052 | 44092 | 106 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Landfill and Black Sturgeon | 2 | B065-B077 | Red Rock | 0 | 44087 |  | 46 | 44093 | [5 empty] | Glen Greening | 02 | Corbiere and Sons Contracting463020200910-8Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting463020200910-8Light Truck - Pick up- After Jan 101243.75Inv#052 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4630 | 20200910-8 | 53510212 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-09-10 | 1 | Inv#052 | 44092 | 106 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Landfill and Black Sturgeon | 2 | B065-B077 | Red Rock | 0 | 44087 |  | 46 | 44093 | [5 empty] | Glen Greening | 02 | Corbiere and Sons Contracting463020200910-8L.O.A.1210 | Corbiere and Sons Contracting463020200910-8L.O.A.1210Inv#052 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4630 | 20200910-8 | 53510212 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 9 | HR |  |  | 75 |  | 675 | 87.75 | 762.75 | 2020-09-10 | 1 | Inv#052 | 44092 | 106 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Landfill and Black Sturgeon | 2 | B065-B077 | Red Rock | 0 | 44087 |  | 46 | 44093 | [5 empty] | Glen Greening | 02 | Corbiere and Sons Contracting463020200910-8Operator - Principle - After Jan 109675 | Corbiere and Sons Contracting463020200910-8Operator - Principle - After Jan 109675Inv#052 | [5 empty] | 1 | 675 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4658 | 20200911-10 | 53510504 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 7 | Dynamic | 98.61 | 0 |  |  | 920.36 | 119.6468 | 1040.0068 | 2020-09-11 | 1 | Inv#052 | 44092 | 106 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Stockpiling and loading RT, spreading gravel | 5 | C050-C069 | Antler Lake | 0 | 44087 |  | 9 | 44091 | [5 empty] | Mandy Sandhu | 05 | Corbiere and Sons Contracting465820200911-10Dozer D6 or equal- After Jan 107920.36 | Corbiere and Sons Contracting465820200911-10Dozer D6 or equal- After Jan 107920.36Inv#052 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 920.36 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4658 | 20200911-10 | 53510504 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 7 | Dynamic | 103.84 | 0 |  |  | 969.15 | 125.9895 | 1095.1395 | 2020-09-11 | 1 | Inv#052 | 44092 | 106 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Stockpiling and loading RT, spreading gravel | 5 | C050-C069 | Antler Lake | 0 | 44087 |  | 9 | 44091 | [5 empty] | Mandy Sandhu | 05 | Corbiere and Sons Contracting465820200911-10Excavator - 30 ton- After Jan 107969.15 | Corbiere and Sons Contracting465820200911-10Excavator - 30 ton- After Jan 107969.15Inv#052 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 969.15 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4658 | 20200911-10 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-09-11 | 1 | Inv#052 | 44092 | 106 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Stockpiling and loading RT, spreading gravel | 5 | C050-C069 | Antler Lake | 0 | 44087 |  | 9 | 44091 | [5 empty] | Mandy Sandhu | 05 | Corbiere and Sons Contracting465820200911-10Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting465820200911-10Light Truck - Pick up- After Jan 102487.5Inv#052 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4658 | 20200911-10 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 7 | Dynamic | 103.54 | 0 |  |  | 966.35 | 125.6255 | 1091.9755 | 2020-09-11 | 1 | Inv#052 | 44092 | 106 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Stockpiling and loading RT, spreading gravel | 5 | C050-C069 | Antler Lake | 0 | 44087 |  | 9 | 44091 | [5 empty] | Mandy Sandhu | 05 | Corbiere and Sons Contracting465820200911-10Rock Truck - 30 Ton- After Jan 107966.35 | Corbiere and Sons Contracting465820200911-10Rock Truck - 30 Ton- After Jan 107966.35Inv#052 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 966.35 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4658 | 20200911-10 | 53510504 | Access | 0 | Foreman | 95 | 4 | HR |  |  | 95 | 0 | 380 | 49.4 | 429.4 | 2020-09-11 | 1 | Inv#052 | 44092 | 106 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Stockpiling and loading RT, spreading gravel | 5 | C050-C069 | Antler Lake | 0 | 44087 |  | 9 | 44091 | [5 empty] | Mandy Sandhu | 05 | Corbiere and Sons Contracting465820200911-10Foreman4380 | Corbiere and Sons Contracting465820200911-10Foreman4380Inv#052 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4658 | 20200911-10 | 53510504 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2020-09-11 | 1 | Inv#052 | 44092 | 106 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Stockpiling and loading RT, spreading gravel | 5 | C050-C069 | Antler Lake | 0 | 44087 |  | 9 | 44091 | [5 empty] | Mandy Sandhu | 05 | Corbiere and Sons Contracting465820200911-10L.O.A.4840 | Corbiere and Sons Contracting465820200911-10L.O.A.4840Inv#052 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4658 | 20200911-10 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 21 | HR |  |  | 75 | 0 | 1575 | 204.75 | 1779.75 | 2020-09-11 | 1 | Inv#052 | 44092 | 106 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Stockpiling and loading RT, spreading gravel | 5 | C050-C069 | Antler Lake | 0 | 44087 |  | 9 | 44091 | [5 empty] | Mandy Sandhu | 05 | Corbiere and Sons Contracting465820200911-10Operator - Principle - After Jan 10211575 | Corbiere and Sons Contracting465820200911-10Operator - Principle - After Jan 10211575Inv#052 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1575 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4678 | 20200911-30 | 53510504 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 97.5 | Dynamic | 41.4 | 0 |  |  | 5382 | 699.66 | 6081.66 | 2020-09-11 | 1 | Inv#052 | 44092 | 106 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel hauling from North Shore's Pit just East of Schreiber into WF5 access roads. | 5 | C076-C116 | Cook Lake | 0 | 44087 |  | 9 | 44091 | [5 empty] | Mandy Sandhu | 05 | Corbiere and Sons Contracting467820200911-30Dump - Triaxle- After Jan 1097.55382 | Corbiere and Sons Contracting467820200911-30Dump - Triaxle- After Jan 1097.55382Inv#052 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 5382 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4678 | 20200911-30 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-09-11 | 1 | Inv#052 | 44092 | 106 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel hauling from North Shore's Pit just East of Schreiber into WF5 access roads. | 5 | C076-C116 | Cook Lake | 0 | 44087 |  | 9 | 44091 | [5 empty] | Mandy Sandhu | 05 | Corbiere and Sons Contracting467820200911-30Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting467820200911-30Light Truck - Pick up- After Jan 101243.75Inv#052 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4678 | 20200911-30 | 53510504 | Access | 0 | Construction Coordinator | 80 | 11.5 | HR |  |  | 80 | 0 | 920 | 119.6 | 1039.6 | 2020-09-11 | 1 | Inv#052 | 44092 | 106 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel hauling from North Shore's Pit just East of Schreiber into WF5 access roads. | 5 | C076-C116 | Cook Lake | 0 | 44087 |  | 9 | 44091 | [5 empty] | Mandy Sandhu | 05 | Corbiere and Sons Contracting467820200911-30Construction Coordinator11.5920 | Corbiere and Sons Contracting467820200911-30Construction Coordinator11.5920Inv#052 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 920 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4678 | 20200911-30 | 53510504 | Access | 0 | L.O.A. | 210 | 11 | DAY |  |  |  | 0 | 2310 | 300.3 | 2610.3 | 2020-09-11 | 1 | Inv#052 | 44092 | 106 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel hauling from North Shore's Pit just East of Schreiber into WF5 access roads. | 5 | C076-C116 | Cook Lake | 0 | 44087 |  | 9 | 44091 | [5 empty] | Mandy Sandhu | 05 | Corbiere and Sons Contracting467820200911-30L.O.A.112310 | Corbiere and Sons Contracting467820200911-30L.O.A.112310Inv#052 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 2310 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4678 | 20200911-30 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 97.5 | HR |  |  | 70 | 0 | 6825 | 887.25 | 7712.25 | 2020-09-11 | 1 | Inv#052 | 44092 | 106 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel hauling from North Shore's Pit just East of Schreiber into WF5 access roads. | 5 | C076-C116 | Cook Lake | 0 | 44087 |  | 9 | 44091 | [5 empty] | Mandy Sandhu | 05 | Corbiere and Sons Contracting467820200911-30Driver - AZ - After Jan 1097.56825 | Corbiere and Sons Contracting467820200911-30Driver - AZ - After Jan 1097.56825Inv#052 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 6825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4681 | 20200911-31 | 53510504 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 10.5 | Dynamic | 41.4 | 0 |  |  | 579.6 | 75.348 | 654.948 | 2020-09-11 | 1 | Inv#052 | 44092 | 106 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | (1) missed ticket for gravel hauling. | 5 | C076-C116 | Cook Lake | 0 | 44092 |  | 9 | 44092 | [5 empty] | Mandy Sandhu | 05 | Corbiere and Sons Contracting468120200911-31Dump - Triaxle- After Jan 1010.5579.6 | Corbiere and Sons Contracting468120200911-31Dump - Triaxle- After Jan 1010.5579.6Inv#052 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 579.6 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4681 | 20200911-31 | 53510504 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-09-11 | 1 | Inv#052 | 44092 | 106 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | (1) missed ticket for gravel hauling. | 5 | C076-C116 | Cook Lake | 0 | 44092 |  | 9 | 44092 | [5 empty] | Mandy Sandhu | 05 | Corbiere and Sons Contracting468120200911-31L.O.A.1210 | Corbiere and Sons Contracting468120200911-31L.O.A.1210Inv#052 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4681 | 20200911-31 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 10.5 | HR |  |  | 70 | 0 | 735 | 95.55 | 830.55 | 2020-09-11 | 1 | Inv#052 | 44092 | 106 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | (1) missed ticket for gravel hauling. | 5 | C076-C116 | Cook Lake | 0 | 44092 |  | 9 | 44092 | [5 empty] | Mandy Sandhu | 05 | Corbiere and Sons Contracting468120200911-31Driver - AZ - After Jan 1010.5735 | Corbiere and Sons Contracting468120200911-31Driver - AZ - After Jan 1010.5735Inv#052 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 735 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4712 | 20200912-12 | 53510504 | Access | 0 | Loader JD 524 to 624 or equal | 99 | 7.5 | HR | 74.25 | 0 |  |  | 742.5 | 96.525 | 839.025 | 2020-09-12 | 1 | Inv#052 | 44092 | 106 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock truck loading loader all day.DZ working on gravel spread | 5 | C050-C069 | Antler Lake | 0 | 44090 |  | 9 | 44093 | [5 empty] | Mandy Sandhu | 05 | Corbiere and Sons Contracting471220200912-12Loader JD 524 to 624 or equal7.5742.5 | Corbiere and Sons Contracting471220200912-12Loader JD 524 to 624 or equal7.5742.5Inv#052 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 742.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4712 | 20200912-12 | 53510504 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 7.5 | Dynamic | 98.61 | 0 |  |  | 986.1 | 128.193 | 1114.293 | 2020-09-12 | 1 | Inv#052 | 44092 | 106 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock truck loading loader all day.DZ working on gravel spread | 5 | C050-C069 | Antler Lake | 0 | 44090 |  | 9 | 44093 | [5 empty] | Mandy Sandhu | 05 | Corbiere and Sons Contracting471220200912-12Dozer D6 or equal- After Jan 107.5986.1 | Corbiere and Sons Contracting471220200912-12Dozer D6 or equal- After Jan 107.5986.1Inv#052 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 986.1 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4712 | 20200912-12 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-09-12 | 1 | Inv#052 | 44092 | 106 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock truck loading loader all day.DZ working on gravel spread | 5 | C050-C069 | Antler Lake | 0 | 44090 |  | 9 | 44093 | [5 empty] | Mandy Sandhu | 05 | Corbiere and Sons Contracting471220200912-12Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting471220200912-12Light Truck - Pick up- After Jan 102487.5Inv#052 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4712 | 20200912-12 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 8 | Dynamic | 103.54 | 0 |  |  | 1104.4 | 143.572 | 1247.972 | 2020-09-12 | 1 | Inv#052 | 44092 | 106 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock truck loading loader all day.DZ working on gravel spread | 5 | C050-C069 | Antler Lake | 0 | 44090 |  | 9 | 44093 | [5 empty] | Mandy Sandhu | 05 | Corbiere and Sons Contracting471220200912-12Rock Truck - 30 Ton- After Jan 1081104.4 | Corbiere and Sons Contracting471220200912-12Rock Truck - 30 Ton- After Jan 1081104.4Inv#052 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1104.4 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4712 | 20200912-12 | 53510504 | Access | 0 | Foreman | 95 | 4 | HR |  |  | 95 | 0 | 380 | 49.4 | 429.4 | 2020-09-12 | 1 | Inv#052 | 44092 | 106 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock truck loading loader all day.DZ working on gravel spread | 5 | C050-C069 | Antler Lake | 0 | 44090 |  | 9 | 44093 | [5 empty] | Mandy Sandhu | 05 | Corbiere and Sons Contracting471220200912-12Foreman4380 | Corbiere and Sons Contracting471220200912-12Foreman4380Inv#052 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4712 | 20200912-12 | 53510504 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2020-09-12 | 1 | Inv#052 | 44092 | 106 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock truck loading loader all day.DZ working on gravel spread | 5 | C050-C069 | Antler Lake | 0 | 44090 |  | 9 | 44093 | [5 empty] | Mandy Sandhu | 05 | Corbiere and Sons Contracting471220200912-12L.O.A.4840 | Corbiere and Sons Contracting471220200912-12L.O.A.4840Inv#052 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4712 | 20200912-12 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 16 | HR |  |  | 75 | 0 | 1200 | 156 | 1356 | 2020-09-12 | 1 | Inv#052 | 44092 | 106 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock truck loading loader all day.DZ working on gravel spread | 5 | C050-C069 | Antler Lake | 0 | 44090 |  | 9 | 44093 | [5 empty] | Mandy Sandhu | 05 | Corbiere and Sons Contracting471220200912-12Operator - Principle - After Jan 10161200 | Corbiere and Sons Contracting471220200912-12Operator - Principle - After Jan 10161200Inv#052 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1200 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4712 | 20200912-12 | 53510504 | Access | 0 | Labourer - General - After Jan 10 | 60 | 8 | HR |  |  | 60 | 0 | 480 | 62.4 | 542.4 | 2020-09-12 | 1 | Inv#052 | 44092 | 106 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock truck loading loader all day.DZ working on gravel spread | 5 | C050-C069 | Antler Lake | 0 | 44090 |  | 9 | 44093 | [5 empty] | Mandy Sandhu | 05 | Corbiere and Sons Contracting471220200912-12Labourer - General - After Jan 108480 | Corbiere and Sons Contracting471220200912-12Labourer - General - After Jan 108480Inv#052 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 480 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4701 | 20200913-10 | 53510504 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10 | Dynamic | 98.61 | 0 |  |  | 1314.8 | 170.924 | 1485.724 | 2020-09-13 | 1 | Inv#052 | 44092 | 106 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock truck worked all day hauling material from stockpile that was already on site via the JD300 and DZR. | 5 | C076-C116 | Cook Lake | 0 | 44090 |  | 9 | 44093 | [5 empty] | Mandy Sandhu | 05 | Corbiere and Sons Contracting470120200913-10Dozer D6 or equal- After Jan 10101314.8 | Corbiere and Sons Contracting470120200913-10Dozer D6 or equal- After Jan 10101314.8Inv#052 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1314.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4701 | 20200913-10 | 53510504 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10 | Dynamic | 103.84 | 0 |  |  | 1384.5 | 179.985 | 1564.485 | 2020-09-13 | 1 | Inv#052 | 44092 | 106 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock truck worked all day hauling material from stockpile that was already on site via the JD300 and DZR. | 5 | C076-C116 | Cook Lake | 0 | 44090 |  | 9 | 44093 | [5 empty] | Mandy Sandhu | 05 | Corbiere and Sons Contracting470120200913-10Excavator - 30 ton- After Jan 10101384.5 | Corbiere and Sons Contracting470120200913-10Excavator - 30 ton- After Jan 10101384.5Inv#052 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1384.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4701 | 20200913-10 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-09-13 | 1 | Inv#052 | 44092 | 106 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock truck worked all day hauling material from stockpile that was already on site via the JD300 and DZR. | 5 | C076-C116 | Cook Lake | 0 | 44090 |  | 9 | 44093 | [5 empty] | Mandy Sandhu | 05 | Corbiere and Sons Contracting470120200913-10Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting470120200913-10Light Truck - Pick up- After Jan 102487.5Inv#052 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4701 | 20200913-10 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 10 | Dynamic | 103.54 | 0 |  |  | 1380.5 | 179.465 | 1559.965 | 2020-09-13 | 1 | Inv#052 | 44092 | 106 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock truck worked all day hauling material from stockpile that was already on site via the JD300 and DZR. | 5 | C076-C116 | Cook Lake | 0 | 44090 |  | 9 | 44093 | [5 empty] | Mandy Sandhu | 05 | Corbiere and Sons Contracting470120200913-10Rock Truck - 30 Ton- After Jan 10101380.5 | Corbiere and Sons Contracting470120200913-10Rock Truck - 30 Ton- After Jan 10101380.5Inv#052 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1380.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4701 | 20200913-10 | 53510504 | Access | 0 | Foreman | 95 | 3 | HR |  |  | 95 | 0 | 285 | 37.05 | 322.05 | 2020-09-13 | 1 | Inv#052 | 44092 | 106 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock truck worked all day hauling material from stockpile that was already on site via the JD300 and DZR. | 5 | C076-C116 | Cook Lake | 0 | 44090 |  | 9 | 44093 | [5 empty] | Mandy Sandhu | 05 | Corbiere and Sons Contracting470120200913-10Foreman3285 | Corbiere and Sons Contracting470120200913-10Foreman3285Inv#052 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 285 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4701 | 20200913-10 | 53510504 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2020-09-13 | 1 | Inv#052 | 44092 | 106 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock truck worked all day hauling material from stockpile that was already on site via the JD300 and DZR. | 5 | C076-C116 | Cook Lake | 0 | 44090 |  | 9 | 44093 | [5 empty] | Mandy Sandhu | 05 | Corbiere and Sons Contracting470120200913-10L.O.A.4840 | Corbiere and Sons Contracting470120200913-10L.O.A.4840Inv#052 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4701 | 20200913-10 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 22 | HR |  |  | 75 | 0 | 1650 | 214.5 | 1864.5 | 2020-09-13 | 1 | Inv#052 | 44092 | 106 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock truck worked all day hauling material from stockpile that was already on site via the JD300 and DZR. | 5 | C076-C116 | Cook Lake | 0 | 44090 |  | 9 | 44093 | [5 empty] | Mandy Sandhu | 05 | Corbiere and Sons Contracting470120200913-10Operator - Principle - After Jan 10221650 | Corbiere and Sons Contracting470120200913-10Operator - Principle - After Jan 10221650Inv#052 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1650 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4701 | 20200913-10 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 11 | HR |  |  | 70 | 0 | 770 | 100.1 | 870.1 | 2020-09-13 | 1 | Inv#052 | 44092 | 106 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock truck worked all day hauling material from stockpile that was already on site via the JD300 and DZR. | 5 | C076-C116 | Cook Lake | 0 | 44090 |  | 9 | 44093 | [5 empty] | Mandy Sandhu | 05 | Corbiere and Sons Contracting470120200913-10Driver - AZ - After Jan 1011770 | Corbiere and Sons Contracting470120200913-10Driver - AZ - After Jan 1011770Inv#052 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 770 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4698 | 20200913-7 | 53510503 | Access | 0 | Feller Buncher | 240 | 4 | HR | 180 |  |  |  | 960 | 124.8 | 1084.8 | 2020-09-13 | 1 | Inv#052 | 44092 | 106 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | FB corduroy a wet area for 75m, fed wood to Evan for access down a vertical face | 5 | C050-C069 | Antler Lake | 0 | 44090 |  | 9 | 44093 | [5 empty] | Mandy Sandhu | 05 | Corbiere and Sons Contracting469820200913-7Feller Buncher4960 | Corbiere and Sons Contracting469820200913-7Feller Buncher4960Inv#052 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4698 | 20200913-7 | 53510503 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 4 | Dynamic | 103.84 | 0 |  |  | 553.8 | 71.994 | 625.794 | 2020-09-13 | 1 | Inv#052 | 44092 | 106 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | FB corduroy a wet area for 75m, fed wood to Evan for access down a vertical face | 5 | C050-C069 | Antler Lake | 0 | 44090 |  | 9 | 44093 | [5 empty] | Mandy Sandhu | 05 | Corbiere and Sons Contracting469820200913-7Excavator - 30 ton- After Jan 104553.8 | Corbiere and Sons Contracting469820200913-7Excavator - 30 ton- After Jan 104553.8Inv#052 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 553.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4698 | 20200913-7 | 53510503 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-09-13 | 1 | Inv#052 | 44092 | 106 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | FB corduroy a wet area for 75m, fed wood to Evan for access down a vertical face | 5 | C050-C069 | Antler Lake | 0 | 44090 |  | 9 | 44093 | [5 empty] | Mandy Sandhu | 05 | Corbiere and Sons Contracting469820200913-7Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting469820200913-7Light Truck - Pick up- After Jan 102487.5Inv#052 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4698 | 20200913-7 | 53510503 | Access | 0 | Foreman | 95 | 4 | HR |  |  | 95 | 0 | 380 | 49.4 | 429.4 | 2020-09-13 | 1 | Inv#052 | 44092 | 106 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | FB corduroy a wet area for 75m, fed wood to Evan for access down a vertical face | 5 | C050-C069 | Antler Lake | 0 | 44090 |  | 9 | 44093 | [5 empty] | Mandy Sandhu | 05 | Corbiere and Sons Contracting469820200913-7Foreman4380 | Corbiere and Sons Contracting469820200913-7Foreman4380Inv#052 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4698 | 20200913-7 | 53510503 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2020-09-13 | 1 | Inv#052 | 44092 | 106 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | FB corduroy a wet area for 75m, fed wood to Evan for access down a vertical face | 5 | C050-C069 | Antler Lake | 0 | 44090 |  | 9 | 44093 | [5 empty] | Mandy Sandhu | 05 | Corbiere and Sons Contracting469820200913-7L.O.A.3630 | Corbiere and Sons Contracting469820200913-7L.O.A.3630Inv#052 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4698 | 20200913-7 | 53510503 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 8 | HR |  |  | 75 | 0 | 600 | 78 | 678 | 2020-09-13 | 1 | Inv#052 | 44092 | 106 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | FB corduroy a wet area for 75m, fed wood to Evan for access down a vertical face | 5 | C050-C069 | Antler Lake | 0 | 44090 |  | 9 | 44093 | [5 empty] | Mandy Sandhu | 05 | Corbiere and Sons Contracting469820200913-7Operator - Principle - After Jan 108600 | Corbiere and Sons Contracting469820200913-7Operator - Principle - After Jan 108600Inv#052 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4728 | 20200914-10 | 53510504 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10.5 | Dynamic | 98.61 | 0 |  |  | 1380.54 | 179.4702 | 1560.0102 | 2020-09-14 | 1 | Inv#052 | 44092 | 106 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock truck hauling material that was already on site in stockpile via the 300JD and the Dozer. | 5 | C076-C116 | Cook Lake | 0 | 44092 |  | 9 | 44093 | [5 empty] | Mandy Sandhu | 05 | Corbiere and Sons Contracting472820200914-10Dozer D6 or equal- After Jan 1010.51380.54 | Corbiere and Sons Contracting472820200914-10Dozer D6 or equal- After Jan 1010.51380.54Inv#052 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1380.54 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4728 | 20200914-10 | 53510504 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10.5 | Dynamic | 110.22 | 0 |  |  | 1543.08 | 200.6004 | 1743.6804 | 2020-09-14 | 1 | Inv#052 | 44092 | 106 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock truck hauling material that was already on site in stockpile via the 300JD and the Dozer. | 5 | C076-C116 | Cook Lake | 0 | 44092 |  | 9 | 44093 | [5 empty] | Mandy Sandhu | 05 | Corbiere and Sons Contracting472820200914-10Excavator - 36 ton- After Jan 1010.51543.08 | Corbiere and Sons Contracting472820200914-10Excavator - 36 ton- After Jan 1010.51543.08Inv#052 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1543.08 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4728 | 20200914-10 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-09-14 | 1 | Inv#052 | 44092 | 106 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock truck hauling material that was already on site in stockpile via the 300JD and the Dozer. | 5 | C076-C116 | Cook Lake | 0 | 44092 |  | 9 | 44093 | [5 empty] | Mandy Sandhu | 05 | Corbiere and Sons Contracting472820200914-10Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting472820200914-10Light Truck - Pick up- After Jan 102487.5Inv#052 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4728 | 20200914-10 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 10.5 | Dynamic | 103.54 | 0 |  |  | 1449.525 | 188.4383 | 1637.9633 | 2020-09-14 | 1 | Inv#052 | 44092 | 106 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock truck hauling material that was already on site in stockpile via the 300JD and the Dozer. | 5 | C076-C116 | Cook Lake | 0 | 44092 |  | 9 | 44093 | [5 empty] | Mandy Sandhu | 05 | Corbiere and Sons Contracting472820200914-10Rock Truck - 30 Ton- After Jan 1010.51449.525 | Corbiere and Sons Contracting472820200914-10Rock Truck - 30 Ton- After Jan 1010.51449.525Inv#052 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1449.525 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4728 | 20200914-10 | 53510504 | Access | 0 | Foreman | 95 | 3 | HR |  |  | 95 | 0 | 285 | 37.05 | 322.05 | 2020-09-14 | 1 | Inv#052 | 44092 | 106 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock truck hauling material that was already on site in stockpile via the 300JD and the Dozer. | 5 | C076-C116 | Cook Lake | 0 | 44092 |  | 9 | 44093 | [5 empty] | Mandy Sandhu | 05 | Corbiere and Sons Contracting472820200914-10Foreman3285 | Corbiere and Sons Contracting472820200914-10Foreman3285Inv#052 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 285 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4728 | 20200914-10 | 53510504 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2020-09-14 | 1 | Inv#052 | 44092 | 106 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock truck hauling material that was already on site in stockpile via the 300JD and the Dozer. | 5 | C076-C116 | Cook Lake | 0 | 44092 |  | 9 | 44093 | [5 empty] | Mandy Sandhu | 05 | Corbiere and Sons Contracting472820200914-10L.O.A.4840 | Corbiere and Sons Contracting472820200914-10L.O.A.4840Inv#052 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4728 | 20200914-10 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 23 | HR |  |  | 75 | 0 | 1725 | 224.25 | 1949.25 | 2020-09-14 | 1 | Inv#052 | 44092 | 106 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock truck hauling material that was already on site in stockpile via the 300JD and the Dozer. | 5 | C076-C116 | Cook Lake | 0 | 44092 |  | 9 | 44093 | [5 empty] | Mandy Sandhu | 05 | Corbiere and Sons Contracting472820200914-10Operator - Principle - After Jan 10231725 | Corbiere and Sons Contracting472820200914-10Operator - Principle - After Jan 10231725Inv#052 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4728 | 20200914-10 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 11.5 | HR |  |  | 70 | 0 | 805 | 104.65 | 909.65 | 2020-09-14 | 1 | Inv#052 | 44092 | 106 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock truck hauling material that was already on site in stockpile via the 300JD and the Dozer. | 5 | C076-C116 | Cook Lake | 0 | 44092 |  | 9 | 44093 | [5 empty] | Mandy Sandhu | 05 | Corbiere and Sons Contracting472820200914-10Driver - AZ - After Jan 1011.5805 | Corbiere and Sons Contracting472820200914-10Driver - AZ - After Jan 1011.5805Inv#052 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 805 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4747 | 20200914-21 | 53510504 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 108 | Dynamic | 41.4 | 0 |  |  | 5961.6 | 775.008 | 6736.608 | 2020-09-14 | 1 | Inv#052 | 44092 | 106 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel hauling to WF5 | 5 | C076-C116 | Cook Lake | 0 | 44094 |  | 9 | 44093 | [5 empty] | Mandy Sandhu | 05 | Corbiere and Sons Contracting474720200914-21Dump - Triaxle- After Jan 101085961.6 | Corbiere and Sons Contracting474720200914-21Dump - Triaxle- After Jan 101085961.6Inv#052 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 5961.6 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4747 | 20200914-21 | 53510504 | Access | 0 | L.O.A. | 210 | 8 | DAY |  |  |  | 0 | 1680 | 218.4 | 1898.4 | 2020-09-14 | 1 | Inv#052 | 44092 | 106 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel hauling to WF5 | 5 | C076-C116 | Cook Lake | 0 | 44094 |  | 9 | 44093 | [5 empty] | Mandy Sandhu | 05 | Corbiere and Sons Contracting474720200914-21L.O.A.81680 | Corbiere and Sons Contracting474720200914-21L.O.A.81680Inv#052 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1680 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4747 | 20200914-21 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 108 | HR |  |  | 70 | 0 | 7560 | 982.8 | 8542.8 | 2020-09-14 | 1 | Inv#052 | 44092 | 106 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel hauling to WF5 | 5 | C076-C116 | Cook Lake | 0 | 44094 |  | 9 | 44093 | [5 empty] | Mandy Sandhu | 05 | Corbiere and Sons Contracting474720200914-21Driver - AZ - After Jan 101087560 | Corbiere and Sons Contracting474720200914-21Driver - AZ - After Jan 101087560Inv#052 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 7560 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4759 | 20200915-11 | 53510504 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10.5 | Dynamic | 98.61 | 0 |  |  | 1380.54 | 179.4702 | 1560.0102 | 2020-09-15 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX, DZ and Rock Truck worked all day building road with stockpile material | 5 | C076-C116 | Cook Lake | 0 | 44093 |  | 9 | 44095 | [5 empty] | Mandy Sandhu | 05 | Corbiere and Sons Contracting475920200915-11Dozer D6 or equal- After Jan 1010.51380.54 | Corbiere and Sons Contracting475920200915-11Dozer D6 or equal- After Jan 1010.51380.54Inv#055 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1380.54 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4759 | 20200915-11 | 53510504 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10.5 | Dynamic | 103.84 | 0 |  |  | 1453.725 | 188.9843 | 1642.7093 | 2020-09-15 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX, DZ and Rock Truck worked all day building road with stockpile material | 5 | C076-C116 | Cook Lake | 0 | 44093 |  | 9 | 44095 | [5 empty] | Mandy Sandhu | 05 | Corbiere and Sons Contracting475920200915-11Excavator - 30 ton- After Jan 1010.51453.725 | Corbiere and Sons Contracting475920200915-11Excavator - 30 ton- After Jan 1010.51453.725Inv#055 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1453.725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4759 | 20200915-11 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-09-15 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX, DZ and Rock Truck worked all day building road with stockpile material | 5 | C076-C116 | Cook Lake | 0 | 44093 |  | 9 | 44095 | [5 empty] | Mandy Sandhu | 05 | Corbiere and Sons Contracting475920200915-11Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting475920200915-11Light Truck - Pick up- After Jan 102487.5Inv#055 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4759 | 20200915-11 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 10.5 | Dynamic | 103.54 | 0 |  |  | 1449.525 | 188.4383 | 1637.9633 | 2020-09-15 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX, DZ and Rock Truck worked all day building road with stockpile material | 5 | C076-C116 | Cook Lake | 0 | 44093 |  | 9 | 44095 | [5 empty] | Mandy Sandhu | 05 | Corbiere and Sons Contracting475920200915-11Rock Truck - 30 Ton- After Jan 1010.51449.525 | Corbiere and Sons Contracting475920200915-11Rock Truck - 30 Ton- After Jan 1010.51449.525Inv#055 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1449.525 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4759 | 20200915-11 | 53510504 | Access | 0 | Foreman | 95 | 2 | HR |  |  | 95 | 0 | 190 | 24.7 | 214.7 | 2020-09-15 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX, DZ and Rock Truck worked all day building road with stockpile material | 5 | C076-C116 | Cook Lake | 0 | 44093 |  | 9 | 44095 | [5 empty] | Mandy Sandhu | 05 | Corbiere and Sons Contracting475920200915-11Foreman2190 | Corbiere and Sons Contracting475920200915-11Foreman2190Inv#055 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 190 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4759 | 20200915-11 | 53510504 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2020-09-15 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX, DZ and Rock Truck worked all day building road with stockpile material | 5 | C076-C116 | Cook Lake | 0 | 44093 |  | 9 | 44095 | [5 empty] | Mandy Sandhu | 05 | Corbiere and Sons Contracting475920200915-11L.O.A.3630 | Corbiere and Sons Contracting475920200915-11L.O.A.3630Inv#055 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4759 | 20200915-11 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 23 | HR |  |  | 75 | 0 | 1725 | 224.25 | 1949.25 | 2020-09-15 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX, DZ and Rock Truck worked all day building road with stockpile material | 5 | C076-C116 | Cook Lake | 0 | 44093 |  | 9 | 44095 | [5 empty] | Mandy Sandhu | 05 | Corbiere and Sons Contracting475920200915-11Operator - Principle - After Jan 10231725 | Corbiere and Sons Contracting475920200915-11Operator - Principle - After Jan 10231725Inv#055 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4759 | 20200915-11 | 53510504 | Access | 0 | Labourer - General - After Jan 10 | 60 | 11.5 | HR |  |  | 60 | 0 | 690 | 89.7 | 779.7 | 2020-09-15 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX, DZ and Rock Truck worked all day building road with stockpile material | 5 | C076-C116 | Cook Lake | 0 | 44093 |  | 9 | 44095 | [5 empty] | Mandy Sandhu | 05 | Corbiere and Sons Contracting475920200915-11Labourer - General - After Jan 1011.5690 | Corbiere and Sons Contracting475920200915-11Labourer - General - After Jan 1011.5690Inv#055 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 690 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4761 | 20200915-13 | 53510502 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10.5 | Dynamic | 110.22 | 0 |  |  | 1543.08 | 200.6004 | 1743.6804 | 2020-09-15 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ran 460 Linkbelt helping Valard's hammer all day | 5 | C076-C116 | Cook Lake | 0 | 44093 |  | 9 | 44095 | [5 empty] | Mandy Sandhu | 05 | Corbiere and Sons Contracting476120200915-13Excavator - 36 ton- After Jan 1010.51543.08 | Corbiere and Sons Contracting476120200915-13Excavator - 36 ton- After Jan 1010.51543.08Inv#055 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 1543.08 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4761 | 20200915-13 | 53510502 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-09-15 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ran 460 Linkbelt helping Valard's hammer all day | 5 | C076-C116 | Cook Lake | 0 | 44093 |  | 9 | 44095 | [5 empty] | Mandy Sandhu | 05 | Corbiere and Sons Contracting476120200915-13Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting476120200915-13Light Truck - Pick up- After Jan 101243.75Inv#055 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4761 | 20200915-13 | 53510502 | Access | 0 | Foreman | 95 | 2 | HR |  |  | 95 | 0 | 190 | 24.7 | 214.7 | 2020-09-15 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ran 460 Linkbelt helping Valard's hammer all day | 5 | C076-C116 | Cook Lake | 0 | 44093 |  | 9 | 44095 | [5 empty] | Mandy Sandhu | 05 | Corbiere and Sons Contracting476120200915-13Foreman2190 | Corbiere and Sons Contracting476120200915-13Foreman2190Inv#055 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 190 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4761 | 20200915-13 | 53510502 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-09-15 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ran 460 Linkbelt helping Valard's hammer all day | 5 | C076-C116 | Cook Lake | 0 | 44093 |  | 9 | 44095 | [5 empty] | Mandy Sandhu | 05 | Corbiere and Sons Contracting476120200915-13L.O.A.1210 | Corbiere and Sons Contracting476120200915-13L.O.A.1210Inv#055 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4761 | 20200915-13 | 53510502 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-09-15 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ran 460 Linkbelt helping Valard's hammer all day | 5 | C076-C116 | Cook Lake | 0 | 44093 |  | 9 | 44095 | [5 empty] | Mandy Sandhu | 05 | Corbiere and Sons Contracting476120200915-13Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting476120200915-13Operator - Principle - After Jan 1011.5862.5Inv#055 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4754 | 20200915-6 | 53510504 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10.5 | Dynamic | 98.61 | 0 |  |  | 1380.54 | 179.4702 | 1560.0102 | 2020-09-15 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Loading rock truck all day, spreading gravel from stock pile - completed 150m towards WC7141. Dwayne and Evan on rock trucks | 5 | C050-C069 | Antler Lake | 0 | 44093 |  | 9 | 44095 | [5 empty] | Mandy Sandhu | 05 | Corbiere and Sons Contracting475420200915-6Dozer D6 or equal- After Jan 1010.51380.54 | Corbiere and Sons Contracting475420200915-6Dozer D6 or equal- After Jan 1010.51380.54Inv#055 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1380.54 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4754 | 20200915-6 | 53510504 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9.5 | Dynamic | 103.84 | 0 |  |  | 1315.275 | 170.9857 | 1486.2607 | 2020-09-15 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Loading rock truck all day, spreading gravel from stock pile - completed 150m towards WC7141. Dwayne and Evan on rock trucks | 5 | C050-C069 | Antler Lake | 0 | 44093 |  | 9 | 44095 | [5 empty] | Mandy Sandhu | 05 | Corbiere and Sons Contracting475420200915-6Excavator - 30 ton- After Jan 109.51315.275 | Corbiere and Sons Contracting475420200915-6Excavator - 30 ton- After Jan 109.51315.275Inv#055 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1315.275 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4754 | 20200915-6 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-09-15 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Loading rock truck all day, spreading gravel from stock pile - completed 150m towards WC7141. Dwayne and Evan on rock trucks | 5 | C050-C069 | Antler Lake | 0 | 44093 |  | 9 | 44095 | [5 empty] | Mandy Sandhu | 05 | Corbiere and Sons Contracting475420200915-6Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting475420200915-6Light Truck - Pick up- After Jan 102487.5Inv#055 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4754 | 20200915-6 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 14.5 | Dynamic | 103.54 | 0 |  |  | 2001.725 | 260.2242 | 2261.9493 | 2020-09-15 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Loading rock truck all day, spreading gravel from stock pile - completed 150m towards WC7141. Dwayne and Evan on rock trucks | 5 | C050-C069 | Antler Lake | 0 | 44093 |  | 9 | 44095 | [5 empty] | Mandy Sandhu | 05 | Corbiere and Sons Contracting475420200915-6Rock Truck - 30 Ton- After Jan 1014.52001.725 | Corbiere and Sons Contracting475420200915-6Rock Truck - 30 Ton- After Jan 1014.52001.725Inv#055 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 2001.725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4754 | 20200915-6 | 53510504 | Access | 0 | Foreman | 95 | 4 | HR |  |  | 95 | 0 | 380 | 49.4 | 429.4 | 2020-09-15 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Loading rock truck all day, spreading gravel from stock pile - completed 150m towards WC7141. Dwayne and Evan on rock trucks | 5 | C050-C069 | Antler Lake | 0 | 44093 |  | 9 | 44095 | [5 empty] | Mandy Sandhu | 05 | Corbiere and Sons Contracting475420200915-6Foreman4380 | Corbiere and Sons Contracting475420200915-6Foreman4380Inv#055 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4754 | 20200915-6 | 53510504 | Access | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2020-09-15 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Loading rock truck all day, spreading gravel from stock pile - completed 150m towards WC7141. Dwayne and Evan on rock trucks | 5 | C050-C069 | Antler Lake | 0 | 44093 |  | 9 | 44095 | [5 empty] | Mandy Sandhu | 05 | Corbiere and Sons Contracting475420200915-6L.O.A.51050 | Corbiere and Sons Contracting475420200915-6L.O.A.51050Inv#055 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4754 | 20200915-6 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 26 | HR |  |  | 75 | 0 | 1950 | 253.5 | 2203.5 | 2020-09-15 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Loading rock truck all day, spreading gravel from stock pile - completed 150m towards WC7141. Dwayne and Evan on rock trucks | 5 | C050-C069 | Antler Lake | 0 | 44093 |  | 9 | 44095 | [5 empty] | Mandy Sandhu | 05 | Corbiere and Sons Contracting475420200915-6Operator - Principle - After Jan 10261950 | Corbiere and Sons Contracting475420200915-6Operator - Principle - After Jan 10261950Inv#055 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1950 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4754 | 20200915-6 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 11.5 | HR |  |  | 70 | 0 | 805 | 104.65 | 909.65 | 2020-09-15 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Loading rock truck all day, spreading gravel from stock pile - completed 150m towards WC7141. Dwayne and Evan on rock trucks | 5 | C050-C069 | Antler Lake | 0 | 44093 |  | 9 | 44095 | [5 empty] | Mandy Sandhu | 05 | Corbiere and Sons Contracting475420200915-6Driver - AZ - After Jan 1011.5805 | Corbiere and Sons Contracting475420200915-6Driver - AZ - After Jan 1011.5805Inv#055 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 805 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4757 | 20200915-9 | 53510502 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2020-09-15 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ran rock hammer all day | 5 | C050-C069 | Antler Lake | 0 | 44093 |  | 9 | 44095 | [5 empty] | Mandy Sandhu | 05 | Corbiere and Sons Contracting475720200915-9Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting475720200915-9Excavator - 36 ton- After Jan 1091322.64Inv#055 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 1322.64 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4757 | 20200915-9 | 53510502 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 9 | HR | 47.54 | 0 |  |  | 570.42 | 74.1546 | 644.5746 | 2020-09-15 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ran rock hammer all day | 5 | C050-C069 | Antler Lake | 0 | 44093 |  | 9 | 44095 | [5 empty] | Mandy Sandhu | 05 | Corbiere and Sons Contracting475720200915-9Excavator Hammer - 30 - 50 ton- After Jan 109570.42 | Corbiere and Sons Contracting475720200915-9Excavator Hammer - 30 - 50 ton- After Jan 109570.42Inv#055 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 570.42 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4757 | 20200915-9 | 53510502 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-09-15 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ran rock hammer all day | 5 | C050-C069 | Antler Lake | 0 | 44093 |  | 9 | 44095 | [5 empty] | Mandy Sandhu | 05 | Corbiere and Sons Contracting475720200915-9Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting475720200915-9Light Truck - Pick up- After Jan 101243.75Inv#055 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4757 | 20200915-9 | 53510502 | Access | 0 | Foreman | 95 | 2 | HR |  |  | 95 | 0 | 190 | 24.7 | 214.7 | 2020-09-15 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ran rock hammer all day | 5 | C050-C069 | Antler Lake | 0 | 44093 |  | 9 | 44095 | [5 empty] | Mandy Sandhu | 05 | Corbiere and Sons Contracting475720200915-9Foreman2190 | Corbiere and Sons Contracting475720200915-9Foreman2190Inv#055 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 190 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4757 | 20200915-9 | 53510502 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-09-15 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ran rock hammer all day | 5 | C050-C069 | Antler Lake | 0 | 44093 |  | 9 | 44095 | [5 empty] | Mandy Sandhu | 05 | Corbiere and Sons Contracting475720200915-9L.O.A.1210 | Corbiere and Sons Contracting475720200915-9L.O.A.1210Inv#055 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4757 | 20200915-9 | 53510502 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2020-09-15 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ran rock hammer all day | 5 | C050-C069 | Antler Lake | 0 | 44093 |  | 9 | 44095 | [5 empty] | Mandy Sandhu | 05 | Corbiere and Sons Contracting475720200915-9Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting475720200915-9Operator - Principle - After Jan 1011825Inv#055 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4861 | 20200916-12 | 53510504 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 77 | Dynamic | 41.4 | 0 |  |  | 4250.4 | 552.552 | 4802.952 | 2020-09-16 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 127 hours worked split - 77 for WF5 and 50 for WF4 | 5 | C050-C069 | Antler Lake | 0 | 44096 |  | 36 | 44096 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting486120200916-12Dump - Triaxle- After Jan 10774250.4 | Corbiere and Sons Contracting486120200916-12Dump - Triaxle- After Jan 10774250.4Inv#055 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 4250.4 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4861 | 20200916-12 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-09-16 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 127 hours worked split - 77 for WF5 and 50 for WF4 | 5 | C050-C069 | Antler Lake | 0 | 44096 |  | 36 | 44096 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting486120200916-12Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting486120200916-12Light Truck - Pick up- After Jan 101243.75Inv#055 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4861 | 20200916-12 | 53510504 | Access | 0 | Construction Coordinator | 80 | 11.5 | HR |  |  | 80 | 0 | 920 | 119.6 | 1039.6 | 2020-09-16 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 127 hours worked split - 77 for WF5 and 50 for WF4 | 5 | C050-C069 | Antler Lake | 0 | 44096 |  | 36 | 44096 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting486120200916-12Construction Coordinator11.5920 | Corbiere and Sons Contracting486120200916-12Construction Coordinator11.5920Inv#055 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 920 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4861 | 20200916-12 | 53510504 | Access | 0 | L.O.A. | 210 | 7 | DAY |  |  |  | 0 | 1470 | 191.1 | 1661.1 | 2020-09-16 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 127 hours worked split - 77 for WF5 and 50 for WF4 | 5 | C050-C069 | Antler Lake | 0 | 44096 |  | 36 | 44096 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting486120200916-12L.O.A.71470 | Corbiere and Sons Contracting486120200916-12L.O.A.71470Inv#055 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1470 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4861 | 20200916-12 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 77 | HR |  |  | 70 | 0 | 5390 | 700.7 | 6090.7 | 2020-09-16 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 127 hours worked split - 77 for WF5 and 50 for WF4 | 5 | C050-C069 | Antler Lake | 0 | 44096 |  | 36 | 44096 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting486120200916-12Driver - AZ - After Jan 10775390 | Corbiere and Sons Contracting486120200916-12Driver - AZ - After Jan 10775390Inv#055 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 5390 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4864 | 20200916-15 | 53510504 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10.5 | Dynamic | 98.61 | 0 |  |  | 1380.54 | 179.4702 | 1560.0102 | 2020-09-16 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Loading rock trucks, spreading gravel (120m completed), rolled out geo | 5 | C050-C069 | Antler Lake | 0 | 44096 |  | 36 | 44096 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting486420200916-15Dozer D6 or equal- After Jan 1010.51380.54 | Corbiere and Sons Contracting486420200916-15Dozer D6 or equal- After Jan 1010.51380.54Inv#055 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1380.54 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4864 | 20200916-15 | 53510504 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10.5 | Dynamic | 103.84 | 0 |  |  | 1453.725 | 188.9843 | 1642.7093 | 2020-09-16 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Loading rock trucks, spreading gravel (120m completed), rolled out geo | 5 | C050-C069 | Antler Lake | 0 | 44096 |  | 36 | 44096 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting486420200916-15Excavator - 30 ton- After Jan 1010.51453.725 | Corbiere and Sons Contracting486420200916-15Excavator - 30 ton- After Jan 1010.51453.725Inv#055 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1453.725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4864 | 20200916-15 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-09-16 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Loading rock trucks, spreading gravel (120m completed), rolled out geo | 5 | C050-C069 | Antler Lake | 0 | 44096 |  | 36 | 44096 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting486420200916-15Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting486420200916-15Light Truck - Pick up- After Jan 102487.5Inv#055 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4864 | 20200916-15 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 21 | Dynamic | 103.54 | 0 |  |  | 2899.05 | 376.8765 | 3275.9265 | 2020-09-16 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Loading rock trucks, spreading gravel (120m completed), rolled out geo | 5 | C050-C069 | Antler Lake | 0 | 44096 |  | 36 | 44096 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting486420200916-15Rock Truck - 30 Ton- After Jan 10212899.05 | Corbiere and Sons Contracting486420200916-15Rock Truck - 30 Ton- After Jan 10212899.05Inv#055 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 2899.05 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4864 | 20200916-15 | 53510504 | Access | 0 | Foreman | 95 | 4 | HR |  |  | 95 | 0 | 380 | 49.4 | 429.4 | 2020-09-16 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Loading rock trucks, spreading gravel (120m completed), rolled out geo | 5 | C050-C069 | Antler Lake | 0 | 44096 |  | 36 | 44096 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting486420200916-15Foreman4380 | Corbiere and Sons Contracting486420200916-15Foreman4380Inv#055 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4864 | 20200916-15 | 53510504 | Access | 0 | L.O.A. | 210 | 7 | DAY |  |  |  | 0 | 1470 | 191.1 | 1661.1 | 2020-09-16 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Loading rock trucks, spreading gravel (120m completed), rolled out geo | 5 | C050-C069 | Antler Lake | 0 | 44096 |  | 36 | 44096 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting486420200916-15L.O.A.71470 | Corbiere and Sons Contracting486420200916-15L.O.A.71470Inv#055 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1470 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4864 | 20200916-15 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 23 | HR |  |  | 75 | 0 | 1725 | 224.25 | 1949.25 | 2020-09-16 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Loading rock trucks, spreading gravel (120m completed), rolled out geo | 5 | C050-C069 | Antler Lake | 0 | 44096 |  | 36 | 44096 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting486420200916-15Operator - Principle - After Jan 10231725 | Corbiere and Sons Contracting486420200916-15Operator - Principle - After Jan 10231725Inv#055 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4864 | 20200916-15 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 23 | HR |  |  | 70 | 0 | 1610 | 209.3 | 1819.3 | 2020-09-16 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Loading rock trucks, spreading gravel (120m completed), rolled out geo | 5 | C050-C069 | Antler Lake | 0 | 44096 |  | 36 | 44096 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting486420200916-15Driver - AZ - After Jan 10231610 | Corbiere and Sons Contracting486420200916-15Driver - AZ - After Jan 10231610Inv#055 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1610 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4864 | 20200916-15 | 53510504 | Access | 0 | Labourer - General - After Jan 10 | 60 | 4 | HR |  |  | 60 | 0 | 240 | 31.2 | 271.2 | 2020-09-16 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Loading rock trucks, spreading gravel (120m completed), rolled out geo | 5 | C050-C069 | Antler Lake | 0 | 44096 |  | 36 | 44096 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting486420200916-15Labourer - General - After Jan 104240 | Corbiere and Sons Contracting486420200916-15Labourer - General - After Jan 104240Inv#055 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 240 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4866 | 20200916-17 | 53510502 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10.5 | Dynamic | 110.22 | 0 |  |  | 1543.08 | 200.6004 | 1743.6804 | 2020-09-16 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ran rock hammer all day | 5 | C050-C069 | Antler Lake | 0 | 44096 |  | 36 | 44096 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting486620200916-17Excavator - 36 ton- After Jan 1010.51543.08 | Corbiere and Sons Contracting486620200916-17Excavator - 36 ton- After Jan 1010.51543.08Inv#055 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 1543.08 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4866 | 20200916-17 | 53510502 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 10.5 | HR | 47.54 | 0 |  |  | 665.49 | 86.5137 | 752.0037 | 2020-09-16 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ran rock hammer all day | 5 | C050-C069 | Antler Lake | 0 | 44096 |  | 36 | 44096 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting486620200916-17Excavator Hammer - 30 - 50 ton- After Jan 1010.5665.49 | Corbiere and Sons Contracting486620200916-17Excavator Hammer - 30 - 50 ton- After Jan 1010.5665.49Inv#055 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 665.49 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4866 | 20200916-17 | 53510502 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-09-16 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ran rock hammer all day | 5 | C050-C069 | Antler Lake | 0 | 44096 |  | 36 | 44096 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting486620200916-17Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting486620200916-17Light Truck - Pick up- After Jan 101243.75Inv#055 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4866 | 20200916-17 | 53510502 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-09-16 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ran rock hammer all day | 5 | C050-C069 | Antler Lake | 0 | 44096 |  | 36 | 44096 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting486620200916-17L.O.A.1210 | Corbiere and Sons Contracting486620200916-17L.O.A.1210Inv#055 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4866 | 20200916-17 | 53510502 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-09-16 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ran rock hammer all day | 5 | C050-C069 | Antler Lake | 0 | 44096 |  | 36 | 44096 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting486620200916-17Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting486620200916-17Operator - Principle - After Jan 1011.5862.5Inv#055 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4867 | 20200916-18 | 53510504 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10.5 | Dynamic | 98.61 | 0 |  |  | 1380.54 | 179.4702 | 1560.0102 | 2020-09-16 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hauling material that was already on site to stockpile via the 300JD and the Dozer | 5 | C076-C116 | Cook Lake | 0 | 44096 |  | 36 | 44096 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting486720200916-18Dozer D6 or equal- After Jan 1010.51380.54 | Corbiere and Sons Contracting486720200916-18Dozer D6 or equal- After Jan 1010.51380.54Inv#055 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1380.54 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4867 | 20200916-18 | 53510504 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10.5 | Dynamic | 110.22 | 0 |  |  | 1543.08 | 200.6004 | 1743.6804 | 2020-09-16 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hauling material that was already on site to stockpile via the 300JD and the Dozer | 5 | C076-C116 | Cook Lake | 0 | 44096 |  | 36 | 44096 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting486720200916-18Excavator - 36 ton- After Jan 1010.51543.08 | Corbiere and Sons Contracting486720200916-18Excavator - 36 ton- After Jan 1010.51543.08Inv#055 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1543.08 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4867 | 20200916-18 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-09-16 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hauling material that was already on site to stockpile via the 300JD and the Dozer | 5 | C076-C116 | Cook Lake | 0 | 44096 |  | 36 | 44096 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting486720200916-18Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting486720200916-18Light Truck - Pick up- After Jan 102487.5Inv#055 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4867 | 20200916-18 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 10.5 | Dynamic | 103.54 | 0 |  |  | 1449.525 | 188.4383 | 1637.9633 | 2020-09-16 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hauling material that was already on site to stockpile via the 300JD and the Dozer | 5 | C076-C116 | Cook Lake | 0 | 44096 |  | 36 | 44096 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting486720200916-18Rock Truck - 30 Ton- After Jan 1010.51449.525 | Corbiere and Sons Contracting486720200916-18Rock Truck - 30 Ton- After Jan 1010.51449.525Inv#055 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1449.525 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4867 | 20200916-18 | 53510504 | Access | 0 | Foreman | 95 | 2 | HR |  |  | 95 | 0 | 190 | 24.7 | 214.7 | 2020-09-16 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hauling material that was already on site to stockpile via the 300JD and the Dozer | 5 | C076-C116 | Cook Lake | 0 | 44096 |  | 36 | 44096 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting486720200916-18Foreman2190 | Corbiere and Sons Contracting486720200916-18Foreman2190Inv#055 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 190 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4867 | 20200916-18 | 53510504 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2020-09-16 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hauling material that was already on site to stockpile via the 300JD and the Dozer | 5 | C076-C116 | Cook Lake | 0 | 44096 |  | 36 | 44096 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting486720200916-18L.O.A.4840 | Corbiere and Sons Contracting486720200916-18L.O.A.4840Inv#055 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4867 | 20200916-18 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 23 | HR |  |  | 75 | 0 | 1725 | 224.25 | 1949.25 | 2020-09-16 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hauling material that was already on site to stockpile via the 300JD and the Dozer | 5 | C076-C116 | Cook Lake | 0 | 44096 |  | 36 | 44096 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting486720200916-18Operator - Principle - After Jan 10231725 | Corbiere and Sons Contracting486720200916-18Operator - Principle - After Jan 10231725Inv#055 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4867 | 20200916-18 | 53510504 | Access | 0 | Labourer - General - After Jan 10 | 60 | 11.5 | HR |  |  | 60 | 0 | 690 | 89.7 | 779.7 | 2020-09-16 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hauling material that was already on site to stockpile via the 300JD and the Dozer | 5 | C076-C116 | Cook Lake | 0 | 44096 |  | 36 | 44096 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting486720200916-18Labourer - General - After Jan 1011.5690 | Corbiere and Sons Contracting486720200916-18Labourer - General - After Jan 1011.5690Inv#055 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 690 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4899 | 20200917-16 | 53510504 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10.5 | Dynamic | 98.61 | 0 |  |  | 1380.54 | 179.4702 | 1560.0102 | 2020-09-17 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Loading rock trucks all day, spreading gravel, hauling from stock pile | 5 | C050-C069 | Antler Lake | 0 | 44096 |  | 36 | 44098 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting489920200917-16Dozer D6 or equal- After Jan 1010.51380.54 | Corbiere and Sons Contracting489920200917-16Dozer D6 or equal- After Jan 1010.51380.54Inv#055 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1380.54 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4899 | 20200917-16 | 53510504 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10.5 | Dynamic | 103.84 | 0 |  |  | 1453.725 | 188.9843 | 1642.7093 | 2020-09-17 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Loading rock trucks all day, spreading gravel, hauling from stock pile | 5 | C050-C069 | Antler Lake | 0 | 44096 |  | 36 | 44098 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting489920200917-16Excavator - 30 ton- After Jan 1010.51453.725 | Corbiere and Sons Contracting489920200917-16Excavator - 30 ton- After Jan 1010.51453.725Inv#055 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1453.725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4899 | 20200917-16 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2020-09-17 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Loading rock trucks all day, spreading gravel, hauling from stock pile | 5 | C050-C069 | Antler Lake | 0 | 44096 |  | 36 | 44098 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting489920200917-16Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting489920200917-16Light Truck - Pick up- After Jan 103731.25Inv#055 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 731.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4899 | 20200917-16 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 18 | Dynamic | 103.54 | 0 |  |  | 2484.9 | 323.037 | 2807.937 | 2020-09-17 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Loading rock trucks all day, spreading gravel, hauling from stock pile | 5 | C050-C069 | Antler Lake | 0 | 44096 |  | 36 | 44098 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting489920200917-16Rock Truck - 30 Ton- After Jan 10182484.9 | Corbiere and Sons Contracting489920200917-16Rock Truck - 30 Ton- After Jan 10182484.9Inv#055 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 2484.9 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4899 | 20200917-16 | 53510504 | Access | 0 | Foreman | 95 | 4 | HR |  |  | 95 | 0 | 380 | 49.4 | 429.4 | 2020-09-17 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Loading rock trucks all day, spreading gravel, hauling from stock pile | 5 | C050-C069 | Antler Lake | 0 | 44096 |  | 36 | 44098 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting489920200917-16Foreman4380 | Corbiere and Sons Contracting489920200917-16Foreman4380Inv#055 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4899 | 20200917-16 | 53510504 | Access | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2020-09-17 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Loading rock trucks all day, spreading gravel, hauling from stock pile | 5 | C050-C069 | Antler Lake | 0 | 44096 |  | 36 | 44098 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting489920200917-16L.O.A.51050 | Corbiere and Sons Contracting489920200917-16L.O.A.51050Inv#055 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4899 | 20200917-16 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 23 | HR |  |  | 75 | 0 | 1725 | 224.25 | 1949.25 | 2020-09-17 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Loading rock trucks all day, spreading gravel, hauling from stock pile | 5 | C050-C069 | Antler Lake | 0 | 44096 |  | 36 | 44098 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting489920200917-16Operator - Principle - After Jan 10231725 | Corbiere and Sons Contracting489920200917-16Operator - Principle - After Jan 10231725Inv#055 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4899 | 20200917-16 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 22 | HR |  |  | 70 | 0 | 1540 | 200.2 | 1740.2 | 2020-09-17 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Loading rock trucks all day, spreading gravel, hauling from stock pile | 5 | C050-C069 | Antler Lake | 0 | 44096 |  | 36 | 44098 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting489920200917-16Driver - AZ - After Jan 10221540 | Corbiere and Sons Contracting489920200917-16Driver - AZ - After Jan 10221540Inv#055 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1540 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4900 | 20200917-17 | 53510502 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10.5 | Dynamic | 110.22 | 0 |  |  | 1543.08 | 200.6004 | 1743.6804 | 2020-09-17 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ran rock hammer all day | 5 | C050-C069 | Antler Lake | 0 | 44096 |  | 36 | 44098 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting490020200917-17Excavator - 36 ton- After Jan 1010.51543.08 | Corbiere and Sons Contracting490020200917-17Excavator - 36 ton- After Jan 1010.51543.08Inv#055 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 1543.08 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4900 | 20200917-17 | 53510502 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 10.5 | HR | 47.54 | 0 |  |  | 665.49 | 86.5137 | 752.0037 | 2020-09-17 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ran rock hammer all day | 5 | C050-C069 | Antler Lake | 0 | 44096 |  | 36 | 44098 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting490020200917-17Excavator Hammer - 30 - 50 ton- After Jan 1010.5665.49 | Corbiere and Sons Contracting490020200917-17Excavator Hammer - 30 - 50 ton- After Jan 1010.5665.49Inv#055 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 665.49 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4900 | 20200917-17 | 53510502 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-09-17 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ran rock hammer all day | 5 | C050-C069 | Antler Lake | 0 | 44096 |  | 36 | 44098 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting490020200917-17Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting490020200917-17Light Truck - Pick up- After Jan 101243.75Inv#055 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4900 | 20200917-17 | 53510502 | Access | 0 | Foreman | 95 | 2 | HR |  |  | 95 | 0 | 190 | 24.7 | 214.7 | 2020-09-17 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ran rock hammer all day | 5 | C050-C069 | Antler Lake | 0 | 44096 |  | 36 | 44098 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting490020200917-17Foreman2190 | Corbiere and Sons Contracting490020200917-17Foreman2190Inv#055 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 190 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4900 | 20200917-17 | 53510502 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-09-17 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ran rock hammer all day | 5 | C050-C069 | Antler Lake | 0 | 44096 |  | 36 | 44098 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting490020200917-17L.O.A.1210 | Corbiere and Sons Contracting490020200917-17L.O.A.1210Inv#055 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4900 | 20200917-17 | 53510502 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-09-17 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ran rock hammer all day | 5 | C050-C069 | Antler Lake | 0 | 44096 |  | 36 | 44098 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting490020200917-17Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting490020200917-17Operator - Principle - After Jan 1011.5862.5Inv#055 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4909 | 20200917-22 | 53510212 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 16 | Dynamic | 110.22 | 0 |  |  | 2351.36 | 305.6768 | 2657.0368 | 2020-09-17 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-02 and EX-09 built road down to B-064. | 2 | B054 - B064 | Lofty Davies | 0 | 44096 |  | 37 | 44097 | [5 empty] | Harold Furlong | 02 | Corbiere and Sons Contracting490920200917-22Excavator - 36 ton- After Jan 10162351.36 | Corbiere and Sons Contracting490920200917-22Excavator - 36 ton- After Jan 10162351.36Inv#055 | [5 empty] | 1 | 2351.36 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4909 | 20200917-22 | 53510212 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 16 | HR | 9.16 | 0 |  |  | 195.36 | 25.3968 | 220.7568 | 2020-09-17 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-02 and EX-09 built road down to B-064. | 2 | B054 - B064 | Lofty Davies | 0 | 44096 |  | 37 | 44097 | [5 empty] | Harold Furlong | 02 | Corbiere and Sons Contracting490920200917-22Excavator Thumb - 30 - 50 ton- After Jan 1016195.36 | Corbiere and Sons Contracting490920200917-22Excavator Thumb - 30 - 50 ton- After Jan 1016195.36Inv#055 | [5 empty] | 1 | 195.36 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4909 | 20200917-22 | 53510212 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 |  |  |  | 243.75 | 31.6875 | 275.4375 | 2020-09-17 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-02 and EX-09 built road down to B-064. | 2 | B054 - B064 | Lofty Davies | 0 | 44096 |  | 37 | 44097 | [5 empty] | Harold Furlong | 02 | Corbiere and Sons Contracting490920200917-22Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting490920200917-22Light Truck - Pick up- After Jan 101243.75Inv#055 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4909 | 20200917-22 | 53510212 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 22 | HR |  |  | 75 | 0 | 1650 | 214.5 | 1864.5 | 2020-09-17 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-02 and EX-09 built road down to B-064. | 2 | B054 - B064 | Lofty Davies | 0 | 44096 |  | 37 | 44097 | [5 empty] | Harold Furlong | 02 | Corbiere and Sons Contracting490920200917-22Operator - Principle - After Jan 10221650 | Corbiere and Sons Contracting490920200917-22Operator - Principle - After Jan 10221650Inv#055 | [5 empty] | 1 | 1650 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4977 | 20200918-22 | 53510504 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10.5 | Dynamic | 98.61 | 0 |  |  | 1380.54 | 179.4702 | 1560.0102 | 2020-09-18 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | DZ spreading gravel towards C-051, loading rock trucks all day from stockpile | 5 | C050-C069 | Antler Lake | 0 | 44098 |  | 36 | 44099 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting497720200918-22Dozer D6 or equal- After Jan 1010.51380.54 | Corbiere and Sons Contracting497720200918-22Dozer D6 or equal- After Jan 1010.51380.54Inv#055 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1380.54 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4977 | 20200918-22 | 53510504 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10.5 | Dynamic | 103.84 | 0 |  |  | 1453.725 | 188.9843 | 1642.7093 | 2020-09-18 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | DZ spreading gravel towards C-051, loading rock trucks all day from stockpile | 5 | C050-C069 | Antler Lake | 0 | 44098 |  | 36 | 44099 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting497720200918-22Excavator - 30 ton- After Jan 1010.51453.725 | Corbiere and Sons Contracting497720200918-22Excavator - 30 ton- After Jan 1010.51453.725Inv#055 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1453.725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4977 | 20200918-22 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-09-18 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | DZ spreading gravel towards C-051, loading rock trucks all day from stockpile | 5 | C050-C069 | Antler Lake | 0 | 44098 |  | 36 | 44099 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting497720200918-22Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting497720200918-22Light Truck - Pick up- After Jan 102487.5Inv#055 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4977 | 20200918-22 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 21 | Dynamic | 103.54 | 0 |  |  | 2899.05 | 376.8765 | 3275.9265 | 2020-09-18 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | DZ spreading gravel towards C-051, loading rock trucks all day from stockpile | 5 | C050-C069 | Antler Lake | 0 | 44098 |  | 36 | 44099 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting497720200918-22Rock Truck - 30 Ton- After Jan 10212899.05 | Corbiere and Sons Contracting497720200918-22Rock Truck - 30 Ton- After Jan 10212899.05Inv#055 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 2899.05 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4977 | 20200918-22 | 53510504 | Access | 0 | Foreman | 95 | 4 | HR |  |  | 95 | 0 | 380 | 49.4 | 429.4 | 2020-09-18 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | DZ spreading gravel towards C-051, loading rock trucks all day from stockpile | 5 | C050-C069 | Antler Lake | 0 | 44098 |  | 36 | 44099 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting497720200918-22Foreman4380 | Corbiere and Sons Contracting497720200918-22Foreman4380Inv#055 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4977 | 20200918-22 | 53510504 | Access | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2020-09-18 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | DZ spreading gravel towards C-051, loading rock trucks all day from stockpile | 5 | C050-C069 | Antler Lake | 0 | 44098 |  | 36 | 44099 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting497720200918-22L.O.A.51050 | Corbiere and Sons Contracting497720200918-22L.O.A.51050Inv#055 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4977 | 20200918-22 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 23 | HR |  |  | 75 | 0 | 1725 | 224.25 | 1949.25 | 2020-09-18 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | DZ spreading gravel towards C-051, loading rock trucks all day from stockpile | 5 | C050-C069 | Antler Lake | 0 | 44098 |  | 36 | 44099 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting497720200918-22Operator - Principle - After Jan 10231725 | Corbiere and Sons Contracting497720200918-22Operator - Principle - After Jan 10231725Inv#055 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4977 | 20200918-22 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 23 | HR |  |  | 70 | 0 | 1610 | 209.3 | 1819.3 | 2020-09-18 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | DZ spreading gravel towards C-051, loading rock trucks all day from stockpile | 5 | C050-C069 | Antler Lake | 0 | 44098 |  | 36 | 44099 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting497720200918-22Driver - AZ - After Jan 10231610 | Corbiere and Sons Contracting497720200918-22Driver - AZ - After Jan 10231610Inv#055 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1610 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4979 | 20200918-24 | 53510502 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10.5 | Dynamic | 110.22 | 0 |  |  | 1543.08 | 200.6004 | 1743.6804 | 2020-09-18 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock hammer all day establishing ditches and hammering knobs | 5 | C050-C069 | Antler Lake | 0 | 44098 |  | 36 | 44099 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting497920200918-24Excavator - 36 ton- After Jan 1010.51543.08 | Corbiere and Sons Contracting497920200918-24Excavator - 36 ton- After Jan 1010.51543.08Inv#055 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 1543.08 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4979 | 20200918-24 | 53510502 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 10.5 | HR | 47.54 | 0 |  |  | 665.49 | 86.5137 | 752.0037 | 2020-09-18 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock hammer all day establishing ditches and hammering knobs | 5 | C050-C069 | Antler Lake | 0 | 44098 |  | 36 | 44099 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting497920200918-24Excavator Hammer - 30 - 50 ton- After Jan 1010.5665.49 | Corbiere and Sons Contracting497920200918-24Excavator Hammer - 30 - 50 ton- After Jan 1010.5665.49Inv#055 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 665.49 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4979 | 20200918-24 | 53510502 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-09-18 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock hammer all day establishing ditches and hammering knobs | 5 | C050-C069 | Antler Lake | 0 | 44098 |  | 36 | 44099 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting497920200918-24Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting497920200918-24Light Truck - Pick up- After Jan 101243.75Inv#055 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4979 | 20200918-24 | 53510502 | Access | 0 | Foreman | 95 | 2 | HR |  |  | 95 | 0 | 190 | 24.7 | 214.7 | 2020-09-18 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock hammer all day establishing ditches and hammering knobs | 5 | C050-C069 | Antler Lake | 0 | 44098 |  | 36 | 44099 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting497920200918-24Foreman2190 | Corbiere and Sons Contracting497920200918-24Foreman2190Inv#055 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 190 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4979 | 20200918-24 | 53510502 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-09-18 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock hammer all day establishing ditches and hammering knobs | 5 | C050-C069 | Antler Lake | 0 | 44098 |  | 36 | 44099 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting497920200918-24L.O.A.1210 | Corbiere and Sons Contracting497920200918-24L.O.A.1210Inv#055 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4979 | 20200918-24 | 53510502 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-09-18 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock hammer all day establishing ditches and hammering knobs | 5 | C050-C069 | Antler Lake | 0 | 44098 |  | 36 | 44099 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting497920200918-24Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting497920200918-24Operator - Principle - After Jan 1011.5862.5Inv#055 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4980 | 20200918-25 | 53510503 | Access | 0 | Skidder | 171 | 4 | HR | 128.25 | 0 |  |  | 684 | 88.92 | 772.92 | 2020-09-18 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brought wood to wetland area for corduroy. | 5 | C050-C069 | Antler Lake | 0 | 44098 |  | 36 | 44099 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting498020200918-25Skidder 4684 | Corbiere and Sons Contracting498020200918-25Skidder 4684Inv#055 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 684 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4980 | 20200918-25 | 53510503 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-09-18 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brought wood to wetland area for corduroy. | 5 | C050-C069 | Antler Lake | 0 | 44098 |  | 36 | 44099 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting498020200918-25L.O.A.1210 | Corbiere and Sons Contracting498020200918-25L.O.A.1210Inv#055 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4980 | 20200918-25 | 53510503 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 4 | HR |  |  | 75 | 0 | 300 | 39 | 339 | 2020-09-18 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brought wood to wetland area for corduroy. | 5 | C050-C069 | Antler Lake | 0 | 44098 |  | 36 | 44099 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting498020200918-25Operator - Principle - After Jan 104300 | Corbiere and Sons Contracting498020200918-25Operator - Principle - After Jan 104300Inv#055 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4981 | 20200918-26-R1 | 53510212 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 20 | Dynamic | 110.22 | 0 |  |  | 2939.2 | 382.096 | 3321.296 | 2020-09-18 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-02 and EX-09 built road down to B-064. | 2 | B054 - B064 | Lofty Davies | 0 | 44098 |  | 37 | 44099 | [5 empty] | Harold Furlong | 02 | Corbiere and Sons Contracting498120200918-26-R1Excavator - 36 ton- After Jan 10202939.2 | Corbiere and Sons Contracting498120200918-26-R1Excavator - 36 ton- After Jan 10202939.2Inv#055 | [5 empty] | 1 | 2939.2 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4981 | 20200918-26-R1 | 53510212 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 20 | HR | 9.16 | 0 |  |  | 244.2 | 31.746 | 275.946 | 2020-09-18 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-02 and EX-09 built road down to B-064. | 2 | B054 - B064 | Lofty Davies | 0 | 44098 |  | 37 | 44099 | [5 empty] | Harold Furlong | 02 | Corbiere and Sons Contracting498120200918-26-R1Excavator Thumb - 30 - 50 ton- After Jan 1020244.2 | Corbiere and Sons Contracting498120200918-26-R1Excavator Thumb - 30 - 50 ton- After Jan 1020244.2Inv#055 | [5 empty] | 1 | 244.2 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4981 | 20200918-26-R1 | 53510212 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-09-18 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-02 and EX-09 built road down to B-064. | 2 | B054 - B064 | Lofty Davies | 0 | 44098 |  | 37 | 44099 | [5 empty] | Harold Furlong | 02 | Corbiere and Sons Contracting498120200918-26-R1Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting498120200918-26-R1Light Truck - Pick up- After Jan 101243.75Inv#055 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4981 | 20200918-26-R1 | 53510212 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 22 | HR |  |  | 75 | 0 | 1650 | 214.5 | 1864.5 | 2020-09-18 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-02 and EX-09 built road down to B-064. | 2 | B054 - B064 | Lofty Davies | 0 | 44098 |  | 37 | 44099 | [5 empty] | Harold Furlong | 02 | Corbiere and Sons Contracting498120200918-26-R1Operator - Principle - After Jan 10221650 | Corbiere and Sons Contracting498120200918-26-R1Operator - Principle - After Jan 10221650Inv#055 | [5 empty] | 1 | 1650 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4929 | 20200918-9 | 53510504 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10.5 | Dynamic | 98.61 | 0 |  |  | 1380.54 | 179.4702 | 1560.0102 | 2020-09-18 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock trucks worked all day via 330 CAT and Dozer - John Schroder completed orienation in the morning. | 5 | C076-C116 | Cook Lake | 0 | 44097 |  | 36 | 44098 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting492920200918-9Dozer D6 or equal- After Jan 1010.51380.54 | Corbiere and Sons Contracting492920200918-9Dozer D6 or equal- After Jan 1010.51380.54Inv#055 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1380.54 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4929 | 20200918-9 | 53510504 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10.5 | Dynamic | 110.22 | 0 |  |  | 1543.08 | 200.6004 | 1743.6804 | 2020-09-18 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock trucks worked all day via 330 CAT and Dozer - John Schroder completed orienation in the morning. | 5 | C076-C116 | Cook Lake | 0 | 44097 |  | 36 | 44098 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting492920200918-9Excavator - 36 ton- After Jan 1010.51543.08 | Corbiere and Sons Contracting492920200918-9Excavator - 36 ton- After Jan 1010.51543.08Inv#055 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1543.08 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4929 | 20200918-9 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-09-18 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock trucks worked all day via 330 CAT and Dozer - John Schroder completed orienation in the morning. | 5 | C076-C116 | Cook Lake | 0 | 44097 |  | 36 | 44098 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting492920200918-9Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting492920200918-9Light Truck - Pick up- After Jan 102487.5Inv#055 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4929 | 20200918-9 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 16 | Dynamic | 103.54 | 0 |  |  | 2208.8 | 287.144 | 2495.944 | 2020-09-18 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock trucks worked all day via 330 CAT and Dozer - John Schroder completed orienation in the morning. | 5 | C076-C116 | Cook Lake | 0 | 44097 |  | 36 | 44098 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting492920200918-9Rock Truck - 30 Ton- After Jan 10162208.8 | Corbiere and Sons Contracting492920200918-9Rock Truck - 30 Ton- After Jan 10162208.8Inv#055 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 2208.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4929 | 20200918-9 | 53510504 | Access | 0 | Foreman | 95 | 4 | HR |  |  | 95 | 0 | 380 | 49.4 | 429.4 | 2020-09-18 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock trucks worked all day via 330 CAT and Dozer - John Schroder completed orienation in the morning. | 5 | C076-C116 | Cook Lake | 0 | 44097 |  | 36 | 44098 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting492920200918-9Foreman4380 | Corbiere and Sons Contracting492920200918-9Foreman4380Inv#055 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4929 | 20200918-9 | 53510504 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2020-09-18 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock trucks worked all day via 330 CAT and Dozer - John Schroder completed orienation in the morning. | 5 | C076-C116 | Cook Lake | 0 | 44097 |  | 36 | 44098 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting492920200918-9L.O.A.4840 | Corbiere and Sons Contracting492920200918-9L.O.A.4840Inv#055 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4929 | 20200918-9 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 23 | HR |  |  | 75 | 0 | 1725 | 224.25 | 1949.25 | 2020-09-18 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock trucks worked all day via 330 CAT and Dozer - John Schroder completed orienation in the morning. | 5 | C076-C116 | Cook Lake | 0 | 44097 |  | 36 | 44098 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting492920200918-9Operator - Principle - After Jan 10231725 | Corbiere and Sons Contracting492920200918-9Operator - Principle - After Jan 10231725Inv#055 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4929 | 20200918-9 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 18 | HR |  |  | 70 | 0 | 1260 | 163.8 | 1423.8 | 2020-09-18 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock trucks worked all day via 330 CAT and Dozer - John Schroder completed orienation in the morning. | 5 | C076-C116 | Cook Lake | 0 | 44097 |  | 36 | 44098 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting492920200918-9Driver - AZ - After Jan 10181260 | Corbiere and Sons Contracting492920200918-9Driver - AZ - After Jan 10181260Inv#055 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5060 | 20200919-10 | 53510503 | Access | 0 | Feller Buncher | 240 | 6 | HR | 180 | 0 |  |  | 1440 | 187.2 | 1627.2 | 2020-09-19 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Corduroyrf 75 meters of wetland and put mats down over creek | 5 | C070 - C075 | Antler Lake | 0 | 44097 |  | 36 | 44099 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting506020200919-10Feller Buncher61440 | Corbiere and Sons Contracting506020200919-10Feller Buncher61440Inv#055 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 1440 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5060 | 20200919-10 | 53510503 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-09-19 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Corduroyrf 75 meters of wetland and put mats down over creek | 5 | C070 - C075 | Antler Lake | 0 | 44097 |  | 36 | 44099 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting506020200919-10L.O.A.1210 | Corbiere and Sons Contracting506020200919-10L.O.A.1210Inv#055 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5060 | 20200919-10 | 53510503 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 75 | 0 | 450 | 58.5 | 508.5 | 2020-09-19 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Corduroyrf 75 meters of wetland and put mats down over creek | 5 | C070 - C075 | Antler Lake | 0 | 44097 |  | 36 | 44099 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting506020200919-10Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting506020200919-10Operator - Principle - After Jan 106450Inv#055 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4999 | 20200919-12 | 53510502 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10.5 | Dynamic | 110.22 | 0 |  |  | 1543.08 | 200.6004 | 1743.6804 | 2020-09-19 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock hammer establishing ditches and hammering knobs | 5 | 050-069 | Antler Lake | 0 | 44098 |  | 36 | 44099 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting499920200919-12Excavator - 36 ton- After Jan 1010.51543.08 | Corbiere and Sons Contracting499920200919-12Excavator - 36 ton- After Jan 1010.51543.08Inv#055 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 1543.08 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4999 | 20200919-12 | 53510502 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 10.5 | HR | 47.54 | 0 |  |  | 665.49 | 86.5137 | 752.0037 | 2020-09-19 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock hammer establishing ditches and hammering knobs | 5 | 050-069 | Antler Lake | 0 | 44098 |  | 36 | 44099 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting499920200919-12Excavator Hammer - 30 - 50 ton- After Jan 1010.5665.49 | Corbiere and Sons Contracting499920200919-12Excavator Hammer - 30 - 50 ton- After Jan 1010.5665.49Inv#055 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 665.49 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4999 | 20200919-12 | 53510502 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-09-19 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock hammer establishing ditches and hammering knobs | 5 | 050-069 | Antler Lake | 0 | 44098 |  | 36 | 44099 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting499920200919-12Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting499920200919-12Light Truck - Pick up- After Jan 101243.75Inv#055 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4999 | 20200919-12 | 53510502 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-09-19 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock hammer establishing ditches and hammering knobs | 5 | 050-069 | Antler Lake | 0 | 44098 |  | 36 | 44099 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting499920200919-12L.O.A.1210 | Corbiere and Sons Contracting499920200919-12L.O.A.1210Inv#055 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4999 | 20200919-12 | 53510502 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-09-19 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock hammer establishing ditches and hammering knobs | 5 | 050-069 | Antler Lake | 0 | 44098 |  | 36 | 44099 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting499920200919-12Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting499920200919-12Operator - Principle - After Jan 1011.5862.5Inv#055 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5001 | 20200919-14 | 53510504 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10.5 | Dynamic | 98.61 | 0 |  |  | 1380.54 | 179.4702 | 1560.0102 | 2020-09-19 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock trucks worked all day via 336 CAT and DZR | 5 | C076-C116 | Cook Lake | 0 | 44098 |  | 36 | 44099 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting500120200919-14Dozer D6 or equal- After Jan 1010.51380.54 | Corbiere and Sons Contracting500120200919-14Dozer D6 or equal- After Jan 1010.51380.54Inv#055 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1380.54 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5001 | 20200919-14 | 53510504 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10.5 | Dynamic | 110.22 | 0 |  |  | 1543.08 | 200.6004 | 1743.6804 | 2020-09-19 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock trucks worked all day via 336 CAT and DZR | 5 | C076-C116 | Cook Lake | 0 | 44098 |  | 36 | 44099 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting500120200919-14Excavator - 36 ton- After Jan 1010.51543.08 | Corbiere and Sons Contracting500120200919-14Excavator - 36 ton- After Jan 1010.51543.08Inv#055 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1543.08 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5001 | 20200919-14 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-09-19 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock trucks worked all day via 336 CAT and DZR | 5 | C076-C116 | Cook Lake | 0 | 44098 |  | 36 | 44099 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting500120200919-14Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting500120200919-14Light Truck - Pick up- After Jan 102487.5Inv#055 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5001 | 20200919-14 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 21 | Dynamic | 103.54 | 0 |  |  | 2899.05 | 376.8765 | 3275.9265 | 2020-09-19 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock trucks worked all day via 336 CAT and DZR | 5 | C076-C116 | Cook Lake | 0 | 44098 |  | 36 | 44099 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting500120200919-14Rock Truck - 30 Ton- After Jan 10212899.05 | Corbiere and Sons Contracting500120200919-14Rock Truck - 30 Ton- After Jan 10212899.05Inv#055 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 2899.05 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5001 | 20200919-14 | 53510504 | Access | 0 | Foreman | 95 | 3 | HR |  |  | 95 | 0 | 285 | 37.05 | 322.05 | 2020-09-19 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock trucks worked all day via 336 CAT and DZR | 5 | C076-C116 | Cook Lake | 0 | 44098 |  | 36 | 44099 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting500120200919-14Foreman3285 | Corbiere and Sons Contracting500120200919-14Foreman3285Inv#055 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 285 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5001 | 20200919-14 | 53510504 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2020-09-19 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock trucks worked all day via 336 CAT and DZR | 5 | C076-C116 | Cook Lake | 0 | 44098 |  | 36 | 44099 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting500120200919-14L.O.A.4840 | Corbiere and Sons Contracting500120200919-14L.O.A.4840Inv#055 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5001 | 20200919-14 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 23 | HR |  |  | 75 | 0 | 1725 | 224.25 | 1949.25 | 2020-09-19 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock trucks worked all day via 336 CAT and DZR | 5 | C076-C116 | Cook Lake | 0 | 44098 |  | 36 | 44099 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting500120200919-14Operator - Principle - After Jan 10231725 | Corbiere and Sons Contracting500120200919-14Operator - Principle - After Jan 10231725Inv#055 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5001 | 20200919-14 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 23 | HR |  |  | 70 | 0 | 1610 | 209.3 | 1819.3 | 2020-09-19 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock trucks worked all day via 336 CAT and DZR | 5 | C076-C116 | Cook Lake | 0 | 44098 |  | 36 | 44099 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting500120200919-14Driver - AZ - After Jan 10231610 | Corbiere and Sons Contracting500120200919-14Driver - AZ - After Jan 10231610Inv#055 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1610 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5002 | 20200919-15 | 53510502 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9.5 | Dynamic | 103.84 | 0 |  |  | 1315.275 | 170.9857 | 1486.2607 | 2020-09-19 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock hammer until 4:30 when track came off | 5 | C076-C116 | Cook Lake | 0 | 44098 |  | 36 | 44099 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting500220200919-15Excavator - 30 ton- After Jan 109.51315.275 | Corbiere and Sons Contracting500220200919-15Excavator - 30 ton- After Jan 109.51315.275Inv#055 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 1315.275 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5002 | 20200919-15 | 53510502 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 9.5 | HR | 47.54 | 0 |  |  | 602.11 | 78.2743 | 680.3843 | 2020-09-19 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock hammer until 4:30 when track came off | 5 | C076-C116 | Cook Lake | 0 | 44098 |  | 36 | 44099 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting500220200919-15Excavator Hammer - 30 - 50 ton- After Jan 109.5602.11 | Corbiere and Sons Contracting500220200919-15Excavator Hammer - 30 - 50 ton- After Jan 109.5602.11Inv#055 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 602.11 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5002 | 20200919-15 | 53510502 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-09-19 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock hammer until 4:30 when track came off | 5 | C076-C116 | Cook Lake | 0 | 44098 |  | 36 | 44099 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting500220200919-15Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting500220200919-15Light Truck - Pick up- After Jan 101243.75Inv#055 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5002 | 20200919-15 | 53510502 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-09-19 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock hammer until 4:30 when track came off | 5 | C076-C116 | Cook Lake | 0 | 44098 |  | 36 | 44099 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting500220200919-15L.O.A.1210 | Corbiere and Sons Contracting500220200919-15L.O.A.1210Inv#055 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5002 | 20200919-15 | 53510502 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 10 | HR |  |  | 75 | 0 | 750 | 97.5 | 847.5 | 2020-09-19 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock hammer until 4:30 when track came off | 5 | C076-C116 | Cook Lake | 0 | 44098 |  | 36 | 44099 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting500220200919-15Operator - Principle - After Jan 1010750 | Corbiere and Sons Contracting500220200919-15Operator - Principle - After Jan 1010750Inv#055 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 750 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5011 | 20200919-23 | 53510212 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10 | Dynamic | 110.22 | 0 |  |  | 1469.6 | 191.048 | 1660.648 | 2020-09-19 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Built road down to B-064 and rained out. | 2 | B054 - B064 | Lofty Davies | 0 | 44099 |  | 37 | 44100 | [5 empty] | Harold Furlong | 02 | Corbiere and Sons Contracting501120200919-23Excavator - 36 ton- After Jan 10101469.6 | Corbiere and Sons Contracting501120200919-23Excavator - 36 ton- After Jan 10101469.6Inv#055 | [5 empty] | 1 | 1469.6 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5011 | 20200919-23 | 53510212 | Access | 0 | Excavator Thumb - 8 -20 ton- After Jan 10 | 8.76 | 10 | HR | 6.57 | 0 |  |  | 87.6 | 11.388 | 98.988 | 2020-09-19 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Built road down to B-064 and rained out. | 2 | B054 - B064 | Lofty Davies | 0 | 44099 |  | 37 | 44100 | [5 empty] | Harold Furlong | 02 | Corbiere and Sons Contracting501120200919-23Excavator Thumb - 8 -20 ton- After Jan 101087.6 | Corbiere and Sons Contracting501120200919-23Excavator Thumb - 8 -20 ton- After Jan 101087.6Inv#055 | [5 empty] | 1 | 87.6 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5011 | 20200919-23 | 53510212 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-09-19 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Built road down to B-064 and rained out. | 2 | B054 - B064 | Lofty Davies | 0 | 44099 |  | 37 | 44100 | [5 empty] | Harold Furlong | 02 | Corbiere and Sons Contracting501120200919-23Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting501120200919-23Light Truck - Pick up- After Jan 101243.75Inv#055 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5011 | 20200919-23 | 53510212 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 10 | HR |  |  | 75 | 0 | 750 | 97.5 | 847.5 | 2020-09-19 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Built road down to B-064 and rained out. | 2 | B054 - B064 | Lofty Davies | 0 | 44099 |  | 37 | 44100 | [5 empty] | Harold Furlong | 02 | Corbiere and Sons Contracting501120200919-23Operator - Principle - After Jan 1010750 | Corbiere and Sons Contracting501120200919-23Operator - Principle - After Jan 1010750Inv#055 | [5 empty] | 1 | 750 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6172 | 20200919-28 | 53510504 | Access | 0 | L.O.A. | 210 | 8 | DAY |  |  |  | 0 | 1680 | 218.4 | 1898.4 | 2020-09-19 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | (8) Charges of LOA for Taranis trucks that we have retained as no gravel was needed this day. | 5 | C076-C116 | Cook Lake | 0 | 44136 |  | 51 | 44136 | [5 empty] | Betty Moghrabi | 05 | Corbiere and Sons Contracting617220200919-28L.O.A.81680 | Corbiere and Sons Contracting617220200919-28L.O.A.81680Inv#070 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1680 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4996 | 20200919-8 | 53510504 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 4 | Dynamic | 98.61 | 0 |  |  | 525.92 | 68.3696 | 594.2896 | 2020-09-19 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Loaded trucks, spreaded gravel, hauling gravel | 5 | C050-C069 | Antler Lake | 0 | 44098 |  | 36 | 44099 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting499620200919-8Dozer D6 or equal- After Jan 104525.92 | Corbiere and Sons Contracting499620200919-8Dozer D6 or equal- After Jan 104525.92Inv#055 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 525.92 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4996 | 20200919-8 | 53510504 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 4 | Dynamic | 103.84 | 0 |  |  | 553.8 | 71.994 | 625.794 | 2020-09-19 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Loaded trucks, spreaded gravel, hauling gravel | 5 | C050-C069 | Antler Lake | 0 | 44098 |  | 36 | 44099 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting499620200919-8Excavator - 30 ton- After Jan 104553.8 | Corbiere and Sons Contracting499620200919-8Excavator - 30 ton- After Jan 104553.8Inv#055 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 553.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4996 | 20200919-8 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-09-19 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Loaded trucks, spreaded gravel, hauling gravel | 5 | C050-C069 | Antler Lake | 0 | 44098 |  | 36 | 44099 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting499620200919-8Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting499620200919-8Light Truck - Pick up- After Jan 102487.5Inv#055 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4996 | 20200919-8 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 8 | Dynamic | 103.54 | 0 |  |  | 1104.4 | 143.572 | 1247.972 | 2020-09-19 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Loaded trucks, spreaded gravel, hauling gravel | 5 | C050-C069 | Antler Lake | 0 | 44098 |  | 36 | 44099 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting499620200919-8Rock Truck - 30 Ton- After Jan 1081104.4 | Corbiere and Sons Contracting499620200919-8Rock Truck - 30 Ton- After Jan 1081104.4Inv#055 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1104.4 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4996 | 20200919-8 | 53510504 | Access | 0 | Foreman | 95 | 5 | HR |  |  | 95 | 0 | 475 | 61.75 | 536.75 | 2020-09-19 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Loaded trucks, spreaded gravel, hauling gravel | 5 | C050-C069 | Antler Lake | 0 | 44098 |  | 36 | 44099 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting499620200919-8Foreman5475 | Corbiere and Sons Contracting499620200919-8Foreman5475Inv#055 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 475 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4996 | 20200919-8 | 53510504 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2020-09-19 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Loaded trucks, spreaded gravel, hauling gravel | 5 | C050-C069 | Antler Lake | 0 | 44098 |  | 36 | 44099 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting499620200919-8L.O.A.3630 | Corbiere and Sons Contracting499620200919-8L.O.A.3630Inv#055 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4996 | 20200919-8 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 9 | HR |  |  | 75 | 0 | 675 | 87.75 | 762.75 | 2020-09-19 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Loaded trucks, spreaded gravel, hauling gravel | 5 | C050-C069 | Antler Lake | 0 | 44098 |  | 36 | 44099 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting499620200919-8Operator - Principle - After Jan 109675 | Corbiere and Sons Contracting499620200919-8Operator - Principle - After Jan 109675Inv#055 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 675 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 4996 | 20200919-8 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 9 | HR |  |  | 70 | 0 | 630 | 81.9 | 711.9 | 2020-09-19 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Loaded trucks, spreaded gravel, hauling gravel | 5 | C050-C069 | Antler Lake | 0 | 44098 |  | 36 | 44099 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting499620200919-8Driver - AZ - After Jan 109630 | Corbiere and Sons Contracting499620200919-8Driver - AZ - After Jan 109630Inv#055 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5026 | 20200920-11 | 53510512 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10.5 | Dynamic | 98.61 | 0 |  |  | 1380.54 | 179.4702 | 1560.0102 | 2020-09-20 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | DZ doing road maintenance all day at C-042 | 5 | C036-C049 | Pays Plat River | 0 | 44099 |  | 36 | 44100 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting502620200920-11Dozer D6 or equal- After Jan 1010.51380.54 | Corbiere and Sons Contracting502620200920-11Dozer D6 or equal- After Jan 1010.51380.54Inv#055 | [5 empty] | 1 | 1380.54 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5026 | 20200920-11 | 53510512 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-09-20 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | DZ doing road maintenance all day at C-042 | 5 | C036-C049 | Pays Plat River | 0 | 44099 |  | 36 | 44100 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting502620200920-11L.O.A.1210 | Corbiere and Sons Contracting502620200920-11L.O.A.1210Inv#055 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5026 | 20200920-11 | 53510512 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-09-20 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | DZ doing road maintenance all day at C-042 | 5 | C036-C049 | Pays Plat River | 0 | 44099 |  | 36 | 44100 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting502620200920-11Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting502620200920-11Operator - Principle - After Jan 1011.5862.5Inv#055 | [5 empty] | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5028 | 20200920-13 | 53510504 | Access | 0 | Loader JD 524 to 624 or equal | 99 | 5 | HR | 74.25 | 0 |  |  | 495 | 64.35 | 559.35 | 2020-09-20 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Loaded rock trucks, spot gravelling towards C-051 | 5 | C050-C069 | Antler Lake | 0 | 44099 |  | 36 | 44100 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting502820200920-13Loader JD 524 to 624 or equal5495 | Corbiere and Sons Contracting502820200920-13Loader JD 524 to 624 or equal5495Inv#055 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 495 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5028 | 20200920-13 | 53510504 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10.5 | Dynamic | 98.61 | 0 |  |  | 1380.54 | 179.4702 | 1560.0102 | 2020-09-20 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Loaded rock trucks, spot gravelling towards C-051 | 5 | C050-C069 | Antler Lake | 0 | 44099 |  | 36 | 44100 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting502820200920-13Dozer D6 or equal- After Jan 1010.51380.54 | Corbiere and Sons Contracting502820200920-13Dozer D6 or equal- After Jan 1010.51380.54Inv#055 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1380.54 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5028 | 20200920-13 | 53510504 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 5.5 | Dynamic | 110.22 | 0 |  |  | 808.28 | 105.0764 | 913.3564 | 2020-09-20 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Loaded rock trucks, spot gravelling towards C-051 | 5 | C050-C069 | Antler Lake | 0 | 44099 |  | 36 | 44100 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting502820200920-13Excavator - 36 ton- After Jan 105.5808.28 | Corbiere and Sons Contracting502820200920-13Excavator - 36 ton- After Jan 105.5808.28Inv#055 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 808.28 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5028 | 20200920-13 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2020-09-20 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Loaded rock trucks, spot gravelling towards C-051 | 5 | C050-C069 | Antler Lake | 0 | 44099 |  | 36 | 44100 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting502820200920-13Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting502820200920-13Light Truck - Pick up- After Jan 103731.25Inv#055 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 731.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5028 | 20200920-13 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 21 | Dynamic | 103.54 | 0 |  |  | 2899.05 | 376.8765 | 3275.9265 | 2020-09-20 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Loaded rock trucks, spot gravelling towards C-051 | 5 | C050-C069 | Antler Lake | 0 | 44099 |  | 36 | 44100 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting502820200920-13Rock Truck - 30 Ton- After Jan 10212899.05 | Corbiere and Sons Contracting502820200920-13Rock Truck - 30 Ton- After Jan 10212899.05Inv#055 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 2899.05 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5028 | 20200920-13 | 53510504 | Access | 0 | Foreman | 95 | 4 | HR |  |  | 95 | 0 | 380 | 49.4 | 429.4 | 2020-09-20 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Loaded rock trucks, spot gravelling towards C-051 | 5 | C050-C069 | Antler Lake | 0 | 44099 |  | 36 | 44100 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting502820200920-13Foreman4380 | Corbiere and Sons Contracting502820200920-13Foreman4380Inv#055 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5028 | 20200920-13 | 53510504 | Access | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2020-09-20 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Loaded rock trucks, spot gravelling towards C-051 | 5 | C050-C069 | Antler Lake | 0 | 44099 |  | 36 | 44100 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting502820200920-13L.O.A.61260 | Corbiere and Sons Contracting502820200920-13L.O.A.61260Inv#055 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5028 | 20200920-13 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 23 | HR |  |  | 75 | 0 | 1725 | 224.25 | 1949.25 | 2020-09-20 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Loaded rock trucks, spot gravelling towards C-051 | 5 | C050-C069 | Antler Lake | 0 | 44099 |  | 36 | 44100 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting502820200920-13Operator - Principle - After Jan 10231725 | Corbiere and Sons Contracting502820200920-13Operator - Principle - After Jan 10231725Inv#055 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5028 | 20200920-13 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 23 | HR |  |  | 70 | 0 | 1610 | 209.3 | 1819.3 | 2020-09-20 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Loaded rock trucks, spot gravelling towards C-051 | 5 | C050-C069 | Antler Lake | 0 | 44099 |  | 36 | 44100 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting502820200920-13Driver - AZ - After Jan 10231610 | Corbiere and Sons Contracting502820200920-13Driver - AZ - After Jan 10231610Inv#055 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1610 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5030 | 20200920-15 | 53510502 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10.5 | Dynamic | 110.22 | 0 |  |  | 1543.08 | 200.6004 | 1743.6804 | 2020-09-20 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | On Rock hammer establishing ditches and hammering knobs all day. | 5 | 050-069 | Antler Lake | 0 | 44099 |  | 36 | 44100 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting503020200920-15Excavator - 36 ton- After Jan 1010.51543.08 | Corbiere and Sons Contracting503020200920-15Excavator - 36 ton- After Jan 1010.51543.08Inv#055 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 1543.08 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5030 | 20200920-15 | 53510502 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 10.5 | HR | 47.54 | 0 |  |  | 665.49 | 86.5137 | 752.0037 | 2020-09-20 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | On Rock hammer establishing ditches and hammering knobs all day. | 5 | 050-069 | Antler Lake | 0 | 44099 |  | 36 | 44100 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting503020200920-15Excavator Hammer - 30 - 50 ton- After Jan 1010.5665.49 | Corbiere and Sons Contracting503020200920-15Excavator Hammer - 30 - 50 ton- After Jan 1010.5665.49Inv#055 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 665.49 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5030 | 20200920-15 | 53510502 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-09-20 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | On Rock hammer establishing ditches and hammering knobs all day. | 5 | 050-069 | Antler Lake | 0 | 44099 |  | 36 | 44100 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting503020200920-15Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting503020200920-15Light Truck - Pick up- After Jan 101243.75Inv#055 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5030 | 20200920-15 | 53510502 | Access | 0 | Foreman | 95 | 2 | HR |  |  | 95 | 0 | 190 | 24.7 | 214.7 | 2020-09-20 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | On Rock hammer establishing ditches and hammering knobs all day. | 5 | 050-069 | Antler Lake | 0 | 44099 |  | 36 | 44100 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting503020200920-15Foreman2190 | Corbiere and Sons Contracting503020200920-15Foreman2190Inv#055 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 190 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5030 | 20200920-15 | 53510502 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-09-20 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | On Rock hammer establishing ditches and hammering knobs all day. | 5 | 050-069 | Antler Lake | 0 | 44099 |  | 36 | 44100 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting503020200920-15L.O.A.1210 | Corbiere and Sons Contracting503020200920-15L.O.A.1210Inv#055 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5030 | 20200920-15 | 53510502 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-09-20 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | On Rock hammer establishing ditches and hammering knobs all day. | 5 | 050-069 | Antler Lake | 0 | 44099 |  | 36 | 44100 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting503020200920-15Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting503020200920-15Operator - Principle - After Jan 1011.5862.5Inv#055 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5031 | 20200920-16 | 53510504 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10.5 | Dynamic | 98.61 | 0 |  |  | 1380.54 | 179.4702 | 1560.0102 | 2020-09-20 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel haul, hauling material already on site in stockpile via the 300JD and dozer | 5 | C076-C116 | Cook Lake | 0 | 44099 |  | 36 | 44100 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting503120200920-16Dozer D6 or equal- After Jan 1010.51380.54 | Corbiere and Sons Contracting503120200920-16Dozer D6 or equal- After Jan 1010.51380.54Inv#055 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1380.54 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5031 | 20200920-16 | 53510504 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 13.5 | Dynamic | 110.22 | 0 |  |  | 1983.96 | 257.9148 | 2241.8748 | 2020-09-20 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel haul, hauling material already on site in stockpile via the 300JD and dozer | 5 | C076-C116 | Cook Lake | 0 | 44099 |  | 36 | 44100 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting503120200920-16Excavator - 36 ton- After Jan 1013.51983.96 | Corbiere and Sons Contracting503120200920-16Excavator - 36 ton- After Jan 1013.51983.96Inv#055 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1983.96 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5031 | 20200920-16 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-09-20 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel haul, hauling material already on site in stockpile via the 300JD and dozer | 5 | C076-C116 | Cook Lake | 0 | 44099 |  | 36 | 44100 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting503120200920-16Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting503120200920-16Light Truck - Pick up- After Jan 102487.5Inv#055 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5031 | 20200920-16 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 10.5 | Dynamic | 103.54 | 0 |  |  | 1449.525 | 188.4383 | 1637.9633 | 2020-09-20 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel haul, hauling material already on site in stockpile via the 300JD and dozer | 5 | C076-C116 | Cook Lake | 0 | 44099 |  | 36 | 44100 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting503120200920-16Rock Truck - 30 Ton- After Jan 1010.51449.525 | Corbiere and Sons Contracting503120200920-16Rock Truck - 30 Ton- After Jan 1010.51449.525Inv#055 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1449.525 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5031 | 20200920-16 | 53510504 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2020-09-20 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel haul, hauling material already on site in stockpile via the 300JD and dozer | 5 | C076-C116 | Cook Lake | 0 | 44099 |  | 36 | 44100 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting503120200920-16L.O.A.3630 | Corbiere and Sons Contracting503120200920-16L.O.A.3630Inv#055 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5031 | 20200920-16 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 27 | HR |  |  | 75 | 0 | 2025 | 263.25 | 2288.25 | 2020-09-20 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel haul, hauling material already on site in stockpile via the 300JD and dozer | 5 | C076-C116 | Cook Lake | 0 | 44099 |  | 36 | 44100 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting503120200920-16Operator - Principle - After Jan 10272025 | Corbiere and Sons Contracting503120200920-16Operator - Principle - After Jan 10272025Inv#055 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 2025 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5031 | 20200920-16 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 11.5 | HR |  |  | 70 | 0 | 805 | 104.65 | 909.65 | 2020-09-20 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel haul, hauling material already on site in stockpile via the 300JD and dozer | 5 | C076-C116 | Cook Lake | 0 | 44099 |  | 36 | 44100 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting503120200920-16Driver - AZ - After Jan 1011.5805 | Corbiere and Sons Contracting503120200920-16Driver - AZ - After Jan 1011.5805Inv#055 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 805 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5036 | 20200920-21 | 53510212 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 12 | Dynamic | 110.22 | 0 |  |  | 1763.52 | 229.2576 | 1992.7776 | 2020-09-20 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Built road down to B-064. | 2 | B054 - B064 | Lofty Davies | 0 | 44099 |  | 37 | 44100 | [5 empty] | Harold Furlong | 02 | Corbiere and Sons Contracting503620200920-21Excavator - 36 ton- After Jan 10121763.52 | Corbiere and Sons Contracting503620200920-21Excavator - 36 ton- After Jan 10121763.52Inv#055 | [5 empty] | 1 | 1763.52 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5036 | 20200920-21 | 53510212 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 12 | HR | 9.16 | 0 |  |  | 146.52 | 19.0476 | 165.5676 | 2020-09-20 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Built road down to B-064. | 2 | B054 - B064 | Lofty Davies | 0 | 44099 |  | 37 | 44100 | [5 empty] | Harold Furlong | 02 | Corbiere and Sons Contracting503620200920-21Excavator Thumb - 30 - 50 ton- After Jan 1012146.52 | Corbiere and Sons Contracting503620200920-21Excavator Thumb - 30 - 50 ton- After Jan 1012146.52Inv#055 | [5 empty] | 1 | 146.52 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5036 | 20200920-21 | 53510212 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-09-20 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Built road down to B-064. | 2 | B054 - B064 | Lofty Davies | 0 | 44099 |  | 37 | 44100 | [5 empty] | Harold Furlong | 02 | Corbiere and Sons Contracting503620200920-21Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting503620200920-21Light Truck - Pick up- After Jan 101243.75Inv#055 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5036 | 20200920-21 | 53510212 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2020-09-20 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Built road down to B-064. | 2 | B054 - B064 | Lofty Davies | 0 | 44099 |  | 37 | 44100 | [5 empty] | Harold Furlong | 02 | Corbiere and Sons Contracting503620200920-21Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting503620200920-21Operator - Principle - After Jan 1012900Inv#055 | [5 empty] | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6173 | 20200920-29 | 53510504 | Access | 0 | L.O.A. | 210 | 8 | DAY |  |  |  | 0 | 1680 | 218.4 | 1898.4 | 2020-09-20 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 8) charges of LOA for Taranis trucks as no gravel was required over the weekend. | 5 | C076-C116 | Cook Lake | 0 | 44136 |  | 51 | 44136 | [5 empty] | Betty Moghrabi | 05 | Corbiere and Sons Contracting617320200920-29L.O.A.81680 | Corbiere and Sons Contracting617320200920-29L.O.A.81680Inv#070 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1680 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5050 | 20200921-12 | 53510504 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 110.5 | Dynamic | 41.4 | 0 |  |  | 6099.6 | 792.948 | 6892.548 | 2020-09-21 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel hauling in WF5 to Antler Lake Rd | 5 | C050-C069 | Antler Lake | 0 | 44099 |  | 50 | 44101 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting505020200921-12Dump - Triaxle- After Jan 10110.56099.6 | Corbiere and Sons Contracting505020200921-12Dump - Triaxle- After Jan 10110.56099.6Inv#055 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 6099.6 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5050 | 20200921-12 | 53510504 | Access | 0 | L.O.A. | 210 | 11 | DAY |  |  |  | 0 | 2310 | 300.3 | 2610.3 | 2020-09-21 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel hauling in WF5 to Antler Lake Rd | 5 | C050-C069 | Antler Lake | 0 | 44099 |  | 50 | 44101 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting505020200921-12L.O.A.112310 | Corbiere and Sons Contracting505020200921-12L.O.A.112310Inv#055 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 2310 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5050 | 20200921-12 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 110.5 | HR |  |  | 70 | 0 | 7735 | 1005.55 | 8740.55 | 2020-09-21 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel hauling in WF5 to Antler Lake Rd | 5 | C050-C069 | Antler Lake | 0 | 44099 |  | 50 | 44101 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting505020200921-12Driver - AZ - After Jan 10110.57735 | Corbiere and Sons Contracting505020200921-12Driver - AZ - After Jan 10110.57735Inv#055 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 7735 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5055 | 20200921-17 | 53510312 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10 | Dynamic | 98.61 | 0 |  |  | 1314.8 | 170.924 | 1485.724 | 2020-09-21 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Tuned up road B-136 to B-142 | 3 | B136-B144 | Fire Hill Road Est | 0 | 44099 |  | 37 | 44100 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting505520200921-17Dozer D6 or equal- After Jan 10101314.8 | Corbiere and Sons Contracting505520200921-17Dozer D6 or equal- After Jan 10101314.8Inv#055 | [5 empty] | 1 | 1314.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5055 | 20200921-17 | 53510312 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-09-21 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Tuned up road B-136 to B-142 | 3 | B136-B144 | Fire Hill Road Est | 0 | 44099 |  | 37 | 44100 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting505520200921-17Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting505520200921-17Light Truck - Pick up- After Jan 101243.75Inv#055 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5055 | 20200921-17 | 53510312 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2020-09-21 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Tuned up road B-136 to B-142 | 3 | B136-B144 | Fire Hill Road Est | 0 | 44099 |  | 37 | 44100 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting505520200921-17Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting505520200921-17Operator - Principle - After Jan 1011825Inv#055 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5056 | 20200921-18 | 53510312 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2020-09-21 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Worked on bridge approaches on access road into Blair Lake. | 3 | B182-B186 | Blair Lake Road | 0 | 44099 |  | 37 | 44100 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting505620200921-18Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting505620200921-18Excavator - 36 ton- After Jan 1091322.64Inv#055 | [5 empty] | 1 | 1322.64 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5056 | 20200921-18 | 53510312 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2020-09-21 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Worked on bridge approaches on access road into Blair Lake. | 3 | B182-B186 | Blair Lake Road | 0 | 44099 |  | 37 | 44100 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting505620200921-18Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting505620200921-18Excavator Thumb - 30 - 50 ton- After Jan 109109.89Inv#055 | [5 empty] | 1 | 109.89 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5056 | 20200921-18 | 53510312 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-09-21 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Worked on bridge approaches on access road into Blair Lake. | 3 | B182-B186 | Blair Lake Road | 0 | 44099 |  | 37 | 44100 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting505620200921-18Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting505620200921-18Light Truck - Pick up- After Jan 101243.75Inv#055 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5056 | 20200921-18 | 53510312 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 10 | HR |  |  | 75 | 0 | 750 | 97.5 | 847.5 | 2020-09-21 | 1 | Inv#055 | 44102 | 107 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Worked on bridge approaches on access road into Blair Lake. | 3 | B182-B186 | Blair Lake Road | 0 | 44099 |  | 37 | 44100 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting505620200921-18Operator - Principle - After Jan 1010750 | Corbiere and Sons Contracting505620200921-18Operator - Principle - After Jan 1010750Inv#055 | [5 empty] | 1 | 750 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5116 | 20200921-22 | 53510504 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10.5 | Dynamic | 98.61 | 0 |  |  | 1380.54 | 179.4702 | 1560.0102 | 2020-09-21 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 2 Excavators, 1 Dozer, 1 Rock Truck spreading gravel from stockpiles. | 5 | C076-C116 | Cook Lake | 0 | 44102 |  | 50 | 44102 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting511620200921-22Dozer D6 or equal- After Jan 1010.51380.54 | Corbiere and Sons Contracting511620200921-22Dozer D6 or equal- After Jan 1010.51380.54Inv#057 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1380.54 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5116 | 20200921-22 | 53510504 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 21 | Dynamic | 110.22 | 0 |  |  | 3086.16 | 401.2008 | 3487.3608 | 2020-09-21 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 2 Excavators, 1 Dozer, 1 Rock Truck spreading gravel from stockpiles. | 5 | C076-C116 | Cook Lake | 0 | 44102 |  | 50 | 44102 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting511620200921-22Excavator - 36 ton- After Jan 10213086.16 | Corbiere and Sons Contracting511620200921-22Excavator - 36 ton- After Jan 10213086.16Inv#057 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 3086.16 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5116 | 20200921-22 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-09-21 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 2 Excavators, 1 Dozer, 1 Rock Truck spreading gravel from stockpiles. | 5 | C076-C116 | Cook Lake | 0 | 44102 |  | 50 | 44102 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting511620200921-22Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting511620200921-22Light Truck - Pick up- After Jan 102487.5Inv#057 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5116 | 20200921-22 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 10.5 | Dynamic | 103.54 | 0 |  |  | 1449.525 | 188.4383 | 1637.9633 | 2020-09-21 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 2 Excavators, 1 Dozer, 1 Rock Truck spreading gravel from stockpiles. | 5 | C076-C116 | Cook Lake | 0 | 44102 |  | 50 | 44102 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting511620200921-22Rock Truck - 30 Ton- After Jan 1010.51449.525 | Corbiere and Sons Contracting511620200921-22Rock Truck - 30 Ton- After Jan 1010.51449.525Inv#057 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1449.525 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5116 | 20200921-22 | 53510504 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2020-09-21 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 2 Excavators, 1 Dozer, 1 Rock Truck spreading gravel from stockpiles. | 5 | C076-C116 | Cook Lake | 0 | 44102 |  | 50 | 44102 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting511620200921-22L.O.A.4840 | Corbiere and Sons Contracting511620200921-22L.O.A.4840Inv#057 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5116 | 20200921-22 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 34.5 | HR |  |  | 75 | 0 | 2587.5 | 336.375 | 2923.875 | 2020-09-21 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 2 Excavators, 1 Dozer, 1 Rock Truck spreading gravel from stockpiles. | 5 | C076-C116 | Cook Lake | 0 | 44102 |  | 50 | 44102 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting511620200921-22Operator - Principle - After Jan 1034.52587.5 | Corbiere and Sons Contracting511620200921-22Operator - Principle - After Jan 1034.52587.5Inv#057 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 2587.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5116 | 20200921-22 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 11.5 | HR |  |  | 70 | 0 | 805 | 104.65 | 909.65 | 2020-09-21 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 2 Excavators, 1 Dozer, 1 Rock Truck spreading gravel from stockpiles. | 5 | C076-C116 | Cook Lake | 0 | 44102 |  | 50 | 44102 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting511620200921-22Driver - AZ - After Jan 1011.5805 | Corbiere and Sons Contracting511620200921-22Driver - AZ - After Jan 1011.5805Inv#057 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 805 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5120 | 20200921-26 | 53510504 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10.5 | Dynamic | 98.61 | 0 |  |  | 1380.54 | 179.4702 | 1560.0102 | 2020-09-21 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavators loaded rock trucks, Dozer spreaded gravelDawson Campbell completed orientation in the morning | 5 | C050-C069 | Antler Lake | 0 | 44102 |  | 50 | 44102 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting512020200921-26Dozer D6 or equal- After Jan 1010.51380.54 | Corbiere and Sons Contracting512020200921-26Dozer D6 or equal- After Jan 1010.51380.54Inv#057 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1380.54 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5120 | 20200921-26 | 53510504 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 5.5 | Dynamic | 103.84 | 0 |  |  | 761.475 | 98.9917 | 860.4668 | 2020-09-21 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavators loaded rock trucks, Dozer spreaded gravelDawson Campbell completed orientation in the morning | 5 | C050-C069 | Antler Lake | 0 | 44102 |  | 50 | 44102 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting512020200921-26Excavator - 30 ton- After Jan 105.5761.475 | Corbiere and Sons Contracting512020200921-26Excavator - 30 ton- After Jan 105.5761.475Inv#057 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 761.475 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5120 | 20200921-26 | 53510504 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 7 | Dynamic | 110.22 | 0 |  |  | 1028.72 | 133.7336 | 1162.4536 | 2020-09-21 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavators loaded rock trucks, Dozer spreaded gravelDawson Campbell completed orientation in the morning | 5 | C050-C069 | Antler Lake | 0 | 44102 |  | 50 | 44102 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting512020200921-26Excavator - 36 ton- After Jan 1071028.72 | Corbiere and Sons Contracting512020200921-26Excavator - 36 ton- After Jan 1071028.72Inv#057 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1028.72 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5120 | 20200921-26 | 53510504 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 7 | HR | 9.16 | 0 |  |  | 85.47 | 11.1111 | 96.5811 | 2020-09-21 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavators loaded rock trucks, Dozer spreaded gravelDawson Campbell completed orientation in the morning | 5 | C050-C069 | Antler Lake | 0 | 44102 |  | 50 | 44102 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting512020200921-26Excavator Thumb - 30 - 50 ton- After Jan 10785.47 | Corbiere and Sons Contracting512020200921-26Excavator Thumb - 30 - 50 ton- After Jan 10785.47Inv#057 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 85.47 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5120 | 20200921-26 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-09-21 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavators loaded rock trucks, Dozer spreaded gravelDawson Campbell completed orientation in the morning | 5 | C050-C069 | Antler Lake | 0 | 44102 |  | 50 | 44102 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting512020200921-26Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting512020200921-26Light Truck - Pick up- After Jan 102487.5Inv#057 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5120 | 20200921-26 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 21 | Dynamic | 103.54 | 0 |  |  | 2899.05 | 376.8765 | 3275.9265 | 2020-09-21 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavators loaded rock trucks, Dozer spreaded gravelDawson Campbell completed orientation in the morning | 5 | C050-C069 | Antler Lake | 0 | 44102 |  | 50 | 44102 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting512020200921-26Rock Truck - 30 Ton- After Jan 10212899.05 | Corbiere and Sons Contracting512020200921-26Rock Truck - 30 Ton- After Jan 10212899.05Inv#057 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 2899.05 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5120 | 20200921-26 | 53510504 | Access | 0 | Foreman | 95 | 6 | HR |  |  | 95 | 0 | 570 | 74.1 | 644.1 | 2020-09-21 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavators loaded rock trucks, Dozer spreaded gravelDawson Campbell completed orientation in the morning | 5 | C050-C069 | Antler Lake | 0 | 44102 |  | 50 | 44102 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting512020200921-26Foreman6570 | Corbiere and Sons Contracting512020200921-26Foreman6570Inv#057 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 570 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5120 | 20200921-26 | 53510504 | Access | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2020-09-21 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavators loaded rock trucks, Dozer spreaded gravelDawson Campbell completed orientation in the morning | 5 | C050-C069 | Antler Lake | 0 | 44102 |  | 50 | 44102 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting512020200921-26L.O.A.61260 | Corbiere and Sons Contracting512020200921-26L.O.A.61260Inv#057 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5120 | 20200921-26 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 30.5 | HR |  |  | 75 | 0 | 2287.5 | 297.375 | 2584.875 | 2020-09-21 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavators loaded rock trucks, Dozer spreaded gravelDawson Campbell completed orientation in the morning | 5 | C050-C069 | Antler Lake | 0 | 44102 |  | 50 | 44102 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting512020200921-26Operator - Principle - After Jan 1030.52287.5 | Corbiere and Sons Contracting512020200921-26Operator - Principle - After Jan 1030.52287.5Inv#057 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 2287.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5120 | 20200921-26 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 23 | HR |  |  | 70 | 0 | 1610 | 209.3 | 1819.3 | 2020-09-21 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavators loaded rock trucks, Dozer spreaded gravelDawson Campbell completed orientation in the morning | 5 | C050-C069 | Antler Lake | 0 | 44102 |  | 50 | 44102 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting512020200921-26Driver - AZ - After Jan 10231610 | Corbiere and Sons Contracting512020200921-26Driver - AZ - After Jan 10231610Inv#057 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1610 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5121 | 20200921-27 | 53510502 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9.5 | Dynamic | 110.22 | 0 |  |  | 1396.12 | 181.4956 | 1577.6156 | 2020-09-21 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock hammer all day - left 1 hour early. | 5 | C050-C069 | Antler Lake | 0 | 44102 |  | 50 | 44102 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting512120200921-27Excavator - 36 ton- After Jan 109.51396.12 | Corbiere and Sons Contracting512120200921-27Excavator - 36 ton- After Jan 109.51396.12Inv#057 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 1396.12 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5121 | 20200921-27 | 53510502 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 9.5 | HR | 47.54 | 0 |  |  | 602.11 | 78.2743 | 680.3843 | 2020-09-21 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock hammer all day - left 1 hour early. | 5 | C050-C069 | Antler Lake | 0 | 44102 |  | 50 | 44102 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting512120200921-27Excavator Hammer - 30 - 50 ton- After Jan 109.5602.11 | Corbiere and Sons Contracting512120200921-27Excavator Hammer - 30 - 50 ton- After Jan 109.5602.11Inv#057 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 602.11 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5121 | 20200921-27 | 53510502 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-09-21 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock hammer all day - left 1 hour early. | 5 | C050-C069 | Antler Lake | 0 | 44102 |  | 50 | 44102 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting512120200921-27Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting512120200921-27Light Truck - Pick up- After Jan 101243.75Inv#057 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5121 | 20200921-27 | 53510502 | Access | 0 | Foreman | 95 | 2 | HR |  |  | 95 | 0 | 190 | 24.7 | 214.7 | 2020-09-21 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock hammer all day - left 1 hour early. | 5 | C050-C069 | Antler Lake | 0 | 44102 |  | 50 | 44102 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting512120200921-27Foreman2190 | Corbiere and Sons Contracting512120200921-27Foreman2190Inv#057 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 190 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5121 | 20200921-27 | 53510502 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-09-21 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock hammer all day - left 1 hour early. | 5 | C050-C069 | Antler Lake | 0 | 44102 |  | 50 | 44102 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting512120200921-27L.O.A.1210 | Corbiere and Sons Contracting512120200921-27L.O.A.1210Inv#057 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5121 | 20200921-27 | 53510502 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 10.5 | HR |  |  | 75 | 0 | 787.5 | 102.375 | 889.875 | 2020-09-21 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock hammer all day - left 1 hour early. | 5 | C050-C069 | Antler Lake | 0 | 44102 |  | 50 | 44102 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting512120200921-27Operator - Principle - After Jan 1010.5787.5 | Corbiere and Sons Contracting512120200921-27Operator - Principle - After Jan 1010.5787.5Inv#057 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 787.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5182 | 20200921-34 | 53510412 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 1 | Dynamic | 98.61 | 0 |  |  | 131.48 | 17.0924 | 148.5724 | 2020-09-21 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rescued Valards labourers pickup stuck in the road. Rescued Atwells pickup stuck in the road at 7070 bridge. | 4 | C011-C029 | Nishin Creek Road | 0 | 44104 |  | 36 | 44104 | [5 empty] | Mike Lecocq | 04 | Corbiere and Sons Contracting518220200921-34Dozer D6 or equal- After Jan 101131.48 | Corbiere and Sons Contracting518220200921-34Dozer D6 or equal- After Jan 101131.48Inv#057 | [5 empty] | 1 | 131.48 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5182 | 20200921-34 | 53510412 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 2 | Dynamic | 110.22 | 0 |  |  | 293.92 | 38.2096 | 332.1296 | 2020-09-21 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rescued Valards labourers pickup stuck in the road. Rescued Atwells pickup stuck in the road at 7070 bridge. | 4 | C011-C029 | Nishin Creek Road | 0 | 44104 |  | 36 | 44104 | [5 empty] | Mike Lecocq | 04 | Corbiere and Sons Contracting518220200921-34Excavator - 36 ton- After Jan 102293.92 | Corbiere and Sons Contracting518220200921-34Excavator - 36 ton- After Jan 102293.92Inv#057 | [5 empty] | 1 | 293.92 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5182 | 20200921-34 | 53510412 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-09-21 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rescued Valards labourers pickup stuck in the road. Rescued Atwells pickup stuck in the road at 7070 bridge. | 4 | C011-C029 | Nishin Creek Road | 0 | 44104 |  | 36 | 44104 | [5 empty] | Mike Lecocq | 04 | Corbiere and Sons Contracting518220200921-34L.O.A.1210 | Corbiere and Sons Contracting518220200921-34L.O.A.1210Inv#057 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5182 | 20200921-34 | 53510412 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 3 | HR |  |  | 75 | 0 | 225 | 29.25 | 254.25 | 2020-09-21 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rescued Valards labourers pickup stuck in the road. Rescued Atwells pickup stuck in the road at 7070 bridge. | 4 | C011-C029 | Nishin Creek Road | 0 | 44104 |  | 36 | 44104 | [5 empty] | Mike Lecocq | 04 | Corbiere and Sons Contracting518220200921-34Operator - Principle - After Jan 103225 | Corbiere and Sons Contracting518220200921-34Operator - Principle - After Jan 103225Inv#057 | [5 empty] | 1 | 225 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5083 | 20200922-23 | 53510312 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 5 | Dynamic | 98.61 | 0 |  |  | 657.4 | 85.462 | 742.862 | 2020-09-22 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | DZ-05 finished road maintenance at B-136 then moved into WF2 Land fill | 3 | B136-B144 | Fire Hill Creek Road east | 0 | 44100 |  | 37 | 44101 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting508320200922-23Dozer D6 or equal- After Jan 105657.4 | Corbiere and Sons Contracting508320200922-23Dozer D6 or equal- After Jan 105657.4Inv#057 | [5 empty] | 1 | 657.4 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5083 | 20200922-23 | 53510312 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 75 | 0 | 450 | 58.5 | 508.5 | 2020-09-22 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | DZ-05 finished road maintenance at B-136 then moved into WF2 Land fill | 3 | B136-B144 | Fire Hill Creek Road east | 0 | 44100 |  | 37 | 44101 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting508320200922-23Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting508320200922-23Operator - Principle - After Jan 106450Inv#057 | [5 empty] | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5084 | 20200922-24 | 53510312 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 4 | Dynamic | 110.22 | 0 |  |  | 587.84 | 76.4192 | 664.2592 | 2020-09-22 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-07 worked on the access hill at Kama Cliffs then moved into WF2 Landfill | 3 | B159-B160 | Kama Cliffs | 0 | 44096 |  | 37 | 44101 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting508420200922-24Excavator - 36 ton- After Jan 104587.84 | Corbiere and Sons Contracting508420200922-24Excavator - 36 ton- After Jan 104587.84Inv#057 | [5 empty] | 1 | 587.84 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5084 | 20200922-24 | 53510312 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 4 | HR | 9.16 | 0 |  |  | 48.84 | 6.3492 | 55.1892 | 2020-09-22 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-07 worked on the access hill at Kama Cliffs then moved into WF2 Landfill | 3 | B159-B160 | Kama Cliffs | 0 | 44096 |  | 37 | 44101 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting508420200922-24Excavator Thumb - 30 - 50 ton- After Jan 10448.84 | Corbiere and Sons Contracting508420200922-24Excavator Thumb - 30 - 50 ton- After Jan 10448.84Inv#057 | [5 empty] | 1 | 48.84 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5084 | 20200922-24 | 53510312 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-09-22 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-07 worked on the access hill at Kama Cliffs then moved into WF2 Landfill | 3 | B159-B160 | Kama Cliffs | 0 | 44096 |  | 37 | 44101 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting508420200922-24Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting508420200922-24Light Truck - Pick up- After Jan 101243.75Inv#057 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5084 | 20200922-24 | 53510312 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5 | HR |  |  | 75 | 0 | 375 | 48.75 | 423.75 | 2020-09-22 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-07 worked on the access hill at Kama Cliffs then moved into WF2 Landfill | 3 | B159-B160 | Kama Cliffs | 0 | 44096 |  | 37 | 44101 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting508420200922-24Operator - Principle - After Jan 105375 | Corbiere and Sons Contracting508420200922-24Operator - Principle - After Jan 105375Inv#057 | [5 empty] | 1 | 375 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5085 | 20200922-25 | 53510312 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 6.5 | Dynamic | 110.22 | 0 |  |  | 955.24 | 124.1812 | 1079.4212 | 2020-09-22 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-05 loaded out 20' bridge then finished access road alignement then moved to WF2 landfill road. | 3 | B182-B186 | Blair Lake Road | 0 | 44100 |  | 37 | 44101 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting508520200922-25Excavator - 36 ton- After Jan 106.5955.24 | Corbiere and Sons Contracting508520200922-25Excavator - 36 ton- After Jan 106.5955.24Inv#057 | [5 empty] | 1 | 955.24 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5085 | 20200922-25 | 53510312 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 6.5 | HR | 9.16 | 0 |  |  | 79.365 | 10.3174 | 89.6825 | 2020-09-22 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-05 loaded out 20' bridge then finished access road alignement then moved to WF2 landfill road. | 3 | B182-B186 | Blair Lake Road | 0 | 44100 |  | 37 | 44101 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting508520200922-25Excavator Thumb - 30 - 50 ton- After Jan 106.579.365 | Corbiere and Sons Contracting508520200922-25Excavator Thumb - 30 - 50 ton- After Jan 106.579.365Inv#057 | [5 empty] | 1 | 79.365 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5085 | 20200922-25 | 53510312 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-09-22 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-05 loaded out 20' bridge then finished access road alignement then moved to WF2 landfill road. | 3 | B182-B186 | Blair Lake Road | 0 | 44100 |  | 37 | 44101 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting508520200922-25Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting508520200922-25Light Truck - Pick up- After Jan 101243.75Inv#057 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5085 | 20200922-25 | 53510312 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 8.5 | HR |  |  | 75 | 0 | 637.5 | 82.875 | 720.375 | 2020-09-22 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-05 loaded out 20' bridge then finished access road alignement then moved to WF2 landfill road. | 3 | B182-B186 | Blair Lake Road | 0 | 44100 |  | 37 | 44101 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting508520200922-25Operator - Principle - After Jan 108.5637.5 | Corbiere and Sons Contracting508520200922-25Operator - Principle - After Jan 108.5637.5Inv#057 | [5 empty] | 1 | 637.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5123 | 20200922-28 | 53510504 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 11 | Dynamic | 41.4 | 0 |  |  | 607.2 | 78.936 | 686.136 | 2020-09-22 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Missed ticket from September 22nd Crystal Hicks time for looking after gravel from Sept 21st & 22nd - 2xLOA, 2xPickups | 5 | C050-C069 | Antler Lake | 0 | 44102 |  | 49 | 44102 | [5 empty] | Travis Chisolm | 05 | Corbiere and Sons Contracting512320200922-28Dump - Triaxle- After Jan 1011607.2 | Corbiere and Sons Contracting512320200922-28Dump - Triaxle- After Jan 1011607.2Inv#057 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 607.2 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5123 | 20200922-28 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-09-22 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Missed ticket from September 22nd Crystal Hicks time for looking after gravel from Sept 21st & 22nd - 2xLOA, 2xPickups | 5 | C050-C069 | Antler Lake | 0 | 44102 |  | 49 | 44102 | [5 empty] | Travis Chisolm | 05 | Corbiere and Sons Contracting512320200922-28Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting512320200922-28Light Truck - Pick up- After Jan 102487.5Inv#057 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5123 | 20200922-28 | 53510504 | Access | 0 | Construction Coordinator | 80 | 12 | HR |  |  | 80 | 0 | 960 | 124.8 | 1084.8 | 2020-09-22 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Missed ticket from September 22nd Crystal Hicks time for looking after gravel from Sept 21st & 22nd - 2xLOA, 2xPickups | 5 | C050-C069 | Antler Lake | 0 | 44102 |  | 49 | 44102 | [5 empty] | Travis Chisolm | 05 | Corbiere and Sons Contracting512320200922-28Construction Coordinator12960 | Corbiere and Sons Contracting512320200922-28Construction Coordinator12960Inv#057 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5123 | 20200922-28 | 53510504 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2020-09-22 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Missed ticket from September 22nd Crystal Hicks time for looking after gravel from Sept 21st & 22nd - 2xLOA, 2xPickups | 5 | C050-C069 | Antler Lake | 0 | 44102 |  | 49 | 44102 | [5 empty] | Travis Chisolm | 05 | Corbiere and Sons Contracting512320200922-28L.O.A.3630 | Corbiere and Sons Contracting512320200922-28L.O.A.3630Inv#057 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5123 | 20200922-28 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 11 | HR |  |  | 70 | 0 | 770 | 100.1 | 870.1 | 2020-09-22 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Missed ticket from September 22nd Crystal Hicks time for looking after gravel from Sept 21st & 22nd - 2xLOA, 2xPickups | 5 | C050-C069 | Antler Lake | 0 | 44102 |  | 49 | 44102 | [5 empty] | Travis Chisolm | 05 | Corbiere and Sons Contracting512320200922-28Driver - AZ - After Jan 1011770 | Corbiere and Sons Contracting512320200922-28Driver - AZ - After Jan 1011770Inv#057 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 770 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5124 | 20200922-29 | 53510504 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10.5 | Dynamic | 98.61 | 0 |  |  | 1380.54 | 179.4702 | 1560.0102 | 2020-09-22 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock trucks hauling material that was already on site in stockpile with the 300JD and Dozer | 5 | C076-C116 | Cook Lake | 0 | 44102 |  | 50 | 44102 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting512420200922-29Dozer D6 or equal- After Jan 1010.51380.54 | Corbiere and Sons Contracting512420200922-29Dozer D6 or equal- After Jan 1010.51380.54Inv#057 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1380.54 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5124 | 20200922-29 | 53510504 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10.5 | Dynamic | 110.22 | 0 |  |  | 1543.08 | 200.6004 | 1743.6804 | 2020-09-22 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock trucks hauling material that was already on site in stockpile with the 300JD and Dozer | 5 | C076-C116 | Cook Lake | 0 | 44102 |  | 50 | 44102 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting512420200922-29Excavator - 36 ton- After Jan 1010.51543.08 | Corbiere and Sons Contracting512420200922-29Excavator - 36 ton- After Jan 1010.51543.08Inv#057 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1543.08 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5124 | 20200922-29 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-09-22 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock trucks hauling material that was already on site in stockpile with the 300JD and Dozer | 5 | C076-C116 | Cook Lake | 0 | 44102 |  | 50 | 44102 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting512420200922-29Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting512420200922-29Light Truck - Pick up- After Jan 102487.5Inv#057 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5124 | 20200922-29 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 21 | Dynamic | 103.54 | 0 |  |  | 2899.05 | 376.8765 | 3275.9265 | 2020-09-22 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock trucks hauling material that was already on site in stockpile with the 300JD and Dozer | 5 | C076-C116 | Cook Lake | 0 | 44102 |  | 50 | 44102 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting512420200922-29Rock Truck - 30 Ton- After Jan 10212899.05 | Corbiere and Sons Contracting512420200922-29Rock Truck - 30 Ton- After Jan 10212899.05Inv#057 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 2899.05 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5124 | 20200922-29 | 53510504 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2020-09-22 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock trucks hauling material that was already on site in stockpile with the 300JD and Dozer | 5 | C076-C116 | Cook Lake | 0 | 44102 |  | 50 | 44102 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting512420200922-29L.O.A.4840 | Corbiere and Sons Contracting512420200922-29L.O.A.4840Inv#057 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5124 | 20200922-29 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 23 | HR |  |  | 75 | 0 | 1725 | 224.25 | 1949.25 | 2020-09-22 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock trucks hauling material that was already on site in stockpile with the 300JD and Dozer | 5 | C076-C116 | Cook Lake | 0 | 44102 |  | 50 | 44102 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting512420200922-29Operator - Principle - After Jan 10231725 | Corbiere and Sons Contracting512420200922-29Operator - Principle - After Jan 10231725Inv#057 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5124 | 20200922-29 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 23 | HR |  |  | 70 | 0 | 1610 | 209.3 | 1819.3 | 2020-09-22 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock trucks hauling material that was already on site in stockpile with the 300JD and Dozer | 5 | C076-C116 | Cook Lake | 0 | 44102 |  | 50 | 44102 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting512420200922-29Driver - AZ - After Jan 10231610 | Corbiere and Sons Contracting512420200922-29Driver - AZ - After Jan 10231610Inv#057 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1610 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5126 | 20200922-31 | 53510504 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10.5 | Dynamic | 98.61 | 0 |  |  | 1380.54 | 179.4702 | 1560.0102 | 2020-09-22 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Spreading gravel from C-052.5 to C-053Excavator loading rock trucks | 5 | C050-C069 | Antler Lake | 0 | 44102 |  | 50 | 44102 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting512620200922-31Dozer D6 or equal- After Jan 1010.51380.54 | Corbiere and Sons Contracting512620200922-31Dozer D6 or equal- After Jan 1010.51380.54Inv#057 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1380.54 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5126 | 20200922-31 | 53510504 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10.5 | Dynamic | 103.84 | 0 |  |  | 1453.725 | 188.9843 | 1642.7093 | 2020-09-22 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Spreading gravel from C-052.5 to C-053Excavator loading rock trucks | 5 | C050-C069 | Antler Lake | 0 | 44102 |  | 50 | 44102 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting512620200922-31Excavator - 30 ton- After Jan 1010.51453.725 | Corbiere and Sons Contracting512620200922-31Excavator - 30 ton- After Jan 1010.51453.725Inv#057 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1453.725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5126 | 20200922-31 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-09-22 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Spreading gravel from C-052.5 to C-053Excavator loading rock trucks | 5 | C050-C069 | Antler Lake | 0 | 44102 |  | 50 | 44102 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting512620200922-31Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting512620200922-31Light Truck - Pick up- After Jan 102487.5Inv#057 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5126 | 20200922-31 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 21 | Dynamic | 103.54 | 0 |  |  | 2899.05 | 376.8765 | 3275.9265 | 2020-09-22 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Spreading gravel from C-052.5 to C-053Excavator loading rock trucks | 5 | C050-C069 | Antler Lake | 0 | 44102 |  | 50 | 44102 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting512620200922-31Rock Truck - 30 Ton- After Jan 10212899.05 | Corbiere and Sons Contracting512620200922-31Rock Truck - 30 Ton- After Jan 10212899.05Inv#057 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 2899.05 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5126 | 20200922-31 | 53510504 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2020-09-22 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Spreading gravel from C-052.5 to C-053Excavator loading rock trucks | 5 | C050-C069 | Antler Lake | 0 | 44102 |  | 50 | 44102 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting512620200922-31L.O.A.4840 | Corbiere and Sons Contracting512620200922-31L.O.A.4840Inv#057 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5126 | 20200922-31 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 23 | HR |  |  | 75 | 0 | 1725 | 224.25 | 1949.25 | 2020-09-22 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Spreading gravel from C-052.5 to C-053Excavator loading rock trucks | 5 | C050-C069 | Antler Lake | 0 | 44102 |  | 50 | 44102 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting512620200922-31Operator - Principle - After Jan 10231725 | Corbiere and Sons Contracting512620200922-31Operator - Principle - After Jan 10231725Inv#057 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5126 | 20200922-31 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 23 | HR |  |  | 70 | 0 | 1610 | 209.3 | 1819.3 | 2020-09-22 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Spreading gravel from C-052.5 to C-053Excavator loading rock trucks | 5 | C050-C069 | Antler Lake | 0 | 44102 |  | 50 | 44102 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting512620200922-31Driver - AZ - After Jan 10231610 | Corbiere and Sons Contracting512620200922-31Driver - AZ - After Jan 10231610Inv#057 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1610 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5127 | 20200922-32 | 53510502 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 6 | Dynamic | 110.22 | 0 |  |  | 881.76 | 114.6288 | 996.3888 | 2020-09-22 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Running rock hammer for 6 hours - equipment down the rest of the day. | 5 | C050-C069 | Antler Lake | 0 | 44102 |  | 50 | 44102 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting512720200922-32Excavator - 36 ton- After Jan 106881.76 | Corbiere and Sons Contracting512720200922-32Excavator - 36 ton- After Jan 106881.76Inv#057 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 881.76 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5127 | 20200922-32 | 53510502 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 6 | HR | 47.54 | 0 |  |  | 380.28 | 49.4364 | 429.7164 | 2020-09-22 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Running rock hammer for 6 hours - equipment down the rest of the day. | 5 | C050-C069 | Antler Lake | 0 | 44102 |  | 50 | 44102 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting512720200922-32Excavator Hammer - 30 - 50 ton- After Jan 106380.28 | Corbiere and Sons Contracting512720200922-32Excavator Hammer - 30 - 50 ton- After Jan 106380.28Inv#057 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 380.28 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5127 | 20200922-32 | 53510502 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-09-22 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Running rock hammer for 6 hours - equipment down the rest of the day. | 5 | C050-C069 | Antler Lake | 0 | 44102 |  | 50 | 44102 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting512720200922-32Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting512720200922-32Light Truck - Pick up- After Jan 101243.75Inv#057 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5127 | 20200922-32 | 53510502 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-09-22 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Running rock hammer for 6 hours - equipment down the rest of the day. | 5 | C050-C069 | Antler Lake | 0 | 44102 |  | 50 | 44102 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting512720200922-32L.O.A.1210 | Corbiere and Sons Contracting512720200922-32L.O.A.1210Inv#057 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5127 | 20200922-32 | 53510502 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 75 | 0 | 450 | 58.5 | 508.5 | 2020-09-22 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Running rock hammer for 6 hours - equipment down the rest of the day. | 5 | C050-C069 | Antler Lake | 0 | 44102 |  | 50 | 44102 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting512720200922-32Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting512720200922-32Operator - Principle - After Jan 106450Inv#057 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5099 | 20200923-12 | 53510504 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10.5 | Dynamic | 98.61 | 0 |  |  | 1380.54 | 179.4702 | 1560.0102 | 2020-09-23 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 150m complete towards C-052. | 5 | C050-C069 | Antler Lake | 0 | 44100 |  | 50 | 44101 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting509920200923-12Dozer D6 or equal- After Jan 1010.51380.54 | Corbiere and Sons Contracting509920200923-12Dozer D6 or equal- After Jan 1010.51380.54Inv#057 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1380.54 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5099 | 20200923-12 | 53510504 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10.5 | Dynamic | 103.84 | 0 |  |  | 1453.725 | 188.9843 | 1642.7093 | 2020-09-23 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 150m complete towards C-052. | 5 | C050-C069 | Antler Lake | 0 | 44100 |  | 50 | 44101 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting509920200923-12Excavator - 30 ton- After Jan 1010.51453.725 | Corbiere and Sons Contracting509920200923-12Excavator - 30 ton- After Jan 1010.51453.725Inv#057 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1453.725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5099 | 20200923-12 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2020-09-23 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 150m complete towards C-052. | 5 | C050-C069 | Antler Lake | 0 | 44100 |  | 50 | 44101 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting509920200923-12Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting509920200923-12Light Truck - Pick up- After Jan 103731.25Inv#057 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 731.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5099 | 20200923-12 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 21 | Dynamic | 103.54 | 0 |  |  | 2899.05 | 376.8765 | 3275.9265 | 2020-09-23 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 150m complete towards C-052. | 5 | C050-C069 | Antler Lake | 0 | 44100 |  | 50 | 44101 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting509920200923-12Rock Truck - 30 Ton- After Jan 10212899.05 | Corbiere and Sons Contracting509920200923-12Rock Truck - 30 Ton- After Jan 10212899.05Inv#057 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 2899.05 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5099 | 20200923-12 | 53510504 | Access | 0 | Foreman | 95 | 6 | HR |  |  | 95 | 0 | 570 | 74.1 | 644.1 | 2020-09-23 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 150m complete towards C-052. | 5 | C050-C069 | Antler Lake | 0 | 44100 |  | 50 | 44101 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting509920200923-12Foreman6570 | Corbiere and Sons Contracting509920200923-12Foreman6570Inv#057 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 570 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5099 | 20200923-12 | 53510504 | Access | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2020-09-23 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 150m complete towards C-052. | 5 | C050-C069 | Antler Lake | 0 | 44100 |  | 50 | 44101 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting509920200923-12L.O.A.51050 | Corbiere and Sons Contracting509920200923-12L.O.A.51050Inv#057 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5099 | 20200923-12 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 23 | HR |  |  | 75 | 0 | 1725 | 224.25 | 1949.25 | 2020-09-23 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 150m complete towards C-052. | 5 | C050-C069 | Antler Lake | 0 | 44100 |  | 50 | 44101 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting509920200923-12Operator - Principle - After Jan 10231725 | Corbiere and Sons Contracting509920200923-12Operator - Principle - After Jan 10231725Inv#057 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5099 | 20200923-12 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 23 | HR |  |  | 70 | 0 | 1610 | 209.3 | 1819.3 | 2020-09-23 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 150m complete towards C-052. | 5 | C050-C069 | Antler Lake | 0 | 44100 |  | 50 | 44101 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting509920200923-12Driver - AZ - After Jan 10231610 | Corbiere and Sons Contracting509920200923-12Driver - AZ - After Jan 10231610Inv#057 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1610 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5100 | 20200923-13 | 53510502 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 8.5 | Dynamic | 110.22 | 0 |  |  | 1249.16 | 162.3908 | 1411.5508 | 2020-09-23 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock hammer all day (went down for 2 hrs) | 5 | C050-C069 | Antler Lake | 0 | 44100 |  | 50 | 44101 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting510020200923-13Excavator - 36 ton- After Jan 108.51249.16 | Corbiere and Sons Contracting510020200923-13Excavator - 36 ton- After Jan 108.51249.16Inv#057 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 1249.16 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5100 | 20200923-13 | 53510502 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 8.5 | HR | 47.54 | 0 |  |  | 538.73 | 70.0349 | 608.7649 | 2020-09-23 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock hammer all day (went down for 2 hrs) | 5 | C050-C069 | Antler Lake | 0 | 44100 |  | 50 | 44101 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting510020200923-13Excavator Hammer - 30 - 50 ton- After Jan 108.5538.73 | Corbiere and Sons Contracting510020200923-13Excavator Hammer - 30 - 50 ton- After Jan 108.5538.73Inv#057 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 538.73 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5100 | 20200923-13 | 53510502 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-09-23 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock hammer all day (went down for 2 hrs) | 5 | C050-C069 | Antler Lake | 0 | 44100 |  | 50 | 44101 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting510020200923-13Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting510020200923-13Light Truck - Pick up- After Jan 101243.75Inv#057 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5100 | 20200923-13 | 53510502 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-09-23 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock hammer all day (went down for 2 hrs) | 5 | C050-C069 | Antler Lake | 0 | 44100 |  | 50 | 44101 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting510020200923-13L.O.A.1210 | Corbiere and Sons Contracting510020200923-13L.O.A.1210Inv#057 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5100 | 20200923-13 | 53510502 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-09-23 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock hammer all day (went down for 2 hrs) | 5 | C050-C069 | Antler Lake | 0 | 44100 |  | 50 | 44101 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting510020200923-13Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting510020200923-13Operator - Principle - After Jan 1011.5862.5Inv#057 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5101 | 20200923-14 | 53510503 | Access | 0 | Feller Buncher | 240 | 3 | HR | 180 |  |  |  | 720 | 93.6 | 813.6 | 2020-09-23 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working in wetland area with corduroy | 5 | C050-C069 | Antler Lake | 0 | 44100 |  | 50 | 44101 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting510120200923-14Feller Buncher3720 | Corbiere and Sons Contracting510120200923-14Feller Buncher3720Inv#057 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 720 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5101 | 20200923-14 | 53510503 | Access | 0 | Skidder | 171 | 3 | HR | 128.25 | 0 |  |  | 513 | 66.69 | 579.69 | 2020-09-23 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working in wetland area with corduroy | 5 | C050-C069 | Antler Lake | 0 | 44100 |  | 50 | 44101 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting510120200923-14Skidder 3513 | Corbiere and Sons Contracting510120200923-14Skidder 3513Inv#057 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 513 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5101 | 20200923-14 | 53510503 | Access | 0 | Foreman | 95 | 2 | HR |  |  | 95 | 0 | 190 | 24.7 | 214.7 | 2020-09-23 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working in wetland area with corduroy | 5 | C050-C069 | Antler Lake | 0 | 44100 |  | 50 | 44101 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting510120200923-14Foreman2190 | Corbiere and Sons Contracting510120200923-14Foreman2190Inv#057 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 190 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5101 | 20200923-14 | 53510503 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-09-23 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working in wetland area with corduroy | 5 | C050-C069 | Antler Lake | 0 | 44100 |  | 50 | 44101 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting510120200923-14L.O.A.2420 | Corbiere and Sons Contracting510120200923-14L.O.A.2420Inv#057 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5101 | 20200923-14 | 53510503 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 75 | 0 | 450 | 58.5 | 508.5 | 2020-09-23 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working in wetland area with corduroy | 5 | C050-C069 | Antler Lake | 0 | 44100 |  | 50 | 44101 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting510120200923-14Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting510120200923-14Operator - Principle - After Jan 106450Inv#057 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5102 | 20200923-15 | 53510504 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10.5 | Dynamic | 98.61 | 0 |  |  | 1380.54 | 179.4702 | 1560.0102 | 2020-09-23 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Loading RTs, spreading gravel, hauling to C-084 - C-085. | 5 | C076-C116 | Cook Lake | 0 | 44100 |  | 50 | 44101 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting510220200923-15Dozer D6 or equal- After Jan 1010.51380.54 | Corbiere and Sons Contracting510220200923-15Dozer D6 or equal- After Jan 1010.51380.54Inv#057 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1380.54 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5102 | 20200923-15 | 53510504 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10.5 | Dynamic | 110.22 | 0 |  |  | 1543.08 | 200.6004 | 1743.6804 | 2020-09-23 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Loading RTs, spreading gravel, hauling to C-084 - C-085. | 5 | C076-C116 | Cook Lake | 0 | 44100 |  | 50 | 44101 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting510220200923-15Excavator - 36 ton- After Jan 1010.51543.08 | Corbiere and Sons Contracting510220200923-15Excavator - 36 ton- After Jan 1010.51543.08Inv#057 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1543.08 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5102 | 20200923-15 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-09-23 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Loading RTs, spreading gravel, hauling to C-084 - C-085. | 5 | C076-C116 | Cook Lake | 0 | 44100 |  | 50 | 44101 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting510220200923-15Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting510220200923-15Light Truck - Pick up- After Jan 102487.5Inv#057 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5102 | 20200923-15 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 21 | Dynamic | 103.54 | 0 |  |  | 2899.05 | 376.8765 | 3275.9265 | 2020-09-23 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Loading RTs, spreading gravel, hauling to C-084 - C-085. | 5 | C076-C116 | Cook Lake | 0 | 44100 |  | 50 | 44101 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting510220200923-15Rock Truck - 30 Ton- After Jan 10212899.05 | Corbiere and Sons Contracting510220200923-15Rock Truck - 30 Ton- After Jan 10212899.05Inv#057 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 2899.05 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5102 | 20200923-15 | 53510504 | Access | 0 | Foreman | 95 | 4 | HR |  |  | 95 | 0 | 380 | 49.4 | 429.4 | 2020-09-23 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Loading RTs, spreading gravel, hauling to C-084 - C-085. | 5 | C076-C116 | Cook Lake | 0 | 44100 |  | 50 | 44101 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting510220200923-15Foreman4380 | Corbiere and Sons Contracting510220200923-15Foreman4380Inv#057 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5102 | 20200923-15 | 53510504 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2020-09-23 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Loading RTs, spreading gravel, hauling to C-084 - C-085. | 5 | C076-C116 | Cook Lake | 0 | 44100 |  | 50 | 44101 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting510220200923-15L.O.A.4840 | Corbiere and Sons Contracting510220200923-15L.O.A.4840Inv#057 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5102 | 20200923-15 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 23 | HR |  |  | 75 | 0 | 1725 | 224.25 | 1949.25 | 2020-09-23 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Loading RTs, spreading gravel, hauling to C-084 - C-085. | 5 | C076-C116 | Cook Lake | 0 | 44100 |  | 50 | 44101 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting510220200923-15Operator - Principle - After Jan 10231725 | Corbiere and Sons Contracting510220200923-15Operator - Principle - After Jan 10231725Inv#057 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5102 | 20200923-15 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 23 | HR |  |  | 70 | 0 | 1610 | 209.3 | 1819.3 | 2020-09-23 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Loading RTs, spreading gravel, hauling to C-084 - C-085. | 5 | C076-C116 | Cook Lake | 0 | 44100 |  | 50 | 44101 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting510220200923-15Driver - AZ - After Jan 10231610 | Corbiere and Sons Contracting510220200923-15Driver - AZ - After Jan 10231610Inv#057 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1610 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5133 | 20200923-30 | 53510504 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 40.5 | Dynamic | 41.4 | 0 |  |  | 2235.6 | 290.628 | 2526.228 | 2020-09-23 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hauling in WF5 from pit to C-050 - C-059 Crystal Hicks time for September 23rd & 24th - 2xLOA and 2xPickup | 5 | C050-C069 | Antler Lake | 0 | 44102 |  | 50 | 44102 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting513320200923-30Dump - Triaxle- After Jan 1040.52235.6 | Corbiere and Sons Contracting513320200923-30Dump - Triaxle- After Jan 1040.52235.6Inv#057 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 2235.6 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5133 | 20200923-30 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-09-23 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hauling in WF5 from pit to C-050 - C-059 Crystal Hicks time for September 23rd & 24th - 2xLOA and 2xPickup | 5 | C050-C069 | Antler Lake | 0 | 44102 |  | 50 | 44102 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting513320200923-30Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting513320200923-30Light Truck - Pick up- After Jan 102487.5Inv#057 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5133 | 20200923-30 | 53510504 | Access | 0 | Construction Coordinator | 80 | 12 | HR |  |  | 80 | 0 | 960 | 124.8 | 1084.8 | 2020-09-23 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hauling in WF5 from pit to C-050 - C-059 Crystal Hicks time for September 23rd & 24th - 2xLOA and 2xPickup | 5 | C050-C069 | Antler Lake | 0 | 44102 |  | 50 | 44102 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting513320200923-30Construction Coordinator12960 | Corbiere and Sons Contracting513320200923-30Construction Coordinator12960Inv#057 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5133 | 20200923-30 | 53510504 | Access | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2020-09-23 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hauling in WF5 from pit to C-050 - C-059 Crystal Hicks time for September 23rd & 24th - 2xLOA and 2xPickup | 5 | C050-C069 | Antler Lake | 0 | 44102 |  | 50 | 44102 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting513320200923-30L.O.A.61260 | Corbiere and Sons Contracting513320200923-30L.O.A.61260Inv#057 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5133 | 20200923-30 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 40.5 | HR |  |  | 70 | 0 | 2835 | 368.55 | 3203.55 | 2020-09-23 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hauling in WF5 from pit to C-050 - C-059 Crystal Hicks time for September 23rd & 24th - 2xLOA and 2xPickup | 5 | C050-C069 | Antler Lake | 0 | 44102 |  | 50 | 44102 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting513320200923-30Driver - AZ - After Jan 1040.52835 | Corbiere and Sons Contracting513320200923-30Driver - AZ - After Jan 1040.52835Inv#057 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 2835 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5138 | 20200923-35 | 53510412 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 12 | Dynamic | 110.22 | 0 |  |  | 1763.52 | 229.2576 | 1992.7776 | 2020-09-23 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Assisting Valards hammer machine to access C-017 - 6 hrs Assisting Valards hammer machine on main road ditch line - 6 hrs | 4 | C011-C029 | Michin Creek Road | 0 | 44103 |  | 36 | 44103 | [5 empty] | Mike Lecocq | 04 | Corbiere and Sons Contracting513820200923-35Excavator - 36 ton- After Jan 10121763.52 | Corbiere and Sons Contracting513820200923-35Excavator - 36 ton- After Jan 10121763.52Inv#057 | [5 empty] | 1 | 1763.52 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5138 | 20200923-35 | 53510412 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 12 | HR | 9.16 | 0 |  |  | 146.52 | 19.0476 | 165.5676 | 2020-09-23 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Assisting Valards hammer machine to access C-017 - 6 hrs Assisting Valards hammer machine on main road ditch line - 6 hrs | 4 | C011-C029 | Michin Creek Road | 0 | 44103 |  | 36 | 44103 | [5 empty] | Mike Lecocq | 04 | Corbiere and Sons Contracting513820200923-35Excavator Thumb - 30 - 50 ton- After Jan 1012146.52 | Corbiere and Sons Contracting513820200923-35Excavator Thumb - 30 - 50 ton- After Jan 1012146.52Inv#057 | [5 empty] | 1 | 146.52 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5138 | 20200923-35 | 53510412 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-09-23 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Assisting Valards hammer machine to access C-017 - 6 hrs Assisting Valards hammer machine on main road ditch line - 6 hrs | 4 | C011-C029 | Michin Creek Road | 0 | 44103 |  | 36 | 44103 | [5 empty] | Mike Lecocq | 04 | Corbiere and Sons Contracting513820200923-35Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting513820200923-35Light Truck - Pick up- After Jan 101243.75Inv#057 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5138 | 20200923-35 | 53510412 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-09-23 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Assisting Valards hammer machine to access C-017 - 6 hrs Assisting Valards hammer machine on main road ditch line - 6 hrs | 4 | C011-C029 | Michin Creek Road | 0 | 44103 |  | 36 | 44103 | [5 empty] | Mike Lecocq | 04 | Corbiere and Sons Contracting513820200923-35L.O.A.1210 | Corbiere and Sons Contracting513820200923-35L.O.A.1210Inv#057 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5138 | 20200923-35 | 53510412 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2020-09-23 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Assisting Valards hammer machine to access C-017 - 6 hrs Assisting Valards hammer machine on main road ditch line - 6 hrs | 4 | C011-C029 | Michin Creek Road | 0 | 44103 |  | 36 | 44103 | [5 empty] | Mike Lecocq | 04 | Corbiere and Sons Contracting513820200923-35Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting513820200923-35Operator - Principle - After Jan 1012900Inv#057 | [5 empty] | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5150 | 20200924-12 | 53510502 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10.5 | Dynamic | 103.84 | 0 |  |  | 1453.725 | 188.9843 | 1642.7093 | 2020-09-24 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Worked on the AU1 road leading into C-055 (250m complete)Rock hammer for 7 hours, down mid day for welding repair. Labourers cleaed up garbage (mostly geo for half the day) | 5 | C050-C069 | Antler Lake | 0 | 44102 |  | 50 | 44105 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting515020200924-12Excavator - 30 ton- After Jan 1010.51453.725 | Corbiere and Sons Contracting515020200924-12Excavator - 30 ton- After Jan 1010.51453.725Inv#057 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 1453.725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5150 | 20200924-12 | 53510502 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 7 | Dynamic | 110.22 | 0 |  |  | 1028.72 | 133.7336 | 1162.4536 | 2020-09-24 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Worked on the AU1 road leading into C-055 (250m complete)Rock hammer for 7 hours, down mid day for welding repair. Labourers cleaed up garbage (mostly geo for half the day) | 5 | C050-C069 | Antler Lake | 0 | 44102 |  | 50 | 44105 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting515020200924-12Excavator - 36 ton- After Jan 1071028.72 | Corbiere and Sons Contracting515020200924-12Excavator - 36 ton- After Jan 1071028.72Inv#057 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 1028.72 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5150 | 20200924-12 | 53510502 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10.5 | HR | 9.16 | 0 |  |  | 128.205 | 16.6667 | 144.8716 | 2020-09-24 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Worked on the AU1 road leading into C-055 (250m complete)Rock hammer for 7 hours, down mid day for welding repair. Labourers cleaed up garbage (mostly geo for half the day) | 5 | C050-C069 | Antler Lake | 0 | 44102 |  | 50 | 44105 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting515020200924-12Excavator Thumb - 30 - 50 ton- After Jan 1010.5128.205 | Corbiere and Sons Contracting515020200924-12Excavator Thumb - 30 - 50 ton- After Jan 1010.5128.205Inv#057 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 128.205 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5150 | 20200924-12 | 53510502 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 7 | HR | 47.54 | 0 |  |  | 443.66 | 57.6758 | 501.3358 | 2020-09-24 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Worked on the AU1 road leading into C-055 (250m complete)Rock hammer for 7 hours, down mid day for welding repair. Labourers cleaed up garbage (mostly geo for half the day) | 5 | C050-C069 | Antler Lake | 0 | 44102 |  | 50 | 44105 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting515020200924-12Excavator Hammer - 30 - 50 ton- After Jan 107443.66 | Corbiere and Sons Contracting515020200924-12Excavator Hammer - 30 - 50 ton- After Jan 107443.66Inv#057 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 443.66 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5150 | 20200924-12 | 53510502 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-09-24 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Worked on the AU1 road leading into C-055 (250m complete)Rock hammer for 7 hours, down mid day for welding repair. Labourers cleaed up garbage (mostly geo for half the day) | 5 | C050-C069 | Antler Lake | 0 | 44102 |  | 50 | 44105 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting515020200924-12Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting515020200924-12Light Truck - Pick up- After Jan 102487.5Inv#057 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5150 | 20200924-12 | 53510502 | Access | 0 | Foreman | 95 | 6 | HR |  |  | 95 | 0 | 570 | 74.1 | 644.1 | 2020-09-24 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Worked on the AU1 road leading into C-055 (250m complete)Rock hammer for 7 hours, down mid day for welding repair. Labourers cleaed up garbage (mostly geo for half the day) | 5 | C050-C069 | Antler Lake | 0 | 44102 |  | 50 | 44105 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting515020200924-12Foreman6570 | Corbiere and Sons Contracting515020200924-12Foreman6570Inv#057 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 570 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5150 | 20200924-12 | 53510502 | Access | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2020-09-24 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Worked on the AU1 road leading into C-055 (250m complete)Rock hammer for 7 hours, down mid day for welding repair. Labourers cleaed up garbage (mostly geo for half the day) | 5 | C050-C069 | Antler Lake | 0 | 44102 |  | 50 | 44105 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting515020200924-12L.O.A.51050 | Corbiere and Sons Contracting515020200924-12L.O.A.51050Inv#057 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5150 | 20200924-12 | 53510502 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 23 | HR |  |  | 75 | 0 | 1725 | 224.25 | 1949.25 | 2020-09-24 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Worked on the AU1 road leading into C-055 (250m complete)Rock hammer for 7 hours, down mid day for welding repair. Labourers cleaed up garbage (mostly geo for half the day) | 5 | C050-C069 | Antler Lake | 0 | 44102 |  | 50 | 44105 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting515020200924-12Operator - Principle - After Jan 10231725 | Corbiere and Sons Contracting515020200924-12Operator - Principle - After Jan 10231725Inv#057 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 1725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5150 | 20200924-12 | 53510502 | Access | 0 | Labourer - General - After Jan 10 | 60 | 12 | HR |  |  | 60 | 0 | 720 | 93.6 | 813.6 | 2020-09-24 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Worked on the AU1 road leading into C-055 (250m complete)Rock hammer for 7 hours, down mid day for welding repair. Labourers cleaed up garbage (mostly geo for half the day) | 5 | C050-C069 | Antler Lake | 0 | 44102 |  | 50 | 44105 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting515020200924-12Labourer - General - After Jan 1012720 | Corbiere and Sons Contracting515020200924-12Labourer - General - After Jan 1012720Inv#057 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 720 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5151 | 20200924-13 | 53510504 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10.5 | Dynamic | 98.61 | 0 |  |  | 1380.54 | 179.4702 | 1560.0102 | 2020-09-24 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer spreading gravel towards C-052 (20ms away from being complete this section) Excavator loading rock trucks hauling to C-052 from stockpile | 5 | C050-C069 | Antler Lake | 0 | 44102 |  | 50 | 44102 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting515120200924-13Dozer D6 or equal- After Jan 1010.51380.54 | Corbiere and Sons Contracting515120200924-13Dozer D6 or equal- After Jan 1010.51380.54Inv#057 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1380.54 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5151 | 20200924-13 | 53510504 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10.5 | Dynamic | 103.84 | 0 |  |  | 1453.725 | 188.9843 | 1642.7093 | 2020-09-24 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer spreading gravel towards C-052 (20ms away from being complete this section) Excavator loading rock trucks hauling to C-052 from stockpile | 5 | C050-C069 | Antler Lake | 0 | 44102 |  | 50 | 44102 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting515120200924-13Excavator - 30 ton- After Jan 1010.51453.725 | Corbiere and Sons Contracting515120200924-13Excavator - 30 ton- After Jan 1010.51453.725Inv#057 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1453.725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5151 | 20200924-13 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-09-24 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer spreading gravel towards C-052 (20ms away from being complete this section) Excavator loading rock trucks hauling to C-052 from stockpile | 5 | C050-C069 | Antler Lake | 0 | 44102 |  | 50 | 44102 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting515120200924-13Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting515120200924-13Light Truck - Pick up- After Jan 102487.5Inv#057 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5151 | 20200924-13 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 21 | Dynamic | 103.54 | 0 |  |  | 2899.05 | 376.8765 | 3275.9265 | 2020-09-24 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer spreading gravel towards C-052 (20ms away from being complete this section) Excavator loading rock trucks hauling to C-052 from stockpile | 5 | C050-C069 | Antler Lake | 0 | 44102 |  | 50 | 44102 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting515120200924-13Rock Truck - 30 Ton- After Jan 10212899.05 | Corbiere and Sons Contracting515120200924-13Rock Truck - 30 Ton- After Jan 10212899.05Inv#057 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 2899.05 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5151 | 20200924-13 | 53510504 | Access | 0 | Foreman | 95 | 4 | HR |  |  | 95 | 0 | 380 | 49.4 | 429.4 | 2020-09-24 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer spreading gravel towards C-052 (20ms away from being complete this section) Excavator loading rock trucks hauling to C-052 from stockpile | 5 | C050-C069 | Antler Lake | 0 | 44102 |  | 50 | 44102 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting515120200924-13Foreman4380 | Corbiere and Sons Contracting515120200924-13Foreman4380Inv#057 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5151 | 20200924-13 | 53510504 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2020-09-24 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer spreading gravel towards C-052 (20ms away from being complete this section) Excavator loading rock trucks hauling to C-052 from stockpile | 5 | C050-C069 | Antler Lake | 0 | 44102 |  | 50 | 44102 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting515120200924-13L.O.A.4840 | Corbiere and Sons Contracting515120200924-13L.O.A.4840Inv#057 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5151 | 20200924-13 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 46 | HR |  |  | 75 | 0 | 3450 | 448.5 | 3898.5 | 2020-09-24 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer spreading gravel towards C-052 (20ms away from being complete this section) Excavator loading rock trucks hauling to C-052 from stockpile | 5 | C050-C069 | Antler Lake | 0 | 44102 |  | 50 | 44102 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting515120200924-13Operator - Principle - After Jan 10463450 | Corbiere and Sons Contracting515120200924-13Operator - Principle - After Jan 10463450Inv#057 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 3450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5163 | 20200924-25 | 53510504 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10.5 | Dynamic | 98.61 | 0 |  |  | 1380.54 | 179.4702 | 1560.0102 | 2020-09-24 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer spreading gravel from RT drops, Excavators loading rock trucks, 1 hauling C-092 - C-090 for spread, other hauling to installation of WC7362.01 | 5 | C076-C116 | Cook Lake | 0 | 44102 |  | 50 | 44103 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting516320200924-25Dozer D6 or equal- After Jan 1010.51380.54 | Corbiere and Sons Contracting516320200924-25Dozer D6 or equal- After Jan 1010.51380.54Inv#057 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1380.54 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5163 | 20200924-25 | 53510504 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10.5 | Dynamic | 103.84 | 0 |  |  | 1453.725 | 188.9843 | 1642.7093 | 2020-09-24 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer spreading gravel from RT drops, Excavators loading rock trucks, 1 hauling C-092 - C-090 for spread, other hauling to installation of WC7362.01 | 5 | C076-C116 | Cook Lake | 0 | 44102 |  | 50 | 44103 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting516320200924-25Excavator - 30 ton- After Jan 1010.51453.725 | Corbiere and Sons Contracting516320200924-25Excavator - 30 ton- After Jan 1010.51453.725Inv#057 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1453.725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5163 | 20200924-25 | 53510504 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10.5 | Dynamic | 110.22 | 0 |  |  | 1543.08 | 200.6004 | 1743.6804 | 2020-09-24 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer spreading gravel from RT drops, Excavators loading rock trucks, 1 hauling C-092 - C-090 for spread, other hauling to installation of WC7362.01 | 5 | C076-C116 | Cook Lake | 0 | 44102 |  | 50 | 44103 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting516320200924-25Excavator - 36 ton- After Jan 1010.51543.08 | Corbiere and Sons Contracting516320200924-25Excavator - 36 ton- After Jan 1010.51543.08Inv#057 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1543.08 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5163 | 20200924-25 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-09-24 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer spreading gravel from RT drops, Excavators loading rock trucks, 1 hauling C-092 - C-090 for spread, other hauling to installation of WC7362.01 | 5 | C076-C116 | Cook Lake | 0 | 44102 |  | 50 | 44103 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting516320200924-25Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting516320200924-25Light Truck - Pick up- After Jan 102487.5Inv#057 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5163 | 20200924-25 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 10.5 | Dynamic | 103.54 | 0 |  |  | 1449.525 | 188.4383 | 1637.9633 | 2020-09-24 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer spreading gravel from RT drops, Excavators loading rock trucks, 1 hauling C-092 - C-090 for spread, other hauling to installation of WC7362.01 | 5 | C076-C116 | Cook Lake | 0 | 44102 |  | 50 | 44103 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting516320200924-25Rock Truck - 30 Ton- After Jan 1010.51449.525 | Corbiere and Sons Contracting516320200924-25Rock Truck - 30 Ton- After Jan 1010.51449.525Inv#057 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1449.525 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5163 | 20200924-25 | 53510504 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2020-09-24 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer spreading gravel from RT drops, Excavators loading rock trucks, 1 hauling C-092 - C-090 for spread, other hauling to installation of WC7362.01 | 5 | C076-C116 | Cook Lake | 0 | 44102 |  | 50 | 44103 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting516320200924-25L.O.A.4840 | Corbiere and Sons Contracting516320200924-25L.O.A.4840Inv#057 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5163 | 20200924-25 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 34.5 | HR |  |  | 75 | 0 | 2587.5 | 336.375 | 2923.875 | 2020-09-24 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer spreading gravel from RT drops, Excavators loading rock trucks, 1 hauling C-092 - C-090 for spread, other hauling to installation of WC7362.01 | 5 | C076-C116 | Cook Lake | 0 | 44102 |  | 50 | 44103 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting516320200924-25Operator - Principle - After Jan 1034.52587.5 | Corbiere and Sons Contracting516320200924-25Operator - Principle - After Jan 1034.52587.5Inv#057 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 2587.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5163 | 20200924-25 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 11.5 | HR |  |  | 70 | 0 | 805 | 104.65 | 909.65 | 2020-09-24 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer spreading gravel from RT drops, Excavators loading rock trucks, 1 hauling C-092 - C-090 for spread, other hauling to installation of WC7362.01 | 5 | C076-C116 | Cook Lake | 0 | 44102 |  | 50 | 44103 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting516320200924-25Driver - AZ - After Jan 1011.5805 | Corbiere and Sons Contracting516320200924-25Driver - AZ - After Jan 1011.5805Inv#057 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 805 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5164 | 20200924-26 | 53510412 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10 | Dynamic | 110.22 | 0 |  |  | 1469.6 | 191.048 | 1660.648 | 2020-09-24 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Assisting Valards hammer at C-017 | 4 | C015-C029 | Nishin Creek Road East | 0 | 44102 |  | 36 | 44104 | [5 empty] | Mike Lecocq | 04 | Corbiere and Sons Contracting516420200924-26Excavator - 36 ton- After Jan 10101469.6 | Corbiere and Sons Contracting516420200924-26Excavator - 36 ton- After Jan 10101469.6Inv#057 | [5 empty] | 1 | 1469.6 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5164 | 20200924-26 | 53510412 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 9.16 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2020-09-24 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Assisting Valards hammer at C-017 | 4 | C015-C029 | Nishin Creek Road East | 0 | 44102 |  | 36 | 44104 | [5 empty] | Mike Lecocq | 04 | Corbiere and Sons Contracting516420200924-26Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting516420200924-26Excavator Thumb - 30 - 50 ton- After Jan 1010122.1Inv#057 | [5 empty] | 1 | 122.1 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5164 | 20200924-26 | 53510412 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-09-24 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Assisting Valards hammer at C-017 | 4 | C015-C029 | Nishin Creek Road East | 0 | 44102 |  | 36 | 44104 | [5 empty] | Mike Lecocq | 04 | Corbiere and Sons Contracting516420200924-26Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting516420200924-26Light Truck - Pick up- After Jan 101243.75Inv#057 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5164 | 20200924-26 | 53510412 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-09-24 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Assisting Valards hammer at C-017 | 4 | C015-C029 | Nishin Creek Road East | 0 | 44102 |  | 36 | 44104 | [5 empty] | Mike Lecocq | 04 | Corbiere and Sons Contracting516420200924-26L.O.A.1210 | Corbiere and Sons Contracting516420200924-26L.O.A.1210Inv#057 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5164 | 20200924-26 | 53510412 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 10 | HR |  |  | 75 | 0 | 750 | 97.5 | 847.5 | 2020-09-24 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Assisting Valards hammer at C-017 | 4 | C015-C029 | Nishin Creek Road East | 0 | 44102 |  | 36 | 44104 | [5 empty] | Mike Lecocq | 04 | Corbiere and Sons Contracting516420200924-26Operator - Principle - After Jan 1010750 | Corbiere and Sons Contracting516420200924-26Operator - Principle - After Jan 1010750Inv#057 | [5 empty] | 1 | 750 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5197 | 20200925-12 | 53510504 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 9.5 | Dynamic | 98.61 | 0 |  |  | 1249.06 | 162.3778 | 1411.4378 | 2020-09-25 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer spreading gravel towards C-052, rock trucks hauling gravel | 5 | C050-C069 | Antler Lake | 0 | 44104 |  | 50 | 44105 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting519720200925-12Dozer D6 or equal- After Jan 109.51249.06 | Corbiere and Sons Contracting519720200925-12Dozer D6 or equal- After Jan 109.51249.06Inv#057 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1249.06 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5197 | 20200925-12 | 53510504 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10.5 | Dynamic | 103.84 | 0 |  |  | 1453.725 | 188.9843 | 1642.7093 | 2020-09-25 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer spreading gravel towards C-052, rock trucks hauling gravel | 5 | C050-C069 | Antler Lake | 0 | 44104 |  | 50 | 44105 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting519720200925-12Excavator - 30 ton- After Jan 1010.51453.725 | Corbiere and Sons Contracting519720200925-12Excavator - 30 ton- After Jan 1010.51453.725Inv#057 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1453.725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5197 | 20200925-12 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-09-25 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer spreading gravel towards C-052, rock trucks hauling gravel | 5 | C050-C069 | Antler Lake | 0 | 44104 |  | 50 | 44105 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting519720200925-12Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting519720200925-12Light Truck - Pick up- After Jan 102487.5Inv#057 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5197 | 20200925-12 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 20 | Dynamic | 103.54 | 0 |  |  | 2761 | 358.93 | 3119.93 | 2020-09-25 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer spreading gravel towards C-052, rock trucks hauling gravel | 5 | C050-C069 | Antler Lake | 0 | 44104 |  | 50 | 44105 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting519720200925-12Rock Truck - 30 Ton- After Jan 10202761 | Corbiere and Sons Contracting519720200925-12Rock Truck - 30 Ton- After Jan 10202761Inv#057 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 2761 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5197 | 20200925-12 | 53510504 | Access | 0 | Foreman | 95 | 6 | HR |  |  | 95 | 0 | 570 | 74.1 | 644.1 | 2020-09-25 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer spreading gravel towards C-052, rock trucks hauling gravel | 5 | C050-C069 | Antler Lake | 0 | 44104 |  | 50 | 44105 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting519720200925-12Foreman6570 | Corbiere and Sons Contracting519720200925-12Foreman6570Inv#057 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 570 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5197 | 20200925-12 | 53510504 | Access | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2020-09-25 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer spreading gravel towards C-052, rock trucks hauling gravel | 5 | C050-C069 | Antler Lake | 0 | 44104 |  | 50 | 44105 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting519720200925-12L.O.A.51050 | Corbiere and Sons Contracting519720200925-12L.O.A.51050Inv#057 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5197 | 20200925-12 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 22 | HR |  |  | 75 | 0 | 1650 | 214.5 | 1864.5 | 2020-09-25 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer spreading gravel towards C-052, rock trucks hauling gravel | 5 | C050-C069 | Antler Lake | 0 | 44104 |  | 50 | 44105 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting519720200925-12Operator - Principle - After Jan 10221650 | Corbiere and Sons Contracting519720200925-12Operator - Principle - After Jan 10221650Inv#057 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1650 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5197 | 20200925-12 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 21 | HR |  |  | 70 | 0 | 1470 | 191.1 | 1661.1 | 2020-09-25 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer spreading gravel towards C-052, rock trucks hauling gravel | 5 | C050-C069 | Antler Lake | 0 | 44104 |  | 50 | 44105 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting519720200925-12Driver - AZ - After Jan 10211470 | Corbiere and Sons Contracting519720200925-12Driver - AZ - After Jan 10211470Inv#057 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1470 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5198 | 20200925-13 | 53510502 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10.5 | Dynamic | 110.22 | 0 |  |  | 1543.08 | 200.6004 | 1743.6804 | 2020-09-25 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock hammer all day - working towards big hill past the 40' bridge install | 5 | C050-C069 | Antler Lake | 0 | 44104 |  | 50 | 44105 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting519820200925-13Excavator - 36 ton- After Jan 1010.51543.08 | Corbiere and Sons Contracting519820200925-13Excavator - 36 ton- After Jan 1010.51543.08Inv#057 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 1543.08 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5198 | 20200925-13 | 53510502 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 10.5 | HR | 47.54 | 0 |  |  | 665.49 | 86.5137 | 752.0037 | 2020-09-25 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock hammer all day - working towards big hill past the 40' bridge install | 5 | C050-C069 | Antler Lake | 0 | 44104 |  | 50 | 44105 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting519820200925-13Excavator Hammer - 30 - 50 ton- After Jan 1010.5665.49 | Corbiere and Sons Contracting519820200925-13Excavator Hammer - 30 - 50 ton- After Jan 1010.5665.49Inv#057 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 665.49 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5198 | 20200925-13 | 53510502 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-09-25 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock hammer all day - working towards big hill past the 40' bridge install | 5 | C050-C069 | Antler Lake | 0 | 44104 |  | 50 | 44105 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting519820200925-13Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting519820200925-13Light Truck - Pick up- After Jan 101243.75Inv#057 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5198 | 20200925-13 | 53510502 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-09-25 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock hammer all day - working towards big hill past the 40' bridge install | 5 | C050-C069 | Antler Lake | 0 | 44104 |  | 50 | 44105 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting519820200925-13L.O.A.1210 | Corbiere and Sons Contracting519820200925-13L.O.A.1210Inv#057 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5198 | 20200925-13 | 53510502 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-09-25 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock hammer all day - working towards big hill past the 40' bridge install | 5 | C050-C069 | Antler Lake | 0 | 44104 |  | 50 | 44105 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting519820200925-13Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting519820200925-13Operator - Principle - After Jan 1011.5862.5Inv#057 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5200 | 20200925-15 | 53510504 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10.5 | Dynamic | 98.61 | 0 |  |  | 1380.54 | 179.4702 | 1560.0102 | 2020-09-25 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer spreading gravel, excavators loading rock trucks | 5 | C076-C116 | Cook Lake | 0 | 44104 |  | 50 | 44105 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting520020200925-15Dozer D6 or equal- After Jan 1010.51380.54 | Corbiere and Sons Contracting520020200925-15Dozer D6 or equal- After Jan 1010.51380.54Inv#057 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1380.54 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5200 | 20200925-15 | 53510504 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10.5 | Dynamic | 103.84 | 0 |  |  | 1453.725 | 188.9843 | 1642.7093 | 2020-09-25 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer spreading gravel, excavators loading rock trucks | 5 | C076-C116 | Cook Lake | 0 | 44104 |  | 50 | 44105 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting520020200925-15Excavator - 30 ton- After Jan 1010.51453.725 | Corbiere and Sons Contracting520020200925-15Excavator - 30 ton- After Jan 1010.51453.725Inv#057 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1453.725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5200 | 20200925-15 | 53510504 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10.5 | Dynamic | 110.22 | 0 |  |  | 1543.08 | 200.6004 | 1743.6804 | 2020-09-25 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer spreading gravel, excavators loading rock trucks | 5 | C076-C116 | Cook Lake | 0 | 44104 |  | 50 | 44105 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting520020200925-15Excavator - 36 ton- After Jan 1010.51543.08 | Corbiere and Sons Contracting520020200925-15Excavator - 36 ton- After Jan 1010.51543.08Inv#057 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1543.08 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5200 | 20200925-15 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-09-25 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer spreading gravel, excavators loading rock trucks | 5 | C076-C116 | Cook Lake | 0 | 44104 |  | 50 | 44105 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting520020200925-15Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting520020200925-15Light Truck - Pick up- After Jan 102487.5Inv#057 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5200 | 20200925-15 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 21 | Dynamic | 103.54 | 0 |  |  | 2899.05 | 376.8765 | 3275.9265 | 2020-09-25 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer spreading gravel, excavators loading rock trucks | 5 | C076-C116 | Cook Lake | 0 | 44104 |  | 50 | 44105 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting520020200925-15Rock Truck - 30 Ton- After Jan 10212899.05 | Corbiere and Sons Contracting520020200925-15Rock Truck - 30 Ton- After Jan 10212899.05Inv#057 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 2899.05 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5200 | 20200925-15 | 53510504 | Access | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2020-09-25 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer spreading gravel, excavators loading rock trucks | 5 | C076-C116 | Cook Lake | 0 | 44104 |  | 50 | 44105 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting520020200925-15L.O.A.51050 | Corbiere and Sons Contracting520020200925-15L.O.A.51050Inv#057 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5200 | 20200925-15 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 34.5 | HR |  |  | 75 | 0 | 2587.5 | 336.375 | 2923.875 | 2020-09-25 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer spreading gravel, excavators loading rock trucks | 5 | C076-C116 | Cook Lake | 0 | 44104 |  | 50 | 44105 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting520020200925-15Operator - Principle - After Jan 1034.52587.5 | Corbiere and Sons Contracting520020200925-15Operator - Principle - After Jan 1034.52587.5Inv#057 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 2587.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5200 | 20200925-15 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 23 | HR |  |  | 70 | 0 | 1610 | 209.3 | 1819.3 | 2020-09-25 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer spreading gravel, excavators loading rock trucks | 5 | C076-C116 | Cook Lake | 0 | 44104 |  | 50 | 44105 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting520020200925-15Driver - AZ - After Jan 10231610 | Corbiere and Sons Contracting520020200925-15Driver - AZ - After Jan 10231610Inv#057 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1610 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5201 | 20200925-16 | 53510502 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10.5 | Dynamic | 110.22 | 0 |  |  | 1543.08 | 200.6004 | 1743.6804 | 2020-09-25 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock hammer all day (down for 2 hours) | 5 | C076-C116 | Cook Lake | 0 | 44104 |  | 50 | 44105 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting520120200925-16Excavator - 36 ton- After Jan 1010.51543.08 | Corbiere and Sons Contracting520120200925-16Excavator - 36 ton- After Jan 1010.51543.08Inv#057 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 1543.08 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5201 | 20200925-16 | 53510502 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 10.5 | HR | 47.54 | 0 |  |  | 665.49 | 86.5137 | 752.0037 | 2020-09-25 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock hammer all day (down for 2 hours) | 5 | C076-C116 | Cook Lake | 0 | 44104 |  | 50 | 44105 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting520120200925-16Excavator Hammer - 30 - 50 ton- After Jan 1010.5665.49 | Corbiere and Sons Contracting520120200925-16Excavator Hammer - 30 - 50 ton- After Jan 1010.5665.49Inv#057 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 665.49 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5201 | 20200925-16 | 53510502 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-09-25 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock hammer all day (down for 2 hours) | 5 | C076-C116 | Cook Lake | 0 | 44104 |  | 50 | 44105 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting520120200925-16Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting520120200925-16Light Truck - Pick up- After Jan 101243.75Inv#057 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5201 | 20200925-16 | 53510502 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-09-25 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock hammer all day (down for 2 hours) | 5 | C076-C116 | Cook Lake | 0 | 44104 |  | 50 | 44105 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting520120200925-16L.O.A.1210 | Corbiere and Sons Contracting520120200925-16L.O.A.1210Inv#057 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5201 | 20200925-16 | 53510502 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-09-25 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock hammer all day (down for 2 hours) | 5 | C076-C116 | Cook Lake | 0 | 44104 |  | 50 | 44105 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting520120200925-16Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting520120200925-16Operator - Principle - After Jan 1011.5862.5Inv#057 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5228 | 20200926-12 | 53510504 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10.5 | Dynamic | 98.61 | 0 |  |  | 1380.54 | 179.4702 | 1560.0102 | 2020-09-26 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | DZ spreading gravel from C-053 - C-054, loading rock trucks for haul all day. | 5 | C050-C069 | Antler Lake | 0 | 44104 |  | 50 | 44104 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting522820200926-12Dozer D6 or equal- After Jan 1010.51380.54 | Corbiere and Sons Contracting522820200926-12Dozer D6 or equal- After Jan 1010.51380.54Inv#057 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1380.54 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5228 | 20200926-12 | 53510504 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10.5 | Dynamic | 103.84 | 0 |  |  | 1453.725 | 188.9843 | 1642.7093 | 2020-09-26 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | DZ spreading gravel from C-053 - C-054, loading rock trucks for haul all day. | 5 | C050-C069 | Antler Lake | 0 | 44104 |  | 50 | 44104 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting522820200926-12Excavator - 30 ton- After Jan 1010.51453.725 | Corbiere and Sons Contracting522820200926-12Excavator - 30 ton- After Jan 1010.51453.725Inv#057 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1453.725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5228 | 20200926-12 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-09-26 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | DZ spreading gravel from C-053 - C-054, loading rock trucks for haul all day. | 5 | C050-C069 | Antler Lake | 0 | 44104 |  | 50 | 44104 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting522820200926-12Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting522820200926-12Light Truck - Pick up- After Jan 102487.5Inv#057 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5228 | 20200926-12 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 21 | Dynamic | 103.54 | 0 |  |  | 2899.05 | 376.8765 | 3275.9265 | 2020-09-26 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | DZ spreading gravel from C-053 - C-054, loading rock trucks for haul all day. | 5 | C050-C069 | Antler Lake | 0 | 44104 |  | 50 | 44104 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting522820200926-12Rock Truck - 30 Ton- After Jan 10212899.05 | Corbiere and Sons Contracting522820200926-12Rock Truck - 30 Ton- After Jan 10212899.05Inv#057 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 2899.05 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5228 | 20200926-12 | 53510504 | Access | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2020-09-26 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | DZ spreading gravel from C-053 - C-054, loading rock trucks for haul all day. | 5 | C050-C069 | Antler Lake | 0 | 44104 |  | 50 | 44104 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting522820200926-12L.O.A.51050 | Corbiere and Sons Contracting522820200926-12L.O.A.51050Inv#057 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5228 | 20200926-12 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 27 | HR |  |  | 75 | 0 | 2025 | 263.25 | 2288.25 | 2020-09-26 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | DZ spreading gravel from C-053 - C-054, loading rock trucks for haul all day. | 5 | C050-C069 | Antler Lake | 0 | 44104 |  | 50 | 44104 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting522820200926-12Operator - Principle - After Jan 10272025 | Corbiere and Sons Contracting522820200926-12Operator - Principle - After Jan 10272025Inv#057 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 2025 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5228 | 20200926-12 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 23 | HR |  |  | 70 | 0 | 1610 | 209.3 | 1819.3 | 2020-09-26 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | DZ spreading gravel from C-053 - C-054, loading rock trucks for haul all day. | 5 | C050-C069 | Antler Lake | 0 | 44104 |  | 50 | 44104 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting522820200926-12Driver - AZ - After Jan 10231610 | Corbiere and Sons Contracting522820200926-12Driver - AZ - After Jan 10231610Inv#057 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1610 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5229 | 20200926-13 | 53510502 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 8.5 | Dynamic | 110.22 | 0 |  |  | 1249.16 | 162.3908 | 1411.5508 | 2020-09-26 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Continue on rock hammer which went down for 2 hours | 5 | C050-C069 | Antler Lake | 0 | 44104 |  | 50 | 44104 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting522920200926-13Excavator - 36 ton- After Jan 108.51249.16 | Corbiere and Sons Contracting522920200926-13Excavator - 36 ton- After Jan 108.51249.16Inv#057 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 1249.16 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5229 | 20200926-13 | 53510502 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 8.5 | HR | 47.54 | 0 |  |  | 538.73 | 70.0349 | 608.7649 | 2020-09-26 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Continue on rock hammer which went down for 2 hours | 5 | C050-C069 | Antler Lake | 0 | 44104 |  | 50 | 44104 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting522920200926-13Excavator Hammer - 30 - 50 ton- After Jan 108.5538.73 | Corbiere and Sons Contracting522920200926-13Excavator Hammer - 30 - 50 ton- After Jan 108.5538.73Inv#057 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 538.73 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5229 | 20200926-13 | 53510502 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-09-26 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Continue on rock hammer which went down for 2 hours | 5 | C050-C069 | Antler Lake | 0 | 44104 |  | 50 | 44104 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting522920200926-13Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting522920200926-13Light Truck - Pick up- After Jan 101243.75Inv#057 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5229 | 20200926-13 | 53510502 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-09-26 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Continue on rock hammer which went down for 2 hours | 5 | C050-C069 | Antler Lake | 0 | 44104 |  | 50 | 44104 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting522920200926-13L.O.A.1210 | Corbiere and Sons Contracting522920200926-13L.O.A.1210Inv#057 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5229 | 20200926-13 | 53510502 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-09-26 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Continue on rock hammer which went down for 2 hours | 5 | C050-C069 | Antler Lake | 0 | 44104 |  | 50 | 44104 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting522920200926-13Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting522920200926-13Operator - Principle - After Jan 1011.5862.5Inv#057 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5230 | 20200926-14 | 53510503 | Access | 0 | Feller Buncher | 240 | 3 | HR | 180 | 0 |  |  | 720 | 93.6 | 813.6 | 2020-09-26 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Worked in wetland area for 3 hours putting down corduroy. | 5 | C050-C069 | Antler Lake | 0 | 44104 |  | 50 | 44104 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting523020200926-14Feller Buncher3720 | Corbiere and Sons Contracting523020200926-14Feller Buncher3720Inv#057 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 720 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5230 | 20200926-14 | 53510503 | Access | 0 | Skidder | 171 | 3 | HR | 128.25 | 0 |  |  | 513 | 66.69 | 579.69 | 2020-09-26 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Worked in wetland area for 3 hours putting down corduroy. | 5 | C050-C069 | Antler Lake | 0 | 44104 |  | 50 | 44104 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting523020200926-14Skidder 3513 | Corbiere and Sons Contracting523020200926-14Skidder 3513Inv#057 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 513 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5230 | 20200926-14 | 53510503 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 3 | Dynamic | 103.84 | 0 |  |  | 415.35 | 53.9955 | 469.3455 | 2020-09-26 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Worked in wetland area for 3 hours putting down corduroy. | 5 | C050-C069 | Antler Lake | 0 | 44104 |  | 50 | 44104 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting523020200926-14Excavator - 30 ton- After Jan 103415.35 | Corbiere and Sons Contracting523020200926-14Excavator - 30 ton- After Jan 103415.35Inv#057 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 415.35 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5230 | 20200926-14 | 53510503 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 3 | HR | 9.16 | 0 |  |  | 36.63 | 4.7619 | 41.3919 | 2020-09-26 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Worked in wetland area for 3 hours putting down corduroy. | 5 | C050-C069 | Antler Lake | 0 | 44104 |  | 50 | 44104 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting523020200926-14Excavator Thumb - 30 - 50 ton- After Jan 10336.63 | Corbiere and Sons Contracting523020200926-14Excavator Thumb - 30 - 50 ton- After Jan 10336.63Inv#057 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 36.63 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5230 | 20200926-14 | 53510503 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-09-26 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Worked in wetland area for 3 hours putting down corduroy. | 5 | C050-C069 | Antler Lake | 0 | 44104 |  | 50 | 44104 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting523020200926-14Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting523020200926-14Light Truck - Pick up- After Jan 102487.5Inv#057 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5230 | 20200926-14 | 53510503 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2020-09-26 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Worked in wetland area for 3 hours putting down corduroy. | 5 | C050-C069 | Antler Lake | 0 | 44104 |  | 50 | 44104 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting523020200926-14L.O.A.3630 | Corbiere and Sons Contracting523020200926-14L.O.A.3630Inv#057 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5230 | 20200926-14 | 53510503 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2020-09-26 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Worked in wetland area for 3 hours putting down corduroy. | 5 | C050-C069 | Antler Lake | 0 | 44104 |  | 50 | 44104 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting523020200926-14Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting523020200926-14Operator - Principle - After Jan 1011825Inv#057 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5231 | 20200926-15 | 53510504 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10.5 | Dynamic | 98.61 | 0 |  |  | 1380.54 | 179.4702 | 1560.0102 | 2020-09-26 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Spreading gravel, loading rock trucks | 5 | C076-C116 | Cook Lake | 0 | 44104 |  | 50 | 44104 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting523120200926-15Dozer D6 or equal- After Jan 1010.51380.54 | Corbiere and Sons Contracting523120200926-15Dozer D6 or equal- After Jan 1010.51380.54Inv#057 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1380.54 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5231 | 20200926-15 | 53510504 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 7.5 | Dynamic | 103.84 | 0 |  |  | 1038.375 | 134.9888 | 1173.3637 | 2020-09-26 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Spreading gravel, loading rock trucks | 5 | C076-C116 | Cook Lake | 0 | 44104 |  | 50 | 44104 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting523120200926-15Excavator - 30 ton- After Jan 107.51038.375 | Corbiere and Sons Contracting523120200926-15Excavator - 30 ton- After Jan 107.51038.375Inv#057 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1038.375 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5231 | 20200926-15 | 53510504 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10.5 | Dynamic | 110.22 | 0 |  |  | 1543.08 | 200.6004 | 1743.6804 | 2020-09-26 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Spreading gravel, loading rock trucks | 5 | C076-C116 | Cook Lake | 0 | 44104 |  | 50 | 44104 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting523120200926-15Excavator - 36 ton- After Jan 1010.51543.08 | Corbiere and Sons Contracting523120200926-15Excavator - 36 ton- After Jan 1010.51543.08Inv#057 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1543.08 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5231 | 20200926-15 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-09-26 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Spreading gravel, loading rock trucks | 5 | C076-C116 | Cook Lake | 0 | 44104 |  | 50 | 44104 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting523120200926-15Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting523120200926-15Light Truck - Pick up- After Jan 102487.5Inv#057 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5231 | 20200926-15 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 21 | Dynamic | 103.54 | 0 |  |  | 2899.05 | 376.8765 | 3275.9265 | 2020-09-26 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Spreading gravel, loading rock trucks | 5 | C076-C116 | Cook Lake | 0 | 44104 |  | 50 | 44104 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting523120200926-15Rock Truck - 30 Ton- After Jan 10212899.05 | Corbiere and Sons Contracting523120200926-15Rock Truck - 30 Ton- After Jan 10212899.05Inv#057 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 2899.05 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5231 | 20200926-15 | 53510504 | Access | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2020-09-26 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Spreading gravel, loading rock trucks | 5 | C076-C116 | Cook Lake | 0 | 44104 |  | 50 | 44104 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting523120200926-15L.O.A.51050 | Corbiere and Sons Contracting523120200926-15L.O.A.51050Inv#057 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5231 | 20200926-15 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 31.5 | HR |  |  | 75 | 0 | 2362.5 | 307.125 | 2669.625 | 2020-09-26 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Spreading gravel, loading rock trucks | 5 | C076-C116 | Cook Lake | 0 | 44104 |  | 50 | 44104 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting523120200926-15Operator - Principle - After Jan 1031.52362.5 | Corbiere and Sons Contracting523120200926-15Operator - Principle - After Jan 1031.52362.5Inv#057 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 2362.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5231 | 20200926-15 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 23 | HR |  |  | 70 | 0 | 1610 | 209.3 | 1819.3 | 2020-09-26 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Spreading gravel, loading rock trucks | 5 | C076-C116 | Cook Lake | 0 | 44104 |  | 50 | 44104 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting523120200926-15Driver - AZ - After Jan 10231610 | Corbiere and Sons Contracting523120200926-15Driver - AZ - After Jan 10231610Inv#057 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1610 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5233 | 20200926-17 | 53510502 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10.5 | Dynamic | 110.22 | 0 |  |  | 1543.08 | 200.6004 | 1743.6804 | 2020-09-26 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock Hammer All Day | 5 | C076-C116 | Cook Lake Road | 0 | 44104 |  | 50 | 44104 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting523320200926-17Excavator - 36 ton- After Jan 1010.51543.08 | Corbiere and Sons Contracting523320200926-17Excavator - 36 ton- After Jan 1010.51543.08Inv#057 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 1543.08 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5233 | 20200926-17 | 53510502 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 10.5 | HR | 47.54 | 0 |  |  | 665.49 | 86.5137 | 752.0037 | 2020-09-26 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock Hammer All Day | 5 | C076-C116 | Cook Lake Road | 0 | 44104 |  | 50 | 44104 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting523320200926-17Excavator Hammer - 30 - 50 ton- After Jan 1010.5665.49 | Corbiere and Sons Contracting523320200926-17Excavator Hammer - 30 - 50 ton- After Jan 1010.5665.49Inv#057 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 665.49 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5233 | 20200926-17 | 53510502 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-09-26 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock Hammer All Day | 5 | C076-C116 | Cook Lake Road | 0 | 44104 |  | 50 | 44104 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting523320200926-17Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting523320200926-17Light Truck - Pick up- After Jan 101243.75Inv#057 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5233 | 20200926-17 | 53510502 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-09-26 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock Hammer All Day | 5 | C076-C116 | Cook Lake Road | 0 | 44104 |  | 50 | 44104 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting523320200926-17L.O.A.1210 | Corbiere and Sons Contracting523320200926-17L.O.A.1210Inv#057 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5233 | 20200926-17 | 53510502 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-09-26 | 1 | Inv#057 | 44106 | 108 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock Hammer All Day | 5 | C076-C116 | Cook Lake Road | 0 | 44104 |  | 50 | 44104 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting523320200926-17Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting523320200926-17Operator - Principle - After Jan 1011.5862.5Inv#057 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5269 | 20200927-12 | 53510504 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10.5 | Dynamic | 98.61 | 0 |  |  | 1380.54 | 179.4702 | 1560.0102 | 2020-09-27 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer from C-054 - went 180msBrian unloading rock trucks on excavatorRock trucks hauling all day towards C-054 | 5 | C050-C069 | Antler Lake | 0 | 44106 |  | 50 | 44107 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting526920200927-12Dozer D6 or equal- After Jan 1010.51380.54 | Corbiere and Sons Contracting526920200927-12Dozer D6 or equal- After Jan 1010.51380.54INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1380.54 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5269 | 20200927-12 | 53510504 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10.5 | Dynamic | 103.84 | 0 |  |  | 1453.725 | 188.9843 | 1642.7093 | 2020-09-27 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer from C-054 - went 180msBrian unloading rock trucks on excavatorRock trucks hauling all day towards C-054 | 5 | C050-C069 | Antler Lake | 0 | 44106 |  | 50 | 44107 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting526920200927-12Excavator - 30 ton- After Jan 1010.51453.725 | Corbiere and Sons Contracting526920200927-12Excavator - 30 ton- After Jan 1010.51453.725INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1453.725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5269 | 20200927-12 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2020-09-27 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer from C-054 - went 180msBrian unloading rock trucks on excavatorRock trucks hauling all day towards C-054 | 5 | C050-C069 | Antler Lake | 0 | 44106 |  | 50 | 44107 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting526920200927-12Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting526920200927-12Light Truck - Pick up- After Jan 103731.25INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 731.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5269 | 20200927-12 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 21 | Dynamic | 103.54 | 0 |  |  | 2899.05 | 376.8765 | 3275.9265 | 2020-09-27 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer from C-054 - went 180msBrian unloading rock trucks on excavatorRock trucks hauling all day towards C-054 | 5 | C050-C069 | Antler Lake | 0 | 44106 |  | 50 | 44107 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting526920200927-12Rock Truck - 30 Ton- After Jan 10212899.05 | Corbiere and Sons Contracting526920200927-12Rock Truck - 30 Ton- After Jan 10212899.05INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 2899.05 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5269 | 20200927-12 | 53510504 | Access | 0 | Foreman | 95 | 6 | HR |  |  | 95 | 0 | 570 | 74.1 | 644.1 | 2020-09-27 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer from C-054 - went 180msBrian unloading rock trucks on excavatorRock trucks hauling all day towards C-054 | 5 | C050-C069 | Antler Lake | 0 | 44106 |  | 50 | 44107 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting526920200927-12Foreman6570 | Corbiere and Sons Contracting526920200927-12Foreman6570INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 570 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5269 | 20200927-12 | 53510504 | Access | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2020-09-27 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer from C-054 - went 180msBrian unloading rock trucks on excavatorRock trucks hauling all day towards C-054 | 5 | C050-C069 | Antler Lake | 0 | 44106 |  | 50 | 44107 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting526920200927-12L.O.A.51050 | Corbiere and Sons Contracting526920200927-12L.O.A.51050INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5269 | 20200927-12 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 23 | HR |  |  | 75 | 0 | 1725 | 224.25 | 1949.25 | 2020-09-27 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer from C-054 - went 180msBrian unloading rock trucks on excavatorRock trucks hauling all day towards C-054 | 5 | C050-C069 | Antler Lake | 0 | 44106 |  | 50 | 44107 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting526920200927-12Operator - Principle - After Jan 10231725 | Corbiere and Sons Contracting526920200927-12Operator - Principle - After Jan 10231725INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5269 | 20200927-12 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 23 | HR |  |  | 70 | 0 | 1610 | 209.3 | 1819.3 | 2020-09-27 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer from C-054 - went 180msBrian unloading rock trucks on excavatorRock trucks hauling all day towards C-054 | 5 | C050-C069 | Antler Lake | 0 | 44106 |  | 50 | 44107 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting526920200927-12Driver - AZ - After Jan 10231610 | Corbiere and Sons Contracting526920200927-12Driver - AZ - After Jan 10231610INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1610 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5270 | 20200927-13 | 53510502 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10.5 | Dynamic | 110.22 | 0 |  |  | 1543.08 | 200.6004 | 1743.6804 | 2020-09-27 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock hammer at Big hill past the 40' bridge | 5 | C050-C069 | Antler Lake | 0 | 44106 |  | 50 | 44107 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting527020200927-13Excavator - 36 ton- After Jan 1010.51543.08 | Corbiere and Sons Contracting527020200927-13Excavator - 36 ton- After Jan 1010.51543.08INV#058 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 1543.08 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5270 | 20200927-13 | 53510502 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 10.5 | HR | 47.54 | 0 |  |  | 665.49 | 86.5137 | 752.0037 | 2020-09-27 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock hammer at Big hill past the 40' bridge | 5 | C050-C069 | Antler Lake | 0 | 44106 |  | 50 | 44107 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting527020200927-13Excavator Hammer - 30 - 50 ton- After Jan 1010.5665.49 | Corbiere and Sons Contracting527020200927-13Excavator Hammer - 30 - 50 ton- After Jan 1010.5665.49INV#058 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 665.49 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5270 | 20200927-13 | 53510502 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-09-27 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock hammer at Big hill past the 40' bridge | 5 | C050-C069 | Antler Lake | 0 | 44106 |  | 50 | 44107 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting527020200927-13Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting527020200927-13Light Truck - Pick up- After Jan 101243.75INV#058 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5270 | 20200927-13 | 53510502 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-09-27 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock hammer at Big hill past the 40' bridge | 5 | C050-C069 | Antler Lake | 0 | 44106 |  | 50 | 44107 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting527020200927-13L.O.A.1210 | Corbiere and Sons Contracting527020200927-13L.O.A.1210INV#058 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5270 | 20200927-13 | 53510502 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-09-27 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock hammer at Big hill past the 40' bridge | 5 | C050-C069 | Antler Lake | 0 | 44106 |  | 50 | 44107 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting527020200927-13Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting527020200927-13Operator - Principle - After Jan 1011.5862.5INV#058 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5272 | 20200927-15 | 53510504 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10.5 | Dynamic | 98.61 | 0 |  |  | 1380.54 | 179.4702 | 1560.0102 | 2020-09-27 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel hauling and spreading from C-088 - C-090Labourer bringing in and laying down geo | 5 | C076-C092 | Cook Lake | 0 | 44106 |  | 50 | 44107 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting527220200927-15Dozer D6 or equal- After Jan 1010.51380.54 | Corbiere and Sons Contracting527220200927-15Dozer D6 or equal- After Jan 1010.51380.54INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1380.54 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5272 | 20200927-15 | 53510504 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10.5 | Dynamic | 103.84 | 0 |  |  | 1453.725 | 188.9843 | 1642.7093 | 2020-09-27 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel hauling and spreading from C-088 - C-090Labourer bringing in and laying down geo | 5 | C076-C092 | Cook Lake | 0 | 44106 |  | 50 | 44107 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting527220200927-15Excavator - 30 ton- After Jan 1010.51453.725 | Corbiere and Sons Contracting527220200927-15Excavator - 30 ton- After Jan 1010.51453.725INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1453.725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5272 | 20200927-15 | 53510504 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10.5 | Dynamic | 110.22 | 0 |  |  | 1543.08 | 200.6004 | 1743.6804 | 2020-09-27 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel hauling and spreading from C-088 - C-090Labourer bringing in and laying down geo | 5 | C076-C092 | Cook Lake | 0 | 44106 |  | 50 | 44107 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting527220200927-15Excavator - 36 ton- After Jan 1010.51543.08 | Corbiere and Sons Contracting527220200927-15Excavator - 36 ton- After Jan 1010.51543.08INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1543.08 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5272 | 20200927-15 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-09-27 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel hauling and spreading from C-088 - C-090Labourer bringing in and laying down geo | 5 | C076-C092 | Cook Lake | 0 | 44106 |  | 50 | 44107 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting527220200927-15Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting527220200927-15Light Truck - Pick up- After Jan 102487.5INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5272 | 20200927-15 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 19 | Dynamic | 103.54 | 0 |  |  | 2622.95 | 340.9835 | 2963.9335 | 2020-09-27 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel hauling and spreading from C-088 - C-090Labourer bringing in and laying down geo | 5 | C076-C092 | Cook Lake | 0 | 44106 |  | 50 | 44107 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting527220200927-15Rock Truck - 30 Ton- After Jan 10192622.95 | Corbiere and Sons Contracting527220200927-15Rock Truck - 30 Ton- After Jan 10192622.95INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 2622.95 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5272 | 20200927-15 | 53510504 | Access | 0 | Foreman | 95 | 4 | HR |  |  | 95 | 0 | 380 | 49.4 | 429.4 | 2020-09-27 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel hauling and spreading from C-088 - C-090Labourer bringing in and laying down geo | 5 | C076-C092 | Cook Lake | 0 | 44106 |  | 50 | 44107 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting527220200927-15Foreman4380 | Corbiere and Sons Contracting527220200927-15Foreman4380INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5272 | 20200927-15 | 53510504 | Access | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2020-09-27 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel hauling and spreading from C-088 - C-090Labourer bringing in and laying down geo | 5 | C076-C092 | Cook Lake | 0 | 44106 |  | 50 | 44107 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting527220200927-15L.O.A.61260 | Corbiere and Sons Contracting527220200927-15L.O.A.61260INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5272 | 20200927-15 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 34.5 | HR |  |  | 75 | 0 | 2587.5 | 336.375 | 2923.875 | 2020-09-27 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel hauling and spreading from C-088 - C-090Labourer bringing in and laying down geo | 5 | C076-C092 | Cook Lake | 0 | 44106 |  | 50 | 44107 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting527220200927-15Operator - Principle - After Jan 1034.52587.5 | Corbiere and Sons Contracting527220200927-15Operator - Principle - After Jan 1034.52587.5INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 2587.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5272 | 20200927-15 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 23 | HR |  |  | 70 | 0 | 1610 | 209.3 | 1819.3 | 2020-09-27 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel hauling and spreading from C-088 - C-090Labourer bringing in and laying down geo | 5 | C076-C092 | Cook Lake | 0 | 44106 |  | 50 | 44107 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting527220200927-15Driver - AZ - After Jan 10231610 | Corbiere and Sons Contracting527220200927-15Driver - AZ - After Jan 10231610INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1610 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5272 | 20200927-15 | 53510504 | Access | 0 | Labourer - General - After Jan 10 | 60 | 6 | HR |  |  | 60 | 0 | 360 | 46.8 | 406.8 | 2020-09-27 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel hauling and spreading from C-088 - C-090Labourer bringing in and laying down geo | 5 | C076-C092 | Cook Lake | 0 | 44106 |  | 50 | 44107 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting527220200927-15Labourer - General - After Jan 106360 | Corbiere and Sons Contracting527220200927-15Labourer - General - After Jan 106360INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 360 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5273 | 20200927-16 | 53510502 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10.5 | Dynamic | 110.22 | 0 |  |  | 1543.08 | 200.6004 | 1743.6804 | 2020-09-27 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock hammer from C-083 | 5 | 076-092 | Cook Lake | 0 | 44106 |  | 50 | 44107 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting527320200927-16Excavator - 36 ton- After Jan 1010.51543.08 | Corbiere and Sons Contracting527320200927-16Excavator - 36 ton- After Jan 1010.51543.08INV#058 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 1543.08 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5273 | 20200927-16 | 53510502 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 10.5 | HR | 47.54 | 0 |  |  | 665.49 | 86.5137 | 752.0037 | 2020-09-27 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock hammer from C-083 | 5 | 076-092 | Cook Lake | 0 | 44106 |  | 50 | 44107 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting527320200927-16Excavator Hammer - 30 - 50 ton- After Jan 1010.5665.49 | Corbiere and Sons Contracting527320200927-16Excavator Hammer - 30 - 50 ton- After Jan 1010.5665.49INV#058 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 665.49 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5273 | 20200927-16 | 53510502 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-09-27 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock hammer from C-083 | 5 | 076-092 | Cook Lake | 0 | 44106 |  | 50 | 44107 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting527320200927-16Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting527320200927-16Light Truck - Pick up- After Jan 101243.75INV#058 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5273 | 20200927-16 | 53510502 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-09-27 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock hammer from C-083 | 5 | 076-092 | Cook Lake | 0 | 44106 |  | 50 | 44107 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting527320200927-16L.O.A.1210 | Corbiere and Sons Contracting527320200927-16L.O.A.1210INV#058 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5273 | 20200927-16 | 53510502 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-09-27 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock hammer from C-083 | 5 | 076-092 | Cook Lake | 0 | 44106 |  | 50 | 44107 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting527320200927-16Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting527320200927-16Operator - Principle - After Jan 1011.5862.5INV#058 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5413 | 20200927-22 | 53510512 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10.5 | Dynamic | 98.61 | 0 |  |  | 1380.54 | 179.4702 | 1560.0102 | 2020-09-27 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Terry ran dozer doing road maintenance from C-039. | 5 | C036-C049 | Pays Plat River | 0 | 44110 |  | 36 | 44110 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting541320200927-22Dozer D6 or equal- After Jan 1010.51380.54 | Corbiere and Sons Contracting541320200927-22Dozer D6 or equal- After Jan 1010.51380.54INV#058 | [5 empty] | 1 | 1380.54 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5413 | 20200927-22 | 53510512 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-09-27 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Terry ran dozer doing road maintenance from C-039. | 5 | C036-C049 | Pays Plat River | 0 | 44110 |  | 36 | 44110 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting541320200927-22Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting541320200927-22Light Truck - Pick up- After Jan 101243.75INV#058 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5413 | 20200927-22 | 53510512 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-09-27 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Terry ran dozer doing road maintenance from C-039. | 5 | C036-C049 | Pays Plat River | 0 | 44110 |  | 36 | 44110 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting541320200927-22L.O.A.1210 | Corbiere and Sons Contracting541320200927-22L.O.A.1210INV#058 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5413 | 20200927-22 | 53510512 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-09-27 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Terry ran dozer doing road maintenance from C-039. | 5 | C036-C049 | Pays Plat River | 0 | 44110 |  | 36 | 44110 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting541320200927-22Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting541320200927-22Operator - Principle - After Jan 1011.5862.5INV#058 | [5 empty] | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6174 | 20200927-24 | 53510504 | Access | 0 | L.O.A. | 210 | 8 | DAY |  |  |  | 0 | 1680 | 218.4 | 1898.4 | 2020-09-27 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Triaxles from Taranis on standby due to shortage of hours - LOA agreed to be paid when no haul available to retain trucks. | 5 | C076-C116 | Cook Lake | 0 | 44136 |  | 51 | 44136 | [5 empty] | Betty Moghrabi | 05 | Corbiere and Sons Contracting617420200927-24L.O.A.81680 | Corbiere and Sons Contracting617420200927-24L.O.A.81680Inv#070 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1680 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5276 | 20200928-12 | 53510504 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 34.5 | Dynamic | 41.4 | 0 |  |  | 1904.4 | 247.572 | 2151.972 | 2020-09-28 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 3 trucks hauling to WF5 Antler Lake Rd | 5 | C050-C069 | Antler Lake | 0 | 44106 |  | 50 | 44107 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting527620200928-12Dump - Triaxle- After Jan 1034.51904.4 | Corbiere and Sons Contracting527620200928-12Dump - Triaxle- After Jan 1034.51904.4INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1904.4 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5276 | 20200928-12 | 53510504 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2020-09-28 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 3 trucks hauling to WF5 Antler Lake Rd | 5 | C050-C069 | Antler Lake | 0 | 44106 |  | 50 | 44107 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting527620200928-12L.O.A.3630 | Corbiere and Sons Contracting527620200928-12L.O.A.3630INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5276 | 20200928-12 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 34.5 | HR |  |  | 70 | 0 | 2415 | 313.95 | 2728.95 | 2020-09-28 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 3 trucks hauling to WF5 Antler Lake Rd | 5 | C050-C069 | Antler Lake | 0 | 44106 |  | 50 | 44107 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting527620200928-12Driver - AZ - After Jan 1034.52415 | Corbiere and Sons Contracting527620200928-12Driver - AZ - After Jan 1034.52415INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 2415 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5277 | 20200928-13 | 53510504 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10.5 | Dynamic | 98.61 | 0 |  |  | 1380.54 | 179.4702 | 1560.0102 | 2020-09-28 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Spreading gravel towards C-055 - C-056 - went 340mBrian and EX loading trucks all dayJoe and Dawson on rock trucks all day | 5 | C050-C069 | Antler Lake | 0 | 44106 |  | 50 | 44107 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting527720200928-13Dozer D6 or equal- After Jan 1010.51380.54 | Corbiere and Sons Contracting527720200928-13Dozer D6 or equal- After Jan 1010.51380.54INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1380.54 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5277 | 20200928-13 | 53510504 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10.5 | Dynamic | 103.84 | 0 |  |  | 1453.725 | 188.9843 | 1642.7093 | 2020-09-28 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Spreading gravel towards C-055 - C-056 - went 340mBrian and EX loading trucks all dayJoe and Dawson on rock trucks all day | 5 | C050-C069 | Antler Lake | 0 | 44106 |  | 50 | 44107 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting527720200928-13Excavator - 30 ton- After Jan 1010.51453.725 | Corbiere and Sons Contracting527720200928-13Excavator - 30 ton- After Jan 1010.51453.725INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1453.725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5277 | 20200928-13 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-09-28 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Spreading gravel towards C-055 - C-056 - went 340mBrian and EX loading trucks all dayJoe and Dawson on rock trucks all day | 5 | C050-C069 | Antler Lake | 0 | 44106 |  | 50 | 44107 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting527720200928-13Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting527720200928-13Light Truck - Pick up- After Jan 102487.5INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5277 | 20200928-13 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 21 | Dynamic | 103.54 | 0 |  |  | 2899.05 | 376.8765 | 3275.9265 | 2020-09-28 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Spreading gravel towards C-055 - C-056 - went 340mBrian and EX loading trucks all dayJoe and Dawson on rock trucks all day | 5 | C050-C069 | Antler Lake | 0 | 44106 |  | 50 | 44107 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting527720200928-13Rock Truck - 30 Ton- After Jan 10212899.05 | Corbiere and Sons Contracting527720200928-13Rock Truck - 30 Ton- After Jan 10212899.05INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 2899.05 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5277 | 20200928-13 | 53510504 | Access | 0 | Foreman | 95 | 6 | HR |  |  | 95 | 0 | 570 | 74.1 | 644.1 | 2020-09-28 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Spreading gravel towards C-055 - C-056 - went 340mBrian and EX loading trucks all dayJoe and Dawson on rock trucks all day | 5 | C050-C069 | Antler Lake | 0 | 44106 |  | 50 | 44107 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting527720200928-13Foreman6570 | Corbiere and Sons Contracting527720200928-13Foreman6570INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 570 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5277 | 20200928-13 | 53510504 | Access | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2020-09-28 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Spreading gravel towards C-055 - C-056 - went 340mBrian and EX loading trucks all dayJoe and Dawson on rock trucks all day | 5 | C050-C069 | Antler Lake | 0 | 44106 |  | 50 | 44107 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting527720200928-13L.O.A.51050 | Corbiere and Sons Contracting527720200928-13L.O.A.51050INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5277 | 20200928-13 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 23 | HR |  |  | 75 | 0 | 1725 | 224.25 | 1949.25 | 2020-09-28 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Spreading gravel towards C-055 - C-056 - went 340mBrian and EX loading trucks all dayJoe and Dawson on rock trucks all day | 5 | C050-C069 | Antler Lake | 0 | 44106 |  | 50 | 44107 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting527720200928-13Operator - Principle - After Jan 10231725 | Corbiere and Sons Contracting527720200928-13Operator - Principle - After Jan 10231725INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5277 | 20200928-13 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 23 | HR |  |  | 70 | 0 | 1610 | 209.3 | 1819.3 | 2020-09-28 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Spreading gravel towards C-055 - C-056 - went 340mBrian and EX loading trucks all dayJoe and Dawson on rock trucks all day | 5 | C050-C069 | Antler Lake | 0 | 44106 |  | 50 | 44107 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting527720200928-13Driver - AZ - After Jan 10231610 | Corbiere and Sons Contracting527720200928-13Driver - AZ - After Jan 10231610INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1610 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5278 | 20200928-14 | 53510502 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10.5 | Dynamic | 110.22 | 0 |  |  | 1543.08 | 200.6004 | 1743.6804 | 2020-09-28 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock hammer towards C-058 all day | 5 | C050-C069 | Antler Lake | 0 | 44106 |  | 50 | 44107 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting527820200928-14Excavator - 36 ton- After Jan 1010.51543.08 | Corbiere and Sons Contracting527820200928-14Excavator - 36 ton- After Jan 1010.51543.08INV#058 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 1543.08 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5278 | 20200928-14 | 53510502 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 10.5 | HR | 47.54 | 0 |  |  | 665.49 | 86.5137 | 752.0037 | 2020-09-28 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock hammer towards C-058 all day | 5 | C050-C069 | Antler Lake | 0 | 44106 |  | 50 | 44107 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting527820200928-14Excavator Hammer - 30 - 50 ton- After Jan 1010.5665.49 | Corbiere and Sons Contracting527820200928-14Excavator Hammer - 30 - 50 ton- After Jan 1010.5665.49INV#058 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 665.49 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5278 | 20200928-14 | 53510502 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-09-28 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock hammer towards C-058 all day | 5 | C050-C069 | Antler Lake | 0 | 44106 |  | 50 | 44107 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting527820200928-14Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting527820200928-14Light Truck - Pick up- After Jan 101243.75INV#058 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5278 | 20200928-14 | 53510502 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-09-28 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock hammer towards C-058 all day | 5 | C050-C069 | Antler Lake | 0 | 44106 |  | 50 | 44107 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting527820200928-14L.O.A.1210 | Corbiere and Sons Contracting527820200928-14L.O.A.1210INV#058 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5278 | 20200928-14 | 53510502 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-09-28 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock hammer towards C-058 all day | 5 | C050-C069 | Antler Lake | 0 | 44106 |  | 50 | 44107 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting527820200928-14Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting527820200928-14Operator - Principle - After Jan 1011.5862.5INV#058 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5282 | 20200928-18 | 53510504 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10.5 | Dynamic | 98.61 | 0 |  |  | 1380.54 | 179.4702 | 1560.0102 | 2020-09-28 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer spreading gravel all day from C-088 - C-090Rock trucks hauling all day, Excavators loading | 5 | C076-C166 | Cook Lake | 0 | 44106 |  | 50 | 44107 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting528220200928-18Dozer D6 or equal- After Jan 1010.51380.54 | Corbiere and Sons Contracting528220200928-18Dozer D6 or equal- After Jan 1010.51380.54INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1380.54 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5282 | 20200928-18 | 53510504 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10.5 | Dynamic | 103.84 | 0 |  |  | 1453.725 | 188.9843 | 1642.7093 | 2020-09-28 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer spreading gravel all day from C-088 - C-090Rock trucks hauling all day, Excavators loading | 5 | C076-C166 | Cook Lake | 0 | 44106 |  | 50 | 44107 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting528220200928-18Excavator - 30 ton- After Jan 1010.51453.725 | Corbiere and Sons Contracting528220200928-18Excavator - 30 ton- After Jan 1010.51453.725INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1453.725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5282 | 20200928-18 | 53510504 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 8.5 | Dynamic | 110.22 | 0 |  |  | 1249.16 | 162.3908 | 1411.5508 | 2020-09-28 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer spreading gravel all day from C-088 - C-090Rock trucks hauling all day, Excavators loading | 5 | C076-C166 | Cook Lake | 0 | 44106 |  | 50 | 44107 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting528220200928-18Excavator - 36 ton- After Jan 108.51249.16 | Corbiere and Sons Contracting528220200928-18Excavator - 36 ton- After Jan 108.51249.16INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1249.16 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5282 | 20200928-18 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-09-28 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer spreading gravel all day from C-088 - C-090Rock trucks hauling all day, Excavators loading | 5 | C076-C166 | Cook Lake | 0 | 44106 |  | 50 | 44107 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting528220200928-18Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting528220200928-18Light Truck - Pick up- After Jan 102487.5INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5282 | 20200928-18 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 17 | Dynamic | 103.54 | 0 |  |  | 2346.85 | 305.0905 | 2651.9405 | 2020-09-28 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer spreading gravel all day from C-088 - C-090Rock trucks hauling all day, Excavators loading | 5 | C076-C166 | Cook Lake | 0 | 44106 |  | 50 | 44107 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting528220200928-18Rock Truck - 30 Ton- After Jan 10172346.85 | Corbiere and Sons Contracting528220200928-18Rock Truck - 30 Ton- After Jan 10172346.85INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 2346.85 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5282 | 20200928-18 | 53510504 | Access | 0 | Foreman | 95 | 6 | HR |  |  | 95 | 0 | 570 | 74.1 | 644.1 | 2020-09-28 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer spreading gravel all day from C-088 - C-090Rock trucks hauling all day, Excavators loading | 5 | C076-C166 | Cook Lake | 0 | 44106 |  | 50 | 44107 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting528220200928-18Foreman6570 | Corbiere and Sons Contracting528220200928-18Foreman6570INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 570 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5282 | 20200928-18 | 53510504 | Access | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2020-09-28 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer spreading gravel all day from C-088 - C-090Rock trucks hauling all day, Excavators loading | 5 | C076-C166 | Cook Lake | 0 | 44106 |  | 50 | 44107 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting528220200928-18L.O.A.51050 | Corbiere and Sons Contracting528220200928-18L.O.A.51050INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5282 | 20200928-18 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 32.5 | HR |  |  | 75 | 0 | 2437.5 | 316.875 | 2754.375 | 2020-09-28 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer spreading gravel all day from C-088 - C-090Rock trucks hauling all day, Excavators loading | 5 | C076-C166 | Cook Lake | 0 | 44106 |  | 50 | 44107 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting528220200928-18Operator - Principle - After Jan 1032.52437.5 | Corbiere and Sons Contracting528220200928-18Operator - Principle - After Jan 1032.52437.5INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 2437.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5282 | 20200928-18 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 19 | HR |  |  | 70 | 0 | 1330 | 172.9 | 1502.9 | 2020-09-28 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer spreading gravel all day from C-088 - C-090Rock trucks hauling all day, Excavators loading | 5 | C076-C166 | Cook Lake | 0 | 44106 |  | 50 | 44107 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting528220200928-18Driver - AZ - After Jan 10191330 | Corbiere and Sons Contracting528220200928-18Driver - AZ - After Jan 10191330INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1330 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5282 | 20200928-18 | 53510504 | Access | 0 | Labourer - General - After Jan 10 | 60 | 2 | HR |  |  | 60 | 0 | 120 | 15.6 | 135.6 | 2020-09-28 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer spreading gravel all day from C-088 - C-090Rock trucks hauling all day, Excavators loading | 5 | C076-C166 | Cook Lake | 0 | 44106 |  | 50 | 44107 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting528220200928-18Labourer - General - After Jan 102120 | Corbiere and Sons Contracting528220200928-18Labourer - General - After Jan 102120INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 120 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5284 | 20200928-20 | 53510502 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10.5 | Dynamic | 110.22 | 0 |  |  | 1543.08 | 200.6004 | 1743.6804 | 2020-09-28 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock hammer all dayCleaned off rocks as they were being crushed | 5 | C076-C116 | Cook Lake | 0 | 44106 |  | 50 | 44107 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting528420200928-20Excavator - 36 ton- After Jan 1010.51543.08 | Corbiere and Sons Contracting528420200928-20Excavator - 36 ton- After Jan 1010.51543.08INV#058 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 1543.08 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5284 | 20200928-20 | 53510502 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 10.5 | HR | 47.54 | 0 |  |  | 665.49 | 86.5137 | 752.0037 | 2020-09-28 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock hammer all dayCleaned off rocks as they were being crushed | 5 | C076-C116 | Cook Lake | 0 | 44106 |  | 50 | 44107 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting528420200928-20Excavator Hammer - 30 - 50 ton- After Jan 1010.5665.49 | Corbiere and Sons Contracting528420200928-20Excavator Hammer - 30 - 50 ton- After Jan 1010.5665.49INV#058 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 665.49 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5284 | 20200928-20 | 53510502 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-09-28 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock hammer all dayCleaned off rocks as they were being crushed | 5 | C076-C116 | Cook Lake | 0 | 44106 |  | 50 | 44107 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting528420200928-20Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting528420200928-20Light Truck - Pick up- After Jan 101243.75INV#058 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5284 | 20200928-20 | 53510502 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-09-28 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock hammer all dayCleaned off rocks as they were being crushed | 5 | C076-C116 | Cook Lake | 0 | 44106 |  | 50 | 44107 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting528420200928-20L.O.A.1210 | Corbiere and Sons Contracting528420200928-20L.O.A.1210INV#058 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5284 | 20200928-20 | 53510502 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-09-28 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock hammer all dayCleaned off rocks as they were being crushed | 5 | C076-C116 | Cook Lake | 0 | 44106 |  | 50 | 44107 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting528420200928-20Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting528420200928-20Operator - Principle - After Jan 1011.5862.5INV#058 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5284 | 20200928-20 | 53510502 | Access | 0 | Labourer - General - After Jan 10 | 60 | 3.5 | HR |  |  | 60 | 0 | 210 | 27.3 | 237.3 | 2020-09-28 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock hammer all dayCleaned off rocks as they were being crushed | 5 | C076-C116 | Cook Lake | 0 | 44106 |  | 50 | 44107 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting528420200928-20Labourer - General - After Jan 103.5210 | Corbiere and Sons Contracting528420200928-20Labourer - General - After Jan 103.5210INV#058 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5304 | 20200929-12 | 53510504 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10.5 | Dynamic | 98.61 | 0 |  |  | 1380.54 | 179.4702 | 1560.0102 | 2020-09-29 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Spreading gravel from C-088 - C-090 and hen over to C-083Excavator working with rock trucks all day - reclaimed slope | 5 | C076-C116 | Cook Lake | 0 | 44107 |  | 50 | 44107 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting530420200929-12Dozer D6 or equal- After Jan 1010.51380.54 | Corbiere and Sons Contracting530420200929-12Dozer D6 or equal- After Jan 1010.51380.54INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1380.54 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5304 | 20200929-12 | 53510504 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10.5 | Dynamic | 103.84 | 0 |  |  | 1453.725 | 188.9843 | 1642.7093 | 2020-09-29 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Spreading gravel from C-088 - C-090 and hen over to C-083Excavator working with rock trucks all day - reclaimed slope | 5 | C076-C116 | Cook Lake | 0 | 44107 |  | 50 | 44107 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting530420200929-12Excavator - 30 ton- After Jan 1010.51453.725 | Corbiere and Sons Contracting530420200929-12Excavator - 30 ton- After Jan 1010.51453.725INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1453.725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5304 | 20200929-12 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-09-29 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Spreading gravel from C-088 - C-090 and hen over to C-083Excavator working with rock trucks all day - reclaimed slope | 5 | C076-C116 | Cook Lake | 0 | 44107 |  | 50 | 44107 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting530420200929-12Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting530420200929-12Light Truck - Pick up- After Jan 102487.5INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5304 | 20200929-12 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 17.5 | Dynamic | 103.54 | 0 |  |  | 2415.875 | 314.0638 | 2729.9387 | 2020-09-29 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Spreading gravel from C-088 - C-090 and hen over to C-083Excavator working with rock trucks all day - reclaimed slope | 5 | C076-C116 | Cook Lake | 0 | 44107 |  | 50 | 44107 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting530420200929-12Rock Truck - 30 Ton- After Jan 1017.52415.875 | Corbiere and Sons Contracting530420200929-12Rock Truck - 30 Ton- After Jan 1017.52415.875INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 2415.875 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5304 | 20200929-12 | 53510504 | Access | 0 | Foreman | 95 | 4 | HR |  |  | 95 | 0 | 380 | 49.4 | 429.4 | 2020-09-29 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Spreading gravel from C-088 - C-090 and hen over to C-083Excavator working with rock trucks all day - reclaimed slope | 5 | C076-C116 | Cook Lake | 0 | 44107 |  | 50 | 44107 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting530420200929-12Foreman4380 | Corbiere and Sons Contracting530420200929-12Foreman4380INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5304 | 20200929-12 | 53510504 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2020-09-29 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Spreading gravel from C-088 - C-090 and hen over to C-083Excavator working with rock trucks all day - reclaimed slope | 5 | C076-C116 | Cook Lake | 0 | 44107 |  | 50 | 44107 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting530420200929-12L.O.A.4840 | Corbiere and Sons Contracting530420200929-12L.O.A.4840INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5304 | 20200929-12 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 23 | HR |  |  | 75 | 0 | 1725 | 224.25 | 1949.25 | 2020-09-29 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Spreading gravel from C-088 - C-090 and hen over to C-083Excavator working with rock trucks all day - reclaimed slope | 5 | C076-C116 | Cook Lake | 0 | 44107 |  | 50 | 44107 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting530420200929-12Operator - Principle - After Jan 10231725 | Corbiere and Sons Contracting530420200929-12Operator - Principle - After Jan 10231725INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5304 | 20200929-12 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 19 | HR |  |  | 70 | 0 | 1330 | 172.9 | 1502.9 | 2020-09-29 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Spreading gravel from C-088 - C-090 and hen over to C-083Excavator working with rock trucks all day - reclaimed slope | 5 | C076-C116 | Cook Lake | 0 | 44107 |  | 50 | 44107 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting530420200929-12Driver - AZ - After Jan 10191330 | Corbiere and Sons Contracting530420200929-12Driver - AZ - After Jan 10191330INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1330 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5300 | 20200929-8 | 53510504 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10.5 | Dynamic | 98.61 | 0 |  |  | 1380.54 | 179.4702 | 1560.0102 | 2020-09-29 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel spread - 200m done from C-055Excavator loading rock trucks all day | 5 | C050-C069 | Antler Lake | 0 | 44107 |  | 50 | 44107 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting530020200929-8Dozer D6 or equal- After Jan 1010.51380.54 | Corbiere and Sons Contracting530020200929-8Dozer D6 or equal- After Jan 1010.51380.54INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1380.54 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5300 | 20200929-8 | 53510504 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10.5 | Dynamic | 103.84 | 0 |  |  | 1453.725 | 188.9843 | 1642.7093 | 2020-09-29 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel spread - 200m done from C-055Excavator loading rock trucks all day | 5 | C050-C069 | Antler Lake | 0 | 44107 |  | 50 | 44107 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting530020200929-8Excavator - 30 ton- After Jan 1010.51453.725 | Corbiere and Sons Contracting530020200929-8Excavator - 30 ton- After Jan 1010.51453.725INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1453.725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5300 | 20200929-8 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-09-29 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel spread - 200m done from C-055Excavator loading rock trucks all day | 5 | C050-C069 | Antler Lake | 0 | 44107 |  | 50 | 44107 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting530020200929-8Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting530020200929-8Light Truck - Pick up- After Jan 102487.5INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5300 | 20200929-8 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 21 | Dynamic | 103.54 | 0 |  |  | 2899.05 | 376.8765 | 3275.9265 | 2020-09-29 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel spread - 200m done from C-055Excavator loading rock trucks all day | 5 | C050-C069 | Antler Lake | 0 | 44107 |  | 50 | 44107 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting530020200929-8Rock Truck - 30 Ton- After Jan 10212899.05 | Corbiere and Sons Contracting530020200929-8Rock Truck - 30 Ton- After Jan 10212899.05INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 2899.05 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5300 | 20200929-8 | 53510504 | Access | 0 | Foreman | 95 | 6 | HR |  |  | 95 | 0 | 570 | 74.1 | 644.1 | 2020-09-29 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel spread - 200m done from C-055Excavator loading rock trucks all day | 5 | C050-C069 | Antler Lake | 0 | 44107 |  | 50 | 44107 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting530020200929-8Foreman6570 | Corbiere and Sons Contracting530020200929-8Foreman6570INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 570 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5300 | 20200929-8 | 53510504 | Access | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2020-09-29 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel spread - 200m done from C-055Excavator loading rock trucks all day | 5 | C050-C069 | Antler Lake | 0 | 44107 |  | 50 | 44107 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting530020200929-8L.O.A.51050 | Corbiere and Sons Contracting530020200929-8L.O.A.51050INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5300 | 20200929-8 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 23 | HR |  |  | 75 | 0 | 1725 | 224.25 | 1949.25 | 2020-09-29 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel spread - 200m done from C-055Excavator loading rock trucks all day | 5 | C050-C069 | Antler Lake | 0 | 44107 |  | 50 | 44107 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting530020200929-8Operator - Principle - After Jan 10231725 | Corbiere and Sons Contracting530020200929-8Operator - Principle - After Jan 10231725INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5300 | 20200929-8 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 23 | HR |  |  | 70 | 0 | 1610 | 209.3 | 1819.3 | 2020-09-29 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel spread - 200m done from C-055Excavator loading rock trucks all day | 5 | C050-C069 | Antler Lake | 0 | 44107 |  | 50 | 44107 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting530020200929-8Driver - AZ - After Jan 10231610 | Corbiere and Sons Contracting530020200929-8Driver - AZ - After Jan 10231610INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1610 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5301 | 20200929-9 | 53510502 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10.5 | Dynamic | 110.22 | 0 |  |  | 1543.08 | 200.6004 | 1743.6804 | 2020-09-29 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock hammer all day towards C-058 | 5 | C050-C069 | Antler Lake | 0 | 44103 |  | 50 | 44107 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting530120200929-9Excavator - 36 ton- After Jan 1010.51543.08 | Corbiere and Sons Contracting530120200929-9Excavator - 36 ton- After Jan 1010.51543.08INV#058 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 1543.08 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5301 | 20200929-9 | 53510502 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 10.5 | HR | 47.54 | 0 |  |  | 665.49 | 86.5137 | 752.0037 | 2020-09-29 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock hammer all day towards C-058 | 5 | C050-C069 | Antler Lake | 0 | 44103 |  | 50 | 44107 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting530120200929-9Excavator Hammer - 30 - 50 ton- After Jan 1010.5665.49 | Corbiere and Sons Contracting530120200929-9Excavator Hammer - 30 - 50 ton- After Jan 1010.5665.49INV#058 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 665.49 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5301 | 20200929-9 | 53510502 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-09-29 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock hammer all day towards C-058 | 5 | C050-C069 | Antler Lake | 0 | 44103 |  | 50 | 44107 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting530120200929-9Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting530120200929-9Light Truck - Pick up- After Jan 101243.75INV#058 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5301 | 20200929-9 | 53510502 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-09-29 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock hammer all day towards C-058 | 5 | C050-C069 | Antler Lake | 0 | 44103 |  | 50 | 44107 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting530120200929-9L.O.A.1210 | Corbiere and Sons Contracting530120200929-9L.O.A.1210INV#058 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5301 | 20200929-9 | 53510502 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-09-29 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock hammer all day towards C-058 | 5 | C050-C069 | Antler Lake | 0 | 44103 |  | 50 | 44107 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting530120200929-9Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting530120200929-9Operator - Principle - After Jan 1011.5862.5INV#058 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5365 | 20200930-18 | 53510504 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10.5 | Dynamic | 98.61 | 0 |  |  | 1380.54 | 179.4702 | 1560.0102 | 2020-09-30 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks all day for gravel haulDozer spreading gravel C-055 - C056 | 5 | C050-C069 | Antler Lake | 0 | 44109 |  | 50 | 44109 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting536520200930-18Dozer D6 or equal- After Jan 1010.51380.54 | Corbiere and Sons Contracting536520200930-18Dozer D6 or equal- After Jan 1010.51380.54INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1380.54 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5365 | 20200930-18 | 53510504 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10.5 | Dynamic | 103.84 | 0 |  |  | 1453.725 | 188.9843 | 1642.7093 | 2020-09-30 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks all day for gravel haulDozer spreading gravel C-055 - C056 | 5 | C050-C069 | Antler Lake | 0 | 44109 |  | 50 | 44109 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting536520200930-18Excavator - 30 ton- After Jan 1010.51453.725 | Corbiere and Sons Contracting536520200930-18Excavator - 30 ton- After Jan 1010.51453.725INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1453.725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5365 | 20200930-18 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-09-30 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks all day for gravel haulDozer spreading gravel C-055 - C056 | 5 | C050-C069 | Antler Lake | 0 | 44109 |  | 50 | 44109 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting536520200930-18Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting536520200930-18Light Truck - Pick up- After Jan 102487.5INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5365 | 20200930-18 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 21 | Dynamic | 103.54 | 0 |  |  | 2899.05 | 376.8765 | 3275.9265 | 2020-09-30 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks all day for gravel haulDozer spreading gravel C-055 - C056 | 5 | C050-C069 | Antler Lake | 0 | 44109 |  | 50 | 44109 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting536520200930-18Rock Truck - 30 Ton- After Jan 10212899.05 | Corbiere and Sons Contracting536520200930-18Rock Truck - 30 Ton- After Jan 10212899.05INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 2899.05 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5365 | 20200930-18 | 53510504 | Access | 0 | Foreman | 95 | 6 | HR |  |  | 95 | 0 | 570 | 74.1 | 644.1 | 2020-09-30 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks all day for gravel haulDozer spreading gravel C-055 - C056 | 5 | C050-C069 | Antler Lake | 0 | 44109 |  | 50 | 44109 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting536520200930-18Foreman6570 | Corbiere and Sons Contracting536520200930-18Foreman6570INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 570 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5365 | 20200930-18 | 53510504 | Access | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2020-09-30 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks all day for gravel haulDozer spreading gravel C-055 - C056 | 5 | C050-C069 | Antler Lake | 0 | 44109 |  | 50 | 44109 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting536520200930-18L.O.A.51050 | Corbiere and Sons Contracting536520200930-18L.O.A.51050INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5365 | 20200930-18 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 23 | HR |  |  | 75 | 0 | 1725 | 224.25 | 1949.25 | 2020-09-30 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks all day for gravel haulDozer spreading gravel C-055 - C056 | 5 | C050-C069 | Antler Lake | 0 | 44109 |  | 50 | 44109 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting536520200930-18Operator - Principle - After Jan 10231725 | Corbiere and Sons Contracting536520200930-18Operator - Principle - After Jan 10231725INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5365 | 20200930-18 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 23 | HR |  |  | 70 | 0 | 1610 | 209.3 | 1819.3 | 2020-09-30 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks all day for gravel haulDozer spreading gravel C-055 - C056 | 5 | C050-C069 | Antler Lake | 0 | 44109 |  | 50 | 44109 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting536520200930-18Driver - AZ - After Jan 10231610 | Corbiere and Sons Contracting536520200930-18Driver - AZ - After Jan 10231610INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1610 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5366 | 20200930-19 | 53510502 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10.5 | Dynamic | 110.22 | 0 |  |  | 1543.08 | 200.6004 | 1743.6804 | 2020-09-30 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock hammer all day from C-056 | 5 | C050-C069 | Antler Lake | 0 | 44109 |  | 50 | 44109 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting536620200930-19Excavator - 36 ton- After Jan 1010.51543.08 | Corbiere and Sons Contracting536620200930-19Excavator - 36 ton- After Jan 1010.51543.08INV#058 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 1543.08 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5366 | 20200930-19 | 53510502 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 10.5 | HR | 47.54 | 0 |  |  | 665.49 | 86.5137 | 752.0037 | 2020-09-30 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock hammer all day from C-056 | 5 | C050-C069 | Antler Lake | 0 | 44109 |  | 50 | 44109 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting536620200930-19Excavator Hammer - 30 - 50 ton- After Jan 1010.5665.49 | Corbiere and Sons Contracting536620200930-19Excavator Hammer - 30 - 50 ton- After Jan 1010.5665.49INV#058 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 665.49 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5366 | 20200930-19 | 53510502 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-09-30 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock hammer all day from C-056 | 5 | C050-C069 | Antler Lake | 0 | 44109 |  | 50 | 44109 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting536620200930-19Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting536620200930-19Light Truck - Pick up- After Jan 101243.75INV#058 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5366 | 20200930-19 | 53510502 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-09-30 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock hammer all day from C-056 | 5 | C050-C069 | Antler Lake | 0 | 44109 |  | 50 | 44109 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting536620200930-19L.O.A.1210 | Corbiere and Sons Contracting536620200930-19L.O.A.1210INV#058 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5366 | 20200930-19 | 53510502 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-09-30 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock hammer all day from C-056 | 5 | C050-C069 | Antler Lake | 0 | 44109 |  | 50 | 44109 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting536620200930-19Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting536620200930-19Operator - Principle - After Jan 1011.5862.5INV#058 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5367 | 20200930-20 | 53510504 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 7.5 | Dynamic | 98.61 | 0 |  |  | 986.1 | 128.193 | 1114.293 | 2020-09-30 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel hauling from C-085 - C-083 Dozer spreading gravel from C-083 - C085Excavator loaded rock trucks | 5 | C076-C092 | Cook Lake | 0 | 44109 |  | 50 | 44109 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting536720200930-20Dozer D6 or equal- After Jan 107.5986.1 | Corbiere and Sons Contracting536720200930-20Dozer D6 or equal- After Jan 107.5986.1INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 986.1 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5367 | 20200930-20 | 53510504 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 6.5 | Dynamic | 103.84 | 0 |  |  | 899.925 | 116.9903 | 1016.9153 | 2020-09-30 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel hauling from C-085 - C-083 Dozer spreading gravel from C-083 - C085Excavator loaded rock trucks | 5 | C076-C092 | Cook Lake | 0 | 44109 |  | 50 | 44109 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting536720200930-20Excavator - 30 ton- After Jan 106.5899.925 | Corbiere and Sons Contracting536720200930-20Excavator - 30 ton- After Jan 106.5899.925INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 899.925 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5367 | 20200930-20 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-09-30 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel hauling from C-085 - C-083 Dozer spreading gravel from C-083 - C085Excavator loaded rock trucks | 5 | C076-C092 | Cook Lake | 0 | 44109 |  | 50 | 44109 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting536720200930-20Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting536720200930-20Light Truck - Pick up- After Jan 102487.5INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5367 | 20200930-20 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 14 | Dynamic | 103.54 | 0 |  |  | 1932.7 | 251.251 | 2183.951 | 2020-09-30 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel hauling from C-085 - C-083 Dozer spreading gravel from C-083 - C085Excavator loaded rock trucks | 5 | C076-C092 | Cook Lake | 0 | 44109 |  | 50 | 44109 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting536720200930-20Rock Truck - 30 Ton- After Jan 10141932.7 | Corbiere and Sons Contracting536720200930-20Rock Truck - 30 Ton- After Jan 10141932.7INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1932.7 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5367 | 20200930-20 | 53510504 | Access | 0 | Foreman | 95 | 4 | HR |  |  | 95 | 0 | 380 | 49.4 | 429.4 | 2020-09-30 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel hauling from C-085 - C-083 Dozer spreading gravel from C-083 - C085Excavator loaded rock trucks | 5 | C076-C092 | Cook Lake | 0 | 44109 |  | 50 | 44109 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting536720200930-20Foreman4380 | Corbiere and Sons Contracting536720200930-20Foreman4380INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5367 | 20200930-20 | 53510504 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2020-09-30 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel hauling from C-085 - C-083 Dozer spreading gravel from C-083 - C085Excavator loaded rock trucks | 5 | C076-C092 | Cook Lake | 0 | 44109 |  | 50 | 44109 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting536720200930-20L.O.A.4840 | Corbiere and Sons Contracting536720200930-20L.O.A.4840INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5367 | 20200930-20 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 15.5 | HR |  |  | 75 | 0 | 1162.5 | 151.125 | 1313.625 | 2020-09-30 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel hauling from C-085 - C-083 Dozer spreading gravel from C-083 - C085Excavator loaded rock trucks | 5 | C076-C092 | Cook Lake | 0 | 44109 |  | 50 | 44109 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting536720200930-20Operator - Principle - After Jan 1015.51162.5 | Corbiere and Sons Contracting536720200930-20Operator - Principle - After Jan 1015.51162.5INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1162.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5367 | 20200930-20 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 15.5 | HR |  |  | 70 | 0 | 1085 | 141.05 | 1226.05 | 2020-09-30 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel hauling from C-085 - C-083 Dozer spreading gravel from C-083 - C085Excavator loaded rock trucks | 5 | C076-C092 | Cook Lake | 0 | 44109 |  | 50 | 44109 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting536720200930-20Driver - AZ - After Jan 1015.51085 | Corbiere and Sons Contracting536720200930-20Driver - AZ - After Jan 1015.51085INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1085 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5368 | 20200930-21 | 53510512 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 3 | Dynamic | 98.61 | 0 |  |  | 394.44 | 51.2772 | 445.7172 | 2020-09-30 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance for 3 hours in the morning with dozer | 5 | C076-C116 | Cook Lake | 0 | 44109 |  | 50 | 44109 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting536820200930-21Dozer D6 or equal- After Jan 103394.44 | Corbiere and Sons Contracting536820200930-21Dozer D6 or equal- After Jan 103394.44INV#058 | [5 empty] | 1 | 394.44 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5368 | 20200930-21 | 53510512 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 3 | HR |  |  | 75 | 0 | 225 | 29.25 | 254.25 | 2020-09-30 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance for 3 hours in the morning with dozer | 5 | C076-C116 | Cook Lake | 0 | 44109 |  | 50 | 44109 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting536820200930-21Operator - Principle - After Jan 103225 | Corbiere and Sons Contracting536820200930-21Operator - Principle - After Jan 103225INV#058 | [5 empty] | 1 | 225 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5328 | 20200930-9 | 53510504 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 94.5 | Dynamic | 41.4 | 0 |  |  | 5216.4 | 678.132 | 5894.532 | 2020-09-30 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel hauling in WF5 to Antler Lake Road Access | 5 | C050-C069 | Antler Lake | 0 | 44107 |  | 50 | 44109 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting532820200930-9Dump - Triaxle- After Jan 1094.55216.4 | Corbiere and Sons Contracting532820200930-9Dump - Triaxle- After Jan 1094.55216.4INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 5216.4 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5328 | 20200930-9 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-09-30 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel hauling in WF5 to Antler Lake Road Access | 5 | C050-C069 | Antler Lake | 0 | 44107 |  | 50 | 44109 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting532820200930-9Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting532820200930-9Light Truck - Pick up- After Jan 101243.75INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5328 | 20200930-9 | 53510504 | Access | 0 | Construction Coordinator | 80 | 6 | HR |  |  | 80 | 0 | 480 | 62.4 | 542.4 | 2020-09-30 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel hauling in WF5 to Antler Lake Road Access | 5 | C050-C069 | Antler Lake | 0 | 44107 |  | 50 | 44109 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting532820200930-9Construction Coordinator6480 | Corbiere and Sons Contracting532820200930-9Construction Coordinator6480INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 480 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5328 | 20200930-9 | 53510504 | Access | 0 | L.O.A. | 210 | 10 | DAY |  |  |  | 0 | 2100 | 273 | 2373 | 2020-09-30 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel hauling in WF5 to Antler Lake Road Access | 5 | C050-C069 | Antler Lake | 0 | 44107 |  | 50 | 44109 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting532820200930-9L.O.A.102100 | Corbiere and Sons Contracting532820200930-9L.O.A.102100INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 2100 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5328 | 20200930-9 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 94.5 | HR |  |  | 70 | 0 | 6615 | 859.95 | 7474.95 | 2020-09-30 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel hauling in WF5 to Antler Lake Road Access | 5 | C050-C069 | Antler Lake | 0 | 44107 |  | 50 | 44109 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting532820200930-9Driver - AZ - After Jan 1094.56615 | Corbiere and Sons Contracting532820200930-9Driver - AZ - After Jan 1094.56615INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 6615 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5381 | 20201001-10 | 53510502 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 5 | Dynamic | 110.22 | 0 |  |  | 734.8 | 95.524 | 830.324 | 2020-10-01 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock hammer for 5 hours | 5 | C076-C116 | Cook Lake | 0 | 44109 |  | 50 | 44109 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting538120201001-10Excavator - 36 ton- After Jan 105734.8 | Corbiere and Sons Contracting538120201001-10Excavator - 36 ton- After Jan 105734.8INV#058 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 734.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5381 | 20201001-10 | 53510502 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 5 | HR | 47.54 | 0 |  |  | 316.9 | 41.197 | 358.097 | 2020-10-01 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock hammer for 5 hours | 5 | C076-C116 | Cook Lake | 0 | 44109 |  | 50 | 44109 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting538120201001-10Excavator Hammer - 30 - 50 ton- After Jan 105316.9 | Corbiere and Sons Contracting538120201001-10Excavator Hammer - 30 - 50 ton- After Jan 105316.9INV#058 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 316.9 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5381 | 20201001-10 | 53510502 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-10-01 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock hammer for 5 hours | 5 | C076-C116 | Cook Lake | 0 | 44109 |  | 50 | 44109 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting538120201001-10Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting538120201001-10Light Truck - Pick up- After Jan 101243.75INV#058 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5381 | 20201001-10 | 53510502 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-10-01 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock hammer for 5 hours | 5 | C076-C116 | Cook Lake | 0 | 44109 |  | 50 | 44109 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting538120201001-10L.O.A.1210 | Corbiere and Sons Contracting538120201001-10L.O.A.1210INV#058 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5381 | 20201001-10 | 53510502 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5 | HR |  |  | 75 | 0 | 375 | 48.75 | 423.75 | 2020-10-01 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock hammer for 5 hours | 5 | C076-C116 | Cook Lake | 0 | 44109 |  | 50 | 44109 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting538120201001-10Operator - Principle - After Jan 105375 | Corbiere and Sons Contracting538120201001-10Operator - Principle - After Jan 105375INV#058 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 375 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5384 | 20201001-13 | 53510503 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 5.5 | Dynamic | 103.84 | 0 |  |  | 761.475 | 98.9917 | 860.4668 | 2020-10-01 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Put down corduroy at C-081 | 5 | C076-C116 | Cook Lake | 0 | 44109 |  | 50 | 44109 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting538420201001-13Excavator - 30 ton- After Jan 105.5761.475 | Corbiere and Sons Contracting538420201001-13Excavator - 30 ton- After Jan 105.5761.475INV#058 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 761.475 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5384 | 20201001-13 | 53510503 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 5.5 | HR | 9.16 | 0 |  |  | 67.155 | 8.7302 | 75.8851 | 2020-10-01 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Put down corduroy at C-081 | 5 | C076-C116 | Cook Lake | 0 | 44109 |  | 50 | 44109 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting538420201001-13Excavator Thumb - 30 - 50 ton- After Jan 105.567.155 | Corbiere and Sons Contracting538420201001-13Excavator Thumb - 30 - 50 ton- After Jan 105.567.155INV#058 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 67.155 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5384 | 20201001-13 | 53510503 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-10-01 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Put down corduroy at C-081 | 5 | C076-C116 | Cook Lake | 0 | 44109 |  | 50 | 44109 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting538420201001-13L.O.A.1210 | Corbiere and Sons Contracting538420201001-13L.O.A.1210INV#058 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5384 | 20201001-13 | 53510503 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 75 | 0 | 450 | 58.5 | 508.5 | 2020-10-01 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Put down corduroy at C-081 | 5 | C076-C116 | Cook Lake | 0 | 44109 |  | 50 | 44109 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting538420201001-13Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting538420201001-13Operator - Principle - After Jan 106450INV#058 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5385 | 20201001-14 | 53510504 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10.5 | Dynamic | 98.61 | 0 |  |  | 1380.54 | 179.4702 | 1560.0102 | 2020-10-01 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer spreading gravel, excavator loading rock trucks, Chris and John hauling with rock trucks all day - C-083 - C-085 | 5 | C076-C116 | Cook Lake | 0 | 44109 |  | 50 | 44109 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting538520201001-14Dozer D6 or equal- After Jan 1010.51380.54 | Corbiere and Sons Contracting538520201001-14Dozer D6 or equal- After Jan 1010.51380.54INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1380.54 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5385 | 20201001-14 | 53510504 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10.5 | Dynamic | 103.84 | 0 |  |  | 1453.725 | 188.9843 | 1642.7093 | 2020-10-01 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer spreading gravel, excavator loading rock trucks, Chris and John hauling with rock trucks all day - C-083 - C-085 | 5 | C076-C116 | Cook Lake | 0 | 44109 |  | 50 | 44109 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting538520201001-14Excavator - 30 ton- After Jan 1010.51453.725 | Corbiere and Sons Contracting538520201001-14Excavator - 30 ton- After Jan 1010.51453.725INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1453.725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5385 | 20201001-14 | 53510504 | Access | 0 | ATV - Side by Side w/ roll bar- After Jan 10 | 18.45 | 6 | HR | 13.84 | 0 |  |  | 110.7 | 14.391 | 125.091 | 2020-10-01 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer spreading gravel, excavator loading rock trucks, Chris and John hauling with rock trucks all day - C-083 - C-085 | 5 | C076-C116 | Cook Lake | 0 | 44109 |  | 50 | 44109 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting538520201001-14ATV - Side by Side w/ roll bar- After Jan 106110.7 | Corbiere and Sons Contracting538520201001-14ATV - Side by Side w/ roll bar- After Jan 106110.7INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 110.7 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5385 | 20201001-14 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-10-01 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer spreading gravel, excavator loading rock trucks, Chris and John hauling with rock trucks all day - C-083 - C-085 | 5 | C076-C116 | Cook Lake | 0 | 44109 |  | 50 | 44109 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting538520201001-14Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting538520201001-14Light Truck - Pick up- After Jan 102487.5INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5385 | 20201001-14 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 18 | Dynamic | 103.54 | 0 |  |  | 2484.9 | 323.037 | 2807.937 | 2020-10-01 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer spreading gravel, excavator loading rock trucks, Chris and John hauling with rock trucks all day - C-083 - C-085 | 5 | C076-C116 | Cook Lake | 0 | 44109 |  | 50 | 44109 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting538520201001-14Rock Truck - 30 Ton- After Jan 10182484.9 | Corbiere and Sons Contracting538520201001-14Rock Truck - 30 Ton- After Jan 10182484.9INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 2484.9 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5385 | 20201001-14 | 53510504 | Access | 0 | Foreman | 95 | 6 | HR |  |  | 95 | 0 | 570 | 74.1 | 644.1 | 2020-10-01 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer spreading gravel, excavator loading rock trucks, Chris and John hauling with rock trucks all day - C-083 - C-085 | 5 | C076-C116 | Cook Lake | 0 | 44109 |  | 50 | 44109 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting538520201001-14Foreman6570 | Corbiere and Sons Contracting538520201001-14Foreman6570INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 570 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5385 | 20201001-14 | 53510504 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2020-10-01 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer spreading gravel, excavator loading rock trucks, Chris and John hauling with rock trucks all day - C-083 - C-085 | 5 | C076-C116 | Cook Lake | 0 | 44109 |  | 50 | 44109 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting538520201001-14L.O.A.4840 | Corbiere and Sons Contracting538520201001-14L.O.A.4840INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5385 | 20201001-14 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 23 | HR |  |  | 75 | 0 | 1725 | 224.25 | 1949.25 | 2020-10-01 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer spreading gravel, excavator loading rock trucks, Chris and John hauling with rock trucks all day - C-083 - C-085 | 5 | C076-C116 | Cook Lake | 0 | 44109 |  | 50 | 44109 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting538520201001-14Operator - Principle - After Jan 10231725 | Corbiere and Sons Contracting538520201001-14Operator - Principle - After Jan 10231725INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5385 | 20201001-14 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 19.5 | HR |  |  | 70 | 0 | 1365 | 177.45 | 1542.45 | 2020-10-01 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer spreading gravel, excavator loading rock trucks, Chris and John hauling with rock trucks all day - C-083 - C-085 | 5 | C076-C116 | Cook Lake | 0 | 44109 |  | 50 | 44109 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting538520201001-14Driver - AZ - After Jan 1019.51365 | Corbiere and Sons Contracting538520201001-14Driver - AZ - After Jan 1019.51365INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1365 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5386 | 20201001-15 | 53510504 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10.5 | Dynamic | 98.61 | 0 |  |  | 1380.54 | 179.4702 | 1560.0102 | 2020-10-01 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-001 loading rock trucks all day from C-056 stockpile, Dozer spreading gravel, rock trucks hauling gravel | 5 | C050-C069 | Antler Lake | 0 | 44109 |  | 50 | 44109 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting538620201001-15Dozer D6 or equal- After Jan 1010.51380.54 | Corbiere and Sons Contracting538620201001-15Dozer D6 or equal- After Jan 1010.51380.54INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1380.54 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5386 | 20201001-15 | 53510504 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10.5 | Dynamic | 103.84 | 0 |  |  | 1453.725 | 188.9843 | 1642.7093 | 2020-10-01 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-001 loading rock trucks all day from C-056 stockpile, Dozer spreading gravel, rock trucks hauling gravel | 5 | C050-C069 | Antler Lake | 0 | 44109 |  | 50 | 44109 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting538620201001-15Excavator - 30 ton- After Jan 1010.51453.725 | Corbiere and Sons Contracting538620201001-15Excavator - 30 ton- After Jan 1010.51453.725INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1453.725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5386 | 20201001-15 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-10-01 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-001 loading rock trucks all day from C-056 stockpile, Dozer spreading gravel, rock trucks hauling gravel | 5 | C050-C069 | Antler Lake | 0 | 44109 |  | 50 | 44109 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting538620201001-15Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting538620201001-15Light Truck - Pick up- After Jan 102487.5INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5386 | 20201001-15 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 21 | Dynamic | 103.54 | 0 |  |  | 2899.05 | 376.8765 | 3275.9265 | 2020-10-01 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-001 loading rock trucks all day from C-056 stockpile, Dozer spreading gravel, rock trucks hauling gravel | 5 | C050-C069 | Antler Lake | 0 | 44109 |  | 50 | 44109 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting538620201001-15Rock Truck - 30 Ton- After Jan 10212899.05 | Corbiere and Sons Contracting538620201001-15Rock Truck - 30 Ton- After Jan 10212899.05INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 2899.05 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5386 | 20201001-15 | 53510504 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2020-10-01 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-001 loading rock trucks all day from C-056 stockpile, Dozer spreading gravel, rock trucks hauling gravel | 5 | C050-C069 | Antler Lake | 0 | 44109 |  | 50 | 44109 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting538620201001-15L.O.A.4840 | Corbiere and Sons Contracting538620201001-15L.O.A.4840INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5386 | 20201001-15 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 23 | HR |  |  | 75 | 0 | 1725 | 224.25 | 1949.25 | 2020-10-01 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-001 loading rock trucks all day from C-056 stockpile, Dozer spreading gravel, rock trucks hauling gravel | 5 | C050-C069 | Antler Lake | 0 | 44109 |  | 50 | 44109 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting538620201001-15Operator - Principle - After Jan 10231725 | Corbiere and Sons Contracting538620201001-15Operator - Principle - After Jan 10231725INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5386 | 20201001-15 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 23 | HR |  |  | 70 | 0 | 1610 | 209.3 | 1819.3 | 2020-10-01 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-001 loading rock trucks all day from C-056 stockpile, Dozer spreading gravel, rock trucks hauling gravel | 5 | C050-C069 | Antler Lake | 0 | 44109 |  | 50 | 44109 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting538620201001-15Driver - AZ - After Jan 10231610 | Corbiere and Sons Contracting538620201001-15Driver - AZ - After Jan 10231610INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1610 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5388 | 20201001-17 | 53510502 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10.5 | Dynamic | 110.22 | 0 |  |  | 1543.08 | 200.6004 | 1743.6804 | 2020-10-01 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock hammer from C-058 all day | 5 | C050-C069 | Antler Lake | 0 | 44109 |  | 50 | 44109 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting538820201001-17Excavator - 36 ton- After Jan 1010.51543.08 | Corbiere and Sons Contracting538820201001-17Excavator - 36 ton- After Jan 1010.51543.08INV#058 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 1543.08 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5388 | 20201001-17 | 53510502 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 10.5 | HR | 47.54 | 0 |  |  | 665.49 | 86.5137 | 752.0037 | 2020-10-01 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock hammer from C-058 all day | 5 | C050-C069 | Antler Lake | 0 | 44109 |  | 50 | 44109 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting538820201001-17Excavator Hammer - 30 - 50 ton- After Jan 1010.5665.49 | Corbiere and Sons Contracting538820201001-17Excavator Hammer - 30 - 50 ton- After Jan 1010.5665.49INV#058 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 665.49 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5388 | 20201001-17 | 53510502 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-10-01 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock hammer from C-058 all day | 5 | C050-C069 | Antler Lake | 0 | 44109 |  | 50 | 44109 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting538820201001-17Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting538820201001-17Light Truck - Pick up- After Jan 101243.75INV#058 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5388 | 20201001-17 | 53510502 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-10-01 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock hammer from C-058 all day | 5 | C050-C069 | Antler Lake | 0 | 44109 |  | 50 | 44109 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting538820201001-17L.O.A.1210 | Corbiere and Sons Contracting538820201001-17L.O.A.1210INV#058 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5388 | 20201001-17 | 53510502 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-10-01 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock hammer from C-058 all day | 5 | C050-C069 | Antler Lake | 0 | 44109 |  | 50 | 44109 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting538820201001-17Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting538820201001-17Operator - Principle - After Jan 1011.5862.5INV#058 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5401 | 20201002-12 | 53510504 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10.5 | Dynamic | 98.61 | 0 |  |  | 1380.54 | 179.4702 | 1560.0102 | 2020-10-02 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Labourers rolling out and delivering geo, loading rock trucks with excavator, working on dozer spreading gravel from C-059, Joe and Dawson driving rock trucks | 5 | C050-C069 | Antler Lake | 0 | 44109 |  | 50 | 44109 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting540120201002-12Dozer D6 or equal- After Jan 1010.51380.54 | Corbiere and Sons Contracting540120201002-12Dozer D6 or equal- After Jan 1010.51380.54INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1380.54 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5401 | 20201002-12 | 53510504 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10.5 | Dynamic | 103.84 | 0 |  |  | 1453.725 | 188.9843 | 1642.7093 | 2020-10-02 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Labourers rolling out and delivering geo, loading rock trucks with excavator, working on dozer spreading gravel from C-059, Joe and Dawson driving rock trucks | 5 | C050-C069 | Antler Lake | 0 | 44109 |  | 50 | 44109 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting540120201002-12Excavator - 30 ton- After Jan 1010.51453.725 | Corbiere and Sons Contracting540120201002-12Excavator - 30 ton- After Jan 1010.51453.725INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1453.725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5401 | 20201002-12 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-10-02 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Labourers rolling out and delivering geo, loading rock trucks with excavator, working on dozer spreading gravel from C-059, Joe and Dawson driving rock trucks | 5 | C050-C069 | Antler Lake | 0 | 44109 |  | 50 | 44109 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting540120201002-12Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting540120201002-12Light Truck - Pick up- After Jan 102487.5INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5401 | 20201002-12 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 21 | Dynamic | 103.54 | 0 |  |  | 2899.05 | 376.8765 | 3275.9265 | 2020-10-02 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Labourers rolling out and delivering geo, loading rock trucks with excavator, working on dozer spreading gravel from C-059, Joe and Dawson driving rock trucks | 5 | C050-C069 | Antler Lake | 0 | 44109 |  | 50 | 44109 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting540120201002-12Rock Truck - 30 Ton- After Jan 10212899.05 | Corbiere and Sons Contracting540120201002-12Rock Truck - 30 Ton- After Jan 10212899.05INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 2899.05 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5401 | 20201002-12 | 53510504 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2020-10-02 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Labourers rolling out and delivering geo, loading rock trucks with excavator, working on dozer spreading gravel from C-059, Joe and Dawson driving rock trucks | 5 | C050-C069 | Antler Lake | 0 | 44109 |  | 50 | 44109 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting540120201002-12L.O.A.4840 | Corbiere and Sons Contracting540120201002-12L.O.A.4840INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5401 | 20201002-12 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 23 | HR |  |  | 75 | 0 | 1725 | 224.25 | 1949.25 | 2020-10-02 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Labourers rolling out and delivering geo, loading rock trucks with excavator, working on dozer spreading gravel from C-059, Joe and Dawson driving rock trucks | 5 | C050-C069 | Antler Lake | 0 | 44109 |  | 50 | 44109 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting540120201002-12Operator - Principle - After Jan 10231725 | Corbiere and Sons Contracting540120201002-12Operator - Principle - After Jan 10231725INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5401 | 20201002-12 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 23 | HR |  |  | 70 | 0 | 1610 | 209.3 | 1819.3 | 2020-10-02 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Labourers rolling out and delivering geo, loading rock trucks with excavator, working on dozer spreading gravel from C-059, Joe and Dawson driving rock trucks | 5 | C050-C069 | Antler Lake | 0 | 44109 |  | 50 | 44109 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting540120201002-12Driver - AZ - After Jan 10231610 | Corbiere and Sons Contracting540120201002-12Driver - AZ - After Jan 10231610INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1610 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5401 | 20201002-12 | 53510504 | Access | 0 | Labourer - General - After Jan 10 | 60 | 4 | HR |  |  | 60 | 0 | 240 | 31.2 | 271.2 | 2020-10-02 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Labourers rolling out and delivering geo, loading rock trucks with excavator, working on dozer spreading gravel from C-059, Joe and Dawson driving rock trucks | 5 | C050-C069 | Antler Lake | 0 | 44109 |  | 50 | 44109 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting540120201002-12Labourer - General - After Jan 104240 | Corbiere and Sons Contracting540120201002-12Labourer - General - After Jan 104240INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 240 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5402 | 20201002-13 | 53510502 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10.5 | Dynamic | 110.22 | 0 |  |  | 1543.08 | 200.6004 | 1743.6804 | 2020-10-02 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock hammer all day | 5 | C050-C069 | Antler Lake | 0 | 44109 |  | 50 | 44109 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting540220201002-13Excavator - 36 ton- After Jan 1010.51543.08 | Corbiere and Sons Contracting540220201002-13Excavator - 36 ton- After Jan 1010.51543.08INV#058 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 1543.08 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5402 | 20201002-13 | 53510502 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 10.5 | HR | 47.54 | 0 |  |  | 665.49 | 86.5137 | 752.0037 | 2020-10-02 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock hammer all day | 5 | C050-C069 | Antler Lake | 0 | 44109 |  | 50 | 44109 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting540220201002-13Excavator Hammer - 30 - 50 ton- After Jan 1010.5665.49 | Corbiere and Sons Contracting540220201002-13Excavator Hammer - 30 - 50 ton- After Jan 1010.5665.49INV#058 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 665.49 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5402 | 20201002-13 | 53510502 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-10-02 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock hammer all day | 5 | C050-C069 | Antler Lake | 0 | 44109 |  | 50 | 44109 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting540220201002-13Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting540220201002-13Light Truck - Pick up- After Jan 101243.75INV#058 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5402 | 20201002-13 | 53510502 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-10-02 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock hammer all day | 5 | C050-C069 | Antler Lake | 0 | 44109 |  | 50 | 44109 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting540220201002-13L.O.A.1210 | Corbiere and Sons Contracting540220201002-13L.O.A.1210INV#058 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5402 | 20201002-13 | 53510502 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-10-02 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock hammer all day | 5 | C050-C069 | Antler Lake | 0 | 44109 |  | 50 | 44109 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting540220201002-13Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting540220201002-13Operator - Principle - After Jan 1011.5862.5INV#058 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5395 | 20201002-6 | 53510502 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10.5 | Dynamic | 110.22 | 0 |  |  | 1543.08 | 200.6004 | 1743.6804 | 2020-10-02 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock hammer all day from C-093 | 5 | C093-C116 | Cook Lake | 0 | 44109 |  | 50 | 44109 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting539520201002-6Excavator - 36 ton- After Jan 1010.51543.08 | Corbiere and Sons Contracting539520201002-6Excavator - 36 ton- After Jan 1010.51543.08INV#058 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 1543.08 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5395 | 20201002-6 | 53510502 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 10.5 | HR | 47.54 | 0 |  |  | 665.49 | 86.5137 | 752.0037 | 2020-10-02 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock hammer all day from C-093 | 5 | C093-C116 | Cook Lake | 0 | 44109 |  | 50 | 44109 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting539520201002-6Excavator Hammer - 30 - 50 ton- After Jan 1010.5665.49 | Corbiere and Sons Contracting539520201002-6Excavator Hammer - 30 - 50 ton- After Jan 1010.5665.49INV#058 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 665.49 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5395 | 20201002-6 | 53510502 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-10-02 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock hammer all day from C-093 | 5 | C093-C116 | Cook Lake | 0 | 44109 |  | 50 | 44109 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting539520201002-6Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting539520201002-6Light Truck - Pick up- After Jan 101243.75INV#058 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5395 | 20201002-6 | 53510502 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-10-02 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock hammer all day from C-093 | 5 | C093-C116 | Cook Lake | 0 | 44109 |  | 50 | 44109 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting539520201002-6L.O.A.1210 | Corbiere and Sons Contracting539520201002-6L.O.A.1210INV#058 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5395 | 20201002-6 | 53510502 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-10-02 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock hammer all day from C-093 | 5 | C093-C116 | Cook Lake | 0 | 44109 |  | 50 | 44109 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting539520201002-6Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting539520201002-6Operator - Principle - After Jan 1011.5862.5INV#058 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5396 | 20201002-7 | 53510504 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10.5 | Dynamic | 98.61 | 0 |  |  | 1380.54 | 179.4702 | 1560.0102 | 2020-10-02 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer spreading gravel from C-081-C-080, excavator loading rock trucks at C-082, Chris and John hauling with rock trucks all day | 5 | C076-C092 | Cook Lake | 0 | 44109 |  | 50 | 44109 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting539620201002-7Dozer D6 or equal- After Jan 1010.51380.54 | Corbiere and Sons Contracting539620201002-7Dozer D6 or equal- After Jan 1010.51380.54INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1380.54 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5396 | 20201002-7 | 53510504 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10.5 | Dynamic | 103.84 | 0 |  |  | 1453.725 | 188.9843 | 1642.7093 | 2020-10-02 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer spreading gravel from C-081-C-080, excavator loading rock trucks at C-082, Chris and John hauling with rock trucks all day | 5 | C076-C092 | Cook Lake | 0 | 44109 |  | 50 | 44109 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting539620201002-7Excavator - 30 ton- After Jan 1010.51453.725 | Corbiere and Sons Contracting539620201002-7Excavator - 30 ton- After Jan 1010.51453.725INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1453.725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5396 | 20201002-7 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-10-02 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer spreading gravel from C-081-C-080, excavator loading rock trucks at C-082, Chris and John hauling with rock trucks all day | 5 | C076-C092 | Cook Lake | 0 | 44109 |  | 50 | 44109 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting539620201002-7Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting539620201002-7Light Truck - Pick up- After Jan 102487.5INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5396 | 20201002-7 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 18 | Dynamic | 103.54 | 0 |  |  | 2484.9 | 323.037 | 2807.937 | 2020-10-02 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer spreading gravel from C-081-C-080, excavator loading rock trucks at C-082, Chris and John hauling with rock trucks all day | 5 | C076-C092 | Cook Lake | 0 | 44109 |  | 50 | 44109 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting539620201002-7Rock Truck - 30 Ton- After Jan 10182484.9 | Corbiere and Sons Contracting539620201002-7Rock Truck - 30 Ton- After Jan 10182484.9INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 2484.9 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5396 | 20201002-7 | 53510504 | Access | 0 | Foreman | 95 | 4 | HR |  |  | 95 | 0 | 380 | 49.4 | 429.4 | 2020-10-02 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer spreading gravel from C-081-C-080, excavator loading rock trucks at C-082, Chris and John hauling with rock trucks all day | 5 | C076-C092 | Cook Lake | 0 | 44109 |  | 50 | 44109 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting539620201002-7Foreman4380 | Corbiere and Sons Contracting539620201002-7Foreman4380INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5396 | 20201002-7 | 53510504 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2020-10-02 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer spreading gravel from C-081-C-080, excavator loading rock trucks at C-082, Chris and John hauling with rock trucks all day | 5 | C076-C092 | Cook Lake | 0 | 44109 |  | 50 | 44109 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting539620201002-7L.O.A.4840 | Corbiere and Sons Contracting539620201002-7L.O.A.4840INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5396 | 20201002-7 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 23 | HR |  |  | 75 | 0 | 1725 | 224.25 | 1949.25 | 2020-10-02 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer spreading gravel from C-081-C-080, excavator loading rock trucks at C-082, Chris and John hauling with rock trucks all day | 5 | C076-C092 | Cook Lake | 0 | 44109 |  | 50 | 44109 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting539620201002-7Operator - Principle - After Jan 10231725 | Corbiere and Sons Contracting539620201002-7Operator - Principle - After Jan 10231725INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5396 | 20201002-7 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 19.5 | HR |  |  | 70 | 0 | 1365 | 177.45 | 1542.45 | 2020-10-02 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer spreading gravel from C-081-C-080, excavator loading rock trucks at C-082, Chris and John hauling with rock trucks all day | 5 | C076-C092 | Cook Lake | 0 | 44109 |  | 50 | 44109 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting539620201002-7Driver - AZ - After Jan 1019.51365 | Corbiere and Sons Contracting539620201002-7Driver - AZ - After Jan 1019.51365INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1365 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5398 | 20201002-9 | 53510503 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 3 | Dynamic | 103.84 | 0 |  |  | 415.35 | 53.9955 | 469.3455 | 2020-10-02 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Put down corduroy | 5 | C076-C116 | Cook Lake | 0 | 44109 |  | 50 | 44109 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting539820201002-9Excavator - 30 ton- After Jan 103415.35 | Corbiere and Sons Contracting539820201002-9Excavator - 30 ton- After Jan 103415.35INV#058 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 415.35 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5398 | 20201002-9 | 53510503 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 3 | HR | 9.16 | 0 |  |  | 36.63 | 4.7619 | 41.3919 | 2020-10-02 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Put down corduroy | 5 | C076-C116 | Cook Lake | 0 | 44109 |  | 50 | 44109 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting539820201002-9Excavator Thumb - 30 - 50 ton- After Jan 10336.63 | Corbiere and Sons Contracting539820201002-9Excavator Thumb - 30 - 50 ton- After Jan 10336.63INV#058 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 36.63 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5398 | 20201002-9 | 53510503 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 3.5 | HR |  |  | 75 | 0 | 262.5 | 34.125 | 296.625 | 2020-10-02 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Put down corduroy | 5 | C076-C116 | Cook Lake | 0 | 44109 |  | 50 | 44109 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting539820201002-9Operator - Principle - After Jan 103.5262.5 | Corbiere and Sons Contracting539820201002-9Operator - Principle - After Jan 103.5262.5INV#058 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 262.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5474 | 20201003-10 | 53510504 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10.5 | Dynamic | 98.61 | 0 |  |  | 1380.54 | 179.4702 | 1560.0102 | 2020-10-03 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading up rock trucks for stock piling, dozer spreading gravel from C-058, Rock trucks hauling | 5 | C050-C069 | Antler Lake | 0 | 44111 |  | 50 | 44115 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting547420201003-10Dozer D6 or equal- After Jan 1010.51380.54 | Corbiere and Sons Contracting547420201003-10Dozer D6 or equal- After Jan 1010.51380.54INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1380.54 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5474 | 20201003-10 | 53510504 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10.5 | Dynamic | 103.84 | 0 |  |  | 1453.725 | 188.9843 | 1642.7093 | 2020-10-03 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading up rock trucks for stock piling, dozer spreading gravel from C-058, Rock trucks hauling | 5 | C050-C069 | Antler Lake | 0 | 44111 |  | 50 | 44115 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting547420201003-10Excavator - 30 ton- After Jan 1010.51453.725 | Corbiere and Sons Contracting547420201003-10Excavator - 30 ton- After Jan 1010.51453.725INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1453.725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5474 | 20201003-10 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-10-03 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading up rock trucks for stock piling, dozer spreading gravel from C-058, Rock trucks hauling | 5 | C050-C069 | Antler Lake | 0 | 44111 |  | 50 | 44115 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting547420201003-10Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting547420201003-10Light Truck - Pick up- After Jan 102487.5INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5474 | 20201003-10 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 21 | Dynamic | 103.54 | 0 |  |  | 2899.05 | 376.8765 | 3275.9265 | 2020-10-03 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading up rock trucks for stock piling, dozer spreading gravel from C-058, Rock trucks hauling | 5 | C050-C069 | Antler Lake | 0 | 44111 |  | 50 | 44115 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting547420201003-10Rock Truck - 30 Ton- After Jan 10212899.05 | Corbiere and Sons Contracting547420201003-10Rock Truck - 30 Ton- After Jan 10212899.05INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 2899.05 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5474 | 20201003-10 | 53510504 | Access | 0 | Foreman | 95 | 6 | HR |  |  | 95 | 0 | 570 | 74.1 | 644.1 | 2020-10-03 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading up rock trucks for stock piling, dozer spreading gravel from C-058, Rock trucks hauling | 5 | C050-C069 | Antler Lake | 0 | 44111 |  | 50 | 44115 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting547420201003-10Foreman6570 | Corbiere and Sons Contracting547420201003-10Foreman6570INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 570 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5474 | 20201003-10 | 53510504 | Access | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2020-10-03 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading up rock trucks for stock piling, dozer spreading gravel from C-058, Rock trucks hauling | 5 | C050-C069 | Antler Lake | 0 | 44111 |  | 50 | 44115 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting547420201003-10L.O.A.51050 | Corbiere and Sons Contracting547420201003-10L.O.A.51050INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5474 | 20201003-10 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 23 | HR |  |  | 75 | 0 | 1725 | 224.25 | 1949.25 | 2020-10-03 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading up rock trucks for stock piling, dozer spreading gravel from C-058, Rock trucks hauling | 5 | C050-C069 | Antler Lake | 0 | 44111 |  | 50 | 44115 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting547420201003-10Operator - Principle - After Jan 10231725 | Corbiere and Sons Contracting547420201003-10Operator - Principle - After Jan 10231725INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5474 | 20201003-10 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 23 | HR |  |  | 70 | 0 | 1610 | 209.3 | 1819.3 | 2020-10-03 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading up rock trucks for stock piling, dozer spreading gravel from C-058, Rock trucks hauling | 5 | C050-C069 | Antler Lake | 0 | 44111 |  | 50 | 44115 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting547420201003-10Driver - AZ - After Jan 10231610 | Corbiere and Sons Contracting547420201003-10Driver - AZ - After Jan 10231610INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1610 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5475 | 20201003-11 | 53510502 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10.5 | Dynamic | 110.22 | 0 |  |  | 1543.08 | 200.6004 | 1743.6804 | 2020-10-03 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock hammer from C-058 hill | 5 | C050-C069 | Antler Lake | 0 | 44111 |  | 50 | 44115 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting547520201003-11Excavator - 36 ton- After Jan 1010.51543.08 | Corbiere and Sons Contracting547520201003-11Excavator - 36 ton- After Jan 1010.51543.08INV#058 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 1543.08 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5475 | 20201003-11 | 53510502 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 10.5 | HR | 47.54 | 0 |  |  | 665.49 | 86.5137 | 752.0037 | 2020-10-03 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock hammer from C-058 hill | 5 | C050-C069 | Antler Lake | 0 | 44111 |  | 50 | 44115 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting547520201003-11Excavator Hammer - 30 - 50 ton- After Jan 1010.5665.49 | Corbiere and Sons Contracting547520201003-11Excavator Hammer - 30 - 50 ton- After Jan 1010.5665.49INV#058 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 665.49 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5475 | 20201003-11 | 53510502 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-10-03 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock hammer from C-058 hill | 5 | C050-C069 | Antler Lake | 0 | 44111 |  | 50 | 44115 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting547520201003-11Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting547520201003-11Light Truck - Pick up- After Jan 101243.75INV#058 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5475 | 20201003-11 | 53510502 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-10-03 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock hammer from C-058 hill | 5 | C050-C069 | Antler Lake | 0 | 44111 |  | 50 | 44115 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting547520201003-11L.O.A.1210 | Corbiere and Sons Contracting547520201003-11L.O.A.1210INV#058 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5475 | 20201003-11 | 53510502 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-10-03 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock hammer from C-058 hill | 5 | C050-C069 | Antler Lake | 0 | 44111 |  | 50 | 44115 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting547520201003-11Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting547520201003-11Operator - Principle - After Jan 1011.5862.5INV#058 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5478 | 20201003-14 | 53510502 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10.5 | Dynamic | 103.84 | 0 |  |  | 1453.725 | 188.9843 | 1642.7093 | 2020-10-03 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer all day from C-093, Excavator working with hammer | 5 | C093-C116 | Cook Lake | 0 | 44111 |  | 50 | 44118 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting547820201003-14Excavator - 30 ton- After Jan 1010.51453.725 | Corbiere and Sons Contracting547820201003-14Excavator - 30 ton- After Jan 1010.51453.725INV#058 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 1453.725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5478 | 20201003-14 | 53510502 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10.5 | Dynamic | 110.22 | 0 |  |  | 1543.08 | 200.6004 | 1743.6804 | 2020-10-03 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer all day from C-093, Excavator working with hammer | 5 | C093-C116 | Cook Lake | 0 | 44111 |  | 50 | 44118 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting547820201003-14Excavator - 36 ton- After Jan 1010.51543.08 | Corbiere and Sons Contracting547820201003-14Excavator - 36 ton- After Jan 1010.51543.08INV#058 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 1543.08 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5478 | 20201003-14 | 53510502 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10.5 | HR | 9.16 | 0 |  |  | 128.205 | 16.6667 | 144.8716 | 2020-10-03 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer all day from C-093, Excavator working with hammer | 5 | C093-C116 | Cook Lake | 0 | 44111 |  | 50 | 44118 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting547820201003-14Excavator Thumb - 30 - 50 ton- After Jan 1010.5128.205 | Corbiere and Sons Contracting547820201003-14Excavator Thumb - 30 - 50 ton- After Jan 1010.5128.205INV#058 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 128.205 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5478 | 20201003-14 | 53510502 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 10.5 | HR | 47.54 | 0 |  |  | 665.49 | 86.5137 | 752.0037 | 2020-10-03 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer all day from C-093, Excavator working with hammer | 5 | C093-C116 | Cook Lake | 0 | 44111 |  | 50 | 44118 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting547820201003-14Excavator Hammer - 30 - 50 ton- After Jan 1010.5665.49 | Corbiere and Sons Contracting547820201003-14Excavator Hammer - 30 - 50 ton- After Jan 1010.5665.49INV#058 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 665.49 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5478 | 20201003-14 | 53510502 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-10-03 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer all day from C-093, Excavator working with hammer | 5 | C093-C116 | Cook Lake | 0 | 44111 |  | 50 | 44118 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting547820201003-14Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting547820201003-14Light Truck - Pick up- After Jan 101243.75INV#058 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5478 | 20201003-14 | 53510502 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-10-03 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer all day from C-093, Excavator working with hammer | 5 | C093-C116 | Cook Lake | 0 | 44111 |  | 50 | 44118 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting547820201003-14L.O.A.2420 | Corbiere and Sons Contracting547820201003-14L.O.A.2420INV#058 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5478 | 20201003-14 | 53510502 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 23 | HR |  |  | 75 | 0 | 1725 | 224.25 | 1949.25 | 2020-10-03 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer all day from C-093, Excavator working with hammer | 5 | C093-C116 | Cook Lake | 0 | 44111 |  | 50 | 44118 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting547820201003-14Operator - Principle - After Jan 10231725 | Corbiere and Sons Contracting547820201003-14Operator - Principle - After Jan 10231725INV#058 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 1725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5480 | 20201003-16 | 53510504 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10.5 | Dynamic | 98.61 | 0 |  |  | 1380.54 | 179.4702 | 1560.0102 | 2020-10-03 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks all day from C-080, Dozer spreading gravel all day from C-080, Rock trucks hauling gravel all day | 5 | C076-C092 | Cook Lake | 0 | 44111 |  | 50 | 44115 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting548020201003-16Dozer D6 or equal- After Jan 1010.51380.54 | Corbiere and Sons Contracting548020201003-16Dozer D6 or equal- After Jan 1010.51380.54INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1380.54 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5480 | 20201003-16 | 53510504 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10.5 | Dynamic | 103.84 | 0 |  |  | 1453.725 | 188.9843 | 1642.7093 | 2020-10-03 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks all day from C-080, Dozer spreading gravel all day from C-080, Rock trucks hauling gravel all day | 5 | C076-C092 | Cook Lake | 0 | 44111 |  | 50 | 44115 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting548020201003-16Excavator - 30 ton- After Jan 1010.51453.725 | Corbiere and Sons Contracting548020201003-16Excavator - 30 ton- After Jan 1010.51453.725INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1453.725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5480 | 20201003-16 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-10-03 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks all day from C-080, Dozer spreading gravel all day from C-080, Rock trucks hauling gravel all day | 5 | C076-C092 | Cook Lake | 0 | 44111 |  | 50 | 44115 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting548020201003-16Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting548020201003-16Light Truck - Pick up- After Jan 102487.5INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5480 | 20201003-16 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 18 | Dynamic | 103.54 | 0 |  |  | 2484.9 | 323.037 | 2807.937 | 2020-10-03 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks all day from C-080, Dozer spreading gravel all day from C-080, Rock trucks hauling gravel all day | 5 | C076-C092 | Cook Lake | 0 | 44111 |  | 50 | 44115 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting548020201003-16Rock Truck - 30 Ton- After Jan 10182484.9 | Corbiere and Sons Contracting548020201003-16Rock Truck - 30 Ton- After Jan 10182484.9INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 2484.9 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5480 | 20201003-16 | 53510504 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2020-10-03 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks all day from C-080, Dozer spreading gravel all day from C-080, Rock trucks hauling gravel all day | 5 | C076-C092 | Cook Lake | 0 | 44111 |  | 50 | 44115 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting548020201003-16L.O.A.4840 | Corbiere and Sons Contracting548020201003-16L.O.A.4840INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5480 | 20201003-16 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 23 | HR |  |  | 75 | 0 | 1725 | 224.25 | 1949.25 | 2020-10-03 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks all day from C-080, Dozer spreading gravel all day from C-080, Rock trucks hauling gravel all day | 5 | C076-C092 | Cook Lake | 0 | 44111 |  | 50 | 44115 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting548020201003-16Operator - Principle - After Jan 10231725 | Corbiere and Sons Contracting548020201003-16Operator - Principle - After Jan 10231725INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5480 | 20201003-16 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 19.5 | HR |  |  | 70 | 0 | 1365 | 177.45 | 1542.45 | 2020-10-03 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks all day from C-080, Dozer spreading gravel all day from C-080, Rock trucks hauling gravel all day | 5 | C076-C092 | Cook Lake | 0 | 44111 |  | 50 | 44115 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting548020201003-16Driver - AZ - After Jan 1019.51365 | Corbiere and Sons Contracting548020201003-16Driver - AZ - After Jan 1019.51365INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1365 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5483 | 20201003-19 | 53510512 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 5.5 | Dynamic | 110.22 | 0 |  |  | 808.28 | 105.0764 | 913.3564 | 2020-10-03 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance on 460 linkbelt | 5 | C076-C116 | Cook Lake | 0 | 44111 |  | 50 | 44115 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting548320201003-19Excavator - 36 ton- After Jan 105.5808.28 | Corbiere and Sons Contracting548320201003-19Excavator - 36 ton- After Jan 105.5808.28INV#058 | [5 empty] | 1 | 808.28 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5483 | 20201003-19 | 53510512 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-10-03 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance on 460 linkbelt | 5 | C076-C116 | Cook Lake | 0 | 44111 |  | 50 | 44115 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting548320201003-19L.O.A.1210 | Corbiere and Sons Contracting548320201003-19L.O.A.1210INV#058 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5483 | 20201003-19 | 53510512 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 75 | 0 | 450 | 58.5 | 508.5 | 2020-10-03 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance on 460 linkbelt | 5 | C076-C116 | Cook Lake | 0 | 44111 |  | 50 | 44115 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting548320201003-19Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting548320201003-19Operator - Principle - After Jan 106450INV#058 | [5 empty] | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5718 | 20201003-28 | 53510504 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 11.5 | Dynamic | 41.4 | 0 |  |  | 634.8 | 82.524 | 717.324 | 2020-10-03 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Missed ticket - Hauling from Gurney Lake Road pit to Antler Lake in WF5 - Travel from Thunder Bay | 5 | C050-C069 | Antler Lake | 0 | 44123 |  | 50 | 44125 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting571820201003-28Dump - Triaxle- After Jan 1011.5634.8 | Corbiere and Sons Contracting571820201003-28Dump - Triaxle- After Jan 1011.5634.8Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 634.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5718 | 20201003-28 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 11.5 | HR |  |  | 70 | 0 | 805 | 104.65 | 909.65 | 2020-10-03 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Missed ticket - Hauling from Gurney Lake Road pit to Antler Lake in WF5 - Travel from Thunder Bay | 5 | C050-C069 | Antler Lake | 0 | 44123 |  | 50 | 44125 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting571820201003-28Driver - AZ - After Jan 1011.5805 | Corbiere and Sons Contracting571820201003-28Driver - AZ - After Jan 1011.5805Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 805 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5471 | 20201003-7 | 53510504 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 66 | Dynamic | 41.4 | 0 |  |  | 3643.2 | 473.616 | 4116.816 | 2020-10-03 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hauling from Gurney Lake Road pit to Antler Lake in WF5 - Travel from Thunder Bay * 1 ticket from Taranis missing | 5 | C050-C069 | Antler Lake | 0 | 44111 |  | 50 | 44115 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting547120201003-7Dump - Triaxle- After Jan 10663643.2 | Corbiere and Sons Contracting547120201003-7Dump - Triaxle- After Jan 10663643.2INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 3643.2 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5471 | 20201003-7 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 66 | HR |  |  | 70 | 0 | 4620 | 600.6 | 5220.6 | 2020-10-03 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hauling from Gurney Lake Road pit to Antler Lake in WF5 - Travel from Thunder Bay * 1 ticket from Taranis missing | 5 | C050-C069 | Antler Lake | 0 | 44111 |  | 50 | 44115 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting547120201003-7Driver - AZ - After Jan 10664620 | Corbiere and Sons Contracting547120201003-7Driver - AZ - After Jan 10664620INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 4620 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5498 | 20201004-10 | 53510504 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10.5 | Dynamic | 98.61 | 0 |  |  | 1380.54 | 179.4702 | 1560.0102 | 2020-10-04 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks, dozer pushing gravel to C059 and then to C066 | 5 | C050-C069 | Antler Lake | 0 | 44111 |  | 50 | 44115 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting549820201004-10Dozer D6 or equal- After Jan 1010.51380.54 | Corbiere and Sons Contracting549820201004-10Dozer D6 or equal- After Jan 1010.51380.54INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1380.54 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5498 | 20201004-10 | 53510504 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10.5 | Dynamic | 103.84 | 0 |  |  | 1453.725 | 188.9843 | 1642.7093 | 2020-10-04 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks, dozer pushing gravel to C059 and then to C066 | 5 | C050-C069 | Antler Lake | 0 | 44111 |  | 50 | 44115 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting549820201004-10Excavator - 30 ton- After Jan 1010.51453.725 | Corbiere and Sons Contracting549820201004-10Excavator - 30 ton- After Jan 1010.51453.725INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1453.725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5498 | 20201004-10 | 53510504 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 5 | HR | 9.16 | 0 |  |  | 61.05 | 7.9365 | 68.9865 | 2020-10-04 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks, dozer pushing gravel to C059 and then to C066 | 5 | C050-C069 | Antler Lake | 0 | 44111 |  | 50 | 44115 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting549820201004-10Excavator Thumb - 30 - 50 ton- After Jan 10561.05 | Corbiere and Sons Contracting549820201004-10Excavator Thumb - 30 - 50 ton- After Jan 10561.05INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 61.05 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5498 | 20201004-10 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-10-04 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks, dozer pushing gravel to C059 and then to C066 | 5 | C050-C069 | Antler Lake | 0 | 44111 |  | 50 | 44115 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting549820201004-10Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting549820201004-10Light Truck - Pick up- After Jan 102487.5INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5498 | 20201004-10 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 13 | Dynamic | 103.54 | 0 |  |  | 1794.65 | 233.3045 | 2027.9545 | 2020-10-04 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks, dozer pushing gravel to C059 and then to C066 | 5 | C050-C069 | Antler Lake | 0 | 44111 |  | 50 | 44115 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting549820201004-10Rock Truck - 30 Ton- After Jan 10131794.65 | Corbiere and Sons Contracting549820201004-10Rock Truck - 30 Ton- After Jan 10131794.65INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1794.65 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5498 | 20201004-10 | 53510504 | Access | 0 | Foreman | 95 | 4 | HR |  |  | 95 | 0 | 380 | 49.4 | 429.4 | 2020-10-04 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks, dozer pushing gravel to C059 and then to C066 | 5 | C050-C069 | Antler Lake | 0 | 44111 |  | 50 | 44115 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting549820201004-10Foreman4380 | Corbiere and Sons Contracting549820201004-10Foreman4380INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5498 | 20201004-10 | 53510504 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2020-10-04 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks, dozer pushing gravel to C059 and then to C066 | 5 | C050-C069 | Antler Lake | 0 | 44111 |  | 50 | 44115 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting549820201004-10L.O.A.4840 | Corbiere and Sons Contracting549820201004-10L.O.A.4840INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5498 | 20201004-10 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 23 | HR |  |  | 75 | 0 | 1725 | 224.25 | 1949.25 | 2020-10-04 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks, dozer pushing gravel to C059 and then to C066 | 5 | C050-C069 | Antler Lake | 0 | 44111 |  | 50 | 44115 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting549820201004-10Operator - Principle - After Jan 10231725 | Corbiere and Sons Contracting549820201004-10Operator - Principle - After Jan 10231725INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5498 | 20201004-10 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 15 | HR |  |  | 70 | 0 | 1050 | 136.5 | 1186.5 | 2020-10-04 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks, dozer pushing gravel to C059 and then to C066 | 5 | C050-C069 | Antler Lake | 0 | 44111 |  | 50 | 44115 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting549820201004-10Driver - AZ - After Jan 10151050 | Corbiere and Sons Contracting549820201004-10Driver - AZ - After Jan 10151050INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5499 | 20201004-11 | 53510504 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10.5 | Dynamic | 98.61 | 0 |  |  | 1380.54 | 179.4702 | 1560.0102 | 2020-10-04 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks, dozer spreading gravel from C-080 - C-079 | 5 | C076-c092 | Cook Lake | 0 | 44111 |  | 50 | 44115 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting549920201004-11Dozer D6 or equal- After Jan 1010.51380.54 | Corbiere and Sons Contracting549920201004-11Dozer D6 or equal- After Jan 1010.51380.54INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1380.54 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5499 | 20201004-11 | 53510504 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10.5 | Dynamic | 103.84 | 0 |  |  | 1453.725 | 188.9843 | 1642.7093 | 2020-10-04 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks, dozer spreading gravel from C-080 - C-079 | 5 | C076-c092 | Cook Lake | 0 | 44111 |  | 50 | 44115 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting549920201004-11Excavator - 30 ton- After Jan 1010.51453.725 | Corbiere and Sons Contracting549920201004-11Excavator - 30 ton- After Jan 1010.51453.725INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1453.725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5499 | 20201004-11 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-10-04 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks, dozer spreading gravel from C-080 - C-079 | 5 | C076-c092 | Cook Lake | 0 | 44111 |  | 50 | 44115 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting549920201004-11Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting549920201004-11Light Truck - Pick up- After Jan 102487.5INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5499 | 20201004-11 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 21 | Dynamic | 103.54 | 0 |  |  | 2899.05 | 376.8765 | 3275.9265 | 2020-10-04 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks, dozer spreading gravel from C-080 - C-079 | 5 | C076-c092 | Cook Lake | 0 | 44111 |  | 50 | 44115 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting549920201004-11Rock Truck - 30 Ton- After Jan 10212899.05 | Corbiere and Sons Contracting549920201004-11Rock Truck - 30 Ton- After Jan 10212899.05INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 2899.05 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5499 | 20201004-11 | 53510504 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2020-10-04 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks, dozer spreading gravel from C-080 - C-079 | 5 | C076-c092 | Cook Lake | 0 | 44111 |  | 50 | 44115 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting549920201004-11L.O.A.4840 | Corbiere and Sons Contracting549920201004-11L.O.A.4840INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5499 | 20201004-11 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 23 | HR |  |  | 75 | 0 | 1725 | 224.25 | 1949.25 | 2020-10-04 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks, dozer spreading gravel from C-080 - C-079 | 5 | C076-c092 | Cook Lake | 0 | 44111 |  | 50 | 44115 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting549920201004-11Operator - Principle - After Jan 10231725 | Corbiere and Sons Contracting549920201004-11Operator - Principle - After Jan 10231725INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5499 | 20201004-11 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 23 | HR |  |  | 70 | 0 | 1610 | 209.3 | 1819.3 | 2020-10-04 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks, dozer spreading gravel from C-080 - C-079 | 5 | C076-c092 | Cook Lake | 0 | 44111 |  | 50 | 44115 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting549920201004-11Driver - AZ - After Jan 10231610 | Corbiere and Sons Contracting549920201004-11Driver - AZ - After Jan 10231610INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1610 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5500 | 20201004-12 | 53510502 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10.5 | Dynamic | 110.22 | 0 |  |  | 1543.08 | 200.6004 | 1743.6804 | 2020-10-04 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 460 Linkbelt working with the hammer all day. | 5 | C076-C116 | Cook Lake | 0 | 44111 |  | 50 | 44115 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting550020201004-12Excavator - 36 ton- After Jan 1010.51543.08 | Corbiere and Sons Contracting550020201004-12Excavator - 36 ton- After Jan 1010.51543.08INV#058 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 1543.08 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5500 | 20201004-12 | 53510502 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10.5 | Dynamic | 110.22 | 0 |  |  | 1543.08 | 200.6004 | 1743.6804 | 2020-10-04 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 460 Linkbelt working with the hammer all day. | 5 | C076-C116 | Cook Lake | 0 | 44111 |  | 50 | 44115 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting550020201004-12Excavator - 36 ton- After Jan 1010.51543.08 | Corbiere and Sons Contracting550020201004-12Excavator - 36 ton- After Jan 1010.51543.08INV#058 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 1543.08 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5500 | 20201004-12 | 53510502 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 10.5 | HR | 47.54 | 0 |  |  | 665.49 | 86.5137 | 752.0037 | 2020-10-04 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 460 Linkbelt working with the hammer all day. | 5 | C076-C116 | Cook Lake | 0 | 44111 |  | 50 | 44115 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting550020201004-12Excavator Hammer - 30 - 50 ton- After Jan 1010.5665.49 | Corbiere and Sons Contracting550020201004-12Excavator Hammer - 30 - 50 ton- After Jan 1010.5665.49INV#058 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 665.49 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5500 | 20201004-12 | 53510502 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-10-04 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 460 Linkbelt working with the hammer all day. | 5 | C076-C116 | Cook Lake | 0 | 44111 |  | 50 | 44115 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting550020201004-12Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting550020201004-12Light Truck - Pick up- After Jan 101243.75INV#058 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5500 | 20201004-12 | 53510502 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-10-04 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 460 Linkbelt working with the hammer all day. | 5 | C076-C116 | Cook Lake | 0 | 44111 |  | 50 | 44115 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting550020201004-12L.O.A.2420 | Corbiere and Sons Contracting550020201004-12L.O.A.2420INV#058 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5500 | 20201004-12 | 53510502 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 23 | HR |  |  | 75 | 0 | 1725 | 224.25 | 1949.25 | 2020-10-04 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 460 Linkbelt working with the hammer all day. | 5 | C076-C116 | Cook Lake | 0 | 44111 |  | 50 | 44115 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting550020201004-12Operator - Principle - After Jan 10231725 | Corbiere and Sons Contracting550020201004-12Operator - Principle - After Jan 10231725INV#058 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 1725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5556 | 20201005-20 | 53510504 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10.5 | Dynamic | 98.61 | 0 |  |  | 1380.54 | 179.4702 | 1560.0102 | 2020-10-05 | 1 | INV#064 | 44124 | 113 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Loaded rock trucks from stockpile all day, dozer spreading gravel all day from C-059. | 5 | C050-C069 | Antler Lake | 0 | 44116 |  | 50 | 44123 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting555620201005-20Dozer D6 or equal- After Jan 1010.51380.54 | Corbiere and Sons Contracting555620201005-20Dozer D6 or equal- After Jan 1010.51380.54INV#064 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1380.54 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5556 | 20201005-20 | 53510504 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10.5 | Dynamic | 103.84 | 0 |  |  | 1453.725 | 188.9843 | 1642.7093 | 2020-10-05 | 1 | INV#064 | 44124 | 113 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Loaded rock trucks from stockpile all day, dozer spreading gravel all day from C-059. | 5 | C050-C069 | Antler Lake | 0 | 44116 |  | 50 | 44123 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting555620201005-20Excavator - 30 ton- After Jan 1010.51453.725 | Corbiere and Sons Contracting555620201005-20Excavator - 30 ton- After Jan 1010.51453.725INV#064 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1453.725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5556 | 20201005-20 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-10-05 | 1 | INV#064 | 44124 | 113 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Loaded rock trucks from stockpile all day, dozer spreading gravel all day from C-059. | 5 | C050-C069 | Antler Lake | 0 | 44116 |  | 50 | 44123 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting555620201005-20Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting555620201005-20Light Truck - Pick up- After Jan 102487.5INV#064 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5556 | 20201005-20 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 10.5 | Dynamic | 103.54 | 0 |  |  | 1449.525 | 188.4383 | 1637.9633 | 2020-10-05 | 1 | INV#064 | 44124 | 113 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Loaded rock trucks from stockpile all day, dozer spreading gravel all day from C-059. | 5 | C050-C069 | Antler Lake | 0 | 44116 |  | 50 | 44123 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting555620201005-20Rock Truck - 30 Ton- After Jan 1010.51449.525 | Corbiere and Sons Contracting555620201005-20Rock Truck - 30 Ton- After Jan 1010.51449.525INV#064 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1449.525 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5556 | 20201005-20 | 53510504 | Access | 0 | Foreman | 95 | 6 | HR |  |  | 95 | 0 | 570 | 74.1 | 644.1 | 2020-10-05 | 1 | INV#064 | 44124 | 113 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Loaded rock trucks from stockpile all day, dozer spreading gravel all day from C-059. | 5 | C050-C069 | Antler Lake | 0 | 44116 |  | 50 | 44123 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting555620201005-20Foreman6570 | Corbiere and Sons Contracting555620201005-20Foreman6570INV#064 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 570 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5556 | 20201005-20 | 53510504 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2020-10-05 | 1 | INV#064 | 44124 | 113 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Loaded rock trucks from stockpile all day, dozer spreading gravel all day from C-059. | 5 | C050-C069 | Antler Lake | 0 | 44116 |  | 50 | 44123 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting555620201005-20L.O.A.3630 | Corbiere and Sons Contracting555620201005-20L.O.A.3630INV#064 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5556 | 20201005-20 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 23 | HR |  |  | 75 | 0 | 1725 | 224.25 | 1949.25 | 2020-10-05 | 1 | INV#064 | 44124 | 113 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Loaded rock trucks from stockpile all day, dozer spreading gravel all day from C-059. | 5 | C050-C069 | Antler Lake | 0 | 44116 |  | 50 | 44123 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting555620201005-20Operator - Principle - After Jan 10231725 | Corbiere and Sons Contracting555620201005-20Operator - Principle - After Jan 10231725INV#064 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5556 | 20201005-20 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 11.5 | HR |  |  | 70 | 0 | 805 | 104.65 | 909.65 | 2020-10-05 | 1 | INV#064 | 44124 | 113 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Loaded rock trucks from stockpile all day, dozer spreading gravel all day from C-059. | 5 | C050-C069 | Antler Lake | 0 | 44116 |  | 50 | 44123 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting555620201005-20Driver - AZ - After Jan 1011.5805 | Corbiere and Sons Contracting555620201005-20Driver - AZ - After Jan 1011.5805INV#064 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 805 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5558 | 20201005-22 | 53510502 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 2.5 | Dynamic | 110.22 | 0 |  |  | 367.4 | 47.762 | 415.162 | 2020-10-05 | 1 | INV#064 | 44124 | 113 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock hammer for 3 hours. | 5 | C050-C059 | Antler Lake Rd | 0 | 44116 |  | 50 | 44123 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting555820201005-22Excavator - 36 ton- After Jan 102.5367.4 | Corbiere and Sons Contracting555820201005-22Excavator - 36 ton- After Jan 102.5367.4INV#064 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 367.4 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5558 | 20201005-22 | 53510502 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 2.5 | HR | 47.54 | 0 |  |  | 158.45 | 20.5985 | 179.0485 | 2020-10-05 | 1 | INV#064 | 44124 | 113 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock hammer for 3 hours. | 5 | C050-C059 | Antler Lake Rd | 0 | 44116 |  | 50 | 44123 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting555820201005-22Excavator Hammer - 30 - 50 ton- After Jan 102.5158.45 | Corbiere and Sons Contracting555820201005-22Excavator Hammer - 30 - 50 ton- After Jan 102.5158.45INV#064 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 158.45 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5558 | 20201005-22 | 53510502 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 3 | HR |  |  | 75 | 0 | 225 | 29.25 | 254.25 | 2020-10-05 | 1 | INV#064 | 44124 | 113 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock hammer for 3 hours. | 5 | C050-C059 | Antler Lake Rd | 0 | 44116 |  | 50 | 44123 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting555820201005-22Operator - Principle - After Jan 103225 | Corbiere and Sons Contracting555820201005-22Operator - Principle - After Jan 103225INV#064 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 225 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5559 | 20201005-23 | 53510504 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10.5 | Dynamic | 98.61 | 0 |  |  | 1380.54 | 179.4702 | 1560.0102 | 2020-10-05 | 1 | INV#064 | 44124 | 113 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Load rock trucks all day from C-085. Dozer spreading gravel from C-083 - C-085. | 5 | C076-C092 | Cook Lake Rd - W | 0 | 44116 |  | 50 | 44123 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting555920201005-23Dozer D6 or equal- After Jan 1010.51380.54 | Corbiere and Sons Contracting555920201005-23Dozer D6 or equal- After Jan 1010.51380.54INV#064 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1380.54 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5559 | 20201005-23 | 53510504 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10.5 | Dynamic | 103.84 | 0 |  |  | 1453.725 | 188.9843 | 1642.7093 | 2020-10-05 | 1 | INV#064 | 44124 | 113 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Load rock trucks all day from C-085. Dozer spreading gravel from C-083 - C-085. | 5 | C076-C092 | Cook Lake Rd - W | 0 | 44116 |  | 50 | 44123 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting555920201005-23Excavator - 30 ton- After Jan 1010.51453.725 | Corbiere and Sons Contracting555920201005-23Excavator - 30 ton- After Jan 1010.51453.725INV#064 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1453.725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5559 | 20201005-23 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-10-05 | 1 | INV#064 | 44124 | 113 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Load rock trucks all day from C-085. Dozer spreading gravel from C-083 - C-085. | 5 | C076-C092 | Cook Lake Rd - W | 0 | 44116 |  | 50 | 44123 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting555920201005-23Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting555920201005-23Light Truck - Pick up- After Jan 102487.5INV#064 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5559 | 20201005-23 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 10.5 | Dynamic | 103.54 | 0 |  |  | 1449.525 | 188.4383 | 1637.9633 | 2020-10-05 | 1 | INV#064 | 44124 | 113 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Load rock trucks all day from C-085. Dozer spreading gravel from C-083 - C-085. | 5 | C076-C092 | Cook Lake Rd - W | 0 | 44116 |  | 50 | 44123 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting555920201005-23Rock Truck - 30 Ton- After Jan 1010.51449.525 | Corbiere and Sons Contracting555920201005-23Rock Truck - 30 Ton- After Jan 1010.51449.525INV#064 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1449.525 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5559 | 20201005-23 | 53510504 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2020-10-05 | 1 | INV#064 | 44124 | 113 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Load rock trucks all day from C-085. Dozer spreading gravel from C-083 - C-085. | 5 | C076-C092 | Cook Lake Rd - W | 0 | 44116 |  | 50 | 44123 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting555920201005-23L.O.A.3630 | Corbiere and Sons Contracting555920201005-23L.O.A.3630INV#064 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5559 | 20201005-23 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 23 | HR |  |  | 75 | 0 | 1725 | 224.25 | 1949.25 | 2020-10-05 | 1 | INV#064 | 44124 | 113 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Load rock trucks all day from C-085. Dozer spreading gravel from C-083 - C-085. | 5 | C076-C092 | Cook Lake Rd - W | 0 | 44116 |  | 50 | 44123 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting555920201005-23Operator - Principle - After Jan 10231725 | Corbiere and Sons Contracting555920201005-23Operator - Principle - After Jan 10231725INV#064 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5559 | 20201005-23 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 11.5 | HR |  |  | 70 | 0 | 805 | 104.65 | 909.65 | 2020-10-05 | 1 | INV#064 | 44124 | 113 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Load rock trucks all day from C-085. Dozer spreading gravel from C-083 - C-085. | 5 | C076-C092 | Cook Lake Rd - W | 0 | 44116 |  | 50 | 44123 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting555920201005-23Driver - AZ - After Jan 1011.5805 | Corbiere and Sons Contracting555920201005-23Driver - AZ - After Jan 1011.5805INV#064 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 805 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5511 | 20201005-9 | 53510504 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 101 | Dynamic | 41.4 | 0 |  |  | 5575.2 | 724.776 | 6299.976 | 2020-10-05 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 8 trucks hauling from Worthington Bay pit to Antler Lake Rd - trucks travelled from Thunder Bay | 5 | C050-C069 | Antler Lake | 0 | 44112 |  | 50 | 44112 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting551120201005-9Dump - Triaxle- After Jan 101015575.2 | Corbiere and Sons Contracting551120201005-9Dump - Triaxle- After Jan 101015575.2INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 5575.2 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5511 | 20201005-9 | 53510504 | Access | 0 | L.O.A. | 210 | 8 | DAY |  |  |  | 0 | 1680 | 218.4 | 1898.4 | 2020-10-05 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 8 trucks hauling from Worthington Bay pit to Antler Lake Rd - trucks travelled from Thunder Bay | 5 | C050-C069 | Antler Lake | 0 | 44112 |  | 50 | 44112 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting551120201005-9L.O.A.81680 | Corbiere and Sons Contracting551120201005-9L.O.A.81680INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1680 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5511 | 20201005-9 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 101 | HR |  |  | 70 | 0 | 7070 | 919.1 | 7989.1 | 2020-10-05 | 1 | INV#058 | 44118 | 112 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 8 trucks hauling from Worthington Bay pit to Antler Lake Rd - trucks travelled from Thunder Bay | 5 | C050-C069 | Antler Lake | 0 | 44112 |  | 50 | 44112 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting551120201005-9Driver - AZ - After Jan 101017070 | Corbiere and Sons Contracting551120201005-9Driver - AZ - After Jan 101017070INV#058 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 7070 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5567 | 20201006-14 | 53510504 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 89 | Dynamic | 41.4 | 0 |  |  | 4912.8 | 638.664 | 5551.464 | 2020-10-06 | 1 | INV#064 | 44124 | 113 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel hauling from Worthington Bay pit to Antler Lake Rd Crystals time for October 5th and 6th. | 5 | C-050 - C-069 | Antler Lake | 0 | 44116 |  | 49 | 44123 | [5 empty] | Travis Chisolm | 05 | Corbiere and Sons Contracting556720201006-14Dump - Triaxle- After Jan 10894912.8 | Corbiere and Sons Contracting556720201006-14Dump - Triaxle- After Jan 10894912.8INV#064 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 4912.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5567 | 20201006-14 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-10-06 | 1 | INV#064 | 44124 | 113 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel hauling from Worthington Bay pit to Antler Lake Rd Crystals time for October 5th and 6th. | 5 | C-050 - C-069 | Antler Lake | 0 | 44116 |  | 49 | 44123 | [5 empty] | Travis Chisolm | 05 | Corbiere and Sons Contracting556720201006-14Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting556720201006-14Light Truck - Pick up- After Jan 102487.5INV#064 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5567 | 20201006-14 | 53510504 | Access | 0 | Construction Coordinator | 80 | 12 | HR |  |  | 80 | 0 | 960 | 124.8 | 1084.8 | 2020-10-06 | 1 | INV#064 | 44124 | 113 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel hauling from Worthington Bay pit to Antler Lake Rd Crystals time for October 5th and 6th. | 5 | C-050 - C-069 | Antler Lake | 0 | 44116 |  | 49 | 44123 | [5 empty] | Travis Chisolm | 05 | Corbiere and Sons Contracting556720201006-14Construction Coordinator12960 | Corbiere and Sons Contracting556720201006-14Construction Coordinator12960INV#064 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5567 | 20201006-14 | 53510504 | Access | 0 | L.O.A. | 210 | 10 | DAY |  |  |  | 0 | 2100 | 273 | 2373 | 2020-10-06 | 1 | INV#064 | 44124 | 113 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel hauling from Worthington Bay pit to Antler Lake Rd Crystals time for October 5th and 6th. | 5 | C-050 - C-069 | Antler Lake | 0 | 44116 |  | 49 | 44123 | [5 empty] | Travis Chisolm | 05 | Corbiere and Sons Contracting556720201006-14L.O.A.102100 | Corbiere and Sons Contracting556720201006-14L.O.A.102100INV#064 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 2100 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5567 | 20201006-14 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 89 | HR |  |  | 70 | 0 | 6230 | 809.9 | 7039.9 | 2020-10-06 | 1 | INV#064 | 44124 | 113 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel hauling from Worthington Bay pit to Antler Lake Rd Crystals time for October 5th and 6th. | 5 | C-050 - C-069 | Antler Lake | 0 | 44116 |  | 49 | 44123 | [5 empty] | Travis Chisolm | 05 | Corbiere and Sons Contracting556720201006-14Driver - AZ - After Jan 10896230 | Corbiere and Sons Contracting556720201006-14Driver - AZ - After Jan 10896230INV#064 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 6230 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5569 | 20201006-16 | 53510504 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10.5 | Dynamic | 98.61 | 0 |  |  | 1380.54 | 179.4702 | 1560.0102 | 2020-10-06 | 1 | INV#064 | 44124 | 113 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavators loading rock trucks, dozer spreading gravel from C-060, labourers delivered and rolled out geo | 5 | Towers: C-050 - C-069 | Antler Lake Rd | 0 | 44116 |  | 50 | 44123 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting556920201006-16Dozer D6 or equal- After Jan 1010.51380.54 | Corbiere and Sons Contracting556920201006-16Dozer D6 or equal- After Jan 1010.51380.54INV#064 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1380.54 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5569 | 20201006-16 | 53510504 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 103.84 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2020-10-06 | 1 | INV#064 | 44124 | 113 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavators loading rock trucks, dozer spreading gravel from C-060, labourers delivered and rolled out geo | 5 | Towers: C-050 - C-069 | Antler Lake Rd | 0 | 44116 |  | 50 | 44123 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting556920201006-16Excavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting556920201006-16Excavator - 30 ton- After Jan 1091246.05INV#064 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1246.05 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5569 | 20201006-16 | 53510504 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 6.5 | Dynamic | 103.84 | 0 |  |  | 899.925 | 116.9903 | 1016.9153 | 2020-10-06 | 1 | INV#064 | 44124 | 113 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavators loading rock trucks, dozer spreading gravel from C-060, labourers delivered and rolled out geo | 5 | Towers: C-050 - C-069 | Antler Lake Rd | 0 | 44116 |  | 50 | 44123 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting556920201006-16Excavator - 30 ton- After Jan 106.5899.925 | Corbiere and Sons Contracting556920201006-16Excavator - 30 ton- After Jan 106.5899.925INV#064 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 899.925 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5569 | 20201006-16 | 53510504 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 6.5 | HR | 9.16 | 0 |  |  | 79.365 | 10.3174 | 89.6825 | 2020-10-06 | 1 | INV#064 | 44124 | 113 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavators loading rock trucks, dozer spreading gravel from C-060, labourers delivered and rolled out geo | 5 | Towers: C-050 - C-069 | Antler Lake Rd | 0 | 44116 |  | 50 | 44123 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting556920201006-16Excavator Thumb - 30 - 50 ton- After Jan 106.579.365 | Corbiere and Sons Contracting556920201006-16Excavator Thumb - 30 - 50 ton- After Jan 106.579.365INV#064 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 79.365 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5569 | 20201006-16 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 4 | DAY | 182.81 | 0 |  |  | 975 | 126.75 | 1101.75 | 2020-10-06 | 1 | INV#064 | 44124 | 113 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavators loading rock trucks, dozer spreading gravel from C-060, labourers delivered and rolled out geo | 5 | Towers: C-050 - C-069 | Antler Lake Rd | 0 | 44116 |  | 50 | 44123 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting556920201006-16Light Truck - Pick up- After Jan 104975 | Corbiere and Sons Contracting556920201006-16Light Truck - Pick up- After Jan 104975INV#064 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 975 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5569 | 20201006-16 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 18 | Dynamic | 103.54 | 0 |  |  | 2484.9 | 323.037 | 2807.937 | 2020-10-06 | 1 | INV#064 | 44124 | 113 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavators loading rock trucks, dozer spreading gravel from C-060, labourers delivered and rolled out geo | 5 | Towers: C-050 - C-069 | Antler Lake Rd | 0 | 44116 |  | 50 | 44123 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting556920201006-16Rock Truck - 30 Ton- After Jan 10182484.9 | Corbiere and Sons Contracting556920201006-16Rock Truck - 30 Ton- After Jan 10182484.9INV#064 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 2484.9 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5569 | 20201006-16 | 53510504 | Access | 0 | Foreman | 95 | 6 | HR |  |  | 95 | 0 | 570 | 74.1 | 644.1 | 2020-10-06 | 1 | INV#064 | 44124 | 113 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavators loading rock trucks, dozer spreading gravel from C-060, labourers delivered and rolled out geo | 5 | Towers: C-050 - C-069 | Antler Lake Rd | 0 | 44116 |  | 50 | 44123 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting556920201006-16Foreman6570 | Corbiere and Sons Contracting556920201006-16Foreman6570INV#064 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 570 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5569 | 20201006-16 | 53510504 | Access | 0 | L.O.A. | 210 | 8 | DAY |  |  |  | 0 | 1680 | 218.4 | 1898.4 | 2020-10-06 | 1 | INV#064 | 44124 | 113 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavators loading rock trucks, dozer spreading gravel from C-060, labourers delivered and rolled out geo | 5 | Towers: C-050 - C-069 | Antler Lake Rd | 0 | 44116 |  | 50 | 44123 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting556920201006-16L.O.A.81680 | Corbiere and Sons Contracting556920201006-16L.O.A.81680INV#064 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1680 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5569 | 20201006-16 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 28.5 | HR |  |  | 75 | 0 | 2137.5 | 277.875 | 2415.375 | 2020-10-06 | 1 | INV#064 | 44124 | 113 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavators loading rock trucks, dozer spreading gravel from C-060, labourers delivered and rolled out geo | 5 | Towers: C-050 - C-069 | Antler Lake Rd | 0 | 44116 |  | 50 | 44123 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting556920201006-16Operator - Principle - After Jan 1028.52137.5 | Corbiere and Sons Contracting556920201006-16Operator - Principle - After Jan 1028.52137.5INV#064 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 2137.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5569 | 20201006-16 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 19.5 | HR |  |  | 70 | 0 | 1365 | 177.45 | 1542.45 | 2020-10-06 | 1 | INV#064 | 44124 | 113 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavators loading rock trucks, dozer spreading gravel from C-060, labourers delivered and rolled out geo | 5 | Towers: C-050 - C-069 | Antler Lake Rd | 0 | 44116 |  | 50 | 44123 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting556920201006-16Driver - AZ - After Jan 1019.51365 | Corbiere and Sons Contracting556920201006-16Driver - AZ - After Jan 1019.51365INV#064 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1365 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5569 | 20201006-16 | 53510504 | Access | 0 | Labourer - General - After Jan 10 | 60 | 10 | HR |  |  | 60 | 0 | 600 | 78 | 678 | 2020-10-06 | 1 | INV#064 | 44124 | 113 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavators loading rock trucks, dozer spreading gravel from C-060, labourers delivered and rolled out geo | 5 | Towers: C-050 - C-069 | Antler Lake Rd | 0 | 44116 |  | 50 | 44123 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting556920201006-16Labourer - General - After Jan 1010600 | Corbiere and Sons Contracting556920201006-16Labourer - General - After Jan 1010600INV#064 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5573 | 20201006-19 | 53510504 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10.5 | Dynamic | 98.61 | 0 |  |  | 1380.54 | 179.4702 | 1560.0102 | 2020-10-06 | 1 | INV#064 | 44124 | 113 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks, dozer spreading gravel from C-084. | 5 | C-093 - C-116 | Cook Lake Rd - W | 0 | 44116 |  | 50 | 44123 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting557320201006-19Dozer D6 or equal- After Jan 1010.51380.54 | Corbiere and Sons Contracting557320201006-19Dozer D6 or equal- After Jan 1010.51380.54INV#064 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1380.54 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5573 | 20201006-19 | 53510504 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10.5 | Dynamic | 103.84 | 0 |  |  | 1453.725 | 188.9843 | 1642.7093 | 2020-10-06 | 1 | INV#064 | 44124 | 113 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks, dozer spreading gravel from C-084. | 5 | C-093 - C-116 | Cook Lake Rd - W | 0 | 44116 |  | 50 | 44123 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting557320201006-19Excavator - 30 ton- After Jan 1010.51453.725 | Corbiere and Sons Contracting557320201006-19Excavator - 30 ton- After Jan 1010.51453.725INV#064 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1453.725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5573 | 20201006-19 | 53510504 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 5 | Dynamic | 110.22 | 0 |  |  | 734.8 | 95.524 | 830.324 | 2020-10-06 | 1 | INV#064 | 44124 | 113 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks, dozer spreading gravel from C-084. | 5 | C-093 - C-116 | Cook Lake Rd - W | 0 | 44116 |  | 50 | 44123 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting557320201006-19Excavator - 36 ton- After Jan 105734.8 | Corbiere and Sons Contracting557320201006-19Excavator - 36 ton- After Jan 105734.8INV#064 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 734.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5573 | 20201006-19 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-10-06 | 1 | INV#064 | 44124 | 113 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks, dozer spreading gravel from C-084. | 5 | C-093 - C-116 | Cook Lake Rd - W | 0 | 44116 |  | 50 | 44123 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting557320201006-19Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting557320201006-19Light Truck - Pick up- After Jan 102487.5INV#064 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5573 | 20201006-19 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 19 | Dynamic | 103.54 | 0 |  |  | 2622.95 | 340.9835 | 2963.9335 | 2020-10-06 | 1 | INV#064 | 44124 | 113 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks, dozer spreading gravel from C-084. | 5 | C-093 - C-116 | Cook Lake Rd - W | 0 | 44116 |  | 50 | 44123 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting557320201006-19Rock Truck - 30 Ton- After Jan 10192622.95 | Corbiere and Sons Contracting557320201006-19Rock Truck - 30 Ton- After Jan 10192622.95INV#064 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 2622.95 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5573 | 20201006-19 | 53510504 | Access | 0 | Foreman | 95 | 6 | HR |  |  | 95 | 0 | 570 | 74.1 | 644.1 | 2020-10-06 | 1 | INV#064 | 44124 | 113 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks, dozer spreading gravel from C-084. | 5 | C-093 - C-116 | Cook Lake Rd - W | 0 | 44116 |  | 50 | 44123 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting557320201006-19Foreman6570 | Corbiere and Sons Contracting557320201006-19Foreman6570INV#064 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 570 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5573 | 20201006-19 | 53510504 | Access | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2020-10-06 | 1 | INV#064 | 44124 | 113 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks, dozer spreading gravel from C-084. | 5 | C-093 - C-116 | Cook Lake Rd - W | 0 | 44116 |  | 50 | 44123 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting557320201006-19L.O.A.61260 | Corbiere and Sons Contracting557320201006-19L.O.A.61260INV#064 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5573 | 20201006-19 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 28.5 | HR |  |  | 75 | 0 | 2137.5 | 277.875 | 2415.375 | 2020-10-06 | 1 | INV#064 | 44124 | 113 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks, dozer spreading gravel from C-084. | 5 | C-093 - C-116 | Cook Lake Rd - W | 0 | 44116 |  | 50 | 44123 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting557320201006-19Operator - Principle - After Jan 1028.52137.5 | Corbiere and Sons Contracting557320201006-19Operator - Principle - After Jan 1028.52137.5INV#064 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 2137.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5573 | 20201006-19 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 21 | HR |  |  | 70 | 0 | 1470 | 191.1 | 1661.1 | 2020-10-06 | 1 | INV#064 | 44124 | 113 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks, dozer spreading gravel from C-084. | 5 | C-093 - C-116 | Cook Lake Rd - W | 0 | 44116 |  | 50 | 44123 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting557320201006-19Driver - AZ - After Jan 10211470 | Corbiere and Sons Contracting557320201006-19Driver - AZ - After Jan 10211470INV#064 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1470 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5572 | 20201006-20 | 53510502 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 7.5 | Dynamic | 110.22 | 0 |  |  | 1102.2 | 143.286 | 1245.486 | 2020-10-06 | 1 | INV#064 | 44124 | 113 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ran hammer part of day. | 5 | C-076 - C-116 | Cook Lake | 0 | 44116 |  | 50 | 44123 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting557220201006-20Excavator - 36 ton- After Jan 107.51102.2 | Corbiere and Sons Contracting557220201006-20Excavator - 36 ton- After Jan 107.51102.2INV#064 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 1102.2 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5572 | 20201006-20 | 53510502 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 7.5 | HR | 47.54 | 0 |  |  | 475.35 | 61.7955 | 537.1455 | 2020-10-06 | 1 | INV#064 | 44124 | 113 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ran hammer part of day. | 5 | C-076 - C-116 | Cook Lake | 0 | 44116 |  | 50 | 44123 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting557220201006-20Excavator Hammer - 30 - 50 ton- After Jan 107.5475.35 | Corbiere and Sons Contracting557220201006-20Excavator Hammer - 30 - 50 ton- After Jan 107.5475.35INV#064 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 475.35 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5572 | 20201006-20 | 53510502 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-10-06 | 1 | INV#064 | 44124 | 113 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ran hammer part of day. | 5 | C-076 - C-116 | Cook Lake | 0 | 44116 |  | 50 | 44123 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting557220201006-20Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting557220201006-20Light Truck - Pick up- After Jan 101243.75INV#064 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5572 | 20201006-20 | 53510502 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-10-06 | 1 | INV#064 | 44124 | 113 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ran hammer part of day. | 5 | C-076 - C-116 | Cook Lake | 0 | 44116 |  | 50 | 44123 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting557220201006-20L.O.A.1210 | Corbiere and Sons Contracting557220201006-20L.O.A.1210INV#064 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5572 | 20201006-20 | 53510502 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 8 | HR |  |  | 75 | 0 | 600 | 78 | 678 | 2020-10-06 | 1 | INV#064 | 44124 | 113 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ran hammer part of day. | 5 | C-076 - C-116 | Cook Lake | 0 | 44116 |  | 50 | 44123 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting557220201006-20Operator - Principle - After Jan 108600 | Corbiere and Sons Contracting557220201006-20Operator - Principle - After Jan 108600INV#064 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5584 | 20201007-14 | 53510504 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 99 | Dynamic | 41.4 | 0 |  |  | 5464.8 | 710.424 | 6175.224 | 2020-10-07 | 1 | INV#064 | 44124 | 113 | 0 | 0 | Arlene Dahl | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling from Worthington Bay pit to Antler Lake Road | 5 | C-050 - C-069 | Antler Lake Rd | 0 | 44116 |  | 50 | 44121 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting558420201007-14Dump - Triaxle- After Jan 10995464.8 | Corbiere and Sons Contracting558420201007-14Dump - Triaxle- After Jan 10995464.8INV#064 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 5464.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5584 | 20201007-14 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-10-07 | 1 | INV#064 | 44124 | 113 | 0 | 0 | Arlene Dahl | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling from Worthington Bay pit to Antler Lake Road | 5 | C-050 - C-069 | Antler Lake Rd | 0 | 44116 |  | 50 | 44121 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting558420201007-14Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting558420201007-14Light Truck - Pick up- After Jan 101243.75INV#064 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5584 | 20201007-14 | 53510504 | Access | 0 | Construction Coordinator | 80 | 6 | HR |  |  | 80 | 0 | 480 | 62.4 | 542.4 | 2020-10-07 | 1 | INV#064 | 44124 | 113 | 0 | 0 | Arlene Dahl | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling from Worthington Bay pit to Antler Lake Road | 5 | C-050 - C-069 | Antler Lake Rd | 0 | 44116 |  | 50 | 44121 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting558420201007-14Construction Coordinator6480 | Corbiere and Sons Contracting558420201007-14Construction Coordinator6480INV#064 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 480 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5584 | 20201007-14 | 53510504 | Access | 0 | L.O.A. | 210 | 9 | DAY |  |  |  | 0 | 1890 | 245.7 | 2135.7 | 2020-10-07 | 1 | INV#064 | 44124 | 113 | 0 | 0 | Arlene Dahl | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling from Worthington Bay pit to Antler Lake Road | 5 | C-050 - C-069 | Antler Lake Rd | 0 | 44116 |  | 50 | 44121 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting558420201007-14L.O.A.91890 | Corbiere and Sons Contracting558420201007-14L.O.A.91890INV#064 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1890 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5584 | 20201007-14 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 99 | HR |  |  | 70 | 0 | 6930 | 900.9 | 7830.9 | 2020-10-07 | 1 | INV#064 | 44124 | 113 | 0 | 0 | Arlene Dahl | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling from Worthington Bay pit to Antler Lake Road | 5 | C-050 - C-069 | Antler Lake Rd | 0 | 44116 |  | 50 | 44121 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting558420201007-14Driver - AZ - After Jan 10996930 | Corbiere and Sons Contracting558420201007-14Driver - AZ - After Jan 10996930INV#064 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 6930 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5585 | 20201007-15 | 53510504 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 7.5 | Dynamic | 98.61 | 0 |  |  | 986.1 | 128.193 | 1114.293 | 2020-10-07 | 1 | INV#064 | 44124 | 113 | 0 | 0 | Arlene Dahl | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Bailed material for dozer spread, Dozer spreading gravel towards WC7201, walked machine to C-060 area to help bail dirt, stockpiling gravel | 5 | C-050 - C-069 | Antler Lake Rd | 0 | 44116 |  | 50 | 44121 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting558520201007-15Dozer D6 or equal- After Jan 107.5986.1 | Corbiere and Sons Contracting558520201007-15Dozer D6 or equal- After Jan 107.5986.1INV#064 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 986.1 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5585 | 20201007-15 | 53510504 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9.5 | Dynamic | 103.84 | 0 |  |  | 1315.275 | 170.9857 | 1486.2607 | 2020-10-07 | 1 | INV#064 | 44124 | 113 | 0 | 0 | Arlene Dahl | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Bailed material for dozer spread, Dozer spreading gravel towards WC7201, walked machine to C-060 area to help bail dirt, stockpiling gravel | 5 | C-050 - C-069 | Antler Lake Rd | 0 | 44116 |  | 50 | 44121 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting558520201007-15Excavator - 30 ton- After Jan 109.51315.275 | Corbiere and Sons Contracting558520201007-15Excavator - 30 ton- After Jan 109.51315.275INV#064 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1315.275 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5585 | 20201007-15 | 53510504 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 3 | Dynamic | 110.22 | 0 |  |  | 440.88 | 57.3144 | 498.1944 | 2020-10-07 | 1 | INV#064 | 44124 | 113 | 0 | 0 | Arlene Dahl | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Bailed material for dozer spread, Dozer spreading gravel towards WC7201, walked machine to C-060 area to help bail dirt, stockpiling gravel | 5 | C-050 - C-069 | Antler Lake Rd | 0 | 44116 |  | 50 | 44121 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting558520201007-15Excavator - 36 ton- After Jan 103440.88 | Corbiere and Sons Contracting558520201007-15Excavator - 36 ton- After Jan 103440.88INV#064 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 440.88 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5585 | 20201007-15 | 53510504 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 4 | HR | 9.16 | 0 |  |  | 48.84 | 6.3492 | 55.1892 | 2020-10-07 | 1 | INV#064 | 44124 | 113 | 0 | 0 | Arlene Dahl | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Bailed material for dozer spread, Dozer spreading gravel towards WC7201, walked machine to C-060 area to help bail dirt, stockpiling gravel | 5 | C-050 - C-069 | Antler Lake Rd | 0 | 44116 |  | 50 | 44121 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting558520201007-15Excavator Thumb - 30 - 50 ton- After Jan 10448.84 | Corbiere and Sons Contracting558520201007-15Excavator Thumb - 30 - 50 ton- After Jan 10448.84INV#064 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 48.84 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5585 | 20201007-15 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-10-07 | 1 | INV#064 | 44124 | 113 | 0 | 0 | Arlene Dahl | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Bailed material for dozer spread, Dozer spreading gravel towards WC7201, walked machine to C-060 area to help bail dirt, stockpiling gravel | 5 | C-050 - C-069 | Antler Lake Rd | 0 | 44116 |  | 50 | 44121 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting558520201007-15Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting558520201007-15Light Truck - Pick up- After Jan 102487.5INV#064 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5585 | 20201007-15 | 53510504 | Access | 0 | Foreman | 95 | 3 | HR |  |  | 95 | 0 | 285 | 37.05 | 322.05 | 2020-10-07 | 1 | INV#064 | 44124 | 113 | 0 | 0 | Arlene Dahl | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Bailed material for dozer spread, Dozer spreading gravel towards WC7201, walked machine to C-060 area to help bail dirt, stockpiling gravel | 5 | C-050 - C-069 | Antler Lake Rd | 0 | 44116 |  | 50 | 44121 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting558520201007-15Foreman3285 | Corbiere and Sons Contracting558520201007-15Foreman3285INV#064 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 285 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5585 | 20201007-15 | 53510504 | Access | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2020-10-07 | 1 | INV#064 | 44124 | 113 | 0 | 0 | Arlene Dahl | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Bailed material for dozer spread, Dozer spreading gravel towards WC7201, walked machine to C-060 area to help bail dirt, stockpiling gravel | 5 | C-050 - C-069 | Antler Lake Rd | 0 | 44116 |  | 50 | 44121 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting558520201007-15L.O.A.51050 | Corbiere and Sons Contracting558520201007-15L.O.A.51050INV#064 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5585 | 20201007-15 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 21 | HR |  |  | 75 | 0 | 1575 | 204.75 | 1779.75 | 2020-10-07 | 1 | INV#064 | 44124 | 113 | 0 | 0 | Arlene Dahl | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Bailed material for dozer spread, Dozer spreading gravel towards WC7201, walked machine to C-060 area to help bail dirt, stockpiling gravel | 5 | C-050 - C-069 | Antler Lake Rd | 0 | 44116 |  | 50 | 44121 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting558520201007-15Operator - Principle - After Jan 10211575 | Corbiere and Sons Contracting558520201007-15Operator - Principle - After Jan 10211575INV#064 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1575 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5585 | 20201007-15 | 53510504 | Access | 0 | Labourer - General - After Jan 10 | 60 | 2 | HR |  |  | 60 | 0 | 120 | 15.6 | 135.6 | 2020-10-07 | 1 | INV#064 | 44124 | 113 | 0 | 0 | Arlene Dahl | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Bailed material for dozer spread, Dozer spreading gravel towards WC7201, walked machine to C-060 area to help bail dirt, stockpiling gravel | 5 | C-050 - C-069 | Antler Lake Rd | 0 | 44116 |  | 50 | 44121 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting558520201007-15Labourer - General - After Jan 102120 | Corbiere and Sons Contracting558520201007-15Labourer - General - After Jan 102120INV#064 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 120 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5587 | 20201007-17 | 53510512 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 5 | Dynamic | 103.84 | 0 |  |  | 692.25 | 89.9925 | 782.2425 | 2020-10-07 | 1 | INV#064 | 44124 | 113 | 0 | 0 | Arlene Dahl | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixed road for the remainder of day | 5 | C-050 - C-069 | Antler Lake Rd | 0 | 44116 |  | 50 | 44121 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting558720201007-17Excavator - 30 ton- After Jan 105692.25 | Corbiere and Sons Contracting558720201007-17Excavator - 30 ton- After Jan 105692.25INV#064 | [5 empty] | 1 | 692.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5587 | 20201007-17 | 53510512 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5.5 | HR |  |  | 75 | 0 | 412.5 | 53.625 | 466.125 | 2020-10-07 | 1 | INV#064 | 44124 | 113 | 0 | 0 | Arlene Dahl | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixed road for the remainder of day | 5 | C-050 - C-069 | Antler Lake Rd | 0 | 44116 |  | 50 | 44121 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting558720201007-17Operator - Principle - After Jan 105.5412.5 | Corbiere and Sons Contracting558720201007-17Operator - Principle - After Jan 105.5412.5INV#064 | [5 empty] | 1 | 412.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5596 | 20201007-26 | 53510312 | Access | 0 | Labourer - General - After Jan 10 | 60 | 10 | HR |  |  | 60 | 0 | 600 | 78 | 678 | 2020-10-07 | 1 | INV#064 | 44124 | 113 | 0 | 0 | Arlene Dahl | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Shovelled the highway entrances at Gurney and North Shore Pit | 3 | B-187 - B-193 | Gurney Lake Rd | 0 | 44116 |  | 37 | 44123 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting559620201007-26Labourer - General - After Jan 1010600 | Corbiere and Sons Contracting559620201007-26Labourer - General - After Jan 1010600INV#064 | [5 empty] | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5838 | 20201007-32 | 53510512 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10.5 | Dynamic | 98.61 | 0 |  |  | 1380.54 | 179.4702 | 1560.0102 | 2020-10-07 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer doing road maintenance from C-093 | 5 | C093-C116 | Cook Lake | 0 | 44127 |  | 36 | 44127 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting583820201007-32Dozer D6 or equal- After Jan 1010.51380.54 | Corbiere and Sons Contracting583820201007-32Dozer D6 or equal- After Jan 1010.51380.54Inv#068 | [5 empty] | 1 | 1380.54 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5838 | 20201007-32 | 53510512 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-10-07 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer doing road maintenance from C-093 | 5 | C093-C116 | Cook Lake | 0 | 44127 |  | 36 | 44127 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting583820201007-32L.O.A.1210 | Corbiere and Sons Contracting583820201007-32L.O.A.1210Inv#068 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5838 | 20201007-32 | 53510512 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-10-07 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer doing road maintenance from C-093 | 5 | C093-C116 | Cook Lake | 0 | 44127 |  | 36 | 44127 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting583820201007-32Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting583820201007-32Operator - Principle - After Jan 1011.5862.5Inv#068 | [5 empty] | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5629 | 20201008-14 | 53510504 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 3 | Dynamic | 98.61 | 0 |  |  | 394.44 | 51.2772 | 445.7172 | 2020-10-08 | 1 | INV#064 | 44124 | 113 | 0 | 0 | Arlene Dahl | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Capping corduroy, loading rock trucks, hauling gravel | 5 | C-050 - C-069 | Antler Lake Rd | 0 | 44115 |  | 49 | 44121 | [5 empty] | Travis Chisolm | 05 | Corbiere and Sons Contracting562920201008-14Dozer D6 or equal- After Jan 103394.44 | Corbiere and Sons Contracting562920201008-14Dozer D6 or equal- After Jan 103394.44INV#064 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 394.44 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5629 | 20201008-14 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 3 | Dynamic | 103.54 | 0 |  |  | 414.15 | 53.8395 | 467.9895 | 2020-10-08 | 1 | INV#064 | 44124 | 113 | 0 | 0 | Arlene Dahl | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Capping corduroy, loading rock trucks, hauling gravel | 5 | C-050 - C-069 | Antler Lake Rd | 0 | 44115 |  | 49 | 44121 | [5 empty] | Travis Chisolm | 05 | Corbiere and Sons Contracting562920201008-14Rock Truck - 30 Ton- After Jan 103414.15 | Corbiere and Sons Contracting562920201008-14Rock Truck - 30 Ton- After Jan 103414.15INV#064 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 414.15 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5629 | 20201008-14 | 53510504 | Access | 0 | Foreman | 95 | 2 | HR |  |  | 95 | 0 | 190 | 24.7 | 214.7 | 2020-10-08 | 1 | INV#064 | 44124 | 113 | 0 | 0 | Arlene Dahl | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Capping corduroy, loading rock trucks, hauling gravel | 5 | C-050 - C-069 | Antler Lake Rd | 0 | 44115 |  | 49 | 44121 | [5 empty] | Travis Chisolm | 05 | Corbiere and Sons Contracting562920201008-14Foreman2190 | Corbiere and Sons Contracting562920201008-14Foreman2190INV#064 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 190 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5629 | 20201008-14 | 53510504 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-10-08 | 1 | INV#064 | 44124 | 113 | 0 | 0 | Arlene Dahl | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Capping corduroy, loading rock trucks, hauling gravel | 5 | C-050 - C-069 | Antler Lake Rd | 0 | 44115 |  | 49 | 44121 | [5 empty] | Travis Chisolm | 05 | Corbiere and Sons Contracting562920201008-14L.O.A.1210 | Corbiere and Sons Contracting562920201008-14L.O.A.1210INV#064 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5629 | 20201008-14 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 3 | HR |  |  | 75 | 0 | 225 | 29.25 | 254.25 | 2020-10-08 | 1 | INV#064 | 44124 | 113 | 0 | 0 | Arlene Dahl | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Capping corduroy, loading rock trucks, hauling gravel | 5 | C-050 - C-069 | Antler Lake Rd | 0 | 44115 |  | 49 | 44121 | [5 empty] | Travis Chisolm | 05 | Corbiere and Sons Contracting562920201008-14Operator - Principle - After Jan 103225 | Corbiere and Sons Contracting562920201008-14Operator - Principle - After Jan 103225INV#064 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 225 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5629 | 20201008-14 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 3 | HR |  |  | 70 | 0 | 210 | 27.3 | 237.3 | 2020-10-08 | 1 | INV#064 | 44124 | 113 | 0 | 0 | Arlene Dahl | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Capping corduroy, loading rock trucks, hauling gravel | 5 | C-050 - C-069 | Antler Lake Rd | 0 | 44115 |  | 49 | 44121 | [5 empty] | Travis Chisolm | 05 | Corbiere and Sons Contracting562920201008-14Driver - AZ - After Jan 103210 | Corbiere and Sons Contracting562920201008-14Driver - AZ - After Jan 103210INV#064 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5630 | 20201008-15 | 53510512 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 7.5 | Dynamic | 98.61 | 0 |  |  | 986.1 | 128.193 | 1114.293 | 2020-10-08 | 1 | INV#064 | 44124 | 113 | 0 | 0 | Arlene Dahl | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Maintenance on AN road towards C-059. | 5 | C-050 - C-069 | Antler Lake Rd | 0 | 44115 |  | 49 | 44121 | [5 empty] | Travis Chisolm | 05 | Corbiere and Sons Contracting563020201008-15Dozer D6 or equal- After Jan 107.5986.1 | Corbiere and Sons Contracting563020201008-15Dozer D6 or equal- After Jan 107.5986.1INV#064 | [5 empty] | 1 | 986.1 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5630 | 20201008-15 | 53510512 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-10-08 | 1 | INV#064 | 44124 | 113 | 0 | 0 | Arlene Dahl | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Maintenance on AN road towards C-059. | 5 | C-050 - C-069 | Antler Lake Rd | 0 | 44115 |  | 49 | 44121 | [5 empty] | Travis Chisolm | 05 | Corbiere and Sons Contracting563020201008-15L.O.A.1210 | Corbiere and Sons Contracting563020201008-15L.O.A.1210INV#064 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5630 | 20201008-15 | 53510512 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 8.5 | HR |  |  | 75 | 0 | 637.5 | 82.875 | 720.375 | 2020-10-08 | 1 | INV#064 | 44124 | 113 | 0 | 0 | Arlene Dahl | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Maintenance on AN road towards C-059. | 5 | C-050 - C-069 | Antler Lake Rd | 0 | 44115 |  | 49 | 44121 | [5 empty] | Travis Chisolm | 05 | Corbiere and Sons Contracting563020201008-15Operator - Principle - After Jan 108.5637.5 | Corbiere and Sons Contracting563020201008-15Operator - Principle - After Jan 108.5637.5INV#064 | [5 empty] | 1 | 637.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5632 | 20201008-17 | 53510504 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10.5 | Dynamic | 98.61 | 0 |  |  | 1380.54 | 179.4702 | 1560.0102 | 2020-10-08 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Arlene Dahl | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hauling gravel to C-084 - C085.Excavator loading rock trucks, dozer spreading gravel | 5 | C-076 - C-092 | Cook Lake Rd - W | 0 | 44115 |  | 49 | 44125 | [5 empty] | Travis Chisolm | 05 | Corbiere and Sons Contracting563220201008-17Dozer D6 or equal- After Jan 1010.51380.54 | Corbiere and Sons Contracting563220201008-17Dozer D6 or equal- After Jan 1010.51380.54Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1380.54 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5632 | 20201008-17 | 53510504 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10.5 | Dynamic | 103.84 | 0 |  |  | 1453.725 | 188.9843 | 1642.7093 | 2020-10-08 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Arlene Dahl | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hauling gravel to C-084 - C085.Excavator loading rock trucks, dozer spreading gravel | 5 | C-076 - C-092 | Cook Lake Rd - W | 0 | 44115 |  | 49 | 44125 | [5 empty] | Travis Chisolm | 05 | Corbiere and Sons Contracting563220201008-17Excavator - 30 ton- After Jan 1010.51453.725 | Corbiere and Sons Contracting563220201008-17Excavator - 30 ton- After Jan 1010.51453.725Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1453.725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5632 | 20201008-17 | 53510504 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 4 | Dynamic | 110.22 | 0 |  |  | 587.84 | 76.4192 | 664.2592 | 2020-10-08 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Arlene Dahl | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hauling gravel to C-084 - C085.Excavator loading rock trucks, dozer spreading gravel | 5 | C-076 - C-092 | Cook Lake Rd - W | 0 | 44115 |  | 49 | 44125 | [5 empty] | Travis Chisolm | 05 | Corbiere and Sons Contracting563220201008-17Excavator - 36 ton- After Jan 104587.84 | Corbiere and Sons Contracting563220201008-17Excavator - 36 ton- After Jan 104587.84Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 587.84 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5632 | 20201008-17 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-10-08 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Arlene Dahl | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hauling gravel to C-084 - C085.Excavator loading rock trucks, dozer spreading gravel | 5 | C-076 - C-092 | Cook Lake Rd - W | 0 | 44115 |  | 49 | 44125 | [5 empty] | Travis Chisolm | 05 | Corbiere and Sons Contracting563220201008-17Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting563220201008-17Light Truck - Pick up- After Jan 102487.5Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5632 | 20201008-17 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 10.5 | Dynamic | 103.54 | 0 |  |  | 1449.525 | 188.4383 | 1637.9633 | 2020-10-08 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Arlene Dahl | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hauling gravel to C-084 - C085.Excavator loading rock trucks, dozer spreading gravel | 5 | C-076 - C-092 | Cook Lake Rd - W | 0 | 44115 |  | 49 | 44125 | [5 empty] | Travis Chisolm | 05 | Corbiere and Sons Contracting563220201008-17Rock Truck - 30 Ton- After Jan 1010.51449.525 | Corbiere and Sons Contracting563220201008-17Rock Truck - 30 Ton- After Jan 1010.51449.525Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1449.525 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5632 | 20201008-17 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 10.5 | Dynamic | 103.54 | 0 |  |  | 1449.525 | 188.4383 | 1637.9633 | 2020-10-08 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Arlene Dahl | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hauling gravel to C-084 - C085.Excavator loading rock trucks, dozer spreading gravel | 5 | C-076 - C-092 | Cook Lake Rd - W | 0 | 44115 |  | 49 | 44125 | [5 empty] | Travis Chisolm | 05 | Corbiere and Sons Contracting563220201008-17Rock Truck - 30 Ton- After Jan 1010.51449.525 | Corbiere and Sons Contracting563220201008-17Rock Truck - 30 Ton- After Jan 1010.51449.525Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1449.525 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5632 | 20201008-17 | 53510504 | Access | 0 | Foreman | 95 | 5 | HR |  |  | 95 | 0 | 475 | 61.75 | 536.75 | 2020-10-08 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Arlene Dahl | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hauling gravel to C-084 - C085.Excavator loading rock trucks, dozer spreading gravel | 5 | C-076 - C-092 | Cook Lake Rd - W | 0 | 44115 |  | 49 | 44125 | [5 empty] | Travis Chisolm | 05 | Corbiere and Sons Contracting563220201008-17Foreman5475 | Corbiere and Sons Contracting563220201008-17Foreman5475Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 475 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5632 | 20201008-17 | 53510504 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2020-10-08 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Arlene Dahl | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hauling gravel to C-084 - C085.Excavator loading rock trucks, dozer spreading gravel | 5 | C-076 - C-092 | Cook Lake Rd - W | 0 | 44115 |  | 49 | 44125 | [5 empty] | Travis Chisolm | 05 | Corbiere and Sons Contracting563220201008-17L.O.A.4840 | Corbiere and Sons Contracting563220201008-17L.O.A.4840Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5632 | 20201008-17 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 27 | HR |  |  | 75 | 0 | 2025 | 263.25 | 2288.25 | 2020-10-08 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Arlene Dahl | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hauling gravel to C-084 - C085.Excavator loading rock trucks, dozer spreading gravel | 5 | C-076 - C-092 | Cook Lake Rd - W | 0 | 44115 |  | 49 | 44125 | [5 empty] | Travis Chisolm | 05 | Corbiere and Sons Contracting563220201008-17Operator - Principle - After Jan 10272025 | Corbiere and Sons Contracting563220201008-17Operator - Principle - After Jan 10272025Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 2025 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5632 | 20201008-17 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 23 | HR |  |  | 70 | 0 | 1610 | 209.3 | 1819.3 | 2020-10-08 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Arlene Dahl | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hauling gravel to C-084 - C085.Excavator loading rock trucks, dozer spreading gravel | 5 | C-076 - C-092 | Cook Lake Rd - W | 0 | 44115 |  | 49 | 44125 | [5 empty] | Travis Chisolm | 05 | Corbiere and Sons Contracting563220201008-17Driver - AZ - After Jan 10231610 | Corbiere and Sons Contracting563220201008-17Driver - AZ - After Jan 10231610Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1610 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5632 | 20201008-17 | 53510504 | Access | 0 | Labourer - General - After Jan 10 | 60 | 3 | HR |  |  | 60 | 0 | 180 | 23.4 | 203.4 | 2020-10-08 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Arlene Dahl | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hauling gravel to C-084 - C085.Excavator loading rock trucks, dozer spreading gravel | 5 | C-076 - C-092 | Cook Lake Rd - W | 0 | 44115 |  | 49 | 44125 | [5 empty] | Travis Chisolm | 05 | Corbiere and Sons Contracting563220201008-17Labourer - General - After Jan 103180 | Corbiere and Sons Contracting563220201008-17Labourer - General - After Jan 103180Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 180 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5635 | 20201008-20 | 53510502 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10.5 | Dynamic | 110.22 | 0 |  |  | 1543.08 | 200.6004 | 1743.6804 | 2020-10-08 | 1 | INV#064 | 44124 | 113 | 0 | 0 | Arlene Dahl | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock hammer all day from C-093 | 5 | C-093 - C-116 | Cook Lake Rd - E | 0 | 44115 |  | 49 | 44121 | [5 empty] | Travis Chisolm | 05 | Corbiere and Sons Contracting563520201008-20Excavator - 36 ton- After Jan 1010.51543.08 | Corbiere and Sons Contracting563520201008-20Excavator - 36 ton- After Jan 1010.51543.08INV#064 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 1543.08 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5635 | 20201008-20 | 53510502 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 10.5 | HR | 47.54 | 0 |  |  | 665.49 | 86.5137 | 752.0037 | 2020-10-08 | 1 | INV#064 | 44124 | 113 | 0 | 0 | Arlene Dahl | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock hammer all day from C-093 | 5 | C-093 - C-116 | Cook Lake Rd - E | 0 | 44115 |  | 49 | 44121 | [5 empty] | Travis Chisolm | 05 | Corbiere and Sons Contracting563520201008-20Excavator Hammer - 30 - 50 ton- After Jan 1010.5665.49 | Corbiere and Sons Contracting563520201008-20Excavator Hammer - 30 - 50 ton- After Jan 1010.5665.49INV#064 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 665.49 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5635 | 20201008-20 | 53510502 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-10-08 | 1 | INV#064 | 44124 | 113 | 0 | 0 | Arlene Dahl | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock hammer all day from C-093 | 5 | C-093 - C-116 | Cook Lake Rd - E | 0 | 44115 |  | 49 | 44121 | [5 empty] | Travis Chisolm | 05 | Corbiere and Sons Contracting563520201008-20Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting563520201008-20Light Truck - Pick up- After Jan 101243.75INV#064 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5635 | 20201008-20 | 53510502 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-10-08 | 1 | INV#064 | 44124 | 113 | 0 | 0 | Arlene Dahl | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock hammer all day from C-093 | 5 | C-093 - C-116 | Cook Lake Rd - E | 0 | 44115 |  | 49 | 44121 | [5 empty] | Travis Chisolm | 05 | Corbiere and Sons Contracting563520201008-20L.O.A.1210 | Corbiere and Sons Contracting563520201008-20L.O.A.1210INV#064 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5635 | 20201008-20 | 53510502 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-10-08 | 1 | INV#064 | 44124 | 113 | 0 | 0 | Arlene Dahl | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock hammer all day from C-093 | 5 | C-093 - C-116 | Cook Lake Rd - E | 0 | 44115 |  | 49 | 44121 | [5 empty] | Travis Chisolm | 05 | Corbiere and Sons Contracting563520201008-20Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting563520201008-20Operator - Principle - After Jan 1011.5862.5INV#064 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5645 | 20201009-18 | 53510512 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10.5 | Dynamic | 98.61 | 0 |  |  | 1380.54 | 179.4702 | 1560.0102 | 2020-10-09 | 1 | INV#064 | 44124 | 113 | 0 | 0 | Arlene Dahl | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Moving road from C-037 - C-038 and fixing up patches with gravel. | 5 | C-036 - C-049 | Pays Plat River Rd - E | 0 | 44118 |  | 49 | 44121 | [5 empty] | Travis Chisolm | 05 | Corbiere and Sons Contracting564520201009-18Dozer D6 or equal- After Jan 1010.51380.54 | Corbiere and Sons Contracting564520201009-18Dozer D6 or equal- After Jan 1010.51380.54INV#064 | [5 empty] | 1 | 1380.54 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5645 | 20201009-18 | 53510512 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10.5 | Dynamic | 110.22 | 0 |  |  | 1543.08 | 200.6004 | 1743.6804 | 2020-10-09 | 1 | INV#064 | 44124 | 113 | 0 | 0 | Arlene Dahl | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Moving road from C-037 - C-038 and fixing up patches with gravel. | 5 | C-036 - C-049 | Pays Plat River Rd - E | 0 | 44118 |  | 49 | 44121 | [5 empty] | Travis Chisolm | 05 | Corbiere and Sons Contracting564520201009-18Excavator - 36 ton- After Jan 1010.51543.08 | Corbiere and Sons Contracting564520201009-18Excavator - 36 ton- After Jan 1010.51543.08INV#064 | [5 empty] | 1 | 1543.08 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5645 | 20201009-18 | 53510512 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-10-09 | 1 | INV#064 | 44124 | 113 | 0 | 0 | Arlene Dahl | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Moving road from C-037 - C-038 and fixing up patches with gravel. | 5 | C-036 - C-049 | Pays Plat River Rd - E | 0 | 44118 |  | 49 | 44121 | [5 empty] | Travis Chisolm | 05 | Corbiere and Sons Contracting564520201009-18Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting564520201009-18Light Truck - Pick up- After Jan 102487.5INV#064 | [5 empty] | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5645 | 20201009-18 | 53510512 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 10.5 | Dynamic | 103.54 | 0 |  |  | 1449.525 | 188.4383 | 1637.9633 | 2020-10-09 | 1 | INV#064 | 44124 | 113 | 0 | 0 | Arlene Dahl | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Moving road from C-037 - C-038 and fixing up patches with gravel. | 5 | C-036 - C-049 | Pays Plat River Rd - E | 0 | 44118 |  | 49 | 44121 | [5 empty] | Travis Chisolm | 05 | Corbiere and Sons Contracting564520201009-18Rock Truck - 30 Ton- After Jan 1010.51449.525 | Corbiere and Sons Contracting564520201009-18Rock Truck - 30 Ton- After Jan 1010.51449.525INV#064 | [5 empty] | 1 | 1449.525 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5645 | 20201009-18 | 53510512 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  |  | 630 | 81.9 | 711.9 | 2020-10-09 | 1 | INV#064 | 44124 | 113 | 0 | 0 | Arlene Dahl | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Moving road from C-037 - C-038 and fixing up patches with gravel. | 5 | C-036 - C-049 | Pays Plat River Rd - E | 0 | 44118 |  | 49 | 44121 | [5 empty] | Travis Chisolm | 05 | Corbiere and Sons Contracting564520201009-18L.O.A.3630 | Corbiere and Sons Contracting564520201009-18L.O.A.3630INV#064 | [5 empty] | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5645 | 20201009-18 | 53510512 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 23 | HR |  |  | 75 | 0 | 1725 | 224.25 | 1949.25 | 2020-10-09 | 1 | INV#064 | 44124 | 113 | 0 | 0 | Arlene Dahl | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Moving road from C-037 - C-038 and fixing up patches with gravel. | 5 | C-036 - C-049 | Pays Plat River Rd - E | 0 | 44118 |  | 49 | 44121 | [5 empty] | Travis Chisolm | 05 | Corbiere and Sons Contracting564520201009-18Operator - Principle - After Jan 10231725 | Corbiere and Sons Contracting564520201009-18Operator - Principle - After Jan 10231725INV#064 | [5 empty] | 1 | 1725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5645 | 20201009-18 | 53510512 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 11.5 | HR |  |  | 70 | 0 | 805 | 104.65 | 909.65 | 2020-10-09 | 1 | INV#064 | 44124 | 113 | 0 | 0 | Arlene Dahl | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Moving road from C-037 - C-038 and fixing up patches with gravel. | 5 | C-036 - C-049 | Pays Plat River Rd - E | 0 | 44118 |  | 49 | 44121 | [5 empty] | Travis Chisolm | 05 | Corbiere and Sons Contracting564520201009-18Driver - AZ - After Jan 1011.5805 | Corbiere and Sons Contracting564520201009-18Driver - AZ - After Jan 1011.5805INV#064 | [5 empty] | 1 | 805 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5647 | 20201009-20 | 53510504 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10.5 | Dynamic | 98.61 | 0 |  |  | 1380.54 | 179.4702 | 1560.0102 | 2020-10-09 | 1 | INV#064 | 44124 | 113 | 0 | 0 | Arlene Dahl | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hauling and spreading gravel up to 7201 and C-060 - C-059 | 5 | C-050 - C-069 | Antler Lake Rd | 0 | 44118 |  | 49 | 44121 | [5 empty] | Travis Chisolm | 05 | Corbiere and Sons Contracting564720201009-20Dozer D6 or equal- After Jan 1010.51380.54 | Corbiere and Sons Contracting564720201009-20Dozer D6 or equal- After Jan 1010.51380.54INV#064 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1380.54 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5647 | 20201009-20 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-10-09 | 1 | INV#064 | 44124 | 113 | 0 | 0 | Arlene Dahl | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hauling and spreading gravel up to 7201 and C-060 - C-059 | 5 | C-050 - C-069 | Antler Lake Rd | 0 | 44118 |  | 49 | 44121 | [5 empty] | Travis Chisolm | 05 | Corbiere and Sons Contracting564720201009-20Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting564720201009-20Light Truck - Pick up- After Jan 102487.5INV#064 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5647 | 20201009-20 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 8.5 | Dynamic | 103.54 | 0 |  |  | 1173.425 | 152.5453 | 1325.9703 | 2020-10-09 | 1 | INV#064 | 44124 | 113 | 0 | 0 | Arlene Dahl | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hauling and spreading gravel up to 7201 and C-060 - C-059 | 5 | C-050 - C-069 | Antler Lake Rd | 0 | 44118 |  | 49 | 44121 | [5 empty] | Travis Chisolm | 05 | Corbiere and Sons Contracting564720201009-20Rock Truck - 30 Ton- After Jan 108.51173.425 | Corbiere and Sons Contracting564720201009-20Rock Truck - 30 Ton- After Jan 108.51173.425INV#064 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1173.425 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5647 | 20201009-20 | 53510504 | Access | 0 | Foreman | 95 | 4 | HR |  |  | 95 | 0 | 380 | 49.4 | 429.4 | 2020-10-09 | 1 | INV#064 | 44124 | 113 | 0 | 0 | Arlene Dahl | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hauling and spreading gravel up to 7201 and C-060 - C-059 | 5 | C-050 - C-069 | Antler Lake Rd | 0 | 44118 |  | 49 | 44121 | [5 empty] | Travis Chisolm | 05 | Corbiere and Sons Contracting564720201009-20Foreman4380 | Corbiere and Sons Contracting564720201009-20Foreman4380INV#064 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5647 | 20201009-20 | 53510504 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-10-09 | 1 | INV#064 | 44124 | 113 | 0 | 0 | Arlene Dahl | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hauling and spreading gravel up to 7201 and C-060 - C-059 | 5 | C-050 - C-069 | Antler Lake Rd | 0 | 44118 |  | 49 | 44121 | [5 empty] | Travis Chisolm | 05 | Corbiere and Sons Contracting564720201009-20L.O.A.2420 | Corbiere and Sons Contracting564720201009-20L.O.A.2420INV#064 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5647 | 20201009-20 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 |  | 862.5 | 112.125 | 974.625 | 2020-10-09 | 1 | INV#064 | 44124 | 113 | 0 | 0 | Arlene Dahl | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hauling and spreading gravel up to 7201 and C-060 - C-059 | 5 | C-050 - C-069 | Antler Lake Rd | 0 | 44118 |  | 49 | 44121 | [5 empty] | Travis Chisolm | 05 | Corbiere and Sons Contracting564720201009-20Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting564720201009-20Operator - Principle - After Jan 1011.5862.5INV#064 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5647 | 20201009-20 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 9.5 | HR |  |  | 70 | 0 | 665 | 86.45 | 751.45 | 2020-10-09 | 1 | INV#064 | 44124 | 113 | 0 | 0 | Arlene Dahl | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hauling and spreading gravel up to 7201 and C-060 - C-059 | 5 | C-050 - C-069 | Antler Lake Rd | 0 | 44118 |  | 49 | 44121 | [5 empty] | Travis Chisolm | 05 | Corbiere and Sons Contracting564720201009-20Driver - AZ - After Jan 109.5665 | Corbiere and Sons Contracting564720201009-20Driver - AZ - After Jan 109.5665INV#064 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 665 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5648 | 20201009-21 | 53510503 | Access | 0 | Feller Buncher | 240 | 3 | HR | 180 | 0 |  |  | 720 | 93.6 | 813.6 | 2020-10-09 | 1 | INV#064 | 44124 | 113 | 0 | 0 | Arlene Dahl | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Put down corduroy between C-074 and C-075 as directed by Wes. | 5 | C-070 - C-075 | White Sand Rd | 0 | 44118 |  | 49 | 44121 | [5 empty] | Travis Chisolm | 05 | Corbiere and Sons Contracting564820201009-21Feller Buncher3720 | Corbiere and Sons Contracting564820201009-21Feller Buncher3720INV#064 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 720 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5648 | 20201009-21 | 53510503 | Access | 0 | Skidder | 171 | 3 | HR | 128.25 | 0 |  |  | 513 | 66.69 | 579.69 | 2020-10-09 | 1 | INV#064 | 44124 | 113 | 0 | 0 | Arlene Dahl | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Put down corduroy between C-074 and C-075 as directed by Wes. | 5 | C-070 - C-075 | White Sand Rd | 0 | 44118 |  | 49 | 44121 | [5 empty] | Travis Chisolm | 05 | Corbiere and Sons Contracting564820201009-21Skidder 3513 | Corbiere and Sons Contracting564820201009-21Skidder 3513INV#064 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 513 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5648 | 20201009-21 | 53510503 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-10-09 | 1 | INV#064 | 44124 | 113 | 0 | 0 | Arlene Dahl | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Put down corduroy between C-074 and C-075 as directed by Wes. | 5 | C-070 - C-075 | White Sand Rd | 0 | 44118 |  | 49 | 44121 | [5 empty] | Travis Chisolm | 05 | Corbiere and Sons Contracting564820201009-21L.O.A.2420 | Corbiere and Sons Contracting564820201009-21L.O.A.2420INV#064 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5648 | 20201009-21 | 53510503 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 75 | 0 | 450 | 58.5 | 508.5 | 2020-10-09 | 1 | INV#064 | 44124 | 113 | 0 | 0 | Arlene Dahl | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Put down corduroy between C-074 and C-075 as directed by Wes. | 5 | C-070 - C-075 | White Sand Rd | 0 | 44118 |  | 49 | 44121 | [5 empty] | Travis Chisolm | 05 | Corbiere and Sons Contracting564820201009-21Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting564820201009-21Operator - Principle - After Jan 106450INV#064 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5649 | 20201009-22 | 53510502 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10.5 | Dynamic | 110.22 | 0 |  |  | 1543.08 | 200.6004 | 1743.6804 | 2020-10-09 | 1 | INV#064 | 44124 | 113 | 0 | 0 | Arlene Dahl | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer all day from C-079 - C-080 | 5 | C-076 - C-092 | Cook Lake Rd - W | 0 | 44118 |  | 49 | 44121 | [5 empty] | Travis Chisolm | 05 | Corbiere and Sons Contracting564920201009-22Excavator - 36 ton- After Jan 1010.51543.08 | Corbiere and Sons Contracting564920201009-22Excavator - 36 ton- After Jan 1010.51543.08INV#064 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 1543.08 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5649 | 20201009-22 | 53510502 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 10.5 | HR | 47.54 | 0 |  |  | 665.49 | 86.5137 | 752.0037 | 2020-10-09 | 1 | INV#064 | 44124 | 113 | 0 | 0 | Arlene Dahl | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer all day from C-079 - C-080 | 5 | C-076 - C-092 | Cook Lake Rd - W | 0 | 44118 |  | 49 | 44121 | [5 empty] | Travis Chisolm | 05 | Corbiere and Sons Contracting564920201009-22Excavator Hammer - 30 - 50 ton- After Jan 1010.5665.49 | Corbiere and Sons Contracting564920201009-22Excavator Hammer - 30 - 50 ton- After Jan 1010.5665.49INV#064 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 665.49 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5649 | 20201009-22 | 53510502 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-10-09 | 1 | INV#064 | 44124 | 113 | 0 | 0 | Arlene Dahl | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer all day from C-079 - C-080 | 5 | C-076 - C-092 | Cook Lake Rd - W | 0 | 44118 |  | 49 | 44121 | [5 empty] | Travis Chisolm | 05 | Corbiere and Sons Contracting564920201009-22Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting564920201009-22Light Truck - Pick up- After Jan 101243.75INV#064 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5649 | 20201009-22 | 53510502 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-10-09 | 1 | INV#064 | 44124 | 113 | 0 | 0 | Arlene Dahl | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer all day from C-079 - C-080 | 5 | C-076 - C-092 | Cook Lake Rd - W | 0 | 44118 |  | 49 | 44121 | [5 empty] | Travis Chisolm | 05 | Corbiere and Sons Contracting564920201009-22L.O.A.1210 | Corbiere and Sons Contracting564920201009-22L.O.A.1210INV#064 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5649 | 20201009-22 | 53510502 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-10-09 | 1 | INV#064 | 44124 | 113 | 0 | 0 | Arlene Dahl | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer all day from C-079 - C-080 | 5 | C-076 - C-092 | Cook Lake Rd - W | 0 | 44118 |  | 49 | 44121 | [5 empty] | Travis Chisolm | 05 | Corbiere and Sons Contracting564920201009-22Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting564920201009-22Operator - Principle - After Jan 1011.5862.5INV#064 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5650 | 20201009-23 | 53510512 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10.5 | Dynamic | 98.61 | 0 |  |  | 1380.54 | 179.4702 | 1560.0102 | 2020-10-09 | 1 | INV#064 | 44124 | 113 | 0 | 0 | Arlene Dahl | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer doing road maintenance between C-093 and WC7491Dwayne road maintenance from C-085 - C-081 | 5 | C-076 - C-116 | Cook Lake Rd | 0 | 44118 |  | 49 | 44121 | [5 empty] | Travis Chisolm | 05 | Corbiere and Sons Contracting565020201009-23Dozer D6 or equal- After Jan 1010.51380.54 | Corbiere and Sons Contracting565020201009-23Dozer D6 or equal- After Jan 1010.51380.54INV#064 | [5 empty] | 1 | 1380.54 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5650 | 20201009-23 | 53510512 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 5 | Dynamic | 103.84 | 0 |  |  | 692.25 | 89.9925 | 782.2425 | 2020-10-09 | 1 | INV#064 | 44124 | 113 | 0 | 0 | Arlene Dahl | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer doing road maintenance between C-093 and WC7491Dwayne road maintenance from C-085 - C-081 | 5 | C-076 - C-116 | Cook Lake Rd | 0 | 44118 |  | 49 | 44121 | [5 empty] | Travis Chisolm | 05 | Corbiere and Sons Contracting565020201009-23Excavator - 30 ton- After Jan 105692.25 | Corbiere and Sons Contracting565020201009-23Excavator - 30 ton- After Jan 105692.25INV#064 | [5 empty] | 1 | 692.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5650 | 20201009-23 | 53510512 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-10-09 | 1 | INV#064 | 44124 | 113 | 0 | 0 | Arlene Dahl | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer doing road maintenance between C-093 and WC7491Dwayne road maintenance from C-085 - C-081 | 5 | C-076 - C-116 | Cook Lake Rd | 0 | 44118 |  | 49 | 44121 | [5 empty] | Travis Chisolm | 05 | Corbiere and Sons Contracting565020201009-23Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting565020201009-23Light Truck - Pick up- After Jan 101243.75INV#064 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5650 | 20201009-23 | 53510512 | Access | 0 | Foreman | 95 | 4 | HR |  |  | 95 | 0 | 380 | 49.4 | 429.4 | 2020-10-09 | 1 | INV#064 | 44124 | 113 | 0 | 0 | Arlene Dahl | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer doing road maintenance between C-093 and WC7491Dwayne road maintenance from C-085 - C-081 | 5 | C-076 - C-116 | Cook Lake Rd | 0 | 44118 |  | 49 | 44121 | [5 empty] | Travis Chisolm | 05 | Corbiere and Sons Contracting565020201009-23Foreman4380 | Corbiere and Sons Contracting565020201009-23Foreman4380INV#064 | [5 empty] | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5650 | 20201009-23 | 53510512 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-10-09 | 1 | INV#064 | 44124 | 113 | 0 | 0 | Arlene Dahl | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer doing road maintenance between C-093 and WC7491Dwayne road maintenance from C-085 - C-081 | 5 | C-076 - C-116 | Cook Lake Rd | 0 | 44118 |  | 49 | 44121 | [5 empty] | Travis Chisolm | 05 | Corbiere and Sons Contracting565020201009-23L.O.A.1210 | Corbiere and Sons Contracting565020201009-23L.O.A.1210INV#064 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5650 | 20201009-23 | 53510512 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 17 | HR |  |  | 75 | 0 | 1275 | 165.75 | 1440.75 | 2020-10-09 | 1 | INV#064 | 44124 | 113 | 0 | 0 | Arlene Dahl | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer doing road maintenance between C-093 and WC7491Dwayne road maintenance from C-085 - C-081 | 5 | C-076 - C-116 | Cook Lake Rd | 0 | 44118 |  | 49 | 44121 | [5 empty] | Travis Chisolm | 05 | Corbiere and Sons Contracting565020201009-23Operator - Principle - After Jan 10171275 | Corbiere and Sons Contracting565020201009-23Operator - Principle - After Jan 10171275INV#064 | [5 empty] | 1 | 1275 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5666 | 20201010-14 | 53510503 | Access | 0 | Skidder | 171 | 4 | HR | 128.25 | 0 |  |  | 684 | 88.92 | 772.92 | 2020-10-10 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Arlene Dahl | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator building temp access with corduroy, skidder moved bundles to wetland shoefly at C-062 | 5 | C-050 - C-069 | Antler Lake Rd | 0 | 44118 |  | 49 | 44123 | [5 empty] | Travis Chisolm | 05 | Corbiere and Sons Contracting566620201010-14Skidder 4684 | Corbiere and Sons Contracting566620201010-14Skidder 4684Inv#068 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 684 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5666 | 20201010-14 | 53510503 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 3 | Dynamic | 103.84 | 0 |  |  | 415.35 | 53.9955 | 469.3455 | 2020-10-10 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Arlene Dahl | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator building temp access with corduroy, skidder moved bundles to wetland shoefly at C-062 | 5 | C-050 - C-069 | Antler Lake Rd | 0 | 44118 |  | 49 | 44123 | [5 empty] | Travis Chisolm | 05 | Corbiere and Sons Contracting566620201010-14Excavator - 30 ton- After Jan 103415.35 | Corbiere and Sons Contracting566620201010-14Excavator - 30 ton- After Jan 103415.35Inv#068 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 415.35 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5666 | 20201010-14 | 53510503 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 3 | HR | 9.16 | 0 |  |  | 36.63 | 4.7619 | 41.3919 | 2020-10-10 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Arlene Dahl | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator building temp access with corduroy, skidder moved bundles to wetland shoefly at C-062 | 5 | C-050 - C-069 | Antler Lake Rd | 0 | 44118 |  | 49 | 44123 | [5 empty] | Travis Chisolm | 05 | Corbiere and Sons Contracting566620201010-14Excavator Thumb - 30 - 50 ton- After Jan 10336.63 | Corbiere and Sons Contracting566620201010-14Excavator Thumb - 30 - 50 ton- After Jan 10336.63Inv#068 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 36.63 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5666 | 20201010-14 | 53510503 | Access | 0 | Foreman | 95 | 2 | HR |  |  | 95 | 0 | 190 | 24.7 | 214.7 | 2020-10-10 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Arlene Dahl | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator building temp access with corduroy, skidder moved bundles to wetland shoefly at C-062 | 5 | C-050 - C-069 | Antler Lake Rd | 0 | 44118 |  | 49 | 44123 | [5 empty] | Travis Chisolm | 05 | Corbiere and Sons Contracting566620201010-14Foreman2190 | Corbiere and Sons Contracting566620201010-14Foreman2190Inv#068 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 190 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5666 | 20201010-14 | 53510503 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-10-10 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Arlene Dahl | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator building temp access with corduroy, skidder moved bundles to wetland shoefly at C-062 | 5 | C-050 - C-069 | Antler Lake Rd | 0 | 44118 |  | 49 | 44123 | [5 empty] | Travis Chisolm | 05 | Corbiere and Sons Contracting566620201010-14L.O.A.1210 | Corbiere and Sons Contracting566620201010-14L.O.A.1210Inv#068 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5666 | 20201010-14 | 53510503 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 7 | HR |  |  | 75 | 0 | 525 | 68.25 | 593.25 | 2020-10-10 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Arlene Dahl | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator building temp access with corduroy, skidder moved bundles to wetland shoefly at C-062 | 5 | C-050 - C-069 | Antler Lake Rd | 0 | 44118 |  | 49 | 44123 | [5 empty] | Travis Chisolm | 05 | Corbiere and Sons Contracting566620201010-14Operator - Principle - After Jan 107525 | Corbiere and Sons Contracting566620201010-14Operator - Principle - After Jan 107525Inv#068 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 525 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5667 | 20201010-15 | 53510512 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 5 | Dynamic | 98.61 | 0 |  |  | 657.4 | 85.462 | 742.862 | 2020-10-10 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Arlene Dahl | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Widening road along lake | 5 | C-050 - C-069 | Antler Lake Rd | 0 | 44118 |  | 49 | 44123 | [5 empty] | Travis Chisolm | 05 | Corbiere and Sons Contracting566720201010-15Dozer D6 or equal- After Jan 105657.4 | Corbiere and Sons Contracting566720201010-15Dozer D6 or equal- After Jan 105657.4Inv#068 | [5 empty] | 1 | 657.4 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5667 | 20201010-15 | 53510512 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-10-10 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Arlene Dahl | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Widening road along lake | 5 | C-050 - C-069 | Antler Lake Rd | 0 | 44118 |  | 49 | 44123 | [5 empty] | Travis Chisolm | 05 | Corbiere and Sons Contracting566720201010-15L.O.A.1210 | Corbiere and Sons Contracting566720201010-15L.O.A.1210Inv#068 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5667 | 20201010-15 | 53510512 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5 | HR |  |  | 75 | 0 | 375 | 48.75 | 423.75 | 2020-10-10 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Arlene Dahl | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Widening road along lake | 5 | C-050 - C-069 | Antler Lake Rd | 0 | 44118 |  | 49 | 44123 | [5 empty] | Travis Chisolm | 05 | Corbiere and Sons Contracting566720201010-15Operator - Principle - After Jan 105375 | Corbiere and Sons Contracting566720201010-15Operator - Principle - After Jan 105375Inv#068 | [5 empty] | 1 | 375 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5668 | 20201010-16 | 53510504 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 5 | Dynamic | 103.84 | 0 |  |  | 692.25 | 89.9925 | 782.2425 | 2020-10-10 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Arlene Dahl | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks - sent home as prep workin needed to be done. | 5 | C-050 - C-069 | Antler Lake Rd | 0 | 44118 |  | 49 | 44123 | [5 empty] | Travis Chisolm | 05 | Corbiere and Sons Contracting566820201010-16Excavator - 30 ton- After Jan 105692.25 | Corbiere and Sons Contracting566820201010-16Excavator - 30 ton- After Jan 105692.25Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 692.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5668 | 20201010-16 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-10-10 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Arlene Dahl | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks - sent home as prep workin needed to be done. | 5 | C-050 - C-069 | Antler Lake Rd | 0 | 44118 |  | 49 | 44123 | [5 empty] | Travis Chisolm | 05 | Corbiere and Sons Contracting566820201010-16Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting566820201010-16Light Truck - Pick up- After Jan 101243.75Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5668 | 20201010-16 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 13 | Dynamic | 103.54 | 0 |  |  | 1794.65 | 233.3045 | 2027.9545 | 2020-10-10 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Arlene Dahl | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks - sent home as prep workin needed to be done. | 5 | C-050 - C-069 | Antler Lake Rd | 0 | 44118 |  | 49 | 44123 | [5 empty] | Travis Chisolm | 05 | Corbiere and Sons Contracting566820201010-16Rock Truck - 30 Ton- After Jan 10131794.65 | Corbiere and Sons Contracting566820201010-16Rock Truck - 30 Ton- After Jan 10131794.65Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1794.65 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5669 | 20201010-17 | 53510502 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 7 | Dynamic | 110.22 | 0 |  |  | 1028.72 | 133.7336 | 1162.4536 | 2020-10-10 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Arlene Dahl | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock hammer from 10:30-6:00pm | 5 | C-050 - C-069 | Antler Lake Rd | 0 | 44118 |  | 49 | 44123 | [5 empty] | Travis Chisolm | 05 | Corbiere and Sons Contracting566920201010-17Excavator - 36 ton- After Jan 1071028.72 | Corbiere and Sons Contracting566920201010-17Excavator - 36 ton- After Jan 1071028.72Inv#068 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 1028.72 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5669 | 20201010-17 | 53510502 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 7 | HR | 47.54 | 0 |  |  | 443.66 | 57.6758 | 501.3358 | 2020-10-10 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Arlene Dahl | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock hammer from 10:30-6:00pm | 5 | C-050 - C-069 | Antler Lake Rd | 0 | 44118 |  | 49 | 44123 | [5 empty] | Travis Chisolm | 05 | Corbiere and Sons Contracting566920201010-17Excavator Hammer - 30 - 50 ton- After Jan 107443.66 | Corbiere and Sons Contracting566920201010-17Excavator Hammer - 30 - 50 ton- After Jan 107443.66Inv#068 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 443.66 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5669 | 20201010-17 | 53510502 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-10-10 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Arlene Dahl | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock hammer from 10:30-6:00pm | 5 | C-050 - C-069 | Antler Lake Rd | 0 | 44118 |  | 49 | 44123 | [5 empty] | Travis Chisolm | 05 | Corbiere and Sons Contracting566920201010-17Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting566920201010-17Light Truck - Pick up- After Jan 101243.75Inv#068 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5669 | 20201010-17 | 53510502 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-10-10 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Arlene Dahl | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock hammer from 10:30-6:00pm | 5 | C-050 - C-069 | Antler Lake Rd | 0 | 44118 |  | 49 | 44123 | [5 empty] | Travis Chisolm | 05 | Corbiere and Sons Contracting566920201010-17L.O.A.1210 | Corbiere and Sons Contracting566920201010-17L.O.A.1210Inv#068 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5669 | 20201010-17 | 53510502 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 7.5 | HR |  |  | 75 | 0 | 562.5 | 73.125 | 635.625 | 2020-10-10 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Arlene Dahl | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock hammer from 10:30-6:00pm | 5 | C-050 - C-069 | Antler Lake Rd | 0 | 44118 |  | 49 | 44123 | [5 empty] | Travis Chisolm | 05 | Corbiere and Sons Contracting566920201010-17Operator - Principle - After Jan 107.5562.5 | Corbiere and Sons Contracting566920201010-17Operator - Principle - After Jan 107.5562.5Inv#068 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 562.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5670 | 20201010-18 | 53510503 | Access | 0 | Feller Buncher | 240 | 3 | HR | 180 | 0 |  |  | 720 | 93.6 | 813.6 | 2020-10-10 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Arlene Dahl | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Putting down corudroy between C-074 - C075 as directed by Wes - 60m complete. | 5 | C-070 - C-075 | White Sands Rd | 0 | 44118 |  | 49 | 44123 | [5 empty] | Travis Chisolm | 05 | Corbiere and Sons Contracting567020201010-18Feller Buncher3720 | Corbiere and Sons Contracting567020201010-18Feller Buncher3720Inv#068 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 720 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5670 | 20201010-18 | 53510503 | Access | 0 | Skidder | 171 | 3 | HR | 128.25 | 0 |  |  | 513 | 66.69 | 579.69 | 2020-10-10 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Arlene Dahl | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Putting down corudroy between C-074 - C075 as directed by Wes - 60m complete. | 5 | C-070 - C-075 | White Sands Rd | 0 | 44118 |  | 49 | 44123 | [5 empty] | Travis Chisolm | 05 | Corbiere and Sons Contracting567020201010-18Skidder 3513 | Corbiere and Sons Contracting567020201010-18Skidder 3513Inv#068 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 513 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5670 | 20201010-18 | 53510503 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-10-10 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Arlene Dahl | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Putting down corudroy between C-074 - C075 as directed by Wes - 60m complete. | 5 | C-070 - C-075 | White Sands Rd | 0 | 44118 |  | 49 | 44123 | [5 empty] | Travis Chisolm | 05 | Corbiere and Sons Contracting567020201010-18L.O.A.2420 | Corbiere and Sons Contracting567020201010-18L.O.A.2420Inv#068 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5670 | 20201010-18 | 53510503 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 75 | 0 | 450 | 58.5 | 508.5 | 2020-10-10 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Arlene Dahl | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Putting down corudroy between C-074 - C075 as directed by Wes - 60m complete. | 5 | C-070 - C-075 | White Sands Rd | 0 | 44118 |  | 49 | 44123 | [5 empty] | Travis Chisolm | 05 | Corbiere and Sons Contracting567020201010-18Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting567020201010-18Operator - Principle - After Jan 106450Inv#068 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5671 | 20201010-19 | 53510502 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10.5 | Dynamic | 110.22 | 0 |  |  | 1543.08 | 200.6004 | 1743.6804 | 2020-10-10 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Arlene Dahl | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working on rock hammer all day | 5 | C-076 - C-116 | Cook Lake Rd | 0 | 44118 |  | 49 | 44123 | [5 empty] | Travis Chisolm | 05 | Corbiere and Sons Contracting567120201010-19Excavator - 36 ton- After Jan 1010.51543.08 | Corbiere and Sons Contracting567120201010-19Excavator - 36 ton- After Jan 1010.51543.08Inv#068 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 1543.08 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5671 | 20201010-19 | 53510502 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 10.5 | HR | 47.54 | 0 |  |  | 665.49 | 86.5137 | 752.0037 | 2020-10-10 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Arlene Dahl | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working on rock hammer all day | 5 | C-076 - C-116 | Cook Lake Rd | 0 | 44118 |  | 49 | 44123 | [5 empty] | Travis Chisolm | 05 | Corbiere and Sons Contracting567120201010-19Excavator Hammer - 30 - 50 ton- After Jan 1010.5665.49 | Corbiere and Sons Contracting567120201010-19Excavator Hammer - 30 - 50 ton- After Jan 1010.5665.49Inv#068 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 665.49 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5671 | 20201010-19 | 53510502 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-10-10 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Arlene Dahl | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working on rock hammer all day | 5 | C-076 - C-116 | Cook Lake Rd | 0 | 44118 |  | 49 | 44123 | [5 empty] | Travis Chisolm | 05 | Corbiere and Sons Contracting567120201010-19Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting567120201010-19Light Truck - Pick up- After Jan 101243.75Inv#068 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5671 | 20201010-19 | 53510502 | Access | 0 | Foreman | 95 | 3 | HR |  |  | 95 | 0 | 285 | 37.05 | 322.05 | 2020-10-10 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Arlene Dahl | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working on rock hammer all day | 5 | C-076 - C-116 | Cook Lake Rd | 0 | 44118 |  | 49 | 44123 | [5 empty] | Travis Chisolm | 05 | Corbiere and Sons Contracting567120201010-19Foreman3285 | Corbiere and Sons Contracting567120201010-19Foreman3285Inv#068 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 285 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5671 | 20201010-19 | 53510502 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-10-10 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Arlene Dahl | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working on rock hammer all day | 5 | C-076 - C-116 | Cook Lake Rd | 0 | 44118 |  | 49 | 44123 | [5 empty] | Travis Chisolm | 05 | Corbiere and Sons Contracting567120201010-19L.O.A.1210 | Corbiere and Sons Contracting567120201010-19L.O.A.1210Inv#068 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5671 | 20201010-19 | 53510502 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-10-10 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Arlene Dahl | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working on rock hammer all day | 5 | C-076 - C-116 | Cook Lake Rd | 0 | 44118 |  | 49 | 44123 | [5 empty] | Travis Chisolm | 05 | Corbiere and Sons Contracting567120201010-19Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting567120201010-19Operator - Principle - After Jan 1011.5862.5Inv#068 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5675 | 20201010-23 | 53510512 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10.5 | Dynamic | 98.61 | 0 |  |  | 1380.54 | 179.4702 | 1560.0102 | 2020-10-10 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Arlene Dahl | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer doing road maintenace all day | 5 | C-076 - C-116 | Cook Lake Rd | 0 | 44118 |  | 49 | 44123 | [5 empty] | Travis Chisolm | 05 | Corbiere and Sons Contracting567520201010-23Dozer D6 or equal- After Jan 1010.51380.54 | Corbiere and Sons Contracting567520201010-23Dozer D6 or equal- After Jan 1010.51380.54Inv#068 | [5 empty] | 1 | 1380.54 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5675 | 20201010-23 | 53510512 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-10-10 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Arlene Dahl | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer doing road maintenace all day | 5 | C-076 - C-116 | Cook Lake Rd | 0 | 44118 |  | 49 | 44123 | [5 empty] | Travis Chisolm | 05 | Corbiere and Sons Contracting567520201010-23Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting567520201010-23Light Truck - Pick up- After Jan 101243.75Inv#068 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5675 | 20201010-23 | 53510512 | Access | 0 | Foreman | 95 | 3 | HR |  |  | 95 | 0 | 285 | 37.05 | 322.05 | 2020-10-10 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Arlene Dahl | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer doing road maintenace all day | 5 | C-076 - C-116 | Cook Lake Rd | 0 | 44118 |  | 49 | 44123 | [5 empty] | Travis Chisolm | 05 | Corbiere and Sons Contracting567520201010-23Foreman3285 | Corbiere and Sons Contracting567520201010-23Foreman3285Inv#068 | [5 empty] | 1 | 285 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5675 | 20201010-23 | 53510512 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-10-10 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Arlene Dahl | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer doing road maintenace all day | 5 | C-076 - C-116 | Cook Lake Rd | 0 | 44118 |  | 49 | 44123 | [5 empty] | Travis Chisolm | 05 | Corbiere and Sons Contracting567520201010-23L.O.A.1210 | Corbiere and Sons Contracting567520201010-23L.O.A.1210Inv#068 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5675 | 20201010-23 | 53510512 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-10-10 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Arlene Dahl | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer doing road maintenace all day | 5 | C-076 - C-116 | Cook Lake Rd | 0 | 44118 |  | 49 | 44123 | [5 empty] | Travis Chisolm | 05 | Corbiere and Sons Contracting567520201010-23Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting567520201010-23Operator - Principle - After Jan 1011.5862.5Inv#068 | [5 empty] | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5691 | 20201011-10 | 53510502 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10.5 | Dynamic | 110.22 | 0 |  |  | 1543.08 | 200.6004 | 1743.6804 | 2020-10-11 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Arlene Dahl | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working on hammer all day from C-078 - C-080 | 5 | C-076 - C-092 | Cook Lake Rd - W | 0 | 44120 |  | 49 | 44123 | [5 empty] | Travis Chisolm | 05 | Corbiere and Sons Contracting569120201011-10Excavator - 36 ton- After Jan 1010.51543.08 | Corbiere and Sons Contracting569120201011-10Excavator - 36 ton- After Jan 1010.51543.08Inv#068 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 1543.08 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5691 | 20201011-10 | 53510502 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 10.5 | HR | 47.54 | 0 |  |  | 665.49 | 86.5137 | 752.0037 | 2020-10-11 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Arlene Dahl | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working on hammer all day from C-078 - C-080 | 5 | C-076 - C-092 | Cook Lake Rd - W | 0 | 44120 |  | 49 | 44123 | [5 empty] | Travis Chisolm | 05 | Corbiere and Sons Contracting569120201011-10Excavator Hammer - 30 - 50 ton- After Jan 1010.5665.49 | Corbiere and Sons Contracting569120201011-10Excavator Hammer - 30 - 50 ton- After Jan 1010.5665.49Inv#068 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 665.49 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5691 | 20201011-10 | 53510502 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-10-11 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Arlene Dahl | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working on hammer all day from C-078 - C-080 | 5 | C-076 - C-092 | Cook Lake Rd - W | 0 | 44120 |  | 49 | 44123 | [5 empty] | Travis Chisolm | 05 | Corbiere and Sons Contracting569120201011-10Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting569120201011-10Light Truck - Pick up- After Jan 101243.75Inv#068 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5691 | 20201011-10 | 53510502 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-10-11 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Arlene Dahl | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working on hammer all day from C-078 - C-080 | 5 | C-076 - C-092 | Cook Lake Rd - W | 0 | 44120 |  | 49 | 44123 | [5 empty] | Travis Chisolm | 05 | Corbiere and Sons Contracting569120201011-10L.O.A.1210 | Corbiere and Sons Contracting569120201011-10L.O.A.1210Inv#068 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5691 | 20201011-10 | 53510502 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-10-11 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Arlene Dahl | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working on hammer all day from C-078 - C-080 | 5 | C-076 - C-092 | Cook Lake Rd - W | 0 | 44120 |  | 49 | 44123 | [5 empty] | Travis Chisolm | 05 | Corbiere and Sons Contracting569120201011-10Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting569120201011-10Operator - Principle - After Jan 1011.5862.5Inv#068 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5686 | 20201011-11 | 53510504 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10.5 | Dynamic | 98.61 | 0 |  |  | 1380.54 | 179.4702 | 1560.0102 | 2020-10-11 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Arlene Dahl | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks, dozer spreading gravel | 5 | C-050 - C-069 | Antler Lake Rd | 0 | 44120 |  | 49 | 44123 | [5 empty] | Travis Chisolm | 05 | Corbiere and Sons Contracting568620201011-11Dozer D6 or equal- After Jan 1010.51380.54 | Corbiere and Sons Contracting568620201011-11Dozer D6 or equal- After Jan 1010.51380.54Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1380.54 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5686 | 20201011-11 | 53510504 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 6 | Dynamic | 103.84 | 0 |  |  | 830.7 | 107.991 | 938.691 | 2020-10-11 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Arlene Dahl | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks, dozer spreading gravel | 5 | C-050 - C-069 | Antler Lake Rd | 0 | 44120 |  | 49 | 44123 | [5 empty] | Travis Chisolm | 05 | Corbiere and Sons Contracting568620201011-11Excavator - 30 ton- After Jan 106830.7 | Corbiere and Sons Contracting568620201011-11Excavator - 30 ton- After Jan 106830.7Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 830.7 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5686 | 20201011-11 | 53510504 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 5 | Dynamic | 110.22 | 0 |  |  | 734.8 | 95.524 | 830.324 | 2020-10-11 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Arlene Dahl | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks, dozer spreading gravel | 5 | C-050 - C-069 | Antler Lake Rd | 0 | 44120 |  | 49 | 44123 | [5 empty] | Travis Chisolm | 05 | Corbiere and Sons Contracting568620201011-11Excavator - 36 ton- After Jan 105734.8 | Corbiere and Sons Contracting568620201011-11Excavator - 36 ton- After Jan 105734.8Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 734.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5686 | 20201011-11 | 53510504 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 5 | HR | 9.16 | 0 |  |  | 61.05 | 7.9365 | 68.9865 | 2020-10-11 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Arlene Dahl | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks, dozer spreading gravel | 5 | C-050 - C-069 | Antler Lake Rd | 0 | 44120 |  | 49 | 44123 | [5 empty] | Travis Chisolm | 05 | Corbiere and Sons Contracting568620201011-11Excavator Thumb - 30 - 50 ton- After Jan 10561.05 | Corbiere and Sons Contracting568620201011-11Excavator Thumb - 30 - 50 ton- After Jan 10561.05Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 61.05 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5686 | 20201011-11 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-10-11 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Arlene Dahl | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks, dozer spreading gravel | 5 | C-050 - C-069 | Antler Lake Rd | 0 | 44120 |  | 49 | 44123 | [5 empty] | Travis Chisolm | 05 | Corbiere and Sons Contracting568620201011-11Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting568620201011-11Light Truck - Pick up- After Jan 102487.5Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5686 | 20201011-11 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 6 | Dynamic | 103.54 | 0 |  |  | 828.3 | 107.679 | 935.979 | 2020-10-11 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Arlene Dahl | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks, dozer spreading gravel | 5 | C-050 - C-069 | Antler Lake Rd | 0 | 44120 |  | 49 | 44123 | [5 empty] | Travis Chisolm | 05 | Corbiere and Sons Contracting568620201011-11Rock Truck - 30 Ton- After Jan 106828.3 | Corbiere and Sons Contracting568620201011-11Rock Truck - 30 Ton- After Jan 106828.3Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 828.3 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5686 | 20201011-11 | 53510504 | Access | 0 | Foreman | 95 | 4 | HR |  |  | 95 | 0 | 380 | 49.4 | 429.4 | 2020-10-11 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Arlene Dahl | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks, dozer spreading gravel | 5 | C-050 - C-069 | Antler Lake Rd | 0 | 44120 |  | 49 | 44123 | [5 empty] | Travis Chisolm | 05 | Corbiere and Sons Contracting568620201011-11Foreman4380 | Corbiere and Sons Contracting568620201011-11Foreman4380Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5686 | 20201011-11 | 53510504 | Access | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2020-10-11 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Arlene Dahl | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks, dozer spreading gravel | 5 | C-050 - C-069 | Antler Lake Rd | 0 | 44120 |  | 49 | 44123 | [5 empty] | Travis Chisolm | 05 | Corbiere and Sons Contracting568620201011-11L.O.A.51050 | Corbiere and Sons Contracting568620201011-11L.O.A.51050Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5686 | 20201011-11 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 24 | HR |  |  | 75 | 0 | 1800 | 234 | 2034 | 2020-10-11 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Arlene Dahl | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks, dozer spreading gravel | 5 | C-050 - C-069 | Antler Lake Rd | 0 | 44120 |  | 49 | 44123 | [5 empty] | Travis Chisolm | 05 | Corbiere and Sons Contracting568620201011-11Operator - Principle - After Jan 10241800 | Corbiere and Sons Contracting568620201011-11Operator - Principle - After Jan 10241800Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1800 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5686 | 20201011-11 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 8.5 | HR |  |  | 70 | 0 | 595 | 77.35 | 672.35 | 2020-10-11 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Arlene Dahl | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks, dozer spreading gravel | 5 | C-050 - C-069 | Antler Lake Rd | 0 | 44120 |  | 49 | 44123 | [5 empty] | Travis Chisolm | 05 | Corbiere and Sons Contracting568620201011-11Driver - AZ - After Jan 108.5595 | Corbiere and Sons Contracting568620201011-11Driver - AZ - After Jan 108.5595Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 595 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5687 | 20201011-12 | 53510512 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 3 | Dynamic | 103.84 | 0 |  |  | 415.35 | 53.9955 | 469.3455 | 2020-10-11 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Arlene Dahl | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Shaping road and doing maintenance | 5 | C-050 - C-069 | Antler Lake Rd | 0 | 44120 |  | 49 | 44123 | [5 empty] | Travis Chisolm | 05 | Corbiere and Sons Contracting568720201011-12Excavator - 30 ton- After Jan 103415.35 | Corbiere and Sons Contracting568720201011-12Excavator - 30 ton- After Jan 103415.35Inv#068 | [5 empty] | 1 | 415.35 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5687 | 20201011-12 | 53510512 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 3 | HR |  |  | 75 | 0 | 225 | 29.25 | 254.25 | 2020-10-11 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Arlene Dahl | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Shaping road and doing maintenance | 5 | C-050 - C-069 | Antler Lake Rd | 0 | 44120 |  | 49 | 44123 | [5 empty] | Travis Chisolm | 05 | Corbiere and Sons Contracting568720201011-12Operator - Principle - After Jan 103225 | Corbiere and Sons Contracting568720201011-12Operator - Principle - After Jan 103225Inv#068 | [5 empty] | 1 | 225 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5688 | 20201011-13 | 53510503 | Access | 0 | Feller Buncher | 240 | 5 | HR | 180 | 0 |  |  | 1200 | 156 | 1356 | 2020-10-11 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Arlene Dahl | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Greg on Feller Buncher putting down corduroy from C-061 - C-062 - Cory on SkidderBen and Blade rolling out geo in wetland access development area | 5 | C-050 - C-069 | Antler Lake Rd | 0 | 44120 |  | 49 | 44123 | [5 empty] | Travis Chisolm | 05 | Corbiere and Sons Contracting568820201011-13Feller Buncher51200 | Corbiere and Sons Contracting568820201011-13Feller Buncher51200Inv#068 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 1200 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5688 | 20201011-13 | 53510503 | Access | 0 | Skidder | 171 | 5 | HR | 128.25 | 0 |  |  | 855 | 111.15 | 966.15 | 2020-10-11 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Arlene Dahl | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Greg on Feller Buncher putting down corduroy from C-061 - C-062 - Cory on SkidderBen and Blade rolling out geo in wetland access development area | 5 | C-050 - C-069 | Antler Lake Rd | 0 | 44120 |  | 49 | 44123 | [5 empty] | Travis Chisolm | 05 | Corbiere and Sons Contracting568820201011-13Skidder 5855 | Corbiere and Sons Contracting568820201011-13Skidder 5855Inv#068 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 855 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5688 | 20201011-13 | 53510503 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-10-11 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Arlene Dahl | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Greg on Feller Buncher putting down corduroy from C-061 - C-062 - Cory on SkidderBen and Blade rolling out geo in wetland access development area | 5 | C-050 - C-069 | Antler Lake Rd | 0 | 44120 |  | 49 | 44123 | [5 empty] | Travis Chisolm | 05 | Corbiere and Sons Contracting568820201011-13Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting568820201011-13Light Truck - Pick up- After Jan 102487.5Inv#068 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5688 | 20201011-13 | 53510503 | Access | 0 | Foreman | 95 | 4 | HR |  |  | 95 | 0 | 380 | 49.4 | 429.4 | 2020-10-11 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Arlene Dahl | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Greg on Feller Buncher putting down corduroy from C-061 - C-062 - Cory on SkidderBen and Blade rolling out geo in wetland access development area | 5 | C-050 - C-069 | Antler Lake Rd | 0 | 44120 |  | 49 | 44123 | [5 empty] | Travis Chisolm | 05 | Corbiere and Sons Contracting568820201011-13Foreman4380 | Corbiere and Sons Contracting568820201011-13Foreman4380Inv#068 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5688 | 20201011-13 | 53510503 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2020-10-11 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Arlene Dahl | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Greg on Feller Buncher putting down corduroy from C-061 - C-062 - Cory on SkidderBen and Blade rolling out geo in wetland access development area | 5 | C-050 - C-069 | Antler Lake Rd | 0 | 44120 |  | 49 | 44123 | [5 empty] | Travis Chisolm | 05 | Corbiere and Sons Contracting568820201011-13L.O.A.4840 | Corbiere and Sons Contracting568820201011-13L.O.A.4840Inv#068 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5688 | 20201011-13 | 53510503 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 10 | HR |  |  | 75 | 0 | 750 | 97.5 | 847.5 | 2020-10-11 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Arlene Dahl | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Greg on Feller Buncher putting down corduroy from C-061 - C-062 - Cory on SkidderBen and Blade rolling out geo in wetland access development area | 5 | C-050 - C-069 | Antler Lake Rd | 0 | 44120 |  | 49 | 44123 | [5 empty] | Travis Chisolm | 05 | Corbiere and Sons Contracting568820201011-13Operator - Principle - After Jan 1010750 | Corbiere and Sons Contracting568820201011-13Operator - Principle - After Jan 1010750Inv#068 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 750 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5688 | 20201011-13 | 53510503 | Access | 0 | Labourer - General - After Jan 10 | 60 | 6 | HR |  |  | 60 | 0 | 360 | 46.8 | 406.8 | 2020-10-11 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Arlene Dahl | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Greg on Feller Buncher putting down corduroy from C-061 - C-062 - Cory on SkidderBen and Blade rolling out geo in wetland access development area | 5 | C-050 - C-069 | Antler Lake Rd | 0 | 44120 |  | 49 | 44123 | [5 empty] | Travis Chisolm | 05 | Corbiere and Sons Contracting568820201011-13Labourer - General - After Jan 106360 | Corbiere and Sons Contracting568820201011-13Labourer - General - After Jan 106360Inv#068 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 360 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5685 | 20201011-9 | 53510504 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10.5 | Dynamic | 103.84 | 0 |  |  | 1453.725 | 188.9843 | 1642.7093 | 2020-10-11 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Arlene Dahl | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock trucks and excavator on gravel haul | 5 | C-076 - C-116 | Cook Lake Rd | 0 | 44120 |  | 49 | 44123 | [5 empty] | Travis Chisolm | 05 | Corbiere and Sons Contracting568520201011-9Excavator - 30 ton- After Jan 1010.51453.725 | Corbiere and Sons Contracting568520201011-9Excavator - 30 ton- After Jan 1010.51453.725Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1453.725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5685 | 20201011-9 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 19 | Dynamic | 103.54 | 0 |  |  | 2622.95 | 340.9835 | 2963.9335 | 2020-10-11 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Arlene Dahl | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock trucks and excavator on gravel haul | 5 | C-076 - C-116 | Cook Lake Rd | 0 | 44120 |  | 49 | 44123 | [5 empty] | Travis Chisolm | 05 | Corbiere and Sons Contracting568520201011-9Rock Truck - 30 Ton- After Jan 10192622.95 | Corbiere and Sons Contracting568520201011-9Rock Truck - 30 Ton- After Jan 10192622.95Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 2622.95 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5685 | 20201011-9 | 53510504 | Access | 0 | Foreman | 95 | 6 | HR |  |  | 95 | 0 | 570 | 74.1 | 644.1 | 2020-10-11 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Arlene Dahl | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock trucks and excavator on gravel haul | 5 | C-076 - C-116 | Cook Lake Rd | 0 | 44120 |  | 49 | 44123 | [5 empty] | Travis Chisolm | 05 | Corbiere and Sons Contracting568520201011-9Foreman6570 | Corbiere and Sons Contracting568520201011-9Foreman6570Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 570 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5685 | 20201011-9 | 53510504 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2020-10-11 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Arlene Dahl | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock trucks and excavator on gravel haul | 5 | C-076 - C-116 | Cook Lake Rd | 0 | 44120 |  | 49 | 44123 | [5 empty] | Travis Chisolm | 05 | Corbiere and Sons Contracting568520201011-9L.O.A.4840 | Corbiere and Sons Contracting568520201011-9L.O.A.4840Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5685 | 20201011-9 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-10-11 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Arlene Dahl | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock trucks and excavator on gravel haul | 5 | C-076 - C-116 | Cook Lake Rd | 0 | 44120 |  | 49 | 44123 | [5 empty] | Travis Chisolm | 05 | Corbiere and Sons Contracting568520201011-9Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting568520201011-9Operator - Principle - After Jan 1011.5862.5Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5685 | 20201011-9 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 21 | HR |  |  | 70 | 0 | 1470 | 191.1 | 1661.1 | 2020-10-11 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Arlene Dahl | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock trucks and excavator on gravel haul | 5 | C-076 - C-116 | Cook Lake Rd | 0 | 44120 |  | 49 | 44123 | [5 empty] | Travis Chisolm | 05 | Corbiere and Sons Contracting568520201011-9Driver - AZ - After Jan 10211470 | Corbiere and Sons Contracting568520201011-9Driver - AZ - After Jan 10211470Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1470 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5842 | 20201012-13 | 53510503 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 5 | Dynamic | 98.61 | 0 |  |  | 657.4 | 85.462 | 742.862 | 2020-10-12 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks until rain delay, dozer spreading gravel over wetland access area, rock trucks running until rain delay. Ben and Blade rolling out geo for 2 hours | 5 | C050-C069 | Antler Lake | 0 | 44127 |  | 36 | 44127 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting584220201012-13Dozer D6 or equal- After Jan 105657.4 | Corbiere and Sons Contracting584220201012-13Dozer D6 or equal- After Jan 105657.4Inv#068 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 657.4 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5842 | 20201012-13 | 53510503 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 5 | Dynamic | 110.22 | 0 |  |  | 734.8 | 95.524 | 830.324 | 2020-10-12 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks until rain delay, dozer spreading gravel over wetland access area, rock trucks running until rain delay. Ben and Blade rolling out geo for 2 hours | 5 | C050-C069 | Antler Lake | 0 | 44127 |  | 36 | 44127 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting584220201012-13Excavator - 36 ton- After Jan 105734.8 | Corbiere and Sons Contracting584220201012-13Excavator - 36 ton- After Jan 105734.8Inv#068 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 734.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5842 | 20201012-13 | 53510503 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 5 | HR | 9.16 | 0 |  |  | 61.05 | 7.9365 | 68.9865 | 2020-10-12 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks until rain delay, dozer spreading gravel over wetland access area, rock trucks running until rain delay. Ben and Blade rolling out geo for 2 hours | 5 | C050-C069 | Antler Lake | 0 | 44127 |  | 36 | 44127 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting584220201012-13Excavator Thumb - 30 - 50 ton- After Jan 10561.05 | Corbiere and Sons Contracting584220201012-13Excavator Thumb - 30 - 50 ton- After Jan 10561.05Inv#068 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 61.05 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5842 | 20201012-13 | 53510503 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2020-10-12 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks until rain delay, dozer spreading gravel over wetland access area, rock trucks running until rain delay. Ben and Blade rolling out geo for 2 hours | 5 | C050-C069 | Antler Lake | 0 | 44127 |  | 36 | 44127 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting584220201012-13Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting584220201012-13Light Truck - Pick up- After Jan 103731.25Inv#068 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 731.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5842 | 20201012-13 | 53510503 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 5 | Dynamic | 103.54 | 0 |  |  | 690.25 | 89.7325 | 779.9825 | 2020-10-12 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks until rain delay, dozer spreading gravel over wetland access area, rock trucks running until rain delay. Ben and Blade rolling out geo for 2 hours | 5 | C050-C069 | Antler Lake | 0 | 44127 |  | 36 | 44127 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting584220201012-13Rock Truck - 30 Ton- After Jan 105690.25 | Corbiere and Sons Contracting584220201012-13Rock Truck - 30 Ton- After Jan 105690.25Inv#068 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 690.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5842 | 20201012-13 | 53510503 | Access | 0 | Foreman | 95 | 5 | HR |  |  | 95 | 0 | 475 | 61.75 | 536.75 | 2020-10-12 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks until rain delay, dozer spreading gravel over wetland access area, rock trucks running until rain delay. Ben and Blade rolling out geo for 2 hours | 5 | C050-C069 | Antler Lake | 0 | 44127 |  | 36 | 44127 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting584220201012-13Foreman5475 | Corbiere and Sons Contracting584220201012-13Foreman5475Inv#068 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 475 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5842 | 20201012-13 | 53510503 | Access | 0 | L.O.A. | 210 | 7 | DAY |  |  |  | 0 | 1470 | 191.1 | 1661.1 | 2020-10-12 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks until rain delay, dozer spreading gravel over wetland access area, rock trucks running until rain delay. Ben and Blade rolling out geo for 2 hours | 5 | C050-C069 | Antler Lake | 0 | 44127 |  | 36 | 44127 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting584220201012-13L.O.A.71470 | Corbiere and Sons Contracting584220201012-13L.O.A.71470Inv#068 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 1470 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5842 | 20201012-13 | 53510503 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2020-10-12 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks until rain delay, dozer spreading gravel over wetland access area, rock trucks running until rain delay. Ben and Blade rolling out geo for 2 hours | 5 | C050-C069 | Antler Lake | 0 | 44127 |  | 36 | 44127 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting584220201012-13Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting584220201012-13Operator - Principle - After Jan 1011825Inv#068 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5842 | 20201012-13 | 53510503 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 5.5 | HR |  |  | 70 | 0 | 385 | 50.05 | 435.05 | 2020-10-12 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks until rain delay, dozer spreading gravel over wetland access area, rock trucks running until rain delay. Ben and Blade rolling out geo for 2 hours | 5 | C050-C069 | Antler Lake | 0 | 44127 |  | 36 | 44127 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting584220201012-13Driver - AZ - After Jan 105.5385 | Corbiere and Sons Contracting584220201012-13Driver - AZ - After Jan 105.5385Inv#068 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 385 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5842 | 20201012-13 | 53510503 | Access | 0 | Labourer - General - After Jan 10 | 60 | 15 | HR |  |  | 60 | 0 | 900 | 117 | 1017 | 2020-10-12 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks until rain delay, dozer spreading gravel over wetland access area, rock trucks running until rain delay. Ben and Blade rolling out geo for 2 hours | 5 | C050-C069 | Antler Lake | 0 | 44127 |  | 36 | 44127 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting584220201012-13Labourer - General - After Jan 1015900 | Corbiere and Sons Contracting584220201012-13Labourer - General - After Jan 1015900Inv#068 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5844 | 20201012-15 | 53510504 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10 | Dynamic | 98.61 | 0 |  |  | 1314.8 | 170.924 | 1485.724 | 2020-10-12 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Leslie on excavator, Gary on dozer and Stacey on rock truck capping road near WC7491.Dwayne on excavator, Tim on dozer, Chris on rock truck cammping road near C-078 - C-079 | 5 | C076-C116 | Cook Lake | 0 | 44127 |  | 36 | 44127 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting584420201012-15Dozer D6 or equal- After Jan 10101314.8 | Corbiere and Sons Contracting584420201012-15Dozer D6 or equal- After Jan 10101314.8Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1314.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5844 | 20201012-15 | 53510504 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 5 | Dynamic | 103.84 | 0 |  |  | 692.25 | 89.9925 | 782.2425 | 2020-10-12 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Leslie on excavator, Gary on dozer and Stacey on rock truck capping road near WC7491.Dwayne on excavator, Tim on dozer, Chris on rock truck cammping road near C-078 - C-079 | 5 | C076-C116 | Cook Lake | 0 | 44127 |  | 36 | 44127 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting584420201012-15Excavator - 30 ton- After Jan 105692.25 | Corbiere and Sons Contracting584420201012-15Excavator - 30 ton- After Jan 105692.25Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 692.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5844 | 20201012-15 | 53510504 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 5 | Dynamic | 110.22 | 0 |  |  | 734.8 | 95.524 | 830.324 | 2020-10-12 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Leslie on excavator, Gary on dozer and Stacey on rock truck capping road near WC7491.Dwayne on excavator, Tim on dozer, Chris on rock truck cammping road near C-078 - C-079 | 5 | C076-C116 | Cook Lake | 0 | 44127 |  | 36 | 44127 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting584420201012-15Excavator - 36 ton- After Jan 105734.8 | Corbiere and Sons Contracting584420201012-15Excavator - 36 ton- After Jan 105734.8Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 734.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5844 | 20201012-15 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2020-10-12 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Leslie on excavator, Gary on dozer and Stacey on rock truck capping road near WC7491.Dwayne on excavator, Tim on dozer, Chris on rock truck cammping road near C-078 - C-079 | 5 | C076-C116 | Cook Lake | 0 | 44127 |  | 36 | 44127 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting584420201012-15Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting584420201012-15Light Truck - Pick up- After Jan 103731.25Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 731.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5844 | 20201012-15 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 10 | Dynamic | 103.54 | 0 |  |  | 1380.5 | 179.465 | 1559.965 | 2020-10-12 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Leslie on excavator, Gary on dozer and Stacey on rock truck capping road near WC7491.Dwayne on excavator, Tim on dozer, Chris on rock truck cammping road near C-078 - C-079 | 5 | C076-C116 | Cook Lake | 0 | 44127 |  | 36 | 44127 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting584420201012-15Rock Truck - 30 Ton- After Jan 10101380.5 | Corbiere and Sons Contracting584420201012-15Rock Truck - 30 Ton- After Jan 10101380.5Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1380.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5844 | 20201012-15 | 53510504 | Access | 0 | Foreman | 95 | 5.5 | HR |  |  | 95 | 0 | 522.5 | 67.925 | 590.425 | 2020-10-12 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Leslie on excavator, Gary on dozer and Stacey on rock truck capping road near WC7491.Dwayne on excavator, Tim on dozer, Chris on rock truck cammping road near C-078 - C-079 | 5 | C076-C116 | Cook Lake | 0 | 44127 |  | 36 | 44127 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting584420201012-15Foreman5.5522.5 | Corbiere and Sons Contracting584420201012-15Foreman5.5522.5Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 522.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5844 | 20201012-15 | 53510504 | Access | 0 | L.O.A. | 210 | 7 | DAY |  |  |  | 0 | 1470 | 191.1 | 1661.1 | 2020-10-12 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Leslie on excavator, Gary on dozer and Stacey on rock truck capping road near WC7491.Dwayne on excavator, Tim on dozer, Chris on rock truck cammping road near C-078 - C-079 | 5 | C076-C116 | Cook Lake | 0 | 44127 |  | 36 | 44127 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting584420201012-15L.O.A.71470 | Corbiere and Sons Contracting584420201012-15L.O.A.71470Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1470 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5844 | 20201012-15 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 22 | HR |  |  | 75 | 0 | 1650 | 214.5 | 1864.5 | 2020-10-12 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Leslie on excavator, Gary on dozer and Stacey on rock truck capping road near WC7491.Dwayne on excavator, Tim on dozer, Chris on rock truck cammping road near C-078 - C-079 | 5 | C076-C116 | Cook Lake | 0 | 44127 |  | 36 | 44127 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting584420201012-15Operator - Principle - After Jan 10221650 | Corbiere and Sons Contracting584420201012-15Operator - Principle - After Jan 10221650Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1650 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5844 | 20201012-15 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 11 | HR |  |  | 70 | 0 | 770 | 100.1 | 870.1 | 2020-10-12 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Leslie on excavator, Gary on dozer and Stacey on rock truck capping road near WC7491.Dwayne on excavator, Tim on dozer, Chris on rock truck cammping road near C-078 - C-079 | 5 | C076-C116 | Cook Lake | 0 | 44127 |  | 36 | 44127 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting584420201012-15Driver - AZ - After Jan 1011770 | Corbiere and Sons Contracting584420201012-15Driver - AZ - After Jan 1011770Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 770 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6088 | 20201012-19 | 53510312 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 6 | Dynamic | 110.22 | 0 |  |  | 881.76 | 114.6288 | 996.3888 | 2020-10-12 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-08 worked on road maintenance in Lachance. | 3 | B161-B181 | Lachance Road | 0 | 44134 |  | 37 | 44134 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting608820201012-19Excavator - 36 ton- After Jan 106881.76 | Corbiere and Sons Contracting608820201012-19Excavator - 36 ton- After Jan 106881.76Inv#070 | [5 empty] | 1 | 881.76 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6088 | 20201012-19 | 53510312 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 6 | HR | 9.16 | 0 |  |  | 73.26 | 9.5238 | 82.7838 | 2020-10-12 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-08 worked on road maintenance in Lachance. | 3 | B161-B181 | Lachance Road | 0 | 44134 |  | 37 | 44134 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting608820201012-19Excavator Thumb - 30 - 50 ton- After Jan 10673.26 | Corbiere and Sons Contracting608820201012-19Excavator Thumb - 30 - 50 ton- After Jan 10673.26Inv#070 | [5 empty] | 1 | 73.26 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6088 | 20201012-19 | 53510312 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-10-12 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-08 worked on road maintenance in Lachance. | 3 | B161-B181 | Lachance Road | 0 | 44134 |  | 37 | 44134 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting608820201012-19Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting608820201012-19Light Truck - Pick up- After Jan 101243.75Inv#070 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6088 | 20201012-19 | 53510312 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 7 | HR |  |  | 75 | 0 | 525 | 68.25 | 593.25 | 2020-10-12 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-08 worked on road maintenance in Lachance. | 3 | B161-B181 | Lachance Road | 0 | 44134 |  | 37 | 44134 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting608820201012-19Operator - Principle - After Jan 107525 | Corbiere and Sons Contracting608820201012-19Operator - Principle - After Jan 107525Inv#070 | [5 empty] | 1 | 525 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5740 | 20201013-12 | 53510502 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 4 | Dynamic | 103.84 | 0 |  |  | 553.8 | 71.994 | 625.794 | 2020-10-13 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Standby due to weather delay for crew members and equipment doing unit rate workExcavator building road into C-066 | 5 | C050-C069 | Antler Lake | 0 | 44122 |  | 52 | 44125 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting574020201013-12Excavator - 30 ton- After Jan 104553.8 | Corbiere and Sons Contracting574020201013-12Excavator - 30 ton- After Jan 104553.8Inv#068 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 553.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5740 | 20201013-12 | 53510502 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 4 | HR | 9.16 | 0 |  |  | 48.84 | 6.3492 | 55.1892 | 2020-10-13 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Standby due to weather delay for crew members and equipment doing unit rate workExcavator building road into C-066 | 5 | C050-C069 | Antler Lake | 0 | 44122 |  | 52 | 44125 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting574020201013-12Excavator Thumb - 30 - 50 ton- After Jan 10448.84 | Corbiere and Sons Contracting574020201013-12Excavator Thumb - 30 - 50 ton- After Jan 10448.84Inv#068 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 48.84 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5740 | 20201013-12 | 53510502 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-10-13 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Standby due to weather delay for crew members and equipment doing unit rate workExcavator building road into C-066 | 5 | C050-C069 | Antler Lake | 0 | 44122 |  | 52 | 44125 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting574020201013-12L.O.A.1210 | Corbiere and Sons Contracting574020201013-12L.O.A.1210Inv#068 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5740 | 20201013-12 | 53510502 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 4 | HR |  |  | 75 | 0 | 300 | 39 | 339 | 2020-10-13 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Standby due to weather delay for crew members and equipment doing unit rate workExcavator building road into C-066 | 5 | C050-C069 | Antler Lake | 0 | 44122 |  | 52 | 44125 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting574020201013-12Operator - Principle - After Jan 104300 | Corbiere and Sons Contracting574020201013-12Operator - Principle - After Jan 104300Inv#068 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5742 | 20201013-13 | 53510502 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 4 | Dynamic | 110.22 | 0 |  |  | 587.84 | 76.4192 | 664.2592 | 2020-10-13 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Standby due to weather delay for crew members and equipment doing T&M workDarrel Innes would've been on hammer at C-079 all day - rained out | 5 | 076-092 | Cook Lake | 0 | 44123 |  | 52 | 44125 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting574220201013-13Excavator - 36 ton- After Jan 104587.84 | Corbiere and Sons Contracting574220201013-13Excavator - 36 ton- After Jan 104587.84Inv#068 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 587.84 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5742 | 20201013-13 | 53510502 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 4 | HR | 47.54 | 0 |  |  | 253.52 | 32.9576 | 286.4776 | 2020-10-13 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Standby due to weather delay for crew members and equipment doing T&M workDarrel Innes would've been on hammer at C-079 all day - rained out | 5 | 076-092 | Cook Lake | 0 | 44123 |  | 52 | 44125 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting574220201013-13Excavator Hammer - 30 - 50 ton- After Jan 104253.52 | Corbiere and Sons Contracting574220201013-13Excavator Hammer - 30 - 50 ton- After Jan 104253.52Inv#068 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 253.52 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5742 | 20201013-13 | 53510502 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-10-13 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Standby due to weather delay for crew members and equipment doing T&M workDarrel Innes would've been on hammer at C-079 all day - rained out | 5 | 076-092 | Cook Lake | 0 | 44123 |  | 52 | 44125 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting574220201013-13L.O.A.1210 | Corbiere and Sons Contracting574220201013-13L.O.A.1210Inv#068 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5742 | 20201013-13 | 53510502 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 4 | HR |  |  | 75 | 0 | 300 | 39 | 339 | 2020-10-13 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Standby due to weather delay for crew members and equipment doing T&M workDarrel Innes would've been on hammer at C-079 all day - rained out | 5 | 076-092 | Cook Lake | 0 | 44123 |  | 52 | 44125 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting574220201013-13Operator - Principle - After Jan 104300 | Corbiere and Sons Contracting574220201013-13Operator - Principle - After Jan 104300Inv#068 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5743 | 20201013-14 | 53510504 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 8.5 | Dynamic | 98.61 | 0 |  |  | 1117.58 | 145.2854 | 1262.8654 | 2020-10-13 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Standby due to weather delay for crew members and equipment doing T&M workExcavators loading rock trucks, dozer spreading gravel | 5 | C093-C116 | Cook Lake | 0 | 44123 |  | 52 | 44125 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting574320201013-14Dozer D6 or equal- After Jan 108.51117.58 | Corbiere and Sons Contracting574320201013-14Dozer D6 or equal- After Jan 108.51117.58Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1117.58 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5743 | 20201013-14 | 53510504 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10.5 | Dynamic | 103.84 | 0 |  |  | 1453.725 | 188.9843 | 1642.7093 | 2020-10-13 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Standby due to weather delay for crew members and equipment doing T&M workExcavators loading rock trucks, dozer spreading gravel | 5 | C093-C116 | Cook Lake | 0 | 44123 |  | 52 | 44125 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting574320201013-14Excavator - 30 ton- After Jan 1010.51453.725 | Corbiere and Sons Contracting574320201013-14Excavator - 30 ton- After Jan 1010.51453.725Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1453.725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5743 | 20201013-14 | 53510504 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 4 | Dynamic | 110.22 | 0 |  |  | 587.84 | 76.4192 | 664.2592 | 2020-10-13 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Standby due to weather delay for crew members and equipment doing T&M workExcavators loading rock trucks, dozer spreading gravel | 5 | C093-C116 | Cook Lake | 0 | 44123 |  | 52 | 44125 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting574320201013-14Excavator - 36 ton- After Jan 104587.84 | Corbiere and Sons Contracting574320201013-14Excavator - 36 ton- After Jan 104587.84Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 587.84 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5743 | 20201013-14 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-10-13 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Standby due to weather delay for crew members and equipment doing T&M workExcavators loading rock trucks, dozer spreading gravel | 5 | C093-C116 | Cook Lake | 0 | 44123 |  | 52 | 44125 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting574320201013-14Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting574320201013-14Light Truck - Pick up- After Jan 102487.5Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5743 | 20201013-14 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 18 | Dynamic | 103.54 | 0 |  |  | 2484.9 | 323.037 | 2807.937 | 2020-10-13 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Standby due to weather delay for crew members and equipment doing T&M workExcavators loading rock trucks, dozer spreading gravel | 5 | C093-C116 | Cook Lake | 0 | 44123 |  | 52 | 44125 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting574320201013-14Rock Truck - 30 Ton- After Jan 10182484.9 | Corbiere and Sons Contracting574320201013-14Rock Truck - 30 Ton- After Jan 10182484.9Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 2484.9 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5743 | 20201013-14 | 53510504 | Access | 0 | Foreman | 95 | 8 | HR |  |  | 95 | 0 | 760 | 98.8 | 858.8 | 2020-10-13 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Standby due to weather delay for crew members and equipment doing T&M workExcavators loading rock trucks, dozer spreading gravel | 5 | C093-C116 | Cook Lake | 0 | 44123 |  | 52 | 44125 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting574320201013-14Foreman8760 | Corbiere and Sons Contracting574320201013-14Foreman8760Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 760 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5743 | 20201013-14 | 53510504 | Access | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2020-10-13 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Standby due to weather delay for crew members and equipment doing T&M workExcavators loading rock trucks, dozer spreading gravel | 5 | C093-C116 | Cook Lake | 0 | 44123 |  | 52 | 44125 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting574320201013-14L.O.A.61260 | Corbiere and Sons Contracting574320201013-14L.O.A.61260Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5743 | 20201013-14 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 25 | HR |  |  | 75 | 0 | 1875 | 243.75 | 2118.75 | 2020-10-13 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Standby due to weather delay for crew members and equipment doing T&M workExcavators loading rock trucks, dozer spreading gravel | 5 | C093-C116 | Cook Lake | 0 | 44123 |  | 52 | 44125 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting574320201013-14Operator - Principle - After Jan 10251875 | Corbiere and Sons Contracting574320201013-14Operator - Principle - After Jan 10251875Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1875 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5743 | 20201013-14 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 20 | HR |  |  | 70 | 0 | 1400 | 182 | 1582 | 2020-10-13 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Standby due to weather delay for crew members and equipment doing T&M workExcavators loading rock trucks, dozer spreading gravel | 5 | C093-C116 | Cook Lake | 0 | 44123 |  | 52 | 44125 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting574320201013-14Driver - AZ - After Jan 10201400 | Corbiere and Sons Contracting574320201013-14Driver - AZ - After Jan 10201400Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1400 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5747 | 20201013-18 | 53510502 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 4 | Dynamic | 98.61 | 0 |  |  | 525.92 | 68.3696 | 594.2896 | 2020-10-13 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Standby due to weather delay for crew members and equipment doing unit rate workEX-008 would have continued building road from C094 EEX-002 would have continued building AN road from C-077 WDZ-005 would have worked from C-077 | 5 | C076-C116 | Cook Lake | 0 | 44123 |  | 52 | 44125 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting574720201013-18Dozer D6 or equal- After Jan 104525.92 | Corbiere and Sons Contracting574720201013-18Dozer D6 or equal- After Jan 104525.92Inv#068 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 525.92 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5747 | 20201013-18 | 53510502 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 8 | Dynamic | 110.22 | 0 |  |  | 1175.68 | 152.8384 | 1328.5184 | 2020-10-13 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Standby due to weather delay for crew members and equipment doing unit rate workEX-008 would have continued building road from C094 EEX-002 would have continued building AN road from C-077 WDZ-005 would have worked from C-077 | 5 | C076-C116 | Cook Lake | 0 | 44123 |  | 52 | 44125 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting574720201013-18Excavator - 36 ton- After Jan 1081175.68 | Corbiere and Sons Contracting574720201013-18Excavator - 36 ton- After Jan 1081175.68Inv#068 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 1175.68 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5747 | 20201013-18 | 53510502 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 4 | HR | 9.16 | 0 |  |  | 48.84 | 6.3492 | 55.1892 | 2020-10-13 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Standby due to weather delay for crew members and equipment doing unit rate workEX-008 would have continued building road from C094 EEX-002 would have continued building AN road from C-077 WDZ-005 would have worked from C-077 | 5 | C076-C116 | Cook Lake | 0 | 44123 |  | 52 | 44125 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting574720201013-18Excavator Thumb - 30 - 50 ton- After Jan 10448.84 | Corbiere and Sons Contracting574720201013-18Excavator Thumb - 30 - 50 ton- After Jan 10448.84Inv#068 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 48.84 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5747 | 20201013-18 | 53510502 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2020-10-13 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Standby due to weather delay for crew members and equipment doing unit rate workEX-008 would have continued building road from C094 EEX-002 would have continued building AN road from C-077 WDZ-005 would have worked from C-077 | 5 | C076-C116 | Cook Lake | 0 | 44123 |  | 52 | 44125 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting574720201013-18L.O.A.3630 | Corbiere and Sons Contracting574720201013-18L.O.A.3630Inv#068 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5747 | 20201013-18 | 53510502 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2020-10-13 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Standby due to weather delay for crew members and equipment doing unit rate workEX-008 would have continued building road from C094 EEX-002 would have continued building AN road from C-077 WDZ-005 would have worked from C-077 | 5 | C076-C116 | Cook Lake | 0 | 44123 |  | 52 | 44125 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting574720201013-18Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting574720201013-18Operator - Principle - After Jan 1012900Inv#068 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5775 | 20201013-22 | 53510312 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10 | Dynamic | 103.84 | 0 |  |  | 1384.5 | 179.985 | 1564.485 | 2020-10-13 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-08 worked on B-168 - B-181 trying to remove water issues building up and over the access road in Lachance East. | 3 | B168-B181 | Lachance Road East | 0 | 44126 |  | 50 | 44126 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting577520201013-22Excavator - 30 ton- After Jan 10101384.5 | Corbiere and Sons Contracting577520201013-22Excavator - 30 ton- After Jan 10101384.5Inv#068 | [5 empty] | 1 | 1384.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5775 | 20201013-22 | 53510312 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 9.16 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2020-10-13 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-08 worked on B-168 - B-181 trying to remove water issues building up and over the access road in Lachance East. | 3 | B168-B181 | Lachance Road East | 0 | 44126 |  | 50 | 44126 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting577520201013-22Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting577520201013-22Excavator Thumb - 30 - 50 ton- After Jan 1010122.1Inv#068 | [5 empty] | 1 | 122.1 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5775 | 20201013-22 | 53510312 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-10-13 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-08 worked on B-168 - B-181 trying to remove water issues building up and over the access road in Lachance East. | 3 | B168-B181 | Lachance Road East | 0 | 44126 |  | 50 | 44126 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting577520201013-22Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting577520201013-22Light Truck - Pick up- After Jan 101243.75Inv#068 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5775 | 20201013-22 | 53510312 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2020-10-13 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-08 worked on B-168 - B-181 trying to remove water issues building up and over the access road in Lachance East. | 3 | B168-B181 | Lachance Road East | 0 | 44126 |  | 50 | 44126 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting577520201013-22Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting577520201013-22Operator - Principle - After Jan 1011825Inv#068 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5776 | 20201013-23 | 53510312 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 8 | Dynamic | 110.22 | 0 |  |  | 1175.68 | 152.8384 | 1328.5184 | 2020-10-13 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-02 worked on 6790.01 WC and removing built up water on Blair Lake Rd access | 3 | B182-B186 | Blair Lake Road | 0 | 44126 |  | 50 | 44126 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting577620201013-23Excavator - 36 ton- After Jan 1081175.68 | Corbiere and Sons Contracting577620201013-23Excavator - 36 ton- After Jan 1081175.68Inv#068 | [5 empty] | 1 | 1175.68 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5776 | 20201013-23 | 53510312 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 8 | HR | 9.16 | 0 |  |  | 97.68 | 12.6984 | 110.3784 | 2020-10-13 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-02 worked on 6790.01 WC and removing built up water on Blair Lake Rd access | 3 | B182-B186 | Blair Lake Road | 0 | 44126 |  | 50 | 44126 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting577620201013-23Excavator Thumb - 30 - 50 ton- After Jan 10897.68 | Corbiere and Sons Contracting577620201013-23Excavator Thumb - 30 - 50 ton- After Jan 10897.68Inv#068 | [5 empty] | 1 | 97.68 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5776 | 20201013-23 | 53510312 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-10-13 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-02 worked on 6790.01 WC and removing built up water on Blair Lake Rd access | 3 | B182-B186 | Blair Lake Road | 0 | 44126 |  | 50 | 44126 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting577620201013-23Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting577620201013-23Light Truck - Pick up- After Jan 101243.75Inv#068 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5776 | 20201013-23 | 53510312 | Access | 0 | Foreman | 95 | 2 | HR |  |  | 95 | 0 | 190 | 24.7 | 214.7 | 2020-10-13 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-02 worked on 6790.01 WC and removing built up water on Blair Lake Rd access | 3 | B182-B186 | Blair Lake Road | 0 | 44126 |  | 50 | 44126 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting577620201013-23Foreman2190 | Corbiere and Sons Contracting577620201013-23Foreman2190Inv#068 | [5 empty] | 1 | 190 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5776 | 20201013-23 | 53510312 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 9 | HR |  |  | 75 | 0 | 675 | 87.75 | 762.75 | 2020-10-13 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-02 worked on 6790.01 WC and removing built up water on Blair Lake Rd access | 3 | B182-B186 | Blair Lake Road | 0 | 44126 |  | 50 | 44126 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting577620201013-23Operator - Principle - After Jan 109675 | Corbiere and Sons Contracting577620201013-23Operator - Principle - After Jan 109675Inv#068 | [5 empty] | 1 | 675 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5729 | 20201013-8 | 53510504 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 4 | Dynamic | 98.61 | 0 |  |  | 525.92 | 68.3696 | 594.2896 | 2020-10-13 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Standby due to weather delay for crew members and equipment doing T&M workExcavator loading rock trucks, dozer spreading gravel beyond WC7204 | 5 | C050-C069 | Antler Lake | 0 | 44122 |  | 52 | 44125 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting572920201013-8Dozer D6 or equal- After Jan 104525.92 | Corbiere and Sons Contracting572920201013-8Dozer D6 or equal- After Jan 104525.92Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 525.92 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5729 | 20201013-8 | 53510504 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 4 | Dynamic | 103.84 | 0 |  |  | 553.8 | 71.994 | 625.794 | 2020-10-13 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Standby due to weather delay for crew members and equipment doing T&M workExcavator loading rock trucks, dozer spreading gravel beyond WC7204 | 5 | C050-C069 | Antler Lake | 0 | 44122 |  | 52 | 44125 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting572920201013-8Excavator - 30 ton- After Jan 104553.8 | Corbiere and Sons Contracting572920201013-8Excavator - 30 ton- After Jan 104553.8Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 553.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5729 | 20201013-8 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 8 | Dynamic | 103.54 | 0 |  |  | 1104.4 | 143.572 | 1247.972 | 2020-10-13 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Standby due to weather delay for crew members and equipment doing T&M workExcavator loading rock trucks, dozer spreading gravel beyond WC7204 | 5 | C050-C069 | Antler Lake | 0 | 44122 |  | 52 | 44125 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting572920201013-8Rock Truck - 30 Ton- After Jan 1081104.4 | Corbiere and Sons Contracting572920201013-8Rock Truck - 30 Ton- After Jan 1081104.4Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1104.4 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5729 | 20201013-8 | 53510504 | Access | 0 | Foreman | 95 | 4 | HR |  |  | 95 | 0 | 380 | 49.4 | 429.4 | 2020-10-13 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Standby due to weather delay for crew members and equipment doing T&M workExcavator loading rock trucks, dozer spreading gravel beyond WC7204 | 5 | C050-C069 | Antler Lake | 0 | 44122 |  | 52 | 44125 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting572920201013-8Foreman4380 | Corbiere and Sons Contracting572920201013-8Foreman4380Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5729 | 20201013-8 | 53510504 | Access | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2020-10-13 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Standby due to weather delay for crew members and equipment doing T&M workExcavator loading rock trucks, dozer spreading gravel beyond WC7204 | 5 | C050-C069 | Antler Lake | 0 | 44122 |  | 52 | 44125 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting572920201013-8L.O.A.51050 | Corbiere and Sons Contracting572920201013-8L.O.A.51050Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5729 | 20201013-8 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 8 | HR |  |  | 75 | 0 | 600 | 78 | 678 | 2020-10-13 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Standby due to weather delay for crew members and equipment doing T&M workExcavator loading rock trucks, dozer spreading gravel beyond WC7204 | 5 | C050-C069 | Antler Lake | 0 | 44122 |  | 52 | 44125 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting572920201013-8Operator - Principle - After Jan 108600 | Corbiere and Sons Contracting572920201013-8Operator - Principle - After Jan 108600Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5729 | 20201013-8 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 8 | HR |  |  | 70 | 0 | 560 | 72.8 | 632.8 | 2020-10-13 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Standby due to weather delay for crew members and equipment doing T&M workExcavator loading rock trucks, dozer spreading gravel beyond WC7204 | 5 | C050-C069 | Antler Lake | 0 | 44122 |  | 52 | 44125 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting572920201013-8Driver - AZ - After Jan 108560 | Corbiere and Sons Contracting572920201013-8Driver - AZ - After Jan 108560Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 560 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5730 | 20201013-9 | 53510502 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 4 | Dynamic | 110.22 | 0 |  |  | 587.84 | 76.4192 | 664.2592 | 2020-10-13 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Standby due to weather delay for crew members and equipment doing T&M workOn Hammer just past steep hill at C-062 | 5 | C050-C069 | Antler Lake | 0 | 44122 |  | 52 | 44125 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting573020201013-9Excavator - 36 ton- After Jan 104587.84 | Corbiere and Sons Contracting573020201013-9Excavator - 36 ton- After Jan 104587.84Inv#068 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 587.84 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5730 | 20201013-9 | 53510502 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 4 | HR | 47.54 | 0 |  |  | 253.52 | 32.9576 | 286.4776 | 2020-10-13 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Standby due to weather delay for crew members and equipment doing T&M workOn Hammer just past steep hill at C-062 | 5 | C050-C069 | Antler Lake | 0 | 44122 |  | 52 | 44125 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting573020201013-9Excavator Hammer - 30 - 50 ton- After Jan 104253.52 | Corbiere and Sons Contracting573020201013-9Excavator Hammer - 30 - 50 ton- After Jan 104253.52Inv#068 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 253.52 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5730 | 20201013-9 | 53510502 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-10-13 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Standby due to weather delay for crew members and equipment doing T&M workOn Hammer just past steep hill at C-062 | 5 | C050-C069 | Antler Lake | 0 | 44122 |  | 52 | 44125 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting573020201013-9L.O.A.1210 | Corbiere and Sons Contracting573020201013-9L.O.A.1210Inv#068 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5730 | 20201013-9 | 53510502 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 4 | HR |  |  | 75 | 0 | 300 | 39 | 339 | 2020-10-13 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Standby due to weather delay for crew members and equipment doing T&M workOn Hammer just past steep hill at C-062 | 5 | C050-C069 | Antler Lake | 0 | 44122 |  | 52 | 44125 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting573020201013-9Operator - Principle - After Jan 104300 | Corbiere and Sons Contracting573020201013-9Operator - Principle - After Jan 104300Inv#068 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5758 | 20201014-10 | 53510504 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 8 | Dynamic | 98.61 | 0 |  |  | 1051.84 | 136.7392 | 1188.5792 | 2020-10-14 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks, dozer spreading gravel between unmarked culverts on KM1 and KM2. | 5 | C076-C116 | Cook Lake | 0 | 44123 |  | 52 | 44126 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting575820201014-10Dozer D6 or equal- After Jan 1081051.84 | Corbiere and Sons Contracting575820201014-10Dozer D6 or equal- After Jan 1081051.84Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1051.84 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5758 | 20201014-10 | 53510504 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 8 | Dynamic | 103.84 | 0 |  |  | 1107.6 | 143.988 | 1251.588 | 2020-10-14 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks, dozer spreading gravel between unmarked culverts on KM1 and KM2. | 5 | C076-C116 | Cook Lake | 0 | 44123 |  | 52 | 44126 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting575820201014-10Excavator - 30 ton- After Jan 1081107.6 | Corbiere and Sons Contracting575820201014-10Excavator - 30 ton- After Jan 1081107.6Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1107.6 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5758 | 20201014-10 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-10-14 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks, dozer spreading gravel between unmarked culverts on KM1 and KM2. | 5 | C076-C116 | Cook Lake | 0 | 44123 |  | 52 | 44126 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting575820201014-10Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting575820201014-10Light Truck - Pick up- After Jan 102487.5Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5758 | 20201014-10 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 16 | Dynamic | 103.54 | 0 |  |  | 2208.8 | 287.144 | 2495.944 | 2020-10-14 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks, dozer spreading gravel between unmarked culverts on KM1 and KM2. | 5 | C076-C116 | Cook Lake | 0 | 44123 |  | 52 | 44126 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting575820201014-10Rock Truck - 30 Ton- After Jan 10162208.8 | Corbiere and Sons Contracting575820201014-10Rock Truck - 30 Ton- After Jan 10162208.8Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 2208.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5758 | 20201014-10 | 53510504 | Access | 0 | Foreman | 95 | 6 | HR |  |  | 95 | 0 | 570 | 74.1 | 644.1 | 2020-10-14 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks, dozer spreading gravel between unmarked culverts on KM1 and KM2. | 5 | C076-C116 | Cook Lake | 0 | 44123 |  | 52 | 44126 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting575820201014-10Foreman6570 | Corbiere and Sons Contracting575820201014-10Foreman6570Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 570 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5758 | 20201014-10 | 53510504 | Access | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2020-10-14 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks, dozer spreading gravel between unmarked culverts on KM1 and KM2. | 5 | C076-C116 | Cook Lake | 0 | 44123 |  | 52 | 44126 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting575820201014-10L.O.A.51050 | Corbiere and Sons Contracting575820201014-10L.O.A.51050Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5758 | 20201014-10 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 36 | HR |  |  | 75 | 0 | 2700 | 351 | 3051 | 2020-10-14 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks, dozer spreading gravel between unmarked culverts on KM1 and KM2. | 5 | C076-C116 | Cook Lake | 0 | 44123 |  | 52 | 44126 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting575820201014-10Operator - Principle - After Jan 10362700 | Corbiere and Sons Contracting575820201014-10Operator - Principle - After Jan 10362700Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 2700 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5765 | 20201014-16 | 53510312 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 9 | Dynamic | 98.61 | 0 |  |  | 1183.32 | 153.8316 | 1337.1516 | 2020-10-14 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | DZ-01 and RT-01 hauled, spread and fixed punchouts at private driveway residence on Matta's Rd B-092 - B-099 access road. | 3 | B088-B099 | Maata's Road | 0 | 44123 |  | 50 | 44126 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting576520201014-16Dozer D6 or equal- After Jan 1091183.32 | Corbiere and Sons Contracting576520201014-16Dozer D6 or equal- After Jan 1091183.32Inv#068 | [5 empty] | 1 | 1183.32 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5765 | 20201014-16 | 53510312 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 10 | Dynamic | 41.4 | 0 |  |  | 552 | 71.76 | 623.76 | 2020-10-14 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | DZ-01 and RT-01 hauled, spread and fixed punchouts at private driveway residence on Matta's Rd B-092 - B-099 access road. | 3 | B088-B099 | Maata's Road | 0 | 44123 |  | 50 | 44126 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting576520201014-16Dump - Triaxle- After Jan 1010552 | Corbiere and Sons Contracting576520201014-16Dump - Triaxle- After Jan 1010552Inv#068 | [5 empty] | 1 | 552 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5765 | 20201014-16 | 53510312 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-10-14 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | DZ-01 and RT-01 hauled, spread and fixed punchouts at private driveway residence on Matta's Rd B-092 - B-099 access road. | 3 | B088-B099 | Maata's Road | 0 | 44123 |  | 50 | 44126 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting576520201014-16Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting576520201014-16Light Truck - Pick up- After Jan 101243.75Inv#068 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5765 | 20201014-16 | 53510312 | Access | 0 | Foreman | 95 | 6 | HR |  |  | 95 | 0 | 570 | 74.1 | 644.1 | 2020-10-14 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | DZ-01 and RT-01 hauled, spread and fixed punchouts at private driveway residence on Matta's Rd B-092 - B-099 access road. | 3 | B088-B099 | Maata's Road | 0 | 44123 |  | 50 | 44126 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting576520201014-16Foreman6570 | Corbiere and Sons Contracting576520201014-16Foreman6570Inv#068 | [5 empty] | 1 | 570 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5765 | 20201014-16 | 53510312 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 10 | HR |  |  | 75 | 0 | 750 | 97.5 | 847.5 | 2020-10-14 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | DZ-01 and RT-01 hauled, spread and fixed punchouts at private driveway residence on Matta's Rd B-092 - B-099 access road. | 3 | B088-B099 | Maata's Road | 0 | 44123 |  | 50 | 44126 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting576520201014-16Operator - Principle - After Jan 1010750 | Corbiere and Sons Contracting576520201014-16Operator - Principle - After Jan 1010750Inv#068 | [5 empty] | 1 | 750 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5765 | 20201014-16 | 53510312 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 10 | HR |  |  | 70 | 0 | 700 | 91 | 791 | 2020-10-14 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | DZ-01 and RT-01 hauled, spread and fixed punchouts at private driveway residence on Matta's Rd B-092 - B-099 access road. | 3 | B088-B099 | Maata's Road | 0 | 44123 |  | 50 | 44126 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting576520201014-16Driver - AZ - After Jan 1010700 | Corbiere and Sons Contracting576520201014-16Driver - AZ - After Jan 1010700Inv#068 | [5 empty] | 1 | 700 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5766 | 20201014-17 | 53510312 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 9 | Dynamic | 98.61 | 0 |  |  | 1183.32 | 153.8316 | 1337.1516 | 2020-10-14 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | DZ-05 trimmed road and fixed hill in Kama Cliffs | 3 | B150-B158 | Kama Cliffs | 0 | 44123 |  | 50 | 44126 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting576620201014-17Dozer D6 or equal- After Jan 1091183.32 | Corbiere and Sons Contracting576620201014-17Dozer D6 or equal- After Jan 1091183.32Inv#068 | [5 empty] | 1 | 1183.32 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5766 | 20201014-17 | 53510312 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-10-14 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | DZ-05 trimmed road and fixed hill in Kama Cliffs | 3 | B150-B158 | Kama Cliffs | 0 | 44123 |  | 50 | 44126 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting576620201014-17Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting576620201014-17Light Truck - Pick up- After Jan 101243.75Inv#068 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5766 | 20201014-17 | 53510312 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 10 | HR |  |  | 75 | 0 | 750 | 97.5 | 847.5 | 2020-10-14 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | DZ-05 trimmed road and fixed hill in Kama Cliffs | 3 | B150-B158 | Kama Cliffs | 0 | 44123 |  | 50 | 44126 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting576620201014-17Operator - Principle - After Jan 1010750 | Corbiere and Sons Contracting576620201014-17Operator - Principle - After Jan 1010750Inv#068 | [5 empty] | 1 | 750 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5767 | 20201014-18 | 53510312 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2020-10-14 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-08 ditched water and patched road where possible in Lachance East | 3 | B168-B181 | Lachnace Road East | 0 | 44123 |  | 50 | 44126 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting576720201014-18Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting576720201014-18Excavator - 30 ton- After Jan 10111522.95Inv#068 | [5 empty] | 1 | 1522.95 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5767 | 20201014-18 | 53510312 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2020-10-14 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-08 ditched water and patched road where possible in Lachance East | 3 | B168-B181 | Lachnace Road East | 0 | 44123 |  | 50 | 44126 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting576720201014-18Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting576720201014-18Excavator Thumb - 30 - 50 ton- After Jan 1011134.31Inv#068 | [5 empty] | 1 | 134.31 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5767 | 20201014-18 | 53510312 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-10-14 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-08 ditched water and patched road where possible in Lachance East | 3 | B168-B181 | Lachnace Road East | 0 | 44123 |  | 50 | 44126 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting576720201014-18Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting576720201014-18Light Truck - Pick up- After Jan 101243.75Inv#068 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5767 | 20201014-18 | 53510312 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2020-10-14 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-08 ditched water and patched road where possible in Lachance East | 3 | B168-B181 | Lachnace Road East | 0 | 44123 |  | 50 | 44126 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting576720201014-18Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting576720201014-18Operator - Principle - After Jan 1012900Inv#068 | [5 empty] | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5793 | 20201015-10 | 53510212 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 5 | Dynamic | 98.61 | 0 |  |  | 657.4 | 85.462 | 742.862 | 2020-10-15 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | DZ-05 back bladed Landfill road and got rid of ruts and got water off the road. | 2 | B065-B077 | Red Rock | 0 | 44125 |  | 50 | 44126 | [5 empty] | Wes Seminowich | 02 | Corbiere and Sons Contracting579320201015-10Dozer D6 or equal- After Jan 105657.4 | Corbiere and Sons Contracting579320201015-10Dozer D6 or equal- After Jan 105657.4Inv#068 | [5 empty] | 1 | 657.4 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5793 | 20201015-10 | 53510212 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 75 | 0 | 450 | 58.5 | 508.5 | 2020-10-15 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | DZ-05 back bladed Landfill road and got rid of ruts and got water off the road. | 2 | B065-B077 | Red Rock | 0 | 44125 |  | 50 | 44126 | [5 empty] | Wes Seminowich | 02 | Corbiere and Sons Contracting579320201015-10Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting579320201015-10Operator - Principle - After Jan 106450Inv#068 | [5 empty] | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5792 | 20201015-9 | 53510312 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 5 | Dynamic | 98.61 | 0 |  |  | 657.4 | 85.462 | 742.862 | 2020-10-15 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | DZ-01 back bladed private driveway and ditched water to culvert | 3 | B092-B099 | Maata's Road West | 0 | 44125 |  | 50 | 44126 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting579220201015-9Dozer D6 or equal- After Jan 105657.4 | Corbiere and Sons Contracting579220201015-9Dozer D6 or equal- After Jan 105657.4Inv#068 | [5 empty] | 1 | 657.4 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5792 | 20201015-9 | 53510312 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5 | HR |  |  | 75 | 0 | 375 | 48.75 | 423.75 | 2020-10-15 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | DZ-01 back bladed private driveway and ditched water to culvert | 3 | B092-B099 | Maata's Road West | 0 | 44125 |  | 50 | 44126 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting579220201015-9Operator - Principle - After Jan 105375 | Corbiere and Sons Contracting579220201015-9Operator - Principle - After Jan 105375Inv#068 | [5 empty] | 1 | 375 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5808 | 20201016-10 | 53510502 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2020-10-16 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer all day from C-076 - C-078 | 5 | C076-C092 | Cook Lake | 0 | 44125 |  | 52 | 44126 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting580820201016-10Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting580820201016-10Excavator - 36 ton- After Jan 10111616.56Inv#068 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 1616.56 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5808 | 20201016-10 | 53510502 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 11 | HR | 47.54 | 0 |  |  | 697.18 | 90.6334 | 787.8134 | 2020-10-16 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer all day from C-076 - C-078 | 5 | C076-C092 | Cook Lake | 0 | 44125 |  | 52 | 44126 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting580820201016-10Excavator Hammer - 30 - 50 ton- After Jan 1011697.18 | Corbiere and Sons Contracting580820201016-10Excavator Hammer - 30 - 50 ton- After Jan 1011697.18Inv#068 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 697.18 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5808 | 20201016-10 | 53510502 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-10-16 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer all day from C-076 - C-078 | 5 | C076-C092 | Cook Lake | 0 | 44125 |  | 52 | 44126 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting580820201016-10Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting580820201016-10Light Truck - Pick up- After Jan 101243.75Inv#068 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5808 | 20201016-10 | 53510502 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-10-16 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer all day from C-076 - C-078 | 5 | C076-C092 | Cook Lake | 0 | 44125 |  | 52 | 44126 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting580820201016-10L.O.A.1210 | Corbiere and Sons Contracting580820201016-10L.O.A.1210Inv#068 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5808 | 20201016-10 | 53510502 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2020-10-16 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer all day from C-076 - C-078 | 5 | C076-C092 | Cook Lake | 0 | 44125 |  | 52 | 44126 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting580820201016-10Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting580820201016-10Operator - Principle - After Jan 1012900Inv#068 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5817 | 20201016-18 | 53510312 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2020-10-16 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | DZ-04 worked at Kama Cliffs doing road maintenance | 3 | B159-B160 | Kama Cliffs | 0 | 44125 |  | 50 | 44126 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting581720201016-18Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting581720201016-18Dozer D6 or equal- After Jan 10111446.28Inv#068 | [5 empty] | 1 | 1446.28 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5817 | 20201016-18 | 53510312 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-10-16 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | DZ-04 worked at Kama Cliffs doing road maintenance | 3 | B159-B160 | Kama Cliffs | 0 | 44125 |  | 50 | 44126 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting581720201016-18Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting581720201016-18Light Truck - Pick up- After Jan 101243.75Inv#068 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5817 | 20201016-18 | 53510312 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2020-10-16 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | DZ-04 worked at Kama Cliffs doing road maintenance | 3 | B159-B160 | Kama Cliffs | 0 | 44125 |  | 50 | 44126 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting581720201016-18Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting581720201016-18Operator - Principle - After Jan 1012900Inv#068 | [5 empty] | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5818 | 20201016-19 | 53510312 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10 | Dynamic | 103.84 | 0 |  |  | 1384.5 | 179.985 | 1564.485 | 2020-10-16 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-08 ditched water and fixed road Lachance East | 3 | B168-B181 | Lachance Road East | 0 | 44125 |  | 50 | 44126 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting581820201016-19Excavator - 30 ton- After Jan 10101384.5 | Corbiere and Sons Contracting581820201016-19Excavator - 30 ton- After Jan 10101384.5Inv#068 | [5 empty] | 1 | 1384.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5818 | 20201016-19 | 53510312 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 9.16 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2020-10-16 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-08 ditched water and fixed road Lachance East | 3 | B168-B181 | Lachance Road East | 0 | 44125 |  | 50 | 44126 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting581820201016-19Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting581820201016-19Excavator Thumb - 30 - 50 ton- After Jan 1010122.1Inv#068 | [5 empty] | 1 | 122.1 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5818 | 20201016-19 | 53510312 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-10-16 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-08 ditched water and fixed road Lachance East | 3 | B168-B181 | Lachance Road East | 0 | 44125 |  | 50 | 44126 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting581820201016-19Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting581820201016-19Light Truck - Pick up- After Jan 101243.75Inv#068 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5818 | 20201016-19 | 53510312 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2020-10-16 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-08 ditched water and fixed road Lachance East | 3 | B168-B181 | Lachance Road East | 0 | 44125 |  | 50 | 44126 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting581820201016-19Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting581820201016-19Operator - Principle - After Jan 1011825Inv#068 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5806 | 20201016-8 | 53510502 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 21 | Dynamic | 110.22 | 0 |  |  | 3086.16 | 401.2008 | 3487.3608 | 2020-10-16 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer and excavator on Antler Lake Rd hammering road and widening road all day from C-063. | 5 | C050-C069 | Antler Lake | 0 | 44125 |  | 52 | 44126 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting580620201016-8Excavator - 36 ton- After Jan 10213086.16 | Corbiere and Sons Contracting580620201016-8Excavator - 36 ton- After Jan 10213086.16Inv#068 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 3086.16 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5806 | 20201016-8 | 53510502 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 10.5 | HR | 47.54 | 0 |  |  | 665.49 | 86.5137 | 752.0037 | 2020-10-16 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer and excavator on Antler Lake Rd hammering road and widening road all day from C-063. | 5 | C050-C069 | Antler Lake | 0 | 44125 |  | 52 | 44126 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting580620201016-8Excavator Hammer - 30 - 50 ton- After Jan 1010.5665.49 | Corbiere and Sons Contracting580620201016-8Excavator Hammer - 30 - 50 ton- After Jan 1010.5665.49Inv#068 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 665.49 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5806 | 20201016-8 | 53510502 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-10-16 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer and excavator on Antler Lake Rd hammering road and widening road all day from C-063. | 5 | C050-C069 | Antler Lake | 0 | 44125 |  | 52 | 44126 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting580620201016-8Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting580620201016-8Light Truck - Pick up- After Jan 101243.75Inv#068 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5806 | 20201016-8 | 53510502 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-10-16 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer and excavator on Antler Lake Rd hammering road and widening road all day from C-063. | 5 | C050-C069 | Antler Lake | 0 | 44125 |  | 52 | 44126 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting580620201016-8L.O.A.2420 | Corbiere and Sons Contracting580620201016-8L.O.A.2420Inv#068 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5806 | 20201016-8 | 53510502 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 23 | HR |  |  | 75 | 0 | 1725 | 224.25 | 1949.25 | 2020-10-16 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammer and excavator on Antler Lake Rd hammering road and widening road all day from C-063. | 5 | C050-C069 | Antler Lake | 0 | 44125 |  | 52 | 44126 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting580620201016-8Operator - Principle - After Jan 10231725 | Corbiere and Sons Contracting580620201016-8Operator - Principle - After Jan 10231725Inv#068 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 1725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5807 | 20201016-9 | 53510512 | Access | 0 | Loader JD 524 to 624 or equal | 99 | 11 | HR | 74.25 | 0 |  |  | 1089 | 141.57 | 1230.57 | 2020-10-16 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Loader, Dozer and (2) Rock Trucks doing road maintenance all day on KM12nd dozer doing maintenance from C-090 - C093 | 5 | C076-C116 | Cook Lake | 0 | 44125 |  | 52 | 44126 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting580720201016-9Loader JD 524 to 624 or equal111089 | Corbiere and Sons Contracting580720201016-9Loader JD 524 to 624 or equal111089Inv#068 | [5 empty] | 1 | 1089 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5807 | 20201016-9 | 53510512 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 22 | Dynamic | 98.61 | 0 |  |  | 2892.56 | 376.0328 | 3268.5928 | 2020-10-16 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Loader, Dozer and (2) Rock Trucks doing road maintenance all day on KM12nd dozer doing maintenance from C-090 - C093 | 5 | C076-C116 | Cook Lake | 0 | 44125 |  | 52 | 44126 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting580720201016-9Dozer D6 or equal- After Jan 10222892.56 | Corbiere and Sons Contracting580720201016-9Dozer D6 or equal- After Jan 10222892.56Inv#068 | [5 empty] | 1 | 2892.56 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5807 | 20201016-9 | 53510512 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2020-10-16 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Loader, Dozer and (2) Rock Trucks doing road maintenance all day on KM12nd dozer doing maintenance from C-090 - C093 | 5 | C076-C116 | Cook Lake | 0 | 44125 |  | 52 | 44126 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting580720201016-9Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting580720201016-9Light Truck - Pick up- After Jan 103731.25Inv#068 | [5 empty] | 1 | 731.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5807 | 20201016-9 | 53510512 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 22 | Dynamic | 103.54 | 0 |  |  | 3037.1 | 394.823 | 3431.923 | 2020-10-16 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Loader, Dozer and (2) Rock Trucks doing road maintenance all day on KM12nd dozer doing maintenance from C-090 - C093 | 5 | C076-C116 | Cook Lake | 0 | 44125 |  | 52 | 44126 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting580720201016-9Rock Truck - 30 Ton- After Jan 10223037.1 | Corbiere and Sons Contracting580720201016-9Rock Truck - 30 Ton- After Jan 10223037.1Inv#068 | [5 empty] | 1 | 3037.1 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5807 | 20201016-9 | 53510512 | Access | 0 | Foreman | 95 | 6 | HR |  |  | 95 | 0 | 570 | 74.1 | 644.1 | 2020-10-16 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Loader, Dozer and (2) Rock Trucks doing road maintenance all day on KM12nd dozer doing maintenance from C-090 - C093 | 5 | C076-C116 | Cook Lake | 0 | 44125 |  | 52 | 44126 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting580720201016-9Foreman6570 | Corbiere and Sons Contracting580720201016-9Foreman6570Inv#068 | [5 empty] | 1 | 570 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5807 | 20201016-9 | 53510512 | Access | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2020-10-16 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Loader, Dozer and (2) Rock Trucks doing road maintenance all day on KM12nd dozer doing maintenance from C-090 - C093 | 5 | C076-C116 | Cook Lake | 0 | 44125 |  | 52 | 44126 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting580720201016-9L.O.A.61260 | Corbiere and Sons Contracting580720201016-9L.O.A.61260Inv#068 | [5 empty] | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5807 | 20201016-9 | 53510512 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 36 | HR |  |  | 75 | 0 | 2700 | 351 | 3051 | 2020-10-16 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Loader, Dozer and (2) Rock Trucks doing road maintenance all day on KM12nd dozer doing maintenance from C-090 - C093 | 5 | C076-C116 | Cook Lake | 0 | 44125 |  | 52 | 44126 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting580720201016-9Operator - Principle - After Jan 10362700 | Corbiere and Sons Contracting580720201016-9Operator - Principle - After Jan 10362700Inv#068 | [5 empty] | 1 | 2700 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5807 | 20201016-9 | 53510512 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 24 | HR |  |  | 70 | 0 | 1680 | 218.4 | 1898.4 | 2020-10-16 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Loader, Dozer and (2) Rock Trucks doing road maintenance all day on KM12nd dozer doing maintenance from C-090 - C093 | 5 | C076-C116 | Cook Lake | 0 | 44125 |  | 52 | 44126 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting580720201016-9Driver - AZ - After Jan 10241680 | Corbiere and Sons Contracting580720201016-9Driver - AZ - After Jan 10241680Inv#068 | [5 empty] | 1 | 1680 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5856 | 20201017-10 | 53510504 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 2 | Dynamic | 103.84 | 0 |  |  | 276.9 | 35.997 | 312.897 | 2020-10-17 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hauled gravel for backfill, rolled out 40m of geo | 5 | C050-C069 | Antler Lake | 0 | 44126 |  | 52 | 44127 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting585620201017-10Excavator - 30 ton- After Jan 102276.9 | Corbiere and Sons Contracting585620201017-10Excavator - 30 ton- After Jan 102276.9Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 276.9 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5856 | 20201017-10 | 53510504 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 5 | Dynamic | 110.22 | 0 |  |  | 734.8 | 95.524 | 830.324 | 2020-10-17 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hauled gravel for backfill, rolled out 40m of geo | 5 | C050-C069 | Antler Lake | 0 | 44126 |  | 52 | 44127 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting585620201017-10Excavator - 36 ton- After Jan 105734.8 | Corbiere and Sons Contracting585620201017-10Excavator - 36 ton- After Jan 105734.8Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 734.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5856 | 20201017-10 | 53510504 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 5 | HR | 9.16 | 0 |  |  | 61.05 | 7.9365 | 68.9865 | 2020-10-17 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hauled gravel for backfill, rolled out 40m of geo | 5 | C050-C069 | Antler Lake | 0 | 44126 |  | 52 | 44127 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting585620201017-10Excavator Thumb - 30 - 50 ton- After Jan 10561.05 | Corbiere and Sons Contracting585620201017-10Excavator Thumb - 30 - 50 ton- After Jan 10561.05Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 61.05 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5856 | 20201017-10 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-10-17 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hauled gravel for backfill, rolled out 40m of geo | 5 | C050-C069 | Antler Lake | 0 | 44126 |  | 52 | 44127 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting585620201017-10Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting585620201017-10Light Truck - Pick up- After Jan 101243.75Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5856 | 20201017-10 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 5 | Dynamic | 103.54 | 0 |  |  | 690.25 | 89.7325 | 779.9825 | 2020-10-17 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hauled gravel for backfill, rolled out 40m of geo | 5 | C050-C069 | Antler Lake | 0 | 44126 |  | 52 | 44127 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting585620201017-10Rock Truck - 30 Ton- After Jan 105690.25 | Corbiere and Sons Contracting585620201017-10Rock Truck - 30 Ton- After Jan 105690.25Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 690.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5856 | 20201017-10 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 7 | HR |  |  | 75 | 0 | 525 | 68.25 | 593.25 | 2020-10-17 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hauled gravel for backfill, rolled out 40m of geo | 5 | C050-C069 | Antler Lake | 0 | 44126 |  | 52 | 44127 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting585620201017-10Operator - Principle - After Jan 107525 | Corbiere and Sons Contracting585620201017-10Operator - Principle - After Jan 107525Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 525 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5856 | 20201017-10 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 5 | HR |  |  | 70 | 0 | 350 | 45.5 | 395.5 | 2020-10-17 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hauled gravel for backfill, rolled out 40m of geo | 5 | C050-C069 | Antler Lake | 0 | 44126 |  | 52 | 44127 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting585620201017-10Driver - AZ - After Jan 105350 | Corbiere and Sons Contracting585620201017-10Driver - AZ - After Jan 105350Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 350 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5856 | 20201017-10 | 53510504 | Access | 0 | Labourer - General - After Jan 10 | 60 | 2 | HR |  |  | 60 | 0 | 120 | 15.6 | 135.6 | 2020-10-17 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hauled gravel for backfill, rolled out 40m of geo | 5 | C050-C069 | Antler Lake | 0 | 44126 |  | 52 | 44127 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting585620201017-10Labourer - General - After Jan 102120 | Corbiere and Sons Contracting585620201017-10Labourer - General - After Jan 102120Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 120 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5861 | 20201017-15 | 53510504 | Access | 0 | Loader JD 524 to 624 or equal | 99 | 10.5 | HR | 74.25 | 0 |  |  | 1039.5 | 135.135 | 1174.635 | 2020-10-17 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Loader loading rock trucks, dozer spreading gravel | 5 | C076-C116 | Cook Lake | 0 | 44126 |  | 52 | 44127 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting586120201017-15Loader JD 524 to 624 or equal10.51039.5 | Corbiere and Sons Contracting586120201017-15Loader JD 524 to 624 or equal10.51039.5Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1039.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5861 | 20201017-15 | 53510504 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10.5 | Dynamic | 98.61 | 0 |  |  | 1380.54 | 179.4702 | 1560.0102 | 2020-10-17 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Loader loading rock trucks, dozer spreading gravel | 5 | C076-C116 | Cook Lake | 0 | 44126 |  | 52 | 44127 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting586120201017-15Dozer D6 or equal- After Jan 1010.51380.54 | Corbiere and Sons Contracting586120201017-15Dozer D6 or equal- After Jan 1010.51380.54Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1380.54 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5861 | 20201017-15 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-10-17 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Loader loading rock trucks, dozer spreading gravel | 5 | C076-C116 | Cook Lake | 0 | 44126 |  | 52 | 44127 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting586120201017-15Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting586120201017-15Light Truck - Pick up- After Jan 102487.5Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5861 | 20201017-15 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 21 | Dynamic | 103.54 | 0 |  |  | 2899.05 | 376.8765 | 3275.9265 | 2020-10-17 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Loader loading rock trucks, dozer spreading gravel | 5 | C076-C116 | Cook Lake | 0 | 44126 |  | 52 | 44127 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting586120201017-15Rock Truck - 30 Ton- After Jan 10212899.05 | Corbiere and Sons Contracting586120201017-15Rock Truck - 30 Ton- After Jan 10212899.05Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 2899.05 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5861 | 20201017-15 | 53510504 | Access | 0 | Foreman | 95 | 6 | HR |  |  | 95 | 0 | 570 | 74.1 | 644.1 | 2020-10-17 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Loader loading rock trucks, dozer spreading gravel | 5 | C076-C116 | Cook Lake | 0 | 44126 |  | 52 | 44127 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting586120201017-15Foreman6570 | Corbiere and Sons Contracting586120201017-15Foreman6570Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 570 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5861 | 20201017-15 | 53510504 | Access | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2020-10-17 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Loader loading rock trucks, dozer spreading gravel | 5 | C076-C116 | Cook Lake | 0 | 44126 |  | 52 | 44127 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting586120201017-15L.O.A.51050 | Corbiere and Sons Contracting586120201017-15L.O.A.51050Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5861 | 20201017-15 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 23 | HR |  |  | 75 | 0 | 1725 | 224.25 | 1949.25 | 2020-10-17 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Loader loading rock trucks, dozer spreading gravel | 5 | C076-C116 | Cook Lake | 0 | 44126 |  | 52 | 44127 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting586120201017-15Operator - Principle - After Jan 10231725 | Corbiere and Sons Contracting586120201017-15Operator - Principle - After Jan 10231725Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5861 | 20201017-15 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 23 | HR |  |  | 70 | 0 | 1610 | 209.3 | 1819.3 | 2020-10-17 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Loader loading rock trucks, dozer spreading gravel | 5 | C076-C116 | Cook Lake | 0 | 44126 |  | 52 | 44127 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting586120201017-15Driver - AZ - After Jan 10231610 | Corbiere and Sons Contracting586120201017-15Driver - AZ - After Jan 10231610Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1610 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5864 | 20201017-18 | 53510512 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10.5 | Dynamic | 110.22 | 0 |  |  | 1543.08 | 200.6004 | 1743.6804 | 2020-10-17 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance from C-076 - C-083 | 5 | C076-C092 | Cook Lake | 0 | 44126 |  | 52 | 44127 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting586420201017-18Excavator - 36 ton- After Jan 1010.51543.08 | Corbiere and Sons Contracting586420201017-18Excavator - 36 ton- After Jan 1010.51543.08Inv#068 | [5 empty] | 1 | 1543.08 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5864 | 20201017-18 | 53510512 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-10-17 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance from C-076 - C-083 | 5 | C076-C092 | Cook Lake | 0 | 44126 |  | 52 | 44127 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting586420201017-18Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting586420201017-18Light Truck - Pick up- After Jan 101243.75Inv#068 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5864 | 20201017-18 | 53510512 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-10-17 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance from C-076 - C-083 | 5 | C076-C092 | Cook Lake | 0 | 44126 |  | 52 | 44127 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting586420201017-18L.O.A.1210 | Corbiere and Sons Contracting586420201017-18L.O.A.1210Inv#068 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5864 | 20201017-18 | 53510512 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-10-17 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance from C-076 - C-083 | 5 | C076-C092 | Cook Lake | 0 | 44126 |  | 52 | 44127 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting586420201017-18Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting586420201017-18Operator - Principle - After Jan 1011.5862.5Inv#068 | [5 empty] | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6093 | 20201017-25 | 53510312 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10 | Dynamic | 103.84 | 0 |  |  | 1384.5 | 179.985 | 1564.485 | 2020-10-17 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-08 ditched water and fixed road Lachance East. | 3 | B161-B181 | Lachance Lake Roaad | 0 | 44134 |  | 37 | 44134 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting609320201017-25Excavator - 30 ton- After Jan 10101384.5 | Corbiere and Sons Contracting609320201017-25Excavator - 30 ton- After Jan 10101384.5Inv#070 | [5 empty] | 1 | 1384.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6093 | 20201017-25 | 53510312 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 9.16 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2020-10-17 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-08 ditched water and fixed road Lachance East. | 3 | B161-B181 | Lachance Lake Roaad | 0 | 44134 |  | 37 | 44134 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting609320201017-25Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting609320201017-25Excavator Thumb - 30 - 50 ton- After Jan 1010122.1Inv#070 | [5 empty] | 1 | 122.1 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6093 | 20201017-25 | 53510312 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-10-17 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-08 ditched water and fixed road Lachance East. | 3 | B161-B181 | Lachance Lake Roaad | 0 | 44134 |  | 37 | 44134 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting609320201017-25Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting609320201017-25Light Truck - Pick up- After Jan 101243.75Inv#070 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6093 | 20201017-25 | 53510312 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2020-10-17 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-08 ditched water and fixed road Lachance East. | 3 | B161-B181 | Lachance Lake Roaad | 0 | 44134 |  | 37 | 44134 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting609320201017-25Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting609320201017-25Operator - Principle - After Jan 1011825Inv#070 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5874 | 20201018-10 | 53510504 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10.5 | Dynamic | 98.61 | 0 |  |  | 1380.54 | 179.4702 | 1560.0102 | 2020-10-18 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks, dozer spreading gravel | 5 | C050-C069 | Antler Lake | 0 | 44126 |  | 52 | 44127 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting587420201018-10Dozer D6 or equal- After Jan 1010.51380.54 | Corbiere and Sons Contracting587420201018-10Dozer D6 or equal- After Jan 1010.51380.54Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1380.54 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5874 | 20201018-10 | 53510504 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10.5 | Dynamic | 103.84 | 0 |  |  | 1453.725 | 188.9843 | 1642.7093 | 2020-10-18 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks, dozer spreading gravel | 5 | C050-C069 | Antler Lake | 0 | 44126 |  | 52 | 44127 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting587420201018-10Excavator - 30 ton- After Jan 1010.51453.725 | Corbiere and Sons Contracting587420201018-10Excavator - 30 ton- After Jan 1010.51453.725Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1453.725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5874 | 20201018-10 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-10-18 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks, dozer spreading gravel | 5 | C050-C069 | Antler Lake | 0 | 44126 |  | 52 | 44127 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting587420201018-10Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting587420201018-10Light Truck - Pick up- After Jan 102487.5Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5874 | 20201018-10 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 21 | Dynamic | 103.54 | 0 |  |  | 2899.05 | 376.8765 | 3275.9265 | 2020-10-18 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks, dozer spreading gravel | 5 | C050-C069 | Antler Lake | 0 | 44126 |  | 52 | 44127 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting587420201018-10Rock Truck - 30 Ton- After Jan 10212899.05 | Corbiere and Sons Contracting587420201018-10Rock Truck - 30 Ton- After Jan 10212899.05Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 2899.05 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5874 | 20201018-10 | 53510504 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2020-10-18 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks, dozer spreading gravel | 5 | C050-C069 | Antler Lake | 0 | 44126 |  | 52 | 44127 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting587420201018-10L.O.A.4840 | Corbiere and Sons Contracting587420201018-10L.O.A.4840Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5874 | 20201018-10 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 23 | HR |  |  | 75 | 0 | 1725 | 224.25 | 1949.25 | 2020-10-18 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks, dozer spreading gravel | 5 | C050-C069 | Antler Lake | 0 | 44126 |  | 52 | 44127 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting587420201018-10Operator - Principle - After Jan 10231725 | Corbiere and Sons Contracting587420201018-10Operator - Principle - After Jan 10231725Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5874 | 20201018-10 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 23 | HR |  |  | 70 | 0 | 1610 | 209.3 | 1819.3 | 2020-10-18 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks, dozer spreading gravel | 5 | C050-C069 | Antler Lake | 0 | 44126 |  | 52 | 44127 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting587420201018-10Driver - AZ - After Jan 10231610 | Corbiere and Sons Contracting587420201018-10Driver - AZ - After Jan 10231610Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1610 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5875 | 20201018-11 | 53510502 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 3 | Dynamic | 103.84 | 0 |  |  | 415.35 | 53.9955 | 469.3455 | 2020-10-18 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jesse on excavator cleaing up rock from hammer, Ron on hammer at C-062, labourers installing geo | 5 | C050-C069 | Antler Lake | 0 | 44126 |  | 52 | 44127 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting587520201018-11Excavator - 30 ton- After Jan 103415.35 | Corbiere and Sons Contracting587520201018-11Excavator - 30 ton- After Jan 103415.35Inv#068 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 415.35 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5875 | 20201018-11 | 53510502 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10.5 | Dynamic | 110.22 | 0 |  |  | 1543.08 | 200.6004 | 1743.6804 | 2020-10-18 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jesse on excavator cleaing up rock from hammer, Ron on hammer at C-062, labourers installing geo | 5 | C050-C069 | Antler Lake | 0 | 44126 |  | 52 | 44127 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting587520201018-11Excavator - 36 ton- After Jan 1010.51543.08 | Corbiere and Sons Contracting587520201018-11Excavator - 36 ton- After Jan 1010.51543.08Inv#068 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 1543.08 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5875 | 20201018-11 | 53510502 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 3 | HR | 9.16 | 0 |  |  | 36.63 | 4.7619 | 41.3919 | 2020-10-18 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jesse on excavator cleaing up rock from hammer, Ron on hammer at C-062, labourers installing geo | 5 | C050-C069 | Antler Lake | 0 | 44126 |  | 52 | 44127 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting587520201018-11Excavator Thumb - 30 - 50 ton- After Jan 10336.63 | Corbiere and Sons Contracting587520201018-11Excavator Thumb - 30 - 50 ton- After Jan 10336.63Inv#068 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 36.63 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5875 | 20201018-11 | 53510502 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10.5 | HR | 9.16 | 0 |  |  | 128.205 | 16.6667 | 144.8716 | 2020-10-18 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jesse on excavator cleaing up rock from hammer, Ron on hammer at C-062, labourers installing geo | 5 | C050-C069 | Antler Lake | 0 | 44126 |  | 52 | 44127 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting587520201018-11Excavator Thumb - 30 - 50 ton- After Jan 1010.5128.205 | Corbiere and Sons Contracting587520201018-11Excavator Thumb - 30 - 50 ton- After Jan 1010.5128.205Inv#068 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 128.205 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5875 | 20201018-11 | 53510502 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-10-18 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jesse on excavator cleaing up rock from hammer, Ron on hammer at C-062, labourers installing geo | 5 | C050-C069 | Antler Lake | 0 | 44126 |  | 52 | 44127 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting587520201018-11Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting587520201018-11Light Truck - Pick up- After Jan 101243.75Inv#068 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5875 | 20201018-11 | 53510502 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-10-18 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jesse on excavator cleaing up rock from hammer, Ron on hammer at C-062, labourers installing geo | 5 | C050-C069 | Antler Lake | 0 | 44126 |  | 52 | 44127 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting587520201018-11L.O.A.2420 | Corbiere and Sons Contracting587520201018-11L.O.A.2420Inv#068 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5875 | 20201018-11 | 53510502 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 14.5 | HR |  |  | 75 | 0 | 1087.5 | 141.375 | 1228.875 | 2020-10-18 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jesse on excavator cleaing up rock from hammer, Ron on hammer at C-062, labourers installing geo | 5 | C050-C069 | Antler Lake | 0 | 44126 |  | 52 | 44127 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting587520201018-11Operator - Principle - After Jan 1014.51087.5 | Corbiere and Sons Contracting587520201018-11Operator - Principle - After Jan 1014.51087.5Inv#068 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 1087.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5875 | 20201018-11 | 53510502 | Access | 0 | Labourer - General - After Jan 10 | 60 | 6 | HR |  |  | 60 | 0 | 360 | 46.8 | 406.8 | 2020-10-18 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jesse on excavator cleaing up rock from hammer, Ron on hammer at C-062, labourers installing geo | 5 | C050-C069 | Antler Lake | 0 | 44126 |  | 52 | 44127 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting587520201018-11Labourer - General - After Jan 106360 | Corbiere and Sons Contracting587520201018-11Labourer - General - After Jan 106360Inv#068 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 360 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5882 | 20201018-18 | 53510512 | Access | 0 | Loader JD 524 to 624 or equal | 99 | 10.5 | HR | 74.25 | 0 |  |  | 1039.5 | 135.135 | 1174.635 | 2020-10-18 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock truck hauling for road maintenance, Darrel on loader and Gary spreading gravel on dozer | 5 | C076-C116 | Cook Lake | 0 | 44126 |  | 52 | 44127 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting588220201018-18Loader JD 524 to 624 or equal10.51039.5 | Corbiere and Sons Contracting588220201018-18Loader JD 524 to 624 or equal10.51039.5Inv#068 | [5 empty] | 1 | 1039.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5882 | 20201018-18 | 53510512 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10.5 | Dynamic | 98.61 | 0 |  |  | 1380.54 | 179.4702 | 1560.0102 | 2020-10-18 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock truck hauling for road maintenance, Darrel on loader and Gary spreading gravel on dozer | 5 | C076-C116 | Cook Lake | 0 | 44126 |  | 52 | 44127 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting588220201018-18Dozer D6 or equal- After Jan 1010.51380.54 | Corbiere and Sons Contracting588220201018-18Dozer D6 or equal- After Jan 1010.51380.54Inv#068 | [5 empty] | 1 | 1380.54 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5882 | 20201018-18 | 53510512 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-10-18 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock truck hauling for road maintenance, Darrel on loader and Gary spreading gravel on dozer | 5 | C076-C116 | Cook Lake | 0 | 44126 |  | 52 | 44127 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting588220201018-18Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting588220201018-18Light Truck - Pick up- After Jan 102487.5Inv#068 | [5 empty] | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5882 | 20201018-18 | 53510512 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 10.5 | Dynamic | 103.54 | 0 |  |  | 1449.525 | 188.4383 | 1637.9633 | 2020-10-18 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock truck hauling for road maintenance, Darrel on loader and Gary spreading gravel on dozer | 5 | C076-C116 | Cook Lake | 0 | 44126 |  | 52 | 44127 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting588220201018-18Rock Truck - 30 Ton- After Jan 1010.51449.525 | Corbiere and Sons Contracting588220201018-18Rock Truck - 30 Ton- After Jan 1010.51449.525Inv#068 | [5 empty] | 1 | 1449.525 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5882 | 20201018-18 | 53510512 | Access | 0 | Foreman | 95 | 4 | HR |  |  | 95 | 0 | 380 | 49.4 | 429.4 | 2020-10-18 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock truck hauling for road maintenance, Darrel on loader and Gary spreading gravel on dozer | 5 | C076-C116 | Cook Lake | 0 | 44126 |  | 52 | 44127 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting588220201018-18Foreman4380 | Corbiere and Sons Contracting588220201018-18Foreman4380Inv#068 | [5 empty] | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5882 | 20201018-18 | 53510512 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2020-10-18 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock truck hauling for road maintenance, Darrel on loader and Gary spreading gravel on dozer | 5 | C076-C116 | Cook Lake | 0 | 44126 |  | 52 | 44127 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting588220201018-18L.O.A.3630 | Corbiere and Sons Contracting588220201018-18L.O.A.3630Inv#068 | [5 empty] | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5882 | 20201018-18 | 53510512 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 23 | HR |  |  | 75 | 0 | 1725 | 224.25 | 1949.25 | 2020-10-18 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock truck hauling for road maintenance, Darrel on loader and Gary spreading gravel on dozer | 5 | C076-C116 | Cook Lake | 0 | 44126 |  | 52 | 44127 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting588220201018-18Operator - Principle - After Jan 10231725 | Corbiere and Sons Contracting588220201018-18Operator - Principle - After Jan 10231725Inv#068 | [5 empty] | 1 | 1725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5882 | 20201018-18 | 53510512 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 11.5 | HR |  |  | 70 | 0 | 805 | 104.65 | 909.65 | 2020-10-18 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock truck hauling for road maintenance, Darrel on loader and Gary spreading gravel on dozer | 5 | C076-C116 | Cook Lake | 0 | 44126 |  | 52 | 44127 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting588220201018-18Driver - AZ - After Jan 1011.5805 | Corbiere and Sons Contracting588220201018-18Driver - AZ - After Jan 1011.5805Inv#068 | [5 empty] | 1 | 805 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5883 | 20201018-19 | 53510503 | Access | 0 | Skidder | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2020-10-18 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Skidder hauling trees from far away to put down corduroy as nothing available at C-094-C095, Miek and Rob on excavators putting down corduroy - 80m | 5 | C076-C116 | Cook Lake | 0 | 44126 |  | 52 | 44127 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting588320201018-19Skidder 91539 | Corbiere and Sons Contracting588320201018-19Skidder 91539Inv#068 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5883 | 20201018-19 | 53510503 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 19 | Dynamic | 110.22 | 0 |  |  | 2792.24 | 362.9912 | 3155.2312 | 2020-10-18 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Skidder hauling trees from far away to put down corduroy as nothing available at C-094-C095, Miek and Rob on excavators putting down corduroy - 80m | 5 | C076-C116 | Cook Lake | 0 | 44126 |  | 52 | 44127 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting588320201018-19Excavator - 36 ton- After Jan 10192792.24 | Corbiere and Sons Contracting588320201018-19Excavator - 36 ton- After Jan 10192792.24Inv#068 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 2792.24 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5883 | 20201018-19 | 53510503 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10.5 | HR | 9.16 | 0 |  |  | 128.205 | 16.6667 | 144.8716 | 2020-10-18 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Skidder hauling trees from far away to put down corduroy as nothing available at C-094-C095, Miek and Rob on excavators putting down corduroy - 80m | 5 | C076-C116 | Cook Lake | 0 | 44126 |  | 52 | 44127 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting588320201018-19Excavator Thumb - 30 - 50 ton- After Jan 1010.5128.205 | Corbiere and Sons Contracting588320201018-19Excavator Thumb - 30 - 50 ton- After Jan 1010.5128.205Inv#068 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 128.205 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5883 | 20201018-19 | 53510503 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-10-18 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Skidder hauling trees from far away to put down corduroy as nothing available at C-094-C095, Miek and Rob on excavators putting down corduroy - 80m | 5 | C076-C116 | Cook Lake | 0 | 44126 |  | 52 | 44127 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting588320201018-19Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting588320201018-19Light Truck - Pick up- After Jan 101243.75Inv#068 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5883 | 20201018-19 | 53510503 | Access | 0 | Foreman | 95 | 4 | HR |  |  | 95 | 0 | 380 | 49.4 | 429.4 | 2020-10-18 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Skidder hauling trees from far away to put down corduroy as nothing available at C-094-C095, Miek and Rob on excavators putting down corduroy - 80m | 5 | C076-C116 | Cook Lake | 0 | 44126 |  | 52 | 44127 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting588320201018-19Foreman4380 | Corbiere and Sons Contracting588320201018-19Foreman4380Inv#068 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5883 | 20201018-19 | 53510503 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2020-10-18 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Skidder hauling trees from far away to put down corduroy as nothing available at C-094-C095, Miek and Rob on excavators putting down corduroy - 80m | 5 | C076-C116 | Cook Lake | 0 | 44126 |  | 52 | 44127 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting588320201018-19L.O.A.3630 | Corbiere and Sons Contracting588320201018-19L.O.A.3630Inv#068 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5883 | 20201018-19 | 53510503 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 34.5 | HR |  |  | 75 | 0 | 2587.5 | 336.375 | 2923.875 | 2020-10-18 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Skidder hauling trees from far away to put down corduroy as nothing available at C-094-C095, Miek and Rob on excavators putting down corduroy - 80m | 5 | C076-C116 | Cook Lake | 0 | 44126 |  | 52 | 44127 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting588320201018-19Operator - Principle - After Jan 1034.52587.5 | Corbiere and Sons Contracting588320201018-19Operator - Principle - After Jan 1034.52587.5Inv#068 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 2587.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6096 | 20201018-25 | 53510312 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 5 | Dynamic | 41.4 | 0 |  |  | 276 | 35.88 | 311.88 | 2020-10-18 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel truck hauled 3 loads of B2 and 1 load of Pit run to Golf Course Road B-087 per Valard request. | 3 | B085-B087 | Golf Course Road | 0 | 44134 |  | 37 | 44134 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting609620201018-25Dump - Triaxle- After Jan 105276 | Corbiere and Sons Contracting609620201018-25Dump - Triaxle- After Jan 105276Inv#070 | [5 empty] | 1 | 276 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6096 | 20201018-25 | 53510312 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 5 | HR |  |  | 70 | 0 | 350 | 45.5 | 395.5 | 2020-10-18 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel truck hauled 3 loads of B2 and 1 load of Pit run to Golf Course Road B-087 per Valard request. | 3 | B085-B087 | Golf Course Road | 0 | 44134 |  | 37 | 44134 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting609620201018-25Driver - AZ - After Jan 105350 | Corbiere and Sons Contracting609620201018-25Driver - AZ - After Jan 105350Inv#070 | [5 empty] | 1 | 350 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5895 | 20201019-10 | 53510504 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10.5 | Dynamic | 98.61 | 0 |  |  | 1380.54 | 179.4702 | 1560.0102 | 2020-10-19 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks with material for roads, dozer spreading gravelLabourers bringing in rolls of geo and rolling it out | 5 | C050-C069 | Antler Lake | 0 | 44126 |  | 52 | 44127 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting589520201019-10Dozer D6 or equal- After Jan 1010.51380.54 | Corbiere and Sons Contracting589520201019-10Dozer D6 or equal- After Jan 1010.51380.54Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1380.54 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5895 | 20201019-10 | 53510504 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10.5 | Dynamic | 103.84 | 0 |  |  | 1453.725 | 188.9843 | 1642.7093 | 2020-10-19 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks with material for roads, dozer spreading gravelLabourers bringing in rolls of geo and rolling it out | 5 | C050-C069 | Antler Lake | 0 | 44126 |  | 52 | 44127 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting589520201019-10Excavator - 30 ton- After Jan 1010.51453.725 | Corbiere and Sons Contracting589520201019-10Excavator - 30 ton- After Jan 1010.51453.725Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1453.725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5895 | 20201019-10 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-10-19 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks with material for roads, dozer spreading gravelLabourers bringing in rolls of geo and rolling it out | 5 | C050-C069 | Antler Lake | 0 | 44126 |  | 52 | 44127 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting589520201019-10Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting589520201019-10Light Truck - Pick up- After Jan 102487.5Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5895 | 20201019-10 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 21 | Dynamic | 103.54 | 0 |  |  | 2899.05 | 376.8765 | 3275.9265 | 2020-10-19 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks with material for roads, dozer spreading gravelLabourers bringing in rolls of geo and rolling it out | 5 | C050-C069 | Antler Lake | 0 | 44126 |  | 52 | 44127 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting589520201019-10Rock Truck - 30 Ton- After Jan 10212899.05 | Corbiere and Sons Contracting589520201019-10Rock Truck - 30 Ton- After Jan 10212899.05Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 2899.05 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5895 | 20201019-10 | 53510504 | Access | 0 | Foreman | 95 | 6 | HR |  |  | 95 | 0 | 570 | 74.1 | 644.1 | 2020-10-19 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks with material for roads, dozer spreading gravelLabourers bringing in rolls of geo and rolling it out | 5 | C050-C069 | Antler Lake | 0 | 44126 |  | 52 | 44127 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting589520201019-10Foreman6570 | Corbiere and Sons Contracting589520201019-10Foreman6570Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 570 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5895 | 20201019-10 | 53510504 | Access | 0 | L.O.A. | 210 | 7 | DAY |  |  |  | 0 | 1470 | 191.1 | 1661.1 | 2020-10-19 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks with material for roads, dozer spreading gravelLabourers bringing in rolls of geo and rolling it out | 5 | C050-C069 | Antler Lake | 0 | 44126 |  | 52 | 44127 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting589520201019-10L.O.A.71470 | Corbiere and Sons Contracting589520201019-10L.O.A.71470Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1470 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5895 | 20201019-10 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 23 | HR |  |  | 75 | 0 | 1725 | 224.25 | 1949.25 | 2020-10-19 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks with material for roads, dozer spreading gravelLabourers bringing in rolls of geo and rolling it out | 5 | C050-C069 | Antler Lake | 0 | 44126 |  | 52 | 44127 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting589520201019-10Operator - Principle - After Jan 10231725 | Corbiere and Sons Contracting589520201019-10Operator - Principle - After Jan 10231725Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5895 | 20201019-10 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 23 | HR |  |  | 70 | 0 | 1610 | 209.3 | 1819.3 | 2020-10-19 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks with material for roads, dozer spreading gravelLabourers bringing in rolls of geo and rolling it out | 5 | C050-C069 | Antler Lake | 0 | 44126 |  | 52 | 44127 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting589520201019-10Driver - AZ - After Jan 10231610 | Corbiere and Sons Contracting589520201019-10Driver - AZ - After Jan 10231610Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1610 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5895 | 20201019-10 | 53510504 | Access | 0 | Labourer - General - After Jan 10 | 60 | 6 | HR |  |  | 60 | 0 | 360 | 46.8 | 406.8 | 2020-10-19 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks with material for roads, dozer spreading gravelLabourers bringing in rolls of geo and rolling it out | 5 | C050-C069 | Antler Lake | 0 | 44126 |  | 52 | 44127 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting589520201019-10Labourer - General - After Jan 106360 | Corbiere and Sons Contracting589520201019-10Labourer - General - After Jan 106360Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 360 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5902 | 20201019-17 | 53510512 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 4 | Dynamic | 98.61 | 0 |  |  | 525.92 | 68.3696 | 594.2896 | 2020-10-19 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 350X4 and dozer doing road maintenance from C-095 | 5 | C093-C116 | Cook Lake | 0 | 44126 |  | 52 | 44127 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting590220201019-17Dozer D6 or equal- After Jan 104525.92 | Corbiere and Sons Contracting590220201019-17Dozer D6 or equal- After Jan 104525.92Inv#068 | [5 empty] | 1 | 525.92 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5902 | 20201019-17 | 53510512 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 4 | Dynamic | 110.22 | 0 |  |  | 587.84 | 76.4192 | 664.2592 | 2020-10-19 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 350X4 and dozer doing road maintenance from C-095 | 5 | C093-C116 | Cook Lake | 0 | 44126 |  | 52 | 44127 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting590220201019-17Excavator - 36 ton- After Jan 104587.84 | Corbiere and Sons Contracting590220201019-17Excavator - 36 ton- After Jan 104587.84Inv#068 | [5 empty] | 1 | 587.84 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5902 | 20201019-17 | 53510512 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-10-19 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 350X4 and dozer doing road maintenance from C-095 | 5 | C093-C116 | Cook Lake | 0 | 44126 |  | 52 | 44127 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting590220201019-17L.O.A.2420 | Corbiere and Sons Contracting590220201019-17L.O.A.2420Inv#068 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5902 | 20201019-17 | 53510512 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 8 | HR |  |  | 75 | 0 | 600 | 78 | 678 | 2020-10-19 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 350X4 and dozer doing road maintenance from C-095 | 5 | C093-C116 | Cook Lake | 0 | 44126 |  | 52 | 44127 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting590220201019-17Operator - Principle - After Jan 108600 | Corbiere and Sons Contracting590220201019-17Operator - Principle - After Jan 108600Inv#068 | [5 empty] | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5903 | 20201019-18 | 53510504 | Access | 0 | Loader JD 524 to 624 or equal | 99 | 10.5 | HR | 74.25 | 0 |  |  | 1039.5 | 135.135 | 1174.635 | 2020-10-19 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gary on dozer for road maintenance, Chris on rock truck hauling gravel for cappingJohn on rock truck hauling from laydown to KM3-KM4 for capping, Darrell on loader at laydown loading rock trucks | 5 | C076-C116 | Cook Lake | 0 | 44126 |  | 52 | 44127 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting590320201019-18Loader JD 524 to 624 or equal10.51039.5 | Corbiere and Sons Contracting590320201019-18Loader JD 524 to 624 or equal10.51039.5Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1039.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5903 | 20201019-18 | 53510504 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 4 | Dynamic | 98.61 | 0 |  |  | 525.92 | 68.3696 | 594.2896 | 2020-10-19 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gary on dozer for road maintenance, Chris on rock truck hauling gravel for cappingJohn on rock truck hauling from laydown to KM3-KM4 for capping, Darrell on loader at laydown loading rock trucks | 5 | C076-C116 | Cook Lake | 0 | 44126 |  | 52 | 44127 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting590320201019-18Dozer D6 or equal- After Jan 104525.92 | Corbiere and Sons Contracting590320201019-18Dozer D6 or equal- After Jan 104525.92Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 525.92 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5903 | 20201019-18 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-10-19 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gary on dozer for road maintenance, Chris on rock truck hauling gravel for cappingJohn on rock truck hauling from laydown to KM3-KM4 for capping, Darrell on loader at laydown loading rock trucks | 5 | C076-C116 | Cook Lake | 0 | 44126 |  | 52 | 44127 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting590320201019-18Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting590320201019-18Light Truck - Pick up- After Jan 102487.5Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5903 | 20201019-18 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 18 | Dynamic | 103.54 | 0 |  |  | 2484.9 | 323.037 | 2807.937 | 2020-10-19 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gary on dozer for road maintenance, Chris on rock truck hauling gravel for cappingJohn on rock truck hauling from laydown to KM3-KM4 for capping, Darrell on loader at laydown loading rock trucks | 5 | C076-C116 | Cook Lake | 0 | 44126 |  | 52 | 44127 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting590320201019-18Rock Truck - 30 Ton- After Jan 10182484.9 | Corbiere and Sons Contracting590320201019-18Rock Truck - 30 Ton- After Jan 10182484.9Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 2484.9 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5903 | 20201019-18 | 53510504 | Access | 0 | Foreman | 95 | 4 | HR |  |  | 95 | 0 | 380 | 49.4 | 429.4 | 2020-10-19 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gary on dozer for road maintenance, Chris on rock truck hauling gravel for cappingJohn on rock truck hauling from laydown to KM3-KM4 for capping, Darrell on loader at laydown loading rock trucks | 5 | C076-C116 | Cook Lake | 0 | 44126 |  | 52 | 44127 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting590320201019-18Foreman4380 | Corbiere and Sons Contracting590320201019-18Foreman4380Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5903 | 20201019-18 | 53510504 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2020-10-19 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gary on dozer for road maintenance, Chris on rock truck hauling gravel for cappingJohn on rock truck hauling from laydown to KM3-KM4 for capping, Darrell on loader at laydown loading rock trucks | 5 | C076-C116 | Cook Lake | 0 | 44126 |  | 52 | 44127 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting590320201019-18L.O.A.3630 | Corbiere and Sons Contracting590320201019-18L.O.A.3630Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5903 | 20201019-18 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 15.5 | HR |  |  | 75 | 0 | 1162.5 | 151.125 | 1313.625 | 2020-10-19 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gary on dozer for road maintenance, Chris on rock truck hauling gravel for cappingJohn on rock truck hauling from laydown to KM3-KM4 for capping, Darrell on loader at laydown loading rock trucks | 5 | C076-C116 | Cook Lake | 0 | 44126 |  | 52 | 44127 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting590320201019-18Operator - Principle - After Jan 1015.51162.5 | Corbiere and Sons Contracting590320201019-18Operator - Principle - After Jan 1015.51162.5Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1162.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5903 | 20201019-18 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 19.5 | HR |  |  | 70 | 0 | 1365 | 177.45 | 1542.45 | 2020-10-19 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gary on dozer for road maintenance, Chris on rock truck hauling gravel for cappingJohn on rock truck hauling from laydown to KM3-KM4 for capping, Darrell on loader at laydown loading rock trucks | 5 | C076-C116 | Cook Lake | 0 | 44126 |  | 52 | 44127 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting590320201019-18Driver - AZ - After Jan 1019.51365 | Corbiere and Sons Contracting590320201019-18Driver - AZ - After Jan 1019.51365Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1365 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5906 | 20201019-21 | 53510503 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 3.5 | Dynamic | 103.84 | 0 |  |  | 484.575 | 62.9948 | 547.5697 | 2020-10-19 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Build corduroy to install location | 5 | C076-C116 | Cook Lake | 0 | 44126 |  | 52 | 44127 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting590620201019-21Excavator - 30 ton- After Jan 103.5484.575 | Corbiere and Sons Contracting590620201019-21Excavator - 30 ton- After Jan 103.5484.575Inv#068 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 484.575 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5906 | 20201019-21 | 53510503 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 3.5 | HR |  |  | 75 | 0 | 262.5 | 34.125 | 296.625 | 2020-10-19 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Build corduroy to install location | 5 | C076-C116 | Cook Lake | 0 | 44126 |  | 52 | 44127 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting590620201019-21Operator - Principle - After Jan 103.5262.5 | Corbiere and Sons Contracting590620201019-21Operator - Principle - After Jan 103.5262.5Inv#068 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 262.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5906 | 20201019-21 | 53510503 | Access | 0 | Labourer - General - After Jan 10 | 60 | 7 | HR |  |  | 60 | 0 | 420 | 54.6 | 474.6 | 2020-10-19 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Build corduroy to install location | 5 | C076-C116 | Cook Lake | 0 | 44126 |  | 52 | 44127 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting590620201019-21Labourer - General - After Jan 107420 | Corbiere and Sons Contracting590620201019-21Labourer - General - After Jan 107420Inv#068 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6029 | 20201019-27 | 53510312 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10 | Dynamic | 98.61 | 0 |  |  | 1314.8 | 170.924 | 1485.724 | 2020-10-19 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-09 shifted road location at B-079 to avoid an anchor at Landfill road. DZ-05 removed water off the road with run off ditches and back bladed. | 3 | B078-B084 | Red Roc Road No. 7 | 0 | 44133 |  | 50 | 44133 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting602920201019-27Dozer D6 or equal- After Jan 10101314.8 | Corbiere and Sons Contracting602920201019-27Dozer D6 or equal- After Jan 10101314.8Inv#068 | [5 empty] | 1 | 1314.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6029 | 20201019-27 | 53510312 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 5 | Dynamic | 110.22 | 0 |  |  | 734.8 | 95.524 | 830.324 | 2020-10-19 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-09 shifted road location at B-079 to avoid an anchor at Landfill road. DZ-05 removed water off the road with run off ditches and back bladed. | 3 | B078-B084 | Red Roc Road No. 7 | 0 | 44133 |  | 50 | 44133 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting602920201019-27Excavator - 36 ton- After Jan 105734.8 | Corbiere and Sons Contracting602920201019-27Excavator - 36 ton- After Jan 105734.8Inv#068 | [5 empty] | 1 | 734.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6029 | 20201019-27 | 53510312 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 5 | HR | 9.16 | 0 |  |  | 61.05 | 7.9365 | 68.9865 | 2020-10-19 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-09 shifted road location at B-079 to avoid an anchor at Landfill road. DZ-05 removed water off the road with run off ditches and back bladed. | 3 | B078-B084 | Red Roc Road No. 7 | 0 | 44133 |  | 50 | 44133 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting602920201019-27Excavator Thumb - 30 - 50 ton- After Jan 10561.05 | Corbiere and Sons Contracting602920201019-27Excavator Thumb - 30 - 50 ton- After Jan 10561.05Inv#068 | [5 empty] | 1 | 61.05 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6029 | 20201019-27 | 53510312 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-10-19 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-09 shifted road location at B-079 to avoid an anchor at Landfill road. DZ-05 removed water off the road with run off ditches and back bladed. | 3 | B078-B084 | Red Roc Road No. 7 | 0 | 44133 |  | 50 | 44133 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting602920201019-27Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting602920201019-27Light Truck - Pick up- After Jan 102487.5Inv#068 | [5 empty] | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6029 | 20201019-27 | 53510312 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 17 | HR |  |  | 75 | 0 | 1275 | 165.75 | 1440.75 | 2020-10-19 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-09 shifted road location at B-079 to avoid an anchor at Landfill road. DZ-05 removed water off the road with run off ditches and back bladed. | 3 | B078-B084 | Red Roc Road No. 7 | 0 | 44133 |  | 50 | 44133 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting602920201019-27Operator - Principle - After Jan 10171275 | Corbiere and Sons Contracting602920201019-27Operator - Principle - After Jan 10171275Inv#068 | [5 empty] | 1 | 1275 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6030 | 20201019-28 | 53510312 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10 | Dynamic | 103.84 | 0 |  |  | 1384.5 | 179.985 | 1564.485 | 2020-10-19 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ditched water and managed road maintenance at Lachance Rd | 3 | B 161-B181 | Lachance Road | 0 | 44133 |  | 50 | 44133 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting603020201019-28Excavator - 30 ton- After Jan 10101384.5 | Corbiere and Sons Contracting603020201019-28Excavator - 30 ton- After Jan 10101384.5Inv#068 | [5 empty] | 1 | 1384.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6030 | 20201019-28 | 53510312 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 9.16 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2020-10-19 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ditched water and managed road maintenance at Lachance Rd | 3 | B 161-B181 | Lachance Road | 0 | 44133 |  | 50 | 44133 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting603020201019-28Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting603020201019-28Excavator Thumb - 30 - 50 ton- After Jan 1010122.1Inv#068 | [5 empty] | 1 | 122.1 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6030 | 20201019-28 | 53510312 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-10-19 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ditched water and managed road maintenance at Lachance Rd | 3 | B 161-B181 | Lachance Road | 0 | 44133 |  | 50 | 44133 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting603020201019-28Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting603020201019-28Light Truck - Pick up- After Jan 101243.75Inv#068 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6030 | 20201019-28 | 53510312 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2020-10-19 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ditched water and managed road maintenance at Lachance Rd | 3 | B 161-B181 | Lachance Road | 0 | 44133 |  | 50 | 44133 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting603020201019-28Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting603020201019-28Operator - Principle - After Jan 1011825Inv#068 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5893 | 20201019-8 | 53510504 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 17 | Dynamic | 41.4 | 0 |  |  | 938.4 | 121.992 | 1060.392 | 2020-10-19 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hauling gravel from Worthington Bay pit to Cook Lake Road Access | 5 | C076-C116 | Cook Lake | 0 | 44126 |  | 52 | 44127 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting589320201019-8Dump - Triaxle- After Jan 1017938.4 | Corbiere and Sons Contracting589320201019-8Dump - Triaxle- After Jan 1017938.4Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 938.4 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5893 | 20201019-8 | 53510504 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-10-19 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hauling gravel from Worthington Bay pit to Cook Lake Road Access | 5 | C076-C116 | Cook Lake | 0 | 44126 |  | 52 | 44127 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting589320201019-8L.O.A.1210 | Corbiere and Sons Contracting589320201019-8L.O.A.1210Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5893 | 20201019-8 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 17 | HR |  |  | 70 | 0 | 1190 | 154.7 | 1344.7 | 2020-10-19 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hauling gravel from Worthington Bay pit to Cook Lake Road Access | 5 | C076-C116 | Cook Lake | 0 | 44126 |  | 52 | 44127 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting589320201019-8Driver - AZ - After Jan 10171190 | Corbiere and Sons Contracting589320201019-8Driver - AZ - After Jan 10171190Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1190 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5934 | 20201020-11 | 53510504 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10.5 | Dynamic | 98.61 | 0 |  |  | 1380.54 | 179.4702 | 1560.0102 | 2020-10-20 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks, rock trucks hauling gravel, dozer spreading gravelLabourers laid geo | 5 | C050-C069 | Antler Lake | 0 | 44127 |  | 52 | 44129 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting593420201020-11Dozer D6 or equal- After Jan 1010.51380.54 | Corbiere and Sons Contracting593420201020-11Dozer D6 or equal- After Jan 1010.51380.54Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1380.54 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5934 | 20201020-11 | 53510504 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10.5 | Dynamic | 103.84 | 0 |  |  | 1453.725 | 188.9843 | 1642.7093 | 2020-10-20 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks, rock trucks hauling gravel, dozer spreading gravelLabourers laid geo | 5 | C050-C069 | Antler Lake | 0 | 44127 |  | 52 | 44129 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting593420201020-11Excavator - 30 ton- After Jan 1010.51453.725 | Corbiere and Sons Contracting593420201020-11Excavator - 30 ton- After Jan 1010.51453.725Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1453.725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5934 | 20201020-11 | 53510504 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10.5 | HR | 9.16 | 0 |  |  | 128.205 | 16.6667 | 144.8716 | 2020-10-20 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks, rock trucks hauling gravel, dozer spreading gravelLabourers laid geo | 5 | C050-C069 | Antler Lake | 0 | 44127 |  | 52 | 44129 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting593420201020-11Excavator Thumb - 30 - 50 ton- After Jan 1010.5128.205 | Corbiere and Sons Contracting593420201020-11Excavator Thumb - 30 - 50 ton- After Jan 1010.5128.205Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 128.205 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5934 | 20201020-11 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-10-20 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks, rock trucks hauling gravel, dozer spreading gravelLabourers laid geo | 5 | C050-C069 | Antler Lake | 0 | 44127 |  | 52 | 44129 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting593420201020-11Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting593420201020-11Light Truck - Pick up- After Jan 102487.5Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5934 | 20201020-11 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 17.5 | Dynamic | 103.54 | 0 |  |  | 2415.875 | 314.0638 | 2729.9387 | 2020-10-20 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks, rock trucks hauling gravel, dozer spreading gravelLabourers laid geo | 5 | C050-C069 | Antler Lake | 0 | 44127 |  | 52 | 44129 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting593420201020-11Rock Truck - 30 Ton- After Jan 1017.52415.875 | Corbiere and Sons Contracting593420201020-11Rock Truck - 30 Ton- After Jan 1017.52415.875Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 2415.875 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5934 | 20201020-11 | 53510504 | Access | 0 | Foreman | 95 | 4 | HR |  |  | 95 | 0 | 380 | 49.4 | 429.4 | 2020-10-20 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks, rock trucks hauling gravel, dozer spreading gravelLabourers laid geo | 5 | C050-C069 | Antler Lake | 0 | 44127 |  | 52 | 44129 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting593420201020-11Foreman4380 | Corbiere and Sons Contracting593420201020-11Foreman4380Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5934 | 20201020-11 | 53510504 | Access | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2020-10-20 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks, rock trucks hauling gravel, dozer spreading gravelLabourers laid geo | 5 | C050-C069 | Antler Lake | 0 | 44127 |  | 52 | 44129 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting593420201020-11L.O.A.51050 | Corbiere and Sons Contracting593420201020-11L.O.A.51050Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5934 | 20201020-11 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 23 | HR |  |  | 75 | 0 | 1725 | 224.25 | 1949.25 | 2020-10-20 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks, rock trucks hauling gravel, dozer spreading gravelLabourers laid geo | 5 | C050-C069 | Antler Lake | 0 | 44127 |  | 52 | 44129 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting593420201020-11Operator - Principle - After Jan 10231725 | Corbiere and Sons Contracting593420201020-11Operator - Principle - After Jan 10231725Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5934 | 20201020-11 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 19 | HR |  |  | 70 | 0 | 1330 | 172.9 | 1502.9 | 2020-10-20 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks, rock trucks hauling gravel, dozer spreading gravelLabourers laid geo | 5 | C050-C069 | Antler Lake | 0 | 44127 |  | 52 | 44129 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting593420201020-11Driver - AZ - After Jan 10191330 | Corbiere and Sons Contracting593420201020-11Driver - AZ - After Jan 10191330Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1330 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5934 | 20201020-11 | 53510504 | Access | 0 | Labourer - General - After Jan 10 | 60 | 6 | HR |  |  | 60 | 0 | 360 | 46.8 | 406.8 | 2020-10-20 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks, rock trucks hauling gravel, dozer spreading gravelLabourers laid geo | 5 | C050-C069 | Antler Lake | 0 | 44127 |  | 52 | 44129 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting593420201020-11Labourer - General - After Jan 106360 | Corbiere and Sons Contracting593420201020-11Labourer - General - After Jan 106360Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 360 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5943 | 20201020-20 | 53510504 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 21 | Dynamic | 98.61 | 0 |  |  | 2761.08 | 358.9404 | 3120.0204 | 2020-10-20 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavators loading rock trucks, dozers doing gravel spread. | 5 | C076-C116 | Cook Lake | 0 | 44127 |  | 52 | 44129 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting594320201020-20Dozer D6 or equal- After Jan 10212761.08 | Corbiere and Sons Contracting594320201020-20Dozer D6 or equal- After Jan 10212761.08Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 2761.08 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5943 | 20201020-20 | 53510504 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10.5 | Dynamic | 103.84 | 0 |  |  | 1453.725 | 188.9843 | 1642.7093 | 2020-10-20 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavators loading rock trucks, dozers doing gravel spread. | 5 | C076-C116 | Cook Lake | 0 | 44127 |  | 52 | 44129 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting594320201020-20Excavator - 30 ton- After Jan 1010.51453.725 | Corbiere and Sons Contracting594320201020-20Excavator - 30 ton- After Jan 1010.51453.725Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1453.725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5943 | 20201020-20 | 53510504 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10.5 | Dynamic | 110.22 | 0 |  |  | 1543.08 | 200.6004 | 1743.6804 | 2020-10-20 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavators loading rock trucks, dozers doing gravel spread. | 5 | C076-C116 | Cook Lake | 0 | 44127 |  | 52 | 44129 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting594320201020-20Excavator - 36 ton- After Jan 1010.51543.08 | Corbiere and Sons Contracting594320201020-20Excavator - 36 ton- After Jan 1010.51543.08Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1543.08 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5943 | 20201020-20 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2020-10-20 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavators loading rock trucks, dozers doing gravel spread. | 5 | C076-C116 | Cook Lake | 0 | 44127 |  | 52 | 44129 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting594320201020-20Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting594320201020-20Light Truck - Pick up- After Jan 103731.25Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 731.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5943 | 20201020-20 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 21 | Dynamic | 103.54 | 0 |  |  | 2899.05 | 376.8765 | 3275.9265 | 2020-10-20 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavators loading rock trucks, dozers doing gravel spread. | 5 | C076-C116 | Cook Lake | 0 | 44127 |  | 52 | 44129 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting594320201020-20Rock Truck - 30 Ton- After Jan 10212899.05 | Corbiere and Sons Contracting594320201020-20Rock Truck - 30 Ton- After Jan 10212899.05Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 2899.05 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5943 | 20201020-20 | 53510504 | Access | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2020-10-20 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavators loading rock trucks, dozers doing gravel spread. | 5 | C076-C116 | Cook Lake | 0 | 44127 |  | 52 | 44129 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting594320201020-20L.O.A.61260 | Corbiere and Sons Contracting594320201020-20L.O.A.61260Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5943 | 20201020-20 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 52 | HR |  |  | 75 | 0 | 3900 | 507 | 4407 | 2020-10-20 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavators loading rock trucks, dozers doing gravel spread. | 5 | C076-C116 | Cook Lake | 0 | 44127 |  | 52 | 44129 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting594320201020-20Operator - Principle - After Jan 10523900 | Corbiere and Sons Contracting594320201020-20Operator - Principle - After Jan 10523900Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 3900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5943 | 20201020-20 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 23 | HR |  |  | 70 | 0 | 1610 | 209.3 | 1819.3 | 2020-10-20 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavators loading rock trucks, dozers doing gravel spread. | 5 | C076-C116 | Cook Lake | 0 | 44127 |  | 52 | 44129 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting594320201020-20Driver - AZ - After Jan 10231610 | Corbiere and Sons Contracting594320201020-20Driver - AZ - After Jan 10231610Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1610 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5944 | 20201020-21 | 53510512 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 4 | Dynamic | 110.22 | 0 |  |  | 587.84 | 76.4192 | 664.2592 | 2020-10-20 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance just south of WC at C-094 | 5 | C093-C116 | Cook Lake | 0 | 44127 |  | 52 | 44129 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting594420201020-21Excavator - 36 ton- After Jan 104587.84 | Corbiere and Sons Contracting594420201020-21Excavator - 36 ton- After Jan 104587.84Inv#068 | [5 empty] | 1 | 587.84 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5944 | 20201020-21 | 53510512 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 4 | HR | 9.16 | 0 |  |  | 48.84 | 6.3492 | 55.1892 | 2020-10-20 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance just south of WC at C-094 | 5 | C093-C116 | Cook Lake | 0 | 44127 |  | 52 | 44129 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting594420201020-21Excavator Thumb - 30 - 50 ton- After Jan 10448.84 | Corbiere and Sons Contracting594420201020-21Excavator Thumb - 30 - 50 ton- After Jan 10448.84Inv#068 | [5 empty] | 1 | 48.84 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5944 | 20201020-21 | 53510512 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-10-20 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance just south of WC at C-094 | 5 | C093-C116 | Cook Lake | 0 | 44127 |  | 52 | 44129 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting594420201020-21Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting594420201020-21Light Truck - Pick up- After Jan 101243.75Inv#068 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5944 | 20201020-21 | 53510512 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-10-20 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance just south of WC at C-094 | 5 | C093-C116 | Cook Lake | 0 | 44127 |  | 52 | 44129 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting594420201020-21L.O.A.1210 | Corbiere and Sons Contracting594420201020-21L.O.A.1210Inv#068 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 5944 | 20201020-21 | 53510512 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 4 | HR |  |  | 75 | 0 | 300 | 39 | 339 | 2020-10-20 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance just south of WC at C-094 | 5 | C093-C116 | Cook Lake | 0 | 44127 |  | 52 | 44129 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting594420201020-21Operator - Principle - After Jan 104300 | Corbiere and Sons Contracting594420201020-21Operator - Principle - After Jan 104300Inv#068 | [5 empty] | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6039 | 20201020-30 | 53510312 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 8 | Dynamic | 103.84 | 0 |  |  | 1107.6 | 143.988 | 1251.588 | 2020-10-20 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-08 floated to Landfill and ditched water walking in. | 3 | B078-B084 | Red Rock Road No.7 | 0 | 44133 |  | 50 | 44133 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting603920201020-30Excavator - 30 ton- After Jan 1081107.6 | Corbiere and Sons Contracting603920201020-30Excavator - 30 ton- After Jan 1081107.6Inv#068 | [5 empty] | 1 | 1107.6 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6039 | 20201020-30 | 53510312 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 8 | HR | 9.16 | 0 |  |  | 97.68 | 12.6984 | 110.3784 | 2020-10-20 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-08 floated to Landfill and ditched water walking in. | 3 | B078-B084 | Red Rock Road No.7 | 0 | 44133 |  | 50 | 44133 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting603920201020-30Excavator Thumb - 30 - 50 ton- After Jan 10897.68 | Corbiere and Sons Contracting603920201020-30Excavator Thumb - 30 - 50 ton- After Jan 10897.68Inv#068 | [5 empty] | 1 | 97.68 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6039 | 20201020-30 | 53510312 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-10-20 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-08 floated to Landfill and ditched water walking in. | 3 | B078-B084 | Red Rock Road No.7 | 0 | 44133 |  | 50 | 44133 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting603920201020-30Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting603920201020-30Light Truck - Pick up- After Jan 101243.75Inv#068 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6039 | 20201020-30 | 53510312 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 9 | HR |  |  | 75 | 0 | 675 | 87.75 | 762.75 | 2020-10-20 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-08 floated to Landfill and ditched water walking in. | 3 | B078-B084 | Red Rock Road No.7 | 0 | 44133 |  | 50 | 44133 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting603920201020-30Operator - Principle - After Jan 109675 | Corbiere and Sons Contracting603920201020-30Operator - Principle - After Jan 109675Inv#068 | [5 empty] | 1 | 675 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6042 | 20201020-33 | 53510412 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 7 | Dynamic | 98.61 | 0 |  |  | 920.36 | 119.6468 | 1040.0068 | 2020-10-20 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-07 fixed bad spots while walking in, DZ-04 trimmed up existing access road and fixed bad spots. | 4 | B194-B210 | Little Gravel River Road | 0 | 44133 |  | 50 | 44133 | [5 empty] | Wes Seminowich | 04 | Corbiere and Sons Contracting604220201020-33Dozer D6 or equal- After Jan 107920.36 | Corbiere and Sons Contracting604220201020-33Dozer D6 or equal- After Jan 107920.36Inv#068 | [5 empty] | 1 | 920.36 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6042 | 20201020-33 | 53510412 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 3 | Dynamic | 110.22 | 0 |  |  | 440.88 | 57.3144 | 498.1944 | 2020-10-20 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-07 fixed bad spots while walking in, DZ-04 trimmed up existing access road and fixed bad spots. | 4 | B194-B210 | Little Gravel River Road | 0 | 44133 |  | 50 | 44133 | [5 empty] | Wes Seminowich | 04 | Corbiere and Sons Contracting604220201020-33Excavator - 36 ton- After Jan 103440.88 | Corbiere and Sons Contracting604220201020-33Excavator - 36 ton- After Jan 103440.88Inv#068 | [5 empty] | 1 | 440.88 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6042 | 20201020-33 | 53510412 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 3 | HR | 9.16 | 0 |  |  | 36.63 | 4.7619 | 41.3919 | 2020-10-20 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-07 fixed bad spots while walking in, DZ-04 trimmed up existing access road and fixed bad spots. | 4 | B194-B210 | Little Gravel River Road | 0 | 44133 |  | 50 | 44133 | [5 empty] | Wes Seminowich | 04 | Corbiere and Sons Contracting604220201020-33Excavator Thumb - 30 - 50 ton- After Jan 10336.63 | Corbiere and Sons Contracting604220201020-33Excavator Thumb - 30 - 50 ton- After Jan 10336.63Inv#068 | [5 empty] | 1 | 36.63 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6042 | 20201020-33 | 53510412 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 10 | HR |  |  | 75 | 0 | 750 | 97.5 | 847.5 | 2020-10-20 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-07 fixed bad spots while walking in, DZ-04 trimmed up existing access road and fixed bad spots. | 4 | B194-B210 | Little Gravel River Road | 0 | 44133 |  | 50 | 44133 | [5 empty] | Wes Seminowich | 04 | Corbiere and Sons Contracting604220201020-33Operator - Principle - After Jan 1010750 | Corbiere and Sons Contracting604220201020-33Operator - Principle - After Jan 1010750Inv#068 | [5 empty] | 1 | 750 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6046 | 20201021-10 | 53510504 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 6.5 | Dynamic | 103.84 | 0 |  |  | 899.925 | 116.9903 | 1016.9153 | 2020-10-21 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel hauling, excavator loading rock trucks. Shut down at 1 and 2 respectively due to causing damage to roads. | 5 | C050-C069 | Antler Lake | 0 | 44133 |  | 37 | 44133 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting604620201021-10Excavator - 30 ton- After Jan 106.5899.925 | Corbiere and Sons Contracting604620201021-10Excavator - 30 ton- After Jan 106.5899.925Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 899.925 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6046 | 20201021-10 | 53510504 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 6.5 | HR | 9.16 | 0 |  |  | 79.365 | 10.3174 | 89.6825 | 2020-10-21 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel hauling, excavator loading rock trucks. Shut down at 1 and 2 respectively due to causing damage to roads. | 5 | C050-C069 | Antler Lake | 0 | 44133 |  | 37 | 44133 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting604620201021-10Excavator Thumb - 30 - 50 ton- After Jan 106.579.365 | Corbiere and Sons Contracting604620201021-10Excavator Thumb - 30 - 50 ton- After Jan 106.579.365Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 79.365 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6046 | 20201021-10 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-10-21 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel hauling, excavator loading rock trucks. Shut down at 1 and 2 respectively due to causing damage to roads. | 5 | C050-C069 | Antler Lake | 0 | 44133 |  | 37 | 44133 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting604620201021-10Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting604620201021-10Light Truck - Pick up- After Jan 101243.75Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6046 | 20201021-10 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 8.5 | Dynamic | 103.54 | 0 |  |  | 1173.425 | 152.5453 | 1325.9703 | 2020-10-21 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel hauling, excavator loading rock trucks. Shut down at 1 and 2 respectively due to causing damage to roads. | 5 | C050-C069 | Antler Lake | 0 | 44133 |  | 37 | 44133 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting604620201021-10Rock Truck - 30 Ton- After Jan 108.51173.425 | Corbiere and Sons Contracting604620201021-10Rock Truck - 30 Ton- After Jan 108.51173.425Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1173.425 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6046 | 20201021-10 | 53510504 | Access | 0 | Foreman | 95 | 3 | HR |  |  | 95 | 0 | 285 | 37.05 | 322.05 | 2020-10-21 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel hauling, excavator loading rock trucks. Shut down at 1 and 2 respectively due to causing damage to roads. | 5 | C050-C069 | Antler Lake | 0 | 44133 |  | 37 | 44133 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting604620201021-10Foreman3285 | Corbiere and Sons Contracting604620201021-10Foreman3285Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 285 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6046 | 20201021-10 | 53510504 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2020-10-21 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel hauling, excavator loading rock trucks. Shut down at 1 and 2 respectively due to causing damage to roads. | 5 | C050-C069 | Antler Lake | 0 | 44133 |  | 37 | 44133 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting604620201021-10L.O.A.3630 | Corbiere and Sons Contracting604620201021-10L.O.A.3630Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6046 | 20201021-10 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 7 | HR |  |  | 75 | 0 | 525 | 68.25 | 593.25 | 2020-10-21 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel hauling, excavator loading rock trucks. Shut down at 1 and 2 respectively due to causing damage to roads. | 5 | C050-C069 | Antler Lake | 0 | 44133 |  | 37 | 44133 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting604620201021-10Operator - Principle - After Jan 107525 | Corbiere and Sons Contracting604620201021-10Operator - Principle - After Jan 107525Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 525 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6046 | 20201021-10 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 9 | HR |  |  | 70 | 0 | 630 | 81.9 | 711.9 | 2020-10-21 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel hauling, excavator loading rock trucks. Shut down at 1 and 2 respectively due to causing damage to roads. | 5 | C050-C069 | Antler Lake | 0 | 44133 |  | 37 | 44133 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting604620201021-10Driver - AZ - After Jan 109630 | Corbiere and Sons Contracting604620201021-10Driver - AZ - After Jan 109630Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6046 | 20201021-10 | 53510504 | Access | 0 | Labourer - General - After Jan 10 | 60 | 3 | HR |  |  | 60 | 0 | 180 | 23.4 | 203.4 | 2020-10-21 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel hauling, excavator loading rock trucks. Shut down at 1 and 2 respectively due to causing damage to roads. | 5 | C050-C069 | Antler Lake | 0 | 44133 |  | 37 | 44133 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting604620201021-10Labourer - General - After Jan 103180 | Corbiere and Sons Contracting604620201021-10Labourer - General - After Jan 103180Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 180 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6049 | 20201021-13 | 53510504 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 21 | Dynamic | 98.61 | 0 |  |  | 2761.08 | 358.9404 | 3120.0204 | 2020-10-21 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gerrit on excavator loading rock trucks. Chris hauled for gravel haul remainder of day to C-084. Mike hauling between KM2-KM4.Dozers both spreading gravel all day. | 5 | C076-C116 | Cook Lake | 0 | 44133 |  | 37 | 44133 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting604920201021-13Dozer D6 or equal- After Jan 10212761.08 | Corbiere and Sons Contracting604920201021-13Dozer D6 or equal- After Jan 10212761.08Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 2761.08 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6049 | 20201021-13 | 53510504 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10.5 | Dynamic | 110.22 | 0 |  |  | 1543.08 | 200.6004 | 1743.6804 | 2020-10-21 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gerrit on excavator loading rock trucks. Chris hauled for gravel haul remainder of day to C-084. Mike hauling between KM2-KM4.Dozers both spreading gravel all day. | 5 | C076-C116 | Cook Lake | 0 | 44133 |  | 37 | 44133 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting604920201021-13Excavator - 36 ton- After Jan 1010.51543.08 | Corbiere and Sons Contracting604920201021-13Excavator - 36 ton- After Jan 1010.51543.08Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1543.08 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6049 | 20201021-13 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-10-21 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gerrit on excavator loading rock trucks. Chris hauled for gravel haul remainder of day to C-084. Mike hauling between KM2-KM4.Dozers both spreading gravel all day. | 5 | C076-C116 | Cook Lake | 0 | 44133 |  | 37 | 44133 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting604920201021-13Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting604920201021-13Light Truck - Pick up- After Jan 102487.5Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6049 | 20201021-13 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 17.5 | Dynamic | 103.54 | 0 |  |  | 2415.875 | 314.0638 | 2729.9387 | 2020-10-21 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gerrit on excavator loading rock trucks. Chris hauled for gravel haul remainder of day to C-084. Mike hauling between KM2-KM4.Dozers both spreading gravel all day. | 5 | C076-C116 | Cook Lake | 0 | 44133 |  | 37 | 44133 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting604920201021-13Rock Truck - 30 Ton- After Jan 1017.52415.875 | Corbiere and Sons Contracting604920201021-13Rock Truck - 30 Ton- After Jan 1017.52415.875Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 2415.875 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6049 | 20201021-13 | 53510504 | Access | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2020-10-21 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gerrit on excavator loading rock trucks. Chris hauled for gravel haul remainder of day to C-084. Mike hauling between KM2-KM4.Dozers both spreading gravel all day. | 5 | C076-C116 | Cook Lake | 0 | 44133 |  | 37 | 44133 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting604920201021-13L.O.A.51050 | Corbiere and Sons Contracting604920201021-13L.O.A.51050Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6049 | 20201021-13 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 34.5 | HR |  |  | 75 | 0 | 2587.5 | 336.375 | 2923.875 | 2020-10-21 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gerrit on excavator loading rock trucks. Chris hauled for gravel haul remainder of day to C-084. Mike hauling between KM2-KM4.Dozers both spreading gravel all day. | 5 | C076-C116 | Cook Lake | 0 | 44133 |  | 37 | 44133 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting604920201021-13Operator - Principle - After Jan 1034.52587.5 | Corbiere and Sons Contracting604920201021-13Operator - Principle - After Jan 1034.52587.5Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 2587.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6049 | 20201021-13 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 19 | HR |  |  | 70 | 0 | 1330 | 172.9 | 1502.9 | 2020-10-21 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gerrit on excavator loading rock trucks. Chris hauled for gravel haul remainder of day to C-084. Mike hauling between KM2-KM4.Dozers both spreading gravel all day. | 5 | C076-C116 | Cook Lake | 0 | 44133 |  | 37 | 44133 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting604920201021-13Driver - AZ - After Jan 10191330 | Corbiere and Sons Contracting604920201021-13Driver - AZ - After Jan 10191330Inv#068 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1330 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6050 | 20201021-14 | 53510503 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 8 | Dynamic | 110.22 | 0 |  |  | 1175.68 | 152.8384 | 1328.5184 | 2020-10-21 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Putting down 60m of corduroy | 5 | C076-C116 | Cook Lake | 0 | 44133 |  | 37 | 44133 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting605020201021-14Excavator - 36 ton- After Jan 1081175.68 | Corbiere and Sons Contracting605020201021-14Excavator - 36 ton- After Jan 1081175.68Inv#068 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 1175.68 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6050 | 20201021-14 | 53510503 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-10-21 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Putting down 60m of corduroy | 5 | C076-C116 | Cook Lake | 0 | 44133 |  | 37 | 44133 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting605020201021-14L.O.A.1210 | Corbiere and Sons Contracting605020201021-14L.O.A.1210Inv#068 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6050 | 20201021-14 | 53510503 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 8 | HR |  |  | 75 | 0 | 600 | 78 | 678 | 2020-10-21 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Putting down 60m of corduroy | 5 | C076-C116 | Cook Lake | 0 | 44133 |  | 37 | 44133 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting605020201021-14Operator - Principle - After Jan 108600 | Corbiere and Sons Contracting605020201021-14Operator - Principle - After Jan 108600Inv#068 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6056 | 20201021-20 | 53510312 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10 | Dynamic | 98.61 | 0 |  |  | 1314.8 | 170.924 | 1485.724 | 2020-10-21 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-09, EX-08 and DZ-05 cleared water and ditched to provide access. | 3 | B078-B084 | Red Rock Road No. 7 | 0 | 44133 |  | 50 | 44133 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting605620201021-20Dozer D6 or equal- After Jan 10101314.8 | Corbiere and Sons Contracting605620201021-20Dozer D6 or equal- After Jan 10101314.8Inv#068 | [5 empty] | 1 | 1314.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6056 | 20201021-20 | 53510312 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10 | Dynamic | 103.84 | 0 |  |  | 1384.5 | 179.985 | 1564.485 | 2020-10-21 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-09, EX-08 and DZ-05 cleared water and ditched to provide access. | 3 | B078-B084 | Red Rock Road No. 7 | 0 | 44133 |  | 50 | 44133 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting605620201021-20Excavator - 30 ton- After Jan 10101384.5 | Corbiere and Sons Contracting605620201021-20Excavator - 30 ton- After Jan 10101384.5Inv#068 | [5 empty] | 1 | 1384.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6056 | 20201021-20 | 53510312 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10 | Dynamic | 110.22 | 0 |  |  | 1469.6 | 191.048 | 1660.648 | 2020-10-21 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-09, EX-08 and DZ-05 cleared water and ditched to provide access. | 3 | B078-B084 | Red Rock Road No. 7 | 0 | 44133 |  | 50 | 44133 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting605620201021-20Excavator - 36 ton- After Jan 10101469.6 | Corbiere and Sons Contracting605620201021-20Excavator - 36 ton- After Jan 10101469.6Inv#068 | [5 empty] | 1 | 1469.6 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6056 | 20201021-20 | 53510312 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 20 | HR | 9.16 | 0 |  |  | 244.2 | 31.746 | 275.946 | 2020-10-21 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-09, EX-08 and DZ-05 cleared water and ditched to provide access. | 3 | B078-B084 | Red Rock Road No. 7 | 0 | 44133 |  | 50 | 44133 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting605620201021-20Excavator Thumb - 30 - 50 ton- After Jan 1020244.2 | Corbiere and Sons Contracting605620201021-20Excavator Thumb - 30 - 50 ton- After Jan 1020244.2Inv#068 | [5 empty] | 1 | 244.2 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6056 | 20201021-20 | 53510312 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 4 | DAY | 182.81 | 0 |  |  | 975 | 126.75 | 1101.75 | 2020-10-21 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-09, EX-08 and DZ-05 cleared water and ditched to provide access. | 3 | B078-B084 | Red Rock Road No. 7 | 0 | 44133 |  | 50 | 44133 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting605620201021-20Light Truck - Pick up- After Jan 104975 | Corbiere and Sons Contracting605620201021-20Light Truck - Pick up- After Jan 104975Inv#068 | [5 empty] | 1 | 975 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6056 | 20201021-20 | 53510312 | Access | 0 | Foreman | 95 | 6 | HR |  |  | 95 | 0 | 570 | 74.1 | 644.1 | 2020-10-21 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-09, EX-08 and DZ-05 cleared water and ditched to provide access. | 3 | B078-B084 | Red Rock Road No. 7 | 0 | 44133 |  | 50 | 44133 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting605620201021-20Foreman6570 | Corbiere and Sons Contracting605620201021-20Foreman6570Inv#068 | [5 empty] | 1 | 570 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6056 | 20201021-20 | 53510312 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 33 | HR |  |  | 75 | 0 | 2475 | 321.75 | 2796.75 | 2020-10-21 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-09, EX-08 and DZ-05 cleared water and ditched to provide access. | 3 | B078-B084 | Red Rock Road No. 7 | 0 | 44133 |  | 50 | 44133 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting605620201021-20Operator - Principle - After Jan 10332475 | Corbiere and Sons Contracting605620201021-20Operator - Principle - After Jan 10332475Inv#068 | [5 empty] | 1 | 2475 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6061 | 20201021-25 | 53510412 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 7 | Dynamic | 98.61 | 0 |  |  | 920.36 | 119.6468 | 1040.0068 | 2020-10-21 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-07 unloaded culverts and walked mats in and ditched, DZ-04 removed snow and made run off ditches | 4 | B194-B210 | Little Gravel River Road | 0 | 44133 |  | 50 | 44133 | [5 empty] | Wes Seminowich | 04 | Corbiere and Sons Contracting606120201021-25Dozer D6 or equal- After Jan 107920.36 | Corbiere and Sons Contracting606120201021-25Dozer D6 or equal- After Jan 107920.36Inv#068 | [5 empty] | 1 | 920.36 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6061 | 20201021-25 | 53510412 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 3 | Dynamic | 110.22 | 0 |  |  | 440.88 | 57.3144 | 498.1944 | 2020-10-21 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-07 unloaded culverts and walked mats in and ditched, DZ-04 removed snow and made run off ditches | 4 | B194-B210 | Little Gravel River Road | 0 | 44133 |  | 50 | 44133 | [5 empty] | Wes Seminowich | 04 | Corbiere and Sons Contracting606120201021-25Excavator - 36 ton- After Jan 103440.88 | Corbiere and Sons Contracting606120201021-25Excavator - 36 ton- After Jan 103440.88Inv#068 | [5 empty] | 1 | 440.88 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6061 | 20201021-25 | 53510412 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 3 | HR | 9.16 | 0 |  |  | 36.63 | 4.7619 | 41.3919 | 2020-10-21 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-07 unloaded culverts and walked mats in and ditched, DZ-04 removed snow and made run off ditches | 4 | B194-B210 | Little Gravel River Road | 0 | 44133 |  | 50 | 44133 | [5 empty] | Wes Seminowich | 04 | Corbiere and Sons Contracting606120201021-25Excavator Thumb - 30 - 50 ton- After Jan 10336.63 | Corbiere and Sons Contracting606120201021-25Excavator Thumb - 30 - 50 ton- After Jan 10336.63Inv#068 | [5 empty] | 1 | 36.63 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6061 | 20201021-25 | 53510412 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-10-21 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-07 unloaded culverts and walked mats in and ditched, DZ-04 removed snow and made run off ditches | 4 | B194-B210 | Little Gravel River Road | 0 | 44133 |  | 50 | 44133 | [5 empty] | Wes Seminowich | 04 | Corbiere and Sons Contracting606120201021-25Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting606120201021-25Light Truck - Pick up- After Jan 101243.75Inv#068 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6061 | 20201021-25 | 53510412 | Access | 0 | Foreman | 95 | 6 | HR |  |  | 95 | 0 | 570 | 74.1 | 644.1 | 2020-10-21 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-07 unloaded culverts and walked mats in and ditched, DZ-04 removed snow and made run off ditches | 4 | B194-B210 | Little Gravel River Road | 0 | 44133 |  | 50 | 44133 | [5 empty] | Wes Seminowich | 04 | Corbiere and Sons Contracting606120201021-25Foreman6570 | Corbiere and Sons Contracting606120201021-25Foreman6570Inv#068 | [5 empty] | 1 | 570 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6061 | 20201021-25 | 53510412 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 20 | HR |  |  | 75 | 0 | 1500 | 195 | 1695 | 2020-10-21 | 1 | Inv#068 | 44134 | 118 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-07 unloaded culverts and walked mats in and ditched, DZ-04 removed snow and made run off ditches | 4 | B194-B210 | Little Gravel River Road | 0 | 44133 |  | 50 | 44133 | [5 empty] | Wes Seminowich | 04 | Corbiere and Sons Contracting606120201021-25Operator - Principle - After Jan 10201500 | Corbiere and Sons Contracting606120201021-25Operator - Principle - After Jan 10201500Inv#068 | [5 empty] | 1 | 1500 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6111 | 20201022-12 | 53510503 | Access | 0 | Skidder | 171 | 5 | HR | 128.25 | 0 |  |  | 855 | 111.15 | 966.15 | 2020-10-22 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brought corduroy and put down corduroy from C-078 | 5 | C076-C092 | Cook Lake | 0 | 44134 |  | 37 | 44135 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting611120201022-12Skidder 5855 | Corbiere and Sons Contracting611120201022-12Skidder 5855Inv#070 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 855 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6111 | 20201022-12 | 53510503 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 3 | Dynamic | 103.84 | 0 |  |  | 415.35 | 53.9955 | 469.3455 | 2020-10-22 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brought corduroy and put down corduroy from C-078 | 5 | C076-C092 | Cook Lake | 0 | 44134 |  | 37 | 44135 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting611120201022-12Excavator - 30 ton- After Jan 103415.35 | Corbiere and Sons Contracting611120201022-12Excavator - 30 ton- After Jan 103415.35Inv#070 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 415.35 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6111 | 20201022-12 | 53510503 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 3 | HR | 9.16 | 0 |  |  | 36.63 | 4.7619 | 41.3919 | 2020-10-22 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brought corduroy and put down corduroy from C-078 | 5 | C076-C092 | Cook Lake | 0 | 44134 |  | 37 | 44135 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting611120201022-12Excavator Thumb - 30 - 50 ton- After Jan 10336.63 | Corbiere and Sons Contracting611120201022-12Excavator Thumb - 30 - 50 ton- After Jan 10336.63Inv#070 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 36.63 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6111 | 20201022-12 | 53510503 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-10-22 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brought corduroy and put down corduroy from C-078 | 5 | C076-C092 | Cook Lake | 0 | 44134 |  | 37 | 44135 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting611120201022-12Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting611120201022-12Light Truck - Pick up- After Jan 101243.75Inv#070 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6111 | 20201022-12 | 53510503 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-10-22 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brought corduroy and put down corduroy from C-078 | 5 | C076-C092 | Cook Lake | 0 | 44134 |  | 37 | 44135 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting611120201022-12L.O.A.1210 | Corbiere and Sons Contracting611120201022-12L.O.A.1210Inv#070 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6111 | 20201022-12 | 53510503 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 10 | HR |  |  | 75 | 0 | 750 | 97.5 | 847.5 | 2020-10-22 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Brought corduroy and put down corduroy from C-078 | 5 | C076-C092 | Cook Lake | 0 | 44134 |  | 37 | 44135 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting611120201022-12Operator - Principle - After Jan 1010750 | Corbiere and Sons Contracting611120201022-12Operator - Principle - After Jan 1010750Inv#070 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 750 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6112 | 20201022-13 | 53510504 | Access | 0 | Loader JD 524 to 624 or equal | 99 | 6 | HR | 74.25 | 0 |  |  | 594 | 77.22 | 671.22 | 2020-10-22 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator and loader loading rock trucks from KM3-KM4 - Rock trucks hauling all day, dozers spreading gravel from C-080-C-084 and C-094. | 5 | C076-C116 | Cook Lake | 0 | 44134 |  | 37 | 44135 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting611220201022-13Loader JD 524 to 624 or equal6594 | Corbiere and Sons Contracting611220201022-13Loader JD 524 to 624 or equal6594Inv#070 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 594 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6112 | 20201022-13 | 53510504 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 21 | Dynamic | 98.61 | 0 |  |  | 2761.08 | 358.9404 | 3120.0204 | 2020-10-22 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator and loader loading rock trucks from KM3-KM4 - Rock trucks hauling all day, dozers spreading gravel from C-080-C-084 and C-094. | 5 | C076-C116 | Cook Lake | 0 | 44134 |  | 37 | 44135 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting611220201022-13Dozer D6 or equal- After Jan 10212761.08 | Corbiere and Sons Contracting611220201022-13Dozer D6 or equal- After Jan 10212761.08Inv#070 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 2761.08 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6112 | 20201022-13 | 53510504 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10.5 | Dynamic | 110.22 | 0 |  |  | 1543.08 | 200.6004 | 1743.6804 | 2020-10-22 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator and loader loading rock trucks from KM3-KM4 - Rock trucks hauling all day, dozers spreading gravel from C-080-C-084 and C-094. | 5 | C076-C116 | Cook Lake | 0 | 44134 |  | 37 | 44135 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting611220201022-13Excavator - 36 ton- After Jan 1010.51543.08 | Corbiere and Sons Contracting611220201022-13Excavator - 36 ton- After Jan 1010.51543.08Inv#070 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1543.08 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6112 | 20201022-13 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-10-22 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator and loader loading rock trucks from KM3-KM4 - Rock trucks hauling all day, dozers spreading gravel from C-080-C-084 and C-094. | 5 | C076-C116 | Cook Lake | 0 | 44134 |  | 37 | 44135 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting611220201022-13Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting611220201022-13Light Truck - Pick up- After Jan 102487.5Inv#070 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6112 | 20201022-13 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 28 | Dynamic | 103.54 | 0 |  |  | 3865.4 | 502.502 | 4367.902 | 2020-10-22 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator and loader loading rock trucks from KM3-KM4 - Rock trucks hauling all day, dozers spreading gravel from C-080-C-084 and C-094. | 5 | C076-C116 | Cook Lake | 0 | 44134 |  | 37 | 44135 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting611220201022-13Rock Truck - 30 Ton- After Jan 10283865.4 | Corbiere and Sons Contracting611220201022-13Rock Truck - 30 Ton- After Jan 10283865.4Inv#070 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 3865.4 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6112 | 20201022-13 | 53510504 | Access | 0 | L.O.A. | 210 | 8 | DAY |  |  |  | 0 | 1680 | 218.4 | 1898.4 | 2020-10-22 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator and loader loading rock trucks from KM3-KM4 - Rock trucks hauling all day, dozers spreading gravel from C-080-C-084 and C-094. | 5 | C076-C116 | Cook Lake | 0 | 44134 |  | 37 | 44135 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting611220201022-13L.O.A.81680 | Corbiere and Sons Contracting611220201022-13L.O.A.81680Inv#070 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1680 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6112 | 20201022-13 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 58 | HR |  |  | 75 | 0 | 4350 | 565.5 | 4915.5 | 2020-10-22 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator and loader loading rock trucks from KM3-KM4 - Rock trucks hauling all day, dozers spreading gravel from C-080-C-084 and C-094. | 5 | C076-C116 | Cook Lake | 0 | 44134 |  | 37 | 44135 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting611220201022-13Operator - Principle - After Jan 10584350 | Corbiere and Sons Contracting611220201022-13Operator - Principle - After Jan 10584350Inv#070 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 4350 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6112 | 20201022-13 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 19 | HR |  |  | 70 | 0 | 1330 | 172.9 | 1502.9 | 2020-10-22 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator and loader loading rock trucks from KM3-KM4 - Rock trucks hauling all day, dozers spreading gravel from C-080-C-084 and C-094. | 5 | C076-C116 | Cook Lake | 0 | 44134 |  | 37 | 44135 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting611220201022-13Driver - AZ - After Jan 10191330 | Corbiere and Sons Contracting611220201022-13Driver - AZ - After Jan 10191330Inv#070 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1330 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6113 | 20201022-14 | 53510502 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 3 | Dynamic | 91.79 | 0 |  |  | 367.17 | 47.7321 | 414.9021 | 2020-10-22 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float went to Marathon yard and brought 4 rolls of geo to White Sands. | 5 | C070-C075 | White Sand | 0 | 44134 |  | 37 | 44135 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting611320201022-14Tractor Trailer - 60 Ton- After Jan 103367.17 | Corbiere and Sons Contracting611320201022-14Tractor Trailer - 60 Ton- After Jan 103367.17Inv#070 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 367.17 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6113 | 20201022-14 | 53510502 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-10-22 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float went to Marathon yard and brought 4 rolls of geo to White Sands. | 5 | C070-C075 | White Sand | 0 | 44134 |  | 37 | 44135 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting611320201022-14L.O.A.1210 | Corbiere and Sons Contracting611320201022-14L.O.A.1210Inv#070 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6113 | 20201022-14 | 53510502 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 3 | HR |  |  | 70 | 0 | 210 | 27.3 | 237.3 | 2020-10-22 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float went to Marathon yard and brought 4 rolls of geo to White Sands. | 5 | C070-C075 | White Sand | 0 | 44134 |  | 37 | 44135 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting611320201022-14Driver - AZ - After Jan 103210 | Corbiere and Sons Contracting611320201022-14Driver - AZ - After Jan 103210Inv#070 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6116 | 20201022-16 | 53510504 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 8 | Dynamic | 98.61 | 0 |  |  | 1051.84 | 136.7392 | 1188.5792 | 2020-10-22 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel hauling and spread - 400m completed | 5 | C050-C069 | Antler Lake | 0 | 44134 |  | 37 | 44135 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting611620201022-16Dozer D6 or equal- After Jan 1081051.84 | Corbiere and Sons Contracting611620201022-16Dozer D6 or equal- After Jan 1081051.84Inv#070 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1051.84 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6116 | 20201022-16 | 53510504 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 8 | Dynamic | 103.84 | 0 |  |  | 1107.6 | 143.988 | 1251.588 | 2020-10-22 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel hauling and spread - 400m completed | 5 | C050-C069 | Antler Lake | 0 | 44134 |  | 37 | 44135 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting611620201022-16Excavator - 30 ton- After Jan 1081107.6 | Corbiere and Sons Contracting611620201022-16Excavator - 30 ton- After Jan 1081107.6Inv#070 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1107.6 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6116 | 20201022-16 | 53510504 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 8 | HR | 9.16 | 0 |  |  | 97.68 | 12.6984 | 110.3784 | 2020-10-22 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel hauling and spread - 400m completed | 5 | C050-C069 | Antler Lake | 0 | 44134 |  | 37 | 44135 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting611620201022-16Excavator Thumb - 30 - 50 ton- After Jan 10897.68 | Corbiere and Sons Contracting611620201022-16Excavator Thumb - 30 - 50 ton- After Jan 10897.68Inv#070 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 97.68 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6116 | 20201022-16 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-10-22 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel hauling and spread - 400m completed | 5 | C050-C069 | Antler Lake | 0 | 44134 |  | 37 | 44135 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting611620201022-16Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting611620201022-16Light Truck - Pick up- After Jan 102487.5Inv#070 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6116 | 20201022-16 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 8 | Dynamic | 103.54 | 0 |  |  | 1104.4 | 143.572 | 1247.972 | 2020-10-22 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel hauling and spread - 400m completed | 5 | C050-C069 | Antler Lake | 0 | 44134 |  | 37 | 44135 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting611620201022-16Rock Truck - 30 Ton- After Jan 1081104.4 | Corbiere and Sons Contracting611620201022-16Rock Truck - 30 Ton- After Jan 1081104.4Inv#070 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1104.4 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6116 | 20201022-16 | 53510504 | Access | 0 | Foreman | 95 | 6 | HR |  |  | 95 | 0 | 570 | 74.1 | 644.1 | 2020-10-22 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel hauling and spread - 400m completed | 5 | C050-C069 | Antler Lake | 0 | 44134 |  | 37 | 44135 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting611620201022-16Foreman6570 | Corbiere and Sons Contracting611620201022-16Foreman6570Inv#070 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 570 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6116 | 20201022-16 | 53510504 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2020-10-22 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel hauling and spread - 400m completed | 5 | C050-C069 | Antler Lake | 0 | 44134 |  | 37 | 44135 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting611620201022-16L.O.A.4840 | Corbiere and Sons Contracting611620201022-16L.O.A.4840Inv#070 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6116 | 20201022-16 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 16 | HR |  |  | 75 | 0 | 1200 | 156 | 1356 | 2020-10-22 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel hauling and spread - 400m completed | 5 | C050-C069 | Antler Lake | 0 | 44134 |  | 37 | 44135 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting611620201022-16Operator - Principle - After Jan 10161200 | Corbiere and Sons Contracting611620201022-16Operator - Principle - After Jan 10161200Inv#070 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1200 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6116 | 20201022-16 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 8 | HR |  |  | 70 | 0 | 560 | 72.8 | 632.8 | 2020-10-22 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel hauling and spread - 400m completed | 5 | C050-C069 | Antler Lake | 0 | 44134 |  | 37 | 44135 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting611620201022-16Driver - AZ - After Jan 108560 | Corbiere and Sons Contracting611620201022-16Driver - AZ - After Jan 108560Inv#070 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 560 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6120 | 20201022-20 | 53510312 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2020-10-22 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ditched and woked on shoofly B-075 - B-077 | 3 | B078-B084 | Red Rock Road No. 7 | 0 | 44134 |  | 50 | 44135 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting612020201022-20Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting612020201022-20Excavator - 30 ton- After Jan 10111522.95Inv#070 | [5 empty] | 1 | 1522.95 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6120 | 20201022-20 | 53510312 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2020-10-22 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ditched and woked on shoofly B-075 - B-077 | 3 | B078-B084 | Red Rock Road No. 7 | 0 | 44134 |  | 50 | 44135 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting612020201022-20Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting612020201022-20Excavator Thumb - 30 - 50 ton- After Jan 1011134.31Inv#070 | [5 empty] | 1 | 134.31 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6120 | 20201022-20 | 53510312 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-10-22 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ditched and woked on shoofly B-075 - B-077 | 3 | B078-B084 | Red Rock Road No. 7 | 0 | 44134 |  | 50 | 44135 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting612020201022-20Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting612020201022-20Light Truck - Pick up- After Jan 101243.75Inv#070 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6120 | 20201022-20 | 53510312 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2020-10-22 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ditched and woked on shoofly B-075 - B-077 | 3 | B078-B084 | Red Rock Road No. 7 | 0 | 44134 |  | 50 | 44135 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting612020201022-20Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting612020201022-20Operator - Principle - After Jan 1012900Inv#070 | [5 empty] | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6124 | 20201022-24 | 53510412 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 4 | Dynamic | 110.22 | 0 |  |  | 587.84 | 76.4192 | 664.2592 | 2020-10-22 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Maintenance on road under HONE line near B-204 - B-205 | 4 | B204-B210 | Little Gravel River Rd - E | 0 | 44134 |  | 50 | 44135 | [5 empty] | Wes Seminowich | 04 | Corbiere and Sons Contracting612420201022-24Excavator - 36 ton- After Jan 104587.84 | Corbiere and Sons Contracting612420201022-24Excavator - 36 ton- After Jan 104587.84Inv#070 | [5 empty] | 1 | 587.84 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6124 | 20201022-24 | 53510412 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 4 | HR | 9.16 | 0 |  |  | 48.84 | 6.3492 | 55.1892 | 2020-10-22 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Maintenance on road under HONE line near B-204 - B-205 | 4 | B204-B210 | Little Gravel River Rd - E | 0 | 44134 |  | 50 | 44135 | [5 empty] | Wes Seminowich | 04 | Corbiere and Sons Contracting612420201022-24Excavator Thumb - 30 - 50 ton- After Jan 10448.84 | Corbiere and Sons Contracting612420201022-24Excavator Thumb - 30 - 50 ton- After Jan 10448.84Inv#070 | [5 empty] | 1 | 48.84 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6124 | 20201022-24 | 53510412 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 4 | HR |  |  | 75 | 0 | 300 | 39 | 339 | 2020-10-22 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Maintenance on road under HONE line near B-204 - B-205 | 4 | B204-B210 | Little Gravel River Rd - E | 0 | 44134 |  | 50 | 44135 | [5 empty] | Wes Seminowich | 04 | Corbiere and Sons Contracting612420201022-24Operator - Principle - After Jan 104300 | Corbiere and Sons Contracting612420201022-24Operator - Principle - After Jan 104300Inv#070 | [5 empty] | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6136 | 20201023-10 | 53510312 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10 | Dynamic | 98.61 | 0 |  |  | 1314.8 | 170.924 | 1485.724 | 2020-10-23 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Cleared off wet road and bridge approaches and kept road passable for Valard traffic. | 3 | B078-B084 | Red Rock Road No. 7 | 0 | 44135 |  | 50 | 44135 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting613620201023-10Dozer D6 or equal- After Jan 10101314.8 | Corbiere and Sons Contracting613620201023-10Dozer D6 or equal- After Jan 10101314.8Inv#070 | [5 empty] | 1 | 1314.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6136 | 20201023-10 | 53510312 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10 | Dynamic | 103.84 | 0 |  |  | 1384.5 | 179.985 | 1564.485 | 2020-10-23 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Cleared off wet road and bridge approaches and kept road passable for Valard traffic. | 3 | B078-B084 | Red Rock Road No. 7 | 0 | 44135 |  | 50 | 44135 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting613620201023-10Excavator - 30 ton- After Jan 10101384.5 | Corbiere and Sons Contracting613620201023-10Excavator - 30 ton- After Jan 10101384.5Inv#070 | [5 empty] | 1 | 1384.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6136 | 20201023-10 | 53510312 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10 | Dynamic | 110.22 | 0 |  |  | 1469.6 | 191.048 | 1660.648 | 2020-10-23 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Cleared off wet road and bridge approaches and kept road passable for Valard traffic. | 3 | B078-B084 | Red Rock Road No. 7 | 0 | 44135 |  | 50 | 44135 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting613620201023-10Excavator - 36 ton- After Jan 10101469.6 | Corbiere and Sons Contracting613620201023-10Excavator - 36 ton- After Jan 10101469.6Inv#070 | [5 empty] | 1 | 1469.6 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6136 | 20201023-10 | 53510312 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 20 | HR | 9.16 | 0 |  |  | 244.2 | 31.746 | 275.946 | 2020-10-23 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Cleared off wet road and bridge approaches and kept road passable for Valard traffic. | 3 | B078-B084 | Red Rock Road No. 7 | 0 | 44135 |  | 50 | 44135 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting613620201023-10Excavator Thumb - 30 - 50 ton- After Jan 1020244.2 | Corbiere and Sons Contracting613620201023-10Excavator Thumb - 30 - 50 ton- After Jan 1020244.2Inv#070 | [5 empty] | 1 | 244.2 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6136 | 20201023-10 | 53510312 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-10-23 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Cleared off wet road and bridge approaches and kept road passable for Valard traffic. | 3 | B078-B084 | Red Rock Road No. 7 | 0 | 44135 |  | 50 | 44135 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting613620201023-10Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting613620201023-10Light Truck - Pick up- After Jan 102487.5Inv#070 | [5 empty] | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6136 | 20201023-10 | 53510312 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 33 | HR |  |  | 75 | 0 | 2475 | 321.75 | 2796.75 | 2020-10-23 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Cleared off wet road and bridge approaches and kept road passable for Valard traffic. | 3 | B078-B084 | Red Rock Road No. 7 | 0 | 44135 |  | 50 | 44135 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting613620201023-10Operator - Principle - After Jan 10332475 | Corbiere and Sons Contracting613620201023-10Operator - Principle - After Jan 10332475Inv#070 | [5 empty] | 1 | 2475 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6139 | 20201023-13 | 53510412 | Access | 0 | Labourer - General - After Jan 10 | 60 | 10 | HR |  |  | 60 | 0 | 600 | 78 | 678 | 2020-10-23 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Labourers shovelled entrances | 4 | B194-B210 | Little Gravel River Rd | 0 | 44135 |  | 50 | 44135 | [5 empty] | Wes Seminowich | 04 | Corbiere and Sons Contracting613920201023-13Labourer - General - After Jan 1010600 | Corbiere and Sons Contracting613920201023-13Labourer - General - After Jan 1010600Inv#070 | [5 empty] | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6240 | 20201023-25 | 53510503 | Access | 0 | Skidder | 171 | 11 | HR | 128.25 | 0 |  |  | 1881 | 244.53 | 2125.53 | 2020-10-23 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Putting down Corduroy from C078 and C093 | 5 | C093-C116 | Cook Lake | 0 | 44139 |  | 52 | 44140 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting624020201023-25Skidder 111881 | Corbiere and Sons Contracting624020201023-25Skidder 111881Inv#070 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 1881 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6240 | 20201023-25 | 53510503 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-10-23 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Putting down Corduroy from C078 and C093 | 5 | C093-C116 | Cook Lake | 0 | 44139 |  | 52 | 44140 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting624020201023-25Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting624020201023-25Light Truck - Pick up- After Jan 101243.75Inv#070 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6240 | 20201023-25 | 53510503 | Access | 0 | Foreman | 95 | 4 | HR |  |  | 95 | 0 | 380 | 49.4 | 429.4 | 2020-10-23 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Putting down Corduroy from C078 and C093 | 5 | C093-C116 | Cook Lake | 0 | 44139 |  | 52 | 44140 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting624020201023-25Foreman4380 | Corbiere and Sons Contracting624020201023-25Foreman4380Inv#070 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6240 | 20201023-25 | 53510503 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-10-23 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Putting down Corduroy from C078 and C093 | 5 | C093-C116 | Cook Lake | 0 | 44139 |  | 52 | 44140 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting624020201023-25L.O.A.2420 | Corbiere and Sons Contracting624020201023-25L.O.A.2420Inv#070 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6240 | 20201023-25 | 53510503 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-10-23 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Putting down Corduroy from C078 and C093 | 5 | C093-C116 | Cook Lake | 0 | 44139 |  | 52 | 44140 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting624020201023-25Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting624020201023-25Operator - Principle - After Jan 1011.5862.5Inv#070 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6241 | 20201023-26 | 53510504 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 21 | Dynamic | 98.61 | 0 |  |  | 2761.08 | 358.9404 | 3120.0204 | 2020-10-23 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel hauling and spreading in various areas from Km1 to C095 | 5 | C093-C116 | Cook Lake | 0 | 44139 |  | 52 | 44140 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting624120201023-26Dozer D6 or equal- After Jan 10212761.08 | Corbiere and Sons Contracting624120201023-26Dozer D6 or equal- After Jan 10212761.08Inv#070 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 2761.08 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6241 | 20201023-26 | 53510504 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10.5 | Dynamic | 103.84 | 0 |  |  | 1453.725 | 188.9843 | 1642.7093 | 2020-10-23 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel hauling and spreading in various areas from Km1 to C095 | 5 | C093-C116 | Cook Lake | 0 | 44139 |  | 52 | 44140 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting624120201023-26Excavator - 30 ton- After Jan 1010.51453.725 | Corbiere and Sons Contracting624120201023-26Excavator - 30 ton- After Jan 1010.51453.725Inv#070 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1453.725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6241 | 20201023-26 | 53510504 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10.5 | HR | 9.16 | 0 |  |  | 128.205 | 16.6667 | 144.8716 | 2020-10-23 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel hauling and spreading in various areas from Km1 to C095 | 5 | C093-C116 | Cook Lake | 0 | 44139 |  | 52 | 44140 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting624120201023-26Excavator Thumb - 30 - 50 ton- After Jan 1010.5128.205 | Corbiere and Sons Contracting624120201023-26Excavator Thumb - 30 - 50 ton- After Jan 1010.5128.205Inv#070 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 128.205 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6241 | 20201023-26 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-10-23 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel hauling and spreading in various areas from Km1 to C095 | 5 | C093-C116 | Cook Lake | 0 | 44139 |  | 52 | 44140 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting624120201023-26Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting624120201023-26Light Truck - Pick up- After Jan 102487.5Inv#070 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6241 | 20201023-26 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 31.5 | Dynamic | 103.54 | 0 |  |  | 4348.575 | 565.3148 | 4913.8898 | 2020-10-23 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel hauling and spreading in various areas from Km1 to C095 | 5 | C093-C116 | Cook Lake | 0 | 44139 |  | 52 | 44140 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting624120201023-26Rock Truck - 30 Ton- After Jan 1031.54348.575 | Corbiere and Sons Contracting624120201023-26Rock Truck - 30 Ton- After Jan 1031.54348.575Inv#070 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 4348.575 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6241 | 20201023-26 | 53510504 | Access | 0 | Foreman | 95 | 4 | HR |  |  | 95 | 0 | 380 | 49.4 | 429.4 | 2020-10-23 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel hauling and spreading in various areas from Km1 to C095 | 5 | C093-C116 | Cook Lake | 0 | 44139 |  | 52 | 44140 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting624120201023-26Foreman4380 | Corbiere and Sons Contracting624120201023-26Foreman4380Inv#070 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6241 | 20201023-26 | 53510504 | Access | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2020-10-23 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel hauling and spreading in various areas from Km1 to C095 | 5 | C093-C116 | Cook Lake | 0 | 44139 |  | 52 | 44140 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting624120201023-26L.O.A.61260 | Corbiere and Sons Contracting624120201023-26L.O.A.61260Inv#070 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6241 | 20201023-26 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 34.5 | HR |  |  | 75 | 0 | 2587.5 | 336.375 | 2923.875 | 2020-10-23 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel hauling and spreading in various areas from Km1 to C095 | 5 | C093-C116 | Cook Lake | 0 | 44139 |  | 52 | 44140 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting624120201023-26Operator - Principle - After Jan 1034.52587.5 | Corbiere and Sons Contracting624120201023-26Operator - Principle - After Jan 1034.52587.5Inv#070 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 2587.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6241 | 20201023-26 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 34.5 | HR |  |  | 70 | 0 | 2415 | 313.95 | 2728.95 | 2020-10-23 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel hauling and spreading in various areas from Km1 to C095 | 5 | C093-C116 | Cook Lake | 0 | 44139 |  | 52 | 44140 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting624120201023-26Driver - AZ - After Jan 1034.52415 | Corbiere and Sons Contracting624120201023-26Driver - AZ - After Jan 1034.52415Inv#070 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 2415 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6242 | 20201023-27 | 53510512 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10.5 | Dynamic | 110.22 | 0 |  |  | 1543.08 | 200.6004 | 1743.6804 | 2020-10-23 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dwayne on EX011 doing road maintenance between Km2-Km3 all day | 5 | C093-C116 | Cook Lake | 0 | 44139 |  | 52 | 44140 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting624220201023-27Excavator - 36 ton- After Jan 1010.51543.08 | Corbiere and Sons Contracting624220201023-27Excavator - 36 ton- After Jan 1010.51543.08Inv#070 | [5 empty] | 1 | 1543.08 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6242 | 20201023-27 | 53510512 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-10-23 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dwayne on EX011 doing road maintenance between Km2-Km3 all day | 5 | C093-C116 | Cook Lake | 0 | 44139 |  | 52 | 44140 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting624220201023-27Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting624220201023-27Light Truck - Pick up- After Jan 101243.75Inv#070 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6242 | 20201023-27 | 53510512 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-10-23 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dwayne on EX011 doing road maintenance between Km2-Km3 all day | 5 | C093-C116 | Cook Lake | 0 | 44139 |  | 52 | 44140 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting624220201023-27L.O.A.1210 | Corbiere and Sons Contracting624220201023-27L.O.A.1210Inv#070 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6242 | 20201023-27 | 53510512 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-10-23 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dwayne on EX011 doing road maintenance between Km2-Km3 all day | 5 | C093-C116 | Cook Lake | 0 | 44139 |  | 52 | 44140 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting624220201023-27Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting624220201023-27Operator - Principle - After Jan 1011.5862.5Inv#070 | [5 empty] | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6248 | 20201024-15 | 53510502 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 3 | Dynamic | 103.54 | 0 |  |  | 414.15 | 53.8395 | 467.9895 | 2020-10-24 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Joe and Rock Truck delivering geo to C069 | 5 | C069 | Antler Lake | 0 | 44139 |  | 52 | 44140 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting624820201024-15Rock Truck - 30 Ton- After Jan 103414.15 | Corbiere and Sons Contracting624820201024-15Rock Truck - 30 Ton- After Jan 103414.15Inv#070 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 414.15 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6248 | 20201024-15 | 53510502 | Access | 0 | Foreman | 95 | 2 | HR |  |  | 95 | 0 | 190 | 24.7 | 214.7 | 2020-10-24 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Joe and Rock Truck delivering geo to C069 | 5 | C069 | Antler Lake | 0 | 44139 |  | 52 | 44140 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting624820201024-15Foreman2190 | Corbiere and Sons Contracting624820201024-15Foreman2190Inv#070 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 190 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6248 | 20201024-15 | 53510502 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-10-24 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Joe and Rock Truck delivering geo to C069 | 5 | C069 | Antler Lake | 0 | 44139 |  | 52 | 44140 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting624820201024-15L.O.A.2420 | Corbiere and Sons Contracting624820201024-15L.O.A.2420Inv#070 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6248 | 20201024-15 | 53510502 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 3 | HR |  |  | 70 | 0 | 210 | 27.3 | 237.3 | 2020-10-24 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Joe and Rock Truck delivering geo to C069 | 5 | C069 | Antler Lake | 0 | 44139 |  | 52 | 44140 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting624820201024-15Driver - AZ - After Jan 103210 | Corbiere and Sons Contracting624820201024-15Driver - AZ - After Jan 103210Inv#070 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6251 | 20201024-18 | 53510503 | Access | 0 | Skidder | 171 | 11 | HR | 128.25 | 0 |  |  | 1881 | 244.53 | 2125.53 | 2020-10-24 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Putting down corduroy from C093 | 5 | C093 | Cook Lake | 0 | 44139 |  | 52 | 44140 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting625120201024-18Skidder 111881 | Corbiere and Sons Contracting625120201024-18Skidder 111881Inv#070 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 1881 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6251 | 20201024-18 | 53510503 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 4 | Dynamic | 110.22 | 0 |  |  | 587.84 | 76.4192 | 664.2592 | 2020-10-24 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Putting down corduroy from C093 | 5 | C093 | Cook Lake | 0 | 44139 |  | 52 | 44140 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting625120201024-18Excavator - 36 ton- After Jan 104587.84 | Corbiere and Sons Contracting625120201024-18Excavator - 36 ton- After Jan 104587.84Inv#070 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 587.84 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6251 | 20201024-18 | 53510503 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-10-24 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Putting down corduroy from C093 | 5 | C093 | Cook Lake | 0 | 44139 |  | 52 | 44140 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting625120201024-18Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting625120201024-18Light Truck - Pick up- After Jan 101243.75Inv#070 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6251 | 20201024-18 | 53510503 | Access | 0 | Foreman | 95 | 4 | HR |  |  | 95 | 0 | 380 | 49.4 | 429.4 | 2020-10-24 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Putting down corduroy from C093 | 5 | C093 | Cook Lake | 0 | 44139 |  | 52 | 44140 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting625120201024-18Foreman4380 | Corbiere and Sons Contracting625120201024-18Foreman4380Inv#070 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6251 | 20201024-18 | 53510503 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2020-10-24 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Putting down corduroy from C093 | 5 | C093 | Cook Lake | 0 | 44139 |  | 52 | 44140 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting625120201024-18L.O.A.3630 | Corbiere and Sons Contracting625120201024-18L.O.A.3630Inv#070 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6251 | 20201024-18 | 53510503 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 15.5 | HR |  |  | 75 | 0 | 1162.5 | 151.125 | 1313.625 | 2020-10-24 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Putting down corduroy from C093 | 5 | C093 | Cook Lake | 0 | 44139 |  | 52 | 44140 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting625120201024-18Operator - Principle - After Jan 1015.51162.5 | Corbiere and Sons Contracting625120201024-18Operator - Principle - After Jan 1015.51162.5Inv#070 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 1162.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6252 | 20201024-19 | 53510504 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 21 | Dynamic | 98.61 | 0 |  |  | 2761.08 | 358.9404 | 3120.0204 | 2020-10-24 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling and spreading between Km1-Km3 on Cooks Lake Road | 5 | C076-C116 | Cook Lake | 0 | 44139 |  | 52 | 44140 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting625220201024-19Dozer D6 or equal- After Jan 10212761.08 | Corbiere and Sons Contracting625220201024-19Dozer D6 or equal- After Jan 10212761.08Inv#070 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 2761.08 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6252 | 20201024-19 | 53510504 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10.5 | Dynamic | 103.84 | 0 |  |  | 1453.725 | 188.9843 | 1642.7093 | 2020-10-24 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling and spreading between Km1-Km3 on Cooks Lake Road | 5 | C076-C116 | Cook Lake | 0 | 44139 |  | 52 | 44140 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting625220201024-19Excavator - 30 ton- After Jan 1010.51453.725 | Corbiere and Sons Contracting625220201024-19Excavator - 30 ton- After Jan 1010.51453.725Inv#070 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1453.725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6252 | 20201024-19 | 53510504 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 6.5 | Dynamic | 110.22 | 0 |  |  | 955.24 | 124.1812 | 1079.4212 | 2020-10-24 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling and spreading between Km1-Km3 on Cooks Lake Road | 5 | C076-C116 | Cook Lake | 0 | 44139 |  | 52 | 44140 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting625220201024-19Excavator - 36 ton- After Jan 106.5955.24 | Corbiere and Sons Contracting625220201024-19Excavator - 36 ton- After Jan 106.5955.24Inv#070 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 955.24 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6252 | 20201024-19 | 53510504 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10.5 | HR | 9.16 | 0 |  |  | 128.205 | 16.6667 | 144.8716 | 2020-10-24 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling and spreading between Km1-Km3 on Cooks Lake Road | 5 | C076-C116 | Cook Lake | 0 | 44139 |  | 52 | 44140 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting625220201024-19Excavator Thumb - 30 - 50 ton- After Jan 1010.5128.205 | Corbiere and Sons Contracting625220201024-19Excavator Thumb - 30 - 50 ton- After Jan 1010.5128.205Inv#070 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 128.205 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6252 | 20201024-19 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2020-10-24 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling and spreading between Km1-Km3 on Cooks Lake Road | 5 | C076-C116 | Cook Lake | 0 | 44139 |  | 52 | 44140 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting625220201024-19Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting625220201024-19Light Truck - Pick up- After Jan 103731.25Inv#070 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 731.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6252 | 20201024-19 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 31.5 | Dynamic | 103.54 | 0 |  |  | 4348.575 | 565.3148 | 4913.8898 | 2020-10-24 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling and spreading between Km1-Km3 on Cooks Lake Road | 5 | C076-C116 | Cook Lake | 0 | 44139 |  | 52 | 44140 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting625220201024-19Rock Truck - 30 Ton- After Jan 1031.54348.575 | Corbiere and Sons Contracting625220201024-19Rock Truck - 30 Ton- After Jan 1031.54348.575Inv#070 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 4348.575 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6252 | 20201024-19 | 53510504 | Access | 0 | Foreman | 95 | 6 | HR |  |  | 95 | 0 | 570 | 74.1 | 644.1 | 2020-10-24 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling and spreading between Km1-Km3 on Cooks Lake Road | 5 | C076-C116 | Cook Lake | 0 | 44139 |  | 52 | 44140 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting625220201024-19Foreman6570 | Corbiere and Sons Contracting625220201024-19Foreman6570Inv#070 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 570 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6252 | 20201024-19 | 53510504 | Access | 0 | L.O.A. | 210 | 7 | DAY |  |  |  | 0 | 1470 | 191.1 | 1661.1 | 2020-10-24 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling and spreading between Km1-Km3 on Cooks Lake Road | 5 | C076-C116 | Cook Lake | 0 | 44139 |  | 52 | 44140 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting625220201024-19L.O.A.71470 | Corbiere and Sons Contracting625220201024-19L.O.A.71470Inv#070 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1470 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6252 | 20201024-19 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 38.5 | HR |  |  | 75 | 0 | 2887.5 | 375.375 | 3262.875 | 2020-10-24 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling and spreading between Km1-Km3 on Cooks Lake Road | 5 | C076-C116 | Cook Lake | 0 | 44139 |  | 52 | 44140 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting625220201024-19Operator - Principle - After Jan 1038.52887.5 | Corbiere and Sons Contracting625220201024-19Operator - Principle - After Jan 1038.52887.5Inv#070 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 2887.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6252 | 20201024-19 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 34.5 | HR |  |  | 70 | 0 | 2415 | 313.95 | 2728.95 | 2020-10-24 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling and spreading between Km1-Km3 on Cooks Lake Road | 5 | C076-C116 | Cook Lake | 0 | 44139 |  | 52 | 44140 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting625220201024-19Driver - AZ - After Jan 1034.52415 | Corbiere and Sons Contracting625220201024-19Driver - AZ - After Jan 1034.52415Inv#070 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 2415 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6256 | 20201024-23 | 53510502 | Access | 0 | Labourer - General - After Jan 10 | 60 | 6 | HR |  |  | 60 | 0 | 360 | 46.8 | 406.8 | 2020-10-24 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Labourers delivering geo to site | 5 | C070-C075 | White Sand | 0 | 44139 |  | 52 | 44140 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting625620201024-23Labourer - General - After Jan 106360 | Corbiere and Sons Contracting625620201024-23Labourer - General - After Jan 106360Inv#070 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 360 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7089 | 20201024-25 | 53510312 | Access | 0 | Marooka- After Jan 10 | 144.6 | 5 | Dynamic | 108.45 | 0 |  |  | 723 | 93.99 | 816.99 | 2020-10-24 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Army truck for use by North Shore in Landfill Rd area from B-077 - B-084 | 3 | B078-B084 | Red Rock No. 7 | 0 | 44169 |  | 37 | 44169 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting708920201024-25Marooka- After Jan 105723 | Corbiere and Sons Contracting708920201024-25Marooka- After Jan 105723Inv#081 | [5 empty] | 1 | 723 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6260 | 20201025-11 | 53510502 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 4 | Dynamic | 103.84 | 0 |  |  | 553.8 | 71.994 | 625.794 | 2020-10-25 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Cutting down ramp and casting material from C069 | 5 | C069 | Antler Lake | 0 | 44139 |  | 52 | 44140 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting626020201025-11Excavator - 30 ton- After Jan 104553.8 | Corbiere and Sons Contracting626020201025-11Excavator - 30 ton- After Jan 104553.8Inv#070 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 553.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6260 | 20201025-11 | 53510502 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-10-25 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Cutting down ramp and casting material from C069 | 5 | C069 | Antler Lake | 0 | 44139 |  | 52 | 44140 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting626020201025-11Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting626020201025-11Light Truck - Pick up- After Jan 101243.75Inv#070 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6260 | 20201025-11 | 53510502 | Access | 0 | Foreman | 95 | 2 | HR |  |  | 95 | 0 | 190 | 24.7 | 214.7 | 2020-10-25 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Cutting down ramp and casting material from C069 | 5 | C069 | Antler Lake | 0 | 44139 |  | 52 | 44140 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting626020201025-11Foreman2190 | Corbiere and Sons Contracting626020201025-11Foreman2190Inv#070 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 190 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6260 | 20201025-11 | 53510502 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-10-25 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Cutting down ramp and casting material from C069 | 5 | C069 | Antler Lake | 0 | 44139 |  | 52 | 44140 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting626020201025-11L.O.A.2420 | Corbiere and Sons Contracting626020201025-11L.O.A.2420Inv#070 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6260 | 20201025-11 | 53510502 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 4 | HR |  |  | 75 | 0 | 300 | 39 | 339 | 2020-10-25 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Cutting down ramp and casting material from C069 | 5 | C069 | Antler Lake | 0 | 44139 |  | 52 | 44140 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting626020201025-11Operator - Principle - After Jan 104300 | Corbiere and Sons Contracting626020201025-11Operator - Principle - After Jan 104300Inv#070 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6262 | 20201025-13 | 53510503 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 4 | Dynamic | 110.22 | 0 |  |  | 587.84 | 76.4192 | 664.2592 | 2020-10-25 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Wetland access development area from C063 | 5 | C063 | Antler Lake | 0 | 44139 |  | 52 | 44140 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting626220201025-13Excavator - 36 ton- After Jan 104587.84 | Corbiere and Sons Contracting626220201025-13Excavator - 36 ton- After Jan 104587.84Inv#070 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 587.84 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6262 | 20201025-13 | 53510503 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 4 | HR | 9.16 | 0 |  |  | 48.84 | 6.3492 | 55.1892 | 2020-10-25 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Wetland access development area from C063 | 5 | C063 | Antler Lake | 0 | 44139 |  | 52 | 44140 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting626220201025-13Excavator Thumb - 30 - 50 ton- After Jan 10448.84 | Corbiere and Sons Contracting626220201025-13Excavator Thumb - 30 - 50 ton- After Jan 10448.84Inv#070 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 48.84 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6262 | 20201025-13 | 53510503 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-10-25 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Wetland access development area from C063 | 5 | C063 | Antler Lake | 0 | 44139 |  | 52 | 44140 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting626220201025-13Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting626220201025-13Light Truck - Pick up- After Jan 101243.75Inv#070 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6262 | 20201025-13 | 53510503 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 5 | Dynamic | 103.54 | 0 |  |  | 690.25 | 89.7325 | 779.9825 | 2020-10-25 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Wetland access development area from C063 | 5 | C063 | Antler Lake | 0 | 44139 |  | 52 | 44140 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting626220201025-13Rock Truck - 30 Ton- After Jan 105690.25 | Corbiere and Sons Contracting626220201025-13Rock Truck - 30 Ton- After Jan 105690.25Inv#070 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 690.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6262 | 20201025-13 | 53510503 | Access | 0 | Foreman | 95 | 4 | HR |  |  | 95 | 0 | 380 | 49.4 | 429.4 | 2020-10-25 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Wetland access development area from C063 | 5 | C063 | Antler Lake | 0 | 44139 |  | 52 | 44140 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting626220201025-13Foreman4380 | Corbiere and Sons Contracting626220201025-13Foreman4380Inv#070 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6262 | 20201025-13 | 53510503 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 4.5 | HR |  |  | 75 | 0 | 337.5 | 43.875 | 381.375 | 2020-10-25 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Wetland access development area from C063 | 5 | C063 | Antler Lake | 0 | 44139 |  | 52 | 44140 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting626220201025-13Operator - Principle - After Jan 104.5337.5 | Corbiere and Sons Contracting626220201025-13Operator - Principle - After Jan 104.5337.5Inv#070 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 337.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6262 | 20201025-13 | 53510503 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 5.5 | HR |  |  | 70 | 0 | 385 | 50.05 | 435.05 | 2020-10-25 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Wetland access development area from C063 | 5 | C063 | Antler Lake | 0 | 44139 |  | 52 | 44140 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting626220201025-13Driver - AZ - After Jan 105.5385 | Corbiere and Sons Contracting626220201025-13Driver - AZ - After Jan 105.5385Inv#070 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 385 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6266 | 20201025-17-R1 | 53510504 | Access | 0 | Loader JD 524 to 624 or equal | 99 | 10.5 | HR | 74.25 | 0 |  |  | 1039.5 | 135.135 | 1174.635 | 2020-10-25 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hauling and spreading of gravel on Cooks Lake Road East | 5 | C093-C116 | Cook Lake | 0 | 44139 |  | 52 | 44140 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting626620201025-17-R1Loader JD 524 to 624 or equal10.51039.5 | Corbiere and Sons Contracting626620201025-17-R1Loader JD 524 to 624 or equal10.51039.5Inv#070 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1039.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6266 | 20201025-17-R1 | 53510504 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 17.5 | Dynamic | 98.61 | 0 |  |  | 2300.9 | 299.117 | 2600.017 | 2020-10-25 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hauling and spreading of gravel on Cooks Lake Road East | 5 | C093-C116 | Cook Lake | 0 | 44139 |  | 52 | 44140 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting626620201025-17-R1Dozer D6 or equal- After Jan 1017.52300.9 | Corbiere and Sons Contracting626620201025-17-R1Dozer D6 or equal- After Jan 1017.52300.9Inv#070 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 2300.9 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6266 | 20201025-17-R1 | 53510504 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 13.5 | Dynamic | 110.22 | 0 |  |  | 1983.96 | 257.9148 | 2241.8748 | 2020-10-25 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hauling and spreading of gravel on Cooks Lake Road East | 5 | C093-C116 | Cook Lake | 0 | 44139 |  | 52 | 44140 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting626620201025-17-R1Excavator - 36 ton- After Jan 1013.51983.96 | Corbiere and Sons Contracting626620201025-17-R1Excavator - 36 ton- After Jan 1013.51983.96Inv#070 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1983.96 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6266 | 20201025-17-R1 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2020-10-25 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hauling and spreading of gravel on Cooks Lake Road East | 5 | C093-C116 | Cook Lake | 0 | 44139 |  | 52 | 44140 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting626620201025-17-R1Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting626620201025-17-R1Light Truck - Pick up- After Jan 103731.25Inv#070 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 731.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6266 | 20201025-17-R1 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 21 | Dynamic | 103.54 | 0 |  |  | 2899.05 | 376.8765 | 3275.9265 | 2020-10-25 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hauling and spreading of gravel on Cooks Lake Road East | 5 | C093-C116 | Cook Lake | 0 | 44139 |  | 52 | 44140 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting626620201025-17-R1Rock Truck - 30 Ton- After Jan 10212899.05 | Corbiere and Sons Contracting626620201025-17-R1Rock Truck - 30 Ton- After Jan 10212899.05Inv#070 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 2899.05 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6266 | 20201025-17-R1 | 53510504 | Access | 0 | Foreman | 95 | 6 | HR |  |  | 95 | 0 | 570 | 74.1 | 644.1 | 2020-10-25 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hauling and spreading of gravel on Cooks Lake Road East | 5 | C093-C116 | Cook Lake | 0 | 44139 |  | 52 | 44140 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting626620201025-17-R1Foreman6570 | Corbiere and Sons Contracting626620201025-17-R1Foreman6570Inv#070 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 570 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6266 | 20201025-17-R1 | 53510504 | Access | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2020-10-25 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hauling and spreading of gravel on Cooks Lake Road East | 5 | C093-C116 | Cook Lake | 0 | 44139 |  | 52 | 44140 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting626620201025-17-R1L.O.A.61260 | Corbiere and Sons Contracting626620201025-17-R1L.O.A.61260Inv#070 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6266 | 20201025-17-R1 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 44.5 | HR |  |  | 75 | 0 | 3337.5 | 433.875 | 3771.375 | 2020-10-25 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hauling and spreading of gravel on Cooks Lake Road East | 5 | C093-C116 | Cook Lake | 0 | 44139 |  | 52 | 44140 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting626620201025-17-R1Operator - Principle - After Jan 1044.53337.5 | Corbiere and Sons Contracting626620201025-17-R1Operator - Principle - After Jan 1044.53337.5Inv#070 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 3337.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6266 | 20201025-17-R1 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 23 | HR |  |  | 70 | 0 | 1610 | 209.3 | 1819.3 | 2020-10-25 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hauling and spreading of gravel on Cooks Lake Road East | 5 | C093-C116 | Cook Lake | 0 | 44139 |  | 52 | 44140 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting626620201025-17-R1Driver - AZ - After Jan 10231610 | Corbiere and Sons Contracting626620201025-17-R1Driver - AZ - After Jan 10231610Inv#070 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1610 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6267 | 20201025-18 | 53510503 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 4 | Dynamic | 110.22 | 0 |  |  | 587.84 | 76.4192 | 664.2592 | 2020-10-25 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 40m's of corduroy put down at C093 | 5 | C093 | Cook Lake | 0 | 44139 |  | 52 | 44140 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting626720201025-18Excavator - 36 ton- After Jan 104587.84 | Corbiere and Sons Contracting626720201025-18Excavator - 36 ton- After Jan 104587.84Inv#070 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 587.84 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6267 | 20201025-18 | 53510503 | Access | 0 | Foreman | 95 | 3 | HR |  |  | 95 | 0 | 285 | 37.05 | 322.05 | 2020-10-25 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 40m's of corduroy put down at C093 | 5 | C093 | Cook Lake | 0 | 44139 |  | 52 | 44140 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting626720201025-18Foreman3285 | Corbiere and Sons Contracting626720201025-18Foreman3285Inv#070 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 285 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6267 | 20201025-18 | 53510503 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 4.5 | HR |  |  | 75 | 0 | 337.5 | 43.875 | 381.375 | 2020-10-25 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 40m's of corduroy put down at C093 | 5 | C093 | Cook Lake | 0 | 44139 |  | 52 | 44140 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting626720201025-18Operator - Principle - After Jan 104.5337.5 | Corbiere and Sons Contracting626720201025-18Operator - Principle - After Jan 104.5337.5Inv#070 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 337.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6268 | 20201025-19 | 53510512 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10.5 | Dynamic | 103.84 | 0 |  |  | 1453.725 | 188.9843 | 1642.7093 | 2020-10-25 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance being done between C086-C092 - Should be Ex005 | 5 | C076-C116 | Cook Lake | 0 | 44139 |  | 52 | 44140 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting626820201025-19Excavator - 30 ton- After Jan 1010.51453.725 | Corbiere and Sons Contracting626820201025-19Excavator - 30 ton- After Jan 1010.51453.725Inv#070 | [5 empty] | 1 | 1453.725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6268 | 20201025-19 | 53510512 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10.5 | HR | 9.16 | 0 |  |  | 128.205 | 16.6667 | 144.8716 | 2020-10-25 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance being done between C086-C092 - Should be Ex005 | 5 | C076-C116 | Cook Lake | 0 | 44139 |  | 52 | 44140 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting626820201025-19Excavator Thumb - 30 - 50 ton- After Jan 1010.5128.205 | Corbiere and Sons Contracting626820201025-19Excavator Thumb - 30 - 50 ton- After Jan 1010.5128.205Inv#070 | [5 empty] | 1 | 128.205 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6268 | 20201025-19 | 53510512 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-10-25 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance being done between C086-C092 - Should be Ex005 | 5 | C076-C116 | Cook Lake | 0 | 44139 |  | 52 | 44140 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting626820201025-19L.O.A.1210 | Corbiere and Sons Contracting626820201025-19L.O.A.1210Inv#070 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6268 | 20201025-19 | 53510512 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-10-25 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance being done between C086-C092 - Should be Ex005 | 5 | C076-C116 | Cook Lake | 0 | 44139 |  | 52 | 44140 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting626820201025-19Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting626820201025-19Operator - Principle - After Jan 1011.5862.5Inv#070 | [5 empty] | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6186 | 20201026-15 | 53510412 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 6 | Dynamic | 98.61 |  |  |  | 788.88 | 102.5544 | 891.4344 | 2020-10-26 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Worked on water hole and trimming Little Gravel River Rd | 4 |  | Little Gravel River Rd | 0 | 44135 |  | 50 | 44136 | [5 empty] | Wes Seminowich | 04 | Corbiere and Sons Contracting618620201026-15Dozer D6 or equal- After Jan 106788.88 | Corbiere and Sons Contracting618620201026-15Dozer D6 or equal- After Jan 106788.88Inv#070 | [5 empty] | 1 | 788.88 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6186 | 20201026-15 | 53510412 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 6 | Dynamic | 110.22 | 0 |  |  | 881.76 | 114.6288 | 996.3888 | 2020-10-26 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Worked on water hole and trimming Little Gravel River Rd | 4 |  | Little Gravel River Rd | 0 | 44135 |  | 50 | 44136 | [5 empty] | Wes Seminowich | 04 | Corbiere and Sons Contracting618620201026-15Excavator - 36 ton- After Jan 106881.76 | Corbiere and Sons Contracting618620201026-15Excavator - 36 ton- After Jan 106881.76Inv#070 | [5 empty] | 1 | 881.76 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6186 | 20201026-15 | 53510412 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 6 | HR | 9.16 | 0 |  |  | 73.26 | 9.5238 | 82.7838 | 2020-10-26 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Worked on water hole and trimming Little Gravel River Rd | 4 |  | Little Gravel River Rd | 0 | 44135 |  | 50 | 44136 | [5 empty] | Wes Seminowich | 04 | Corbiere and Sons Contracting618620201026-15Excavator Thumb - 30 - 50 ton- After Jan 10673.26 | Corbiere and Sons Contracting618620201026-15Excavator Thumb - 30 - 50 ton- After Jan 10673.26Inv#070 | [5 empty] | 1 | 73.26 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6186 | 20201026-15 | 53510412 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-10-26 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Worked on water hole and trimming Little Gravel River Rd | 4 |  | Little Gravel River Rd | 0 | 44135 |  | 50 | 44136 | [5 empty] | Wes Seminowich | 04 | Corbiere and Sons Contracting618620201026-15Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting618620201026-15Light Truck - Pick up- After Jan 101243.75Inv#070 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6186 | 20201026-15 | 53510412 | Access | 0 | Foreman | 95 | 2 | HR |  |  | 95 | 0 | 190 | 24.7 | 214.7 | 2020-10-26 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Worked on water hole and trimming Little Gravel River Rd | 4 |  | Little Gravel River Rd | 0 | 44135 |  | 50 | 44136 | [5 empty] | Wes Seminowich | 04 | Corbiere and Sons Contracting618620201026-15Foreman2190 | Corbiere and Sons Contracting618620201026-15Foreman2190Inv#070 | [5 empty] | 1 | 190 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6186 | 20201026-15 | 53510412 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 14 | HR |  |  | 75 | 0 | 1050 | 136.5 | 1186.5 | 2020-10-26 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Worked on water hole and trimming Little Gravel River Rd | 4 |  | Little Gravel River Rd | 0 | 44135 |  | 50 | 44136 | [5 empty] | Wes Seminowich | 04 | Corbiere and Sons Contracting618620201026-15Operator - Principle - After Jan 10141050 | Corbiere and Sons Contracting618620201026-15Operator - Principle - After Jan 10141050Inv#070 | [5 empty] | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6275 | 20201026-21 | 53510503 | Access | 0 | Skidder | 171 | 5 | HR | 128.25 | 0 |  |  | 855 | 111.15 | 966.15 | 2020-10-26 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Putting down Corduroy for access into C069 | 5 | C069 | Antler Lake | 0 | 44140 |  | 50 | 44142 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting627520201026-21Skidder 5855 | Corbiere and Sons Contracting627520201026-21Skidder 5855Inv#070 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 855 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6275 | 20201026-21 | 53510503 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 5 | Dynamic | 110.22 | 0 |  |  | 734.8 | 95.524 | 830.324 | 2020-10-26 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Putting down Corduroy for access into C069 | 5 | C069 | Antler Lake | 0 | 44140 |  | 50 | 44142 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting627520201026-21Excavator - 36 ton- After Jan 105734.8 | Corbiere and Sons Contracting627520201026-21Excavator - 36 ton- After Jan 105734.8Inv#070 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 734.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6275 | 20201026-21 | 53510503 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 5 | HR | 9.16 | 0 |  |  | 61.05 | 7.9365 | 68.9865 | 2020-10-26 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Putting down Corduroy for access into C069 | 5 | C069 | Antler Lake | 0 | 44140 |  | 50 | 44142 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting627520201026-21Excavator Thumb - 30 - 50 ton- After Jan 10561.05 | Corbiere and Sons Contracting627520201026-21Excavator Thumb - 30 - 50 ton- After Jan 10561.05Inv#070 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 61.05 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6275 | 20201026-21 | 53510503 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-10-26 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Putting down Corduroy for access into C069 | 5 | C069 | Antler Lake | 0 | 44140 |  | 50 | 44142 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting627520201026-21Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting627520201026-21Light Truck - Pick up- After Jan 101243.75Inv#070 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6275 | 20201026-21 | 53510503 | Access | 0 | Foreman | 95 | 4 | HR |  |  | 95 | 0 | 380 | 49.4 | 429.4 | 2020-10-26 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Putting down Corduroy for access into C069 | 5 | C069 | Antler Lake | 0 | 44140 |  | 50 | 44142 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting627520201026-21Foreman4380 | Corbiere and Sons Contracting627520201026-21Foreman4380Inv#070 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6275 | 20201026-21 | 53510503 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2020-10-26 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Putting down Corduroy for access into C069 | 5 | C069 | Antler Lake | 0 | 44140 |  | 50 | 44142 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting627520201026-21L.O.A.3630 | Corbiere and Sons Contracting627520201026-21L.O.A.3630Inv#070 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6275 | 20201026-21 | 53510503 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2020-10-26 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Putting down Corduroy for access into C069 | 5 | C069 | Antler Lake | 0 | 44140 |  | 50 | 44142 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting627520201026-21Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting627520201026-21Operator - Principle - After Jan 1011825Inv#070 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6277 | 20201026-23 | 53510504 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 6 | Dynamic | 98.61 | 0 |  |  | 788.88 | 102.5544 | 891.4344 | 2020-10-26 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Spread from C069 | 5 | C050-C069 | Antler Lake | 0 | 44140 |  | 50 | 44142 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting627720201026-23Dozer D6 or equal- After Jan 106788.88 | Corbiere and Sons Contracting627720201026-23Dozer D6 or equal- After Jan 106788.88Inv#070 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 788.88 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6277 | 20201026-23 | 53510504 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 6 | Dynamic | 110.22 | 0 |  |  | 881.76 | 114.6288 | 996.3888 | 2020-10-26 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Spread from C069 | 5 | C050-C069 | Antler Lake | 0 | 44140 |  | 50 | 44142 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting627720201026-23Excavator - 36 ton- After Jan 106881.76 | Corbiere and Sons Contracting627720201026-23Excavator - 36 ton- After Jan 106881.76Inv#070 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 881.76 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6277 | 20201026-23 | 53510504 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 6 | HR | 9.16 | 0 |  |  | 73.26 | 9.5238 | 82.7838 | 2020-10-26 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Spread from C069 | 5 | C050-C069 | Antler Lake | 0 | 44140 |  | 50 | 44142 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting627720201026-23Excavator Thumb - 30 - 50 ton- After Jan 10673.26 | Corbiere and Sons Contracting627720201026-23Excavator Thumb - 30 - 50 ton- After Jan 10673.26Inv#070 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 73.26 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6277 | 20201026-23 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-10-26 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Spread from C069 | 5 | C050-C069 | Antler Lake | 0 | 44140 |  | 50 | 44142 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting627720201026-23Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting627720201026-23Light Truck - Pick up- After Jan 101243.75Inv#070 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6277 | 20201026-23 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 7 | Dynamic | 103.54 |  |  |  | 966.35 | 125.6255 | 1091.9755 | 2020-10-26 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Spread from C069 | 5 | C050-C069 | Antler Lake | 0 | 44140 |  | 50 | 44142 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting627720201026-23Rock Truck - 30 Ton- After Jan 107966.35 | Corbiere and Sons Contracting627720201026-23Rock Truck - 30 Ton- After Jan 107966.35Inv#070 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 966.35 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6277 | 20201026-23 | 53510504 | Access | 0 | Foreman | 95 | 4 | HR |  |  | 95 | 0 | 380 | 49.4 | 429.4 | 2020-10-26 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Spread from C069 | 5 | C050-C069 | Antler Lake | 0 | 44140 |  | 50 | 44142 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting627720201026-23Foreman4380 | Corbiere and Sons Contracting627720201026-23Foreman4380Inv#070 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6277 | 20201026-23 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12.5 | HR |  |  | 75 | 0 | 937.5 | 121.875 | 1059.375 | 2020-10-26 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Spread from C069 | 5 | C050-C069 | Antler Lake | 0 | 44140 |  | 50 | 44142 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting627720201026-23Operator - Principle - After Jan 1012.5937.5 | Corbiere and Sons Contracting627720201026-23Operator - Principle - After Jan 1012.5937.5Inv#070 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 937.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6277 | 20201026-23 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 7.5 | HR |  |  | 70 | 0 | 525 | 68.25 | 593.25 | 2020-10-26 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Spread from C069 | 5 | C050-C069 | Antler Lake | 0 | 44140 |  | 50 | 44142 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting627720201026-23Driver - AZ - After Jan 107.5525 | Corbiere and Sons Contracting627720201026-23Driver - AZ - After Jan 107.5525Inv#070 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 525 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6278 | 20201026-24 | 53510512 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 4 | Dynamic | 103.84 | 0 |  |  | 553.8 | 71.994 | 625.794 | 2020-10-26 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Diverting road 50m from C069 | 5 | C069 | Antler Lake | 0 | 44140 |  | 50 | 44142 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting627820201026-24Excavator - 30 ton- After Jan 104553.8 | Corbiere and Sons Contracting627820201026-24Excavator - 30 ton- After Jan 104553.8Inv#070 | [5 empty] | 1 | 553.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6278 | 20201026-24 | 53510512 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 4 | HR |  |  | 75 | 0 | 300 | 39 | 339 | 2020-10-26 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Diverting road 50m from C069 | 5 | C069 | Antler Lake | 0 | 44140 |  | 50 | 44142 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting627820201026-24Operator - Principle - After Jan 104300 | Corbiere and Sons Contracting627820201026-24Operator - Principle - After Jan 104300Inv#070 | [5 empty] | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6281 | 20201026-27 | 53510503 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 5 | Dynamic | 103.84 | 0 |  |  | 692.25 | 89.9925 | 782.2425 | 2020-10-26 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jordan on Ex005 putting down corduroy from C093 for 5 hours | 5 | C093 | Cook Lake | 0 | 44140 |  | 50 | 44142 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting628120201026-27Excavator - 30 ton- After Jan 105692.25 | Corbiere and Sons Contracting628120201026-27Excavator - 30 ton- After Jan 105692.25Inv#070 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 692.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6281 | 20201026-27 | 53510503 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 5 | HR | 9.16 | 0 |  |  | 61.05 | 7.9365 | 68.9865 | 2020-10-26 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jordan on Ex005 putting down corduroy from C093 for 5 hours | 5 | C093 | Cook Lake | 0 | 44140 |  | 50 | 44142 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting628120201026-27Excavator Thumb - 30 - 50 ton- After Jan 10561.05 | Corbiere and Sons Contracting628120201026-27Excavator Thumb - 30 - 50 ton- After Jan 10561.05Inv#070 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 61.05 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6281 | 20201026-27 | 53510503 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-10-26 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jordan on Ex005 putting down corduroy from C093 for 5 hours | 5 | C093 | Cook Lake | 0 | 44140 |  | 50 | 44142 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting628120201026-27L.O.A.1210 | Corbiere and Sons Contracting628120201026-27L.O.A.1210Inv#070 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6281 | 20201026-27 | 53510503 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5 | HR |  |  | 75 | 0 | 375 | 48.75 | 423.75 | 2020-10-26 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jordan on Ex005 putting down corduroy from C093 for 5 hours | 5 | C093 | Cook Lake | 0 | 44140 |  | 50 | 44142 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting628120201026-27Operator - Principle - After Jan 105375 | Corbiere and Sons Contracting628120201026-27Operator - Principle - After Jan 105375Inv#070 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 375 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6282 | 20201026-28 | 53510512 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 5 | Dynamic | 110.22 | 0 |  |  | 734.8 | 95.524 | 830.324 | 2020-10-26 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rob and Ex011 performed 5 hours of road maintenance along main access | 5 | C093 | Cook Lake | 0 | 44140 |  | 50 | 44142 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting628220201026-28Excavator - 36 ton- After Jan 105734.8 | Corbiere and Sons Contracting628220201026-28Excavator - 36 ton- After Jan 105734.8Inv#070 | [5 empty] | 1 | 734.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6282 | 20201026-28 | 53510512 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-10-26 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rob and Ex011 performed 5 hours of road maintenance along main access | 5 | C093 | Cook Lake | 0 | 44140 |  | 50 | 44142 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting628220201026-28L.O.A.1210 | Corbiere and Sons Contracting628220201026-28L.O.A.1210Inv#070 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6282 | 20201026-28 | 53510512 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5.5 | HR |  |  | 75 | 0 | 412.5 | 53.625 | 466.125 | 2020-10-26 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rob and Ex011 performed 5 hours of road maintenance along main access | 5 | C093 | Cook Lake | 0 | 44140 |  | 50 | 44142 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting628220201026-28Operator - Principle - After Jan 105.5412.5 | Corbiere and Sons Contracting628220201026-28Operator - Principle - After Jan 105.5412.5Inv#070 | [5 empty] | 1 | 412.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6283 | 20201026-29 | 53510504 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10.5 | Dynamic | 98.61 | 0 |  |  | 1380.54 | 179.4702 | 1560.0102 | 2020-10-26 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Spread happening on various areas from Cooks Lake Road E | 5 | C093 | Cook Lake | 0 | 44140 |  | 50 | 44142 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting628320201026-29Dozer D6 or equal- After Jan 1010.51380.54 | Corbiere and Sons Contracting628320201026-29Dozer D6 or equal- After Jan 1010.51380.54Inv#070 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1380.54 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6283 | 20201026-29 | 53510504 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10.5 | Dynamic | 110.22 | 0 |  |  | 1543.08 | 200.6004 | 1743.6804 | 2020-10-26 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Spread happening on various areas from Cooks Lake Road E | 5 | C093 | Cook Lake | 0 | 44140 |  | 50 | 44142 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting628320201026-29Excavator - 36 ton- After Jan 1010.51543.08 | Corbiere and Sons Contracting628320201026-29Excavator - 36 ton- After Jan 1010.51543.08Inv#070 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1543.08 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6283 | 20201026-29 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2020-10-26 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Spread happening on various areas from Cooks Lake Road E | 5 | C093 | Cook Lake | 0 | 44140 |  | 50 | 44142 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting628320201026-29Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting628320201026-29Light Truck - Pick up- After Jan 103731.25Inv#070 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 731.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6283 | 20201026-29 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 31.5 | Dynamic | 103.54 | 0 |  |  | 4348.575 | 565.3148 | 4913.8898 | 2020-10-26 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Spread happening on various areas from Cooks Lake Road E | 5 | C093 | Cook Lake | 0 | 44140 |  | 50 | 44142 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting628320201026-29Rock Truck - 30 Ton- After Jan 1031.54348.575 | Corbiere and Sons Contracting628320201026-29Rock Truck - 30 Ton- After Jan 1031.54348.575Inv#070 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 4348.575 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6283 | 20201026-29 | 53510504 | Access | 0 | Foreman | 95 | 6 | HR |  |  | 95 | 0 | 570 | 74.1 | 644.1 | 2020-10-26 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Spread happening on various areas from Cooks Lake Road E | 5 | C093 | Cook Lake | 0 | 44140 |  | 50 | 44142 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting628320201026-29Foreman6570 | Corbiere and Sons Contracting628320201026-29Foreman6570Inv#070 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 570 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6283 | 20201026-29 | 53510504 | Access | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2020-10-26 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Spread happening on various areas from Cooks Lake Road E | 5 | C093 | Cook Lake | 0 | 44140 |  | 50 | 44142 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting628320201026-29L.O.A.51050 | Corbiere and Sons Contracting628320201026-29L.O.A.51050Inv#070 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6283 | 20201026-29 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 23 | HR |  |  | 75 | 0 | 1725 | 224.25 | 1949.25 | 2020-10-26 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Spread happening on various areas from Cooks Lake Road E | 5 | C093 | Cook Lake | 0 | 44140 |  | 50 | 44142 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting628320201026-29Operator - Principle - After Jan 10231725 | Corbiere and Sons Contracting628320201026-29Operator - Principle - After Jan 10231725Inv#070 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6283 | 20201026-29 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 34.5 | HR |  |  | 70 | 0 | 2415 | 313.95 | 2728.95 | 2020-10-26 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Spread happening on various areas from Cooks Lake Road E | 5 | C093 | Cook Lake | 0 | 44140 |  | 50 | 44142 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting628320201026-29Driver - AZ - After Jan 1034.52415 | Corbiere and Sons Contracting628320201026-29Driver - AZ - After Jan 1034.52415Inv#070 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 2415 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6289 | 20201027-17 | 53510502 | Access | 0 | Skidder | 171 | 4 | HR | 128.25 | 0 |  |  | 684 | 88.92 | 772.92 | 2020-10-27 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Road from C067-C069 | 5 | C061-C069 | Antler Lake | 0 | 44140 |  | 50 | 44141 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting628920201027-17Skidder 4684 | Corbiere and Sons Contracting628920201027-17Skidder 4684Inv#070 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 684 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6289 | 20201027-17 | 53510502 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10 | Dynamic | 103.84 | 0 |  |  | 1384.5 | 179.985 | 1564.485 | 2020-10-27 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Road from C067-C069 | 5 | C061-C069 | Antler Lake | 0 | 44140 |  | 50 | 44141 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting628920201027-17Excavator - 30 ton- After Jan 10101384.5 | Corbiere and Sons Contracting628920201027-17Excavator - 30 ton- After Jan 10101384.5Inv#070 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 1384.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6289 | 20201027-17 | 53510502 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 3 | HR | 9.16 | 0 |  |  | 36.63 | 4.7619 | 41.3919 | 2020-10-27 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Road from C067-C069 | 5 | C061-C069 | Antler Lake | 0 | 44140 |  | 50 | 44141 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting628920201027-17Excavator Thumb - 30 - 50 ton- After Jan 10336.63 | Corbiere and Sons Contracting628920201027-17Excavator Thumb - 30 - 50 ton- After Jan 10336.63Inv#070 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 36.63 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6289 | 20201027-17 | 53510502 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-10-27 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Road from C067-C069 | 5 | C061-C069 | Antler Lake | 0 | 44140 |  | 50 | 44141 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting628920201027-17Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting628920201027-17Light Truck - Pick up- After Jan 101243.75Inv#070 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6289 | 20201027-17 | 53510502 | Access | 0 | Foreman | 95 | 4 | HR |  |  | 95 | 0 | 380 | 49.4 | 429.4 | 2020-10-27 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Road from C067-C069 | 5 | C061-C069 | Antler Lake | 0 | 44140 |  | 50 | 44141 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting628920201027-17Foreman4380 | Corbiere and Sons Contracting628920201027-17Foreman4380Inv#070 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6289 | 20201027-17 | 53510502 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-10-27 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Road from C067-C069 | 5 | C061-C069 | Antler Lake | 0 | 44140 |  | 50 | 44141 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting628920201027-17L.O.A.2420 | Corbiere and Sons Contracting628920201027-17L.O.A.2420Inv#070 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6289 | 20201027-17 | 53510502 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 14 | HR |  |  | 75 | 0 | 1050 | 136.5 | 1186.5 | 2020-10-27 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Road from C067-C069 | 5 | C061-C069 | Antler Lake | 0 | 44140 |  | 50 | 44141 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting628920201027-17Operator - Principle - After Jan 10141050 | Corbiere and Sons Contracting628920201027-17Operator - Principle - After Jan 10141050Inv#070 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6289 | 20201027-17 | 53510502 | Access | 0 | Labourer - General - After Jan 10 | 60 | 4 | HR |  |  | 60 | 0 | 240 | 31.2 | 271.2 | 2020-10-27 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building Road from C067-C069 | 5 | C061-C069 | Antler Lake | 0 | 44140 |  | 50 | 44141 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting628920201027-17Labourer - General - After Jan 104240 | Corbiere and Sons Contracting628920201027-17Labourer - General - After Jan 104240Inv#070 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 240 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6291 | 20201027-19 | 53510504 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10.5 | Dynamic | 98.61 | 0 |  |  | 1380.54 | 179.4702 | 1560.0102 | 2020-10-27 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel spread between C061 and C069 on Antler Lake Road | 5 | C061-C069 | Antler Lake | 0 | 44140 |  | 50 | 44141 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting629120201027-19Dozer D6 or equal- After Jan 1010.51380.54 | Corbiere and Sons Contracting629120201027-19Dozer D6 or equal- After Jan 1010.51380.54Inv#070 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1380.54 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6291 | 20201027-19 | 53510504 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 7.5 | Dynamic | 103.84 | 0 |  |  | 1038.375 | 134.9888 | 1173.3637 | 2020-10-27 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel spread between C061 and C069 on Antler Lake Road | 5 | C061-C069 | Antler Lake | 0 | 44140 |  | 50 | 44141 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting629120201027-19Excavator - 30 ton- After Jan 107.51038.375 | Corbiere and Sons Contracting629120201027-19Excavator - 30 ton- After Jan 107.51038.375Inv#070 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1038.375 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6291 | 20201027-19 | 53510504 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 7.5 | HR | 9.16 | 0 |  |  | 91.575 | 11.9047 | 103.4797 | 2020-10-27 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel spread between C061 and C069 on Antler Lake Road | 5 | C061-C069 | Antler Lake | 0 | 44140 |  | 50 | 44141 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting629120201027-19Excavator Thumb - 30 - 50 ton- After Jan 107.591.575 | Corbiere and Sons Contracting629120201027-19Excavator Thumb - 30 - 50 ton- After Jan 107.591.575Inv#070 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 91.575 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6291 | 20201027-19 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-10-27 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel spread between C061 and C069 on Antler Lake Road | 5 | C061-C069 | Antler Lake | 0 | 44140 |  | 50 | 44141 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting629120201027-19Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting629120201027-19Light Truck - Pick up- After Jan 102487.5Inv#070 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6291 | 20201027-19 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 10.5 | Dynamic | 103.54 | 0 |  |  | 1449.525 | 188.4383 | 1637.9633 | 2020-10-27 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel spread between C061 and C069 on Antler Lake Road | 5 | C061-C069 | Antler Lake | 0 | 44140 |  | 50 | 44141 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting629120201027-19Rock Truck - 30 Ton- After Jan 1010.51449.525 | Corbiere and Sons Contracting629120201027-19Rock Truck - 30 Ton- After Jan 1010.51449.525Inv#070 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1449.525 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6291 | 20201027-19 | 53510504 | Access | 0 | Foreman | 95 | 4 | HR |  |  | 95 | 0 | 380 | 49.4 | 429.4 | 2020-10-27 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel spread between C061 and C069 on Antler Lake Road | 5 | C061-C069 | Antler Lake | 0 | 44140 |  | 50 | 44141 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting629120201027-19Foreman4380 | Corbiere and Sons Contracting629120201027-19Foreman4380Inv#070 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6291 | 20201027-19 | 53510504 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-10-27 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel spread between C061 and C069 on Antler Lake Road | 5 | C061-C069 | Antler Lake | 0 | 44140 |  | 50 | 44141 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting629120201027-19L.O.A.2420 | Corbiere and Sons Contracting629120201027-19L.O.A.2420Inv#070 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6291 | 20201027-19 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 20 | HR |  |  | 75 | 0 | 1500 | 195 | 1695 | 2020-10-27 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel spread between C061 and C069 on Antler Lake Road | 5 | C061-C069 | Antler Lake | 0 | 44140 |  | 50 | 44141 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting629120201027-19Operator - Principle - After Jan 10201500 | Corbiere and Sons Contracting629120201027-19Operator - Principle - After Jan 10201500Inv#070 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1500 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6291 | 20201027-19 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 11.5 | HR |  |  | 70 | 0 | 805 | 104.65 | 909.65 | 2020-10-27 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel spread between C061 and C069 on Antler Lake Road | 5 | C061-C069 | Antler Lake | 0 | 44140 |  | 50 | 44141 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting629120201027-19Driver - AZ - After Jan 1011.5805 | Corbiere and Sons Contracting629120201027-19Driver - AZ - After Jan 1011.5805Inv#070 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 805 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6296 | 20201027-24 | 53510504 | Access | 0 | Loader JD 524 to 624 or equal | 99 | 6.5 | HR | 74.25 | 0 |  |  | 643.5 | 83.655 | 727.155 | 2020-10-27 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel haul and spread happening between C093-C099 | 5 | C093-C116 | Cook Lake | 0 | 44140 |  | 50 | 44141 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting629620201027-24Loader JD 524 to 624 or equal6.5643.5 | Corbiere and Sons Contracting629620201027-24Loader JD 524 to 624 or equal6.5643.5Inv#070 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 643.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6296 | 20201027-24 | 53510504 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10.5 | Dynamic | 98.61 | 0 |  |  | 1380.54 | 179.4702 | 1560.0102 | 2020-10-27 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel haul and spread happening between C093-C099 | 5 | C093-C116 | Cook Lake | 0 | 44140 |  | 50 | 44141 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting629620201027-24Dozer D6 or equal- After Jan 1010.51380.54 | Corbiere and Sons Contracting629620201027-24Dozer D6 or equal- After Jan 1010.51380.54Inv#070 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1380.54 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6296 | 20201027-24 | 53510504 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10.5 | Dynamic | 110.22 | 0 |  |  | 1543.08 | 200.6004 | 1743.6804 | 2020-10-27 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel haul and spread happening between C093-C099 | 5 | C093-C116 | Cook Lake | 0 | 44140 |  | 50 | 44141 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting629620201027-24Excavator - 36 ton- After Jan 1010.51543.08 | Corbiere and Sons Contracting629620201027-24Excavator - 36 ton- After Jan 1010.51543.08Inv#070 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1543.08 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6296 | 20201027-24 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-10-27 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel haul and spread happening between C093-C099 | 5 | C093-C116 | Cook Lake | 0 | 44140 |  | 50 | 44141 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting629620201027-24Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting629620201027-24Light Truck - Pick up- After Jan 102487.5Inv#070 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6296 | 20201027-24 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 24.5 | Dynamic | 103.54 | 0 |  |  | 3382.225 | 439.6893 | 3821.9142 | 2020-10-27 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel haul and spread happening between C093-C099 | 5 | C093-C116 | Cook Lake | 0 | 44140 |  | 50 | 44141 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting629620201027-24Rock Truck - 30 Ton- After Jan 1024.53382.225 | Corbiere and Sons Contracting629620201027-24Rock Truck - 30 Ton- After Jan 1024.53382.225Inv#070 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 3382.225 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6296 | 20201027-24 | 53510504 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2020-10-27 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel haul and spread happening between C093-C099 | 5 | C093-C116 | Cook Lake | 0 | 44140 |  | 50 | 44141 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting629620201027-24L.O.A.3630 | Corbiere and Sons Contracting629620201027-24L.O.A.3630Inv#070 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6296 | 20201027-24 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 29.5 | HR |  |  | 75 | 0 | 2212.5 | 287.625 | 2500.125 | 2020-10-27 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel haul and spread happening between C093-C099 | 5 | C093-C116 | Cook Lake | 0 | 44140 |  | 50 | 44141 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting629620201027-24Operator - Principle - After Jan 1029.52212.5 | Corbiere and Sons Contracting629620201027-24Operator - Principle - After Jan 1029.52212.5Inv#070 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 2212.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6296 | 20201027-24 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 26.5 | HR |  |  | 70 | 0 | 1855 | 241.15 | 2096.15 | 2020-10-27 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel haul and spread happening between C093-C099 | 5 | C093-C116 | Cook Lake | 0 | 44140 |  | 50 | 44141 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting629620201027-24Driver - AZ - After Jan 1026.51855 | Corbiere and Sons Contracting629620201027-24Driver - AZ - After Jan 1026.51855Inv#070 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1855 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6302 | 20201028-16 | 53510504 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 6.5 | Dynamic | 98.61 | 0 |  |  | 854.62 | 111.1006 | 965.7206 | 2020-10-28 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel haul and spread happening from C064 and C069 | 5 | C064-C069 | Antler Lake | 0 | 44140 |  | 50 | 44141 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting630220201028-16Dozer D6 or equal- After Jan 106.5854.62 | Corbiere and Sons Contracting630220201028-16Dozer D6 or equal- After Jan 106.5854.62Inv#070 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 854.62 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6302 | 20201028-16 | 53510504 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 7.5 | Dynamic | 103.84 | 0 |  |  | 1038.375 | 134.9888 | 1173.3637 | 2020-10-28 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel haul and spread happening from C064 and C069 | 5 | C064-C069 | Antler Lake | 0 | 44140 |  | 50 | 44141 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting630220201028-16Excavator - 30 ton- After Jan 107.51038.375 | Corbiere and Sons Contracting630220201028-16Excavator - 30 ton- After Jan 107.51038.375Inv#070 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1038.375 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6302 | 20201028-16 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-10-28 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel haul and spread happening from C064 and C069 | 5 | C064-C069 | Antler Lake | 0 | 44140 |  | 50 | 44141 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting630220201028-16Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting630220201028-16Light Truck - Pick up- After Jan 101243.75Inv#070 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6302 | 20201028-16 | 53510504 | Access | 0 | Foreman | 95 | 6 | HR |  |  | 95 | 0 | 570 | 74.1 | 644.1 | 2020-10-28 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel haul and spread happening from C064 and C069 | 5 | C064-C069 | Antler Lake | 0 | 44140 |  | 50 | 44141 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting630220201028-16Foreman6570 | Corbiere and Sons Contracting630220201028-16Foreman6570Inv#070 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 570 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6302 | 20201028-16 | 53510504 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2020-10-28 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel haul and spread happening from C064 and C069 | 5 | C064-C069 | Antler Lake | 0 | 44140 |  | 50 | 44141 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting630220201028-16L.O.A.3630 | Corbiere and Sons Contracting630220201028-16L.O.A.3630Inv#070 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6302 | 20201028-16 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 14.5 | HR |  |  | 75 | 0 | 1087.5 | 141.375 | 1228.875 | 2020-10-28 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel haul and spread happening from C064 and C069 | 5 | C064-C069 | Antler Lake | 0 | 44140 |  | 50 | 44141 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting630220201028-16Operator - Principle - After Jan 1014.51087.5 | Corbiere and Sons Contracting630220201028-16Operator - Principle - After Jan 1014.51087.5Inv#070 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1087.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6304 | 20201028-18 | 53510502 | Access | 0 | Skidder | 171 | 2 | HR | 128.25 | 0 |  |  | 342 | 44.46 | 386.46 | 2020-10-28 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building road and rock hammering towards C069 | 5 | C050-C069 | Antler Lake | 0 | 44140 |  | 50 | 44141 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting630420201028-18Skidder 2342 | Corbiere and Sons Contracting630420201028-18Skidder 2342Inv#070 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 342 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6304 | 20201028-18 | 53510502 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 2 | Dynamic | 98.61 | 0 |  |  | 262.96 | 34.1848 | 297.1448 | 2020-10-28 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building road and rock hammering towards C069 | 5 | C050-C069 | Antler Lake | 0 | 44140 |  | 50 | 44141 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting630420201028-18Dozer D6 or equal- After Jan 102262.96 | Corbiere and Sons Contracting630420201028-18Dozer D6 or equal- After Jan 102262.96Inv#070 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 262.96 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6304 | 20201028-18 | 53510502 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 5.5 | Dynamic | 110.22 | 0 |  |  | 808.28 | 105.0764 | 913.3564 | 2020-10-28 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building road and rock hammering towards C069 | 5 | C050-C069 | Antler Lake | 0 | 44140 |  | 50 | 44141 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting630420201028-18Excavator - 36 ton- After Jan 105.5808.28 | Corbiere and Sons Contracting630420201028-18Excavator - 36 ton- After Jan 105.5808.28Inv#070 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 808.28 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6304 | 20201028-18 | 53510502 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 2 | HR | 9.16 | 0 |  |  | 24.42 | 3.1746 | 27.5946 | 2020-10-28 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building road and rock hammering towards C069 | 5 | C050-C069 | Antler Lake | 0 | 44140 |  | 50 | 44141 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting630420201028-18Excavator Thumb - 30 - 50 ton- After Jan 10224.42 | Corbiere and Sons Contracting630420201028-18Excavator Thumb - 30 - 50 ton- After Jan 10224.42Inv#070 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 24.42 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6304 | 20201028-18 | 53510502 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 3.5 | HR | 47.54 | 0 |  |  | 221.83 | 28.8379 | 250.6679 | 2020-10-28 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building road and rock hammering towards C069 | 5 | C050-C069 | Antler Lake | 0 | 44140 |  | 50 | 44141 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting630420201028-18Excavator Hammer - 30 - 50 ton- After Jan 103.5221.83 | Corbiere and Sons Contracting630420201028-18Excavator Hammer - 30 - 50 ton- After Jan 103.5221.83Inv#070 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 221.83 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6304 | 20201028-18 | 53510502 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-10-28 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building road and rock hammering towards C069 | 5 | C050-C069 | Antler Lake | 0 | 44140 |  | 50 | 44141 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting630420201028-18Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting630420201028-18Light Truck - Pick up- After Jan 102487.5Inv#070 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6304 | 20201028-18 | 53510502 | Access | 0 | Foreman | 95 | 3 | HR |  |  | 95 | 0 | 285 | 37.05 | 322.05 | 2020-10-28 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building road and rock hammering towards C069 | 5 | C050-C069 | Antler Lake | 0 | 44140 |  | 50 | 44141 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting630420201028-18Foreman3285 | Corbiere and Sons Contracting630420201028-18Foreman3285Inv#070 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 285 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6304 | 20201028-18 | 53510502 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-10-28 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building road and rock hammering towards C069 | 5 | C050-C069 | Antler Lake | 0 | 44140 |  | 50 | 44141 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting630420201028-18L.O.A.1210 | Corbiere and Sons Contracting630420201028-18L.O.A.1210Inv#070 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6304 | 20201028-18 | 53510502 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 9.5 | HR |  |  | 75 | 0 | 712.5 | 92.625 | 805.125 | 2020-10-28 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building road and rock hammering towards C069 | 5 | C050-C069 | Antler Lake | 0 | 44140 |  | 50 | 44141 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting630420201028-18Operator - Principle - After Jan 109.5712.5 | Corbiere and Sons Contracting630420201028-18Operator - Principle - After Jan 109.5712.5Inv#070 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 712.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6305 | 20201028-19 | 53510511 | Access | 0 | Skidder | 171 | 3 | HR | 128.25 | 0 |  |  | 513 | 66.69 | 579.69 | 2020-10-28 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Removing snow on access roads | 5 | C076-C116 | Cook Lake | 0 | 44140 |  | 50 | 44141 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting630520201028-19Skidder 3513 | Corbiere and Sons Contracting630520201028-19Skidder 3513Inv#070 | [5 empty] | 1 | 513 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6305 | 20201028-19 | 53510511 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10.5 | Dynamic | 98.61 | 0 |  |  | 1380.54 | 179.4702 | 1560.0102 | 2020-10-28 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Removing snow on access roads | 5 | C076-C116 | Cook Lake | 0 | 44140 |  | 50 | 44141 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting630520201028-19Dozer D6 or equal- After Jan 1010.51380.54 | Corbiere and Sons Contracting630520201028-19Dozer D6 or equal- After Jan 1010.51380.54Inv#070 | [5 empty] | 1 | 1380.54 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6305 | 20201028-19 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-10-28 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Removing snow on access roads | 5 | C076-C116 | Cook Lake | 0 | 44140 |  | 50 | 44141 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting630520201028-19Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting630520201028-19Light Truck - Pick up- After Jan 101243.75Inv#070 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6305 | 20201028-19 | 53510511 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-10-28 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Removing snow on access roads | 5 | C076-C116 | Cook Lake | 0 | 44140 |  | 50 | 44141 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting630520201028-19L.O.A.2420 | Corbiere and Sons Contracting630520201028-19L.O.A.2420Inv#070 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6305 | 20201028-19 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 14.5 | HR |  |  | 75 | 0 | 1087.5 | 141.375 | 1228.875 | 2020-10-28 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Removing snow on access roads | 5 | C076-C116 | Cook Lake | 0 | 44140 |  | 50 | 44141 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting630520201028-19Operator - Principle - After Jan 1014.51087.5 | Corbiere and Sons Contracting630520201028-19Operator - Principle - After Jan 1014.51087.5Inv#070 | [5 empty] | 1 | 1087.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6306 | 20201028-20 | 53510504 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 9 | Dynamic | 98.61 | 0 |  |  | 1183.32 | 153.8316 | 1337.1516 | 2020-10-28 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel hauling and spread happening from C093-C099 | 5 | C093-C116 | Cook Lake | 0 | 44140 |  | 50 | 44141 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting630620201028-20Dozer D6 or equal- After Jan 1091183.32 | Corbiere and Sons Contracting630620201028-20Dozer D6 or equal- After Jan 1091183.32Inv#070 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1183.32 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6306 | 20201028-20 | 53510504 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10.5 | Dynamic | 110.22 | 0 |  |  | 1543.08 | 200.6004 | 1743.6804 | 2020-10-28 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel hauling and spread happening from C093-C099 | 5 | C093-C116 | Cook Lake | 0 | 44140 |  | 50 | 44141 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting630620201028-20Excavator - 36 ton- After Jan 1010.51543.08 | Corbiere and Sons Contracting630620201028-20Excavator - 36 ton- After Jan 1010.51543.08Inv#070 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1543.08 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6306 | 20201028-20 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-10-28 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel hauling and spread happening from C093-C099 | 5 | C093-C116 | Cook Lake | 0 | 44140 |  | 50 | 44141 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting630620201028-20Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting630620201028-20Light Truck - Pick up- After Jan 102487.5Inv#070 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6306 | 20201028-20 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 31.5 | Dynamic | 103.54 | 0 |  |  | 4348.575 | 565.3148 | 4913.8898 | 2020-10-28 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel hauling and spread happening from C093-C099 | 5 | C093-C116 | Cook Lake | 0 | 44140 |  | 50 | 44141 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting630620201028-20Rock Truck - 30 Ton- After Jan 1031.54348.575 | Corbiere and Sons Contracting630620201028-20Rock Truck - 30 Ton- After Jan 1031.54348.575Inv#070 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 4348.575 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6306 | 20201028-20 | 53510504 | Access | 0 | Foreman | 95 | 6 | HR |  |  | 95 | 0 | 570 | 74.1 | 644.1 | 2020-10-28 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel hauling and spread happening from C093-C099 | 5 | C093-C116 | Cook Lake | 0 | 44140 |  | 50 | 44141 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting630620201028-20Foreman6570 | Corbiere and Sons Contracting630620201028-20Foreman6570Inv#070 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 570 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6306 | 20201028-20 | 53510504 | Access | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2020-10-28 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel hauling and spread happening from C093-C099 | 5 | C093-C116 | Cook Lake | 0 | 44140 |  | 50 | 44141 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting630620201028-20L.O.A.61260 | Corbiere and Sons Contracting630620201028-20L.O.A.61260Inv#070 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6306 | 20201028-20 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 21 | HR |  |  | 75 | 0 | 1575 | 204.75 | 1779.75 | 2020-10-28 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel hauling and spread happening from C093-C099 | 5 | C093-C116 | Cook Lake | 0 | 44140 |  | 50 | 44141 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting630620201028-20Operator - Principle - After Jan 10211575 | Corbiere and Sons Contracting630620201028-20Operator - Principle - After Jan 10211575Inv#070 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1575 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6306 | 20201028-20 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 34.5 | HR |  |  | 70 | 0 | 2415 | 313.95 | 2728.95 | 2020-10-28 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel hauling and spread happening from C093-C099 | 5 | C093-C116 | Cook Lake | 0 | 44140 |  | 50 | 44141 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting630620201028-20Driver - AZ - After Jan 1034.52415 | Corbiere and Sons Contracting630620201028-20Driver - AZ - After Jan 1034.52415Inv#070 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 2415 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6309 | 20201028-23 | 53510503 | Access | 0 | Skidder | 171 | 3 | HR | 128.25 | 0 |  |  | 513 | 66.69 | 579.69 | 2020-10-28 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Putting down corduroy from C094 | 5 | C093-C116 | Cook Lake | 0 | 44140 |  | 50 | 44141 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting630920201028-23Skidder 3513 | Corbiere and Sons Contracting630920201028-23Skidder 3513Inv#070 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 513 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6309 | 20201028-23 | 53510503 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 5 | Dynamic | 103.84 | 0 |  |  | 692.25 | 89.9925 | 782.2425 | 2020-10-28 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Putting down corduroy from C094 | 5 | C093-C116 | Cook Lake | 0 | 44140 |  | 50 | 44141 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting630920201028-23Excavator - 30 ton- After Jan 105692.25 | Corbiere and Sons Contracting630920201028-23Excavator - 30 ton- After Jan 105692.25Inv#070 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 692.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6309 | 20201028-23 | 53510503 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 7.5 | Dynamic | 110.22 | 0 |  |  | 1102.2 | 143.286 | 1245.486 | 2020-10-28 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Putting down corduroy from C094 | 5 | C093-C116 | Cook Lake | 0 | 44140 |  | 50 | 44141 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting630920201028-23Excavator - 36 ton- After Jan 107.51102.2 | Corbiere and Sons Contracting630920201028-23Excavator - 36 ton- After Jan 107.51102.2Inv#070 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 1102.2 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6309 | 20201028-23 | 53510503 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 5 | HR | 9.16 | 0 |  |  | 61.05 | 7.9365 | 68.9865 | 2020-10-28 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Putting down corduroy from C094 | 5 | C093-C116 | Cook Lake | 0 | 44140 |  | 50 | 44141 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting630920201028-23Excavator Thumb - 30 - 50 ton- After Jan 10561.05 | Corbiere and Sons Contracting630920201028-23Excavator Thumb - 30 - 50 ton- After Jan 10561.05Inv#070 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 61.05 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6309 | 20201028-23 | 53510503 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-10-28 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Putting down corduroy from C094 | 5 | C093-C116 | Cook Lake | 0 | 44140 |  | 50 | 44141 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting630920201028-23Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting630920201028-23Light Truck - Pick up- After Jan 101243.75Inv#070 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6309 | 20201028-23 | 53510503 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-10-28 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Putting down corduroy from C094 | 5 | C093-C116 | Cook Lake | 0 | 44140 |  | 50 | 44141 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting630920201028-23L.O.A.1210 | Corbiere and Sons Contracting630920201028-23L.O.A.1210Inv#070 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6309 | 20201028-23 | 53510503 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 15.5 | HR |  |  | 75 | 0 | 1162.5 | 151.125 | 1313.625 | 2020-10-28 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Putting down corduroy from C094 | 5 | C093-C116 | Cook Lake | 0 | 44140 |  | 50 | 44141 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting630920201028-23Operator - Principle - After Jan 1015.51162.5 | Corbiere and Sons Contracting630920201028-23Operator - Principle - After Jan 1015.51162.5Inv#070 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 1162.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6310 | 20201028-24 | 53510512 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 2 | Dynamic | 98.61 | 0 |  |  | 262.96 | 34.1848 | 297.1448 | 2020-10-28 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance being performed from C083 and C003 | 5 | C076-C093 | Cook Lake | 0 | 44140 |  | 50 | 44141 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting631020201028-24Dozer D6 or equal- After Jan 102262.96 | Corbiere and Sons Contracting631020201028-24Dozer D6 or equal- After Jan 102262.96Inv#070 | [5 empty] | 1 | 262.96 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6310 | 20201028-24 | 53510512 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 1.5 | Dynamic | 110.22 | 0 |  |  | 220.44 | 28.6572 | 249.0972 | 2020-10-28 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance being performed from C083 and C003 | 5 | C076-C093 | Cook Lake | 0 | 44140 |  | 50 | 44141 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting631020201028-24Excavator - 36 ton- After Jan 101.5220.44 | Corbiere and Sons Contracting631020201028-24Excavator - 36 ton- After Jan 101.5220.44Inv#070 | [5 empty] | 1 | 220.44 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6310 | 20201028-24 | 53510512 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 4 | HR |  |  | 75 | 0 | 300 | 39 | 339 | 2020-10-28 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance being performed from C083 and C003 | 5 | C076-C093 | Cook Lake | 0 | 44140 |  | 50 | 44141 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting631020201028-24Operator - Principle - After Jan 104300 | Corbiere and Sons Contracting631020201028-24Operator - Principle - After Jan 104300Inv#070 | [5 empty] | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6315 | 20201029-14 | 53510504 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 55.5 | Dynamic | 41.4 | 0 |  |  | 3063.6 | 398.268 | 3461.868 | 2020-10-29 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling from worthington bay pit to Cooks Lake access | 5 | C076-C116 | Cook Lake | 0 | 44140 |  | 37 | 44141 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting631520201029-14Dump - Triaxle- After Jan 1055.53063.6 | Corbiere and Sons Contracting631520201029-14Dump - Triaxle- After Jan 1055.53063.6Inv#070 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 3063.6 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6315 | 20201029-14 | 53510504 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-10-29 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling from worthington bay pit to Cooks Lake access | 5 | C076-C116 | Cook Lake | 0 | 44140 |  | 37 | 44141 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting631520201029-14L.O.A.2420 | Corbiere and Sons Contracting631520201029-14L.O.A.2420Inv#070 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6315 | 20201029-14 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 55.5 | HR |  |  | 70 | 0 | 3885 | 505.05 | 4390.05 | 2020-10-29 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling from worthington bay pit to Cooks Lake access | 5 | C076-C116 | Cook Lake | 0 | 44140 |  | 37 | 44141 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting631520201029-14Driver - AZ - After Jan 1055.53885 | Corbiere and Sons Contracting631520201029-14Driver - AZ - After Jan 1055.53885Inv#070 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 3885 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6318 | 20201029-17 | 53510504 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 5 | Dynamic | 98.61 | 0 |  |  | 657.4 | 85.462 | 742.862 | 2020-10-29 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling on Antler Lake road in areas from C061-C069 | 5 | C050-C069 | Antler Lake | 0 | 44140 |  | 37 | 44141 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting631820201029-17Dozer D6 or equal- After Jan 105657.4 | Corbiere and Sons Contracting631820201029-17Dozer D6 or equal- After Jan 105657.4Inv#070 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 657.4 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6318 | 20201029-17 | 53510504 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10.5 | Dynamic | 110.22 | 0 |  |  | 1543.08 | 200.6004 | 1743.6804 | 2020-10-29 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling on Antler Lake road in areas from C061-C069 | 5 | C050-C069 | Antler Lake | 0 | 44140 |  | 37 | 44141 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting631820201029-17Excavator - 36 ton- After Jan 1010.51543.08 | Corbiere and Sons Contracting631820201029-17Excavator - 36 ton- After Jan 1010.51543.08Inv#070 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1543.08 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6318 | 20201029-17 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-10-29 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling on Antler Lake road in areas from C061-C069 | 5 | C050-C069 | Antler Lake | 0 | 44140 |  | 37 | 44141 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting631820201029-17Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting631820201029-17Light Truck - Pick up- After Jan 102487.5Inv#070 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6318 | 20201029-17 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 8 | Dynamic | 103.54 | 0 |  |  | 1104.4 | 143.572 | 1247.972 | 2020-10-29 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling on Antler Lake road in areas from C061-C069 | 5 | C050-C069 | Antler Lake | 0 | 44140 |  | 37 | 44141 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting631820201029-17Rock Truck - 30 Ton- After Jan 1081104.4 | Corbiere and Sons Contracting631820201029-17Rock Truck - 30 Ton- After Jan 1081104.4Inv#070 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1104.4 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6318 | 20201029-17 | 53510504 | Access | 0 | Foreman | 95 | 6 | HR |  |  | 95 | 0 | 570 | 74.1 | 644.1 | 2020-10-29 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling on Antler Lake road in areas from C061-C069 | 5 | C050-C069 | Antler Lake | 0 | 44140 |  | 37 | 44141 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting631820201029-17Foreman6570 | Corbiere and Sons Contracting631820201029-17Foreman6570Inv#070 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 570 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6318 | 20201029-17 | 53510504 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2020-10-29 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling on Antler Lake road in areas from C061-C069 | 5 | C050-C069 | Antler Lake | 0 | 44140 |  | 37 | 44141 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting631820201029-17L.O.A.3630 | Corbiere and Sons Contracting631820201029-17L.O.A.3630Inv#070 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6318 | 20201029-17 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 17 | HR |  |  | 75 | 0 | 1275 | 165.75 | 1440.75 | 2020-10-29 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling on Antler Lake road in areas from C061-C069 | 5 | C050-C069 | Antler Lake | 0 | 44140 |  | 37 | 44141 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting631820201029-17Operator - Principle - After Jan 10171275 | Corbiere and Sons Contracting631820201029-17Operator - Principle - After Jan 10171275Inv#070 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1275 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6318 | 20201029-17 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 8 | HR |  |  | 70 | 0 | 560 | 72.8 | 632.8 | 2020-10-29 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling on Antler Lake road in areas from C061-C069 | 5 | C050-C069 | Antler Lake | 0 | 44140 |  | 37 | 44141 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting631820201029-17Driver - AZ - After Jan 108560 | Corbiere and Sons Contracting631820201029-17Driver - AZ - After Jan 108560Inv#070 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 560 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6319 | 20201029-18 | 53510502 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 5.5 | Dynamic | 110.22 | 0 |  |  | 808.28 | 105.0764 | 913.3564 | 2020-10-29 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock Hammer working from Shoefly at C069 | 5 | C050-C069 | Antler Lake | 0 | 44140 |  | 37 | 44141 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting631920201029-18Excavator - 36 ton- After Jan 105.5808.28 | Corbiere and Sons Contracting631920201029-18Excavator - 36 ton- After Jan 105.5808.28Inv#070 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 808.28 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6319 | 20201029-18 | 53510502 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 5.5 | HR | 9.16 | 0 |  |  | 67.155 | 8.7302 | 75.8851 | 2020-10-29 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock Hammer working from Shoefly at C069 | 5 | C050-C069 | Antler Lake | 0 | 44140 |  | 37 | 44141 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting631920201029-18Excavator Thumb - 30 - 50 ton- After Jan 105.567.155 | Corbiere and Sons Contracting631920201029-18Excavator Thumb - 30 - 50 ton- After Jan 105.567.155Inv#070 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 67.155 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6319 | 20201029-18 | 53510502 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 75 | 0 | 450 | 58.5 | 508.5 | 2020-10-29 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock Hammer working from Shoefly at C069 | 5 | C050-C069 | Antler Lake | 0 | 44140 |  | 37 | 44141 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting631920201029-18Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting631920201029-18Operator - Principle - After Jan 106450Inv#070 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6320 | 20201029-19 | 53510511 | Access | 0 | Skidder | 171 | 3.5 | HR | 128.25 | 0 |  |  | 598.5 | 77.805 | 676.305 | 2020-10-29 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Access Maitenance being done across the access road | 5 | C076-C116 | Cook Lake | 0 | 44140 |  | 37 | 44141 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting632020201029-19Skidder 3.5598.5 | Corbiere and Sons Contracting632020201029-19Skidder 3.5598.5Inv#070 | [5 empty] | 1 | 598.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6320 | 20201029-19 | 53510511 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10.5 | Dynamic | 98.61 | 0 |  |  | 1380.54 | 179.4702 | 1560.0102 | 2020-10-29 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Access Maitenance being done across the access road | 5 | C076-C116 | Cook Lake | 0 | 44140 |  | 37 | 44141 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting632020201029-19Dozer D6 or equal- After Jan 1010.51380.54 | Corbiere and Sons Contracting632020201029-19Dozer D6 or equal- After Jan 1010.51380.54Inv#070 | [5 empty] | 1 | 1380.54 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6320 | 20201029-19 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-10-29 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Access Maitenance being done across the access road | 5 | C076-C116 | Cook Lake | 0 | 44140 |  | 37 | 44141 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting632020201029-19Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting632020201029-19Light Truck - Pick up- After Jan 101243.75Inv#070 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6320 | 20201029-19 | 53510511 | Access | 0 | Foreman | 95 | 3 | HR |  |  | 95 | 0 | 285 | 37.05 | 322.05 | 2020-10-29 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Access Maitenance being done across the access road | 5 | C076-C116 | Cook Lake | 0 | 44140 |  | 37 | 44141 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting632020201029-19Foreman3285 | Corbiere and Sons Contracting632020201029-19Foreman3285Inv#070 | [5 empty] | 1 | 285 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6320 | 20201029-19 | 53510511 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2020-10-29 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Access Maitenance being done across the access road | 5 | C076-C116 | Cook Lake | 0 | 44140 |  | 37 | 44141 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting632020201029-19L.O.A.3630 | Corbiere and Sons Contracting632020201029-19L.O.A.3630Inv#070 | [5 empty] | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6320 | 20201029-19 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 15 | HR |  |  | 75 | 0 | 1125 | 146.25 | 1271.25 | 2020-10-29 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter Access Maitenance being done across the access road | 5 | C076-C116 | Cook Lake | 0 | 44140 |  | 37 | 44141 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting632020201029-19Operator - Principle - After Jan 10151125 | Corbiere and Sons Contracting632020201029-19Operator - Principle - After Jan 10151125Inv#070 | [5 empty] | 1 | 1125 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6321 | 20201029-20 | 53510504 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 9 | Dynamic | 98.61 | 0 |  |  | 1183.32 | 153.8316 | 1337.1516 | 2020-10-29 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling being performed between C093-C099 | 5 | C093-C099 | Cook Lake | 0 | 44140 |  | 37 | 44141 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting632120201029-20Dozer D6 or equal- After Jan 1091183.32 | Corbiere and Sons Contracting632120201029-20Dozer D6 or equal- After Jan 1091183.32Inv#070 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1183.32 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6321 | 20201029-20 | 53510504 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10.5 | Dynamic | 110.22 | 0 |  |  | 1543.08 | 200.6004 | 1743.6804 | 2020-10-29 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling being performed between C093-C099 | 5 | C093-C099 | Cook Lake | 0 | 44140 |  | 37 | 44141 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting632120201029-20Excavator - 36 ton- After Jan 1010.51543.08 | Corbiere and Sons Contracting632120201029-20Excavator - 36 ton- After Jan 1010.51543.08Inv#070 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1543.08 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6321 | 20201029-20 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-10-29 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling being performed between C093-C099 | 5 | C093-C099 | Cook Lake | 0 | 44140 |  | 37 | 44141 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting632120201029-20Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting632120201029-20Light Truck - Pick up- After Jan 102487.5Inv#070 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6321 | 20201029-20 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 31.5 | Dynamic | 103.54 | 0 |  |  | 4348.575 | 565.3148 | 4913.8898 | 2020-10-29 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling being performed between C093-C099 | 5 | C093-C099 | Cook Lake | 0 | 44140 |  | 37 | 44141 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting632120201029-20Rock Truck - 30 Ton- After Jan 1031.54348.575 | Corbiere and Sons Contracting632120201029-20Rock Truck - 30 Ton- After Jan 1031.54348.575Inv#070 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 4348.575 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6321 | 20201029-20 | 53510504 | Access | 0 | Foreman | 95 | 4 | HR |  |  | 95 | 0 | 380 | 49.4 | 429.4 | 2020-10-29 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling being performed between C093-C099 | 5 | C093-C099 | Cook Lake | 0 | 44140 |  | 37 | 44141 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting632120201029-20Foreman4380 | Corbiere and Sons Contracting632120201029-20Foreman4380Inv#070 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6321 | 20201029-20 | 53510504 | Access | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2020-10-29 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling being performed between C093-C099 | 5 | C093-C099 | Cook Lake | 0 | 44140 |  | 37 | 44141 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting632120201029-20L.O.A.51050 | Corbiere and Sons Contracting632120201029-20L.O.A.51050Inv#070 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6321 | 20201029-20 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 21 | HR |  |  | 75 |  | 1575 | 204.75 | 1779.75 | 2020-10-29 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling being performed between C093-C099 | 5 | C093-C099 | Cook Lake | 0 | 44140 |  | 37 | 44141 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting632120201029-20Operator - Principle - After Jan 10211575 | Corbiere and Sons Contracting632120201029-20Operator - Principle - After Jan 10211575Inv#070 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1575 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6321 | 20201029-20 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 34.5 | HR |  |  | 70 | 0 | 2415 | 313.95 | 2728.95 | 2020-10-29 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling being performed between C093-C099 | 5 | C093-C099 | Cook Lake | 0 | 44140 |  | 37 | 44141 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting632120201029-20Driver - AZ - After Jan 1034.52415 | Corbiere and Sons Contracting632120201029-20Driver - AZ - After Jan 1034.52415Inv#070 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 2415 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6324 | 20201029-23 | 53510503 | Access | 0 | Skidder | 171 | 2 | HR | 128.25 | 0 |  |  | 342 | 44.46 | 386.46 | 2020-10-29 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Putting down corduroy from C097 and C081 | 5 | C081-C097 | Cook Lake | 0 | 44140 |  | 37 | 44141 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting632420201029-23Skidder 2342 | Corbiere and Sons Contracting632420201029-23Skidder 2342Inv#070 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 342 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6324 | 20201029-23 | 53510503 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9.5 | Dynamic | 110.22 | 0 |  |  | 1396.12 | 181.4956 | 1577.6156 | 2020-10-29 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Putting down corduroy from C097 and C081 | 5 | C081-C097 | Cook Lake | 0 | 44140 |  | 37 | 44141 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting632420201029-23Excavator - 36 ton- After Jan 109.51396.12 | Corbiere and Sons Contracting632420201029-23Excavator - 36 ton- After Jan 109.51396.12Inv#070 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 1396.12 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6324 | 20201029-23 | 53510503 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-10-29 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Putting down corduroy from C097 and C081 | 5 | C081-C097 | Cook Lake | 0 | 44140 |  | 37 | 44141 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting632420201029-23Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting632420201029-23Light Truck - Pick up- After Jan 101243.75Inv#070 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6324 | 20201029-23 | 53510503 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-10-29 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Putting down corduroy from C097 and C081 | 5 | C081-C097 | Cook Lake | 0 | 44140 |  | 37 | 44141 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting632420201029-23L.O.A.1210 | Corbiere and Sons Contracting632420201029-23L.O.A.1210Inv#070 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6324 | 20201029-23 | 53510503 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12.5 | HR |  |  | 75 | 0 | 937.5 | 121.875 | 1059.375 | 2020-10-29 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Putting down corduroy from C097 and C081 | 5 | C081-C097 | Cook Lake | 0 | 44140 |  | 37 | 44141 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting632420201029-23Operator - Principle - After Jan 1012.5937.5 | Corbiere and Sons Contracting632420201029-23Operator - Principle - After Jan 1012.5937.5Inv#070 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 937.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6325 | 20201029-24 | 53510512 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 2 | Dynamic | 98.61 | 0 |  |  | 262.96 | 34.1848 | 297.1448 | 2020-10-29 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Maintenance being done from C081 and C093 | 5 | C093-C116 | Cook Lake | 0 | 44140 |  | 37 | 44141 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting632520201029-24Dozer D6 or equal- After Jan 102262.96 | Corbiere and Sons Contracting632520201029-24Dozer D6 or equal- After Jan 102262.96Inv#070 | [5 empty] | 1 | 262.96 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6325 | 20201029-24 | 53510512 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 4 | Dynamic | 110.22 | 0 |  |  | 587.84 | 76.4192 | 664.2592 | 2020-10-29 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Maintenance being done from C081 and C093 | 5 | C093-C116 | Cook Lake | 0 | 44140 |  | 37 | 44141 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting632520201029-24Excavator - 36 ton- After Jan 104587.84 | Corbiere and Sons Contracting632520201029-24Excavator - 36 ton- After Jan 104587.84Inv#070 | [5 empty] | 1 | 587.84 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6325 | 20201029-24 | 53510512 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 75 | 0 | 450 | 58.5 | 508.5 | 2020-10-29 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Maintenance being done from C081 and C093 | 5 | C093-C116 | Cook Lake | 0 | 44140 |  | 37 | 44141 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting632520201029-24Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting632520201029-24Operator - Principle - After Jan 106450Inv#070 | [5 empty] | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6442 | 20201029-27 | 53510412 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 4 | Dynamic | 110.22 | 0 |  |  | 587.84 | 76.4192 | 664.2592 | 2020-10-29 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixing road and scraping hills from C007 | 4 | C001-C028 | Nishin Road | 0 | 44143 |  | 37 | 44144 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting644220201029-27Excavator - 36 ton- After Jan 104587.84 | Corbiere and Sons Contracting644220201029-27Excavator - 36 ton- After Jan 104587.84Inv#071 | [5 empty] | 1 | 587.84 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6442 | 20201029-27 | 53510412 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 4 | HR | 9.16 | 0 |  |  | 48.84 | 6.3492 | 55.1892 | 2020-10-29 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixing road and scraping hills from C007 | 4 | C001-C028 | Nishin Road | 0 | 44143 |  | 37 | 44144 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting644220201029-27Excavator Thumb - 30 - 50 ton- After Jan 10448.84 | Corbiere and Sons Contracting644220201029-27Excavator Thumb - 30 - 50 ton- After Jan 10448.84Inv#071 | [5 empty] | 1 | 48.84 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6442 | 20201029-27 | 53510412 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-10-29 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixing road and scraping hills from C007 | 4 | C001-C028 | Nishin Road | 0 | 44143 |  | 37 | 44144 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting644220201029-27L.O.A.1210 | Corbiere and Sons Contracting644220201029-27L.O.A.1210Inv#071 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6442 | 20201029-27 | 53510412 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 4 | HR |  |  | 75 | 0 | 300 | 39 | 339 | 2020-10-29 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixing road and scraping hills from C007 | 4 | C001-C028 | Nishin Road | 0 | 44143 |  | 37 | 44144 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting644220201029-27Operator - Principle - After Jan 104300 | Corbiere and Sons Contracting644220201029-27Operator - Principle - After Jan 104300Inv#071 | [5 empty] | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6329 | 20201030-14 | 53510504 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 56.5 | Dynamic | 41.4 | 0 |  |  | 3118.8 | 405.444 | 3524.244 | 2020-10-30 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling in WF5 from Worthington Bay pit to Cooks Lake Road | 5 | C093-C116 | Cook Lake | 0 | 44140 |  | 37 | 44141 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting632920201030-14Dump - Triaxle- After Jan 1056.53118.8 | Corbiere and Sons Contracting632920201030-14Dump - Triaxle- After Jan 1056.53118.8Inv#070 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 3118.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6329 | 20201030-14 | 53510504 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-10-30 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling in WF5 from Worthington Bay pit to Cooks Lake Road | 5 | C093-C116 | Cook Lake | 0 | 44140 |  | 37 | 44141 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting632920201030-14L.O.A.2420 | Corbiere and Sons Contracting632920201030-14L.O.A.2420Inv#070 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6329 | 20201030-14 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 56.5 | HR |  |  | 70 | 0 | 3955 | 514.15 | 4469.15 | 2020-10-30 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling in WF5 from Worthington Bay pit to Cooks Lake Road | 5 | C093-C116 | Cook Lake | 0 | 44140 |  | 37 | 44141 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting632920201030-14Driver - AZ - After Jan 1056.53955 | Corbiere and Sons Contracting632920201030-14Driver - AZ - After Jan 1056.53955Inv#070 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 3955 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6331 | 20201030-16 | 53510502 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 17 | Dynamic | 103.84 | 0 |  |  | 2353.65 | 305.9745 | 2659.6245 | 2020-10-30 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building road from C061, C067 and C069 - Rock Hammer working between C062 and C067 | 5 | C050-C069 | Antler Lake | 0 | 44140 |  | 37 | 44141 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting633120201030-16Excavator - 30 ton- After Jan 10172353.65 | Corbiere and Sons Contracting633120201030-16Excavator - 30 ton- After Jan 10172353.65Inv#070 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 2353.65 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6331 | 20201030-16 | 53510502 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10.5 | Dynamic | 110.22 | 0 |  |  | 1543.08 | 200.6004 | 1743.6804 | 2020-10-30 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building road from C061, C067 and C069 - Rock Hammer working between C062 and C067 | 5 | C050-C069 | Antler Lake | 0 | 44140 |  | 37 | 44141 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting633120201030-16Excavator - 36 ton- After Jan 1010.51543.08 | Corbiere and Sons Contracting633120201030-16Excavator - 36 ton- After Jan 1010.51543.08Inv#070 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 1543.08 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6331 | 20201030-16 | 53510502 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 6.5 | HR | 9.16 | 0 |  |  | 79.365 | 10.3174 | 89.6825 | 2020-10-30 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building road from C061, C067 and C069 - Rock Hammer working between C062 and C067 | 5 | C050-C069 | Antler Lake | 0 | 44140 |  | 37 | 44141 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting633120201030-16Excavator Thumb - 30 - 50 ton- After Jan 106.579.365 | Corbiere and Sons Contracting633120201030-16Excavator Thumb - 30 - 50 ton- After Jan 106.579.365Inv#070 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 79.365 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6331 | 20201030-16 | 53510502 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 10.5 | HR | 47.54 | 0 |  |  | 665.49 | 86.5137 | 752.0037 | 2020-10-30 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building road from C061, C067 and C069 - Rock Hammer working between C062 and C067 | 5 | C050-C069 | Antler Lake | 0 | 44140 |  | 37 | 44141 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting633120201030-16Excavator Hammer - 30 - 50 ton- After Jan 1010.5665.49 | Corbiere and Sons Contracting633120201030-16Excavator Hammer - 30 - 50 ton- After Jan 1010.5665.49Inv#070 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 665.49 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6331 | 20201030-16 | 53510502 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2020-10-30 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building road from C061, C067 and C069 - Rock Hammer working between C062 and C067 | 5 | C050-C069 | Antler Lake | 0 | 44140 |  | 37 | 44141 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting633120201030-16Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting633120201030-16Light Truck - Pick up- After Jan 103731.25Inv#070 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 731.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6331 | 20201030-16 | 53510502 | Access | 0 | Foreman | 95 | 10 | HR |  |  | 95 | 0 | 950 | 123.5 | 1073.5 | 2020-10-30 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building road from C061, C067 and C069 - Rock Hammer working between C062 and C067 | 5 | C050-C069 | Antler Lake | 0 | 44140 |  | 37 | 44141 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting633120201030-16Foreman10950 | Corbiere and Sons Contracting633120201030-16Foreman10950Inv#070 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 950 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6331 | 20201030-16 | 53510502 | Access | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2020-10-30 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building road from C061, C067 and C069 - Rock Hammer working between C062 and C067 | 5 | C050-C069 | Antler Lake | 0 | 44140 |  | 37 | 44141 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting633120201030-16L.O.A.51050 | Corbiere and Sons Contracting633120201030-16L.O.A.51050Inv#070 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6331 | 20201030-16 | 53510502 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 41.5 | HR |  |  | 75 | 0 | 3112.5 | 404.625 | 3517.125 | 2020-10-30 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building road from C061, C067 and C069 - Rock Hammer working between C062 and C067 | 5 | C050-C069 | Antler Lake | 0 | 44140 |  | 37 | 44141 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting633120201030-16Operator - Principle - After Jan 1041.53112.5 | Corbiere and Sons Contracting633120201030-16Operator - Principle - After Jan 1041.53112.5Inv#070 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 3112.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6334 | 20201030-19 | 53510504 | Access | 0 | Loader JD 524 to 624 or equal | 99 | 10.5 | HR | 74.25 | 0 |  |  | 1039.5 | 135.135 | 1174.635 | 2020-10-30 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling and spread from C093 Eastward | 5 | C093-C116 | Cook Lake | 0 | 44140 |  | 37 | 44141 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting633420201030-19Loader JD 524 to 624 or equal10.51039.5 | Corbiere and Sons Contracting633420201030-19Loader JD 524 to 624 or equal10.51039.5Inv#070 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1039.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6334 | 20201030-19 | 53510504 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10.5 | Dynamic | 98.61 | 0 |  |  | 1380.54 | 179.4702 | 1560.0102 | 2020-10-30 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling and spread from C093 Eastward | 5 | C093-C116 | Cook Lake | 0 | 44140 |  | 37 | 44141 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting633420201030-19Dozer D6 or equal- After Jan 1010.51380.54 | Corbiere and Sons Contracting633420201030-19Dozer D6 or equal- After Jan 1010.51380.54Inv#070 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1380.54 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6334 | 20201030-19 | 53510504 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 6 | Dynamic | 110.22 | 0 |  |  | 881.76 | 114.6288 | 996.3888 | 2020-10-30 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling and spread from C093 Eastward | 5 | C093-C116 | Cook Lake | 0 | 44140 |  | 37 | 44141 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting633420201030-19Excavator - 36 ton- After Jan 106881.76 | Corbiere and Sons Contracting633420201030-19Excavator - 36 ton- After Jan 106881.76Inv#070 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 881.76 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6334 | 20201030-19 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-10-30 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling and spread from C093 Eastward | 5 | C093-C116 | Cook Lake | 0 | 44140 |  | 37 | 44141 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting633420201030-19Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting633420201030-19Light Truck - Pick up- After Jan 102487.5Inv#070 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6334 | 20201030-19 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 31.5 | Dynamic | 103.54 | 0 |  |  | 4348.575 | 565.3148 | 4913.8898 | 2020-10-30 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling and spread from C093 Eastward | 5 | C093-C116 | Cook Lake | 0 | 44140 |  | 37 | 44141 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting633420201030-19Rock Truck - 30 Ton- After Jan 1031.54348.575 | Corbiere and Sons Contracting633420201030-19Rock Truck - 30 Ton- After Jan 1031.54348.575Inv#070 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 4348.575 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6334 | 20201030-19 | 53510504 | Access | 0 | Foreman | 95 | 6 | HR |  |  | 95 | 0 | 570 | 74.1 | 644.1 | 2020-10-30 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling and spread from C093 Eastward | 5 | C093-C116 | Cook Lake | 0 | 44140 |  | 37 | 44141 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting633420201030-19Foreman6570 | Corbiere and Sons Contracting633420201030-19Foreman6570Inv#070 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 570 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6334 | 20201030-19 | 53510504 | Access | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2020-10-30 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling and spread from C093 Eastward | 5 | C093-C116 | Cook Lake | 0 | 44140 |  | 37 | 44141 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting633420201030-19L.O.A.51050 | Corbiere and Sons Contracting633420201030-19L.O.A.51050Inv#070 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6334 | 20201030-19 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 29 | HR |  |  | 75 | 0 | 2175 | 282.75 | 2457.75 | 2020-10-30 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling and spread from C093 Eastward | 5 | C093-C116 | Cook Lake | 0 | 44140 |  | 37 | 44141 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting633420201030-19Operator - Principle - After Jan 10292175 | Corbiere and Sons Contracting633420201030-19Operator - Principle - After Jan 10292175Inv#070 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 2175 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6334 | 20201030-19 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 34.5 | HR |  |  | 70 | 0 | 2415 | 313.95 | 2728.95 | 2020-10-30 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling and spread from C093 Eastward | 5 | C093-C116 | Cook Lake | 0 | 44140 |  | 37 | 44141 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting633420201030-19Driver - AZ - After Jan 1034.52415 | Corbiere and Sons Contracting633420201030-19Driver - AZ - After Jan 1034.52415Inv#070 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 2415 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6336 | 20201030-21 | 53510512 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 4 | Dynamic | 98.61 | 0 |  |  | 525.92 | 68.3696 | 594.2896 | 2020-10-30 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Greg grom doing road maintenance from 6:30-11:00 | 5 | C093-C116 | Cook Lake | 0 | 44140 |  | 37 | 44141 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting633620201030-21Dozer D6 or equal- After Jan 104525.92 | Corbiere and Sons Contracting633620201030-21Dozer D6 or equal- After Jan 104525.92Inv#070 | [5 empty] | 1 | 525.92 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6336 | 20201030-21 | 53510512 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 4.5 | HR |  |  | 75 | 0 | 337.5 | 43.875 | 381.375 | 2020-10-30 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Greg grom doing road maintenance from 6:30-11:00 | 5 | C093-C116 | Cook Lake | 0 | 44140 |  | 37 | 44141 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting633620201030-21Operator - Principle - After Jan 104.5337.5 | Corbiere and Sons Contracting633620201030-21Operator - Principle - After Jan 104.5337.5Inv#070 | [5 empty] | 1 | 337.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6230 | 20201030-6 | 53510312 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10 | Dynamic | 98.61 | 0 |  |  | 1314.8 | 170.924 | 1485.724 | 2020-10-30 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-08 and DZ-05 did road miantenance for access, pulled Valard and contractor trucks through bad spots in the road and fixed where possible. | 3 | B078-B084 | Red Rock Rd No. 7 | 0 | 44135 |  | 37 | 44136 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting623020201030-6Dozer D6 or equal- After Jan 10101314.8 | Corbiere and Sons Contracting623020201030-6Dozer D6 or equal- After Jan 10101314.8Inv#070 | [5 empty] | 1 | 1314.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6230 | 20201030-6 | 53510312 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10 | Dynamic | 103.84 | 0 |  |  | 1384.5 | 179.985 | 1564.485 | 2020-10-30 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-08 and DZ-05 did road miantenance for access, pulled Valard and contractor trucks through bad spots in the road and fixed where possible. | 3 | B078-B084 | Red Rock Rd No. 7 | 0 | 44135 |  | 37 | 44136 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting623020201030-6Excavator - 30 ton- After Jan 10101384.5 | Corbiere and Sons Contracting623020201030-6Excavator - 30 ton- After Jan 10101384.5Inv#070 | [5 empty] | 1 | 1384.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6230 | 20201030-6 | 53510312 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 9.16 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2020-10-30 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-08 and DZ-05 did road miantenance for access, pulled Valard and contractor trucks through bad spots in the road and fixed where possible. | 3 | B078-B084 | Red Rock Rd No. 7 | 0 | 44135 |  | 37 | 44136 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting623020201030-6Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting623020201030-6Excavator Thumb - 30 - 50 ton- After Jan 1010122.1Inv#070 | [5 empty] | 1 | 122.1 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6230 | 20201030-6 | 53510312 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-10-30 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-08 and DZ-05 did road miantenance for access, pulled Valard and contractor trucks through bad spots in the road and fixed where possible. | 3 | B078-B084 | Red Rock Rd No. 7 | 0 | 44135 |  | 37 | 44136 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting623020201030-6Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting623020201030-6Light Truck - Pick up- After Jan 101243.75Inv#070 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6230 | 20201030-6 | 53510312 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 22 | HR |  |  | 75 | 0 | 1650 | 214.5 | 1864.5 | 2020-10-30 | 1 | Inv#070 | 44144 | 124 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-08 and DZ-05 did road miantenance for access, pulled Valard and contractor trucks through bad spots in the road and fixed where possible. | 3 | B078-B084 | Red Rock Rd No. 7 | 0 | 44135 |  | 37 | 44136 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting623020201030-6Operator - Principle - After Jan 10221650 | Corbiere and Sons Contracting623020201030-6Operator - Principle - After Jan 10221650Inv#070 | [5 empty] | 1 | 1650 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6372 | 20201031-10 | 53510504 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 29.5 | Dynamic | 41.4 | 0 |  |  | 1628.4 | 211.692 | 1840.092 | 2020-10-31 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel hauling from worthington bay pit to Cooks Lake Road E access | 5 | C076-C116 | Cook Lake | 0 | 44143 |  | 37 | 44144 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting637220201031-10Dump - Triaxle- After Jan 1029.51628.4 | Corbiere and Sons Contracting637220201031-10Dump - Triaxle- After Jan 1029.51628.4Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1628.4 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6372 | 20201031-10 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2020-10-31 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel hauling from worthington bay pit to Cooks Lake Road E access | 5 | C076-C116 | Cook Lake | 0 | 44143 |  | 37 | 44144 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting637220201031-10Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting637220201031-10Light Truck - Pick up- After Jan 103731.25Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 731.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6372 | 20201031-10 | 53510504 | Access | 0 | Construction Coordinator | 80 | 18 | HR |  |  | 80 | 0 | 1440 | 187.2 | 1627.2 | 2020-10-31 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel hauling from worthington bay pit to Cooks Lake Road E access | 5 | C076-C116 | Cook Lake | 0 | 44143 |  | 37 | 44144 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting637220201031-10Construction Coordinator181440 | Corbiere and Sons Contracting637220201031-10Construction Coordinator181440Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1440 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6372 | 20201031-10 | 53510504 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2020-10-31 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel hauling from worthington bay pit to Cooks Lake Road E access | 5 | C076-C116 | Cook Lake | 0 | 44143 |  | 37 | 44144 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting637220201031-10L.O.A.4840 | Corbiere and Sons Contracting637220201031-10L.O.A.4840Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6372 | 20201031-10 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 29.5 | HR |  |  | 70 | 0 | 2065 | 268.45 | 2333.45 | 2020-10-31 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel hauling from worthington bay pit to Cooks Lake Road E access | 5 | C076-C116 | Cook Lake | 0 | 44143 |  | 37 | 44144 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting637220201031-10Driver - AZ - After Jan 1029.52065 | Corbiere and Sons Contracting637220201031-10Driver - AZ - After Jan 1029.52065Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 2065 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6374 | 20201031-12 | 53510502 | Access | 0 | Skidder | 171 | 3 | HR | 128.25 | 0 |  |  | 513 | 66.69 | 579.69 | 2020-10-31 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building road from C061 and C067-C069 - Rock hammer working from C067-C069 | 5 | C050-C069 | Antler Lake | 0 | 44143 |  | 37 | 44144 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting637420201031-12Skidder 3513 | Corbiere and Sons Contracting637420201031-12Skidder 3513Inv#071 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 513 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6374 | 20201031-12 | 53510502 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 8 | Dynamic | 98.61 | 0 |  |  | 1051.84 | 136.7392 | 1188.5792 | 2020-10-31 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building road from C061 and C067-C069 - Rock hammer working from C067-C069 | 5 | C050-C069 | Antler Lake | 0 | 44143 |  | 37 | 44144 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting637420201031-12Dozer D6 or equal- After Jan 1081051.84 | Corbiere and Sons Contracting637420201031-12Dozer D6 or equal- After Jan 1081051.84Inv#071 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 1051.84 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6374 | 20201031-12 | 53510502 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10.5 | Dynamic | 103.84 | 0 |  |  | 1453.725 | 188.9843 | 1642.7093 | 2020-10-31 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building road from C061 and C067-C069 - Rock hammer working from C067-C069 | 5 | C050-C069 | Antler Lake | 0 | 44143 |  | 37 | 44144 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting637420201031-12Excavator - 30 ton- After Jan 1010.51453.725 | Corbiere and Sons Contracting637420201031-12Excavator - 30 ton- After Jan 1010.51453.725Inv#071 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 1453.725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6374 | 20201031-12 | 53510502 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10.5 | Dynamic | 110.22 | 0 |  |  | 1543.08 | 200.6004 | 1743.6804 | 2020-10-31 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building road from C061 and C067-C069 - Rock hammer working from C067-C069 | 5 | C050-C069 | Antler Lake | 0 | 44143 |  | 37 | 44144 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting637420201031-12Excavator - 36 ton- After Jan 1010.51543.08 | Corbiere and Sons Contracting637420201031-12Excavator - 36 ton- After Jan 1010.51543.08Inv#071 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 1543.08 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6374 | 20201031-12 | 53510502 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 10.5 | HR | 47.54 | 0 |  |  | 665.49 | 86.5137 | 752.0037 | 2020-10-31 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building road from C061 and C067-C069 - Rock hammer working from C067-C069 | 5 | C050-C069 | Antler Lake | 0 | 44143 |  | 37 | 44144 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting637420201031-12Excavator Hammer - 30 - 50 ton- After Jan 1010.5665.49 | Corbiere and Sons Contracting637420201031-12Excavator Hammer - 30 - 50 ton- After Jan 1010.5665.49Inv#071 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 665.49 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6374 | 20201031-12 | 53510502 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2020-10-31 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building road from C061 and C067-C069 - Rock hammer working from C067-C069 | 5 | C050-C069 | Antler Lake | 0 | 44143 |  | 37 | 44144 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting637420201031-12Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting637420201031-12Light Truck - Pick up- After Jan 103731.25Inv#071 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 731.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6374 | 20201031-12 | 53510502 | Access | 0 | Foreman | 95 | 8 | HR |  |  | 95 | 0 | 760 | 98.8 | 858.8 | 2020-10-31 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building road from C061 and C067-C069 - Rock hammer working from C067-C069 | 5 | C050-C069 | Antler Lake | 0 | 44143 |  | 37 | 44144 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting637420201031-12Foreman8760 | Corbiere and Sons Contracting637420201031-12Foreman8760Inv#071 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 760 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6374 | 20201031-12 | 53510502 | Access | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2020-10-31 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building road from C061 and C067-C069 - Rock hammer working from C067-C069 | 5 | C050-C069 | Antler Lake | 0 | 44143 |  | 37 | 44144 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting637420201031-12L.O.A.61260 | Corbiere and Sons Contracting637420201031-12L.O.A.61260Inv#071 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6374 | 20201031-12 | 53510502 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 34 | HR |  |  | 75 | 0 | 2550 | 331.5 | 2881.5 | 2020-10-31 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building road from C061 and C067-C069 - Rock hammer working from C067-C069 | 5 | C050-C069 | Antler Lake | 0 | 44143 |  | 37 | 44144 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting637420201031-12Operator - Principle - After Jan 10342550 | Corbiere and Sons Contracting637420201031-12Operator - Principle - After Jan 10342550Inv#071 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 2550 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6374 | 20201031-12 | 53510502 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 5 | HR |  |  | 70 | 0 | 350 | 45.5 | 395.5 | 2020-10-31 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building road from C061 and C067-C069 - Rock hammer working from C067-C069 | 5 | C050-C069 | Antler Lake | 0 | 44143 |  | 37 | 44144 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting637420201031-12Driver - AZ - After Jan 105350 | Corbiere and Sons Contracting637420201031-12Driver - AZ - After Jan 105350Inv#071 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 350 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6378 | 20201031-16 | 53510502 | Access | 0 | Skidder | 171 | 8 | HR | 128.25 | 0 |  |  | 1368 | 177.84 | 1545.84 | 2020-10-31 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Putting down corduroy from C098-C099 | 5 | C093-C116 | Cook Lake | 0 | 44143 |  | 37 | 44144 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting637820201031-16Skidder 81368 | Corbiere and Sons Contracting637820201031-16Skidder 81368Inv#071 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 1368 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6378 | 20201031-16 | 53510502 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 4.5 | Dynamic | 103.84 | 0 |  |  | 623.025 | 80.9933 | 704.0182 | 2020-10-31 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Putting down corduroy from C098-C099 | 5 | C093-C116 | Cook Lake | 0 | 44143 |  | 37 | 44144 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting637820201031-16Excavator - 30 ton- After Jan 104.5623.025 | Corbiere and Sons Contracting637820201031-16Excavator - 30 ton- After Jan 104.5623.025Inv#071 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 623.025 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6378 | 20201031-16 | 53510502 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 8 | Dynamic | 110.22 | 0 |  |  | 1175.68 | 152.8384 | 1328.5184 | 2020-10-31 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Putting down corduroy from C098-C099 | 5 | C093-C116 | Cook Lake | 0 | 44143 |  | 37 | 44144 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting637820201031-16Excavator - 36 ton- After Jan 1081175.68 | Corbiere and Sons Contracting637820201031-16Excavator - 36 ton- After Jan 1081175.68Inv#071 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 1175.68 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6378 | 20201031-16 | 53510502 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 4.5 | HR | 9.16 | 0 |  |  | 54.945 | 7.1429 | 62.0879 | 2020-10-31 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Putting down corduroy from C098-C099 | 5 | C093-C116 | Cook Lake | 0 | 44143 |  | 37 | 44144 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting637820201031-16Excavator Thumb - 30 - 50 ton- After Jan 104.554.945 | Corbiere and Sons Contracting637820201031-16Excavator Thumb - 30 - 50 ton- After Jan 104.554.945Inv#071 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 54.945 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6378 | 20201031-16 | 53510502 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-10-31 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Putting down corduroy from C098-C099 | 5 | C093-C116 | Cook Lake | 0 | 44143 |  | 37 | 44144 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting637820201031-16Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting637820201031-16Light Truck - Pick up- After Jan 101243.75Inv#071 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6378 | 20201031-16 | 53510502 | Access | 0 | Foreman | 95 | 4 | HR |  |  | 95 | 0 | 380 | 49.4 | 429.4 | 2020-10-31 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Putting down corduroy from C098-C099 | 5 | C093-C116 | Cook Lake | 0 | 44143 |  | 37 | 44144 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting637820201031-16Foreman4380 | Corbiere and Sons Contracting637820201031-16Foreman4380Inv#071 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6378 | 20201031-16 | 53510502 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2020-10-31 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Putting down corduroy from C098-C099 | 5 | C093-C116 | Cook Lake | 0 | 44143 |  | 37 | 44144 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting637820201031-16L.O.A.4840 | Corbiere and Sons Contracting637820201031-16L.O.A.4840Inv#071 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6378 | 20201031-16 | 53510502 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 21 | HR |  |  | 75 | 0 | 1575 | 204.75 | 1779.75 | 2020-10-31 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Putting down corduroy from C098-C099 | 5 | C093-C116 | Cook Lake | 0 | 44143 |  | 37 | 44144 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting637820201031-16Operator - Principle - After Jan 10211575 | Corbiere and Sons Contracting637820201031-16Operator - Principle - After Jan 10211575Inv#071 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 1575 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6379 | 20201031-17 | 53530501 | Rig/Access Mats | 0 | Feller Buncher | 240 | 3 | HR | 180 | 0 |  |  | 720 | 93.6 | 813.6 | 2020-10-31 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Rig/Access Mat Handling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rig mats being moved and installed for temp crossing 7541 | 5 | C093-C116 | Cook Lake | 0 | 44143 |  | 37 | 44144 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting637920201031-17Feller Buncher3720 | Corbiere and Sons Contracting637920201031-17Feller Buncher3720Inv#071 |  |  | WF5-WaterCrossing |  |  | 1 | 720 | WC403 | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6379 | 20201031-17 | 53530501 | Rig/Access Mats | 0 | Skidder | 171 | 3 | HR | 128.25 | 0 |  |  | 513 | 66.69 | 579.69 | 2020-10-31 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Rig/Access Mat Handling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rig mats being moved and installed for temp crossing 7541 | 5 | C093-C116 | Cook Lake | 0 | 44143 |  | 37 | 44144 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting637920201031-17Skidder 3513 | Corbiere and Sons Contracting637920201031-17Skidder 3513Inv#071 |  |  | WF5-WaterCrossing |  |  | 1 | 513 | WC403 | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6379 | 20201031-17 | 53530501 | Rig/Access Mats | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 3 | Dynamic | 110.22 | 0 |  |  | 440.88 | 57.3144 | 498.1944 | 2020-10-31 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Rig/Access Mat Handling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rig mats being moved and installed for temp crossing 7541 | 5 | C093-C116 | Cook Lake | 0 | 44143 |  | 37 | 44144 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting637920201031-17Excavator - 36 ton- After Jan 103440.88 | Corbiere and Sons Contracting637920201031-17Excavator - 36 ton- After Jan 103440.88Inv#071 |  |  | WF5-WaterCrossing |  |  | 1 | 440.88 | WC403 | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6379 | 20201031-17 | 53530501 | Rig/Access Mats | 0 | Foreman | 95 | 2 | HR |  |  | 95 | 0 | 190 | 24.7 | 214.7 | 2020-10-31 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Rig/Access Mat Handling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rig mats being moved and installed for temp crossing 7541 | 5 | C093-C116 | Cook Lake | 0 | 44143 |  | 37 | 44144 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting637920201031-17Foreman2190 | Corbiere and Sons Contracting637920201031-17Foreman2190Inv#071 |  |  | WF5-WaterCrossing |  |  | 1 | 190 | WC403 | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6379 | 20201031-17 | 53530501 | Rig/Access Mats | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-10-31 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Rig/Access Mat Handling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rig mats being moved and installed for temp crossing 7541 | 5 | C093-C116 | Cook Lake | 0 | 44143 |  | 37 | 44144 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting637920201031-17L.O.A.1210 | Corbiere and Sons Contracting637920201031-17L.O.A.1210Inv#071 |  |  | WF5-WaterCrossing |  |  | 1 | 210 | WC403 | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6379 | 20201031-17 | 53530501 | Rig/Access Mats | 0 | Operator - Principle - After Jan 10 | 75 | 9.5 | HR |  |  | 75 | 0 | 712.5 | 92.625 | 805.125 | 2020-10-31 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Rig/Access Mat Handling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rig mats being moved and installed for temp crossing 7541 | 5 | C093-C116 | Cook Lake | 0 | 44143 |  | 37 | 44144 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting637920201031-17Operator - Principle - After Jan 109.5712.5 | Corbiere and Sons Contracting637920201031-17Operator - Principle - After Jan 109.5712.5Inv#071 |  |  | WF5-WaterCrossing |  |  | 1 | 712.5 | WC403 | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6380 | 20201031-18 | 53510504 | Access | 0 | Loader JD 524 to 624 or equal | 99 | 10.5 | HR | 74.25 | 0 |  |  | 1039.5 | 135.135 | 1174.635 | 2020-10-31 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling in Cooks Lake Road E for areas from C094-C099 | 5 | C093-C116 | Cook Lake | 0 | 44143 |  | 37 | 44144 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting638020201031-18Loader JD 524 to 624 or equal10.51039.5 | Corbiere and Sons Contracting638020201031-18Loader JD 524 to 624 or equal10.51039.5Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1039.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6380 | 20201031-18 | 53510504 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 9 | Dynamic | 98.61 | 0 |  |  | 1183.32 | 153.8316 | 1337.1516 | 2020-10-31 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling in Cooks Lake Road E for areas from C094-C099 | 5 | C093-C116 | Cook Lake | 0 | 44143 |  | 37 | 44144 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting638020201031-18Dozer D6 or equal- After Jan 1091183.32 | Corbiere and Sons Contracting638020201031-18Dozer D6 or equal- After Jan 1091183.32Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1183.32 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6380 | 20201031-18 | 53510504 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10.5 | Dynamic | 103.84 | 0 |  |  | 1453.725 | 188.9843 | 1642.7093 | 2020-10-31 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling in Cooks Lake Road E for areas from C094-C099 | 5 | C093-C116 | Cook Lake | 0 | 44143 |  | 37 | 44144 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting638020201031-18Excavator - 30 ton- After Jan 1010.51453.725 | Corbiere and Sons Contracting638020201031-18Excavator - 30 ton- After Jan 1010.51453.725Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1453.725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6380 | 20201031-18 | 53510504 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10.5 | HR | 9.16 | 0 |  |  | 128.205 | 16.6667 | 144.8716 | 2020-10-31 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling in Cooks Lake Road E for areas from C094-C099 | 5 | C093-C116 | Cook Lake | 0 | 44143 |  | 37 | 44144 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting638020201031-18Excavator Thumb - 30 - 50 ton- After Jan 1010.5128.205 | Corbiere and Sons Contracting638020201031-18Excavator Thumb - 30 - 50 ton- After Jan 1010.5128.205Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 128.205 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6380 | 20201031-18 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2020-10-31 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling in Cooks Lake Road E for areas from C094-C099 | 5 | C093-C116 | Cook Lake | 0 | 44143 |  | 37 | 44144 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting638020201031-18Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting638020201031-18Light Truck - Pick up- After Jan 103731.25Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 731.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6380 | 20201031-18 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 31.5 | Dynamic | 103.54 | 0 |  |  | 4348.575 | 565.3148 | 4913.8898 | 2020-10-31 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling in Cooks Lake Road E for areas from C094-C099 | 5 | C093-C116 | Cook Lake | 0 | 44143 |  | 37 | 44144 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting638020201031-18Rock Truck - 30 Ton- After Jan 1031.54348.575 | Corbiere and Sons Contracting638020201031-18Rock Truck - 30 Ton- After Jan 1031.54348.575Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 4348.575 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6380 | 20201031-18 | 53510504 | Access | 0 | Foreman | 95 | 6 | HR |  |  | 95 | 0 | 570 | 74.1 | 644.1 | 2020-10-31 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling in Cooks Lake Road E for areas from C094-C099 | 5 | C093-C116 | Cook Lake | 0 | 44143 |  | 37 | 44144 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting638020201031-18Foreman6570 | Corbiere and Sons Contracting638020201031-18Foreman6570Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 570 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6380 | 20201031-18 | 53510504 | Access | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2020-10-31 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling in Cooks Lake Road E for areas from C094-C099 | 5 | C093-C116 | Cook Lake | 0 | 44143 |  | 37 | 44144 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting638020201031-18L.O.A.61260 | Corbiere and Sons Contracting638020201031-18L.O.A.61260Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6380 | 20201031-18 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 32 | HR |  |  | 75 | 0 | 2400 | 312 | 2712 | 2020-10-31 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling in Cooks Lake Road E for areas from C094-C099 | 5 | C093-C116 | Cook Lake | 0 | 44143 |  | 37 | 44144 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting638020201031-18Operator - Principle - After Jan 10322400 | Corbiere and Sons Contracting638020201031-18Operator - Principle - After Jan 10322400Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 2400 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6380 | 20201031-18 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 34.5 | HR |  |  | 70 | 0 | 2415 | 313.95 | 2728.95 | 2020-10-31 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling in Cooks Lake Road E for areas from C094-C099 | 5 | C093-C116 | Cook Lake | 0 | 44143 |  | 37 | 44144 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting638020201031-18Driver - AZ - After Jan 1034.52415 | Corbiere and Sons Contracting638020201031-18Driver - AZ - After Jan 1034.52415Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 2415 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6341 | 20201031-5 | 53510312 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10 | Dynamic | 98.61 | 0 |  |  | 1314.8 | 170.924 | 1485.724 | 2020-10-31 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer trimmed and fixed road in bad spots from B074-B084 | 3 | B077-B084 | Red Rock Road | 0 | 44142 |  | 37 | 44142 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting634120201031-5Dozer D6 or equal- After Jan 10101314.8 | Corbiere and Sons Contracting634120201031-5Dozer D6 or equal- After Jan 10101314.8Inv#071 | [5 empty] | 1 | 1314.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6341 | 20201031-5 | 53510312 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-10-31 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer trimmed and fixed road in bad spots from B074-B084 | 3 | B077-B084 | Red Rock Road | 0 | 44142 |  | 37 | 44142 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting634120201031-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting634120201031-5Light Truck - Pick up- After Jan 101243.75Inv#071 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6341 | 20201031-5 | 53510312 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2020-10-31 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer trimmed and fixed road in bad spots from B074-B084 | 3 | B077-B084 | Red Rock Road | 0 | 44142 |  | 37 | 44142 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting634120201031-5Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting634120201031-5Operator - Principle - After Jan 1011825Inv#071 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6389 | 20201101-10 | 53510511 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10.5 | Dynamic | 98.61 | 0 |  |  | 1380.54 | 179.4702 | 1560.0102 | 2020-11-01 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dz doing winter maintenance on roads all day | 5 | C093-C116 | Cook Lake | 0 | 44143 |  | 37 | 44144 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting638920201101-10Dozer D6 or equal- After Jan 1010.51380.54 | Corbiere and Sons Contracting638920201101-10Dozer D6 or equal- After Jan 1010.51380.54Inv#071 | [5 empty] | 1 | 1380.54 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6389 | 20201101-10 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-11-01 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dz doing winter maintenance on roads all day | 5 | C093-C116 | Cook Lake | 0 | 44143 |  | 37 | 44144 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting638920201101-10Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting638920201101-10Light Truck - Pick up- After Jan 101243.75Inv#071 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6389 | 20201101-10 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-11-01 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dz doing winter maintenance on roads all day | 5 | C093-C116 | Cook Lake | 0 | 44143 |  | 37 | 44144 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting638920201101-10L.O.A.1210 | Corbiere and Sons Contracting638920201101-10L.O.A.1210Inv#071 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6389 | 20201101-10 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-11-01 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dz doing winter maintenance on roads all day | 5 | C093-C116 | Cook Lake | 0 | 44143 |  | 37 | 44144 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting638920201101-10Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting638920201101-10Operator - Principle - After Jan 1011.5862.5Inv#071 | [5 empty] | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6385 | 20201101-6 | 53510502 | Access | 0 | Skidder | 171 | 10.5 | HR | 128.25 | 0 |  |  | 1795.5 | 233.415 | 2028.915 | 2020-11-01 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building new road from C067 and C069 - Skidding of trees to C061 | 5 | C050-C069 | Antler Lake | 0 | 44143 |  | 37 | 44144 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting638520201101-6Skidder 10.51795.5 | Corbiere and Sons Contracting638520201101-6Skidder 10.51795.5Inv#071 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 1795.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6385 | 20201101-6 | 53510502 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 8 | Dynamic | 98.61 | 0 |  |  | 1051.84 | 136.7392 | 1188.5792 | 2020-11-01 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building new road from C067 and C069 - Skidding of trees to C061 | 5 | C050-C069 | Antler Lake | 0 | 44143 |  | 37 | 44144 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting638520201101-6Dozer D6 or equal- After Jan 1081051.84 | Corbiere and Sons Contracting638520201101-6Dozer D6 or equal- After Jan 1081051.84Inv#071 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 1051.84 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6385 | 20201101-6 | 53510502 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 18.5 | Dynamic | 103.84 | 0 |  |  | 2561.325 | 332.9722 | 2894.2973 | 2020-11-01 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building new road from C067 and C069 - Skidding of trees to C061 | 5 | C050-C069 | Antler Lake | 0 | 44143 |  | 37 | 44144 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting638520201101-6Excavator - 30 ton- After Jan 1018.52561.325 | Corbiere and Sons Contracting638520201101-6Excavator - 30 ton- After Jan 1018.52561.325Inv#071 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 2561.325 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6385 | 20201101-6 | 53510502 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9.5 | Dynamic | 110.22 | 0 |  |  | 1396.12 | 181.4956 | 1577.6156 | 2020-11-01 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building new road from C067 and C069 - Skidding of trees to C061 | 5 | C050-C069 | Antler Lake | 0 | 44143 |  | 37 | 44144 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting638520201101-6Excavator - 36 ton- After Jan 109.51396.12 | Corbiere and Sons Contracting638520201101-6Excavator - 36 ton- After Jan 109.51396.12Inv#071 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 1396.12 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6385 | 20201101-6 | 53510502 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10.5 | HR | 9.16 | 0 |  |  | 128.205 | 16.6667 | 144.8716 | 2020-11-01 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building new road from C067 and C069 - Skidding of trees to C061 | 5 | C050-C069 | Antler Lake | 0 | 44143 |  | 37 | 44144 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting638520201101-6Excavator Thumb - 30 - 50 ton- After Jan 1010.5128.205 | Corbiere and Sons Contracting638520201101-6Excavator Thumb - 30 - 50 ton- After Jan 1010.5128.205Inv#071 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 128.205 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6385 | 20201101-6 | 53510502 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 9.5 | HR | 47.54 | 0 |  |  | 602.11 | 78.2743 | 680.3843 | 2020-11-01 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building new road from C067 and C069 - Skidding of trees to C061 | 5 | C050-C069 | Antler Lake | 0 | 44143 |  | 37 | 44144 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting638520201101-6Excavator Hammer - 30 - 50 ton- After Jan 109.5602.11 | Corbiere and Sons Contracting638520201101-6Excavator Hammer - 30 - 50 ton- After Jan 109.5602.11Inv#071 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 602.11 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6385 | 20201101-6 | 53510502 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-11-01 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building new road from C067 and C069 - Skidding of trees to C061 | 5 | C050-C069 | Antler Lake | 0 | 44143 |  | 37 | 44144 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting638520201101-6Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting638520201101-6Light Truck - Pick up- After Jan 102487.5Inv#071 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6385 | 20201101-6 | 53510502 | Access | 0 | Light Truck w/ Tandum Trailer- After Jan 10 | 337.5 | 1 | DAY | 253.13 | 0 |  |  | 337.5 | 43.875 | 381.375 | 2020-11-01 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building new road from C067 and C069 - Skidding of trees to C061 | 5 | C050-C069 | Antler Lake | 0 | 44143 |  | 37 | 44144 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting638520201101-6Light Truck w/ Tandum Trailer- After Jan 101337.5 | Corbiere and Sons Contracting638520201101-6Light Truck w/ Tandum Trailer- After Jan 101337.5Inv#071 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 337.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6385 | 20201101-6 | 53510502 | Access | 0 | Foreman | 95 | 10 | HR |  |  | 95 | 0 | 950 | 123.5 | 1073.5 | 2020-11-01 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building new road from C067 and C069 - Skidding of trees to C061 | 5 | C050-C069 | Antler Lake | 0 | 44143 |  | 37 | 44144 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting638520201101-6Foreman10950 | Corbiere and Sons Contracting638520201101-6Foreman10950Inv#071 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 950 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6385 | 20201101-6 | 53510502 | Access | 0 | L.O.A. | 210 | 7 | DAY |  |  |  | 0 | 1470 | 191.1 | 1661.1 | 2020-11-01 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building new road from C067 and C069 - Skidding of trees to C061 | 5 | C050-C069 | Antler Lake | 0 | 44143 |  | 37 | 44144 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting638520201101-6L.O.A.71470 | Corbiere and Sons Contracting638520201101-6L.O.A.71470Inv#071 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 1470 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6385 | 20201101-6 | 53510502 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 49 | HR |  |  | 75 | 0 | 3675 | 477.75 | 4152.75 | 2020-11-01 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building new road from C067 and C069 - Skidding of trees to C061 | 5 | C050-C069 | Antler Lake | 0 | 44143 |  | 37 | 44144 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting638520201101-6Operator - Principle - After Jan 10493675 | Corbiere and Sons Contracting638520201101-6Operator - Principle - After Jan 10493675Inv#071 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 3675 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6385 | 20201101-6 | 53510502 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 1 | HR |  |  | 70 | 0 | 70 | 9.1 | 79.1 | 2020-11-01 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building new road from C067 and C069 - Skidding of trees to C061 | 5 | C050-C069 | Antler Lake | 0 | 44143 |  | 37 | 44144 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting638520201101-6Driver - AZ - After Jan 10170 | Corbiere and Sons Contracting638520201101-6Driver - AZ - After Jan 10170Inv#071 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 70 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6386 | 20201101-7 | 53510504 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 3 | Dynamic | 98.61 | 0 |  |  | 394.44 | 51.2772 | 445.7172 | 2020-11-01 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel haul and spread from C067 and C069 | 5 | C067-C069 | Antler Lake | 0 | 44143 |  | 37 | 44144 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting638620201101-7Dozer D6 or equal- After Jan 103394.44 | Corbiere and Sons Contracting638620201101-7Dozer D6 or equal- After Jan 103394.44Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 394.44 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6386 | 20201101-7 | 53510504 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 3 | Dynamic | 103.84 | 0 |  |  | 415.35 | 53.9955 | 469.3455 | 2020-11-01 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel haul and spread from C067 and C069 | 5 | C067-C069 | Antler Lake | 0 | 44143 |  | 37 | 44144 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting638620201101-7Excavator - 30 ton- After Jan 103415.35 | Corbiere and Sons Contracting638620201101-7Excavator - 30 ton- After Jan 103415.35Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 415.35 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6386 | 20201101-7 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-11-01 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel haul and spread from C067 and C069 | 5 | C067-C069 | Antler Lake | 0 | 44143 |  | 37 | 44144 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting638620201101-7Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting638620201101-7Light Truck - Pick up- After Jan 101243.75Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6386 | 20201101-7 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 5 | Dynamic | 103.54 | 0 |  |  | 690.25 | 89.7325 | 779.9825 | 2020-11-01 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel haul and spread from C067 and C069 | 5 | C067-C069 | Antler Lake | 0 | 44143 |  | 37 | 44144 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting638620201101-7Rock Truck - 30 Ton- After Jan 105690.25 | Corbiere and Sons Contracting638620201101-7Rock Truck - 30 Ton- After Jan 105690.25Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 690.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6386 | 20201101-7 | 53510504 | Access | 0 | Foreman | 95 | 2 | HR |  |  | 95 | 0 | 190 | 24.7 | 214.7 | 2020-11-01 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel haul and spread from C067 and C069 | 5 | C067-C069 | Antler Lake | 0 | 44143 |  | 37 | 44144 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting638620201101-7Foreman2190 | Corbiere and Sons Contracting638620201101-7Foreman2190Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 190 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6386 | 20201101-7 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 7 | HR |  |  | 75 | 0 | 525 | 68.25 | 593.25 | 2020-11-01 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel haul and spread from C067 and C069 | 5 | C067-C069 | Antler Lake | 0 | 44143 |  | 37 | 44144 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting638620201101-7Operator - Principle - After Jan 107525 | Corbiere and Sons Contracting638620201101-7Operator - Principle - After Jan 107525Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 525 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6386 | 20201101-7 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 5 | HR |  |  | 70 | 0 | 350 | 45.5 | 395.5 | 2020-11-01 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel haul and spread from C067 and C069 | 5 | C067-C069 | Antler Lake | 0 | 44143 |  | 37 | 44144 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting638620201101-7Driver - AZ - After Jan 105350 | Corbiere and Sons Contracting638620201101-7Driver - AZ - After Jan 105350Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 350 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6387 | 20201101-8 | 53510503 | Access | 0 | Skidder | 171 | 11 | HR | 128.25 | 0 |  |  | 1881 | 244.53 | 2125.53 | 2020-11-01 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Putting down corduroy from C097-C100 | 5 | C093-C116 | Cook Lake | 0 | 44143 |  | 37 | 44144 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting638720201101-8Skidder 111881 | Corbiere and Sons Contracting638720201101-8Skidder 111881Inv#071 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 1881 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6387 | 20201101-8 | 53510503 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 2 | Dynamic | 103.84 | 0 |  |  | 276.9 | 35.997 | 312.897 | 2020-11-01 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Putting down corduroy from C097-C100 | 5 | C093-C116 | Cook Lake | 0 | 44143 |  | 37 | 44144 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting638720201101-8Excavator - 30 ton- After Jan 102276.9 | Corbiere and Sons Contracting638720201101-8Excavator - 30 ton- After Jan 102276.9Inv#071 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 276.9 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6387 | 20201101-8 | 53510503 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10.5 | Dynamic | 110.22 | 0 |  |  | 1543.08 | 200.6004 | 1743.6804 | 2020-11-01 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Putting down corduroy from C097-C100 | 5 | C093-C116 | Cook Lake | 0 | 44143 |  | 37 | 44144 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting638720201101-8Excavator - 36 ton- After Jan 1010.51543.08 | Corbiere and Sons Contracting638720201101-8Excavator - 36 ton- After Jan 1010.51543.08Inv#071 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 1543.08 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6387 | 20201101-8 | 53510503 | Access | 0 | Light Truck w/ Tandum Trailer- After Jan 10 | 337.5 | 1 | DAY | 253.13 | 0 |  |  | 337.5 | 43.875 | 381.375 | 2020-11-01 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Putting down corduroy from C097-C100 | 5 | C093-C116 | Cook Lake | 0 | 44143 |  | 37 | 44144 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting638720201101-8Light Truck w/ Tandum Trailer- After Jan 101337.5 | Corbiere and Sons Contracting638720201101-8Light Truck w/ Tandum Trailer- After Jan 101337.5Inv#071 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 337.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6387 | 20201101-8 | 53510503 | Access | 0 | Foreman | 95 | 6 | HR |  |  | 95 | 0 | 570 | 74.1 | 644.1 | 2020-11-01 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Putting down corduroy from C097-C100 | 5 | C093-C116 | Cook Lake | 0 | 44143 |  | 37 | 44144 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting638720201101-8Foreman6570 | Corbiere and Sons Contracting638720201101-8Foreman6570Inv#071 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 570 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6387 | 20201101-8 | 53510503 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2020-11-01 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Putting down corduroy from C097-C100 | 5 | C093-C116 | Cook Lake | 0 | 44143 |  | 37 | 44144 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting638720201101-8L.O.A.4840 | Corbiere and Sons Contracting638720201101-8L.O.A.4840Inv#071 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6387 | 20201101-8 | 53510503 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 25 | HR |  |  | 75 | 0 | 1875 | 243.75 | 2118.75 | 2020-11-01 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Putting down corduroy from C097-C100 | 5 | C093-C116 | Cook Lake | 0 | 44143 |  | 37 | 44144 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting638720201101-8Operator - Principle - After Jan 10251875 | Corbiere and Sons Contracting638720201101-8Operator - Principle - After Jan 10251875Inv#071 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 1875 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6388 | 20201101-9 | 53510504 | Access | 0 | Loader JD 524 to 624 or equal | 99 | 10.5 | HR | 74.25 | 0 |  |  | 1039.5 | 135.135 | 1174.635 | 2020-11-01 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel hauling and spread from C099 all day | 5 | C093-C116 | Cook Lake | 0 | 44143 |  | 37 | 44144 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting638820201101-9Loader JD 524 to 624 or equal10.51039.5 | Corbiere and Sons Contracting638820201101-9Loader JD 524 to 624 or equal10.51039.5Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1039.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6388 | 20201101-9 | 53510504 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10.5 | Dynamic | 98.61 | 0 |  |  | 1380.54 | 179.4702 | 1560.0102 | 2020-11-01 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel hauling and spread from C099 all day | 5 | C093-C116 | Cook Lake | 0 | 44143 |  | 37 | 44144 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting638820201101-9Dozer D6 or equal- After Jan 1010.51380.54 | Corbiere and Sons Contracting638820201101-9Dozer D6 or equal- After Jan 1010.51380.54Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1380.54 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6388 | 20201101-9 | 53510504 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10.5 | Dynamic | 103.84 | 0 |  |  | 1453.725 | 188.9843 | 1642.7093 | 2020-11-01 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel hauling and spread from C099 all day | 5 | C093-C116 | Cook Lake | 0 | 44143 |  | 37 | 44144 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting638820201101-9Excavator - 30 ton- After Jan 1010.51453.725 | Corbiere and Sons Contracting638820201101-9Excavator - 30 ton- After Jan 1010.51453.725Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1453.725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6388 | 20201101-9 | 53510504 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10.5 | HR | 9.16 | 0 |  |  | 128.205 | 16.6667 | 144.8716 | 2020-11-01 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel hauling and spread from C099 all day | 5 | C093-C116 | Cook Lake | 0 | 44143 |  | 37 | 44144 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting638820201101-9Excavator Thumb - 30 - 50 ton- After Jan 1010.5128.205 | Corbiere and Sons Contracting638820201101-9Excavator Thumb - 30 - 50 ton- After Jan 1010.5128.205Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 128.205 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6388 | 20201101-9 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2020-11-01 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel hauling and spread from C099 all day | 5 | C093-C116 | Cook Lake | 0 | 44143 |  | 37 | 44144 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting638820201101-9Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting638820201101-9Light Truck - Pick up- After Jan 103731.25Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 731.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6388 | 20201101-9 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 31.5 | Dynamic | 103.54 | 0 |  |  | 4348.575 | 565.3148 | 4913.8898 | 2020-11-01 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel hauling and spread from C099 all day | 5 | C093-C116 | Cook Lake | 0 | 44143 |  | 37 | 44144 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting638820201101-9Rock Truck - 30 Ton- After Jan 1031.54348.575 | Corbiere and Sons Contracting638820201101-9Rock Truck - 30 Ton- After Jan 1031.54348.575Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 4348.575 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6388 | 20201101-9 | 53510504 | Access | 0 | Foreman | 95 | 6 | HR |  |  | 95 | 0 | 570 | 74.1 | 644.1 | 2020-11-01 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel hauling and spread from C099 all day | 5 | C093-C116 | Cook Lake | 0 | 44143 |  | 37 | 44144 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting638820201101-9Foreman6570 | Corbiere and Sons Contracting638820201101-9Foreman6570Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 570 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6388 | 20201101-9 | 53510504 | Access | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2020-11-01 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel hauling and spread from C099 all day | 5 | C093-C116 | Cook Lake | 0 | 44143 |  | 37 | 44144 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting638820201101-9L.O.A.61260 | Corbiere and Sons Contracting638820201101-9L.O.A.61260Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6388 | 20201101-9 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 34.5 | HR |  |  | 75 | 0 | 2587.5 | 336.375 | 2923.875 | 2020-11-01 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel hauling and spread from C099 all day | 5 | C093-C116 | Cook Lake | 0 | 44143 |  | 37 | 44144 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting638820201101-9Operator - Principle - After Jan 1034.52587.5 | Corbiere and Sons Contracting638820201101-9Operator - Principle - After Jan 1034.52587.5Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 2587.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6388 | 20201101-9 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 34.5 | HR |  |  | 70 | 0 | 2415 | 313.95 | 2728.95 | 2020-11-01 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel hauling and spread from C099 all day | 5 | C093-C116 | Cook Lake | 0 | 44143 |  | 37 | 44144 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting638820201101-9Driver - AZ - After Jan 1034.52415 | Corbiere and Sons Contracting638820201101-9Driver - AZ - After Jan 1034.52415Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 2415 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6363 | 20201102-13 | 53510504 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10.5 | Dynamic | 98.61 | 0 |  |  | 1380.54 | 179.4702 | 1560.0102 | 2020-11-02 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Haul and Spread happening from C061-C069 | 5 | C050-C069 | Antler Lake | 0 | 44142 |  | 37 | 44142 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting636320201102-13Dozer D6 or equal- After Jan 1010.51380.54 | Corbiere and Sons Contracting636320201102-13Dozer D6 or equal- After Jan 1010.51380.54Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1380.54 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6363 | 20201102-13 | 53510504 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10.5 | Dynamic | 103.84 | 0 |  |  | 1453.725 | 188.9843 | 1642.7093 | 2020-11-02 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Haul and Spread happening from C061-C069 | 5 | C050-C069 | Antler Lake | 0 | 44142 |  | 37 | 44142 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting636320201102-13Excavator - 30 ton- After Jan 1010.51453.725 | Corbiere and Sons Contracting636320201102-13Excavator - 30 ton- After Jan 1010.51453.725Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1453.725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6363 | 20201102-13 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-11-02 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Haul and Spread happening from C061-C069 | 5 | C050-C069 | Antler Lake | 0 | 44142 |  | 37 | 44142 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting636320201102-13Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting636320201102-13Light Truck - Pick up- After Jan 102487.5Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6363 | 20201102-13 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 21 | Dynamic | 103.54 | 0 |  |  | 2899.05 | 376.8765 | 3275.9265 | 2020-11-02 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Haul and Spread happening from C061-C069 | 5 | C050-C069 | Antler Lake | 0 | 44142 |  | 37 | 44142 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting636320201102-13Rock Truck - 30 Ton- After Jan 10212899.05 | Corbiere and Sons Contracting636320201102-13Rock Truck - 30 Ton- After Jan 10212899.05Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 2899.05 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6363 | 20201102-13 | 53510504 | Access | 0 | Foreman | 95 | 8 | HR |  |  | 95 | 0 | 760 | 98.8 | 858.8 | 2020-11-02 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Haul and Spread happening from C061-C069 | 5 | C050-C069 | Antler Lake | 0 | 44142 |  | 37 | 44142 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting636320201102-13Foreman8760 | Corbiere and Sons Contracting636320201102-13Foreman8760Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 760 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6363 | 20201102-13 | 53510504 | Access | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2020-11-02 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Haul and Spread happening from C061-C069 | 5 | C050-C069 | Antler Lake | 0 | 44142 |  | 37 | 44142 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting636320201102-13L.O.A.61260 | Corbiere and Sons Contracting636320201102-13L.O.A.61260Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6363 | 20201102-13 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 23 | HR |  |  | 75 | 0 | 1725 | 224.25 | 1949.25 | 2020-11-02 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Haul and Spread happening from C061-C069 | 5 | C050-C069 | Antler Lake | 0 | 44142 |  | 37 | 44142 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting636320201102-13Operator - Principle - After Jan 10231725 | Corbiere and Sons Contracting636320201102-13Operator - Principle - After Jan 10231725Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6363 | 20201102-13 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 21 | HR |  |  | 70 | 0 | 1470 | 191.1 | 1661.1 | 2020-11-02 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Haul and Spread happening from C061-C069 | 5 | C050-C069 | Antler Lake | 0 | 44142 |  | 37 | 44142 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting636320201102-13Driver - AZ - After Jan 10211470 | Corbiere and Sons Contracting636320201102-13Driver - AZ - After Jan 10211470Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1470 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6363 | 20201102-13 | 53510504 | Access | 0 | Labourer - General - After Jan 10 | 60 | 3 | HR |  |  | 60 | 0 | 180 | 23.4 | 203.4 | 2020-11-02 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Haul and Spread happening from C061-C069 | 5 | C050-C069 | Antler Lake | 0 | 44142 |  | 37 | 44142 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting636320201102-13Labourer - General - After Jan 103180 | Corbiere and Sons Contracting636320201102-13Labourer - General - After Jan 103180Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 180 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6368 | 20201102-18 | 53510502 | Access | 0 | Skidder | 171 | 11 | HR | 128.25 | 0 |  |  | 1881 | 244.53 | 2125.53 | 2020-11-02 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Putting down corduroy from C100 | 5 | C076-C116 | Cooks Lake Road East | 0 | 44142 |  | 37 | 44142 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting636820201102-18Skidder 111881 | Corbiere and Sons Contracting636820201102-18Skidder 111881Inv#071 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 1881 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6368 | 20201102-18 | 53510502 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 11 | Dynamic | 103.84 | 0 |  |  | 1522.95 | 197.9835 | 1720.9335 | 2020-11-02 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Putting down corduroy from C100 | 5 | C076-C116 | Cooks Lake Road East | 0 | 44142 |  | 37 | 44142 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting636820201102-18Excavator - 30 ton- After Jan 10111522.95 | Corbiere and Sons Contracting636820201102-18Excavator - 30 ton- After Jan 10111522.95Inv#071 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 1522.95 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6368 | 20201102-18 | 53510502 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-11-02 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Putting down corduroy from C100 | 5 | C076-C116 | Cooks Lake Road East | 0 | 44142 |  | 37 | 44142 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting636820201102-18Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting636820201102-18Light Truck - Pick up- After Jan 101243.75Inv#071 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6368 | 20201102-18 | 53510502 | Access | 0 | Foreman | 95 | 4 | HR |  |  | 95 | 0 | 380 | 49.4 | 429.4 | 2020-11-02 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Putting down corduroy from C100 | 5 | C076-C116 | Cooks Lake Road East | 0 | 44142 |  | 37 | 44142 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting636820201102-18Foreman4380 | Corbiere and Sons Contracting636820201102-18Foreman4380Inv#071 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6368 | 20201102-18 | 53510502 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2020-11-02 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Putting down corduroy from C100 | 5 | C076-C116 | Cooks Lake Road East | 0 | 44142 |  | 37 | 44142 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting636820201102-18L.O.A.3630 | Corbiere and Sons Contracting636820201102-18L.O.A.3630Inv#071 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6368 | 20201102-18 | 53510502 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 23 | HR |  |  | 75 | 0 | 1725 | 224.25 | 1949.25 | 2020-11-02 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Putting down corduroy from C100 | 5 | C076-C116 | Cooks Lake Road East | 0 | 44142 |  | 37 | 44142 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting636820201102-18Operator - Principle - After Jan 10231725 | Corbiere and Sons Contracting636820201102-18Operator - Principle - After Jan 10231725Inv#071 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 1725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6370 | 20201102-20 | 53510504 | Access | 0 | Loader JD 524 to 624 or equal | 99 | 4 | HR | 74.25 | 0 |  |  | 396 | 51.48 | 447.48 | 2020-11-02 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling and spread performed from C094-C099 | 5 | C093-C116 | Cook Lake | 0 | 44142 |  | 37 | 44142 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting637020201102-20Loader JD 524 to 624 or equal4396 | Corbiere and Sons Contracting637020201102-20Loader JD 524 to 624 or equal4396Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 396 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6370 | 20201102-20 | 53510504 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 21 | Dynamic | 98.61 | 0 |  |  | 2761.08 | 358.9404 | 3120.0204 | 2020-11-02 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling and spread performed from C094-C099 | 5 | C093-C116 | Cook Lake | 0 | 44142 |  | 37 | 44142 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting637020201102-20Dozer D6 or equal- After Jan 10212761.08 | Corbiere and Sons Contracting637020201102-20Dozer D6 or equal- After Jan 10212761.08Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 2761.08 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6370 | 20201102-20 | 53510504 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10.5 | Dynamic | 103.84 | 0 |  |  | 1453.725 | 188.9843 | 1642.7093 | 2020-11-02 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling and spread performed from C094-C099 | 5 | C093-C116 | Cook Lake | 0 | 44142 |  | 37 | 44142 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting637020201102-20Excavator - 30 ton- After Jan 1010.51453.725 | Corbiere and Sons Contracting637020201102-20Excavator - 30 ton- After Jan 1010.51453.725Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1453.725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6370 | 20201102-20 | 53510504 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10.5 | HR | 9.16 | 0 |  |  | 128.205 | 16.6667 | 144.8716 | 2020-11-02 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling and spread performed from C094-C099 | 5 | C093-C116 | Cook Lake | 0 | 44142 |  | 37 | 44142 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting637020201102-20Excavator Thumb - 30 - 50 ton- After Jan 1010.5128.205 | Corbiere and Sons Contracting637020201102-20Excavator Thumb - 30 - 50 ton- After Jan 1010.5128.205Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 128.205 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6370 | 20201102-20 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2020-11-02 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling and spread performed from C094-C099 | 5 | C093-C116 | Cook Lake | 0 | 44142 |  | 37 | 44142 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting637020201102-20Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting637020201102-20Light Truck - Pick up- After Jan 103731.25Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 731.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6370 | 20201102-20 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 31.5 | Dynamic | 103.54 | 0 |  |  | 4348.575 | 565.3148 | 4913.8898 | 2020-11-02 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling and spread performed from C094-C099 | 5 | C093-C116 | Cook Lake | 0 | 44142 |  | 37 | 44142 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting637020201102-20Rock Truck - 30 Ton- After Jan 1031.54348.575 | Corbiere and Sons Contracting637020201102-20Rock Truck - 30 Ton- After Jan 1031.54348.575Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 4348.575 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6370 | 20201102-20 | 53510504 | Access | 0 | Foreman | 95 | 4 | HR |  |  | 95 | 0 | 380 | 49.4 | 429.4 | 2020-11-02 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling and spread performed from C094-C099 | 5 | C093-C116 | Cook Lake | 0 | 44142 |  | 37 | 44142 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting637020201102-20Foreman4380 | Corbiere and Sons Contracting637020201102-20Foreman4380Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6370 | 20201102-20 | 53510504 | Access | 0 | L.O.A. | 210 | 7 | DAY |  |  |  | 0 | 1470 | 191.1 | 1661.1 | 2020-11-02 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling and spread performed from C094-C099 | 5 | C093-C116 | Cook Lake | 0 | 44142 |  | 37 | 44142 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting637020201102-20L.O.A.71470 | Corbiere and Sons Contracting637020201102-20L.O.A.71470Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1470 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6370 | 20201102-20 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 38.5 | HR |  |  | 75 | 0 | 2887.5 | 375.375 | 3262.875 | 2020-11-02 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling and spread performed from C094-C099 | 5 | C093-C116 | Cook Lake | 0 | 44142 |  | 37 | 44142 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting637020201102-20Operator - Principle - After Jan 1038.52887.5 | Corbiere and Sons Contracting637020201102-20Operator - Principle - After Jan 1038.52887.5Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 2887.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6370 | 20201102-20 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 34.5 | HR |  |  | 70 | 0 | 2415 | 313.95 | 2728.95 | 2020-11-02 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling and spread performed from C094-C099 | 5 | C093-C116 | Cook Lake | 0 | 44142 |  | 37 | 44142 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting637020201102-20Driver - AZ - After Jan 1034.52415 | Corbiere and Sons Contracting637020201102-20Driver - AZ - After Jan 1034.52415Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 2415 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6471 | 20201102-22 | 53510412 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 1.5 | HR |  |  | 75 | 0 | 112.5 | 14.625 | 127.125 | 2020-11-02 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Site visits to several locations that need to be fixed with ditching or rock damns | 4 | C011-C029 | Nishin Creek Road | 0 | 44144 |  | 37 | 44145 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting647120201102-22Operator - Principle - After Jan 101.5112.5 | Corbiere and Sons Contracting647120201102-22Operator - Principle - After Jan 101.5112.5Inv#071 | [5 empty] | 1 | 112.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6401 | 20201103-11 | 53510412 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 3 | Dynamic | 110.22 | 0 |  |  | 440.88 | 57.3144 | 498.1944 | 2020-11-03 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ex fixing up bad spots in road on way out of B204 access | 4 | B193-B210 | Little Gravel River Road | 0 | 44143 |  | 37 | 44144 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting640120201103-11Excavator - 36 ton- After Jan 103440.88 | Corbiere and Sons Contracting640120201103-11Excavator - 36 ton- After Jan 103440.88Inv#071 | [5 empty] | 1 | 440.88 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6401 | 20201103-11 | 53510412 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 3 | HR | 9.16 | 0 |  |  | 36.63 | 4.7619 | 41.3919 | 2020-11-03 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ex fixing up bad spots in road on way out of B204 access | 4 | B193-B210 | Little Gravel River Road | 0 | 44143 |  | 37 | 44144 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting640120201103-11Excavator Thumb - 30 - 50 ton- After Jan 10336.63 | Corbiere and Sons Contracting640120201103-11Excavator Thumb - 30 - 50 ton- After Jan 10336.63Inv#071 | [5 empty] | 1 | 36.63 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6401 | 20201103-11 | 53510412 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 3 | HR |  |  | 75 | 0 | 225 | 29.25 | 254.25 | 2020-11-03 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ex fixing up bad spots in road on way out of B204 access | 4 | B193-B210 | Little Gravel River Road | 0 | 44143 |  | 37 | 44144 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting640120201103-11Operator - Principle - After Jan 103225 | Corbiere and Sons Contracting640120201103-11Operator - Principle - After Jan 103225Inv#071 | [5 empty] | 1 | 225 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6402 | 20201103-12 | 53510504 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 65 | Dynamic | 41.4 | 0 |  |  | 3588 | 466.44 | 4054.44 | 2020-11-03 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling from Worthinton bay pit to Cooks Lake Road East | 5 | C076-C116 | Cook Lake | 0 | 44143 |  | 37 | 44144 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting640220201103-12Dump - Triaxle- After Jan 10653588 | Corbiere and Sons Contracting640220201103-12Dump - Triaxle- After Jan 10653588Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 3588 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6402 | 20201103-12 | 53510504 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2020-11-03 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling from Worthinton bay pit to Cooks Lake Road East | 5 | C076-C116 | Cook Lake | 0 | 44143 |  | 37 | 44144 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting640220201103-12L.O.A.3630 | Corbiere and Sons Contracting640220201103-12L.O.A.3630Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6402 | 20201103-12 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 65 | HR |  |  | 70 | 0 | 4550 | 591.5 | 5141.5 | 2020-11-03 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling from Worthinton bay pit to Cooks Lake Road East | 5 | C076-C116 | Cook Lake | 0 | 44143 |  | 37 | 44144 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting640220201103-12Driver - AZ - After Jan 10654550 | Corbiere and Sons Contracting640220201103-12Driver - AZ - After Jan 10654550Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 4550 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6404 | 20201103-14 | 53510504 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10.5 | Dynamic | 98.61 | 0 |  |  | 1380.54 | 179.4702 | 1560.0102 | 2020-11-03 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Haul and Spread being done on antler at C062 | 5 | C050-C069 | Antler Lake | 0 | 44143 |  | 37 | 44144 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting640420201103-14Dozer D6 or equal- After Jan 1010.51380.54 | Corbiere and Sons Contracting640420201103-14Dozer D6 or equal- After Jan 1010.51380.54Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1380.54 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6404 | 20201103-14 | 53510504 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10.5 | Dynamic | 103.84 | 0 |  |  | 1453.725 | 188.9843 | 1642.7093 | 2020-11-03 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Haul and Spread being done on antler at C062 | 5 | C050-C069 | Antler Lake | 0 | 44143 |  | 37 | 44144 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting640420201103-14Excavator - 30 ton- After Jan 1010.51453.725 | Corbiere and Sons Contracting640420201103-14Excavator - 30 ton- After Jan 1010.51453.725Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1453.725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6404 | 20201103-14 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-11-03 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Haul and Spread being done on antler at C062 | 5 | C050-C069 | Antler Lake | 0 | 44143 |  | 37 | 44144 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting640420201103-14Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting640420201103-14Light Truck - Pick up- After Jan 102487.5Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6404 | 20201103-14 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 10.5 | Dynamic | 103.54 | 0 |  |  | 1449.525 | 188.4383 | 1637.9633 | 2020-11-03 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Haul and Spread being done on antler at C062 | 5 | C050-C069 | Antler Lake | 0 | 44143 |  | 37 | 44144 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting640420201103-14Rock Truck - 30 Ton- After Jan 1010.51449.525 | Corbiere and Sons Contracting640420201103-14Rock Truck - 30 Ton- After Jan 1010.51449.525Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1449.525 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6404 | 20201103-14 | 53510504 | Access | 0 | Foreman | 95 | 4 | HR |  |  | 95 | 0 | 380 | 49.4 | 429.4 | 2020-11-03 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Haul and Spread being done on antler at C062 | 5 | C050-C069 | Antler Lake | 0 | 44143 |  | 37 | 44144 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting640420201103-14Foreman4380 | Corbiere and Sons Contracting640420201103-14Foreman4380Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6404 | 20201103-14 | 53510504 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2020-11-03 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Haul and Spread being done on antler at C062 | 5 | C050-C069 | Antler Lake | 0 | 44143 |  | 37 | 44144 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting640420201103-14L.O.A.4840 | Corbiere and Sons Contracting640420201103-14L.O.A.4840Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6404 | 20201103-14 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 23 | HR |  |  | 75 | 0 | 1725 | 224.25 | 1949.25 | 2020-11-03 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Haul and Spread being done on antler at C062 | 5 | C050-C069 | Antler Lake | 0 | 44143 |  | 37 | 44144 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting640420201103-14Operator - Principle - After Jan 10231725 | Corbiere and Sons Contracting640420201103-14Operator - Principle - After Jan 10231725Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6404 | 20201103-14 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 11.5 | HR |  |  | 70 | 0 | 805 | 104.65 | 909.65 | 2020-11-03 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Haul and Spread being done on antler at C062 | 5 | C050-C069 | Antler Lake | 0 | 44143 |  | 37 | 44144 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting640420201103-14Driver - AZ - After Jan 1011.5805 | Corbiere and Sons Contracting640420201103-14Driver - AZ - After Jan 1011.5805Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 805 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6405 | 20201103-15 | 53510502 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 8 | Dynamic | 103.84 | 0 |  |  | 1107.6 | 143.988 | 1251.588 | 2020-11-03 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building new road from C061 and and rock hammer working from C062 | 5 | C061-C062 | Antler Lake | 0 | 44143 |  | 37 | 44144 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting640520201103-15Excavator - 30 ton- After Jan 1081107.6 | Corbiere and Sons Contracting640520201103-15Excavator - 30 ton- After Jan 1081107.6Inv#071 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 1107.6 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6405 | 20201103-15 | 53550503 | Earthworks | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10.5 | Dynamic | 110.22 | 0 |  |  | 1543.08 | 200.6004 | 1743.6804 | 2020-11-03 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Access Rock Blasting |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building new road from C061 and and rock hammer working from C062 | 5 | C061-C062 | Antler Lake | 0 | 44143 |  | 37 | 44144 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting640520201103-15Excavator - 36 ton- After Jan 1010.51543.08 | Corbiere and Sons Contracting640520201103-15Excavator - 36 ton- After Jan 1010.51543.08Inv#071 |  | WF5-Earthwork | WF5-Earthwork |  | 1 | 1 | 1543.08 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6405 | 20201103-15 | 53510502 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 8 | HR | 9.16 | 0 |  |  | 97.68 | 12.6984 | 110.3784 | 2020-11-03 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building new road from C061 and and rock hammer working from C062 | 5 | C061-C062 | Antler Lake | 0 | 44143 |  | 37 | 44144 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting640520201103-15Excavator Thumb - 30 - 50 ton- After Jan 10897.68 | Corbiere and Sons Contracting640520201103-15Excavator Thumb - 30 - 50 ton- After Jan 10897.68Inv#071 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 97.68 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6405 | 20201103-15 | 53550503 | Earthworks | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 10.5 | HR | 47.54 | 0 |  |  | 665.49 | 86.5137 | 752.0037 | 2020-11-03 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Access Rock Blasting |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building new road from C061 and and rock hammer working from C062 | 5 | C061-C062 | Antler Lake | 0 | 44143 |  | 37 | 44144 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting640520201103-15Excavator Hammer - 30 - 50 ton- After Jan 1010.5665.49 | Corbiere and Sons Contracting640520201103-15Excavator Hammer - 30 - 50 ton- After Jan 1010.5665.49Inv#071 |  | WF5-Earthwork | WF5-Earthwork |  | 1 | 1 | 665.49 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6405 | 20201103-15 | 53550503 | Earthworks | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-11-03 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Access Rock Blasting |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building new road from C061 and and rock hammer working from C062 | 5 | C061-C062 | Antler Lake | 0 | 44143 |  | 37 | 44144 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting640520201103-15Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting640520201103-15Light Truck - Pick up- After Jan 101243.75Inv#071 |  | WF5-Earthwork | WF5-Earthwork |  | 1 | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6405 | 20201103-15 | 53510502 | Access | 0 | Foreman | 95 | 4 | HR |  |  | 95 | 0 | 380 | 49.4 | 429.4 | 2020-11-03 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building new road from C061 and and rock hammer working from C062 | 5 | C061-C062 | Antler Lake | 0 | 44143 |  | 37 | 44144 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting640520201103-15Foreman4380 | Corbiere and Sons Contracting640520201103-15Foreman4380Inv#071 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6405 | 20201103-15 | 53550503 | Earthworks | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-11-03 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Access Rock Blasting |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building new road from C061 and and rock hammer working from C062 | 5 | C061-C062 | Antler Lake | 0 | 44143 |  | 37 | 44144 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting640520201103-15L.O.A.1210 | Corbiere and Sons Contracting640520201103-15L.O.A.1210Inv#071 |  | WF5-Earthwork | WF5-Earthwork |  | 1 | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6405 | 20201103-15 | 53510502 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 8.5 | HR |  |  | 75 | 0 | 637.5 | 82.875 | 720.375 | 2020-11-03 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building new road from C061 and and rock hammer working from C062 | 5 | C061-C062 | Antler Lake | 0 | 44143 |  | 37 | 44144 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting640520201103-15Operator - Principle - After Jan 108.5637.5 | Corbiere and Sons Contracting640520201103-15Operator - Principle - After Jan 108.5637.5Inv#071 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 637.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6405 | 20201103-15 | 53550503 | Earthworks | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-11-03 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Access Rock Blasting |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building new road from C061 and and rock hammer working from C062 | 5 | C061-C062 | Antler Lake | 0 | 44143 |  | 37 | 44144 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting640520201103-15Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting640520201103-15Operator - Principle - After Jan 1011.5862.5Inv#071 |  | WF5-Earthwork | WF5-Earthwork |  | 1 | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6407 | 20201103-17 | 53510503 | Access | 0 | Skidder | 171 | 7 | HR | 128.25 | 0 |  |  | 1197 | 155.61 | 1352.61 | 2020-11-03 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Putting down corduroy from C099-C100 | 5 | C093-C116 | Cook Lake | 0 | 44143 |  | 37 | 44144 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting640720201103-17Skidder 71197 | Corbiere and Sons Contracting640720201103-17Skidder 71197Inv#071 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 1197 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6407 | 20201103-17 | 53510503 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 4 | Dynamic | 103.84 | 0 |  |  | 553.8 | 71.994 | 625.794 | 2020-11-03 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Putting down corduroy from C099-C100 | 5 | C093-C116 | Cook Lake | 0 | 44143 |  | 37 | 44144 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting640720201103-17Excavator - 30 ton- After Jan 104553.8 | Corbiere and Sons Contracting640720201103-17Excavator - 30 ton- After Jan 104553.8Inv#071 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 553.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6407 | 20201103-17 | 53510503 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-11-03 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Putting down corduroy from C099-C100 | 5 | C093-C116 | Cook Lake | 0 | 44143 |  | 37 | 44144 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting640720201103-17Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting640720201103-17Light Truck - Pick up- After Jan 101243.75Inv#071 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6407 | 20201103-17 | 53510503 | Access | 0 | Foreman | 95 | 4 | HR |  |  | 95 | 0 | 380 | 49.4 | 429.4 | 2020-11-03 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Putting down corduroy from C099-C100 | 5 | C093-C116 | Cook Lake | 0 | 44143 |  | 37 | 44144 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting640720201103-17Foreman4380 | Corbiere and Sons Contracting640720201103-17Foreman4380Inv#071 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6407 | 20201103-17 | 53510503 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2020-11-03 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Putting down corduroy from C099-C100 | 5 | C093-C116 | Cook Lake | 0 | 44143 |  | 37 | 44144 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting640720201103-17L.O.A.3630 | Corbiere and Sons Contracting640720201103-17L.O.A.3630Inv#071 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6407 | 20201103-17 | 53510503 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-11-03 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Putting down corduroy from C099-C100 | 5 | C093-C116 | Cook Lake | 0 | 44143 |  | 37 | 44144 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting640720201103-17Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting640720201103-17Operator - Principle - After Jan 1011.5862.5Inv#071 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6408 | 20201103-18 | 53510504 | Access | 0 | Loader JD 524 to 624 or equal | 99 | 4 | HR | 74.25 | 0 |  |  | 396 | 51.48 | 447.48 | 2020-11-03 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling and spread from C099 | 5 | C093-C116 | Cook Lake | 0 | 44143 |  | 37 | 44144 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting640820201103-18Loader JD 524 to 624 or equal4396 | Corbiere and Sons Contracting640820201103-18Loader JD 524 to 624 or equal4396Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 396 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6408 | 20201103-18 | 53510504 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2020-11-03 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling and spread from C099 | 5 | C093-C116 | Cook Lake | 0 | 44143 |  | 37 | 44144 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting640820201103-18Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting640820201103-18Dozer D6 or equal- After Jan 10111446.28Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1446.28 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6408 | 20201103-18 | 53510504 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 21 | Dynamic | 103.84 | 0 |  |  | 2907.45 | 377.9685 | 3285.4185 | 2020-11-03 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling and spread from C099 | 5 | C093-C116 | Cook Lake | 0 | 44143 |  | 37 | 44144 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting640820201103-18Excavator - 30 ton- After Jan 10212907.45 | Corbiere and Sons Contracting640820201103-18Excavator - 30 ton- After Jan 10212907.45Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 2907.45 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6408 | 20201103-18 | 53510504 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10.5 | HR | 9.16 | 0 |  |  | 128.205 | 16.6667 | 144.8716 | 2020-11-03 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling and spread from C099 | 5 | C093-C116 | Cook Lake | 0 | 44143 |  | 37 | 44144 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting640820201103-18Excavator Thumb - 30 - 50 ton- After Jan 1010.5128.205 | Corbiere and Sons Contracting640820201103-18Excavator Thumb - 30 - 50 ton- After Jan 1010.5128.205Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 128.205 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6408 | 20201103-18 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2020-11-03 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling and spread from C099 | 5 | C093-C116 | Cook Lake | 0 | 44143 |  | 37 | 44144 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting640820201103-18Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting640820201103-18Light Truck - Pick up- After Jan 103731.25Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 731.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6408 | 20201103-18 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 31.5 | Dynamic | 103.54 | 0 |  |  | 4348.575 | 565.3148 | 4913.8898 | 2020-11-03 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling and spread from C099 | 5 | C093-C116 | Cook Lake | 0 | 44143 |  | 37 | 44144 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting640820201103-18Rock Truck - 30 Ton- After Jan 1031.54348.575 | Corbiere and Sons Contracting640820201103-18Rock Truck - 30 Ton- After Jan 1031.54348.575Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 4348.575 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6408 | 20201103-18 | 53510504 | Access | 0 | Foreman | 95 | 6 | HR |  |  | 95 | 0 | 570 | 74.1 | 644.1 | 2020-11-03 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling and spread from C099 | 5 | C093-C116 | Cook Lake | 0 | 44143 |  | 37 | 44144 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting640820201103-18Foreman6570 | Corbiere and Sons Contracting640820201103-18Foreman6570Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 570 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6408 | 20201103-18 | 53510504 | Access | 0 | L.O.A. | 210 | 7 | DAY |  |  |  | 0 | 1470 | 191.1 | 1661.1 | 2020-11-03 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling and spread from C099 | 5 | C093-C116 | Cook Lake | 0 | 44143 |  | 37 | 44144 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting640820201103-18L.O.A.71470 | Corbiere and Sons Contracting640820201103-18L.O.A.71470Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1470 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6408 | 20201103-18 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 38.5 | HR |  |  | 75 | 0 | 2887.5 | 375.375 | 3262.875 | 2020-11-03 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling and spread from C099 | 5 | C093-C116 | Cook Lake | 0 | 44143 |  | 37 | 44144 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting640820201103-18Operator - Principle - After Jan 1038.52887.5 | Corbiere and Sons Contracting640820201103-18Operator - Principle - After Jan 1038.52887.5Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 2887.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6408 | 20201103-18 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 34.5 | HR |  |  | 70 | 0 | 2415 | 313.95 | 2728.95 | 2020-11-03 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling and spread from C099 | 5 | C093-C116 | Cook Lake | 0 | 44143 |  | 37 | 44144 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting640820201103-18Driver - AZ - After Jan 1034.52415 | Corbiere and Sons Contracting640820201103-18Driver - AZ - After Jan 1034.52415Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 2415 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6427 | 20201104-16 | 53510504 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 54.5 | Dynamic | 41.4 | 0 |  |  | 3008.4 | 391.092 | 3399.492 | 2020-11-04 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling from Worthington Bay pit to Cooks Lake laydown | 5 | C093-C116 | Cook Lake | 0 | 44143 |  | 37 | 44145 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting642720201104-16Dump - Triaxle- After Jan 1054.53008.4 | Corbiere and Sons Contracting642720201104-16Dump - Triaxle- After Jan 1054.53008.4Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 3008.4 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6427 | 20201104-16 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-11-04 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling from Worthington Bay pit to Cooks Lake laydown | 5 | C093-C116 | Cook Lake | 0 | 44143 |  | 37 | 44145 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting642720201104-16Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting642720201104-16Light Truck - Pick up- After Jan 102487.5Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6427 | 20201104-16 | 53510504 | Access | 0 | Construction Coordinator | 80 | 12 | HR |  |  | 80 | 0 | 960 | 124.8 | 1084.8 | 2020-11-04 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling from Worthington Bay pit to Cooks Lake laydown | 5 | C093-C116 | Cook Lake | 0 | 44143 |  | 37 | 44145 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting642720201104-16Construction Coordinator12960 | Corbiere and Sons Contracting642720201104-16Construction Coordinator12960Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6427 | 20201104-16 | 53510504 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2020-11-04 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling from Worthington Bay pit to Cooks Lake laydown | 5 | C093-C116 | Cook Lake | 0 | 44143 |  | 37 | 44145 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting642720201104-16L.O.A.4840 | Corbiere and Sons Contracting642720201104-16L.O.A.4840Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6427 | 20201104-16 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 54.5 | HR |  |  | 70 | 0 | 3815 | 495.95 | 4310.95 | 2020-11-04 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling from Worthington Bay pit to Cooks Lake laydown | 5 | C093-C116 | Cook Lake | 0 | 44143 |  | 37 | 44145 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting642720201104-16Driver - AZ - After Jan 1054.53815 | Corbiere and Sons Contracting642720201104-16Driver - AZ - After Jan 1054.53815Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 3815 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6429 | 20201104-18 | 53510504 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 9 | Dynamic | 98.61 | 0 |  |  | 1183.32 | 153.8316 | 1337.1516 | 2020-11-04 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working on the gravel spread from C069 | 5 | C050-C069 | Antler Lake | 0 | 44143 |  | 37 | 44145 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting642920201104-18Dozer D6 or equal- After Jan 1091183.32 | Corbiere and Sons Contracting642920201104-18Dozer D6 or equal- After Jan 1091183.32Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1183.32 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6429 | 20201104-18 | 53510504 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10.5 | Dynamic | 103.84 | 0 |  |  | 1453.725 | 188.9843 | 1642.7093 | 2020-11-04 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working on the gravel spread from C069 | 5 | C050-C069 | Antler Lake | 0 | 44143 |  | 37 | 44145 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting642920201104-18Excavator - 30 ton- After Jan 1010.51453.725 | Corbiere and Sons Contracting642920201104-18Excavator - 30 ton- After Jan 1010.51453.725Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1453.725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6429 | 20201104-18 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-11-04 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working on the gravel spread from C069 | 5 | C050-C069 | Antler Lake | 0 | 44143 |  | 37 | 44145 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting642920201104-18Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting642920201104-18Light Truck - Pick up- After Jan 102487.5Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6429 | 20201104-18 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 20 | Dynamic | 103.54 | 0 |  |  | 2761 | 358.93 | 3119.93 | 2020-11-04 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working on the gravel spread from C069 | 5 | C050-C069 | Antler Lake | 0 | 44143 |  | 37 | 44145 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting642920201104-18Rock Truck - 30 Ton- After Jan 10202761 | Corbiere and Sons Contracting642920201104-18Rock Truck - 30 Ton- After Jan 10202761Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 2761 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6429 | 20201104-18 | 53510504 | Access | 0 | Foreman | 95 | 4 | HR |  |  | 95 | 0 | 380 | 49.4 | 429.4 | 2020-11-04 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working on the gravel spread from C069 | 5 | C050-C069 | Antler Lake | 0 | 44143 |  | 37 | 44145 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting642920201104-18Foreman4380 | Corbiere and Sons Contracting642920201104-18Foreman4380Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6429 | 20201104-18 | 53510504 | Access | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2020-11-04 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working on the gravel spread from C069 | 5 | C050-C069 | Antler Lake | 0 | 44143 |  | 37 | 44145 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting642920201104-18L.O.A.61260 | Corbiere and Sons Contracting642920201104-18L.O.A.61260Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6429 | 20201104-18 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 21 | HR |  |  | 75 | 0 | 1575 | 204.75 | 1779.75 | 2020-11-04 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working on the gravel spread from C069 | 5 | C050-C069 | Antler Lake | 0 | 44143 |  | 37 | 44145 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting642920201104-18Operator - Principle - After Jan 10211575 | Corbiere and Sons Contracting642920201104-18Operator - Principle - After Jan 10211575Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1575 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6429 | 20201104-18 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 22 | HR |  |  | 70 | 0 | 1540 | 200.2 | 1740.2 | 2020-11-04 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working on the gravel spread from C069 | 5 | C050-C069 | Antler Lake | 0 | 44143 |  | 37 | 44145 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting642920201104-18Driver - AZ - After Jan 10221540 | Corbiere and Sons Contracting642920201104-18Driver - AZ - After Jan 10221540Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1540 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6429 | 20201104-18 | 53510504 | Access | 0 | Labourer - General - After Jan 10 | 60 | 3 | HR |  |  | 60 | 0 | 180 | 23.4 | 203.4 | 2020-11-04 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working on the gravel spread from C069 | 5 | C050-C069 | Antler Lake | 0 | 44143 |  | 37 | 44145 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting642920201104-18Labourer - General - After Jan 103180 | Corbiere and Sons Contracting642920201104-18Labourer - General - After Jan 103180Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 180 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6430 | 20201104-19 | 53510502 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 7 | Dynamic | 103.84 | 0 |  |  | 969.15 | 125.9895 | 1095.1395 | 2020-11-04 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building new road from C061 and C069 and rock hammering from C061 | 5 | C050-C069 | Antler Lake | 0 | 44143 |  | 37 | 44145 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting643020201104-19Excavator - 30 ton- After Jan 107969.15 | Corbiere and Sons Contracting643020201104-19Excavator - 30 ton- After Jan 107969.15Inv#071 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 969.15 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6430 | 20201104-19 | 53510502 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 3 | Dynamic | 110.22 | 0 |  |  | 440.88 | 57.3144 | 498.1944 | 2020-11-04 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building new road from C061 and C069 and rock hammering from C061 | 5 | C050-C069 | Antler Lake | 0 | 44143 |  | 37 | 44145 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting643020201104-19Excavator - 36 ton- After Jan 103440.88 | Corbiere and Sons Contracting643020201104-19Excavator - 36 ton- After Jan 103440.88Inv#071 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 440.88 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6430 | 20201104-19 | 53550503 | Earthworks | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10.5 | Dynamic | 110.22 | 0 |  |  | 1543.08 | 200.6004 | 1743.6804 | 2020-11-04 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Access Rock Blasting |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building new road from C061 and C069 and rock hammering from C061 | 5 | C050-C069 | Antler Lake | 0 | 44143 |  | 37 | 44145 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting643020201104-19Excavator - 36 ton- After Jan 1010.51543.08 | Corbiere and Sons Contracting643020201104-19Excavator - 36 ton- After Jan 1010.51543.08Inv#071 |  | WF5-Earthwork | WF5-Earthwork |  | 1 | 1 | 1543.08 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6430 | 20201104-19 | 53510502 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 9.16 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2020-11-04 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building new road from C061 and C069 and rock hammering from C061 | 5 | C050-C069 | Antler Lake | 0 | 44143 |  | 37 | 44145 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting643020201104-19Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting643020201104-19Excavator Thumb - 30 - 50 ton- After Jan 1010122.1Inv#071 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 122.1 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6430 | 20201104-19 | 53550503 | Earthworks | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 10.5 | HR | 47.54 | 0 |  |  | 665.49 | 86.5137 | 752.0037 | 2020-11-04 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Access Rock Blasting |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building new road from C061 and C069 and rock hammering from C061 | 5 | C050-C069 | Antler Lake | 0 | 44143 |  | 37 | 44145 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting643020201104-19Excavator Hammer - 30 - 50 ton- After Jan 1010.5665.49 | Corbiere and Sons Contracting643020201104-19Excavator Hammer - 30 - 50 ton- After Jan 1010.5665.49Inv#071 |  | WF5-Earthwork | WF5-Earthwork |  | 1 | 1 | 665.49 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6430 | 20201104-19 | 53550503 | Earthworks | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-11-04 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Access Rock Blasting |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building new road from C061 and C069 and rock hammering from C061 | 5 | C050-C069 | Antler Lake | 0 | 44143 |  | 37 | 44145 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting643020201104-19Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting643020201104-19Light Truck - Pick up- After Jan 101243.75Inv#071 |  | WF5-Earthwork | WF5-Earthwork |  | 1 | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6430 | 20201104-19 | 53510502 | Access | 0 | Foreman | 95 | 4 | HR |  |  | 95 | 0 | 380 | 49.4 | 429.4 | 2020-11-04 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building new road from C061 and C069 and rock hammering from C061 | 5 | C050-C069 | Antler Lake | 0 | 44143 |  | 37 | 44145 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting643020201104-19Foreman4380 | Corbiere and Sons Contracting643020201104-19Foreman4380Inv#071 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6430 | 20201104-19 | 53510502 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-11-04 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building new road from C061 and C069 and rock hammering from C061 | 5 | C050-C069 | Antler Lake | 0 | 44143 |  | 37 | 44145 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting643020201104-19L.O.A.2420 | Corbiere and Sons Contracting643020201104-19L.O.A.2420Inv#071 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6430 | 20201104-19 | 53550503 | Earthworks | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-11-04 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Access Rock Blasting |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building new road from C061 and C069 and rock hammering from C061 | 5 | C050-C069 | Antler Lake | 0 | 44143 |  | 37 | 44145 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting643020201104-19L.O.A.1210 | Corbiere and Sons Contracting643020201104-19L.O.A.1210Inv#071 |  | WF5-Earthwork | WF5-Earthwork |  | 1 | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6430 | 20201104-19 | 53510502 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 10.5 | HR |  |  | 75 | 0 | 787.5 | 102.375 | 889.875 | 2020-11-04 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building new road from C061 and C069 and rock hammering from C061 | 5 | C050-C069 | Antler Lake | 0 | 44143 |  | 37 | 44145 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting643020201104-19Operator - Principle - After Jan 1010.5787.5 | Corbiere and Sons Contracting643020201104-19Operator - Principle - After Jan 1010.5787.5Inv#071 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 787.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6430 | 20201104-19 | 53550503 | Earthworks | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-11-04 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Access Rock Blasting |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building new road from C061 and C069 and rock hammering from C061 | 5 | C050-C069 | Antler Lake | 0 | 44143 |  | 37 | 44145 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting643020201104-19Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting643020201104-19Operator - Principle - After Jan 1011.5862.5Inv#071 |  | WF5-Earthwork | WF5-Earthwork |  | 1 | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6430 | 20201104-19 | 53510502 | Access | 0 | Labourer - General - After Jan 10 | 60 | 3 | HR |  |  | 60 | 0 | 180 | 23.4 | 203.4 | 2020-11-04 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building new road from C061 and C069 and rock hammering from C061 | 5 | C050-C069 | Antler Lake | 0 | 44143 |  | 37 | 44145 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting643020201104-19Labourer - General - After Jan 103180 | Corbiere and Sons Contracting643020201104-19Labourer - General - After Jan 103180Inv#071 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 180 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6433 | 20201104-22 | 53510512 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 2 | Dynamic | 98.61 | 0 |  |  | 262.96 | 34.1848 | 297.1448 | 2020-11-04 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance being done with DZ from C069 | 5 | C050-C069 | Antler Lake | 0 | 44143 |  | 37 | 44145 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting643320201104-22Dozer D6 or equal- After Jan 102262.96 | Corbiere and Sons Contracting643320201104-22Dozer D6 or equal- After Jan 102262.96Inv#071 | [5 empty] | 1 | 262.96 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6433 | 20201104-22 | 53510512 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 2 | HR |  |  | 75 | 0 | 150 | 19.5 | 169.5 | 2020-11-04 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance being done with DZ from C069 | 5 | C050-C069 | Antler Lake | 0 | 44143 |  | 37 | 44145 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting643320201104-22Operator - Principle - After Jan 102150 | Corbiere and Sons Contracting643320201104-22Operator - Principle - After Jan 102150Inv#071 | [5 empty] | 1 | 150 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6434 | 20201104-23 | 53510503 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 2 | Dynamic | 103.84 | 0 |  |  | 276.9 | 35.997 | 312.897 | 2020-11-04 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Put down 30m of corduroy from C100 | 5 | C100 | Cook Lake | 0 | 44143 |  | 37 | 44145 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting643420201104-23Excavator - 30 ton- After Jan 102276.9 | Corbiere and Sons Contracting643420201104-23Excavator - 30 ton- After Jan 102276.9Inv#071 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 276.9 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6434 | 20201104-23 | 53510503 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-11-04 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Put down 30m of corduroy from C100 | 5 | C100 | Cook Lake | 0 | 44143 |  | 37 | 44145 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting643420201104-23L.O.A.1210 | Corbiere and Sons Contracting643420201104-23L.O.A.1210Inv#071 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6434 | 20201104-23 | 53510503 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 2 | HR |  |  | 75 | 0 | 150 | 19.5 | 169.5 | 2020-11-04 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Put down 30m of corduroy from C100 | 5 | C100 | Cook Lake | 0 | 44143 |  | 37 | 44145 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting643420201104-23Operator - Principle - After Jan 102150 | Corbiere and Sons Contracting643420201104-23Operator - Principle - After Jan 102150Inv#071 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 150 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6435 | 20201104-24 | 53510504 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10.5 | Dynamic | 103.84 | 0 |  |  | 1453.725 | 188.9843 | 1642.7093 | 2020-11-04 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling done on Cooks lake East towards C100 | 5 | C093-C116 | Cook Lake | 0 | 44143 |  | 37 | 44145 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting643520201104-24Excavator - 30 ton- After Jan 1010.51453.725 | Corbiere and Sons Contracting643520201104-24Excavator - 30 ton- After Jan 1010.51453.725Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1453.725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6435 | 20201104-24 | 53510504 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9.5 | Dynamic | 110.22 | 0 |  |  | 1396.12 | 181.4956 | 1577.6156 | 2020-11-04 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling done on Cooks lake East towards C100 | 5 | C093-C116 | Cook Lake | 0 | 44143 |  | 37 | 44145 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting643520201104-24Excavator - 36 ton- After Jan 109.51396.12 | Corbiere and Sons Contracting643520201104-24Excavator - 36 ton- After Jan 109.51396.12Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1396.12 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6435 | 20201104-24 | 53510504 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10.5 | HR | 9.16 | 0 |  |  | 128.205 | 16.6667 | 144.8716 | 2020-11-04 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling done on Cooks lake East towards C100 | 5 | C093-C116 | Cook Lake | 0 | 44143 |  | 37 | 44145 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting643520201104-24Excavator Thumb - 30 - 50 ton- After Jan 1010.5128.205 | Corbiere and Sons Contracting643520201104-24Excavator Thumb - 30 - 50 ton- After Jan 1010.5128.205Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 128.205 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6435 | 20201104-24 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-11-04 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling done on Cooks lake East towards C100 | 5 | C093-C116 | Cook Lake | 0 | 44143 |  | 37 | 44145 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting643520201104-24Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting643520201104-24Light Truck - Pick up- After Jan 102487.5Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6435 | 20201104-24 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 31.5 | Dynamic | 103.54 | 0 |  |  | 4348.575 | 565.3148 | 4913.8898 | 2020-11-04 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling done on Cooks lake East towards C100 | 5 | C093-C116 | Cook Lake | 0 | 44143 |  | 37 | 44145 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting643520201104-24Rock Truck - 30 Ton- After Jan 1031.54348.575 | Corbiere and Sons Contracting643520201104-24Rock Truck - 30 Ton- After Jan 1031.54348.575Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 4348.575 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6435 | 20201104-24 | 53510504 | Access | 0 | Foreman | 95 | 6 | HR |  |  | 95 | 0 | 570 | 74.1 | 644.1 | 2020-11-04 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling done on Cooks lake East towards C100 | 5 | C093-C116 | Cook Lake | 0 | 44143 |  | 37 | 44145 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting643520201104-24Foreman6570 | Corbiere and Sons Contracting643520201104-24Foreman6570Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 570 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6435 | 20201104-24 | 53510504 | Access | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2020-11-04 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling done on Cooks lake East towards C100 | 5 | C093-C116 | Cook Lake | 0 | 44143 |  | 37 | 44145 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting643520201104-24L.O.A.61260 | Corbiere and Sons Contracting643520201104-24L.O.A.61260Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6435 | 20201104-24 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 22 | HR |  |  | 75 | 0 | 1650 | 214.5 | 1864.5 | 2020-11-04 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling done on Cooks lake East towards C100 | 5 | C093-C116 | Cook Lake | 0 | 44143 |  | 37 | 44145 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting643520201104-24Operator - Principle - After Jan 10221650 | Corbiere and Sons Contracting643520201104-24Operator - Principle - After Jan 10221650Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1650 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6435 | 20201104-24 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 34.5 | HR |  |  | 70 | 0 | 2415 | 313.95 | 2728.95 | 2020-11-04 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling done on Cooks lake East towards C100 | 5 | C093-C116 | Cook Lake | 0 | 44143 |  | 37 | 44145 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting643520201104-24Driver - AZ - After Jan 1034.52415 | Corbiere and Sons Contracting643520201104-24Driver - AZ - After Jan 1034.52415Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 2415 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6437 | 20201104-26 | 53510512 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 4 | Dynamic | 98.61 | 0 |  |  | 525.92 | 68.3696 | 594.2896 | 2020-11-04 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozers did road maintenance after dragging in bridges | 5 | C093-C116 | Cooks Lake Road East | 0 | 44139 |  | 37 | 44145 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting643720201104-26Dozer D6 or equal- After Jan 104525.92 | Corbiere and Sons Contracting643720201104-26Dozer D6 or equal- After Jan 104525.92Inv#071 | [5 empty] | 1 | 525.92 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6437 | 20201104-26 | 53510512 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 4 | HR |  |  | 75 | 0 | 300 | 39 | 339 | 2020-11-04 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozers did road maintenance after dragging in bridges | 5 | C093-C116 | Cooks Lake Road East | 0 | 44139 |  | 37 | 44145 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting643720201104-26Operator - Principle - After Jan 104300 | Corbiere and Sons Contracting643720201104-26Operator - Principle - After Jan 104300Inv#071 | [5 empty] | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6438 | 20201104-27 | 53510502 | Access | 0 | Skidder | 171 | 5 | HR | 128.25 | 0 |  |  | 855 | 111.15 | 966.15 | 2020-11-04 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Skidding wood to C100 for access | 5 | C100 | Cooks Lake Road East | 0 | 44143 |  | 37 | 44145 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting643820201104-27Skidder 5855 | Corbiere and Sons Contracting643820201104-27Skidder 5855Inv#071 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 855 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6438 | 20201104-27 | 53510502 | Access | 0 | Foreman | 95 | 4 | HR |  |  | 95 | 0 | 380 | 49.4 | 429.4 | 2020-11-04 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Skidding wood to C100 for access | 5 | C100 | Cooks Lake Road East | 0 | 44143 |  | 37 | 44145 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting643820201104-27Foreman4380 | Corbiere and Sons Contracting643820201104-27Foreman4380Inv#071 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6438 | 20201104-27 | 53510502 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-11-04 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Skidding wood to C100 for access | 5 | C100 | Cooks Lake Road East | 0 | 44143 |  | 37 | 44145 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting643820201104-27L.O.A.1210 | Corbiere and Sons Contracting643820201104-27L.O.A.1210Inv#071 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6438 | 20201104-27 | 53510502 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6.5 | HR |  |  | 75 | 0 | 487.5 | 63.375 | 550.875 | 2020-11-04 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Skidding wood to C100 for access | 5 | C100 | Cooks Lake Road East | 0 | 44143 |  | 37 | 44145 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting643820201104-27Operator - Principle - After Jan 106.5487.5 | Corbiere and Sons Contracting643820201104-27Operator - Principle - After Jan 106.5487.5Inv#071 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6417 | 20201104-7 | 53510312 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2020-11-04 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer doing road maintenance all day at landfill road | 3 | B080-B084 | Landfill Road | 0 | 44143 |  | 37 | 44145 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting641720201104-7Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting641720201104-7Dozer D6 or equal- After Jan 10111446.28Inv#071 | [5 empty] | 1 | 1446.28 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6417 | 20201104-7 | 53510312 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-11-04 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer doing road maintenance all day at landfill road | 3 | B080-B084 | Landfill Road | 0 | 44143 |  | 37 | 44145 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting641720201104-7Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting641720201104-7Light Truck - Pick up- After Jan 101243.75Inv#071 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6417 | 20201104-7 | 53510312 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2020-11-04 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer doing road maintenance all day at landfill road | 3 | B080-B084 | Landfill Road | 0 | 44143 |  | 37 | 44145 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting641720201104-7Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting641720201104-7Operator - Principle - After Jan 1012900Inv#071 | [5 empty] | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6454 | 20201105-12-R1 | 53510312 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 13 | Dynamic | 98.61 | 0 |  |  | 1709.24 | 222.2012 | 1931.4412 | 2020-11-05 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer helping maintain road while steel and supplies being moved in | 3 | B084 | Landfill Road | 0 | 44143 |  | 37 | 44145 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting645420201105-12-R1Dozer D6 or equal- After Jan 10131709.24 | Corbiere and Sons Contracting645420201105-12-R1Dozer D6 or equal- After Jan 10131709.24Inv#071 | [5 empty] | 1 | 1709.24 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6454 | 20201105-12-R1 | 53510312 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-11-05 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer helping maintain road while steel and supplies being moved in | 3 | B084 | Landfill Road | 0 | 44143 |  | 37 | 44145 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting645420201105-12-R1Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting645420201105-12-R1Light Truck - Pick up- After Jan 101243.75Inv#071 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6454 | 20201105-12-R1 | 53510312 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 14 | HR |  |  | 75 | 0 | 1050 | 136.5 | 1186.5 | 2020-11-05 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer helping maintain road while steel and supplies being moved in | 3 | B084 | Landfill Road | 0 | 44143 |  | 37 | 44145 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting645420201105-12-R1Operator - Principle - After Jan 10141050 | Corbiere and Sons Contracting645420201105-12-R1Operator - Principle - After Jan 10141050Inv#071 | [5 empty] | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6460 | 20201105-18 | 53510504 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 5 | Dynamic | 98.61 | 0 |  |  | 657.4 | 85.462 | 742.862 | 2020-11-05 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working on gravel spread from C067 | 5 | C050-C069 | Antler Lake | 0 | 44143 |  | 37 | 44145 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting646020201105-18Dozer D6 or equal- After Jan 105657.4 | Corbiere and Sons Contracting646020201105-18Dozer D6 or equal- After Jan 105657.4Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 657.4 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6460 | 20201105-18 | 53510504 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 7 | Dynamic | 103.84 | 0 |  |  | 969.15 | 125.9895 | 1095.1395 | 2020-11-05 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working on gravel spread from C067 | 5 | C050-C069 | Antler Lake | 0 | 44143 |  | 37 | 44145 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting646020201105-18Excavator - 30 ton- After Jan 107969.15 | Corbiere and Sons Contracting646020201105-18Excavator - 30 ton- After Jan 107969.15Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 969.15 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6460 | 20201105-18 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-11-05 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working on gravel spread from C067 | 5 | C050-C069 | Antler Lake | 0 | 44143 |  | 37 | 44145 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting646020201105-18Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting646020201105-18Light Truck - Pick up- After Jan 102487.5Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6460 | 20201105-18 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 8 | Dynamic | 103.54 | 0 |  |  | 1104.4 | 143.572 | 1247.972 | 2020-11-05 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working on gravel spread from C067 | 5 | C050-C069 | Antler Lake | 0 | 44143 |  | 37 | 44145 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting646020201105-18Rock Truck - 30 Ton- After Jan 1081104.4 | Corbiere and Sons Contracting646020201105-18Rock Truck - 30 Ton- After Jan 1081104.4Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1104.4 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6460 | 20201105-18 | 53510504 | Access | 0 | Foreman | 95 | 4 | HR |  |  | 95 | 0 | 380 | 49.4 | 429.4 | 2020-11-05 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working on gravel spread from C067 | 5 | C050-C069 | Antler Lake | 0 | 44143 |  | 37 | 44145 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting646020201105-18Foreman4380 | Corbiere and Sons Contracting646020201105-18Foreman4380Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6460 | 20201105-18 | 53510504 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-11-05 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working on gravel spread from C067 | 5 | C050-C069 | Antler Lake | 0 | 44143 |  | 37 | 44145 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting646020201105-18L.O.A.2420 | Corbiere and Sons Contracting646020201105-18L.O.A.2420Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6460 | 20201105-18 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12.5 | HR |  |  | 75 | 0 | 937.5 | 121.875 | 1059.375 | 2020-11-05 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working on gravel spread from C067 | 5 | C050-C069 | Antler Lake | 0 | 44143 |  | 37 | 44145 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting646020201105-18Operator - Principle - After Jan 1012.5937.5 | Corbiere and Sons Contracting646020201105-18Operator - Principle - After Jan 1012.5937.5Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 937.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6460 | 20201105-18 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 8 | HR |  |  | 70 | 0 | 560 | 72.8 | 632.8 | 2020-11-05 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working on gravel spread from C067 | 5 | C050-C069 | Antler Lake | 0 | 44143 |  | 37 | 44145 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting646020201105-18Driver - AZ - After Jan 108560 | Corbiere and Sons Contracting646020201105-18Driver - AZ - After Jan 108560Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 560 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6461 | 20201105-19 | 53510502 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 2 | Dynamic | 103.84 | 0 |  |  | 276.9 | 35.997 | 312.897 | 2020-11-05 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock Hammering from C061 | 5 | C061 | Antler Lake | 0 | 44143 |  | 37 | 44145 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting646120201105-19Excavator - 30 ton- After Jan 102276.9 | Corbiere and Sons Contracting646120201105-19Excavator - 30 ton- After Jan 102276.9Inv#071 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 276.9 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6461 | 20201105-19 | 53510502 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 5 | Dynamic | 110.22 | 0 |  |  | 734.8 | 95.524 | 830.324 | 2020-11-05 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock Hammering from C061 | 5 | C061 | Antler Lake | 0 | 44143 |  | 37 | 44145 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting646120201105-19Excavator - 36 ton- After Jan 105734.8 | Corbiere and Sons Contracting646120201105-19Excavator - 36 ton- After Jan 105734.8Inv#071 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 734.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6461 | 20201105-19 | 53510502 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 2 | HR | 9.16 | 0 |  |  | 24.42 | 3.1746 | 27.5946 | 2020-11-05 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock Hammering from C061 | 5 | C061 | Antler Lake | 0 | 44143 |  | 37 | 44145 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting646120201105-19Excavator Thumb - 30 - 50 ton- After Jan 10224.42 | Corbiere and Sons Contracting646120201105-19Excavator Thumb - 30 - 50 ton- After Jan 10224.42Inv#071 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 24.42 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6461 | 20201105-19 | 53550503 | Earthworks | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 5 | HR | 47.54 | 0 |  |  | 316.9 | 41.197 | 358.097 | 2020-11-05 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Access Rock Blasting |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock Hammering from C061 | 5 | C061 | Antler Lake | 0 | 44143 |  | 37 | 44145 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting646120201105-19Excavator Hammer - 30 - 50 ton- After Jan 105316.9 | Corbiere and Sons Contracting646120201105-19Excavator Hammer - 30 - 50 ton- After Jan 105316.9Inv#071 |  | WF5-Earthwork | WF5-Earthwork |  | 1 | 1 | 316.9 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6461 | 20201105-19 | 53510502 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-11-05 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock Hammering from C061 | 5 | C061 | Antler Lake | 0 | 44143 |  | 37 | 44145 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting646120201105-19L.O.A.1210 | Corbiere and Sons Contracting646120201105-19L.O.A.1210Inv#071 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6461 | 20201105-19 | 53510502 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 2 | HR |  |  | 75 | 0 | 150 | 19.5 | 169.5 | 2020-11-05 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock Hammering from C061 | 5 | C061 | Antler Lake | 0 | 44143 |  | 37 | 44145 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting646120201105-19Operator - Principle - After Jan 102150 | Corbiere and Sons Contracting646120201105-19Operator - Principle - After Jan 102150Inv#071 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 150 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6461 | 20201105-19 | 53550503 | Earthworks | 0 | Operator - Principle - After Jan 10 | 75 | 5 | HR |  |  | 75 | 0 | 375 | 48.75 | 423.75 | 2020-11-05 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Access Rock Blasting |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock Hammering from C061 | 5 | C061 | Antler Lake | 0 | 44143 |  | 37 | 44145 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting646120201105-19Operator - Principle - After Jan 105375 | Corbiere and Sons Contracting646120201105-19Operator - Principle - After Jan 105375Inv#071 |  | WF5-Earthwork | WF5-Earthwork |  | 1 | 1 | 375 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6463 | 20201105-21 | 53510512 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 6 | Dynamic | 98.61 | 0 |  |  | 788.88 | 102.5544 | 891.4344 | 2020-11-05 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Widening road from C059 | 5 | C059 | Antler Lake | 0 | 44143 |  | 37 | 44145 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting646320201105-21Dozer D6 or equal- After Jan 106788.88 | Corbiere and Sons Contracting646320201105-21Dozer D6 or equal- After Jan 106788.88Inv#071 | [5 empty] | 1 | 788.88 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6463 | 20201105-21 | 53510512 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 75 | 0 | 450 | 58.5 | 508.5 | 2020-11-05 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Widening road from C059 | 5 | C059 | Antler Lake | 0 | 44143 |  | 37 | 44145 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting646320201105-21Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting646320201105-21Operator - Principle - After Jan 106450Inv#071 | [5 empty] | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6465 | 20201105-23 | 53510504 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 6 | Dynamic | 98.61 | 0 |  |  | 788.88 | 102.5544 | 891.4344 | 2020-11-05 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling on Cooks lake road E towards C100 | 5 | C100 | Cook Lake Road East | 0 | 44143 |  | 37 | 44145 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting646520201105-23Dozer D6 or equal- After Jan 106788.88 | Corbiere and Sons Contracting646520201105-23Dozer D6 or equal- After Jan 106788.88Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 788.88 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6465 | 20201105-23 | 53510504 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10.5 | Dynamic | 103.84 | 0 |  |  | 1453.725 | 188.9843 | 1642.7093 | 2020-11-05 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling on Cooks lake road E towards C100 | 5 | C100 | Cook Lake Road East | 0 | 44143 |  | 37 | 44145 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting646520201105-23Excavator - 30 ton- After Jan 1010.51453.725 | Corbiere and Sons Contracting646520201105-23Excavator - 30 ton- After Jan 1010.51453.725Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1453.725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6465 | 20201105-23 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2020-11-05 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling on Cooks lake road E towards C100 | 5 | C100 | Cook Lake Road East | 0 | 44143 |  | 37 | 44145 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting646520201105-23Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting646520201105-23Light Truck - Pick up- After Jan 103731.25Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 731.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6465 | 20201105-23 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 31.5 | Dynamic | 103.54 | 0 |  |  | 4348.575 | 565.3148 | 4913.8898 | 2020-11-05 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling on Cooks lake road E towards C100 | 5 | C100 | Cook Lake Road East | 0 | 44143 |  | 37 | 44145 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting646520201105-23Rock Truck - 30 Ton- After Jan 1031.54348.575 | Corbiere and Sons Contracting646520201105-23Rock Truck - 30 Ton- After Jan 1031.54348.575Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 4348.575 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6465 | 20201105-23 | 53510504 | Access | 0 | Foreman | 95 | 6 | HR |  |  | 95 | 0 | 570 | 74.1 | 644.1 | 2020-11-05 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling on Cooks lake road E towards C100 | 5 | C100 | Cook Lake Road East | 0 | 44143 |  | 37 | 44145 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting646520201105-23Foreman6570 | Corbiere and Sons Contracting646520201105-23Foreman6570Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 570 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6465 | 20201105-23 | 53510504 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2020-11-05 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling on Cooks lake road E towards C100 | 5 | C100 | Cook Lake Road East | 0 | 44143 |  | 37 | 44145 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting646520201105-23L.O.A.4840 | Corbiere and Sons Contracting646520201105-23L.O.A.4840Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6465 | 20201105-23 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 17.5 | HR |  |  | 75 | 0 | 1312.5 | 170.625 | 1483.125 | 2020-11-05 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling on Cooks lake road E towards C100 | 5 | C100 | Cook Lake Road East | 0 | 44143 |  | 37 | 44145 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting646520201105-23Operator - Principle - After Jan 1017.51312.5 | Corbiere and Sons Contracting646520201105-23Operator - Principle - After Jan 1017.51312.5Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1312.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6465 | 20201105-23 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 31.5 | HR |  |  | 70 | 0 | 2205 | 286.65 | 2491.65 | 2020-11-05 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling on Cooks lake road E towards C100 | 5 | C100 | Cook Lake Road East | 0 | 44143 |  | 37 | 44145 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting646520201105-23Driver - AZ - After Jan 1031.52205 | Corbiere and Sons Contracting646520201105-23Driver - AZ - After Jan 1031.52205Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 2205 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6465 | 20201105-23 | 53510504 | Access | 0 | Labourer - General - After Jan 10 | 60 | 3 | HR |  |  | 60 | 0 | 180 | 23.4 | 203.4 | 2020-11-05 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling on Cooks lake road E towards C100 | 5 | C100 | Cook Lake Road East | 0 | 44143 |  | 37 | 44145 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting646520201105-23Labourer - General - After Jan 103180 | Corbiere and Sons Contracting646520201105-23Labourer - General - After Jan 103180Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 180 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6483 | 20201106-10 | 53510512 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 7.5 | Dynamic | 103.84 | 0 |  |  | 1038.375 | 134.9888 | 1173.3637 | 2020-11-06 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixing road from C054 | 5 | C054 | Antler Lake | 0 | 44146 |  | 52 | 44146 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting648320201106-10Excavator - 30 ton- After Jan 107.51038.375 | Corbiere and Sons Contracting648320201106-10Excavator - 30 ton- After Jan 107.51038.375Inv#071 | [5 empty] | 1 | 1038.375 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6483 | 20201106-10 | 53510512 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-11-06 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixing road from C054 | 5 | C054 | Antler Lake | 0 | 44146 |  | 52 | 44146 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting648320201106-10Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting648320201106-10Light Truck - Pick up- After Jan 101243.75Inv#071 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6483 | 20201106-10 | 53510512 | Access | 0 | Foreman | 95 | 4 | HR |  |  | 95 | 0 | 380 | 49.4 | 429.4 | 2020-11-06 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixing road from C054 | 5 | C054 | Antler Lake | 0 | 44146 |  | 52 | 44146 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting648320201106-10Foreman4380 | Corbiere and Sons Contracting648320201106-10Foreman4380Inv#071 | [5 empty] | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6483 | 20201106-10 | 53510512 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-11-06 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixing road from C054 | 5 | C054 | Antler Lake | 0 | 44146 |  | 52 | 44146 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting648320201106-10L.O.A.2420 | Corbiere and Sons Contracting648320201106-10L.O.A.2420Inv#071 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6483 | 20201106-10 | 53510512 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 8 | HR |  |  | 75 | 0 | 600 | 78 | 678 | 2020-11-06 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixing road from C054 | 5 | C054 | Antler Lake | 0 | 44146 |  | 52 | 44146 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting648320201106-10Operator - Principle - After Jan 108600 | Corbiere and Sons Contracting648320201106-10Operator - Principle - After Jan 108600Inv#071 | [5 empty] | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6485 | 20201106-12 | 53510502 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 3 | Dynamic | 110.22 | 0 |  |  | 440.88 | 57.3144 | 498.1944 | 2020-11-06 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building turn around at C069 | 5 | C069 | Antler Lake | 0 | 44146 |  | 52 | 37571 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting648520201106-12Excavator - 36 ton- After Jan 103440.88 | Corbiere and Sons Contracting648520201106-12Excavator - 36 ton- After Jan 103440.88Inv#071 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 440.88 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6485 | 20201106-12 | 53510502 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 3 | HR | 9.16 | 0 |  |  | 36.63 | 4.7619 | 41.3919 | 2020-11-06 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building turn around at C069 | 5 | C069 | Antler Lake | 0 | 44146 |  | 52 | 37571 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting648520201106-12Excavator Thumb - 30 - 50 ton- After Jan 10336.63 | Corbiere and Sons Contracting648520201106-12Excavator Thumb - 30 - 50 ton- After Jan 10336.63Inv#071 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 36.63 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6485 | 20201106-12 | 53510502 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 3 | HR |  |  | 75 | 0 | 225 | 29.25 | 254.25 | 2020-11-06 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building turn around at C069 | 5 | C069 | Antler Lake | 0 | 44146 |  | 52 | 37571 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting648520201106-12Operator - Principle - After Jan 103225 | Corbiere and Sons Contracting648520201106-12Operator - Principle - After Jan 103225Inv#071 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 225 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6486 | 20201106-13 | 53550503 | Earthworks | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 1 | Dynamic | 110.22 | 0 |  |  | 146.96 | 19.1048 | 166.0648 | 2020-11-06 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Access Rock Blasting |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Access Rock Blasting for 1 hour until break down - C061 | 5 | C050-C069 | Antler Lake | 0 | 44146 |  | 52 | 44146 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting648620201106-13Excavator - 36 ton- After Jan 101146.96 | Corbiere and Sons Contracting648620201106-13Excavator - 36 ton- After Jan 101146.96Inv#071 |  | WF5-Earthwork | WF5-Earthwork |  | 1 | 1 | 146.96 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6486 | 20201106-13 | 53550503 | Earthworks | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 1 | HR | 47.54 | 0 |  |  | 63.38 | 8.2394 | 71.6194 | 2020-11-06 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Access Rock Blasting |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Access Rock Blasting for 1 hour until break down - C061 | 5 | C050-C069 | Antler Lake | 0 | 44146 |  | 52 | 44146 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting648620201106-13Excavator Hammer - 30 - 50 ton- After Jan 10163.38 | Corbiere and Sons Contracting648620201106-13Excavator Hammer - 30 - 50 ton- After Jan 10163.38Inv#071 |  | WF5-Earthwork | WF5-Earthwork |  | 1 | 1 | 63.38 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6486 | 20201106-13 | 53550503 | Earthworks | 0 | Operator - Principle - After Jan 10 | 75 | 1 | HR |  |  | 75 | 0 | 75 | 9.75 | 84.75 | 2020-11-06 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Access Rock Blasting |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Access Rock Blasting for 1 hour until break down - C061 | 5 | C050-C069 | Antler Lake | 0 | 44146 |  | 52 | 44146 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting648620201106-13Operator - Principle - After Jan 10175 | Corbiere and Sons Contracting648620201106-13Operator - Principle - After Jan 10175Inv#071 |  | WF5-Earthwork | WF5-Earthwork |  | 1 | 1 | 75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6489 | 20201106-16 | 53510504 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10.5 | Dynamic | 98.61 | 0 |  |  | 1380.54 | 179.4702 | 1560.0102 | 2020-11-06 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling and spread from C097-C100 | 5 | C093-C116 | Cook Lake | 0 | 44146 |  | 52 | 44146 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting648920201106-16Dozer D6 or equal- After Jan 1010.51380.54 | Corbiere and Sons Contracting648920201106-16Dozer D6 or equal- After Jan 1010.51380.54Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1380.54 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6489 | 20201106-16 | 53510504 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10.5 | Dynamic | 103.84 | 0 |  |  | 1453.725 | 188.9843 | 1642.7093 | 2020-11-06 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling and spread from C097-C100 | 5 | C093-C116 | Cook Lake | 0 | 44146 |  | 52 | 44146 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting648920201106-16Excavator - 30 ton- After Jan 1010.51453.725 | Corbiere and Sons Contracting648920201106-16Excavator - 30 ton- After Jan 1010.51453.725Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1453.725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6489 | 20201106-16 | 53510504 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10.5 | HR | 9.16 | 0 |  |  | 128.205 | 16.6667 | 144.8716 | 2020-11-06 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling and spread from C097-C100 | 5 | C093-C116 | Cook Lake | 0 | 44146 |  | 52 | 44146 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting648920201106-16Excavator Thumb - 30 - 50 ton- After Jan 1010.5128.205 | Corbiere and Sons Contracting648920201106-16Excavator Thumb - 30 - 50 ton- After Jan 1010.5128.205Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 128.205 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6489 | 20201106-16 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-11-06 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling and spread from C097-C100 | 5 | C093-C116 | Cook Lake | 0 | 44146 |  | 52 | 44146 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting648920201106-16Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting648920201106-16Light Truck - Pick up- After Jan 102487.5Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6489 | 20201106-16 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 21 | Dynamic | 103.54 | 0 |  |  | 2899.05 | 376.8765 | 3275.9265 | 2020-11-06 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling and spread from C097-C100 | 5 | C093-C116 | Cook Lake | 0 | 44146 |  | 52 | 44146 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting648920201106-16Rock Truck - 30 Ton- After Jan 10212899.05 | Corbiere and Sons Contracting648920201106-16Rock Truck - 30 Ton- After Jan 10212899.05Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 2899.05 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6489 | 20201106-16 | 53510504 | Access | 0 | Foreman | 95 | 4 | HR |  |  | 95 | 0 | 380 | 49.4 | 429.4 | 2020-11-06 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling and spread from C097-C100 | 5 | C093-C116 | Cook Lake | 0 | 44146 |  | 52 | 44146 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting648920201106-16Foreman4380 | Corbiere and Sons Contracting648920201106-16Foreman4380Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6489 | 20201106-16 | 53510504 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2020-11-06 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling and spread from C097-C100 | 5 | C093-C116 | Cook Lake | 0 | 44146 |  | 52 | 44146 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting648920201106-16L.O.A.4840 | Corbiere and Sons Contracting648920201106-16L.O.A.4840Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6489 | 20201106-16 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 23 | HR |  |  | 75 | 0 | 1725 | 224.25 | 1949.25 | 2020-11-06 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling and spread from C097-C100 | 5 | C093-C116 | Cook Lake | 0 | 44146 |  | 52 | 44146 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting648920201106-16Operator - Principle - After Jan 10231725 | Corbiere and Sons Contracting648920201106-16Operator - Principle - After Jan 10231725Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6489 | 20201106-16 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 23 | HR |  |  | 70 | 0 | 1610 | 209.3 | 1819.3 | 2020-11-06 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling and spread from C097-C100 | 5 | C093-C116 | Cook Lake | 0 | 44146 |  | 52 | 44146 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting648920201106-16Driver - AZ - After Jan 10231610 | Corbiere and Sons Contracting648920201106-16Driver - AZ - After Jan 10231610Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1610 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6490 | 20201106-17 | 53510512 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 2 | Dynamic | 98.61 | 0 |  |  | 262.96 | 34.1848 | 297.1448 | 2020-11-06 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | DZ did road maintenance after dragging in bridge | 5 | C093-C116 | Cook Lake | 0 | 44146 |  | 52 | 44146 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting649020201106-17Dozer D6 or equal- After Jan 102262.96 | Corbiere and Sons Contracting649020201106-17Dozer D6 or equal- After Jan 102262.96Inv#071 | [5 empty] | 1 | 262.96 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6490 | 20201106-17 | 53510512 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 2 | HR |  |  | 75 | 0 | 150 | 19.5 | 169.5 | 2020-11-06 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | DZ did road maintenance after dragging in bridge | 5 | C093-C116 | Cook Lake | 0 | 44146 |  | 52 | 44146 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting649020201106-17Operator - Principle - After Jan 102150 | Corbiere and Sons Contracting649020201106-17Operator - Principle - After Jan 102150Inv#071 | [5 empty] | 1 | 150 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6491 | 20201106-18 | 53510503 | Access | 0 | Skidder | 171 | 9.5 | HR | 128.25 | 0 |  |  | 1624.5 | 211.185 | 1835.685 | 2020-11-06 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Skidder bringing corduroy for access into C101 | 5 | C093-C116 | Cook Lake | 0 | 44146 |  | 52 | 44146 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting649120201106-18Skidder 9.51624.5 | Corbiere and Sons Contracting649120201106-18Skidder 9.51624.5Inv#071 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 1624.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6491 | 20201106-18 | 53510503 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-11-06 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Skidder bringing corduroy for access into C101 | 5 | C093-C116 | Cook Lake | 0 | 44146 |  | 52 | 44146 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting649120201106-18Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting649120201106-18Light Truck - Pick up- After Jan 101243.75Inv#071 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6491 | 20201106-18 | 53510503 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-11-06 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Skidder bringing corduroy for access into C101 | 5 | C093-C116 | Cook Lake | 0 | 44146 |  | 52 | 44146 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting649120201106-18L.O.A.1210 | Corbiere and Sons Contracting649120201106-18L.O.A.1210Inv#071 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6491 | 20201106-18 | 53510503 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 9.5 | HR |  |  | 75 | 0 | 712.5 | 92.625 | 805.125 | 2020-11-06 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Skidder bringing corduroy for access into C101 | 5 | C093-C116 | Cook Lake | 0 | 44146 |  | 52 | 44146 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting649120201106-18Operator - Principle - After Jan 109.5712.5 | Corbiere and Sons Contracting649120201106-18Operator - Principle - After Jan 109.5712.5Inv#071 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 712.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6530 | 20201106-24 | 53510412 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10 | Dynamic | 110.22 | 0 |  |  | 1469.6 | 191.048 | 1660.648 | 2020-11-06 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-07 and RT-04 fixed bad spots on Little Gravel River Rd | 4 | B194-B203 | Little Gravel River Rd | 0 | 44147 |  | 37 | 44147 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting653020201106-24Excavator - 36 ton- After Jan 10101469.6 | Corbiere and Sons Contracting653020201106-24Excavator - 36 ton- After Jan 10101469.6Inv#076 | [5 empty] | 1 | 1469.6 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6530 | 20201106-24 | 53510412 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 9.16 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2020-11-06 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-07 and RT-04 fixed bad spots on Little Gravel River Rd | 4 | B194-B203 | Little Gravel River Rd | 0 | 44147 |  | 37 | 44147 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting653020201106-24Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting653020201106-24Excavator Thumb - 30 - 50 ton- After Jan 1010122.1Inv#076 | [5 empty] | 1 | 122.1 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6530 | 20201106-24 | 53510412 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-11-06 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-07 and RT-04 fixed bad spots on Little Gravel River Rd | 4 | B194-B203 | Little Gravel River Rd | 0 | 44147 |  | 37 | 44147 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting653020201106-24Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting653020201106-24Light Truck - Pick up- After Jan 101243.75Inv#076 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6530 | 20201106-24 | 53510412 | Access | 0 | Rock Truck - 40 Ton- After Jan 10 | 205.96 | 6 | Dynamic | 154.47 | 0 |  |  | 1235.76 | 160.6488 | 1396.4088 | 2020-11-06 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-07 and RT-04 fixed bad spots on Little Gravel River Rd | 4 | B194-B203 | Little Gravel River Rd | 0 | 44147 |  | 37 | 44147 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting653020201106-24Rock Truck - 40 Ton- After Jan 1061235.76 | Corbiere and Sons Contracting653020201106-24Rock Truck - 40 Ton- After Jan 1061235.76Inv#076 | [5 empty] | 1 | 1235.76 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6530 | 20201106-24 | 53510412 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 18 | HR |  |  | 75 | 0 | 1350 | 175.5 | 1525.5 | 2020-11-06 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-07 and RT-04 fixed bad spots on Little Gravel River Rd | 4 | B194-B203 | Little Gravel River Rd | 0 | 44147 |  | 37 | 44147 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting653020201106-24Operator - Principle - After Jan 10181350 | Corbiere and Sons Contracting653020201106-24Operator - Principle - After Jan 10181350Inv#076 | [5 empty] | 1 | 1350 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6482 | 20201106-9 | 53510504 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10.5 | Dynamic | 98.61 | 0 |  |  | 1380.54 | 179.4702 | 1560.0102 | 2020-11-06 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling and spread from C069 | 5 | C069 | Antler Lake | 0 | 44146 |  | 52 | 44146 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting648220201106-9Dozer D6 or equal- After Jan 1010.51380.54 | Corbiere and Sons Contracting648220201106-9Dozer D6 or equal- After Jan 1010.51380.54Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1380.54 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6482 | 20201106-9 | 53510504 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 3 | Dynamic | 103.84 | 0 |  |  | 415.35 | 53.9955 | 469.3455 | 2020-11-06 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling and spread from C069 | 5 | C069 | Antler Lake | 0 | 44146 |  | 52 | 44146 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting648220201106-9Excavator - 30 ton- After Jan 103415.35 | Corbiere and Sons Contracting648220201106-9Excavator - 30 ton- After Jan 103415.35Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 415.35 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6482 | 20201106-9 | 53510504 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 8 | Dynamic | 110.22 | 0 |  |  | 1175.68 | 152.8384 | 1328.5184 | 2020-11-06 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling and spread from C069 | 5 | C069 | Antler Lake | 0 | 44146 |  | 52 | 44146 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting648220201106-9Excavator - 36 ton- After Jan 1081175.68 | Corbiere and Sons Contracting648220201106-9Excavator - 36 ton- After Jan 1081175.68Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1175.68 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6482 | 20201106-9 | 53510504 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 8 | HR | 9.16 | 0 |  |  | 97.68 | 12.6984 | 110.3784 | 2020-11-06 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling and spread from C069 | 5 | C069 | Antler Lake | 0 | 44146 |  | 52 | 44146 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting648220201106-9Excavator Thumb - 30 - 50 ton- After Jan 10897.68 | Corbiere and Sons Contracting648220201106-9Excavator Thumb - 30 - 50 ton- After Jan 10897.68Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 97.68 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6482 | 20201106-9 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-11-06 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling and spread from C069 | 5 | C069 | Antler Lake | 0 | 44146 |  | 52 | 44146 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting648220201106-9Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting648220201106-9Light Truck - Pick up- After Jan 101243.75Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6482 | 20201106-9 | 53510504 | Access | 0 | Light Truck w/ Tandum Trailer- After Jan 10 | 337.5 | 1 | DAY | 253.13 | 0 |  |  | 337.5 | 43.875 | 381.375 | 2020-11-06 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling and spread from C069 | 5 | C069 | Antler Lake | 0 | 44146 |  | 52 | 44146 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting648220201106-9Light Truck w/ Tandum Trailer- After Jan 101337.5 | Corbiere and Sons Contracting648220201106-9Light Truck w/ Tandum Trailer- After Jan 101337.5Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 337.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6482 | 20201106-9 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 16.5 | Dynamic | 103.54 | 0 |  |  | 2277.825 | 296.1173 | 2573.9423 | 2020-11-06 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling and spread from C069 | 5 | C069 | Antler Lake | 0 | 44146 |  | 52 | 44146 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting648220201106-9Rock Truck - 30 Ton- After Jan 1016.52277.825 | Corbiere and Sons Contracting648220201106-9Rock Truck - 30 Ton- After Jan 1016.52277.825Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 2277.825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6482 | 20201106-9 | 53510504 | Access | 0 | Foreman | 95 | 6 | HR |  |  | 95 | 0 | 570 | 74.1 | 644.1 | 2020-11-06 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling and spread from C069 | 5 | C069 | Antler Lake | 0 | 44146 |  | 52 | 44146 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting648220201106-9Foreman6570 | Corbiere and Sons Contracting648220201106-9Foreman6570Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 570 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6482 | 20201106-9 | 53510504 | Access | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2020-11-06 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling and spread from C069 | 5 | C069 | Antler Lake | 0 | 44146 |  | 52 | 44146 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting648220201106-9L.O.A.61260 | Corbiere and Sons Contracting648220201106-9L.O.A.61260Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6482 | 20201106-9 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 29.5 | HR |  |  | 75 | 0 | 2212.5 | 287.625 | 2500.125 | 2020-11-06 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling and spread from C069 | 5 | C069 | Antler Lake | 0 | 44146 |  | 52 | 44146 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting648220201106-9Operator - Principle - After Jan 1029.52212.5 | Corbiere and Sons Contracting648220201106-9Operator - Principle - After Jan 1029.52212.5Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 2212.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6482 | 20201106-9 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 11.5 | HR |  |  | 70 | 0 | 805 | 104.65 | 909.65 | 2020-11-06 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Hauling and spread from C069 | 5 | C069 | Antler Lake | 0 | 44146 |  | 52 | 44146 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting648220201106-9Driver - AZ - After Jan 1011.5805 | Corbiere and Sons Contracting648220201106-9Driver - AZ - After Jan 1011.5805Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 805 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6501 | 20201107-10 | 53550503 | Earthworks | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10.5 | Dynamic | 110.22 | 0 |  |  | 1543.08 | 200.6004 | 1743.6804 | 2020-11-07 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Access Rock Blasting |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gary at shoefly on Rock Hammer All day | 5 | C050-C069 | Antler Lake | 0 | 44146 |  | 52 | 44146 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting650120201107-10Excavator - 36 ton- After Jan 1010.51543.08 | Corbiere and Sons Contracting650120201107-10Excavator - 36 ton- After Jan 1010.51543.08Inv#071 |  | WF5-Earthwork | WF5-Earthwork |  | 1 | 1 | 1543.08 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6501 | 20201107-10 | 53550503 | Earthworks | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 10.5 | HR | 47.54 | 0 |  |  | 665.49 | 86.5137 | 752.0037 | 2020-11-07 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Access Rock Blasting |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gary at shoefly on Rock Hammer All day | 5 | C050-C069 | Antler Lake | 0 | 44146 |  | 52 | 44146 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting650120201107-10Excavator Hammer - 30 - 50 ton- After Jan 1010.5665.49 | Corbiere and Sons Contracting650120201107-10Excavator Hammer - 30 - 50 ton- After Jan 1010.5665.49Inv#071 |  | WF5-Earthwork | WF5-Earthwork |  | 1 | 1 | 665.49 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6501 | 20201107-10 | 53550503 | Earthworks | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-11-07 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Access Rock Blasting |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gary at shoefly on Rock Hammer All day | 5 | C050-C069 | Antler Lake | 0 | 44146 |  | 52 | 44146 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting650120201107-10Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting650120201107-10Light Truck - Pick up- After Jan 101243.75Inv#071 |  | WF5-Earthwork | WF5-Earthwork |  | 1 | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6501 | 20201107-10 | 53550503 | Earthworks | 0 | Foreman | 95 | 6 | HR |  |  | 95 | 0 | 570 | 74.1 | 644.1 | 2020-11-07 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Access Rock Blasting |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gary at shoefly on Rock Hammer All day | 5 | C050-C069 | Antler Lake | 0 | 44146 |  | 52 | 44146 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting650120201107-10Foreman6570 | Corbiere and Sons Contracting650120201107-10Foreman6570Inv#071 |  | WF5-Earthwork | WF5-Earthwork |  | 1 | 1 | 570 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6501 | 20201107-10 | 53550503 | Earthworks | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-11-07 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Access Rock Blasting |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gary at shoefly on Rock Hammer All day | 5 | C050-C069 | Antler Lake | 0 | 44146 |  | 52 | 44146 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting650120201107-10L.O.A.1210 | Corbiere and Sons Contracting650120201107-10L.O.A.1210Inv#071 |  | WF5-Earthwork | WF5-Earthwork |  | 1 | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6501 | 20201107-10 | 53550503 | Earthworks | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-11-07 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Access Rock Blasting |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gary at shoefly on Rock Hammer All day | 5 | C050-C069 | Antler Lake | 0 | 44146 |  | 52 | 44146 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting650120201107-10Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting650120201107-10Operator - Principle - After Jan 1011.5862.5Inv#071 |  | WF5-Earthwork | WF5-Earthwork |  | 1 | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6503 | 20201107-12 | 53510504 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10.5 | Dynamic | 98.61 | 0 |  |  | 1380.54 | 179.4702 | 1560.0102 | 2020-11-07 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Haul and spread to C100 on Cooks Lake Road East | 5 | C093-C116 | Cook Lake | 0 | 44146 |  | 52 | 44146 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting650320201107-12Dozer D6 or equal- After Jan 1010.51380.54 | Corbiere and Sons Contracting650320201107-12Dozer D6 or equal- After Jan 1010.51380.54Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1380.54 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6503 | 20201107-12 | 53510504 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10.5 | Dynamic | 103.84 | 0 |  |  | 1453.725 | 188.9843 | 1642.7093 | 2020-11-07 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Haul and spread to C100 on Cooks Lake Road East | 5 | C093-C116 | Cook Lake | 0 | 44146 |  | 52 | 44146 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting650320201107-12Excavator - 30 ton- After Jan 1010.51453.725 | Corbiere and Sons Contracting650320201107-12Excavator - 30 ton- After Jan 1010.51453.725Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1453.725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6503 | 20201107-12 | 53510504 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10.5 | HR | 9.16 | 0 |  |  | 128.205 | 16.6667 | 144.8716 | 2020-11-07 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Haul and spread to C100 on Cooks Lake Road East | 5 | C093-C116 | Cook Lake | 0 | 44146 |  | 52 | 44146 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting650320201107-12Excavator Thumb - 30 - 50 ton- After Jan 1010.5128.205 | Corbiere and Sons Contracting650320201107-12Excavator Thumb - 30 - 50 ton- After Jan 1010.5128.205Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 128.205 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6503 | 20201107-12 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2020-11-07 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Haul and spread to C100 on Cooks Lake Road East | 5 | C093-C116 | Cook Lake | 0 | 44146 |  | 52 | 44146 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting650320201107-12Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting650320201107-12Light Truck - Pick up- After Jan 103731.25Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 731.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6503 | 20201107-12 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 21 | Dynamic | 103.54 | 0 |  |  | 2899.05 | 376.8765 | 3275.9265 | 2020-11-07 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Haul and spread to C100 on Cooks Lake Road East | 5 | C093-C116 | Cook Lake | 0 | 44146 |  | 52 | 44146 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting650320201107-12Rock Truck - 30 Ton- After Jan 10212899.05 | Corbiere and Sons Contracting650320201107-12Rock Truck - 30 Ton- After Jan 10212899.05Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 2899.05 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6503 | 20201107-12 | 53510504 | Access | 0 | Foreman | 95 | 4 | HR |  |  | 95 | 0 | 380 | 49.4 | 429.4 | 2020-11-07 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Haul and spread to C100 on Cooks Lake Road East | 5 | C093-C116 | Cook Lake | 0 | 44146 |  | 52 | 44146 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting650320201107-12Foreman4380 | Corbiere and Sons Contracting650320201107-12Foreman4380Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6503 | 20201107-12 | 53510504 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2020-11-07 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Haul and spread to C100 on Cooks Lake Road East | 5 | C093-C116 | Cook Lake | 0 | 44146 |  | 52 | 44146 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting650320201107-12L.O.A.4840 | Corbiere and Sons Contracting650320201107-12L.O.A.4840Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6503 | 20201107-12 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 23 | HR |  |  | 75 | 0 | 1725 | 224.25 | 1949.25 | 2020-11-07 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Haul and spread to C100 on Cooks Lake Road East | 5 | C093-C116 | Cook Lake | 0 | 44146 |  | 52 | 44146 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting650320201107-12Operator - Principle - After Jan 10231725 | Corbiere and Sons Contracting650320201107-12Operator - Principle - After Jan 10231725Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6503 | 20201107-12 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 23 | HR |  |  | 70 | 0 | 1610 | 209.3 | 1819.3 | 2020-11-07 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel Haul and spread to C100 on Cooks Lake Road East | 5 | C093-C116 | Cook Lake | 0 | 44146 |  | 52 | 44146 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting650320201107-12Driver - AZ - After Jan 10231610 | Corbiere and Sons Contracting650320201107-12Driver - AZ - After Jan 10231610Inv#071 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1610 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6504 | 20201107-13 | 53510512 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10.5 | Dynamic | 98.61 | 0 |  |  | 1380.54 | 179.4702 | 1560.0102 | 2020-11-07 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Greg on DZ doing road maintenance from C094-C100 all day | 5 | C093-C116 | Cook Lake | 0 | 44146 |  | 52 | 44146 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting650420201107-13Dozer D6 or equal- After Jan 1010.51380.54 | Corbiere and Sons Contracting650420201107-13Dozer D6 or equal- After Jan 1010.51380.54Inv#071 | [5 empty] | 1 | 1380.54 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6504 | 20201107-13 | 53510512 | Access | 0 | Foreman | 95 | 4 | HR |  |  | 95 | 0 | 380 | 49.4 | 429.4 | 2020-11-07 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Greg on DZ doing road maintenance from C094-C100 all day | 5 | C093-C116 | Cook Lake | 0 | 44146 |  | 52 | 44146 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting650420201107-13Foreman4380 | Corbiere and Sons Contracting650420201107-13Foreman4380Inv#071 | [5 empty] | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6504 | 20201107-13 | 53510512 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-11-07 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Greg on DZ doing road maintenance from C094-C100 all day | 5 | C093-C116 | Cook Lake | 0 | 44146 |  | 52 | 44146 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting650420201107-13L.O.A.1210 | Corbiere and Sons Contracting650420201107-13L.O.A.1210Inv#071 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6504 | 20201107-13 | 53510512 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-11-07 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Greg on DZ doing road maintenance from C094-C100 all day | 5 | C093-C116 | Cook Lake | 0 | 44146 |  | 52 | 44146 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting650420201107-13Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting650420201107-13Operator - Principle - After Jan 1011.5862.5Inv#071 | [5 empty] | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6500 | 20201107-9 | 53510512 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 6 | Dynamic | 98.61 | 0 |  |  | 788.88 | 102.5544 | 891.4344 | 2020-11-07 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | DZ doing road maintenance from C061-C069 | 5 | C061-C069 | Antler Lake | 0 | 44146 |  | 52 | 44146 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting650020201107-9Dozer D6 or equal- After Jan 106788.88 | Corbiere and Sons Contracting650020201107-9Dozer D6 or equal- After Jan 106788.88Inv#071 | [5 empty] | 1 | 788.88 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6500 | 20201107-9 | 53510512 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-11-07 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | DZ doing road maintenance from C061-C069 | 5 | C061-C069 | Antler Lake | 0 | 44146 |  | 52 | 44146 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting650020201107-9L.O.A.1210 | Corbiere and Sons Contracting650020201107-9L.O.A.1210Inv#071 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6500 | 20201107-9 | 53510512 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 75 | 0 | 450 | 58.5 | 508.5 | 2020-11-07 | 1 | Inv#071 | 44148 | 125 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | DZ doing road maintenance from C061-C069 | 5 | C061-C069 | Antler Lake | 0 | 44146 |  | 52 | 44146 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting650020201107-9Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting650020201107-9Operator - Principle - After Jan 106450Inv#071 | [5 empty] | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6541 | 20201108-12 | 53510312 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 9 | Dynamic | 110.22 | 0 |  |  | 1322.64 | 171.9432 | 1494.5832 | 2020-11-08 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-07 installed cross frain culverts and ditched along mail access road Gurney Lake Rd | 3 | B187-B193 | Gurney Lake Road | 0 | 44147 |  | 37 | 44147 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting654120201108-12Excavator - 36 ton- After Jan 1091322.64 | Corbiere and Sons Contracting654120201108-12Excavator - 36 ton- After Jan 1091322.64Inv#076 | [5 empty] | 1 | 1322.64 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6541 | 20201108-12 | 53510312 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2020-11-08 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-07 installed cross frain culverts and ditched along mail access road Gurney Lake Rd | 3 | B187-B193 | Gurney Lake Road | 0 | 44147 |  | 37 | 44147 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting654120201108-12Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting654120201108-12Excavator Thumb - 30 - 50 ton- After Jan 109109.89Inv#076 | [5 empty] | 1 | 109.89 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6541 | 20201108-12 | 53510312 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-11-08 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-07 installed cross frain culverts and ditched along mail access road Gurney Lake Rd | 3 | B187-B193 | Gurney Lake Road | 0 | 44147 |  | 37 | 44147 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting654120201108-12Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting654120201108-12Light Truck - Pick up- After Jan 101243.75Inv#076 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6541 | 20201108-12 | 53510312 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 9 | HR |  |  | 75 | 0 | 675 | 87.75 | 762.75 | 2020-11-08 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-07 installed cross frain culverts and ditched along mail access road Gurney Lake Rd | 3 | B187-B193 | Gurney Lake Road | 0 | 44147 |  | 37 | 44147 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting654120201108-12Operator - Principle - After Jan 109675 | Corbiere and Sons Contracting654120201108-12Operator - Principle - After Jan 109675Inv#076 | [5 empty] | 1 | 675 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6513 | 20201108-8-R1 | 53550503 | Earthworks | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10.5 | Dynamic | 110.22 | 0 |  |  | 1543.08 | 200.6004 | 1743.6804 | 2020-11-08 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Access Rock Blasting |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock Hammering all day from big hill on shoefly | 5 | C050-C069 | Antler Lake | 0 | 44146 |  | 52 | 44147 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting651320201108-8-R1Excavator - 36 ton- After Jan 1010.51543.08 | Corbiere and Sons Contracting651320201108-8-R1Excavator - 36 ton- After Jan 1010.51543.08Inv#076 |  | WF5-Earthwork | WF5-Earthwork |  | 1 | 1 | 1543.08 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6513 | 20201108-8-R1 | 53550503 | Earthworks | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 10.5 | HR | 47.54 | 0 |  |  | 665.49 | 86.5137 | 752.0037 | 2020-11-08 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Access Rock Blasting |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock Hammering all day from big hill on shoefly | 5 | C050-C069 | Antler Lake | 0 | 44146 |  | 52 | 44147 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting651320201108-8-R1Excavator Hammer - 30 - 50 ton- After Jan 1010.5665.49 | Corbiere and Sons Contracting651320201108-8-R1Excavator Hammer - 30 - 50 ton- After Jan 1010.5665.49Inv#076 |  | WF5-Earthwork | WF5-Earthwork |  | 1 | 1 | 665.49 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6513 | 20201108-8-R1 | 53550503 | Earthworks | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-11-08 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Access Rock Blasting |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock Hammering all day from big hill on shoefly | 5 | C050-C069 | Antler Lake | 0 | 44146 |  | 52 | 44147 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting651320201108-8-R1Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting651320201108-8-R1Light Truck - Pick up- After Jan 101243.75Inv#076 |  | WF5-Earthwork | WF5-Earthwork |  | 1 | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6513 | 20201108-8-R1 | 53550503 | Earthworks | 0 | Foreman | 95 | 4 | HR |  |  | 95 | 0 | 380 | 49.4 | 429.4 | 2020-11-08 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Access Rock Blasting |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock Hammering all day from big hill on shoefly | 5 | C050-C069 | Antler Lake | 0 | 44146 |  | 52 | 44147 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting651320201108-8-R1Foreman4380 | Corbiere and Sons Contracting651320201108-8-R1Foreman4380Inv#076 |  | WF5-Earthwork | WF5-Earthwork |  | 1 | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6513 | 20201108-8-R1 | 53550503 | Earthworks | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-11-08 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Access Rock Blasting |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock Hammering all day from big hill on shoefly | 5 | C050-C069 | Antler Lake | 0 | 44146 |  | 52 | 44147 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting651320201108-8-R1L.O.A.1210 | Corbiere and Sons Contracting651320201108-8-R1L.O.A.1210Inv#076 |  | WF5-Earthwork | WF5-Earthwork |  | 1 | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6513 | 20201108-8-R1 | 53550503 | Earthworks | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-11-08 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Access Rock Blasting |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock Hammering all day from big hill on shoefly | 5 | C050-C069 | Antler Lake | 0 | 44146 |  | 52 | 44147 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting651320201108-8-R1Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting651320201108-8-R1Operator - Principle - After Jan 1011.5862.5Inv#076 |  | WF5-Earthwork | WF5-Earthwork |  | 1 | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6546 | 20201109-10 | 53510312 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10 | Dynamic | 110.22 | 0 |  |  | 1469.6 | 191.048 | 1660.648 | 2020-11-09 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixed bad spots in the road and added material where possible. Layed mats down at B-082 hill Landfill Rd. | 3 | B078-B084 | Red Rock Rd No. 7 | 0 | 44147 |  | 37 | 44147 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting654620201109-10Excavator - 36 ton- After Jan 10101469.6 | Corbiere and Sons Contracting654620201109-10Excavator - 36 ton- After Jan 10101469.6Inv#076 | [5 empty] | 1 | 1469.6 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6546 | 20201109-10 | 53510312 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 9.16 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2020-11-09 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixed bad spots in the road and added material where possible. Layed mats down at B-082 hill Landfill Rd. | 3 | B078-B084 | Red Rock Rd No. 7 | 0 | 44147 |  | 37 | 44147 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting654620201109-10Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting654620201109-10Excavator Thumb - 30 - 50 ton- After Jan 1010122.1Inv#076 | [5 empty] | 1 | 122.1 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6546 | 20201109-10 | 53510312 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-11-09 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixed bad spots in the road and added material where possible. Layed mats down at B-082 hill Landfill Rd. | 3 | B078-B084 | Red Rock Rd No. 7 | 0 | 44147 |  | 37 | 44147 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting654620201109-10Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting654620201109-10Light Truck - Pick up- After Jan 101243.75Inv#076 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6546 | 20201109-10 | 53510312 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2020-11-09 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixed bad spots in the road and added material where possible. Layed mats down at B-082 hill Landfill Rd. | 3 | B078-B084 | Red Rock Rd No. 7 | 0 | 44147 |  | 37 | 44147 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting654620201109-10Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting654620201109-10Operator - Principle - After Jan 1011825Inv#076 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6570 | 20201109-17 | 53510512 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 9.5 | Dynamic | 98.61 | 0 |  |  | 1249.06 | 162.3778 | 1411.4378 | 2020-11-09 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Maintenance on roads, fixing washouts | 5 | C-050 - C-069 | Antler Lake | 0 | 44147 |  | 52 | 44149 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting657020201109-17Dozer D6 or equal- After Jan 109.51249.06 | Corbiere and Sons Contracting657020201109-17Dozer D6 or equal- After Jan 109.51249.06Inv#076 | [5 empty] | 1 | 1249.06 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6570 | 20201109-17 | 53510512 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10.5 | Dynamic | 103.84 | 0 |  |  | 1453.725 | 188.9843 | 1642.7093 | 2020-11-09 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Maintenance on roads, fixing washouts | 5 | C-050 - C-069 | Antler Lake | 0 | 44147 |  | 52 | 44149 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting657020201109-17Excavator - 30 ton- After Jan 1010.51453.725 | Corbiere and Sons Contracting657020201109-17Excavator - 30 ton- After Jan 1010.51453.725Inv#076 | [5 empty] | 1 | 1453.725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6570 | 20201109-17 | 53510512 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 3 | HR | 9.16 | 0 |  |  | 36.63 | 4.7619 | 41.3919 | 2020-11-09 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Maintenance on roads, fixing washouts | 5 | C-050 - C-069 | Antler Lake | 0 | 44147 |  | 52 | 44149 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting657020201109-17Excavator Thumb - 30 - 50 ton- After Jan 10336.63 | Corbiere and Sons Contracting657020201109-17Excavator Thumb - 30 - 50 ton- After Jan 10336.63Inv#076 | [5 empty] | 1 | 36.63 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6570 | 20201109-17 | 53510512 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-11-09 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Maintenance on roads, fixing washouts | 5 | C-050 - C-069 | Antler Lake | 0 | 44147 |  | 52 | 44149 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting657020201109-17Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting657020201109-17Light Truck - Pick up- After Jan 102487.5Inv#076 | [5 empty] | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6570 | 20201109-17 | 53510512 | Access | 0 | Foreman | 95 | 6 | HR |  |  | 95 | 0 | 570 | 74.1 | 644.1 | 2020-11-09 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Maintenance on roads, fixing washouts | 5 | C-050 - C-069 | Antler Lake | 0 | 44147 |  | 52 | 44149 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting657020201109-17Foreman6570 | Corbiere and Sons Contracting657020201109-17Foreman6570Inv#076 | [5 empty] | 1 | 570 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6570 | 20201109-17 | 53510512 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2020-11-09 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Maintenance on roads, fixing washouts | 5 | C-050 - C-069 | Antler Lake | 0 | 44147 |  | 52 | 44149 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting657020201109-17L.O.A.3630 | Corbiere and Sons Contracting657020201109-17L.O.A.3630Inv#076 | [5 empty] | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6570 | 20201109-17 | 53510512 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 22 | HR |  |  | 75 | 0 | 1650 | 214.5 | 1864.5 | 2020-11-09 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Maintenance on roads, fixing washouts | 5 | C-050 - C-069 | Antler Lake | 0 | 44147 |  | 52 | 44149 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting657020201109-17Operator - Principle - After Jan 10221650 | Corbiere and Sons Contracting657020201109-17Operator - Principle - After Jan 10221650Inv#076 | [5 empty] | 1 | 1650 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6572 | 20201109-18 | 53550503 | Earthworks | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-11-09 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Nathan Kyme | Access Rock Blasting |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gary hammering ditch line on the big hill from C-065 - C-069 shoefly, Greg 1 hour spreading rock from hammer. | 5 | C-050 - C-069 | Antler Lake Rd | 0 | 44147 |  | 52 | 44149 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting657220201109-18L.O.A.1210 | Corbiere and Sons Contracting657220201109-18L.O.A.1210Inv#076 |  | WF5-Earthwork | WF5-Earthwork |  | 1 | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6572 | 20201109-18 | 53550503 | Earthworks | 0 | Operator - Principle - After Jan 10 | 75 | 12.5 | HR |  |  | 75 | 0 | 937.5 | 121.875 | 1059.375 | 2020-11-09 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Nathan Kyme | Access Rock Blasting |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gary hammering ditch line on the big hill from C-065 - C-069 shoefly, Greg 1 hour spreading rock from hammer. | 5 | C-050 - C-069 | Antler Lake Rd | 0 | 44147 |  | 52 | 44149 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting657220201109-18Operator - Principle - After Jan 1012.5937.5 | Corbiere and Sons Contracting657220201109-18Operator - Principle - After Jan 1012.5937.5Inv#076 |  | WF5-Earthwork | WF5-Earthwork |  | 1 | 1 | 937.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6571 | 20201109-19 | 53560502 | Water Crossings | 0 | Labourer - General - After Jan 10 | 60 | 19.5 | HR |  |  | 60 | 0 | 1170 | 152.1 | 1322.1 | 2020-11-09 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Nathan Kyme | >6M Water Crossing Install |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavators working on install of WC7550, installing bridge abutments, pads and build approaches for WC7550.01, laid armoured rock. Rock trucks hauled for WC7550.01 for 8.5 hours, and WC7541 for 3 hoursLabourers worked on WCs - set up rigging and sling chains | 5 | C-076 - C-092 | Cook Lake Rd | 0 | 44147 |  | 52 | 44149 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting657120201109-19Labourer - General - After Jan 1019.51170 | Corbiere and Sons Contracting657120201109-19Labourer - General - After Jan 1019.51170Inv#076 |  |  | WF5-WaterCrossing |  |  | 0.16667 | 195 | WC403 | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6573 | 20201109-20 | 53510504 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 6.5 | Dynamic | 110.22 | 0 |  |  | 955.24 | 124.1812 | 1079.4212 | 2020-11-09 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Loaded rock trucks for haul the remainder of day | 5 | C-076 - C-116 | Cook Lake Rd | 0 | 44147 |  | 52 | 44149 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting657320201109-20Excavator - 36 ton- After Jan 106.5955.24 | Corbiere and Sons Contracting657320201109-20Excavator - 36 ton- After Jan 106.5955.24Inv#076 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 955.24 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6573 | 20201109-20 | 53510504 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-11-09 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Loaded rock trucks for haul the remainder of day | 5 | C-076 - C-116 | Cook Lake Rd | 0 | 44147 |  | 52 | 44149 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting657320201109-20L.O.A.1210 | Corbiere and Sons Contracting657320201109-20L.O.A.1210Inv#076 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6573 | 20201109-20 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 7 | HR |  |  | 75 | 0 | 525 | 68.25 | 593.25 | 2020-11-09 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Loaded rock trucks for haul the remainder of day | 5 | C-076 - C-116 | Cook Lake Rd | 0 | 44147 |  | 52 | 44149 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting657320201109-20Operator - Principle - After Jan 107525 | Corbiere and Sons Contracting657320201109-20Operator - Principle - After Jan 107525Inv#076 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 525 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6574 | 20201109-21 | 53510512 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10.5 | Dynamic | 98.61 | 0 |  |  | 1380.54 | 179.4702 | 1560.0102 | 2020-11-09 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX completeing toad maintenance from C-093, Dozer completing road maintenance from WC7491 to C-102 | 5 | C-076 - C-116 | Cook Lake | 0 | 44147 |  | 52 | 44149 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting657420201109-21Dozer D6 or equal- After Jan 1010.51380.54 | Corbiere and Sons Contracting657420201109-21Dozer D6 or equal- After Jan 1010.51380.54Inv#076 | [5 empty] | 1 | 1380.54 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6574 | 20201109-21 | 53510512 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 5 | Dynamic | 103.84 | 0 |  |  | 692.25 | 89.9925 | 782.2425 | 2020-11-09 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX completeing toad maintenance from C-093, Dozer completing road maintenance from WC7491 to C-102 | 5 | C-076 - C-116 | Cook Lake | 0 | 44147 |  | 52 | 44149 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting657420201109-21Excavator - 30 ton- After Jan 105692.25 | Corbiere and Sons Contracting657420201109-21Excavator - 30 ton- After Jan 105692.25Inv#076 | [5 empty] | 1 | 692.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6574 | 20201109-21 | 53510512 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 5 | HR | 9.16 | 0 |  |  | 61.05 | 7.9365 | 68.9865 | 2020-11-09 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX completeing toad maintenance from C-093, Dozer completing road maintenance from WC7491 to C-102 | 5 | C-076 - C-116 | Cook Lake | 0 | 44147 |  | 52 | 44149 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting657420201109-21Excavator Thumb - 30 - 50 ton- After Jan 10561.05 | Corbiere and Sons Contracting657420201109-21Excavator Thumb - 30 - 50 ton- After Jan 10561.05Inv#076 | [5 empty] | 1 | 61.05 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6574 | 20201109-21 | 53510512 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-11-09 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX completeing toad maintenance from C-093, Dozer completing road maintenance from WC7491 to C-102 | 5 | C-076 - C-116 | Cook Lake | 0 | 44147 |  | 52 | 44149 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting657420201109-21Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting657420201109-21Light Truck - Pick up- After Jan 101243.75Inv#076 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6574 | 20201109-21 | 53510512 | Access | 0 | Foreman | 95 | 4 | HR |  |  | 95 | 0 | 380 | 49.4 | 429.4 | 2020-11-09 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX completeing toad maintenance from C-093, Dozer completing road maintenance from WC7491 to C-102 | 5 | C-076 - C-116 | Cook Lake | 0 | 44147 |  | 52 | 44149 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting657420201109-21Foreman4380 | Corbiere and Sons Contracting657420201109-21Foreman4380Inv#076 | [5 empty] | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6574 | 20201109-21 | 53510512 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-11-09 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX completeing toad maintenance from C-093, Dozer completing road maintenance from WC7491 to C-102 | 5 | C-076 - C-116 | Cook Lake | 0 | 44147 |  | 52 | 44149 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting657420201109-21L.O.A.2420 | Corbiere and Sons Contracting657420201109-21L.O.A.2420Inv#076 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6574 | 20201109-21 | 53510512 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 17 | HR |  |  | 75 | 0 | 1275 | 165.75 | 1440.75 | 2020-11-09 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX completeing toad maintenance from C-093, Dozer completing road maintenance from WC7491 to C-102 | 5 | C-076 - C-116 | Cook Lake | 0 | 44147 |  | 52 | 44149 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting657420201109-21Operator - Principle - After Jan 10171275 | Corbiere and Sons Contracting657420201109-21Operator - Principle - After Jan 10171275Inv#076 | [5 empty] | 1 | 1275 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6575 | 20201109-22 | 53510502 | Access | 0 | Skidder | 171 | 6 | HR | 128.25 | 0 |  |  | 1026 | 133.38 | 1159.38 | 2020-11-09 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Skidder haul corduroy to access for C102-C-103Labourers lay geo | 5 | C-076 - C-116 | Cook Lake | 0 | 44147 |  | 52 | 44149 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting657520201109-22Skidder 61026 | Corbiere and Sons Contracting657520201109-22Skidder 61026Inv#076 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 1026 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6575 | 20201109-22 | 53510502 | Access | 0 | Foreman | 95 | 2 | HR |  |  | 95 | 0 | 190 | 24.7 | 214.7 | 2020-11-09 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Skidder haul corduroy to access for C102-C-103Labourers lay geo | 5 | C-076 - C-116 | Cook Lake | 0 | 44147 |  | 52 | 44149 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting657520201109-22Foreman2190 | Corbiere and Sons Contracting657520201109-22Foreman2190Inv#076 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 190 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6575 | 20201109-22 | 53510502 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-11-09 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Skidder haul corduroy to access for C102-C-103Labourers lay geo | 5 | C-076 - C-116 | Cook Lake | 0 | 44147 |  | 52 | 44149 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting657520201109-22L.O.A.1210 | Corbiere and Sons Contracting657520201109-22L.O.A.1210Inv#076 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6575 | 20201109-22 | 53510502 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 75 | 0 | 450 | 58.5 | 508.5 | 2020-11-09 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Skidder haul corduroy to access for C102-C-103Labourers lay geo | 5 | C-076 - C-116 | Cook Lake | 0 | 44147 |  | 52 | 44149 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting657520201109-22Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting657520201109-22Operator - Principle - After Jan 106450Inv#076 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6575 | 20201109-22 | 53510502 | Access | 0 | Labourer - General - After Jan 10 | 60 | 6 | HR |  |  | 60 | 0 | 360 | 46.8 | 406.8 | 2020-11-09 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Skidder haul corduroy to access for C102-C-103Labourers lay geo | 5 | C-076 - C-116 | Cook Lake | 0 | 44147 |  | 52 | 44149 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting657520201109-22Labourer - General - After Jan 106360 | Corbiere and Sons Contracting657520201109-22Labourer - General - After Jan 106360Inv#076 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 360 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6677 | 20201110-15 | 53510512 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 6 | Dynamic | 103.84 | 0 |  |  | 830.7 | 107.991 | 938.691 | 2020-11-10 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixing sink holes at C-057 | 5 | C050-C069 | Antler Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting667720201110-15Excavator - 30 ton- After Jan 106830.7 | Corbiere and Sons Contracting667720201110-15Excavator - 30 ton- After Jan 106830.7Inv#076 | [5 empty] | 1 | 830.7 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6677 | 20201110-15 | 53510512 | Access | 0 | Foreman | 95 | 3 | HR |  |  | 95 | 0 | 285 | 37.05 | 322.05 | 2020-11-10 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixing sink holes at C-057 | 5 | C050-C069 | Antler Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting667720201110-15Foreman3285 | Corbiere and Sons Contracting667720201110-15Foreman3285Inv#076 | [5 empty] | 1 | 285 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6677 | 20201110-15 | 53510512 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-11-10 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixing sink holes at C-057 | 5 | C050-C069 | Antler Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting667720201110-15L.O.A.1210 | Corbiere and Sons Contracting667720201110-15L.O.A.1210Inv#076 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6677 | 20201110-15 | 53510512 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 75 | 0 | 450 | 58.5 | 508.5 | 2020-11-10 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixing sink holes at C-057 | 5 | C050-C069 | Antler Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting667720201110-15Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting667720201110-15Operator - Principle - After Jan 106450Inv#076 | [5 empty] | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6680 | 20201110-18 | 53550503 | Earthworks | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 3 | Dynamic | 103.84 | 0 |  |  | 415.35 | 53.9955 | 469.3455 | 2020-11-10 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Access Rock Blasting |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 30 ton cleaning up rock from rock hammer Greg on rock hammer from C-061 Gary on rock hammer from C-065 - C-069 | 5 | C050-C069 | Antler Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting668020201110-18Excavator - 30 ton- After Jan 103415.35 | Corbiere and Sons Contracting668020201110-18Excavator - 30 ton- After Jan 103415.35Inv#076 |  | WF5-Earthwork | WF5-Earthwork |  | 1 | 1 | 415.35 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6680 | 20201110-18 | 53550503 | Earthworks | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 21 | Dynamic | 110.22 | 0 |  |  | 3086.16 | 401.2008 | 3487.3608 | 2020-11-10 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Access Rock Blasting |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 30 ton cleaning up rock from rock hammer Greg on rock hammer from C-061 Gary on rock hammer from C-065 - C-069 | 5 | C050-C069 | Antler Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting668020201110-18Excavator - 36 ton- After Jan 10213086.16 | Corbiere and Sons Contracting668020201110-18Excavator - 36 ton- After Jan 10213086.16Inv#076 |  | WF5-Earthwork | WF5-Earthwork |  | 1 | 1 | 3086.16 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6680 | 20201110-18 | 53550503 | Earthworks | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 3 | HR | 9.16 | 0 |  |  | 36.63 | 4.7619 | 41.3919 | 2020-11-10 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Access Rock Blasting |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 30 ton cleaning up rock from rock hammer Greg on rock hammer from C-061 Gary on rock hammer from C-065 - C-069 | 5 | C050-C069 | Antler Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting668020201110-18Excavator Thumb - 30 - 50 ton- After Jan 10336.63 | Corbiere and Sons Contracting668020201110-18Excavator Thumb - 30 - 50 ton- After Jan 10336.63Inv#076 |  | WF5-Earthwork | WF5-Earthwork |  | 1 | 1 | 36.63 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6680 | 20201110-18 | 53550503 | Earthworks | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 21 | HR | 47.54 | 0 |  |  | 1330.98 | 173.0274 | 1504.0074 | 2020-11-10 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Access Rock Blasting |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 30 ton cleaning up rock from rock hammer Greg on rock hammer from C-061 Gary on rock hammer from C-065 - C-069 | 5 | C050-C069 | Antler Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting668020201110-18Excavator Hammer - 30 - 50 ton- After Jan 10211330.98 | Corbiere and Sons Contracting668020201110-18Excavator Hammer - 30 - 50 ton- After Jan 10211330.98Inv#076 |  | WF5-Earthwork | WF5-Earthwork |  | 1 | 1 | 1330.98 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6680 | 20201110-18 | 53550503 | Earthworks | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-11-10 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Access Rock Blasting |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 30 ton cleaning up rock from rock hammer Greg on rock hammer from C-061 Gary on rock hammer from C-065 - C-069 | 5 | C050-C069 | Antler Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting668020201110-18Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting668020201110-18Light Truck - Pick up- After Jan 101243.75Inv#076 |  | WF5-Earthwork | WF5-Earthwork |  | 1 | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6680 | 20201110-18 | 53550503 | Earthworks | 0 | Light Truck w/ Tandum Trailer- After Jan 10 | 337.5 | 1 | DAY | 253.13 | 0 |  |  | 337.5 | 43.875 | 381.375 | 2020-11-10 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Access Rock Blasting |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 30 ton cleaning up rock from rock hammer Greg on rock hammer from C-061 Gary on rock hammer from C-065 - C-069 | 5 | C050-C069 | Antler Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting668020201110-18Light Truck w/ Tandum Trailer- After Jan 101337.5 | Corbiere and Sons Contracting668020201110-18Light Truck w/ Tandum Trailer- After Jan 101337.5Inv#076 |  | WF5-Earthwork | WF5-Earthwork |  | 1 | 1 | 337.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6680 | 20201110-18 | 53550503 | Earthworks | 0 | Foreman | 95 | 6 | HR |  |  | 95 | 0 | 570 | 74.1 | 644.1 | 2020-11-10 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Access Rock Blasting |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 30 ton cleaning up rock from rock hammer Greg on rock hammer from C-061 Gary on rock hammer from C-065 - C-069 | 5 | C050-C069 | Antler Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting668020201110-18Foreman6570 | Corbiere and Sons Contracting668020201110-18Foreman6570Inv#076 |  | WF5-Earthwork | WF5-Earthwork |  | 1 | 1 | 570 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6680 | 20201110-18 | 53550503 | Earthworks | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2020-11-10 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Access Rock Blasting |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 30 ton cleaning up rock from rock hammer Greg on rock hammer from C-061 Gary on rock hammer from C-065 - C-069 | 5 | C050-C069 | Antler Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting668020201110-18L.O.A.3630 | Corbiere and Sons Contracting668020201110-18L.O.A.3630Inv#076 |  | WF5-Earthwork | WF5-Earthwork |  | 1 | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6680 | 20201110-18 | 53550503 | Earthworks | 0 | Operator - Principle - After Jan 10 | 75 | 26.5 | HR |  |  | 75 | 0 | 1987.5 | 258.375 | 2245.875 | 2020-11-10 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Access Rock Blasting |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 30 ton cleaning up rock from rock hammer Greg on rock hammer from C-061 Gary on rock hammer from C-065 - C-069 | 5 | C050-C069 | Antler Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting668020201110-18Operator - Principle - After Jan 1026.51987.5 | Corbiere and Sons Contracting668020201110-18Operator - Principle - After Jan 1026.51987.5Inv#076 |  | WF5-Earthwork | WF5-Earthwork |  | 1 | 1 | 1987.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6681 | 20201110-19 | 53510503 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 5 | Dynamic | 110.22 | 0 |  |  | 734.8 | 95.524 | 830.324 | 2020-11-10 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Laid down 50m of corduroy from C-101. | 5 | C093-C116 | Cook Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting668120201110-19Excavator - 36 ton- After Jan 105734.8 | Corbiere and Sons Contracting668120201110-19Excavator - 36 ton- After Jan 105734.8Inv#076 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 734.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6681 | 20201110-19 | 53510503 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-11-10 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Laid down 50m of corduroy from C-101. | 5 | C093-C116 | Cook Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting668120201110-19L.O.A.1210 | Corbiere and Sons Contracting668120201110-19L.O.A.1210Inv#076 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6681 | 20201110-19 | 53510503 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5.5 | HR |  |  | 75 | 0 | 412.5 | 53.625 | 466.125 | 2020-11-10 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Laid down 50m of corduroy from C-101. | 5 | C093-C116 | Cook Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting668120201110-19Operator - Principle - After Jan 105.5412.5 | Corbiere and Sons Contracting668120201110-19Operator - Principle - After Jan 105.5412.5Inv#076 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 412.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6682 | 20201110-20 | 53560502 | Water Crossings | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 7.5 | Dynamic | 110.22 | 0 |  |  | 1102.2 | 143.286 | 1245.486 | 2020-11-10 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | >6M Water Crossing Install |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Sorting out 2" minus clean rock for temp crossing WC7541 Skidder mobing in WC7580.01 Labourers escort skidder and WC7580.01 in | 5 | C076-C116 | Cook Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting668220201110-20Excavator - 36 ton- After Jan 107.51102.2 | Corbiere and Sons Contracting668220201110-20Excavator - 36 ton- After Jan 107.51102.2Inv#076 |  |  | WF5-WaterCrossing |  |  | 0.5 | 551.1 | WC403 | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6682 | 20201110-20 | 53560502 | Water Crossings | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-11-10 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | >6M Water Crossing Install |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Sorting out 2" minus clean rock for temp crossing WC7541 Skidder mobing in WC7580.01 Labourers escort skidder and WC7580.01 in | 5 | C076-C116 | Cook Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting668220201110-20Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting668220201110-20Operator - Principle - After Jan 1011.5862.5Inv#076 |  |  | WF5-WaterCrossing |  |  | 0.32609 | 281.25 | WC403 | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6684 | 20201110-22 | 53510512 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 6 | Dynamic | 98.61 | 0 |  |  | 788.88 | 102.5544 | 891.4344 | 2020-11-10 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance from WC7491 | 5 | C076-C116 | Cook Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting668420201110-22Dozer D6 or equal- After Jan 106788.88 | Corbiere and Sons Contracting668420201110-22Dozer D6 or equal- After Jan 106788.88Inv#076 | [5 empty] | 1 | 788.88 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6684 | 20201110-22 | 53510512 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-11-10 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance from WC7491 | 5 | C076-C116 | Cook Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting668420201110-22L.O.A.1210 | Corbiere and Sons Contracting668420201110-22L.O.A.1210Inv#076 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6684 | 20201110-22 | 53510512 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6.5 | HR |  |  | 75 | 0 | 487.5 | 63.375 | 550.875 | 2020-11-10 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance from WC7491 | 5 | C076-C116 | Cook Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting668420201110-22Operator - Principle - After Jan 106.5487.5 | Corbiere and Sons Contracting668420201110-22Operator - Principle - After Jan 106.5487.5Inv#076 | [5 empty] | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6685 | 20201110-23 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 15 | Dynamic | 103.54 |  |  |  | 2070.75 | 269.1975 | 2339.9475 | 2020-11-10 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock truck drivers sent home as road conditions too soft | 5 | C076-C116 | Cook Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting668520201110-23Rock Truck - 30 Ton- After Jan 10152070.75 | Corbiere and Sons Contracting668520201110-23Rock Truck - 30 Ton- After Jan 10152070.75Inv#076 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 2070.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6685 | 20201110-23 | 53510504 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2020-11-10 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock truck drivers sent home as road conditions too soft | 5 | C076-C116 | Cook Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting668520201110-23L.O.A.3630 | Corbiere and Sons Contracting668520201110-23L.O.A.3630Inv#076 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6685 | 20201110-23 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 15 | HR |  |  | 70 | 0 | 1050 | 136.5 | 1186.5 | 2020-11-10 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock truck drivers sent home as road conditions too soft | 5 | C076-C116 | Cook Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting668520201110-23Driver - AZ - After Jan 10151050 | Corbiere and Sons Contracting668520201110-23Driver - AZ - After Jan 10151050Inv#076 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6586 | 20201110-8 | 53510312 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 5 | Dynamic | 110.22 | 0 |  |  | 734.8 | 95.524 | 830.324 | 2020-11-10 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixed bad spots in the road and added material where possible | 3 | B-078 - B-084 | Red Rock Rd No. 7 | 0 | 44148 |  | 37 | 44149 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting658620201110-8Excavator - 36 ton- After Jan 105734.8 | Corbiere and Sons Contracting658620201110-8Excavator - 36 ton- After Jan 105734.8Inv#076 | [5 empty] | 1 | 734.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6586 | 20201110-8 | 53510312 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 5 | HR | 9.16 | 0 |  |  | 61.05 | 7.9365 | 68.9865 | 2020-11-10 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixed bad spots in the road and added material where possible | 3 | B-078 - B-084 | Red Rock Rd No. 7 | 0 | 44148 |  | 37 | 44149 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting658620201110-8Excavator Thumb - 30 - 50 ton- After Jan 10561.05 | Corbiere and Sons Contracting658620201110-8Excavator Thumb - 30 - 50 ton- After Jan 10561.05Inv#076 | [5 empty] | 1 | 61.05 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6586 | 20201110-8 | 53510312 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5 | HR |  |  | 75 | 0 | 375 | 48.75 | 423.75 | 2020-11-10 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixed bad spots in the road and added material where possible | 3 | B-078 - B-084 | Red Rock Rd No. 7 | 0 | 44148 |  | 37 | 44149 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting658620201110-8Operator - Principle - After Jan 105375 | Corbiere and Sons Contracting658620201110-8Operator - Principle - After Jan 105375Inv#076 | [5 empty] | 1 | 375 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6605 | 20201111-11 | 53510502 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 2 | Dynamic | 91.79 | 0 |  |  | 244.78 | 31.8214 | 276.6014 | 2020-11-11 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float picked up 5 rolls of geo from Valard Marathon yard and brought them to Cooks Lake laydown | 5 | C076-C116 | Cook Lake | 0 | 44150 |  | 52 | 44152 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting660520201111-11Tractor Trailer - 60 Ton- After Jan 102244.78 | Corbiere and Sons Contracting660520201111-11Tractor Trailer - 60 Ton- After Jan 102244.78Inv#076 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 244.78 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6605 | 20201111-11 | 53510502 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 2 | HR |  |  | 70 | 0 | 140 | 18.2 | 158.2 | 2020-11-11 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float picked up 5 rolls of geo from Valard Marathon yard and brought them to Cooks Lake laydown | 5 | C076-C116 | Cook Lake | 0 | 44150 |  | 52 | 44152 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting660520201111-11Driver - AZ - After Jan 102140 | Corbiere and Sons Contracting660520201111-11Driver - AZ - After Jan 102140Inv#076 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6606 | 20201111-12 | 53560501 | Water Crossings | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 6 | Dynamic | 110.22 | 0 |  |  | 881.76 | 114.6288 | 996.3888 | 2020-11-11 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Nathan Kyme | <6M Water Crossing Install |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-011 and labourers installed temp crossing 7541 | 5 | C076-C116 | Cook Lake Rd | 0 | 44150 |  | 52 | 44152 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting660620201111-12Excavator - 36 ton- After Jan 106881.76 | Corbiere and Sons Contracting660620201111-12Excavator - 36 ton- After Jan 106881.76Inv#076 |  |  | WF5-WaterCrossing |  |  | 1 | 881.76 | WC403 | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6606 | 20201111-12 | 53560501 | Water Crossings | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-11-11 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Nathan Kyme | <6M Water Crossing Install |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-011 and labourers installed temp crossing 7541 | 5 | C076-C116 | Cook Lake Rd | 0 | 44150 |  | 52 | 44152 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting660620201111-12Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting660620201111-12Light Truck - Pick up- After Jan 101243.75Inv#076 |  |  | WF5-WaterCrossing |  |  | 1 | 243.75 | WC403 | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6606 | 20201111-12 | 53560501 | Water Crossings | 0 | Light Truck w/ Tandum Trailer- After Jan 10 | 337.5 | 1 | DAY | 253.13 | 0 |  |  | 337.5 | 43.875 | 381.375 | 2020-11-11 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Nathan Kyme | <6M Water Crossing Install |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-011 and labourers installed temp crossing 7541 | 5 | C076-C116 | Cook Lake Rd | 0 | 44150 |  | 52 | 44152 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting660620201111-12Light Truck w/ Tandum Trailer- After Jan 101337.5 | Corbiere and Sons Contracting660620201111-12Light Truck w/ Tandum Trailer- After Jan 101337.5Inv#076 |  |  | WF5-WaterCrossing |  |  | 1 | 337.5 | WC403 | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6606 | 20201111-12 | 53560501 | Water Crossings | 0 | Foreman | 95 | 4 | HR |  |  | 95 | 0 | 380 | 49.4 | 429.4 | 2020-11-11 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Nathan Kyme | <6M Water Crossing Install |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-011 and labourers installed temp crossing 7541 | 5 | C076-C116 | Cook Lake Rd | 0 | 44150 |  | 52 | 44152 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting660620201111-12Foreman4380 | Corbiere and Sons Contracting660620201111-12Foreman4380Inv#076 |  |  | WF5-WaterCrossing |  |  | 1 | 380 | WC403 | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6606 | 20201111-12 | 53560501 | Water Crossings | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2020-11-11 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Nathan Kyme | <6M Water Crossing Install |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-011 and labourers installed temp crossing 7541 | 5 | C076-C116 | Cook Lake Rd | 0 | 44150 |  | 52 | 44152 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting660620201111-12L.O.A.4840 | Corbiere and Sons Contracting660620201111-12L.O.A.4840Inv#076 |  |  | WF5-WaterCrossing |  |  | 1 | 840 | WC403 | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6606 | 20201111-12 | 53560501 | Water Crossings | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 75 | 0 | 450 | 58.5 | 508.5 | 2020-11-11 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Nathan Kyme | <6M Water Crossing Install |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-011 and labourers installed temp crossing 7541 | 5 | C076-C116 | Cook Lake Rd | 0 | 44150 |  | 52 | 44152 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting660620201111-12Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting660620201111-12Operator - Principle - After Jan 106450Inv#076 |  |  | WF5-WaterCrossing |  |  | 1 | 450 | WC403 | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6606 | 20201111-12 | 53560501 | Water Crossings | 0 | Labourer - General - After Jan 10 | 60 | 8 | HR |  |  | 60 | 0 | 480 | 62.4 | 542.4 | 2020-11-11 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Nathan Kyme | <6M Water Crossing Install |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-011 and labourers installed temp crossing 7541 | 5 | C076-C116 | Cook Lake Rd | 0 | 44150 |  | 52 | 44152 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting660620201111-12Labourer - General - After Jan 108480 | Corbiere and Sons Contracting660620201111-12Labourer - General - After Jan 108480Inv#076 |  |  | WF5-WaterCrossing |  |  | 1 | 480 | WC403 | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6607 | 20201111-13 | 53510511 | Access | 0 | Skidder | 171 | 6 | HR | 128.25 | 0 |  |  | 1026 | 133.38 | 1159.38 | 2020-11-11 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer and skidder doing snow removal in the morning | 5 | C076-C116 | Cook Lake | 0 | 44150 |  | 52 | 44152 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting660720201111-13Skidder 61026 | Corbiere and Sons Contracting660720201111-13Skidder 61026Inv#076 | [5 empty] | 1 | 1026 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6607 | 20201111-13 | 53510511 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 4.5 | Dynamic | 98.61 | 0 |  |  | 591.66 | 76.9158 | 668.5758 | 2020-11-11 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer and skidder doing snow removal in the morning | 5 | C076-C116 | Cook Lake | 0 | 44150 |  | 52 | 44152 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting660720201111-13Dozer D6 or equal- After Jan 104.5591.66 | Corbiere and Sons Contracting660720201111-13Dozer D6 or equal- After Jan 104.5591.66Inv#076 | [5 empty] | 1 | 591.66 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6607 | 20201111-13 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-11-11 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer and skidder doing snow removal in the morning | 5 | C076-C116 | Cook Lake | 0 | 44150 |  | 52 | 44152 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting660720201111-13Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting660720201111-13Light Truck - Pick up- After Jan 102487.5Inv#076 | [5 empty] | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6607 | 20201111-13 | 53510511 | Access | 0 | Foreman | 95 | 4 | HR |  |  | 95 | 0 | 380 | 49.4 | 429.4 | 2020-11-11 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer and skidder doing snow removal in the morning | 5 | C076-C116 | Cook Lake | 0 | 44150 |  | 52 | 44152 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting660720201111-13Foreman4380 | Corbiere and Sons Contracting660720201111-13Foreman4380Inv#076 | [5 empty] | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6607 | 20201111-13 | 53510511 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-11-11 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer and skidder doing snow removal in the morning | 5 | C076-C116 | Cook Lake | 0 | 44150 |  | 52 | 44152 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting660720201111-13L.O.A.2420 | Corbiere and Sons Contracting660720201111-13L.O.A.2420Inv#076 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6607 | 20201111-13 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 10.5 | HR |  |  | 75 | 0 | 787.5 | 102.375 | 889.875 | 2020-11-11 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Nathan Kyme | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer and skidder doing snow removal in the morning | 5 | C076-C116 | Cook Lake | 0 | 44150 |  | 52 | 44152 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting660720201111-13Operator - Principle - After Jan 1010.5787.5 | Corbiere and Sons Contracting660720201111-13Operator - Principle - After Jan 1010.5787.5Inv#076 | [5 empty] | 1 | 787.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6608 | 20201111-14 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 15 | Dynamic | 103.54 | 0 |  |  | 2070.75 | 269.1975 | 2339.9475 | 2020-11-11 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road too soft for rock trucks to permit | 5 | C076-C116 | Cook Lake | 0 | 44150 |  | 52 | 44152 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting660820201111-14Rock Truck - 30 Ton- After Jan 10152070.75 | Corbiere and Sons Contracting660820201111-14Rock Truck - 30 Ton- After Jan 10152070.75Inv#076 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 2070.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6608 | 20201111-14 | 53510504 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2020-11-11 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road too soft for rock trucks to permit | 5 | C076-C116 | Cook Lake | 0 | 44150 |  | 52 | 44152 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting660820201111-14L.O.A.3630 | Corbiere and Sons Contracting660820201111-14L.O.A.3630Inv#076 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6608 | 20201111-14 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 15 | HR |  |  | 70 | 0 | 1050 | 136.5 | 1186.5 | 2020-11-11 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road too soft for rock trucks to permit | 5 | C076-C116 | Cook Lake | 0 | 44150 |  | 52 | 44152 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting660820201111-14Driver - AZ - After Jan 10151050 | Corbiere and Sons Contracting660820201111-14Driver - AZ - After Jan 10151050Inv#076 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6612 | 20201111-15 | 53550503 | Earthworks | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 21 | Dynamic | 110.22 | 0 |  |  | 3086.16 | 401.2008 | 3487.3608 | 2020-11-11 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Nathan Kyme | Access Rock Blasting |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gary on hammer from C-061 and also the shoefly for C-065-C-069Ron on secondary hammer from C-065 shoefly | 5 | C070 - C075 | Antler Lake | 0 | 44150 |  | 52 | 44152 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting661220201111-15Excavator - 36 ton- After Jan 10213086.16 | Corbiere and Sons Contracting661220201111-15Excavator - 36 ton- After Jan 10213086.16Inv#076 |  | WF5-Earthwork | WF5-Earthwork |  | 1 | 1 | 3086.16 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6612 | 20201111-15 | 53550503 | Earthworks | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 21 | HR | 47.54 | 0 |  |  | 1330.98 | 173.0274 | 1504.0074 | 2020-11-11 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Nathan Kyme | Access Rock Blasting |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gary on hammer from C-061 and also the shoefly for C-065-C-069Ron on secondary hammer from C-065 shoefly | 5 | C070 - C075 | Antler Lake | 0 | 44150 |  | 52 | 44152 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting661220201111-15Excavator Hammer - 30 - 50 ton- After Jan 10211330.98 | Corbiere and Sons Contracting661220201111-15Excavator Hammer - 30 - 50 ton- After Jan 10211330.98Inv#076 |  | WF5-Earthwork | WF5-Earthwork |  | 1 | 1 | 1330.98 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6612 | 20201111-15 | 53550503 | Earthworks | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-11-11 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Nathan Kyme | Access Rock Blasting |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gary on hammer from C-061 and also the shoefly for C-065-C-069Ron on secondary hammer from C-065 shoefly | 5 | C070 - C075 | Antler Lake | 0 | 44150 |  | 52 | 44152 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting661220201111-15Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting661220201111-15Light Truck - Pick up- After Jan 101243.75Inv#076 |  | WF5-Earthwork | WF5-Earthwork |  | 1 | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6613 | 20201111-16 | 53510502 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 8.5 | Dynamic | 103.84 | 0 |  |  | 1176.825 | 152.9872 | 1329.8122 | 2020-11-11 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building road to C-061 | 5 | C050-C069 | Antler Lake | 0 | 44150 |  | 52 | 44152 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting661320201111-16Excavator - 30 ton- After Jan 108.51176.825 | Corbiere and Sons Contracting661320201111-16Excavator - 30 ton- After Jan 108.51176.825Inv#076 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 1176.825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6613 | 20201111-16 | 53510502 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 8.5 | HR | 9.16 | 0 |  |  | 103.785 | 13.4921 | 117.2771 | 2020-11-11 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building road to C-061 | 5 | C050-C069 | Antler Lake | 0 | 44150 |  | 52 | 44152 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting661320201111-16Excavator Thumb - 30 - 50 ton- After Jan 108.5103.785 | Corbiere and Sons Contracting661320201111-16Excavator Thumb - 30 - 50 ton- After Jan 108.5103.785Inv#076 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 103.785 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6613 | 20201111-16 | 53510502 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-11-11 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building road to C-061 | 5 | C050-C069 | Antler Lake | 0 | 44150 |  | 52 | 44152 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting661320201111-16Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting661320201111-16Light Truck - Pick up- After Jan 101243.75Inv#076 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6613 | 20201111-16 | 53510502 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-11-11 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building road to C-061 | 5 | C050-C069 | Antler Lake | 0 | 44150 |  | 52 | 44152 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting661320201111-16L.O.A.1210 | Corbiere and Sons Contracting661320201111-16L.O.A.1210Inv#076 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6613 | 20201111-16 | 53510502 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 9 | HR |  |  | 75 | 0 | 675 | 87.75 | 762.75 | 2020-11-11 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building road to C-061 | 5 | C050-C069 | Antler Lake | 0 | 44150 |  | 52 | 44152 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting661320201111-16Operator - Principle - After Jan 109675 | Corbiere and Sons Contracting661320201111-16Operator - Principle - After Jan 109675Inv#076 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 675 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6616 | 20201111-19 | 53510512 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 6 | Dynamic | 98.61 | 0 |  |  | 788.88 | 102.5544 | 891.4344 | 2020-11-11 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance for half the day Greg Grom doing road maintenance for half day - drag rig mats from C065 to second laydown for 2.5 hours | 5 | C050-C069 | Antler Lake | 0 | 44150 |  | 52 | 44152 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting661620201111-19Dozer D6 or equal- After Jan 106788.88 | Corbiere and Sons Contracting661620201111-19Dozer D6 or equal- After Jan 106788.88Inv#076 | [5 empty] | 1 | 788.88 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6616 | 20201111-19 | 53510512 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-11-11 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance for half the day Greg Grom doing road maintenance for half day - drag rig mats from C065 to second laydown for 2.5 hours | 5 | C050-C069 | Antler Lake | 0 | 44150 |  | 52 | 44152 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting661620201111-19L.O.A.1210 | Corbiere and Sons Contracting661620201111-19L.O.A.1210Inv#076 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6616 | 20201111-19 | 53510512 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 75 | 0 | 450 | 58.5 | 508.5 | 2020-11-11 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance for half the day Greg Grom doing road maintenance for half day - drag rig mats from C065 to second laydown for 2.5 hours | 5 | C050-C069 | Antler Lake | 0 | 44150 |  | 52 | 44152 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting661620201111-19Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting661620201111-19Operator - Principle - After Jan 106450Inv#076 | [5 empty] | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6804 | 20201111-23 | 53510312 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10 | Dynamic | 98.61 | 0 |  |  | 1314.8 | 170.924 | 1485.724 | 2020-11-11 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Doing road maintenance across Landfill access | 3 | B077-B084 | Landfill Road | 0 | 44159 |  | 37 | 44160 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting680420201111-23Dozer D6 or equal- After Jan 10101314.8 | Corbiere and Sons Contracting680420201111-23Dozer D6 or equal- After Jan 10101314.8Inv#076 | [5 empty] | 1 | 1314.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6804 | 20201111-23 | 53510312 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 6 | Dynamic | 110.22 | 0 |  |  | 881.76 | 114.6288 | 996.3888 | 2020-11-11 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Doing road maintenance across Landfill access | 3 | B077-B084 | Landfill Road | 0 | 44159 |  | 37 | 44160 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting680420201111-23Excavator - 36 ton- After Jan 106881.76 | Corbiere and Sons Contracting680420201111-23Excavator - 36 ton- After Jan 106881.76Inv#076 | [5 empty] | 1 | 881.76 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6804 | 20201111-23 | 53510312 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 6 | HR | 9.16 | 0 |  |  | 73.26 | 9.5238 | 82.7838 | 2020-11-11 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Doing road maintenance across Landfill access | 3 | B077-B084 | Landfill Road | 0 | 44159 |  | 37 | 44160 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting680420201111-23Excavator Thumb - 30 - 50 ton- After Jan 10673.26 | Corbiere and Sons Contracting680420201111-23Excavator Thumb - 30 - 50 ton- After Jan 10673.26Inv#076 | [5 empty] | 1 | 73.26 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6804 | 20201111-23 | 53510312 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-11-11 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Doing road maintenance across Landfill access | 3 | B077-B084 | Landfill Road | 0 | 44159 |  | 37 | 44160 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting680420201111-23Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting680420201111-23Light Truck - Pick up- After Jan 102487.5Inv#076 | [5 empty] | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6804 | 20201111-23 | 53510312 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 18 | HR |  |  | 75 | 0 | 1350 | 175.5 | 1525.5 | 2020-11-11 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Doing road maintenance across Landfill access | 3 | B077-B084 | Landfill Road | 0 | 44159 |  | 37 | 44160 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting680420201111-23Operator - Principle - After Jan 10181350 | Corbiere and Sons Contracting680420201111-23Operator - Principle - After Jan 10181350Inv#076 | [5 empty] | 1 | 1350 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6805 | 20201111-24 | 53510312 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 5 | Dynamic | 95.24 | 0 |  |  | 634.9 | 82.537 | 717.437 | 2020-11-11 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across area from B119 - escorted from North Shore yard by Labourer | 3 | B119 | Fire Hill Creek West | 0 | 44159 |  | 37 | 44160 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting680520201111-24Grader - Cat 12 to 14 or equal- After Jan 105634.9 | Corbiere and Sons Contracting680520201111-24Grader - Cat 12 to 14 or equal- After Jan 105634.9Inv#076 | [5 empty] | 1 | 634.9 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6805 | 20201111-24 | 53510312 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-11-11 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across area from B119 - escorted from North Shore yard by Labourer | 3 | B119 | Fire Hill Creek West | 0 | 44159 |  | 37 | 44160 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting680520201111-24Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting680520201111-24Light Truck - Pick up- After Jan 101243.75Inv#076 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6805 | 20201111-24 | 53510312 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5 | HR |  |  | 75 | 0 | 375 | 48.75 | 423.75 | 2020-11-11 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across area from B119 - escorted from North Shore yard by Labourer | 3 | B119 | Fire Hill Creek West | 0 | 44159 |  | 37 | 44160 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting680520201111-24Operator - Principle - After Jan 105375 | Corbiere and Sons Contracting680520201111-24Operator - Principle - After Jan 105375Inv#076 | [5 empty] | 1 | 375 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6805 | 20201111-24 | 53510312 | Access | 0 | Labourer - General - After Jan 10 | 60 | 5 | HR |  |  | 60 | 0 | 300 | 39 | 339 | 2020-11-11 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across area from B119 - escorted from North Shore yard by Labourer | 3 | B119 | Fire Hill Creek West | 0 | 44159 |  | 37 | 44160 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting680520201111-24Labourer - General - After Jan 105300 | Corbiere and Sons Contracting680520201111-24Labourer - General - After Jan 105300Inv#076 | [5 empty] | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6806 | 20201111-25 | 53510311 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 5 | Dynamic | 110.22 | 0 |  |  | 734.8 | 95.524 | 830.324 | 2020-11-11 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Clearing off snow and track packed road | 3 | B136-B144 | Fire Hill Creek East | 0 | 44159 |  | 37 | 44160 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting680620201111-25Excavator - 36 ton- After Jan 105734.8 | Corbiere and Sons Contracting680620201111-25Excavator - 36 ton- After Jan 105734.8Inv#076 | [5 empty] | 1 | 734.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6806 | 20201111-25 | 53510311 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 5 | HR | 9.16 | 0 |  |  | 61.05 | 7.9365 | 68.9865 | 2020-11-11 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Clearing off snow and track packed road | 3 | B136-B144 | Fire Hill Creek East | 0 | 44159 |  | 37 | 44160 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting680620201111-25Excavator Thumb - 30 - 50 ton- After Jan 10561.05 | Corbiere and Sons Contracting680620201111-25Excavator Thumb - 30 - 50 ton- After Jan 10561.05Inv#076 | [5 empty] | 1 | 61.05 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6806 | 20201111-25 | 53510311 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-11-11 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Clearing off snow and track packed road | 3 | B136-B144 | Fire Hill Creek East | 0 | 44159 |  | 37 | 44160 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting680620201111-25Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting680620201111-25Light Truck - Pick up- After Jan 101243.75Inv#076 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6806 | 20201111-25 | 53510311 | Access | 0 | Foreman | 95 | 4 | HR |  |  | 95 | 0 | 380 | 49.4 | 429.4 | 2020-11-11 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Clearing off snow and track packed road | 3 | B136-B144 | Fire Hill Creek East | 0 | 44159 |  | 37 | 44160 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting680620201111-25Foreman4380 | Corbiere and Sons Contracting680620201111-25Foreman4380Inv#076 | [5 empty] | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6806 | 20201111-25 | 53510311 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5 | HR |  |  | 75 | 0 | 375 | 48.75 | 423.75 | 2020-11-11 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Clearing off snow and track packed road | 3 | B136-B144 | Fire Hill Creek East | 0 | 44159 |  | 37 | 44160 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting680620201111-25Operator - Principle - After Jan 105375 | Corbiere and Sons Contracting680620201111-25Operator - Principle - After Jan 105375Inv#076 | [5 empty] | 1 | 375 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6809 | 20201111-28 | 53510411 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10 | Dynamic | 98.61 | 0 |  |  | 1314.8 | 170.924 | 1485.724 | 2020-11-11 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dz clearing snow for access between structures B200 and B207 | 4 | B200-B207 | Little Gravel River Road | 0 | 44159 |  | 37 | 44160 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting680920201111-28Dozer D6 or equal- After Jan 10101314.8 | Corbiere and Sons Contracting680920201111-28Dozer D6 or equal- After Jan 10101314.8Inv#076 | [5 empty] | 1 | 1314.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6809 | 20201111-28 | 53510411 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2020-11-11 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dz clearing snow for access between structures B200 and B207 | 4 | B200-B207 | Little Gravel River Road | 0 | 44159 |  | 37 | 44160 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting680920201111-28Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting680920201111-28Operator - Principle - After Jan 1011825Inv#076 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6813 | 20201111-32 | 53510512 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 4 | Dynamic | 103.84 | 0 |  |  | 553.8 | 71.994 | 625.794 | 2020-11-11 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ex-08 did 4 hours of road maintenance after gravel haul complete | 5 | C031-C035 | Pays Plat River | 0 | 44159 |  | 37 | 44160 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting681320201111-32Excavator - 30 ton- After Jan 104553.8 | Corbiere and Sons Contracting681320201111-32Excavator - 30 ton- After Jan 104553.8Inv#076 | [5 empty] | 1 | 553.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6813 | 20201111-32 | 53510512 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 4 | HR | 9.16 | 0 |  |  | 48.84 | 6.3492 | 55.1892 | 2020-11-11 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ex-08 did 4 hours of road maintenance after gravel haul complete | 5 | C031-C035 | Pays Plat River | 0 | 44159 |  | 37 | 44160 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting681320201111-32Excavator Thumb - 30 - 50 ton- After Jan 10448.84 | Corbiere and Sons Contracting681320201111-32Excavator Thumb - 30 - 50 ton- After Jan 10448.84Inv#076 | [5 empty] | 1 | 48.84 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6813 | 20201111-32 | 53510512 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 4 | HR |  |  | 75 | 0 | 300 | 39 | 339 | 2020-11-11 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ex-08 did 4 hours of road maintenance after gravel haul complete | 5 | C031-C035 | Pays Plat River | 0 | 44159 |  | 37 | 44160 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting681320201111-32Operator - Principle - After Jan 104300 | Corbiere and Sons Contracting681320201111-32Operator - Principle - After Jan 104300Inv#076 | [5 empty] | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6623 | 20201112-10 | 53510502 | Access | 0 | Skidder | 171 | 5 | HR | 128.25 | 0 |  |  | 855 | 111.15 | 966.15 | 2020-11-12 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Put down corduroy with skidder for 5 hours at C-102 - C-103 | 5 | C093-C116 | Cook Lake | 0 | 44150 |  | 52 | 44152 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting662320201112-10Skidder 5855 | Corbiere and Sons Contracting662320201112-10Skidder 5855Inv#076 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 855 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6623 | 20201112-10 | 53510502 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 5 | Dynamic | 110.22 | 0 |  |  | 734.8 | 95.524 | 830.324 | 2020-11-12 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Put down corduroy with skidder for 5 hours at C-102 - C-103 | 5 | C093-C116 | Cook Lake | 0 | 44150 |  | 52 | 44152 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting662320201112-10Excavator - 36 ton- After Jan 105734.8 | Corbiere and Sons Contracting662320201112-10Excavator - 36 ton- After Jan 105734.8Inv#076 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 734.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6623 | 20201112-10 | 53510502 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-11-12 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Put down corduroy with skidder for 5 hours at C-102 - C-103 | 5 | C093-C116 | Cook Lake | 0 | 44150 |  | 52 | 44152 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting662320201112-10Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting662320201112-10Light Truck - Pick up- After Jan 102487.5Inv#076 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6623 | 20201112-10 | 53510502 | Access | 0 | Foreman | 95 | 4 | HR |  |  | 95 |  | 380 | 49.4 | 429.4 | 2020-11-12 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Put down corduroy with skidder for 5 hours at C-102 - C-103 | 5 | C093-C116 | Cook Lake | 0 | 44150 |  | 52 | 44152 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting662320201112-10Foreman4380 | Corbiere and Sons Contracting662320201112-10Foreman4380Inv#076 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6623 | 20201112-10 | 53510502 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2020-11-12 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Put down corduroy with skidder for 5 hours at C-102 - C-103 | 5 | C093-C116 | Cook Lake | 0 | 44150 |  | 52 | 44152 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting662320201112-10L.O.A.3630 | Corbiere and Sons Contracting662320201112-10L.O.A.3630Inv#076 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6623 | 20201112-10 | 53510502 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 10 | HR |  |  | 75 | 0 | 750 | 97.5 | 847.5 | 2020-11-12 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Put down corduroy with skidder for 5 hours at C-102 - C-103 | 5 | C093-C116 | Cook Lake | 0 | 44150 |  | 52 | 44152 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting662320201112-10Operator - Principle - After Jan 1010750 | Corbiere and Sons Contracting662320201112-10Operator - Principle - After Jan 1010750Inv#076 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 750 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6624 | 20201112-11 | 53510512 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 3 | Dynamic | 110.22 | 0 |  |  | 440.88 | 57.3144 | 498.1944 | 2020-11-12 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Installed temp crossing at non permitted and unmarked crossing at C-104. | 5 | C-093 - C-116 | Cook Lake Rd E | 0 | 44150 |  | 52 | 44152 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting662420201112-11Excavator - 36 ton- After Jan 103440.88 | Corbiere and Sons Contracting662420201112-11Excavator - 36 ton- After Jan 103440.88Inv#076 | [5 empty] | 1 | 440.88 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6624 | 20201112-11 | 53510512 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 3 | HR |  |  | 75 | 0 | 225 | 29.25 | 254.25 | 2020-11-12 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Installed temp crossing at non permitted and unmarked crossing at C-104. | 5 | C-093 - C-116 | Cook Lake Rd E | 0 | 44150 |  | 52 | 44152 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting662420201112-11Operator - Principle - After Jan 103225 | Corbiere and Sons Contracting662420201112-11Operator - Principle - After Jan 103225Inv#076 | [5 empty] | 1 | 225 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6625 | 20201112-12 | 53510512 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10.5 | Dynamic | 110.22 | 0 |  |  | 1543.08 | 200.6004 | 1743.6804 | 2020-11-12 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-011 doing road maintenance from WC7541 to C-0104 all dayDarrel took triaxle to Dorion uard and loaded with blast mats to bring to Cook Lake to drag on access roads for maintenance | 5 | C-076 - C-116 | Cook Lake Rd | 0 | 44150 |  | 52 | 44152 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting662520201112-12Excavator - 36 ton- After Jan 1010.51543.08 | Corbiere and Sons Contracting662520201112-12Excavator - 36 ton- After Jan 1010.51543.08Inv#076 | [5 empty] | 1 | 1543.08 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6625 | 20201112-12 | 53510512 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 8 | Dynamic | 41.4 | 0 |  |  | 441.6 | 57.408 | 499.008 | 2020-11-12 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-011 doing road maintenance from WC7541 to C-0104 all dayDarrel took triaxle to Dorion uard and loaded with blast mats to bring to Cook Lake to drag on access roads for maintenance | 5 | C-076 - C-116 | Cook Lake Rd | 0 | 44150 |  | 52 | 44152 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting662520201112-12Dump - Triaxle- After Jan 108441.6 | Corbiere and Sons Contracting662520201112-12Dump - Triaxle- After Jan 108441.6Inv#076 | [5 empty] | 1 | 441.6 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6625 | 20201112-12 | 53510512 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-11-12 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-011 doing road maintenance from WC7541 to C-0104 all dayDarrel took triaxle to Dorion uard and loaded with blast mats to bring to Cook Lake to drag on access roads for maintenance | 5 | C-076 - C-116 | Cook Lake Rd | 0 | 44150 |  | 52 | 44152 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting662520201112-12Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting662520201112-12Light Truck - Pick up- After Jan 101243.75Inv#076 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6625 | 20201112-12 | 53510512 | Access | 0 | Foreman | 95 | 3 | HR |  |  | 95 | 0 | 285 | 37.05 | 322.05 | 2020-11-12 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-011 doing road maintenance from WC7541 to C-0104 all dayDarrel took triaxle to Dorion uard and loaded with blast mats to bring to Cook Lake to drag on access roads for maintenance | 5 | C-076 - C-116 | Cook Lake Rd | 0 | 44150 |  | 52 | 44152 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting662520201112-12Foreman3285 | Corbiere and Sons Contracting662520201112-12Foreman3285Inv#076 | [5 empty] | 1 | 285 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6625 | 20201112-12 | 53510512 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-11-12 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-011 doing road maintenance from WC7541 to C-0104 all dayDarrel took triaxle to Dorion uard and loaded with blast mats to bring to Cook Lake to drag on access roads for maintenance | 5 | C-076 - C-116 | Cook Lake Rd | 0 | 44150 |  | 52 | 44152 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting662520201112-12L.O.A.2420 | Corbiere and Sons Contracting662520201112-12L.O.A.2420Inv#076 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6625 | 20201112-12 | 53510512 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-11-12 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-011 doing road maintenance from WC7541 to C-0104 all dayDarrel took triaxle to Dorion uard and loaded with blast mats to bring to Cook Lake to drag on access roads for maintenance | 5 | C-076 - C-116 | Cook Lake Rd | 0 | 44150 |  | 52 | 44152 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting662520201112-12Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting662520201112-12Operator - Principle - After Jan 1011.5862.5Inv#076 | [5 empty] | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6625 | 20201112-12 | 53510512 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 8 | HR |  |  | 70 | 0 | 560 | 72.8 | 632.8 | 2020-11-12 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-011 doing road maintenance from WC7541 to C-0104 all dayDarrel took triaxle to Dorion uard and loaded with blast mats to bring to Cook Lake to drag on access roads for maintenance | 5 | C-076 - C-116 | Cook Lake Rd | 0 | 44150 |  | 52 | 44152 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting662520201112-12Driver - AZ - After Jan 108560 | Corbiere and Sons Contracting662520201112-12Driver - AZ - After Jan 108560Inv#076 | [5 empty] | 1 | 560 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6629 | 20201112-16 | 53510512 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 5 | Dynamic | 103.84 | 0 |  |  | 692.25 | 89.9925 | 782.2425 | 2020-11-12 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Diverting road from C-062 | 5 | C050-C069 | Antler Lake | 0 | 44150 |  | 52 | 44152 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting662920201112-16Excavator - 30 ton- After Jan 105692.25 | Corbiere and Sons Contracting662920201112-16Excavator - 30 ton- After Jan 105692.25Inv#076 | [5 empty] | 1 | 692.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6629 | 20201112-16 | 53510512 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 5 | HR | 9.16 | 0 |  |  | 61.05 | 7.9365 | 68.9865 | 2020-11-12 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Diverting road from C-062 | 5 | C050-C069 | Antler Lake | 0 | 44150 |  | 52 | 44152 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting662920201112-16Excavator Thumb - 30 - 50 ton- After Jan 10561.05 | Corbiere and Sons Contracting662920201112-16Excavator Thumb - 30 - 50 ton- After Jan 10561.05Inv#076 | [5 empty] | 1 | 61.05 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6629 | 20201112-16 | 53510512 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-11-12 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Diverting road from C-062 | 5 | C050-C069 | Antler Lake | 0 | 44150 |  | 52 | 44152 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting662920201112-16L.O.A.1210 | Corbiere and Sons Contracting662920201112-16L.O.A.1210Inv#076 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6629 | 20201112-16 | 53510512 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5.5 | HR |  |  | 75 | 0 | 412.5 | 53.625 | 466.125 | 2020-11-12 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Diverting road from C-062 | 5 | C050-C069 | Antler Lake | 0 | 44150 |  | 52 | 44152 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting662920201112-16Operator - Principle - After Jan 105.5412.5 | Corbiere and Sons Contracting662920201112-16Operator - Principle - After Jan 105.5412.5Inv#076 | [5 empty] | 1 | 412.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6630 | 20201112-17 | 53510503 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 2 | Dynamic | 103.84 | 0 |  |  | 276.9 | 35.997 | 312.897 | 2020-11-12 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixing disturbed wetland south of C-061. | 5 | C050-C069 | Antler Lake | 0 | 44150 |  | 52 | 44152 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting663020201112-17Excavator - 30 ton- After Jan 102276.9 | Corbiere and Sons Contracting663020201112-17Excavator - 30 ton- After Jan 102276.9Inv#076 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 276.9 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6630 | 20201112-17 | 53510503 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 2 | HR | 9.16 | 0 |  |  | 24.42 | 3.1746 | 27.5946 | 2020-11-12 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixing disturbed wetland south of C-061. | 5 | C050-C069 | Antler Lake | 0 | 44150 |  | 52 | 44152 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting663020201112-17Excavator Thumb - 30 - 50 ton- After Jan 10224.42 | Corbiere and Sons Contracting663020201112-17Excavator Thumb - 30 - 50 ton- After Jan 10224.42Inv#076 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 24.42 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6630 | 20201112-17 | 53510503 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 2 | HR |  |  | 75 | 0 | 150 | 19.5 | 169.5 | 2020-11-12 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Nathan Kyme | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixing disturbed wetland south of C-061. | 5 | C050-C069 | Antler Lake | 0 | 44150 |  | 52 | 44152 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting663020201112-17Operator - Principle - After Jan 102150 | Corbiere and Sons Contracting663020201112-17Operator - Principle - After Jan 102150Inv#076 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 150 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6631 | 20201112-18 | 53550503 | Earthworks | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10.5 | Dynamic | 110.22 | 0 |  |  | 1543.08 | 200.6004 | 1743.6804 | 2020-11-12 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Nathan Kyme | Access Rock Blasting |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock hammer at C-061 and then the shoefly from C-065 - C-069 on the big knobs. | 5 | C050-C069 | Antler Lake | 0 | 44150 |  | 52 | 44152 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting663120201112-18Excavator - 36 ton- After Jan 1010.51543.08 | Corbiere and Sons Contracting663120201112-18Excavator - 36 ton- After Jan 1010.51543.08Inv#076 |  | WF5-Earthwork | WF5-Earthwork |  | 1 | 1 | 1543.08 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6631 | 20201112-18 | 53550503 | Earthworks | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 10.5 | HR | 47.54 | 0 |  |  | 665.49 | 86.5137 | 752.0037 | 2020-11-12 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Nathan Kyme | Access Rock Blasting |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock hammer at C-061 and then the shoefly from C-065 - C-069 on the big knobs. | 5 | C050-C069 | Antler Lake | 0 | 44150 |  | 52 | 44152 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting663120201112-18Excavator Hammer - 30 - 50 ton- After Jan 1010.5665.49 | Corbiere and Sons Contracting663120201112-18Excavator Hammer - 30 - 50 ton- After Jan 1010.5665.49Inv#076 |  | WF5-Earthwork | WF5-Earthwork |  | 1 | 1 | 665.49 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6631 | 20201112-18 | 53550503 | Earthworks | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-11-12 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Nathan Kyme | Access Rock Blasting |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock hammer at C-061 and then the shoefly from C-065 - C-069 on the big knobs. | 5 | C050-C069 | Antler Lake | 0 | 44150 |  | 52 | 44152 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting663120201112-18Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting663120201112-18Light Truck - Pick up- After Jan 101243.75Inv#076 |  | WF5-Earthwork | WF5-Earthwork |  | 1 | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6631 | 20201112-18 | 53550503 | Earthworks | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-11-12 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Nathan Kyme | Access Rock Blasting |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock hammer at C-061 and then the shoefly from C-065 - C-069 on the big knobs. | 5 | C050-C069 | Antler Lake | 0 | 44150 |  | 52 | 44152 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting663120201112-18L.O.A.1210 | Corbiere and Sons Contracting663120201112-18L.O.A.1210Inv#076 |  | WF5-Earthwork | WF5-Earthwork |  | 1 | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6631 | 20201112-18 | 53550503 | Earthworks | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-11-12 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Nathan Kyme | Access Rock Blasting |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock hammer at C-061 and then the shoefly from C-065 - C-069 on the big knobs. | 5 | C050-C069 | Antler Lake | 0 | 44150 |  | 52 | 44152 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting663120201112-18Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting663120201112-18Operator - Principle - After Jan 1011.5862.5Inv#076 |  | WF5-Earthwork | WF5-Earthwork |  | 1 | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6815 | 20201112-20 | 53510311 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10 | Dynamic | 95.24 | 0 |  |  | 1269.8 | 165.074 | 1434.874 | 2020-11-12 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Maata's road - Rob on triaxle brought 3 loads of material to Maata's - Float moved Grader to Maata's | 3 | B088-B099 | Maata's Road | 0 | 44159 |  | 37 | 44160 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting681520201112-20Grader - Cat 12 to 14 or equal- After Jan 10101269.8 | Corbiere and Sons Contracting681520201112-20Grader - Cat 12 to 14 or equal- After Jan 10101269.8Inv#076 | [5 empty] | 1 | 1269.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6815 | 20201112-20 | 53510311 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 6 | Dynamic | 41.4 | 0 |  |  | 331.2 | 43.056 | 374.256 | 2020-11-12 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Maata's road - Rob on triaxle brought 3 loads of material to Maata's - Float moved Grader to Maata's | 3 | B088-B099 | Maata's Road | 0 | 44159 |  | 37 | 44160 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting681520201112-20Dump - Triaxle- After Jan 106331.2 | Corbiere and Sons Contracting681520201112-20Dump - Triaxle- After Jan 106331.2Inv#076 | [5 empty] | 1 | 331.2 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6815 | 20201112-20 | 53510311 | Access | 0 | Light Truck - 1 to 3 Ton- After Jan 10 | 243.75 | 1 | DAY | 182.81 |  |  |  | 243.75 | 31.6875 | 275.4375 | 2020-11-12 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Maata's road - Rob on triaxle brought 3 loads of material to Maata's - Float moved Grader to Maata's | 3 | B088-B099 | Maata's Road | 0 | 44159 |  | 37 | 44160 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting681520201112-20Light Truck - 1 to 3 Ton- After Jan 101243.75 | Corbiere and Sons Contracting681520201112-20Light Truck - 1 to 3 Ton- After Jan 101243.75Inv#076 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6815 | 20201112-20 | 53510311 | Access | 0 | Tractor Trailer - 50 Ton- After Jan 10 | 111.75 | 4 | Dynamic | 83.81 | 0 |  |  | 447 | 58.11 | 505.11 | 2020-11-12 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Maata's road - Rob on triaxle brought 3 loads of material to Maata's - Float moved Grader to Maata's | 3 | B088-B099 | Maata's Road | 0 | 44159 |  | 37 | 44160 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting681520201112-20Tractor Trailer - 50 Ton- After Jan 104447 | Corbiere and Sons Contracting681520201112-20Tractor Trailer - 50 Ton- After Jan 104447Inv#076 | [5 empty] | 1 | 447 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6815 | 20201112-20 | 53510311 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2020-11-12 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Maata's road - Rob on triaxle brought 3 loads of material to Maata's - Float moved Grader to Maata's | 3 | B088-B099 | Maata's Road | 0 | 44159 |  | 37 | 44160 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting681520201112-20Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting681520201112-20Operator - Principle - After Jan 1011825Inv#076 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6815 | 20201112-20 | 53510311 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 10 | HR |  |  | 70 | 0 | 700 | 91 | 791 | 2020-11-12 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Maata's road - Rob on triaxle brought 3 loads of material to Maata's - Float moved Grader to Maata's | 3 | B088-B099 | Maata's Road | 0 | 44159 |  | 37 | 44160 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting681520201112-20Driver - AZ - After Jan 1010700 | Corbiere and Sons Contracting681520201112-20Driver - AZ - After Jan 1010700Inv#076 | [5 empty] | 1 | 700 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6816 | 20201112-21 | 53510311 | Access | 0 | Sander Truck - Forestry- After Jan 10 | 86.38 | 4 | Dynamic | 64.79 | 0 |  |  | 345.52 | 44.9176 | 390.4376 | 2020-11-12 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Sander truck working across Doghead River Road | 3 | B100-B110 | Dog Head Road | 0 | 44159 |  | 37 | 44160 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting681620201112-21Sander Truck - Forestry- After Jan 104345.52 | Corbiere and Sons Contracting681620201112-21Sander Truck - Forestry- After Jan 104345.52Inv#076 | [5 empty] | 1 | 345.52 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6816 | 20201112-21 | 53510311 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 4 | HR |  |  | 70 | 0 | 280 | 36.4 | 316.4 | 2020-11-12 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Sander truck working across Doghead River Road | 3 | B100-B110 | Dog Head Road | 0 | 44159 |  | 37 | 44160 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting681620201112-21Driver - AZ - After Jan 104280 | Corbiere and Sons Contracting681620201112-21Driver - AZ - After Jan 104280Inv#076 | [5 empty] | 1 | 280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6622 | 20201112-9 | 53510504 | Access | 0 | Light Truck w/ Tandum Trailer- After Jan 10 | 337.5 | 1 | DAY | 253.13 | 0 |  |  | 337.5 | 43.875 | 381.375 | 2020-11-12 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float picked up rolls of geo at Armtec in Thunder BayDrivers and rock trucks came in but roads too soft to continue, damage was being doneLabourers unloaded rolls of geo with Shawn and brought to site | 5 | C076-C077 | Cook Lake Rd | 0 | 44150 |  | 52 | 44152 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting662220201112-9Light Truck w/ Tandum Trailer- After Jan 101337.5 | Corbiere and Sons Contracting662220201112-9Light Truck w/ Tandum Trailer- After Jan 101337.5Inv#076 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 337.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6622 | 20201112-9 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 15 | Dynamic | 103.54 | 0 |  |  | 2070.75 | 269.1975 | 2339.9475 | 2020-11-12 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float picked up rolls of geo at Armtec in Thunder BayDrivers and rock trucks came in but roads too soft to continue, damage was being doneLabourers unloaded rolls of geo with Shawn and brought to site | 5 | C076-C077 | Cook Lake Rd | 0 | 44150 |  | 52 | 44152 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting662220201112-9Rock Truck - 30 Ton- After Jan 10152070.75 | Corbiere and Sons Contracting662220201112-9Rock Truck - 30 Ton- After Jan 10152070.75Inv#076 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 2070.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6622 | 20201112-9 | 53510504 | Access | 0 | Tractor Trailer - 60 Ton- After Jan 10 | 122.39 | 9 | Dynamic | 91.79 | 0 |  |  | 1101.51 | 143.1963 | 1244.7063 | 2020-11-12 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float picked up rolls of geo at Armtec in Thunder BayDrivers and rock trucks came in but roads too soft to continue, damage was being doneLabourers unloaded rolls of geo with Shawn and brought to site | 5 | C076-C077 | Cook Lake Rd | 0 | 44150 |  | 52 | 44152 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting662220201112-9Tractor Trailer - 60 Ton- After Jan 1091101.51 | Corbiere and Sons Contracting662220201112-9Tractor Trailer - 60 Ton- After Jan 1091101.51Inv#076 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1101.51 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6622 | 20201112-9 | 53510504 | Access | 0 | Foreman | 95 | 3 | HR |  |  | 95 | 0 | 285 | 37.05 | 322.05 | 2020-11-12 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float picked up rolls of geo at Armtec in Thunder BayDrivers and rock trucks came in but roads too soft to continue, damage was being doneLabourers unloaded rolls of geo with Shawn and brought to site | 5 | C076-C077 | Cook Lake Rd | 0 | 44150 |  | 52 | 44152 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting662220201112-9Foreman3285 | Corbiere and Sons Contracting662220201112-9Foreman3285Inv#076 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 285 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6622 | 20201112-9 | 53510504 | Access | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2020-11-12 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float picked up rolls of geo at Armtec in Thunder BayDrivers and rock trucks came in but roads too soft to continue, damage was being doneLabourers unloaded rolls of geo with Shawn and brought to site | 5 | C076-C077 | Cook Lake Rd | 0 | 44150 |  | 52 | 44152 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting662220201112-9L.O.A.61260 | Corbiere and Sons Contracting662220201112-9L.O.A.61260Inv#076 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6622 | 20201112-9 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 24 | HR |  |  | 70 | 0 | 1680 | 218.4 | 1898.4 | 2020-11-12 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float picked up rolls of geo at Armtec in Thunder BayDrivers and rock trucks came in but roads too soft to continue, damage was being doneLabourers unloaded rolls of geo with Shawn and brought to site | 5 | C076-C077 | Cook Lake Rd | 0 | 44150 |  | 52 | 44152 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting662220201112-9Driver - AZ - After Jan 10241680 | Corbiere and Sons Contracting662220201112-9Driver - AZ - After Jan 10241680Inv#076 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1680 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6622 | 20201112-9 | 53510504 | Access | 0 | Labourer - General - After Jan 10 | 60 | 13 | HR |  |  | 60 | 0 | 780 | 101.4 | 881.4 | 2020-11-12 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float picked up rolls of geo at Armtec in Thunder BayDrivers and rock trucks came in but roads too soft to continue, damage was being doneLabourers unloaded rolls of geo with Shawn and brought to site | 5 | C076-C077 | Cook Lake Rd | 0 | 44150 |  | 52 | 44152 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting662220201112-9Labourer - General - After Jan 1013780 | Corbiere and Sons Contracting662220201112-9Labourer - General - After Jan 1013780Inv#076 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 780 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6643 | 20201113-11 | 53510504 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10.5 | Dynamic | 110.22 | 0 |  |  | 1543.08 | 200.6004 | 1743.6804 | 2020-11-13 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator working with rock truck along the road by the "Y", Rock truck spend day hauling for capping of existing road up to WC7580.01 | 5 | C076-C116 | Cook Lake | 0 | 44150 |  | 52 | 44152 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting664320201113-11Excavator - 36 ton- After Jan 1010.51543.08 | Corbiere and Sons Contracting664320201113-11Excavator - 36 ton- After Jan 1010.51543.08Inv#076 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1543.08 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6643 | 20201113-11 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-11-13 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator working with rock truck along the road by the "Y", Rock truck spend day hauling for capping of existing road up to WC7580.01 | 5 | C076-C116 | Cook Lake | 0 | 44150 |  | 52 | 44152 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting664320201113-11Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting664320201113-11Light Truck - Pick up- After Jan 101243.75Inv#076 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6643 | 20201113-11 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 10.5 | Dynamic | 103.54 | 0 |  |  | 1449.525 | 188.4383 | 1637.9633 | 2020-11-13 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator working with rock truck along the road by the "Y", Rock truck spend day hauling for capping of existing road up to WC7580.01 | 5 | C076-C116 | Cook Lake | 0 | 44150 |  | 52 | 44152 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting664320201113-11Rock Truck - 30 Ton- After Jan 1010.51449.525 | Corbiere and Sons Contracting664320201113-11Rock Truck - 30 Ton- After Jan 1010.51449.525Inv#076 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1449.525 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6643 | 20201113-11 | 53510504 | Access | 0 | Foreman | 95 | 4 | HR |  |  | 95 | 0 | 380 | 49.4 | 429.4 | 2020-11-13 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator working with rock truck along the road by the "Y", Rock truck spend day hauling for capping of existing road up to WC7580.01 | 5 | C076-C116 | Cook Lake | 0 | 44150 |  | 52 | 44152 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting664320201113-11Foreman4380 | Corbiere and Sons Contracting664320201113-11Foreman4380Inv#076 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6643 | 20201113-11 | 53510504 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-11-13 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator working with rock truck along the road by the "Y", Rock truck spend day hauling for capping of existing road up to WC7580.01 | 5 | C076-C116 | Cook Lake | 0 | 44150 |  | 52 | 44152 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting664320201113-11L.O.A.2420 | Corbiere and Sons Contracting664320201113-11L.O.A.2420Inv#076 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6643 | 20201113-11 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-11-13 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator working with rock truck along the road by the "Y", Rock truck spend day hauling for capping of existing road up to WC7580.01 | 5 | C076-C116 | Cook Lake | 0 | 44150 |  | 52 | 44152 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting664320201113-11Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting664320201113-11Operator - Principle - After Jan 1011.5862.5Inv#076 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6643 | 20201113-11 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 11.5 | HR |  |  | 70 | 0 | 805 | 104.65 | 909.65 | 2020-11-13 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Nathan Kyme | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator working with rock truck along the road by the "Y", Rock truck spend day hauling for capping of existing road up to WC7580.01 | 5 | C076-C116 | Cook Lake | 0 | 44150 |  | 52 | 44152 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting664320201113-11Driver - AZ - After Jan 1011.5805 | Corbiere and Sons Contracting664320201113-11Driver - AZ - After Jan 1011.5805Inv#076 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 805 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6646 | 20201113-14 | 53550503 | Earthworks | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10.5 | Dynamic | 110.22 | 0 |  |  | 1543.08 | 200.6004 | 1743.6804 | 2020-01-13 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Nathan Kyme | Access Rock Blasting |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock hammer working from shoefly at C-065 - C-069 | 5 | C050-C069 | Antler Lake | 0 | 44150 |  | 52 | 44152 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting664620201113-14Excavator - 36 ton- After Jan 1010.51543.08 | Corbiere and Sons Contracting664620201113-14Excavator - 36 ton- After Jan 1010.51543.08Inv#076 |  | WF5-Earthwork | WF5-Earthwork |  | 1 | 1 | 1543.08 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6646 | 20201113-14 | 53550503 | Earthworks | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 10.5 | HR | 47.54 | 0 |  |  | 665.49 | 86.5137 | 752.0037 | 2020-01-13 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Nathan Kyme | Access Rock Blasting |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock hammer working from shoefly at C-065 - C-069 | 5 | C050-C069 | Antler Lake | 0 | 44150 |  | 52 | 44152 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting664620201113-14Excavator Hammer - 30 - 50 ton- After Jan 1010.5665.49 | Corbiere and Sons Contracting664620201113-14Excavator Hammer - 30 - 50 ton- After Jan 1010.5665.49Inv#076 |  | WF5-Earthwork | WF5-Earthwork |  | 1 | 1 | 665.49 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6646 | 20201113-14 | 53550503 | Earthworks | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-01-13 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Nathan Kyme | Access Rock Blasting |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock hammer working from shoefly at C-065 - C-069 | 5 | C050-C069 | Antler Lake | 0 | 44150 |  | 52 | 44152 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting664620201113-14Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting664620201113-14Light Truck - Pick up- After Jan 101243.75Inv#076 |  | WF5-Earthwork | WF5-Earthwork |  | 1 | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6646 | 20201113-14 | 53550503 | Earthworks | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-01-13 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Nathan Kyme | Access Rock Blasting |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock hammer working from shoefly at C-065 - C-069 | 5 | C050-C069 | Antler Lake | 0 | 44150 |  | 52 | 44152 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting664620201113-14L.O.A.1210 | Corbiere and Sons Contracting664620201113-14L.O.A.1210Inv#076 |  | WF5-Earthwork | WF5-Earthwork |  | 1 | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6646 | 20201113-14 | 53550503 | Earthworks | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-01-13 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Nathan Kyme | Access Rock Blasting |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock hammer working from shoefly at C-065 - C-069 | 5 | C050-C069 | Antler Lake | 0 | 44150 |  | 52 | 44152 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting664620201113-14Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting664620201113-14Operator - Principle - After Jan 1011.5862.5Inv#076 |  | WF5-Earthwork | WF5-Earthwork |  | 1 | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6647 | 20201113-15 | 53510502 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 7 | Dynamic | 103.84 | 0 |  |  | 969.15 | 125.9895 | 1095.1395 | 2020-11-13 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building road at C-061 access | 5 | C050-C069 | Antler Lake | 0 | 44150 |  | 52 | 44152 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting664720201113-15Excavator - 30 ton- After Jan 107969.15 | Corbiere and Sons Contracting664720201113-15Excavator - 30 ton- After Jan 107969.15Inv#076 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 969.15 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6647 | 20201113-15 | 53510502 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 7 | HR | 9.16 | 0 |  |  | 85.47 | 11.1111 | 96.5811 | 2020-11-13 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building road at C-061 access | 5 | C050-C069 | Antler Lake | 0 | 44150 |  | 52 | 44152 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting664720201113-15Excavator Thumb - 30 - 50 ton- After Jan 10785.47 | Corbiere and Sons Contracting664720201113-15Excavator Thumb - 30 - 50 ton- After Jan 10785.47Inv#076 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 85.47 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6647 | 20201113-15 | 53510502 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-11-13 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building road at C-061 access | 5 | C050-C069 | Antler Lake | 0 | 44150 |  | 52 | 44152 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting664720201113-15Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting664720201113-15Light Truck - Pick up- After Jan 101243.75Inv#076 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6647 | 20201113-15 | 53510502 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-11-13 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building road at C-061 access | 5 | C050-C069 | Antler Lake | 0 | 44150 |  | 52 | 44152 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting664720201113-15L.O.A.1210 | Corbiere and Sons Contracting664720201113-15L.O.A.1210Inv#076 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6647 | 20201113-15 | 53510502 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 7.5 | HR |  |  | 75 | 0 | 562.5 | 73.125 | 635.625 | 2020-11-13 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Nathan Kyme | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building road at C-061 access | 5 | C050-C069 | Antler Lake | 0 | 44150 |  | 52 | 44152 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting664720201113-15Operator - Principle - After Jan 107.5562.5 | Corbiere and Sons Contracting664720201113-15Operator - Principle - After Jan 107.5562.5Inv#076 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 562.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6648 | 20201113-16 | 53510512 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 2 | Dynamic | 103.84 | 0 |  |  | 276.9 | 35.997 | 312.897 | 2020-11-13 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 2 hours doing maintenance for C-064 access | 5 | C050-C069 | Antler Lake | 0 | 44150 |  | 52 | 44152 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting664820201113-16Excavator - 30 ton- After Jan 102276.9 | Corbiere and Sons Contracting664820201113-16Excavator - 30 ton- After Jan 102276.9Inv#076 | [5 empty] | 1 | 276.9 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6648 | 20201113-16 | 53510512 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 2 | HR | 9.16 | 0 |  |  | 24.42 | 3.1746 | 27.5946 | 2020-11-13 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 2 hours doing maintenance for C-064 access | 5 | C050-C069 | Antler Lake | 0 | 44150 |  | 52 | 44152 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting664820201113-16Excavator Thumb - 30 - 50 ton- After Jan 10224.42 | Corbiere and Sons Contracting664820201113-16Excavator Thumb - 30 - 50 ton- After Jan 10224.42Inv#076 | [5 empty] | 1 | 24.42 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6648 | 20201113-16 | 53510512 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 2 | HR |  |  | 75 | 0 | 150 | 19.5 | 169.5 | 2020-11-13 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Nathan Kyme | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 2 hours doing maintenance for C-064 access | 5 | C050-C069 | Antler Lake | 0 | 44150 |  | 52 | 44152 | [5 empty] | Kelton Percival | 05 | Corbiere and Sons Contracting664820201113-16Operator - Principle - After Jan 102150 | Corbiere and Sons Contracting664820201113-16Operator - Principle - After Jan 102150Inv#076 | [5 empty] | 1 | 150 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6827 | 20201113-22 | 53510312 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 4 | Dynamic | 95.24 | 0 |  |  | 507.92 | 66.0296 | 573.9496 | 2020-11-13 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Lachance road then floated to Maata's | 3 | B161-B181 | Lachance Road | 0 | 44159 |  | 37 | 44160 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting682720201113-22Grader - Cat 12 to 14 or equal- After Jan 104507.92 | Corbiere and Sons Contracting682720201113-22Grader - Cat 12 to 14 or equal- After Jan 104507.92Inv#076 | [5 empty] | 1 | 507.92 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6827 | 20201113-22 | 53510312 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-11-13 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Lachance road then floated to Maata's | 3 | B161-B181 | Lachance Road | 0 | 44159 |  | 37 | 44160 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting682720201113-22Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting682720201113-22Light Truck - Pick up- After Jan 101243.75Inv#076 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6827 | 20201113-22 | 53510312 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 4 | HR |  |  | 75 | 0 | 300 | 39 | 339 | 2020-11-13 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Lachance road then floated to Maata's | 3 | B161-B181 | Lachance Road | 0 | 44159 |  | 37 | 44160 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting682720201113-22Operator - Principle - After Jan 104300 | Corbiere and Sons Contracting682720201113-22Operator - Principle - After Jan 104300Inv#076 | [5 empty] | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6828 | 20201113-23 | 53510312 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 4 | Dynamic | 95.24 | 0 |  |  | 507.92 | 66.0296 | 573.9496 | 2020-11-13 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Maata's road from B092-B099 | 3 | B092-B099 | Maata's Road | 0 | 44159 |  | 37 | 44160 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting682820201113-23Grader - Cat 12 to 14 or equal- After Jan 104507.92 | Corbiere and Sons Contracting682820201113-23Grader - Cat 12 to 14 or equal- After Jan 104507.92Inv#076 | [5 empty] | 1 | 507.92 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6828 | 20201113-23 | 53510312 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-11-13 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Maata's road from B092-B099 | 3 | B092-B099 | Maata's Road | 0 | 44159 |  | 37 | 44160 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting682820201113-23Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting682820201113-23Light Truck - Pick up- After Jan 101243.75Inv#076 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6828 | 20201113-23 | 53510312 | Access | 0 | Foreman | 95 | 4 | HR |  |  | 95 | 0 | 380 | 49.4 | 429.4 | 2020-11-13 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Maata's road from B092-B099 | 3 | B092-B099 | Maata's Road | 0 | 44159 |  | 37 | 44160 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting682820201113-23Foreman4380 | Corbiere and Sons Contracting682820201113-23Foreman4380Inv#076 | [5 empty] | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6828 | 20201113-23 | 53510312 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 4 | HR |  |  | 75 | 0 | 300 | 39 | 339 | 2020-11-13 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Maata's road from B092-B099 | 3 | B092-B099 | Maata's Road | 0 | 44159 |  | 37 | 44160 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting682820201113-23Operator - Principle - After Jan 104300 | Corbiere and Sons Contracting682820201113-23Operator - Principle - After Jan 104300Inv#076 | [5 empty] | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6895 | 20201114-10 | 53550503 | Earthworks | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10.5 | Dynamic | 110.22 | 0 |  |  | 1543.08 | 200.6004 | 1743.6804 | 2020-11-14 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Access Rock Blasting |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammering 2 knobs at C-065 - C-069 diversion road. | 5 | C050-C069 | Antler Lake | 0 | 44161 |  | 37 | 44161 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting689520201114-10Excavator - 36 ton- After Jan 1010.51543.08 | Corbiere and Sons Contracting689520201114-10Excavator - 36 ton- After Jan 1010.51543.08Inv#081 |  | WF5-Earthwork | WF5-Earthwork |  | 1 | 1 | 1543.08 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6895 | 20201114-10 | 53550503 | Earthworks | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 10.5 | HR | 47.54 | 0 |  |  | 665.49 | 86.5137 | 752.0037 | 2020-11-14 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Access Rock Blasting |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammering 2 knobs at C-065 - C-069 diversion road. | 5 | C050-C069 | Antler Lake | 0 | 44161 |  | 37 | 44161 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting689520201114-10Excavator Hammer - 30 - 50 ton- After Jan 1010.5665.49 | Corbiere and Sons Contracting689520201114-10Excavator Hammer - 30 - 50 ton- After Jan 1010.5665.49Inv#081 |  | WF5-Earthwork | WF5-Earthwork |  | 1 | 1 | 665.49 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6895 | 20201114-10 | 53550503 | Earthworks | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-11-14 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Access Rock Blasting |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammering 2 knobs at C-065 - C-069 diversion road. | 5 | C050-C069 | Antler Lake | 0 | 44161 |  | 37 | 44161 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting689520201114-10Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting689520201114-10Light Truck - Pick up- After Jan 101243.75Inv#081 |  | WF5-Earthwork | WF5-Earthwork |  | 1 | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6895 | 20201114-10 | 53550503 | Earthworks | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-11-14 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Access Rock Blasting |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammering 2 knobs at C-065 - C-069 diversion road. | 5 | C050-C069 | Antler Lake | 0 | 44161 |  | 37 | 44161 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting689520201114-10L.O.A.1210 | Corbiere and Sons Contracting689520201114-10L.O.A.1210Inv#081 |  | WF5-Earthwork | WF5-Earthwork |  | 1 | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6895 | 20201114-10 | 53550503 | Earthworks | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-11-14 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Access Rock Blasting |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hammering 2 knobs at C-065 - C-069 diversion road. | 5 | C050-C069 | Antler Lake | 0 | 44161 |  | 37 | 44161 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting689520201114-10Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting689520201114-10Operator - Principle - After Jan 1011.5862.5Inv#081 |  | WF5-Earthwork | WF5-Earthwork |  | 1 | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6896 | 20201114-11 | 53510503 | Access | 0 | Skidder | 171 | 4 | HR | 128.25 | 0 |  |  | 684 | 88.92 | 772.92 | 2020-11-14 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator putting corduroy down by WC7600.01Skidder delivered trees for corduroy at WC7600.01 | 5 | C076-C116 | Cook Lake | 0 | 44161 |  | 37 | 44161 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting689620201114-11Skidder 4684 | Corbiere and Sons Contracting689620201114-11Skidder 4684Inv#081 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 684 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6896 | 20201114-11 | 53510503 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 5 | Dynamic | 110.22 | 0 |  |  | 734.8 | 95.524 | 830.324 | 2020-11-14 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator putting corduroy down by WC7600.01Skidder delivered trees for corduroy at WC7600.01 | 5 | C076-C116 | Cook Lake | 0 | 44161 |  | 37 | 44161 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting689620201114-11Excavator - 36 ton- After Jan 105734.8 | Corbiere and Sons Contracting689620201114-11Excavator - 36 ton- After Jan 105734.8Inv#081 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 734.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6896 | 20201114-11 | 53510503 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-11-14 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator putting corduroy down by WC7600.01Skidder delivered trees for corduroy at WC7600.01 | 5 | C076-C116 | Cook Lake | 0 | 44161 |  | 37 | 44161 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting689620201114-11Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting689620201114-11Light Truck - Pick up- After Jan 101243.75Inv#081 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6896 | 20201114-11 | 53510503 | Access | 0 | Foreman | 95 | 4 | HR |  |  | 95 | 0 | 380 | 49.4 | 429.4 | 2020-11-14 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator putting corduroy down by WC7600.01Skidder delivered trees for corduroy at WC7600.01 | 5 | C076-C116 | Cook Lake | 0 | 44161 |  | 37 | 44161 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting689620201114-11Foreman4380 | Corbiere and Sons Contracting689620201114-11Foreman4380Inv#081 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6896 | 20201114-11 | 53510503 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2020-11-14 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator putting corduroy down by WC7600.01Skidder delivered trees for corduroy at WC7600.01 | 5 | C076-C116 | Cook Lake | 0 | 44161 |  | 37 | 44161 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting689620201114-11L.O.A.3630 | Corbiere and Sons Contracting689620201114-11L.O.A.3630Inv#081 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6896 | 20201114-11 | 53510503 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 9 | HR |  |  | 75 | 0 | 675 | 87.75 | 762.75 | 2020-11-14 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator putting corduroy down by WC7600.01Skidder delivered trees for corduroy at WC7600.01 | 5 | C076-C116 | Cook Lake | 0 | 44161 |  | 37 | 44161 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting689620201114-11Operator - Principle - After Jan 109675 | Corbiere and Sons Contracting689620201114-11Operator - Principle - After Jan 109675Inv#081 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 675 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6898 | 20201114-13 | 53510512 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 4 | Dynamic | 103.84 | 0 |  |  | 553.8 | 71.994 | 625.794 | 2020-11-14 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance | 5 | C076-C116 | Cook Lake | 0 | 44161 |  | 37 | 44161 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting689820201114-13Excavator - 30 ton- After Jan 104553.8 | Corbiere and Sons Contracting689820201114-13Excavator - 30 ton- After Jan 104553.8Inv#081 | [5 empty] | 1 | 553.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6898 | 20201114-13 | 53510512 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 4 | Dynamic | 110.22 | 0 |  |  | 587.84 | 76.4192 | 664.2592 | 2020-11-14 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance | 5 | C076-C116 | Cook Lake | 0 | 44161 |  | 37 | 44161 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting689820201114-13Excavator - 36 ton- After Jan 104587.84 | Corbiere and Sons Contracting689820201114-13Excavator - 36 ton- After Jan 104587.84Inv#081 | [5 empty] | 1 | 587.84 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6898 | 20201114-13 | 53510512 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 4 | HR | 9.16 | 0 |  |  | 48.84 | 6.3492 | 55.1892 | 2020-11-14 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance | 5 | C076-C116 | Cook Lake | 0 | 44161 |  | 37 | 44161 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting689820201114-13Excavator Thumb - 30 - 50 ton- After Jan 10448.84 | Corbiere and Sons Contracting689820201114-13Excavator Thumb - 30 - 50 ton- After Jan 10448.84Inv#081 | [5 empty] | 1 | 48.84 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6898 | 20201114-13 | 53510512 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-11-14 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance | 5 | C076-C116 | Cook Lake | 0 | 44161 |  | 37 | 44161 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting689820201114-13Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting689820201114-13Light Truck - Pick up- After Jan 101243.75Inv#081 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6898 | 20201114-13 | 53510512 | Access | 0 | Foreman | 95 | 4 | HR |  |  | 95 | 0 | 380 | 49.4 | 429.4 | 2020-11-14 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance | 5 | C076-C116 | Cook Lake | 0 | 44161 |  | 37 | 44161 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting689820201114-13Foreman4380 | Corbiere and Sons Contracting689820201114-13Foreman4380Inv#081 | [5 empty] | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6898 | 20201114-13 | 53510512 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 8 | HR |  |  | 75 | 0 | 600 | 78 | 678 | 2020-11-14 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance | 5 | C076-C116 | Cook Lake | 0 | 44161 |  | 37 | 44161 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting689820201114-13Operator - Principle - After Jan 108600 | Corbiere and Sons Contracting689820201114-13Operator - Principle - After Jan 108600Inv#081 | [5 empty] | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6899 | 20201114-14 | 53510504 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 7 | Dynamic | 110.22 | 0 |  |  | 1028.72 | 133.7336 | 1162.4536 | 2020-11-14 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Managing stock pile for gravel and forwarding material | 5 | C076-C116 | Cook Lake | 0 | 44161 |  | 37 | 44161 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting689920201114-14Excavator - 36 ton- After Jan 1071028.72 | Corbiere and Sons Contracting689920201114-14Excavator - 36 ton- After Jan 1071028.72Inv#081 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1028.72 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6899 | 20201114-14 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-11-14 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Managing stock pile for gravel and forwarding material | 5 | C076-C116 | Cook Lake | 0 | 44161 |  | 37 | 44161 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting689920201114-14Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting689920201114-14Light Truck - Pick up- After Jan 101243.75Inv#081 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6899 | 20201114-14 | 53510504 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-11-14 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Managing stock pile for gravel and forwarding material | 5 | C076-C116 | Cook Lake | 0 | 44161 |  | 37 | 44161 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting689920201114-14L.O.A.1210 | Corbiere and Sons Contracting689920201114-14L.O.A.1210Inv#081 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6899 | 20201114-14 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 7.5 | HR |  |  | 75 | 0 | 562.5 | 73.125 | 635.625 | 2020-11-14 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Managing stock pile for gravel and forwarding material | 5 | C076-C116 | Cook Lake | 0 | 44161 |  | 37 | 44161 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting689920201114-14Operator - Principle - After Jan 107.5562.5 | Corbiere and Sons Contracting689920201114-14Operator - Principle - After Jan 107.5562.5Inv#081 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 562.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6833 | 20201114-17 | 53510312 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 8 | Dynamic | 110.22 | 0 |  |  | 1175.68 | 152.8384 | 1328.5184 | 2020-11-14 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-5 patching holes in road and then demobbed excess geo from site | 3 | B077-B084 | Landfill Road | 0 | 44159 |  | 37 | 44160 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting683320201114-17Excavator - 36 ton- After Jan 1081175.68 | Corbiere and Sons Contracting683320201114-17Excavator - 36 ton- After Jan 1081175.68Inv#076 | [5 empty] | 1 | 1175.68 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6833 | 20201114-17 | 53510312 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 8 | HR | 9.16 | 0 |  |  | 97.68 | 12.6984 | 110.3784 | 2020-11-14 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-5 patching holes in road and then demobbed excess geo from site | 3 | B077-B084 | Landfill Road | 0 | 44159 |  | 37 | 44160 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting683320201114-17Excavator Thumb - 30 - 50 ton- After Jan 10897.68 | Corbiere and Sons Contracting683320201114-17Excavator Thumb - 30 - 50 ton- After Jan 10897.68Inv#076 | [5 empty] | 1 | 97.68 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6833 | 20201114-17 | 53510312 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 9 | HR |  |  | 75 | 0 | 675 | 87.75 | 762.75 | 2020-11-14 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-5 patching holes in road and then demobbed excess geo from site | 3 | B077-B084 | Landfill Road | 0 | 44159 |  | 37 | 44160 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting683320201114-17Operator - Principle - After Jan 109675 | Corbiere and Sons Contracting683320201114-17Operator - Principle - After Jan 109675Inv#076 | [5 empty] | 1 | 675 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6834 | 20201114-18 | 53510311 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 5 | Dynamic | 98.61 | 0 |  |  | 657.4 | 85.462 | 742.862 | 2020-11-14 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | DZ clearing snow on ground from B096-B098 | 3 | B088-B099 | Maata's Road | 0 | 44159 |  | 37 | 44160 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting683420201114-18Dozer D6 or equal- After Jan 105657.4 | Corbiere and Sons Contracting683420201114-18Dozer D6 or equal- After Jan 105657.4Inv#076 | [5 empty] | 1 | 657.4 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6834 | 20201114-18 | 53510311 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-11-14 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | DZ clearing snow on ground from B096-B098 | 3 | B088-B099 | Maata's Road | 0 | 44159 |  | 37 | 44160 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting683420201114-18Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting683420201114-18Light Truck - Pick up- After Jan 102487.5Inv#076 | [5 empty] | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6834 | 20201114-18 | 53510311 | Access | 0 | Foreman | 95 | 4 | HR |  |  | 95 | 0 | 380 | 49.4 | 429.4 | 2020-11-14 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | DZ clearing snow on ground from B096-B098 | 3 | B088-B099 | Maata's Road | 0 | 44159 |  | 37 | 44160 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting683420201114-18Foreman4380 | Corbiere and Sons Contracting683420201114-18Foreman4380Inv#076 | [5 empty] | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6834 | 20201114-18 | 53510311 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5 | HR |  |  | 75 | 0 | 375 | 48.75 | 423.75 | 2020-11-14 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | DZ clearing snow on ground from B096-B098 | 3 | B088-B099 | Maata's Road | 0 | 44159 |  | 37 | 44160 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting683420201114-18Operator - Principle - After Jan 105375 | Corbiere and Sons Contracting683420201114-18Operator - Principle - After Jan 105375Inv#076 | [5 empty] | 1 | 375 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6835 | 20201114-19 | 53510311 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 4 | Dynamic | 98.61 | 0 |  |  | 525.92 | 68.3696 | 594.2896 | 2020-11-14 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | DZ moved to Jackfish from Maata's and then demobbed after clearing snow | 3 | B159-B161 | Lackfish River Road | 0 | 44159 |  | 37 | 44160 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting683520201114-19Dozer D6 or equal- After Jan 104525.92 | Corbiere and Sons Contracting683520201114-19Dozer D6 or equal- After Jan 104525.92Inv#076 | [5 empty] | 1 | 525.92 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6835 | 20201114-19 | 53510311 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 75 | 0 | 450 | 58.5 | 508.5 | 2020-11-14 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | DZ moved to Jackfish from Maata's and then demobbed after clearing snow | 3 | B159-B161 | Lackfish River Road | 0 | 44159 |  | 37 | 44160 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting683520201114-19Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting683520201114-19Operator - Principle - After Jan 106450Inv#076 | [5 empty] | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7028 | 20201114-24 | 53510311 | Access | 0 | 3rd Party Charges | 1 | 1071.84 | unit |  |  |  |  | 1071.84 | 139.3392 | 1211.1792 | 2020-11-14 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance B-159 - B160 structure - clearing of snow. | 3 | B159-B160 | Jackfish Road | 0 | 44165 |  | 36 | 44174 | 371 | Traffic Control - Road Maintenance - Clearing of Snow |  |  |  | Mike Lecocq | 03 | Corbiere and Sons Contracting702820201114-243rd Party Charges1071.841071.84 | Corbiere and Sons Contracting702820201114-243rd Party Charges1071.841071.84Inv#082 | [5 empty] | 1 | 1071.84 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6893 | 20201114-8 | 53510504 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10.5 | Dynamic | 98.61 | 0 |  |  | 1380.54 | 179.4702 | 1560.0102 | 2020-11-14 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Labourers delivering and rolling out geoDozer spreading gravel all day, Excavator loading rock truck all day, Rock truck hauling all day | 5 | C117-C124 | Mill Road South | 0 | 44161 |  | 37 | 44161 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting689320201114-8Dozer D6 or equal- After Jan 1010.51380.54 | Corbiere and Sons Contracting689320201114-8Dozer D6 or equal- After Jan 1010.51380.54Inv#081 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1380.54 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6893 | 20201114-8 | 53510504 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10.5 | Dynamic | 103.84 | 0 |  |  | 1453.725 | 188.9843 | 1642.7093 | 2020-11-14 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Labourers delivering and rolling out geoDozer spreading gravel all day, Excavator loading rock truck all day, Rock truck hauling all day | 5 | C117-C124 | Mill Road South | 0 | 44161 |  | 37 | 44161 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting689320201114-8Excavator - 30 ton- After Jan 1010.51453.725 | Corbiere and Sons Contracting689320201114-8Excavator - 30 ton- After Jan 1010.51453.725Inv#081 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1453.725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6893 | 20201114-8 | 53510504 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10.5 | HR | 9.16 | 0 |  |  | 128.205 | 16.6667 | 144.8716 | 2020-11-14 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Labourers delivering and rolling out geoDozer spreading gravel all day, Excavator loading rock truck all day, Rock truck hauling all day | 5 | C117-C124 | Mill Road South | 0 | 44161 |  | 37 | 44161 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting689320201114-8Excavator Thumb - 30 - 50 ton- After Jan 1010.5128.205 | Corbiere and Sons Contracting689320201114-8Excavator Thumb - 30 - 50 ton- After Jan 1010.5128.205Inv#081 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 128.205 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6893 | 20201114-8 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-11-14 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Labourers delivering and rolling out geoDozer spreading gravel all day, Excavator loading rock truck all day, Rock truck hauling all day | 5 | C117-C124 | Mill Road South | 0 | 44161 |  | 37 | 44161 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting689320201114-8Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting689320201114-8Light Truck - Pick up- After Jan 102487.5Inv#081 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6893 | 20201114-8 | 53510504 | Access | 0 | Light Truck w/ Tandum Trailer- After Jan 10 | 337.5 | 1 | DAY | 253.13 | 0 |  |  | 337.5 | 43.875 | 381.375 | 2020-11-14 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Labourers delivering and rolling out geoDozer spreading gravel all day, Excavator loading rock truck all day, Rock truck hauling all day | 5 | C117-C124 | Mill Road South | 0 | 44161 |  | 37 | 44161 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting689320201114-8Light Truck w/ Tandum Trailer- After Jan 101337.5 | Corbiere and Sons Contracting689320201114-8Light Truck w/ Tandum Trailer- After Jan 101337.5Inv#081 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 337.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6893 | 20201114-8 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 10.5 | Dynamic | 103.54 | 0 |  |  | 1449.525 | 188.4383 | 1637.9633 | 2020-11-14 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Labourers delivering and rolling out geoDozer spreading gravel all day, Excavator loading rock truck all day, Rock truck hauling all day | 5 | C117-C124 | Mill Road South | 0 | 44161 |  | 37 | 44161 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting689320201114-8Rock Truck - 30 Ton- After Jan 1010.51449.525 | Corbiere and Sons Contracting689320201114-8Rock Truck - 30 Ton- After Jan 1010.51449.525Inv#081 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1449.525 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6893 | 20201114-8 | 53510504 | Access | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2020-11-14 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Labourers delivering and rolling out geoDozer spreading gravel all day, Excavator loading rock truck all day, Rock truck hauling all day | 5 | C117-C124 | Mill Road South | 0 | 44161 |  | 37 | 44161 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting689320201114-8L.O.A.51050 | Corbiere and Sons Contracting689320201114-8L.O.A.51050Inv#081 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6893 | 20201114-8 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 23 | HR |  |  | 75 | 0 | 1725 | 224.25 | 1949.25 | 2020-11-14 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Labourers delivering and rolling out geoDozer spreading gravel all day, Excavator loading rock truck all day, Rock truck hauling all day | 5 | C117-C124 | Mill Road South | 0 | 44161 |  | 37 | 44161 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting689320201114-8Operator - Principle - After Jan 10231725 | Corbiere and Sons Contracting689320201114-8Operator - Principle - After Jan 10231725Inv#081 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6893 | 20201114-8 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 11.5 | HR |  |  | 70 | 0 | 805 | 104.65 | 909.65 | 2020-11-14 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Labourers delivering and rolling out geoDozer spreading gravel all day, Excavator loading rock truck all day, Rock truck hauling all day | 5 | C117-C124 | Mill Road South | 0 | 44161 |  | 37 | 44161 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting689320201114-8Driver - AZ - After Jan 1011.5805 | Corbiere and Sons Contracting689320201114-8Driver - AZ - After Jan 1011.5805Inv#081 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 805 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6893 | 20201114-8 | 53510504 | Access | 0 | Labourer - General - After Jan 10 | 60 | 10 | HR |  |  | 60 | 0 | 600 | 78 | 678 | 2020-11-14 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Labourers delivering and rolling out geoDozer spreading gravel all day, Excavator loading rock truck all day, Rock truck hauling all day | 5 | C117-C124 | Mill Road South | 0 | 44161 |  | 37 | 44161 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting689320201114-8Labourer - General - After Jan 1010600 | Corbiere and Sons Contracting689320201114-8Labourer - General - After Jan 1010600Inv#081 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6894 | 20201114-9 | 53510512 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10.5 | Dynamic | 103.84 | 0 |  |  | 1453.725 | 188.9843 | 1642.7093 | 2020-11-14 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Tying in new diversion road at C-062 - road is not ready for capping | 5 | C050-C069 | Antler Lake | 0 | 44161 |  | 37 | 44161 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting689420201114-9Excavator - 30 ton- After Jan 1010.51453.725 | Corbiere and Sons Contracting689420201114-9Excavator - 30 ton- After Jan 1010.51453.725Inv#081 | [5 empty] | 1 | 1453.725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6894 | 20201114-9 | 53510512 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10.5 | HR | 9.16 | 0 |  |  | 128.205 | 16.6667 | 144.8716 | 2020-11-14 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Tying in new diversion road at C-062 - road is not ready for capping | 5 | C050-C069 | Antler Lake | 0 | 44161 |  | 37 | 44161 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting689420201114-9Excavator Thumb - 30 - 50 ton- After Jan 1010.5128.205 | Corbiere and Sons Contracting689420201114-9Excavator Thumb - 30 - 50 ton- After Jan 1010.5128.205Inv#081 | [5 empty] | 1 | 128.205 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6894 | 20201114-9 | 53510512 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-11-14 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Tying in new diversion road at C-062 - road is not ready for capping | 5 | C050-C069 | Antler Lake | 0 | 44161 |  | 37 | 44161 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting689420201114-9Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting689420201114-9Light Truck - Pick up- After Jan 101243.75Inv#081 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6894 | 20201114-9 | 53510512 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-11-14 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Tying in new diversion road at C-062 - road is not ready for capping | 5 | C050-C069 | Antler Lake | 0 | 44161 |  | 37 | 44161 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting689420201114-9L.O.A.1210 | Corbiere and Sons Contracting689420201114-9L.O.A.1210Inv#081 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6894 | 20201114-9 | 53510512 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-11-14 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Tying in new diversion road at C-062 - road is not ready for capping | 5 | C050-C069 | Antler Lake | 0 | 44161 |  | 37 | 44161 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting689420201114-9Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting689420201114-9Operator - Principle - After Jan 1011.5862.5Inv#081 | [5 empty] | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6697 | 20201115-10 | 53510512 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 5 | Dynamic | 98.61 | 0 |  |  | 657.4 | 85.462 | 742.862 | 2020-11-15 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-015 and Dozer doing road maintenance. | 5 | C076-C116 | Cook Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting669720201115-10Dozer D6 or equal- After Jan 105657.4 | Corbiere and Sons Contracting669720201115-10Dozer D6 or equal- After Jan 105657.4Inv#076 | [5 empty] | 1 | 657.4 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6697 | 20201115-10 | 53510512 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 5 | Dynamic | 103.84 | 0 |  |  | 692.25 | 89.9925 | 782.2425 | 2020-11-15 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-015 and Dozer doing road maintenance. | 5 | C076-C116 | Cook Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting669720201115-10Excavator - 30 ton- After Jan 105692.25 | Corbiere and Sons Contracting669720201115-10Excavator - 30 ton- After Jan 105692.25Inv#076 | [5 empty] | 1 | 692.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6697 | 20201115-10 | 53510512 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 5 | HR | 9.16 | 0 |  |  | 61.05 | 7.9365 | 68.9865 | 2020-11-15 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-015 and Dozer doing road maintenance. | 5 | C076-C116 | Cook Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting669720201115-10Excavator Thumb - 30 - 50 ton- After Jan 10561.05 | Corbiere and Sons Contracting669720201115-10Excavator Thumb - 30 - 50 ton- After Jan 10561.05Inv#076 | [5 empty] | 1 | 61.05 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6697 | 20201115-10 | 53510512 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-11-15 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-015 and Dozer doing road maintenance. | 5 | C076-C116 | Cook Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting669720201115-10Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting669720201115-10Light Truck - Pick up- After Jan 101243.75Inv#076 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6697 | 20201115-10 | 53510512 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-11-15 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-015 and Dozer doing road maintenance. | 5 | C076-C116 | Cook Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting669720201115-10L.O.A.2420 | Corbiere and Sons Contracting669720201115-10L.O.A.2420Inv#076 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6697 | 20201115-10 | 53510512 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 10 | HR |  |  | 75 | 0 | 750 | 97.5 | 847.5 | 2020-11-15 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-015 and Dozer doing road maintenance. | 5 | C076-C116 | Cook Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting669720201115-10Operator - Principle - After Jan 1010750 | Corbiere and Sons Contracting669720201115-10Operator - Principle - After Jan 1010750Inv#076 | [5 empty] | 1 | 750 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6700 | 20201115-13 | 53510512 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 5 | Dynamic | 98.61 | 0 |  |  | 657.4 | 85.462 | 742.862 | 2020-11-15 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer cleared snow and did scrapping for 5 hours after being floated. | 5 | C050-C069 | Antler Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting670020201115-13Dozer D6 or equal- After Jan 105657.4 | Corbiere and Sons Contracting670020201115-13Dozer D6 or equal- After Jan 105657.4Inv#076 | [5 empty] | 1 | 657.4 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6700 | 20201115-13 | 53510512 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-11-15 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer cleared snow and did scrapping for 5 hours after being floated. | 5 | C050-C069 | Antler Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting670020201115-13Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting670020201115-13Light Truck - Pick up- After Jan 101243.75Inv#076 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6700 | 20201115-13 | 53510512 | Access | 0 | Foreman | 95 | 3 | HR |  |  | 95 | 0 | 285 | 37.05 | 322.05 | 2020-11-15 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer cleared snow and did scrapping for 5 hours after being floated. | 5 | C050-C069 | Antler Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting670020201115-13Foreman3285 | Corbiere and Sons Contracting670020201115-13Foreman3285Inv#076 | [5 empty] | 1 | 285 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6700 | 20201115-13 | 53510512 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-11-15 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer cleared snow and did scrapping for 5 hours after being floated. | 5 | C050-C069 | Antler Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting670020201115-13L.O.A.1210 | Corbiere and Sons Contracting670020201115-13L.O.A.1210Inv#076 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6700 | 20201115-13 | 53510512 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5 | HR |  |  | 75 | 0 | 375 | 48.75 | 423.75 | 2020-11-15 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer cleared snow and did scrapping for 5 hours after being floated. | 5 | C050-C069 | Antler Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting670020201115-13Operator - Principle - After Jan 105375 | Corbiere and Sons Contracting670020201115-13Operator - Principle - After Jan 105375Inv#076 | [5 empty] | 1 | 375 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6840 | 20201115-14 | 53520101 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-11-15 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Foreman met with Valard on site and walked area to come up with a plan for clearing and access | 1 | A-001 to Highway 17 | Substation | 0 | 44159 |  | 37 | 44160 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting684020201115-14Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting684020201115-14Light Truck - Pick up- After Jan 101243.75Inv#076 |  |  | WF1-Merchantable Clearing |  |  | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6840 | 20201115-14 | 53520101 | Clearing | 0 | Foreman | 95 | 6 | HR |  |  | 95 | 0 | 570 | 74.1 | 644.1 | 2020-11-15 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Foreman met with Valard on site and walked area to come up with a plan for clearing and access | 1 | A-001 to Highway 17 | Substation | 0 | 44159 |  | 37 | 44160 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting684020201115-14Foreman6570 | Corbiere and Sons Contracting684020201115-14Foreman6570Inv#076 |  |  | WF1-Merchantable Clearing |  |  | 1 | 570 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6871 | 20201115-16 | 53510312 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 5.5 | Dynamic | 110.22 | 0 |  |  | 808.28 | 105.0764 | 913.3564 | 2020-11-15 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Repaired road B-074 - B-084 | 3 | B078-B084 | Red Rock No. 07 | 0 | 44160 |  | 37 | 44160 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting687120201115-16Excavator - 36 ton- After Jan 105.5808.28 | Corbiere and Sons Contracting687120201115-16Excavator - 36 ton- After Jan 105.5808.28Inv#081 | [5 empty] | 1 | 808.28 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6871 | 20201115-16 | 53510312 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 5.5 | HR | 9.16 | 0 |  |  | 67.155 | 8.7302 | 75.8851 | 2020-11-15 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Repaired road B-074 - B-084 | 3 | B078-B084 | Red Rock No. 07 | 0 | 44160 |  | 37 | 44160 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting687120201115-16Excavator Thumb - 30 - 50 ton- After Jan 105.567.155 | Corbiere and Sons Contracting687120201115-16Excavator Thumb - 30 - 50 ton- After Jan 105.567.155Inv#081 | [5 empty] | 1 | 67.155 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6871 | 20201115-16 | 53510312 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6.5 | HR |  |  | 75 | 0 | 487.5 | 63.375 | 550.875 | 2020-11-15 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Repaired road B-074 - B-084 | 3 | B078-B084 | Red Rock No. 07 | 0 | 44160 |  | 37 | 44160 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting687120201115-16Operator - Principle - After Jan 106.5487.5 | Corbiere and Sons Contracting687120201115-16Operator - Principle - After Jan 106.5487.5Inv#081 | [5 empty] | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6691 | 20201115-4 | 53510312 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10.5 | Dynamic | 98.61 | 0 |  |  | 1380.54 | 179.4702 | 1560.0102 | 2020-11-15 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer dragging tires across Fire Hill Rd East to manage water build up - night shift | 3 | B136-B144 | Fire Hill Road east | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting669120201115-4Dozer D6 or equal- After Jan 1010.51380.54 | Corbiere and Sons Contracting669120201115-4Dozer D6 or equal- After Jan 1010.51380.54Inv#076 | [5 empty] | 1 | 1380.54 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6691 | 20201115-4 | 53510312 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-11-15 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer dragging tires across Fire Hill Rd East to manage water build up - night shift | 3 | B136-B144 | Fire Hill Road east | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting669120201115-4L.O.A.1210 | Corbiere and Sons Contracting669120201115-4L.O.A.1210Inv#076 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6691 | 20201115-4 | 53510312 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-11-15 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer dragging tires across Fire Hill Rd East to manage water build up - night shift | 3 | B136-B144 | Fire Hill Road east | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting669120201115-4Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting669120201115-4Operator - Principle - After Jan 1011.5862.5Inv#076 | [5 empty] | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6694 | 20201115-7 | 53530501 | Rig/Access Mats | 0 | Skidder | 171 | 5 | HR | 128.25 | 0 |  |  | 855 | 111.15 | 966.15 | 2020-11-15 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Rig/Access Mat Handling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Mobilizing mats to WC7600.01 | 5 | C076-C116 | Cook Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting669420201115-7Skidder 5855 | Corbiere and Sons Contracting669420201115-7Skidder 5855Inv#076 |  |  | WF5-WaterCrossing |  |  | 1 | 855 | WC406 | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6694 | 20201115-7 | 53530501 | Rig/Access Mats | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-11-15 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Rig/Access Mat Handling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Mobilizing mats to WC7600.01 | 5 | C076-C116 | Cook Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting669420201115-7Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting669420201115-7Light Truck - Pick up- After Jan 101243.75Inv#076 |  |  | WF5-WaterCrossing |  |  | 1 | 243.75 | WC406 | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6694 | 20201115-7 | 53530501 | Rig/Access Mats | 0 | Light Truck w/ Tandum Trailer- After Jan 10 | 337.5 | 1 | DAY | 253.13 | 0 |  |  | 337.5 | 43.875 | 381.375 | 2020-11-15 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Rig/Access Mat Handling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Mobilizing mats to WC7600.01 | 5 | C076-C116 | Cook Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting669420201115-7Light Truck w/ Tandum Trailer- After Jan 101337.5 | Corbiere and Sons Contracting669420201115-7Light Truck w/ Tandum Trailer- After Jan 101337.5Inv#076 |  |  | WF5-WaterCrossing |  |  | 1 | 337.5 | WC406 | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6694 | 20201115-7 | 53530501 | Rig/Access Mats | 0 | Foreman | 95 | 2 | HR |  |  | 95 | 0 | 190 | 24.7 | 214.7 | 2020-11-15 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Rig/Access Mat Handling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Mobilizing mats to WC7600.01 | 5 | C076-C116 | Cook Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting669420201115-7Foreman2190 | Corbiere and Sons Contracting669420201115-7Foreman2190Inv#076 |  |  | WF5-WaterCrossing |  |  | 1 | 190 | WC406 | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6694 | 20201115-7 | 53530501 | Rig/Access Mats | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2020-11-15 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Rig/Access Mat Handling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Mobilizing mats to WC7600.01 | 5 | C076-C116 | Cook Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting669420201115-7L.O.A.51050 | Corbiere and Sons Contracting669420201115-7L.O.A.51050Inv#076 |  |  | WF5-WaterCrossing |  |  | 1 | 1050 | WC406 | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6694 | 20201115-7 | 53530501 | Rig/Access Mats | 0 | Operator - Principle - After Jan 10 | 75 | 5 | HR |  |  | 75 | 0 | 375 | 48.75 | 423.75 | 2020-11-15 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Rig/Access Mat Handling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Mobilizing mats to WC7600.01 | 5 | C076-C116 | Cook Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting669420201115-7Operator - Principle - After Jan 105375 | Corbiere and Sons Contracting669420201115-7Operator - Principle - After Jan 105375Inv#076 |  |  | WF5-WaterCrossing |  |  | 1 | 375 | WC406 | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6694 | 20201115-7 | 53530501 | Rig/Access Mats | 0 | Labourer - General - After Jan 10 | 60 | 9 | HR |  |  | 60 | 0 | 540 | 70.2 | 610.2 | 2020-11-15 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Rig/Access Mat Handling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Mobilizing mats to WC7600.01 | 5 | C076-C116 | Cook Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting669420201115-7Labourer - General - After Jan 109540 | Corbiere and Sons Contracting669420201115-7Labourer - General - After Jan 109540Inv#076 |  |  | WF5-WaterCrossing |  |  | 1 | 540 | WC406 | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6696 | 20201115-9 | 53510502 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 5 | Dynamic | 110.22 | 0 |  |  | 734.8 | 95.524 | 830.324 | 2020-11-15 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working with corduroy from C-106. | 5 | C093-C116 | Cook Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting669620201115-9Excavator - 36 ton- After Jan 105734.8 | Corbiere and Sons Contracting669620201115-9Excavator - 36 ton- After Jan 105734.8Inv#076 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 734.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6696 | 20201115-9 | 53510502 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-11-15 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working with corduroy from C-106. | 5 | C093-C116 | Cook Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting669620201115-9Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting669620201115-9Light Truck - Pick up- After Jan 101243.75Inv#076 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6696 | 20201115-9 | 53510502 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-11-15 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working with corduroy from C-106. | 5 | C093-C116 | Cook Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting669620201115-9L.O.A.1210 | Corbiere and Sons Contracting669620201115-9L.O.A.1210Inv#076 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6696 | 20201115-9 | 53510502 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5 | HR |  |  | 75 | 0 | 375 | 48.75 | 423.75 | 2020-11-15 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working with corduroy from C-106. | 5 | C093-C116 | Cook Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting669620201115-9Operator - Principle - After Jan 105375 | Corbiere and Sons Contracting669620201115-9Operator - Principle - After Jan 105375Inv#076 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 375 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6710 | 20201116-10 | 53510504 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10.5 | Dynamic | 103.84 | 0 |  |  | 1453.725 | 188.9843 | 1642.7093 | 2020-11-16 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock truck hauling gravel for C-062 and was on excavator loading. | 5 | C050-C069 | Antler Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting671020201116-10Excavator - 30 ton- After Jan 1010.51453.725 | Corbiere and Sons Contracting671020201116-10Excavator - 30 ton- After Jan 1010.51453.725Inv#076 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1453.725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6710 | 20201116-10 | 53510504 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10.5 | HR | 9.16 | 0 |  |  | 128.205 | 16.6667 | 144.8716 | 2020-11-16 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock truck hauling gravel for C-062 and was on excavator loading. | 5 | C050-C069 | Antler Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting671020201116-10Excavator Thumb - 30 - 50 ton- After Jan 1010.5128.205 | Corbiere and Sons Contracting671020201116-10Excavator Thumb - 30 - 50 ton- After Jan 1010.5128.205Inv#076 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 128.205 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6710 | 20201116-10 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-11-16 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock truck hauling gravel for C-062 and was on excavator loading. | 5 | C050-C069 | Antler Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting671020201116-10Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting671020201116-10Light Truck - Pick up- After Jan 101243.75Inv#076 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6710 | 20201116-10 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 10.5 | Dynamic | 103.54 | 0 |  |  | 1449.525 | 188.4383 | 1637.9633 | 2020-11-16 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock truck hauling gravel for C-062 and was on excavator loading. | 5 | C050-C069 | Antler Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting671020201116-10Rock Truck - 30 Ton- After Jan 1010.51449.525 | Corbiere and Sons Contracting671020201116-10Rock Truck - 30 Ton- After Jan 1010.51449.525Inv#076 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1449.525 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6710 | 20201116-10 | 53510504 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-11-16 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock truck hauling gravel for C-062 and was on excavator loading. | 5 | C050-C069 | Antler Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting671020201116-10L.O.A.2420 | Corbiere and Sons Contracting671020201116-10L.O.A.2420Inv#076 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6710 | 20201116-10 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-11-16 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock truck hauling gravel for C-062 and was on excavator loading. | 5 | C050-C069 | Antler Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting671020201116-10Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting671020201116-10Operator - Principle - After Jan 1011.5862.5Inv#076 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6710 | 20201116-10 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 11.5 | HR |  |  | 70 | 0 | 805 | 104.65 | 909.65 | 2020-11-16 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock truck hauling gravel for C-062 and was on excavator loading. | 5 | C050-C069 | Antler Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting671020201116-10Driver - AZ - After Jan 1011.5805 | Corbiere and Sons Contracting671020201116-10Driver - AZ - After Jan 1011.5805Inv#076 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 805 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6712 | 20201116-12 | 53510503 | Access | 0 | Skidder | 171 | 8.5 | HR | 128.25 | 0 |  |  | 1453.5 | 188.955 | 1642.455 | 2020-11-16 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 30m of corduroy put down near C-120 | 5 | C117-C124 | Mill Road | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting671220201116-12Skidder 8.51453.5 | Corbiere and Sons Contracting671220201116-12Skidder 8.51453.5Inv#076 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 1453.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6712 | 20201116-12 | 53510503 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 3 | Dynamic | 103.84 | 0 |  |  | 415.35 | 53.9955 | 469.3455 | 2020-11-16 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 30m of corduroy put down near C-120 | 5 | C117-C124 | Mill Road | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting671220201116-12Excavator - 30 ton- After Jan 103415.35 | Corbiere and Sons Contracting671220201116-12Excavator - 30 ton- After Jan 103415.35Inv#076 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 415.35 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6712 | 20201116-12 | 53510503 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 3 | HR | 9.16 | 0 |  |  | 36.63 | 4.7619 | 41.3919 | 2020-11-16 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 30m of corduroy put down near C-120 | 5 | C117-C124 | Mill Road | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting671220201116-12Excavator Thumb - 30 - 50 ton- After Jan 10336.63 | Corbiere and Sons Contracting671220201116-12Excavator Thumb - 30 - 50 ton- After Jan 10336.63Inv#076 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 36.63 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6712 | 20201116-12 | 53510503 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-11-16 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 30m of corduroy put down near C-120 | 5 | C117-C124 | Mill Road | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting671220201116-12Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting671220201116-12Light Truck - Pick up- After Jan 101243.75Inv#076 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6712 | 20201116-12 | 53510503 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-11-16 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 30m of corduroy put down near C-120 | 5 | C117-C124 | Mill Road | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting671220201116-12L.O.A.2420 | Corbiere and Sons Contracting671220201116-12L.O.A.2420Inv#076 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6712 | 20201116-12 | 53510503 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-11-16 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 30m of corduroy put down near C-120 | 5 | C117-C124 | Mill Road | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting671220201116-12Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting671220201116-12Operator - Principle - After Jan 1011.5862.5Inv#076 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6714 | 20201116-14 | 53530501 | Rig/Access Mats | 0 | Skidder | 171 | 6 | HR | 128.25 | 0 |  |  | 1026 | 133.38 | 1159.38 | 2020-11-16 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Rig/Access Mat Handling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Skidder mobing in mats for WC7600.01 | 5 | C076-C116 | Cook Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting671420201116-14Skidder 61026 | Corbiere and Sons Contracting671420201116-14Skidder 61026Inv#076 |  |  | WF5-WaterCrossing |  |  | 1 | 1026 | WC406 | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6714 | 20201116-14 | 53530501 | Rig/Access Mats | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-11-16 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Rig/Access Mat Handling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Skidder mobing in mats for WC7600.01 | 5 | C076-C116 | Cook Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting671420201116-14Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting671420201116-14Light Truck - Pick up- After Jan 101243.75Inv#076 |  |  | WF5-WaterCrossing |  |  | 1 | 243.75 | WC406 | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6714 | 20201116-14 | 53530501 | Rig/Access Mats | 0 | Foreman | 95 | 3 | HR |  |  | 95 | 0 | 285 | 37.05 | 322.05 | 2020-11-16 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Rig/Access Mat Handling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Skidder mobing in mats for WC7600.01 | 5 | C076-C116 | Cook Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting671420201116-14Foreman3285 | Corbiere and Sons Contracting671420201116-14Foreman3285Inv#076 |  |  | WF5-WaterCrossing |  |  | 1 | 285 | WC406 | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6714 | 20201116-14 | 53530501 | Rig/Access Mats | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-11-16 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Rig/Access Mat Handling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Skidder mobing in mats for WC7600.01 | 5 | C076-C116 | Cook Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting671420201116-14L.O.A.1210 | Corbiere and Sons Contracting671420201116-14L.O.A.1210Inv#076 |  |  | WF5-WaterCrossing |  |  | 1 | 210 | WC406 | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6714 | 20201116-14 | 53530501 | Rig/Access Mats | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 75 | 0 | 450 | 58.5 | 508.5 | 2020-11-16 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Rig/Access Mat Handling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Skidder mobing in mats for WC7600.01 | 5 | C076-C116 | Cook Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting671420201116-14Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting671420201116-14Operator - Principle - After Jan 106450Inv#076 |  |  | WF5-WaterCrossing |  |  | 1 | 450 | WC406 | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6715 | 20201116-15 | 53510512 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10.5 | Dynamic | 110.22 | 0 |  |  | 1543.08 | 200.6004 | 1743.6804 | 2020-11-16 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 460 Linkbelt doing road maintenance from C-093 - C-099 all day | 5 | C076-C116 | Cook Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting671520201116-15Excavator - 36 ton- After Jan 1010.51543.08 | Corbiere and Sons Contracting671520201116-15Excavator - 36 ton- After Jan 1010.51543.08Inv#076 | [5 empty] | 1 | 1543.08 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6715 | 20201116-15 | 53510512 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-11-16 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 460 Linkbelt doing road maintenance from C-093 - C-099 all day | 5 | C076-C116 | Cook Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting671520201116-15Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting671520201116-15Light Truck - Pick up- After Jan 101243.75Inv#076 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6715 | 20201116-15 | 53510512 | Access | 0 | Foreman | 95 | 3 | HR |  |  | 95 | 0 | 285 | 37.05 | 322.05 | 2020-11-16 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 460 Linkbelt doing road maintenance from C-093 - C-099 all day | 5 | C076-C116 | Cook Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting671520201116-15Foreman3285 | Corbiere and Sons Contracting671520201116-15Foreman3285Inv#076 | [5 empty] | 1 | 285 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6715 | 20201116-15 | 53510512 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-11-16 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 460 Linkbelt doing road maintenance from C-093 - C-099 all day | 5 | C076-C116 | Cook Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting671520201116-15L.O.A.1210 | Corbiere and Sons Contracting671520201116-15L.O.A.1210Inv#076 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6715 | 20201116-15 | 53510512 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-11-16 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 460 Linkbelt doing road maintenance from C-093 - C-099 all day | 5 | C076-C116 | Cook Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting671520201116-15Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting671520201116-15Operator - Principle - After Jan 1011.5862.5Inv#076 | [5 empty] | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6843 | 20201116-18 | 53510112 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 5 | Dynamic | 98.61 | 0 |  |  | 657.4 | 85.462 | 742.862 | 2020-11-16 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | DZ-05 trimmed up AU1 road | 1 | A001 | Lakeshore | 0 | 44159 |  | 50 | 44160 | [5 empty] | Wes Seminowich | 01 | Corbiere and Sons Contracting684320201116-18Dozer D6 or equal- After Jan 105657.4 | Corbiere and Sons Contracting684320201116-18Dozer D6 or equal- After Jan 105657.4Inv#081 | [5 empty] | 1 | 657.4 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6843 | 20201116-18 | 53510112 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-11-16 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | DZ-05 trimmed up AU1 road | 1 | A001 | Lakeshore | 0 | 44159 |  | 50 | 44160 | [5 empty] | Wes Seminowich | 01 | Corbiere and Sons Contracting684320201116-18Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting684320201116-18Light Truck - Pick up- After Jan 101243.75Inv#081 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6843 | 20201116-18 | 53510112 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5 | HR |  |  | 75 | 0 | 375 | 48.75 | 423.75 | 2020-11-16 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | DZ-05 trimmed up AU1 road | 1 | A001 | Lakeshore | 0 | 44159 |  | 50 | 44160 | [5 empty] | Wes Seminowich | 01 | Corbiere and Sons Contracting684320201116-18Operator - Principle - After Jan 105375 | Corbiere and Sons Contracting684320201116-18Operator - Principle - After Jan 105375Inv#081 | [5 empty] | 1 | 375 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6844 | 20201116-19 | 53520101 | Clearing | 0 | Feller Buncher | 240 | 5 | HR | 180 | 0 |  |  | 1200 | 156 | 1356 | 2020-11-16 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | FB-01 walked in and cleared trees on AU1 road | 1 | A001 | Lakeshore | 0 | 44159 |  | 50 | 44160 | [5 empty] | Wes Seminowich | 01 | Corbiere and Sons Contracting684420201116-19Feller Buncher51200 | Corbiere and Sons Contracting684420201116-19Feller Buncher51200Inv#081 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1200 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6844 | 20201116-19 | 53520101 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-11-16 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | FB-01 walked in and cleared trees on AU1 road | 1 | A001 | Lakeshore | 0 | 44159 |  | 50 | 44160 | [5 empty] | Wes Seminowich | 01 | Corbiere and Sons Contracting684420201116-19Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting684420201116-19Light Truck - Pick up- After Jan 102487.5Inv#081 |  |  | WF1-Merchantable Clearing |  |  | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6844 | 20201116-19 | 53520101 | Clearing | 0 | Foreman | 95 | 6 | HR |  |  | 95 | 0 | 570 | 74.1 | 644.1 | 2020-11-16 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | FB-01 walked in and cleared trees on AU1 road | 1 | A001 | Lakeshore | 0 | 44159 |  | 50 | 44160 | [5 empty] | Wes Seminowich | 01 | Corbiere and Sons Contracting684420201116-19Foreman6570 | Corbiere and Sons Contracting684420201116-19Foreman6570Inv#081 |  |  | WF1-Merchantable Clearing |  |  | 1 | 570 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6844 | 20201116-19 | 53520101 | Clearing | 0 | Operator - Principle - After Jan 10 | 75 | 5 | HR |  |  | 75 | 0 | 375 | 48.75 | 423.75 | 2020-11-16 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | FB-01 walked in and cleared trees on AU1 road | 1 | A001 | Lakeshore | 0 | 44159 |  | 50 | 44160 | [5 empty] | Wes Seminowich | 01 | Corbiere and Sons Contracting684420201116-19Operator - Principle - After Jan 105375 | Corbiere and Sons Contracting684420201116-19Operator - Principle - After Jan 105375Inv#081 |  |  | WF1-Merchantable Clearing |  |  | 1 | 375 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6708 | 20201116-8 | 53510511 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 8.5 | Dynamic | 98.61 | 0 |  |  | 1117.58 | 145.2854 | 1262.8654 | 2020-11-16 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer clearing snow | 5 | C031-C049 | Pays Plat River | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting670820201116-8Dozer D6 or equal- After Jan 108.51117.58 | Corbiere and Sons Contracting670820201116-8Dozer D6 or equal- After Jan 108.51117.58Inv#076 | [5 empty] | 1 | 1117.58 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6708 | 20201116-8 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-11-16 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer clearing snow | 5 | C031-C049 | Pays Plat River | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting670820201116-8Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting670820201116-8Light Truck - Pick up- After Jan 101243.75Inv#076 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6708 | 20201116-8 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-11-16 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer clearing snow | 5 | C031-C049 | Pays Plat River | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting670820201116-8L.O.A.1210 | Corbiere and Sons Contracting670820201116-8L.O.A.1210Inv#076 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6708 | 20201116-8 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 9.5 | HR |  |  | 75 | 0 | 712.5 | 92.625 | 805.125 | 2020-11-16 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer clearing snow | 5 | C031-C049 | Pays Plat River | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting670820201116-8Operator - Principle - After Jan 109.5712.5 | Corbiere and Sons Contracting670820201116-8Operator - Principle - After Jan 109.5712.5Inv#076 | [5 empty] | 1 | 712.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6728 | 20201117-12 | 53510504 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 3 | Dynamic | 103.84 | 0 |  |  | 415.35 | 53.9955 | 469.3455 | 2020-11-17 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Evan loaded rock trucks, Chris hauling gravel with rock truck, Dwayne raking gravel over corduroy with bucket. | 5 | C076-C116 | Cook Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting672820201117-12Excavator - 30 ton- After Jan 103415.35 | Corbiere and Sons Contracting672820201117-12Excavator - 30 ton- After Jan 103415.35Inv#076 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 415.35 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6728 | 20201117-12 | 53510504 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 6.5 | Dynamic | 110.22 | 0 |  |  | 955.24 | 124.1812 | 1079.4212 | 2020-11-17 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Evan loaded rock trucks, Chris hauling gravel with rock truck, Dwayne raking gravel over corduroy with bucket. | 5 | C076-C116 | Cook Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting672820201117-12Excavator - 36 ton- After Jan 106.5955.24 | Corbiere and Sons Contracting672820201117-12Excavator - 36 ton- After Jan 106.5955.24Inv#076 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 955.24 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6728 | 20201117-12 | 53510504 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 3 | HR | 9.16 | 0 |  |  | 36.63 | 4.7619 | 41.3919 | 2020-11-17 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Evan loaded rock trucks, Chris hauling gravel with rock truck, Dwayne raking gravel over corduroy with bucket. | 5 | C076-C116 | Cook Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting672820201117-12Excavator Thumb - 30 - 50 ton- After Jan 10336.63 | Corbiere and Sons Contracting672820201117-12Excavator Thumb - 30 - 50 ton- After Jan 10336.63Inv#076 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 36.63 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6728 | 20201117-12 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-11-17 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Evan loaded rock trucks, Chris hauling gravel with rock truck, Dwayne raking gravel over corduroy with bucket. | 5 | C076-C116 | Cook Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting672820201117-12Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting672820201117-12Light Truck - Pick up- After Jan 101243.75Inv#076 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6728 | 20201117-12 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 8 | Dynamic | 103.54 | 0 |  |  | 1104.4 | 143.572 | 1247.972 | 2020-11-17 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Evan loaded rock trucks, Chris hauling gravel with rock truck, Dwayne raking gravel over corduroy with bucket. | 5 | C076-C116 | Cook Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting672820201117-12Rock Truck - 30 Ton- After Jan 1081104.4 | Corbiere and Sons Contracting672820201117-12Rock Truck - 30 Ton- After Jan 1081104.4Inv#076 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1104.4 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6728 | 20201117-12 | 53510504 | Access | 0 | Foreman | 95 | 3 | HR |  |  | 95 | 0 | 285 | 37.05 | 322.05 | 2020-11-17 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Evan loaded rock trucks, Chris hauling gravel with rock truck, Dwayne raking gravel over corduroy with bucket. | 5 | C076-C116 | Cook Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting672820201117-12Foreman3285 | Corbiere and Sons Contracting672820201117-12Foreman3285Inv#076 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 285 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6728 | 20201117-12 | 53510504 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-11-17 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Evan loaded rock trucks, Chris hauling gravel with rock truck, Dwayne raking gravel over corduroy with bucket. | 5 | C076-C116 | Cook Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting672820201117-12L.O.A.2420 | Corbiere and Sons Contracting672820201117-12L.O.A.2420Inv#076 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6728 | 20201117-12 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 10.5 | HR |  |  | 75 | 0 | 787.5 | 102.375 | 889.875 | 2020-11-17 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Evan loaded rock trucks, Chris hauling gravel with rock truck, Dwayne raking gravel over corduroy with bucket. | 5 | C076-C116 | Cook Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting672820201117-12Operator - Principle - After Jan 1010.5787.5 | Corbiere and Sons Contracting672820201117-12Operator - Principle - After Jan 1010.5787.5Inv#076 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 787.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6728 | 20201117-12 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 8.5 | HR |  |  | 70 | 0 | 595 | 77.35 | 672.35 | 2020-11-17 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Evan loaded rock trucks, Chris hauling gravel with rock truck, Dwayne raking gravel over corduroy with bucket. | 5 | C076-C116 | Cook Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting672820201117-12Driver - AZ - After Jan 108.5595 | Corbiere and Sons Contracting672820201117-12Driver - AZ - After Jan 108.5595Inv#076 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 595 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6729 | 20201117-13 | 53510512 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10.5 | Dynamic | 98.61 | 0 |  |  | 1380.54 | 179.4702 | 1560.0102 | 2020-11-17 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator doing road miantenance from C-100 all dayDozer doing road maintenance from C-095 - C102 all day | 5 | C093-C116 | Cook Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting672920201117-13Dozer D6 or equal- After Jan 1010.51380.54 | Corbiere and Sons Contracting672920201117-13Dozer D6 or equal- After Jan 1010.51380.54Inv#076 | [5 empty] | 1 | 1380.54 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6729 | 20201117-13 | 53510512 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10.5 | Dynamic | 103.84 | 0 |  |  | 1453.725 | 188.9843 | 1642.7093 | 2020-11-17 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator doing road miantenance from C-100 all dayDozer doing road maintenance from C-095 - C102 all day | 5 | C093-C116 | Cook Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting672920201117-13Excavator - 30 ton- After Jan 1010.51453.725 | Corbiere and Sons Contracting672920201117-13Excavator - 30 ton- After Jan 1010.51453.725Inv#076 | [5 empty] | 1 | 1453.725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6729 | 20201117-13 | 53510512 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10.5 | HR | 9.16 | 0 |  |  | 128.205 | 16.6667 | 144.8716 | 2020-11-17 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator doing road miantenance from C-100 all dayDozer doing road maintenance from C-095 - C102 all day | 5 | C093-C116 | Cook Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting672920201117-13Excavator Thumb - 30 - 50 ton- After Jan 1010.5128.205 | Corbiere and Sons Contracting672920201117-13Excavator Thumb - 30 - 50 ton- After Jan 1010.5128.205Inv#076 | [5 empty] | 1 | 128.205 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6729 | 20201117-13 | 53510512 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-11-17 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator doing road miantenance from C-100 all dayDozer doing road maintenance from C-095 - C102 all day | 5 | C093-C116 | Cook Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting672920201117-13Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting672920201117-13Light Truck - Pick up- After Jan 101243.75Inv#076 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6729 | 20201117-13 | 53510512 | Access | 0 | Foreman | 95 | 3 | HR |  |  | 95 | 0 | 285 | 37.05 | 322.05 | 2020-11-17 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator doing road miantenance from C-100 all dayDozer doing road maintenance from C-095 - C102 all day | 5 | C093-C116 | Cook Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting672920201117-13Foreman3285 | Corbiere and Sons Contracting672920201117-13Foreman3285Inv#076 | [5 empty] | 1 | 285 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6729 | 20201117-13 | 53510512 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-11-17 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator doing road miantenance from C-100 all dayDozer doing road maintenance from C-095 - C102 all day | 5 | C093-C116 | Cook Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting672920201117-13L.O.A.2420 | Corbiere and Sons Contracting672920201117-13L.O.A.2420Inv#076 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6729 | 20201117-13 | 53510512 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 23 | HR |  |  | 75 | 0 | 1725 | 224.25 | 1949.25 | 2020-11-17 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator doing road miantenance from C-100 all dayDozer doing road maintenance from C-095 - C102 all day | 5 | C093-C116 | Cook Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting672920201117-13Operator - Principle - After Jan 10231725 | Corbiere and Sons Contracting672920201117-13Operator - Principle - After Jan 10231725Inv#076 | [5 empty] | 1 | 1725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6730 | 20201117-14 | 53510511 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 6 | Dynamic | 98.61 | 0 |  |  | 788.88 | 102.5544 | 891.4344 | 2020-11-17 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer pulling tires and plowing to C-049 | 5 | C036-C049 | Pays Plat River | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting673020201117-14Dozer D6 or equal- After Jan 106788.88 | Corbiere and Sons Contracting673020201117-14Dozer D6 or equal- After Jan 106788.88Inv#076 | [5 empty] | 1 | 788.88 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6730 | 20201117-14 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-11-17 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer pulling tires and plowing to C-049 | 5 | C036-C049 | Pays Plat River | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting673020201117-14L.O.A.1210 | Corbiere and Sons Contracting673020201117-14L.O.A.1210Inv#076 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6730 | 20201117-14 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 75 | 0 | 450 | 58.5 | 508.5 | 2020-11-17 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer pulling tires and plowing to C-049 | 5 | C036-C049 | Pays Plat River | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting673020201117-14Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting673020201117-14Operator - Principle - After Jan 106450Inv#076 | [5 empty] | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6850 | 20201117-18 | 53520101 | Clearing | 0 | Feller Buncher | 240 | 10 | HR | 180 | 0 |  |  | 2400 | 312 | 2712 | 2020-11-17 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | FB-01 and SK-01 cleared ROW | 1 | A001 | Lakeshore | 0 | 44159 |  | 50 | 44160 | [5 empty] | Wes Seminowich | 01 | Corbiere and Sons Contracting685020201117-18Feller Buncher102400 | Corbiere and Sons Contracting685020201117-18Feller Buncher102400Inv#081 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2400 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6850 | 20201117-18 | 53520101 | Clearing | 0 | Skidder | 171 | 7 | HR | 128.25 | 0 |  |  | 1197 | 155.61 | 1352.61 | 2020-11-17 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | FB-01 and SK-01 cleared ROW | 1 | A001 | Lakeshore | 0 | 44159 |  | 50 | 44160 | [5 empty] | Wes Seminowich | 01 | Corbiere and Sons Contracting685020201117-18Skidder 71197 | Corbiere and Sons Contracting685020201117-18Skidder 71197Inv#081 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1197 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6850 | 20201117-18 | 53520101 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2020-11-17 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | FB-01 and SK-01 cleared ROW | 1 | A001 | Lakeshore | 0 | 44159 |  | 50 | 44160 | [5 empty] | Wes Seminowich | 01 | Corbiere and Sons Contracting685020201117-18Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting685020201117-18Light Truck - Pick up- After Jan 103731.25Inv#081 |  |  | WF1-Merchantable Clearing |  |  | 1 | 731.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6850 | 20201117-18 | 53520101 | Clearing | 0 | Foreman | 95 | 6 | HR |  |  | 95 | 0 | 570 | 74.1 | 644.1 | 2020-11-17 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | FB-01 and SK-01 cleared ROW | 1 | A001 | Lakeshore | 0 | 44159 |  | 50 | 44160 | [5 empty] | Wes Seminowich | 01 | Corbiere and Sons Contracting685020201117-18Foreman6570 | Corbiere and Sons Contracting685020201117-18Foreman6570Inv#081 |  |  | WF1-Merchantable Clearing |  |  | 1 | 570 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6850 | 20201117-18 | 53520101 | Clearing | 0 | Operator - Principle - After Jan 10 | 75 | 18 | HR |  |  | 75 | 0 | 1350 | 175.5 | 1525.5 | 2020-11-17 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | FB-01 and SK-01 cleared ROW | 1 | A001 | Lakeshore | 0 | 44159 |  | 50 | 44160 | [5 empty] | Wes Seminowich | 01 | Corbiere and Sons Contracting685020201117-18Operator - Principle - After Jan 10181350 | Corbiere and Sons Contracting685020201117-18Operator - Principle - After Jan 10181350Inv#081 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1350 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6743 | 20201118-12 | 53510502 | Access | 0 | Skidder | 171 | 5 | HR | 128.25 | 0 |  |  | 855 | 111.15 | 966.15 | 2020-11-18 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator putting down corduroy to establish bank from C-108, Ghislain spent 1/2 day bringing wood to Dwayne to establish bank at C-108, rock truck hauling | 5 | C076-C116 | Cook Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting674320201118-12Skidder 5855 | Corbiere and Sons Contracting674320201118-12Skidder 5855Inv#076 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 855 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6743 | 20201118-12 | 53510502 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 5.5 | Dynamic | 103.84 | 0 |  |  | 761.475 | 98.9917 | 860.4668 | 2020-11-18 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator putting down corduroy to establish bank from C-108, Ghislain spent 1/2 day bringing wood to Dwayne to establish bank at C-108, rock truck hauling | 5 | C076-C116 | Cook Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting674320201118-12Excavator - 30 ton- After Jan 105.5761.475 | Corbiere and Sons Contracting674320201118-12Excavator - 30 ton- After Jan 105.5761.475Inv#076 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 761.475 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6743 | 20201118-12 | 53510502 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 5.5 | HR | 9.16 | 0 |  |  | 67.155 | 8.7302 | 75.8851 | 2020-11-18 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator putting down corduroy to establish bank from C-108, Ghislain spent 1/2 day bringing wood to Dwayne to establish bank at C-108, rock truck hauling | 5 | C076-C116 | Cook Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting674320201118-12Excavator Thumb - 30 - 50 ton- After Jan 105.567.155 | Corbiere and Sons Contracting674320201118-12Excavator Thumb - 30 - 50 ton- After Jan 105.567.155Inv#076 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 67.155 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6743 | 20201118-12 | 53510502 | Access | 0 | ATV - Side by Side w/ roll bar- After Jan 10 | 18.45 | 5 | HR | 13.84 | 0 |  |  | 92.25 | 11.9925 | 104.2425 | 2020-11-18 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator putting down corduroy to establish bank from C-108, Ghislain spent 1/2 day bringing wood to Dwayne to establish bank at C-108, rock truck hauling | 5 | C076-C116 | Cook Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting674320201118-12ATV - Side by Side w/ roll bar- After Jan 10592.25 | Corbiere and Sons Contracting674320201118-12ATV - Side by Side w/ roll bar- After Jan 10592.25Inv#076 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 92.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6743 | 20201118-12 | 53510502 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-11-18 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator putting down corduroy to establish bank from C-108, Ghislain spent 1/2 day bringing wood to Dwayne to establish bank at C-108, rock truck hauling | 5 | C076-C116 | Cook Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting674320201118-12Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting674320201118-12Light Truck - Pick up- After Jan 101243.75Inv#076 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6743 | 20201118-12 | 53510502 | Access | 0 | Foreman | 95 | 3 | HR |  |  | 95 | 0 | 285 | 37.05 | 322.05 | 2020-11-18 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator putting down corduroy to establish bank from C-108, Ghislain spent 1/2 day bringing wood to Dwayne to establish bank at C-108, rock truck hauling | 5 | C076-C116 | Cook Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting674320201118-12Foreman3285 | Corbiere and Sons Contracting674320201118-12Foreman3285Inv#076 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 285 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6743 | 20201118-12 | 53510502 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-11-18 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator putting down corduroy to establish bank from C-108, Ghislain spent 1/2 day bringing wood to Dwayne to establish bank at C-108, rock truck hauling | 5 | C076-C116 | Cook Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting674320201118-12L.O.A.2420 | Corbiere and Sons Contracting674320201118-12L.O.A.2420Inv#076 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6743 | 20201118-12 | 53510502 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2020-11-18 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator putting down corduroy to establish bank from C-108, Ghislain spent 1/2 day bringing wood to Dwayne to establish bank at C-108, rock truck hauling | 5 | C076-C116 | Cook Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting674320201118-12Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting674320201118-12Operator - Principle - After Jan 1011825Inv#076 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6744 | 20201118-13 | 53510512 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 5.5 | Dynamic | 98.61 | 0 |  |  | 723.14 | 94.0082 | 817.1482 | 2020-11-18 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance from C-094 to C-106 | 5 | C076-C116 | Cook Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting674420201118-13Dozer D6 or equal- After Jan 105.5723.14 | Corbiere and Sons Contracting674420201118-13Dozer D6 or equal- After Jan 105.5723.14Inv#076 | [5 empty] | 1 | 723.14 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6744 | 20201118-13 | 53510512 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 5.5 | Dynamic | 103.84 | 0 |  |  | 761.475 | 98.9917 | 860.4668 | 2020-11-18 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance from C-094 to C-106 | 5 | C076-C116 | Cook Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting674420201118-13Excavator - 30 ton- After Jan 105.5761.475 | Corbiere and Sons Contracting674420201118-13Excavator - 30 ton- After Jan 105.5761.475Inv#076 | [5 empty] | 1 | 761.475 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6744 | 20201118-13 | 53510512 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10.5 | Dynamic | 110.22 | 0 |  |  | 1543.08 | 200.6004 | 1743.6804 | 2020-11-18 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance from C-094 to C-106 | 5 | C076-C116 | Cook Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting674420201118-13Excavator - 36 ton- After Jan 1010.51543.08 | Corbiere and Sons Contracting674420201118-13Excavator - 36 ton- After Jan 1010.51543.08Inv#076 | [5 empty] | 1 | 1543.08 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6744 | 20201118-13 | 53510512 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 5.5 | HR | 9.16 | 0 |  |  | 67.155 | 8.7302 | 75.8851 | 2020-11-18 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance from C-094 to C-106 | 5 | C076-C116 | Cook Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting674420201118-13Excavator Thumb - 30 - 50 ton- After Jan 105.567.155 | Corbiere and Sons Contracting674420201118-13Excavator Thumb - 30 - 50 ton- After Jan 105.567.155Inv#076 | [5 empty] | 1 | 67.155 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6744 | 20201118-13 | 53510512 | Access | 0 | ATV - Side by Side w/ roll bar- After Jan 10 | 18.45 | 5 | HR | 13.84 | 0 |  |  | 92.25 | 11.9925 | 104.2425 | 2020-11-18 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance from C-094 to C-106 | 5 | C076-C116 | Cook Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting674420201118-13ATV - Side by Side w/ roll bar- After Jan 10592.25 | Corbiere and Sons Contracting674420201118-13ATV - Side by Side w/ roll bar- After Jan 10592.25Inv#076 | [5 empty] | 1 | 92.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6744 | 20201118-13 | 53510512 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-11-18 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance from C-094 to C-106 | 5 | C076-C116 | Cook Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting674420201118-13Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting674420201118-13Light Truck - Pick up- After Jan 101243.75Inv#076 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6744 | 20201118-13 | 53510512 | Access | 0 | Foreman | 95 | 4 | HR |  |  | 95 | 0 | 380 | 49.4 | 429.4 | 2020-11-18 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance from C-094 to C-106 | 5 | C076-C116 | Cook Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting674420201118-13Foreman4380 | Corbiere and Sons Contracting674420201118-13Foreman4380Inv#076 | [5 empty] | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6744 | 20201118-13 | 53510512 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2020-11-18 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance from C-094 to C-106 | 5 | C076-C116 | Cook Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting674420201118-13L.O.A.4840 | Corbiere and Sons Contracting674420201118-13L.O.A.4840Inv#076 | [5 empty] | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6744 | 20201118-13 | 53510512 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 23.5 | HR |  |  | 75 | 0 | 1762.5 | 229.125 | 1991.625 | 2020-11-18 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance from C-094 to C-106 | 5 | C076-C116 | Cook Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting674420201118-13Operator - Principle - After Jan 1023.51762.5 | Corbiere and Sons Contracting674420201118-13Operator - Principle - After Jan 1023.51762.5Inv#076 | [5 empty] | 1 | 1762.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6745 | 20201118-14 | 53510504 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 5 | Dynamic | 98.61 | 0 |  |  | 657.4 | 85.462 | 742.862 | 2020-11-18 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Reg loading rock truck, Chris on rock truck, Tim spreading gravel | 5 | C076-C116 | Cook Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting674520201118-14Dozer D6 or equal- After Jan 105657.4 | Corbiere and Sons Contracting674520201118-14Dozer D6 or equal- After Jan 105657.4Inv#076 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 657.4 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6745 | 20201118-14 | 53510504 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 5 | Dynamic | 103.84 | 0 |  |  | 692.25 | 89.9925 | 782.2425 | 2020-11-18 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Reg loading rock truck, Chris on rock truck, Tim spreading gravel | 5 | C076-C116 | Cook Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting674520201118-14Excavator - 30 ton- After Jan 105692.25 | Corbiere and Sons Contracting674520201118-14Excavator - 30 ton- After Jan 105692.25Inv#076 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 692.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6745 | 20201118-14 | 53510504 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 5 | HR | 9.16 | 0 |  |  | 61.05 | 7.9365 | 68.9865 | 2020-11-18 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Reg loading rock truck, Chris on rock truck, Tim spreading gravel | 5 | C076-C116 | Cook Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting674520201118-14Excavator Thumb - 30 - 50 ton- After Jan 10561.05 | Corbiere and Sons Contracting674520201118-14Excavator Thumb - 30 - 50 ton- After Jan 10561.05Inv#076 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 61.05 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6745 | 20201118-14 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-11-18 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Reg loading rock truck, Chris on rock truck, Tim spreading gravel | 5 | C076-C116 | Cook Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting674520201118-14Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting674520201118-14Light Truck - Pick up- After Jan 102487.5Inv#076 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6745 | 20201118-14 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 6.5 | Dynamic | 103.54 | 0 |  |  | 897.325 | 116.6522 | 1013.9773 | 2020-11-18 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Reg loading rock truck, Chris on rock truck, Tim spreading gravel | 5 | C076-C116 | Cook Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting674520201118-14Rock Truck - 30 Ton- After Jan 106.5897.325 | Corbiere and Sons Contracting674520201118-14Rock Truck - 30 Ton- After Jan 106.5897.325Inv#076 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 897.325 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6745 | 20201118-14 | 53510504 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-11-18 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Reg loading rock truck, Chris on rock truck, Tim spreading gravel | 5 | C076-C116 | Cook Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting674520201118-14L.O.A.1210 | Corbiere and Sons Contracting674520201118-14L.O.A.1210Inv#076 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6745 | 20201118-14 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2020-11-18 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Reg loading rock truck, Chris on rock truck, Tim spreading gravel | 5 | C076-C116 | Cook Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting674520201118-14Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting674520201118-14Operator - Principle - After Jan 1011825Inv#076 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6745 | 20201118-14 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 7.5 | HR |  |  | 70 | 0 | 525 | 68.25 | 593.25 | 2020-11-18 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Reg loading rock truck, Chris on rock truck, Tim spreading gravel | 5 | C076-C116 | Cook Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting674520201118-14Driver - AZ - After Jan 107.5525 | Corbiere and Sons Contracting674520201118-14Driver - AZ - After Jan 107.5525Inv#076 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 525 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6856 | 20201118-17 | 53520101 | Clearing | 0 | Feller Buncher | 240 | 9 | HR | 180 | 0 |  |  | 2160 | 280.8 | 2440.8 | 2020-11-18 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | FB-01 and SK-01 walked in and cleaned ROW | 1 | Highway 17 to A-017 | MacGregor | 0 | 44159 |  | 50 | 44160 | [5 empty] | Wes Seminowich | 01 | Corbiere and Sons Contracting685620201118-17Feller Buncher92160 | Corbiere and Sons Contracting685620201118-17Feller Buncher92160Inv#081 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2160 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6856 | 20201118-17 | 53520101 | Clearing | 0 | Skidder | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2020-11-18 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | FB-01 and SK-01 walked in and cleaned ROW | 1 | Highway 17 to A-017 | MacGregor | 0 | 44159 |  | 50 | 44160 | [5 empty] | Wes Seminowich | 01 | Corbiere and Sons Contracting685620201118-17Skidder 91539 | Corbiere and Sons Contracting685620201118-17Skidder 91539Inv#081 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6856 | 20201118-17 | 53520101 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2020-11-18 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | FB-01 and SK-01 walked in and cleaned ROW | 1 | Highway 17 to A-017 | MacGregor | 0 | 44159 |  | 50 | 44160 | [5 empty] | Wes Seminowich | 01 | Corbiere and Sons Contracting685620201118-17Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting685620201118-17Light Truck - Pick up- After Jan 103731.25Inv#081 |  |  | WF1-Merchantable Clearing |  |  | 1 | 731.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6856 | 20201118-17 | 53520101 | Clearing | 0 | Foreman | 95 | 6 | HR |  |  | 95 | 0 | 570 | 74.1 | 644.1 | 2020-11-18 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | FB-01 and SK-01 walked in and cleaned ROW | 1 | Highway 17 to A-017 | MacGregor | 0 | 44159 |  | 50 | 44160 | [5 empty] | Wes Seminowich | 01 | Corbiere and Sons Contracting685620201118-17Foreman6570 | Corbiere and Sons Contracting685620201118-17Foreman6570Inv#081 |  |  | WF1-Merchantable Clearing |  |  | 1 | 570 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6856 | 20201118-17 | 53520101 | Clearing | 0 | Operator - Principle - After Jan 10 | 75 | 22 | HR |  |  | 75 | 0 | 1650 | 214.5 | 1864.5 | 2020-11-18 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Merchantable Clearing |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | FB-01 and SK-01 walked in and cleaned ROW | 1 | Highway 17 to A-017 | MacGregor | 0 | 44159 |  | 50 | 44160 | [5 empty] | Wes Seminowich | 01 | Corbiere and Sons Contracting685620201118-17Operator - Principle - After Jan 10221650 | Corbiere and Sons Contracting685620201118-17Operator - Principle - After Jan 10221650Inv#081 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1650 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6862 | 20201118-23 | 53510511 | Access | 0 | 3rd Party Charges | 1 | 800.4 | unit |  |  |  |  | 800.4 | 104.052 | 904.452 | 2020-11-18 | 1 | Inv#081 | 44173 | 128 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 15 | Approved | ROW INTERNAL - Sand for Road Maintenance - 3rd Party | 9015 | Sand used for winter access maintenance on Cooks and Antler Lake Roads. | 5 | C076-C116 | Cook Lake | 0 | 44159 |  | 50 | 44160 | 0154 | Loaded and Delivered Sand to Terrace Bay |  |  |  | Wes Seminowich | 05 | Corbiere and Sons Contracting686220201118-233rd Party Charges800.4800.4 | Corbiere and Sons Contracting686220201118-233rd Party Charges800.4800.4Inv#081 | [5 empty] | 1 | 800.4 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6736 | 20201118-5 | 53520104 | Clearing | 0 | Chainsaw and consumables- After Jan 10 | 60 | 3 | unit/man/day | 0 | 0 |  |  | 180 | 23.4 | 203.4 | 2020-11-18 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfallers working from A-001 | 1 | A002-A010 | MacGregor - West | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 01 | Corbiere and Sons Contracting673620201118-5Chainsaw and consumables- After Jan 103180 | Corbiere and Sons Contracting673620201118-5Chainsaw and consumables- After Jan 103180Inv#076 |  |  | WF1-Handfalling |  |  | 1 | 180 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6736 | 20201118-5 | 53520104 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-11-18 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfallers working from A-001 | 1 | A002-A010 | MacGregor - West | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 01 | Corbiere and Sons Contracting673620201118-5Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting673620201118-5Light Truck - Pick up- After Jan 102487.5Inv#076 |  |  | WF1-Handfalling |  |  | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6736 | 20201118-5 | 53520104 | Clearing | 0 | Foreman | 95 | 6 | HR |  |  | 95 | 0 | 570 | 74.1 | 644.1 | 2020-11-18 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfallers working from A-001 | 1 | A002-A010 | MacGregor - West | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 01 | Corbiere and Sons Contracting673620201118-5Foreman6570 | Corbiere and Sons Contracting673620201118-5Foreman6570Inv#076 |  |  | WF1-Handfalling |  |  | 1 | 570 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6736 | 20201118-5 | 53520104 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-11-18 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfallers working from A-001 | 1 | A002-A010 | MacGregor - West | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 01 | Corbiere and Sons Contracting673620201118-5L.O.A.2420 | Corbiere and Sons Contracting673620201118-5L.O.A.2420Inv#076 |  |  | WF1-Handfalling |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6736 | 20201118-5 | 53520104 | Clearing | 0 | Labourer - Specialized - After Jan 10 | 70 | 33 | HR |  |  | 70 | 0 | 2310 | 300.3 | 2610.3 | 2020-11-18 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Handfallers working from A-001 | 1 | A002-A010 | MacGregor - West | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 01 | Corbiere and Sons Contracting673620201118-5Labourer - Specialized - After Jan 10332310 | Corbiere and Sons Contracting673620201118-5Labourer - Specialized - After Jan 10332310Inv#076 |  |  | WF1-Handfalling |  |  | 1 | 2310 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6739 | 20201118-8 | 53560503 | Water Crossings | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 1 | Dynamic | 98.61 | 0 |  |  | 131.48 | 17.0924 | 148.5724 | 2020-11-18 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Culvert Install |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator working on install of WC7671, Rock truck brought in 2 loads of gravel for capping of mats, Dozer putting gravel around mats. Labourers cutting and placing geo for WC7674 and rigging up mats | 5 | C117-C124 | Mill Road South | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting673920201118-8Dozer D6 or equal- After Jan 101131.48 | Corbiere and Sons Contracting673920201118-8Dozer D6 or equal- After Jan 101131.48Inv#076 |  |  | WF5-WaterCrossing |  |  | 1 | 131.48 | WC412 | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6739 | 20201118-8 | 53560503 | Water Crossings | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 4 | Dynamic | 103.84 | 0 |  |  | 553.8 | 71.994 | 625.794 | 2020-11-18 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Culvert Install |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator working on install of WC7671, Rock truck brought in 2 loads of gravel for capping of mats, Dozer putting gravel around mats. Labourers cutting and placing geo for WC7674 and rigging up mats | 5 | C117-C124 | Mill Road South | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting673920201118-8Excavator - 30 ton- After Jan 104553.8 | Corbiere and Sons Contracting673920201118-8Excavator - 30 ton- After Jan 104553.8Inv#076 |  |  | WF5-WaterCrossing |  |  | 1 | 553.8 | WC412 | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6739 | 20201118-8 | 53560503 | Water Crossings | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-11-18 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Culvert Install |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator working on install of WC7671, Rock truck brought in 2 loads of gravel for capping of mats, Dozer putting gravel around mats. Labourers cutting and placing geo for WC7674 and rigging up mats | 5 | C117-C124 | Mill Road South | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting673920201118-8Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting673920201118-8Light Truck - Pick up- After Jan 101243.75Inv#076 |  |  | WF5-WaterCrossing |  |  | 1 | 243.75 | WC412 | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6739 | 20201118-8 | 53560503 | Water Crossings | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 3 | Dynamic | 103.54 | 0 |  |  | 414.15 | 53.8395 | 467.9895 | 2020-11-18 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Culvert Install |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator working on install of WC7671, Rock truck brought in 2 loads of gravel for capping of mats, Dozer putting gravel around mats. Labourers cutting and placing geo for WC7674 and rigging up mats | 5 | C117-C124 | Mill Road South | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting673920201118-8Rock Truck - 30 Ton- After Jan 103414.15 | Corbiere and Sons Contracting673920201118-8Rock Truck - 30 Ton- After Jan 103414.15Inv#076 |  |  | WF5-WaterCrossing |  |  | 1 | 414.15 | WC412 | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6739 | 20201118-8 | 53560503 | Water Crossings | 0 | Foreman | 95 | 3 | HR |  |  | 95 | 0 | 285 | 37.05 | 322.05 | 2020-11-18 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Culvert Install |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator working on install of WC7671, Rock truck brought in 2 loads of gravel for capping of mats, Dozer putting gravel around mats. Labourers cutting and placing geo for WC7674 and rigging up mats | 5 | C117-C124 | Mill Road South | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting673920201118-8Foreman3285 | Corbiere and Sons Contracting673920201118-8Foreman3285Inv#076 |  |  | WF5-WaterCrossing |  |  | 1 | 285 | WC412 | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6739 | 20201118-8 | 53560503 | Water Crossings | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2020-11-18 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Culvert Install |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator working on install of WC7671, Rock truck brought in 2 loads of gravel for capping of mats, Dozer putting gravel around mats. Labourers cutting and placing geo for WC7674 and rigging up mats | 5 | C117-C124 | Mill Road South | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting673920201118-8L.O.A.3630 | Corbiere and Sons Contracting673920201118-8L.O.A.3630Inv#076 |  |  | WF5-WaterCrossing |  |  | 1 | 630 | WC412 | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6739 | 20201118-8 | 53560503 | Water Crossings | 0 | Operator - Principle - After Jan 10 | 75 | 5 | HR |  |  | 75 | 0 | 375 | 48.75 | 423.75 | 2020-11-18 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Culvert Install |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator working on install of WC7671, Rock truck brought in 2 loads of gravel for capping of mats, Dozer putting gravel around mats. Labourers cutting and placing geo for WC7674 and rigging up mats | 5 | C117-C124 | Mill Road South | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting673920201118-8Operator - Principle - After Jan 105375 | Corbiere and Sons Contracting673920201118-8Operator - Principle - After Jan 105375Inv#076 |  |  | WF5-WaterCrossing |  |  | 1 | 375 | WC412 | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6739 | 20201118-8 | 53560503 | Water Crossings | 0 | Driver - AZ - After Jan 10 | 70 | 3 | HR |  |  | 70 | 0 | 210 | 27.3 | 237.3 | 2020-11-18 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Culvert Install |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator working on install of WC7671, Rock truck brought in 2 loads of gravel for capping of mats, Dozer putting gravel around mats. Labourers cutting and placing geo for WC7674 and rigging up mats | 5 | C117-C124 | Mill Road South | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting673920201118-8Driver - AZ - After Jan 103210 | Corbiere and Sons Contracting673920201118-8Driver - AZ - After Jan 103210Inv#076 |  |  | WF5-WaterCrossing |  |  | 1 | 210 | WC412 | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6739 | 20201118-8 | 53560503 | Water Crossings | 0 | Labourer - General - After Jan 10 | 60 | 8 | HR |  |  | 60 | 0 | 480 | 62.4 | 542.4 | 2020-11-18 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Culvert Install |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator working on install of WC7671, Rock truck brought in 2 loads of gravel for capping of mats, Dozer putting gravel around mats. Labourers cutting and placing geo for WC7674 and rigging up mats | 5 | C117-C124 | Mill Road South | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting673920201118-8Labourer - General - After Jan 108480 | Corbiere and Sons Contracting673920201118-8Labourer - General - After Jan 108480Inv#076 |  |  | WF5-WaterCrossing |  |  | 1 | 480 | WC412 | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6740 | 20201118-9 | 53510504 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 6 | Dynamic | 98.61 | 0 |  |  | 788.88 | 102.5544 | 891.4344 | 2020-11-18 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loaded rock truck for capping, rock truck hauled gravel, dozer spread gravel | 5 | C117-C124 | Mill Road South | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting674020201118-9Dozer D6 or equal- After Jan 106788.88 | Corbiere and Sons Contracting674020201118-9Dozer D6 or equal- After Jan 106788.88Inv#076 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 788.88 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6740 | 20201118-9 | 53510504 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 6 | Dynamic | 103.84 | 0 |  |  | 830.7 | 107.991 | 938.691 | 2020-11-18 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loaded rock truck for capping, rock truck hauled gravel, dozer spread gravel | 5 | C117-C124 | Mill Road South | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting674020201118-9Excavator - 30 ton- After Jan 106830.7 | Corbiere and Sons Contracting674020201118-9Excavator - 30 ton- After Jan 106830.7Inv#076 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 830.7 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6740 | 20201118-9 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-11-18 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loaded rock truck for capping, rock truck hauled gravel, dozer spread gravel | 5 | C117-C124 | Mill Road South | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting674020201118-9Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting674020201118-9Light Truck - Pick up- After Jan 102487.5Inv#076 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6740 | 20201118-9 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 7 | Dynamic | 103.54 | 0 |  |  | 966.35 | 125.6255 | 1091.9755 | 2020-11-18 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loaded rock truck for capping, rock truck hauled gravel, dozer spread gravel | 5 | C117-C124 | Mill Road South | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting674020201118-9Rock Truck - 30 Ton- After Jan 107966.35 | Corbiere and Sons Contracting674020201118-9Rock Truck - 30 Ton- After Jan 107966.35Inv#076 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 966.35 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6740 | 20201118-9 | 53510504 | Access | 0 | Foreman | 95 | 2 | HR |  |  | 95 | 0 | 190 | 24.7 | 214.7 | 2020-11-18 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loaded rock truck for capping, rock truck hauled gravel, dozer spread gravel | 5 | C117-C124 | Mill Road South | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting674020201118-9Foreman2190 | Corbiere and Sons Contracting674020201118-9Foreman2190Inv#076 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 190 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6740 | 20201118-9 | 53510504 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2020-11-18 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loaded rock truck for capping, rock truck hauled gravel, dozer spread gravel | 5 | C117-C124 | Mill Road South | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting674020201118-9L.O.A.3630 | Corbiere and Sons Contracting674020201118-9L.O.A.3630Inv#076 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6740 | 20201118-9 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 13 | HR |  |  | 75 | 0 | 975 | 126.75 | 1101.75 | 2020-11-18 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loaded rock truck for capping, rock truck hauled gravel, dozer spread gravel | 5 | C117-C124 | Mill Road South | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting674020201118-9Operator - Principle - After Jan 1013975 | Corbiere and Sons Contracting674020201118-9Operator - Principle - After Jan 1013975Inv#076 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 975 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6740 | 20201118-9 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 7.5 | HR |  |  | 70 | 0 | 525 | 68.25 | 593.25 | 2020-11-18 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loaded rock truck for capping, rock truck hauled gravel, dozer spread gravel | 5 | C117-C124 | Mill Road South | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting674020201118-9Driver - AZ - After Jan 107.5525 | Corbiere and Sons Contracting674020201118-9Driver - AZ - After Jan 107.5525Inv#076 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 525 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6755 | 20201119-10 | 53510511 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10 | Dynamic | 103.84 | 0 |  |  | 1384.5 | 179.985 | 1564.485 | 2020-11-19 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jesse on excavator doing winter access maintenance, Gary ran EX in morning and then went to Pays Plat with the dozer | 5 | C050-C069 | Antler Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting675520201119-10Excavator - 30 ton- After Jan 10101384.5 | Corbiere and Sons Contracting675520201119-10Excavator - 30 ton- After Jan 10101384.5Inv#076 | [5 empty] | 1 | 1384.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6755 | 20201119-10 | 53510511 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10 | HR | 9.16 | 0 |  |  | 122.1 | 15.873 | 137.973 | 2020-11-19 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jesse on excavator doing winter access maintenance, Gary ran EX in morning and then went to Pays Plat with the dozer | 5 | C050-C069 | Antler Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting675520201119-10Excavator Thumb - 30 - 50 ton- After Jan 1010122.1 | Corbiere and Sons Contracting675520201119-10Excavator Thumb - 30 - 50 ton- After Jan 1010122.1Inv#076 | [5 empty] | 1 | 122.1 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6755 | 20201119-10 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-11-19 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jesse on excavator doing winter access maintenance, Gary ran EX in morning and then went to Pays Plat with the dozer | 5 | C050-C069 | Antler Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting675520201119-10Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting675520201119-10Light Truck - Pick up- After Jan 101243.75Inv#076 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6755 | 20201119-10 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-11-19 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jesse on excavator doing winter access maintenance, Gary ran EX in morning and then went to Pays Plat with the dozer | 5 | C050-C069 | Antler Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting675520201119-10L.O.A.1210 | Corbiere and Sons Contracting675520201119-10L.O.A.1210Inv#076 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6755 | 20201119-10 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 10.5 | HR |  |  | 75 | 0 | 787.5 | 102.375 | 889.875 | 2020-11-19 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jesse on excavator doing winter access maintenance, Gary ran EX in morning and then went to Pays Plat with the dozer | 5 | C050-C069 | Antler Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting675520201119-10Operator - Principle - After Jan 1010.5787.5 | Corbiere and Sons Contracting675520201119-10Operator - Principle - After Jan 1010.5787.5Inv#076 | [5 empty] | 1 | 787.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6759 | 20201119-14 | 53510512 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 6 | Dynamic | 110.22 | 0 |  |  | 881.76 | 114.6288 | 996.3888 | 2020-11-19 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance | 5 | C076-C116 | Cook Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting675920201119-14Excavator - 36 ton- After Jan 106881.76 | Corbiere and Sons Contracting675920201119-14Excavator - 36 ton- After Jan 106881.76Inv#076 | [5 empty] | 1 | 881.76 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6759 | 20201119-14 | 53510512 | Access | 0 | Foreman | 95 | 2 | HR |  |  | 95 | 0 | 190 | 24.7 | 214.7 | 2020-11-19 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance | 5 | C076-C116 | Cook Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting675920201119-14Foreman2190 | Corbiere and Sons Contracting675920201119-14Foreman2190Inv#076 | [5 empty] | 1 | 190 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6759 | 20201119-14 | 53510512 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-11-19 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance | 5 | C076-C116 | Cook Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting675920201119-14L.O.A.1210 | Corbiere and Sons Contracting675920201119-14L.O.A.1210Inv#076 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6759 | 20201119-14 | 53510512 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6.5 | HR |  |  | 75 | 0 | 487.5 | 63.375 | 550.875 | 2020-11-19 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road Maintenance | 5 | C076-C116 | Cook Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting675920201119-14Operator - Principle - After Jan 106.5487.5 | Corbiere and Sons Contracting675920201119-14Operator - Principle - After Jan 106.5487.5Inv#076 | [5 empty] | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6760 | 20201119-15 | 53510504 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10.5 | Dynamic | 98.61 | 0 |  |  | 1380.54 | 179.4702 | 1560.0102 | 2020-11-19 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock truck, dozer spreading gravel all day from C-105 | 5 | C093-C116 | Cook Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting676020201119-15Dozer D6 or equal- After Jan 1010.51380.54 | Corbiere and Sons Contracting676020201119-15Dozer D6 or equal- After Jan 1010.51380.54Inv#076 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1380.54 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6760 | 20201119-15 | 53510504 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10.5 | Dynamic | 110.22 | 0 |  |  | 1543.08 | 200.6004 | 1743.6804 | 2020-11-19 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock truck, dozer spreading gravel all day from C-105 | 5 | C093-C116 | Cook Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting676020201119-15Excavator - 36 ton- After Jan 1010.51543.08 | Corbiere and Sons Contracting676020201119-15Excavator - 36 ton- After Jan 1010.51543.08Inv#076 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1543.08 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6760 | 20201119-15 | 53510504 | Access | 0 | ATV - Side by Side w/ roll bar- After Jan 10 | 18.45 | 10 | HR | 13.84 | 0 |  |  | 184.5 | 23.985 | 208.485 | 2020-11-19 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock truck, dozer spreading gravel all day from C-105 | 5 | C093-C116 | Cook Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting676020201119-15ATV - Side by Side w/ roll bar- After Jan 1010184.5 | Corbiere and Sons Contracting676020201119-15ATV - Side by Side w/ roll bar- After Jan 1010184.5Inv#076 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 184.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6760 | 20201119-15 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2020-11-19 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock truck, dozer spreading gravel all day from C-105 | 5 | C093-C116 | Cook Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting676020201119-15Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting676020201119-15Light Truck - Pick up- After Jan 103731.25Inv#076 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 731.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6760 | 20201119-15 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 10.5 | Dynamic | 103.54 | 0 |  |  | 1449.525 | 188.4383 | 1637.9633 | 2020-11-19 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock truck, dozer spreading gravel all day from C-105 | 5 | C093-C116 | Cook Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting676020201119-15Rock Truck - 30 Ton- After Jan 1010.51449.525 | Corbiere and Sons Contracting676020201119-15Rock Truck - 30 Ton- After Jan 1010.51449.525Inv#076 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1449.525 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6760 | 20201119-15 | 53510504 | Access | 0 | Foreman | 95 | 5 | HR |  |  | 95 | 0 | 475 | 61.75 | 536.75 | 2020-11-19 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock truck, dozer spreading gravel all day from C-105 | 5 | C093-C116 | Cook Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting676020201119-15Foreman5475 | Corbiere and Sons Contracting676020201119-15Foreman5475Inv#076 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 475 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6760 | 20201119-15 | 53510504 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2020-11-19 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock truck, dozer spreading gravel all day from C-105 | 5 | C093-C116 | Cook Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting676020201119-15L.O.A.4840 | Corbiere and Sons Contracting676020201119-15L.O.A.4840Inv#076 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6760 | 20201119-15 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 23 | HR |  |  | 75 | 0 | 1725 | 224.25 | 1949.25 | 2020-11-19 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock truck, dozer spreading gravel all day from C-105 | 5 | C093-C116 | Cook Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting676020201119-15Operator - Principle - After Jan 10231725 | Corbiere and Sons Contracting676020201119-15Operator - Principle - After Jan 10231725Inv#076 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6760 | 20201119-15 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 11.5 | HR |  |  | 70 | 0 | 805 | 104.65 | 909.65 | 2020-11-19 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock truck, dozer spreading gravel all day from C-105 | 5 | C093-C116 | Cook Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting676020201119-15Driver - AZ - After Jan 1011.5805 | Corbiere and Sons Contracting676020201119-15Driver - AZ - After Jan 1011.5805Inv#076 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 805 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6761 | 20201119-16 | 53510504 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10.5 | Dynamic | 98.61 | 0 |  |  | 1380.54 | 179.4702 | 1560.0102 | 2020-11-19 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock truck all day, Rock truck on Mill Rd at C-120, dozer spreading gravel at C-120. | 5 | C117-C124 | Mill Road South | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting676120201119-16Dozer D6 or equal- After Jan 1010.51380.54 | Corbiere and Sons Contracting676120201119-16Dozer D6 or equal- After Jan 1010.51380.54Inv#076 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1380.54 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6761 | 20201119-16 | 53510504 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10.5 | Dynamic | 103.84 | 0 |  |  | 1453.725 | 188.9843 | 1642.7093 | 2020-11-19 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock truck all day, Rock truck on Mill Rd at C-120, dozer spreading gravel at C-120. | 5 | C117-C124 | Mill Road South | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting676120201119-16Excavator - 30 ton- After Jan 1010.51453.725 | Corbiere and Sons Contracting676120201119-16Excavator - 30 ton- After Jan 1010.51453.725Inv#076 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1453.725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6761 | 20201119-16 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-11-19 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock truck all day, Rock truck on Mill Rd at C-120, dozer spreading gravel at C-120. | 5 | C117-C124 | Mill Road South | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting676120201119-16Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting676120201119-16Light Truck - Pick up- After Jan 102487.5Inv#076 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6761 | 20201119-16 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 10.5 | Dynamic | 103.54 | 0 |  |  | 1449.525 | 188.4383 | 1637.9633 | 2020-11-19 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock truck all day, Rock truck on Mill Rd at C-120, dozer spreading gravel at C-120. | 5 | C117-C124 | Mill Road South | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting676120201119-16Rock Truck - 30 Ton- After Jan 1010.51449.525 | Corbiere and Sons Contracting676120201119-16Rock Truck - 30 Ton- After Jan 1010.51449.525Inv#076 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1449.525 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6761 | 20201119-16 | 53510504 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2020-11-19 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock truck all day, Rock truck on Mill Rd at C-120, dozer spreading gravel at C-120. | 5 | C117-C124 | Mill Road South | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting676120201119-16L.O.A.3630 | Corbiere and Sons Contracting676120201119-16L.O.A.3630Inv#076 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6761 | 20201119-16 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 23 | HR |  |  | 75 | 0 | 1725 | 224.25 | 1949.25 | 2020-11-19 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock truck all day, Rock truck on Mill Rd at C-120, dozer spreading gravel at C-120. | 5 | C117-C124 | Mill Road South | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting676120201119-16Operator - Principle - After Jan 10231725 | Corbiere and Sons Contracting676120201119-16Operator - Principle - After Jan 10231725Inv#076 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6761 | 20201119-16 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 11.5 | HR |  |  | 70 | 0 | 805 | 104.65 | 909.65 | 2020-11-19 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock truck all day, Rock truck on Mill Rd at C-120, dozer spreading gravel at C-120. | 5 | C117-C124 | Mill Road South | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting676120201119-16Driver - AZ - After Jan 1011.5805 | Corbiere and Sons Contracting676120201119-16Driver - AZ - After Jan 1011.5805Inv#076 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 805 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6869 | 20201119-23 | 53510412 | Access | 0 | Labourer - General - After Jan 10 | 60 | 4 | HR |  |  | 60 | 0 | 240 | 31.2 | 271.2 | 2020-11-19 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Labourers brought geo from Church Rd to Cavers Rd and did traffic control for EX-09 floating out of Church. | 4 | C015-C029 | Nishin Creek Road | 0 | 44159 |  | 50 | 44160 | [5 empty] | Wes Seminowich | 04 | Corbiere and Sons Contracting686920201119-23Labourer - General - After Jan 104240 | Corbiere and Sons Contracting686920201119-23Labourer - General - After Jan 104240Inv#081 | [5 empty] | 1 | 240 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6750 | 20201119-5 | 53520104 | Clearing | 0 | Chainsaw and consumables- After Jan 10 | 60 | 3 | unit/man/day | 0 | 0 |  |  | 180 | 23.4 | 203.4 | 2020-11-19 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working from A-001 - A-002 | 1 | A002-A010 | MacGregor | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 01 | Corbiere and Sons Contracting675020201119-5Chainsaw and consumables- After Jan 103180 | Corbiere and Sons Contracting675020201119-5Chainsaw and consumables- After Jan 103180Inv#076 |  |  | WF1-Handfalling |  |  | 1 | 180 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6750 | 20201119-5 | 53520104 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-11-19 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working from A-001 - A-002 | 1 | A002-A010 | MacGregor | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 01 | Corbiere and Sons Contracting675020201119-5Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting675020201119-5Light Truck - Pick up- After Jan 102487.5Inv#076 |  |  | WF1-Handfalling |  |  | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6750 | 20201119-5 | 53520104 | Clearing | 0 | Foreman | 95 | 6 | HR |  |  | 95 | 0 | 570 | 74.1 | 644.1 | 2020-11-19 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working from A-001 - A-002 | 1 | A002-A010 | MacGregor | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 01 | Corbiere and Sons Contracting675020201119-5Foreman6570 | Corbiere and Sons Contracting675020201119-5Foreman6570Inv#076 |  |  | WF1-Handfalling |  |  | 1 | 570 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6750 | 20201119-5 | 53520104 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-11-19 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working from A-001 - A-002 | 1 | A002-A010 | MacGregor | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 01 | Corbiere and Sons Contracting675020201119-5L.O.A.2420 | Corbiere and Sons Contracting675020201119-5L.O.A.2420Inv#076 |  |  | WF1-Handfalling |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6750 | 20201119-5 | 53520104 | Clearing | 0 | Labourer - Specialized - After Jan 10 | 70 | 33 | HR |  |  | 70 | 0 | 2310 | 300.3 | 2610.3 | 2020-11-19 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working from A-001 - A-002 | 1 | A002-A010 | MacGregor | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 01 | Corbiere and Sons Contracting675020201119-5Labourer - Specialized - After Jan 10332310 | Corbiere and Sons Contracting675020201119-5Labourer - Specialized - After Jan 10332310Inv#076 |  |  | WF1-Handfalling |  |  | 1 | 2310 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6753 | 20201119-8 | 53510511 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 6 | Dynamic | 98.61 | 0 |  |  | 788.88 | 102.5544 | 891.4344 | 2020-11-19 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer doing winter maintenance for 6.5 hrs. | 5 | C031-C049 | Pays Plat River | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting675320201119-8Dozer D6 or equal- After Jan 106788.88 | Corbiere and Sons Contracting675320201119-8Dozer D6 or equal- After Jan 106788.88Inv#076 | [5 empty] | 1 | 788.88 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6753 | 20201119-8 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-11-19 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer doing winter maintenance for 6.5 hrs. | 5 | C031-C049 | Pays Plat River | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting675320201119-8Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting675320201119-8Light Truck - Pick up- After Jan 101243.75Inv#076 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6753 | 20201119-8 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-11-19 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer doing winter maintenance for 6.5 hrs. | 5 | C031-C049 | Pays Plat River | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting675320201119-8L.O.A.1210 | Corbiere and Sons Contracting675320201119-8L.O.A.1210Inv#076 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6753 | 20201119-8 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6.5 | HR |  |  | 75 | 0 | 487.5 | 63.375 | 550.875 | 2020-11-19 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer doing winter maintenance for 6.5 hrs. | 5 | C031-C049 | Pays Plat River | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting675320201119-8Operator - Principle - After Jan 106.5487.5 | Corbiere and Sons Contracting675320201119-8Operator - Principle - After Jan 106.5487.5Inv#076 | [5 empty] | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6771 | 20201120-10 | 53510504 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10.5 | Dynamic | 98.61 | 0 |  |  | 1380.54 | 179.4702 | 1560.0102 | 2020-11-20 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock truck hauling gravel for spread at C-118Dozer spreading gravel from C-118Excavator loading rock trucks all dayLabourers rolling out geo | 5 | C117-C124 | Mill Road South | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting677120201120-10Dozer D6 or equal- After Jan 1010.51380.54 | Corbiere and Sons Contracting677120201120-10Dozer D6 or equal- After Jan 1010.51380.54Inv#076 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1380.54 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6771 | 20201120-10 | 53510504 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10.5 | Dynamic | 103.84 | 0 |  |  | 1453.725 | 188.9843 | 1642.7093 | 2020-11-20 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock truck hauling gravel for spread at C-118Dozer spreading gravel from C-118Excavator loading rock trucks all dayLabourers rolling out geo | 5 | C117-C124 | Mill Road South | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting677120201120-10Excavator - 30 ton- After Jan 1010.51453.725 | Corbiere and Sons Contracting677120201120-10Excavator - 30 ton- After Jan 1010.51453.725Inv#076 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1453.725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6771 | 20201120-10 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-11-20 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock truck hauling gravel for spread at C-118Dozer spreading gravel from C-118Excavator loading rock trucks all dayLabourers rolling out geo | 5 | C117-C124 | Mill Road South | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting677120201120-10Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting677120201120-10Light Truck - Pick up- After Jan 102487.5Inv#076 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6771 | 20201120-10 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 10.5 | Dynamic | 103.54 | 0 |  |  | 1449.525 | 188.4383 | 1637.9633 | 2020-11-20 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock truck hauling gravel for spread at C-118Dozer spreading gravel from C-118Excavator loading rock trucks all dayLabourers rolling out geo | 5 | C117-C124 | Mill Road South | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting677120201120-10Rock Truck - 30 Ton- After Jan 1010.51449.525 | Corbiere and Sons Contracting677120201120-10Rock Truck - 30 Ton- After Jan 1010.51449.525Inv#076 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1449.525 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6771 | 20201120-10 | 53510504 | Access | 0 | Foreman | 95 | 6 | HR |  |  | 95 | 0 | 570 | 74.1 | 644.1 | 2020-11-20 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock truck hauling gravel for spread at C-118Dozer spreading gravel from C-118Excavator loading rock trucks all dayLabourers rolling out geo | 5 | C117-C124 | Mill Road South | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting677120201120-10Foreman6570 | Corbiere and Sons Contracting677120201120-10Foreman6570Inv#076 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 570 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6771 | 20201120-10 | 53510504 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2020-11-20 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock truck hauling gravel for spread at C-118Dozer spreading gravel from C-118Excavator loading rock trucks all dayLabourers rolling out geo | 5 | C117-C124 | Mill Road South | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting677120201120-10L.O.A.4840 | Corbiere and Sons Contracting677120201120-10L.O.A.4840Inv#076 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6771 | 20201120-10 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 23 | HR |  |  | 75 | 0 | 1725 | 224.25 | 1949.25 | 2020-11-20 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock truck hauling gravel for spread at C-118Dozer spreading gravel from C-118Excavator loading rock trucks all dayLabourers rolling out geo | 5 | C117-C124 | Mill Road South | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting677120201120-10Operator - Principle - After Jan 10231725 | Corbiere and Sons Contracting677120201120-10Operator - Principle - After Jan 10231725Inv#076 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6771 | 20201120-10 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 11.5 | HR |  |  | 70 | 0 | 805 | 104.65 | 909.65 | 2020-11-20 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock truck hauling gravel for spread at C-118Dozer spreading gravel from C-118Excavator loading rock trucks all dayLabourers rolling out geo | 5 | C117-C124 | Mill Road South | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting677120201120-10Driver - AZ - After Jan 1011.5805 | Corbiere and Sons Contracting677120201120-10Driver - AZ - After Jan 1011.5805Inv#076 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 805 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6771 | 20201120-10 | 53510504 | Access | 0 | Labourer - General - After Jan 10 | 60 | 6 | HR |  |  | 60 | 0 | 360 | 46.8 | 406.8 | 2020-11-20 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Rock truck hauling gravel for spread at C-118Dozer spreading gravel from C-118Excavator loading rock trucks all dayLabourers rolling out geo | 5 | C117-C124 | Mill Road South | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting677120201120-10Labourer - General - After Jan 106360 | Corbiere and Sons Contracting677120201120-10Labourer - General - After Jan 106360Inv#076 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 360 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6772 | 20201120-11 | 53510511 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 5.5 | Dynamic | 98.61 | 0 |  |  | 723.14 | 94.0082 | 817.1482 | 2020-11-20 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer doing winter maintenance for 6 hours | 5 | C031-C049 | Pays Plat River | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting677220201120-11Dozer D6 or equal- After Jan 105.5723.14 | Corbiere and Sons Contracting677220201120-11Dozer D6 or equal- After Jan 105.5723.14Inv#076 | [5 empty] | 1 | 723.14 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6772 | 20201120-11 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-11-20 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer doing winter maintenance for 6 hours | 5 | C031-C049 | Pays Plat River | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting677220201120-11Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting677220201120-11Light Truck - Pick up- After Jan 101243.75Inv#076 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6772 | 20201120-11 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-11-20 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer doing winter maintenance for 6 hours | 5 | C031-C049 | Pays Plat River | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting677220201120-11L.O.A.1210 | Corbiere and Sons Contracting677220201120-11L.O.A.1210Inv#076 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6772 | 20201120-11 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 75 | 0 | 450 | 58.5 | 508.5 | 2020-11-20 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer doing winter maintenance for 6 hours | 5 | C031-C049 | Pays Plat River | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting677220201120-11Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting677220201120-11Operator - Principle - After Jan 106450Inv#076 | [5 empty] | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6774 | 20201120-13 | 53560501 | Water Crossings | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 7 | Dynamic | 103.84 | 0 |  |  | 969.15 | 125.9895 | 1095.1395 | 2020-11-20 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | <6M Water Crossing Install |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Labourers rigging up 20' bridge onto float, assisting Rej with the rig mat crossing and rock armouring at WC7600.01Rej put down rig mat crossing at WC7600.01 and ground prep with rock armouring. | 5 | C076-C116 | Cook Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting677420201120-13Excavator - 30 ton- After Jan 107969.15 | Corbiere and Sons Contracting677420201120-13Excavator - 30 ton- After Jan 107969.15Inv#076 |  |  | WF5-WaterCrossing |  |  | 0.5 | 484.575 | WC406 | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6774 | 20201120-13 | 53560501 | Water Crossings | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 7 | HR | 9.16 | 0 |  |  | 85.47 | 11.1111 | 96.5811 | 2020-11-20 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | <6M Water Crossing Install |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Labourers rigging up 20' bridge onto float, assisting Rej with the rig mat crossing and rock armouring at WC7600.01Rej put down rig mat crossing at WC7600.01 and ground prep with rock armouring. | 5 | C076-C116 | Cook Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting677420201120-13Excavator Thumb - 30 - 50 ton- After Jan 10785.47 | Corbiere and Sons Contracting677420201120-13Excavator Thumb - 30 - 50 ton- After Jan 10785.47Inv#076 |  |  | WF5-WaterCrossing |  |  | 0.5 | 42.735 | WC406 | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6774 | 20201120-13 | 53560501 | Water Crossings | 0 | ATV - Side by Side w/ roll bar- After Jan 10 | 18.45 | 5 | HR | 13.84 | 0 |  |  | 92.25 | 11.9925 | 104.2425 | 2020-11-20 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | <6M Water Crossing Install |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Labourers rigging up 20' bridge onto float, assisting Rej with the rig mat crossing and rock armouring at WC7600.01Rej put down rig mat crossing at WC7600.01 and ground prep with rock armouring. | 5 | C076-C116 | Cook Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting677420201120-13ATV - Side by Side w/ roll bar- After Jan 10592.25 | Corbiere and Sons Contracting677420201120-13ATV - Side by Side w/ roll bar- After Jan 10592.25Inv#076 |  |  | WF5-WaterCrossing |  |  | 0.5 | 46.125 | WC406 | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6774 | 20201120-13 | 53560501 | Water Crossings | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-11-20 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | <6M Water Crossing Install |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Labourers rigging up 20' bridge onto float, assisting Rej with the rig mat crossing and rock armouring at WC7600.01Rej put down rig mat crossing at WC7600.01 and ground prep with rock armouring. | 5 | C076-C116 | Cook Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting677420201120-13Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting677420201120-13Light Truck - Pick up- After Jan 101243.75Inv#076 |  |  | WF5-WaterCrossing |  |  | 0.5 | 121.875 | WC406 | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6774 | 20201120-13 | 53560501 | Water Crossings | 0 | Light Truck w/ Tandum Trailer- After Jan 10 | 337.5 | 1 | DAY | 253.13 | 0 |  |  | 337.5 | 43.875 | 381.375 | 2020-11-20 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | <6M Water Crossing Install |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Labourers rigging up 20' bridge onto float, assisting Rej with the rig mat crossing and rock armouring at WC7600.01Rej put down rig mat crossing at WC7600.01 and ground prep with rock armouring. | 5 | C076-C116 | Cook Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting677420201120-13Light Truck w/ Tandum Trailer- After Jan 101337.5 | Corbiere and Sons Contracting677420201120-13Light Truck w/ Tandum Trailer- After Jan 101337.5Inv#076 |  |  | WF5-WaterCrossing |  |  | 0.5 | 168.75 | WC406 | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6774 | 20201120-13 | 53560501 | Water Crossings | 0 | Foreman | 95 | 3 | HR |  |  | 95 | 0 | 285 | 37.05 | 322.05 | 2020-11-20 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | <6M Water Crossing Install |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Labourers rigging up 20' bridge onto float, assisting Rej with the rig mat crossing and rock armouring at WC7600.01Rej put down rig mat crossing at WC7600.01 and ground prep with rock armouring. | 5 | C076-C116 | Cook Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting677420201120-13Foreman3285 | Corbiere and Sons Contracting677420201120-13Foreman3285Inv#076 |  |  | WF5-WaterCrossing |  |  | 0.5 | 142.5 | WC406 | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6774 | 20201120-13 | 53560501 | Water Crossings | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2020-11-20 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | <6M Water Crossing Install |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Labourers rigging up 20' bridge onto float, assisting Rej with the rig mat crossing and rock armouring at WC7600.01Rej put down rig mat crossing at WC7600.01 and ground prep with rock armouring. | 5 | C076-C116 | Cook Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting677420201120-13L.O.A.3630 | Corbiere and Sons Contracting677420201120-13L.O.A.3630Inv#076 |  |  | WF5-WaterCrossing |  |  | 0.5 | 315 | WC406 | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6774 | 20201120-13 | 53560501 | Water Crossings | 0 | Operator - Principle - After Jan 10 | 75 | 7.5 | HR |  |  | 75 | 0 | 562.5 | 73.125 | 635.625 | 2020-11-20 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | <6M Water Crossing Install |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Labourers rigging up 20' bridge onto float, assisting Rej with the rig mat crossing and rock armouring at WC7600.01Rej put down rig mat crossing at WC7600.01 and ground prep with rock armouring. | 5 | C076-C116 | Cook Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting677420201120-13Operator - Principle - After Jan 107.5562.5 | Corbiere and Sons Contracting677420201120-13Operator - Principle - After Jan 107.5562.5Inv#076 |  |  | WF5-WaterCrossing |  |  | 0.5 | 281.25 | WC406 | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6774 | 20201120-13 | 53560501 | Water Crossings | 0 | Labourer - General - After Jan 10 | 60 | 10 | HR |  |  | 60 | 0 | 600 | 78 | 678 | 2020-11-20 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | <6M Water Crossing Install |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Labourers rigging up 20' bridge onto float, assisting Rej with the rig mat crossing and rock armouring at WC7600.01Rej put down rig mat crossing at WC7600.01 and ground prep with rock armouring. | 5 | C076-C116 | Cook Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting677420201120-13Labourer - General - After Jan 1010600 | Corbiere and Sons Contracting677420201120-13Labourer - General - After Jan 1010600Inv#076 |  |  | WF5-WaterCrossing |  |  | 0.5 | 300 | WC406 | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6775 | 20201120-14 | 53510504 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 4 | Dynamic | 98.61 | 0 |  |  | 525.92 | 68.3696 | 594.2896 | 2020-11-20 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Labourers rolling out geo for gravel spread from C-106, Rob loading rock trucks, rock truck hauling gravel for spread, dozer spreading gravel. | 5 | C076-C116 | Cook Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting677520201120-14Dozer D6 or equal- After Jan 104525.92 | Corbiere and Sons Contracting677520201120-14Dozer D6 or equal- After Jan 104525.92Inv#076 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 525.92 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6775 | 20201120-14 | 53510504 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 4 | Dynamic | 110.22 | 0 |  |  | 587.84 | 76.4192 | 664.2592 | 2020-11-20 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Labourers rolling out geo for gravel spread from C-106, Rob loading rock trucks, rock truck hauling gravel for spread, dozer spreading gravel. | 5 | C076-C116 | Cook Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting677520201120-14Excavator - 36 ton- After Jan 104587.84 | Corbiere and Sons Contracting677520201120-14Excavator - 36 ton- After Jan 104587.84Inv#076 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 587.84 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6775 | 20201120-14 | 53510504 | Access | 0 | ATV - Side by Side w/ roll bar- After Jan 10 | 18.45 | 4 | HR | 13.84 | 0 |  |  | 73.8 | 9.594 | 83.394 | 2020-11-20 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Labourers rolling out geo for gravel spread from C-106, Rob loading rock trucks, rock truck hauling gravel for spread, dozer spreading gravel. | 5 | C076-C116 | Cook Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting677520201120-14ATV - Side by Side w/ roll bar- After Jan 10473.8 | Corbiere and Sons Contracting677520201120-14ATV - Side by Side w/ roll bar- After Jan 10473.8Inv#076 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 73.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6775 | 20201120-14 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-11-20 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Labourers rolling out geo for gravel spread from C-106, Rob loading rock trucks, rock truck hauling gravel for spread, dozer spreading gravel. | 5 | C076-C116 | Cook Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting677520201120-14Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting677520201120-14Light Truck - Pick up- After Jan 102487.5Inv#076 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6775 | 20201120-14 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 4 | Dynamic | 103.54 | 0 |  |  | 552.2 | 71.786 | 623.986 | 2020-11-20 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Labourers rolling out geo for gravel spread from C-106, Rob loading rock trucks, rock truck hauling gravel for spread, dozer spreading gravel. | 5 | C076-C116 | Cook Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting677520201120-14Rock Truck - 30 Ton- After Jan 104552.2 | Corbiere and Sons Contracting677520201120-14Rock Truck - 30 Ton- After Jan 104552.2Inv#076 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 552.2 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6775 | 20201120-14 | 53510504 | Access | 0 | Foreman | 95 | 3 | HR |  |  | 95 | 0 | 285 | 37.05 | 322.05 | 2020-11-20 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Labourers rolling out geo for gravel spread from C-106, Rob loading rock trucks, rock truck hauling gravel for spread, dozer spreading gravel. | 5 | C076-C116 | Cook Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting677520201120-14Foreman3285 | Corbiere and Sons Contracting677520201120-14Foreman3285Inv#076 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 285 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6775 | 20201120-14 | 53510504 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-11-20 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Labourers rolling out geo for gravel spread from C-106, Rob loading rock trucks, rock truck hauling gravel for spread, dozer spreading gravel. | 5 | C076-C116 | Cook Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting677520201120-14L.O.A.2420 | Corbiere and Sons Contracting677520201120-14L.O.A.2420Inv#076 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6775 | 20201120-14 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 9 | HR |  |  | 75 | 0 | 675 | 87.75 | 762.75 | 2020-11-20 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Labourers rolling out geo for gravel spread from C-106, Rob loading rock trucks, rock truck hauling gravel for spread, dozer spreading gravel. | 5 | C076-C116 | Cook Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting677520201120-14Operator - Principle - After Jan 109675 | Corbiere and Sons Contracting677520201120-14Operator - Principle - After Jan 109675Inv#076 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 675 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6775 | 20201120-14 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 4.5 | HR |  |  | 70 | 0 | 315 | 40.95 | 355.95 | 2020-11-20 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Labourers rolling out geo for gravel spread from C-106, Rob loading rock trucks, rock truck hauling gravel for spread, dozer spreading gravel. | 5 | C076-C116 | Cook Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting677520201120-14Driver - AZ - After Jan 104.5315 | Corbiere and Sons Contracting677520201120-14Driver - AZ - After Jan 104.5315Inv#076 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 315 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6775 | 20201120-14 | 53510504 | Access | 0 | Labourer - General - After Jan 10 | 60 | 4 | HR |  |  | 60 | 0 | 240 | 31.2 | 271.2 | 2020-11-20 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Labourers rolling out geo for gravel spread from C-106, Rob loading rock trucks, rock truck hauling gravel for spread, dozer spreading gravel. | 5 | C076-C116 | Cook Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting677520201120-14Labourer - General - After Jan 104240 | Corbiere and Sons Contracting677520201120-14Labourer - General - After Jan 104240Inv#076 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 240 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6777 | 20201120-16 | 53510512 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 6.5 | Dynamic | 110.22 | 0 |  |  | 955.24 | 124.1812 | 1079.4212 | 2020-11-20 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Scrapping hills for maintenance | 5 | C076-C116 | Cook Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting677720201120-16Excavator - 36 ton- After Jan 106.5955.24 | Corbiere and Sons Contracting677720201120-16Excavator - 36 ton- After Jan 106.5955.24Inv#076 | [5 empty] | 1 | 955.24 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6777 | 20201120-16 | 53510512 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-11-20 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Scrapping hills for maintenance | 5 | C076-C116 | Cook Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting677720201120-16Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting677720201120-16Light Truck - Pick up- After Jan 101243.75Inv#076 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6777 | 20201120-16 | 53510512 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-11-20 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Scrapping hills for maintenance | 5 | C076-C116 | Cook Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting677720201120-16L.O.A.1210 | Corbiere and Sons Contracting677720201120-16L.O.A.1210Inv#076 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6777 | 20201120-16 | 53510512 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 7 | HR |  |  | 75 | 0 | 525 | 68.25 | 593.25 | 2020-11-20 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Scrapping hills for maintenance | 5 | C076-C116 | Cook Lake | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting677720201120-16Operator - Principle - After Jan 107525 | Corbiere and Sons Contracting677720201120-16Operator - Principle - After Jan 107525Inv#076 | [5 empty] | 1 | 525 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6780 | 20201120-19 | 53510312 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 1 | Dynamic | 98.61 | 0 |  |  | 131.48 | 17.0924 | 148.5724 | 2020-11-20 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Maintenance to road on way out | 3 | B145-B149 | Camp 81 Road | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting678020201120-19Dozer D6 or equal- After Jan 101131.48 | Corbiere and Sons Contracting678020201120-19Dozer D6 or equal- After Jan 101131.48Inv#076 | [5 empty] | 1 | 131.48 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6780 | 20201120-19 | 53510312 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 2 | Dynamic | 110.22 | 0 |  |  | 293.92 | 38.2096 | 332.1296 | 2020-11-20 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Maintenance to road on way out | 3 | B145-B149 | Camp 81 Road | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting678020201120-19Excavator - 36 ton- After Jan 102293.92 | Corbiere and Sons Contracting678020201120-19Excavator - 36 ton- After Jan 102293.92Inv#076 | [5 empty] | 1 | 293.92 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6780 | 20201120-19 | 53510312 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 2 | HR | 9.16 | 0 |  |  | 24.42 | 3.1746 | 27.5946 | 2020-11-20 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Maintenance to road on way out | 3 | B145-B149 | Camp 81 Road | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting678020201120-19Excavator Thumb - 30 - 50 ton- After Jan 10224.42 | Corbiere and Sons Contracting678020201120-19Excavator Thumb - 30 - 50 ton- After Jan 10224.42Inv#076 | [5 empty] | 1 | 24.42 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6780 | 20201120-19 | 53510312 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 3 | HR |  |  | 75 | 0 | 225 | 29.25 | 254.25 | 2020-11-20 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Maintenance to road on way out | 3 | B145-B149 | Camp 81 Road | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting678020201120-19Operator - Principle - After Jan 103225 | Corbiere and Sons Contracting678020201120-19Operator - Principle - After Jan 103225Inv#076 | [5 empty] | 1 | 225 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6784 | 20201120-23 | 53510412 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 5 | Dynamic | 98.61 | 0 |  |  | 657.4 | 85.462 | 742.862 | 2020-11-20 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | DZ-01 dragged culvert in to B-206 and walked to B-217 | 4 | B194-B203 | Little Gravel River Road | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 04 | Corbiere and Sons Contracting678420201120-23Dozer D6 or equal- After Jan 105657.4 | Corbiere and Sons Contracting678420201120-23Dozer D6 or equal- After Jan 105657.4Inv#076 | [5 empty] | 1 | 657.4 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6784 | 20201120-23 | 53510412 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-11-20 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | DZ-01 dragged culvert in to B-206 and walked to B-217 | 4 | B194-B203 | Little Gravel River Road | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 04 | Corbiere and Sons Contracting678420201120-23Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting678420201120-23Light Truck - Pick up- After Jan 101243.75Inv#076 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6784 | 20201120-23 | 53510412 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 75 | 0 | 450 | 58.5 | 508.5 | 2020-11-20 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | DZ-01 dragged culvert in to B-206 and walked to B-217 | 4 | B194-B203 | Little Gravel River Road | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 04 | Corbiere and Sons Contracting678420201120-23Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting678420201120-23Operator - Principle - After Jan 106450Inv#076 | [5 empty] | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6784 | 20201120-23 | 53510412 | Access | 0 | Labourer - General - After Jan 10 | 60 | 6 | HR |  |  | 60 | 0 | 360 | 46.8 | 406.8 | 2020-11-20 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | DZ-01 dragged culvert in to B-206 and walked to B-217 | 4 | B194-B203 | Little Gravel River Road | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 04 | Corbiere and Sons Contracting678420201120-23Labourer - General - After Jan 106360 | Corbiere and Sons Contracting678420201120-23Labourer - General - After Jan 106360Inv#076 | [5 empty] | 1 | 360 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6766 | 20201120-5 | 53520104 | Clearing | 0 | Chainsaw and consumables- After Jan 10 | 60 | 3 | unit/man/day | 0 | 0 |  |  | 180 | 23.4 | 203.4 | 2020-11-20 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working from A-002 | 1 | A002-A010 | MacGregor | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 01 | Corbiere and Sons Contracting676620201120-5Chainsaw and consumables- After Jan 103180 | Corbiere and Sons Contracting676620201120-5Chainsaw and consumables- After Jan 103180Inv#076 |  |  | WF1-Handfalling |  |  | 1 | 180 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6766 | 20201120-5 | 53520104 | Clearing | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-11-20 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working from A-002 | 1 | A002-A010 | MacGregor | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 01 | Corbiere and Sons Contracting676620201120-5Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting676620201120-5Light Truck - Pick up- After Jan 102487.5Inv#076 |  |  | WF1-Handfalling |  |  | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6766 | 20201120-5 | 53520104 | Clearing | 0 | Foreman | 95 | 6 | HR |  |  | 95 | 0 | 570 | 74.1 | 644.1 | 2020-11-20 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working from A-002 | 1 | A002-A010 | MacGregor | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 01 | Corbiere and Sons Contracting676620201120-5Foreman6570 | Corbiere and Sons Contracting676620201120-5Foreman6570Inv#076 |  |  | WF1-Handfalling |  |  | 1 | 570 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6766 | 20201120-5 | 53520104 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-11-20 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working from A-002 | 1 | A002-A010 | MacGregor | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 01 | Corbiere and Sons Contracting676620201120-5L.O.A.2420 | Corbiere and Sons Contracting676620201120-5L.O.A.2420Inv#076 |  |  | WF1-Handfalling |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6766 | 20201120-5 | 53520104 | Clearing | 0 | Labourer - Specialized - After Jan 10 | 70 | 33 | HR |  |  | 70 | 0 | 2310 | 300.3 | 2610.3 | 2020-11-20 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | Hand Falling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working from A-002 | 1 | A002-A010 | MacGregor | 0 | 44156 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 01 | Corbiere and Sons Contracting676620201120-5Labourer - Specialized - After Jan 10332310 | Corbiere and Sons Contracting676620201120-5Labourer - Specialized - After Jan 10332310Inv#076 |  |  | WF1-Handfalling |  |  | 1 | 2310 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6797 | 20201121-11 | 53510412 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 6 | Dynamic | 98.61 | 0 |  |  | 788.88 | 102.5544 | 891.4344 | 2020-11-21 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance and filled in ruts B-204 - B-217 | 4 | B204-B217 | Little Gravel River Road East | 0 | 44158 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 04 | Corbiere and Sons Contracting679720201121-11Dozer D6 or equal- After Jan 106788.88 | Corbiere and Sons Contracting679720201121-11Dozer D6 or equal- After Jan 106788.88Inv#076 | [5 empty] | 1 | 788.88 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6797 | 20201121-11 | 53510412 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 7 | HR |  |  | 75 | 0 | 525 | 68.25 | 593.25 | 2020-11-21 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance and filled in ruts B-204 - B-217 | 4 | B204-B217 | Little Gravel River Road East | 0 | 44158 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 04 | Corbiere and Sons Contracting679720201121-11Operator - Principle - After Jan 107525 | Corbiere and Sons Contracting679720201121-11Operator - Principle - After Jan 107525Inv#076 | [5 empty] | 1 | 525 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6880 | 20201121-18 | 53510504 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 6 | Dynamic | 98.61 | 0 |  |  | 788.88 | 102.5544 | 891.4344 | 2020-11-21 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock truck, rock truck hauled gravel, dozer spreading gravelLabourer bringing and rolling out geo | 5 | C117-C124 | Mill Road South | 0 | 44160 |  | 50 | 44162 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting688020201121-18Dozer D6 or equal- After Jan 106788.88 | Corbiere and Sons Contracting688020201121-18Dozer D6 or equal- After Jan 106788.88Inv#081 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 788.88 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6880 | 20201121-18 | 53510504 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 6 | Dynamic | 103.84 | 0 |  |  | 830.7 | 107.991 | 938.691 | 2020-11-21 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock truck, rock truck hauled gravel, dozer spreading gravelLabourer bringing and rolling out geo | 5 | C117-C124 | Mill Road South | 0 | 44160 |  | 50 | 44162 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting688020201121-18Excavator - 30 ton- After Jan 106830.7 | Corbiere and Sons Contracting688020201121-18Excavator - 30 ton- After Jan 106830.7Inv#081 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 830.7 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6880 | 20201121-18 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-11-21 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock truck, rock truck hauled gravel, dozer spreading gravelLabourer bringing and rolling out geo | 5 | C117-C124 | Mill Road South | 0 | 44160 |  | 50 | 44162 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting688020201121-18Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting688020201121-18Light Truck - Pick up- After Jan 102487.5Inv#081 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6880 | 20201121-18 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 6 | Dynamic | 103.54 | 0 |  |  | 828.3 | 107.679 | 935.979 | 2020-11-21 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock truck, rock truck hauled gravel, dozer spreading gravelLabourer bringing and rolling out geo | 5 | C117-C124 | Mill Road South | 0 | 44160 |  | 50 | 44162 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting688020201121-18Rock Truck - 30 Ton- After Jan 106828.3 | Corbiere and Sons Contracting688020201121-18Rock Truck - 30 Ton- After Jan 106828.3Inv#081 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 828.3 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6880 | 20201121-18 | 53510504 | Access | 0 | Foreman | 95 | 4 | HR |  |  | 95 |  | 380 | 49.4 | 429.4 | 2020-11-21 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock truck, rock truck hauled gravel, dozer spreading gravelLabourer bringing and rolling out geo | 5 | C117-C124 | Mill Road South | 0 | 44160 |  | 50 | 44162 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting688020201121-18Foreman4380 | Corbiere and Sons Contracting688020201121-18Foreman4380Inv#081 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6880 | 20201121-18 | 53510504 | Access | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2020-11-21 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock truck, rock truck hauled gravel, dozer spreading gravelLabourer bringing and rolling out geo | 5 | C117-C124 | Mill Road South | 0 | 44160 |  | 50 | 44162 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting688020201121-18L.O.A.51050 | Corbiere and Sons Contracting688020201121-18L.O.A.51050Inv#081 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6880 | 20201121-18 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2020-11-21 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock truck, rock truck hauled gravel, dozer spreading gravelLabourer bringing and rolling out geo | 5 | C117-C124 | Mill Road South | 0 | 44160 |  | 50 | 44162 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting688020201121-18Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting688020201121-18Operator - Principle - After Jan 1012900Inv#081 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6880 | 20201121-18 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 6 | HR |  |  | 70 | 0 | 420 | 54.6 | 474.6 | 2020-11-21 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock truck, rock truck hauled gravel, dozer spreading gravelLabourer bringing and rolling out geo | 5 | C117-C124 | Mill Road South | 0 | 44160 |  | 50 | 44162 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting688020201121-18Driver - AZ - After Jan 106420 | Corbiere and Sons Contracting688020201121-18Driver - AZ - After Jan 106420Inv#081 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6880 | 20201121-18 | 53510504 | Access | 0 | Labourer - General - After Jan 10 | 60 | 4 | HR |  |  | 60 | 0 | 240 | 31.2 | 271.2 | 2020-11-21 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock truck, rock truck hauled gravel, dozer spreading gravelLabourer bringing and rolling out geo | 5 | C117-C124 | Mill Road South | 0 | 44160 |  | 50 | 44162 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting688020201121-18Labourer - General - After Jan 104240 | Corbiere and Sons Contracting688020201121-18Labourer - General - After Jan 104240Inv#081 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 240 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6881 | 20201121-19 | 53510502 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10.5 | Dynamic | 103.84 | 0 |  |  | 1453.725 | 188.9843 | 1642.7093 | 2020-11-21 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator tying in road to C-064 | 5 | C050-C069 | Antler Lake | 0 | 44160 |  | 50 | 44162 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting688120201121-19Excavator - 30 ton- After Jan 1010.51453.725 | Corbiere and Sons Contracting688120201121-19Excavator - 30 ton- After Jan 1010.51453.725Inv#081 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 1453.725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6881 | 20201121-19 | 53510502 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10.5 | HR | 9.16 | 0 |  |  | 128.205 | 16.6667 | 144.8716 | 2020-11-21 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator tying in road to C-064 | 5 | C050-C069 | Antler Lake | 0 | 44160 |  | 50 | 44162 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting688120201121-19Excavator Thumb - 30 - 50 ton- After Jan 1010.5128.205 | Corbiere and Sons Contracting688120201121-19Excavator Thumb - 30 - 50 ton- After Jan 1010.5128.205Inv#081 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 128.205 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6881 | 20201121-19 | 53510502 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-11-21 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator tying in road to C-064 | 5 | C050-C069 | Antler Lake | 0 | 44160 |  | 50 | 44162 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting688120201121-19Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting688120201121-19Light Truck - Pick up- After Jan 101243.75Inv#081 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6881 | 20201121-19 | 53510502 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-11-21 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator tying in road to C-064 | 5 | C050-C069 | Antler Lake | 0 | 44160 |  | 50 | 44162 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting688120201121-19L.O.A.1210 | Corbiere and Sons Contracting688120201121-19L.O.A.1210Inv#081 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6881 | 20201121-19 | 53510502 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-11-21 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator tying in road to C-064 | 5 | C050-C069 | Antler Lake | 0 | 44160 |  | 50 | 44162 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting688120201121-19Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting688120201121-19Operator - Principle - After Jan 1011.5862.5Inv#081 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6883 | 20201121-21 | 53510504 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 8 | Dynamic | 98.61 | 0 |  |  | 1051.84 | 136.7392 | 1188.5792 | 2020-11-21 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Linkbelt loading rock trucks, Rock truck hauling, Dozer spreading gravel from C-107. Labourer putting down geo from C-107 | 5 | C093-C116 | Cook Lake | 0 | 44160 |  | 50 | 44162 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting688320201121-21Dozer D6 or equal- After Jan 1081051.84 | Corbiere and Sons Contracting688320201121-21Dozer D6 or equal- After Jan 1081051.84Inv#081 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1051.84 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6883 | 20201121-21 | 53510504 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 8 | Dynamic | 110.22 | 0 |  |  | 1175.68 | 152.8384 | 1328.5184 | 2020-11-21 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Linkbelt loading rock trucks, Rock truck hauling, Dozer spreading gravel from C-107. Labourer putting down geo from C-107 | 5 | C093-C116 | Cook Lake | 0 | 44160 |  | 50 | 44162 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting688320201121-21Excavator - 36 ton- After Jan 1081175.68 | Corbiere and Sons Contracting688320201121-21Excavator - 36 ton- After Jan 1081175.68Inv#081 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1175.68 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6883 | 20201121-21 | 53510504 | Access | 0 | ATV - Side by Side w/ roll bar- After Jan 10 | 18.45 | 5 | HR | 13.84 | 0 |  |  | 92.25 | 11.9925 | 104.2425 | 2020-11-21 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Linkbelt loading rock trucks, Rock truck hauling, Dozer spreading gravel from C-107. Labourer putting down geo from C-107 | 5 | C093-C116 | Cook Lake | 0 | 44160 |  | 50 | 44162 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting688320201121-21ATV - Side by Side w/ roll bar- After Jan 10592.25 | Corbiere and Sons Contracting688320201121-21ATV - Side by Side w/ roll bar- After Jan 10592.25Inv#081 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 92.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6883 | 20201121-21 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-11-21 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Linkbelt loading rock trucks, Rock truck hauling, Dozer spreading gravel from C-107. Labourer putting down geo from C-107 | 5 | C093-C116 | Cook Lake | 0 | 44160 |  | 50 | 44162 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting688320201121-21Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting688320201121-21Light Truck - Pick up- After Jan 102487.5Inv#081 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6883 | 20201121-21 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 8 | Dynamic | 103.54 | 0 |  |  | 1104.4 | 143.572 | 1247.972 | 2020-11-21 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Linkbelt loading rock trucks, Rock truck hauling, Dozer spreading gravel from C-107. Labourer putting down geo from C-107 | 5 | C093-C116 | Cook Lake | 0 | 44160 |  | 50 | 44162 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting688320201121-21Rock Truck - 30 Ton- After Jan 1081104.4 | Corbiere and Sons Contracting688320201121-21Rock Truck - 30 Ton- After Jan 1081104.4Inv#081 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1104.4 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6883 | 20201121-21 | 53510504 | Access | 0 | Foreman | 95 | 4 | HR |  |  | 95 | 0 | 380 | 49.4 | 429.4 | 2020-11-21 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Linkbelt loading rock trucks, Rock truck hauling, Dozer spreading gravel from C-107. Labourer putting down geo from C-107 | 5 | C093-C116 | Cook Lake | 0 | 44160 |  | 50 | 44162 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting688320201121-21Foreman4380 | Corbiere and Sons Contracting688320201121-21Foreman4380Inv#081 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6883 | 20201121-21 | 53510504 | Access | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2020-11-21 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Linkbelt loading rock trucks, Rock truck hauling, Dozer spreading gravel from C-107. Labourer putting down geo from C-107 | 5 | C093-C116 | Cook Lake | 0 | 44160 |  | 50 | 44162 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting688320201121-21L.O.A.51050 | Corbiere and Sons Contracting688320201121-21L.O.A.51050Inv#081 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6883 | 20201121-21 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 24 | HR |  |  | 75 | 0 | 1800 | 234 | 2034 | 2020-11-21 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Linkbelt loading rock trucks, Rock truck hauling, Dozer spreading gravel from C-107. Labourer putting down geo from C-107 | 5 | C093-C116 | Cook Lake | 0 | 44160 |  | 50 | 44162 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting688320201121-21Operator - Principle - After Jan 10241800 | Corbiere and Sons Contracting688320201121-21Operator - Principle - After Jan 10241800Inv#081 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1800 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6883 | 20201121-21 | 53510504 | Access | 0 | Labourer - General - After Jan 10 | 60 | 6 | HR |  |  | 60 | 0 | 360 | 46.8 | 406.8 | 2020-11-21 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Linkbelt loading rock trucks, Rock truck hauling, Dozer spreading gravel from C-107. Labourer putting down geo from C-107 | 5 | C093-C116 | Cook Lake | 0 | 44160 |  | 50 | 44162 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting688320201121-21Labourer - General - After Jan 106360 | Corbiere and Sons Contracting688320201121-21Labourer - General - After Jan 106360Inv#081 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 360 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6884 | 20201121-22 | 53510511 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 7.5 | Dynamic | 103.84 | 0 |  |  | 1038.375 | 134.9888 | 1173.3637 | 2020-11-21 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator on road maintenanceLabourer on sanding truck going acorss Cooks Lake Rd | 5 | C076-C116 | Cook Lake | 0 | 44160 |  | 50 | 44162 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting688420201121-22Excavator - 30 ton- After Jan 107.51038.375 | Corbiere and Sons Contracting688420201121-22Excavator - 30 ton- After Jan 107.51038.375Inv#081 | [5 empty] | 1 | 1038.375 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6884 | 20201121-22 | 53510511 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 7.5 | HR | 9.16 | 0 |  |  | 91.575 | 11.9047 | 103.4797 | 2020-11-21 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator on road maintenanceLabourer on sanding truck going acorss Cooks Lake Rd | 5 | C076-C116 | Cook Lake | 0 | 44160 |  | 50 | 44162 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting688420201121-22Excavator Thumb - 30 - 50 ton- After Jan 107.591.575 | Corbiere and Sons Contracting688420201121-22Excavator Thumb - 30 - 50 ton- After Jan 107.591.575Inv#081 | [5 empty] | 1 | 91.575 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6884 | 20201121-22 | 53510511 | Access | 0 | Sander Truck - Hwy- After Jan 10 | 55 | 11 | Dynamic | 41.25 | 0 |  |  | 605 | 78.65 | 683.65 | 2020-11-21 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator on road maintenanceLabourer on sanding truck going acorss Cooks Lake Rd | 5 | C076-C116 | Cook Lake | 0 | 44160 |  | 50 | 44162 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting688420201121-22Sander Truck - Hwy- After Jan 1011605 | Corbiere and Sons Contracting688420201121-22Sander Truck - Hwy- After Jan 1011605Inv#081 | [5 empty] | 1 | 605 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6884 | 20201121-22 | 53510511 | Access | 0 | ATV - Side by Side w/ roll bar- After Jan 10 | 18.45 | 5 | HR | 13.84 | 0 |  |  | 92.25 | 11.9925 | 104.2425 | 2020-11-21 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator on road maintenanceLabourer on sanding truck going acorss Cooks Lake Rd | 5 | C076-C116 | Cook Lake | 0 | 44160 |  | 50 | 44162 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting688420201121-22ATV - Side by Side w/ roll bar- After Jan 10592.25 | Corbiere and Sons Contracting688420201121-22ATV - Side by Side w/ roll bar- After Jan 10592.25Inv#081 | [5 empty] | 1 | 92.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6884 | 20201121-22 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-11-21 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator on road maintenanceLabourer on sanding truck going acorss Cooks Lake Rd | 5 | C076-C116 | Cook Lake | 0 | 44160 |  | 50 | 44162 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting688420201121-22Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting688420201121-22Light Truck - Pick up- After Jan 102487.5Inv#081 | [5 empty] | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6884 | 20201121-22 | 53510511 | Access | 0 | Foreman | 95 | 5 | HR |  |  | 95 | 0 | 475 | 61.75 | 536.75 | 2020-11-21 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator on road maintenanceLabourer on sanding truck going acorss Cooks Lake Rd | 5 | C076-C116 | Cook Lake | 0 | 44160 |  | 50 | 44162 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting688420201121-22Foreman5475 | Corbiere and Sons Contracting688420201121-22Foreman5475Inv#081 | [5 empty] | 1 | 475 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6884 | 20201121-22 | 53510511 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-11-21 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator on road maintenanceLabourer on sanding truck going acorss Cooks Lake Rd | 5 | C076-C116 | Cook Lake | 0 | 44160 |  | 50 | 44162 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting688420201121-22L.O.A.2420 | Corbiere and Sons Contracting688420201121-22L.O.A.2420Inv#081 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6884 | 20201121-22 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 8 | HR |  |  | 75 | 0 | 600 | 78 | 678 | 2020-11-21 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator on road maintenanceLabourer on sanding truck going acorss Cooks Lake Rd | 5 | C076-C116 | Cook Lake | 0 | 44160 |  | 50 | 44162 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting688420201121-22Operator - Principle - After Jan 108600 | Corbiere and Sons Contracting688420201121-22Operator - Principle - After Jan 108600Inv#081 | [5 empty] | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6884 | 20201121-22 | 53510511 | Access | 0 | Labourer - General - After Jan 10 | 60 | 11.5 | HR |  |  | 60 | 0 | 690 | 89.7 | 779.7 | 2020-11-21 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator on road maintenanceLabourer on sanding truck going acorss Cooks Lake Rd | 5 | C076-C116 | Cook Lake | 0 | 44160 |  | 50 | 44162 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting688420201121-22Labourer - General - After Jan 1011.5690 | Corbiere and Sons Contracting688420201121-22Labourer - General - After Jan 1011.5690Inv#081 | [5 empty] | 1 | 690 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6794 | 20201121-8 | 53510312 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2020-11-21 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-07 and DZ-05 made a crane pull off and patched road in Landfill. | 3 | B078-B084 | Red Rock Road No. 7 | 0 | 44158 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting679420201121-8Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting679420201121-8Dozer D6 or equal- After Jan 10111446.28Inv#076 | [5 empty] | 1 | 1446.28 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6794 | 20201121-8 | 53510312 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 11 | Dynamic | 110.22 | 0 |  |  | 1616.56 | 210.1528 | 1826.7128 | 2020-11-21 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-07 and DZ-05 made a crane pull off and patched road in Landfill. | 3 | B078-B084 | Red Rock Road No. 7 | 0 | 44158 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting679420201121-8Excavator - 36 ton- After Jan 10111616.56 | Corbiere and Sons Contracting679420201121-8Excavator - 36 ton- After Jan 10111616.56Inv#076 | [5 empty] | 1 | 1616.56 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6794 | 20201121-8 | 53510312 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 11 | HR | 9.16 | 0 |  |  | 134.31 | 17.4603 | 151.7703 | 2020-11-21 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-07 and DZ-05 made a crane pull off and patched road in Landfill. | 3 | B078-B084 | Red Rock Road No. 7 | 0 | 44158 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting679420201121-8Excavator Thumb - 30 - 50 ton- After Jan 1011134.31 | Corbiere and Sons Contracting679420201121-8Excavator Thumb - 30 - 50 ton- After Jan 1011134.31Inv#076 | [5 empty] | 1 | 134.31 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6794 | 20201121-8 | 53510312 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-11-21 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-07 and DZ-05 made a crane pull off and patched road in Landfill. | 3 | B078-B084 | Red Rock Road No. 7 | 0 | 44158 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting679420201121-8Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting679420201121-8Light Truck - Pick up- After Jan 102487.5Inv#076 | [5 empty] | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6794 | 20201121-8 | 53510312 | Access | 0 | Foreman | 95 | 4 | HR |  |  | 95 | 0 | 380 | 49.4 | 429.4 | 2020-11-21 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-07 and DZ-05 made a crane pull off and patched road in Landfill. | 3 | B078-B084 | Red Rock Road No. 7 | 0 | 44158 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting679420201121-8Foreman4380 | Corbiere and Sons Contracting679420201121-8Foreman4380Inv#076 | [5 empty] | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6794 | 20201121-8 | 53510312 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 22 | HR |  |  | 75 | 0 | 1650 | 214.5 | 1864.5 | 2020-11-21 | 1 | Inv#076 | 44160 | 127 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-07 and DZ-05 made a crane pull off and patched road in Landfill. | 3 | B078-B084 | Red Rock Road No. 7 | 0 | 44158 |  | 50 | 44159 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting679420201121-8Operator - Principle - After Jan 10221650 | Corbiere and Sons Contracting679420201121-8Operator - Principle - After Jan 10221650Inv#076 | [5 empty] | 1 | 1650 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6911 | 20201122-11 | 53510504 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10.5 | Dynamic | 98.61 | 0 |  |  | 1380.54 | 179.4702 | 1560.0102 | 2020-11-22 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX loading Rock truck all day, Sozer spreading gravel from C-107 - C-109. | 5 | C093-C116 | Cook Lake | 0 | 44161 |  | 50 | 44162 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting691120201122-11Dozer D6 or equal- After Jan 1010.51380.54 | Corbiere and Sons Contracting691120201122-11Dozer D6 or equal- After Jan 1010.51380.54Inv#081 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1380.54 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6911 | 20201122-11 | 53510504 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10.5 | Dynamic | 110.22 | 0 |  |  | 1543.08 | 200.6004 | 1743.6804 | 2020-11-22 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX loading Rock truck all day, Sozer spreading gravel from C-107 - C-109. | 5 | C093-C116 | Cook Lake | 0 | 44161 |  | 50 | 44162 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting691120201122-11Excavator - 36 ton- After Jan 1010.51543.08 | Corbiere and Sons Contracting691120201122-11Excavator - 36 ton- After Jan 1010.51543.08Inv#081 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1543.08 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6911 | 20201122-11 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-11-22 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX loading Rock truck all day, Sozer spreading gravel from C-107 - C-109. | 5 | C093-C116 | Cook Lake | 0 | 44161 |  | 50 | 44162 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting691120201122-11Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting691120201122-11Light Truck - Pick up- After Jan 102487.5Inv#081 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6911 | 20201122-11 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 10.5 | Dynamic | 103.54 | 0 |  |  | 1449.525 | 188.4383 | 1637.9633 | 2020-11-22 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX loading Rock truck all day, Sozer spreading gravel from C-107 - C-109. | 5 | C093-C116 | Cook Lake | 0 | 44161 |  | 50 | 44162 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting691120201122-11Rock Truck - 30 Ton- After Jan 1010.51449.525 | Corbiere and Sons Contracting691120201122-11Rock Truck - 30 Ton- After Jan 1010.51449.525Inv#081 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1449.525 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6911 | 20201122-11 | 53510504 | Access | 0 | Foreman | 95 | 4 | HR |  |  | 95 | 0 | 380 | 49.4 | 429.4 | 2020-11-22 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX loading Rock truck all day, Sozer spreading gravel from C-107 - C-109. | 5 | C093-C116 | Cook Lake | 0 | 44161 |  | 50 | 44162 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting691120201122-11Foreman4380 | Corbiere and Sons Contracting691120201122-11Foreman4380Inv#081 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6911 | 20201122-11 | 53510504 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2020-11-22 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX loading Rock truck all day, Sozer spreading gravel from C-107 - C-109. | 5 | C093-C116 | Cook Lake | 0 | 44161 |  | 50 | 44162 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting691120201122-11L.O.A.4840 | Corbiere and Sons Contracting691120201122-11L.O.A.4840Inv#081 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6911 | 20201122-11 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 23 | HR |  |  | 75 | 0 | 1725 | 224.25 | 1949.25 | 2020-11-22 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX loading Rock truck all day, Sozer spreading gravel from C-107 - C-109. | 5 | C093-C116 | Cook Lake | 0 | 44161 |  | 50 | 44162 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting691120201122-11Operator - Principle - After Jan 10231725 | Corbiere and Sons Contracting691120201122-11Operator - Principle - After Jan 10231725Inv#081 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6911 | 20201122-11 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 11.5 | HR |  |  | 70 | 0 | 805 | 104.65 | 909.65 | 2020-11-22 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX loading Rock truck all day, Sozer spreading gravel from C-107 - C-109. | 5 | C093-C116 | Cook Lake | 0 | 44161 |  | 50 | 44162 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting691120201122-11Driver - AZ - After Jan 1011.5805 | Corbiere and Sons Contracting691120201122-11Driver - AZ - After Jan 1011.5805Inv#081 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 805 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6912 | 20201122-12 | 53510504 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10 | Dynamic | 98.61 | 0 |  |  | 1314.8 | 170.924 | 1485.724 | 2020-11-22 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks, dozer spreading gravel from C-120Labourer on site working on geo. | 5 | C117-C124 | Mill Road South | 0 | 44161 |  | 50 | 44162 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting691220201122-12Dozer D6 or equal- After Jan 10101314.8 | Corbiere and Sons Contracting691220201122-12Dozer D6 or equal- After Jan 10101314.8Inv#081 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1314.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6912 | 20201122-12 | 53510504 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10 | Dynamic | 103.84 | 0 |  |  | 1384.5 | 179.985 | 1564.485 | 2020-11-22 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks, dozer spreading gravel from C-120Labourer on site working on geo. | 5 | C117-C124 | Mill Road South | 0 | 44161 |  | 50 | 44162 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting691220201122-12Excavator - 30 ton- After Jan 10101384.5 | Corbiere and Sons Contracting691220201122-12Excavator - 30 ton- After Jan 10101384.5Inv#081 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1384.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6912 | 20201122-12 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-11-22 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks, dozer spreading gravel from C-120Labourer on site working on geo. | 5 | C117-C124 | Mill Road South | 0 | 44161 |  | 50 | 44162 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting691220201122-12Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting691220201122-12Light Truck - Pick up- After Jan 102487.5Inv#081 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6912 | 20201122-12 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 10 | Dynamic | 103.54 | 0 |  |  | 1380.5 | 179.465 | 1559.965 | 2020-11-22 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks, dozer spreading gravel from C-120Labourer on site working on geo. | 5 | C117-C124 | Mill Road South | 0 | 44161 |  | 50 | 44162 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting691220201122-12Rock Truck - 30 Ton- After Jan 10101380.5 | Corbiere and Sons Contracting691220201122-12Rock Truck - 30 Ton- After Jan 10101380.5Inv#081 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1380.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6912 | 20201122-12 | 53510504 | Access | 0 | Foreman | 95 | 4 | HR |  |  | 95 | 0 | 380 | 49.4 | 429.4 | 2020-11-22 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks, dozer spreading gravel from C-120Labourer on site working on geo. | 5 | C117-C124 | Mill Road South | 0 | 44161 |  | 50 | 44162 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting691220201122-12Foreman4380 | Corbiere and Sons Contracting691220201122-12Foreman4380Inv#081 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6912 | 20201122-12 | 53510504 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2020-11-22 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks, dozer spreading gravel from C-120Labourer on site working on geo. | 5 | C117-C124 | Mill Road South | 0 | 44161 |  | 50 | 44162 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting691220201122-12L.O.A.4840 | Corbiere and Sons Contracting691220201122-12L.O.A.4840Inv#081 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6912 | 20201122-12 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 21 | HR |  |  | 75 | 0 | 1575 | 204.75 | 1779.75 | 2020-11-22 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks, dozer spreading gravel from C-120Labourer on site working on geo. | 5 | C117-C124 | Mill Road South | 0 | 44161 |  | 50 | 44162 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting691220201122-12Operator - Principle - After Jan 10211575 | Corbiere and Sons Contracting691220201122-12Operator - Principle - After Jan 10211575Inv#081 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1575 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6912 | 20201122-12 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 10.5 | HR |  |  | 70 | 0 | 735 | 95.55 | 830.55 | 2020-11-22 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks, dozer spreading gravel from C-120Labourer on site working on geo. | 5 | C117-C124 | Mill Road South | 0 | 44161 |  | 50 | 44162 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting691220201122-12Driver - AZ - After Jan 1010.5735 | Corbiere and Sons Contracting691220201122-12Driver - AZ - After Jan 1010.5735Inv#081 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 735 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6912 | 20201122-12 | 53510504 | Access | 0 | Labourer - General - After Jan 10 | 60 | 3 | HR |  |  | 60 | 0 | 180 | 23.4 | 203.4 | 2020-11-22 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks, dozer spreading gravel from C-120Labourer on site working on geo. | 5 | C117-C124 | Mill Road South | 0 | 44161 |  | 50 | 44162 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting691220201122-12Labourer - General - After Jan 103180 | Corbiere and Sons Contracting691220201122-12Labourer - General - After Jan 103180Inv#081 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 180 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6914 | 20201122-14 | 53510312 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10.5 | Dynamic | 98.61 | 0 |  |  | 1380.54 | 179.4702 | 1560.0102 | 2020-11-22 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixed road up for crane access in Landfill Rd | 3 | B078-B084 | Red Rock No. 7 | 0 | 44161 |  | 50 | 44162 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting691420201122-14Dozer D6 or equal- After Jan 1010.51380.54 | Corbiere and Sons Contracting691420201122-14Dozer D6 or equal- After Jan 1010.51380.54Inv#081 | [5 empty] | 1 | 1380.54 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6914 | 20201122-14 | 53510312 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 21 | Dynamic | 110.22 | 0 |  |  | 3086.16 | 401.2008 | 3487.3608 | 2020-11-22 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixed road up for crane access in Landfill Rd | 3 | B078-B084 | Red Rock No. 7 | 0 | 44161 |  | 50 | 44162 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting691420201122-14Excavator - 36 ton- After Jan 10213086.16 | Corbiere and Sons Contracting691420201122-14Excavator - 36 ton- After Jan 10213086.16Inv#081 | [5 empty] | 1 | 3086.16 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6914 | 20201122-14 | 53510312 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 21 | HR | 9.16 | 0 |  |  | 256.41 | 33.3333 | 289.7433 | 2020-11-22 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixed road up for crane access in Landfill Rd | 3 | B078-B084 | Red Rock No. 7 | 0 | 44161 |  | 50 | 44162 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting691420201122-14Excavator Thumb - 30 - 50 ton- After Jan 1021256.41 | Corbiere and Sons Contracting691420201122-14Excavator Thumb - 30 - 50 ton- After Jan 1021256.41Inv#081 | [5 empty] | 1 | 256.41 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6914 | 20201122-14 | 53510312 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-11-22 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixed road up for crane access in Landfill Rd | 3 | B078-B084 | Red Rock No. 7 | 0 | 44161 |  | 50 | 44162 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting691420201122-14Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting691420201122-14Light Truck - Pick up- After Jan 102487.5Inv#081 | [5 empty] | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6914 | 20201122-14 | 53510312 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 34.5 | HR |  |  | 75 | 0 | 2587.5 | 336.375 | 2923.875 | 2020-11-22 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Fixed road up for crane access in Landfill Rd | 3 | B078-B084 | Red Rock No. 7 | 0 | 44161 |  | 50 | 44162 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting691420201122-14Operator - Principle - After Jan 1034.52587.5 | Corbiere and Sons Contracting691420201122-14Operator - Principle - After Jan 1034.52587.5Inv#081 | [5 empty] | 1 | 2587.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6907 | 20201122-7 | 53510502 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 8 | Dynamic | 103.84 | 0 |  |  | 1107.6 | 143.988 | 1251.588 | 2020-11-22 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working on tying access to C-064 until machine went down. | 5 | C050-C069 | Antler Lake | 0 | 44161 |  | 50 | 44162 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting690720201122-7Excavator - 30 ton- After Jan 1081107.6 | Corbiere and Sons Contracting690720201122-7Excavator - 30 ton- After Jan 1081107.6Inv#081 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 1107.6 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6907 | 20201122-7 | 53510502 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 8 | HR | 9.16 | 0 |  |  | 97.68 | 12.6984 | 110.3784 | 2020-11-22 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working on tying access to C-064 until machine went down. | 5 | C050-C069 | Antler Lake | 0 | 44161 |  | 50 | 44162 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting690720201122-7Excavator Thumb - 30 - 50 ton- After Jan 10897.68 | Corbiere and Sons Contracting690720201122-7Excavator Thumb - 30 - 50 ton- After Jan 10897.68Inv#081 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 97.68 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6907 | 20201122-7 | 53510502 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-11-22 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working on tying access to C-064 until machine went down. | 5 | C050-C069 | Antler Lake | 0 | 44161 |  | 50 | 44162 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting690720201122-7Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting690720201122-7Light Truck - Pick up- After Jan 102487.5Inv#081 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6907 | 20201122-7 | 53510502 | Access | 0 | Foreman | 95 | 4 | HR |  |  | 95 | 0 | 380 | 49.4 | 429.4 | 2020-11-22 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working on tying access to C-064 until machine went down. | 5 | C050-C069 | Antler Lake | 0 | 44161 |  | 50 | 44162 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting690720201122-7Foreman4380 | Corbiere and Sons Contracting690720201122-7Foreman4380Inv#081 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6907 | 20201122-7 | 53510502 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-11-22 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working on tying access to C-064 until machine went down. | 5 | C050-C069 | Antler Lake | 0 | 44161 |  | 50 | 44162 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting690720201122-7L.O.A.1210 | Corbiere and Sons Contracting690720201122-7L.O.A.1210Inv#081 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6907 | 20201122-7 | 53510502 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 8.5 | HR |  |  | 75 | 0 | 637.5 | 82.875 | 720.375 | 2020-11-22 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working on tying access to C-064 until machine went down. | 5 | C050-C069 | Antler Lake | 0 | 44161 |  | 50 | 44162 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting690720201122-7Operator - Principle - After Jan 108.5637.5 | Corbiere and Sons Contracting690720201122-7Operator - Principle - After Jan 108.5637.5Inv#081 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 637.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6908 | 20201122-8 | 53510511 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 1 | Dynamic | 103.84 | 0 |  |  | 138.45 | 17.9985 | 156.4485 | 2020-11-22 | 1 | Inv#081 | 44173 | 128 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 15 | Approved | ROW INTERNAL - Sand for Road Maintenance - 3rd Party | 9015 | Sander truck working across access roads all day, EX005 loading sander truck - 1 hour billed for last 2 days of sanding. | 5 | C050-C069 | Antler Lake | 1 | 44161 |  | 50 | 44162 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting690820201122-8Excavator - 30 ton- After Jan 101138.45 | Corbiere and Sons Contracting690820201122-8Excavator - 30 ton- After Jan 101138.45Inv#081 | [5 empty] | 1 | 138.45 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6908 | 20201122-8 | 53510511 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 1 | HR | 9.16 | 0 |  |  | 12.21 | 1.5873 | 13.7973 | 2020-11-22 | 1 | Inv#081 | 44173 | 128 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 15 | Approved | ROW INTERNAL - Sand for Road Maintenance - 3rd Party | 9015 | Sander truck working across access roads all day, EX005 loading sander truck - 1 hour billed for last 2 days of sanding. | 5 | C050-C069 | Antler Lake | 1 | 44161 |  | 50 | 44162 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting690820201122-8Excavator Thumb - 30 - 50 ton- After Jan 10112.21 | Corbiere and Sons Contracting690820201122-8Excavator Thumb - 30 - 50 ton- After Jan 10112.21Inv#081 | [5 empty] | 1 | 12.21 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6908 | 20201122-8 | 53510511 | Access | 0 | Sander Truck - Hwy- After Jan 10 | 55 | 11 | Dynamic | 41.25 | 0 |  |  | 605 | 78.65 | 683.65 | 2020-11-22 | 1 | Inv#081 | 44173 | 128 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 15 | Approved | ROW INTERNAL - Sand for Road Maintenance - 3rd Party | 9015 | Sander truck working across access roads all day, EX005 loading sander truck - 1 hour billed for last 2 days of sanding. | 5 | C050-C069 | Antler Lake | 1 | 44161 |  | 50 | 44162 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting690820201122-8Sander Truck - Hwy- After Jan 1011605 | Corbiere and Sons Contracting690820201122-8Sander Truck - Hwy- After Jan 1011605Inv#081 | [5 empty] | 1 | 605 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6908 | 20201122-8 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-11-22 | 1 | Inv#081 | 44173 | 128 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 15 | Approved | ROW INTERNAL - Sand for Road Maintenance - 3rd Party | 9015 | Sander truck working across access roads all day, EX005 loading sander truck - 1 hour billed for last 2 days of sanding. | 5 | C050-C069 | Antler Lake | 1 | 44161 |  | 50 | 44162 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting690820201122-8L.O.A.1210 | Corbiere and Sons Contracting690820201122-8L.O.A.1210Inv#081 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6908 | 20201122-8 | 53510511 | Access | 0 | Labourer - General - After Jan 10 | 60 | 12 | HR |  |  | 60 | 0 | 720 | 93.6 | 813.6 | 2020-11-22 | 1 | Inv#081 | 44173 | 128 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 15 | Approved | ROW INTERNAL - Sand for Road Maintenance - 3rd Party | 9015 | Sander truck working across access roads all day, EX005 loading sander truck - 1 hour billed for last 2 days of sanding. | 5 | C050-C069 | Antler Lake | 1 | 44161 |  | 50 | 44162 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting690820201122-8Labourer - General - After Jan 1012720 | Corbiere and Sons Contracting690820201122-8Labourer - General - After Jan 1012720Inv#081 | [5 empty] | 1 | 720 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6927 | 20201123-11 | 53510511 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 5.5 | Dynamic | 98.61 | 0 |  |  | 723.14 | 94.0082 | 817.1482 | 2020-11-23 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator and dozer on winter maintenance and scrapping hills. | 5 | C050-C069 | Antler Lake | 0 | 44163 |  | 50 | 44165 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting692720201123-11Dozer D6 or equal- After Jan 105.5723.14 | Corbiere and Sons Contracting692720201123-11Dozer D6 or equal- After Jan 105.5723.14Inv#081 | [5 empty] | 1 | 723.14 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6927 | 20201123-11 | 53510511 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 4 | Dynamic | 103.84 | 0 |  |  | 553.8 | 71.994 | 625.794 | 2020-11-23 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator and dozer on winter maintenance and scrapping hills. | 5 | C050-C069 | Antler Lake | 0 | 44163 |  | 50 | 44165 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting692720201123-11Excavator - 30 ton- After Jan 104553.8 | Corbiere and Sons Contracting692720201123-11Excavator - 30 ton- After Jan 104553.8Inv#081 | [5 empty] | 1 | 553.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6927 | 20201123-11 | 53510511 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 4 | HR | 9.16 | 0 |  |  | 48.84 | 6.3492 | 55.1892 | 2020-11-23 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator and dozer on winter maintenance and scrapping hills. | 5 | C050-C069 | Antler Lake | 0 | 44163 |  | 50 | 44165 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting692720201123-11Excavator Thumb - 30 - 50 ton- After Jan 10448.84 | Corbiere and Sons Contracting692720201123-11Excavator Thumb - 30 - 50 ton- After Jan 10448.84Inv#081 | [5 empty] | 1 | 48.84 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6927 | 20201123-11 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-11-23 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator and dozer on winter maintenance and scrapping hills. | 5 | C050-C069 | Antler Lake | 0 | 44163 |  | 50 | 44165 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting692720201123-11Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting692720201123-11Light Truck - Pick up- After Jan 101243.75Inv#081 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6927 | 20201123-11 | 53510511 | Access | 0 | Foreman | 95 | 2 | HR |  |  | 95 | 0 | 190 | 24.7 | 214.7 | 2020-11-23 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator and dozer on winter maintenance and scrapping hills. | 5 | C050-C069 | Antler Lake | 0 | 44163 |  | 50 | 44165 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting692720201123-11Foreman2190 | Corbiere and Sons Contracting692720201123-11Foreman2190Inv#081 | [5 empty] | 1 | 190 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6927 | 20201123-11 | 53510511 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-11-23 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator and dozer on winter maintenance and scrapping hills. | 5 | C050-C069 | Antler Lake | 0 | 44163 |  | 50 | 44165 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting692720201123-11L.O.A.2420 | Corbiere and Sons Contracting692720201123-11L.O.A.2420Inv#081 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6927 | 20201123-11 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 10 | HR |  |  | 75 | 0 | 750 | 97.5 | 847.5 | 2020-11-23 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator and dozer on winter maintenance and scrapping hills. | 5 | C050-C069 | Antler Lake | 0 | 44163 |  | 50 | 44165 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting692720201123-11Operator - Principle - After Jan 1010750 | Corbiere and Sons Contracting692720201123-11Operator - Principle - After Jan 1010750Inv#081 | [5 empty] | 1 | 750 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6928 | 20201123-12 | 53510502 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 2 | Dynamic | 103.84 | 0 |  |  | 276.9 | 35.997 | 312.897 | 2020-11-23 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Completing tie in to C-064 | 5 | C050-C069 | Antler Lake | 0 | 44163 |  | 50 | 44165 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting692820201123-12Excavator - 30 ton- After Jan 102276.9 | Corbiere and Sons Contracting692820201123-12Excavator - 30 ton- After Jan 102276.9Inv#081 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 276.9 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6928 | 20201123-12 | 53510502 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 2 | HR | 9.16 | 0 |  |  | 24.42 | 3.1746 | 27.5946 | 2020-11-23 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Completing tie in to C-064 | 5 | C050-C069 | Antler Lake | 0 | 44163 |  | 50 | 44165 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting692820201123-12Excavator Thumb - 30 - 50 ton- After Jan 10224.42 | Corbiere and Sons Contracting692820201123-12Excavator Thumb - 30 - 50 ton- After Jan 10224.42Inv#081 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 24.42 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6928 | 20201123-12 | 53510502 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 2 | HR |  |  | 75 | 0 | 150 | 19.5 | 169.5 | 2020-11-23 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Completing tie in to C-064 | 5 | C050-C069 | Antler Lake | 0 | 44163 |  | 50 | 44165 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting692820201123-12Operator - Principle - After Jan 102150 | Corbiere and Sons Contracting692820201123-12Operator - Principle - After Jan 102150Inv#081 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 150 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6929 | 20201123-13 | 53550503 | Earthworks | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 2 | Dynamic | 103.84 | 0 |  |  | 276.9 | 35.997 | 312.897 | 2020-11-23 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Access Rock Blasting |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 2 hours cleaing up rock from hammering | 5 | C050-C069 | Antler Lake | 0 | 44163 |  | 50 | 44165 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting692920201123-13Excavator - 30 ton- After Jan 102276.9 | Corbiere and Sons Contracting692920201123-13Excavator - 30 ton- After Jan 102276.9Inv#081 |  | WF5-Earthwork | WF5-Earthwork |  | 1 | 1 | 276.9 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6929 | 20201123-13 | 53550503 | Earthworks | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 2 | HR | 9.16 | 0 |  |  | 24.42 | 3.1746 | 27.5946 | 2020-11-23 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Access Rock Blasting |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 2 hours cleaing up rock from hammering | 5 | C050-C069 | Antler Lake | 0 | 44163 |  | 50 | 44165 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting692920201123-13Excavator Thumb - 30 - 50 ton- After Jan 10224.42 | Corbiere and Sons Contracting692920201123-13Excavator Thumb - 30 - 50 ton- After Jan 10224.42Inv#081 |  | WF5-Earthwork | WF5-Earthwork |  | 1 | 1 | 24.42 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6929 | 20201123-13 | 53550503 | Earthworks | 0 | Operator - Principle - After Jan 10 | 75 | 2 | HR |  |  | 75 | 0 | 150 | 19.5 | 169.5 | 2020-11-23 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Access Rock Blasting |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | 2 hours cleaing up rock from hammering | 5 | C050-C069 | Antler Lake | 0 | 44163 |  | 50 | 44165 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting692920201123-13Operator - Principle - After Jan 102150 | Corbiere and Sons Contracting692920201123-13Operator - Principle - After Jan 102150Inv#081 |  | WF5-Earthwork | WF5-Earthwork |  | 1 | 1 | 150 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6931 | 20201123-15 | 53510504 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 5 | Dynamic | 98.61 | 0 |  |  | 657.4 | 85.462 | 742.862 | 2020-11-23 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel haul for C-050 - C-051 | 5 | C050-C069 | Antler Lake | 0 | 44163 |  | 50 | 44165 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting693120201123-15Dozer D6 or equal- After Jan 105657.4 | Corbiere and Sons Contracting693120201123-15Dozer D6 or equal- After Jan 105657.4Inv#081 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 657.4 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6931 | 20201123-15 | 53510504 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 5 | Dynamic | 103.84 | 0 |  |  | 692.25 | 89.9925 | 782.2425 | 2020-11-23 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel haul for C-050 - C-051 | 5 | C050-C069 | Antler Lake | 0 | 44163 |  | 50 | 44165 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting693120201123-15Excavator - 30 ton- After Jan 105692.25 | Corbiere and Sons Contracting693120201123-15Excavator - 30 ton- After Jan 105692.25Inv#081 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 692.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6931 | 20201123-15 | 53510504 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 5 | HR | 9.16 | 0 |  |  | 61.05 | 7.9365 | 68.9865 | 2020-11-23 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel haul for C-050 - C-051 | 5 | C050-C069 | Antler Lake | 0 | 44163 |  | 50 | 44165 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting693120201123-15Excavator Thumb - 30 - 50 ton- After Jan 10561.05 | Corbiere and Sons Contracting693120201123-15Excavator Thumb - 30 - 50 ton- After Jan 10561.05Inv#081 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 61.05 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6931 | 20201123-15 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-11-23 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel haul for C-050 - C-051 | 5 | C050-C069 | Antler Lake | 0 | 44163 |  | 50 | 44165 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting693120201123-15Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting693120201123-15Light Truck - Pick up- After Jan 101243.75Inv#081 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6931 | 20201123-15 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 5 | Dynamic | 103.54 | 0 |  |  | 690.25 | 89.7325 | 779.9825 | 2020-11-23 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel haul for C-050 - C-051 | 5 | C050-C069 | Antler Lake | 0 | 44163 |  | 50 | 44165 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting693120201123-15Rock Truck - 30 Ton- After Jan 105690.25 | Corbiere and Sons Contracting693120201123-15Rock Truck - 30 Ton- After Jan 105690.25Inv#081 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 690.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6931 | 20201123-15 | 53510504 | Access | 0 | Foreman | 95 | 2 | HR |  |  | 95 | 0 | 190 | 24.7 | 214.7 | 2020-11-23 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel haul for C-050 - C-051 | 5 | C050-C069 | Antler Lake | 0 | 44163 |  | 50 | 44165 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting693120201123-15Foreman2190 | Corbiere and Sons Contracting693120201123-15Foreman2190Inv#081 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 190 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6931 | 20201123-15 | 53510504 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-11-23 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel haul for C-050 - C-051 | 5 | C050-C069 | Antler Lake | 0 | 44163 |  | 50 | 44165 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting693120201123-15L.O.A.2420 | Corbiere and Sons Contracting693120201123-15L.O.A.2420Inv#081 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6931 | 20201123-15 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2020-11-23 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel haul for C-050 - C-051 | 5 | C050-C069 | Antler Lake | 0 | 44163 |  | 50 | 44165 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting693120201123-15Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting693120201123-15Operator - Principle - After Jan 1011825Inv#081 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6931 | 20201123-15 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 5.5 | HR |  |  | 70 | 0 | 385 | 50.05 | 435.05 | 2020-11-23 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel haul for C-050 - C-051 | 5 | C050-C069 | Antler Lake | 0 | 44163 |  | 50 | 44165 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting693120201123-15Driver - AZ - After Jan 105.5385 | Corbiere and Sons Contracting693120201123-15Driver - AZ - After Jan 105.5385Inv#081 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 385 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6934 | 20201123-18 | 53510511 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 6 | Dynamic | 110.22 | 0 |  |  | 881.76 | 114.6288 | 996.3888 | 2020-11-23 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Labourer on sander truck all day working across Cooks Lake access Roads, Excavator scrapping snow for access | 5 | C076-C116 | Cook Lake | 0 | 44163 |  | 50 | 44165 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting693420201123-18Excavator - 36 ton- After Jan 106881.76 | Corbiere and Sons Contracting693420201123-18Excavator - 36 ton- After Jan 106881.76Inv#081 | [5 empty] | 1 | 881.76 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6934 | 20201123-18 | 53510511 | Access | 0 | Sander Truck - Hwy- After Jan 10 | 55 | 11.5 | Dynamic | 41.25 | 0 |  |  | 632.5 | 82.225 | 714.725 | 2020-11-23 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Labourer on sander truck all day working across Cooks Lake access Roads, Excavator scrapping snow for access | 5 | C076-C116 | Cook Lake | 0 | 44163 |  | 50 | 44165 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting693420201123-18Sander Truck - Hwy- After Jan 1011.5632.5 | Corbiere and Sons Contracting693420201123-18Sander Truck - Hwy- After Jan 1011.5632.5Inv#081 | [5 empty] | 1 | 632.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6934 | 20201123-18 | 53510511 | Access | 0 | Foreman | 95 | 3 | HR |  |  | 95 | 0 | 285 | 37.05 | 322.05 | 2020-11-23 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Labourer on sander truck all day working across Cooks Lake access Roads, Excavator scrapping snow for access | 5 | C076-C116 | Cook Lake | 0 | 44163 |  | 50 | 44165 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting693420201123-18Foreman3285 | Corbiere and Sons Contracting693420201123-18Foreman3285Inv#081 | [5 empty] | 1 | 285 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6934 | 20201123-18 | 53510511 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2020-11-23 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Labourer on sander truck all day working across Cooks Lake access Roads, Excavator scrapping snow for access | 5 | C076-C116 | Cook Lake | 0 | 44163 |  | 50 | 44165 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting693420201123-18L.O.A.3630 | Corbiere and Sons Contracting693420201123-18L.O.A.3630Inv#081 | [5 empty] | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6934 | 20201123-18 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 75 | 0 | 450 | 58.5 | 508.5 | 2020-11-23 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Labourer on sander truck all day working across Cooks Lake access Roads, Excavator scrapping snow for access | 5 | C076-C116 | Cook Lake | 0 | 44163 |  | 50 | 44165 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting693420201123-18Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting693420201123-18Operator - Principle - After Jan 106450Inv#081 | [5 empty] | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6934 | 20201123-18 | 53510511 | Access | 0 | Labourer - General - After Jan 10 | 60 | 12 | HR |  |  | 60 | 0 | 720 | 93.6 | 813.6 | 2020-11-23 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Labourer on sander truck all day working across Cooks Lake access Roads, Excavator scrapping snow for access | 5 | C076-C116 | Cook Lake | 0 | 44163 |  | 50 | 44165 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting693420201123-18Labourer - General - After Jan 1012720 | Corbiere and Sons Contracting693420201123-18Labourer - General - After Jan 1012720Inv#081 | [5 empty] | 1 | 720 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6940 | 20201123-24 | 53510312 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 1 | Dynamic | 110.22 | 0 |  |  | 146.96 | 19.1048 | 166.0648 | 2020-11-23 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved excavator from Landfill to Camp 81 laydown. | 3 | B078-B084 | Red Rock Road No. 7 | 0 | 44163 |  | 50 | 44165 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting694020201123-24Excavator - 36 ton- After Jan 101146.96 | Corbiere and Sons Contracting694020201123-24Excavator - 36 ton- After Jan 101146.96Inv#081 | [5 empty] | 1 | 146.96 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6940 | 20201123-24 | 53510312 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 1 | HR | 9.16 | 0 |  |  | 12.21 | 1.5873 | 13.7973 | 2020-11-23 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved excavator from Landfill to Camp 81 laydown. | 3 | B078-B084 | Red Rock Road No. 7 | 0 | 44163 |  | 50 | 44165 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting694020201123-24Excavator Thumb - 30 - 50 ton- After Jan 10112.21 | Corbiere and Sons Contracting694020201123-24Excavator Thumb - 30 - 50 ton- After Jan 10112.21Inv#081 | [5 empty] | 1 | 12.21 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6940 | 20201123-24 | 53510312 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-11-23 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved excavator from Landfill to Camp 81 laydown. | 3 | B078-B084 | Red Rock Road No. 7 | 0 | 44163 |  | 50 | 44165 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting694020201123-24Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting694020201123-24Light Truck - Pick up- After Jan 101243.75Inv#081 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6940 | 20201123-24 | 53510312 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 7 | HR |  |  | 75 | 0 | 525 | 68.25 | 593.25 | 2020-11-23 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved excavator from Landfill to Camp 81 laydown. | 3 | B078-B084 | Red Rock Road No. 7 | 0 | 44163 |  | 50 | 44165 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting694020201123-24Operator - Principle - After Jan 107525 | Corbiere and Sons Contracting694020201123-24Operator - Principle - After Jan 107525Inv#081 | [5 empty] | 1 | 525 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6941 | 20201123-25 | 53510312 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 2 | Dynamic | 95.24 | 0 |  |  | 253.96 | 33.0148 | 286.9748 | 2020-11-23 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Operator and labourer took chains off grader and drove from Maata's Rd to North Shore yard. | 3 | B088-B099 | Maata's Road | 0 | 44163 |  | 50 | 44165 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting694120201123-25Grader - Cat 12 to 14 or equal- After Jan 102253.96 | Corbiere and Sons Contracting694120201123-25Grader - Cat 12 to 14 or equal- After Jan 102253.96Inv#081 | [5 empty] | 1 | 253.96 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6941 | 20201123-25 | 53510312 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 2 | HR |  |  | 75 | 0 | 150 | 19.5 | 169.5 | 2020-11-23 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Operator and labourer took chains off grader and drove from Maata's Rd to North Shore yard. | 3 | B088-B099 | Maata's Road | 0 | 44163 |  | 50 | 44165 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting694120201123-25Operator - Principle - After Jan 102150 | Corbiere and Sons Contracting694120201123-25Operator - Principle - After Jan 102150Inv#081 | [5 empty] | 1 | 150 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6941 | 20201123-25 | 53510312 | Access | 0 | Labourer - General - After Jan 10 | 60 | 2 | HR |  |  | 60 | 0 | 120 | 15.6 | 135.6 | 2020-11-23 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Operator and labourer took chains off grader and drove from Maata's Rd to North Shore yard. | 3 | B088-B099 | Maata's Road | 0 | 44163 |  | 50 | 44165 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting694120201123-25Labourer - General - After Jan 102120 | Corbiere and Sons Contracting694120201123-25Labourer - General - After Jan 102120Inv#081 | [5 empty] | 1 | 120 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6948 | 20201123-33 | 53510511 | Access | 0 | 3rd Party Charges | 1 | 789.26 | unit |  |  |  |  | 789.26 | 102.6038 | 891.8638 | 2020-11-23 | 1 | Inv#082 | 44181 | 130 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 15 | Approved | ROW INTERNAL - Sand for Road Maintenance - 3rd Party | 9015 | Sand used for winter access maintenance on Cooks and Antler Lake Rd | 5 | C050-C069 | Antler Lake | 0 | 44163 |  | 36 | 44113 | 0154 | Loaded and delivered Sand to Terrace Bay Yard |  |  |  | Mike Lecocq | 05 | Corbiere and Sons Contracting694820201123-333rd Party Charges789.26789.26 | Corbiere and Sons Contracting694820201123-333rd Party Charges789.26789.26Inv#082 | [5 empty] | 1 | 789.26 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6961 | 20201124-12 | 53510511 | Access | 0 | Sander Truck - Hwy- After Jan 10 | 55 | 10.5 | Dynamic | 41.25 | 0 |  |  | 577.5 | 75.075 | 652.575 | 2020-11-24 | 1 | Inv#081 | 44173 | 128 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 15 | Approved | ROW INTERNAL - Sand for Road Maintenance - 3rd Party | 9015 | Labourer running sander truck all day | 5 | C093-C116 | Cook Lake | 1 | 44163 |  | 50 | 44165 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting696120201124-12Sander Truck - Hwy- After Jan 1010.5577.5 | Corbiere and Sons Contracting696120201124-12Sander Truck - Hwy- After Jan 1010.5577.5Inv#081 | [5 empty] | 1 | 577.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6961 | 20201124-12 | 53510511 | Access | 0 | ATV - Side by Side w/ roll bar- After Jan 10 | 18.45 | 2 | HR | 13.84 | 0 |  |  | 36.9 | 4.797 | 41.697 | 2020-11-24 | 1 | Inv#081 | 44173 | 128 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 15 | Approved | ROW INTERNAL - Sand for Road Maintenance - 3rd Party | 9015 | Labourer running sander truck all day | 5 | C093-C116 | Cook Lake | 1 | 44163 |  | 50 | 44165 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting696120201124-12ATV - Side by Side w/ roll bar- After Jan 10236.9 | Corbiere and Sons Contracting696120201124-12ATV - Side by Side w/ roll bar- After Jan 10236.9Inv#081 | [5 empty] | 1 | 36.9 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6961 | 20201124-12 | 53510511 | Access | 0 | Foreman | 95 | 2 | HR |  |  | 95 | 0 | 190 | 24.7 | 214.7 | 2020-11-24 | 1 | Inv#081 | 44173 | 128 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 15 | Approved | ROW INTERNAL - Sand for Road Maintenance - 3rd Party | 9015 | Labourer running sander truck all day | 5 | C093-C116 | Cook Lake | 1 | 44163 |  | 50 | 44165 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting696120201124-12Foreman2190 | Corbiere and Sons Contracting696120201124-12Foreman2190Inv#081 | [5 empty] | 1 | 190 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6961 | 20201124-12 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-11-24 | 1 | Inv#081 | 44173 | 128 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 15 | Approved | ROW INTERNAL - Sand for Road Maintenance - 3rd Party | 9015 | Labourer running sander truck all day | 5 | C093-C116 | Cook Lake | 1 | 44163 |  | 50 | 44165 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting696120201124-12L.O.A.1210 | Corbiere and Sons Contracting696120201124-12L.O.A.1210Inv#081 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6961 | 20201124-12 | 53510511 | Access | 0 | Labourer - General - After Jan 10 | 60 | 11.5 | HR |  |  | 60 | 0 | 690 | 89.7 | 779.7 | 2020-11-24 | 1 | Inv#081 | 44173 | 128 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 15 | Approved | ROW INTERNAL - Sand for Road Maintenance - 3rd Party | 9015 | Labourer running sander truck all day | 5 | C093-C116 | Cook Lake | 1 | 44163 |  | 50 | 44165 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting696120201124-12Labourer - General - After Jan 1011.5690 | Corbiere and Sons Contracting696120201124-12Labourer - General - After Jan 1011.5690Inv#081 | [5 empty] | 1 | 690 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6962 | 20201124-13 | 53510512 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10.5 | Dynamic | 110.22 | 0 |  |  | 1543.08 | 200.6004 | 1743.6804 | 2020-11-24 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-011 doing road maintenance from C-100 - C-109 | 5 | C076-C092 | Cook Lake | 0 | 44163 |  | 50 | 44165 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting696220201124-13Excavator - 36 ton- After Jan 1010.51543.08 | Corbiere and Sons Contracting696220201124-13Excavator - 36 ton- After Jan 1010.51543.08Inv#081 | [5 empty] | 1 | 1543.08 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6962 | 20201124-13 | 53510512 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-11-24 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-011 doing road maintenance from C-100 - C-109 | 5 | C076-C092 | Cook Lake | 0 | 44163 |  | 50 | 44165 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting696220201124-13Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting696220201124-13Light Truck - Pick up- After Jan 101243.75Inv#081 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6962 | 20201124-13 | 53510512 | Access | 0 | Foreman | 95 | 2 | HR |  |  | 95 | 0 | 190 | 24.7 | 214.7 | 2020-11-24 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-011 doing road maintenance from C-100 - C-109 | 5 | C076-C092 | Cook Lake | 0 | 44163 |  | 50 | 44165 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting696220201124-13Foreman2190 | Corbiere and Sons Contracting696220201124-13Foreman2190Inv#081 | [5 empty] | 1 | 190 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6962 | 20201124-13 | 53510512 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-11-24 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-011 doing road maintenance from C-100 - C-109 | 5 | C076-C092 | Cook Lake | 0 | 44163 |  | 50 | 44165 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting696220201124-13L.O.A.1210 | Corbiere and Sons Contracting696220201124-13L.O.A.1210Inv#081 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6962 | 20201124-13 | 53510512 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-11-24 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-011 doing road maintenance from C-100 - C-109 | 5 | C076-C092 | Cook Lake | 0 | 44163 |  | 50 | 44165 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting696220201124-13Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting696220201124-13Operator - Principle - After Jan 1011.5862.5Inv#081 | [5 empty] | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6963 | 20201124-14 | 53510504 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 6.5 | Dynamic | 98.61 | 0 |  |  | 854.62 | 111.1006 | 965.7206 | 2020-11-24 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks, rock truck hauling gravel, dozer spreading gravel | 5 | C076-C116 | Cook Lake | 0 | 44163 |  | 50 | 44165 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting696320201124-14Dozer D6 or equal- After Jan 106.5854.62 | Corbiere and Sons Contracting696320201124-14Dozer D6 or equal- After Jan 106.5854.62Inv#081 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 854.62 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6963 | 20201124-14 | 53510504 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 6.5 | Dynamic | 110.22 | 0 |  |  | 955.24 | 124.1812 | 1079.4212 | 2020-11-24 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks, rock truck hauling gravel, dozer spreading gravel | 5 | C076-C116 | Cook Lake | 0 | 44163 |  | 50 | 44165 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting696320201124-14Excavator - 36 ton- After Jan 106.5955.24 | Corbiere and Sons Contracting696320201124-14Excavator - 36 ton- After Jan 106.5955.24Inv#081 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 955.24 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6963 | 20201124-14 | 53510504 | Access | 0 | ATV - Side by Side w/ roll bar- After Jan 10 | 18.45 | 4 | HR | 13.84 | 0 |  |  | 73.8 | 9.594 | 83.394 | 2020-11-24 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks, rock truck hauling gravel, dozer spreading gravel | 5 | C076-C116 | Cook Lake | 0 | 44163 |  | 50 | 44165 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting696320201124-14ATV - Side by Side w/ roll bar- After Jan 10473.8 | Corbiere and Sons Contracting696320201124-14ATV - Side by Side w/ roll bar- After Jan 10473.8Inv#081 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 73.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6963 | 20201124-14 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-11-24 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks, rock truck hauling gravel, dozer spreading gravel | 5 | C076-C116 | Cook Lake | 0 | 44163 |  | 50 | 44165 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting696320201124-14Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting696320201124-14Light Truck - Pick up- After Jan 102487.5Inv#081 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6963 | 20201124-14 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 10.5 | Dynamic | 103.54 | 0 |  |  | 1449.525 | 188.4383 | 1637.9633 | 2020-11-24 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks, rock truck hauling gravel, dozer spreading gravel | 5 | C076-C116 | Cook Lake | 0 | 44163 |  | 50 | 44165 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting696320201124-14Rock Truck - 30 Ton- After Jan 1010.51449.525 | Corbiere and Sons Contracting696320201124-14Rock Truck - 30 Ton- After Jan 1010.51449.525Inv#081 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1449.525 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6963 | 20201124-14 | 53510504 | Access | 0 | Foreman | 95 | 4 | HR |  |  | 95 | 0 | 380 | 49.4 | 429.4 | 2020-11-24 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks, rock truck hauling gravel, dozer spreading gravel | 5 | C076-C116 | Cook Lake | 0 | 44163 |  | 50 | 44165 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting696320201124-14Foreman4380 | Corbiere and Sons Contracting696320201124-14Foreman4380Inv#081 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6963 | 20201124-14 | 53510504 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2020-11-24 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks, rock truck hauling gravel, dozer spreading gravel | 5 | C076-C116 | Cook Lake | 0 | 44163 |  | 50 | 44165 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting696320201124-14L.O.A.4840 | Corbiere and Sons Contracting696320201124-14L.O.A.4840Inv#081 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6963 | 20201124-14 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 15 | HR |  |  | 75 | 0 | 1125 | 146.25 | 1271.25 | 2020-11-24 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks, rock truck hauling gravel, dozer spreading gravel | 5 | C076-C116 | Cook Lake | 0 | 44163 |  | 50 | 44165 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting696320201124-14Operator - Principle - After Jan 10151125 | Corbiere and Sons Contracting696320201124-14Operator - Principle - After Jan 10151125Inv#081 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1125 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6963 | 20201124-14 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 11.5 | HR |  |  | 70 | 0 | 805 | 104.65 | 909.65 | 2020-11-24 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks, rock truck hauling gravel, dozer spreading gravel | 5 | C076-C116 | Cook Lake | 0 | 44163 |  | 50 | 44165 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting696320201124-14Driver - AZ - After Jan 1011.5805 | Corbiere and Sons Contracting696320201124-14Driver - AZ - After Jan 1011.5805Inv#081 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 805 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6964 | 20201124-15 | 53530501 | Rig/Access Mats | 0 | Skidder | 171 | 10.5 | HR | 128.25 | 0 |  |  | 1795.5 | 233.415 | 2028.915 | 2020-11-24 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Rig/Access Mat Handling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Skidder dragging rig mats from laydown to C-109 all day | 5 | C093-C116 | Cook Lake | 0 | 44163 |  | 50 | 44165 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting696420201124-15Skidder 10.51795.5 | Corbiere and Sons Contracting696420201124-15Skidder 10.51795.5Inv#081 |  |  | WF5-WaterCrossing |  |  | 0.5 | 897.75 | WC409 | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6964 | 20201124-15 | 53530501 | Rig/Access Mats | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-11-24 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Rig/Access Mat Handling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Skidder dragging rig mats from laydown to C-109 all day | 5 | C093-C116 | Cook Lake | 0 | 44163 |  | 50 | 44165 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting696420201124-15Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting696420201124-15Light Truck - Pick up- After Jan 101243.75Inv#081 |  |  | WF5-WaterCrossing |  |  | 0.5 | 121.875 | WC409 | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6964 | 20201124-15 | 53530501 | Rig/Access Mats | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-11-24 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Rig/Access Mat Handling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Skidder dragging rig mats from laydown to C-109 all day | 5 | C093-C116 | Cook Lake | 0 | 44163 |  | 50 | 44165 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting696420201124-15L.O.A.1210 | Corbiere and Sons Contracting696420201124-15L.O.A.1210Inv#081 |  |  | WF5-WaterCrossing |  |  | 0.5 | 105 | WC409 | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6964 | 20201124-15 | 53530501 | Rig/Access Mats | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-11-24 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Rig/Access Mat Handling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Skidder dragging rig mats from laydown to C-109 all day | 5 | C093-C116 | Cook Lake | 0 | 44163 |  | 50 | 44165 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting696420201124-15Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting696420201124-15Operator - Principle - After Jan 1011.5862.5Inv#081 |  |  | WF5-WaterCrossing |  |  | 0.5 | 431.25 | WC409 | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6965 | 20201124-16 | 53510212 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 4 | Dynamic | 98.61 | 0 |  |  | 525.92 | 68.3696 | 594.2896 | 2020-11-24 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float walked dozer out of Little Gravel and floated over to Lofty Davies and walked in and cleared snow and broke up ice on hill at B-063 Lofty Davies Road | 2 | B054 - B064 | Lofty Davies | 0 | 44163 |  | 50 | 44165 | [5 empty] | Wes Seminowich | 02 | Corbiere and Sons Contracting696520201124-16Dozer D6 or equal- After Jan 104525.92 | Corbiere and Sons Contracting696520201124-16Dozer D6 or equal- After Jan 104525.92Inv#081 | [5 empty] | 1 | 525.92 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6965 | 20201124-16 | 53510212 | Access | 0 | Tractor Trailer - 50 Ton- After Jan 10 | 111.75 | 2 | Dynamic | 83.81 | 0 |  |  | 223.5 | 29.055 | 252.555 | 2020-11-24 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float walked dozer out of Little Gravel and floated over to Lofty Davies and walked in and cleared snow and broke up ice on hill at B-063 Lofty Davies Road | 2 | B054 - B064 | Lofty Davies | 0 | 44163 |  | 50 | 44165 | [5 empty] | Wes Seminowich | 02 | Corbiere and Sons Contracting696520201124-16Tractor Trailer - 50 Ton- After Jan 102223.5 | Corbiere and Sons Contracting696520201124-16Tractor Trailer - 50 Ton- After Jan 102223.5Inv#081 | [5 empty] | 1 | 223.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6965 | 20201124-16 | 53510212 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 4 | HR |  |  | 75 | 0 | 300 | 39 | 339 | 2020-11-24 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float walked dozer out of Little Gravel and floated over to Lofty Davies and walked in and cleared snow and broke up ice on hill at B-063 Lofty Davies Road | 2 | B054 - B064 | Lofty Davies | 0 | 44163 |  | 50 | 44165 | [5 empty] | Wes Seminowich | 02 | Corbiere and Sons Contracting696520201124-16Operator - Principle - After Jan 104300 | Corbiere and Sons Contracting696520201124-16Operator - Principle - After Jan 104300Inv#081 | [5 empty] | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6965 | 20201124-16 | 53510212 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 2 | HR |  |  | 70 | 0 | 140 | 18.2 | 158.2 | 2020-11-24 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float walked dozer out of Little Gravel and floated over to Lofty Davies and walked in and cleared snow and broke up ice on hill at B-063 Lofty Davies Road | 2 | B054 - B064 | Lofty Davies | 0 | 44163 |  | 50 | 44165 | [5 empty] | Wes Seminowich | 02 | Corbiere and Sons Contracting696520201124-16Driver - AZ - After Jan 102140 | Corbiere and Sons Contracting696520201124-16Driver - AZ - After Jan 102140Inv#081 | [5 empty] | 1 | 140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6965 | 20201124-16 | 53510212 | Access | 0 | Labourer - General - After Jan 10 | 60 | 4 | HR |  |  | 60 | 0 | 240 | 31.2 | 271.2 | 2020-11-24 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float walked dozer out of Little Gravel and floated over to Lofty Davies and walked in and cleared snow and broke up ice on hill at B-063 Lofty Davies Road | 2 | B054 - B064 | Lofty Davies | 0 | 44163 |  | 50 | 44165 | [5 empty] | Wes Seminowich | 02 | Corbiere and Sons Contracting696520201124-16Labourer - General - After Jan 104240 | Corbiere and Sons Contracting696520201124-16Labourer - General - After Jan 104240Inv#081 | [5 empty] | 1 | 240 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6970 | 20201124-21 | 53510412 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 8 | Dynamic | 98.61 | 0 |  |  | 1051.84 | 136.7392 | 1188.5792 | 2020-11-24 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-09 scrapped hill at C-018, DZ-04 trimmed road and filled in ruts from C-027 - C-007 Nishin Lake RdLabourer bumped vehicles around for all the different moves. | 4 | C011-C029 | Nishin Lake Road | 0 | 44163 |  | 50 | 44165 | [5 empty] | Wes Seminowich | 04 | Corbiere and Sons Contracting697020201124-21Dozer D6 or equal- After Jan 1081051.84 | Corbiere and Sons Contracting697020201124-21Dozer D6 or equal- After Jan 1081051.84Inv#081 | [5 empty] | 1 | 1051.84 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6970 | 20201124-21 | 53510412 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 3 | Dynamic | 110.22 | 0 |  |  | 440.88 | 57.3144 | 498.1944 | 2020-11-24 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-09 scrapped hill at C-018, DZ-04 trimmed road and filled in ruts from C-027 - C-007 Nishin Lake RdLabourer bumped vehicles around for all the different moves. | 4 | C011-C029 | Nishin Lake Road | 0 | 44163 |  | 50 | 44165 | [5 empty] | Wes Seminowich | 04 | Corbiere and Sons Contracting697020201124-21Excavator - 36 ton- After Jan 103440.88 | Corbiere and Sons Contracting697020201124-21Excavator - 36 ton- After Jan 103440.88Inv#081 | [5 empty] | 1 | 440.88 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6970 | 20201124-21 | 53510412 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 3 | HR | 9.16 | 0 |  |  | 36.63 | 4.7619 | 41.3919 | 2020-11-24 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-09 scrapped hill at C-018, DZ-04 trimmed road and filled in ruts from C-027 - C-007 Nishin Lake RdLabourer bumped vehicles around for all the different moves. | 4 | C011-C029 | Nishin Lake Road | 0 | 44163 |  | 50 | 44165 | [5 empty] | Wes Seminowich | 04 | Corbiere and Sons Contracting697020201124-21Excavator Thumb - 30 - 50 ton- After Jan 10336.63 | Corbiere and Sons Contracting697020201124-21Excavator Thumb - 30 - 50 ton- After Jan 10336.63Inv#081 | [5 empty] | 1 | 36.63 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6970 | 20201124-21 | 53510412 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-11-24 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-09 scrapped hill at C-018, DZ-04 trimmed road and filled in ruts from C-027 - C-007 Nishin Lake RdLabourer bumped vehicles around for all the different moves. | 4 | C011-C029 | Nishin Lake Road | 0 | 44163 |  | 50 | 44165 | [5 empty] | Wes Seminowich | 04 | Corbiere and Sons Contracting697020201124-21Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting697020201124-21Light Truck - Pick up- After Jan 101243.75Inv#081 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6970 | 20201124-21 | 53510412 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2020-11-24 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-09 scrapped hill at C-018, DZ-04 trimmed road and filled in ruts from C-027 - C-007 Nishin Lake RdLabourer bumped vehicles around for all the different moves. | 4 | C011-C029 | Nishin Lake Road | 0 | 44163 |  | 50 | 44165 | [5 empty] | Wes Seminowich | 04 | Corbiere and Sons Contracting697020201124-21Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting697020201124-21Operator - Principle - After Jan 1012900Inv#081 | [5 empty] | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6970 | 20201124-21 | 53510412 | Access | 0 | Labourer - General - After Jan 10 | 60 | 2 | HR |  |  | 60 | 0 | 120 | 15.6 | 135.6 | 2020-11-24 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-09 scrapped hill at C-018, DZ-04 trimmed road and filled in ruts from C-027 - C-007 Nishin Lake RdLabourer bumped vehicles around for all the different moves. | 4 | C011-C029 | Nishin Lake Road | 0 | 44163 |  | 50 | 44165 | [5 empty] | Wes Seminowich | 04 | Corbiere and Sons Contracting697020201124-21Labourer - General - After Jan 102120 | Corbiere and Sons Contracting697020201124-21Labourer - General - After Jan 102120Inv#081 | [5 empty] | 1 | 120 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7187 | 20201124-26 | 53510511 | Access | 0 | 3rd Party Charges | 1 | 1038.57 | unit |  |  |  |  | 1038.57 | 135.0141 | 1173.5841 | 2020-11-24 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Supply and delivery of screen sand for Cooks and Antler Lake Rds | 5 | C076-C116 | Cook Lake | 0 | 44173 |  | 37 | 44173 | 18113 | Supply and Delivery of Screen Sand |  |  |  | Harold Furlong | 05 | Corbiere and Sons Contracting718720201124-263rd Party Charges1038.571038.57 | Corbiere and Sons Contracting718720201124-263rd Party Charges1038.571038.57Inv#082 | [5 empty] | 1 | 1038.57 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6957 | 20201124-8 | 53510504 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10.5 | Dynamic | 98.61 | 0 |  |  | 1380.54 | 179.4702 | 1560.0102 | 2020-11-24 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock truck for haul and spreadRock truck hauling C-050Dozer spreading gravel from C-050 | 5 | C050-C069 | Antler Lake | 0 | 44163 |  | 50 | 44165 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting695720201124-8Dozer D6 or equal- After Jan 1010.51380.54 | Corbiere and Sons Contracting695720201124-8Dozer D6 or equal- After Jan 1010.51380.54Inv#081 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1380.54 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6957 | 20201124-8 | 53510504 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10.5 | Dynamic | 103.84 | 0 |  |  | 1453.725 | 188.9843 | 1642.7093 | 2020-11-24 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock truck for haul and spreadRock truck hauling C-050Dozer spreading gravel from C-050 | 5 | C050-C069 | Antler Lake | 0 | 44163 |  | 50 | 44165 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting695720201124-8Excavator - 30 ton- After Jan 1010.51453.725 | Corbiere and Sons Contracting695720201124-8Excavator - 30 ton- After Jan 1010.51453.725Inv#081 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1453.725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6957 | 20201124-8 | 53510504 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10.5 | HR | 9.16 | 0 |  |  | 128.205 | 16.6667 | 144.8716 | 2020-11-24 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock truck for haul and spreadRock truck hauling C-050Dozer spreading gravel from C-050 | 5 | C050-C069 | Antler Lake | 0 | 44163 |  | 50 | 44165 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting695720201124-8Excavator Thumb - 30 - 50 ton- After Jan 1010.5128.205 | Corbiere and Sons Contracting695720201124-8Excavator Thumb - 30 - 50 ton- After Jan 1010.5128.205Inv#081 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 128.205 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6957 | 20201124-8 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2020-11-24 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock truck for haul and spreadRock truck hauling C-050Dozer spreading gravel from C-050 | 5 | C050-C069 | Antler Lake | 0 | 44163 |  | 50 | 44165 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting695720201124-8Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting695720201124-8Light Truck - Pick up- After Jan 103731.25Inv#081 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 731.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6957 | 20201124-8 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 10.5 | Dynamic | 103.54 | 0 |  |  | 1449.525 | 188.4383 | 1637.9633 | 2020-11-24 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock truck for haul and spreadRock truck hauling C-050Dozer spreading gravel from C-050 | 5 | C050-C069 | Antler Lake | 0 | 44163 |  | 50 | 44165 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting695720201124-8Rock Truck - 30 Ton- After Jan 1010.51449.525 | Corbiere and Sons Contracting695720201124-8Rock Truck - 30 Ton- After Jan 1010.51449.525Inv#081 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1449.525 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6957 | 20201124-8 | 53510504 | Access | 0 | Foreman | 95 | 10 | HR |  |  | 95 | 0 | 950 | 123.5 | 1073.5 | 2020-11-24 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock truck for haul and spreadRock truck hauling C-050Dozer spreading gravel from C-050 | 5 | C050-C069 | Antler Lake | 0 | 44163 |  | 50 | 44165 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting695720201124-8Foreman10950 | Corbiere and Sons Contracting695720201124-8Foreman10950Inv#081 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 950 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6957 | 20201124-8 | 53510504 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2020-11-24 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock truck for haul and spreadRock truck hauling C-050Dozer spreading gravel from C-050 | 5 | C050-C069 | Antler Lake | 0 | 44163 |  | 50 | 44165 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting695720201124-8L.O.A.4840 | Corbiere and Sons Contracting695720201124-8L.O.A.4840Inv#081 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 6957 | 20201124-8 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 34.5 | HR |  |  | 75 | 0 | 2587.5 | 336.375 | 2923.875 | 2020-11-24 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock truck for haul and spreadRock truck hauling C-050Dozer spreading gravel from C-050 | 5 | C050-C069 | Antler Lake | 0 | 44163 |  | 50 | 44165 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting695720201124-8Operator - Principle - After Jan 1034.52587.5 | Corbiere and Sons Contracting695720201124-8Operator - Principle - After Jan 1034.52587.5Inv#081 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 2587.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7012 | 20201125-12 | 53510312 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 8 | Dynamic | 98.61 | 0 |  |  | 1051.84 | 136.7392 | 1188.5792 | 2020-11-25 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer cleared snow and broke up icy patches in Landfill Rd, Labourer bumped operators trck to the back of Landfill Rd. | 3 | B078-B084 | Red Rock Rd No. 7 | 0 | 44165 |  | 50 | 44168 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting701220201125-12Dozer D6 or equal- After Jan 1081051.84 | Corbiere and Sons Contracting701220201125-12Dozer D6 or equal- After Jan 1081051.84Inv#081 | [5 empty] | 1 | 1051.84 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7012 | 20201125-12 | 53510312 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-11-25 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer cleared snow and broke up icy patches in Landfill Rd, Labourer bumped operators trck to the back of Landfill Rd. | 3 | B078-B084 | Red Rock Rd No. 7 | 0 | 44165 |  | 50 | 44168 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting701220201125-12Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting701220201125-12Light Truck - Pick up- After Jan 101243.75Inv#081 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7012 | 20201125-12 | 53510312 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 8.5 | HR |  |  | 75 | 0 | 637.5 | 82.875 | 720.375 | 2020-11-25 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer cleared snow and broke up icy patches in Landfill Rd, Labourer bumped operators trck to the back of Landfill Rd. | 3 | B078-B084 | Red Rock Rd No. 7 | 0 | 44165 |  | 50 | 44168 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting701220201125-12Operator - Principle - After Jan 108.5637.5 | Corbiere and Sons Contracting701220201125-12Operator - Principle - After Jan 108.5637.5Inv#081 | [5 empty] | 1 | 637.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7012 | 20201125-12 | 53510312 | Access | 0 | Labourer - General - After Jan 10 | 60 | 4 | HR |  |  | 60 | 0 | 240 | 31.2 | 271.2 | 2020-11-25 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer cleared snow and broke up icy patches in Landfill Rd, Labourer bumped operators trck to the back of Landfill Rd. | 3 | B078-B084 | Red Rock Rd No. 7 | 0 | 44165 |  | 50 | 44168 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting701220201125-12Labourer - General - After Jan 104240 | Corbiere and Sons Contracting701220201125-12Labourer - General - After Jan 104240Inv#081 | [5 empty] | 1 | 240 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7016 | 20201125-16 | 53510412 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 2 | Dynamic | 98.61 | 0 |  |  | 262.96 | 34.1848 | 297.1448 | 2020-11-25 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-07 and DZ-05 patched road on the way into to Little Gravel River work site before building subgrade. | 4 | B194-B203 | Little Gravel River Road | 0 | 44165 |  | 50 | 44168 | [5 empty] | Wes Seminowich | 04 | Corbiere and Sons Contracting701620201125-16Dozer D6 or equal- After Jan 102262.96 | Corbiere and Sons Contracting701620201125-16Dozer D6 or equal- After Jan 102262.96Inv#081 | [5 empty] | 1 | 262.96 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7016 | 20201125-16 | 53510412 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 2 | Dynamic | 110.22 | 0 |  |  | 293.92 | 38.2096 | 332.1296 | 2020-11-25 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-07 and DZ-05 patched road on the way into to Little Gravel River work site before building subgrade. | 4 | B194-B203 | Little Gravel River Road | 0 | 44165 |  | 50 | 44168 | [5 empty] | Wes Seminowich | 04 | Corbiere and Sons Contracting701620201125-16Excavator - 36 ton- After Jan 102293.92 | Corbiere and Sons Contracting701620201125-16Excavator - 36 ton- After Jan 102293.92Inv#081 | [5 empty] | 1 | 293.92 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7016 | 20201125-16 | 53510412 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 2 | HR | 9.16 | 0 |  |  | 24.42 | 3.1746 | 27.5946 | 2020-11-25 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-07 and DZ-05 patched road on the way into to Little Gravel River work site before building subgrade. | 4 | B194-B203 | Little Gravel River Road | 0 | 44165 |  | 50 | 44168 | [5 empty] | Wes Seminowich | 04 | Corbiere and Sons Contracting701620201125-16Excavator Thumb - 30 - 50 ton- After Jan 10224.42 | Corbiere and Sons Contracting701620201125-16Excavator Thumb - 30 - 50 ton- After Jan 10224.42Inv#081 | [5 empty] | 1 | 24.42 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7016 | 20201125-16 | 53510412 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-11-25 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-07 and DZ-05 patched road on the way into to Little Gravel River work site before building subgrade. | 4 | B194-B203 | Little Gravel River Road | 0 | 44165 |  | 50 | 44168 | [5 empty] | Wes Seminowich | 04 | Corbiere and Sons Contracting701620201125-16Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting701620201125-16Light Truck - Pick up- After Jan 101243.75Inv#081 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7016 | 20201125-16 | 53510412 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 8 | HR |  |  | 75 | 0 | 600 | 78 | 678 | 2020-11-25 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-07 and DZ-05 patched road on the way into to Little Gravel River work site before building subgrade. | 4 | B194-B203 | Little Gravel River Road | 0 | 44165 |  | 50 | 44168 | [5 empty] | Wes Seminowich | 04 | Corbiere and Sons Contracting701620201125-16Operator - Principle - After Jan 108600 | Corbiere and Sons Contracting701620201125-16Operator - Principle - After Jan 108600Inv#081 | [5 empty] | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7017 | 20201125-17 | 53510412 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 5 | Dynamic | 110.22 | 0 |  |  | 734.8 | 95.524 | 830.324 | 2020-11-25 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-09 fixed 2 bad spots in Nishin Lake Rd | 4 | C011-C029 | Nishin Creek Road | 0 | 44165 |  | 50 | 44168 | [5 empty] | Wes Seminowich | 04 | Corbiere and Sons Contracting701720201125-17Excavator - 36 ton- After Jan 105734.8 | Corbiere and Sons Contracting701720201125-17Excavator - 36 ton- After Jan 105734.8Inv#081 | [5 empty] | 1 | 734.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7017 | 20201125-17 | 53510412 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 5 | HR | 9.16 | 0 |  |  | 61.05 | 7.9365 | 68.9865 | 2020-11-25 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-09 fixed 2 bad spots in Nishin Lake Rd | 4 | C011-C029 | Nishin Creek Road | 0 | 44165 |  | 50 | 44168 | [5 empty] | Wes Seminowich | 04 | Corbiere and Sons Contracting701720201125-17Excavator Thumb - 30 - 50 ton- After Jan 10561.05 | Corbiere and Sons Contracting701720201125-17Excavator Thumb - 30 - 50 ton- After Jan 10561.05Inv#081 | [5 empty] | 1 | 61.05 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7017 | 20201125-17 | 53510412 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 75 | 0 | 450 | 58.5 | 508.5 | 2020-11-25 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-09 fixed 2 bad spots in Nishin Lake Rd | 4 | C011-C029 | Nishin Creek Road | 0 | 44165 |  | 50 | 44168 | [5 empty] | Wes Seminowich | 04 | Corbiere and Sons Contracting701720201125-17Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting701720201125-17Operator - Principle - After Jan 106450Inv#081 | [5 empty] | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7024 | 20201125-24 | 53510504 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 4 | Dynamic | 110.22 | 0 |  |  | 587.84 | 76.4192 | 664.2592 | 2020-11-25 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | (2) Labourers cleaned up debris and geo rolls, (1) labourer went to Marathon with truck and traile to get timbers and geo. Operator loaded and hauled gravel himself from stockpile all day. | 5 | C076-C116 | Cook Lake | 0 | 44165 |  | 50 | 44168 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting702420201125-24Excavator - 36 ton- After Jan 104587.84 | Corbiere and Sons Contracting702420201125-24Excavator - 36 ton- After Jan 104587.84Inv#081 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 587.84 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7024 | 20201125-24 | 53510504 | Access | 0 | Light Truck w/ Tandum Trailer- After Jan 10 | 337.5 | 1 | DAY | 253.13 | 0 |  |  | 337.5 | 43.875 | 381.375 | 2020-11-25 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | (2) Labourers cleaned up debris and geo rolls, (1) labourer went to Marathon with truck and traile to get timbers and geo. Operator loaded and hauled gravel himself from stockpile all day. | 5 | C076-C116 | Cook Lake | 0 | 44165 |  | 50 | 44168 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting702420201125-24Light Truck w/ Tandum Trailer- After Jan 101337.5 | Corbiere and Sons Contracting702420201125-24Light Truck w/ Tandum Trailer- After Jan 101337.5Inv#081 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 337.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7024 | 20201125-24 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 6.5 | Dynamic | 103.54 | 0 |  |  | 897.325 | 116.6522 | 1013.9773 | 2020-11-25 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | (2) Labourers cleaned up debris and geo rolls, (1) labourer went to Marathon with truck and traile to get timbers and geo. Operator loaded and hauled gravel himself from stockpile all day. | 5 | C076-C116 | Cook Lake | 0 | 44165 |  | 50 | 44168 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting702420201125-24Rock Truck - 30 Ton- After Jan 106.5897.325 | Corbiere and Sons Contracting702420201125-24Rock Truck - 30 Ton- After Jan 106.5897.325Inv#081 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 897.325 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7024 | 20201125-24 | 53510504 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-11-25 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | (2) Labourers cleaned up debris and geo rolls, (1) labourer went to Marathon with truck and traile to get timbers and geo. Operator loaded and hauled gravel himself from stockpile all day. | 5 | C076-C116 | Cook Lake | 0 | 44165 |  | 50 | 44168 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting702420201125-24L.O.A.2420 | Corbiere and Sons Contracting702420201125-24L.O.A.2420Inv#081 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7024 | 20201125-24 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-11-25 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | (2) Labourers cleaned up debris and geo rolls, (1) labourer went to Marathon with truck and traile to get timbers and geo. Operator loaded and hauled gravel himself from stockpile all day. | 5 | C076-C116 | Cook Lake | 0 | 44165 |  | 50 | 44168 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting702420201125-24Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting702420201125-24Operator - Principle - After Jan 1011.5862.5Inv#081 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7024 | 20201125-24 | 53510504 | Access | 0 | Labourer - General - After Jan 10 | 60 | 9 | HR |  |  | 60 | 0 | 540 | 70.2 | 610.2 | 2020-11-25 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | (2) Labourers cleaned up debris and geo rolls, (1) labourer went to Marathon with truck and traile to get timbers and geo. Operator loaded and hauled gravel himself from stockpile all day. | 5 | C076-C116 | Cook Lake | 0 | 44165 |  | 50 | 44168 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting702420201125-24Labourer - General - After Jan 109540 | Corbiere and Sons Contracting702420201125-24Labourer - General - After Jan 109540Inv#081 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 540 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7025 | 20201125-25 | 53530501 | Rig/Access Mats | 0 | Skidder | 171 | 7.5 | HR | 128.25 | 0 |  |  | 1282.5 | 166.725 | 1449.225 | 2020-11-25 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Rig/Access Mat Handling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Labourers working on rig mat install and laying geo, Skidder hauling rig mats to C-109 laydown area, Excavator installed permitted crossing WC7611. | 5 | C076-C116 | Cook Lake | 0 | 44165 |  | 50 | 44168 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting702520201125-25Skidder 7.51282.5 | Corbiere and Sons Contracting702520201125-25Skidder 7.51282.5Inv#081 |  |  | WF5-WaterCrossing |  |  | 0.5 | 641.25 | WC409 | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7025 | 20201125-25 | 53530501 | Rig/Access Mats | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 7.5 | Dynamic | 110.22 | 0 |  |  | 1102.2 | 143.286 | 1245.486 | 2020-11-25 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Rig/Access Mat Handling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Labourers working on rig mat install and laying geo, Skidder hauling rig mats to C-109 laydown area, Excavator installed permitted crossing WC7611. | 5 | C076-C116 | Cook Lake | 0 | 44165 |  | 50 | 44168 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting702520201125-25Excavator - 36 ton- After Jan 107.51102.2 | Corbiere and Sons Contracting702520201125-25Excavator - 36 ton- After Jan 107.51102.2Inv#081 |  |  | WF5-WaterCrossing |  |  | 0.5 | 551.1 | WC409 | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7025 | 20201125-25 | 53530501 | Rig/Access Mats | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-11-25 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Rig/Access Mat Handling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Labourers working on rig mat install and laying geo, Skidder hauling rig mats to C-109 laydown area, Excavator installed permitted crossing WC7611. | 5 | C076-C116 | Cook Lake | 0 | 44165 |  | 50 | 44168 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting702520201125-25Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting702520201125-25Light Truck - Pick up- After Jan 101243.75Inv#081 |  |  | WF5-WaterCrossing |  |  | 0.5 | 121.875 | WC409 | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7025 | 20201125-25 | 53530501 | Rig/Access Mats | 0 | Foreman | 95 | 3 | HR |  |  | 95 | 0 | 285 | 37.05 | 322.05 | 2020-11-25 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Rig/Access Mat Handling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Labourers working on rig mat install and laying geo, Skidder hauling rig mats to C-109 laydown area, Excavator installed permitted crossing WC7611. | 5 | C076-C116 | Cook Lake | 0 | 44165 |  | 50 | 44168 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting702520201125-25Foreman3285 | Corbiere and Sons Contracting702520201125-25Foreman3285Inv#081 |  |  | WF5-WaterCrossing |  |  | 0.5 | 142.5 | WC409 | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7025 | 20201125-25 | 53530501 | Rig/Access Mats | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2020-11-25 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Rig/Access Mat Handling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Labourers working on rig mat install and laying geo, Skidder hauling rig mats to C-109 laydown area, Excavator installed permitted crossing WC7611. | 5 | C076-C116 | Cook Lake | 0 | 44165 |  | 50 | 44168 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting702520201125-25L.O.A.4840 | Corbiere and Sons Contracting702520201125-25L.O.A.4840Inv#081 |  |  | WF5-WaterCrossing |  |  | 0.5 | 420 | WC409 | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7025 | 20201125-25 | 53530501 | Rig/Access Mats | 0 | Operator - Principle - After Jan 10 | 75 | 16 | HR |  |  | 75 | 0 | 1200 | 156 | 1356 | 2020-11-25 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Rig/Access Mat Handling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Labourers working on rig mat install and laying geo, Skidder hauling rig mats to C-109 laydown area, Excavator installed permitted crossing WC7611. | 5 | C076-C116 | Cook Lake | 0 | 44165 |  | 50 | 44168 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting702520201125-25Operator - Principle - After Jan 10161200 | Corbiere and Sons Contracting702520201125-25Operator - Principle - After Jan 10161200Inv#081 |  |  | WF5-WaterCrossing |  |  | 0.5 | 600 | WC409 | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7025 | 20201125-25 | 53530501 | Rig/Access Mats | 0 | Labourer - General - After Jan 10 | 60 | 9 | HR |  |  | 60 | 0 | 540 | 70.2 | 610.2 | 2020-11-25 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Rig/Access Mat Handling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Labourers working on rig mat install and laying geo, Skidder hauling rig mats to C-109 laydown area, Excavator installed permitted crossing WC7611. | 5 | C076-C116 | Cook Lake | 0 | 44165 |  | 50 | 44168 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting702520201125-25Labourer - General - After Jan 109540 | Corbiere and Sons Contracting702520201125-25Labourer - General - After Jan 109540Inv#081 |  |  | WF5-WaterCrossing |  |  | 0.5 | 270 | WC409 | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7027 | 20201125-27 | 53510511 | Access | 0 | Skidder | 171 | 3 | HR | 128.25 | 0 |  |  | 513 | 66.69 | 579.69 | 2020-11-25 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Darrel sanding roads all day at Cooks Lake East, Dozer doing winter road maintenance, Skidder scrapping hills, Excavator doing winter road maintenance | 5 | C076-C116 | Cook Lake | 0 | 44165 |  | 50 | 44168 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting702720201125-27Skidder 3513 | Corbiere and Sons Contracting702720201125-27Skidder 3513Inv#081 | [5 empty] | 1 | 513 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7027 | 20201125-27 | 53510511 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10.5 | Dynamic | 98.61 | 0 |  |  | 1380.54 | 179.4702 | 1560.0102 | 2020-11-25 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Darrel sanding roads all day at Cooks Lake East, Dozer doing winter road maintenance, Skidder scrapping hills, Excavator doing winter road maintenance | 5 | C076-C116 | Cook Lake | 0 | 44165 |  | 50 | 44168 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting702720201125-27Dozer D6 or equal- After Jan 1010.51380.54 | Corbiere and Sons Contracting702720201125-27Dozer D6 or equal- After Jan 1010.51380.54Inv#081 | [5 empty] | 1 | 1380.54 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7027 | 20201125-27 | 53510511 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 3 | Dynamic | 110.22 | 0 |  |  | 440.88 | 57.3144 | 498.1944 | 2020-11-25 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Darrel sanding roads all day at Cooks Lake East, Dozer doing winter road maintenance, Skidder scrapping hills, Excavator doing winter road maintenance | 5 | C076-C116 | Cook Lake | 0 | 44165 |  | 50 | 44168 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting702720201125-27Excavator - 36 ton- After Jan 103440.88 | Corbiere and Sons Contracting702720201125-27Excavator - 36 ton- After Jan 103440.88Inv#081 | [5 empty] | 1 | 440.88 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7027 | 20201125-27 | 53510511 | Access | 0 | Sander Truck - Hwy- After Jan 10 | 55 | 10.5 | Dynamic | 41.25 | 0 |  |  | 577.5 | 75.075 | 652.575 | 2020-11-25 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Darrel sanding roads all day at Cooks Lake East, Dozer doing winter road maintenance, Skidder scrapping hills, Excavator doing winter road maintenance | 5 | C076-C116 | Cook Lake | 0 | 44165 |  | 50 | 44168 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting702720201125-27Sander Truck - Hwy- After Jan 1010.5577.5 | Corbiere and Sons Contracting702720201125-27Sander Truck - Hwy- After Jan 1010.5577.5Inv#081 | [5 empty] | 1 | 577.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7027 | 20201125-27 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-11-25 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Darrel sanding roads all day at Cooks Lake East, Dozer doing winter road maintenance, Skidder scrapping hills, Excavator doing winter road maintenance | 5 | C076-C116 | Cook Lake | 0 | 44165 |  | 50 | 44168 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting702720201125-27Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting702720201125-27Light Truck - Pick up- After Jan 102487.5Inv#081 | [5 empty] | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7027 | 20201125-27 | 53510511 | Access | 0 | Foreman | 95 | 5 | HR |  |  | 95 | 0 | 475 | 61.75 | 536.75 | 2020-11-25 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Darrel sanding roads all day at Cooks Lake East, Dozer doing winter road maintenance, Skidder scrapping hills, Excavator doing winter road maintenance | 5 | C076-C116 | Cook Lake | 0 | 44165 |  | 50 | 44168 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting702720201125-27Foreman5475 | Corbiere and Sons Contracting702720201125-27Foreman5475Inv#081 | [5 empty] | 1 | 475 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7027 | 20201125-27 | 53510511 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2020-11-25 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Darrel sanding roads all day at Cooks Lake East, Dozer doing winter road maintenance, Skidder scrapping hills, Excavator doing winter road maintenance | 5 | C076-C116 | Cook Lake | 0 | 44165 |  | 50 | 44168 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting702720201125-27L.O.A.3630 | Corbiere and Sons Contracting702720201125-27L.O.A.3630Inv#081 | [5 empty] | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7027 | 20201125-27 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 18.5 | HR |  |  | 75 | 0 | 1387.5 | 180.375 | 1567.875 | 2020-11-25 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Darrel sanding roads all day at Cooks Lake East, Dozer doing winter road maintenance, Skidder scrapping hills, Excavator doing winter road maintenance | 5 | C076-C116 | Cook Lake | 0 | 44165 |  | 50 | 44168 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting702720201125-27Operator - Principle - After Jan 1018.51387.5 | Corbiere and Sons Contracting702720201125-27Operator - Principle - After Jan 1018.51387.5Inv#081 | [5 empty] | 1 | 1387.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7027 | 20201125-27 | 53510511 | Access | 0 | Labourer - General - After Jan 10 | 60 | 11.5 | HR |  |  | 60 | 0 | 690 | 89.7 | 779.7 | 2020-11-25 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Darrel sanding roads all day at Cooks Lake East, Dozer doing winter road maintenance, Skidder scrapping hills, Excavator doing winter road maintenance | 5 | C076-C116 | Cook Lake | 0 | 44165 |  | 50 | 44168 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting702720201125-27Labourer - General - After Jan 1011.5690 | Corbiere and Sons Contracting702720201125-27Labourer - General - After Jan 1011.5690Inv#081 | [5 empty] | 1 | 690 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7005 | 20201125-5 | 53510504 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 5.5 | Dynamic | 98.61 | 0 |  |  | 723.14 | 94.0082 | 817.1482 | 2020-11-25 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loaded rock truck and worked on capping from C-050 - C-051, dozer spreading gravel from C-050 - C-051 | 5 | C050-C069 | Antler Lake | 0 | 44160 |  | 50 | 44168 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting700520201125-5Dozer D6 or equal- After Jan 105.5723.14 | Corbiere and Sons Contracting700520201125-5Dozer D6 or equal- After Jan 105.5723.14Inv#081 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 723.14 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7005 | 20201125-5 | 53510504 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10.5 | Dynamic | 103.84 | 0 |  |  | 1453.725 | 188.9843 | 1642.7093 | 2020-11-25 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loaded rock truck and worked on capping from C-050 - C-051, dozer spreading gravel from C-050 - C-051 | 5 | C050-C069 | Antler Lake | 0 | 44160 |  | 50 | 44168 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting700520201125-5Excavator - 30 ton- After Jan 1010.51453.725 | Corbiere and Sons Contracting700520201125-5Excavator - 30 ton- After Jan 1010.51453.725Inv#081 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1453.725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7005 | 20201125-5 | 53510504 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10.5 | HR | 9.16 | 0 |  |  | 128.205 | 16.6667 | 144.8716 | 2020-11-25 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loaded rock truck and worked on capping from C-050 - C-051, dozer spreading gravel from C-050 - C-051 | 5 | C050-C069 | Antler Lake | 0 | 44160 |  | 50 | 44168 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting700520201125-5Excavator Thumb - 30 - 50 ton- After Jan 1010.5128.205 | Corbiere and Sons Contracting700520201125-5Excavator Thumb - 30 - 50 ton- After Jan 1010.5128.205Inv#081 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 128.205 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7005 | 20201125-5 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2020-11-25 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loaded rock truck and worked on capping from C-050 - C-051, dozer spreading gravel from C-050 - C-051 | 5 | C050-C069 | Antler Lake | 0 | 44160 |  | 50 | 44168 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting700520201125-5Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting700520201125-5Light Truck - Pick up- After Jan 103731.25Inv#081 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 731.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7005 | 20201125-5 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 10.5 | Dynamic | 103.54 | 0 |  |  | 1449.525 | 188.4383 | 1637.9633 | 2020-11-25 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loaded rock truck and worked on capping from C-050 - C-051, dozer spreading gravel from C-050 - C-051 | 5 | C050-C069 | Antler Lake | 0 | 44160 |  | 50 | 44168 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting700520201125-5Rock Truck - 30 Ton- After Jan 1010.51449.525 | Corbiere and Sons Contracting700520201125-5Rock Truck - 30 Ton- After Jan 1010.51449.525Inv#081 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1449.525 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7005 | 20201125-5 | 53510504 | Access | 0 | Foreman | 95 | 4 | HR |  |  | 95 | 0 | 380 | 49.4 | 429.4 | 2020-11-25 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loaded rock truck and worked on capping from C-050 - C-051, dozer spreading gravel from C-050 - C-051 | 5 | C050-C069 | Antler Lake | 0 | 44160 |  | 50 | 44168 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting700520201125-5Foreman4380 | Corbiere and Sons Contracting700520201125-5Foreman4380Inv#081 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7005 | 20201125-5 | 53510504 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2020-11-25 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loaded rock truck and worked on capping from C-050 - C-051, dozer spreading gravel from C-050 - C-051 | 5 | C050-C069 | Antler Lake | 0 | 44160 |  | 50 | 44168 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting700520201125-5L.O.A.4840 | Corbiere and Sons Contracting700520201125-5L.O.A.4840Inv#081 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7005 | 20201125-5 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 17.5 | HR |  |  | 75 | 0 | 1312.5 | 170.625 | 1483.125 | 2020-11-25 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loaded rock truck and worked on capping from C-050 - C-051, dozer spreading gravel from C-050 - C-051 | 5 | C050-C069 | Antler Lake | 0 | 44160 |  | 50 | 44168 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting700520201125-5Operator - Principle - After Jan 1017.51312.5 | Corbiere and Sons Contracting700520201125-5Operator - Principle - After Jan 1017.51312.5Inv#081 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1312.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7005 | 20201125-5 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 11.5 | HR |  |  | 70 | 0 | 805 | 104.65 | 909.65 | 2020-11-25 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loaded rock truck and worked on capping from C-050 - C-051, dozer spreading gravel from C-050 - C-051 | 5 | C050-C069 | Antler Lake | 0 | 44160 |  | 50 | 44168 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting700520201125-5Driver - AZ - After Jan 1011.5805 | Corbiere and Sons Contracting700520201125-5Driver - AZ - After Jan 1011.5805Inv#081 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 805 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7006 | 20201125-6 | 53510511 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 5 | Dynamic | 98.61 | 0 |  |  | 657.4 | 85.462 | 742.862 | 2020-11-25 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Snowplowing East side of Antler at Valards request. | 5 | C050-C069 | Antler Lake | 0 | 44165 |  | 50 | 44168 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting700620201125-6Dozer D6 or equal- After Jan 105657.4 | Corbiere and Sons Contracting700620201125-6Dozer D6 or equal- After Jan 105657.4Inv#081 | [5 empty] | 1 | 657.4 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7006 | 20201125-6 | 53510511 | Access | 0 | Foreman | 95 | 2 | HR |  |  | 95 | 0 | 190 | 24.7 | 214.7 | 2020-11-25 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Snowplowing East side of Antler at Valards request. | 5 | C050-C069 | Antler Lake | 0 | 44165 |  | 50 | 44168 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting700620201125-6Foreman2190 | Corbiere and Sons Contracting700620201125-6Foreman2190Inv#081 | [5 empty] | 1 | 190 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7006 | 20201125-6 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5.5 | HR |  |  | 75 | 0 | 412.5 | 53.625 | 466.125 | 2020-11-25 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Snowplowing East side of Antler at Valards request. | 5 | C050-C069 | Antler Lake | 0 | 44165 |  | 50 | 44168 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting700620201125-6Operator - Principle - After Jan 105.5412.5 | Corbiere and Sons Contracting700620201125-6Operator - Principle - After Jan 105.5412.5Inv#081 | [5 empty] | 1 | 412.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7007 | 20201125-7 | 53510504 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 2 | Dynamic | 103.84 | 0 |  |  | 276.9 | 35.997 | 312.897 | 2020-11-25 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Operator spent 2 hours capping corduroy from C-074, labourer spent 2 hours rolling out geo | 5 | C070-C075 | White Sand | 0 | 44165 |  | 50 | 44168 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting700720201125-7Excavator - 30 ton- After Jan 102276.9 | Corbiere and Sons Contracting700720201125-7Excavator - 30 ton- After Jan 102276.9Inv#081 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 276.9 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7007 | 20201125-7 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-11-25 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Operator spent 2 hours capping corduroy from C-074, labourer spent 2 hours rolling out geo | 5 | C070-C075 | White Sand | 0 | 44165 |  | 50 | 44168 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting700720201125-7Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting700720201125-7Light Truck - Pick up- After Jan 101243.75Inv#081 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7007 | 20201125-7 | 53510504 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-11-25 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Operator spent 2 hours capping corduroy from C-074, labourer spent 2 hours rolling out geo | 5 | C070-C075 | White Sand | 0 | 44165 |  | 50 | 44168 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting700720201125-7L.O.A.1210 | Corbiere and Sons Contracting700720201125-7L.O.A.1210Inv#081 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7007 | 20201125-7 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 2 | HR |  |  | 75 | 0 | 150 | 19.5 | 169.5 | 2020-11-25 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Operator spent 2 hours capping corduroy from C-074, labourer spent 2 hours rolling out geo | 5 | C070-C075 | White Sand | 0 | 44165 |  | 50 | 44168 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting700720201125-7Operator - Principle - After Jan 102150 | Corbiere and Sons Contracting700720201125-7Operator - Principle - After Jan 102150Inv#081 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 150 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7007 | 20201125-7 | 53510504 | Access | 0 | Labourer - General - After Jan 10 | 60 | 2 | HR |  |  | 60 | 0 | 120 | 15.6 | 135.6 | 2020-11-25 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Operator spent 2 hours capping corduroy from C-074, labourer spent 2 hours rolling out geo | 5 | C070-C075 | White Sand | 0 | 44165 |  | 50 | 44168 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting700720201125-7Labourer - General - After Jan 102120 | Corbiere and Sons Contracting700720201125-7Labourer - General - After Jan 102120Inv#081 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 120 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7043 | 20201126-13 | 53510511 | Access | 0 | Skidder | 171 | 3.5 | HR | 128.25 | 0 |  |  | 598.5 | 77.805 | 676.305 | 2020-11-26 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer and excavator doing winter access maintenance, skidder scrapped hills | 5 | C076-C116 | Cook Lake | 0 | 44165 |  | 37 | 44167 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting704320201126-13Skidder 3.5598.5 | Corbiere and Sons Contracting704320201126-13Skidder 3.5598.5Inv#081 | [5 empty] | 1 | 598.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7043 | 20201126-13 | 53510511 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10.5 | Dynamic | 98.61 | 0 |  |  | 1380.54 | 179.4702 | 1560.0102 | 2020-11-26 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer and excavator doing winter access maintenance, skidder scrapped hills | 5 | C076-C116 | Cook Lake | 0 | 44165 |  | 37 | 44167 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting704320201126-13Dozer D6 or equal- After Jan 1010.51380.54 | Corbiere and Sons Contracting704320201126-13Dozer D6 or equal- After Jan 1010.51380.54Inv#081 | [5 empty] | 1 | 1380.54 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7043 | 20201126-13 | 53510511 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 1.5 | Dynamic | 110.22 | 0 |  |  | 220.44 | 28.6572 | 249.0972 | 2020-11-26 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer and excavator doing winter access maintenance, skidder scrapped hills | 5 | C076-C116 | Cook Lake | 0 | 44165 |  | 37 | 44167 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting704320201126-13Excavator - 36 ton- After Jan 101.5220.44 | Corbiere and Sons Contracting704320201126-13Excavator - 36 ton- After Jan 101.5220.44Inv#081 | [5 empty] | 1 | 220.44 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7043 | 20201126-13 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-11-26 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer and excavator doing winter access maintenance, skidder scrapped hills | 5 | C076-C116 | Cook Lake | 0 | 44165 |  | 37 | 44167 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting704320201126-13Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting704320201126-13Light Truck - Pick up- After Jan 102487.5Inv#081 | [5 empty] | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7043 | 20201126-13 | 53510511 | Access | 0 | Foreman | 95 | 2 | HR |  |  | 95 | 0 | 190 | 24.7 | 214.7 | 2020-11-26 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer and excavator doing winter access maintenance, skidder scrapped hills | 5 | C076-C116 | Cook Lake | 0 | 44165 |  | 37 | 44167 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting704320201126-13Foreman2190 | Corbiere and Sons Contracting704320201126-13Foreman2190Inv#081 | [5 empty] | 1 | 190 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7043 | 20201126-13 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-11-26 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer and excavator doing winter access maintenance, skidder scrapped hills | 5 | C076-C116 | Cook Lake | 0 | 44165 |  | 37 | 44167 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting704320201126-13L.O.A.1210 | Corbiere and Sons Contracting704320201126-13L.O.A.1210Inv#081 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7043 | 20201126-13 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 17.5 | HR |  |  | 75 | 0 | 1312.5 | 170.625 | 1483.125 | 2020-11-26 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer and excavator doing winter access maintenance, skidder scrapped hills | 5 | C076-C116 | Cook Lake | 0 | 44165 |  | 37 | 44167 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting704320201126-13Operator - Principle - After Jan 1017.51312.5 | Corbiere and Sons Contracting704320201126-13Operator - Principle - After Jan 1017.51312.5Inv#081 | [5 empty] | 1 | 1312.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7044 | 20201126-14 | 53510504 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10.5 | Dynamic | 98.61 | 0 |  |  | 1380.54 | 179.4702 | 1560.0102 | 2020-11-26 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks and working on road capping from C-050 and C-051Rock truck hauling gravel towards C-051Dozer capping road from C-051 and C-050 all day | 5 | C050-C069 | Antler Lake | 0 | 44165 |  | 50 | 44168 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting704420201126-14Dozer D6 or equal- After Jan 1010.51380.54 | Corbiere and Sons Contracting704420201126-14Dozer D6 or equal- After Jan 1010.51380.54Inv#081 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1380.54 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7044 | 20201126-14 | 53510504 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10.5 | Dynamic | 103.84 | 0 |  |  | 1453.725 | 188.9843 | 1642.7093 | 2020-11-26 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks and working on road capping from C-050 and C-051Rock truck hauling gravel towards C-051Dozer capping road from C-051 and C-050 all day | 5 | C050-C069 | Antler Lake | 0 | 44165 |  | 50 | 44168 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting704420201126-14Excavator - 30 ton- After Jan 1010.51453.725 | Corbiere and Sons Contracting704420201126-14Excavator - 30 ton- After Jan 1010.51453.725Inv#081 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1453.725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7044 | 20201126-14 | 53510504 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10.5 | HR | 9.16 | 0 |  |  | 128.205 | 16.6667 | 144.8716 | 2020-11-26 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks and working on road capping from C-050 and C-051Rock truck hauling gravel towards C-051Dozer capping road from C-051 and C-050 all day | 5 | C050-C069 | Antler Lake | 0 | 44165 |  | 50 | 44168 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting704420201126-14Excavator Thumb - 30 - 50 ton- After Jan 1010.5128.205 | Corbiere and Sons Contracting704420201126-14Excavator Thumb - 30 - 50 ton- After Jan 1010.5128.205Inv#081 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 128.205 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7044 | 20201126-14 | 53510504 | Access | 0 | ATV - Side by Side w/ roll bar- After Jan 10 | 18.45 | 6 | HR | 13.84 | 0 |  |  | 110.7 | 14.391 | 125.091 | 2020-11-26 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks and working on road capping from C-050 and C-051Rock truck hauling gravel towards C-051Dozer capping road from C-051 and C-050 all day | 5 | C050-C069 | Antler Lake | 0 | 44165 |  | 50 | 44168 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting704420201126-14ATV - Side by Side w/ roll bar- After Jan 106110.7 | Corbiere and Sons Contracting704420201126-14ATV - Side by Side w/ roll bar- After Jan 106110.7Inv#081 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 110.7 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7044 | 20201126-14 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-11-26 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks and working on road capping from C-050 and C-051Rock truck hauling gravel towards C-051Dozer capping road from C-051 and C-050 all day | 5 | C050-C069 | Antler Lake | 0 | 44165 |  | 50 | 44168 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting704420201126-14Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting704420201126-14Light Truck - Pick up- After Jan 102487.5Inv#081 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7044 | 20201126-14 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 10.5 | Dynamic | 103.54 | 0 |  |  | 1449.525 | 188.4383 | 1637.9633 | 2020-11-26 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks and working on road capping from C-050 and C-051Rock truck hauling gravel towards C-051Dozer capping road from C-051 and C-050 all day | 5 | C050-C069 | Antler Lake | 0 | 44165 |  | 50 | 44168 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting704420201126-14Rock Truck - 30 Ton- After Jan 1010.51449.525 | Corbiere and Sons Contracting704420201126-14Rock Truck - 30 Ton- After Jan 1010.51449.525Inv#081 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1449.525 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7044 | 20201126-14 | 53510504 | Access | 0 | Foreman | 95 | 6 | HR |  |  | 95 | 0 | 570 | 74.1 | 644.1 | 2020-11-26 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks and working on road capping from C-050 and C-051Rock truck hauling gravel towards C-051Dozer capping road from C-051 and C-050 all day | 5 | C050-C069 | Antler Lake | 0 | 44165 |  | 50 | 44168 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting704420201126-14Foreman6570 | Corbiere and Sons Contracting704420201126-14Foreman6570Inv#081 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 570 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7044 | 20201126-14 | 53510504 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2020-11-26 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks and working on road capping from C-050 and C-051Rock truck hauling gravel towards C-051Dozer capping road from C-051 and C-050 all day | 5 | C050-C069 | Antler Lake | 0 | 44165 |  | 50 | 44168 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting704420201126-14L.O.A.4840 | Corbiere and Sons Contracting704420201126-14L.O.A.4840Inv#081 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7044 | 20201126-14 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 23 | HR |  |  | 75 | 0 | 1725 | 224.25 | 1949.25 | 2020-11-26 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks and working on road capping from C-050 and C-051Rock truck hauling gravel towards C-051Dozer capping road from C-051 and C-050 all day | 5 | C050-C069 | Antler Lake | 0 | 44165 |  | 50 | 44168 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting704420201126-14Operator - Principle - After Jan 10231725 | Corbiere and Sons Contracting704420201126-14Operator - Principle - After Jan 10231725Inv#081 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7044 | 20201126-14 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 11.5 | HR |  |  | 70 | 0 | 805 | 104.65 | 909.65 | 2020-11-26 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks and working on road capping from C-050 and C-051Rock truck hauling gravel towards C-051Dozer capping road from C-051 and C-050 all day | 5 | C050-C069 | Antler Lake | 0 | 44165 |  | 50 | 44168 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting704420201126-14Driver - AZ - After Jan 1011.5805 | Corbiere and Sons Contracting704420201126-14Driver - AZ - After Jan 1011.5805Inv#081 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 805 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7046 | 20201126-16 | 53510511 | Access | 0 | Sander Truck - Hwy- After Jan 10 | 55 | 10.5 | Dynamic | 41.25 | 0 |  |  | 577.5 | 75.075 | 652.575 | 2020-11-26 | 1 | Inv#081 | 44173 | 128 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 15 | Approved | ROW INTERNAL - Sand for Road Maintenance - 3rd Party | 9015 | Sanding roads all day | 5 | C050-C069 | Antler Lake | 0 | 44165 |  | 50 | 44168 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting704620201126-16Sander Truck - Hwy- After Jan 1010.5577.5 | Corbiere and Sons Contracting704620201126-16Sander Truck - Hwy- After Jan 1010.5577.5Inv#081 | [5 empty] | 1 | 577.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7046 | 20201126-16 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-11-26 | 1 | Inv#081 | 44173 | 128 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 15 | Approved | ROW INTERNAL - Sand for Road Maintenance - 3rd Party | 9015 | Sanding roads all day | 5 | C050-C069 | Antler Lake | 0 | 44165 |  | 50 | 44168 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting704620201126-16L.O.A.1210 | Corbiere and Sons Contracting704620201126-16L.O.A.1210Inv#081 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7046 | 20201126-16 | 53510511 | Access | 0 | Labourer - General - After Jan 10 | 60 | 11.5 | HR |  |  | 60 | 0 | 690 | 89.7 | 779.7 | 2020-11-26 | 1 | Inv#081 | 44173 | 128 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 15 | Approved | ROW INTERNAL - Sand for Road Maintenance - 3rd Party | 9015 | Sanding roads all day | 5 | C050-C069 | Antler Lake | 0 | 44165 |  | 50 | 44168 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting704620201126-16Labourer - General - After Jan 1011.5690 | Corbiere and Sons Contracting704620201126-16Labourer - General - After Jan 1011.5690Inv#081 | [5 empty] | 1 | 690 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7039 | 20201126-9-R1 | 53510312 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10 | Dynamic | 98.61 | 0 |  |  | 1314.8 | 170.924 | 1485.724 | 2020-11-26 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | DZ-01 cleared snow and broke up icy patches in Landfill Rd. | 3 | B078-B084 | Red Rock Road No. 7 | 0 | 44165 |  | 50 | 44168 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting703920201126-9-R1Dozer D6 or equal- After Jan 10101314.8 | Corbiere and Sons Contracting703920201126-9-R1Dozer D6 or equal- After Jan 10101314.8Inv#081 | [5 empty] | 1 | 1314.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7039 | 20201126-9-R1 | 53510312 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 |  |  |  | 243.75 | 31.6875 | 275.4375 | 2020-11-26 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | DZ-01 cleared snow and broke up icy patches in Landfill Rd. | 3 | B078-B084 | Red Rock Road No. 7 | 0 | 44165 |  | 50 | 44168 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting703920201126-9-R1Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting703920201126-9-R1Light Truck - Pick up- After Jan 101243.75Inv#081 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7039 | 20201126-9-R1 | 53510312 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2020-11-26 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | DZ-01 cleared snow and broke up icy patches in Landfill Rd. | 3 | B078-B084 | Red Rock Road No. 7 | 0 | 44165 |  | 50 | 44168 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting703920201126-9-R1Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting703920201126-9-R1Operator - Principle - After Jan 1011825Inv#081 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7058 | 20201127-11 | 53510504 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10.5 | Dynamic | 98.61 | 0 |  |  | 1380.54 | 179.4702 | 1560.0102 | 2020-11-27 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock truck and working on capping all day, Rock truck hauling all day, Dozer spreading gravel from C-050 - C-051. | 5 | C050-C069 | Antler Lake | 0 | 44166 |  | 50 | 44168 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting705820201127-11Dozer D6 or equal- After Jan 1010.51380.54 | Corbiere and Sons Contracting705820201127-11Dozer D6 or equal- After Jan 1010.51380.54Inv#081 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1380.54 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7058 | 20201127-11 | 53510504 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10.5 | Dynamic | 103.84 | 0 |  |  | 1453.725 | 188.9843 | 1642.7093 | 2020-11-27 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock truck and working on capping all day, Rock truck hauling all day, Dozer spreading gravel from C-050 - C-051. | 5 | C050-C069 | Antler Lake | 0 | 44166 |  | 50 | 44168 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting705820201127-11Excavator - 30 ton- After Jan 1010.51453.725 | Corbiere and Sons Contracting705820201127-11Excavator - 30 ton- After Jan 1010.51453.725Inv#081 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1453.725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7058 | 20201127-11 | 53510504 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10.5 | HR | 9.16 | 0 |  |  | 128.205 | 16.6667 | 144.8716 | 2020-11-27 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock truck and working on capping all day, Rock truck hauling all day, Dozer spreading gravel from C-050 - C-051. | 5 | C050-C069 | Antler Lake | 0 | 44166 |  | 50 | 44168 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting705820201127-11Excavator Thumb - 30 - 50 ton- After Jan 1010.5128.205 | Corbiere and Sons Contracting705820201127-11Excavator Thumb - 30 - 50 ton- After Jan 1010.5128.205Inv#081 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 128.205 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7058 | 20201127-11 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-11-27 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock truck and working on capping all day, Rock truck hauling all day, Dozer spreading gravel from C-050 - C-051. | 5 | C050-C069 | Antler Lake | 0 | 44166 |  | 50 | 44168 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting705820201127-11Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting705820201127-11Light Truck - Pick up- After Jan 102487.5Inv#081 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7058 | 20201127-11 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 10.5 | Dynamic | 103.54 | 0 |  |  | 1449.525 | 188.4383 | 1637.9633 | 2020-11-27 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock truck and working on capping all day, Rock truck hauling all day, Dozer spreading gravel from C-050 - C-051. | 5 | C050-C069 | Antler Lake | 0 | 44166 |  | 50 | 44168 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting705820201127-11Rock Truck - 30 Ton- After Jan 1010.51449.525 | Corbiere and Sons Contracting705820201127-11Rock Truck - 30 Ton- After Jan 1010.51449.525Inv#081 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1449.525 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7058 | 20201127-11 | 53510504 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2020-11-27 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock truck and working on capping all day, Rock truck hauling all day, Dozer spreading gravel from C-050 - C-051. | 5 | C050-C069 | Antler Lake | 0 | 44166 |  | 50 | 44168 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting705820201127-11L.O.A.3630 | Corbiere and Sons Contracting705820201127-11L.O.A.3630Inv#081 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7058 | 20201127-11 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 23 | HR |  |  | 75 | 0 | 1725 | 224.25 | 1949.25 | 2020-11-27 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock truck and working on capping all day, Rock truck hauling all day, Dozer spreading gravel from C-050 - C-051. | 5 | C050-C069 | Antler Lake | 0 | 44166 |  | 50 | 44168 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting705820201127-11Operator - Principle - After Jan 10231725 | Corbiere and Sons Contracting705820201127-11Operator - Principle - After Jan 10231725Inv#081 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7058 | 20201127-11 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 11.5 | HR |  |  | 70 | 0 | 805 | 104.65 | 909.65 | 2020-11-27 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock truck and working on capping all day, Rock truck hauling all day, Dozer spreading gravel from C-050 - C-051. | 5 | C050-C069 | Antler Lake | 0 | 44166 |  | 50 | 44168 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting705820201127-11Driver - AZ - After Jan 1011.5805 | Corbiere and Sons Contracting705820201127-11Driver - AZ - After Jan 1011.5805Inv#081 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 805 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7061 | 20201127-14 | 53510511 | Access | 0 | Skidder | 171 | 6 | HR | 128.25 | 0 |  |  | 1026 | 133.38 | 1159.38 | 2020-11-27 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | sander truck all day working across Cooks Lkae accessOperator all day on winter road maintenance - 2 hours on dozer and rest of day on the grader. | 5 | C076-C116 | Cook Lake | 0 | 44166 |  | 37 | 44167 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting706120201127-14Skidder 61026 | Corbiere and Sons Contracting706120201127-14Skidder 61026Inv#081 | [5 empty] | 1 | 1026 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7061 | 20201127-14 | 53510511 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 3 | Dynamic | 98.61 | 0 |  |  | 394.44 | 51.2772 | 445.7172 | 2020-11-27 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | sander truck all day working across Cooks Lkae accessOperator all day on winter road maintenance - 2 hours on dozer and rest of day on the grader. | 5 | C076-C116 | Cook Lake | 0 | 44166 |  | 37 | 44167 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting706120201127-14Dozer D6 or equal- After Jan 103394.44 | Corbiere and Sons Contracting706120201127-14Dozer D6 or equal- After Jan 103394.44Inv#081 | [5 empty] | 1 | 394.44 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7061 | 20201127-14 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 7 | Dynamic | 95.24 | 0 |  |  | 888.86 | 115.5518 | 1004.4118 | 2020-11-27 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | sander truck all day working across Cooks Lkae accessOperator all day on winter road maintenance - 2 hours on dozer and rest of day on the grader. | 5 | C076-C116 | Cook Lake | 0 | 44166 |  | 37 | 44167 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting706120201127-14Grader - Cat 12 to 14 or equal- After Jan 107888.86 | Corbiere and Sons Contracting706120201127-14Grader - Cat 12 to 14 or equal- After Jan 107888.86Inv#081 | [5 empty] | 1 | 888.86 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7061 | 20201127-14 | 53510511 | Access | 0 | Sander Truck - Hwy- After Jan 10 | 55 | 9.5 | Dynamic | 41.25 | 0 |  |  | 522.5 | 67.925 | 590.425 | 2020-11-27 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | sander truck all day working across Cooks Lkae accessOperator all day on winter road maintenance - 2 hours on dozer and rest of day on the grader. | 5 | C076-C116 | Cook Lake | 0 | 44166 |  | 37 | 44167 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting706120201127-14Sander Truck - Hwy- After Jan 109.5522.5 | Corbiere and Sons Contracting706120201127-14Sander Truck - Hwy- After Jan 109.5522.5Inv#081 | [5 empty] | 1 | 522.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7061 | 20201127-14 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-11-27 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | sander truck all day working across Cooks Lkae accessOperator all day on winter road maintenance - 2 hours on dozer and rest of day on the grader. | 5 | C076-C116 | Cook Lake | 0 | 44166 |  | 37 | 44167 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting706120201127-14Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting706120201127-14Light Truck - Pick up- After Jan 102487.5Inv#081 | [5 empty] | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7061 | 20201127-14 | 53510511 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2020-11-27 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | sander truck all day working across Cooks Lkae accessOperator all day on winter road maintenance - 2 hours on dozer and rest of day on the grader. | 5 | C076-C116 | Cook Lake | 0 | 44166 |  | 37 | 44167 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting706120201127-14L.O.A.3630 | Corbiere and Sons Contracting706120201127-14L.O.A.3630Inv#081 | [5 empty] | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7061 | 20201127-14 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 17.5 | HR |  |  | 75 | 0 | 1312.5 | 170.625 | 1483.125 | 2020-11-27 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | sander truck all day working across Cooks Lkae accessOperator all day on winter road maintenance - 2 hours on dozer and rest of day on the grader. | 5 | C076-C116 | Cook Lake | 0 | 44166 |  | 37 | 44167 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting706120201127-14Operator - Principle - After Jan 1017.51312.5 | Corbiere and Sons Contracting706120201127-14Operator - Principle - After Jan 1017.51312.5Inv#081 | [5 empty] | 1 | 1312.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7061 | 20201127-14 | 53510511 | Access | 0 | Labourer - General - After Jan 10 | 60 | 11.5 | HR |  |  | 60 | 0 | 690 | 89.7 | 779.7 | 2020-11-27 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | sander truck all day working across Cooks Lkae accessOperator all day on winter road maintenance - 2 hours on dozer and rest of day on the grader. | 5 | C076-C116 | Cook Lake | 0 | 44166 |  | 37 | 44167 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting706120201127-14Labourer - General - After Jan 1011.5690 | Corbiere and Sons Contracting706120201127-14Labourer - General - After Jan 1011.5690Inv#081 | [5 empty] | 1 | 690 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7062 | 20201127-15 | 53510504 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10.5 | Dynamic | 103.84 | 0 |  |  | 1453.725 | 188.9843 | 1642.7093 | 2020-11-27 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loaded Rock truck, Rock truck hauling gravel all day. | 5 | C076-C116 | Cook Lake | 0 | 44166 |  | 37 | 44167 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting706220201127-15Excavator - 30 ton- After Jan 1010.51453.725 | Corbiere and Sons Contracting706220201127-15Excavator - 30 ton- After Jan 1010.51453.725Inv#081 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1453.725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7062 | 20201127-15 | 53510504 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10.5 | HR | 9.16 | 0 |  |  | 128.205 | 16.6667 | 144.8716 | 2020-11-27 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loaded Rock truck, Rock truck hauling gravel all day. | 5 | C076-C116 | Cook Lake | 0 | 44166 |  | 37 | 44167 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting706220201127-15Excavator Thumb - 30 - 50 ton- After Jan 1010.5128.205 | Corbiere and Sons Contracting706220201127-15Excavator Thumb - 30 - 50 ton- After Jan 1010.5128.205Inv#081 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 128.205 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7062 | 20201127-15 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-11-27 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loaded Rock truck, Rock truck hauling gravel all day. | 5 | C076-C116 | Cook Lake | 0 | 44166 |  | 37 | 44167 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting706220201127-15Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting706220201127-15Light Truck - Pick up- After Jan 101243.75Inv#081 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7062 | 20201127-15 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 10.5 | Dynamic | 103.54 | 0 |  |  | 1449.525 | 188.4383 | 1637.9633 | 2020-11-27 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loaded Rock truck, Rock truck hauling gravel all day. | 5 | C076-C116 | Cook Lake | 0 | 44166 |  | 37 | 44167 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting706220201127-15Rock Truck - 30 Ton- After Jan 1010.51449.525 | Corbiere and Sons Contracting706220201127-15Rock Truck - 30 Ton- After Jan 1010.51449.525Inv#081 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1449.525 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7062 | 20201127-15 | 53510504 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-11-27 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loaded Rock truck, Rock truck hauling gravel all day. | 5 | C076-C116 | Cook Lake | 0 | 44166 |  | 37 | 44167 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting706220201127-15L.O.A.2420 | Corbiere and Sons Contracting706220201127-15L.O.A.2420Inv#081 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7062 | 20201127-15 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-11-27 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loaded Rock truck, Rock truck hauling gravel all day. | 5 | C076-C116 | Cook Lake | 0 | 44166 |  | 37 | 44167 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting706220201127-15Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting706220201127-15Operator - Principle - After Jan 1011.5862.5Inv#081 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7062 | 20201127-15 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 11.5 | HR |  |  | 70 | 0 | 805 | 104.65 | 909.65 | 2020-11-27 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loaded Rock truck, Rock truck hauling gravel all day. | 5 | C076-C116 | Cook Lake | 0 | 44166 |  | 37 | 44167 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting706220201127-15Driver - AZ - After Jan 1011.5805 | Corbiere and Sons Contracting706220201127-15Driver - AZ - After Jan 1011.5805Inv#081 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 805 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7065 | 20201127-18 | 53510511 | Access | 0 | 3rd Party Charges | 1 | 783.7 | unit |  |  |  |  | 783.7 | 101.881 | 885.581 | 2020-11-27 | 1 | Inv#081 | 44173 | 128 | 0 | 1 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 15 | Approved | ROW INTERNAL - Sand for Road Maintenance - 3rd Party | 9015 | Sand used for winter access maintenance on Cooks and Antler Lake Rd. | 5 | C076-C116 | Cook Lake | 0 | 44166 |  | 36 | 44168 | 156 | Loaded and Delivered Sand to Cooks Laydown |  |  |  | Mike Lecocq | 05 | Corbiere and Sons Contracting706520201127-183rd Party Charges783.7783.7 | Corbiere and Sons Contracting706520201127-183rd Party Charges783.7783.7Inv#081 | [5 empty] | 1 | 783.7 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7320 | 20201127-20 | 53510412 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 9 | Dynamic | 98.61 | 0 |  |  | 1183.32 | 153.8316 | 1337.1516 | 2020-11-27 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Valard used D6 dozer to fix ruts between tower C-002 - C-006. | 4 | C002-C010 | Gravel River Road East | 0 | 44179 |  | 50 | 44180 | [5 empty] | Wes Seminowich | 04 | Corbiere and Sons Contracting732020201127-20Dozer D6 or equal- After Jan 1091183.32 | Corbiere and Sons Contracting732020201127-20Dozer D6 or equal- After Jan 1091183.32Inv#082 | [5 empty] | 1 | 1183.32 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7052 | 20201127-5 | 53510212 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 5 | Dynamic | 98.61 | 0 |  |  | 657.4 | 85.462 | 742.862 | 2020-11-27 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved dozer from Landfill to LoftyDozer cleared snow and ice at B-063 hill and made sure Valard pickups and equipment could get up the hill. | 2 | B054 - B064 | Lofty Davies | 0 | 44166 |  | 50 | 44168 | [5 empty] | Wes Seminowich | 02 | Corbiere and Sons Contracting705220201127-5Dozer D6 or equal- After Jan 105657.4 | Corbiere and Sons Contracting705220201127-5Dozer D6 or equal- After Jan 105657.4Inv#081 | [5 empty] | 1 | 657.4 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7052 | 20201127-5 | 53510212 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-11-27 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved dozer from Landfill to LoftyDozer cleared snow and ice at B-063 hill and made sure Valard pickups and equipment could get up the hill. | 2 | B054 - B064 | Lofty Davies | 0 | 44166 |  | 50 | 44168 | [5 empty] | Wes Seminowich | 02 | Corbiere and Sons Contracting705220201127-5Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting705220201127-5Light Truck - Pick up- After Jan 101243.75Inv#081 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7052 | 20201127-5 | 53510212 | Access | 0 | Tractor Trailer - 50 Ton- After Jan 10 | 111.75 | 2 | Dynamic | 83.81 | 0 |  |  | 223.5 | 29.055 | 252.555 | 2020-11-27 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved dozer from Landfill to LoftyDozer cleared snow and ice at B-063 hill and made sure Valard pickups and equipment could get up the hill. | 2 | B054 - B064 | Lofty Davies | 0 | 44166 |  | 50 | 44168 | [5 empty] | Wes Seminowich | 02 | Corbiere and Sons Contracting705220201127-5Tractor Trailer - 50 Ton- After Jan 102223.5 | Corbiere and Sons Contracting705220201127-5Tractor Trailer - 50 Ton- After Jan 102223.5Inv#081 | [5 empty] | 1 | 223.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7052 | 20201127-5 | 53510212 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5.5 | HR |  |  | 75 | 0 | 412.5 | 53.625 | 466.125 | 2020-11-27 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved dozer from Landfill to LoftyDozer cleared snow and ice at B-063 hill and made sure Valard pickups and equipment could get up the hill. | 2 | B054 - B064 | Lofty Davies | 0 | 44166 |  | 50 | 44168 | [5 empty] | Wes Seminowich | 02 | Corbiere and Sons Contracting705220201127-5Operator - Principle - After Jan 105.5412.5 | Corbiere and Sons Contracting705220201127-5Operator - Principle - After Jan 105.5412.5Inv#081 | [5 empty] | 1 | 412.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7052 | 20201127-5 | 53510212 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 2 | HR |  |  | 70 | 0 | 140 | 18.2 | 158.2 | 2020-11-27 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved dozer from Landfill to LoftyDozer cleared snow and ice at B-063 hill and made sure Valard pickups and equipment could get up the hill. | 2 | B054 - B064 | Lofty Davies | 0 | 44166 |  | 50 | 44168 | [5 empty] | Wes Seminowich | 02 | Corbiere and Sons Contracting705220201127-5Driver - AZ - After Jan 102140 | Corbiere and Sons Contracting705220201127-5Driver - AZ - After Jan 102140Inv#081 | [5 empty] | 1 | 140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7053 | 20201127-6 | 53510312 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 5 | Dynamic | 98.61 | 0 |  |  | 657.4 | 85.462 | 742.862 | 2020-11-27 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer cleared snow and broke up icy patches in Landfill Rd | 3 | B078-B084 | Red Rock Rd No. 7 | 0 | 44166 |  | 50 | 44168 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting705320201127-6Dozer D6 or equal- After Jan 105657.4 | Corbiere and Sons Contracting705320201127-6Dozer D6 or equal- After Jan 105657.4Inv#081 | [5 empty] | 1 | 657.4 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7053 | 20201127-6 | 53510312 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 75 | 0 | 450 | 58.5 | 508.5 | 2020-11-27 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer cleared snow and broke up icy patches in Landfill Rd | 3 | B078-B084 | Red Rock Rd No. 7 | 0 | 44166 |  | 50 | 44168 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting705320201127-6Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting705320201127-6Operator - Principle - After Jan 106450Inv#081 | [5 empty] | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7055 | 20201127-8 | 53510412 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-11-27 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jean Marc ran Gervais dozer in Gravel River Rd | 4 | C002-C010 | Gravel River Road East | 0 | 44166 |  | 50 | 44168 | [5 empty] | Wes Seminowich | 04 | Corbiere and Sons Contracting705520201127-8Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting705520201127-8Light Truck - Pick up- After Jan 101243.75Inv#081 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7055 | 20201127-8 | 53510412 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 10 | HR |  |  | 75 | 0 | 750 | 97.5 | 847.5 | 2020-11-27 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jean Marc ran Gervais dozer in Gravel River Rd | 4 | C002-C010 | Gravel River Road East | 0 | 44166 |  | 50 | 44168 | [5 empty] | Wes Seminowich | 04 | Corbiere and Sons Contracting705520201127-8Operator - Principle - After Jan 1010750 | Corbiere and Sons Contracting705520201127-8Operator - Principle - After Jan 1010750Inv#081 | [5 empty] | 1 | 750 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7056 | 20201127-9 | 53510412 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10 | Dynamic | 98.61 | 0 |  |  | 1314.8 | 170.924 | 1485.724 | 2020-11-27 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | DZ-04 plowed snow and broke up icy patches in Nishin East C-014 - C-025. | 4 | C015-C029 | Nishin Creek Road | 0 | 44166 |  | 50 | 44168 | [5 empty] | Wes Seminowich | 04 | Corbiere and Sons Contracting705620201127-9Dozer D6 or equal- After Jan 10101314.8 | Corbiere and Sons Contracting705620201127-9Dozer D6 or equal- After Jan 10101314.8Inv#081 | [5 empty] | 1 | 1314.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7056 | 20201127-9 | 53510412 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-11-27 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | DZ-04 plowed snow and broke up icy patches in Nishin East C-014 - C-025. | 4 | C015-C029 | Nishin Creek Road | 0 | 44166 |  | 50 | 44168 | [5 empty] | Wes Seminowich | 04 | Corbiere and Sons Contracting705620201127-9Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting705620201127-9Light Truck - Pick up- After Jan 101243.75Inv#081 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7056 | 20201127-9 | 53510412 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2020-11-27 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | DZ-04 plowed snow and broke up icy patches in Nishin East C-014 - C-025. | 4 | C015-C029 | Nishin Creek Road | 0 | 44166 |  | 50 | 44168 | [5 empty] | Wes Seminowich | 04 | Corbiere and Sons Contracting705620201127-9Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting705620201127-9Operator - Principle - After Jan 1011825Inv#081 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7076 | 20201128-10 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10.5 | Dynamic | 95.24 | 0 |  |  | 1333.29 | 173.3277 | 1506.6177 | 2020-11-28 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Sander sanding across Cooks Lake Road all dayGrader all day working across access roads | 5 | C076-C116 | Cook Lake | 0 | 44166 |  | 37 | 44167 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting707620201128-10Grader - Cat 12 to 14 or equal- After Jan 1010.51333.29 | Corbiere and Sons Contracting707620201128-10Grader - Cat 12 to 14 or equal- After Jan 1010.51333.29Inv#081 | [5 empty] | 1 | 1333.29 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7076 | 20201128-10 | 53510511 | Access | 0 | Sander Truck - Hwy- After Jan 10 | 55 | 10.5 | Dynamic | 41.25 | 0 |  |  | 577.5 | 75.075 | 652.575 | 2020-11-28 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Sander sanding across Cooks Lake Road all dayGrader all day working across access roads | 5 | C076-C116 | Cook Lake | 0 | 44166 |  | 37 | 44167 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting707620201128-10Sander Truck - Hwy- After Jan 1010.5577.5 | Corbiere and Sons Contracting707620201128-10Sander Truck - Hwy- After Jan 1010.5577.5Inv#081 | [5 empty] | 1 | 577.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7076 | 20201128-10 | 53510511 | Access | 0 | ATV - Side by Side w/ roll bar- After Jan 10 | 18.45 | 4 | HR | 13.84 | 0 |  |  | 73.8 | 9.594 | 83.394 | 2020-11-28 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Sander sanding across Cooks Lake Road all dayGrader all day working across access roads | 5 | C076-C116 | Cook Lake | 0 | 44166 |  | 37 | 44167 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting707620201128-10ATV - Side by Side w/ roll bar- After Jan 10473.8 | Corbiere and Sons Contracting707620201128-10ATV - Side by Side w/ roll bar- After Jan 10473.8Inv#081 | [5 empty] | 1 | 73.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7076 | 20201128-10 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-11-28 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Sander sanding across Cooks Lake Road all dayGrader all day working across access roads | 5 | C076-C116 | Cook Lake | 0 | 44166 |  | 37 | 44167 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting707620201128-10Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting707620201128-10Light Truck - Pick up- After Jan 102487.5Inv#081 | [5 empty] | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7076 | 20201128-10 | 53510511 | Access | 0 | Foreman | 95 | 4 | HR |  |  | 95 | 0 | 380 | 49.4 | 429.4 | 2020-11-28 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Sander sanding across Cooks Lake Road all dayGrader all day working across access roads | 5 | C076-C116 | Cook Lake | 0 | 44166 |  | 37 | 44167 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting707620201128-10Foreman4380 | Corbiere and Sons Contracting707620201128-10Foreman4380Inv#081 | [5 empty] | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7076 | 20201128-10 | 53510511 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2020-11-28 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Sander sanding across Cooks Lake Road all dayGrader all day working across access roads | 5 | C076-C116 | Cook Lake | 0 | 44166 |  | 37 | 44167 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting707620201128-10L.O.A.3630 | Corbiere and Sons Contracting707620201128-10L.O.A.3630Inv#081 | [5 empty] | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7076 | 20201128-10 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 23 | HR |  |  | 75 | 0 | 1725 | 224.25 | 1949.25 | 2020-11-28 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Sander sanding across Cooks Lake Road all dayGrader all day working across access roads | 5 | C076-C116 | Cook Lake | 0 | 44166 |  | 37 | 44167 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting707620201128-10Operator - Principle - After Jan 10231725 | Corbiere and Sons Contracting707620201128-10Operator - Principle - After Jan 10231725Inv#081 | [5 empty] | 1 | 1725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7077 | 20201128-11 | 53510503 | Access | 0 | Feller Buncher | 240 | 6 | HR | 180 | 0 |  |  | 1440 | 187.2 | 1627.2 | 2020-11-28 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Operators put down 70m of corduroy from C-111 | 5 | C076-C116 | Cook Lake | 0 | 44166 |  | 37 | 44167 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting707720201128-11Feller Buncher61440 | Corbiere and Sons Contracting707720201128-11Feller Buncher61440Inv#081 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 1440 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7077 | 20201128-11 | 53510503 | Access | 0 | Skidder | 171 | 6 | HR | 128.25 | 0 |  |  | 1026 | 133.38 | 1159.38 | 2020-11-28 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Operators put down 70m of corduroy from C-111 | 5 | C076-C116 | Cook Lake | 0 | 44166 |  | 37 | 44167 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting707720201128-11Skidder 61026 | Corbiere and Sons Contracting707720201128-11Skidder 61026Inv#081 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 1026 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7077 | 20201128-11 | 53510503 | Access | 0 | ATV - Side by Side w/ roll bar- After Jan 10 | 18.45 | 4 | HR | 13.84 | 0 |  |  | 73.8 | 9.594 | 83.394 | 2020-11-28 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Operators put down 70m of corduroy from C-111 | 5 | C076-C116 | Cook Lake | 0 | 44166 |  | 37 | 44167 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting707720201128-11ATV - Side by Side w/ roll bar- After Jan 10473.8 | Corbiere and Sons Contracting707720201128-11ATV - Side by Side w/ roll bar- After Jan 10473.8Inv#081 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 73.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7077 | 20201128-11 | 53510503 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-11-28 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Operators put down 70m of corduroy from C-111 | 5 | C076-C116 | Cook Lake | 0 | 44166 |  | 37 | 44167 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting707720201128-11Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting707720201128-11Light Truck - Pick up- After Jan 101243.75Inv#081 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7077 | 20201128-11 | 53510503 | Access | 0 | Foreman | 95 | 4 | HR |  |  | 95 | 0 | 380 | 49.4 | 429.4 | 2020-11-28 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Operators put down 70m of corduroy from C-111 | 5 | C076-C116 | Cook Lake | 0 | 44166 |  | 37 | 44167 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting707720201128-11Foreman4380 | Corbiere and Sons Contracting707720201128-11Foreman4380Inv#081 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7077 | 20201128-11 | 53510503 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-11-28 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Operators put down 70m of corduroy from C-111 | 5 | C076-C116 | Cook Lake | 0 | 44166 |  | 37 | 44167 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting707720201128-11L.O.A.2420 | Corbiere and Sons Contracting707720201128-11L.O.A.2420Inv#081 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7077 | 20201128-11 | 53510503 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2020-11-28 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Operators put down 70m of corduroy from C-111 | 5 | C076-C116 | Cook Lake | 0 | 44166 |  | 37 | 44167 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting707720201128-11Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting707720201128-11Operator - Principle - After Jan 1012900Inv#081 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7078 | 20201128-12 | 53510504 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 6 | Dynamic | 110.22 | 0 |  |  | 881.76 | 114.6288 | 996.3888 | 2020-11-28 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks for gravel haul, rock truck hauled gravel, labourer put down corduroy for gravel haul. | 5 | C076-C116 | Cook Lake | 0 | 44166 |  | 37 | 44167 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting707820201128-12Excavator - 36 ton- After Jan 106881.76 | Corbiere and Sons Contracting707820201128-12Excavator - 36 ton- After Jan 106881.76Inv#081 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 881.76 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7078 | 20201128-12 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-11-28 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks for gravel haul, rock truck hauled gravel, labourer put down corduroy for gravel haul. | 5 | C076-C116 | Cook Lake | 0 | 44166 |  | 37 | 44167 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting707820201128-12Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting707820201128-12Light Truck - Pick up- After Jan 101243.75Inv#081 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7078 | 20201128-12 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 6 | Dynamic | 103.54 | 0 |  |  | 828.3 | 107.679 | 935.979 | 2020-11-28 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks for gravel haul, rock truck hauled gravel, labourer put down corduroy for gravel haul. | 5 | C076-C116 | Cook Lake | 0 | 44166 |  | 37 | 44167 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting707820201128-12Rock Truck - 30 Ton- After Jan 106828.3 | Corbiere and Sons Contracting707820201128-12Rock Truck - 30 Ton- After Jan 106828.3Inv#081 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 828.3 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7078 | 20201128-12 | 53510504 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2020-11-28 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks for gravel haul, rock truck hauled gravel, labourer put down corduroy for gravel haul. | 5 | C076-C116 | Cook Lake | 0 | 44166 |  | 37 | 44167 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting707820201128-12L.O.A.3630 | Corbiere and Sons Contracting707820201128-12L.O.A.3630Inv#081 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7078 | 20201128-12 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 75 | 0 | 450 | 58.5 | 508.5 | 2020-11-28 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks for gravel haul, rock truck hauled gravel, labourer put down corduroy for gravel haul. | 5 | C076-C116 | Cook Lake | 0 | 44166 |  | 37 | 44167 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting707820201128-12Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting707820201128-12Operator - Principle - After Jan 106450Inv#081 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7078 | 20201128-12 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 6 | HR |  |  | 70 | 0 | 420 | 54.6 | 474.6 | 2020-11-28 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks for gravel haul, rock truck hauled gravel, labourer put down corduroy for gravel haul. | 5 | C076-C116 | Cook Lake | 0 | 44166 |  | 37 | 44167 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting707820201128-12Driver - AZ - After Jan 106420 | Corbiere and Sons Contracting707820201128-12Driver - AZ - After Jan 106420Inv#081 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7078 | 20201128-12 | 53510504 | Access | 0 | Labourer - General - After Jan 10 | 60 | 3 | HR |  |  | 60 | 0 | 180 | 23.4 | 203.4 | 2020-11-28 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks for gravel haul, rock truck hauled gravel, labourer put down corduroy for gravel haul. | 5 | C076-C116 | Cook Lake | 0 | 44166 |  | 37 | 44167 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting707820201128-12Labourer - General - After Jan 103180 | Corbiere and Sons Contracting707820201128-12Labourer - General - After Jan 103180Inv#081 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 180 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7115 | 20201128-14 | 53510212 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10 | Dynamic | 98.61 | 0 |  |  | 1314.8 | 170.924 | 1485.724 | 2020-11-28 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved dozer from Lofty to LandfillDozer cleared snow and ice at B-063 hill and floated to Landfill and cleared at B-084. | 2 | B065-B077 | Red Rock | 0 | 44170 |  | 37 | 44171 | [5 empty] | Harold Furlong | 02 | Corbiere and Sons Contracting711520201128-14Dozer D6 or equal- After Jan 10101314.8 | Corbiere and Sons Contracting711520201128-14Dozer D6 or equal- After Jan 10101314.8Inv#081 | [5 empty] | 1 | 1314.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7115 | 20201128-14 | 53510212 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-11-28 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved dozer from Lofty to LandfillDozer cleared snow and ice at B-063 hill and floated to Landfill and cleared at B-084. | 2 | B065-B077 | Red Rock | 0 | 44170 |  | 37 | 44171 | [5 empty] | Harold Furlong | 02 | Corbiere and Sons Contracting711520201128-14Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting711520201128-14Light Truck - Pick up- After Jan 101243.75Inv#081 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7115 | 20201128-14 | 53510212 | Access | 0 | Tractor Trailer - 50 Ton- After Jan 10 | 111.75 | 2 | Dynamic | 83.81 | 0 |  |  | 223.5 | 29.055 | 252.555 | 2020-11-28 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved dozer from Lofty to LandfillDozer cleared snow and ice at B-063 hill and floated to Landfill and cleared at B-084. | 2 | B065-B077 | Red Rock | 0 | 44170 |  | 37 | 44171 | [5 empty] | Harold Furlong | 02 | Corbiere and Sons Contracting711520201128-14Tractor Trailer - 50 Ton- After Jan 102223.5 | Corbiere and Sons Contracting711520201128-14Tractor Trailer - 50 Ton- After Jan 102223.5Inv#081 | [5 empty] | 1 | 223.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7115 | 20201128-14 | 53510212 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2020-11-28 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved dozer from Lofty to LandfillDozer cleared snow and ice at B-063 hill and floated to Landfill and cleared at B-084. | 2 | B065-B077 | Red Rock | 0 | 44170 |  | 37 | 44171 | [5 empty] | Harold Furlong | 02 | Corbiere and Sons Contracting711520201128-14Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting711520201128-14Operator - Principle - After Jan 1011825Inv#081 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7115 | 20201128-14 | 53510212 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 2 | HR |  |  | 70 | 0 | 140 | 18.2 | 158.2 | 2020-11-28 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved dozer from Lofty to LandfillDozer cleared snow and ice at B-063 hill and floated to Landfill and cleared at B-084. | 2 | B065-B077 | Red Rock | 0 | 44170 |  | 37 | 44171 | [5 empty] | Harold Furlong | 02 | Corbiere and Sons Contracting711520201128-14Driver - AZ - After Jan 102140 | Corbiere and Sons Contracting711520201128-14Driver - AZ - After Jan 102140Inv#081 | [5 empty] | 1 | 140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7117 | 20201128-16 | 53510412 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 5 | Dynamic | 110.22 | 0 |  |  | 734.8 | 95.524 | 830.324 | 2020-11-28 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-02 fixed up punch outs | 4 | B194-B203 | Little Gravel River Road | 0 | 44170 |  | 37 | 44171 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting711720201128-16Excavator - 36 ton- After Jan 105734.8 | Corbiere and Sons Contracting711720201128-16Excavator - 36 ton- After Jan 105734.8Inv#081 | [5 empty] | 1 | 734.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7117 | 20201128-16 | 53510412 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 5 | HR | 9.16 | 0 |  |  | 61.05 | 7.9365 | 68.9865 | 2020-11-28 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-02 fixed up punch outs | 4 | B194-B203 | Little Gravel River Road | 0 | 44170 |  | 37 | 44171 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting711720201128-16Excavator Thumb - 30 - 50 ton- After Jan 10561.05 | Corbiere and Sons Contracting711720201128-16Excavator Thumb - 30 - 50 ton- After Jan 10561.05Inv#081 | [5 empty] | 1 | 61.05 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7117 | 20201128-16 | 53510412 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-11-28 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-02 fixed up punch outs | 4 | B194-B203 | Little Gravel River Road | 0 | 44170 |  | 37 | 44171 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting711720201128-16Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting711720201128-16Light Truck - Pick up- After Jan 102487.5Inv#081 | [5 empty] | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7117 | 20201128-16 | 53510412 | Access | 0 | Foreman | 95 | 4 | HR |  |  | 95 | 0 | 380 | 49.4 | 429.4 | 2020-11-28 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-02 fixed up punch outs | 4 | B194-B203 | Little Gravel River Road | 0 | 44170 |  | 37 | 44171 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting711720201128-16Foreman4380 | Corbiere and Sons Contracting711720201128-16Foreman4380Inv#081 | [5 empty] | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7117 | 20201128-16 | 53510412 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5 | HR |  |  | 75 | 0 | 375 | 48.75 | 423.75 | 2020-11-28 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-02 fixed up punch outs | 4 | B194-B203 | Little Gravel River Road | 0 | 44170 |  | 37 | 44171 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting711720201128-16Operator - Principle - After Jan 105375 | Corbiere and Sons Contracting711720201128-16Operator - Principle - After Jan 105375Inv#081 | [5 empty] | 1 | 375 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7118 | 20201128-17 | 53510412 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 11 | Dynamic | 98.61 | 0 |  |  | 1446.28 | 188.0164 | 1634.2964 | 2020-11-28 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | DZ-05 cleared snow and trimmed Nishin Lake Road and then floated over to Blair Lake Road and fixed bad spots on access road. | 4 | C011-C029 | Nishin Creek Road | 0 | 44170 |  | 37 | 44171 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting711820201128-17Dozer D6 or equal- After Jan 10111446.28 | Corbiere and Sons Contracting711820201128-17Dozer D6 or equal- After Jan 10111446.28Inv#081 | [5 empty] | 1 | 1446.28 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7118 | 20201128-17 | 53510412 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-11-28 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | DZ-05 cleared snow and trimmed Nishin Lake Road and then floated over to Blair Lake Road and fixed bad spots on access road. | 4 | C011-C029 | Nishin Creek Road | 0 | 44170 |  | 37 | 44171 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting711820201128-17Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting711820201128-17Light Truck - Pick up- After Jan 101243.75Inv#081 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7118 | 20201128-17 | 53510412 | Access | 0 | Tractor Trailer - 50 Ton- After Jan 10 | 111.75 | 2 | Dynamic | 83.81 | 0 |  |  | 223.5 | 29.055 | 252.555 | 2020-11-28 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | DZ-05 cleared snow and trimmed Nishin Lake Road and then floated over to Blair Lake Road and fixed bad spots on access road. | 4 | C011-C029 | Nishin Creek Road | 0 | 44170 |  | 37 | 44171 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting711820201128-17Tractor Trailer - 50 Ton- After Jan 102223.5 | Corbiere and Sons Contracting711820201128-17Tractor Trailer - 50 Ton- After Jan 102223.5Inv#081 | [5 empty] | 1 | 223.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7118 | 20201128-17 | 53510412 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 13 | HR |  |  | 75 | 0 | 975 | 126.75 | 1101.75 | 2020-11-28 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | DZ-05 cleared snow and trimmed Nishin Lake Road and then floated over to Blair Lake Road and fixed bad spots on access road. | 4 | C011-C029 | Nishin Creek Road | 0 | 44170 |  | 37 | 44171 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting711820201128-17Operator - Principle - After Jan 1013975 | Corbiere and Sons Contracting711820201128-17Operator - Principle - After Jan 1013975Inv#081 | [5 empty] | 1 | 975 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7118 | 20201128-17 | 53510412 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 2 | HR |  |  | 70 | 0 | 140 | 18.2 | 158.2 | 2020-11-28 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | DZ-05 cleared snow and trimmed Nishin Lake Road and then floated over to Blair Lake Road and fixed bad spots on access road. | 4 | C011-C029 | Nishin Creek Road | 0 | 44170 |  | 37 | 44171 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting711820201128-17Driver - AZ - After Jan 102140 | Corbiere and Sons Contracting711820201128-17Driver - AZ - After Jan 102140Inv#081 | [5 empty] | 1 | 140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7139 | 20201129-11 | 53510504 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10.5 | Dynamic | 98.61 | 0 |  |  | 1380.54 | 179.4702 | 1560.0102 | 2020-11-29 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-015 loading rock trucks, rock trucks hauling gravel to Cooks Lake West C-080, dozer spreading gravel from C-080.Labourer loaded up some geo and delivered to Terry at Cooks West and put down. | 5 | C076-C092 | Cook Lake | 0 | 44172 |  | 37 | 44172 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting713920201129-11Dozer D6 or equal- After Jan 1010.51380.54 | Corbiere and Sons Contracting713920201129-11Dozer D6 or equal- After Jan 1010.51380.54Inv#082 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1380.54 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7139 | 20201129-11 | 53510504 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10.5 | Dynamic | 103.84 | 0 |  |  | 1453.725 | 188.9843 | 1642.7093 | 2020-11-29 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-015 loading rock trucks, rock trucks hauling gravel to Cooks Lake West C-080, dozer spreading gravel from C-080.Labourer loaded up some geo and delivered to Terry at Cooks West and put down. | 5 | C076-C092 | Cook Lake | 0 | 44172 |  | 37 | 44172 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting713920201129-11Excavator - 30 ton- After Jan 1010.51453.725 | Corbiere and Sons Contracting713920201129-11Excavator - 30 ton- After Jan 1010.51453.725Inv#082 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1453.725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7139 | 20201129-11 | 53510504 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10.5 | HR | 9.16 | 0 |  |  | 128.205 | 16.6667 | 144.8716 | 2020-11-29 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-015 loading rock trucks, rock trucks hauling gravel to Cooks Lake West C-080, dozer spreading gravel from C-080.Labourer loaded up some geo and delivered to Terry at Cooks West and put down. | 5 | C076-C092 | Cook Lake | 0 | 44172 |  | 37 | 44172 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting713920201129-11Excavator Thumb - 30 - 50 ton- After Jan 1010.5128.205 | Corbiere and Sons Contracting713920201129-11Excavator Thumb - 30 - 50 ton- After Jan 1010.5128.205Inv#082 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 128.205 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7139 | 20201129-11 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-11-29 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-015 loading rock trucks, rock trucks hauling gravel to Cooks Lake West C-080, dozer spreading gravel from C-080.Labourer loaded up some geo and delivered to Terry at Cooks West and put down. | 5 | C076-C092 | Cook Lake | 0 | 44172 |  | 37 | 44172 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting713920201129-11Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting713920201129-11Light Truck - Pick up- After Jan 102487.5Inv#082 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7139 | 20201129-11 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 26 | Dynamic | 103.54 | 0 |  |  | 3589.3 | 466.609 | 4055.909 | 2020-11-29 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-015 loading rock trucks, rock trucks hauling gravel to Cooks Lake West C-080, dozer spreading gravel from C-080.Labourer loaded up some geo and delivered to Terry at Cooks West and put down. | 5 | C076-C092 | Cook Lake | 0 | 44172 |  | 37 | 44172 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting713920201129-11Rock Truck - 30 Ton- After Jan 10263589.3 | Corbiere and Sons Contracting713920201129-11Rock Truck - 30 Ton- After Jan 10263589.3Inv#082 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 3589.3 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7139 | 20201129-11 | 53510504 | Access | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2020-11-29 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-015 loading rock trucks, rock trucks hauling gravel to Cooks Lake West C-080, dozer spreading gravel from C-080.Labourer loaded up some geo and delivered to Terry at Cooks West and put down. | 5 | C076-C092 | Cook Lake | 0 | 44172 |  | 37 | 44172 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting713920201129-11L.O.A.51050 | Corbiere and Sons Contracting713920201129-11L.O.A.51050Inv#082 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7139 | 20201129-11 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 23 | HR |  |  | 75 | 0 | 1725 | 224.25 | 1949.25 | 2020-11-29 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-015 loading rock trucks, rock trucks hauling gravel to Cooks Lake West C-080, dozer spreading gravel from C-080.Labourer loaded up some geo and delivered to Terry at Cooks West and put down. | 5 | C076-C092 | Cook Lake | 0 | 44172 |  | 37 | 44172 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting713920201129-11Operator - Principle - After Jan 10231725 | Corbiere and Sons Contracting713920201129-11Operator - Principle - After Jan 10231725Inv#082 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7139 | 20201129-11 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 28.5 | HR |  |  | 70 | 0 | 1995 | 259.35 | 2254.35 | 2020-11-29 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-015 loading rock trucks, rock trucks hauling gravel to Cooks Lake West C-080, dozer spreading gravel from C-080.Labourer loaded up some geo and delivered to Terry at Cooks West and put down. | 5 | C076-C092 | Cook Lake | 0 | 44172 |  | 37 | 44172 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting713920201129-11Driver - AZ - After Jan 1028.51995 | Corbiere and Sons Contracting713920201129-11Driver - AZ - After Jan 1028.51995Inv#082 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1995 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7139 | 20201129-11 | 53510504 | Access | 0 | Labourer - General - After Jan 10 | 60 | 4 | HR |  |  | 60 | 0 | 240 | 31.2 | 271.2 | 2020-11-29 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-015 loading rock trucks, rock trucks hauling gravel to Cooks Lake West C-080, dozer spreading gravel from C-080.Labourer loaded up some geo and delivered to Terry at Cooks West and put down. | 5 | C076-C092 | Cook Lake | 0 | 44172 |  | 37 | 44172 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting713920201129-11Labourer - General - After Jan 104240 | Corbiere and Sons Contracting713920201129-11Labourer - General - After Jan 104240Inv#082 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 240 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7141 | 20201129-13 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 11 | Dynamic | 95.24 | 0 |  |  | 1396.78 | 181.5814 | 1578.3614 | 2020-11-29 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grading across access roads all day. | 5 | C076-C116 | Cook Lake | 0 | 44172 |  | 37 | 44172 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting714120201129-13Grader - Cat 12 to 14 or equal- After Jan 10111396.78 | Corbiere and Sons Contracting714120201129-13Grader - Cat 12 to 14 or equal- After Jan 10111396.78Inv#082 | [5 empty] | 1 | 1396.78 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7141 | 20201129-13 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-11-29 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grading across access roads all day. | 5 | C076-C116 | Cook Lake | 0 | 44172 |  | 37 | 44172 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting714120201129-13Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting714120201129-13Light Truck - Pick up- After Jan 101243.75Inv#082 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7141 | 20201129-13 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-11-29 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grading across access roads all day. | 5 | C076-C116 | Cook Lake | 0 | 44172 |  | 37 | 44172 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting714120201129-13L.O.A.1210 | Corbiere and Sons Contracting714120201129-13L.O.A.1210Inv#082 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7141 | 20201129-13 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-11-29 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grading across access roads all day. | 5 | C076-C116 | Cook Lake | 0 | 44172 |  | 37 | 44172 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting714120201129-13Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting714120201129-13Operator - Principle - After Jan 1011.5862.5Inv#082 | [5 empty] | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7121 | 20201129-8 | 53510212 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 4 | Dynamic | 98.61 | 0 |  |  | 525.92 | 68.3696 | 594.2896 | 2020-11-29 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | DZ-01 cleared snow and ice at B-063 hill | 2 | B054 - B064 | Lofty Davies | 0 | 44170 |  | 37 | 44171 | [5 empty] | Harold Furlong | 02 | Corbiere and Sons Contracting712120201129-8Dozer D6 or equal- After Jan 104525.92 | Corbiere and Sons Contracting712120201129-8Dozer D6 or equal- After Jan 104525.92Inv#081 | [5 empty] | 1 | 525.92 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7121 | 20201129-8 | 53510212 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-11-29 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | DZ-01 cleared snow and ice at B-063 hill | 2 | B054 - B064 | Lofty Davies | 0 | 44170 |  | 37 | 44171 | [5 empty] | Harold Furlong | 02 | Corbiere and Sons Contracting712120201129-8Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting712120201129-8Light Truck - Pick up- After Jan 101243.75Inv#081 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7121 | 20201129-8 | 53510212 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5 | HR |  |  | 75 | 0 | 375 | 48.75 | 423.75 | 2020-11-29 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | DZ-01 cleared snow and ice at B-063 hill | 2 | B054 - B064 | Lofty Davies | 0 | 44170 |  | 37 | 44171 | [5 empty] | Harold Furlong | 02 | Corbiere and Sons Contracting712120201129-8Operator - Principle - After Jan 105375 | Corbiere and Sons Contracting712120201129-8Operator - Principle - After Jan 105375Inv#081 | [5 empty] | 1 | 375 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7122 | 20201129-9 | 53510212 | Access | 0 | Tractor Trailer - 50 Ton- After Jan 10 | 111.75 | 3.5 | Dynamic | 83.81 | 0 |  |  | 391.125 | 50.8462 | 441.9712 | 2020-11-29 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved DZ-01 from Landfill to Lofty Davies | 2 | B065-B077 | Red Rock | 0 | 44170 |  | 37 | 44171 | [5 empty] | Harold Furlong | 02 | Corbiere and Sons Contracting712220201129-9Tractor Trailer - 50 Ton- After Jan 103.5391.125 | Corbiere and Sons Contracting712220201129-9Tractor Trailer - 50 Ton- After Jan 103.5391.125Inv#081 | [5 empty] | 1 | 391.125 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7122 | 20201129-9 | 53510212 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 3.5 | HR |  |  | 70 | 0 | 245 | 31.85 | 276.85 | 2020-11-29 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved DZ-01 from Landfill to Lofty Davies | 2 | B065-B077 | Red Rock | 0 | 44170 |  | 37 | 44171 | [5 empty] | Harold Furlong | 02 | Corbiere and Sons Contracting712220201129-9Driver - AZ - After Jan 103.5245 | Corbiere and Sons Contracting712220201129-9Driver - AZ - After Jan 103.5245Inv#081 | [5 empty] | 1 | 245 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7134 | 20201130-11 | 53510212 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10 | Dynamic | 98.61 | 0 |  |  | 1314.8 | 170.924 | 1485.724 | 2020-11-30 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer cleared to B-064 at Lofty and cleared into LandfillSander sanded Lofty | 2 | B054 - B064 | Lofty Davies | 0 | 44170 |  | 37 | 44171 | [5 empty] | Harold Furlong | 02 | Corbiere and Sons Contracting713420201130-11Dozer D6 or equal- After Jan 10101314.8 | Corbiere and Sons Contracting713420201130-11Dozer D6 or equal- After Jan 10101314.8Inv#081 | [5 empty] | 1 | 1314.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7134 | 20201130-11 | 53510212 | Access | 0 | Sander Truck - Hwy- After Jan 10 | 55 | 4 | Dynamic | 41.25 | 0 |  |  | 220 | 28.6 | 248.6 | 2020-11-30 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer cleared to B-064 at Lofty and cleared into LandfillSander sanded Lofty | 2 | B054 - B064 | Lofty Davies | 0 | 44170 |  | 37 | 44171 | [5 empty] | Harold Furlong | 02 | Corbiere and Sons Contracting713420201130-11Sander Truck - Hwy- After Jan 104220 | Corbiere and Sons Contracting713420201130-11Sander Truck - Hwy- After Jan 104220Inv#081 | [5 empty] | 1 | 220 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7134 | 20201130-11 | 53510212 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-11-30 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer cleared to B-064 at Lofty and cleared into LandfillSander sanded Lofty | 2 | B054 - B064 | Lofty Davies | 0 | 44170 |  | 37 | 44171 | [5 empty] | Harold Furlong | 02 | Corbiere and Sons Contracting713420201130-11Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting713420201130-11Light Truck - Pick up- After Jan 101243.75Inv#081 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7134 | 20201130-11 | 53510212 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2020-11-30 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer cleared to B-064 at Lofty and cleared into LandfillSander sanded Lofty | 2 | B054 - B064 | Lofty Davies | 0 | 44170 |  | 37 | 44171 | [5 empty] | Harold Furlong | 02 | Corbiere and Sons Contracting713420201130-11Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting713420201130-11Operator - Principle - After Jan 1011825Inv#081 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7134 | 20201130-11 | 53510212 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 4 | HR |  |  | 70 | 0 | 280 | 36.4 | 316.4 | 2020-11-30 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer cleared to B-064 at Lofty and cleared into LandfillSander sanded Lofty | 2 | B054 - B064 | Lofty Davies | 0 | 44170 |  | 37 | 44171 | [5 empty] | Harold Furlong | 02 | Corbiere and Sons Contracting713420201130-11Driver - AZ - After Jan 104280 | Corbiere and Sons Contracting713420201130-11Driver - AZ - After Jan 104280Inv#081 | [5 empty] | 1 | 280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7129 | 20201130-6 | 53510502 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10.5 | Dynamic | 103.84 | 0 |  |  | 1453.725 | 188.9843 | 1642.7093 | 2020-11-30 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-017 building road from C-061EX-014 & hammer working from C-061 and C-064 | 5 | C050-C069 | Antler Lake | 0 | 44170 |  | 37 | 44171 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting712920201130-6Excavator - 30 ton- After Jan 1010.51453.725 | Corbiere and Sons Contracting712920201130-6Excavator - 30 ton- After Jan 1010.51453.725Inv#081 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 1453.725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7129 | 20201130-6 | 53510502 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10.5 | Dynamic | 110.22 | 0 |  |  | 1543.08 | 200.6004 | 1743.6804 | 2020-11-30 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-017 building road from C-061EX-014 & hammer working from C-061 and C-064 | 5 | C050-C069 | Antler Lake | 0 | 44170 |  | 37 | 44171 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting712920201130-6Excavator - 36 ton- After Jan 1010.51543.08 | Corbiere and Sons Contracting712920201130-6Excavator - 36 ton- After Jan 1010.51543.08Inv#081 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 1543.08 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7129 | 20201130-6 | 53510502 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10.5 | HR | 9.16 | 0 |  |  | 128.205 | 16.6667 | 144.8716 | 2020-11-30 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-017 building road from C-061EX-014 & hammer working from C-061 and C-064 | 5 | C050-C069 | Antler Lake | 0 | 44170 |  | 37 | 44171 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting712920201130-6Excavator Thumb - 30 - 50 ton- After Jan 1010.5128.205 | Corbiere and Sons Contracting712920201130-6Excavator Thumb - 30 - 50 ton- After Jan 1010.5128.205Inv#081 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 128.205 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7129 | 20201130-6 | 53510502 | Access | 0 | Excavator Hammer - 30 - 50 ton- After Jan 10 | 63.38 | 10.5 | HR | 47.54 | 0 |  |  | 665.49 | 86.5137 | 752.0037 | 2020-11-30 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-017 building road from C-061EX-014 & hammer working from C-061 and C-064 | 5 | C050-C069 | Antler Lake | 0 | 44170 |  | 37 | 44171 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting712920201130-6Excavator Hammer - 30 - 50 ton- After Jan 1010.5665.49 | Corbiere and Sons Contracting712920201130-6Excavator Hammer - 30 - 50 ton- After Jan 1010.5665.49Inv#081 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 665.49 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7129 | 20201130-6 | 53510502 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-11-30 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-017 building road from C-061EX-014 & hammer working from C-061 and C-064 | 5 | C050-C069 | Antler Lake | 0 | 44170 |  | 37 | 44171 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting712920201130-6Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting712920201130-6Light Truck - Pick up- After Jan 101243.75Inv#081 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7129 | 20201130-6 | 53510502 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-11-30 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-017 building road from C-061EX-014 & hammer working from C-061 and C-064 | 5 | C050-C069 | Antler Lake | 0 | 44170 |  | 37 | 44171 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting712920201130-6L.O.A.2420 | Corbiere and Sons Contracting712920201130-6L.O.A.2420Inv#081 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7129 | 20201130-6 | 53510502 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 23 | HR |  |  | 75 | 0 | 1725 | 224.25 | 1949.25 | 2020-11-30 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-017 building road from C-061EX-014 & hammer working from C-061 and C-064 | 5 | C050-C069 | Antler Lake | 0 | 44170 |  | 37 | 44171 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting712920201130-6Operator - Principle - After Jan 10231725 | Corbiere and Sons Contracting712920201130-6Operator - Principle - After Jan 10231725Inv#081 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 1725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7130 | 20201130-7 | 53510504 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10.5 | Dynamic | 98.61 | 0 |  |  | 1380.54 | 179.4702 | 1560.0102 | 2020-11-30 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Exacavator loading rock trucks all day, Rocks truck each hauling gravel to C-079 and C-081 all day, Dozer spreading gravel from C-019 and Dozer spreading and capping from C-109. Labourer rolled out geo for gravel haul | 5 | C076-C116 | Cook Lake | 0 | 44170 |  | 37 | 44171 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting713020201130-7Dozer D6 or equal- After Jan 1010.51380.54 | Corbiere and Sons Contracting713020201130-7Dozer D6 or equal- After Jan 1010.51380.54Inv#081 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1380.54 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7130 | 20201130-7 | 53510504 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10.5 | Dynamic | 98.61 | 0 |  |  | 1380.54 | 179.4702 | 1560.0102 | 2020-11-30 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Exacavator loading rock trucks all day, Rocks truck each hauling gravel to C-079 and C-081 all day, Dozer spreading gravel from C-019 and Dozer spreading and capping from C-109. Labourer rolled out geo for gravel haul | 5 | C076-C116 | Cook Lake | 0 | 44170 |  | 37 | 44171 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting713020201130-7Dozer D6 or equal- After Jan 1010.51380.54 | Corbiere and Sons Contracting713020201130-7Dozer D6 or equal- After Jan 1010.51380.54Inv#081 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1380.54 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7130 | 20201130-7 | 53510504 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10.5 | Dynamic | 103.84 | 0 |  |  | 1453.725 | 188.9843 | 1642.7093 | 2020-11-30 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Exacavator loading rock trucks all day, Rocks truck each hauling gravel to C-079 and C-081 all day, Dozer spreading gravel from C-019 and Dozer spreading and capping from C-109. Labourer rolled out geo for gravel haul | 5 | C076-C116 | Cook Lake | 0 | 44170 |  | 37 | 44171 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting713020201130-7Excavator - 30 ton- After Jan 1010.51453.725 | Corbiere and Sons Contracting713020201130-7Excavator - 30 ton- After Jan 1010.51453.725Inv#081 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1453.725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7130 | 20201130-7 | 53510504 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10.5 | HR | 9.16 | 0 |  |  | 128.205 | 16.6667 | 144.8716 | 2020-11-30 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Exacavator loading rock trucks all day, Rocks truck each hauling gravel to C-079 and C-081 all day, Dozer spreading gravel from C-019 and Dozer spreading and capping from C-109. Labourer rolled out geo for gravel haul | 5 | C076-C116 | Cook Lake | 0 | 44170 |  | 37 | 44171 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting713020201130-7Excavator Thumb - 30 - 50 ton- After Jan 1010.5128.205 | Corbiere and Sons Contracting713020201130-7Excavator Thumb - 30 - 50 ton- After Jan 1010.5128.205Inv#081 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 128.205 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7130 | 20201130-7 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 21 | Dynamic | 103.54 | 0 |  |  | 2899.05 | 376.8765 | 3275.9265 | 2020-11-30 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Exacavator loading rock trucks all day, Rocks truck each hauling gravel to C-079 and C-081 all day, Dozer spreading gravel from C-019 and Dozer spreading and capping from C-109. Labourer rolled out geo for gravel haul | 5 | C076-C116 | Cook Lake | 0 | 44170 |  | 37 | 44171 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting713020201130-7Rock Truck - 30 Ton- After Jan 10212899.05 | Corbiere and Sons Contracting713020201130-7Rock Truck - 30 Ton- After Jan 10212899.05Inv#081 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 2899.05 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7130 | 20201130-7 | 53510504 | Access | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2020-11-30 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Exacavator loading rock trucks all day, Rocks truck each hauling gravel to C-079 and C-081 all day, Dozer spreading gravel from C-019 and Dozer spreading and capping from C-109. Labourer rolled out geo for gravel haul | 5 | C076-C116 | Cook Lake | 0 | 44170 |  | 37 | 44171 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting713020201130-7L.O.A.51050 | Corbiere and Sons Contracting713020201130-7L.O.A.51050Inv#081 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7130 | 20201130-7 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 34.5 | HR |  |  | 75 | 0 | 2587.5 | 336.375 | 2923.875 | 2020-11-30 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Exacavator loading rock trucks all day, Rocks truck each hauling gravel to C-079 and C-081 all day, Dozer spreading gravel from C-019 and Dozer spreading and capping from C-109. Labourer rolled out geo for gravel haul | 5 | C076-C116 | Cook Lake | 0 | 44170 |  | 37 | 44171 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting713020201130-7Operator - Principle - After Jan 1034.52587.5 | Corbiere and Sons Contracting713020201130-7Operator - Principle - After Jan 1034.52587.5Inv#081 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 2587.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7130 | 20201130-7 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 23 | HR |  |  | 70 | 0 | 1610 | 209.3 | 1819.3 | 2020-11-30 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Exacavator loading rock trucks all day, Rocks truck each hauling gravel to C-079 and C-081 all day, Dozer spreading gravel from C-019 and Dozer spreading and capping from C-109. Labourer rolled out geo for gravel haul | 5 | C076-C116 | Cook Lake | 0 | 44170 |  | 37 | 44171 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting713020201130-7Driver - AZ - After Jan 10231610 | Corbiere and Sons Contracting713020201130-7Driver - AZ - After Jan 10231610Inv#081 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1610 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7130 | 20201130-7 | 53510504 | Access | 0 | Labourer - General - After Jan 10 | 60 | 3 | HR |  |  | 60 | 0 | 180 | 23.4 | 203.4 | 2020-11-30 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Exacavator loading rock trucks all day, Rocks truck each hauling gravel to C-079 and C-081 all day, Dozer spreading gravel from C-019 and Dozer spreading and capping from C-109. Labourer rolled out geo for gravel haul | 5 | C076-C116 | Cook Lake | 0 | 44170 |  | 37 | 44171 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting713020201130-7Labourer - General - After Jan 103180 | Corbiere and Sons Contracting713020201130-7Labourer - General - After Jan 103180Inv#081 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 180 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7132 | 20201130-9 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10.5 | Dynamic | 95.24 | 0 |  |  | 1333.29 | 173.3277 | 1506.6177 | 2020-11-30 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader doing winter road maintenance all day | 5 | C076-C116 | Cook Lake | 0 | 44170 |  | 37 | 44171 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting713220201130-9Grader - Cat 12 to 14 or equal- After Jan 1010.51333.29 | Corbiere and Sons Contracting713220201130-9Grader - Cat 12 to 14 or equal- After Jan 1010.51333.29Inv#081 | [5 empty] | 1 | 1333.29 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7132 | 20201130-9 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-11-30 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader doing winter road maintenance all day | 5 | C076-C116 | Cook Lake | 0 | 44170 |  | 37 | 44171 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting713220201130-9L.O.A.1210 | Corbiere and Sons Contracting713220201130-9L.O.A.1210Inv#081 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7132 | 20201130-9 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-11-30 | 1 | Inv#081 | 44173 | 128 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader doing winter road maintenance all day | 5 | C076-C116 | Cook Lake | 0 | 44170 |  | 37 | 44171 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting713220201130-9Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting713220201130-9Operator - Principle - After Jan 1011.5862.5Inv#081 | [5 empty] | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7151 | 20201201-10 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 9 | Dynamic | 95.24 | 0 |  |  | 1142.82 | 148.5666 | 1291.3866 | 2020-12-01 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader doing winter access maintenance all day. | 5 | C076-C116 | Cook Lake | 0 | 44172 |  | 37 | 44173 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting715120201201-10Grader - Cat 12 to 14 or equal- After Jan 1091142.82 | Corbiere and Sons Contracting715120201201-10Grader - Cat 12 to 14 or equal- After Jan 1091142.82Inv#082 | [5 empty] | 1 | 1142.82 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7151 | 20201201-10 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-12-01 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader doing winter access maintenance all day. | 5 | C076-C116 | Cook Lake | 0 | 44172 |  | 37 | 44173 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting715120201201-10Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting715120201201-10Light Truck - Pick up- After Jan 101243.75Inv#082 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7151 | 20201201-10 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-12-01 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader doing winter access maintenance all day. | 5 | C076-C116 | Cook Lake | 0 | 44172 |  | 37 | 44173 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting715120201201-10L.O.A.1210 | Corbiere and Sons Contracting715120201201-10L.O.A.1210Inv#082 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7151 | 20201201-10 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 10 | HR |  |  | 75 | 0 | 750 | 97.5 | 847.5 | 2020-12-01 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader doing winter access maintenance all day. | 5 | C076-C116 | Cook Lake | 0 | 44172 |  | 37 | 44173 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting715120201201-10Operator - Principle - After Jan 1010750 | Corbiere and Sons Contracting715120201201-10Operator - Principle - After Jan 1010750Inv#082 | [5 empty] | 1 | 750 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7152 | 20201201-11 | 53510502 | Access | 0 | Skidder | 171 | 10.5 | HR | 128.25 | 0 |  |  | 1795.5 | 233.415 | 2028.915 | 2020-12-01 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building AN road from C-075 | 5 | C070-C075 | White Sand | 0 | 44172 |  | 37 | 44173 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting715220201201-11Skidder 10.51795.5 | Corbiere and Sons Contracting715220201201-11Skidder 10.51795.5Inv#082 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 1795.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7152 | 20201201-11 | 53510502 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10.5 | Dynamic | 103.84 | 0 |  |  | 1453.725 | 188.9843 | 1642.7093 | 2020-12-01 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building AN road from C-075 | 5 | C070-C075 | White Sand | 0 | 44172 |  | 37 | 44173 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting715220201201-11Excavator - 30 ton- After Jan 1010.51453.725 | Corbiere and Sons Contracting715220201201-11Excavator - 30 ton- After Jan 1010.51453.725Inv#082 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 1453.725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7152 | 20201201-11 | 53510502 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-12-01 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building AN road from C-075 | 5 | C070-C075 | White Sand | 0 | 44172 |  | 37 | 44173 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting715220201201-11Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting715220201201-11Light Truck - Pick up- After Jan 101243.75Inv#082 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7152 | 20201201-11 | 53510502 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-12-01 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building AN road from C-075 | 5 | C070-C075 | White Sand | 0 | 44172 |  | 37 | 44173 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting715220201201-11L.O.A.2420 | Corbiere and Sons Contracting715220201201-11L.O.A.2420Inv#082 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7152 | 20201201-11 | 53510502 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 23 | HR |  |  | 75 | 0 | 1725 | 224.25 | 1949.25 | 2020-12-01 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building AN road from C-075 | 5 | C070-C075 | White Sand | 0 | 44172 |  | 37 | 44173 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting715220201201-11Operator - Principle - After Jan 10231725 | Corbiere and Sons Contracting715220201201-11Operator - Principle - After Jan 10231725Inv#082 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 1725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7148 | 20201201-7 | 53510502 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10.5 | Dynamic | 103.84 | 0 |  |  | 1453.725 | 188.9843 | 1642.7093 | 2020-12-01 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building road from C-061. | 5 | C050-C069 | Antler Lake | 0 | 44172 |  | 37 | 44173 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting714820201201-7Excavator - 30 ton- After Jan 1010.51453.725 | Corbiere and Sons Contracting714820201201-7Excavator - 30 ton- After Jan 1010.51453.725Inv#082 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 1453.725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7148 | 20201201-7 | 53510502 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10.5 | HR | 9.16 | 0 |  |  | 128.205 | 16.6667 | 144.8716 | 2020-12-01 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building road from C-061. | 5 | C050-C069 | Antler Lake | 0 | 44172 |  | 37 | 44173 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting714820201201-7Excavator Thumb - 30 - 50 ton- After Jan 1010.5128.205 | Corbiere and Sons Contracting714820201201-7Excavator Thumb - 30 - 50 ton- After Jan 1010.5128.205Inv#082 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 128.205 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7148 | 20201201-7 | 53510502 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-12-01 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building road from C-061. | 5 | C050-C069 | Antler Lake | 0 | 44172 |  | 37 | 44173 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting714820201201-7Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting714820201201-7Light Truck - Pick up- After Jan 101243.75Inv#082 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7148 | 20201201-7 | 53510502 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-12-01 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building road from C-061. | 5 | C050-C069 | Antler Lake | 0 | 44172 |  | 37 | 44173 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting714820201201-7L.O.A.1210 | Corbiere and Sons Contracting714820201201-7L.O.A.1210Inv#082 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7148 | 20201201-7 | 53510502 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-12-01 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building road from C-061. | 5 | C050-C069 | Antler Lake | 0 | 44172 |  | 37 | 44173 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting714820201201-7Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting714820201201-7Operator - Principle - After Jan 1011.5862.5Inv#082 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7149 | 20201201-8 | 53510504 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 18 | Dynamic | 98.61 | 0 |  |  | 2366.64 | 307.6632 | 2674.3032 | 2020-12-01 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks for gravel haul, rock trucks hauling gravel to C-079, Rock truck hauling gravel to C-081, and C-110. Dozers spreading gravel at C-078 and C-109, labourers rolling out geo for gravel haul. | 5 | C076-C116 | Cook Lake | 0 | 44172 |  | 37 | 44173 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting714920201201-8Dozer D6 or equal- After Jan 10182366.64 | Corbiere and Sons Contracting714920201201-8Dozer D6 or equal- After Jan 10182366.64Inv#082 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 2366.64 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7149 | 20201201-8 | 53510504 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 103.84 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2020-12-01 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks for gravel haul, rock trucks hauling gravel to C-079, Rock truck hauling gravel to C-081, and C-110. Dozers spreading gravel at C-078 and C-109, labourers rolling out geo for gravel haul. | 5 | C076-C116 | Cook Lake | 0 | 44172 |  | 37 | 44173 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting714920201201-8Excavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting714920201201-8Excavator - 30 ton- After Jan 1091246.05Inv#082 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1246.05 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7149 | 20201201-8 | 53510504 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2020-12-01 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks for gravel haul, rock trucks hauling gravel to C-079, Rock truck hauling gravel to C-081, and C-110. Dozers spreading gravel at C-078 and C-109, labourers rolling out geo for gravel haul. | 5 | C076-C116 | Cook Lake | 0 | 44172 |  | 37 | 44173 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting714920201201-8Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting714920201201-8Excavator Thumb - 30 - 50 ton- After Jan 109109.89Inv#082 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 109.89 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7149 | 20201201-8 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-12-01 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks for gravel haul, rock trucks hauling gravel to C-079, Rock truck hauling gravel to C-081, and C-110. Dozers spreading gravel at C-078 and C-109, labourers rolling out geo for gravel haul. | 5 | C076-C116 | Cook Lake | 0 | 44172 |  | 37 | 44173 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting714920201201-8Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting714920201201-8Light Truck - Pick up- After Jan 102487.5Inv#082 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7149 | 20201201-8 | 53510504 | Access | 0 | Light Truck w/ Tandum Trailer- After Jan 10 | 337.5 | 1 | DAY | 253.13 | 0 |  |  | 337.5 | 43.875 | 381.375 | 2020-12-01 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks for gravel haul, rock trucks hauling gravel to C-079, Rock truck hauling gravel to C-081, and C-110. Dozers spreading gravel at C-078 and C-109, labourers rolling out geo for gravel haul. | 5 | C076-C116 | Cook Lake | 0 | 44172 |  | 37 | 44173 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting714920201201-8Light Truck w/ Tandum Trailer- After Jan 101337.5 | Corbiere and Sons Contracting714920201201-8Light Truck w/ Tandum Trailer- After Jan 101337.5Inv#082 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 337.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7149 | 20201201-8 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 27 | Dynamic | 103.54 | 0 |  |  | 3727.35 | 484.5555 | 4211.9055 | 2020-12-01 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks for gravel haul, rock trucks hauling gravel to C-079, Rock truck hauling gravel to C-081, and C-110. Dozers spreading gravel at C-078 and C-109, labourers rolling out geo for gravel haul. | 5 | C076-C116 | Cook Lake | 0 | 44172 |  | 37 | 44173 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting714920201201-8Rock Truck - 30 Ton- After Jan 10273727.35 | Corbiere and Sons Contracting714920201201-8Rock Truck - 30 Ton- After Jan 10273727.35Inv#082 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 3727.35 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7149 | 20201201-8 | 53510504 | Access | 0 | Foreman | 95 | 6 | HR |  |  | 95 | 0 | 570 | 74.1 | 644.1 | 2020-12-01 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks for gravel haul, rock trucks hauling gravel to C-079, Rock truck hauling gravel to C-081, and C-110. Dozers spreading gravel at C-078 and C-109, labourers rolling out geo for gravel haul. | 5 | C076-C116 | Cook Lake | 0 | 44172 |  | 37 | 44173 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting714920201201-8Foreman6570 | Corbiere and Sons Contracting714920201201-8Foreman6570Inv#082 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 570 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7149 | 20201201-8 | 53510504 | Access | 0 | L.O.A. | 210 | 9 | DAY |  |  |  | 0 | 1890 | 245.7 | 2135.7 | 2020-12-01 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks for gravel haul, rock trucks hauling gravel to C-079, Rock truck hauling gravel to C-081, and C-110. Dozers spreading gravel at C-078 and C-109, labourers rolling out geo for gravel haul. | 5 | C076-C116 | Cook Lake | 0 | 44172 |  | 37 | 44173 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting714920201201-8L.O.A.91890 | Corbiere and Sons Contracting714920201201-8L.O.A.91890Inv#082 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1890 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7149 | 20201201-8 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 30 | HR |  |  | 75 | 0 | 2250 | 292.5 | 2542.5 | 2020-12-01 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks for gravel haul, rock trucks hauling gravel to C-079, Rock truck hauling gravel to C-081, and C-110. Dozers spreading gravel at C-078 and C-109, labourers rolling out geo for gravel haul. | 5 | C076-C116 | Cook Lake | 0 | 44172 |  | 37 | 44173 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting714920201201-8Operator - Principle - After Jan 10302250 | Corbiere and Sons Contracting714920201201-8Operator - Principle - After Jan 10302250Inv#082 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 2250 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7149 | 20201201-8 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 30 | HR |  |  | 70 | 0 | 2100 | 273 | 2373 | 2020-12-01 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks for gravel haul, rock trucks hauling gravel to C-079, Rock truck hauling gravel to C-081, and C-110. Dozers spreading gravel at C-078 and C-109, labourers rolling out geo for gravel haul. | 5 | C076-C116 | Cook Lake | 0 | 44172 |  | 37 | 44173 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting714920201201-8Driver - AZ - After Jan 10302100 | Corbiere and Sons Contracting714920201201-8Driver - AZ - After Jan 10302100Inv#082 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 2100 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7149 | 20201201-8 | 53510504 | Access | 0 | Labourer - General - After Jan 10 | 60 | 8 | HR |  |  | 60 | 0 | 480 | 62.4 | 542.4 | 2020-12-01 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks for gravel haul, rock trucks hauling gravel to C-079, Rock truck hauling gravel to C-081, and C-110. Dozers spreading gravel at C-078 and C-109, labourers rolling out geo for gravel haul. | 5 | C076-C116 | Cook Lake | 0 | 44172 |  | 37 | 44173 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting714920201201-8Labourer - General - After Jan 108480 | Corbiere and Sons Contracting714920201201-8Labourer - General - After Jan 108480Inv#082 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 480 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7231 | 20201202-15 | 53510502 | Access | 0 | Skidder | 171 | 10.5 | HR | 128.25 | 0 |  |  | 1795.5 | 233.415 | 2028.915 | 2020-12-02 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building AN road to the showfly at C-075 - T&M | 5 | C070-C075 | White Sand | 0 | 44175 |  | 37 | 44175 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting723120201202-15Skidder 10.51795.5 | Corbiere and Sons Contracting723120201202-15Skidder 10.51795.5Inv#082 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 1795.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7231 | 20201202-15 | 53510502 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10.5 | Dynamic | 103.84 | 0 |  |  | 1453.725 | 188.9843 | 1642.7093 | 2020-12-02 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building AN road to the showfly at C-075 - T&M | 5 | C070-C075 | White Sand | 0 | 44175 |  | 37 | 44175 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting723120201202-15Excavator - 30 ton- After Jan 1010.51453.725 | Corbiere and Sons Contracting723120201202-15Excavator - 30 ton- After Jan 1010.51453.725Inv#082 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 1453.725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7231 | 20201202-15 | 53510502 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-12-02 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building AN road to the showfly at C-075 - T&M | 5 | C070-C075 | White Sand | 0 | 44175 |  | 37 | 44175 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting723120201202-15Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting723120201202-15Light Truck - Pick up- After Jan 101243.75Inv#082 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7231 | 20201202-15 | 53510502 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-12-02 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building AN road to the showfly at C-075 - T&M | 5 | C070-C075 | White Sand | 0 | 44175 |  | 37 | 44175 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting723120201202-15L.O.A.2420 | Corbiere and Sons Contracting723120201202-15L.O.A.2420Inv#082 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7231 | 20201202-15 | 53510502 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 23 | HR |  |  | 75 | 0 | 1725 | 224.25 | 1949.25 | 2020-12-02 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Building AN road to the showfly at C-075 - T&M | 5 | C070-C075 | White Sand | 0 | 44175 |  | 37 | 44175 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting723120201202-15Operator - Principle - After Jan 10231725 | Corbiere and Sons Contracting723120201202-15Operator - Principle - After Jan 10231725Inv#082 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 1725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7232 | 20201202-16 | 53510512 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10.5 | Dynamic | 103.84 | 0 |  |  | 1453.725 | 188.9843 | 1642.7093 | 2020-12-02 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance from C-093 | 5 | C093-C116 | Cavers | 0 | 44175 |  | 37 | 44175 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting723220201202-16Excavator - 30 ton- After Jan 1010.51453.725 | Corbiere and Sons Contracting723220201202-16Excavator - 30 ton- After Jan 1010.51453.725Inv#082 | [5 empty] | 1 | 1453.725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7232 | 20201202-16 | 53510512 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10.5 | HR | 9.16 | 0 |  |  | 128.205 | 16.6667 | 144.8716 | 2020-12-02 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance from C-093 | 5 | C093-C116 | Cavers | 0 | 44175 |  | 37 | 44175 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting723220201202-16Excavator Thumb - 30 - 50 ton- After Jan 1010.5128.205 | Corbiere and Sons Contracting723220201202-16Excavator Thumb - 30 - 50 ton- After Jan 1010.5128.205Inv#082 | [5 empty] | 1 | 128.205 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7232 | 20201202-16 | 53510512 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-12-02 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance from C-093 | 5 | C093-C116 | Cavers | 0 | 44175 |  | 37 | 44175 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting723220201202-16Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting723220201202-16Light Truck - Pick up- After Jan 101243.75Inv#082 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7232 | 20201202-16 | 53510512 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-12-02 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance from C-093 | 5 | C093-C116 | Cavers | 0 | 44175 |  | 37 | 44175 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting723220201202-16L.O.A.1210 | Corbiere and Sons Contracting723220201202-16L.O.A.1210Inv#082 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7232 | 20201202-16 | 53510512 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-12-02 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance from C-093 | 5 | C093-C116 | Cavers | 0 | 44175 |  | 37 | 44175 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting723220201202-16Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting723220201202-16Operator - Principle - After Jan 1011.5862.5Inv#082 | [5 empty] | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7233 | 20201202-17 | 53510504 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10.5 | Dynamic | 98.61 | 0 |  |  | 1380.54 | 179.4702 | 1560.0102 | 2020-12-02 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator lading rock truck for haul to C-111, dozer spreading gravel from C-111. | 5 | C093-C116 | Cook Lake | 0 | 44175 |  | 37 | 44175 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting723320201202-17Dozer D6 or equal- After Jan 1010.51380.54 | Corbiere and Sons Contracting723320201202-17Dozer D6 or equal- After Jan 1010.51380.54Inv#082 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1380.54 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7233 | 20201202-17 | 53510504 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10.5 | Dynamic | 103.84 | 0 |  |  | 1453.725 | 188.9843 | 1642.7093 | 2020-12-02 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator lading rock truck for haul to C-111, dozer spreading gravel from C-111. | 5 | C093-C116 | Cook Lake | 0 | 44175 |  | 37 | 44175 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting723320201202-17Excavator - 30 ton- After Jan 1010.51453.725 | Corbiere and Sons Contracting723320201202-17Excavator - 30 ton- After Jan 1010.51453.725Inv#082 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1453.725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7233 | 20201202-17 | 53510504 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10.5 | HR | 9.16 | 0 |  |  | 128.205 | 16.6667 | 144.8716 | 2020-12-02 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator lading rock truck for haul to C-111, dozer spreading gravel from C-111. | 5 | C093-C116 | Cook Lake | 0 | 44175 |  | 37 | 44175 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting723320201202-17Excavator Thumb - 30 - 50 ton- After Jan 1010.5128.205 | Corbiere and Sons Contracting723320201202-17Excavator Thumb - 30 - 50 ton- After Jan 1010.5128.205Inv#082 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 128.205 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7233 | 20201202-17 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-12-02 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator lading rock truck for haul to C-111, dozer spreading gravel from C-111. | 5 | C093-C116 | Cook Lake | 0 | 44175 |  | 37 | 44175 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting723320201202-17Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting723320201202-17Light Truck - Pick up- After Jan 101243.75Inv#082 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7233 | 20201202-17 | 53510504 | Access | 0 | Light Truck w/ Tandum Trailer- After Jan 10 | 337.5 | 1 | DAY | 253.13 | 0 |  |  | 337.5 | 43.875 | 381.375 | 2020-12-02 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator lading rock truck for haul to C-111, dozer spreading gravel from C-111. | 5 | C093-C116 | Cook Lake | 0 | 44175 |  | 37 | 44175 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting723320201202-17Light Truck w/ Tandum Trailer- After Jan 101337.5 | Corbiere and Sons Contracting723320201202-17Light Truck w/ Tandum Trailer- After Jan 101337.5Inv#082 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 337.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7233 | 20201202-17 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 10.5 | Dynamic | 103.54 | 0 |  |  | 1449.525 | 188.4383 | 1637.9633 | 2020-12-02 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator lading rock truck for haul to C-111, dozer spreading gravel from C-111. | 5 | C093-C116 | Cook Lake | 0 | 44175 |  | 37 | 44175 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting723320201202-17Rock Truck - 30 Ton- After Jan 1010.51449.525 | Corbiere and Sons Contracting723320201202-17Rock Truck - 30 Ton- After Jan 1010.51449.525Inv#082 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1449.525 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7233 | 20201202-17 | 53510504 | Access | 0 | Foreman | 95 | 4 | HR |  |  | 95 | 0 | 380 | 49.4 | 429.4 | 2020-12-02 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator lading rock truck for haul to C-111, dozer spreading gravel from C-111. | 5 | C093-C116 | Cook Lake | 0 | 44175 |  | 37 | 44175 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting723320201202-17Foreman4380 | Corbiere and Sons Contracting723320201202-17Foreman4380Inv#082 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7233 | 20201202-17 | 53510504 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2020-12-02 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator lading rock truck for haul to C-111, dozer spreading gravel from C-111. | 5 | C093-C116 | Cook Lake | 0 | 44175 |  | 37 | 44175 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting723320201202-17L.O.A.3630 | Corbiere and Sons Contracting723320201202-17L.O.A.3630Inv#082 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7233 | 20201202-17 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 23 | HR |  |  | 75 | 0 | 1725 | 224.25 | 1949.25 | 2020-12-02 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator lading rock truck for haul to C-111, dozer spreading gravel from C-111. | 5 | C093-C116 | Cook Lake | 0 | 44175 |  | 37 | 44175 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting723320201202-17Operator - Principle - After Jan 10231725 | Corbiere and Sons Contracting723320201202-17Operator - Principle - After Jan 10231725Inv#082 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7233 | 20201202-17 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 11.5 | HR |  |  | 70 | 0 | 805 | 104.65 | 909.65 | 2020-12-02 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator lading rock truck for haul to C-111, dozer spreading gravel from C-111. | 5 | C093-C116 | Cook Lake | 0 | 44175 |  | 37 | 44175 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting723320201202-17Driver - AZ - After Jan 1011.5805 | Corbiere and Sons Contracting723320201202-17Driver - AZ - After Jan 1011.5805Inv#082 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 805 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7234 | 20201202-18 | 53510511 | Access | 0 | Skidder | 171 | 4 | HR | 128.25 | 0 |  |  | 684 | 88.92 | 772.92 | 2020-12-02 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Cole on skidder removing snow, Gary on grader doing road maintenance. | 5 | C076-C092 | Cavers | 0 | 44175 |  | 37 | 44175 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting723420201202-18Skidder 4684 | Corbiere and Sons Contracting723420201202-18Skidder 4684Inv#082 | [5 empty] | 1 | 684 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7234 | 20201202-18 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10.5 | Dynamic | 95.24 | 0 |  |  | 1333.29 | 173.3277 | 1506.6177 | 2020-12-02 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Cole on skidder removing snow, Gary on grader doing road maintenance. | 5 | C076-C092 | Cavers | 0 | 44175 |  | 37 | 44175 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting723420201202-18Grader - Cat 12 to 14 or equal- After Jan 1010.51333.29 | Corbiere and Sons Contracting723420201202-18Grader - Cat 12 to 14 or equal- After Jan 1010.51333.29Inv#082 | [5 empty] | 1 | 1333.29 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7234 | 20201202-18 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-12-02 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Cole on skidder removing snow, Gary on grader doing road maintenance. | 5 | C076-C092 | Cavers | 0 | 44175 |  | 37 | 44175 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting723420201202-18Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting723420201202-18Light Truck - Pick up- After Jan 101243.75Inv#082 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7234 | 20201202-18 | 53510511 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-12-02 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Cole on skidder removing snow, Gary on grader doing road maintenance. | 5 | C076-C092 | Cavers | 0 | 44175 |  | 37 | 44175 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting723420201202-18L.O.A.2420 | Corbiere and Sons Contracting723420201202-18L.O.A.2420Inv#082 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7234 | 20201202-18 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 15.5 | HR |  |  | 75 | 0 | 1162.5 | 151.125 | 1313.625 | 2020-12-02 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Cole on skidder removing snow, Gary on grader doing road maintenance. | 5 | C076-C092 | Cavers | 0 | 44175 |  | 37 | 44175 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting723420201202-18Operator - Principle - After Jan 1015.51162.5 | Corbiere and Sons Contracting723420201202-18Operator - Principle - After Jan 1015.51162.5Inv#082 | [5 empty] | 1 | 1162.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7195 | 20201202-6 | 53510212 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 6 | Dynamic | 98.61 | 0 |  |  | 788.88 | 102.5544 | 891.4344 | 2020-12-02 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved dozer from Landfill to LoftyDozer cleared hill at B-063 and helped crane up the hill, walked out and demobed to North Shore yard. | 2 | B054 - B064 | Lofty Davies | 0 | 44173 |  | 37 | 44174 | [5 empty] | Harold Furlong | 02 | Corbiere and Sons Contracting719520201202-6Dozer D6 or equal- After Jan 106788.88 | Corbiere and Sons Contracting719520201202-6Dozer D6 or equal- After Jan 106788.88Inv#082 | [5 empty] | 1 | 788.88 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7195 | 20201202-6 | 53510212 | Access | 0 | Tractor Trailer - 50 Ton- After Jan 10 | 111.75 | 3 | Dynamic | 83.81 | 0 |  |  | 335.25 | 43.5825 | 378.8325 | 2020-12-02 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved dozer from Landfill to LoftyDozer cleared hill at B-063 and helped crane up the hill, walked out and demobed to North Shore yard. | 2 | B054 - B064 | Lofty Davies | 0 | 44173 |  | 37 | 44174 | [5 empty] | Harold Furlong | 02 | Corbiere and Sons Contracting719520201202-6Tractor Trailer - 50 Ton- After Jan 103335.25 | Corbiere and Sons Contracting719520201202-6Tractor Trailer - 50 Ton- After Jan 103335.25Inv#082 | [5 empty] | 1 | 335.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7195 | 20201202-6 | 53510212 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 75 | 0 | 450 | 58.5 | 508.5 | 2020-12-02 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved dozer from Landfill to LoftyDozer cleared hill at B-063 and helped crane up the hill, walked out and demobed to North Shore yard. | 2 | B054 - B064 | Lofty Davies | 0 | 44173 |  | 37 | 44174 | [5 empty] | Harold Furlong | 02 | Corbiere and Sons Contracting719520201202-6Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting719520201202-6Operator - Principle - After Jan 106450Inv#082 | [5 empty] | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7195 | 20201202-6 | 53510212 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 3 | HR |  |  | 70 | 0 | 210 | 27.3 | 237.3 | 2020-12-02 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved dozer from Landfill to LoftyDozer cleared hill at B-063 and helped crane up the hill, walked out and demobed to North Shore yard. | 2 | B054 - B064 | Lofty Davies | 0 | 44173 |  | 37 | 44174 | [5 empty] | Harold Furlong | 02 | Corbiere and Sons Contracting719520201202-6Driver - AZ - After Jan 103210 | Corbiere and Sons Contracting719520201202-6Driver - AZ - After Jan 103210Inv#082 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7197 | 20201202-8 | 53510312 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 2 | Dynamic | 98.61 | 0 |  |  | 262.96 | 34.1848 | 297.1448 | 2020-12-02 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | DZ-04 cleared snow in towards Gurney. | 3 | B187-B193 | Gurney Lake Road | 0 | 44173 |  | 37 | 44174 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting719720201202-8Dozer D6 or equal- After Jan 102262.96 | Corbiere and Sons Contracting719720201202-8Dozer D6 or equal- After Jan 102262.96Inv#082 | [5 empty] | 1 | 262.96 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7197 | 20201202-8 | 53510312 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 2 | HR |  |  | 75 | 0 | 150 | 19.5 | 169.5 | 2020-12-02 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | DZ-04 cleared snow in towards Gurney. | 3 | B187-B193 | Gurney Lake Road | 0 | 44173 |  | 37 | 44174 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting719720201202-8Operator - Principle - After Jan 102150 | Corbiere and Sons Contracting719720201202-8Operator - Principle - After Jan 102150Inv#082 | [5 empty] | 1 | 150 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7210 | 20201203-10 | 53510412 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 5 | Dynamic | 110.22 | 0 |  |  | 734.8 | 95.524 | 830.324 | 2020-12-03 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-05 fixed punch outs causes by rock trucks gravel haul. | 4 | B194-B203 | Little Gravel River Rd | 0 | 44173 |  | 37 | 44174 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting721020201203-10Excavator - 36 ton- After Jan 105734.8 | Corbiere and Sons Contracting721020201203-10Excavator - 36 ton- After Jan 105734.8Inv#082 | [5 empty] | 1 | 734.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7210 | 20201203-10 | 53510412 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 5 | HR | 9.16 | 0 |  |  | 61.05 | 7.9365 | 68.9865 | 2020-12-03 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-05 fixed punch outs causes by rock trucks gravel haul. | 4 | B194-B203 | Little Gravel River Rd | 0 | 44173 |  | 37 | 44174 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting721020201203-10Excavator Thumb - 30 - 50 ton- After Jan 10561.05 | Corbiere and Sons Contracting721020201203-10Excavator Thumb - 30 - 50 ton- After Jan 10561.05Inv#082 | [5 empty] | 1 | 61.05 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7210 | 20201203-10 | 53510412 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5 | HR |  |  | 75 | 0 | 375 | 48.75 | 423.75 | 2020-12-03 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-05 fixed punch outs causes by rock trucks gravel haul. | 4 | B194-B203 | Little Gravel River Rd | 0 | 44173 |  | 37 | 44174 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting721020201203-10Operator - Principle - After Jan 105375 | Corbiere and Sons Contracting721020201203-10Operator - Principle - After Jan 105375Inv#082 | [5 empty] | 1 | 375 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7240 | 20201203-18 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10.5 | Dynamic | 95.24 | 0 |  |  | 1333.29 | 173.3277 | 1506.6177 | 2020-12-03 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across access roads. | 5 | C050-C069 | Antler Lake | 0 | 44175 |  | 37 | 44175 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting724020201203-18Grader - Cat 12 to 14 or equal- After Jan 1010.51333.29 | Corbiere and Sons Contracting724020201203-18Grader - Cat 12 to 14 or equal- After Jan 1010.51333.29Inv#082 | [5 empty] | 1 | 1333.29 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7240 | 20201203-18 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-12-03 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across access roads. | 5 | C050-C069 | Antler Lake | 0 | 44175 |  | 37 | 44175 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting724020201203-18Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting724020201203-18Light Truck - Pick up- After Jan 101243.75Inv#082 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7240 | 20201203-18 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-12-03 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across access roads. | 5 | C050-C069 | Antler Lake | 0 | 44175 |  | 37 | 44175 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting724020201203-18L.O.A.1210 | Corbiere and Sons Contracting724020201203-18L.O.A.1210Inv#082 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7240 | 20201203-18 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-12-03 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across access roads. | 5 | C050-C069 | Antler Lake | 0 | 44175 |  | 37 | 44175 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting724020201203-18Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting724020201203-18Operator - Principle - After Jan 1011.5862.5Inv#082 | [5 empty] | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7241 | 20201203-19 | 53510511 | Access | 0 | Skidder | 171 | 5 | HR | 128.25 | 0 |  |  | 855 | 111.15 | 966.15 | 2020-12-03 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Skidder doing winter road miantenance, grader working across access roads. | 5 | C076-C116 | Cook Lake | 0 | 44175 |  | 37 | 44175 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting724120201203-19Skidder 5855 | Corbiere and Sons Contracting724120201203-19Skidder 5855Inv#082 | [5 empty] | 1 | 855 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7241 | 20201203-19 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10.5 | Dynamic | 95.24 | 0 |  |  | 1333.29 | 173.3277 | 1506.6177 | 2020-12-03 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Skidder doing winter road miantenance, grader working across access roads. | 5 | C076-C116 | Cook Lake | 0 | 44175 |  | 37 | 44175 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting724120201203-19Grader - Cat 12 to 14 or equal- After Jan 1010.51333.29 | Corbiere and Sons Contracting724120201203-19Grader - Cat 12 to 14 or equal- After Jan 1010.51333.29Inv#082 | [5 empty] | 1 | 1333.29 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7241 | 20201203-19 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-12-03 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Skidder doing winter road miantenance, grader working across access roads. | 5 | C076-C116 | Cook Lake | 0 | 44175 |  | 37 | 44175 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting724120201203-19Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting724120201203-19Light Truck - Pick up- After Jan 101243.75Inv#082 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7241 | 20201203-19 | 53510511 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-12-03 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Skidder doing winter road miantenance, grader working across access roads. | 5 | C076-C116 | Cook Lake | 0 | 44175 |  | 37 | 44175 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting724120201203-19L.O.A.2420 | Corbiere and Sons Contracting724120201203-19L.O.A.2420Inv#082 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7241 | 20201203-19 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 16.5 | HR |  |  | 75 | 0 | 1237.5 | 160.875 | 1398.375 | 2020-12-03 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Skidder doing winter road miantenance, grader working across access roads. | 5 | C076-C116 | Cook Lake | 0 | 44175 |  | 37 | 44175 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting724120201203-19Operator - Principle - After Jan 1016.51237.5 | Corbiere and Sons Contracting724120201203-19Operator - Principle - After Jan 1016.51237.5Inv#082 | [5 empty] | 1 | 1237.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7206 | 20201203-6 | 53510112 | Access | 0 | Sander Truck - Hwy- After Jan 10 | 55 | 10 | Dynamic | 41.25 | 0 |  |  | 550 | 71.5 | 621.5 | 2020-12-03 | 1 | Inv#082 | 44181 | 130 | 0 | 1 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 15 | Approved | ROW INTERNAL - Sand for Road Maintenance - 3rd Party | 9015 | Sander worked from Mrakic Pit to A002 | 1 | Highway 17 to A-017 | MacGregor | 0 | 44173 |  | 37 | 44174 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting720620201203-6Sander Truck - Hwy- After Jan 1010550 | Corbiere and Sons Contracting720620201203-6Sander Truck - Hwy- After Jan 1010550Inv#082 | [5 empty] | 1 | 550 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7206 | 20201203-6 | 53510112 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 10 | HR |  |  | 70 | 0 | 700 | 91 | 791 | 2020-12-03 | 1 | Inv#082 | 44181 | 130 | 0 | 1 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 15 | Approved | ROW INTERNAL - Sand for Road Maintenance - 3rd Party | 9015 | Sander worked from Mrakic Pit to A002 | 1 | Highway 17 to A-017 | MacGregor | 0 | 44173 |  | 37 | 44174 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting720620201203-6Driver - AZ - After Jan 1010700 | Corbiere and Sons Contracting720620201203-6Driver - AZ - After Jan 1010700Inv#082 | [5 empty] | 1 | 700 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7208 | 20201203-8 | 53510312 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 7 | Dynamic | 98.61 | 0 |  |  | 920.36 | 119.6468 | 1040.0068 | 2020-12-03 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer cleared Gurney Lake Rd of snow and drug bridge in. | 3 | B187-B193 | Gurney Lake Road | 0 | 44173 |  | 37 | 44174 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting720820201203-8Dozer D6 or equal- After Jan 107920.36 | Corbiere and Sons Contracting720820201203-8Dozer D6 or equal- After Jan 107920.36Inv#082 | [5 empty] | 1 | 920.36 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7208 | 20201203-8 | 53510312 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-12-03 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer cleared Gurney Lake Rd of snow and drug bridge in. | 3 | B187-B193 | Gurney Lake Road | 0 | 44173 |  | 37 | 44174 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting720820201203-8Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting720820201203-8Light Truck - Pick up- After Jan 101243.75Inv#082 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7208 | 20201203-8 | 53510312 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 8 | HR |  |  | 75 | 0 | 600 | 78 | 678 | 2020-12-03 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer cleared Gurney Lake Rd of snow and drug bridge in. | 3 | B187-B193 | Gurney Lake Road | 0 | 44173 |  | 37 | 44174 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting720820201203-8Operator - Principle - After Jan 108600 | Corbiere and Sons Contracting720820201203-8Operator - Principle - After Jan 108600Inv#082 | [5 empty] | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7223 | 20201204-10 | 53510412 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 8 | Dynamic | 110.22 | 0 |  |  | 1175.68 | 152.8384 | 1328.5184 | 2020-12-04 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-09 fixed up broken corduroy and holes in the road with help from Chris. | 4 | B194-B203 | Little Gravel River Rd | 0 | 44173 |  | 37 | 44175 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting722320201204-10Excavator - 36 ton- After Jan 1081175.68 | Corbiere and Sons Contracting722320201204-10Excavator - 36 ton- After Jan 1081175.68Inv#082 | [5 empty] | 1 | 1175.68 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7223 | 20201204-10 | 53510412 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 8 | HR | 9.16 | 0 |  |  | 97.68 | 12.6984 | 110.3784 | 2020-12-04 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-09 fixed up broken corduroy and holes in the road with help from Chris. | 4 | B194-B203 | Little Gravel River Rd | 0 | 44173 |  | 37 | 44175 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting722320201204-10Excavator Thumb - 30 - 50 ton- After Jan 10897.68 | Corbiere and Sons Contracting722320201204-10Excavator Thumb - 30 - 50 ton- After Jan 10897.68Inv#082 | [5 empty] | 1 | 97.68 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7223 | 20201204-10 | 53510412 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-12-04 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-09 fixed up broken corduroy and holes in the road with help from Chris. | 4 | B194-B203 | Little Gravel River Rd | 0 | 44173 |  | 37 | 44175 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting722320201204-10Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting722320201204-10Light Truck - Pick up- After Jan 101243.75Inv#082 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7223 | 20201204-10 | 53510412 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2020-12-04 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-09 fixed up broken corduroy and holes in the road with help from Chris. | 4 | B194-B203 | Little Gravel River Rd | 0 | 44173 |  | 37 | 44175 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting722320201204-10Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting722320201204-10Operator - Principle - After Jan 1011825Inv#082 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7243 | 20201204-13 | 53510504 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 45.5 | Dynamic | 41.4 | 0 |  |  | 2511.6 | 326.508 | 2838.108 | 2020-12-04 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hauling gravel from Antler Lake stockpile over to White Sands | 5 | C070-C075 | White Sand | 0 | 44175 |  | 37 | 44175 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting724320201204-13Dump - Triaxle- After Jan 1045.52511.6 | Corbiere and Sons Contracting724320201204-13Dump - Triaxle- After Jan 1045.52511.6Inv#082 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 2511.6 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7243 | 20201204-13 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 45.5 | HR |  |  | 70 | 0 | 3185 | 414.05 | 3599.05 | 2020-12-04 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Hauling gravel from Antler Lake stockpile over to White Sands | 5 | C070-C075 | White Sand | 0 | 44175 |  | 37 | 44175 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting724320201204-13Driver - AZ - After Jan 1045.53185 | Corbiere and Sons Contracting724320201204-13Driver - AZ - After Jan 1045.53185Inv#082 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 3185 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7247 | 20201204-17 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10.5 | Dynamic | 95.24 | 0 |  |  | 1333.29 | 173.3277 | 1506.6177 | 2020-12-04 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader doing winter access maintenance | 5 | C031-C049 | Pays Plat River | 0 | 44175 |  | 37 | 44175 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting724720201204-17Grader - Cat 12 to 14 or equal- After Jan 1010.51333.29 | Corbiere and Sons Contracting724720201204-17Grader - Cat 12 to 14 or equal- After Jan 1010.51333.29Inv#082 | [5 empty] | 1 | 1333.29 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7247 | 20201204-17 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-12-04 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader doing winter access maintenance | 5 | C031-C049 | Pays Plat River | 0 | 44175 |  | 37 | 44175 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting724720201204-17Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting724720201204-17Light Truck - Pick up- After Jan 101243.75Inv#082 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7247 | 20201204-17 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-12-04 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader doing winter access maintenance | 5 | C031-C049 | Pays Plat River | 0 | 44175 |  | 37 | 44175 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting724720201204-17L.O.A.1210 | Corbiere and Sons Contracting724720201204-17L.O.A.1210Inv#082 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7247 | 20201204-17 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-12-04 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader doing winter access maintenance | 5 | C031-C049 | Pays Plat River | 0 | 44175 |  | 37 | 44175 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting724720201204-17Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting724720201204-17Operator - Principle - After Jan 1011.5862.5Inv#082 | [5 empty] | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7248 | 20201204-18 | 53510504 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10.5 | Dynamic | 103.84 | 0 |  |  | 1453.725 | 188.9843 | 1642.7093 | 2020-12-04 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Loading trucks from stockpile. | 5 | C050-C069 | Antler Lake | 0 | 44175 |  | 37 | 44175 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting724820201204-18Excavator - 30 ton- After Jan 1010.51453.725 | Corbiere and Sons Contracting724820201204-18Excavator - 30 ton- After Jan 1010.51453.725Inv#082 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1453.725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7248 | 20201204-18 | 53510504 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10.5 | HR | 9.16 | 0 |  |  | 128.205 | 16.6667 | 144.8716 | 2020-12-04 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Loading trucks from stockpile. | 5 | C050-C069 | Antler Lake | 0 | 44175 |  | 37 | 44175 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting724820201204-18Excavator Thumb - 30 - 50 ton- After Jan 1010.5128.205 | Corbiere and Sons Contracting724820201204-18Excavator Thumb - 30 - 50 ton- After Jan 1010.5128.205Inv#082 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 128.205 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7248 | 20201204-18 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-12-04 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Loading trucks from stockpile. | 5 | C050-C069 | Antler Lake | 0 | 44175 |  | 37 | 44175 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting724820201204-18Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting724820201204-18Light Truck - Pick up- After Jan 101243.75Inv#082 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7248 | 20201204-18 | 53510504 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-12-04 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Loading trucks from stockpile. | 5 | C050-C069 | Antler Lake | 0 | 44175 |  | 37 | 44175 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting724820201204-18L.O.A.1210 | Corbiere and Sons Contracting724820201204-18L.O.A.1210Inv#082 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7248 | 20201204-18 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-12-04 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Loading trucks from stockpile. | 5 | C050-C069 | Antler Lake | 0 | 44175 |  | 37 | 44175 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting724820201204-18Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting724820201204-18Operator - Principle - After Jan 1011.5862.5Inv#082 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7249 | 20201204-19 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10.5 | Dynamic | 95.24 | 0 |  |  | 1333.29 | 173.3277 | 1506.6177 | 2020-12-04 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader doing winter access maintenance. | 5 | C050-C069 | Antler Lake | 0 | 44175 |  | 37 | 44175 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting724920201204-19Grader - Cat 12 to 14 or equal- After Jan 1010.51333.29 | Corbiere and Sons Contracting724920201204-19Grader - Cat 12 to 14 or equal- After Jan 1010.51333.29Inv#082 | [5 empty] | 1 | 1333.29 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7249 | 20201204-19 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-12-04 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader doing winter access maintenance. | 5 | C050-C069 | Antler Lake | 0 | 44175 |  | 37 | 44175 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting724920201204-19L.O.A.1210 | Corbiere and Sons Contracting724920201204-19L.O.A.1210Inv#082 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7249 | 20201204-19 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-12-04 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader doing winter access maintenance. | 5 | C050-C069 | Antler Lake | 0 | 44175 |  | 37 | 44175 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting724920201204-19Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting724920201204-19Operator - Principle - After Jan 1011.5862.5Inv#082 | [5 empty] | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7250 | 20201204-20 | 53510504 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10.5 | Dynamic | 98.61 | 0 |  |  | 1380.54 | 179.4702 | 1560.0102 | 2020-12-04 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks from main entrance, rock trucks hauling, dozer spreading from C-075. Jon coordinating, labourer picked up, delivered and rolled out geo. | 5 | C070-C075 | White Sand | 0 | 44175 |  | 37 | 44175 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting725020201204-20Dozer D6 or equal- After Jan 1010.51380.54 | Corbiere and Sons Contracting725020201204-20Dozer D6 or equal- After Jan 1010.51380.54Inv#082 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1380.54 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7250 | 20201204-20 | 53510504 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10.5 | Dynamic | 103.84 | 0 |  |  | 1453.725 | 188.9843 | 1642.7093 | 2020-12-04 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks from main entrance, rock trucks hauling, dozer spreading from C-075. Jon coordinating, labourer picked up, delivered and rolled out geo. | 5 | C070-C075 | White Sand | 0 | 44175 |  | 37 | 44175 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting725020201204-20Excavator - 30 ton- After Jan 1010.51453.725 | Corbiere and Sons Contracting725020201204-20Excavator - 30 ton- After Jan 1010.51453.725Inv#082 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1453.725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7250 | 20201204-20 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 4 | DAY | 182.81 | 0 |  |  | 975 | 126.75 | 1101.75 | 2020-12-04 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks from main entrance, rock trucks hauling, dozer spreading from C-075. Jon coordinating, labourer picked up, delivered and rolled out geo. | 5 | C070-C075 | White Sand | 0 | 44175 |  | 37 | 44175 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting725020201204-20Light Truck - Pick up- After Jan 104975 | Corbiere and Sons Contracting725020201204-20Light Truck - Pick up- After Jan 104975Inv#082 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 975 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7250 | 20201204-20 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 21 | Dynamic | 103.54 | 0 |  |  | 2899.05 | 376.8765 | 3275.9265 | 2020-12-04 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks from main entrance, rock trucks hauling, dozer spreading from C-075. Jon coordinating, labourer picked up, delivered and rolled out geo. | 5 | C070-C075 | White Sand | 0 | 44175 |  | 37 | 44175 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting725020201204-20Rock Truck - 30 Ton- After Jan 10212899.05 | Corbiere and Sons Contracting725020201204-20Rock Truck - 30 Ton- After Jan 10212899.05Inv#082 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 2899.05 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7250 | 20201204-20 | 53510504 | Access | 0 | Foreman | 95 | 6 | HR |  |  | 95 | 0 | 570 | 74.1 | 644.1 | 2020-12-04 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks from main entrance, rock trucks hauling, dozer spreading from C-075. Jon coordinating, labourer picked up, delivered and rolled out geo. | 5 | C070-C075 | White Sand | 0 | 44175 |  | 37 | 44175 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting725020201204-20Foreman6570 | Corbiere and Sons Contracting725020201204-20Foreman6570Inv#082 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 570 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7250 | 20201204-20 | 53510504 | Access | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2020-12-04 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks from main entrance, rock trucks hauling, dozer spreading from C-075. Jon coordinating, labourer picked up, delivered and rolled out geo. | 5 | C070-C075 | White Sand | 0 | 44175 |  | 37 | 44175 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting725020201204-20L.O.A.61260 | Corbiere and Sons Contracting725020201204-20L.O.A.61260Inv#082 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7250 | 20201204-20 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 23 | HR |  |  | 75 | 0 | 1725 | 224.25 | 1949.25 | 2020-12-04 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks from main entrance, rock trucks hauling, dozer spreading from C-075. Jon coordinating, labourer picked up, delivered and rolled out geo. | 5 | C070-C075 | White Sand | 0 | 44175 |  | 37 | 44175 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting725020201204-20Operator - Principle - After Jan 10231725 | Corbiere and Sons Contracting725020201204-20Operator - Principle - After Jan 10231725Inv#082 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7250 | 20201204-20 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 23 | HR |  |  | 70 | 0 | 1610 | 209.3 | 1819.3 | 2020-12-04 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks from main entrance, rock trucks hauling, dozer spreading from C-075. Jon coordinating, labourer picked up, delivered and rolled out geo. | 5 | C070-C075 | White Sand | 0 | 44175 |  | 37 | 44175 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting725020201204-20Driver - AZ - After Jan 10231610 | Corbiere and Sons Contracting725020201204-20Driver - AZ - After Jan 10231610Inv#082 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1610 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7250 | 20201204-20 | 53510504 | Access | 0 | Labourer - General - After Jan 10 | 60 | 4 | HR |  |  | 60 | 0 | 240 | 31.2 | 271.2 | 2020-12-04 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks from main entrance, rock trucks hauling, dozer spreading from C-075. Jon coordinating, labourer picked up, delivered and rolled out geo. | 5 | C070-C075 | White Sand | 0 | 44175 |  | 37 | 44175 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting725020201204-20Labourer - General - After Jan 104240 | Corbiere and Sons Contracting725020201204-20Labourer - General - After Jan 104240Inv#082 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 240 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7264 | 20201205-10 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10.5 | Dynamic | 95.24 | 0 |  |  | 1333.29 | 173.3277 | 1506.6177 | 2020-12-05 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grading from highway uo to ROW and towards C-075. | 5 | C070-C075 | White Sand | 0 | 44176 |  | 37 | 44178 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting726420201205-10Grader - Cat 12 to 14 or equal- After Jan 1010.51333.29 | Corbiere and Sons Contracting726420201205-10Grader - Cat 12 to 14 or equal- After Jan 1010.51333.29Inv#082 | [5 empty] | 1 | 1333.29 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7264 | 20201205-10 | 53510511 | Access | 0 | Foreman | 95 | 2 | HR |  |  | 95 | 0 | 190 | 24.7 | 214.7 | 2020-12-05 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grading from highway uo to ROW and towards C-075. | 5 | C070-C075 | White Sand | 0 | 44176 |  | 37 | 44178 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting726420201205-10Foreman2190 | Corbiere and Sons Contracting726420201205-10Foreman2190Inv#082 | [5 empty] | 1 | 190 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7264 | 20201205-10 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-12-05 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grading from highway uo to ROW and towards C-075. | 5 | C070-C075 | White Sand | 0 | 44176 |  | 37 | 44178 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting726420201205-10L.O.A.1210 | Corbiere and Sons Contracting726420201205-10L.O.A.1210Inv#082 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7264 | 20201205-10 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-12-05 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grading from highway uo to ROW and towards C-075. | 5 | C070-C075 | White Sand | 0 | 44176 |  | 37 | 44178 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting726420201205-10Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting726420201205-10Operator - Principle - After Jan 1011.5862.5Inv#082 | [5 empty] | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7267 | 20201205-13 | 53510504 | Access | 0 | Dump - Triaxle- After Jan 10 | 55.2 | 54 | Dynamic | 41.4 | 0 |  |  | 2980.8 | 387.504 | 3368.304 | 2020-12-05 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel hauling from stock pile on Antler Lake Rd to White Sands Rd. | 5 | C070-C075 | White Sand | 0 | 44178 |  | 37 | 44181 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting726720201205-13Dump - Triaxle- After Jan 10542980.8 | Corbiere and Sons Contracting726720201205-13Dump - Triaxle- After Jan 10542980.8Inv#082 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 2980.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7267 | 20201205-13 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-12-05 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel hauling from stock pile on Antler Lake Rd to White Sands Rd. | 5 | C070-C075 | White Sand | 0 | 44178 |  | 37 | 44181 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting726720201205-13Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting726720201205-13Light Truck - Pick up- After Jan 101243.75Inv#082 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7267 | 20201205-13 | 53510504 | Access | 0 | Construction Coordinator | 80 | 6 | HR |  |  | 80 | 0 | 480 | 62.4 | 542.4 | 2020-12-05 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel hauling from stock pile on Antler Lake Rd to White Sands Rd. | 5 | C070-C075 | White Sand | 0 | 44178 |  | 37 | 44181 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting726720201205-13Construction Coordinator6480 | Corbiere and Sons Contracting726720201205-13Construction Coordinator6480Inv#082 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 480 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7267 | 20201205-13 | 53510504 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-12-05 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel hauling from stock pile on Antler Lake Rd to White Sands Rd. | 5 | C070-C075 | White Sand | 0 | 44178 |  | 37 | 44181 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting726720201205-13L.O.A.1210 | Corbiere and Sons Contracting726720201205-13L.O.A.1210Inv#082 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7267 | 20201205-13 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 54 | HR |  |  | 70 | 0 | 3780 | 491.4 | 4271.4 | 2020-12-05 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel hauling from stock pile on Antler Lake Rd to White Sands Rd. | 5 | C070-C075 | White Sand | 0 | 44178 |  | 37 | 44181 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting726720201205-13Driver - AZ - After Jan 10543780 | Corbiere and Sons Contracting726720201205-13Driver - AZ - After Jan 10543780Inv#082 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 3780 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7269 | 20201205-15 | 53510412 | Access | 0 | Sander Truck - Hwy- After Jan 10 | 55 | 9 | Dynamic | 41.25 | 0 |  |  | 495 | 64.35 | 559.35 | 2020-12-05 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Sander worked on Gurney Lake Rd towards B-193 for the gravel haul | 4 | B194-B203 | Little Gravel River Road | 0 | 44178 |  | 37 | 44181 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting726920201205-15Sander Truck - Hwy- After Jan 109495 | Corbiere and Sons Contracting726920201205-15Sander Truck - Hwy- After Jan 109495Inv#082 | [5 empty] | 1 | 495 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7269 | 20201205-15 | 53510412 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 9 | HR |  |  | 70 | 0 | 630 | 81.9 | 711.9 | 2020-12-05 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Sander worked on Gurney Lake Rd towards B-193 for the gravel haul | 4 | B194-B203 | Little Gravel River Road | 0 | 44178 |  | 37 | 44181 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting726920201205-15Driver - AZ - After Jan 109630 | Corbiere and Sons Contracting726920201205-15Driver - AZ - After Jan 109630Inv#082 | [5 empty] | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7260 | 20201205-6 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 8.5 | Dynamic | 95.24 | 0 |  |  | 1079.33 | 140.3129 | 1219.6429 | 2020-12-05 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader workng across Pays Plat access roads | 5 | C031-C049 | Pays Plat River | 0 | 44176 |  | 37 | 44178 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting726020201205-6Grader - Cat 12 to 14 or equal- After Jan 108.51079.33 | Corbiere and Sons Contracting726020201205-6Grader - Cat 12 to 14 or equal- After Jan 108.51079.33Inv#082 | [5 empty] | 1 | 1079.33 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7260 | 20201205-6 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-12-05 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader workng across Pays Plat access roads | 5 | C031-C049 | Pays Plat River | 0 | 44176 |  | 37 | 44178 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting726020201205-6Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting726020201205-6Light Truck - Pick up- After Jan 101243.75Inv#082 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7260 | 20201205-6 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-12-05 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader workng across Pays Plat access roads | 5 | C031-C049 | Pays Plat River | 0 | 44176 |  | 37 | 44178 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting726020201205-6L.O.A.1210 | Corbiere and Sons Contracting726020201205-6L.O.A.1210Inv#082 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7260 | 20201205-6 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 9.5 | HR |  |  | 75 | 0 | 712.5 | 92.625 | 805.125 | 2020-12-05 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader workng across Pays Plat access roads | 5 | C031-C049 | Pays Plat River | 0 | 44176 |  | 37 | 44178 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting726020201205-6Operator - Principle - After Jan 109.5712.5 | Corbiere and Sons Contracting726020201205-6Operator - Principle - After Jan 109.5712.5Inv#082 | [5 empty] | 1 | 712.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7262 | 20201205-8 | 53510504 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10.5 | Dynamic | 103.84 | 0 |  |  | 1453.725 | 188.9843 | 1642.7093 | 2020-12-05 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading trucks from stock pile. | 5 | C050-C069 | Antler Lake | 0 | 44176 |  | 37 | 44178 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting726220201205-8Excavator - 30 ton- After Jan 1010.51453.725 | Corbiere and Sons Contracting726220201205-8Excavator - 30 ton- After Jan 1010.51453.725Inv#082 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1453.725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7262 | 20201205-8 | 53510504 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10.5 | HR | 9.16 | 0 |  |  | 128.205 | 16.6667 | 144.8716 | 2020-12-05 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading trucks from stock pile. | 5 | C050-C069 | Antler Lake | 0 | 44176 |  | 37 | 44178 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting726220201205-8Excavator Thumb - 30 - 50 ton- After Jan 1010.5128.205 | Corbiere and Sons Contracting726220201205-8Excavator Thumb - 30 - 50 ton- After Jan 1010.5128.205Inv#082 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 128.205 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7262 | 20201205-8 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-12-05 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading trucks from stock pile. | 5 | C050-C069 | Antler Lake | 0 | 44176 |  | 37 | 44178 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting726220201205-8Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting726220201205-8Light Truck - Pick up- After Jan 101243.75Inv#082 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7262 | 20201205-8 | 53510504 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-12-05 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading trucks from stock pile. | 5 | C050-C069 | Antler Lake | 0 | 44176 |  | 37 | 44178 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting726220201205-8L.O.A.1210 | Corbiere and Sons Contracting726220201205-8L.O.A.1210Inv#082 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7262 | 20201205-8 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-12-05 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading trucks from stock pile. | 5 | C050-C069 | Antler Lake | 0 | 44176 |  | 37 | 44178 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting726220201205-8Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting726220201205-8Operator - Principle - After Jan 1011.5862.5Inv#082 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7263 | 20201205-9 | 53510504 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10.5 | Dynamic | 98.61 | 0 |  |  | 1380.54 | 179.4702 | 1560.0102 | 2020-12-05 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks from main entrance, rock trucks hauling, dozer spreading gravel from C-075. Labourer rolling geo. | 5 | C070-C075 | White Sand | 0 | 44176 |  | 37 | 44178 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting726320201205-9Dozer D6 or equal- After Jan 1010.51380.54 | Corbiere and Sons Contracting726320201205-9Dozer D6 or equal- After Jan 1010.51380.54Inv#082 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1380.54 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7263 | 20201205-9 | 53510504 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10.5 | Dynamic | 103.84 | 0 |  |  | 1453.725 | 188.9843 | 1642.7093 | 2020-12-05 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks from main entrance, rock trucks hauling, dozer spreading gravel from C-075. Labourer rolling geo. | 5 | C070-C075 | White Sand | 0 | 44176 |  | 37 | 44178 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting726320201205-9Excavator - 30 ton- After Jan 1010.51453.725 | Corbiere and Sons Contracting726320201205-9Excavator - 30 ton- After Jan 1010.51453.725Inv#082 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1453.725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7263 | 20201205-9 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2020-12-05 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks from main entrance, rock trucks hauling, dozer spreading gravel from C-075. Labourer rolling geo. | 5 | C070-C075 | White Sand | 0 | 44176 |  | 37 | 44178 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting726320201205-9Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting726320201205-9Light Truck - Pick up- After Jan 103731.25Inv#082 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 731.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7263 | 20201205-9 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 21 | Dynamic | 103.54 | 0 |  |  | 2899.05 | 376.8765 | 3275.9265 | 2020-12-05 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks from main entrance, rock trucks hauling, dozer spreading gravel from C-075. Labourer rolling geo. | 5 | C070-C075 | White Sand | 0 | 44176 |  | 37 | 44178 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting726320201205-9Rock Truck - 30 Ton- After Jan 10212899.05 | Corbiere and Sons Contracting726320201205-9Rock Truck - 30 Ton- After Jan 10212899.05Inv#082 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 2899.05 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7263 | 20201205-9 | 53510504 | Access | 0 | Foreman | 95 | 10 | HR |  |  | 95 | 0 | 950 | 123.5 | 1073.5 | 2020-12-05 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks from main entrance, rock trucks hauling, dozer spreading gravel from C-075. Labourer rolling geo. | 5 | C070-C075 | White Sand | 0 | 44176 |  | 37 | 44178 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting726320201205-9Foreman10950 | Corbiere and Sons Contracting726320201205-9Foreman10950Inv#082 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 950 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7263 | 20201205-9 | 53510504 | Access | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2020-12-05 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks from main entrance, rock trucks hauling, dozer spreading gravel from C-075. Labourer rolling geo. | 5 | C070-C075 | White Sand | 0 | 44176 |  | 37 | 44178 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting726320201205-9L.O.A.61260 | Corbiere and Sons Contracting726320201205-9L.O.A.61260Inv#082 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7263 | 20201205-9 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 23 | HR |  |  | 75 | 0 | 1725 | 224.25 | 1949.25 | 2020-12-05 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks from main entrance, rock trucks hauling, dozer spreading gravel from C-075. Labourer rolling geo. | 5 | C070-C075 | White Sand | 0 | 44176 |  | 37 | 44178 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting726320201205-9Operator - Principle - After Jan 10231725 | Corbiere and Sons Contracting726320201205-9Operator - Principle - After Jan 10231725Inv#082 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7263 | 20201205-9 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 23 | HR |  |  | 70 | 0 | 1610 | 209.3 | 1819.3 | 2020-12-05 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks from main entrance, rock trucks hauling, dozer spreading gravel from C-075. Labourer rolling geo. | 5 | C070-C075 | White Sand | 0 | 44176 |  | 37 | 44178 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting726320201205-9Driver - AZ - After Jan 10231610 | Corbiere and Sons Contracting726320201205-9Driver - AZ - After Jan 10231610Inv#082 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1610 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7263 | 20201205-9 | 53510504 | Access | 0 | Labourer - General - After Jan 10 | 60 | 3 | HR |  |  | 60 | 0 | 180 | 23.4 | 203.4 | 2020-12-05 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks from main entrance, rock trucks hauling, dozer spreading gravel from C-075. Labourer rolling geo. | 5 | C070-C075 | White Sand | 0 | 44176 |  | 37 | 44178 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting726320201205-9Labourer - General - After Jan 103180 | Corbiere and Sons Contracting726320201205-9Labourer - General - After Jan 103180Inv#082 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 180 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7282 | 20201206-12 | 53510504 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10.5 | Dynamic | 98.61 | 0 |  |  | 1380.54 | 179.4702 | 1560.0102 | 2020-12-06 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX loading rock trucks from main entrance, rock trucks hauling all day, dozer spreading gravel from C-075. | 5 | C070-C075 | White Sand | 0 | 44179 |  | 37 | 44181 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting728220201206-12Dozer D6 or equal- After Jan 1010.51380.54 | Corbiere and Sons Contracting728220201206-12Dozer D6 or equal- After Jan 1010.51380.54Inv#082 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1380.54 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7282 | 20201206-12 | 53510504 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10.5 | Dynamic | 103.84 | 0 |  |  | 1453.725 | 188.9843 | 1642.7093 | 2020-12-06 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX loading rock trucks from main entrance, rock trucks hauling all day, dozer spreading gravel from C-075. | 5 | C070-C075 | White Sand | 0 | 44179 |  | 37 | 44181 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting728220201206-12Excavator - 30 ton- After Jan 1010.51453.725 | Corbiere and Sons Contracting728220201206-12Excavator - 30 ton- After Jan 1010.51453.725Inv#082 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1453.725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7282 | 20201206-12 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2020-12-06 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX loading rock trucks from main entrance, rock trucks hauling all day, dozer spreading gravel from C-075. | 5 | C070-C075 | White Sand | 0 | 44179 |  | 37 | 44181 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting728220201206-12Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting728220201206-12Light Truck - Pick up- After Jan 103731.25Inv#082 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 731.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7282 | 20201206-12 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 21 | Dynamic | 103.54 | 0 |  |  | 2899.05 | 376.8765 | 3275.9265 | 2020-12-06 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX loading rock trucks from main entrance, rock trucks hauling all day, dozer spreading gravel from C-075. | 5 | C070-C075 | White Sand | 0 | 44179 |  | 37 | 44181 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting728220201206-12Rock Truck - 30 Ton- After Jan 10212899.05 | Corbiere and Sons Contracting728220201206-12Rock Truck - 30 Ton- After Jan 10212899.05Inv#082 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 2899.05 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7282 | 20201206-12 | 53510504 | Access | 0 | Foreman | 95 | 10 | HR |  |  | 95 | 0 | 950 | 123.5 | 1073.5 | 2020-12-06 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX loading rock trucks from main entrance, rock trucks hauling all day, dozer spreading gravel from C-075. | 5 | C070-C075 | White Sand | 0 | 44179 |  | 37 | 44181 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting728220201206-12Foreman10950 | Corbiere and Sons Contracting728220201206-12Foreman10950Inv#082 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 950 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7282 | 20201206-12 | 53510504 | Access | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2020-12-06 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX loading rock trucks from main entrance, rock trucks hauling all day, dozer spreading gravel from C-075. | 5 | C070-C075 | White Sand | 0 | 44179 |  | 37 | 44181 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting728220201206-12L.O.A.51050 | Corbiere and Sons Contracting728220201206-12L.O.A.51050Inv#082 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7282 | 20201206-12 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 23 | HR |  |  | 75 | 0 | 1725 | 224.25 | 1949.25 | 2020-12-06 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX loading rock trucks from main entrance, rock trucks hauling all day, dozer spreading gravel from C-075. | 5 | C070-C075 | White Sand | 0 | 44179 |  | 37 | 44181 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting728220201206-12Operator - Principle - After Jan 10231725 | Corbiere and Sons Contracting728220201206-12Operator - Principle - After Jan 10231725Inv#082 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7282 | 20201206-12 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 23 | HR |  |  | 70 | 0 | 1610 | 209.3 | 1819.3 | 2020-12-06 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX loading rock trucks from main entrance, rock trucks hauling all day, dozer spreading gravel from C-075. | 5 | C070-C075 | White Sand | 0 | 44179 |  | 37 | 44181 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting728220201206-12Driver - AZ - After Jan 10231610 | Corbiere and Sons Contracting728220201206-12Driver - AZ - After Jan 10231610Inv#082 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1610 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7283 | 20201206-13 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 5.5 | Dynamic | 95.24 | 0 |  |  | 698.39 | 90.7907 | 789.1807 | 2020-12-06 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working all morning until 12:30pm | 5 | C070-C075 | White Sand | 0 | 44179 |  | 37 | 44181 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting728320201206-13Grader - Cat 12 to 14 or equal- After Jan 105.5698.39 | Corbiere and Sons Contracting728320201206-13Grader - Cat 12 to 14 or equal- After Jan 105.5698.39Inv#082 | [5 empty] | 1 | 698.39 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7283 | 20201206-13 | 53510511 | Access | 0 | Foreman | 95 | 2 | HR |  |  | 95 | 0 | 190 | 24.7 | 214.7 | 2020-12-06 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working all morning until 12:30pm | 5 | C070-C075 | White Sand | 0 | 44179 |  | 37 | 44181 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting728320201206-13Foreman2190 | Corbiere and Sons Contracting728320201206-13Foreman2190Inv#082 | [5 empty] | 1 | 190 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7283 | 20201206-13 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-12-06 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working all morning until 12:30pm | 5 | C070-C075 | White Sand | 0 | 44179 |  | 37 | 44181 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting728320201206-13L.O.A.1210 | Corbiere and Sons Contracting728320201206-13L.O.A.1210Inv#082 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7283 | 20201206-13 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 75 | 0 | 450 | 58.5 | 508.5 | 2020-12-06 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working all morning until 12:30pm | 5 | C070-C075 | White Sand | 0 | 44179 |  | 37 | 44181 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting728320201206-13Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting728320201206-13Operator - Principle - After Jan 106450Inv#082 | [5 empty] | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7284 | 20201206-14 | 53510504 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 4 | Dynamic | 98.61 | 0 |  |  | 525.92 | 68.3696 | 594.2896 | 2020-12-06 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-15 loaded rock trucks for gravel, rock truck hauling, dozer spreading gravel. | 5 | C076-C116 | Cook Lake | 0 | 44179 |  | 37 | 44181 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting728420201206-14Dozer D6 or equal- After Jan 104525.92 | Corbiere and Sons Contracting728420201206-14Dozer D6 or equal- After Jan 104525.92Inv#082 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 525.92 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7284 | 20201206-14 | 53510504 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 4 | Dynamic | 103.84 | 0 |  |  | 553.8 | 71.994 | 625.794 | 2020-12-06 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-15 loaded rock trucks for gravel, rock truck hauling, dozer spreading gravel. | 5 | C076-C116 | Cook Lake | 0 | 44179 |  | 37 | 44181 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting728420201206-14Excavator - 30 ton- After Jan 104553.8 | Corbiere and Sons Contracting728420201206-14Excavator - 30 ton- After Jan 104553.8Inv#082 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 553.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7284 | 20201206-14 | 53510504 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 4 | HR | 9.16 | 0 |  |  | 48.84 | 6.3492 | 55.1892 | 2020-12-06 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-15 loaded rock trucks for gravel, rock truck hauling, dozer spreading gravel. | 5 | C076-C116 | Cook Lake | 0 | 44179 |  | 37 | 44181 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting728420201206-14Excavator Thumb - 30 - 50 ton- After Jan 10448.84 | Corbiere and Sons Contracting728420201206-14Excavator Thumb - 30 - 50 ton- After Jan 10448.84Inv#082 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 48.84 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7284 | 20201206-14 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-12-06 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-15 loaded rock trucks for gravel, rock truck hauling, dozer spreading gravel. | 5 | C076-C116 | Cook Lake | 0 | 44179 |  | 37 | 44181 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting728420201206-14Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting728420201206-14Light Truck - Pick up- After Jan 102487.5Inv#082 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7284 | 20201206-14 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 4 | Dynamic | 103.54 | 0 |  |  | 552.2 | 71.786 | 623.986 | 2020-12-06 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-15 loaded rock trucks for gravel, rock truck hauling, dozer spreading gravel. | 5 | C076-C116 | Cook Lake | 0 | 44179 |  | 37 | 44181 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting728420201206-14Rock Truck - 30 Ton- After Jan 104552.2 | Corbiere and Sons Contracting728420201206-14Rock Truck - 30 Ton- After Jan 104552.2Inv#082 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 552.2 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7284 | 20201206-14 | 53510504 | Access | 0 | Foreman | 95 | 4 | HR |  |  | 95 | 0 | 380 | 49.4 | 429.4 | 2020-12-06 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-15 loaded rock trucks for gravel, rock truck hauling, dozer spreading gravel. | 5 | C076-C116 | Cook Lake | 0 | 44179 |  | 37 | 44181 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting728420201206-14Foreman4380 | Corbiere and Sons Contracting728420201206-14Foreman4380Inv#082 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7284 | 20201206-14 | 53510504 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2020-12-06 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-15 loaded rock trucks for gravel, rock truck hauling, dozer spreading gravel. | 5 | C076-C116 | Cook Lake | 0 | 44179 |  | 37 | 44181 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting728420201206-14L.O.A.4840 | Corbiere and Sons Contracting728420201206-14L.O.A.4840Inv#082 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7284 | 20201206-14 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 8 | HR |  |  | 75 | 0 | 600 | 78 | 678 | 2020-12-06 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-15 loaded rock trucks for gravel, rock truck hauling, dozer spreading gravel. | 5 | C076-C116 | Cook Lake | 0 | 44179 |  | 37 | 44181 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting728420201206-14Operator - Principle - After Jan 108600 | Corbiere and Sons Contracting728420201206-14Operator - Principle - After Jan 108600Inv#082 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7284 | 20201206-14 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 4 | HR |  |  | 70 | 0 | 280 | 36.4 | 316.4 | 2020-12-06 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-15 loaded rock trucks for gravel, rock truck hauling, dozer spreading gravel. | 5 | C076-C116 | Cook Lake | 0 | 44179 |  | 37 | 44181 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting728420201206-14Driver - AZ - After Jan 104280 | Corbiere and Sons Contracting728420201206-14Driver - AZ - After Jan 104280Inv#082 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7285 | 20201206-15 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10.5 | Dynamic | 95.24 | 0 |  |  | 1333.29 | 173.3277 | 1506.6177 | 2020-12-06 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader doing winter road maintenance all day | 5 | C076-C116 | Cook Lake | 0 | 44179 |  | 37 | 44181 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting728520201206-15Grader - Cat 12 to 14 or equal- After Jan 1010.51333.29 | Corbiere and Sons Contracting728520201206-15Grader - Cat 12 to 14 or equal- After Jan 1010.51333.29Inv#082 | [5 empty] | 1 | 1333.29 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7285 | 20201206-15 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-12-06 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader doing winter road maintenance all day | 5 | C076-C116 | Cook Lake | 0 | 44179 |  | 37 | 44181 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting728520201206-15Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting728520201206-15Light Truck - Pick up- After Jan 101243.75Inv#082 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7285 | 20201206-15 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-12-06 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader doing winter road maintenance all day | 5 | C076-C116 | Cook Lake | 0 | 44179 |  | 37 | 44181 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting728520201206-15L.O.A.1210 | Corbiere and Sons Contracting728520201206-15L.O.A.1210Inv#082 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7285 | 20201206-15 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-12-06 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader doing winter road maintenance all day | 5 | C076-C116 | Cook Lake | 0 | 44179 |  | 37 | 44181 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting728520201206-15Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting728520201206-15Operator - Principle - After Jan 1011.5862.5Inv#082 | [5 empty] | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7287 | 20201206-17 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 3.5 | Dynamic | 95.24 | 0 |  |  | 444.43 | 57.7759 | 502.2059 | 2020-12-06 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working on Mill Rd S. | 5 | C117-C124 | Mill Road | 0 | 44179 |  | 37 | 44181 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting728720201206-17Grader - Cat 12 to 14 or equal- After Jan 103.5444.43 | Corbiere and Sons Contracting728720201206-17Grader - Cat 12 to 14 or equal- After Jan 103.5444.43Inv#082 | [5 empty] | 1 | 444.43 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7287 | 20201206-17 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 3.5 | HR |  |  | 75 | 0 | 262.5 | 34.125 | 296.625 | 2020-12-06 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working on Mill Rd S. | 5 | C117-C124 | Mill Road | 0 | 44179 |  | 37 | 44181 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting728720201206-17Operator - Principle - After Jan 103.5262.5 | Corbiere and Sons Contracting728720201206-17Operator - Principle - After Jan 103.5262.5Inv#082 | [5 empty] | 1 | 262.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7275 | 20201206-5 | 53510412 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 2 | Dynamic | 98.61 | 0 |  |  | 262.96 | 34.1848 | 297.1448 | 2020-12-06 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Sander hauled 2 loads of sand in for gravel haul. | 4 | B194-B203 | Little Gravel River Road | 0 | 44179 |  | 37 | 44181 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting727520201206-5Dozer D6 or equal- After Jan 102262.96 | Corbiere and Sons Contracting727520201206-5Dozer D6 or equal- After Jan 102262.96Inv#082 | [5 empty] | 1 | 262.96 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7275 | 20201206-5 | 53510412 | Access | 0 | Sander Truck - Hwy- After Jan 10 | 55 | 5 | Dynamic | 41.25 | 0 |  |  | 275 | 35.75 | 310.75 | 2020-12-06 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Sander hauled 2 loads of sand in for gravel haul. | 4 | B194-B203 | Little Gravel River Road | 0 | 44179 |  | 37 | 44181 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting727520201206-5Sander Truck - Hwy- After Jan 105275 | Corbiere and Sons Contracting727520201206-5Sander Truck - Hwy- After Jan 105275Inv#082 | [5 empty] | 1 | 275 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7275 | 20201206-5 | 53510412 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 2 | HR |  |  | 75 | 0 | 150 | 19.5 | 169.5 | 2020-12-06 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Sander hauled 2 loads of sand in for gravel haul. | 4 | B194-B203 | Little Gravel River Road | 0 | 44179 |  | 37 | 44181 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting727520201206-5Operator - Principle - After Jan 102150 | Corbiere and Sons Contracting727520201206-5Operator - Principle - After Jan 102150Inv#082 | [5 empty] | 1 | 150 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7275 | 20201206-5 | 53510412 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 5 | HR |  |  | 70 | 0 | 350 | 45.5 | 395.5 | 2020-12-06 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Sander hauled 2 loads of sand in for gravel haul. | 4 | B194-B203 | Little Gravel River Road | 0 | 44179 |  | 37 | 44181 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting727520201206-5Driver - AZ - After Jan 105350 | Corbiere and Sons Contracting727520201206-5Driver - AZ - After Jan 105350Inv#082 | [5 empty] | 1 | 350 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7305 | 20201207-16 | 53510504 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10.5 | Dynamic | 98.61 | 0 |  |  | 1380.54 | 179.4702 | 1560.0102 | 2020-12-07 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX loading rock trucks from main entrance, rock trucks hauling, dozer spreading from C-073 - C-074. Labourer rolling out geo. | 5 | C070-C075 | White Sand | 0 | 44179 |  | 37 | 44181 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting730520201207-16Dozer D6 or equal- After Jan 1010.51380.54 | Corbiere and Sons Contracting730520201207-16Dozer D6 or equal- After Jan 1010.51380.54Inv#082 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1380.54 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7305 | 20201207-16 | 53510504 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10.5 | Dynamic | 103.84 | 0 |  |  | 1453.725 | 188.9843 | 1642.7093 | 2020-12-07 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX loading rock trucks from main entrance, rock trucks hauling, dozer spreading from C-073 - C-074. Labourer rolling out geo. | 5 | C070-C075 | White Sand | 0 | 44179 |  | 37 | 44181 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting730520201207-16Excavator - 30 ton- After Jan 1010.51453.725 | Corbiere and Sons Contracting730520201207-16Excavator - 30 ton- After Jan 1010.51453.725Inv#082 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1453.725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7305 | 20201207-16 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2020-12-07 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX loading rock trucks from main entrance, rock trucks hauling, dozer spreading from C-073 - C-074. Labourer rolling out geo. | 5 | C070-C075 | White Sand | 0 | 44179 |  | 37 | 44181 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting730520201207-16Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting730520201207-16Light Truck - Pick up- After Jan 103731.25Inv#082 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 731.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7305 | 20201207-16 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 21 | Dynamic | 103.54 | 0 |  |  | 2899.05 | 376.8765 | 3275.9265 | 2020-12-07 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX loading rock trucks from main entrance, rock trucks hauling, dozer spreading from C-073 - C-074. Labourer rolling out geo. | 5 | C070-C075 | White Sand | 0 | 44179 |  | 37 | 44181 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting730520201207-16Rock Truck - 30 Ton- After Jan 10212899.05 | Corbiere and Sons Contracting730520201207-16Rock Truck - 30 Ton- After Jan 10212899.05Inv#082 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 2899.05 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7305 | 20201207-16 | 53510504 | Access | 0 | Foreman | 95 | 4 | HR |  |  | 95 | 0 | 380 | 49.4 | 429.4 | 2020-12-07 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX loading rock trucks from main entrance, rock trucks hauling, dozer spreading from C-073 - C-074. Labourer rolling out geo. | 5 | C070-C075 | White Sand | 0 | 44179 |  | 37 | 44181 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting730520201207-16Foreman4380 | Corbiere and Sons Contracting730520201207-16Foreman4380Inv#082 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7305 | 20201207-16 | 53510504 | Access | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2020-12-07 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX loading rock trucks from main entrance, rock trucks hauling, dozer spreading from C-073 - C-074. Labourer rolling out geo. | 5 | C070-C075 | White Sand | 0 | 44179 |  | 37 | 44181 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting730520201207-16L.O.A.61260 | Corbiere and Sons Contracting730520201207-16L.O.A.61260Inv#082 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7305 | 20201207-16 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 23 | HR |  |  | 75 | 0 | 1725 | 224.25 | 1949.25 | 2020-12-07 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX loading rock trucks from main entrance, rock trucks hauling, dozer spreading from C-073 - C-074. Labourer rolling out geo. | 5 | C070-C075 | White Sand | 0 | 44179 |  | 37 | 44181 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting730520201207-16Operator - Principle - After Jan 10231725 | Corbiere and Sons Contracting730520201207-16Operator - Principle - After Jan 10231725Inv#082 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7305 | 20201207-16 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 23 | HR |  |  | 70 | 0 | 1610 | 209.3 | 1819.3 | 2020-12-07 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX loading rock trucks from main entrance, rock trucks hauling, dozer spreading from C-073 - C-074. Labourer rolling out geo. | 5 | C070-C075 | White Sand | 0 | 44179 |  | 37 | 44181 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting730520201207-16Driver - AZ - After Jan 10231610 | Corbiere and Sons Contracting730520201207-16Driver - AZ - After Jan 10231610Inv#082 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1610 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7305 | 20201207-16 | 53510504 | Access | 0 | Labourer - General - After Jan 10 | 60 | 3 | HR |  |  | 60 | 0 | 180 | 23.4 | 203.4 | 2020-12-07 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX loading rock trucks from main entrance, rock trucks hauling, dozer spreading from C-073 - C-074. Labourer rolling out geo. | 5 | C070-C075 | White Sand | 0 | 44179 |  | 37 | 44181 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting730520201207-16Labourer - General - After Jan 103180 | Corbiere and Sons Contracting730520201207-16Labourer - General - After Jan 103180Inv#082 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 180 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7306 | 20201207-17 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10.5 | Dynamic | 95.24 | 0 |  |  | 1333.29 | 173.3277 | 1506.6177 | 2020-12-07 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Cooks Lake Rd | 5 | C076-C116 | Cook Lake | 0 | 44179 |  | 37 | 44181 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting730620201207-17Grader - Cat 12 to 14 or equal- After Jan 1010.51333.29 | Corbiere and Sons Contracting730620201207-17Grader - Cat 12 to 14 or equal- After Jan 1010.51333.29Inv#082 | [5 empty] | 1 | 1333.29 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7306 | 20201207-17 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-12-07 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Cooks Lake Rd | 5 | C076-C116 | Cook Lake | 0 | 44179 |  | 37 | 44181 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting730620201207-17Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting730620201207-17Light Truck - Pick up- After Jan 101243.75Inv#082 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7306 | 20201207-17 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-12-07 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Cooks Lake Rd | 5 | C076-C116 | Cook Lake | 0 | 44179 |  | 37 | 44181 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting730620201207-17L.O.A.1210 | Corbiere and Sons Contracting730620201207-17L.O.A.1210Inv#082 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7306 | 20201207-17 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-12-07 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Cooks Lake Rd | 5 | C076-C116 | Cook Lake | 0 | 44179 |  | 37 | 44181 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting730620201207-17Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting730620201207-17Operator - Principle - After Jan 1011.5862.5Inv#082 | [5 empty] | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7298 | 20201207-9 | 53510412 | Access | 0 | Sander Truck - Hwy- After Jan 10 | 55 | 8 | Dynamic | 41.25 | 0 |  |  | 440 | 57.2 | 497.2 | 2020-12-07 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Sander hauled 4 loads of sand to cover hills rock truck was hauling on | 4 | B194-B203 | Little Gravel River Road | 0 | 44179 |  | 37 | 44181 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting729820201207-9Sander Truck - Hwy- After Jan 108440 | Corbiere and Sons Contracting729820201207-9Sander Truck - Hwy- After Jan 108440Inv#082 | [5 empty] | 1 | 440 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7298 | 20201207-9 | 53510412 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 8 | HR |  |  | 70 | 0 | 560 | 72.8 | 632.8 | 2020-12-07 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Sander hauled 4 loads of sand to cover hills rock truck was hauling on | 4 | B194-B203 | Little Gravel River Road | 0 | 44179 |  | 37 | 44181 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting729820201207-9Driver - AZ - After Jan 108560 | Corbiere and Sons Contracting729820201207-9Driver - AZ - After Jan 108560Inv#082 | [5 empty] | 1 | 560 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7316 | 20201208-10 | 53510412 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 4 | Dynamic | 98.61 | 0 |  |  | 525.92 | 68.3696 | 594.2896 |  | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | DZ-05 trimmed roads | 4 | B194-B203 | Little Gravel River Road | 0 | 44179 |  | 37 | 44181 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting731620201208-10Dozer D6 or equal- After Jan 104525.92 | Corbiere and Sons Contracting731620201208-10Dozer D6 or equal- After Jan 104525.92Inv#082 | [5 empty] | 1 | 525.92 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7316 | 20201208-10 | 53510412 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 4 | HR |  |  | 75 | 0 | 300 | 39 | 339 |  | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | DZ-05 trimmed roads | 4 | B194-B203 | Little Gravel River Road | 0 | 44179 |  | 37 | 44181 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting731620201208-10Operator - Principle - After Jan 104300 | Corbiere and Sons Contracting731620201208-10Operator - Principle - After Jan 104300Inv#082 | [5 empty] | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7325 | 20201208-14 | 53510504 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 6 | Dynamic | 98.61 | 0 |  |  | 788.88 | 102.5544 | 891.4344 | 2020-12-08 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX loading rock trucks for gravel spread, rock truck hauling, dozer spreading from C-115. | 5 | C093-C116 | Cook Lake | 0 | 44180 |  | 50 | 44180 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting732520201208-14Dozer D6 or equal- After Jan 106788.88 | Corbiere and Sons Contracting732520201208-14Dozer D6 or equal- After Jan 106788.88Inv#082 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 788.88 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7325 | 20201208-14 | 53510504 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 6 | Dynamic | 110.22 | 0 |  |  | 881.76 | 114.6288 | 996.3888 | 2020-12-08 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX loading rock trucks for gravel spread, rock truck hauling, dozer spreading from C-115. | 5 | C093-C116 | Cook Lake | 0 | 44180 |  | 50 | 44180 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting732520201208-14Excavator - 36 ton- After Jan 106881.76 | Corbiere and Sons Contracting732520201208-14Excavator - 36 ton- After Jan 106881.76Inv#082 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 881.76 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7325 | 20201208-14 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-12-08 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX loading rock trucks for gravel spread, rock truck hauling, dozer spreading from C-115. | 5 | C093-C116 | Cook Lake | 0 | 44180 |  | 50 | 44180 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting732520201208-14Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting732520201208-14Light Truck - Pick up- After Jan 102487.5Inv#082 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7325 | 20201208-14 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 7 | Dynamic | 103.54 | 0 |  |  | 966.35 | 125.6255 | 1091.9755 | 2020-12-08 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX loading rock trucks for gravel spread, rock truck hauling, dozer spreading from C-115. | 5 | C093-C116 | Cook Lake | 0 | 44180 |  | 50 | 44180 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting732520201208-14Rock Truck - 30 Ton- After Jan 107966.35 | Corbiere and Sons Contracting732520201208-14Rock Truck - 30 Ton- After Jan 107966.35Inv#082 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 966.35 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7325 | 20201208-14 | 53510504 | Access | 0 | Foreman | 95 | 4 | HR |  |  | 95 | 0 | 380 | 49.4 | 429.4 | 2020-12-08 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX loading rock trucks for gravel spread, rock truck hauling, dozer spreading from C-115. | 5 | C093-C116 | Cook Lake | 0 | 44180 |  | 50 | 44180 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting732520201208-14Foreman4380 | Corbiere and Sons Contracting732520201208-14Foreman4380Inv#082 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7325 | 20201208-14 | 53510504 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2020-12-08 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX loading rock trucks for gravel spread, rock truck hauling, dozer spreading from C-115. | 5 | C093-C116 | Cook Lake | 0 | 44180 |  | 50 | 44180 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting732520201208-14L.O.A.4840 | Corbiere and Sons Contracting732520201208-14L.O.A.4840Inv#082 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7325 | 20201208-14 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 12 | HR |  |  | 75 | 0 | 900 | 117 | 1017 | 2020-12-08 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX loading rock trucks for gravel spread, rock truck hauling, dozer spreading from C-115. | 5 | C093-C116 | Cook Lake | 0 | 44180 |  | 50 | 44180 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting732520201208-14Operator - Principle - After Jan 1012900 | Corbiere and Sons Contracting732520201208-14Operator - Principle - After Jan 1012900Inv#082 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7325 | 20201208-14 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 7 | HR |  |  | 70 | 0 | 490 | 63.7 | 553.7 | 2020-12-08 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX loading rock trucks for gravel spread, rock truck hauling, dozer spreading from C-115. | 5 | C093-C116 | Cook Lake | 0 | 44180 |  | 50 | 44180 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting732520201208-14Driver - AZ - After Jan 107490 | Corbiere and Sons Contracting732520201208-14Driver - AZ - After Jan 107490Inv#082 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 490 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7326 | 20201208-15 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 6 | Dynamic | 95.24 | 0 |  |  | 761.88 | 99.0444 | 860.9244 | 2020-12-08 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter access maintenance with grader. | 5 | C076-C116 | Cook Lake | 0 | 44180 |  | 50 | 44180 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting732620201208-15Grader - Cat 12 to 14 or equal- After Jan 106761.88 | Corbiere and Sons Contracting732620201208-15Grader - Cat 12 to 14 or equal- After Jan 106761.88Inv#082 | [5 empty] | 1 | 761.88 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7326 | 20201208-15 | 53510511 | Access | 0 | Light Truck - 1 to 3 Ton- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-12-08 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter access maintenance with grader. | 5 | C076-C116 | Cook Lake | 0 | 44180 |  | 50 | 44180 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting732620201208-15Light Truck - 1 to 3 Ton- After Jan 101243.75 | Corbiere and Sons Contracting732620201208-15Light Truck - 1 to 3 Ton- After Jan 101243.75Inv#082 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7326 | 20201208-15 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-12-08 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter access maintenance with grader. | 5 | C076-C116 | Cook Lake | 0 | 44180 |  | 50 | 44180 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting732620201208-15L.O.A.1210 | Corbiere and Sons Contracting732620201208-15L.O.A.1210Inv#082 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7326 | 20201208-15 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 75 | 0 | 450 | 58.5 | 508.5 | 2020-12-08 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Winter access maintenance with grader. | 5 | C076-C116 | Cook Lake | 0 | 44180 |  | 50 | 44180 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting732620201208-15Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting732620201208-15Operator - Principle - After Jan 106450Inv#082 | [5 empty] | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7327 | 20201208-16 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 5.5 | Dynamic | 95.24 | 0 |  |  | 698.39 | 90.7907 | 789.1807 | 2020-12-08 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Mill Road | 5 | C117-C124 | Mill Road | 0 | 44180 |  | 50 | 44180 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting732720201208-16Grader - Cat 12 to 14 or equal- After Jan 105.5698.39 | Corbiere and Sons Contracting732720201208-16Grader - Cat 12 to 14 or equal- After Jan 105.5698.39Inv#082 | [5 empty] | 1 | 698.39 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7327 | 20201208-16 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-12-08 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Mill Road | 5 | C117-C124 | Mill Road | 0 | 44180 |  | 50 | 44180 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting732720201208-16Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting732720201208-16Light Truck - Pick up- After Jan 101243.75Inv#082 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7327 | 20201208-16 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-12-08 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Mill Road | 5 | C117-C124 | Mill Road | 0 | 44180 |  | 50 | 44180 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting732720201208-16L.O.A.1210 | Corbiere and Sons Contracting732720201208-16L.O.A.1210Inv#082 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7327 | 20201208-16 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 75 | 0 | 450 | 58.5 | 508.5 | 2020-12-08 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Mill Road | 5 | C117-C124 | Mill Road | 0 | 44180 |  | 50 | 44180 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting732720201208-16Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting732720201208-16Operator - Principle - After Jan 106450Inv#082 | [5 empty] | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7408 | 20201208-17 | 53510503 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 6.5 | Dynamic | 103.84 | 0 |  |  | 899.925 | 116.9903 | 1016.9153 | 2020-12-08 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading trees to bring to C-075, Rock trucks hauling trees from C-071 to C-075 - both also laid out geo. | 5 | C070-C075 | White Sand | 0 | 44181 |  | 50 | 44181 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting740820201208-17Excavator - 30 ton- After Jan 106.5899.925 | Corbiere and Sons Contracting740820201208-17Excavator - 30 ton- After Jan 106.5899.925Inv#082 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 899.925 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7408 | 20201208-17 | 53510503 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 6.5 | HR | 9.16 | 0 |  |  | 79.365 | 10.3174 | 89.6825 | 2020-12-08 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading trees to bring to C-075, Rock trucks hauling trees from C-071 to C-075 - both also laid out geo. | 5 | C070-C075 | White Sand | 0 | 44181 |  | 50 | 44181 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting740820201208-17Excavator Thumb - 30 - 50 ton- After Jan 106.579.365 | Corbiere and Sons Contracting740820201208-17Excavator Thumb - 30 - 50 ton- After Jan 106.579.365Inv#082 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 79.365 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7408 | 20201208-17 | 53510503 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2020-12-08 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading trees to bring to C-075, Rock trucks hauling trees from C-071 to C-075 - both also laid out geo. | 5 | C070-C075 | White Sand | 0 | 44181 |  | 50 | 44181 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting740820201208-17Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting740820201208-17Light Truck - Pick up- After Jan 103731.25Inv#082 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 731.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7408 | 20201208-17 | 53510503 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 14 | Dynamic | 103.54 | 0 |  |  | 1932.7 | 251.251 | 2183.951 | 2020-12-08 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading trees to bring to C-075, Rock trucks hauling trees from C-071 to C-075 - both also laid out geo. | 5 | C070-C075 | White Sand | 0 | 44181 |  | 50 | 44181 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting740820201208-17Rock Truck - 30 Ton- After Jan 10141932.7 | Corbiere and Sons Contracting740820201208-17Rock Truck - 30 Ton- After Jan 10141932.7Inv#082 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 1932.7 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7408 | 20201208-17 | 53510503 | Access | 0 | Foreman | 95 | 4 | HR |  |  | 95 | 0 | 380 | 49.4 | 429.4 | 2020-12-08 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading trees to bring to C-075, Rock trucks hauling trees from C-071 to C-075 - both also laid out geo. | 5 | C070-C075 | White Sand | 0 | 44181 |  | 50 | 44181 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting740820201208-17Foreman4380 | Corbiere and Sons Contracting740820201208-17Foreman4380Inv#082 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7408 | 20201208-17 | 53510503 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2020-12-08 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading trees to bring to C-075, Rock trucks hauling trees from C-071 to C-075 - both also laid out geo. | 5 | C070-C075 | White Sand | 0 | 44181 |  | 50 | 44181 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting740820201208-17L.O.A.4840 | Corbiere and Sons Contracting740820201208-17L.O.A.4840Inv#082 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7408 | 20201208-17 | 53510503 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 7 | HR |  |  | 75 | 0 | 525 | 68.25 | 593.25 | 2020-12-08 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading trees to bring to C-075, Rock trucks hauling trees from C-071 to C-075 - both also laid out geo. | 5 | C070-C075 | White Sand | 0 | 44181 |  | 50 | 44181 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting740820201208-17Operator - Principle - After Jan 107525 | Corbiere and Sons Contracting740820201208-17Operator - Principle - After Jan 107525Inv#082 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 525 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7408 | 20201208-17 | 53510503 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 23 | HR |  |  | 70 | 0 | 1610 | 209.3 | 1819.3 | 2020-12-08 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading trees to bring to C-075, Rock trucks hauling trees from C-071 to C-075 - both also laid out geo. | 5 | C070-C075 | White Sand | 0 | 44181 |  | 50 | 44181 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting740820201208-17Driver - AZ - After Jan 10231610 | Corbiere and Sons Contracting740820201208-17Driver - AZ - After Jan 10231610Inv#082 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 1610 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7405 | 20201208-19 | 53510511 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 8.5 | Dynamic | 98.61 | 0 |  |  | 1117.58 | 145.2854 | 1262.8654 | 2020-12-08 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer spent most of day doing winter maintenance | 5 | C070-C075 | White Sand | 0 | 44181 |  | 50 | 44181 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting740520201208-19Dozer D6 or equal- After Jan 108.51117.58 | Corbiere and Sons Contracting740520201208-19Dozer D6 or equal- After Jan 108.51117.58Inv#082 | [5 empty] | 1 | 1117.58 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7405 | 20201208-19 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-12-08 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer spent most of day doing winter maintenance | 5 | C070-C075 | White Sand | 0 | 44181 |  | 50 | 44181 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting740520201208-19L.O.A.1210 | Corbiere and Sons Contracting740520201208-19L.O.A.1210Inv#082 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7405 | 20201208-19 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 9.5 | HR |  |  | 75 | 0 | 712.5 | 92.625 | 805.125 | 2020-12-08 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer spent most of day doing winter maintenance | 5 | C070-C075 | White Sand | 0 | 44181 |  | 50 | 44181 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting740520201208-19Operator - Principle - After Jan 109.5712.5 | Corbiere and Sons Contracting740520201208-19Operator - Principle - After Jan 109.5712.5Inv#082 | [5 empty] | 1 | 712.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7349 | 20201209-21 | 53510503 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 1.5 | Dynamic | 103.84 | 0 |  |  | 207.675 | 26.9977 | 234.6728 | 2020-12-09 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Placing corduroy | 5 | C070-C075 | White Sand | 0 | 44179 |  | 50 | 44180 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting734920201209-21Excavator - 30 ton- After Jan 101.5207.675 | Corbiere and Sons Contracting734920201209-21Excavator - 30 ton- After Jan 101.5207.675Inv#082 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 207.675 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7349 | 20201209-21 | 53510503 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 1.5 | HR | 9.16 | 0 |  |  | 18.315 | 2.3809 | 20.6959 | 2020-12-09 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Placing corduroy | 5 | C070-C075 | White Sand | 0 | 44179 |  | 50 | 44180 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting734920201209-21Excavator Thumb - 30 - 50 ton- After Jan 101.518.315 | Corbiere and Sons Contracting734920201209-21Excavator Thumb - 30 - 50 ton- After Jan 101.518.315Inv#082 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 18.315 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7349 | 20201209-21 | 53510503 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 2 | HR |  |  | 75 | 0 | 150 | 19.5 | 169.5 | 2020-12-09 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Placing corduroy | 5 | C070-C075 | White Sand | 0 | 44179 |  | 50 | 44180 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting734920201209-21Operator - Principle - After Jan 102150 | Corbiere and Sons Contracting734920201209-21Operator - Principle - After Jan 102150Inv#082 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 150 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7350 | 20201209-22 | 53510504 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10.5 | Dynamic | 98.61 | 0 |  |  | 1380.54 | 179.4702 | 1560.0102 | 2020-12-09 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX loading rock trucks, rock trucks hauling from C-070, dozer spreading gravel from C-070. Labourer rolling out geo. | 5 | C070-C075 | White Sand | 0 | 44179 |  | 50 | 44180 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting735020201209-22Dozer D6 or equal- After Jan 1010.51380.54 | Corbiere and Sons Contracting735020201209-22Dozer D6 or equal- After Jan 1010.51380.54Inv#082 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1380.54 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7350 | 20201209-22 | 53510504 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9 | Dynamic | 103.84 | 0 |  |  | 1246.05 | 161.9865 | 1408.0365 | 2020-12-09 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX loading rock trucks, rock trucks hauling from C-070, dozer spreading gravel from C-070. Labourer rolling out geo. | 5 | C070-C075 | White Sand | 0 | 44179 |  | 50 | 44180 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting735020201209-22Excavator - 30 ton- After Jan 1091246.05 | Corbiere and Sons Contracting735020201209-22Excavator - 30 ton- After Jan 1091246.05Inv#082 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1246.05 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7350 | 20201209-22 | 53510504 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9 | HR | 9.16 | 0 |  |  | 109.89 | 14.2857 | 124.1757 | 2020-12-09 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX loading rock trucks, rock trucks hauling from C-070, dozer spreading gravel from C-070. Labourer rolling out geo. | 5 | C070-C075 | White Sand | 0 | 44179 |  | 50 | 44180 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting735020201209-22Excavator Thumb - 30 - 50 ton- After Jan 109109.89 | Corbiere and Sons Contracting735020201209-22Excavator Thumb - 30 - 50 ton- After Jan 109109.89Inv#082 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 109.89 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7350 | 20201209-22 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2020-12-09 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX loading rock trucks, rock trucks hauling from C-070, dozer spreading gravel from C-070. Labourer rolling out geo. | 5 | C070-C075 | White Sand | 0 | 44179 |  | 50 | 44180 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting735020201209-22Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting735020201209-22Light Truck - Pick up- After Jan 103731.25Inv#082 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 731.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7350 | 20201209-22 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 21 | Dynamic | 103.54 | 0 |  |  | 2899.05 | 376.8765 | 3275.9265 | 2020-12-09 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX loading rock trucks, rock trucks hauling from C-070, dozer spreading gravel from C-070. Labourer rolling out geo. | 5 | C070-C075 | White Sand | 0 | 44179 |  | 50 | 44180 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting735020201209-22Rock Truck - 30 Ton- After Jan 10212899.05 | Corbiere and Sons Contracting735020201209-22Rock Truck - 30 Ton- After Jan 10212899.05Inv#082 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 2899.05 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7350 | 20201209-22 | 53510504 | Access | 0 | Foreman | 95 | 6 | HR |  |  | 95 | 0 | 570 | 74.1 | 644.1 | 2020-12-09 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX loading rock trucks, rock trucks hauling from C-070, dozer spreading gravel from C-070. Labourer rolling out geo. | 5 | C070-C075 | White Sand | 0 | 44179 |  | 50 | 44180 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting735020201209-22Foreman6570 | Corbiere and Sons Contracting735020201209-22Foreman6570Inv#082 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 570 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7350 | 20201209-22 | 53510504 | Access | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2020-12-09 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX loading rock trucks, rock trucks hauling from C-070, dozer spreading gravel from C-070. Labourer rolling out geo. | 5 | C070-C075 | White Sand | 0 | 44179 |  | 50 | 44180 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting735020201209-22L.O.A.61260 | Corbiere and Sons Contracting735020201209-22L.O.A.61260Inv#082 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7350 | 20201209-22 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 21 | HR |  |  | 75 | 0 | 1575 | 204.75 | 1779.75 | 2020-12-09 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX loading rock trucks, rock trucks hauling from C-070, dozer spreading gravel from C-070. Labourer rolling out geo. | 5 | C070-C075 | White Sand | 0 | 44179 |  | 50 | 44180 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting735020201209-22Operator - Principle - After Jan 10211575 | Corbiere and Sons Contracting735020201209-22Operator - Principle - After Jan 10211575Inv#082 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1575 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7350 | 20201209-22 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 23 | HR |  |  | 70 | 0 | 1610 | 209.3 | 1819.3 | 2020-12-09 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX loading rock trucks, rock trucks hauling from C-070, dozer spreading gravel from C-070. Labourer rolling out geo. | 5 | C070-C075 | White Sand | 0 | 44179 |  | 50 | 44180 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting735020201209-22Driver - AZ - After Jan 10231610 | Corbiere and Sons Contracting735020201209-22Driver - AZ - After Jan 10231610Inv#082 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1610 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7350 | 20201209-22 | 53510504 | Access | 0 | Labourer - General - After Jan 10 | 60 | 3 | HR |  |  | 60 | 0 | 180 | 23.4 | 203.4 | 2020-12-09 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX loading rock trucks, rock trucks hauling from C-070, dozer spreading gravel from C-070. Labourer rolling out geo. | 5 | C070-C075 | White Sand | 0 | 44179 |  | 50 | 44180 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting735020201209-22Labourer - General - After Jan 103180 | Corbiere and Sons Contracting735020201209-22Labourer - General - After Jan 103180Inv#082 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 180 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7351 | 20201209-23 | 53510504 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10.5 | Dynamic | 98.61 | 0 |  |  | 1380.54 | 179.4702 | 1560.0102 | 2020-12-09 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX loading rock trucks, rock trucks hauling, dozer spreading from C-078 | 5 | C076-C092 | Cook Lake | 0 | 44179 |  | 50 | 44180 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting735120201209-23Dozer D6 or equal- After Jan 1010.51380.54 | Corbiere and Sons Contracting735120201209-23Dozer D6 or equal- After Jan 1010.51380.54Inv#082 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1380.54 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7351 | 20201209-23 | 53510504 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 21.5 | Dynamic | 110.22 | 0 |  |  | 3159.64 | 410.7532 | 3570.3932 | 2020-12-09 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX loading rock trucks, rock trucks hauling, dozer spreading from C-078 | 5 | C076-C092 | Cook Lake | 0 | 44179 |  | 50 | 44180 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting735120201209-23Excavator - 36 ton- After Jan 1021.53159.64 | Corbiere and Sons Contracting735120201209-23Excavator - 36 ton- After Jan 1021.53159.64Inv#082 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 3159.64 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7351 | 20201209-23 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2020-12-09 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX loading rock trucks, rock trucks hauling, dozer spreading from C-078 | 5 | C076-C092 | Cook Lake | 0 | 44179 |  | 50 | 44180 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting735120201209-23Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting735120201209-23Light Truck - Pick up- After Jan 103731.25Inv#082 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 731.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7351 | 20201209-23 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 16 | Dynamic | 103.54 | 0 |  |  | 2208.8 | 287.144 | 2495.944 | 2020-12-09 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX loading rock trucks, rock trucks hauling, dozer spreading from C-078 | 5 | C076-C092 | Cook Lake | 0 | 44179 |  | 50 | 44180 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting735120201209-23Rock Truck - 30 Ton- After Jan 10162208.8 | Corbiere and Sons Contracting735120201209-23Rock Truck - 30 Ton- After Jan 10162208.8Inv#082 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 2208.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7351 | 20201209-23 | 53510504 | Access | 0 | Foreman | 95 | 6 | HR |  |  | 95 | 0 | 570 | 74.1 | 644.1 | 2020-12-09 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX loading rock trucks, rock trucks hauling, dozer spreading from C-078 | 5 | C076-C092 | Cook Lake | 0 | 44179 |  | 50 | 44180 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting735120201209-23Foreman6570 | Corbiere and Sons Contracting735120201209-23Foreman6570Inv#082 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 570 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7351 | 20201209-23 | 53510504 | Access | 0 | L.O.A. | 210 | 7 | DAY |  |  |  | 0 | 1470 | 191.1 | 1661.1 | 2020-12-09 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX loading rock trucks, rock trucks hauling, dozer spreading from C-078 | 5 | C076-C092 | Cook Lake | 0 | 44179 |  | 50 | 44180 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting735120201209-23L.O.A.71470 | Corbiere and Sons Contracting735120201209-23L.O.A.71470Inv#082 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1470 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7351 | 20201209-23 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 34.5 | HR |  |  | 75 | 0 | 2587.5 | 336.375 | 2923.875 | 2020-12-09 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX loading rock trucks, rock trucks hauling, dozer spreading from C-078 | 5 | C076-C092 | Cook Lake | 0 | 44179 |  | 50 | 44180 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting735120201209-23Operator - Principle - After Jan 1034.52587.5 | Corbiere and Sons Contracting735120201209-23Operator - Principle - After Jan 1034.52587.5Inv#082 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 2587.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7351 | 20201209-23 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 17.5 | HR |  |  | 70 | 0 | 1225 | 159.25 | 1384.25 | 2020-12-09 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX loading rock trucks, rock trucks hauling, dozer spreading from C-078 | 5 | C076-C092 | Cook Lake | 0 | 44179 |  | 50 | 44180 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting735120201209-23Driver - AZ - After Jan 1017.51225 | Corbiere and Sons Contracting735120201209-23Driver - AZ - After Jan 1017.51225Inv#082 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1225 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7352 | 20201209-24 | 53510511 | Access | 0 | Sander Truck - Hwy- After Jan 10 | 55 | 5 | Dynamic | 41.25 | 0 |  |  | 275 | 35.75 | 310.75 | 2020-12-09 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Sander sanding road between WF5 and WF6. | 5 | C076-C116 | Cook Lake | 0 | 44179 |  | 50 | 44180 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting735220201209-24Sander Truck - Hwy- After Jan 105275 | Corbiere and Sons Contracting735220201209-24Sander Truck - Hwy- After Jan 105275Inv#082 | [5 empty] | 1 | 275 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7352 | 20201209-24 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-12-09 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Sander sanding road between WF5 and WF6. | 5 | C076-C116 | Cook Lake | 0 | 44179 |  | 50 | 44180 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting735220201209-24L.O.A.1210 | Corbiere and Sons Contracting735220201209-24L.O.A.1210Inv#082 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7352 | 20201209-24 | 53510511 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 5.5 | HR |  |  | 70 | 0 | 385 | 50.05 | 435.05 | 2020-12-09 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Sander sanding road between WF5 and WF6. | 5 | C076-C116 | Cook Lake | 0 | 44179 |  | 50 | 44180 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting735220201209-24Driver - AZ - After Jan 105.5385 | Corbiere and Sons Contracting735220201209-24Driver - AZ - After Jan 105.5385Inv#082 | [5 empty] | 1 | 385 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7404 | 20201209-26 | 53510411 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 8 | Dynamic | 95.24 | 0 |  |  | 1015.84 | 132.0592 | 1147.8992 | 2020-12-09 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Graded Nishin for rest of the day. | 4 | C011-C029 | Nishin Creek Road | 0 | 44181 |  | 50 | 44181 | [5 empty] | Wes Seminowich | 04 | Corbiere and Sons Contracting740420201209-26Grader - Cat 12 to 14 or equal- After Jan 1081015.84 | Corbiere and Sons Contracting740420201209-26Grader - Cat 12 to 14 or equal- After Jan 1081015.84Inv#082 | [5 empty] | 1 | 1015.84 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7404 | 20201209-26 | 53510411 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-12-09 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Graded Nishin for rest of the day. | 4 | C011-C029 | Nishin Creek Road | 0 | 44181 |  | 50 | 44181 | [5 empty] | Wes Seminowich | 04 | Corbiere and Sons Contracting740420201209-26Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting740420201209-26Light Truck - Pick up- After Jan 101243.75Inv#082 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7404 | 20201209-26 | 53510411 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-12-09 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Graded Nishin for rest of the day. | 4 | C011-C029 | Nishin Creek Road | 0 | 44181 |  | 50 | 44181 | [5 empty] | Wes Seminowich | 04 | Corbiere and Sons Contracting740420201209-26L.O.A.1210 | Corbiere and Sons Contracting740420201209-26L.O.A.1210Inv#082 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7404 | 20201209-26 | 53510411 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 9 | HR |  |  | 75 | 0 | 675 | 87.75 | 762.75 | 2020-12-09 | 1 | Inv#082 | 44181 | 130 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Graded Nishin for rest of the day. | 4 | C011-C029 | Nishin Creek Road | 0 | 44181 |  | 50 | 44181 | [5 empty] | Wes Seminowich | 04 | Corbiere and Sons Contracting740420201209-26Operator - Principle - After Jan 109675 | Corbiere and Sons Contracting740420201209-26Operator - Principle - After Jan 109675Inv#082 | [5 empty] | 1 | 675 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 808 | 202012-1 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 40 | HR | 22.5 | 0 |  |  | 1200 | 156 | 1356 | 2020-01-05 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Project Supervision | 0 |  |  | 36 | 43839 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting808202012-1Light Truck - Pick up401200 | Corbiere and Sons Contracting808202012-1Light Truck - Pick up401200Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1200 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 808 | 202012-1 | 53520101 | Clearing | 0 | Project Manager | 110 | 12 | HR |  |  |  | 0 | 1320 | 171.6 | 1491.6 | 2020-01-05 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Project Supervision | 0 |  |  | 36 | 43839 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting808202012-1Project Manager121320 | Corbiere and Sons Contracting808202012-1Project Manager121320Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1320 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 808 | 202012-1 | 53520101 | Clearing | 0 | Superintendent | 105 | 12 | HR |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2020-01-05 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Project Supervision | 0 |  |  | 36 | 43839 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting808202012-1Superintendent121260 | Corbiere and Sons Contracting808202012-1Superintendent121260Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 808 | 202012-1 | 53520101 | Clearing | 0 | Project Coordinator | 80 | 12 | HR |  |  |  | 0 | 960 | 124.8 | 1084.8 | 2020-01-05 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Project Supervision | 0 |  |  | 36 | 43839 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting808202012-1Project Coordinator12960 | Corbiere and Sons Contracting808202012-1Project Coordinator12960Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 808 | 202012-1 | 53520101 | Clearing | 0 | Project Controls | 70 | 12 | HR |  |  |  | 0 | 840 | 109.2 | 949.2 | 2020-01-05 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Project Supervision | 0 |  |  | 36 | 43839 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting808202012-1Project Controls12840 | Corbiere and Sons Contracting808202012-1Project Controls12840Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 808 | 202012-1 | 53520101 | Clearing | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2020-01-05 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Project Supervision |  |  | Project Supervision | 0 |  |  | 36 | 43839 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting808202012-1L.O.A.4840 | Corbiere and Sons Contracting808202012-1L.O.A.4840Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7363 | 20201210-11 | 53510312 | Access | 0 | Sander Truck - Hwy- After Jan 10 | 55 | 7 | Dynamic | 41.25 | 0 |  |  | 385 | 50.05 | 435.05 | 2020-12-10 | 0 | Inv#090 | 44203 | 136 | 0 | 1 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 15 | Approved | ROW INTERNAL - Sand for Road Maintenance - 3rd Party | 9015 | Sander hauled 4 loads of sand to Gurney Lake Rd. | 3 | B187-B193 | Gurney Lake Road | 0 | 44179 |  | 50 | 44180 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting736320201210-11Sander Truck - Hwy- After Jan 107385 | Corbiere and Sons Contracting736320201210-11Sander Truck - Hwy- After Jan 107385Inv#090 | [5 empty] | 1 | 385 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7363 | 20201210-11 | 53510312 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 7 | HR |  |  | 70 | 0 | 490 | 63.7 | 553.7 | 2020-12-10 | 0 | Inv#090 | 44203 | 136 | 0 | 1 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  | 15 | Approved | ROW INTERNAL - Sand for Road Maintenance - 3rd Party | 9015 | Sander hauled 4 loads of sand to Gurney Lake Rd. | 3 | B187-B193 | Gurney Lake Road | 0 | 44179 |  | 50 | 44180 | [5 empty] | Wes Seminowich | 03 | Corbiere and Sons Contracting736320201210-11Driver - AZ - After Jan 107490 | Corbiere and Sons Contracting736320201210-11Driver - AZ - After Jan 107490Inv#090 | [5 empty] | 1 | 490 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7432 | 20201210-13 | 53510411 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 9 | Dynamic | 95.24 | 0 |  |  | 1142.82 | 148.5666 | 1291.3866 | 2020-12-10 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Nishin access roads and then floated at the end of the day. | 4 | C011-C029 | Nishin Creek Road | 0 | 44183 |  | 50 | 44183 | [5 empty] | Wes Seminowich | 04 | Corbiere and Sons Contracting743220201210-13Grader - Cat 12 to 14 or equal- After Jan 1091142.82 | Corbiere and Sons Contracting743220201210-13Grader - Cat 12 to 14 or equal- After Jan 1091142.82Inv#090 | [5 empty] | 1 | 1142.82 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7432 | 20201210-13 | 53510411 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-12-10 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Nishin access roads and then floated at the end of the day. | 4 | C011-C029 | Nishin Creek Road | 0 | 44183 |  | 50 | 44183 | [5 empty] | Wes Seminowich | 04 | Corbiere and Sons Contracting743220201210-13Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting743220201210-13Light Truck - Pick up- After Jan 101243.75Inv#090 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7432 | 20201210-13 | 53510411 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-12-10 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Nishin access roads and then floated at the end of the day. | 4 | C011-C029 | Nishin Creek Road | 0 | 44183 |  | 50 | 44183 | [5 empty] | Wes Seminowich | 04 | Corbiere and Sons Contracting743220201210-13L.O.A.1210 | Corbiere and Sons Contracting743220201210-13L.O.A.1210Inv#090 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7432 | 20201210-13 | 53510411 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 9.5 | HR |  |  | 75 | 0 | 712.5 | 92.625 | 805.125 | 2020-12-10 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Nishin access roads and then floated at the end of the day. | 4 | C011-C029 | Nishin Creek Road | 0 | 44183 |  | 50 | 44183 | [5 empty] | Wes Seminowich | 04 | Corbiere and Sons Contracting743220201210-13Operator - Principle - After Jan 109.5712.5 | Corbiere and Sons Contracting743220201210-13Operator - Principle - After Jan 109.5712.5Inv#090 | [5 empty] | 1 | 712.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7436 | 20201210-17 | 53510511 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10.5 | Dynamic | 103.84 | 0 |  |  | 1453.725 | 188.9843 | 1642.7093 | 2020-12-10 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance all day in Pays Plat. | 5 | C031-C049 | Pays Plat River | 0 | 44183 |  | 50 | 44183 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting743620201210-17Excavator - 30 ton- After Jan 1010.51453.725 | Corbiere and Sons Contracting743620201210-17Excavator - 30 ton- After Jan 1010.51453.725Inv#090 | [5 empty] | 1 | 1453.725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7436 | 20201210-17 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-12-10 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance all day in Pays Plat. | 5 | C031-C049 | Pays Plat River | 0 | 44183 |  | 50 | 44183 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting743620201210-17L.O.A.1210 | Corbiere and Sons Contracting743620201210-17L.O.A.1210Inv#090 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7436 | 20201210-17 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-12-10 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Road maintenance all day in Pays Plat. | 5 | C031-C049 | Pays Plat River | 0 | 44183 |  | 50 | 44183 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting743620201210-17Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting743620201210-17Operator - Principle - After Jan 1011.5862.5Inv#090 | [5 empty] | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7437 | 20201210-18 | 53510512 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 4.5 | Dynamic | 110.22 | 0 |  |  | 661.32 | 85.9716 | 747.2916 | 2020-12-10 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working on widening shoeflies from C-065 - C-069 | 5 | C050-C069 | Antler Lake | 0 | 44183 |  | 50 | 44183 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting743720201210-18Excavator - 36 ton- After Jan 104.5661.32 | Corbiere and Sons Contracting743720201210-18Excavator - 36 ton- After Jan 104.5661.32Inv#090 | [5 empty] | 1 | 661.32 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7437 | 20201210-18 | 53510512 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 4.5 | HR | 9.16 | 0 |  |  | 54.945 | 7.1429 | 62.0879 | 2020-12-10 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working on widening shoeflies from C-065 - C-069 | 5 | C050-C069 | Antler Lake | 0 | 44183 |  | 50 | 44183 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting743720201210-18Excavator Thumb - 30 - 50 ton- After Jan 104.554.945 | Corbiere and Sons Contracting743720201210-18Excavator Thumb - 30 - 50 ton- After Jan 104.554.945Inv#090 | [5 empty] | 1 | 54.945 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7437 | 20201210-18 | 53510512 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-12-10 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working on widening shoeflies from C-065 - C-069 | 5 | C050-C069 | Antler Lake | 0 | 44183 |  | 50 | 44183 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting743720201210-18Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting743720201210-18Light Truck - Pick up- After Jan 101243.75Inv#090 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7437 | 20201210-18 | 53510512 | Access | 0 | Foreman | 95 | 2 | HR |  |  | 95 | 0 | 190 | 24.7 | 214.7 | 2020-12-10 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working on widening shoeflies from C-065 - C-069 | 5 | C050-C069 | Antler Lake | 0 | 44183 |  | 50 | 44183 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting743720201210-18Foreman2190 | Corbiere and Sons Contracting743720201210-18Foreman2190Inv#090 | [5 empty] | 1 | 190 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7437 | 20201210-18 | 53510512 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-12-10 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working on widening shoeflies from C-065 - C-069 | 5 | C050-C069 | Antler Lake | 0 | 44183 |  | 50 | 44183 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting743720201210-18L.O.A.1210 | Corbiere and Sons Contracting743720201210-18L.O.A.1210Inv#090 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7437 | 20201210-18 | 53510512 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5 | HR |  |  | 75 | 0 | 375 | 48.75 | 423.75 | 2020-12-10 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working on widening shoeflies from C-065 - C-069 | 5 | C050-C069 | Antler Lake | 0 | 44183 |  | 50 | 44183 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting743720201210-18Operator - Principle - After Jan 105375 | Corbiere and Sons Contracting743720201210-18Operator - Principle - After Jan 105375Inv#090 | [5 empty] | 1 | 375 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7438 | 20201210-19 | 53510504 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 6.5 | Dynamic | 98.61 | 0 |  |  | 854.62 | 111.1006 | 965.7206 | 2020-12-10 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks, rock trucks hauling, dozer pushing gravel from C-070 | 5 | C070-C075 | White Sand | 0 | 44183 |  | 50 | 44183 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting743820201210-19Dozer D6 or equal- After Jan 106.5854.62 | Corbiere and Sons Contracting743820201210-19Dozer D6 or equal- After Jan 106.5854.62Inv#090 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 854.62 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7438 | 20201210-19 | 53510504 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 8 | Dynamic | 103.84 | 0 |  |  | 1107.6 | 143.988 | 1251.588 | 2020-12-10 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks, rock trucks hauling, dozer pushing gravel from C-070 | 5 | C070-C075 | White Sand | 0 | 44183 |  | 50 | 44183 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting743820201210-19Excavator - 30 ton- After Jan 1081107.6 | Corbiere and Sons Contracting743820201210-19Excavator - 30 ton- After Jan 1081107.6Inv#090 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1107.6 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7438 | 20201210-19 | 53510504 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 8 | HR | 9.16 | 0 |  |  | 97.68 | 12.6984 | 110.3784 | 2020-12-10 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks, rock trucks hauling, dozer pushing gravel from C-070 | 5 | C070-C075 | White Sand | 0 | 44183 |  | 50 | 44183 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting743820201210-19Excavator Thumb - 30 - 50 ton- After Jan 10897.68 | Corbiere and Sons Contracting743820201210-19Excavator Thumb - 30 - 50 ton- After Jan 10897.68Inv#090 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 97.68 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7438 | 20201210-19 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-12-10 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks, rock trucks hauling, dozer pushing gravel from C-070 | 5 | C070-C075 | White Sand | 0 | 44183 |  | 50 | 44183 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting743820201210-19Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting743820201210-19Light Truck - Pick up- After Jan 102487.5Inv#090 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7438 | 20201210-19 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 16 | Dynamic | 103.54 | 0 |  |  | 2208.8 | 287.144 | 2495.944 | 2020-12-10 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks, rock trucks hauling, dozer pushing gravel from C-070 | 5 | C070-C075 | White Sand | 0 | 44183 |  | 50 | 44183 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting743820201210-19Rock Truck - 30 Ton- After Jan 10162208.8 | Corbiere and Sons Contracting743820201210-19Rock Truck - 30 Ton- After Jan 10162208.8Inv#090 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 2208.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7438 | 20201210-19 | 53510504 | Access | 0 | Foreman | 95 | 4 | HR |  |  | 95 | 0 | 380 | 49.4 | 429.4 | 2020-12-10 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks, rock trucks hauling, dozer pushing gravel from C-070 | 5 | C070-C075 | White Sand | 0 | 44183 |  | 50 | 44183 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting743820201210-19Foreman4380 | Corbiere and Sons Contracting743820201210-19Foreman4380Inv#090 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7438 | 20201210-19 | 53510504 | Access | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2020-12-10 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks, rock trucks hauling, dozer pushing gravel from C-070 | 5 | C070-C075 | White Sand | 0 | 44183 |  | 50 | 44183 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting743820201210-19L.O.A.51050 | Corbiere and Sons Contracting743820201210-19L.O.A.51050Inv#090 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7438 | 20201210-19 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 15.5 | HR |  |  | 75 | 0 | 1162.5 | 151.125 | 1313.625 | 2020-12-10 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks, rock trucks hauling, dozer pushing gravel from C-070 | 5 | C070-C075 | White Sand | 0 | 44183 |  | 50 | 44183 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting743820201210-19Operator - Principle - After Jan 1015.51162.5 | Corbiere and Sons Contracting743820201210-19Operator - Principle - After Jan 1015.51162.5Inv#090 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1162.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7438 | 20201210-19 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 18 | HR |  |  | 70 | 0 | 1260 | 163.8 | 1423.8 | 2020-12-10 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator loading rock trucks, rock trucks hauling, dozer pushing gravel from C-070 | 5 | C070-C075 | White Sand | 0 | 44183 |  | 50 | 44183 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting743820201210-19Driver - AZ - After Jan 10181260 | Corbiere and Sons Contracting743820201210-19Driver - AZ - After Jan 10181260Inv#090 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7439 | 20201210-20 | 53510503 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 2.5 | Dynamic | 103.84 | 0 |  |  | 346.125 | 44.9963 | 391.1212 | 2020-12-10 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator putting down corduroy from C-075 | 5 | C070-C075 | White Sand | 0 | 44183 |  | 50 | 44183 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting743920201210-20Excavator - 30 ton- After Jan 102.5346.125 | Corbiere and Sons Contracting743920201210-20Excavator - 30 ton- After Jan 102.5346.125Inv#090 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 346.125 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7439 | 20201210-20 | 53510503 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 2.5 | HR | 9.16 | 0 |  |  | 30.525 | 3.9682 | 34.4933 | 2020-12-10 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator putting down corduroy from C-075 | 5 | C070-C075 | White Sand | 0 | 44183 |  | 50 | 44183 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting743920201210-20Excavator Thumb - 30 - 50 ton- After Jan 102.530.525 | Corbiere and Sons Contracting743920201210-20Excavator Thumb - 30 - 50 ton- After Jan 102.530.525Inv#090 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 30.525 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7439 | 20201210-20 | 53510503 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-12-10 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator putting down corduroy from C-075 | 5 | C070-C075 | White Sand | 0 | 44183 |  | 50 | 44183 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting743920201210-20Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting743920201210-20Light Truck - Pick up- After Jan 101243.75Inv#090 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7439 | 20201210-20 | 53510503 | Access | 0 | Foreman | 95 | 2 | HR |  |  | 95 | 0 | 190 | 24.7 | 214.7 | 2020-12-10 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator putting down corduroy from C-075 | 5 | C070-C075 | White Sand | 0 | 44183 |  | 50 | 44183 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting743920201210-20Foreman2190 | Corbiere and Sons Contracting743920201210-20Foreman2190Inv#090 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 190 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7439 | 20201210-20 | 53510503 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 3 | HR |  |  | 75 | 0 | 225 | 29.25 | 254.25 | 2020-12-10 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Excavator putting down corduroy from C-075 | 5 | C070-C075 | White Sand | 0 | 44183 |  | 50 | 44183 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting743920201210-20Operator - Principle - After Jan 103225 | Corbiere and Sons Contracting743920201210-20Operator - Principle - After Jan 103225Inv#090 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 225 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7440 | 20201210-21 | 53510504 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 6.5 | Dynamic | 98.61 | 0 |  |  | 854.62 | 111.1006 | 965.7206 | 2020-12-10 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jordan and Darrel loading rock trucks, Chris and Dawson hauling gravel, Dwayne spreading gravel from C-078, Dustin capping road from C-078, Gary capping road from C-115. | 5 | C076-C116 | Cook Lake | 0 | 44183 |  | 50 | 44183 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting744020201210-21Dozer D6 or equal- After Jan 106.5854.62 | Corbiere and Sons Contracting744020201210-21Dozer D6 or equal- After Jan 106.5854.62Inv#090 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 854.62 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7440 | 20201210-21 | 53510504 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 6 | Dynamic | 103.84 | 0 |  |  | 830.7 | 107.991 | 938.691 | 2020-12-10 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jordan and Darrel loading rock trucks, Chris and Dawson hauling gravel, Dwayne spreading gravel from C-078, Dustin capping road from C-078, Gary capping road from C-115. | 5 | C076-C116 | Cook Lake | 0 | 44183 |  | 50 | 44183 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting744020201210-21Excavator - 30 ton- After Jan 106830.7 | Corbiere and Sons Contracting744020201210-21Excavator - 30 ton- After Jan 106830.7Inv#090 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 830.7 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7440 | 20201210-21 | 53510504 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 14.5 | Dynamic | 110.22 | 0 |  |  | 2130.92 | 277.0196 | 2407.9396 | 2020-12-10 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jordan and Darrel loading rock trucks, Chris and Dawson hauling gravel, Dwayne spreading gravel from C-078, Dustin capping road from C-078, Gary capping road from C-115. | 5 | C076-C116 | Cook Lake | 0 | 44183 |  | 50 | 44183 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting744020201210-21Excavator - 36 ton- After Jan 1014.52130.92 | Corbiere and Sons Contracting744020201210-21Excavator - 36 ton- After Jan 1014.52130.92Inv#090 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 2130.92 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7440 | 20201210-21 | 53510504 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 6 | HR | 9.16 | 0 |  |  | 73.26 | 9.5238 | 82.7838 | 2020-12-10 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jordan and Darrel loading rock trucks, Chris and Dawson hauling gravel, Dwayne spreading gravel from C-078, Dustin capping road from C-078, Gary capping road from C-115. | 5 | C076-C116 | Cook Lake | 0 | 44183 |  | 50 | 44183 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting744020201210-21Excavator Thumb - 30 - 50 ton- After Jan 10673.26 | Corbiere and Sons Contracting744020201210-21Excavator Thumb - 30 - 50 ton- After Jan 10673.26Inv#090 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 73.26 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7440 | 20201210-21 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2020-12-10 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jordan and Darrel loading rock trucks, Chris and Dawson hauling gravel, Dwayne spreading gravel from C-078, Dustin capping road from C-078, Gary capping road from C-115. | 5 | C076-C116 | Cook Lake | 0 | 44183 |  | 50 | 44183 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting744020201210-21Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting744020201210-21Light Truck - Pick up- After Jan 103731.25Inv#090 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 731.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7440 | 20201210-21 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 15.5 | Dynamic | 103.54 | 0 |  |  | 2139.775 | 278.1707 | 2417.9457 | 2020-12-10 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jordan and Darrel loading rock trucks, Chris and Dawson hauling gravel, Dwayne spreading gravel from C-078, Dustin capping road from C-078, Gary capping road from C-115. | 5 | C076-C116 | Cook Lake | 0 | 44183 |  | 50 | 44183 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting744020201210-21Rock Truck - 30 Ton- After Jan 1015.52139.775 | Corbiere and Sons Contracting744020201210-21Rock Truck - 30 Ton- After Jan 1015.52139.775Inv#090 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 2139.775 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7440 | 20201210-21 | 53510504 | Access | 0 | Foreman | 95 | 4 | HR |  |  | 95 | 0 | 380 | 49.4 | 429.4 | 2020-12-10 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jordan and Darrel loading rock trucks, Chris and Dawson hauling gravel, Dwayne spreading gravel from C-078, Dustin capping road from C-078, Gary capping road from C-115. | 5 | C076-C116 | Cook Lake | 0 | 44183 |  | 50 | 44183 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting744020201210-21Foreman4380 | Corbiere and Sons Contracting744020201210-21Foreman4380Inv#090 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7440 | 20201210-21 | 53510504 | Access | 0 | L.O.A. | 210 | 7 | DAY |  |  |  | 0 | 1470 | 191.1 | 1661.1 | 2020-12-10 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jordan and Darrel loading rock trucks, Chris and Dawson hauling gravel, Dwayne spreading gravel from C-078, Dustin capping road from C-078, Gary capping road from C-115. | 5 | C076-C116 | Cook Lake | 0 | 44183 |  | 50 | 44183 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting744020201210-21L.O.A.71470 | Corbiere and Sons Contracting744020201210-21L.O.A.71470Inv#090 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1470 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7440 | 20201210-21 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 28.5 | HR |  |  | 75 | 0 | 2137.5 | 277.875 | 2415.375 | 2020-12-10 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jordan and Darrel loading rock trucks, Chris and Dawson hauling gravel, Dwayne spreading gravel from C-078, Dustin capping road from C-078, Gary capping road from C-115. | 5 | C076-C116 | Cook Lake | 0 | 44183 |  | 50 | 44183 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting744020201210-21Operator - Principle - After Jan 1028.52137.5 | Corbiere and Sons Contracting744020201210-21Operator - Principle - After Jan 1028.52137.5Inv#090 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 2137.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7440 | 20201210-21 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 17 | HR |  |  | 70 | 0 | 1190 | 154.7 | 1344.7 | 2020-12-10 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jordan and Darrel loading rock trucks, Chris and Dawson hauling gravel, Dwayne spreading gravel from C-078, Dustin capping road from C-078, Gary capping road from C-115. | 5 | C076-C116 | Cook Lake | 0 | 44183 |  | 50 | 44183 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting744020201210-21Driver - AZ - After Jan 10171190 | Corbiere and Sons Contracting744020201210-21Driver - AZ - After Jan 10171190Inv#090 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1190 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7441 | 20201210-22 | 53510502 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 4.5 | Dynamic | 103.84 | 0 |  |  | 623.025 | 80.9933 | 704.0182 | 2020-12-10 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jordan moving road from C-111, Dwayne built a trunaround at C-076. | 5 | C076-C116 | Cook Lake | 0 | 44183 |  | 50 | 44183 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting744120201210-22Excavator - 30 ton- After Jan 104.5623.025 | Corbiere and Sons Contracting744120201210-22Excavator - 30 ton- After Jan 104.5623.025Inv#090 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 623.025 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7441 | 20201210-22 | 53510502 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 1.5 | Dynamic | 110.22 | 0 |  |  | 220.44 | 28.6572 | 249.0972 | 2020-12-10 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jordan moving road from C-111, Dwayne built a trunaround at C-076. | 5 | C076-C116 | Cook Lake | 0 | 44183 |  | 50 | 44183 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting744120201210-22Excavator - 36 ton- After Jan 101.5220.44 | Corbiere and Sons Contracting744120201210-22Excavator - 36 ton- After Jan 101.5220.44Inv#090 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 220.44 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7441 | 20201210-22 | 53510502 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 4.5 | HR | 9.16 | 0 |  |  | 54.945 | 7.1429 | 62.0879 | 2020-12-10 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jordan moving road from C-111, Dwayne built a trunaround at C-076. | 5 | C076-C116 | Cook Lake | 0 | 44183 |  | 50 | 44183 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting744120201210-22Excavator Thumb - 30 - 50 ton- After Jan 104.554.945 | Corbiere and Sons Contracting744120201210-22Excavator Thumb - 30 - 50 ton- After Jan 104.554.945Inv#090 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 54.945 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7441 | 20201210-22 | 53510502 | Access | 0 | Foreman | 95 | 2 | HR |  |  | 95 | 0 | 190 | 24.7 | 214.7 | 2020-12-10 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jordan moving road from C-111, Dwayne built a trunaround at C-076. | 5 | C076-C116 | Cook Lake | 0 | 44183 |  | 50 | 44183 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting744120201210-22Foreman2190 | Corbiere and Sons Contracting744120201210-22Foreman2190Inv#090 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 190 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7441 | 20201210-22 | 53510502 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 7 | HR |  |  | 75 | 0 | 525 | 68.25 | 593.25 | 2020-12-10 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Jordan moving road from C-111, Dwayne built a trunaround at C-076. | 5 | C076-C116 | Cook Lake | 0 | 44183 |  | 50 | 44183 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting744120201210-22Operator - Principle - After Jan 107525 | Corbiere and Sons Contracting744120201210-22Operator - Principle - After Jan 107525Inv#090 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 525 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7442 | 20201210-23 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 6 | Dynamic | 95.24 | 0 |  |  | 761.88 | 99.0444 | 860.9244 | 2020-12-10 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Cole ran grader for 6 hours on Cooks. | 5 | C076-C116 | Cook Lake | 0 | 44183 |  | 50 | 44183 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting744220201210-23Grader - Cat 12 to 14 or equal- After Jan 106761.88 | Corbiere and Sons Contracting744220201210-23Grader - Cat 12 to 14 or equal- After Jan 106761.88Inv#090 | [5 empty] | 1 | 761.88 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7442 | 20201210-23 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-12-10 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Cole ran grader for 6 hours on Cooks. | 5 | C076-C116 | Cook Lake | 0 | 44183 |  | 50 | 44183 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting744220201210-23Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting744220201210-23Light Truck - Pick up- After Jan 101243.75Inv#090 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7442 | 20201210-23 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-12-10 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Cole ran grader for 6 hours on Cooks. | 5 | C076-C116 | Cook Lake | 0 | 44183 |  | 50 | 44183 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting744220201210-23L.O.A.1210 | Corbiere and Sons Contracting744220201210-23L.O.A.1210Inv#090 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7442 | 20201210-23 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 75 | 0 | 450 | 58.5 | 508.5 | 2020-12-10 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Cole ran grader for 6 hours on Cooks. | 5 | C076-C116 | Cook Lake | 0 | 44183 |  | 50 | 44183 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting744220201210-23Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting744220201210-23Operator - Principle - After Jan 106450Inv#090 | [5 empty] | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7359 | 20201210-7 | 53510412 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 7 | Dynamic | 98.61 | 0 |  |  | 920.36 | 119.6468 | 1040.0068 | 2020-12-10 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | DZ-05 cleared snow and ice from Gurney to Little Gravel Rd. | 4 | B194-B203 | Little Gravel River Road | 0 | 44179 |  | 50 | 44180 | [5 empty] | Wes Seminowich | 04 | Corbiere and Sons Contracting735920201210-7Dozer D6 or equal- After Jan 107920.36 | Corbiere and Sons Contracting735920201210-7Dozer D6 or equal- After Jan 107920.36Inv#090 | [5 empty] | 1 | 920.36 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7359 | 20201210-7 | 53510412 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-12-10 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | DZ-05 cleared snow and ice from Gurney to Little Gravel Rd. | 4 | B194-B203 | Little Gravel River Road | 0 | 44179 |  | 50 | 44180 | [5 empty] | Wes Seminowich | 04 | Corbiere and Sons Contracting735920201210-7Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting735920201210-7Light Truck - Pick up- After Jan 101243.75Inv#090 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7359 | 20201210-7 | 53510412 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 8 | HR |  |  | 75 | 0 | 600 | 78 | 678 | 2020-12-10 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | DZ-05 cleared snow and ice from Gurney to Little Gravel Rd. | 4 | B194-B203 | Little Gravel River Road | 0 | 44179 |  | 50 | 44180 | [5 empty] | Wes Seminowich | 04 | Corbiere and Sons Contracting735920201210-7Operator - Principle - After Jan 108600 | Corbiere and Sons Contracting735920201210-7Operator - Principle - After Jan 108600Inv#090 | [5 empty] | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7447 | 20201211-12 | 53510511 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 4 | Dynamic | 103.84 | 0 |  |  | 553.8 | 71.994 | 625.794 | 2020-12-11 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader grading Pays Plat East and then was floated to Antler to continue grading. Excavator doing road maintenance. | 5 | C031-C049 | Pays Plat River | 0 | 44183 |  | 50 | 44183 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting744720201211-12Excavator - 30 ton- After Jan 104553.8 | Corbiere and Sons Contracting744720201211-12Excavator - 30 ton- After Jan 104553.8Inv#090 | [5 empty] | 1 | 553.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7447 | 20201211-12 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 6 | Dynamic | 95.24 | 0 |  |  | 761.88 | 99.0444 | 860.9244 | 2020-12-11 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader grading Pays Plat East and then was floated to Antler to continue grading. Excavator doing road maintenance. | 5 | C031-C049 | Pays Plat River | 0 | 44183 |  | 50 | 44183 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting744720201211-12Grader - Cat 12 to 14 or equal- After Jan 106761.88 | Corbiere and Sons Contracting744720201211-12Grader - Cat 12 to 14 or equal- After Jan 106761.88Inv#090 | [5 empty] | 1 | 761.88 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7447 | 20201211-12 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-12-11 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader grading Pays Plat East and then was floated to Antler to continue grading. Excavator doing road maintenance. | 5 | C031-C049 | Pays Plat River | 0 | 44183 |  | 50 | 44183 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting744720201211-12Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting744720201211-12Light Truck - Pick up- After Jan 101243.75Inv#090 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7447 | 20201211-12 | 53510511 | Access | 0 | Foreman | 95 | 2 | HR |  |  | 95 | 0 | 190 | 24.7 | 214.7 | 2020-12-11 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader grading Pays Plat East and then was floated to Antler to continue grading. Excavator doing road maintenance. | 5 | C031-C049 | Pays Plat River | 0 | 44183 |  | 50 | 44183 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting744720201211-12Foreman2190 | Corbiere and Sons Contracting744720201211-12Foreman2190Inv#090 | [5 empty] | 1 | 190 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7447 | 20201211-12 | 53510511 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-12-11 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader grading Pays Plat East and then was floated to Antler to continue grading. Excavator doing road maintenance. | 5 | C031-C049 | Pays Plat River | 0 | 44183 |  | 50 | 44183 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting744720201211-12L.O.A.2420 | Corbiere and Sons Contracting744720201211-12L.O.A.2420Inv#090 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7447 | 20201211-12 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 10.5 | HR |  |  | 75 | 0 | 787.5 | 102.375 | 889.875 | 2020-12-11 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader grading Pays Plat East and then was floated to Antler to continue grading. Excavator doing road maintenance. | 5 | C031-C049 | Pays Plat River | 0 | 44183 |  | 50 | 44183 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting744720201211-12Operator - Principle - After Jan 1010.5787.5 | Corbiere and Sons Contracting744720201211-12Operator - Principle - After Jan 1010.5787.5Inv#090 | [5 empty] | 1 | 787.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7448 | 20201211-13 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 4 | Dynamic | 95.24 | 0 |  |  | 507.92 | 66.0296 | 573.9496 | 2020-12-11 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Greg floated to this location in the afternoon and started grading access roads. | 5 | C050-C069 | Antler Lake | 0 | 44183 |  | 50 | 44183 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting744820201211-13Grader - Cat 12 to 14 or equal- After Jan 104507.92 | Corbiere and Sons Contracting744820201211-13Grader - Cat 12 to 14 or equal- After Jan 104507.92Inv#090 | [5 empty] | 1 | 507.92 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7448 | 20201211-13 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 4 | HR |  |  | 75 | 0 | 300 | 39 | 339 | 2020-12-11 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Greg floated to this location in the afternoon and started grading access roads. | 5 | C050-C069 | Antler Lake | 0 | 44183 |  | 50 | 44183 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting744820201211-13Operator - Principle - After Jan 104300 | Corbiere and Sons Contracting744820201211-13Operator - Principle - After Jan 104300Inv#090 | [5 empty] | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7450 | 20201211-15 | 53510503 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 9.5 | Dynamic | 103.84 | 0 |  |  | 1315.275 | 170.9857 | 1486.2607 | 2020-12-11 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ron and Blade spent 3 hours working with corduroy and gravel from C-075 (night shift)Jesse loading trees and placing corduroy, Joe on rock truck hauling and unloading trees | 5 | C070-C075 | White Sand | 0 | 44183 |  | 50 | 44183 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting745020201211-15Excavator - 30 ton- After Jan 109.51315.275 | Corbiere and Sons Contracting745020201211-15Excavator - 30 ton- After Jan 109.51315.275Inv#090 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 1315.275 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7450 | 20201211-15 | 53510503 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 9.5 | HR | 9.16 | 0 |  |  | 115.995 | 15.0793 | 131.0744 | 2020-12-11 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ron and Blade spent 3 hours working with corduroy and gravel from C-075 (night shift)Jesse loading trees and placing corduroy, Joe on rock truck hauling and unloading trees | 5 | C070-C075 | White Sand | 0 | 44183 |  | 50 | 44183 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting745020201211-15Excavator Thumb - 30 - 50 ton- After Jan 109.5115.995 | Corbiere and Sons Contracting745020201211-15Excavator Thumb - 30 - 50 ton- After Jan 109.5115.995Inv#090 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 115.995 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7450 | 20201211-15 | 53510503 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2020-12-11 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ron and Blade spent 3 hours working with corduroy and gravel from C-075 (night shift)Jesse loading trees and placing corduroy, Joe on rock truck hauling and unloading trees | 5 | C070-C075 | White Sand | 0 | 44183 |  | 50 | 44183 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting745020201211-15Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting745020201211-15Light Truck - Pick up- After Jan 103731.25Inv#090 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 731.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7450 | 20201211-15 | 53510503 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 8 | Dynamic | 103.54 | 0 |  |  | 1104.4 | 143.572 | 1247.972 | 2020-12-11 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ron and Blade spent 3 hours working with corduroy and gravel from C-075 (night shift)Jesse loading trees and placing corduroy, Joe on rock truck hauling and unloading trees | 5 | C070-C075 | White Sand | 0 | 44183 |  | 50 | 44183 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting745020201211-15Rock Truck - 30 Ton- After Jan 1081104.4 | Corbiere and Sons Contracting745020201211-15Rock Truck - 30 Ton- After Jan 1081104.4Inv#090 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 1104.4 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7450 | 20201211-15 | 53510503 | Access | 0 | Foreman | 95 | 4 | HR |  |  | 95 | 0 | 380 | 49.4 | 429.4 | 2020-12-11 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ron and Blade spent 3 hours working with corduroy and gravel from C-075 (night shift)Jesse loading trees and placing corduroy, Joe on rock truck hauling and unloading trees | 5 | C070-C075 | White Sand | 0 | 44183 |  | 50 | 44183 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting745020201211-15Foreman4380 | Corbiere and Sons Contracting745020201211-15Foreman4380Inv#090 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7450 | 20201211-15 | 53510503 | Access | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2020-12-11 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ron and Blade spent 3 hours working with corduroy and gravel from C-075 (night shift)Jesse loading trees and placing corduroy, Joe on rock truck hauling and unloading trees | 5 | C070-C075 | White Sand | 0 | 44183 |  | 50 | 44183 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting745020201211-15L.O.A.51050 | Corbiere and Sons Contracting745020201211-15L.O.A.51050Inv#090 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7450 | 20201211-15 | 53510503 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 10 | HR |  |  | 75 | 0 | 750 | 97.5 | 847.5 | 2020-12-11 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ron and Blade spent 3 hours working with corduroy and gravel from C-075 (night shift)Jesse loading trees and placing corduroy, Joe on rock truck hauling and unloading trees | 5 | C070-C075 | White Sand | 0 | 44183 |  | 50 | 44183 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting745020201211-15Operator - Principle - After Jan 1010750 | Corbiere and Sons Contracting745020201211-15Operator - Principle - After Jan 1010750Inv#090 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 750 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7450 | 20201211-15 | 53510503 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 9.5 | HR |  |  | 70 | 0 | 665 | 86.45 | 751.45 | 2020-12-11 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ron and Blade spent 3 hours working with corduroy and gravel from C-075 (night shift)Jesse loading trees and placing corduroy, Joe on rock truck hauling and unloading trees | 5 | C070-C075 | White Sand | 0 | 44183 |  | 50 | 44183 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting745020201211-15Driver - AZ - After Jan 109.5665 | Corbiere and Sons Contracting745020201211-15Driver - AZ - After Jan 109.5665Inv#090 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 665 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7450 | 20201211-15 | 53510503 | Access | 0 | Labourer - General - After Jan 10 | 60 | 3 | HR |  |  | 60 | 0 | 180 | 23.4 | 203.4 | 2020-12-11 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Ron and Blade spent 3 hours working with corduroy and gravel from C-075 (night shift)Jesse loading trees and placing corduroy, Joe on rock truck hauling and unloading trees | 5 | C070-C075 | White Sand | 0 | 44183 |  | 50 | 44183 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting745020201211-15Labourer - General - After Jan 103180 | Corbiere and Sons Contracting745020201211-15Labourer - General - After Jan 103180Inv#090 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 180 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7451 | 20201211-16 | 53510511 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 2.5 | Dynamic | 103.84 | 0 |  |  | 346.125 | 44.9963 | 391.1212 | 2020-12-11 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX scraping hills | 5 | C070-C075 | White Sand | 0 | 44183 |  | 50 | 44183 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting745120201211-16Excavator - 30 ton- After Jan 102.5346.125 | Corbiere and Sons Contracting745120201211-16Excavator - 30 ton- After Jan 102.5346.125Inv#090 | [5 empty] | 1 | 346.125 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7451 | 20201211-16 | 53510511 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 2.5 | HR | 9.16 | 0 |  |  | 30.525 | 3.9682 | 34.4933 | 2020-12-11 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX scraping hills | 5 | C070-C075 | White Sand | 0 | 44183 |  | 50 | 44183 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting745120201211-16Excavator Thumb - 30 - 50 ton- After Jan 102.530.525 | Corbiere and Sons Contracting745120201211-16Excavator Thumb - 30 - 50 ton- After Jan 102.530.525Inv#090 | [5 empty] | 1 | 30.525 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7451 | 20201211-16 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 3 | HR |  |  | 75 | 0 | 225 | 29.25 | 254.25 | 2020-12-11 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX scraping hills | 5 | C070-C075 | White Sand | 0 | 44183 |  | 50 | 44183 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting745120201211-16Operator - Principle - After Jan 103225 | Corbiere and Sons Contracting745120201211-16Operator - Principle - After Jan 103225Inv#090 | [5 empty] | 1 | 225 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7453 | 20201211-18 | 53510504 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 5.5 | Dynamic | 98.61 | 0 |  |  | 723.14 | 94.0082 | 817.1482 | 2020-12-11 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer capping road from C-105, Jordan and Cole loading rock trucks for gravel haul, Darrel spreading gravel, Chris and Dawson hauling with rock trucks | 5 | C076-C116 | Cook Lake | 0 | 44183 |  | 50 | 44183 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting745320201211-18Dozer D6 or equal- After Jan 105.5723.14 | Corbiere and Sons Contracting745320201211-18Dozer D6 or equal- After Jan 105.5723.14Inv#090 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 723.14 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7453 | 20201211-18 | 53510504 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 5.5 | Dynamic | 103.84 | 0 |  |  | 761.475 | 98.9917 | 860.4668 | 2020-12-11 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer capping road from C-105, Jordan and Cole loading rock trucks for gravel haul, Darrel spreading gravel, Chris and Dawson hauling with rock trucks | 5 | C076-C116 | Cook Lake | 0 | 44183 |  | 50 | 44183 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting745320201211-18Excavator - 30 ton- After Jan 105.5761.475 | Corbiere and Sons Contracting745320201211-18Excavator - 30 ton- After Jan 105.5761.475Inv#090 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 761.475 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7453 | 20201211-18 | 53510504 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 16.5 | Dynamic | 110.22 | 0 |  |  | 2424.84 | 315.2292 | 2740.0692 | 2020-12-11 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer capping road from C-105, Jordan and Cole loading rock trucks for gravel haul, Darrel spreading gravel, Chris and Dawson hauling with rock trucks | 5 | C076-C116 | Cook Lake | 0 | 44183 |  | 50 | 44183 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting745320201211-18Excavator - 36 ton- After Jan 1016.52424.84 | Corbiere and Sons Contracting745320201211-18Excavator - 36 ton- After Jan 1016.52424.84Inv#090 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 2424.84 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7453 | 20201211-18 | 53510504 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 5.5 | HR | 9.16 | 0 |  |  | 67.155 | 8.7302 | 75.8851 | 2020-12-11 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer capping road from C-105, Jordan and Cole loading rock trucks for gravel haul, Darrel spreading gravel, Chris and Dawson hauling with rock trucks | 5 | C076-C116 | Cook Lake | 0 | 44183 |  | 50 | 44183 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting745320201211-18Excavator Thumb - 30 - 50 ton- After Jan 105.567.155 | Corbiere and Sons Contracting745320201211-18Excavator Thumb - 30 - 50 ton- After Jan 105.567.155Inv#090 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 67.155 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7453 | 20201211-18 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2020-12-11 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer capping road from C-105, Jordan and Cole loading rock trucks for gravel haul, Darrel spreading gravel, Chris and Dawson hauling with rock trucks | 5 | C076-C116 | Cook Lake | 0 | 44183 |  | 50 | 44183 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting745320201211-18Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting745320201211-18Light Truck - Pick up- After Jan 103731.25Inv#090 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 731.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7453 | 20201211-18 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 21 | Dynamic | 103.54 | 0 |  |  | 2899.05 | 376.8765 | 3275.9265 | 2020-12-11 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer capping road from C-105, Jordan and Cole loading rock trucks for gravel haul, Darrel spreading gravel, Chris and Dawson hauling with rock trucks | 5 | C076-C116 | Cook Lake | 0 | 44183 |  | 50 | 44183 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting745320201211-18Rock Truck - 30 Ton- After Jan 10212899.05 | Corbiere and Sons Contracting745320201211-18Rock Truck - 30 Ton- After Jan 10212899.05Inv#090 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 2899.05 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7453 | 20201211-18 | 53510504 | Access | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2020-12-11 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer capping road from C-105, Jordan and Cole loading rock trucks for gravel haul, Darrel spreading gravel, Chris and Dawson hauling with rock trucks | 5 | C076-C116 | Cook Lake | 0 | 44183 |  | 50 | 44183 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting745320201211-18L.O.A.61260 | Corbiere and Sons Contracting745320201211-18L.O.A.61260Inv#090 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7453 | 20201211-18 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 29.5 | HR |  |  | 75 | 0 | 2212.5 | 287.625 | 2500.125 | 2020-12-11 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer capping road from C-105, Jordan and Cole loading rock trucks for gravel haul, Darrel spreading gravel, Chris and Dawson hauling with rock trucks | 5 | C076-C116 | Cook Lake | 0 | 44183 |  | 50 | 44183 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting745320201211-18Operator - Principle - After Jan 1029.52212.5 | Corbiere and Sons Contracting745320201211-18Operator - Principle - After Jan 1029.52212.5Inv#090 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 2212.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7453 | 20201211-18 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 23 | HR |  |  | 70 | 0 | 1610 | 209.3 | 1819.3 | 2020-12-11 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer capping road from C-105, Jordan and Cole loading rock trucks for gravel haul, Darrel spreading gravel, Chris and Dawson hauling with rock trucks | 5 | C076-C116 | Cook Lake | 0 | 44183 |  | 50 | 44183 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting745320201211-18Driver - AZ - After Jan 10231610 | Corbiere and Sons Contracting745320201211-18Driver - AZ - After Jan 10231610Inv#090 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1610 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7454 | 20201211-19 | 53510511 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 3 | Dynamic | 103.84 | 0 |  |  | 415.35 | 53.9955 | 469.3455 | 2020-12-11 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-017 and EX-011 completing winter access maintenance, grader working across access roads. | 5 | C070-C116 | Cook Lake | 0 | 44183 |  | 50 | 44183 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting745420201211-19Excavator - 30 ton- After Jan 103415.35 | Corbiere and Sons Contracting745420201211-19Excavator - 30 ton- After Jan 103415.35Inv#090 | [5 empty] | 1 | 415.35 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7454 | 20201211-19 | 53510511 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 3 | Dynamic | 110.22 | 0 |  |  | 440.88 | 57.3144 | 498.1944 | 2020-12-11 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-017 and EX-011 completing winter access maintenance, grader working across access roads. | 5 | C070-C116 | Cook Lake | 0 | 44183 |  | 50 | 44183 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting745420201211-19Excavator - 36 ton- After Jan 103440.88 | Corbiere and Sons Contracting745420201211-19Excavator - 36 ton- After Jan 103440.88Inv#090 | [5 empty] | 1 | 440.88 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7454 | 20201211-19 | 53510511 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 3 | HR | 9.16 | 0 |  |  | 36.63 | 4.7619 | 41.3919 | 2020-12-11 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-017 and EX-011 completing winter access maintenance, grader working across access roads. | 5 | C070-C116 | Cook Lake | 0 | 44183 |  | 50 | 44183 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting745420201211-19Excavator Thumb - 30 - 50 ton- After Jan 10336.63 | Corbiere and Sons Contracting745420201211-19Excavator Thumb - 30 - 50 ton- After Jan 10336.63Inv#090 | [5 empty] | 1 | 36.63 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7454 | 20201211-19 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10.5 | Dynamic | 95.24 | 0 |  |  | 1333.29 | 173.3277 | 1506.6177 | 2020-12-11 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-017 and EX-011 completing winter access maintenance, grader working across access roads. | 5 | C070-C116 | Cook Lake | 0 | 44183 |  | 50 | 44183 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting745420201211-19Grader - Cat 12 to 14 or equal- After Jan 1010.51333.29 | Corbiere and Sons Contracting745420201211-19Grader - Cat 12 to 14 or equal- After Jan 1010.51333.29Inv#090 | [5 empty] | 1 | 1333.29 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7454 | 20201211-19 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-12-11 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-017 and EX-011 completing winter access maintenance, grader working across access roads. | 5 | C070-C116 | Cook Lake | 0 | 44183 |  | 50 | 44183 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting745420201211-19Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting745420201211-19Light Truck - Pick up- After Jan 101243.75Inv#090 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7454 | 20201211-19 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-12-11 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-017 and EX-011 completing winter access maintenance, grader working across access roads. | 5 | C070-C116 | Cook Lake | 0 | 44183 |  | 50 | 44183 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting745420201211-19L.O.A.1210 | Corbiere and Sons Contracting745420201211-19L.O.A.1210Inv#090 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7454 | 20201211-19 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 17.5 | HR |  |  | 75 | 0 | 1312.5 | 170.625 | 1483.125 | 2020-12-11 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-017 and EX-011 completing winter access maintenance, grader working across access roads. | 5 | C070-C116 | Cook Lake | 0 | 44183 |  | 50 | 44183 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting745420201211-19Operator - Principle - After Jan 1017.51312.5 | Corbiere and Sons Contracting745420201211-19Operator - Principle - After Jan 1017.51312.5Inv#090 | [5 empty] | 1 | 1312.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7444 | 20201211-9 | 53510411 | Access | 0 | Sander Truck - Hwy- After Jan 10 | 55 | 10.5 | Dynamic | 41.25 | 0 |  |  | 577.5 | 75.075 | 652.575 | 2020-12-11 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Roads being sanded across Little Gravel River Rd. | 4 | B194-B210 | Little Gravel River Road | 0 | 44183 |  | 50 | 44183 | [5 empty] | Wes Seminowich | 04 | Corbiere and Sons Contracting744420201211-9Sander Truck - Hwy- After Jan 1010.5577.5 | Corbiere and Sons Contracting744420201211-9Sander Truck - Hwy- After Jan 1010.5577.5Inv#090 | [5 empty] | 1 | 577.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7444 | 20201211-9 | 53510411 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-12-11 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Roads being sanded across Little Gravel River Rd. | 4 | B194-B210 | Little Gravel River Road | 0 | 44183 |  | 50 | 44183 | [5 empty] | Wes Seminowich | 04 | Corbiere and Sons Contracting744420201211-9L.O.A.1210 | Corbiere and Sons Contracting744420201211-9L.O.A.1210Inv#090 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7444 | 20201211-9 | 53510411 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 11.5 | HR |  |  | 70 | 0 | 805 | 104.65 | 909.65 | 2020-12-11 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Roads being sanded across Little Gravel River Rd. | 4 | B194-B210 | Little Gravel River Road | 0 | 44183 |  | 50 | 44183 | [5 empty] | Wes Seminowich | 04 | Corbiere and Sons Contracting744420201211-9Driver - AZ - After Jan 1011.5805 | Corbiere and Sons Contracting744420201211-9Driver - AZ - After Jan 1011.5805Inv#090 | [5 empty] | 1 | 805 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7465 | 20201212-10 | 53510504 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 14 | Dynamic | 110.22 | 0 |  |  | 2057.44 | 267.4672 | 2324.9072 | 2020-12-12 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Labourers delivered and rolled out geo, EX-011 loading rock trucks from C-102, Rock truck hauling, EX-013 spreading gravel | 5 | C076-C116 | Cook Lake | 0 | 44184 |  | 37 | 44200 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting746520201212-10Excavator - 36 ton- After Jan 10142057.44 | Corbiere and Sons Contracting746520201212-10Excavator - 36 ton- After Jan 10142057.44Inv#090 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 2057.44 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7465 | 20201212-10 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-12-12 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Labourers delivered and rolled out geo, EX-011 loading rock trucks from C-102, Rock truck hauling, EX-013 spreading gravel | 5 | C076-C116 | Cook Lake | 0 | 44184 |  | 37 | 44200 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting746520201212-10Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting746520201212-10Light Truck - Pick up- After Jan 102487.5Inv#090 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7465 | 20201212-10 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 10.5 | Dynamic | 103.54 | 0 |  |  | 1449.525 | 188.4383 | 1637.9633 | 2020-12-12 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Labourers delivered and rolled out geo, EX-011 loading rock trucks from C-102, Rock truck hauling, EX-013 spreading gravel | 5 | C076-C116 | Cook Lake | 0 | 44184 |  | 37 | 44200 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting746520201212-10Rock Truck - 30 Ton- After Jan 1010.51449.525 | Corbiere and Sons Contracting746520201212-10Rock Truck - 30 Ton- After Jan 1010.51449.525Inv#090 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1449.525 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7465 | 20201212-10 | 53510504 | Access | 0 | Foreman | 95 | 4 | HR |  |  | 95 | 0 | 380 | 49.4 | 429.4 | 2020-12-12 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Labourers delivered and rolled out geo, EX-011 loading rock trucks from C-102, Rock truck hauling, EX-013 spreading gravel | 5 | C076-C116 | Cook Lake | 0 | 44184 |  | 37 | 44200 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting746520201212-10Foreman4380 | Corbiere and Sons Contracting746520201212-10Foreman4380Inv#090 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7465 | 20201212-10 | 53510504 | Access | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2020-12-12 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Labourers delivered and rolled out geo, EX-011 loading rock trucks from C-102, Rock truck hauling, EX-013 spreading gravel | 5 | C076-C116 | Cook Lake | 0 | 44184 |  | 37 | 44200 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting746520201212-10L.O.A.51050 | Corbiere and Sons Contracting746520201212-10L.O.A.51050Inv#090 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7465 | 20201212-10 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 15.5 | HR |  |  | 75 | 0 | 1162.5 | 151.125 | 1313.625 | 2020-12-12 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Labourers delivered and rolled out geo, EX-011 loading rock trucks from C-102, Rock truck hauling, EX-013 spreading gravel | 5 | C076-C116 | Cook Lake | 0 | 44184 |  | 37 | 44200 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting746520201212-10Operator - Principle - After Jan 1015.51162.5 | Corbiere and Sons Contracting746520201212-10Operator - Principle - After Jan 1015.51162.5Inv#090 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1162.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7465 | 20201212-10 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 11.5 | HR |  |  | 70 | 0 | 805 | 104.65 | 909.65 | 2020-12-12 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Labourers delivered and rolled out geo, EX-011 loading rock trucks from C-102, Rock truck hauling, EX-013 spreading gravel | 5 | C076-C116 | Cook Lake | 0 | 44184 |  | 37 | 44200 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting746520201212-10Driver - AZ - After Jan 1011.5805 | Corbiere and Sons Contracting746520201212-10Driver - AZ - After Jan 1011.5805Inv#090 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 805 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7465 | 20201212-10 | 53510504 | Access | 0 | Labourer - General - After Jan 10 | 60 | 12 | HR |  |  | 60 | 0 | 720 | 93.6 | 813.6 | 2020-12-12 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Labourers delivered and rolled out geo, EX-011 loading rock trucks from C-102, Rock truck hauling, EX-013 spreading gravel | 5 | C076-C116 | Cook Lake | 0 | 44184 |  | 37 | 44200 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting746520201212-10Labourer - General - After Jan 1012720 | Corbiere and Sons Contracting746520201212-10Labourer - General - After Jan 1012720Inv#090 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 720 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7466 | 20201212-11 | 53510511 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10.5 | Dynamic | 98.61 | 0 |  |  | 1380.54 | 179.4702 | 1560.0102 | 2020-12-12 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer working from C-094 - C-097, Grader working across access roads all day, Excavator sanding hill. | 5 | C076-C116 | Cook Lake | 0 | 44184 |  | 37 | 44200 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting746620201212-11Dozer D6 or equal- After Jan 1010.51380.54 | Corbiere and Sons Contracting746620201212-11Dozer D6 or equal- After Jan 1010.51380.54Inv#090 | [5 empty] | 1 | 1380.54 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7466 | 20201212-11 | 53510511 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 3 | Dynamic | 110.22 | 0 |  |  | 440.88 | 57.3144 | 498.1944 | 2020-12-12 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer working from C-094 - C-097, Grader working across access roads all day, Excavator sanding hill. | 5 | C076-C116 | Cook Lake | 0 | 44184 |  | 37 | 44200 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting746620201212-11Excavator - 36 ton- After Jan 103440.88 | Corbiere and Sons Contracting746620201212-11Excavator - 36 ton- After Jan 103440.88Inv#090 | [5 empty] | 1 | 440.88 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7466 | 20201212-11 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10.5 | Dynamic | 95.24 | 0 |  |  | 1333.29 | 173.3277 | 1506.6177 | 2020-12-12 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer working from C-094 - C-097, Grader working across access roads all day, Excavator sanding hill. | 5 | C076-C116 | Cook Lake | 0 | 44184 |  | 37 | 44200 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting746620201212-11Grader - Cat 12 to 14 or equal- After Jan 1010.51333.29 | Corbiere and Sons Contracting746620201212-11Grader - Cat 12 to 14 or equal- After Jan 1010.51333.29Inv#090 | [5 empty] | 1 | 1333.29 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7466 | 20201212-11 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-12-12 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer working from C-094 - C-097, Grader working across access roads all day, Excavator sanding hill. | 5 | C076-C116 | Cook Lake | 0 | 44184 |  | 37 | 44200 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting746620201212-11Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting746620201212-11Light Truck - Pick up- After Jan 101243.75Inv#090 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7466 | 20201212-11 | 53510511 | Access | 0 | Foreman | 95 | 4 | HR |  |  | 95 | 0 | 380 | 49.4 | 429.4 | 2020-12-12 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer working from C-094 - C-097, Grader working across access roads all day, Excavator sanding hill. | 5 | C076-C116 | Cook Lake | 0 | 44184 |  | 37 | 44200 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting746620201212-11Foreman4380 | Corbiere and Sons Contracting746620201212-11Foreman4380Inv#090 | [5 empty] | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7466 | 20201212-11 | 53510511 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-12-12 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer working from C-094 - C-097, Grader working across access roads all day, Excavator sanding hill. | 5 | C076-C116 | Cook Lake | 0 | 44184 |  | 37 | 44200 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting746620201212-11L.O.A.2420 | Corbiere and Sons Contracting746620201212-11L.O.A.2420Inv#090 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7466 | 20201212-11 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 26 | HR |  |  | 75 | 0 | 1950 | 253.5 | 2203.5 | 2020-12-12 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer working from C-094 - C-097, Grader working across access roads all day, Excavator sanding hill. | 5 | C076-C116 | Cook Lake | 0 | 44184 |  | 37 | 44200 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting746620201212-11Operator - Principle - After Jan 10261950 | Corbiere and Sons Contracting746620201212-11Operator - Principle - After Jan 10261950Inv#090 | [5 empty] | 1 | 1950 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7467 | 20201212-12 | 53510512 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 10.5 | Dynamic | 110.22 | 0 |  |  | 1543.08 | 200.6004 | 1743.6804 | 2020-12-12 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Maintenance to road from C-083 | 5 | C076-C092 | Cook Lake | 0 | 44184 |  | 37 | 44200 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting746720201212-12Excavator - 36 ton- After Jan 1010.51543.08 | Corbiere and Sons Contracting746720201212-12Excavator - 36 ton- After Jan 1010.51543.08Inv#090 | [5 empty] | 1 | 1543.08 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7467 | 20201212-12 | 53510512 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-12-12 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Maintenance to road from C-083 | 5 | C076-C092 | Cook Lake | 0 | 44184 |  | 37 | 44200 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting746720201212-12Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting746720201212-12Light Truck - Pick up- After Jan 101243.75Inv#090 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7467 | 20201212-12 | 53510512 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-12-12 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Maintenance to road from C-083 | 5 | C076-C092 | Cook Lake | 0 | 44184 |  | 37 | 44200 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting746720201212-12L.O.A.1210 | Corbiere and Sons Contracting746720201212-12L.O.A.1210Inv#090 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7467 | 20201212-12 | 53510512 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-12-12 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Maintenance to road from C-083 | 5 | C076-C092 | Cook Lake | 0 | 44184 |  | 37 | 44200 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting746720201212-12Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting746720201212-12Operator - Principle - After Jan 1011.5862.5Inv#090 | [5 empty] | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7468 | 20201212-13 | 53510503 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 4.5 | Dynamic | 110.22 | 0 |  |  | 661.32 | 85.9716 | 747.2916 | 2020-12-12 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Putting down corduroy at switchback | 5 | C076-C116 | Cook Lake | 0 | 44184 |  | 37 | 44200 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting746820201212-13Excavator - 36 ton- After Jan 104.5661.32 | Corbiere and Sons Contracting746820201212-13Excavator - 36 ton- After Jan 104.5661.32Inv#090 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 661.32 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7468 | 20201212-13 | 53510503 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-12-12 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Putting down corduroy at switchback | 5 | C076-C116 | Cook Lake | 0 | 44184 |  | 37 | 44200 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting746820201212-13L.O.A.1210 | Corbiere and Sons Contracting746820201212-13L.O.A.1210Inv#090 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7468 | 20201212-13 | 53510503 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5 | HR |  |  | 75 | 0 | 375 | 48.75 | 423.75 | 2020-12-12 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Putting down corduroy at switchback | 5 | C076-C116 | Cook Lake | 0 | 44184 |  | 37 | 44200 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting746820201212-13Operator - Principle - After Jan 105375 | Corbiere and Sons Contracting746820201212-13Operator - Principle - After Jan 105375Inv#090 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 375 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7715 | 20201212-14 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 9 | Dynamic | 95.24 | 0 |  |  | 1142.82 | 148.5666 | 1291.3866 | 2020-12-12 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working across Antler Lake access all day. | 5 | C050-C069 | Antler Lake | 0 | 44203 |  | 36 | 44207 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting771520201212-14Grader - Cat 12 to 14 or equal- After Jan 1091142.82 | Corbiere and Sons Contracting771520201212-14Grader - Cat 12 to 14 or equal- After Jan 1091142.82Inv#095 | [5 empty] | 1 | 1142.82 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7715 | 20201212-14 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-12-12 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working across Antler Lake access all day. | 5 | C050-C069 | Antler Lake | 0 | 44203 |  | 36 | 44207 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting771520201212-14Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting771520201212-14Light Truck - Pick up- After Jan 101243.75Inv#095 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7715 | 20201212-14 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-12-12 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working across Antler Lake access all day. | 5 | C050-C069 | Antler Lake | 0 | 44203 |  | 36 | 44207 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting771520201212-14L.O.A.1210 | Corbiere and Sons Contracting771520201212-14L.O.A.1210Inv#095 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7715 | 20201212-14 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 9.5 | HR |  |  | 75 | 0 | 712.5 | 92.625 | 805.125 | 2020-12-12 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working across Antler Lake access all day. | 5 | C050-C069 | Antler Lake | 0 | 44203 |  | 36 | 44207 | [5 empty] | Mike Lecocq | 05 | Corbiere and Sons Contracting771520201212-14Operator - Principle - After Jan 109.5712.5 | Corbiere and Sons Contracting771520201212-14Operator - Principle - After Jan 109.5712.5Inv#095 | [5 empty] | 1 | 712.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7464 | 20201212-9 | 53510504 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 4 | Dynamic | 98.61 | 0 |  |  | 525.92 | 68.3696 | 594.2896 | 2020-12-12 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel haul and spread happening from C-075. Labourer laying geo. | 5 | C070-C075 | White Sand | 0 | 44184 |  | 37 | 44200 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting746420201212-9Dozer D6 or equal- After Jan 104525.92 | Corbiere and Sons Contracting746420201212-9Dozer D6 or equal- After Jan 104525.92Inv#090 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 525.92 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7464 | 20201212-9 | 53510504 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10.5 | Dynamic | 103.84 | 0 |  |  | 1453.725 | 188.9843 | 1642.7093 | 2020-12-12 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel haul and spread happening from C-075. Labourer laying geo. | 5 | C070-C075 | White Sand | 0 | 44184 |  | 37 | 44200 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting746420201212-9Excavator - 30 ton- After Jan 1010.51453.725 | Corbiere and Sons Contracting746420201212-9Excavator - 30 ton- After Jan 1010.51453.725Inv#090 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1453.725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7464 | 20201212-9 | 53510504 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10.5 | HR | 9.16 | 0 |  |  | 128.205 | 16.6667 | 144.8716 | 2020-12-12 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel haul and spread happening from C-075. Labourer laying geo. | 5 | C070-C075 | White Sand | 0 | 44184 |  | 37 | 44200 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting746420201212-9Excavator Thumb - 30 - 50 ton- After Jan 1010.5128.205 | Corbiere and Sons Contracting746420201212-9Excavator Thumb - 30 - 50 ton- After Jan 1010.5128.205Inv#090 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 128.205 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7464 | 20201212-9 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 3 | DAY | 182.81 | 0 |  |  | 731.25 | 95.0625 | 826.3125 | 2020-12-12 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel haul and spread happening from C-075. Labourer laying geo. | 5 | C070-C075 | White Sand | 0 | 44184 |  | 37 | 44200 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting746420201212-9Light Truck - Pick up- After Jan 103731.25 | Corbiere and Sons Contracting746420201212-9Light Truck - Pick up- After Jan 103731.25Inv#090 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 731.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7464 | 20201212-9 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 13.5 | Dynamic | 103.54 | 0 |  |  | 1863.675 | 242.2777 | 2105.9527 | 2020-12-12 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel haul and spread happening from C-075. Labourer laying geo. | 5 | C070-C075 | White Sand | 0 | 44184 |  | 37 | 44200 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting746420201212-9Rock Truck - 30 Ton- After Jan 1013.51863.675 | Corbiere and Sons Contracting746420201212-9Rock Truck - 30 Ton- After Jan 1013.51863.675Inv#090 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1863.675 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7464 | 20201212-9 | 53510504 | Access | 0 | Foreman | 95 | 4 | HR |  |  | 95 | 0 | 380 | 49.4 | 429.4 | 2020-12-12 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel haul and spread happening from C-075. Labourer laying geo. | 5 | C070-C075 | White Sand | 0 | 44184 |  | 37 | 44200 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting746420201212-9Foreman4380 | Corbiere and Sons Contracting746420201212-9Foreman4380Inv#090 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7464 | 20201212-9 | 53510504 | Access | 0 | L.O.A. | 210 | 6 | DAY |  |  |  | 0 | 1260 | 163.8 | 1423.8 | 2020-12-12 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel haul and spread happening from C-075. Labourer laying geo. | 5 | C070-C075 | White Sand | 0 | 44184 |  | 37 | 44200 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting746420201212-9L.O.A.61260 | Corbiere and Sons Contracting746420201212-9L.O.A.61260Inv#090 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1260 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7464 | 20201212-9 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 16 | HR |  |  | 75 | 0 | 1200 | 156 | 1356 | 2020-12-12 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel haul and spread happening from C-075. Labourer laying geo. | 5 | C070-C075 | White Sand | 0 | 44184 |  | 37 | 44200 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting746420201212-9Operator - Principle - After Jan 10161200 | Corbiere and Sons Contracting746420201212-9Operator - Principle - After Jan 10161200Inv#090 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1200 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7464 | 20201212-9 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 15 | HR |  |  | 70 | 0 | 1050 | 136.5 | 1186.5 | 2020-12-12 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel haul and spread happening from C-075. Labourer laying geo. | 5 | C070-C075 | White Sand | 0 | 44184 |  | 37 | 44200 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting746420201212-9Driver - AZ - After Jan 10151050 | Corbiere and Sons Contracting746420201212-9Driver - AZ - After Jan 10151050Inv#090 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7464 | 20201212-9 | 53510504 | Access | 0 | Labourer - General - After Jan 10 | 60 | 3 | HR |  |  | 60 | 0 | 180 | 23.4 | 203.4 | 2020-12-12 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Gravel haul and spread happening from C-075. Labourer laying geo. | 5 | C070-C075 | White Sand | 0 | 44184 |  | 37 | 44200 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting746420201212-9Labourer - General - After Jan 103180 | Corbiere and Sons Contracting746420201212-9Labourer - General - After Jan 103180Inv#090 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 180 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7480 | 20201213-12 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 8.5 | Dynamic | 95.24 | 0 |  |  | 1079.33 | 140.3129 | 1219.6429 | 2020-12-13 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader floated in and graded all day to C-069 access. | 5 | C050-C069 | Antler Lake | 0 | 44186 |  | 37 | 44200 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting748020201213-12Grader - Cat 12 to 14 or equal- After Jan 108.51079.33 | Corbiere and Sons Contracting748020201213-12Grader - Cat 12 to 14 or equal- After Jan 108.51079.33Inv#090 | [5 empty] | 1 | 1079.33 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7480 | 20201213-12 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-12-13 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader floated in and graded all day to C-069 access. | 5 | C050-C069 | Antler Lake | 0 | 44186 |  | 37 | 44200 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting748020201213-12Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting748020201213-12Light Truck - Pick up- After Jan 101243.75Inv#090 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7480 | 20201213-12 | 53510511 | Access | 0 | Foreman | 95 | 2 | HR |  |  | 95 | 0 | 190 | 24.7 | 214.7 | 2020-12-13 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader floated in and graded all day to C-069 access. | 5 | C050-C069 | Antler Lake | 0 | 44186 |  | 37 | 44200 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting748020201213-12Foreman2190 | Corbiere and Sons Contracting748020201213-12Foreman2190Inv#090 | [5 empty] | 1 | 190 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7480 | 20201213-12 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-12-13 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader floated in and graded all day to C-069 access. | 5 | C050-C069 | Antler Lake | 0 | 44186 |  | 37 | 44200 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting748020201213-12L.O.A.1210 | Corbiere and Sons Contracting748020201213-12L.O.A.1210Inv#090 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7480 | 20201213-12 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 9.5 | HR |  |  | 75 | 0 | 712.5 | 92.625 | 805.125 | 2020-12-13 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader floated in and graded all day to C-069 access. | 5 | C050-C069 | Antler Lake | 0 | 44186 |  | 37 | 44200 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting748020201213-12Operator - Principle - After Jan 109.5712.5 | Corbiere and Sons Contracting748020201213-12Operator - Principle - After Jan 109.5712.5Inv#090 | [5 empty] | 1 | 712.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7481 | 20201213-13 | 53510504 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 10.5 | Dynamic | 103.84 | 0 |  |  | 1453.725 | 188.9843 | 1642.7093 | 2020-12-13 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working on gravel haul and spread from C-075. | 5 | C070-C075 | White Sands | 0 | 44186 |  | 37 | 44200 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting748120201213-13Excavator - 30 ton- After Jan 1010.51453.725 | Corbiere and Sons Contracting748120201213-13Excavator - 30 ton- After Jan 1010.51453.725Inv#090 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1453.725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7481 | 20201213-13 | 53510504 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 10.5 | HR | 9.16 | 0 |  |  | 128.205 | 16.6667 | 144.8716 | 2020-12-13 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working on gravel haul and spread from C-075. | 5 | C070-C075 | White Sands | 0 | 44186 |  | 37 | 44200 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting748120201213-13Excavator Thumb - 30 - 50 ton- After Jan 1010.5128.205 | Corbiere and Sons Contracting748120201213-13Excavator Thumb - 30 - 50 ton- After Jan 1010.5128.205Inv#090 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 128.205 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7481 | 20201213-13 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-12-13 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working on gravel haul and spread from C-075. | 5 | C070-C075 | White Sands | 0 | 44186 |  | 37 | 44200 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting748120201213-13Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting748120201213-13Light Truck - Pick up- After Jan 102487.5Inv#090 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7481 | 20201213-13 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 10.5 | Dynamic | 103.54 | 0 |  |  | 1449.525 | 188.4383 | 1637.9633 | 2020-12-13 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working on gravel haul and spread from C-075. | 5 | C070-C075 | White Sands | 0 | 44186 |  | 37 | 44200 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting748120201213-13Rock Truck - 30 Ton- After Jan 1010.51449.525 | Corbiere and Sons Contracting748120201213-13Rock Truck - 30 Ton- After Jan 1010.51449.525Inv#090 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1449.525 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7481 | 20201213-13 | 53510504 | Access | 0 | Foreman | 95 | 4 | HR |  |  | 95 | 0 | 380 | 49.4 | 429.4 | 2020-12-13 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working on gravel haul and spread from C-075. | 5 | C070-C075 | White Sands | 0 | 44186 |  | 37 | 44200 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting748120201213-13Foreman4380 | Corbiere and Sons Contracting748120201213-13Foreman4380Inv#090 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7481 | 20201213-13 | 53510504 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2020-12-13 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working on gravel haul and spread from C-075. | 5 | C070-C075 | White Sands | 0 | 44186 |  | 37 | 44200 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting748120201213-13L.O.A.3630 | Corbiere and Sons Contracting748120201213-13L.O.A.3630Inv#090 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7481 | 20201213-13 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 23 | HR |  |  | 75 | 0 | 1725 | 224.25 | 1949.25 | 2020-12-13 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Working on gravel haul and spread from C-075. | 5 | C070-C075 | White Sands | 0 | 44186 |  | 37 | 44200 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting748120201213-13Operator - Principle - After Jan 10231725 | Corbiere and Sons Contracting748120201213-13Operator - Principle - After Jan 10231725Inv#090 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1725 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7483 | 20201213-15 | 53510511 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 2 | Dynamic | 110.22 | 0 |  |  | 293.92 | 38.2096 | 332.1296 | 2020-12-13 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Sander truck working across access roads. 350X4 did 2 hours of winter road maintenance. | 5 | C076-C116 | Cook Lake | 0 | 44186 |  | 37 | 44200 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting748320201213-15Excavator - 36 ton- After Jan 102293.92 | Corbiere and Sons Contracting748320201213-15Excavator - 36 ton- After Jan 102293.92Inv#090 | [5 empty] | 1 | 293.92 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7483 | 20201213-15 | 53510511 | Access | 0 | Sander Truck - Hwy- After Jan 10 | 55 | 10.5 | Dynamic | 41.25 | 0 |  |  | 577.5 | 75.075 | 652.575 | 2020-12-13 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Sander truck working across access roads. 350X4 did 2 hours of winter road maintenance. | 5 | C076-C116 | Cook Lake | 0 | 44186 |  | 37 | 44200 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting748320201213-15Sander Truck - Hwy- After Jan 1010.5577.5 | Corbiere and Sons Contracting748320201213-15Sander Truck - Hwy- After Jan 1010.5577.5Inv#090 | [5 empty] | 1 | 577.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7483 | 20201213-15 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-12-13 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Sander truck working across access roads. 350X4 did 2 hours of winter road maintenance. | 5 | C076-C116 | Cook Lake | 0 | 44186 |  | 37 | 44200 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting748320201213-15Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting748320201213-15Light Truck - Pick up- After Jan 101243.75Inv#090 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7483 | 20201213-15 | 53510511 | Access | 0 | Foreman | 95 | 3 | HR |  |  | 95 | 0 | 285 | 37.05 | 322.05 | 2020-12-13 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Sander truck working across access roads. 350X4 did 2 hours of winter road maintenance. | 5 | C076-C116 | Cook Lake | 0 | 44186 |  | 37 | 44200 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting748320201213-15Foreman3285 | Corbiere and Sons Contracting748320201213-15Foreman3285Inv#090 | [5 empty] | 1 | 285 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7483 | 20201213-15 | 53510511 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2020-12-13 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Sander truck working across access roads. 350X4 did 2 hours of winter road maintenance. | 5 | C076-C116 | Cook Lake | 0 | 44186 |  | 37 | 44200 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting748320201213-15L.O.A.3630 | Corbiere and Sons Contracting748320201213-15L.O.A.3630Inv#090 | [5 empty] | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7483 | 20201213-15 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 2 | HR |  |  | 75 | 0 | 150 | 19.5 | 169.5 | 2020-12-13 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Sander truck working across access roads. 350X4 did 2 hours of winter road maintenance. | 5 | C076-C116 | Cook Lake | 0 | 44186 |  | 37 | 44200 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting748320201213-15Operator - Principle - After Jan 102150 | Corbiere and Sons Contracting748320201213-15Operator - Principle - After Jan 102150Inv#090 | [5 empty] | 1 | 150 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7483 | 20201213-15 | 53510511 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 11.5 | HR |  |  | 70 | 0 | 805 | 104.65 | 909.65 | 2020-12-13 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Sander truck working across access roads. 350X4 did 2 hours of winter road maintenance. | 5 | C076-C116 | Cook Lake | 0 | 44186 |  | 37 | 44200 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting748320201213-15Driver - AZ - After Jan 1011.5805 | Corbiere and Sons Contracting748320201213-15Driver - AZ - After Jan 1011.5805Inv#090 | [5 empty] | 1 | 805 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7484 | 20201213-16 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-12-13 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Labourer went to Marathon and picked up rolls of geo and collar for culvert, rock truck capping hill from C-100 | 5 | C093-C116 | Cook Lake | 0 | 44186 |  | 37 | 44200 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting748420201213-16Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting748420201213-16Light Truck - Pick up- After Jan 101243.75Inv#090 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7484 | 20201213-16 | 53510504 | Access | 0 | Light Truck w/ Tandum Trailer- After Jan 10 | 337.5 | 1 | DAY | 253.13 | 0 |  |  | 337.5 | 43.875 | 381.375 | 2020-12-13 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Labourer went to Marathon and picked up rolls of geo and collar for culvert, rock truck capping hill from C-100 | 5 | C093-C116 | Cook Lake | 0 | 44186 |  | 37 | 44200 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting748420201213-16Light Truck w/ Tandum Trailer- After Jan 101337.5 | Corbiere and Sons Contracting748420201213-16Light Truck w/ Tandum Trailer- After Jan 101337.5Inv#090 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 337.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7484 | 20201213-16 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 5 | Dynamic | 103.54 | 0 |  |  | 690.25 | 89.7325 | 779.9825 | 2020-12-13 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Labourer went to Marathon and picked up rolls of geo and collar for culvert, rock truck capping hill from C-100 | 5 | C093-C116 | Cook Lake | 0 | 44186 |  | 37 | 44200 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting748420201213-16Rock Truck - 30 Ton- After Jan 105690.25 | Corbiere and Sons Contracting748420201213-16Rock Truck - 30 Ton- After Jan 105690.25Inv#090 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 690.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7484 | 20201213-16 | 53510504 | Access | 0 | Foreman | 95 | 3 | HR |  |  | 95 | 0 | 285 | 37.05 | 322.05 | 2020-12-13 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Labourer went to Marathon and picked up rolls of geo and collar for culvert, rock truck capping hill from C-100 | 5 | C093-C116 | Cook Lake | 0 | 44186 |  | 37 | 44200 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting748420201213-16Foreman3285 | Corbiere and Sons Contracting748420201213-16Foreman3285Inv#090 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 285 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7484 | 20201213-16 | 53510504 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-12-13 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Labourer went to Marathon and picked up rolls of geo and collar for culvert, rock truck capping hill from C-100 | 5 | C093-C116 | Cook Lake | 0 | 44186 |  | 37 | 44200 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting748420201213-16L.O.A.2420 | Corbiere and Sons Contracting748420201213-16L.O.A.2420Inv#090 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7484 | 20201213-16 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 5 | HR |  |  | 70 | 0 | 350 | 45.5 | 395.5 | 2020-12-13 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Labourer went to Marathon and picked up rolls of geo and collar for culvert, rock truck capping hill from C-100 | 5 | C093-C116 | Cook Lake | 0 | 44186 |  | 37 | 44200 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting748420201213-16Driver - AZ - After Jan 105350 | Corbiere and Sons Contracting748420201213-16Driver - AZ - After Jan 105350Inv#090 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 350 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7484 | 20201213-16 | 53510504 | Access | 0 | Labourer - General - After Jan 10 | 60 | 6 | HR |  |  | 60 | 0 | 360 | 46.8 | 406.8 | 2020-12-13 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Labourer went to Marathon and picked up rolls of geo and collar for culvert, rock truck capping hill from C-100 | 5 | C093-C116 | Cook Lake | 0 | 44186 |  | 37 | 44200 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting748420201213-16Labourer - General - After Jan 106360 | Corbiere and Sons Contracting748420201213-16Labourer - General - After Jan 106360Inv#090 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 360 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7717 | 20201213-17 | 53510411 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10.5 | Dynamic | 95.24 | 0 |  |  | 1333.29 | 173.3277 | 1506.6177 | 2020-12-13 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working from Highway to B-216 | 4 | B211-C001 | Gravel River Road | 0 | 44203 |  | 36 | 44207 | [5 empty] | Mike Lecocq | 04 | Corbiere and Sons Contracting771720201213-17Grader - Cat 12 to 14 or equal- After Jan 1010.51333.29 | Corbiere and Sons Contracting771720201213-17Grader - Cat 12 to 14 or equal- After Jan 1010.51333.29Inv#095 | [5 empty] | 1 | 1333.29 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7717 | 20201213-17 | 53510411 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-12-13 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working from Highway to B-216 | 4 | B211-C001 | Gravel River Road | 0 | 44203 |  | 36 | 44207 | [5 empty] | Mike Lecocq | 04 | Corbiere and Sons Contracting771720201213-17Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting771720201213-17Light Truck - Pick up- After Jan 101243.75Inv#095 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7717 | 20201213-17 | 53510411 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-12-13 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working from Highway to B-216 | 4 | B211-C001 | Gravel River Road | 0 | 44203 |  | 36 | 44207 | [5 empty] | Mike Lecocq | 04 | Corbiere and Sons Contracting771720201213-17L.O.A.1210 | Corbiere and Sons Contracting771720201213-17L.O.A.1210Inv#095 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7717 | 20201213-17 | 53510411 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-12-13 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working from Highway to B-216 | 4 | B211-C001 | Gravel River Road | 0 | 44203 |  | 36 | 44207 | [5 empty] | Mike Lecocq | 04 | Corbiere and Sons Contracting771720201213-17Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting771720201213-17Operator - Principle - After Jan 1011.5862.5Inv#095 | [5 empty] | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7474 | 20201213-6 | 53510312 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 7 | Dynamic | 98.61 | 0 |  |  | 920.36 | 119.6468 | 1040.0068 | 2020-12-13 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | DZ-05 walked out of Gurney and floated over to Blair Lake Rd.Sander hauled 1 load to Gurney Lake for float moves | 3 | B187-B193 | Gurney Lake Road | 0 | 44186 |  | 37 | 44200 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting747420201213-6Dozer D6 or equal- After Jan 107920.36 | Corbiere and Sons Contracting747420201213-6Dozer D6 or equal- After Jan 107920.36Inv#090 | [5 empty] | 1 | 920.36 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7474 | 20201213-6 | 53510312 | Access | 0 | Sander Truck - Hwy- After Jan 10 | 55 | 2 | Dynamic | 41.25 | 0 |  |  | 110 | 14.3 | 124.3 | 2020-12-13 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | DZ-05 walked out of Gurney and floated over to Blair Lake Rd.Sander hauled 1 load to Gurney Lake for float moves | 3 | B187-B193 | Gurney Lake Road | 0 | 44186 |  | 37 | 44200 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting747420201213-6Sander Truck - Hwy- After Jan 102110 | Corbiere and Sons Contracting747420201213-6Sander Truck - Hwy- After Jan 102110Inv#090 | [5 empty] | 1 | 110 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7474 | 20201213-6 | 53510312 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-12-13 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | DZ-05 walked out of Gurney and floated over to Blair Lake Rd.Sander hauled 1 load to Gurney Lake for float moves | 3 | B187-B193 | Gurney Lake Road | 0 | 44186 |  | 37 | 44200 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting747420201213-6Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting747420201213-6Light Truck - Pick up- After Jan 101243.75Inv#090 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7474 | 20201213-6 | 53510312 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 8 | HR |  |  | 75 | 0 | 600 | 78 | 678 | 2020-12-13 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | DZ-05 walked out of Gurney and floated over to Blair Lake Rd.Sander hauled 1 load to Gurney Lake for float moves | 3 | B187-B193 | Gurney Lake Road | 0 | 44186 |  | 37 | 44200 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting747420201213-6Operator - Principle - After Jan 108600 | Corbiere and Sons Contracting747420201213-6Operator - Principle - After Jan 108600Inv#090 | [5 empty] | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7474 | 20201213-6 | 53510312 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 2 | HR |  |  | 70 | 0 | 140 | 18.2 | 158.2 | 2020-12-13 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | DZ-05 walked out of Gurney and floated over to Blair Lake Rd.Sander hauled 1 load to Gurney Lake for float moves | 3 | B187-B193 | Gurney Lake Road | 0 | 44186 |  | 37 | 44200 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting747420201213-6Driver - AZ - After Jan 102140 | Corbiere and Sons Contracting747420201213-6Driver - AZ - After Jan 102140Inv#090 | [5 empty] | 1 | 140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7475 | 20201213-7 | 53510312 | Access | 0 | Sander Truck - Hwy- After Jan 10 | 55 | 4 | Dynamic | 41.25 | 0 |  |  | 220 | 28.6 | 248.6 | 2020-12-13 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Sander hauled 2 loads to Lachance Rd for float moves | 3 | B161-B181 | Lachance Road | 0 | 44186 |  | 37 | 44200 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting747520201213-7Sander Truck - Hwy- After Jan 104220 | Corbiere and Sons Contracting747520201213-7Sander Truck - Hwy- After Jan 104220Inv#090 | [5 empty] | 1 | 220 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7475 | 20201213-7 | 53510312 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 4 | HR |  |  | 70 | 0 | 280 | 36.4 | 316.4 | 2020-12-13 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Sander hauled 2 loads to Lachance Rd for float moves | 3 | B161-B181 | Lachance Road | 0 | 44186 |  | 37 | 44200 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting747520201213-7Driver - AZ - After Jan 104280 | Corbiere and Sons Contracting747520201213-7Driver - AZ - After Jan 104280Inv#090 | [5 empty] | 1 | 280 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7498 | 20201214-14 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 8.5 | Dynamic | 95.24 | 0 |  |  | 1079.33 | 140.3129 | 1219.6429 | 2020-12-14 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Greg on grader worked across access roads all the way to C-048. | 5 | C036-C049 | Pays Plat River | 0 | 44186 |  | 37 | 44200 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting749820201214-14Grader - Cat 12 to 14 or equal- After Jan 108.51079.33 | Corbiere and Sons Contracting749820201214-14Grader - Cat 12 to 14 or equal- After Jan 108.51079.33Inv#090 | [5 empty] | 1 | 1079.33 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7498 | 20201214-14 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-12-14 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Greg on grader worked across access roads all the way to C-048. | 5 | C036-C049 | Pays Plat River | 0 | 44186 |  | 37 | 44200 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting749820201214-14Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting749820201214-14Light Truck - Pick up- After Jan 101243.75Inv#090 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7498 | 20201214-14 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-12-14 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Greg on grader worked across access roads all the way to C-048. | 5 | C036-C049 | Pays Plat River | 0 | 44186 |  | 37 | 44200 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting749820201214-14L.O.A.1210 | Corbiere and Sons Contracting749820201214-14L.O.A.1210Inv#090 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7498 | 20201214-14 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 9.5 | HR |  |  | 75 | 0 | 712.5 | 92.625 | 805.125 | 2020-12-14 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Greg on grader worked across access roads all the way to C-048. | 5 | C036-C049 | Pays Plat River | 0 | 44186 |  | 37 | 44200 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting749820201214-14Operator - Principle - After Jan 109.5712.5 | Corbiere and Sons Contracting749820201214-14Operator - Principle - After Jan 109.5712.5Inv#090 | [5 empty] | 1 | 712.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7499 | 20201214-15 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10.5 | Dynamic | 95.24 | 0 |  |  | 1333.29 | 173.3277 | 1506.6177 | 2020-12-14 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Antler Lake access road all day. | 5 | C050-C069 | Antler Lake | 0 | 44186 |  | 37 | 44200 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting749920201214-15Grader - Cat 12 to 14 or equal- After Jan 1010.51333.29 | Corbiere and Sons Contracting749920201214-15Grader - Cat 12 to 14 or equal- After Jan 1010.51333.29Inv#090 | [5 empty] | 1 | 1333.29 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7499 | 20201214-15 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-12-14 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Antler Lake access road all day. | 5 | C050-C069 | Antler Lake | 0 | 44186 |  | 37 | 44200 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting749920201214-15Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting749920201214-15Light Truck - Pick up- After Jan 101243.75Inv#090 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7499 | 20201214-15 | 53510511 | Access | 0 | Foreman | 95 | 2 | HR |  |  | 95 | 0 | 190 | 24.7 | 214.7 | 2020-12-14 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Antler Lake access road all day. | 5 | C050-C069 | Antler Lake | 0 | 44186 |  | 37 | 44200 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting749920201214-15Foreman2190 | Corbiere and Sons Contracting749920201214-15Foreman2190Inv#090 | [5 empty] | 1 | 190 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7499 | 20201214-15 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-12-14 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Antler Lake access road all day. | 5 | C050-C069 | Antler Lake | 0 | 44186 |  | 37 | 44200 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting749920201214-15L.O.A.1210 | Corbiere and Sons Contracting749920201214-15L.O.A.1210Inv#090 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7499 | 20201214-15 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-12-14 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Antler Lake access road all day. | 5 | C050-C069 | Antler Lake | 0 | 44186 |  | 37 | 44200 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting749920201214-15Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting749920201214-15Operator - Principle - After Jan 1011.5862.5Inv#090 | [5 empty] | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7500 | 20201214-16 | 53510504 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 8 | Dynamic | 103.84 | 0 |  |  | 1107.6 | 143.988 | 1251.588 | 2020-12-14 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Continued on gravel spread and haul towards C-075.Labourer rolling out geo | 5 | C070-C075 | White Sand | 0 | 44186 |  | 37 | 44200 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting750020201214-16Excavator - 30 ton- After Jan 1081107.6 | Corbiere and Sons Contracting750020201214-16Excavator - 30 ton- After Jan 1081107.6Inv#090 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1107.6 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7500 | 20201214-16 | 53510504 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 8 | HR | 9.16 | 0 |  |  | 97.68 | 12.6984 | 110.3784 | 2020-12-14 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Continued on gravel spread and haul towards C-075.Labourer rolling out geo | 5 | C070-C075 | White Sand | 0 | 44186 |  | 37 | 44200 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting750020201214-16Excavator Thumb - 30 - 50 ton- After Jan 10897.68 | Corbiere and Sons Contracting750020201214-16Excavator Thumb - 30 - 50 ton- After Jan 10897.68Inv#090 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 97.68 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7500 | 20201214-16 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-12-14 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Continued on gravel spread and haul towards C-075.Labourer rolling out geo | 5 | C070-C075 | White Sand | 0 | 44186 |  | 37 | 44200 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting750020201214-16Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting750020201214-16Light Truck - Pick up- After Jan 102487.5Inv#090 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7500 | 20201214-16 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 8 | Dynamic | 103.54 | 0 |  |  | 1104.4 | 143.572 | 1247.972 | 2020-12-14 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Continued on gravel spread and haul towards C-075.Labourer rolling out geo | 5 | C070-C075 | White Sand | 0 | 44186 |  | 37 | 44200 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting750020201214-16Rock Truck - 30 Ton- After Jan 1081104.4 | Corbiere and Sons Contracting750020201214-16Rock Truck - 30 Ton- After Jan 1081104.4Inv#090 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1104.4 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7500 | 20201214-16 | 53510504 | Access | 0 | Foreman | 95 | 4 | HR |  |  | 95 | 0 | 380 | 49.4 | 429.4 | 2020-12-14 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Continued on gravel spread and haul towards C-075.Labourer rolling out geo | 5 | C070-C075 | White Sand | 0 | 44186 |  | 37 | 44200 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting750020201214-16Foreman4380 | Corbiere and Sons Contracting750020201214-16Foreman4380Inv#090 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7500 | 20201214-16 | 53510504 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2020-12-14 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Continued on gravel spread and haul towards C-075.Labourer rolling out geo | 5 | C070-C075 | White Sand | 0 | 44186 |  | 37 | 44200 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting750020201214-16L.O.A.4840 | Corbiere and Sons Contracting750020201214-16L.O.A.4840Inv#090 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7500 | 20201214-16 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 8 | HR |  |  | 75 | 0 | 600 | 78 | 678 | 2020-12-14 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Continued on gravel spread and haul towards C-075.Labourer rolling out geo | 5 | C070-C075 | White Sand | 0 | 44186 |  | 37 | 44200 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting750020201214-16Operator - Principle - After Jan 108600 | Corbiere and Sons Contracting750020201214-16Operator - Principle - After Jan 108600Inv#090 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7500 | 20201214-16 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 8 | HR |  |  | 70 | 0 | 560 | 72.8 | 632.8 | 2020-12-14 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Continued on gravel spread and haul towards C-075.Labourer rolling out geo | 5 | C070-C075 | White Sand | 0 | 44186 |  | 37 | 44200 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting750020201214-16Driver - AZ - After Jan 108560 | Corbiere and Sons Contracting750020201214-16Driver - AZ - After Jan 108560Inv#090 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 560 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7500 | 20201214-16 | 53510504 | Access | 0 | Labourer - General - After Jan 10 | 60 | 2 | HR |  |  | 60 | 0 | 120 | 15.6 | 135.6 | 2020-12-14 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Continued on gravel spread and haul towards C-075.Labourer rolling out geo | 5 | C070-C075 | White Sand | 0 | 44186 |  | 37 | 44200 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting750020201214-16Labourer - General - After Jan 102120 | Corbiere and Sons Contracting750020201214-16Labourer - General - After Jan 102120Inv#090 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 120 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7501 | 20201214-17 | 53510511 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 2.5 | Dynamic | 103.84 | 0 |  |  | 346.125 | 44.9963 | 391.1212 | 2020-12-14 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-017 completed 3 hrs of winter access maintenance. | 5 | C070-C075 | White Sand | 0 | 44186 |  | 37 | 44200 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting750120201214-17Excavator - 30 ton- After Jan 102.5346.125 | Corbiere and Sons Contracting750120201214-17Excavator - 30 ton- After Jan 102.5346.125Inv#090 | [5 empty] | 1 | 346.125 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7501 | 20201214-17 | 53510511 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 2.5 | HR | 9.16 | 0 |  |  | 30.525 | 3.9682 | 34.4933 | 2020-12-14 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-017 completed 3 hrs of winter access maintenance. | 5 | C070-C075 | White Sand | 0 | 44186 |  | 37 | 44200 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting750120201214-17Excavator Thumb - 30 - 50 ton- After Jan 102.530.525 | Corbiere and Sons Contracting750120201214-17Excavator Thumb - 30 - 50 ton- After Jan 102.530.525Inv#090 | [5 empty] | 1 | 30.525 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7501 | 20201214-17 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 3.5 | HR |  |  | 75 | 0 | 262.5 | 34.125 | 296.625 | 2020-12-14 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-017 completed 3 hrs of winter access maintenance. | 5 | C070-C075 | White Sand | 0 | 44186 |  | 37 | 44200 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting750120201214-17Operator - Principle - After Jan 103.5262.5 | Corbiere and Sons Contracting750120201214-17Operator - Principle - After Jan 103.5262.5Inv#090 | [5 empty] | 1 | 262.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7502 | 20201214-18 | 53510503 | Access | 0 | Skidder | 171 | 8 | HR | 128.25 | 0 |  |  | 1368 | 177.84 | 1545.84 | 2020-12-14 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX and skidder building corduroy from C-096. | 5 | C093-C116 | Cook Lake | 0 | 44186 |  | 37 | 44200 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting750220201214-18Skidder 81368 | Corbiere and Sons Contracting750220201214-18Skidder 81368Inv#090 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 1368 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7502 | 20201214-18 | 53510503 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 8 | Dynamic | 110.22 | 0 |  |  | 1175.68 | 152.8384 | 1328.5184 | 2020-12-14 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX and skidder building corduroy from C-096. | 5 | C093-C116 | Cook Lake | 0 | 44186 |  | 37 | 44200 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting750220201214-18Excavator - 36 ton- After Jan 1081175.68 | Corbiere and Sons Contracting750220201214-18Excavator - 36 ton- After Jan 1081175.68Inv#090 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 1175.68 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7502 | 20201214-18 | 53510503 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-12-14 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX and skidder building corduroy from C-096. | 5 | C093-C116 | Cook Lake | 0 | 44186 |  | 37 | 44200 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting750220201214-18Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting750220201214-18Light Truck - Pick up- After Jan 102487.5Inv#090 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7502 | 20201214-18 | 53510503 | Access | 0 | Foreman | 95 | 4 | HR |  |  | 95 | 0 | 380 | 49.4 | 429.4 | 2020-12-14 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX and skidder building corduroy from C-096. | 5 | C093-C116 | Cook Lake | 0 | 44186 |  | 37 | 44200 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting750220201214-18Foreman4380 | Corbiere and Sons Contracting750220201214-18Foreman4380Inv#090 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7502 | 20201214-18 | 53510503 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2020-12-14 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX and skidder building corduroy from C-096. | 5 | C093-C116 | Cook Lake | 0 | 44186 |  | 37 | 44200 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting750220201214-18L.O.A.3630 | Corbiere and Sons Contracting750220201214-18L.O.A.3630Inv#090 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7502 | 20201214-18 | 53510503 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 17 | HR |  |  | 75 | 0 | 1275 | 165.75 | 1440.75 | 2020-12-14 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Wetland Access Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX and skidder building corduroy from C-096. | 5 | C093-C116 | Cook Lake | 0 | 44186 |  | 37 | 44200 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting750220201214-18Operator - Principle - After Jan 10171275 | Corbiere and Sons Contracting750220201214-18Operator - Principle - After Jan 10171275Inv#090 |  | WF5-Wetland Access Development | WF5-Wetland Access Development |  | 1 | 1 | 1275 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7503 | 20201214-19 | 53510511 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 2.5 | Dynamic | 110.22 | 0 |  |  | 367.4 | 47.762 | 415.162 | 2020-12-14 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Completing winter road maintenance | 5 | C093-C116 | Cook Lake | 0 | 44186 |  | 37 | 44200 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting750320201214-19Excavator - 36 ton- After Jan 102.5367.4 | Corbiere and Sons Contracting750320201214-19Excavator - 36 ton- After Jan 102.5367.4Inv#090 | [5 empty] | 1 | 367.4 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7503 | 20201214-19 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 3 | HR |  |  | 75 | 0 | 225 | 29.25 | 254.25 | 2020-12-14 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Completing winter road maintenance | 5 | C093-C116 | Cook Lake | 0 | 44186 |  | 37 | 44200 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting750320201214-19Operator - Principle - After Jan 103225 | Corbiere and Sons Contracting750320201214-19Operator - Principle - After Jan 103225Inv#090 | [5 empty] | 1 | 225 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7492 | 20201214-8 | 53510312 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 9 | Dynamic | 98.61 | 0 |  |  | 1183.32 | 153.8316 | 1337.1516 | 2020-12-14 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Opened road from KM3 to B-181 | 3 | B161-B181 | Lachance road | 0 | 44186 |  | 37 | 44200 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting749220201214-8Dozer D6 or equal- After Jan 1091183.32 | Corbiere and Sons Contracting749220201214-8Dozer D6 or equal- After Jan 1091183.32Inv#090 | [5 empty] | 1 | 1183.32 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7492 | 20201214-8 | 53510312 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-12-14 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Opened road from KM3 to B-181 | 3 | B161-B181 | Lachance road | 0 | 44186 |  | 37 | 44200 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting749220201214-8Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting749220201214-8Light Truck - Pick up- After Jan 101243.75Inv#090 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7492 | 20201214-8 | 53510312 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 10 | HR |  |  | 75 | 0 | 750 | 97.5 | 847.5 | 2020-12-14 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Opened road from KM3 to B-181 | 3 | B161-B181 | Lachance road | 0 | 44186 |  | 37 | 44200 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting749220201214-8Operator - Principle - After Jan 1010750 | Corbiere and Sons Contracting749220201214-8Operator - Principle - After Jan 1010750Inv#090 | [5 empty] | 1 | 750 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7514 | 20201215-10 | 53510502 | Access | 0 | Excavator - 30 ton- After Jan 10 | 138.45 | 3 | Dynamic | 103.84 | 0 |  |  | 415.35 | 53.9955 | 469.3455 | 2020-12-15 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-17 moving remaining trees to C-075, Rock Truck hauling leftover trees to C-075. | 5 | C070-C075 | White Sand | 0 | 44186 |  | 37 | 44200 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting751420201215-10Excavator - 30 ton- After Jan 103415.35 | Corbiere and Sons Contracting751420201215-10Excavator - 30 ton- After Jan 103415.35Inv#090 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 415.35 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7514 | 20201215-10 | 53510502 | Access | 0 | Excavator Thumb - 30 - 50 ton- After Jan 10 | 12.21 | 3 | HR | 9.16 | 0 |  |  | 36.63 | 4.7619 | 41.3919 | 2020-12-15 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-17 moving remaining trees to C-075, Rock Truck hauling leftover trees to C-075. | 5 | C070-C075 | White Sand | 0 | 44186 |  | 37 | 44200 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting751420201215-10Excavator Thumb - 30 - 50 ton- After Jan 10336.63 | Corbiere and Sons Contracting751420201215-10Excavator Thumb - 30 - 50 ton- After Jan 10336.63Inv#090 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 36.63 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7514 | 20201215-10 | 53510502 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-12-15 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-17 moving remaining trees to C-075, Rock Truck hauling leftover trees to C-075. | 5 | C070-C075 | White Sand | 0 | 44186 |  | 37 | 44200 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting751420201215-10Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting751420201215-10Light Truck - Pick up- After Jan 101243.75Inv#090 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7514 | 20201215-10 | 53510502 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 3 | Dynamic | 103.54 | 0 |  |  | 414.15 | 53.8395 | 467.9895 | 2020-12-15 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-17 moving remaining trees to C-075, Rock Truck hauling leftover trees to C-075. | 5 | C070-C075 | White Sand | 0 | 44186 |  | 37 | 44200 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting751420201215-10Rock Truck - 30 Ton- After Jan 103414.15 | Corbiere and Sons Contracting751420201215-10Rock Truck - 30 Ton- After Jan 103414.15Inv#090 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 414.15 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7514 | 20201215-10 | 53510502 | Access | 0 | Foreman | 95 | 2 | HR |  |  | 95 | 0 | 190 | 24.7 | 214.7 | 2020-12-15 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-17 moving remaining trees to C-075, Rock Truck hauling leftover trees to C-075. | 5 | C070-C075 | White Sand | 0 | 44186 |  | 37 | 44200 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting751420201215-10Foreman2190 | Corbiere and Sons Contracting751420201215-10Foreman2190Inv#090 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 190 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7514 | 20201215-10 | 53510502 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 3 | HR |  |  | 75 | 0 | 225 | 29.25 | 254.25 | 2020-12-15 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-17 moving remaining trees to C-075, Rock Truck hauling leftover trees to C-075. | 5 | C070-C075 | White Sand | 0 | 44186 |  | 37 | 44200 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting751420201215-10Operator - Principle - After Jan 103225 | Corbiere and Sons Contracting751420201215-10Operator - Principle - After Jan 103225Inv#090 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 225 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7514 | 20201215-10 | 53510502 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 3 | HR |  |  | 70 | 0 | 210 | 27.3 | 237.3 | 2020-12-15 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-17 moving remaining trees to C-075, Rock Truck hauling leftover trees to C-075. | 5 | C070-C075 | White Sand | 0 | 44186 |  | 37 | 44200 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting751420201215-10Driver - AZ - After Jan 103210 | Corbiere and Sons Contracting751420201215-10Driver - AZ - After Jan 103210Inv#090 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7516 | 20201215-12 | 53510504 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 8.5 | Dynamic | 98.61 | 0 |  |  | 1117.58 | 145.2854 | 1262.8654 | 2020-12-15 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX loading rock truck from C-096, rock truck hauling for C-094-C-097, dozer spreading from C-094 - C-097. | 5 | C093-C116 | Cook Lake | 0 | 44186 |  | 37 | 44200 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting751620201215-12Dozer D6 or equal- After Jan 108.51117.58 | Corbiere and Sons Contracting751620201215-12Dozer D6 or equal- After Jan 108.51117.58Inv#090 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1117.58 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7516 | 20201215-12 | 53510504 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 8.5 | Dynamic | 110.22 | 0 |  |  | 1249.16 | 162.3908 | 1411.5508 | 2020-12-15 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX loading rock truck from C-096, rock truck hauling for C-094-C-097, dozer spreading from C-094 - C-097. | 5 | C093-C116 | Cook Lake | 0 | 44186 |  | 37 | 44200 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting751620201215-12Excavator - 36 ton- After Jan 108.51249.16 | Corbiere and Sons Contracting751620201215-12Excavator - 36 ton- After Jan 108.51249.16Inv#090 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1249.16 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7516 | 20201215-12 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-12-15 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX loading rock truck from C-096, rock truck hauling for C-094-C-097, dozer spreading from C-094 - C-097. | 5 | C093-C116 | Cook Lake | 0 | 44186 |  | 37 | 44200 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting751620201215-12Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting751620201215-12Light Truck - Pick up- After Jan 102487.5Inv#090 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7516 | 20201215-12 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 8.5 | Dynamic | 103.54 | 0 |  |  | 1173.425 | 152.5453 | 1325.9703 | 2020-12-15 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX loading rock truck from C-096, rock truck hauling for C-094-C-097, dozer spreading from C-094 - C-097. | 5 | C093-C116 | Cook Lake | 0 | 44186 |  | 37 | 44200 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting751620201215-12Rock Truck - 30 Ton- After Jan 108.51173.425 | Corbiere and Sons Contracting751620201215-12Rock Truck - 30 Ton- After Jan 108.51173.425Inv#090 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1173.425 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7516 | 20201215-12 | 53510504 | Access | 0 | Foreman | 95 | 6 | HR |  |  | 95 | 0 | 570 | 74.1 | 644.1 | 2020-12-15 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX loading rock truck from C-096, rock truck hauling for C-094-C-097, dozer spreading from C-094 - C-097. | 5 | C093-C116 | Cook Lake | 0 | 44186 |  | 37 | 44200 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting751620201215-12Foreman6570 | Corbiere and Sons Contracting751620201215-12Foreman6570Inv#090 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 570 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7516 | 20201215-12 | 53510504 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2020-12-15 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX loading rock truck from C-096, rock truck hauling for C-094-C-097, dozer spreading from C-094 - C-097. | 5 | C093-C116 | Cook Lake | 0 | 44186 |  | 37 | 44200 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting751620201215-12L.O.A.4840 | Corbiere and Sons Contracting751620201215-12L.O.A.4840Inv#090 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7516 | 20201215-12 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 18 | HR |  |  | 75 | 0 | 1350 | 175.5 | 1525.5 | 2020-12-15 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX loading rock truck from C-096, rock truck hauling for C-094-C-097, dozer spreading from C-094 - C-097. | 5 | C093-C116 | Cook Lake | 0 | 44186 |  | 37 | 44200 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting751620201215-12Operator - Principle - After Jan 10181350 | Corbiere and Sons Contracting751620201215-12Operator - Principle - After Jan 10181350Inv#090 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1350 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7516 | 20201215-12 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 9 | HR |  |  | 70 | 0 | 630 | 81.9 | 711.9 | 2020-12-15 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX loading rock truck from C-096, rock truck hauling for C-094-C-097, dozer spreading from C-094 - C-097. | 5 | C093-C116 | Cook Lake | 0 | 44186 |  | 37 | 44200 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting751620201215-12Driver - AZ - After Jan 109630 | Corbiere and Sons Contracting751620201215-12Driver - AZ - After Jan 109630Inv#090 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7517 | 20201215-13 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10.5 | Dynamic | 95.24 | 0 |  |  | 1333.29 | 173.3277 | 1506.6177 | 2020-12-15 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across access roads. | 5 | C076-C116 | Cook Lake | 0 | 44186 |  | 37 | 44200 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting751720201215-13Grader - Cat 12 to 14 or equal- After Jan 1010.51333.29 | Corbiere and Sons Contracting751720201215-13Grader - Cat 12 to 14 or equal- After Jan 1010.51333.29Inv#090 | [5 empty] | 1 | 1333.29 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7517 | 20201215-13 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-12-15 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across access roads. | 5 | C076-C116 | Cook Lake | 0 | 44186 |  | 37 | 44200 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting751720201215-13Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting751720201215-13Light Truck - Pick up- After Jan 101243.75Inv#090 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7517 | 20201215-13 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-12-15 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across access roads. | 5 | C076-C116 | Cook Lake | 0 | 44186 |  | 37 | 44200 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting751720201215-13L.O.A.1210 | Corbiere and Sons Contracting751720201215-13L.O.A.1210Inv#090 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7517 | 20201215-13 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-12-15 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across access roads. | 5 | C076-C116 | Cook Lake | 0 | 44186 |  | 37 | 44200 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting751720201215-13Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting751720201215-13Operator - Principle - After Jan 1011.5862.5Inv#090 | [5 empty] | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7518 | 20201215-14 | 53510312 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 6 | Dynamic | 98.61 | 0 |  |  | 788.88 | 102.5544 | 891.4344 | 2020-12-15 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | DZ-05 cleared snow B-167-B-161 Lachance W | 3 | B161-B167 | Lachance Road West | 0 | 44186 |  | 37 | 44200 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting751820201215-14Dozer D6 or equal- After Jan 106788.88 | Corbiere and Sons Contracting751820201215-14Dozer D6 or equal- After Jan 106788.88Inv#090 | [5 empty] | 1 | 788.88 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7518 | 20201215-14 | 53510312 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-12-15 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | DZ-05 cleared snow B-167-B-161 Lachance W | 3 | B161-B167 | Lachance Road West | 0 | 44186 |  | 37 | 44200 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting751820201215-14Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting751820201215-14Light Truck - Pick up- After Jan 101243.75Inv#090 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7518 | 20201215-14 | 53510312 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 7 | HR |  |  | 75 | 0 | 525 | 68.25 | 593.25 | 2020-12-15 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | DZ-05 cleared snow B-167-B-161 Lachance W | 3 | B161-B167 | Lachance Road West | 0 | 44186 |  | 37 | 44200 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting751820201215-14Operator - Principle - After Jan 107525 | Corbiere and Sons Contracting751820201215-14Operator - Principle - After Jan 107525Inv#090 | [5 empty] | 1 | 525 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7512 | 20201215-8 | 53510311 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 7.5 | Dynamic | 95.24 | 0 |  |  | 952.35 | 123.8055 | 1076.1555 | 2020-12-15 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across access roads. | 3 | B187-B193 | Gurney Lake Road | 0 | 44186 |  | 37 | 44200 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting751220201215-8Grader - Cat 12 to 14 or equal- After Jan 107.5952.35 | Corbiere and Sons Contracting751220201215-8Grader - Cat 12 to 14 or equal- After Jan 107.5952.35Inv#090 | [5 empty] | 1 | 952.35 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7512 | 20201215-8 | 53510311 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-12-15 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across access roads. | 3 | B187-B193 | Gurney Lake Road | 0 | 44186 |  | 37 | 44200 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting751220201215-8Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting751220201215-8Light Truck - Pick up- After Jan 101243.75Inv#090 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7512 | 20201215-8 | 53510311 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-12-15 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across access roads. | 3 | B187-B193 | Gurney Lake Road | 0 | 44186 |  | 37 | 44200 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting751220201215-8L.O.A.1210 | Corbiere and Sons Contracting751220201215-8L.O.A.1210Inv#090 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7512 | 20201215-8 | 53510311 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 8.5 | HR |  |  | 75 | 0 | 637.5 | 82.875 | 720.375 | 2020-12-15 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across access roads. | 3 | B187-B193 | Gurney Lake Road | 0 | 44186 |  | 37 | 44200 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting751220201215-8Operator - Principle - After Jan 108.5637.5 | Corbiere and Sons Contracting751220201215-8Operator - Principle - After Jan 108.5637.5Inv#090 | [5 empty] | 1 | 637.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7531 | 20201216-10 | 53510504 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 15.5 | Dynamic | 110.22 | 0 |  |  | 2277.88 | 296.1244 | 2574.0044 | 2020-12-16 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-011 working on gravel spread, EX-013 loading rock truck, rock truck hauling, labourer rolled out geo. | 5 | C093-C116 | Cook Lake | 0 | 44187 |  | 37 | 44201 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting753120201216-10Excavator - 36 ton- After Jan 1015.52277.88 | Corbiere and Sons Contracting753120201216-10Excavator - 36 ton- After Jan 1015.52277.88Inv#090 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 2277.88 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7531 | 20201216-10 | 53510504 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-12-16 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-011 working on gravel spread, EX-013 loading rock truck, rock truck hauling, labourer rolled out geo. | 5 | C093-C116 | Cook Lake | 0 | 44187 |  | 37 | 44201 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting753120201216-10Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting753120201216-10Light Truck - Pick up- After Jan 101243.75Inv#090 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7531 | 20201216-10 | 53510504 | Access | 0 | Rock Truck - 30 Ton- After Jan 10 | 138.05 | 10.5 | Dynamic | 103.54 | 0 |  |  | 1449.525 | 188.4383 | 1637.9633 | 2020-12-16 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-011 working on gravel spread, EX-013 loading rock truck, rock truck hauling, labourer rolled out geo. | 5 | C093-C116 | Cook Lake | 0 | 44187 |  | 37 | 44201 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting753120201216-10Rock Truck - 30 Ton- After Jan 1010.51449.525 | Corbiere and Sons Contracting753120201216-10Rock Truck - 30 Ton- After Jan 1010.51449.525Inv#090 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1449.525 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7531 | 20201216-10 | 53510504 | Access | 0 | Foreman | 95 | 4 | HR |  |  | 95 | 0 | 380 | 49.4 | 429.4 | 2020-12-16 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-011 working on gravel spread, EX-013 loading rock truck, rock truck hauling, labourer rolled out geo. | 5 | C093-C116 | Cook Lake | 0 | 44187 |  | 37 | 44201 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting753120201216-10Foreman4380 | Corbiere and Sons Contracting753120201216-10Foreman4380Inv#090 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7531 | 20201216-10 | 53510504 | Access | 0 | L.O.A. | 210 | 4 | DAY |  |  |  | 0 | 840 | 109.2 | 949.2 | 2020-12-16 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-011 working on gravel spread, EX-013 loading rock truck, rock truck hauling, labourer rolled out geo. | 5 | C093-C116 | Cook Lake | 0 | 44187 |  | 37 | 44201 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting753120201216-10L.O.A.4840 | Corbiere and Sons Contracting753120201216-10L.O.A.4840Inv#090 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 840 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7531 | 20201216-10 | 53510504 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 17 | HR |  |  | 75 | 0 | 1275 | 165.75 | 1440.75 | 2020-12-16 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-011 working on gravel spread, EX-013 loading rock truck, rock truck hauling, labourer rolled out geo. | 5 | C093-C116 | Cook Lake | 0 | 44187 |  | 37 | 44201 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting753120201216-10Operator - Principle - After Jan 10171275 | Corbiere and Sons Contracting753120201216-10Operator - Principle - After Jan 10171275Inv#090 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 1275 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7531 | 20201216-10 | 53510504 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 11.5 | HR |  |  | 70 | 0 | 805 | 104.65 | 909.65 | 2020-12-16 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-011 working on gravel spread, EX-013 loading rock truck, rock truck hauling, labourer rolled out geo. | 5 | C093-C116 | Cook Lake | 0 | 44187 |  | 37 | 44201 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting753120201216-10Driver - AZ - After Jan 1011.5805 | Corbiere and Sons Contracting753120201216-10Driver - AZ - After Jan 1011.5805Inv#090 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 805 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7531 | 20201216-10 | 53510504 | Access | 0 | Labourer - General - After Jan 10 | 60 | 4 | HR |  |  | 60 | 0 | 240 | 31.2 | 271.2 | 2020-12-16 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Gravel Hauling |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | EX-011 working on gravel spread, EX-013 loading rock truck, rock truck hauling, labourer rolled out geo. | 5 | C093-C116 | Cook Lake | 0 | 44187 |  | 37 | 44201 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting753120201216-10Labourer - General - After Jan 104240 | Corbiere and Sons Contracting753120201216-10Labourer - General - After Jan 104240Inv#090 |  | WF5-Gravel Hauling/Spreading | WF5-Gravel Hauling/Spreading |  | 1 | 1 | 240 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7528 | 20201216-7 | 53510411 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10.5 | Dynamic | 95.24 | 0 |  |  | 1333.29 | 173.3277 | 1506.6177 | 2020-12-16 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across access roads. | 4 | C011-C029 | Nishin creek | 0 | 44187 |  | 37 | 44201 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting752820201216-7Grader - Cat 12 to 14 or equal- After Jan 1010.51333.29 | Corbiere and Sons Contracting752820201216-7Grader - Cat 12 to 14 or equal- After Jan 1010.51333.29Inv#090 | [5 empty] | 1 | 1333.29 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7528 | 20201216-7 | 53510411 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-12-16 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across access roads. | 4 | C011-C029 | Nishin creek | 0 | 44187 |  | 37 | 44201 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting752820201216-7Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting752820201216-7Light Truck - Pick up- After Jan 101243.75Inv#090 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7528 | 20201216-7 | 53510411 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-12-16 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across access roads. | 4 | C011-C029 | Nishin creek | 0 | 44187 |  | 37 | 44201 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting752820201216-7L.O.A.1210 | Corbiere and Sons Contracting752820201216-7L.O.A.1210Inv#090 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7528 | 20201216-7 | 53510411 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-12-16 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across access roads. | 4 | C011-C029 | Nishin creek | 0 | 44187 |  | 37 | 44201 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting752820201216-7Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting752820201216-7Operator - Principle - After Jan 1011.5862.5Inv#090 | [5 empty] | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7530 | 20201216-9 | 53510511 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10.5 | Dynamic | 98.61 | 0 |  |  | 1380.54 | 179.4702 | 1560.0102 | 2020-12-16 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Terry spreading gravel all day for capping, Dustin working with plow and sander all day across access roads. | 5 | C076-C116 | Cook Lake | 0 | 44187 |  | 37 | 44201 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting753020201216-9Dozer D6 or equal- After Jan 1010.51380.54 | Corbiere and Sons Contracting753020201216-9Dozer D6 or equal- After Jan 1010.51380.54Inv#090 | [5 empty] | 1 | 1380.54 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7530 | 20201216-9 | 53510511 | Access | 0 | Sander Truck - Hwy- After Jan 10 | 55 | 10.5 | Dynamic | 41.25 | 0 |  |  | 577.5 | 75.075 | 652.575 | 2020-12-16 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Terry spreading gravel all day for capping, Dustin working with plow and sander all day across access roads. | 5 | C076-C116 | Cook Lake | 0 | 44187 |  | 37 | 44201 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting753020201216-9Sander Truck - Hwy- After Jan 1010.5577.5 | Corbiere and Sons Contracting753020201216-9Sander Truck - Hwy- After Jan 1010.5577.5Inv#090 | [5 empty] | 1 | 577.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7530 | 20201216-9 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-12-16 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Terry spreading gravel all day for capping, Dustin working with plow and sander all day across access roads. | 5 | C076-C116 | Cook Lake | 0 | 44187 |  | 37 | 44201 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting753020201216-9Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting753020201216-9Light Truck - Pick up- After Jan 102487.5Inv#090 | [5 empty] | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7530 | 20201216-9 | 53510511 | Access | 0 | Foreman | 95 | 4 | HR |  |  | 95 | 0 | 380 | 49.4 | 429.4 | 2020-12-16 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Terry spreading gravel all day for capping, Dustin working with plow and sander all day across access roads. | 5 | C076-C116 | Cook Lake | 0 | 44187 |  | 37 | 44201 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting753020201216-9Foreman4380 | Corbiere and Sons Contracting753020201216-9Foreman4380Inv#090 | [5 empty] | 1 | 380 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7530 | 20201216-9 | 53510511 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-12-16 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Terry spreading gravel all day for capping, Dustin working with plow and sander all day across access roads. | 5 | C076-C116 | Cook Lake | 0 | 44187 |  | 37 | 44201 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting753020201216-9L.O.A.2420 | Corbiere and Sons Contracting753020201216-9L.O.A.2420Inv#090 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7530 | 20201216-9 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-12-16 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Terry spreading gravel all day for capping, Dustin working with plow and sander all day across access roads. | 5 | C076-C116 | Cook Lake | 0 | 44187 |  | 37 | 44201 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting753020201216-9Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting753020201216-9Operator - Principle - After Jan 1011.5862.5Inv#090 | [5 empty] | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7530 | 20201216-9 | 53510511 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 11.5 | HR |  |  | 70 | 0 | 805 | 104.65 | 909.65 | 2020-12-16 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Terry spreading gravel all day for capping, Dustin working with plow and sander all day across access roads. | 5 | C076-C116 | Cook Lake | 0 | 44187 |  | 37 | 44201 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting753020201216-9Driver - AZ - After Jan 1011.5805 | Corbiere and Sons Contracting753020201216-9Driver - AZ - After Jan 1011.5805Inv#090 | [5 empty] | 1 | 805 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7559 | 20201217-18 | 53510511 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 10.5 | Dynamic | 98.61 | 0 |  |  | 1380.54 | 179.4702 | 1560.0102 | 2020-12-17 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer doing snow removal all dayJordan on EX for 3 hours scratching hill, Gary took over for the rest of the day (5 hrs) . | 5 | C076-C116 | Cook Lake | 0 | 44196 |  | 37 | 44201 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting755920201217-18Dozer D6 or equal- After Jan 1010.51380.54 | Corbiere and Sons Contracting755920201217-18Dozer D6 or equal- After Jan 1010.51380.54Inv#090 | [5 empty] | 1 | 1380.54 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7559 | 20201217-18 | 53510511 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 8 | Dynamic | 110.22 | 0 |  |  | 1175.68 | 152.8384 | 1328.5184 | 2020-12-17 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer doing snow removal all dayJordan on EX for 3 hours scratching hill, Gary took over for the rest of the day (5 hrs) . | 5 | C076-C116 | Cook Lake | 0 | 44196 |  | 37 | 44201 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting755920201217-18Excavator - 36 ton- After Jan 1081175.68 | Corbiere and Sons Contracting755920201217-18Excavator - 36 ton- After Jan 1081175.68Inv#090 | [5 empty] | 1 | 1175.68 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7559 | 20201217-18 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 2 | DAY | 182.81 | 0 |  |  | 487.5 | 63.375 | 550.875 | 2020-12-17 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer doing snow removal all dayJordan on EX for 3 hours scratching hill, Gary took over for the rest of the day (5 hrs) . | 5 | C076-C116 | Cook Lake | 0 | 44196 |  | 37 | 44201 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting755920201217-18Light Truck - Pick up- After Jan 102487.5 | Corbiere and Sons Contracting755920201217-18Light Truck - Pick up- After Jan 102487.5Inv#090 | [5 empty] | 1 | 487.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7559 | 20201217-18 | 53510511 | Access | 0 | Foreman | 95 | 3 | HR |  |  | 95 | 0 | 285 | 37.05 | 322.05 | 2020-12-17 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer doing snow removal all dayJordan on EX for 3 hours scratching hill, Gary took over for the rest of the day (5 hrs) . | 5 | C076-C116 | Cook Lake | 0 | 44196 |  | 37 | 44201 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting755920201217-18Foreman3285 | Corbiere and Sons Contracting755920201217-18Foreman3285Inv#090 | [5 empty] | 1 | 285 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7559 | 20201217-18 | 53510511 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2020-12-17 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer doing snow removal all dayJordan on EX for 3 hours scratching hill, Gary took over for the rest of the day (5 hrs) . | 5 | C076-C116 | Cook Lake | 0 | 44196 |  | 37 | 44201 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting755920201217-18L.O.A.3630 | Corbiere and Sons Contracting755920201217-18L.O.A.3630Inv#090 | [5 empty] | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7559 | 20201217-18 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 19.5 | HR |  |  | 75 | 0 | 1462.5 | 190.125 | 1652.625 | 2020-12-17 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer doing snow removal all dayJordan on EX for 3 hours scratching hill, Gary took over for the rest of the day (5 hrs) . | 5 | C076-C116 | Cook Lake | 0 | 44196 |  | 37 | 44201 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting755920201217-18Operator - Principle - After Jan 1019.51462.5 | Corbiere and Sons Contracting755920201217-18Operator - Principle - After Jan 1019.51462.5Inv#090 | [5 empty] | 1 | 1462.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7547 | 20201217-6 | 53510312 | Access | 0 | Tractor Trailer - 50 Ton- After Jan 10 | 111.75 | 3 | Dynamic | 83.81 | 0 |  |  | 335.25 | 43.5825 | 378.8325 | 2020-12-17 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved grader from North Shore yard to Lachance | 3 | B161-B181 | Lachance Road | 0 | 44196 |  | 37 | 44201 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting754720201217-6Tractor Trailer - 50 Ton- After Jan 103335.25 | Corbiere and Sons Contracting754720201217-6Tractor Trailer - 50 Ton- After Jan 103335.25Inv#090 | [5 empty] | 1 | 335.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7547 | 20201217-6 | 53510312 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 3 | HR |  |  | 70 | 0 | 210 | 27.3 | 237.3 | 2020-12-17 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Float moved grader from North Shore yard to Lachance | 3 | B161-B181 | Lachance Road | 0 | 44196 |  | 37 | 44201 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting754720201217-6Driver - AZ - After Jan 103210 | Corbiere and Sons Contracting754720201217-6Driver - AZ - After Jan 103210Inv#090 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7548 | 20201217-7 | 53510411 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10.5 | Dynamic | 95.24 | 0 |  |  | 1333.29 | 173.3277 | 1506.6177 | 2020-12-17 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Nishin access roads. | 4 | C011-C029 | Nishin Creek Road | 0 | 44196 |  | 37 | 44201 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting754820201217-7Grader - Cat 12 to 14 or equal- After Jan 1010.51333.29 | Corbiere and Sons Contracting754820201217-7Grader - Cat 12 to 14 or equal- After Jan 1010.51333.29Inv#090 | [5 empty] | 1 | 1333.29 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7548 | 20201217-7 | 53510411 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-12-17 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Nishin access roads. | 4 | C011-C029 | Nishin Creek Road | 0 | 44196 |  | 37 | 44201 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting754820201217-7L.O.A.1210 | Corbiere and Sons Contracting754820201217-7L.O.A.1210Inv#090 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7548 | 20201217-7 | 53510411 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-12-17 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Nishin access roads. | 4 | C011-C029 | Nishin Creek Road | 0 | 44196 |  | 37 | 44201 | [5 empty] | Harold Furlong | 04 | Corbiere and Sons Contracting754820201217-7Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting754820201217-7Operator - Principle - After Jan 1011.5862.5Inv#090 | [5 empty] | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7785 | 20201218-13 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10.5 | Dynamic | 95.24 | 0 |  |  | 1333.29 | 173.3277 | 1506.6177 | 2020-12-18 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across access roads all day | 5 | C050-C069 | Antler Lake | 0 | 44209 |  | 50 | 44209 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting778520201218-13Grader - Cat 12 to 14 or equal- After Jan 1010.51333.29 | Corbiere and Sons Contracting778520201218-13Grader - Cat 12 to 14 or equal- After Jan 1010.51333.29Inv#095 | [5 empty] | 1 | 1333.29 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7785 | 20201218-13 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-12-18 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across access roads all day | 5 | C050-C069 | Antler Lake | 0 | 44209 |  | 50 | 44209 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting778520201218-13Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting778520201218-13Light Truck - Pick up- After Jan 101243.75Inv#095 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7785 | 20201218-13 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-12-18 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across access roads all day | 5 | C050-C069 | Antler Lake | 0 | 44209 |  | 50 | 44209 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting778520201218-13L.O.A.1210 | Corbiere and Sons Contracting778520201218-13L.O.A.1210Inv#095 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7785 | 20201218-13 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-12-18 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across access roads all day | 5 | C050-C069 | Antler Lake | 0 | 44209 |  | 50 | 44209 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting778520201218-13Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting778520201218-13Operator - Principle - After Jan 1011.5862.5Inv#095 | [5 empty] | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7792 | 20201218-20 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 5 | Dynamic | 95.24 | 0 |  |  | 634.9 | 82.537 | 717.437 | 2020-12-18 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Pays Plat access roads for the morning | 5 | C031-C049 | Pays Plat River | 0 | 44209 |  | 50 | 44209 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting779220201218-20Grader - Cat 12 to 14 or equal- After Jan 105634.9 | Corbiere and Sons Contracting779220201218-20Grader - Cat 12 to 14 or equal- After Jan 105634.9Inv#095 | [5 empty] | 1 | 634.9 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7792 | 20201218-20 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-12-18 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Pays Plat access roads for the morning | 5 | C031-C049 | Pays Plat River | 0 | 44209 |  | 50 | 44209 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting779220201218-20Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting779220201218-20Light Truck - Pick up- After Jan 101243.75Inv#095 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7792 | 20201218-20 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-12-18 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Pays Plat access roads for the morning | 5 | C031-C049 | Pays Plat River | 0 | 44209 |  | 50 | 44209 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting779220201218-20L.O.A.1210 | Corbiere and Sons Contracting779220201218-20L.O.A.1210Inv#095 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7792 | 20201218-20 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 75 | 0 | 450 | 58.5 | 508.5 | 2020-12-18 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Pays Plat access roads for the morning | 5 | C031-C049 | Pays Plat River | 0 | 44209 |  | 50 | 44209 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting779220201218-20Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting779220201218-20Operator - Principle - After Jan 106450Inv#095 | [5 empty] | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7793 | 20201218-21 | 53510511 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 9 | Dynamic | 98.61 | 0 |  |  | 1183.32 | 153.8316 | 1337.1516 | 2020-12-18 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer doing snow removal from KM4 into Cooks West | 5 | C076-C116 | Cook Lake | 0 | 44209 |  | 50 | 44209 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting779320201218-21Dozer D6 or equal- After Jan 1091183.32 | Corbiere and Sons Contracting779320201218-21Dozer D6 or equal- After Jan 1091183.32Inv#095 | [5 empty] | 1 | 1183.32 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7793 | 20201218-21 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-12-18 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer doing snow removal from KM4 into Cooks West | 5 | C076-C116 | Cook Lake | 0 | 44209 |  | 50 | 44209 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting779320201218-21Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting779320201218-21Light Truck - Pick up- After Jan 101243.75Inv#095 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7793 | 20201218-21 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-12-18 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer doing snow removal from KM4 into Cooks West | 5 | C076-C116 | Cook Lake | 0 | 44209 |  | 50 | 44209 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting779320201218-21L.O.A.1210 | Corbiere and Sons Contracting779320201218-21L.O.A.1210Inv#095 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7793 | 20201218-21 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 10 | HR |  |  | 75 | 0 | 750 | 97.5 | 847.5 | 2020-12-18 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer doing snow removal from KM4 into Cooks West | 5 | C076-C116 | Cook Lake | 0 | 44209 |  | 50 | 44209 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting779320201218-21Operator - Principle - After Jan 1010750 | Corbiere and Sons Contracting779320201218-21Operator - Principle - After Jan 1010750Inv#095 | [5 empty] | 1 | 750 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7795 | 20201218-23 | 53510502 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-12-18 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Stacey did general cleanup and demobed rolls of geo from KM10 | 5 | C076-C116 | Cook Lake | 0 | 44209 |  | 50 | 44209 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting779520201218-23Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting779520201218-23Light Truck - Pick up- After Jan 101243.75Inv#095 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7795 | 20201218-23 | 53510502 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-12-18 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Stacey did general cleanup and demobed rolls of geo from KM10 | 5 | C076-C116 | Cook Lake | 0 | 44209 |  | 50 | 44209 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting779520201218-23L.O.A.1210 | Corbiere and Sons Contracting779520201218-23L.O.A.1210Inv#095 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7795 | 20201218-23 | 53510502 | Access | 0 | Labourer - General - After Jan 10 | 60 | 6 | HR |  |  | 60 | 0 | 360 | 46.8 | 406.8 | 2020-12-18 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | New All Season Development |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Stacey did general cleanup and demobed rolls of geo from KM10 | 5 | C076-C116 | Cook Lake | 0 | 44209 |  | 50 | 44209 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting779520201218-23Labourer - General - After Jan 106360 | Corbiere and Sons Contracting779520201218-23Labourer - General - After Jan 106360Inv#095 |  | WF5-New All Season Development | WF5-New All Season Development |  | 1 | 1 | 360 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7569 | 20201218-6 | 53510312 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 9 | Dynamic | 95.24 | 0 |  |  | 1142.82 | 148.5666 | 1291.3866 | 2020-12-18 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader worked on Lachance then floated to Landfill, Rob sanding access roads | 3 | B161-B181 | LaChance Road | 0 | 44196 |  | 37 | 44201 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting756920201218-6Grader - Cat 12 to 14 or equal- After Jan 1091142.82 | Corbiere and Sons Contracting756920201218-6Grader - Cat 12 to 14 or equal- After Jan 1091142.82Inv#090 | [5 empty] | 1 | 1142.82 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7569 | 20201218-6 | 53510312 | Access | 0 | Sander Truck - Hwy- After Jan 10 | 55 | 11 | Dynamic | 41.25 | 0 |  |  | 605 | 78.65 | 683.65 | 2020-12-18 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader worked on Lachance then floated to Landfill, Rob sanding access roads | 3 | B161-B181 | LaChance Road | 0 | 44196 |  | 37 | 44201 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting756920201218-6Sander Truck - Hwy- After Jan 1011605 | Corbiere and Sons Contracting756920201218-6Sander Truck - Hwy- After Jan 1011605Inv#090 | [5 empty] | 1 | 605 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7569 | 20201218-6 | 53510312 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-12-18 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader worked on Lachance then floated to Landfill, Rob sanding access roads | 3 | B161-B181 | LaChance Road | 0 | 44196 |  | 37 | 44201 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting756920201218-6Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting756920201218-6Light Truck - Pick up- After Jan 101243.75Inv#090 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7569 | 20201218-6 | 53510312 | Access | 0 | Tractor Trailer - 50 Ton- After Jan 10 | 111.75 | 3 | Dynamic | 83.81 | 0 |  |  | 335.25 | 43.5825 | 378.8325 | 2020-12-18 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader worked on Lachance then floated to Landfill, Rob sanding access roads | 3 | B161-B181 | LaChance Road | 0 | 44196 |  | 37 | 44201 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting756920201218-6Tractor Trailer - 50 Ton- After Jan 103335.25 | Corbiere and Sons Contracting756920201218-6Tractor Trailer - 50 Ton- After Jan 103335.25Inv#090 | [5 empty] | 1 | 335.25 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7569 | 20201218-6 | 53510312 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11 | HR |  |  | 75 | 0 | 825 | 107.25 | 932.25 | 2020-12-18 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader worked on Lachance then floated to Landfill, Rob sanding access roads | 3 | B161-B181 | LaChance Road | 0 | 44196 |  | 37 | 44201 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting756920201218-6Operator - Principle - After Jan 1011825 | Corbiere and Sons Contracting756920201218-6Operator - Principle - After Jan 1011825Inv#090 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7569 | 20201218-6 | 53510312 | Access | 0 | Driver - AZ - After Jan 10 | 70 | 14 | HR |  |  | 70 | 0 | 980 | 127.4 | 1107.4 | 2020-12-18 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader worked on Lachance then floated to Landfill, Rob sanding access roads | 3 | B161-B181 | LaChance Road | 0 | 44196 |  | 37 | 44201 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting756920201218-6Driver - AZ - After Jan 1014980 | Corbiere and Sons Contracting756920201218-6Driver - AZ - After Jan 1014980Inv#090 | [5 empty] | 1 | 980 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7797 | 20201219-13 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10.5 | Dynamic | 95.24 | 0 |  |  | 1333.29 | 173.3277 | 1506.6177 | 2020-12-19 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Antler Lake all day | 5 | C050-C069 | Antler Lake | 0 | 43843 |  | 50 | 44209 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting779720201219-13Grader - Cat 12 to 14 or equal- After Jan 1010.51333.29 | Corbiere and Sons Contracting779720201219-13Grader - Cat 12 to 14 or equal- After Jan 1010.51333.29Inv#095 | [5 empty] | 1 | 1333.29 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7797 | 20201219-13 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-12-19 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Antler Lake all day | 5 | C050-C069 | Antler Lake | 0 | 43843 |  | 50 | 44209 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting779720201219-13Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting779720201219-13Light Truck - Pick up- After Jan 101243.75Inv#095 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7797 | 20201219-13 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-12-19 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Antler Lake all day | 5 | C050-C069 | Antler Lake | 0 | 43843 |  | 50 | 44209 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting779720201219-13L.O.A.1210 | Corbiere and Sons Contracting779720201219-13L.O.A.1210Inv#095 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7797 | 20201219-13 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-12-19 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Antler Lake all day | 5 | C050-C069 | Antler Lake | 0 | 43843 |  | 50 | 44209 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting779720201219-13Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting779720201219-13Operator - Principle - After Jan 1011.5862.5Inv#095 | [5 empty] | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7802 | 20201219-18 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10.5 | Dynamic | 95.24 | 0 |  |  | 1333.29 | 173.3277 | 1506.6177 | 2020-12-19 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Pays Plat all day | 5 | C031-C049 | Pays Plat River | 0 | 44209 |  | 50 | 44209 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting780220201219-18Grader - Cat 12 to 14 or equal- After Jan 1010.51333.29 | Corbiere and Sons Contracting780220201219-18Grader - Cat 12 to 14 or equal- After Jan 1010.51333.29Inv#095 | [5 empty] | 1 | 1333.29 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7802 | 20201219-18 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-12-19 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Pays Plat all day | 5 | C031-C049 | Pays Plat River | 0 | 44209 |  | 50 | 44209 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting780220201219-18Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting780220201219-18Light Truck - Pick up- After Jan 101243.75Inv#095 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7802 | 20201219-18 | 53510511 | Access | 0 | Foreman | 95 | 2 | HR |  |  | 95 | 0 | 190 | 24.7 | 214.7 | 2020-12-19 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Pays Plat all day | 5 | C031-C049 | Pays Plat River | 0 | 44209 |  | 50 | 44209 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting780220201219-18Foreman2190 | Corbiere and Sons Contracting780220201219-18Foreman2190Inv#095 | [5 empty] | 1 | 190 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7802 | 20201219-18 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-12-19 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Pays Plat all day | 5 | C031-C049 | Pays Plat River | 0 | 44209 |  | 50 | 44209 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting780220201219-18L.O.A.1210 | Corbiere and Sons Contracting780220201219-18L.O.A.1210Inv#095 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7802 | 20201219-18 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-12-19 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Pays Plat all day | 5 | C031-C049 | Pays Plat River | 0 | 44209 |  | 50 | 44209 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting780220201219-18Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting780220201219-18Operator - Principle - After Jan 1011.5862.5Inv#095 | [5 empty] | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7580 | 20201219-6 | 53510312 | Access | 0 | Sander Truck - Hwy- After Jan 10 | 55 | 6 | Dynamic | 41.25 | 0 |  |  | 330 | 42.9 | 372.9 | 2020-12-19 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Sander sanded Lachance, Gurney and Little Gravel Rd for de-mob. | 3 | B161-B181 | Lachance Road | 0 | 44187 |  | 37 | 44201 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting758020201219-6Sander Truck - Hwy- After Jan 106330 | Corbiere and Sons Contracting758020201219-6Sander Truck - Hwy- After Jan 106330Inv#090 | [5 empty] | 1 | 330 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7580 | 20201219-6 | 53510312 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 6 | HR |  |  | 75 | 0 | 450 | 58.5 | 508.5 | 2020-12-19 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Sander sanded Lachance, Gurney and Little Gravel Rd for de-mob. | 3 | B161-B181 | Lachance Road | 0 | 44187 |  | 37 | 44201 | [5 empty] | Harold Furlong | 03 | Corbiere and Sons Contracting758020201219-6Operator - Principle - After Jan 106450 | Corbiere and Sons Contracting758020201219-6Operator - Principle - After Jan 106450Inv#090 | [5 empty] | 1 | 450 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7817 | 20201220-16 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10.5 | Dynamic | 95.24 | 0 |  |  | 1333.29 | 173.3277 | 1506.6177 | 2020-12-20 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across access roads all day | 5 | C031-C049 | Pays Plat River | 0 | 44209 |  | 50 | 44209 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting781720201220-16Grader - Cat 12 to 14 or equal- After Jan 1010.51333.29 | Corbiere and Sons Contracting781720201220-16Grader - Cat 12 to 14 or equal- After Jan 1010.51333.29Inv#095 | [5 empty] | 1 | 1333.29 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7817 | 20201220-16 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-12-20 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across access roads all day | 5 | C031-C049 | Pays Plat River | 0 | 44209 |  | 50 | 44209 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting781720201220-16Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting781720201220-16Light Truck - Pick up- After Jan 101243.75Inv#095 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7817 | 20201220-16 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-12-20 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across access roads all day | 5 | C031-C049 | Pays Plat River | 0 | 44209 |  | 50 | 44209 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting781720201220-16L.O.A.1210 | Corbiere and Sons Contracting781720201220-16L.O.A.1210Inv#095 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7817 | 20201220-16 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-12-20 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across access roads all day | 5 | C031-C049 | Pays Plat River | 0 | 44209 |  | 50 | 44209 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting781720201220-16Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting781720201220-16Operator - Principle - After Jan 1011.5862.5Inv#095 | [5 empty] | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7852 | 20201220-17 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 1 | Dynamic | 98.61 | 0 |  |  | 131.48 | 17.0924 | 148.5724 | 2020-12-20 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Open Neys road with dozer, plowing snow. | 6 | C219-C236 | Neys | 0 | 44214 |  | 50 | 44215 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting785220201220-17Dozer D6 or equal- After Jan 101131.48 | Corbiere and Sons Contracting785220201220-17Dozer D6 or equal- After Jan 101131.48Inv#095 | [5 empty] | 1 | 131.48 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7852 | 20201220-17 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-12-20 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Open Neys road with dozer, plowing snow. | 6 | C219-C236 | Neys | 0 | 44214 |  | 50 | 44215 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting785220201220-17L.O.A.1210 | Corbiere and Sons Contracting785220201220-17L.O.A.1210Inv#095 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7852 | 20201220-17 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 1 | HR |  |  | 75 | 0 | 75 | 9.75 | 84.75 | 2020-12-20 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Open Neys road with dozer, plowing snow. | 6 | C219-C236 | Neys | 0 | 44214 |  | 50 | 44215 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting785220201220-17Operator - Principle - After Jan 10175 | Corbiere and Sons Contracting785220201220-17Operator - Principle - After Jan 10175Inv#095 | [5 empty] | 1 | 75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7853 | 20201220-18 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 2 | Dynamic | 98.61 | 0 |  |  | 262.96 | 34.1848 | 297.1448 | 2020-12-20 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Open Culvert Creek road with dozer, plowing snow. | 6 | C237-C243 | Culvert Creek | 0 | 44214 |  | 50 | 44215 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting785320201220-18Dozer D6 or equal- After Jan 102262.96 | Corbiere and Sons Contracting785320201220-18Dozer D6 or equal- After Jan 102262.96Inv#095 | [5 empty] | 1 | 262.96 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7853 | 20201220-18 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-12-20 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Open Culvert Creek road with dozer, plowing snow. | 6 | C237-C243 | Culvert Creek | 0 | 44214 |  | 50 | 44215 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting785320201220-18L.O.A.1210 | Corbiere and Sons Contracting785320201220-18L.O.A.1210Inv#095 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7853 | 20201220-18 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 2 | HR |  |  | 75 | 0 | 150 | 19.5 | 169.5 | 2020-12-20 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Open Culvert Creek road with dozer, plowing snow. | 6 | C237-C243 | Culvert Creek | 0 | 44214 |  | 50 | 44215 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting785320201220-18Operator - Principle - After Jan 102150 | Corbiere and Sons Contracting785320201220-18Operator - Principle - After Jan 102150Inv#095 | [5 empty] | 1 | 150 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7929 | 20201220-19 | 53510511 | Access | 0 | 3rd Party Charges | 1 | 469.8 | unit |  |  |  |  | 469.8 | 61.074 | 530.874 | 2020-12-20 | 0 | Inv#109 | 44251 | 143 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Plowing Prairie River / Santoy Mountain / Lake A and Sanding Lake A on December 20th, 2020 | 5 | C155-C157 | Santoy Mountain | 0 | 44217 |  | 36 | 44217 | 18291 | Plow Truck and Sanding |  |  |  | Mike Lecocq | 05 | Corbiere and Sons Contracting792920201220-193rd Party Charges469.8469.8 | Corbiere and Sons Contracting792920201220-193rd Party Charges469.8469.8Inv#109 | [5 empty] | 1 | 469.8 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7592 | 20201220-6 | 53510512 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 3 | Dynamic | 98.61 | 0 |  |  | 394.44 | 51.2772 | 445.7172 | 2020-12-20 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer opened up C-031 - C-035 and turnarounds as well as the dump area. | 5 | C031-C035 | Pays Plat River | 0 | 44187 |  | 37 | 44201 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting759220201220-6Dozer D6 or equal- After Jan 103394.44 | Corbiere and Sons Contracting759220201220-6Dozer D6 or equal- After Jan 103394.44Inv#090 | [5 empty] | 1 | 394.44 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7592 | 20201220-6 | 53510512 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 3 | HR |  |  | 75 | 0 | 225 | 29.25 | 254.25 | 2020-12-20 | 0 | Inv#090 | 44203 | 136 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dozer opened up C-031 - C-035 and turnarounds as well as the dump area. | 5 | C031-C035 | Pays Plat River | 0 | 44187 |  | 37 | 44201 | [5 empty] | Harold Furlong | 05 | Corbiere and Sons Contracting759220201220-6Operator - Principle - After Jan 103225 | Corbiere and Sons Contracting759220201220-6Operator - Principle - After Jan 103225Inv#090 | [5 empty] | 1 | 225 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7809 | 20201220-8 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10.5 | Dynamic | 95.24 | 0 |  |  | 1333.29 | 173.3277 | 1506.6177 | 2020-12-20 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Spent day grading access roads | 5 | C050-C069 | Antler Lake | 0 | 44209 |  | 50 | 44209 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting780920201220-8Grader - Cat 12 to 14 or equal- After Jan 1010.51333.29 | Corbiere and Sons Contracting780920201220-8Grader - Cat 12 to 14 or equal- After Jan 1010.51333.29Inv#095 | [5 empty] | 1 | 1333.29 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7809 | 20201220-8 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-12-20 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Spent day grading access roads | 5 | C050-C069 | Antler Lake | 0 | 44209 |  | 50 | 44209 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting780920201220-8Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting780920201220-8Light Truck - Pick up- After Jan 101243.75Inv#095 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7809 | 20201220-8 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-12-20 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Spent day grading access roads | 5 | C050-C069 | Antler Lake | 0 | 44209 |  | 50 | 44209 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting780920201220-8L.O.A.1210 | Corbiere and Sons Contracting780920201220-8L.O.A.1210Inv#095 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7809 | 20201220-8 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-12-20 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Spent day grading access roads | 5 | C050-C069 | Antler Lake | 0 | 44209 |  | 50 | 44209 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting780920201220-8Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting780920201220-8Operator - Principle - After Jan 1011.5862.5Inv#095 | [5 empty] | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7827 | 20201221-10 | 53510611 | Access | 0 | Dozer D6 or equal- After Jan 10 | 131.48 | 2 | Dynamic | 98.61 | 0 |  |  | 262.96 | 34.1848 | 297.1448 | 2020-12-21 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dustin did snow removal once dropped off | 6 | C129-C151 | Lake A | 0 | 44210 |  | 50 | 44214 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting782720201221-10Dozer D6 or equal- After Jan 102262.96 | Corbiere and Sons Contracting782720201221-10Dozer D6 or equal- After Jan 102262.96Inv#095 | [5 empty] | 1 | 262.96 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7827 | 20201221-10 | 53510611 | Access | 0 | Excavator - 36 ton- After Jan 10 | 146.96 | 2 | Dynamic | 110.22 | 0 |  |  | 293.92 | 38.2096 | 332.1296 | 2020-12-21 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dustin did snow removal once dropped off | 6 | C129-C151 | Lake A | 0 | 44210 |  | 50 | 44214 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting782720201221-10Excavator - 36 ton- After Jan 102293.92 | Corbiere and Sons Contracting782720201221-10Excavator - 36 ton- After Jan 102293.92Inv#095 | [5 empty] | 1 | 293.92 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7827 | 20201221-10 | 53510611 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-12-21 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dustin did snow removal once dropped off | 6 | C129-C151 | Lake A | 0 | 44210 |  | 50 | 44214 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting782720201221-10Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting782720201221-10Light Truck - Pick up- After Jan 101243.75Inv#095 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7827 | 20201221-10 | 53510611 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-12-21 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dustin did snow removal once dropped off | 6 | C129-C151 | Lake A | 0 | 44210 |  | 50 | 44214 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting782720201221-10L.O.A.1210 | Corbiere and Sons Contracting782720201221-10L.O.A.1210Inv#095 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7827 | 20201221-10 | 53510611 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 4 | HR |  |  | 75 | 0 | 300 | 39 | 339 | 2020-12-21 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Dustin did snow removal once dropped off | 6 | C129-C151 | Lake A | 0 | 44210 |  | 50 | 44214 | [5 empty] | Wes Seminowich | 06 | Corbiere and Sons Contracting782720201221-10Operator - Principle - After Jan 104300 | Corbiere and Sons Contracting782720201221-10Operator - Principle - After Jan 104300Inv#095 | [5 empty] | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7824 | 20201221-7 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10.5 | Dynamic | 95.24 | 0 |  |  | 1333.29 | 173.3277 | 1506.6177 | 2020-12-21 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Len working on grader across access roads all day | 5 | C031-C049 | Pays Plat River | 0 | 44210 |  | 50 | 44214 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting782420201221-7Grader - Cat 12 to 14 or equal- After Jan 1010.51333.29 | Corbiere and Sons Contracting782420201221-7Grader - Cat 12 to 14 or equal- After Jan 1010.51333.29Inv#095 | [5 empty] | 1 | 1333.29 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7824 | 20201221-7 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-12-21 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Len working on grader across access roads all day | 5 | C031-C049 | Pays Plat River | 0 | 44210 |  | 50 | 44214 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting782420201221-7Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting782420201221-7Light Truck - Pick up- After Jan 101243.75Inv#095 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7824 | 20201221-7 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-12-21 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Len working on grader across access roads all day | 5 | C031-C049 | Pays Plat River | 0 | 44210 |  | 50 | 44214 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting782420201221-7L.O.A.1210 | Corbiere and Sons Contracting782420201221-7L.O.A.1210Inv#095 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7824 | 20201221-7 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-12-21 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Len working on grader across access roads all day | 5 | C031-C049 | Pays Plat River | 0 | 44210 |  | 50 | 44214 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting782420201221-7Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting782420201221-7Operator - Principle - After Jan 1011.5862.5Inv#095 | [5 empty] | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7825 | 20201221-8 | 53510511 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 10.5 | Dynamic | 95.24 | 0 |  |  | 1333.29 | 173.3277 | 1506.6177 | 2020-12-21 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Antler Lake access roads all day | 5 | C050-C069 | Antler Lake | 0 | 44210 |  | 50 | 44214 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting782520201221-8Grader - Cat 12 to 14 or equal- After Jan 1010.51333.29 | Corbiere and Sons Contracting782520201221-8Grader - Cat 12 to 14 or equal- After Jan 1010.51333.29Inv#095 | [5 empty] | 1 | 1333.29 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7825 | 20201221-8 | 53510511 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-12-21 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Antler Lake access roads all day | 5 | C050-C069 | Antler Lake | 0 | 44210 |  | 50 | 44214 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting782520201221-8Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting782520201221-8Light Truck - Pick up- After Jan 101243.75Inv#095 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7825 | 20201221-8 | 53510511 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-12-21 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Antler Lake access roads all day | 5 | C050-C069 | Antler Lake | 0 | 44210 |  | 50 | 44214 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting782520201221-8L.O.A.1210 | Corbiere and Sons Contracting782520201221-8L.O.A.1210Inv#095 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7825 | 20201221-8 | 53510511 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 11.5 | HR |  |  | 75 | 0 | 862.5 | 112.125 | 974.625 | 2020-12-21 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | Winter Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader working across Antler Lake access roads all day | 5 | C050-C069 | Antler Lake | 0 | 44210 |  | 50 | 44214 | [5 empty] | Wes Seminowich | 05 | Corbiere and Sons Contracting782520201221-8Operator - Principle - After Jan 1011.5862.5 | Corbiere and Sons Contracting782520201221-8Operator - Principle - After Jan 1011.5862.5Inv#095 | [5 empty] | 1 | 862.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7652 | 20201229-2 | 53510312 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 5 | Dynamic | 95.24 | 0 |  |  | 634.9 | 82.537 | 717.437 | 2020-12-29 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader opened up Gurney Lake Rd | 3 | B187-B193 | Gurney Lake Road | 0 | 44202 |  | 36 | 44207 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting765220201229-2Grader - Cat 12 to 14 or equal- After Jan 105634.9 | Corbiere and Sons Contracting765220201229-2Grader - Cat 12 to 14 or equal- After Jan 105634.9Inv#095 | [5 empty] | 1 | 634.9 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7652 | 20201229-2 | 53510312 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5 | HR |  |  | 75 | 0 | 375 | 48.75 | 423.75 | 2020-12-29 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader opened up Gurney Lake Rd | 3 | B187-B193 | Gurney Lake Road | 0 | 44202 |  | 36 | 44207 | [5 empty] | Mike Lecocq | 03 | Corbiere and Sons Contracting765220201229-2Operator - Principle - After Jan 105375 | Corbiere and Sons Contracting765220201229-2Operator - Principle - After Jan 105375Inv#095 | [5 empty] | 1 | 375 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7653 | 20201229-3 | 53510412 | Access | 0 | Grader - Cat 12 to 14 or equal- After Jan 10 | 126.98 | 4 | Dynamic | 95.24 | 0 |  |  | 507.92 | 66.0296 | 573.9496 | 2020-12-29 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader opened up Little Gravel River Rd | 4 | B194-B210 | Little Gravel River Rd | 0 | 44202 |  | 36 | 44207 | [5 empty] | Mike Lecocq | 04 | Corbiere and Sons Contracting765320201229-3Grader - Cat 12 to 14 or equal- After Jan 104507.92 | Corbiere and Sons Contracting765320201229-3Grader - Cat 12 to 14 or equal- After Jan 104507.92Inv#095 | [5 empty] | 1 | 507.92 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7653 | 20201229-3 | 53510412 | Access | 0 | Light Truck - Pick up- After Jan 10 | 243.75 | 1 | DAY | 182.81 | 0 |  |  | 243.75 | 31.6875 | 275.4375 | 2020-12-29 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader opened up Little Gravel River Rd | 4 | B194-B210 | Little Gravel River Rd | 0 | 44202 |  | 36 | 44207 | [5 empty] | Mike Lecocq | 04 | Corbiere and Sons Contracting765320201229-3Light Truck - Pick up- After Jan 101243.75 | Corbiere and Sons Contracting765320201229-3Light Truck - Pick up- After Jan 101243.75Inv#095 | [5 empty] | 1 | 243.75 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 7653 | 20201229-3 | 53510412 | Access | 0 | Operator - Principle - After Jan 10 | 75 | 5 | HR |  |  | 75 | 0 | 375 | 48.75 | 423.75 | 2020-12-29 | 0 | Inv#095 | 44217 | 139 | 0 | 0 | Glenda Pevie | All Season Access Maintenance |  | VC7556-2019-017 | 929 OF |  |  |  | Approved |  |  | Grader opened up Little Gravel River Rd | 4 | B194-B210 | Little Gravel River Rd | 0 | 44202 |  | 36 | 44207 | [5 empty] | Mike Lecocq | 04 | Corbiere and Sons Contracting765320201229-3Operator - Principle - After Jan 105375 | Corbiere and Sons Contracting765320201229-3Operator - Principle - After Jan 105375Inv#095 | [5 empty] | 1 | 375 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 809 | 202012-2-R1 | 53520102 | Clearing | 0 | Loader JD 524 to 624 or equal | 99 | 5 | HR | 74.25 | 0 |  |  | 495 | 64.35 | 559.35 | 2020-01-05 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | General yard maintenance |  |  | General yard maintenance | 0 |  |  | 36 | 43840 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting809202012-2-R1Loader JD 524 to 624 or equal5495 | Corbiere and Sons Contracting809202012-2-R1Loader JD 524 to 624 or equal5495Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 495 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 809 | 202012-2-R1 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2020-01-05 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | General yard maintenance |  |  | General yard maintenance | 0 |  |  | 36 | 43840 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting809202012-2-R1Light Truck - Pick up10300 | Corbiere and Sons Contracting809202012-2-R1Light Truck - Pick up10300Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 809 | 202012-2-R1 | 53520102 | Clearing | 0 | Operator - Apprentice | 60 | 10 | HR |  |  |  | 0 | 600 | 78 | 678 | 2020-01-05 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | General yard maintenance |  |  | General yard maintenance | 0 |  |  | 36 | 43840 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting809202012-2-R1Operator - Apprentice10600 | Corbiere and Sons Contracting809202012-2-R1Operator - Apprentice10600Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 810 | 202012-3-R1 | 53510111 | Access | 0 | Dozer - D5 or equal | 99 | 9 | HR | 74.25 | 0 |  |  | 891 | 115.83 | 1006.83 | 2020-01-05 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 14 | Approved | snow removal on assembly and crane pads - ongoing | 9013 | Snow Removal-Wind Farm and various access roads |  |  | Snow Removal-Wind Farm and various access roads | 0 |  |  | 36 | 43840 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting810202012-3-R1Dozer - D5 or equal9891 | Corbiere and Sons Contracting810202012-3-R1Dozer - D5 or equal9891Inv#006R01 | [5 empty] | 1 | 891 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 810 | 202012-3-R1 | 53510111 | Access | 0 | Dozer D6 or equal | 135 | 9 | HR | 101.25 | 0 |  |  | 1215 | 157.95 | 1372.95 | 2020-01-05 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 14 | Approved | snow removal on assembly and crane pads - ongoing | 9013 | Snow Removal-Wind Farm and various access roads |  |  | Snow Removal-Wind Farm and various access roads | 0 |  |  | 36 | 43840 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting810202012-3-R1Dozer D6 or equal91215 | Corbiere and Sons Contracting810202012-3-R1Dozer D6 or equal91215Inv#006R01 | [5 empty] | 1 | 1215 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 810 | 202012-3-R1 | 53510111 | Access | 0 | Dozer D6 or equal | 135 | 9 | HR | 101.25 | 0 |  |  | 1215 | 157.95 | 1372.95 | 2020-01-05 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 14 | Approved | snow removal on assembly and crane pads - ongoing | 9013 | Snow Removal-Wind Farm and various access roads |  |  | Snow Removal-Wind Farm and various access roads | 0 |  |  | 36 | 43840 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting810202012-3-R1Dozer D6 or equal91215 | Corbiere and Sons Contracting810202012-3-R1Dozer D6 or equal91215Inv#006R01 | [5 empty] | 1 | 1215 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 810 | 202012-3-R1 | 53510111 | Access | 0 | Excavator - 36 ton | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2020-01-05 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 14 | Approved | snow removal on assembly and crane pads - ongoing | 9013 | Snow Removal-Wind Farm and various access roads |  |  | Snow Removal-Wind Farm and various access roads | 0 |  |  | 36 | 43840 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting810202012-3-R1Excavator - 36 ton91539 | Corbiere and Sons Contracting810202012-3-R1Excavator - 36 ton91539Inv#006R01 | [5 empty] | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 810 | 202012-3-R1 | 53510111 | Access | 0 | Excavator - 36 ton | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2020-01-05 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 14 | Approved | snow removal on assembly and crane pads - ongoing | 9013 | Snow Removal-Wind Farm and various access roads |  |  | Snow Removal-Wind Farm and various access roads | 0 |  |  | 36 | 43840 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting810202012-3-R1Excavator - 36 ton91539 | Corbiere and Sons Contracting810202012-3-R1Excavator - 36 ton91539Inv#006R01 | [5 empty] | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 810 | 202012-3-R1 | 53510111 | Access | 0 | Grader - Cat 12 to 14 or equal | 126 | 18 | HR | 94.5 | 0 |  |  | 2268 | 294.84 | 2562.84 | 2020-01-05 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 14 | Approved | snow removal on assembly and crane pads - ongoing | 9013 | Snow Removal-Wind Farm and various access roads |  |  | Snow Removal-Wind Farm and various access roads | 0 |  |  | 36 | 43840 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting810202012-3-R1Grader - Cat 12 to 14 or equal182268 | Corbiere and Sons Contracting810202012-3-R1Grader - Cat 12 to 14 or equal182268Inv#006R01 | [5 empty] | 1 | 2268 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 810 | 202012-3-R1 | 53510111 | Access | 0 | Loader JD 524 to 624 or equal | 99 | 9 | HR | 74.25 | 0 |  |  | 891 | 115.83 | 1006.83 | 2020-01-05 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 14 | Approved | snow removal on assembly and crane pads - ongoing | 9013 | Snow Removal-Wind Farm and various access roads |  |  | Snow Removal-Wind Farm and various access roads | 0 |  |  | 36 | 43840 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting810202012-3-R1Loader JD 524 to 624 or equal9891 | Corbiere and Sons Contracting810202012-3-R1Loader JD 524 to 624 or equal9891Inv#006R01 | [5 empty] | 1 | 891 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 810 | 202012-3-R1 | 53510111 | Access | 0 | Light Truck - Pick up | 30 | 50 | HR | 22.5 | 0 |  |  | 1500 | 195 | 1695 | 2020-01-05 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 14 | Approved | snow removal on assembly and crane pads - ongoing | 9013 | Snow Removal-Wind Farm and various access roads |  |  | Snow Removal-Wind Farm and various access roads | 0 |  |  | 36 | 43840 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting810202012-3-R1Light Truck - Pick up501500 | Corbiere and Sons Contracting810202012-3-R1Light Truck - Pick up501500Inv#006R01 | [5 empty] | 1 | 1500 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 810 | 202012-3-R1 | 53510111 | Access | 0 | Operator - Principle | 90 | 88 | HR |  |  |  | 0 | 7920 | 1029.6 | 8949.6 | 2020-01-05 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 14 | Approved | snow removal on assembly and crane pads - ongoing | 9013 | Snow Removal-Wind Farm and various access roads |  |  | Snow Removal-Wind Farm and various access roads | 0 |  |  | 36 | 43840 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting810202012-3-R1Operator - Principle887920 | Corbiere and Sons Contracting810202012-3-R1Operator - Principle887920Inv#006R01 | [5 empty] | 1 | 7920 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 810 | 202012-3-R1 | 53510111 | Access | 0 | Labourer - Specialized | 75 | 11 | HR |  |  |  | 0 | 825 | 107.25 | 932.25 | 2020-01-05 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 14 | Approved | snow removal on assembly and crane pads - ongoing | 9013 | Snow Removal-Wind Farm and various access roads |  |  | Snow Removal-Wind Farm and various access roads | 0 |  |  | 36 | 43840 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting810202012-3-R1Labourer - Specialized11825 | Corbiere and Sons Contracting810202012-3-R1Labourer - Specialized11825Inv#006R01 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 810 | 202012-3-R1 | 53510111 | Access | 0 | Labourer - General | 65 | 11 | HR |  |  |  | 0 | 715 | 92.95 | 807.95 | 2020-01-05 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 14 | Approved | snow removal on assembly and crane pads - ongoing | 9013 | Snow Removal-Wind Farm and various access roads |  |  | Snow Removal-Wind Farm and various access roads | 0 |  |  | 36 | 43840 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting810202012-3-R1Labourer - General11715 | Corbiere and Sons Contracting810202012-3-R1Labourer - General11715Inv#006R01 | [5 empty] | 1 | 715 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 810 | 202012-3-R1 | 53510111 | Access | 0 | L.O.A. | 210 | 8 | DAY |  |  |  | 0 | 1680 | 218.4 | 1898.4 | 2020-01-05 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 14 | Approved | snow removal on assembly and crane pads - ongoing | 9013 | Snow Removal-Wind Farm and various access roads |  |  | Snow Removal-Wind Farm and various access roads | 0 |  |  | 36 | 43840 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting810202012-3-R1L.O.A.81680 | Corbiere and Sons Contracting810202012-3-R1L.O.A.81680Inv#006R01 | [5 empty] | 1 | 1680 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 812 | 202012-5-R1 | 53520102 | Clearing | 0 | Brusher | 202.5 | 9 | HR | 151.88 | 0 |  |  | 1822.5 | 236.925 | 2059.425 | 2020-01-05 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Excavators NS0EX-01, NS-EX-02, NS-EX-04 raked and piled towers B004-B005, Feller Buncher NS-FB-01 and Skidder NS-SK-01 completed all clearing B004 - B005, Grader Cleared all Wolf and Cavern access - NS-BR- 01 completed Cavern Road access via mulching 2m and finishing mulching at B004, Float NS-RT-03 flosted COR-DZ-01 from Harold Crescent to McGregor then to Mckenzie |  |  | Fish Hatchery - A128 to B017 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting812202012-5-R1Brusher91822.5 | Corbiere and Sons Contracting812202012-5-R1Brusher91822.5Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1822.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 812 | 202012-5-R1 | 53520101 | Clearing | 0 | Feller Buncher | 240 | 9 | HR | 180 | 0 |  |  | 2160 | 280.8 | 2440.8 | 2020-01-05 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Excavators NS0EX-01, NS-EX-02, NS-EX-04 raked and piled towers B004-B005, Feller Buncher NS-FB-01 and Skidder NS-SK-01 completed all clearing B004 - B005, Grader Cleared all Wolf and Cavern access - NS-BR- 01 completed Cavern Road access via mulching 2m and finishing mulching at B004, Float NS-RT-03 flosted COR-DZ-01 from Harold Crescent to McGregor then to Mckenzie |  |  | Fish Hatchery - A128 to B017 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting812202012-5-R1Feller Buncher92160 | Corbiere and Sons Contracting812202012-5-R1Feller Buncher92160Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2160 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 812 | 202012-5-R1 | 53520101 | Clearing | 0 | Skidder | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2020-01-05 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Excavators NS0EX-01, NS-EX-02, NS-EX-04 raked and piled towers B004-B005, Feller Buncher NS-FB-01 and Skidder NS-SK-01 completed all clearing B004 - B005, Grader Cleared all Wolf and Cavern access - NS-BR- 01 completed Cavern Road access via mulching 2m and finishing mulching at B004, Float NS-RT-03 flosted COR-DZ-01 from Harold Crescent to McGregor then to Mckenzie |  |  | Fish Hatchery - A128 to B017 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting812202012-5-R1Skidder 91539 | Corbiere and Sons Contracting812202012-5-R1Skidder 91539Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 812 | 202012-5-R1 | 53520102 | Clearing | 0 | Dozer D6 or equal | 135 | 9 | HR | 101.25 | 0 |  |  | 1215 | 157.95 | 1372.95 | 2020-01-05 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Excavators NS0EX-01, NS-EX-02, NS-EX-04 raked and piled towers B004-B005, Feller Buncher NS-FB-01 and Skidder NS-SK-01 completed all clearing B004 - B005, Grader Cleared all Wolf and Cavern access - NS-BR- 01 completed Cavern Road access via mulching 2m and finishing mulching at B004, Float NS-RT-03 flosted COR-DZ-01 from Harold Crescent to McGregor then to Mckenzie |  |  | Fish Hatchery - A128 to B017 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting812202012-5-R1Dozer D6 or equal91215 | Corbiere and Sons Contracting812202012-5-R1Dozer D6 or equal91215Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1215 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 812 | 202012-5-R1 | 53520102 | Clearing | 0 | Excavator - 30 ton | 139.5 | 9 | HR | 104.63 | 0 |  |  | 1255.5 | 163.215 | 1418.715 | 2020-01-05 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Excavators NS0EX-01, NS-EX-02, NS-EX-04 raked and piled towers B004-B005, Feller Buncher NS-FB-01 and Skidder NS-SK-01 completed all clearing B004 - B005, Grader Cleared all Wolf and Cavern access - NS-BR- 01 completed Cavern Road access via mulching 2m and finishing mulching at B004, Float NS-RT-03 flosted COR-DZ-01 from Harold Crescent to McGregor then to Mckenzie |  |  | Fish Hatchery - A128 to B017 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting812202012-5-R1Excavator - 30 ton91255.5 | Corbiere and Sons Contracting812202012-5-R1Excavator - 30 ton91255.5Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1255.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 812 | 202012-5-R1 | 53520102 | Clearing | 0 | Excavator - 36 ton | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2020-01-05 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Excavators NS0EX-01, NS-EX-02, NS-EX-04 raked and piled towers B004-B005, Feller Buncher NS-FB-01 and Skidder NS-SK-01 completed all clearing B004 - B005, Grader Cleared all Wolf and Cavern access - NS-BR- 01 completed Cavern Road access via mulching 2m and finishing mulching at B004, Float NS-RT-03 flosted COR-DZ-01 from Harold Crescent to McGregor then to Mckenzie |  |  | Fish Hatchery - A128 to B017 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting812202012-5-R1Excavator - 36 ton91539 | Corbiere and Sons Contracting812202012-5-R1Excavator - 36 ton91539Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 812 | 202012-5-R1 | 53520102 | Clearing | 0 | Excavator - 36 ton | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2020-01-05 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Excavators NS0EX-01, NS-EX-02, NS-EX-04 raked and piled towers B004-B005, Feller Buncher NS-FB-01 and Skidder NS-SK-01 completed all clearing B004 - B005, Grader Cleared all Wolf and Cavern access - NS-BR- 01 completed Cavern Road access via mulching 2m and finishing mulching at B004, Float NS-RT-03 flosted COR-DZ-01 from Harold Crescent to McGregor then to Mckenzie |  |  | Fish Hatchery - A128 to B017 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting812202012-5-R1Excavator - 36 ton91539 | Corbiere and Sons Contracting812202012-5-R1Excavator - 36 ton91539Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 812 | 202012-5-R1 | 53520102 | Clearing | 0 | Excavator Thumb - 30 - 50 ton | 13.5 | 9 | HR | 10.13 | 0 |  |  | 121.5 | 15.795 | 137.295 | 2020-01-05 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Excavators NS0EX-01, NS-EX-02, NS-EX-04 raked and piled towers B004-B005, Feller Buncher NS-FB-01 and Skidder NS-SK-01 completed all clearing B004 - B005, Grader Cleared all Wolf and Cavern access - NS-BR- 01 completed Cavern Road access via mulching 2m and finishing mulching at B004, Float NS-RT-03 flosted COR-DZ-01 from Harold Crescent to McGregor then to Mckenzie |  |  | Fish Hatchery - A128 to B017 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting812202012-5-R1Excavator Thumb - 30 - 50 ton9121.5 | Corbiere and Sons Contracting812202012-5-R1Excavator Thumb - 30 - 50 ton9121.5Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 121.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 812 | 202012-5-R1 | 53520102 | Clearing | 0 | Excavator Thumb - 30 - 50 ton | 13.5 | 9 | HR | 10.13 | 0 |  |  | 121.5 | 15.795 | 137.295 | 2020-01-05 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Excavators NS0EX-01, NS-EX-02, NS-EX-04 raked and piled towers B004-B005, Feller Buncher NS-FB-01 and Skidder NS-SK-01 completed all clearing B004 - B005, Grader Cleared all Wolf and Cavern access - NS-BR- 01 completed Cavern Road access via mulching 2m and finishing mulching at B004, Float NS-RT-03 flosted COR-DZ-01 from Harold Crescent to McGregor then to Mckenzie |  |  | Fish Hatchery - A128 to B017 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting812202012-5-R1Excavator Thumb - 30 - 50 ton9121.5 | Corbiere and Sons Contracting812202012-5-R1Excavator Thumb - 30 - 50 ton9121.5Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 121.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 812 | 202012-5-R1 | 53520102 | Clearing | 0 | Excavator Thumb - 30 - 50 ton | 13.5 | 9 | HR | 10.13 | 0 |  |  | 121.5 | 15.795 | 137.295 | 2020-01-05 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Excavators NS0EX-01, NS-EX-02, NS-EX-04 raked and piled towers B004-B005, Feller Buncher NS-FB-01 and Skidder NS-SK-01 completed all clearing B004 - B005, Grader Cleared all Wolf and Cavern access - NS-BR- 01 completed Cavern Road access via mulching 2m and finishing mulching at B004, Float NS-RT-03 flosted COR-DZ-01 from Harold Crescent to McGregor then to Mckenzie |  |  | Fish Hatchery - A128 to B017 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting812202012-5-R1Excavator Thumb - 30 - 50 ton9121.5 | Corbiere and Sons Contracting812202012-5-R1Excavator Thumb - 30 - 50 ton9121.5Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 121.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 812 | 202012-5-R1 | 53510111 | Access | 0 | Excavator Grinder Att.- 30 - 50 ton | 108 | 9 | HR | 81 | 0 |  |  | 972 | 126.36 | 1098.36 | 2020-01-05 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Excavators NS0EX-01, NS-EX-02, NS-EX-04 raked and piled towers B004-B005, Feller Buncher NS-FB-01 and Skidder NS-SK-01 completed all clearing B004 - B005, Grader Cleared all Wolf and Cavern access - NS-BR- 01 completed Cavern Road access via mulching 2m and finishing mulching at B004, Float NS-RT-03 flosted COR-DZ-01 from Harold Crescent to McGregor then to Mckenzie |  |  | Fish Hatchery - A128 to B017 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting812202012-5-R1Excavator Grinder Att.- 30 - 50 ton9972 | Corbiere and Sons Contracting812202012-5-R1Excavator Grinder Att.- 30 - 50 ton9972Inv#006R01 | [5 empty] | 1 | 972 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 812 | 202012-5-R1 | 53510111 | Access | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2020-01-05 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Excavators NS0EX-01, NS-EX-02, NS-EX-04 raked and piled towers B004-B005, Feller Buncher NS-FB-01 and Skidder NS-SK-01 completed all clearing B004 - B005, Grader Cleared all Wolf and Cavern access - NS-BR- 01 completed Cavern Road access via mulching 2m and finishing mulching at B004, Float NS-RT-03 flosted COR-DZ-01 from Harold Crescent to McGregor then to Mckenzie |  |  | Fish Hatchery - A128 to B017 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting812202012-5-R1Light Truck - Pick up10300 | Corbiere and Sons Contracting812202012-5-R1Light Truck - Pick up10300Inv#006R01 | [5 empty] | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 812 | 202012-5-R1 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 30 | HR | 22.5 | 0 |  |  | 900 | 117 | 1017 | 2020-01-05 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Excavators NS0EX-01, NS-EX-02, NS-EX-04 raked and piled towers B004-B005, Feller Buncher NS-FB-01 and Skidder NS-SK-01 completed all clearing B004 - B005, Grader Cleared all Wolf and Cavern access - NS-BR- 01 completed Cavern Road access via mulching 2m and finishing mulching at B004, Float NS-RT-03 flosted COR-DZ-01 from Harold Crescent to McGregor then to Mckenzie |  |  | Fish Hatchery - A128 to B017 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting812202012-5-R1Light Truck - Pick up30900 | Corbiere and Sons Contracting812202012-5-R1Light Truck - Pick up30900Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 812 | 202012-5-R1 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 40 | HR | 22.5 | 0 |  |  | 1200 | 156 | 1356 | 2020-01-05 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Excavators NS0EX-01, NS-EX-02, NS-EX-04 raked and piled towers B004-B005, Feller Buncher NS-FB-01 and Skidder NS-SK-01 completed all clearing B004 - B005, Grader Cleared all Wolf and Cavern access - NS-BR- 01 completed Cavern Road access via mulching 2m and finishing mulching at B004, Float NS-RT-03 flosted COR-DZ-01 from Harold Crescent to McGregor then to Mckenzie |  |  | Fish Hatchery - A128 to B017 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting812202012-5-R1Light Truck - Pick up401200 | Corbiere and Sons Contracting812202012-5-R1Light Truck - Pick up401200Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1200 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 812 | 202012-5-R1 | 53520102 | Clearing | 0 | Tractor Trailer - 50 Ton | 130.5 | 10 | HR | 97.88 | 0 |  |  | 1305 | 169.65 | 1474.65 | 2020-01-05 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Excavators NS0EX-01, NS-EX-02, NS-EX-04 raked and piled towers B004-B005, Feller Buncher NS-FB-01 and Skidder NS-SK-01 completed all clearing B004 - B005, Grader Cleared all Wolf and Cavern access - NS-BR- 01 completed Cavern Road access via mulching 2m and finishing mulching at B004, Float NS-RT-03 flosted COR-DZ-01 from Harold Crescent to McGregor then to Mckenzie |  |  | Fish Hatchery - A128 to B017 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting812202012-5-R1Tractor Trailer - 50 Ton101305 | Corbiere and Sons Contracting812202012-5-R1Tractor Trailer - 50 Ton101305Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1305 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 812 | 202012-5-R1 | 53510111 | Access | 0 | Foreman | 95 | 1 | HR |  |  |  | 0 | 95 | 12.35 | 107.35 | 2020-01-05 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Excavators NS0EX-01, NS-EX-02, NS-EX-04 raked and piled towers B004-B005, Feller Buncher NS-FB-01 and Skidder NS-SK-01 completed all clearing B004 - B005, Grader Cleared all Wolf and Cavern access - NS-BR- 01 completed Cavern Road access via mulching 2m and finishing mulching at B004, Float NS-RT-03 flosted COR-DZ-01 from Harold Crescent to McGregor then to Mckenzie |  |  | Fish Hatchery - A128 to B017 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting812202012-5-R1Foreman195 | Corbiere and Sons Contracting812202012-5-R1Foreman195Inv#006R01 | [5 empty] | 1 | 95 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 812 | 202012-5-R1 | 53520101 | Clearing | 0 | Foreman | 95 | 8 | HR |  |  |  | 0 | 760 | 98.8 | 858.8 | 2020-01-05 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Excavators NS0EX-01, NS-EX-02, NS-EX-04 raked and piled towers B004-B005, Feller Buncher NS-FB-01 and Skidder NS-SK-01 completed all clearing B004 - B005, Grader Cleared all Wolf and Cavern access - NS-BR- 01 completed Cavern Road access via mulching 2m and finishing mulching at B004, Float NS-RT-03 flosted COR-DZ-01 from Harold Crescent to McGregor then to Mckenzie |  |  | Fish Hatchery - A128 to B017 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting812202012-5-R1Foreman8760 | Corbiere and Sons Contracting812202012-5-R1Foreman8760Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 760 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 812 | 202012-5-R1 | 53520102 | Clearing | 0 | Foreman | 95 | 3 | HR |  |  |  | 0 | 285 | 37.05 | 322.05 | 2020-01-05 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Excavators NS0EX-01, NS-EX-02, NS-EX-04 raked and piled towers B004-B005, Feller Buncher NS-FB-01 and Skidder NS-SK-01 completed all clearing B004 - B005, Grader Cleared all Wolf and Cavern access - NS-BR- 01 completed Cavern Road access via mulching 2m and finishing mulching at B004, Float NS-RT-03 flosted COR-DZ-01 from Harold Crescent to McGregor then to Mckenzie |  |  | Fish Hatchery - A128 to B017 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting812202012-5-R1Foreman3285 | Corbiere and Sons Contracting812202012-5-R1Foreman3285Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 285 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 812 | 202012-5-R1 | 53510111 | Access | 0 | Operator - Principle | 90 | 22 | HR |  |  |  | 0 | 1980 | 257.4 | 2237.4 | 2020-01-05 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Excavators NS0EX-01, NS-EX-02, NS-EX-04 raked and piled towers B004-B005, Feller Buncher NS-FB-01 and Skidder NS-SK-01 completed all clearing B004 - B005, Grader Cleared all Wolf and Cavern access - NS-BR- 01 completed Cavern Road access via mulching 2m and finishing mulching at B004, Float NS-RT-03 flosted COR-DZ-01 from Harold Crescent to McGregor then to Mckenzie |  |  | Fish Hatchery - A128 to B017 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting812202012-5-R1Operator - Principle221980 | Corbiere and Sons Contracting812202012-5-R1Operator - Principle221980Inv#006R01 | [5 empty] | 1 | 1980 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 812 | 202012-5-R1 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 22 | HR |  |  |  | 0 | 1980 | 257.4 | 2237.4 | 2020-01-05 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Excavators NS0EX-01, NS-EX-02, NS-EX-04 raked and piled towers B004-B005, Feller Buncher NS-FB-01 and Skidder NS-SK-01 completed all clearing B004 - B005, Grader Cleared all Wolf and Cavern access - NS-BR- 01 completed Cavern Road access via mulching 2m and finishing mulching at B004, Float NS-RT-03 flosted COR-DZ-01 from Harold Crescent to McGregor then to Mckenzie |  |  | Fish Hatchery - A128 to B017 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting812202012-5-R1Operator - Principle221980 | Corbiere and Sons Contracting812202012-5-R1Operator - Principle221980Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1980 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 812 | 202012-5-R1 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 44 | HR |  |  |  | 0 | 3960 | 514.8 | 4474.8 | 2020-01-05 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Excavators NS0EX-01, NS-EX-02, NS-EX-04 raked and piled towers B004-B005, Feller Buncher NS-FB-01 and Skidder NS-SK-01 completed all clearing B004 - B005, Grader Cleared all Wolf and Cavern access - NS-BR- 01 completed Cavern Road access via mulching 2m and finishing mulching at B004, Float NS-RT-03 flosted COR-DZ-01 from Harold Crescent to McGregor then to Mckenzie |  |  | Fish Hatchery - A128 to B017 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting812202012-5-R1Operator - Principle443960 | Corbiere and Sons Contracting812202012-5-R1Operator - Principle443960Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 3960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 812 | 202012-5-R1 | 53510111 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-01-05 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Excavators NS0EX-01, NS-EX-02, NS-EX-04 raked and piled towers B004-B005, Feller Buncher NS-FB-01 and Skidder NS-SK-01 completed all clearing B004 - B005, Grader Cleared all Wolf and Cavern access - NS-BR- 01 completed Cavern Road access via mulching 2m and finishing mulching at B004, Float NS-RT-03 flosted COR-DZ-01 from Harold Crescent to McGregor then to Mckenzie |  |  | Fish Hatchery - A128 to B017 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting812202012-5-R1L.O.A.2420 | Corbiere and Sons Contracting812202012-5-R1L.O.A.2420Inv#006R01 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 812 | 202012-5-R1 | 53520101 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-01-05 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Excavators NS0EX-01, NS-EX-02, NS-EX-04 raked and piled towers B004-B005, Feller Buncher NS-FB-01 and Skidder NS-SK-01 completed all clearing B004 - B005, Grader Cleared all Wolf and Cavern access - NS-BR- 01 completed Cavern Road access via mulching 2m and finishing mulching at B004, Float NS-RT-03 flosted COR-DZ-01 from Harold Crescent to McGregor then to Mckenzie |  |  | Fish Hatchery - A128 to B017 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting812202012-5-R1L.O.A.2420 | Corbiere and Sons Contracting812202012-5-R1L.O.A.2420Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 812 | 202012-5-R1 | 53520102 | Clearing | 0 | L.O.A. | 210 | 5 | DAY |  |  |  | 0 | 1050 | 136.5 | 1186.5 | 2020-01-05 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Excavators NS0EX-01, NS-EX-02, NS-EX-04 raked and piled towers B004-B005, Feller Buncher NS-FB-01 and Skidder NS-SK-01 completed all clearing B004 - B005, Grader Cleared all Wolf and Cavern access - NS-BR- 01 completed Cavern Road access via mulching 2m and finishing mulching at B004, Float NS-RT-03 flosted COR-DZ-01 from Harold Crescent to McGregor then to Mckenzie |  |  | Fish Hatchery - A128 to B017 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting812202012-5-R1L.O.A.51050 | Corbiere and Sons Contracting812202012-5-R1L.O.A.51050Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1050 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 872 | 202013-1 | 53510111 | Access | 0 | Light Truck - Pick up | 30 | 8 | HR | 22.5 | 0 |  |  | 240 | 31.2 | 271.2 | 2020-01-09 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  | 53510106 Splitted cost from 53510104, 53510111, 53520101 53520102, 53520104 - these codes had cost on the given day |  |  |  |  | Project supervision |  |  | Project supervision | 0 |  |  | 36 | 43839 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting872202013-1Light Truck - Pick up8240 | Corbiere and Sons Contracting872202013-1Light Truck - Pick up8240Inv#006R01 | [5 empty] | 1 | 240 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 872 | 202013-1 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 8 | HR | 22.5 | 0 |  |  | 240 | 31.2 | 271.2 | 2020-01-09 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | 53510106 Splitted cost from 53510104, 53510111, 53520101 53520102, 53520104 - these codes had cost on the given day |  |  |  |  | Project supervision |  |  | Project supervision | 0 |  |  | 36 | 43839 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting872202013-1Light Truck - Pick up8240 | Corbiere and Sons Contracting872202013-1Light Truck - Pick up8240Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 240 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 872 | 202013-1 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 8 | HR | 22.5 | 0 |  |  | 240 | 31.2 | 271.2 | 2020-01-09 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | 53510106 Splitted cost from 53510104, 53510111, 53520101 53520102, 53520104 - these codes had cost on the given day |  |  |  |  | Project supervision |  |  | Project supervision | 0 |  |  | 36 | 43839 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting872202013-1Light Truck - Pick up8240 | Corbiere and Sons Contracting872202013-1Light Truck - Pick up8240Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 240 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 872 | 202013-1 | 53520104 | Clearing | 0 | Light Truck - Pick up | 30 | 8 | HR | 22.5 | 0 |  |  | 240 | 31.2 | 271.2 | 2020-01-09 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  | 53510106 Splitted cost from 53510104, 53510111, 53520101 53520102, 53520104 - these codes had cost on the given day |  |  |  |  | Project supervision |  |  | Project supervision | 0 |  |  | 36 | 43839 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting872202013-1Light Truck - Pick up8240 | Corbiere and Sons Contracting872202013-1Light Truck - Pick up8240Inv#006R01 |  |  | WF1-Handfalling |  |  | 1 | 240 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 872 | 202013-1 | 53510111 | Access | 0 | Project Manager | 110 | 2.4 | HR |  |  | 110 | 0 | 264 | 34.32 | 298.32 | 2020-01-09 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  | 53510106 Splitted cost from 53510104, 53510111, 53520101 53520102, 53520104 - these codes had cost on the given day |  |  |  |  | Project supervision |  |  | Project supervision | 0 |  |  | 36 | 43839 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting872202013-1Project Manager2.4264 | Corbiere and Sons Contracting872202013-1Project Manager2.4264Inv#006R01 | [5 empty] | 1 | 264 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 872 | 202013-1 | 53520101 | Clearing | 0 | Project Manager | 110 | 2.4 | HR |  |  | 110 | 0 | 264 | 34.32 | 298.32 | 2020-01-09 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | 53510106 Splitted cost from 53510104, 53510111, 53520101 53520102, 53520104 - these codes had cost on the given day |  |  |  |  | Project supervision |  |  | Project supervision | 0 |  |  | 36 | 43839 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting872202013-1Project Manager2.4264 | Corbiere and Sons Contracting872202013-1Project Manager2.4264Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 264 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 872 | 202013-1 | 53520102 | Clearing | 0 | Project Manager | 110 | 2.4 | HR |  |  | 110 | 0 | 264 | 34.32 | 298.32 | 2020-01-09 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | 53510106 Splitted cost from 53510104, 53510111, 53520101 53520102, 53520104 - these codes had cost on the given day |  |  |  |  | Project supervision |  |  | Project supervision | 0 |  |  | 36 | 43839 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting872202013-1Project Manager2.4264 | Corbiere and Sons Contracting872202013-1Project Manager2.4264Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 264 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 872 | 202013-1 | 53520104 | Clearing | 0 | Project Manager | 110 | 2.4 | HR |  |  | 110 | 0 | 264 | 34.32 | 298.32 | 2020-01-09 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  | 53510106 Splitted cost from 53510104, 53510111, 53520101 53520102, 53520104 - these codes had cost on the given day |  |  |  |  | Project supervision |  |  | Project supervision | 0 |  |  | 36 | 43839 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting872202013-1Project Manager2.4264 | Corbiere and Sons Contracting872202013-1Project Manager2.4264Inv#006R01 |  |  | WF1-Handfalling |  |  | 1 | 264 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 872 | 202013-1 | 53510111 | Access | 0 | Superintendent | 105 | 2.4 | HR |  |  | 105 | 0 | 252 | 32.76 | 284.76 | 2020-01-09 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  | 53510106 Splitted cost from 53510104, 53510111, 53520101 53520102, 53520104 - these codes had cost on the given day |  |  |  |  | Project supervision |  |  | Project supervision | 0 |  |  | 36 | 43839 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting872202013-1Superintendent2.4252 | Corbiere and Sons Contracting872202013-1Superintendent2.4252Inv#006R01 | [5 empty] | 1 | 252 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 872 | 202013-1 | 53520101 | Clearing | 0 | Superintendent | 105 | 2.4 | HR |  |  | 105 | 0 | 252 | 32.76 | 284.76 | 2020-01-09 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | 53510106 Splitted cost from 53510104, 53510111, 53520101 53520102, 53520104 - these codes had cost on the given day |  |  |  |  | Project supervision |  |  | Project supervision | 0 |  |  | 36 | 43839 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting872202013-1Superintendent2.4252 | Corbiere and Sons Contracting872202013-1Superintendent2.4252Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 252 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 872 | 202013-1 | 53520102 | Clearing | 0 | Superintendent | 105 | 2.4 | HR |  |  | 105 | 0 | 252 | 32.76 | 284.76 | 2020-01-09 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | 53510106 Splitted cost from 53510104, 53510111, 53520101 53520102, 53520104 - these codes had cost on the given day |  |  |  |  | Project supervision |  |  | Project supervision | 0 |  |  | 36 | 43839 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting872202013-1Superintendent2.4252 | Corbiere and Sons Contracting872202013-1Superintendent2.4252Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 252 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 872 | 202013-1 | 53520104 | Clearing | 0 | Superintendent | 105 | 2.4 | HR |  |  | 105 | 0 | 252 | 32.76 | 284.76 | 2020-01-09 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  | 53510106 Splitted cost from 53510104, 53510111, 53520101 53520102, 53520104 - these codes had cost on the given day |  |  |  |  | Project supervision |  |  | Project supervision | 0 |  |  | 36 | 43839 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting872202013-1Superintendent2.4252 | Corbiere and Sons Contracting872202013-1Superintendent2.4252Inv#006R01 |  |  | WF1-Handfalling |  |  | 1 | 252 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 872 | 202013-1 | 53510111 | Access | 0 | Project Coordinator | 80 | 2.4 | HR |  |  | 80 | 0 | 192 | 24.96 | 216.96 | 2020-01-09 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  | 53510106 Splitted cost from 53510104, 53510111, 53520101 53520102, 53520104 - these codes had cost on the given day |  |  |  |  | Project supervision |  |  | Project supervision | 0 |  |  | 36 | 43839 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting872202013-1Project Coordinator2.4192 | Corbiere and Sons Contracting872202013-1Project Coordinator2.4192Inv#006R01 | [5 empty] | 1 | 192 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 872 | 202013-1 | 53520101 | Clearing | 0 | Project Coordinator | 80 | 2.4 | HR |  |  | 80 | 0 | 192 | 24.96 | 216.96 | 2020-01-09 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | 53510106 Splitted cost from 53510104, 53510111, 53520101 53520102, 53520104 - these codes had cost on the given day |  |  |  |  | Project supervision |  |  | Project supervision | 0 |  |  | 36 | 43839 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting872202013-1Project Coordinator2.4192 | Corbiere and Sons Contracting872202013-1Project Coordinator2.4192Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 192 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 872 | 202013-1 | 53520102 | Clearing | 0 | Project Coordinator | 80 | 2.4 | HR |  |  | 80 | 0 | 192 | 24.96 | 216.96 | 2020-01-09 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | 53510106 Splitted cost from 53510104, 53510111, 53520101 53520102, 53520104 - these codes had cost on the given day |  |  |  |  | Project supervision |  |  | Project supervision | 0 |  |  | 36 | 43839 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting872202013-1Project Coordinator2.4192 | Corbiere and Sons Contracting872202013-1Project Coordinator2.4192Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 192 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 872 | 202013-1 | 53520104 | Clearing | 0 | Project Coordinator | 80 | 2.4 | HR |  |  | 80 | 0 | 192 | 24.96 | 216.96 | 2020-01-09 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  | 53510106 Splitted cost from 53510104, 53510111, 53520101 53520102, 53520104 - these codes had cost on the given day |  |  |  |  | Project supervision |  |  | Project supervision | 0 |  |  | 36 | 43839 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting872202013-1Project Coordinator2.4192 | Corbiere and Sons Contracting872202013-1Project Coordinator2.4192Inv#006R01 |  |  | WF1-Handfalling |  |  | 1 | 192 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 872 | 202013-1 | 53510111 | Access | 0 | Project Controls | 70 | 2.4 | HR |  |  | 70 | 0 | 168 | 21.84 | 189.84 | 2020-01-09 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  | 53510106 Splitted cost from 53510104, 53510111, 53520101 53520102, 53520104 - these codes had cost on the given day |  |  |  |  | Project supervision |  |  | Project supervision | 0 |  |  | 36 | 43839 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting872202013-1Project Controls2.4168 | Corbiere and Sons Contracting872202013-1Project Controls2.4168Inv#006R01 | [5 empty] | 1 | 168 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 872 | 202013-1 | 53520101 | Clearing | 0 | Project Controls | 70 | 2.4 | HR |  |  | 70 | 0 | 168 | 21.84 | 189.84 | 2020-01-09 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | 53510106 Splitted cost from 53510104, 53510111, 53520101 53520102, 53520104 - these codes had cost on the given day |  |  |  |  | Project supervision |  |  | Project supervision | 0 |  |  | 36 | 43839 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting872202013-1Project Controls2.4168 | Corbiere and Sons Contracting872202013-1Project Controls2.4168Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 168 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 872 | 202013-1 | 53520102 | Clearing | 0 | Project Controls | 70 | 2.4 | HR |  |  | 70 | 0 | 168 | 21.84 | 189.84 | 2020-01-09 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | 53510106 Splitted cost from 53510104, 53510111, 53520101 53520102, 53520104 - these codes had cost on the given day |  |  |  |  | Project supervision |  |  | Project supervision | 0 |  |  | 36 | 43839 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting872202013-1Project Controls2.4168 | Corbiere and Sons Contracting872202013-1Project Controls2.4168Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 168 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 872 | 202013-1 | 53520104 | Clearing | 0 | Project Controls | 70 | 2.4 | HR |  |  | 70 | 0 | 168 | 21.84 | 189.84 | 2020-01-09 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  | 53510106 Splitted cost from 53510104, 53510111, 53520101 53520102, 53520104 - these codes had cost on the given day |  |  |  |  | Project supervision |  |  | Project supervision | 0 |  |  | 36 | 43839 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting872202013-1Project Controls2.4168 | Corbiere and Sons Contracting872202013-1Project Controls2.4168Inv#006R01 |  |  | WF1-Handfalling |  |  | 1 | 168 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 872 | 202013-1 | 53510111 | Access | 0 | L.O.A. | 210 | 0.8 | DAY |  |  |  | 0 | 168 | 21.84 | 189.84 | 2020-01-09 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  | 53510106 Splitted cost from 53510104, 53510111, 53520101 53520102, 53520104 - these codes had cost on the given day |  |  |  |  | Project supervision |  |  | Project supervision | 0 |  |  | 36 | 43839 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting872202013-1L.O.A.0.8168 | Corbiere and Sons Contracting872202013-1L.O.A.0.8168Inv#006R01 | [5 empty] | 1 | 168 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 872 | 202013-1 | 53520101 | Clearing | 0 | L.O.A. | 210 | 0.8 | DAY |  |  |  | 0 | 168 | 21.84 | 189.84 | 2020-01-09 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | 53510106 Splitted cost from 53510104, 53510111, 53520101 53520102, 53520104 - these codes had cost on the given day |  |  |  |  | Project supervision |  |  | Project supervision | 0 |  |  | 36 | 43839 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting872202013-1L.O.A.0.8168 | Corbiere and Sons Contracting872202013-1L.O.A.0.8168Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 168 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 872 | 202013-1 | 53520102 | Clearing | 0 | L.O.A. | 210 | 0.8 | DAY |  |  |  | 0 | 168 | 21.84 | 189.84 | 2020-01-09 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | 53510106 Splitted cost from 53510104, 53510111, 53520101 53520102, 53520104 - these codes had cost on the given day |  |  |  |  | Project supervision |  |  | Project supervision | 0 |  |  | 36 | 43839 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting872202013-1L.O.A.0.8168 | Corbiere and Sons Contracting872202013-1L.O.A.0.8168Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 168 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 872 | 202013-1 | 53520104 | Clearing | 0 | L.O.A. | 210 | 0.8 | DAY |  |  |  | 0 | 168 | 21.84 | 189.84 | 2020-01-09 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  | 53510106 Splitted cost from 53510104, 53510111, 53520101 53520102, 53520104 - these codes had cost on the given day |  |  |  |  | Project supervision |  |  | Project supervision | 0 |  |  | 36 | 43839 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting872202013-1L.O.A.0.8168 | Corbiere and Sons Contracting872202013-1L.O.A.0.8168Inv#006R01 |  |  | WF1-Handfalling |  |  | 1 | 168 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 987 | 202013-22 | 53520102 | Clearing | 0 | Brusher | 202.5 | 5 | HR | 151.88 | 0 |  |  | 1012.5 | 131.625 | 1144.125 | 2020-01-14 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Excavators NS0EX-01, NS-EX-02, build road within 50m of B004 - NS-EX-04 raked towers B006-B004, Feller Buncher NS-FB-01 and Skidder NS-SK-01 completed road corridor clearing from Cavern Road to B003, - Grader NS-GR-01 and Dozer NS-DZ-01 performed winter clearing of Eldrardo Road - NS-BR-01 completed mulching between B004 and handcut area before breaking a track pully at 1:00pm , Float NS-RT-03 floated NS-DZ-01 and NS-GR-01 to Eldarodo Road for winter clearing, Floated COR-EX-011 from Greenwich to Beck |  |  | Fish Hatchery - A128 - B017 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting987202013-22Brusher51012.5 | Corbiere and Sons Contracting987202013-22Brusher51012.5Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1012.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 987 | 202013-22 | 53520101 | Clearing | 0 | Feller Buncher | 240 | 9 | HR | 180 | 0 |  |  | 2160 | 280.8 | 2440.8 | 2020-01-14 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Excavators NS0EX-01, NS-EX-02, build road within 50m of B004 - NS-EX-04 raked towers B006-B004, Feller Buncher NS-FB-01 and Skidder NS-SK-01 completed road corridor clearing from Cavern Road to B003, - Grader NS-GR-01 and Dozer NS-DZ-01 performed winter clearing of Eldrardo Road - NS-BR-01 completed mulching between B004 and handcut area before breaking a track pully at 1:00pm , Float NS-RT-03 floated NS-DZ-01 and NS-GR-01 to Eldarodo Road for winter clearing, Floated COR-EX-011 from Greenwich to Beck |  |  | Fish Hatchery - A128 - B017 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting987202013-22Feller Buncher92160 | Corbiere and Sons Contracting987202013-22Feller Buncher92160Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2160 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 987 | 202013-22 | 53520101 | Clearing | 0 | Skidder | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2020-01-14 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Excavators NS0EX-01, NS-EX-02, build road within 50m of B004 - NS-EX-04 raked towers B006-B004, Feller Buncher NS-FB-01 and Skidder NS-SK-01 completed road corridor clearing from Cavern Road to B003, - Grader NS-GR-01 and Dozer NS-DZ-01 performed winter clearing of Eldrardo Road - NS-BR-01 completed mulching between B004 and handcut area before breaking a track pully at 1:00pm , Float NS-RT-03 floated NS-DZ-01 and NS-GR-01 to Eldarodo Road for winter clearing, Floated COR-EX-011 from Greenwich to Beck |  |  | Fish Hatchery - A128 - B017 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting987202013-22Skidder 91539 | Corbiere and Sons Contracting987202013-22Skidder 91539Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 987 | 202013-22 | 53510111 | Access | 0 | Dozer D6 or equal | 135 | 8 | HR | 101.25 | 0 |  |  | 1080 | 140.4 | 1220.4 | 2020-01-14 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Excavators NS0EX-01, NS-EX-02, build road within 50m of B004 - NS-EX-04 raked towers B006-B004, Feller Buncher NS-FB-01 and Skidder NS-SK-01 completed road corridor clearing from Cavern Road to B003, - Grader NS-GR-01 and Dozer NS-DZ-01 performed winter clearing of Eldrardo Road - NS-BR-01 completed mulching between B004 and handcut area before breaking a track pully at 1:00pm , Float NS-RT-03 floated NS-DZ-01 and NS-GR-01 to Eldarodo Road for winter clearing, Floated COR-EX-011 from Greenwich to Beck |  |  | Fish Hatchery - A128 - B017 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting987202013-22Dozer D6 or equal81080 | Corbiere and Sons Contracting987202013-22Dozer D6 or equal81080Inv#006R01 | [5 empty] | 1 | 1080 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 987 | 202013-22 | 53520102 | Clearing | 0 | Excavator - 36 ton | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2020-01-14 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Excavators NS0EX-01, NS-EX-02, build road within 50m of B004 - NS-EX-04 raked towers B006-B004, Feller Buncher NS-FB-01 and Skidder NS-SK-01 completed road corridor clearing from Cavern Road to B003, - Grader NS-GR-01 and Dozer NS-DZ-01 performed winter clearing of Eldrardo Road - NS-BR-01 completed mulching between B004 and handcut area before breaking a track pully at 1:00pm , Float NS-RT-03 floated NS-DZ-01 and NS-GR-01 to Eldarodo Road for winter clearing, Floated COR-EX-011 from Greenwich to Beck |  |  | Fish Hatchery - A128 - B017 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting987202013-22Excavator - 36 ton91539 | Corbiere and Sons Contracting987202013-22Excavator - 36 ton91539Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 987 | 202013-22 | 53520102 | Clearing | 0 | Excavator Thumb - 30 - 50 ton | 13.5 | 9 | HR | 10.13 | 0 |  |  | 121.5 | 15.795 | 137.295 | 2020-01-14 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Excavators NS0EX-01, NS-EX-02, build road within 50m of B004 - NS-EX-04 raked towers B006-B004, Feller Buncher NS-FB-01 and Skidder NS-SK-01 completed road corridor clearing from Cavern Road to B003, - Grader NS-GR-01 and Dozer NS-DZ-01 performed winter clearing of Eldrardo Road - NS-BR-01 completed mulching between B004 and handcut area before breaking a track pully at 1:00pm , Float NS-RT-03 floated NS-DZ-01 and NS-GR-01 to Eldarodo Road for winter clearing, Floated COR-EX-011 from Greenwich to Beck |  |  | Fish Hatchery - A128 - B017 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting987202013-22Excavator Thumb - 30 - 50 ton9121.5 | Corbiere and Sons Contracting987202013-22Excavator Thumb - 30 - 50 ton9121.5Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 121.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 987 | 202013-22 | 53510111 | Access | 0 | Grader - Cat 12 to 14 or equal | 126 | 9 | HR | 94.5 | 0 |  |  | 1134 | 147.42 | 1281.42 | 2020-01-14 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Excavators NS0EX-01, NS-EX-02, build road within 50m of B004 - NS-EX-04 raked towers B006-B004, Feller Buncher NS-FB-01 and Skidder NS-SK-01 completed road corridor clearing from Cavern Road to B003, - Grader NS-GR-01 and Dozer NS-DZ-01 performed winter clearing of Eldrardo Road - NS-BR-01 completed mulching between B004 and handcut area before breaking a track pully at 1:00pm , Float NS-RT-03 floated NS-DZ-01 and NS-GR-01 to Eldarodo Road for winter clearing, Floated COR-EX-011 from Greenwich to Beck |  |  | Fish Hatchery - A128 - B017 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting987202013-22Grader - Cat 12 to 14 or equal91134 | Corbiere and Sons Contracting987202013-22Grader - Cat 12 to 14 or equal91134Inv#006R01 | [5 empty] | 1 | 1134 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 987 | 202013-22 | 53510111 | Access | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2020-01-14 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Excavators NS0EX-01, NS-EX-02, build road within 50m of B004 - NS-EX-04 raked towers B006-B004, Feller Buncher NS-FB-01 and Skidder NS-SK-01 completed road corridor clearing from Cavern Road to B003, - Grader NS-GR-01 and Dozer NS-DZ-01 performed winter clearing of Eldrardo Road - NS-BR-01 completed mulching between B004 and handcut area before breaking a track pully at 1:00pm , Float NS-RT-03 floated NS-DZ-01 and NS-GR-01 to Eldarodo Road for winter clearing, Floated COR-EX-011 from Greenwich to Beck |  |  | Fish Hatchery - A128 - B017 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting987202013-22Light Truck - Pick up20600 | Corbiere and Sons Contracting987202013-22Light Truck - Pick up20600Inv#006R01 | [5 empty] | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 987 | 202013-22 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 30 | HR | 22.5 | 0 |  |  | 900 | 117 | 1017 | 2020-01-14 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Excavators NS0EX-01, NS-EX-02, build road within 50m of B004 - NS-EX-04 raked towers B006-B004, Feller Buncher NS-FB-01 and Skidder NS-SK-01 completed road corridor clearing from Cavern Road to B003, - Grader NS-GR-01 and Dozer NS-DZ-01 performed winter clearing of Eldrardo Road - NS-BR-01 completed mulching between B004 and handcut area before breaking a track pully at 1:00pm , Float NS-RT-03 floated NS-DZ-01 and NS-GR-01 to Eldarodo Road for winter clearing, Floated COR-EX-011 from Greenwich to Beck |  |  | Fish Hatchery - A128 - B017 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting987202013-22Light Truck - Pick up30900 | Corbiere and Sons Contracting987202013-22Light Truck - Pick up30900Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 987 | 202013-22 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2020-01-14 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Excavators NS0EX-01, NS-EX-02, build road within 50m of B004 - NS-EX-04 raked towers B006-B004, Feller Buncher NS-FB-01 and Skidder NS-SK-01 completed road corridor clearing from Cavern Road to B003, - Grader NS-GR-01 and Dozer NS-DZ-01 performed winter clearing of Eldrardo Road - NS-BR-01 completed mulching between B004 and handcut area before breaking a track pully at 1:00pm , Float NS-RT-03 floated NS-DZ-01 and NS-GR-01 to Eldarodo Road for winter clearing, Floated COR-EX-011 from Greenwich to Beck |  |  | Fish Hatchery - A128 - B017 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting987202013-22Light Truck - Pick up20600 | Corbiere and Sons Contracting987202013-22Light Truck - Pick up20600Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 987 | 202013-22 | 53520101 | Clearing | 0 | Foreman | 95 | 6 | HR |  |  |  | 0 | 570 | 74.1 | 644.1 | 2020-01-14 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Excavators NS0EX-01, NS-EX-02, build road within 50m of B004 - NS-EX-04 raked towers B006-B004, Feller Buncher NS-FB-01 and Skidder NS-SK-01 completed road corridor clearing from Cavern Road to B003, - Grader NS-GR-01 and Dozer NS-DZ-01 performed winter clearing of Eldrardo Road - NS-BR-01 completed mulching between B004 and handcut area before breaking a track pully at 1:00pm , Float NS-RT-03 floated NS-DZ-01 and NS-GR-01 to Eldarodo Road for winter clearing, Floated COR-EX-011 from Greenwich to Beck |  |  | Fish Hatchery - A128 - B017 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting987202013-22Foreman6570 | Corbiere and Sons Contracting987202013-22Foreman6570Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 570 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 987 | 202013-22 | 53510111 | Access | 0 | Operator - Principle | 90 | 11 | HR |  |  |  | 0 | 990 | 128.7 | 1118.7 | 2020-01-14 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Excavators NS0EX-01, NS-EX-02, build road within 50m of B004 - NS-EX-04 raked towers B006-B004, Feller Buncher NS-FB-01 and Skidder NS-SK-01 completed road corridor clearing from Cavern Road to B003, - Grader NS-GR-01 and Dozer NS-DZ-01 performed winter clearing of Eldrardo Road - NS-BR-01 completed mulching between B004 and handcut area before breaking a track pully at 1:00pm , Float NS-RT-03 floated NS-DZ-01 and NS-GR-01 to Eldarodo Road for winter clearing, Floated COR-EX-011 from Greenwich to Beck |  |  | Fish Hatchery - A128 - B017 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting987202013-22Operator - Principle11990 | Corbiere and Sons Contracting987202013-22Operator - Principle11990Inv#006R01 | [5 empty] | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 987 | 202013-22 | 53510111 | Access | 0 | Operator - Principle | 90 | 11 | HR |  |  |  | 0 | 990 | 128.7 | 1118.7 | 2020-01-14 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Excavators NS0EX-01, NS-EX-02, build road within 50m of B004 - NS-EX-04 raked towers B006-B004, Feller Buncher NS-FB-01 and Skidder NS-SK-01 completed road corridor clearing from Cavern Road to B003, - Grader NS-GR-01 and Dozer NS-DZ-01 performed winter clearing of Eldrardo Road - NS-BR-01 completed mulching between B004 and handcut area before breaking a track pully at 1:00pm , Float NS-RT-03 floated NS-DZ-01 and NS-GR-01 to Eldarodo Road for winter clearing, Floated COR-EX-011 from Greenwich to Beck |  |  | Fish Hatchery - A128 - B017 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting987202013-22Operator - Principle11990 | Corbiere and Sons Contracting987202013-22Operator - Principle11990Inv#006R01 | [5 empty] | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 987 | 202013-22 | 53520101 | Clearing | 0 | Operator - Principle | 90 | 22 | HR |  |  |  | 0 | 1980 | 257.4 | 2237.4 | 2020-01-14 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Excavators NS0EX-01, NS-EX-02, build road within 50m of B004 - NS-EX-04 raked towers B006-B004, Feller Buncher NS-FB-01 and Skidder NS-SK-01 completed road corridor clearing from Cavern Road to B003, - Grader NS-GR-01 and Dozer NS-DZ-01 performed winter clearing of Eldrardo Road - NS-BR-01 completed mulching between B004 and handcut area before breaking a track pully at 1:00pm , Float NS-RT-03 floated NS-DZ-01 and NS-GR-01 to Eldarodo Road for winter clearing, Floated COR-EX-011 from Greenwich to Beck |  |  | Fish Hatchery - A128 - B017 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting987202013-22Operator - Principle221980 | Corbiere and Sons Contracting987202013-22Operator - Principle221980Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 1980 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 987 | 202013-22 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 22 | HR |  |  |  | 0 | 1980 | 257.4 | 2237.4 | 2020-01-14 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Excavators NS0EX-01, NS-EX-02, build road within 50m of B004 - NS-EX-04 raked towers B006-B004, Feller Buncher NS-FB-01 and Skidder NS-SK-01 completed road corridor clearing from Cavern Road to B003, - Grader NS-GR-01 and Dozer NS-DZ-01 performed winter clearing of Eldrardo Road - NS-BR-01 completed mulching between B004 and handcut area before breaking a track pully at 1:00pm , Float NS-RT-03 floated NS-DZ-01 and NS-GR-01 to Eldarodo Road for winter clearing, Floated COR-EX-011 from Greenwich to Beck |  |  | Fish Hatchery - A128 - B017 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting987202013-22Operator - Principle221980 | Corbiere and Sons Contracting987202013-22Operator - Principle221980Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1980 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 987 | 202013-22 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 18 | HR |  |  |  | 0 | 1620 | 210.6 | 1830.6 | 2020-01-14 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Excavators NS0EX-01, NS-EX-02, build road within 50m of B004 - NS-EX-04 raked towers B006-B004, Feller Buncher NS-FB-01 and Skidder NS-SK-01 completed road corridor clearing from Cavern Road to B003, - Grader NS-GR-01 and Dozer NS-DZ-01 performed winter clearing of Eldrardo Road - NS-BR-01 completed mulching between B004 and handcut area before breaking a track pully at 1:00pm , Float NS-RT-03 floated NS-DZ-01 and NS-GR-01 to Eldarodo Road for winter clearing, Floated COR-EX-011 from Greenwich to Beck |  |  | Fish Hatchery - A128 - B017 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting987202013-22Operator - Principle181620 | Corbiere and Sons Contracting987202013-22Operator - Principle181620Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1620 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 987 | 202013-22 | 53510111 | Access | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-01-14 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Excavators NS0EX-01, NS-EX-02, build road within 50m of B004 - NS-EX-04 raked towers B006-B004, Feller Buncher NS-FB-01 and Skidder NS-SK-01 completed road corridor clearing from Cavern Road to B003, - Grader NS-GR-01 and Dozer NS-DZ-01 performed winter clearing of Eldrardo Road - NS-BR-01 completed mulching between B004 and handcut area before breaking a track pully at 1:00pm , Float NS-RT-03 floated NS-DZ-01 and NS-GR-01 to Eldarodo Road for winter clearing, Floated COR-EX-011 from Greenwich to Beck |  |  | Fish Hatchery - A128 - B017 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting987202013-22L.O.A.2420 | Corbiere and Sons Contracting987202013-22L.O.A.2420Inv#006R01 | [5 empty] | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 987 | 202013-22 | 53520101 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-01-14 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Excavators NS0EX-01, NS-EX-02, build road within 50m of B004 - NS-EX-04 raked towers B006-B004, Feller Buncher NS-FB-01 and Skidder NS-SK-01 completed road corridor clearing from Cavern Road to B003, - Grader NS-GR-01 and Dozer NS-DZ-01 performed winter clearing of Eldrardo Road - NS-BR-01 completed mulching between B004 and handcut area before breaking a track pully at 1:00pm , Float NS-RT-03 floated NS-DZ-01 and NS-GR-01 to Eldarodo Road for winter clearing, Floated COR-EX-011 from Greenwich to Beck |  |  | Fish Hatchery - A128 - B017 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting987202013-22L.O.A.2420 | Corbiere and Sons Contracting987202013-22L.O.A.2420Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 987 | 202013-22 | 53520102 | Clearing | 0 | L.O.A. | 210 | 2 | DAY |  |  |  | 0 | 420 | 54.6 | 474.6 | 2020-01-14 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Excavators NS0EX-01, NS-EX-02, build road within 50m of B004 - NS-EX-04 raked towers B006-B004, Feller Buncher NS-FB-01 and Skidder NS-SK-01 completed road corridor clearing from Cavern Road to B003, - Grader NS-GR-01 and Dozer NS-DZ-01 performed winter clearing of Eldrardo Road - NS-BR-01 completed mulching between B004 and handcut area before breaking a track pully at 1:00pm , Float NS-RT-03 floated NS-DZ-01 and NS-GR-01 to Eldarodo Road for winter clearing, Floated COR-EX-011 from Greenwich to Beck |  |  | Fish Hatchery - A128 - B017 | 0 |  |  | 36 | 43845 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting987202013-22L.O.A.2420 | Corbiere and Sons Contracting987202013-22L.O.A.2420Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 420 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 873 | 202013-2-R1 | 53520102 | Clearing | 0 | Loader JD 524 to 624 or equal | 99 | 5 | HR | 74.25 | 0 |  |  | 495 | 64.35 | 559.35 | 2020-01-09 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | General Yard Maintenance |  |  | General Yard Maintenance | 0 |  |  | 36 | 43840 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting873202013-2-R1Loader JD 524 to 624 or equal5495 | Corbiere and Sons Contracting873202013-2-R1Loader JD 524 to 624 or equal5495Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 495 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 873 | 202013-2-R1 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2020-01-09 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | General Yard Maintenance |  |  | General Yard Maintenance | 0 |  |  | 36 | 43840 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting873202013-2-R1Light Truck - Pick up10300 | Corbiere and Sons Contracting873202013-2-R1Light Truck - Pick up10300Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 873 | 202013-2-R1 | 53520102 | Clearing | 0 | Operator - Apprentice | 60 | 10 | HR |  |  |  | 0 | 600 | 78 | 678 | 2020-01-09 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | General Yard Maintenance |  |  | General Yard Maintenance | 0 |  |  | 36 | 43840 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting873202013-2-R1Operator - Apprentice10600 | Corbiere and Sons Contracting873202013-2-R1Operator - Apprentice10600Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 874 | 202013-3 | 53510111 | Access | 0 | Dozer D6 or equal | 135 | 9 | HR | 101.25 | 0 |  |  | 1215 | 157.95 | 1372.95 | 2020-01-09 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 14 | Approved | snow removal on assembly and crane pads - ongoing | 9013 | Clearing pads |  |  | MacKenzie East - A030 - A035 | 0 |  |  | 36 | 43839 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting874202013-3Dozer D6 or equal91215 | Corbiere and Sons Contracting874202013-3Dozer D6 or equal91215Inv#006R01 | [5 empty] | 1 | 1215 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 874 | 202013-3 | 53510111 | Access | 0 | Operator - Principle | 90 | 11 | HR |  |  |  | 0 | 990 | 128.7 | 1118.7 | 2020-01-09 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 14 | Approved | snow removal on assembly and crane pads - ongoing | 9013 | Clearing pads |  |  | MacKenzie East - A030 - A035 | 0 |  |  | 36 | 43839 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting874202013-3Operator - Principle11990 | Corbiere and Sons Contracting874202013-3Operator - Principle11990Inv#006R01 | [5 empty] | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 874 | 202013-3 | 53510111 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-01-09 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 14 | Approved | snow removal on assembly and crane pads - ongoing | 9013 | Clearing pads |  |  | MacKenzie East - A030 - A035 | 0 |  |  | 36 | 43839 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting874202013-3L.O.A.1210 | Corbiere and Sons Contracting874202013-3L.O.A.1210Inv#006R01 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 875 | 202013-4 | 53510111 | Access | 0 | Excavator - 36 ton | 171 | 18 | HR | 128.25 | 0 |  |  | 3078 | 400.14 | 3478.14 | 2020-01-09 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Fuelling, cleaning tracks, escorting equipment, seperating gravel for sand truck and snow removal at Kabi pit, structure 036-046 snow removal |  |  | Beck Road W - Rd. Building - A036 - A046 | 0 |  |  | 36 | 43839 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting875202013-4Excavator - 36 ton183078 | Corbiere and Sons Contracting875202013-4Excavator - 36 ton183078Inv#006R01 | [5 empty] | 1 | 3078 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 875 | 202013-4 | 53510111 | Access | 0 | Light Truck - Pick up | 30 | 30 | HR | 22.5 | 0 |  |  | 900 | 117 | 1017 | 2020-01-09 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Fuelling, cleaning tracks, escorting equipment, seperating gravel for sand truck and snow removal at Kabi pit, structure 036-046 snow removal |  |  | Beck Road W - Rd. Building - A036 - A046 | 0 |  |  | 36 | 43839 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting875202013-4Light Truck - Pick up30900 | Corbiere and Sons Contracting875202013-4Light Truck - Pick up30900Inv#006R01 | [5 empty] | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 875 | 202013-4 | 53510111 | Access | 0 | Operator - Principle | 90 | 22 | HR |  |  |  | 0 | 1980 | 257.4 | 2237.4 | 2020-01-09 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Fuelling, cleaning tracks, escorting equipment, seperating gravel for sand truck and snow removal at Kabi pit, structure 036-046 snow removal |  |  | Beck Road W - Rd. Building - A036 - A046 | 0 |  |  | 36 | 43839 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting875202013-4Operator - Principle221980 | Corbiere and Sons Contracting875202013-4Operator - Principle221980Inv#006R01 | [5 empty] | 1 | 1980 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 875 | 202013-4 | 53510111 | Access | 0 | Labourer - General | 65 | 11 | HR |  |  |  | 0 | 715 | 92.95 | 807.95 | 2020-01-09 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Fuelling, cleaning tracks, escorting equipment, seperating gravel for sand truck and snow removal at Kabi pit, structure 036-046 snow removal |  |  | Beck Road W - Rd. Building - A036 - A046 | 0 |  |  | 36 | 43839 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting875202013-4Labourer - General11715 | Corbiere and Sons Contracting875202013-4Labourer - General11715Inv#006R01 | [5 empty] | 1 | 715 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 875 | 202013-4 | 53510111 | Access | 0 | L.O.A. | 210 | 3 | DAY |  |  |  | 0 | 630 | 81.9 | 711.9 | 2020-01-09 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Fuelling, cleaning tracks, escorting equipment, seperating gravel for sand truck and snow removal at Kabi pit, structure 036-046 snow removal |  |  | Beck Road W - Rd. Building - A036 - A046 | 0 |  |  | 36 | 43839 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting875202013-4L.O.A.3630 | Corbiere and Sons Contracting875202013-4L.O.A.3630Inv#006R01 | [5 empty] | 1 | 630 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 876 | 202013-5 | 53510111 | Access | 0 | Dozer D6 or equal | 135 | 9 | HR | 101.25 | 0 |  |  | 1215 | 157.95 | 1372.95 | 2020-01-09 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Eldorado - A055 - A079-Snow Removal |  |  | Eldorado - A055 - A079-Snow Removal | 0 |  |  | 37 | 43840 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting876202013-5Dozer D6 or equal91215 | Corbiere and Sons Contracting876202013-5Dozer D6 or equal91215Inv#006R01 | [5 empty] | 1 | 1215 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 876 | 202013-5 | 53510111 | Access | 0 | Operator - Principle | 90 | 11 | HR |  |  |  | 0 | 990 | 128.7 | 1118.7 | 2020-01-09 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Eldorado - A055 - A079-Snow Removal |  |  | Eldorado - A055 - A079-Snow Removal | 0 |  |  | 37 | 43840 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting876202013-5Operator - Principle11990 | Corbiere and Sons Contracting876202013-5Operator - Principle11990Inv#006R01 | [5 empty] | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 876 | 202013-5 | 53510111 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-01-09 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Eldorado - A055 - A079-Snow Removal |  |  | Eldorado - A055 - A079-Snow Removal | 0 |  |  | 37 | 43840 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting876202013-5L.O.A.1210 | Corbiere and Sons Contracting876202013-5L.O.A.1210Inv#006R01 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 877 | 202013-6 | 53510111 | Access | 0 | Dozer - D5 or equal | 99 | 9 | HR | 74.25 | 0 |  |  | 891 | 115.83 | 1006.83 | 2020-01-09 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Graders clearing snow from Ouimet Canyon and Beck road access roads, sander truck sanding at Ouimet canyon, Float truck moved rig mats from 118 to 132, moved 336 excavator from Ouimet Canyon to Beck Rd., 1 dozer at 99 West, 1 dozer at 116 East and West. Road Clearing into 81/82 & 76/94/95 to prep for gravel for Saturday. |  |  | Wind Farm - A080-A117 | 0 |  |  | 37 | 43840 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting877202013-6Dozer - D5 or equal9891 | Corbiere and Sons Contracting877202013-6Dozer - D5 or equal9891Inv#006R01 | [5 empty] | 1 | 891 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 877 | 202013-6 | 53510111 | Access | 0 | Excavator - 30 ton | 139.5 | 18 | HR | 104.63 | 0 |  |  | 2511 | 326.43 | 2837.43 | 2020-01-09 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Graders clearing snow from Ouimet Canyon and Beck road access roads, sander truck sanding at Ouimet canyon, Float truck moved rig mats from 118 to 132, moved 336 excavator from Ouimet Canyon to Beck Rd., 1 dozer at 99 West, 1 dozer at 116 East and West. Road Clearing into 81/82 & 76/94/95 to prep for gravel for Saturday. |  |  | Wind Farm - A080-A117 | 0 |  |  | 37 | 43840 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting877202013-6Excavator - 30 ton182511 | Corbiere and Sons Contracting877202013-6Excavator - 30 ton182511Inv#006R01 | [5 empty] | 1 | 2511 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 877 | 202013-6 | 53510111 | Access | 0 | Excavator - 36 ton | 171 | 18 | HR | 128.25 | 0 |  |  | 3078 | 400.14 | 3478.14 | 2020-01-09 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Graders clearing snow from Ouimet Canyon and Beck road access roads, sander truck sanding at Ouimet canyon, Float truck moved rig mats from 118 to 132, moved 336 excavator from Ouimet Canyon to Beck Rd., 1 dozer at 99 West, 1 dozer at 116 East and West. Road Clearing into 81/82 & 76/94/95 to prep for gravel for Saturday. |  |  | Wind Farm - A080-A117 | 0 |  |  | 37 | 43840 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting877202013-6Excavator - 36 ton183078 | Corbiere and Sons Contracting877202013-6Excavator - 36 ton183078Inv#006R01 | [5 empty] | 1 | 3078 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 877 | 202013-6 | 53510111 | Access | 0 | Grader - Cat 12 to 14 or equal | 126 | 18 | HR | 94.5 | 0 |  |  | 2268 | 294.84 | 2562.84 | 2020-01-09 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Graders clearing snow from Ouimet Canyon and Beck road access roads, sander truck sanding at Ouimet canyon, Float truck moved rig mats from 118 to 132, moved 336 excavator from Ouimet Canyon to Beck Rd., 1 dozer at 99 West, 1 dozer at 116 East and West. Road Clearing into 81/82 & 76/94/95 to prep for gravel for Saturday. |  |  | Wind Farm - A080-A117 | 0 |  |  | 37 | 43840 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting877202013-6Grader - Cat 12 to 14 or equal182268 | Corbiere and Sons Contracting877202013-6Grader - Cat 12 to 14 or equal182268Inv#006R01 | [5 empty] | 1 | 2268 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 877 | 202013-6 | 53510111 | Access | 0 | Sander Truck | 112.5 | 9 | HR | 84.38 | 0 |  |  | 1012.5 | 131.625 | 1144.125 | 2020-01-09 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Graders clearing snow from Ouimet Canyon and Beck road access roads, sander truck sanding at Ouimet canyon, Float truck moved rig mats from 118 to 132, moved 336 excavator from Ouimet Canyon to Beck Rd., 1 dozer at 99 West, 1 dozer at 116 East and West. Road Clearing into 81/82 & 76/94/95 to prep for gravel for Saturday. |  |  | Wind Farm - A080-A117 | 0 |  |  | 37 | 43840 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting877202013-6Sander Truck91012.5 | Corbiere and Sons Contracting877202013-6Sander Truck91012.5Inv#006R01 | [5 empty] | 1 | 1012.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 877 | 202013-6 | 53510111 | Access | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2020-01-09 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Graders clearing snow from Ouimet Canyon and Beck road access roads, sander truck sanding at Ouimet canyon, Float truck moved rig mats from 118 to 132, moved 336 excavator from Ouimet Canyon to Beck Rd., 1 dozer at 99 West, 1 dozer at 116 East and West. Road Clearing into 81/82 & 76/94/95 to prep for gravel for Saturday. |  |  | Wind Farm - A080-A117 | 0 |  |  | 37 | 43840 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting877202013-6Light Truck - Pick up20600 | Corbiere and Sons Contracting877202013-6Light Truck - Pick up20600Inv#006R01 | [5 empty] | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 877 | 202013-6 | 53510111 | Access | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2020-01-09 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Graders clearing snow from Ouimet Canyon and Beck road access roads, sander truck sanding at Ouimet canyon, Float truck moved rig mats from 118 to 132, moved 336 excavator from Ouimet Canyon to Beck Rd., 1 dozer at 99 West, 1 dozer at 116 East and West. Road Clearing into 81/82 & 76/94/95 to prep for gravel for Saturday. |  |  | Wind Farm - A080-A117 | 0 |  |  | 37 | 43840 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting877202013-6Light Truck - Pick up10300 | Corbiere and Sons Contracting877202013-6Light Truck - Pick up10300Inv#006R01 | [5 empty] | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 877 | 202013-6 | 53510111 | Access | 0 | Tractor Trailer - 60 Ton | 135 | 10 | HR | 101.25 | 0 |  |  | 1350 | 175.5 | 1525.5 | 2020-01-09 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Graders clearing snow from Ouimet Canyon and Beck road access roads, sander truck sanding at Ouimet canyon, Float truck moved rig mats from 118 to 132, moved 336 excavator from Ouimet Canyon to Beck Rd., 1 dozer at 99 West, 1 dozer at 116 East and West. Road Clearing into 81/82 & 76/94/95 to prep for gravel for Saturday. |  |  | Wind Farm - A080-A117 | 0 |  |  | 37 | 43840 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting877202013-6Tractor Trailer - 60 Ton101350 | Corbiere and Sons Contracting877202013-6Tractor Trailer - 60 Ton101350Inv#006R01 | [5 empty] | 1 | 1350 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 877 | 202013-6 | 53510111 | Access | 0 | Foreman | 95 | 12 | HR |  |  |  | 0 | 1140 | 148.2 | 1288.2 | 2020-01-09 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Graders clearing snow from Ouimet Canyon and Beck road access roads, sander truck sanding at Ouimet canyon, Float truck moved rig mats from 118 to 132, moved 336 excavator from Ouimet Canyon to Beck Rd., 1 dozer at 99 West, 1 dozer at 116 East and West. Road Clearing into 81/82 & 76/94/95 to prep for gravel for Saturday. |  |  | Wind Farm - A080-A117 | 0 |  |  | 37 | 43840 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting877202013-6Foreman121140 | Corbiere and Sons Contracting877202013-6Foreman121140Inv#006R01 | [5 empty] | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 877 | 202013-6 | 53510111 | Access | 0 | Operator - Principle | 90 | 88 | HR |  |  |  | 0 | 7920 | 1029.6 | 8949.6 | 2020-01-09 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Graders clearing snow from Ouimet Canyon and Beck road access roads, sander truck sanding at Ouimet canyon, Float truck moved rig mats from 118 to 132, moved 336 excavator from Ouimet Canyon to Beck Rd., 1 dozer at 99 West, 1 dozer at 116 East and West. Road Clearing into 81/82 & 76/94/95 to prep for gravel for Saturday. |  |  | Wind Farm - A080-A117 | 0 |  |  | 37 | 43840 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting877202013-6Operator - Principle887920 | Corbiere and Sons Contracting877202013-6Operator - Principle887920Inv#006R01 | [5 empty] | 1 | 7920 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 877 | 202013-6 | 53510111 | Access | 0 | Operator - Intermdiate | 75 | 11 | HR |  |  | 70 | 0 | 825 | 107.25 | 932.25 | 2020-01-09 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Graders clearing snow from Ouimet Canyon and Beck road access roads, sander truck sanding at Ouimet canyon, Float truck moved rig mats from 118 to 132, moved 336 excavator from Ouimet Canyon to Beck Rd., 1 dozer at 99 West, 1 dozer at 116 East and West. Road Clearing into 81/82 & 76/94/95 to prep for gravel for Saturday. |  |  | Wind Farm - A080-A117 | 0 |  |  | 37 | 43840 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting877202013-6Operator - Intermdiate11825 | Corbiere and Sons Contracting877202013-6Operator - Intermdiate11825Inv#006R01 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 877 | 202013-6 | 53510111 | Access | 0 | Labourer - Specialized | 75 | 11 | HR |  |  |  | 0 | 825 | 107.25 | 932.25 | 2020-01-09 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Graders clearing snow from Ouimet Canyon and Beck road access roads, sander truck sanding at Ouimet canyon, Float truck moved rig mats from 118 to 132, moved 336 excavator from Ouimet Canyon to Beck Rd., 1 dozer at 99 West, 1 dozer at 116 East and West. Road Clearing into 81/82 & 76/94/95 to prep for gravel for Saturday. |  |  | Wind Farm - A080-A117 | 0 |  |  | 37 | 43840 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting877202013-6Labourer - Specialized11825 | Corbiere and Sons Contracting877202013-6Labourer - Specialized11825Inv#006R01 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 877 | 202013-6 | 53520101 | Clearing | 0 | L.O.A. | 210 | 11 | DAY |  |  |  | 0 | 2310 | 300.3 | 2610.3 | 2020-01-09 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Graders clearing snow from Ouimet Canyon and Beck road access roads, sander truck sanding at Ouimet canyon, Float truck moved rig mats from 118 to 132, moved 336 excavator from Ouimet Canyon to Beck Rd., 1 dozer at 99 West, 1 dozer at 116 East and West. Road Clearing into 81/82 & 76/94/95 to prep for gravel for Saturday. |  |  | Wind Farm - A080-A117 | 0 |  |  | 37 | 43840 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting877202013-6L.O.A.112310 | Corbiere and Sons Contracting877202013-6L.O.A.112310Inv#006R01 |  |  | WF1-Merchantable Clearing |  |  | 1 | 2310 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 878 | 202013-7-R1 | 53520102 | Clearing | 0 | Brusher | 202.5 | 18 | HR | 151.88 | 0 |  |  | 3645 | 473.85 | 4118.85 | 2020-01-09 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding material from A080, A082, A084., Handfelling A087-A086, Cutting at Tower 81, Finish brushing and raking at 117 East, load 329 & 350 Linkbelt & float to 42 West, 336 Clear access rds into towers, walk equipment down to 122 to start raking & brushing |  |  | Wind Farm - A080-A117 | 0 |  |  | 37 | 43840 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting878202013-7-R1Brusher183645 | Corbiere and Sons Contracting878202013-7-R1Brusher183645Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 3645 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 878 | 202013-7-R1 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 18 | HR | 417.6 | 0 |  |  | 10022.4 | 1302.912 | 11325.312 | 2020-01-09 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding material from A080, A082, A084., Handfelling A087-A086, Cutting at Tower 81, Finish brushing and raking at 117 East, load 329 & 350 Linkbelt & float to 42 West, 336 Clear access rds into towers, walk equipment down to 122 to start raking & brushing |  |  | Wind Farm - A080-A117 | 0 |  |  | 37 | 43840 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting878202013-7-R1Grinder - 4710 Peterson or equal1810022.4 | Corbiere and Sons Contracting878202013-7-R1Grinder - 4710 Peterson or equal1810022.4Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 10022.4 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 878 | 202013-7-R1 | 53520102 | Clearing | 0 | Log Loader | 153 | 18 | HR | 114.75 | 0 |  |  | 2754 | 358.02 | 3112.02 | 2020-01-09 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding material from A080, A082, A084., Handfelling A087-A086, Cutting at Tower 81, Finish brushing and raking at 117 East, load 329 & 350 Linkbelt & float to 42 West, 336 Clear access rds into towers, walk equipment down to 122 to start raking & brushing |  |  | Wind Farm - A080-A117 | 0 |  |  | 37 | 43840 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting878202013-7-R1Log Loader182754 | Corbiere and Sons Contracting878202013-7-R1Log Loader182754Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2754 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 878 | 202013-7-R1 | 53520102 | Clearing | 0 | Mulcher | 205 | 4 | HR | 153.75 | 0 |  |  | 820 | 106.6 | 926.6 | 2020-01-09 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding material from A080, A082, A084., Handfelling A087-A086, Cutting at Tower 81, Finish brushing and raking at 117 East, load 329 & 350 Linkbelt & float to 42 West, 336 Clear access rds into towers, walk equipment down to 122 to start raking & brushing |  |  | Wind Farm - A080-A117 | 0 |  |  | 37 | 43840 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting878202013-7-R1Mulcher4820 | Corbiere and Sons Contracting878202013-7-R1Mulcher4820Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 820 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 878 | 202013-7-R1 | 53520104 | Clearing | 0 | Chainsaw and consummables | 120 | 8 | Day |  | 0 |  |  | 960 | 124.8 | 1084.8 | 2020-01-09 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding material from A080, A082, A084., Handfelling A087-A086, Cutting at Tower 81, Finish brushing and raking at 117 East, load 329 & 350 Linkbelt & float to 42 West, 336 Clear access rds into towers, walk equipment down to 122 to start raking & brushing |  |  | Wind Farm - A080-A117 | 0 |  |  | 37 | 43840 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting878202013-7-R1Chainsaw and consummables8960 | Corbiere and Sons Contracting878202013-7-R1Chainsaw and consummables8960Inv#006R01 |  |  | WF1-Handfalling |  |  | 1 | 960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 878 | 202013-7-R1 | 53520102 | Clearing | 0 | Excavator - 36 ton | 171 | 18 | HR | 128.25 | 0 |  |  | 3078 | 400.14 | 3478.14 | 2020-01-09 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding material from A080, A082, A084., Handfelling A087-A086, Cutting at Tower 81, Finish brushing and raking at 117 East, load 329 & 350 Linkbelt & float to 42 West, 336 Clear access rds into towers, walk equipment down to 122 to start raking & brushing |  |  | Wind Farm - A080-A117 | 0 |  |  | 37 | 43840 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting878202013-7-R1Excavator - 36 ton183078 | Corbiere and Sons Contracting878202013-7-R1Excavator - 36 ton183078Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 3078 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 878 | 202013-7-R1 | 53520102 | Clearing | 0 | Excavator - 36 ton | 171 | 9 | HR | 128.25 | 0 |  |  | 1539 | 200.07 | 1739.07 | 2020-01-09 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding material from A080, A082, A084., Handfelling A087-A086, Cutting at Tower 81, Finish brushing and raking at 117 East, load 329 & 350 Linkbelt & float to 42 West, 336 Clear access rds into towers, walk equipment down to 122 to start raking & brushing |  |  | Wind Farm - A080-A117 | 0 |  |  | 37 | 43840 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting878202013-7-R1Excavator - 36 ton91539 | Corbiere and Sons Contracting878202013-7-R1Excavator - 36 ton91539Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1539 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 878 | 202013-7-R1 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2020-01-09 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding material from A080, A082, A084., Handfelling A087-A086, Cutting at Tower 81, Finish brushing and raking at 117 East, load 329 & 350 Linkbelt & float to 42 West, 336 Clear access rds into towers, walk equipment down to 122 to start raking & brushing |  |  | Wind Farm - A080-A117 | 0 |  |  | 37 | 43840 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting878202013-7-R1Light Truck - Pick up20600 | Corbiere and Sons Contracting878202013-7-R1Light Truck - Pick up20600Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 878 | 202013-7-R1 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 30 | HR | 22.5 | 0 |  |  | 900 | 117 | 1017 | 2020-01-09 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding material from A080, A082, A084., Handfelling A087-A086, Cutting at Tower 81, Finish brushing and raking at 117 East, load 329 & 350 Linkbelt & float to 42 West, 336 Clear access rds into towers, walk equipment down to 122 to start raking & brushing |  |  | Wind Farm - A080-A117 | 0 |  |  | 37 | 43840 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting878202013-7-R1Light Truck - Pick up30900 | Corbiere and Sons Contracting878202013-7-R1Light Truck - Pick up30900Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 900 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 878 | 202013-7-R1 | 53520104 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2020-01-09 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding material from A080, A082, A084., Handfelling A087-A086, Cutting at Tower 81, Finish brushing and raking at 117 East, load 329 & 350 Linkbelt & float to 42 West, 336 Clear access rds into towers, walk equipment down to 122 to start raking & brushing |  |  | Wind Farm - A080-A117 | 0 |  |  | 37 | 43840 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting878202013-7-R1Light Truck - Pick up20600 | Corbiere and Sons Contracting878202013-7-R1Light Truck - Pick up20600Inv#006R01 |  |  | WF1-Handfalling |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 878 | 202013-7-R1 | 53520104 | Clearing | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2020-01-09 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding material from A080, A082, A084., Handfelling A087-A086, Cutting at Tower 81, Finish brushing and raking at 117 East, load 329 & 350 Linkbelt & float to 42 West, 336 Clear access rds into towers, walk equipment down to 122 to start raking & brushing |  |  | Wind Farm - A080-A117 | 0 |  |  | 37 | 43840 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting878202013-7-R1Light Truck - Pick up20600 | Corbiere and Sons Contracting878202013-7-R1Light Truck - Pick up20600Inv#006R01 |  |  | WF1-Handfalling |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 878 | 202013-7-R1 | 53520104 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  |  | 0 | 1140 | 148.2 | 1288.2 | 2020-01-09 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding material from A080, A082, A084., Handfelling A087-A086, Cutting at Tower 81, Finish brushing and raking at 117 East, load 329 & 350 Linkbelt & float to 42 West, 336 Clear access rds into towers, walk equipment down to 122 to start raking & brushing |  |  | Wind Farm - A080-A117 | 0 |  |  | 37 | 43840 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting878202013-7-R1Foreman121140 | Corbiere and Sons Contracting878202013-7-R1Foreman121140Inv#006R01 |  |  | WF1-Handfalling |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 878 | 202013-7-R1 | 53520104 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  |  | 0 | 1140 | 148.2 | 1288.2 | 2020-01-09 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding material from A080, A082, A084., Handfelling A087-A086, Cutting at Tower 81, Finish brushing and raking at 117 East, load 329 & 350 Linkbelt & float to 42 West, 336 Clear access rds into towers, walk equipment down to 122 to start raking & brushing |  |  | Wind Farm - A080-A117 | 0 |  |  | 37 | 43840 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting878202013-7-R1Foreman121140 | Corbiere and Sons Contracting878202013-7-R1Foreman121140Inv#006R01 |  |  | WF1-Handfalling |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 878 | 202013-7-R1 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 22 | HR |  |  |  | 0 | 1980 | 257.4 | 2237.4 | 2020-01-09 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding material from A080, A082, A084., Handfelling A087-A086, Cutting at Tower 81, Finish brushing and raking at 117 East, load 329 & 350 Linkbelt & float to 42 West, 336 Clear access rds into towers, walk equipment down to 122 to start raking & brushing |  |  | Wind Farm - A080-A117 | 0 |  |  | 37 | 43840 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting878202013-7-R1Operator - Principle221980 | Corbiere and Sons Contracting878202013-7-R1Operator - Principle221980Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1980 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 878 | 202013-7-R1 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 66 | HR |  |  |  | 0 | 5940 | 772.2 | 6712.2 | 2020-01-09 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding material from A080, A082, A084., Handfelling A087-A086, Cutting at Tower 81, Finish brushing and raking at 117 East, load 329 & 350 Linkbelt & float to 42 West, 336 Clear access rds into towers, walk equipment down to 122 to start raking & brushing |  |  | Wind Farm - A080-A117 | 0 |  |  | 37 | 43840 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting878202013-7-R1Operator - Principle665940 | Corbiere and Sons Contracting878202013-7-R1Operator - Principle665940Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 5940 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 878 | 202013-7-R1 | 53520104 | Clearing | 0 | Labourer - Specialized | 75 | 66 | HR |  |  |  | 0 | 4950 | 643.5 | 5593.5 | 2020-01-09 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding material from A080, A082, A084., Handfelling A087-A086, Cutting at Tower 81, Finish brushing and raking at 117 East, load 329 & 350 Linkbelt & float to 42 West, 336 Clear access rds into towers, walk equipment down to 122 to start raking & brushing |  |  | Wind Farm - A080-A117 | 0 |  |  | 37 | 43840 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting878202013-7-R1Labourer - Specialized664950 | Corbiere and Sons Contracting878202013-7-R1Labourer - Specialized664950Inv#006R01 |  |  | WF1-Handfalling |  |  | 1 | 4950 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 878 | 202013-7-R1 | 53520102 | Clearing | 0 | L.O.A. | 210 | 8 | DAY |  |  |  | 0 | 1680 | 218.4 | 1898.4 | 2020-01-09 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding material from A080, A082, A084., Handfelling A087-A086, Cutting at Tower 81, Finish brushing and raking at 117 East, load 329 & 350 Linkbelt & float to 42 West, 336 Clear access rds into towers, walk equipment down to 122 to start raking & brushing |  |  | Wind Farm - A080-A117 | 0 |  |  | 37 | 43840 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting878202013-7-R1L.O.A.81680 | Corbiere and Sons Contracting878202013-7-R1L.O.A.81680Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1680 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 878 | 202013-7-R1 | 53520104 | Clearing | 0 | L.O.A. | 210 | 8 | DAY |  |  |  | 0 | 1680 | 218.4 | 1898.4 | 2020-01-09 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Grinding material from A080, A082, A084., Handfelling A087-A086, Cutting at Tower 81, Finish brushing and raking at 117 East, load 329 & 350 Linkbelt & float to 42 West, 336 Clear access rds into towers, walk equipment down to 122 to start raking & brushing |  |  | Wind Farm - A080-A117 | 0 |  |  | 37 | 43840 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting878202013-7-R1L.O.A.81680 | Corbiere and Sons Contracting878202013-7-R1L.O.A.81680Inv#006R01 |  |  | WF1-Handfalling |  |  | 1 | 1680 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 879 | 202013-8 | 53520102 | Clearing | 0 | Feller Buncher | 240 | 36 | HR | 180 | 0 |  |  | 8640 | 1123.2 | 9763.2 | 2020-01-09 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing from A132 to A134 |  |  | Fish Hatchery - A128 - B017 | 0 |  |  | 37 | 43840 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting879202013-8Feller Buncher368640 | Corbiere and Sons Contracting879202013-8Feller Buncher368640Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 8640 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 879 | 202013-8 | 53520102 | Clearing | 0 | Skidder | 171 | 27 | HR | 128.25 | 0 |  |  | 4617 | 600.21 | 5217.21 | 2020-01-09 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing from A132 to A134 |  |  | Fish Hatchery - A128 - B017 | 0 |  |  | 37 | 43840 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting879202013-8Skidder 274617 | Corbiere and Sons Contracting879202013-8Skidder 274617Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 4617 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 879 | 202013-8 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 40 | HR | 22.5 | 0 |  |  | 1200 | 156 | 1356 | 2020-01-09 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing from A132 to A134 |  |  | Fish Hatchery - A128 - B017 | 0 |  |  | 37 | 43840 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting879202013-8Light Truck - Pick up401200 | Corbiere and Sons Contracting879202013-8Light Truck - Pick up401200Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1200 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 879 | 202013-8 | 53520102 | Clearing | 0 | Foreman | 95 | 12 | HR |  |  |  | 0 | 1140 | 148.2 | 1288.2 | 2020-01-09 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing from A132 to A134 |  |  | Fish Hatchery - A128 - B017 | 0 |  |  | 37 | 43840 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting879202013-8Foreman121140 | Corbiere and Sons Contracting879202013-8Foreman121140Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 879 | 202013-8 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 77 | HR |  |  |  | 0 | 6930 | 900.9 | 7830.9 | 2020-01-09 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing from A132 to A134 |  |  | Fish Hatchery - A128 - B017 | 0 |  |  | 37 | 43840 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting879202013-8Operator - Principle776930 | Corbiere and Sons Contracting879202013-8Operator - Principle776930Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 6930 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 879 | 202013-8 | 53520102 | Clearing | 0 | L.O.A. | 210 | 8 | DAY |  |  |  | 0 | 1680 | 218.4 | 1898.4 | 2020-01-09 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Clearing from A132 to A134 |  |  | Fish Hatchery - A128 - B017 | 0 |  |  | 37 | 43840 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting879202013-8L.O.A.81680 | Corbiere and Sons Contracting879202013-8L.O.A.81680Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1680 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 901 | 202014-1 | 53510107 | Access | 0 | Light Truck - Pick up | 30 | 4.4444 | HR | 22.5 | 0 |  |  | 133.3333 | 17.3333 | 150.6666 | 2020-01-04 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Access Mob/Demob |  | VC7556-2019-017 | TBD - waiting on PO |  | 53510106 Splitted cost to 53510102, 53510104, 53510107, 53510111, 53520101, 53520102, 53520104, 53560101, 53560103- these codes had cost on the given day |  |  |  |  | Project supervision |  |  |  | 0 |  |  | 36 | 43841 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting901202014-1Light Truck - Pick up4.4444444133.3333 | Corbiere and Sons Contracting901202014-1Light Truck - Pick up4.4444444133.3333Inv#006R01 |  | WF1 Mob/Demob | WF1 Mob/Demob |  | 0.5 | 0.5 | 66.6667 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 901 | 202014-1 | 53510111 | Access | 0 | Light Truck - Pick up | 30 | 4.4444 | HR | 22.5 | 0 |  |  | 133.3333 | 17.3333 | 150.6666 | 2020-01-04 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  | 53510106 Splitted cost to 53510102, 53510104, 53510107, 53510111, 53520101, 53520102, 53520104, 53560101, 53560103- these codes had cost on the given day |  |  |  |  | Project supervision |  |  |  | 0 |  |  | 36 | 43841 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting901202014-1Light Truck - Pick up4.4444444133.3333 | Corbiere and Sons Contracting901202014-1Light Truck - Pick up4.4444444133.3333Inv#006R01 |  | WF1 Mob/Demob |  |  | 0.5 | 0.5 | 66.6667 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 901 | 202014-1 | 53520101 | Clearing | 0 | Light Truck - Pick up | 30 | 4.4444 | HR | 22.5 | 0 |  |  | 133.3333 | 17.3333 | 150.6666 | 2020-01-04 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | 53510106 Splitted cost to 53510102, 53510104, 53510107, 53510111, 53520101, 53520102, 53520104, 53560101, 53560103- these codes had cost on the given day |  |  |  |  | Project supervision |  |  |  | 0 |  |  | 36 | 43841 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting901202014-1Light Truck - Pick up4.4444444133.3333 | Corbiere and Sons Contracting901202014-1Light Truck - Pick up4.4444444133.3333Inv#006R01 |  | WF1 Mob/Demob | WF1-Merchantable Clearing |  | 0.5 | 0.5 | 66.6667 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 901 | 202014-1 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 4.4444 | HR | 22.5 | 0 |  |  | 133.3333 | 17.3333 | 150.6666 | 2020-01-04 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | 53510106 Splitted cost to 53510102, 53510104, 53510107, 53510111, 53520101, 53520102, 53520104, 53560101, 53560103- these codes had cost on the given day |  |  |  |  | Project supervision |  |  |  | 0 |  |  | 36 | 43841 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting901202014-1Light Truck - Pick up4.4444444133.3333 | Corbiere and Sons Contracting901202014-1Light Truck - Pick up4.4444444133.3333Inv#006R01 |  | WF1 Mob/Demob | WF1-Non-merchantable Clearing |  | 0.5 | 0.5 | 66.6667 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 901 | 202014-1 | 53520104 | Clearing | 0 | Light Truck - Pick up | 30 | 4.4444 | HR | 22.5 | 0 |  |  | 133.3333 | 17.3333 | 150.6666 | 2020-01-04 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  | 53510106 Splitted cost to 53510102, 53510104, 53510107, 53510111, 53520101, 53520102, 53520104, 53560101, 53560103- these codes had cost on the given day |  |  |  |  | Project supervision |  |  |  | 0 |  |  | 36 | 43841 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting901202014-1Light Truck - Pick up4.4444444133.3333 | Corbiere and Sons Contracting901202014-1Light Truck - Pick up4.4444444133.3333Inv#006R01 |  | WF1 Mob/Demob | WF1-Handfalling |  | 0.5 | 0.5 | 66.6667 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 901 | 202014-1 | 53510107 | Access | 0 | Project Manager | 110 | 1.3333 | HR |  |  | 110 | 0 | 146.6667 | 19.0667 | 165.7334 | 2020-01-04 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Access Mob/Demob |  | VC7556-2019-017 | TBD - waiting on PO |  | 53510106 Splitted cost to 53510102, 53510104, 53510107, 53510111, 53520101, 53520102, 53520104, 53560101, 53560103- these codes had cost on the given day |  |  |  |  | Project supervision |  |  |  | 0 |  |  | 36 | 43841 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting901202014-1Project Manager1.3333333146.6667 | Corbiere and Sons Contracting901202014-1Project Manager1.3333333146.6667Inv#006R01 |  | WF1 Mob/Demob | WF1 Mob/Demob |  | 0.5 | 0.5 | 73.3333 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 901 | 202014-1 | 53510111 | Access | 0 | Project Manager | 110 | 1.3333 | HR |  |  | 110 | 0 | 146.6667 | 19.0667 | 165.7334 | 2020-01-04 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  | 53510106 Splitted cost to 53510102, 53510104, 53510107, 53510111, 53520101, 53520102, 53520104, 53560101, 53560103- these codes had cost on the given day |  |  |  |  | Project supervision |  |  |  | 0 |  |  | 36 | 43841 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting901202014-1Project Manager1.3333333146.6667 | Corbiere and Sons Contracting901202014-1Project Manager1.3333333146.6667Inv#006R01 |  | WF1 Mob/Demob |  |  | 0.5 | 0.5 | 73.3333 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 901 | 202014-1 | 53520101 | Clearing | 0 | Project Manager | 110 | 1.3333 | HR |  |  | 110 | 0 | 146.6667 | 19.0667 | 165.7334 | 2020-01-04 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | 53510106 Splitted cost to 53510102, 53510104, 53510107, 53510111, 53520101, 53520102, 53520104, 53560101, 53560103- these codes had cost on the given day |  |  |  |  | Project supervision |  |  |  | 0 |  |  | 36 | 43841 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting901202014-1Project Manager1.3333333146.6667 | Corbiere and Sons Contracting901202014-1Project Manager1.3333333146.6667Inv#006R01 |  | WF1 Mob/Demob | WF1-Merchantable Clearing |  | 0.5 | 0.5 | 73.3333 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 901 | 202014-1 | 53520102 | Clearing | 0 | Project Manager | 110 | 1.3333 | HR |  |  | 110 | 0 | 146.6667 | 19.0667 | 165.7334 | 2020-01-04 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | 53510106 Splitted cost to 53510102, 53510104, 53510107, 53510111, 53520101, 53520102, 53520104, 53560101, 53560103- these codes had cost on the given day |  |  |  |  | Project supervision |  |  |  | 0 |  |  | 36 | 43841 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting901202014-1Project Manager1.3333333146.6667 | Corbiere and Sons Contracting901202014-1Project Manager1.3333333146.6667Inv#006R01 |  | WF1 Mob/Demob | WF1-Non-merchantable Clearing |  | 0.5 | 0.5 | 73.3333 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 901 | 202014-1 | 53520104 | Clearing | 0 | Project Manager | 110 | 1.3333 | HR |  |  | 110 | 0 | 146.6667 | 19.0667 | 165.7334 | 2020-01-04 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  | 53510106 Splitted cost to 53510102, 53510104, 53510107, 53510111, 53520101, 53520102, 53520104, 53560101, 53560103- these codes had cost on the given day |  |  |  |  | Project supervision |  |  |  | 0 |  |  | 36 | 43841 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting901202014-1Project Manager1.3333333146.6667 | Corbiere and Sons Contracting901202014-1Project Manager1.3333333146.6667Inv#006R01 |  | WF1 Mob/Demob | WF1-Handfalling |  | 0.5 | 0.5 | 73.3333 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 901 | 202014-1 | 53510107 | Access | 0 | Superintendent | 105 | 1.3333 | HR |  |  | 105 | 0 | 140 | 18.2 | 158.2 | 2020-01-04 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Access Mob/Demob |  | VC7556-2019-017 | TBD - waiting on PO |  | 53510106 Splitted cost to 53510102, 53510104, 53510107, 53510111, 53520101, 53520102, 53520104, 53560101, 53560103- these codes had cost on the given day |  |  |  |  | Project supervision |  |  |  | 0 |  |  | 36 | 43841 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting901202014-1Superintendent1.3333333140 | Corbiere and Sons Contracting901202014-1Superintendent1.3333333140Inv#006R01 |  | WF1 Mob/Demob | WF1 Mob/Demob |  | 0.5 | 0.5 | 70 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 901 | 202014-1 | 53510111 | Access | 0 | Superintendent | 105 | 1.3333 | HR |  |  | 105 | 0 | 140 | 18.2 | 158.2 | 2020-01-04 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  | 53510106 Splitted cost to 53510102, 53510104, 53510107, 53510111, 53520101, 53520102, 53520104, 53560101, 53560103- these codes had cost on the given day |  |  |  |  | Project supervision |  |  |  | 0 |  |  | 36 | 43841 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting901202014-1Superintendent1.3333333140 | Corbiere and Sons Contracting901202014-1Superintendent1.3333333140Inv#006R01 |  | WF1 Mob/Demob |  |  | 0.5 | 0.5 | 70 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 901 | 202014-1 | 53520101 | Clearing | 0 | Superintendent | 105 | 1.3333 | HR |  |  | 105 | 0 | 140 | 18.2 | 158.2 | 2020-01-04 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | 53510106 Splitted cost to 53510102, 53510104, 53510107, 53510111, 53520101, 53520102, 53520104, 53560101, 53560103- these codes had cost on the given day |  |  |  |  | Project supervision |  |  |  | 0 |  |  | 36 | 43841 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting901202014-1Superintendent1.3333333140 | Corbiere and Sons Contracting901202014-1Superintendent1.3333333140Inv#006R01 |  | WF1 Mob/Demob | WF1-Merchantable Clearing |  | 0.5 | 0.5 | 70 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 901 | 202014-1 | 53520102 | Clearing | 0 | Superintendent | 105 | 1.3333 | HR |  |  | 105 | 0 | 140 | 18.2 | 158.2 | 2020-01-04 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | 53510106 Splitted cost to 53510102, 53510104, 53510107, 53510111, 53520101, 53520102, 53520104, 53560101, 53560103- these codes had cost on the given day |  |  |  |  | Project supervision |  |  |  | 0 |  |  | 36 | 43841 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting901202014-1Superintendent1.3333333140 | Corbiere and Sons Contracting901202014-1Superintendent1.3333333140Inv#006R01 |  | WF1 Mob/Demob | WF1-Non-merchantable Clearing |  | 0.5 | 0.5 | 70 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 901 | 202014-1 | 53520104 | Clearing | 0 | Superintendent | 105 | 1.3333 | HR |  |  | 105 | 0 | 140 | 18.2 | 158.2 | 2020-01-04 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  | 53510106 Splitted cost to 53510102, 53510104, 53510107, 53510111, 53520101, 53520102, 53520104, 53560101, 53560103- these codes had cost on the given day |  |  |  |  | Project supervision |  |  |  | 0 |  |  | 36 | 43841 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting901202014-1Superintendent1.3333333140 | Corbiere and Sons Contracting901202014-1Superintendent1.3333333140Inv#006R01 |  | WF1 Mob/Demob | WF1-Handfalling |  | 0.5 | 0.5 | 70 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 901 | 202014-1 | 53510107 | Access | 0 | Project Coordinator | 80 | 1.3333 | HR |  |  | 80 | 0 | 106.6667 | 13.8667 | 120.5334 | 2020-01-04 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Access Mob/Demob |  | VC7556-2019-017 | TBD - waiting on PO |  | 53510106 Splitted cost to 53510102, 53510104, 53510107, 53510111, 53520101, 53520102, 53520104, 53560101, 53560103- these codes had cost on the given day |  |  |  |  | Project supervision |  |  |  | 0 |  |  | 36 | 43841 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting901202014-1Project Coordinator1.3333333106.6667 | Corbiere and Sons Contracting901202014-1Project Coordinator1.3333333106.6667Inv#006R01 |  | WF1 Mob/Demob | WF1 Mob/Demob |  | 0.5 | 0.5 | 53.3334 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 901 | 202014-1 | 53510111 | Access | 0 | Project Coordinator | 80 | 1.3333 | HR |  |  | 80 | 0 | 106.6667 | 13.8667 | 120.5334 | 2020-01-04 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  | 53510106 Splitted cost to 53510102, 53510104, 53510107, 53510111, 53520101, 53520102, 53520104, 53560101, 53560103- these codes had cost on the given day |  |  |  |  | Project supervision |  |  |  | 0 |  |  | 36 | 43841 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting901202014-1Project Coordinator1.3333333106.6667 | Corbiere and Sons Contracting901202014-1Project Coordinator1.3333333106.6667Inv#006R01 |  | WF1 Mob/Demob |  |  | 0.5 | 0.5 | 53.3334 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 901 | 202014-1 | 53520101 | Clearing | 0 | Project Coordinator | 80 | 1.3333 | HR |  |  | 80 | 0 | 106.6667 | 13.8667 | 120.5334 | 2020-01-04 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | 53510106 Splitted cost to 53510102, 53510104, 53510107, 53510111, 53520101, 53520102, 53520104, 53560101, 53560103- these codes had cost on the given day |  |  |  |  | Project supervision |  |  |  | 0 |  |  | 36 | 43841 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting901202014-1Project Coordinator1.3333333106.6667 | Corbiere and Sons Contracting901202014-1Project Coordinator1.3333333106.6667Inv#006R01 |  | WF1 Mob/Demob | WF1-Merchantable Clearing |  | 0.5 | 0.5 | 53.3334 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 901 | 202014-1 | 53520102 | Clearing | 0 | Project Coordinator | 80 | 1.3333 | HR |  |  | 80 | 0 | 106.6667 | 13.8667 | 120.5334 | 2020-01-04 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | 53510106 Splitted cost to 53510102, 53510104, 53510107, 53510111, 53520101, 53520102, 53520104, 53560101, 53560103- these codes had cost on the given day |  |  |  |  | Project supervision |  |  |  | 0 |  |  | 36 | 43841 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting901202014-1Project Coordinator1.3333333106.6667 | Corbiere and Sons Contracting901202014-1Project Coordinator1.3333333106.6667Inv#006R01 |  | WF1 Mob/Demob | WF1-Non-merchantable Clearing |  | 0.5 | 0.5 | 53.3334 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 901 | 202014-1 | 53520104 | Clearing | 0 | Project Coordinator | 80 | 1.3333 | HR |  |  | 80 | 0 | 106.6667 | 13.8667 | 120.5334 | 2020-01-04 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  | 53510106 Splitted cost to 53510102, 53510104, 53510107, 53510111, 53520101, 53520102, 53520104, 53560101, 53560103- these codes had cost on the given day |  |  |  |  | Project supervision |  |  |  | 0 |  |  | 36 | 43841 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting901202014-1Project Coordinator1.3333333106.6667 | Corbiere and Sons Contracting901202014-1Project Coordinator1.3333333106.6667Inv#006R01 |  | WF1 Mob/Demob | WF1-Handfalling |  | 0.5 | 0.5 | 53.3334 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 901 | 202014-1 | 53510107 | Access | 0 | Project Controls | 70 | 1.3333 | HR |  |  | 70 | 0 | 93.3333 | 12.1333 | 105.4666 | 2020-01-04 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Access Mob/Demob |  | VC7556-2019-017 | TBD - waiting on PO |  | 53510106 Splitted cost to 53510102, 53510104, 53510107, 53510111, 53520101, 53520102, 53520104, 53560101, 53560103- these codes had cost on the given day |  |  |  |  | Project supervision |  |  |  | 0 |  |  | 36 | 43841 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting901202014-1Project Controls1.333333393.3333 | Corbiere and Sons Contracting901202014-1Project Controls1.333333393.3333Inv#006R01 |  | WF1 Mob/Demob | WF1 Mob/Demob |  | 0.5 | 0.5 | 46.6666 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 901 | 202014-1 | 53510111 | Access | 0 | Project Controls | 70 | 1.3333 | HR |  |  | 70 | 0 | 93.3333 | 12.1333 | 105.4666 | 2020-01-04 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  | 53510106 Splitted cost to 53510102, 53510104, 53510107, 53510111, 53520101, 53520102, 53520104, 53560101, 53560103- these codes had cost on the given day |  |  |  |  | Project supervision |  |  |  | 0 |  |  | 36 | 43841 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting901202014-1Project Controls1.333333393.3333 | Corbiere and Sons Contracting901202014-1Project Controls1.333333393.3333Inv#006R01 |  | WF1 Mob/Demob |  |  | 0.5 | 0.5 | 46.6666 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 901 | 202014-1 | 53520101 | Clearing | 0 | Project Controls | 70 | 1.3333 | HR |  |  | 70 | 0 | 93.3333 | 12.1333 | 105.4666 | 2020-01-04 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | 53510106 Splitted cost to 53510102, 53510104, 53510107, 53510111, 53520101, 53520102, 53520104, 53560101, 53560103- these codes had cost on the given day |  |  |  |  | Project supervision |  |  |  | 0 |  |  | 36 | 43841 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting901202014-1Project Controls1.333333393.3333 | Corbiere and Sons Contracting901202014-1Project Controls1.333333393.3333Inv#006R01 |  | WF1 Mob/Demob | WF1-Merchantable Clearing |  | 0.5 | 0.5 | 46.6666 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 901 | 202014-1 | 53520102 | Clearing | 0 | Project Controls | 70 | 1.3333 | HR |  |  | 70 | 0 | 93.3333 | 12.1333 | 105.4666 | 2020-01-04 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | 53510106 Splitted cost to 53510102, 53510104, 53510107, 53510111, 53520101, 53520102, 53520104, 53560101, 53560103- these codes had cost on the given day |  |  |  |  | Project supervision |  |  |  | 0 |  |  | 36 | 43841 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting901202014-1Project Controls1.333333393.3333 | Corbiere and Sons Contracting901202014-1Project Controls1.333333393.3333Inv#006R01 |  | WF1 Mob/Demob | WF1-Non-merchantable Clearing |  | 0.5 | 0.5 | 46.6666 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 901 | 202014-1 | 53520104 | Clearing | 0 | Project Controls | 70 | 1.3333 | HR |  |  | 70 | 0 | 93.3333 | 12.1333 | 105.4666 | 2020-01-04 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  | 53510106 Splitted cost to 53510102, 53510104, 53510107, 53510111, 53520101, 53520102, 53520104, 53560101, 53560103- these codes had cost on the given day |  |  |  |  | Project supervision |  |  |  | 0 |  |  | 36 | 43841 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting901202014-1Project Controls1.333333393.3333 | Corbiere and Sons Contracting901202014-1Project Controls1.333333393.3333Inv#006R01 |  | WF1 Mob/Demob | WF1-Handfalling |  | 0.5 | 0.5 | 46.6666 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 901 | 202014-1 | 53510107 | Access | 0 | L.O.A. | 210 | 0.44444 | DAY |  |  |  | 0 | 93.3333 | 12.1333 | 105.4666 | 2020-01-04 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Access Mob/Demob |  | VC7556-2019-017 | TBD - waiting on PO |  | 53510106 Splitted cost to 53510102, 53510104, 53510107, 53510111, 53520101, 53520102, 53520104, 53560101, 53560103- these codes had cost on the given day |  |  |  |  | Project supervision |  |  |  | 0 |  |  | 36 | 43841 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting901202014-1L.O.A.0.444444493.3333 | Corbiere and Sons Contracting901202014-1L.O.A.0.444444493.3333Inv#006R01 |  | WF1 Mob/Demob | WF1 Mob/Demob |  | 0.5 | 0.5 | 46.6666 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 901 | 202014-1 | 53510111 | Access | 0 | L.O.A. | 210 | 0.44444 | DAY |  |  |  | 0 | 93.3333 | 12.1333 | 105.4666 | 2020-01-04 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  | 53510106 Splitted cost to 53510102, 53510104, 53510107, 53510111, 53520101, 53520102, 53520104, 53560101, 53560103- these codes had cost on the given day |  |  |  |  | Project supervision |  |  |  | 0 |  |  | 36 | 43841 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting901202014-1L.O.A.0.444444493.3333 | Corbiere and Sons Contracting901202014-1L.O.A.0.444444493.3333Inv#006R01 |  | WF1 Mob/Demob |  |  | 0.5 | 0.5 | 46.6666 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 901 | 202014-1 | 53520101 | Clearing | 0 | L.O.A. | 210 | 0.44444 | DAY |  |  |  | 0 | 93.3333 | 12.1333 | 105.4666 | 2020-01-04 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | 53510106 Splitted cost to 53510102, 53510104, 53510107, 53510111, 53520101, 53520102, 53520104, 53560101, 53560103- these codes had cost on the given day |  |  |  |  | Project supervision |  |  |  | 0 |  |  | 36 | 43841 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting901202014-1L.O.A.0.444444493.3333 | Corbiere and Sons Contracting901202014-1L.O.A.0.444444493.3333Inv#006R01 |  | WF1 Mob/Demob | WF1-Merchantable Clearing |  | 0.5 | 0.5 | 46.6666 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 901 | 202014-1 | 53520102 | Clearing | 0 | L.O.A. | 210 | 0.44444 | DAY |  |  |  | 0 | 93.3333 | 12.1333 | 105.4666 | 2020-01-04 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO |  | 53510106 Splitted cost to 53510102, 53510104, 53510107, 53510111, 53520101, 53520102, 53520104, 53560101, 53560103- these codes had cost on the given day |  |  |  |  | Project supervision |  |  |  | 0 |  |  | 36 | 43841 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting901202014-1L.O.A.0.444444493.3333 | Corbiere and Sons Contracting901202014-1L.O.A.0.444444493.3333Inv#006R01 |  | WF1 Mob/Demob | WF1-Non-merchantable Clearing |  | 0.5 | 0.5 | 46.6666 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 901 | 202014-1 | 53520104 | Clearing | 0 | L.O.A. | 210 | 0.44444 | DAY |  |  |  | 0 | 93.3333 | 12.1333 | 105.4666 | 2020-01-04 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO |  | 53510106 Splitted cost to 53510102, 53510104, 53510107, 53510111, 53520101, 53520102, 53520104, 53560101, 53560103- these codes had cost on the given day |  |  |  |  | Project supervision |  |  |  | 0 |  |  | 36 | 43841 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting901202014-1L.O.A.0.444444493.3333 | Corbiere and Sons Contracting901202014-1L.O.A.0.444444493.3333Inv#006R01 |  | WF1 Mob/Demob | WF1-Handfalling |  | 0.5 | 0.5 | 46.6666 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 902 | 202014-2 | 53520102 | Clearing | 0 | Loader JD 524 to 624 or equal | 99 | 5 | HR | 74.25 | 0 |  |  | 495 | 64.35 | 559.35 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | General Yard Maintenance |  |  | General Yard Maintenance | 0 |  |  | 36 | 43841 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting902202014-2Loader JD 524 to 624 or equal5495 | Corbiere and Sons Contracting902202014-2Loader JD 524 to 624 or equal5495Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 495 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 902 | 202014-2 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | General Yard Maintenance |  |  | General Yard Maintenance | 0 |  |  | 36 | 43841 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting902202014-2Light Truck - Pick up10300 | Corbiere and Sons Contracting902202014-2Light Truck - Pick up10300Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 902 | 202014-2 | 53520102 | Clearing | 0 | Operator - Apprentice | 60 | 10 | HR |  |  |  | 0 | 600 | 78 | 678 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | General Yard Maintenance |  |  | General Yard Maintenance | 0 |  |  | 36 | 43841 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting902202014-2Operator - Apprentice10600 | Corbiere and Sons Contracting902202014-2Operator - Apprentice10600Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 903 | 202014-3 | 53510111 | Access | 0 | Dozer D6 or equal | 135 | 10 | HR | 101.25 | 0 |  |  | 1350 | 175.5 | 1525.5 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 14 | Approved | snow removal on assembly and crane pads - ongoing | 9013 | Clearing Pads for Valard |  |  | MacKenzie East - A30 to A035 | 0 |  |  | 36 | 43841 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting903202014-3Dozer D6 or equal101350 | Corbiere and Sons Contracting903202014-3Dozer D6 or equal101350Inv#006R01 | [5 empty] | 1 | 1350 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 903 | 202014-3 | 53510111 | Access | 0 | Operator - Principle | 90 | 11 | HR |  |  |  | 0 | 990 | 128.7 | 1118.7 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 14 | Approved | snow removal on assembly and crane pads - ongoing | 9013 | Clearing Pads for Valard |  |  | MacKenzie East - A30 to A035 | 0 |  |  | 36 | 43841 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting903202014-3Operator - Principle11990 | Corbiere and Sons Contracting903202014-3Operator - Principle11990Inv#006R01 | [5 empty] | 1 | 990 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 903 | 202014-3 | 53510111 | Access | 0 | L.O.A. | 210 | 1 | DAY |  |  |  | 0 | 210 | 27.3 | 237.3 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 1 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO |  |  | 14 | Approved | snow removal on assembly and crane pads - ongoing | 9013 | Clearing Pads for Valard |  |  | MacKenzie East - A30 to A035 | 0 |  |  | 36 | 43841 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting903202014-3L.O.A.1210 | Corbiere and Sons Contracting903202014-3L.O.A.1210Inv#006R01 | [5 empty] | 1 | 210 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 904 | 202014-4 | 53520102 | Clearing | 0 | Brusher | 202.5 | 9 | HR | 151.88 | 0 |  |  | 1822.5 | 236.925 | 2059.425 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Raking and Brushing Towards A036 and 5 Orientations |  |  |  | 0 |  |  | 36 | 43841 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting904202014-4Brusher91822.5 | Corbiere and Sons Contracting904202014-4Brusher91822.5Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1822.5 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 904 | 202014-4 | 53520102 | Clearing | 0 | Excavator - 36 ton | 171 | 18 | HR | 128.25 | 0 |  |  | 3078 | 400.14 | 3478.14 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Raking and Brushing Towards A036 and 5 Orientations |  |  |  | 0 |  |  | 36 | 43841 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting904202014-4Excavator - 36 ton183078 | Corbiere and Sons Contracting904202014-4Excavator - 36 ton183078Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 3078 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 904 | 202014-4 | 53520102 | Clearing | 0 | Light Truck - Pick up | 30 | 10 | HR | 22.5 | 0 |  |  | 300 | 39 | 339 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Raking and Brushing Towards A036 and 5 Orientations |  |  |  | 0 |  |  | 36 | 43841 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting904202014-4Light Truck - Pick up10300 | Corbiere and Sons Contracting904202014-4Light Truck - Pick up10300Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 300 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 904 | 202014-4 | 53520102 | Clearing | 0 | Operator - Principle | 90 | 58 | HR |  |  |  | 0 | 5220 | 678.6 | 5898.6 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Raking and Brushing Towards A036 and 5 Orientations |  |  |  | 0 |  |  | 36 | 43841 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting904202014-4Operator - Principle585220 | Corbiere and Sons Contracting904202014-4Operator - Principle585220Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 5220 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 904 | 202014-4 | 53520102 | Clearing | 0 | L.O.A. | 210 | 7 | DAY |  |  |  | 0 | 1470 | 191.1 | 1661.1 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Raking and Brushing Towards A036 and 5 Orientations |  |  |  | 0 |  |  | 36 | 43841 | [5 empty] | Mike Lecocq | 01 | Corbiere and Sons Contracting904202014-4L.O.A.71470 | Corbiere and Sons Contracting904202014-4L.O.A.71470Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 1470 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 907 | 202014-7 | 53510111 | Access | 0 | Grader - Cat 12 to 14 or equal | 126 | 27 | HR | 94.5 | 0 |  |  | 3402 | 442.26 | 3844.26 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Rd. Building from A081; A094-A095 and down to A091-A092 |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43844 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting907202014-7Grader - Cat 12 to 14 or equal273402 | Corbiere and Sons Contracting907202014-7Grader - Cat 12 to 14 or equal273402Inv#006R01 | [5 empty] | 1 | 3402 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 907 | 202014-7 | 53510111 | Access | 0 | Sander Truck | 112.5 | 10 | HR | 84.38 | 0 |  |  | 1125 | 146.25 | 1271.25 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Rd. Building from A081; A094-A095 and down to A091-A092 |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43844 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting907202014-7Sander Truck101125 | Corbiere and Sons Contracting907202014-7Sander Truck101125Inv#006R01 | [5 empty] | 1 | 1125 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 907 | 202014-7 | 53510111 | Access | 0 | Light Truck - Pick up | 30 | 20 | HR | 22.5 | 0 |  |  | 600 | 78 | 678 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Rd. Building from A081; A094-A095 and down to A091-A092 |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43844 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting907202014-7Light Truck - Pick up20600 | Corbiere and Sons Contracting907202014-7Light Truck - Pick up20600Inv#006R01 | [5 empty] | 1 | 600 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 907 | 202014-7 | 53510111 | Access | 0 | Tractor Trailer - 60 Ton | 135 | 10 | HR | 101.25 | 0 |  |  | 1350 | 175.5 | 1525.5 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Rd. Building from A081; A094-A095 and down to A091-A092 |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43844 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting907202014-7Tractor Trailer - 60 Ton101350 | Corbiere and Sons Contracting907202014-7Tractor Trailer - 60 Ton101350Inv#006R01 | [5 empty] | 1 | 1350 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 907 | 202014-7 | 53510111 | Access | 0 | Foreman | 95 | 12 | HR |  |  |  | 0 | 1140 | 148.2 | 1288.2 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Rd. Building from A081; A094-A095 and down to A091-A092 |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43844 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting907202014-7Foreman121140 | Corbiere and Sons Contracting907202014-7Foreman121140Inv#006R01 | [5 empty] | 1 | 1140 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 907 | 202014-7 | 53510111 | Access | 0 | Operator - Principle | 90 | 44 | HR |  |  |  | 0 | 3960 | 514.8 | 4474.8 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Rd. Building from A081; A094-A095 and down to A091-A092 |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43844 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting907202014-7Operator - Principle443960 | Corbiere and Sons Contracting907202014-7Operator - Principle443960Inv#006R01 | [5 empty] | 1 | 3960 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 907 | 202014-7 | 53510111 | Access | 0 | Operator - Intermdiate | 75 | 11 | HR |  |  | 70 | 0 | 825 | 107.25 | 932.25 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Rd. Building from A081; A094-A095 and down to A091-A092 |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43844 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting907202014-7Operator - Intermdiate11825 | Corbiere and Sons Contracting907202014-7Operator - Intermdiate11825Inv#006R01 | [5 empty] | 1 | 825 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 907 | 202014-7 | 53510111 | Access | 0 | Labourer - General | 65 | 11 | HR |  |  |  | 0 | 715 | 92.95 | 807.95 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Rd. Building from A081; A094-A095 and down to A091-A092 |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43844 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting907202014-7Labourer - General11715 | Corbiere and Sons Contracting907202014-7Labourer - General11715Inv#006R01 | [5 empty] | 1 | 715 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 907 | 202014-7 | 53510111 | Access | 0 | L.O.A. | 210 | 7 | DAY |  |  |  | 0 | 1470 | 191.1 | 1661.1 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Winter Access Maintenance |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Rd. Building from A081; A094-A095 and down to A091-A092 |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43844 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting907202014-7L.O.A.71470 | Corbiere and Sons Contracting907202014-7L.O.A.71470Inv#006R01 | [5 empty] | 1 | 1470 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 908 | 202014-8 | 53520102 | Clearing | 0 | Brusher | 202.5 | 18 | HR | 151.88 | 0 |  |  | 3645 | 473.85 | 4118.85 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling at A080 and A085; Grinding of Material at A080 and A086; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43842 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting908202014-8Brusher183645 | Corbiere and Sons Contracting908202014-8Brusher183645Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 3645 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 908 | 202014-8 | 53520102 | Clearing | 0 | Grinder - 4710 Peterson or equal | 556.8 | 18 | HR | 417.6 | 0 |  |  | 10022.4 | 1302.912 | 11325.312 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling at A080 and A085; Grinding of Material at A080 and A086; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43842 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting908202014-8Grinder - 4710 Peterson or equal1810022.4 | Corbiere and Sons Contracting908202014-8Grinder - 4710 Peterson or equal1810022.4Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 10022.4 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 908 | 202014-8 | 53520102 | Clearing | 0 | Log Loader | 153 | 18 | HR | 114.75 | 0 |  |  | 2754 | 358.02 | 3112.02 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Non-merchantable Clearing |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling at A080 and A085; Grinding of Material at A080 and A086; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43842 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting908202014-8Log Loader182754 | Corbiere and Sons Contracting908202014-8Log Loader182754Inv#006R01 |  |  | WF1-Non-merchantable Clearing |  |  | 1 | 2754 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 908 | 202014-8 | 53520104 | Clearing | 0 | Chainsaw and consummables | 120 | 6 | Day |  | 0 |  |  | 720 | 93.6 | 813.6 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling at A080 and A085; Grinding of Material at A080 and A086; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43842 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting908202014-8Chainsaw and consummables6720 | Corbiere and Sons Contracting908202014-8Chainsaw and consummables6720Inv#006R01 |  |  | WF1-Handfalling |  |  | 1 | 720 |  | #N/A
Corbiere and Sons Contracting | 6 | 0 | 908 | 202014-8 | 53520104 | Clearing | 0 | Chainsaw and consummables | 120 | 5 | Day |  | 0 |  |  | 600 | 78 | 678 | 2020-01-10 | 1 | Inv#006R01 | 43857 | 84 | 0 | 0 | Terrance Bob | Hand Falling |  | VC7556-2019-017 | TBD - waiting on PO | [6 empty] | Handfelling at A080 and A085; Grinding of Material at A080 and A086; |  |  | Wind Farm - A080 to A117 | 0 |  |  | 37 | 43842 | [5 empty] | Harold Furlong | 01 | Corbiere and Sons Contracting908202014-8Chainsaw and consummables5600 | Corbiere and Sons Contracting908202014-8Chainsaw and consummables5600Inv#006R01 |  |  | WF1-Handfalling |  |  | 1 | 600 |  | #N/A